## Slide 1: AESO Cluster 2 Process Overview
January 2025

## Slide 2
Purpose
Public
The purpose of this presentation is to provide Market Participants with a high-level overview of AESO’s Cluster 2 process including timelines and deliverables for the Preliminary Assessment Stage (Stage 1) and Detailed Assessment Stage (Stage 2).

## Slide 3
Cluster 2 Applications
Public
The AESO received more than 100 applications for Cluster 2.
The review of these applications took place in November and December 2024 and projects that met the requirements for acceptance into Cluster 2 are included on the January 2025 Connection Project List.
96 projects, totaling over 17 GW of supply, have been accepted to proceed to Stage 1
  For information about these projects, see the Project Dashboard, List, and Map, which can be found on the Connection Project Reporting page on the AESO website.

## Slide 4: Cluster 2 Timeline
Note: Dates may be adjusted as needed as Cluster 2 progresses.
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
2024 |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  | 2026 |  | 
$
$
$
SASR Deadline
Required Deliverables Due
$
Stage 0
Stage 2
Stage 1
Cluster 3
Project List Published
Assessment Package Issued

## Slide 5: Timeline Summary
Deliverable | Target Date
Stage 1 | 
Draft Preliminary Study Scopes Issued | January 17, 2025
Study Scope comments due | February 3, 2035
Preliminary Assessment Package issued | June 18, 2025
Detailed Assessment Fee invoice issued | June 18, 2025
Change Proposal Submissions Due | July 4, 2025
Detailed Assessment Fee Due | July 18, 2025
Stage 2 | 
Detailed Assessment Package issued | December 2025
Change Proposal Submissions Due | February 2026
GUOC evidence/payment & TFO Stage 3&4 Security | Q1 2026

## Slide 6: Stage 1 – Preliminary Assessment
Project Plan
Draft Preliminary Assessment Study Scope
  Provided by the AESO January 17, 2025. MP comments due February 3, 2025
Dynamic model review
At the end of Stage 1, AESO will issue Preliminary Assessment Package, consisting of
  Preliminary Assessment Report
  Class 5 Cost Estimate (+100/-50%)
  High Level Congestion Estimate
  Detailed Assessment Fee Invoice

## Slide 7: Stage 2 – Detailed Assessment
Detailed Assessment Package
  Project-Specific Detailed Assessment Report
    Power flow, short circuit, and stability results for the study area
    Mitigation measures/list of RAS and Preferred connection alternative
    Discussion on conceptual long-term transmission plans in the area
    Facility Scope and Updated Class 5 Estimate
  Congestion assessments and Conceptual System Plans will be posted on AESO website.

## Slide 8: Stage 2 – Detailed Assessment
Project Change Proposals can be submitted upon issuance of Detailed Assessment Packages
MP Decision
  GUOC Evidence or Payment (BTF) or Security (Connection)
    Project Inclusion Status
  Stage 3 & 4 security provided to the TFO
  Reassessment Fee incurred if project cancels

## Slide 9: Process Beyond Stage 2
Stage 3 – Functional Specification, SAS contract execution, regulatory preparation (if applicable)
Stage 4 – AUC applications (if applicable)
Stage 5 – Construction
Stage 6 – Close Out

## Slide 10: Next Steps
AESO will issue draft preliminary assessment study scopes on January 17th
Study scope comments submission – February 3, 2025
For project-specific questions, please reach out to your respective AESO PM.
AESO PMs will conduct project-specific kick-off meetings late January-early February.
Upon request, AESO PMs can also schedule further process discussions with interested Market Participants.
If you haven’t already done so, please bookmark the AESO’s Cluster Assessment page and sign up for the AESO’s Stakeholder Newsletter to stay informed.

## Slide 11: Thank You