## AESO Connection Pro - Data List
Project | Subproject | Project Type | Planning Area | STS MW Change | DTS MW Change | MW Type | Process Stage | Planned ISD | Applied On
P0513 Pteragen Peace Butte Wind Farm | 1 | Connection | 4-Medicine Hat | 119.7 | 0.1 | Wind | 5 | 2022-12-01 16:00 | 2005-10-14
P0479 Naturener Wild Rose 1 Wind Farm | 1 | Connection | 4-Medicine Hat | 217.6 | 4 | Wind | 5 | 2022-08-15 16:00 | 2005-05-12
P0693 Naturener Wild Rose 2 Wind Farm | 1 | Connection | 4-Medicine Hat | 192 | 4 | Wind | 5 | 2022-08-15 16:00 | 2007-04-03 10:00
P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 2 | Connection | 37-Provost | 0 | 25 | Load | 5 | 2020-11-01 | 2008-08-22
P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2020-11-01 | 2008-08-22
P0863 TransCanada Keystone KXL Pumpstation #3-Current | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08
P0864 TransCanada Keystone KXL Pumpstation #4-Armitage | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08
P0865 TransCanada Keystone KXL Pumpstation #5-Cavendish | 1 | Connection | 48-Empress | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08
P1080 Old Elm Wind Farm | 1 | Connection | 55-Glenwood | 60 | 0 | Wind | 3 | 2022-10-31 16:00 | 2010-04-29
P1250 Enel Grizzly Bear Wind | 1 | Connection | 13-Lloydminster | 120 | 1.5 | Wind | 5 | 2021-10-01 16:00 | 2011-08-02 10:00
P0803 Mustus Energy Biomass Generator | 1 | Connection | 18-High Level | 41.5 | 0 | Biomass | 5 | 2023-06-15 16:00 | 2011-11-09
P1289 Maxim Power Deerland Peaking Station | 1 | Connection | 33-Fort Saskatchewan | 185.8 | 0 | Gas Turbine | 5 | 2020-12-01 16:00 | 2011-12-02
P1290 Whitetail Peaking Station | 1 | Connection | 19-Peace River | 0 | 1 | Gas | 5 | 2019-12-31 16:00 | 2011-12-07
P1290 Whitetail Peaking Station | 2 | Connection | 19-Peace River | 200 | 0 | Gas | 5 | 2019-12-31 16:00 | 2011-12-07
P1410 ATCO Heartland Pump Station Connection | 2 | Connection | 56-Vegreville | 0 | 20 | Load | 5 | 2020-11-01 | 2013-02-05 10:00
P1412 Trans Mountain Pipeline Gainford Substation 16501S | 1 | Connection | 40-Wabamun | 0 | 11 | Load | 5 | 2022-06-01 16:00 | 2013-02-11 10:00
P1440 CP Genesee Generating Units 4 & 5 | 1 | Connection | 60-Edmonton | 0 | 50 | Combined Cycle | 5 | 2021-02-01 16:00 | 2013-04-30 10:00
P1440 CP Genesee Generating Units 4 & 5 | 2 | Connection | 60-Edmonton | 505 | 0 | Combined Cycle | 5 | 2022-03-31 16:00 | 2013-04-30 10:00
P1440 CP Genesee Generating Units 4 & 5 | 3 | Connection | 60-Edmonton | 505 | 0 | Combined Cycle | 5 | 2023-03-31 16:00 | 2013-04-30 10:00
P1442 Fortis New Anthony Henday Substation | 1 | Connection | 60-Edmonton | 0 | 21 | Load | 5 | 2022-06-01 16:00 | 2013-05-02 10:00
P1460 Fortis New Hornbeck Substation | 1 | Connection | 29-Hinton/Edson | 0 | 18 | Load | 5 | 2022-06-01 16:00 | 2013-07-22 10:00
P1500 Renewable Energy Service WAGF | 1 | Connection | 53-Fort Macleod | 47 | 1 | Wind | 5 | 2022-11-30 16:00 | 2013-11-18 10:00
P1505 ATCO City of Grande Prairie New POD | 1 | Connection | 20-Grande Prairie | 0 | 15.5 | Load | 5 | 2021-06-01 16:00 | 2013-12-10 10:00
P1533 Joss MPC WAGF | 1 | Connection | 48-Empress | 120 | 0 | Wind | 5 | 2020-08-15 16:00 | 2014-03-01
P1566 Calgary Energy Centre Peaking Plant New Generator Capacity | 1 | Connection | 6-Calgary | 150 | 1 | Simple Cycle | 5 | 2021-12-01 16:00 | 2014-06-03
P1567 EDPR Sharp Hills Wind Farm | 1 | Connection | 42-Hanna | 248.4 | 1 | Wind | 5 | 2020-11-15 | 2014-06-04
P1567 EDPR Sharp Hills Wind Farm | 2 | Connection | 42-Hanna | 51.6 | 0 | Wind | 5 | 2020-11-15 | 2014-06-04
P1647 Fengate Strathcona Cogeneration | 1 | Connection | 33-Fort Saskatchewan | 0 | 65 | Cogen | 5 | 2020-03-01 | 2015-02-13 10:00
P1647 Fengate Strathcona Cogeneration | 2 | Connection | 33-Fort Saskatchewan | 60 | 0 | Cogen | 5 | 2020-10-01 16:00 | 2015-02-13 10:00
P1649 EPCOR Garneau Area Upgrade | 1 | Connection | 60-Edmonton | 0 | 0 | Load | 4 | 2020-06-30 16:00 | 2015-02-20 10:00
P1649 EPCOR Garneau Area Upgrade | 2 | Connection | 60-Edmonton | 0 | 20.9 | Load | 4 | 2022-09-30 16:00 | 2015-02-20 10:00
P1659 EPCOR Strathcona Capacity Increase | 1 | Connection | 60-Edmonton | 0 | 14.2 | Load | 5 | 2020-06-01 16:00 | 2015-03-19 10:00
P1695 EPCOR Riverview Substation New POD | 1 | Connection | 60-Edmonton | 0 | 24 | Load | 5 | 2020-02-04 16:00 | 2015-08-24 10:00
P1698 Joss Jenner WAGF - Phase 2 | 1 | BTF | 48-Empress | 180 | 0 | Wind | 5 | 2020-08-15 16:00 | 2015-09-08 10:00
P1704 Paintearth Wind Power | 1 | Connection | 42-Hanna | 150 | 1 | Wind | 4 | 2021-09-30 16:00 | 2015-10-08 10:00
P1710 Capital Power Halkirk 2 Wind | 1 | Connection | 36-Alliance/Battle River | 150 | 1.8 | Wind | 3 | 2022-09-30 16:00 | 2015-10-22 10:00
P1718 Wheatland WAGF Project | 1 | Connection | 43-Sheerness | 120 | 0 | Wind | 5 | 2019-12-31 16:00 | 2015-10-30
P1719 Stirling WAGF Project | 1 | Connection | 54-Lethbridge | 113 | 0 | Wind | 5 | 2020-09-15 16:00 | 2015-10-30
P1734 Suncor Forty Mile Maleb WAGF | 1 | Connection | 4-Medicine Hat | 200 | 0.3 | Wind | 5 | 2022-09-01 10:00 | 2016-01-06 10:00
P1740 Kineticor Peace River Power Generator | 1 | Connection | 19-Peace River | 93 | 2 | Gas | 2 | 2021-09-30 16:00 | 2016-01-07 10:00
P1756 TPG Canyon Creek PHES Storage Project | 1 | Connection | 29-Hinton/Edson | 75 | 64 | Pumped Storage | 3 | 2021-08-10 16:00 | 2016-03-02 10:00
P1770 NextEra Red Deer Battery Energy Storage System | 1 | Connection | 42-Hanna | 40 | 46 | Battery | 2 | 2020-12-01 16:00 | 2016-03-18 10:00
P1772 Ghost Pine Battery Energy Storage System | 1 | BTF | 42-Hanna | 0 | 34.7 | Battery | 2 | 2020-12-01 16:00 | 2016-03-18 10:00
P1780 Sequoia Energy Oyen MPC Wind | 1 | Connection | 42-Hanna | 100 | 1 | Wind | 2 | 2021-12-14 16:00 | 2016-04-06 10:00
P1782 Fortis Provost Reliability | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2021-05-01 | 2016-04-11 10:00
P1786 Sequoia Schuler WAGF (MPC) | 1 | Connection | 4-Medicine Hat | 100 | 1 | Wind | 2 | 2022-12-15 16:00 | 2016-04-13 10:00
P1800 Capital Power Whitla Wind Power Facility | 2 | Connection | 4-Medicine Hat | 97.2 | 1 | Wind | 5 | 2020-09-01 16:00 | 2016-05-25 10:00
P1812 Suncor Forty Mile Granlea WAGF | 1 | Connection | 4-Medicine Hat | 200 | 0.3 | Wind | 5 | 2020-06-01 10:00 | 2016-07-04 10:00
P1824 Lone Pine LP - Lone Pine WAGF | 1 | Connection | 42-Hanna | 172.8 | 1 | Wind | 2 | 2022-04-30 | 2016-07-28 10:00
P1828 HEP Capital Alderson Solar | 1 | Connection | 4-Medicine Hat | 100 | 1 | Solar | 2 | 2020-04-01 16:00 | 2016-07-29 10:00
P1831 Fortis 255S Vulcan Faribault Farms DG PV | 1 | BTF | 49-Stavely | 14 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-05 10:00
P1833 Fortis Tilley 498S DG Gas | 1 | BTF | 47-Brooks | 16 | 0 | Gas | 3 | 2021-07-01 16:00 | 2016-08-05 10:00
P1837 Fortis 498S Tilley DG PV | 1 | BTF | 52-Vauxhall | 14 | 0 | Solar | 5 | 2020-10-28 16:00 | 2016-08-05 10:00
P1838 Fortis 895S Suffield DG PV | 1 | BTF | 4-Medicine Hat | 23 | 0 | Solar | 5 | 2020-06-30 16:00 | 2016-08-05 10:00
P1839 Fortis 421S Hays DG PV | 1 | BTF | 52-Vauxhall | 15 | 0 | Solar | 5 | 2020-03-01 16:00 | 2016-08-05 10:00
P1839 Fortis 421S Hays DG PV | 2 | BTF | 52-Vauxhall | 0 | 0 | Solar | 5 | 2020-07-17 16:00 | 2016-08-05 10:00
P1840 Fortis 275S Jenner Solar DER | 1 | BTF | 48-Empress | 23 | 0 | Solar | 5 | 2020-11-12 16:00 | 2016-08-05 10:00
P1849 Fortis Burdett 368S DG P/V | 1 | BTF | 52-Vauxhall | 10.5 | 0 | Solar | 5 | 2020-07-15 16:00 | 2016-08-24 10:00
P1850 Fortis Coaldale 254S DER Solar 3 | 1 | BTF | 54-Lethbridge | 22 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-26 10:00
P1851 Fortis Monarch 492S DER Solar | 1 | BTF | 54-Lethbridge | 20 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-26 10:00
P1853 Fortis Buffalo Atlee Cluster 1 WAGF | 1 | BTF | 48-Empress | 18.3 | 0 | Wind | 5 | 2020-09-01 16:00 | 2016-08-30 10:00
P1856 NaturEner Buffalo Trail WAGF | 1 | Connection | 4-Medicine Hat | 100 | 3 | Wind | 2 | 2022-07-15 16:00 | 2016-09-01 10:00
P1857 NaturEner Ross Creek WAGF | 1 | Connection | 4-Medicine Hat | 100 | 3 | Wind | 2 | 2022-07-15 16:00 | 2016-09-01 10:00
P1858 Enterprise Prosperity Wind | 1 | Connection | 45-Strathmore/Blackie | 175 | 2 | Wind | 2 | 2022-12-31 | 2016-09-07 10:00
P1863 Northland Buffalo Trail WAGF | 1 | Connection | 28-Cold Lake | 100 | 1 | Wind | 2 | 2020-12-31 10:00 | 2016-09-16 10:00
P1866 Peace River Power Upgrade | 1 | BTF | 19-Peace River | 125 | 2 | Gas Turbine | 2 | 2021-09-30 16:00 | 2016-09-19 10:00
P1862 Fortis Spring Coulee 385S Solar DG | 1 | BTF | 55-Glenwood | 28.5 | 0 | Solar | 5 | 2020-11-30 16:00 | 2016-09-28 10:00
P1864 BowArk Drywood Gas Generator | 1 | Connection | 45-Strathmore/Blackie | 38 | 1 | Gas | 4 | 2021-01-31 10:00 | 2016-09-30 10:00
P1870 Fortis Stavely 349S DER Solar | 1 | BTF | 49-Stavely | 8.5 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-10-05 10:00
P1878 Fortis 257S Hull DER Solar | 2 | BTF | 52-Vauxhall | 17 | 0 | Solar | 5 | 2019-12-23 16:00 | 2016-10-24 10:00
P1879 Claresholm Solar Connection | 1 | Connection | 49-Stavely | 130 | 0.6 | Solar | 5 | 2020-06-30 16:00 | 2016-10-25 10:00
P1885 Joss Wind Northern Lights WAGF | 1 | Connection | 26-Swan Hills | 400 | 3 | Wind | 2 | 2020-11-01 | 2016-11-01 10:00
P1891 Archer Piikani Solar | 1 | Connection | 53-Fort Macleod | 40 | 0.1 | Solar | 2 | 2021-09-01 16:00 | 2016-11-07 10:00
P1892 Fortis Buffalo Atlee Cluster 3 WAGF DER | 1 | BTF | 48-Empress | 17.3 | 0 | Wind | 5 | 2020-09-01 16:00 | 2016-11-15 10:00
P1893 Red Deer River Solar | 1 | Connection | 35-Red Deer | 150 | 0.5 | Solar | 2 | 2020-12-01 16:00 | 2016-11-15 10:00
P1898 Pattern Lanfine North Wind | 1 | Connection | 42-Hanna | 145 | 0 | Wind | 3 | 2022-09-30 16:00 | 2016-12-02 10:00
P1902 FortisAlberta Fincastle Area Capacity and Reliability Project | 1 | Connection | 52-Vauxhall | 0 | 11.1 | Load | 5 | 2020-06-16 16:00 | 2016-12-20 10:00
P1908 TransAlta Cowley Ridge 1 Wind | 1 | BTF | 53-Fort Macleod | 21 | 0.5 | Wind | 5 | 2020-12-31 16:00 | 2016-12-22 10:00
P1909 TransAlta Garden Plain Wind | 1 | Connection | 42-Hanna | 130 | 4 | Wind | 3 | 2020-12-11 16:00 | 2016-12-22 10:00
P1913 Glenridge Wind | 1 | Connection | 43-Sheerness | 150 | 1 | Wind | 2 | 2020-10-01 10:00 | 2017-01-19 10:00
P1918 FortisAlberta Conrad DER Solar 1 | 1 | BTF | 52-Vauxhall | 18.4 | 0 | Solar | 3 | 2020-08-14 16:00 | 2017-02-06 10:00
P1922 FortisAlberta Vauxhall Solar DER | 2 | BTF | 52-Vauxhall | 17 | 0 | Solar | 5 | 2019-12-23 16:00 | 2017-03-14 10:00
P1926 Solar Krafte Vauxhall | 1 | Connection | 52-Vauxhall | 150 | 0.4 | Solar | 3 | 2021-06-30 16:00 | 2017-03-23 10:00
P1927 Solar Krafte Brooks | 1 | Connection | 47-Brooks | 400 | 1 | Solar | 3 | 2021-06-30 16:00 | 2017-03-23 10:00
P1928 RealPart Calgary Area Solar | 1 | Connection | 6-Calgary | 150 | 0.3 | Solar | 2 | 2020-12-20 16:00 | 2017-03-24 10:00
P1932 FortisAlberta Namaka DER Solar | 1 | BTF | 45-Strathmore/Blackie | 15.5 | 0 | Solar | 3 | 2020-06-15 16:00 | 2017-04-10 10:00
P1959 FortisAlberta Conrad DER Solar 2 | 1 | BTF | 52-Vauxhall | 18 | 0 | Solar | 3 | 2020-08-14 16:00 | 2017-05-08 10:00
P1967 FortisAlberta Jenner 275S DER | 1 | BTF | 48-Empress | 16.1 | 0 | Gas | 5 | 2021-02-28 | 2017-06-06 10:00
P1978 ATCO Michichi DER Solar | 1 | BTF | 42-Hanna | 61 | 0 | Solar | 2 | 2020-11-01 16:00 | 2017-06-20 10:00
P1981 NextEra Buffalo Trail Solar | 1 | Connection | 37-Provost | 70 | 0.5 | Solar | 2 | 2020-11-01 | 2017-07-07 10:00
P1982 EDTI DG Solar BTF | 1 | BTF | 60-Edmonton | 0 | 0 | Solar | 3 | 2021-01-31 | 2017-07-07 10:00
P1984 FortisAlberta Gleichen DG Solar | 1 | BTF | 45-Strathmore/Blackie | 17 | 0 | Solar | 3 | 2020-06-15 16:00 | 2017-07-17 10:00
P1987 Solar Krafte Rainier | 1 | Connection | 47-Brooks | 450 | 1.1 | Solar | 2 | 2020-11-15 | 2017-07-28 10:00
P1991 ENMAX Zephyr MPC Wind | 1 | Connection | 52-Vauxhall | 200 | 1 | Wind | 2 | 2020-12-01 10:00 | 2017-08-14 10:00
P1995 ATCO Coronation 773S Solar DG | 1 | BTF | 42-Hanna | 12 | 0 | Solar | 2 | 2020-09-30 16:00 | 2017-08-30 10:00
P2000 ENMAX Taber BTF Wind | 1 | BTF | 52-Vauxhall | 21 | 0 | Wind | 2 | 2020-12-01 16:00 | 2017-09-18 10:00
P2002 Soventix Forestburg Area Solar | 1 | Connection | 36-Alliance/Battle River | 40 | 0.1 | Solar | 2 | 2020-01-20 16:00 | 2017-09-25 10:00
P2003 Pattern Development Lanfine South Wind | 1 | Connection | 42-Hanna | 140.4 | 1.5 | Wind | 2 | 2022-09-30 16:00 | 2017-09-25 10:00
P2007 Chiniki Solar | 1 | Connection | 44-Seebe | 40 | 0.3 | Solar | 2 | 2021-11-30 16:00 | 2017-10-02 10:00
P2008 Greengate Lathom MPC Solar | 1 | Connection | 47-Brooks | 120 | 0.5 | Solar | 2 | 2020-12-01 16:00 | 2017-10-20 10:00
P2009 Greengate Travers MPC Solar | 1 | Connection | 49-Stavely | 400 | 0.5 | Solar | 4 | 2020-12-01 16:00 | 2017-10-20 10:00
P2012 Keyera West Pembina 359S Gas Turbine | 1 | BTF | 30-Drayton Valley | 4.9 | 0 | Gas Turbine | 5 | 2020-02-01 | 2017-10-25 10:00
P2023 FortisAlberta Kananaskis Area Reliability | 1 | Connection | 44-Seebe | 0 | 4.7 | Load | 6 | 2019-12-12 16:00 | 2017-11-22 10:00
P2021 Suncor TG1 & TG2 Testing and Commissioning | 1 | BTF | 25-Fort McMurray | 0 | 0 | Equipment Change | 6 | 2020-02-04 16:00 | 2017-11-27 10:00
P2028 FortisAlberta Barrhead-Westlock Area Reliability | 1 | Connection | 40-Wabamun | 0 | 0 | Load | 3 | 2020-12-01 16:00 | 2017-12-05 10:00
P2029 FortisAlberta Strathmore 151S DER Solar 1 | 1 | BTF | 45-Strathmore/Blackie | 16.7 | 0 | Solar | 3 | 2020-11-15 16:00 | 2017-12-06 10:00
P2030 FortisAlberta Strathmore 151S DER Solar 2 | 1 | BTF | 45-Strathmore/Blackie | 19.5 | 0 | Solar | 3 | 2020-11-15 16:00 | 2017-12-07 10:00
P2031 ATCO M.D. of Greenview Load | 1 | Connection | 22-Grande Cache | 0 | 20 | Load | 3 | 2020-12-01 16:00 | 2018-01-02 10:00
P2032 Cascade Combined Cycle | 1 | Connection | 29-Hinton/Edson | 450 | 11.5 | Combined Cycle | 3 | 2021-01-02 16:00 | 2018-01-02 10:00
P2032 Cascade Combined Cycle | 2 | Connection | 29-Hinton/Edson | 450 | 0 | Combined Cycle | 3 | 2022-01-02 | 2018-01-02 10:00
P2034 Cold Lake Area Energy Centre | 1 | Connection | 28-Cold Lake | 100 | 30 | Cogen | 3 | 2020-10-01 16:00 | 2018-01-02 10:00
P2035 FortisAlberta Willesdengreen DER Gas Turbine | 1 | BTF | 30-Drayton Valley | 1.3 | 0 | Gas | 3 | 2020-03-01 | 2018-01-02 10:00
P2037 FortisAlberta Taber 83S DER Solar | 1 | BTF | 52-Vauxhall | 16 | 0 | Solar | 2 | 2020-05-01 16:00 | 2018-01-08 10:00
P2041 TransAlta Windrise MPC Wind | 1 | Connection | 53-Fort Macleod | 220 | 3 | Wind | 4 | 2020-12-17 16:00 | 2018-01-12 10:00
P2050 Enbridge Abee 993S Upgrade | 1 | Connection | 27-Athabasca/Lac La Biche | 0 | 13 | Load | 4 | 2021-03-01 16:00 | 2018-02-05 10:00
P2057 Imperial Oil Edmonton 95S Cogen | 1 | BTF | 60-Edmonton | 0 | 0 | Cogen | 5 | 2019-12-13 16:00 | 2018-02-15 10:00
P2057 Imperial Oil Edmonton 95S Cogen | 2 | BTF | 60-Edmonton | 0 | 0 | Cogen | 5 | 2020-05-13 16:00 | 2018-02-15 10:00
P2059 ATCO Three Hills 770S DER Solar 1 | 1 | BTF | 42-Hanna | 14 | 0 | Solar | 3 | 2020-09-30 16:00 | 2018-02-20 10:00
P2060 ATCO Three Hills 770S DER Solar 2 | 1 | BTF | 42-Hanna | 25 | 0 | Solar | 3 | 2020-09-30 16:00 | 2018-02-20 10:00
P2061 ATCO Michichi Creek 802S DER Solar | 1 | BTF | 42-Hanna | 11 | 0 | Solar | 3 | 2020-09-30 16:00 | 2018-02-20 10:00
P2065 Enel Grizzly Bear Wind Phase 2 | 1 | BTF | 13-Lloydminster | 30 | 0 | Wind | 2 | 2021-10-01 16:00 | 2018-03-09 10:00
P2068 Four Rivers Wind | 1 | Connection | 4-Medicine Hat | 450 | 0.5 | Wind | 2 | 2021-03-31 16:00 | 2018-03-26 10:00
P2074 FortisAlberta Spruce Grove Area Load | 1 | Connection | 60-Edmonton | 0 | 240 | Load | 2 | 2020-09-11 16:00 | 2018-04-06 10:00
P2076 ATCO Thornton 2091S Contract Change | 1 | Contract | 22-Grande Cache | 0 | 12.1 | DTS | 2 | 2020-02-01 | 2018-04-09 10:00
P2078 FortisAlberta Taber 83S DER Solar | 1 | BTF | 52-Vauxhall | 14 | 0 | Solar | 2 | 2020-05-01 16:00 | 2018-04-11 10:00
P2082 Suncor Base Plant Cogen | 1 | Connection | 25-Fort McMurray | 815 | 0 | Cogen | 3 | 2021-07-01 16:00 | 2018-04-24 10:00
P2086 FortisAlberta Brooks 121S DER Solar (83L) | 1 | BTF | 47-Brooks | 13 | 0 | Solar | 5 | 2020-12-31 16:00 | 2018-05-14 10:00
P2092 FortisAlberta Brooks 121S DER Solar (257LE) | 1 | BTF | 47-Brooks | 12 | 0 | Solar | 5 | 2020-12-31 16:00 | 2018-05-14 10:00
P2091 EDP Renewables Blue Bridge Solar | 1 | Connection | 48-Empress | 150 | 5 | Solar | 2 | 2020-10-01 16:00 | 2018-05-22 10:00
P2096 CKPC Petrochemical Facility | 1 | Connection | 33-Fort Saskatchewan | 0 | 30 | Load | 3 | 2021-07-31 | 2018-05-24 10:00
P2097 FortisAlberta Innisfail 214S DER Solar | 1 | BTF | 39-Didsbury | 4.3 | 0 | Solar | 5 | 2019-12-15 | 2018-05-28 10:00
P2098 TransAlta Tempest MPC Wind | 1 | Connection | 54-Lethbridge | 115 | 1 | Wind | 2 | 2020-12-01 16:00 | 2018-05-29 10:00
P2102 EPC East Calgary Area Reliability | 1 | Connection | 6-Calgary | 0 | 26 | Load | 2 | 2021-07-30 16:00 | 2018-06-07 10:00
P2105 ATCO Merritt Area Load and Reliability | 1 | Connection | 20-Grande Prairie | 0 | 20 | Load | 2 | 2020-06-01 10:00 | 2018-06-18 10:00
P2108 FortisAlberta Entwistle 235S DER Gas | 1 | BTF | 40-Wabamun | 1.8 | 0 | Gas | 3 | 2020-03-01 | 2018-06-19 10:00
P2110 ATCO Power Poplar Hill Gas | 1 | BTF | 20-Grande Prairie | 32 | 0 | Gas Turbine | 5 | 2020-07-01 16:00 | 2018-06-26 10:00
P2119 FortisAlberta Coleman Area Reliability | 1 | Connection | 53-Fort Macleod | 0 | 0 | Other | 3 | 2021-03-01 16:00 | 2018-07-04 10:00
P2123 FortisAlberta Lethbridge Area Reliability | 1 | Connection | 54-Lethbridge | 0 | 0 | Other | 3 | 2020-07-01 16:00 | 2018-07-11 10:00
P2124 Northland Bow City MPC Solar | 1 | Connection | 47-Brooks | 400 | 2 | Solar | 2 | 2020-11-01 | 2018-07-11 10:00
P2122 Cypress Wind Project Connection | 1 | Connection | 4-Medicine Hat | 201.6 | 2.7 | Wind | 3 | 2021-06-01 16:00 | 2018-07-12 10:00
P2127 Suncor Base Plant Change | 1 | BTF | 25-Fort McMurray | 0 | 0 | Equipment Change | 5 | 2020-01-30 16:00 | 2018-07-17 10:00
P2133 EDTI Southeast Edmonton Area Load and Reliability | 1 | Connection | 60-Edmonton | 0 | 31 | Load | 2 | 2021-02-01 16:00 | 2018-08-07 10:00
P2134 CNRL Muskeg River 847S Change | 1 | BTF | 25-Fort McMurray | 0 | 0 | Other | 5 | 2021-06-30 16:00 | 2018-08-07 10:00
P2136 FortisAlberta Brazeau Area Reliability | 1 | Connection | 30-Drayton Valley | 0 | 5.4 | Load | 2 | 2020-09-01 16:00 | 2018-08-09 10:00
P2137 Enerfin Winnifred MPC Wind | 1 | Connection | 4-Medicine Hat | 90 | 1 | Wind | 3 | 2021-12-01 16:00 | 2018-08-10 10:00
P2138 Quill Rocky Mountain Gas | 1 | Connection | 30-Drayton Valley | 295 | 0.5 | Simple Cycle | 2 | 2020-09-01 16:00 | 2018-08-20 10:00
P2140 PBC Paul Band Solar | 1 | Connection | 40-Wabamun | 37 | 0.5 | Solar | 2 | 2020-07-01 16:00 | 2018-08-20 10:00
P2150 ATCO Power Valleyview Gas | 1 | BTF | 23-Valleyview | 32 | 0 | Gas Turbine | 3 | 2020-07-01 16:00 | 2018-09-07 10:00
P2151 CMH Central Area Upgrade | 1 | BTF | 4-Medicine Hat | 0 | 0 | Other | 5 | 2020-03-31 16:00 | 2018-09-07 10:00
P2155 ATCO Monitor 2 774S DER Solar | 1 | BTF | 38-Caroline | 21.6 | 0 | Solar | 2 | 2020-05-01 16:00 | 2018-09-14 10:00
P2158 Maxim Power Milner Change | 1 | BTF | 22-Grande Cache | 208 | 0 | Gas Turbine | 3 | 2020-02-01 16:00 | 2018-09-24 10:00
P2171 FortisAlberta Westfield 107S DER Solar | 1 | BTF | 52-Vauxhall | 18.4 | 9.3 | Solar | 3 | 2020-06-01 16:00 | 2018-10-22 10:00
P2176 FortisAlberta Acheson 305S DER Solar | 1 | BTF | 60-Edmonton | 8.5 | 0 | Solar | 2 | 2020-11-01 | 2018-10-29 10:00
P2177 FortisAlberta Red Deer 63S DER Solar | 1 | BTF | 35-Red Deer | 18.3 | 0 | Solar | 2 | 2020-12-31 17:00 | 2018-10-31 09:00
P2178 ATCO Green Stocking 925S Contract Change | 1 | Contract | 25-Fort McMurray | 0 | -16 | DTS | 3 | 2020-01-01 16:00 | 2018-11-08 09:00
P2179 ATCO 9L32/66 Change | 1 | Connection | 25-Fort McMurray | 0 | 0 | Equipment Change | 2 | 2021-06-30 16:00 | 2018-11-09 09:00
P2180 ATCO Rainbow Lake Gas | 1 | Connection | 17-Rainbow Lake | 55 | 0 | Gas Turbine | 3 | 2020-04-01 16:00 | 2018-11-16 09:00
P2183 ATCO Fieldgate 824S DER Gas | 1 | BTF | 26-Swan Hills | 10 | 0 | Gas | 3 | 2020-02-01 | 2018-11-19 09:00
P2184 EDTI Victoria Change | 1 | Connection | 60-Edmonton | 0 | 0 | Equipment Change | 6 | 2019-12-15 | 2018-11-21 09:00
P2189 ATCO Wood Buffalo Area Load Project | 1 | Connection | 25-Fort McMurray | 0 | 16.4 | Load | 2 | 2022-04-01 16:00 | 2018-11-30 10:00
P2192 ENMAX FMC Change | 1 | BTF | 6-Calgary | 0 | 0 | Cogen | 3 | 2020-05-25 16:00 | 2019-01-02 10:00
P2194 FortisAlberta East Crossfield 64S DER Solar | 1 | BTF | 57-Airdrie | 1.6 | 0 | Solar | 3 | 2021-03-01 16:00 | 2019-01-04 10:00
P2195 FortisAlberta Bassano 435S DER Solar | 1 | BTF | 47-Brooks | 9.7 | 0 | Solar | 2 | 2021-06-01 10:00 | 2019-01-07 10:00
P2196 Grand Prairie MPC Gas | 1 | Connection | 20-Grande Prairie | 360 | 5 | Combined Cycle | 2 | 2021-10-01 16:00 | 2019-01-11 10:00
P2198 TransAlta Summerview 2 Battery Storage | 1 | BTF | 53-Fort Macleod | 10 | 0 | Battery | 3 | 2020-06-23 16:00 | 2019-01-11 10:00
P2199 FortisAlberta Buffalo Atlee Cluster 2 | 1 | BTF | 48-Empress | 13.8 | 0 | Wind | 2 | 2020-09-01 16:00 | 2019-01-28 10:00
P2201 ENMAX SS-1 Substation Change | 1 | BTF | 6-Calgary | 0 | 0 | Other | 2 | 2024-01-01 16:00 | 2019-01-30 10:00
P2203 Enbridge South Terminal Gas | 1 | BTF | 60-Edmonton | 19.8 | 0 | Other | 3 | 2020-12-01 16:00 | 2019-02-07 10:00
P2206 Suncor Meadow Creek Cogen | 1 | Connection | 25-Fort McMurray | 60 | 4 | Cogen | 2 | 2022-07-01 10:00 | 2019-02-11 10:00
P2209 ATCO Monitor 1 774S DER Solar | 1 | BTF | 42-Hanna | 4 | 0 | Solar | 2 | 2020-05-01 16:00 | 2019-02-15 10:00
P2210 EDTI Strathcona Change | 1 | Connection | 60-Edmonton | 0 | 0 | Other | 5 | 2020-03-01 | 2019-02-19 10:00
P2211 ENGIE Buffalo Trail South MPC Wind | 1 | Connection | 4-Medicine Hat | 200 | 6 | Wind | 2 | 2021-12-24 16:00 | 2019-02-25 10:00
P2212 RESC Rattlesnake Ridge MPC Wind | 1 | Connection | 4-Medicine Hat | 150 | 1 | Wind | 3 | 2021-07-30 16:00 | 2019-02-28 10:00
P2213 FortisAlberta Eckville-Rimbey Area Reliability | 1 | Connection | 35-Red Deer | 0 | 0 | Equipment Change | 2 | 2022-12-31 16:00 | 2019-03-15 10:00
P2214 ATCO Rycroft 730S Battery DER | 1 | BTF | 20-Grande Prairie | 17 | 0 | Battery | 3 | 2020-07-01 16:00 | 2019-03-15 10:00
P2216 FortisAlberta Chappice Lake 649S DER Solar | 1 | BTF | 4-Medicine Hat | 10.5 | 0 | Solar | 3 | 2020-12-01 16:00 | 2019-03-22 10:00
P2217 FortisAlberta Marion 21S Contract Change | 1 | Contract | 40-Wabamun | 0 | 0 | DTS | 3 | 2021-10-31 16:00 | 2019-03-26 10:00
P2218 ENGIE Duchess Solar | 1 | Connection | 47-Brooks | 90 | 0.1 | Solar | 2 | 2021-09-15 16:00 | 2019-04-01 10:00
P2220 CMH Al Rothbauer 321S Contract Change | 1 | Contract | 4-Medicine Hat | 44 | 0 | STS | 2 | 2020-05-21 16:00 | 2019-04-08 10:00
P2222 ENMAX Crossfield CRS3 Battery Storage | 1 | BTF | 57-Airdrie | 0 | 0 | Battery | 3 | 2020-08-20 16:00 | 2019-04-08 10:00
P2224 Capital Power Genesee Unit 2 Change | 1 | BTF | 40-Wabamun | 0 | 0 | Other | 5 | 2020-05-01 16:00 | 2019-04-12 10:00
P2227 FortisAlberta Mearns Area Load | 1 | Connection | 60-Edmonton | 0 | 20 | Other | 2 | 2021-07-01 16:00 | 2019-04-23 10:00
P2228 FortisAlberta Sangudo Area Load | 1 | Connection | 40-Wabamun | 0 | 20 | Other | 2 | 2021-07-01 16:00 | 2019-04-23 10:00
P2229 FortisAlberta Whitecourt Area Load | 1 | Connection | 26-Swan Hills | 0 | 20 | Other | 2 | 2021-11-02 16:00 | 2019-04-23 10:00
P2231 FortisAlberta Ponoka 331S DER Solar | 1 | BTF | 31-Wetaskiwin | 4 | 0 | Solar | 3 | 2020-03-27 16:00 | 2019-05-03 10:00
P2232 ENGIE Buffalo Trail North MPC Wind | 1 | Connection | 4-Medicine Hat | 200 | 6 | Wind | 2 | 2021-11-02 16:00 | 2019-05-03 10:00
P2239 CMH Unit 17 Gas | 1 | BTF | 4-Medicine Hat | 0 | 0 | Gas Turbine | 2 | 2021-07-30 16:00 | 2019-05-03 10:00
P2233 FortisAlberta Jenner 275S Change | 1 | BTF | 48-Empress | 0 | 0 | Equipment Change | 2 | 2020-09-01 16:00 | 2019-05-07 10:00
P2235 Pembina Empress Cogen | 1 | BTF | 48-Empress | 45.8 | 0 | Cogen | 2 | 2021-10-01 16:00 | 2019-05-08 10:00
P2236 RESC Enterprise MPC Solar | 1 | Connection | 49-Stavely | 80 | 3 | Solar | 2 | 2021-08-31 16:00 | 2019-05-09 10:00
P2237 RESC Forty Mile MPC Wind | 1 | Connection | 4-Medicine Hat | 400 | 10 | Wind | 2 | 2021-08-31 16:00 | 2019-05-09 10:00
P2234 Jenner Wind Phase 3 | 1 | BTF | 42-Hanna | 109.2 | 1 | Wind | 2 | 2020-08-15 16:00 | 2019-05-10 10:00
P2240 FortisAlberta 198S Blackfalds DER Gas Phase 2 | 1 | BTF | 35-Red Deer | 0 | 0 | Gas | 3 | 2020-08-01 | 2019-05-23 10:00
P2238 Pembina CDH Load | 1 | Connection | 33-Fort Saskatchewan | 0 | 27.5 | Load | 2 | 2022-03-01 16:00 | 2019-06-03 10:00
P2241 FortisAlberta 368S Burdett DER Solar | 1 | BTF | 52-Vauxhall | 15 | 0 | Solar | 2 | 2021-04-01 16:00 | 2019-06-05 10:00
P2242 ATCO Sarah Lake 743S DER Geothermal | 1 | BTF | 26-Swan Hills | 13.5 | 0 | Gas | 2 | 2020-03-16 16:00 | 2019-06-13 10:00
P2244 - ATCO Wapiti 823S DER Gas | 1 | BTF | 20-Grande Prairie | 3.6 | 0 | Gas | 2 | 2020-05-01 16:00 | 2019-06-19 10:00
P2245 ATCO Freeman Lake 742S Change | 1 | BTF | 26-Swan Hills | 0 | -3.4 | Other | 5 | 2020-10-01 16:00 | 2019-06-20 10:00
P2248 ATCO Michichi Creek 802S DER Solar | 1 | BTF | 42-Hanna | 13.5 | 0 | Solar | 1 | 2021-04-01 16:00 | 2019-06-26 10:00
P2247 Buffalo Plains MPC Wind | 1 | Connection | 47-Brooks | 500 | 2 | Wind | 2 | 2022-10-01 16:00 | 2019-06-28 10:00
P2249 FortisAlberta Empress 394S DER Solar 1 | 1 | BTF | 48-Empress | 22 | 0 | Solar | 2 | 2021-05-01 16:00 | 2019-06-28 10:00
P2250 FortisAlberta Empress 394S DER Solar 2 | 1 | BTF | 48-Empress | 15.5 | 0 | Solar | 2 | 2021-05-01 16:00 | 2019-06-28 10:00
P2253 FortisAlberta Riverbend 618S Contract Change | 1 | Contract | 54-Lethbridge | 0 | 7.6 | DTS | 2 | 2020-04-01 16:00 | 2019-07-03 10:00
P2254 RESC Hilda MPC Wind | 1 | Connection | 48-Empress | 100 | 3 | Wind | 2 | 2022-08-31 16:00 | 2019-07-08 10:00
P2255 Pembina BFG 452S Contract Change | 1 | Contract | 33-Fort Saskatchewan | 0 | 2.5 | DTS | 3 | 2020-02-01 | 2019-07-09 10:00
P2256 ATCO Poplar Hill Load | 1 | Connection | 20-Grande Prairie | 0 | 24.6 | Other | 2 | 2022-03-01 16:00 | 2019-07-11 10:00
P2258 FortisAlberta Brooks 121S DER Gas | 1 | BTF | 47-Brooks | 4 | 0 | Gas Turbine | 1 | 2020-09-15 16:00 | 2019-07-11 10:00
P2259 FortisAlberta Metiskow 648S DER Solar | 1 | BTF | 37-Provost | 22 | 0 | Solar | 1 | 2021-05-01 | 2019-07-17 10:00
P2260 FortisAlberta High River 65S DER Gas | 1 | BTF | 46-High River | 14.3 | 0 | Gas Turbine | 2 | 2020-11-20 16:00 | 2019-07-19 10:00
P2262 Suncor ISDF MacKay River 874S Change | 1 | BTF | 25-Fort McMurray | 0 | 10 | Other | 2 | 2021-04-01 16:00 | 2019-07-31 10:00
P2263 BER Hand Hills MPC Wind | 1 | Connection | 42-Hanna | 200 | 0.2 | Wind | 2 | 2021-12-10 16:00 | 2019-08-02 10:00
P2264 ATCO Michichi Creek 802S Contract Change | 1 | Contract | 42-Hanna | 0 | 31 | DTS | 2 | 2020-02-01 16:00 | 2019-08-12 10:00
P2265 FortisAlberta Duchess 339S DER Gas | 1 | BTF | 47-Brooks | 4.5 | 0 | Gas Turbine | 2 | 2020-03-01 16:00 | 2019-08-13 10:00
P2266 ATCO Seal Lake 869S DER Solar | 1 | BTF | 19-Peace River | 0 | 0 | Solar | 2 | 2020-08-03 16:00 | 2019-08-14 10:00
P2267 FortisAlberta Cheviot 101S Contract Change | 1 | Contract | 29-Hinton/Edson | 0 | -8 | DTS | 2 | 2020-03-09 16:00 | 2019-08-15 10:00
P2268 TCE Saddlebrook Solar and Storage | 1 | Connection | 46-High River | 17 | 7.5 | Solar | 2 | 2021-11-29 16:00 | 2019-08-26 10:00
P2269 Sunset Solar | 1 | Connection | 52-Vauxhall | 60 | 0.3 | Solar | 1 | 2021-12-22 16:00 | 2019-08-28 10:00
P2270 ENMAX Shepard Gas Upgrade | 1 | BTF | 6-Calgary | 13 | 0 | Combined Cycle | 2 | 2020-04-15 16:00 | 2019-09-03 10:00
P2271 FortisAlberta Seebe 245S Contract Change | 1 | Contract | 44-Seebe | 0 | 2.8 | DTS | 1 | 2020-01-02 16:00 | 2019-09-04 10:00
P2272 FortisAlberta Buffalo Creek 526S DER Storage | 1 | BTF | 32-Wainwright | 15.9 | 0 | Other | 1 | 2020-12-10 16:00 | 2019-09-06 10:00
P2277 FortisAlberta Rose Valley 635S Contract Change | 1 | Contract | 29-Hinton/Edson | 0 | 0 | DTS | 2 | 2025-12-31 16:00 | 2019-09-19 10:00
P2279 CNRL Primrose East 641S Gas | 1 | BTF | 28-Cold Lake | 0 | 0 | Gas Turbine | 1 | 2021-07-01 16:00 | 2019-09-19 10:00
P2280 ATCO Germain 950S Contract Change | 1 | Contract | 25-Fort McMurray | 0 | -4 | DTS | 1 | 2020-10-01 16:00 | 2019-09-25 10:00
P2281 CRD Timberlands 209S Contract Change | 1 | Contract | 35-Red Deer | 0 | 8 | DTS | 2 | 2020-02-01 | 2019-09-30 10:00
P2282 CRD North Red Deer 217S Contract Change | 1 | Contract | 35-Red Deer | 0 | -8 | DTS | 2 | 2020-02-01 | 2019-09-30 10:00
P2283 CRD Piper Creek 247S Contract Change | 1 | Contract | 35-Red Deer | 0 | 8 | DTS | 2 | 2020-02-01 | 2019-09-30 10:00
P2284 FortisAlberta Cutting Lake 227S DER Gas | 1 | BTF | 47-Brooks | 7.5 | 0 | Gas Turbine | 1 | 2021-11-15 10:00 | 2019-09-30 10:00
P2289 Heartland Scotford Change | 1 | BTF | 33-Fort Saskatchewan | 0 | 0 | Equipment Change | 1 | 2020-06-05 16:00 | 2019-10-23 10:00
P2290 ATCO Bridge Creek 798S DER Gas | 1 | BTF | 20-Grande Prairie | 1.3 | 0 | Gas Turbine | 1 | 2021-04-09 16:00 | 2019-10-23 10:00
P2292 FortisAlberta Killarney Lake 267S DER Solar/Battery Storage | 1 | BTF | 37-Provost | 18 | 0 | Solar | 1 | 2021-05-01 | 2019-10-28 10:00
P2293 FortisAlberta East Crossfield 64S DER Wasteheat | 1 | BTF | 57-Airdrie | 9.5 | 0 | Wasteheat | 1 | 2021-12-01 16:00 | 2019-10-28 10:00
P2297 FortisAlberta Burdett 368S DER Solar Battery Storage | 1 | BTF | 52-Vauxhall | 17.5 | 0 | Solar | 1 | 2021-05-01 | 2019-11-15 10:00
P2299 Transalta Kaybob 3 Cogen | 1 | Connection | 26-Swan Hills | 42.8 | 0 | Cogen | 1 | 2021-08-30 16:00 | 2019-11-15 10:00
P2296 ATCO Willow Lake 2009S Contract Change | 1 | Contract | 25-Fort McMurray | 0 | 25.6 | DTS | 1 | 2020-08-03 16:00 | 2019-11-22 10:00
BTF denotes a behind the fence project and is not governed by the Connection Process. DTS and STS project types denote active contract change requests and are not governed by the Connection Process.