EPCOR | 665s D2404 (665s Dome), 665s T3 (665s Dome) | 2020-12-15 08:00 | 2020-12-15 17:00 | N | Y | investigate low SF6 gas pressure | Circuit Breaker, Transformer |  | Investigate low SF6 gas pressure | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | Altalink 5s T2 | 2020-12-15 08:00 | 2020-12-16 16:00 | N | N | GIS minor maintenance | Terminal Equipment |  |  | For Information Only
ALTALINK | 378s 652 (378s Shell Caroline) | 2020-12-15 08:30 | 2020-12-15 13:30 | N | N | trip testing | Circuit Breaker | 378s 652 (378s Shell Caroline) |  | Contingency Requires Mitigation
ALTALINK | 650s 752 (650s Hansman Lake) | 2020-12-15 09:30 | 2020-12-15 10:30 | N | Y | gas leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Lethbridge, ALTALINK | 674S725LW, 725L (674s Lethbridge Bowron - 725BL) | 2020-12-15 10:00 | 2020-12-15 16:00 | N | Y | install new RAS protections | Terminal Equipment, Line | 725L (674s Lethbridge Bowron - 725BL) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 378s 452 (378s Shell Caroline) | 2020-12-15 13:31 | 2020-12-15 17:30 | N | N | trip testing | Circuit Breaker | 378s 452 (378s Shell Caroline) |  | Contingency Requires Mitigation
AESO-SC | OATI | 2020-12-15 18:00 | 2020-12-15 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-12-16 07:00 | 2020-12-17 18:00 | N | Y | component replacements | Line | 909L (310p Sundance - 665s Dome) | Component replacements 909L74-Replace Sleeve. See Also SAP: 272769 1045L RB required due to proximity | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 277S Hayter, 748L (267s Killarney Lake - 277s Hayter) | 2020-12-16 13:00 | 2020-12-16 17:00 | N | Y | installing new 25kV bus tie breaker | Station, Line | 748L (267s Killarney Lake - 277s Hayter) |  | Restricts Generation
EPCOR | 557s T2 (557s Castle Downs) | 2020-12-17 07:00 | 2020-12-17 17:00 | N | Y | settings update | Transformer | 557s T2 (557s Castle Downs) | Outage to Tx2 bay for settings update | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2020-12-17 07:15 | 2020-12-18 17:45 | N | Y | maintenance on structures 340, 355, 365 and 381 | Line | 906L (17s Benalto - 42s Sarcee) | Scope of work includes maintenance on structures 340, 355, 365 and 381 | 240 kV, Pre-Condition
ENMAX | 35.1TR (ENMAX 35) | 2020-12-17 08:00 | 2020-12-17 12:00 | N | N | oil sampling TR, TC | Transformer |  |  | For Information Only
ENMAX | 39.1TR (ENMAX 39) | 2020-12-17 08:00 | 2020-12-17 16:00 | N | N | oil sampling bushing,TR, TC | Transformer |  |  | For Information Only
EPCOR | 240BA3 (629s Argyll Transfer Station - 814s Bellamy) | 2020-12-17 08:00 | 2020-12-17 17:00 | N | Y | top up low SF6 on Phase 1 on BDS13 compartment | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 392s T2 (392s Black Diamond), 13L/158L (65s High River - 392s Black Diamond) | 2020-12-17 09:15 | 2020-12-17 17:15 | N | N | install bird cover on CT1 and 25kV UDG cables | Transformer, Line |  | Install bird cover on CT1 and 25kV UDG cables | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 35.2TR (ENMAX 35) | 2020-12-17 12:00 | 2020-12-17 16:00 | N | N | oil sampling TR, TC | Transformer |  |  | For Information Only
NWE | Marias Shunt Capacitor | 2020-12-18 06:23 | 2020-12-31 23:59 | N | Y | bank #4 forced outage | Shunts |  | Terminal Clearance, Brastrup, Mark - PAR 406-671-5494, Awaiting Parts | For Information Only
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-12-18 13:00 | 2020-12-18 16:00 | N | Y | restore 2.80L due to urgent outage taken by Altalink on 5s T2 | Shunts |  | Outage required to restore 2.80L due to urgent outage taken by Altalink on 5s T2 | For Information Only
ENMAX | 2.4TR (ENMAX 2) | 2020-12-18 13:00 | 2020-12-18 16:00 | N | N | restore 2.80L due to urgent outage taken by Altalink on 5s T2 | Transformer |  | Outage required to restore 2.80L due to urgent outage taken by Altalink on 5s T2 | For Information Only
ENMAX | 162.2TR (162s Beddington), 39.82L (ENMAX 162 Beddington - ENMAX 39), 162s Beddington 138 kV South Bus, 162s Beddington 240 kV South Bus | 2020-12-19 06:00 | 2020-12-20 16:00 | N | Y | RTU & line protection upgrade and settings changes | Transformer, Line, Bus |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 956L (59s Peigan - 103s Goose Lake) | 2020-12-19 07:00 | 2020-12-19 18:00 | N | N | urgent work includes maintenance on str 50 and 56 | Line |  |  | Pre-Condition
ENMAX | 12.2TR (ENMAX 12) | 2020-12-19 08:00 | 2020-12-21 16:00 | N | N | NGR installation. | Transformer | 12.2TR (ENMAX 12)
ENMAX | 6.80L (ENMAX 6 - ENMAX 35) | 2020-12-19 08:00 | 2020-12-22 16:00 | N | N | transmission line pole relocation phasing required | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.5TR (ENMAX 1) | 2020-12-19 08:00 | 2020-12-19 16:00 | N | N | oil sampling, check reversing switch | Transformer
ALTALINK | 1049L (59s Peigan - 138s Windy Flats) | 2020-12-20 07:15 | 2020-12-20 12:45 | N | Y | maintenance on structure 1 | Line |  |  | Pre-Condition
ENMAX | 8.5TR (ENMAX 8) | 2020-12-21 08:00 | 2020-12-21 16:00 | N | N | top up oil | Transformer
ALTALINK | 288s T2 (288s Wolf Creek), 288s Wolf Creek 138kV Bus 2, 288s 1452 (288s Wolf Creek) | 2020-12-22 08:00 | 2020-12-22 13:00 | N | Y | urgent outage to fix loose terminal connections on 288s45 | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 37s 76 (37s North Calder) | 2020-12-22 08:30 | 2020-12-22 17:30 | N | Y | complete wiring, commissioning and function testing for reclosing circuit for breaker | Circuit Breaker | 37s 76 (37s North Calder) |  | 240 kV, Contingency Requires Mitigation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-12-27 08:00 | 2021-01-03 18:00 | N | N | 30PT-121 XO bushing leaking | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-12-28 08:00 | 2021-01-04 18:00 | N | N | 29EDD8, 29PT-47 | Not In Model | Unmodeled Transmission Facility (Suncor) | 29EDD8;29PT-47 SYSTEM;PM 5y,10y | For Information Only
ALTALINK | 511s ACF21 (511s Crossings) | 2020-12-30 13:00 | 2021-01-07 17:30 | N | Y | forced outage | Shunts |  |  | 240 kV, For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-12-31 08:00 | 2021-01-06 18:00 | N | N | 29EDD-70, 29PT-221 | Not In Model | Unmodeled Transmission Facility (Suncor) | 29EDD-70 29PT-221 4.16KV Resistor Fault - 72kV | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-01 08:00 | 2021-12-31 18:00 | N | N | 30EDD-200, 29EDD-106, 29EDD-141, 29EDD-192 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-01 08:00 | 2022-01-01 18:00 | N | N | 30EDD-200 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
FORTIS | BFD2 Blackfalds | 2021-01-01 08:00 | 2021-02-05 16:00 | N | N | P2240 Blackfalds DER Gas Phase 2. 4 MW. ISD Jan 29, 2021 | Unit
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-01 08:00 | 2023-01-04 18:00 | N | N | 30EDD-200 | Not In Model | 30EDD-200 30PR-32 Reactor Str Sagging - 72kV |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-01 08:00 | 2022-01-11 18:00 | N | N | 30EDD-200 | Not In Model |  | 30EDD200;30PT-121 SYSTEM;PM 5y - 72kV | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-02 08:00 | 2023-01-05 18:00 | N | N | 29EDD-181 | Not In Model | 29EDD-181; SUBSTATION GROUND TEST;PM 5y - 34.5kV |  | For Information Only
ENMAX | 10.2TR (ENMAX 10) | 2021-01-04 08:00 | 2021-01-07 16:00 | N | N | bus outage to investigate noise | Transformer
ATCO | 7L228 (845s Big Mountain - 2091s Thornton) | 2021-01-04 08:00 | 2021-01-11 15:30 | N | Y | mitigation work, changing poles and wire work | Line | 7L228 (845s Big Mountain - 2091s Thornton) | Mitigation work, changing poles and wire work | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 7L64 (779s Chinchaga River - 789s Keg River) | 2021-01-04 08:00 | 2021-01-11 12:00 | N | Y | changing cross arms for wildfire mitigation | Line |  | Changing cross arms for wildfire mitigation | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-01-04 08:00 | 2021-02-04 16:00 | Y | Y | structure refurbishment | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 610L (83s Taber - 336s Fincastle), 172L (83s Taber - 172EL), 83s C2 (83s Taber), 83s T1 (83s Taber) | 2021-01-04 09:00 | 2021-01-07 17:00 | N | Y | urgent replace 138kV switch 83s36. | Line, Shunts, Transformer |  | Taber 83s Urgent Repair - Replace 138kV switch 83s36. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 277s T2 (277s Hayter), 277s 252 (277s Hayter), 277s Hayter 138kV Bus | 2021-01-05 07:00 | 2021-02-08 10:00 | N | N | reconfiguring the 138kV bus in preparation for the new 398L (P1782) | Transformer, Circuit Breaker, Bus | P1782, V.Chan Dec 15, 2020 | Reconfiguring the 138kV bus in preparation for the new 398L | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-05 08:00 | 2023-06-01 18:00 | N | N | 29PT-69 | Not In Model | 29EDD19;29PT-69 SYSTEM;PM 5y 72kV |  | For Information Only
ATCO | 739s 602 (739s Edith Lake), 6L11 (739s Edith Lake - 854s Swan Dive) | 2021-01-05 10:00 | 2021-01-05 15:00 | N | N | replace failed tank heater | Circuit Breaker, Line |  | Replace Failed Tank heater | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 702L (137s Sedgewick - 757s Battle River) | 2021-01-06 07:00 | 2021-01-06 18:00 | N | Y | maintenance | Line |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12), 12.2TR (ENMAX 12) | 2021-01-06 08:00 | 2021-01-07 16:00 | N | Y | maintenance | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 6L05, 6L05 (764s Heisler - 6L05 tap) | 2021-01-06 08:30 | 2021-01-06 17:00 | N | N | Replacing pole and insulators on 6L05 | Terminal Equipment, Line | 6L05 (764s Heisler - 6L05 tap) | Replacing pole and insulators on 6L05 | Creates Radial Feeds, Firm Load Loss
ALTALINK | 610L (83s Taber - 336s Fincastle), 172L (83s Taber - 172EL), 83s T1 (83s Taber), 83s C2 (83s Taber) | 2021-01-06 09:00 | 2021-01-06 17:00 | N | Y | there is a 20c hotspot on 83s2 that needs to be looked at. | Line, Transformer, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-01-06 11:00 | 2021-01-06 15:00 | N | Y | maintenance | Switch | 250p 11 (250p Bighorn Plant) | Brushgear | Restricts Generation
ATCO | 7L39 (811s Clairmont Lake - 7L39 tap), 811s 709 (811s Clairmont Lake) | 2021-01-07 08:00 | 2021-01-10 16:00 | N | Y | protection upgrades | Line, Circuit Breaker | 7L39 (811s Clairmont Lake - 7L39 tap), 811s 709 (811s Clairmont Lake) | 811S Clairmont Lake Protection upgrades Wiring modification to 21A/7L39 & 21B/7L39 709CT modification, 709 Logic/Alarms, SCADA updates, SCADA End-End Checks and 1Z wiring | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Affects Cranking Path
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-01-07 09:00 | 2021-01-07 13:00 | N | Y | maintenance | Switch | 250p 22 (250p Bighorn Plant) |  | Restricts Generation
ALTALINK | 511s ACF21 (511s Crossings), 511s 2152 (511s Crossings) | 2021-01-07 09:00 | 2021-01-07 17:30 | N | Y | breaker fault investigation & repair | Shunts, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 156L (235s Entwistle - 156BL) | 2021-01-08 07:00 | 2021-01-11 18:00 | N | N | replacing structures 93, 154 and 158 and maintenance on structures 105 and 159 | Line |  | Scope of work includes replacing structures 93, 154 and 158 and maintenance on Structures 105 and 159 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENBRIDGE, MONTANA | 120s MATL PST, 120s 1352 (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte) | 2021-01-08 10:00 | 2021-01-08 14:00 | N | Y | rising edge to piggy-back on the outage at the MATL 120S substation | Transformer, Circuit Breaker, Shunts |  | Piggy backing off of emergency outage for line repair by Kline; investigate substation alarm | 240 kV, Pre-Condition, Limits ATC
MONTANA | MATL (120s Picture Butte - Montana) | 2021-01-08 10:00 | 2021-01-08 14:00 | N | Y | urgent repair on structure 166-5 | Line |  | Urgent outage request to repair 941L transmission structure 166/5. | 240 kV, Pre-Condition, Limits ATC
ENMAXEC | KHW1 Kettles Hill Wind | 2021-01-09 18:15 | 2021-01-09 18:55 | N | N | replace a network security appliance that will impact communications | Unit |  |  | Affects Visibility
SUNCOR | 635EDD-1001 635-752-623 (635EDD-1001) | 2021-01-10 08:00 | 2021-01-10 17:00 | N | N | breaker close circuit repair | Circuit Breaker |  | 144kV Circuit Breaker Close Circuit Repair | Contingency Requires Mitigation, For Information Only
EPCOR | 72MG16 (Garneau - Meadowlark), M724 (Meadowlark), G721 (Garneau), G726 (Garneau) | 2021-01-11 07:00 | 2021-01-15 17:00 | N | N | breaker op-checks | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2021-01-11 07:00 | 2021-01-14 18:00 | N | Y | create temporary open point 'A' @ structure #1A & open point 'B' @ structure #31 | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 5B138-1.82 (ENMAX 5), 1.82L (ENMAX 1 - ENMAX 5) | 2021-01-11 08:00 | 2021-01-11 12:00 | N | N | 5 sub RTU commissioning | Circuit Breaker, Line | 1.82L (ENMAX 1 - ENMAX 5) | ENMAX 5 sub RTU commissioning | For Information Only, Pre-Condition
ATCO | 7L139 (819s Whitby Lake - 7L139D2) | 2021-01-11 08:00 | 2021-01-14 15:00 | N | N | change cross arms and insulators | Line | 7L139 (819s Whitby Lake - 7L139D2) | Changing Cross Arms and insulators; | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | D05 T1 (D05 Syncrude) | 2021-01-11 08:00 | 2021-01-13 20:00 | N | Y | maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20), 20B138-1.81 (ENMAX 20) | 2021-01-11 08:00 | 2021-01-12 16:00 | N | N | switch maintenance | Line, Transformer, Circuit Breaker | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20) | HV SW maint SW81, SW82, SW83, MD-20.1TR | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 2MD138-2.1CAP (ENMAX 2), 2B138-D95 (ENMAX 2), 2B138-D96 (ENMAX 2), 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2021-01-11 08:00 | 2021-01-12 16:00 | N | Y | GIS maintenance | Switch, Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 226s Garden City RTU/SCADA | 2021-01-11 10:00 | 2021-01-11 11:00 | N | N | network configuration changes | Terminal Equipment |  | " Hybrid wireless equipment upgrade to Enbridge router. " Outage expected to be 30 mins which will result in a brief loss of telemetry. " Field personnel will be onsite to execute any requests from the AESO/AltaLink if required. " No loss of MW production or reactive capability is expected. | Affects Visibility
ALTALINK | 753L (65s High River - 253s Blackie), 65s 753E (65s High River) | 2021-01-11 10:45 | 2021-01-14 17:45 | N | Y | urgent 65s753E CT replacement - leaking oil and 65s753E grading cap replacement | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | 615S Halkirk | 2021-01-11 11:00 | 2021-01-11 12:00 | N | N | communication outage | Station |  |  | Affects Visibility
ENMAX | 1.84L (ENMAX 1 - ENMAX 5), 5B138-1.84 (ENMAX 5) | 2021-01-11 12:00 | 2021-01-11 16:00 | N | N | 5sub RTU commissioning | Line, Circuit Breaker | 1.84L (ENMAX 1 - ENMAX 5) |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar) | 2021-01-11 12:00 | 2021-01-15 18:00 | N | Y | component and fire mitigation Str's range 1-72 | Line | 921L (71s Lamoureux - 987s Clover Bar) |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 251s Whitla | 2021-01-11 14:00 | 2021-01-11 15:00 | N | N | communication outage | Station |  |  | Affects Visibility
VISIONREQ | 354S Summerview | 2021-01-12 07:00 | 2021-01-23 20:00 | N | N | WindCharger upgrade work | Station |  |  | Restricts Generation
ALTALINK | 138s Windy Flats 240kV Bus 1, 138S R1 (138s Windy Flats) | 2021-01-12 07:00 | 2021-01-12 19:00 | N | Y | installation of x2 cast-in-place foundation points for the new 240kV high bay structure | Bus, Shunts | 138s Windy Flats 240kV Bus 1, 138S R1 (138s Windy Flats) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-01-12 07:00 | 2021-01-12 16:00 | N | Y | creating temporary open point 'C' @ structure #1A | Line | 909L (310p Sundance - 665s Dome) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 156L (19s Wabamun - 156BL) | 2021-01-12 07:00 | 2021-01-13 18:00 | N | N | maintenance | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2021-01-12 08:00 | 2021-01-12 12:00 | N | N | RTU commissioning | Line | 2.82L (ENMAX 2 - ENMAX 5) |  | For Information Only, Pre-Condition
ATCO | 7L82 (788s Hotchkiss - 855s Hamburg), 7L82 (853s Ring Creek - 855s Hamburg) | 2021-01-12 08:00 | 2021-01-12 17:00 | N | Y | emergency work to replace broken structure 953 on 7L82 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 320p 2152 (320p Keephills) | 2021-01-12 09:00 | 2021-01-12 11:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 310p 1152 (310p Sundance) | 2021-01-12 12:00 | 2021-01-12 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2021-01-12 12:00 | 2021-01-12 16:00 | N | N | RTU commissioning | Line | 2.83L (ENMAX 5 - 2.83L tap) |  | For Information Only, Pre-Condition
ALTALINK | 45S Bretona | 2021-01-12 12:30 | 2021-01-12 17:00 | N | N | 45s 2231 - maintenance on 2231L relays | Station | 25kV |  | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-01-12 16:00 | 2021-02-08 09:00 | N | Y | work on structures 909L2 - 909L6, installing one new tower, and salvaging one new tower | Line | 909L (Open Point 'C' - E665s) - GOI | preliminary outage request to work on tructures 909L2 - 909L6, installing one new tower, and salvaging one new tower | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | ENMAX 5 B138-5BT7 ( ENMAX 5) | 2021-01-13 08:00 | 2021-01-13 12:00 | N | N | RTU commissioning. | Circuit Breaker | 5 B138-5BT7 (ENMAX 5) |  | For Information Only
ENMAX | 23.3TR (ENMAX 23) | 2021-01-13 08:00 | 2021-03-29 18:00 | N | N | oil leak repair | Transformer |  | 23.3TR Oil Leak Repair - Possible Secondary Bushing | For Information Only
ALTALINK | 5s T1 (5s East Calgary) | 2021-01-13 08:00 | 2021-01-14 16:00 | N | Y | GIS switch maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20) | 2021-01-13 08:00 | 2021-01-14 16:00 | N | N | switch maintenance | Line, Transformer | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2021-01-13 10:27 | 2021-01-15 16:00 | N | N | line pole damage caused by the extreme winds in the area | Line |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2021-01-13 11:13 | 2021-02-02 16:00 | N | N | line pole damage caused by the extreme winds in the area | Line
ENMAX | 5B138-5BT12 (ENMAX 5) | 2021-01-13 12:00 | 2021-01-13 16:00 | N | N | RTU commissioning | Circuit Breaker | 5B138-5BT12 (ENMAX 5) |  | Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2021-01-13 23:00 | 2021-01-14 03:00 | N | Y | maintenance | Switch |  | Brushgear | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2021-01-14 03:00 | 2021-01-14 07:00 | N | Y | maintenance | Switch |  | brushgear | 240 kV, For Information Only, Pre-Condition, Restricts Generation
ENMAX | 5.1TR (ENMAX 5) | 2021-01-14 08:00 | 2021-01-14 16:00 | N | N | 5sub RTU commissioning | Transformer | 5.1TR (ENMAX 5) |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2021-01-14 08:00 | 2021-01-14 18:00 | N | Y | 7B138-7.82 - heater fail on near pole, SF6 gas sample | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1045L (310p Sundance - 1045AL) | 2021-01-14 18:01 | 2021-02-28 09:00 | N | Y | preliminary outage request to work on 1045L Str 12, installing one new tower, and salvaging one new tower | Line | 1045L (310p Sundance - 1045AL) |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 510s ACF11 (510s Sunnybrook) | 2021-01-15 07:00 | 2021-01-21 15:30 | N | N | forced outage | Shunts |  |  | 500 kV
BCH | Natal T1 (BCH Natal) | 2021-01-15 08:00 | 2021-01-15 17:00 | N | Y | urgent bushing syringe samples | Transformer | Natal T1 (BCH Natal) |  | Pre-Condition
CapitalPower | 615S Halkirk | 2021-01-15 09:00 | 2021-01-15 17:00 | N | N | connection of the fibre optic comms line back into T74 | Station |  | This communication only outage for turbines on circuit 4 is to allow for the connection of the fibre optic comms line back into T74 to fully restore this turbine to operation. The communication outage is only applied to the 13 turbines on circuit 4. There will be no impact on MW or MVAR visibility to AESO Site can still respond to Wind Ramp Management setpoint during communication outage except the 13 turbines that has no communication. Those 13 turbines can be manually curtailed onsite by operation team if required. | Affects Visibility
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21) | 2021-01-16 08:00 | 2021-01-17 18:00 | N | Y | HV SW maint SW81, SW82, SW83, SW84, SW85, MD-21.1TR, MD21.4TR | Line, Transformer | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L92 (Cranbrook - Selkirk) | 2021-01-16 09:00 | 2021-01-16 17:00 | Y | Y | breaker repair | Line | 5L92 (Cranbrook - Selkirk) |  | Limits ATC, 500 kV
EPCOR | 330P 12TC1 (330p Genesee), 330p 805 (330p Genesee) | 2021-01-18 07:00 | 2021-01-18 17:00 | N | Y | outage required for op checks to 805 breaker | Transformer, Circuit Breaker |  | Outage required for op-checks to 805 breaker | 500 kV, Contingency Requires Mitigation, Creates Radial Feeds
Saskpower | Sask Power SW901T | 2021-01-18 07:00 | 2021-01-29 16:30 | N | Y | maintenance | Circuit Breaker | Sask Power SW901T |  | Limits ATC
EPCOR | 816s T1 (816s Petrolia) | 2021-01-18 07:00 | 2021-01-22 17:00 | N | Y | tapchanger repair | Transformer | 816s T1 (816s Petrolia) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72NK23 (Kennedale - Namao), 72CK12 (987s Clover Bar - Kennedale), 72NW15 (Namao - Woodcroft), 72VN21 (511s Victoria - Namao) | 2021-01-18 07:00 | 2021-01-25 17:00 | N | N | 72KN23 protection upgrade | Line |  | 72KN23 protection upgrade | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.84L (ENMAX 2 - ENMAX 8) | 2021-01-18 08:00 | 2021-01-19 16:00 | N | N | maintenace | Line |  | GIS Switch maintenance. 8SW1A15, 8SW1A51. 8SW1A1 | For Information Only
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 2021-01-18 08:00 | 2021-01-30 17:40 | N | Y | 811s protection upgrades, 710CT modification, logic/alarms, SCADA updates & end-end checks and wiring | Line | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 811S Clairmont Lake Protection upgrades, 710CT modification, 710 Logic/Alarms, SCADA updates, SCADA End-End Checks and 1Z wiring | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L64 (779s Chinchaga River - 789s Keg River) | 2021-01-18 08:00 | 2021-01-25 16:00 | N | Y | changing cross arms for wildfire mitigation | Line | 7L64 (779s Chinchaga River - 789s Keg River) | Changing cross arms for wildfire mitigation | Pre-Condition, Affects Cranking Path
ATCO | 7L228 (845s Big Mountain - 2091s Thornton) | 2021-01-18 08:00 | 2021-01-24 15:30 | N | Y | mitigation work, changing poles and wire work | Line |  | Mitigation work, changing poles and wire work | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 2.3TR (ENMAX 2) | 2021-01-18 08:00 | 2021-01-22 16:00 | N | N | switch maintenance | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21), 21.2TR (ENMAX 21), 21.1C (ENMAX 21), 21B138-21.CAP (ENMAX 21) | 2021-01-18 08:00 | 2021-01-19 16:00 | N | Y | maintenance | Line, Transformer, Shunts, Circuit Breaker | 50L (44s Bearspaw Plant - ENMAX 21), 21.2TR (ENMAX 21), 21.1C (ENMAX 21) | HV SW maint SW87, SW88, SW89, SW90, MD-21.2TR | For Information Only, Pre-Condition
ATCO | 7L139 (819s Whitby Lake - 7L139D2) | 2021-01-18 08:00 | 2021-01-21 15:00 | N | N | changing cross arms and insulators; crews will be doing their own switching | Line |  | Changing Cross Arms and insulators; crews will be doing their own swtiching | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | D05 T2 (D05 Syncrude) | 2021-01-18 08:00 | 2021-01-18 20:00 | N | Y | maintenance | Transformer |  | Significant Outage: 260kV Transformer T2 @ D05 Substation: The following Circuit Breakers will be operated:78, 513, 516 The following switches will be operated: 78A, 78B, 509 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.5TR (ENMAX 5) | 2021-01-18 08:00 | 2021-01-18 16:00 | N | N | RTU commissioning, close open required on return for commissioning | Transformer |  |  | For Information Only
ALTALINK | 368s 879 (368s Burdett), 879L (244s Bowmanton - 368s Burdett) | 2021-01-18 08:15 | 2021-01-27 10:45 | N | Y | install and commission new GE C60/breaker fail for 368s879 (752) | Circuit Breaker, Line | Install and commission new GE C60/Breaker Fail for 368s879 (752). |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 368s T1 (368s Burdett) | 2021-01-18 09:00 | 2021-01-25 16:45 | N | N | install new protection and control for 368s15 and 368s382, VT and CT work | Transformer |  | Install new protection and control for 368s15 and 368s382. Install VTs in the Switchgear on the line side of both breakers. Connect transformer CTs to the Bus undervoltage relays, commission 25kV Breaker Fails. | For Information Only
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2021-01-18 09:00 | 2021-01-28 14:26 | N | Y | OPGW D/C with 161L | Line | Cleresholm Project 180L Str's Range 1-20 to complete the OPGW D/C with 161L |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar) | 2021-01-18 12:00 | 2021-01-22 18:00 | N | Y | component's and fire mitigation bundled Str's range 1-72 | Line | 921L (71s Lamoureux - 987s Clover Bar) |  | 240 kV, Pre-Condition, Affects Cranking Path
EPCOR | 330P 12TC2 (330p Genesee), 330p 809 (330p Genesee) | 2021-01-19 07:00 | 2021-01-19 17:00 | N | Y | op-checks to 809 breaker | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, For Information Only, Pre-Condition
ALTALINK | 198S Blackfalds | 2021-01-19 07:00 | 2021-01-19 17:00 | N | N | anti-islanding protection on 25 kV feeder L9 (SEL-2411) will be out of service | Station |  | anti-islanding protection on feeder L9 (SEL-2411) at Blackfalds will be out of service. Fortis/DG requested work for new connection, Fortis has informed us that DG outage has been planned with them. | For Information Only, Restricts Generation
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead) | 2021-01-19 07:30 | 2021-01-19 17:30 | N | Y | implementation of RAS scheme | Line | 880L (321s Al Rothbauer - 523s Bullshead) | Implementation of RAS scheme for 321s Rothbauer. Breaker outage is required to implement CT circuits for protection and trip circuits to breaker. | Creates Radial Feeds, Firm Load Loss
ENMAX | 5.6TR (ENMAX 5) | 2021-01-19 08:00 | 2021-01-19 16:00 | N | N | 5sub RTU commissioning | Transformer |  | 5sub RTU Commissioning. Close open required on return for commissioning. | For Information Only
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe) | 2021-01-19 08:00 | 2021-01-19 16:30 | N | Y | emergency repair; 198s1 repair | Line | Emergency Repair; 198s1 repair |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 7L146 (700s Bonnyville - 970s Bourque) | 2021-01-19 10:00 | 2021-01-19 14:00 | N | Y | open for TPR outage | Line |  |  | Pre-Condition
ALTALINK | 167s 2052 (167s Ipiatik Lake), 428L (167s Ipiatik Lake - 818s Winefred) | 2021-01-19 12:30 | 2021-01-19 17:30 | N | N | breaker heater replacement | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2021-01-19 18:00 | 2021-01-19 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 133L (19s Wabamun - 234L), 522L (133L - 522AL), 522L (320p Keephills - 133L) | 2021-01-20 07:00 | 2021-01-20 18:00 | N | N | fire mitigation | Line |  |  | Firm Load Loss, For Information Only, Pre-Condition
EPCOR | 330p 1203 (330p Genesee) | 2021-01-20 07:00 | 2021-01-20 11:00 | N | Y | op-checks to 1203 breaker | Circuit Breaker |  | Outage required for op-checks to 1203 breaker | 500 kV, Contingency Requires Mitigation
BCH | Natal T1 (BCH Natal) | 2021-01-20 07:30 | 2021-01-20 17:30 | N | Y | urgent bushing syringe samples | Transformer | Natal T1 (BCH Natal) | Urgent bushing syringe samples required-gasses present last sample | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 5.9TR (ENMAX 5) | 2021-01-20 08:00 | 2021-01-20 16:00 | N | N | 5sub RTU commissioning | Transformer |  | 5sub RTU Commissioning. Close open required on return for commissioning. | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 15.60L (ENMAX 15 - ENMAX 21), 21.4TR (ENMAX 21) | 2021-01-20 08:00 | 2021-01-22 16:00 | N | N | maintenance | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2021-01-20 08:00 | 2021-01-27 17:00 | N | N | maintenance | Line | 890L (58s Edson - 207s Pinedale) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 681s 152 (681s Bannerman) | 2021-01-20 08:00 | 2021-01-21 18:00 | N | Y | urgent breaker maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 7L194 (2009s Willow Lake - 2011s Dawes) | 2021-01-20 08:00 | 2021-01-20 17:00 | N | N | pole replacement | Line |  | Pole replacement | Creates Radial Feeds, Firm Load Loss
ENMAX | 8B138-3A0 (ENMAX 8) | 2021-01-20 08:00 | 2021-01-21 16:00 | N | N | switch maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | 330p 1206 (330p Genesee) | 2021-01-20 12:30 | 2021-01-20 17:00 | N | Y | op-checks to 1206 breaker | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 133L (19s Wabamun - 234L) | 2021-01-20 18:00 | 2021-01-21 18:00 | N | N | fire mitigation | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 1209 (330p Genesee) | 2021-01-21 07:00 | 2021-01-21 11:00 | N | Y | op-checks to 1209 breaker | Circuit Breaker |  | Outage required for op-checks to 1209 breaker | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 107s 457W (107s Westfield) | 2021-01-21 07:15 | 2021-01-27 18:45 | N | N | install new 25kV PT and associated equipment for 457LW feeder | Circuit Breaker | ISD for P2171 (WEF1 gen addition) is Feb 1, 2021. | Install new 25kV PT for 457LW feeder, install new JB and wire, demo old modules and install new modules in control building for 107s457W Breaker. Test operate protections. | For Information Only, Pre-Condition
ALTALINK | 874L (45s Bretona - 522s Cooking Lake) | 2021-01-21 07:15 | 2021-02-02 17:45 | N | N | structure changes and reframes | Line |  | GOI required to complete component replacement scope on structures 105 to 264, Structure changes and reframes. | Creates Radial Feeds, Firm Load Loss
ATCO | 2075s ACF22 (2075s Newell) | 2021-01-21 07:30 | 2021-01-21 17:30 | N | Y | repair structural towers supporting ACF22 capacitor banks | Shunts |  | Repair Structural Towers Supporting ACF22 Capacitor Banks, No constraints, redundant filter bank ACF12 is still in service | 240 kV
ENMAX | 5.10TR (ENMAX 5) | 2021-01-21 08:00 | 2021-01-21 16:00 | N | N | 5sub RTU commissioning | Transformer |  | 5sub RTU Commissioning. Close open required on return for commissioning. | For Information Only
ATCO | 7L121 (833s Mariana - 860s Crow) | 2021-01-21 08:00 | 2021-01-21 17:00 | N | N | pole replacement | Line |  | Pole replacement Brief outages required at 860S Crow & 833S Mariana to isolate required section of line | Creates Radial Feeds, Firm Load Loss
ALTALINK | 484s Millar Western RTU/SCADA | 2021-01-21 09:00 | 2021-01-21 12:00 | N | N | urgent: investigate intrusion alarm at site | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2021-01-21 10:00 | 2021-01-21 14:00 | N | Y | Lemming Lake S- Telecom - 7L91 protection relay | Line |  |  | Pre-Condition, Restricts Generation
EPCOR | 330p 1201 (330p Genesee) | 2021-01-21 12:30 | 2021-01-21 17:00 | N | Y | op-checks to 1201 breaker | Circuit Breaker |  | Outage required for op-checks to 1201 breaker | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8), 8B138-4A0 (ENMAX 8), 1B138-10A0 (ENMAX 1), 8B138-3A0 (ENMAX 8), 1B138-1A0 (ENMAX 1), 8B138-2A0 (ENMAX 8), 8.5TR (ENMAX 8), 8.6TR (ENMAX 8) | 2021-01-21 14:00 | 2021-01-21 16:00 | N | N | GIS switch repair | Line, Circuit Breaker, Transformer |  | GIS Switch repair. 8-SW3a51 -motor does not shut off in the ground position LD. Outage required to return 3a0@ 8sub | Contingency Requires Mitigation, Pre-Condition
ENMAX | 8.5TR (ENMAX 8), 8.6TR (ENMAX 8), 8B138-3A0 (ENMAX 8), 8B138-2A0 (ENMAX 8) | 2021-01-21 14:00 | 2021-01-21 16:00 | N | N | GIS switch repair | Transformer, Circuit Breaker |  | GIS switch repair. 8-SW3a51 -motor does not shut off in the ground position LD. Outage required to return 3a0@ 8sub | For Information Only
SUNCOR | 139S Hillridge | 2021-01-22 00:04 | 2021-01-22 11:00 | N | N | communication issues | Station |  |  | For Information Only
ALTALINK | 12s T1 (12s Heartland) | 2021-01-22 00:12 | 2021-01-28 18:00 | N | N | forced outage | Transformer |  |  | 500 kV
EPCOR | 330p 1204 (330p Genesee) | 2021-01-22 07:00 | 2021-01-22 11:00 | N | Y | op-checks to 1204 breaker | Circuit Breaker |  | Outage required for op-checks to 1204 breaker | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 2075s ACF12 (2075s Newell) | 2021-01-22 07:30 | 2021-01-22 17:30 | N | Y | repair structural towers | Shunts |  | Repair Structural Towers Supporting ACF12 Capacitor Banks, No constraints, redundant filter bank ACF22 is still in service | 240 kV, Pre-Condition
EPCOR | 330p 1207 (330p Genesee) | 2021-01-22 12:30 | 2021-01-22 17:00 | N | Y | op-checks to 1207 breaker | Circuit Breaker |  | Outage required for op-checks to 1207 breaker | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 15.60L (ENMAX 15 - ENMAX 21), 21B69-15.60 (ENMAX 21), 15B69-15.60 (ENMAX 15) | 2021-01-22 16:01 | 2021-01-26 16:00 | N | N | forced: 69kV bus switch issue | Line, Circuit Breaker | 15.60L (ENMAX 15 - ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-01-24 08:00 | 2023-01-07 18:00 | N | N | 29EDD-161 | Not In Model | 29EDD-161;29PT-582 SYSTEM;PM 5y,10y and SUBSTATION GROUND TEST;PM 5y - 34.5kV |  | For Information Only
ALTALINK | 368s C2 (368s Burdett) | 2021-01-24 08:15 | 2021-01-24 12:45 | N | N | wire and commission trips to 368s44 from GE C60 for 368s879 (752) breaker fail and wire and commission trip from 368s44 to 368s879 breaker | Shunts | 368s C2 (368s Burdett) | Wire and commission trips to 368s44 from GE C60 for 368s879 (752) breaker fail. Wire and commission trip from 368s44 to 368s879 breaker. | Pre-Condition
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2021-01-24 12:15 | 2021-01-24 16:45 | N | N | wire and commission trips to 368s35 from GE C60 for 368s879 (752) breaker fail | Shunts | 368s C1 (368s Burdett) |  | Pre-Condition
EPCOR | 814s B2402 (814s Bellamy) | 2021-01-25 07:00 | 2021-01-25 17:00 | N | Y | beaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR, ALTALINK | 330p 807 (330p Genesee), 430L (330P Genesee - 510S Sunnybrook) | 2021-01-25 07:00 | 2021-01-25 17:00 | N | Y | op-checks to 807 breaker | Circuit Breaker, Line |  | Outage required for op-checks to 807 breaker | For Information Only, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-01-25 07:00 | 2021-01-26 17:00 | N | Y | breaker op-checks | Line |  | Outage required for breaker op-checks | 240 kV, For Information Only, Affects Cranking Path
ALTALINK | 234L (310p Sundance - 505L tap), 505L (505L - 234L) | 2021-01-25 07:00 | 2021-02-19 18:00 | N | N | working on 234L Strs 68-73, replacing conductor and structures | Line |  |  | For Information Only
EPCOR | 987s T3 (987s Clover Bar), 987s Cloverbar 240kV Bus 3 | 2021-01-25 07:00 | 2021-01-28 17:00 | N | Y | breaker op-checks | Transformer, Bus |  | Outage required for breaker op-checks | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 234L (310p Sundance - 505L tap), 505L (505L - 234L), 521AL (867s Sundance Blow-Down - 521L), 521L (505L - 512L) | 2021-01-25 07:00 | 2021-01-26 18:00 | N | N | maintenance on structure 521L11/234L103 and replacingsStructure 521L9/234L105 | Line |  |  | For Information Only, Pre-Condition
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 43.2TR (ENMAX 43), 33B138-33.84 (ENMAX 33) | 2021-01-25 08:00 | 2021-01-26 16:00 | N | N | HV SW maintenance SW84, SW85, SW86, MD-43.2TR | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2021-01-25 08:00 | 2021-01-27 17:00 | N | Y | emergency repairs - replace failed pump on thyristor cooling system | Shunts |  | Emergency Repairs to 813S SVC. Replace failed pump on thyristor cooling system. concern is if backup fails the SVC would be OOS | Pre-Condition
ENMAX | 26B138-26BT3 (ENMAX 26) | 2021-01-25 08:00 | 2021-01-25 16:00 | N | N | heater circuit contactor upgrades | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2021-01-25 09:00 | 2021-01-28 20:00 | N | Y | urgent tap changer repair | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2021-01-25 12:00 | 2021-01-28 17:32 | N | Y | component's and fire mitigation bundled structures range 2-24 | Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ATCO | 828s 507 (828s Sulphur Point), 828s 507C1 (828s Sulphur Point), 828s 507C2 (828s Sulphur Point) | 2021-01-25 13:00 | 2021-01-25 17:00 | N | N | relay testing on 507C protection | Circuit Breaker, Shunts |  | Relay Testing On 507C protection, Capacitor bank must be OOS, Breaker 507 will be Open and on Local for duration of testing. | For Information Only, Pre-Condition
EPCOR | 8L10 (330P Genesee - Fording Coal Mine), 330p 808 (330p Genesee) | 2021-01-26 07:00 | 2021-01-26 17:00 | N | N | op-checks to 808 breaker | Line, Circuit Breaker |  | Outage required for op-checks to 808 breaker | For Information Only
ALTALINK | 107s T1 (107s Westfield), 722L (107s Westfield - 368s Burdett) | 2021-01-26 07:15 | 2021-01-27 18:00 | N | N | maintenance | Transformer, Line |  | Wire JB on 138kV PTs (107s20), loop checks, finalize, swap out bus connectors. Install new motor mech on 107s2, test operate and adjust switch. Wire CTs on T1 for LOP on undervoltage protection, saturation test. Test operate equipment. 2nd Scope: Wire and commission trips to 368s722X from GE C60 for 368s879 (752) breaker fail. | For Information Only
ENMAX | 22.2TR (ENMAX 22) | 2021-01-26 08:00 | 2021-01-26 16:00 | N | N | slip over CT ground shield ground wire corrective, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 21B138-20.82 (ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21) | 2021-01-26 08:00 | 2021-01-26 16:00 | N | N | heater circuit contactor upgrades | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 186s C1 (186s Dry Creek) | 2021-01-26 08:15 | 2021-01-26 16:45 | N | N | investigate low gas alarm and possible leak with gas top up | Shunts |  |  | For Information Only
ALTALINK, EPCOR | 38s 738W (38s East Edmonton), 738L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2021-01-26 09:30 | 2021-01-26 17:00 | N | N | urgent testing & inspection | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 368s T2 (368s Burdett) | 2021-01-26 11:30 | 2021-01-26 14:30 | N | N | wire and commission trips to 368s42 from GE C60 for 368s879 (752) breaker fail | Transformer | 368s T2 (368s Burdett) This outage overlaps with 879L with affects the DG. |  | For Information Only
ALTALINK | 736L (38s East Edmonton - 293s Bernese) | 2021-01-27 07:00 | 2021-01-27 12:00 | N | N | maintenance | Line |  | Update 293s (C60/252) relay settings. Operate breakers 38s2952 and 293s252 to function test trips to Enbridge. Top up SF6 on 38s736E. | For Information Only
EPCOR | 330p 806 (330p Genesee) | 2021-01-27 07:00 | 2021-01-27 17:00 | N | N | outage required for op-checks to 806 breaker | Circuit Breaker |  |  | Creates Radial Feeds, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43), 43.1TR (ENMAX 43) | 2021-01-27 08:00 | 2021-01-28 16:00 | N | N | maintenance | Line, Transformer |  | HV SW maint SW81, SW82, SW83, MD-43.1TR | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.5TR (ENMAX 1) | 2021-01-27 08:00 | 2021-01-28 16:00 | N | N | noise investigation, check reversing switch | Transformer |  | 1BA8-1.5TR Noise Invesigation. Check Reversing Switch | For Information Only
ATCO | 7L24 (846s Grand Centre - 7L24D3) | 2021-01-27 08:00 | 2021-01-28 12:00 | N | Y | pole replacement | Line |  | Pole replacement | Creates Radial Feeds, Firm Load Loss
ALTALINK | 668L (394s Empress - 562s Cypress), 562s 1352 (562s Cypress), 562s 1452 (562s Cypress) | 2021-01-27 08:00 | 2021-01-28 17:30 | N | N | replace 562s53 PT | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 293s T2 (293s Bernese) | 2021-01-27 11:00 | 2021-02-19 09:00 | N | N | Customer bus connection to the AltaLink system. | Transformer |  |  | For Information Only
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2021-01-27 12:30 | 2021-01-27 15:30 | N | Y | maintenance | Line | 612L (336s Fincastle - 368s Burdett) | Wire and commission trips to 368s612 from GE C60 for 368s879 (752) breaker fail. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2021-01-28 08:00 | 2021-01-28 12:00 | N | Y | high load move under STR 143-144 | Line |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 844L (358s Amoco Brazeau - 477s Amoco West Pembina) | 2021-01-28 12:45 | 2021-01-28 17:00 | N | N | high load move under STR 42-43 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
Saskpower | SaskPower C1S | 2021-01-29 14:00 | 2021-03-19 17:00 | N | Y | replacing 4 structures and stringing across Lake Diefenbaker | Line | SaskPower C1S | replacing 4 structures and stringing across Lake Diefenbaker | Limits ATC
EPCOR | 72MG16 (Garneau - Meadowlark), T3 (Meadowlark) | 2021-01-30 07:00 | 2021-01-31 17:00 | N | N | investigate repair/damaged cables | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 1080L (ENMAX 25 - ENMAX 65) | 2021-01-30 08:00 | 2021-01-30 16:00 | N | Y | repair hotspot | Line |  |  | 240 kV, Pre-Condition
EPCOR | 987s T2 (987s Clover Bar), 987s T4 (987s Clover Bar), 987s CC721 (987s Clover Bar) | 2021-02-01 07:00 | 2021-02-04 17:00 | N | Y | breaker op-checks | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 805s T3 (805s Jasper), 805s J2404 (805s Jasper), 805s J2405 (805s Jasper) | 2021-02-01 07:00 | 2021-02-03 15:00 | N | Y | breaker op-checks | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 997L (71s Lamoureux - 410s Josephburg), 921L (71s Lamoureux - 987s Clover Bar), 71s 1252 (71s Lamoureux), 71s 1352 (71s Lamoureux), 71s 1452 (71s Lamoureux) | 2021-02-01 07:00 | 2021-02-04 07:00 | N | Y | replace DC junction box | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 7L64 (779s Chinchaga River - 789s Keg River) | 2021-02-01 08:00 | 2021-02-08 12:00 | N | Y | changing cross arms | Line | 7L64 (779s Chinchaga River - 789s Keg River) | Changing cross arms for wildfire mitigation | Pre-Condition, Affects Cranking Path
ENMAX | 2.2TR (ENMAX 2) | 2021-02-01 08:00 | 2021-02-03 16:00 | N | N | GIS switch maintenance | Transformer |  | GIS Switch Maintenance 2B8-2.25, 2B8-2.27, 2B8-2.BT6, 2B8-2BT5, 2SW225_225G, 2SW227_227G, 2SW520_520G, 2SW523_523G, 2SW508_508G. Oil sampling TC, MT. Check Reversing Switch. Filmax. Maint. | For Information Only
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | 2021-02-01 08:00 | 2021-02-03 16:00 | N | N | HV SW maintenance | Line, Transformer | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | HV SW maint SW81, SW82, SW83, SW84, SW89, MD-22.1TR, MD-22.3TR | Creates Radial Feeds, Firm Load Loss
ATCO | 7L228 (845s Big Mountain - 2091s Thornton) | 2021-02-01 08:00 | 2021-02-03 17:04 | N | Y | Mitigation work, changing poles and wire work | Line |  | Mitigation work, changing poles and wire work | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 863L (618s Riverbend - 891L tap) | 2021-02-01 09:00 | 2021-02-01 18:00 | N | Y | insulator bell resistance testing on 863L structures range 79-159 | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage
SUNCOR | 139S Hillridge | 2021-02-01 11:10 | 2021-02-01 15:32 | N | N | communication issues | Station |  |  | For Information Only
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2021-02-01 12:00 | 2021-02-02 18:00 | N | Y | component and fire mitigation bundled Str's range 2-24 | Line | 920L (37s North Calder - 557s Castle Downs) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 805s J724 (805s Jasper), 72JW19 (805s Jasper - Woodcroft) | 2021-02-02 07:00 | 2021-02-02 17:00 | N | N | maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 2075s ACF12 (2075s Newell) | 2021-02-02 07:30 | 2021-02-02 17:30 | N | N | repair structural towers | Shunts |  | Repair Structural Towers Supporting ACF12 Capacitor Banks, No constraints, redundant filter bank ACF22 is still in service | 240 kV, For Information Only
ALTALINK | 64s East Crossfield 138kV Bus1, 64s East Crossfield 138kV Bus2 | 2021-02-02 08:00 | 2021-02-02 18:00 | N | Y | Real-time repair for copper theft replacement | Bus |  | URGENT REQUEST | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Restricts Generation
ALTALINK | 28s 25 (28s West Brooks) | 2021-02-02 08:00 | 2021-02-22 16:15 | N | N | emergency work | Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-02-02 08:00 | 2023-01-10 18:00 | N | N | 29EDD-221 | Not In Model | 29EDD-221;29PT-605 SYSTEM;PM 5y,10y and SUBSTATION GROUND TEST; PM 5y - 34.5kV |  | For Information Only
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2021-02-03 07:00 | 2021-02-05 17:30 | N | Y | component's and fire mitigation bundled str's range 26-100 | Line | 920L (71s Lamoureux - 557s Castle Downs) | Component's and Fire Mitigation Bundled Str's range 26-100 | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 9L101 (957s McClelland - 2005s Secord) | 2021-02-03 07:00 | 2021-02-06 14:45 | N | Y | line move for mine expansion | Line | 9L101 (2005s Secord - 957s McClelland) | Line move for mine expansion. Attach new line to existing 9L101 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2021-02-03 08:00 | 2021-02-15 17:00 | N | N | line rebuild and maintenance | Line | 890L (58s Edson - 207s Pinedale) | Scope of work includes rebuilding portion of 890L between strs 77 and 87A and Maintenance on structures 122 and 123 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 398L (545s Provost -277s Hayter) | 2021-02-03 08:00 | 2021-02-17 16:00 | N | N | P1782 ISD Feb 10, 2021 | Line
Lethbridge, ALTALINK | 111s 207L (111s Coalbanks), 207L (111s Coalbanks - 370s North Lethbridge) | 2021-02-03 08:00 | 2021-02-03 12:00 | N | N | make changes and re-test C60 relay | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 35s 9 (35s Rundle) | 2021-02-03 08:00 | 2021-04-11 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 757s 607 (757s Battle River), 757s 607C (757s Battle River) | 2021-02-03 08:00 | 2021-02-03 15:00 | N | N | testing 607C SPAJ relay | Circuit Breaker, Shunts |  | Testing 607C SPAJ Relay, Cap unavailable during testing but can be restored within 10 minutes if required | For Information Only, Pre-Condition
ENMAX | 28.2TR (ENMAX 28) | 2021-02-03 08:00 | 2021-02-03 16:00 | N | N | replace MT gas relay - crack in gas gauge glass, check reversing switch | Transformer |  | 28.2TR - replace MT gas relay -crack in gas gauge glass. Check Reversing Switch | For Information Only
ENMAX | 2.2TR (ENMAX 2) | 2021-02-03 16:00 | 2021-02-05 16:00 | N | N | GIS maintenance | Transformer |  | GIS Maintenance 2SW325, 2SW425_425G, 2SW327, 2SW427_427G, 2SW518_518G, 2SW509_509G. | For Information Only
ALTALINK | 71s 1352 (71s Lamoureux) | 2021-02-04 07:00 | 2021-02-16 15:00 | N | Y | replacing M/O breaker with a new SF6 breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) | 2021-02-04 08:00 | 2021-02-05 16:00 | N | N | HV SW maintenance SW85, SW86, SW87, SW88, MD-22.2TR | Line, Transformer | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 21.1TR (ENMAX 21) | 2021-02-04 08:00 | 2021-02-04 16:00 | N | N | replace winding temp gauge, check reversing switch | Transformer |  | 21.1TR Corrective - Replace winding temp gauge. Check Reversing Switch | For Information Only
CMH | MH69S-1 Power Plant Switchyard RTU/SCADA | 2021-02-04 08:00 | 2021-02-04 10:00 | N | N | CMH1 switch 12 replacement | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 237s 152 (237s Foothills) | 2021-02-04 08:30 | 2021-02-04 13:30 | N | N | replace breaker heaters | Circuit Breaker |  |  | Contingency Requires Mitigation
SUNCOR | 139S Hillridge | 2021-02-04 14:25 | 2021-03-02 11:25 | N | N | troubleshoot the operational functionality of the cap bank | Station |  |  | For Information Only
ALTALINK | 163s 6352 (163s Amoco Empress), 163s C1 (163s Amoco Empress) | 2021-02-04 18:00 | 2021-02-19 18:00 | N | N | emergency troubleshoot | Circuit Breaker, Shunts | 163s C1 (163s Amoco Empress) | real time outage due to a failure on the heater circuit associated with breaker 163s6352 (C1 cap bank breaker). | For Information Only, Pre-Condition
ALTALINK | 3L (245s Seebe - 3AL) | 2021-02-05 07:00 | 2021-02-10 18:00 | N | N | replacing structures 4 and 7 and maintenance on structures 1, 2, 6, 19, 29, 32, 36, 38, 53, 54, 55, 62, 132 and 133 | Line |  | scope of work includes replacing structures 4 and 7 and maintenance on structures 1, 2, 6, 19, 29, 32, 36, 38, 53, 54, 55, 62, 132 and 133 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
SUNCOR | 29EDD-65 Edd65Sub | 2021-02-05 08:00 | 2021-02-06 18:00 | N | N | 29EDD- 65; battery main and test | Station |  | 29EDD- 65; battery main and test; PDM 5y (A) | For Information Only
ATCO | 7L228 (845s Big Mountain - 2091s Thornton) | 2021-02-07 12:00 | 2021-02-10 12:00 | N | Y | mitigation work, changing poles and wire work | Line |  | Mitigation work, changing poles and wire work | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2021-02-08 07:15 | 2021-02-11 12:45 | N | Y | Calgary ring Rrad 50L line clearance | Line |  | Calgary Ring Road 50L line clearance  Outage required for bolt replacement on new Str 133 and 134 and 135 steel poles. | For Information Only, Pre-Condition
ENMAX | 2.1TR (ENMAX 2) | 2021-02-08 08:00 | 2021-02-10 16:00 | N | N | GIS minor maintenance | Transformer |  | GIS minor maintenance 2SW536, 2SW542, 2SW544, 2SW547, 2SW221, 2SW549G, 2SW223, 2SW421, 2SW423, 2B8-2.BT10, 2B8-2.21, 2B8-2.23. | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-02-08 09:00 | 2021-02-08 16:00 | N | Y | closing temporary open point 'C' @ structure #1A | Line | 909L (310p Sundance - 665s Dome), |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 277s Hayter 138kV Bus, 398L (545s Provost -277s Hayter), 277s T2 (277s Hayter) | 2021-02-08 10:00 | 2021-02-10 13:00 | N | Y | protections on 277s852 will be completed along with 398L energized | Bus, Line, Transformer | P1782, V.Chan Jan 26, 2021 | Protections on 277s852 will be completed along with 398L and associated equipment being energized | For Information Only, Restricts Generation
ATCO | 7L64 (747s Bassett - 748s Haig River), 7L64 (747s Bassett - 930s Arcenciel), 7L64 (748s Haig River - 779s Chinchaga River) | 2021-02-08 12:00 | 2021-03-30 16:00 | N | Y | changing cross arms for wildfire mitigation | Line |  | Changing cross arms for wildfire mitigation | Pre-Condition, Affects Cranking Path
ALTALINK | 42s 74 (42s Sarcee), 42s C2 (42s Sarcee) | 2021-02-08 13:00 | 2021-02-09 17:00 | N | Y | emergency repair replace failed relay | Circuit Breaker, Shunts |  | Emergency Repair; replace failed relay | 240 kV, Pre-Condition
ENMAX | 162B240-RB135 (ENMAX 162) | 2021-02-09 08:00 | 2021-02-09 16:00 | N | Y | replace motor cut off switch | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 9L57 (939s Livock - 960s Birchwood Creek) | 2021-02-09 10:00 | 2021-02-15 17:00 | N | Y | setting poles for new OPGW | Line |  | Setting poles for new OPGW | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2021-02-10 07:00 | 2021-02-17 19:00 | N | Y | annual inspection and maintenance | Line | Annual Inspection and Maintenance, VCS and Valve Hall Work; AML Crews will be installing vibration recorders on Structures #491 & 494 |  | 500 kV, Pre-Condition
ALTALINK | 504S Queenstown, 161L (255s Vulcan - 504s Queenstown), 853L (504s Queenstown - 853AL) | 2021-02-10 07:30 | 2021-02-10 16:30 | N | N | add LAs to 138 kV bus | Station, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 31.1C (ENMAX 31) | 2021-02-10 08:00 | 2021-02-11 16:00 | N | N | relay, protection testing | Shunts | Relay, Protection Testing - 31RLY138-31CAP |  | For Information Only, Pre-Condition
ENMAX | 65B138-D85 (ENMAX 65) | 2021-02-10 08:00 | 2021-02-10 12:00 | N | N | heater circuit contactor upgrades | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2021-02-10 08:00 | 2021-02-12 18:00 | N | Y | component's and fire mitigation bundled str's range 26-100 | Line | 920L (71s Lamoureux - 557s Castle Downs) | Component's and Fire Mitigation Bundled Str's range 26-100 | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2021-02-10 08:15 | 2021-02-10 16:45 | N | N | investigated POW controller for 5s752 | Shunts | 5s752 is generating a breaker trouble alarm every time it is called to close. Investigated POW controller for 5s752 |  | For Information Only, Pre-Condition
ENMAX | 65B138-D84 (ENMAX 65) | 2021-02-10 12:00 | 2021-02-10 16:00 | N | N | heater circuit contactor upgrades | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 715L (545s Provost - 650s Hansman Lake), 715AL (650s Hansman lake - 715L Tap) | 2021-02-10 14:00 | 2021-02-15 18:00 | N | N | upgrading 715L A and B protections at 650s Hansman Lake, a new ethernet switch will be installed at 650s | Line | Upgrading 715L A and B protections at 650s Hansman Lake. End-end testing will be completed between 650s and 545s on the new TPR channel. A new ethernet switch will also be installed at this time as well at 650s. Reclosers on 715L at both 650s and 545s will need to be operated to function test the protection scheme. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 2.1TR (ENMAX 2) | 2021-02-10 16:00 | 2021-02-11 16:00 | N | N | GIS minor maintenance | Transformer | GIS Minor Maintenance 2SW537, 2SW543, 2SW545, 2SW548, 2SW321, 2SW550G, 2SW323 |  | For Information Only
AESO-SC | ABS1 Burdett Solar | 2021-02-11 07:00 | 2021-03-17 16:00 | N | N | P1849. 10.5 MW Solar, ISD Feb 18, 2021 | Unit
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2021-02-11 07:00 | 2021-02-11 18:00 | N | N | maintenance on structure 298 and 373 | Line |  | scope of work includes maintenance on structure 298 and 373 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 65B138-D81 (ENMAX 65) | 2021-02-11 08:00 | 2021-02-11 12:00 | N | N | heater circuit contactor upgrades | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 65B138-D82 (ENMAX 65) | 2021-02-11 12:00 | 2021-02-11 16:00 | N | N | heater circuit contactor upgrades | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-02-12 09:00 | 2021-02-12 17:00 | Y | Y | LLP for tree removal | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-02-13 06:15 | 2021-02-15 15:45 | N | Y | component replacement and structure changes | Line |  | Component Replacement and Structure changes From structure 146 to 252. Line to be out continuous. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37), 37.2TR (ENMAX 37) | 2021-02-13 08:00 | 2021-02-14 16:00 | N | Y | HV SW maint SW84, SW85, SW86, MD-37.2TR | Line, Transformer | 37.82L (74s Janet - ENMAX 37), 37.2TR (ENMAX 37) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | WEF1 Westfield Solar | 2021-02-15 08:00 | 2021-03-18 16:00 | N | N | P2171. 19 MW Solar DER. ISD Feb 22, 2021 | Unit
FORTIS | BUR1 Burdett Solar | 2021-02-15 08:00 | 2021-03-16 16:00 | N | N | P2241. 20 MW Solar DER. ISD Feb 22, 2021 | Unit
ATCO | 9L99 (801s Anderson - 807s Sheerness) | 2021-02-15 10:00 | 2021-03-16 16:00 | N | Y | customer to complete their substation lighting work, 901A disconnect work | Line |  | Heartland Generation has asked ATCO to take 9L99 out of service on the morning of Feb 13 2021. Sheerness will require a condition guarantee on 9L99 to complete their substation lighting work. There is also work planned for 901A disconnect, | 240 kV, Restricts Generation, Affects Cranking Path
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-02-16 06:15 | 2021-02-19 15:45 | N | Y | component replacement and structure changes from structure 146 to 252 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
EPCOR | 803s T1 (803s Lambton), 803s L2401 (803s Lambton), 803s L2402 (803s Lambton) | 2021-02-16 07:00 | 2021-02-19 17:00 | N | Y | breaker op-checks | Transformer, Circuit Breaker |  | Outage required breaker op-checks | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 748L (267s Killarney Lake - 277s Hayter), 277s T1 (277s Hayter) | 2021-02-16 07:00 | 2021-03-07 10:00 | N | N | installing a new 138kV breaker and associated equipment | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia), 805s J2403 (805s Jasper), 805s J2404 (805s Jasper) | 2021-02-16 07:00 | 2021-02-19 17:00 | N | Y | breaker op-checks | Line, Circuit Breaker |  | Outage required for breaker op-checks | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1041L (370s North Lethbridge - 554s Travers) | 2021-02-16 07:00 | 2021-02-17 18:00 | N | Y | install phase raiser Str 208 for line clearance mitigation | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe) | 2021-02-16 07:15 | 2021-02-27 17:45 | N | Y | maintenance | Line |  | Scope of work includes replacing structures 18, 19, 20, 30, 31, 39, 68, 70, 73, 74, 76, 100, 102 and 103 and maintenance on structures 21, 22 and 69 | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 511s SVC Plus (511s Crossings) | 2021-02-16 07:30 | 2021-02-17 16:30 | N | Y | programming upgrade and fire system cross-zoning | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 661s T1 (661s Laura Lake) | 2021-02-16 08:00 | 2021-02-16 17:00 | N | N | install bird coverup | Transformer |  |  | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2021-02-16 08:00 | 2021-02-16 16:00 | N | N | replace winding and temperature gauges; check reversing switch | Transformer |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32), 31B138-31.84 (ENMAX 31), 32B138-31.84 (ENMAX 32), 32B138-32BT5 (ENMAX 32) | 2021-02-16 08:00 | 2021-02-17 16:00 | N | N | switch maintenance SW81, SW82, SW90, MD-32.3TR | Line, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 7L22 (790s Poplar Hill - 7L22D3), 790s 702 (790s Poplar Hill) | 2021-02-16 08:00 | 2021-02-24 19:24 | N | Y | upgrade protection | Line, Circuit Breaker |  | Upgrade protection/alarms on 702 and 7L22 relays. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 71s 1252 (71s Lamoureux) | 2021-02-16 08:00 | 2021-02-17 08:00 | N | Y | replacing with new SF6 breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation,Affects Cranking Path
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2021-02-16 09:00 | 2021-02-19 18:00 | N | N | component replacements | Line | 202L (58s Edson - 178s Cynthia) | Component Replacements on Str's range 373-813 | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2021-02-16 09:15 | 2021-02-26 17:45 | N | Y | damper replacements (Str's 1-389) | Line |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-02-16 10:00 | 2021-02-16 16:00 | N | Y | creating temporary open point 'C' @ structure #1A | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2021-02-16 10:00 | 2021-02-25 16:00 | N | Y | replacement of under rated and rotten cross arms | Line |  | Replacement of under rated and rotten crossarms | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-02-16 16:00 | 2021-02-23 08:00 | N | Y | replacing structure #4 | Line |  | 909L (Open Point 'C' - E665s) - GOI replacing structure #4 | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
AESO-SC | OATI | 2021-02-16 18:00 | 2021-02-16 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK, EPCOR | 738L (38s East Edmonton - 95s Imperial Oil Edmonton), 38s 738W (38s East Edmonton) | 2021-02-17 07:00 | 2021-02-18 18:00 | N | N | P5 urgent repairs on 738L overhead shield wire and breaker testing | Line, Circuit Breaker |  | P5 Urgent repairs on 738L overhead shield wire due to storm. 738L10- OHSW separating. Also Epcor performing repairs on their 738AL1 switch on Feb 11. Required for MAPs crew 38s738W Breaker testing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Hardisty), 72LH8 (803s Lambton - Hardisty) | 2021-02-17 07:00 | 2021-02-24 17:00 | N | N | transformer replacement | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 39.2TR (ENMAX 39) | 2021-02-17 08:00 | 2021-02-17 16:00 | N | N | corrective - replace winding and temperature gauges and check reversing switch | Transformer |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2021-02-17 08:00 | 2021-02-17 16:00 | N | N | oil sampling | Transformer |  | Oil sampling MT, TC. Check Reversing Switch. Rodent Prevention (Duct Seal) 31.2TR MD | For Information Only, Pre-Condition
ENMAX | 162.3TR (162s Beddington) | 2021-02-17 08:00 | 2021-02-17 16:00 | N | N | RTU commissioning | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 71s T1 (71s Lamoureux), 71s 1252 (71s Lamoureux), 71s 1352 (71s Lamoureux), 921L (71s Lamoureux - 987s Clover Bar) | 2021-02-17 08:00 | 2021-02-20 10:00 | N | Y | replacing M/O breaker | Transformer, Circuit Breaker, Line | Replacing M/O Breaker with a new SF6 Breaker |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 2B138-D91 (ENMAX 2) | 2021-02-17 08:00 | 2021-02-17 16:00 | N | N | GIS minor maintenance | Circuit Breaker |  | GIS Minor Maintenance 2B138-D91, 2MD103_103G, 2MD100_100G. | For Information Only
ATCO | 801s 907 (801s Anderson) | 2021-02-17 08:00 | 2021-02-18 17:00 | N | Y | forced outage | Circuit Breaker |  | 801S Anderson 907 BREAKER MIN OIL HLR PARTIAL TESTING BKR 907 Partial Maint. SHEERNESS UNIT 1 TIED TO SYSTEM BY BKR 906 ONLY | 240 kV, Contingency Requires Mitigation
ALTALINK | 353s 138 kV Bus 1 (353s Plamondon) | 2021-02-17 20:00 | 2021-02-17 23:59 | N | N | urgent - VT3 investigation and cable repair | Bus | URGENT 353s31 - VT3 investigation and cable repair from VTs secondary connection box and outdoor JBVT3. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove) | 2021-02-18 07:00 | 2021-02-20 18:00 | N | N | scope of work includes maintenance on structures 212, 215, 217, 218, 220 and 221 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 763L (28s West Brooks - 763AL) | 2021-02-18 07:15 | 2021-02-18 17:45 | N | N | emergency repair; damper repair (str 763L56) | Line |  |  | Pre-Condition
ENMAX | 6.82L (ENMAX 6 - ENMAX 41), 6.1TR (ENMAX 6) | 2021-02-18 08:00 | 2021-02-19 16:00 | N | N | leak found, oil sampling, bushing, check reversing switch | Line, Transformer |  | 6PT138-Z31 South Leak Found. Oil Sampling TC, Bushing. Check Reversing Switch. 6.1TR Corrective - Secondary Cable Circulating Current Hazard | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 36.2TR (ENMAX 36) | 2021-02-18 08:00 | 2021-02-18 16:00 | N | N | replace temperature gauges, secondary cable circulating current hazard | Transformer |  | 36.2TR Corrective - Replace both liquid and winding temp gauges. Check Reversing Switch. 36.2TR Corrective - Secondary Cable Circulating Current Hazard | For Information Only
ALTALINK | 293s T2 (293s Bernese) | 2021-02-19 08:00 | 2021-02-22 16:00 | N | N | customer testing on 490-SWGR-1-IS and customer bus connection to AltaLink system | Transformer | ISD for SET1 is March 1. |  | For Information Only
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-02-20 06:15 | 2021-02-22 15:45 | N | Y | component replacement and structure changes from structure 146 to 252 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2021-02-20 07:00 | 2021-02-27 18:00 | N | Y | install phase raiser assemblies on structures 51, 52, 80, 81 for clearance mitigation | Line |  | Install Phase raiser assemblies on structures 51, 52, 80, 81 for clearance mitigation | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 37.81L (ENMAX 37 - ENMAX 38), 37.1TR (ENMAX 37) | 2021-02-20 08:00 | 2021-02-21 16:00 | N | N | switch maintenance, check reversing switch | Line, Transformer |  | HV SW maint SW81, SW82, SW83, MD-37.1TR. Check Reversing Switch | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-02-20 09:00 | 2021-02-20 17:00 | Y | Y | LLP for tree removal | Line | 1L274 (48s Pocaterra - Britt Creek) | LLP for tree removal | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 71s 1252 (71s Lamoureux) | 2021-02-20 10:00 | 2021-02-23 10:00 | N | Y | replacing with new SF6 breaker | Circuit Breaker |  | Replacing M/O Breaker with a new SF6 Breaker | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2021-02-21 07:00 | 2021-02-21 18:00 | N | Y | maintenance | Line |  | Scope of work includes maintenance on str 17 See Also 273230 908L RB required due to proximity - Common Tower | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2021-02-22 06:00 | 2021-02-26 16:00 | N | N | forced outage | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 803s T2 (803s Lambton), 803s L2402 (803s Lambton), 803s L2405 (803s Lambton) | 2021-02-22 07:00 | 2021-02-26 17:00 | N | Y | breaker op-checks | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RG7 (Garneau - Rossdale), G722 (Garneau), G723 (Garneau), RG725 (Rossdale) | 2021-02-22 07:00 | 2021-02-26 17:00 | N | N | SF6 maintenance | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T4 (805s Jasper), 805s J2405 (805s Jasper), 805s J2406 (805s Jasper) | 2021-02-22 07:00 | 2021-02-26 17:00 | N | Y | breaker op-checks | Transformer, Circuit Breaker |  | Outage required for breaker op-checks | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | Sask Power A1P | 2021-02-22 08:00 | 2021-03-04 11:00 | N | Y | maintenance | Line | Sask Power A1P |  | Limits ATC, Pre-Condition
ENMAX | 6.82L (ENMAX 6 - ENMAX 41), 33.83L (ENMAX 33 - ENMAX 41), 41.2TR (ENMAX 41), 41.1C (ENMAX 41), 33B138-33.83 (ENMAX 33), 41B138-41BT3 (ENMAX 41) | 2021-02-22 08:00 | 2021-02-25 16:00 | N | N | maintenance | Line, Transformer, Shunts, Circuit Breaker | 6.82L (ENMAX 6 - ENMAX 41), 33.83L (ENMAX 33 - ENMAX 41), 41.2TR (ENMAX 41), 41.1C (ENMAX 41) | HV SW maint SW81, SW82, SW83, SW87, SW88, SW89, SW90, SW95, MD-41.2TR | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.3TR (ENMAX 32) | 2021-02-22 08:00 | 2021-02-24 08:00 | N | N | GIS switch maintenance | Transformer |  | GIS Switch Maintenance 32SW502_502G, 32SW510, 32SW503, 32SW505, 32SW507, 32SW509, 32SW219, 32SW419, 32SW512, 32SW514G, 32SW221, 32SW421, 32B8-32.BT2, 32B8-32.BT4, 32B8-32.3TR, 32B8-32.19, 32B8-32.21, 32B8-32.BT3 32.3TR. 8kV bus 1-1. 2-1. 8-32.19. 8-32.21. | For Information Only
BCH | Natal T4 (BCH Natal) | 2021-02-22 08:00 | 2021-03-05 18:00 | N | Y | 2B1 PN upgrades | Transformer | Natal T4 (BCH Natal) |  | 240 kV, For Information Only
SUNCOR | 29EDD-1, 29PL9-17 (29EDD-1 Millennium - 29EDD-94 Voyageur) | 2021-02-22 08:00 | 2021-02-28 18:00 | N | Y | 29PT-419 & 29PT-418 5 & 10 Year PM | Terminal Equipment, Line |  | 29PT-419 & 29PT-418 5 & 10 Year PM | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENBRIDGE | SET1 South Edmonton Terminal | 2021-02-22 08:00 | 2021-03-08 16:00 | N | N | P2203 Enbridge South Terminal Gas. 20 MW Gas. ISD Mar 1, 2021 | Unit
ALTALINK | 256s C1 (256s Harmattan) | 2021-02-22 08:30 | 2021-02-25 15:30 | N | N | 138kV CT replacement | Shunts |  |  | Pre-Condition
BCH | 2L294 (A.A. Lambert - Nelway) | 2021-02-22 09:00 | 2021-02-26 17:00 | N | Y | flashed insulator replacement and arcing horn installation | Line | For OC: 1. Import ATC value of 550 MW is entered so that a value of 845 MW is posted for BC/MATL ATC import on S&D. 2. For BC/MATL import: TRMr+ = 200 MW, TRM = 200 + 65 = 265 MW. 3. BC/MATL import ATC = 1110 MW (from Table 6a and 6b SCP 302) - 265 MW = 845 MW. 4. In order to show 845 MW on S&D, we need to account for the max MATL import ATC: 310 MW (Table 3a) - 15 MW (MATL TRM) = 295 MW so the BC Import ATC becomes, 845 MW - 295 MW = 550 MW. |  | Limits ATC, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 17s 717W (17s Benalto) | 2021-02-22 09:30 | 2021-02-26 14:30 | N | Y | C60 replacement and commissioning | Line, Circuit Breaker |  | C60 Replacement and commissioning - See also below for trip tests associated with this work | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 677L (305s Acheson - 595s Spruce Grove) | 2021-02-22 09:30 | 2021-02-24 18:00 | N | N | replacing structure 32 and maintenance on structures 7, 15, 37 and 38 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 9.3TR (ENMAX 9) | 2021-02-22 12:00 | 2021-02-22 16:00 | N | N | install duct seal to the NGR cable duct | Transformer |  |  | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2021-02-22 12:00 | 2021-02-26 18:00 | N | N | component replacements on structure range 373-813 | Line |  | component replacements on structure range 373-813 and 202L178s Dead Ends | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 331s 421 (331s Ponoka), 421L (288s Wolf Creek - 331s Ponoka) | 2021-02-22 12:30 | 2021-02-22 15:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | Breaker maintenance and PRC5 (1st Trip, 1st Close, 2nd Trip) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 814L (28s West Brooks - 121s Brooks) | 2021-02-22 15:30 | 2021-02-22 16:15 | N | N | replace failed west phase CT for 28s25 | Line |  | Replace failed west phase CT for s25 currently OOS. Using 28s22 to test energize on return to service, 814L will be temporarily de energized. | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-02-23 06:15 | 2021-02-26 15:45 | N | Y | component replacement and structure changes from structure 146 to 252 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2021-02-23 07:00 | 2021-02-26 18:00 | N | N | replacing structure 260, installing a new mutt pole for the Fortis underbuilt  structure 259A and maintenance on structures 227, 231 and 255 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 133L (19s Wabamun - 234L), 522L (133L - 522AL), 522AL (868s Keephills Make-Up - 522L), 522L (866s Sundance Make-Up - 522AL tap) | 2021-02-23 07:00 | 2021-02-23 18:00 | N | N | fire mitigation on structures #679, 683 & 685 | Line |  |  | For Information Only
ENMAX | 36.5TR (ENMAX 36) | 2021-02-23 08:00 | 2021-02-23 16:00 | N | N | replace both liquid and winding temp gauges | Transformer |  | 36.5TR Corrective - Replace both liquid and winding temp gauges | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-02-23 08:00 | 2021-02-23 18:00 | N | Y | closing temporary open point 'C' @ structure #1A | Line |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 535s 5852 (535s Joffre) | 2021-02-23 09:30 | 2021-02-23 13:00 | N | N | 138kV Breaker Maintenance | Circuit Breaker
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar), 71s T1 (71s Lamoureux), 71s 1252 (71s Lamoureux), 71s 1352 (71s Lamoureux) | 2021-02-23 10:00 | 2021-02-23 16:00 | N | Y | replace risers on 1252 breaker | Line, Transformer, Circuit Breaker |  | 240kV West bus out of service to replace risers on 1252 breaker | Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2021-02-23 11:15 | 2021-02-23 16:45 | N | N | outage required for damper installation on str. 9 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L146 (700s Bonnyville - 970s Bourque) | 2021-02-23 12:00 | 2021-02-23 14:00 | N | Y | open for TPR outage | Line |  |  | Pre-Condition
ALTALINK | 535s 5752 (535s Joffre) | 2021-02-23 13:01 | 2021-02-23 16:30 | N | N | 138 kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon), 788L (157s Lac La Biche - 788AL), 157s T1 (157s Lac La Biche), 157s C1 (157s Lac La Biche) | 2021-02-24 07:00 | 2021-02-24 18:00 | N | N | replace C Phase on 138kV Bus PT2, and strain insulators at 728L dead end | Line, Transformer, Shunts | 157s T1 (157s Lac La Biche), 788L (157s Lac La Biche - 788AL), 728L (157s Lac La Biche - 353s Plamondon) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2021-02-24 07:00 | 2021-02-26 17:00 | N | Y | breaker op-checks | Line |  | Outage required for breaker op-checks | 240 kV, Contingency Requires Mitigation
ALTALINK | 901L (63s Red Deer - 901AL), 901L (74s Janet - 901AL) | 2021-02-24 08:00 | 2021-03-05 17:00 | N | Y | line protection upgrade for 901L at all three stations (three terminal line) | Line |  | line protection upgrade for 901L at all three stations (three terminal line). Includes relay replacements/setting changes at 63s/74s and relay firmware/setting changes at 64s. Line breakers will be required for outage duration for commissioning purposes. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 14.1TR (ENMAX 14) | 2021-02-24 08:00 | 2021-02-24 16:00 | N | N | liquid temp gauge replacement, check reversing switch, secondary cable circulating current hazard | Transformer |  | 14.1TR Liquid Temp Gauge Replacement. Check Reversing Switch. 14.1TR Corrective - Secondary Cable Circulating Current Hazard | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-02-24 08:00 | 2023-01-11 18:00 | N | N | 29EDD-211; substation ground test; PM 5y - 34.5kV | Not In Model |  |  | For Information Only
ENMAX | 32.3TR (ENMAX 32) | 2021-02-24 08:00 | 2021-02-25 16:00 | N | N | GIS switch maintenance | Transformer |  |  | For Information Only
ALTALINK | 942L (71s Lamoureux - 681s Bannerman) | 2021-02-24 09:00 | 2021-03-02 18:00 | N | Y | screw pile installation and foundation work | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 997L (71s Lamoureux - 410s Josephburg) | 2021-02-24 09:00 | 2021-03-02 18:00 | N | Y | screw pile installation and foundation work | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 756L (87s Gaetz - 535s Joffre) | 2021-02-24 09:15 | 2021-02-24 17:15 | N | N | 30 deg hotspot repair; 535s756X | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-02-24 11:00 | 2021-02-24 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | T2 (Hardisty) | 2021-02-24 17:01 | 2021-07-12 17:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22) | 2021-02-25 08:00 | 2021-02-25 12:00 | N | N | secondary cable circulating cCurrent hazard | Transformer |  | 22.2TR Corrective - Secondary Cable Circulating Current Hazard | For Information Only
ENMAX | 14.3TR (ENMAX 14) | 2021-02-25 08:00 | 2021-02-25 16:00 | N | N | liquid and winding temp gauge replacement, check reversing switch | Transformer |  | 14.3TR Liquid and Winding Temp Gauge Replacement. Check Reversing Switch | For Information Only
ALTALINK | 56s C1 (56s Boyle) | 2021-02-25 08:00 | 2021-02-25 17:30 | N | N | complete design changes to allow trip coil monitoring on cap bank breaker | Shunts |  |  | For Information Only
ENMAX | 5.1TR (ENMAX 5) | 2021-02-25 08:00 | 2021-02-25 16:00 | N | N | 5sub RTU commissioning | Transformer |  | 5sub RTU commissioning, close open required on return for commissioning | For Information Only
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-02-25 09:00 | 2021-02-25 13:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 535s 5452 (535s Joffre) | 2021-02-25 09:30 | 2021-02-25 13:00 | N | N | 138kV Breaker Maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 22.3TR (ENMAX 22) | 2021-02-25 12:00 | 2021-02-25 16:00 | N | N | secondary cable circulating current hazard | Transformer |  | 22.3TR Corrective - Secondary Cable Circulating Current Hazard | For Information Only, Pre-Condition
ATCO | 733s 701 (733s Simonette), 7L80 (733s Simonette - 740s H.R.Milner) | 2021-02-26 08:00 | 2021-02-27 16:00 | N | Y | 733S upgrade project | Circuit Breaker, Line |  | 733S Upgrade Project - Wiring modifications to 7L80PT and testing needs to be completed. The high side risers to 902Ss mobile sub will be attached to 7L80 during this outage. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Affects Cranking Path
ENMAX | 24.2TR (ENMAX 24) | 2021-02-26 08:00 | 2021-02-26 12:00 | N | N | secondary cable circulating current hazard, check reversing switch | Transformer |  | 24.2TR Corrective - Secondary Cable Circulating Current Hazard. Check Reversing Switch | For Information Only
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-02-27 06:15 | 2021-03-01 15:45 | N | Y | component replacement and structure changes from structure 146 to 252 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 733s Simonette 144kV Bus, 7L40 (733s Simonette - 813s Little Smoky) | 2021-02-28 08:00 | 2021-03-15 16:00 | N | Y | protection upgrade at 733s | Bus, Line |  | 7L80, 7L40, 702T, 25KV bus protection needs to be upgraded at 733s. This requires a 144KV station outage. 835s Mobile sub will be installed on 7L80 to by pass the 144KV to keep the 25KV load fed.835s mobile sub will be in service power the 25KV. Isolation points: Mar1-15: 733S 502TD, 733S 7L80D1, & 813S 7L40D3 Isolation Points Mar15-29: 733S 702A & 813S 7L40D3 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1045L (805s Jasper - 1045AL Tap), 1045L (310p Sundance - 1045AL), 1045AL (320p Keephills - 1045L) | 2021-02-28 09:00 | 2021-02-28 18:00 | N | Y | closing temporary open point 'A' @ structure #1A and open point 'B' @ structure #31 | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
EPCOR | T2 (Rossdale) | 2021-03-01 07:00 | 2021-03-05 17:00 | N | N | ABB warranty work R608N, R6T2 | Transformer |  |  | For Information Only
EPCOR | 805s T1 (805s Jasper), 805s C1 (805s Jasper), 72JW19 (805s Jasper - Woodcroft), 72JM18 (805s Jasper - Meadowlark), 805s J2401 (805s Jasper), 805s J2403 (805s Jasper) | 2021-03-01 07:00 | 2021-03-05 17:00 | N | Y | outage required for breaker op-checks | Transformer, Shunts, Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition
EPCOR | 803s T3 (803s Lambton), 803s L2405 (803s Lambton), 803s L2403 (803s Lambton), 803s L721 (803s Lambton) | 2021-03-01 07:00 | 2021-03-05 17:00 | N | Y | outage required for breaker op-checks | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-03-01 08:00 | 2023-02-04 18:00 | N | N | 29EDD-161; 29PT-582 system | Not In Model | Unmodeled Transmission Facility (Suncor), 29EDD-161; 29PT-582 SYSTEM ;PM 5y, 10y - 34.5kV |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-03-01 08:00 | 2023-02-05 18:00 | N | N | 29EDD-171; 29PT-600 system | Not In Model | Unmodeled Transmission Facility (Suncor), 29EDD-171; 29PT-600 SYSTEM; PM 5y, 10y - 34.5kV |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-03-01 08:00 | 2023-02-03 18:00 | N | N | 29EDD-221 ;29PT-605 system | Not In Model | 29EDD-221 ;29PT-605 system; PM 5y, 10y - 34kV |  | For Information Only
SUNCOR | 29PL9-16 (29EDD-1 Millennium - 29EDD-94 Voyageur), 29EDD-1 | 2021-03-01 08:00 | 2021-03-07 18:00 | N | Y | 29PT-419 and 29PT-418 5 | Line, Terminal Equipment |  | 29PT-419 & 29PT-418 5 & 10 Year PM | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.4TR (162s Beddington) | 2021-03-01 08:00 | 2021-03-01 16:00 | N | N | RTU commissioning and transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 8.2TR (ENMAX 8) | 2021-03-01 08:00 | 2021-03-01 16:00 | N | N | investigation for CT replacement and check reversing switch | Transformer |  |  | For Information Only
ATCO | 790s 703 (790s Poplar Hill), 7L07 (790s Poplar Hill - 815s Goodfare) | 2021-03-01 08:00 | 2021-03-09 16:00 | N | Y | upgrade 703 and 7L07 protection | Circuit Breaker, Line |  | Upgrade 703 and 7L07 protection | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54), 41.1TR (ENMAX 41), 54B138-41.84 (ENMAX 54), 41B138-41BT3 (ENMAX 41), 40B138-40.81 (ENMAX 40) | 2021-03-01 08:00 | 2021-03-03 16:00 | N | N | HV SW maint SW84, SW85, SW86, SW91, SW92, SW93, SW94, MD-41.1TR | Line, Transformer, Circuit Breaker | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54), 41.1TR (ENMAX 41) |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2021-03-01 09:15 | 2021-03-12 17:45 | N | Y | damper replacements (Str's 38-389) | Line |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 17s 637 (17s Benalto), 637L (17s Benalto - 580s Sylvan Lake) | 2021-03-01 10:00 | 2021-03-01 12:00 | N | N | trip test for 17s637 required for 17s717 C60 protection replacement | Circuit Breaker, Line |  | Trip test for 17s637 required for 17s717 C60 Protection replacement | Creates Radial Feeds, Firm Load Loss
ALTALINK | 434s 452 (434s Stony Plain), 452L (367s Harry Smith - 434s Stony Plain) | 2021-03-01 11:00 | 2021-03-04 13:30 | N | N | breaker maintenance | Circuit Breaker, Line |  | Breaker maintenance and 1st trip tests on 434s452. Replace 434s1. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2021-03-01 12:00 | 2021-03-05 18:00 | N | N | component replacements | Line |  | Component Replacements on Str's range 373-813 and 202L178s Dead Ends | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 9L11 (813s Little Smoky - 834s Wesley Creek) | 2021-03-01 12:00 | 2021-03-08 15:00 | N | Y | pole replacement and enforcers | Line |  | Pole replacement and enforcers | 240 kV, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 774L (276s Prentiss - 332s Ellis), 332s T1 (332s Ellis), 332s 152 (332s Ellis), 332s Ellis 138 kV South Bus, 276s 774N (276s Un Carb Prentiss) | 2021-03-01 12:15 | 2021-03-04 17:45 | N | N | 774L L3 A87 protection replacement | Line, Transformer, Circuit Breaker, Bus |  | 774L L3 A87 Protection Replacement. 2nd Scope Replace 276s1 damaged switch. 2nd Scope to repair damaged 276s1 switch. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 91 (17s Benalto), 17s 92 (17s Benalto) | 2021-03-01 12:30 | 2021-03-01 14:30 | N | N | trip test 17s92 required for 17s717 C60 protection replacement | Switch, Circuit Breaker |  | Trip test 17s92 required for 17s717 C60 Protection replacement | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 17s T3 (17s Benalto) | 2021-03-01 15:00 | 2021-03-01 17:00 | N | Y | trip test 17s2852 required for 17s717 C60 protection replacement | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 562s 2052 (562s Cypress) | 2021-03-02 08:00 | 2021-03-02 12:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Limits ATC
ALTALINK | 33s 6 (33s Spray) | 2021-03-02 08:00 | 2021-03-09 08:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 1106L (237s Foothills - ENMAX 65) | 2021-03-02 08:00 | 2021-03-02 18:00 | N | Y | maintenance | Line |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 747L (99s North St. Albert - 711L) | 2021-03-02 08:00 | 2021-03-04 17:30 | N | N | replacement of center phase PT | Line |  | Replacement of Center phase PT. 726L and 747L to be deenergized to facilitate the work. Relays OOS are: 726L, 747L, 898L, 81/25L1, 81/25L2. Temporary settings on 898L. See P&C assessment for further details. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 5.7TR (ENMAX 5) | 2021-03-02 08:00 | 2021-03-02 16:00 | N | N | maintenance | Transformer |  | 5sub RTU Commissioning. Network required for alternate switching. Open, close, open required on MD on return. Gas relay testing. Check Reversing Switch. Transformer Maintenance. Oil Sampling TC, MT | For Information Only
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2021-03-02 11:15 | 2021-03-02 16:45 | N | N | outage required for damper installation on Str. 9 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 562s 1452 (562s Cypress) | 2021-03-02 13:00 | 2021-03-02 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2021-03-03 07:00 | 2021-03-04 18:00 | N | N | maintenance on structures 253, 254, 264 and 265 11 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.8TR (ENMAX 5) | 2021-03-03 08:00 | 2021-03-03 16:00 | N | N | RTU commissioning | Transformer |  | RTU commissioning. network required for alternate switching, gas relay testing, transformer maintenance. check reversing switch, oil sampling, maintenance | For Information Only
ALTALINK | 562s 1752 (562s Cypress) | 2021-03-03 08:00 | 2021-03-03 12:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 162.3TR (162s Beddington) | 2021-03-03 08:00 | 2021-03-04 16:00 | N | N | GIS switch maintenance, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 1107L (237s Foothills - ENMAX 65) | 2021-03-03 08:00 | 2021-03-03 18:00 | N | Y | replace switch, remove bird nest & add deterant | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 51s 408N (51s Wainwright), 408L (51s Wainwright - 252s Jarrow) | 2021-03-03 09:00 | 2021-03-03 18:00 | N | N | rreaker maintenance and PRC5 (1st trip, 1st close, 2nd trip) | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 310pT35 (310p Sundance) | 2021-03-03 10:00 | 2021-03-10 16:00 | N | Y | replacement bus differential protection | Transformer |  |  | 240 kV
ALTALINK | 562s 1852 (562s Cypress) | 2021-03-03 13:00 | 2021-03-03 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 62s 12 (62s Brazeau) | 2021-03-03 23:00 | 2021-03-04 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 11 (62s Brazeau) | 2021-03-04 03:00 | 2021-03-04 07:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX | 38.1C (ENMAX 38), 38CS138-38CAP (ENMAX 38) | 2021-03-04 08:00 | 2021-03-04 16:00 | N | N | hot spot and switcher frame not grounded repairs | Shunts, Circuit Breaker |  |  | For Information Only, Pre-Condition
ENMAX | 7.2TR (ENMAX 7) | 2021-03-04 08:00 | 2021-03-04 16:00 | N | N | oil/winding temp alarms. check reversing switch | Transformer |  | 7.2TR oil/winding temp alarms. Check Reversing Switch | For Information Only
CapitalPower | 615S Halkirk | 2021-03-04 08:00 | 2021-03-04 14:00 | N | N | communications only outage to facilitate the door alarm switchover | Station |  |  | For Information Only
ALTALINK | 562s 1352 (562s Cypress) | 2021-03-04 08:00 | 2021-03-04 12:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 15.1TR (ENMAX 15) | 2021-03-04 08:00 | 2021-03-04 16:00 | N | N | corrective - rerun CT ground shield ground wire, liquid temp. gauge replacement, check reversing switch | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 1109L (ENMAX 25 - ENMAX 65), 65B240-D134 (ENMAX 65), 65B240-D135 (ENMAX 65) | 2021-03-04 08:00 | 2021-03-04 18:00 | N | Y | replace switch mech | Line, Circuit Breaker |  | 65 Sub SW140, SW139 Replace Switch Mech | 240 kV, Contingency Requires Mitigation
ALTALINK | 763L (158s Vauxhall - 257s Hull) | 2021-03-04 09:15 | 2021-03-04 17:45 | N | N | replace cracked insulators | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane) | 2021-03-05 07:00 | 2021-03-06 18:00 | N | N | maintenance on structures 98, 99, 106 and 111 | Line | Scope of work includes maintenance on structures 98, 99, 106 and 111 |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 40.1TR (ENMAX 40) | 2021-03-05 08:00 | 2021-03-05 16:00 | N | N | temp gauge replacement, check reversing switch, oil sampling | Transformer |  | 40.1TR Liquid and Winding Temp Gauge Replacement. Check Reversing Switch. Oil Sampling TC, MT | For Information Only
ATCO | 2075s ACF13 (2075s Newell) | 2021-03-05 08:00 | 2021-03-05 15:30 | N | Y | emergency repairs to filter bay | Shunts | Emergency Repairs to Filter Bay, redundant filter in service. | A lid on one of the reactors is damaged and could blow off into energized equipment causing more damage. | 240 kV, For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2021-03-05 08:00 | 2021-03-05 16:00 | N | N | rerun CT ground shield ground wire, check reversing switch | Transformer |  | 15.2TR Corrective - Rerun CT ground shield ground wire, Check Reversing Switch | For Information Only
ENMAX | 9.2TR (ENMAX 9) | 2021-03-05 08:00 | 2021-03-05 16:00 | N | N | H3 bushing/riser connection, check reversing switch, oil sampling | Transformer | 9.2TR - hot spot - H3 bushing/riser connection. Check Reversing Switch. Oil Sampling - 9.2TR - HV Bushings, MT, T |  | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-03-06 07:00 | 2021-03-14 18:00 | N | Y | install phase raiser assemblies on structures 51, 52, 80, 81 for clearance mitigation | Line |  | Install Phase raiser assemblies on structures 51, 52, 80, 81 for clearance mitigation. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-03-07 06:15 | 2021-03-08 15:45 | N | Y | component replacement and structure changes from structure 146 to 252 | Line |  | Outage Required for Component Replacement and Structure changes From structure 146 to 252. Line to be out continuous. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 748L (267s Killarney Lake - 277s Hayter), 277s T1 (277s Hayter) | 2021-03-07 10:00 | 2021-03-09 18:00 | N | N | facilitate end to end testing on 748L along with the reclosers | Line, Transformer |  | Crews will be returning their GOI and receiving an Advice to facilitate end to end testing on 748L along with the reclosers; all grounds will be removed for this work. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2404 (987s Clover Bar) | 2021-03-08 07:00 | 2021-03-11 17:00 | N | Y | outage required for breaker op checks | Line, Circuit Breaker |  | outage required for breaker op checks | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Affects Cranking Path
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 2021-03-08 07:00 | 2021-03-08 18:00 | N | N | replacing structures and maintenance | Line |  | Scope of work includes replacing structures 4A, 11A and 24 and maintenance on Structures 1A, 2A, 3A, 6A, 9A, 10A, 14A, 15A, 19A, 2, 24, 120 and 123A. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 1059L (803s Lambton - 1059AL), 803s L2401 (803s Lambton), 803s L2404 (803s Lambton) | 2021-03-08 07:00 | 2021-03-10 17:00 | N | Y | breaker op-checks | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RG1 (Garneau - Rossdale), G724 (Garneau), G725 (Garneau), RG7210 (Rossdale) | 2021-03-08 07:00 | 2021-03-12 17:00 | N | N | SF6 maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead) | 2021-03-08 07:00 | 2021-03-08 18:00 | N | Y | maintenance on structures 13, 20, 64 and 77 | Line |  | Scope of work includes maintenance on structures 13, 20, 64 and 77 | Creates Radial Feeds, Firm Load Loss
ALTALINK | 38s 7252 (38s East Edmonton) | 2021-03-08 07:30 | 2021-03-11 18:30 | N | Y | replace CT31 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2021-03-08 08:00 | 2021-03-08 16:00 | N | N | SF6 gas sample retest | Line | 9.80L (ENMAX 9 - ENMAX 31) | 9B138-9.80 SF6 gas sample retest (Dec 2020) | Pre-Condition
ALTALINK | 77s Sagitawah 240 kV East Bus, 77s Sagitawah 138 kV East Bus, 77s T2 (77s Sagitawah) | 2021-03-08 08:00 | 2021-03-12 12:00 | N | Y | replace 77s38, replace 240 kV East Bus protection | Bus, Transformer | 77s T2 (77s Sagitawah), 77s Sagitawah 240 kV East Bus | Replace 77s38. Replace 240kV East Bus Protection | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2021-03-08 08:00 | 2021-03-08 10:00 | N | N | 5sub RTU Commissioning. | Line |  |  | Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2021-03-08 08:00 | 2021-03-11 16:00 | N | N | line preventative maintenance | Line |  | Line Preventative Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) | 2021-03-08 08:00 | 2021-03-09 16:00 | N | N | HV switch maintenance | Line, Transformer |  | HV SW maint SW85, SW86, SW89, MD-39.1TR, MD-39.3TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s 1052 (121s Brooks) | 2021-03-08 08:15 | 2021-03-11 16:45 | N | N | 1052 breaker C60 cutover | Circuit Breaker |  | 1052 breaker C60 cutover | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, ATCO | 526s 152 (526s Buffalo Creek), 7L129 (526s Buffalo Creek - 918s Bauer) | 2021-03-08 09:00 | 2021-03-11 16:00 | N | Y | mitigation work for crossing | Circuit Breaker, Line |  | Mitigation work for crossing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.83L (ENMAX 5 - 2.83L tap), 5B138-2.83 (ENMAX 5) | 2021-03-08 10:00 | 2021-03-08 12:00 | N | N | 5sub RTU commissioning | Line, Circuit Breaker |  | 5sub RTU Commissioning. Open close open of 138kV disconnect switches required. | Pre-Condition
ALTALINK | 945s T2 (945s Sunshine Village) | 2021-03-08 11:30 | 2021-03-09 13:00 | N | N | training on the PAS breaker | Transformer |  | training on the PAS breaker - This is for Fortis's PLT training | For Information Only
ENMAX | ENMAX 5 PT138-Z33 (ENMAX 5) | 2021-03-08 12:00 | 2021-03-08 14:00 | N | N | 5sub RTU commissioning | Terminal Equipment |  | 5sub RTU Commissioning. Open close open of 138kV disconnect switch required. 2.83L Distance protection disabled while PTs are offline. Line remains protected by differential protection. | For Information Only
ALTALINK | 288s Wolf Creek 138kV Bus 2, 288s T2 (288s Wolf Creek) | 2021-03-08 12:00 | 2021-03-08 17:00 | N | N | repair loose PT terminal | Bus, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 37s 82 (37s North Calder), 37s 88 (37s North Calder) | 2021-03-08 12:00 | 2021-03-11 18:00 | N | Y | replace 37s83 switch | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Affects Cranking Path
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2021-03-08 12:00 | 2021-03-12 18:00 | N | N | component replacements | Line |  | Component Replacements on Str's range 373-813 and 202L178s Dead Ends | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 523s T1 (523s Bullshead) | 2021-03-08 12:30 | 2021-03-18 17:30 | N | N | oil recondition, corrosive sulphur removal, piping repairs and VR1 replace contacts | Transformer |  | T1; oil recondition, corrosive sulphur removal, piping repairs. VR1; replace contacts | For Information Only
ALTALINK | 892L (244s Bowmanton - 895s Suffield) | 2021-03-09 06:15 | 2021-03-11 16:30 | N | Y | component replacement and structure changes from structure 146 to 252 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 730L (197s Bardo - 732L) | 2021-03-09 07:00 | 2021-03-11 18:00 | N | N | install foundation for steel structure that will replace 730L Str 2 & 3 as part of component replacement project: foundation is under Str 730L3 guy wires | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 415s Drywood) | 2021-03-09 07:00 | 2021-03-11 18:00 | N | N | replacing structures 217, 218, 219, 220, 221, 222, 223, 224 and 229 and maintenance on structures 129, 130, 132, 177 and 178 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | RL1 (848s Ruth Lake - D05 Syncrude) | 2021-03-09 08:00 | 2021-03-11 20:00 | N | Y | maintenance | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 151s 765W (151s Strathmore), 765L (151s Strathmore - 419s Chestermere) | 2021-03-09 08:30 | 2021-03-09 17:30 | N | N | rebuild dashpot | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 827s SVC (827s Cranberry Lake) | 2021-03-09 09:00 | 2021-03-10 16:00 | N | Y | air cooled preventative maintenance | Shunts |  | Air Cooled Maintenance PM | Pre-Condition
ALTALINK | 757L (17s Benalto - 297s Rimbey) | 2021-03-09 09:00 | 2021-03-09 14:00 | N | N | trip test for 17s757 required for 17s717 C60 protection replacement | Line |  |  | Firm Load Loss, Pre-Condition
ALTALINK | 749AL (267s Killarney Lake - 749L), 748L (267s Killarney Lake - 277s Hayter), 267S Killarney Lake | 2021-03-10 07:00 | 2021-03-14 18:00 | N | N | install 276s16, and replacing SS1 station service transformer | Line, Station |  | Install 276s16, and replacing SS1 station service transformer. Demo grounding switch 267S1, 267s19 and 138kV Bus. Install new switch for 749L isolation 267s16. This is also the optimal time to tie in Cap bank CT's to new bus differential, and T1 CT's. Tripping 25kV breakers and Cap bank circuit switchers from new protections. | Creates Radial Feeds, Firm Load Loss
EPCOR | VHBB1 (Rossdale) | 2021-03-10 07:00 | 2021-03-10 12:00 | N | N | ops-check for various protection | Circuit Breaker |  | isolate VHBB1 and op check from various protection | Pre-Condition
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) | 2021-03-10 08:00 | 2021-03-11 16:00 | N | N | HV switch maintenance, check reverse switch, oil sampling and circulating current hazard | Line, Transformer |  | HV SW maint SW81, SW82, MD-39.2TR, MD-39.4TR, Check Reversing Switch 39.2, 39.4. Corrective 39MD138-39.4TR wouldnt electrically open over 90 degrees. 39.4TR Oil sampling TC. 39.4TR Corrective - Secondary Cable Circulating Current Hazard | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 151s 733E (151s Strathmore), 733L (151s Strathmore - 428S Namaka) | 2021-03-10 08:30 | 2021-03-10 17:30 | N | N | rebuild dashpot | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | VHBB2 (Rossdale) | 2021-03-10 12:00 | 2021-03-10 17:00 | N | N | ops-check for various protection | Circuit Breaker |  | Isolate VHBB2 for op checks from various protection | Pre-Condition
EPCOR | R72C1 (Rossdale) | 2021-03-11 07:00 | 2021-03-11 12:00 | N | N | op check from various protection | Circuit Breaker |  |  | Pre-Condition
EPCOR | RR723 (Rossdale) | 2021-03-11 07:00 | 2021-03-11 12:00 | N | N | isolate RR723 and op check from various protection | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 324s 1152 (324s Cassils) | 2021-03-11 08:30 | 2021-03-11 13:30 | N | Y | investigate/repair gas gauge, gas top up | Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | R72C2 (Rossdale) | 2021-03-11 12:00 | 2021-03-11 17:00 | N | N | op check from various protection | Circuit Breaker |  |  | Pre-Condition
EPCOR | RR729 (Rossdale) | 2021-03-11 12:00 | 2021-03-11 17:00 | N | N | isolate RR729 and op check from various protection | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2021-03-12 07:00 | 2021-03-19 14:45 | N | N | replace structures | Line | 174L (197s Bardo - 289s Saunders Lake) | Replacing structures, bird diverter installation, straighten leaning structures | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
EPCOR | 987s CCP7213 (987s Clover Bar) | 2021-03-12 07:00 | 2021-03-12 11:30 | N | N | breaker op-checks | Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29EDD-2 Tar Island | 2021-03-12 08:00 | 2021-03-16 18:00 | N | N | cable termination repair on line 29PL3-3 located in 29EDD-2/22 | Station | Not modelled in EMS or PSSE |  | For Information Only
ENMAX | 11.3TR (ENMAX 11) | 2021-03-12 08:30 | 2021-03-12 15:00 | N | N | rerun CT ground wire and check reversing switch | Transformer |  |  | For Information Only
EPCOR | 987s CCP7214 (987s Clover Bar) | 2021-03-12 12:30 | 2021-03-12 17:00 | N | N | breaker op-checks | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 320p 6A (320p Keephills), 320p 7A (320p Keephills) | 2021-03-12 15:00 | 2021-05-19 17:00 | N | Y | replacement of 320p852 and work on 320p589 | Switch |  |  | 240 kV, Restricts Generation
EPCOR | T2 (Strathcona) | 2021-03-12 22:00 | 2021-03-14 20:00 | N | N | emergency repair to bus tie cables | Transformer |  |  | For Information Only
ALTALINK | 38s T4 (38s East Edmonton) | 2021-03-13 08:00 | 2021-03-13 20:00 | N | Y | installation of grading capacitors to breaker 38s18 | Transformer |  | Installation of Grading Capacitors to Breaker 38s18 | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 121S Brooks | 2021-03-13 09:00 | 2021-03-14 17:00 | N | Y | urgent - replace 25 kV tie switch 121s43 | Station |  | Urgent replace 25kV Tie Switch 121s43 from real time damage that occured 2nd Scope: Test 121sT2 (Tx18408) due to fault that occured during real time outage | For Information Only
ALTALINK | 759L (87s Gaetz - 276s Prentiss) | 2021-03-14 07:15 | 2021-03-14 20:15 | N | N | urgebt - pole hit by vehicle and needs to be replaced 759L103 | Line |  | P5 Pole hit by vehicle and needs to be replaced 759L103 | For Information Only, Pre-Condition
ALTALINK | 749AL (267s Killarney Lake - 749L tap) | 2021-03-14 18:00 | 2021-03-29 18:00 | N | N | project work - new breaker addition and TPR/protection upgrades (P1782) | Line | P1782 | 267s requires new breaker addition including line, breaker fail & bus protections; 648s requires new TPR channel to 267s and modifications to existing line relay settings. 899s requires 749L Line relay upgrades, CVT addition, and installation of new control module with breaker fail protection on 899s749X breaker (local testing only at 899s required as no TPR channel from 899s to 648s or 267s). End to End Testing between 267s and 648s Metiskow. Requires recloser control at 648s and 267s | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 814s B2406 (814s Bellamy) | 2021-03-15 07:00 | 2021-03-17 17:00 | N | Y | breaker maintenance and repair | Circuit Breaker |  | B2406 breaker maintenance and repair | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1045L (805s Jasper - 1045AL Tap), 805s J2406 (805s Jasper), 805s J2407 (805s Jasper) | 2021-03-15 07:00 | 2021-03-17 17:00 | N | Y | breaker op-checks | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s SU2401 (657s Summerside), 657s SU2402 (657s Summerside) | 2021-03-15 07:00 | 2021-03-15 17:00 | N | Y | DFR upgrade | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Strathcona), S723 (Strathcona) | 2021-03-15 07:00 | 2021-03-23 17:00 | N | N | TX2 replacement | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | RS724 (Rossdale) | 2021-03-15 07:00 | 2021-03-15 12:00 | N | N | isolate RS724 and op check from various protection | Circuit Breaker |  |  | For Information Only
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2021-03-15 08:00 | 2021-03-20 17:00 | N | N | HV SW maintenance | Line, Transformer | HV SW maint SW83, SW84, SW85, SW86, SW87, SW88, SW89, MD-32.2TR, MD-32.1TR, SW83 CM, 32.2TR MD CM, Check Reversing Switch 32.1, 32.2, Oil Sampling 32.2TR Bushing |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 36.3TR (ENMAX 36) | 2021-03-15 08:00 | 2021-03-15 16:00 | N | N | maintenance | Transformer |  | 36.3TR Corrective - Secondary Cable Circulating Current Hazard. 36.3TR Tap Changer Investigate Oil Leak. Check Reversing Switch | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2021-03-15 08:00 | 2021-03-18 15:00 | N | N | line preventative maintenance | Line |  | Line Preventative Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RV2 (511s Victoria - Rossdale), 72RV4 (511s Victoria - Rossdale), 72RV6 (511s Victoria - Rossdale), 72VN21 (511s Victoria - Namao), N725 (Namao) | 2021-03-15 08:00 | 2021-03-26 17:00 | N | N | degassing RV cables | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L130 (705s Kitscoty - 710s Vermilion) | 2021-03-15 08:00 | 2021-03-15 17:00 | N | N | pole is leaning into the river | Line |  | pole is leaning into the river, needs to be repaired. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s T2 (121s Brooks) | 2021-03-15 08:15 | 2021-03-25 16:45 | N | N | cutover all protections for 25 kV as well as T2, airbreak control modules for 289, 489, 689 & addition of grounding relays to 25 kV feeders | Transformer |  |  | For Information Only
ALTALINK | 919L (77s Sagitawah - 310p Sundance), 77s 14 (77s Sagitawah), 77s 48 (77s Sagitawah) | 2021-03-15 09:00 | 2021-03-19 11:00 | N | Y | replace CVTs & strain insulators | Line, Circuit Breaker | 919L (77s Sagitawah - 310p Sundance) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 17s T2 (17s Benalto), 17s 85 (17s Benalto) | 2021-03-15 09:30 | 2021-03-25 14:30 | N | Y | T2 A prot replacement, 289 control modifications, various alarm changes | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 959S SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2021-03-15 10:00 | 2021-03-26 16:00 | N | Y | yearly turn around - PRC relay testing - work in valve hall - fan replacement | Shunts, Circuit Breaker |  | Yearly turn around - PRC relay testing - work in valve hall - fan replacement | 240 kV, Pre-Condition
ATCO | 9L11 (813s Little Smoky - 834s Wesley Creek) | 2021-03-15 12:00 | 2021-03-19 10:24 | N | Y | pole replacement and enforcers | Line |  | Pole replacement and enforcers | 240 kV, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 202L (58s Edson - 178s Cynthia), 178s 202N (178s Cynthia) | 2021-03-15 12:00 | 2021-03-19 18:00 | N | N | component replacements | Line, Circuit Breaker | component replacements on Str's range 373-813 and 202L178s dead ends |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 733s 702 (733s Simonette), 7L40 (733s Simonette - 813s Little Smoky) | 2021-03-15 16:01 | 2021-03-28 09:25 | N | Y | bus protection needs to be upgraded at 733s | Circuit Breaker, Line | This record is split up from 7L40 record from Feb 28 - March 29. | 7L80, 7L40, 702T, 25KV bus protection needs to be upgraded at 733s. This requires a 144KV station outage. 835s Mobile sub will be installed on 7L80 to by pass the 144KV to keep the 25KV load fed.835s mobile sub will be in service power the 25KV. Isolation points: Mar1-15: 733S 502TD, 733S 7L80D1, & 813S 7L40D3 Isolation Points Mar15-29: 733S 702A & 813S 7L40D3 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 113L (20s Ghost - 33s Spray) | 2021-03-16 07:00 | 2021-03-16 18:00 | N | N | P5 urgent repair 113L89 permanent fix crossarm and insulator | Line |  | P5 urgent repair 113L89 permanent fix crossarm and insulator | Pre-Condition, Affects Cranking Path
ALTALINK | 511s T30 (511s Crossings), 511s SVC Plus (511s Crossings) | 2021-03-16 07:00 | 2021-03-16 17:00 | N | Y | 511s1752 wiring corrections | Transformer, Shunts |  |  | 240 kV
ALTALINK | 749L (899s Edgerton - 749AL) | 2021-03-16 07:00 | 2021-03-22 18:00 | N | N | line clearance mitigation on structures #160 - 212 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2021-03-16 07:00 | 2021-03-16 17:00 | N | Y | DFR upgrade | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L85 (856s Kinosis - 977s Salt Creek) | 2021-03-16 08:00 | 2021-03-16 18:00 | N | Y | replace defective RTXP test switches | Line |  | Outage needed for isolation of 901CT & 902CT Primaries to replace Defective RTXP test switches. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 14.4TR (ENMAX 14) | 2021-03-16 08:00 | 2021-03-16 16:00 | N | N | secondary cable circulating current hazard & check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 818s 41 (818s Winefred), 818s C3 (818s Winefred) | 2021-03-16 08:30 | 2021-03-16 13:00 | N | N | breaker maintenance including 1st trip testing | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 356s 652 (356s Milo) | 2021-03-16 08:30 | 2021-03-16 13:30 | N | Y | C phase low gas, top up and investigated for the leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 186s T2 (186s Dry Creek) | 2021-03-16 08:30 | 2021-03-16 16:30 | N | N | investigate issue with tapchanger issue | Transformer |  |  | For Information Only
BCH | 5L52 (Custer - Ingledow) | 2021-03-16 09:00 | 2021-03-16 19:00 | N | Y | insulator replacement, BC maintenance does not affect the Alberta ATC | Line |  | insulator replacement | Limits ATC, 500 kV
ALTALINK | 818s 17 (818s Winefred), 818s C2 (818s Winefred) | 2021-03-16 13:00 | 2021-03-16 17:30 | N | N | breaker maintenance including 1st trip testing | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 356s 952 (356s Milo) | 2021-03-16 13:35 | 2021-03-16 17:30 | N | Y | replace breaker heaters | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 657s T1 (657s Summerside), 657s SU2401 (657s Summerside), 657s SU2404 (657s Summerside) | 2021-03-17 07:00 | 2021-03-17 17:00 | N | Y | DFR upgrade | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 138S R1 (138s Windy Flats), 138s Windy Flats 240kV Bus 1 | 2021-03-17 07:00 | 2021-03-24 18:00 | N | Y | tie-in, soak and energize new T2 | Shunts, Bus | P2041 TransAlta Windrise project. Confirmed with AltaLink. V.Chan Nov 9k, 2020. | 240kV Bus #1 outage to tie-in, soak and energize new T2 Transformer | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 771L (162s Beddington - ENMAX 47) | 2021-03-17 07:15 | 2021-03-19 17:45 | N | Y | maintenance on structures 17, 19, 22, 24 and 25 | Line |  | Scope of work includes maintenance on structures 17, 19, 22, 24 and 25 | For Information Only, Pre-Condition
ALTALINK | 631L (186s Dry Creek - 199s East Airdrie) | 2021-03-17 07:15 | 2021-03-19 17:45 | N | N | maintenance on structures 11, 15, 27 and 87 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 822L (38s East Edmonton - 133s Stelco Edmonton), 38s 822X (38s East Edmonton) | 2021-03-17 07:30 | 2021-03-17 19:00 | N | N | installation of grading capacitors to breaker 38s822X | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 133S Stelco Edmonton | 2021-03-17 07:30 | 2021-03-24 17:00 | N | N | T1 leak repair and maintenance, replace single bushing on T1 | Station |  | Customer requested outage. T1 leak repair and maintenance. Replace single bushing on T1 | For Information Only
EPCOR | V721 (Victoria), V729 (Victoria) | 2021-03-17 07:30 | 2021-03-18 17:00 | N | N | relay maintenance and breaker op checks | Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 771L (162s Beddington - ENMAX 47), 47.1TR (ENMAX 47), 47.2TR (ENMAX 47) | 2021-03-17 08:00 | 2021-03-19 17:00 | N | N | substation washing - line OOS by Altalink | Line, Transformer |  | Substation washing - 47SUB, 138kV, 47.1TR, 47B138-BT3, 47.2TR. Line OOS by Altalink | For Information Only
ALTALINK | 818s 14 (818s Winefred), 818s C1 (818s Winefred) | 2021-03-17 08:30 | 2021-03-17 13:00 | N | N | beaker maintenance including 1st trip testing | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 856s Kinosis RTU/SCADA | 2021-03-17 09:00 | 2021-03-17 16:00 | N | N | emergency replace failing batteries | Terminal Equipment |  | Replace batteries on RTU which all indicate failed. It is possible RTU will lose its program if it loses power. To reduce down time, have a copy of program preloaded on laptop. Visibility and control of the Substation will be interrupted during the process. | Affects Visibility
ATCO | 9L45 (856s Kinosis - 2049s Kettle River) | 2021-03-17 12:01 | 2021-03-18 17:00 | N | Y | replace defective RTXP test switches | Line |  | All RTXP test switches manufactured from 2001 - 2008 will be replaced. These defective test switches have been previously identified during the data collection phase of the project. Each defective test switch will have a replacement work order assigned to the protective relay asset it is associated with. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 428L (167s Ipiatik Lake - 818s Winefred) | 2021-03-17 13:00 | 2021-03-17 17:30 | N | N | breaker maintenance including 1st trip testing | Line |  | Breaker maintenance including 1st Trip testing. | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 657s T2 (657s Summerside), 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside) | 2021-03-18 07:00 | 2021-03-18 17:00 | N | Y | DFR upgrade | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 932L (74s Janet - 162s Beddington) | 2021-03-18 07:15 | 2021-03-20 17:45 | N | Y | maintenance on structures 3, 4, 6, 7, 8, and 98 | Line |  | Scope of work includes maintenance on structures 3, 4, 6, 7, 8, and 98 | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 856s 902T (856s Kinosis) | 2021-03-18 08:00 | 2021-03-19 12:43 | N | Y | RTXP test switch replacement | Transformer |  | All RTXP test switches manufactured from 2001 - 2008 will be replaced. These defective test switches have been previously identified during the data collection phase of the project. Each defective test switch will have a replacement work order assigned to the protective relay asset it is associated with. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 72s 952 (72s Leismer) | 2021-03-18 08:00 | 2021-03-18 13:00 | N | Y | breaker maintenance and PRC5 (1st trip, 1 close, 2nd trip) | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 601L (230s Wardlow - 275s Jenner), 275s T3 (275s Jenner), 230s 601 (230s Wardlow) | 2021-03-18 08:00 | 2021-03-18 18:00 | N | N | maintenance on structures 3, 4, 8 and 95, make sure trip mechanism works when Fortis switches it out for customer outage | Line, Transformer, Switch |  |  | Firm Load Loss, For Information Only
EPCOR, ALTALINK | 805s C1 (805s Jasper), 1044L (805s Jasper - 816s Petrolia) | 2021-03-20 07:00 | 2021-03-26 06:00 | N | Y | Jasper 240 kV reactor and cap bank repair | Shunts, Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2021-03-20 08:00 | 2021-03-25 16:00 | N | Y | line mitigation work | Line |  | Line Mitigation work | Creates Radial Feeds, Firm Load Loss
ALTALINK | 989L (77s Sagitawah - 310p Sundance) | 2021-03-21 09:00 | 2021-03-24 19:00 | N | Y | replace 77s31 CVTs | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | T3 (Meadowlark), 72MG16 (Garneau - Meadowlark), M723 (Meadowlark), M724 (Meadowlark) | 2021-03-22 07:00 | 2021-03-31 17:00 | N | N | TX3 CT wiring and tap-changer repair | Transformer, Line, Circuit Breaker |  | Civil work for line addition. Work being coordinated with TX3 outage at Meadowlark which has 72MG16 offloaded already | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 138s Windy Flats 138kV Bus 2, 608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm), 603L (138s Windy Flats - 243s Soderglen Wind Farm) | 2021-03-22 07:15 | 2021-03-24 18:45 | N | Y | allow stringing of slack span from new 497L | Bus, Line | P2041 | allow stringing of slack span from new 497L into substation as part of the Windrise station addition (P2041) | 240 kV, Restricts Generation
EPCOR | 72RV6 (511s Victoria - Rossdale), V723 (Victoria), V724 (Victoria) | 2021-03-22 07:30 | 2021-03-24 17:00 | N | N | relay maintenance and op checks (V723,V724) | Line, Circuit Breaker | Isolate Rv6 Node for relay maintenance and op checks (V723,V724) |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 528S Blue Trail Wind Farm | 2021-03-22 08:00 | 2021-03-24 18:00 | N | N | stringing of 497L into Windy Flats | Station
ALTALINK | 418s Ardenville | 2021-03-22 08:00 | 2021-03-24 18:00 | N | N | stringing of 497L into Windy Flats | Station
GWPCORP | 243S Soderglen Wind Farm | 2021-03-22 08:00 | 2021-03-24 18:00 | N | N | stringing of 497L into Windy Flats 138s | Station |  | stringing of 497L into Windy Flats 138s substation. Site AC will be 0MW for the duration of the outage.
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22), 22PT138-31 (ENMAX 22) | 2021-03-22 08:00 | 2021-03-22 12:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  | Spring Substation Washing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65.2TR (ENMAX 65) | 2021-03-22 09:00 | 2021-04-01 16:00 | N | Y | oil sampling transformer | Transformer |  | Online Monitoring Installation. 65.2TR Replace PRD Flag. Check Reversing Switch. Oil Sampling TC, MT | 240 kV, Contingency Requires Mitigation
ATCO | 7L70 (700s Bonnyville - 707s St.Paul) | 2021-03-22 09:00 | 2021-03-25 16:30 | N | Y | cross arm change | Line |  | Cross arm change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 795L (121s Brooks - 421s Hays) | 2021-03-22 09:00 | 2021-03-23 18:00 | N | N | maintenance on structures 10 and 20 | Line | Scope of work includes maintenance on structures 10 and 20 |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) | 2021-03-22 12:00 | 2021-03-22 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2021-03-22 12:00 | 2021-03-26 18:00 | N | N | Component Replacements | Line | Component Replacements on Str's range 373-813 and 202L178s Dead Ends |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 749L (899s Edgerton - 7LB749) | 2021-03-23 07:00 | 2021-03-24 18:00 | N | Y | line clearance mitigation on structures 421 and 422 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 778L (87s Gaetz - 217s North Red Deer) | 2021-03-23 07:15 | 2021-03-23 12:40 | N | N | maintenance on structures 8 and 51 | Line |  |  | Pre-Condition
ALTALINK | 17s 3 (17s Benalto) | 2021-03-23 08:00 | 2021-03-23 10:30 | N | Y | trip test for 17s T2 protection upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 33.1TR (ENMAX 33) | 2021-03-23 08:00 | 2021-03-23 12:00 | N | N | oil sampling transformer and check reversing switch | Transformer |  | Oil Sampling MT, TC. Check Reversing Switch | For Information Only
ALTALINK | 17s 9 (17s Benalto) | 2021-03-23 11:00 | 2021-03-23 13:30 | N | Y | trip test for 17s T2 protection upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 28.1TR (ENMAX 28), 1.80L (ENMAX 1 - ENMAX 28) | 2021-03-23 12:00 | 2021-03-23 18:00 | N | N | spring substation washing | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.2TR (ENMAX 33) | 2021-03-23 12:00 | 2021-03-23 16:00 | N | N | oil sampling transformer and check reversing switch | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 464L (87s Gaetz - 209s Timberlands) | 2021-03-23 12:45 | 2021-03-23 17:30 | N | Y | maintenance on structures 4, 8 11 and 12 | Line |  | Scope of work includes maintenance on structures 4, 8 11 and 12 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 4 (17s Benalto) | 2021-03-23 14:00 | 2021-03-23 16:30 | N | Y | trip test for 17s T2 protection upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition,Affects Cranking Path
EPCOR | T2 (Strathcona) | 2021-03-23 17:01 | 2021-08-30 06:59 | N | N | Strathcona TX2 replacement - 1007218 | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 821L (158s Vauxhall - 421s Hays) | 2021-03-24 07:15 | 2021-03-26 17:45 | N | N | maintenance on structures 7, 8 and 13. emergency repair; West Phase CT replacement (421s821W) | Line | Scope of work includes maintenance on structures 7, 8 and 13. Emergency Repair; West Phase CT replacement (421s821W) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 482S Haynes, 482s T1 (482s Haynes) | 2021-03-24 07:30 | 2021-03-24 16:30 | N | N | provide access for NGR inspection and testing | Station, Transformer |  | Switch and ground for customer. Provide access for NGR inspection and testing. | For Information Only
ALTALINK | 17s 77 (17s Benalto) | 2021-03-24 08:00 | 2021-03-24 10:30 | N | Y | trip test 17s13 required for 17s T2 protection upgrade | Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ENMAX | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2021-03-24 08:00 | 2021-03-24 12:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.1C (ENMAX 31) | 2021-03-24 08:00 | 2021-03-24 16:00 | N | N | hot spots | Shunts |  | hot spots - 31.1Cap | Pre-Condition
ALTALINK | 739L (14s Devon - 305s Acheson), 14s 739N (14s Devon) | 2021-03-24 09:00 | 2021-03-31 17:00 | N | N | urgent 14s739N breaker replacement (like for like) | Line, Circuit Breaker |  | URGENT 14s739N Breaker replacement (Like for Like) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 3L (42s Sarcee - 272s Springbank), 272s T1 (272s Springbank) | 2021-03-24 09:30 | 2021-03-24 16:30 | N | N | emergency repair, broken switch repair (272s3E) | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 17s C1 (17s Benalto), 17s 16 (17s Benalto) | 2021-03-24 11:00 | 2021-03-24 13:30 | N | Y | trip test 17s16 required for 17s T2 protection upgrade | Shunts, Circuit Breaker |  | Trip test 17s16 required for 17s T2 Protection upgrade | 240 kV, Pre-Condition
ENMAX | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2021-03-24 12:00 | 2021-03-24 18:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 138s Windy Flats 138kV Bus 1 | 2021-03-24 14:15 | 2021-04-19 08:45 | N | N | construction activity (P2041) | Bus |  |  | For Information Only
EPCOR | 816s T2 (816s Petrolia) | 2021-03-25 07:00 | 2021-03-26 17:00 | N | Y | tap changer repair | Transformer |  |  | 240 kV, For Information Only
Saskpower | SaskPower A1R | 2021-03-25 07:00 | 2021-03-26 16:00 | N | Y | high load move | Line |  |  | Limits ATC, Pre-Condition
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2021-03-25 08:00 | 2021-03-25 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2021-03-25 08:00 | 2021-03-26 17:00 | N | Y | line mitigation work | Line |  | Line Mitigation Work | Pre-Condition, Restricts Generation
ALTALINK | 237s 652 (237s Foothills) | 2021-03-25 08:30 | 2021-03-25 15:30 | N | N | investigate SF6 leak and top up | Circuit Breaker |  |  | Contingency Requires Mitigation
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-03-25 09:00 | 2021-03-25 17:00 | Y | Y | BC Hydro work | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354S Summerview | 2021-03-25 11:00 | 2021-03-25 16:00 | N | N | WindCharger software updates | Station |  |  | Restricts Generation
ALTALINK | 728L (353s Plamondon - 405s Waupisoo) | 2021-03-25 11:00 | 2021-03-25 17:30 | N | N | connect 472s 138kV power cables to 728L and close Open Point A | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23), 23.4TR (ENMAX 23) | 2021-03-25 12:00 | 2021-03-25 18:00 | N | Y | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 405s T1 (405s Waupisoo), 405s 728 (405s Waupisoo), 405s C2 (405s Waupisoo) | 2021-03-26 07:00 | 2021-03-27 08:00 | N | N | replace 138kv bus connectors, switch and transformer maintenance | Transformer, Circuit Breaker, Shunts |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge) | 2021-03-26 07:15 | 2021-03-26 14:45 | N | N | maintenance on structure 51 | Line |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2021-03-26 08:00 | 2021-03-26 16:00 | N | N | secondary cable circulating current hazard, check reversing switch | Transformer |  | 6.4TR Corrective - Secondary Cable Circulating Current Hazard. Check Reversing Switch | For Information Only
ALTALINK | 995L (62s Brazeau - 995AL tap), 995AL (68s Willesden Green - 995L tap), 995L (17s Benalto - 995AL tap) | 2021-03-26 12:00 | 2021-03-26 20:00 | N | Y | *P5 temporary fix OHSW/anchors 995L101 | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 405S Waupisoo, 796L (405s Waupisoo - 796AL tap), 405s C1 (405s Waupisoo), 405s C2 (405s Waupisoo), 633L (56s Boyle - 405s Waupisoo), 728L (353s Plamondon - 405s Waupisoo) | 2021-03-27 07:00 | 2021-03-27 20:00 | N | Y | replace 138kv bus connectors, switch maintenance, T1 maintenance | Station, Line, Shunts |  | Replace 138kv bus connectors, Switch maintenance, T1 bushing replacement, T1 maintenance, T1 Oil leak repair, LTC valve body repair and filter packs. Mobile substation required to maintain Fortis loads during outage. 242s1 maintenance, 242s T1 maintenance. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 1036L (356s Milo - 554s Travers) | 2021-03-27 07:00 | 2021-04-01 18:00 | N | Y | installation of phase raiser assemblies on structure 28 and 29 and interphase spacers on spans 27 to 30 | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 267S Killarney Lake | 2021-03-27 08:00 | 2021-04-05 11:30 | N | N | new breaker 267s 749A commissioning - Apr 21, 2021 (Install new Line PT and 899s749X Line and breaker fail protection (P1782) | Station |  |  | For Information Only, Pre-Condition
ALTALINK | 121s 1052 (121s Brooks) | 2021-03-27 08:15 | 2021-03-28 16:45 | N | N | 1052 breaker C60 cutover | Circuit Breaker | 121s 1052 (121s Brooks) (bus tie) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 405s T1 (405s Waupisoo), 728L (353s Plamondon - 405s Waupisoo), 405s Waupisoo 138 kV Bus 1, 405s C2 (405s Waupisoo) | 2021-03-27 19:00 | 2021-03-29 13:00 | N | N | replace 138kv bus connectors, switch maintenance, T1 maintenance | Transformer, Line, Bus, Shunts | 728L (353s Plamondon - 405s Waupisoo) | Replace 138kv bus connectors, Switch maintenance, T1 bushing replacement, T1 maintenance, T1 Oil leak repair, LTC valve body repair and filter packs. Mobile substation required to maintain Fortis loads during outage. P&C to uninstall temporary settings on 633L @ 56s and 796L @ 282s & enable voltage sensitive protections @ 405s. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 24.81L (ENMAX 24 - ENMAX 31), 31.84L (ENMAX 31 - ENMAX 32), 31.3TR (ENMAX 31), 31.2TR (ENMAX 31) | 2021-03-28 08:00 | 2021-03-28 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31.1C (ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31) | 2021-03-28 12:00 | 2021-03-28 18:00 | N | N | spring substation washing | Line, Shunts, Transformer |  |  | Pre-Condition
EPCOR | 816s T1 (816s Petrolia), 816s P2401 (816s Petrolia), 816s P2402 (816s Petrolia) | 2021-03-29 07:00 | 2021-04-02 17:00 | N | Y | relay maintenance breaker op-checks | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T1 (Kennedale), K721 (Kennedale), K722 (Kennedale), 72CK13 (987s Clover Bar - Kennedale) | 2021-03-29 07:00 | 2021-03-29 17:00 | N | N | 1007343-039439 - yard lighting replacement | Transformer, Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | RG725 (Rossdale), 72RG7 (Garneau - Rossdale) | 2021-03-29 07:00 | 2021-03-29 12:00 | N | N | op check on RG725 from various protection | Circuit Breaker, Line | RG725 (Rossdale), 72RG7 (Garneau - Rossdale) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s Sagitawah 138 kV West Bus, 77s T1 (77s Sagitawah), 77s 452 (77s Sagitawah), 77s 352 (77s Sagitawah) | 2021-03-29 09:00 | 2021-03-31 12:00 | N | N | strain insulator replacement at 77s | Line, Bus, Transformer, Circuit Breaker | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s Sagitawah 138 kV West Bus |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 65.2TR (ENMAX 65), 65B138-D85 (ENMAX 65), 65B138-D82 (ENMAX 65), ENMAX 65 138 kV North Bus | 2021-03-29 09:00 | 2021-03-30 16:00 | N | Y | 65PT138-Z32 replacement | Transformer, Circuit Breaker, Bus | 65.2TR (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 903L (17s Benalto - 320p Keephills), 17s 7 (17s Benalto), 17s 8 (17s Benalto), 320p 2152 (320p Keephills) | 2021-03-29 09:30 | 2021-04-08 15:45 | N | Y | protection upgrade and work on str. 66 | Line, Circuit Breaker | 903L (17s Benalto - 320p Keephills) | 903L protection upgrade at 17s and 320p. And 2nd GOI box for Lines crew working on STR 903L66 for Mar 30 only | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 728L (353s Plamondon - 405s Waupisoo), 405s 728 (405s Waupisoo) | 2021-03-29 12:00 | 2021-03-29 17:00 | N | N | remove 472s 138 kV power cables from 728L, create open point C | Line, Circuit Breaker |  | Remove 472s 138kV power cables from 728L. Create Open Point A | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | RW727 (Rossdale), 72RW3 (Rossdale - Woodcroft) | 2021-03-29 12:00 | 2021-03-29 17:00 | N | N | maintenance op checks on RW727 from various protection | Circuit Breaker, Line | RW727 (Rossdale), 72RW3 (Rossdale - Woodcroft) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 989s 703 (989s Quigley) | 2021-03-29 12:30 | 2021-03-29 15:30 | N | N | PRC 005 trip coil testing 703 | Circuit Breaker | 989s 703 (989s Quigley) | PRC 005 Trip Coil Testing 703 | Firm Load Loss
ALTALINK | 749L (648s Metiskow - 749AL tap), 749AL (267s Killarney Lake - 749L tap), 648s 749E (648s Metiskow) | 2021-03-29 18:00 | 2021-04-01 17:00 | N | N | end to end testing between 267s and 648s Metiskow (P1782) | Line, Circuit Breaker |  | End to End Testing between 267s and 648s Metiskow. Requires recloser control at 648s and 267s; 267s requires new breaker addition including line, breaker fail & bus protections; 648s requires new TPR channel to 267s and modifications to existing line relay settings. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | K722 (Kennedale), K723 (Kennedale), T2 (Kennedale) | 2021-03-30 07:00 | 2021-03-30 17:00 | N | N | 1007343-039439 yard lighting replacement | Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2021-03-30 07:00 | 2021-03-30 18:00 | N | N | urgent P5 work on structures 185A, 186, 187, 187A | Line |  |  | Pre-Condition, Affects Cranking Path
EPCOR | EPCOR Satellite Phone | 2021-03-30 08:00 | 2021-03-30 16:00 | N | N | SAT phone outage | Not In Model |  |  | For Information Only
ALTALINK | 827L (28s West Brooks - 121s Brooks), 121s 827W (121s Brooks) | 2021-03-30 08:15 | 2021-04-01 16:45 | N | N | 1152 breaker C6 cutover and CTs for 138kV B" bus protection | Line, Circuit Breaker |  | 1152 breaker C6 cutover and CTs for 138kV B" bus protection | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 989s 704 (989s Quigley) | 2021-03-30 08:30 | 2021-03-30 11:00 | N | N | trip coil testing PRC 005 | Circuit Breaker |  | PRC 005 Trip Coil testing. 704 | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 103s 252 (103s Goose Lake) | 2021-03-30 08:30 | 2021-03-30 12:29 | N | Y | investigate and top up gas | Circuit Breaker | 103s 252 (103s Goose Lake) |  | 240 kV, Pre-Condition
ALTALINK | 191s 792N (191s NW Cardiff), 792L (150s Clyde - 191s N.W. Cardiff) | 2021-03-30 09:30 | 2021-03-30 13:30 | N | N | breaker maintenance including 1st trip testing | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 989s 701 (989s Quigley) | 2021-03-30 11:30 | 2021-03-30 16:00 | N | N | trip coil testing PRC 005 | Circuit Breaker |  | PRC005 Trip Coil testing. Test and Operate | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 191s 792X (191s NW Cardiff), 792L (92s Viscount - 191s N.W. Cardiff) | 2021-03-30 13:30 | 2021-03-30 17:30 | N | N | breaker maintenance including 1st trip testing. | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CNRL | 838s 75-TR-1701 (838s Horizon Mining), 838s 75-TR-1801 (838s Horizon Mining), 75-PLH-901 (838s Horizon Mining - 849s Joslyn) | 2021-03-31 07:30 | 2021-04-09 18:00 | N | Y | 260 kV MOD, CT and CVT maintenance and bus maintenance | Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 9.1TR (ENMAX 9), 9.80L (ENMAX 9 - ENMAX 31) | 2021-03-31 08:00 | 2021-03-31 16:00 | N | N | spring substation washing and check reversing switch | Transformer, Line |  |  | For Information Only, Pre-Condition
ATCO | 829s 701T (829s Boucher Creek) | 2021-03-31 10:00 | 2021-03-31 13:00 | N | N | outage to add mid span arrestors at customers request | Transformer |  | Outage to add mid span arrestors at customers request. | For Information Only
ALTALINK | 103s 552 (103s Goose Lake) | 2021-03-31 12:30 | 2021-03-31 17:30 | N | Y | investigate and top up gas and replace thermostat | Circuit Breaker | 103s 552 (103s Goose Lake) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe) | 2021-03-31 17:00 | 2021-04-02 14:00 | N | N | forced outage | Line
CNRL | 842s 75-TR-8701 (842s Horizon Upgrading) | 2021-04-01 07:30 | 2021-04-25 18:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, Pre-Condition
CNRL | 842s 75-TR-4701 (842s Horizon Upgrading) | 2021-04-01 07:30 | 2021-04-21 18:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, Pre-Condition
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights), MH69s3 MH69-308 (MH69s3 South Ridge), MH69s5 MH69-502 (MH69s5 NE Crescent Height) | 2021-04-01 08:00 | 2021-04-01 16:00 | N | N | replace insulators | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 9 - ENMAX 43), 9PT138-Z31 (ENMAX 9), 9.3TR (ENMAX 9), 9.2TR (ENMAX 9) | 2021-04-01 08:00 | 2021-04-01 16:00 | N | N | spring substation washing | Line, Terminal Equipment, Transformer | 9.83L (ENMAX 9 - ENMAX 43), 2.81L (ENMAX 2 - ENMAX 9) | Spring Substation Washing. Check Reversing Switch | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 370s 207X (370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge) | 2021-04-02 07:00 | 2021-04-06 12:30 | N | Y | cut over new C60 and salvage old controls and alarms | Circuit Breaker, Line |  | Line outage on 207L to cut over new C60 and salvage old controls and alarms | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 790s 509C (790s Poplar Hill) | 2021-04-02 14:00 | 2021-04-24 18:00 | N | N | forced outage | Shunts |  |  | Pre-Condition
EPCOR | T3 (Rossdale) | 2021-04-02 20:00 | 2021-05-16 17:00 | N | N | install scaffolding for termination completion at Rossdale on RW3 | Transformer |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2021-04-02 20:00 | 2021-06-12 17:19 | N | N | termination completion at Rossdale on RW3 | Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | T2 (Rossdale), 72RV4 (511s Victoria - Rossdale) | 2021-04-02 20:00 | 2021-04-05 17:00 | N | N | install scaffolding for termination completion at Rossdale on RW3 | Transformer, Line
ATCO | 951s SVC (951s Thickwood) | 2021-04-02 23:28 | 2021-04-08 15:00 | N | N | forced outage | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 39.82L (ENMAX 162 Beddington - ENMAX 39), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) | 2021-04-03 08:00 | 2021-04-03 12:00 | N | N | HV SW maint SW84, SW88 | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 39.82L (ENMAX 162 Beddington - ENMAX 39), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) | 2021-04-03 12:00 | 2021-04-03 18:00 | N | N | HV SW maint SW83, SW87 | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 71s 752 (71s Lamoureux) | 2021-04-05 07:00 | 2021-04-08 17:00 | N | N | replace leaking CT's | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2021-04-05 08:00 | 2021-04-05 11:00 | N | N | realign 2.83L | Line |  | Green Line LRT - realign 2.83L down Blackfoot Trail to 15th St. Outage required to remove 2s leg jumpers | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays) | 2021-04-05 08:15 | 2021-04-08 15:45 | N | N | 1252 breaker C60 cutover, L12 A and B line protections and CTs for 138kV B" bus protection | Line | 795L (121s Brooks - 421s Hays) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 25MD240-2GSU (ENMAX 25), 2GSU-XF-001 (ENMAX 25) | 2021-04-05 09:00 | 2021-04-12 16:00 | N | Y | switching crew required | Switch, Transformer |  | SEC Outage. | 240 kV, Restricts Generation
ENMAX | 25B240-D140 (ENMAX 25), 25B240-D141 (ENMAX 25), 25MD240-3GSU (ENMAX 25), 3GSU-XF-001 (ENMAX 25) | 2021-04-05 09:00 | 2021-04-21 18:00 | N | Y | maintenance | Circuit Breaker, Switch, Transformer |  | HV SW maint SW150, SW151, MD maint-3GSU. Power factor test 25PT240-Z45, 240kV-25MCT3. Replace Switch Mech SW150, SW151. HV Breaker maintenance 25B240-D140 | 240 kV, Restricts Generation
ENMAX | 2.83L (ENMAX 2 - 2.83L tap) | 2021-04-05 11:00 | 2021-04-18 13:00 | N | N | realign 2.83L | Line | 2.83L (ENMAX 2 - 2.83L tap) | green line lrt. Realign 2.83L down Blackfoot trail to 15th ST. | For Information Only
EPCOR | 665s T1 (665s Dome) | 2021-04-06 07:00 | 2021-04-06 17:00 | N | Y | leak repair | Transformer |  |  | 240 kV, For Information Only
EPCOR | H724 (Hardisty Epcor), 72CH9 (987s Clover Bar - Hardisty) | 2021-04-06 07:00 | 2021-04-06 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | H724 Breaker Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 816s T2 (816s Petrolia) | 2021-04-06 07:00 | 2021-04-08 15:00 | N | Y | relay maintenance breaker op-checks | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 901L (63s Red Deer - 901AL tap), 901L (74s Janet - 901AL tap) | 2021-04-06 07:15 | 2021-04-06 17:45 | N | Y | inspect welds on 901L210 | Line | 901L (63s Red Deer - 901AL tap), 901L (74s Janet - 901AL tap) | Asset Management request for crew to hold GOI and escort Acuren to inspect welds on 901L210 and have welder on hand if needed. | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72MG16 (Garneau - Meadowlark) | 2021-04-06 07:30 | 2021-04-09 17:00 | N | N | decommissioning breaker fail trip/CT circuits | Line | Isolate 72MG16 Bay for decommissioning breaker fail trip/CT circuits |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s 770E (370s North Lethbridge), 770L (254s Coaldale - 370s North Lethbridge) | 2021-04-06 07:30 | 2021-04-06 12:00 | N | N | trip test 370s770E initiated by 370s207X breaker fail protection | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | E511s Victoria T1 (511s Victoria) | 2021-04-06 07:30 | 2021-04-09 17:00 | N | N | relay calibrations and op checks | Transformer | Isolate TX1 bay at Victoria S/S to preform relay calibrations and op checks |  | For Information Only
ENMAX | 36.3TR (ENMAX 36) | 2021-04-06 08:00 | 2021-04-08 16:00 | N | N | 36.3TR LTC - high oil level. 36.3TR - LTC check conservator tank oil level range - LD | Transformer |  |  | For Information Only
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2021-04-06 08:00 | 2021-04-06 09:00 | N | N | spring pothead washing | Line | 1.80L (ENMAX 1 - ENMAX 28) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2021-04-06 09:00 | 2021-04-06 10:00 | N | N | spring pothead washing | Line | 1.81L (ENMAX 1 - ENMAX 20) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2011s 701 (2011s Dawes) | 2021-04-06 09:00 | 2021-04-06 10:59 | N | N | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | For Information Only
BCH | 5L52 (Custer - Ingledow) | 2021-04-06 09:00 | 2021-04-08 17:00 | N | Y | disconnect switch inspections, BC Maintenance does not affect the Alberta ATC | Line |  | disconnect switch inspections | Limits ATC, 500 kV
ALTALINK | 749L (899s Edgerton - 749AL tap) | 2021-04-06 09:30 | 2021-04-12 09:00 | N | N | install new line PT and 899s749X line and breaker fail protection (P1782) | Line | 749L (899s Edgerton - 749AL), P1782 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 434s T1 (434s East Stony Plain) | 2021-04-06 10:00 | 2021-04-16 17:00 | N | N | replace 434s210x, 434s481E & 434s36W breakers and risers | Transformer |  | Replace 434s210x, 434s481E & 434s36W breakers and risers. T1 bushing replacement. T1 maintenance, Hot spot repairs, Leaks & Oil reclaim | For Information Only
ALTALINK | 63s 2752 (63s Red Deer) | 2021-04-06 10:00 | 2021-04-08 17:30 | N | Y | breaker maintenance and grading cap replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2021-04-06 10:00 | 2021-04-06 11:00 | N | N | spring pothead washing | Line | 9.83L (ENMAX 9 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2011s 705 (2011s Dawes) | 2021-04-06 11:00 | 2021-04-06 12:59 | N | N | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2021-04-06 11:00 | 2021-04-06 12:00 | N | N | spring pothead washing | Line | 33.84L (ENMAX 33 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 370s 175 (370s North Lethbridge), 172L (181s Chinook - 370s North Lethbridge) | 2021-04-06 12:30 | 2021-04-06 17:00 | N | Y | trip test 370s175 initiated by 370s207X breaker fail protection | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2011s 706 (2011s Dawes) | 2021-04-06 13:00 | 2021-04-06 14:59 | N | N | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | Pre-Condition
ALTALINK | 281s T1 (281s Johnson) | 2021-04-06 13:30 | 2021-04-07 17:30 | N | Y | investigate IDD alarm | Transformer |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 2011s 708 (2011s Dawes) | 2021-04-06 15:00 | 2021-04-06 16:30 | N | N | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | Pre-Condition
EPCOR | H725 (Hardisty Epcor), 72CH11 (987s Clover Bar - Hardisty) | 2021-04-07 07:00 | 2021-04-07 17:00 | N | N | doble H725 bay CT's | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 422s 700 (422s Westwood), 746s 700N (746s Sherwood Park) | 2021-04-07 07:00 | 2021-04-07 14:00 | N | N | scope of work includes maintenance on structures 30, 31 and 32 | Line, Circuit Breaker | 700L (422s Westwood - 746L), 700L (746s Sherwood Park - 746L), 746L (700L - 746AL) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2075S Newell | 2021-04-07 08:00 | 2021-04-09 17:30 | N | N | emergency outage for valve cooling pump | Station
ENMAX | 39.3TR (ENMAX 39) | 2021-04-07 08:00 | 2021-04-08 16:00 | N | N | replacement of external control wiring, check reversing switch and Oil Sampling | Transformer |  | Replacement of external control wiring. Check Reversing Switch. Oil Sampling MT, TC. | For Information Only
ALTALINK | 790L (434s Stony Plain - 790AL tap), 434s T1 (434s East Stony Plain), 434s 790 (434s Stony Plain) | 2021-04-07 08:00 | 2021-04-07 17:00 | N | N | repair sight glass on 138kV PTs | Line, Transformer, Circuit Breaker | 790L (434s Stony Plain - 790AL) | Repair sight glass on 138kV PTs. Disable 452L & UF protections to complete this work. | Creates Radial Feeds, Firm Load Loss
ATCO | 2011s 901 (2011s Dawes) | 2021-04-07 08:00 | 2021-04-07 11:00 | N | Y | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | 240 kV, Contingency Requires Mitigation
ATCO | 802s 606 (802s Michichi Creek), 6L56 (763s Hanna - 802s Michichi Creek) | 2021-04-07 08:00 | 2021-04-09 17:00 | N | N | open due to a potential clearing time issue | Circuit Breaker, Line |  |  | Over/Under Voltage, Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2021-04-07 08:00 | 2021-04-07 10:00 | N | N | spring transmission line washing | Line | 15.62L (ENMAX 15 - ENMAX 16) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2021-04-07 08:00 | 2021-04-07 16:00 | N | Y | transmission cables sheath test | Line | 833L (ENMAX 2 - ENMAX 12) |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 671L (39s Bickerdike - 58s Edson) | 2021-04-07 09:00 | 2021-04-14 12:00 | N | N | move 58s 671L Line (L4) protections and 58s671 BF protection to new control building | Line | 671L (39s Bickerdike - 58s Edson) |  | Contingency Requires Mitigation, Pre-Condition
VISIONREQ, GWPCORP, ALTALINK, STROBE, TRANSALTA | 354S Summerview, 243S Soderglen Wind Farm, 418s Ardenville, 240S McBride Lake, Transalta Wind Control Centre | 2021-04-07 09:00 | 2021-04-07 16:00 | N | N | firewall software updates | Station, SCInternal |  |  | Affects Visibility
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2021-04-07 10:00 | 2021-04-07 12:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2011s 904 (2011s Dawes) | 2021-04-07 11:01 | 2021-04-07 13:00 | N | Y | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2021-04-07 12:00 | 2021-04-07 16:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2011s 905 (2011s Dawes) | 2021-04-07 13:01 | 2021-04-07 16:00 | N | Y | PRC 005 trip coil testing | Circuit Breaker |  | PRC 005 Trip Coil testing. Test and Operate Trip coil 1 & 2 must be completed, | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2021-04-08 07:00 | 2021-04-12 17:00 | N | N | Urgent repair tasks on 472L Str 254, 259, 271, 289 and 333. | Line | 472L (213s Hughenden - 472AL) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 657s T1 (657s Summerside), 657s SUAB1 (657s Summerside), 657s SU2404 (657s Summerside), 657s SU2401 (657s Summerside) | 2021-04-08 07:00 | 2021-04-09 17:00 | N | Y | SUDS8 Repair | Transformer, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28) | 2021-04-08 08:00 | 2021-04-08 16:00 | N | Y | spring substation washing | Line, Transformer | 28.80L (42s Sarcee - ENMAX 28) | Transmission - Cables - Sheath Test - 138-28.80 Line XLPE, Check Reversing Switch | Creates Radial Feeds, Firm Load Loss
ENMAX | 15.60L (ENMAX 15 - ENMAX 21) | 2021-04-08 08:00 | 2021-04-08 12:00 | N | N | spring transmission line washing. | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2011s 901T (2011s Dawes) | 2021-04-08 08:00 | 2021-04-08 16:00 | N | Y | maintenance | Transformer |  | Testing SPR (Sudden Pressure Relay) on 901T. PRC005 Testing. Station service will be supplied by backup generation during work | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2021-04-08 08:00 | 2021-04-10 17:00 | N | N | emergency outage | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2021-04-08 08:00 | 2021-04-08 17:15 | N | N | Scope of work includes maintenance on structures 84, 89 and 95 | Line | 776L (308s Albchem Beaverhill Creek - 410s Josephburg) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead) | 2021-04-08 11:15 | 2021-04-08 16:45 | N | Y | bird hazard mitigation on 138kV bus 1 | Line | 880L (321s Al Rothbauer - 523s Bullshead) |  | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 523s C1 (523s Bullshead), 523s 33 (523s Bullshead) | 2021-04-08 11:15 | 2021-04-08 16:45 | N | N | bird hazard mitigation on 138 kV bus 1 | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2021-04-08 12:00 | 2021-04-08 16:00 | N | N | spring transmission line washing. | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 898L (37s North Calder - 92s Viscount) | 2021-04-09 07:00 | 2021-04-09 18:00 | N | N | maintenance on structure 26, 29, 37, 47 and 49 | Line | 898L (37s North Calder - 92s Viscount) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 434s Stony Plain RTU/SCADA | 2021-04-09 07:00 | 2021-04-09 17:30 | N | N | update configuration for 434s210x, 434s481E & 434s36W breakers | Terminal Equipment |  | Update config for the replacement of 434s210x, 434s481E & 434s36W breakers. Supervisory will be in local control. No ACC visibility for 15 min during update. Restoration time 30 min. RTU restored each day. | Affects Visibility
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21), 21B138-21.80 (ENMAX 21) | 2021-04-09 08:00 | 2021-04-09 16:00 | N | Y | transmission - cables - sheath test - 138-21.80 line XLPE | Line, Circuit Breaker | 21.80L (42s Sarcee - ENMAX 21) |  | For Information Only, Pre-Condition
EPCOR | T2 (Strathcona) | 2021-04-09 16:00 | 2021-04-11 17:00 | N | N | feeder breaker work | Transformer |  | Bus 2 outage request to repair buswork on S8 breaker. This is in alignment with Strathcona TX2 outage. 1000001 - S8 Feeder Repair at Strathcona | For Information Only
ALTALINK | 815L (13s Deerland - 127s Bruderheim) | 2021-04-10 07:00 | 2021-04-10 18:00 | N | N | maintenance on structure 49 and 52 | Line | 815L (13s Deerland - 127s Bruderheim) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 113L (20s Ghost - 33s Spray) | 2021-04-10 07:15 | 2021-04-15 17:45 | N | N | structure replacement for structures 165, 166, 167, 168 and maintenance on structures 6, 7, 28, 31, 35, 37, 118, 127, 128, 132, 156, 157, 158, 194, 207, 214, 221 | Line | 113L (20s Ghost - 33s Spray) | Scope of work includes replacing structures 165, 166, 167 and 168 and maintenance on structures 6, 7, 28, 31, 35, 37, 118, 127, 128, 132, 156, 157, 158, 194, 207, 214 and 221 | Pre-Condition, Affects Cranking Path
CNRL | 838s 75-TR-2701 (838s Horizon Mining), 838s 75-TR-2801 (838s Horizon Mining), 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2021-04-10 07:30 | 2021-04-19 18:00 | N | Y | 260 kV MOD, CT and CVT maintenance and bus maintenance | Transformer, Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 349s T1 (349s Stavely), 197L (349s Stavely - 928s East Stavely) | 2021-04-11 09:00 | 2021-04-11 15:00 | N | Y | urgent bird hazard mitigation on 138kV high bus and 349s197 maintenance | Transformer, Line | 197L (349s Stavely - 928s East Stavely) | urgent bird hazard mitigation on 138kV high bus & CB 349s197 Maintenance and 1st trip. | Restricts Generation
ALTALINK | 831L (121s Brooks - 831AL tap), 831L (339s Duchess - 831AL tap) | 2021-04-11 09:00 | 2021-04-11 17:45 | N | N | fire mitigation structures 9,19 | Line | 831L (121s Brooks - 831AL), 831L (339s Duchess - 831AL) | Fire Mitigation 831L Str's 9,19 | For Information Only
ALTALINK | 121s 831N (121s Brooks) | 2021-04-11 09:00 | 2021-04-11 14:45 | N | N | test trips from new protections on south bus | Circuit Breaker | 831L (121s Brooks - 831AL) |  | For Information Only, Pre-Condition
EPCOR | 557s CD2404 (557s Castle Downs), 557s T2 (557s Castle Downs) | 2021-04-12 07:00 | 2021-04-22 17:00 | N | Y | doble, breaker & switch maintenance | Circuit Breaker, Transformer | 557s CD2404 (557s Castle Downs), 557s T2 (557s Castle Downs) |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside) | 2021-04-12 07:00 | 2021-04-12 17:00 | N | Y | DFR upgrade | Line | 1057L (89s Ellerslie - 657s Summerside) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia) | 2021-04-12 07:00 | 2021-04-14 17:00 | N | Y | relay maintenance breaker op-checks | Line | 908L (89s Ellerslie - 816s Petrolia) |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 415s 21 (415s Drywood), 415s164 (415s Drywood), 415s T1 (415s Drywood), 164L (103s Goose Lake - 415s Drywood) | 2021-04-12 07:15 | 2021-04-13 01:52 | N | N | replace the T1"A" protection and add neutral CT circuit and protection | Circuit Breaker, Switch, Transformer, Line |  | Outage to replace the T1"A" protection and add Neutral CT circuit & protection. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 391s T1 (391s Balzac) | 2021-04-12 07:15 | 2021-04-16 15:45 | N | N | salvage 391s36 and replace with bus work | Transformer | SOW is to salvage 391s36 and replace with bus work. Install bird cover on all components. Install single hanging blades on bus side of 391s9. |  | For Information Only
EPCOR | E511s Victoria T2 (511s Victoria) | 2021-04-12 07:30 | 2021-04-16 17:00 | N | N | perform relay calibrations and op checks | Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.84L (ENMAX 3 - ENMAX 13) | 2021-04-12 08:00 | 2021-04-12 16:00 | N | N | power factor test 3B138-3.84-CT | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 5.6TR (ENMAX 5) | 2021-04-12 08:00 | 2021-04-15 16:00 | N | N | power factor test transformer, secondary cable tests, maintenance & gas relay testing | Transformer |  |  | For Information Only
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 33.1TR (ENMAX 33) | 2021-04-12 08:00 | 2021-04-12 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 734s 701 (734s Sturgeon) | 2021-04-12 08:00 | 2021-04-18 18:00 | N | N | forced outage | Circuit Breaker |  | forced outage | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc) | 2021-04-12 08:00 | 2021-04-14 18:00 | N | N | maintenance on Strs 1, 11, 20, 22, 34, 37, 121 and 122 | Line | 838L (14s Devon - 325s Leduc) | Maintenance on Strs 1, 11, 20, 22, 34, 37, 121 and 122 | Creates Radial Feeds, Firm Load Loss
Syncrude | UE-1 7201 (UE-1 Syncrude Plant 30-2), UE-1 7202 (UE-1 Syncrude Plant 30-2), UE-1 7203 (UE-1 Syncrude Plant 30-2), UE-1 7204 (UE-1 Syncrude Plant 30-2) | 2021-04-12 08:00 | 2021-04-26 20:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ENMAX | 25B240-D140 (ENMAX 25) | 2021-04-12 08:00 | 2021-04-12 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 510s 2052 (510s Sunnybrook), 510s 1952 (510s Sunnybrook), 510s ACF21 (510s Sunnybrook), 510s ACF22 (510s Sunnybrook) | 2021-04-12 08:00 | 2021-04-16 16:00 | N | Y | annual filter bank outage | Circuit Breaker, Shunts | Annual Filter Bank outage, AC Disconnect Maintenance and 510s2152 Maintenance WATL limit power transfer limits will limited to 700MW during this time |  | 500 kV, Pre-Condition
ALTALINK | 58s 35 (58s Edson), 58s C1 (58s Edson) | 2021-04-12 08:00 | 2021-04-12 10:00 | N | N | complete functional breaker trip test | Circuit Breaker, Shunts |  | Tie in 96/552 BF, 96/1052 BF, 96/1352 BF Trips. - Complete functional Breaker Trip Test. | Pre-Condition
ALTALINK | 368s 879 (368s Burdett), 879L (244s Bowmanton - 368s Burdett) | 2021-04-12 08:15 | 2021-04-12 16:45 | N | Y | install maintenance switch | Circuit Breaker, Line | 879L (244s Bowmanton - 368s Burdett) | Install a maintenance switch for breaker 368s879.. Deficiency work as 43m was not originally intended to be removed. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ATCO | 933s 704 (933s Tower Road), 7L97 (933s Tower Road - 7LA97) | 2021-04-12 08:30 | 2021-04-12 11:30 | N | N | trip coil testing | Circuit Breaker, Line | 7L97 (933s Tower Road - 7LA97) | PRC 005 Trip coil testing 704. 7L97 Open ended | Creates Radial Feeds, Firm Load Loss
ALTALINK | 749L (899s Edgerton - 749AL tap) | 2021-04-12 09:00 | 2021-04-13 09:00 | N | N | function test new protections including recloser | Line | 749L (899s Edgerton - 749AL) | Function test new protections including recloser | Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 217s T2 (217s North Red Deer) | 2021-04-12 09:00 | 2021-04-14 15:30 | N | N | power transformer testing and LTC overhaul | Transformer |  |  | For Information Only
ALTALINK | 71s 1352 (71s Lamoureux), 71s 1452 (71s Lamoureux), 997L (71s Lamoureux - 410s Josephburg) | 2021-04-12 09:30 | 2021-05-02 08:00 | N | Y | structure install, conductor tie in, OPGW installation (P1647) | Circuit Breaker, Line |  | Structure install, conductor tie in, OPGW installation, settings update and functional testing to 71s & 410s. Close Open Point 'A' & Open Point 'B'. Energization of 430s. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 900L (17s Benalto - 63s Red Deer) | 2021-04-12 09:30 | 2021-04-23 15:00 | N | Y | protection upgrade at 17s and 63s | Line | 900L protection upgrade at 17s and 63s, Adding 43M for 63s152, 63s252, and 17s10, Also updating 17s10 C60 and add syncronizer, Add recloser to 17s10. Removing old 17s 240kv PLC(and its manual synchronizer system), 17s10 was the last breaker on the 240kv PLC/synchronizer as well as the 240kv manual synchronizer and NOTES section of the SLD can removed after this is complete. Also Remove existing recloser from 17s1652 Breaker |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 942L (71s Lamoureux - 681s Bannerman) | 2021-04-12 09:30 | 2021-04-20 18:00 | N | Y | structure install, conductor tie in, and OPGW installation | Line |  | Structure install, conductor tie in, and OPGW installation | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 58s 202X (58s Edson), 202L (58s Edson - 178s Cynthia) | 2021-04-12 10:30 | 2021-04-12 12:30 | N | N | functional breaker trip test | Circuit Breaker, Line |  | Tie in 96/552 BF, 96/1052 BF, 96/1352 BF Trips. - Complete functional Breaker Trip Test. | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, Lethbridge | 370s 2552 (370s North Lethbridge), 370s 2352 (370s North Lethbridge), 370s 66 (370s North Lethbridge), 370s 667 (370s North Lethbridge), 370s T6 (370s North Lethbridge), 370s North Lethbridge 138kV Bus 3, 667L (146s Lethbridge MacDonald - 370s North Lethbridge) | 2021-04-12 11:00 | 2021-04-19 18:00 | N | Y | maintain and doble 370sT6 | Circuit Breaker, Transformer, Bus, Line |  | PRC 5: maintain and doble 370sT6, fix leaks, maintain 370s2352, also we need bus3 to mitigate the bird situation. | 240 kV, Contingency Requires Mitigation
ALTALINK | 121s T2 (121s Brooks) | 2021-04-12 11:15 | 2021-04-12 17:45 | N | N | remove existing CT contribution form old bus protection | Transformer |  | Outage to remove existing CT contribution form old bus protection | For Information Only
ALTALINK | 214s T2 (214s Innisfail) | 2021-04-12 11:15 | 2021-04-15 17:45 | N | N | fix leaks, maintain, doble, SFRA test Tx18422 | Transformer |  | fix leaks, maintain, doble, SFRA test Tx18422 | For Information Only
ATCO | 933s 703 (933s Tower Road), 7L165 (718s Parsons Creek - 933s Tower Road) | 2021-04-12 12:00 | 2021-04-12 15:00 | N | N | trip coil testing | Circuit Breaker, Line | 7L165 (718s Parsons Creek - 933s Tower Road) | PRC005 Trip coil testing, 703, 7L165 Open ended | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 45s 897 (45s Bretona), 897L (38s East Edmonton - 45s Bretona) | 2021-04-12 12:30 | 2021-04-12 16:30 | N | N | breaker maintenance and 1st trip tests on 45s897 | Circuit Breaker, Line | 897L (38s East Edmonton - 45s Bretona) | Breaker maintenance and 1st trip tests on 45s897. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2021-04-12 13:00 | 2021-04-12 15:00 | N | N | functional breaker trip test | Line | 890L (58s Edson - 207s Pinedale) | Tie in 96/552 BF, 96/1052 BF, 96/1352 BF Trips. - Complete functional Breaker Trip Test. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2021-04-12 15:30 | 2021-04-12 17:30 | N | N | breaker trip test | Line | 740L (39s Bickerdike - 58s Edson) | Tie in 96/552 BF, 96/1052 BF, 96/1352 BF Trips. - Complete functional Breaker Trip Test. | Over/Under Voltage, Pre-Condition
ENMAX | 25MD240-1GSU (ENMAX 25) | 2021-04-12 17:00 | 2021-05-08 18:00 | N | Y | switch maintenance, insulator washing, power factor testing | Switch |  |  | 240 kV, Restricts Generation
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2021-04-13 06:00 | 2021-04-14 18:00 | N | N | line upgrades | Line | 8L10 (330P Genesee - Fording Coal Mine) |  | For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa), 38s 215N (38s East Edmonton) | 2021-04-13 07:00 | 2021-04-13 20:00 | N | N | replace insulators on switch 38s40 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2021-04-13 07:00 | 2021-04-13 17:00 | N | Y | DFR upgrade | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 58S Edson | 2021-04-13 08:00 | 2021-04-13 12:00 | N | N | 58s 25kV West Bus - move PT2 distribution to new building, & functional trip tests to west bus 25kV breakers | Station |  |  | For Information Only, Restricts Generation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2021-04-13 08:00 | 2021-04-14 16:00 | N | N | relay, protection testing | Line |  | Relay, Protection Testing - 21RLY69-21.61L | Creates Radial Feeds, Firm Load Loss
ENMAX | 162s 138-RB92 (162s Beddington) | 2021-04-13 08:00 | 2021-04-13 16:00 | N | N | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 162B138-RB92 | Contingency Requires Mitigation
ALTALINK | 910s 701T (910s Excel) | 2021-04-13 08:00 | 2021-04-13 20:00 | N | N | electrical inspection | Transformer |  | TransCanada Electrical Outage Request for: Oyen Pump Station M36 Station Electrical Inspection (@ 910S EXCEL) | For Information Only
ALTALINK | 121s 1052 (121s Brooks) | 2021-04-13 08:15 | 2021-04-13 16:45 | N | N | 138kV bus A protection CT cutover and trip testing | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 74s C2 (74s Janet), 74s C1 (74s Janet) | 2021-04-13 08:30 | 2021-04-13 17:30 | N | N | PRC 5 maintenance and adjust 74s53 | Shunts |  |  | For Information Only
VISIONREQ | 354S Summerview | 2021-04-13 09:00 | 2021-04-13 12:00 | N | N | insulator replacement on feeder L11 | Station |  |  | Restricts Generation
ALTALINK | 898L (37s North Calder - 92s Viscount), 92s 898 (92s Viscount) | 2021-04-13 09:00 | 2021-04-13 17:00 | N | N | breaker maintenance and 1st trip tests, heater replacement, & gauge install on 92s898. | Line, Circuit Breaker | 898L (37s North Calder - 92s Viscount) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 899s 749N (899s Edgerton), 749L (899s Edgerton - 7LB749 tap) | 2021-04-13 09:00 | 2021-04-14 16:00 | N | Y | functionally trip 899s749N from new 899s749X breaker fail protection | Circuit Breaker, Line | 749L (899s Edgerton - 7LB749) |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23), 23.4TR (ENMAX 23) | 2021-04-13 12:00 | 2021-04-13 18:00 | N | Y | spring substation washing | Line, Transformer |  | Spring Substation Washing. Check Reversing Switch. Original outage date March 18th. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 58S Edson | 2021-04-13 13:30 | 2021-04-13 17:00 | N | N | 25kV East Bus - move PT2 distribution to new building, & functional trip tests to east bus 25kV breakers | Station |  |  | For Information Only
ENMAX | EGC1 Shepard | 2021-04-14 06:00 | 2021-04-16 18:00 | N | N | communication outage to upgrade control system and communication network | Unit |  |  | Affects Visibility
ALTALINK | 865L (38s East Edmonton - 216s Knightsbridge) | 2021-04-14 07:00 | 2021-04-14 20:00 | N | N | replace insulators on switch 38s42 | Line | 865L (38s East Edmonton - 216s Knightsbridge) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 267s 749A (267s Killarney Lake) | 2021-04-14 08:00 | 2021-04-21 16:00 | N | N | P1782 ISD Apr 21, 2021, new breaker commissioning | Circuit Breaker |  | new breaker 267s 749A commissioning - Apr 21, 2021 (Install new Line PT and 899s749X Line and breaker fail protection (P1782)
ALTALINK | 748L (267s Killarney Lake - 277s Hayter) | 2021-04-14 08:00 | 2021-04-14 12:00 | N | N | replace 2 - t tap connectors on 748L SAs | Line | 748L (267s Killarney Lake - 277s Hayter) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 121s 827W (121s Brooks), 827L (28s West Brooks - 121s Brooks) | 2021-04-14 08:15 | 2021-04-14 16:45 | N | N | 138kV Bus A protection CT cutover and trip testing | Circuit Breaker, Line | 827L (28s West Brooks - 121s Brooks) |  | Over/Under Voltage, Pre-Condition
ALTALINK | 199s C1 (199s East Ardrie), 199s 41 (199s East Airdrie) | 2021-04-14 08:30 | 2021-04-14 17:30 | N | N | capbank breaker maintenance | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 74s 103 (74s Janet), 74s C3 (74s Janet), 74s C4 (74s Janet) | 2021-04-14 08:30 | 2021-04-14 17:30 | N | Y | C phase wiring issues and replace cabinet heater | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-04-14 09:00 | 2021-04-14 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 162B138-RB80 (SS-162) | 2021-04-14 12:00 | 2021-04-14 16:00 | N | N | replace counter, dashpot checks | Circuit Breaker |  | 162B138-RB80 Replace Counter. Dashpot Checks | Contingency Requires Mitigation, Pre-Condition
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32) | 2021-04-14 12:00 | 2021-04-14 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition
EPCOR | 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside), 657s T2 (657s Summerside) | 2021-04-15 07:00 | 2021-04-15 17:00 | N | Y | upgrade DFR | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor) | 2021-04-15 07:00 | 2021-04-15 20:00 | N | N | replace insulators on switch 38s49 | Line | 731L (38s East Edmonton - 420s Broadmoor) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR, ATCO | 29PL6-4 (29EDD-1 Millennium - 836s Steepbank), 29EDD-1 29EDD1s1552 (29EDD-1 Millennium), 29EDD-1 29EDD1s1652 (29EDD-1 Millennium), 836s 622 (836s Steepbank), 836s 623 (836s Steepbank) | 2021-04-15 08:00 | 2021-05-01 15:00 | N | N | 72kV line 29PL6-4 outage for line A/B protection upgrades | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2021-04-15 08:00 | 2021-04-15 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 985L (74s Janet - ENMAX 25) | 2021-04-15 08:00 | 2021-04-15 18:00 | N | Y | C phase wiring issues and replace cabinet heater | Line | 985L (74s Janet - ENMAX 25) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 21.1C (ENMAX 21) | 2021-04-15 08:00 | 2021-04-16 16:00 | N | N | relay, protection testing - 21RLY138-21CAP | Shunts |  |  | Pre-Condition
ENMAX | 162B138-RB84 (SS-162) | 2021-04-15 08:00 | 2021-04-15 12:00 | N | N | replace strapping on heater blankets, dashpot checks | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
CapitalPower | 615s Halkirk RTU/SCADA | 2021-04-15 08:00 | 2021-04-15 10:00 | N | N | quarterly windows patching | Terminal Equipment |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays), 121s 795X (121s Brooks) | 2021-04-15 08:15 | 2021-04-15 16:45 | N | N | 138kV bus A protection CTs and trip testing | Line, Circuit Breaker | 795L (121s Brooks - 421s Hays) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-04-15 09:00 | 2021-04-15 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 162s 138-RB85 (162s Beddington) | 2021-04-15 12:00 | 2021-04-15 16:00 | N | N | replace strapping on heater blankets, dashpot checks | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 816s P2403 (816s Petrolia) | 2021-04-16 07:00 | 2021-04-16 17:00 | N | Y | relay maintenance relay op-checks | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 38s 761N (38s East Edmonton) | 2021-04-16 07:00 | 2021-04-16 20:00 | N | N | replace insulators on switch 38s90 | Line, Circuit Breaker | 761L (38s East Edmonton - 71s Lamoureux) |  | Pre-Condition
NAKODA | 162s 138-RB94 (162s Beddington) | 2021-04-16 08:00 | 2021-04-16 16:00 | N | N | ENMAX breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 26.83L (ENMAX 26 - ENMAX 65) | 2021-04-16 08:00 | 2021-04-16 16:00 | N | N | hot spot 26 sub SW 81 center phase hinge and replace counter | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake) | 2021-04-18 01:29 | 2021-04-19 18:00 | N | N | forced | Line
SUNCOR | 29EDD-34 Edd34Sub | 2021-04-18 08:00 | 2021-05-01 18:00 | N | N | 5 year system PM - 29PL6-45 | Station |  | 5Yr System PM 29PL6-45 | For Information Only
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13), 5B138-2.83 (ENMAX 5), 13B138-2.83 (ENMAX 13) | 2021-04-18 13:00 | 2021-04-18 16:00 | N | N | Green Line LRT. realign 2.83L down Blackfoot trail to 15th ST, re-install 2s leg jumpers | Line, Circuit Breaker | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | Green Line LRT. Realign 2.83L down Blackfoot trail to 15th ST. Outage required to re-install 2s leg jumpers | Pre-Condition
EPCOR | BR721 (Rossdale), 814s T1 (814s Bellamy) | 2021-04-19 07:00 | 2021-04-19 12:00 | N | N | maintenance op checks | Circuit Breaker, Transformer |  | Isolate BR721 for maintenance op checks from various protection | 240 kV, Pre-Condition
ALTALINK | Exshaw Extension, L300 (1020s Exshaw extension - 985s Exshaw) | 2021-04-19 07:00 | 2021-04-27 19:00 | N | N | testing and maintenance | Station, Line |  |  | For Information Only
EPCOR | 72MG16 (Garneau - Meadowlark) | 2021-04-19 07:00 | 2021-04-19 17:00 | N | N | civil work for line addition | Line |  | Civil work for line addition. Work being coordinated with TX3 outage at Meadowlark which has 72MG16 offloaded already | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 415s T2 (415s Drywood) | 2021-04-19 07:15 | 2021-04-23 09:45 | N | Y | outage to add T2 "S" protection and add neutral CT circuit | Transformer |  |  | Restricts Generation
ALTALINK | 391s T2 (391s Balzac) | 2021-04-19 07:15 | 2021-04-23 15:45 | N | N | salvage 391s34 and replace with bus work and install bird cover on all components | Transformer |  | SOW is to salvage 391s34 and replace with bus work. Install bird cover on all components. | For Information Only
ENMAX | 5.7TR (ENMAX 5) | 2021-04-19 08:00 | 2021-04-27 16:00 | N | N | CT install and bushing replacement, power factor test transformer | Transformer |  |  | For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2021-04-19 08:00 | 2021-04-22 16:00 | N | N | power factor test transformer, secondary cable tests, transformer maintenance, gas relay testing. oil sampling | Transformer |  |  | For Information Only
ATCO | 809s 704 (809s Louise Creek) | 2021-04-19 08:00 | 2021-05-14 16:27 | N | N | Louise Creek rebuild project, complete wiring for 21A and 21B relays, CT ratio changes, relay programming, commission control, alarms and status and blocking procedures for BF and Bus protections | Circuit Breaker |  | Louise Creek Rebuild project 7L43 will be tied together with 7L19 via 700D1 at 809S Louise Creek Complete wiring for 21A and 21B relays. CT ratio changes. Relay programming. Commission control, alarms and status. Blocking procedures for BF and Bus protections | For Information Only, Pre-Condition
ATCO | 790s 701T (790s Poplar Hill) | 2021-04-19 08:00 | 2021-05-03 16:00 | N | N | protection & SCADA upgrade | Transformer |  | 790S Poplar Hill Protection & SCADA Upgrade Outage on 701T | For Information Only
ENMAX | 162.1TR (162s Beddington) | 2021-04-19 08:00 | 2021-04-30 16:00 | N | Y | install and test/commission new tap changer controller | Transformer |  | Online Monitoring Installation. Install a new tap changer controller (DEV 90) and test/commission. | 240 kV, For Information Only
ALTALINK | 121s 814W (121s Brooks), 814L (28s West Brooks - 121s Brooks) | 2021-04-19 08:15 | 2021-04-19 16:45 | N | N | cut over trips from new protections on south bus | Circuit Breaker, Line | 814L (28s West Brooks - 121s Brooks) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 138s 497 (138s Windy Flats), 138s 1852 (138s Windy Flats) | 2021-04-19 08:45 | 2021-05-26 09:15 | N | N | advice on 138s497 to allow completion of construction and closing of open point Z' (P2041) | Switch, Circuit Breaker |  |  | For Information Only
ATCO | 963s 901T (963s Coyote Lake), 963s 901 (963s Coyote Lake), 963s 701 (963s Coyote Lake), 9L29 (946s Oakland - 963s Coyote Lake), 7L128 (802s Michichi Creek - 963s Coyote Lake) | 2021-04-19 09:00 | 2021-04-22 17:00 | N | Y | transformer major testing, PRC-005 trip coil testing on breakers | Transformer, Circuit Breaker, Line |  | Transformer Major testing is required on 901T. PRC 005 trip coil testing is require on 701 and 901 breakers. During switching allow for Pause time on 701 & 901 Breakers for testing and operating/trip coil testing. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 840S McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2021-04-19 09:30 | 2021-04-20 13:00 | Y | Y | replace failed thyristor (emergency outage) | Station, Line |  |  | Limits ATC, Pre-Condition
ALTALINK | 69s 913N (69s North Barrhead), 913L (69s North Barrhead - 732s Mitsue) | 2021-04-19 10:30 | 2021-04-22 17:30 | N | Y | replace grading capacitors, breaker maintenance including 1st trip testing | Circuit Breaker, Line | 913L (69s North Barrhead - 338s Cherhill) |  | 240 kV, Affects Cranking Path
ATCO | 813s SVC (813s Little Smoky) | 2021-04-19 11:00 | 2021-04-22 09:00 | N | Y | SVC maintenance and fix 703T leaks | Shunts |  | SVC Maintenance , fix 703T Leaks | Pre-Condition
ALTALINK | 149s T1 (149s Nisku) | 2021-04-19 11:00 | 2021-04-30 17:00 | N | N | T1 oil reclaim, bushing replacement, and leak repairs | Transformer |  |  | For Information Only
ALTALINK | 254s T1 (254s Coaldale) | 2021-04-19 12:00 | 2021-04-23 08:00 | N | Y | replacement of existing T1 transformer protections | Transformer |  | Replacement of existing T1 transformer protections, trip and block close check to C/S 195, and initiate 96/195 protection, trip checks to breakers 152, 252 and 752, and transfer trip initiate check to INIVEN shelf for L7. 254s443X DG will be called down for outage. | Restricts Generation
ALTALINK | 62s T3 (62s Brazeau) | 2021-04-19 12:30 | 2021-04-22 13:30 | N | Y | transformer maintenance including doble, oil leak repairs, LAs | Transformer |  |  | 240 kV, For Information Only, Pre-Condition
CNRL | 838s 75-TR-2801 (838s Horizon Mining) | 2021-04-19 18:00 | 2021-04-27 15:00 | N | Y | forced outage - transformer testing | Circuit Breaker | 838s 75-TR-1801 (838s Horizon Mining) |  | 240 kV
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2021-04-20 08:00 | 2021-04-21 17:00 | N | N | temp bypass being installed between 648s - 221s | Line |  | Hot Line Work: AML Creating Open points A and B and Energize Temp Bypass on 472L. Temp bypass being installed between 648s - 221s. Open Point A - 472L20 between Str. 472L411 and Str. 472L412 Open Point B - 472AL between Str. 472AL2 and Str. 472AL3 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 859s 702T (859s Primrose) | 2021-04-20 09:00 | 2021-04-20 18:00 | N | N | tap changer oil fill in conservator compartment | Transformer |  |  | For Information Only
AESO-SC | OATI | 2021-04-20 18:00 | 2021-04-20 19:00 | N | N | perform an inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
EPCOR | 113s T1 (113s Inland Cement) | 2021-04-21 06:00 | 2021-04-25 20:00 | N | N | relay maint & repair | Transformer |  | Relay Maint & Repair - coordinated with customer shutdown | For Information Only, Pre-Condition
EPCOR | V726 (Victoria) | 2021-04-21 07:00 | 2021-04-21 17:00 | N | N | maintenance op checks | Circuit Breaker |  | isolate V726 for maintenance op checks | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 612L (336s Fincastle - 368s Burdett), 336s 612 (336s Fincastle) | 2021-04-21 07:15 | 2021-04-24 17:45 | N | Y | maintenance on structures 87, 203, 206 and 212 | Line, Circuit Breaker | 612L (336s Fincastle - 368s Burdett) | Scope of work includes maintenance on structures 87, 203, 206 and 212 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2021-04-21 08:00 | 2021-04-22 15:00 | N | N | install 3 arresters in their switchyard | Transformer |  | customer to install 3 arresters in their switchyard | Firm Load Loss, For Information Only
CMH | MH69s1 69kV North Bus (MH69s1 Power P Switchyard), MH69s1 MH69-2 (MH69s1 Power P Switchyard), MH69s1 MH69-13 (MH69s1 Power P Switchyard), MH69s1 MH69-24 (MH69s1 Power P Switchyard), MH69s1 MH69-34 (MH69s1 Power P Switchyard) | 2021-04-21 08:00 | 2021-04-28 17:00 | N | N | rung T14/T5R north T14 segment upgrade phase 4B | Bus, Circuit Breaker |  |  | For Information Only
CMH | MH69s1 69kV North Bus (MH69s1 Power P Switchyard), 4L (MH69S-1 Power Plant - MH69S-6 Riverview), MH69s6 MH69-607 (MH69s6 Riverview), MH69s1 MH69-2 (MH69s1 Power P Switchyard), MH69s1 MH69-13 (MH69s1 Power P Switchyard), MH69s1 MH69-24 (MH69s1 Power P Switchyard), MH69s1 MH69-34 (MH69s1 Power P Switchyard) | 2021-04-21 08:00 | 2021-04-28 16:00 | N | N | MH69-1 and MH69-33 switch replacement | Bus, Line, Circuit Breaker |  | 69kV disconnect switch replacement work on the North Bus at the CMH Power Generation facility. The switches being replaced are MH69-1 and MH69-33. | Pre-Condition
Lethbridge, ALTALINK | 172L (181s Chinook - 370s North Lethbridge), 463L (181s Chinook - 463AL tap) | 2021-04-21 08:00 | 2021-04-21 16:00 | N | Y | 138 kV switch maintenance | Line | 463L (15s Fort Macleod - 181s Chinook), 172L (181s Chinook - 370s North Lethbridge) | 138 kV switch maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 429s T1 (429s Nelson Lake), 883L (288s Wolf Creek - 429s Nelson Lake) | 2021-04-21 08:00 | 2021-04-27 17:00 | N | N | replace T1 "A" and "S" transformer protection at 429s, trips circuit includes 429s1, 429s883, 429s2160X and 429s2161N | Transformer, Line |  | Replace T1 "A" and "S" transformer protection at 429s. Trips circuits will include 429s1, 429s883, 429s2160X and 429s2161N | Firm Load Loss, For Information Only
Saskpower | Sask Power SW903T | 2021-04-21 08:00 | 2021-04-21 17:00 | N | N | SW915BKR - testing | Circuit Breaker |  |  | For Information Only
ALTALINK | 339s T1 (339s Duchess), 831L (339s Duchess - 831AL tap) | 2021-04-21 08:15 | 2021-04-22 17:45 | N | N | complete project deficiencies (from 2020). T1/VR1 maintenance, doble, breaker maintenance, replace gasket (339s23W) | Transformer, Line |  | complete project deficiencies (from 2020). T1/VR1 maintenance, doble. Breaker maintenance, replace gasket (339s23W) | Creates Radial Feeds, Firm Load Loss
ALTALINK | 58s T1 (58s Edson) | 2021-04-21 09:00 | 2021-04-28 08:00 | N | N | move T1 protections to new building | Transformer |  |  | For Information Only
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2021-04-21 17:00 | 2021-04-22 08:00 | N | N | line between open Points A and B 213s stays open | Line |  | Line between Open Points A and B 213s Stays Open | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 62s 12 (62s Brazeau) | 2021-04-21 23:00 | 2021-04-22 04:00 | N | N | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 11 (62s Brazeau) | 2021-04-22 04:00 | 2021-04-22 07:00 | N | Y | maintenanace | Switch | Brushgear repair |  | 240 kV, Restricts Generation
EPCOR | V725 (Victoria) | 2021-04-22 07:00 | 2021-04-22 17:00 | N | N | relay op checks | Circuit Breaker | Isolate V725 breaker for relay op checks |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
CNRL | 842s 75-TR-5701 (842s Horizon Upgrading) | 2021-04-22 07:30 | 2021-05-01 18:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2021-04-22 08:00 | 2021-04-24 17:00 | N | N | replace 472L410 and 472AL1 | Line | Replace 472L410 and 472AL1 with 1 new structure. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32), 32PT138-Z31 (ENMAX 32) | 2021-04-22 08:00 | 2021-04-22 16:00 | N | N | lighting spire broken | Line, Transformer, Terminal Equipment |  | Lighting Spire broken - 138KV west side, south section | Creates Radial Feeds, Firm Load Loss
EPCOR | V727 (Victoria), V728 (Victoria), E511s Victoria T5 (511s Victoria), CV5 (511s Victoria - 557s Castle Downs) | 2021-04-23 07:00 | 2021-04-23 17:00 | N | Y | perform maintenance op checks on V2401,V727,V728. | Circuit Breaker, Transformer, Line |  | Isolate TX5 Bay to perform maintenance op checks on V2401,V727,V728. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 744L (235s Entwistle - 744AL tap) | 2021-04-23 07:00 | 2021-04-25 18:00 | N | N | urgent replacement of cross arms and insulators on str 123A and 125A | Line | 744L (235s Entwistle - 744AL) | Urgent replacement of cross arms/insulators on Str 123A & 125A. Replace conductor on all 3 phases between Str 123A and 125A. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 463L (181s Chinook - 463AL tap), 463AL (492s Monarch - 463L tap) | 2021-04-23 07:15 | 2021-04-23 17:45 | N | Y | maintenance on structures 28 and 31 | Line | 463L (15s Fort Macleod - 463AL tap), 463L (181s Chinook - 463AL) | Scope of work includes maintenance on Strs 28 and 31 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
CNRL | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading), 75-PLH-902 (838s Horizon Mining - 849s Joslyn) | 2021-04-23 07:30 | 2021-04-26 18:00 | N | Y | 260 kV MOD, CT and CVT maintenance and bus maintenance | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 254s T1 (254s Coaldale) | 2021-04-23 08:00 | 2021-04-24 19:00 | N | Y | replacement of existing T1 transformer protections | Transformer |  | Replacement of existing T1 transformer protections, trip and block close check to C/S 195, and initiate 96/195 protection, trip checks to breakers 152, 252 and 752, and transfer trip initiate check to INIVEN shelf for L7. 254s443X | Restricts Generation
ALTALINK | 286s T1 (286s Yasa) | 2021-04-23 08:00 | 2021-05-04 13:00 | N | N | working on NGR and cables | Transformer |  | Customer working on NGR and cables | For Information Only
ALTALINK | 415s 352 (415s Drywood) | 2021-04-23 09:45 | 2021-04-23 11:15 | N | N | verify tripping to 352 from T2 S protection | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 415s 21 (415s Drywood), 415s T1 (415s Drywood), 164L (103s Goose Lake - 415s Drywood) | 2021-04-23 11:15 | 2021-04-25 15:00 | N | N | verify tripping to 152 from T2 S protection and finish replacement the T1 A protection | Circuit Breaker, Transformer, Line |  | Outage to verify tripping to 152 from T2 "S" protection. Finish Outage to replace the T1"A" protection and add Neutral CT circuit & protection due to recall to real time event. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
CapitalPower | 1018s Shamrock RTU/SCADA | 2021-04-23 12:00 | 2021-04-23 15:00 | N | N | communication only outage | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 754L (245s Seebe - 985s Exshaw - 437s Baymag) | 2021-04-24 03:00 | 2021-04-24 07:00 | N | N | create open point on 742L for customer switch replacement | Line |  | Create open point on 742L for customer switch replacement. 754L65A will be fixed on Tues April 27 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, EPCOR | 747L (37s North Calder - 711L tap), 747L (99s North St. Albert - 711L tap), 711L (Inland Cement - 747L tap) | 2021-04-24 06:00 | 2021-04-25 20:00 | N | Y | retrofit 711L4 and breaker maint | Line | 747L (37s North Calder - 711L), 747L (99s North St. Albert - 711L), 711L (Inland Cement - 747L tap) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
Lafarge Canada | 985s T1 (985s Exshaw), 985s T2 (985s Exshaw) | 2021-04-24 07:00 | 2021-04-27 19:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 742L (985s Exshaw - 754L), 742L (985s Exshaw - 754L tap) | 2021-04-24 07:00 | 2021-04-29 08:00 | N | N | customer switch replacement, customer substation maintenance | Line |  |  | For Information Only, Pre-Condition
EPCOR | 72JW19 (805s Jasper - Woodcroft), 805s J724 (805s Jasper), W721 (Woodcroft) | 2021-04-24 07:00 | 2021-04-24 19:00 | N | N | emergency investigation/testing | Line, Circuit Breaker |  | emergency investigation/Testing of CVT, J724 CT Doble, Arrestor Doble | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 277s 2187X (277s Hayter) | 2021-04-24 07:30 | 2021-04-24 10:30 | N | Y | modifying settings and verifying trip circuit from 87/138B2 | Circuit Breaker |  | Modifying settings and verifying trip circuit from 87/138B2 | Restricts Generation
Syncrude | UE-1 7204 (UE-1 Syncrude Plant 30-2), UE-1 7205 (UE-1 Syncrude Plant 30-2), UE-1 7209 (UE-1 Syncrude Plant 30-2) | 2021-04-24 08:00 | 2021-04-25 20:00 | N | Y | maintenance | Circuit Breaker, Switch |  | Non-Significant Outage: UE-1 Subststation Following Circuit Breakers wil be operated: 1509 (UE-1 Subst.) 52-7204 (UE-1 Subst.) 52-7205 (UE-1 Subst.) Following Switches will be operated: 72-09 (UE-1 Subst.) 72-14 (UE-1 Subst.) 72-15 (UE-1 Subst.) | Restricts Generation
ALTALINK | 993s T2 (993s Abee) | 2021-04-24 08:00 | 2021-05-08 16:00 | N | N | P2050 ISD May 1, 2021. 993sT2 energized in Dec 2020 but customer will be connecting load on May 2021 | Transformer
ALTALINK | 277s 464 (277s Hayter) | 2021-04-24 10:30 | 2021-04-24 13:30 | N | Y | modifying settings and verifying trip circuit from 87/138B2 | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2021-04-24 17:00 | 2021-04-27 08:00 | N | N | line between open points A and B 213s stays open | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 50L (44s Bearspaw Plant - ENMAX 21), 21.4TR (ENMAX 21), 21.1TR (ENMAX 21), 21.2TR (ENMAX 21), 21.1C (ENMAX 21) | 2021-04-25 08:00 | 2021-04-25 16:00 | N | Y | HV SW maint SW86 | Line, Transformer, Shunts | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 50L (44s Bearspaw Plant - ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 435s T1 (435s Bassano) | 2021-04-25 08:15 | 2021-04-28 17:45 | N | N | install bird cover | Transformer |  | Install Bird Cover (TX low side, s10, s11, U/G cables) | For Information Only
EPCOR | 557s CD2401 (557s Castle Downs), 557s CD2406 (557s Castle Downs), 557s T1 (557s Castle Downs) | 2021-04-26 07:00 | 2021-04-30 17:00 | N | Y | maintenance | Circuit Breaker, Transformer | 557s T1 (557s Castle Downs), 557s CD2406 (557s Castle Downs) | TX1 Doble, TX1 Tap Changer Maintenance, CD2406 maintenance | 240 kV, Contingency Requires Mitigation
CNRL | 842s 75-TR-7701 (842s Horizon Upgrading) | 2021-04-26 07:30 | 2021-05-02 18:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 31.3TR (ENMAX 31) | 2021-04-26 08:00 | 2021-04-30 16:00 | N | N | LTC mech drive shaft seal replacement, filmax LTC oil filtration maintenance, check reversing switch, tapchanger inspection, oil sampling | Transformer |  | 31.3TR LTC Mech drive shaft seal needs to be replaced. Filmax LTC Oil Filtration Maintenance. Check Reversing Switch. Tapchanger Inspection. Oil Sampling | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2021-04-26 08:00 | 2021-04-26 10:00 | N | N | breaker trip test | Line | 202L (58s Edson - 178s Cynthia) | Complete functional Breaker Trip Test required for T1 protection move to new building | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 185s T2 (185s Bretville) | 2021-04-26 08:00 | 2021-04-26 18:00 | N | N | T2 doble & SFRA, fix hydran | Transformer |  |  | For Information Only
ENMAX | 13.3TR (ENMAX 13) | 2021-04-26 08:00 | 2021-04-30 16:00 | N | N | power factor test transformer, maintenance, gas relay testing, check reversing switch, oil sampling MT, TC | Transformer |  | Power factor test transformer, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil Sampling MT, TC. | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2021-04-26 08:00 | 2021-04-30 16:00 | N | N | ECI bushing replacements, check reversing switch | Transformer |  | ECI bushing replacements. Check Reversing Switch | For Information Only
REDDEER | 194s T1 (194s South Red Deer) | 2021-04-26 09:00 | 2021-04-28 12:00 | N | N | power transformer testing | Transformer | 194s T1 (194s South Red Deer) |  | For Information Only
ALTALINK | 415s 146E (415s Drywood), 162L (229s Glenwood - 415s Drywood) | 2021-04-26 09:15 | 2021-04-30 12:45 | N | N | replace the L2 A protection and verify tripping to 252 from T2 S protection | Circuit Breaker, Line |  | Outage to replace the L2"A" protection. Outage to verify tripping to 252 from T2 "S" protection. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 853AL (435s Bassano - 853L tap) | 2021-04-26 09:15 | 2021-04-28 17:45 | N | N | urgent repair dampers | Line |  | Urgent Repair Dampers 853AL Str's ( 2, 68, 74, 84, 100, 116, 124, 132, 136, 140) | For Information Only
ALTALINK | 305s 453 (305s Acheson), 453L (305s Acheson - 367s Harry Smith) | 2021-04-26 09:30 | 2021-04-29 15:00 | N | N | urgent replace leaking CTs off of breaker 305s453 | Circuit Breaker, Line |  | urgent replace leaking CTs off of breaker 305s453 | Pre-Condition,Affects Cranking Path
ALTALINK | 17s 11 (17s Benalto) | 2021-04-26 10:00 | 2021-04-26 12:00 | N | Y | trip test 17s11 | Circuit Breaker | Trip test 17s11 required for 900L (17s-63s Protection replacement) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2021-04-26 10:30 | 2021-04-26 12:30 | N | N | breaker trip test | Line | Complete functional Breaker 58s740X Trip Test for T1 protection move to new building |  | Pre-Condition
ALTALINK | 853L (28s West Brooks - 853AL tap), 28s 25 (28s West Brooks), 28s 28 (28s West Brooks) | 2021-04-26 11:00 | 2021-04-29 17:45 | N | N | replacement of 138kV PTs at 28s33 | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2021-04-26 12:00 | 2021-04-30 18:00 | N | Y | component replacements 1045L str's range 1-175 | Line | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | Component Replacements 1045L Str's Range 1-175 See Also 272816 909L R/B required due to proximity. | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 17s 6 (17s Benalto) | 2021-04-26 12:30 | 2021-04-26 14:30 | N | Y | trip test 17s6 | Circuit Breaker | Trip test 17s6 required for 900L (17s-63s Protection replacement) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s T5 (62s Brazeau) | 2021-04-26 13:00 | 2021-04-27 15:00 | N | Y | transformer maintenance | Transformer | Transformer maintenance including doble, oil leak repairs, LAs Schedued By: Tyler Schiltroth Requested By: MAPS North Contact #: Issue to: Jory Schell Contact #:403-318-4758 |  | 240 kV, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2021-04-26 13:00 | 2021-04-26 15:00 | N | N | breaker trip test | Line | 890L (58s Edson - 207s Pinedale) | Complete functional Breaker Trip Test required for T1 protections move to new building | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s T5 (121s Brooks) | 2021-04-26 13:15 | 2021-05-02 17:45 | N | Y | replacing 25 kV bushings | Transformer |  | Replacing T5 * 25 kV Bushings, fixing transformer leak and maintaining TC | Restricts Generation
ALTALINK | 17s 7 (17s Benalto) | 2021-04-26 15:00 | 2021-04-26 17:00 | N | Y | trip test 17s7 | Circuit Breaker | Trip test 17s7 required for 900L (17s-63s Protection replacement) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2021-04-27 06:00 | 2021-04-28 18:00 | N | N | line upgrades | Line |  |  | For Information Only
ALTALINK | 121s T5 (121s Brooks) | 2021-04-27 07:45 | 2021-04-28 16:45 | N | Y | replace 25kV PTs (PT4) | Transformer |  |  | For Information Only, Restricts Generation
Syncrude | UE-1 (D05 Syncrude - UE-1 Syncrude Plant 30-2), UE-1 7205 (UE-1 Syncrude Plant 30-2), UE-1 7206 (UE-1 Syncrude Plant 30-2), UE-1 7207 (UE-1 Syncrude Plant 30-2), UE-1 7208 (UE-1 Syncrude Plant 30-2) | 2021-04-27 08:00 | 2021-05-11 20:00 | N | N | 30-2PSWG72-1 "B" Bus PM UE-1 Substation | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 1.80L (ENMAX 1 - ENMAX 28), 28.1TR (ENMAX 28) | 2021-04-27 08:00 | 2021-04-28 18:00 | N | N | ECI bushing replacement | Line, Transformer |  | ECI bushing replacements. Bus outage required for bushing installation. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 58s C1 (58s Edson), 58s 35 (58s Edson) | 2021-04-27 08:00 | 2021-04-27 10:00 | N | N | complete breaker functional trip test | Shunts, Circuit Breaker |  | Complete functional Breaker Trip Test required for T1 protections move to new building | Pre-Condition
ALTALINK | 472L (213s Hughenden - 472AL tap), 472AL (221s Sunken Lake - 472L tap) | 2021-04-27 08:00 | 2021-04-28 17:00 | N | N | de-energize temp bypass and temp structures | Line |  | 472L (472L408-213s) - Advice: Hot Line Work AML Closing Open points A and B to De-energize Temp Bypass/ & Temp Structures Open Point A - 472L20 between Str. 472L411 and Str. 472L412 Open Point B - 472AL between Str. 472AL2 and Str. 472AL3 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial), 77s 352 (77s Sagitawah), 77s 552 (77s Sagitawah) | 2021-04-27 08:30 | 2021-04-27 17:30 | N | N | install expansion connections due to 77s15 pile jacking and stressing connections and extend VT2 risers | Line, Circuit Breaker |  | Install expansion connections due to 77s15 pile jacking and stressing connections. Extend VT2 risers | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 17s 1 (17s Benalto) | 2021-04-27 09:00 | 2021-04-27 11:00 | N | Y | trip test | Circuit Breaker |  | Trip test 17s1 required for 900L (17s-63s Protection replacement) | 240 kV, Contingency Requires Mitigation, Pre-Condition
TRANSALTA | 239S Castle River | 2021-04-27 09:00 | 2021-04-27 14:00 | N | N | accommodate the safe crossing of an underground cable | Station |  |  | Restricts Generation
ALTALINK | 17s T3 (17s Benalto) | 2021-04-27 11:30 | 2021-04-27 13:30 | N | Y | trip test 17s2852 | Transformer |  | Trip test 17s2852 required for 900L (17s-63s Protection replacement) | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 754L (245s Seebe - 985s Exshaw - 437s Baymag) | 2021-04-27 12:30 | 2021-04-27 17:30 | N | N | close open point on 742L after customer switch replacement, adjust 754L65A for proper operation | Line |  | Close open point on 742L after customer switch replacement. Adjust 754L65A for proper operation. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 710s 707 (710s Vermilion), 710s 707C (710s Vermilion) | 2021-04-27 16:30 | 2021-05-04 18:00 | N | N | urgent - environmental assessment due to proximity to nesting | Circuit Breaker, Shunts |  | birds nesting in close proximity to the Vermillion cap which has triggered the need for an environmental assessment. 710s707C will be unavailable until May 4/21. | For Information Only, Pre-Condition
AESO-SC | OATI | 2021-04-27 18:00 | 2021-04-27 19:00 | N | N | perform an inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2021-04-28 07:00 | 2021-04-29 18:00 | Y | Y | 1201L X-rays str's 11-22 | Line |  |  | 500 kV, Limits ATC, Pre-Condition, Affects Cranking Path
MONTANA | 120s 1352 (120s Picture Butte), 120s 240kV Bus 1 (120s Picture Butte), MATL (120s Picture Butte - Montana) | 2021-04-28 07:00 | 2021-04-28 18:30 | N | N | opportunity maintenance work | Circuit Breaker, Bus, Line |  | Taking advantage of 1201L outage& the following maintenance items will be completed; RTU outage as needed to complete alarm checks to ACC and timer modification as needed& station will be out, Complete M120s1352 trip coil monitor alarm, Relay PMs for site& operating lockouts& operating remote tripping to US side as required, 914L end to end checks& tripping of remote end breakers and Line Maintenance on 941L Requested Bby: Aaron Tang Issue to: James Sharun (REG)/Steve Predinchuk (K-Line) Contact #: 780 819-4987/403 836-4471 | For Information Only
ALTALINK | 526L (268s Whitecourt - 520L tap), 503L (268s Whitecourt - 323s Whitecourt Power), 268s Whitecourt 69 kV bus | 2021-04-28 07:00 | 2021-04-29 20:00 | N | N | replacing PT3 | Line, Bus |  | Replacing PT3 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 293s T2 (293s Bernese) | 2021-04-28 07:00 | 2021-04-28 18:00 | N | N | customer work - replace one of the overhead conductors between 490-SWGR-1-IS and 470-BUS-2- IS, relocate kirk-key on 490-SWGR-1-MB | Transformer |  | Customer requested isolation. Enbridge to replace one of the overhead conductors between 490-SWGR-1-IS and 470-BUS-2- IS1. Relocate kirk-key on 490-SWGR-1-MB. | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark), 805s J722 (805s Jasper) | 2021-04-28 07:00 | 2021-04-30 17:00 | N | N | metering upgrade | Line, Circuit Breaker |  | Isolate J722 and JVT06 for metering upgrade | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 671L (39s Bickerdike - 58s Edson) | 2021-04-28 07:00 | 2021-04-28 09:00 | N | N | breaker trip test | Line | 671L (39s Bickerdike - 58s Edson) | Complete functional Breaker Trip Test required for T1 protections move to new building | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
MONTANA | MATL (120s Picture Butte - Montana) | 2021-04-28 07:00 | 2021-04-29 18:00 | N | Y | aligned with 1201L outage | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2021-04-28 07:00 | 2021-04-28 18:30 | N | Y | testing and commissioning new protection for breakers 552 and 652 | Line | 190L (17s Benalto - 320p Keephills) | New C60 breaker fail trip testing on breaker 552, commissioning C60 from L12 'A' and 'B' protections, and cutting new 652 status contacts into 320p389. | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 5.8TR (ENMAX 5) | 2021-04-28 08:00 | 2021-05-10 12:00 | N | N | maintenance and testing | Transformer |  | CT Install and Bushing Replacement. Power factor test transformer. Secondary Cable Tests. 5.8TR Leak Investigate and Repair | For Information Only
ALTALINK | 271s T1 (271s Shell Jumping Pound) | 2021-04-28 08:30 | 2021-04-28 16:30 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 58s T1 (58s Edson) | 2021-04-28 08:30 | 2021-04-28 12:00 | N | N | function trips tests of 25kV breakers and function test 58s37 inside the GOI zone | Transformer |  | Complete function trips tests of 25kV breakers required for T1 protections move to new building, Also function test 58s37 inside the GOI zone | For Information Only
ATCO | 888s 919C (888s Dover), 888s 919 (888s Dover) | 2021-04-28 09:00 | 2021-04-29 16:00 | N | Y | switch replacement | Shunts, Circuit Breaker |  | RTXP TEST SWITCH RECALL (REPLACEMENT) - 87VA-27A-59A/919L @ 888S PRC-005 - TRIP COIL TESTING - BREAKER 919-C @ 888S PRC-005 - TRIP COIL TESTING - BREAKER 919-A @ 888S PRC-005 - TRIP COIL TESTING - BREAKER 919-B @ 888S PRC-005 - AUX TRIP RELAY TESTING - 94CB/919C @ 888S PRC-005 - AUX TRIP RELAY TESTING - 86CB/919C @ 888S PRC-005 - AUX TRIP RELAY TESTING - 86CA/919C @ 888S PRC-005 - AUX TRIP RELAY TESTING - 94C-1/919C @ 888S PRC-005 - AUX TRIP RELAY TESTING - 94CA/919C @ 888S PRC-005 - AUX TRIP RELAY TESTING - 94A-2/919C @ 888S PRC-005 - AUX TRIP RELAY TESTING - 94A-1/919C @ 888S | 240 kV, Pre-Condition
ATCO | 882s 701T (882s Triangle) | 2021-04-28 10:00 | 2021-04-28 16:00 | N | N | replace 500PT1 | Transformer |  | Bus Outage to Replace 500PT1 at 882S Triangle. Customer load transferred to 787S High Prairie and is coordinated with Planned Major customer Maintenance. Station Service will beunavailable. Crew to Monitor DC Battery Voltage during outage duration. | For Information Only
REDDEER | 194s T2 (194s South Red Deer) | 2021-04-28 12:00 | 2021-04-30 15:30 | N | N | power transformer testing | Transformer | 194s T2 (194s South Red Deer) |  | For Information Only
MONTANA, ENBRIDGE | 120s 240kV Bus 1 (120s Picture Butte), 120s MATL PST (120s Picture Butte), 120s C2 (120s Picture Butte), 120s C1 (120s Picture Butte) | 2021-04-29 07:00 | 2021-04-29 18:30 | N | Y | RTU outage, station will be out, complete M120s1352 trip coil monitor alarm, bus relay tripping to breakers in 120s | Bus, Transformer, Shunts |  | Taking advantage of 1201L outage& the following maintenance items will be completed; RTU outage as needed to complete alarm checks to ACC and timer modification as needed& station will be out, Complete M120s1352 trip coil monitor alarm, Relay PMs for site& operating lockouts& bus relay tripping to breakers in 120s. Requested Bby: Aaron Tang Issue to: James Sharun (REG) Contact #: 780 819-4987 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 34B69-21.61 (ENMAX 34) | 2021-04-29 08:00 | 2021-04-30 16:00 | N | N | relay, protection testing - 34RLY69-21.61L | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 135s T1 (135s Conrad) | 2021-04-29 08:30 | 2021-04-29 17:30 | N | N | change CT wiring | Transformer |  |  | For Information Only
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2021-04-29 09:00 | 2021-04-29 12:00 | N | N | to connect 471s and MR1 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 179s T1 (179s Gleichen) | 2021-04-29 12:05 | 2021-05-17 10:00 | N | N | install bird mitigation, crew to replace bushings | Transformer |  | 179s whole station outage required to replace 25kv switches 179s7,179s10,179s21,179s27 and 179s3. Install of new wood cross members as required. Bird mitigation install on new equipment. AML crew to replace bushings on transformer Apr 29- May 2 2021. | For Information Only
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2021-04-30 15:30 | 2021-05-02 17:00 | N | N | structure replacement (forced outage) | Line
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725AL tap), 725AL (618s Riverbend - 725L tap), 725L (111s Coalbanks - 725AL tap) | 2021-05-01 07:15 | 2021-05-02 17:45 | N | Y | urgent conductor repair between structures 348 and 349 and 138kV switch maintenance for CofL | Line |  | Urgent repairing conductor between structures 348 and 349, deemed to be high priority and at risk of failure if not done in the immediate future. 2nd Scope 138kv Switch maintenance for CofL, coordinated with this urgent outage. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 54s 45 (54s Fort Saskatchewan), 54s C1 (54s Fort Saskatchewan) | 2021-05-01 08:00 | 2021-05-01 19:00 | N | N | isolation on cap bank for urgent 54sT1 replacement | Circuit Breaker, Shunts |  | To facilitate the urgent replacement of 54sT1 the following outage will be required. | Pre-Condition
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2021-05-01 08:00 | 2021-05-01 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2021-05-01 08:00 | 2021-05-03 16:00 | N | Y | WCRR DB2 change - 1110 101 ST SW - anchor modification | Line | 7.82L (42s Sarcee - ENMAX 7) | WCRR DB2 CHANGE - 1110 101 ST SW - ANCHOR MODIFICATION | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 271s T2 (271s Shell Jumping Pound) | 2021-05-01 10:00 | 2021-05-06 17:00 | N | N | maintenance, doble, fix leaks and metering upgrade | Transformer |  |  | For Information Only
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 33.2TR (ENMAX 33), 43B138-33.84 (ENMAX 43) | 2021-05-02 08:00 | 2021-05-02 14:00 | N | N | spring substation washing, SW85 maintenance at 33 sub | Line, Transformer, Circuit Breaker |  | Spring Substation Washing. SW 85 at 33 sub - Stiff to operate - need to maintain | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 808s 701T (808s Procter & Gamble) | 2021-05-02 08:00 | 2021-05-03 17:00 | N | N | maintenance | Transformer |  | 701T main. Transfer station service as required Confirm customer outage can be extended to May 3 17:00 | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 33.1TR (ENMAX 33), 41B138-33.83 (ENMAX 41) | 2021-05-02 14:00 | 2021-05-02 18:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s T4 (987s Clover Bar), 987s T2 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s CC721 (987s Clover Bar) | 2021-05-03 07:00 | 2021-05-07 17:00 | N | Y | TX2 Doble, TX2 Zone CVT Doble, C2405 maintenance | Transformer, Circuit Breaker | 987s T4 (987s Clover Bar), 987sC2405 (987s Clover Bar) | TX2 Doble, TX2 Zone CVT Doble, C2405 maintenance, CDS1/CDS31/CDS33/CDS34/CDS39 maintenance | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2021-05-03 07:15 | 2021-05-05 17:45 | N | N | structure replacement and maintenance | Line | 113L (20s Ghost - 33s Spray) | Scope of work includes replacing structures 165, 166, 167 and 168 and maintenance on structures 6, 7, 28, 31, 35, 37, 118, 127, 128, 132, 156, 157, 158, 194, 207, 214 and 221 | Pre-Condition, Affects Cranking Path
ALTALINK | 511s Crossings ACF 1 Bus, 511s 5352 (511s Crossings), 511s 5252 (511s Crossings), 511s ACF12 (511s Crossings), 511s ACF13 (511s Crossings), 511s ACF11 (511s Crossings), 511s SVC Plus (511s Crossings) | 2021-05-03 07:30 | 2021-05-06 16:30 | N | Y | protection wiring changes, annual filter bank outage, AC disconnect maintenance | Bus, Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ATCO | 9L20 (755s Cordel - 766s Nevis), 755s 901 (755s Cordel), 755s 906 (755s Cordel) | 2021-05-03 08:00 | 2021-05-18 10:00 | N | Y | protection upgrade at 9L20, replace 901CT at 755s Cordel | Line, Circuit Breaker |  | Protection upgrade to 9L20, replace 901CT at 755s Cordel. 9L20 Channel C TP Fail 9L20 Channel B TP Fail 755s 9L20 Protection relay | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 28.2TR (ENMAX 28) | 2021-05-03 08:00 | 2021-05-07 16:00 | N | N | ECI bushing replacements | Transformer |  |  | For Information Only
CMH | T14 (MH69s-1 Power Plant Switchyard) | 2021-05-03 08:00 | 2021-05-08 16:00 | N | Y | rung T14/T5R north T14 segment upgrade phase 4B.1 | Transformer |  |  | Pre-Condition, Restricts Generation
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2021-05-03 08:00 | 2021-05-06 16:00 | N | N | air break function test and maintanance | Line |  | Air break function test and maintance | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 25B240-D131 (ENMAX 25) | 2021-05-03 08:00 | 2021-05-03 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 25B240-D131. | 240 kV, Pre-Condition
ENMAX | 47.1TR (ENMAX 47) | 2021-05-03 08:00 | 2021-05-06 16:00 | N | N | relay, protection testing - 47RLY138-47.1TR, SEL-387E, T60 | Transformer |  |  | For Information Only
ENMAX | 11.3TR (ENMAX 11) | 2021-05-03 08:00 | 2021-05-04 16:00 | N | N | tapchanger inspection, rerun CT ground wire, check reversing switch | Transformer |  | Tapchanger inspection. 11.3TR CT Ground Wire To Be Rerun. Check Reversing Switch | For Information Only
ENMAX | 162.2TR (162s Beddington) | 2021-05-03 08:00 | 2021-05-14 16:00 | N | Y | online monitoring installation | Transformer | Online Monitoring Installation. Install a new tap changer controller (DEV 90) and test/commission. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 32.1TR (ENMAX 32) | 2021-05-03 08:00 | 2021-05-14 16:00 | N | N | testing and maintenance, check reversing switch | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch. | For Information Only
ATCO, ALTALINK | 9L961 (13s Deerland - 825s Whitefish Lake) | 2021-05-03 09:00 | 2021-05-05 16:30 | N | Y | replace 13s50 (CVT10) JB | Line | 9L961 (13s Deerland - 825s Whitefish Lake) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
REDDEER | 247s T1 (247s Piper Creek) | 2021-05-03 09:00 | 2021-05-05 12:00 | N | N | power transformer testing | Transformer |  |  | For Information Only
ALTALINK | 763L (158s Vauxhall - 763AL tap) | 2021-05-03 09:00 | 2021-05-04 18:00 | N | N | components 763L structures range 315-395 | Line | 763L (158s Vauxhall - 763AL) | Components 763L Str's Range 315-395 | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ATCO | 801s 907 (801s Anderson) | 2021-05-03 09:00 | 2021-05-06 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | 907 Breaker Maintenance | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek), 63s 452 (63s Red Deer), 63s 552 (63s Red Deer) | 2021-05-03 10:00 | 2021-05-06 15:45 | N | Y | 63s1083 switch replacement | Line, Circuit Breaker |  | replacement of existing switch 63s1083 like for like | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 869s 701T (869s Seal Lake) | 2021-05-03 10:30 | 2021-05-06 16:00 | N | N | 701 maintenance, install bird mitigation material on portion of 25 kV bus | Transformer |  | Complete 701 Maintenance, 701T Major Testing and Install Missing Bird Mitigation Material on portion of 25kV bus | For Information Only
ATCO | 7L64 (779s Chinchaga River - 789s Keg River) | 2021-05-03 12:00 | 2021-06-04 12:00 | N | Y | changing crossarms | Line |  | Changing Crossarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper), 310p 1652 (310p Sundance), 310p 1752 (310p Sundance) | 2021-05-03 12:00 | 2021-05-07 18:00 | N | Y | component replacements 1045L str's range 1-175 | Line, Circuit Breaker | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | Component Replacements 1045L Str's Range 1-175 See Also 272818 909L R/B required due to proximity. | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 283s 31 (283s Violet Grove), 283s C1 (283s Violet Grove) | 2021-05-03 13:00 | 2021-05-03 16:30 | N | N | install a temporary digital disturbance recorder | Circuit Breaker, Shunts |  | Install a temporary Digital Disturbance recorder. Techs will require ACC to deenergize and then re-energize capbank breaker 283s31. Analyze the point-on-wave waveform from the breaker controller and troubleshoot the controller issue. | For Information Only, Pre-Condition
ATCO | 810s 702T (810s Dome Cutbank) | 2021-05-03 13:00 | 2021-05-08 15:00 | N | N | transformer maintenance | Transformer |  | Change 25KV bushings, transformer main. Leak repairs 702TCS main will be done as well. Move GOI point from 702TCS to J1 while main is being done. | For Information Only
ATCO | 859s 701 (859s Primrose), 859s 704 (859s Primrose), 859s 701T (859s Primrose) | 2021-05-04 04:30 | 2021-05-11 18:00 | N | Y | transformer maintenance test and breaker PRC-005 test | Circuit Breaker, Transformer |  |  | Restricts Generation
ALTALINK | 801L (294s Brazeau Outlet Works - 358s Amoco Brazeau), 801AL (445s Elk River - 801L tap) | 2021-05-04 07:00 | 2021-05-07 18:00 | N | Y | structure maintenance | Line | 801L (358s Amoco Brazeau - 801AL), 801AL (445s Elk River - 801L) | Maintenance structure 310, 312, and 314. | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 445s T1 (445s Elk River), 445s T2 (445s Elk River), 445S Elk River | 2021-05-04 07:00 | 2021-05-07 18:00 | N | N | replace switches, protection setting & configuration changes, breaker maintenance | Transformer, Station |  |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28) | 2021-05-04 08:00 | 2021-05-05 18:00 | N | Y | ECI bushing replacements | Line, Transformer |  | ECI bushing replacements. Bus outage required to change bushings | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 25B240-D132 (ENMAX 25) | 2021-05-04 08:00 | 2021-05-04 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 25B240-D132. Breaker OOS Sign on to SEC LOTO | 240 kV, Pre-Condition
ALTALINK | 17s C1 (17s Benalto) | 2021-05-04 09:30 | 2021-05-06 14:30 | N | Y | 17s16 move control, indication, various alarms | Shunts |  |  | 240 kV, Pre-Condition
ATCO | 9L09 (849s Joslyn Creek - 888s Dover), 888s 904 (888s Dover), 888s 905 (888s Dover) | 2021-05-04 09:30 | 2021-05-07 16:15 | N | Y | switch replacements 9L09. breaker maintenance 904, 905, PRC005 work | Line, Circuit Breaker |  | RTXP Switch Replacements 9L09. Breaker Maintenance 904, 905, PRC005 work | 240 kV, For Information Only
ALTALINK | 420s 731 (420s Broadmoor), 731L (420s Broadmoor - 731L tap) | 2021-05-04 10:00 | 2021-05-04 15:30 | N | N | breaker maintenance including 1st trip testing | Circuit Breaker, Line | 731L (420s Broadmoor - 731L) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 790s 509C (790s Poplar Hill) | 2021-05-04 13:00 | 2021-05-17 16:00 | N | N | upgrade protection and alarms on 509 breaker | Shunts |  | 509C OOS to upgrade Protection and Alarms on 509 Breaker | For Information Only, Pre-Condition
ATCO | 790s 702T (790s Poplar Hill) | 2021-05-04 13:00 | 2021-05-17 13:00 | N | N | replace 2K panel with new 7T2 panel and upgrade protection | Transformer |  | Replace 2K panel with new 7T2 panel. Upgrade 702T protection | For Information Only
ALTALINK | 763L (28s West Brooks - 763AL tap) | 2021-05-05 07:00 | 2021-05-07 18:00 | N | N | components 763L str's range 1-257 | Line | 763L (28s West Brooks - 763AL) |  | For Information Only
ALTALINK | 202L (61s Lodgepole - 62s Brazeau), 61s T2 (61s Lodgepole) | 2021-05-05 07:00 | 2021-05-11 17:00 | N | Y | replacing 61s9, 61s10 & 61s11 | Line, Transformer | 202L (61s Lodgepole - 62s Brazeau) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
BSC | BSC1 Brooks Solar | 2021-05-05 07:30 | 2021-05-05 10:30 | N | N | AltaLink work | Unit
ALTALINK | 132s 44 (132s Ware Junction) | 2021-05-05 07:45 | 2021-05-05 17:45 | N | Y | breaker trouble repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 631L (186s Dry Creek - 199s East Airdrie) | 2021-05-05 08:00 | 2021-05-05 18:00 | N | N | open as part of 186s and 199s MPLS upgrades | Line | 631L (186s Dry Creek - 199s East Airdrie) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2021-05-05 08:00 | 2021-05-06 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2021-05-05 09:00 | 2021-05-11 12:00 | N | N | move 58s 740L line (L3) protections to new control building | Line | 740L (39s Bickerdike - 58s Edson) |  | Over/Under Voltage, Pre-Condition
REDDEER | 247s T2 (247s Piper Creek) | 2021-05-05 12:00 | 2021-05-06 15:30 | N | N | power transformer testing | Transformer |  |  | For Information Only
ALTALINK | 370s T1 (370s North Lethbridge) | 2021-05-06 07:00 | 2021-05-06 17:30 | N | N | T1 outage to facilitate RTU splitting and testing | Transformer |  |  | For Information Only
ALTALINK | 13s T2 (13s Deerland), 808L (13s Deerland - 808AL tap), 815L (13s Deerland - 127s Bruderheim) | 2021-05-06 07:00 | 2021-05-06 17:00 | N | Y | maintenance | Transformer, Line |  | Replace 13s JBDC3 with new junction box. DC from the JB supplies 13s101, 13s452, 13s152, 13s552, 13s808N and 13s815W. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 132s 55 (132s Ware Junction) | 2021-05-06 07:45 | 2021-05-06 15:45 | N | Y | replace W P heater | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 286s T2 (286s Yasa) | 2021-05-06 08:00 | 2021-05-17 13:00 | N | N | cable and NGR work by customer | Transformer |  |  | For Information Only
SUNCOR | 635PT-1039 (635EDD-1001) | 2021-05-06 08:00 | 2021-05-14 17:00 | N | N | 144kV Central Sub 635EDD-1001 & 635PT-1039 oil leak repairs | Transformer |  | 144kV Central Sub 635EDD-1001 Dia 2 Downstream 13.8kV Equipment Outage & 635PT-1039 Oil Leak Repairs | For Information Only
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 1055L (629s Argyll Transfer - 816s Petrolia) | 2021-05-07 07:00 | 2021-05-10 17:00 | N | Y | line maintenance | Line | 1055L (629s Argyll Transfer - 816s Petrolia) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 412L (396s Pincher Creek - 632s Russell) | 2021-05-07 07:15 | 2021-05-07 17:45 | N | Y | urgent structure repair | Line |  | Scope of work includes urgent repair on structures 16 and 34 to prevent line failure and unplanned outage. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 864L (397s Benbow - 551s Chevron Kaybob), 864AL (346s Kaybob - 864L tap), 864BL (355s Chevron Knight - 864L tap) | 2021-05-07 08:00 | 2021-05-11 18:00 | N | N | maintenance at all 3 sites (346s/355s/551s) | Line | 864L (397s Benbow - 551s Chevron Kaybob) |  | For Information Only
ENMAX, ALTALINK | 23.4TR (ENMAX 23), 23.80L (74s Janet - ENMAX 23) | 2021-05-07 08:00 | 2021-05-07 18:00 | N | Y | maintenance on switches | Transformer, Line | 23.80L (74s Janet - ENMAX 23) | SW 84 at 23 sub Hot spot - South phase blade/jaw. SW 88 - 23 sub - west phase - sw to riser - line side connection | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 205S Castle Rock Ridge | 2021-05-07 09:00 | 2021-05-07 11:00 | N | N | RTAC data outage for the Riverview wind farm | Station |  |  | Pre-Condition
ALTALINK | 271s T1 (271s Shell Jumping Pound) | 2021-05-07 10:00 | 2021-05-12 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO | 888s 905 (888s Dover), 888s 906 (888s Dover), 9L74 (888s Dover - 960s Birchwood Creek) | 2021-05-07 16:20 | 2021-05-09 16:15 | N | Y | switches replacement, breaker maintenance 906 and PRC005 work | Circuit Breaker, Line |  | RTXP Switch Replacements 9L74. Breaker Maintenance 906, PRC005 work | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Affects Cranking Path
ALTALINK | 790L (432s Carvel - 790AL tap) | 2021-05-08 07:00 | 2021-05-08 18:00 | N | N | replace structure 13 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725BL tap), 725L (15s Fort MacLeod - 725BL tap), 725BL (240s McBride Lake - 725L tap), 674s 725W (674s Lethbridge Bowron) | 2021-05-08 07:15 | 2021-05-08 17:45 | N | Y | urgent repairing on structure 228, damaged insulators and crossarm deemed high risk of starting fire | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 275s T1 (275s Jenner) | 2021-05-08 08:15 | 2021-05-25 15:31 | N | Y | install new bus paralleling reactor for dual secondaries and removal of AMI feed for Bus # 4 | Transformer |  | Isolation of T1 Tx 18457 to install new bus paralleling reactor for dual secondaries Removal of AMI feed for Bus # 4 | 240 kV, For Information Only
ALTALINK | 790L (434s Stony Plain - 790AL tap) | 2021-05-09 07:00 | 2021-05-11 15:30 | N | N | maintenance on structures 67, 68, 69, 84, 90, 96, 97, 103, 113 and 124 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge) | 2021-05-09 07:00 | 2021-05-11 12:30 | N | N | RTU splitting and testing | Transformer |  | T4 Outage to facilitate RTU splitting and testing | For Information Only
SUNCOR | 29PT-100 (29EDD-18) | 2021-05-09 08:00 | 2021-05-12 18:00 | N | N | testing of high voltage & low voltage distribution equipment | Transformer |  |  | For Information Only
Syncrude | UE-1 7204 (UE-1 Syncrude Plant 30-2), UE-1 7205 (UE-1 Syncrude Plant 30-2) | 2021-05-09 08:00 | 2021-05-16 20:00 | N | Y | maintenance | Circuit Breaker |  |  | For Information Only, Pre-Condition, Restricts Generation
ATCO | 888s 905 (888s Dover) | 2021-05-09 16:15 | 2021-05-14 16:00 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | K722 (Kennedale), K723 (Kennedale), T2 (Kennedale) | 2021-05-10 07:00 | 2021-05-11 17:00 | N | N | repair KAB2 | Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s C2402 (987s Clover Bar) | 2021-05-10 07:00 | 2021-05-14 17:00 | N | Y | maintenance and doble | Circuit Breaker | 987s C2402 (987s Clover Bar) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | T1 (Meadowlark) | 2021-05-10 07:00 | 2021-05-10 17:00 | N | N | tap changer maintenance | Transformer |  |  | For Information Only
EPCOR | 330p 802 (330p Genesee), 330P SST1 (330P Genesee) | 2021-05-10 07:00 | 2021-05-14 17:00 | N | N | 802 bay doble and breaker and relay maintenance | Circuit Breaker, Transformer |  | 802 Bay Doble and Breaker Maintenance and Relay Maintenance | For Information Only
ALTALINK | 511s Crossings ACF 2 Bus, 511s 5052 (511s Crossings), 511s 4952 (511s Crossings), 511s ACF21 (511s Crossings), 511s ACF22 (511s Crossings) | 2021-05-10 07:30 | 2021-05-14 16:30 | N | Y | protection wiring changes, annual filter bank outage, AC disconnect and grounding switch Maintenance, exchange 511s77 K3 relay | Bus, Circuit Breaker, Shunts |  |  | 240 kV, For Information Only, Pre-Condition
ALTALINK, Lethbridge | 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2021-05-10 08:00 | 2021-05-11 15:30 | N | Y | air break function test and maintance | Line | 824L (593s Lethbridge Lakeview - 618s Riverbend) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
SUNCOR | 29EDD-71 144kV Bus 29PP-47 | 2021-05-10 08:00 | 2021-05-16 18:00 | N | N | 5 year maintenance on 29PP-47 and 29PT-576 | Bus |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 39.2TR (ENMAX 39) | 2021-05-10 08:00 | 2021-05-11 16:00 | N | N | tapchanger inspection. | Transformer |  |  | For Information Only
ENMAX | 25B240-D134 (ENMAX 25) | 2021-05-10 08:00 | 2021-05-10 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 25B240-D134 | 240 kV, Contingency Requires Mitigation
ENMAX | 26.1TR (ENMAX 26) | 2021-05-10 08:00 | 2021-05-14 16:00 | N | N | maintenance and testing | Transformer |  | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil Sampling MT, TC. Check reversing switch. Secondary Cable Circulating Current Hazard | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2021-05-10 08:00 | 2021-05-14 16:00 | N | N | ECI bushing replacements | Transformer |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2021-05-10 08:00 | 2021-05-14 16:00 | N | N | pole relocate | Line | 31.84L (ENMAX 31 - ENMAX 32) |  | Pre-Condition
ALTALINK | 74s Janet 240kV Bus 2, 74s T2 (74s Janet), 929L (74S Janet - 287s Hazelwood), 74s C3 (74s Janet), 74s C4 (74s Janet) | 2021-05-10 08:15 | 2021-05-10 13:45 | N | Y | creating open point 'A' in 240kV B2 bus | Bus, Transformer, Line, Shunts | 929L (74S Janet - 287s Hazelwood), 74s T2 (74s Janet) |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 763L (28s West Brooks - 763AL tap) | 2021-05-10 09:00 | 2021-05-14 18:00 | N | N | components 763L str's range 1-257 | Line | 763L (28s West Brooks - 763AL) |  | For Information Only
ATCO | 768s 701T (768s Rowley) | 2021-05-10 09:00 | 2021-05-12 17:00 | N | N | transformer maintenance | Transformer |  | 701T Transformer maintenance | For Information Only
ATCO | 939s 903T (939s Livock), 9L10 (876s Brintnell - 939s Livock) | 2021-05-10 11:00 | 2021-05-11 14:00 | N | Y | replace risers to limit the tension on the porcelain switch stacks | Transformer, Line |  | Foundation heaving has created a problem with the Flexible bus connected to 900D1 and 9L10D1. GOI is required to replace risers to limit the tension on the porcelain switch stacks. | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 827s 703T (827s Cranberry Lake), 827s SVC (827s Cranberry Lake) | 2021-05-10 11:00 | 2021-05-13 17:00 | N | Y | maintenance on 703T, 401 and SVC | Transformer, Shunts |  | 703T, 401, SVC main | Pre-Condition
ALTALINK | 929L (74S Janet - 287s Hazelwood), 74s 252 (74s Janet), 74s 352 (74s Janet) | 2021-05-10 12:00 | 2021-05-20 14:00 | N | Y | replace 138kV switches 3N and 3X | Line, Circuit Breaker | 929L (74S Janet - 287s Hazelwood) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2021-05-10 12:00 | 2021-05-14 18:00 | N | Y | component replacements 1045L Str's range 1-175 | Line | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | component replacements 1045L Str's range 1-175 See Also 272820 909L R/B required due to proximity. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 809s 707 (809s Louise Creek), 7L56 (738s Virginia Hills - 809s Louise Creek) | 2021-05-10 12:00 | 2021-05-10 16:00 | N | N | move the panel in the control building | Circuit Breaker, Line |  | Taking temporary outage 707/7L56 to move the panel in the control building. Should only be a 30 minute outage. We will block the panel, move it, and unblock it. | Pre-Condition
ALTALINK | 320p 767N (320p Keephills), 767L (320p Keephills - 767AL tap) | 2021-05-10 12:30 | 2021-05-21 13:00 | N | N | replacing 1052 breaker control and breaker fail relays with new C60 module | Circuit Breaker, Line |  |  | For Information Only, Affects Cranking Path
ALTALINK | 447s T1 (447s Enchant) | 2021-05-10 14:30 | 2021-05-16 17:30 | N | N | bushing replacement, hot spot repairs (s4, s5), breaker maintenance (s322X) and remove U/G cable (T1-VT1) | Transformer |  |  | For Information Only
EPCOR | T2 (Meadowlark) | 2021-05-11 07:00 | 2021-05-11 17:00 | N | N | tap changer maintenance | Transformer |  |  | For Information Only
ALTALINK | 54s T1 (54s Fort Saskatchewan), 54s T3 (54s Fort Saskatchewan) | 2021-05-11 07:30 | 2021-05-15 16:30 | N | N | urgent replacement 54s48, 54s25, repair 54s26, 54s3, 54s42, 54s8, install bird cover on T1 | Transformer | urgent replacement 54s48, 54s25, post and strain insulators. Repair 54s26, 54s3, 54s42, 54s8. Install bird cover on T1, bus tie and any elements requiring full bus outage. 81UF relay will have to be disabled to facilitate the outage. |  | For Information Only
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2021-05-11 08:00 | 2021-05-11 18:00 | N | N | 25 kV riser replacement and installation of bird cover-ups | Transformer | 262s T2 (262s Rocky Mountain House) |  | For Information Only
ENMAX | 11B138-BT5 (ENMAX 11) | 2021-05-11 08:00 | 2021-05-11 16:00 | N | N | current sensor - back up tank heater circuit | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 25B240-D135 (ENMAX 25) | 2021-05-11 08:00 | 2021-05-11 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2021-05-11 08:00 | 2021-05-11 16:00 | N | N | pole damage (emergency repair) | Line
ATCO, ALTALINK | 9L960 (13s Deerland - 825s Whitefish Lake), 13s 1752 (13s Deerland), 13s 1652 (13s Deerland) | 2021-05-11 09:00 | 2021-05-13 16:30 | N | Y | replace 13s52 (CVT12) JB | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 63s 752 (63s Red Deer), 63s 852 (63s Red Deer), 914L (63s Red Deer - 87s Gaetz) | 2021-05-11 09:30 | 2021-05-15 15:45 | N | Y | replacement of existing CVT 63s59, test 87s breaker trip from line protections | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 233s 708X (233s Beamer), 708L (233s Beamer - 708AL tap) | 2021-05-11 11:00 | 2021-05-11 17:00 | N | N | 388s MPLS node upgrade, 388s MPLS node upgrade. | Circuit Breaker, Line | Breaker to be opened prior to protection disable/enable as part of 388s MPLS node upgrade. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 33s 3 (33s Spray) | 2021-05-11 16:00 | 2021-05-11 18:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 33s 6 (33s Spray) | 2021-05-11 16:00 | 2021-05-11 18:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 993S Abee | 2021-05-12 07:00 | 2021-05-12 16:00 | N | N | Enbridge trip testing 993s437 | Station |  |  | For Information Only
AESO-SC | BRD1 Burdett Solar | 2021-05-12 07:00 | 2021-05-14 17:00 | N | N | BRD1 transformer inspection | Unit |  |  | Restricts Generation
ALTALINK | 730L (197s Bardo - 732L tap) | 2021-05-12 07:00 | 2021-05-19 18:00 | N | N | monopole installation at structures 2&3, component replacements on structures 7, 34, 36, 41 and 42 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 11.81L (ENMAX 11 - ENMAX 13), 11B138-11.81 (ENMAX 11) | 2021-05-12 08:00 | 2021-05-12 12:00 | N | N | SF6 gas sample 11B138-11.81 | Line, Circuit Breaker | 11.81L (ENMAX 11 - ENMAX 13) |  | Pre-Condition
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2021-05-12 08:00 | 2021-05-12 18:00 | N | N | 25 kV riser replacement and installation of bird cover-ups | Transformer | 262s T1 (262s Rocky Mountain House) |  | For Information Only
ALTALINK | 186s C1 (186s Dry Creek) | 2021-05-12 09:15 | 2021-05-12 17:15 | N | N | remove the bird nest and test | Shunts |  | Remove the bird nest and test the capbank from real time event that caused 186sC1 to be forced OOS May 4th, 2021 | Pre-Condition
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 14B138-14.83 (ENMAX 14) | 2021-05-12 12:00 | 2021-05-12 16:00 | N | N | SF6 gas sample 14B138-14.83 | Line, Circuit Breaker | 14.83L (ENMAX 14 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L137 (768s Rowley - 770s Three Hills), 768s 703 (768s Rowley) | 2021-05-13 08:30 | 2021-05-13 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | 768S 703 Breaker Maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 7B138-7.84 (ENMAX 7), 7.84L (ENMAX 7 - ENMAX 36) | 2021-05-14 08:00 | 2021-05-14 16:00 | N | N | SF6 gas sample 7B138-7.84 | Circuit Breaker, Line | 7.84L (ENMAX 7 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 138s T1 (138s Windy Flats), 497L (138s Windy Flats - 1063s Windrise), 1063s Windrise, 138s Windy Flats 138kV Bus 1 | 2021-05-14 08:00 | 2021-06-07 16:00 | N | N | P2041 Windrise. ISD May 26, 2021 | Transformer, Line, Station, Bus
EPCOR | 72RV4 (511s Victoria - Rossdale), RV726 (Rossdale) | 2021-05-14 20:00 | 2021-05-16 17:00 | N | N | outage required to remove scaffolding for termination completion @ Rossdale on RW3 | Line, Circuit Breaker |  |  | For Information Only
EPCOR | T2 (Rossdale), T3 (Rossdale), R721 (Rossdale), R723 (Rossdale), R724 (Rossdale) | 2021-05-14 20:00 | 2021-05-16 17:00 | N | N | remove scaffolding for termination completion @ Rossdale on RW3 | Transformer, Circuit Breaker |  | outage required to remove scaffolding for termination completion @ Rossdale on RW3 | For Information Only
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2021-05-15 07:00 | 2021-05-16 17:00 | N | Y | line maintenance | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 13B138-2.83 (ENMAX 13), 2.83L (ENMAX 13 - 2.83L tap) | 2021-05-15 08:00 | 2021-05-15 16:00 | N | N | SF6 gas sample 13B138-2.83 | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 16.1TR (ENMAX 16) | 2021-05-15 10:00 | 2021-05-15 16:00 | N | N | arc flash door recall & PK block shorting bar swap | Transformer |  |  | For Information Only
ALTALINK | 900L (17s Benalto - 63s Red Deer), 63s 152 (63s Red Deer), 63s 252 (63s Red Deer) | 2021-05-16 06:15 | 2021-05-16 17:45 | N | Y | replacement of existing CVT 63s36 | Line, Circuit Breaker | 900L (17s Benalto - 63s Red Deer) |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31B138-31CAP (ENMAX 31), 31.1TR (ENMAX 31), 31.1C (ENMAX 31), 31.2TR (ENMAX 31), 31B138-9.80 (ENMAX 31) | 2021-05-16 08:00 | 2021-05-16 18:00 | N | N | SW89 & SW84 @ 31 sub stiff to operate and adjust all phases | Line, Circuit Breaker, Transformer, Shunts |  |  | For Information Only
ENMAX | 16.2TR (ENMAX 16) | 2021-05-16 10:00 | 2021-05-16 16:00 | N | N | arc flash door recall & PK block shorting bar swap | Transformer |  |  | For Information Only
EPCOR | E511s Victoria T1 (511s Victoria) | 2021-05-17 07:00 | 2021-05-28 17:00 | N | N | Victoria TX1 DGA replacement | Transformer |  | Victoria TX1 DGA replacement - 107382.038156 | For Information Only
EPCOR | 330p 803 (330p Genesee) | 2021-05-17 07:00 | 2021-05-17 17:00 | N | N | 803 relay maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | G726 (Garneau), T2 (Garneau), G725 (Garneau) | 2021-05-17 07:30 | 2021-05-28 17:00 | N | N | isolate TX2 bay at Garneau for transformer protection upgrade | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 38.1TR (ENMAX 38) | 2021-05-17 08:00 | 2021-05-19 16:00 | N | N | tapchanger inspection. check reversing switch | Transformer |  |  | For Information Only
ENMAX | 41.1TR (ENMAX 41) | 2021-05-17 08:00 | 2021-05-21 16:00 | N | N | ECI bushing replacements | Transformer
ENMAX | 9.1TR (ENMAX 9) | 2021-05-17 08:00 | 2021-05-20 16:00 | N | N | power factor test transformer, transformer maintenance. gas relay testing | Transformer
ENMAX | 21.1TR (ENMAX 21) | 2021-05-17 08:00 | 2021-05-21 16:00 | N | N | bushing replacement | Transformer
ALTALINK | 430s Ursus, 997L (71s Lamoureux - 430s Ursus), 1027L (410s Josephburg - 430s Ursus), 430s Ursus 240kV Bus 1, 430s Ursus 240kV Bus 2, 430s 901T (430s Ursus), 430s 902T (430s Ursus) | 2021-05-17 08:00 | 2021-06-08 16:00 | N | N | P1647 Fengate. ISD June 3, 2021 | Station, Line, Bus, Transformer |  |  | Affects Cranking Path
ENMAX | 22B138-22.81 (ENMAX 22), 22.81L (ENMAX 22 - ENMAX 39), 39B138-22.81 (ENMAX 39) | 2021-05-17 08:00 | 2021-05-21 16:00 | N | N | pole relocate, no phasing required on return | Circuit Breaker, Line | 22.81L (ENMAX 22 - ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 809s 706 (809s Louise Creek) | 2021-05-17 08:00 | 2021-06-10 17:00 | N | N | breaker protection upgrade | Circuit Breaker |  | Louise Creek Rebuild project - 706 Breaker Protection upgrade Bypass 700D1 in service until May 25, 2021 - Protection Changes will be required at 739S Edith Lake and 851S Morse River 700D1 Bypass will be available May 17-25, 2021, After May 25, Bypass is not available as the bypass is being moved. 2 days emergency restoration at that point Complete wiring for 21A and 21B relays. CT ratio changes Relay programming. Commission control, alarms and status. Blocking procedures for BF and Bus protections | For Information Only, Pre-Condition
ATCO | 793s 702T (A793s West Peace) | 2021-05-17 08:30 | 2021-05-19 15:00 | N | N | maintenance testing and leak repairs. | Transformer |  | Major maintenance testing of 702T and leak repairs. | For Information Only
ATCO | 888s 916 (888s Dover), 888s 916R (888s Dover) | 2021-05-17 08:30 | 2021-05-19 16:00 | N | Y | RTXP switch replacements, leak mitigation on 916R, breaker maintenance 916, PRC005 work | Circuit Breaker, Shunts |  | RTXP Switch Replacements, Leak mitigation on 916R, Breaker maintenance 916, PRC005 work | For Information Only
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2021-05-17 09:15 | 2021-05-17 12:45 | N | N | disconnect 471s and MR1 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 535s T6 (535s Joffre) | 2021-05-17 11:15 | 2021-05-20 17:45 | N | N | T6 maintain, doble, fix leaks | Transformer |  |  | For Information Only
ALTALINK | 185s 352 (185s Bretville), 606L (184s Petro-Canada Edmonton - 185s Bretville), 185s 452 (185s Bretville) | 2021-05-17 11:30 | 2021-05-17 17:30 | N | N | open as part of 185s radio replacement | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 102s SVC (102s Langdon), 102s T4 (102s Langdon) | 2021-05-17 11:30 | 2021-05-20 17:30 | N | Y | 4 year SVC and T4 maintenance | Shunts, Transformer | 102s SVC (102s Langdon) |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2021-05-17 12:00 | 2021-05-19 16:00 | N | Y | component replacements 1045L str's range 1-175 | Line | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | Component Replacements 1045L Str's Range 1-175 See Also 272822 909L R/B required due to proximity. | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 447s T2 (447s Enchant) | 2021-05-17 12:30 | 2021-05-20 17:30 | N | N | maintenance, bird nest removal | Transformer |  | Maintenance, doble, SFRA, IDD/DC ground (T2). Bird cover. Hot spot repair (s9). Bird nest removal (s18) | For Information Only
ALTALINK | 700L (422s Westwood - 746s Sherwood Park), 746L (700L tap - 746AL tap) | 2021-05-17 13:00 | 2021-05-17 17:00 | N | N | remove 475s 138kV risers to 700L | Line |  | Remove 475s 138kV risers to 700L. Create Open Point A. RSLD 3 | Creates Radial Feeds, Firm Load Loss
ALTALINK | 814L (28s West Brooks - 121s Brooks), 28s 22 (28s West Brooks), 28s 25 (28s West Brooks) | 2021-05-17 13:15 | 2021-05-20 17:45 | N | N | replacement of 138kV PTs at 28s34 | Line, Circuit Breaker | 814L (28s West Brooks - 121s Brooks) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 602s 2082N (602s Cold Creek) | 2021-05-18 08:30 | 2021-05-18 17:00 | N | Y | complete Fortis requested wiring and settings changes on 602s2082N | Circuit Breaker |  | complete Fortis requested wiring and settings changes on 602s2082N. Open Advice & alternate T1 & T2 settings via maintenance switch to avoid arc flash hazard in switchgear building. | For Information Only, Restricts Generation
ALTALINK | 13s 1652 (13s Deerland) | 2021-05-18 09:00 | 2021-05-18 12:30 | N | Y | maintenance and fix bent pallet switches | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 13s 1752 (13s Deerland) | 2021-05-18 13:00 | 2021-05-18 17:00 | N | Y | maintenance and fix moisture in SF6 gauge | Circuit Breaker |  | Maintenance on 13s1752 including 1st trip testing. Fix moisture in SF6 gauge | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-05-19 00:01 | 2021-05-20 05:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-05-19 07:00 | 2021-06-28 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 727L (678s Okotoks - 727AL tap) | 2021-05-19 07:15 | 2021-05-19 17:45 | N | N | maintenance (Str 75 ~ 83) | Line | 727L (678s Okotoks - 727AL) |  | Over/Under Voltage, Pre-Condition
SUNCOR | 29EDD-71 752-4622 (29EDD-71) | 2021-05-19 08:00 | 2021-05-19 18:00 | N | N | repair insulator chip | Circuit Breaker |  | 29-752-4622; REPAIR INSULATOR CHIP; (A) | For Information Only
ALTALINK | 906s T1 (906s Ross Creek) | 2021-05-19 08:00 | 2021-08-18 16:00 | N | N | forced outage | Transformer
ALTALINK | 13s 852 (13s Deerland) | 2021-05-19 09:00 | 2021-05-19 12:30 | N | N | maintenance on 13s852 including 1st trip testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 58s C1 (58s Edson) | 2021-05-19 09:00 | 2021-09-09 16:00 | N | N | install new protections | Shunts |  |  | Pre-Condition
ALTALINK | 574s 552 (574s Nilrem), 574s 652 (574s Nilrem), 953L (574s Nilrem - 755s Cordel) | 2021-05-19 12:30 | 2021-05-19 16:30 | N | Y | open as part of 478s - 9465R Radio upgrade | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 13s 1252 (13s Deerland) | 2021-05-19 13:00 | 2021-05-19 17:00 | N | Y | maintenance on 13s1252 including 1st trip testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition,Affects Cranking Path
ALTALINK | 739L (14s Devon - 305s Acheson) | 2021-05-20 07:00 | 2021-05-20 18:00 | N | N | maintenance on structures 447, 465 and 611 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 320p 809X (320p Keephills), 809L (320p Keephills - 510s Sunnybrook) | 2021-05-20 08:00 | 2021-05-20 11:30 | N | Y | breaker fail trip testing on breaker 1152 (320p809X) and commissioning 1152 BF trip | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | 3.84L (ENMAX 3 - ENMAX 13) | 2021-05-20 08:00 | 2021-05-20 16:00 | N | N | Breaker maintenance | Line |  | HV Breaker maintenance. SF6 Gas sample 3B138-3.84 | Creates Radial Feeds, Firm Load Loss
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2021-05-20 08:00 | 2021-05-20 16:00 | N | Y | repair broken strands | Line |  |  | 500 kV
REDDEER | 247s T1 (247s Piper Creek) | 2021-05-20 09:00 | 2021-05-20 15:00 | N | N | power transformer outage request | Transformer
GENT | BHL1 Bellshill | 2021-05-20 09:00 | 2021-05-20 15:00 | N | N | AltaLink RAS/TT work | Unit
ALTALINK | 54s 706N (54s Fort Saskatchewan), 706L (54s Fort Saskatchewan - 706AL tap) | 2021-05-20 09:00 | 2021-05-20 12:30 | N | N | breaker maintenance | Circuit Breaker, Line |  | Maintenance on 54s706N including 1st trip testing. Top up SF6 gas. | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
REDDEER | 217s T1 (217s North Red Deer) | 2021-05-20 09:00 | 2021-08-19 15:00 | N | N | power transformer replacement (like-for-like) | Transformer |  |  | For Information Only
ALTALINK | 320p 834X (320p Keephills), 834L (320p Keephills - 384s Keystone) | 2021-05-20 11:30 | 2021-05-20 14:30 | N | N | breaker trip testing | Circuit Breaker, Line |  | New C60 breaker fail trip testing on breaker 1252 (320p834X) and commissioning 1252 BF trip to C60. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 74s Janet 240kV Bus 2, 929L (74S Janet - 287s Hazelwood), 74s T2 (74s Janet), 74s C3 (74s Janet), 74s C4 (74s Janet) | 2021-05-20 12:45 | 2021-05-20 18:00 | N | Y | close open point A on 240kV B2 bus | Bus, Line, Transformer, Shunts | 929L (74S Janet - 287s Hazelwood), 74s T2 (74s Janet) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 54s 709N (54s Fort Saskatchewan), 709L (54s Fort Saskatchewan - 172s Sherritt) | 2021-05-20 13:00 | 2021-05-20 17:00 | N | Y | breaker maintenance | Circuit Breaker, Line |  | Maintenance on 54s709N including 1st trip testing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 138s 240kV Bus 1 (138s Windy Flats), 138s 252 (138s Windy Flats), 138s 552 (138s Windy Flats), 138s 752 (138s Windy Flats), 138s 1052 (138s Windy Flats) | 2021-05-20 13:01 | 2021-05-20 14:01 | N | Y | opening breakers on 240 kV bus 1 to facilitate first time energization of 138s 138 kV bus 1 after 48 hr 138sT1 Tx18979 soak for return to service switching (P2041) | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 138s Windy Flats 138kV Bus1 | 2021-05-20 13:01 | 2021-05-28 08:30 | N | N | complete end to end/functional testing (P2041) | Bus
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside) | 2021-05-21 07:30 | 2021-05-21 17:30 | N | Y | maintenance on structure 1057L1/908L233 | Line | 1057L (89s Ellerslie - 657s Summerside) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 507L (83s Taber - 257s Hull), 83s 507 (83s Taber) | 2021-05-21 08:15 | 2021-05-21 15:45 | N | N | hotspot repair (83s39) | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 932s 906 (932s Pemukan) | 2021-05-21 10:48 | 2021-06-09 16:00 | N | Y | real time emergency outage to fix major oil leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p 91 (320p Keephills), 320p T1 (320p Keephills) | 2021-05-21 13:00 | 2021-05-21 15:30 | N | Y | new C60 breaker fail trip testing on breaker 952 (320p91) and commissioning 952 BF trip to C60 | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2021-05-22 07:00 | 2021-05-23 18:00 | N | N | replace structures 718 and 749 | Line | 739L (14s Devon - 155s Blackmud) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.83L (162s Beddington - ENMAX 11), 162B138-RB84 (ENMAX 162), 162B138-RB85 (ENMAX 162) | 2021-05-22 08:00 | 2021-05-22 16:00 | N | N | power factor test | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 330p 1207 (330p Genesee), 330p 1208 (330p Genesee) | 2021-05-24 07:00 | 2021-05-24 17:00 | N | Y | arrestor doble, zone relay maintenance | Circuit Breaker |  | G3 Arrestor Doble, G3 Zone Relay Maintenance | 500 kV, Contingency Requires Mitigation
ALTALINK | 83s 138kV West Bus (83s Taber), 610L (83s Taber - 336s Fincastle), 172L (83s Taber - 172EL tap), 83s C2 (83s Taber), 83s T1 (83s Taber) | 2021-05-24 07:00 | 2021-05-26 16:06 | N | Y | urgent: repair/replace 138kV switch 83s36, raise 138kV bus | Bus, Line, Shunts, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 760L (163s Amoco Empress - 394s Empress) | 2021-05-24 07:00 | 2021-06-03 17:00 | N | N | upgrade of 760L line A and B protections | Line |  | 760L line outage to allow upgrade of 760L line A and B protections at 394s and 163s, and breaker 394s760N protection replacement | Creates Radial Feeds, Firm Load Loss
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2021-05-24 07:15 | 2021-05-26 17:45 | N | N | maintenance (str 103 - 294) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635PT-1070 (635EDD-1003) | 2021-05-24 08:00 | 2021-06-07 18:00 | N | Y | 144kV central sub 635EDD-1001 dia 6 lower bay | Transformer |  | 144kV Central Sub 635EDD-1001 Dia 6 Lower Bay Equipment Outage 635PT-1070 will not be restored until a later date as per generator outage schedule | Restricts Generation
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2021-05-24 08:00 | 2021-05-24 16:00 | N | N | kinectrics cable testing, transmission - potheads, O-ring replacements 138-9.83 | Line |  | Kinectrics Cable testing. Transmission - Potheads, O-Ring replacements 138-9.83 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L19 (809s Louise Creek - 851s Morse River) | 2021-05-25 | 2021-06-09 14:45 | N | N | remove 7L43/7L19 bypass (through 700D1) connection point on 7L19 | Line |  | Remove 7L43/7L19 bypass (through 700D1) connection point on 7L19 in preparation for it to be moved to 7L43 on 2-50619 | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s T2 (987s Clover Bar) | 2021-05-25 07:00 | 2021-05-25 17:00 | N | Y | 72kV tie line maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 744L (235s Entwistle - 744AL tap) | 2021-05-25 07:00 | 2021-05-26 18:00 | N | N | insulator washing on structures #1A - 21A & 5 - 11 | Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72MG16 (Garneau - Meadowlark) | 2021-05-25 07:00 | 2021-06-11 17:00 | N | N | civil work at meadowlark | Line | Outage required for civil work at Meadowlark S/S near 72MG16 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s 1224 (2029s Heathfield), 2029s ACF23 (2029s Heathfield) | 2021-05-25 07:00 | 2021-06-18 15:00 | N | Y | perform PRC-005 tests on all devices associated with ACF23 and breaker 1224 | Circuit Breaker, Shunts |  | Perform PRC-005 tests on all devices associated with ACF23 and breaker 1224, Filter will be unavailable, One device worked on at a time | 500 kV, Pre-Condition
ALTALINK | 138s 240kV Bus 1 (138s Windy Flats), 138s R1 (138s Windy Flats), 138s 252 (138s Windy Flats), 138s 752 (138s Windy Flats), 138s 552 (138s Windy Flats), 138s 1052 (138s Windy Flats), 138s T1 (138s Windy Flats) | 2021-05-25 07:30 | 2021-05-25 17:30 | N | Y | 240kV Bus #1 outage to allow change out of non-corona free connectors from 240kV Bus #1 to 138s1789 air switch (P2041) | Bus, Shunts, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 65.1TR (ENMAX 65) | 2021-05-25 08:00 | 2021-05-27 16:00 | N | Y | replacing DGA tubing, oil sampling MT, TC | Transformer | GE will be replacing all the DGA tubing with insulated tubing. Oil Sampling MT, TC. Check Reversing Switch. |  | 240 kV, Contingency Requires Mitigation
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 33.2TR (ENMAX 33) | 2021-05-25 08:00 | 2021-05-25 16:00 | N | N | kinectrics cable testing, O-ring replacements | Line, Transformer | SW 85 at 33 sub - Stiff to operate - need to maintain. Kinectrics Cable testing. Transmission - Potheads, O-Ring replacements 138-33.84 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.2TR (ENMAX 15) | 2021-05-25 08:00 | 2021-06-01 16:00 | N | N | MV bushing replacement, check reversing wwitch | Transformer |  |  | For Information Only
TRANSALTA | 240S McBride Lake | 2021-05-25 08:00 | 2021-05-25 13:00 | N | Y | repair work at site | Station |  |  | Restricts Generation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2021-05-25 08:00 | 2021-05-28 13:00 | N | N | HV breaker maintenance | Line | HV Breaker maintenance 16B69-15.62 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s 910 (2075s Newell), 2075s 911 (2075s Newell), 2075s ACF21 (2075s Newell), 2075s ACF22 (2075s Newell), 2075s ACF23 (2075s Newell), 2075s ACF24 (2075s Newell) | 2021-05-25 08:00 | 2021-06-25 15:30 | N | Y | filter banks maintenance | Circuit Breaker, Shunts |  | Filter Bank Maintenance, EATL will be limited to 750 MW, | 240 kV, Pre-Condition
SUNCOR | 139s C1 (139s Hillridge) | 2021-05-25 08:00 | 2021-05-25 17:00 | N | N | annual maintenance & cleaning | Shunts |  |  | For Information Only
ATCO | 755s 905 (755s Cordel), 755s 906 (755s Cordel), 9L953 (574s Nilrem - 755s Cordel) | 2021-05-25 08:00 | 2021-05-31 16:00 | N | Y | protection upgrade for 9L953, 906/905 breakers | Circuit Breaker, Line | 9L953 (574s Nilrem - 755s Cordel) | Protection upgrade for 9L953, 906/905 Breakers. We will need to modify the wiring on 9L953D1 during this outage and test its operation during the switching back to normal at the end of the outage. | 240 kV, Contingency Requires Mitigation,Affects Cranking Path
ENMAX | 13.1TR (ENMAX 13) | 2021-05-25 08:00 | 2021-05-25 16:00 | N | N | arc flash door recall & PK block shorting bar swap | Transformer |  |  | For Information Only
ALTALINK | 185s T1 (185s Bretville) | 2021-05-25 08:30 | 2021-05-25 17:00 | N | N | fix Hydran sensor, fix leaks, fix main cabinet, replace gas detector | Transformer |  |  | For Information Only
ATCO | 888s 907 (888s Dover) | 2021-05-25 08:30 | 2021-05-27 16:00 | N | Y | breaker maintenance and RTXP switch replacements | Circuit Breaker |  | RTXP Switch Replacements 9L43, Breaker Maintenance on BKR 907, PRC005 work | 240 kV, Contingency Requires Mitigation,Affects Cranking Path
ALTALINK | 364s T1 (364s Whitecourt Industrial) | 2021-05-25 09:00 | 2021-06-02 17:30 | N | N | T1: corrosive sulfur removal, fix leaks, replace fan contactor, doble, replace LA's. VR1: fix leaks, maintain, doble, fix LTC | Transformer |  |  | For Information Only
ATCO | 940s 701T (940s Beartrap) | 2021-05-25 09:30 | 2021-05-27 16:30 | N | N | complete maintenance | Transformer |  | 940S 701T Complete Maintenance | For Information Only
ATCO | 813s 901T (813s Little Smoky), 813s Little Smoky 240kV Bus 1 | 2021-05-25 11:00 | 2021-05-26 15:00 | N | Y | remove rubber covering from switch bottle actuator arms on 813S 901TD and change 901T CT ratio | Transformer, Bus |  | Remove rubber covering from switch bottle actuator arms on 813S 901TD Once complete go to GOI for 901T CT ratio change GOI # 2-56072 | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition,Affects Cranking Path
ALTALINK | 39s 29 (39s Bickerdike) | 2021-05-25 11:30 | 2021-05-27 14:30 | N | Y | replace 240kV CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 118s C1 (118s Canmore) | 2021-05-25 11:45 | 2021-05-27 17:45 | N | N | cap bank A protection upgrade SR760 (50/51/59/60/C1) | Shunts |  |  | For Information Only
ATCO | 7L85 (801s Anderson - 803s Bullpound) | 2021-05-25 12:00 | 2021-05-25 15:00 | N | N | emergency repairs to fix 2 mid span spacers that are hanging down and 1 set of insulators to change | Line |  | Emergency repairs to fix 2 midspan spacers that are hanging down and 1 set of insulators to change | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
AESO-SC | OATI | 2021-05-25 18:00 | 2021-05-25 18:00 | N | N | perform an inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 610L (83s Taber - 336s Fincastle) | 2021-05-26 07:15 | 2021-05-26 17:45 | N | Y | urgent repair 610L str's 10, 17, 20 down lead repairs | Line |  | Urgent Repair 610L Str's 10, 17, 20 Down Lead repairs | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.5TR (ENMAX 1) | 2021-05-26 08:00 | 2021-05-26 16:00 | N | N | deluge system investigate and repair | Transformer |  | 1.5TR Deluge system investigate and repair. | For Information Only
ATCO | 7L85 (803s Bullpound - 804s Wintering Hills) | 2021-05-26 08:00 | 2021-05-26 17:30 | N | N | emergency repair pole #410 | Line |  | Emergency GOI on 7L85 to repair Pole #410, damage discovered during line inspection | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Lethbridge | 172L (181s Chinook - 370s North Lethbridge) | 2021-05-26 08:00 | 2021-05-26 12:00 | N | Y | make changes on C60 relay settings and commission | Line |  | protection outages to make changes on C60 relay settings and commission | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2021-05-26 08:00 | 2021-05-26 16:00 | N | N | cable testing and maintenance | Line |  | Kinectrics Cable testing. Install PD sensors. Transmission - Potheads, O-Ring replacements 138-3.82 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.2TR (ENMAX 13) | 2021-05-26 08:00 | 2021-05-26 16:00 | N | N | arc flash door recall & PK block shorting bar swap | Transformer |  | Arc Flash Door Recall & PK Block Shorting Bar Swap | For Information Only
ATCO | 730s 702 (730s Rycroft) | 2021-05-26 09:00 | 2021-05-26 17:00 | N | N | Low CT oil needs topping up | Circuit Breaker |  | Low CT oil needs topping up, By-Bass Switch 7L68D3 will be closed prior to Outage to maintain service to 7L10 customers. 811S 7L68 Protection changes are required prior to closing 7L68D3, See associated CSP# 2-56710. | Pre-Condition
ALTALINK | 463L (181s Chinook - 463AL tap) | 2021-05-26 13:00 | 2021-05-26 16:00 | N | Y | protection outages to make changes on C60 relay settings and commission | Line |  | City of Lethbridge emergency outage. Open end outage on 463L to update protection settings. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2021-05-27 07:00 | 2021-05-28 12:00 | N | N | insulator washing on structures #205-209, 241-256, 259 & 260 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 673L (131s Moon Lake - 283s Violet Grove) | 2021-05-27 07:00 | 2021-05-29 18:00 | N | N | raise insulators on 673L Str 191 & 192 for line clearance mitigation | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725BL tap) | 2021-05-27 08:00 | 2021-05-27 12:00 | N | Y | protection outages to make changes on C60 relay settings and commission | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2021-05-27 08:00 | 2021-05-27 16:00 | N | N | re-install lightning spire | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-05-27 08:00 | 2021-05-27 18:00 | Y | Y | hazard tree removal | Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.3TR (ENMAX 13) | 2021-05-27 08:00 | 2021-05-27 16:00 | N | N | arc flash door recall & PK block shorting bar swap | Transformer |  |  | For Information Only
ALTALINK | 58s 671 (58s Edson), 671L (39s Bickerdike - 58s Edson) | 2021-05-27 08:30 | 2021-05-27 16:30 | N | N | 1st trip and PRC5 maintenance on 138kV SF6 breaker | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725AL tap) | 2021-05-27 13:00 | 2021-05-27 16:00 | N | Y | protection outages to make changes on C60 relay settings and commission | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 138s 240kV Bus 1 (138s Windy Flats), 138s 252 (138s Windy Flats), 138s 552 (138s Windy Flats), 138s 752 (138s Windy Flats), 138s 1052 (138s Windy Flats) | 2021-05-28 07:30 | 2021-06-02 08:30 | N | Y | opening breakers on 240kV bus 1 via 138s252, 138s552, 138s752 & 138s1052 (P2041) | Bus, Circuit Breaker |  | Opening breakers on 240kV BUS 1 via 138s252, 138s552, 138s752 & 138s1052 to facilitate first time energization of 138s 138kV BUS 1 after 138sT1 Tx18979 soak for return to service switching ref 275612 138s 138kV BUS 1 GOI. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 883s 701T (883s Gregoire) | 2021-05-28 08:00 | 2021-05-30 17:00 | N | N | planned outage with customer for 701TCS maintenance | Transformer |  | Planned outage with Customer for 701TCS maintenance. | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap), 6L21 (Youngstown Express - 6L09 tap), 6L09 (772s Youngstown - 776s Richdale), 6L09 (772s Youngstown - 6L21 tap) | 2021-05-28 08:00 | 2021-05-28 17:30 | N | N | emergency repair of inoperable switches 6L09D6 and 6L09D7 | Line |  | Emergency Repair of inoperable switches 6L09D6 and 6L09D7 | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.82L (ENMAX 3 - ENMAX 8), 3B138-3.82 (ENMAX 3) | 2021-05-28 08:00 | 2021-05-28 16:00 | N | N | kinectrics cable testing | Line, Circuit Breaker |  | Kinectrics Cable testing. Remove PD sensors 24-36hrs after initial re-energization | Creates Radial Feeds, Firm Load Loss
ATCO | 888s 908 (888s Dover) | 2021-05-28 08:30 | 2021-05-29 16:00 | N | Y | RTXP switch replacements 9L43, breaker maintenance on 908 | Circuit Breaker |  | RTXP Switch Replacements 9L43, Breaker Maintenance on 908, PRC005 work | 240 kV, Pre-Condition
ATCO | 834s 502 (834s Wesley Creek), 834s 502R (834s Wesley Creek) | 2021-05-28 08:30 | 2021-05-28 15:30 | N | N | complete 502 maintenance and testing | Circuit Breaker, Shunts |  | Complete 502 maintenance and testing | Pre-Condition
ALTALINK | 729L (542s Ervick - 729AL tap) | 2021-05-28 12:00 | 2021-05-28 18:00 | N | N | insulator washing on structures #25, 27 - 30, 121 - 123, 125, 198 & 199 | Line |  | Insulator washing on Structures #25, 27 - 30, 121 - 123, 125, 198 & 199 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2021-05-28 14:00 | 2021-05-29 16:00 | N | N | HV breaker maintenance 34B69-16.60 | Line | 16.60L (ENMAX 16 - ENMAX 34) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 394s T1 (394s Empress), 394s T3 (394s Empress), 394s 138kV Bus 1 (394s Empress) | 2021-05-28 14:00 | 2021-06-03 17:00 | N | N | replacement of the control and protection modules | Transformer, Bus |  | Expand 760L GOI to include 138KV Bus 1 & 25kV Bus 1 outage to allow replacement of the following control and protection modules: 138KV Bus 1, Transformers T1 and T3, Breaker 394s36 (552), Voltage Regulator VR1, 138KV VT9, 13.8KV PT7, 138KV Air Brake 394s4 (189). | Pre-Condition
ALTALINK | 277s T2 (277s Hayter) | 2021-05-28 18:00 | 2021-07-31 16:00 | N | N | real-time outage birds nest in T2 | Transformer |  | real-time outage Birds nest in T2. Load moved to T1 via internal bypass | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2021-05-29 10:00 | 2021-05-29 16:00 | N | N | arc flash door recall and PK block shorting bar swap. | Transformer |  |  | For Information Only
ATCO | 888s 908 (888s Dover), 888s 909 (888s Dover), 9L58 (848s Ruth Lake - 888s Dover) | 2021-05-29 16:30 | 2021-05-30 16:00 | N | Y | 9L58 RTXP switch replacements and 909 breaker maintenance and PRC005 work | Circuit Breaker, Line |  | RTXP Switch Replacements 9L58, Breaker Maintenance on 909, PRC005 work | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 23.4TR (ENMAX 23) | 2021-05-30 08:00 | 2021-05-30 18:00 | N | N | arc flash door recall and PK block shorting bar swap | Transformer |  | Arc Flash Door Recall & PK Block Shorting Bar Swap. | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2021-05-30 10:00 | 2021-05-30 16:00 | N | N | arc flash door recall & PK block shorting bar swap | Transformer |  | Arc Flash Door Recall & PK Block Shorting Bar Swap. | For Information Only, Pre-Condition
ALTALINK, ENMAX | 74s T1 (74s Janet), 691L (74s Janet - 419s Chestermere), 37.82L (74s Janet - ENMAX 37), 74s Janet 138kV North Bus, 74s C1 (74s Janet), 74s C2 (74s Janet) | 2021-05-31 06:00 | 2021-06-02 17:00 | N | Y | switch 74s17 replacement | Transformer, Line, Bus, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
EPCOR | EP 803s T2 (EP 803s Lambton) | 2021-05-31 07:00 | 2021-06-07 17:00 | N | Y | emergency tap changer investigation | Transformer |  |  | 240 kV, Firm Load Loss, Pre-Condition
EPCOR | 987s CCP7213 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale), 987s 72kV Bus 3 (987s Clover Bar) | 2021-05-31 07:00 | 2021-06-02 17:00 | N | Y | breaker maintenance | Circuit Breaker, Line, Bus | Bus 3 CVT Doble, CDS9/CDS14/CGDS2 maintenance |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | 52s T2 (52s East Industrial) | 2021-05-31 07:00 | 2021-06-11 17:00 | N | Y | DGA replacement | Transformer |  | East Industrial TX2 DGA Replacement - 1007382.036969 | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | VHBB1 (Rossdale) | 2021-05-31 07:00 | 2021-06-17 21:00 | N | N | replace existing M/O circuit breaker | Circuit Breaker | Replace existing M/O circuit breaker with new SF6 circuit breaker (1007158) |  | Pre-Condition
EPCOR | T1 (EPCOR Riverview) | 2021-05-31 07:00 | 2021-06-02 17:00 | N | Y | grating install and tank heater repair | Transformer | RWDS1 and RWDS10 adjustment, grating install, RW2401 Tank Heater repair |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 268s 199N (268s Whitecourt), 199L (268s Whitecourt - 199AL tap) | 2021-05-31 07:00 | 2021-06-03 18:00 | N | N | insulator washing on structures #367 - 412 | Circuit Breaker, Line |  | Insulator washing on Structures #367 - 412 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 635EDD-1001 635-752-661 (635EDD-1001), 635EDD-1001 635-752-662 (635EDD-1001), 635PT-1037 (635EDD-1001) | 2021-05-31 08:00 | 2021-06-07 18:00 | N | N | upper bay equipment outage | Circuit Breaker, Transformer |  | 144kV Central Sub 635EDD-1001 Dia 6 Upper Bay Equipment Outage | For Information Only
ALTALINK | 74s 2152 (74s Janet) | 2021-05-31 08:00 | 2021-06-08 13:30 | N | Y | breaker replacement with SF 6 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.8TR (ENMAX 1) | 2021-05-31 08:00 | 2021-06-03 16:00 | N | N | power factor test transformer, transformer maintenance, gas relay testing, check reversing switch, oil sampling TC | Transformer |  | Power factor test transformer, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil Sampling TC | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2021-05-31 08:00 | 2021-06-03 16:00 | N | N | power factor test transformer, secondary cable tests, transformer maintenance, gas relay testing, oil sampling MT, TC. check reversing switch | Transformer |  | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil Sampling MT, TC. Check reversing switch. | For Information Only
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2021-05-31 08:00 | 2021-06-03 16:00 | N | N | breaker maintenance 16B69-16.60 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.3TR (ENMAX 38) | 2021-05-31 08:00 | 2021-06-01 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ATCO | 809s 902T (809s Louise Creek), 809s 701C (809s Louise Creek) | 2021-05-31 08:00 | 2021-06-28 17:00 | N | Y | Louise Creek rebuild project - demo work on old 144 KV protection, CT modifications, wiring new panel | Transformer, Shunts | Check with OPTRA close to outage if project or capital maintenance. V.Chan Nov 9, 2020. | Louise Creek Rebuild project Demo work on old 144KV protection, CT modifications to CT707, CT709, Wiring new panel 7P1, 7C1, 7B1 Prep new bypass deadend structure and connect new bypass to 7L56 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 63s 2652 (63s Red Deer) | 2021-05-31 10:00 | 2021-06-03 17:30 | N | Y | breaker maintenance and grading cap replacement | Circuit Breaker |  | 240kV breaker maintenance and grading cap replacement | 240 kV, Contingency Requires Mitigation
ATCO | 840s 901T (840s MCNEILLSTATION), 840s 701T (840s MCNEILLSTATION), 840S McNeill Station | 2021-05-31 10:00 | 2021-06-11 15:30 | N | Y | transformer and breaker testing | Transformer, Station |  | TRANSFORMER CLASS1 MAJOR TESTING 901T BREAKER VACUUM VA8012 COMPLETE TESTING @ MCNEILL STATION 840S 502, 507, 508, 509, 511, 512 Plus various other Mechanical issues on the valve hall | Limits ATC
ALTALINK | 39s 33 (39s Bickerdike) | 2021-05-31 11:30 | 2021-06-03 16:30 | N | Y | replace 240kV CTs | Circuit Breaker |  |  | 240 kV
ALTALINK | 649s T1 (649s Chappice Lake) | 2021-05-31 11:30 | 2021-05-31 17:30 | N | N | standard relay maintenance | Transformer |  |  | For Information Only
Syncrude | UE-1 30-2PTR72-A1 (UE-1), UE-1 7202 (UE-1 Syncrude Plant 30-2) | 2021-05-31 12:00 | 2021-06-09 20:00 | N | Y | urgent work | Transformer, Circuit Breaker |  | There is an abnormal sound and possible bushing leak on the 30-2PTR72-A1 Transformer at UE-1 Substation. It needs to be isolated asap to prevent any further damage or equipment trips. | Restricts Generation
ATCO | 755s 903 (755s Cordel) | 2021-05-31 12:00 | 2021-06-10 12:00 | N | Y | test and operate of 903, protection upgrade on 9L80 | Circuit Breaker |  | Test and Operate of 903. Protection upgrade on 9L80 during plan shut down under GOI 2-54986B. Test and operate | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 320p T1 (320p Keephills), 320p 91 (320p Keephills) | 2021-05-31 12:30 | 2021-06-11 13:30 | N | Y | replacing breaker control and breaker fail relays | Transformer, Circuit Breaker | Replacing 952 (320p91) breaker control and breaker fail relays with new C60 module. |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 790s 705 (790s Poplar Hill), 7L101 (790s Poplar Hill - 944s Lowe Lake) | 2021-05-31 13:00 | 2021-06-03 18:00 | N | Y | wiring in protection for 705 trip and close circuit | Circuit Breaker, Line |  | Wiring in protection for 705 Trip and Close CCT. This outage date was coordinated with the planned customer outage on May 30 - June 21, 2021 | Restricts Generation, Affects Cranking Path
ALTALINK | 138s T1 (138s Windy Flats) | 2021-05-31 13:30 | 2021-06-02 17:30 | N | Y | testing | Transformer |  | 138sT1 transformer testing: " Excitation test " Core ground measurements " Doble PF testing to check insulation " TTR " SFRA " Winding resistance " DGA samples collected | For Information Only
ALTALINK | 151s T2 (151s Strathmore) | 2021-05-31 14:00 | 2021-06-02 17:00 | N | N | maintenance, doble, SFRA (T2), switch maintenance (s31, s34), breaker maintenance (s35) | Transformer |  |  | For Information Only
ATCO | 9L16 (755s Cordel - 972s Tinchebray), 755s 904 (755s Cordel), 755s 905 (755s Cordel) | 2021-06-01 08:00 | 2021-06-14 17:00 | N | Y | 9L16 protection upgrade, update protection to 905 & 904 breakers | Line, Circuit Breaker |  | 9L16 Protection upgrade, update protection to 905 & 904 Breakers 9L80 included Initially in Outage Starting May 31 and will be restored on June 4th. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENBRIDGE, BLACKSPRING | 485s DVAR1 (485s Blacksprings), 485s DVAR2 (485s Blacksprings) | 2021-06-01 08:00 | 2021-06-04 17:00 | N | N | maintenance | Shunts |  |  | Pre-Condition
ALTALINK | 879L (244s Bowmanton - 368s Burdett) | 2021-06-01 09:15 | 2021-06-25 17:45 | N | Y | rebuild str's 500-734 line protection upgrades at 244s/368s, as well as new T-tap connection (Rattlesnake Ridge) (P2212) | Line |  | 879L Rebuild Str's 500-734. Line Protection upgrades at 244s/368s, as well as new T-tap connection (Rattlesnake Ridge) | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 768L (209s Timberlands - 217s North Red Deer) | 2021-06-02 07:15 | 2021-06-02 17:45 | N | Y | maintenance on structure 49 | Line | 768L (209s Timberlands - 217s North Red Deer) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 199L (268s Whitecourt - 199AL tap), 199L (347s Fox Creek - 199AL tap) | 2021-06-02 07:30 | 2021-06-02 17:30 | N | Y | maintenance | Line |  |  | Restricts Generation
ENMAX | 21.1C (ENMAX 21) | 2021-06-02 08:00 | 2021-06-03 16:00 | N | N | maintenance | Shunts |  | Cap bank, HV Maintenance | Pre-Condition
ENMAX | 2.3TR (ENMAX 2) | 2021-06-02 08:00 | 2021-06-03 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12), 12B138-833L (ENMAX 12) | 2021-06-02 08:00 | 2021-06-02 16:00 | N | Y | transmission, cables sheath test - 138-833 Line XLPE | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 9L80 (755s Cordel - 757s Battle River), 757s 912T (757s Battle River), 757s 710 (757s Battle River), 757s 912 (757s Battle River) | 2021-06-02 08:30 | 2021-06-09 16:30 | N | Y | PRC005 work on 912T, 912, 910 912 breaker maintenance | Line, Transformer, Circuit Breaker |  | PRC005 work on 912T, 912, 910 912 Breaker Maintenance | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
Saskpower | SASK POWER P2S | 2021-06-02 09:00 | 2021-06-02 17:00 | N | Y | maintenance | Line |  |  | For Information Only
ALTALINK | 89s 2152 (89s Ellerslie) | 2021-06-02 10:30 | 2021-06-02 16:30 | N | Y | maintenance for 1st trip testing and CT leak inspect gauge | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
Saskpower | SaskPower A1R | 2021-06-03 07:00 | 2021-06-03 17:00 | N | Y | high load move | Line |  |  | Limits ATC, Pre-Condition
EPCOR | RW2405 (EPCOR Riverview), RW2403 (EPCOR Riverview), 1139L (367s Harry Smith - EPCOR Riverview) | 2021-06-03 07:00 | 2021-06-04 17:00 | N | Y | adjust RWDS6/RWDS9 | Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s C2406 (987s Clover Bar) | 2021-06-03 07:00 | 2021-06-04 17:00 | N | Y | doble C2406 bay CT's | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Lethbridge | 241s T2 (241s Lethbridge Uplands), 813L (146s Lethbridge MacDonald - 241s Lethbridge Uplands) | 2021-06-03 08:00 | 2021-06-03 13:00 | N | N | air break function test and maintenance | Transformer, Line | 813L (146s Lethbridge MacDonald - 241s Lethbridge Uplands) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
TRANSALTAW | WRW1 Windrise | 2021-06-03 08:00 | 2021-08-31 16:00 | N | N | P2401 Windrise Generator. 206 MW. ISD June 10, 2021 | Unit
ALTALINK, Lethbridge | 734L (241s Uplands - 370s North Lethbridge), 241s T1 (241s Uplands) | 2021-06-03 13:00 | 2021-06-03 17:00 | N | Y |  | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 394s T1 (394s Empress) | 2021-06-03 17:00 | 2021-06-11 16:30 | N | N | cutover of 25 kV feeder breaker | Transformer |  |  | For Information Only, Pre-Condition
ALPAC | 282s Grassland (Alpac) RTU/SCADA | 2021-06-03 19:00 | 2021-06-03 20:00 | N | N | internet outage | Terminal Equipment |  |  | For Information Only
ALTALINK | 56L (20s Ghost - 245s Seebe) | 2021-06-04 07:00 | 2021-06-08 18:00 | N | N | structure maintenance | Line | 56L (20s Ghost - 245s Seebe) | Scope of work includes maintenance on structures 1, 5, 41, 45, 55, 57, 60, 62, 75, 88, 105, 107, 112, 114, 130, 131, 147, 148, 153, 159 and 175. | Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2021-06-04 07:15 | 2021-06-06 17:45 | N | Y | structure maintenance | Line | 717L (17s Benalto - 262s Rocky Mountain House) | Scope of work includes maintenance on structures 98, 104, 107, 116 and 118 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 37.1TR (ENMAX 37), 37.81L (ENMAX 37 - ENMAX 38) | 2021-06-04 08:00 | 2021-06-04 16:00 | N | N | power factor test 37PT138-Z31 | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 15.1TR (ENMAX 15) | 2021-06-04 08:00 | 2021-06-11 16:00 | N | N | MV bushing replacement | Transformer |  | 15.1TR MV Bushing Replacement. | For Information Only
Saskpower | SaskPower C1S | 2021-06-04 09:00 | 2021-06-04 16:00 | N | Y | maintenance | Line | SaskPower C1S | replacing 4 structures and stringing across Lake Diefenbaker | Limits ATC
ATCO | 790s 509C (790s Poplar Hill) | 2021-06-05 08:00 | 2021-06-07 13:00 | N | N | add another CT input from 509 to 87TA/702T protection relay | Shunts |  | Add another CT input from 509 to 87TA/702T protection relay. 509C was temporarily put back into service until engineering had come up with a fix | For Information Only, Pre-Condition
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2021-06-06 07:00 | 2021-06-12 16:00 | N | N | cartwright lighting upgrading signage near line | Line |  | Cartwright lighting upgrading signage near line | For Information Only, Pre-Condition
ENMAX | 23.3TR (ENMAX 23) | 2021-06-06 12:00 | 2021-06-17 16:00 | N | N | 23 sub cable trench replacement | Transformer |  |  | For Information Only
ALTALINK | 204s T1 (204s Sandypoint) | 2021-06-06 12:00 | 2021-06-09 12:00 | N | N | customer work | Transformer |  |  | For Information Only
ALTALINK | 511s 4852 (511s Crossings), 511s 4952 (511s Crossings), 1325L (510s Sunnybrook - 511s Crossings) | 2021-06-07 07:00 | 2021-06-17 18:00 | N | Y | semi annual inspection and maintenance | Circuit Breaker, Line | 1325L (510s Sunnybrook - 511s Crossings) | Semi Annual Inspection and Maintenance, Doble T11 and Valve Hall and DC yard Inspection | 500 kV, Pre-Condition
EPCOR | 72DS26 (665s Dome - Strathcona), 665s D721 (665s Dome) | 2021-06-07 07:00 | 2021-06-18 17:00 | N | N | line maintenance | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | RW2402 (EPCOR Riverview), RW2403 (EPCOR Riverview), T2 (EPCOR Riverview) | 2021-06-07 07:00 | 2021-06-11 17:00 | N | Y | RWDS4/RWDS5 adjustment, grating install, TX2 dehydrator install | Circuit Breaker, Transformer |  | RWDS4/RWDS5 adjustment, grating install, TX2 dehydrator install | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 510s Sunnybrook 500kV A Bus, 510s Sunnybrook 500kV B Bus | 2021-06-07 07:00 | 2021-06-16 18:00 | N | Y | modifications to DC circuit | Bus |  | Motor Mech modifications to DC circuit | 500 kV, Contingency Requires Mitigation, Pre-Condition,Affects Cranking Path
EPCOR | T1 (Woodcroft) | 2021-06-07 07:00 | 2021-06-08 17:00 | N | N | isolate TX1 to cutover and commission 15 KV bus overcurrent protection | Transformer |  | Isolate TX1 to cutover and commission 15KV bus overcurrent protection. | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2021-06-07 08:00 | 2021-06-10 16:00 | N | N | secondary bushing leak repair | Transformer |  |  | For Information Only
ENMAX | 32.2TR (ENMAX 32) | 2021-06-07 08:00 | 2021-06-10 16:00 | N | N | transformer maintenance and test | Transformer |  | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch, Oil Sampling MT, TC, Bushing | For Information Only
ENMAX | 16B69-16.63 (ENMAX 16), 16.63L (ENMAX 16 - ENMAX 36) | 2021-06-07 08:00 | 2021-06-08 16:00 | N | N | breaker maintenance 16B69-16.63 | Circuit Breaker, Line |  |  | Overload, Pre-Condition
ATCO | 854s 601T (854s Swan Dive) | 2021-06-07 08:00 | 2021-06-09 17:00 | N | N | perform 601T maintenance | Transformer |  | perform 601T maintenance, coordinated with a customer outage June 7-9th | For Information Only
ATCO | 9L30 (888s Dover - 951s Thickwood), 888s 910 (888s Dover), 888s 911 (888s Dover) | 2021-06-07 08:30 | 2021-06-15 12:00 | N | Y | switch replacements 9L30, breaker maintenance, PRC005 work | Line, Circuit Breaker |  | RTXP Switch Replacements 9L30, Breaker Maintenance on 910, 911, PRC005 work | 240 kV, For Information Only, Pre-Condition
ATCO | 813s 902T (813s Little Smoky) | 2021-06-07 11:00 | 2021-06-11 17:00 | N | Y | maintenance and CT ratio change | Transformer |  | 902T Main. and CT ratio change | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 392s T3 (392s Black Diamond), 812L (392s Black Diamond - 812AL tap) | 2021-06-07 11:30 | 2021-06-10 17:30 | N | N | fix leaks, change H1 bushing, get fall arrest plate welded on | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L80 (733s Simonette - 740s H.R.Milner) | 2021-06-07 12:00 | 2021-06-17 12:00 | N | Y | climbing and walk up inspection with insulator repairs | Line |  | Climbing and walk up inspection with insulator repairs | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 39.82L (ENMAX 39 - ENMAX 162) | 2021-06-07 23:00 | 2021-06-08 06:00 | N | N | high-load/house move | Line |  |  | Pre-Condition
ATCO | 787s 703C (787s High Prairie) | 2021-06-08 03:00 | 2021-06-11 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - ENMAX 162) | 2021-06-08 07:00 | 2021-06-12 16:00 | N | Y | work on 1325L OPGW over line, required for safety | Line | 918L (162s Beddington - 281s Johnson) |  | 240 kV, Affects Cranking Path
ALTALINK | 535s T3 (535s Joffre) | 2021-06-08 07:45 | 2021-06-10 17:45 | N | N | maintenance, doble, fix leaks | Transformer |  |  | For Information Only
ALTALINK | 320p Keephills 240kV Bus B, 1045AL (320p Keephills - 1045L tap), 320p T1 (320p Keephills), 320p 2152 (320p Keephills), 320p 752 (320p Keephills), 320p 352 (320p Keephills) | 2021-06-08 08:00 | 2021-06-09 18:30 | N | Y | new C60 breaker fail trip testing on breakers 320p1352, 320p352, 320p752, 320p215 | Bus, Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 31.1C (ENMAX 31), 31B138-31CAP (ENMAX 31) | 2021-06-08 08:00 | 2021-06-10 16:00 | N | N | HV maintenance and hot spots | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 244s T2 (244s Bowmanton) | 2021-06-08 08:30 | 2021-06-09 11:45 | N | Y | maintenance, doble | Transformer |  |  | 240 kV
ATCO | 715s 701T (715s Leming Lake) | 2021-06-08 09:00 | 2021-06-09 11:45 | N | N | oil leak mitigation, clean unit and tighten, install flange wraps. etc. | Transformer |  | 715S Leming Lake Oil Leak mitigation on 701T Transformer. Clean unit and tighten, install Flange wraps. Etc. | For Information Only
TRANSALTA | KH2 Keephills #2 Generator Test | 2021-06-08 09:30 | 2021-06-08 17:00 | N | N | AGC Tests | Unit
ALTALINK | 251s Whitla | 2021-06-08 10:00 | 2021-06-08 10:30 | N | N | communication outage | Station |  |  | Affects Visibility
ALTALINK | 74s 2152 (74s Janet), 925L (63s Red Deer - 74s Janet) | 2021-06-08 13:00 | 2021-06-10 17:30 | N | Y | replace breaker 74s2152 to SF6, replace risers from switch 21N to new breaker | Circuit Breaker, Line | 925L (63s Red Deer - 74s Janet) |  | 240 kV, Contingency Requires Mitigation
EPCOR | T2 (Woodcroft) | 2021-06-09 07:00 | 2021-06-10 17:00 | N | N | isolate TX2 to cutover and commission 15 kV bus overcurrent protection | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2021-06-09 07:00 | 2021-06-10 18:00 | N | N | replacement of 720L str. 40 for line clearance mitigation | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | EP 803s L2405 (EP 803s Lambton) | 2021-06-09 07:00 | 2021-06-09 14:45 | N | Y | breaker fail cutovers | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 646L (237s Foothills - 678s Okotoks) | 2021-06-09 07:15 | 2021-06-10 17:45 | N | N | structure maintenance | Line | 646L (237s Foothills - 678s Okotoks) | maintenance on structures 144, 149, 153, 158 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 310P Sundance RTU/SCADA | 2021-06-09 08:00 | 2021-06-10 16:00 | N | N | unplanned maintenance outage of the stations RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek) | 2021-06-09 08:00 | 2021-06-09 12:00 | N | N | open as part of 859L TPR replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 13B138-13.82 (ENMAX 13), 22B138-13.82 (ENMAX 22) | 2021-06-09 08:00 | 2021-06-11 16:00 | N | N | HV breaker maintenance 22B138-13.82 (HLR) and SF6 gas sample 13B138-13.82 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 785s 701T (785s Judy Creek Gas Plant) | 2021-06-09 08:00 | 2021-06-11 17:00 | N | N | transformer maintenance | Transformer |  | Transformer Maintenance coordinated with customer planned outage | For Information Only
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2021-06-10 07:15 | 2021-06-10 17:45 | N | Y | urgent repair | Line |  | URGENT REPAIR  On top phase sub-conductor saddle, the main support pin is half way out. Reinstall saddle pin and replace keeper keys. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK, EPCOR | 809L (320p Keephills - 510s Sunnybrook), 320p 809X (320p Keephills) | 2021-06-10 08:00 | 2021-06-10 11:30 | N | Y | new C60 breaker fail trip testing on breaker 1152 (320p809X) and commissioning 1152 BF trip to C60 | Line, Circuit Breaker |  | New C60 breaker fail trip testing on breaker 1152 (320p809X) and commissioning 1152 BF trip to C60. | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2021-06-10 08:00 | 2021-06-10 17:00 | N | N | change glass on deadend and compression dead-end | Line |  | GOI 802S-804S-change glass on dead-end and compression dead-end | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 320p 834X (320p Keephills), 834L (320p Keephills - 384s Keystone) | 2021-06-10 11:30 | 2021-06-10 14:30 | N | N | new C60 breaker fail trip testing on breaker 1252 (320p834X) and commissioning 1252 BF trip to C60 | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2021-06-11 07:15 | 2021-06-11 16:45 | N | Y | urgent repair to the broken conductor strands | Line |  | RGENT REPAIR  There are 4-5 broken strands on the top phase outside sub-bundle. Make repairs to broken conductor strands | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 320P Keephills | 2021-06-11 08:00 | 2021-06-11 11:00 | N | N | 320p 192 new C60 breaker fail trip testing on breaker 1952 (320p192) | Station |  |  | For Information Only
ATCO | 834s 502 (834s Wesley Creek), 834s 502R (834s Wesley Creek) | 2021-06-11 08:30 | 2021-06-11 15:30 | N | N | complete 502 maintenance and testing | Circuit Breaker, Shunts |  | Complete 502 maintenance and testing 502 & 502R OOS for the duration of the work | Pre-Condition
ALTALINK | 320P Keephills | 2021-06-11 11:00 | 2021-06-11 14:00 | N | N | 320P 191- new C60 breaker fail trip testing on breaker 1852 (320p191) | Station |  |  | For Information Only
ALTALINK | 320p 767N (320p Keephills), 767L (320p Keephills - 767AL tap) | 2021-06-11 13:30 | 2021-06-11 16:00 | N | N | new C60 breaker fail trip testing on breaker 1052 (320p767N) | Circuit Breaker, Line |  |  | Pre-Condition, Affects Cranking Path
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2021-06-13 08:00 | 2021-06-13 16:00 | N | N | Electrical contractor installing a conduit over wire | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 730L (285s East Camrose - 732L tap), 285s T1 (285s East Camrose) | 2021-06-14 06:00 | 2021-06-15 18:30 | N | N | insulator replacements on the 138kV north bus | Line, Transformer | 730L (285s East Camrose - 732L tap) | 285s 138kV North Bus & T1 (730L) - GOI Insulator replacements on the 138kV North bus | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 2029s ACF22 (2029s Heathfield) | 2021-06-14 07:00 | 2021-06-25 15:00 | N | Y | filter maintenance | Shunts | 2029s ACF22 (2029s Heathfield) | Perform PRC-005 tests on all devices associated with ACF22 and breaker 1223, Filter will be unavailable, One device worked on at a time 10BF22+SW1- 86, 94 relays 10R20+R22 - F602, F502 trench relay, 87, 86, 94 Diff Relay 10R02+R1- 86, 94 relays 1223 Trip Coils Filter Maintenance | 500 kV, Pre-Condition
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 665s D2404 (665s Dome), 665s T3 (665s Dome), 72DS26 (665s Dome - Strathcona) | 2021-06-14 07:00 | 2021-06-18 17:00 | N | Y | repair disconnect, switch adjustment and breaker rise repair | Line, Circuit Breaker, Transformer | 665s D2404 (665s Dome), 665s T3 (665s Dome), 909L (89s Ellerslie - 665s Dome) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
SUNCOR | 139s Hillridge RTU/SCADA | 2021-06-14 07:00 | 2021-06-14 07:15 | N | N | analog tags being added to the RTAC | Terminal Equipment |  | Enbridge Remote Operations Center will contact AESO/AltaLink 30 minutes prior to commencing. | Affects Visibility
EPCOR | T3 (Woodcroft) | 2021-06-14 07:00 | 2021-06-15 17:00 | N | N | cutover and commission 15KV bus overcurrent protection | Transformer | T3 (Woodcroft)
ALTALINK | 226s Garden City RTU/SCADA | 2021-06-14 07:00 | 2021-06-14 07:15 | N | N | analog tags being added to the RTAC | Terminal Equipment |  | Enbridge Remote Operations Center will contact AESO/AltaLink 30 minutes prior to commencing. | Affects Visibility
ALTALINK | 753L (65s High River - 253s Blackie) | 2021-06-14 07:15 | 2021-06-18 17:45 | N | N | insulator wash program | Line | 753L (65s High River - 253s Blackie) |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 431s T1 (431s Hussar) | 2021-06-14 08:00 | 2021-06-16 13:00 | N | N | complete T1 leak repair | Transformer | 431s T1 (431s Hussar) | Customer requested outage. AltaLink to complete T1 leak repair | For Information Only
ENMAX | 1.5TR (ENMAX 1) | 2021-06-14 08:00 | 2021-06-18 16:00 | N | N | power factor test transformer, maintenance, gas relay testing, oil sampling TC | Transformer | 1.5TR (ENMAX 1) | Power factor test transformer, Transformer Maintenance. Gas Relay Testing. Oil Sampling TC | For Information Only
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2021-06-14 08:00 | 2021-06-14 12:00 | N | Y | substation summer washing | Line | 833L (ENMAX 2 - ENMAX 12) |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 10.1TR (ENMAX 10) | 2021-06-14 08:00 | 2021-06-16 16:00 | N | N | neutral reactor install | Transformer |  | 10 Sub Neutral Reactor Install | For Information Only
ENMAX | 13.60L (ENMAX 13 - ENMAX 27) | 2021-06-14 08:00 | 2021-06-15 16:00 | N | N | breaker maintenance | Line | 13.60L (ENMAX 13 - ENMAX 27) | HV Breaker maintenance. 27B69-13.60 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.1TR (ENMAX 38) | 2021-06-14 08:00 | 2021-06-16 12:00 | N | N | CT replacement | Transformer | 38.1TR (ENMAX 38) | 38.1TR CT replacement | For Information Only
ATCO | 796s 701 (796s Nipisi), 7L61 (780s Lubicon - 796s Nipisi) | 2021-06-14 08:30 | 2021-06-15 16:30 | N | N | breaker 701 maintenance | Circuit Breaker, Line | 7L61 (780s Lubicon - 796s Nipisi) | Breaker 701 maintenance | Creates Radial Feeds, Firm Load Loss
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde) | 2021-06-14 09:30 | 2021-06-14 17:30 | N | N | 150s792X 1st trip & PRC5 maintenance | Line, Circuit Breaker | 792L (150s Clyde - 191s N.W. Cardiff) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2021-06-14 10:00 | 2021-06-17 17:00 | N | Y | arm and pole changes, sampling, climbing inspection | Line | 7L28 (717s Ethel Lake - 846s Grand Centre) | Arm Changes Pole Changes Sampling Inspection Sampling Climbing inspection | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 700s 702T (700s Bonnyville) | 2021-06-14 10:30 | 2021-06-17 16:00 | N | N | complete major maintenance, tap changer maintenance, tap changer filter | Transformer | 700s 702T (700s Bonnyville) | 700S 702T Complete major Maintenance, Tap changer maintenance, tap changer filter
ENMAX, ALTALINK | 12.1TR (ENMAX 12), 832L (ENMAX 10 - ENMAX 12) | 2021-06-14 12:00 | 2021-06-14 18:00 | N | Y | substation summer washing | Transformer, Line | 832L (ENMAX 10 - ENMAX 12) | 832L. 12.1TR. 12PT138-Z31 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 5.7TR (ENMAX 5) | 2021-06-14 12:00 | 2021-06-19 16:00 | N | N | 25 kV panel replacement | Transformer |  | 25 kV panel replacement. Network to switch out on June 14th, return to service June 20th. | For Information Only
ATCO | 786s 702T (786s High Level) | 2021-06-14 12:00 | 2021-06-19 17:00 | N | N | maintenance testing of 702T | Transformer | 786s 702T (786s High Level) | Maintenance Testing of 702T | For Information Only, Pre-Condition
ALTALINK | 885L (648s Metiskow - 650s Hansman Lake), 648s T1 (648s Metiskow) | 2021-06-14 12:00 | 2021-06-17 12:00 | N | N | replacement of 648s18 and PTs | Line, Transformer |  |  | Pre-Condition
ALTALINK | 63s 352 (63s Red Deer) | 2021-06-14 12:30 | 2021-06-17 17:30 | N | Y |  | Circuit Breaker | 63s 352 (63s Red Deer) |  | 240 kV, Contingency Requires Mitigation
ATCO | 914s 701 (914s Bindloss), 914s 701T (914s Bindloss) | 2021-06-15 07:00 | 2021-06-16 18:00 | N | N | 701T and 701 Tap changer repair | Circuit Breaker, Transformer | 914s 701T (914s Bindloss) | 701T and 701 Tap changer repair. Working with the customer to coordinate with there planned outage of June15/16 | For Information Only
ENMAXEC | 383S Kettles Hill Windfarm | 2021-06-15 07:00 | 2021-06-17 17:00 | N | Y | line maintenance on 616L | Station |  | line maintenance on 616L (89s-59s  383s) which would require a full station outage for 383s Both transformer units will be offline simultaneously | For Information Only, Restricts Generation
ALTALINK | 616L (59s Peigan - 103s Goose Lake) | 2021-06-15 07:15 | 2021-06-17 16:45 | N | Y | replace structure 56 and maintenance on structures 53 and 55 | Line | 616L (59s Peigan - 103s Goose Lake) |  | Pre-Condition, Restricts Generation
ENMAX | 35.2TR (ENMAX 35) | 2021-06-15 08:00 | 2021-06-15 10:00 | N | N | substation summer washing | Transformer | 35.2TR (ENMAX 35) |  | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2021-06-15 08:00 | 2021-06-21 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer |  | Tapchanger inspection. Check Reversing Switch. 13.1TR External CT ground shield wire routed incorrectly | For Information Only
ALTALINK | 199s C1 (199s East Ardrie), 199s 41 (199s East Airdrie) | 2021-06-15 08:30 | 2021-06-15 16:30 | N | N | gas leak repairs | Shunts, Circuit Breaker | 199s 41 (199s East Airdrie), 199s C1 (199s East Ardrie) |  | Pre-Condition
ALTALINK | 430s 901T (430s Ursus) | 2021-06-15 09:00 | 2021-06-15 11:00 | N | Y | customer requested to install PTs on their switchgear | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 430s 240kV Bus 1 (430s Ursus) | 2021-06-15 09:00 | 2021-06-15 11:00 | N | Y | facilitate the energization of equipment | Bus |  |  | 240 kV, For Information Only
ENMAX | 35.1TR (ENMAX 35) | 2021-06-15 10:00 | 2021-06-15 12:00 | N | N | substation summer washing | Transformer | 35.1TR (ENMAX 35) |  | For Information Only, Pre-Condition
ENMAX | 6.80L (ENMAX 6 - ENMAX 35) | 2021-06-15 12:00 | 2021-06-15 14:00 | N | N | substation summer washing | Line | 6.80L (ENMAX 6 - ENMAX 35) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L112 (888s Dover - 951s Thickwood), 888s 911 (888s Dover), 888s 912 (888s Dover) | 2021-06-15 12:05 | 2021-06-16 17:00 | N | Y | RTXP switch replacements 9L112, breaker maintenance on 912, PRC005 work | Line, Circuit Breaker | 9L112 (888s Dover - 951s Thickwood), 888s 911 (888s Dover), 888s 912 (888s Dover) | RTXP Switch Replacements 9L112, Breaker Maintenance on 912, PRC005 work | 240 kV
ALTALINK | 430s 240kV Bus 2 (430s Ursus) | 2021-06-15 13:00 | 2021-06-15 15:00 | N | Y | facilitate the energization of equipment | Bus |  |  | 240 kV, Pre-Condition
ALTALINK | 430s 902T (430s Ursus) | 2021-06-15 13:00 | 2021-06-15 15:00 | N | Y | customer requested to install PTs on their switchgear | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 35.81L (42s Sarcee - ENMAX 35) | 2021-06-15 14:00 | 2021-06-15 16:00 | N | Y | substation summer washing | Line | 35.81L (42s Sarcee - ENMAX 35) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.1TR (ENMAX 14) | 2021-06-15 14:00 | 2021-06-18 16:00 | N | N | neutral reactor install | Transformer |  | 14 Sub Neutral Reactor Install | For Information Only
ALTALINK | 285s T2 (285s East Camrose), 729L (285s East Camrose - 542s Ervick), 285s East Camrose 138kV South Bus | 2021-06-16 06:00 | 2021-06-18 18:30 | N | N | insulator replacements on 138kV south bus. | Transformer, Line, Bus | 729L (285s East Camrose - 542s Ervick) | Insulator replacements on the 138kV South bus. No affect on DG as 25kV bus will remain energized. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | AML 511s SVC Plus (AML 511s Crossings) | 2021-06-16 07:00 | 2021-06-16 16:30 | N | Y | fire system work | Shunts | 511s SVC Plus (511s Crossings) |  | 240 kV, Pre-Condition
ALTALINK | 523s T2 (523s Bullshead) | 2021-06-16 08:00 | 2021-06-17 15:30 | N | N | urgent repair,replace and test qualitrol temperature monitor | Transformer |  |  | For Information Only
ATCO | 2075s 904 (2075s Newell), 2075s 916 (2075s Newell), 2075s 919 (2075s Newell), 2075s 922 (2075s Newell), 2075s 900BS1 240kV bus ( 2075s Newell) | 2021-06-16 08:00 | 2021-06-16 15:30 | N | Y | breakers PRC-005 testing | Circuit Breaker, Bus | 2075s 900BS1 240kV bus ( 2075s Newell) | PRC-005 testing will be also conducted on all breakers on 900BS1 (904, 916, 919, & 922) Unable to properly block outputs, thus requesting breakers to be opened (900BS1 out of service during testing) | 240 kV, Contingency Requires Mitigation, Pre-Condition,Affects Cranking Path
ENMAX | 8B138-1A0 (ENMAX 8), 8B138-7A0 (ENMAX 8), 2B138-D81 (ENMAX 2), 2B138-D82 (ENMAX 2), 2.84L (ENMAX 2 - ENMAX 8) | 2021-06-16 08:00 | 2021-06-17 16:00 | N | N | 8 Sub I&R 7AO & 1AO tripped and 2.84L B protection failure | Circuit Breaker, Line | 2.84L (ENMAX 2 - ENMAX 8) |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 7.1TR (ENMAX 7) | 2021-06-16 08:00 | 2021-06-18 16:00 | N | N | cable trench replacement | Transformer |  | 7 sub cable trench replacement | For Information Only
ENMAX | 15B69-15.60 (ENMAX 15), 15.60L (ENMAX 15 - ENMAX 21) | 2021-06-16 08:00 | 2021-06-17 16:00 | N | N | breaker maintenance 15B69-15.60 | Circuit Breaker, Line | 15.60L (ENMAX 15 - ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 54.1TR (ENMAX 54), 41.84L (ENMAX 41 - ENMAX 54), 54.81L (ENMAX 54 - ENMAX 65) | 2021-06-16 08:00 | 2021-06-16 18:00 | N | N | substation summer washing | Transformer, Line | 41.84L (ENMAX 41 - ENMAX 54), 54.81L (ENMAX 54 - ENMAX 65) |  | For Information Only, Pre-Condition
ATCO | 888s 902 (888s Dover), 9L08 (849s Joslyn Creek - 888s Dover) | 2021-06-16 08:30 | 2021-06-18 17:00 | N | Y | replace RTXP switch and PRC005 work | Circuit Breaker, Line | 9L08 (849s Joslyn Creek - 888s Dover) | RTXP Switch Replacements 9L08, PRC005 work | 240 kV, Pre-Condition
ALTALINK | 291s 433 (291s Cochrane), 433L (291s Cochrane - AML 793s Horse Creek) | 2021-06-16 08:45 | 2021-06-16 16:45 | N | N | tank heater replacement | Circuit Breaker, Line | 433L (291s Cochrane - AML 793s Horse Creek) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2021-06-16 09:00 | 2021-06-16 12:00 | N | N | urgent repair damaged conductor | Line |  | Our field staff has found a damaged conductor between Structures 521 and 522 | Pre-Condition
ENMAX | 38.2TR (ENMAX 38) | 2021-06-16 12:00 | 2021-06-18 16:00 | N | N | CT replacement | Transformer | 38.2TR (ENMAX 38) | 38.2TR CT Replacement | For Information Only
ALTALINK | 431s T2 (431s Hussar) | 2021-06-16 13:01 | 2021-06-21 16:00 | N | N | complete T2 leak repair | Transformer | 431s T2 (431s Hussar) | Customer requested outage. AltaLink to complete T2 leak repair, maintenance, doble | For Information Only, Pre-Condition
GENL | WCD1 West Cadotte | 2021-06-17 00:01 | 2021-06-17 06:00 | N | N | emergency maintenance | Unit | periodic outages of 15 minutes during the window. This may result in reporting connection to AESO data centre dropping during this period. |  | Affects Visibility
ALTALINK | 426S Coalspur, 501L (302s Cardinal River - 501CL tap) | 2021-06-17 07:30 | 2021-06-17 16:30 | N | N | create open point E' on 501L and connect 474s mobile | Station, Line | Create Open Point E Between Str 3 and Str 4 on 501L and Connect 474s Mobile Low side cables to 501L at Str 2 Open Jumpers. |  | Creates Radial Feeds, Firm Load Loss, For Information Only
ALTALINK | 430s 901T (430s Ursus) | 2021-06-17 10:00 | 2021-06-17 11:30 | N | Y | customer requested to install PTs on their switchgear | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 730s 701T (730s Rycroft) | 2021-06-17 13:00 | 2021-07-12 09:00 | N | Y | transformer class 2 major testing | Transformer | 730s 701T (730s Rycroft) | 730S 701T TRANSFORMER CLASS2 MAJOR TESTING Leak severity, 701T main, 701TCS main Transformer out of service, load on 902S | For Information Only
ALTALINK | 430s 902T (430s Ursus) | 2021-06-17 15:00 | 2021-06-17 16:30 | N | Y | customer requested to install PTs on their switchgear | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 814s T1 (814s Bellamy), 72RV6 (EP 511s Victoria - Rossdale) | 2021-06-17 19:00 | 2021-06-17 21:00 | N | N | breaker energization | Transformer, Line | VHBB1 breaker energization after breaker replacement |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 191s 792X (191s NW Cardiff) | 2021-06-18 07:00 | 2021-06-21 18:00 | N | N | structure maintenance | Line, Circuit Breaker | 792L (92s Viscount - 191s N.W. Cardiff) | Maintenance on structures 64, 65, 67, 68, 69, 71, 112, 113, 114, 117, 118, 126, 171, 173, 174, 176, 177, 181, 183 and 184. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54), 41.1TR (ENMAX 41) | 2021-06-18 08:00 | 2021-06-18 12:00 | N | N | substation summer washing | Line, Transformer | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54) | 40.81L. 41.84L. 41.1TR. 41PT138-Z31. Substation Summer Washing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 426S Coalspur, 740L (426s Coalspur - 740L tap) | 2021-06-18 08:00 | 2021-08-27 08:00 | N | N | add new 426s740 138 kV breaker, maintenance | Station, Line |  | Add New 426s740 138kV breaker, new dead end and 426s1 switch Level existing TX pad and Re-install containment, Install new 3 phase 69kV PTs for 426s VT1 and relocate, Install new 69kV SS1 TX and reclocate to Bus, New 69kV Bypass switch 426s5 Replace 426s501W 69kV Breaker, Remove / Salvage VR1 Regulator, And T1 Maintenance Work. | For Information Only
ATCO | 732s 503R (732s Mitsue) | 2021-06-18 08:00 | 2021-06-18 17:00 | N | N | breaker maintenance | Shunts | 732s 503R (732s Mitsue) | 503 BKR Maintenance | Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), 16B69-15.62 (ENMAX 16) | 2021-06-18 08:00 | 2021-06-18 16:00 | N | N | power factor test 16B69-15.62 | Line, Circuit Breaker | 15.62L (ENMAX 15 - ENMAX 16) | Power factor test 16B69-15.62 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 6.82L (ENMAX 6 - ENMAX 41), 41.2TR (ENMAX 41), 41.1C (ENMAX 41) | 2021-06-18 12:00 | 2021-06-18 18:00 | N | N | substation summer washing | Line, Transformer, Shunts | 33.83L (ENMAX 33 - ENMAX 41), 6.82L (ENMAX 6 - ENMAX 41) | 33.83L. 6.82L. 41.2TR. 41.1CAP. 41PT138-Z32, Substation Summer Washing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 557s T2 (557s Castle Downs) | 2021-06-19 07:00 | 2021-06-20 17:00 | N | Y | tap changer maintenance | Transformer | 557s T2 (557s Castle Downs) | TX2 Tap Changer Maintenance and CD2404 Bay CT Doble | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 790s 703 (790s Poplar Hill), 7L07 (790s Poplar Hill - 815s Goodfare) | 2021-06-19 08:00 | 2021-06-19 17:00 | N | Y | removal of old panels | Circuit Breaker, Line | 7L07 (790s Poplar Hill - 815s Goodfare) | Move existing wiring that is run in-between panels to allow removal of old panels. Once wiring has been moved. Test logic to ensure functionality | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 28.2TR (ENMAX 28) | 2021-06-19 08:00 | 2021-06-19 16:00 | N | N | bleed gas from transformer main tank | Transformer | Bleed gas from transformer main tank. |  | For Information Only
VISIONREQ | 354S Summerview | 2021-06-19 08:00 | 2021-06-19 14:00 | N | Y | repair work at site | Station |  |  | Restricts Generation
ENMAX | 7.2TR (ENMAX 7) | 2021-06-20 08:00 | 2021-06-25 16:00 | N | N | 7 sub cable trench replacement | Transformer | 7.2TR (ENMAX 7) |  | For Information Only
VISIONREQ | 354S Summerview | 2021-06-20 08:00 | 2021-06-20 18:00 | N | Y | repair work at site | Station |  |  | Restricts Generation
ATCO | 790s 702 (790s Poplar Hill), 7L22 (790s Poplar Hill - 7L88 tap) | 2021-06-20 08:00 | 2021-06-20 17:00 | N | Y | removal of old panels | Circuit Breaker, Line | 7L22 (790s Poplar Hill - 7L88 tap) | Move existing wiring that is run in-between panels to allow removal of old panels. Once wiring has been moved. Test logic to ensure functionality | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 74s T2 (74s Janet) | 2021-06-20 11:00 | 2021-07-13 18:00 | N | Y | maintenance | Transformer | 74s T2 (74s Janet) | Corrosive sulphur in oil. Will require the oil reclaim reclamation to remove corrosive Sulphur content in the oil. | 240 kV, Contingency Requires Mitigation
VISIONREQ | 354S Summerview | 2021-06-21 07:00 | 2021-06-22 19:00 | N | N | maintneance | Station |  |  | Pre-Condition, Restricts Generation
EPCOR | 330p 1205 (330p Genesee) | 2021-06-21 07:00 | 2021-06-23 17:00 | N | Y | 1205 maintenance and CT Doble | Circuit Breaker | 330p 1205 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
EPCOR | EP 511s Victoria T5 (EP 511s Victoria) | 2021-06-21 07:00 | 2021-06-25 17:00 | N | Y | inspect oil leaks | Transformer | E511s Victoria T5 (511s Victoria) |  | 240 kV, For Information Only
EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton) | 2021-06-21 07:00 | 2021-06-22 17:00 | N | Y | cutover controls, status, alarms to new RTU | Line, Circuit Breaker | 1058L (657s Summerside - EP 803s Lambton) | cutover controls, status, alarms to new RTU at Summerside / breaker fail cutovers on L2403 | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ENMAX | 74s 2252 (74s Janet), 1003L (74s Janet - ENMAX 25) | 2021-06-21 07:30 | 2021-06-30 17:30 | N | Y | breaker replacement with SF6 breaker | Circuit Breaker, Line | 1003L (74s Janet - ENMAX 25) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 12B138-832L (ENMAX 12), 832L (ENMAX 10 - ENMAX 12) | 2021-06-21 08:00 | 2021-06-22 16:00 | N | Y | HV breaker maintenance 12B138-832L | Circuit Breaker, Line | 832L (ENMAX 10 - ENMAX 12) | HV Breaker maintenance 12B138-832L. Original outage date May 31- Jun 1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 35.1TR (ENMAX 35) | 2021-06-21 08:00 | 2021-07-02 16:15 | N | N | PF and secondary cable tests, check reverse switch, oil sampling, tap changer, transformer maintenance | Transformer | 35.1TR (ENMAX 35) | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Check reversing switch, Oil Sampling MT, TC | For Information Only
ENMAX | 32.1TR (ENMAX 32) | 2021-06-21 08:00 | 2021-06-22 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
EPCOR | 524s T1 (524s Owen Corning) | 2021-06-21 08:00 | 2021-06-21 12:00 | N | N | oil leak repair | Transformer | 524s T1 (524s Owen Corning) | TX1 Oil Leak Repair | For Information Only
ENMAX | 26.2TR (ENMAX 26) | 2021-06-21 08:00 | 2021-06-24 16:00 | N | N | testing and manitenance | Transformer | 26.2TR (ENMAX 26) | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil Sampling MT, TC. Check reversing switch. Secondary Cable Circulating Current Hazard | For Information Only
ENMAX | 12.2TR (ENMAX 12) | 2021-06-21 08:00 | 2021-07-01 16:00 | N | N | testing and maintenance | Transformer | 12.2TR (ENMAX 12) | HV Bushing Replacement. Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil Sampling MT, TC. 12.2TR Slip Over CT Corrective - Rerun ground shield ground wire | For Information Only
ATCO | 9L27 (755s Cordel - 863s Paintearth), 755s 902 (755s Cordel), 755s 903 (755s Cordel) | 2021-06-21 08:00 | 2021-07-09 17:00 | N | Y | protection upgrade to 9L27 and breakers 902/903; replace 903A, 9L27D1 and 903PT | Line, Circuit Breaker | 9L27 (755s Cordel - 863s Paintearth), 755s 903 (755s Cordel), 755s 902 (755s Cordel) | Protection upgrade to 9L27 and breakers 902/903, Replace 903A, 9L27D1 and 903PT. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 5B138-5BT12 (ENMAX 5) | 2021-06-21 08:00 | 2021-07-16 16:00 | N | N | 5sub TRV project | Circuit Breaker | 5B138-5BT12 (ENMAX 5) | 5sub TRV Project. Replace circuit breaker | For Information Only
Syncrude | Mildred C1 (Syncrude Mildred Lake) | 2021-06-21 08:00 | 2021-06-23 20:00 | N | N | maintenance | Shunts |  |  | For Information Only
ATCO | 732s 902T (732s Mitsue), 732s 503R (732s Mitsue) | 2021-06-21 08:00 | 2021-06-24 16:30 | N | Y | 902T leak mitigation and PM | Transformer, Shunts | 732s 902T (732s Mitsue) | 902T leak mitigation and PM | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 933s 701T (933s Tower Road), 933s 701 (933s Tower Road) | 2021-06-21 08:30 | 2021-06-25 16:20 | N | N | 701T leak mitigation and transformer PM | Transformer, Circuit Breaker | 933s 701T (933s Tower Road) | 701T leak mitigation and transformer PM | For Information Only
ALTALINK | 74s C2 (74s Janet), 74s C1 (74s Janet) | 2021-06-21 08:30 | 2021-06-22 14:30 | N | N | investigate cap bank neutral grounding | Shunts | 74s C1 (74s Janet), 74s C2 (74s Janet) | Investigate Cap bank neutral grounding | For Information Only, Pre-Condition
ALTALINK | 996S Imperial Oil Carson Lake, 996s T1 (996s Imperial Oil Carson Lake) | 2021-06-21 09:00 | 2021-06-24 18:00 | N | N | metering upgrade | Station, Transformer | 996s T1 (996s Imperial Oil Carson Lake) | Metering upgrade. Replace 2.4kV PTs and CTs and 996s8. T1: replace bushings, maintain, doble, SFRA. replace pin cap insulators on 69kV bus, bus work extension plates, fix low gas alarm on 996s519 | For Information Only
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2021-06-21 10:00 | 2021-06-25 17:00 | N | Y | arm change, pole changes and sampling inspection | Line | 7L28 (717s Ethel Lake - 846s Grand Centre) | Arm Change pole Changes Sampling Inspection | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 624L (312s Fidler - 354s Summerview) | 2021-06-21 10:00 | 2021-06-21 15:00 | N | Y | maintenance | Line | 624L (312s Fidler - 354s Summerview) |  | Restricts Generation
ATCO | 837s 704 (837s Mahihkan), 837s 701T (837s Mahihkan) | 2021-06-21 11:00 | 2021-06-25 12:00 | N | N | 701T and breaker 704 maintenance including relay testing on 704 50BF relay | Circuit Breaker, Transformer | 837s 704 (837s Mahihkan), 837s 701T (837s Mahihkan) | 837S Mahihkan Complete 701T Maintenance, 704 Breaker Maintenance, Complete Relay testing on 704 50BF Relay. | For Information Only
ATCO | 7L80 (733s Simonette - 740s H.R.Milner) | 2021-06-21 12:00 | 2021-06-23 20:30 | N | Y | climbing and walk up inspection with insulator repairs | Line | 7L80 (733s Simonette - 740s H.R.Milner) | Climbing and walk up inspection with insulator repairs | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 602s T2 (602s Cold Creek) | 2021-06-21 12:00 | 2021-06-24 18:00 | N | N | maintenance | Transformer | 602s T2 (602s Cold Creek) | replace 602s16, maintain 2077N & 2070N, T2: doble, install LA stand offs, fix leaks, replace bird cover. | For Information Only
ALTALINK | 320p 1352 (320p Keephills), 1045AL (320p Keephills - 1045L tap) | 2021-06-21 12:30 | 2021-06-30 18:00 | N | N | replacing 1352 breaker control and breaker fail relays with new C60 module | Circuit Breaker, Line | 1045AL (320p Keephills - 1045L tap) | Replacing 1352 breaker control and breaker fail relays with new C60 module. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 650s T1 (650s Hansman Lake) | 2021-06-21 13:30 | 2021-06-24 16:00 | N | Y | fix leaks, maintenance, doble on T1, 650s70 maintenance | Transformer | 650s T1 (650s Hansman Lake) | Fix leaks, maintenance, doble on T1. 650s70 maintenance | 240 kV, Pre-Condition
AESO-SC | OATI | 2021-06-21 19:30 | 2021-06-21 20:30 | N | N | performing an infrastructure enhancement of a new storage area network | SCInternal |  | performing an infrastructure enhancement of a new storage area network | For Information Only
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2021-06-22 07:00 | 2021-06-22 18:00 | N | N | structure maintenance | Line | 792L (150s Clyde - 191s N.W. Cardiff) | 792L (150s - 191s) - GOI Maintenance on structures 194, 195 and 196. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 767L (310p Sundance - 767AL tap) | 2021-06-22 07:00 | 2021-06-24 18:00 | N | N |  | Line | 767L (320p Keephills - 767AL tap) | 767L (310p - 767L50) - GOI Line clearance mitigation on Structures #767L27 & 767L41 | Pre-Condition, Affects Cranking Path
ALTALINK | 396s 56 (396s Pincher Creek), 396s C1 (396s Pincher Creek) | 2021-06-22 09:15 | 2021-06-23 16:45 | N | N | 1st trip & maintenance | Circuit Breaker, Shunts | 396s C1 (396s Pincher Creek), 396s 56 (396s Pincher Creek) |  | For Information Only, Pre-Condition
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood) | 2021-06-22 12:00 | 2021-06-22 18:00 | N | N | open 694L breakers for 422s MPLS upgrade | Line | 694L (54s Fort Saskatchewan - 422s Westwood) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2021-06-22 18:00 | 2021-06-22 19:00 | N | N | performing an inter-site transfer business continuity drill | SCInternal |  | perform an Inter-Site Transfer business continuity drill | For Information Only
ENMAX | 38B138-38.1CAP (ENMAX 38) | 2021-06-23 08:00 | 2021-06-23 16:00 | N | N | HV breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 38B138-38.1CAP | Pre-Condition
SUNCOR | 29PT-101 (29EDD-18) | 2021-06-23 08:00 | 2021-06-23 18:00 | N | N | install IR windows on 29PT-101 | Transformer |  | INSTALL IR WINDOWS ON 29PT-101 | For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2021-06-23 08:00 | 2021-06-24 16:00 | N | N | tapchanger inspection, check reversing switch, transformer maintenance, gas relay testing | Transformer | 8.5TR (ENMAX 8) | Tapchanger inspection. Check Reversing Switch. Transformer Maintenance . Gas Relay Testing | For Information Only
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 38s 737N (38s East Edmonton) | 2021-06-23 08:30 | 2021-06-23 19:30 | N | N | replace insulators on switch 38s38 | Line, Circuit Breaker | 737L (38s East Edmonton - 95s Imperial Oil Edmonton) | Job Scope: Replace insulators on switch 38s38. Maintenance on 38s38 to repair hot spot. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | WHT1 Whitla | 2021-06-23 14:00 | 2021-06-23 16:30 | N | N | communication only outage | Unit |  |  | For Information Only
ALPAC | 282s Grassland (Alpac) RTU/SCADA | 2021-06-24 00:01 | 2021-06-24 06:00 | N | N | SCADA and Phone outage | Terminal Equipment |  |  | For Information Only
ALTALINK | 1148L (251s Whitla - 1018s Shamrock) | 2021-06-24 07:00 | 2021-06-25 12:00 | N | N | customer requested outage for phase II expansion (P1800) | Line |  |  | 240 kV, Restricts Generation
EPCOR | 330P 12TC2 (330p Genesee), 330p 500kV Bus 2 (330p Genesee) | 2021-06-24 07:00 | 2021-06-25 17:00 | N | Y | switch maintenance | Transformer, Bus | 330P 12TC2 (330p Genesee), 330p Genesee 500 kV Bus 2 | 1203A/1206A/1209B/12TC2D Switch Maintenance | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 251s SR2 (251s Whitla) | 2021-06-24 08:00 | 2021-06-25 11:00 | N | Y | urgent repair; replace/test qualitrol temperature monitor | Shunts | 251s SR2 (251s Whitla) | Urgent Repair; replace/test Qualitrol temperature monitor | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 21B138-20.82 (ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21) | 2021-06-24 08:00 | 2021-06-24 16:00 | N | N | sample SF6 gas 21B138-20.82 | Circuit Breaker, Line | 20.82L (ENMAX 20 - ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 103s 652 (103s Goose Lake) | 2021-06-24 08:30 | 2021-06-24 16:30 | N | Y | top up SF6 gas | Circuit Breaker | 103s 652 (103s Goose Lake) |  | 240 kV, Contingency Requires Mitigation
ATCO | 9L28 (937s AMR02 - 960s Birchwood Creek), 937s 06-DS-89T2 (937s Amr02) | 2021-06-24 08:30 | 2021-06-27 08:00 | N | Y | complete the maintenance on their disconnect switches | Line, Switch |  | Petro China Canada have scheduled to have GE come to site to complete the maintenance on their disconnect switches | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | 72NW15 (Namao - Woodcroft) | 2021-06-25 07:00 | 2021-07-12 17:00 | N | N | line maintenance and upgrades | Line | 72NW15 (Namao - Woodcroft) | Line Maintenance & Upgrades, Woodcroft Zone PT Doble | Creates Radial Feeds, Firm Load Loss
EPCOR | 330p 806 (330p Genesee) | 2021-06-25 07:00 | 2021-06-25 17:00 | N | N | repair CT leak | Circuit Breaker | 330p 806 (330p Genesee) |  | Pre-Condition
ALTALINK | 702L (137s Sedgewick - 377s Hardisty) | 2021-06-25 07:00 | 2021-06-25 18:00 | N | Y | urgent repair on structure 370 to replace the arms and insulation | Line |  |  | Restricts Generation
ALTALINK | 310p RTU/SCADA (310p Sundance) | 2021-06-25 08:00 | 2021-06-26 16:00 | N | N | RTU maintenance | Terminal Equipment |  | unplanned maintenance outage of the stations RTU | Affects Visibility
Syncrude | Mildred C2 (Syncrude Mildred Lake) | 2021-06-25 08:00 | 2021-06-27 20:00 | N | N | maintenance | Shunts |  |  | For Information Only
CAPPOWERLP | ENC1 Cloverbar #1, ENC2 Cloverbar #2, ENC3 Cloverbar #3 | 2021-06-26 13:00 | 2021-06-26 21:00 | N | N | communications only outage to update firewall, affecting site internet and VOIP phones | Unit |  | Communications only outage to update firewall, affecting site internet and VOIP phones | For Information Only
ALTALINK | 434s T1 (434s East Stony Plain) | 2021-06-27 08:00 | 2021-06-30 16:00 | N | N | replace 434s36W power cables to Fortis equipment | Transformer | 434s T1 (434s East Stony Plain) |  | For Information Only
ATCO | 9L19 (937s AMR02 - 960s Birchwood Creek), 937s 06-DS-89T1 (937s Amr02) | 2021-06-27 09:30 | 2021-06-29 16:00 | N | Y | complete the maintenance on their disconnect switches | Line, Switch |  | Petro China Canada have scheduled to have GE come to site to complete the maintenance on their disconnect switches | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | G724 (Garneau) | 2021-06-28 07:00 | 2021-06-30 11:00 | N | N | 72 kV BF upgrade cutovers | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 2029s ACF21 (2029s Heathfield) | 2021-06-28 07:00 | 2021-06-30 08:15 | N | N | perform PRC005 tests on all devices associated with ACF21 | Shunts |  | Perform PRC005 tests on all devices associated with ACF21, Filter will be unavailable, One device worked on at a time. No effect to Transfer capabilities | 500 kV, Pre-Condition
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2021-06-28 08:00 | 2021-06-30 17:00 | N | N | change 6L12D2-arm insulators | Line | 6L12 (775s Sullivan Lake - 6L25 tap) | 6L12 GOI 775S-6L12D1 to 6L12D2-Arm Insulator Change | For Information Only, Pre-Condition
ATCO | 809s 705 (809s Louise Creek), 7L55 (743s Sarah Lake - 809s Louise Creek) | 2021-06-28 08:00 | 2021-07-12 17:00 | N | N | replace breaker 705 Louise Creek rebuild project | Circuit Breaker, Line | 7L55 (743s Sarah Lake - 809s Louise Creek) | Louise Creek Rebuild project Replace breaker 705. Complete wiring for 21A and 21B relays. CT ratio changes Relay programming. Commission control, alarms and status. Blocking procedures for BF and Bus protections. | For Information Only, Pre-Condition
SUNCOR, ATCO | 29EDD-1 29EDD1s1352 (29EDD-1 Millennium), 29EDD-1 29EDD1s1252 (29EDD-1 Millennium), 737s 601T (737s Horseshoe), 737s 602T (737s Horseshoe), 6L32 (29EDD-1 Millennium - 737s Horseshoe) | 2021-06-28 08:00 | 2021-07-06 18:00 | N | N | 29EDD - 1 - 10 year PM on breakers and 29CVT-6 system 5y/10y | Circuit Breaker, Transformer, Line | 29EDD-1 29EDD1s1352 (29EDD-1 Millennium) |  | Contingency Requires Mitigation
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2021-06-28 08:00 | 2021-07-02 13:45 | N | Y | maintenance | Transformer |  | Syncrude Non-Significant Outage: T6 Transformer (72/13.8kV) @ Plant 31 Substation Following Breakers will be operated: 635 (Plant 31 Substation) 6335 (Plant 31 Subsstation) | Restricts Generation
ATCO | 739s 601 (739s Edith Lake), 739s 701T (739s Edith Lake) | 2021-06-28 08:00 | 2021-07-02 16:00 | N | N | 701T maintenance and leak mitigation and 601 breaker maintenance | Circuit Breaker, Transformer | 739s 701T (739s Edith Lake) | 701T maintenance and leak mitigation. 601 Breaker maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 63s 452 (63s Red Deer) | 2021-06-28 10:30 | 2021-06-30 17:30 | N | Y | repair leaks and top up oil and maintain PRC5 | Circuit Breaker | 63s 452 (63s Red Deer) | 356sPerform 1st trip then repair leaks and top up oil and maintain PRC5. | 240 kV, Contingency Requires Mitigation
ALTALINK | 28s 240kV Bus 2 (28s West Brooks), 28s T2 (28s West Brooks) | 2021-06-28 11:15 | 2021-06-29 17:45 | N | Y | install corona mitigation fittings | Bus, Transformer | 28s 240kV Bus 2 (28s West Brooks) | Install corona mitigation fittings on the 240kV bus ends to reduce discharge noise. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 5.8TR (ENMAX 5) | 2021-06-28 12:00 | 2021-07-08 12:00 | N | N | 25kV panel replacement | Transformer |  |  | For Information Only
ALTALINK | 320p 352 (320p Keephills) | 2021-06-28 12:30 | 2021-06-29 12:00 | N | Y | fix indicator cover, clean up rusty JB | Circuit Breaker | 320p 352 (320p Keephills) | 1st trip and PRC5 maintenance, fix indicator cover, clean up rusty JB | 240 kV, For Information Only
AESO-SC | OATI | 2021-06-28 19:30 | 2021-06-28 20:30 | N | N | upgrading one of storage area network | SCInternal |  | performing an infrastructure enhancement of a new storage area network | For Information Only
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2021-06-29 07:00 | 2021-06-29 18:00 | N | N | urgent outage to repair x-arm on structure | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-06-29 07:30 | 2021-06-30 07:30 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTAGAS | Lethbridge Taber (ME02) | 2021-06-29 07:30 | 2021-06-29 18:00 | N | N | AltaLink 25 kV bus outage at 83s | Unit
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-06-29 08:00 | 2021-06-29 18:00 | Y | Y | AltaLink/BCH PN test | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 813s SVC (813s Little Smoky) | 2021-06-29 08:00 | 2021-07-03 16:00 | N | Y | forced outage (not designed for high temperature) | Shunts |  |  | Pre-Condition
ALTALINK | 320p 240kV Bus B (320p Keephills), 320p T1 (320p Keephills) | 2021-06-29 08:00 | 2021-06-30 18:30 | N | Y | new C60 breaker fail trip testing on breakers, commissioning breaker and T1 protections | Bus, Transformer | 320p Keephills 240kV Bus B |  | 240 kV, Pre-Condition
ALTALINK | 65s T2 (65s High River) | 2021-06-29 08:30 | 2021-06-29 17:00 | N | N | replace LTC controller | Transformer |  |  | For Information Only
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2021-06-29 12:00 | 2021-06-29 18:00 | N | N | open breakers on 700L for 746s MPLS upgrade | Line | 700L (422s Westwood - 746s Sherwood Park) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 636L (420s Broadmoor - 746s Sherwood Park) | 2021-06-30 07:00 | 2021-06-30 18:00 | N | N | urgent repair on structure 10 to repair OHSW | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 68S Willesden Green | 2021-06-30 09:00 | 2021-06-30 17:00 | N | N | 68s relays -tech's to investigate breaker152/252 and IED trouble alarms | Station |  | ACC P5 Trouble - Tech to investigate Breaker152/252 Trouble alarms and IED Trouble Alarms coming from T1 A Prot. 68s T1 A protection to be taken out of service. Redundant B protection to remain in service for duration of outage | For Information Only
EPCOR | G723 (Garneau) | 2021-06-30 11:30 | 2021-07-02 17:00 | N | N | 72 kV BF upgrade cutovers | Circuit Breaker |  | 72 kV BF upgrade cutovers | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 28s 240kV Bus 1 (28s West Brooks), 28s T1 (28s West Brooks), 28s R1 (28s West Brooks) | 2021-07-01 07:15 | 2021-07-01 16:00 | N | Y | install corona mitigation fittings | Bus, Transformer, Shunts | 28s 240kV Bus 1 (28s West Brooks) | install corona mitigation fittings on the 240kV bus ends to reduce discharge noise Changed record from continuous to daily based on conversation with SC (2021 Jun 30) | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2021-07-02 03:45 | 2021-07-05 18:30 | N | Y | forced outage due to damaged conductor | Line | 906L (17s Benalto - 42s Sarcee) |  | 240 kV
SUNCOR | 635EDD-1000 635-752-142 (635EDD-1000), 635PT-1003 (635EDD-1000), 635EDD-1000 635-752-143 (635EDD-1000) | 2021-07-02 08:00 | 2021-07-13 17:00 | N | N | 144kV main sub 635EDD-1000 Dia 4 equipment outage | Circuit Breaker, Transformer |  |  | For Information Only
ATCO, ALTALINK | 840S McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2021-07-03 10:45 | 2021-07-23 13:55 | Y | Y | forced outage | Station, Line |  | forced outage due to glycol leak | Limits ATC
ATCO | 930s Syn Condenser (930s Arcenciel) | 2021-07-04 03:35 | 2021-07-05 18:38 | N | Y | forced outage | Shunts |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2021-07-04 08:00 | 2021-07-11 16:00 | N | N | 6 sub cable trench replacement | Transformer |  |  | For Information Only
EPCOR | EP 803s T3 (EP 803s Lambton), 72LH8 (EP 803s Lambton - EPCOR Hardisty), 72LS24 (EP 803s Lambton - Strathcona) | 2021-07-05 07:00 | 2021-07-09 17:00 | N | Y | isolate Lambton TX3 bay, 72LH8, 72LS24 for breaker fail cutovers and op checks | Transformer, Line | 72LH8 (EP 803s Lambton - EPCOR Hardisty), 72LS24 (EP 803s Lambton - Strathcona) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72KN23 (Kennedale - Namao) | 2021-07-05 07:00 | 2021-07-07 17:00 | N | N | metering upgrades | Line |  |  | For Information Only, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EPCOR Hardisty), T2 (EPCOR Hardisty) | 2021-07-05 07:00 | 2021-07-12 17:00 | N | N | Hardisty TX2 replacement - 1007220 | Line, Transformer | 72LH8 (EP 803s Lambton - EPCOR Hardisty), T2 (EPCOR Hardisty) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | G721 (Garneau) | 2021-07-05 07:00 | 2021-07-07 11:00 | N | N | 72 kV BF upgrade cutovers | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 52s T1 (52s East Industrial) | 2021-07-05 07:00 | 2021-07-09 17:00 | N | Y | isolate TX1 to relocate revenue metering and transformer controls | Transformer | 52s T1 (52s East Industrial) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 391s T1 (391s Balzac) | 2021-07-05 07:15 | 2021-07-06 15:45 | N | N | install bird mitigation to 25 kV bus portions | Transformer | 391s T1 (391s Balzac) | SOW is Install bird mitigation to 25kv bus portions. | For Information Only
ATCO | 2075s 917 (2075s Newell), 2075s 918 (2075s Newell), 2075s ACF14 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s SVC1 (2075s Newell) | 2021-07-05 08:00 | 2021-07-30 17:30 | N | Y | cooling system maintenance | Circuit Breaker, Shunts | 2075s SVC1 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell), 2075s 918 (2075s Newell), 2075s 917 (2075s Newell) | Cooling system maintenance, LOPs | 240 kV
ENMAX | 15B69-15.62 (ENMAX 15), 15.62L (ENMAX 15 - ENMAX 16) | 2021-07-05 08:00 | 2021-07-06 16:00 | N | N | HV breaker maintenance 15B69-15.62 | Circuit Breaker, Line | 15.62L (ENMAX 15 - ENMAX 16) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2021-07-05 08:00 | 2021-07-06 17:00 | N | N | 6L12D3 to 6L12D4-arm insulator change | Line |  | 6L12 GOI 6L12D3 to 6L12D4-Arm Insulator Change | Pre-Condition
ENMAX | 21.2TR (ENMAX 21) | 2021-07-05 08:00 | 2021-07-08 16:00 | N | N | power factor test transformer | Transformer |  | ECI buhings. Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil sampling MT, TC | For Information Only
EPCOR | 72RV2 (EP 511s Victoria - Rossdale) | 2021-07-05 08:00 | 2021-07-10 17:00 | N | N | repair of RV2 pothead | Line | 72RV2 (511s Victoria - Rossdale) |  | For Information Only
ATCO | 813s 503R (813s Little Smoky) | 2021-07-05 09:25 | 2021-07-06 14:30 | N | N | forced | Shunts |  |  | For Information Only
ATCO | 885s 704 (885s McMillan), 885s 501R (885s McMillan), 885s 902T (885s McMillan), 7L02 (860s Crow - 885s McMillan) | 2021-07-05 09:30 | 2021-07-08 16:00 | N | Y | 7L02, 902T RTXP replacements and 704 breaker maintenance | Circuit Breaker, Shunts, Transformer, Line | 7L02 (860s Crow - 885s McMillan) | 7L02, 902T, RTXP replacements 704 Breaker Maintenance | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 283s T1 (283s Violet Grove) | 2021-07-05 09:30 | 2021-07-08 18:00 | N | N | T1 'A' protection upgrade and trip testing | Transformer | 283s T1 (283s Violet Grove) | T1 'A' protection upgrade and trip testing | For Information Only
ALTALINK | 928L (17s Benalto - 42s Sarcee), 42s 928N (42s Sarcee) | 2021-07-05 09:30 | 2021-07-07 16:30 | N | Y | migrate and commission new RTU and LAN | Line, Circuit Breaker | 928L (17s Benalto - 42s Sarcee) | Migrate and commission all 42s928N & L1-928L at 42s Sarcee associated line protections, recloser, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | 240 kV, Affects Visibility, Pre-Condition
ATCO | 809s 901T (809s Louise Creek), 809s 503R (809s Louise Creek), 809s 504R (809s Louise Creek) | 2021-07-05 10:00 | 2021-07-13 17:00 | N | Y | modifications to 901T - Louise Creek rebuild project- | Transformer, Shunts | May need to split the record closer to outage | Louise Creek Rebuild project- Replace 912, 900PT1, CT modifications to 906CT, 912CT, and 901T July 5-13  Isolation Points: 809S 901TD, 809S 701B, 809S 201TD, 809S 500D1  809S 901T OOS 809S 911 Breaker will be in-operable at the end of this outage and will be included on the following GOI for 809S 902T on August 23 2-50617. | 240 kV, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2021-07-05 10:00 | 2021-07-08 15:00 | N | Y | crossarm changing | Line | 1. OC had issues with running VSAT using the daily PSSE case for June 5. VSAT is showing unsolved (we've tried changing parameters and disconnecting system from WECC but still couldn't get the case to solve). 2. OC did a quick studies in PSSE by adjusting the load in GP area and it was found that the current Vlim3 is still valid and that the most restrictive limit is the thermal concern. Thermal concern will be reached before any voltage stability limit is reached. | Crossarm changing | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 19s T10 (19s Wabamun) | 2021-07-05 10:00 | 2021-07-13 17:00 | N | Y | replacing high/load side bushings and transformer maintenance | Transformer |  | Replacing high/load side bushings and transformer mtce. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 837s 705 (837s Mahihkan), 837s 702T (837s Mahihkan) | 2021-07-05 11:00 | 2021-07-09 12:00 | N | N | complete 702T maintenance, complete Relay testing on 705 50BF relay | Circuit Breaker, Transformer | 837s 702T (837s Mahihkan), 837s 705 (837s Mahihkan) | 837S Mahihkan Complete 702T Maintenance, 705 Breaker Maintenance, Complete Relay testing on 705 50BF Relay. | For Information Only
ATCO | 7L80 (733s Simonette - 740s H.R. Milner) | 2021-07-05 12:00 | 2021-07-11 17:00 | N | Y | climbing and walk up inspection with insulator repairs | Line | 7L80 (733s Simonette - 740s H.R.Milner) | Climbing and walk up inspection with insulator repairs | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 199L (347s Fox Creek - 199AL tap) | 2021-07-05 12:00 | 2021-07-23 18:00 | N | N | component replacements 199L ( str's range 13-178) | Line | 199L (347s Fox Creek - 199AL tap) | Component Replacements 199L ( Str's Range 13-178). Temporary settings to be implemented to keep IPP @ 259s online. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 749L (648s Metiskow - 749AL tap) | 2021-07-06 07:00 | 2021-07-07 18:00 | N | N | urgent repairs on structures #Str. 12, 44, 60, 107 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | TL-1 (Aurora - Aurora) | 2021-07-06 08:00 | 2021-07-06 20:00 | N | N | TL1 72kV transmission line @ G01 maintenance | Line |  |  | For Information Only
ATCO, SUNCOR | 6L32 (29EDD-1 Millennium - 737s Horseshoe) | 2021-07-06 08:00 | 2021-07-07 18:00 | N | N | PL6-32 29EDD-20 | Line |  |  | For Information Only
ALTALINK | 283s 31 (283s Violet Grove), 283s C1 (283s Violet Grove) | 2021-07-06 08:30 | 2021-07-06 17:30 | N | N | urgent replacement of 283s31 CT15 | Circuit Breaker, Shunts |  |  | For Information Only
BCH | 2L294 (A.A. Lambert - Nelway) | 2021-07-06 09:00 | 2021-07-09 17:00 | N | Y | insulator replacement | Line | 2L294 (Nelway - A.A. Lambert) |  | Limits ATC, Pre-Condition
ALTALINK, Lethbridge | 618s 824 (618s Riverbend), 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2021-07-06 09:15 | 2021-07-07 16:45 | N | Y | 1st trip & maintenance (PRC5) | Circuit Breaker, Line | 824L (593s Lethbridge Lakeview - 618s Riverbend), 618s 824 (618s Riverbend) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 368s T2 (368s Burdett) | 2021-07-06 09:45 | 2021-07-06 17:15 | N | N | replace and test 368s T2 LTC voltage regulator control | Transformer |  |  | For Information Only
CAPPOWERLP | ENC1 Cloverbar #1, ENC2 Cloverbar #2, ENC3 Cloverbar #3 | 2021-07-06 14:30 | 2021-07-06 16:30 | N | N | communications only outage to update firewall, affecting site internet and VOIP phones | Unit |  | Communications only outage to update Wiband network install which will cause intermittent disruptions to VOIP phones. | For Information Only
EPCOR | 330P 12TC2 (330p Genesee), 330p 809 (330p Genesee) | 2021-07-07 07:00 | 2021-07-16 17:00 | N | Y | emergency bushing investigation | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 391s T2 (391s Balzac) | 2021-07-07 07:30 | 2021-07-08 15:30 | N | N | Install bird mitigation | Transformer | 391s T2 (391s Balzac) | SOW is Install bird mitigation to 25kv bus portions. | For Information Only
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2021-07-07 07:45 | 2021-07-07 12:15 | N | Y | 9202R MPLS upgrade | Line | Open as part of 9202R MPLS upgrade. 887L must be open during reroute due to RAS being OOS. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 25B240-D141 (ENMAX 25) | 2021-07-07 08:00 | 2021-07-07 16:00 | N | Y | breaker maintenance | Circuit Breaker | 25B240-D141 (ENMAX 25) | HV breaker maintenance 25B240-D141 | 240 kV, For Information Only
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2021-07-07 08:00 | 2021-07-09 17:00 | N | N | crossarm and insulator change | Line |  | Crossarm & Insulator Change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek) | 2021-07-07 08:30 | 2021-07-07 17:30 | N | N | 308s T1 calibrations | Transformer | SFRA and leakage reactance and temperature gauge checks/calibrations |  | For Information Only
EPCOR | G722 (Garneau) | 2021-07-07 13:00 | 2021-07-09 17:00 | N | N | 72 kV BF upgrade cutovers | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 847L (602s Cold Creek - 847AL tap) | 2021-07-08 07:00 | 2021-07-13 18:00 | N | Y | replace 847L Str 291 and 297 for line clearance mitigation | Line | 847L (602s Cold Creek - 847AL tap) | Replace 847L Str 291 and 297 for line clearance mitigation. Repair wood pecker hole on 847L Str 277. Repair downlead on 847L Str 275. | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 25B240-D136 (ENMAX 25) | 2021-07-08 08:00 | 2021-07-08 16:00 | N | Y | breaker maintenance | Circuit Breaker | 25B240-D136 (ENMAX 25) | HV Breaker maintenance 25B240-D136 | 240 kV
ALTALINK | 719L (263s Strachan - 719AL tap) | 2021-07-08 08:00 | 2021-07-08 16:00 | N | N | forced outage due to burnt crossarm | Line
ATCO | 803s 701T (803s Bullpound), 7L85 (801s Anderson - 803s Bullpound) | 2021-07-08 08:30 | 2021-07-14 17:30 | N | N | transformer and circuit switcher maintenance | Transformer, Line |  | Transformer and Circuit switcher Maintenance Mobile Sub will be in service to carry load, no outage to customer expected | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 283s T2 (283s Violet Grove) | 2021-07-09 07:00 | 2021-07-09 18:00 | N | N | T1 'B' protection upgrade and trip testing | Transformer | 283s T2 (283s Violet Grove) |  | For Information Only
ALTALINK | 744L (228s T.M.P.L.Niton - 744AL tap) | 2021-07-09 07:00 | 2021-07-09 18:00 | N | N | urgent repair due to possible lightning damage on Structure #215 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 719L (256s Harmattan - 719CL tap) | 2021-07-09 07:15 | 2021-07-11 17:45 | N | Y | maintenance work (Strs 4 ~ 72) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 25B240-D133 (ENMAX 25) | 2021-07-09 08:00 | 2021-07-09 16:00 | N | Y | breaker maintenance | Circuit Breaker | 25B240-D133 (ENMAX 25) | HV Breaker maintenance 25B240-D133 | 240 kV
ALTALINK | 749L (899s Edgerton - 7LB749 tap) | 2021-07-10 07:00 | 2021-07-14 18:00 | N | Y | urgent repairs on structures #str. 323, 329, 341, 434, 435, 454, 457 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 13L (65s High River - 392s Black Diamond) | 2021-07-10 07:15 | 2021-07-13 17:45 | N | N | replacing structures 121, 131 and 137 and maintenance on structures 6, 8, 9, 11 and 50 | Line |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-07-10 08:00 | 2021-07-22 17:00 | N | N | 635PL6-1000 | Not In Model | Unmodeled Transmission Facility (Suncor) | Overpass Haul Road Line Raise | For Information Only
TRANSALTA, TRANSALTAW | IEW1 Summerview Phase 1, 354s L11 (354s Summerview) | 2021-07-10 08:00 | 2021-07-11 14:00 | N | Y | power pole replacement | Unit, Switch |  |  | For Information Only, Restricts Generation
TRANSALTA, TRANSALTAW | IEW1 Summerview Phase 1, 354s L21 (354s Summerview) | 2021-07-11 08:00 | 2021-07-11 18:00 | N | Y | power pole replacement | Unit, Switch |  |  | For Information Only, Restricts Generation
ENMAX | 39.82L (ENMAX 39 - ENMAX 162) | 2021-07-11 08:00 | 2021-07-11 16:00 | N | N | SF6 gas sample 39B138-39.82 | Line |  |  | Overload, Pre-Condition
EPCOR | 52s E2402 (52s East Industrial), 52s T2 (52s East Industrial) | 2021-07-12 07:00 | 2021-07-16 17:00 | N | Y | isolate TX2 bay to relocate metering and transformer controls | Circuit Breaker, Transformer | 52s T2 (52s East Industrial) | Isolate TX2 bay to relocate metering and transformer controls. | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 322S Cowley Ridge | 2021-07-12 07:00 | 2021-07-13 19:00 | N | N | maintenance | Station |  |  | Restricts Generation
EPCOR | T4 (Rossdale), RR729 (Rossdale), R724 (Rossdale) | 2021-07-12 07:00 | 2021-07-14 17:00 | N | N | maintenance | Transformer, Circuit Breaker | R724 (Rossdale), RR729 (Rossdale), T4 (Rossdale) | TX4 Tapchanger Maintenance, TX4 Zone Doble, RAB4/RDS11/RDS8 maintenance, Bushing tap leak. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 719L (263s Strachan - 719AL tap) | 2021-07-12 07:15 | 2021-07-16 17:45 | N | N | maintenance work (structures 366 - 402) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s 1209 (2029s Heathfield), 2029s 1208 (2029s Heathfield), 2029s ACF21 (2029s Heathfield), 2029s ACF22 (2029s Heathfield), 2029s ACF23 (2029s Heathfield) | 2021-07-12 07:30 | 2021-07-16 15:00 | N | Y | PRC testing AC filter bank | Circuit Breaker, Shunts | 2029s ACF21 (2029s Heathfield), 2029s ACF22 (2029s Heathfield), 2029s ACF23 (2029s Heathfield) | PRC testing AC Filter Bank 2 No Filter redundancy during work | 500 kV, Pre-Condition
ALTALINK | 205s T1 (205s Castle Rock Ridge), 205s 13 (205s Castle Rock Ridge) | 2021-07-12 07:30 | 2021-07-13 17:00 | N | Y | substation outage | Transformer, Switch |  | Enel Green Power will be performing its annual Substation Outage For Castle Rock Ridge wind Project On 7/12/21 commencing at 07:30 MT, and scheduled to End @ 7/13/21 17:00 MT. We will be requesting an Altalink switchmen for switching operations at the 205-S 240kV Altalink Substation at 07:30 MT on 7/12/21 and 17:00 MT on 7/13/21 customer maintenance outage | 240 kV, For Information Only, Restricts Generation
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2021-07-12 08:00 | 2021-07-16 17:00 | N | N | arm insulator change | Line |  | 6L12 GOI 6L12D4 to 6L12D5-774S-Arm Insulator Change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.5TR (ENMAX 8) | 2021-07-12 08:00 | 2021-07-13 16:00 | N | N | replace tapchanger gasket, transformer maintenance, gas relay testing | Transformer |  |  | For Information Only
ALTALINK | 510s ACF11 (510s Sunnybrook) | 2021-07-12 08:00 | 2021-07-16 16:00 | N | Y | annual filter bank outage and inspection | Shunts | 510s ACF11 (510s Sunnybrook) | Annual Filter Bank outage and inspection | 500 kV, For Information Only
ENMAX | 162B240-RB133 (ENMAX 162) | 2021-07-12 08:00 | 2021-07-12 11:00 | N | Y | SF6 sample, dashpot checks | Circuit Breaker | 162B240-RB133 (ENMAX 162) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 803s T1 (EP 803s Lambton), EP 803s L2401 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton) | 2021-07-12 08:00 | 2021-07-16 12:00 | N | Y | tower removal | Transformer, Circuit Breaker | EP 803s T1 (EP 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 12.1TR (ENMAX 12) | 2021-07-12 08:00 | 2021-07-16 16:00 | N | N | HV bushing replacement, rerun ground shield ground wire, investigate BA & BB breaker rosettes, oil sampling MT, TC | Transformer |  | HV Bushing Replacement. Rerun ground shield ground wire. 12.1TR Investigate BA & BB Breaker Rosettes. Oil sampling MT, TC | For Information Only
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2021-07-12 08:00 | 2021-08-06 16:00 | N | N | cap bank replacement (cap 16) | Shunts |  |  | For Information Only
ENMAX | 41.1TR (ENMAX 41) | 2021-07-12 08:00 | 2021-07-23 16:00 | N | N | power factor test transformer, secondary cable tests, transformer maintenance, oil sampling MT, TC | Transformer |  | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance. Oil Sampling MT, TC | For Information Only
BCH | 2L294 (BCH A. A. Lambert - BCH Nelway) | 2021-07-12 09:00 | 2021-07-14 20:00 | N | Y | insulator replacement | Line | 2L294 (Nelway - A.A. Lambert) |  | Limits ATC, Pre-Condition
ALTALINK | 42s 906N (42s Sarcee), 906L (17s Benalto - 42s Sarcee) | 2021-07-12 09:30 | 2021-07-14 16:30 | N | Y | migrate and commission all 42s906N & L4-906L at 42s Sarcee associated line protections, metering, and devices | Circuit Breaker, Line | 906L (17s Benalto - 42s Sarcee) |  | 240 kV, Pre-Condition
ATCO | 885s 901 (885s McMillan), 885s 902 (885s McMillan), 9L89 (885s McMillan - 2011s Dawes) | 2021-07-12 09:30 | 2021-07-15 16:00 | N | Y | 901 breaker maintenance, 9L89 RTXP switch replacements | Circuit Breaker, Line | 9L89 (885s McMillan - 2011s Dawes) | 901 Breaker Maintenance & 9L89 RTXP switch replacements - The GOI zone can be reduced to 901A, 901B for 885S 901 breaker Maintenance after the RTXP switches have been replaced. | 240 kV
ATCO | 876s 901T (876s Brintnell) | 2021-07-12 10:00 | 2021-07-15 16:30 | N | Y | 901T leak mitigation and transformer maintenance | Transformer | 876s 901T (876s Brintnell) | 901T Leak mitigation, and 901T transformer Maintenance | 240 kV, For Information Only
ATCO | 706s 702T (706s Irish Creek), 706s 704 (706s Irish Creek) | 2021-07-12 10:00 | 2021-07-16 14:00 | N | N | isolate transformer complete testing and leak repair | Transformer, Circuit Breaker | 706s 702T (706s Irish Creek) | Isolate Transformer complete testing and leak repair | For Information Only
ENMAX | 162B240-RB134 (ENMAX 162) | 2021-07-12 11:00 | 2021-07-12 13:00 | N | Y | SF6 sample, dashpot checks | Circuit Breaker | 162B240-RB134 (ENMAX 162) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 89s 652 (89s Ellerslie), 89s 752 (89s Ellerslie) | 2021-07-12 11:00 | 2021-07-15 18:00 | N | Y | replace 240kV PTs 89s75. 89s652 maintenance including 1st trips and 12 grading capacitors | Line, Circuit Breaker | 908L (89s Ellerslie - 816s Petrolia), 89s 752 (89s Ellerslie), 89s 652 (89s Ellerslie) |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 162B240-RB131 (ENMAX 162) | 2021-07-12 13:00 | 2021-07-12 16:00 | N | Y | SF6 gas sample, dashpot checks | Circuit Breaker | 162B240-RB131 (ENMAX 162) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 283s C1 (283s Violet Grove), 283s 31 (283s Violet Grove) | 2021-07-13 07:30 | 2021-07-13 17:30 | N | N | transformer protection upgrade, trip testing to breaker | Shunts, Circuit Breaker | 283s C1 (283s Violet Grove) |  | Pre-Condition
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2021-07-13 08:00 | 2021-07-14 16:00 | N | Y | annual filter bank outage and inspections | Shunts | 510s ACF12 (510s Sunnybrook) |  | 500 kV, For Information Only
ENMAX | 25B240-D132 (ENMAX 25) | 2021-07-13 08:00 | 2021-07-13 16:00 | N | Y | HV breaker maintenance | Circuit Breaker | 25B240-D132 (ENMAX 25) |  | 240 kV, Pre-Condition
ENMAX | 38.2TR (ENMAX 38) | 2021-07-13 08:00 | 2021-07-16 16:00 | N | N | power factor test transformer, maintenance, gas relay testing, check reversing switch, oil sampling MT. ECI bushings | Transformer |  | Power factor test transformer. Transformer maintenance. Gas relay testing. Check reversing switch. Oil sampling MT. ECI Bushings | For Information Only
BLACKSPRING | 485s T2 (485s Blackspring) | 2021-07-13 08:00 | 2021-07-14 17:00 | N | N | install Qualitrol QTMS bushing monitoring | Transformer |  |  | 240 kV, Restricts Generation
BCH | 1L274 (B1s BCH Natal - 1D1L274), 1L275 (799s Coleman - Natal) | 2021-07-13 08:00 | 2021-07-13 18:00 | N | Y | NTL station work | Line | *****For OC****** 1. 2L294 is out-of-service July 12, 2021 - July 16, 2021. "To Int S&D" and "To Ext S&D" are not selected and "Import ATC" is left blank because 2L294 is more restrictive on AB-BC import ATC. 2. S&D report import calculation will be incorrect if there are 2 records with Import ATC values at the same time, therefore "To Int S&D" and "To Ext S&D" are not selected in this case and Import ATC field is left blank. 3. Please fill in correct values and select "To Int S&D" and "To Ext S&D" for future 1L274 outages and also edit General Internal Comment 4 on Study tab. |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK, EPCOR | 738L (38s East Edmonton - 95s Imperial Oil Edmonton), 38s 738W (38s East Edmonton) | 2021-07-13 08:00 | 2021-07-13 17:30 | N | N | breaker inspection and testing. | Line, Circuit Breaker | Replacing gas mixture on 38s738W. Breaker inspection and testing. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L938 (77s Sagitawah - 809s Louise Creek), 809s 901T (809s Louise Creek), 809s 503R (809s Louise Creek), 809s 504R (809s Louise Creek) | 2021-07-13 17:01 | 2021-08-22 17:00 | N | Y | Louise Creek rebuild project | Line, Transformer, Shunts | May need to split the record closer to outage | Louise Creek Rebuild project- Replace 912, 900PT1, CT modifications to 906CT, 912CT, and 901T July 5-13  Isolation Points: 809S 901TD, 809S 701B, 809S 201TD, 809S 500D1  809S 901T OOS July 13-August 22  Expand GOI  Isolation points: 809S 911A, 809S 906A, 809S 701A, 809S 500D1, 809S 201TD1 & 77S938N (COG From AltaLink) - 809S 901T OOS & 9L938 OOS 809S 911 Breaker will be in-operable at the end of this outage and will be included on the following GOI for 809S 902T on August 23 2-50617. | 240 kV, Pre-Condition, Affects Cranking Path
TRANSALTA | 240S McBride Lake | 2021-07-14 07:00 | 2021-07-15 19:00 | N | N | maintenance | Station |  |  | For Information Only
ENEL, ALTALINK | 205s T2 (205s Castle Rock Ridge), 205s 14 (205s Castle Rock Ridge) | 2021-07-14 07:30 | 2021-07-15 17:00 | N | Y | substation outage | Transformer, Switch |  | Enel Green Power will be performing its Annual Substation Outage For Riverview Wind Project On 7/14/21 commencing at 07:30 MT, and scheduled to End @ 7/15/21 17:00 MT. We will be requesting an Altalink switchmen for switching operations at the 205-S 240kV Altalink Substation at 07:30 MT on 7/14/21 and 17:00 MT on 7/15/21. We request Altalink to confirm receipt of this message for a switchman on requested dates | 240 kV, For Information Only, Restricts Generation
ALTALINK | 205s 14 (205s Castle Rock Ridge) | 2021-07-14 07:30 | 2021-07-15 17:00 | N | Y | Customer maintenance | Switch |  |  | For Information Only, Restricts Generation
ALTALINK | 673L (131s Moon Lake - 283s Violet Grove) | 2021-07-14 07:30 | 2021-07-14 12:30 | N | N | transformer protection upgrade, trip testing to breaker | Line | 673L (131s Moon Lake - 283s Violet Grove) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ENMAX | 25B240-D142 (ENMAX 25) | 2021-07-14 08:00 | 2021-07-14 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
ALTALINK | 151s C1 (151s Strathmore) | 2021-07-14 08:00 | 2021-07-14 12:30 | N | N | verify trip coil circuit to cap bank breaker (151s44) | Shunts |  |  | Over/Under Voltage
ATCO | 7L81 (BCH Fort Nelson G.S. - 791s Rainbow Lake) | 2021-07-14 08:00 | 2021-07-14 17:00 | N | Y | urgent: line conductor | Line |  | Broken Structure  Emergency Repairs | Restricts Generation, Affects Cranking Path
ALTALINK | 118s C1 (118s Canmore) | 2021-07-14 08:15 | 2021-07-15 17:45 | N | N | C1 SR850 Protection Upgrade - SCADA deficiencies | Shunts |  |  | For Information Only
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 92s 792 (92s Viscount) | 2021-07-14 08:30 | 2021-07-14 17:30 | N | N | breaker maintenance | Line, Circuit Breaker | 792L (92s Viscount - 191s N.W. Cardiff) | Breaker maintenance and 1st trip tests & heater replacement on 92s792. 92s5 switch adjustment. 191s24 switch adjustment. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ALTALINK | 968L (138s Windy Flats - 370s North Lethbridge) | 2021-07-14 09:15 | 2021-07-19 14:45 | N | Y | Outage required on 240kv bus to install future breaker piles | Line | 968L (138s Windy Flats - 370s North Lethbridge) |  | 240 kV, Pre-Condition
ALTALINK | 835L (283s Violet Grove - 835AL tap) | 2021-07-14 12:30 | 2021-07-14 17:30 | N | N | Transformer protection upgrade, trip testing to breaker | Line | 835L (283s Violet Grove - 835AL tap) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 803s 701T (803s Bullpound) | 2021-07-14 17:31 | 2021-07-15 17:30 | N | N | transformer and circuit switcher maintenance | Transformer |  | Transformer and Circuit switcher Maintenance Mobile Sub will be in service to carry load, no outage to customer expected | For Information Only
ALTALINK | 749L (899s Edgerton - 749AL tap) | 2021-07-15 07:00 | 2021-07-15 18:00 | N | N | urgent repairs on structures #Str. 138, 177 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 729L (542s Ervick - 729AL tap) | 2021-07-15 07:00 | 2021-07-15 18:00 | N | Y | fire mitigation on structures #15 & 123 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, Lethbridge | 725L (15s Fort MacLeod - 674s Lethbridge Bowron) | 2021-07-15 08:00 | 2021-07-15 13:00 | N | Y | air break function test and maintance | Line | 725L (15s Fort MacLeod - 674s Lethbridge Bowron) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2021-07-15 08:00 | 2021-07-15 16:00 | N | N | breaker maintenance | Shunts |  | HV Breaker maintenance 14CS138-14.2CAP | For Information Only
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove), 283s 836W (283s Violet Grove) | 2021-07-15 09:00 | 2021-07-15 10:30 | N | Y | transformer protection upgrade, trip testing to breaker | Line, Circuit Breaker | 836L (61s Lodgepole - 283s Violet Grove) | Transformer protection upgrade, trip testing to breaker | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L85 (803s Bullpound - 804s Wintering Hills) | 2021-07-15 15:30 | 2021-07-15 17:30 | N | N | transformer and circuit switcher maintenance | Line |  | Transformer and Circuit switcher Maintenance Mobile Sub will be in service to carry load, no outage to customer expected | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
SUNCOR | 29EDD-71 144kV Bus 29PP-46 | 2021-07-16 08:00 | 2021-07-21 18:00 | N | N | 5y maintenance | Bus |  |  | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2021-07-16 10:00 | 2021-07-19 15:00 | N | Y | crossarm changing | Line | Current Vlim3 is still valid and that the most restrictive limit is the thermal concern. Thermal concern will be reached before any voltage stability limit is reached. | Crossarm changing | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 396s T3 (396s Pincher Creek) | 2021-07-17 06:45 | 2021-07-17 20:15 | N | N | urgent oil level gauge replacement to prevent future misoperation and lockout | Transformer | 396s T3 (396s Pincher Creek) | 396sT3 TX18592 Low Oil Trip - Urgent Priority Work (oil level gauge replacement) to prevent future misoperation and lockout. 396s41(CHD Waterton Dam & Reidco Power) Required offline for duration of outage | For Information Only
EPCOR | 987s C2403 (987s Clover Bar) | 2021-07-17 07:00 | 2021-07-17 17:00 | N | Y | dashpot repair | Circuit Breaker | 987s C2403 (987s Clover Bar) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 185L (379s Shell Canada Waterton - 415s Drywood) | 2021-07-17 07:15 | 2021-07-17 16:15 | N | N | urgent conductor repair 185L162, 131 & 135 strs | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.3TR (ENMAX 2) | 2021-07-17 08:00 | 2021-07-18 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer | 2.3TR (ENMAX 2) |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703BL) | 2021-07-18 07:00 | 2021-07-19 18:00 | N | N | line clearance mitigation on structures #113, 124, 125 & 194. | Line | 703L (213s Hughenden - 703BL) |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 24B138-24.83 (ENMAX 24), 24.1TR (ENMAX 24), 24.83L (74s Janet - ENMAX 24), 24.81L (ENMAX 24 - ENMAX 31) | 2021-07-18 08:00 | 2021-07-18 18:00 | N | Y | breaker maintenance 24B138-24.83 | Circuit Breaker, Transformer, Line | 24.83L (74s Janet - ENMAX 24), 24.81L (ENMAX 24 - ENMAX 31) | HV Breaker maintenance 24B138-24.83. SF6 Gas sample 24B138-24BT3. Check reversing switch 24.1TR | Creates Radial Feeds, Firm Load Loss
ALTALINK | 396s T1 (396s Pincher Creek) | 2021-07-18 09:30 | 2021-07-23 17:30 | N | N | 396s30 breaker replacement. | Transformer | 396s T1 (396s Pincher Creek) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
BCH | 5L91 (Ashton Creek - Selkirk) | 2021-07-18 14:00 | 2021-07-22 18:00 | N | Y | forced outage due to forest fire | Line | 5L91 (Selkirk - Ashton Creek) |  | 500 kV, Limits ATC, Pre-Condition
EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy) | 2021-07-19 07:00 | 2021-07-23 17:00 | N | Y | substation life cycle replacement of HV VTs | Line | 1055L (629s Argyll Transfer Station - 816s Petrolia) | Substation Life Cycle Replacement of HV VTs - Petrolia- 1055L CVT | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 657s SU2401 (657s Summerside) | 2021-07-19 07:00 | 2021-07-20 17:00 | N | Y | cutover new controls, status, alarms to new RTU | Circuit Breaker | 657s SU2401 (657s Summerside) | Isolate SU2401 to cutover new controls, status, alarms to new RTU. | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 24.2TR (ENMAX 24), 24.82L (ENMAX 24 - ENMAX 65) | 2021-07-19 08:00 | 2021-07-19 16:00 | N | N | power factor test 24PT138-Z32 | Transformer, Line | 24.82L (ENMAX 24 - ENMAX 65), 24.2TR (ENMAX 24) |  | Pre-Condition
ENMAX | 1.5TR (ENMAX 1) | 2021-07-19 08:00 | 2021-07-23 16:00 | N | N | tapchanger inspection, oil leak repair and oil sampling | Transformer | 1.5TR (ENMAX 1) | Tapchanger inspection. Reinhausen. 1.5TR Oil Leak Repair Follow Up. Oil Sampling TC | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2021-07-19 08:00 | 2021-07-20 16:00 | N | N | CT replacement | Transformer |  | 31.1TR CT Replacement | For Information Only
ATCO | 769s 703T (769s Stettler) | 2021-07-19 08:00 | 2021-07-21 15:30 | N | N | bird proofing to the south bus and transformer | Transformer | 769s 703T (769s Stettler) | Bird proofing to the south bus and transformer low side. Load will be transferred to 701T | Creates Radial Feeds, Firm Load Loss
ATCO | 743s 702T (743s Sarah Lake) | 2021-07-19 08:00 | 2021-08-06 16:00 | N | N | 702T Leak mitigation, 502VR replacement | Transformer | 743s 702T (743s Sarah Lake) | 702T Leak mitigation, 502VR replacement | For Information Only
ENMAX | 35.2TR (ENMAX 35) | 2021-07-19 08:00 | 2021-07-22 16:00 | N | N | power factor test transformer, secondary cable tests, maintenance,check reversing switch, oil sampling | Transformer | 35.2TR (ENMAX 35) | Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Check reversing switch, Oil Sampling MT, TC | For Information Only
ENMAX | 25B240-D138 (ENMAX 25) | 2021-07-19 08:00 | 2021-07-19 16:00 | N | Y | breaker maintenance | Circuit Breaker | 25B240-D138 (ENMAX 25) |  | 240 kV
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 2B138-D83 (ENMAX 2), 2B138-D84 (ENMAX 2) | 2021-07-19 08:00 | 2021-07-21 16:00 | N | N | replace relay and commission | Line, Circuit Breaker | 2.81L (ENMAX 2 - ENMAX 9) |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2021-07-19 09:00 | 2021-07-22 17:00 | N | Y | install and commission new SCADA meter | Line | 21.80L (42s Sarcee - ENMAX 21) | Migrate and commission all 42s21 (752) & L7-21.80L at 42s Sarcee associated line protections, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Install and commission new SCADA meter. | Pre-Condition
ALTALINK | 514L (513s Range. Pipe Lundbreck - 514BL tap), 513s T1 (513s Range. Pipe Lundbreck) | 2021-07-19 09:15 | 2021-07-23 17:45 | N | N | 514L components str's range 209-431 | Line, Transformer | 514L (513s Lundbreck - 514BL) |  | Pre-Condition
ALTALINK | 283s T2 (283s Violet Grove) | 2021-07-19 09:30 | 2021-07-22 18:00 | N | N | protection upgrade and trip testing | Transformer | 283s T2 (283s Violet Grove) |  | For Information Only
ATCO, ALTALINK | 885s 902 (885s McMillan), 885s 903 (885s McMillan), 9L55 (852s Round Hill - 885s McMillan) | 2021-07-19 09:30 | 2021-07-21 16:00 | N | Y | 9L55 RTXP replacements and 903 breaker maintenance | Circuit Breaker, Line | 9L55 (852s Round Hill - 885s McMillan) | 9L55 RTXP replacements 903 Breaker Maintenance The GOI zone can be reduced to only include 903 breaker after the RTXP switches have been replaced. 903A, 903B | 240 kV, Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2021-07-19 10:00 | 2021-07-20 15:37 | N | Y | pump replacements and in line filter installation | Shunts | 813s SVC (813s Little Smoky) | Work on glycol system. Pump replacements and in line filter installation. | Pre-Condition
ATCO | 741s 701T (741s Fox Creek) | 2021-07-19 10:00 | 2021-07-23 16:00 | N | N | replace rads on 701T, 703 Breaker maintenance | Transformer | 741s 701T (741s Fox Creek) | Replace Rads on 701T, 703 Breaker maintenance, 25kv Load transferred to 702T | For Information Only
ALTALINK | 434s T3 (434s East Stony Plain) | 2021-07-19 10:00 | 2021-07-22 18:00 | N | N | replace 434s285N, replace power cables to 434s477N - 25 kV work | Transformer | 434s T3 (434s East Stony Plain) | Replace 434s285N. Replace power cables to 434s477N. Transition from 273997 434s477N  GOI. RSLD 5 to be implemented at the end of this outage. | For Information Only
ALTALINK, EPCOR | 89s 752 (89s Ellerslie), 89s 852 (89s Ellerslie), 908L (89s Ellerslie - 908AL tap), 908AL (52S East Industrial - 908L tap), 908L (38s East Edmonton - 908AL tap) | 2021-07-19 11:00 | 2021-07-22 18:00 | N | Y | replace 240 kV PTs 89s76 and 89s15 maintenance | Circuit Breaker, Line | 908L (38s East Edmonton - 908AL tap), 908AL (52S East Industrial - 908L tap), 908L (89s Ellerslie - 908AL tap), 89s 852 (89s Ellerslie), 89s 752 (89s Ellerslie) | Replace 240kV PTs 89s76. 89s15 maintenance. | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 76L (33s Spray - 115s Mt. Allan) | 2021-07-19 12:15 | 2021-07-21 17:45 | N | N | drain vaults and SVC replacements | Line | 76L (33s Spray - 115s Mt. Allan) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 562s T1 (562s Cypress) | 2021-07-19 12:30 | 2021-07-22 16:30 | N | Y | doble, maintenance, leak repairs | Transformer | 562s T1 (562s Cypress) | Doble, Maintenance, leak repairs | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 71s 1252 (71s Lamoureux) | 2021-07-20 07:00 | 2021-07-20 18:00 | N | Y | isolate breaker for ABB representative to complete commissioning | Circuit Breaker | 71s 1252 (71s Lamoureux) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 226S Garden City | 2021-07-20 07:00 | 2021-07-21 18:00 | N | N | replace HX transformer bushings, winding temp sensor and general annual maintenance inspection | Station |  | Replace HX transformer bushings. Replace transformer winding temp sensor. General annual maintenance inspection and punch list items | For Information Only
EPCOR | EP 511s Victoria T2 (EP 511s Victoria) | 2021-07-20 07:00 | 2021-07-20 17:00 | N | N | tap changer maintenance | Transformer | EP 511s Victoria T2 (EP 511s Victoria) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 891L (226s Garden City - 863L tap) | 2021-07-20 07:15 | 2021-07-22 17:45 | N | Y | maintenance | Line | 891L (226s Garden City - 863L) | Scope of work includes maintenance on structures 7, 9, 15, 17, 18, 20, 24, 28, 29, 30, 35 and 37 | Restricts Generation
ATCO | 7L49 (729s Otauwau - 732s Mitsue) | 2021-07-20 08:00 | 2021-07-20 15:00 | N | N | change pole from test and treat data | Line | 7L49 (729s Otauwau - 732s Mitsue) | Change pole from test and treat data | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 25B240-D139 (ENMAX 25) | 2021-07-20 08:00 | 2021-07-20 16:00 | N | Y | breaker maintenance 25B240-D139 | Circuit Breaker | 25B240-D139 (ENMAX 25) |  | 240 kV, Pre-Condition
ATCO | 721s 701T (721s La Corey) | 2021-07-20 08:00 | 2021-07-22 16:00 | N | N | 701T & 501VR maintenance | Transformer | 721s 701T (721s La Corey) | 701T & 501VR maintenance, load to be transferred to 702T | For Information Only
ATCO | 7L760 (767s Oyen - 7LA760 tap), 7LA760 (914s Bindloss - 7LA760 tap) | 2021-07-20 08:00 | 2021-07-20 17:00 | N | Y | planned high load to cross under 7L760 in two locations | Line | 7L760 (767s Oyen - 7LA760 tap), 7LA760 (914s Bindloss - 7LA760 tap) | Planned High load to cross under 7L760 in Two locations | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 263s 35 (263s Strachan), 263s C1 (263s Strachan) | 2021-07-20 09:00 | 2021-07-20 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts | 263s C1 (263s Strachan) |  | Pre-Condition
AESO-SC | OATI | 2021-07-20 18:00 | 2021-07-20 19:00 | N | N | performing an inter-site transfer business continuity drill | SCInternal |  | perform an Inter-Site Transfer business continuity drill | For Information Only
SUNCOR | 139S Hillridge | 2021-07-21 02:07 | 2021-07-23 07:51 | N | N | communication issues | Station |  |  | For Information Only
ALTALINK | 71s 1352 (71s Lamoureux) | 2021-07-21 07:00 | 2021-07-21 18:00 | N | Y | isolate breaker for ABB representative to complete commissioning | Circuit Breaker | 71s 1352 (71s Lamoureux) |  | 240 kV, Contingency Requires Mitigation
EPCOR | 657s SU2402 (657s Summerside) | 2021-07-21 07:00 | 2021-07-21 17:00 | N | Y | isolate SU2402 to cutover controls, status, alarms to new RTU | Circuit Breaker | 657s SU2402 (657s Summerside) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3B138-3.84 (ENMAX 3), 3.84L (ENMAX 3 - ENMAX 13) | 2021-07-21 08:00 | 2021-07-21 16:00 | N | N | breaker maintenance 3B13-3.84 | Circuit Breaker, Line | 3.84L (ENMAX 3 - ENMAX 13) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2021-07-21 08:00 | 2021-07-21 16:00 | N | N | power factor testing 23PT138-Z31 | Line, Transformer | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | ML1 (D05 Syncrude - Syncrude Mildred Lake) | 2021-07-21 08:00 | 2021-07-21 20:00 | N | N | maintenance | Line | ML1 (D05 Syncrude - Syncrude Mildred Lake) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s 552 (63s Red Deer) | 2021-07-21 08:15 | 2021-07-21 17:15 | N | Y | 1st trip PRC5 maintenance | Circuit Breaker | 63s 552 (63s Red Deer) |  | 240 kV, Contingency Requires Mitigation
ATCO | 885s 903 (885s McMillan) | 2021-07-21 16:01 | 2021-07-22 16:00 | N | Y | breaker maintenance | Circuit Breaker | 9L55 (852s Round Hill - 885s McMillan) | The GOI zone can be reduced to only include 903 breaker after the RTXP switches have been replaced. 903A, 903B | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 657s SU2403 (657s Summerside) | 2021-07-22 07:00 | 2021-07-22 17:00 | N | Y | cutover new controls, status, alarms to new RTU | Circuit Breaker | 657s SU2403 (657s Summerside) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 24B138-24.82 (ENMAX 24), 24.82L (ENMAX 24 - ENMAX 65) | 2021-07-22 08:00 | 2021-07-22 12:00 | N | N | SF6 gas sample 24B138-24.82 | Circuit Breaker, Line | 24.82L (ENMAX 24 - ENMAX 65) |  | Pre-Condition
ENMAX | 3.3TR (ENMAX 3), 3.82L (ENMAX 3 - ENMAX 8) | 2021-07-22 08:00 | 2021-07-22 16:00 | N | N | power factor test 3PT138-Z31 | Transformer, Line | 3.82L (ENMAX 3 - ENMAX 8), 3.3TR (ENMAX 3) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 2 (17s Benalto) | 2021-07-22 09:00 | 2021-07-22 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker | 17s 2 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood) | 2021-07-22 09:30 | 2021-07-23 18:00 | N | N | install a new structure between structures 3 and 4 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 657s SU2404 (657s Summerside) | 2021-07-23 07:00 | 2021-07-23 17:00 | N | Y | cutover new controls, status, alarms to new RTU | Circuit Breaker | 657s SU2404 (657s Summerside) | Isolate SU2404 to cutover new controls, status, alarms to new RTU. | 240 kV, Contingency Requires Mitigation
ALTALINK | 283s T1 (283s Violet Grove) | 2021-07-23 07:00 | 2021-07-23 18:00 | N | N | T2 'B' protection upgrade and trip testing | Transformer | 283s T1 (283s Violet Grove), 483L (283s Violet Grove - DVp Drayton Valley Power) |  | For Information Only
ALTALINK | 752L (653s Summit - 752AL tap) | 2021-07-23 07:15 | 2021-07-23 14:45 | N | N | repairing conductor (str 89-90) | Line | 752L (653s Summit - 752AL tap) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BHE, ALTALINK | 719s Rattlesnake Ridge, 879AL (719s Rattlesnake Ridge - 879L), 719s T1 (719s Rattlesnake Ridge), 719s 138CB1 (719s Rattlesnake Ridge), 719s 138MDS1 (719s Rattlesnake Ridge) | 2021-07-23 08:00 | 2021-09-07 16:00 | N | N | P2212 ISD August 31, 2021 | Station, Line, Transformer, Circuit Breaker, Switch
ENMAX | 31B138-24.81 (ENMAX 31), 24.81L (ENMAX 24 - ENMAX 31) | 2021-07-23 08:00 | 2021-07-23 16:00 | N | N | SF6 gas sample 31B138-24.81 | Circuit Breaker, Line | 24.81L (ENMAX 24 - ENMAX 31), 31B138-24.81 (ENMAX 31) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2021-07-23 08:00 | 2021-07-23 16:00 | N | N | power factor test 16B69-16.61 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 691L (74s Janet - 419s Chestermere), 74s 691 (74s Janet) | 2021-07-24 07:15 | 2021-07-25 16:45 | N | N | install and commission relays for RAS on 691L, remove RAS from line protection relay | Line, Circuit Breaker |  | Install and commission relays for RAS on 691L, remove RAS from line protection relay. | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 13.60L (ENMAX 13 - ENMAX 27) | 2021-07-24 08:00 | 2021-07-24 16:00 | N | N | power factor test 27B69-13.60 | Line | 13.60L (ENMAX 13 - ENMAX 27) | Power factor test 27B69-13.60 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek), 396s 185 (396s Pincher Creek) | 2021-07-24 12:30 | 2021-07-29 17:30 | N | N | breaker replacement | Line, Circuit Breaker | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 396s185 breaker replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 15.1TR (ENMAX 15) | 2021-07-25 08:00 | 2021-08-27 16:00 | N | N | install new Albarrie, plastibeton, duct banks and cables, phasing required on return | Transformer |  | 15.1TR MV Bushing Replacement. | For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54), 41.1TR (ENMAX 41) | 2021-07-25 08:00 | 2021-07-25 12:00 | N | N | substation summer washing | Line, Transformer | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54), 41.1TR (ENMAX 41) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 6.82L (ENMAX 6 - ENMAX 41), 41.2TR (ENMAX 41), 41.1C (ENMAX 41) | 2021-07-25 12:00 | 2021-07-25 18:00 | N | N | substation summer washing | Line, Transformer, Shunts | 33.83L (ENMAX 33 - ENMAX 41), 6.82L (ENMAX 6 - ENMAX 41), 41.2TR (ENMAX 41), 41.1C (ENMAX 41) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2021-07-26 07:00 | 2021-07-30 17:00 | N | Y | replace Dome 909LW CVT | Line | 909L (310p Sundance - 665s Dome) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 72CH11 (987s Clover Bar - EPCOR Hardisty), H725 (EPCOR Hardisty), H722 (EPCOR Hardisty), T1 (EPCOR Hardisty) | 2021-07-26 07:00 | 2021-08-03 17:00 | N | N | Hardisty T1 replacement | Line, Circuit Breaker, Transformer | 72CH11 (987s Clover Bar - EPCOR Hardisty), H725 (EPCOR Hardisty), H722 (EPCOR Hardisty), T1 (EPCOR Hardisty) | Hardisty TX1 Replacement - 1007222 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 151s 765W (151s Strathmore) | 2021-07-26 07:15 | 2021-07-27 16:20 | N | Y | maintenance on structures 103 and 104 | Line, Circuit Breaker | 765L (151s Strathmore - 419s Chestermere) | Scope of work includes maintenance on structures 103 and 104. 2nd Scope: Install and commission relays for RAS on 765L, remove RAS from line protection relay. 3rd scope: 1st Trip and Maintenance (leaky Dashpot) | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 3.3TR (ENMAX 3) | 2021-07-26 08:00 | 2021-07-29 16:00 | N | N | ECI bushings, power factor test transformer, secondary cable tests, maintenance, gas relay testing and check reversing switch and oil sampling | Transformer |  |  | For Information Only
ENMAX | 5.9TR (ENMAX 5) | 2021-07-26 08:00 | 2021-07-29 16:00 | N | N | power factor test transformer, secondary cable tests, transformer maintenance, gas relay testing, check reversing switch, replace PRD junction box | Transformer | 5.9TR (ENMAX 5) |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2021-07-26 08:00 | 2021-07-29 16:00 | N | N | tapchanger inspection, check reversing switch, oil sampling | Transformer | 1.6TR (ENMAX 1) |  | For Information Only
Syncrude | D05 T1 (D05 Syncrude) | 2021-07-26 08:00 | 2021-07-29 04:00 | N | Y | maintenance | Transformer | D05 T1 (D05 Syncrude) | Significant Outage: T1 Transformer (260/72KV) in D05 Substation Following Circuit Breakers will be operated to isolate T1: 519, 511, 71 Following MOD's will be operated to isolate T1: 519A, 519B, 511A, 511B, 510, 71A, 71B | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 10.1TR (ENMAX 10) | 2021-07-26 08:00 | 2021-07-29 16:00 | N | N | 10 sub cable trench replacement | Transformer |  |  | For Information Only
ATCO | 770s 701T (770s Three Hills) | 2021-07-26 08:00 | 2021-07-29 12:00 | N | N | maintenance | Transformer |  | 701T Maintenance | For Information Only
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12), 12B138-833L (ENMAX 12) | 2021-07-26 08:00 | 2021-07-27 16:00 | N | Y | HV breaker maintenance | Line, Circuit Breaker | 833L (ENMAX 2 - ENMAX 12) | HV Breaker maintenance 12B138-833L. Original outage June 28-29 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 42s 916E (42s Sarcee), 916L (5s East Calgary - 42s Sarcee) | 2021-07-26 09:00 | 2021-07-29 17:00 | N | Y | migrate and commission all 42s916E (1352) & L13-916L at 42s Sarcee associated line protections, recloser, POW, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | Circuit Breaker, Line | 916L (5s East Calgary - 42s Sarcee) | Migrate and commission all 42s916E (1352) & L13-916L at 42s Sarcee associated line protections, recloser, POW, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | 240 kV, Pre-Condition
ALTALINK | 513s T1 (513s Range. Pipe Lundbreck), 514L (513s Range. Pipe Lundbreck - 514BL tap) | 2021-07-26 09:15 | 2021-07-30 17:45 | N | N | 514L components str's range 209-431 | Transformer, Line | 514L (513s Lundbreck - 514BL) |  | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2021-07-26 10:00 | 2021-08-09 15:00 | N | Y | crossarm changing | Line | 7L32 (813s Little Smoky - 862s South Bezanson) | Crossarm changing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 754s 701T (754s Ksituan River) | 2021-07-26 10:00 | 2021-07-28 17:00 | N | N | 754S 701T major maintenance & 501VR leak repair | Transformer | 754s 701T (754s Ksituan River) | 754S 701T Major Maintenance & 501VR leak repair, 25kv load to be transferred to 754S 703T | Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2021-07-26 10:00 | 2021-07-29 15:00 | N | Y | crossarm changes | Line | 7L40 (733s Simonette - 813s Little Smoky) | crossarm changes | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 71s 1452 (71s Lamoureux) | 2021-07-26 11:00 | 2021-07-26 16:30 | N | Y | maintenance on breaker including 1st trip | Circuit Breaker | 71s 1452 (71s Lamoureux) |  | 240 kV, Contingency Requires Mitigation
AIRLIQUIDE | ALC03L (402s Scotford Expansion - 408s Air Liquide Scotford) | 2021-07-26 11:00 | 2021-07-26 13:00 | N | N | emergency replace insulator string on structure 9 C phase | Line |  | Emergency Outage to replace Insulator String on Structure 9 C phase, Insulator has signs of flash over. | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 199L (268s Whitecourt - 199AL tap), 268s 199N (268s Whitecourt) | 2021-07-26 12:00 | 2021-07-29 18:00 | N | N | component replacements 199L (Str's 191-413) | Line, Circuit Breaker | 199L (268s Whitecourt - 199AL) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek) | 2021-07-26 12:30 | 2021-08-09 10:30 | N | N | fix T1 oil leaks, fix 308s4 | Transformer |  |  | For Information Only
ALTALINK | 283s 31 (283s Violet Grove), 283s C1 (283s Violet Grove) | 2021-07-27 07:30 | 2021-07-27 17:30 | N | N | transformer protection upgrade, trip testing to breaker | Circuit Breaker, Shunts | 283s C1 (283s Violet Grove) |  | Pre-Condition
ALTALINK | 434s T1 (434s East Stony Plain) | 2021-07-27 08:00 | 2021-07-27 16:30 | N | N | replace power cables to 434s36W | Transformer |  |  | For Information Only
ATCO | 7L89 (700s Bonnyville - 721s La Corey) | 2021-07-27 09:00 | 2021-07-27 15:00 | N | Y | removing 7L89PT2 | Line | 7L89 (721s La Corey - 826s Marguerite Lake) | Removing 7L89PT1, as Auto sectionalizing scheme is no longer in required | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 71s 652 (71s Lamoureux) | 2021-07-27 11:30 | 2021-07-28 17:30 | N | N | maintenance on breaker, fix gearbox sight glass leak | Circuit Breaker |  |  | Contingency Requires Mitigation
AESO-SC | OATI | 2021-07-27 19:30 | 2021-07-27 20:30 | N | N | upgrade one of their Storage Area Networks (SAN) | SCInternal |  | upgrade one of their Storage Area Networks (SAN) | For Information Only
ALTALINK | 283s 673 (283s Violet Grove), 673L (131s Moon Lake - 283s Violet Grove) | 2021-07-28 07:30 | 2021-07-28 12:30 | N | N | transformer protection upgrade, trip testing to breaker | Circuit Breaker, Line | 673L (131s Moon Lake - 283s Violet Grove) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation
FORTIS | Jenner Solar DER | 2021-07-28 08:00 | 2021-08-12 16:00 | N | N | P1840. 23 MW Solar DER. ISD August 5, 2021 | Unit
ATCO | 718s 703 (718s Parsons Creek), 7L165 (718s Parsons Creek - 933s Tower Road) | 2021-07-28 08:00 | 2021-07-29 17:00 | N | N | 703 breaker maintenance | Circuit Breaker, Line |  | 703 Breaker Maintenance | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 36.81L (44s Bearspaw - ENMAX 36), 36B138-36.81 (ENMAX 36) | 2021-07-28 08:00 | 2021-07-28 16:00 | N | Y | HV breaker maintenance | Line, Circuit Breaker | 36.81L (44s Bearspaw - ENMAX 36) | HV Breaker maintenance 36B138-36.81. Original outage date June 30th | For Information Only
ATCO | 749s 701T (749s Flyingshot Lake) | 2021-07-28 09:00 | 2021-07-29 17:00 | N | N | 701T major | Transformer | 749s 701T (749s Flyingshot Lake) | 701T major, load transferred to 702T, coordinated with Aquatera DG outage | For Information Only, Restricts Generation
ATCO | 7L89 (721s La Corey - 826s Marguerite Lake) | 2021-07-28 09:00 | 2021-07-28 15:00 | N | Y | removing 7L89PT1 | Line |  | Removing 7L89PT2, as Auto sectionalizing scheme is no longer in required | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 835L (283s Violet Grove - 835AL tap) | 2021-07-28 12:30 | 2021-07-28 17:30 | N | N | transformer protection upgrade, trip testing to breaker | Line | 835L (283s Violet Grove - 835AL tap) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
EPCOR | 805s T3 (805s Jasper) | 2021-07-29 07:00 | 2021-07-29 17:00 | N | Y | bus PT inspection with ABB | Transformer | 805s T3 (805s Jasper) |  | 240 kV, For Information Only
ALTALINK | 498s T2 (498s Tilley) | 2021-07-29 07:15 | 2021-07-29 14:00 | N | N | complete trip testing on 498s22, settings change, and CT wiring for new protections | Transformer |  |  | For Information Only
ALTALINK | 151s T2 (151s Strathmore) | 2021-07-29 07:45 | 2021-07-29 17:45 | N | N | replace temp gauges | Transformer | 151s T2 (151s Strathmore) |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2021-07-29 08:00 | 2021-07-29 12:00 | N | N | SF6 gas sample, resample | Line | 14.83L (ENMAX 14 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 89s 252 (89s Ellerslie) | 2021-07-29 08:00 | 2021-07-29 11:00 | N | Y | breaker maintenance | Circuit Breaker | 89s 252 (89s Ellerslie) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 283s 836W (283s Violet Grove), 836L (61s Lodgepole - 283s Violet Grove) | 2021-07-29 09:00 | 2021-07-29 10:30 | N | Y | transformer protection upgrade, trip testing to breaker | Circuit Breaker, Line | 836L (61s Lodgepole - 283s Violet Grove) |  | Contingency Requires Mitigation, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 47B138-771/1 (ENMAX 47) | 2021-07-29 12:00 | 2021-07-29 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10), 10.2TR (ENMAX 10) | 2021-07-30 08:00 | 2021-07-30 16:00 | N | Y | power factor test 10PT138-693, 10PT138-Z31 | Line, Transformer | 693L (42s Sarcee - ENMAX 10), 10.2TR (ENMAX 10) | Power factor test 10PT138-693, 10PT138-Z31 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib), 718s 702 (718s Parsons Creek) | 2021-07-30 08:00 | 2021-07-30 17:00 | N | N | 702 breaker maintenance | Line, Circuit Breaker |  | 702 Breaker Maintenance | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-07-31 08:00 | 2021-08-12 17:00 | N | N | 635PL6-1001 | Not In Model | Unmodeled Transmission Facility (Suncor) | Overpass Haul Road Line Raise | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel) | 2021-08-01 08:00 | 2021-08-11 16:00 | N | N | forced outage & availability | Shunts |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-08-02 08:00 | 2021-08-05 18:00 | N | N | 29EDD18; 29PL3-167 system; PM 5y | Not In Model |  |  | For Information Only
ENMAX | 24.82L (ENMAX 24 - ENMAX 65), 24.2TR (ENMAX 24) | 2021-08-02 08:00 | 2021-08-02 12:00 | N | N | substation summer washing and check reversing switch | Line, Transformer |  |  | For Information Only
ENMAX, ALTALINK | 24.81L (ENMAX 24 - ENMAX 31), 24.83L (74s Janet - ENMAX 24), 24.1TR (ENMAX 24) | 2021-08-02 12:00 | 2021-08-02 18:00 | N | Y | substation summer washing and check reversing switch | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 330P GT2 (330p Genesee), 330p 1204 (330p Genesee) | 2021-08-03 07:00 | 2021-08-13 17:00 | N | Y | maintenance | Transformer, Circuit Breaker |  | 1204 Bay Doble, G2 Arrestor Doble, G2 Zone Relay Maintenance | 500 kV, Contingency Requires Mitigation
ENMAX | 28.2TR (ENMAX 28) | 2021-08-03 08:00 | 2021-08-05 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ATCO | 863s 902 (863s Paintearth), 9L948 (650s Hansman Lake - 863s Paintearth) | 2021-08-03 08:00 | 2021-08-05 17:00 | N | Y | 902 maintenance | Circuit Breaker, Line |  | 902 Maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ENMAX | 8.1TR (ENMAX 8), 8.2TR (ENMAX 8) | 2021-08-03 08:00 | 2021-08-15 16:00 | N | N | GIS switch maintenance and testing | Transformer | 8.1TR (ENMAX 8), 8.2TR (ENMAX 8) | GIS Switch maint. 8SW6A52, 8SW6A02, 8SW6A81, 8SW6A82, 8SW7A11, 8SW6A01, Do not operate 6a51. Power factor test transformer. Secondary Cable Tests, Transformer maint. Gas relay testing. Summer washing. | For Information Only
ATCO | 848s 907 (848s Ruth Lake) | 2021-08-03 08:00 | 2021-08-05 11:30 | N | Y | 907 breaker maintenance | Circuit Breaker |  | 907 BKR Maintenance | 240 kV, Contingency Requires Mitigation
ENMAX | 40B138-40.81 (ENMAX 40), 40.81L (ENMAX 40 - ENMAX 41) | 2021-08-03 08:00 | 2021-08-03 12:00 | N | N | SF6 gas sample | Circuit Breaker, Line | 40.81L (ENMAX 40 - ENMAX 41) | SF6 gas sample 40B138-40.81 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20), 20B138-20.82 (ENMAX 20) | 2021-08-03 08:00 | 2021-08-03 16:00 | N | N | power factor test 20PT138-Z31 | Line, Transformer, Circuit Breaker | 20.3TR (ENMAX 20), 20.82L (ENMAX 20 - ENMAX 21) | Power factor test 20PT138-Z31 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 199L (268s Whitecourt - 199AL tap) | 2021-08-03 09:00 | 2021-08-06 18:00 | N | N | component replacements 199L | Line | 199L (268s Whitecourt - 199AL) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514L (513s Range. Pipe Lundbreck - 514BL tap) | 2021-08-03 09:15 | 2021-08-03 15:45 | N | Y | 514L2 replace insulation | Line | 514L (396s Pincher Creek - 514BL), 514L (513s Lundbreck - 514BL) |  | Restricts Generation
ALTALINK | 42s C2 (42s Sarcee) | 2021-08-03 09:30 | 2021-08-05 16:30 | N | Y | migrate and commission all cap bank C2 & 42S74 (2152) associated protections, breakers, breaker fail, POW alarms, status, controls, metering and remote access to new RTU and LAN | Shunts | 42s C2 (42s Sarcee) |  | 240 kV, For Information Only
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2021-08-03 10:00 | 2021-08-05 10:00 | N | Y | transformer and switches maintenance | Line |  |  | Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2021-08-03 10:00 | 2021-08-09 15:00 | N | Y | crossarm changes | Line | 7L40 (733s Simonette - 813s Little Smoky) | crossarm changes | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 322S Cowley Ridge | 2021-08-03 10:00 | 2021-08-03 15:00 | N | Y | maintenance to 69CS1 | Station |  |  | Restricts Generation
ALTALINK | 74s 552 (74s Janet) | 2021-08-03 11:00 | 2021-08-05 17:00 | N | Y | crew will get ACC to perform a couple of open and closes as needed when they are ready | Circuit Breaker | 74s 552 (74s Janet) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 41.1C (ENMAX 41) | 2021-08-03 12:00 | 2021-08-03 16:00 | N | N | SF6 gas sample | Shunts | 41.1C (ENMAX 41) | SF6 Gas sample 41B138-41.1CAP | Pre-Condition
EPCOR | T1 (EPCOR Hardisty) | 2021-08-03 17:01 | 2021-12-07 17:00 | N | N | Hardisty T1 replacement | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 428s T2 (428s Namaka), 428s 652 (428s Namaka) | 2021-08-04 08:00 | 2021-08-04 17:00 | N | Y | PRC - 005 gather load readings for compliant relay maintenance | Transformer, Circuit Breaker | 428s T2 (428s Namaka) | Techs require T2 out of service and T1 to take load. This is required to gather load readings for PRC005 Compliant relay maintenance. | Pre-Condition
SUNCOR, ATCO | 29EDD-1 72kV South Bus (29EDD-1 Millennium), 29EDD-1 260kV South Bus 1 (29EDD-1 Millennium), 29EDD-1 260kV South Bus 2 (29EDD-1 Millennium), 29EDD-1 29EDD1s1052 (29EDD-1 Millennium), 29EDD-1 29EDD1S1452 (29EDD-1 Millennium), 29EDD-1 29EDD1s1852 (29EDD-1 Millennium), 29EDD-1 29EDD1s352 (29EDD-1 Millennium), 29EDD-1 29EDD1s652 (29EDD-1 Millennium), 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake), 29EDD-1 952-103 (29EDD-1 Millennium), 29EDD-1 952-106 (29EDD-1 Millennium) | 2021-08-04 08:00 | 2021-08-21 18:00 | N | Y | preventative maintenance | Bus, Circuit Breaker, Line |  | 29EDD1 (South Bus) (estimated dates August 3 to August 14th) Preventative Maintenance for: - 29EDD-1T1 + Relays + Meter + IR windows, 29EDD-1S1452, Tap Changer - X72B1 + Relays, 29EDD-1S24/1S32/1S40, 29CVT-16A/B/C, 29PVT-2A/B/C + Disconnect/Fuse, 29EDD-1S1852 + CT's - X260B2 + Relays, 1S16, 1S20, 1S23, 29CVT-14A/B/C, PVT2 Panel, 1S1052 + Relays - 29EDD1S852, 29CT-7A/B/C - X260B1 + Relays, 29PT-167/168/169, 29PS-75/77/161, 1S12, 1S15, 29CVT-12, 1S6, 1S652, 1S352, 952-103/106 - 29CVT-1A/B/C, 29EDD-1S2/3/252 + Relay, 29PLA180A/B/C, 29EDD1SPL9-2 + Relay + Meter (will be dependant on GTG-5 offline) 29PL6-22 ( L7), from 29EDD-1/ 29EDD-2: (estimated dates August 7 to August 18th) - 72kV line 29PL-6-22 (L7) outage for replacement of A/B Protection Upgrade Note - Part of Suncor Turn Around | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 22.2TR (ENMAX 22) | 2021-08-04 08:00 | 2021-08-07 16:00 | N | N | tapchanger inspection | Transformer | 22.2TR (ENMAX 22) | Tapchanger inspection. 22.2X-TC, 22.2Y-TC | For Information Only
ENMAX, ALTALINK | 1080L (ENMAX 25 - ENMAX 65), 25B240-D138 (ENMAX 25), 25B240-D139 (ENMAX 25) | 2021-08-04 08:00 | 2021-08-05 16:00 | N | Y | 25MD240-1080 replacement | Line, Circuit Breaker | 1080L (ENMAX 25 - ENMAX 65) |  | 240 kV
ALTALINK | 287s 552 (287s Hazelwood) | 2021-08-04 10:00 | 2021-08-04 14:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  | 240kV breaker maintenance | 240 kV, Contingency Requires Mitigation
ENMAX | 32.3TR (ENMAX 32) | 2021-08-04 12:00 | 2021-08-09 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2021-08-04 23:00 | 2021-08-05 03:00 | N | N | maintenanace | Switch |  | TAU Requested Generator Outage (brushgear) | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2021-08-05 03:00 | 2021-08-05 07:00 | N | N | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 788L (898s Heart Lake - 788AL tap) | 2021-08-05 07:00 | 2021-08-05 18:00 | N | Y | replacing Structure #285 and maintenance on Structure #284 | Line | 788L (898s Heart Lake - 788AL tap) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 908L (38s East Edmonton - 89s Ellerslie), 908AL (52S East Industrial - 908L tap) | 2021-08-05 07:00 | 2021-08-11 22:00 | N | Y | replace damaged insulation, jumper strings | Line | 908L (38s East Edmonton - 89s Ellerslie), 908AL (52S East Industrial - 908L tap) | Repair sub bundle, broken inner core between 908L234 and 242. Replace all damaged dead end insulation and jumper strings 908L234. Repair Mid-span OHSW Tie 908L249. Replace all Dead-end insulation to 25 KIP NGK. | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 214s T2 (214s Innisfail) | 2021-08-05 07:15 | 2021-08-05 18:45 | N | N | replace 214s T2 wildlife cover up | Transformer |  | Replace 214s T2 Wildlife Cover up  Design error by Hubbell / Cantega on previously installed wildlife cover up. | For Information Only
ATCO | 848s 701 (848s Ruth Lake), 7L71 (848s Ruth Lake - 2082s Dog Rib) | 2021-08-05 08:00 | 2021-08-06 16:30 | N | N | 701 BKR Maintenance | Circuit Breaker, Line |  | 701 BKR Maintenance | Over/Under Voltage, Overload, Pre-Condition
ATCO | 863s 902T (863s Paintearth) | 2021-08-05 08:00 | 2021-08-06 17:00 | N | Y | 902Tleak mitigation | Transformer | 863s 902T (863s Paintearth) | 902T Leak mitigation | 240 kV, For Information Only, Pre-Condition
ALTALINK | 444L (198s Blackfalds - 217s North Red Deer) | 2021-08-06 07:15 | 2021-08-11 17:45 | N | Y | Scope of work includes replacing structures 7, 8, 10 and 12 and maintenance on Structures 1, 2, 6 and 25 | Line | 444L (198s Blackfalds - 217s North Red Deer) | Scope of work includes replacing structures 7, 8, 10 and 12 and maintenance on Structures 1, 2, 6 and 25 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 1202L (89s Ellerslie - 320p Keephills) | 2021-08-06 08:00 | 2021-08-06 18:00 | N | N | urgent repair | Line |  |  | 240 kV, Pre-Condition
SUNCOR | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2021-08-07 08:00 | 2021-08-21 18:00 | N | N | replacement of A/B protection upgrade | Line | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 29PL6-22 ( L7), from 29EDD-1/ 29EDD-2: (estimated dates August 7 to August 18th) - 72kV line 29PL-6-22 (L7) outage for replacement of A/B Protection Upgrade | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 16.63L (ENMAX 16 - ENMAX 36) | 2021-08-07 08:00 | 2021-08-07 16:00 | N | N | power factor test 16B69-16.63 | Line | 16.63L (ENMAX 16 - ENMAX 36) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALPAC | 282s RTU/SCADA (282s Grassland (Alpac)) | 2021-08-08 00:01 | 2021-08-08 06:00 | N | N | SCADA, internet and phone outage | Terminal Equipment |  |  | For Information Only
SUNCOR | 29PT-101 (29EDD-18) | 2021-08-08 08:00 | 2021-08-13 18:00 | N | N | turn around maintenance testing of high voltage & low voltage distribution equipment | Transformer |  |  | For Information Only, Pre-Condition
SUNCOR | 29PT-100 (29EDD-18) | 2021-08-08 08:00 | 2021-08-10 18:00 | N | N | turn around maintenance testing of high voltage & low voltage distribution equipment | Transformer |  | Turn Around Maintenance Testing of High voltage & low voltage Distribution Equipment | For Information Only, Pre-Condition
ATCO, SUNCOR | 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake) | 2021-08-08 11:00 | 2021-08-15 17:00 | N | Y | maintenance activities at Suncor base plant | Line |  | Suncor performing perform 5/10Yr maintenance activities at Suncor base plant, Suncor requesting ATCO isolation on this date and to gain escorted access to substation Ruth Lake 848S to verify and if possible hang red and yellow Suncor operation cross locks at ATCO Ruth lake disconnect for this line. | 240 kV, Pre-Condition,Affects Cranking Path
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2021-08-09 07:00 | 2021-08-09 16:00 | N | N | investigate noise complaint | Line |  |  | For Information Only, Pre-Condition
EPCOR | 330p 805 (330p Genesee), 330P 12TC1 (330p Genesee) | 2021-08-09 07:00 | 2021-08-13 17:00 | N | Y | breaker maintenance and CT doble | Circuit Breaker, Transformer | 330p 805 (330p Genesee), 330P 12TC1 (330p Genesee) | 805 Maintenance and CT Doble | 500 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 276s T3 (276s Union Carbide Prentiss), 775L (276s Prentiss - 535s Joffre), 276s 138kV South Bus (276s Union Carbide Prentiss) | 2021-08-09 07:00 | 2021-08-20 18:00 | N | N | maintenance, doble and oil reclaim, protection installation and testing | Transformer, Line, Bus | 276s T3 (276s Union Carbide Prentiss) | Maintenance , Doble and oil reclaim 2nd Scope: T3(TX18625) bushing CT installation, 276s775X breaker fail relay installation and 138kV South Bus B protection installation , Cutover all points to new SCADA system, Config file updates, SCADA commissioning and function testing | Pre-Condition
EPCOR | 330P 12TC1 (330p Genesee), 330P Genesee 500 kV Bus 1, 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee) | 2021-08-09 07:00 | 2021-08-14 17:00 | N | Y | emergency lightning spire repair | Transformer, Bus, Circuit Breaker | 330P 12TC1 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 805 (330p Genesee) | Emergency Lightning Spire Repair # 12 Spire | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 771S 701T | 2021-08-09 08:00 | 2021-08-12 17:00 | N | N | 701T maintenance | Terminal Equipment | 771s 701T (771s Veteran) | 701T Maintenance | For Information Only
ALTALINK | 233s T1 (233s Beamer) | 2021-08-09 08:00 | 2021-08-13 12:00 | N | N | NGR maintenance and breaker replacement (233s21) | Transformer | 233s T1 (233s Beamer) | Customer NGR maintenance and breaker replacement (233s21) | For Information Only
ATCO | 732s 901 (732s Mitsue) | 2021-08-09 08:00 | 2021-08-12 12:00 | N | Y | breaker maintenance | Circuit Breaker | 732s 901 (732s Mitsue) | 732S 901 Breaker Maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 2075s 900SST1 (2075s Newell) | 2021-08-09 08:00 | 2021-08-23 17:30 | N | Y | install breaker thermal windows in LV1 room at 2075S Newell and 900SST1 gasket replacements | Transformer | 2075s 900SST1 (2075s Newell) | - Install Breaker Thermal Windows in LV1 Room at 2075S Newell - 900SST1 Gasket Repalcements | 240 kV, For Information Only
ATCO | 7L84 (722s Crystal Lake - 749s Flyingshot Lake) | 2021-08-09 08:00 | 2021-08-18 13:00 | N | Y | modifications to structures 14,59,128, & 129, switch replacement 702A & 7L84D1 | Line | 7L84 (722s Crystal Lake - 749s Flyingshot Lake) | 7L84 line mitigation project Modifications to Structures 14,59,128, & 129 Replace switch 702A & 7L84D1 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 13.2TR (ENMAX 13) | 2021-08-09 08:00 | 2021-08-12 16:00 | N | N | ECI bushings power factor test transformer, check reversing switch, oil sampling MT, TC | Transformer |  | ECI bushings Power factor test transformer. Check Reversing Switch. Oil sampling MT, TC | For Information Only
ENMAX | 16.61L (ENMAX 16 - ENMAX 27), 27.2TR (ENMAX 27) | 2021-08-09 08:00 | 2021-08-10 16:00 | N | N | tapchanger inspection | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2021-08-09 08:00 | 2021-08-27 16:00 | N | Y | line relocation | Line |  | Line relocation at Bow Trail. Phasing required across SW82. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 21.1TR (ENMAX 21) | 2021-08-09 08:00 | 2021-08-20 16:00 | N | N | 21sub TRV project- 21.1TR CT replacement | Transformer |  |  | For Information Only
ATCO | 848s 902 (848s Ruth Lake) | 2021-08-09 08:30 | 2021-08-11 16:30 | N | Y | 902 BKR Maintenance | Circuit Breaker | 848s 902 (848s Ruth Lake) | 902 BKR Maintenance | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 865s 701T (865s Saddlehills) | 2021-08-09 09:00 | 2021-08-12 17:00 | N | N | maintenance, mobile sub installation | Transformer | 865s 701T (865s Saddlehills) | 701 & 701T maintenance. Mobile sub will be installed | For Information Only, Pre-Condition
ALTALINK | 804L (40s Wetaskiwin - 86s Bigstone) | 2021-08-09 09:30 | 2021-08-10 18:00 | N | N | fire mitigation component replacement | Line | 804L (40s Wetaskiwin - 86s Bigstone) | Fire Mitigation Component Replacement Str 48, 49, 87, 90, 91, 92 and 93, See Also 858L RB SAP 275615 Due to proximity to 804/803L | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 42s T2 (42s Sarcee) | 2021-08-09 09:30 | 2021-08-12 16:30 | N | Y | migrate and commission T1 | Transformer | 42s T2 (42s Sarcee) | Migrate and commission all T1 TX18507, 42S63 (289), 42S60 (1152) associated transformer protections, tap changer, breaker, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. . | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 434s T3 (434s East Stony Plain) | 2021-08-09 10:00 | 2021-08-12 18:00 | N | N | replace bushings, repair hot spot on 434s27 | Transformer |  | Replace T3 25kV Bushings. Repair hot spot on 434s27 | For Information Only
ALTALINK | 526s T1 (526s Buffalo Creek) | 2021-08-09 10:00 | 2021-08-12 16:00 | N | N | wiring new CT circuit to new protection and installing 25kV PT on 336L | Transformer |  | wiring new CT circuit to new protection and installing 25kV PT on 336L | For Information Only
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek), 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2021-08-09 10:30 | 2021-08-12 18:00 | N | N |  | Transformer, Line |  | Vacuum fill T1, maintain 138kV s/w's: 308s6,308s7, 308s1, 308s2 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 385s T3 (385s Spring Coulee) | 2021-08-09 11:30 | 2021-08-12 17:30 | N | N | bushing, 25kV breaker replacement | Transformer | 385s T3 (385s Spring Coulee) | T3; 25kV/69kV bushing replacement. 25kV Breaker Replacement (385s112) | For Information Only
ALTALINK | 199L (268s Whitecourt - 199AL tap), 268s 199N (268s Whitecourt) | 2021-08-09 12:00 | 2021-08-11 16:00 | N | N | component replacement 199L (str's range 191-413) | Line, Circuit Breaker | 199L (268s Whitecourt - 199AL) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 900L (17s Benalto - 63s Red Deer) | 2021-08-10 07:00 | 2021-08-12 18:00 | N | Y | phase raiser installation on 900L2 | Line | 900L (17s Benalto - 63s Red Deer) | GOI required for Phase Raiser installation on 900L2 | 240 kV, For Information Only, Affects Cranking Path
ALTALINK | 787L (71s Lamoureux - 787AL tap) | 2021-08-10 07:00 | 2021-08-10 18:00 | N | Y | fire mitigation on structure #8 | Line | 787L (71s Lamoureux - 787AL tap) | Fire mitigation on Structure #8 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
SUNCOR | 29PT-204 (29EDD-18), 29PS-204 (29EDD-18) | 2021-08-10 08:00 | 2021-08-24 18:00 | N | N | maintenance | Transformer, Switch |  | Turn Around Maintenance Testing of High voltage & low voltage Distribution Equipment | For Information Only
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake) | 2021-08-11 07:00 | 2021-08-11 18:00 | N | N | fire mitigation component replacements str 13 and 16 | Line | 858L (40s Wetaskiwin - 289s Saunders Lake) |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 787L (166s Dow Chemical Fort Saskatchewan - 787AL tap), 166s T2 (166s Dow Chemical Fort Saskatchewan), 166s T3 (166s Dow Chemical Fort Saskatchewan) | 2021-08-11 07:00 | 2021-08-11 18:00 | N | Y | PRC5 maintenance on 166s787W, fix broken shroud on CT & maintenance | Line, Transformer | OC studies showed that DOW outflow limit may be 100 MW with both 707L and 787L out-of-service at the same time. |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 34.1TR (ENMAX 34) | 2021-08-11 08:00 | 2021-08-12 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 723L (438s Westlock - 724L tap) | 2021-08-12 07:00 | 2021-08-13 18:00 | N | N | *P5 urgent scope of work includes urgent repair on structures 122C, 122D, 123, 124, 125, 126, 127, 128 and 130 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 732s 903 (732s Mitsue) | 2021-08-12 08:00 | 2021-08-18 15:00 | N | Y | breaker maintenance | Circuit Breaker | 732s 903 (732s Mitsue) | 903 Breaker Maintenance | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | ML1 (D05 Syncrude - Syncrude Mildred Lake) | 2021-08-12 08:00 | 2021-08-12 20:00 | N | N | maintenance | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 2005s 905 (2005s Secord) | 2021-08-12 08:00 | 2021-08-12 11:30 | N | Y | PRC005 trip coil on breaker 905 | Circuit Breaker |  | Test and Operate. PRC005 Trip coil on Breaker 905 | 240 kV, Contingency Requires Mitigation
ALTALINK | 19s 905 (19s Wabamun), 905L (19s Wabamun - 37s North Calder) | 2021-08-12 08:30 | 2021-08-12 17:30 | N | Y | replace grading capacitor on 19s905 240kV breaker | Circuit Breaker, Line | 905L (19s Wabamun - 37s North Calder), 19s 905 (19s Wabamun) |  | 240 kV, Pre-Condition
ATCO | 2005s 906 (2005s Secord) | 2021-08-12 11:45 | 2021-08-12 16:30 | N | Y | PRC005 trip coil on breaker 906 | Circuit Breaker |  | Test and Operate. PRC005 Trip coil on Breaker 906 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, ENMAX | 1109L (ENMAX 25 - ENMAX 65), 25B240-D142 (ENMAX 25), 25B240-D141 (ENMAX 25) | 2021-08-13 08:00 | 2021-08-13 16:00 | N | Y | power factor test 25MD240-1109 LA. 25 Sub SW152, SW153 replace switch | Line, Circuit Breaker | 1109L (ENMAX 25 - ENMAX 65) |  | 240 kV, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-08-13 08:00 | 2021-09-01 18:00 | N | N | replace switches at 29EDD-8 and 29EDD-9 during turn around for 29PL6-24 | Not In Model |  |  | For Information Only
ALTALINK | 233s T2 (233s Beamer) | 2021-08-13 12:30 | 2021-08-17 16:30 | N | N | customer NGR maintenance and breaker replacement (233s22) | Transformer | 233s T2 (233s Beamer) |  | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2021-08-14 08:00 | 2021-08-14 16:00 | N | N | disconnected conservator breather tube | Transformer |  | 28.2TR disconnected conservator breather tube | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks), 525s 850N (525s Carseland) | 2021-08-14 09:15 | 2021-08-14 12:45 | N | Y | connect mobile (475s) | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 525s T3 (525s Carseland) | 2021-08-14 12:46 | 2021-09-15 10:00 | N | N | T3 replacement, 25kV work, SCADA upgrade, and salvage 25kV bypass bus/switches (s20,s24,s25) | Transformer |  |  | For Information Only
SUNCOR | 29PL7-2 (29EDD-18 - 29EDD-63) | 2021-08-15 08:00 | 2021-08-23 18:00 | N | Y | maintenance and testing of 29PT-179 and 30PT-219, 144 kV breakers/switches, GCB and PRC-005 testing | Line |  | Maintenance and testing of 29PT-179 and 30PT-219, 144 kV breakers/switches, GCB and PRC-005 testing (Turn Around) | Restricts Generation
ALTALINK | 83s T1 (83s Taber) | 2021-08-15 11:00 | 2021-08-19 15:30 | N | Y | replace 138 kV LAs, TC filter, 25 kV bushings, and 138 kV bushings on T1 | Transformer |  |  | Restricts Generation
EPCOR | 330p 1208 (330p Genesee) | 2021-08-16 07:00 | 2021-08-20 17:00 | N | Y | emergency lightning spire repair #9 spire | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 14.3TR (ENMAX 14) | 2021-08-16 08:00 | 2021-08-17 16:00 | N | N | tapchanger inspection, oil sampling MT, TC | Transformer |  |  | For Information Only
SUNCOR | 139S Hillridge | 2021-08-16 08:00 | 2021-08-18 17:00 | N | N | breaker positive ground fault and stress cone termination repairs | Station |  | Repair breaker positive ground fault on 52F4 Replace hot stress cone termination at PMTs 139s 52F4 breaker will be removed from service Isolation via 139s 52F4 breaker fully racked out | For Information Only
ENMAX | 8.3TR (ENMAX 8), 8.4TR (ENMAX 8) | 2021-08-16 08:00 | 2021-08-29 16:00 | N | N | switch maintenance | Transformer | 8.3TR (ENMAX 8), 8.4TR (ENMAX 8) | GIS Switch maint. 8SW4A01, 8SW5A51, 8SW5A1, 8SW4A82, 8SW4A02, 8SW4A81, 8SW4A52, 8SW4A10. Check Reversing Switch 8.3TR, 8.4TR. Do not ground 8SW4A51 or 8SW5A52. NGR repl. | For Information Only, Pre-Condition
ENMAX | 3.4TR (ENMAX 3) | 2021-08-16 08:00 | 2021-08-19 16:00 | N | N | testing and maintemance | Transformer |  | ECI Bushings. Power factor test transformer, Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil Sampling, TC. Check reversing switch. | For Information Only
ATCO | 848s 908 (848s Ruth Lake) | 2021-08-16 08:30 | 2021-08-18 16:30 | N | Y | maintenance | Circuit Breaker | 848s 908 (848s Ruth Lake) | 908 BKR Maintenance | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 770s 703T (770s Three Hills) | 2021-08-16 09:00 | 2021-08-25 17:00 | N | N | maintenance | Transformer | 770s 703T (770s Three Hills) | 703T Maintenance | For Information Only
ALTALINK | 3L (42s Sarcee - 272s Springbank), 42s 3W (42s Sarcee) | 2021-08-16 09:30 | 2021-08-18 16:30 | N | N | protection upgrade and testing | Line, Circuit Breaker |  | Migrate and commission all 42s3W (852) & L8-3L at 42s Sarcee associated line protections, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 17s 717W (17s Benalto), 717L (17s Benalto - 262s Rocky Mountain House) | 2021-08-16 09:30 | 2021-08-19 14:30 | N | Y | line A/B protection replacement, tie in new 138B3 'B' CT | Circuit Breaker, Line |  | A/B Line prot replacement. Tie in new 138B3 'B' CT cont | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet) | 2021-08-16 10:30 | 2021-08-17 17:30 | N | Y | PRC5 - 1st trip & maintenance (SF6) | Shunts |  | PRC5 1st Trip & Maintenance (SF6) | 240 kV
ALTALINK | 946L (38s East Edmonton - 89s Ellerslie) | 2021-08-16 12:00 | 2021-08-18 15:00 | N | Y | component replacements 946L (str's range 30-71) | Line | 946L (38s East Edmonton - 89s Ellerslie) |  | 240 kV
ALTALINK | 748L (267s Killarney Lake - 277s Hayter), 749AL (267s Killarney Lake - 749L tap), 267s T1 (267s Killarney Lake), 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2021-08-16 12:00 | 2021-08-20 18:00 | N | N | replacing 267s23 (C2) with a new breaker/switch and VT2 | Line, Transformer, Shunts | 749AL (267s Killarney Lake - 749L), 748L (267s Killarney Lake - 277s Hayter) | Replacing 267s23 (C2) with a new breaker/switch and VT2. See below for complete list of work. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive) | 2021-08-16 12:00 | 2021-08-19 17:30 | N | N | changing poles from test and treat data | Line |  | Changing poles from test and treat data | Creates Radial Feeds, Firm Load Loss
ALTALINK | 268s T3 (268s Whitecourt) | 2021-08-16 12:30 | 2021-08-17 17:30 | N | N | fix oil leaks, hydran, SFRA test | Transformer | 268s T3 (268s Whitecourt) |  | For Information Only
ALTALINK | 528S Blue Trail Wind Farm | 2021-08-17 07:00 | 2021-08-19 17:00 | N | N | maintenance | Station |  |  | For Information Only
ALTALINK | 787AL (906s Ross Creek - 787L tap), 787L (71s Lamoureux - 166s Dow Chemical Fort Saskatchewan) | 2021-08-17 07:00 | 2021-08-18 18:00 | N | Y | maintain, doble and top up oil on transformers | Line | T1: maintain, doble, fix GT, tip up oil, filter motor trouble, rad leak, conservator pipe leak T3: maintain, doble, top up oil, Tx valve leak, TS1 SS sign install. 906s1 needs some adjusting |  | Pre-Condition, Affects Cranking Path
ALTALINK | 727L (65s High River - 142s Magcan - 678s Okotoks), 727AL (142s Magcan - 727L tap) | 2021-08-17 07:15 | 2021-08-18 17:45 | N | N | maintenance (Str 6, 7, 10, 20, 24) | Line | 727AL (142s Magcan - 727L tap) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm) | 2021-08-17 07:15 | 2021-08-19 17:45 | N | Y | salvage 608AL31 airbrake | Line | 608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm) | Salvage 608AL31 Airbrake and install at training yard. | Restricts Generation
ALTALINK | 1018s T2 (1018s Shamrock), 1018s 7290-SW-003 (1018s Shamrock), 1018s 7290-CB-008 (1018s Shamrock) | 2021-08-17 08:00 | 2021-08-31 16:00 | N | N | P1800 Capital Power Whitla Wind Power Facility. ISD August 24, 2021 | Transformer, Switch, Circuit Breaker
Syncrude | Syncrude Mildred Lake | 2021-08-17 08:00 | 2021-08-30 16:35 | N | N | T3 transformer @ Plant 31 Substation | Station | Non-Significant Outage: T3 Transformer (72/13.8kV) @ Plant 31 Substation Following Circuit Breakers will be operated: CB # 335, and 3235 @ Plant 31 Substation Following Switches will be operated: 334 @ Plant 31 Substation |  | For Information Only
Whitla 2 Wind Generation L.P. | WHT2 Whitla 2 | 2021-08-17 08:00 | 2021-11-30 16:00 | N | N | Capital Power Whitla Wind Power Facility: P1800: 97 MW. ISD September 15, 2021 P2338: 54 MW wind. ISD Sept 15, 2021 | Unit
AESO-SC | OATI | 2021-08-17 18:00 | 2021-08-17 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
EPCOR | HDS1 (EPCOR Hardisty), 72CH11 (987s Clover Bar - EPCOR Hardisty) | 2021-08-18 07:00 | 2021-08-18 17:00 | N | N | hot contact repair/maintenance | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 10.2TR (ENMAX 10) | 2021-08-18 08:00 | 2021-08-19 16:00 | N | N | tapchanger inspection, check reversing switch, oil sampling MT, TC | Transformer |  |  | For Information Only
Saskpower | SASK POWER P2C | 2021-08-18 09:00 | 2021-08-19 18:00 | N | N | maintenance | Line |  |  | For Information Only
ALTALINK | 418s Ardenville | 2021-08-19 07:00 | 2021-08-20 19:00 | N | N | maintenance | Station |  |  | Restricts Generation
EPCOR | EP 511s Victoria T1 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria) | 2021-08-19 07:00 | 2021-08-19 17:00 | N | N | VDS4/VDS5 maintenance | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons), 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen), 166s T1 (166s Dow Chemical Fort Saskatchewan), 166s T2 (166s Dow Chemical Fort Saskatchewan), 258s T1 (258s Dow Hydro Carbons), 258s 252 (258s Dow Hydrocarbons), 258s 552 (258s Dow Hydrocarbons) | 2021-08-19 07:00 | 2021-08-19 18:00 | N | Y | 1st trip PRC5 maintenance on 166s862N, fix CT shroud and capacitor mount, 166s899N capacitor mounting kit, T1, replace conservator gauge, fix Hydran monitor warning,166s1 & 166s24 clean and adjust | Line, Transformer, Circuit Breaker |  | 1st trip PRC5 maintenance on 166s862N, fix CT shroud and capacitor mount; 166s899N capacitor mounting kit; T1: replace conservator gauge, fix Hydran monitor warning. 166s1 & 166s24 clean and adjust | Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ATCO | 848s 605 (848s Ruth Lake) | 2021-08-19 08:30 | 2021-08-20 16:30 | N | N | 848S 605 breaker maintenance | Circuit Breaker | 848s 605 (848s Ruth Lake) | 848S 605 BKR Maintenance | Contingency Requires Mitigation
ATCO | 725s 701T (725s Goose River) | 2021-08-19 09:00 | 2021-08-19 19:00 | N | N | repair 701T leaks | Transformer |  | Repair 701T leaks | For Information Only
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan), 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons), 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen), 258s T1 (258s Dow Hydro Carbons), 258s 252 (258s Dow Hydrocarbons), 258s 552 (258s Dow Hydrocarbons) | 2021-08-19 18:00 | 2021-08-20 18:00 | N | Y | migrate alarms and controls from the existing SCADA system to the new system | Transformer, Line, Circuit Breaker |  | Migrate alarms and controls from the existing SCADA system to the new system. This will include 138kV Bus 1 protection, T1 Protection, breakers 258s252, 258s652, and 258s552 controls and status, MOD 258s862X control and status, and 862L protection alarms. | Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
EPCOR | EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), 72RV6 (EP 511s Victoria - Rossdale) | 2021-08-20 07:00 | 2021-08-20 17:00 | N | N | maintenance on VDS9 | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 790L (434s Stony Plain - 790AL tap) | 2021-08-20 07:00 | 2021-08-24 18:00 | N | N | maintenance on structures 68, 69, 96, 97, 103, and 113 | Line | 790L (434s Stony Plain - 790AL tap) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 267s C1 (267s Killarney Lake), 267s C3 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 748L (267s Killarney Lake - 277s Hayter) | 2021-08-20 18:00 | 2021-08-25 18:00 | N | N | replacing 267s23 (C2) with a new breaker/switch and VT2. | Shunts, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 258s T1 (258s Dow Hydro Carbons), 258s 138kV Bus 1 (258s Dowhydrocarbons), 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons) | 2021-08-20 18:00 | 2021-09-03 18:00 | N | Y | migrate alarms and controls from the existing SCADA system to the new system. This will include 138kV Bus 1 protection, T1 Protection, breakers 258s252, 258s652, and 258s552 controls and status, MOD 258s862X control and status, and 862L protection alarms. 166s4 switch replacement and strain insulator replacement on 862L @ 258s | Transformer, Bus, Line |  | Migrate alarms and controls from the existing SCADA system to the new system. This will include 138kV Bus 1 protection, T1 Protection, breakers 258s252, 258s652, and 258s552 controls and status, MOD 258s862X control and status, and 862L protection alarms. 166s4 switch replacement and strain insulator replacement on 862L @ 258s | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
TRANSALTA | 240S McBride Lake | 2021-08-21 08:00 | 2021-08-22 17:00 | N | N | maintenance | Station |  |  | For Information Only
ALTALINK | 244s T1 (244s Bowmanton) | 2021-08-22 10:00 | 2021-08-25 17:30 | N | Y | maintenance, doble, leak repair | Transformer | 244s T1 (244s Bowmanton) |  | 240 kV, For Information Only
ATCO | 809s 503R (809s Louise Creek), 809s 504R (809s Louise Creek) | 2021-08-22 17:00 | 2021-09-09 16:00 | N | N | Louise Creek rebuild project | Shunts |  |  | Pre-Condition
ATCO | 809s 911 (809s Louise Creek) | 2021-08-22 17:00 | 2021-08-30 13:40 | N | Y | louise creek rebuild project | Circuit Breaker |  | Louise Creek Rebuild project Upgrade - 809S 911 BKR Replacement To be issued once the work on 809S 901T is complete. On August 30th once the GOI for 809S 902T (2-50617) is issued this permit will be released as it will be within the zone of that GOI | 240 kV, Pre-Condition
ATCO | 9L939 (77s Sagitawah - 809s Louise Creek) | 2021-08-22 17:00 | 2021-08-27 14:00 | N | Y | louise creek rebuild project | Line |  | Louise Creek Rebuild project- Replace 911. 9L939 needs to be out of service as it runs over the top of 911 breaker inside the substation | 240 kV, Overload, Affects Cranking Path
EPCOR | 72MG16 (Garneau - Meadowlark), MDS8 (Meadowlark) | 2021-08-23 07:00 | 2021-08-27 17:00 | N | N | CVT and arrestor doble, maintenanace | Line, Switch | Meadowlark MDS8 LCR and MDS10 Maintenance, 72MG16 CVT and Arrestor Doble |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72JW19 (805s Jasper - Woodcroft), 805s J724 (805s Jasper) | 2021-08-23 07:00 | 2021-08-25 16:40 | N | N | CVT/arrestor doble, maintenance | Line, Circuit Breaker | 72JW19 (805s Jasper - Woodcroft) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 133S Stelco Edmonton | 2021-08-23 07:00 | 2021-08-26 08:00 | N | N | cleaning switchgear and adjusting switches | Station | Customer outage for cleaning switchgear and adjusting switches (133s7). PCA to extend a grounded GOI to AltaSteel |  | For Information Only
ENMAX | 9.2TR (ENMAX 9) | 2021-08-23 08:00 | 2021-08-25 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ATCO | 763s 602T (763s Hanna) | 2021-08-23 08:00 | 2021-08-26 17:00 | N | N | transformer maintenance | Transformer |  | 602T Transformer maintenance. Install the mobile sub onto the 72KV bus, connected to 500D4 | For Information Only
ENMAX | 5B138-5BT7 (ENMAX 5) | 2021-08-23 08:00 | 2021-10-06 16:00 | N | N | replace circuit breaker | Circuit Breaker |  |  | For Information Only
ENMAX | 21.2TR (ENMAX 21) | 2021-08-23 08:00 | 2021-09-03 16:00 | N | N | CT replacement | Transformer | 21sub TRV Project. 21.2TR CT Replacement. Gas relay testing. Transformer maintenance. Oil Sampling TC, MT |  | For Information Only
ATCO | 796s 702TCS (796s Nipisi), 796s 702T (796s Nipisi) | 2021-08-23 08:00 | 2021-08-25 17:00 | N | N | 702TCS and 702T Maintenance | Circuit Breaker, Transformer | 796s 702T (796s Nipisi) | 702TCS and 702T Maintenance. Hot line crew booked to cut in J1 between the 144KV bus and 702TCS on Monday Aug 23, Tap back up on Thursday Aug 26th. | For Information Only
ATCO | 848s 601 (848s Ruth Lake) | 2021-08-23 08:30 | 2021-08-26 16:30 | N | N | breaker maintenance | Circuit Breaker | 848s 601 (848s Ruth Lake) | 601 BKR Maintenance | For Information Only
ENMAX | 12.1TR (ENMAX 12) | 2021-08-23 08:50 | 2021-09-05 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ATCO | 846s 702T (846s Grand Centre) | 2021-08-23 09:00 | 2021-08-25 12:00 | N | N | transformer test | Transformer | 846s 702T (846s Grand Centre) | Complete major Testing on 702T, Load from 702T will be transferred to 701T for duration. | For Information Only
ALTALINK | 42s T1 (42s Sarcee) | 2021-08-23 09:30 | 2021-08-26 16:30 | N | Y | migrate and commission | Transformer | 42s T1 (42s Sarcee) | Migrate and commission all T1 TX18508, 42S44 (189), 42S40 (252) associated transformer protections, tap changer, breaker, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. . | 240 kV, Contingency Requires Mitigation
ALTALINK | 332s T1 (332s Ellis) | 2021-08-23 09:30 | 2021-08-24 17:30 | N | N | LTC controller replacement | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside) | 2021-08-23 09:30 | 2021-08-24 17:00 | N | Y | line isolation for new RTU at summerside | Line | 1057L (89s Ellerslie - 657s Summerside) | Isolate 1057L to cut over controls, status, alarms to new RTU at Summerside | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 17s T1 (17s Benalto) | 2021-08-23 09:30 | 2021-09-01 14:30 | N | N | breaker trip tests | Transformer | 17s T1 (17s Benalto) | T1 high side slip on CT's , T1/VR1 prot upgrade, s48 MOD control module repl, 25kv breaker trip tests, Tie in new 138B3 'B' CT cont | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2021-08-23 10:00 | 2021-08-30 15:00 | N | Y | crossarm changing | Line | 7L32 (813s Little Smoky - 862s South Bezanson) | Crossarm changing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2021-08-23 12:00 | 2021-08-25 16:40 | N | Y | component replacements | Line | Component Replacements 947L (Str's Range 2-88) |  | Pre-Condition, Affects Cranking Path
ATCO | 809s 704 (809s Louise Creek), 809s 705 (809s Louise Creek), 809s 706 (809s Louise Creek), 809s 901T (809s Louise Creek), 7L19 (809s Louise Creek - 851s Morse River), 7L55 (743s Sarah Lake - 809s Louise Creek) | 2021-08-23 13:00 | 2021-08-23 15:00 | N | Y | outage to remove existing 700PT | Circuit Breaker, Transformer, Line |  | Aug 23, 2021 13:00 -15:00 - 144Kv Bus partial outage, 809S 901T OOS, 7L19 OOS, 7L55 OOS 7L43 tied to 7L56 with N.O. 809S 700D1 - 2 Hour outage to remove existing 700PT and Cut in J1 jumper. See attached SLD -Isolation points:809S 700B, 809S 7L43D1, 809S 7L55D1, 809S 7L19D1, 809S 701A | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 809s 704 (809s Louise Creek), 809s 705 (809s Louise Creek), 809s 901T (809s Louise Creek), 7L55 (743s Sarah Lake - 809s Louise Creek) | 2021-08-23 15:00 | 2021-08-25 09:30 | N | Y | install and commission new 700PT | Circuit Breaker, Transformer, Line |  | Aug 23, 2021 15:00 - Aug 25, 2021 09:30 - 144Kv Bus partial outage, 7L55 OOS, 7L43 tied to 7L56 - Install New 700PT1 - Isolation Points: J1, 7L43D1, 7L55D1 - install and commission new 700PT. Work will proceed under fair weather conditions only | 240 kV, Pre-Condition
ENMAXGPI | 134s RTU/SCADA (134s Taber Wind Farm) | 2021-08-23 17:00 | 2021-08-23 18:00 | N | N | troubleshoot failover between redundant communication paths | Terminal Equipment |  | Troubleshoot failover between redundant communication paths and Collect data to determine if failover process can be improved. Visibility of the farm active power and reactive power output would be lost. The AESO would not be able to provide a signal for facility limit. A wind farm operator will be at the farm and could limit output upon request. Voltage regulation would remain in operation. Set point could be changed by operator if necessary. | Affects Visibility
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2021-08-24 07:00 | 2021-08-26 18:00 | N | N | line clearance mitigation between Structures #141 - 143 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island | 2021-08-24 08:00 | 2021-09-08 18:00 | N | N | replacement of B protection upgrade | Line | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island, 29EDD-1 29EDD1s1152 (29EDD-1 Millennium) | 29PL6-6 ( L5), from 29 EDD-1 / 29EDD-2: (estimated dates August 22 to September 10) - 72kV line 29PL-6-6 (L5) outage for replacement of B Protection Upgrade | Contingency Requires Mitigation, Pre-Condition
SUNCOR | 635PL9-1000 (2005s Secord - 635EDD-1000) | 2021-08-24 08:00 | 2021-09-07 17:00 | N | Y | line structure change for line lift, maintenance | Line |  | 260kV line structure change for line lift; maintenance of 260kV line, transformer, associated equipment and protection | 240 kV, Creates Radial Feeds, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2021-08-24 08:00 | 2021-09-30 23:00 | N | N | 29EDD-2 252 5024 replace air blowers & rebuild cell | Not In Model | Not modelled in EMS or PSSE | - 29EDD-2 252-5204 Replace Air Blowers & rebuild cell during STG4 outage, 29PT2 OLTC service, replace winding RTD | For Information Only
ALBIAN, ATCO | 919s 907 (919s Hartley), 9LJH2 (919s Hartley - 920s Jackpine) | 2021-08-24 09:00 | 2021-08-24 14:00 | N | Y | PRC005 trip coil testing, test and operate 907 | Circuit Breaker, Line |  | PRC005 Trip coil testing. Test and operate 907 | 240 kV, Creates Radial Feeds, Firm Load Loss
ALBIAN | 920s 902T (920s Jackpine), 920s 902 (920s Jackpine) | 2021-08-24 09:00 | 2021-08-24 14:00 | N | Y | PRC-005 - trip coil testing | Transformer, Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 902, 920S 902T OOS | 240 kV, For Information Only
ALTALINK | 5s C3 (5s East Calgary), 5s 752 (5s East Calgary) | 2021-08-24 09:30 | 2021-08-24 17:00 | N | N | breaker maintenance | Shunts, Circuit Breaker | 5s C3 (5s East Calgary) |  | Pre-Condition
ALTALINK | 500s T2 (500s Flatbush) | 2021-08-24 10:00 | 2021-08-25 16:00 | N | N | isolation & grounding required for Plains Midstream | Transformer |  | Isolation & grounding required for Plains Midstream | For Information Only
ATCO | 930s 709 (930s Arcenciel) | 2021-08-24 13:00 | 2021-08-24 14:00 | N | N | prc trip coil testing | Circuit Breaker |  | prc trip coil testing | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 930s SVC (930s Arcenciel), 930s 718 (930s Arcenciel) | 2021-08-24 13:00 | 2021-08-28 15:30 | N | Y | SVC air cooling maintenance, various PRC relay testing | Shunts, Circuit Breaker |  | SVC air cooling maintenance, various PRC relay testing | Pre-Condition
ATCO | 930s 717 (930s Arcenciel), 930s 717C (930s Arcenciel) | 2021-08-24 14:00 | 2021-08-24 15:30 | N | N | prc trip coil testing | Circuit Breaker, Shunts |  | prc trip coil testing. 717C OOS for duration | Pre-Condition
BCH | 1L274 (EFT - 1D2L274) | 2021-08-25 | 2021-08-25 08:00 | N | Y | EFD T1 station work | Line | 1L274 (EFT - 1D2L274) | structure refurbishment EFD T1 station work. Outage scheduled Aug 24 2300 to Aug 25 0300. AESO/AML supplies GRH and FRO | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 13s T2 (13s Deerland), 808L (13s Deerland - 808AL tap), 815L (13s Deerland - 127s Bruderheim) | 2021-08-25 07:00 | 2021-08-25 19:00 | N | Y | replace 13s JBDC3 with new junction box | Transformer, Line | 13s T2 (13s Deerland), 808L (13s Deerland - 808AL tap), 815L (13s Deerland - 127s Bruderheim) | Replace 13s JBDC3 with new junction box. DC from the JB supplies 13s101, 13s452, 13s152, 13s552, 13s808N and 13s815W. | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 104s T1 (104s Watson Creek) | 2021-08-25 07:00 | 2021-08-25 20:00 | N | N | complete reconfiguration of T1 to TMPL new equipment | Transformer |  |  | For Information Only
EPCOR | G723 (Garneau) | 2021-08-25 07:00 | 2021-08-25 17:00 | N | N | investigate/repair G723 RTU close issue | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 225L (67s Stirling - 225s Magrath), 225AL (313s Raymond Reservoir - 225L tap) | 2021-08-25 07:15 | 2021-08-26 17:45 | N | Y | urgent repair to change arms and insulators on structures 97, 98 and 99. | Line |  | Scope of work includes urgent repair to change arms and insulators on structures 97, 98 and 99. | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | Bonnybrook BON1 | 2021-08-25 08:00 | 2022-02-01 16:00 | N | N | P2395. 10 MW. ISD Nov 30, 2021 | Unit
SUNCOR | 29EDD-1 72kV North Bus (29EDD-1 Millennium), 29EDD-1 T2 (29EDD-1 Millennium), 29EDD-1 29EDD1s1152 (29EDD-1 Millennium), 29EDD-1 29EDD1s1552 (29EDD-1 Millennium), 29EDD-1 260kV North Bus 2 (29EDD-1 Millennium), 29EDD-1 29EDD1s752 (29EDD-1 Millennium), 29EDD-1 29EDD1s952 (29EDD-1 Millennium) | 2021-08-25 08:00 | 2021-09-08 18:00 | N | Y | preventative maintenance | Bus, Transformer, Circuit Breaker |  | North Bus work is contingent on South Bus being completed North Bus will not be isolated until South Bus has returned to service. 29EDD1 X72 (North Bus) (estimated dates August 22nd to September 2nd) Preventative Maintenance for: - 29EDD-1T2 + Relays + Meter + IR windows, 29EDD-1S1152 + CT's, Tap Changer - N72B1, 29EDD-1S57/1S52/1S53/1S1552/1S25/1S22, 29PVT-1A/B/C - N260B2 + Relays, 29EDD-1S14 / 1S17 / 1S21 / 1S952, 29CVT-13A/B/C, 29EDD-1 Relay controller - 29EDD-1S752, 29CT-7A/B/C Note - Part of Suncor Turn Around | Pre-Condition
ALTALINK | 33s 3 (33s Spray) | 2021-08-25 08:00 | 2021-08-26 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 33s 6 (33s Spray) | 2021-08-25 08:00 | 2021-08-26 16:00 | N | Y | maintenance | Switch |  | Brushgear | Restricts Generation
ALTALINK | 33s 2 (33s Spray) | 2021-08-25 08:00 | 2021-08-25 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek) | 2021-08-25 08:00 | 2021-08-26 17:30 | N | N | urgent followup for further testing after recent maintenance | Transformer |  |  | For Information Only
REDDEER | 217s T2 (217s North Red Deer) | 2021-08-25 09:00 | 2021-09-10 15:00 | N | N | P&C revisions for replacement project | Transformer | 217s T2 (217s North Red Deer) |  | For Information Only
ATCO | 809s 704 (809s Louise Creek), 809s 705 (809s Louise Creek), 809s 706 (809s Louise Creek), 809s 901T (809s Louise Creek), 7L55 (743s Sarah Lake - 809s Louise Creek), 7L19 (809s Louise Creek - 851s Morse River) | 2021-08-25 09:30 | 2021-08-25 11:30 | N | Y | re-attach Jumper J1 at 809S | Circuit Breaker, Transformer, Line |  | .Aug 25, 2021 09:30 - 11:30 - 144Kv Bus partial outage, 809S 901T OOS, 7L19 OOS, 7L55 OOS 7L43 tied to 7L56 with N.O. 809S 700D1 - 2 Hour outage to Re-attach Jumper J1 at 809S - Isolation points:809S 700B, 809S 7L43D1, 809S 7L55D1, 809S 7L19D1, 809S 701A - 7L43 & 7L56 Tie Split at end of this work open N.O. 809S 700D1 Work will proceed under fair weather conditions only | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 846s 701T (846s Grand Centre) | 2021-08-25 12:00 | 2021-08-25 16:40 | N | N | complete major testing on 701T | Transformer | 846s 701T (846s Grand Centre) | Complete major Testing on 701T, Load from 701T will be transferred to 702T for duration. | For Information Only, Pre-Condition
ALTALINK | 233s T1 (233s Beamer) | 2021-08-25 13:00 | 2021-08-26 11:00 | N | N | customer urgent repair of switchgear | Transformer |  |  | For Information Only
ATCO | 738s 701T (738s Virginia Hills) | 2021-08-25 14:00 | 2021-09-10 12:00 | N | N | transformer maintenance and leak mitigation | Transformer |  | 701T Maintenance and leak mitigation Hot line crew to tap up mobile on Aug 25th | For Information Only
EPCOR | 1058L (657s Summerside - EP 803s Lambton) | 2021-08-26 07:00 | 2021-08-27 17:00 | N | Y | isolate 1058L to cut over alarms, status and controls to new RTU at summerside | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 33s 138kV Bus (33s Spray), 113L (20s Ghost - 33s Spray), 76L (33s Spray - 115s Mt. Allan), 84L (33s Spray - 35s Rundle) | 2021-08-26 08:00 | 2021-08-26 16:00 | N | Y | 33s5 switch maintenance | Bus, Line |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ATCO | 9L59 (801s Anderson - 972s Tinchebray) | 2021-08-26 08:00 | 2021-08-26 17:00 | N | Y | change angle pole | Line | 9L59 (801s Anderson - 972s Tinchebray) | Change Angle Pole | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 848s 905 (848s Ruth Lake) | 2021-08-26 08:30 | 2021-08-26 16:30 | N | Y | maintenance | Circuit Breaker | 848s 905 (848s Ruth Lake) | 905 BKR Maintenance | 240 kV, Contingency Requires Mitigation
ALTALINK | 285s T1 (285s East Camrose) | 2021-08-26 16:30 | 2021-09-16 19:00 | N | N | cutover feeders on the 25 kV North bus to new switchgear building #1, close open points G-M | Transformer |  | Cutover feeders on the 25kV North bus to new switchgear building #1. Close Open Points G-M. Go to RSLD 1a for Salvage Release at the start of return switching. Go to RSLD2 at the end of the outage. | For Information Only
ALTALINK | 33s 5 (33s Spray) | 2021-08-26 17:00 | 2021-09-05 17:00 | N | N | maintenance | Switch |  | Spray One Turbine Inspection | Restricts Generation
ALTALINK | 820L (67s Stirling - 820AL tap), 820L (254s Coaldale - 820AL tap), 820AL (315s Chin Chute - 820L tap) | 2021-08-27 07:15 | 2021-08-27 17:45 | N | Y | scope of work includes urgent repair to replace structure 283 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 740L (426s Coalspur - 740L tap), 501L (426s Coalspur - 501CL tap), 426S Coalspur | 2021-08-27 07:30 | 2021-08-27 16:30 | N | N | close open point E on 501L and disconnect 474s Mobile Low side cables from 501L | Line, Station |  | Close Open Point E on 501L and disconnect 474s Mobile Low side cables from 501L | For Information Only
ALTALINK | 740L (426s Coalspur - 740L tap), 426s 1 (426s Coalspur) | 2021-08-27 07:30 | 2021-08-27 16:30 | N | N | hot line work close open point 'D' on 740L and disconnect mobile cables from 762L | Line, Switch |  | HOT LINE WORK Close Open Point 'D' on 740L and disconnect mobile cables from 762L | For Information Only
ALTALINK | 233s T2 (233s Beamer) | 2021-08-27 13:00 | 2021-08-29 11:00 | N | N | customer Switchgear work | Transformer |  |  | For Information Only
ENMAX | 5.10TR (ENMAX 5) | 2021-08-28 07:00 | 2021-08-30 18:00 | N | N | remove existing NGR and install new NGR | Transformer |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy), 814s B2401 (814s Bellamy), 814s B2407 (814s Bellamy) | 2021-08-28 07:00 | 2021-08-29 19:00 | N | Y | oil clean up and inspection, doble | Transformer, Circuit Breaker | 814s T1 (814s Bellamy), 814s B2407 (814s Bellamy), 814s B2401 (814s Bellamy) | Bellamy TX1 Oil Clean up and inspection, Doble Bellamy TX1 PT | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 691L (74s Janet - 419s Chestermere) | 2021-08-29 08:00 | 2021-08-29 17:30 | N | Y | replace breaker 74s691 grading capacitors | Line |  | Replace Breaker 74s691 Grading Capacitors | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 15.2TR (ENMAX 15) | 2021-08-29 08:00 | 2021-10-01 16:00 | N | N | install new Albarrie, plastibeton, duct banks and cables, phasing required on return | Transformer |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2021-08-29 08:00 | 2021-10-01 16:00 | N | N | install new Albarrie, plastibeton, duct banks and cables, phasing required on return | Transformer |  |  | For Information Only
ATCO | 930s 702T (930s Arcenciel), 930s Syn Condenser (930s Arcenciel) | 2021-08-29 09:00 | 2021-08-31 17:00 | N | Y | 702T maintenance, PRC testing | Transformer, Shunts |  | 702T Maintenance, PRC Testing | Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8), 8B138-3A0 (ENMAX 8), 8B138-4A0 (ENMAX 8), 1B138-10A0 (ENMAX 1), 1B138-1A0 (ENMAX 1) | 2021-08-29 12:00 | 2021-08-29 16:00 | N | N | return 8.3TR, 8.4TR bus section | Line, Circuit Breaker |  | Outage required to return 8.3TR, 8.4TR bus section | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | EP 803s LDS4 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s T2 (EP 803s Lambton) | 2021-08-30 07:00 | 2021-08-30 17:00 | N | Y | LDS4 disconnect maintenance | Switch, Circuit Breaker, Transformer | EP 803s L2402 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T4 (Rossdale), RR729 (Rossdale), R724 (Rossdale) | 2021-08-30 07:00 | 2021-09-10 17:00 | N | N | backfill replacement: RW3-RV2 crossing | Transformer, Circuit Breaker | T4 (Rossdale), RR729 (Rossdale), R724 (Rossdale) | backfill replacement: RW3-RV2 Crossing (1007205) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 385s 226 (385s Spring Coulee), 225L (229s Glenwood - 385s Spring Coulee) | 2021-08-30 07:00 | 2021-08-30 12:30 | N | N | urgent switch hot spot repair | Switch, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T2 (Strathcona), S723 (Strathcona) | 2021-08-30 07:00 | 2021-09-09 17:00 | N | N | strathcona TX2 replacement | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 665s T2 (665s Dome) | 2021-08-30 07:00 | 2021-09-10 17:00 | N | Y | replace 240 kV bushings | Transformer | 665s T2 (665s Dome) | replace 240kV bushings (1007378) | 240 kV, For Information Only
ENMAX | 38.1TR (ENMAX 38) | 2021-08-30 08:00 | 2021-09-03 16:00 | N | N | ECI bushing, power factor test transformer and transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 26.1TR (ENMAX 26) | 2021-08-30 08:00 | 2021-09-01 12:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2021-08-30 08:00 | 2021-09-02 17:00 | N | Y | clearance mitigation | Line | 7L91 (715s Leming Lake - 826s Marguerite Lake) | Clearance Mitigation GOI on 7L91 HOP on 7L66 | Pre-Condition, Restricts Generation
ENMAX | 16.1TR (ENMAX 16), 16.61L (ENMAX 16 - ENMAX 27), 15.62L (ENMAX 15 - ENMAX 16), 16.60L (ENMAX 16 - ENMAX 34) | 2021-08-30 08:00 | 2021-09-02 16:00 | N | N | power factor test transformer, transformer maintenance, gas relay testing, check reversing switch and oil sampling MT, TC. | Transformer, Line |  | Power factor test transformer, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil Sampling MT, TC. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s 637 (17s Benalto), 637L (17s Benalto - 580s Sylvan Lake) | 2021-08-30 08:00 | 2021-08-30 16:00 | N | N | tie in new 138B3 'B' CT cont & trip test 17s637 | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L113 (853s Ring Creek - 930s Arcenciel) | 2021-08-30 09:00 | 2021-08-30 15:30 | N | Y | Time Domain Line Protection Project for circuit modifications required to install new relays at Ring Creek 853S & Arcenceil 930S substations | Line | 7L113 (853s Ring Creek - 930s Arcenciel) | Time Domain Line Protection Project for circuit modifications required to install new relays at Ring Creek 853S & Arcenceil 930S Substations. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 74s 2752 (74s Janet) | 2021-08-30 09:00 | 2021-08-31 17:30 | N | Y | replace breaker 74s2752 grading capacitors | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
BCH | 5L91 (Ashton Creek - Selkirk) | 2021-08-30 09:00 | 2021-09-01 17:00 | N | Y | structure replacemen | Line | 5L91 (Selkirk - Ashton Creek) | structure replacement, BC maintenance does not affect the Alberta ATC | 500 kV, Limits ATC, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 42s 28 (42s Sarcee), 28B138-28.80 (ENMAX 28) | 2021-08-30 09:00 | 2021-09-01 17:00 | N | Y | migrate and commission line protections, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN | Line, Circuit Breaker | 28.80L (42s Sarcee - ENMAX 28) | Migrate and commission all 42s28 (652) & L6-28.80L at 42s Sarcee associated line protections, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. . | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 170L (632s Russell - 799s Coleman) | 2021-08-30 09:15 | 2021-09-03 17:45 | N | Y | fire mitigation; structure replacements strs 48-54 | Line | 170L (632s Russell - 799s Coleman) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 320p T4 (320p Keephills) | 2021-08-30 09:30 | 2021-09-02 18:30 | N | N | T4 replace oil, fix leaky explosion tube, change high and low side neutral bushings | Transformer |  |  | For Information Only
ALTALINK | 38s T3 (38s East Edmonton) | 2021-08-30 10:00 | 2021-08-31 18:00 | N | N | maintenance on T3. leak repair and SFRA test | Transformer | 38s T3 (38s East Edmonton) |  | For Information Only
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2021-08-30 12:00 | 2021-09-03 18:00 | N | Y | component replacements 947L (str's range 2-88) | Line | 947L (89s Ellerslie - 987s Clover Bar) |  | 240 kV, Affects Cranking Path
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2021-08-30 12:00 | 2021-08-31 17:00 | N | N | changing poles from test and treat data | Line |  | Changing poles from test and treat data | Creates Radial Feeds, Firm Load Loss
ALTALINK | 40s T2 (40s Wetaskiwin) | 2021-08-30 12:30 | 2021-09-02 17:30 | N | N | fix leaks, maintain, doble, bushing replacements | Transformer | 40s T2 (40s Wetaskiwin) |  | For Information Only
ALTALINK | 526s T1 (526s Buffalo Creek) | 2021-08-30 13:00 | 2021-09-01 17:00 | N | N | T1 doble, remove nest. VR1 maintain, doble, fix heater, fix leaks | Transformer | 526s T1 (526s Buffalo Creek) |  | For Information Only
ATCO | 9L938 (77s Sagitawah - 809s Louise Creek), 809s 902T (809s Louise Creek), 809s 910 (809s Louise Creek), 809s 911 (809s Louise Creek), 809s 912 (809s Louise Creek), 809s 702 (809s Louise Creek) | 2021-08-30 14:00 | 2021-10-04 17:00 | N | Y | Louise Creek Rebuild project upgrade 902T protection, replace 911 breaker | Line, Transformer, Circuit Breaker |  | Louise Creek Rebuild project Upgrade 902T protection. Replacing 809S 911 BKR | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
AESO-SC | OATI | 2021-08-30 17:30 | 2021-08-30 18:30 | N | N | upgrade one of their Storage Area Networks (SAN) | SCInternal |  | upgrade one of their Storage Area Networks (SAN) | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-08-31 06:00 | 2021-09-01 07:00 | N | Y | maintenance | Switch |  | Fall leakdown test. | For Information Only, Restricts Generation
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-08-31 06:00 | 2021-09-01 07:00 | N | Y | maintenance | Switch |  | Fall leakdown test. | For Information Only, Restricts Generation
EPCOR | W722 (Woodcroft) | 2021-08-31 07:00 | 2021-08-31 17:00 | N | N | CT doble | Circuit Breaker | W722 (Woodcroft) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s 46 (17s Benalto), 17s 2852 (17s Benalto), 17s T3 (17s Benalto) | 2021-08-31 08:00 | 2021-08-31 11:00 | N | Y | trip test | Switch, Circuit Breaker, Transformer | 17s 46 (17s Benalto), 17s 2852 (17s Benalto), 17s T3 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L04 (ATC 793s West Peace River - 839s Daishowa), ATC 793s 704 (ATC 793s West Peace River) | 2021-08-31 08:00 | 2021-09-01 16:00 | N | Y | maintenance PM | Line, Circuit Breaker |  | Complete 704 Maintenance PM, Mercer is aware they will be islanded for the duration | Restricts Generation
ATCO | 840s 511 (840s McNeill) | 2021-08-31 08:30 | 2021-08-31 17:00 | N | N | 511 breaker maintenance | Circuit Breaker |  | 511 breaker maintenance. | For Information Only
ALTALINK | 370s T3 (370s North Lethbridge) | 2021-08-31 08:30 | 2021-09-01 16:30 | N | Y | clean up oil spill and repair leak | Transformer | 370s T3 (370s North Lethbridge) |  | 240 kV, Overload, Pre-Condition
ATCO | 6L02 (757s Battle River - 765s Mannix Mine), 757s 604 (757s Battle River) | 2021-08-31 08:45 | 2021-08-31 17:30 | N | N | repair | Line, Circuit Breaker |  | 604 Repair. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 822s 701T (822s Wolf Lake) | 2021-08-31 09:00 | 2021-09-02 16:00 | N | N | complete major testing | Transformer | 822s 701T (822s Wolf Lake) | Complete major Testing on 701T | For Information Only
ALTALINK | 17s 92 (17s Benalto), 17s 91 (17s Benalto) | 2021-08-31 11:30 | 2021-08-31 14:30 | N | N | trip test | Circuit Breaker, Switch | 17s 92 (17s Benalto) |  | Contingency Requires Mitigation, Pre-Condition
SUNCOR | 30PL2-1 (30EDD-1 - 30EDD-2) | 2021-09-01 06:00 | 2021-09-14 18:00 | N | N | 5y replace bushings in 621T in 30EDD-1 | Line | 30EDD2;30PL2-1 SYSTEM;PM 5y Replace Bushings in 621T in 30EDD-1 30EDD-1 621T Oil Leaks |  | For Information Only
ALTALINK | 409s T2 (409s Shell Scotford) | 2021-09-01 07:00 | 2021-09-08 08:00 | N | N | install new 409s102 breaker | Transformer |  |  | For Information Only
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2021-09-01 07:00 | 2021-09-01 17:00 | N | N | line arrestor doble | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 700L (422s Westwood - 746s Sherwood Park), 746L (700L tap - 746AL tap) | 2021-09-01 07:00 | 2021-09-01 18:00 | N | N | maintenance on structures 32, 33, 34, 36 and 116 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 225L (225s Magrath - 385s Spring Coulee) | 2021-09-01 07:15 | 2021-10-08 17:45 | N | N | rebuilding from structure 282 to 400. | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 17s 51 (17s Benalto), 17s 757N (17s Benalto), 757L (17s Benalto - 758L tap) | 2021-09-01 08:00 | 2021-09-01 11:00 | N | N | trip test | Switch, Circuit Breaker, Line | 17s 757N (17s Benalto), 17s 51 (17s Benalto), 757L (17s Benalto - 758L tap) |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
Saskpower | SASK POWER P2C | 2021-09-01 08:00 | 2021-09-04 18:00 | N | N | forced outage | Line |  |  | For Information Only
SUNCOR | 635PL9-1000 (2005s Secord - 635EDD-1000), 635EDD-1000 635-752-111 (635EDD-1000), 635EDD-1000 635-752-121 (635EDD-1000), 635EDD-1000 635-752-131 (635EDD-1000), 635EDD-1000 635-752-142 (635EDD-1000), 635EDD-1000 635-752-152 (635EDD-1000), 635EDD-1000 635-752-161 (635EDD-1000) | 2021-09-01 08:00 | 2021-09-06 17:00 | N | Y | bus-side disconnect repairs | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap) | 2021-09-01 08:00 | 2021-09-01 17:00 | N | Y | topping up the low oil and N2 in P2. | Line |  | Topping up the low oil and N2 in P2. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 525s 850N (525s Carseland), 850L (525s Carseland - 678s Okotoks) | 2021-09-01 08:30 | 2021-09-01 12:00 | N | Y | commission new T3 'B' protection breaker fail trip | Circuit Breaker, Line | Demo old T3 'S' Protection breaker fail trip. Cut in and commission new T3 'B' protection breaker fail trip and new VR2 protection trip to 525s850N. Re-prove breaker fail protection trip to 525s45 (525s45 to remain closed/in service at all times) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 840s 512 (840s McNeill) | 2021-09-01 08:30 | 2021-09-01 16:30 | N | N | breaker maintenance | Circuit Breaker |  | Breaker 512 Maintenance | For Information Only
ALBIAN, ATCO | 920s 901T (920s Jackpine), 920s 901 (920s Jackpine), 9LJH1 (919s Hartley - 920s Jackpine), 919s 905 (919s Hartley) | 2021-09-01 09:00 | 2021-09-01 16:00 | N | Y | prc-005 trip coil testing breaker 901 | Transformer, Circuit Breaker, Line |  | PRC-005 - TRIP COIL TESTING - BREAKER 901, 920S 901T OOS, Test and operate 905 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 2852 (74s Janet) | 2021-09-01 09:00 | 2021-09-02 17:30 | N | Y | replace grading capacitors | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
Saskpower | Sask Power AS902, Sask Power AS905 | 2021-09-01 09:00 | 2021-09-01 15:00 | N | N | SPC maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 26.2TR (ENMAX 26) | 2021-09-01 12:00 | 2021-09-03 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ALTALINK | 851L (253s Blackie - 525s Carseland), 525s 851X (525s Carseland) | 2021-09-01 12:30 | 2021-09-01 16:00 | N | Y | commission protection breaker fail trip | Line, Circuit Breaker | Demo old T3 'S' Protection breaker fail trip. Cut in and commission new T3 'B' protection breaker fail trip and new VR2 protection trip to 525s851X. Re-prove breaker fail protection trip to 525s45 (525s45 to remain closed/in service at all times) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 17s 717W (17s Benalto) | 2021-09-01 12:30 | 2021-09-01 16:30 | N | Y | trip test | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 409s T2 (409s Shell Scotford) | 2021-09-02 07:00 | 2021-09-08 08:30 | N | N | oil reclamation & maintenance | Transformer | 409s T2 (409s Shell Scotford) | 409s T2 Oil reclamation & maintenance. Transition to 409s 138 kV Bus 1, T2, & 856L - GOI | For Information Only
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake), 811s 707 (811s Clairmont Lake) | 2021-09-02 08:00 | 2021-09-02 17:00 | N | Y | leak repair and oil top up on 707 CT | Line, Circuit Breaker |  | GOI for leak repair and oil top up on 707 CT. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 2B138-D83 (ENMAX 2), 2B138-D84 (ENMAX 2) | 2021-09-02 08:00 | 2021-09-05 16:00 | N | N | Sub 2 - replace BMR2 relay and commission | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ATCO | 6L97 (735s Swan River - 739s Edith Lake) | 2021-09-02 08:00 | 2021-09-05 14:00 | N | N | changing poles from test and treat data | Line |  | changing poles from test and treat data | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12), 12.1TR (ENMAX 12) | 2021-09-02 08:00 | 2021-09-05 18:00 | N | Y | urgent - 12.1 TR oil level alarm, remove leaking radiator and remediate oil spil | Line, Transformer | 832L (ENMAX 10 - ENMAX 12) | 12.1TR oil level alarm, radiator leak. Outage required to remove leaking radiator and remediate oil spill. 12.1TR already OOS | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 320p 52 (320p Keephills) | 2021-09-02 08:30 | 2021-09-04 20:30 | N | Y | maintenance | Switch |  |  | For Information Only, Pre-Condition
ATCO | 840s 502 (840s McNeill) | 2021-09-02 08:30 | 2021-09-02 16:30 | N | N | breaker maintenance | Circuit Breaker |  | Breaker 502 Maintenance | Pre-Condition
BCH | 5L96 (Selkirk - Vaseux Lake) | 2021-09-02 09:00 | 2021-09-03 17:00 | N | Y | insulator replacement | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2021-09-02 09:00 | 2021-09-02 16:00 | N | N | working on structure 440132/ 6L12-462 | Line |  | GOI for Working on structure 440132/ 6L12-462. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 987s C2402 (987s Clover Bar) | 2021-09-03 07:00 | 2021-09-03 17:00 | N | Y | emergency fix leaking | Circuit Breaker | 987s C2402 (987s Clover Bar) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 861L (71s Lamoureux - 258s Dow Hydro Carbons), 258s T2 ( 258s Dow Hydro Carbons), 258s 138kV Bus 2 (258s Dowhydrocarbons) | 2021-09-03 07:00 | 2021-09-18 18:00 | N | Y | migrate alarms and controls from the existing SCADA system to the new system and replace strain insulators for 861L | Line, Transformer, Bus |  | Migrate alarms and controls from the existing SCADA system to the new system. This will include 138kV Bus 2 protection, T2 Protection, breakers 258s152, 258s252, and 258s552 controls and status, MOD 258s861W control and status, and 861L protection alarms. Strain insulators for 861L into the substation will be replaced. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 320p 401 (320p Keephills) | 2021-09-03 08:30 | 2021-09-03 13:30 | N | N | 1st trip and PRC5 maintenance, replace tank heater relay | Circuit Breaker |  | 1st trip and PRC5 maintenance, replace tank heater relay; New C60 breaker fail trip testing on breaker 1452 (320p401) | For Information Only, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2021-09-06 07:00 | 2021-10-20 20:00 | N | Y | maintenance | Switch |  | unit overhaul | 240 kV, Restricts Generation
ENMAX | 16.61L (ENMAX 16 - ENMAX 27), 27.1TR (ENMAX 27), 27B69-16.61 (ENMAX 27), 16B69-16.61 (ENMAX 16) | 2021-09-06 08:00 | 2021-09-14 16:00 | N | N | fall substation washing & 27.1TR HV, MV bushings replacement | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 7.84L (ENMAX 7 - ENMAX 36), 7B138-7.84 (ENMAX 7) | 2021-09-06 08:00 | 2021-09-10 16:00 | N | N | 7 sub cable trench replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-09-06 09:00 | 2021-09-06 19:00 | Y | Y | station equipnment inspection | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), 72RG1 (Garneau - Rossdale), VHBB2 (Rossdale), RR729 (Rossdale) | 2021-09-07 07:00 | 2021-09-10 17:00 | N | N | arrestor doble, breaker/switch maintenance | Line, Circuit Breaker | 72RG1 (Garneau - Rossdale), 72RV2 (EP 511s Victoria - Rossdale), VHBB2 (Rossdale), RR729 (Rossdale) | Bus 3 PT/Arrestor Doble, RDS9/RDS10/RDS12/RDS14/BD2W Switch Maintenance, RG7210 Breaker Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
WINDYPWPL | 112S Windy Point | 2021-09-07 07:00 | 2021-09-10 17:00 | N | N | 72 month maintenance, repair cables | Station | resolve concerns discovered during our 72-month maintenance as well as repair cables that had a termination failure on the low-side of the MPT to bring the site back to full capacity |  | Restricts Generation
SHELL | 847s 901T (847s Muskeg River) | 2021-09-07 07:00 | 2021-09-11 09:00 | N | Y | maintenance | Transformer |  | CNRL Request for their Plant Outage | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 646L (237s Foothills - 678s Okotoks) | 2021-09-07 07:00 | 2021-09-07 18:00 | N | N | maintenance on structure 148 | Line | 646L (237s Foothills - 678s Okotoks) | 712L (99s - 595s) - GOI Job Scope: Scope of work includes maintenance on structure 148 Scope of work includes maintenance on structure 148 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T3 (Poundmaker) | 2021-09-07 07:00 | 2021-09-08 17:00 | N | Y | removal of 240 kV bus work (P1649) | Transformer | Removal of 240 kV bus work for PM2405 bay installation for WETUP project. Tx3 to be energized from through PM2404 breaker during the restoration of this outage with 240 kV bus removed from PMDS1 to PMAB3 for the duration on PM2405 bay installation. Physical bus separation from PMDS1 to PMAB3 to remain upon Tx3 restoration. |  | Contingency Requires Mitigation, Firm Load Loss
EPCOR | T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft) | 2021-09-07 07:00 | 2021-09-15 12:00 | N | N | WDS3 switch outage | Transformer, Circuit Breaker | T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2021-09-07 07:45 | 2021-09-08 16:45 | N | Y | fix 63s1083 MOD | Line | 1083L (63s Red Deer - 288s Wolf Creek) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 764s 602T (764s Heisler) | 2021-09-07 08:00 | 2021-09-08 15:15 | N | N | maintenance | Transformer |  | 602T Maintenance | For Information Only
ENMAX | 2.82L (SS-2 - SS-5), 1.84L (SS-1 - SS-5), 5.7TR (SS-5), 5.5TR (SS-5), 5B138-2.82 (SS-5) | 2021-09-07 08:00 | 2021-10-06 16:00 | N | N | 5 sub Z31 Bus diff and Autoswitching relay replacement; 86 Lockout testing 86T-5, 86T-7, 86-Z31; 5sub replace 1.84 breaker | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 11.1TR (ENMAX 11) | 2021-09-07 08:00 | 2021-09-11 18:00 | N | N | maintenance and testing | Transformer |  | ECI bushings. Power factor test transformer, Transformer Secondary Cable Tests. Check reversing switch. Oil sampling MT, TC. 11 Sub 11.1TR Tap changer heater failure | For Information Only
Syncrude | Aurora UT2 (Aurora), 21 (Aurora), 22 (Aurora) | 2021-09-07 08:00 | 2021-09-13 20:00 | N | N | transformer outage | Transformer, Circuit Breaker | Non-Significant Outage: UT-2 Transformer (72/13.8kV) @ G01 Substation Following Circuit Breakers will be operated: CB # 21, and 22 @ G01 Substation Following MOD's will be operated: 25 @ G01 Substation |  | For Information Only
ENMAX, ALTALINK | 7.84L (ENMAX 7 - ENMAX 36), 36.81L (44s Bearspaw - ENMAX 36), 36.1TR (ENMAX 36), 36.3TR (ENMAX 36), 36B138-36BT3 (ENMAX 36) | 2021-09-07 08:00 | 2021-09-07 18:00 | N | Y | fall substation washing and maintenance | Line, Transformer, Circuit Breaker |  | Fall Substation Washing. 36MD138-36.3TR outside phases not sitting flat, adjust as needed. SW83 at 36 sub Stiff to operate - maintain and lubricate. Check Reversing Switch 36.1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s Heathfield, 12L70 (12s Heartland - 2029s Heathfield), 12L85 (12s Heartland - 2029s Heathfield) | 2021-09-07 08:30 | 2021-09-26 17:30 | N | Y | valve hall Inspections | Station, Line |  | AC Yards Will also be de-energized for grounding switch work. Valve Hall Inspections - Valve Hall Camera Repairs - LOP work | 500 kV, For Information Only
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2021-09-07 08:30 | 2021-09-26 17:30 | N | Y | EATL Outage | Line |  | 2021 EATL Outage: | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK, ATCO | 1088L (324s Cassils - 2075s Newell), 923L (356s Milo - 2075s Newell), 2075S Newell, 1087L (324s Cassils - 2075s Newell), 1035L (244s Bowmanton - 2075s Newell) | 2021-09-07 08:30 | 2021-09-26 17:30 | N | Y | valve hall inspection | Line, Station |  | AC Yards Will also be de-energized for grounding switch work. Valve Hall Inspections - Valve Hall Camera Repairs - LOP work | 240 kV, For Information Only, Affects Cranking Path
ATCO | 925s 902T (925s Green Stocking), 9L77 (925s Green Stocking - 934s Black Fly) | 2021-09-07 08:30 | 2021-09-09 16:50 | N | Y | 902T maintenance | Transformer, Line |  | 902T maintenance, load transferred to 901T | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2021-09-07 09:00 | 2021-09-10 17:00 | Y | Y | insulator replacement, BC maintenance does not affect the Alberta ATC | Line | 5L98 (BCH Nicola - Vaseux Lake) |  | Limits ATC, 500 kV
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10) | 2021-09-07 09:00 | 2021-09-09 17:00 | N | Y | migrate and commission all 42s693 (1452) & L5-693L at 42s Sarcee associated line protections | Line | 693L (42s Sarcee - ENMAX 10) | Migrate and commission all 42s693 (1452) & L5-693L at 42s Sarcee associated line protections, recloser, POW, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2021-09-07 09:00 | 2021-09-09 18:00 | N | Y | component replacements 947L (str's range 2-88) | Line | 947L (89s Ellerslie - 987s Clover Bar) |  | 240 kV, For Information Only, Limits ATC, Pre-Condition, Affects Cranking Path
ALTALINK | 170L (632s Russell - 799s Coleman) | 2021-09-07 09:15 | 2021-09-09 17:45 | N | Y | fire mitigation; structure replacements strs 48-54 | Line | 170L (632s Russell - 799s Coleman) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 17s T3 (17s Benalto), 17s 2852 (17s Benalto) | 2021-09-07 09:30 | 2021-09-09 17:00 | N | Y | SCADA alarm/control upgrade for T3, s389, s2852, tie in new 138B3 'B' CT cont | Transformer, Circuit Breaker | 17s T3 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2021-09-07 10:00 | 2021-09-13 15:00 | N | Y | crossarm changing | Line |  | Crossarm changing | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 255s T1 (255s Vulcan) | 2021-09-07 11:30 | 2021-09-16 17:30 | N | N | T1 maintenance/repairs (replace cracked CTs bushing, SFRA, Doble, repair oil leaks, repair bushing flange) | Transformer | 255s T1 (255s Vulcan) | T1 maintenance/repairs (replace cracked CTs bushing, SFRA, Doble, repair oil leaks, repair bushing flange) | For Information Only
ALTALINK | 814L (28s West Brooks - 121s Brooks) | 2021-09-08 06:15 | 2021-09-14 16:45 | N | N | line protection replacement | Line | 814L (28s West Brooks - 121s Brooks) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works) | 2021-09-08 07:00 | 2021-09-14 18:00 | N | Y | replace 801L Str 4, 15, 94 and 97 for urgent line clearance mitigation | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK, ATCO | 409s 138kV Bus B1 (409s Shell Scotford), 856L (409s Shell Scotford - 410s Josephburg), ALC01L (408s Air Liquide Scotford - 409s Shell Scotford), 409s T2 (409s Shell Scotford) | 2021-09-08 07:00 | 2021-09-14 18:00 | N | Y | transformer oil reclamation, regasketing, bird cover, oil temp gauge investigation, & maintenance | Bus, Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 1041L (370s North Lethbridge - 554s Travers) | 2021-09-08 07:00 | 2021-09-08 18:00 | N | Y | P5 urgent repair, overhead components | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2021-09-08 07:15 | 2021-09-08 17:45 | N | N | urgent repair to install new spacers | Line | urgent repair to install new spacers on the bottom phase between structures 14 and 15. To prevent major damage to conductor & failure |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s 2552 (370s North Lethbridge) | 2021-09-08 07:15 | 2021-09-08 17:45 | N | N | isolate bus to provide clearance for new screw pile install | Circuit Breaker |  |  | For Information Only
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 9 - ENMAX 43), 9.3TR (ENMAX 9) | 2021-09-08 08:00 | 2021-09-08 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 39s 847W (39s Bickerdike), 847L (39s Bickerdike - 406s Fickle Lake), 39s 252 (39s Bickerdike), 39s 352 (39s Bickerdike) | 2021-09-08 08:00 | 2021-09-08 11:00 | N | N | open jumpers at 847L Str. 847L58, hot line work | Switch, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | T15 (MH69s-1 Power Plant Switchyard) | 2021-09-08 08:00 | 2021-09-17 17:00 | N | Y | rung T15 north T15 segment upgrade phase 4C | Transformer | T15 (MH69s-1 Power Plant Switchyard) |  | Restricts Generation
WFML | WWD1 Weldwood 20MW Steam Turb. | 2021-09-08 08:00 | 2021-09-10 10:59 | N | N | due to 847L outage | Unit
ATCO | 840s 509 (840s McNeill) | 2021-09-08 08:30 | 2021-09-08 16:30 | N | Y | breaker 509 maintenance | Circuit Breaker |  | 840S 509PT2, 840S 509PT3, 840S 509PTD, 840S 509R1, 840S 509R2, 840S 509R3. Breaker 509 Maintenance 91 MW power limit when Emergency VAR Absorption off (current state) | Limits ATC
RVLP | RIV1 Riverview | 2021-09-08 10:00 | 2021-09-08 13:00 | N | N | due to 893L outage | Unit
ALTALINK | 58s C1 (58s Edson) | 2021-09-08 10:00 | 2021-09-09 16:00 | N | N | replace star point CT4 in 58s35 and re-energize cap bank | Shunts |  |  | For Information Only
ALTALINK, CRRLP | CRR1 Enel Alberta Castle Rock Wind Farm | 2021-09-08 10:00 | 2021-09-08 13:00 | N | N | due to 893L outage | Unit
PCLP | CRR2 Castle Rock Ridge 2 | 2021-09-08 10:00 | 2021-09-08 13:00 | N | N | due to 893L outage | Unit
ATCOP | OMRH CUPC Oldman River | 2021-09-08 10:00 | 2021-09-08 13:00 | N | N | due to 893L outage | Unit
ALTALINK | 847L (39s Bickerdike - 406s Fickle Lake) | 2021-09-08 11:30 | 2021-09-14 17:00 | N | Y | issue 847L and temp bypass to move 847L slack span to make room for future expansion, and connect temp bypass to 847L (close Open Point A) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Poundmaker), 1098L (805s Jasper - Poundmaker), PM2401 (Poundmaker), PM2402 (Poundmaker), PM2403 (Poundmaker) | 2021-09-09 07:00 | 2021-09-10 17:00 | N | Y | continuation of 240 kV ring re-configuration for WETUP project (P1649) | Transformer, Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2021-09-09 07:00 | 2021-09-10 18:00 | N | Y | *P5 urgent repair 1005L Str's 225 -226 overhead components | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge) | 2021-09-09 07:15 | 2021-09-14 12:45 | N | N | Isolate line to provide clearance for pile and structure install for new 25kV feeder on bus 4 | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2021-09-09 07:30 | 2021-09-09 17:30 | N | N | installation of bird cover-ups | Transformer |  |  | For Information Only
ENMAX | 16.60L (ENMAX 16 - ENMAX 34), 34.2TR (ENMAX 34) | 2021-09-09 08:00 | 2021-09-09 12:00 | N | N | fall substation washing | Line, Transformer | 16.60L (ENMAX 16 - ENMAX 34), 34.2TR (ENMAX 34) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 755L (247s Piper Creek - 535s Joffre), 535s 5552 (535s Joffre), 535s 5452 (535s Joffre) | 2021-09-09 08:00 | 2021-09-09 16:30 | N | N | urgent: clean hotspot and adjust 535s67 | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition, Affects Cranking Path
ALTALINK | 44s 860W (44s Bearspaw), 860L (44s Bearspaw Plant - 291s Cochrane) | 2021-09-09 08:00 | 2021-09-09 17:30 | N | N | fix tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALBIAN, SHELL | 919s 906 (919s Hartley), 847s 901T (847s Muskeg River) | 2021-09-09 08:30 | 2021-09-10 16:00 | N | Y | PRC005 trip coil testing, test and operate 906 | Circuit Breaker, Transformer |  | PRC005 Trip coil testing, Test and operate 906, 901T @ 847S OOS Coordinated with generator Planned outage | 240 kV, For Information Only
ATCO | 840s 508 (840s McNeill) | 2021-09-09 08:30 | 2021-09-09 16:30 | N | Y | breaker 508 maintenance | Circuit Breaker |  | 840S 508C1, 840S 508C2, 840S 508C3, 840S 508PT1, 840S 508PT2, 840S 508PT3, 840S 508PTD, 840S 508R1, 840S 508R2, 840S 508R3. Breaker 508 Maintenance 91 MW power limit when Emergency VAR Absorption off (current state) | Limits ATC
ATCO | 794s 702T (794s Valleyview) | 2021-09-09 10:00 | 2021-09-10 17:00 | N | N | maintenance | Transformer |  | 794S 702T Maintenance, Load transferred to 794S 701T | For Information Only, Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 34.1TR (ENMAX 34) | 2021-09-09 12:00 | 2021-09-09 18:00 | N | N | fall substation washing | Line, Transformer | 21.61L (ENMAX 21 - ENMAX 34), 34.1TR (ENMAX 34) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 741s 701 (741s Fox Creek) | 2021-09-10 08:00 | 2021-09-24 16:00 | N | N | modifications at Fox Creek 741S -like for like breaker replacement. ISD Sep 17, 2021 | Circuit Breaker |  | for planned modifications at Fox Creek 741S
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake) | 2021-09-10 11:00 | 2021-09-17 17:00 | N | Y | maintenance activities at Suncor base plant | Line |  | Suncor performing perform 5/10Yr maintenance activities at Suncor base plant, Suncor requesting ATCO isolation on this date and to gain escorted access to substation Ruth Lake 848S to verify and if possible hang red and yellow Suncor operation cross locks at ATCO Ruth lake disconnect for this line. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 320p 2089 (320p Keephills) | 2021-09-10 12:30 | 2021-11-01 16:30 | N | Y | maintenance | Switch |  |  | 500 kV, Restricts Generation
ENMAX | 11.81L (ENMAX 11 - ENMAX 13), 11.4TR (ENMAX 11), 11.1TR (ENMAX 11) | 2021-09-11 08:00 | 2021-09-11 18:00 | N | N | fall substation washing, hot spots west and east phase | Line, Transformer
ALTALINK | 740AL (414s Gulf Robb - 740L tap) | 2021-09-11 08:00 | 2021-09-11 17:00 | N | N | scope of work includes maintenance on structures 9 and 10 | Line | 740AL (414s Gulf Robb - 740L tap)
ALTALINK | 749AL (267s Killarney Lake - 749L tap) | 2021-09-12 07:00 | 2021-09-17 18:00 | N | N | installation of new double dead-end structures and taps for energization of the new 749AL alignment, closing open points 'A' & 'B' | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 38.1C (ENMAX 38), 38.1TR (ENMAX 38), 38.3TR (ENMAX 38) | 2021-09-12 08:00 | 2021-09-12 13:00 | N | N | fall substation washing | Line, Shunts, Transformer | 38.83L (ENMAX 38 - ENMAX 39), 38.1TR (ENMAX 38), 38.3TR (ENMAX 38), 38.1C (ENMAX 38) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 37.81L (ENMAX 37 - ENMAX 38), 38.2TR (ENMAX 38), 38.3TR (ENMAX 38), 38.1C (ENMAX 38) | 2021-09-12 13:00 | 2021-09-12 18:00 | N | N | fall substation washing | Line, Transformer, Shunts | 37.81L (ENMAX 37 - ENMAX 38), 38.2TR (ENMAX 38), 38.3TR (ENMAX 38), 38.1C (ENMAX 38) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 511s T30 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings) | 2021-09-13 07:00 | 2021-09-17 17:00 | N | Y | doble T30, SVC Plus maintenance, MSR re-wiring | Transformer, Shunts | 511s T30 (511s Crossings), 511s SVC Plus (511s Crossings) |  | 240 kV, Pre-Condition
EPCOR | 657s T1 (657s Summerside) | 2021-09-13 07:00 | 2021-09-14 17:00 | N | Y | cut over control, alarms, status to new RTU | Transformer | Isolate Summerside TX1 Bay to cut over control, alarms, status to new RTU |  | 240 kV, Contingency Requires Mitigation
EPCOR | T3 (Poundmaker) | 2021-09-13 07:00 | 2021-11-15 17:00 | N | Y | 240 kV ring re-configuration (P1649) | Transformer | Continuation of 240 kV ring re-configuration for WETUP project. Tx3 bay to be isolated for 240 kV bus re-configuration and installation of PM2405, PMDS11 and CVT's. Upon restoration Tx3 to be energized from PM2404 and a new isolation point of PMDS11 disconnect to remain open. |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer), 63s 26 (63s Red Deer), 63s T3 (63s Red Deer), 63s 51 (63s Red Deer), 426L (63s Red Deer - 194s South Red Deer) | 2021-09-13 07:30 | 2021-09-17 13:00 | N | Y | trip testing | Transformer, Circuit Breaker, Line | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer), 63s 26 (63s Red Deer), 63s T3 (63s Red Deer), 63s 51 (63s Red Deer), 426L (63s Red Deer - 194s South Red Deer) | Wire CT contributions for new 138kV bus protections and complete trip testing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.82L (ENMAX 11 - ENMAX 14), 14.1C (ENMAX 14), 14.2C (ENMAX 14), 14.1TR (ENMAX 14), 14.3TR (ENMAX 14) | 2021-09-13 08:00 | 2021-09-13 13:00 | N | N | fall substation washing | Line, Shunts, Transformer | 11.82L (ENMAX 11 - ENMAX 14), 14.1C (ENMAX 14), 14.2C (ENMAX 14) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CMH | MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2021-09-13 08:00 | 2021-09-24 14:00 | N | N | accommodate repairs due to a recent grass fire | Line |  |  | For Information Only
ENMAX | 1.5TR (ENMAX 1) | 2021-09-13 08:00 | 2021-09-17 16:00 | N | N | transformer maintenance | Transformer | Power factor test transformer, Transformer Maintenance. Gas Relay Testing. |  | For Information Only
ATCO | 925s 901T (925s Green Stocking) | 2021-09-13 08:30 | 2021-09-16 16:50 | N | Y | 901T maintenance | Transformer |  | 901T maintenance | 240 kV, For Information Only
ENMAX | 35.81L (42s Sarcee - ENMAX 35) | 2021-09-13 09:00 | 2021-09-15 17:00 | N | Y | migrate and commission all 42s35 (352) & L3-35.81L at 42s Sarcee | Line | 35.81L (42s Sarcee - ENMAX 35) | Migrate and commission all 42s35 (352) & L3-35.81L at 42s Sarcee associated line protections, recloser, POW, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. . | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 37s T6 (37s North Calder) | 2021-09-13 12:00 | 2021-09-30 18:00 | N | Y | maintenance, doble and leak repairs, PRC5 work | Transformer | 37s T6 (37s North Calder) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L99 (727s Kinuso - 745s Slave Lake) | 2021-09-13 12:00 | 2021-09-20 14:00 | N | N | pole repairs from test and treat | Line |  | Pole repairs from test and treat | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 786s 703 (786s High Level), 786s 703T (786s High Level), 786s SVC (786s High Level) | 2021-09-13 12:00 | 2021-09-16 17:00 | N | Y | 703T Maintenance | Circuit Breaker, Transformer, Shunts |  | 703T Maintenance | For Information Only
ALTALINK | 437s T1 (437s Baymag) | 2021-09-13 12:15 | 2022-05-06 18:00 | N | N | T1 A & B protection replacement | Transformer |  |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 14.1C (ENMAX 14), 14.2C (ENMAX 14), 14.2TR (ENMAX 14), 14.4TR (ENMAX 14) | 2021-09-13 13:00 | 2021-09-13 18:00 | N | N | fall substation washing | Line, Shunts, Transformer | 14.83L (ENMAX 14 - ENMAX 36), 14.1C (ENMAX 14), 14.2C (ENMAX 14) | Fall Substation Washing. Check Reversing Switch 14.2TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T1 (EP 511s Victoria) | 2021-09-14 07:00 | 2021-09-16 17:00 | N | N | tap changer maintenance | Transformer | E511s Victoria T1 (511s Victoria) |  | For Information Only
KP | PMB1 Keyera West Pembina Gas Turbine | 2021-09-14 08:00 | 2021-09-14 12:00 | N | N | transmission station outage to wire trip from low voltage gear | Unit
ATCO | 775s 603 (775s Sullivan Lake) | 2021-09-14 08:00 | 2021-09-16 16:00 | N | N | substation rebuild demo 603 breaker | Circuit Breaker |  | 775S Sullivan Lake Substation Rebuild. Demo 603 Breaker | For Information Only
SUNCOR | 29PL7-3 (29EDD-65 - 29EDD-71), 29PT 236 (29EDD-65), 29EDD-71 752-4633 (29EDD-71), 29EDD-71 752-4634 (29EDD-71), 29EDD-65 952-4823 (29EDD-65), 29EDD-65 952-4822 (29EDD-65) | 2021-09-14 08:00 | 2021-09-16 18:00 | N | Y | PM 5y | Line, Transformer, Circuit Breaker |  | 29EDD65;29PT-250 & 29PL7-3 SYSTEM;PM 5y 29PT-236 & 29PL7-3 SYST;PM 5y(A) 29EDD-71; 144KV NODE, 29PT-246 MAINT;5y(A) | 240 kV, Overload, Pre-Condition
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2021-09-14 08:00 | 2021-09-14 16:00 | N | N | substation rebuild connect bypass, install openers/isolators on 6L03 | Line | 6L03 (775s Sullivan Lake - 6L17 tap) | 775S Sullivan Lake Substation Rebuild Connect bypass, install openers/isolators on 6L03 6L03 will remain open at 775S after this outage and will be tied to 6L12 under GOI 2-52641 on Sept 15, 2021 | For Information Only
ALTALINK | 359S Esso West Pembina | 2021-09-14 08:00 | 2021-09-14 12:00 | N | Y | station outage to wire trip from their low voltage gear DS-XRMR-8803-1 to 359s7225X Breaker | Station |  | Customer requires station outage to wire trip from their low voltage gear DS-XRMR-8803-1 to their 359s7225X Breaker. and perform trip test. Wiring to be completed inside Altalinks switchgear building, Station De-energized due to Arc Flash requirements. | For Information Only, Restricts Generation
Saskpower | Sask Power H1P line | 2021-09-14 08:00 | 2021-09-15 14:00 | N | N | SPC maintenance | Line |  |  | For Information Only
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 9.1TR (ENMAX 9) | 2021-09-14 08:00 | 2021-09-14 16:00 | N | N | fall substation washing | Line, Transformer | 9.80L (ENMAX 9 - ENMAX 31), 9.1TR (ENMAX 9) |  | For Information Only
ATCO | 749s 701 (749s Flyingshot Lake) | 2021-09-14 09:00 | 2021-09-16 16:30 | N | Y | testing | Circuit Breaker |  | 749S 701 testing | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2021-09-14 09:30 | 2021-09-14 14:30 | N | N | weed spraying and cleanup within C1 fence | Shunts |  |  | Pre-Condition
ATCO | 828s 701 (828s Sulphur Point), 7L93 (828s Sulphur Point - 930s Arcenciel) | 2021-09-14 09:30 | 2021-09-14 10:30 | N | Y | PRC-005 - trip coil testing T&O required for testing | Circuit Breaker, Line |  | PRC-005 - TRIP COIL TESTING - BREAKER 701 @ 828S 701 T&O required for testing TRIP & CLOSE coils Open 7L93D2 for test and operate on 701 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 840s 504 (840s McNeill) | 2021-09-14 10:30 | 2021-09-14 16:30 | N | Y | breaker 504 repair | Circuit Breaker |  | ATCO requires 840S 25 Kv BKR 504 OOS to repair damaged capacitors (one has bushing hanging off to the side) Affected Equipment is 504C1, 504C2, and 504C3 and 504R1, 504R2 and 504R3 The Power limit is expected to be 91 MW | Limits ATC
ATCO | 2085s 601T (2085s Sheridan) | 2021-09-14 12:00 | 2021-09-15 11:00 | N | N | transformer leak repair | Transformer |  | Transformer Leak Repair | For Information Only
ATCO | 828s 703 (828s Sulphur Point), 7L133 (786s High Level - 828s Sulphur Point) | 2021-09-14 13:30 | 2021-09-14 16:30 | N | Y | PRC-005 - trip coil testing | Circuit Breaker, Line | 7L133 (786s High Level - 828s Sulphur Point) | PRC-005 - TRIP COIL TESTING - BREAKER 703 @ 828S 703 OOS for duration of work under T&O for trip coil testing. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 406s 847L58 (406s Fickle Lake) | 2021-09-14 17:00 | 2021-09-15 15:30 | N | Y | Cascade Power Project | Switch |  |  | Creates Radial Feeds, For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 409s T1 (409s Shell Scotford) | 2021-09-15 07:00 | 2021-09-16 08:00 | N | N | install new 409s100 breaker | Transformer |  |  | For Information Only
ALTALINK | 409s T3 (409s Shell Scotford) | 2021-09-15 07:00 | 2021-09-16 08:00 | N | N | open 409s117& remove 409s115 PT fuses | Transformer |  |  | For Information Only
ALTALINK | 477s T1 (477s Amoco West Pembina), 844L (358s Amoco Brazeau - 477s Amoco West Pembina), 841L (477s Amoco West Pembina - 489s Amoco Canada Brazeau River) | 2021-09-15 07:00 | 2021-09-15 19:00 | N | Y | urgent outage to demo cables | Transformer, Line |  | Urgent outage to demo cables going to the Customer facility to alleviate the Safety concern at site. Create an Open Point on the 4.16kV bus and issue a Salvage Clearance to facilitate the 477s Customer disconnection request. RSLD1 sh.1 to be implemented at the end of the outage. | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 763L (28s West Brooks - 763AL tap) | 2021-09-15 07:00 | 2021-09-17 18:00 | N | N | components replacements for 763L Str's range 23-256 | Line |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2021-09-15 07:00 | 2021-09-16 18:00 | N | Y | component replacements on 920L Str's Range ( 52D-100 ) | Line | 920L (71s Lamoureux - 557s Castle Downs) |  | 240 kV, For Information Only, Pre-Condition, Affects Cranking Path
ALTALINK | 759L (87s Gaetz - 276s Prentiss) | 2021-09-15 07:15 | 2021-09-15 17:45 | N | N | maintenance on structures 1 and 2 | Line |  |  | For Information Only
ALTALINK | 1148L (251s Whitla - 1018s Shamrock) | 2021-09-15 08:00 | 2021-09-15 14:00 | N | Y | maintenance | Line |  |  | 240 kV, Restricts Generation
ATCO | 775s 602 (775s Sullivan Lake) | 2021-09-15 08:00 | 2021-09-16 16:00 | N | N | 775S Sullivan Lake substation rebuild: demolish 602 breaker | Circuit Breaker |  | 775S Sullivan Lake Substation Rebuild. Demo 602 Breaker | For Information Only
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap), 6L12 (775s Sullivan Lake - 6L25 tap) | 2021-09-15 08:00 | 2021-09-15 16:00 | N | N | 775S Sullivan Lake substation rebuild | Line |  | 775S Sullivan Lake Substation Rebuild Connect bypass, install openers/isolators ( J2 on 6L12) 775S Bypass will be energized on restoration ( 6L03 & 6L12 tied together bypassing 775S) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.4TR (ENMAX 21), 21.61L (ENMAX 21 - ENMAX 34), 15.60L (ENMAX 15 - ENMAX 21) | 2021-09-15 08:00 | 2021-10-01 16:00 | N | N | 21.4TR HV H0X0 bushings replacement and maintenance | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
Syncrude | Mildred T2 (Syncrude Mildred Lake) | 2021-09-15 08:00 | 2021-09-15 20:00 | N | N | maintenance | Transformer |  |  | Limits Ratings
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek) | 2021-09-15 08:00 | 2021-09-15 16:00 | N | N | changing pole from test and treat data | Line |  | changing pole from test and treat data | Creates Radial Feeds, For Information Only, Pre-Condition
ALTALINK | 807L (410s Josephburg - 402s Scotford Expansion), 807L (233s Beamer - 807AL tap) | 2021-09-15 08:00 | 2021-09-15 17:00 | N | Y | part of 402s MPLS upgrade | Line | 807L (410s Josephburg - 402s Scotford Expansion) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 2085s 602T (2085s Sheridan) | 2021-09-15 12:00 | 2021-09-16 11:00 | N | N | transformer leak repair | Transformer |  | Transformer Leak Repair | For Information Only
ALTALINK | 39s 847W (39s Bickerdike), 847L (39s Bickerdike - 406s Fickle Lake) | 2021-09-15 15:30 | 2021-09-15 16:00 | N | Y | required to close CPS1 Switch | Switch, Line |  |  | Creates Radial Feeds, For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 39s 740X (39s Bickerdike) | 2021-09-15 16:00 | 2021-09-15 18:00 | N | N | create Open Point C on 740L - hot line work | Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 847L (39s Bickerdike - 406s Fickle Lake) | 2021-09-15 16:00 | 2021-09-24 17:00 | N | Y | 847L will be open at 406s and supplying 740L during this time | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s 12 (62s Brazeau) | 2021-09-15 23:00 | 2021-09-16 03:00 | N | N | maintenance | Switch |  |  | 240 kV, Restricts Generation
EPCOR | 657s T2 (657s Summerside), 657s SU2403 (657s Summerside), 657s SU2402 (657s Summerside) | 2021-09-16 07:00 | 2021-09-17 17:00 | N | Y | cut over controls, alarms, status to new RTU | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, ATCO | 857L (409s Shell Scotford - 410s Josephburg), ALC02L (409s Shell Scotford - 879s Scotford Upgrader), 409s 138kV Bus B2 (409s Shell Scotford), 409s T1 (409s Shell Scotford), 409s T3 (409s Shell Scotford) | 2021-09-16 07:00 | 2021-09-22 15:30 | N | Y | 409s T1 oil reclamation, regasketing, oil monitor replacement, bird cover, T3 maintenance, T1 & T3 NGR maintenance, 409s807N grading cap replacements. 409s110 breaker maintenance including 1st trips | Line, Bus, Transformer |  | Transition to 409sT1 outage at the end of this outage. 409s T1 oil reclamation, regasketing, oil monitor replacement, bird cover. T3 maintenance. T1 & T3 NGR maintenance. 409s807N grading cap replacements. 409s110 breaker maintenance including 1st trips. | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2021-09-16 08:00 | 2021-09-16 14:00 | N | N | URGENT P5* replace failing cross arms on 799L595 | Line |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32) | 2021-09-16 08:00 | 2021-09-16 12:00 | N | N | fall substation washing | Line, Transformer | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32) |  | For Information Only
ALTALINK | 39s 352 (39s Bickerdike), 39s 452 (39s Bickerdike), 39s 740X (39s Bickerdike) | 2021-09-16 08:00 | 2021-09-23 17:00 | N | N | move 740L-426s Slack spans as they come into the station to make room for future 240kV | Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR | 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale) | 2021-09-16 08:00 | 2021-09-16 15:00 | N | N | transmission switching school | Line, Circuit Breaker |  | Kennedale K724 Isolation for Transmission Switching School (Isolates 72CK12 from Kennedale) | Creates Radial Feeds, Firm Load Loss
ATCO | 775S Sullivan Lake, 6L15 (763s Hanna - 775s Sullivan Lake) | 2021-09-16 08:00 | 2021-11-30 11:59 | N | N | 775S Sullivan Lake substation rebuild complete breaker and disconnect switch replacement, 775S Sullivan Lake substation rebuild complete breaker and disconnect switch replacement | Station, Line |  | 775S Sullivan Lake Substation Rebuild Complete Breaker and Disconnect switch replacement 6L03 & 6L12 tied together bypassing 775S Sullivan Lake | Pre-Condition
ALBIAN, ATCO | 919s 908 (919s Hartley), 847s 902T (847s Muskeg River) | 2021-09-16 08:30 | 2021-09-17 16:00 | N | Y | PRC005 trip coil testing | Circuit Breaker, Transformer |  | PRC005 Trip coil testing. Test and operate 908 847S 902T OOS,Muskeg GTG-2 Generator will be unavailable. Coordinated with generator Planned outage | 240 kV, Restricts Generation
ATCO | 786s 505C (786s High Level) | 2021-09-16 09:00 | 2021-09-16 17:00 | N | N | 505 Maintenance | Shunts |  | 505 Maintenance | For Information Only
ALTALINK | 65s T2 (65s High River) | 2021-09-16 09:00 | 2021-09-16 17:00 | N | N | replace LTC beckwith controller | Transformer |  |  | For Information Only
Saskpower | Sask Power AS902, Sask Power AS905 | 2021-09-16 09:00 | 2021-09-16 15:00 | N | N | SPC maintenance | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2021-09-16 09:15 | 2021-09-17 17:15 | N | Y | PRC 1st trip & maintenance | Line | 7.82L (42s Sarcee - ENMAX 7) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2021-09-16 12:00 | 2021-09-16 18:00 | N | N | fall substation washing | Line, Transformer | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2021-09-16 14:00 | 2021-09-16 18:00 | N | N | URGENT *P5* replace failing cross arms on 799L827 | Line |  |  | For Information Only
ATCO | 749s 703 (749s Flyingshot Lake) | 2021-09-16 16:30 | 2021-09-18 16:30 | N | Y | testing | Circuit Breaker |  | 749S 703 testing | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 730L (285s East Camrose - 732L tap), 285s 96 (285s East Camrose), 285s T1 (285s East Camrose) | 2021-09-16 17:00 | 2021-09-16 18:00 | N | N | energize the new switchgear building #1 via 285s730N | Line, Switch, Transformer |  | deenergize a portion of the 138kV bus to energize the new switchgear building #1 via 285s730N | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 841L (477s Amoco West Pembina - 489s Amoco Canada Brazeau River) | 2021-09-17 07:00 | 2021-09-20 18:00 | N | N | replace 841L Str 32 and 33 for line clearance mitigation | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 790s 704 (790s Poplar Hill) | 2021-09-17 08:00 | 2021-10-01 16:00 | N | N | modifications at Poplar Hill 790S - like for like breaker replacement. ISD Sep 24, 2021 | Circuit Breaker |  | for planned modifications at Poplar Hill 790S
ATCO | 786s 506 (786s High Level), 786s 506C (786s High Level) | 2021-09-17 09:00 | 2021-09-17 17:00 | N | N | maintenance | Circuit Breaker, Shunts |  | 506 Maintenance | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2021-09-17 10:15 | 2021-09-17 13:45 | N | N | mobile disconnect | Line | 850L (525s Carseland - 678s Okotoks) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 63s 240kV North Bus (63s Red Deer), 63s T1 (63s Red Deer), 63s 24 (63s Red Deer), 63s 152 (63s Red Deer), 63s 452 (63s Red Deer), 63s 752 (63s Red Deer), 63s 2652 (63s Red Deer) | 2021-09-17 13:00 | 2021-09-20 17:00 | N | Y | wire CT contributions for new 138kV bus protections and complete trip testing | Bus, Transformer, Circuit Breaker | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer), 63s 152 (63s Red Deer), 63s 452 (63s Red Deer), 63s 752 (63s Red Deer), 63s 2652 (63s Red Deer) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 20.82L (ENMAX 20 - ENMAX 21), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21), 21.80L (42s Sarcee - ENMAX 21) | 2021-09-18 08:00 | 2021-09-18 18:00 | N | Y | fall substation washing, replace H bushings on 21.4TR | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 39.82L (ENMAX 39 - ENMAX 162), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) | 2021-09-18 08:00 | 2021-09-18 13:00 | N | N | fall substation washing | Line, Transformer | 38.83L (ENMAX 38 - ENMAX 39), 39.82L (ENMAX 39 - ENMAX 162), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 581s T1 (581s Amoco Ricinus) | 2021-09-18 08:30 | 2021-09-20 13:30 | N | N | disconnect customer  create open point in 4.16 kV bus | Transformer |  |  | For Information Only
ATCO | 786s 507 (786s High Level), 786s 507C (786s High Level) | 2021-09-18 09:00 | 2021-09-19 12:00 | N | N | 507 Maintenance | Circuit Breaker, Shunts |  | 507 Maintenance | Pre-Condition
BCH | 5L92 (Cranbrook - Selkirk) | 2021-09-18 09:00 | 2021-09-25 17:00 | Y | Y | insulator replacement | Line | 5L92 (Cranbrook - Selkirk) |  | Limits ATC, 500 kV
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 39.82L (ENMAX 39 - ENMAX 162), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) | 2021-09-18 13:00 | 2021-09-18 18:00 | N | N | fall substation washing | Line, Transformer | 22.81L (ENMAX 22 - ENMAX 39), 39.82L (ENMAX 39 - ENMAX 162), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2021-09-19 07:15 | 2021-09-20 16:45 | N | Y | urgent - replace cross arms and insulators on 463L Str 159 | Line |  | Urgent - Replace cross arms and insulators on 463L Str 159 due to eyebolt on crossarm to insulator connection failing | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 24.81L (ENMAX 24 - ENMAX 31), 31.84L (ENMAX 31 - ENMAX 32), 31.3TR (ENMAX 31), 31.2TR (ENMAX 31) | 2021-09-19 08:00 | 2021-09-19 13:00 | N | N | fall substation washing | Line, Transformer | 24.81L (ENMAX 24 - ENMAX 31), 31.84L (ENMAX 31 - ENMAX 32), 31.3TR (ENMAX 31), 31.2TR (ENMAX 31) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2021-09-19 08:00 | 2021-09-19 16:00 | N | N | cathodic protection and manhole inspections | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 786s 508C (786s High Level) | 2021-09-19 12:00 | 2021-09-20 17:00 | N | N | 508 Maintenance | Shunts |  | 508 Maintenance | Pre-Condition
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31.1C (ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31) | 2021-09-19 13:00 | 2021-09-19 18:00 | N | N | fall substation washing | Line, Shunts, Transformer | 9.80L (ENMAX 9 - ENMAX 31), 31.1C (ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31) |  | Pre-Condition
EPCOR | T2 (Rossdale) | 2021-09-20 07:00 | 2021-09-20 17:00 | N | N | R6T2 PCU replacement for P&C | Transformer |  |  | For Information Only
EPCOR | T3 (Woodcroft), W722 (Woodcroft), W724 (Woodcroft) | 2021-09-20 07:00 | 2021-10-01 17:00 | N | N | woodcroft WDS6 LCR | Transformer, Circuit Breaker | W724 (Woodcroft), W722 (Woodcroft), T3 (Woodcroft) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 12L44 (939s Livock - 951s Thickwood Hills), 12L41 (510s Sunnybrook - 939s Livock), 951s 1213R (951s Thickwood HIlls) | 2021-09-20 07:15 | 2021-09-27 16:45 | N | Y | CT and PT circuit extension and commissioning new RAS relays | Line, Shunts |  | Suncor Capacity increase project Complete commissioning of RAS relays. 951S APL will be required to run on the standby generator. Cut in new CT and PT circuit extension to the new RAS relays, T&O Line Terminal Open (LTO) on 1206, 1207, and 12L44D1 @ 939S APL Livock and 1244D1, 1205, 1206, 1201TA, and 901TA @ 951S APL Thickwood. Complete commissioning of RAS relays, end-to- end tests including output to Thickwood RAS | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 769s 701T (769s Sttettler) | 2021-09-20 08:00 | 2021-09-23 13:00 | N | N | replace 500PT1, bird proofing to the north bus | Transformer |  | Replace 500PT1, Bird proofing to the north bus and transformer low side. Load will be transferred to 703T | Pre-Condition
ATCO | 790s 704 (790s Poplar Hill), 790s 703T (790s Poplar Hill) | 2021-09-20 08:00 | 2021-09-22 17:00 | N | N | replace 1 phase on 790S 704, 790S 703T maintenance | Circuit Breaker, Transformer |  | Replace 1 phase on 790S 704, 790S 703T maintenance | Restricts Generation
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | 2021-09-20 08:00 | 2021-09-20 12:00 | N | N | fall substation washing | Line, Transformer | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 718s 701T (718s Parsons Creek) | 2021-09-20 08:00 | 2021-09-27 16:30 | N | N | replace 501 breaker | Transformer | 718s 701T (718s Parsons Creek) | replace 501 breaker. | For Information Only
ALTALINK | 763L (28s West Brooks - 763AL tap) | 2021-09-20 09:00 | 2021-09-24 18:00 | N | N | components replacements | Line | Components replacements for 763L Str's Range 23-256 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
NOVAC, NOVACORP | 330L2 (I-330s Nova Corp Plant - 535s Joffre), 330s 138kV Bus 1B (330s Nova Corp) | 2021-09-20 09:00 | 2021-09-24 17:00 | N | Y | maintenance | Line, Bus |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 535s 97N (535s Joffre) | 2021-09-20 09:00 | 2021-09-24 16:00 | N | Y | customer planned maintenance | Switch |  |  | For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 42s C1 (42s Sarcee) | 2021-09-20 09:30 | 2021-09-22 16:30 | N | N | migrate and commission | Shunts | 42s C1 (42s Sarcee) | Migrate and commission all Cap bank C1 & 42S1652 associated protections, breakers, breaker fail, POW alarms, status, controls, metering and remote access to new RTU and LAN. | For Information Only, Pre-Condition
ALTALINK | 17s 757N (17s Benalto) | 2021-09-20 09:30 | 2021-09-26 14:30 | N | N | line protection replacement, breaker fail replace | Circuit Breaker | A/B Line prot replacement ,s757N breaker fail replace. - Replacing existing 43M/2052 (for s757N), Adding recloser supervisory enable/disable to 17s757N, Tie in new 138B3 'B' CT contribution |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 946s 901 (946s Oakland) | 2021-09-20 09:30 | 2021-09-21 17:30 | N | Y | repair 901 leak | Circuit Breaker |  | Repair 901 leak | 240 kV, Contingency Requires Mitigation
ALTALINK | 545s T1 (545s Provost) | 2021-09-20 10:00 | 2021-09-28 17:00 | N | N | replace T1 transformer protections | Transformer |  |  | For Information Only
ALTALINK | 54L (123s Banff - 177s West Cascade) | 2021-09-20 10:00 | 2021-09-21 15:00 | N | N | fire mitigation (str 300-302) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) | 2021-09-20 12:00 | 2021-09-20 18:00 | N | N | fall substation washing | Line, Transformer | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 650s T3 (650s Hansman Lake), 650S SVC (650s Hansman Lake) | 2021-09-20 12:30 | 2021-09-23 17:30 | N | Y | maintenance on SVC. T3 maintenance, doble | Transformer, Shunts | 650S SVC (650s Hansman Lake), 650s T3 (650s Hansman Lake) | Maintenance on SVC. T3 maintenance, doble Schedued By: Tyler Schiltroth Requested By: MAPS North Contact #: Issue to: Jory Schell Contact #:403-318-4758 | 240 kV, Pre-Condition
ALTALINK | 5s T1 (5s East Calgary) | 2021-09-20 12:30 | 2021-09-23 16:30 | N | Y | maintenance, doble | Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | EP 511s Victoria T3 (EP 511s Victoria) | 2021-09-21 07:00 | 2021-09-23 17:00 | N | N | tap changer maintenance | Transformer | E511s Victoria T3 (511s Victoria) |  | For Information Only
ALTALINK | 370s 2552 (370s North Lethbridge), 370s T4 (370s North Lethbridge) | 2021-09-21 07:15 | 2021-11-29 16:59 | N | N | isolate bus to provide clearance for new steel and equipment installation | Circuit Breaker, Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 428s T2 (428s Namaka) | 2021-09-21 07:15 | 2021-09-24 09:45 | N | N | installation of CTs | Transformer |  | Installation of CTs for DER connection | For Information Only
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2021-09-21 08:00 | 2021-09-21 12:00 | N | N | fall substation washing | Line, Transformer | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L25 (773s Coronation - 6L12 tap), 6L12 (774s Monitor - 6L25 tap), 6L12 (775s Sullivan Lake - 6L25 tap) | 2021-09-21 08:00 | 2021-09-22 17:00 | N | N | cross arm and insulator change | Line |  | Cross arm and insulator change 773S load will be transferred to adjacent subs | Pre-Condition
ALTALINK | 523s T1 (523s Bullshead) | 2021-09-21 09:00 | 2021-09-22 17:30 | N | N | install new metering equipment and wiring | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23), 23.4TR (ENMAX 23) | 2021-09-21 12:00 | 2021-09-21 16:00 | N | Y | fall substation washing | Line, Transformer | 23.80L (74s Janet - ENMAX 23), 23.4TR (ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2021-09-21 18:00 | 2021-09-21 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 205s 352 (205s Castle Rock Ridge) | 2021-09-22 07:30 | 2021-09-22 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, NOVAC | 535s 5852 (535s Joffre), 535s 5952 (535s Joffre), 330L2 (I-330s Nova Corp Plant - 535s Joffre) | 2021-09-22 08:00 | 2021-09-23 17:00 | N | N | PRC5 trip testing with customer | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 180s 189 (180s Cope Creek), 180s T1 (180s Cope Creek) | 2021-09-22 09:30 | 2021-09-22 14:30 | N | N | recertify Transalta employees for switching on the Altalink system | Switch, Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 244s 2552 (244s Bowmanton) | 2021-09-22 09:30 | 2021-09-22 13:30 | N | N | PRC5 breaker 1st trip and maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 722s 701T (722s Crystal Lake) | 2021-09-22 10:00 | 2021-09-29 18:00 | N | N | 722S 701T maintenance | Transformer |  | 722S 701T maintenance, load transferred to 722S 702T | For Information Only, Pre-Condition
ALTALINK | 205s 452 (205s Castle Rock) | 2021-09-22 12:30 | 2021-09-22 17:00 | N | Y | replace heaters | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 244s 2652 (244s Bowmanton) | 2021-09-22 13:30 | 2021-09-22 17:30 | N | N | PRC5 breaker 1st trip and maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 409s T1 (409s Shell Scotford) | 2021-09-22 14:00 | 2021-09-28 17:00 | N | N | 409s T1 oil reclamation and maintenance | Transformer | 409s T2 (409s Shell Scotford) |  | For Information Only
ALTALINK | 409s T3 (409s Shell Scotford) | 2021-09-22 14:00 | 2021-09-28 17:00 | N | N | close 409s117 & install 409s115 PT Fuses | Transformer |  |  | For Information Only
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove) | 2021-09-23 07:00 | 2021-09-23 18:00 | N | Y | maintenance on structure 147 | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK, PANC | 391s 23 (391s Balzac), PCES02L (391s Balzac - PCES02S Balzac Power Station) | 2021-09-23 07:00 | 2021-10-01 17:00 | N | Y | maintenance | Switch, Line |  | Customer maintenance @ PCES02s | For Information Only, Restricts Generation
ALTALINK | 498s T2 (498s Tilley) | 2021-09-23 07:15 | 2021-09-23 14:00 | N | N | complete trip testing on 498s22, settings change, and CT wiring for new protections | Transformer |  | T2 outage to complete trip testing on 498s22, settings change, and CT wiring for new protections | For Information Only
Syncrude | ML1 (D05 Syncrude - Syncrude Mildred Lake) | 2021-09-23 08:00 | 2021-09-23 14:30 | N | N | repair failed backup relay protection | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2021-09-23 08:00 | 2021-09-24 17:00 | N | N | cross arm and insulator change | Line |  | Cross arm and insulator change | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 1.5TR (ENMAX 1) | 2021-09-23 08:00 | 2021-09-23 10:00 | N | N | fall substation washing | Transformer | 1.5TR (ENMAX 1) |  | For Information Only
GENL | GEN5 Carson Creek | 2021-09-23 10:00 | 2021-09-23 14:00 | N | N | due to ATCO Virginia telecom work | Unit
ENMAX | 1.6TR (ENMAX 1) | 2021-09-23 10:00 | 2021-09-23 12:00 | N | N | fall substation washing | Transformer | 1.6TR (ENMAX 1) |  | For Information Only, Pre-Condition
ENMAX | 1.7TR (ENMAX 1) | 2021-09-23 12:00 | 2021-09-23 14:00 | N | N | fall substation washing | Transformer | 1.7TR (ENMAX 1) |  | For Information Only, Pre-Condition
ENMAX | EGC1 Shepard | 2021-09-23 12:30 | 2021-09-23 14:30 | N | N | update firewalls | Unit |  |  | Affects Visibility
ENMAX | 1.8TR (ENMAX 1) | 2021-09-23 14:00 | 2021-09-23 16:00 | N | N | fall substation washing | Transformer | 1.8TR (ENMAX 1) |  | For Information Only, Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe) | 2021-09-24 07:15 | 2021-09-24 13:45 | N | N | maintenance on structures 175 | Line |  |  | Overload, Pre-Condition
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 40.2TR (ENMAX 40) | 2021-09-24 08:00 | 2021-09-24 16:00 | N | N | power factor test 40PT138-Z31 | Line, Transformer |  | Power factor test 40PT138-Z31. 40.2TR already OOS | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EXPPIPE1 | 762s RTU/SCADA (762s Conklin) | 2021-09-24 08:00 | 2021-09-24 17:00 | N | N | RTU update | Terminal Equipment |  |  | Affects Visibility
TERICPOWER | ERV2 Buffalo Creek Battery | 2021-09-24 08:00 | 2021-10-08 16:00 | N | N | P2272 Fortis Alberta Buffalo Creek 526s DER Storage. 20 MW. ISD Oct 1, 2021 | Unit
ALTALINK | 39s 740X (39s Bickerdike) | 2021-09-24 08:30 | 2021-09-24 10:30 | N | N | hot line work - close open point C on 740L | Switch |  | Close open point C on 740L - Hot Line work | For Information Only
ALTALINK | 847L (39s Bickerdike - 406s Fickle Lake) | 2021-09-24 15:00 | 2021-09-24 17:00 | N | Y | close jumpers at 847L str. 847L58 | Line |  | Required to close jumpers at 847L Str.847L58 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 39S Bickerdike | 2021-09-24 17:30 | 2021-09-24 20:00 | N | N | CPS1 hot line work - disconnect temp cables from 740L and 847L | Station |  | Required to disconnect temp cables from 740L and 847L - Hot line work | Pre-Condition
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2021-09-25 08:00 | 2021-09-25 11:00 | N | N | cathodic protection and manhole inspections | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2021-09-25 08:00 | 2021-09-25 16:00 | N | N | cables oil sampling - 138-33.84 line LPOF | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2021-09-25 11:00 | 2021-09-25 12:00 | N | N | investigate leaking cables | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2021-09-25 12:00 | 2021-09-25 16:00 | N | N | 1.81L (ENMAX 1 - ENMAX 20) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8) | 2021-09-26 08:00 | 2021-09-26 12:00 | N | N | cathodic protection and manhole inspections | Line |  |  | For Information Only, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 38.1TR (ENMAX 38), 38.1C (ENMAX 38), 38.3TR (ENMAX 38) | 2021-09-26 08:00 | 2021-09-26 13:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 635-752-653 (635EDD-1001), 635EDD-1001 635-752-652 (635EDD-1001) | 2021-09-26 08:00 | 2021-10-12 17:00 | N | Y | diameter 5 equipment outage | Circuit Breaker |  |  | Restricts Generation
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2021-09-26 12:00 | 2021-09-26 16:00 | N | N | cathodic protection and manhole inspections | Line |  |  | For Information Only
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38) | 2021-09-26 13:00 | 2021-09-26 18:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T5 (EP 511s Victoria), CV5 (EP 511s Victoria - 557s Castle Downs) | 2021-09-27 07:00 | 2021-11-23 14:00 | N | Y | regasketing Victoria T5 | Transformer, Line | E511s Victoria T5 (511s Victoria) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2021-09-27 07:00 | 2021-09-27 09:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s Cloverbar 72kV Bus 3, 72CK12 (987s Clover Bar - Kennedale), 987s CGB2 (987s Clover Bar), 987s CC13 (987s Clover Bar), 987s CCP7213 (987s Clover Bar) | 2021-09-27 07:00 | 2021-09-27 17:00 | N | Y | maintenance | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 935L (324s Cassils - 356s Milo) | 2021-09-27 07:00 | 2021-09-28 18:00 | N | Y | urgent repair insulator change on 935L | Line |  | GOI required for P5 Urgent Repair insulator change on 935L | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 63s T2 (63s Red Deer), 63s T4 (63s Red Deer), 63s 51 (63s Red Deer), 427L (63s Red Deer - 247s Piper Creek), 648L (63s Red Deer - 580s Sylvan Lake) | 2021-09-27 07:30 | 2021-10-01 14:00 | N | Y | wire CT contributions for new 138 kV bus protections and complete trip testing | Transformer, Circuit Breaker, Line | 427L (63s Red Deer - 247s Piper Creek), 648L (63s Red Deer - 580s Sylvan Lake), 63s T2 (63s Red Deer), 63s T2 (63s Red Deer), 63s 25 (63s Red Deer), 63s 51 (63s Red Deer), 63s 427 (63s Red Deer), 63s 648 (63s Red Deer) | Wire CT contributions for new 138kV bus protections and complete trip testing | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
Syncrude | 221 (Aurora), 222 (Aurora) | 2021-09-27 08:00 | 2021-10-17 23:00 | N | Y | maintenance | Circuit Breaker |  | Significant Outage: Generator G21 Isolation to support G21 Outage. MOD # 221B, 222A and 224 wiil be operated at G01 Substation. | Restricts Generation
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2021-09-27 08:00 | 2021-10-24 16:00 | N | Y | line relocation at 101 street | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 29PL6-46 (29EDD-34) | 2021-09-27 08:00 | 2021-10-10 18:00 | N | N | 5 year system PM | Line |  |  | For Information Only
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2021-09-27 08:00 | 2021-09-27 16:00 | N | Y | clearance mitigation | Line |  | GOI on 7L66 for clearance mitigation, there will also be a HOP on 7L91 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2021-09-27 08:00 | 2021-10-01 18:00 | N | Y | forced outage | Shunts |  | The SC had a mechanical failure (Broken Fins). | Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2021-09-27 08:00 | 2021-10-04 12:00 | N | N | changing X arms and installing stubs | Line | 7L12 (834s Wesley Creek - 7LA12 tap) | Changing X Arms and installing stubs | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 35.1TR (ENMAX 35) | 2021-09-27 08:00 | 2021-09-29 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2021-09-27 08:00 | 2021-09-28 16:00 | N | N | tapchanger inspection, oil sampling TC, MT | Transformer |  |  | For Information Only
ALTALINK | 33s 6 (33s Spray) | 2021-09-27 08:00 | 2021-09-30 10:00 | N | N | maintenance | Switch |  | CTs and RTU work by TransAlta | Pre-Condition, Restricts Generation
TRANSALTAGP | EAGL Whitecourt Power | 2021-09-27 08:00 | 2021-10-11 16:00 | N | N | P2415 Whitecourt Generating Station Modification. ISD October 4, 2021 | Unit
ATCO | 848s 608 (848s Ruth Lake) | 2021-09-27 08:30 | 2021-10-01 16:30 | N | N | maintenance | Circuit Breaker | 848s 608 (848s Ruth Lake) | 608 BKR Maintenance | Pre-Condition
ATCO | 826s 901T (826s Marguerite Lake) | 2021-09-27 09:00 | 2021-10-04 09:00 | N | Y | oil reclamation | Transformer |  | 901T oil reclamation | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 2L294 (A.A. Lambert - Cranbrook) | 2021-09-27 09:00 | 2021-09-27 17:00 | N | Y | structure replacement | Line | 2L294 (A.A. Lambert - Cranbrook) |  | Limits ATC, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2021-09-27 09:00 | 2021-09-27 11:00 | N | N | fall pothead washing | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 150L (42s Sarcee - 150AL tap), 42s 150W (42s Sarcee) | 2021-09-27 09:30 | 2021-09-29 16:30 | N | N | migrate and commission all 42s150W, 150L at 42s Sarcee associated line protections, teleprotection, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN | Line, Circuit Breaker | 150L (42s Sarcee - 150AL) | Migrate and commission all 42s150W (952) & L9-150L at 42s Sarcee associated line protections, Teleprotection, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. . SScheduled by: Mohamed Maremi Project PM: Golaleh Rahimi Issue to: Jesse Soonias Contact #: 403-606-8152 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | ATC 793s 703 (ATC 793s West Peace River), 7L06 (787s High Prairie - ATC 793s West Peace River) | 2021-09-27 09:30 | 2021-10-01 12:00 | N | N | PRC-005 trip coil testing breaker, breaker min oil | Circuit Breaker, Line |  | 793S 703 BREAKER MIN OIL HLR COMPLETE TESTING @ WEST PEACE RIVER 793S 703, PRC-005 - TRIP COIL TESTING - BREAKER 703 @ 793S | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L84 (722s Crystal Lake - 749s Flyingshot Lake) | 2021-09-27 10:00 | 2021-09-30 16:00 | N | Y | re-framing structure 59 and 60 | Line |  | Re Framing structure 59 and 60 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 741s 704 (741s Fox Creek), 741s 702T (741s Fox Creek) | 2021-09-27 10:00 | 2021-09-29 16:30 | N | N | breaker complete, load transferred to 741S 701T | Circuit Breaker, Transformer | 741s 702T (741s Fox Creek) | 741S 704 Breaker Complete, load transferred to 741S 701T | For Information Only
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2021-09-27 11:00 | 2021-09-27 13:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 12s 952 (12s Heartland) | 2021-09-27 11:00 | 2021-09-27 17:30 | N | Y | gas top up and take care of breaker trouble alarm | Circuit Breaker |  | Gas top up and take care of breaker trouble alarm | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 398L (277s Hayter - 545s Provost), 545s 398 (545s Provost) | 2021-09-27 11:30 | 2021-09-27 14:30 | N | N | trip testing from new transformer protection | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 83s T1 (83s Taber) | 2021-09-27 12:00 | 2021-09-30 18:00 | N | Y | urgent repair 83s7 broken interrupters on 25 kV bus | Transformer | 83s T1 (83s Taber) | Repair 83s7 broken interrupters on 25 kV bus. From crew lead Trevor Schwartzenberger: "This is the low side of 83sT1. ACC has been advised to only use it under an emergency. I think this should be scheduled in September when the bushings get changed. 25 kV bus outage will be required." Complete 138 kV bushing and 138 kV arrestor replacements on T1. | For Information Only, Restricts Generation
ALTAGAS | Lethbridge Taber (ME02) | 2021-09-27 12:00 | 2021-09-30 18:00 | N | N | urgent repair 83s7 broken interrupters on 25 kV bus | Unit
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2021-09-27 13:00 | 2021-09-27 15:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 199s C1 (199s East Ardrie), 199s 41 (199s East Airdrie) | 2021-09-27 13:30 | 2021-09-30 17:30 | N | N | install/commission new protection | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 715L (545s Provost - 650s Hansman Lake), 545s 715 (545s Provost) | 2021-09-27 14:30 | 2021-09-27 17:30 | N | N | trip testing from new transformer protection | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2021-09-27 16:30 | 2021-10-01 17:00 | N | Y | cross arm and insulator replacement | Line |  | Cross arm and insulator replacement. and attach slack span for tap up for Mobile sub to 846S to 7L28 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2021-09-27 17:30 | 2021-09-27 18:30 | N | N | upgrading one of the Storage Area Networks (SAN) | SCInternal |  |  | For Information Only
ATCO | 844s 701T (844s AEC Mill), 844s 702T (844s AEC Mill) | 2021-09-28 07:00 | 2021-09-28 19:00 | N | N | maintenance | Transformer |  | Slave Lake Pulp (SLP AKA AEC Mill) is planning to have a complete power outage on September 28th, 2021. The outage starts at 7:00am by isolating the mill from the grid (from 701T and 702T) by opening 401TD and 402TD. | For Information Only, Restricts Generation
ATCO | 844s 701T (844s AEC Mill), 7L31 (732s Mitsue - 844s AEC MILL) | 2021-09-28 07:00 | 2021-09-30 17:00 | N | N | 701T maintenance, 844S 700PT1 protection upgrades and 7L31 open ended at 844S | Transformer, Line |  | 701T Maintenance, 844S 700PT1 Protection upgrades, 7L31 open ended at 844S- in conjunction with AEC planned outage. Outage required to Expand GOI to include 700PT1 to facilitate wiring changes required for upcoming 844S Protection upgrade, Slave lake Pulp will be on shutdown during this time. 7L31 and 7L30 will be protected from the 732s Mitsue. | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 498s RTU/SCADA (498s Tilley) | 2021-09-28 08:00 | 2021-09-28 16:00 | N | N | Final acceptance this date, RTU for any small cleanup items required | Terminal Equipment |  | Final acceptance this date, RTU for any small cleanup items required. Visibility to site to be lost for approx 15 minutes during reboot as required. | Affects Visibility
ALTALINK | 62s T5 (62s Brazeau) | 2021-09-28 08:00 | 2021-10-03 18:00 | N | Y | 62sT5 PRC5 doble, maintenance | Transformer | 62s T5 (62s Brazeau) | 62sT5 PRC5 doble, maintenance, buck indicator, gas monitor failure, Connect IDD, LA base insulators, leak from H1, LTC push buttons replace for MR | 240 kV, Creates Radial Feeds, Pre-Condition
SUNCOR | 29PL7-4 (29EDD-65 - 29EDD-71), 29EDD-65 952-4812 (29EDD-65), 29EDD-65 952-4813 (29EDD-65) | 2021-09-28 08:00 | 2021-10-09 18:00 | N | Y | 29EDD65, ;29PT-257 & 29PL7-4 SYSTEMs;PM 5y 29EDD65 ;29PT-260 & 29PL7-4 SYSTEM; PM 5y 29EDD-71;29PT-241 & 29PL7-4 SYSTEM;5y(A) | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2021-09-28 08:00 | 2021-09-28 12:00 | N | N | cathodic protection and manhole inspections | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354s DVAR2 (354s Summerview) | 2021-09-28 08:00 | 2021-09-28 16:00 | N | N | repairs and upgrades | Shunts |  |  | For Information Only
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2021-09-28 08:15 | 2021-09-28 20:00 | N | N | replace insulators on 38s38 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 320p T6 (320p Keephills), 320p PS2 (320p Keephills), 320p 2652 (320p Keephills), 320p 2852 (320p Keephills) | 2021-09-28 09:30 | 2021-10-17 18:00 | N | Y | maintenance, leaks, CT replacement, model 11 relay replacements | Transformer, Circuit Breaker | 320p T6 (320p Keephills) | T6 Maintenance, leaks, CT replacement, Model 11 Relay replacements. | 500 kV, Pre-Condition
ATCO | 850s 701T (850s Rainbow Cogen), 791s 459 (791s Rainbow Lake), 4L230 (850s Rainbow Cogen - 791s Rainbow Lake) | 2021-09-28 12:00 | 2021-10-02 15:00 | N | Y | perform maintenance and testing | Transformer, Circuit Breaker, Line |  | Heartland requested work Perform maintenance testing on the following equipment: 850S 701T 791S BKR 459 | Restricts Generation
ATCO | 7L82 (853s Ring Creek - 855s Hamburg), 853s 701T (853s Ring Creek) | 2021-09-28 14:00 | 2021-10-03 20:30 | N | Y | maintenance, replace PT and repair leaks | Line, Transformer |  | 701T Maintenance, 701TCS Maintenance, Leaks 501VR, Replace 700PT1 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap) | 2021-09-29 07:00 | 2021-10-03 18:00 | N | N | maintenance on structures | Line | 706L (54s Fort Saskatchewan - 706AL) | Maintenance on structures 1, 2, 6, 7, 8, 9, 13, 14, 20, 21, 23, 36, 46, 51, 52, 53, 54 and 60. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20) | 2021-09-29 08:00 | 2021-09-29 12:00 | N | N | fall substation washing | Line, Transformer | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20) |  | Creates Radial Feeds, Pre-Condition
ALTALINK | 69s T5 (69s North Barrhead) | 2021-09-29 08:30 | 2021-09-29 18:00 | N | N | investigate breaker fai | Transformer | Investigate breaker fail initiate issue on 69s723E |  | For Information Only
ALTALINK | 69s 723E (69s North Barrhead), 723L (69s North Barrhead - 724L tap) | 2021-09-29 08:30 | 2021-09-29 18:00 | N | N | investigate breaker fail | Circuit Breaker, Line | investigate breaker fail initiate issue on 69s723E |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 244s 2152 (244s Bowmanton) | 2021-09-29 09:30 | 2021-09-29 13:30 | N | N | breaker maintenance, complete PRC-5 | Circuit Breaker | 244s 2152 (244s Bowmanton) | First trip, then Breaker maintenance, GOI after to complete PRC-5 | Contingency Requires Mitigation
ENMAX | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20) | 2021-09-29 12:00 | 2021-09-29 18:00 | N | N | fall substation washing | Line, Transformer | 20.82L (ENMAX 20 - ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s 2252 (244s Bowmanton) | 2021-09-29 13:35 | 2021-09-29 17:30 | N | N | breaker maintenance, complete PRC-5 | Circuit Breaker | 244s 2252 (244s Bowmanton) | First trip, then Breaker maintenance, GOI after to complete PRC-5 | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 77s 26 (77s Sagitawah) | 2021-09-30 03:30 | 2021-10-18 18:00 | N | N | forced out | Circuit Breaker |  |  | 240 kV
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake), 174L (197s Bardo - 289s Saunders Lake) | 2021-09-30 07:00 | 2021-09-30 15:00 | N | N | high load move | Line | 858L (40s Wetaskiwin - 289s Saunders Lake) | 174L - High load move between Structures #46 & 47 858L - High load move between Structures #203 & 204 | Over/Under Voltage, Pre-Condition
BHE | 719s Rattlesnake Ridge | 2021-09-30 08:00 | 2021-10-03 16:45 | N | N | preparation for altalink work on 879L | Station |  |  | Firm Load Loss, For Information Only
ENMAX | 35.2TR (ENMAX 35) | 2021-09-30 08:00 | 2021-10-04 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2021-09-30 08:00 | 2021-09-30 16:00 | N | N | cathodic protection and manhole inspections | Line |  |  | Pre-Condition
ALTALINK | 332s C1 (332s Ellis) | 2021-09-30 08:30 | 2021-09-30 17:30 | N | N | 138kV breaker maintenance | Shunts |  |  | Pre-Condition
ALTALINK | 767L (320p Keephills - 767AL tap) | 2021-09-30 08:30 | 2021-09-30 17:30 | N | N | 320p767N maintenance and replace grading capacitors | Line |  |  | For Information Only, Affects Cranking Path
ATCO | 741s 701 (741s Fox Creek), 7L90 (741s Fox Creek - 7LA90 tap) | 2021-09-30 09:00 | 2021-09-30 17:30 | N | N | top up 741S 701 | Circuit Breaker, Line |  | Top Up 741S 701 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 755s 901 (755s Cordel) | 2021-10-01 07:00 | 2021-10-05 16:30 | N | Y | replace 755S 901CT | Circuit Breaker |  | Replace 755S 901CT 757S Protection upgrade to 9L79 relays, testing of MODs @755s Oct1, 2021, 755S 901A & 755S 902B - due to changes of Heartland Generation outage Oct 2, 2021 12:01- Oct 5, 2021 16:30 - 755S 901A & 755S 902B & COG From Heartland on 757S 9L79D1. | 240 kV, Contingency Requires Mitigation
IMPERIALOIL | 889s 5CB-G1 (889s Mahkeses) | 2021-10-01 07:00 | 2021-10-01 15:00 | N | Y | replacement of breaker | Circuit Breaker |  | replacement of generator breaker | For Information Only, Restricts Generation
ALTALINK | 879L (244s Bowmanton - 368s Burdett), 368s 879 (368s Burdett), 244s 3152 (244s Bowmanton), 244s 3252 (244s Bowmanton) | 2021-10-01 07:15 | 2021-10-03 16:45 | N | N | line protection upgrades | Line, Circuit Breaker | 879L (244s Bowmanton - 368s Burdett) | line protection upgrades at 244s and 368s and re-conductor 879AL T-tap (Rattlesnake Ridge) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 2.1TR (ENMAX 2) | 2021-10-01 08:00 | 2021-10-01 16:00 | N | N | winding temp gauge replacement | Transformer |  | 2.1TR Winding temp gauge replacement. 2.1TR LTC counter not working | For Information Only
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 33.1TR (ENMAX 33) | 2021-10-01 08:00 | 2021-10-01 16:00 | N | N | power factor test 33PT138-Z31 | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MHS9 T11 (MHS9 Power Plant), MH-6L (MH69s-1 Power Plant Switchyard - MHS9 Power Plant) | 2021-10-01 08:00 | 2021-10-03 16:00 | N | Y | install new PT | Transformer, Line | MHS9 T11 (MHS9 Power Plant), MH-6L (MH69s-1 Power Plant Switchyard - MHS9 Power Plant) | replace 69kV bus PTs 106 and 107 | Pre-Condition, Restricts Generation
ALTALINK | 63s 240kV South Bus (63s Red Deer), 63s T2 (63s Red Deer), 63s 352 (63s Red Deer), 63s 652 (63s Red Deer), 63s 952 (63s Red Deer), 63s 2752 (63s Red Deer), 63s 25 (63s Red Deer) | 2021-10-01 14:00 | 2021-10-04 17:00 | N | Y | wire CT contributions for new 138kV bus protections and complete trip testing | Bus, Transformer, Circuit Breaker | 63s 2752 (63s Red Deer), 63s 952 (63s Red Deer), 63s 652 (63s Red Deer), 63s 352 (63s Red Deer), 63s T2 (63s Red Deer) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 9L79 (755s Cordel - 757s Battle River), 757s 911 (757s Battle River) | 2021-10-01 20:00 | 2021-10-06 17:00 | N | Y | replace breaker operating mech's | Line, Circuit Breaker |  | Heartland Notice - Replace Breaker operating mech's on 757S 911 | 240 kV, For Information Only, Restricts Generation,Affects Cranking Path
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 36.5TR (ENMAX 36), 36.2TR (ENMAX 36), 16.63L (ENMAX 16 - ENMAX 36) | 2021-10-02 08:00 | 2021-10-02 18:00 | N | N | fall substation washing and replace PRD junction box. relays, lockout testing 86B-Z32. | Line, Transformer |  | Fall Substation Washing. 36.2 MD east phase wont open past 90. 36.5TR Replace PRD Junction Box. Relays, Lockout Testing 86B-Z32. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.1TR (ENMAX 40) | 2021-10-03 08:00 | 2021-11-05 16:00 | N | N | install new Albarrie, plastibeton, duct banks and cables phasing required on return | Transformer |  |  | For Information Only
ATCO | 809s 910 (809s Louise Creek) | 2021-10-03 17:00 | 2021-10-04 08:00 | N | Y | partial protection upgrade and will be completed under the 9L02 outage | Circuit Breaker |  | When 902T & 9L938 outage is complete on October 3, 2021, Breaker 809S 910 will remain OOS as it is a shared breaker with the following 9L02 outage on Oct 4, 2021. OOS due to only a partial protection upgrade and will be completed under the 9L02 outage Oct. 4-24, 2021 | 240 kV, Contingency Requires Mitigation
ALTALINK | 827L (28s West Brooks - 121s Brooks) | 2021-10-04 06:15 | 2021-10-13 16:45 | N | N | 827L A21/B21 line protection replacement at121s and 28s, 1152(121s827) CT and CTJB replacement | Line |  | 1st scope 827L A21/B21 Line Protection Replacements@ 121s, 2nd scope 827L A21/B21 Line Protection Replacements @ 28s 1152(121s827) CT and CTJB replacement | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
AESO-SC | SCC | 2021-10-04 07:00 | 2021-10-22 18:00 | N | N | generator control system replacement | SCInternal |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper) | 2021-10-04 07:00 | 2021-10-06 17:00 | N | Y | 15kV bus PT investigation | Transformer |  |  | 240 kV, For Information Only
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs) | 2021-10-04 07:00 | 2021-10-15 17:00 | N | Y | CV5 manhole inspections | Line |  |  | 240 kV, For Information Only
EPCOR | 330p 1201 (330p Genesee) | 2021-10-04 07:00 | 2021-10-06 17:00 | N | Y | 1201 Maintenance and CT Doble | Circuit Breaker | 330p 1201 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 33.2TR (ENMAX 33) | 2021-10-04 08:00 | 2021-10-04 13:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 809s 503R (809s Louise Creek), 809s 504R (809s Louise Creek) | 2021-10-04 08:00 | 2022-03-03 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
ENMAX | 8.1TR (ENMAX 8) | 2021-10-04 08:00 | 2021-10-05 16:00 | N | N | transformer maintenance | Transformer |  | tapchanger inspection. check reversing switch. Gas Relay Testing. Transformer Maintenance | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2021-10-04 08:00 | 2021-10-06 16:00 | N | N | 31.3TR CT replacement | Transformer |  |  | For Information Only
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2021-10-04 08:00 | 2021-10-08 17:00 | N | Y | change arms insulators | Line | 7L77 (395s North Holden - 709s Vegreville) | GOI on 7L77 from 7L77D1 to 395S Holdon change arms insulators | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L02 (809s Louise Creek - 813s Little Smoky), 809s 903 (809s Louise Creek), 809s 910 (809s Louise Creek) | 2021-10-04 08:01 | 2021-11-02 17:00 | N | Y | Louise Creek rebuild project | Line, Circuit Breaker |  | Louise Creek Rebuild project Wiring for 903/910BF relays. CT ratio changes. Relay programming and functionality. Commission control, alarms and status. Blocking procedures for BF protections. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO | 848s 604 (848s Ruth Lake) | 2021-10-04 08:30 | 2021-10-04 16:30 | N | N | 604 breaker maintenance | Circuit Breaker |  | 604 BKR Maintenance | For Information Only
ALTALINK | 764L (304s Shell Limestone - 581s Amoco Ricinus), 719AL (581s Amoco Ricinus - 719L tap) | 2021-10-04 08:30 | 2021-10-06 17:00 | N | N | line maintenance | Line | (719AL) maintenance on structure 81. (764L) maintenance on structures 1, 7, 50, 53, 143. (304s) 25kV breaker maintenance (304s281X). Maintenance, doble (T2 (TX18585)), install polymer insulator and ring. (581s) hotspots, adjust switches (581s2, 581s719AL) |  | For Information Only
BCH | 2L293 (Nelway - Selkirk) | 2021-10-04 09:00 | 2021-10-08 17:00 | N | Y | structure replacement, BC maintenance does not affect the Alberta ATC | Line | 2L293 (Nelway - Selkirk) | structure replacement, BC Maintenance does not affect the Alberta ATC | For Information Only, Limits ATC
BCH | 5L52 (Custer - Ingledow) | 2021-10-04 09:00 | 2021-10-04 13:00 | N | Y | BPA outage | Line |  |  | Limits ATC, 500 kV
ALTALINK | 42s 76 (42s Sarcee), 42s C3 (42s Sarcee) | 2021-10-04 09:30 | 2021-10-06 16:30 | N | Y | migrate and commission all Cap bank C3 & 42S76 (2252) | Circuit Breaker, Shunts | Migrate and commission all Cap bank C3 & 42S76 (2252) associated protections, breakers, breaker fail, POW alarms, status, controls, metering and remote access to new RTU and LAN. |  | For Information Only
ALTALINK | 61s T1 (61s Lodgepole), 836L (61s Lodgepole - 283s Violet Grove), 202L (61s Lodgepole - 202AL tap) | 2021-10-04 11:00 | 2021-10-08 13:00 | N | Y | replacing 61s13 and strain insulators on 836L | Transformer, Line | 61s T1 (61s Lodgepole), 202L (61s Lodgepole - 62s Brazeau), 836L (61s Lodgepole - 283s Violet Grove) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 741s 504C (741s Fox Creek) | 2021-10-04 11:00 | 2021-10-05 17:00 | N | N | 504 maintenance and leak repair | Shunts |  | 504 Maint and leak repair, 504C 5Mvar Capacitor will be unavailable for the duration | For Information Only
WINDYPWPL | 112S Windy Point | 2021-10-04 12:00 | 2021-10-07 15:00 | N | N | repair cables | Station | We would like to request a full outage for Old Man II windfarm from 10/4/2021 HE1300MDT to 10/7/2021 1500MDT. We will be taking the site offline to pull old cables out and install new cables for the low side MPT to restore the windfarm back to full capacity. We are also providing safe access to replace pad mount foundation for Turbine #6. Please let me know if you have any questions. |  | Restricts Generation
ALTALINK | 410s T1 (410s Josephburg) | 2021-10-04 12:00 | 2021-10-07 12:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 48s 887X (48s Pocaterra), 887L (48s Pocaterra - BCH Britt Creek) | 2021-10-04 12:15 | 2021-10-08 17:45 | N | Y | install breaker failure protection | Circuit Breaker, Line | 887L (48s Pocaterra - BCH Britt Creek) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C3 (74s Janet) | 2021-10-04 12:30 | 2021-10-04 17:30 | N | Y | emergency repair; change settings/test relay | Shunts |  | emergency repair; change settings/test relay (re: mis-operation) | 240 kV, Pre-Condition
ATCO | 757s 705 (757s Battle River) | 2021-10-04 13:00 | 2021-10-04 17:00 | N | N | PRC 005 work on 705 Breaker | Circuit Breaker |  | PRC005 work on 705 Breaker, heartland will need to transfer SST to alternate source for unit#5 Unit #5 shut down from October 1-5 | For Information Only
ENMAX | 33.83L (ENMAX 33 - ENMAX 41) | 2021-10-04 13:00 | 2021-10-04 16:00 | N | N | fall substation washing | Line | fall substation washing 33B138-33.83L breaker only. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 251s SR2 (251s Whitla) | 2021-10-05 07:00 | 2021-10-05 16:30 | N | Y | urgent repair to replace and test top oil temperature sensor | Shunts |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 995S Rangelandyarrow, 185AL (415s Drywood - 995s Yarrow) | 2021-10-05 08:00 | 2021-10-07 18:00 | N | N | completion of scope on 185AL, replace dead-end insulation on 185AL | Station, Line
SUNCOR | 29EDD-22 | 2021-10-05 08:00 | 2021-10-20 18:00 | N | N | 29PT-84 OLTC maintenance, bird cover and stress cones | Station | 29EDD-22 29PT-84 OLTC Maintenance, bird cover and stress cones |  | For Information Only
ALTALINK | 285s T1 (285s East Camrose) | 2021-10-05 08:00 | 2021-10-07 18:00 | N | N | bushings replacement | Transformer
ALTALINK | 526L (515s Fed Pipe Judy Creek - 6L126 tap) | 2021-10-05 08:00 | 2021-10-05 17:00 | N | N | component replacement on structures #442, 470 & 505 | Line
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28) | 2021-10-05 08:00 | 2021-10-05 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 848s 906 (848s Ruth Lake) | 2021-10-05 08:30 | 2021-10-06 16:30 | N | Y | breaker maintenance | Circuit Breaker |  | 906 BKR Maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 789s 705R (789s Keg River) | 2021-10-05 09:00 | 2021-10-07 17:30 | N | N | leak repair | Shunts |  | 705R Leak Repair | Pre-Condition
ENMAX | 1.80L (ENMAX 1 - ENMAX 28), 28.1TR (ENMAX 28) | 2021-10-05 12:00 | 2021-10-05 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s T2 (523s Bullshead) | 2021-10-06 07:00 | 2021-10-06 16:30 | N | N | urgent - replace and test top oil RTD sensor | Transformer |  | Outage required on T2 (TX18933) to replace and test top oil RTD sensor. Work scope is classified as urgent repair by Altalink. | For Information Only
ALTALINK | 703L (213s Hughenden - 703BL) | 2021-10-06 07:00 | 2021-10-06 18:00 | N | N | urgent repair on structure 703L83 | Line | 703L (213s Hughenden - 703BL) | GOI required for P5 Urgent Repair on structure 703L83 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2021-10-06 07:00 | 2021-10-09 18:00 | N | Y | repositioning line on structure #287 for future T- tap | Line | 964L (244s Bowmanton - 251s Whitla) | Repositioning line on Structure #287 for future T-tap | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 370s T1 (370s North Lethbridge), 370s T4 (370s North Lethbridge) | 2021-10-06 07:30 | 2021-10-06 17:30 | N | N | cut free section of bus between 370s5 and 370s45/370s4. create open points "C" for future 25 kV BUS & "D" & "E" to faciliate AMI move | Transformer |  | Cut free section of bus between 370s5 and 370s45/370s4. Create Open Points "C" for future 25kV BUS & "D" & "E" to faciliate AMI move. Requires DG at 370s to be offline for duration of the outage. | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2021-10-06 08:00 | 2021-10-12 18:00 | N | N | NGR installation | Transformer |  |  | For Information Only
SUNCOR | 635PL7-1004 (635EDD-1001 - 635EDD-1002), 635PT-1036 (635EDD-1001), 635EDD-1001 635-752-651 (635EDD-1001), 635EDD-1001 635-752-652 (635EDD-1001), 635EDD-1001 635-752-653 (635EDD-1001) | 2021-10-06 08:00 | 2021-10-21 17:00 | N | Y | dia 5 equipment outage at 635EDD-1001 | Line, Transformer, Circuit Breaker | 635-752-651, 635-752-652, 635-752-653 and 635PT-1069, 635PT-1036 | 144kV Central Sub 635EDD-1001 Dia 5 Equipment Outage | Pre-Condition, Restricts Generation
CMH | MH-16L (MH69S-2 - MH69S-16), MH69s2 MH69-224 (MH69s2 North Industrial) | 2021-10-06 08:00 | 2021-10-13 08:00 | N | Y | construction at the CMH facility | Line, Circuit Breaker | MH69-224 Circuit breaker MH69-225 Switch 662-SW-8001 | construction at the CMH Power Generation facility | Pre-Condition, Restricts Generation
VISIONREQ | 354s DVAR1 (354s Summerview), 354s DVAR2 (354s Summerview) | 2021-10-06 08:00 | 2021-10-06 16:00 | N | Y | integration work for WindCharger | Shunts |  |  | For Information Only, Restricts Generation
ENMAX | 16.60L (ENMAX 16 - ENMAX 34), 34B69-16.60 (ENMAX 34) | 2021-10-06 08:00 | 2021-10-06 12:00 | N | N | investigate SEL 321 relay | Line, Circuit Breaker |  | Investigate SEL 321 relay. Troubleshoot 69kV PT sec. circuit if required. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.5TR (ENMAX 8) | 2021-10-06 08:00 | 2021-10-22 16:00 | N | N | HV bushing replacement, testing and maintenance | Transformer |  | HV Bushing Replacement. Power factor test transformer, Secondary Cable Tests, Transformer Maintenance. Gas Relay Testing. Check reversing switch, Oil Sampling MT, TC. Summer Washing. | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-10-06 11:00 | 2021-10-06 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 34B69-21.61 (ENMAX 34) | 2021-10-06 12:00 | 2021-10-06 16:00 | N | N | investigate SEL 321 relay | Line, Circuit Breaker |  | Investigate SEL 321 relay. Troubleshoot 69kV PT sec. circuit if required. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.7TR (ENMAX 5) | 2021-10-06 16:00 | 2021-10-21 16:00 | N | N | relay replacement and testing | Transformer |  | relay replacement, substation - Relays, Lockout Testing. Outage continues from Z31 bus outage | For Information Only
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 48S Pocaterra | 2021-10-07 07:30 | 2021-10-07 18:00 | N | Y | install breaker failure protection for breaker 252 | Line, Station | 777L (48s Pocaterra - 245s Seebe) |  | For Information Only, Pre-Condition
ENMAX | 1.82L (ENMAX 1 - ENMAX 5), 5B138-1.82 (ENMAX 5) | 2021-10-07 08:00 | 2021-10-30 16:00 | N | N | 5sub TRV project: replace circuit breaker | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 535s 1152 (535s Joffre) | 2021-10-07 08:15 | 2021-10-07 17:45 | N | N | add grading capacitors on 535s1152 and other breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-10-07 09:00 | 2021-10-07 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK, EPCOR | 89s 652 (89s Ellerslie), 89s 752 (89s Ellerslie), 908L (89s Ellerslie - 816s Petrolia) | 2021-10-07 09:30 | 2021-10-07 13:30 | N | Y | fix wiring in 89s75 secondary box | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 332s 423 (332s Ellis), 423L (212s N.E.Lacombe - 332s Ellis) | 2021-10-07 09:30 | 2021-10-07 15:30 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1081L (17s Benalto - 281s Johnson) | 2021-10-08 07:00 | 2021-10-08 18:00 | N | Y | P5 urgent repair: replace insulators 1081L506 | Line |  |  | 240 kV, For Information Only
ALTALINK | 336s 610 (336s Fincastle), 610L (83s Taber - 336s Fincastle) | 2021-10-08 11:15 | 2021-10-12 16:45 | N | Y | complete wiring for CT inputs to the new RAS relays from breaker 336s610 and test | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 930s Syn Condenser (930s Arcenciel) | 2021-10-08 14:50 | 2021-10-19 18:00 | N | Y | forced outage | Shunts |  | The SC had a mechanical failure (Broken Fins). | Pre-Condition
ALTALINK | 747L (99s North St. Albert - 711L tap) | 2021-10-09 06:00 | 2021-10-09 20:00 | N | N | urgent replacement of 747L structures 58 and 59 due to sinkhole | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 749L (648s Metiskow - 749AL tap) | 2021-10-09 07:00 | 2021-10-12 18:00 | N | N | urgent repair installation of clamp star assemblies | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 164L (103s Goose Lake - 415s Drywood), 415s T1 (415s Drywood) | 2021-10-09 07:30 | 2021-10-11 16:30 | N | N | replace the T1"A" protection and add neutral CT circuit & protection and maintenance on structures | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2021-10-09 08:00 | 2021-10-09 16:00 | N | N | SF6 top up, low density alarm | Line
ENMAX | 21.1C (ENMAX 21) | 2021-10-09 10:00 | 2021-10-09 16:00 | N | N | fall substation washing | Shunts |  |  | For Information Only
ALTALINK | 924L (102s Langdon - 356s Milo) | 2021-10-10 07:00 | 2021-10-12 18:00 | N | Y | bird flight diverter installation | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 1206L (12s Heartland - 89s Ellerslie) | 2021-10-11 09:30 | 2021-10-13 18:00 | N | Y | maintenance on structures | Line | 1206L (12s Heartland - 89s Ellerslie) |  | 500 kV, Pre-Condition
ALTALINK | 415s 352 (415s Drywood), 185L (379s Shell Canada Waterton - 415s Drywood), 185AL (415s Drywood - 995s Yarrow) | 2021-10-11 16:30 | 2021-10-11 18:30 | N | N | verify tripping to 352 from T2 "B" protection | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 665s DDS4 (665s Dome), 665s T2 (665s Dome), 909L (310p Sundance - 665s Dome) | 2021-10-12 07:00 | 2021-10-12 17:00 | N | Y | DDS4 maintenance | Switch, Transformer, Line | 665s T2 (665s Dome), 665s DDS4 (665s Dome) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
AIRLIQUIDE | ALC03L (402s Scotford Expansion - 408s Air Liquide Scotford) | 2021-10-12 08:00 | 2021-10-13 17:00 | N | Y | replacing and cleaning insulators | Line |  | Replacing and cleaning insulators ALCO03L | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 7L12 (834s Wesley Creek - 869s Seal Lake) | 2021-10-12 08:00 | 2021-10-18 12:00 | N | N | changing crossarms and installing stubs | Line |  | Changing X Arms and installing stubs | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2021-10-12 08:00 | 2021-11-20 16:00 | N | N | TRV project. replace circuit breaker | Line | 2.83L (ENMAX 5 - 2.83L tap) |  | For Information Only, Pre-Condition
ENMAX | 36.2TR (ENMAX 36) | 2021-10-12 08:00 | 2021-10-13 16:00 | N | N | Tapchanger inspection. Oil sampling MT, TC. Filmax LTC Oil Filtration Maintenance | Transformer |  |  | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2021-10-12 08:00 | 2021-10-12 10:00 | N | N | TRV mitigation investigation | Transformer |  |  | For Information Only
ATCO | 720s 902T (720s Wabasca) | 2021-10-12 08:00 | 2021-10-15 16:00 | N | Y | leak mitigation and transformer maintenance | Transformer |  | 902T leak mitigation and transformer maintenance | 240 kV, For Information Only
ATCO | 977s 901T (977s Salt Creek), 7L135 (820s Hangingstone - 977s Salt Creek) | 2021-10-12 08:30 | 2021-10-15 16:50 | N | Y | 901T maintenance | Transformer, Line |  | 901T maintenance | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2021-10-12 09:00 | 2021-10-14 17:00 | N | Y | install and commission new SCADA meter | Line | Migrate and commission all 42s7 (1552) & L15-7.82L at 42s Sarcee associated line protections, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Install and commission new SCADA meter. |  | For Information Only, Pre-Condition
BCH | 2L112 (Boundary - Nelway) | 2021-10-12 09:00 | 2021-11-12 17:00 | N | Y | oil containment install, BC Maintenance does not affect the Alberta ATC | Line | 2L112 (Nelway - Boundary) | Oil containment install | 240 kV, Limits ATC
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove) | 2021-10-12 09:30 | 2021-10-24 15:30 | N | N | replace 99s21 switch and 99s712X breaker | Line | 712L (99s North St. Albert - 595s Spruce Grove) | Replace 99s21 switch and 99s712X breaker. Add surge arresters to 712L. Replace 712L protections. Add 96/79/252 protection. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s T1 (370s North Lethbridge) | 2021-10-12 09:30 | 2021-10-12 17:30 | N | N | install 25kV bus 1 AMI at new location | Transformer | Install 25kV bus 1 AMI at new location. Close open point D & E to restore AMI. Requires DG at 370s to be offline for duration of the outage. |  | For Information Only, Restricts Generation
ENMAX | 38.3TR (ENMAX 38) | 2021-10-12 10:00 | 2021-10-12 12:00 | N | N | TRV mitigation investigation | Transformer |  |  | For Information Only
ALTALINK | 253s 753W (253s Blackie), 753L (65s High River - 253s Blackie) | 2021-10-12 12:00 | 2021-10-14 17:00 | N | Y | breaker maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
BCH | 1L274 (Britt Creek - 1D4L274) | 2021-10-12 12:00 | 2021-10-12 16:00 | Y | Y | repair damaged conductor riser near BCK 1D21 | Line | 1L274 (Britt Creek - 1D4L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
ALTALINK | 13s 815W (13s Deerland), 815L (13s Deerland - 127s Bruderheim) | 2021-10-12 12:00 | 2021-10-12 18:30 | N | N | diode replacement | Switch, Line | Investigate a circuit issue on 13s815W. D1 diode replacement in 489 circuit. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 42s 74 (42s Sarcee), 42s C2 (42s Sarcee) | 2021-10-12 13:00 | 2021-10-14 17:00 | N | Y | PRC005 relay maintenance | Circuit Breaker, Shunts | Techs will require 42sC2 Cap bank OOS to complete PRC005 compliant relay maintenance and trip path verifications. |  | 240 kV, Pre-Condition
ALTALINK | 526s T1 (526s Buffalo Creek) | 2021-10-12 13:00 | 2021-10-14 17:00 | N | N | doble, fix heater, fix leaks | Transformer | 526s T1 (526s Buffalo Creek) | T1 doble, remove nest. VR1 maintain, doble, fix heater, fix leaks | For Information Only
REDDEER, ALTALINK | 209S Timberlands, 209s 768W (209s Timberlands), 464L (87s Gaetz - 209s Timberlands), 768L (209s Timberlands - 217s North Red Deer), 209s T1 (209s Timberlands) | 2021-10-12 15:00 | 2021-10-25 09:00 | N | Y | P&C relay testing and maintenance | Station, Circuit Breaker, Line, Transformer |  |  | Pre-Condition
ALTALINK | 62s 12 (62s Brazeau) | 2021-10-12 23:00 | 2021-10-14 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 749L (899s Edgerton - 749L118AN) | 2021-10-13 07:00 | 2021-10-17 18:00 | N | Y | urgent repair installation of clamp star assemblies 749L Str 119-295A. | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo) | 2021-10-13 07:00 | 2021-10-16 18:00 | N | Y | structure maintenance | Line |  | GOI required for Bird Flight Diverter Installation on 927L Structures 257-264 | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 162L (229s Glenwood - 415s Drywood) | 2021-10-13 07:15 | 2021-10-15 16:45 | N | N | Tx line protection | Line |  | Install and connect new 69kv PTs, tie in new VT input to TX protection. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Restricts Generation
ATCO | 2075s ACF21 (2075s Newell) | 2021-10-13 07:56 | 2021-10-26 18:00 | N | Y | forced outage | Shunts |  |  | 240 kV
ALTALINK | 121s T5 (121s Brooks) | 2021-10-13 08:00 | 2021-10-14 18:00 | N | N | commissioning 27/138BN & T5 CT wiring change | Transformer |  | 121s83X Protection setting change, cutover, and trip test. Commissioning 27/138BN & T5 CT wiring change, 2nd scope install VT on breaker 121s83X. | For Information Only, Restricts Generation
BSC | BSC1 Brooks Solar | 2021-10-13 08:00 | 2021-10-13 15:00 | N | N | 121sT5 outage | Unit
TRANSALTA | 229s T1 (229s Glenwood), 229s T2 (229s Glenwood) | 2021-10-13 08:15 | 2021-10-15 17:15 | N | N | transformer protection and commissioning / testing | Transformer |  | connect new voltage input to transformer protection and commissioning / testing | Creates Radial Feeds, Firm Load Loss
ATCO | 828s 507 (828s Sulphur Point), 828s 507C1 (828s Sulphur Point), 828s 507C2 (828s Sulphur Point) | 2021-10-13 08:30 | 2021-10-13 16:30 | N | N | 507 complete maintenance and electrical testing | Circuit Breaker, Shunts |  | 507 Complete Maintenance and Electrical Testing, 507, 501C1 & 507C@ OOS for the Duration of the work | For Information Only, Pre-Condition
ATCO | 749s 704 (749s Flyingshot Lake) | 2021-10-13 09:00 | 2021-10-14 16:30 | N | N | testing | Circuit Breaker |  | 749S 704 testing | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 58s 35 (58s Edson), 58s C1 (58s Edson) | 2021-10-13 10:30 | 2021-10-13 18:00 | N | N | investigate 58s35 breaker status issues | Circuit Breaker, Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 1212L (12s Heartland - 89s Ellerslie) | 2021-10-14 07:00 | 2021-10-16 18:00 | N | Y | maintenance on structures 31, 42, 46, 71 and 76 | Line | 1212L (12s Heartland - 89s Ellerslie) | Scope of work includes maintenance on structures 31, 42, 46, 71 and 76 | 500 kV, Pre-Condition
ALTALINK | 215L (38s East Edmonton - 286s Yasa), 38s 215N (38s East Edmonton) | 2021-10-14 07:00 | 2021-10-16 15:00 | N | N | installing foundation for future monopole dead end for future T-Tap on 215L to new 309s Anthony Henday | Line, Circuit Breaker | 215L (38s East Edmonton - 286s Yasa) | Installing foundation for future monopole dead end for future T-Tap on 215L to new 309s Anthony Henday. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 844L (358s Amoco Brazeau - 477s Amoco West Pembina) | 2021-10-14 07:00 | 2021-10-16 18:00 | N | N | maintenance on structures 1A, 1B, 10, 69 and 72 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | EX1-01L (402s Scotford Expansion - 879s Scotford Upgrader) | 2021-10-14 08:00 | 2021-10-15 15:00 | N | N | cleaning and replacing insulators | Line | EX1-01L (402s Scotford Expansion - 879s Scotford Upgrader) | Cleaning and replacing insulators EX1-01L. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 16.2TR (ENMAX 16) | 2021-10-14 08:00 | 2021-10-15 16:00 | N | N | tapchanger inspection, check reversing switch, oil sampling MT, TC | Transformer |  | Tapchanger inspection. Check Reversing Switch. Oil sampling MT, TC | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2021-10-14 08:00 | 2021-10-18 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ALTALINK | 879L (244s Bowmanton - 368s Burdett), 368s C1 (368s Burdett), 368s C2 (368s Burdett), 368s T1 (368s Burdett) | 2021-10-14 08:15 | 2021-10-15 15:45 | N | N | install/commission new protections (rattlesnake ridge) (P2212) | Line, Shunts, Transformer | 879L (244s Bowmanton - 368s Burdett), 368s C1 (368s Burdett), 368s C2 (368s Burdett) | install/commission new protections (rattlesnake ridge) (P2212) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
AOSI | BRD1 Burdett Solar | 2021-10-14 08:15 | 2021-10-15 15:45 | N | N | 879L, 368sT1, 368sC1 & C2 outage | Unit
ALTAGAS | Lethbridge Burdett (ME03) | 2021-10-14 08:15 | 2021-10-15 15:45 | N | N | 879L, 368sT1, 368sC1 & C2 outage | Unit
FORTIS | BUR1 Burdett Solar | 2021-10-14 08:15 | 2021-10-15 15:45 | N | N | 879L, 368sT1, 368sC1 & C2 outage | Unit
ATCO | GEN6 Judy Creek Generator | 2021-10-14 10:00 | 2021-10-14 14:00 | N | N | 852s, 809s RTU/SCADA work | Unit
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2021-10-15 08:00 | 2021-10-15 10:00 | N | N | fall transmission line washing | Line | 15.62L (ENMAX 15 - ENMAX 16) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 749s 702 (749s Flyingshot Lake) | 2021-10-15 09:00 | 2021-10-15 16:30 | N | N | 749S 702 testing | Circuit Breaker | 749s 702 (749s Flyingshot Lake) | 749S 702 testing | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2021-10-15 10:00 | 2021-10-15 12:00 | N | N | fall transmission line washing, shared structure with 15.62L | Line | 16.60L (ENMAX 16 - ENMAX 34) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2021-10-15 12:00 | 2021-10-15 14:00 | N | N | fall transmission line washing | Line | 16.61L (ENMAX 16 - ENMAX 27) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 722L (107s Westfield - 368s Burdett), 612L (336s Fincastle - 368s Burdett), 368s C1 (368s Burdett), 368s C2 (368s Burdett), 368s T2 (368s Burdett) | 2021-10-16 08:15 | 2021-10-17 15:45 | N | N | install/commission new protections (rattlesnake ridge) | Line, Shunts, Transformer | 722L (107s Westfield - 368s Burdett), 612L (336s Fincastle - 368s Burdett), 368s C1 (368s Burdett), 368s C2 (368s Burdett) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 820L (254s Coaldale - 820AL tap), 820AL (315s Chin Chute - 820L tap), 820L (67s Stirling - 820AL tap) | 2021-10-17 07:15 | 2021-10-19 17:45 | N | Y | maintenance on structures 160, 161, 168, 175, 176, 177, 179, 187, 190, 197 and 198 | Line | 820L (254s Coaldale - 820AL tap), 820AL (315s Chin Chute - 820L tap), 820L (67s Stirling - 820AL tap) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2021-10-18 07:30 | 2021-10-22 17:30 | N | Y | replace point on wave relay associated with 510s1452 and ACF14 TX 18882 | Shunts |  |  | 500 kV, Pre-Condition
ENMAX | 24.82L (ENMAX 24 - ENMAX 65) | 2021-10-18 08:00 | 2021-10-22 16:00 | N | N | cable trench replacement | Line |  |  | Pre-Condition
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2021-10-18 08:00 | 2021-10-29 18:00 | N | Y | urgent repair damper | Line | GOI required for P5 Urgent Repair damper scope between structures 82 and 262. *Completion of Damper Replacement CRU scope between Structures 300 & 367 will coincide with this outage. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | D05 T2 (D05 Syncrude) | 2021-10-18 08:00 | 2021-10-18 20:00 | N | Y | T2 transformer outage | Transformer | Significant Outage: T2 Transformer (260/72KV) in D05 Substation Following Circuit Breakers will be operated to isolate T2: 516, 513, 78 Following MOD's will be operated to isolate T1: 516A, 516B, 513A, 513B, 509, 78A, 78B |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 888s 906 (888s Dover) | 2021-10-18 09:00 | 2021-10-20 16:15 | N | Y | breaker maintenance | Circuit Breaker |  | Breaker Maintenance 906 | Contingency Requires Mitigation
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2021-10-18 09:00 | 2021-10-27 20:47 | Y | Y | components-structure range 383-464 | Line | 1201L (520s Bennett - BCH Cranbrook) |  | 500 kV, Pre-Condition, Affects Cranking Path
MONTANA, ENBRIDGE | MATL (120s Picture Butte - Montana), Hay Lake North Series Capacitor | 2021-10-18 09:00 | 2021-10-18 18:00 | N | Y | annual maintenance routine | Line, Shunts | MATL (120s Picture Butte - Montana) | Annual maintenance routine - in conjunction with south bound and 1201L outage. The following maintenance items will be completed; K-Line Line maintenance | 240 kV, Limits ATC, Pre-Condition
ATCO | 743s 601 (743s Sarah Lake), 6L126 (743s Sarah Lake - 515L tap) | 2021-10-18 09:00 | 2021-10-20 16:00 | N | N | breaker maintenance | Circuit Breaker, Line | 6L126 (743s Sarah Lake - 515L tap) | 743S 601 Breaker Maintenance. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L94 (Cranbrook - 102s Langdon) | 2021-10-18 09:00 | 2021-10-21 17:00 | Y | Y | NERC PM | Line | 5L94 (Cranbrook - 102s Langdon) |  | 500 kV, Pre-Condition
ATCO | 811s 701C (811s Clairmont Lake) | 2021-10-18 09:00 | 2021-10-19 17:00 | N | N |  | Shunts | 811s 701C (811s Clairmont Lake) | 701CCS complete maintenance, 701C OOS for duration | Pre-Condition
ENBRIDGE, MONTANA | 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte) | 2021-10-18 09:00 | 2021-10-19 18:00 | N | Y | annual maintenance routine | Transformer, Shunts | MATL (120s Picture Butte - Montana) | Annual maintenance routine - in conjunction with south bound and 1201L outage. The following maintenance items will be completed; Rising Edge -RTU outage as needed to complete ORION change out and complete alarm checks to ACC and timer modification as needed& station will be out -PS1; diverter, filters, exciter tank conservator bladder -switch maintenance -AC station service outage for testing ATS | 240 kV, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2021-10-18 09:00 | 2021-10-30 17:00 | N | Y | maintenance | Line | MATL (120s Picture Butte - Montana) |  | 240 kV, Limits ATC, Pre-Condition
EPCOR | 72LS24 (EP 803s Lambton - Strathcona) | 2021-10-18 09:30 | 2021-11-08 16:00 | N | N | Line Maintenance | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 42s 70 (42s Sarcee) | 2021-10-18 09:30 | 2021-10-19 16:30 | N | Y | migrate and commission | Circuit Breaker | 42s 70 (42s Sarcee) | Migrate and commission all 42s70 (1052) at 42s Sarcee associated protections, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Project PM: Golaleh Rahimi Issue to: Jesse Soonias Contact #: 403-606-8152 | 240 kV, Contingency Requires Mitigation
ATCO | 7L75 (ATC 793s West Peace River - 800s Friedenstal) | 2021-10-18 10:00 | 2021-10-20 12:00 | N | Y | 701 breaker maintenance | Line |  | 800S Friedenstal Breaker 701 Maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 67s T2 (67s Stirling) | 2021-10-18 10:00 | 2021-10-19 18:00 | N | N | investigate and replace failing LTC controller | Transformer | 67s T2 (67s Stirling) |  | Pre-Condition
ALTALINK | 520s 552 (520s Benett) | 2021-10-18 10:05 | 2021-10-25 17:30 | N | Y | 520s552 replace "A phase" pole, & corona ring bent replacement | Circuit Breaker | 520s 552 (520s Benett) |  | 500 kV, Pre-Condition
ALTALINK | 385s T3 (385s Spring Coulee) | 2021-10-18 10:30 | 2021-10-23 17:30 | N | N | 69kV/25kV bushing replacement, fix leaks, install fall arrest post | Transformer | 385s T3 (385s Spring Coulee) |  | For Information Only
ALTALINK | 89s Ellerslie 240kV Bus 1, 89s T1 (89s Ellerslie) | 2021-10-18 11:00 | 2021-10-21 18:00 | N | Y | replace 240kV PTs 89s80 & 89s90 | Bus, Transformer | 289s 240kV Bus 1 (289s Saunders Lake), 89s T1 (89s Ellerslie) |  | 240 kV, 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 6L21 (Youngstown Express - 6L09 tap), 6L09 (767s Oyen - 6L21 tap), 6L09 (772s Youngstown - 6L21 tap) | 2021-10-18 12:00 | 2021-10-18 15:00 | N | N | bypass inoperable switch 6L09D6 | Line |  | GOI to bypass inoperable switch 6L09D6, and adjust 6L09D7 so we can sectionalize 6L09 for upcoming work. Date agreed upon with Enbridge Pipelines, Youngstown to be back fed on the 25kv. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2021-10-18 12:00 | 2021-11-01 11:00 | N | Y | replace crossarms and replace poles | Line |  | Replace cross arms and replace poles | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 42s C1 (42s Sarcee) | 2021-10-18 13:00 | 2021-10-18 17:00 | N | N | PRC005 compliant relay maintenance and trip path verifications | Shunts |  | Techs will require 42sC1 Cap bank OOS to complete PRC005 compliant relay maintenance and trip path verifications. | Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale) | 2021-10-18 16:00 | 2021-10-19 18:00 | N | N | cross arm change | Line |  | Sample Climbing inspection and cross arm change. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
MONTANA, ENBRIDGE | MATL (120s Picture Butte - Montana), Hay Lake North Series Capacitor | 2021-10-18 18:00 | 2021-10-23 18:00 | N | Y | annual maintenance routine | Line, Shunts | MATL (120s Picture Butte - Montana) | Annual maintenance routine - in conjunction with south bound and 1201L outage. The following maintenance items will be completed; Rising Edge -RTU outage as needed to complete ORION change out and complete alarm checks to ACC and timer modification as needed& station will be out -PS1; diverter, filters, exciter tank conservator bladder -switch maintenance -Relay PMs for site& operating lockouts& -AC station service outage for testing ATS KLINE -line maintenance | 240 kV, Pre-Condition
ALTALINK | 39s 1052 (39s Bickerdike) | 2021-10-19 07:00 | 2021-12-13 18:00 | N | Y | addition of new breaker 39s1152 and associated equipmen (P2032) | Circuit Breaker | P2032 | GOI to allow for the addition of new breaker 39s1152 and associated equipment. New 39s1152 is Being installed between 39s11A, and 39s31, Part of 240kV Expansion cascade project. and Add new 39s973 MOD which will remain normal open until the 973L is relocated to this diameter.Add New 39s56 switch (P2032) | 240 kV, Contingency Requires Mitigation
ALTALINK | 284S Nose Creek | 2021-10-19 08:00 | 2021-10-20 16:00 | N | N | switchgear maintenance | Station |  | Customer switchgear maintenance | For Information Only
ENMAX | 6.1TR (ENMAX 6) | 2021-10-19 08:00 | 2021-10-20 16:00 | N | N | tapchanger inspection, 6.1TR, TC replace PRD junction box | Transformer | 6.1TR (ENMAX 6) |  | For Information Only
ALTALINK | 42s C3 (42s Sarcee), 42s 76 (42s Sarcee) | 2021-10-19 09:15 | 2021-10-21 17:00 | N | Y | complete PRC005 compliant relay maintenance and trip path verifications | Shunts, Circuit Breaker |  | Techs will require 42sC3 Cap bank OOS to complete PRC005 compliant relay maintenance and trip path verifications. | 240 kV, Pre-Condition
ALTALINK | 508s T1 (508s Lakesend), 508s 2 (508s Lakesend) | 2021-10-20 07:30 | 2021-10-20 17:30 | N | N | T1 leak, maintain, doble bird cover, maintain 508s696 | Transformer, Switch | 508s T1 (508s Lakesend) |  | For Information Only
ATCO | 6L09 (772s Youngstown - 776s Richdale) | 2021-10-20 08:00 | 2021-10-22 16:00 | N | N | pole/crossarm replacement 6L09 | Line | 6L09 (772s Youngstown - 776s Richdale) | pole/crossarm replacement 6L09 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 77s 26 (77s Sagitawah) | 2021-10-20 09:30 | 2021-10-21 17:30 | N | Y | urgent replace failed grading capacitors and do an internal inspection on the phase's contacts that had the cap failure | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L73 (800s Friedenstal - 829s Boucher Creek), 800s 702 (800s Friedenstal) | 2021-10-20 12:00 | 2021-10-22 17:00 | N | Y | 800S Friedenstal breaker 702 maintenance | Line, Circuit Breaker |  | 800S Friedenstal Breaker 702 Maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2021-10-21 07:00 | 2021-10-21 18:00 | N | Y | maintenance on structure #913L124 | Line | 913L (69s North Barrhead - 338s Cherhill) | Crews performing mtce. on Structure #913L124 | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 13L (65s High River - 392s Black Diamond) | 2021-10-21 07:00 | 2021-10-21 18:00 | N | N | urgent repair on 13L - cross arm replacement | Line |  | GOI Required for Completion of Urgent Repair on 13L. Notification # 10366905  Cross Arm Replacement. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 5R ATP1382 (A.T. Plastics 5R), ATPAB3 (A.T. Plastics 5Rs) | 2021-10-21 07:00 | 2021-10-22 17:00 | N | N | AT Plastics CT repair and relay maintenance | Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 135s T1 (135s Conrad) | 2021-10-21 07:15 | 2021-10-21 17:45 | N | N | install new CT secondary cables from T1 secondary CTs to the new control building for undervoltage protection LOP | Transformer |  | Install new CT secondary cables from T1 secondary CTs to the new control building for undervoltage protection LOP | For Information Only
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank) | 2021-10-21 08:00 | 2021-11-05 18:00 | N | N | line protection upgrade | Line |  | 1. 72kV Line 29PL6-3 outage for Line A/B Protection Upgrades 2. Correct leaning 29PL6-3 Powerline structure deficiency near 30EDD1. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 225L (225s Magrath - 385s Spring Coulee) | 2021-10-21 08:15 | 2021-11-16 17:45 | N | N | rebuilding a portion of 225L from structure 282 to structure 400 | Line | 225L (225s Magrath - 385s Spring Coulee) | Scope of work includes rebuilding a portion of 225L from structure 282 to structure 400 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ATCO | 930s Syn Condenser (930s Arcenciel) | 2021-10-21 14:53 | 2021-10-27 12:00 | N | Y | forced outage | Shunts |  |  | Pre-Condition
ENMAX | 5.8TR (ENMAX 5) | 2021-10-22 08:00 | 2021-11-05 16:00 | N | N | relay replacement. 5.8TR ground shield ground rerun | Transformer | 5.8TR (ENMAX 5) |  | For Information Only, Pre-Condition
SUNCOR | 29EDD-71 | 2021-10-22 08:00 | 2021-10-23 18:00 | N | N | breaker functional test | Terminal Equipment |  | 29EDD71; BREAKER FUNCTIONAL TEST REG 5y_A 29-752-4613;29-752-4614;29-752-4621;29-752-4622;29-752-4623 29-752-4624; 29-752-4631; 29-752-4632; 29-752-4633; 29-752-4634 29-752-4641;29-752-4642;29-752-4644 29-752-4651;29-752-4652;29-752-4654 | Pre-Condition
ALTALINK | 795L (121s Brooks - 421s Hays) | 2021-10-23 07:00 | 2021-10-28 18:00 | N | N | bird fight diverter installation | Line | 795L (121s Brooks - 421s Hays) | GOI required for Bird Flight Diverter Installation on 795L Str. 40-41, 51-56, 62-65, 75-76, 84-86, 89-95, 161, 162, 165-175, 280, 281, 338, 339. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.84L (ENMAX 2 - ENMAX 8) | 2021-10-23 08:00 | 2021-10-23 16:00 | N | N | cathodic protection and manhole inspections | Line |  | Cathodic protection and manhole inspections | For Information Only
SSLP | HYS1 Hays | 2021-10-23 08:00 | 2021-11-06 16:00 | N | N | P1839 Fortis 421S Hays 23 MW DG PV. ISD June 23, 2021. DG ISD Oct 30, 2021 | Unit
BHE Canada | 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte) | 2021-10-23 18:00 | 2021-10-30 17:00 | N | Y | annual maintenance routine | Transformer, Shunts | MATL (120s Picture Butte - Montana) | Annual maintenance routine - in conjunction with south bound and 1201L outage. The following maintenance items will be completed; Rising Edge -RTU outage as needed to complete ORION change out and complete alarm checks to ACC and timer modification as needed& station will be out -PS1; diverter, filters, exciter tank conservator bladder -switch maintenance -Relay PMs for site& operating lockouts& -AC station service outage for testing ATS | 240 kV, Limits ATC, Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2021-10-24 08:00 | 2021-10-25 16:00 | N | N | cable trench replacement | Transformer |  |  | For Information Only
ENMAX | 2.83L (ENMAX 5 - 2.83L tap), 5.9TR (ENMAX 5), 5.10TR (ENMAX 5), 5B138-2.83 (ENMAX 5) | 2021-10-24 08:00 | 2021-10-24 18:00 | N | N | fall substation washing, maintenance and testing | Line, Transformer, Circuit Breaker |  | Fall Substation Washing. 5.10 TC Replace PRD Junction Box. Check Reversing Switch 5.10TR. 5.10TR MD whips reset. 5MD138-5.9TR east phase whip will not set. Relays, Lockout Testing 86T10, 86T9, 86Z33 2.83L. 5.9TR. 5.10TR. 5PT138-Z33 | Pre-Condition
ATCO | 809s 903 (809s Louise Creek) | 2021-10-24 17:01 | 2021-10-25 07:59 | N | Y | Louise Creek rebuild project | Circuit Breaker |  |  | For Information Only
EPCOR | 987s SST2 (987s Clover Bar) | 2021-10-25 07:00 | 2021-10-29 17:00 | N | N | clover Bar SDS2L LCR - SST2 work | Transformer |  | clover Bar SDS2L LCR - SST2 Outage | For Information Only
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook) | 2021-10-25 07:00 | 2021-11-03 10:52 | N | Y | spire #6 and # 7 repair | Line |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2021-10-25 08:00 | 2021-11-01 12:00 | N | N | changing X Arms and installing stubs | Line | 7L12 (834s Wesley Creek - 7LA12 tap) | Changing X Arms and installing stubs | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2021-10-25 08:00 | 2021-10-30 17:00 | N | Y | change arms & insulators | Line |  | change arms & insulators | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
CMH | MH-60L (MH69s5 North East Cresent Heights - MHS7 Brier Park) | 2021-10-25 08:00 | 2021-10-27 08:00 | N | N | repairs due to a recent grass fire | Line |  |  | For Information Only
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21), 21B138-21.CAP (ENMAX 21), 21.2TR (ENMAX 21) | 2021-10-25 08:00 | 2021-10-25 16:00 | N | Y | fall substation washing | Line, Circuit Breaker, Transformer |  |  | For Information Only, Pre-Condition
ATCO | 700s 706C (700s Bonnyville), 700s 706 (700s Bonnyville) | 2021-10-25 08:00 | 2021-10-27 16:00 | N | N | replace 706CT | Shunts, Circuit Breaker |  | Replace 706CT | Pre-Condition
ALTALINK | 58L (32s Barrier - 245s Seebe), 245s 58X (245s Seebe) | 2021-10-25 08:00 | 2021-10-26 17:00 | N | N | work on the PLC | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 11.2TR (ENMAX 11) | 2021-10-25 08:00 | 2021-10-28 16:00 | N | N | cable trench replacement | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 5s T2 (5s East Calgary), 5s 240kV Bus 1 (5s East Calgary), 138kV Bus Z31 (ENMAX 2) | 2021-10-25 09:00 | 2021-10-27 13:50 | N | Y | change conservator bladder | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s Heathfield | 2021-10-25 09:00 | 2021-10-29 17:30 | N | Y | 2029S 500SST1/T2 - breaker thermal window install | Station |  | Breaker thermal window installs in LV1 & LV2. One LV will be performed at a time, then the other switched out. 500 kV breakers on transformer primary will be opened for a few moments while opening 501VRA & 502VRA. | For Information Only
ALTALINK | 42s 80 (42s Sarcee) | 2021-10-25 09:30 | 2021-10-27 12:30 | N | N | migrate and commission 42s80 (1252) | Circuit Breaker | 42s 80 (42s Sarcee) | Migrate and commission all 42s80 (1252) at 42s Sarcee associated protections, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Install and commission new SCADA meter for 42S80 metering. Project PM: Golaleh Rahimi Issue to: Jesse Soonias Contact #: 403-606-8152 | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2021-10-25 09:45 | 2021-11-03 17:45 | N | Y | install/commission new line protections | Line | Build new T-tap into new 991s substation (Little Bow). Install/commission new line protections |  | 240 kV, Pre-Condition
ATCO | 7L22 (790s Poplar Hill - 7L88 tap), 790s 702 (790s Poplar Hill) | 2021-10-25 10:00 | 2021-10-26 16:00 | N | Y | breaker maintenance | Line, Circuit Breaker |  | 790S 702 maintenance, 7L22 open ended | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 919L (77s Sagitawah - 310p Sundance) | 2021-10-25 11:00 | 2021-10-29 15:00 | N | Y | replacement of 77s919x | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
BLACKSPRING | 485S Black Springs | 2021-10-25 11:00 | 2021-10-25 12:00 | N | N | validate the reactive power commands | Station |  | To validate the reactive power commands issued by Master Control (PPC) to the DSTATCOM installed at circuits T1 and T2 | For Information Only
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia) | 2021-10-25 12:00 | 2021-10-27 18:00 | N | Y | component replacements and fire mitigation | Line | Component replacements and fire mitigation on 908L Str's Range 200-232 |  | 240 kV, For Information Only, Affects Cranking Path
ALTALINK | 89s 1252 (89s Ellerslie) | 2021-10-25 12:00 | 2021-11-05 17:30 | N | Y | replace breaker fail relay | Circuit Breaker | 89s 1252 (89s Ellerslie) | replace 89s1252 breaker fail relay | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 89s 1352 (89s Ellerslie), 89s 1452 (89s Ellerslie) | 2021-10-25 13:00 | 2021-10-28 18:00 | N | N | replace 240 kV PTs 89s80 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
AESO-SC | OATI | 2021-10-25 20:00 | 2021-10-25 21:00 | N | N | upgrading one of the Storage Area Networks (SAN) | SCInternal |  |  | For Information Only
ALTALINK | 426L (63s Red Deer - 194s South Red Deer) | 2021-10-26 07:00 | 2021-10-26 18:00 | N | N | maintenance | Line | 426L (63s Red Deer - 194s South Red Deer) | Scope of work includes maintenance on structure 13. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 151s 765W (151s Strathmore) | 2021-10-26 07:30 | 2021-10-26 12:30 | N | Y | install and commission relays for RAS179 on 765L | Line, Circuit Breaker |  | Install and commission relays for RAS179 on 765L. For new Fortis DER installs at 151s & 428s | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 135s T2 (135s Conrad) | 2021-10-26 07:30 | 2021-11-23 11:00 | N | N | cable installation from T2 secondary CTs to the new control building and change to feeder protection settings for the 135s4670 breaker | Transformer |  | Install new CT secondary cables from T2 secondary CTs to the new control building for undervoltage protection LOP. 2nd scope Change feeder protection settings for the 135s4670 breaker. Commission transfer trip inputs from other protections. | For Information Only
ATCO | 740s 144kV Main Bus (740s H.R.Milner), 740s 703T (740s H.R.Milner) | 2021-10-26 08:00 | 2021-11-09 09:00 | N | N | 740S 700BS1 outage | Bus, Transformer |  | 740S HR Milner Bus 1-2 Upgrade 740S 700BS1 outage Maxim Power 144kV remains in service | Pre-Condition
REDDEER | 194s T2 (194s South Red Deer) | 2021-10-26 08:00 | 2021-11-01 09:00 | N | N | relay testing and maintenance | Transformer | 194s T1 (194s South Red Deer) | P&C relay testing and maintenance | For Information Only
ATCO | 757s 709 (757s Battle River) | 2021-10-26 08:00 | 2021-10-26 17:00 | N | N | PRC005 work | Circuit Breaker |  | PRC005 work on 709 Breaker | For Information Only
ATCO | 757s 707 (757s Battle River) | 2021-10-26 08:00 | 2021-10-26 17:00 | N | N | PRC005 work | Circuit Breaker |  | PRC005 work on 707 Breaker | For Information Only
ATCO | 757s 706 (757s Battle River) | 2021-10-26 08:00 | 2021-10-26 17:00 | N | N | PRC005 work | Circuit Breaker |  | PRC005 work on 706 Breaker | For Information Only
ALTALINK | 452L (367s Harry Smith - 434s Stony Plain), 434s T3 (434s East Stony Plain), 434s 452 (434s Stony Plain) | 2021-10-26 08:00 | 2021-10-28 18:00 | N | N | replace 434s2, replace 434s1 existing grounding mat, T3 pipe bus dampening repairs | Line, Transformer, Circuit Breaker | 434s T3 (434s East Stony Plain), 452L (367s Harry Smith - 434s Stony Plain), 434s 7 (434s Stony Plain) | Replace 434s2, Replace 434s1 existing grounding mat, T3 pipe bus dampening repairs | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 17s 85 (17s Benalto), 17s T2 (17s Benalto) | 2021-10-26 08:30 | 2021-10-26 17:30 | N | N | breaker maintenance | Circuit Breaker, Transformer | 17s T2 (17s Benalto) | Replace 6 grading capacitors on 17s85 breaker like for like. Other maintenance work on the breaker as required, | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 421s C1 (421s Hays) | 2021-10-26 08:30 | 2021-10-26 16:30 | N | N | weed spraying on C1 and tighten risers | Shunts | 421s C1 (421s Hays) |  | Pre-Condition
CapitalPower | 615s DVAR1 (615s Halkirk) | 2021-10-26 09:00 | 2021-10-29 17:00 | N | N | work on the DSTAT | Shunts |  |  | Pre-Condition
VISIONREQ | 354S Summerview | 2021-10-26 09:00 | 2021-10-26 12:00 | N | N | WindCharger software updates | Station |  |  | Restricts Generation
AESO-SC | OATI | 2021-10-26 18:00 | 2021-10-26 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 853L (504s Queenstown - 853AL tap) | 2021-10-27 07:00 | 2021-10-30 18:00 | N | Y | bird flight diverter installation on 853L structures 282-330 | Line |  | GOI required for Bird Flight Diverter Installation on 853L Structures 282-330 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 71s T2 (71s Lamoureux) | 2021-10-27 07:30 | 2021-10-27 18:00 | N | Y | urgent fix tap changer runaway on T2 | Transformer |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 29EDD-71 Edd71Sub | 2021-10-27 08:00 | 2021-11-04 18:00 | N | N | breaker 10 year maintenance and test | Station |  | 29EDD71;29-752-4631 MAINT & TEST;PM 10y 29EDD71;29-752-4634 MAINT & TEST;PM 10y 29EDD71;29-752-4644 MAINT & TEST;PM 10y 29EDD71;29-752-4654 MAINT & TEST;PM 10y | Pre-Condition
ALTALINK | 65s 727N (65s High River), 727L (65s High River - 727AL tap) | 2021-10-27 08:30 | 2021-10-27 16:30 | N | N | 65s High River grading cap (65s727N) | Circuit Breaker, Line |  |  | Over/Under Voltage, Pre-Condition
ATCO | 811s 709 (811s Clairmont Lake), 7L39 (811s Clairmont Lake - 7L39 tap) | 2021-10-27 09:00 | 2021-10-27 17:00 | N | Y | 811S 709 partial maintenance | Circuit Breaker, Line |  | 811S 709 partial maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 749s 701T (749s Flyingshot Lake) | 2021-10-27 09:00 | 2021-10-28 17:00 | N | N | 701T leak investigate and repair | Transformer |  | 701T Leak Investigate/Repair transfer load to 749S 702T | For Information Only, Pre-Condition
ALTALINK | 421s 795N (421s Hays), 795L (121s Brooks - 421s Hays) | 2021-10-27 09:15 | 2021-10-28 15:45 | N | N | 1st trip and maintenance - PRC5 | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | 1.7TR (ENMAX 1) | 2021-10-28 08:00 | 2021-10-28 16:00 | N | N | oil sampling, HV bushing, TC | Transformer |  |  | For Information Only
ATCO | 826s 503R (826s Marguerite Lake), 826s 504R (826s Marguerite Lake) | 2021-10-28 09:00 | 2021-10-28 14:00 | N | N | emergency: repair hotspot found on 826S 504A during heat scanning | Shunts | 826s 504R (826s Marguerite Lake) | Repair hotspot found on 826S 504A during heat scanning. 826S 503R and 826S 504R will be unavailable for the duration. | Pre-Condition
ALTALINK | 68s T2 (68s Willesden Green), 68s 552 (68s Amoco Willesden Green) | 2021-10-28 09:30 | 2021-11-01 17:30 | N | Y | tie in new CT circuit for ne A87 protection, modify transformer protection relays setting and testing | Transformer, Circuit Breaker |  | Tie in new CT circuit for ne A87/DER protection. Modify Transformer protection relays setting and Test trip to 68s3103 Modify 370s552 Breaker Fail Protection and Test trip to 68s3103 | 240 kV, For Information Only, Pre-Condition
ENMAX | 6.80L (ENMAX 6 - ENMAX 35), 6B138-6.80 (ENMAX 6) | 2021-10-29 08:00 | 2021-10-31 12:00 | N | N | 6 sub cable trench replacement | Line, Circuit Breaker |  | 6 sub cable trench replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | 615S Halkirk | 2021-10-29 13:00 | 2021-10-29 15:00 | N | N | communications only outage to work on RTAC program changes | Station |  | Communication outage only due to work on RTAC program changes. AESO will lose Halkirk telemetry data intermittently and visibility to MW and MVar. There is no impact to generation, but the site will not be able to respond to the ramp management plan. Worker on site to respond to curtailments if dispatched verbally. Minimum Load Requirement: N/A Available Capacity: 150 MW MVAR: N/A AS Availability: N/A Comments: MVAR will be impacted by DSTACOM work happening at the same time | For Information Only
ATCO | 757s 704 (757s Battle River) | 2021-10-29 14:00 | 2021-11-23 15:30 | N | Y | 704T maintenance work and PRC005 work on 704 breaker | Circuit Breaker | 757s 704 (757s Battle River) | 704T Maintenance work for Heartland generation. PRC005 work on 704 Breaker | Restricts Generation
NEXENI | I-PCES02S Balzac | 2021-10-29 18:00 | 2021-10-29 23:59 | N | N | router replacement | Station |  | Balzac Power station will have to replace a router. This will result in the ADAMS being down for 5-10 minutes while the new router reboots. Currently, the plan is for the reboot to occur at 18:00(HE 19) October 29th. The control room operator will liaise with the system controller to ensure communication is not compromised during the outage | For Information Only
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2021-10-30 10:00 | 2021-11-15 16:00 | N | N | 14 sub fencing replacement | Shunts |  |  | For Information Only, Pre-Condition
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2021-10-31 08:00 | 2021-11-02 16:00 | N | N | 8sub RTU commissioning | Line |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon) | 2021-10-31 08:00 | 2021-10-31 16:00 | N | N | investigate high corona, possible internal broken strands on the conductor | Line |  | Investigate high Corona, possibly some internal broken strands on the conductor | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2021-10-31 12:00 | 2021-11-05 12:00 | N | N | 6 sub cable trench replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5B138-5BT7 (ENMAX 5) | 2021-10-31 23:00 | 2021-11-01 01:00 | N | N | relay replacement. 5.8TR, commissioning checks | Circuit Breaker |  |  | For Information Only
EPCOR | VHBB2 (Rossdale) | 2021-11-01 07:00 | 2021-11-25 18:59 | N | N | breaker outage | Circuit Breaker |  |  | Pre-Condition
EPCOR | 1164L (816s Petrolia - EPCOR Riverview), RW2401 (EPCOR Riverview), RW2402 (EPCOR Riverview) | 2021-11-01 07:00 | 2021-11-04 17:00 | N | Y | RWDS2 / RWDS3 / RWDS11 adjustments | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39) | 2021-11-01 08:00 | 2021-11-06 10:14 | N | N | breaker refurbishments | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | STR1 Strathmore Solar DER, STR2 Strathmore Solar DER | 2021-11-01 08:00 | 2022-02-22 16:00 | N | N | P2029 FortisAlberta Strathmore 151S DER Solar 1, 18 MW. ISD Feb 15, 2022, P2030 FortisAlberta Strathmore 151S DER Solar 2, 23 MW. ISD Feb 15, 2022 | Unit
ALTALINK | 763L (158s Vauxhall - 257s Hull) | 2021-11-01 09:00 | 2021-11-08 18:00 | N | N | components 763L Str's Range (423-515) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 2075s 900SST1 (2075s Newell), 2075s 900SST2 (2075s Newell) | 2021-11-01 09:00 | 2021-11-05 17:30 | N | Y | breaker thermal window installs in low voltage equipment | Transformer |  | Breaker thermal window installs in LV1 & LV2. As Each Station service is removed-from and returned-to service the 240Kv breakers will be opened temporarily to allow for isolating the low voltage devices. (2075S 920 & 2075S 921 for 500SST1) & (2075S 904 & 2075S 905 for 500SST2) One LV will be performed at a time, then the other switched out. | 240 kV, For Information Only, Pre-Condition
ATCO | 757s 702 (757s Battle River), 757s 702B (757s Battle River) | 2021-11-01 09:00 | 2021-11-05 15:30 | N | Y | PRC005 work on 702 breaker | Circuit Breaker, Switch |  | PRC005 work on 702 Breaker Unit #4 shut down from October 29th to Nov 19 | Pre-Condition
ATCO | 834s 501 (834s Wesley Creek), 834s 502 (834s Wesley Creek), 834s 503 (834s Wesley Creek), 834s 502R (834s Wesley Creek) | 2021-11-01 09:00 | 2021-11-12 16:00 | N | N | install oil containment around 902T | Circuit Breaker, Shunts |  | Install and oil containment around 902T. 502R Unavailable Need an outage to move 25KV cables around. Station service will need to be run from the alternate source. | Pre-Condition
ALTALINK | 17s 138kV Bus 4 (17s Benalto), 17s T2 (17s Benalto), 848L (17s Benalto - 848AL tap) | 2021-11-01 09:30 | 2021-11-20 18:00 | N | Y | replace 138 kV bus and line protection | Bus, Transformer, Line |  | Replace 138kv Bus 4 bus prots, Replace breaker fails on s92, s85, s848X Replace s85 sync check, Replace line protections on 848L, Tie in new 138B3 'B' CT cont, and Tie in new 138B3 'B' CT cont | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 194s T1 (194s South Red Deer) | 2021-11-01 10:00 | 2021-11-08 09:00 | N | N | relay testing and maintenance | Transformer | 194s T2 (194s South Red Deer) | P&C relay testing and maintenance | For Information Only
ALTALINK | 905L (19s Wabamun - 37s North Calder), 37s 76 (37s North Calder), 37s 82 (37s North Calder) | 2021-11-01 11:00 | 2021-11-10 17:30 | N | Y | replace 37s77 & 37s79 switches, salvage 37s74 and maintenance on 37s76 including first trip testing | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 89s T2 (89s Ellerslie), 89s Ellerslie 240kV Bus 2, 89s 1652 (89s Ellerslie), 89s 852 (89s Ellerslie), 89s 452 (89s Ellerslie) | 2021-11-01 11:00 | 2021-11-04 18:00 | N | Y | replace 240kV PTs 89s91, maintenance on 89s8, 89s16, 89s32, trip testing from replacement 89s1252 breaker fail relay | Transformer, Bus, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 786s 701T (786s High Level), 786s 701TCS (786s High Level), 786s SVC (786s High Level), 7L133 (786s High Level - 828s Sulphur Point) | 2021-11-01 11:01 | 2021-11-05 17:30 | N | N | transformer major testing, CCT SW S&C complete test and maintenance | Transformer, Switch, Shunts, Line | 786s 701T (786s High Level) | 786S 701T TRANSFORMER CLASS2 MAJOR TESTING 786S 701TCS CCT_SW S&C COMPLETE TEST & MAINTAIN Will lose 700PT2 in the isolation which limits distance relays on 7L59 to overcurrent Close 7L59D5 to tie 7L76 & 7L59, Relay changes required at 789S Keg River | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 447s T1 (447s Enchant) | 2021-11-01 11:30 | 2021-11-03 17:30 | N | N | bushing replacement | Transformer | 447s T1 (447s Enchant) |  | For Information Only
BHE Canada | Hay Lake North Series Capacitor | 2021-11-01 12:00 | 2021-11-04 18:00 | N | Y | series capacitors issues at Hay Lake | Shunts |  |  | 240 kV, Limits ATC
ALTALINK, EPCOR | 908L (38s East Edmonton - 89s Ellerslie), 52s T2 (52s East Industrial) | 2021-11-01 12:00 | 2021-11-04 18:00 | N | Y | component replacements and fire mitigation on Str's range 233-298 | Line, Transformer |  |  | 240 kV, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 434s T1 (434s East Stony Plain) | 2021-11-01 12:00 | 2021-11-02 16:00 | N | N | install bird cover ups on T1 25 kV bushings and 36L feeder conductor terminations | Transformer | 434s T1 (434s East Stony Plain) |  | For Information Only
ALTALINK | 316s T1 (316s West Crossfield) | 2021-11-01 12:00 | 2021-11-04 17:30 | N | N | doble and maintenance | Transformer |  |  | For Information Only
ALTALINK | 245s T2 (245s Seebe) | 2021-11-01 12:30 | 2021-11-10 13:00 | N | N | TX protection replacements | Transformer |  |  | For Information Only
VISIONREQ | 354S Summerview | 2021-11-02 08:00 | 2021-11-04 18:00 | N | N | wind charger maintenance | Station |  |  | Restricts Generation
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2021-11-02 08:00 | 2021-11-11 17:00 | N | Y | urgent damper replacement | Line |  |  | 240 kV, Pre-Condition
SUNCOR | 635EDD-1000 PT-1001 (635EDD-1000), 635PL9-1001 (2005s Secord - 635EDD-1000) | 2021-11-02 08:00 | 2021-11-16 17:00 | N | Y | line structure change for line lift; line & transformer maintenance and protection work | Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 37.2TR (ENMAX 37) | 2021-11-02 08:00 | 2021-11-02 16:00 | N | N | oil sampling, replace LTC mech heaters | Transformer |  |  | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2021-11-02 08:00 | 2021-11-03 16:00 | N | N | tripping hazard, oil sampling | Transformer |  |  | For Information Only
ALTALINK | 142s 3 (142s Magcan), 142s C1 (142s Magcan) | 2021-11-02 09:00 | 2021-11-02 14:30 | N | N | replace dashpot, oil top up | Circuit Breaker, Shunts | 142s C1 (142s Magcan) |  | For Information Only, Pre-Condition
ATCO | 749s 702 (749s Flyingshot Lake) | 2021-11-02 09:00 | 2021-11-02 16:30 | N | N | testing | Circuit Breaker |  | 749S 702 testing | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2021-11-02 11:00 | 2021-11-02 17:00 | N | N | high load move | Line |  | High Load move | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2021-11-03 08:00 | 2021-11-03 16:00 | N | N | 5sub TRV Project - investigate control wiring in circuit breaker | Line |  | 5sub TRV Project. Investigate control wiring in circuit breaker. | For Information Only, Pre-Condition
ATCO | 9L40 (732s Mitsue - 809s Louise Creek) | 2021-11-03 08:00 | 2021-11-30 17:00 | N | Y | wiring for 903/904BF relays | Line |  | Louise Creek rebuild project. Wiring for 903/904BF relays. CT ratio changes | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 8.5TR (ENMAX 8) | 2021-11-03 08:00 | 2021-11-05 16:00 | N | N | 8sub RTU commissioning | Transformer |  |  | For Information Only
ALTALINK | 385s T1 (385s Spring Coulee), 385s T2 (385s Spring Coulee) | 2021-11-03 08:30 | 2021-11-03 17:30 | N | N | wire CT secondary contributions to new 69 kV U/V protections | Transformer |  | Wire CT secondary contributions to new 69kV U/V protections | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2021-11-03 23:00 | 2021-11-04 03:00 | N | N | maintenance | Switch |  | unit outage request by TransAlta | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2021-11-04 03:00 | 2021-11-04 07:00 | N | N | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 993s T2 (993s Abee) | 2021-11-04 07:00 | 2021-11-04 19:30 | N | N | Enbridge to service switches 410-BUS-2-IS and 70-SWGR-1-IS and hang grounds at 410-BUS-2-IS and 70-SWGR-1- IS | Transformer |  | Enbridge to service switches 410-BUS-2-IS and 70-SWGR-1-IS. Enbridge to hang grounds at 410-BUS-2-IS and 70-SWGR-1- IS. Enbridge request to hang their own tag as well. | For Information Only
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge), 865L (38s East Edmonton - 216s Knightsbridge), 216S Knightsbridge, 317S Baseline | 2021-11-04 07:00 | 2021-11-05 23:00 | N | N | insulator replacement, switch maintenance, SCADA upgrade | Line, Station |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 89s 1952 (89s Ellerslie) | 2021-11-04 08:00 | 2021-11-04 13:00 | N | Y | trip testing from replacement 89s1252 breaker fail relay | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 162.3TR (162s Beddington) | 2021-11-04 08:00 | 2021-11-04 16:00 | N | N | replace counter on 162.3TR tap changer, oil sampling, filmax LTC oil filtration | Transformer |  | Replace Counter on 162.3TR Tap Changer. Oil Sampling MT, TC. Filmax LTC Oil Filtration Maintenance. LV load to transfer Nov 4th approx. 1:30 am, return Nov 5th 1:30am | For Information Only
ALTALINK | 245s 10 (245s Seebe) | 2021-11-04 11:00 | 2021-11-04 14:29 | N | N | functional trip test (245s3E); re T2 protection replacements | Circuit Breaker | 245s 10 (245s Seebe) |  | For Information Only
NWE | Marias Shunt Capacitor | 2021-11-04 12:30 | 2021-11-30 17:00 | N | Y | bank #2 forced outage | Shunts |  |  | For Information Only
ALTALINK | 89s 2252 (89s Ellerslie) | 2021-11-04 13:00 | 2021-11-04 17:30 | N | Y | trip testing from replacement 89s1252 breaker fail relay | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2021-11-04 14:30 | 2021-11-04 17:00 | N | Y | functional trip test (245s3E); re T2 protection replacements | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 657s T2 (657s Summerside) | 2021-11-05 07:00 | 2021-11-26 17:00 | N | Y | SUBT23 cell install | Transformer | Tx2 isolation required for SUBT23 cell install as part of Southeast Expansion Project |  | 240 kV, For Information Only
EPCOR | 1139L (367s Harry Smith - EPCOR Riverview), RW2403 (EPCOR Riverview), RW2405 (EPCOR Riverview) | 2021-11-05 07:00 | 2021-11-06 17:00 | N | Y | RWDS12 adjustment | Line, Circuit Breaker |  | RWDS12 adjustment | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 3L (245s Seebe - 3AL Tap) | 2021-11-05 08:00 | 2021-11-05 10:29 | N | N | functional trip test | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 6.80L (ENMAX 6 - ENMAX 35) | 2021-11-05 08:00 | 2021-11-07 16:00 | N | N | cable trench replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.4TR (162s Beddington) | 2021-11-05 08:00 | 2021-11-05 16:00 | N | N | 162.4TR corrective | Transformer | 162.4TR Corrective -162MD138-162.4TR north phase not fully closed. LV load transfer Nov. 5th approximately 1:30am return to normal Nov 6th approx. 1:30am. |  | For Information Only
ENMAX | 3.4TR (ENMAX 3) | 2021-11-05 08:00 | 2021-11-05 16:00 | N | N | LTC cabinet - heater fails | Transformer |  |  | For Information Only
ALTALINK | 245s 58X (245s Seebe), 58L (32s Barrier - 245s Seebe) | 2021-11-05 10:30 | 2021-11-05 13:00 | N | N | functional trip test and protection replacements | Circuit Breaker, Line | 58L (32s Barrier - 245s Seebe) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 89s 1152 (89s Ellerslie), 946L (38s East Edmonton - 89s Ellerslie) | 2021-11-05 12:00 | 2021-11-05 17:00 | N | Y | trip testing from replacement 89s1252 breaker fail relay | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial) | 2021-11-07 07:00 | 2021-11-09 18:00 | N | N | maintenance on structures 51, 52, 60, 67, 68 and 71. | Line | 797L (268s Whitecourt - 364s Whitecourt industrial) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2021-11-07 08:00 | 2021-11-07 12:00 | N | N | transmission cables - oil sampling | Line | 9.83L (ENMAX 9 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.83L (ENMAX 1 - ENMAX 8), 8B138-4A0 (ENMAX 8), 8B138-3A0 (ENMAX 8) | 2021-11-07 08:00 | 2021-11-09 16:00 | N | N | 8sub RTU commissioning | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s SST2 (987s Clover Bar) | 2021-11-08 02:00 | 2021-11-08 06:00 | N | Y | swap SST back to SST2 | Transformer |  |  | Restricts Generation
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings) | 2021-11-08 07:00 | 2021-11-08 18:00 | N | N | urgent - BF11 and DC filter bank cap inspection | Line |  | Urgent outage required for BF11 and DC Filter Bank Cap Inspection | 500 kV, Pre-Condition
ALTALINK | 749L (899s-7L749D3) - GOI, 749L (899s Edgerton - 7LB749 tap) | 2021-11-08 07:00 | 2021-11-16 18:00 | N | Y | Urgent repair: installation of clamp star assemblies on 749L Str 295B - 472 | Terminal Equipment, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2021-11-08 07:15 | 2021-11-09 17:45 | N | N | urgent replacement of cross arms and insulation on structures 132,133,134 | Line |  | GOI Required for completion of Urgent Repair Scope. Scope entails replacement of Cross arms and insulation on structures 132,133,134. | Pre-Condition, Affects Cranking Path
ATCO | 740s 703T (740s H.R.Milner) | 2021-11-08 08:00 | 2021-11-08 17:00 | N | N | HR Milner upgrade project outage to connect 902S mobile substation to load side of breaker 503 | Transformer |  | HR Milner Upgrade Project Outage to connect 902SMobile Substation to load side of breaker 503 | Pre-Condition
ATCO | 7L139 (707s St. Paul - 7LA139 tap) | 2021-11-08 08:00 | 2021-11-09 17:00 | N | N | change arms insulators | Line | 7L139 (707s St. Paul - 7LA139 tap) | GOI on 7L139 D3 to 707s St Paul Change Arms Insulators | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 702T (802s Michichi Creek) | 2021-11-08 08:00 | 2021-11-11 17:00 | N | N | station upgrade, transformer maintenance, bus upgrade south of 700D2 | Line, Transformer |  | 802S MICHICHI SUBSTATION TCM UPGRADES 702T Transformer PM Bus upgrade south of 700D2 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 869s Seal Lake) | 2021-11-08 08:00 | 2021-11-10 12:00 | N | N | changing X Arms and installing stubs | Line |  | Changing X Arms and installing stubs | Creates Radial Feeds, Firm Load Loss
ENMAX | 10.2TR (ENMAX 10) | 2021-11-08 08:00 | 2021-11-08 16:00 | N | N | LTC low oil | Transformer |  | 10.2TR LTC low oil | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2021-11-08 08:00 | 2021-11-08 16:00 | N | N | clean up punch list items | Transformer |  |  | For Information Only
ENMAX | 9.83L (ENMAX 9 - ENMAX 43), 43B138-9.83 (ENMAX 43) | 2021-11-08 08:00 | 2021-11-08 16:00 | N | N | corrective - heater replacement | Line, Circuit Breaker |  | 43B138-9.83 Corrective - Heater replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1000 635-952-635PT-1001 (635EDD-1000) | 2021-11-08 08:00 | 2021-11-15 17:00 | N | Y | bus-side disconnect repairs main sub 635EDD-1000 | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker) | 2021-11-08 09:30 | 2021-11-10 16:00 | N | Y | line maintenance | Line | 930L (37s North Calder - Poundmaker) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2021-11-08 12:00 | 2021-11-29 17:00 | N | Y | replace crossarms and replace poles | Line |  | Replace crossarms and replace poles | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 602s T2 (602s Cold Creek) | 2021-11-09 07:00 | 2021-11-10 18:00 | N | N | swapping out old motor parts for new ones | Transformer |  |  | For Information Only
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap) | 2021-11-09 07:00 | 2021-11-10 18:00 | N | N | repair structure 63 and 64 and raise post insulators on structure 61. | Line |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 763L (158s Vauxhall - 763AL tap) | 2021-11-09 07:00 | 2021-11-10 18:00 | N | N | components replacements for 763L str's range 310-409 | Line |  |  | Over/Under Voltage, Pre-Condition
ATCO | 837s 701 (837s Mahihkan), 7L157 (837s Mahihkan - 970s Bourque) | 2021-11-09 08:00 | 2021-11-09 17:00 | N | N | emergency repair to 837S 701A | Circuit Breaker, Line | 7L157 (837s Mahihkan - 970s Bourque) | 837S 701A Hot Spot detected on thermal scan, Due to the temperature being above 30 C, criteria dictates we must resolve this issue within a week. Need to operate 837S 701A a few times and see if wiping the contacts reduces the hotspot to an acceptable level. 7L157 Will be Open ended at 837S for approximately an hour. | Over/Under Voltage, Pre-Condition
ALTALINK | 745AL (411s Obed - 745A1L tap) | 2021-11-09 08:00 | 2021-11-09 16:00 | N | N | urgent P5 repair crossarm replacement 745AL47 | Line |  |  | For Information Only
ALTALINK | 511s DC Filter (511s Crossings) | 2021-11-09 08:00 | 2021-11-09 16:30 | N | Y | urgent DC Filter banks inspection | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale) | 2021-11-09 08:00 | 2021-11-20 14:51 | N | N | pole replacement/arm replacement/ inter-phase spacers on 6L09 | Line |  | Pole Replacement/ Arm Replacement/ Interphase spacers on 6L09. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 34B69-21.61 (ENMAX 34), 21.61L (ENMAX 21 - ENMAX 34) | 2021-11-09 08:00 | 2021-11-09 16:00 | N | N | investigate SEL 321 relay. | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 740s 701T (740s H.R.Milner), 740s 702T (740s H.R.Milner), 740s 703T (740s H.R.Milner), 740s 144kV Main Bus (740s H.R.Milner), 740s 144kV Floating Bus (740s H.R.Milner), 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2021-11-09 08:00 | 2021-11-29 17:00 | N | Y | upgrade HR Milner project | Transformer, Bus, Line |  | HR Milner upgrade Project Total 144kV station outage (Maxim Power and GCC 14.6kV OOS) 25kV and 14.4kV will remain in service via 902S Mobile Sub tied to 7L80 703T will be backfed to maintain the 14.4kV supply to CST Coal T1, CST Coal T2 OOS | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 1.7TR (ENMAX 1) | 2021-11-09 08:00 | 2021-11-09 16:00 | N | N | oil sampling, HV bushing, TC | Transformer |  |  | For Information Only
ALTALINK | 634s T1 (634s Shell Raven River) | 2021-11-09 08:15 | 2021-11-09 17:45 | N | N | create open point to disconnect customer from the AltaLink system | Transformer |  | Create and open point to disconnect customer from the AltaLink system. Disconnect all control cables and customer connection to NGR installed inside customer interfacing JB (SHJB1). Remove BE1-81 relay and associated electro-mechanical relays. Remove revenue meter. Modify settings for T1 and VR1 protections to remove breaker 52 (634s8) trip signals. Update SCADA configuration and supervisory book. | For Information Only
ATCO | 7L23 (858s Narrows Creek - 7L23 tap), 7L23 (732s Mitsue - 796s Nipisi) | 2021-11-09 10:00 | 2021-11-09 14:00 | N | N | escorting high load under line crossings | Line |  | escorting high load under line crossings | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 5s 852 (5s East Calgary), 5s C4 (5s East Calgary) | 2021-11-10 07:30 | 2021-11-10 16:30 | N | N | install new platform/pedestal on breaker | Circuit Breaker, Shunts | 5s C4 (5s East Calgary) |  | Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2021-11-10 08:00 | 2021-11-12 16:00 | N | N | RTU commissioning | Line |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-1 T1 (29EDD-1 Millennium) | 2021-11-10 08:00 | 2021-11-13 18:00 | N | Y | transformer OLTC controller replacement | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L139 (819s Whitby Lake - 7LA139 tap) | 2021-11-10 08:00 | 2021-11-10 17:00 | N | N | change arms insulators | Line | 7L139 (819s Whitby Lake - 7LA139 tap) | GOI on 7L139 D2 to 819S Whitby Lake Change Arms Insulators | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek), 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2021-11-11 07:30 | 2021-11-14 16:30 | N | N | closing Open Point 'A' and connecting new customer equipment (P2448) | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
GENL | WCD1 West Cadotte | 2021-11-11 08:00 | 2021-11-11 20:00 | N | N | due to ATCO Wesley Creek, Simon Lake telecom work | Unit
ALTALINK | 957L (72s Leismer - 723s Christina Lake) | 2021-11-12 07:00 | 2021-11-12 20:00 | N | Y | urgent repair of 957L49: replace left pole on H-frame tangent after damage from vehicle accident | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21) | 2021-11-13 08:00 | 2021-11-13 18:00 | N | Y | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton) | 2021-11-15 07:00 | 2021-11-19 16:20 | N | Y | 1058L line maintenance and Lambton LDS6 LCR | Line, Circuit Breaker | 1058L (657s Summerside - EP 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330P 12TC2 (330p Genesee), 330p 1209 (330p Genesee), 330p 1203 (330p Genesee), 330p 1206 (330p Genesee), 330p 809 (330p Genesee) | 2021-11-15 07:00 | 2021-11-20 17:00 | N | Y | spire #3 repair | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 8.1TR (ENMAX 8), 8.2TR (ENMAX 8), 8B138-6A0 (ENMAX 8), 8B138-7A0 (ENMAX 8) | 2021-11-15 08:00 | 2021-11-19 16:00 | N | N | 8sub RTU commissioning | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 13.60L (ENMAX 13 - ENMAX 27), 13.4TR (ENMAX 13), 27.2TR (ENMAX 27) | 2021-11-15 08:00 | 2021-11-23 16:00 | N | N | 27.2TR HV, MV bushings replacement | Line, Transformer |  | 27.2TR HV, MV bushings Repl | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28) | 2021-11-15 08:00 | 2021-11-21 16:00 | N | Y | breaker refurbishment and maintenance | Line, Transformer |  | HPL breaker refurbishments on 28B138-28.80. 28B138-28.80 NEAR PHASE GAUGE Replacement. 28B138-28.80 Replace Relay in Breaker Mech. 28B138-28.80 Failure to close.. SW80 at 28 SUB stiff to open and close. 28 Sub SW80 - Replace North and South stops. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 802s 703T (802s Michichi Creek), 802s 705C (802s Michichi Creek) | 2021-11-15 08:00 | 2021-11-30 17:00 | N | N | 802s substation TCM upgrades: outdoor cabling, new 703T bus upgrade south of 700D1 commissioning and testing | Transformer, Shunts |  | 802S MICHICHI SUBSTATION TCM UPGRADES Outdoor Cabling Wiring New 703T Bus upgrade south of 700D1 Commissioning and Testing Energization | Pre-Condition
Syncrude | Aurora UT2 (Aurora) | 2021-11-15 08:00 | 2021-11-19 21:50 | N | N | maintenance | Transformer |  | Non-Significant Outage: UT-2 Transformer (72/13.8kV) @ G01 Substation Following Circuit Breakers will be operated: 21 @ G01 Substation 22 @ G01 Substation Following MOD's will be operated: 25 @ G01 Substation | For Information Only
ENMAX, ALTALINK | 1080L (ENMAX 25 - ENMAX 65) | 2021-11-15 08:00 | 2021-11-17 16:00 | N | Y | 25MD240-1080 replacement | Line |  |  | 240 kV, For Information Only
ALTALINK | 942L (71s Lamoureux - 681s Bannerman) | 2021-11-15 09:00 | 2021-11-18 18:00 | N | Y | replace insulation on 9 structures between structures #3 - 32. | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 763L (28s West Brooks - 763AL tap) | 2021-11-15 09:00 | 2021-11-18 18:00 | N | N | components replacements for 763L str's range 23-256 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2021-11-15 12:00 | 2021-11-19 18:00 | N | Y | component replacements and fire mitigation (Str's range 905L( 2-180)) | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 3L (245s Seebe - 3AL Tap), 245s 3E (245s Seebe) | 2021-11-15 12:30 | 2021-11-19 17:30 | N | N | protection replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 186s C1 (186s Dry Creek) | 2021-11-15 12:30 | 2021-11-22 17:30 | N | N | replace POW breaker 186s17 | Shunts |  |  | Pre-Condition
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2021-11-16 07:00 | 2021-11-16 18:00 | N | N | repair broken switch 262s49 | Transformer |  | Repair broken switch 262s49, P&C settings changes on: 168L 50/51/79/L2 SEL351S and 235L 50/51/79/L1 SEL351S | For Information Only
ALTALINK | 199S East Airdrie | 2021-11-16 07:30 | 2021-11-17 17:30 | N | N | 199s2238 (25kV breaker) to add remote recloser control to 199s2238 as part of the ACC visibility upgrade program | Station |  |  | For Information Only
ALTALINK | 20s T5 (20s Ghost) | 2021-11-16 07:30 | 2021-11-16 17:30 | N | N | replace station service, risers and fuse | Transformer |  |  | For Information Only
ALTALINK | 62S Brazeau | 2021-11-16 07:30 | 2021-11-16 15:30 | N | N | station service transformer testing | Station |  | TransAlta requested advice for Station Service transformer testing and maintenance. | For Information Only
ATCO | 951s SVC (951s Thickwood) | 2021-11-16 16:00 | 2021-11-19 16:20 | N | N | forced outage | Shunts |  |  | 240 kV, Pre-Condition
AESO-SC | OATI | 2021-11-16 18:00 | 2021-11-16 19:00 | N | N | Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 755L (247s Piper Creek - 535s Joffre) | 2021-11-16 18:50 | 2021-11-17 10:00 | N | N | forced outage | Line |  |  | Affects Cranking Path
EPCOR | 1098L (805s Jasper - Poundmaker), T2 (Poundmaker), PM2401 (Poundmaker), PM2402 (Poundmaker), PM2403 (Poundmaker) | 2021-11-17 07:00 | 2021-12-20 17:00 | N | Y | 240 kV ring re-configuration for WETUP project (P1649) | Line, Transformer, Circuit Breaker | Continuation of 240 kV ring re-configuration for WETUP project. HV bus re-configuration to tie Tx2 in between PM2401 and newly installed PM2405. Outage will provide isolation for HV bus re work and PMDS12 installation. |  | Creates Radial Feeds, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 370s T4 (370s North Lethbridge) | 2021-11-17 07:15 | 2021-11-29 17:45 | N | N | complete tie in of new BUS to 370sT4 TX18851 & Fortis feeder 465LE | Transformer |  |  | For Information Only
ALTALINK | 225L (67s Stirling - 225s Magrath), 225AL (313s Raymond Reservoir - 225L tap) | 2021-11-17 07:15 | 2021-12-13 17:45 | N | Y | rebuilding a portion of 225L from structure 241 to structure 281 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
TRANSALTA, ALTALINK | 179s 876 (179s Gleichen), 876L (179s Gleichen - 253s Blackie) | 2021-11-17 07:30 | 2021-11-17 16:30 | N | N | breaker outage | Circuit Breaker, Line | breaker outage to complete CT contributions to 154 RAS relays, loop checks to be completed |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CapitalPower | 615S Halkirk | 2021-11-17 08:00 | 2021-11-17 16:00 | N | N | communications only outage to work on HWP | Station |  | AS Availability N-A Minimum Load Requirement: N/A Available Capacity: 150 MW MVAR: N/A AS Availability: N/A | Affects Visibility, For Information Only
ALTALINK | 235s T4 (235s Entwistle) | 2021-11-17 08:00 | 2021-11-17 17:00 | N | N | installing new PT in the 25kV switchgear on 478L | Transformer |  |  | For Information Only
ALTALINK | 68s T2 (68s Willesden Green), 68s 552 (68s Amoco Willesden Green) | 2021-11-17 08:00 | 2021-11-17 18:00 | N | Y | URGENT repair broken 25kV switch (68s19) | Transformer, Circuit Breaker |  | URGENT repair broken 25kV switch (68s19) PM: MAPS (Darren) Issue to: Peter Johnson Contact #: 403.896.6061 | 240 kV
SUNCOR | 635EDD-1000 635-752-162 (635EDD-1000) | 2021-11-17 08:00 | 2021-11-18 18:00 | N | N | 635PS-1033 bonding strap installation | Circuit Breaker |  |  | For Information Only
ENMAX | 20.1TR (ENMAX 20) | 2021-11-17 08:00 | 2021-11-17 16:00 | N | N | relay, lockout testing. 20.1TR-86 | Transformer |  | Relay, Lockout Testing. 20.1TR-86 | For Information Only
ALTALINK | 54L (118s Canmore - 85L tap) | 2021-11-17 10:00 | 2021-11-17 17:45 | N | N | emergency repair to replace insulators on str 146 | Line | Emergency Repair; replace insulators str 146 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2021-11-17 10:00 | 2021-11-18 17:00 | N | N | outage to escort several high loads under crossing | Line |  | outage to escort several high loads under crossing | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 930s Syn Condenser (930s Arcenciel) | 2021-11-17 11:00 | 2021-11-25 18:00 | N | Y | investigation & repair | Shunts |  | ABB Rep Investigation & Repair | Pre-Condition
ALTALINK | 165s T1 (165s Gainford) | 2021-11-18 07:00 | 2021-11-19 17:10 | N | N | isolate 165s in order to cut existing cable and install new temp cables to customer (Trans Mountain) | Transformer |  |  | For Information Only
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2021-11-18 07:00 | 2021-11-19 18:00 | N | N | maintenance on structures 704, 712, 718, and 719 | Line | 799L (77s Sagitawah - 443s South Mayerthorpe) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2021-11-18 07:15 | 2021-11-19 17:45 | N | N | emergency repair - replace all cross arm assemblies on structures 261, 262 | Line |  | Emergency Repair; Replace all cross arm assemblies on structures 261, 262 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 199s T1 (199s East Airdrie) | 2021-11-18 07:30 | 2021-11-18 17:30 | N | N | alarm splitting on T1 (TX5744) as part of ACC visibility upgrade program | Transformer |  | Outage required to complete alarm splitting on T1 (TX5744) as part of ACC visibility upgrade program. As there is no redundant protection on T1 an equipment outage is required to complete this work. | For Information Only
ALTALINK | 33s 6 (33s Spray) | 2021-11-18 07:30 | 2021-11-19 08:30 | N | Y | maintenance | Switch |  | TransAlta requested Spray Unit 2 disconnect. | Restricts Generation
ENMAX | 32.1TR (ENMAX 32) | 2021-11-18 08:00 | 2021-11-18 16:00 | N | N | relay, lockout testing. 32.1TR-86 | Transformer |  |  | For Information Only
ALTALINK | 121s T5 (121s Brooks) | 2021-11-18 09:15 | 2021-11-18 15:45 | N | N | riser install on Line PT9 | Transformer | Complete riser install on Line PT9 for DER project (P2092) |  | For Information Only, Restricts Generation
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2021-11-20 07:00 | 2021-11-25 18:00 | N | N | maintenance on structures | Line | 799L (235s Entwistle - 443s South Mayerthorpe) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 104s T1 (104s Watson Creek) | 2021-11-20 07:00 | 2021-11-21 19:30 | N | N | complete reconfiguration of T1 to new equipment and demolish existing connection to old equipment | Transformer |  |  | For Information Only
CapitalPower | 615S Halkirk | 2021-11-20 08:00 | 2021-11-20 10:00 | N | N | Vestas Jumpbox Integration | Station |  | Vestas Jumpbox Integration. The work involves a B2B connection changeover that will disrupt the Vestas remote connection to VOB. | For Information Only
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2021-11-20 12:00 | 2021-11-20 16:00 | N | N | 5sub TRV project, first energization of 5B138-2.83 | Line
ALTALINK | 37s T5 (37s North Calder) | 2021-11-21 07:00 | 2021-11-23 17:00 | N | N | replacement of UG cables | Transformer
ALTALINK | 157s T1 (157s Lac La Biche) | 2021-11-22 07:00 | 2021-11-25 18:00 | N | N | urgent repair request to replace 25kv switch 157s289 and install new bird mitigation | Transformer |  | Urgent repair request to replace 25kv switch 157s289 like for like replacement, installation of new bird mitigation | For Information Only
EPCOR | T1 (EPCOR Hardisty), 72CH11 (987s Clover Bar - EPCOR Hardisty) | 2021-11-22 07:00 | 2021-12-07 17:00 | N | N | Hardisty TX1 replacement - 1007222 | Transformer, Line | 72CH11 (987s Clover Bar - EPCOR Hardisty), T1 (EPCOR Hardisty) | 72CH11 (987s Clover Bar - EPCOR Hardisty), T1 (EPCOR Hardisty) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L157 (837s Mahihkan - 970s Bourque) | 2021-11-22 08:00 | 2021-11-22 17:00 | N | N | hot spot repair to 837S 701A | Line |  | Hot Spot repair to 837S 701A 837S 701A Hot Spot detected on thermal scan, Need to operate 837S 701A a few times and see if wiping the contacts reduces the hotspot to an acceptable level. 7L157 Will be Open ended for approximately an hour. | Over/Under Voltage, Pre-Condition
ENMAX | 41.1C (ENMAX 41), 41.2TR (ENMAX 41), 6.82L (ENMAX 6 - ENMAX 41), 33.83L (ENMAX 33 - ENMAX 41) | 2021-11-22 08:00 | 2021-11-26 16:00 | N | N | 41 sub 138kV DFR upgrade | Shunts, Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 25B240-D131 (ENMAX 25) | 2021-11-22 08:00 | 2021-11-22 16:00 | N | N | breaker maintenance 25B240-D131 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162.1TR (162s Beddington), 240kV North Bus (ENMAX 162), 138kV North Bus (ENMAX 162) | 2021-11-22 08:00 | 2021-11-23 16:00 | N | Y | fault pressure testing - 240-162.1TR | Transformer, Bus |  | Fault Pressure Testing - 240-162.1TR. Relay, Lockout testing 86-T1A, 86-T1B | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition
ENMAX | 32.3TR (ENMAX 32) | 2021-11-22 08:00 | 2021-11-22 16:00 | N | N | relay, lockout testing 32.3TR-86 | Transformer |  |  | For Information Only
ENMAX | 8B138-4A0 (ENMAX 8), 8B138-5A0 (ENMAX 8), 8.3TR (ENMAX 8), 8.4TR (ENMAX 8) | 2021-11-22 08:00 | 2021-11-26 16:00 | N | N | 8sub RTU commissioning | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings) | 2021-11-22 08:45 | 2021-11-24 16:45 | N | N | urgent investigate and repair water leak in the thyristor tower | Line |  | Urgent outage required to Investigate and repair water leak in the thyristor tower | 500 kV, Pre-Condition
ALTALINK | 827L (28s West Brooks - 121s Brooks) | 2021-11-22 09:15 | 2021-11-25 17:45 | N | N | fire mitigation and component replacements (str 1C-35) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook) | 2021-11-22 09:30 | 2021-11-26 17:00 | N | Y | spire #2 Repair | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2021-11-22 12:00 | 2021-11-25 18:00 | N | Y | component replacements and fire mitigation(Str's Range 905L( 2-180) | Line |  |  | 240 kV, Overload, Pre-Condition
ALTALINK | 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake), 748L (267s Killarney Lake - 277s Hayter) | 2021-11-22 12:00 | 2021-11-22 17:00 | N | N | creating 267s open point 'A' | Shunts, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet) | 2021-11-22 12:30 | 2021-11-26 17:30 | N | Y | 74s C4 relay replacement | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2021-11-22 17:00 | 2021-12-01 10:00 | N | N | replacing 267s23 with a new switch and breaker | Shunts |  |  | Pre-Condition
ALTALINK | 730L (285s East Camrose - 732L tap) | 2021-11-23 07:00 | 2021-11-25 18:00 | N | N | urgent repair on 730L. Replace arms and insulators on structures 95 and 100 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | T1 (Woodcroft) | 2021-11-23 07:00 | 2021-11-24 17:00 | N | N | tap changer maintenance and high temp investigation | Transformer |  | Woodcroft TX1 Tap Changer Maintenance and High Temp investigation. | For Information Only, Pre-Condition
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2021-11-23 07:00 | 2021-11-23 18:00 | N | Y | escort Acuren to inspect welds on 903L66 | Line |  |  | 240 kV, For Information Only, Affects Cranking Path
ALTALINK | 275s T1 (275s Jenner) | 2021-11-23 07:15 | 2021-11-25 15:45 | N | Y | isolation of T1 Tx 18457 to install new Bird mitigation for the secondary side of T1 bus work and new reactor portion | Transformer | 275s T1 (275s Jenner) |  | 240 kV
Syncrude | UE-1 30-2PTR72-A2 (UE-1) | 2021-11-23 08:00 | 2021-12-02 20:00 | N | N | maintenance | Transformer |  | Non-Significant Outage: 30-2PTR72-A2 Transformer (72/13.8kV) @ UE-1 Substation Following Circuit Breakers will be operated: 52-7203 @ UE-1 Substation Following MOD's will be operated: 72-03 @ UE-1 Substation | For Information Only
ALTALINK | 204s T1 (204s Sandypoint) | 2021-11-23 08:00 | 2021-11-26 08:00 | N | N | customer switchgear inspection | Transformer |  |  | For Information Only
ENMAX | 32.2TR (ENMAX 32) | 2021-11-23 08:00 | 2021-11-23 16:00 | N | N | relay, lockout testing 32.2TR-86 | Transformer |  |  | For Information Only
ENMAX | 1B138-8A0 (ENMAX 1) | 2021-11-23 08:00 | 2021-11-24 17:00 | N | N | forced outage | Circuit Breaker |  |  | Contingency Requires Mitigation
HEARTLDGEN | HRT1 Heartland Petrochemical | 2021-11-23 08:00 | 2021-12-07 16:00 | N | N | P1647 Fengate Strathcona. 116 MW Gas. ISD Nov 30, 2021 | Unit
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2021-11-23 08:30 | 2021-11-23 11:30 | N | N | PRC005 trip coil testing | Line |  | T&O of 703 for PRC005 trip coil testing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2021-11-23 09:00 | 2021-12-17 17:00 | Y | Y | transmission refurbishment | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | SaskPower C1S | 2021-11-23 11:00 | 2021-11-26 17:00 | N | Y | maintenance | Line | SaskPower C1S | replacing 4 structures and stringing across Lake Diefenbaker | Limits ATC
ENMAXGPI | 134s RTU/SCADA (134s Taber Wind Farm) | 2021-11-23 21:15 | 2021-11-23 21:45 | N | N | upgrade network device | Terminal Equipment |  |  | Affects Visibility
BHE | 719s 138CB1 (719s Rattlesnake Ridge) | 2021-11-24 07:00 | 2021-11-24 17:30 | N | N | tie the PT and CT wiring into the SGRE SCADA control | Circuit Breaker |  |  | For Information Only
ENMAX | 162.2TR (162s Beddington), 138kV South Bus (ENMAX 162), 240kV South Bus (ENMAX 162) | 2021-11-24 08:00 | 2021-11-25 16:00 | N | Y | online monitoring project and testing | Transformer, Bus | Resolve online monitoring project punch list items. Fault Pressure Testing - 240-162.2TR, Relay, Lockout testing 86-T2A, 86-T2B |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek) | 2021-11-24 08:00 | 2021-11-24 12:00 | N | N | open for 793s MPLS upgrade | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 906L (17s Benalto - 42s Sarcee), 42s 906N (42s Sarcee) | 2021-11-24 09:00 | 2021-11-24 15:30 | N | Y | replace heater | Line, Circuit Breaker | 42s906N (906L) GOI |  | 240 kV, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2021-11-24 10:30 | 2021-11-24 15:30 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 27.2TR (ENMAX 27) | 2021-11-25 07:46 | 2021-12-01 16:00 | N | N | gas relay trip | Transformer
ALTALINK | 250p 22 (250p Bighorn Plant) | 2021-11-25 08:30 | 2021-11-25 13:30 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 102s 7452 (102s Langdon) | 2021-11-25 09:00 | 2021-11-25 15:30 | N | Y | replace heater | Circuit Breaker |  |  | 240 kV, For Information Only, Limits Ratings
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), 72RG1 (Garneau - Rossdale), VHBB2 (Rossdale), RG7210 (Rossdale), RV728 (Rossdale), RR729 (Rossdale) | 2021-11-25 19:00 | 2021-11-25 21:00 | N | N | Rossdale VHBB2 LCR initial energization | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark), M724 (Meadowlark), G724 (Garneau), G726 (Garneau) | 2021-11-26 07:00 | 2021-12-10 09:00 | N | N | steel install for new Duresca bus installation | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1252 (29EDD-1 Millennium) | 2021-11-26 08:00 | 2021-11-26 15:30 | N | N | repair avian protection on breaker | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2021-11-28 08:00 | 2021-11-28 16:00 | N | N | change POLE1000292114 | Line |  | change POLE1000292114 at rear of 3344 Barrett Pl NW. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8B138-1A0 (ENMAX 8), 8B138-7A0 (ENMAX 8), 2.84L (ENMAX 2 - ENMAX 8) | 2021-11-28 08:00 | 2021-11-30 16:00 | N | N | 8 sub RTU commissioning | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | GN2 Genesee #2 | 2021-11-28 08:00 | 2021-12-01 16:00 | N | N | P2224 Capital Power Genesee Unit 2 Change. ISD Nov 28, 2021 | Unit
EPCOR | T2 (Rossdale) | 2021-11-29 07:00 | 2021-11-29 17:00 | N | N | take measurements on low side for LCR in 2022 | Transformer |  |  | For Information Only
EPCOR | EP 803s L2401 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s LDS2 (EP 803s Lambton), EP 803s T1 (EP 803s Lambton) | 2021-11-29 07:00 | 2021-12-04 17:00 | N | Y | Lambton LDS2 LCR | Circuit Breaker, Switch, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 1205 (330p Genesee) | 2021-11-29 07:00 | 2021-12-03 17:00 | N | Y | spire #8 repair | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | EP 511s V728 (EP 511s Victoria), EP 511s V729 (EP 511s Victoria), 72VN21 (EP 511s Victoria - Namao) | 2021-11-29 07:00 | 2021-12-20 17:00 | N | N | structure replacement | Circuit Breaker, Line |  |  | Contingency Requires Mitigation
Saskpower | SASK POWER P2A | 2021-11-29 07:00 | 2021-12-04 18:00 | N | N | planned outage | Line |  |  | For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 41.84L (ENMAX 41 - ENMAX 54), 41.1TR (ENMAX 41), 41B138-40.81 (ENMAX 41), 41B138-41.84 (ENMAX 41), 41B138-41BT3 (ENMAX 41) | 2021-11-29 08:00 | 2021-12-02 16:00 | N | N | 41 sub 138kV DFR upgrade | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.4TR (ENMAX 2) | 2021-11-29 08:00 | 2021-11-29 16:00 | N | N | oil sampling bushing, check reversing switch | Transformer |  |  | For Information Only
ATCO | 740s 503 (740s H.R. Milner), 740s 703T (740s H.R.Milner) | 2021-11-29 08:00 | 2021-11-30 17:00 | N | N | disconnect 902S mobile substation to load side of breaker 503, HR Milner upgrade project: | Circuit Breaker, Transformer |  | HR Milner Upgrade Project Outage to disconnect 902SMobile Substation to load side of breaker 503 | For Information Only
ALTALINK | 827L (28s West Brooks - 121s Brooks) | 2021-11-29 09:15 | 2021-12-01 12:45 | N | N | fire mitigation and component replacements (str 1C-35) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 443L (55s Olds - 214s Innisfail) | 2021-11-29 09:15 | 2021-12-03 17:45 | N | N | components and structure replacements (Str 1-86) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 115s T2 (115s Mount Allan) | 2021-11-29 09:30 | 2021-12-02 17:30 | N | N | emergency work; remove gas from TX | Transformer |  |  | For Information Only
ALTALINK | 17s 43 (17s Benalto), 17s 1652 (17s Benalto) | 2021-11-29 10:00 | 2021-11-29 12:00 | N | Y | trip test from 17s85 BF Replacement | Switch, Circuit Breaker | 17s 43 (17s Benalto), 17s 1652 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 71s T1 (71s Lamoureux), 71s 240kV West Bus (71s Lamoureux), 71s 1252 (71s Lamoureux), 71s 1552 (71s Lamoureux) | 2021-11-29 12:00 | 2021-12-03 18:00 | N | Y | add new 240kV 'B' protection | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2021-11-29 12:00 | 2021-12-02 18:00 | N | Y | component replacements and fire mitigation (Str's Range 905L( 2-180)) | Line |  |  | 240 kV, Overload
ALTALINK | 17s 23 (17s Benalto), 17s 3 (17s Benalto) | 2021-11-29 12:30 | 2021-11-29 14:30 | N | Y | trip test from 17s85 BF replacement | Switch, Circuit Breaker | 17s 23 (17s Benalto), 17s 3 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 17s 39 (17s Benalto), 17s 9 (17s Benalto) | 2021-11-29 15:00 | 2021-11-29 17:00 | N | Y | trip test from 17s85 BF Replacement | Switch, Circuit Breaker | 17s 39 (17s Benalto), 17s 9 (17s Benalto) |  | 240 kV, Pre-Condition,
Saskpower | SaskPower PQ904 | 2021-11-30 07:00 | 2021-12-01 15:00 | N | N | maintenance | Circuit Breaker |  |  | Limits ATC
ENMAX | 32.1TR (ENMAX 32) | 2021-11-30 08:00 | 2021-11-30 16:00 | N | N | relay, lockout testing | Transformer |  | Relay, Lockout Testing. 32.1TR-86. | For Information Only
MILNERP | HRM H.R. Milner new gas | 2021-11-30 08:00 | 2021-12-14 16:00 | N | N | P2350 Milner 1 & 2 92 MW Gas. ISD Dec 7, 2021 | Unit
ENMAX | 35.1TR (ENMAX 35) | 2021-11-30 08:00 | 2021-11-30 12:00 | N | N | oil sampling TC, gas relay testing, filmax LTC oil filtration maintenance | Transformer |  | Oil sampling TC. Gas Relay Testing. Filmax LTC Oil Filtration Maintenance | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2021-11-30 08:00 | 2021-11-30 16:00 | N | N | oil sampling TC | Transformer |  |  | For Information Only
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap), 6L12 (775s Sullivan Lake - 6L25 tap) | 2021-11-30 08:00 | 2021-12-20 08:59 | N | N | 775S Sullivan Lake substation rebuild | Line |  | 775S Sullivan Lake Substation Rebuild Outage to 6L03/6L12 Close openers/isolators J1 on 6L03 and J2 on 6L12. Disconnect bypass. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 324s 2152 (324s Cassils) | 2021-11-30 09:30 | 2021-11-30 15:30 | N | Y | heater replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 34 (17s Benalto), 17s 4 (17s Benalto) | 2021-11-30 10:00 | 2021-11-30 12:00 | N | Y | trip test from 17s85 BF replacement | Switch, Circuit Breaker | 17s 34 (17s Benalto), 17s 4 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 35.2TR (ENMAX 35) | 2021-11-30 12:00 | 2021-11-30 16:00 | N | N | gas relay testing, oil sampling MT, filmax LTC oil filtration maintenance | Transformer |  | Gas Relay Testing. Oil Sampling MT. Filmax LTC Oil Filtration Maintenance | For Information Only, Pre-Condition
ALTALINK | 17s 13 (17s Benalto), 17s 59 (17s Benalto) | 2021-11-30 12:30 | 2021-11-30 14:30 | N | Y | trip test from s85 BF | Circuit Breaker, Switch | 17s 13 (17s Benalto), 17s 59 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 79 (17s Benalto), 17s C1 (17s Benalto) | 2021-11-30 15:00 | 2021-11-30 17:00 | N | Y | trip test from 85 BF | Switch, Shunts | 17s C1 (17s Benalto) |  | 240 kV, Pre-Condition
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2021-11-30 21:24 | 2021-12-03 18:00 | Y | Y | forced outage | Line |  |  | 500 kV, Affects Cranking Path
BHE Canada | MATL (120s Picture Butte - Montana) | 2021-11-30 21:24 | 2021-12-03 18:00 | N | Y | forced outage | Line |  |  | 240 kV, Limits ATC, Pre-Condition
EPCOR | G723 (Garneau) | 2021-12-01 07:00 | 2021-12-01 17:00 | N | N | P&C RAS scheme cut over and op-checks | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 33s 3 (33s Spray) | 2021-12-01 07:30 | 2021-12-02 16:30 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 39.4TR (ENMAX 39) | 2021-12-01 08:00 | 2021-12-01 16:00 | N | N | oil sampling TC, MT, corrective -secondary cable circulating current hazard | Transformer |  | Oil sampling TC, MT. 39.4TR Corrective - Secondary Cable Circulating Current Hazard. | For Information Only
ENMAX | 31B138-31CAP (ENMAX 31) | 2021-12-01 08:00 | 2021-12-08 16:00 | N | N | 31 sub cap bank vehicle gate addition | Circuit Breaker |  | 31 Sub Cap Bank Vehicle Gate Addition | Pre-Condition
ALTALINK | 463L (15s Fort Macleod - 463AL tap) | 2021-12-01 08:00 | 2021-12-01 15:15 | N | N | forced outage | Line
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514BL (322s Cowley Ridge Wind Plant - 514L tap), 514L (513s Range. Pipe Lundbreck - 514BL tap) | 2021-12-01 08:00 | 2021-12-03 18:00 | N | N | forced outage | Line
ALTALINK | 616L (103s Goose Lake - 616AL tap), 616AL (383s Kettles Hill Windfarm - 616L tap), 616L (59s Peigan - 103s Goose Lake), 616L (59s Peigan - 616AL tap) | 2021-12-01 08:00 | 2021-12-01 17:25 | N | N | forced outage | Line
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2021-12-01 08:00 | 2021-12-06 15:00 | N | N | pole replacement/ arm replacement/ inter-phase spacers on 6L09. | Line |  | Pole replacement/ Arm replacement/ inter-phase spacers on 6L09. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.6TR (ENMAX 8) | 2021-12-01 08:00 | 2021-12-04 08:00 | N | N | 8sub RTU commissioning | Transformer |  | 8.6TR. 8s 86-T6 transformer differential protection. | For Information Only
ALTALINK | 863L (618s Riverbend - 891L tap) | 2021-12-01 08:00 | 2021-12-03 18:00 | N | N | forced outage | Line
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2021-12-01 08:00 | 2021-12-08 16:00 | N | N | repair leaking cables | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 2021-12-01 08:00 | 2021-12-03 18:00 | N | N | forced outage | Line
CapitalPower | 615s DVAR1 (615s Halkirk), 615s DVAR2 (615s Halkirk) | 2021-12-01 09:00 | 2021-12-03 17:00 | N | N | inverter repair & DSTAT testing | Shunts
ALTALINK | 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 748L (267s Killarney Lake - 277s Hayter), 267s C3 (267s Killarney Lake) | 2021-12-01 10:00 | 2021-12-02 14:00 | N | N | closing 267s Open Point 'A' | Shunts, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | G724 (Garneau) | 2021-12-02 07:00 | 2021-12-02 17:00 | N | N | cut over P&C RAS scheme and op-checks | Circuit Breaker |  | Garneau: P&C RAS Scheme Cut Over and Op-Checks | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.1TR (ENMAX 5) | 2021-12-02 08:00 | 2021-12-04 08:00 | N | N | 5sub TRV project - replace MV circuit breaker, check reversing switch | Transformer |  | 5sub TRV Project. Replace MV circuit breaker. Check reversing switch | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2021-12-02 08:00 | 2021-12-02 16:00 | N | N | relay, lockout testing | Transformer |  | Relay, Lockout Testing. 6.4TR-86 | For Information Only, Pre-Condition
ENMAX | 39.1TR (ENMAX 39) | 2021-12-02 08:00 | 2021-12-02 16:00 | N | N | oil sampling bushing, TC, MT, secondary cable circulating current hazard | Transformer |  | Oil Sampling Bushing, TC, MT. Secondary Cable Circulating Current Hazard, | For Information Only, Pre-Condition
ALTALINK | 166S Dow Chemical Fort Saskatchewan | 2021-12-02 08:30 | 2021-12-02 17:30 | N | Y | urgent - hot spot repairs - 166s19, lightning arrestor replacement | Station |  | URGENT Replace 3 138kV lightning arrestors on 138kV bus that 166s19 is on. The 138kV bus LAs require replacement under urgent replacement due to 20 degree hot spot. Due to risk and consequence of failure. | For Information Only
ALTALINK | 679L (478s Tucuman - 574s Nilrem), 478s 679 (478s Tucuman) | 2021-12-02 08:30 | 2021-12-02 15:30 | N | N | tank heater replacement | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 276s C1 (276s Prentiss), 276s 652 (276s Un Carb Prentiss) | 2021-12-02 08:30 | 2021-12-02 17:30 | N | N | tank heater replacement | Shunts, Circuit Breaker |  | Tank heater replacement. PM: MAPS (Glenn) Issue to: Enrique Chacon Contact #: 403-896-2114 | Pre-Condition
ALTALINK | 604L (149s Nisku - 155s Blackmud) | 2021-12-03 07:00 | 2021-12-06 18:00 | N | N | moving line between structures #22 - 36 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee) | 2021-12-03 07:00 | 2021-12-04 18:00 | N | Y | maintenance on structures 57, 59, 62, 67 and 68 | Line |  |  | 500 kV, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation,Affects Cranking Path
EPCOR | 72KN23 (Kennedale - Namao), 72NW15 (Namao - Woodcroft), 72VN21 (EP 511s Victoria - Namao) | 2021-12-04 07:00 | 2021-12-04 17:00 | N | N | Namao NVT01 Cutovers | Line |  |  | For Information Only, Pre-Condition
Syncrude | D05 LCF (D05) | 2021-12-04 08:00 | 2021-12-04 20:00 | N | N | urgent lower camp feeder outage | Transformer |  |  | For Information Only
ENMAX | 8.5TR (ENMAX 8), 8.6TR (ENMAX 8) | 2021-12-04 08:00 | 2021-12-05 16:00 | N | N | 8 sub RTU commissioning | Transformer |  |  | For Information Only
ALTALINK | 370s T1 (370s North Lethbridge) | 2021-12-06 07:15 | 2021-12-12 17:45 | N | N | complete secondary U/G cabling, install tie breaker | Transformer |  | Removal of overhead conductor to 465L1, complete secondary U/G cabling, reconductor bus 1 & prep for 370s452 on future outage. Breaker trip tests for 370s1552 breaker fail on 370s40 & 370s10. DG required to be offline for duration of the outage | For Information Only, Restricts Generation
ENMAX | 38.1C (ENMAX 38), 38B138-38.1CAP (ENMAX 38) | 2021-12-06 07:30 | 2021-12-09 10:00 | N | N | forced outage | Shunts, Circuit Breaker |  | ENMAX has an unscheduled outage to 38.1CAP this morning. 38B138-38.1CAP failed to close when commanded. ENMAX crews will investigate. Estimated time of restoration is Dec. 7, 2021 @ 16:00. Will update as information becomes available. The crew has determined that the closing mechanism is broken and requires replacement parts. These parts will have to be ordered and as such, Enmax 38 Sub Cap bank is out of service until further notice. We will send updates as we are made aware. AESO real-time has been notified. | For Information Only
ENMAX | 5.5TR (ENMAX 5) | 2021-12-06 08:00 | 2021-12-11 08:00 | N | N | relay testing | Transformer | Relay, Protection Testing - SR760, T-60, SEL 351S. 5sub TRV Project. Replace MV circuit breaker. Check reversing switch |  | For Information Only
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2021-12-06 09:00 | 2021-12-13 12:00 | N | Y | changing poles from test and treat | Line |  | Changing poles from test and treat | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 814L (28s West Brooks - 121s Brooks) | 2021-12-06 09:15 | 2021-12-09 17:45 | N | N | fire mitigation and component replacements (str 4-35) | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 443L (55s Olds - 214s Innisfail) | 2021-12-06 09:15 | 2021-12-09 17:45 | N | N | components and structure replacements (Str 1-86) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 212s 461 (212s N.E. Lacombe), 461L (198s Blackfalds - 212s N.E. Lacombe) | 2021-12-06 10:30 | 2021-12-06 16:30 | N | N | replacing tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2021-12-06 12:00 | 2021-12-20 17:00 | N | Y | replace cross arms and replace poles | Line |  | Replace crossarms and replace poles. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 526L (515s Fed Pipe Judy Creek - 6L126 tap) | 2021-12-07 07:00 | 2021-12-07 18:00 | N | N | replacing structure #526L489 | Line |  |  | Firm Load Loss
ALTALINK | 221s T2 (221s Sunken Lake) | 2021-12-07 07:00 | 2021-12-07 23:00 | N | N | urgent - replace 2 phases cracked CT below T2 | Transformer |  | URGENT Replace 2 phases cracked CT below T2 (Where note 8 is below T2)Like for like replacement | For Information Only
ALTALINK, Lethbridge | 370s 175 (370s North Lethbridge), 172L (181s Chinook - 370s North Lethbridge) | 2021-12-07 07:15 | 2021-12-07 17:45 | N | Y | complete P&C cutovers | Circuit Breaker, Line | Isolate breaker to complete P&C Cutovers, Remove and Add Trips, Modify Block Close |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 55s T2 (55s Olds) | 2021-12-07 07:30 | 2021-12-08 17:30 | N | N | safety requirement re - 443L work | Transformer |  | safety requirement re: 443L GOI (line crosses over top of this section of the 25kV bus) | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 31B138-31.84 (ENMAX 31) | 2021-12-07 08:00 | 2021-12-07 16:00 | N | N | 31 sub 138 kV DFR equipment upgrade | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 42s C3 (42s Sarcee), 42s C2 (42s Sarcee), 42s 75 (42s Sarcee), 42s 76 (42s Sarcee) | 2021-12-07 08:00 | 2021-12-07 17:00 | N | Y | investigate C3 unbalanced alarm | Shunts, Switch, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 21.1C (ENMAX 21), 21B138-21.CAP (ENMAX 21) | 2021-12-07 08:00 | 2021-12-07 16:00 | N | N | relay, lockout testing | Shunts, Circuit Breaker |  | relay, lockout testing. 21.1CAP-86 | For Information Only, Pre-Condition
ALTALINK | 71s 552 (71s Lamoureux) | 2021-12-07 08:00 | 2021-12-07 13:00 | N | N | trip testing from new 240 kV 'B' protection | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 17s 51 (17s Benalto), 17s 757N (17s Benalto) | 2021-12-07 08:00 | 2021-12-07 11:00 | N | N | trip test from new s92 breaker fail and s757N breaker fail | Switch, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 678S Okotoks | 2021-12-07 08:30 | 2021-12-08 17:30 | N | N | 25 kV feeder - add remote recloser control to 678s81E | Station | 25kV breaker | Outage to add remote recloser control to 678s81E as part of the ACC visibility upgrade program. Recloser will need to be functioned during this outage. | For Information Only
ATCO | 787s 703C (787s High Prairie), 787s 703 (787s High Prairie) | 2021-12-07 09:30 | 2021-12-08 16:00 | N | N | re-wire trip circuit | Shunts, Circuit Breaker |  | Re-wire Trip Circuit, 703C OOS | Pre-Condition
ALTALINK | 17s 637 (17s Benalto), 637L (17s Benalto - 580s Sylvan Lake) | 2021-12-07 11:30 | 2021-12-07 14:30 | N | N | trip test from new s92 breaker fail and s757N breaker fail | Circuit Breaker, Line | 637L (17s Benalto - 580s Sylvan Lake), 17s 637 (17s Benalto) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 71s 152 (71s Lamoureux) | 2021-12-07 13:00 | 2021-12-07 17:30 | N | N | trip testing from new 240kV 'B' protection. | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 17s 717W (17s Benalto) | 2021-12-07 15:00 | 2021-12-07 18:00 | N | N | trip test | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge), 370s 207X (370s North Lethbridge) | 2021-12-08 07:15 | 2021-12-08 14:45 | N | Y | complete P&C cutovers, remove and add trips, modify block close | Line, Circuit Breaker |  | Isolate breaker to complete P&C Cutovers, Remove and Add Trips, Modify Block Close. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 17s 2852 (17s Benalto), 17s T3 (17s Benalto) | 2021-12-08 08:00 | 2021-12-08 11:00 | N | Y | trip test from new s92 breaker fail and s757N breaker fail | Circuit Breaker, Transformer | 17s T3 (17s Benalto), 17s 2852 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 47.2TR (ENMAX 47) | 2021-12-08 08:00 | 2021-12-08 16:00 | N | N | oil sampling TC, ceck reversing switch, LTC oil filtration maintenance | Transformer |  | Oil Sampling TC. Check Reversing Switch. LTC Oil Filtration Maintenance | For Information Only
ALTALINK | 237s 652 (237s Foothills) | 2021-12-08 08:30 | 2021-12-08 17:30 | N | N | SF6 gas top up | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 63s 51 (63s Red Deer) | 2021-12-08 09:30 | 2021-12-09 09:00 | N | N | replacing tank heater | Circuit Breaker |  |  | For Information Only
ATCO | 948s 704 (948s Heatburg), 7L159 (948s Heatburg - 7LA159 tap) | 2021-12-08 12:00 | 2021-12-08 16:30 | N | N | T&O of 704 for PRC005 trip coil testing | Circuit Breaker, Line |  | T&O of 704 for PRC005 trip coil testing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 370s 770E (370s North Lethbridge), 770L (254s Coaldale - 370s North Lethbridge) | 2021-12-09 07:15 | 2021-12-09 17:45 | N | N | isolate breaker to complete P&C cutovers | Circuit Breaker, Line |  | Isolate breaker to complete P&C Cutovers, Remove and Add Trips, Modify Block Close | For Information Only
ALTALINK | 787L (71s Lamoureux - 787AL tap), 166s T3 (166s Dow Chemical Fort Saskatchewan) | 2021-12-09 08:00 | 2021-12-09 16:00 | N | Y | urgent repairs to 166s17 switch | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 33.1TR (ENMAX 33) | 2021-12-09 08:00 | 2021-12-09 16:00 | N | N | relay, lockout testing | Transformer |  |  | For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2021-12-09 08:00 | 2021-12-09 12:00 | N | N | oil sampling, tap changer heater failure | Transformer |  |  | For Information Only
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2021-12-09 08:00 | 2021-12-09 16:00 | N | N | 138 kV DFR equipment upgrade | Line |  |  | For Information Only
ALTALINK, BHE Canada | 1005L (120s Picture Butte - 356s Milo), 356s 252 (356s Milo), 356s 152 (356s Milo), 120s 152 (120s Picture Butte), 120s 252 (120s Picture Butte) | 2021-12-09 09:15 | 2021-12-20 17:45 | N | Y | connect customer substation to 1005AL, final commissioning (P2009) | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 426L (63s Red Deer - 194s South Red Deer) | 2021-12-09 09:15 | 2021-12-09 17:45 | N | N | maintenance structure 13 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 428s 652 (428s Namaka), 428s T2 (428s Namaka) | 2021-12-09 09:30 | 2021-12-09 15:30 | N | N | SF6 gas top up | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 71s 952 (71s Lamoureux), 71s C1 (71s Lamoureux) | 2021-12-09 09:30 | 2021-12-09 13:30 | N | N | trip testing from new 240 kV 'B' protection | Circuit Breaker, Shunts |  | Trip testing from new 240kV 'B' protection. | Pre-Condition
ENMAX | 11.2TR (ENMAX 11) | 2021-12-09 12:00 | 2021-12-09 16:00 | N | N | oil leak and reversing switch check | Transformer |  | 11.2TR Oil Leak At Gas Relay. 11.2TR Check reversing Switch | For Information Only
ATCO | 863s 902T (863s Paintearth) | 2021-12-09 13:00 | 2022-09-07 17:00 | N | Y | forced outage and troubleshooting | Transformer |  | Troubleshoot Oil Level Gauge Gnd Fault , all load was transferred to 901T after the ground fault on 902T had cleared the sub. When they transferred the load the ground fault went away so they are waiting to see if it comes back before they transfer load back to 902T. 902T is available if needed | 240 kV, Pre-Condition
ALTALINK | 71s 1052 (71s Lamoureux), 71s C2 (71s Lamoureux) | 2021-12-09 13:30 | 2021-12-09 17:30 | N | N | trip testing from new 240 kV 'B' protection | Circuit Breaker, Shunts |  | Trip testing from new 240kV 'B' protection. | Pre-Condition
ALTALINK | 719L (256s Harmattan - 719CL tap) | 2021-12-10 07:15 | 2021-12-11 17:45 | N | N | maintenance work on strs 65, 68, 69, 70 and 72 | Line |  | maintenance work on Strs 65, 68, 69, 70 and 72 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T3 (370s North Lethbridge), 370s 2152 (370s North Lethbridge) | 2021-12-10 07:15 | 2021-12-10 14:45 | N | Y | complete P&C cutovers, remove and add trips, modify block close | Transformer, Circuit Breaker | 370s 2152 (370s North Lethbridge) | Isolate breaker to complete P&C Cutovers, Remove and Add Trips, Modify Block Close | 240 kV, Overload, Pre-Condition
ALTALINK | 755L (247s Piper Creek - 535s Joffre) | 2021-12-10 07:15 | 2021-12-12 17:45 | N | N | urgent spacer installation at structures 118 - 125 | Line |  | Urgent spacer installation at structures 118 - 125 to prevent conductor damage during winter storms | Pre-Condition, Affects Cranking Path
ENMAX | 33.2TR (ENMAX 33) | 2021-12-10 08:00 | 2021-12-10 16:00 | N | N | relay, lockout testing | Transformer |  | Relay, Lockout Testing. 33.2TR-86. | For Information Only
ENMAX | 31B138-31CAP (ENMAX 31) | 2021-12-10 08:00 | 2021-12-10 16:00 | N | N | 138 kV DFR equipment upgrade | Circuit Breaker |  | 31 SUB 138kV DFR Equipment Upgrade | Pre-Condition
ALTALINK | 77S Sagitawah | 2021-12-10 09:00 | 2021-12-10 17:00 | N | N | replace A87/240B-W failed relay | Station |  | Job Scope(Urgent work): Replace the A87/240B-W failed relay. Redundant protection always in service. | For Information Only
ENMAX | 5.5TR (ENMAX 5) | 2021-12-11 08:00 | 2021-12-12 16:00 | N | N | 5 sub TRV project- replace MV circuit breaker | Transformer |  | 5sub TRV Project. Replace MV circuit breaker, bus outage required to install new breaker | For Information Only
EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton) | 2021-12-13 07:00 | 2021-12-17 17:00 | N | Y | LDS6 LCR | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s 2552 (370s North Lethbridge), 370s 1552 (370s North Lethbridge), 370s T4 (370s North Lethbridge) | 2021-12-13 07:15 | 2021-12-16 17:45 | N | N | bus protection modifications | Circuit Breaker, Transformer | 370s2552 370s1552 & 25kV BUS 4 GOI Tie in bus protection trips from B1 and B3 to 370s2552. Modification of CT circuits, Block Closes, and Trips to 370s1552, CT modification on T4. Finalize AMI Power termination to BUS 4 |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | PM2405 (Poundmaker), PMDS11 (Poundmaker), PMDS12 (Poundmaker) | 2021-12-13 08:00 | 2021-12-27 16:00 | N | N | ISD Dec 20, 2021. P1649 | Circuit Breaker, Switch
ENMAX | 38.1C (ENMAX 38) | 2021-12-13 08:00 | 2021-12-14 16:00 | N | N | 38 SUB 138kV DFR Equipment Upgrade | Shunts |  |  | Pre-Condition
ENMAX | 31.2TR (ENMAX 31) | 2021-12-13 08:00 | 2021-12-13 16:00 | N | N | 31 sub 138 kV DFR equipment upgrade | Transformer |  |  | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2021-12-13 08:00 | 2021-12-14 16:00 | N | N | 38 sub 138 kV DFR equipment upgrade | Transformer |  | 38 SUB 138kV DFR Equipment Upgrade. Close open close required on MD on return. | For Information Only
ATCO | 774s 705C (774s Monitor) | 2021-12-13 09:00 | 2021-12-13 19:00 | N | N | investigate alarm on 774s 705C | Shunts |  | investigate 705C Imbalanced shunt alarm on 774S 705C | For Information Only
ALTALINK | 789L (898s Heart Lake - 789BL tap) | 2021-12-13 09:00 | 2021-12-15 18:00 | N | Y | maintenance on structures #77 & 78 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 443L (55s Olds - 214s Innisfail) | 2021-12-13 09:15 | 2021-12-16 16:30 | N | N | components and structure replacements (Str 1-86) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 6L02 (765s Mannix Mine - 873s Marion Lake) | 2021-12-13 10:00 | 2021-12-13 17:00 | N | N | urgent work to repair 6L02D4 | Line |  | Urgent work to repair 6L02D4. Isolate 6L02D4 to repair switch See HOP 2-61986 for cutting Jumpers cut in on each side of switch | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2021-12-13 11:00 | 2021-12-15 14:40 | N | Y | fire mitigation component replacement | Line | Fire Mitigation component replacement's 915L( Str's 12, 13, 14) Double circuits 947L See Also 947L R/B SAP: 277629 |  | 240 kV, For Information Only
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain) | 2021-12-13 13:00 | 2021-12-22 12:00 | N | Y | changing poles from test and treat | Line |  | Changing poles from test and treat | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T2 (Woodcroft) | 2021-12-14 07:00 | 2021-12-15 17:00 | N | N | tap changer maintenance and leak Inspection | Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 700L (422s Westwood - 746s Sherwood Park), 746L (700L tap - 746AL tap), 422s 700 (422s Westwood) | 2021-12-14 07:00 | 2021-12-15 18:00 | N | N | replace 700L41 in preparation for line move and relocation | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 205S Castle Rock Ridge | 2021-12-14 07:30 | 2021-12-14 14:00 | N | N | feeder 2 of Castle Rock Ridge outage to facilitate the safe exchange of MV/LV transformer at CRR1 turbine 9. | Station |  | We need to take a Castle Rock Ridge Feeder 2 outage on Tuesday, 12.14.2021 from 07:30 MT to 14:00 MT, to facilitate the safe exchange of MV/LV transformer at CRR1 turbine 9. | Restricts Generation
ALTALINK | 283s 835E (283s Violet Grove), 835L (283s Violet Grove - 835AL tap) | 2021-12-14 07:30 | 2021-12-15 14:30 | N | N | replace leaking A phase CT on 283s835E | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 40.1TR (ENMAX 40) | 2021-12-14 08:00 | 2021-12-14 16:00 | N | N | relay, lockout testing, 40.1TR-86 | Transformer |  |  | For Information Only
ENMAX | 24.81L (ENMAX 24 - ENMAX 31), 31B138-24.81 (ENMAX 31) | 2021-12-14 08:00 | 2021-12-14 16:00 | N | N | 31 SUB 138kV DFR equipment upgrade | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2021-12-14 08:00 | 2021-12-14 11:00 | N | Y | top up SF6 | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap), 6L21 (Youngstown Express - 6L09 tap), 6L09 (772s Youngstown - 776s Richdale) | 2021-12-14 08:00 | 2021-12-18 15:15 | N | N | pole replacement on 6L09 | Line |  | Pole replacement/ Arm replacement/ interphase spacers on 6L09. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 428s T2 (428s Namaka), 428s 652 (428s Namaka) | 2021-12-14 08:00 | 2021-12-15 16:00 | N | N | bird cover up installation | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 370s T4 (370s North Lethbridge) | 2021-12-14 08:00 | 2021-12-28 16:00 | N | N | P2123 Fortis Alberta Lethbridge Area Reliability. ISD Dec 21, 2021. N.O. Transformer will be closed. | Transformer
ALTALINK | 723s T2 (723s Christina Lake), 723s 252 (723s Christina Lake) | 2021-12-14 09:00 | 2021-12-14 17:00 | N | Y | replace fuse holder for 723s31, SF6 top up & maintenance on 723s252 and sub checks | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 17s T3 (17s Benalto), 17s 2852 (17s Benalto) | 2021-12-14 09:30 | 2021-12-14 17:30 | N | Y | leak repair, heater repair (17s2852) | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 757s 708 (757s Battle River) | 2021-12-14 10:00 | 2021-12-14 13:00 | N | N | PRC005 work on breaker708 | Circuit Breaker |  | PRC005 work on 708 Breaker - - 1-2 hours duration in time period, will not overlap with 757S 706, 757S 707, or 757S 709 No outage will use Floating breaker 757S 706 to keep line in service by closing 757S 708Y and closing 757S 706 prior to outage. GenAlta BellShill DG AML Sedgewick  DG is required to be off line, due to DTT when Breaker 708 is open. | Pre-Condition, Restricts Generation
ALTALINK | 320p 2152 (320p Keephills) | 2021-12-14 11:00 | 2021-12-14 14:00 | N | Y | top up SF6 | Circuit Breaker |  |  | 240 kV, Pre-Condition
AESO-SC | OATI | 2021-12-14 18:00 | 2021-12-14 19:00 | N | N | Inter-Site transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 755L (247s Piper Creek - 535s Joffre) | 2021-12-15 07:15 | 2021-12-15 17:45 | N | N | urgent spacer installation at structures 118 - 125 | Line |  | Urgent spacer installation at structures 118 - 125 to prevent conductor damage during winter storms | Pre-Condition, Affects Cranking Path
ALTALINK, Travers2SolarLP | 991s Little Bow, TVS1 Travers, 1005AL (991s Little Bow - 1005L tap) | 2021-12-15 08:00 | 2022-08-30 16:00 | N | N | P2009 Greengate Travers Solar. 400 MW. ISD Dec 15, 2021 | Station, Unit, Line
ENMAX | 40.2TR (ENMAX 40) | 2021-12-15 08:00 | 2021-12-15 16:00 | N | N | relay, lockout testing, 40.2TR-86 | Transformer |  |  | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2021-12-15 08:00 | 2021-12-15 16:00 | N | N | 31 sub 138 kV DFR equipment upgrade | Transformer |  | 31 SUB 138kV DFR Equipment Upgrade | For Information Only
ENMAX | 37.81L (ENMAX 37 - ENMAX 38), 38.2TR (ENMAX 38), 38B138-37.81 (ENMAX 38) | 2021-12-15 08:00 | 2021-12-16 16:00 | N | N | 38 sub 138 kV DFR equipment upgrade | Line, Transformer, Circuit Breaker |  | 38 SUB 138kV DFR Equipment Upgrade | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 526s 336 (526s Buffalo Creek) | 2021-12-15 08:30 | 2021-12-15 16:30 | N | N | 25 kV breaker - add addition alarming to 336s protection | Circuit Breaker |  | Feeder outage to add addition alarming to 336s protection. Only single protection hence the feeder outage. | Pre-Condition, Restricts Generation
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake), 17s 637 (17s Benalto) | 2021-12-15 09:00 | 2021-12-15 17:00 | N | N | install step up transformer for heaters | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 268s T1 (268s Whitecourt) | 2021-12-15 09:30 | 2021-12-15 17:30 | N | N | urgent work to repair bushing | Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
TRANSALTAGP | EAGL Whitecourt Power | 2021-12-15 09:30 | 2021-12-15 17:30 | N | N | due to 268sT1 outage | Unit
ALTALINK | 62s 11 (62s Brazeau) | 2021-12-15 23:00 | 2021-12-16 03:00 | N | Y | maintenance | Switch |  | unit outage request by TransAlta | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2021-12-16 03:00 | 2021-12-16 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
EPCOR | T3 (Woodcroft) | 2021-12-16 07:00 | 2021-12-16 17:00 | N | N | tap changer maintenance | Transformer |  |  | For Information Only
ENMAX | 6.1TR (ENMAX 6) | 2021-12-16 08:00 | 2021-12-16 16:00 | N | N | relay, lockout testing, 6.1TR-86 | Transformer |  |  | For Information Only
ALTALINK | 12s RTU/SCADA (12s Heartland) | 2021-12-16 08:00 | 2021-12-16 16:00 | N | N | urgent repair | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 17s 757N (17s Benalto), 757L (17s Benalto - 758L tap) | 2021-12-16 11:00 | 2021-12-16 17:00 | N | N | install step up transformer for heaters | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2021-12-16 11:00 | 2021-12-16 15:00 | N | N | escort high load under line | Line |  | Escort High Load Under Line | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
BHE Canada | Great Falls Switchyard (NorthWestern Energy) - Marias (MATL) | 2021-12-16 13:00 | 2021-12-16 15:00 | N | Y | detached shield wire urgent repair | Line |  |  | Limits ATC, Pre-Condition
EPCOR | T1 (Strathcona), 72DS26 (665s Dome - Strathcona) | 2021-12-20 07:00 | 2021-12-20 17:00 | N | N | P&C winding temperature gauge repair | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 29s T2 (29s Cascade) | 2021-12-20 07:30 | 2021-12-20 11:30 | N | N | battery maintenance | Transformer |  |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2021-12-20 08:00 | 2021-12-20 16:00 | N | N | 31 SUB 138kV DFR equipment upgrade | Transformer |  |  | For Information Only
ENMAX | 14.2TR (ENMAX 14) | 2021-12-20 08:00 | 2021-12-20 16:00 | N | N | oil sampling tap changer | Transformer |  |  | For Information Only
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 38.1TR (ENMAX 38), 38B138-38.83 (ENMAX 38) | 2021-12-20 08:00 | 2021-12-21 16:00 | N | N | 38 sub 138kV DFR equipment upgrade | Line, Transformer, Circuit Breaker | 38.83L. 38.1TR 38 SUB 138kV DFR Equipment Upgrade |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap), 6L25 (773s Coronation - 6L12 tap), 773s 601TD (773s Coronation) | 2021-12-20 09:00 | 2021-12-20 17:00 | N | N | repair D2 on 6L12 and perform work on 601TD | Line, Switch |  | We require GOI on 6L12/6L25 to repair D2 on 6L12 773S load will be offloaded to adjacent subs Techs to perform work on 601TD at the same time as 6L12/6L25 outage | For Information Only, Pre-Condition
ALTALINK | 58s 890 (58s Edson), 890L (58s Edson - 207s Pinedale) | 2021-12-21 06:30 | 2021-12-21 18:00 | N | N | complete CT cutovers for new RAS relays | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | G725 (Garneau) | 2021-12-21 07:00 | 2021-12-21 17:00 | N | N | P&C RAS scheme cut over and op-checks | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | RW727 (Rossdale), 72RW3 (Rossdale - Woodcroft) | 2021-12-21 07:00 | 2021-12-21 17:00 | N | N | low SF6 emergency top up | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 531s T1 (531s Shell Schrader Creek) | 2021-12-21 09:00 | 2021-12-21 15:00 | N | N | repair 97.0 degree hot spot | Transformer |  |  | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia), 58s 34 (58s Edson) | 2021-12-22 06:30 | 2021-12-22 18:00 | N | N | complete CT cutovers for new RAS relays | Line, Switch |  |  | Overload, Pre-Condition, Affects Cranking Path
EPCOR | G722 (Garneau) | 2021-12-22 07:00 | 2021-12-22 17:00 | N | N | Garneau: P&C RAS scheme cut over and op-checks | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 118s C1 (118s Canmore) | 2021-12-22 09:00 | 2021-12-22 14:00 | N | N | correcting deficiencies, changing settings on A50/51A,B,C/51N/59/60/C1 | Shunts |  |  | For Information Only
ATCO | 741s 701 (741s Fox Creek), 7L90 (741s Fox Creek - 7LA90 tap) | 2021-12-22 10:00 | 2021-12-22 16:00 | N | N | emergency SF6 gas top up | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-01-01 08:00 | 2023-03-07 18:00 | N | N | 30EDD-200 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-01-01 08:00 | 2022-11-09 18:00 | N | N | 29EDD-8 | Not In Model | Unmodeled Transmission Facility (Suncor) | 29EDD8/29PT-47 SYS PM (5Y/10Y) | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-01-01 08:00 | 2022-10-19 18:00 | N | N | 29EDD-9 | Not In Model | Unmodeled Transmission Facility (Suncor) | 29EDD9/29PT-48 SYS main&test PM(5Y/10Y) | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-01-01 08:00 | 2023-03-06 18:00 | N | N | 30EDD-200 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ALTALINK | 17s 2852 (17s Benalto), 17s T3 (17s Benalto) | 2022-01-02 09:30 | 2022-01-02 17:30 | N | Y | urgent repair to tank heater to prevent cyclic SF6 lockouts | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain) | 2022-01-04 09:00 | 2022-01-10 12:00 | N | Y | changing poles mitigation and test and treat | Line |  | Changing Poles Mitigation and Test and Treat | Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-01-04 09:00 | 2022-01-10 12:00 | N | N | changing arms and pole repairs | Line |  | Changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2022-01-04 17:30 | 2022-01-07 19:00 | N | N | forced outage | Line |  |  | For Information Only
ALTALINK | 305s C1 (305s Acheson) | 2022-01-05 08:30 | 2022-01-07 17:30 | N | N | replace the following relay: C1 A50/51/27/59/C1 SR850 | Shunts |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-01-07 07:00 | 2022-01-18 18:00 | N | N | 174L Phase 3 rebuild (structures 539 to 691) | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
NPC | Elmworth DER Gas | 2022-01-07 08:00 | 2022-01-21 16:00 | N | N | P2394 AtCO Elmworth 731s DER Gas. 9 MW. ISD Jan 14, 2022 | Unit
ATCO | 779s 701T (779s Chinchaga River) | 2022-01-07 09:00 | 2022-02-04 17:30 | N | N | replacement project | Transformer |  | 779S 701T Replacement project Replace 701T with new assets (701PT and 502T) | For Information Only
ALTALINK | 39s T1 (39s Bickerdike), 39s 240kV Bus 1 (39s Bickerdike), 39s 26 (39s Bickerdike), 39s 33 (39s Bickerdike) | 2022-01-08 07:00 | 2022-01-09 18:00 | N | Y |  | Transformer, Bus, Circuit Breaker |  | URGENT Replace to 39s25 switch, Like for like | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock) | 2022-01-09 20:17 | 2022-01-10 17:36 | N | Y | forced outage | Line |  |  | 500 kV
EPCOR | M723 (Meadowlark) | 2022-01-10 07:00 | 2022-01-10 17:00 | N | N | P&C RAS scheme cut over and op-checks | Circuit Breaker |  |  | For Information Only
ALTALINK | 745L (39s Bickerdike - 745AL tap) | 2022-01-10 07:00 | 2022-01-12 12:00 | N | N | installing transmission line foundations for new 345s Hornbeck (P1460) | Line | Check with OPTRA closer to the project (V.Chan). 7/15/2021 | Installing transmission line foundations for the new 345s Hornbeck substation. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 657s T1 (657s Summerside) | 2022-01-10 07:00 | 2022-01-11 17:00 | N | Y | removal of 240 kV bus work for SU2405 bay installation for south east expansion project creating open point | Transformer |  | Removal of 240 kV bus work for SU2405 bay installation for South East Expansion Project. Tx1 to be energized from SU2404 breaker during the restoration of this outage with 240 kV bus removed from SUDS2 to SUAB1 for the duration on SU2405 bay installation. Physical bus separation from SUDS2 to SUAB1 to remain upon Tx1 restoration. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 657s SUDS2 (657s Summerside) | 2022-01-10 07:00 | 2022-04-01 06:59 | N | Y | temporary open point between SUDS2 and Summerside T1 | Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 7.84L (ENMAX 7 - ENMAX 36), 7.1TR (ENMAX 7) | 2022-01-10 08:00 | 2022-01-11 18:00 | N | N | maintenance | Line, Transformer |  | HV SW Maint. SW84, SW85, SW86, SW87, MD-7.1TR | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 9L05 (809s Louise Creek - 813s Little Smoky) | 2022-01-10 08:00 | 2022-02-06 17:00 | N | Y | Louise Creek rebuild project wiring for 904/905BF relays, CT ratio changes, relay programming and functionality, commission control, alarms and status, blocking procedures for BF and bus protections | Line |  | Louise Creek Rebuild project Wiring for 904/905BF relays. CT ratio changes. Relay programming and functionality. Commission control, alarms and status. Blocking procedures for BF and Bus protections. | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 202L (61s Lodgepole - 202AL tap) | 2022-01-10 12:00 | 2022-01-17 15:00 | N | N | component replacements | Line | Component Replacement's 202L (Str's Range 201-331) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
EPCOR | 657s SU2401 (657s Summerside) | 2022-01-10 17:55 | 2022-01-19 18:00 | N | Y | forced outage | Circuit Breaker | 657s SU2401 (657s Summerside) |  | 240 kV
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2022-01-11 07:00 | 2022-01-14 18:00 | N | Y | replace insulators, tower hardware, and steel members | Line | replace insulators, tower hardware, and steel members on structures 66, 67, 68, 86, 89, and 117 |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32) | 2022-01-11 08:00 | 2022-01-11 16:00 | N | N | investigate 32 sub lattice structure | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1052L (28s West Brooks - 324s Cassils) | 2022-01-11 08:00 | 2022-01-11 17:30 | N | Y | install new corona ring on dead end | Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 433L (291s Cochrane - AML 793s Horse Creek) | 2022-01-11 09:00 | 2022-01-12 18:00 | N | N | switch repair | Line | 291s24 switch not closed properly and needs to be repaired |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 104s T2 (104s Watson Creek) | 2022-01-11 09:30 | 2022-01-11 16:30 | N | N | repair DC ground & replace micro switch | Transformer |  |  | For Information Only
Whitla 2 Wind Generation L.P. | WHT2 Whitla 2 | 2022-01-11 14:00 | 2022-01-11 15:00 | N | N | control system test | Unit |  | We have discovered a communication loss issue with the control system at Whitla 2 Wind Farm that is reoccurring at somewhat patterned intervals of time. The communication loss can result in an unexpected drop of output of the wind farm, not caused by the weather conditions. To support reliable grid conditions, we would like to request taking Whitla 2 Wind Farm off AESO ramp management control at the next predicted occurrences of the communication loss: Jan 11, 2022 from 14:00 to 15:00, and Jan 12, 2022 from 17:00 to 18:00. The AC of the farm will remain unaffected (fully available, 151 MW at time of this email). The turbines will be free to generate based on wind speed during the requested time and will not be subject to AESOs wind ramp management. Personnel will be available on site to respond to any curtailment directives if they are received. AESO will still have complete visibility of telemetry from the site. | For Information Only
EPCOR | 72RG7 (Garneau - Rossdale), RG725 (Rossdale) | 2022-01-12 07:00 | 2022-01-12 17:00 | N | N | Rossdale: P&C RAS scheme cut over and op-checks | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T1 (370s North Lethbridge) | 2022-01-12 07:15 | 2022-01-18 17:45 | N | N | complete secondary U/G cabling, install tie breaker, reconfigure Bus 1 | Transformer |  |  | For Information Only, Restricts Generation
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7), 7.2TR (ENMAX 7), 7B138-7BT3 (ENMAX 7) | 2022-01-12 08:00 | 2022-01-13 18:00 | N | Y | HV SW Maint. SW81, SW82, SW83, SW88, MD-7.2TR | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 32B138-32BT5 (ENMAX 32), 32.2TR (ENMAX 32) | 2022-01-12 08:00 | 2022-01-12 16:00 | N | N | investigate 32sub lattice structure | Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2022-01-12 11:00 | 2022-01-12 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
Whitla 2 Wind Generation L.P. | WHT2 Whitla 2 | 2022-01-12 17:00 | 2022-01-12 18:00 | N | N | control system test | Unit |  | We have discovered a communication loss issue with the control system at Whitla 2 Wind Farm that is reoccurring at somewhat patterned intervals of time. The communication loss can result in an unexpected drop of output of the wind farm, not caused by the weather conditions. To support reliable grid conditions, we would like to request taking Whitla 2 Wind Farm off AESO ramp management control at the next predicted occurrences of the communication loss: Jan 11, 2022 from 14:00 to 15:00, and Jan 12, 2022 from 17:00 to 18:00. The AC of the farm will remain unaffected (fully available, 151 MW at time of this email). The turbines will be free to generate based on wind speed during the requested time and will not be subject to AESOs wind ramp management. Personnel will be available on site to respond to any curtailment directives if they are received. AESO will still have complete visibility of telemetry from the site. | For Information Only
ENMAX | 2B138-D95 (ENMAX 2) | 2022-01-13 08:00 | 2022-01-13 16:00 | N | N | relay, lockout testing | Circuit Breaker |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32) | 2022-01-13 08:00 | 2022-01-13 16:00 | N | N | investigate 32sub lattice structure | Line, Transformer |  |  | Pre-Condition
ENMAX | 31.1C (ENMAX 31) | 2022-01-13 08:00 | 2022-01-13 16:00 | N | N | SF6 gas top up | Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2022-01-13 09:00 | 2022-01-13 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 41B138-40.81 (ENMAX 41) | 2022-01-14 08:00 | 2022-01-14 11:00 | N | N | 41 sub 138 kV DFR upgrade | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 41.1C (ENMAX 41) | 2022-01-14 08:00 | 2022-01-14 16:00 | N | N | 41 Sub 138 kV DFR upgrade | Shunts |  |  | Pre-Condition
ENMAX | 41B138-41BT3 (ENMAX 41) | 2022-01-14 11:00 | 2022-01-14 16:00 | N | N | 41 sub 138 kV DFR upgrade | Circuit Breaker |  |  | For Information Only
ENMAX | 21.4TR (ENMAX 21) | 2022-01-15 08:00 | 2022-01-15 16:00 | N | N | SF6 top up | Transformer |  | SF6 top up 21B69-21.4TR Low Density Alarm. 21 SUB, 21MD138-21.4TR failed cabinet heater | For Information Only
EPCOR | 72VN21 (EP 511s Victoria - Namao) | 2022-01-17 07:00 | 2022-01-21 15:15 | N | N | VN21 pole transfer | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s T2 (657s Summerside), 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside) | 2022-01-17 07:00 | 2022-01-19 17:00 | N | Y | south east expansion project: 240 kV bus removed between SUDS2 and SUAB1 for SU2405 breaker bay | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2022-01-17 07:15 | 2022-01-30 17:45 | N | N | scope of work includes rebuilding a section of 113L from structure 1 to 96 | Line |  |  | Pre-Condition, Affects Cranking Path
ENMAX | 2B138-D81 (ENMAX 2) | 2022-01-17 08:00 | 2022-01-17 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D81 Breaker Fail Protection. Breaker fail on 2B138-D81. 2B138-D81 reclosing to be turned off while testing is progress. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 37.81L (ENMAX 37 - ENMAX 38) | 2022-01-17 08:00 | 2022-01-19 16:00 | N | N | emergency pole replacement on str 5 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (ENMAX 32 - ENMAX 40), 40.1TR (ENMAX 40) | 2022-01-17 08:00 | 2022-01-18 18:00 | N | N | HV SW maintenance SW84, SW85, SW86, MD-40.1TR | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 37.2TR (ENMAX 37) | 2022-01-17 08:00 | 2022-01-17 16:00 | N | N | oil sampling TC | Transformer |  |  | For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2022-01-17 08:30 | 2022-01-20 12:00 | N | N | reconfigure T1 NGR and remove T2 NGR | Transformer |  | Customer outage to reconfigure T1 NGR from 50ohm to 200ohm and complete relay testing @ 133s. T2 NGR to be removed. RSLD 1 to be implemented at the end of the outage. | For Information Only
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-01-17 09:00 | 2022-01-24 12:00 | N | N | changing arms and pole repairs | Line |  | Changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ENMAX | 8.3TR (ENMAX 8) | 2022-01-18 08:00 | 2022-01-18 16:00 | N | N | 8.3TR low oil top up | Transformer |  |  | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2022-01-18 08:00 | 2022-01-19 16:00 | N | N | rack in new replacement breakers into cells | Transformer |  |  | For Information Only
ENMAX | 2B138-D96 (ENMAX 2) | 2022-01-18 08:00 | 2022-01-18 16:00 | N | N | relay, lockout testing, breaker fail protection | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain) | 2022-01-18 09:00 | 2022-01-26 12:00 | N | Y | changing poles under mitigation and test and treat | Line |  | Changing Poles under Mitigation and Test and Treat | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane) | 2022-01-18 09:00 | 2022-01-18 15:00 | N | N | high load move between structures #44 & 45 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354S Summerview | 2022-01-18 10:00 | 2022-01-18 14:00 | N | N | control software update | Station |  |  | Affects Visibility, Restricts Generation
ALTALINK | 294s T1 (294s Brazeau Outlet Works) | 2022-01-18 10:00 | 2022-01-18 17:30 | N | N | investigative testing on T1 | Transformer |  | Investigative testing on T1 as there is a major concern with this transformer, a sharp increase in arcing gases is an indication of something going on inside the transformer. | For Information Only
AESO-SC | OATI | 2022-01-18 18:00 | 2022-01-18 19:00 | N | N | Inter-Site transfer business continuity drill | SCInternal |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40), 40.81L (ENMAX 40 - ENMAX 41) | 2022-01-19 08:00 | 2022-01-20 18:00 | N | N | high volt switch maintenance | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 924L (102s Langdon - 356s Milo) | 2022-01-19 08:00 | 2022-01-23 18:00 | N | Y | component replacements for 924L | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 10.1TR (ENMAX 10) | 2022-01-19 08:00 | 2022-01-19 12:00 | N | N | temp diff alarm MT and LTC, oil top up | Transformer |  | 10.1Tr Temp diff alarm - MT and LTC. Oil top up | For Information Only
ALTALINK | 21s T1 (21s Marion) | 2022-01-19 08:00 | 2022-01-21 17:30 | N | N | create open points to isolate customer from transmission system | Transformer | 21s T1 (21s Marion) |  | For Information Only
ENMAX | 2B138-D83 (ENMAX 2) | 2022-01-19 08:00 | 2022-01-19 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D83 Breaker Fail Protection. Breaker fail on 2B138-D83. 2B138-D83 reclosing to be turned off while testing is progress. | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 368S Burdett | 2022-01-19 10:00 | 2022-01-20 13:00 | N | N | BRD1 T4 oil processing | Station |  | Jan 19th - Open 89M-M1-2, Open, ground and lock 89-F2 - Close 89M-M1-2, site capacity 6.3 MW , reactive capability 3.78 MVAr - Perform work  Oil processing Jan 20th - Complete work - Open 89M-M1-2, Remove lock and close 89-F2 - Close 89M-M1-2, site capacity 10.5 MW , reactive capability 7.56 MVAr Work complete -100% availability for generation | Restricts Generation
ENMAX | 10.2TR (ENMAX 10) | 2022-01-19 12:00 | 2022-01-19 16:00 | N | N | 10.2TR low oil top up | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 708L (71s Lamoureux - 708AL Tap) | 2022-01-20 07:00 | 2022-01-21 18:00 | N | N | urgent repair on structures 46 and 47 involving cross arm replacement | Line |  | GOI required for completion of Urgent Repair on structures 46 and 47 involving cross arm replacement. | Over/Under Voltage, Overload, Pre-Condition,Affects Cranking Path
ENMAX | 2B138-D84 (ENMAX 2) | 2022-01-20 08:00 | 2022-01-20 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D84 Breaker Fail Protection. Breaker fail on 2B138-D84. 2B138-D84 reclosing to be turned off while testing is progress. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2022-01-20 08:00 | 2022-01-22 17:00 | N | Y | install new structures and equipment in the existing line and remove conductor between new 973L2 and 1135L3 (P2032) | Line |  | Install new 973L Str 2 in the existing line. Install new 1135L3 in the existing 973L line. Install conductor between new Str 2 and 1C to connect 973L in the new alignment. Remove conductor between new 973L2 and 1135L3. (P2032) | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2022-01-21 07:00 | 2022-01-21 18:00 | N | N | maintenance on structures 112 and 113 | Line |  | Scope of work includes maintenance on structures on 112 and 113 | Pre-Condition
EPCOR | 657s T2 (657s Summerside), 657s SU2402 (657s Summerside) | 2022-01-21 07:30 | 2022-01-21 18:00 | N | Y | emergency PRD repair | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2B138-D85 (ENMAX 2) | 2022-01-21 08:00 | 2022-01-21 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D85 Breaker Fail Protection. Breaker fail on 2B138-D85. 2B138-D85 reclosing to be turned off while testing is progress. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 410s 1152 (410s Josephburg) | 2022-01-21 17:56 | 2022-01-25 18:00 | N | N | forced | Circuit Breaker
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2022-01-22 07:00 | 2022-01-22 18:00 | N | Y | maintenance on structure 48 | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 974L (39s Bickerdike - 310p Sundance) | 2022-01-23 08:00 | 2022-01-25 17:00 | N | Y | install new structures and equipment in the existing line and remove conductor between new 974L2 and 1084L3 (P2032) | Line |  | Install new 974L Str 2 in the existing line. Install new 1084L Str 3 in the existing 974L line. Install conductor between new 974L Str 2 and 1C to connect 974L in the new alignment. Remove conductor between new 974L2 and 1084L3. (P2032) | 240 kV, Over/Under Voltage, Pre-Condition
EPCOR | T1 (Garneau) | 2022-01-24 07:00 | 2022-06-16 22:00 | N | N | provide clearances for Tx1 replacement | Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 803s L2403 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s T3 (EP 803s Lambton) | 2022-01-24 07:00 | 2022-01-28 17:00 | N | Y | Lambton LDS5 LCR | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.3TR (ENMAX 14) | 2022-01-24 08:00 | 2022-01-24 16:00 | N | N | 14 sub 138kV DFR upgrade | Transformer |  | 14 Sub 138kV DFR Upgrade. Close open close required on MD on return to service for commissioning purposes. | For Information Only
ENMAX | 34.2TR (ENMAX 34), 16.60L (ENMAX 16 - ENMAX 34) | 2022-01-24 08:00 | 2022-01-25 18:00 | N | N | maintenance on SW66, SW65, SW64, MD-34.2TR and SW64 | Transformer, Line |  | HV SW Maint. SW66, SW65, SW64, MD-34.2TR. SW64 at 34 sub -4 water sheds need to be replaced. Check Reversing Switch 34.2 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap) | 2022-01-24 08:00 | 2022-01-27 17:00 | N | Y | reroute transmission line around water | Line |  | GOI 7L129D3 to 526S Buffalo Creek Reroute Transmission Line around water | Firm Load Loss, Overload, Pre-Condition
ALTALINK | 14s 739E (14s Devon), 739L (14s Devon - 155s Blackmud) | 2022-01-24 13:30 | 2022-01-24 17:30 | N | N | test recloser functions after line protection settings changes | Circuit Breaker, Line |  | GOI on breaker 14s739E to test recloser functions after line protection settings changes as per Sys Ops requests. No physical work on the breaker so grounds are not required. Reclosers to stay enabled for testing purposes. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 789L (898s Heart Lake - 789BL tap) | 2022-01-25 07:00 | 2022-01-27 18:00 | N | Y | includes maintenance on structure 78 | Line |  | Scope of work includes maintenance on structure 78 | For Information Only
ALTALINK | 370s T1 (370s North Lethbridge) | 2022-01-25 07:15 | 2022-01-31 17:45 | N | N | complete final install of 370s452, 370s5, reconductoring of bus#1 | Transformer |  | Final Outage on T1 and Bus 1 to complete final install of 370s452, 370s5, Reconductoring of Bus#1. Closing Open Point G | For Information Only, Restricts Generation
ALTALINK | 64s T3 (64s East Crossfield) | 2022-01-25 07:30 | 2022-01-26 18:00 | N | N | cleanup in the control cabinet and potential control cable jacket repair | Transformer |  | Job Scope: Mice infestation cleanup in the TX control cabinet, potential control cable jacket repair | For Information Only
ENMAX | 2B138-D88 (ENMAX 2) | 2022-01-25 08:00 | 2022-01-25 16:00 | N | N | relay lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D88 Breaker Fail Protection. Breaker fail on 2B138-D88. 2B138-D88 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.1TR (ENMAX 14) | 2022-01-25 08:00 | 2022-01-25 16:00 | N | N | 138kV DFR upgrade | Transformer |  | 14 Sub 138kV DFR Upgrade. Close open close required on MD on return to service for commissioning purposes. | For Information Only
ATCO | 930s SVC (930s Arcenciel), 930s 711 (930s Arcenciel), 930s 712 (930s Arcenciel), 930s 701T (930s Arcenciel), 930s 144kV 700BS5 (930s Arcenciel) | 2022-01-25 08:00 | 2022-01-26 14:00 | N | Y | replace recalled RXTP test switches on 700BS5 protection circuits | Shunts, Circuit Breaker, Transformer, Bus |  | Replace recalled RXTP Test Switches on 700BS5 Protection Circuits - 930S SVC unavailable | Pre-Condition, Prevents Normal Events
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 17s 717W (17s Benalto) | 2022-01-25 08:30 | 2022-01-25 17:30 | N | N | install step up transformer for heaters | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Prevents Normal Events
ALTALINK | 39s 29 (39s Bickerdike) | 2022-01-26 07:00 | 2022-01-29 18:00 | N | Y | install A frame for future 974L and 1168L | Circuit Breaker |  | Install A frame for future 974L and 1168L | 240 kV, Contingency Requires Mitigation
ALTALINK | 202L (61s Lodgepole - 202AL tap) | 2022-01-26 07:00 | 2022-01-30 18:00 | N | N | component replacement | Line |  | Component Replacement's 202L (Str's Range 201-331) | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 14.4TR (ENMAX 14) | 2022-01-26 08:00 | 2022-01-26 16:00 | N | N | 14 Sub 138 kV DFR upgrade | Transformer |  | 14 Sub 138kV DFR Upgrade. Close open close required on MD on return to service for commissioning purposes. | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 34.1TR (ENMAX 34), 21B69-21.61 (ENMAX 21), 34B69-21.61 (ENMAX 34) | 2022-01-26 08:00 | 2022-01-27 18:00 | N | N | HV switch maintenance, check reversing switch | Line, Transformer, Circuit Breaker |  | HV SW Maint. SW61, SW62, SW63, MD-34.1TR. 34MD69-34.1TR - north whip not seated - adjustment needed. Check Reversing Switch 34.1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2B138-D89 (ENMAX 2) | 2022-01-26 08:00 | 2022-01-26 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D89 Breaker Fail Protection. Breaker fail on 2B138-D89. 2B138-D89 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 275s 2 (275s Jenner) | 2022-01-26 10:00 | 2022-01-26 15:00 | N | Y | urgent outage to replace heaters | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe) | 2022-01-27 07:45 | 2022-01-27 16:15 | N | Y | de-energize 777L due to the PLC being out of service | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage, Pre-Condition
ENMAX | 2B138-D90 (ENMAX 2) | 2022-01-27 08:00 | 2022-01-27 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D90 Breaker Fail Protection. Breaker fail on 2B138-D90. 2B138-D90 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 150L (42s Sarcee - 150AL tap) | 2022-01-27 08:00 | 2022-01-30 17:00 | N | N | 150L line move project | Line |  | 150L line move project. 150L176 and 176A Structure to be moved to accommodate road widening. | For Information Only, Pre-Condition
ENMAX | 14.2TR (ENMAX 14) | 2022-01-27 08:00 | 2022-01-27 16:00 | N | N | 138kV DFR upgrade | Transformer |  | 14 Sub 138kV DFR Upgrade. Close open close required on MD on return to service for commissioning purposes. | For Information Only
ALTALINK | 968L (138s Windy Flats - 370s North Lethbridge) | 2022-01-28 07:00 | 2022-01-28 18:00 | N | Y | urgent outage for clearance check | Line |  |  | 240 kV, Overload, Pre-Condition
EPCOR | 657s T1 (657s Summerside) | 2022-01-28 07:00 | 2022-01-28 18:00 | N | N | emergency repair | Transformer |  |  | 240 kV
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-01-28 07:00 | 2022-02-08 18:00 | N | N | phase 3 rebuild, structures 539 to 691 | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 779s 701T (779s Chinchaga River) | 2022-01-28 08:00 | 2022-02-04 16:00 | N | N | transformer replacement (capital maintenance) ISD Feb 4, 2022 | Transformer
ALTALINK | 33s 2 (33s Spray) | 2022-01-29 07:15 | 2022-01-30 17:45 | N | Y | stringing new conductor on 113L. GOI required due to limits of approach violation | Circuit Breaker |  | Scope of work includes stringing new conductor on 113L from 33s Spray to Structure 2. GOI required due to limits of approach violation & cannot be done under reclosing. | Restricts Generation
ALTALINK | 76L (33s Spray - 115s Mt. Allan) | 2022-01-29 07:15 | 2022-01-30 17:45 | N | N | stringing new conductor on 113L. GOI required due to limits of approach violation | Line |  | Scope of work includes stringing new conductor on 113L from 33s Spray to Structure 2. GOI required due to limits of approach violation & cannot be done under reclosing. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
Syncrude | D05 79 (D05 D05), D05 LCF (D05) | 2022-01-30 08:00 | 2022-02-11 20:00 | N | N | lower camp feeder outage | Circuit Breaker, Transformer |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper) | 2022-01-31 07:00 | 2022-02-04 17:00 | N | Y | Jasper protection upgrade cutovers | Transformer |  |  | 240 kV, For Information Only
EPCOR | PM2402 (Poundmaker), PM2403 (Poundmaker) | 2022-01-31 07:00 | 2022-03-11 17:00 | N | Y | WETUP project (P1649) - tie in of new Tx4 | Circuit Breaker |  | Continuation of 240 kV ring re-configuration for WETUP project. (P1649) Outage will provide isolation for tie in of new Tx4. | 240 kV, Contingency Requires Mitigation
EPCOR | 805s J2401 (805s Jasper) | 2022-01-31 07:00 | 2022-01-31 17:00 | N | Y | Jasper P&C RAS cut over and op-checks | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 814s T1 (814s Bellamy), 814s B2401 (814s Bellamy), 814s B2407 (814s Bellamy) | 2022-01-31 07:00 | 2022-02-04 17:00 | N | Y | maintenance | Transformer, Circuit Breaker |  | Bellamy 240kV SF6 Maintenance | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8), 3.3TR (ENMAX 3) | 2022-01-31 08:00 | 2022-02-01 18:00 | N | N | switch maintenace | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 15.1TR (ENMAX 15) | 2022-01-31 08:00 | 2022-01-31 16:00 | N | N | take measurements of secondary cabinet for PT install | Transformer |  | Take measurements of secondary cabinet for PT install | For Information Only
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain) | 2022-01-31 09:00 | 2022-02-07 12:11 | N | Y | changing poles under mitigation and test | Line |  | Changing Poles under Mitigation and Test and treat | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-01-31 09:00 | 2022-02-07 12:00 | N | N | changing arms and pole repairs | Line |  | Changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ENMAX | 31.1C (ENMAX 31) | 2022-01-31 10:00 | 2022-02-15 16:00 | N | N | fencing replacement | Shunts |  | 31 Sub Fencing Replacement | For Information Only, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2022-01-31 12:30 | 2022-01-31 15:30 | N | Y | investigate small leak at PST | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 520s 552 (520s Benett), 1201L (520s Bennett - BCH Cranbrook) | 2022-01-31 12:30 | 2022-01-31 15:30 | Y | Y | urgent high priority work. 520s552 gas sampling to confirm SF6 concentrations | Circuit Breaker, Line |  |  | 500 kV, Limits ATC, Pre-Condition, Affects Cranking Path
EPCOR | 805s J2407 (805s Jasper) | 2022-02-01 07:00 | 2022-02-01 17:00 | N | Y | cut over P&C RAS scheme and op-checks | Circuit Breaker |  | cut over P&C RAS scheme and Op-Checks | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 368S Burdett | 2022-02-01 07:30 | 2022-02-02 12:00 | N | N | BRD1 T4 oil processing | Station |  | Feb 1 - Open 89M-M1-2, Open, ground and lock 89-F2 - Close 89M-M1-2, site capacity 6.3 MW , reactive capability 3.78 MVAr - Perform work  Oil processing Feb 2 - Complete work - Open 89M-M1-2, Remove lock and close 89-F2 - Close 89M-M1-2, site capacity 10.5 MW , reactive capability 7.56 MVAr Work complete -100% availability for generation | Restricts Generation
ALTALINK | 1018s RTU/SCADA (1018s Shamrock) | 2022-02-01 08:00 | 2022-02-04 13:00 | N | N | capacitor bank and RTU outages | Terminal Equipment |  | 1. Will require momentary RTU outages from Feb 1st to 4th to upload new logic, this may impact the MW setpoint setting to the AESO momentarily. 2. A Protection outage to the Capacitor Bank for Shamrock 2 SEL 487V for testing and addition of a discharge timer - Feb 1st to 4th | Affects Visibility
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2022-02-01 09:00 | 2022-02-03 17:00 | Y | Y | tree removals around Natal Substation, Sparwood | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge) | 2022-02-01 10:00 | 2022-02-02 17:30 | N | N | completion of U/G termination from 370s84 to bus 4 on bus 4 side of cable, and close open point F | Transformer |  | Completion of U/G termination from 370s84 to Bus 4 on Bus 4 Side of Cable, Close Open Point "F" | For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa) | 2022-02-02 07:00 | 2022-02-05 15:00 | N | N | installing foundation for future monopole dead end for future T-Tap on 215L to new 309s Anthony Henday (P1442) | Line | 215L (38s East Edmonton - 286s Yasa) | Installing foundation for future monopole dead end for future T-Tap on 215L to new 309s Anthony Henday. | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.84L (ENMAX 3 - ENMAX 13), 3.4TR (ENMAX 3) | 2022-02-02 08:00 | 2022-02-03 18:00 | N | N | HV SW maintenance SW84, SW85, SW86, MD-3.4TR | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.2TR (ENMAX 21) | 2022-02-02 08:00 | 2022-02-02 16:00 | N | N | maintenance | Transformer |  | DC ground on 21.2TR conserv. Oil Level Gauge | For Information Only
ALTALINK | 1018s Shamrock | 2022-02-02 10:00 | 2022-02-02 15:00 | N | N | complete testing on the capacitor for WHT2 with the new Logic addition | Station |  | Complete testing on the capacitor for Shamrock 2 February 2nd with the new Logic addition - testing involves the following " Simulate Cap Bank out-of-service " If current plant conditions are >120MWs, then the plant should be constrained to 120MWs " If current plant conditions are <120MWs, we will need the AESO to send a MW setpoint of >120MWs to verify that the RTU constrains the MW Setpoint value it sends to the PPC to 120MWs. | Restricts Generation
ALTALINK | 62s 11 (62s Brazeau) | 2022-02-02 23:00 | 2022-02-03 03:00 | N | N | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2022-02-03 03:00 | 2022-02-03 07:00 | N | Y | maintenance | Switch |  | brushgear | 240 kV, Restricts Generation
EPCOR | PMDS13 (Poundmaker), PM721 (Poundmaker), T4 (Poundmaker), PMDS14 (Poundmaker) | 2022-02-04 08:00 | 2022-02-18 16:00 | N | N | P1649 Garneau Upgrade. ISD Feb 11, 2022 | Switch, Circuit Breaker, Transformer
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2022-02-04 11:00 | 2022-02-04 15:00 | Y | Y | line outage required for the repair and testing of NIC 5CB25 POW Controller | Line |  |  | Limits ATC, 500 kV
ALTALINK | 415s 185W (415s Drywood), 185L (379s Shell Canada Waterton - 415s Drywood) | 2022-02-06 07:15 | 2022-02-06 17:45 | N | N | urgent repair - replace structure 134 due to wind damage | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Meadowlark) | 2022-02-07 07:00 | 2022-02-11 17:00 | N | N | provide clearance for 72PM25 stringing | Transformer |  |  | For Information Only
EPCOR | 805s T4 (805s Jasper) | 2022-02-07 07:00 | 2022-02-10 17:00 | N | Y | Jasper protection upgrade cutovers | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2022-02-07 07:00 | 2022-02-15 18:00 | N | Y | completion of damper replacement CRU scope between structures 243 & 299 | Line |  | GOI required for completion of Damper Replacement CRU scope between Structures 243 & 299. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2022-02-07 07:15 | 2022-02-27 17:45 | N | N | rebuild a section of 113L from structure 1 to 96 | Line |  | Scope of work includes rebuilding a section of 113L from structure 1 to 96 | Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 10.1TR (ENMAX 10), 832L (ENMAX 10 - ENMAX 12) | 2022-02-07 08:00 | 2022-02-08 18:00 | N | Y | HV SW maintenance SW81, SW82, SW83, MD-10.1TR | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 8.2TR (ENMAX 8) | 2022-02-07 08:00 | 2022-02-11 16:00 | N | N | 8 sub 25kV feeder and bus protections. replacement | Transformer |  | 8 Sub 25kV Feeder & Bus Prot. Replacement. Check Reversing Switch | For Information Only
ALTALINK | 410s 552 (410s Josephburg), 410s 1152 (410s Josephburg), 706L (410s Josephburg - 706AL tap) | 2022-02-07 09:30 | 2022-02-10 18:00 | N | N | migration of alarms, status and control of breakers 410s552 and 410s1152 | Circuit Breaker, Line |  | Migration of alarms, status and control of breakers 410s552 and 410s1152. Migration of control and status of MOD 410s706X. Functioning of these devices will be required. Migration of alarms, metering and controls to protections L3/A87/21 and L3/B87/21. Migration and function testing of CVT11 Alarms. | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2022-02-07 11:45 | 2022-02-07 18:15 | N | Y | open 887L for 266s MPLS upgrade | Line | WebOMS: 11319538 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
KP | PMB1 Keyera West Pembina Gas Turbine | 2022-02-07 12:00 | 2022-02-09 18:00 | N | N | due to 202L (61s - 202AL tap) work | Unit
ALTALINK | 202L (61s Lodgepole - 202AL tap) | 2022-02-07 12:00 | 2022-02-09 18:00 | N | N | component replacement's 202L (str's range 201-331) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 745L (39s Bickerdike - 745AL tap) | 2022-02-08 07:00 | 2022-02-10 18:00 | N | N | installing transmission line foundations for the new 345s Hornbeck substation | Line |  | Installing transmission line foundations for the new 345s Hornbeck substation | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
WFML | WWD1 Weldwood 20MW Steam Turb. | 2022-02-08 07:00 | 2022-02-10 18:00 | N | N | due to 745L (39s - 745AL tap) work | Unit
ENMAX, ALTALINK | 918L (281s Johnson - ENMAX 162) | 2022-02-08 07:15 | 2022-02-09 17:45 | N | Y | fire mitigation | Line |  | fire mitigation (Str 797, 810, 813, 818, 825, 835) | 240 kV, For Information Only, Affects Cranking Path
ENMAX | 14B138-14.83 (ENMAX 14), 14.83L (ENMAX 14 - ENMAX 36) | 2022-02-08 08:00 | 2022-02-08 16:00 | N | N | DFR upgrade | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2022-02-08 09:00 | 2022-02-09 17:00 | N | Y | CBK 2D23 hotspot repair | Line | 2L113 (B1s Natal - B2s Cranbrook), CBK 2B5 OOS | Logging beside power lines 42-01 to 44-01 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Pre-Condition
AESO-SC | OATI | 2022-02-08 18:00 | 2022-02-08 22:00 | N | N | network maintenance on interconnections between OATIs datacenters | SCInternal |  | OATI will be performing network maintenance on Tuesday February 08, on the datacenter interconnections between OATIs datacenters. Due to high availability configuration, there will be no impact unless contingencies occur. The event window is scheduled from 6:00PM to 10:00PM (MS). If contingencies do occur, please ensure that NSI in WIT is aligned with NSI in EMS and if a mismatch does occur enable back-scheduler prior to start of the ramp and proceed with SCP 302 1.10.3. | For Information Only
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2022-02-09 08:00 | 2022-02-10 15:00 | N | N | repair disconnect switch | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2022-02-09 08:00 | 2022-02-09 16:00 | N | N | 14 sub 138 kV DFR upgrade | Shunts |  |  | For Information Only, Pre-Condition
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10), 10.2TR (ENMAX 10), 10B138-693 (ENMAX 10) | 2022-02-09 08:00 | 2022-02-10 18:00 | N | Y | HV switch maintenance | Line, Transformer, Circuit Breaker |  | HV SW Maint. SW84, SW85, SW86, MD-10.2TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 927L (102s Langdon - 356s Milo), 102s 6552 (102s Langdon), 102s 6652 (102s Langdon), 356s 552 (356s Milo), 356s 652 (356s Milo) | 2022-02-09 09:00 | 2022-02-16 18:00 | N | Y | component replacements for 927L (str' 1A-302) and updates | Line, Circuit Breaker |  | (1) Component replacements for 927L (Str' 1A-302). D/C 924L. (2) RAS changes; re 991s capacity increase | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 275s 2 (275s Jenner) | 2022-02-09 10:00 | 2022-02-09 15:00 | N | N | urgent - replace heaters | Circuit Breaker |  | urgent outage to replace heaters | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 202L (178s Cynthia - 202AL tap) | 2022-02-10 07:00 | 2022-02-10 12:00 | N | N | live line work to create open point 'A' | Line |  | Live line work to create Open Point 'A' between structures 202L372A and 202L178S Westside South Bay IN. Reclosers to be blocked on 202L (178s - 61s). | For Information Only, Affects Cranking Path
TRANSALTA, ALTALINK | 59s T1 (59s Peigan), 616L (59s Peigan - 616AL tap), 159s 138kV Bus 1 (159s Colinton) | 2022-02-10 07:30 | 2022-02-10 16:30 | N | Y | repair PT oil level glass | Transformer, Line, Bus |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Overload, Pre-Condition
ALTALINK | 339s T1 (339s Duchess) | 2022-02-10 07:45 | 2022-02-10 17:45 | N | N | urgent repair | Transformer |  | Urgent repair on burnt 339s T1 TX CT block. Techs require protection outages to investigate burnt CT wiring in the TX Cabinet. T1 A Protections T1 B Protections | For Information Only
ENMAX | 9.2TR (ENMAX 9) | 2022-02-10 08:00 | 2022-02-10 16:00 | N | N | secondary cabinet internal investigation for Reg PT install design | Transformer |  | 9.2TR Secondary Cabinet internal investigation for Reg PT install design | For Information Only
ALTALINK | 202L (178s Cynthia - 202AL tap) | 2022-02-10 11:30 | 2022-02-11 13:30 | N | N | component replacement | Line |  | Component Replacement's 202L (Str 202L178S Westside South Bay IN) | For Information Only, Affects Cranking Path
ALTALINK | 245s T1 (245s Seebe) | 2022-02-10 15:00 | 2022-02-12 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper) | 2022-02-11 07:00 | 2022-02-11 17:00 | N | Y | arc flash protection installation | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 202L (178s Cynthia - 202AL tap) | 2022-02-11 13:00 | 2022-02-11 18:00 | N | N | live line work to close open point 'A' | Line |  | Live line work to close Open Point 'A' between structures 202L372A and 202L178S Westside South Bay IN. Reclosers to be blocked on 202L (178s - 61s). | For Information Only, Affects Cranking Path
ALPAC | 282S Grassland (Alpac) | 2022-02-12 09:00 | 2022-02-12 17:00 | N | N | phone system and internet maintenance | Station |  |  | Affects Reserves, Prevents Normal Events
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 26.1TR (ENMAX 26) | 2022-02-14 08:00 | 2022-02-15 18:00 | N | N | maintainence | Line, Transformer |  | HV SW Maint. SW86, SW85, SW84, MD-26.1TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.4TR (ENMAX 8) | 2022-02-14 08:00 | 2022-02-18 16:00 | N | N | 8 Sub 25 kV feeder & bus protection replacement | Transformer |  | 8 Sub 25kV Feeder & Bus Prot. Replacement | For Information Only
ENMAX | 2B138-D93 (ENMAX 2) | 2022-02-14 08:00 | 2022-02-14 16:00 | N | N | relay lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D93 Breaker Fail Protection. Breaker fail on 2B138-D93. 2B138-D93 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain) | 2022-02-14 09:00 | 2022-02-23 14:00 | N | Y | changing poles under mitigation and test | Line |  | Changing Poles under Mitigation and Test N treat | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 410s 652 (410s Josephburg), 410s 752 (410s Josephburg), 807L (410s Josephburg - 807AL tap) | 2022-02-14 09:30 | 2022-02-17 18:00 | N | N | migration of alarms, status and control of breakers | Circuit Breaker, Line | Migration of alarms, status and control of breakers 410s752 and 410s652. Migration of control and status of MOD 410s807 (will toggle status as MOD is part of GOI). Functioning of these devices will be required. Migration of alarms, metering and controls to protections L7/A87/21 and L7/B87/21. Migration and function testing of CVT8 Alarms |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2022-02-14 13:00 | 2022-02-17 16:00 | N | N | crossarm and pole replacement. | Line |  | crossarm and pole replacement. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-02-14 13:00 | 2022-02-21 12:00 | N | N | changing arms and pole repairs | Line |  | Changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ENMAX | 2B138-D94 (ENMAX 2) | 2022-02-15 08:00 | 2022-02-15 16:00 | N | N | relay testing | Circuit Breaker |  | Relay, Lockout Testing. D94 Breaker Fail Protection. Breaker fail on 2B138-D94. 2B138-D94 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 830L (562s Cypress - 840s McNeill Station), 840S McNeill Station | 2022-02-15 09:00 | 2022-02-15 16:30 | Y | Y | urgent rewire of RAS logic | Line, Station |  | Urgent rewire of RAS logic on the following relays - No redundancy, therefore GOI required on element 830L A81_RAS/L18 BE181O/U2 830L A32R_RAS/L18 BE132 830L A32_RAS/L18 BE132 | Limits ATC, Pre-Condition
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2022-02-16 07:00 | 2022-03-01 18:00 | N | Y | complete damper replacement CRU scope between structures 243 & 299 | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 33s 3 (33s Spray) | 2022-02-16 08:00 | 2022-02-17 17:00 | N | Y | minor maintenance | Switch |  |  | Restricts Generation
ENMAX | 31.1C (ENMAX 31) | 2022-02-16 08:00 | 2022-02-16 16:00 | N | N | emergency: neutral imbalance alarm | Shunts |  |  | For Information Only, Pre-Condition
ENMAX | 2B138-D86 (ENMAX 2) | 2022-02-16 08:00 | 2022-02-16 16:00 | N | N | relay, lockout testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.83L (ENMAX 26 - ENMAX 65), 26.2TR (ENMAX 26), 26B138-26BT3 (ENMAX 26) | 2022-02-16 08:00 | 2022-02-17 18:00 | N | N | HV SW Maint. SW83, SW82, SW81, MD-26.2TR | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-02-17 07:00 | 2022-02-28 18:00 | N | N | phase 3 rebuild, structures 539 to 691 | Line |  | Outage required for 174L Phase 3 Rebuild, Structures 539 to 691 | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 2B138-D95 (ENMAX 2) | 2022-02-17 08:00 | 2022-02-17 16:00 | N | N | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D95 Breaker Fail Protection. Breaker fail on 2B138-D95. Altalink Capbank CB 752 close will be blocked while this device is tripped. 2B138-D95 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 309s T1 (309s Anthony Henday) | 2022-02-19 07:00 | 2022-02-23 14:30 | N | N | complete measuring, termination and testing of secondary feeder cables off of 26.5 kV Bus 1 | Transformer |  | TMPL contractor to complete measuring, termination and testing of secondary feeder cables off of 26.5kV Bus 1. | For Information Only
SUNCOR | 29EDD-94 29-952-9701 (29EDD-94 Voyageur) | 2022-02-21 08:00 | 2022-03-05 18:00 | N | Y | maintenance and testing | Circuit Breaker |  | 46778041 29EDD94;29-952-9701 MAIN & TEST;PM & PRC-023 PL9-16 setting changes | 240 kV, Contingency Requires Mitigation
ALTALINK | 254s T2 (254s Coaldale), 254s 25kV Bus 2 (254s Coaldale) | 2022-02-22 07:00 | 2022-02-28 17:45 | N | N | install and test 25 kV equipment | Transformer, Bus |  | Install and test the single-phase VT on 414L. Replace, test and commission 414L Feeder relay. Replace, test and commission T2 B Relay. Confirm all SCADA integrations and Test to ACC. Install and test 25kV feeder cable from Fortis. | For Information Only, Restricts Generation
EPCOR | 816s T2 (816s Petrolia) | 2022-02-22 07:00 | 2022-03-04 17:00 | N | Y | tap changer repair | Transformer |  | Petrolia TX2 Tap Changer Repair (Reinhausen Contractors) | 240 kV, For Information Only
Syncrude | Mildred T16 (Syncrude Mildred Lake) | 2022-02-22 08:00 | 2022-03-06 20:00 | N | N | breaker 1635 will be operated | Transformer |  | Non-Significant Outage: T16 Transformer 72/13.8kV) @ Plant 31 Substation Following breaker will be operated: 1635 @ Plant 31 Substation | For Information Only
ENMAX | 2B138-D87 (ENMAX 2) | 2022-02-22 08:00 | 2022-02-22 16:00 | N | N | relay lockout testing | Circuit Breaker | Relay, Lockout Testing. D87 Breaker Fail Protection. Breaker fail on 2B138-D87. 2B138-D87 reclosing to be turned off while testing is progress. |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 41.84L (ENMAX 41 - ENMAX 54), 54.81L (ENMAX 54 - ENMAX 65), 54.1TR (ENMAX 54) | 2022-02-22 08:00 | 2022-02-25 18:00 | N | N | high volt switch maintenance | Line, Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 410s 852 (410s Josephburg), 410s 952 (410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2022-02-22 08:00 | 2022-02-24 18:00 | N | N | migration of controls and alarms of breakers and disconnects | Line, Circuit Breaker | 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | Migration of alarms, status and control of breakers 410s852 and 410s952. Migration of control and status of MOD 410s776E. Functioning of these devices will be required. Migration of alarms, metering and controls to protections L5/A21 and L5/B21. Migration and function testing of CVT9 Alarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 135s 20 (135s Conrad) | 2022-02-22 08:30 | 2022-02-22 15:30 | N | N | installation of wildlife cover | Circuit Breaker |  | Installation of wildlife cover on 135s37 PT primary and primary riser. | For Information Only
ALTALINK | 65s 434(65s Highriver), 434L (65s High River - 237s Foothills) | 2022-02-22 10:30 | 2022-02-22 17:30 | N | N | replacing tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 2049s 721 (2049s Kettle River), 2049s 721C (2049s Kettle River) | 2022-02-22 12:00 | 2022-02-22 14:00 | N | N | trip coil testing | Switch, Shunts |  | PRC-005 - TRIP COIL TESTING - BREAKER 2049S 721 | Pre-Condition
ALTALINK | 702L (137s Sedgewick - 757s Battle River) | 2022-02-22 12:00 | 2022-02-22 18:00 | N | Y | fire mitigation on structures #113, 116 & 117 | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Restricts Generation
GENT | BHL1 Bellshill | 2022-02-22 12:00 | 2022-02-22 18:00 | N | N | AltaLink fire mitigation on 702L | Unit
ATCO | 2049s 722C (2049s Kettle River), 2049s 722 (2049s Kettle River) | 2022-02-22 14:00 | 2022-02-22 16:00 | N | N | trip coil testing | Shunts, Switch |  | PRC-005 - TRIP COIL TESTING - BREAKER 2049S 722 | Pre-Condition
GENT | BHL1 Bellshill | 2022-02-23 07:00 | 2022-02-25 18:00 | N | N | AltaLink fire mitigation on 702L | Unit
ALTALINK | 702L (137s Sedgewick - 377s Hardisty) | 2022-02-23 07:00 | 2022-02-25 18:00 | N | N | fire mitigation on structures #210 - 456 | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 2B138-D91 (ENMAX 2) | 2022-02-23 08:00 | 2022-02-23 16:00 | N | N | relay lockout testing | Circuit Breaker |  | Relay, Lockout Testing. D91 Breaker Fail Protection. Breaker fail on 2B138-D91. 2B138-D91 reclosing to be turned off while testing is is progress. | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 159s T2 (159s Colinton) | 2022-02-23 09:00 | 2022-02-23 18:00 | N | N | secure 159s63 underground cable, fix some loose bird cover | Transformer |  | Secure 159s63 u/g cable fix, some loose bird cover. 159s63 is currently OOS the cable is loose and not secured properly, it is leaning against the structure. | For Information Only
ATCO | 2049s 902 (2049s Kettle River) | 2022-02-23 10:00 | 2022-02-23 13:00 | N | Y | PRC-005 - trip coil testing breaker 902-A, B, C | Circuit Breaker |  | 5512731 PRC-005 - TRIP COIL TESTING - BREAKER 902-A @ 2049S 5517972 PRC-005 - TRIP COIL TESTING - BREAKER 902-B @ 2049S 5512761 PRC-005 - TRIP COIL TESTING - BREAKER 902-C @ 2049S | 240 kV, Contingency Requires Mitigation
ATCO | 2049s 903 (2049s Kettle River) | 2022-02-23 13:00 | 2022-02-23 16:00 | N | Y | PRC-005 - trip coil testing on breaker 903-A, B, C | Circuit Breaker |  | 5517280 PRC-005 - TRIP COIL TESTING - BREAKER 903-A @ 2049S 5518490 PRC-005 - TRIP COIL TESTING - BREAKER 903-B @ 2049S 5512776 PRC-005 - TRIP COIL TESTING - BREAKER 903-C @ 2049S | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2022-02-24 07:00 | 2022-02-27 18:00 | N | Y | maintenance on structures 310p, 1 ,21, 22, 23, 24, 25, 26, 55, 57, 74, 75, 80, 89, 90, 91, 102, 110, 111, 120 and 121 | Line |  | Scope of work includes maintenance on structures 310p, 1 ,21, 22, 23, 24, 25, 26, 55, 57, 74, 75, 80, 89, 90, 91, 102, 110, 111, 120 and 121 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 309s T2 (309s Anthony Henday) | 2022-02-24 07:00 | 2022-02-28 14:30 | N | N | complete measuring, termination and testing of secondary feeder cables off of 26.5 kV Bus 2 | Transformer |  |  | For Information Only
ALTALINK | 310p 240kV Bus B (310p Sundance) | 2022-02-24 07:00 | 2022-02-24 18:00 | N | Y | replace insulators on structures 310P and 1 on 1046L | Bus |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 276s 652 (276s Un Carb Prentiss), 276s C1 (276s Prentiss) | 2022-02-24 08:30 | 2022-02-24 17:30 | N | N | tank heater replacement | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 2049s 905 (2049s Kettle River) | 2022-02-24 10:00 | 2022-02-24 13:00 | N | Y | PRC-005 - trip coil testing breaker 905-A, B, C | Circuit Breaker |  | 5512746 PRC-005 - TRIP COIL TESTING - BREAKER 905-A @ 2049S 5518415 PRC-005 - TRIP COIL TESTING - BREAKER 905-B @ 2049S 5514807 PRC-005 - TRIP COIL TESTING - BREAKER 905-C @ 2049S | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 1.6TR (ENMAX 1) | 2022-02-24 12:45 | 2022-02-28 15:00 | N | N | emergency work | Transformer |  | 1.6TR has been taken out of service due to malfunction on the deluge system and risk of flashover. | For Information Only
ATCO | 2049s 906 (2049s Kettle River) | 2022-02-24 13:00 | 2022-02-24 16:00 | N | Y | PRC-005 - trip coil testing on breaker 906-A, B, C | Circuit Breaker |  | 5518505 PRC-005 - TRIP COIL TESTING - BREAKER 906-A @ 2049S 5512791 PRC-005 - TRIP COIL TESTING - BREAKER 906-B @ 2049S 5512855 PRC-005 - TRIP COIL TESTING - BREAKER 906-C @ 2049S | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 41.2TR (ENMAX 41) | 2022-02-25 08:00 | 2022-02-25 16:00 | N | N | breaker measurements | Transformer |  | Breakers Measurements for Siemens Allis | For Information Only
ENMAX | 21.1C (ENMAX 21), 21B138-21.CAP (ENMAX 21) | 2022-02-25 08:00 | 2022-02-25 16:00 | N | N | relay, lockout testing, 21.1CAP-86 | Shunts, Circuit Breaker |  | Relay, Lockout Testing. 21.1CAP-86 | Pre-Condition
EPCOR | 72PM25 (Poundmaker - Meadowlark), M725 (Meadowlark), M726 (Meadowlark), MDS11 (Meadowlark), MDS12 (Meadowlark) | 2022-02-25 08:00 | 2022-04-15 16:00 | N | N | P1649 Garneau upgrade. ISD April 8, 2022 | Line, Circuit Breaker, Switch
ENMAX | 1.81L (ENMAX 1 - ENMAX 20), 1.80L (ENMAX 1 - ENMAX 28) | 2022-02-27 08:00 | 2022-02-27 11:00 | N | N | manhole inspections | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.82L (ENMAX 1 - ENMAX 5), 1.84L (ENMAX 1 - ENMAX 5) | 2022-02-27 11:00 | 2022-02-27 14:00 | N | N | manhole inspections | Line |  |  | Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8), 1.85L (ENMAX 1 - ENMAX 8) | 2022-02-27 14:00 | 2022-02-27 18:00 | N | N | manhole inspections | Line |  |  | Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark) | 2022-02-28 07:00 | 2022-04-01 17:00 | N | N | P1649 - 72 kV re-configuration for 72PM25 line addition | Line | 72MG16 (Garneau - Meadowlark) | Meadowlark S/S 72 kV Re-Configuration for 72PM25 line addition | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2022-02-28 07:30 | 2022-03-01 17:30 | N | Y | installing bird divertors | Line | Scope of work includes installing bird divertors on the OHSW on structures 36, 37, 38, 39, 40 and 41. See also 1046L Recloser block SAP: 277117 required due to proximity to 902L |  | 240 kV, Pre-Condition
ATCO | 2029s 1200SST2 (2029s Heathfield) | 2022-02-28 08:00 | 2022-03-03 15:20 | N | N | investigate and repair in LV2 | Transformer |  | Breaker 10NA02-Q03 Investigate & Repair in LV2. Low voltage isolations will occur in the 480 V rooms (in addition to using 502VRA). Alarms will occur when switching out the LV room, as the circuits change over from 1 source to the other. 500 kV breakers on transformer primary will be opened for a few moments while opening 502VRA. | For Information Only
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2022-02-28 08:00 | 2022-02-28 11:30 | N | N | high load move | Line |  | late request for a high load move on 658L (562s-649s) for tomorrow (Monday Feb 27 2022). The line needs to be deenergized between 8am-11:30am tomorrow morning. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B240-D130 (ENMAX 65) | 2022-02-28 08:00 | 2022-02-28 16:00 | N | Y | relay lockout testing | Circuit Breaker | Relay, Lockout Testing. 65-BF D130-86. 65B240-D130 sync check, reclosing and breaker fail scheme disabled while BM-21 offline. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2022-02-28 08:00 | 2022-03-01 18:00 | N | N | switch maintenance | Line, Transformer |  | HV SW Maint. SW81, SW82, SW83, 23MD138-23.3TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-02-28 09:00 | 2022-03-07 12:00 | N | N | changing arms and pole repairs | Line |  | changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ATCO | 9L939 (77s Sagitawah - 809s Louise Creek), 809s 905 (809s Louise Creek), 809s 906 (809s Louise Creek) | 2022-02-28 09:00 | 2022-03-27 17:00 | N | Y | Louise Creek rebuild project: relay wiring and programming, CT ratio changes | Line, Circuit Breaker |  | Louise Creek Rebuild project Wiring for 905/906BF relays. CT ratio changes. Relay programming. Commission control, alarms and status. Blocking procedures for BF and Bus protections. | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
Saskpower | SaskPower A1R | 2022-02-28 09:00 | 2022-03-05 18:00 | N | Y | planned outage | Line |  |  | Limits ATC, Pre-Condition
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive) | 2022-02-28 10:00 | 2022-03-03 12:00 | N | N | changing pole structure | Line |  | Changing pole structure 98 and stringing shield wire Part of 742S freeman lake decommissioning | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 960s 901 (960s Birchwood Creek) | 2022-02-28 12:00 | 2022-02-28 14:00 | N | Y | PRC-005 - trip coil testing on breaker 901-A, B, C | Circuit Breaker |  | 5518002 PRC-005 - TRIP COIL TESTING - BREAKER 901-A @ 960S 5518430 PRC-005 - TRIP COIL TESTING - BREAKER 901-B @ 960S 5518180 PRC-005 - TRIP COIL TESTING - BREAKER 901-C @ 960S | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 702L (137s Sedgewick - 377s Hardisty) | 2022-02-28 12:00 | 2022-03-04 18:00 | N | N | fire mitigation on structures #210 - 456 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 786s 702 (786s High Level) | 2022-02-28 12:00 | 2022-03-07 17:30 | N | N | 7L76 line protection upgrade - new panel 7P2 | Circuit Breaker |  | 7L76 Line Protection Upgrade - New Panel 7P2 . 7L59D5 will be closed, relay setting changes required at 789S Keg River | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
GENT | BHL1 Bellshill | 2022-02-28 12:00 | 2022-03-04 18:00 | N | N | AltaLink fire mitigation on 702L | Unit
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10) | 2022-02-28 12:30 | 2022-02-28 17:30 | N | Y | breaker outage on 42s693 breaker to add in wiring for trip coil monitoring | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 960s 902 (960s Birchwood Creek) | 2022-02-28 14:00 | 2022-02-28 16:00 | N | Y | PRC-005 - trip coil testing on breaker 902-A, B, C | Circuit Breaker |  | 5518535 PRC-005 - TRIP COIL TESTING - BREAKER 902-A @ 960S 5516239 PRC-005 - TRIP COIL TESTING - BREAKER 902-B @ 960S 5518445 PRC-005 - TRIP COIL TESTING - BREAKER 902-C @ 960S | 240 kV, Pre-Condition
ALTALINK | 99s T1 (99s North St. Albert) | 2022-03-01 07:00 | 2022-03-15 18:00 | N | N | trip testing from new T1 A and T1 B protections, upgrade protections and relocate modules | Transformer |  | trip testing from new T1 A and T1 B protections; add slip on CT to T1; upgrade 99s2024, 99s2030N, & 99s278E protections; relocate 99s3 ,99s2, & PT2 modules; replace 99s278E | For Information Only
ALTALINK | 745L (39s Bickerdike - 745AL tap) | 2022-03-01 07:00 | 2022-03-05 19:00 | N | N | cut OPGW and splice in new OPGW going in/out of new Hornbeck substation at 745L77 & 745L78 | Line |  | modify 745L78, replace 745L77, add T-Tap structure between 745L77 & 745L78 and install temporary bypass, cut OPGW and splice in new OPGW going in/out of new Hornbeck substation at 745L77 & 745L78 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 254s T1 (254s Coaldale) | 2022-03-01 07:00 | 2022-03-01 17:00 | N | Y | trip test 254s407N, 254s411X, 254s443X breakers from new T2 B protection | Transformer |  |  | Restricts Generation
ENMAX | 11.83L (ENMAX 162 - ENMAX 11) | 2022-03-01 08:00 | 2022-03-01 16:00 | N | N | urgent removal of plastic debris in line | Line |  |  | Overload, Pre-Condition
ATCO | 936s 701 (936s Norberg) | 2022-03-01 08:00 | 2022-03-01 16:00 | N | N | emergency investigation of low gas | Circuit Breaker |  |  | Firm Load Loss, Pre-Condition
ENMAX | 65B240-D131 (ENMAX 65) | 2022-03-01 08:00 | 2022-03-01 16:00 | N | Y | relay lockout testing | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D131-86. 65B240-D131 sync check, reclosing and breaker fail scheme disabled while BM-22 offline. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | AML 511s SVC Plus (AML 511s Crossings) | 2022-03-01 08:00 | 2022-03-02 16:00 | N | Y | VCS expansion tank leak repair | Shunts |  |  | 240 kV, Pre-Condition
ATCO | 7L92 (777s Vilna - 819s Whitby Lake), 819s 701 (819s Whitby Lake) | 2022-03-01 10:00 | 2022-03-03 17:00 | N | N | PRC-005 - microprocessor and aux trip relay testing; replace RTXP switches | Line, Circuit Breaker |  | 5517892 PRC-005 - MICROPROCESSOR RELAY TESTING - 21B-79/7L92 @ 819S 5507727 PRC-005 - MICROPROCESSOR RELAY TESTING - 21A/7L92 @ 819S 5505571 PRC-005 - AUX TRIP RELAY TESTING - 94L2-2/7L92 @ 819S 5518640 PRC-005 - TRIP COIL TESTING - BREAKER 702 @ 819S Plus replace RTXP switches | Over/Under Voltage, Pre-Condition
ATCO | 960s 905 (960s Birchwood Creek) | 2022-03-01 10:00 | 2022-03-01 13:00 | N | Y | PRC-005 - trip coil testing | Circuit Breaker |  | 5518520 PRC-005 - TRIP COIL TESTING - BREAKER 905-A @ 960S 5516254 PRC-005 - TRIP COIL TESTING - BREAKER 905-B @ 960S 5517418 PRC-005 - TRIP COIL TESTING - BREAKER 905-C @ 960S | 240 kV, Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo) | 2022-03-01 12:00 | 2022-03-11 18:00 | N | Y | component replacements for 927L (Str' 1A-302): D/C 924L | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO | 960s 906 (960s Birchwood Creek) | 2022-03-01 13:00 | 2022-03-01 16:00 | N | Y | PRC-005 - trip coil testing | Circuit Breaker |  | 5517987 PRC-005 - TRIP COIL TESTING - BREAKER 906-A @ 960S 5514822 PRC-005 - TRIP COIL TESTING - BREAKER 906-B @ 960S 5512870 PRC-005 - TRIP COIL TESTING - BREAKER 906-C @ 960S | 240 kV, Pre-Condition
ENMAX | 65B240-D132 (ENMAX 65) | 2022-03-02 08:00 | 2022-03-02 16:00 | N | Y | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D132-86. 65B240-D132 sync check, reclosing and breaker fail scheme disabled while BM-23 offline. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 23MD138-23.4TR (ENMAX 23), 23.80L (74s Janet - ENMAX 23) | 2022-03-02 08:00 | 2022-03-04 18:00 | N | Y | maintenance on SW84, SW88, SW87, MD-23.4TR | Switch, Line |  | HV SW Maint. SW84, SW88, SW87, MD-23.4TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BHE Canada | Marias South Series Capacitor | 2022-03-02 09:00 | 2022-03-02 11:00 | N | Y | urgent testing for imbalance issue | Shunts |  |  | 240 kV, Limits ATC
ATCO | 960s 908 (960s Birchwood Creek) | 2022-03-02 10:00 | 2022-03-02 13:00 | N | Y | trip coil testing PRC-005 | Circuit Breaker |  | 5518195 PRC-005 - TRIP COIL TESTING - BREAKER 908-B @ 960S 5512885 PRC-005 - TRIP COIL TESTING - BREAKER 908-A @ 960S 5518210 PRC-005 - TRIP COIL TESTING - BREAKER 908-C @ 960S | 240 kV, Pre-Condition
BHE Canada | Hay Lake North Series Capacitor | 2022-03-02 11:00 | 2022-03-02 15:00 | N | Y | urgent testing for imbalance issue | Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 250p 11 (250p Bighorn Plant), 250P 1 (250P Bighorn Plant) | 2022-03-02 11:00 | 2022-03-02 15:00 | N | Y | maintenance | Switch, Circuit Breaker |  |  | Restricts Generation
BHE Canada | Marias South Series Capacitor | 2022-03-02 13:00 | 2022-03-02 15:00 | N | Y | urgent testing for imbalance issue | Shunts |  |  | 240 kV, Limits ATC
ATCO | 960s 909 (960s Birchwood Creek) | 2022-03-02 13:00 | 2022-03-02 16:00 | N | Y | trip coil testing PRC-005 | Circuit Breaker |  | 5516224 PRC-005 - TRIP COIL TESTING - BREAKER 909-A @ 960S 5518225 PRC-005 - TRIP COIL TESTING - BREAKER 909-C @ 960S 5512900 PRC-005 - TRIP COIL TESTING - BREAKER 909-B @ 960S | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 2L294 (A.A. Lambert - Cranbrook) | 2022-03-02 17:00 | 2022-03-04 17:00 | N | Y | inspection of CBK 2D24 and the removal of 2GD24 | Line |  |  | Limits ATC, Pre-Condition
ENMAX | 65B240-D133 (ENMAX 65) | 2022-03-03 08:00 | 2022-03-03 16:00 | N | Y | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D133-86. 65B240-D133 sync check, reclosing and breaker fail scheme disabled while BM-24 offline. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO, ALTALINK | 819s 702 (819s Whitby Lake), 7L794 (157s Lac La Biche - 819s Whitby Lake) | 2022-03-03 09:00 | 2022-03-04 14:00 | N | Y |  | Circuit Breaker, Line |  | 5517917 PRC-005 - MICROPROCESSOR RELAY TESTING - 67N-21B-79/7L794 @ 819S 5505809 PRC-005 - MICROPROCESSOR RELAY TESTING - 21A/7L794 @ 819S 5511787 PRC-005 - AUX TRIP RELAY TESTING - 94L2-2/7L794 @ 819S 5518640 PRC-005 - TRIP COIL TESTING - BREAKER 702 @ 819S Plus replace RTXP switches | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant), 250P 2 (250P Bighorn Plant) | 2022-03-03 09:00 | 2022-03-03 13:00 | N | Y | maintenance | Switch, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 814L (28s West Brooks - 121s Brooks), 121s 814W (121s Brooks) | 2022-03-03 09:30 | 2022-03-03 16:30 | N | N | breaker operation and maintenance | Line, Circuit Breaker |  | 1st Trip and maintenance if required | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 65B138-D85 (ENMAX 65) | 2022-03-04 08:00 | 2022-03-04 16:00 | N | N | relay, lockout testing, 65B138-D85 sync check | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D135-85. 65B138-D85 sync check, reclosing and breaker fail scheme disabled while BM-06 offline. | Contingency Requires Mitigation, Pre-Condition
ATCO | 819s 704 (819s Whitby Lake), 7L139 (819s Whitby Lake - 7LA139 tap) | 2022-03-04 14:00 | 2022-03-04 16:00 | N | N | 5517220 PRC-005 - trip coil testing- breaker 704 at 819s | Circuit Breaker, Line |  | 5517220 PRC-005 - TRIP COIL TESTING - BREAKER 704 @ 819S | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 345s T1 (345s Hornbeck) | 2022-03-05 19:00 | 2022-06-21 07:00 | N | N | transitioning from a CI to GOI | Transformer |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2022-03-06 05:37 | 2022-04-15 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib) | 2022-03-06 08:00 | 2022-03-06 17:00 | N | N | replace structure 126 on 7L71 due to failed test and treat | Line | 7L71 (718s Parsons Creek - 2082s Dog Rib) | Replace structure 126 on 7L71 due to failed test and treat. | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-94 29-952-9706 (29EDD-94 Voyageur) | 2022-03-06 08:00 | 2022-03-13 18:00 | N | Y | PRC-023 PL9-17 setting changes | Circuit Breaker | 46778046 29EDD94;29-952-9706 MAIN & TEST;PM & PRC-023 PL9-17 setting changes |  | 240 kV, Contingency Requires Mitigation
EPCOR | 657s T1 (657s Summerside), 657s SU2401 (657s Summerside), 657s SU2404 (657s Summerside) | 2022-03-07 07:00 | 2022-04-07 08:00 | N | Y | continuation of 240 kV ring re-configuration for P2133 | Transformer, Circuit Breaker |  | Summerside S/S Tx1 bay outage Continuation of 240 kV ring re-configuration for South East Expansion Project. (P2133) Tx1 bay to be isolated for 240 kV bus re-configuration and installation of SU2405, SUDS11 and CVT's. Upon restoration Tx1 to be energized from SU2404 and a new isolation point of SUDS11 disconnect to remain open. | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | T3 (EPCOR Hardisty), 72CH9 (987s Clover Bar - EPCOR Hardisty) | 2022-03-07 07:00 | 2022-03-11 17:00 | N | N | TX3 zone op-checks and P&C maintenance | Transformer, Line | TX3 Zone @ Hardisty Hardisty TX3 Zone Op-Checks, P&C Maintenance |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2022-03-07 07:00 | 2022-03-09 18:00 | N | N | 9 sub TRV mitigation and pile installation | Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | EP 511s Victoria T4 (EP 511s Victoria) | 2022-03-07 07:00 | 2022-03-08 17:00 | N | N | tap changer maintenance | Transformer | TX4 @ Victoria E511S Victoria TX4 Tap Changer Maintenance |  | For Information Only
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2022-03-07 07:00 | 2022-04-03 17:00 | N | N | 72JW19 termination rebuild on Jasper side | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2022-03-07 07:15 | 2022-03-10 16:20 | N | N | maintenance on structures 78-80, 86 | Line |  | Maintenance (Str 78-80, 86). Fortis to remove underbuild | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTAGAS | Lethbridge Burdett (ME03) | 2022-03-07 07:15 | 2022-03-12 14:45 | N | N | AltaLink mitigation on 612L | Unit
ALTALINK | 113L (20s Ghost - 33s Spray) | 2022-03-07 07:15 | 2022-03-27 17:45 | N | N | rebuilding a section of 113L from structure 1 to 96 | Line |  |  | Pre-Condition, Affects Cranking Path
ENMAX | 24.2TR (ENMAX 24), 24.82L (ENMAX 24 - ENMAX 65) | 2022-03-07 08:00 | 2022-03-07 18:00 | N | N | maintenance on SW81 and MD-24.2TR | Transformer, Line |  |  | Pre-Condition
ALTALINK | 102s SVC (102s Langdon), 102s T4 (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon) | 2022-03-07 08:00 | 2022-03-10 17:00 | N | Y | VCS pump swap investigation and motor maintenance. | Shunts, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 65B240-D134 (ENMAX 65) | 2022-03-07 08:00 | 2022-03-07 16:00 | N | Y | relay, lockout testing | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D134-86. 65B240-D134 sync check, reclosing and breaker fail scheme disabled while BM-25 offline. | 240 kV, Contingency Requires Mitigation
ALTALINK | 410s T1 (410s Josephburg), 410s 138kV Bus 1 (410s Josephburg), 410s 240kV Bus 1 (410s Josephburg) | 2022-03-07 09:30 | 2022-03-10 18:00 | N | Y | migration of control, status, alarms, metering and controls to protections | Transformer, Bus |  | Migration of control and status of MODs 410s12 and 410s15. Functioning of these devices will be required. Migration of alarms, metering and controls to protections T1/A87/50/51, T1/B87/50/51, 240B1/A87, 240B1/B87, 138B1/A87, and 138B1/B87. Migration and function testing of CVT3 and VT5 Alarms | 240 kV, Contingency Requires Mitigation
ATCO | 951s SVC (951s Thickwood), 951S 902 (951s Thickwood Hills), 951s 903 (951s Thickwood Hills) | 2022-03-07 10:00 | 2022-03-11 17:30 | N | Y | warranty repairs and annual inspections | Shunts, Circuit Breaker |  | Warranty Repairs, annual inspections | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 846s 701T (846s Grand Centre) | 2022-03-07 10:30 | 2022-03-08 16:30 | N | N | RTXP replacement for transformer protection | Transformer | 846s 701T (846s Grand Centre) | RTXP Replacement for Transformer Protection. | For Information Only
ALTALINK | 1018s RTU/SCADA (1018s Shamrock) | 2022-03-07 10:30 | 2022-03-07 12:30 | N | N | network outage to accommodate the integration of the ADLS LCM | Terminal Equipment |  | Network Outage to Accommodate the Integration of the ADLS LCM. EMOC/CPC will not have remote control to the farm. AESO will not be able to auto-dispatch the farm but will still have visibility of generation, etc. Any dispatches/directives will have to be responded to by on-site personnel. CPC requests that for the duration of this outage, WHT1 be placed on Curtailment Mode 3 to prevent curtailment. | Affects Visibility
ALTALINK | 702L (137s Sedgewick - 377s Hardisty) | 2022-03-07 12:00 | 2022-03-10 15:45 | N | N | fire mitigation on structures #210 - 456 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2022-03-07 12:00 | 2022-03-09 15:30 | N | N | urgent repair arms and damper on structures 728 and 692 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 790s 509 (790s Poplar Hill), 790s 509C (790s Poplar Hill) | 2022-03-07 12:00 | 2022-03-11 17:30 | N | N | 790S 509C cap bank replacement | Circuit Breaker, Shunts |  | 790S 509C Cap bank replacement | For Information Only, Pre-Condition
GENT | BHL1 Bellshill | 2022-03-07 12:00 | 2022-03-11 18:00 | N | N | AltaLink fire mitigation on 702L | Unit
ALTALINK | 69s 723E (69s North Barrhead), 723L (69s North Barrhead - 724L tap) | 2022-03-07 12:00 | 2022-03-10 18:00 | N | N | 69s14 switch and 723L strain insulator replacement | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 24.81L (ENMAX 24 - ENMAX 31), 24.83L (74s Janet - ENMAX 24), 24.1TR (ENMAX 24) | 2022-03-08 08:00 | 2022-03-08 18:00 | N | Y | HV switch maintenance | Line, Transformer |  | HV SW Maint. MD-24.1TR. Check Reversing Switch. 24 Sub Bird Nest Removal. SF6 Gas Sample - 24B138-24.83, 24B138-24.81, SF6 Top Up - 31B138-24.81 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B240-D135 (ENMAX 65) | 2022-03-08 08:00 | 2022-03-08 16:00 | N | Y | relay lockout testing | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D135-86. 65B240-D135 sync check, reclosing and breaker fail scheme disabled while BM-26 offline. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | SDH1 Saddle Hills | 2022-03-08 09:00 | 2022-03-08 17:00 | N | N | due to Clairmont telecom work | Unit
ATCO | MUL1 Mowat | 2022-03-08 09:00 | 2022-03-08 17:00 | N | N | due to Clairmont telecom work | Unit
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2022-03-08 11:00 | 2022-03-08 15:00 | Y | Y | repair and testing of NIC 5CB25 POW controller, BC maintenance does not affect the Alberta ATC | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ENMAX | 65B138-D81 (ENMAX 65) | 2022-03-09 08:00 | 2022-03-09 16:00 | N | N | relay, lockout testing | Circuit Breaker | 65B138-D81 (ENMAX 65) | Relay, Lockout Testing. 65-BF D135-81. 65B138-D81 sync check, reclosing and breaker fail scheme disabled while BM-01 offline. | Contingency Requires Mitigation
ENMAX | 11.81L (ENMAX 11 - ENMAX 13), 11.1TR (ENMAX 11), 11.4TR (ENMAX 11), 13B138-11.81 (ENMAX 13), 11B138-11.81 (ENMAX 11), 11B138-BT5 (ENMAX 11) | 2022-03-09 08:00 | 2022-03-10 18:00 | N | N | HV switch maintenance | Line, Transformer, Circuit Breaker |  | HV SW Maint. SW81, SW82, SW83, SW87, MD-11.4TR, MD-11.1TR | For Information Only, Pre-Condition
FORTIS | BRK2 Brooks Solar DER | 2022-03-09 08:00 | 2022-03-23 15:00 | N | N | P2092 FortisAlberta Brooks 121S DER Solar (257LE), 15 MW ISD Mar 16, 2022 | Unit
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee), 385s 225 (385s Spring Coulee) | 2022-03-09 08:30 | 2022-03-09 16:30 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 846s 702T (846s Grand Centre) | 2022-03-09 09:00 | 2022-03-10 17:30 | N | N | RTXP replacement for transformer protection | Transformer | 846s 702T (846s Grand Centre) | RTXP Replacement for Transformer Protection. | For Information Only, Pre-Condition
ALTALINK | 443L (55s Olds - 214s Innisfail) | 2022-03-10 07:00 | 2022-03-10 18:00 | N | N | urgent outage to repair crossarm & insulation on structure #443L19 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 65B138-D82 (ENMAX 65) | 2022-03-10 08:00 | 2022-03-10 16:00 | N | N | relay, lockout testing 65-BF D135-82 | Circuit Breaker | 65B138-D82 (ENMAX 65) | Relay, Lockout Testing. 65-BF D135-82. 65B138-D82 sync check, reclosing and breaker fail scheme disabled while BM-03 offline. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 1.5TR (ENMAX 1) | 2022-03-10 08:00 | 2022-03-10 16:00 | N | N | maintenance | Transformer |  | Oil Sampling MT, TC. Check Reversing Switch. 1.5TR Oil Leak Repair Follow Up | For Information Only
ALTALINK | 324s 1552 (324s Cassils) | 2022-03-10 11:30 | 2022-03-16 18:00 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV
ATCO | 813s SVC (813s Little Smoky) | 2022-03-10 16:20 | 2022-03-12 18:00 | N | Y | forced outage | Shunts
ALTALINK | 410s 152 (410s Josephburg) | 2022-03-10 17:30 | 2022-03-14 18:00 | N | N | forced outage | Circuit Breaker |  |  | 240 kV
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-03-11 07:00 | 2022-03-17 18:00 | N | N | urgent: multiple conductor repairs | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 99s 747X (99s North St Albert), 747L (99s North St. Albert - 711L tap) | 2022-03-11 07:30 | 2022-03-11 12:30 | N | N | trip testing from new T1 A and T1 B protections | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
FORTIS | BRK1 Brooks Solar DER | 2022-03-11 08:00 | 2022-03-25 16:00 | N | N | P2086 FortisAlberta Brooks 121S DER Solar (83L), 15 MW ISD Mar 18, 2022 | Unit
ENMAX | 65B138-D83 (ENMAX 65) | 2022-03-11 08:00 | 2022-03-11 16:00 | N | N | relay lockout testing | Circuit Breaker | Relay, Lockout Testing. 65-BF D135-83. 65B138-D83 sync check, reclosing and breaker fail scheme disabled while BM-04 offline. |  | Contingency Requires Mitigation
ALTALINK | 99s 712X (99s North St Albert), 712L (99s North St. Albert - 595s Spruce Grove) | 2022-03-11 12:30 | 2022-03-11 17:30 | N | N | trip testing from new T1 A and T1 B protections | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2022-03-12 07:00 | 2022-03-12 18:00 | N | Y | fire mitigation on structure #224 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
VISIONREQ | 354S Summerview, 354s DVAR1 (354s Summerview), 354s DVAR2 (354s Summerview) | 2022-03-13 09:00 | 2022-03-13 13:00 | N | N | additional wiring for FFR project | Station, Shunts |  |  | Restricts Generation
ALTALINK | 418L (20s Ghost - 189L tap) | 2022-03-14 07:15 | 2022-03-14 17:45 | N | N | replace structure 134 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 64s T1 (64s East Crossfield) | 2022-03-14 07:30 | 2022-03-18 17:30 | N | Y | new PT install, new protections, bird cover | Transformer |  | New PT install, new protections, bird cover (solar DER) | For Information Only
ENMAX | 2.3TR (ENMAX 2) | 2022-03-14 08:00 | 2022-03-17 16:00 | N | N | 2.3TR LTC re-pipe inlet & return, oil sampling, check reversing switch | Transformer |  | 2.3TR LTC Re-Pipe inlet & return. Oil Sampling TC, MT. Check Reversing Switch | For Information Only
ENMAX | 65B138-D84 (ENMAX 65) | 2022-03-14 08:00 | 2022-03-14 16:00 | N | N | relay lockout testing | Circuit Breaker |  | Relay, Lockout Testing. 65-BF D135-84. 65B138-D84 sync check, reclosing and breaker fail scheme disabled while BM-05 offline. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 1.6TR (ENMAX 1) | 2022-03-14 08:00 | 2022-03-19 16:00 | N | N | oil sampling, check reversing switch | Transformer |  | Oil Sampling TC, Bushing, MT. Check Reversing Switch | For Information Only
ENMAX | 23.3TR (ENMAX 23) | 2022-03-14 08:00 | 2022-03-14 16:00 | N | N | rack in new replacement breakers into cells | Transformer | 23.3TR (ENMAX 23) |  | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2022-03-14 09:00 | 2022-03-16 17:00 | Y | Y | tree removals 0-01 to 22-01 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-03-14 09:00 | 2022-03-21 12:00 | N | N | changing arms and pole repairs | Line |  | Changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ALTALINK | 410s 240kV Bus 2 (410s Josephburg), 410s 138kV Bus 2 (410s Josephburg), 410s T2 (410s Josephburg) | 2022-03-14 09:30 | 2022-03-18 18:00 | N | Y | migration of control, status, alarms, metering and controls to protections | Bus, Transformer |  | Migration of control and status of MODs 410s14 and 410s16. Functioning of these devices will be required. Migration of alarms, metering and controls to protections T2/A87/50/51, T2/B87/50/51, 240B2/A87, 240B2/B87, 138B2/A87, and 138B2/B87. Migration and function testing of CVT4 and VT6 Alarms | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 9L11 (813s Little Smoky - 834s Wesley Creek) | 2022-03-14 10:00 | 2022-03-21 16:00 | N | Y | pole replacements, test & treat | Line | 9L11 (813s Little Smoky - 834s Wesley Creek) | Pole replacements, Test & Treat | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 2075s ACF11 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell) | 2022-03-14 10:00 | 2022-03-18 17:30 | N | Y | 901T oil work | Shunts |  | 901T Oil Work, redundant Filter in service This outage will reduce EATL dispatch to a maximum of 750 MW. | 240 kV, Pre-Condition
ALTALINK | 28S West Brooks 138kV Bus 2, 827L (28s West Brooks - 121s Brooks), 853L (28s West Brooks - 853AL tap), 28s T2 (28s West Brooks) | 2022-03-14 12:00 | 2022-03-15 18:00 | N | Y | 28s27 hot switch, 28s827L line polymer dead end damage, 28s827E motor mech | Bus, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO, ALTALINK | 7L230 (69s North Barrhead - 7L230 tap), 7L230 (743s Sarah Lake - 7L230 tap) | 2022-03-14 12:00 | 2022-03-18 18:00 | N | Y | maintenance, equipment replacement and protection upgrade | Line |  | 69s16 Switch Replacement. 723L strain insulator replacement. Upgrade 7L230L protection @ 69s. 234s2285 1st trip & maintenance. 234s888 & 234s1 maintenance. Fortis to backfeed 234s station service through 157LOU 1xyz. P&C will require reclosers to be enabled during commissioning of 7L230L protections. | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1206L (12s Heartland - 89s Ellerslie) | 2022-03-14 12:00 | 2022-03-17 18:00 | N | Y | component replacements on 1206L | Line |  |  | 500 kV, Pre-Condition
ALTAGAS | HMT1 AltaGas Harmattan | 2022-03-15 07:00 | 2022-03-18 18:00 | N | N | AltaLink component replacements on 719L | Unit
EPCOR | 72LH8 (EP 803s Lambton - EPCOR Hardisty) | 2022-03-15 07:00 | 2022-04-05 17:00 | N | N | aerial 50st widening, CP rail overpass project | Line |  |  | For Information Only
ALTALINK | 719L (256s Harmattan - 719CL tap) | 2022-03-15 07:00 | 2022-03-18 18:00 | N | N | component replacements structures #8 - 133 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 846s 701 (846s Grand Centre), 7L28 (717s Ethel Lake - 846s Grand Centre) | 2022-03-15 09:00 | 2022-03-15 17:30 | N | Y | replace RTXP for Line protection | Circuit Breaker, Line |  | RTXP Replacement for Line Protection. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2022-03-16 07:00 | 2022-03-18 18:00 | N | Y | urgent repair on structures #128, 172 & 230 | Line | 1035L (244s Bowmanton - 2075s Newell) |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ATCO | 846s 702 (846s Grand Centre), 7L24 (846s Grand Centre - 7LA24 tap) | 2022-03-16 09:00 | 2022-03-16 17:30 | N | Y | RTXP replacement for line protection | Circuit Breaker, Line |  | RTXP Replacement for Line Protection. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 766s 901T (766s Nevis) | 2022-03-16 09:00 | 2022-03-17 16:00 | N | Y | install new 9S4 Nevis RAS panel | Transformer |  | Install new 9S4 Nevis RAS panel. Outage required on 901T for new CT input wiring. | 240 kV, Over/Under Voltage, Overload, Pre-Condition
Travers2SolarLP | TVS1 Travers Solar Phase 2 | 2022-03-17 08:00 | 2022-08-30 16:00 | N | N | P2341 Travers Solar Phase 2. 65 MW. ISD March 24, 2022 | Unit
ALTALINK | 69s T5 (69s North Barrhead) | 2022-03-17 08:00 | 2022-03-17 17:30 | N | N | prove new 94 high speed tripping relay operation for 138kV bus restoration scheme on T5 standalone protection | Transformer |  |  | For Information Only
ALTALINK | 702L (137s Sedgewick - 377s Hardisty) | 2022-03-18 07:00 | 2022-03-19 19:00 | N | N | fire mitigation on structures #210 - 456 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 76L (33s Spray - 115s Mt. Allan), 33s 75 (33s Spray) | 2022-03-18 07:15 | 2022-03-20 17:45 | N | N | stringing new conductor on 113L from 33s Spray to Structure 2 | Line, Switch |  |  | Contingency Requires Mitigation, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 9L912 (63s Red Deer - 766s Nevis), 766s 902 (766s Nevis) | 2022-03-18 09:00 | 2022-03-18 17:00 | N | Y | installation of new RAS relays requires updates to 89b and 52a/b contacts on 9L912D1, 902 | Line, Circuit Breaker |  | Installation of new RAS relays requires updates to 89b and 52a/b contacts on 9L912D1, 902. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
BCH | 2L294 (A.A. Lambert - Cranbrook) | 2022-03-18 09:00 | 2022-03-18 18:00 | N | Y | repair damaged insulators - priority work | Line |  |  | Limits ATC, Pre-Condition
ATCO, ALTALINK | 840S McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2022-03-18 11:19 | 2022-03-20 17:00 | Y | Y | forced outage | Station, Line |  | forced outage due to transformer gas alarm | Limits ATC
NWE, BHE Canada, BHE | Marias South Series Capacitor, North Series Capacitor (BHE Hay Lake) | 2022-03-18 16:30 | 2022-08-16 18:00 | N | Y | repair series capacitor bypass breaker | Shunts |  |  | 240 kV, Limits ATC
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2022-03-19 08:00 | 2022-03-21 20:00 | N | N | accommodate stringing of new conductor for 7L238 new build over existing 6L09 and HWY 9 | Line |  | Outage to isolate 6L09 to accommodate stringing of new conductor for 7L238 new build over existing 6l09 and HWY 9 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.6TR (ENMAX 1) | 2022-03-19 08:00 | 2022-03-19 18:00 | N | N | repair SW25 | Transformer |  |  | For Information Only
ENMAX | 11.82L (ENMAX 11 - ENMAX 14), 11.83L (ENMAX 162 - ENMAX 11), 11.2TR (ENMAX 11), 11.3TR (ENMAX 11) | 2022-03-19 08:00 | 2022-03-20 18:00 | N | N | switch maintenance, check reversing switch, replace junction box and substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALBIAN | 920s 902T (920s Jackpine) | 2022-03-19 10:00 | 2022-03-29 10:00 | N | Y | Albian turnaround | Transformer |  | Build and remove scaffold around 920S 902T (532-TP-9402) NGR and sensing resistor enclosures. 10 year PM on 72kV GIS switchgear in 532-EE-402 Inspection of the 72kV NGR and sensing resistor in the ATCO Yard. We have had some nuisance NGR trips / alarms and we want to inspect, clean and test the NGR and sensing resistor enclosures and wiring. | 240 kV
EPCOR | EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), 72RV6 (EP 511s Victoria - Rossdale) | 2022-03-21 07:00 | 2022-03-22 17:00 | N | N | disconnects repair | Circuit Breaker, Line | VDS8 and VDS10 @ Victoria E511S Victoria VDS8/VDS10 disconnect repair (broken springs) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | T4 (Rossdale) | 2022-03-21 07:00 | 2022-04-08 17:00 | N | N | bushing replacement | Transformer |  |  | For Information Only
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2022-03-21 07:00 | 2022-03-23 18:00 | N | N | 9 sub TRV mitigation and capacitor install | Line | 9.83L (ENMAX 9 - ENMAX 43) | 9 Sub TRV Mitigation. Capacitor install. | Creates Radial Feeds, Firm Load Loss
CMH | MH69s5 MH69-T52 (MH69s5 NE Crescent Height), MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2022-03-21 07:30 | 2022-03-25 12:00 | N | N | replace disconnect switches | Transformer, Line |  | The City of Medicine Hat is planning to replace two (2) 69 kV disconnect switches on Bus 701 in the MH69S-5 NE Crescent Heights substation. The switch numbers are MH69-508 and MH69-509. The MH69- 50L 69 kV transmission line will be opened and isolated at MH69-511 69 kV disconnect switch in this substation but will remain energized from MHS-2 N. Industrial substation. The T-52 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 5S2-M 13.8kV main breaker and MH69-506 69kV disconnect switch. | Creates Radial Feeds, Firm Load Loss
ENMAX | 20B138-1.81 (ENMAX 20), 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20) | 2022-03-21 08:00 | 2022-03-21 12:00 | N | N | spring substation washing | Circuit Breaker, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2022-03-21 08:00 | 2022-03-22 16:00 | N | N | relay, lockout testing | Shunts |  | Relay, Lockout Testing. 14-86-CAP1, 14-86-CAP2 | For Information Only, Pre-Condition
ALTALINK | 719L (256s Harmattan - 719CL tap) | 2022-03-21 09:00 | 2022-03-23 18:00 | N | N | component replacements structures #8 - 133 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 410s 152 (410s Josephburg), 410s 252 (410s Josephburg), 1027L (410s Josephburg - 430s Ursus) | 2022-03-21 09:30 | 2022-03-22 18:00 | N | Y | migration of alarms, status and control of breakers 410s152 and 410s252 | Circuit Breaker, Line |  | Migration of alarms, status and control of breakers 410s152 and 410s252. Migration of control and status of MOD 410s1027. Functioning of these devices will be required. Migration of alarms, metering and controls to protections L1/A21/79 and L1/B21. Migration and function testing of CVT1 Alarms | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 99s T2 (99s North St. Albert) | 2022-03-21 09:30 | 2022-03-31 18:30 | N | N | trip testing from new T2 A and T2 B protections | Transformer |  | Trip testing from new T2 A and T2 B protections. Upgrade 99s2025 & 99s273X protections. Relocate 99s27 ,99s26, 99s30, & PT3 modules. Replace 99s273X. RSLD2 to be implemented at the end of the outage. | For Information Only
ATCO | 800s 501C1 (800s Friedenstal), 800s 501C2 (800s Friedenstal) | 2022-03-21 10:00 | 2022-04-01 17:30 | N | N | cap bank replacement | Shunts |  | Cap Bank Replacement | For Information Only, Pre-Condition
ALTALINK | 149s 604 (149s Nisku), 604L (149s Nisku - 155s Blackmud) | 2022-03-21 10:30 | 2022-03-21 17:30 | N | N | breaker maintenance including 1st trip testing and repair tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 103s 1352 (103s Goose Lake), 103s 1452 (103s Goose Lake), 613L (103s Goose Lake - 396s Pincher Creek) | 2022-03-21 11:00 | 2022-03-21 19:30 | N | Y | 138kV switch maintenance | Circuit Breaker, Line | 613L (103s Goose Lake - 396s Pincher Creek) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 61s 202X (61s Lodgepole), 202L (61s Lodgepole - 62s Brazeau) | 2022-03-21 12:00 | 2022-03-21 15:30 | N | Y | breaker maintenance including 1st trip testing | Circuit Breaker, Line |  | Breaker maintenance including 1st trip testing. | Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 20B138-20.82 (ENMAX 20), 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20) | 2022-03-21 12:00 | 2022-03-21 18:00 | N | N | spring substation washing | Circuit Breaker, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, CHDI | 225s 15 (225s Magrath), CHD-1 (CHD1S Taylor Hydro - 225s Magrath) | 2022-03-21 12:15 | 2022-03-25 17:45 | N | Y | replace A&B line protection | Circuit Breaker, Line |  |  | Restricts Generation
FORTIS | BFD1 Blackfalds | 2022-03-21 12:30 | 2022-03-21 17:00 | N | N | 444L outage (AltaLink procedure) | Unit
ALTALINK | 74s 104 (74s Janet), 74s C3 (74s Janet), 74s C4 (74s Janet) | 2022-03-21 12:30 | 2022-03-21 17:30 | N | Y | standard relay maintenance | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 198s 444 (198s Blackfalds), 444L (198s Blackfalds - 217s North Red Deer) | 2022-03-21 12:30 | 2022-03-21 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 39s 1052 (39s Bickerdike), 39s 1152 (39s Bickerdike) | 2022-03-22 07:00 | 2022-03-29 18:00 | N | Y | install new 39s973 MOS | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 924L (102s Langdon - 356s Milo), 102s 6852 (102s Langdon), 102s 6952 (102s Langdon), 356s 852 (356s Milo), 356s 952 (356s Milo) | 2022-03-22 07:15 | 2022-03-24 17:45 | N | Y | RAS changes; re 991s capacity increase | Line, Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition, Affects Cranking Path
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | 2022-03-22 08:00 | 2022-03-22 18:00 | N | N | spring substation washing; SW82 and other maintenance | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EXPPIPE, ATCO | Youngstown Express, 6L21 (Youngstown Express - 6L09 tap), 6L09 (767s Oyen - 6L21 tap), 6L09 (772s Youngstown - 6L21 tap) | 2022-03-22 08:00 | 2022-03-22 17:00 | N | N | 6L21 pole replacement/ arm replacement/ interphase spacers | Station, Line |  | 6L21 Pole replacement/ Arm replacement/ Interphase spacers. Express PipelineTotal Station Outage | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH, ALTALINK | 1L275 (799s Coleman - Natal), 786L (799s Coleman - BCH Natal) | 2022-03-22 08:30 | 2022-03-25 16:30 | N | Y | install marker balls and replace insulators | Line | 786L (799s Coleman - BCH Natal), 1L275 (799s Coleman - Natal) WebOMS ID: 11504492 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 10 (17s Benalto) | 2022-03-22 08:30 | 2022-03-22 13:00 | N | Y | 1st trip and PRC5 maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 62s 201 (62s Brazeau), 801L (62s Brazeau - 294s Brazeau Outlet Works) | 2022-03-22 08:30 | 2022-03-22 11:30 | N | Y | breaker maintenance including 1st trip testing & replace tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, For Information Only, Pre-Condition
ALTALINK | 103s 994 (103s Goose Lake), 994L (103s Goose Lake - 312s Fidler), 103s 552 (103s Goose Lake), 103s 652 (103s Goose Lake) | 2022-03-22 08:30 | 2022-03-22 17:30 | N | Y | 240kV switch maintenance | Switch, Line, Circuit Breaker | 994L (103s Goose Lake - 312s Fidler) |  | 240 kV, Contingency Requires Mitigation
BCH | 2L294 (A.A. Lambert - Cranbrook) | 2022-03-22 08:30 | 2022-03-24 14:00 | N | Y | FBC outage notification | Line |  |  | Limits ATC, Pre-Condition
ALTALINK | 45s 874 (45s Bretona), 874L (45s Bretona - 522s Cooking Lake) | 2022-03-22 09:00 | 2022-03-22 16:30 | N | N | breaker maintenance including 1st trip testing & repair tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L52 (Custer - Ingledow) | 2022-03-22 09:00 | 2022-03-31 13:00 | N | Y | replace end of life transmission insulators | Line | 5L52 (Custer - Ingledow) | insulator replacement | Limits ATC, 500 kV
ALTALINK | 1206L (12s Heartland - 89s Ellerslie) | 2022-03-22 12:00 | 2022-03-24 18:00 | N | Y | component replacements on 1206L ( structure range 2-193) | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 62s 202 (62s Brazeau), 202L (61s Lodgepole - 62s Brazeau) | 2022-03-22 12:30 | 2022-03-22 15:30 | N | Y | breaker maintenance including 1st trip testing | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 17s 8 (17s Benalto) | 2022-03-22 13:00 | 2022-03-22 17:30 | N | Y | 1st trip and PRC5 maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 103s 552 (103s Goose Lake) | 2022-03-22 14:55 | 2022-04-08 10:27 | N | N | forced outage | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 1120L (108s Amelia - 410s Josephburg) | 2022-03-23 07:00 | 2022-03-24 18:00 | N | Y | migration of alarms, status and control of breakers | Line |  | Migration of alarms, status and control of breakers 410s352 and 410s452. Migration of control and status of MOD 410s1120. Functioning of these devices will be required. Migration of alarms, metering and controls to protections L1/A21 and L1/B21/79. Migration and function testing of CVT2 Alarms | 240 kV, Affects Cranking Path
EPCOR | EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria) | 2022-03-23 07:00 | 2022-03-23 17:00 | N | N | VDS4 disconnect repair (broken spring) | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2022-03-23 08:00 | 2022-03-24 15:00 | N | N | arm and pole replaement | Line |  | GOI required on 6L09 for arm and pole replacement. | Creates Radial Feeds, Firm Load Loss
ATCO | 7L121 (917s Horse River - 7LA121 tap) | 2022-03-23 08:00 | 2022-03-24 17:00 | N | N | create high load corridor | Line |  | Project to permanently raise two sections, one each, of 7L121 and 7LA121 at the 833S Mariana Lake substation to create a high load corridor. Project to permanently raise two sections, one each, of 7L121 and 7LA121 at the 833S Mariana Lake substation to create a high load corridor. 833S complete Substation Outage | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22), 22PT138-32 (ENMAX 22) | 2022-03-23 08:00 | 2022-03-23 18:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment | Spring Substation Washing. 22MD138-22.2TR - North and Center whip not seated properly. Check Reversing Switch (X), (Y)
Saskpower | Sask Power PR901 | 2022-03-23 08:00 | 2022-03-24 17:30 | N | Y | maintenance | Circuit Breaker |  |  | Limits ATC
ALTALINK | 103s 14 (103s Goose Lake), 955L (59s Peigan - 103s Goose Lake) | 2022-03-23 08:30 | 2022-03-23 17:30 | N | Y | 240kV switch maintenance | Switch, Line | 955L (59s Peigan - 103s Goose Lake) |  | Pre-Condition, Restricts Generation
ALTALINK | 276s 774N (276s Un Carb Prentiss), 774L (276s Prentiss - 332s Ellis) | 2022-03-23 08:30 | 2022-03-23 12:29 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 42s C1 (42s Sarcee) | 2022-03-23 09:00 | 2022-03-23 17:30 | N | N | 42s1652 breaker investigation | Shunts | 42s C1 (42s Sarcee) | Techs require a GOI on 42s1652 breaker to investigate the following point on wave contacts as well as the following relays - S50/51/27/59/C1, A87/50/51/59/27/C1 | Pre-Condition
ALTALINK | 410s 1152 (410s Josephburg) | 2022-03-23 09:00 | 2022-03-23 17:00 | N | N | PRC5 maintenance, fix tank heater and investigate SF6 leak | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 276s 16 (276s Un Carb Prentiss) | 2022-03-23 12:30 | 2022-03-23 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2022-03-23 23:00 | 2022-03-24 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2022-03-24 03:00 | 2022-03-24 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2022-03-24 08:00 | 2022-03-24 18:00 | N | N | spring substation washing | Line, Transformer | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 99s 138kV Bus (99s North St. Albert), 712L (99s North St. Albert - 595s Spruce Grove), 99s 19 (99s North St. Albert), 99s T2 (99s North St. Albert) | 2022-03-24 08:00 | 2022-03-24 17:30 | N | N | maintenance on 99s20 | Bus, Line, Switch, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
TRANSALTA | 59s 11 (59s Peigan), 59s 8 (59s Peigan) | 2022-03-24 09:30 | 2022-03-24 14:30 | N | N | switches being changed to N.O. status | Switch |  |  | For Information Only
ALTALINK | 132s RTU/SCADA (132s Ware Junction) | 2022-03-24 09:30 | 2022-03-24 17:00 | N | N | emergency - replace failed LAN switch | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 752L (653s Summit - 752AL tap) | 2022-03-25 07:00 | 2022-03-25 17:45 | N | N | emergency repair structures 90, 97 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32) | 2022-03-25 08:00 | 2022-03-25 18:00 | N | N | spring substation washing | Line, Transformer |  | Spring Substation Washing. 32.3TR Corrective - Secondary Cable Circulating Current Hazard. Check Reversing Switch | For Information Only, Pre-Condition
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2022-03-25 11:00 | 2022-03-25 15:00 | Y | Y | NIC 5CB25 POW controller, , BC maintenance does not affect the Alberta ATC | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 752L (64s East Crossfield - 752AL tap) | 2022-03-26 07:00 | 2022-03-26 17:45 | N | N | emergency conductor repairs on 752L Str 54 and 61 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.1TR (ENMAX 33), 33.2TR (ENMAX 33), 33.84L (ENMAX 33 - ENMAX 43), 33.83L (ENMAX 33 - ENMAX 41) | 2022-03-26 08:00 | 2022-03-26 18:00 | N | N | spring substation washing | Transformer, Line |  | Spring Substation Washing. Backfeed 8kV bus to power station service TR. | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2022-03-28 07:00 | 2022-03-30 14:00 | N | Y | castledowns 920LE bay op-checks, P&C maintenance | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
EPCOR | 805s T3 (805s Jasper) | 2022-03-28 07:00 | 2022-03-28 17:00 | N | Y | arc flash protection removal | Transformer | 805s T3 (805s Jasper) |  | 240 kV
ALTALINK | 65s T2 (65s High River) | 2022-03-28 07:30 | 2022-03-28 12:30 | N | N | adding supervisory control to 65s1 & 65s3 | Transformer |  |  | For Information Only
CMH | MH69s5 MH69-T51 (MH69s5 NE Crescent Height) | 2022-03-28 07:30 | 2022-03-30 09:00 | N | N | PRC-005 testing and tapchanger maintenance | Transformer |  |  | For Information Only
ATCO | 802s 701T (802s Michichi Creek), 7L128 (802s Michichi Creek - 963s Coyote Lake), 7L25 (768s Rowley - 802s Michichi Creek) | 2022-03-28 08:00 | 2022-04-04 17:00 | N | N | tcm upgrades, outdoor cabling, wiring new 703T, bus upgrade south of 700D1, 700D1 replacement, 700PT1 replacement, commissioning and testing | Transformer, Line |  | 802S MICHICHI SUBSTATION TCM UPGRADES Outdoor Cabling Wiring New 703T Bus upgrade south of 700D1 700D1 Replacement 700PT1 Replacement Commissioning and Testing | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2022-03-28 08:00 | 2022-03-28 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-03-28 09:00 | 2022-04-04 12:00 | N | N | changing arms and pole repairs | Line |  | Changing Arms and Pole Repairs | Creates Radial Feeds, Firm Load Loss
ALTALINK | 719L (256s Harmattan - 719CL tap) | 2022-03-28 09:00 | 2022-04-03 17:00 | N | N | component replacements, structures #8 - 133 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO, SHELL | EX1-01L (402s Scotford Expansion - 879s Scotford Upgrader), 402s 452 (402s Scotford Expansion One), 402s 552 (402s Scotford Expansion One), 402s 652 (402s Scotford Expansion One), 402s 701T (402s Scotford Expansion 1) | 2022-03-28 09:00 | 2022-04-08 09:00 | N | N | maintenance, PRC-005 trip coil & relay testing, RTXP replacements, DFR & line differential addition | Line, Circuit Breaker, Transformer |  | 701T Maintenance, breaker maintenance, PRC-005 trip coil & relay testing, RTXP replacements, DFR & line differential addition | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L97 (735s Swan River - 739s Edith Lake), 735s 603 (735s Swan River) | 2022-03-28 10:00 | 2022-04-11 18:00 | N | N | replace breaker 603 | Line, Circuit Breaker |  | Replace Breaker 603 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 42s 80 (42s Sarcee) | 2022-03-28 11:00 | 2022-03-31 17:30 | N | N | 138kV CT replacements | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 370s 47 (370s North Lethbridge), 370s 1252 (370s North Lethbridge), 968L (138s Windy Flats - 370s North Lethbridge) | 2022-03-28 11:15 | 2022-04-07 15:45 | N | Y | 240kV breaker (370s47) replacement | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23), 23.4TR (ENMAX 23) | 2022-03-28 12:00 | 2022-03-28 18:00 | N | Y | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1212L (12s Heartland - 89s Ellerslie) | 2022-03-28 12:00 | 2022-03-31 18:00 | N | Y | component replacements on 1212L ( structure range 20-194) | Line |  |  | 500 kV
ALTALINK | 65s T3 (65s High River) | 2022-03-28 12:30 | 2022-03-28 17:30 | N | N | adding supervisory control to 65s46 & 65s54 | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 535s 6452 (535s Joffre) | 2022-03-28 12:30 | 2022-03-28 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2022-03-28 17:00 | 2022-03-29 06:00 | N | N | high load move | Line |  |  | For Information Only
ALTALINK | 631L (186s Dry Creek - 199s East Airdrie), 199s 631 (199s East Airdrie), 199s T1 (199s East Airdrie) | 2022-03-29 07:00 | 2022-04-05 17:00 | N | N | switch and insulator replacement | Line, Circuit Breaker, Transformer | 631L (186s Dry Creek - 199s East Airdrie) | 138kV Switch Replacement (199s3, 199s17). Strain insulator replacement | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 668L (394s Empress - 562s Cypress), 394s 138kV Bus 2 (394s Empress), 394s T4 (394s Empress), 394s T2 (394s Empress), 562s 1352 (562s Cypress), 562s 1452 (562s Cypress) | 2022-03-29 07:00 | 2022-04-18 12:00 | N | N | relocate P&C to new building | Line, Bus, Transformer, Circuit Breaker |  | Relocate P&C to new building including, T2 and T4 A&B Protections T4 Metering, VR2 Trip Modules, 394s32 Airbreak Modules, 852 and 952 Breaker Fail Modules, PT3 and PT8 Distribution Modules and Modify PT3 Structure | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 394s T4 (394s Empress) | 2022-03-29 07:00 | 2022-03-29 18:00 | N | N | creating open point 'A' | Transformer |  | Creating Open Point 'A' | For Information Only
EPCOR | 805s T4 (805s Jasper) | 2022-03-29 07:00 | 2022-03-29 17:00 | N | Y | arc flash protection removal | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 85L (35s Rundle - 54L tap) | 2022-03-29 07:15 | 2022-03-29 17:45 | N | N | fire mitigation, maintenance on structures 5, 7 and 9 | Line |  | Fire mitigation Scope of work includes maintenance on structures 5, 7 and 9 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 65s T1 (65s High River), 13L (65s High River - 392s Black Diamond) | 2022-03-29 07:15 | 2022-03-29 12:45 | N | N | adding supervisory control to 65s22 | Transformer, Line |  | Adding supervisory control to 65s22 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 99s 747X (99s North St. Albert), 747L (99s North St. Albert - 711L tap) | 2022-03-29 07:30 | 2022-03-29 12:30 | N | N | trip testing from new T2 A and T2 B protections | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 728L (353s Plamondon - 405s Waupisoo) | 2022-03-29 07:30 | 2022-03-29 12:00 | N | N |  | Line | 728L (353s-405s)  GOI Strain insulators replacements. Repair broken stops on 353s23. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 267s C1 (267s Killarney Lake) | 2022-03-29 08:00 | 2022-03-29 17:30 | N | N | complete commissioning on the C1 A50/51/27/59/60/C1 relay | Shunts | 267s C1 (267s Killarney Lake) C1 OOS to complete commissioning on the C1 A50/51/27/59/60/C1 relay |  | Pre-Condition
ENMAX | 2B138-D82 (ENMAX 2) | 2022-03-29 08:00 | 2022-03-29 16:00 | N | N | relay, lockout testing | Circuit Breaker | 2B138-D82. 2sub 86BF-D82 Lockout relay Relay, Lockout Testing. D82 Breaker Fail Protection. Breaker fail on 2B138-D82. 2B138-D82 reclosing to be turned off while testing is progress. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SHELL | 847s 901T (847s Muskeg River) | 2022-03-29 08:00 | 2022-04-16 08:00 | N | Y | customer requested outage | Transformer |  | CNRL Request for their GT-1 & GT-2 Outage | 240 kV, Restricts Generation
ENMAX | 11.2TR (ENMAX 11) | 2022-03-29 08:00 | 2022-03-29 16:00 | N | N | repair 11BA8-11.2TR cell door | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28), 28B138-28.80 (ENMAX 28) | 2022-03-29 08:00 | 2022-03-29 12:00 | N | Y | spring substation washing | Line, Transformer, Circuit Breaker |  | Spring Substation Washing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 535s 6352 (535s Joffre) | 2022-03-29 08:30 | 2022-03-29 12:30 | N | N | breaker maintenance | Circuit Breaker |  | 138kV Breaker Maintenance | Pre-Condition
ATCO | 735s 602T (735s Swan River) | 2022-03-29 10:00 | 2022-04-29 18:00 | N | N | required due to clearance issues with outage on BKR 603 | Transformer |  | Real time Outage - GOI required due to clearance issues with outage on BKR 603. HIgh Risk of equipment making contact with 602T as BKR 603 is removed and replaced. Require 602T removed from service to mitigate this risk. | For Information Only
ENMAX | 1.80L (ENMAX 1 - ENMAX 28), 28.1TR (ENMAX 28) | 2022-03-29 12:00 | 2022-03-29 18:00 | N | N | spring substation washing and check reversing switch | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 99s 712X (99s North St. Albert), 712L (99s North St. Albert - 595s Spruce Grove) | 2022-03-29 12:30 | 2022-03-29 17:30 | N | N | trip testing from new T2 A and T2 B protections | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 535s 6252 (535s Joffre) | 2022-03-29 12:31 | 2022-03-29 17:30 | N | N | breaker maintenance | Circuit Breaker |  | 138kV Breaker Maintenance | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon) | 2022-03-29 13:00 | 2022-03-29 17:30 | N | N | strain insulators replacements | Line | 728L (353s-157s)  GOI Strain insulators replacements. Repair broken stops on 353s27. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32), 32B138-32BT5 (ENMAX 32) | 2022-03-30 08:00 | 2022-03-30 18:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.9TR (ENMAX 5) | 2022-03-30 08:00 | 2022-03-30 16:00 | N | N | relay, lockout testing. 5-86-T9 | Transformer |  |  | For Information Only
ALTALINK | 267s 752 (267s Killarney Lake), 267s C2 (267s Killarney Lake) | 2022-03-30 08:00 | 2022-03-30 12:30 | N | N | complete commissioning on the C2 A50/51/27/59/60/C2 relay | Circuit Breaker, Shunts | 267s C2 (267s Killarney Lake) |  | Pre-Condition
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.3TR (SS-9), 9.2TR (SS-9) | 2022-03-30 08:00 | 2022-03-30 18:00 | N | N |  | Line, Transformer | 9.83L (ENMAX 9 - ENMAX 43), 2.81L (ENMAX 2 - ENMAX 9) |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 888s 902 (888s Dover), 9L08 (849s Joslyn Creek - 888s Dover) | 2022-03-30 08:00 | 2022-03-30 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Circuit Breaker, Line |  | Wire DFR into existing CT circuit and wire breaker status to DFR, 9L08 open ended at 888S | 240 kV
ALTALINK | 535s 6152 (535s Joffre) | 2022-03-30 08:30 | 2022-03-30 12:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition
ALTALINK, ATCO | 69s 230W (69s North Barrhead), 7L230 (69s North Barrhead - 7L230 tap) | 2022-03-30 09:30 | 2022-03-31 16:30 | N | N | re-wire CT head to the correct ratio of 400/5 on associated 69s230W breaker in order to energize L5 B protection | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH69s5 MH69-T52 (MH69s5 NE Crescent Height) | 2022-03-30 10:00 | 2022-04-01 13:00 | N | N | PRC-005 testing and tapchanger maintenance | Transformer |  |  | For Information Only
ALTALINK | 267s C3 (267s Killarney Lake), 267s 24 (267s Killarney Lake) | 2022-03-30 13:00 | 2022-03-30 17:30 | N | N | C3 OOS to complete commissioning on the C3 A50/51/27/59/60/C3 relay | Shunts | 267s C3 (267s Killarney Lake) |  | Pre-Condition
ATCO | 888s 904 (888s Dover), 888s 905 (888s Dover), 9L09 (849s Joslyn Creek - 888s Dover) | 2022-03-31 08:00 | 2022-03-31 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Circuit Breaker, Line |  | Wire DFR into existing CT circuit and wire breaker status to DFR, 9L09 Open ended at 888S | 240 kV, Pre-Condition
ALTALINK | 283s 673 (283s Violet Grove), 673L (131s Moon Lake - 283s Violet Grove) | 2022-03-31 08:00 | 2022-03-31 16:30 | N | N | first trip and PRC5 maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 9.1TR (ENMAX 9) | 2022-03-31 08:00 | 2022-03-31 18:00 | N | N | spring substation washing | Line, Transformer | 9.80L (ENMAX 9 - ENMAX 31) |  | Pre-Condition
ENMAX | 5.10TR (ENMAX 5) | 2022-03-31 08:00 | 2022-03-31 16:00 | N | N | relay, lockout testing. 5-86-T10 | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 535s 5552 (535s Joffre) | 2022-03-31 08:30 | 2022-03-31 12:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition
ATCO | MUL1 Mowat | 2022-03-31 09:00 | 2022-03-31 17:30 | N | N | ATCO Clairmont telecom work | Unit
ATCO | SDH1 Saddle Hills | 2022-03-31 09:00 | 2022-03-31 17:30 | N | N | ATCO Clairmont telecom work | Unit
ENMAX | 5.6TR (ENMAX 5) | 2022-04-01 08:00 | 2022-04-01 16:00 | N | N | relay, lockout testing 5-86-T6 | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 26B138-26BT3 (SS-26) | 2022-04-01 08:00 | 2022-04-01 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.82L (ENMAX 1 - ENMAX 5), 5.1TR (ENMAX 5), 5.6TR (ENMAX 5), 5.8TR (ENMAX 5) | 2022-04-02 08:00 | 2022-04-02 18:00 | N | N | fall substation washing | Line, Transformer |  | Fall Substation Washing. 5MD138-5.1TR WEST PHASE OFF STOP. 5.1TR, TC, 5.6TR Replace PRD Junction Box. 5.8TR Relay, Lockout Testing. RTN 5.1TR, 5.8TR, 5.6TR. Oil Sampling -5.8TC. 5MD138-5.1TR East,Centre blades not on stops. LV Breaker Maint 5.8TR | For Information Only, Pre-Condition
ENMAX | 24.81L (ENMAX 24 - ENMAX 31), 31.84L (ENMAX 31 - ENMAX 32), 31.2TR (ENMAX 31), 31.3TR (ENMAX 31) | 2022-04-03 08:00 | 2022-04-03 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 818s 20 (818s Winefred), 818s T2 (818s Winefred) | 2022-04-04 06:30 | 2022-04-14 17:30 | N | N | replace 818s20 breaker protection | Switch, Transformer |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 557s CD2401 (557s Castle Downs), 557s CD2403 (557s Castle Downs) | 2022-04-04 07:00 | 2022-04-08 17:00 | N | Y | Castledowns 920LW way op-checks, P&C maintenance | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 805s T3 (805s Jasper) | 2022-04-04 07:00 | 2022-04-08 17:00 | N | Y | Jasper protection upgrade cutovers and 15 kV bus 3 PT replacement | Transformer |  |  | 240 kV, For Information Only
EPCOR | T2 (Kennedale), K722 (Kennedale), K723 (Kennedale) | 2022-04-04 07:00 | 2022-04-08 17:00 | N | N | Kennedale TX2 zone op-checks, P&C maintenance | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72CN10 (987s Clover Bar - Namao), T3 (Namao), N723 (Namao), N724 (Namao) | 2022-04-04 07:00 | 2022-04-07 17:00 | N | N | Namao and Cloverbar NDS11/NDS12 maintenance and CN723 breaker maintenance | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 492s T1 (492s Monarch) | 2022-04-04 07:00 | 2022-04-04 12:00 | N | N | tie in CT circuit for new 27/DER relay | Transformer |  |  | For Information Only
EPCOR | T2 (Poundmaker), PM2401 (Poundmaker), PM2405 (Poundmaker) | 2022-04-04 07:00 | 2022-04-05 17:00 | N | Y | repair to PMDS12 | Transformer, Circuit Breaker | T2 (Poundmaker) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 330p 1202 (330p Genesee), 330p 1203 (330p Genesee) | 2022-04-04 07:00 | 2022-04-08 17:00 | N | Y | 1202 bay CVT/G1 arrestor doble, 1202B/1203B/12GT1D disconnect maintenance | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 309s T1 (309s Anthony Henday), 309s T2 (309s Anthony Henday) | 2022-04-04 07:30 | 2022-04-06 14:30 | N | N | isolate 309s to complete the AML/TransMountain interconnection functional testing; warranty work on breaker 252 coil | Transformer |  |  | For Information Only
CMH | MHS-3 MH69-T31 (MHS-3 South Ridge), MHS-3 MH69-311 (MHS-3 Southridge) | 2022-04-04 07:30 | 2022-04-08 09:00 | N | N | PRC-005 - tap changer maintenance | Transformer, Circuit Breaker |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-3 Southridge substation. The T-31 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 3S3-M 13.8kV main breaker and MH69-310 69kV disconnect switch | For Information Only, Pre-Condition
ALTALINK | 428s T1 (428s Namaka) | 2022-04-04 08:00 | 2022-04-07 18:00 | N | N | install 138 kV bushing monitors | Transformer |  |  | For Information Only
ENMAX | 65.1TR (ENMAX 65) | 2022-04-04 08:00 | 2022-04-08 16:00 | N | Y | oil sampling - 240-65.1-TC, MT, check reversing switch, 65.1TR, TC replace PRD junction box, leak repair | Transformer | 65.1TR (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation
ATCO | 888s 907 (888s Dover) | 2022-04-04 08:00 | 2022-04-04 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Circuit Breaker |  | Wire DFR into existing CT circuit and wire breaker status to DFR, , Breaker and a half scheme no impact to 9L43 | 240 kV, Contingency Requires Mitigation, Restricts Generation
ENMAX | 2-GSU-XF-0002 (ENMAX 162), 162B240-RB134 (ENMAX 162), 162B240-RB135 (ENMAX 162) | 2022-04-04 08:00 | 2022-04-11 18:00 | N | Y | summer substation washing Z42, RB135, RB134, power factor testing 162PT240-Z42, 162MCT2 | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Restricts Generation
ENMAX | 1.7TR (ENMAX 1) | 2022-04-04 08:00 | 2022-04-06 16:00 | N | N | leak repair | Transformer |  |  | For Information Only
ALTALINK | 719L (263s Strachan - 719AL tap) | 2022-04-04 09:00 | 2022-04-06 18:00 | N | N | component replacements- structures #393 - 401 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 747L (99s North St. Albert - 711L tap), 99s 747X (99s North St. Albert) | 2022-04-04 09:30 | 2022-04-15 17:00 | N | N | 99s747X BF and A&B line protection replacements | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor), 774s 701 (774s Monitor) | 2022-04-04 09:30 | 2022-04-05 17:30 | N | Y | RTXP switch replacement | Line, Circuit Breaker |  | RTXP Switch Replacement | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2022-04-04 10:00 | 2022-04-04 12:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 310p 240kV Bus B (310p Sundance), 310p 240kV Bus C (310p Sundance), 919L (77s Sagitawah - 310p Sundance), 974L (39s Bickerdike - 310p Sundance), 310p T36 (310p Sundance), 310p T30 (310p Sundance) | 2022-04-04 11:00 | 2022-04-08 19:00 | N | Y | trip test, replace 310P1A, 310P1B, 310P4A, 310p452 CT, maintain 240 kV bus switches, replace T36 25 kV bushing, replace 310P252 grading caps & maintenance | Bus, Line, Transformer |  | First trip on 310P2552, 310P2252, 310P1952, 310P1352, 310P1052, 310P752, 310P452, 310P152, & 310P2852. Replace 310P1A, 310P1B, 310P4A, 310p452 CT. Maintain 240kV bus switches. Replace T36 25kV bushing. Replace 310P252 grading caps & maintenance. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 118s 138kV Bus 1 (118s Canmore), 54L (118s Canmore - 85L tap), 118s C1 (118s Canmore), 118s T1 (118s Canmore) | 2022-04-04 11:15 | 2022-04-04 17:45 | N | N | maintenance, PRC on 118s18 | Bus, Line, Shunts, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s 23N (121s Brooks) | 2022-04-04 11:15 | 2022-04-07 16:45 | N | Y | breaker 652 protection upgrade / migration to the new building /L6 meter replacement | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 1212L (12s Heartland - 89s Ellerslie) | 2022-04-04 12:00 | 2022-04-07 18:00 | N | Y | component replacements on 1212L (structure range 20-194) | Line |  |  | 500 kV, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2022-04-04 12:00 | 2022-04-04 13:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 151s 244E (151s Strathmore) | 2022-04-04 12:30 | 2022-04-04 16:30 | N | Y | PRC 005 - 1st trip and breaker maintenance | Circuit Breaker | 151s 244E (151s Strathmore) | PRC005: 1st trip, and maintenance if required. | For Information Only, Restricts Generation
ALTALINK | 348s T2 (348s Marlboro), 348s 252 (348s Marlboro) | 2022-04-04 12:30 | 2022-04-07 17:30 | N | N | T2: fix leaks, maintain, doble | Transformer, Circuit Breaker | 348s T2 (348s Marlboro) |  | For Information Only
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2022-04-04 13:00 | 2022-04-04 14:00 | N | N | spring pothead washing | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2022-04-04 14:00 | 2022-04-04 16:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 508s Lakesend | 2022-04-05 06:00 | 2022-04-05 20:00 | N | N | customer equipment maintenance - switchgear & NGR | Station |  |  | For Information Only
EPCOR | T2 (Strathcona) | 2022-04-05 07:00 | 2022-04-07 17:00 | N | N | strathcona TX2 PRD replacement | Transformer |  |  | For Information Only
ATCO | 9L58 (848s Ruth Lake - 888s Dover), 888s 908 (888s Dover), 888s 909 (888s Dover) | 2022-04-05 08:00 | 2022-04-05 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Line, Circuit Breaker |  | Wire DFR into existing CT circuit and wire breaker status to DFR, 9L58 Open Ended @ 888S | 240 kV, Pre-Condition, Affects Cranking Path
Syncrude | Aurora | 2022-04-05 08:00 | 2022-04-11 20:00 | N | N | breaker and switch testing | Station | Non-Significant Outage: 201-1-PTR72-3 Transformer (13.8/72kV) @ G01 Substation The following breaker will be operated: 52-G20 @ G01 Substation 11 @ G01 Substation 12 @ G01 Substation The following MOD will be operated: 15 @ G01 Substation |  | For Information Only, Restricts Generation
ALTALINK | 118s T1 (118s Canmore) | 2022-04-05 08:15 | 2022-04-07 16:45 | N | N | T1 maintenance, doble, & repair 118s14, 118s16 hot switch repairs | Transformer | 118s T1 (118s Canmore) |  | For Information Only
ALTALINK | 151s C1 (151s Strathmore) | 2022-04-05 08:30 | 2022-04-05 16:30 | N | N | full maintenance | Shunts | 151s C1 (151s Strathmore) |  | Pre-Condition
ALTALINK | 671L (39s Bickerdike - 58s Edson) | 2022-04-05 09:00 | 2022-04-05 14:00 | N | N | completion of high-load move between structures 131 and 132 | Line | 671L GOI required for completion of high-load move between structures 131 and 132. (Carrier PO-25-12417 Load 1) |  | Pre-Condition
ALTALINK | 492s 454E (492s Monarch) | 2022-04-05 12:00 | 2022-04-14 17:00 | N | N | replace and test 454LE (L6) protection | Circuit Breaker | Replace and test 454LE (L6) protection. Install and test new 27B/DER Relay. Replace and install new feeder cables from Fortis |  | For Information Only
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2022-04-05 15:11 | 2022-04-08 17:00 | N | N | forced outage | Line |  |  | Creates Radial Feeds, Firm Load Loss
AESO-SC | OATI | 2022-04-05 18:00 | 2022-04-05 19:00 | N | N | Inter-Site Transfer business continuity drill | SCInternal |  | O | For Information Only
EPCOR | T3 (Poundmaker), PM2404 (Poundmaker), PM2405 (Poundmaker) | 2022-04-06 07:00 | 2022-04-08 17:00 | N | Y | repair to PMDS11 | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 5.1TR (ENMAX 5) | 2022-04-06 08:00 | 2022-04-06 16:00 | N | N | relay, lockout testing. 5-86-T1 | Transformer |  |  | For Information Only
ATCO | 888s 919 (888s Dover), 888s 919C (888s Dover) | 2022-04-06 08:00 | 2022-04-06 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Circuit Breaker, Shunts |  | Wire DFR into existing CT circuit and wire breaker status to DFR | 240 kV, Pre-Condition
ENMAX | 26.2TR (ENMAX 26) | 2022-04-06 08:00 | 2022-04-06 16:00 | N | N | fit testing replacement breaker | Transformer |  |  | For Information Only
ALTALINK | 955L (59s Peigan - 103s Goose Lake) | 2022-04-06 08:00 | 2022-04-07 19:00 | N | Y | emergency work, replace leaking CT | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 431s C1 (431s Hussar) | 2022-04-06 09:00 | 2022-04-06 17:00 | N | N | full maintenance, PRC | Shunts | 431s C1 (431s Hussar) |  | For Information Only, Pre-Condition
BCH | 5L51 (Custer - Ingledow) | 2022-04-06 09:00 | 2022-04-07 17:00 | N | Y | inspection of ING 5GD23, BC maintenance does not affect the Alberta ATC | Line | 5L51 (Custer - Ingledow) | insulator replacement, BC Maintenance does not affect the Alberta ATC | 500 kV, Limits ATC, Pre-Condition
ATCO | 774s 704C (774s Monitor) | 2022-04-06 09:30 | 2022-04-07 17:30 | N | N | switch replacement | Shunts |  | RTXP Switch Replacement | For Information Only, Pre-Condition
FORTIS | MON1 Monarch | 2022-04-07 08:00 | 2022-06-11 13:00 | N | N | P1851 Fortis 492s Monarch DER Solar. 24 MW. ISD June 8, 2022 | Unit
FORTIS | Coaldale Solar DER | 2022-04-07 08:00 | 2022-04-21 16:00 | N | N | P1850 Fortis Coaldale 254S DER Solar 3. 23 MW. ISD April 14, 2022 | Unit
ATCO | 888s 916R (888s Dover) | 2022-04-07 08:00 | 2022-04-07 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Shunts |  | Wire DFR into existing CT circuit and wire breaker status to DFR | 240 kV, Pre-Condition
FORTIS | BRK1 Brooks Solar DER | 2022-04-07 08:00 | 2022-04-21 16:00 | N | N | P1851 492 Monarch DER Solar. ISD April 14, 2022. 24 MW. | Unit
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2022-04-07 08:00 | 2022-04-09 16:00 | N | N | forced outage | Line | Fire has burned down structures |  | Affects Cranking Path
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2022-04-07 08:30 | 2022-04-07 16:30 | N | N | full maintenance, PRC | Shunts | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) |  | Pre-Condition
ATCO | 741s 701 (741s ATC Fox Creek), 7L90 (741s Fox Creek - 7LA90 tap) | 2022-04-07 09:00 | 2022-04-07 16:00 | N | N | emergency - low SF6, investigate and top up | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
PANC | CAVALIER Cavalier RTU/SCADA | 2022-04-07 09:30 | 2022-04-07 14:00 | N | N | multiple communication outages for network maintenance | Terminal Equipment |  | multiple communication outages, most expected to be less than three minutes none expected to be more than 10 minutes. Outage to occur between 9:30 and 14:00. | Affects Visibility
EPCOR | T4 (Rossdale), RR729 (Rossdale), R724 (Rossdale) | 2022-04-08 07:00 | 2022-04-08 17:00 | N | N | zone op-checks, maintenance | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 54.81L (ENMAX 54 - ENMAX 65) | 2022-04-08 08:00 | 2022-04-08 18:00 | N | N | urgent outage to 138-54.81L | Line |  | ENMAX requires a urgent outage to 138-54.81L on April 7, 2022 0800  April 8 1800. The isolation points will be SW88 & SW91 @ 65 sub & 65MD138-54.81. There is an issue with the B phase 65PT138-54.81, crews will be isolating to further investigate and to attempt repairs. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2022-04-08 08:00 | 2022-04-08 10:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L127 (774s Monitor - 932s Pemukan) | 2022-04-08 09:30 | 2022-04-08 14:30 | N | N | RTXP switch replacement | Line |  | RTXP Switch Replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MHS-3 MH69-T33 (MHS-3 South Ridge), MHS-3 MH69-314 (MHS-3 Southridge) | 2022-04-08 10:00 | 2022-04-08 13:00 | N | N | PRC-005 - tapchanger maintenance | Transformer, Circuit Breaker |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-3 Southridge substation. The T-33 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 3S2-M 13.8kV main breaker and MH69-313 69kV disconnect switch. | For Information Only, Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2022-04-08 10:00 | 2022-04-08 11:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2022-04-08 11:00 | 2022-04-08 13:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.60L (ENMAX 15 - ENMAX 21) | 2022-04-08 13:00 | 2022-04-08 14:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2022-04-08 14:00 | 2022-04-08 16:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2022-04-09 07:00 | 2022-04-11 18:00 | N | Y | installing new RAS relay for the future 1024s Cassils substation that will be T- tapped off 964L | Line |  | Installing new RAS Relay for the future 1024s Cassils substation that will be T-tapped off 964L. This new RAS will not be going into service at this point. This outage is to just to install the equipment and complete some pre-commissioning (P1812) | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
Syncrude | UE-1 (D05 Syncrude - UE-1 Syncrude Plant 30-2) | 2022-04-09 08:00 | 2022-04-18 20:00 | N | N | emergency outage | Line |  | Urgent Force Majeure Non-Significant Outage: Cable termination failure on the 72kV UE1 feeder. The following circuit breakers will be operated: 73 (D05 Subst.) 72-06 (UE1 Subst.) 72-07 (UE1 Subst.) 72-08 (UE1 Subst.) 72-05 (UE1 Subst.) 72-04 (UE1 Subst.) 72-1509 (UE1 Subst.) associated MOD will also be operated. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 719L (719L259A - 719L216) | 2022-04-09 08:00 | 2022-04-09 14:00 | N | N | bird's nest removal | Line |  | bird's nests removal between Structures #231 - 241 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 1.82L | 2022-04-09 08:00 | 2022-04-09 16:00 | N | N | repair SW 2a9 and 1 Sub | Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2022-04-09 15:50 | 2022-04-13 16:50 | Y | Y | forced outage | Station, Line |  | forced outage | Limits ATC
FORTIS | CRG1 Camrose | 2022-04-09 17:00 | 2022-04-10 01:00 | N | N | communication maintenance | Unit |  |  | Affects Visibility
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31), 31.1C (ENMAX 31) | 2022-04-10 08:00 | 2022-04-10 18:00 | N | N | spring substation washing and maintenance | Line, Transformer, Shunts |  | Spring Substation Washing. Check Reversing Switch 31.1. Oil Sampling MT, TC | Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-04-10 08:00 | 2022-11-29 18:00 | N | N | 29PL-3 | Not In Model | Unmodeled Transmission Facility (Suncor) | 29PL3-18AB 29PT-23 HFCT | For Information Only
EPCOR | T1 (Kennedale), 72CK13 (987s Clover Bar - Kennedale) | 2022-04-11 07:00 | 2022-04-14 17:00 | N | N | maintenance and TX1 zone op-checks | Transformer, Line |  | Kennedale TX1 Zone Op-Checks, P&C Maintenance | Creates Radial Feeds, Firm Load Loss
EPCOR | T2 (Meadowlark) | 2022-04-11 07:00 | 2022-04-22 17:00 | N | N | secondary feeder re-cabling | Transformer | T2 (Meadowlark) |  | For Information Only
ALTALINK, Lethbridge | 370s 175 (370s North Lethbridge), 172L (181s Chinook - 370s North Lethbridge) | 2022-04-11 07:00 | 2022-04-11 17:30 | N | Y | commission new A67/178RAS and B67/178RAS CT circuits | Circuit Breaker, Line | 172L (181s Chinook - 370s North Lethbridge) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 557s T2 (557s Castle Downs) | 2022-04-11 07:00 | 2022-04-11 17:00 | N | Y | castledows CDDS7 disconnect maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s T2 (657s Summerside) | 2022-04-11 07:00 | 2022-04-29 17:00 | N | Y | continuation of 240 kV ring, re-configuration for SE expansion project (P2133) | Line, Transformer |  | continuation of 240 kV ring re-configuration for South East Expansion Project (P2133), bus re work and SUDS12 installation | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MHS-3 MH69-306 (MHS-3 Southridge), MH69s3 MH69-T32 (MHS-3 Southridge) | 2022-04-11 07:30 | 2022-04-13 09:00 | N | N | PRC-005 - tap changer maintenance | Circuit Breaker, Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-3 Southridge substation. The T-32 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 3S1-M 13.8kV main breaker and MH69-305 69kV disconnect switch. | For Information Only
ALTALINK | 394s T3 (394s Empress) | 2022-04-11 07:30 | 2022-04-21 08:00 | N | N | 394sT3 SA replacement, P&C move to new building | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 985L (74s Janet - ENMAX 25) | 2022-04-11 07:30 | 2022-04-15 17:00 | N | Y | outage to replace damaged section of OPGW between Str 1-2 | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2022-04-11 08:00 | 2022-04-14 16:00 | N | Y | walk up/ climbing inspection | Line | 7L40 (733s Simonette - 813s Little Smoky) | Walk Up/ Climbing inspection | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 2.2TR (ENMAX 2) | 2022-04-11 08:00 | 2022-04-14 16:00 | N | N | maintenance | Transformer |  | Tapchanger maintenance. Counter not working on 2.2TR LTC. ABB LTC Oil Filtration Maintenance. Oil Sampling MT, TC. Check Reversing Switch. 2.2TR Winding Temp Alarm | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28) | 2022-04-11 08:00 | 2022-04-12 16:00 | N | Y | breaker gas sample and maintenance | Line |  | HV breaker SF6 Gas Sample - 28B138-28.80. Gas Sample Baseline. 28B138-28.80 Failure to close. SW80 at 28 SUB stiff to open and close | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.1TR (ENMAX 11) | 2022-04-11 08:00 | 2022-04-16 16:00 | N | N | maintenance | Transformer |  | ECI bushing replacement. 11 Sub 11.1TR Tap changer heater failure. Oil Sampling MT, TC | For Information Only
ENMAX | 6.80L (ENMAX 6 - ENMAX 35) | 2022-04-11 08:00 | 2022-04-12 16:00 | N | N | install bird deterrents near Fish Creek | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock), 12L44 (939s Livock - 951s Thickwood Hills), 951s 240kV 900BS1 (951s Thickwood Hills), 951s 1201T (951s Thickwood Hills) | 2022-04-11 08:00 | 2022-04-14 16:00 | N | Y | 951S construction for 240kv expansion | Line, Bus, Transformer | 12L41 (510s Sunnybrook - 939s Livock), 12L44 (939s Livock - 951s Thickwood Hills) | 951S construction for 240kv expansion - 9L162 & 9L193 addition Connect 910A to 900BS1 Impact: 900BS1 OOS, BKR 901 OOS, BKR 904 OOS, BKR 907 OOS, 920C OOS Apr. 11, 2022 to Apr. 14, 2022 - Isolation points will be, 907B, 904B, 901B, 920A, 900SST1D and 12L41D1 939S | 240 kV, 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 245s T2 (245s Seebe) | 2022-04-11 08:15 | 2022-04-11 17:45 | N | N | install and commission new supervisory controls to airbreak 289 (245s14) | Transformer |  | install and commission new supervisory controls to airbreak 289 (245s14), wiring work required at the control module | For Information Only
ALTALINK | 245s T1 (245s Seebe), 9L (3s Horseshoe - 245s Seebe) | 2022-04-11 08:30 | 2022-04-22 14:00 | N | N | install and commission new supervisory controls to airbreak 189 (245s1), T1 maintenance | Transformer, Line |  | install and commission new supervisory controls to airbreak 189 (245s1), wiring work required at the control module, T1 maintenance | Restricts Generation
AIRLIQUIDE, SHELL | ALC03L (402s Scotford Expansion - 408s Air Liquide Scotford), 402s 702T (402s Scotford Expansion 1) | 2022-04-11 09:00 | 2022-04-23 17:30 | N | Y | 702T, breaker maintenance, trip coil & relay testing | Line, Transformer |  | 702T Maintenance, breaker maintenance, PRC-005 trip coil & relay testing, RTXP replacements, DFR & line differential addition | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 6L96 (735s Swan River - 743s Sarah Lake) | 2022-04-11 10:00 | 2022-04-29 16:30 | N | N | replace breaker 604 | Line |  | Replace Breaker 604 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Saskpower | Sask Power PR902 | 2022-04-11 10:00 | 2022-04-12 15:00 | N | Y | maintenance | Circuit Breaker |  |  | Limits ATC
ALTALINK | 67s T1 (67s Stirling) | 2022-04-11 11:00 | 2022-04-13 17:00 | N | Y | maintenance , doble, SFRA, AMP replacement | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 447s T1 (447s Enchant) | 2022-04-11 11:30 | 2022-05-04 11:50 | N | N | bushing replacement, bird nest removal | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 653s 752 (653s Summit), 752L (653s Summit - 752AL tap) | 2022-04-11 12:30 | 2022-04-11 16:30 | N | N | trip testing and breaker maintenance | Circuit Breaker, Line | 653s 752 (653s Summit) | 1st Trip on 653s752 and maintenance if required. PRC5 | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition, Restricts Generation
ALTALINK | 348s T1 (348s Marlboro), 348s 152 (348s Marlboro) | 2022-04-11 12:30 | 2022-04-13 17:30 | N | N | T1: fix leaks, maintain, doble | Transformer, Circuit Breaker | 348s T1 (348s Marlboro) | T1: fix leaks, maintain, doble, maintain 348s152 | For Information Only
ALTALINK | 37s 82 (37s North Calder) | 2022-04-11 12:30 | 2022-04-13 17:30 | N | Y | first trip and maintenance, replace AC receptacle in cabinet | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 818s C1 (818s Winefred), 818s 14 (818s Winefred) | 2022-04-12 06:30 | 2022-04-12 10:30 | N | N | trip test for the new 818s20 breaker protection | Shunts, Circuit Breaker |  | Trip test for the new 818s20 Breaker Protection | Pre-Condition
ALTALINK | 688L (199s East Airdrie - 688AL tap), 199s C1 (199s East Ardrie), 199s T2 (199s East Airdrie) | 2022-04-12 07:00 | 2022-04-19 17:00 | N | N | 138 kV switch replacement (199s25, 199s26) | Line, Shunts, Transformer | 688L (199s East Airdrie - 688AL tap) | 138kV Switch Replacement (199s25, 199s26) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2022-04-12 07:00 | 2022-04-12 16:00 | N | N | urgent - change arms and insulation on structure 304 | Line |  | Urgent outage to change arms and insulation on structure 304 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2022-04-12 07:00 | 2022-04-13 18:35 | N | Y | installing new RAS relay for the future 1024s Cassils substation that will be T-tapped off 964L | Line |  | Installing new RAS Relay for the future 1024s Cassils substation that will be T-tapped off 964L. This new RAS will not be going into service at this point. This outage is to just install the equipment and complete some pre-commissioning (P1812) | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 121s T5 (121s Brooks) | 2022-04-12 07:15 | 2022-04-12 16:45 | N | Y | replace 121s38 switch glass, migrate 25 kV bus 1 PT distribution to new building | Transformer |  | Replace 121s38 Switch Glass. Migrate 25kV Bus 1 PT distribution to new building. | For Information Only, Restricts Generation
ALTALINK | 309s Anthony Henday, 309s T1 (309s Anthony Henday), 309s T2 (309s Anthony Henday) | 2022-04-12 07:30 | 2022-04-14 14:30 | N | N | open points "A" and "B" will be closed in and bird mitigation installed | Station, Transformer |  |  | For Information Only
BHE Canada | MATL (120s Picture Butte - Montana), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte) | 2022-04-12 08:00 | 2022-04-12 12:00 | N | Y | urgent complete leak cleanup and repair on PS1 | Line, Circuit Breaker |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 221s T2 (221s Sunken Lake) | 2022-04-12 08:00 | 2022-04-13 17:00 | N | N | transformer and switch maintenance | Transformer |  | TX maintenance, AltaLink switch maintenance, Switch maintenance - customer | For Information Only
BHE Canada | 120s MATL PST (120s Picture Butte) | 2022-04-12 08:00 | 2022-04-12 12:00 | N | N | taking advantage of MATL curtailment to complete leak investigation and repair on PS1 | Transformer |  | taking advantage of MATL curtailment to complete leak investigation and repair on PS1. | For Information Only
ALTALINK | 216s T2 (216s Knightsbridge) | 2022-04-12 09:30 | 2022-04-13 17:00 | N | N | fix leaks, breather, maintenance, doble | Transformer |  | 216sT2: fix leaks, breather, maintain, doble | For Information Only
ALTALINK | 818s C2 (818s Winefred), 818s 17 (818s Winefred) | 2022-04-12 10:35 | 2022-04-12 14:00 | N | N | trip test for the new 818s20 breaker protection | Shunts, Circuit Breaker |  | Trip test for the new 818s20 Breaker Protection | Pre-Condition
NWE, BHE Canada | Marias South Series Capacitor | 2022-04-12 12:00 | 2022-11-19 18:00 | N | Y | urgent- replace the Marias series capacitor bypass breaker 2385 Phase B | Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 818s C3 (818s Winefred), 818s 41 (818s Winefred) | 2022-04-12 13:30 | 2022-04-12 17:30 | N | N | trip test for the new 818s20 breaker protection | Shunts, Circuit Breaker |  | Trip test for the new 818s20 Breaker Protection | Pre-Condition
ALTALINK | 710L (56s Boyle - 159s Colinton) | 2022-04-13 07:00 | 2022-04-13 17:00 | N | N | urgent outage to change arms and insulation on structure 134 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 72CH11 (987s Clover Bar - EPCOR Hardisty) | 2022-04-13 07:00 | 2022-04-13 17:00 | N | N | clean and investigate leaking pothead | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 818s 789 (818s Winefred), 789L (818s Winefred - 789BL tap) | 2022-04-13 07:30 | 2022-04-13 11:30 | N | N | trip test for the new 818s20 breaker protection | Circuit Breaker, Line |  |  | Pre-Condition
SUNCOR | 29EDD-71, 29EDD-71 752-4654 (29EDD-71), 29EDD-71 752-4652 (29EDD-71) | 2022-04-13 08:00 | 2022-04-19 18:00 | N | N | maintenance | Station, Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 36.81L (44s Bearspaw - ENMAX 36) | 2022-04-13 08:00 | 2022-04-13 12:00 | N | Y | HV breaker SF6 gas sample - 36B138-36.81 | Line |  |  | For Information Only
ALTALINK | 115s T2 (115s Mount Allan) | 2022-04-13 09:30 | 2022-05-18 17:00 | N | N | emergency work; hydrogen gas buildup needs to be removed from TX | Transformer |  |  | For Information Only
ENMAX | 36B138-36BT3 (ENMAX 36) | 2022-04-13 12:00 | 2022-04-13 16:00 | N | N | HV breaker SF6 gas sample | Circuit Breaker |  |  | For Information Only
ALTALINK | 818s 428 (818s Winefred), 428L (167s Ipiatik Lake - 818s Winefred) | 2022-04-13 12:30 | 2022-04-13 16:30 | N | N | trip test for the new 818s20 breaker protection | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 42s 3W (42s Sarcee), 3L (42s Sarcee - 272s Springbank) | 2022-04-13 14:00 | 2022-04-13 15:30 | N | N | need sufficient load on the line from 245s to provide accurate measurement | Circuit Breaker, Line |  | Need to perform load readings on the new 3L protections that were installed and commissioned at 245s Seebe, Need sufficient load on the line from 245s to provide accurate measurement. | For Information Only, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-04-14 07:00 | 2022-04-25 18:00 | N | N | 174L phase 3 rebuild (structures 539 to 691) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 15s 463 (15s Fort Macleod) | 2022-04-14 07:00 | 2022-04-14 17:30 | N | Y | decommission 50/166RAS A/B protection schemes and repurpose A50/166RAS for 85/1139AIS anti-islanding for 463L LTO and status to 370s and breaker maintenance | Line, Circuit Breaker |  | decommission 50/166RAS A/B protection schemes and repurpose A50/166RAS for 85/1139AIS anti-islanding for 463L LTO and status to 370s and breaker maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower, Whitla 2 Wind Generation L.P. | WHT1 Whitla, WHT2 Whitla 2 | 2022-04-14 12:00 | 2022-04-14 13:00 | N | N | upgrade firmware/software of cradlepoints at Whitla | Unit |  | Unit Whitla Start Date April 14,2022 Start Time 12:00 MST End Date April 12, 2022 End Time 13:00 MST Description Plan to upgrade firmware/Software of Cradlepoints at Whitla. Upgrade will be to the primary so connectivity will switch to backup Cradlepoint before upgrade. This will only be a communication outage, and this will most likely be only a blip (~10seconds). There will be someone on site to respond to curtailments if needed. Minimum Load Requirement NA Available Capacity 201.6/151.2 MVAR NA AS Availability NA Comments | For Information Only
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap), 113s T1 (113s Inland Cement), 113s T2 (113s Inland Cement) | 2022-04-16 07:00 | 2022-04-16 17:00 | N | Y | 113s1, 113s5 maintenance | Line, Transformer | 711L (Inland Cement - 747L tap) |  | For Information Only
ENMAX | 2.3TR (ENMAX 2) | 2022-04-16 08:00 | 2022-04-16 16:00 | N | N | tapchanger oil top up | Transformer |  |  | For Information Only
EPCOR | 113s T1 (113s Inland Cement) | 2022-04-16 17:00 | 2022-04-23 17:00 | N | N | TX1 doble testing | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 284s Nose Creek | 2022-04-17 10:00 | 2022-04-17 11:01 | N | N | maintenance | Station |  |  | For Information Only
ALTALINK | 688L (199s East Airdrie - 688AL tap), 688L (653s Summit - 688AL tap), 688AL (284s Nosecreek - 688L tap) | 2022-04-17 11:00 | 2022-04-22 17:45 | N | N | replace existing T1 transformer, maintenance on structures 688AL 5/6/14 & 688L 15/16/88 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 214s T2 (214s Innisfail) | 2022-04-18 07:00 | 2022-04-18 13:00 | N | Y | cut 2047L1 free from the AML system; feeder cable replacements (2047L, 28LN); 25kV switch replacements (214s11, 214s13); PT replacement (VT9); neutral install to NEUT JB2 | Transformer |  |  | Pre-Condition, Restricts Generation
ENMAX | 162B240-RB131 (ENMAX 162), 162B240-RB132 (ENMAX 162) | 2022-04-18 07:00 | 2022-04-22 17:00 | N | Y | summer substation washing Z41, RB131, RB132, power factor test PT Z41, 162MCT1 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Restricts Generation
CMH | MH69s6 MH69-T61(MH69s6 Riverview), MHS-6 MH69-604 (MHS-6 CMH Riverview) | 2022-04-18 07:30 | 2022-04-20 09:00 | N | N | PRC-005 - tap changer maintenance | Transformer, Circuit Breaker |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-6 Riverview substation. The T-61 30/40/50 MVA 69/13.8 kV power transformer will be de-energized and isolated at 6S1-M 13.8kV main breaker and MH69-605 69kV disconnect switch. | For Information Only
ATCO | 2075s 900SST1 (2075s Newell), 2075s 920 (2075s Newell), 2075s 921 (2075s Newell) | 2022-04-18 08:00 | 2022-04-25 08:00 | N | Y | PRC relay testing on 20D02 diameter - station service transformer protection | Transformer, Circuit Breaker |  | This Permit is for AESO reference only. Switching will be issued from permit # 2-63020 Apr. 18 to Apr. 25, 2022 920A, 921B and 501VRA for 900SST1 Outage PRC Relay Testing on 20D02 Diameter - Station Service Transformer Protection | 240 kV
ALTALINK | 214s T2 (214s Innisfail) | 2022-04-18 13:01 | 2022-04-22 17:00 | N | Y | feeder cable replacements (2047L, 28LN); 25kV switch replacements (214s11, 214s13); PT replacement (VT9); Neutral install to NEUT JB2 | Transformer |  |  | Pre-Condition, Restricts Generation
EPCOR | 816s T1 (816s Petrolia), 816s P2401 (816s Petrolia), 816s P2402 (816s Petrolia) | 2022-04-19 07:00 | 2022-04-22 17:00 | N | Y | TX1 and arrestor doble, PAB1 disconnect maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 240BA2 (629s Argyll Transfer Station - 814s Bellamy) | 2022-04-19 07:00 | 2022-04-19 16:00 | N | N | low SF6 emergency top up | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 394s 138kV Bus 1 (394s Empress), 760L (163s Amoco Empress - 394s Empress), 394s T1 (394s Empress), 394s T3 (394s Empress) | 2022-04-19 07:15 | 2022-04-25 17:45 | N | N | relocate P&C to new building and integrate anti-island scheme and install breaker maintenance switch | Bus, Line, Transformer | 394s 138kV Bus 1 (394s Empress) T1, T3, 760L & 25kV bus1 Relocate P&C to new building including, T3 A&B Protections, Complete 394s952 Breaker Fail Trips; integrate anti-island scheme and install breaker maintenance switch. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 491L tap) | 2022-04-19 07:30 | 2022-04-19 17:00 | N | Y | addition of a RAS relay in the existing CT circuit for ATCO Michichi project and new RAS channel installation | Line |  | Breaker outage to allow for the addition of a RAS relay in the existing CT circuit Required for ATCO Michichi project and new RAS channel installation | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L11 (813s Little Smoky - 834s Wesley Creek), 813s 905 (813s Little Smoky), 813s 906 (813s Little Smoky) | 2022-04-19 08:00 | 2022-05-15 12:00 | N | Y | 813S Little Smoky rebuild | Line, Circuit Breaker |  | 813S Little Smoky Rebuild Remove panels 5H,6H - install new panel 9P3 - BKR 905 and 906 P&C wiring, prep work Relay programming and functionality Commission control, alarms and status | 240 kV, Pre-Condition, Affects Cranking Path
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2022-04-19 08:00 | 2022-04-19 12:00 | N | N | replacing a pole structure and some damaged insulators | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 36.2TR (ENMAX 36) | 2022-04-19 08:00 | 2022-04-29 16:00 | N | N | 36.2TR ECI bushing replacement, testing, maintenance | Transformer |  | 36.2TR ECI bushing replacement, power factor test transformer Secondary Cable Testing. Transformer Maintenance. Gas Relay Testing. Oil Sampling MT, TC. Check Reversing Switch. 36.2TR Gas trip Switch Repalcement | For Information Only
Syncrude | Mildred T15 (Syncrude Mildred Lake), 1535 (Syncrude Mildred Lake) | 2022-04-19 08:00 | 2022-04-27 20:00 | N | N | maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2022-04-19 08:00 | 2022-04-26 16:00 | N | N | 36.2TR ECI bushing replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2022-04-19 09:00 | 2022-04-20 17:00 | Y | Y | replace timber | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 688L (653s Summit - 688AL tap) | 2022-04-19 09:30 | 2022-04-20 13:30 | N | N | 653s688 maintenance PRC5 | Line |  |  | For Information Only
ATCO | 770s 701T (770s Three Hills) | 2022-04-19 10:00 | 2022-04-22 17:00 | N | N | protection upgrade for capstone. Install new tap changer controller | Transformer |  | Protection upgrade for capstone DG. Install new tap changer controller | For Information Only
ALTALINK | 760L (163s Amoco Empress - 394s Empress), 163s 760X (163s Amoco Empress) | 2022-04-19 10:30 | 2022-04-25 16:30 | N | N | breaker outage to integrate anti-island scheme and install breaker maintenance switch | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s T4 (370s North Lethbridge) | 2022-04-19 11:30 | 2022-04-21 17:30 | N | N | complete bird cover on 25kV Bus#4 | Transformer |  |  | For Information Only
ALTALINK | 138s 1652 (138s Windy Flats), 138s R1 (138s Windy Flats) | 2022-04-19 11:30 | 2022-04-21 17:30 | N | Y | breaker and reactor maintenance | Circuit Breaker, Shunts | Maintenance, doble (R1). 138kV Breaker Maintenance (138s1652) |  | Pre-Condition
ALTALINK | 71s 152 (71s Lamoureux) | 2022-04-19 12:00 | 2022-04-22 18:00 | N | N | replacing CTs | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162.1TR (162s Beddington) | 2022-04-19 23:26 | 2022-04-26 18:00 | N | Y | forced outage | Transformer |  | 162.1TR tripped out of services at 2022-04-19 @ 23:26. Field crews investigated problems and found water entering a sudden pressure relay and it is required to be replaced. Asset department and field crews estimate it will take one week to source and replace the relay. Transformer 162.1TR is expected to return to service 2022-04-27 @ 18:00. | 240 kV
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia) | 2022-04-20 07:00 | 2022-04-20 16:00 | N | Y | emergency - top up BDS20 low SF6 | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | R723 (Rossdale), R724 (Rossdale), T3 (Rossdale) | 2022-04-20 07:00 | 2022-04-20 17:00 | N | N | RDS7 - ground conductor repair and disconnect maintenance | Circuit Breaker, Transformer |  | Rossdale RDS7, ground conductor repair, disconnect maintenance | Contingency Requires Mitigation, Pre-Condition
ENMAX | 40.2TR (ENMAX 40) | 2022-04-20 08:00 | 2022-04-21 16:00 | N | N | maintenance | Transformer |  | Tapchanger maintenance. Oil Sampling MT, TC. Filmax LTC Oil Filtration Maintenance | For Information Only
ALTALINK | 65s 2088N (65s High River) | 2022-04-20 08:30 | 2022-04-20 12:30 | N | N | remove UFLS trip scheme - 25 kV breaker | Circuit Breaker |  | Techs require GOI on 65s2088 to remove UFLS trip scheme (FORTIS Request). | For Information Only
ALTALINK | 38s C1 (38s East Edmonton), 38s 3052 (38s East Edmonton) | 2022-04-20 08:30 | 2022-08-14 18:00 | N | N | breaker maintenance and testing | Shunts, Circuit Breaker |  | Breaker maintenance including 1st trip testing. Replace contactor for charge motor | Pre-Condition
ALTALINK | 244s 2952 (244s Bowmanton) | 2022-04-20 09:30 | 2022-04-20 13:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload
CMH | MHS-6 MH69-608 (MHS-6 CMH Riverview), MH69s6 MH69-T62 (MH69s6 Riverview) | 2022-04-20 10:00 | 2022-04-22 13:00 | N | N | PRC-005 - tap changer maintenance | Circuit Breaker, Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-6 Riverview substation. The T-62 30/40/50 MVA 69/13.8 kV power transformer will be de-energized and isolated at 6S2-M 13.8kV main breaker and MH69-609 69kV disconnect switch. | For Information Only, Pre-Condition
ALTALINK | 244s 3052 (244S Bowmanton) | 2022-04-20 13:01 | 2022-04-20 16:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 814s T1 (814s Bellamy), 72RV6 (EP 511s Victoria - Rossdale), VHBB1 (Rossdale) | 2022-04-21 07:00 | 2022-04-21 17:00 | N | Y | hot contacts, maintenance | Transformer, Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage
ALTALINK | 747L (99s North St. Albert - 711L tap), 99s 747X (99s North St. Albert) | 2022-04-21 07:30 | 2022-04-21 12:30 | N | N | remove CT contributions to existing 138Kv A Bus protection. | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2022-04-21 08:00 | 2022-04-22 17:00 | N | N | replacing a pole structure and some damaged insulators | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, BCH | 887L (48s Pocaterra - BCH Britt Creek), 1L274 (EFT 1D22 - 1D3L274) | 2022-04-21 08:00 | 2022-04-21 18:00 | N | Y | open 887L for 237s MPLS upgrade | Line | 887L (48s Pocaterra - BCH Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 632L (325s Leduc - 538s Buford) | 2022-04-21 08:30 | 2022-04-21 13:30 | N | N | close open point A on 472s mobile & MR1 @ 538s | Line | Close Open Point A on 472s mobile & MR1 @ 538s on the line side of 538s632 (632L). RSLD 2 to be implemented at the end of the outage. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, TRANSCANADAP | 760L (163s Amoco Empress - 760AL tap), 163s 760N (163s Amoco Empress), 910s Excel | 2022-04-21 08:30 | 2022-04-21 16:30 | N | N | breaker outage to integrate anti-island scheme and install breaker maintenance switch | Line, Circuit Breaker, Station | Breaker outage to integrate anti-island scheme and install breaker maintenance switch |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 970s 703 (970s Bourque) | 2022-04-21 09:00 | 2022-04-21 11:00 | N | N | test and operate for PRC005 trip coil testing | Circuit Breaker |  | Test and Operate for PRC005 trip coil testing | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 523s 552 (523s Bullshead) | 2022-04-21 09:30 | 2022-04-21 13:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
CHDI | SUM1 Summerview | 2022-04-21 10:00 | 2022-04-21 10:30 | N | N | communication outage for RTU updates | Unit |  |  | Affects Visibility
ATCO | 970s 705 (970s Bourque) | 2022-04-21 11:00 | 2022-04-21 13:00 | N | N | test and operate for PRC005 trip coil testing | Circuit Breaker |  | Test and Operate for PRC005 trip coil testing | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 39s 852 (39s Bickerdike) | 2022-04-21 12:30 | 2022-04-21 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 970s 706 (970s Bourque) | 2022-04-21 13:00 | 2022-04-21 15:00 | N | N | test and operate for PRC005 trip coil testing | Circuit Breaker |  | Test and Operate for PRC005 trip coil testing | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 523s 880 (523s Bullshead) | 2022-04-21 13:01 | 2022-04-21 16:30 | N | Y | 138kV breaker maintenance | Line, Circuit Breaker | 880L (321s Al Rothbauer - 523s Bullshead) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 538s T1 (538s Buford) | 2022-04-21 14:30 | 2022-05-17 13:30 | N | N | bushing and oil replacement, leak repairs, maintenance | Transformer |  | 472s mobile & MR1 to take load @ 538s. 538sT1 bushing replacement, 538sT1 oil replacement, 538sT1 leak repairs and maintenance. 538sVR1 transformer and tap changer maintenance. Replace 538s10, 538s9 hot spot, 538s7 hot spot. Salvage 538s8, 538s11, and 25kV bypass cables. RSLD 4 to be implemented at the end of the outage. Soak transformer for 4 hours | For Information Only
EPCOR | T1 (Rossdale) | 2022-04-22 07:00 | 2022-04-22 17:00 | N | N | tap changer maintenance, move gravel in reactor bay | Transformer |  |  | For Information Only
ALTALINK | 99s T1 (99s North St. Albert) | 2022-04-22 07:30 | 2022-04-22 12:30 | N | N | remove CT contributions to existing 138 kVA bus protection | Transformer |  |  | For Information Only
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2022-04-22 08:00 | 2022-04-30 20:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
Syncrude | Mildred T17 (Syncrude Mildred Lake) | 2022-04-22 08:00 | 2022-04-28 20:00 | N | N | maintenance | Transformer |  | Non-Significant Outage: Plant 31 Substation 72kV "A" Buss: The following 72/13.8kV T17 Transformers will be offline: CB: 1735 will be operated. | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 14.1C (ENMAX 14), 14.2C (ENMAX 14), 14.2TR (ENMAX 14), 14.4TR (ENMAX 14) | 2022-04-22 08:00 | 2022-04-22 16:00 | N | N | power factor test 14PT138-Z31. 14.83L already oos | Line, Shunts, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2022-04-22 08:00 | 2022-04-22 16:00 | N | N | power factor test 5B138-1.82-CT | Line |  |  | For Information Only
Syncrude | Mildred T18 (Syncrude Mildred Lake) | 2022-04-22 08:00 | 2022-04-28 20:00 | N | N | maintenance | Transformer |  | Non-Significant Outage: Plant 31 Substation 72kV "A" Buss: The following 72/13.8kV T18 Transformers will be offline: CB: 1835 will be operated. | For Information Only
ATCO | 970s 707 (970s Bourque) | 2022-04-22 09:00 | 2022-04-22 11:00 | N | N | test and operate for PRC005 trip coil testing | Circuit Breaker |  | Test and Operate for PRC005 trip coil testing | Contingency Requires Mitigation, Pre-Condition
ATCO | 970s 708 (970s Bourque) | 2022-04-22 11:00 | 2022-04-22 13:00 | N | N | test and operate for PRC005 trip coil testing | Circuit Breaker |  | Test and Operate for PRC005 trip coil testing | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 99s T2 (99s North St. Albert) | 2022-04-22 12:30 | 2022-04-22 17:30 | N | N | remove CT contributions to existing 138 kVA bus protection | Transformer |  |  | For Information Only
ALTALINK | 284s Nose Creek, 688AL (284s Nosecreek - 688L tap) | 2022-04-22 17:46 | 2022-04-28 08:00 | N | N | replace existing T1 | Station, Line |  |  | For Information Only
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31), 31.1C (ENMAX 31) | 2022-04-24 08:00 | 2022-04-24 18:00 | N | N | spring substation washing. oil sampling MT, TC | Line, Transformer, Shunts |  |  | Pre-Condition
SUNCOR | 29EDD-94 407T (29EDD-94), 29EDD-94 29-952-9704 (29EDD-94 Voyageur), 29EDD-94 29-952-9705 (29EDD-94 Voyageur) | 2022-04-25 06:00 | 2022-05-06 18:00 | N | Y | maintenance and test | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s Victoria T5 (EP 511s Victoria) | 2022-04-25 07:00 | 2022-04-27 17:00 | N | Y | bushing alarm investigation | Line, Transformer | Victoria TX5 Emergency Outage, Bushing Alarm Investigation |  | 240 kV
EPCOR | 1098L (805s Jasper - Poundmaker), PM2401 (Poundmaker), PM2402 (Poundmaker), EP 805s J2407 (EP 805s Jasper) | 2022-04-25 07:00 | 2022-04-29 17:00 | N | Y | zone doble and disconnect maintenance | Line, Circuit Breaker | Jasper 1098L CVT LCR and Poundmaker/Jasper 1098L Zone Doble and PMDS2/PMDS3/PMDS9 Disconnect Maintenance |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 510s 2852 (510s Sunnybrook) | 2022-04-25 07:00 | 2022-04-25 17:30 | N | Y | install, wire, test and commission new SEL-2411 | Circuit Breaker |  | Install, wire, test and commission new SEL-2411 for Suncor co-gen. RAS scheme | 500 kV, Contingency Requires Mitigation
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2022-04-25 07:00 | 2022-05-09 18:00 | N | Y | removing and installing new protections for the future 1024s | Line | Removing and installing new protections for the future 1024s being tapped off 964L; Closing 964AL Open Point 'A' |  | Creates Radial Feeds, Firm Load Loss, Overload
CMH | MHS9 T11 (MHS9 Power Plant), MH-6L (MH69s-1 Power Plant Switchyard - MHS9 Power Plant) | 2022-04-25 07:30 | 2022-04-29 12:00 | N | Y | PRC-005 - tapchanger maintenance | Transformer, Line | MHS9 T11 (MHS9 Power Plant), MH-6L (MH69s-1 Power Plant Switchyard - MHS9 Power Plant) | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-9 South Saskatchewan substation. This planned maintenance will also include protective relay setting changes for the transformer. The T-11 67.2/89.6/112 MVA 138/69 kV power transformer will be de-energized and isolated at both of the MH69-5 and MH69-11 69 kV disconnect switches as well as the MH138-901 138 kV disconnect switch. | Overload, Pre-Condition, Restricts Generation
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2022-04-25 08:00 | 2022-06-03 16:00 | N | N | replace circuit breaker | Line | 2.82L (ENMAX 2 - ENMAX 5) |  | For Information Only, Pre-Condition
ENMAX | 40.2TR (ENMAX 40) | 2022-04-25 08:00 | 2022-04-28 16:00 | N | N | power factor test transformer | Transformer | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance, Gas relay testing. Oil Sampling MT, TC. 40B8-40.2TR REPLACE COUNTER |  | For Information Only
ATCO | 2075s 240kV Bus 900BS2 ( 2075s Newell), 2075s 900SST2 (2075s Newell) | 2022-04-25 08:00 | 2022-04-27 15:30 | N | Y | PRC relay testing | Bus, Transformer | PRC Relay Testing on 20D02 Diameter - 920, 921, 906, 912, 918 and 923 Breaker Fail Protection will all be tested as a result of PRC-005 Testing | This Permit is for AESO Reference only. Switching will be issued from permit 2-63020 Apr. 25 to Apr. 29, 2022 the isolation will expand to 906A. 912A, 918A, 923A, 920A for a full 900BS2 outage PRC Relay Testing on 20D02 Diameter - 920, 921, 906, 912, 918 and 923 Breaker Fail Protection will all be tested as a result of PRC-005 Testing | Contingency Requires Mitigation
ENMAX | 162.3TR (162s Beddington), 162B138-RB86 (ENMAX 162), 162B138-RB85 (ENMAX 162) | 2022-04-25 08:00 | 2022-04-26 18:00 | N | N | summer substation washing, check reversing switch and oil sampling | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK, Lethbridge | 370s 138kV Bus 1 (370s North Lethbridge), 172L (181s Chinook - 370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge), 770L (254s Coaldale - 370s North Lethbridge), 370s T1 (370s North Lethbridge) | 2022-04-25 08:15 | 2022-04-28 17:45 | N | Y | Install a new MOD switch | Bus, Line, Transformer | Install a new MOD switch between 138kV Bus 1 and 370s3 for future 370s T1 high side CB to avoid having to take this outage again (P7073) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L90 (813s Little Smoky - 7LA90 tap), 741s 701 (741s ATC Fox Creek) | 2022-04-25 09:00 | 2022-05-12 12:30 | N | N | breaker 701 replacement | Line, Circuit Breaker |  | Breaker 701 Replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 888s 906 (888s Dover) | 2022-04-25 09:00 | 2022-04-26 14:00 | N | Y | RAS and DFR addition to 9L74 on Breaker 906 | Circuit Breaker |  | RAS and DFR addition to 9L74 on Breaker 906 | Contingency Requires Mitigation
BCH | 5L91 (Ashton Creek - Selkirk) | 2022-04-25 09:00 | 2022-04-29 16:30 | N | Y | station DS inspection of SEL 5D23, BC maintenance does not affect the Alberta ATC | Line | 5L91 (Selkirk - Ashton Creek) | structure replacement, BC maintenance does not affect the Alberta ATC | 500 kV, Limits ATC, Pre-Condition
ATCO | 951s 920C (951s Thickwood) | 2022-04-25 12:00 | 2022-04-26 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Shunts |  | Wire DFR into existing CT circuit and wire breaker status to DFR | 240 kV, Pre-Condition
ALTALINK | 15s T1 (15s Fort Macleod) | 2022-04-25 12:30 | 2022-05-01 17:30 | N | N | oil reclaim | Transformer |  |  | For Information Only
ALTALINK | 471s Mobile | 2022-04-25 13:00 | 2022-04-27 07:00 | N | N | setting up mobile sub | Station |  |  | For Information Only
ALTALINK | 510s 2952 (510s Sunnybrook) | 2022-04-26 07:00 | 2022-04-26 17:30 | N | Y | install, wire, test and commission new SEL-2411 | Circuit Breaker |  | Install, wire, test and commission new SEL-2411 for Suncor co-gen. RAS scheme | 500 kV, For Information Only
ENMAX | 162B240-RB142 (ENMAX 162), 162B240-RB143 (ENMAX 162), 2-GSU-XF-0002 (ENMAX 162) | 2022-04-26 07:00 | 2022-04-26 17:00 | N | Y | maintenance and grounds required to be installed by Enmax between SW142, SW143 | Circuit Breaker, Transformer |  | Maintenance on 2-EMC-DS-0002 by CEC. Grounds required to bre installed by Enmax between SW142, SW143 | 240 kV, Contingency Requires Mitigation, Restricts Generation
EPCOR | RW2401 (EP Riverview) | 2022-04-26 07:00 | 2022-04-26 17:00 | N | Y | tank heater repair | Circuit Breaker | RW2401 (EPCOR Riverview) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 299s Kingman | 2022-04-26 07:00 | 2022-04-26 18:00 | N | N | customer repairs to 4160V bus | Station |  |  | For Information Only
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2022-04-26 07:00 | 2022-04-27 11:00 | N | N | insulator washing on 729L structures 205-209, 241256, 259, 260 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 876L (179s Gleichen - 253s Blackie) | 2022-04-26 07:15 | 2022-04-28 17:45 | N | Y | emergency repair; clearance mitigation at Str 219 repair damaged conductor at Strs 202/222/223/254 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 77s 552 (77s Sagitawah) | 2022-04-26 07:30 | 2022-04-27 16:30 | N | N | replace leaking center phase CT | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 170L (632s Russell - 799s Coleman) | 2022-04-26 08:00 | 2022-04-28 18:00 | N | Y | 170L required to be out of service for 799s to 632s fiber relocation (reference 279293) | Line | WebOMS outage id #:11669267 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2022-04-26 08:00 | 2022-04-26 16:00 | N | N | HV breaker maintenance HV - SF6 gas sample | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 238s Shell Harmattan | 2022-04-26 08:00 | 2022-04-26 12:30 | N | N | create open point 'A' | Station |  |  | For Information Only
Saskpower | SASK POWER P2C | 2022-04-26 12:00 | 2022-04-30 14:00 | N | Y | maintenance | Line |  | P2C Line, PR 904BKR, PR 906BKR | For Information Only
ALTALINK | 238s Shell Harmattan | 2022-04-26 12:30 | 2022-04-30 13:30 | N | N | 138kV and 25kV T1 bushings replacement, T1 leaks fix, maintenance, doble VR1, leaks fix, maintenance, doble. Station service SS1 and AC distribution panel replacement | Station |  |  | For Information Only
ATCO | 888s 905 (888s Dover) | 2022-04-26 14:01 | 2022-04-26 17:00 | N | Y | RAS and DFR addition to 9L74 | Circuit Breaker |  | RAS and DFR addition to 9L74 | 240 kV, Pre-Condition
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power) | 2022-04-27 07:00 | 2022-04-28 10:00 | N | Y | customer maintenance | Line |  | Customer outage for their maintenance. Iconic to ground 503L under Customer isolation to facilitate the Customer's work. Transition to 279736 268s 69kV Bus & 503L - GOI. | Pre-Condition, Restricts Generation
EPCOR | RW2402 (EP Riverview) | 2022-04-27 07:00 | 2022-04-27 17:00 | N | Y | tank heater repair | Circuit Breaker | RW2402 (EPCOR Riverview) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 99s 747X (99s North St. Albert), 747L (99s North St. Albert - 711L tap), 99s T1 (99s North St. Albert) | 2022-04-27 07:00 | 2022-04-27 17:00 | N | N | complete CT contributions, testing and PTI cutover to new building | Circuit Breaker, Line, Transformer |  | Complete CT contributions from relocated 138Kv A Bus protection from T1 and 152. Trip testing from relocated 138Kv A Bus protection. Complete PT1 cutover to new control building VT Distribution. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 156L (19s Wabamun - 235s Entwistle) | 2022-04-27 07:00 | 2022-04-27 17:00 | N | N | creating 165s open points 'C' and installing 471s mobile substation | Line | 156L (19s Wabamun - 235s Entwistle) |  | For Information Only, Pre-Condition
ALTALINK, SHELL | 807L (410s Josephburg - 402s Scotford Expansion), 807L (233s Beamer - 807AL tap), 402s 252 (402s Scotford Expansion One), 402s 652 (402s Scotford Expansion One) | 2022-04-27 07:15 | 2022-04-28 15:15 | N | N | wire digital fault recorder (DFR), updating relays at 402s, 410s, and 233s | Line, Circuit Breaker |  | Wire digital fault recorder (DFR) from AltaLink Panels in 402s (CT652, CT252, 652PT) from relays 87L-A & 87L-B/807AL. As part of this outage AltaLink will be updating relays at 402s, 410s, and 233s to provide voltage and current signals for new DFR. 410s MPLS, | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 788L (157s Lac La Biche - 788AL tap), 157s 788N (157s Lac La Biche) | 2022-04-27 07:30 | 2022-04-28 14:30 | N | N | replace 6 grading capacitors on 157s788N | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 235s Entwistle | 2022-04-27 07:30 | 2022-04-27 16:30 | N | N | 25 kV breaker and feeder work | Station |  | DTT transfer trip tests to DG. It is required for the breaker to be racked out, into the test position. | For Information Only
ALTALINK | 33s 3 (33s Spray) | 2022-04-27 08:00 | 2022-04-28 17:00 | N | Y | maintenance | Switch |  | SP1 Minor Maintenance | Restricts Generation
ALTALINK | 33s 6 (33s Spray) | 2022-04-27 08:00 | 2022-04-28 17:00 | N | Y | maintenance | Switch |  | TAU SP2 Minor Maintenance | Restricts Generation
ENMAX | 24.82L (ENMAX 24 - ENMAX 65), 24.2TR (ENMAX 24) | 2022-04-27 08:00 | 2022-04-27 16:00 | N | N | HV breaker maintenance 24B138-24.82 | Line, Transformer |  |  | Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8), 3.3TR (ENMAX 3) | 2022-04-27 08:00 | 2022-04-27 12:00 | N | N | summer substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-2 29PT-2 (29EDD-2 Tar Island) | 2022-04-27 08:00 | 2022-04-27 18:00 | N | N | A protection relay settings change | Transformer |  |  | For Information Only
ATCO | 9L30 (888s Dover - 951s Thickwood), 951S 904 (951s Thickwood Hills), 951s 905 (951s Thickwood Hills), 888s 910 (888s Dover), 888s 911 (888s Dover) | 2022-04-27 08:00 | 2022-04-28 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Line, Circuit Breaker |  | Wire DFR into existing CT circuit and wire breaker status to DFR | 240 kV, For Information Only
ATCO | 7L24 (846s Grand Centre - 7LA24 tap) | 2022-04-27 08:00 | 2022-04-27 17:00 | N | Y | relocate structures 188, and 189, for road widening project (AB transportation) | Line |  | GOI required on 7L24 to relocate structures 188, and 189, for road widening project(AB transportation). | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 825s 908C (825s Whitefish Lake) | 2022-04-27 09:00 | 2022-04-29 17:00 | N | Y | check and test individual cans for failure | Shunts |  | 908C OOS to check and test individual cans for failure, This is related to alarms received on February 25, 2022. | 240 kV, Pre-Condition
CapitalPower | WHT1 Whitla | 2022-04-27 10:00 | 2022-04-27 12:00 | N | N | communication outage | Unit |  | Unit Whitla 1 Start Date April 12,2022 Start Time 10:00 MST End Date April 12, 2022 End Time 12:00 MST Description The work to be done is part of a project for Vestas Jumpbox Integration. The work involves a B2B connection changeover that will only disrupt the Vestas remote connection to VOB. There are no planned impacts to EMOC's VOB connection but there is a risk of possible small disruptions. There will be no impact to site communications, generation, or EMOC's ability to dispatch. Minimum Load Requirement NA Available Capacity 202.0 MVAR NA AS Availability NA | For Information Only
CMH | MHS-6 MH69-611 (MHS-6 CMH Riverview), MH-20L (MH69S-3 South Ridge - MH69S-6 Riverview), MHS-6 MH138-620 (MHS-6 CMH Riverview), MH69s6 MH69-T63 (MH69s6 Riverview) | 2022-04-27 10:00 | 2022-04-29 13:00 | N | N | PRC-005 - tapchanger maintenance | Circuit Breaker, Line, Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-6 Riverview substation. The T-63 75/100/125 MVA 138/69 kV power transformer will be de-energized and isolated at MH69-610 69 kV disconnect switch and MH138-621 138 kV disconnect switch. | For Information Only
ALTALINK | 729L (542s Ervick - 729AL tap) | 2022-04-27 11:00 | 2022-04-27 18:00 | N | N | insulator washing on 729L structures 25, 27 to 30, 121 to 123, 125, 198, 199 | Line |  | Insulator washing on 729L structures 25, 27 to 30, 121 to 123, 125, 198, 199 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 3.84L (ENMAX 3 - ENMAX 13), 3.4TR (ENMAX 3) | 2022-04-27 12:00 | 2022-04-27 18:00 | N | N | summer substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 688L (199s East Airdrie - 653s Summit), 688AL (284s Nosecreek - 688L tap) | 2022-04-27 17:00 | 2022-04-27 17:30 | N | Y | momentary de energizing 688L to use breaker at 199s688 to energize new TX at 284s | Line |  | momentary De energizing 688L to use breaker at 199s688 to energize new TX at 284s | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 165s T1 (165s Gainford) | 2022-04-27 17:00 | 2022-06-27 07:00 | N | N | replacing T1 with a new transformer | Transformer |  | Replacing T1 with a new transformer. 471s Mobile Substation will be feeding station load. | For Information Only
ALTALINK | 744L (235s Entwistle - 744AL tap) | 2022-04-28 06:00 | 2022-04-28 16:00 | N | N | Insulator washing on 744L structures 1A to 21A, 5 to 11 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 814s T2 (814s Bellamy), 814s B2402 (814s Bellamy), 814s B2406 (814s Bellamy), T1 (Rossdale), RR723 (Rossdale), R721 (Rossdale) | 2022-04-28 07:00 | 2022-04-29 17:00 | N | Y | BDS18 repair/maintenance, Doble Bellamy TX2 PT | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ATCO | 7L53 (700s Bonnyville - 7L53 tap) | 2022-04-28 08:00 | 2022-04-28 17:00 | N | N | add new structure 782A, and relocate structure 783 for intersection widening project (AB Transportation) | Line |  | GOI required on 7L53 to add new structure 782A, and relocate structure 783 for intersection widening project(AB Transportation). | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 24B138-24BT3 (ENMAX 24) | 2022-04-28 08:00 | 2022-04-28 16:00 | N | N | HV Breaker maintenance 24B138-24BT3 | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 9L112 (888s Dover - 951s Thickwood), 888s 911 (888s Dover), 888s 912 (888s Dover) | 2022-04-28 08:00 | 2022-04-28 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Line, Circuit Breaker |  | Wire DFR into existing CT circuit and wire breaker status to DFR | 240 kV, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43), 43.1TR (ENMAX 43), 9B138-9.83 (ENMAX 9) | 2022-04-28 08:00 | 2022-04-28 12:00 | N | N | summer substation washing | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, BHE | 879AL (719s Rattlesnake Ridge - 879L), 719s 138CB1 (719s Rattlesnake Ridge) | 2022-04-28 08:00 | 2022-04-28 15:00 | N | Y | test trip 719s (Rattlesnake) breaker 138CB1 for implementation of new RAS scheme | Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 268s 69kV Bus (268s Whitecourt), 503L (268s Whitecourt - 323s Whitecourt Power), 526L (268s Whitecourt - 520L tap) | 2022-04-28 09:00 | 2022-04-28 17:00 | N | Y | maintenance on 268s269, 268s68, & 268s24 | Bus, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 43.2TR (ENMAX 43) | 2022-04-28 12:00 | 2022-04-28 18:00 | N | N | summer substation washing, check reversing Switch (X), (Y) | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s T1 (370s North Lethbridge) | 2022-04-28 17:30 | 2022-07-01 10:00 | N | N | Install breaker foundation and breaker between 370s3 and T1 | Transformer |  | Install breaker foundation and breaker between 370s3 and T1. Temp transfer trip to be setup to allow DG to generate via 370sT4 | For Information Only
ENMAX | 33.1TR (ENMAX 33) | 2022-04-29 08:00 | 2022-05-04 11:50 | N | N | urgent reair | Transformer |  |  | For Information Only
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2022-04-29 08:00 | 2022-04-29 16:00 | N | N | HV breaker maintenance HV - SF6 gas sample | Line |  | HV breaker maintenance 32B138-32.83. HV - SF6 gas sample - 32B138-32.83 | Creates Radial Feeds, Firm Load Loss
ATCO | 9L07 (951s Thickwood - 2011s Dawes) | 2022-04-29 08:00 | 2022-04-29 17:00 | N | Y | wire DFR into existing CT circuit and wire breaker status to DFR | Line |  | Wire DFR into existing CT circuit and wire breaker status to DFR | 240 kV, Pre-Condition
ATCO | 801s 901T (801s Anderson) | 2022-04-29 08:00 | 2022-05-01 12:00 | N | Y | wheatland project 801s protection upgrade (P1718) | Transformer |  | WHEATLAND WIND FARM PROJECT 801S Anderson Sub Protection Upgrade | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 21s T1 (21s Marion) | 2022-04-29 08:30 | 2022-04-29 16:30 | N | N | drop oil on T1 to mitigate any further leaks from the transformer | Transformer |  |  | For Information Only
ATCO | 846s 701 (846s Grand Centre), 7L28 (717s Ethel Lake - 846s Grand Centre) | 2022-04-29 10:00 | 2022-04-29 16:00 | N | Y | run a span of wire to connect 7L28 to the 144KV bus by 700D1 | Circuit Breaker, Line |  | GOI for 7L28 to run a span of wire to connect 7L28 to the 144KV bus by 700D1. This will be used the week of May 16th to tap up the mobile sub for 701TS and 702TCS O&M work. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 238s Shell Harmattan | 2022-04-30 13:30 | 2022-04-30 17:30 | N | N | close open point 'A' | Station
SUNCOR | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2022-05-01 06:10 | 2022-05-10 22:00 | N | N | disconnect switch arcing | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
Syncrude | Mildred T4 (Syncrude Mildred Lake) | 2022-05-01 08:00 | 2022-05-04 11:50 | N | Y | mainteance | Transformer |  |  | Restricts Generation
EPCOR | T1 (Meadowlark) | 2022-05-02 07:00 | 2022-05-14 18:00 | N | N | secondary feeder recabling | Transformer |  |  | For Information Only
EPCOR | 330p 1206 (330p Genesee) | 2022-05-02 07:00 | 2022-05-06 17:00 | N | Y | CT doble, breaker maintenance | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | 814s T2 (814s Bellamy), T1 (Rossdale), BR722 (Rossdale), R721 (Rossdale) | 2022-05-02 07:00 | 2022-05-05 17:00 | N | Y | P&C maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s C2406 (987s Clover Bar) | 2022-05-02 07:00 | 2022-05-06 17:00 | N | Y | CT/breaker doble and breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 805s T3 (805s Jasper) | 2022-05-02 07:00 | 2022-05-02 17:00 | N | Y | temporary arc flash protection removal | Transformer |  |  | 240 kV, For Information Only
CMH | MHS7 T71 (MHS7 Brier Park) | 2022-05-02 07:30 | 2022-05-04 09:00 | N | N | PRC-005 tapchanger maintenance | Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-7 Brier Park substation. The T-71 75/100/125 MVA 138/69 kV power transformer will be de-energized and isolated at MH69-725 69 kV disconnect switch and MH138-724 138 kV disconnect switch. | For Information Only
ENMAX | 162B240-RB135 (ENMAX 162) | 2022-05-02 08:00 | 2022-05-02 12:00 | N | Y | trip testing | Circuit Breaker | CEC trip testing |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 1024s Granlea, 964AL (1024s Granlea - 964L tap), 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea) | 2022-05-02 08:00 | 2022-05-09 16:00 | N | N | P1912 Suncor Forty Mile Granlea WAGF Phase 1. ISD May 2, 2022 | Station, Line, Transformer
ENMAX | 14.4TR (ENMAX 14) | 2022-05-02 08:00 | 2022-05-12 16:00 | N | N | power factor test transformer, secondary cable testing, transformer maintenance, gas relay testing, oil sampling MT, TC. check reversing switch | Transformer |  |  | For Information Only
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2022-05-02 08:00 | 2022-05-02 16:00 | N | N | HV breaker maintenance | Line | HV Breaker maintenance 33B138-33.84. HV - SF6 Gas Sample - 33B138-33.84 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.1TR (ENMAX 40) | 2022-05-02 08:00 | 2022-05-05 16:00 | N | N | power factor test transformer, secondary cable testing, relays, gas testing, transformer maintenance, oil sampling MT, TC, replace PRD junction box | Transformer |  | Power factor test transformer. Secondary Cable Test. Relays, Gas Testing. Transformer Maintenance. Oil Sampling MT, TC. Replace PRD Junction Box | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-05-02 08:00 | 2022-09-30 18:00 | N | N | 29PP-901 | Not In Model | Unmodeled Transmission Facility (Suncor) | 29PP-901 - Poor seal / Insulation | For Information Only
Syncrude | Syncrude Mildred Lake | 2022-05-02 08:00 | 2022-05-05 20:00 | N | N | CB 1315 will be operated | Station | Non-Significant Outage: Plant 31 Substation 72kV "A" Buss: The following 72/13.8kV South West tail feeder will be offline: CB: 1315 will be operated. |  | For Information Only
Saskpower | SASK POWER P2C | 2022-05-02 08:00 | 2022-05-06 15:00 | N | Y | maintenance | Line |  | P2C Line, PR 904BKR, PR 906BKR | Pre-Condition
FORTIS | Namaka Solar DER | 2022-05-02 08:00 | 2022-06-04 16:00 | N | N | P1932 Fortis 428s Namaka DER Solar. 20 MW. ISD May 28, 2022 | Unit
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2022-05-02 08:00 | 2022-05-04 08:00 | N | Y | walk up/ climbing inspection | Line | 7L68 (730s Rycroft - 811s Clairmont Lake) | Walk Up/ Climbing Inspection | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2022-05-02 08:00 | 2022-05-11 18:00 | N | Y | protection upgrade | Line |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 718s 701 (718s Parsons Creek), 848s 702 (848s Ruth Lake), 7L47 (718s Parsons Creek - 848s Ruth Lake) | 2022-05-02 08:00 | 2022-05-05 15:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | 701 Breaker Maintenance @ 718s 702 Breaker Maintenance @ 848s | Pre-Condition
BCH | 1L274 (EFT - 1D2L274) | 2022-05-02 09:00 | 2022-05-03 17:00 | N | Y | replace timber and install makerballs | Line | 1L274 (EFT - 1D2L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 391s T1 (391s Balzac) | 2022-05-02 09:15 | 2022-05-03 16:45 | N | N | replace 6 grading capacitor on 391s30 minimum oil breaker | Transformer |  |  | For Information Only
ATCO | 721s 701T (721s La Corey) | 2022-05-02 09:30 | 2022-05-05 16:15 | N | N | maintenance | Transformer |  | 701T Transformer Maintenance | For Information Only
ALTALINK | 99s 712X (99s North St. Albert), 712L (99s North St. Albert - 595s Spruce Grove) | 2022-05-02 09:30 | 2022-05-02 17:30 | N | N | complete CT contributions, trip testing from relocated 138Kv A Bus protection | Circuit Breaker, Line | Complete CT contributions from relocated 138Kv A Bus protection from 99s712x. Trip testing from relocated 138Kv A Bus protection. |  | Creates Radial Feeds, Firm Load Loss
Saskpower | Sask Power P2P | 2022-05-02 10:00 | 2022-05-06 15:00 | N | Y | maintenance | Line |  | P2C Line, PR 904BKR, PR 906BKR | Limits ATC
ATCO | 876S 901TD (876s Brintnell), 876s 901T (876s Brintnell), 876S 901A (876s Brintnell), 876S 906A (876s Brintnell) | 2022-05-02 11:00 | 2022-05-03 17:00 | N | Y | maintenance and repair | Switch, Transformer |  | 901T Transformer and 501VR regulator maintenance, 901TD repairs - 240kV GOI point to 901TD after repairs on 901TD are complete. See GOI 2-63705 25Kv Load will be transferred to 876S 902T | 240 kV, Contingency Requires Mitigation
ENMAX | 162B240-RB134 (ENMAX 162) | 2022-05-02 12:00 | 2022-05-02 16:00 | N | Y | trip testing | Circuit Breaker | CEC trip testing |  | 240 kV, Contingency Requires Mitigation
ATCO | 801s 705 (801s Anderson), 7L85 (801s Anderson - 803s Bullpound) | 2022-05-02 13:00 | 2022-05-05 17:30 | N | N | Wheatland Wind Farm Project protection upgrades (P1718) | Circuit Breaker, Line |  | WHEATLAND WIND FARM PROJECT 801S 7L85 protection upgrades | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.1TR (ENMAX 22) | 2022-05-03 08:00 | 2022-05-05 16:00 | N | N | tapchanger maintenance (X), (Y), oil sampling MT TC(X), (Y) | Transformer |  |  | For Information Only
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2022-05-03 08:00 | 2022-05-03 17:00 | N | Y | integrate anti-island scheme and install breaker maintenance switches | Line |  | line outage to integrate anti-island scheme and install breaker maintenance switches for 562s1352 and 562s1452 | Overload, Pre-Condition
ENMAX | 65B138-D81 (ENMAX 65) | 2022-05-03 08:00 | 2022-05-03 16:00 | N | N | breaker maintenance and trip circuit testing | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 437s Baymag, 754L (118s Canmore - 437s Baymag), 754L (437s Baymag - 742L tap) | 2022-05-03 08:15 | 2022-05-05 15:45 | N | N | replace faulting switch 437s19 & 437s20 | Station, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2022-05-03 09:00 | 2022-05-03 14:00 | N | Y | high-load move between structures 143-144 | Line |  | 202L GOI required for completion of high-load move between structures 143-144. (Carrier PO-DV2203-2) | Overload, Pre-Condition, Affects Cranking Path
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2022-05-03 09:00 | 2022-05-06 17:00 | Y | Y | station work at NIC, BC maintenance does not affect the Alberta ATC | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 138S R2 (138s Windy Flats), 138s 1752 (138s Windy Flats) | 2022-05-03 09:30 | 2022-05-05 17:30 | N | Y | maintenance, doble | Shunts, Circuit Breaker |  | maintenance, doble (R1). 138kV Breaker Maintenance (138s1652) | 240 kV, Pre-Condition
ALTALINK | 887s T1 (887s Mobil Oil Carson Creek) | 2022-05-03 09:30 | 2022-05-04 17:30 | N | N | fix T1 leaks, change 69kV bushings, replace 3 pin caps and strain insulators on transformer low side bus | Transformer |  |  | For Information Only
ALTALINK | 263s 870E (263s Strachan), 870L (262s Rocky Mountain House - 263s Strachan) | 2022-05-03 09:30 | 2022-05-03 17:30 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 876s 901T (876s Brintnell) | 2022-05-03 17:00 | 2022-05-06 15:00 | N | Y | transformer and regulator maintenance 901T Out of service 25Kv | Transformer |  | 901T Transformer and 501VR regulator maintenance 901T Out of service 25Kv Load transferred to 876S 902T under GOI 2-63704 | 240 kV, For Information Only
AESO-SC | OATI | 2022-05-03 18:00 | 2022-05-03 19:00 | N | N | Inter-Site Transfer business continuity drill | SCInternal |  | O | For Information Only
ALTALINK | 250p 22 (250p Bighorn Plant) | 2022-05-03 23:00 | 2022-05-05 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
SUNCOR | 29PL9-12 (29EDD-34 - 29EDD-65), 29EDD-34 29-952-122 (29EDD-34), 29EDD-34 29-952-123 (29EDD-34) | 2022-05-04 06:00 | 2022-05-13 18:00 | N | Y | PRC-023 settings update and maintenance | Line, Circuit Breaker |  | 29EDD34;29PL9-12 SYSTEM;PM 5y,10y & PRC-023 settings update | 240 kV
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-05-04 07:00 | 2022-05-15 18:00 | N | N | 174L phase 3 rebuild, structures 539 to 691 | Line |  | Outage required for 174L Phase 3 Rebuild, Structures 539 to 691 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 718L (250p Bighorn Plant - 263s Strachan), 263s C1 (263s Strachan), 263s 138kV Bus 1 (263s Strachan), 263s T1 (263s Strachan), 250p 718 (250P Bighorn Plant), 262s 870W (262s Rocky Mountain House) | 2022-05-04 07:00 | 2022-05-05 04:30 | N | Y | urgent - conductor repair, switch and insulator replacement | Line, Shunts, Bus, Transformer, Circuit Breaker |  | 1st scope) P5 Urgent repair conductor 718L170 2nd scope) Replace 263s1(motor operated switch), replace strain insulators on 718L and 870L | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s 252 (77s Sagitawah), 77s 452 (77s Sagitawah) | 2022-05-04 07:00 | 2022-05-04 18:00 | N | N | maintenance on structure 799L712 | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2022-05-04 07:00 | 2022-06-15 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 910s 701T (910s Excel) | 2022-05-04 07:00 | 2022-05-04 17:00 | N | N | station inspection | Transformer |  | To hang grounds inside 910s for the following work: TC Energy Electrical Outage Request for: Oyen Pump Station M36 Station Electrical Inspection (@ 910S EXCEL) | For Information Only
ALTALINK | 99s T2 (99s North St. Albert) | 2022-05-04 07:00 | 2022-05-04 17:00 | N | N | testing | Transformer |  | Complete CT contributions from relocated 138Kv A Bus protection from T2. Trip testing from relocated 138Kv A Bus protection to 99s273x & 99s2205. | For Information Only
SUNCOR | 29PL9-12 (29EDD-34 - 29EDD-65), 29EDD-65 29-952-4811 (29EDD-65), 29EDD-65 29-952-4812 (29EDD-65) | 2022-05-04 08:00 | 2022-05-13 18:00 | N | Y | maintenance | Line, Circuit Breaker |  | 29EDD65 ;29PT-259 SYSTEM;PM 5y line 29PL9-12 | 240 kV, For Information Only
ENMAX | 65B240-D130 (ENMAX 65) | 2022-05-04 08:00 | 2022-05-04 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 65B240-D130 | 240 kV, Contingency Requires Mitigation
ALTALINK | 457L (167s Ipiatik Lake - 651s Kirby), 167s 1652 (167s Ipiatik Lake) | 2022-05-04 08:30 | 2022-05-04 16:30 | N | N | tank heater repairs | Line, Circuit Breaker |  |  | Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2022-05-04 09:00 | 2022-05-04 14:00 | Y | Y | install wood pole structures and bypass conductor underneath 1L274 & the tap to FRO on the POC side of BCK | Line | 1L274 (EFT - 1D2L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 433L (291s Cochrane - AML 793s Horse Creek), AML 793s 433 (AML 793s Horse Creek) | 2022-05-04 09:15 | 2022-05-05 16:45 | N | N | replace 6 grading capacitor on 793s433 minimum oil breaker | Line, Circuit Breaker | 433L (291s Cochrane - AML 793s Horse Creek) | Replace 6 grading capacitor on 793s433 minimum oil breaker | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-10L (MHS10 - MHS8 Burnside), MHS8 T81 (MHS8 Burnside), MHS-8 MH69-802 (MHS-8 Burnside), MHS-8 MH138-803 (MHS-8 Burnside), MH-12L (MHS8 Burnside  MHS6 Riverview) | 2022-05-04 10:00 | 2022-05-06 13:00 | N | N | PRC-005 - tapchanger maintenance | Line, Transformer, Circuit Breaker |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-8 Burnside substation. The T-81 75/100/125 MVA 138/69 kV power transformer will be de-energized and isolated at MH69-801 69 kV disconnect switch and the MH138-804 138 kV disconnect switch. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
CNRL | 838s 75-TR-1801 (838s Horizon Mining) | 2022-05-05 07:30 | 2022-05-09 18:00 | N | Y | 5 year PM (breakers, PRC-005) | Transformer | 838s 75-TR-1801 (838s Horizon Mining) |  | 240 kV
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2022-05-05 07:30 | 2022-05-05 12:30 | N | Y | fire risk mitigation; str 337 | Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 65B240-D131 (ENMAX 65) | 2022-05-05 08:00 | 2022-05-05 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 659s T1 (659s Pegasus Lake) | 2022-05-05 08:00 | 2022-05-05 17:30 | N | N | perform tests on T1 | Transformer
ATCO | 729s 705 (729s Otauwau), 7L49 (729s Otauwau - 732s Mitsue) | 2022-05-05 08:00 | 2022-05-13 17:00 | N | N | emergency outage | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 157s T1 (157s Lac La Biche) | 2022-05-05 10:00 | 2022-05-05 16:00 | N | N | investigate oil leak | Transformer
CHDI | SUM1 Summerview | 2022-05-05 11:00 | 2022-05-05 14:00 | N | N | software updaters | Unit
VISIONREQ | 354s Summerview | 2022-05-05 11:00 | 2022-05-05 14:00 | N | N | software updates | Station |  |  | Restricts Generation
ALTALINK | 914L (63s Red Deer - 87s Gaetz) | 2022-05-05 12:31 | 2022-05-05 17:30 | N | Y | fire risk mitigation | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
SUNCOR | 635PL7-1001 (635EDD-1000 - 635EDD-1001) | 2022-05-06 08:00 | 2022-05-16 17:00 | N | N | regulatory maintenance | Line | 635PL7-1001 Regulatory Maintenance on line, associated breakers, other equipment in isolation boundary and protection. |  | Creates Radial Feeds, Pre-Condition
ATCO | 790s 702T (790s Poplar Hill) | 2022-05-06 10:00 | 2022-05-17 14:00 | N | N | transformer & circuit switcher PM | Transformer |  | 790S 702T Transformer & circuit switcher PM, requires 902S mobile substation installation | Pre-Condition
ATCO | 790s 702T (790s Poplar Hill), 790s 702TCS (790s Poplar Hill) | 2022-05-06 14:00 | 2022-05-16 10:00 | N | N | transformer & circuit switcher PM | Transformer, Switch |  | Transformer & circuit switcher PM, requires 902S mobile substation installation | Pre-Condition
ALTALINK | 956L (59s Peigan - 103s Goose Lake) | 2022-05-07 07:00 | 2022-05-07 13:00 | N | N | maintenance on 956L80 | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
Saskpower | Sask Power P2P | 2022-05-07 07:00 | 2022-05-08 16:00 | N | Y | maintenance | Line |  | P2C Line, PR 904BKR, PR 906BKR | Limits ATC
ENMAX | 32B138-31.84 (ENMAX 32), 31.84L (ENMAX 31 - ENMAX 32) | 2022-05-07 08:00 | 2022-05-07 16:00 | N | N | 32B138-31.84 breaker mech exposed to adverse weather | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 39s 29 (39s Bickerdike), 39s 1052 (39s Bickerdike), 39s 1152 (39s Bickerdike), 39s T2 (39s Bickerdike), 39s 240kV Bus 2 (39s Bickerdike) | 2022-05-08 07:00 | 2022-05-12 18:00 | N | Y | install new 973L, 974L and 1168L into A-frames at 39S as part of Cascade project | Circuit Breaker, Transformer, Bus |  | RET Install NEW 973L, 974L and 1168L into A-frames at 39S as part of Cascade Project. New spans to 973L, 974L and 1168L A-frames to cross over 39s 240 kV bus 2. New Spans are not connected to the 39s yet. Close Open Points 'K',L,M,N. Note new 240kV Breakers not installed at this time. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2022-05-08 07:00 | 2022-05-12 18:00 | N | N | modify 740L between Str 51D and 51E | Line |  | Modify 740L between Str 51D and 51E. Install new 973L, 974L and 1168L into A-frames at 39S as part of Cascade Project. | Over/Under Voltage, Pre-Condition
CNRL | 838s 75-BC-1915 (838s Horizon Mining), 838s 75-BC-1916 (838s Horizon Mining), 838s 75-BC-1917 (838s Horizon Mining) | 2022-05-08 07:30 | 2022-05-15 18:00 | N | Y | testing of 260 kV circuit breakers and PRC-005 trip coil testing. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L85 (803s Bullpound - 804s Wintering Hills) | 2022-05-08 08:00 | 2022-05-13 17:00 | N | N | reroute line by adding 4-6 poles and moving the line out along its existing right away to allow the construction of the T-Tap portion down to 981s Badlands (P1718) | Line |  | WHEATLAND WIND FARM PROJECT Outage to reroute line by adding 4-6 poles and moving the line out along its existing right away to allow the construction of the T-Tap portion down to 981s Badlands. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | R721 (Rossdale), R723 (Rossdale), T2 (Rossdale) | 2022-05-09 07:00 | 2022-05-11 14:00 | N | N | P&C maintenance | Circuit Breaker, Transformer |  | Rossdale TX2 Zone Op-Checks, P&C Maintenance | Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition
EPCOR | 805s T1 (805s Jasper), 72JM18 (805s Jasper - Meadowlark), 72JW19 (805s Jasper - Woodcroft) | 2022-05-09 07:00 | 2022-05-13 17:00 | N | Y | surge arrestor replacement | Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T4 (805s Jasper) | 2022-05-09 07:00 | 2022-05-11 15:00 | N | Y | protection upgrade cutovers | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 330p 1207 (330p Genesee) | 2022-05-09 07:00 | 2022-05-13 17:00 | N | Y | breaker maintenance and CT doble | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 100L (498s Tilley - 895s Suffield) | 2022-05-09 07:15 | 2022-05-09 17:45 | N | Y | maintenance (Str 177) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | AML 511s FB Bus 1 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings) | 2022-05-09 07:30 | 2022-05-12 15:00 | N | Y | breaker and AC filter maintenance | Bus, Shunts | ABB Breaker and AC Filter Maintenance, 511s81 and 511s82 Disconnect Maintenance and Negative Fusing install project. Bird Mitigation on AC Filters. |  | 240 kV, Pre-Condition
CMH | MHS2 T23 (MHS-2 North Industria), MH-9L (MH69s2 North Industrial - MHS10) | 2022-05-09 07:30 | 2022-05-10 15:00 | N | N | PRC-005 - tapchanger maintenance | Transformer, Line |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-2 North Industrial substation. The T-23 75/100/125 MVA 138/69 kV power transformer will be de-energized and isolated at MH69-216 69 kV disconnect switch and MH138-219 138 kV disconnect switch. | Creates Radial Feeds, Firm Load Loss
ENMAX | 24.2TR (ENMAX 24) | 2022-05-09 08:00 | 2022-05-10 16:00 | N | N | tapchanger maintenance, oil sampling MT, TC | Transformer |  |  | For Information Only
ATCO | 951S 907 (951s Thickwood Hills), 951s 908 (951s Thickwood Hills), 9L01 (848s Ruth Lake - 951s Thickwood) | 2022-05-09 08:00 | 2022-05-16 12:00 | N | Y | construction on new breaker 909 and installation of gang switches relay settings change and testing on 908 (9L01) and operation of gang switch 9L01D2 | Circuit Breaker, Line |  | **This Permit is one of 3 permits replacing 2-49081 due to AESO request** May 9 -16, Outage on Breakers 907, 908 and Line 9L01. Construction on NEW breaker 909 and installation of gang switches. Relay settings change and testing on 908 (9L01) and operation of gang switch 9L01D2. Isolation points: 848S 9L01D1, 951S 907A, 951S 909A 907 OOS, 908 OOS and 9L01 OOS During this time the NEW bus work will also be in construction. | 240 kV, Pre-Condition
ENMAX | 47.1TR (ENMAX 47) | 2022-05-09 08:00 | 2022-05-13 16:00 | N | N | maintenance | Transformer |  | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas relay testing. Check Reversing Switch. Oil Sampling MT, TC. Secondary Cable Circulating Current Hazard | For Information Only
ENMAX | 65B240-D132 (ENMAX 65) | 2022-05-09 08:00 | 2022-05-09 16:00 | N | Y | HV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2022-05-09 08:00 | 2022-05-10 15:00 | N | N | walk up/ climbing inspection | Line |  | Walk Up/ Climbing inspection 730S SVC addition and 144 kv bus rebuild. Relocate Bypass between 7L68 & 7L10 for Sub Expansion Install new bypass switch 7L68D3 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Syncrude | Mildred T4 (Syncrude Mildred Lake) | 2022-05-09 08:00 | 2022-05-12 16:40 | N | N | 4435 and 435 will be operated | Transformer |  |  | Restricts Generation
ENMAX | 33.2TR (ENMAX 33) | 2022-05-09 08:00 | 2022-05-11 16:00 | N | N | investigate dev. 90 PT | Transformer |  |  | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2022-05-09 09:00 | 2022-05-13 17:00 | Y | Y | install wood pole structures and bypass conductor underneath 1L274 & the tap to FRO on the POC side of BCK | Line | 1L274 (EFT - 1D2L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ENMAX | 15.60L (ENMAX 15 - ENMAX 21) | 2022-05-09 09:00 | 2022-05-09 10:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 721s 702T (721s La Corey) | 2022-05-09 09:00 | 2022-05-11 17:30 | N | N | 702T transformer maintenance & 25kv switch repair, load transferred to 701T | Transformer |  | 702T Transformer Maintenance & 25kv switch repair, load transferred to 701T | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2022-05-09 10:00 | 2022-05-09 11:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 843s 601T (843s Bigknife Creek) | 2022-05-09 10:00 | 2022-05-12 17:30 | N | N | class 2 major testing 601T @ 843S | Transformer |  | TRANSFORMER CLASS2 MAJOR TESTING 601T @ 843S | For Information Only
ALTALINK | 336s T1 (336s Fincastle) | 2022-05-09 10:15 | 2022-05-13 17:45 | N | N | replacement of 25kV & 138kV LA's | Transformer |  |  | For Information Only
ALTALINK | 191s T1 (191s N.W. Cardiff) | 2022-05-09 11:00 | 2022-05-12 17:00 | N | N | T1: fix leaks, maintain, doble, fix fan VR1: maintain, doble, 191s6 VT sweating, inspect | Transformer |  |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2022-05-09 11:00 | 2022-05-09 12:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 437s T2 (437s Baymag) | 2022-05-09 12:30 | 2022-05-13 14:30 | N | N | protection upgrade project for transformer T2; upgrading A and B protections | Transformer |  |  | For Information Only
SUNCOR | 29EDD-94 406T (29EDD-94), 29EDD-94 29-952-9702 (29EDD-94 Voyageur), 29EDD-94 29-952-9703 (29EDD-94 Voyageur) | 2022-05-09 16:00 | 2022-05-18 18:00 | N | Y | maintenance and test | Transformer, Circuit Breaker |  | to be done consecutively one after the other 29EDD94;29-952-9702 MAIN & TEST;PM 10y 29EDD94;29-952-9703 MAIN & TEST;PM 10y 29EDD94;29PT-406 SYSTEM;PM 5y,10y 29EDD94;29PP-84 SYSTEM;PM 5y,10y | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 983L (244s Bowmanton - 251s Whitla) | 2022-05-10 07:00 | 2022-05-11 18:00 | N | Y | re-wire trip circuits, add breaker status for RAS functions and tie in CTs for SEL 451s | Line |  | Re-wire 251s552 and 251s652 trip circuits, add breaker status to L4 protections for RAS functions, re-wire 244s552 and 244s652 trip circuits, add breaker status for RAS at 244s and tie in CTs for SEL 451s at 244s | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 234L (310p Sundance - 505L tap), 234L (133L tap - 505L tap), 505L (234L tap - 505L tap), 521AL (867s Sundance Blow-Down - 521L tap), 521L (505L tap - 521AL tap) | 2022-05-10 07:00 | 2022-05-10 18:00 | N | N | urgent correct insufficient clearance from the bottom phase to the top strut guy off structure 234L82 / 521L33 | Line |  | *P5 Urgent- Correct insufficient clearance from the bottom phase to the top strut guy off Structure 234L82 / 521L33 | For Information Only
ALTALINK | 668L (394s Empress - 562s Cypress), 394s 668 (394s Empress) | 2022-05-10 07:30 | 2022-05-10 17:30 | N | N | integrate anti-island scheme | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 38s 7152 (38s East Edmonton) | 2022-05-10 07:30 | 2022-05-10 16:30 | N | Y | replace 1 grading capacitor on 38s7152 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 65B240-D133 (ENMAX 65) | 2022-05-10 08:00 | 2022-05-10 16:00 | N | Y | HV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2022-05-10 08:30 | 2022-05-12 18:00 | N | N | maintenance and doble testing | Transformer |  |  | For Information Only
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2022-05-10 09:00 | 2022-05-11 16:00 | N | N | urgent work to restore cap bank back into service from real time lockout, replace cap on cap bank and weed spraying | Shunts |  |  | Pre-Condition
ATCO | 718s 702T (718s Parsons Creek) | 2022-05-10 09:00 | 2022-05-13 16:00 | N | N | 702T maintenance | Transformer |  | 702T Maintenance | For Information Only
EPCOR, CapitalPower | 330p Genesee, Clover Bar Energy Centre | 2022-05-10 11:00 | 2022-05-10 12:00 | N | N | SCADA Upgrade | Station, SCInternal |  |  | Affects Visibility
ALTALINK | 89s 352 (89s Ellerslie) | 2022-05-11 07:30 | 2022-05-11 16:30 | N | Y | replace 1 grading capacitor on 89s352 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 394s 952 (394s Empress) | 2022-05-11 07:30 | 2022-05-11 17:30 | N | N | integrate anti-island scheme | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 223s T3 (223s Strome) | 2022-05-11 08:00 | 2022-05-12 17:30 | N | N | maintenance and testing | Transformer |  |  | For Information Only
ALTALINK | 33s 3 (33s Spray) | 2022-05-11 08:00 | 2022-05-11 12:00 | N | Y | maintenance | Switch | 33s3 Advice for TAU SP1 Blackstart testing |  | Restricts Generation
ENMAX | 39.1TR (ENMAX 39) | 2022-05-11 08:00 | 2022-05-12 16:00 | N | N | tapchanger maintenance, oil sampling, bushing, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 65B240-D134 (ENMAX 65) | 2022-05-11 08:00 | 2022-05-11 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2022-05-11 09:00 | 2022-05-13 17:00 | Y | Y | flashed insulator replacements, BC maintenance does not affect the Alberta ATC | Line |  |  | Limits ATC, 500 kV
CMH | MH69s2 T22 (MH69s2 North Industrial) | 2022-05-11 10:00 | 2022-05-13 13:00 | N | N | PRC-005 - tapchanger maintenance | Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-2 North Industrial substation. The T-22 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 2S2-M 13.8kV main breaker and MH69-214 69kV disconnect switch. | For Information Only
ALTALINK | 33s 6 (33s Spray) | 2022-05-11 13:00 | 2022-05-11 17:00 | N | Y | maintenance | Switch | 33s6 Advice for TAU SP2 Blackstart testing |  | Restricts Generation
ALTALINK | 62s 11 (62s Brazeau Plant) | 2022-05-11 23:00 | 2022-05-12 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2022-05-12 03:00 | 2022-05-12 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 394s 760N (394s Empress), 760L (163s Amoco Empress - 394s Empress) | 2022-05-12 07:30 | 2022-05-12 17:30 | N | N | integrate anti-island scheme | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | WHT1 Whitla | 2022-05-12 08:00 | 2022-05-12 11:00 | N | N | communication outage | Unit |  | The work to be done is part of a project for Vestas Jumpbox Integration. The work involves a B2B connection changeover that will only disrupt the Vestas remote connection to VOB. There are no planned impacts to EMOC's VOB connection but there is a risk of possible small disruptions. There will be no impact to site communications, generation, or EMOC's ability to dispatch. | For Information Only
ENMAX | 65B240-D135 (ENMAX 65) | 2022-05-12 08:00 | 2022-05-12 16:00 | N | Y | HV breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 65B240-D135 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 826s 902T (826s Marguerite Lake) | 2022-05-12 08:30 | 2022-05-13 18:00 | N | Y | inspection and maintenance | Transformer |  | Check for moisture in 826S 902T 63T-MT junction boxes after spring melt. This will require a transformer outage. This is an action item for a PRC004 report due to a forced outage on Nov. 8th and 29th 2021 where the transformer locked out. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
Saskpower | Sask Power R1P | 2022-05-12 09:00 | 2022-05-12 12:00 | N | Y | maintenance | Line | R1P Line-RESS to L5 |  | Limits ATC
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2022-05-13 08:00 | 2022-06-03 16:00 | N | N | upgrading storm lines in the Sunnyside area | Line |  | LBCO contactors is working on behalf of the COC upgrading storm lines in the Sunnyside area | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 39s T2 (39s Bickerdike), 973L (39s Bickerdike - 310p Sundance), 39s 138kV Bus 2 (39s Bickerdike), 39s 240kV Bus 2 (39s Bickerdike) | 2022-05-14 08:00 | 2022-05-22 18:30 | N | Y | complete connection of 1135L to existing 973L bay  close open point P, 'G' & New 973L B, breaker testing | Transformer, Line, Bus |  | Complete connection of 1135L to existing 973L bay  Close Open Point P, Close Open Point G Complete breaker fail & T2 trip testing to 39s452, 39s852, 39s1152. Close N.O VT13 39s57. Add supervisory control to new 39s1152, put 39s1152 breaker into service. add Dev 43M maintenance switches to 39s1052, 39s1152, 39s26, & 39s29. Close Open Point New 973L B | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 21.61L (SS-21 - SS-34), 21.4TR (SS-21) | 2022-05-14 08:00 | 2022-05-14 18:00 | N | N | HV breaker maintenance, oils sampling and measurements | Line, Transformer |  | HV Breaker maintenance 21B69-21.4TR. Oil Sampling 21.4TR MT, Bushing. Measure SW62 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 349s T1 (349s Stavely) | 2022-05-14 09:00 | 2022-05-15 17:30 | N | Y | T1 maintenance & doble, valve leak repair, qualitrol sensor issue repair | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 226s 52/F1 (226s Garden City), 226s Garden City | 2022-05-14 20:36 | 2022-05-17 13:02 | N | N | investigate issue with 226s 52/F1 | Circuit Breaker, Station |  | - 52-F1 tripped offline likely due to cable splice failure, site staff investigating issue and require contractor support - Outage for loss of 15MW of capability | Restricts Generation
BCH | 1L274 (48s Pocaterra - Britt Creek), 1L274 (Britt Creek - 1D4L274) | 2022-05-15 08:00 | 2022-05-15 20:00 | Y | Y | building bypass around BCK | Line |  | Building bypass around BCK. During the outage FRO and BCK will be out of service. BC Hydro has requested on return switching to energize from 48s and make parallel at 1D4L274. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | EP 805s J722 (EP 805s Jasper) | 2022-05-15 12:00 | 2022-05-18 16:00 | N | N | forced outage | Circuit Breaker |  |  | For Information Only
ATCO | 9L02 (809s Louise Creek - 813s Little Smoky), 813s 906 (813s Little Smoky), 813s 908 (813s Little Smoky) | 2022-05-15 12:01 | 2022-06-12 12:00 | N | Y | 813S Little Smoky Rebuild - remove panels, breaker 905 and 906 P&C wiring, relay programming and functionality testing | Line, Circuit Breaker |  | 813S Little Smoky Rebuild Remove panels 5H,6H - install new panel 9P3 - BKR 905 and 906 P&C wiring, prep work Relay programming and functionality Commission control, alarms and status | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
SUNCOR, ACCIONA | 139s C1 (139s Hillridge), 139s 52-C (139s Hillridge) | 2022-05-15 15:10 | 2023-03-17 17:32 | N | N | repairs on the charging motor operating mechanism | Shunts, Circuit Breaker |  | Test | Pre-Condition
ATCO | 7L65 (709s Vegreville - 710s Vermilion), 709s 703 (709s Vegreville) | 2022-05-16 07:00 | 2022-05-19 12:00 | N | N | cut over outage for phase one rebuild on 7L65. stringing into A-Frame at 709s Vegreville | Line, Circuit Breaker |  | Cut over outage for phase one rebuild on 7L65. stringing into A-Frame at Vegreville sub 709S. | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 330p 1208 (330p Genesee) | 2022-05-16 07:00 | 2022-05-20 15:40 | N | Y | breaker maintenance and CT doble | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | 72CK13 (987s Clover Bar - Kennedale), K722 (Kennedale), T1 (Kennedale), 987s CK726 (987s Clover Bar) | 2022-05-16 07:00 | 2022-05-26 17:00 | N | N | line arrestors both ends doble disconnect maintenance and CK726 breaker maintenance | Line, Circuit Breaker, Transformer |  | Kennedale TX1 Zone and CK13 Line Arrestors both ends Doble and KAB1/KDS2/KDS3/KDS1/CDS15 Disconnect Maintenace and CK726 Breaker Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2022-05-16 07:00 | 2022-06-03 17:00 | N | Y | BA2 oil degassing | Line |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T3 (Rossdale), R723 (Rossdale), R724 (Rossdale) | 2022-05-16 07:00 | 2022-05-20 17:00 | N | N | zone op-checks, P&C maintenance | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
CMH | MH69s2 T21 (MH69s2 North Industrial) | 2022-05-16 07:30 | 2022-05-18 09:00 | N | N | PRC-005 - tapchanger maintenance | Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-2 North Industrial substation. The T-21 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 2S1-M 13.8kV main breaker and MH69-205 69kV disconnect switch. | For Information Only
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 804s 701 (804s Wintering Hills) | 2022-05-16 08:00 | 2022-05-20 17:00 | N | N | protection upgrade | Line, Circuit Breaker |  | WHEATLAND WIND FARM PROJECT 804S Wintering Hills Sub Protection Upgrade | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43), 9B138-9.83 (ENMAX 9), 43B138-9.83 (ENMAX 43) | 2022-05-16 08:00 | 2022-05-19 16:00 | N | N | HV breaker maintenance 9B138-9.83 | Line, Circuit Breaker |  | HV Breaker maintenance 43B138-9.83. HLR. HV Breaker maintenance 9B138-9.83. HLR. 9.83L DGA sample and sheath testing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 421s 30 (421s Hays), 421s C1 (421s Hays) | 2022-05-16 08:30 | 2022-05-19 16:30 | N | N | PT replacements | Circuit Breaker, Shunts |  |  | For Information Only, Pre-Condition
ATCO | 820s 701T (820s Hangingstone) | 2022-05-16 09:00 | 2022-05-19 17:00 | N | Y | maintenance | Transformer |  | 701T Maintenance | Pre-Condition
ALTALINK | 243s RTU/SCADA (243s Soderglen Wind Farm) | 2022-05-16 09:00 | 2022-05-20 17:00 | N | N | RTU replacement | Terminal Equipment |  |  | Affects Visibility
ATCO | 790s 704 (790s Poplar Hill), 790s 703T (790s Poplar Hill) | 2022-05-16 09:00 | 2022-05-19 17:30 | N | Y | replace 1 phase on 790S 704, 790S 703T maintenance | Circuit Breaker, Transformer | 7L46 oos 5/16 - 5/29 - ensure NPP1 available | Replace 1 phase on 790S 704, 790S 703T maintenance | Restricts Generation
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2022-05-16 09:00 | 2022-05-17 17:00 | N | Y | CBK 2D2CB5 & 2D1CB6 disconnect repairs and 2L113 conductor repair | Line | 2L113 (B1s Natal - B2s Cranbrook), CBK 2B5 OOS | CBK 2D2CB5 & 2D1CB6 Disconnect Repairs | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Pre-Condition
ATCO | 743s 702T (743s Sarah Lake) | 2022-05-16 10:00 | 2022-05-27 16:00 | N | N | testing breaker 706 and 502 status, testing 502VR | Transformer |  | testing Breaker 706 and 502 Status to 67-81-79-SPS/ 5L186 protection for DG addition. Testing 502VR controls and DG logic | For Information Only
Saskpower | SaskPower S1H | 2022-05-16 11:00 | 2022-05-19 19:00 | N | Y | maintenance | Line |  | replacing 4 structures and stringing across Lake Diefenbaker | Limits ATC
ALTALINK | 897L (38s East Edmonton - 45s Bretona), 38s 897 (38s East Edmonton) | 2022-05-16 12:00 | 2022-05-17 18:00 | N | N | components and structure replacements 897L, structure range ( 1-98 ) | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 951s 908 (951s Thickwood Hills) | 2022-05-16 12:00 | 2022-06-30 17:00 | N | Y | addition of NEW bus on 900BS2, construction, commissioning | Circuit Breaker |  | Addition of NEW bus on 900BS2, Construction, Commissioning During this time the NEW bus work will also be in construction. May 16 - 24 isolation points 951S 908B, 951S 909A | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s T2 (17s Benalto), 17s 85 (17s Benalto) | 2022-05-16 12:00 | 2022-05-19 17:30 | N | Y | fix leaks, maintain, test transformer | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2022-05-16 12:00 | 2022-05-19 18:00 | N | N | replacement of the CTs associated with breaker 352, 71s352 1st trip PRC5 maintenance, site glass and grading cap leak fix and investigate 71s726W has no remote operation, 71s252 gearbox site glass leaking oil | Line |  | Replacement of the CTs associated with breaker 352. 71s352 1st trip PRC5 maintenance, site glass and grading cap leak fix. Investigate 71s726W has no remote operation. 71s252 gearbox site glass leaking oil. | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 795L (121s Brooks - 421s Hays), 121s 795X (121s Brooks) | 2022-05-16 12:00 | 2022-05-16 14:00 | N | N | replace CT 121s795X | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 828L (178s Cynthia - 489s Petro Canada Brazeau River) | 2022-05-16 12:30 | 2022-05-19 17:30 | N | N | replace 138 kV CTs at 178s 828X | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 65B138-D82 (ENMAX 65), 65B138-D85 (ENMAX 65), 65.2TR (ENMAX 65), 138kV North Bus (ENMAX 65) | 2022-05-17 08:00 | 2022-05-19 16:00 | N | Y | oil sampling | Circuit Breaker, Transformer, Bus |  | Substation - Oil Sampling - 240-65.2-TC, MT. Check Reversing Switch. 65.2TR, TC Replace PRD Junction Box. 65PT138-Z32 swap | 240 kV, Contingency Requires Mitigation, Pre-Condition
SUNCOR | 635PT-1005, 635EDD-1000 635-752-122 (635EDD-1000), 635EDD-1000 635-752-123 (635EDD-1000) | 2022-05-17 08:00 | 2022-05-25 17:00 | N | N | maintenance and protection system testing | Terminal Equipment, Circuit Breaker |  | regulatory maintenance on transformer, associated breakers, other equipment in isolation boundary and protection system testing | For Information Only
ATCO | 755s 904 (755s Cordel) | 2022-05-17 10:00 | 2022-05-18 14:00 | N | Y | breaker SF6 GL315 complete testing | Circuit Breaker |  | BREAKER SF6 GL315 COMPLETE TESTING 904 | 240 kV, Contingency Requires Mitigation
ALTALINK | 151s 765W (151s Strathmore), 765L (151s Strathmore - 419s Chestermere) | 2022-05-17 11:00 | 2022-05-17 14:00 | N | Y | replace a CT terminal on the A RAS 179 relay | Circuit Breaker, Line |  | Replace a CT terminal on the A RAS 179 relay. Complete loop tests. RAS 179 ' A'Relay to be OOS as well, 'B' protection to remain in place to maintain redundancy | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 632L (325s Leduc - 538s Buford) | 2022-05-17 13:30 | 2022-05-17 17:00 | N | N | remove 472s mobile from the line side of 538s632 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 223s 44 (223s Strome), 223s T2 (223s Strome) | 2022-05-18 07:00 | 2022-05-19 17:00 | N | N | complete bushing monitor installation on T2 | Circuit Breaker, Transformer
ALTALINK | 727L (65s High River - 727AL tap), 727L (678s Okotoks - 727AL tap), 727AL (142s Magcan - 727L tap), 142s Magcan, 142s C1 (142s Magcan) | 2022-05-18 07:15 | 2022-05-18 14:00 | N | N | clearance violation structure change 727AL19 | Line, Station, Shunts |  |  | Pre-Condition
ALTALINK | 394s 36 (394s Empress), 394s T3 (394s Empress) | 2022-05-18 07:30 | 2022-05-18 17:30 | N | N | integrate anti-island scheme | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 7L153 (609s Wheatland - 804s Wintering Hills), 804s 703 (804s Wintering Hills) | 2022-05-18 09:00 | 2022-05-18 12:00 | N | Y | 703 PRC005 trip coil testing | Line, Circuit Breaker |  | 703 PRC005 trip coil testing. Wheatland Generation will be offline for the duration | Pre-Condition, Restricts Generation
ATCO | 859s 701 (859s Primrose), 859s 702 (859s Primrose) | 2022-05-18 10:00 | 2022-05-18 12:00 | N | N | DCS/SCADA testing one breaker at a time | Circuit Breaker |  |  | For Information Only
SHELL | 847s Muskeg River | 2022-05-18 13:00 | 2022-05-18 14:00 | N | N | SCADA work | Station |  |  | Affects Visibility
ALTALINK | 394s T4 (394s Empress), 394s 41 (394s Empress) | 2022-05-19 07:30 | 2022-05-19 17:30 | N | N | integrate anti-island scheme | Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
CNRL | 842s 75-TR-4701 (842s Horizon Upgrading), 842s 75-TR-7701 (842s Horizon Upgrading), 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2022-05-19 07:30 | 2022-05-28 18:00 | N | Y | 5 year PM (breakers, PRC-005) | Transformer, Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 6.4TR (ENMAX 6) | 2022-05-19 08:00 | 2022-05-20 16:00 | N | N | shutters on 6BA25-6.4TR do not work properly | Transformer | Hazard - S-AM - Shutters on 6BA25-6.4TR do not work properly |  | For Information Only
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2022-05-19 09:00 | 2022-05-24 09:00 | N | Y | tap up 2000s on the line side of 700D1 | Line |  | GOI for 7L28 to tap up 2000s on the line side of 700D1 Energize 2000S and soak | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2022-05-19 15:37 | 2022-06-01 10:30 | Y | Y | forced outage | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | STR1 Strathmore Solar DER, STR2 Strathmore Solar DER | 2022-05-20 07:00 | 2022-05-20 08:00 | N | N | re-booting the sites HMI RTAC to enable user audit logs function | Unit |  |  | For Information Only
ENMAX | 8.2TR (ENMAX 8) | 2022-05-20 08:00 | 2022-05-21 18:00 | N | N | protection replacement | Transformer | 8 Sub 8.2TR Protection Replacement. Transformer and bus outage required to change CT rations and commission |  | For Information Only
ATCO | 788s 703 (788s Hotchkiss), 7L63 (783s Cadotte River - 788s Hotchkiss) | 2022-05-20 09:30 | 2022-05-20 14:00 | N | N | Emergency outage - gas top up | Circuit Breaker, Line
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2022-05-20 12:01 | 2022-05-24 17:00 | N | Y | cut over for phase one rebuild on 7L65 | Line |  | Cut over for phase one rebuild on 7L65 south of 709S Vegreville sub. | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 635PT-1038 (635EDD-1001), 635EDD-1001 635-752-613 (635EDD-1001), 635EDD-1001 635-752-612 (635EDD-1001) | 2022-05-23 08:00 | 2022-06-02 17:00 | N | N | regulatory maintenance on transformer, associated breakers | Transformer, Circuit Breaker |  | Regulatory Maintenance on Transformer, associated breakers, other equipment in isolation boundary and protection system testing. | For Information Only
SUNCOR | 29EDD-1 29EDD1s1252 (29EDD-1 Millennium) | 2022-05-23 08:00 | 2022-06-03 16:00 | N | N | breaker replacement | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 133s 1 (133s Stelco Edmonton), 133s 2 (133s Stelco Edmonton) | 2022-05-24 07:00 | 2022-06-21 15:30 | N | N | customer transformer work | Switch |  |  | For Information Only
ENMAX | 24.2TR (ENMAX 24) | 2022-05-24 08:00 | 2022-06-03 16:00 | N | N | 24 sub cable trench replacement, remove and re-install control cables | Transformer |  |  | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2022-05-24 08:00 | 2022-05-25 16:00 | N | N | HV breaker maintenance 41B138-6.82 HLR | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65.1TR (ENMAX 65) | 2022-05-24 08:00 | 2022-05-25 16:00 | N | Y | top up and PRD flag replacement | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition,
ENMAX | 11.4TR (ENMAX 11) | 2022-05-24 08:00 | 2022-05-28 16:00 | N | N | transformer maintenance and testing | Transformer |  | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas relay testing. Oil Sampling MT, TC | For Information Only
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings) | 2022-05-24 08:00 | 2022-05-26 17:00 | N | Y | correct bus pipe connections | Line |  | Correct Bus Pipe connections on B buss, C phase. Buss inspection. "A" and "B" bus will need to be isolated to safely complete this work. The feed from "A" bus to the converter TX runs below the fallen bus. If not fixed further damage could occur to the connector and connection. Possibly leading to a "B" bus outage. This also a WATL link outage | 500 kV, Contingency Requires Mitigation
ATCO | 2082s 701T (2082s Dog Rib) | 2022-05-24 09:00 | 2022-05-27 17:00 | N | N | 701T maintenance | Transformer |  | 701T Maintenance | For Information Only
ATCO | 834s 901T (834s Wesley Creek) | 2022-05-24 09:00 | 2022-05-30 16:00 | N | Y | installation of oil containment around 901T | Transformer |  | Installation of oil containment around 901T. Require the outage to move 25KV cables around. | 240 kV, Over/Under Voltage, Overload, Pre-Condition
BCH | 5L96 (Selkirk - Vaseux Lake) | 2022-05-24 09:00 | 2022-06-02 17:00 | N | Y | flashed insulator replacement, BC maintenance does not affect the Alberta ATC | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 846s Grand Centre, 7L24 (846s Grand Centre - 7LA24 tap) | 2022-05-24 09:01 | 2022-05-26 17:30 | N | Y | switching of 2000s into service | Station, Line |  | Switching of 2000s into service, GOI 144KV bus at 846s open end 7L24 from Bonnyville. Transformers and circuit switchers out of service. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 883s 701T (883s Gregoire) | 2022-05-24 09:30 | 2022-05-27 16:45 | N | N | 701T leak mitigation, RTXP switch replacements | Transformer |  | 701T leak mitigation, RTXP switch replacements. Outage coordinated with interpipe line. | For Information Only
ALTALINK, ATCO | 69s T5 (69s North Barrhead), 723L (69s North Barrhead - 724L tap), 7L230 (69s North Barrhead - 888AL tap) | 2022-05-24 10:00 | 2022-05-26 18:00 | N | N | maintenance | Transformer, Line | Maintenance on 69s50 & 69s20. 69s T5 25kV LAs addition and Doble. Salvage 69s11. RSLD 1 Implemented at the end of the outage. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 755s 905 (755s Cordel) | 2022-05-24 10:00 | 2022-05-26 17:30 | N | Y | breaker testing | Circuit Breaker |  | BREAKER SF6 GL315 COMPLETE TESTING 905 | 240 kV, Contingency Requires Mitigation
ATCO | 959S SVC (959s Lanfine) | 2022-05-24 12:00 | 2022-06-02 10:30 | N | Y | valve hall inspection, transformer testing | Shunts |  | Valve Hall Inspection, Transformer Testing | 240 kV, Pre-Condition
ATCO | 951s 240kV 900BS2 (951s Thickwood Hills) | 2022-05-24 12:00 | 2022-05-31 16:00 | N | Y | addition of new bus on 900BS2, construction, commissioning | Bus |  | Release COG 2-63102 AFTER this GOI is issued **This is 1 of 3 permits to replace 2-49081** Addition of NEW bus on 900BS2, Construction, Commissioning During this time the NEW bus work will also be in construction. May 24-31, 900BS2 outage to tie NEW bus work in (912A and 909B). Isolation points: 951S 903B, 951S 906B, 951S 908B, 951S 910A 903 OOS, 906 OOS, 908 OOS and 900BS2 OOS | 240 kV, Contingency Requires Mitigation
BCH | 5L96 (Selkirk - Vaseux Lake) | 2022-05-24 12:00 | 2022-06-02 17:00 | N | Y | replace defective insulators and install markerballs, BC maintenance does not affect the Alberta ATC | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 163s 6352 (163s Amoco Empress), 163s C1 (163s Amoco Empress) | 2022-05-24 12:30 | 2022-06-02 18:00 | N | N | replacing cap. bank protections | Circuit Breaker, Shunts |  |  | Pre-Condition
TERICPOWER | 728s Mercer Hill DER Battery | 2022-05-25 08:00 | 2022-06-08 16:00 | N | N | P2387 728s Mercer Hill DER Battery Phase 1 (no battery) ISD June 1, 2022 | Unit
ALTALINK | 216s T1 (216s Knightsbridge) | 2022-05-25 08:00 | 2022-05-26 18:00 | N | N | transformer maintenance | Transformer |  | 216sT1: fix leaks, maintain, doble, replace 25kV LA's | For Information Only
ALTALINK | 171s 735X (171s Redwater), 735L (171s Redwater - 233s Beamer) | 2022-05-25 09:00 | 2022-05-25 17:00 | N | N | breaker maintenance | Circuit Breaker, Line | 735L (171s Redwater - 233s Beamer) | breaker maintenance including 1st trips | Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s T4 (63s Red Deer) | 2022-05-25 10:31 | 2022-05-26 17:30 | N | N | maintenance, doble | Transformer |  |  | For Information Only
ALTALINK | 634s T1 (634s Shell Raven River), 719L (378s Shell Caroline - 719BL tap), 719BL (634s Shell Raven River - 719L tap), 719L (719L259A - 719L216) | 2022-05-26 08:00 | 2022-05-26 14:00 | N | N | urgent repair-adjust airbrake 719L216 | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 11B138-BT5 (ENMAX 11) | 2022-05-26 08:00 | 2022-05-26 12:00 | N | N | breaker SF6 Gas Sample - 11B138-BT5 | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-05-26 08:00 | 2022-05-31 18:00 | N | N | 29EDD86;29PT-297 SYSTEM;PM 5y,10y turnaround | Not In Model |  |  | For Information Only
ALTALINK | 968L (138s Windy Flats - 370s North Lethbridge) | 2022-05-26 08:00 | 2022-05-26 17:00 | N | Y | urgent repair on structure 21 | Line |  |  | 240 kV, Overload, Pre-Condition
BCH | 2CB10 (BCH Cranbrook) | 2022-05-26 09:00 | 2022-05-27 17:00 | N | Y | CBK 2CB10 BFPN testing, BC maintenance does not affect the Alberta ATC | Circuit Breaker |  |  | Pre-Condition
ENMAX | 13B138-11.81 (ENMAX 13), 11.81L (ENMAX 11 - ENMAX 13) | 2022-05-26 12:00 | 2022-05-26 16:00 | N | N | breaker SF6 Gas Sample - 13B138-11.81 | Circuit Breaker, Line |  |  | Pre-Condition
SUNCOR | 29EDD-85, 29PL7-7 (29EDD-85 - 29EDD-160) | 2022-05-27 08:00 | 2022-06-02 18:00 | N | N | turnaround | Station, Line |  |  | For Information Only
ATCO | 948s 704 (948s Heatburg), 7L159 (948s Heatburg - 7LA159 tap) | 2022-05-27 08:00 | 2022-05-28 12:00 | N | N | install new 7S1 panel | Circuit Breaker, Line |  | Install new 7S1 panel for Capstone DG addition, 7L159 open at 948S | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 826L (77s Sagitawah - 701s Blue Ridge Lumber), 701s T1 (701s Blue Ridge Lumber) | 2022-05-28 07:00 | 2022-05-28 19:00 | N | N | replace X2 bushing, repair leaks, miscellaneous tasks | Line, Transformer |  | T1: replace X2 bushing, repair leaks, miscellaneous tasks Scheduled Tyler Kee Contact # 780.217.9319
ATCO | 948s 703 (948s Heatburg), 7L16 (766s Nevis - 948s Heatburg) | 2022-05-28 13:00 | 2022-05-28 17:00 | N | N | install new 7S1 panel | Circuit Breaker, Line |  | Install new 7S1 panel for Capstone DG addition. 7L16 open at 948S | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 170L (632s Russell - 799s Coleman) | 2022-05-28 21:00 | 2022-06-24 08:00 | N | Y | 170L urgent de-energization due to clearance concern | Line |  | Weboms Record# 11854742 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CNRL | 842s 75-TR-5701 (842s Horizon Upgrading), 842s 75-TR-8701 (842s Horizon Upgrading), 75-PLH-901 (838s Horizon Mining - 849s Joslyn), 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2022-05-29 07:30 | 2022-06-05 16:00 | N | Y | 5 year PM (breakers, PRC-005) | Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-05-29 08:00 | 2022-06-08 18:00 | N | N | 29EDD160, 29PP-110 turnaround | Not In Model |  |  | For Information Only
ALTALINK | 602s 745N (602s Cold Creek), 745L (602s Cold Creek - 745AL tap) | 2022-05-30 07:00 | 2022-06-08 18:30 | N | Y | replace the 745L line protections and install a new breaker fail protection for 745L | Circuit Breaker, Line |  | Breaker outage to replace the 745L line protections, and install a new breaker fail protection for 745L. At the end of this outage, the line PT (VT1) will be fully installed as well. | Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | K724 (Kennedale), 72CK12 (987s Clover Bar - Kennedale) | 2022-05-30 07:00 | 2022-06-03 17:00 | N | N | K724 bay doble and breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T4 (805s Jasper) | 2022-05-30 07:00 | 2022-05-30 17:00 | N | Y | temporary arc flash protection removal | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | EP 511s V722 (EP 511s Victoria), EP 511s V723 (EP 511s Victoria), EP 511s Victoria T2 (EP 511s Victoria) | 2022-05-30 07:00 | 2022-06-03 17:00 | N | N | arrestor doble and disconnect switch maintenance | Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MHS-3 MH69-T33 (MHS-3 South Ridge) | 2022-05-30 07:30 | 2022-06-01 09:00 | N | N | transformer tapchanger maintenance and ARS PRC-005 testing | Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-3 Southridge substation. The T-33 25/33/41.7 MVA 69/13.8 kV power transformer will be de-energized and isolated at 3S2-M 13.8kV main breaker and MH69-313 69kV disconnect switch. | For Information Only
ALTALINK | 510s ACF11 (510s Sunnybrook) | 2022-05-30 07:30 | 2022-06-01 16:30 | N | Y | filter maintenance. | Shunts |  |  | 500 kV, Pre-Condition
ENMAX | 8.1TR (ENMAX 8) | 2022-05-30 08:00 | 2022-06-10 16:00 | N | N | protection replacement | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12) | 2022-05-30 08:00 | 2022-06-04 16:00 | N | Y | 12B138-832L CT replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 846s Grand Centre | 2022-05-30 08:00 | 2022-05-30 12:59 | N | Y | tap down 2000s on the line side of 700D1 | Line, Station |  | GOI for 7L28 to tap down 2000s on the line side of 700D1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s 902T (2075s Newell), 2075s ACF21 (2075s Newell) | 2022-05-30 08:00 | 2022-06-03 14:08 | N | Y | valve cooling inspection | Transformer, Shunts |  | SVC 2 Will be unavailable for the duration of the outage. Yearly Inspections: - Semi Annual Valve Cooling Inspection - Annual SVC 2 Inspection - Annual Fire System Testing - ACF21 equipment inspections | 240 kV, For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2022-05-30 08:00 | 2022-06-02 16:00 | N | N | tapchanger maintenance | Transformer |  | Tapchanger maintenance (Reinhausen). 11 Sub 11.1TR Tap changer heater failure | For Information Only
CEC2I | CAL1 CALP Gen #1 | 2022-05-30 08:00 | 2022-06-13 16:00 | N | N | P2531 162s Beddington Gas 10 MW increase. ISD June 6, 2022. | Unit
BCH | T1 (BCH Nelway) | 2022-05-30 09:00 | 2022-06-03 17:00 | N | Y | NLY T1 inspection and doble test, BC maintenance does not affect the Alberta ATC | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 6L97 (735s Swan River - 739s Edith Lake), 735s 603 (735s Swan River) | 2022-05-30 10:00 | 2022-05-31 14:00 | N | N | correct deficiency on breaker 603 | Line, Circuit Breaker |  | Correct deficiency on BKR 603 at 735S Swan River from Breaker Replacement Project | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 755s 906 (755s Cordel) | 2022-05-30 10:00 | 2022-06-01 17:30 | N | Y | breaker testing | Circuit Breaker |  | BREAKER SF6 GL315 COMPLETE TESTING 906 | 240 kV, Contingency Requires Mitigation
ALTALINK | 336s T1 (336s Fincastle) | 2022-05-30 10:15 | 2022-06-02 17:45 | N | N | replacement of 25kV & 138kV LA's | Transformer |  | Replacement of 25kV & 138kV LA's, T1 & VR1 doble and maintenance | For Information Only
ALTALINK | 65s 812W (65s High River), 812L (65s High River - 812AL tap) | 2022-05-30 11:00 | 2022-06-02 17:00 | N | N | 1st trip PRC 5 maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 2029s Heathfield | 2022-05-30 11:48 | 2022-06-03 11:48 | N | Y | breaker 1301 maintenance | Station |  | High Speed switch maintenance on 1301 Redundant Return path unavailable. IF the DMR has a sustained fault the link will stay off instead of operating in HV2 return mode | 500 kV, For Information Only
ALTALINK | 729L (542s Ervick - 729AL tap) | 2022-05-30 12:00 | 2022-06-02 18:00 | N | N | fire mitigation components str's range (18-199) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 2049s 901T (2049s Kettle River) | 2022-05-30 12:00 | 2022-06-01 16:00 | N | Y | 901T maintenance | Transformer |  | 901T Maintenance | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 58s 202X (58s Edson), 178s 202N (178s Cynthia), 202L (58s Edson - 178s Cynthia) | 2022-05-30 12:30 | 2022-06-02 17:30 | N | N | breaker maintenance including 1st trips on 58s202X and replace the 138kV CTs at 178s202N. | Circuit Breaker, Line |  | Breaker maintenance including 1st trips on 58s202X. 58s202X maintenance includes change oil, leaky gear box, add missing ground. Replace the 138kV CTs at 58s202X. Replace the 138kV CTs at 178s202N. | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2022-05-31 07:00 | 2022-06-04 09:00 | N | N | urgent repair notifications on 896L2 and 779L3 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 426L (63s Red Deer - 194s South Red Deer), 194s 426 (194s South Red deer) | 2022-05-31 07:30 | 2022-05-31 17:30 | N | N | grading cap replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.2TR (ENMAX 2) | 2022-05-31 08:00 | 2022-06-03 16:00 | N | N | testing and maintenance | Transformer |  | power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas relay testing. 2.2TR Winding Temp Alarm | For Information Only
ATCO | 7L48 (787s High Prairie - 7L48 Tap), 787s 704 (787s High Prairie) | 2022-05-31 09:00 | 2022-05-31 12:00 | Y | N | PRC-005 trip coil testing | Line, Circuit Breaker |  | PRC-005 Trip Coil Testing | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-05-31 10:00 | 2022-06-02 16:00 | N | Y | crossarm/insulator replacement | Line |  | 7L224 Crossarm/Insulator replacement | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L06 (784s Donnelly - 787s High Prairie), 787s 705 (787s High Prairie) | 2022-05-31 12:01 | 2022-05-31 16:00 | N | N | PRC-005 trip coil testing | Line, Switch |  | PRC-005 Trip Coil Testing | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 425L (194s South Red Deer - 217s North Red Deer), 194s 425 (194s South Red deer) | 2022-06-01 07:30 | 2022-06-02 17:00 | N | N | grading cap replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 364s T1 (364s Whitecourt Industrial) | 2022-06-01 09:00 | 2022-06-01 15:30 | N | N | 364s21 replace 2 - 25kV fused disconnects | Transformer |  | 364s21 Replace 2 - 25kV Fused Disconnects - due to Fuse Disconnects Hot Spot West phase is 10 degs above. This is caused when the insulator is beginning to fail. | For Information Only
ATCO | 729s 701T (729s Otauwau) | 2022-06-01 09:00 | 2022-06-06 16:00 | N | N | maintenance | Transformer |  | 701T Transformer Maintenance | For Information Only
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2022-06-01 09:30 | 2022-06-03 16:30 | N | Y | AC filter maintenance | Shunts |  |  | 500 kV, Pre-Condition
CMH | MH-20L (MH69S-3 South Ridge - MH69S-6 Riverview), MHS-3 MH69-T34 (MHS-3 Southridge) | 2022-06-01 10:00 | 2022-06-03 13:00 | N | N | transformer tapchanger maintenance and ARS PRC-005 testing | Line, Transformer |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-3 Southridge substation. This planned maintenance will also require an associated MH138-20L line outage to assure adequate transmission line clearances for the transformer work. The T-34 75/100/125 MVA 138/69 kV power transformer will be de-energized and isolated at MH69-303 69 kV disconnect switch and MH138-318 138 kV disconnect switch (both located in MHS-3 Southridge substation) as well as MH138-621 138 kV disconnect switch (located in MHS-6 Riverview Substation). | Creates Radial Feeds, Firm Load Loss
ALTALINK | 33s 6 (33s Spray) | 2022-06-02 09:00 | 2022-06-02 16:00 | N | Y | maintenance | Switch |  | TAU SP2 Disconnect, Spray Two Brushgear PM | Restricts Generation
ATCO | 732s 501R (732s Mitsue), 732s 501 (732s Mitsue) | 2022-06-02 09:00 | 2022-06-02 16:00 | N | N | breaker maintenance | Shunts, Circuit Breaker |  | Breaker Maintenance | Pre-Condition
ATCO | 859s 701T (859s Primrose), 859s 701 (859s Primrose), 859s 704 (859s Primrose) | 2022-06-03 04:30 | 2022-06-06 11:40 | N | Y | maintenance | Transformer, Circuit Breaker | 859s 701T (859s Primrose) |  | For Information Only, Restricts Generation
ENMAX | 24.82L (ENMAX 24 - ENMAX 65), 24.2TR (ENMAX 24), 24B138-24.82 (ENMAX 24) | 2022-06-03 08:00 | 2022-06-03 16:00 | N | N | 24 sub cable trench replacement, re-install control cables and commission | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.83L (ENMAX 13 - 2.83L Tap), 3.84L (ENMAX 3 - ENMAX 13), 13.1TR (ENMAX 13), 13.3TR (ENMAX 13) | 2022-06-04 08:00 | 2022-06-04 18:00 | N | N | summer substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
PEL | Pembina Empress Cogen | 2022-06-04 08:00 | 2022-06-18 16:00 | N | N | P2235 Pembina Empress Cogen Phase 1 GSU transformer. ISD June 11, 2022 | Unit
ALTALINK | 156L (19s Wabamun - 156BL tap) | 2022-06-04 09:01 | 2022-06-04 18:30 | N | N | GOI required to complete P5 urgent repair notifications on 779L1 | Line |  |  | For Information Only
EPCOR | 72RV4 (EP 511s Victoria - Rossdale) | 2022-06-06 07:00 | 2022-06-10 17:00 | N | N | 72RV4 zone op-checks, P&C maintenance | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 1203 (330p Genesee) | 2022-06-06 07:00 | 2022-06-10 17:00 | N | Y | breaker maintenance and CT doble | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | EP 805s J2404 (EP 805s Jasper) | 2022-06-06 07:00 | 2022-06-11 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
CMH | MHS-6 MH69-611 (MHS-6 CMH Riverview), MHS-6 MH138-620 (MHS-6 CMH Riverview), MHS-6 MH69-T63 (MHS-6 Riverview), MH-20L (MH69S-3 South Ridge - MH69S-6 Riverview) | 2022-06-06 07:30 | 2022-06-09 14:00 | N | N | transformer tapchanger maintenance and ARS PRC-005 testing | Circuit Breaker, Transformer, Line |  | The City of Medicine Hat is planning to perform transformer tapchanger maintenance and ARS PRC-005 testing in the MHS-6 Riverview substation. The T-63 75/100/125 MVA 138/69 kV power transformer will be de-energized and isolated at MH69-610 69 kV disconnect switch and MH138-621 138 kV disconnect switch. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 602s 852 (602s Cold Creek), 602s C1 (602s Cold Creek) | 2022-06-06 07:30 | 2022-06-06 11:00 | N | N | breaker fail protection and complete functional trip test | Circuit Breaker, Shunts | Complete wiring of trips from new 602s745N breaker fail protection and complete functional trip test. |  | For Information Only
ALTALINK | AML 511s 240kV ACF 2 Bus (511s Crossings), AML 511s 5052 (AML 511s Crossings), AML 511s 4952 (AML 511s Crossings), AML 511s ACF21 (AML 511s Crossings), AML 511s ACF22 (AML 511s Crossings) | 2022-06-06 07:30 | 2022-06-09 08:45 | N | Y | maintenance and negative fusing install project, bird mitigation on AC Filters | Bus, Circuit Breaker, Shunts |  | ABB Breaker and AC Filter Maintenance, 511s77 and 511s78 Disconnect Maintenance and Negative Fusing install project. Bird Mitigation on AC Filters. | 240 kV, Pre-Condition
ALTALINK | 919L (77s Sagitawah - 310p Sundance) | 2022-06-06 08:00 | 2022-06-06 17:00 | N | Y | line strain insulator replacement | Line | Line strain insulator replacement @ 310P |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ATCO | 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell) | 2022-06-06 08:00 | 2022-06-08 16:00 | N | Y | yearly inspection | Shunts |  | Yearly Inspections of ACF 1 Filter Banks - ACF 12/13/14, EATL will be limited t0 750MW while ACF 12/13/14 are out of service | 240 kV, Pre-Condition
ENMAX | 5B138-5BT7 (ENMAX 5) | 2022-06-06 08:00 | 2022-06-06 16:00 | N | N | 5BT7 replace lock/unlock coil | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2022-06-06 08:00 | 2022-06-10 16:00 | N | Y | 12B138-833L CT replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 2029s 1302 (2029s Heathfield) | 2022-06-06 08:00 | 2022-06-09 09:45 | N | N | high speed switch maintenance on 1302 | Circuit Breaker |  | High Speed switch maintenance on 1302 Redundant Return path unavailable. IF the HV2 PATH has a sustained fault the link will stay off instead of operating in DMR return mode | 500 kV, For Information Only, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1352 (29EDD-1 Millennium) | 2022-06-06 08:00 | 2022-06-16 18:00 | N | N | Breaker Replacement | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 5.8TR (ENMAX 5) | 2022-06-06 08:00 | 2022-06-09 16:00 | N | N | 5.8TR Leak Investigate and Repair. Tapchanger maintenance | Transformer |  |  | For Information Only
ENMAX | 5.9TR (ENMAX 5) | 2022-06-06 08:00 | 2022-06-11 16:00 | N | N | 5 sub cable trench replacement and remove and re-install control cables | Transformer |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2022-06-06 08:00 | 2022-06-07 16:00 | N | N | HV breaker maintenance | Line |  |  | For Information Only
ALTALINK | 510s ACF21 (510s Sunnybrook), 510s ACF22 (510s Sunnybrook), 510s 1952 (510s Sunnybrook), 510s 2052 (510s Sunnybrook) | 2022-06-06 08:30 | 2022-06-08 16:30 | N | Y | AC filter maintenance | Shunts, Circuit Breaker |  |  | 500 kV, Pre-Condition
BCH | 5L92 (BCH Cranbrook - BCH Selkirk) | 2022-06-06 09:00 | 2022-06-10 16:50 | Y | Y |  | Line | 5L92 (Cranbrook - Selkirk) | CDK 5D24 disconnect inspection, SEL 5D24 inspection and 5CB4 inspection/doble testing, Replace Defective Insulators | Limits ATC, 500 kV
REDDEER | 209s T1 (209s Timberlands) | 2022-06-06 09:00 | 2022-06-06 15:30 | N | N | power transformer 209T1 routine maintenance | Transformer |  |  | Pre-Condition
ATCO | 813s 702 (813s Little Smoky) | 2022-06-06 10:00 | 2022-06-07 15:00 | N | N | breaker maintenance | Circuit Breaker |  | Breaker maintenance | Contingency Requires Mitigation
ATCO | 6L05 (757s Battle River - 843s Bigknife Creek) | 2022-06-06 10:00 | 2022-06-09 17:30 | N | N | breaker min oil HLC completetesting 602 | Line |  | BREAKER MIN OIL HLC COMPLETE TESTING 602 | Creates Radial Feeds, Firm Load Loss
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-06-06 10:00 | 2022-06-09 16:00 | N | Y | 7L224 crossarm/Insulator replacement. | Line |  | 7L224 Crossarm/Insulator replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 38s C2 (38s East Edmonton), 38s 3152 (38s East Edmonton) | 2022-06-06 10:30 | 2022-06-07 17:00 | N | N | PRC5 maintenance, replace 3 breaker capacitors | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 58s T1 (58s Edson) | 2022-06-06 10:30 | 2022-06-15 16:30 | N | N | replace the 25KV and 138KV bushings on T1 | Transformer |  |  | For Information Only
ALTALINK | 602s 452 (602s Cold Creek) | 2022-06-06 11:00 | 2022-06-06 14:00 | N | N | isolate breaker, complete wiring of trips from new 602s745N breaker fail protection and complete functional trip test | Circuit Breaker |  | Isolated breaker, complete wiring of trips from new 602s745N breaker fail protection and complete functional trip test | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar) | 2022-06-06 12:00 | 2022-06-09 18:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2022-06-06 12:00 | 2022-06-10 18:00 | N | N | fire mitigation components str's range (204B - 291) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 256s T2 (256s Harmattan) | 2022-06-06 12:30 | 2022-06-10 17:30 | N | N | maintenance, doble, leak repair, fall arrest pole repair | Transformer |  |  | For Information Only
ALTALINK | 602s 847 (602s Cold Creek) | 2022-06-06 14:00 | 2022-06-06 17:00 | N | Y | isolated breaker, complete wiring of trips from new 602s745N breaker fail protection and complete functional trip test | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 172s T1 (172s Sherritt Gordon) | 2022-06-07 07:30 | 2022-06-07 17:30 | N | N | oil gauge repairs, relay work | Transformer
ALTALINK, ENEL | 205s 14 (205s Castle Rock Ridge), 205s T2 (205s Castle Rock Ridge), 205s 89T2 (205s Castle Rock Ridge), 205s 52M2 (205s Castle Rock Ridge) | 2022-06-07 07:30 | 2022-06-08 15:30 | N | Y | maintenance | Switch, Transformer, Circuit Breaker | Customer equipment maintenance |  | 240 kV, Restricts Generation
ALTALINK | 310p 240kV Bus A (310p Sundance) | 2022-06-07 08:00 | 2022-06-07 17:00 | N | Y | bus strain insulator replacement | Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 14.3TR (SS-14) | 2022-06-07 08:00 | 2022-06-30 16:00 | N | N | power factor test transformer | Transformer |  |  | For Information Only
ENMAXEC | 383s Kettles Hill Windfarm | 2022-06-07 08:00 | 2022-06-07 18:00 | N | Y | DVAr maintenance and testing | Station |  | #1. Asset: Kettles Hill wind farm Outage/Test: DVar PME #1 Outage Planned/Forced: Planned Timing: Tuesday June 7, 2022 8:00  18:00. AC: 0 MW or as provided in declaration #2. Asset: Kettles Hill wind farm Outage/Test: DVar PME #2 Outage Planned/Forced: Planned Timing: Tuesday June 7, 2022 8:00  18:00. AC: 0 MW or as provided in declaration Purpose: The outage is requested for equipment parts annual maintenance inspection/testing on voltage control units PME#1 and #2. Voltage site support will be reduced to 0% (0MVA dynamic support). | For Information Only, Restricts Generation
ENMAXEC | KHW1 Kettles Hill Wind | 2022-06-07 08:00 | 2022-06-07 18:00 | N | N | DVAr maintenance and testing | Unit
EPCOR | T1 (Garneau) | 2022-06-07 08:00 | 2022-06-21 16:00 | N | N | P1649 Garneau upgrade. ISD June 14, 2022 | Transformer
ENMAX | 37.81L (ENMAX 37 - ENMAX 38) | 2022-06-07 08:00 | 2022-06-08 16:00 | N | N | install flight diverters on line | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 432s 790 (432s Carvel), 790L (432s Carvel - 790AL tap) | 2022-06-07 08:30 | 2022-06-07 16:30 | N | N | fix tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 810s 701T (810s Dome Cutbank) | 2022-06-07 09:00 | 2022-06-07 11:00 | N | N | cut in J1 between 701TCS and 144kV bus | Transformer |  | GOI on 701T for HL crew to cut in J1 between 701TCS and 144kV bus Expand GOI for transformer and cct switcher maintenance after HL crew cuts in J1 between 701TCS and 144kV bus under HOP
ALTALINK | 63s 252 (63s Red Deer) | 2022-06-07 09:30 | 2022-06-07 15:00 | N | Y | 1st trip & PRC 5 maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 810s 701T (810s Dome Cutbank), 810s 701TCS (810s Dome Cutbank) | 2022-06-07 11:01 | 2022-06-10 15:00 | N | N | 701T and 701TCS maintenance after crew cuts in J1 between 701TCS and 144kV bus | Transformer, Switch |  | Expand from GOI (2-64383) for 701T and 701TCS maintenance after HL crew cuts in J1 between 701TCS and 144kV bus under HOP
ATCO | 959s 901T (959s Lanfine) | 2022-06-07 12:00 | 2022-06-09 17:30 | N | Y | transformer class 1 major testing | Transformer |  | TRANSFORMER CLASS1 MAJOR TESTING @ LANFINE 959S 901T | Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2022-06-07 18:00 | 2022-06-07 19:00 | N | N | Inter-Site Transfer business continuity drill | SCInternal |  | O | For Information Only
ALTALINK | 68s Willesden Green, 68s T1 (68s Willesden Green), 68s T2 (68s Willesden Green), 68s 152 (68s Willesden Green), 68s 552 (68s Willesden Green) | 2022-06-08 07:00 | 2022-06-08 16:00 | N | Y | replace 68s PT1 240kV PT & 68s5, repair leaks on 68s T3, maintenance on 995L, 3103L, & 495LW protections | Station, Transformer, Circuit Breaker | 68s PT1 240kV PT replacement. Replace 68s5. Repair leaks on 68s T3. Maintenance on 995L, 3103L, & 495LW protections. Update settings on T1 & 96/152 protections for new DER 2 addition. DER 2 not to be in service until a later date TBD. 68s3103 DG confirmed offline for this outage. Transition to 68s T2 & 25kV Bus 2  GOI & 68s495  GOI after this outage is complete |  | 240 kV, For Information Only
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2022-06-08 07:30 | 2022-06-08 17:30 | N | N | perform relay maintenance | Transformer |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-06-08 08:00 | 2022-06-13 18:00 | N | N | 29EDD160;29PP-111 SYSTEM;PM 5y,10y 29EDD160;29PP-110 SYSTEM;PM 5y,10y -Turnaround- | Not In Model |  |  | For Information Only
ENMAX | 15.60L (ENMAX 15 - ENMAX 21), 15B69-15.60 (ENMAX 15) | 2022-06-08 08:00 | 2022-06-09 16:00 | N | N | HV breaker maintenance 15B69-15.60 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 71s 952 (71s Lamoureux), 71s C1 (71s Lamoureux) | 2022-06-08 08:30 | 2022-06-08 17:00 | N | N | 1st trip PRC 5 maintenance, fix open close indicator | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 809S 503 (809s Louise Creek), 809s 503R (809s Louise Creek) | 2022-06-08 09:00 | 2022-06-09 16:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  | Breaker Maintenance | Pre-Condition
ATCO | 813s 703 (813s Little Smoky) | 2022-06-08 10:00 | 2022-06-09 15:00 | N | N | breaker maintenance | Circuit Breaker |  | breaker maintenance | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 68s T2 (68s Willesden Green), 68s 552 (68s Willesden Green) | 2022-06-08 16:01 | 2022-06-09 20:00 | N | Y | replace 68s5 (25 kV) | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2022-06-09 06:00 | 2022-06-09 17:00 | N | Y | line strain insulator replacement at 310P | Line | 902L (19s Wabamun - 310p Sundance) |  | 240 kV, Pre-Condition
ALTALINK | 205s 13 (205s Castle Rock Ridge), 205s T1 (205s Castle Rock Ridge) | 2022-06-09 07:00 | 2022-06-10 15:30 | N | Y | maintenance | Switch, Transformer | 205s13 Advice for customer Customer equipment maintenance |  | 240 kV, Restricts Generation
ALTALINK | 28s 31 (28s West Brooks), 28s 47 (28s West Brooks), 763L (28s West Brooks - 763AL tap) | 2022-06-09 07:00 | 2022-06-09 18:00 | N | Y | clearance concerns ub violation 763L (str's 78-79) | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
EPCOR | T3 (Meadowlark) | 2022-06-09 07:00 | 2022-06-09 17:00 | N | N | measure secondary cabinet | Transformer |  | Meadowlark TX3: Outage for Engineering to measure secondary cabinet. UGT to assist. | For Information Only
ALTALINK | 205S Castle Rock Ridge | 2022-06-09 07:00 | 2022-06-10 18:00 | N | N | annual substation outage | Station
ALTALINK | 510s 2052 (510s Sunnybrook) | 2022-06-09 08:00 | 2022-06-10 16:30 | N | N | forced | Circuit Breaker |  |  | 500 kV
ATCO, SUNCOR | 836s 624 (836s Steepbank), 836s 625 (836s Steepbank), 29PL6-2 (836s Steepbank - 29EDD-55) | 2022-06-09 08:00 | 2022-06-17 18:00 | N | N | switch and arrestor maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L92 (777s Vilna - 7LA92 Tap) | 2022-06-09 09:00 | 2022-06-09 17:00 | N | N | tapping up mobile sub 2000S to be installed for outage at 777S | Line |  | Tapping up mobile sub 2000S to be installed for outage at 777S | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 207s 744 (207s Pinedale), 744L (207s Pinedale - 228s T.M.P.L.Niton) | 2022-06-09 09:00 | 2022-06-09 16:30 | N | N | breaker tank heater repairs | Circuit Breaker, Line | 744L (207s Pinedale - 228s T.M.P.L.Niton) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s 5 (17s Benalto) | 2022-06-09 09:30 | 2022-06-09 15:00 | N | Y | 1st trip and PRC5 maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 781L (71s Lamoureux - 172s Sherritt) | 2022-06-10 07:00 | 2022-06-17 12:00 | N | N | maintenance work on structures # 4, 8, 9, 11, 15, 16, 17 ,19 and 20 | Line |  | Scope of work includes maintenance work on structures 4, 8, 9, 11, 15, 16, 17, 19 and 20 | Contingency Requires Mitigation, Creates Radial Feeds, Overload, Pre-Condition
ALTALINK | 974L (39s Bickerdike - 310p Sundance), 310p 152 (310p Sundance), 310p 252 (310p Sundance) | 2022-06-10 08:00 | 2022-06-10 17:00 | N | Y | line strain insulator replacement @ 310P | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 813s 503 (813s Little Smoky), 813s 503R (813s Little Smoky) | 2022-06-10 10:00 | 2022-06-10 15:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  | breaker maintenance | For Information Only
ATCO | 810s 701T (810s Dome Cutbank) | 2022-06-10 15:01 | 2022-06-10 17:00 | N | N | close J1 between 701TCS and 144kV bus | Transformer |  | Reduce from GOI (2-64384) to 701T for HL crew to close J1 between 701TCS and 144kV bus under HOP | For Information Only
ENMAX | 7.84L (ENMAX 7 - ENMAX 36), 7.1TR (ENMAX 7) | 2022-06-11 08:00 | 2022-06-11 12:00 | N | N | summer substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-71 29PT-232 (29EDD-71), 29EDD-71 29PT-233 (29EDD-71) | 2022-06-11 08:00 | 2022-06-15 18:00 | N | N | maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7), 7.2TR (ENMAX 7), 7B138-7BT3 (ENMAX 7) | 2022-06-11 12:00 | 2022-06-11 18:00 | N | Y | summer substation washing | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72CK13 (987s Clover Bar - Kennedale), 72CK12 (987s Clover Bar - Kennedale), 72CH11 (987s Clover Bar - EP Hardisty), 987s 72kV Bus 3 (987s Clover Bar), 987s 72kV Bus 4 (987s Clover Bar) | 2022-06-12 07:00 | 2022-06-12 19:00 | N | Y | Cloverbar 72kV BUS 3/4 CVT Doble, BUS 4 disconnect maintenance SDS2L/CSDS2/CDS10/CDS12/CDS16/CDS18/CGDS1/GDS1 | Line, Bus |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T3 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), EP 511s V725 (EP 511s Victoria) | 2022-06-13 07:00 | 2022-06-17 17:00 | N | N | Victoria TX3 zone op-checks, P&C maintenance | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 816s T1 (816s Petrolia) | 2022-06-13 07:00 | 2022-06-17 17:00 | N | Y | surge arrestor upgrade | Transformer |  | Petrolia TX1 Surge Arrestor Upgrade, EL Smith Project | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2022-06-13 07:00 | 2022-06-20 17:00 | N | Y | SVC addition and 144 kv bus rebuild | Line |  | SVC addition and 144 kv bus rebuild. Install new bypass switch 7L68D3 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | T2 (Poundmaker) | 2022-06-13 07:00 | 2022-06-20 07:00 | N | Y | tap changer maintenance (reinhausen), bladder repair | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72NW15 (Namao - Woodcroft) | 2022-06-13 07:00 | 2022-06-17 17:00 | N | N | aerial: steel structure refurbishment | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2029s ACF11 (2029s Heathfield), 2029s ACF12 (2029s Heathfield), 2029s ACF13 (2029s Heathfield), 2029s ACF14 (2029s Heathfield) | 2022-06-13 07:30 | 2022-06-17 15:00 | N | Y | AC filter bank 1 inspections | Shunts |  | AC Filter Bank 1 Inspections No Filter redundancy during work and Reduced Voltage Mode Depending on system dispatch levels the voltage will be reduced below 500KV DC and PCAP will adjust accordingly. (1050MW to 950MW range) | 240 kV, Limits Ratings, Pre-Condition
ENMAX | 240kV North Bus (ENMAX 162), 138kV North Bus (ENMAX 162), 162.1TR (162s Beddington) | 2022-06-13 08:00 | 2022-06-14 18:00 | N | Y | summer substation washing | Bus, Transformer |  | Power factor test 162PT240-Z43. Check Reversing Switch. Oil Sampling Bushing, TC, MT. Gas Monitor Taptrans Maintenance. Summer Substation Washing | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 24.1TR (ENMAX 24) | 2022-06-13 08:00 | 2022-06-18 16:00 | N | N | 24 sub cable trench replacement | Transformer |  | 24 sub cable trench replacement. Remove and re-install control cables. | For Information Only
ENMAX | 43B138-33.84 (ENMAX 43), 33B138-33.84 (ENMAX 33), 33.84L (ENMAX 33 - ENMAX 43) | 2022-06-13 08:00 | 2022-06-16 16:00 | N | N | 33.84L DGA sample and sheath testing | Circuit Breaker, Line |  | 33.1TR ECI Bushing / Slip Over CT Repalcement. 33.84L DGA sample and sheath testing. HV Breaker maintenance 43B138-33.84 HLR | Creates Radial Feeds, Firm Load Loss
SUNCOR | 635EDD-1001 635-752-621 (635EDD-1001) | 2022-06-13 08:00 | 2022-06-13 17:00 | N | N | address the water ingress issue in the operating mechanism enclosure | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 8.5TR (ENMAX 8) | 2022-06-13 08:00 | 2022-06-24 16:00 | N | N | protection replacement. | Transformer |  |  | For Information Only
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2022-06-13 08:30 | 2022-06-15 16:30 | N | Y | filter maintenance | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 739s 702T (739s Edith Lake) | 2022-06-13 09:00 | 2022-06-15 16:00 | N | N | Transformer Maintenance | Transformer |  | Transformer Maintenance | For Information Only
ATCO | 7L92 (777s Vilna - 7LA92 tap), 7L92 (777s Vilna - 819s Whitby Lake), 777s 701T (777s Vilna), 777s 701TCS (777s Vilna) | 2022-06-13 09:00 | 2022-06-16 08:00 | N | N | GOI for 701TCS, 701T | Line, Transformer, Switch |  | GOI for 701TCS, 701T. Switching to put 2000S in/out service. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
TRANSALTA | 239s Castle River | 2022-06-13 09:00 | 2022-06-13 17:00 | N | N | substation maintenance | Station |  |  | Restricts Generation
BCH | 2L294 (BCH A. A. Lambert - BCH Cranbrook) | 2022-06-13 09:00 | 2022-06-17 17:00 | N | Y | replace structures and timbers | Line |  |  | Limits ATC, Pre-Condition
ALTALINK | 310p 1052 (310p Sundance), 310p 1152 (310p Sundance), 1046L (310p Sundance - 338s Cherhill) | 2022-06-13 09:30 | 2022-06-13 18:00 | N | Y | line strain insulator replacement | Circuit Breaker, Line | 1046L (310p Sundance - 338s Cherhill) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-06-13 10:00 | 2022-06-15 16:00 | N | Y | crossarm/insulator replacement. | Line |  | 7L224 Crossarm/Insulator replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ATCO | 770s 702 (770s Three Hills), 7L137 (768s Rowley - 770s Three Hills) | 2022-06-13 10:00 | 2022-06-15 17:30 | N | N | breaker testing | Circuit Breaker, Line |  | BREAKER SF6 LTB145D1/B COMPLETE TESTING 702 RTXP TEST SWITCH RECALL (REPLACEMENT) - 21A/7L137 @ 770S RTXP TEST SWITCH RECALL (REPLACEMENT) - 21B/7L137 @ 770S | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 813s 710 (813s Little Smoky) | 2022-06-13 10:00 | 2022-06-14 15:00 | N | N | breaker maintenance | Circuit Breaker |  | breaker maintenance | Contingency Requires Mitigation
ALTALINK | 158s 821E (158s Vauxhall), 821L (158s Vauxhall - 421s Hays) | 2022-06-13 11:00 | 2022-06-16 18:00 | N | Y | replace 138kV strain insulators and maintenance on 158s821E and 158s30 | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, ATCO | 830L (562s Cypress - 840s McNeill Station), 840s 701 (840s McNeill Station), 840s 701T (840s MCNEILLSTATION) | 2022-06-13 12:00 | 2022-06-23 12:20 | Y | Y | valve hall inspection, transformer testing, breaker maintenance | Line, Circuit Breaker, Transformer |  | Valve Hall Inspection, Transformer Testing, Breaker Maintenance | Limits ATC, Pre-Condition
ALTALINK | 310p 1152 (310p Sundance) | 2022-06-13 18:01 | 2022-06-20 18:00 | N | Y | forced | Circuit Breaker |  |  | 240 kV
ALTALINK | 275s T2 (275s Jenner), 275s 46 (275s Jenner), 275s 2252 (275s Jenner) | 2022-06-14 07:30 | 2022-07-05 12:00 | N | Y | install new foundations, structure, reactors, bus work and bird cover on T2 25kV bus | Transformer, Circuit Breaker |  | Demo of old bus work and structure. Install new foundations, structure, reactors, bus work and bird cover on T2 25kV Bus. | 240 kV, For Information Only
ALTALINK | 975s Dalehurst, 745A1L (975s Dalehurst - 745AL tap) | 2022-06-14 08:00 | 2022-06-14 16:00 | N | N | settings changes on the following: 419L 50/51/152 FORM4C, T1 A50/51/51N/T1 SEL351S | Station, Line |  | Techs require a station outage to complete settings changes on the following: Settings changes 419L 50/51/152 FORM4C, T1 A50/51/51N/T1 SEL351S. Station outage required to perform settings changes - No redundancy. | Firm Load Loss, For Information Only, Pre-Condition
ALTALINK | 922L (17s Benalto - 310p Sundance), 310p 1952 (310p Sundance), 310p 2052 (310p Sundance) | 2022-06-14 08:00 | 2022-06-14 17:00 | N | Y | line strain insulator replacement @ 310P | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Affects Cranking Path
ENMAX | 33.1TR (SS-33) | 2022-06-14 08:00 | 2022-06-15 16:00 | N | N | transformer maintenance | Transformer |  | Bushing replacement. Slip over CT install. Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas relay testing. Oil Sampling MT, TC. Check Reversing Switch | For Information Only
ALTALINK | 59s 452 (59s Peigan) | 2022-06-14 09:00 | 2022-06-15 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 394s T1 (394s Empress) | 2022-06-14 11:45 | 2022-06-14 13:15 | N | N | RTU outage for IP address changes | Transformer |  | RTU outage for IP address changes. The whole site is changing to a new subnet. The RTU and substation LAN equipment will be updated early and all devices that report to the RTU will be updated to the new subnet in the same day. Separate outage requests will be provided for the connected devices. T1 maybe returned in service earlier than planned. | For Information Only
ATCO | 724s 601T (724s Hines Creek) | 2022-06-14 16:00 | 2022-06-17 10:16 | N | N | GOI for 601T maintenance | Transformer |  | GOI for 601T maintenance | For Information Only
EPCOR | 987s CGB2 (987s Clover Bar), 987s CGB3 (987s Clover Bar) | 2022-06-15 07:00 | 2022-06-17 17:00 | N | Y | pole remediation | Circuit Breaker | G2 and G3 @ Cloverbar E987S Cloverbar G2-G3 Pole Remediation |  | Restricts Generation
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2022-06-15 08:00 | 2022-06-15 17:00 | N | Y | line strain insulator replacement | Line | 973L (39s Bickerdike - 310p Sundance) |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK, SUNCOREP | SCR2 McGrath | 2022-06-15 08:00 | 2022-06-15 18:00 | N | N | 863L and 891L outage | Unit
ALTALINK | 863L (225s Magrath - 618s Riverbend), 891L (226s Garden City - 863L tap), 226s Garden City | 2022-06-15 08:00 | 2022-06-15 18:00 | N | Y | MPLS upgrades at 226s, 618s, and 225s | Line, Station |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation
ENMAX | 162.2TR (162s Beddington), 138kV South Bus (ENMAX 162), 240kV South Bus (ENMAX 162) | 2022-06-15 08:00 | 2022-06-16 18:00 | N | Y | power factor test, check reversing switch, oil sampling, bushing, maintenance, summer substation washing | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2022-06-15 08:00 | 2022-06-16 16:00 | N | N | breaker maintenance 22B138-22.81L | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 127s T1 (127s Bruderheim) | 2022-06-15 08:30 | 2022-06-16 16:00 | N | N | replace bushing | Transformer
ALTALINK | 159s 710 (159s Colinton), 710L (56s Boyle - 159s Colinton) | 2022-06-15 08:30 | 2022-06-15 16:30 | N | N | heater repairs | Circuit Breaker, Line | 710L (56s Boyle - 159s Colinton) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s 711 (813s Little Smoky) | 2022-06-15 10:00 | 2022-06-16 15:00 | N | N | breaker maintenance | Circuit Breaker |  | breaker maintenance | Contingency Requires Mitigation
ALTALINK | 926L (17s Benalto - 310p Sundance), 310p 2552 (310p Sundance), 310p 2652 (310p Sundance) | 2022-06-16 08:00 | 2022-06-16 17:00 | N | Y | line strain insulator replacement at 310p | Line, Circuit Breaker | 926L (17s Benalto - 310p Sundance) | 926L (310P-17s) - GOI Line strain insulator replacement @ 310P | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 102s SVC (102s Langdon), 102s 552 (102s Langdon), 102s 252 (102s Langdon), 102s T4 (102s Langdon) | 2022-06-16 08:00 | 2022-06-16 16:30 | N | Y | weed spraying and SVC cooling pipe leak investigation/repair | Shunts, Circuit Breaker, Transformer | 102s SVC GOI weed spraying, SVC cooling pipe leak investigation/repair |  | 240 kV, Pre-Condition
ATCO | 7L85 (803s Bullpound - 804s Wintering Hills) | 2022-06-16 08:00 | 2022-06-19 17:00 | N | N | tie-in 7L85 with 981S Badlands sub | Line |  | WHEATLAND WIND FARM PROJECT Tie-in 7L85 with 981S Badlands Sub | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 510s ACF13 (510s Sunnybrook), 510s 1352 (510s Sunnybrook) | 2022-06-16 08:30 | 2022-06-17 16:30 | N | Y | AC filter maintenance | Shunts, Circuit Breaker |  |  | 500 kV, Pre-Condition
ATCO | 739s 603 (739s Edith Lake), 6L97 (735s Swan River - 739s Edith Lake) | 2022-06-16 09:00 | 2022-06-16 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | breaker maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
SUNCOR | 29PL7-5 (29EDD-18 Firebag - 29EDD-71), 29EDD-71 752-4614 (29EDD-71), 29EDD-71 752-4613 (29EDD-71), 29EDD-18 29-752-106 (29EDD-18 Firebag), 29EDD-18 29-752-103 (29EDD-18 Firebag), 29EDD-18 29PT-204 (29EDD-18 Firebag) | 2022-06-17 05:00 | 2022-06-21 18:00 | N | N | 29EDD-18;29PP-118C SYSTEM;PM; 10y 29EDD-71; 144KV NODE, 29PT-238 MAINT; 5y | Line, Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation
EPCOR | 816s T1 (816s Petrolia), 816s P2401 (816s Petrolia), 816s P2402 (816s Petrolia) | 2022-06-17 07:00 | 2022-06-17 17:00 | N | Y | CVT Doble, PAB1 maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
BHE | 719s Rattlesnake Ridge | 2022-06-17 08:00 | 2022-12-17 17:00 | N | N | power performance testing for 1 tower | Station |  |  | Pre-Condition
EPCOR | 657s SU2405 (657s Summerside), 657s T3 (657s Summerside), 657s SUAB1 (657s Summerside), 657s SUDS11 (657s Summerside), 657s SUDS12 (657s Summerside) | 2022-06-17 08:00 | 2022-07-01 16:00 | N | N | P2133 EDTI Southeast Edmonton Area Load and Reliability. ISD June 24, 2022 | Circuit Breaker, Transformer, Switch
CAPPOWERLP | ENC2 Cloverbar #2 | 2022-06-17 16:00 | 2022-06-17 23:00 | N | N | communication only outage | Unit |  | The EPCOR revenue meters are being replaced during the planned outage ending at 16:00. The generation values the new meters read will need to be verified when the unit is online. This will coincide with an hour long, approved and scheduled post reliability run. During this communication only outage, AESO will not have telemetry of generation output. Telemetry of other AESO SCADA points should be unaffected. The generation values will be available to EMOC via internal data streams. | Affects Visibility
ENMAX | 39.82L (SS-39 - SS-162), 162B138-RB82 (SS-162), 162B138-RB83 (SS-162) | 2022-06-18 08:00 | 2022-06-18 12:00 | N | N | summer substation washing | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | SCR1 Base Plant | 2022-06-18 08:00 | 2022-06-18 18:00 | N | N | metering maintenance | Unit |  |  | Affects Visibility
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24), 24.81L (SS-24 - SS-31), 24.1TR (SS-24) | 2022-06-18 08:00 | 2022-06-18 16:00 | N | Y | 24 sub cable trench replacement, re-install control cables and commission. | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
CAPPOWERLP | ENC3 Cloverbar #3 | 2022-06-19 16:00 | 2022-06-19 23:00 | N | N | communication only outage | Unit |  | The EPCOR revenue meters are being replaced during the planned outage ending at 16:00. The generation values the new meters read will need to be verified when the unit is online. This will coincide with an hour long, approved and scheduled post reliability run. During this communication only outage, AESO will not have telemetry of generation output. Telemetry of other AESO SCADA points should be unaffected. The generation values will be available to EMOC via internal data streams. | Affects Visibility
SUNCOR | 30EDD-2 | 2022-06-20 06:00 | 2022-06-30 18:00 | N | N | 30EDD2;30PK-11 system 30EDD2;30PK-10 system | Station |  | 30EDD2;30PK-11 system;PM 5y,10y 30EDD2;30PK-10 system ;PM 5y | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-06-20 06:00 | 2022-07-07 18:00 | N | N | 30PK-10 and 30PK-11 at 30EDD-2 | Not In Model | 30EDD2;30PK-11 SYSTEM;PM 5y,10y 30EDD2;30PK-10 SYSTEM;PM 5y |  | For Information Only
EPCOR | T2 (Poundmaker), PM2401 (Poundmaker), PM2405 (Poundmaker) | 2022-06-20 07:00 | 2022-07-12 17:00 | N | Y | doble, disconnect maintenance | Transformer, Circuit Breaker |  | Poundmaker TX2 Doble, PMAB2/PMDS1 Disconnect Maintenance | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia) | 2022-06-20 07:00 | 2022-06-20 17:00 | N | Y | line arrestor doble | Line |  | Jasper 1044L Line Arrestor Doble | 240 kV, Pre-Condition
EPCOR | 816s T2 (816s Petrolia) | 2022-06-20 07:00 | 2022-06-24 17:00 | N | Y | surge arrestor upgrade | Transformer |  | Petrolia TX2 Surge Arrestor Upgrade, EL Smith Project | 240 kV
ATCO | 9L05 (809s Louise Creek - 813s Little Smoky), 813s 901 (813s Little Smoky), 813s 904 (813s Little Smoky) | 2022-06-20 07:00 | 2022-07-03 12:00 | N | Y | 813S Little Smoky rebuild - remove and install new panels, P&C wiring, prep work, relay programming and functionality, commission control, alarms and status | Line, Circuit Breaker |  | 813S Little Smoky Rebuild Remove panels 5H,6H - install new panel 9P3 - BKR 905 and 906 P&C wiring, prep work Relay programming and functionality Commission control, alarms and status | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 2029s ACF21 (2029s Heathfield), 2029s ACF22 (2029s Heathfield), 2029s ACF23 (2029s Heathfield) | 2022-06-20 07:30 | 2022-06-24 15:00 | N | Y | ACF 2 inspections | Shunts |  | ACF 2 Inspections ACF 1 will be operational | 500 kV, Pre-Condition
ENMAX | 24.2TR (SS-24) | 2022-06-20 08:00 | 2022-07-14 16:00 | N | N | transformer secondary cables are faulted (forced outage) | Transformer |  |  | For Information Only
ATCO | 2075s 240kV Bus 900BS1 ( 2075s Newell), 2075s 900SST2 (2075s Newell) | 2022-06-20 08:00 | 2022-06-21 15:30 | N | Y | PRC relay testing | Bus, Transformer |  | GOI will be as follows: June 13- June 17, 2022 904A, 905B and 502VRA for 900SST2 Outage for 904 trip coil June. 20 to June 24, 2022 the isolation will expand to 910A,916A, 919A, 922A, for a full 900BS1 outage to test 904/905 BF protections PRC Relay Testing on 20D10 Diameter - Station Service Transformer Protection - 904, 905, Breaker Fail Protection will all be tested as a result of PRC-005 Testing | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB132 (SS-162), 162B240-RB133 (SS-162) | 2022-06-20 08:00 | 2022-06-21 18:00 | N | Y | power factor test | Line, Circuit Breaker |  | Power factor test 162PT240-918 | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 310p T34 (310p Sundance), 310p 1152 (310p Sundance), 310p 1252 (310p Sundance) | 2022-06-20 08:00 | 2022-06-20 17:00 | N | Y | strain insulator replacements to T34, replace T34 metering, repair 310p11a | Transformer, Circuit Breaker | 310p T34 (310p Sundance) |  | 240 kV
ENMAX | 15.62L (SS-15 - SS-16) | 2022-06-20 08:00 | 2022-06-23 16:00 | N | N | HV breaker maintenance 15B69-15.62 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 35.2TR (SS-35) | 2022-06-20 08:00 | 2022-06-23 16:00 | N | N | LTC leak repair, tapchanger maintenance | Transformer |  |  | For Information Only
SUNCOR | 29EDD-1 29EDD1s1652 (29EDD-1 Millennium) | 2022-06-20 08:00 | 2022-06-30 09:45 | N | N | breaker replacement | Circuit Breaker |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2022-06-20 08:00 | 2022-06-29 16:00 | N | N | 5 sub cable trench replacement, remove and re-install control cables | Transformer |  |  | For Information Only
ATCO | 848s 910 (848s Ruth Lake) | 2022-06-20 09:00 | 2022-06-22 17:30 | N | Y | breaker maintenance | Circuit Breaker |  | 910 Breaker Maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 7L92 (777s Vilna - 7LA92 tap) | 2022-06-20 09:00 | 2022-06-20 17:00 | N | N | tap down 2000S | Line |  | Partial Line outage to tap down 2000S | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 769s 701 (769s Stettler), 769s 701T (769s Sttettler) | 2022-06-20 09:00 | 2022-06-23 17:30 | N | N | transformer class 2 major testing | Circuit Breaker, Transformer |  | TRANSFORMER CLASS2 MAJOR TESTING 701T @ 769S | For Information Only
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-06-20 10:00 | 2022-06-23 16:00 | N | Y | crossarm/insulator replacement | Line |  | 7L224 Crossarm/Insulator replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 678s Okotoks 138kV Bus 2, 727L (678s Okotoks - 727AL tap), 678s T2 (678s Okotoks) | 2022-06-20 10:15 | 2022-06-23 17:45 | N | N | replacement of the 678s33 138kV switch and the 727L strain insulators | Bus, Line, Transformer | 727L (678s Okotoks - 727AL tap) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 9L29 (946s Oakland - 963s Coyote Lake), 946s 908 (946s Oakland), 946s 909 (946s Oakland), 963s 901 (963s Coyote Lake) | 2022-06-20 10:30 | 2022-06-23 16:00 | N | Y | construction work and install of new RAS relays, 89B and 52A contacts required for RAS signals | Line, Circuit Breaker |  | Construction work and install of new RAS relays. 89B and 52A contacts required for RAS signals | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2049s 902T (2049s Kettle River) | 2022-06-20 12:00 | 2022-06-23 16:00 | N | Y | 902T maintenance and protection | Transformer |  | 902T Maintenance | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 743s 603 (743s Sarah Lake), 6L11 (743s Sarah Lake - 854s Swan Dive) | 2022-06-20 12:00 | 2022-06-21 15:30 | N | N | breaker maintenance | Circuit Breaker, Line |  | Breaker Maintenance | Creates Radial Feeds, Firm Load Loss
TRANSALTA | 239s Castle River | 2022-06-21 07:00 | 2022-06-21 17:00 | N | N | substation maintenance | Station |  |  | Restricts Generation
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2022-06-21 07:00 | 2022-06-22 18:00 | N | Y | component replacement's 920L Str's Range ( 67-100 ) | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 745L (39s Bickerdike - 745AL tap), 39s 37 (39s Bickerdike), 39s 752 (39s Bickerdike) | 2022-06-21 07:00 | 2022-06-28 18:00 | N | N | replacing the745L line protections | Line, Circuit Breaker | Replacing the 745L line protections, and complete settings changes on 652 & 752 breaker fail protections. Complete trip test from 345s1150 & 345s745 to customer breakers at 345s. Removing temporary bypass and closing 345s Open Points 'D' & 'E'. Energizing substation up to 345s Open Point 'A'. Final commissioning of C87/21/31/L1. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 337s T2 (337s Canada Liquidair) | 2022-06-21 07:30 | 2022-06-23 18:00 | N | N | maintenance including fixing leaks, changing breather, washing, & testing. | Transformer | 337sT2 maintenance including fixing leaks, changing breather, washing, & testing. |  | For Information Only
ENMAX | 37.1TR (SS-37) | 2022-06-21 08:00 | 2022-06-24 16:00 | N | N | power factor test transformer | Transformer |  | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas Relay Testing. Oil Sampling MT, TC. Check Reversing Switch. Replace PRD Junction Box | For Information Only
ALTALINK | 185s T2 (185s Bretville) | 2022-06-21 08:00 | 2022-06-23 18:00 | N | N | replace T2 high side bushings, fix leaks, wash transformer. | Transformer |  |  | For Information Only
ALTALINK | 165s T1 (165s Gainford) | 2022-06-21 08:00 | 2022-06-29 16:00 | N | N | P1412 165s TX replacement. ISD June 28, 2022 | Transformer
ALTALINK | 276s T2 (276s Union Carbide Prentiss) | 2022-06-21 08:00 | 2022-07-31 17:00 | N | N | maintain & doble T2 | Transformer |  |  | For Information Only
SUNCOR | 29PL7-10 (29EDD-18 Firebag - 29EDD-85) | 2022-06-21 08:00 | 2022-06-26 18:00 | N | N | maintenance | Line |  | 29EDD85;29PP-100A SYSTEM;PM 5y,10y 29EDD85;29PP-100B SYSTEM;PM 5y,10y 29EDD18;29PT-128&29PL7-10 SYS;PM -Turnaround- | Creates Radial Feeds, Firm Load Loss
ALTALINK | 431s T1 (431s Hussar) | 2022-06-21 08:30 | 2022-06-21 11:30 | N | N | customer maintenance | Transformer | 431s T1 (431s Hussar) | Customer requested outage. | For Information Only
ATCO | 706s 703 (706s Irish Creek), 7L117 (706s Irish Creek - 710s Vermilion) | 2022-06-21 09:30 | 2022-06-23 16:00 | N | N | maintenance and PRC005 work | Circuit Breaker, Line |  | 703 Maintenance and PRC005 work, 7L117 Open ended at 706S | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 431s T2 (431s Hussar) | 2022-06-21 11:31 | 2022-06-21 14:30 | N | N | customer maintenance | Transformer | 431s T2 (431s Hussar) | Customer requested outage. | For Information Only, Pre-Condition
EPCOR | K723 (Kennedale) | 2022-06-22 07:00 | 2022-06-23 17:00 | N | N | doble and breaker maintenance | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 730s 702 (730s Rycroft) | 2022-06-22 07:00 | 2023-01-17 17:30 | N | N | SVC addition and 144 kV bus rebuild, salvage 730s702 and 7L68D3 | Circuit Breaker | SVC addition and 144 kv bus rebuild. Electrical and commissioning Work including SVS (GC) 730S 702 Salvaged up to J1, 7L68D3 (old) Salvaged 7L68 will be tied to 7L10 with bypass 7L68D3 (new) upon completion of this permit, Settings changes required at 811S. |  | Pre-Condition
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2022-06-22 07:15 | 2022-06-22 18:45 | N | Y | urgent wildfire mitigation | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | 11 (Aurora) | 2022-06-22 08:00 | 2022-06-23 20:00 | N | N | maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 162B240-RB135 (SS-162), 162B240-RB136 (SS-162) | 2022-06-22 08:00 | 2022-06-23 18:00 | N | Y | power factor test 162PT240-932 | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 14.3TR (SS-14) | 2022-06-22 08:00 | 2022-07-21 16:00 | N | N | faulty 25KV phase C cable between the 14.3TR transformer and switchgear | Transformer |  |  | For Information Only
ALTALINK | 310p 2452 (310p Sundance) | 2022-06-22 08:30 | 2022-06-22 16:30 | N | Y | grading capacitor replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2022-06-22 10:00 | 2022-06-24 14:00 | N | Y | SVC maintenance and inspection, 703T SPR relay testing | Shunts, Circuit Breaker |  | SVC Maintenance and Vendor Inspection, 703T SPR relay testing | Pre-Condition
ENBRIDGE | SET1 South Edmonton Terminal | 2022-06-22 11:00 | 2022-06-22 14:00 | N | N | repairs and upgrades to the ENB Network | Unit | Enbridge Pipelines Inc. is planning to conduct some repairs and upgrades to the ENB Network on June 22nd that will result in the loss of communication on the SCADA connection between the South Edmonton Terminal (SET1) generation asset and the AESO for approximately three hours from 11:00 to 14:00. |  | Affects Visibility
ENBRIDGE, ALTALINK, ATCO, EXPPIPE | 594s RTU/SCADA (594s Battle Sands), 656s RTU/SCADA (656s Clipper), Youngstown RTU/SCADA (Youngstown Express), 658s RTU/SCADA (658s Chard), 296s RTU/SCADA (296s Rosyth), 892s RTU/SCADA (892s Ribstone Creek), 221s RTU/SCADA (221s Sunken Lake), 216s RTU/SCADA (216s Knightsbridge), 293s RTU/SCADA (293s Bernese), 299s RTU/SCADA (299s Kingman), 301s RTU/SCADA (301s Queensland), 317s RTU/SCADA (317s Baseline) | 2022-06-22 12:00 | 2022-06-22 13:00 | N | N | Enbridge communication outage | Terminal Equipment |  |  | Affects Visibility
EPCOR | 987s CH724 (987s Clover Bar), 72CH11 (987s Clover Bar - EP Hardisty) | 2022-06-23 07:00 | 2022-06-24 17:00 | N | N | apparatus breaker maintenance and cutovers for DFR/UFLS upgrades | Circuit Breaker, Line |  | Cloverbar CH724: Apparatus Breaker Maintenance (June 24) and P&C Cutovers for DFR/UFLS Upgrades (June 23) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 71s 240kV East Bus (71s Lamoureux), 921L (71s Lamoureux - 987s Clover Bar), 71s 1252 (71s Lamoureux), 71s 1352 (71s Lamoureux) | 2022-06-23 07:00 | 2022-06-24 18:00 | N | Y | component replacements on dead end glass on 921L, and component replacement's 921L str's 41 & 72. | Bus, Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 2029s ACF23 (2029s Heathfield) | 2022-06-23 08:00 | 2022-06-30 10:00 | N | Y | forced outage to remove a birds nest | Shunts |  | Forced O/S to remove a birds nest. | 500 kV, Pre-Condition
ALTALINK | 310p 652 (310p Sundance) | 2022-06-23 08:30 | 2022-06-23 16:30 | N | Y | grading capacitor replacement on 310p652 | Circuit Breaker |  |  | 240 kV
ATCO | 848s 608 (848s Ruth Lake) | 2022-06-23 09:00 | 2022-06-23 17:30 | N | N | 608 breaker maintenance | Circuit Breaker |  | 608 Breaker Maintenance | Pre-Condition
ALTALINK | 898L (37s North Calder - 92s Viscount) | 2022-06-24 07:00 | 2022-06-29 18:00 | N | N | maintenance on structures 24/30/35/44-49/51/52 | Line | 898L (37s North Calder - 92s Viscount) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14) | 2022-06-24 08:00 | 2022-06-24 16:00 | N | N | 14 Sub 138kV DFR upgrade | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 310p 352 (310p Sundance) | 2022-06-24 08:30 | 2022-06-24 16:30 | N | Y | grading capacitor replacement on 310p352 | Circuit Breaker |  |  | 240 kV
ATCO | 7L128 (802s Michichi Creek - 963s Coyote Lake), 963s 701 (963s Coyote Lake) | 2022-06-24 09:00 | 2022-06-27 15:30 | N | N | construction work for Blue Earth Hand Hills protection upgrade (P2263) | Line, Circuit Breaker |  | Construction work for Blue Earth Hand Hills protection upgrade | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 848s 606 (848s Ruth Lake) | 2022-06-24 09:00 | 2022-06-24 17:30 | N | N | 606 breaker maintenance | Circuit Breaker |  | 606 Breaker Maintenance | Pre-Condition
ENMAX | 6.80L (SS-6 - SS-35), 6.4TR (SS-6) | 2022-06-25 08:00 | 2022-06-25 12:00 | N | N | summer substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 6.82L (SS-6 - SS-41), 6.1TR (SS-6) | 2022-06-25 12:00 | 2022-06-25 18:00 | N | N | summer substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2022-06-26 07:00 | 2022-06-30 17:00 | N | Y | steel structure refurbishment | Line |  | Aerial: Steel Structure Refurbishment | 240 kV, Pre-Condition, Affects Cranking Path
SUNCOR | 29EDD-34 260kV Bus 29PP-24 (29EDD-34), 29PL7-1 (29EDD-34 - 29EDD-85), 29EDD-34 29PT-112 (29EDD-34) | 2022-06-27 06:00 | 2022-07-12 18:00 | N | Y | 29PP-24 and 29PT-112 system PM 5y,10y and 29PS68 replace damaged contacts | Bus, Line, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), 72LS24 (EP 803s Lambton - Strathcona) | 2022-06-27 07:00 | 2022-06-30 17:00 | N | N | clearance required for hydrovac and conduit install for P&C projects | Line |  | Lambton: Clearance required for Hydrovac. Conduit install for P&C projects. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 165s T1 (165s Gainford) | 2022-06-27 07:00 | 2022-06-28 07:00 | N | N | soaking new transformer | Transformer |  |  | For Information Only
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee) | 2022-06-27 07:00 | 2022-06-29 17:00 | N | Y | disconnect maintenance | Bus, Transformer, Circuit Breaker |  | Genesee 1201A/1204A/1207A/12TC1D/12TC1GS Disconnect Maintenance | 500 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 987s T2 (987s Clover Bar), 987s T4 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s CC721 (987s Clover Bar) | 2022-06-27 07:00 | 2022-06-30 17:00 | N | Y | apparatus-CVT doble and breaker maintenance and CDS1 disconnect maintenance | Transformer, Circuit Breaker |  | Cloverbar C2408, TX2, TX4: Apparatus-CVT Doble and Breaker Maintenance and CDS1 Disconnect Maintenance P&C-Cutovers for Cloverbar DFR and UFLS Upgrade Projects | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.4TR (SS-3) | 2022-06-27 08:00 | 2022-06-30 16:00 | N | N | tapchanger maintenance, oil sampling MT, TC. 3.4TR LTC cabinet - heater fails | Transformer | Tapchanger maintenance (Reinhausen). Oil Sampling MT, TC. 3.4TR LTC cabinet - heater fails |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34), 34B69-16.60 (SS-34) | 2022-06-27 08:00 | 2022-06-28 16:00 | N | N | HV breaker maintenance 34B69-16.60 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.2TR (SS-33) | 2022-06-27 08:00 | 2022-07-08 16:00 | N | N | maintenance and testing | Transformer |  | Bushing/Slip over CT replacement. Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas Relays Testing. Check Rev Switch. Oil Sampling MT, TC. Secondary bush. Leak investigation/repair. 33.2TR MD Retrieve Nameplate info. | For Information Only
ATCO | 848s 911 (848s Ruth Lake) | 2022-06-27 09:00 | 2022-06-29 17:30 | N | Y | breaker maintenance | Circuit Breaker |  | 606 Breaker Maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 7L23 (796s Nipisi - 858s Narrows Creek), 796s 702 (796s Nipisi) | 2022-06-27 09:00 | 2022-06-28 16:00 | N | N | breaker maintenance and PRC-005 trip coil testing | Line, Circuit Breaker |  | Breaker Maintenance, PRC-005 Trip Coil Testing | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 174L (197s Bardo - 395s North Holden), 701L (223s Strome - 395s North Holden), 395s 174W (395s North Holden), 395s 701X (395s North Holden) | 2022-06-27 09:30 | 2022-06-29 15:00 | N | N | new RAS 134 scheme addition, install new "A" and "B" protection relays, modify CT wiring in breaker 395s174W and 395s701X | Line, Circuit Breaker | New RAS 134 scheme addition, Demo old relay and install new "A" and "B" Protection relays, modify CT wiring in breaker 395s174W Trip testing required once construction complete. (P1718). New RAS 134 scheme addition, Demo old relay and install new "A" and "B" Protection relays, modify CT wiring in breaker 395s701X Trip testing required once construction complete (P1718) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 951s SVC (951s Thickwood), 951S 902 (951s Thickwood Hills), 951s 903 (951s Thickwood Hills) | 2022-06-27 10:00 | 2022-06-30 17:00 | N | Y | 2022 CVA fire panel logic updates and SVC building crane inspections | Shunts, Circuit Breaker |  | SVC Building Crane Inspections, 2022 CVA @ 951s Fire panel logic updates. Will need HMI/RTU update, will lose visibility for 5-10 minutes | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-06-27 10:00 | 2022-06-30 16:00 | N | Y | crossarm/insulator replacement | Line |  | 7L224 Crossarm/Insulator replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 770s 701T (770s Three Hills), 770s 701 (770s Three Hills) | 2022-06-27 10:00 | 2022-06-27 15:30 | N | N | breaker SF6 HPL partial testing | Transformer, Circuit Breaker |  | BREAKER SF6 HPL PARTIAL TESTING 701 | For Information Only
ALTALINK | 28s 28 (28s West Brooks) | 2022-06-27 12:30 | 2022-06-29 17:30 | N | N | breaker maintenance | Circuit Breaker |  | 138 kV breaker maintenance | Contingency Requires Mitigation
ALTALINK | 156L (19s Wabamun - 235s Entwistle), 156BL (165s Gainford - 156L Tap) | 2022-06-28 07:00 | 2022-06-29 14:00 | N | N | closing 165s open point 'C' and removing 471s mobile substation | Line |  | Closing 165s Open Point 'C' and removing 471s mobile substation | For Information Only
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), M721 (Meadowlark) | 2022-06-28 07:00 | 2022-06-28 17:00 | N | N | Meadowlark Bus 3 upgrade project: M721 P&C, CT cable removal | Line, Circuit Breaker |  | Meadowlark: M721 P&C: CT Cable Removal. BUS 3 Upgrade Project | Creates Radial Feeds, Firm Load Loss, Pre-Condition
FORTIS | BRK1 Brooks Solar DER | 2022-06-28 07:45 | 2022-06-28 13:45 | N | N | 121s T5 outage - perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2 | Unit
BSC | BSC1 Brooks Solar | 2022-06-28 07:45 | 2022-06-28 13:45 | N | N | 121s T5 outage - perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2 | Unit
ALTALINK | 121s T5 (121s Brooks) | 2022-06-28 07:45 | 2022-06-28 13:45 | N | N | perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2 | Transformer | OC to create generator record. | Fortis requested changes due to overvoltage concerns- Techs require T2 transformer and Bus 2 out of service to perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2. | For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 370s North Lethbridge | 2022-06-28 09:15 | 2022-06-28 15:45 | N | N | trip Test all 25 kV Bus 1 breakers from new breaker C60 module | Station |  |  | For Information Only
ATCO | 6L56 (763s Hanna - 802s Michichi Creek), 763s 601 (763s Hanna) | 2022-06-28 09:30 | 2022-06-29 17:30 | N | N | breaker minimum oil HLC partial testsing | Line, Circuit Breaker |  | BREAKER MIN OIL HLC PARTIAL TESTING | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
FORTIS | BRK2 Brooks Solar DER | 2022-06-28 14:45 | 2022-06-28 17:45 | N | N | 121s T2 outage - perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2 | Unit
ALTALINK | 121s T2 (121s Brooks) | 2022-06-28 14:45 | 2022-06-28 17:45 | N | N | perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2 | Transformer |  | Fortis requested changes due to overvoltage concerns- Techs require T2 transformer and Bus 2 out of service to perform wiring changes from PT2 modules and commission new connections to LTC Controller for T2. Fortis DG required offline | For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 345s T1 (345s Hornbeck) | 2022-06-28 18:00 | 2022-07-03 07:00 | N | N | 345s open point 'A' to remain under REG control TMPL is ready for it to be closed | Transformer |  | 345s Open Point 'A' to remain under REG control TMPL is ready for it to be closed. | For Information Only
ALTALINK | 39s 240kV Bus 1 (39s Bickerdike), 39s 138kV Bus 1 (39s Bickerdike), 974L (39s Bickerdike - 310p Sundance), 39s T1 (39s Bickerdike) | 2022-06-29 07:00 | 2022-07-12 18:00 | N | Y | complete relocation of 974L to new bay at 39s | Bus, Line, Transformer | Complete relocation of 974L to new bay at 39s, Close 39s Open Point "J", 974L Open Point "Q" @ 39s, 974L Open Point "D", and 1048L Open point "N", Rename 39s973E to 39s1135. 974L strain insulator replacements @ 310P. (P2032) |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 89s 952 (89s Ellerslie) | 2022-06-29 08:00 | 2022-06-29 17:00 | N | Y | wiring changes, breaker status checks | Circuit Breaker | Wiring changes can be completed and that the breaker status checks can be done for the single pole open condition |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 29EDD-71 752-4622 (29EDD-71) | 2022-06-29 08:00 | 2022-07-03 18:00 | N | N | repair insulator switch | Circuit Breaker | 29-752-4622 REPAIR INSULATOR CHIP |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 40B138-32.83 (SS-40) | 2022-06-29 08:00 | 2022-06-29 16:00 | N | N | HV breaker maintenance | Line, Circuit Breaker | HV Breaker maintenance 40B138-32.83. HV - SF6 Gas Sample - 40B138-32.83 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 770s 703T (770s Three Hills), 770s 703 (770s Three Hills) | 2022-06-29 10:00 | 2022-06-30 17:30 | N | N | breaker 703 testing, RTXP switch recall | Transformer, Circuit Breaker |  | BREAKER 703 SF6 HPL PARTIAL TESTING RTXP TEST SWITCH RECALL (REPLACEMENT) - 50-51N/703T @ 770S RTXP TEST SWITCH RECALL (REPLACEMENT) - 87/703T @ 770S | For Information Only
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2022-06-29 15:30 | 2022-06-30 18:00 | N | Y | new RAS 134 scheme addition | Line | New RAS 134 scheme addition, Replace copper conductor bus drops from 7L77 to 395s78, modify CT wiring in breaker 395s77E, salvage existing 7L77 revenue meter. Trip testing required (P1718) |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant Plant) | 2022-06-29 23:00 | 2022-06-30 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant Plant) | 2022-06-30 03:00 | 2022-06-30 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38) | 2022-06-30 08:00 | 2022-06-30 12:00 | N | N | HV breaker SF6 gas sample | Line, Circuit Breaker |  | HV breaker SF6 Gas Sample - Baseline 39B138-38.83 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 848s 601 (848s Ruth Lake) | 2022-06-30 09:00 | 2022-06-30 17:30 | N | N | breaker maintenance | Circuit Breaker |  | 601 Breaker Maintenance | For Information Only, Pre-Condition
ENMAX | 22B138-22BT8 (SS-22) | 2022-06-30 12:00 | 2022-06-30 16:00 | N | N | HV breaker SF6 gas sample | Circuit Breaker |  | HV breaker SF6 Gas Sample  22B138-22.BT8 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek), 1L274 (978s BCH Britt Creek - BCH Greenhills Tap) | 2022-07-01 07:00 | 2022-07-01 19:00 | Y | Y | BCK OSP Rev00 step 4 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-07-01 08:00 | 2022-07-02 17:00 | N | N | 635PT-1059 | Not In Model | Unmodeled Transmission Facility (Suncor) | Mine Shovel 635EDD-1015 Protection Testing | For Information Only
ENMAX | 11.81L (SS-11 - SS-13), 13.82L (SS-13 - SS-22), 13.60L (SS-13 - SS-27), 13.2TR (SS-13), 13.4TR (SS-13) | 2022-07-01 08:00 | 2022-07-01 18:00 | N | N | summer substation washing; check reversing switch and other maintenance | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
FORTIS | CRD2 Conrad Solar 2 | 2022-07-01 08:00 | 2023-04-22 23:00 | N | N | P1959 Fortis Alberta Conrad DER Solar 2. ISD April 15, 2023. 18 MW. | Unit
Syncrude | ML2 (Syncrude Mildred Lake - UE-1 Syncrude Plant 30-2), 1015 (Syncrude Mildred Lake), UE-1 7201 (UE-1 Syncrude Plant 30-2) | 2022-07-01 08:00 | 2022-07-15 20:00 | N | N | line outage | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
FORTIS | CRD1 Conrad Solar 1 | 2022-07-01 08:00 | 2023-04-22 23:00 | N | N | P1918 Fortis Alberta Conrad DER Solar 1. ISD April 15, 2023. 23 MW. | Unit
BCH | 2L113 (BCH Cranbrook - BCH Natal) | 2022-07-01 09:00 | 2022-07-01 17:00 | N | Y | NTL 60D21 disconnect repair, 1L274 & 1L275 to be fed from AltaLink | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Pre-Condition
ALTALINK | 345s T1 (345s Hornbeck) | 2022-07-03 07:00 | 2022-07-06 18:00 | N | N | closing 345s open point 'A' and energizing TMPL's new equipment | Transformer |  |  | For Information Only
Syncrude | SCL1 Syncrude #1 | 2022-07-03 08:00 | 2022-07-17 16:00 | N | N | P2512 Syncrude Mildred Lake G5 Modification (like for like). ISD July 10, 2022 | Unit
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-07-04 08:00 | 2022-07-05 17:00 | N | N | 635PT-1060 | Not In Model | Unmodeled Transmission Facility (Suncor) | Mine Shovel 635EDD-1016 Protection Testing | For Information Only
SUNCOR | 29EDD-1 29EDD1s1152 (29EDD-1 Millennium) | 2022-07-04 08:00 | 2022-07-14 16:00 | N | N | breaker replacement | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 513s Lundbreck, 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck) | 2022-07-04 08:30 | 2022-07-08 17:30 | N | N | T1 doble & leak repairs; SFRA test; install mech for lock and tag | Station, Line, Transformer | 513s T1 (Tx 18238) - GOI T1 Doble & leak repairs, SFRA test. Install mech for lock and tag for customer. |  | For Information Only
ALTALINK | 322s Cowley Ridge Windplant | 2022-07-04 09:00 | 2022-07-04 17:00 | N | N | maintenance | Station |  | TransAlta is requesting an outage at Cowley 322s for substation maintenance on July 4 from 0900 to 1800. Site AC 0MW. | Restricts Generation
CHDI | CRE3 Cowley Ridge | 2022-07-04 09:00 | 2022-07-04 17:00 | N | N | substation maintenance | Unit
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514BL (322s Cowley Ridge Windplant - 514L tap), 514L (513s Lundbreck - 514BL tap) | 2022-07-04 09:00 | 2022-07-08 18:00 | N | Y | CRU and fire mitigation on structures #1 - 189 | Line |  |  | For Information Only, Pre-Condition, Restricts Generation
ATCO | 732s 902 (732s Mitsue) | 2022-07-04 09:00 | 2022-07-08 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | breaker maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 848s 603 (848s Ruth Lake) | 2022-07-04 09:00 | 2022-07-05 17:30 | N | N | breaker maintenance | Circuit Breaker |  | 603 Breaker Maintenance | Contingency Requires Mitigation, Pre-Condition
ATCO | 710s 702T (710s Vermilion) | 2022-07-04 09:30 | 2022-07-07 17:30 | N | N | 702T maintenance. PRC005 | Transformer |  | 702T Maintenance. PRC005 | For Information Only
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2022-07-04 09:30 | 2022-07-09 17:00 | N | Y | aerial: steel structure refurbishment | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 734s 701T (734s Sturgeon) | 2022-07-04 10:00 | 2022-07-06 16:00 | N | N | transformer maintenance | Transformer |  | Transformer Maintenance, 701T is currently on Hot standby, no load transfer required. | For Information Only, Pre-Condition
ATCO | 948s 701T (948s Heatburg) | 2022-07-04 10:00 | 2022-07-08 17:30 | N | N | transformer class 2 major testing 701T @ 948S | Transformer |  | TRANSFORMER CLASS2 MAJOR TESTING 701T @ 948S Offload 948s to Nevis/766S-5L235 & Three Hills/770S-5L349 | For Information Only
ALTALINK | 291s T1 (291s Cochrane) | 2022-07-04 10:00 | 2022-07-07 19:00 | N | N | transformer maintenance, doble, bird cover | Transformer |  |  | For Information Only
ATCO | 773s 601T (773s Coronation) | 2022-07-04 10:00 | 2022-07-06 17:30 | N | N | transformer class 2 major testing 601T @ 773s | Transformer |  | TRANSFORMER CLASS2 MAJOR TESTING 601T @ 773S Offload 773s | For Information Only
ALTALINK | 522AL (868s Keephills Make-Up - 522L tap), 522L (866s Sundance Make-Up - 522AL tap) | 2022-07-04 10:30 | 2022-07-04 16:30 | N | N | replace high side LAs on 866sT1 | Line |  |  | For Information Only
ALTALINK | 288s T1 (288s Wolf Creek) | 2022-07-04 12:00 | 2022-07-07 18:00 | N | Y | PRC5 maintenance, doble, leaks | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 805L (86s Bigstone - 964s Pigeon Lake) | 2022-07-04 12:00 | 2022-07-04 18:00 | N | N | P5 urgent repair on 805L128 arm change | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 866s T1 (866s Sundance Make-Up) | 2022-07-04 16:00 | 2022-07-07 17:30 | N | N | re-gasket lid and fix oil leaks on 866sT1 | Transformer |  |  | For Information Only
ALTALINK | 309s T2 (309s Anthony Henday) | 2022-07-05 07:30 | 2022-07-05 15:30 | N | N | installing bird mitigation | Transformer |  |  | For Information Only
ATCO | 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2022-07-05 08:00 | 2022-07-11 17:00 | N | Y | line mitigation, cross arm replacement | Line | July 5 - Temp jumpers to Isolate North/South portions of the line and keep Kakwa online. Portion of 7L80 will be energized from 740S Milner to energize 857S Kakwa Ridge on end of day July 5th, 2022. | Line mitigation, Cross arm replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 65B138-D83 (SS-65) | 2022-07-05 08:00 | 2022-07-05 16:00 | N | N | breaker maintenance and testing | Circuit Breaker |  | HV Breaker maintenance 65B138-D83. HV - SF6 Gas Sample - 65B138-D83, Trip Circuit Testing - 65B138-D83 | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 180s Cope Creek, 180s T1 (180s Cope Creek), 180s T2 (180s Cope Creek) | 2022-07-05 08:00 | 2022-07-12 17:00 | N | N | install pile for new power PT, install station service cabling to disconnect, install new 138kV power PT to supply station service power | Station, Transformer |  | Install pile for new power PT, install station service cabling to disconnect, install new 138kV power PT to supply station service power | For Information Only
ENMAX | 47.1TR (SS-47) | 2022-07-05 08:00 | 2022-07-06 16:00 | N | N | maintenance | Transformer |  | Tapchanger maintenance. 47.1TR LTC Oil Level Issue. Secondary Cable Circulating Current Hazard. Check Reversing Switch. Gas Monitor Hydran Maintenance | For Information Only
ALTALINK | STR1 Strathmore Solar DER, STR2 Strathmore Solar DER | 2022-07-05 08:00 | 2022-07-05 12:00 | N | N | shutting down device ports to troubleshoot communication flapping issues | Unit |  |  | Affects Visibility, For Information Only
SUNCOR | 29PL7-1 (29EDD-34 - 29EDD-85), 29EDD-85 752-10020 (29EDD-85), 29EDD-85 752-10040 (29EDD-85) | 2022-07-05 08:00 | 2022-07-12 18:00 | N | N | 29PT-0426C oil top up | Line, Circuit Breaker | 29PL7-1 29PT-0426 29PT-0426C; OIL TOP UP (M2017356) 29PL7-1 Block 7 Relays CWP18 |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.3TR (SS-22) | 2022-07-05 08:00 | 2022-07-08 16:00 | N | N | testing and maintenance | Transformer |  | Power factor test transformer. Transformer Secondary Cable Testing. Transformer Maintenance. Gas Relays Testing. Oil Sampling | For Information Only
ENMAX | 13.1TR (SS-13) | 2022-07-05 08:00 | 2022-07-12 16:00 | N | N | bushing replacement, testing and maintenance | Transformer |  | XO Bushing Repalcement . Power factor test transformer. Secondary Cable Testing. Bushing replacement. Transformer Maintenance. Gas Relay Testing. Oil Sampling MT, TC | For Information Only
CapitalPower, Whitla 2 Wind Generation L.P. | WHT1 Whitla, WHT2 Whitla 2 | 2022-07-05 09:00 | 2022-07-05 10:00 | N | N | communication outage | Unit |  |  | Affects Visibility
ALTALINK | 309s T1 (309s Anthony Henday), 309s 152 (309s Anthony Henday) | 2022-07-06 07:30 | 2022-07-06 15:30 | N | N | installing bird mitigation | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 1150L (39s Bickerdike  345s Hornbeck), 745L (345s Hornbeck - 745AL tap), 345s Hornbeck, 345s T1 (345s Hornbeck) | 2022-07-06 08:00 | 2022-07-13 16:00 | N | N | P1460 345s Hornbeck Phase 2 ISD July 6, 2022 | Line, Station, Transformer
ENMAX | 14.1C (SS-14), 14.2C (SS-14) | 2022-07-06 08:00 | 2022-07-06 16:00 | N | N | 138kV DFR upgrade | Shunts |  |  | For Information Only, Pre-Condition
ENMAX | 13B138-2.83 (SS-13), 2.83L (SS-13 - 2.83L Tap) | 2022-07-06 08:00 | 2022-07-06 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK, ENMAX | 42s 28 (42s Sarcee), 28.80L (42s Sarcee - SS-28) | 2022-07-06 08:30 | 2022-07-06 13:30 | N | Y | replace front relay display on the C60 breaker protection relay | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 420s 731 (420s Broadmoor), 731L (420s Broadmoor - 731L tap) | 2022-07-06 08:30 | 2022-07-06 16:30 | N | N | investigate SF6 leak | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 285s T2 (285s East Camrose) | 2022-07-06 08:30 | 2022-07-06 17:30 | N | N | urgent request to investigate and repair CT secondaries that are not grounded | Transformer |  | Techs require a GOI on 285sT2 to investigate/repair CT secondaries that are not grounded. | Pre-Condition
ATCO | 848s 913 (848s Ruth Lake) | 2022-07-06 09:00 | 2022-07-08 17:30 | N | Y | breaker maintenance | Circuit Breaker |  | 913 Breaker Maintenance | 240 kV, Contingency Requires Mitigation
ENMAX | 26.81L (SS-26 - SS-32) | 2022-07-07 08:00 | 2022-07-07 16:00 | N | N | HV breaker SF6 gas sample | Line | HV breaker SF6 Gas Sample - 32B138-26.81. 32B138-26.81 Replace Counter. Thermostat bulb adjustment |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L57 (727s Kinuso - 735s Swan River) | 2022-07-07 08:00 | 2022-07-07 16:00 | N | N | high load move | Line |  | High Load Move | Creates Radial Feeds, Firm Load Loss
ATCO | 769s 602 (769s Stettler), 6L44 (769s Stettler - 778s Big Valley) | 2022-07-07 08:30 | 2022-07-08 17:30 | N | N | breaker bulk oil KSO partial testing | Circuit Breaker, Line |  | BREAKER BULK OIL KSO COMPLETE TESTING 602 BREAKER BULK OIL KSO PARTIAL TESTING 602 | Pre-Condition
ENMAX | 162.4TR (SS-162), 162B138-RB94 (SS-162), 162B138-RB92 (SS-162) | 2022-07-09 08:00 | 2022-07-09 18:00 | N | N | summer substation washing, oil sampling, check reversing switch, fix 162MD138-162.4TR | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 987s T1 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar) | 2022-07-11 07:00 | 2022-07-21 17:00 | N | Y | zone doble and CDS19/CDS20/CDS24/CDS38 disconnect maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 52s T2 (52s East Industrial) | 2022-07-11 07:00 | 2022-07-15 17:00 | N | Y | zone op-checks, p&c maintenance | Transformer |  |  | 240 kV, For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-07-11 08:00 | 2022-07-20 18:00 | N | N | 5y,10y maintenance on 29PT-334 at 29EDD94 | Not In Model | 29PT-334 29EDD94;29PT-334 SYSTEM;PM 5y,10y |  | For Information Only
ENMAX | 21.1C (SS-21), 21B138-21.CAP (SS-21) | 2022-07-11 08:00 | 2022-07-28 16:00 | N | N | HV breaker maintenance and substation weed spraying [Capacitor Bank]; 21 Sub fencing replacement | Shunts, Circuit Breaker |  | HV breaker maintenance 21B138-21CAP. Substation Weed Spraying [Capacitor Bank]. 21 Sub Fencing Replacement | For Information Only
ENMAX | 39.2TR (SS-39) | 2022-07-11 08:00 | 2022-07-15 18:00 | N | N | ECI bushing / slip over CT replacement, check reversing switch, transformer maintenance | Transformer |  | ECI Bushing / Slip Over CT Replacement. Check reversing switch. Oil Sampling MT, TC. 39.2TR LTC counter not working - replace | For Information Only
ATCO | 2075s ACF22 (2075s Newell), 2075s ACF23 (2075s Newell), 2075s ACF24 (2075s Newell), 2075S 931 (2075s Newell), 2075S 932 (2075s Newell), 2075S 933 (2075s Newell) | 2022-07-11 08:00 | 2022-07-15 14:45 | N | Y | yearly inspections of ACF 2 filter banks | Shunts, Circuit Breaker |  | Yearly Inspections of ACF 2 Filter Banks - ACF 22/23/24, EATL will be limited t0 750MW while ACF 22/23/24 are out of service | 240 kV, Pre-Condition, Prevents Normal Events
ATCO | 856s 901 (856s Kinosis) | 2022-07-11 09:00 | 2022-07-14 17:30 | N | Y | breaker maintenance | Circuit Breaker |  | 901 Breaker Maintenance | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO | 732s 904 (732s Mitsue) | 2022-07-11 09:00 | 2022-07-15 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | breaker maintenance | 240 kV, Contingency Requires Mitigation
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514BL (322s Cowley Ridge Windplant - 514L tap) | 2022-07-11 09:00 | 2022-07-15 18:00 | N | Y | CRU and fire mitigation on structures #1 - 189 | Line |  |  | Restricts Generation
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek), 1L275 (799s Coleman - BCH Natal) | 2022-07-11 09:00 | 2022-07-11 17:20 | Y | Y | tree removal at Elk Lake provincial park | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
GWPCORP | 243s Soderglen | 2022-07-11 10:00 | 2022-07-12 17:00 | N | N | substation maintenance | Station |  |  | Restricts Generation
ATCO | 706s 705C (706s Irish Creek), 706s 705 (706s Irish Creek) | 2022-07-11 10:00 | 2022-07-15 15:00 | N | N | relay testing, aux relay testing, trip coil testing | Shunts, Circuit Breaker |  | Relay testing, Aux relay testing, trip coil testing | Pre-Condition
ATCO | 775s 604C (775s Sullivan Lake), 775s 604 (775s Sullivan Lake) | 2022-07-11 10:00 | 2022-07-13 17:30 | N | N | SF6 HPL complete testing | Shunts, Circuit Breaker |  | BREAKER SF6 HPL COMPLETE TESTING 604 | Pre-Condition
ALTALINK | 837L (538s Buford - 964s Pigeon Lake) | 2022-07-11 10:00 | 2022-07-11 18:00 | N | N | *P5* urgent repair @ 837L152 & 182 | Line |  |  | Creates Radial Feeds, Firm Load Loss
NEXENI | GWW1 GW Wind #1-Soderglen | 2022-07-11 10:00 | 2022-07-12 17:00 | N | N | substation maintenance | Unit
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-07-11 10:00 | 2022-07-14 16:00 | N | Y | crossarm and insulator replacement project | Line |  | Crossarm and Insulator replacement project | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 754s 701T (754s Ksituan River), 754s 701TCS (754s Ksituan River) | 2022-07-11 10:00 | 2022-07-15 10:00 | N | N | 701TCS maintenance | Transformer, Switch |  | 701TCS Maintenance, Hot line crew will cut in jumper J1 to work under HOP 2-65626, | For Information Only
ALTALINK | 608L (418s Ardenville - 608L Tap), 603L (138s Windy Flats - 243s Soderglen), 138s T2 (138s Windy Flats) | 2022-07-11 10:30 | 2022-07-15 17:30 | N | Y | maintenance, doble, leak repair, bushing and monitor repair | Line, Transformer |  | maintenance, doble, leak repair, bushing and monitor repair (T2). 138kV Breaker Maintenance (138s2152, 138s2552) | 240 kV, Restricts Generation
ALTALINK | 71s T1 (71s Lamoureux) | 2022-07-11 12:00 | 2022-07-28 18:00 | N | Y | replace the 240kV and 138kV bushings on T1, maintenance work (leak repair, bird cleanup) | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 523s C1 (523s Bullshead), 523s 33 (523s Bullshead) | 2022-07-12 07:30 | 2022-07-12 09:30 | N | N | weed spraying | Shunts, Circuit Breaker |  |  | Pre-Condition
ENBRIDGE | 485s T1 (485s Blackspring), 485s 35CBVAR1 (485s Blackspring Ridge), 485s C1 (485s Blackspring) | 2022-07-12 07:30 | 2022-07-13 17:00 | N | N | maintenance | Transformer, Circuit Breaker, Shunts |  |  | 240 kV, Restricts Generation
ENMAX | 36.1TR (SS-36) | 2022-07-12 08:00 | 2022-07-15 16:00 | N | N | maintenance and testing | Transformer |  | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas Relays Testing. Check Reversing Switch. Oil Sampling MT, TC | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-07-12 08:00 | 2022-07-16 17:00 | N | N | 635PL6-1003 | Not In Model | Unmodeled Transmission Facility (Suncor) | Line and Disconnect Switch Major Maintenance (includes 635-652-100204 Breaker) | For Information Only
ENMAX | 14.1C (SS-14), 14.2C (SS-14) | 2022-07-12 08:00 | 2022-07-12 16:00 | N | N | HV breaker maintenance, substation weed spraying | Shunts |  | HV breaker maintenance 14CS138-14.1CAP. Substation Weed Spraying [Capacitor Bank] | For Information Only, Pre-Condition
ALTALINK | 368s 15 (368s Burdett) | 2022-07-12 08:00 | 2022-07-12 16:00 | N | N | 25 kV breaker - connect new cables into the cubicle 2B0254U | Circuit Breaker |  | Fortis Request - will need an advice to connect new cables into the cubicle 2B0254U | For Information Only, Restricts Generation
ALTALINK | 167s T2 (167s Ipiatik Lake) | 2022-07-12 08:00 | 2022-07-13 16:30 | N | Y | maintain, doble, fix fiber conduit | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 575s 138kV Bus 1 (575s Sundre), 719L (378s Shell Caroline - 575s Sundre), 575s T1 (575s Sundre), 575s 719N (575s Sundre) | 2022-07-12 09:00 | 2022-07-12 16:00 | N | N | urgent repair: 575s27 needs repair | Bus, Line, Transformer, Circuit Breaker |  | Urgent repair: 575s27 is hot and needs to be repaired as it is unable to hold load for future outages without failure. 1201L ILRAS OOS at 575s for duration. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 498s C1 (498s Tilley), 498s 33 (498s Tilley) | 2022-07-12 10:30 | 2022-07-12 12:30 | N | N | weed spraying | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 1084L NEW (39s-Open Point 'O') - GOI | 2022-07-12 17:00 | 2022-11-21 08:00 | N | Y | complete 1084L construction | Terminal Equipment |  |  | For Information Only
ALTALINK | 1168L NEW (39s-Open Point 'F') - GOI | 2022-07-12 17:00 | 2022-11-21 08:00 | N | Y | complete 1168L relay testing between 39s and open point 'F' and complete 1168L construction | Terminal Equipment |  |  | For Information Only
ALTALINK | 1135L NEW (39s-Open Point 'H') - GOI | 2022-07-12 17:00 | 2022-11-21 08:00 | N | Y | complete 1135L relay testing between 39s and 1047s and complete 1135L construction | Terminal Equipment |  | test | For Information Only
AESO-SC | OATI | 2022-07-12 18:00 | 2022-07-12 19:00 | N | N | Inter-Site Transfer business continuity drill | SCInternal |  | O | For Information Only
ALTALINK | 74s C1 (74s Janet), 74s C2 (74s Janet) | 2022-07-13 08:00 | 2022-07-13 11:00 | N | N | weed spraying | Shunts |  |  | For Information Only, Pre-Condition
ENMAX | 31.1C (SS-31) | 2022-07-13 08:00 | 2022-07-13 16:00 | N | N | HV breaker maintenance | Shunts | HV breaker maintenance 31B138-31CAP. Substation Weed Spraying [Capacitor Bank] |  | For Information Only
ENMAX | 13.2TR (SS-13) | 2022-07-13 08:00 | 2022-07-28 16:00 | N | N | bushing replacement | Transformer | 13.2TR MV Bushing Replacement. Check Reversing Switch. Oil sampling MT, TC |  | For Information Only
ALTALINK | 178s C1 (178s Cynthia) | 2022-07-13 10:00 | 2022-07-13 16:30 | N | N | PRC 5 maintenance | Shunts |  |  | For Information Only
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet), 74s 102 (74s Janet), 74s 103 (74s Janet) | 2022-07-13 11:01 | 2022-07-13 13:00 | N | Y | vegetation management | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 151s C1 (151s Strathmore) | 2022-07-13 14:00 | 2022-07-13 16:00 | N | N | weed spraying | Shunts |  |  | Pre-Condition
CapitalPower | 1018s 7210-T-002 (1018s Shamrock), 1018s 7290-CB-003 (1018s Shamrock) | 2022-07-14 07:00 | 2022-07-14 17:00 | N | N | trip testing | Transformer, Circuit Breaker | Trip testing I-1018s 240CB2 for the newly installed RAS Relays @ 244s & 251s on 983L Issue to: Lander Marr Contact #: 403-700-4120 |  | Restricts Generation
ENBRIDGE | 485s T2 (485s Blackspring), 485s 35CBVAR2 (485s Blackspring Ridge) | 2022-07-14 07:30 | 2022-07-15 17:00 | N | N | maintenance | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 65B138-D82 (SS-65) | 2022-07-14 08:00 | 2022-07-14 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 167s 2052 (167s Ipiatik Lake), 428L (167s Ipiatik Lake - 818s Winefred) | 2022-07-14 08:00 | 2022-07-14 11:30 | N | N | fix tank heater | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L167 (989s Quigley - 2060s Engstrom) | 2022-07-14 09:00 | 2022-07-15 15:30 | N | N | tap up mobile sub 2000s to 7L167s at 989s | Line |  | Tap up mobile sub 2000s to 7L167s @989s | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 191s 792X (191s N.W. Cardiff) | 2022-07-15 07:00 | 2022-07-19 18:00 | N | N | line move at structures 102-104 | Line, Circuit Breaker |  | Line move at structures 102-104 to accommodate road re-route, Phasing checks will be required at 92s5 during return to service switching. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 635PL7-1002 (635EDD-1000 - 635EDD-1004) | 2022-07-15 08:00 | 2022-07-16 17:30 | N | N | support construction activity in the area | Line | Line Outage to support construction activity in the area |  | For Information Only
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2022-07-16 12:00 | 2022-07-16 18:00 | N | Y |  | Line |  |  | 240 kV, Overload
ATCO | 840s McNeill Station | 2022-07-16 20:10 | 2022-08-16 16:00 | N | N | filter bank forced outage | Station | Filter bank is fed off of Breaker 506 and FA4 is OOS. |  | Limits ATC
ALTALINK | 916L (5s East Calgary - 42s Sarcee), 42s 916E (42s Sarcee) | 2022-07-17 08:15 | 2022-07-21 17:45 | N | Y | vault inspections (1~5) at 42s | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | 330P 12TC2 (330p Genesee), 330p 809 (330p Genesee) | 2022-07-18 07:00 | 2022-07-22 17:00 | N | Y | doble Genesee 12TC2 zone | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | T3 (Poundmaker) | 2022-07-18 07:00 | 2022-07-25 07:00 | N | Y | tap changer maintenance | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 813s 901T (813s Little Smoky), 813s 901 (813s Little Smoky), 813s 905 (813s Little Smoky) | 2022-07-18 08:00 | 2022-08-01 17:00 | N | Y | protection upgrades | Transformer, Circuit Breaker |  | July 18, 2022 to July 30 2022 - Isolation points will be 901B, 905B and 701TD Remove panels 3K,4K - install new panel 9T1 901, 905, 901T CT/PT/P&C wiring Demo existing wiring/cabling Replace 500PT disconnect assembly Relay programming and functionality Commission control, alarms and status | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 732L2 (732AL Tap), 730L61 (732L Tap), 730L62 (732L Tap) | 2022-07-18 08:00 | 2022-07-27 11:30 | N | N | replace switches | Switch | 730L (732L2, 730L61, 730L60) - Advice Create 730/732L Open Points D,E,F Hot Line work  Required to replace 3 switches at the tap, |  | For Information Only
ENMAXGPI | 134s 134.1TR (134s Taber Wind Farm), 134s 134.2TR (134s Taber Wind Farm) | 2022-07-18 08:00 | 2022-07-22 18:00 | N | Y | 4 year BOP substation maintenance | Transformer | 134s T1 (134s Taber Wind Farm), 134s T2 (134s Taber Wind Farm) |  | Restricts Generation
ALTALINK | 447s T1 (447s Enchant) | 2022-07-18 08:00 | 2022-07-23 12:00 | N | N | Install and commission a new GE T60. | Transformer |  | Install and commission a new GE T60 to replace the existing T1_B protection. The new protection will also facilitate undervoltage protection. | For Information Only
ENMAX | 5.1TR (SS-5) | 2022-07-18 08:00 | 2022-07-18 16:00 | N | N | 5.1TR T60 battery fail | Transformer |  |  | For Information Only
SUNCOR | 635EDD-1001 635PT-1036 (635EDD-1001) | 2022-07-18 08:00 | 2022-07-19 20:00 | N | N | top up the oil to the transformer conservator | Transformer |  |  | For Information Only
ATCO | 813s 701 (813s Little Smoky), 813s 707 (813s Little Smoky) | 2022-07-18 08:00 | 2022-08-01 12:00 | N | N | cutover and commission 701 CT/P&C circuits to 901T protection | Circuit Breaker |  | Cutover 701 CT/P&C circuits to 901T Protection Commission 701 CT/P&C circuits to 901T protection | Contingency Requires Mitigation
SUNCOR | 29EDD-1 29EDD1s1752 (29EDD-1 Millennium) | 2022-07-18 08:00 | 2022-07-28 12:00 | N | N | breaker replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 33.83L (SS-33 - SS-41), 41B138-33.83 (SS-41) | 2022-07-18 08:00 | 2022-07-19 16:00 | N | N | breaker maintenance 41B138-33.83 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.84L (SS-1 - SS-5) | 2022-07-18 09:00 | 2022-07-18 12:00 | N | N | upgrade JMUX system to JPAX system | Line |  |  | Pre-Condition
ATCO | 861s 601T (861s Eureka River) | 2022-07-18 09:00 | 2022-07-20 16:00 | N | N | transformer maintenance | Transformer |  | Transformer maintenance 601TD is on Hot standby, currently nor carrying any load | For Information Only
ATCO | 947s 701T (947s Weasel Creek), 947s 701 (947s Weasel Creek) | 2022-07-18 09:30 | 2022-07-20 17:30 | N | N | 701T maintenance | Transformer, Circuit Breaker |  | 701T Maintenance | For Information Only
ATCO | 989s 701T (989s Quigley) | 2022-07-18 09:30 | 2022-07-22 17:00 | N | N | outage on 701T. 2000s will be set up to bypass 701T. | Transformer |  | Outage on 701T. 2000s will be set up to bypass 701T. | For Information Only
ATCO | 769s 703T (769s Stettler), 769s 603 (769s Stettler) | 2022-07-18 09:30 | 2022-07-19 14:00 | N | N | transformer class 1 major testing | Transformer, Circuit Breaker |  | TRANSFORMER CLASS1 MAJOR TESTING @ STETTLER 769S 703T REGULATOR CLASS4 MAJOR PM BREAKER 603 VACUUM HSV PARTIAL / COMPLETE TESTING | Creates Radial Feeds, Firm Load Loss
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-07-18 10:00 | 2022-07-21 16:00 | N | Y | crosarm and insulator replacement | Line |  | Crosarm and Insulator replacement project on 7L224 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L57 (727s Kinuso - 735s Swan River) | 2022-07-18 10:00 | 2022-07-25 16:00 | N | N | pole replacement | Line |  | Pole Replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 42s C1 (42s Sarcee), 42s 1652 (42s Sarcee) | 2022-07-18 11:30 | 2022-07-18 13:30 | N | N | vegetation management | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 719L (575s Sundre - 719CL Tap), 575s 719X (575s Sundre) | 2022-07-18 11:45 | 2022-07-26 18:15 | N | N | minor protection upgrade and upgrade of breaker 552 (575s719X) controls | Line, Circuit Breaker | P&C Minor Protection upgrade on L5 (719LX) line protections, and upgrade of breaker 552 (575s719X) controls and protection. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 500s T2 (500s Flatbush) | 2022-07-18 12:00 | 2022-07-22 18:00 | N | N | full meter repairs and maintenance | Transformer |  | 500s T2 Full Meter, Replace 3 PTs and fuse size for 500s15, 500s T2 Arrestor installation, 500s T1 bushing replacement, 500s 4160V insulator replacement, 500s T1 maintenance, 500s T1 oil leak repair, 500s T2 maintenance, 500s T2 oil leak repair, 500s broken yard lights, 500s3 new sign, 500s4 switch maintenance. | For Information Only
ALTALINK | 288s T2 (288s Wolf Creek) | 2022-07-18 12:00 | 2022-07-21 18:00 | N | Y | first trip PRC5 maintenance, fix oil leaks, doble | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 901L (74s Janet - 901AL tap), 74s 2452 (74s Janet), 74s 2552 (74s Janet) | 2022-07-18 12:00 | 2022-07-21 18:00 | N | Y | replacing VT8 | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 42s C2 (42s Sarcee), 42s C3 (42s Sarcee), 42s 74 (42s Sarcee), 42s 76 (42s Sarcee) | 2022-07-18 13:31 | 2022-07-18 16:30 | N | Y | vegetation management | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L02 (860s Crow - 885s McMillan), 7L121 (860s Crow - 7LA121 tap), 860s 701T (860s Crow), 860S 701TCS (860s Crow) | 2022-07-19 07:00 | 2022-07-19 19:00 | N | N | maintenance and switch replacements | Line, Transformer, Switch |  | 701T, 701TCS Maintenance and RTXP switch replacements, Outage is coordinated with interpipe line | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.1TR (SS-33) | 2022-07-19 08:00 | 2022-08-06 08:15 | N | N | bushing replacement, testing, maintenance | Transformer |  |  | For Information Only
SUNCOR | 139s Hillridge | 2022-07-19 08:00 | 2022-07-22 17:00 | N | N | substation maintenance work | Station |  |  | Restricts Generation
ALTALINK | 180s T2 (180s Cope Creek) | 2022-07-19 08:00 | 2022-07-25 15:30 | N | N | drain oil and undress | Transformer |  |  | For Information Only
SUNCOREP | SCR3 Suncor Chin Chute | 2022-07-19 08:00 | 2022-07-22 17:00 | N | N | substation maintenance work | Unit
ALTALINK | 172EL (139s Hillridge - 172L Tap) | 2022-07-19 08:00 | 2022-07-20 20:00 | N | Y | customer substation maintenance | Line |  |  | Restricts Generation
ENMAX | 20.3TR (SS-20) | 2022-07-19 08:00 | 2022-07-20 16:00 | N | N | tapchanger maintenance, oil sampling | Transformer |  |  | For Information Only
ENMAX | 6.1TR (SS-6) | 2022-07-19 08:00 | 2022-07-22 16:00 | N | N | testing and maintenance | Transformer |  |  | For Information Only
ALTALINK | 151s 44 (151s Strathmore), 151s C1 (151s Strathmore) | 2022-07-19 08:30 | 2022-07-19 17:30 | N | N | maintenance | Switch, Shunts |  |  | Pre-Condition
ATCO | 740s 701B (740s H.R. Milner) | 2022-07-19 09:00 | 2022-07-20 17:00 | N | Y | emergency outage due to arcing | Switch |  |  | Restricts Generation
Saskpower | SaskPower C1S | 2022-07-19 10:00 | 2022-07-22 15:00 | N | Y | maintenance | Line | SaskPower C1S |  | Limits ATC
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2022-07-20 07:00 | 2022-07-20 18:00 | N | N |  | Line |  | Urgent repair at structure 292 due to motor vehicle incident | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2022-07-20 07:00 | 2022-07-23 18:30 | N | N | complete urgent repair on structures | Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72NW15 (Namao - Woodcroft), W723 (Woodcroft), N726 (Namao) | 2022-07-20 07:00 | 2022-07-21 15:00 | N | N | woodcroft surge arrestor replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-18 29PT-101 (29EDD-18 Firebag), 29EDD-18 29-752-101 (29EDD-18 Firebag), 29EDD-18 29-752-105 (29EDD-18 Firebag) | 2022-07-20 08:00 | 2022-07-29 18:00 | N | N | pm 10y | Transformer, Circuit Breaker | 29EDD18;29PT-101 SYSTEM;PM 10Y (A) |  | Contingency Requires Mitigation
ENMAX | 43B138-33.84 (SS-43), 33B138-33.84 (SS-33), 33.84L (SS-33 - SS-43) | 2022-07-20 08:00 | 2022-07-22 16:00 | N | N | breaker maintenance and transformer bushing replacement | Circuit Breaker, Line | HV Breaker maintenance 43B138-33.84 HLR. 33.1TR Bushing replacement. Slip over CT install. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 825s 904 (825s Whitefish Lake) | 2022-07-20 09:00 | 2022-07-21 17:00 | N | Y | fill and repair 904 dashpots | Circuit Breaker |  | Fill and repair 904 Dashpots | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 132s 3 (132s Ware Junction) | 2022-07-20 11:00 | 2022-07-20 14:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 132s 18 (132s Ware Junction) | 2022-07-20 14:31 | 2022-07-20 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge) | 2022-07-21 08:00 | 2022-07-25 17:00 | N | Y | line mitigation and cross arm replacement | Line |  | Line mitigation, Cross arm replacement | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 41.1C (SS-41) | 2022-07-21 08:00 | 2022-07-21 11:00 | N | N | substation weed spraying | Shunts |  | Substation Weed Spraying [Capacitor Bank] | Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-07-21 08:00 | 2022-07-27 18:00 | N | N | 29EDD94;29PT-335 SYSTEM;PM 5y,10y | Not In Model |  |  | For Information Only
ENMAX | 8.2TR (SS-8) | 2022-07-21 08:00 | 2022-08-05 16:00 | N | N | protection replacement | Transformer |  | 8 Sub 8.2TR Protection Replacement. Tapchanger maintenance. Oil Sampling MT, TC. 8.2TR Corrective - Winding Temp Cable Replacement | For Information Only
ENMAX | 38.1C (SS-38) | 2022-07-21 11:00 | 2022-07-21 14:00 | N | N | substation weed spraying | Shunts |  | Substation Weed Spraying [Capacitor Bank] | Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), 72LS24 (EP 803s Lambton - Strathcona) | 2022-07-22 07:00 | 2022-07-22 12:00 | N | N | urgent repair LDS13 | Line |  | Lambton: Clearance required for Hydrovac. Conduit install for P&C projects. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark), 72PM25 (Poundmaker - Meadowlark), PM721 (Poundmaker), M726 (Meadowlark), M725 (Meadowlark) | 2022-07-22 07:00 | 2022-07-29 17:00 | N | N | address installation deficiencies | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty) | 2022-07-22 07:00 | 2022-08-31 17:00 | N | N | line relocation Aerial 50st Widening Project | Line |  |  | Pre-Condition
ALTALINK | 426s 1 (426s Coalspur) | 2022-07-22 07:30 | 2022-07-22 10:00 | N | N | facilitate live line work to cut an Open Point 'E' on 740L outside of 426s at 740L263 for installing corona rings on 426s1 A frame | Switch |  | Taking place during existing 501L outage to install mobile at 983s, This will be live line work to cut an Open Point 'E' on 740L outside of 426s at 740L263, Required to install corona rings on 426s1 A frame, Open point 'E' to be used later to issue GOI. | Pre-Condition
ALTALINK | 501L (426s Coalspur - 501CL tap), 501CL (983s Cadomin - 501L Tap), 501L (302s Cardinal River - 501CL tap) | 2022-07-22 07:30 | 2022-07-22 17:30 | N | N | urgent structures replacement 501L ( str's 284-285) and connect mobile HS and LS cables and create open points C and D | Line |  |  | Pre-Condition
ALTALINK | 740L (426s Coalspur - 743L tap) | 2022-07-22 10:30 | 2022-07-22 14:30 | N | N | install corona rings properly on 426s1 A-frame | Line |  |  | Pre-Condition
ALTALINK | 426s 1 (426s Coalspur) | 2022-07-22 15:00 | 2022-07-22 17:00 | N | N | close Open Point 'E' | Switch |  |  | Pre-Condition
ALTALINK | 983s T1 (983s Cadomin) | 2022-07-22 17:30 | 2022-09-09 07:00 | N | N | transformer T1 replacement | Transformer |  | T1 Transformer Replacement, Replace 983s2 Fuse disconnect switch to 6A, Replace 983s10 Fuse to 100A, Replace 25kV Strain insulators, Install Bird Cover-up, Remove an older spare transformer from the station yard that is not connected, | For Information Only
EPCOR | T1 (Woodcroft) | 2022-07-23 07:00 | 2022-07-24 17:00 | N | N | surge arrestor replacement | Transformer |  | Woodcroft TX1 Surge Arrestor Replacement | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 63s T2 (63s Red Deer), 63s 25 (63s Red Deer) | 2022-07-23 08:00 | 2022-07-28 17:00 | N | Y | PRC 5 maintenance, fix leaks, test | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 575s T1 (575s Sundre) | 2022-07-23 10:00 | 2022-07-23 15:30 | N | N | P&C minor protection upgrade on L5 (719LX) line protections, and upgrade of breaker 552 (575s719X) controls and protection | Transformer |  | P&C Minor Protection upgrade on L5 (719LX) line protections, and upgrade of breaker 552 (575s719X) controls and protection. Required OOS due to non-redundant protection to allow cutover of new protections from 575s719X. T1 Protections will be OOS during the de-energization | For Information Only
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2404 (987s Clover Bar) | 2022-07-24 07:00 | 2022-07-25 17:00 | N | Y | Cloverbar: P&C cutovers for DFR/UFLS upgrades | Line, Circuit Breaker |  | Cloverbar: P&C Cutovers for DFR/UFLS Upgrades | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Affects Cranking Path
ENMAX | 20.1TR (SS-20) | 2022-07-24 08:00 | 2022-07-24 16:00 | N | N | emergency outage to investigate/repair 20.1TR high temp alarm | Transformer |  |  | For Information Only
ALTALINK | 447s T2 (447s Enchant) | 2022-07-24 08:00 | 2022-07-26 16:00 | N | N | modify the T2B protection | Transformer |  | Modify the T2B protection to implement an UV protection element and Transfer Trip Init to 25kV Breakers 852 and 952, complete required additional wiring. Wiring is required for the transformer CT circuits for the UV protection for the LOP. | For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10), 42s 693 (42s Sarcee) | 2022-07-24 08:15 | 2022-07-28 17:45 | N | Y | vault inspections (1~5) at 42s | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial) | 2022-07-24 12:30 | 2022-07-28 10:00 | N | N | forced outage | Line |  | washed out structure | For Information Only
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), T2 (EPCOR Hardisty), H722 (EP Hardisty), H723 (EP Hardisty), H726 (EP Hardisty) | 2022-07-25 07:00 | 2022-07-29 17:00 | N | N | hydrovac-ing under west side BUS section for under ground conduit removal | Line, Transformer, Circuit Breaker |  | hydrovac-ing under west side BUS Section for under ground conduit removal | Creates Radial Feeds, Firm Load Loss
EPCOR | T3 (Poundmaker), PM2404 (Poundmaker), PM2405 (Poundmaker), PMAB3 (Poundmaker) | 2022-07-25 07:00 | 2022-07-27 17:00 | N | Y | disconnect maintenance | Transformer, Circuit Breaker, Switch |  | Poundmaker TX3 Doble, PMAB3/PMDS8 Disconnect Maintenance | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 72RW3 (Rossdale - Woodcroft), RW727 (Rossdale), W724 (Woodcroft), W725 (Woodcroft) | 2022-07-25 07:00 | 2022-07-28 16:00 | N | N | CVT/arrestor doble, surge arrestor replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B240-D130 (SS-65) | 2022-07-25 08:00 | 2022-07-25 16:00 | N | Y | HV breaker SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 255s T2 (255s Vulcan) | 2022-07-25 08:00 | 2022-07-26 17:00 | N | N | UV protection addition and T2 'B' modifications for UV 'B' protection | Transformer |  | UV Prot additition and T2 'B' modificationtions for UV 'B' protection | For Information Only
ENMAX | 20.3TR (SS-20) | 2022-07-25 08:00 | 2022-07-29 16:00 | N | N | power factor test transformer, transformer maintenance and gas relay testing | Transformer |  |  | For Information Only
ENMAX | 38.3TR (SS-38) | 2022-07-25 08:00 | 2022-07-28 10:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2022-07-25 08:00 | 2022-07-28 16:00 | N | N | installing new distribution duct bank | Line, Circuit Breaker |  | Valard installing a new distribution duct bank in the vicinity of 9.83 line | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 856s 903T (856s Kinosis) | 2022-07-25 09:00 | 2022-07-27 17:30 | N | Y | maintenance | Transformer |  | 903T Maintenance | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L167 (989s Quigley - 2060s Engstrom) | 2022-07-25 09:00 | 2022-07-28 15:30 | N | N | tap down mobile sub 2000s to 7L167s at 989s | Line |  | Tap down mobile sub 2000s to 7L167s @989s | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 2L112 (BPA Boundary - BCH Nelway) | 2022-07-25 09:00 | 2022-07-28 16:00 | N | Y | replace poles on structure 1/8 | Line | 2L112 (Nelway - Boundary), on Aug 27 8:00 - 16:00 - 2L112 OOS ( isolation pointsNLY 2CB7 OOS, NLY 2CB8 OOS and NLY T2 OOS) | REPLACE POLES ON STRUCTURE 1/8 | 240 kV, Limits ATC
ALTALINK | 133L (19s Wabamun - 234L Tap) | 2022-07-25 09:00 | 2022-07-28 18:00 | N | N | changing out the old dead-end structure and replace with a new one | Line |  | Urgent repair on STR 855, Crew will be changing out the old dead-end structure and replace with a new one. | Pre-Condition
ALTALINK | 254s 414W (254s Coaldale) | 2022-07-25 09:00 | 2022-07-25 17:00 | N | Y | install bird cover | Circuit Breaker | OC to create gen outage record. Record created |  | Restricts Generation
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-07-25 10:00 | 2022-07-28 16:00 | N | Y | crossarm and insulator replacement project on 7L224 | Line |  | Crossarm and insulator replacement project on 7L224 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 741s 702T (741s Fox Creek), 741s 704 (741s ATC Fox Creek) | 2022-07-25 10:00 | 2022-07-28 13:15 | N | N | transformer 702T and breaker 704 maintenance | Transformer, Circuit Breaker |  | transformer 702T and breaker 704 maintenance | For Information Only
ALTALINK | 83s T1 (83s Taber), 83s 65 (83s Taber) | 2022-07-25 11:00 | 2022-07-25 17:30 | N | Y | remove birds nest | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 251s SR1 (251s Whitla), 251s 1352 (251s Whitla) | 2022-07-25 11:30 | 2022-07-27 11:59 | N | Y | maintenance, doble | Shunts, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 296s Rosyth | 2022-07-26 07:00 | 2022-07-26 22:00 | N | N | settings on T2 A & S protections to reduce fault clearing times | Station | 296s  Relays (281441) July 26, 07:00  July 26, 22:00 Job Scope: Settings on T2 A & S protections to reduce fault clearing times to facilitate grounding and workers safety at the substation. Redundant protection always in service. |  | For Information Only
ALTALINK | 498s 5031 (498s Tilley) | 2022-07-26 07:00 | 2022-07-26 17:00 | N | N | 25 kV breaker - install bird cover | Circuit Breaker |  |  | For Information Only
EPCOR | 657s SU2402 (657s Summerside) | 2022-07-26 07:00 | 2022-07-27 17:00 | N | Y | leak detection | Circuit Breaker |  | Summerside: SU2402 leak detection w/Hitachi | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 296s T1 (296s Rosyth) | 2022-07-26 07:30 | 2022-07-26 21:30 | N | N | maintenance and repair oil leaks | Transformer | maintenance, Doble, and repair oil leaks on T1. |  | For Information Only
ENMAX | 7B138-7BT3 (SS-7) | 2022-07-26 08:00 | 2022-07-26 12:00 | N | N | breaker SF6 gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR DFO | EPCOR WSI Solar DG | 2022-07-26 08:00 | 2022-09-23 16:00 | N | N | P1982 EPCOR WSI Solar DG. ISD August 2, 2022 | Unit
ALTALINK | 250p 22 (250p Bighorn Plant), 250P 2 (250P Bighorn Plant) | 2022-07-26 09:00 | 2022-07-26 13:00 | N | Y | maintenence | Switch, Circuit Breaker | TransAlta requested advice for BH2 generator brushgear outage. |  | Restricts Generation
ENMAX | 47B138-771 (SS-47) | 2022-07-26 12:00 | 2022-07-26 16:00 | N | N | HV breaker SF6 gas sample - 47B138-771 | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 492s 454E (492s Monarch) | 2022-07-27 07:00 | 2022-07-27 17:00 | N | N | install bird bover | Circuit Breaker | OC to create gen outage record. |  | Restricts Generation
ALTALINK | 929L (74S Janet - 287s Hazelwood), 74s 252 (74s Janet) | 2022-07-27 07:30 | 2022-07-27 17:30 | N | Y | 240 kV switch maintenance | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 719L (378s Shell Caroline - 575s Sundre), 575s 719N (575s Sundre) | 2022-07-27 07:45 | 2022-07-27 18:45 | N | N | minor protection upgrade of breaker 552 (575s719X) controls and protection | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
Syncrude | 235 (Syncrude Mildred Lake), Mildred T2 (Syncrude Mildred Lake) | 2022-07-27 08:00 | 2022-08-06 08:15 | N | Y | non significant outage: Plant 31 T2 / bus 2 outage | Circuit Breaker, Transformer | Non-Significant Outage: Plant 31 T2 / Bus 2 Outage: The following Generators will be isolated: G2 (53MW) @ Plant 31 Substation The following Disconnect Switches will be operated: 234 @ Plant 31 Substation The following breakers will be operated: 2345 @ Plant 31 Substation 2235 @ Plant 31 Substation 235 @ Plant 31 Substation The following Transformers will be isolated: T2 @ Plant 31 Substation |  | For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 250p 11 (250p Bighorn Plant), 250P 1 (250P Bighorn Plant) | 2022-07-27 09:00 | 2022-07-27 14:00 | N | Y | maintenance | Switch, Circuit Breaker | TransAlta requested advice for BH1 generator brushgear outage. |  | Restricts Generation
ATCO | 774s 704C (774s Monitor), 774s 704 (774s Monitor) | 2022-07-27 10:00 | 2022-07-28 10:00 | N | N | complete breaker testing | Shunts, Circuit Breaker |  | BREAKER SF6 GL314 COMPLETE TESTING 704 | For Information Only, Pre-Condition
ALTALINK | 732L (299s Kingman - 732AL tap), 732L (730L tap - 732AL tap), 732AL (301s Queensland - 732L tap) | 2022-07-27 12:00 | 2022-08-15 11:30 | N | N | replace 732L2, 730L61, 730L60 switches - like for like | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 251s SR2 (251s Whitla), 251s 1452 (251s Whitla) | 2022-07-27 12:00 | 2022-07-28 17:30 | N | Y | maintenance, doble | Shunts, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 6L15 (763s Hanna - 775s Sullivan Lake) | 2022-07-27 15:00 | 2022-07-27 19:00 | N | N | forced outage | Line |  |  | Pre-Condition
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2022-07-28 07:00 | 2022-07-29 13:00 | N | Y | cutovers for DFR/UFLS upgrades | Line |  |  | 240 kV, Pre-Condition
FMGW | FMG1 Forty Mile Granlea | 2022-07-28 08:00 | 2022-11-25 16:00 | N | N | P1912 Suncor Forty Mile Granlea WAGF Phase 2. 200 MW. ISD August 17, 2022 | Unit
ENMAX | 21.1C (SS-21), 21B138-21.CAP (SS-21) | 2022-07-30 08:00 | 2022-07-30 16:00 | N | N | power factor test - 21B138-21CAP-CT | Shunts, Circuit Breaker |  |  | For Information Only
ENMAX | 27.1TR (SS-27), 27MD69-27.1TR (SS-27) | 2022-07-31 08:00 | 2022-07-31 12:00 | N | N | top up transformer oil as a result of low oil alarm | Transformer, Switch |  |  | For Information Only
ENMAX | 27.2TR (SS-27), 27MD69-27.2TR (SS-27) | 2022-07-31 12:00 | 2022-07-31 16:00 | N | N | top up transformer oil as a result of low oil alarm | Transformer, Switch |  |  | For Information Only, Pre-Condition
ATCO | 789s 705R (789s Keg River) | 2022-08-01 07:20 | 2022-08-12 18:00 | N | N | maintenance | Shunts |  | 705R Leak Repair | Pre-Condition
ATCO | 813s 718 (813s Little Smoky) | 2022-08-01 12:01 | 2022-08-14 12:00 | N | N | cutover and commission 718 CT/P&C circuits to 901T protection | Circuit Breaker |  | Cutover 718 CT/P&C circuits to 901T Protection Commission 718 CT/P&C circuits to 901T protection | Contingency Requires Mitigation, Pre-Condition
ATCO | 813s 705 (813s Little Smoky) | 2022-08-01 12:01 | 2022-08-14 17:00 | N | N | cutover/commission 705 CT/P&C circuits to 901T protection | Circuit Breaker | Cutover 705 CT/P&C circuits to 901T Protection Commission 705 CT/P&C circuits to 901T protection |  | Contingency Requires Mitigation
ATCO | 813s 901T (813s Little Smoky) | 2022-08-01 17:01 | 2022-08-14 17:00 | N | Y | work on 901T | Transformer | July 30, 2022 to Aug. 14 2022 will be for work on 901T Isolation points 901TD and 701TD will be used Remove panels 3K,4K - install new panel 9T1 901, 905, 901T CT/PT/P&C wiring Demo existing wiring/cabling Replace 500PT disconnect assembly Relay programming and functionality Commission control, alarms and status |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 7L80 (740s H.R. Milner - 857s Kakwa Ridge), 7L80 (733s Simonette - 857s Kakwa Ridge) | 2022-08-02 08:00 | 2022-08-08 17:00 | N | Y | line mitigation and cross arm replacement | Line |  | Line mitigation, Cross arm replacement | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2022-08-02 08:00 | 2022-08-02 16:00 | N | N | power factor test 5B138-1.84-CT. | Line, Circuit Breaker |  |  | Pre-Condition
ATCO, GREENGATEP | 9L59 (801s Anderson - 972s Tinchebray), 801s 902 (801s Anderson), 801s 903 (801s Anderson), 972s 901 (972s Tinchebray), 972s 902 (972s Tinchebray) | 2022-08-02 08:00 | 2022-08-24 20:11 | N | Y | line 9LA59 tie-in to Garden Plain sub and protection upgrades at both 801s and 972s | Line, Circuit Breaker |  | TransAlta GARDEN PLAIN PROJECT Line 9LA59 tie-in to Garden Plain Sub Protect up grades at both 801S and 972S | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 65B138-D82 (SS-65) | 2022-08-02 08:00 | 2022-08-03 16:00 | N | N | breaker maintenance 65B138-D82 | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 834s 902T (834s Wesley Creek) | 2022-08-02 09:00 | 2022-08-05 16:00 | N | Y | transformer maintenance | Transformer | Transformer maintenance |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2022-08-02 09:00 | 2022-08-02 12:00 | N | N | test new controls of 6L11D2 | Line | Test new controls of 6L11D2 from 50N/601T-Y0 Relay, if possible field staff will attempt to do this with the MOD decoupled to avoid having multiple operations of the line switch |  | Creates Radial Feeds, Firm Load Loss
ATCO | 757s 701 (757s Battle River), 757s 701T (757s Battle River) | 2022-08-02 09:30 | 2022-08-05 17:30 | N | N | transformer testing | Circuit Breaker, Transformer |  | TRANSFORMER CLASS1 MAJOR TESTING @ BATTLE RIVER 757S 701T | Over/Under Voltage, Pre-Condition
ALTALINK, EPCOR | 1059L (38s East Edmonton - 1059AL tap), 1059AL (52s East Industrial - 1059L tap), 1059L (EP 803s Lambton - 1059AL tap), 52s T1 (52s East Industrial), EP 803s L2401 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton) | 2022-08-02 09:30 | 2022-08-12 17:00 | N | Y | 1059L CT, arrestor, East Industrial TX1 doble, EDS1 disconnect maintenance and P&C maintenance | Line, Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-08-02 10:00 | 2022-08-04 16:00 | N | Y | cross arm and insulator replacement | Line |  | Cross arm and insulator replacement project on 7L224 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 275s 2 (275s Jenner) | 2022-08-02 10:30 | 2022-08-04 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1C (SS-38), 38B138-38.1CAP (SS-38) | 2022-08-02 11:00 | 2022-08-02 14:05 | N | N | emergency work on breaker | Shunts, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive) | 2022-08-02 12:01 | 2022-08-02 16:00 | N | N | test new controls of 6L11D3 | Line | Test new controls of 6L11D3 from 50N/601T-Y0 Relay, if possible field staff will attempt to do this with the MOD decoupled to avoid having multiple operations of the line switch |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2022-08-02 18:00 | 2022-08-02 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
SUNCOR | 29PL9-13 (29EDD-34 - 29EDD-65), 29EDD-65 29-952-4821 (29EDD-65), 29EDD-65 29-952-4822 (29EDD-65), 29EDD-34 29-952-112 (29EDD-34), 29EDD-34 29-952-113 (29EDD-34) | 2022-08-03 06:00 | 2022-08-10 12:00 | N | Y | 29EDD34;29PL9-13 SYSTEM;PM 5y,10y and PRC-023 settings update | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | T4 (Poundmaker), 72PM25 (Poundmaker - Meadowlark), PM2402 (Poundmaker), PMDS4 (Poundmaker), PMDS5 (Poundmaker), PM2403 (Poundmaker), PMDS13 (Poundmaker), PM721 (Poundmaker), M723 (Meadowlark) | 2022-08-03 07:00 | 2022-08-05 17:00 | N | Y | Poundmaker bus 3 CVT doble and disconnects Maintenance | Transformer, Line, Circuit Breaker, Switch | Poundmaker BUS 3 CVT Doble and PMDS4, PMDS5 Disconnect Maintenance |  | 240 kV, Pre-Condition, Prevents Normal Events
TRANSALTA | 528s Blue Trail Wind Farm | 2022-08-03 08:00 | 2022-08-03 13:00 | N | N | maintenance | Station |  |  | For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 21B138-21.80 (SS-21) | 2022-08-03 08:00 | 2022-08-04 16:00 | N | Y | power factor test, test LA's and potheads -138-21.80 | Line, Circuit Breaker | Power factor test Test LA's and Potheads -138-21.80 |  | Pre-Condition
WHEL | WHE1 Wheatland Wind | 2022-08-03 08:00 | 2022-11-09 16:00 | N | N | P1718 Greengate Power Wheatland Wind. ISD Aug 03, 2022. 120 MW. | Unit
ATCO | 7L30 (732s Mitsue - 844s AEC Mill) | 2022-08-03 08:00 | 2022-08-04 16:00 | N | N | emergency pole replacement | Line | Emergency Pole replacement, pole leaning severely |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2022-08-03 09:00 | 2022-08-03 12:00 | N | N | removal of 6L11PT2 from 6L11 to complete A/S scheme removal | Line | Removal of 6L11PT2 from 6L11 to complete A/S Scheme removal |  | Pre-Condition
ALTALINK | 297s T2 (297s Rimbey) | 2022-08-03 09:00 | 2022-08-03 17:30 | N | N | repair oil leaks | Transformer |  |  | For Information Only
ALTALINK | 805L (86s Bigstone - 964s Pigeon Lake), 86s 152 (86s Bigstone) | 2022-08-03 11:30 | 2022-08-04 17:30 | N | N | first trip and PRC5 maintenance | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 6L11 (742s Freeman Lake - 854s Swan Dive) | 2022-08-03 12:01 | 2022-08-03 16:00 | N | N | removal of 6L11PT3 from 6L11 to complete A/S scheme removal | Line |  | Removal of 6L11PT3 from 6L11 to complete A/S Scheme removal | Pre-Condition
TRANSALTA | 418s DVAR (418s Ardenville) | 2022-08-03 13:00 | 2022-08-03 17:00 | N | N | partial outage | Shunts |  |  | For Information Only
SUNCOR | 29EDD-94 29-952-9702 (29EDD-94 Voyageur) | 2022-08-04 08:00 | 2022-08-04 18:00 | N | Y | breaker open for relay replacement | Circuit Breaker |  | This 260kV breaker is required to be open during the relay replacement. No isolation is required. This relay is for the breaker charging circuit only. | 240 kV, Creates Radial Feeds, Firm Load Loss
BHE Canada | 120s C2 (120s Picture Butte), 120s 1252 (120s Picture Butte) | 2022-08-04 08:00 | 2022-10-07 18:00 | N | Y | cap bank work | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 447s Enchant | 2022-08-04 08:00 | 2022-08-05 17:00 | N | N | functional test T2 "B" undervoltage trip to 25kV breakers 409W and 410W | Station | Functional test T2 "B Undervoltage trip to 25kV breakers 409W and 410W. Following relay to be OOS: B87/50/51/51NN/27/T2 & B27/DER Redundancy A protection to remain in service for duration of the outage |  | For Information Only
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 191s 792X (191s N.W. Cardiff) | 2022-08-05 07:00 | 2022-08-06 17:00 | N | N | urgent - iinstall screw barrel at structure 102 and move temporary structure to screw barrel | Line, Circuit Breaker |  | Urgent outage to install screw barrel at structure 102 and move temporary structure to screw barrel | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 801L (62s Brazeau Plant Plant - 294s Brazeau Plant Outlet Works) | 2022-08-05 12:25 | 2022-08-06 00:30 | N | N | forced outage | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 26.2TR (SS-26), 26B138-26.83 (SS-26), 26B138-26BT3 (SS-26), 26MD138-26.2TR (SS-26), SW81 (SS-26), SW82 (SS-26), SW83 (SS-26) | 2022-08-06 08:00 | 2022-08-06 12:00 | N | N | summer substation washing, check reversing switch | Line, Transformer, Circuit Breaker, Switch | Summer Substation Washing. Check Reversing Switch |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32), 26.1TR (SS-26), 26B138-26.81 (SS-26), 26B138-26BT3 (SS-26), 26MD138-26.1TR (SS-26), SW84 (SS-26), SW85 (SS-26), SW86 (SS-26), SW85 (SS-32) | 2022-08-06 12:00 | 2022-08-06 18:00 | N | N | summer substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 89s 252 (89s Ellerslie) | 2022-08-07 16:45 | 2022-09-07 07:29 | N | Y | forced outage | Circuit Breaker | Personnel on site verified there is a fire in the substation. |  | 240 kV, Contingency Requires Mitigation
EPCOR | 665s D2402 (665s Dome) | 2022-08-08 07:00 | 2022-08-13 17:00 | N | Y | D2402 bay doble and breaker maintenance | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
TERICPOWER | 728s Mercer Hill DER Battery | 2022-08-08 08:00 | 2022-08-22 16:00 | N | N | P2387 728s Mercer Hill DER Battery Phase 2, ISD Aug 15, 2022 | Unit
ENMAX | 5.8TR (SS-5) | 2022-08-08 08:00 | 2022-09-02 16:00 | N | N | leak investigation and repair | Transformer | 5.8TR Leak Investigate and Repair. Oil Sampling - 5.8-TC - Tapchanger |  | For Information Only
ATCO | 9L29 (946s Oakland - 963s Coyote Lake), 946s 908 (946s Oakland), 946s 909 (946s Oakland), 946s 908B (946s Oakland), 946s 909A (946s Oakland), 946s 9L29D2 (946s Oakland), 963s 901 (963s Coyote Lake), 963s 901B (963s Coyote Lake), 963s 9L29D1 (963s Coyote Lake) | 2022-08-08 08:00 | 2022-08-11 17:00 | N | Y | P & C circuit cutovers commission | Line, Circuit Breaker, Switch |  | BER Hand Hills Wind Project P & C circuit cutovers Commission LTO 908 & 909 52b open status and line MOD 9L29D2 89b open status @ 946S and LTO 901 open status and line MOD, 9L29D1 open status @ 963S, end-to-end testing | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
TRANSALTA | IEW1 Summerview Phase 1 | 2022-08-08 09:00 | 2022-08-08 17:00 | N | N | substation maintenance | Unit
CHDI | SUM1 Summerview | 2022-08-08 09:00 | 2022-08-08 17:00 | N | N | substation maintenance | Unit
TRANSALTA | IEW2 Summerview Phase 2 | 2022-08-08 09:00 | 2022-08-08 17:00 | N | N | substation maintenance | Unit
VISIONREQ | 354s Summerview | 2022-08-08 09:00 | 2022-08-08 17:00 | N | N | substation maintenance | Station |  |  | Restricts Generation
ATCO | 732s 704 (732s Mitsue) | 2022-08-08 09:00 | 2022-08-10 12:00 | N | N | repair, top up and test the breaker | Circuit Breaker |  | Breaker has an SF6 leak, need to repair/ top up and test the breaker | Contingency Requires Mitigation
ALTALINK | 562s 240kV Bus 2 (562s Cypress), 562s 138kV Bus 2 (562s Cypress), 562s T2 (562s Cypress), 562s 252 (562s Cypress), 562s 1152 (562s Cypress), 562s 1652 (562s Cypress), 562s 2052 (562s Cypress), 562s 6 (562s Cypress), 562s 24 (562s Cypress), 562s 32 (562s Cypress), 562s 40 (562s Cypress) | 2022-08-08 09:00 | 2022-08-11 16:00 | N | Y | new 138 kV Bus 2 B protection being installed | Bus, Transformer, Circuit Breaker, Switch | New 138kV Bus 2 B Protection being installed. Will need to cutover CT circuits and trip test breakers on 138kV Bus 2. |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 2022-08-08 09:00 | 2022-08-11 18:00 | N | N | component replacements | Line | Component Replacements 185L ( Str Range 1-117) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2075s T11 (2075s Newell), 2075s 916 (2075s Newell), 2075s 917 (2075s Newell), 2075S 927 (2075s Newell), 2075S 928 (2075s Newell), 2075S 929 (2075s Newell), 2075S 934 (2075s Newell), 2075s ACF11 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell), 2075S 927A (2075s Newell), 2075S 928A (2075s Newell), 2075S 929A (2075s Newell), 2075S 934A (2075s Newell), 2075s ACF1D1 (2075s Newell) | 2022-08-08 09:00 | 2022-08-25 11:30 | N | Y | inspections, testing and repairs | Line, Transformer, Circuit Breaker, Shunts, Switch | 2075S - NEWELL OUTAGE Switched out under 2-62643 - Valve Hall Inspections - PRC-005 Testing - Fire System Tests - Repair Ground Switches |  | 240 kV, 500 kV, Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2022-08-08 09:00 | 2022-08-25 11:30 | N | Y | inspections, testing and repairs | Line | EATL OUTAGE - Valve Hall Inspections - PRC-005 Testing - Fire System Tests - Repair Ground Switches |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 2029s Heathfield, 2029s 500kV Bus 1200BS1 (2029s Heathfield), 2029s 500kV Bus 1200BS21 (2029s Heathfield), 13L50 (2029s Heathfield - 2075s Newell), 12L70 (12s Heartland - 2029s Heathfield), 12L85 (12s Heartland - 2029s Heathfield), 2029s 1200SST1 (2029s Heathfield), 2029s 1200SST2 (2029s Heathfield), 2029s T11 (2029s Heathfield), 2029s 1201 (2029s Heathfield), 2029s 1202 (2029s Heathfield), 2029s 1203 (2029s Heathfield), 2029s 1204 (2029s Heathfield), 2029s 1205 (2029s Heathfield), 2029s 1207 (2029s Heathfield), 2029s 1206 (2029s Heathfield), 2029s 1208 (2029s Heathfield), 2029s 1209 (2029s Heathfield), 2029s 1214 (2029s Heathfield), 2029s 1215 (2029s Heathfield), 2029s 1221 (2029s Heathfield), 2029s 1224 (2029s Heathfield), 2029s 1302 (2029s Heathfield), 2029s 1200SST1D1 (2029s Heathfield), 2029s 1200SST2D1 (2029s Heathfield), 2029s 1201A (2029s Heathfield), 2029s 1201B (2029s Heathfield), 2029s 1202A (2029s Heathfield), 2029s 1202B (2029s Heathfield), 2029s 1203A (2029s Heathfield), 2029s 1203B (2029s Heathfield), 2029s 1204A (2029s Heathfield), 2029s 1204B (2029s Heathfield), 2029s 1205A (2029s Heathfield), 2029s 1205B (2029s Heathfield), 2029s 1206A (2029s Heathfield), 2029s 1206B (2029s Heathfield), 2029s 1207A (2029s Heathfield), 2029s 1207B (2029s Heathfield), 2029s 1208A (2029s Heathfield), 2029s 1208B (2029s Heathfield), 2029s 1209A (2029s Heathfield), 2029s 1209B (2029s Heathfield), 2029s 1213A (2029s Heathfield), 2029s 1214A (2029s Heathfield), 2029s 1214B (2029s Heathfield), 2029s 1215A (2029s Heathfield), 2029s 1215B (2029s Heathfield), 2029s 1218 (2029s Heathfield), 2029s 1218A (2029s Heathfield), 2029s 1219 (2029s Heathfield), 2029s 1219A (2029s Heathfield), 2029s 1220 (2029s Heathfield), 2029s 1220A (2029s Heathfield), 2029s 1221A (2029s Heathfield), 2029s 1222 (2029s Heathfield), 2029s 1222A (2029s Heathfield), 2029s 1223 (2029s Heathfield), 2029s 1223A (2029s Heathfield), 2029s 1224A (2029s Heathfield), 2029s 12L70D1 (2029s Heathfield), 2029s 12L85D1 (2029s Heathfield), 2029s ACF11 (2029s Heathfield), 2029s ACF12 (2029s Heathfield), 2029s ACF13 (2029s Heathfield), 2029s ACF14 (2029s Heathfield), 2029s ACF1D1 (2029s Heathfield), 2029s ACF21 (2029s Heathfield), 2029s ACF22 (2029s Heathfield), 2029s ACF23 (2029s Heathfield), 2029s ACF2D1 (2029s Heathfield), 2029s T11D1 (2029s Heathfield) | 2022-08-08 09:00 | 2022-08-25 11:30 | N | Y | inspections, testing and repairs | Station, Bus, Line, Transformer, Circuit Breaker, Not In Model, Switch, Shunts | 2029S - HEATHFIELD OUTAGE Switched out under 2-62643 - Valve Hall Inspections - PRC-005 Testing - Fire System Tests - Repair Ground Switches |  | 500 kV, Pre-Condition
ALTALINK | 312s 138kV Bus 1 (312s Fidler), 312s T1 (312s Fidler), 312s 1352 (312s Fidler), 312s 1752 (312s Fidler), 312s 37 (312s Fidler), 312s 42 (312s Fidler), 312s 50 (312s Fidler) | 2022-08-08 10:00 | 2022-08-11 17:30 | N | Y | transformer maintenence | Bus, Transformer, Circuit Breaker, Switch | 312s TX18795 & 138 kV Bus GOI 1st Scope) T1 Maintenance, Doble, 312s40 PT needs oil. Damper wire fastening. PRC5 work 2nd Scope) VT22 Oil top up & leak repair |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ATCO | 728s Mercer Hill | 2022-08-08 10:00 | 2022-08-09 16:00 | N | N | 25 kV breaker 501 maintenance | Station |  | breaker 501 maintenance | For Information Only
ATCO | 907s 701T (907s Waddell) | 2022-08-08 10:30 | 2022-08-10 12:00 | N | N | transformer maintenance | Transformer | 701T Maintenance 2000S Mobile sub will be install in coordination with this outage. |  | Pre-Condition
ALTALINK | 410s 352 (410s Josephburg) | 2022-08-08 11:30 | 2022-08-11 17:30 | N | Y | CT replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 309s T2 (309s Anthony Henday), 309s 252 (309s Anthony Henday) | 2022-08-09 07:00 | 2022-08-10 17:00 | N | N | install cover up on customer 25 kV underground cables and switchyard | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 20s T5 (20s Ghost), 20s 8 (20s Ghost) | 2022-08-09 07:00 | 2022-08-18 17:00 | N | N | complete cutover of 20s222, 20s2068, breaker 152 and VT11 to new building and applicable protections. install CTs for T5A and T5B protections and complete trip testing from all BF | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 893L (312s Fidler - 893AL tap), 893L (893AL tap - 893BL tap), 893AL (112s Windy Point - 893L tap) | 2022-08-09 07:30 | 2022-08-10 16:30 | N | Y | maintenance on 893L 72J/73J/74J | Line |  |  | Pre-Condition, Restricts Generation
ALTALINK | 624L (312s Fidler - 354s Summerview) | 2022-08-09 07:30 | 2022-08-10 16:30 | N | Y | maintenance on 893L 72J/73J/74J due to proximity | Line | required for maintenance on 893L 72J/73J/74J due to proximity |  | Restricts Generation
ENMAX | 13.1TR (SS-13) | 2022-08-09 08:00 | 2022-08-11 16:00 | N | N | power factor test transformer and maintenance | Transformer |  |  | For Information Only
ATCO | 6L03 (757s Battle River - 6L17 Tap) | 2022-08-09 08:00 | 2022-08-11 16:00 | N | N | crossarm and insulator replacement | Line |  | We require a GOI on 6L03 for crossarm and insulator replacement. | Pre-Condition
PEL | Pembina Empress Cogen | 2022-08-09 08:00 | 2022-10-31 16:00 | N | N | P2235 Pembina Empress Cogen Phase 2. 46MW. ISD Sep 14, 2022 | Unit
Syncrude | Mildred T18 (Syncrude Mildred Lake), Mildred T19 (Syncrude Mildred Lake), 1935 (Syncrude Mildred Lake), 1835 (Syncrude Mildred Lake) | 2022-08-09 08:00 | 2022-08-19 20:00 | N | N | install upgraded data concentrator D200 and bay controller D25 | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 20s 138kV North Bus (20s Ghost), 56L (20s Ghost - 245s Seebe), 418L (20s Ghost - 189L Tap), 20s T5 (20s Ghost), 20s 56 (20s Ghost), 20s 452 (20s Ghost), 20s 8 (20s Ghost), 245s 56E (245s Seebe), 20s 18 (20s Ghost), 20s 55 (20s Ghost), 20s 57 (20s Ghost), 20s 79 (20s Ghost), 20s 81 (20s Ghost), 245s 5 (245s Seebe) | 2022-08-09 08:01 | 2022-08-13 18:00 | N | N | complete cutover of VT2/20s8/T5 to new building and applicable protections | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Affects Cranking Path
ALTALINK | 178s T1 (178s Cynthia) | 2022-08-09 08:30 | 2022-08-10 18:00 | N | N | T1 leak repair | Transformer |  |  | For Information Only
ATCO | 7L160 (837s Mahihkan - 970s Bourque), 837s 703 (837s Mahihkan) | 2022-08-09 09:00 | 2022-08-12 16:30 | N | N | breaker major PM | Line, Circuit Breaker |  | 703 Breaker Major PM | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 2075s 240kV Bus 900BS2 ( 2075s Newell), 2075s 906 (2075s Newell), 2075S 912 (2075s Newell), 2075s 918 (2075s Newell), 2075s 921 (2075s Newell), 2075s 923 (2075s Newell), 2075s 906B (2075s Newell), 2075s 912B (2075s Newell), 2075s 918B (2075s Newell), 2075s 921B (2075s Newell), 2075s 924B (2075s Newell) | 2022-08-09 09:00 | 2022-08-09 17:30 | N | Y | PRC-005 testing and AC yard switch repairs/investigations | Bus, Circuit Breaker, Switch |  | 2075S - Newell AC Yard Outage Coordinated with DC outage 2-62645. Switch AC yard out after DC yard is out of service. 916A & 917B will be double tagged. - PRC-005 Testing - AC yard switch repairs/investigations Station service to be fed from alternate station service feed from Fortis. Low voltage isolation to occur on site | 240 kV, Contingency Requires Mitigation
ALTALINK | 805L (86s Bigstone - 964s Pigeon Lake) | 2022-08-10 08:00 | 2022-08-10 13:00 | N | N | close open point A by connecting 472s 138 kV risers to the line side of 964s805E (805L) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
TRANSALTA | 1063s Windrise | 2022-08-10 08:00 | 2022-08-10 16:00 | N | N | maintenance | Station |  |  | For Information Only
ATCO | 2075s 240kV Bus 900BS1 ( 2075s Newell), 2075s 904 (2075s Newell), 2075s 910 (2075s Newell), 2075s 919 (2075s Newell), 2075s 922 (2075s Newell), 2075s 904A (2075s Newell), 2075s 910A (2075s Newell), 2075s 919A (2075s Newell), 2075s 922A (2075s Newell) | 2022-08-10 09:00 | 2022-08-10 17:30 | N | Y | Newell AC yard outage, PRC-005 testing | Bus, Circuit Breaker, Switch | 2075S - Newell AC Yard Outage Coordinated with DC outage 2-62645. Switch AC yard out after DC yard is out of service. 916A & 917B will be double tagged. - PRC-005 Testing - AC yard switch repairs/investigations Station service to be fed from alternate station service feed from Fortis. Low voltage isolation to occur on site |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 863s 902T (863s Paintearth) | 2022-08-10 09:00 | 2022-09-07 17:30 | N | Y | oil reclaim on 902T | Transformer |  | Oil reclaim on 902T at 863s Paintearth 863S 902T is currently OOS and not carrying any load under permit 2-62106 | 240 kV, For Information Only
ATCO | 728s 503 (728s Mercer Hill) | 2022-08-10 10:00 | 2022-08-11 16:00 | N | N | breaker 503 maintenance | Circuit Breaker |  | breaker 503 maintenance | For Information Only
ALTALINK | 837L (538s Buford - 964s Pigeon Lake), 964s 837N (964s Pigeon Lake) | 2022-08-10 13:00 | 2022-08-10 18:00 | N | N | 472s mobile & MR1 to take load @ 964s, maintenance on 964s34 | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 123L (19s Wabamun - 352s Onoway), 352s 123 (352s Onoway), 352s 21 (352s Onoway) | 2022-08-10 13:00 | 2022-08-11 16:00 | N | N | maintenance on structure 17 | Line, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 964s T3 (964s Pigeon Lake) | 2022-08-10 17:00 | 2022-08-29 17:30 | N | N | 964s T3 overhaul and 25 kV equipment maintenance | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 309s T1 (309s Anthony Henday), 309s 152 (309s Anthony Henday) | 2022-08-11 07:00 | 2022-08-12 17:00 | N | N | install cover up on customer 25 kV underground cables and switchyard | Transformer, Circuit Breaker |  |  | For Information Only
Syncrude | T4 (Aurora) | 2022-08-11 08:00 | 2022-10-13 20:00 | N | Y | maintenance | Transformer |  |  | 240 kV, Restricts Generation
ENMAX | 11.4TR (SS-11) | 2022-08-11 08:00 | 2022-08-11 16:00 | N | N | transformer maintenance and testing | Transformer |  | Transformer Maintenance. Gas relay testing. Oil Sampling MT, TC | For Information Only
ATCO | 7L120 (788s Hotchkiss - 905s Meikle), 788s 704 (788s Hotchkiss), 788s 7L120D1 (788s Hotchkiss) | 2022-08-11 09:00 | 2022-08-11 16:00 | N | N | PRC-005 trip testing from protection relay | Line, Circuit Breaker, Switch |  | PRC-005 trip testing from protection relay | Affects Cranking Path
ENMAX | 1.82L (SS-1 - SS-5), 5.1TR (SS-5), 5.6TR (SS-5), 5.8TR (SS-5), 5B138-5BT12 (SS-5), 5B138-5BT7 (SS-5), SW101 (SS-5), SW90 (SS-5), SW94 (SS-5) | 2022-08-12 08:00 | 2022-08-14 16:00 | N | N | investigate and repair 5.8TR leak | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 788s 701R (788s Hotchkiss), 788s 706 (788s Hotchkiss) | 2022-08-12 09:00 | 2022-08-12 16:00 | N | N | prc trip coil testing, SPR relay testing on 701R | Shunts, Circuit Breaker |  | prc trip coil testing, SPR relay testing on 701R | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 39.82L (SS-39 - SS-162), 39B138-39.82 (SS-39), SW88 (SS-39) | 2022-08-13 08:00 | 2022-08-14 16:00 | N | N | 39.3TR ECI bushing/slip over CT/MV bushing replacement, single pole replacement on structure 41 | Line, Circuit Breaker, Switch | 39.3TR ECI Bushing / Slip Over CT / MV Bushing Replacement. Single pole replacement on Structure 41 |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 288s T1 (288s Wolf Creek) | 2022-08-14 08:00 | 2022-08-18 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2022-08-15 07:00 | 2022-08-19 17:00 | N | Y | P&C cutovers for Cloverbar DFR and UFLS upgrade projects | Transformer, Circuit Breaker | Cloverbar TX3: P&C Cutovers for Cloverbar DFR and UFLS Upgrade Projects |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), T1 (Meadowlark), M721 (Meadowlark), M722 (Meadowlark), MAB1 (Meadowlark), MDS2 (Meadowlark), MDS3 (Meadowlark) | 2022-08-15 07:00 | 2022-08-19 17:00 | N | N | doble, MDS2 maintenance and M722 repair | Line, Transformer, Circuit Breaker, Switch | Meadowlark TX1/CVT/Arrestor Doble and MDS2 Disconnect Maintenance and M722 Repair |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 665s D2401 (665s Dome) | 2022-08-15 07:00 | 2022-08-20 17:00 | N | Y | doble and breaker maintenance | Circuit Breaker | Dome D2401 Bay Doble and Breaker Maintenance |  | 240 kV, Creates Radial Feeds, Firm Load Loss,
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2022-08-15 07:00 | 2022-08-16 18:00 | N | N | repair failed switch 401PS-6000 | Line | Suncor has requested an urgent outage to repair their failed switch 401PS-6000 |  | 240 kV, Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-3 29PT-6 (29EDD-3) | 2022-08-15 08:00 | 2022-08-21 16:00 | N | Y | protection work (device 87) | Transformer | The following relay work to be performed during the GTG-6 generator planned outage: 450027580 (M2017356) 29EDD-3 Block 7 Relays CWP02 RELAY,PROTECTION,87T,SR745,FOR 29PT6 RELAY,PROTECTION,87T,SEL387,FOR 29PT6 |  | 240 kV, For Information Only
ATCO, AESO-SC | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge), 7L80-Pseudo (740s H.R. Milner) | 2022-08-15 08:00 | 2022-08-22 17:00 | N | Y | line mitigation, cross arm replacement | Line, Switch | Line mitigation, Cross arm replacement |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek), 396s 185 (396s Pincher Creek), 379s 185N (379s Shell Canada Waterton) | 2022-08-15 09:00 | 2022-08-18 18:00 | N | N | component replacements 185L (str range 1-117) | Line, Circuit Breaker | Component Replacements 185L ( Str Range 1-117) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 562s 240kV Bus 1 (562s Cypress), 562s 138kV Bus 1 (562s Cypress), 562s T1 (562s Cypress), 562s 152 (562s Cypress), 562s 1052 (562s Cypress), 562s 1352 (562s Cypress), 562s 1752 (562s Cypress), 562s 1 (562s Cypress), 562s 19 (562s Cypress), 562s 25 (562s Cypress), 562s 33 (562s Cypress), 562s 59 (562s Cypress), 562s 60 (562s Cypress) | 2022-08-15 09:00 | 2022-08-18 16:00 | N | Y | new 138 kV bus 1 B protection being installed, cutover CT circuits and trip test breakers on 138 kV bus 1 | Bus, Transformer, Circuit Breaker, Switch | New 138kV Bus 1 B Protection being installed. Will need to cutover CT circuits and trip test breakers on 138kV Bus 1. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 800s 703C (800s Friedenstal), 800s 703 (800s Friedenstal) | 2022-08-15 09:00 | 2022-08-16 16:00 | N | N | breaker maintenance | Shunts, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 7L138 (788s Hotchkiss - 905s Meikle), 788s 701 (788s Hotchkiss) | 2022-08-15 09:00 | 2022-08-16 16:00 | N | N | breaker maintenance, PRC trip coil testing from protection relay | Line, Circuit Breaker | breaker maintenance, PRC trip coil testing from protection relay |  | Pre-Condition, Affects Cranking Path
ATCO | 849s 905 (849s Joslyn Creek) | 2022-08-15 09:30 | 2022-08-17 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p 2152 (320p Keephills) | 2022-08-15 10:30 | 2022-08-16 17:30 | N | Y | top up low gas in breaker | Circuit Breaker |  |  | 240 kV
ALTALINK | 38s C1 (38s East Edmonton), 38s 3052 (38s East Edmonton) | 2022-08-15 10:30 | 2022-08-18 17:30 | N | N | 38s3052 trip dashpot and breaker pole replacement | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 6L03 (757s Battle River - 6L17 Tap), 757s 603 (757s Battle River) | 2022-08-15 11:00 | 2022-08-17 16:00 | N | N | crossarm and insulator replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 281s T1 (281s Johnson) | 2022-08-15 11:30 | 2022-08-17 17:30 | N | Y | maintenance, doble | Transformer |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 799s T1 (799s Coleman) | 2022-08-15 11:30 | 2022-08-18 17:30 | N | N | transformer maintenance (TX is currently N.O.) | Transformer |  |  | For Information Only
ATCO | 882s 701T (882s Triangle) | 2022-08-15 13:00 | 2022-08-23 13:00 | N | N | transformer maintenance | Transformer | Transformer maintenance, Load will be transferred to 787S High Prairie |  | For Information Only, Pre-Condition
ALTALINK | 63s 552 (63s Red Deer) | 2022-08-15 13:00 | 2022-08-25 15:19 | N | Y | replacing breaker control and breaker fail relays | Circuit Breaker | Replacing 552 breaker control and breaker fail relays with new C60 module. |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 275s T2 (275s Jenner), 275s 240kV Bus 2 (275s Jenner), 275s 1952 (275s Jenner), 275s 8 (275s Jenner), 275s 15 (275s Jenner), 275s 9 (275s Jenner), 275s 36 (275s Jenner) | 2022-08-16 07:15 | 2022-08-18 17:45 | N | Y | integrate and commission trip circuits and status and to install and test new Z relay, tie in 240kV BUS to new 949L Bay 2nd Scope) repairing 275s36 | Transformer, Bus, Circuit Breaker, Switch | Outage on 275sT2 (TX18458) and associated breakers required to integrate and commission trip circuits and status involving new breaker 275s2652 and to install and test new Z relay on 275s36 airbreak.Tie in 240kV BUS to new 949L Bay 2nd Scope) AML crew repairing 275s36 |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 952 (310p Sundance) | 2022-08-16 07:30 | 2022-08-16 17:30 | N | Y | grading capacitor replacement on 310p952 | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10), 10.2TR (SS-10), SW84 (SS-10), 10MD138-10.2TR (SS-10), SW85 (SS-10), 10B138-693 (SS-10), SW86 (SS-10), 42s 693 (42s Sarcee) | 2022-08-16 08:00 | 2022-08-16 12:00 | N | Y | summer substation washing | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 83s C1 (83s Taber), 83s C2 (83s Taber), 83s 61 (83s Taber), 83s 67 (83s Taber) | 2022-08-16 08:00 | 2022-08-16 11:00 | N | N | weed spraying | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3) | 2022-08-16 08:00 | 2022-08-16 16:00 | N | N | HV breaker A phase CT measurement - 3B138-3.84 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | D05 79 (D05) | 2022-08-16 08:00 | 2022-08-17 20:00 | N | N | lower Camp differential relay changeout | Circuit Breaker |  |  | For Information Only
ALTALINK | 135s 4670 (135s Conrad) | 2022-08-16 08:00 | 2022-08-16 12:00 | N | Y | directional overcurrent settings need to be modified and tested due to modifications on the line | Circuit Breaker | directional overcurrent settings need to be modified and tested due to modifications on the line. A feeder outage is required to complete the modifications and testing. |  | For Information Only, Restricts Generation
SUNCOR, ATCO | 29PL6-1 (836s Steepbank - 29EDD-55), 836s 628 (836s Steepbank), 836s 629 (836s Steepbank), 836s 628A (836s Steepbank), 836s 629A (836s Steepbank), 836s 29PL6-1CS (836s Steepbank) | 2022-08-16 08:00 | 2022-08-30 18:00 | N | N | switch and arrestor maintenance pm 10y | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ENMAX | 31.1C (SS-31), 31B138-31CAP (SS-31) | 2022-08-16 08:00 | 2022-08-16 16:00 | N | N | cap bank current imbalance fuse replacement | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 263s C1 (263s Strachan) | 2022-08-16 08:00 | 2022-11-14 16:00 | N | N | forced outage | Shunts |  |  | For Information Only, Pre-Condition
ATCO | 7L137 (768s Rowley - 770s Three Hills), 768s 703 (768s Rowley), 768s 7L137D1 (768s Rowley) | 2022-08-16 09:00 | 2022-08-16 12:00 | N | N | T&O for commissioning new 52a, 7L137 open at 768S | Line, Circuit Breaker, Switch | T&O for commissioning new 52a, 7L137 Open at 768S |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | T3 (BCH Natal), 2CB1 (BCH Natal) | 2022-08-16 09:00 | 2022-08-30 17:00 | N | Y | disconnect inspections and inspections/doble testing BC maintenance does not affect the Alberta ATC | Transformer, Circuit Breaker | NTL T3 OOS NTL 2CB1 OOS NTL 60CB3 OOS NTL 2D2CB1 OOS NTL 2D3 OOS NTL 60VTT3 OOS |  | 240 kV, For Information Only
ALTALINK | 996s Imperial Oil Carson Lake, 996S 519 (996s Imperial Oil Carson Lake) | 2022-08-16 10:00 | 2022-08-18 16:30 | N | N | 69kV bushing replacement, brazing of new lugs, and replacement of liquid temperature gauge | Station, Switch |  |  | For Information Only
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10.1TR (SS-10), 10MD138-10.1TR (SS-10), SW83 (SS-10), SW82 (SS-10), SW81 (SS-10), 10B138-832 (SS-10), SW86 (SS-12) | 2022-08-16 12:00 | 2022-08-16 18:00 | N | Y | summer substation washing | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett), 368s 35 (368s Burdett), 368s 44 (368s Burdett) | 2022-08-16 12:00 | 2022-08-16 15:00 | N | N | weed spraying | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 768s 704 (768s Rowley), 7L25 (768s Rowley - 802s Michichi Creek) | 2022-08-16 12:01 | 2022-08-16 17:00 | N | N | T&O for commissioning new 52a, 7L25 open at 768S | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 135s 20 (135s Conrad) | 2022-08-16 13:00 | 2022-08-16 17:00 | N | Y | directional overcurrent settings need to be modified and tested due to modifications on the line | Circuit Breaker | Directional overcurrent settings need to be modified and tested due to modifications on the line. A feeder outage is required to complete the modifications and testing. |  | Restricts Generation
ALTALINK | 310p 1852 (310p Sundance) | 2022-08-17 07:30 | 2022-08-17 17:30 | N | Y | grading capacitor replacement | Circuit Breaker | Grading capacitor replacement on 310p1852. 310pT35 will be fed via 1045L. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-18 29-752-105 (29EDD-18 Firebag) | 2022-08-17 08:00 | 2022-08-17 18:00 | N | N | trip coil replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK, ENMAX | 5s T1 (5s East Calgary), MD80 (SS-2), MD88 (SS-2), MD96 (SS-2), MD104 (SS-2), MD112 (SS-2) | 2022-08-17 08:00 | 2022-08-17 10:00 | N | Y | substation washing | Transformer, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 205s Castle Rock Ridge | 2022-08-17 08:45 | 2022-08-17 15:00 | N | Y | perform drilling and repairs on turbine foundations | Station | Enercon is requesting two Castle Rock Ridge circuit outages next week, to perform drilling and repairs on turbine foundations |  | Restricts Generation
ATCO | 834s 708 (834s Wesley Creek) | 2022-08-17 09:00 | 2022-08-18 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2022-08-17 09:00 | 2022-08-17 17:00 | N | Y | required out of service for 9933R MPLS upgrade | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2022-08-17 09:00 | 2022-08-18 17:30 | N | Y | top up low gas in breaker | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ATCO | 7L51 (788s Hotchkiss - 927s Buchanan Creek), 788s 702 (788s Hotchkiss) | 2022-08-17 09:00 | 2022-08-18 16:00 | N | N | breaker maintenance and PRC trip coil testing from protection relay | Line, Circuit Breaker | breaker maintenance, PRC trip coil testing from protection relay |  | Pre-Condition, Affects Cranking Path
ALTALINK, ENMAX | 5s T2 (5s East Calgary), MD87 (SS-2), MD95 (SS-2), MD101 (SS-2), MD103 (SS-2), MD111 (SS-2), MD113 (SS-2) | 2022-08-17 10:00 | 2022-08-17 12:00 | N | Y | substation washing | Transformer, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary), 5s 752 (5s East Calgary), 5s 852 (5s East Calgary), 5s 70 (5s East Calgary) | 2022-08-17 10:00 | 2022-08-17 14:00 | N | N | weed spraying | Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 7L25 (768s Rowley - 802s Michichi Creek), 802s 707 (802s Michichi Creek) | 2022-08-17 11:00 | 2022-08-17 15:00 | N | N | PRC05 707 trip coil testing | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, ENMAX | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary), 5s 752 (5s East Calgary), 5s 852 (5s East Calgary), 5s 70 (5s East Calgary), 2MD138-2.1CAP (SS-2), MD109 (SS-2), MD110 (SS-2) | 2022-08-17 12:00 | 2022-08-17 14:00 | N | N | substation washing | Shunts, Circuit Breaker, Switch | Summer Substation Washing 5s7E |  | Pre-Condition
ENMAX | 2.4TR (SS-2), MD107 (SS-2), MD108 (SS-2), 2MD138-2.4TR (SS-2) | 2022-08-17 14:00 | 2022-08-17 16:00 | N | N | substation washing | Transformer, Switch |  |  | For Information Only
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant Plant) | 2022-08-17 23:00 | 2022-08-18 03:00 | N | Y | maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 62s T2 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant Plant) | 2022-08-18 03:00 | 2022-08-18 07:00 | N | Y | maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 310p 2152 (310p Sundance) | 2022-08-18 07:30 | 2022-08-18 17:30 | N | Y | grading capacitor replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 2.1TR (SS-2) | 2022-08-18 08:00 | 2022-08-18 10:00 | N | N | summer substation washing | Transformer |  |  | For Information Only
ALTALINK | 74s C1 (74s Janet), 74s C2 (74s Janet), 74s 53 (74s Janet), 74s 55 (74s Janet), 74s 54 (74s Janet), 74s 56 (74s Janet) | 2022-08-18 08:00 | 2022-08-18 17:00 | N | N | breaker maintenance work and repair hot switch 74s 53 | Shunts, Switch, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 205s Castle Rock Ridge | 2022-08-18 08:45 | 2022-08-18 15:00 | N | Y | perform drilling and repairs on turbine foundations | Station | Enercon is requesting two Castle Rock Ridge circuit outages next week, to perform drilling and repairs on turbine foundations |  | Restricts Generation
ENMAX | 2.2TR (SS-2) | 2022-08-18 10:00 | 2022-08-18 12:00 | N | N | summer substation washing | Transformer |  |  | For Information Only, Pre-Condition
ATCO | 802s 705C (802s Michichi Creek), 802s 705 (802s Michichi Creek) | 2022-08-18 11:00 | 2022-08-18 13:00 | N | N | PRC05, 705 trip coil testing | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.3TR (SS-2) | 2022-08-18 12:00 | 2022-08-18 14:00 | N | N | summer substation washing | Transformer |  |  | For Information Only, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 706 (802s Michichi Creek) | 2022-08-18 13:01 | 2022-08-18 15:00 | N | N | PRC05, 706 Trip coil testing | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 275s 949 (275s Jenner) | 2022-08-18 17:30 | 2022-10-26 07:30 | N | Y | complete construction and commissioning of new Joss bay addition | Circuit Breaker |  |  | For Information Only
ENMAX | 162.1TR (SS-162), 240kV North Bus (SS-162), 138kV North Bus (SS-162), 162B138-RB80 (SS-162), SW81 (SS-162), 162B138-RB86 (SS-162), SW96 (SS-162), 162B138-RB94 (SS-162), SW110 (SS-162), 162MD138-162.1TR (SS-162), 162MD240-162.1TR (SS-162), 162B240-RB131 (SS-162), 162B240-RB134 (SS-162), SW131 (SS-162), SW141 (SS-162) | 2022-08-19 08:00 | 2022-08-19 17:17 | N | Y | power factor test 162PT240-Z43, summer substation washing | Transformer, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L128 (802s Michichi Creek - 963s Coyote Lake), 802s 704 (802s Michichi Creek), 802s 7L128D1 (802s Michichi Creek), 802s TLO-O (802s Michichi Creek), 963s TLO-O (963s Coyote Lake), 963s 7L128D2 (963s Coyote Lake), 963s 701B (963s Coyote Lake), 963s 701 (963s Coyote Lake), 963s 701A (963s Coyote Lake) | 2022-08-19 13:00 | 2022-09-09 17:00 | N | N | BER hand hills project | Line, Circuit Breaker, Switch | BER Hand Hills Project Install new in-line switches 7L128D3 and 7L128D4, connect 7LA128 T-tap, replace OHSW with OPGW, fiber splicing, P & C circuit cutovers Complete commissioning of the RAS 3-terminal POTT, 52b/704 & line MOD 89b/7L128D1 status and send 7L128 LTO to 21B/7L128 at 963S Coyote LK, 52b/701 & line MOD 89b/7L128D2 status and received 7L128 LTO from 802S Michichi Creek, end-to-end testing |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 955L (59s Peigan - 103s Goose Lake) | 2022-08-20 08:15 | 2022-08-20 14:45 | N | Y | maintenace; str 91 | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 771L (SS-47 - SS-162). 162sub 138KV Bus. SS-47, 162B138-RB82 (SS-162) | 2022-08-21 08:00 | 2022-08-21 18:00 | N | N | summer substation washing | Terminal Equipment, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 162.81L (391s Balzac - SS-162), 162MD138-162.81 (SS-162), SW82 (SS-162), SW83 (SS-162), 162B138-RB80 (SS-162), 162B138-RB81 (SS-162), 391s 28 (391s Balzac) | 2022-08-21 08:00 | 2022-08-21 18:00 | N | Y | summer substation washing | Line, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 74s 552 (74s Janet), 74s 252 (74s Janet), 74s 2N (74s Janet), 74s 5N (74s Janet), 74s 101 (74s Janet) | 2022-08-21 09:00 | 2022-08-31 18:00 | N | Y | replace 74s2N and 74s5N 240kV disconnect switches and new breaker control protections on 252 & 552 | Line, Circuit Breaker, Switch |  |  | 240 kV, Affects Cranking Path
EPCOR | 72DS26 (665s Dome - Strathcona), S721 (Strathcona), 665s D721 (665s Dome), SDS3 (Strathcona), 665s DDS17 (665s Dome) | 2022-08-22 07:00 | 2022-08-28 17:00 | N | N | P&C cutovers for breaker fail and transformer protection upgrade | Line, Circuit Breaker, Switch |  | Strathcona: P&C Cutovers for Breaker Fail and TX Prot. Upgrade | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | T2 (Meadowlark), M722 (Meadowlark), M723 (Meadowlark) | 2022-08-22 07:00 | 2022-08-23 17:00 | N | N | TX2/CVT/Arrestor Doble | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s T4 (987s Clover Bar) | 2022-08-22 07:00 | 2022-08-25 17:00 | N | Y | P&C cutovers for cloverbar DFR, UFLS, RTU upgrade projects | Transformer | Cloverbar TX4: P&C Cutovers for Cloverbar DFR, UFLS, RTU Upgrade Projects |  | 240 kV, Firm Load Loss, Pre-Condition
ALTALINK | 723s 240kV Bus 1 (723s Christina Lake), 723s T1 (723s Christina Lake), 723s 152 (723s Christina Lake) | 2022-08-22 07:30 | 2022-08-24 10:00 | N | Y | maintenance and testing | Bus, Transformer, Circuit Breaker | T1: fix leaks, investigate T/C-MT temperature differential, troubleshoot IDD fail. maintain, doble and fixing 723s3. |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s 452 (63s Red Deer), 1083L (63s Red Deer - 288s Wolf Creek) | 2022-08-22 08:00 | 2022-08-22 11:30 | N | Y | trip test | Circuit Breaker, Line | Trip test from 552 C60 to 452 breaker.Trip test from 452 protections to 552 C60 & Control module. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
CMH | MHS-3 C-31 (MH69S-3) | 2022-08-22 08:00 | 2022-08-23 09:35 | N | N | 69 kV capacitor banks repair and testing | Shunts |  |  | Pre-Condition
ENMAX | 32.1TR (SS-32) | 2022-08-22 08:00 | 2022-08-25 16:00 | N | N | transformer secondary cables work | Transformer | transformer secondary cables are faulted, separate GOI help on 32.11 cell |  | For Information Only
ALTALINK | 244s T1 (244s Bowmanton), 244s 138kV Bus 1 (244s Bowmanton), 244s 240kV Bus 1 (244s Bowmanton), 244s 3752 (244s Bowmanton), 244s 2289 (244s Bowmanton), 244s 2189 (244s Bowmanton), 244s 2552 (244s Bowmanton), 244s 2152 (244s Bowmanton), 244s 47 (244s Bowmanton), 244s 36 (244s Bowmanton), 244s 1 (244s Bowmanton), 244s 9 (244s Bowmanton), 244s 152 (244s Bowmanton), 244s 452 (244s Bowmanton) | 2022-08-22 09:00 | 2022-08-25 16:00 | N | N | new 138kV bus 1 B Protection installation | Transformer, Bus, Circuit Breaker, Switch | New 138kV Bus 1 B Protection being installed. Will need to cutover CT ccts and trip test breakers on 138kV Bus 1. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 759s 601T (759s Castor), 759S 501VR | 2022-08-22 09:30 | 2022-09-02 17:30 | N | N | replace 501VR and upgrade protection circuits | Transformer, Terminal Equipment |  | - Replace 501VR - Upgrade 601T protection circuits | For Information Only
ALTALINK, EPCOR | 1045L (310p Sundance - 1045AL Tap), 1045L (EP 805s Jasper - 1045AL Tap), 1045AL (320p Keephills - 1045L Tap) | 2022-08-22 09:30 | 2022-08-26 17:00 | N | Y | doble and maintenance | Line | Jasper 1045L Zone Doble and J2407 Doble and Maintenance |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 7L53 (706s Irish Creek - 7LA53 Tap), 706s 702 (706s Irish Creek) | 2022-08-22 09:30 | 2022-08-24 21:14 | N | N | maintenance and PRC005 work | Line, Circuit Breaker | 702 Maintenance and PRC005 work, 7L53 Open ended at 706S |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, DAISHOWA | 7L04 (ATC 793s West Peace River - 839s Daishowa), 839s 701T (839s Daishowa Plant), ATC 793s 704 (ATC 793s West Peace River), 839s 701 (839s Daishowa), 147s 1 (147s Daishowa Plant), 147s 107 (147s Daishowa Plant), 147s 108 (147s Daishowa Plant), 147s 109 (147s Daishowa Plant), 147s 12 (147s Daishowa Plant), 147s 15 (147s Daishowa Plant), 147s 19 (147s Daishowa Plant), 147s 9 (147s Daishowa Plant), 147s PS-SITE (147s Daishowa Plant), 147s PS-SS1 (147s Daishowa Plant), 147s PS-SS2 (147s Daishowa Plant) | 2022-08-22 10:00 | 2022-08-26 16:00 | N | Y | 839s 701T, 839s 701 and 793s 704 breaker maintenance | Line, Transformer, Circuit Breaker | 839S 701T and 701 bkr maintenance, 793S 704 bkr maintenance |  | Restricts Generation
ATCO | 885s 902 (885s McMillan) | 2022-08-22 10:00 | 2022-08-25 16:00 | N | Y | 902 maintenance | Circuit Breaker |  | 902 Maintenance | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 885s 902T (885s McMillan), 885s 501R (885s McMillan) | 2022-08-22 10:00 | 2022-08-26 16:00 | N | Y | 902T PRC005 and 501 maintenance | Transformer, Shunts |  | 902T PRC005, 501 Maintenance. | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2022-08-22 11:00 | 2022-08-23 17:00 | N | N | forced outage | Line | 973L (39s Bickerdike - 310p Sundance) |  | 240 kV, Pre-Condition
ATCO | 6L03 (757s Battle River - 6L17 tap) | 2022-08-22 11:00 | 2022-08-25 16:00 | N | N | cross arm and insulator replacement | Line |  | We require a GOI on 6L03 for crossarm and insulator replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 869L (163s Amoco Empress - 204s Sandy Point), 204s T1 (204s Sandypoint), 163s 869W (163s Amoco Empress), 163s 50 (163s Amoco Empress), 204s 869E (204s Sandy Point) | 2022-08-22 11:00 | 2022-09-16 18:00 | N | N | XYZ bushing replacement & IDD, maintenance | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 163s C2 (163s Amoco Empress), 163s 67 (163s Amoco Empress) | 2022-08-22 12:00 | 2022-08-25 18:00 | N | N | replacing cap bank protections | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 191s 792X (191s N.W. Cardiff), 191s 23 (191s N.W. Cardiff) | 2022-08-22 12:00 | 2022-08-26 18:00 | N | N | component replacements 792L structure range 74-185 | Line, Circuit Breaker, Switch |  | component Replacement's 792L Str's Range 74-185 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 681s T1 (681s Bannerman) | 2022-08-22 12:00 | 2022-08-25 17:30 | N | N | maintenance and repair | Transformer |  | T1 maintenance, fix leaks, change Qualitrol, doble. Customer NGR maintenance. | 240 kV, For Information Only
ALTALINK | 901L (63s Red Deer - 901AL tap), 63s 652 (63s Red Deer) | 2022-08-22 13:00 | 2022-08-22 16:30 | N | Y | breaker trip test | Line, Circuit Breaker | Trip test from new 552 C60 to 652 breaker.Trip test from 652 protections to new 552 C60 & Control module. |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 56L (20s Ghost - 245s Seebe), 245s 56E (245s Seebe), 20s 56 (20s Ghost), 245s 5 (245s Seebe), 20s 57 (20s Ghost) | 2022-08-23 07:00 | 2022-08-30 18:00 | N | N | complete cutovers/end to end testing of new line protection and breaker fail | Line, Circuit Breaker, Switch | complete cutovers/end to end testing of new line protection and breaker fail.CT contribution to B bus differntial |  | Pre-Condition
ALTALINK | AML 511s 240kV East Bus (511s Crossings), 102s 240kV East Bus (102s Langdon), 102s 552 (102s Langdon), 102s 5852 (102s Langdon), 102s 6652 (102s Langdon), 102s 6952 (102s Langdon), 102s 7552 (102s Langdon), 102s 90 (102s Langdon), 102s 101 (102s Langdon), 102s 109 (102s Langdon), 102s 117 (102s Langdon), 102s 133 (102s Langdon), AML 511s 5052 (AML 511s Crossings), AML 511s 5352 (AML 511s Crossings), AML 511s 79 (AML 511s Crossings), AML 511s 86 (AML 511s Crossings) | 2022-08-23 07:00 | 2022-08-23 18:00 | N | Y | 130 VDC mod for motor circuit on switches 511s79, 511s86 | Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 6L11D1 (739s Edith Lake) | 2022-08-23 09:00 | 2022-08-23 16:00 | N | N | test and operate MOD, test new SCADA and local controls | Line, Switch | test and operate MOD, test new SCADA and local controls |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2022-08-23 09:00 | 2022-08-23 14:00 | N | N | outage for a high load escort passing under 7L12-740 crossing | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek), 396s 185 (396s Pincher Creek), 379s 185N (379s Shell Canada Waterton) | 2022-08-23 09:00 | 2022-08-26 18:00 | N | N | component replacements, structure changes and stringing 185L ( str range 1-117) | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L73 (729s Otauwau - 745s Slave Lake), 729s 601 (729s Otauwau), 745s 601 (745s Slave Lake), 745s 601T (745s Slave Lake), 745s 601A (745s Slave Lake), 745s 6L73D1 (745s Slave Lake) | 2022-08-23 10:00 | 2022-08-26 16:00 | N | N | breaker maintenance | Line, Circuit Breaker, Transformer, Switch | breaker maintenance, concurrent with 601 at 745S as load will need to be transferred off of 745S |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 794s 701TCS (794s Valleyview), 794s 701T (794s Valleyview) | 2022-08-23 10:00 | 2022-08-26 16:00 | N | N | circuit switcher, transformer, and regulator maintenance | Switch, Transformer |  | Circuit switcher, transformer, and regulator maintenance, Jumper J1 will be created by removing bus side risers from 701TCS using Hot Line Crew under HOP and closed after maintenance | For Information Only
ALTALINK | 250p T2 (250p Bighorn Plant), 250P 2 (250P Bighorn Plant) | 2022-08-24 07:00 | 2022-08-25 07:00 | N | Y | maintenance | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 250p T1 (250p Bighorn Plant), 250P 1 (250P Bighorn Plant) | 2022-08-24 07:00 | 2022-08-25 07:00 | N | Y | maintenance | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | AML 511s 240kV West Bus (511s Crossings), 102s 240kV West Bus (102s Langdon), AML 511s 4852 (AML 511s Crossings), AML 511s 5252 (AML 511s Crossings), 102s 252 (102s Langdon), 102s 5652 (102s Langdon), 102s 6452 (102s Langdon), 102s 6752 (102s Langdon), 102s 7352 (102s Langdon), 102s 87 (102s Langdon), 102s 94 (102s Langdon), 102s 102 (102s Langdon), 102s 110 (102s Langdon), 102s 126 (102s Langdon), AML 511s 73 (AML 511s Crossings), AML 511s 80 (AML 511s Crossings) | 2022-08-24 07:00 | 2022-08-24 18:00 | N | Y | 130 VDC mod for motor circuit on switches 511s73, 511s80. | Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 184s T3 (184s Petro-Canada Edmonton) | 2022-08-24 07:30 | 2022-08-24 17:30 | N | N | urgent - doble test T3 H1 bushing and replace if necessary | Transformer |  |  | For Information Only
CYLP | CYP2 Cypress 2 | 2022-08-24 08:00 | 2023-01-13 16:00 | N | N | P2413 EDF Cypress 2 Wind. 46 MW. ISD Oct 17, 2022 | Unit
ENMAX | 5.10TR (SS-5) | 2022-08-24 08:00 | 2022-08-24 16:00 | N | N | fit testing spare breaker | Transformer |  |  | For Information Only
ALTALINK, AESO-SC | 58s T2 (58s Edson), 58s TR1 (58s Edson), 58s 52L1 (58s Edson), 58s 52G1 (58s Edson), 58s 52G2 (58s Edson), 58s PLNT-Load-PSDO (58s Edson), 58s SS-Load-PSDO (58s Edson), 58s T2-Load-PSDO (58s Edson), 58s ToPLNT-PSDO (58s Edson), 58s 3 (58s Edson) | 2022-08-24 08:00 | 2022-08-26 17:00 | N | Y | complete connections of new 25 kV feeder cables | Transformer, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation
CRLP | CYP1 Cypress 1 | 2022-08-24 08:00 | 2023-04-24 16:00 | N | N | P2122 Cypress Wind Project Connection. 196 MW. ISD Nov 08, 2022 | Unit
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive) | 2022-08-24 09:00 | 2022-08-26 18:00 | N | N | test and operate MOD, test new SCADA and local controls | Line |  | test and operate MOD, test new SCADA and local controls | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | AML 511s ACF21 (AML 511s Crossings), AML 511s ACF22 (AML 511s Crossings) | 2022-08-25 07:30 | 2022-08-26 17:30 | N | Y | 130 VDC mod for motor circuit on switches | Shunts | 130 VDC mod for motor circuit on switches 511s77, 511s78, 511s155, 511s156, 511s2157, 511s2257. |  | For Information Only
ALTALINK | 671L (39s Bickerdike - 58s Edson) | 2022-08-25 08:00 | 2022-08-25 14:00 | N | N | completion of high-load move - carrier PO- ACHE-1-4 | Line | Description/Scope: GOI required for completion of high-load move - Carrier PO- ACHE-1-4 |  | For Information Only, Pre-Condition
ALTALINK | 610L (83s Taber - 336s Fincastle), 83s 610 (83s Taber), 336s 610 (336s Fincastle), 83s 1 (83s Taber), 336s 25 (336s Fincastle) | 2022-08-26 07:15 | 2022-08-26 17:45 | N | Y | replace structure | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 983L (244s Bowmanton - 251s Whitla), 244s 552 (244s Bowmanton), 244s 652 (244s Bowmanton), 251s 552 (251s Whitla), 251s 652 (251s Whitla), 244s 13 (244s Bowmanton), 244s 15 (244s Bowmanton), 251s 13 (251s Whitla), 251s 15 (251s Whitla), 251s 983 (251s Whitla), 244s 983 (244s Bowmanton) | 2022-08-26 08:00 | 2022-09-02 18:00 | N | Y | reconfiguration for substation energization | Line, Circuit Breaker, Switch | Re-configuring 983L117 and closing 983AL Open Point 'A' to connect 983AL to 983L for the energization of the new I- 1019s Woolchester Substation |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy) | 2022-08-27 06:30 | 2022-08-27 17:00 | N | Y | emergency - top up BDS20 low SF6 | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 511s T30 (AML 511s Crossings), AML 511s ACF11 (AML 511s Crossings), AML 511s ACF12 (AML 511s Crossings), AML 511s ACF13 (AML 511s Crossings), AML 511s 5352 (AML 511s Crossings), AML 511s 5252 (AML 511s Crossings) | 2022-08-27 07:30 | 2022-08-29 17:30 | N | Y | 130 VDC mod for motor circuit on switches 511s152, 511s153, 511s154, 511s148, 511s1257, 511s1357, 511s1457, 511s180, 511s150, 511s151, 511s1157, 511s81, 511s82. | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 410s T1 (410s Josephburg) | 2022-08-27 10:00 | 2022-09-01 18:00 | N | Y | 25kV neutral & 138kV bushing replacement; repair leaks, replace hydran and replace old style LA standoffs | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 525s T1 (525s Carseland) | 2022-08-28 07:00 | 2022-08-28 09:30 | N | N | create open point "A" (Nutrien U/G cables) | Transformer |  |  | For Information Only
FORTIS | Tilley DG PV | 2022-08-28 08:00 | 2022-09-11 16:00 | N | N | P1837 Fortis Tilley DG PV. 22 MW. ISD Aug 28, 2022 | Unit
TRANSCANADA, ALTALINK | 782L (269s Wyndham - 525s Carseland), 525s 49 (525s Carseland) | 2022-08-28 08:00 | 2022-09-05 12:00 | N | Y | maintenance | Line, Switch |  |  | Restricts Generation
ALTALINK | 914L (63s Red Deer - 87s Gaetz) | 2022-08-28 08:15 | 2022-08-28 17:45 | N | Y | fire mitigation maintenance (Str448) | Line |  |  | 240 kV, Affects Cranking Path
ALTALINK | 525s T1 (525s Carseland) | 2022-08-28 09:31 | 2022-09-04 08:00 | N | N | drain and remove T1, install new piling and grillage, set new T1 dress and oil fill, T1 NGR install, 525s8 upgrade to include MOD, demo of VR1 | Transformer |  |  | For Information Only
ALTALINK | 58s T2 (58s Edson) | 2022-08-28 12:30 | 2022-09-01 17:30 | N | N | replace 25KV and 138KV bushings on T2, install 25kV LAs and T2 maintenance and doble | Transformer |  |  | For Information Only
EPCOR | EP 803s T3 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s LAB3 (EP 803s Lambton) | 2022-08-29 07:00 | 2022-09-02 17:00 | N | Y | TX3 zone doble, and disconnect maintenance | Transformer, Circuit Breaker, Switch |  | Lambton TX3 Zone Doble and LAB3/LDS10/LDS11 Disconnect Maintenance | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), AML 511s 76 (AML 511s Crossings), AML 511s 74 (AML 511s Crossings), AML 511s 1489 (AML 511s Crossings), AML 511s 4952 (AML 511s Crossings), AML 511s 4852 (AML 511s Crossings), 510s 43 (510s Sunnybrook), 510s 41 (510s Sunnybrook), 510s 4289 (510s Sunnybrook), 510s 2652 (510s Sunnybrook), 510s 2752 (510s Sunnybrook) | 2022-08-29 07:00 | 2022-09-09 17:00 | N | Y | WATL annual link outage, DC Yard maintenance, valve hall grading electrode inspections, VCS work, TDC troubleshooting and capital work at 511s; negative fusing install on motor mechs. | Line, Switch, Circuit Breaker |  |  | 500 kV, For Information Only, Pre-Condition
ALTALINK | 850L (525s Carseland - 678s Okotoks), 525s 850N (525s Carseland), 678s 850 (678s Okotoks), 525s 1 (525s Carseland), 678s 49 (678s Okotoks) | 2022-08-29 07:00 | 2022-08-30 16:30 | N | Y | strain glass replacement on 850L, CT cable replacement on 525s850N | Line, Circuit Breaker, Switch |  |  | Over/Under Voltage, Overload, Pre-Condition
EPCOR | 72RG1 (Garneau - Rossdale), G724 (Garneau), G725 (Garneau), RG7210 (Rossdale) | 2022-08-29 07:00 | 2022-09-09 17:00 | N | N | termination rebuild, P&C cutovers and op-checks | Line, Circuit Breaker |  | Rossdale Side: UGT Termination Rebuild. Rossdale/Garneau RG1 Line Protection Upgrade: P&C Cutovers and Op-Checks | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s T1 (74s Janet), 74s 16 (74s Janet) | 2022-08-29 07:00 | 2022-08-29 11:00 | N | Y | trip test 74s16 from new 552 breaker fail relay | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 951L (132s Ware Junction - 275s Jenner), 132s 951 (132s Ware Junction), 132s 37 (132s Ware Junction), 132s 40 (132s Ware Junction), 275s 1752 (275s Jenner), 275s 1852 (275s Jenner), 275s 951 (275s Jenner) | 2022-08-29 07:15 | 2022-08-30 12:00 | N | Y | test line air-break and circuit breaker status to new Anti-islanding protections | Line, Switch, Circuit Breaker | 951L outage required to integrate, commission and function test line air-break and circuit breaker status to new Anti-islanding protections at 275s Jenner and 132s Ware Junction. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 12.1TR (SS-12) | 2022-08-29 08:00 | 2022-08-29 16:00 | N | N | connect main tank PRD to protection system | Transformer |  |  | For Information Only
ALTALINK | 255s T2 (255s Vulcan) | 2022-08-29 08:00 | 2022-09-01 16:00 | N | N | T2 A and B protection settings changes and commissioning | Transformer | T2 A and B protection settings changes and commissioning. DER element trip test. Breaker Fail function testing will be completed from the 255s16X protection relay to 255s652 breaker. |  | For Information Only
ATCO | 813s 713 (813s Little Smoky) | 2022-08-29 08:00 | 2022-09-11 12:00 | N | N | cutover/commissioning 713 CT/P&C circuits to 901T protection | Circuit Breaker |  | Cutover 713 CT/P&C circuits to 901T Protection Commission 713 CT/P&C circuits to 901T protection | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 813s 711 (813s Little Smoky) | 2022-08-29 08:00 | 2022-09-11 12:00 | N | N | cutover and commission of 711 CT/P&C circuits to 901T protection | Circuit Breaker |  | Cutover 711 CT/P&C circuits to 901T Protection Commission 711 CT/P&C circuits to 901T protection | Contingency Requires Mitigation, Pre-Condition
ATCO | 813s 902T (813s Little Smoky), 813s 904 (813s Little Smoky), 813s 908 (813s Little Smoky) | 2022-08-29 08:00 | 2022-09-11 17:00 | N | Y | decommission panels 1K, 2K, complete wiring of new 9T2 panel, 904, 908, 902T CT/PT/P&C wiring, replace 500PT disconnect assembly, demo existing wiring/cabling | Transformer, Circuit Breaker |  | Aug. 30, 2022 to Sept. 11, 2022 - Isolation points will be 904B, 908B and 702TD Decommission Panels 1K, 2K. Complete wiring of NEW 9T2 Panel 904, 908, 902T CT/PT/P&C wiring Replace 500PT disconnect assembly Demo existing wiring/cabling Commissioning and relay testing | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
RAZR | SRL1 Swan Hills Geothermal | 2022-08-29 08:00 | 2023-08-30 16:00 | N | N |  | Unit
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge) | 2022-08-29 08:00 | 2022-09-04 17:00 | N | Y | line mitigation, cross arm replacement | Line |  | Line mitigation, Cross arm replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 332s T1 (332s Ellis) | 2022-08-29 08:30 | 2022-09-01 16:30 | N | N | fix leaks, maintenance, doble | Transformer |  |  | For Information Only
ATCO | 757s 706 (757s Battle River) | 2022-08-29 09:30 | 2022-08-30 17:30 | N | N | breaker HPF partial testing | Circuit Breaker |  | BREAKER MIN OIL HPF PARTIAL TESTING 706 | For Information Only
ATCO | 2014s 701T (2014s Halfway), 2014s 701 (2014s Halfway) | 2022-08-29 09:30 | 2022-08-31 17:00 | N | N | 701T maintenance | Transformer, Circuit Breaker |  | 701T Maintenance | For Information Only
ATCO | 751s 704C (751s Hill) | 2022-08-29 09:30 | 2022-09-01 17:30 | N | N | switch replacements | Shunts |  | 704C RTXP switch replacements | Pre-Condition
ALTALINK | 170L (632s Russell - 799s Coleman) | 2022-08-29 10:00 | 2022-09-21 13:10 | N | Y | urgent fire mitigation (str 50-55.) | Line | Weboms Record # 12308295 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 809s 905 (809s Louise Creek) | 2022-08-29 10:00 | 2022-09-02 14:00 | N | Y | breaker maintenance | Circuit Breaker |  | breaker maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 772s 504 (772s Youngstown), 772s 504C (772s Youngstown) | 2022-08-29 10:30 | 2022-12-07 17:30 | N | N | capacitor bank replacement | Circuit Breaker, Shunts |  | 504C Capacitor Bank Replacement | Pre-Condition
ATCO | 6L03 (757s Battle River - 6L17 Tap) | 2022-08-29 11:00 | 2022-09-01 16:00 | N | N | cross-arm and insulator replacement. | Line |  | We require a GOI on 6L03 for crossarm and insulator replacement. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 2052 (74s Janet) | 2022-08-29 11:00 | 2022-08-29 13:30 | N | Y | trip test 74s2052 from new 552 breaker fail relay | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 869s 701T (869s Seal Lake), 869s 701 (869s Seal Lake) | 2022-08-29 11:00 | 2022-09-02 16:00 | N | N | transformer and breaker maintenance | Transformer, Circuit Breaker |  | Transformer and Breaker maintenance | For Information Only
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 191s 792X (191s N.W. Cardiff), 191s 23 (191s N.W. Cardiff) | 2022-08-29 12:00 | 2022-09-01 17:15 | N | N | component replacements 792L structure range 74-185 | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 74s 2552 (74s Janet) | 2022-08-29 13:30 | 2022-08-29 16:00 | N | Y | trip test 74s2552 from new 552 breaker fail relay | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
Saskpower | Sask Power R1S line | 2022-08-30 06:00 | 2022-08-30 20:00 | N | Y | maintenance | Line | SaskPower C1S |  | Limits ATC
ALTALINK | 74s 2752 (74s Janet) | 2022-08-30 07:30 | 2022-08-30 10:30 | N | Y | trip test 74s2752 from new 552 breaker fail relay | Circuit Breaker | Trip test 74s2752 from new 552 breaker fail relay |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2022-08-30 08:00 | 2022-09-03 16:00 | N | N | ECI bushing / slip over CT replacement. oil sampling MT, TC | Transformer |  |  | For Information Only
ENMAX | 12.2TR (SS-12) | 2022-08-30 08:00 | 2022-08-30 16:00 | N | N | connect main tank PRD to protection system | Transformer |  |  | For Information Only
ALTALINK | 805L (86s Bigstone - 964s Pigeon Lake) | 2022-08-30 08:00 | 2022-08-30 14:00 | N | N | create open point A on 472s | Line | Create Open Point A on 472s mobile & MR1 by removing the 138kv risers connected to the line side of 964s805E (805L). RSLD 3 to be implemented at the end of the outage. |  | Creates Radial Feeds, Firm Load Loss, For Information Only, Pre-Condition
ENMAX | 5.5TR (SS-5) | 2022-08-30 08:00 | 2022-09-02 16:00 | N | N | power factor test transformer, secondary cable testing, transformer maintenance | Transformer | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas relay testing. Oil Sampling. Check Reversing Switch. 5.5TR, TC Replace PRD Junction Box. 5.5TR Cabinet Heater & Wiring Replacement |  | For Information Only
REDDEER | 217s T1 (217s North Red Deer) | 2022-08-30 08:00 | 2022-08-31 15:00 | N | N | power transformer 14T1 routine maintenance | Transformer |  |  | For Information Only
ALTALINK | 74s 3752 (74s Janet) | 2022-08-30 10:30 | 2022-08-30 13:00 | N | Y | trip test 74s3752 from new 552 breaker fail relay | Circuit Breaker | trip test 74s3752 from new 552 breaker fail relay |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 944L (132s Ware Junction - 275s Jenner), 132s 47 (132s Ware Junction), 132s 51 (132s Ware Junction), 132s 48 (132s Ware Junction), 132s 50 (132s Ware Junction), 132s 944 (132s Ware Junction), 275s 2 (275s Jenner), 275s 3 (275s Jenner), 275s 4 (275s Jenner), 275s 5 (275s Jenner), 275s 944W (275s Jenner) | 2022-08-30 12:00 | 2022-08-31 17:00 | N | Y | integrate, commission, function test line air-break and circuit breaker status to new anti-islanding protections at 275s and 132s | Line, Circuit Breaker, Switch | 944L outage required to integrate, commission and function test line air-break and circuit breaker status to new Anti-islanding protections at 275s Jenner and 132s Ware Junction. |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 929L (74S Janet - 287s Hazelwood), 74s 352 (74s Janet) | 2022-08-30 13:00 | 2022-08-30 15:30 | N | Y | trip test 74s352 from new 552 breaker fail relay | Line, Circuit Breaker | trip test 74s352 from new 552 breaker fail relay |  | 240 kV, Pre-Condition
ENMAX | 11.3TR (SS-11) | 2022-08-31 08:00 | 2022-08-31 16:00 | N | N | moisture in LTC oil level gauge | Transformer |  |  | For Information Only
ALTALINK | 851L (253s Blackie - 525s Carseland), 525s 851X (525s Carseland) | 2022-08-31 08:00 | 2022-09-01 16:30 | N | Y | strain glass replacement on 851L and CT cable replacement on 525s851X | Line, Circuit Breaker | Strain Glass replacement on 851L, CT cable replacement on 525s851X |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 33s 6 (33s Spray) | 2022-08-31 09:00 | 2022-08-31 16:00 | N | Y | maintenance | Switch | TAU Requested Generator brushgear Outage |  | Restricts Generation
ATCO | 959s 706 (959s Lanfine) | 2022-08-31 10:00 | 2022-08-31 12:00 | N | N |  | Circuit Breaker | Test new breaker and switch status inputs for 7L138 line addition |  | Contingency Requires Mitigation
ATCO | 959s 701 (959s Lanfine) | 2022-08-31 12:01 | 2022-08-31 14:00 | N | N | test new breaker and switch status inputs for 7L138 line addition | Circuit Breaker | Test new breaker and switch status inputs for 7L138 line addition |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 739L (14s Devon - 155s Blackmud), 14s 739E (14s Devon), 155s 739 (155s Blackmud) | 2022-09-01 07:00 | 2022-09-01 13:00 | N | N | high-load move between structures 764-765 | Line, Circuit Breaker | GOI required for completion of high-load move between structures 764-765. Carrier po-1801 147-EA |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-09-01 08:00 | 2022-12-31 18:00 | N | N | 30EDD-105/121 | Not In Model | Unmodeled Transmission Facility (Suncor) 30EDD-105/121 Pressure Gauge Replace TPSU Skids |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-09-01 08:00 | 2022-12-31 18:00 | N | N | TPSU skids nitrogen top ups | Not In Model | Unmodeled Transmission Facility (Suncor) TPSU Skids Nitrogen Top Ups |  | For Information Only
ENMAX | 21.2TR (SS-21) | 2022-09-01 08:00 | 2022-09-01 16:00 | N | N | DC ground on 21.2TR conserv, oil level gauge | Transformer | DC Ground on 21.2TR Conserv. Oil Level Gauge |  | For Information Only
ALTALINK | 244s 240kV Bus 2 (244s Bowmanton), 244s 138kV Bus 2 (244s Bowmanton), 244s T2 (244s Bowmanton), 244s 352 (244s Bowmanton), 244s 652 (244s Bowmanton), 244s 2252 (244s Bowmanton), 244s 2652 (244s Bowmanton), 244s 16 (244s Bowmanton), 244s 2389 (244s Bowmanton), 244s 2489 (244s Bowmanton), 244s 8 (244s Bowmanton), 244s 46 (244s Bowmanton), 244s 57 (244s Bowmanton) | 2022-09-01 09:00 | 2022-09-04 16:00 | N | Y | new 138 kV Bus 2 B protection being installed, cutover CT ccts and trip test breakers on 138 kV Bus 2 | Bus, Transformer, Circuit Breaker, Switch | New 138kV Bus 2 B Protection being installed. Will need to cutover CT ccts and trip test breakers on 138kV Bus 2. |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 7L132 (767s Oyen - 959s Lanfine), 959s 702 (959s Lanfine), 959s 703 (959s Lanfine), 959s 702B (959s Lanfine), 959s 703A (959s Lanfine), 959s 7L132D2 (959s Lanfine) | 2022-09-01 10:00 | 2022-09-01 16:00 | N | N | test new breaker and switch status inputs for 7L138 line addition | Line, Circuit Breaker, Switch |  | Test new breaker and switch status inputs for 7L138 line addition | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BluEarth | HHW1 Hand Hills Wind | 2022-09-02 09:00 | 2023-06-16 17:00 | N | N | P2263 BER Hand Hills MPC Wind. 151 MW. ISD September 30, 2022 | Unit
ALTALINK | 525s Carseland | 2022-09-03 09:30 | 2022-09-03 12:00 | N | N | 25 kV breaker 265X - commission new T1, VR3 trips and close blocks | Station | 525s265X breaker outage required to tie in and commission new T1 & VR3 trips and close blocks |  | For Information Only
ALTALINK | 525s Carseland | 2022-09-03 13:00 | 2022-09-03 15:30 | N | N | 25 kV breaker 261N - commission new T1, VR3 trips and close blocks | Station | 525s261N outage required to tie in and commission new T1 & VR3 trips and close blocks |  | For Information Only
ALTALINK, TRANSCANADA | 851L (253s Blackie - 525s Carseland), 782L (269s Wyndham - 525s Carseland), 525s T1 (525s Carseland) | 2022-09-04 07:00 | 2022-09-05 14:00 | N | Y | breaker maintenance, T1 protection trips and close blocks to 552 breaker, 525s7 commissioning, 782L strain glass replacement | Line, Transformer | Expanded GOI on T1 scope to include 525s48 breaker maintenance (AltaLink), T1 protection trips and close blocks to 552 breaker, 525s7 commissioning, 782L strain glass replacement |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.82L (SS-1 - SS-5), 5.1TR (SS-5), 5.6TR (SS-5), 5.8TR (SS-5), 5B138-1.82 (SS-5), 5B138-5BT12 (SS-5), 5B138-5BT7 (SS-5) | 2022-09-04 08:00 | 2022-09-04 13:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.83L (SS-5 - 2.83L Tap), 5.9TR (SS-5), 5.10TR (SS-5), 5B138-2.83 (SS-5), 5B138-5BT12 (SS-5) | 2022-09-04 13:00 | 2022-09-04 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker | Fall Substation Washing. Check Reversing Switch 5.10TR, 5.9TR |  | Pre-Condition
ALTALINK | 83s C1 (83s Taber) | 2022-09-04 15:30 | 2022-11-01 18:00 | N | N | forced outage | Shunts |  |  | Pre-Condition
ATCO | 848s 401R (848s Ruth Lake) | 2022-09-04 16:50 | 2024-09-30 18:00 | N | N | forced outage | Shunts | Atco has informed the SC that 401R @ 848s Ruth Lake will be unavailable until further notice. The breaker needs to be replaced and the earliest estimate is January 2023. Feb 2023 update: Breaker will not be replaced until the 848S Ruth Lake Substation Rebuild end of Q3 2024 |  | Pre-Condition
EPCOR | S722 (Strathcona) | 2022-09-05 07:00 | 2022-09-10 17:00 | N | N | P&C cutovers for breaker fail and TX protection upgrade | Circuit Breaker | Strathcona: P&C Cutovers for Breaker Fail and TX Prot. Upgrade |  | For Information Only
ALTALINK | 244s 138kV Bus 3 (244s Bowmanton), 244s 138kV Bus 4 (244s Bowmanton), 244s 2952 (244s Bowmanton), 244s 3752 (244s Bowmanton) | 2022-09-05 09:00 | 2022-09-08 15:00 | N | N | new 138 kV bus 3/4 B protection being installed, cutover CT circuits and trip test breakers on 138 kV Bus 3/4 | Bus, Circuit Breaker | New 138kV Bus 3/4 B Protection being installed. Will need to cutover CT circuits and trip test breakers on 138kV Bus 3/4. |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker), PM2404 (Poundmaker), PM2403 (Poundmaker), PMAB10 (Poundmaker) | 2022-09-06 07:00 | 2022-09-10 17:00 | N | Y | Poundmaker 930L zone arrestor/CVT doble, PMDS6/PMDS7/PMDS10 disconnect maintenance | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 959s 144kV Bus 700BS2 (959s Lanfine), 959s 703 (959s Lanfine), 959s 706 (959s Lanfine), 959s 707 (959s Lanfine), 959s 7L150D1 (959s Lanfine), 959S 723C (959S Lanfine) | 2022-09-06 07:00 | 2022-11-14 17:00 | N | N | structural steel work and breaker/CT/PT installation and line tie-in | Bus, Circuit Breaker, Switch, Shunts | Pattern Lanfine North WAGF Project Salvage Structural steel & Install new Structural steel Breaker/CT/PT Installation Line Tie-in @ 601S Buffalo Bird Substation |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 418L (20s Ghost - 189L Tap), 20s 452 (20s Ghost) | 2022-09-06 07:00 | 2022-09-13 18:00 | N | N | complete cutovers and end to end testing of new protection | Line, Circuit Breaker | Complete cutovers/End to end testing of new line protection and Breaker fail.CT contribution to B bus Diff. |  | Pre-Condition, Affects Cranking Path
ALTALINK | 113L (20s Ghost - 33s Spray) | 2022-09-06 07:15 | 2022-09-25 17:45 | N | N | rebuild a section of 113L from structure 1 to 96 | Line |  |  | Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 63s 2652 (63s Red Deer) | 2022-09-06 08:00 | 2022-09-16 13:00 | N | Y | replacing 552 breaker control and breaker fail relays with new C60 module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162.3TR (SS-162) | 2022-09-06 08:00 | 2022-09-09 16:00 | N | N | maintenance | Transformer | Tapchanger maintenance. 162.3TR LTC Online filter re-plumb. Oil Sampling MT, TC. Filmax LTC Oil Filtration Maintenance. Check Reversing Switch. Calisto Maintenance |  | For Information Only
ENMAX | 24.82L (SS-24 - SS-65), 24.2TR (SS-24), 24B138-24.82 (SS-24) | 2022-09-06 08:00 | 2022-09-06 16:00 | N | N | HV breaker maintenance 24B138-24.82 | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27), 27MD69-27.2TR (SS-27) | 2022-09-06 08:00 | 2022-09-06 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch | fall substation washing. SW 65, SW 66, SW 67 -retrieve Nameplate Info. 13.60L OOS |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-09-06 08:00 | 2022-12-31 18:00 | N | N | 30EDD-121 | Not In Model | Unmodeled Transmission Facility (Suncor) 30EDD-121 Cable Replacement TPSU Skids |  | For Information Only
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek) | 2022-09-06 08:30 | 2022-09-06 17:30 | N | Y | required for BC Hydro 60L289 outage | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 332s T2 (332s Ellis) | 2022-09-06 08:30 | 2022-09-09 16:30 | N | N | maintenance, doble, replace some signs. | Transformer |  |  | For Information Only
NOVAC, NOVACORP | 330L1 (535s Joffre - 330s Nova Joffre), 330L3 (196s Nova Chemicals - 330L1 Tap), 330s BR-52 (330s Nova Joffre), 196s R3-BR-A (196s Nova Chemicals) | 2022-09-06 09:00 | 2022-09-10 17:00 | N | Y | customer requested maintenance | Line, Circuit Breaker |  |  | Restricts Generation, Affects Cranking Path
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2022-09-06 09:30 | 2022-09-08 18:00 | N | N | install bird diverters at various locations between structures 554 to 603 | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L56 (763s Hanna - 802s Michichi Creek), 802s 701T (802s Michichi Creek), 802s 701 (802s Michichi Creek), 802s 606 (802s Michichi Creek) | 2022-09-06 09:30 | 2022-11-13 12:00 | N | N | 802S Michichi substation TCM upgrades and 701T and breaker 606 replacement | Line, Transformer, Circuit Breaker | 802S Michichi substation TCM upgrades 701T and Bkr 606 replacement |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 844s 702T (844s AEC Mill), 844s 702 (844s AEC Mill) | 2022-09-06 09:30 | 2022-09-19 09:30 | N | N | 702T outage required for protection upgrade | Transformer, Circuit Breaker | 702T outage required for protection upgrade |  | For Information Only, Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-09-06 11:30 | 2022-09-07 12:44 | N | Y | crossarm and insulator replacement project on 7L224 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 365s Canadianoxy Astotin Creek, 846L (127s Bruderheim - 365s Canadianoxy Astotin Creek), 365s 846N (365s Canadianoxy Astotin Creek), 365s T1 (365s Canadianoxy Astotin Creek) | 2022-09-06 12:00 | 2022-09-15 16:00 | N | N | substation equipment maintenance | Station, Line, Circuit Breaker, Transformer | 365s3 138kV PT Replacement,365sT1 corrosive sulfur oil mitigation,T1 replace LAs, 365sT1 Leaky Radiators, 365sT1 Additional Leaks, 365s846N Dashpot empty,365s Gate needs adjustments, 365sT1 double.365s1 Outside Phases Underclosed Adjust. Relay Techs to repair the trip circuit associated with breaker 365s6 with the customer. Then perform functional trips to breakers 365s6 and 365s11 from T1 transformer protections inside the GOI. |  | Pre-Condition
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2022-09-06 12:00 | 2022-09-08 18:00 | N | N | 792L350 replace structure | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s 72kV Bus 1 (987s Clover Bar), 987s 72kV Bus 2 (987s Clover Bar), 987s T2 (987s Clover Bar), 72CN10 (987s Clover Bar - Namao), 72CH9 (987s Clover Bar - EP Hardisty), 987s CC13 (987s Clover Bar), 987s CC24 (987s Clover Bar), 987s CN723 (987s Clover Bar), 987s CH722 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s CGB3 (987s Clover Bar), 987s GB1B (987s Clover Bar), 987s C1 (987s Clover Bar) | 2022-09-07 07:00 | 2022-09-10 17:00 | N | Y | arrestor support replacement, bus 1/2 CVT Doble, CDS2 / CDS4 / CDS6 / CDS7 / CDS8 / CDS21 / CGDS3 / GDS1B1 / GDS1B2 / GDS3 disconnect maintenance and CGB3 / GB1B / C72C1 breaker maintenance | Bus, Transformer, Line, Circuit Breaker, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 89s 252 (89s Ellerslie) | 2022-09-07 07:30 | 2022-09-10 10:00 | N | Y | urgent replace failed CTs at 89s252 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 41.2TR (SS-41) | 2022-09-07 08:00 | 2022-09-07 16:00 | N | N | fit testing spare breaker | Transformer |  |  | For Information Only
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2022-09-07 08:00 | 2022-09-07 16:00 | N | N | power factor test 5B138-1.82-CT | Line, Circuit Breaker |  |  | For Information Only
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - SS-21), 21.2TR (SS-21), 60s50 (SS-21), 21.1C (SS-21), 21MD138-21.2TR (SS-21) | 2022-09-07 08:00 | 2022-09-07 18:00 | N | Y | fall substation washing, check reversing switch 21.1TR | Line, Transformer, Circuit Breaker, Shunts, Switch |  |  | Pre-Condition
ENMAX | 65B138-D85 (SS-65) | 2022-09-07 08:00 | 2022-09-07 16:00 | N | N | breaker maintenance | Circuit Breaker | HV breaker maintenance 65B138-D85 |  | Contingency Requires Mitigation, Pre-Condition
BCH | 2L294 (BCH A. A. Lambert - BCH Nelway) | 2022-09-07 09:00 | 2022-09-20 17:00 | N | Y | insturment transformer replacement BC maintenance does not affect the Alberta ATC | Line | 2L294 (Nelway - A.A. Lambert) |  | Limits ATC, Pre-Condition
ATCO | 2014s 702T (2014s Halfway), 2014s 702 (2014s Halfway) | 2022-09-07 09:30 | 2022-09-09 17:00 | N | N | maintenance | Transformer, Circuit Breaker |  | 702T Maintenance | For Information Only
AESO-SC | OATI | 2022-09-07 18:00 | 2022-09-07 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2022-09-08 08:00 | 2022-09-08 16:00 | N | N | power factor test 5B138-1.84-CT | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell), 2075s 905 (2075s Newell), 2075s 906 (2075s Newell), 2075s 905B (2075s Newell), 2075s 906A (2075s Newell) | 2022-09-08 09:00 | 2022-09-08 17:30 | N | Y | - PRC-005 testing - AC yard switch repairs/investigations | Line, Circuit Breaker, Switch | - PRC-005 Testing - AC yard switch repairs/investigations |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 704L (51s Wainwright - 478s Tucuman) | 2022-09-09 07:00 | 2022-09-11 18:00 | N | N | structure change 284/285/290 and replace arms/insulation structure 303 | Line |  | Structure change 284/285/290 and replace arms/insulation structure 303 | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 501CL (983s Cadomin - 501L Tap), 501L (426s Coalspur - 501CL tap), 426s 501W (426s Coalspur) | 2022-09-09 07:30 | 2022-09-09 17:00 | N | N | remove mobile at 983s | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L06 (784s Donnelly - 787s High Prairie) | 2022-09-09 08:00 | 2022-09-09 17:00 | N | N | attach 902s mobile sub to 144 kV | Line |  | 784S Donnelly Rebuild Project Attach 902S mobile Substation to 144kv | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 2.82L (SS-2 - SS-5), 1.84L (SS-1 - SS-5), 5.5TR (SS-5), 5.7TR (SS-5), 5B138-5BT7 (SS-5), 5B138-1.84 (SS-5), 5B138-2.82 (SS-5), 5MD138-5.5TR (SS-5), 5MD138-5.7TR (SS-5) | 2022-09-09 08:00 | 2022-09-09 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
SUNCOR | 635EDD-1000 635PT-1003 (635EDD-1000) | 2022-09-09 08:00 | 2022-09-10 20:00 | N | N | replace the tap changer gearbox and model 11 gas relay | Transformer |  | Replace the tap changer gearbox and model 11 gas relay | For Information Only
ALTALINK | 302s Cardinal River, 501L (302s Cardinal River - 501CL tap) | 2022-09-09 10:00 | 2022-09-09 15:00 | N | N | disconnect 501L from 302s | Station, Line |  | Cut 302s station free Disconnect 501L from 302s create open points inside 302s | For Information Only
ALTALINK | 747L (99s North St. Albert - 711L tap), 99s 747X (99s North St. Albert) | 2022-09-10 06:00 | 2022-09-10 18:00 | N | N | GOI required to install new stub anchor pole with new guys wires on structure 747L63 | Line, Circuit Breaker | GOI is required to install a new stub anchor pole with new guys wires on structure 747L63. Salvage existing anchors and guy wires as new road construction is happening in the area. There currently is underbuilt on this structure, but it will be removed and put underground when we are on site for the work to be completed. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 610L (83s Taber - 336s Fincastle), 336s 610 (336s Fincastle), 83s 610 (83s Taber) | 2022-09-10 06:15 | 2022-09-11 18:45 | N | Y | SmartWire project, install and connect smart wires power flow controller at 336s | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 814s B2407 (814s Bellamy) | 2022-09-10 07:00 | 2022-09-10 17:00 | N | N | troubleshoot faulty hydraulic system | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 27B69-16.61 (SS-27), 16B69-16.61 (SS-16) | 2022-09-10 08:00 | 2022-09-10 18:00 | N | N | fall substation washing, check reversing switch 27.1TRs, repair insulator on Str 45 | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 304s T2 (304s Shell Limestone), 304s 352 (304s Shell Limestone) | 2022-09-10 08:00 | 2022-09-10 18:00 | N | N | installing grounds for maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 784s 701T (784s Donnelly) | 2022-09-10 08:00 | 2022-09-26 17:00 | N | N | 784S Donnelly Rebuild project | Transformer | 784S Donnelly Rebuild Project - Load carried by Mobile substation Cut over and tie in cables to New Building Panel Protection Work Replacement of 500PT1 and 500SST Commissioning Work |  | For Information Only
EPCOR | 987s 72kV Bus 3 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale), 987s CCP7213 (987s Clover Bar), 987s CC13 (987s Clover Bar), K724 (Kennedale) | 2022-09-11 07:00 | 2022-09-12 17:00 | N | Y | 72kV BUS 3 outage, CDS9/CDS14/CDS17/CGDS2/GDS2 disconnect maintenance; CK12 line protection maintenance, DFR/UFLS upgrades | Bus, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31), 31B138-31.84 (SS-31), 31B138-24.81 (SS-31) | 2022-09-11 08:00 | 2022-09-11 12:00 | N | N | fall substation washing | Line, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 635EDD-1000 635PT-1002 (635EDD-1000) | 2022-09-11 08:00 | 2022-09-12 20:00 | N | N | replace the BETA pressure relay on tap changer diverter | Transformer |  |  | For Information Only
ENMAX | 9.80L (SS-9 - SS-31), 31.1C (SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31B138-9.80 (SS-31) | 2022-09-11 12:01 | 2022-09-11 18:00 | N | N | fall substation sashing | Line, Shunts, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 813s 710 (813s Little Smoky) | 2022-09-11 12:01 | 2022-09-29 23:30 | N | N | cutover/commission 710 CT/P&C circuits to 901T protection | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 813s 704 (813s Little Smoky) | 2022-09-11 12:01 | 2022-09-29 23:30 | N | N | cutover/commission 704 CT/P&C circuits to 901T protection | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 881s 702T (881s Sturgeon) | 2022-09-11 14:00 | 2022-09-12 16:00 | N | N | maintenance on 13.8 kV switchgear | Transformer | Heartland Generation requires an Isolation from 881S 702TD to conduct Maintenance on the 13.8Kv switchgear on GT2 702TD is DLO therefore 7L01 is required to be de-energized prior to Opening and Closing the switch Approximately One hour outage to 7L01 at the start and end of outage |  | Pre-Condition
ATCO | 813s 902T (813s Little Smoky) | 2022-09-11 17:01 | 2022-10-02 12:00 | N | Y | decommission panels 1K, 2K, complete wiring of NEW 9T2 panel & 902T CT/PT/P&C wiring | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | Smartwires | 2022-09-11 18:45 | 2022-10-13 07:45 | N | N | P7082 Smartwires powerflow controller on 610L | Terminal Equipment |  |  | For Information Only
EPCOR | EP 803s L2402 (EP 803s Lambton) | 2022-09-12 07:00 | 2022-09-13 17:00 | N | Y | p&c cutovers, multiplier relocation | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 72VN21 (EP 511s Victoria - Namao), N725 (Namao), EP 511s V728 (EP 511s Victoria), EP 511s V729 (EP 511s Victoria) | 2022-09-12 07:00 | 2022-09-19 16:00 | N | N | emergency outage | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 34.2TR (SS-34) | 2022-09-12 07:00 | 2022-09-16 16:00 | N | N | cable trench tray replacement | Transformer |  |  | For Information Only
EPCOR | S723 (Strathcona) | 2022-09-12 07:00 | 2022-09-17 17:00 | N | N | P&C cutovers for breaker fail and TX protection upgrade | Circuit Breaker |  |  | For Information Only
ATCO | 7L06 (784s Donnelly - ATC 793s West Peace River) | 2022-09-12 08:00 | 2022-09-14 17:00 | N | N | 784S Donnelly rebuild project (700PT2 removal) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 3.4TR (SS-3) | 2022-09-12 08:00 | 2022-09-15 16:00 | N | N | tapchanger maintenance (Reinhausen). oil sampling TC | Transformer |  |  | For Information Only
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (ENMAX 36), 16B69-16.63 (SS-16), 36B69-16.63/36.5TR (SS-36) | 2022-09-12 08:00 | 2022-09-16 16:00 | N | N | bushing replacement, oil sampling | Line, Transformer, Circuit Breaker | 36.5TR HOXO Bushing Replacement. Oil Sampling. One hour soak required on return |  | For Information Only, Pre-Condition
ENMAX | 14.1C (SS-14), 14.2C (SS-14) | 2022-09-12 08:00 | 2022-09-15 16:00 | N | N | cap bank maintenance | Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 256s T1 (256s Harmattan) | 2022-09-12 08:00 | 2022-09-15 17:00 | N | Y | repairing leaks on the transformer radiator | Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), 9BB8-9.1TR (SS-9), 9BA8-9.1TR (SS-9) | 2022-09-12 08:00 | 2022-09-12 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker |  |  | For Information Only
REDDEER | 209s T1 (209s Timberlands), 209s T1 (209s Timberlands), 209s 10 (209s Timberlands) | 2022-09-12 08:00 | 2022-09-15 15:30 | N | N | power transformer 209T1 routine maintenance | Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1852 (29EDD-1 Millennium) | 2022-09-12 08:00 | 2022-09-22 16:00 | N | N | breaker replacement | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock), 12L44 (939s Livock - 951s Thickwood Hills) | 2022-09-12 09:00 | 2022-09-18 17:30 | N | N | breaker maintenance and doble for 1209L | Line |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee), 330p 1208 (330p Genesee), 330p 1209 (330p Genesee) | 2022-09-12 09:30 | 2022-09-18 17:00 | N | Y | breaker maintenance and doble | Line, Circuit Breaker | Genesee 1209L Arrestor Doble, 1208/1209 Breaker Maintenance and Doble, 1208B/1209A/1209LLD Disconnect Maintenance |  | 500 kV, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 658L (562s Cypress - 649s Chappice Lake), 562s 1652 (562s Cypress), 562s 1452 (562s Cypress), 562s 658 (562s Cypress) | 2022-09-12 11:00 | 2022-09-23 12:00 | N | Y | replace 658L A and B line protections and implement SCADA configuration changes | Line, Circuit Breaker, Switch | Replace 658L A and B Line protections and implement SCADA config changes at 562s Cypress and 649s Chappice Lake. Install 138kV MOD and CTs @ 649s. Trip test and commissioning 3 terminal line protections between 662s, 649s and 562s. Connect 658L T-tap to new 662s Hilda Substation. |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO, ALTALINK | 7L224 (650s Hansman Lake - 774s Monitor), 650s 1752 (650s Hansman Lake), 774s 701 (774s Monitor) | 2022-09-12 11:30 | 2022-09-15 16:00 | N | Y | crossarm and insulator replacement project on 7L224 | Line, Circuit Breaker | Crossarm and insulator replacement project on 7L224 |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station), 840s 901 (840s McNeill Station), 840s 701 (840s McNeill Station) | 2022-09-12 12:00 | 2022-09-15 16:15 | Y | Y | valve hall inspection, breaker maintenance | Station, Line, Circuit Breaker |  |  | Limits ATC, Pre-Condition
ALTALINK | 681s T2 (681s Bannerman) | 2022-09-12 12:00 | 2022-09-15 17:30 | N | Y | maintenance, fix leaks, change qualitrol, doble. customer NGR maintenance | Transformer |  |  | 240 kV, For Information Only
ATCO | 784s 7L06D4 (784s Donnelly) | 2022-09-12 12:00 | 2022-09-14 16:00 | N | N | test and operate new SCADA control | Switch |  |  | For Information Only
ALTALINK | 834L (320p Keephills - 384s Keystone), 320p 834X (320p Keephills), 384s 834 (384s Keystone) | 2022-09-12 12:00 | 2022-09-14 18:00 | N | N | line clearance mitigation | Line, Circuit Breaker | Line Clearance Mitigation 834L on structures 4-257 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 63s 2752 (63s Red Deer) | 2022-09-12 13:00 | 2022-09-12 17:00 | N | Y | for the 2652 breaker failure and control P&C upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 294s T2 (294s Brazeau Outlet Works) | 2022-09-12 23:00 | 2022-09-13 07:00 | N | N | fix leaks SFRA, doble, replace broken bus support insulators | Transformer |  |  | For Information Only
ALTALINK | 895s T2 (895s Suffield), 895s 2272 (895s Suffield), 895s 43 (895s Suffield) | 2022-09-13 07:00 | 2022-09-19 13:00 | N | N | upgrade 895s43 switch glass, install new SA on T2, revamp AMI cables to T2 structure for future bus demo | Transformer, Circuit Breaker, Switch | Upgrade 895s43 switch glass, install new SA on T2, revamp AMI cables to T2 structure for future bus demo. |  | For Information Only
ALTALINK | 63s 240kV North Bus (63s Red Deer), 63s T1 (63s Red Deer), 63s 152 (63s Red Deer), 63s 452 (63s Red Deer), 63s 752 (63s Red Deer), 63s 24 (63s Red Deer), 63s 2652 (63s Red Deer) | 2022-09-13 07:30 | 2022-09-13 17:00 | N | Y | 63s 2652 breaker failure and control P&C upgrade | Bus, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514L (513s Lundbreck - 514BL tap) | 2022-09-13 08:00 | 2022-09-13 18:00 | N | Y | changing out insulator on 514L47 | Line |  |  | Pre-Condition, Restricts Generation
ENMAX | 16.60L (SS-16 - SS-34), 16.63L (SS-16 - SS-36), 16.2TR (SS-16), 36B69-16.63/36.5TR (SS-36), 16B69-16.60 (SS-16), 16B69-16.63 (SS-16) | 2022-09-13 08:00 | 2022-09-16 16:00 | N | N | 16.2TR HV & MV bushing replacement | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 841L (477s Amoco West Pembina - 489s Petro-Canada Brazeau River), 477s 841X (477s Amoco West Pembina) | 2022-09-13 08:00 | 2022-09-14 16:00 | N | N | salvage 25 kV underbuild from Altalink 841 line str# 124/1 Gfid# 6906315 to str# 85/ | Line, Circuit Breaker | Fortis Alberta to salvage their 25 KV underbuild from Altalink 841 Line STR# 124/1 Gfid# 6906315 to STR# 85/ |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 635EDD-1000 635PT-1005 (635EDD-1000) | 2022-09-13 08:00 | 2022-09-13 20:00 | N | N | replace model 11 gas relay | Transformer |  |  | For Information Only
ENMAX | 16.2TR (SS-16) | 2022-09-13 08:00 | 2022-09-23 16:00 | N | N | HV & MV bushing replacement, oil sampling MT, TC, check reversing switch | Transformer | 16.2TR HV & MV Bushing Replacement. Oil Sampling MT, TC. Check Reversing Switch. One hour backfeed required on return |  | For Information Only
ALTALINK | 163s C1 (163s Amoco Empress) | 2022-09-13 08:30 | 2022-09-13 13:30 | N | N | functional trip test | Shunts |  |  | Pre-Condition
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap), 811s 708 (811s Clairmont Lake) | 2022-09-13 10:00 | 2022-09-13 11:00 | N | Y | Northstone 731S Elmworth project - protection upgrades | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK, TAYLORPP | 256s T1 (256s Harmattan), 256s 2313W (256s Harmattan), 256s 228X (256s Harmattan), 148s AG-EB25A (148s Schantz), 148s AG-EB510B (148s Schantz), 148s AG-EB510C (148s Schantz), 148s AG-EB510D (148s Schantz), 148s T1 (148s Schantz), 148s T2 (148s Schantz), 148s T3 (148s Schantz) | 2022-09-13 17:00 | 2022-09-23 17:30 | N | Y | oil reclaim work, maint, doble, SFRA, winding test, oil leak repairs & coresense install | Transformer, Switch, Circuit Breaker | T1 Oil reclaim work, maint, doble, SFRA, Winding test, Oil leak repairs & Coresense install |  | Restricts Generation
AESO-SC | OATI | 2022-09-13 18:00 | 2022-09-13 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
SUNCOR, ATCO | 836s 622T (836s Steep Bank), 836s PSD-622-LOAD (836s Steepbank) | 2022-09-14 06:00 | 2022-09-17 18:00 | N | Y | install RFCT on 30PL2-2 | Transformer, Circuit Breaker | 30EDD2;30PL2-2 SYSTEM PM;5y Install RFCT on 30PL2-2 |  | Restricts Generation
ALTALINK | 575s T2 (575s Sundre) | 2022-09-14 08:00 | 2022-09-14 12:30 | N | N | bus differential protection upgrade | Transformer | Protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard. |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28.2TR (SS-28), 42s 29 (42s Sarcee), SW80 (SS-28), SW81 (SS-28), SW82 (SS-28) | 2022-09-14 08:00 | 2022-09-14 12:00 | N | N | fall substation washing | Line, Transformer, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), SW83 (SS-28), SW85 (SS-28), SW84 (SS-28), 28B138-1.80 (SS-28), 28MD138-28.1TR (SS-28) | 2022-09-14 12:00 | 2022-09-14 18:00 | N | N | fall substation washing | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 575s T1 (575s Sundre) | 2022-09-14 13:00 | 2022-09-14 17:30 | N | N | bus differential protection upgrade | Transformer | Protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard. |  | For Information Only
ENMAX | 3.84L (SS-3 - SS-13), 13B138-3.84 (SS-13) | 2022-09-15 08:00 | 2022-09-15 16:00 | N | N | HV breaker SF6 gas sample | Line, Circuit Breaker | HV breaker SF6 Gas Sample - 13B138-3.84 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23), SW81 (SS-23), SW82 (SS-23), 23B138-2.80 (SS-23), 23MD138-23.3TR (SS-23) | 2022-09-15 08:00 | 2022-09-15 12:00 | N | N | fall substation washing | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | Sask Power S1M Line, Sask Power R1P | 2022-09-15 09:00 | 2022-09-15 14:00 | N | N | A4D Line, BA4 Line, BD22 Line, C1Q Line-CCSS to L1, C2W Line, CD 903T, ER 801T, P3C Line-PESS to L1, PA 705P, PA 805T, PA2, PN 402T, PN 802T, R1P Line-PQSS TO L4, R5B Line, S1M Line-L2 to MC, W3B Line, W4B-BA Line, W4B-WL Line, WE 801T OOS | Line |  |  | Limits ATC, Pre-Condition
ATCO | 7L22 (790s Poplar Hill - 7L88 tap), 790s 702 (790s Poplar Hill) | 2022-09-15 10:00 | 2022-09-15 11:00 | N | Y | Northstone 731S Elmworth project protection upgrades | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 74s 30 (74s Janet), SW84 (SS-23), SW87 (SS-23), SW88 (SS-23), 23B138-23.80 (SS-23), 23MD138-23.4TR (SS-23) | 2022-09-15 12:00 | 2022-09-15 18:00 | N | N | fall substation washing | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2022-09-15 12:00 | 2022-09-26 14:00 | N | N | fencing replacement project | Shunts |  |  | Pre-Condition
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare), 790s 703 (790s Poplar Hill) | 2022-09-15 13:00 | 2022-09-15 14:00 | N | Y | Northstone 731S Elmworth project protection upgrades | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, CNRL, ALBIAN | 847s 901T (847s Muskeg River), 919s 906 (919s Hartley) | 2022-09-15 13:30 | 2022-09-23 16:00 | N | Y | troubleshoot | Transformer, Circuit Breaker |  | CNRL plant ESD, they called and requested a Condition of Guarantee. | 240 kV, Restricts Generation
ENMAX | 2.84L (SS-2 - SS-8) | 2022-09-16 08:00 | 2022-09-17 16:00 | N | N | manhole repairs | Line |  |  | Pre-Condition
ATCO | 7L85 (803s ATC Bullpound - 7LA85 Tap) | 2022-09-16 09:00 | 2022-09-16 12:00 | N | N | urgent repair - tie down insulator pin out | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2022-09-17 00:22 | 2022-09-30 18:00 | N | Y | forced outage | Shunts |  |  | Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14), 11.83L (SS-162 - SS-11), 11.3TR (SS-11), 11.2TR (SS-11), 11MD138-11.2TR (SS-11), 11B138-BT5 (SS-11), 11MD138-11.3TR (SS-11) | 2022-09-17 08:00 | 2022-09-17 18:00 | N | N | fall substation washing, retrieve nameplate info and oil sampling MT, TC | Line, Transformer, Switch, Circuit Breaker | Fall Substation Washing. 11 Sub 11.2TR MD & SW -Retrieve Nameplate Info. Oil Sampling MT, TC. |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 719L (575s Sundre - 719CL Tap), 575s 719X (575s Sundre) | 2022-09-17 08:00 | 2022-09-17 12:30 | N | N | protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 719L (378s Shell Caroline - 575s Sundre), 575s 719N (575s Sundre) | 2022-09-17 13:00 | 2022-09-17 17:30 | N | N | protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard. | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27) | 2022-09-18 08:00 | 2022-09-18 10:00 | N | N | fall transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-65 260kV Bus 29PP-0048 (29EDD-65) | 2022-09-18 08:00 | 2022-09-18 18:00 | N | Y | 29PT-253; C phase oil top up | Bus |  |  | 240 kV, For Information Only
ENMAX | 22.81L (SS-22 - SS-39), 39.82L (SS-39 - SS-162), 39.2TR (SS-39), 39.4TR (SS-39), 39MD138-39.4TR (SS-39), 39MD138-39.2TR (SS-39) | 2022-09-18 08:00 | 2022-09-18 12:00 | N | N | fall substation washing and check reversing switch 39.4TR | Line, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 844s 701T (844s AEC Mill), 844s 701 (844s AEC Mill) | 2022-09-18 10:00 | 2022-10-03 16:00 | N | N | 701T outage required for protection upgrade | Transformer, Circuit Breaker |  | 701T outage required for protection upgrade | For Information Only
ENMAX | 15.62L (SS-15 - SS-16) | 2022-09-18 10:00 | 2022-09-18 12:00 | N | N | fall transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34) | 2022-09-18 12:00 | 2022-09-18 14:00 | N | N | fall transmission line washing, shared structure with 15.62L | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 38.83L (SS-38 - SS-39), 39.82L (SS-39 - SS-162), 39.1TR (SS-39), 39.3TR (SS-39) | 2022-09-18 12:00 | 2022-09-18 18:00 | N | N | fall substation washing and check reversing switch 39.3TR | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 255s 34 (255s Vulcan) | 2022-09-18 12:30 | 2022-09-18 15:30 | N | Y | breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
EPCOR | 816s P2401 (816s Petrolia) | 2022-09-19 07:00 | 2022-09-19 17:00 | N | Y | DC cutover | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s Victoria T5 (EP 511s Victoria), EP 511s V2401 (EP 511s Victoria), EP 511s V728 (EP 511s Victoria), EP 511s V727 (EP 511s Victoria), 557s CD2406 (557s Castle Downs) | 2022-09-19 07:00 | 2022-09-29 17:00 | N | Y | op-checks and maintenance | Line, Transformer, Circuit Breaker | Victoria TX5 and CV5 Zone P&C Crew: TX5 and CV5 Zone Op-Checks and Maintenance UGT Crew: CV5 Manhole Inspections and Maintenance |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 345s T1 (345s Hornbeck) | 2022-09-19 07:00 | 2022-09-20 18:00 | N | N | cleaning and installing bird cover | Transformer |  | Cleaning up deficiencies and installing bird cover | For Information Only
EPCOR | 72LS24 (EP 803s Lambton - Strathcona), 72LH8 (EP 803s Lambton - EP Hardisty), S724 (Strathcona) | 2022-09-19 07:00 | 2022-10-04 17:00 | N | N | P&C cutovers for breaker fail and protection upgrades | Line, Circuit Breaker |  | Strathcona: P&C Cutovers for Breaker Fail and TX Prot. Upgrade | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T2 (Meadowlark) | 2022-09-19 07:00 | 2022-09-20 17:00 | N | N | Tx2 revenue metering relocation | Transformer |  |  | For Information Only
ALTALINK | 33s 6 (33s Spray) | 2022-09-19 08:00 | 2022-09-21 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 959s 901T (959s Lanfine), 959s 701 (959s Lanfine) | 2022-09-19 08:00 | 2022-09-19 10:00 | N | Y | test switch status inputs to new protection | Transformer, Circuit Breaker |  | Test switch status inputs to new protection for 7L138 line addition | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 16.63L (SS-16 - SS-36), 36.5TR (ENMAX 36), 36.2TR (SS-36), 16B69-16.63 (SS-16), 36B69-16.63/36.5TR (SS-36), 36B138-14.83 (SS-36), 36B138-36BT3 (SS-36), 36MD138-36.5TR (SS-36), 36MD138-36.2TR (SS-36), SW84 (SS-36) | 2022-09-19 08:00 | 2022-09-19 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch | Fall Substation Washing. 36 Sub SW 61, 36.5R MD & SW -Retrieve Nameplate Info |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 13.2TR (SS-13) | 2022-09-19 08:00 | 2022-09-22 16:00 | N | N | tapchanger maintenance, check reversing switch, oil sampling MT, TC, ol leak repair | Transformer |  |  | For Information Only
Lethbridge | 813L (146s MacDonald - 241s Uplands), 241s 813L (241s Uplands), 146s 813L (146s Macdonald), 241s 13 (241s Uplands), 146s 1 (146s Macdonald) | 2022-09-19 08:00 | 2022-09-30 17:00 | N | N | replace 146S813L 138 kV breaker | Line, Circuit Breaker, Switch | Line outage to replace 146S813L 138 kV breaker. |  | Creates Radial Feeds, Firm Load Loss
Lethbridge | 146s T1 (146s Macdonald) | 2022-09-19 08:00 | 2022-12-09 18:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
ALTALINK | 297s 389 (297s Rimbey), 297s T2 (297s Rimbey) | 2022-09-19 08:00 | 2022-09-21 17:30 | N | N | installing new PT and wiring for future install | Switch, Transformer |  |  | For Information Only
ENMAX | 43.2TR (SS-43) | 2022-09-19 08:00 | 2022-09-23 16:00 | N | N | HV bushing replacement, oil sampling MT, TC(X), (Y), check reversing switch (Y), (X). 43MD138-43.2TR mouse nest removal | Transformer | HV Bushing Replacement. Oil Sampling MT, TC(X), (Y). Check Reversing Switch (Y), (X). 43MD138-43.2TR Mouse Nest Removal |  | For Information Only
ATCO | 2060s 702T (2060s Engstrom) | 2022-09-19 09:30 | 2022-09-21 17:00 | N | N | maintenance | Transformer |  | 702T Maintenance | For Information Only
ALTALINK, EPCOR | 908L (89s Ellerslie - 908AL tap), 908L (38s East Edmonton - 908AL tap), 52s T2 (52s East Industrial), 52s EDS2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2022-09-19 09:30 | 2022-09-23 17:00 | N | Y | CVT/Arrestor/TX2 doble and EDS2/E2T2 Maintenance | Line, Transformer, Switch, Circuit Breaker | East Industrial 908L CVT/Arrestor/TX2 Doble and EDS2/E2T2 Maintenance |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 1.80L (SS-1 - SS-28), 28B138-1.80 (SS-28) | 2022-09-19 10:00 | 2022-09-19 12:00 | N | N | fall pothead washing | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L03 (731s Elmworth - 7L09 tap), 731s 7L03D4 (731s Elmworth) | 2022-09-19 10:00 | 2022-09-19 11:00 | N | Y | 731s Elmworth project protection upgrades | Line, Switch |  | Northstone DG at 731S Elmworth Project Protection upgrades | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 20s T1 (20s Ghost), 20s 30 (20s Ghost), 20s 10 (20s Ghost), 20s 54 (20s Ghost), 20s 1 (20s Ghost), 20s 2 (20s Ghost), 20s 3 (20s Ghost), 20s 4 (20s Ghost) | 2022-09-19 11:00 | 2022-10-04 17:00 | N | N | replace transformer T1 | Transformer, Circuit Breaker | TAU Outage to replace Transformer T1, upgrade protections and function test trips from 20s protections. |  | Restricts Generation
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20) | 2022-09-19 12:00 | 2022-09-19 13:00 | N | N | fall pothead washing | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 834L (320p Keephills - 384s Keystone), 320p 834X (320p Keephills) | 2022-09-19 12:00 | 2022-09-22 16:00 | N | N | line clearance mitigation | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 310p 2152 (310p Sundance) | 2022-09-19 12:30 | 2022-09-22 17:30 | N | Y | breaker maintenance | Circuit Breaker | Breaker maintenance including first trips |  | 240 kV
ENMAX | 9.83L (SS-9 - SS-43) | 2022-09-19 13:00 | 2022-09-19 14:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L03 (775s Sullivan Lake - 6L17 Tap), 775s 603 (775s Sullivan Lake) | 2022-09-19 13:00 | 2022-09-22 16:00 | N | N | crossarm and insulator replacement | Line, Circuit Breaker |  | We require a GOI on 6L03 for crossarm and insulator replacement. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L69 (731s Elmworth - 815s Goodfare), 731s 702 (731s Elmworth) | 2022-09-19 13:00 | 2022-09-19 14:00 | N | Y | protection upgrades | Line, Circuit Breaker |  | Northstone DG at 731S Elmworth Project Protection upgrades | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T1 (Garneau), G722 (Garneau), G721 (Garneau) | 2022-09-19 14:00 | 2022-09-21 17:00 | N | N | forced outage | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43) | 2022-09-19 14:00 | 2022-09-19 16:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 217s T1 (217s North Red Deer) | 2022-09-19 15:00 | 2022-09-23 15:30 | N | N | relay maintenance testing PRC-005 | Transformer |  |  | For Information Only
ALTALINK | 20s 138kV South Bus (20s Ghost), 859L (20s Ghost - AML 793s Horse Creek), 150L (20s Ghost - 150AL Tap), 113L (20s Ghost - 33s Spray), 20s T1 (20s Ghost) | 2022-09-20 07:00 | 2022-09-24 07:59 | N | Y | replace CVT1 and connect to new distribution. complete T1 CT contributions and trip testing new bus protection, trip testing cutover MOD 20s153 to new building and controls | Bus, Line, Transformer | Replace CVT1 and connect to new distribution. Complete T1 CT contributions and trip testing new bus protection, Trip testing Cutover MOD 20s153 to new building and controls |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 790L (434s Stony Plain - 790AL tap) | 2022-09-20 07:30 | 2022-09-20 17:30 | N | N | Operate 790L62 to assess switch condition | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CDVP | VCN1 Vulcan | 2022-09-20 08:00 | 2022-10-04 15:00 | N | N | P1831 Fortis 255S Vulcan Faribault Farms DG PV. 22 MW. ISD September 27, 2022 | Unit
ENMAX | 20.3TR (SS-20) | 2022-09-20 08:00 | 2022-09-20 16:00 | N | N | relay, protection testing, rirmware upgrade | Transformer |  |  | For Information Only
ATCO | 890s 701 (890s Melito), 890s 701T (890s Melito) | 2022-09-20 08:00 | 2022-09-22 16:00 | N | N | breaker maintenance | Circuit Breaker, Transformer |  | breaker maintenance in coordination with plant outage | For Information Only
ENMAX | 8.6TR (SS-8) | 2022-09-20 08:00 | 2022-11-08 15:10 | N | N | testing and maintenance | Transformer | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas Relay Testing. Check Reversing Switch. Oil Sampling MT, TC. |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 32.83L (SS-32 - SS-40), 32.1TR (SS-32), 32.2TR (SS-32), 32B138-32BT5 (SS-32), 32MD138-32.2TR (SS-32) | 2022-09-20 08:00 | 2022-09-20 12:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 20s 150 (20s Ghost), 150L (20s Ghost - 150AL Tap) | 2022-09-20 08:01 | 2022-09-26 16:00 | N | N | full apparatus testing and breaker 20s150 control cutovers in coordination with 20s 138kV bus outage. | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 65s 13N (65s High River), 13L (65s High River - 392s Black Diamond), 65s T1 (65s High River) | 2022-09-20 08:30 | 2022-09-20 16:30 | N | N | gauge relocation | Circuit Breaker, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 437s T2 (437s Baymag) | 2022-09-20 08:30 | 2022-09-20 17:30 | N | N | troubleshoot/trace/test the OLTC controller | Transformer |  |  | For Information Only
ATCO | 851s 701T (851s Morse River) | 2022-09-20 10:00 | 2022-09-22 12:30 | N | N | transformer and VR maintenance, load from substation can be transferred to adjacent subs as per attached email | Transformer |  | transformer and VR maintenance, load from substation can be transferred to adjacent subs as per attached email | For Information Only
ATCO | 815s 702 (815s Goodfare), 7L07 (790s Poplar Hill - 815s Goodfare) | 2022-09-20 10:00 | 2022-09-20 11:00 | N | Y | Northstone 731s Elmworth project protection upgrades | Circuit Breaker, Line |  | Northstone DG at 731S Elmworth Project Protection upgrades | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32) | 2022-09-20 12:00 | 2022-09-20 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 161L (255s Vulcan - 504s Queenstown), 504s 161 (504s Queenstown) | 2022-09-20 13:00 | 2022-09-21 17:00 | N | N | connect CT's for the new RAS 174 relays | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 815s 704 (815s Goodfare), 7L69 (731s Elmworth - 815s Goodfare) | 2022-09-20 13:00 | 2022-09-20 14:00 | N | Y | Northstone 731S Elmworth project protection upgrades | Circuit Breaker, Line |  | Northstone DG at 731S Elmworth Project Protection upgrades | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 746AL (524s Owens Fiberglass - 746L Tap), 524s T1 (524s Owen Corning), 524s 6 (524s Owens Corning) | 2022-09-21 07:00 | 2022-09-21 17:00 | N | N | 524S6 circuit switcher maintenance | Line, Transformer, Circuit Breaker | Owens Corning: 524S6 Circuit Switcher Maintenance |  | For Information Only
ALTALINK | 165s Gainford, 165s T1 (165s Gainford), 156BL (165s Gainford - 156L Tap), 165s 156 (165s Gainford) | 2022-09-21 07:00 | 2022-09-21 19:00 | N | N | cleaning up deficiencies and installing bird cover | Station, Transformer, Line, Circuit Breaker | Cleaning up deficiencies and installing bird cover |  | For Information Only
ALTALINK | 396s T1 (396s Pincher Creek), 396s 30 (396s Pincher Creek) | 2022-09-21 07:30 | 2022-09-21 12:30 | N | N | gauge relocation | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 14.2TR (SS-14), 14.4TR (SS-14), 14B138-14.83 (SS-14), 14.1C (SS-14), 14.2C (SS-14) | 2022-09-21 08:00 | 2022-09-21 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-71 29PT-233 (29EDD-71), 29EDD-71 752-4633 (29EDD-71), 29EDD-71 752-4632 (29EDD-71), 29EDD-71 29PS-252 (29EDD-71 Edd71Sub) | 2022-09-21 08:00 | 2022-09-28 18:00 | N | N | maintenence | Transformer, Circuit Breaker, Switch | 29EDD71;29PT-233 & 30PD-15 SYSTEM;PM 5y 29PT-233 RADIATOR FLANGE LEAK 29EDD-71;144KV NODE,29PT-245 MAINT;PM 5y |  | For Information Only
ATCO | 844s 702T (844s AEC Mill) | 2022-09-21 08:00 | 2022-09-22 17:00 | N | N | maintenence | Transformer |  | Full Mill Shutdown for Slave Lake Pulp, 844S 701T already OOS under permit# 2-65271 | For Information Only, Restricts Generation
ALTALINK | 575s T2 (575s Sundre) | 2022-09-21 08:00 | 2022-09-21 12:30 | N | N | protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard | Transformer | Protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard. |  | For Information Only
ALTALINK | 309s T2 (309s Anthony Henday) | 2022-09-21 08:30 | 2022-09-21 12:30 | N | N | installing nameplates | Transformer |  |  | For Information Only
ALTALINK | 151s C1 (151s Strathmore), 151s 44 (151s Strathmore) | 2022-09-21 10:00 | 2022-09-21 17:30 | N | N | 138 kV breaker maintenance | Shunts, Switch |  |  | Pre-Condition
ALTALINK | 309s T1 (309s Anthony Henday) | 2022-09-21 12:31 | 2022-09-21 16:30 | N | N | installing nameplates | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek), 396s 185 (396s Pincher Creek) | 2022-09-21 12:31 | 2022-09-21 17:30 | N | N | gauge relocation, low gas | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 575s T1 (575s Sundre) | 2022-09-21 13:00 | 2022-09-21 17:30 | N | N | protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 727L (678s Okotoks - 727AL tap) | 2022-09-22 06:15 | 2022-09-23 17:45 | N | N | emergency repair; burnt cross arm replacement (str 93) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | PM2405 (Poundmaker) | 2022-09-22 07:00 | 2022-09-22 17:00 | N | N | emergency - PM2405 SF6 top-up due to low gas | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | T2 (Garneau) | 2022-09-22 07:00 | 2023-05-29 13:00 | N | N |  | Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | T1 (Meadowlark) | 2022-09-22 07:00 | 2022-09-23 17:00 | N | N | Tx1 revenue metering relocation | Transformer |  |  | For Information Only
Lethbridge | 823L (146s MacDonald - 593s Lakeview) | 2022-09-22 08:00 | 2022-09-22 17:00 | N | N | open end to test/trip 823L breaker | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2022-09-22 08:00 | 2022-09-22 20:00 | N | Y | FLAR Jb modifications | Line | this is for FLAR Jb modifications BC maintenance does not affect the Alberta ATC |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 719L (575s Sundre - 719CL Tap), 575s 719X (575s Sundre) | 2022-09-22 08:00 | 2022-09-22 12:30 | N | N | protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard. | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20) | 2022-09-22 08:00 | 2022-09-22 12:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 20.82L (SS-20 - SS-21), 20.3TR (SS-20), 20B138-20.82 (SS-20) | 2022-09-22 12:00 | 2022-09-22 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 719L (378s Shell Caroline - 575s Sundre), 575s 719N (575s Sundre) | 2022-09-22 13:00 | 2022-09-22 17:30 | N | N | protection upgrade project to replace existing, non-redundant, bus differential protection to latest standard | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 297s Rimbey, 757L (297s Rimbey - 758L tap), 297s T1 (297s Rimbey), 297s T2 (297s Rimbey), 297s 189 (297s Rimbey), 297s 389 (297s Rimbey), 297s 757 (297s Rimbey) | 2022-09-23 | 2022-09-23 05:00 | N | N | removing VT3 and installing new VT on Bus 2 | Station, Line, Transformer, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake), 804L (40s Wetaskiwin - 40s 803L Tap), 804L (40s 803L Tap - 86s 803L Tap), 804L (86s Bigstone - 86s 803L Tap), 40s 858N (40s Wetaskiwin) | 2022-09-23 07:00 | 2022-09-25 18:00 | N | N | replace structures 92 and 94 and screw barrels | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage
ALTALINK | 674L (244s Bowmanton - 649s Chappice Lake), 649s Chappice Lake, 244s 3052 (244S Bowmanton), 244s 3152 (244s Bowmanton) | 2022-09-23 08:00 | 2022-10-07 12:00 | N | Y | installation of new A and B line protections at 244s Bowmanton, 649s Chappice Lake | Line, Station, Circuit Breaker | Installation of new A and B line protections at 244s Bowmanton, 649s Chappice Lake. Installation of New CVTs, 25kV PT and 25kV Switch @ 649s Chappice Lake. Also installing new 25kV PT along with all applicable protections for new DER. |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 749s 703 (749s Flyingshot Lake) | 2022-09-23 09:00 | 2022-09-23 10:00 | N | N | 731S Elmworth Project protection upgrades | Circuit Breaker |  | Northstone DG at 731S Elmworth Project Protection upgrades | Over/Under Voltage, Overload, Pre-Condition
ATCO | 749s 702 (749s Flyingshot Lake) | 2022-09-23 14:15 | 2022-09-23 15:30 | N | N | 731S Elmworth Project Protection upgrades | Circuit Breaker |  | Northstone DG at 731S Elmworth Project Protection upgrades | Contingency Requires Mitigation, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38MD138-38.2TR (SS-38), 38.3TR (SS-38), 38MD138-38.3TR (SS-38), 38.1C (SS-38), 38B138-37.81 (SS-38) | 2022-09-24 08:00 | 2022-09-24 13:00 | N | N | fall substation washing, check reversing switch 38.2TR | Line, Transformer, Switch, Shunts, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 20s 138kV North Bus (20s Ghost), 20s 138kV South Bus (20s Ghost), 113L (20s Ghost - 33s Spray), 20s T1 (20s Ghost), 150L (20s Ghost - 150AL Tap), 859L (20s Ghost - AML 793s Horse Creek), 418L (20s Ghost - 189L Tap), 56L (20s Ghost - 245s Seebe) | 2022-09-24 08:00 | 2022-09-24 16:00 | N | Y | complete cutover of MOD 20s14 and functional testing | Bus, Line, Transformer |  |  | Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ENEL, ATCO | 708s Grizzly Bear, 7LA65 (708s Grizzly Bear - 7LA65 tap), 7L65D2 (7LA65 Tap), 7L65D3 (7LA65 Tap), 7LA65D1 (7LA65 Tap) | 2022-09-24 08:00 | 2022-10-08 16:00 | N | N | P1250 Wild Run Grizzly Bear Wind. 120 MW. ISD Dec 01, 2022 | Station, Line, Switch
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 38.1TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 38MD138-38.1TR (SS-38), 38MD138-38.3TR (SS-38) | 2022-09-24 13:00 | 2022-09-24 18:00 | N | N | fall substation washing, check reversing switch 38.1TR | Line, Circuit Breaker, Transformer, Shunts, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 749L (648s Metiskow - 749AL tap) | 2022-09-25 06:00 | 2022-09-26 18:00 | N | N | 749L (project D.0841) scope of work includes replacing structure 2 with a new structure and salvaging the old structure. | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 484s T1 (484s Millar Western) | 2022-09-25 08:00 | 2022-10-03 18:00 | N | N | T1 bushing and arrestor replacement, T1 oil leak, maintenance, and protection replacement | Transformer |  |  | For Information Only
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.2TR (SS-9), 9.3TR (SS-9), 9B138-9.83 (SS-9), 2MD138-2.81 (SS-2), 9MD138-9.3TR (SS-9), 9MD138-9.2TR (SS-9) | 2022-09-25 08:00 | 2022-09-25 18:00 | N | N | fall substation washing, SW88, SW90, 9.3MD & SW | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 795L (121s Brooks - 421s Hays), 121s 138kV South Bus (121s Brooks), 121s T2 (121s Brooks), 121s 827W (121s Brooks), 121s 795X (121s Brooks) | 2022-09-25 11:30 | 2022-09-30 17:45 | N | Y | 121s T2 bushing/LA replacement/121s795x CT replacement | Line, Bus, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 199s T1 (199s East Airdrie) | 2022-09-26 06:30 | 2022-10-07 17:30 | N | N | demo old T1/VR1, install new foundations, install new T1 with NGR and above grade containment | Transformer |  |  | For Information Only
EPCOR | G722 (Garneau), 72RG7 (Garneau - Rossdale), RG725 (Rossdale) | 2022-09-26 07:00 | 2022-10-25 17:00 | N | N | Rossdale RG725 LCR | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | Sask Power R1P | 2022-09-26 07:00 | 2022-09-30 18:30 | N | N | maintenance | Line | BD22 Line, C2H, C2W Line, CD 903T, CD11 Line, ER 801T, FS 729T, GL 801T, PA2, PE 403T, PE 903T, QE 804PR, QE 807T, R1P Line-PQSS TO L4, R1R Line, U91A Line, W1R Line-WYSS to L7, W3B Line, WE 801T |  | Limits ATC, Pre-Condition
EPCOR | 72RG7 (Garneau - Rossdale) | 2022-09-26 07:00 | 2022-09-26 17:00 | N | N | RG7: impedance testing | Line |  |  | Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana), 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte), 120s 1152S (120s Picture Butte) | 2022-09-26 07:00 | 2022-10-07 18:00 | Y | Y | M120s maintenance | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Limits ATC, Pre-Condition
ENMAX | 1.8TR (SS-1) | 2022-09-26 08:00 | 2022-09-29 16:00 | N | N | tapchanger and transformer maintenance | Transformer |  |  | For Information Only
NWE, BHE Canada | Great Falls Switchyard (NorthWestern Energy) - Marias (MATL) | 2022-09-26 08:00 | 2022-09-27 16:30 | N | Y | 2022 Relay WECC Testing | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ENMAX | 26B138-26BT3 (SS-26) | 2022-09-26 08:00 | 2022-10-03 18:00 | N | N | sub cable trench replacement, remove and re-install control cables | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2022-09-26 08:00 | 2022-10-03 10:59 | N | Y | line mitigation, cross arm replacement | Line |  | Line mitigation, Cross arm replacement | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 13.82L (SS-13 - SS-22), 22.1TR (SS-22), 22.3TR (SS-22), 22B138-13.82 (SS-22), 22B138-22BT8 (SS-22), 22MD138-22.1TR (SS-22), 22MD138-22.3TR (SS-22) | 2022-09-26 08:00 | 2022-09-26 12:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 16.61L (SS-16 - SS-27), 15.62L (SS-15 - SS-16), 16.60L (SS-16 - SS-34), 16.1TR (SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16), 16B69-16.61 (SS-16), 16MD69-16.1TR (SS-16) | 2022-09-26 08:00 | 2022-10-06 16:00 | N | N | 16.1TR HV & MV bushing repalcement, check reversing switch, 15.62L tower inspections | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L06 (784s Donnelly - 787s High Prairie) | 2022-09-26 08:00 | 2022-09-26 17:00 | N | N | 784S Donnelly Rebuild Project Detach 902S mobile Substation | Line |  | 784S Donnelly Rebuild Project Detach 902S mobile Substation | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 43.1TR (SS-43) | 2022-09-26 08:00 | 2022-09-30 16:00 | N | N | HV bushing replacement and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 63s 2752 (63s Red Deer) | 2022-09-26 08:00 | 2022-10-07 13:00 | N | Y | 2752 breaker failure and control P&C upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 29EDD-1 29EDD1S1452 (29EDD-1 Millennium) | 2022-09-26 08:00 | 2022-10-06 15:00 | N | N | breaker replacement | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2022-09-26 09:00 | 2022-09-28 18:00 | Y | Y | component replacements on structures #45 - 459 | Line |  |  | 500 kV, Affects Cranking Path
ATCO | 809s 904 (809s Louise Creek) | 2022-09-26 09:00 | 2022-10-03 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | breaker maintenance | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 2060S 701T | 2022-09-26 09:30 | 2022-09-28 21:00 | N | N | maintenance | Terminal Equipment |  | 701T Maintenance | For Information Only
REDDEER | 217s T2 (217s North Red Deer) | 2022-09-26 10:00 | 2022-10-03 08:30 | N | N | relay maintenance testing PRC-005 | Transformer |  |  | For Information Only
ALTALINK | 115s T2 (115s Mount Allan), 115s 252 (115s Mount Allan) | 2022-09-26 10:30 | 2022-10-28 11:00 | N | N | transformer replacement | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 520s T1 (520s Bennett) | 2022-09-26 11:30 | 2022-09-29 17:00 | N | Y | bushing monitor replacement on all 3 phases + spare and DGA monitor (replacing PD monitor on T1, two phases only) | Transformer |  |  | 500 kV, For Information Only
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2022-09-26 12:00 | 2022-10-14 17:30 | N | Y | breaker 401 maintenance, pick overgrown weeds & spray | Shunts, Circuit Breaker |  | - Breaker 401 Maintenance - Pick Overgrown Weeds & Spray | 240 kV, Pre-Condition
ALTALINK | 834L (320p Keephills - 384s Keystone), 384s 834 (384s Keystone), 320p 834X (320p Keephills) | 2022-09-26 12:00 | 2022-09-28 18:00 | N | N | line clearance mitigation 834L on structures 4-257 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 6L09 (772s Youngstown - 776s Richdale) | 2022-09-26 13:00 | 2022-09-30 15:00 | N | N | pole replacement project on 6L09 | Line |  | Pole Replacement Project on 6L09. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 749L (899s Edgerton - 749AL tap) | 2022-09-27 06:00 | 2022-09-27 20:00 | N | Y | 749L (project D.0841) scope of work includes replacing cross-arms on structure 217 & 218 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 162.1TR (SS-162), 240kV North Bus (SS-162), 138kV North Bus (SS-162), 162B138-RB80 (SS-162), 162B138-RB86 (SS-162), 162B138-RB94 (SS-162), 162B240-RB131 (SS-162), 162B240-RB134 (SS-162), 162MD138-162.1TR (SS-162), 162MD240-162.1TR (SS-162), SW109 (SS-162), SW110 (SS-162), SW81 (SS-162), SW96 (SS-162), SW131 (SS-162), SW141 (SS-162) | 2022-09-27 08:00 | 2022-09-27 18:00 | N | N | summer substation washing | Transformer, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
CMH | CMH1 Medicine Hat #1 | 2022-09-27 08:00 | 2022-09-27 11:00 | N | N | migrating power feeds to new UPS panel | Unit |  |  | Affects Visibility
ALTALINK | 804L (40s 803L Tap - 86s 803L Tap), 804L (40s Wetaskiwin - 40s 803L Tap), 804L (86s Bigstone - 86s 803L Tap), 40s 804W (40s Wetaskiwin), 86s 852 (86s Bigstone) | 2022-09-27 08:00 | 2022-10-02 15:00 | N | N | complete salvage / demo of all salvage released equipment and structures at 40s. 803/804L outage required for clearance to safely demo savaged equipment and structures | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L128 (802s Michichi Creek - 963s Coyote Lake) | 2022-09-27 08:00 | 2022-09-30 17:00 | N | N | stringing T-Tap under existing 7L128 between structures 72 and 73 | Line |  | Stringing T-Tap under existing 7L128 between structures 72 and 73. Flying jumpers to be installed between 7L128 and new BER line. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 37s 76 (37s North Calder) | 2022-09-27 08:00 | 2022-09-27 17:30 | N | Y | investigate cold weather alarm and low pressure on 2 heads | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 40s T1 (40s Wetaskiwin) | 2022-09-27 08:00 | 2022-09-28 16:00 | N | N | disconnect risers and salvage 40s79 138kv switch live parts and stack insulators, switch base remains to support string bus from 40s106 | Transformer |  |  | For Information Only
ALTALINK | 535s T2 (535s Joffre) | 2022-09-27 10:00 | 2022-09-27 16:00 | N | N | maintenance, doble, fix leaks | Transformer |  |  | For Information Only
ALTALINK | 535s T2 (535s Joffre) | 2022-09-27 16:00 | 2022-09-29 13:00 | N | N | maintenance, doble, fix leaks | Transformer |  |  | For Information Only
ALTALINK | 749L (899s Edgerton - 7LB749 tap) | 2022-09-28 06:00 | 2022-10-01 18:00 | N | Y | scope of work includes replacing cross-arms on structure 434 & 435, replace dead-end structure 319 | Line | 749L (project D.0841) scope of work includes replacing cross-arms on structure 434 & 435. Replace dead-end structure 319 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, ENMAX | 74s 138kV North Bus (74s Janet), 37.82L (74s Janet - SS-37), 691L (74s Janet - 419s Chestermere), 74s 691 (74s Janet), 74s 76 (74s Janet), 74s 37.82W (74s Janet) | 2022-09-28 07:00 | 2022-09-29 17:00 | N | Y | replacing breaker 74s37.82 | Bus, Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 749L (899s Edgerton - 7LB749 tap), 899s 749N (899s Edgerton) | 2022-09-28 07:30 | 2022-09-28 18:30 | N | Y | 899S (project D.0841) scope of work change ratio on CT8 | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 58L (32s Barrier - 245s Seebe) | 2022-09-28 08:00 | 2022-09-30 17:00 | N | N | FRM maintenance on structures 2/4/8/14/30/40/44 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 11.81L (SS-11 - SS-13), 11.1TR (SS-11), 11.4TR (SS-11), 11B138-BT5 (SS-11), 11MD138-11.1TR (SS-11), 11MD138-11.4TR (SS-11), 11B138-11.81 (SS-11) | 2022-09-28 08:00 | 2022-09-28 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Overload, Pre-Condition
ALTALINK | 906s T1 (906s Ross Creek) | 2022-09-28 08:30 | 2022-09-28 17:30 | N | N | PD test prior to de-energization, doble/sample HV bushings,, inspect H2 IDD connection | Transformer |  |  | For Information Only
ATCO | 9L990 (72s Leismer - 2049s Kettle River) | 2022-09-28 10:00 | 2022-09-28 12:00 | N | Y | ATCOrequires breaker open advice on 9L990 due to slow fault clearing times during ATCO Kettle River telecom upgrades | Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 404s Peace Butte, 600L (404s Peace Butte - 523s Bullshead), 523s 600 (523s Bullshead), 404s 12 (404s Peace Butte), 404s 600 (404s Peace Butte) | 2022-09-29 07:30 | 2022-09-29 18:30 | N | N | check on trip coil, DGA sampling | Station, Line, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 484s Millar Western, 825L (77s Sagitawah - 484s Millar Western), 77s 652 (77s Sagitawah), 77s 552 (77s Sagitawah), 484s 825 (484s Millar Western), 77s 825N (77s Sagitawah), 484s 2 (484s Millar Western), 484s 3 (484s Millar Western), 484s 4 (484s Millar Western), 484s 10 (484s Millar Western) | 2022-09-29 07:30 | 2022-09-29 18:30 | N | Y | switch maintenance, telecom tower salvage | Station, Line, Circuit Breaker, Switch | Switch maintenance on 77s825N, 77s33, 77s34. Telecom tower salvage in proximity to 825L. |  | Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ALTALINK | 230s Wardlow, 601L (230s Wardlow - 275s Jenner) | 2022-09-29 08:00 | 2022-09-29 16:00 | N | N | stringing of new 949L line ( 275s Jenner to 306s Halsbury) across existing 601L | Station, Line |  |  | For Information Only
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 146s 667 (146s Macdonald) | 2022-09-29 08:00 | 2022-09-30 17:00 | N | Y | open end to test/trip 667L breaker and install conductor | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10.1TR (SS-10), 10B138-832 (SS-10), 10MD138-10.1TR (SS-10) | 2022-09-29 08:00 | 2022-09-29 18:00 | N | Y | summer substation washing. oil sampling MT, TC | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
EPCOR | T3 (Rossdale) | 2022-09-29 08:00 | 2022-10-06 15:00 | N | N | forced outage | Transformer |  |  | For Information Only
ALTALINK | 535s T2 (535s Joffre) | 2022-09-29 13:00 | 2022-09-29 18:00 | N | N | Maintenance, doble, fix leaks | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 74s 37.82W (74s Janet), 74s 45 (74s Janet) | 2022-09-29 17:00 | 2022-10-11 17:00 | N | Y | replacing breaker 74s37.82 | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2022-09-30 08:00 | 2022-10-06 18:15 | Y | Y | line maintenance | Line |  |  | 500 kV, Affects Cranking Path
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2022-10-01 08:00 | 2022-10-07 17:00 | N | N | 635PT-1063 | Not In Model | Unmodeled Transmission Facility (Suncor) Mine Shovel 635EDD-1013 Major Maintenance |  | For Information Only
ENMAX, ALTALINK | 7.84L (SS-7 - SS-36), 36.81L (44s Bearspaw Plant - SS-36), 36.1TR (SS-36), 36.3TR (SS-36), 36B138-36BT3 (SS-36), 36B138-36.81 (SS-36), 36B138-7.84 (SS-36), 36MD138-36.1TR (SS-36), 36MD138-36.3TR (SS-36) | 2022-10-01 08:00 | 2022-10-01 18:00 | N | Y | fall substation washing and reversing switch 36.3TR checking | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p RTU/SCADA (330p Genesee) | 2022-10-01 12:00 | 2022-10-01 18:00 | N | N | communication only outage to upgrade GN3 SST3 RTU | Terminal Equipment |  | 1. Genesee Unit 3 MW/MVAR data is currently communicated by the G3 RTU to the EPCOR SCADA system, where it is then passed to the AESO EMS SCADA system. 2. Also, Genesee G3 data for Station Service Transformer SST3 is communicated to the G1/G2 RTU, which uses GT3 and SST3 MW/MVAR data values from the G3 RTU in G1/G2 Net MW calculations (which are reported to the AESO EMS as well by the G1/G2 RTU). 3. We are installing a temporary RTU during the G3 outage (October 1st to November 4th or sooner) to maintain SST3 data throughout the G3 Turnaround/outage, as we are also replacing the G3 RTU during the G3 Turnaround. 4. During the requested comms outage period from noon to 6PM on Saturday, October 1, there will be data interruptions to the SST3 and G3 MW/MVAR data to the AESO EMS. The interruptions to SST3 data will also affect the G1/G2 Net MW calculations. G3 will be offline (i.e. producing 0 MW). 5. During the requested comms outage, all G3 MW/MVAR data will not be available to EPCOR to report to the AESO EMS SCADA system. 6. Also, the loss of SST3 data validity will impact Net MW/MVAR values for G1/G2 during the comms outage. 7. Once the comms outage is over and the transfer of data from the G3 RTU to the temporary RTU is complete, the AESO should once again see valid SST3 values and the G1/G2 metering calculations will no longer be affected. | Affects Visibility
ENMAX | 14.2C (SS-14), 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 14.1C (SS-14) | 2022-10-02 08:00 | 2022-10-02 18:00 | N | N | fall substation washing and reversing switch 14.1TR checking | Line, Shunts, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 38.3TR (SS-38) | 2022-10-02 08:00 | 2022-10-06 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty) | 2022-10-03 07:00 | 2022-10-21 17:00 | N | N | LH8 pole replacement LCR | Line |  |  | Pre-Condition
EPCOR | 330p 1207 (330p Genesee), 330p 1208 (330p Genesee), 330p 1207B (330p Genesee), 330p 1208A (330p Genesee) | 2022-10-03 07:00 | 2022-10-08 17:00 | N | Y | CVT doble, TX arrestor doble, 1207B/1208A/12GT3D maintenance | Circuit Breaker, Switch |  | Genesee 1207 bay CVT doble, TX arrestor doble, 1207B/1208A/12GT3D maintenance | 500 kV, Contingency Requires Mitigation
CapitalPower | GN3 Genesee #3 | 2022-10-03 07:00 | 2022-10-24 17:00 | N | N | communication only outage | Unit |  | The plant's RTU unit will be replaced. This unit communicates SCADA to the AESO. During this event no SCADA will be sent to the AESO. | Affects Visibility
EPCOR | 987s C2405 (987s Clover Bar) | 2022-10-03 07:00 | 2022-10-04 17:00 | N | Y | Cloverbar C2405: P&C cutovers for DFR/UFLS upgrades | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 5.8TR (SS-5) | 2022-10-03 08:00 | 2022-10-03 16:00 | N | N | resample DGA LTC and replace liquid temp gauge | Transformer |  |  | For Information Only
ATCO | 809s 906 (809s Louise Creek) | 2022-10-03 09:00 | 2022-10-07 16:00 | N | Y | 809S 906 breaker maintenance | Circuit Breaker |  | 809S 906 breaker maintenance | 240 kV, Contingency Requires Mitigation
ENMAX | 32.1TR (SS-32) | 2022-10-03 10:30 | 2022-10-22 11:30 | N | N | forced outage | Transformer |  |  | For Information Only
ATCO | 917s 701T (917s Horse River), 917s 701 (917s Horse River) | 2022-10-03 10:30 | 2022-10-05 17:00 | N | N | maintenance | Transformer, Circuit Breaker |  | 701T maintenance and 701 Maintenance. 917s Load will be fed from 833s from new switch that will be installed between 25KV lines. | Pre-Condition
ATCO | 7L06 (784s Donnelly - ATC 793s West Peace River), 813s 901T (813s Little Smoky) | 2022-10-03 11:00 | 2022-10-03 17:00 | N | N | emergency: repair broken shield wire and if necessary, replace crossarm | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 808L (13s Deerland - 808AL tap), 13s 808N (13s Deerland), 13s 91 (13s Deerland), 13s 92 (13s Deerland), 13s 452 (13s Deerland), 13s 152 (13s Deerland) | 2022-10-03 11:00 | 2022-10-03 18:00 | N | N | urgent repair for a hot spot on 13s808N | Line, Switch, Circuit Breaker | 13s808N (13s Deerland 138kV motorized switch) affecting 808L (13s Deerland  808AL Tap) | Urgent repair for a hot spot on 13s808N | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-10-03 11:30 | 2022-10-06 14:30 | N | Y | cross arm replacement | Line |  | GOI Required to continue cross arm replacement project on 7L224. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
TRANSALTA, ALTALINK | 59s T1 (59s Peigan), 616L (59s Peigan - 616AL tap) | 2022-10-03 11:30 | 2022-10-05 15:30 | N | Y | maintenance, doble, leak repairs | Transformer, Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 828L (178s Cynthia - 489s Petro-Canada Brazeau River), 178s 828X (178s Cynthia) | 2022-10-03 11:30 | 2022-10-06 15:00 | N | N | 828L (L5) A&B protection upgrade | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 834L (320p Keephills - 384s Keystone), 320p 834X (320p Keephills) | 2022-10-03 12:00 | 2022-10-05 15:30 | N | N | line clearance mitigation 834L on structures 4-257 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 28s T1 (28s West Brooks) | 2022-10-03 12:00 | 2022-10-06 18:00 | N | Y | 28sT1 maintenance, doble | Transformer | 28s T1 (28s West Brooks) |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 71s 252 (71s Lamoureux) | 2022-10-03 12:30 | 2022-10-06 17:30 | N | N | replacing CTs | Circuit Breaker |  |  | Contingency Requires Mitigation
REDDEER | 247s T2 (247s Piper Creek) | 2022-10-03 15:00 | 2022-10-07 14:00 | N | N | relay maintenance testing PRC-005 | Transformer |  |  | Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2022-10-03 21:00 | 2022-10-04 15:25 | N | Y | forced outage | Shunts |  |  | Pre-Condition
ALTALINK | 807L (233s Beamer - 807AL tap), 233s 807X (233s Beamer) | 2022-10-04 07:30 | 2022-10-04 17:30 | N | N | cutover CTs and functional testing on 233s807X | Line, Circuit Breaker | Cutover CTs and functional testing on 233s807X from new B87/138B1 protection. |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 526L (519L Tap - 526AL Tap) | 2022-10-04 07:30 | 2022-10-04 17:30 | N | N | urgent insulation replacement on 526L237 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s 2652 (63s Red Deer) | 2022-10-04 08:00 | 2022-10-04 13:00 | N | Y | breaker failure and control P&C upgrade | Circuit Breaker | Request for the 2752 Breaker Failure and Control P&C Upgrade. |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 71s 761W (71s Lamoureux), 38s 761N (38s East Edmonton), 71s 552 (71s Lamoureux), 71s 652 (71s Lamoureux) | 2022-10-04 08:00 | 2022-10-04 17:00 | N | N | clean and adjust switch | Line, Switch, Circuit Breaker | Clean and adjust switch 71s761W. |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 65B138-D84 (SS-65) | 2022-10-04 08:00 | 2022-10-04 16:00 | N | N | HV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 8.4TR (SS-8) | 2022-10-04 08:00 | 2022-10-05 16:00 | N | N | tapchanger maintenance, oil sampling MT, TC. check reversing switch. relay, protective maintenance T60 and firmware upgrade 351 | Transformer |  |  | For Information Only
ALTALINK | 535s 5952 (535s Joffre) | 2022-10-04 08:30 | 2022-10-04 12:30 | N | N | 138kV breaker maintenance, repair tank heater | Circuit Breaker |  |  | Contingency Requires Mitigation, Restricts Generation
ALTALINK | 102s 6652 (102s Langdon) | 2022-10-04 08:30 | 2022-10-04 16:30 | N | Y | emergency repair | Circuit Breaker | Emergency repair: Breaker top up and fix alarming issues |  | 240 kV, Contingency Requires Mitigation
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - SS-21), 36.81L (44s Bearspaw Plant - SS-36), 44s 36.81E (44s Bearspaw Plant), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2022-10-04 09:00 | 2022-10-07 18:00 | N | Y | switch replacement, strain insulator replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 535s 5652 (535s Joffre) | 2022-10-04 12:31 | 2022-10-04 16:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition, Restricts Generation
AESO-SC | OATI | 2022-10-04 18:00 | 2022-10-04 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
ATCO | 914s 701T (914s Bindloss), 7LA760 (914s Bindloss - 7LA760 tap), 914s 701 (914s Bindloss) | 2022-10-05 06:30 | 2022-10-05 18:30 | N | N | maintenance at the Bindloss pump station & inspection of NGR at 914s | Transformer, Line, Circuit Breaker |  | TC Energy is requesting outage for 3-year electrical maintenance at the Bindloss pump station & inspection of NGR at 914s. Taken at same time as permit 2-67123. | For Information Only
ALTALINK | 63s T2 (63s Red Deer), 63s 240kV South Bus (63s Red Deer), 63s 652 (63s Red Deer), 63s 952 (63s Red Deer), 63s 352 (63s Red Deer), 63s 25 (63s Red Deer), 63s 10 (63s Red Deer) | 2022-10-05 07:30 | 2022-10-05 17:00 | N | Y | 2752 breaker failure and control P&C upgrade | Transformer, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 631L (186s Dry Creek - 199s East Airdrie), 199s 631 (199s East Airdrie) | 2022-10-05 07:30 | 2022-10-05 15:30 | N | N | functional trip test re: T1 'A' protection | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 233s 6 (233s Beamer) | 2022-10-05 07:30 | 2022-10-05 17:30 | N | N | cutover CTs and functional testing on 233s6 from new B87/138B1 & B87/138B2 protections | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
FORTIS | CLY1 Clydesdale Solar 1 DER | 2022-10-05 08:00 | 2022-10-19 16:00 | N | N | P2362, P2363 Fortis Enchant 447S DER Solar. ISD October 12, 2022 | Unit
ENMAX | 26.2TR (SS-26) | 2022-10-05 08:00 | 2022-10-14 16:00 | N | N | 26 sub cable trench replacement and remove and re-install control cables | Transformer |  |  | For Information Only
ALTALINK | 42s T2 (42s Sarcee), 42s 60 (42s Sarcee) | 2022-10-05 08:00 | 2022-10-05 16:30 | N | Y | emergency repair: IDD alarms failing to alarm ACC | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 285s T2 (285s East Camrose), 285s 1252 (285s East Camrose), 285s 3202 (285s East Camrose) | 2022-10-05 08:30 | 2022-10-05 17:00 | N | Y | inspect VT22 cell and cables for buzzing noise and double u/g cables running between s/w gear buildings, between 285s1352 & 285s1252 | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 368s Burdett | 2022-10-05 09:00 | 2022-10-07 12:00 | N | N | BRD1 - hydrovac services | Station |  | Oct 4th: - 09:00: Inverters 3-4 shutdown for Hydrovac services - Site Capacity: 6.3 MW - Reactive Capacity: 3.78 MVAr Oct 5th: - 12:00: Inverters 3-4 brought back online and Inverter 1-2 shutdown for Hydrovac services - Site Capacity: 6.3 MW - Reactive Capacity: 3.78 MVAr Oct 7th: - 12:00: Hydrovac services complete and all inverters brought back online - Site Capacity: 10.5 MW - Reactive Capacity: 7.56 MVAr | Restricts Generation
ALTALINK | 37s 81 (37s North Calder) | 2022-10-05 09:30 | 2022-10-06 17:30 | N | Y | breaker maintenance including 1st trips, fix counter | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 62s 11 (62s Brazeau Plant Plant), 62s 1 (62s Brazeau Plant Plant) | 2022-10-05 23:00 | 2022-10-06 03:00 | N | Y | maintenance | Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant Plant), 62s 2 (62s Brazeau Plant Plant) | 2022-10-06 03:00 | 2022-10-06 07:00 | N | Y | maintenance | Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 526L (515s Fed Pipe Judy Creek - 6L126 Tap), 515s 526 (515s Fed Pipe Judy Creek) | 2022-10-06 07:00 | 2022-10-07 18:00 | N | N | replace structure #477 with new structure for LCM | Line, Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 688L (199s East Airdrie - 688AL Tap), 199s 688 (199s East Airdrie) | 2022-10-06 07:30 | 2022-10-06 15:30 | N | N | functional trip test re: T1 'A' protection | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 199s C1 (199s East Ardrie) | 2022-10-06 07:30 | 2022-10-06 15:30 | N | N | functional trip test re: T1 'A' protection | Shunts |  |  | Pre-Condition
ALTALINK | 708L (233s Beamer - 708AL tap), 233s 708X (233s Beamer) | 2022-10-06 07:30 | 2022-10-06 17:30 | N | N | cutover CTs and functional testing on 233s708X from new B87/138B2 protection | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 107s Westfield, 722L (107s Westfield - 368s Burdett) | 2022-10-06 07:30 | 2022-10-06 18:00 | N | Y | switch repairs on 107s3, 107s4, 107s10 | Station, Line |  |  | Restricts Generation
ENMAX | 1.5TR (SS-1) | 2022-10-06 08:00 | 2022-10-06 10:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 35.1TR (SS-35) | 2022-10-06 08:00 | 2022-10-07 16:00 | N | N | tapchanger maintenance. oil sampling MT, TC. Filmax LTC oil filtration maintenance. Calisto maintenance | Transformer |  |  | For Information Only
ENMAX | 1.6TR (SS-1) | 2022-10-06 10:00 | 2022-10-06 12:00 | N | N | fall substation washing | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 1.7TR (SS-1) | 2022-10-06 12:00 | 2022-10-06 14:00 | N | N | fall substation washing and check reversing switch | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 1.8TR (SS-1) | 2022-10-06 14:00 | 2022-10-06 16:00 | N | N | fall substation washing and check reversing switch | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer), 233s 735N (233s Beamer) | 2022-10-07 07:30 | 2022-10-07 17:30 | N | N | cutover CTs and functional testing on 233s735N from new B87/138B2 protection | Line, Circuit Breaker | Cutover CTs and functional testing on 233s735N from new B87/138B2 protection. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34), 34.2TR (SS-34), 34B69-16.60 (SS-34), 34MD69-34.2TR (SS-34) | 2022-10-07 08:00 | 2022-10-07 12:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | SASK POWER P2C | 2022-10-07 08:00 | 2022-10-14 19:00 | N | Y | maintenance | Line | P2C Line, PRPS 1 Unit, BHWPS WIND, CWPPS Wind, GSWPS Wind Line(s) Out of Service During Outage or Part of Outage BA 801T, BD22 Line, BR 901T, C2W Line, CD 903T, ER 801T, GL 801T, P2C Line, PA2, PE 403T, PE 903T, R1P Line-PQSS TO L4, R1R Line, U91A Line, W1R Line, W3B Line, WE 801T |  | Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34), 34.1TR (SS-34), 34B69-21.61 (SS-34), 34MD69-34.1TR (SS-34) | 2022-10-07 12:00 | 2022-10-07 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L275 (799s Coleman - BCH Natal) | 2022-10-07 18:00 | 2022-10-14 20:30 | N | Y | replace 1-1, 1-2, 1-3, 4-4 and 4-5 with taller structures to resolve clearance violations for FAC-008 | Line | replace 1-1, 1-2, 1-3, 4-4 and 4-5 with taller structures to resolve clearance violations for FAC-008 BC maintenance does not affect the Alberta ATC |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 710L (56s Boyle - 159s Colinton), 56s 710X (56s Boyle) | 2022-10-08 07:00 | 2022-10-08 18:00 | N | N | replace crossarms and insulators at structure 710L225 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2022-10-08 07:15 | 2022-10-28 17:45 | N | N | rebuilding a section of 113L from structure 1 to 96 | Line | Scope of work includes rebuilding a section of 113L from structure 1 to 96 |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 20.82L (SS-20 - SS-21), 21.1TR (SS-21), 21.4TR (SS-21), 21B138-20.82 (SS-21), 21MD138-21.1TR (SS-21), 21MD138-21.4TR (SS-21) | 2022-10-08 08:00 | 2022-10-08 13:00 | N | Y | fall substation washing, check reversing switch 21.1 | Line, Transformer, Circuit Breaker, Switch | Fall Substation Washing. Check Reversing Switch 21.1. Altalink required to remove 60S100 sec. fuses |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 21.61L (SS-21 - SS-34), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21B69-21.61 (SS-21), 21B69-15.60 (SS-21), SW64 (SS-21), SW65 (SS-21) | 2022-10-08 13:00 | 2022-10-08 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1080L (SS-25 - SS-65) | 2022-10-08 16:43 | 2022-12-19 16:00 | N | Y | forced outage | Line |  |  | 240 kV
ENMAX | 21.61L (SS-21 - SS-34), 16.60L (SS-16 - SS-34), 34.1TR (SS-34), 34.2TR (SS-34), 34B69-16.60 (SS-34), 34B69-21.61 (SS-34), 21B69-21.61 (SS-21) | 2022-10-08 22:00 | 2022-10-09 05:00 | N | N | replaced lightning damaged insulators on transmission lines | Line, Transformer, Circuit Breaker | Replaced lightning damaged insulators on transmission lines. 34sub tie away |  | For Information Only, Pre-Condition
ALTALINK | 199s T2 (199s East Airdrie) | 2022-10-10 06:30 | 2022-10-13 18:00 | N | N | switch replacements (199s23, 199s22, 199s21), create open point 'A' | Transformer | Switch replacements (199s23, 199s22, 199s21). Create Open Point 'A' |  | For Information Only
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2022-10-10 08:00 | 2022-10-17 17:00 | N | Y | line mitigation, cross arm replacement | Line | Line mitigation, Cross arm replacement |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 3.4TR (SS-3) | 2022-10-10 08:00 | 2022-10-15 16:00 | N | N | ECI bushing / slip over CT replacement, oil sampling - 3.4-TC - tapchanger | Transformer |  |  | For Information Only
SUNCOR | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-2 29PT-3 (29EDD-2 Tar Island) | 2022-10-10 08:00 | 2022-10-16 18:00 | N | Y | HV bushing testing, repair and replacement | Line, Transformer | 29PT-3 HV Bushing Testing / Replacement at 29EDD-2 29PZ-1 ATS Repair or Replace at 29EDD-2 29PL6-22 protection relays- L90 and SEL 411L @ 29 EDD-1 (A and B protection relays one at a time) |  | Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap) | 2022-10-10 15:47 | 2022-10-12 17:00 | N | Y | forced outage | Line |  |  | Affects Cranking Path
EPCOR | 72CK13 (987s Clover Bar - Kennedale), K721 (Kennedale) | 2022-10-11 07:00 | 2022-10-11 17:00 | N | N | K721 - emergency investigation of possible cracking/discoloration on CT heads and doble testing | Line, Circuit Breaker | Kennedale: K721 Emergency investigation of possible cracking/discoloration on CT heads and Doble testing |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T4 (Rossdale) | 2022-10-11 07:00 | 2022-11-18 17:00 | N | N | TX4 bushing replacement (OE101863), then backfill replacement: RW3-RV2 Crossing (1007206) | Transformer |  |  | For Information Only
ALTALINK | 922L (17s Benalto - 310p Sundance), 310p 1952 (310p Sundance), 310p 2052 (310p Sundance) | 2022-10-11 07:00 | 2022-10-12 18:00 | N | Y | line strain insulator replacement @ 310P, repair 310p20B | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
EPCOR | T3 (Meadowlark), M723 (Meadowlark), M724 (Meadowlark) | 2022-10-11 07:00 | 2022-11-01 17:00 | N | N | cutover TX3 to new bus 3 switchgear | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor), 774s 701 (774s Monitor) | 2022-10-11 07:00 | 2022-10-14 17:00 | N | Y | RAS modifications for the pattern Lanfine WAGF project (P1898) | Line, Circuit Breaker |  | RAS modifications for the Pattern Lanfine WAGF project | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 12s T1 (12s Heartland) | 2022-10-11 08:00 | 2022-10-12 18:00 | N | Y | repair major oil leaks on the transformer | Transformer |  |  | 500 kV, Pre-Condition
ENMAX | 41.1TR (SS-41) | 2022-10-11 08:00 | 2022-10-13 12:00 | N | N | tapchanger maintenance, oil sampling MT, TC, 41.1TR maintenance | Transformer |  |  | For Information Only
ENMAX | 39.4TR (SS-39) | 2022-10-11 08:00 | 2022-11-01 16:00 | N | N | bushing replacement, CT replacement and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek), AML 793s 859W (AML 793s Horse Creek), 20s 859E (20s Ghost) | 2022-10-11 08:00 | 2022-10-18 18:00 | N | N | complete cutovers/end to end testing of new line protection and breaker fail, CT contribution to B bus differential | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2022-10-11 08:00 | 2022-10-12 16:30 | N | Y | disconnect 472s & MR1 from 649s 138 kV bus | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32) | 2022-10-11 08:00 | 2022-10-11 16:00 | N | N | HV breaker maintenance 32B138-32.83 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2022-10-11 09:00 | 2022-10-27 17:00 | N | Y | replace structures and timbers and PT replacement | Line | replace structures and timbers and PT replacement BC maintenance does not affect the Alberta ATC. |  | For Information Only, Limits ATC
ALTALINK | 233s T2 (233s Beamer) | 2022-10-11 09:00 | 2022-10-17 18:00 | N | N | replace 233s34, cutover T2 CTs to new B87/138B2, cutovers and functionals from new B87/138B2 to breakers 233s22, 233s43, & 233s36 and place new B87/138B2 into service. | Transformer |  |  | For Information Only
ENMAX | 38.1C (SS-38) | 2022-10-11 09:00 | 2022-10-20 16:00 | N | N | 38 sub cap bank vehicle gate | Shunts |  |  | For Information Only
TRANSALTA | 240s McBride Lake | 2022-10-11 10:00 | 2022-10-13 17:00 | N | N | substation maintenance | Station |  |  | Restricts Generation
AKE1WIND, TRANSALTA | AKE1 McBride Lake Windfarm | 2022-10-11 10:00 | 2022-10-13 17:00 | N | N | substation maintenance | Unit
ATCO | 7L90 (813s Little Smoky - 7LA90 tap) | 2022-10-11 10:00 | 2022-10-12 16:00 | N | N | set additional structure | Line |  | Additional Structure to be set | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 7L224 (650s Hansman Lake - 774s Monitor), 650s 1752 (650s Hansman Lake) | 2022-10-11 11:30 | 2022-10-13 14:30 | N | N | continue cross arm replacement project on 7L224 | Line, Circuit Breaker |  | GOI Required to continue cross arm replacement project on 7L224. | For Information Only
ALTALINK | 310p T36 (310p Sundance) | 2022-10-11 12:00 | 2022-10-13 18:00 | N | Y | T36 bushing replacement | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L02 (769s Stettler - 873s Marion Lake) | 2022-10-12 04:00 | 2022-10-14 15:00 | N | N | forced outage | Line | due to 6L02D6 failed during switching |  | For Information Only
ALTALINK, Lethbridge | 725L (674s Bowron - 725AL tap), 725L (111s Coalbanks - 725AL tap), 725AL (618s Riverbend - 725L tap), 674s 725E (674s Bowron) | 2022-10-12 06:30 | 2022-10-12 17:00 | N | Y | 725LE maintenace | Line, Circuit Breaker |  |  | Pre-Condition
Lethbridge, ALTALINK | 674s Bowron, 725BL (240s McBride Lake - 725L tap), 725L (15s Fort MacLeod - 725BL tap), 674s 725W (674s Bowron) | 2022-10-12 06:30 | 2022-10-12 17:30 | N | Y | 725LW, 725LE maintenance and 725L fire mitigation | Station, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 704L (51s Wainwright - 478s Tucuman) | 2022-10-12 07:00 | 2022-10-12 15:00 | N | N | remove guy wire and anchor rod being washed away by the river | Line | *P5* remove guy wire and anchor rod being washed away by the river |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2022-10-12 07:00 | 2022-10-30 18:00 | N | N | under-built violations and structure replacement | Line | 735L GOI is required for the under-built violations and structure replacement on structures 735L 36- 49, 51, 54-56, 60-82 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L93 (615s Halkirk - 972s Tinchebray) | 2022-10-12 07:00 | 2022-10-13 17:00 | N | Y | capital maintenance substation maintenance outage | Line | Capital Maintenance Substation maintenance outage Temporary loss of primary station service while switching 9L93 in and out of service. Station service will rely on Batteries until Standby Gen starts. |  | 240 kV, For Information Only
ALTALINK | 698s 452 (698s Jackfish) | 2022-10-12 07:30 | 2022-10-12 12:30 | N | Y | investigate trip coil 1 fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, Lethbridge | 725L (15s Fort MacLeod - 725BL tap), 725L (674s Bowron - 725BL tap), 725BL (240s McBride Lake - 725L tap) | 2022-10-12 07:30 | 2022-10-12 17:30 | N | Y | 725L fire mitigation on str 725L229 | Line |  |  | Pre-Condition, Restricts Generation
ALTALINK | 216s T3 (216s Knightsbridge), 216s 552 (216s Knightsbridge) | 2022-10-12 07:30 | 2022-10-13 17:30 | N | N | fix leaks, maintainence, & doble on 216s T3 | Transformer, Circuit Breaker |  |  | For Information Only
SUNCOR | 29PL7-3 (29EDD-65 - 29EDD-71), 29EDD-65 29PT-0236 (29EDD-65), 29EDD-71 752-4634 (29EDD-71), 29EDD-71 752-4633 (29EDD-71), 29EDD-65 29-952-4823 (29EDD-65), 29EDD-65 29-952-4822 (29EDD-65), 29EDD-71 29PS-255 (29EDD-71 Edd71Sub), 29EDD-65 29PS-0269 (29EDD-65 Edd65Sub), 29EDD-65 29PS-0272 (29EDD-65 Edd65Sub) | 2022-10-12 08:00 | 2022-10-22 18:00 | N | Y | 29PL7-3; 29EDD-65/71; 10 YEAR PM | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ATCO, ALBIAN, SHELL | 920s 901T (920s Jackpine), 847s 905 (847s Muskeg River), 920s 9LJH-1D2 (920s Jackpine) | 2022-10-12 08:00 | 2022-10-12 18:00 | N | Y | 2022 fall shutdown | Transformer, Circuit Breaker, Switch |  | 1. SF6 gas re-fill on 72kV GIS disconnect switch 532-SG-7401-A01-Q9 2. Open 72kV side cover of 920S 901T to get nameplate data of the 72kV surge arresters. This information is required for Albian Jackpine 72kV system insulation coordination study. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 39B138-22.81 (SS-39), 22B138-22.81 (SS-22) | 2022-10-12 08:00 | 2022-10-13 16:00 | N | N | bushing and CT replacement and breaker maintenance | Line, Circuit Breaker | 39.4TR ECI bushing / CT replacement and HV breaker maintenance 39B138-22.81, Power factor test HV breaker 22B138-22.81 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 65s T1 (65s High River), 65s 13N (65s High River), 392s 13 (392s Black Diamond) | 2022-10-12 08:00 | 2022-10-12 16:00 | N | N | complete the wiring/commissioning for the Tx CT contribution to the new undervoltage protection | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L128 (802s Michichi Creek - 963s Coyote Lake) | 2022-10-12 08:00 | 2022-10-12 14:48 | N | N | forced outage | Line | switch 7L128D3 damaged due to a fire
ENMAX | 5.6TR (SS-5) | 2022-10-12 08:00 | 2022-10-12 16:00 | N | N | update settings 5.6TR-351 | Transformer |  |  | For Information Only
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22BT8 (SS-22), 22B138-22.81 (SS-22), SW85 (SS-22) | 2022-10-12 10:00 | 2022-10-12 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2022-10-12 11:00 | 2022-10-12 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 121s 831N (121s Brooks), 121s 814W (121s Brooks) | 2022-10-12 17:00 | 2022-11-01 17:00 | N | N | temporary bypass to be built between 814L & 831L to feed radial load at 227s & 339s for duration of 121s 138 kV North Bus & T5 outage | Circuit Breaker | 814L and 831L will be de energized from 121s via switches 121s57 & 121s54. Temporary Bypass to be built between 814L & 831L to feed radial load at 227s & 339s for duration of ref 275356 121s 138kV North Bus & T5(18407) GOI. No generation impacts |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s 138 kV North Bus (121s Brooks), 121s T5 (121s Brooks), 121s 37 (121s Brooks), 121s 1052 (121s Brooks), 121s 831N (121s Brooks), 121s 814W (121s Brooks) | 2022-10-12 17:00 | 2022-11-01 07:45 | N | N | upgrade / migrate 'A87' & 'B87' 138N bus protection and 831L, 814L and T5 protections | Bus, Transformer, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
SUNCOR | 29EDD-3 29PT-5 (29EDD-3), 29EDD-3 29Edd-3 | 2022-10-13 06:00 | 2022-10-20 18:00 | N | Y | transformer protection setting changes | Transformer, Station | Transformer protection setting changes Outage will follow the generator RDT reported dates |  | 240 kV, For Information Only, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 665s D2403 (665s Dome), 310p 1352 (310p Sundance), 310p 1452 (310p Sundance), 665s DDS14 (665s Dome) | 2022-10-13 07:00 | 2022-10-18 17:00 | N | Y | doble and breaker maintenance | Line, Circuit Breaker, Switch | Dome D2403 Bay Doble and Breaker Maintenance, 909LW CT/Arrestor Doble |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 973L (39s Bickerdike - 310p Sundance), 310p 2252 (310p Sundance), 310p 2352 (310p Sundance) | 2022-10-13 07:00 | 2022-10-13 17:00 | N | N | line strain insulator replacement | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 610L (83s Taber - 336s Fincastle), 83s 610 (83s Taber), 336s 610 (336s Fincastle) | 2022-10-13 07:15 | 2022-10-14 17:45 | N | Y | disconnect and remove smart wires power flow controller | Line, Circuit Breaker | Outage to disconnect and remove smart wires power flow controller at 336s (AESO Smart Wire Project) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 127s T1 (127s Bruderheim) | 2022-10-13 07:30 | 2022-10-13 16:30 | N | N | replace H1 bushing | Transformer |  |  | For Information Only
ENMAX | 41.2TR (SS-41) | 2022-10-13 08:00 | 2022-10-14 16:00 | N | N | tapchanger maintenance | Transformer | Tapchanger maintenance. Check Reversing Switch. Oil Sampling MT, TC. Filmax LTC Oil Filtration Maintenance. 41.2TR LTC Low Temp Cut Off Switch Replacement. 41.2TR LTC controls - relay #3 sticks a bit. |  | For Information Only
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain) | 2022-10-13 08:00 | 2022-10-17 16:00 | N | Y | pole changes | Line |  | Pole Changes | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 391s 138kV Bus (391s Balzac), 611L (186s Dry Creek - 391S Balzac), 391s T1 (391s Balzac), 391s 25 (391s Balzac), 391s 30 (391s Balzac), 391s 611 (391s Balzac), 391s 16 (391s Balzac), 391s 17 (391s Balzac) | 2022-10-13 08:00 | 2022-10-14 20:30 | N | N | replace manual switch, grading capacitor and switch maintenance | Bus, Line, Transformer, Circuit Breaker, Switch | 1st) Replace 391s17 manual switch (REG) & Replace 6 grading capacitor on 391s30 minimum oil breaker 2nd)Switch maintenance on 391s16, 391s18, 391s23 (AML) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation,
BCH | BCH Line Creek, 1L274 (BCH Line Creek - BCH Line Creek tap), 60-80-02 (BCH Line Creek), 60-80-03 (BCH Line Creek), 60-80-05 (BCH Line Creek) | 2022-10-13 09:00 | 2022-10-13 13:00 | N | N | replacing entrance disconnect, CB, SA, transformer and entrance protection | Station, Line, Switch | LCC is replacing its entrance disconnect, CB, SA, transformer and entrance protection |  | For Information Only, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2022-10-13 09:00 | 2022-10-13 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 39.82L (SS-39 - SS-162), 162B138-RB82 (SS-162), 162B138-RB83 (SS-162), 39B138-39.82 (SS-39) | 2022-10-13 21:00 | 2022-10-14 06:00 | N | N | 138 kV DFR installation | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 812AL (512s Hartell - 812L tap), 812L (392s Black Diamond - 812AL tap), 812L (65s High River - 812AL tap), 512s 812AL (512s Hartell) | 2022-10-14 07:00 | 2022-10-15 18:00 | N | N | replace cross arms and insulators at structures 201 & 237 | Line, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 63s 138kV South Bus (63s Red Deer), 427L (63s Red Deer - 247s Piper Creek), 648L (63s Red Deer - 580s Sylvan Lake), 63s T2 (63s Red Deer), 63s T4 (63s Red Deer), 63s 427 (63s Red Deer), 63s 51 (63s Red Deer), 63s 648 (63s Red Deer) | 2022-10-14 07:00 | 2022-10-14 18:00 | N | Y | complete salvage and demo work to remove 63s22, 63s80x, and 63s16 | Bus, Line, Transformer, Circuit Breaker |  | Complete salvage and demo work to remove 63s22, 63s80x, and 63s16. Removing / Disconnecting 63s22 creates open point releasing 63s80x and 63s16 for salvage. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 820L (254s Coaldale - 820AL tap), 820L (67s Stirling - 820AL tap), 820AL (315s Chin Chute - 820L tap) | 2022-10-14 07:00 | 2022-10-17 18:00 | N | Y | install inline switches and T-tap structures for completion of 820BL (structures #451 & 452) | Line |  | Installing inline switches and T-tap structures for completion of newly built 820BL (Structures #451 & 452) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ENMAX | 26.83L (SS-26 - SS-65), 26.2TR (SS-26), 26B138-26.83 (SS-26), 26B138-26BT3 (SS-26), 26MD138-26.2TR (SS-26) | 2022-10-14 08:00 | 2022-10-14 16:00 | N | N | cable trench replacement and commission control cables | Line, Transformer, Circuit Breaker, Switch |  | 26 sub cable trench replacement. Commission control cables. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33MD138-33.2TR (SS-33), 33B138-33.84 (SS-33), SW84 (SS-33), SW85 (SS-33), SW86 (SS-33), SW86 (SS-43) | 2022-10-15 08:00 | 2022-10-15 14:00 | N | N | fall substation washing | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33), SW81 (SS-33), SW81 (SS-41) | 2022-10-15 14:00 | 2022-10-15 18:00 | N | N | fall substation washing | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 199s T1 (199s East Airdrie) | 2022-10-17 06:30 | 2022-10-24 13:00 | N | N | switch replacements | Transformer | Switch replacements (199s4, 199s7, 199s16) |  | For Information Only
EPCOR | 330p 1207 (330p Genesee), 330p 1208 (330p Genesee), 330p 1208A (330p Genesee), 330p 1207B (330p Genesee) | 2022-10-17 07:00 | 2022-10-18 17:00 | N | Y | protection commissioning and operations checks | Circuit Breaker, Switch | 1207 and 1208 Bays (G3) @ Genesee 330P Genesee (CPC Request): CPC Protection Commissioning and Op Checks on 1207/1208 w/Epcor Operations Assistance |  | 500 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 24.83L (74s Janet - SS-24), 74s T2 (74s Janet), 74s 138kV South Bus (74s Janet), 74s 23.80W (74s Janet), 74s 24.83X (74s Janet), 74s 76 (74s Janet) | 2022-10-17 07:00 | 2022-10-18 17:00 | N | Y | replacing breaker 74s23.80 | Line, Transformer, Bus, Circuit Breaker | Replacing Breaker 74s23.80 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 511s SVC Plus (AML 511s Crossings) | 2022-10-17 07:30 | 2022-10-19 12:55 | N | Y | SVC plus VCS maintenance, fence repair on reactors and IGBT Inspection | Shunts | SVC Plus VCS maintenance, fence repair on Reactors and IGBT Inspection. |  | 240 kV, Pre-Condition
ALTALINK | 294s T1 (294s Brazeau Outlet Works), 294s 36 (294s Brazeau Outlet Works) | 2022-10-17 08:00 | 2022-10-21 18:00 | N | N | replace PTs, revenue meter, protection and maintenance | Transformer, Switch | Replace 294s38 existing 2 PTs with 3 new PTs and replace the revenue meter. Replace T1 protection. T1 maintenance, fix leaks,and replace 25kV bushings. |  | For Information Only
ENMAX | 20.1TR (SS-20) | 2022-10-17 08:00 | 2022-10-18 16:00 | N | N | tapchanger maintenance, oil sampling MT, TC | Transformer |  |  | For Information Only
ENMAX | 9.2TR (SS-9) | 2022-10-17 08:00 | 2022-10-20 16:00 | N | N | 9.2TR PT replacement, oil sampling - 9.2TR - HV bushings, investigate & repair 9.2TR drag hand reset button | Transformer | 9.2TR PT Replacement. Oil Sampling - 9.2TR - HV Bushings. Investigate & Repair 9.2TR Drag Hand Reset Button |  | For Information Only
ATCO | 833s 701T (833s Mariana), 833s 701TCS (833s Mariana), 833s 301 (833s Mariana) | 2022-10-17 08:00 | 2022-10-21 17:30 | N | N | close the new tie switch to back feed the 25KV from 917s Horse River | Transformer, Switch, Circuit Breaker | We are going to close the new tie switch to back feed the 25KV from 917s Horse river and off load the 4160 |  | For Information Only
ENMAX | 26.1TR (SS-26) | 2022-10-17 08:00 | 2022-10-25 16:00 | N | N | 26 sub cable trench replacement, remove and re-install control cables | Transformer |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2022-10-17 08:00 | 2022-10-17 16:00 | N | N | update settings 5.10TR-351 | Transformer |  |  | For Information Only
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13B69-13.60 (SS-13), 27B69-13.60 (SS-27) | 2022-10-17 08:00 | 2022-11-11 16:00 | N | N | bushing replacement, HV breaker maintenance, oil sampling | Line, Transformer, Circuit Breaker | 13.4TR HV & MV Bushing Repalcement. One hour soak required on return. HV Breaker maintenance 27B69-13.60. 13.4TR MD & SW -Retrieve Nameplate Info. Oil Sampling MT |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2022-10-17 09:00 | 2022-10-27 18:00 | N | Y | damper replacements | Line | Damper replacement between Structures #32-243 & 368-389 |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville), 395s 77E (395s North Holden), 709s 704 (709s Vegreville) | 2022-10-17 11:00 | 2022-10-21 15:00 | N | Y |  | Line, Circuit Breaker | GOI required on 7L77 for cross arm and insulator replacement. |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 866s T1 (866s Sundance Make-Up) | 2022-10-17 12:30 | 2022-10-20 15:30 | N | N | re-gasket leaking lid and change broken fan | Transformer |  |  | For Information Only
ALTALINK | 72s T1 (72s Leismer) | 2022-10-18 06:30 | 2022-10-20 18:00 | N | Y | bushing replacement, doble, maintenance | Transformer | 25kV bushing replacement, 72sT1 doble, 72sT1 maint, 72sT1 SFRA&LR and 72sT1 manhole leak |  | 240 kV
ALTALINK | 233s T1 (233s Beamer) | 2022-10-18 07:00 | 2022-10-24 18:00 | N | N | cutover T1 CTs to new B87/138B1 | Transformer | cutover T1 CTs to new B87/138B1. cutovers and functionals from new B87/138B1 to breakers 233s21, 233s40, & 233s35. place new B87/138B1 into service. |  | For Information Only
ALTALINK | 324s 1152 (324s Cassils) | 2022-10-18 08:00 | 2022-10-18 16:30 | N | Y | repair gas gauge | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 862s 701T (862s South Bezanson) | 2022-10-18 08:00 | 2022-11-22 17:00 | N | N | 862S substation rebuild project | Transformer |  | 862S S. Bezanson Substation Rebuild Project, Replace 701T, remove 501VR and 501TD1 Mobile substation 902s installed to carry load | For Information Only
ENMAX | 11.81L (SS-11 - SS-13), 13.82L (SS-13 - SS-22), 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13.2TR (SS-13), 11B138-11.81 (SS-11), 13B138-13.82 (SS-13), 13B69-13.60 (SS-13), 13B138-11.81 (SS-13), 13MD138-13.2TR (SS-13) | 2022-10-18 08:00 | 2022-10-18 18:00 | N | N | 13.4TR HV & MV bushing repalcement. | Line, Transformer, Circuit Breaker, Switch | 13.4TR HV & MV Bushing Repalcement. One hour soak required on return. HV Breaker maintenance 27B69-13.60. 13.4TR MD & SW -Retrieve Nameplate Info. Oil Sampling MT |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson), 811s 710 (811s Clairmont Lake), 7L32D3 (862s South Bezanson) | 2022-10-18 08:00 | 2022-10-18 17:00 | N | Y | 862S S. Bezanson substation rebuild project | Line, Circuit Breaker, Switch | 862S S. Bezanson Substation Rebuild Project, Disconnect and remove 7L32PT3, tap up mobile 902s |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 740s 701T (740s H.R.Milner), 740s 701 (740s H.R. Milner), 740s 701B (740s H.R. Milner) | 2022-10-18 09:00 | 2022-11-04 17:00 | N | Y | switch install | Transformer, Circuit Breaker, Switch | Outage in coordination with a plant outage. install a switch on Maxim power side of the fence. |  | Restricts Generation
ALTALINK | 44s T1 (44s Bearspaw Plant) | 2022-10-18 10:00 | 2022-10-29 17:00 | N | N | salvage and replace components | Transformer | VR1 replace, 44s44 SS replace, 44sT1 LA's high and low, 44sPT1 salvage,44s LA salvage between 44s43 & 44s25, 44s43, 44s25, 44s42, 44s24 salvage |  | For Information Only
ALTALINK | 434L (65s High River - 237s Foothills), 65s 434 (65s High River) | 2022-10-18 10:00 | 2022-10-18 16:00 | N | N | Install, wire and commission a maintenance switch for breaker 1152 | Line, Circuit Breaker | Install, wire and commission a maintenance switch for breaker 1152. Wire breaker status and maintenance switch to the 77/DER relay and commission the circuits |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen), 959s 702 (959s Lanfine), 959s 703 (959s Lanfine) | 2022-10-18 10:00 | 2022-10-19 17:30 | N | N | 767s 701 status wiring, relay settings updates | Line, Circuit Breaker | 767s 701 status wiring to 87L-21A/7L132 & 21B/7L132 for Pattern Lanfine project. Relay settings updates on 87L-21A/7L132 & 21B/7L132 at 767s and 87L-21A/7L132 & 21B/7L132 at 959s. End-to-end testing to confirm new points. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L23 (796s Nipisi - 858s Narrows Creek), 7L23 (732s Mitsue - 858s Narrows Creek) | 2022-10-18 11:00 | 2022-10-18 16:00 | N | N | outage to escort high load under crossing 7L23-305 near the Hwy 754 & Hwy 88 Junction | Line | outage to escort high load under crossing 7L23-305 near the Hwy 754 & Hwy 88 Junction |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 74s 23.80W (74s Janet), 23B138-23.80 (SS-23) | 2022-10-18 17:00 | 2022-10-27 17:00 | N | Y | Replacing Breaker 74s23.80 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 349s 10 (349s Stavely) | 2022-10-19 08:00 | 2022-10-19 16:30 | N | Y | install single phase PT with wildlife cover up, add new junction box and PT distribution module, install new line protection relay | Circuit Breaker | Install single phase PT with wildlife cover up, add a new junction box and PT distribution module. Install new line protection relay. Created a record for transmission constraint under generation de-rate. |  | Pre-Condition, Restricts Generation
ATCO | 939s 240kV Bus 900BS2 (939s Livock), 939s 240kV Bus 900BS3 (939s Livock), 9L10 (876s Brintnell - 939s Livock), 939s 903T (939s Livock), 939s 910 (939s Livock), 939s 911 (939s Livock), 939s 912 (939s Livock) | 2022-10-19 08:00 | 2022-10-25 17:00 | N | Y | Livock Pile Heaving Project - connect bypass to 900BS3 and 900BS2, create open jumper J1 between 900BS3 and 900D1, update relay settings | Bus, Line, Transformer, Circuit Breaker | Livock Pile Heaving Project - Connect bypass to 900BS3 and 900BS2 Create open jumper J1 between 900BS3 and 900D1 Update relay settings too |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson), 7L32D2 (862s South Bezanson) | 2022-10-19 08:00 | 2022-10-19 17:00 | N | Y | 862s S. Bezanson substation rebuild project - disconnect and remove 7L32PT2 | Line, Switch | 862S S. Bezanson Substation Rebuild Project, Disconnect and remove 7L32PT2 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
FORTIS | CLY2 Clydesdale 2 Solar DER | 2022-10-19 08:00 | 2022-11-02 16:00 | N | N | P2364, Fortis Enchant 447S DER Solar. ISD October 26, 2022 P2365, Fortis Enchant 447S DER Solar. ISD October 26, 2022 | Unit
ENMAX | 38.83L (SS-38 - SS-39), 39B138-38.83 (SS-39) | 2022-10-19 08:00 | 2022-10-19 16:00 | N | N | 39B138-38.83 SF6 gas sample - baseline | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.3TR (SS-22) | 2022-10-19 08:00 | 2022-10-20 16:00 | N | N | tapchanger maintenance, gas relay testing | Transformer |  |  | For Information Only
ENMAX | 3.82L (SS-3 - SS-8) | 2022-10-19 08:00 | 2022-10-28 18:00 | N | N | installing storm drain | Line | The City of Calgary installing storm drain |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 786L (799s Coleman - BCH Natal) | 2022-10-19 08:00 | 2022-10-19 17:00 | N | Y | open 786L breakers for testing of RAS equipment at 799s-103s | Line | WebOMS ID: 12555566 Open 786L breakers for testing of RAS equipment at 799s-103s. Work is coordinated with BC Hydro 786/1L275 outage. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO, ALBIAN, SHELL | 920s 901T (920s Jackpine), 847s 905 (847s Muskeg River), 920s 9LJH-1D2 (920s Jackpine) | 2022-10-19 08:00 | 2022-10-19 18:00 | N | Y | SF6 gas re-fill on 72kV GIS disconnect switch 532-SG-7401-A01-Q9 | Transformer, Circuit Breaker, Switch |  | CNRL Albian Sands - Request for a Condition guarantee from ATCO; Scope: SF6 gas re-fill on 72kV GIS disconnect switch 532-SG-7401-A01-Q9, Open 72kV side cover of 920S 901T to get nameplate data of the 72kV surge arresters. This information is required for Albian Jackpine 72kV system insulation coordination study. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 680L (478s Tucuman - 574s Nilrem), 478s 680 (478s Tucuman) | 2022-10-19 08:30 | 2022-10-19 17:00 | N | N | replace tank heater | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 753L (65s High River - 253s Blackie), 65s 753E (65s High River) | 2022-10-19 10:00 | 2022-10-19 16:00 | N | Y | install, wire and commission a maintenance switch for breaker 852 | Line, Circuit Breaker | Install, wire and commission a maintenance switch for breaker 852. Wire breaker status and maintenance switch to the 77/DER relay and commission the circuits |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 370s 1552 (370s North Lethbridge) | 2022-10-19 12:00 | 2022-10-19 14:00 | N | N | trip test 1552 breaker from new C60 module, move trips from 1552 C60 to new breaker | Circuit Breaker | Trip test 1552 breaker from new C60 module. Move trips from 1552 C60 to new breaker |  | Contingency Requires Mitigation
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge), 370s 770E (370s North Lethbridge) | 2022-10-19 14:00 | 2022-10-19 16:00 | N | N | trip test 752 breaker from new C60 module, move trips from 752 C60 to new breaker | Line, Circuit Breaker |  |  | Pre-Condition
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell) | 2022-10-20 06:15 | 2022-10-20 17:45 | N | Y | emergency interphase spacer repair | Line | Emergency Repair; repair the Interphase spacer between structure 99-100 |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), AML 511s 1489 (AML 511s Crossings), 510s 4289 (510s Sunnybrook) | 2022-10-20 07:00 | 2022-10-21 17:00 | N | Y | urgent repair on structure 57 | Line, Switch | Urgent repair required on structure 57 due to farm equipment damage |  | 500 kV, Pre-Condition
ALTALINK | 671L (39s Bickerdike - 58s Edson), 58s 671 (58s Edson) | 2022-10-20 08:00 | 2022-10-20 17:00 | N | N | completion of high-load move between str 131 - 132 | Line, Circuit Breaker | GOI required for completion of high-load move Between str 131 - 132. |  | For Information Only, Pre-Condition
Lethbridge, ALTALINK | 172L (181s Chinook - 370s North Lethbridge), 370s 175 (370s North Lethbridge), 181s 172L (181s Chinook) | 2022-10-20 08:00 | 2022-10-20 10:00 | N | Y | trip test breaker 552 | Line, Circuit Breaker | Trip test 552 breaker from new C60 module. Move trips from 552 C60 to new breaker |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ENMAX | 13.1TR (SS-13) | 2022-10-20 08:00 | 2022-10-21 16:00 | N | N | power factor test transformer | Transformer |  |  | For Information Only
ENMAX | 162B138-RB83 (SS-162) | 2022-10-20 08:00 | 2022-10-20 16:00 | N | N | 138kV DFR installation | Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
ENMAX | 21.1TR (SS-21) | 2022-10-20 08:00 | 2022-10-20 12:00 | N | N | oil sampling MT, TC, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 1.83L (SS-1 - SS-8), 3A10 (SS-8), 4A1 (SS-8), 3A01 (SS-8) | 2022-10-20 08:00 | 2022-10-21 16:00 | N | N | relay lockout and protection testing | Line, Switch | 8sub. Relay, Lockout Testing. 86BFI 1.83L/3a0&4a0, 86BF-3a0, 86BF-4a0. Relay, Protection Testing -86-1.83, 8RLY138-3A0-BKRFAIL, 8RLY138-4A0-BKRFAIL |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 325s 1552 (325s Leduc), 325s C1 (325s Leduc) | 2022-10-20 08:30 | 2022-10-20 16:30 | N | N | PRC 5 maintenance SF6 gas breaker | Circuit Breaker, Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 679L (478s Tucuman - 574s Nilrem), 478s 679 (478s Tucuman), 574s 679 (574s Nilrem) | 2022-10-20 08:30 | 2022-10-20 15:30 | N | N | tank heater replacement | Line, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 727L (65s High River - 727AL tap), 65s 727N (65s High River) | 2022-10-20 10:00 | 2022-10-20 16:00 | N | N | install, wire and commission a maintenance switch for breaker 752 | Line, Circuit Breaker | Install, wire and commission a maintenance switch for breaker 752. Wire breaker status and maintenance switch to the 77/DER relay and commission the circuits Change Ratio of line PT at 65s for sync check updates. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge), 370s 207X (370s North Lethbridge), 111s 207L (111s Coalbanks) | 2022-10-20 10:00 | 2022-10-20 12:00 | N | Y | trip test 652 breaker | Line, Circuit Breaker | Trip test 652 breaker from new C60 module. Move trips from 652 C60 to new breaker |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 370s T3 (370s North Lethbridge), 370s 2152 (370s North Lethbridge) | 2022-10-20 12:00 | 2022-10-20 14:00 | N | Y | trip test breaker | Transformer, Circuit Breaker |  | Trip test 2152 breaker from new C60 module. Move trips from 2152 C60 to new breaker | 240 kV, Overload, Pre-Condition
ENMAX | 21.2TR (SS-21) | 2022-10-20 12:00 | 2022-10-20 16:00 | N | N | oil sampling MT, TC | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 419s 765 (419s Chestermere), 151s 765W (151s Strathmore) | 2022-10-21 06:15 | 2022-10-21 17:45 | N | Y | emergency repair; for conductor on the top right phase at structure 296 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 38s 138kV Bus 1 (38s East Edmonton), 38s T1 (38s East Edmonton), 736L (38s East Edmonton - 293s Bernese), 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 865L (38s East Edmonton - 216s Knightsbridge), 38s 4152 (38s East Edmonton), 38s 737N (38s East Edmonton), 38s 865N (38s East Edmonton), 38s 736E (38s East Edmonton), 38s 73 (38s East Edmonton), 38s 62 (38s East Edmonton), 293s 152 (293s Bernese), 293s 252 (293s Bernese) | 2022-10-22 07:00 | 2022-10-22 19:00 | N | Y | replace insulators on 138kV Bus 1, replace switches 38s93 & 38s94, replace CTs @ 38s736E | Bus, Transformer, Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635PL7-1002 (635EDD-1000 - 635EDD-1004) | 2022-10-22 08:00 | 2022-10-23 20:00 | N | N | line outage to support construction activity in the area | Line |  |  | For Information Only
ENMAX | 14.83L (SS-14 - SS-36), 14.4TR (SS-14), 14.2TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14MD138-14.4TR (SS-14), 14MD138-14.2TR (SS-14), SW84 (SS-14), SW87 (SS-14), 14B138-14.83 (SS-14) | 2022-10-22 08:00 | 2022-10-22 16:00 | N | N | power factor test 14PT138-Z31, Oil Sampling 14.2-TC, MT | Line, Transformer, Shunts, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook), 330p 1201 (330p Genesee), 330p 1202 (330p Genesee) | 2022-10-23 07:00 | 2022-10-23 17:00 | N | Y | urgent-investigate leaking CVT | Line, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, ENMAXGPI | 607L (336s Fincastle - 607AL tap), 607L (135s Conrad - 607AL tap), 607AL (134s Taber Wind Farm - 607L tap), 134s Taber Wind Farm, 135s Conrad | 2022-10-23 09:00 | 2022-10-23 17:00 | N | Y | line maintenance (Str 99) | Line, Station |  |  | Pre-Condition, Restricts Generation
ALTALINK | 607L (135s Conrad - 607AL tap), 135s Conrad | 2022-10-23 17:01 | 2022-10-29 17:00 | N | Y | line maintenance (Str 182 ~ 223) | Line, Station |  |  | Pre-Condition, Restricts Generation
EPCOR | 72NW15 (Namao - Woodcroft) | 2022-10-24 07:00 | 2022-10-27 17:00 | N | N | N726 outage: omicron training | Line |  |  | For Information Only
EPCOR | 1058L (657s Summerside - EP 803s Lambton) | 2022-10-24 07:00 | 2022-10-29 17:00 | N | Y | steel structure refurbishment | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47.2TR (SS-47), 47MD138-47.2TR (SS-47), 47B138-BT3 (SS-47), 47B138-771 (SS-47) | 2022-10-24 07:00 | 2022-11-04 16:00 | N | N | 47 sub cable trench replacement | Transformer, Switch, Circuit Breaker |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2022-10-24 08:00 | 2022-10-24 16:00 | N | N | fit testing spare breaker | Transformer |  |  | For Information Only
ALTALINK | 63s 652 (63s Red Deer) | 2022-10-24 08:00 | 2022-11-04 13:00 | N | Y | 652 breaker failure and control P&C upgrade | Circuit Breaker | 652 GOI Request for the 652 Breaker Failure and Control P&C Upgrade. |  | 240 kV, Contingency Requires Mitigation
ATCO | 813s 711 (813s Little Smoky) | 2022-10-24 08:00 | 2022-11-01 07:59 | N | N | complete new wiring and demo existing wiring/cabling | Circuit Breaker | 813S Little Smoky Rebuild Complete 7L01 wiring panel 7P3, 711 CT/PT/P&C wiring. Demo existing wiring/cabling, remove old panel 8G Relay programming and functionality Commission control, alarms and status |  | Contingency Requires Mitigation
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2022-10-24 08:00 | 2022-10-31 17:00 | N | Y | line mitigation, cross arm replacement | Line | Line mitigation, Cross arm replacement |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12), 12B138-832L (SS-12), 10B138-832 (SS-10), 12MD138-12.1TR (SS-12), SW84 (SS-12) | 2022-10-24 08:00 | 2022-10-25 16:00 | N | Y | install repaired radiator on 12.1TR | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
SUNCOR | 29EDD-1 29EDD1s1552 (29EDD-1 Millennium) | 2022-10-24 08:00 | 2022-11-03 20:00 | N | N | breaker replacement | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 1.85L (SS-1 - SS-8), 1A10 (SS-8), 2A1 (SS-8), 1A01 (SS-8) | 2022-10-24 08:00 | 2022-10-25 16:00 | N | N | 8 sub. relay, lockout testing | Line, Switch | 8sub. Relay, Lockout Testing. 86BFI 1.85L/1a0&2a0, 86BF-2a0. Relay, Protection Testing -86-1.85, 8RLY138-2A0-BKRFAIL |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 7L65 (709s Vegreville - 710s Vermilion), 709s 703 (709s Vegreville), 710s 703 (710s Vermilion) | 2022-10-24 08:00 | 2022-11-04 17:00 | N | N | connect new 7LA65 T-tap | Line, Circuit Breaker | Grizzly Bear Wind 7LA65 T-Tap Project connect new 7LA65 T-tap Cutover and commission Protection/SCADA/Telecom at 708S (ENEL), 709S, 710S |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
Syncrude | Mildred T5 (Syncrude Mildred Lake), 5235 (Syncrude Mildred Lake), 535 (Syncrude Mildred Lake) | 2022-10-24 08:00 | 2022-11-06 20:00 | N | Y | maintenance and repairs | Transformer, Circuit Breaker | Non-Significant Outage: T5 isolatin in Plant 31 to perform maintenance and repairs. The following breakers will be operated: 5235 @ Plant 31 Substation 535 @ Plant 31 Substation The following disconnect switches will be operated: 534 @ Plant 31 Substation The following transformers will be isolated: T5 @ Plant 31 Substation The following generators will be islanded: G5 @ Plant 31 Substation |  | Restricts Generation
BHE | 719s Rattlesnake Ridge | 2022-10-24 09:00 | 2022-10-24 11:00 | N | N | software update | Station | Software update to the wind turbine SCADA will be performed with an expected upload time of 40 minutes. During this time generation will be limited to 0 MW and AESO will not have access to setpoint control. Once the upload is complete the wind farm will be returned to normal operation.Turbines will remain energized but production will be limited to 0MW. |  | Restricts Generation
ALTALINK, ENMAX | 44s Bearspaw Plant, 50L (44s Bearspaw Plant - SS-21), 860L (44s Bearspaw Plant - 291s Cochrane), 36.81L (44s Bearspaw Plant - SS-36), 44s T1 (44s Bearspaw Plant), 44s T2 (44s Bearspaw Plant), 291s 860 (291s Cochrane), 44s 31 (44s Bearspaw Plant), 44s 32 (44s Bearspaw Plant), 44s 33 (44s Bearspaw Plant), 44s 41 (44s Bearspaw Plant) | 2022-10-24 09:00 | 2022-10-29 18:00 | N | Y | 44s34 switch replacement, 860L strain insulator replacement, 860L VSR salvage, 44s35 adjust, 44s860w current sensing fail | Station, Line, Transformer, Circuit Breaker, Switch | 44s34 switch replace, 860L strain insulator replacement, 860L VSR salvage, 44s35 adjust, 44s860w current sensing fail |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 700s 705C (700s Bonnyville) | 2022-10-24 10:00 | 2022-10-28 17:00 | N | N | cap bank replacement | Shunts | 700s 705C cap bank replacement. |  | Pre-Condition
REDDEER | 247s T1 (247s Piper Creek) | 2022-10-24 10:00 | 2022-11-18 21:40 | N | N | relay maintenance testing PRC-005 and transformer LTC maintenance and bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 202L (178s Cynthia - 202AL tap), 178s 202X (178s Cynthia) | 2022-10-24 11:30 | 2022-10-27 15:30 | N | N | protection upgrade | Line, Circuit Breaker | 202L (L2) A&B protection upgrade |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 37s T5 (37s North Calder) | 2022-10-24 12:00 | 2022-11-01 18:00 | N | N | fix leaks, maintain, & doble T5 | Transformer | Fix leaks, maintain, & Doble T5 |  | For Information Only
ATCO | 720s 901T (720s Wabasca), 720s 502R (720s Wabasca), 720s 504R (720s Wabasca) | 2022-10-24 12:00 | 2023-01-16 17:00 | N | Y | perform breaker maintenance, wire in new contacts and test 901TD operation | Transformer, Shunts | 720S Wabasca 901T Replacement, Load transferred to 902T Will need to call down CNRL DG Prior to tying feeders together Nov. 7 expand GOI to include breaker 901, Isolation points will be 901B and 900D1 Nov. 10 contract GOI back to 901TD Scope for this work is to perform breaker maintenance, wire in new contacts, test 901TD operation. |  | 240 kV, Pre-Condition
ALTALINK | 349s 14 (349s Stavely) | 2022-10-24 12:00 | 2022-10-27 16:30 | N | N | 25 kV breaker - install single phase PT with wildlife cover up, add a new junction box and PT distribution module, install new line protection relay | Circuit Breaker | Install single phase PT with wildlife cover up, add a new junction box and PT distribution module. Install new line protection relay |  | For Information Only, Pre-Condition
ATCO | 7L132 (767s Oyen - 959s Lanfine) | 2022-10-24 12:00 | 2022-10-24 17:00 | N | N | install new structure, run conductor and tap up mobile sub | Line |  | Install New structure, run conductor and tap up mobile sub. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 62s T4 (62s Brazeau Plant) | 2022-10-24 12:00 | 2022-10-27 18:00 | N | N | replace bushings on T4 | Transformer | Replace 62s Brazeau 25kV & 138kV Bushings on T4 |  | For Information Only
ALTALINK | 199s T2 (199s East Airdrie) | 2022-10-24 13:00 | 2022-10-24 17:30 | N | N | close open point A | Transformer |  |  | For Information Only
ATCO | 939s 901T (939s Livock), 939s 240kV Bus 900BS1 (939s Livock), 939s 144kV Bus 700BS1 (939s Livock), 7L125 (939s Livock - 950s Germain), 939s 701 (939s Livock), 939s 701TD (939s Livock), 939s 901 (939s Livock), 939s 901TD (939s Livock), 939s 904 (939s Livock) | 2022-10-24 16:00 | 2022-12-19 17:00 | N | Y | Livock pile heaving project | Transformer, Bus, Line, Switch, Circuit Breaker | Livock Pile Heaving Project - Outage on 901T, 900BS1, and 700BS1 Note 950S Germain OOS, temp 25kV generation will be required to supply 25 kV load |  | 240 kV, Pre-Condition
ATCO | 950s 701T (950s Germain), 950s 701 (950s Germain) | 2022-10-24 17:00 | 2022-12-19 14:29 | N | N | transformer maintenance | Transformer, Circuit Breaker | 950s Will be out of service due to the outage at 939s, GOI 2-64806. Temp station service will be set up. 701T O&M to take place in coordination |  | For Information Only, Pre-Condition
ALTALINK | 368s Burdett | 2022-10-25 07:00 | 2022-10-25 17:00 | N | N | customer switch maintenance and testing | Station | Outage to perform maintenance tasks and testing of switches 89-M-M1-1 and 89-M-M1-2 |  | Restricts Generation
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2022-10-25 07:00 | 2022-10-27 18:00 | N | N | urgent repair is to replace STR B with a new structure and salvage the old | Line |  |  | Pre-Condition
ENMAX | 27.1TR (SS-27) | 2022-10-25 08:00 | 2022-10-25 16:00 | N | N | power factor test 27PT69-1. 13.60L already oos | Transformer | power factor test 27PT69-1. 13.60L already oos |  | For Information Only
SNRL | HRV1 High River 1 DER | 2022-10-25 08:00 | 2022-11-08 16:00 | N | N | P2317 FortisAlberta High River 65S DER Gas. 10 MW. ISD November 01, 2022 | Unit
KSLP | TRH1 Kneehill Solar LP | 2022-10-25 08:00 | 2023-02-22 16:00 | N | N | P2059 ATCO Three Hills 770S DER Solar 1. 25 MW. ISD Nov 01, 2022 | Unit
MSLP | MIC1 Michichi Solar | 2022-10-25 08:00 | 2023-03-01 16:00 | N | N | P2061 ATCO Michichi Creek 802S DER Solar. 25 MW. ISD Nov 01, 2022 | Unit
ALTALINK | 320p 2152 (320p Keephills) | 2022-10-25 08:30 | 2022-10-25 17:30 | N | Y | fix SF6 gas leak | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 1652 (310p Sundance) | 2022-10-25 08:30 | 2022-10-25 16:30 | N | Y | 1st trip PRC 5 maintenance | Circuit Breaker |  |  | 240 kV
BCH, ALTALINK | 1L274 (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2022-10-25 09:00 | 2022-11-10 17:00 | Y | Y | replace end of life structures and set poles BC maintenance does not affect the Alberta ATC | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
CMH | MH-30L (MHS-3 Southridge - MHS-5 NE Crescent Heights) | 2022-10-25 10:00 | 2022-10-25 11:00 | N | N | faciltate replacement of damaged line CT terminal blocks | Line | Open 69kV MH-30/40L line to eliminate current from line CT's to faciltate replacement of damaged line CT terminal blocks. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 669L (163s Amoco Empress - 562s Cypress), 163s 669 (163s Amoco Empress), 562s 1752 (562s Cypress), 562s 1852 (562s Cypress), 562s 669 (562s Cypress) | 2022-10-25 11:00 | 2022-10-26 13:00 | N | N | implement 669L prot LTO setting changes and testing as part of new RAS208 scheme | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 275s 240kV Bus 2 (275s Jenner), 275s T2 (275s Jenner), 275s 1952 (275s Jenner), 275s 2252 (275s Jenner), 275s 2652 (275s Jenner), 275s 46 (275s Jenner), 275s 8 (275s Jenner), 275s 47 (275s Jenner), 275s 36 (275s Jenner) | 2022-10-26 07:00 | 2022-10-27 17:00 | N | Y | install slack span, wire bus drops | Bus, Transformer, Circuit Breaker, Switch | Close Open Point "C", Install 949L slack span from transmission structure to A-frame, install wire bus drops to switch. This will energize the new Joss 240kV Bay. 2nd scope: repair hot switch 275s45 |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 557s CD2401 (557s Castle Downs) | 2022-10-26 07:00 | 2022-10-26 17:00 | N | Y | CD2401: NAIT tour switching demonstration | Circuit Breaker |  | CD2401: NAIT Tour Switching Demonstration | 240 kV, Contingency Requires Mitigation
ALTALINK | 336s T1 (336s Fincastle), 336s 752 (336s Fincastle) | 2022-10-26 07:30 | 2022-10-27 17:30 | N | N | techs to replace old T/C controller | Transformer, Circuit Breaker |  | Techs to replace old malfunctioning T/C controller with newer model | For Information Only
ALTALINK | 410s T1 (410s Josephburg), 410s 138kV Bus 1 (410s Josephburg), 410s 552 (410s Josephburg), 410s 852 (410s Josephburg) | 2022-10-26 07:45 | 2022-10-26 17:45 | N | Y | fix leak on SST2 & site checks. | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.1TR (SS-2) | 2022-10-26 08:00 | 2022-10-28 16:00 | N | N | install repaired radiator on 2.1TR, oil sampling MT & TC | Transformer |  |  | For Information Only
ALTALINK | 310p 2352 (310p Sundance) | 2022-10-26 08:30 | 2022-10-26 16:30 | N | Y | 1st trip PRC 5 maintenance | Circuit Breaker |  | 1st trip PRC 5 maintenance. | 240 kV, Contingency Requires Mitigation
ALTALINK | 895s T2 (895s Suffield) | 2022-10-26 08:30 | 2022-10-26 17:30 | N | N | investigate low MT alarm | Transformer |  |  | For Information Only
ALTALINK | 668L (394s Empress - 562s Cypress), 394s 668 (394s Empress), 562s 1352 (562s Cypress), 562s 1452 (562s Cypress), 562s 668 (562s Cypress) | 2022-10-26 13:00 | 2022-10-27 18:30 | N | N | protection and CT cut overs | Line, Circuit Breaker, Switch |  | 562s 668L protection and CT cut overs and testing as part of new RAS208 Scheme | Contingency Requires Mitigation
ALTALINK | 121s 23N (121s Brooks) | 2022-10-26 13:00 | 2022-10-26 15:00 | N | N | circuit cutover and protection trip test | Circuit Breaker |  | Circuit cutover. 152BF, 452BF, T5 A/B, 138NB A/B protection trip test. | Restricts Generation
ENMAX | 11.83L (SS-162 - SS-11), 162B138-RB84 (SS-162), 162B138-RB85 (SS-162), 11B138-11.83 (SS-11) | 2022-10-27 08:00 | 2022-10-28 18:00 | N | N | 162 sub 138kV DFR Installation | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload
ALTALINK | 121s 83X (121s Brooks) | 2022-10-27 08:00 | 2022-10-27 14:00 | N | N | protection setting change. circuit cutover. 152BF, 452BF, T5 A/B, 138NB A/B protection trip test | Circuit Breaker | transmission constraint record is created. |  | Pre-Condition, Restricts Generation
ALTALINK | 71s C2 (71s Lamoureux) | 2022-10-27 08:30 | 2022-10-31 16:30 | N | N | 71s1052 breaker maintenance | Shunts |  |  | Pre-Condition
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 255s 34 (255s Vulcan) | 2022-10-27 09:00 | 2022-10-27 15:00 | N | Y | PRC 1st trip and maintenance if required | Line, Circuit Breaker | 2nd Scope: Hardware tighten structure 180L161. |  | Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation
ALTALINK | 275s 2689 (275s Jenner) | 2022-10-27 16:00 | 2022-11-15 16:00 | N | N | advice to IPP  to build customer owned 949L (306s-275s) | Switch |  |  | 240 kV, For Information Only
ALTALINK | 658L (649s Chappice Lake - 658AL tap), 658L (562s Cypress - 658AL tap), 658AL (662s Hilda - 658AL tap), 562s 658 (562s Cypress), 562s 1452 (562s Cypress), 562s 1652 (562s Cypress) | 2022-10-28 07:00 | 2022-10-30 18:30 | N | Y | 658L (562s - I_662s - 649s) - GOI | Line, Switch, Circuit Breaker | RAS207 and RAS208 implementation and testing from 562s to 662s. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial) | 2022-10-28 07:00 | 2022-10-28 18:00 | N | N | GOI required on 797L51 and urgent repair to install new anchor and salvage old anchor | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s 257X (121s Brooks) | 2022-10-28 08:00 | 2022-10-28 14:00 | N | N | protection setting change, circuit cutover, 152BF, 452BF, T5 A/B, 138NB A/B protection trip test | Circuit Breaker | transmission constraint record is created. |  | Pre-Condition, Restricts Generation
ALTALINK | 349s Stavely, 197L (349s Stavely - 928s East Stavely), 349s T1 (349s Stavely), 349s 197 (349s Stavely), 349s 10 (349s Stavely), 349s 14 (349s Stavely), 349s 4044 (349s Stavely), 349s 20 (349s Stavely), 928s 197W (928s East Stavely) | 2022-10-28 09:30 | 2022-10-30 18:30 | N | N | install 2 under-voltage protection relay, and other relay/functional tests | Station, Line, Transformer, Circuit Breaker, Switch | transmission constraint record is created. |  | Pre-Condition, Restricts Generation
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 197L (349s Stavely - 928s East Stavely), 180L (928s East Stavely - 180AL tap), 255s 34 (255s Vulcan), 349s Stavely, 928s East Stavely, 928s 180N (928s East Stavely), 928s 180X (928s East Stavely), 928s 197W (928s East Stavely), 349s 10 (349s Stavely), 349s 14 (349s Stavely), 349s 20 (349s Stavely), 349s 4044 (349s Stavely), 349s T1 (349s Stavely) | 2022-10-28 10:30 | 2022-10-30 17:30 | N | N | rebuild of autorestoration equipment at 928s, 2nd scope: modify 349s VT2 to a 3 phase setup | Line, Circuit Breaker, Station, Switch, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | EP 511s Victoria T3 (EP 511s Victoria), EP 511s Victoria T4 (EP 511s Victoria) | 2022-10-29 07:00 | 2022-10-29 19:00 | N | N | reactor bay fence repair | Transformer |  |  | For Information Only
ENMAX | 5.9TR (SS-5) | 2022-10-29 08:00 | 2022-10-29 16:00 | N | N | update settings 5.9TR-351 | Transformer |  |  | For Information Only
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2022-10-29 08:00 | 2022-10-29 16:00 | N | N | power factor test 5B138-1.84-CT | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 244s 24 (244s Bowmanton) | 2022-10-29 08:00 | 2022-10-29 17:30 | N | Y | installing mobile voltage transformer MVT1 | Switch | installing mobile voltage transformer MVT1 (Mobile Voltage Transformer) to monitor power quality for future project |  | Pre-Condition
ALTALINK | 180L (15s Fort Macleod - 180AL tap), 15s 180N (15s Fort Macleod) | 2022-10-29 08:15 | 2022-10-30 16:00 | N | Y | installation of screw piles underneath 180L | Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition, Restricts Generation
CLRS | CLR1 Claresholm Solar, CLR2 Claresholm Solar | 2022-10-29 08:15 | 2022-10-30 16:00 | N | N | AltaLink installation of screw piles underneath 180L | Unit
ENMAX | 14.83L (SS-14 - SS-36), 14.2TR (SS-14), 14.4TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14MD138-14.2TR (SS-14), 14MD138-14.4TR (SS-14), 14B138-14.83 (SS-14), SW84 (SS-14), SW87 (SS-14) | 2022-10-30 08:00 | 2022-10-30 16:00 | N | N | power factor test 14PT138-Z31. oil sampling 14.2-TC, MT | Line, Transformer, Shunts, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 51s T3 (51s Wainwright) | 2022-10-30 11:00 | 2022-11-10 18:00 | N | N | corrosive sulphur mitigation, fix leaks, change temp gauge, maintain, doble | Transformer |  |  | For Information Only
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap) | 2022-10-30 15:00 | 2022-11-01 17:00 | N | Y | forced outage | Line |  |  | Affects Cranking Path
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2022-10-30 15:00 | 2022-11-01 17:00 | N | N | forced outage | Line |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy) | 2022-10-31 07:00 | 2022-11-05 17:00 | N | Y | micro switch repair | Transformer | Bellamy 240kV SF6 Maintenance |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2022-10-31 07:00 | 2022-11-02 14:00 | N | Y | scada cut-over's for rtu bus extension | Transformer, Circuit Breaker | Cloverbar TX3: SCADA Cut-Overs for RTU BUS Extension. |  | 240 kV
EPCOR | 816s T1 (816s Petrolia), 816s P2401 (816s Petrolia), 816s P2402 (816s Petrolia), 816s PDS2 (816s Petrolia), 816s PDS3 (816s Petrolia) | 2022-10-31 07:00 | 2022-11-04 17:00 | N | Y | Petrolia PDS2, PDS3 LCR | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | T3 (Poundmaker) | 2022-10-31 07:00 | 2022-11-04 17:00 | N | Y | tap changer maintenance | Transformer | Tap Changer Maintenance (Reinhausen). |  | 240 kV, Pre-Condition
ENMAX | 10.1TR (SS-10) | 2022-10-31 08:00 | 2022-11-02 16:00 | N | N | relay and protection testing | Transformer | Relay, Protection Testing. 10RLY138-10.1TR SEL-351S, T60. |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 40B138-32.83 (SS-40) | 2022-10-31 08:00 | 2022-10-31 16:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 5.5TR (SS-5) | 2022-10-31 08:00 | 2022-11-03 16:00 | N | N | transformer testing | Transformer | Power factor test transformer. Secondary Cable Testing. Transformer Maintenance. Gas relay testing. Oil Sampling. Check Reversing Switch. 5.5TR, TC Replace PRD Junction Box. |  | For Information Only
ENMAX | 8.3TR (SS-8) | 2022-10-31 08:00 | 2022-11-01 16:00 | N | N | tapchanger maintenance. | Transformer | Tapchanger maintenance. Oil Sampling MT, TC. Relay, protection testing T60. Relay, lockout testing 86-8.3TR. |  | For Information Only
Saskpower | Sask Power H1P line | 2022-10-31 08:00 | 2022-11-06 18:00 | N | N | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage BD22 Line, BR 901T, GL 801T, PA2, R1P Line-PQSS TO L4, R1R Line, WL 702P, WL2 Line |  | For Information Only
ALTALINK | 417L (55s Olds - 281s Johnson) | 2022-10-31 08:00 | 2022-10-31 18:00 | N | N | replace dampers on center phase on str 76 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 44s T2 (44s Bearspaw Plant), 44s 33 (44s Bearspaw Plant) | 2022-10-31 08:00 | 2022-11-14 17:00 | N | Y | maintenance | Transformer, Switch |  |  | Restricts Generation
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2022-10-31 08:00 | 2022-11-23 17:00 | N | N | cross arm and insulator replacement project | Line | GOI required on 7L760 for cross arm & insulator replacement project. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2022-10-31 09:00 | 2022-10-31 18:00 | N | N | urgent arm replacement on 776L140 & 776L153 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2022-10-31 09:00 | 2022-10-31 17:00 | N | Y | clearance required to replace badly damaged insulators in the 135 mile BC maintenance does not affect the Alberta ATC | Line | Clearance required to replace badly damaged insulators in the 135 mile BC maintenance does not affect the Alberta ATC |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 44s RTU/SCADA (44s Bearspaw Plant) | 2022-10-31 09:00 | 2022-11-03 17:00 | N | N | update RTU database | Terminal Equipment | RTU database update, Short loss of visibility (2 -15 minutes) during downloading of new configurations about 2 times each day. No impact to TAU as coordinated with Ref 279379 44s 138kV Bus (50L & 36.81L) - GOI |  | Affects Visibility
ALTALINK | 158s 138kV Bus (158s Vauxhall), 158s 21 (158s Vauxhall), 158s 52 (158s Vauxhall) | 2022-10-31 09:00 | 2022-11-07 17:00 | N | N | 138kv bushing replacement and transformer and switch maintenance | Bus, Switch, Circuit Breaker | 158s T2 & 25kV Bus - GOI 138kv Bushing Replacement Maintenance: 158s T2 leaks and maint., 158s6 seized switch, 158s16 hot switch |  | Restricts Generation
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2022-10-31 09:00 | 2022-11-09 18:00 | N | Y | damper replacements | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - SS-21), 36.81L (44s Bearspaw Plant - SS-36), 44s 50X (44s Bearspaw Plant), 44s 36.81E (44s Bearspaw Plant) | 2022-10-31 09:00 | 2022-11-04 18:00 | N | Y | equipment replacement | Line, Circuit Breaker | 44s38 switch replace, 36.18L PT addition, 36.18L strain insulator replace, 36.18L VSR salvage |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1059L (38s East Edmonton - EP 803s Lambton), 1059AL (52s East Industrial - 1059L tap), 52s T1 (52s East Industrial), EP 803s L2401 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton) | 2022-10-31 09:30 | 2022-11-05 17:00 | N | Y | steel structure refurbishment | Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 700s 706 (700s Bonnyville), 700s 706C (700s Bonnyville) | 2022-10-31 10:00 | 2022-11-04 17:00 | N | N | 700s 706C cap bank replacement | Circuit Breaker, Shunts | 700s 706C cap bank replacement |  | Pre-Condition
ALTALINK, EPCOR | 1045AL (320p Keephills - 1045L tap), 1045L (310p Sundance - 1045AL tap), 1045L (EP 805s Jasper - 1045AL tap), EP 805s J2406 (EP 805s Jasper), EP 805s J2407 (EP 805s Jasper), 320p 1352 (320p Keephills), 310p 1652 (310p Sundance), 310p 1752 (310p Sundance) | 2022-10-31 11:00 | 2022-11-04 17:00 | N | Y | customer line injection testing to verify grounding | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 180L (928s East Stavely - 180AL tap) | 2022-10-31 16:30 | 2022-11-09 16:00 | N | N | forced outage | Line |  |  | For Information Only
ALTALINK | 284s T1 (284s Nose Creek) | 2022-11-01 06:00 | 2022-11-03 18:00 | N | N | customer switchgear maintenance | Transformer |  |  | For Information Only
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft), W721 (Woodcroft), EP 805s JDS28 (EP 805s Jasper), EP 805s J724 (EP 805s Jasper) | 2022-11-01 07:00 | 2022-11-02 17:00 | N | N | connector replacements for UGT | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 700s 706C (700s Bonnyville) | 2022-11-01 08:00 | 2022-11-30 16:00 | N | N | Wafer replacement project. Re-rate 706C back to 16.2 MAr (capital maintenance). ISD November 2022 | Shunts
ALTALINK | 63s 552 (63s Red Deer), 901L (63s Red Deer - 901AL tap) | 2022-11-01 08:00 | 2022-11-03 13:00 | N | Y | 552 GOI request for the 652 breaker failure and control P&C upgrade | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Affects Cranking Path
Syncrude | MH1 (Aurora - Aurora) | 2022-11-01 08:00 | 2022-11-02 20:00 | N | N | 72kV powerline outage | Line |  |  | For Information Only
ALTALINK | 740L (39s Bickerdike - 58s Edson), 58s 740X (58s Edson) | 2022-11-01 08:00 | 2022-11-01 16:00 | N | N | 1st trip and PRC5 maintenance | Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition
ALTALINK | 83s C1 (83s Taber), 83s C2 (83s Taber), 83s 61 (83s Taber), 83s 67 (83s Taber) | 2022-11-01 08:30 | 2022-11-01 17:30 | N | N | 83sC1 lockout investigation | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 808L (13s Deerland - 808AL tap) | 2022-11-01 09:00 | 2022-11-04 18:00 | N | N | component replacement's 808L str's range 1-75 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek) | 2022-11-01 09:00 | 2022-11-01 16:00 | N | Y | 9074R to 9273R radio repair | Line | WebOMS#: 12632457 |  | Pre-Condition
ATCO | 7L01 (813s Little Smoky - 881s Sturgeon 2), 813s 7L01D1 (813s Little Smoky) | 2022-11-01 11:00 | 2022-11-06 14:20 | N | N | 813S Little Smoky rebuild | Line, Switch | 813S Little Smoky Rebuild Complete 7L01 wiring panel 7P3, 711, 712 CT/PT/P&C wiring. Demo existing wiring/cabling, remove old panel 8G Relay programming and functionality Commission control, alarms and status |  | Restricts Generation,Affects Cranking Path
AESO-SC | OATI | 2022-11-01 18:00 | 2022-11-01 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
ALTALINK | 924L (102s Langdon - 356s Milo) | 2022-11-02 06:30 | 2022-11-24 14:00 | N | Y | phase 3 of 924L project between structures 13A-299, component replacement | Line | Phase 3 of 924L project between Structures 13A-299, (work include M-tower bracket change outs, replacing insulation, replacing cold end hardware, replacing OHSW assemblies, and replacing spacer assemblies) |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 63s 240kV South Bus (63s Red Deer), 63s T2 (63s Red Deer), 63s 352 (63s Red Deer), 63s 952 (63s Red Deer), 63s 2752 (63s Red Deer) | 2022-11-02 07:30 | 2022-11-02 17:00 | N | Y | 652 breaker failure and control P&C upgrade | Bus, Transformer, Circuit Breaker | 63s 240BN GOI request for the 652 Breaker Failure and Control P&C upgrade. |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 65.1TR (SS-65) | 2022-11-02 08:00 | 2022-11-03 16:00 | N | Y | 65.1TR MT PRD junction box investigate & repair, Calisto cylinder exchange, PRD flag replacement | Transformer | 65.1TR MT PRD Junction Box Investigate & Repair, Calisto cylinder exchange. PRD Flag Replacement |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | MH2 (Aurora - Aurora), 33 (Aurora), 34 (Aurora), 89-37 (Aurora) | 2022-11-02 08:00 | 2022-11-03 20:00 | N | N | maintenance | Line, Circuit Breaker, Switch | Non-Significant Outage - MH2 72kV Powerline Outage: The following Circuit Breakers will be operated: 33 (G01 Substation) 34 (G01 Substation) The following MOD will be operated: 37 (G01Substation) |  | For Information Only
ENMAX | 8B138-5A0 (SS-8) | 2022-11-02 08:00 | 2022-11-02 16:00 | N | N | relay, lockout testing | Circuit Breaker | Relay, Lockout Testing. 86BF-5a0. Relay, Protection Testing - 8RLY138-5A0-BKRFAIL |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 607L (135s Conrad - 607AL tap), 135s Conrad, 135s 152 (135s Conrad), 135s 689 (135s Conrad) | 2022-11-02 10:30 | 2022-11-06 17:45 | N | Y | line maintenance (str 201~222) | Line, Station, Circuit Breaker, Switch | Transmission Line Maintenance (Str 201~222). Ref previous submission 281990. Due to wet/weather conditions the 281990 work can not be completed, in discussions with Fortis, they have agreed to have the 281990 outage returned early and retake the outage in this window transmission constraint record is created. |  | Pre-Condition, Restricts Generation
ALTALINK | 421s C1 (421s Hays), 421s 30 (421s Hays) | 2022-11-02 12:30 | 2022-11-03 17:30 | N | N | emergency investigate B protection and unbalanced alarm | Shunts, Circuit Breaker | Investigate 'B' prot and unbalanced alarm (Cap Bank currently out of service) |  | Pre-Condition
EPCOR | 987s T4 (987s Clover Bar), 987s C2408 (987s Clover Bar) | 2022-11-02 14:01 | 2022-11-03 17:00 | N | Y | SCADA cut-overs for RTU bus extension | Transformer, Circuit Breaker | Cloverbar TX4: SCADA Cut-Overs for RTU BUS Extension |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
Saskpower | SaskPower C1S | 2022-11-03 08:00 | 2022-11-04 18:00 | N | N | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage C1S Line, PRPS 1 Unit, PRPS 2 Unit, CWPPS Wind, BHWPS WIND, GSWPS Wind |  | For Information Only
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station), 814s B2402 (814s Bellamy) | 2022-11-03 08:00 | 2022-11-03 16:00 | N | Y | emergency outage BDS19GS low gas alarm | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
VISIONREQ | 354s RTU/SCADA (354s Summerview) | 2022-11-03 08:00 | 2022-11-03 14:00 | N | N | replace SCADA server for the Summerview 2 site. | Terminal Equipment |  |  | Affects Visibility
ENMAX | 39.3TR (SS-39) | 2022-11-03 08:00 | 2022-11-18 16:00 | N | N | bushing replacement, maintenance and testing | Transformer | 39.3TR HV, LV Bushing replacement. Power factor test transformer. CT Replacement. Transformer Secondary Cable Testing. Transformer Maintenance. Gas Relay Testing. Check Reversing Switch. Oil Sampling MT, TC. One hour backfeed required on return |  | For Information Only, Pre-Condition
ENMAX | 162.81L (391s Balzac - SS-162), 162B138-RB80 (SS-162), 162B138-RB81 (SS-162), 162MD138-162.81 (SS-162) | 2022-11-03 08:00 | 2022-11-04 18:00 | N | Y | 162 sub 138kV DFR installation | Line, Circuit Breaker, Switch |  | 162 Sub 138kV DFR Installation | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 7L48 (794s Valleyview - 7LA48 tap) | 2022-11-03 08:00 | 2022-11-03 17:00 | N | N | high load move to cross under 7L48-20 crossing at NW-23-70-22-5 on Hwy 669 | Line |  | outage for high load move to cross under 7L48-20 crossing at NW-23-70-22-5 on Hwy 669. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 291s T2 (291s Cochrane) | 2022-11-03 08:30 | 2022-11-03 17:30 | N | N | top up TX and investigate station service SS2 | Transformer |  | top up TX and investigate station service SS2 | For Information Only
ENMAX | 2.84L (SS-2 - SS-8) | 2022-11-04 08:00 | 2022-11-04 12:00 | N | N | water sampling manhole | Line |  |  | Pre-Condition
ENMAX | 13.3TR (SS-13) | 2022-11-04 08:00 | 2022-11-04 12:00 | N | N | oil sampling | Transformer | Oil Sampling - 13.3-TC |  | For Information Only
ENMAX | 33.1TR (SS-33) | 2022-11-04 08:00 | 2022-11-04 12:00 | N | N | oil sampling | Transformer | Oil Sampling MT, TC |  | For Information Only
Syncrude | ML1 (D05 - Syncrude Mildred Lake) | 2022-11-04 08:00 | 2022-11-16 20:00 | N | N | maintenance | Line | Non-Significant Outage: Plant 31 ML1 (72kV) Transmission Line Outage: The following breakers will be operated: CB # 52-76 @ D05 Substation CB# 915 @ Plant 31 Substation Following Switches will be operated: 89-76A @ D05 Substation 89-76B @ D05 Substation 914 @ Plant 31 Substation 916 @ Plant 31 Substation |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.2TR (SS-33) | 2022-11-04 12:00 | 2022-11-04 16:00 | N | N | oil sampling MT, TC | Transformer | oil sampling MT, TC |  | For Information Only, Pre-Condition
ENMAX | 23.3TR (SS-23) | 2022-11-04 12:00 | 2022-11-04 16:00 | N | N | oil sampling, maintenance | Transformer | Oil Sampling - 23.3-TC. Filmax LTC Oil Filtration Maintenance. Calisto Maintenance |  | For Information Only
ALTALINK | 731L (38s East Edmonton - 746L tap), 731L (420s Broadmoor - 731L tap), 746L (731L tap - 746BL tap) | 2022-11-05 07:00 | 2022-11-06 13:00 | N | N | urgent - replace structure 746L1 due to damage from farm equipmen | Line | URGENT Replace structure 746L1 due to damage from farm equipment, See also 606L SAP: 282485 for 606L8 repairs that double circuit with 746L1. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2022-11-05 07:00 | 2022-11-05 18:00 | N | N | urgent - 174L694 structure replacement | Line, Circuit Breaker | URGENT *P5* 174L694 Structure Replace |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2022-11-05 07:00 | 2022-11-05 17:00 | N | Y | meter upgrade P&C cut-over | Line | Castledowns: Meter Upgrade P&C Cut-Overs |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 606L (184s Petro-Canada Edmonton - 185s Bretville) | 2022-11-05 07:00 | 2022-11-06 13:00 | N | N | urgent - replace 606L8 due to damage from farm equipment | Line | URGENT Replace 606L8 due to damage from farm equipment, See also 731/746L SAP: 282483 for 746L1 repairs that is double circuit with 606L8. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.1TR (SS-32) | 2022-11-05 08:00 | 2022-11-05 18:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2022-11-06 07:00 | 2022-11-06 17:00 | N | Y | meter upgrade P&C cut-over | Line | Castledowns: Meter Upgrade P&C Cut-Overs |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 32.2TR (SS-32) | 2022-11-06 08:00 | 2022-11-06 18:00 | N | N | fall substation washing | Transformer | Fall Substation Washing. 32s. 8kV bus |  | For Information Only
EPCOR | 557s T2 (557s Castle Downs) | 2022-11-07 07:00 | 2022-11-17 17:00 | N | Y | meter upgrade P&C cut-overs | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS14 (816s Petrolia) | 2022-11-07 07:00 | 2022-11-19 17:00 | N | Y | 1044L insulator LCR | Line, Circuit Breaker, Switch | Petrolia: Apparatus: PDS10, PDS14, PDS15 LCR's Aerial: 1044L Insulator LCR |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 803s T1 (EP 803s Lambton) | 2022-11-07 07:00 | 2022-11-08 17:00 | N | Y | TX1 level gauge repair | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 74s T1 (74s Janet), 74s 16 (74s Janet) | 2022-11-07 07:00 | 2022-11-10 13:00 | N | Y | replace T1 A and B protections | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 113L (20s Ghost - 33s Spray), 33s 113 (33s Spray), 20s 113 (20s Ghost) | 2022-11-07 07:15 | 2022-11-26 14:08 | N | N | rebuilding a section of 113L from structure 1 to 96 | Line, Circuit Breaker | scope of work includes rebuilding a section of 113L from structure 1 to 96 |  | Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 771L (SS-47 - SS-162), 162B138-RB81 (SS-162), 162B138-RB82 (SS-162), 162MD138-771L (SS-162), 47B138-771 (SS-47), 47B138-771/1 (SS-47), 47B138-BT3 (SS-47), 47MD138-47.1TR (SS-47), 47MD138-47.2TR (SS-47), SS-47 | 2022-11-07 08:00 | 2022-11-10 18:00 | N | Y |  | Line, Circuit Breaker, Switch, Station |  | 162 Sub 138kV DFR Installation. 47 sub cable trench replacement. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 20.3TR (SS-20) | 2022-11-07 08:00 | 2022-11-09 16:00 | N | N | relay, protection testing | Transformer | relay, protection testing. 20RLY138-20.3TR. Relays, Lockout Testing 20RLY138-20.3TR |  | For Information Only
ENMAX | 5.1TR (SS-5) | 2022-11-07 08:00 | 2022-11-07 18:00 | N | N | 5 sub DFR commissioning | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 771L (SS-47 - SS-162), 47.1TR (SS-47), 47.2TR (SS-47), 47B138-771 (SS-47), 47B138-771/1 (SS-47), 47B138-BT3 (SS-47) | 2022-11-07 08:00 | 2022-11-10 18:00 | N | N | 47 sub cable trench replacement | Line, Transformer, Circuit Breaker |  | 47 sub cable trench replacement | For Information Only
ATCO | LAN1 Pattern Lanfine North Wind | 2022-11-07 08:00 | 2022-11-21 17:00 | N | N | P1898 Pattern Lanfine North Wind 145 MW. ISD Nov 14, 2022. | Unit
Saskpower | SaskPower C1S | 2022-11-07 08:00 | 2022-11-08 18:00 | N | N | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage C1S Line, PRPS 1 Unit, PRPS 2 Unit, CWPPS Wind, BHWPS WIND, GSWPS Wind |  | For Information Only
ATCO | 827s SVC (827s Cranberry Lake) | 2022-11-07 10:00 | 2022-11-10 14:30 | N | Y | SVC maintenance | Shunts |  |  | Pre-Condition
ATCO | 7L224 (650s Hansman Lake - 774s Monitor), 774s 701 (774s Monitor) | 2022-11-07 10:00 | 2022-11-10 16:00 | N | Y | install 2 relays for line protections RAS A&B | Line, Circuit Breaker |  | Install 2 relays for line protections RAS A&B | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 741s 702T (741s Fox Creek) | 2022-11-07 10:30 | 2022-11-07 17:00 | N | N | fix hot spot of 504TD | Transformer |  |  | For Information Only
ALTALINK | 808L (13s Deerland - 808AL tap) | 2022-11-07 12:00 | 2022-11-10 18:00 | N | N | component replacement's 808L str's range 1-75 | Line |  | Component Replacement's 808L Str's Range 1-75 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 930s SVC (930s Arcenciel) | 2022-11-07 13:00 | 2022-11-09 21:45 | N | Y | perform fall maintenance on SVC, breaker 401 partial maintenance PM | Shunts |  | Perform fall maintenance on SVC. Breaker 401 partial maintenance PM. | Pre-Condition
BHE | 719s Rattlesnake Ridge | 2022-11-07 13:00 | 2022-11-10 14:00 | N | N | software update to the wind turbine SCADA | Station |  |  | Affects Visibility, Restricts Generation
ALTALINK | 1065L (74s Janet - 102s Langdon), 74s 3752 (74s Janet), 74s 3852 (74s Janet), 74s 1065 (74s Janet) | 2022-11-08 07:30 | 2022-11-10 12:00 | N | Y | repairing 74s122 | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
JCLP | JNR3 Jenner 3 | 2022-11-08 08:00 | 2023-07-15 17:00 | N | N | P2234 Jenner Wind Phase 3. 109 MW. ISD Nov 15, 2022. | Unit
ENMAX | 5.6TR (SS-5) | 2022-11-08 08:00 | 2022-11-08 18:00 | N | N | 5 Sub DFR commissioning | Transformer |  |  | For Information Only, Pre-Condition
JALP, JBLP, JCLP | JNR1 Jenner 1, JNR2 Jenner 2, JNR3 Jenner 3 | 2022-11-08 08:00 | 2022-11-22 17:00 | N | N | P1533, P1698 and P2234 Jenner Wind Projects step-up transformers energizations. ISD Nov 15, 2022 | Unit
SUNCOR | 29EDD-71 752-4641 (29EDD-71), 29EDD-71 752-4642 (29EDD-71), 29EDD-71 29PT-235 (29EDD-71), 29EDD-71 29PS-263 (29EDD-71 Edd71Sub) | 2022-11-08 08:00 | 2022-11-15 18:00 | N | Y | urgent - 10-Year preventive maintenance on associated CTs and breakers | Circuit Breaker, Transformer, Switch | Customer request to complete 10-Year preventive maintenance on associated CTs and breakers, in addition giving us an opportunity to trip test the breakers back to the generating unit - completing PRC-005 testing for these assets. |  | Restricts Generation
ENMAX | 8B138-6A0 (SS-8) | 2022-11-08 08:00 | 2022-11-08 16:00 | N | N | relay, lockout testing. 86BF-6a0, relay, protection testing 8RLY138-6A0-BKRFAIL | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L80 (740s H.R. Milner - 857s Kakwa Ridge), 7L80 (733s Simonette - 857s Kakwa Ridge), 7L33 (845s Big Mountain - 7LA33 tap) | 2022-11-08 08:00 | 2022-11-14 17:00 | N | Y | line mitigation, cross arm replacement | Line | Line mitigation, Cross arm replacement |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 434L (65s High River - 237s Foothills), 65s 434 (65s High River) | 2022-11-08 09:00 | 2022-11-08 10:59 | N | N | install, wire and commission a maintenance switch for breaker 1152 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
CapitalPower | 1018s RTU/SCADA (1018s Shamrock) | 2022-11-08 09:00 | 2022-11-08 13:00 | N | N | communications-only outage to do some ICS updates | Terminal Equipment | RTAC needs to be rebooted at least once for each WL1 and WL2.. AESO will see both farms most of the time, but lose visibility of both MW and MVars while the RTAC is being rebooted (each RTAC reboot takes about 1 or 2 minutes). The farm will be unavailable to respond to wind ramp management in real time during the 1-2 minute outages, however site personnel will be on site to respond to curtailments if dispatched verbally. |  | Affects Visibility
TRANSALTA, GWPCORP, VISIONREQ | Transalta Wind Control Centre, 240s McBride Lake, 243s Soderglen, 354s Summerview, 418s Ardenville | 2022-11-08 09:00 | 2022-11-08 15:30 | N | N | firewall software updates | SCInternal, Station |  |  | Affects Visibility
ALTALINK | 753L (65s High River - 253s Blackie), 65s 753E (65s High River) | 2022-11-08 11:00 | 2022-11-08 13:00 | N | Y | install, wire and commission a maintenance switch for breaker 852 | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 39s 240kV Bus 2 (39s Bickerdike), 39s T2 (39s Bickerdike), 39s 1152 (39s Bickerdike), 39s 29 (39s Bickerdike), 39s 1752 (39s Bickerdike), 39s 20 (39s Bickerdike) | 2022-11-09 06:00 | 2022-11-09 18:00 | N | Y | fix corona issue found on 240B2 and DC ground fault found on 1152 breaker | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 701L (223s Strome - 395s North Holden) | 2022-11-09 07:00 | 2022-11-09 13:00 | N | N | change arms and insulation on structure 42 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | EP 803s T2 (EP 803s Lambton) | 2022-11-09 07:00 | 2022-11-10 17:00 | N | Y | level gauge repair | Transformer |  |  | 240 kV, For Information Only
ENMAX | 5.9TR (SS-5) | 2022-11-09 08:00 | 2022-11-09 18:00 | N | N | DFR commissioning | Transformer |  |  | For Information Only
ENMAX | 12.1TR (SS-12) | 2022-11-09 08:00 | 2022-11-10 16:00 | N | N | tapchanger maintenance, 12.1TR investigate BA & BB breaker rosettes, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 678s T2 (678s Okotoks), 678s 452 (678s Okotoks) | 2022-11-09 08:30 | 2022-11-09 17:00 | N | N | bird cover deficiencies | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 65s T2 (65s High River) | 2022-11-09 09:00 | 2022-11-09 11:00 | N | N | complete the wiring for the Tx CT contribution to the new undervoltage protection and commissioning of the CT circuit | Transformer |  |  | For Information Only
ENMAX | 36.2TR (SS-36) | 2022-11-10 08:00 | 2022-11-10 16:00 | N | N | relay, protection testing | Transformer | Relay, Protection Testing, - 36RLY138-36.2TR S SEL |  | For Information Only
ENMAX | 38.3TR (SS-38) | 2022-11-10 08:00 | 2022-11-10 16:00 | N | N | relay, protection testing, firmware upgrade | Transformer | Relay, Protection Testing, Firmware upgrade - 38RLY138-38.3TR S SEL. |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2022-11-10 08:00 | 2022-11-10 18:00 | N | N | 5 sub DFR commissioning | Transformer |  |  | For Information Only
ATCO | 767s 602T (767s Oyen) | 2022-11-10 09:00 | 2022-12-12 12:00 | N | N | connecting 2000s mobile sub | Transformer | GOI for Tap up of low side of 2000s onto 502TD and create an open jumper J1. Reduce GOI to 602TD and Jumper J1 |  | For Information Only
ALTALINK | 74s 240kV Bus 1 (74s Janet), 74s T1 (74s Janet), 74s 16 (74s Janet), 74s 552 (74s Janet), 74s 3752 (74s Janet), 74s 2752 (74s Janet), 74s 2552 (74s Janet), 74s 2052 (74s Janet), 74s 19 (74s Janet) | 2022-11-10 13:00 | 2022-11-10 18:00 | N | Y | test tripping of T1 high and low side breakers for new A and B protections | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 727L (65s High River - 727AL tap), 65s 727N (65s High River) | 2022-11-10 13:00 | 2022-11-10 17:00 | N | N | install, wire and commission a maintenance switch for breaker 752 and change ratio of line PT at 65s for sync check updates. | Line, Circuit Breaker | install, wire and commission a maintenance switch for breaker 752. Wire breaker status and maintenance switch to the 77/DER relay and commission the circuits Change Ratio of line PT at 65s for sync check updates. |  | Pre-Condition
ATCO | 9L09 (849s Joslyn Creek - 888s Dover) | 2022-11-10 13:00 | 2022-11-10 15:00 | N | Y | contingency for telecom outage 2-67282 | Line |  | Contingency for Telecom outage 2-67282, this switching will only be required if AESO requires it for telecom outage 9L09 TPS OOS. Telecom outage is only for 15 minutes duration. | 240 kV, Pre-Condition
ALTALINK | 781L (71s Lamoureux - 172s Sherritt) | 2022-11-11 07:00 | 2022-11-11 18:00 | N | N | x-ray dead-end compression sleeves | Line | X-ray dead-end compression sleeves at 781L str 8. |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 9L46 (932s Pemukan - 959s Lanfine) | 2022-11-11 08:00 | 2022-11-12 17:00 | N | Y | structure foundations work directly under 9L46 | Line |  | Sharp Hills Wind Farm Project Outage for structure foundations work directly under 9L46 | 240 kV, Pre-Condition
ALTALINK | 729L (542s Ervick - 729AL tap) | 2022-11-12 07:00 | 2022-11-12 18:00 | N | N | replace structure 38 due to damage from farm equipment | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial) | 2022-11-12 07:00 | 2022-11-15 18:00 | N | N | urgent replacing structure 65 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 47.1TR (SS-47), 47B138-BT3 (SS-47), 47B138-771/1 (SS-47), 47MD138-47.1TR (SS-47) | 2022-11-12 07:00 | 2022-11-19 16:00 | N | N | 47 sub cable trench replacement | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 39.82L (SS-39 - SS-162), 39B138-39.82 (SS-39) | 2022-11-12 08:00 | 2022-11-13 16:00 | N | N | 39.3TR ECI bushing /slip over CT /MV bushing replacement | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 805s T3 (805s Jasper) | 2022-11-14 06:00 | 2022-11-15 17:00 | N | Y | arc flash protection removal, protection upgrade projects | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 821L (158s Vauxhall - 421s Hays) | 2022-11-14 06:15 | 2022-11-15 17:45 | N | Y | install bird diverters (str 99-110) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 814s T2 (814s Bellamy), 814s B2402 (814s Bellamy), 814s B2406 (814s Bellamy), BR722 (Rossdale), 814s BAB2 (814s Bellamy) | 2022-11-14 07:00 | 2022-11-18 21:40 | N | Y | bellamy 240kV SF6 Maintenance | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2022-11-14 07:00 | 2022-11-24 14:00 | N | Y | damper replacement between structures #32-243 & 368-389 | Line |  |  | 240 kV, Affects Visibility, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 964L (244s Bowmanton - 964L tap), 244s 252 (244s Bowmanton), 244s 352 (244s Bowmanton) | 2022-11-14 07:00 | 2022-11-14 17:30 | N | Y | urgent outage to make corrections to RAS 164 CT circuit | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | EP 803s T3 (EP 803s Lambton) | 2022-11-14 07:00 | 2023-01-27 17:00 | N | Y | 72LS24 protection upgrade p&c cutovers | Transformer | Lambton: 72LS24 Protection Upgrade P&C Cutovers |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 2.4TR (SS-2) | 2022-11-14 08:00 | 2022-11-14 16:00 | N | N | maintenance | Transformer | Oil Sampling MT, TC, Bushing. Check Reversing Switch. Gas Monitor Hydran Maintenance |  | For Information Only
ENMAX | 39.2TR (SS-39) | 2022-11-14 08:00 | 2022-11-14 16:00 | N | N | relay, protection testing, firmware upgrade | Transformer | Relay, Protection Testing, Firmware upgrade - 39RLY138-39.2TR S SEL. |  | For Information Only
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2022-11-14 08:00 | 2022-11-14 18:00 | N | N | DFR commissioning | Line, Circuit Breaker |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2022-11-14 08:00 | 2022-12-04 17:30 | N | N | 7L65 rebuild project | Line | 7L65 Rebuild Project |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s 252 (77s Sagitawah), 77s 452 (77s Sagitawah), 77s 799X (77s Sagitawah) | 2022-11-14 08:00 | 2022-11-17 17:00 | N | N | 77s20 structure leveling and PTs to be removed, re-installed and tested | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
TRANSALTA | GDP1 Garden Plain Wind Farm | 2022-11-14 08:00 | 2023-05-25 12:00 | N | N | P1909 TransAlta Garden Plain Wind 130 MW. ISD November 21, 2022 | Unit
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2022-11-14 09:00 | 2022-11-16 17:00 | Y | Y | switch maintenance | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 86s T1 (86s Bigstone), 914L (86s Bigstone - 289s Saunders Lake), 914L (86s Bigstone - 87s Gaetz), 86s 240kV Bus (86s Bigstone), 86s 1252 (86s Bigstone), 86s 1752 (86s Bigstone), 86s 189 (86s Bigstone) | 2022-11-14 09:30 | 2022-11-14 18:30 | N | Y | replace risers on 86s1752 & 86s1252 and replace 240kV JB DC1 | Transformer, Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 813s 706 (813s Little Smoky) | 2022-11-14 10:00 | 2022-11-28 17:00 | N | N | 7L46 CT/PT/P&C wiring, relay programming and functionality, commission control, alarms and status | Circuit Breaker | 813S Little Smoky Rebuild Complete 706 wiring panel 7L46 CT/PT/P&C wiring. Demo existing wiring/cabling Relay programming and functionality |  | Contingency Requires Mitigation
ATCO | 7L224 (650s Hansman Lake - 774s Monitor), 774s 701 (774s Monitor) | 2022-11-14 10:00 | 2022-11-18 16:00 | N | Y | install 2 relays for line protections RAS A&B | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson), 862s 701T (862s South Bezanson), 7L32D2 (862s South Bezanson) | 2022-11-14 10:00 | 2022-11-14 14:00 | N | Y | 862s south bezanson substation rebuild project reconnect jumper J3 | Line, Transformer, Switch | 862S S. Bezanson Substation Rebuild Project, Reconnect Jumper J3 |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO, GREENGATEP | 9L59 (801s Anderson - 972s Tinchebray), 801s 902 (801s Anderson), 801s 903 (801s Anderson), 801S 902A (801s Anderson), 801S 903A (801s Anderson), 972s 9L59D2 (972s Tinchebray), 801s 9L59D1 (801s Anderson) | 2022-11-14 10:00 | 2022-11-20 17:30 | N | Y | energize 1045s Garden Plain substation and update settings at 801s and 972s on 9L59 relays to 3 terminal line differential | Line, Circuit Breaker, Switch |  | TransAlta Garden Plain Project. Energize 1045s Garden Plain Substation. Update settings at 801s and 972s on 9L59 relays to 3 terminal line differential. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 678s T1 (678s Okotoks), 678s 352 (678s Okotoks) | 2022-11-14 10:30 | 2022-11-24 17:30 | N | N | replacement of the 678s81E & 678s 104W 25 kV circuit breakers | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 421s T1 (421s Hays) | 2022-11-14 10:30 | 2022-11-18 12:30 | N | N | maintenance, install bird cover, replace switches (421s28), create open point 'A' | Transformer | T1 maintenance, install bird cover, replace switches (421s28), create Open Point 'A' |  | For Information Only
ALTALINK | 1135L (39s Bickerdike - Open Point 'H'), 39s 26 (39s Bickerdike), 39s 29 (39s Bickerdike) | 2022-11-14 10:30 | 2022-11-17 16:00 | N | Y | replacement of 39s 26 CTs, repair broken expansion connector | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 808L (13s Deerland - 808AL tap) | 2022-11-14 12:00 | 2022-11-18 18:00 | N | N | component replacements 808L str's range 1-75 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 786s SVC (786s High Level), 786s 703 (786s High Level) | 2022-11-14 12:00 | 2022-11-17 12:15 | N | Y | SVC air cooled maintenance, trip coil testing, relay testing | Shunts, Circuit Breaker | SVC Air Cooled maintenance. 703 PRC-005 Trip coil testing. 401 PRC-005 trip coil testing. 401 Partial maintenance. Various SVC Auxiliary relay PRC-005 testing. Various SVC Microprocessor relay PRC-005 testing. One relay at a time, redundant protection in place |  | Pre-Condition
ALTALINK | 263s C1 (263s Strachan) | 2022-11-14 12:30 | 2022-11-16 17:30 | N | N | breaker testing | Shunts | Breaker testing to see if it requires replacing. Replace all fuse links on C1 cap bank, test each parallel group |  | Pre-Condition
ALTALINK | 748L (267s Killarney Lake - 277s Hayter), 267s 748E (267s Killarney Lake), 277s 748 (277s Hayter) | 2022-11-15 07:00 | 2022-11-15 17:00 | N | N | strain insulator replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2022-11-15 08:00 | 2022-11-15 18:00 | N | N | 5 Sub DFR commissioning | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 6.1TR (SS-6) | 2022-11-15 08:00 | 2022-11-16 16:00 | N | N | maintenance, replacement and testing | Transformer | 6.1TR, TC Replace PRD Junction Box. 6.1TR LTC Gasket Replacement. 6.1TR LTC counter not working - replace. Oil Sampling MT, TC, bushing. Gas relay testing. Gas Monitor Hydran Maintenance |  | For Information Only
ENMAX | 10.2TR (SS-10) | 2022-11-15 08:00 | 2022-11-17 16:00 | N | N | relay, protection testing | Transformer |  |  | For Information Only
ALTALINK | 526s C1 (526s Buffalo Creek) | 2022-11-15 08:00 | 2022-11-15 17:30 | N | N | replace tank heater in cap bank breaker | Shunts |  |  | Pre-Condition
ALTALINK | 122s T3 (122s Alberta Newsprint) | 2022-11-15 09:00 | 2022-11-16 18:00 | N | Y | fix leaks, maintain & test T3, replace cracked CT on 13.8 kV bus | Transformer | Fix leaks, maintain & test T3. Replace cracked CT on 13.8kV bus. |  | 240 kV, For Information Only
ATCO | 767s 144kV Bus 700BS1 (767s Oyen), 767s 701T (767s Oyen), 6L09 (767s Oyen - 6L21 tap), 767s 601 (767s Oyen) | 2022-11-15 11:00 | 2022-11-24 16:59 | N | N | transfer load to 2000S mobile sub to complete protection upgrade and new 700PT installation & 6L09D8 repair | Bus, Transformer, Line, Circuit Breaker | Transfer load to 2000S mobile sub to complete Protection Upgrade and new 700PT installation & 6L09D8 repair. Due to the AltaLink 275s5 OOS Nov 24  27, 2022  Nov 23, 2022 17:00 - Contract GOI to 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 701TD. Oyen 144kV bus will be brought back into service for this time and connection to 7L760 and 7L132 will be restored. Isolation points contracted to 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 701TD There is a small chance that the 144kV PT will not be in service by this time, so 7L132/7L760 zone 2 protection may be relied on for Oyen area outage for the duration of this outage. Nov 28, 2022 08:00 - Expand outage to original Isolation points; 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 7L132D1, & 767S 7L760D1 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BHE | 719s Rattlesnake Ridge | 2022-11-15 13:00 | 2022-11-15 14:00 | N | N | communication outage | Station |  |  | Affects Visibility, Restricts Generation
EPCOR | 805s T4 (805s Jasper) | 2022-11-16 06:00 | 2022-11-17 17:00 | N | Y | protection upgrade projects - arc flash protection removal | Transformer | Jasper TX4: Arc Flash Protection Removal Protection Upgrade Projects |  | 240 kV, Pre-Condition
ALTALINK | 345s T1 (345s Hornbeck) | 2022-11-16 07:00 | 2022-11-16 12:00 | N | N | installing bird cover-up | Transformer |  |  | For Information Only
ALTALINK | 749AL (267s Killarney Lake - 749L tap), 267s 749A (267s Killarney Lake) | 2022-11-16 07:00 | 2022-11-16 17:00 | N | N | strain insulator replacement | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 254s 2162X (254s Coaldale) | 2022-11-16 07:00 | 2022-11-17 15:00 | N | Y | replace the existing Inivien | Circuit Breaker | Transmission Constraint record created. Replace the existing Inivien. The current Telus leased line will be replaced with a direct trip using customer communications. |  | Restricts Generation
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2022-11-16 08:00 | 2022-11-16 18:00 | N | N | 5 sub DFR commissioning | Line, Circuit Breaker | 5 Sub DFR Commissioning. |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek) | 2022-11-16 08:00 | 2022-11-16 18:00 | N | Y | open 887L at 48s for MPLS upgrades | Line | WEBOMS ID 12695773 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 135s 20 (135s Conrad) | 2022-11-16 08:30 | 2022-11-16 15:30 | N | Y | 342L meter replacement | Circuit Breaker | 342L Meter replacement. Requires breaker outage to complete CT work for new metering module install Transmission Constraint record created. |  | Pre-Condition, Restricts Generation
ATCO | 7L133 (786s High Level - 828s Sulphur Point), 786s 704 (786s High Level) | 2022-11-16 08:30 | 2022-11-16 11:30 | N | Y | PRC-005 - 704 trip coil testing | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L59 (786s High Level - 7L59 tap), 786s 701 (786s High Level) | 2022-11-16 14:00 | 2022-11-16 17:00 | N | Y | PRC-005 - 701 trip coil testing | Line, Circuit Breaker |  | PRC-005 - 701 Trip coil testing | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s CGB1 (987s Clover Bar) | 2022-11-17 07:00 | 2022-11-18 16:00 | N | Y | P&C/SCADA RTU bus extension cut overs | Circuit Breaker |  |  | Restricts Generation
EPCOR | 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale) | 2022-11-17 07:00 | 2022-11-17 17:00 | N | N | K724 outage for switching school training | Line, Circuit Breaker | Kennedale: K724 Outage for Switching School Training. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2022-11-17 07:30 | 2022-11-17 16:30 | N | N | transformer installation | Shunts | installing a control power isolation transformer on the newly installed 267s752 |  | Pre-Condition
ENMAX | 31.3TR (SS-31) | 2022-11-17 08:00 | 2022-11-17 12:00 | N | N | oil sampling MT, TC, filmax LTC oil filtration maintenance | Transformer | Oil Sampling MT, TC. Filmax LTC Oil Filtration Maintenance  31.3-TC |  | For Information Only
ENMAX | 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5) | 2022-11-17 08:00 | 2022-11-17 18:00 | N | N | 5 Sub DFR commissioning | Line, Circuit Breaker | 5 Sub DFR Commissioning. |  | For Information Only, Pre-Condition
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek) | 2022-11-17 08:00 | 2022-11-18 17:00 | N | N | replacement of equipment | Line | Replace dead-end and jumper insulators at structures 1 & 23 and replace insulators at structure 84. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.4TR (SS-14) | 2022-11-17 08:00 | 2022-11-17 16:00 | N | N | relay, protection testing, firmware upgrade | Transformer | Relay, Protection Testing, Firmware upgrade - 14RLY138-14.4TR S SEL |  | For Information Only
ALTALINK | 180L (15s Fort Macleod - 180AL tap) | 2022-11-17 10:00 | 2022-11-17 15:00 | N | N | testing | Line | Customer Request from 604s to open south portion of line to conduct testing in coordination with the AESO for their voltage oscillation issues. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 31.2TR (SS-31) | 2022-11-17 12:00 | 2022-11-17 16:00 | N | N | oil sampling MT, TC | Transformer |  |  | For Information Only
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial), 77s 352 (77s Sagitawah), 77s 552 (77s Sagitawah), 77s 798N (77s Sagitawah) | 2022-11-18 07:00 | 2022-11-21 13:00 | N | N | 77s15 structure needs to be leveled due to frost heave | Line, Circuit Breaker, Switch | 77s15 structure needs to be leveled due to frost heave. Switch and base to be removed, supporting legs to be cut and leveled. Switch will be re-installed and timed. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | HLD1 RESC Hilda Wind | 2022-11-18 08:00 | 2023-03-21 16:00 | N | N | P2254 RESC Hilda MPC Wind. 100 MW. ISD November 25, 2022 | Unit
ENMAX | 38.2TR (SS-38) | 2022-11-18 08:00 | 2022-11-18 16:00 | N | N | relay, protection testing, firmware upgrade | Transformer | Relay, Protection Testing, Firmware upgrade - 38RLY138-38.2TR S SEL. |  | For Information Only
ALTALINK | 421s T2 (421s Hays), 421s 467E (421s Hays) | 2022-11-18 12:30 | 2022-11-22 17:30 | N | Y | maintenance | Transformer, Circuit Breaker | T2 maintenance, replace LAs on T2, install bird cover, replace switches (421s14, 421s27), switch maintenance (421s18) |  | Restricts Generation
EPCOR | 72MG16 (Garneau - Meadowlark) | 2022-11-19 07:00 | 2022-11-19 17:00 | N | N | line impedance testing | Line | MG16: Line Impedance Testing |  | For Information Only, Pre-Condition
ALTALINK | 74s 2052 (74s Janet) | 2022-11-19 07:30 | 2022-11-24 16:30 | N | Y | replace 74s2052 breaker protection module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 433L (291s Cochrane - AML 793s Horse Creek) | 2022-11-19 08:00 | 2022-11-19 17:00 | N | N | replace insulators at 433L structure 3 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane) | 2022-11-20 07:00 | 2022-11-20 18:00 | N | N | fire mitigation to replace crossarm, insulators and x-brace on structure 860L108 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 816s P2402 (816s Petrolia), 816s P2403 (816s Petrolia), 816s PDS11 (816s Petrolia), 814s BDS20 (814s Bellamy) | 2022-11-21 07:00 | 2022-12-02 17:00 | N | Y | Petrolia PDS4, PDS5, PDS11 LCR | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Wiskey Jack), 1047s GS001 (1047s Wiskey Jack), 1047s GS002 (1047s Wiskey Jack), 1047s GD003 (1047s Wiskey Jack) | 2022-11-21 08:00 | 2022-11-29 16:00 | N | Y | close open point 'H' | Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ENMAX | 2.1TR (SS-2) | 2022-11-21 08:00 | 2022-11-24 16:00 | N | N | relay, protection testing | Transformer | Relay, Protection Testing. 2RLY138-2.1TR B, 2RLY138-2.1TR A |  | For Information Only
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2022-11-21 08:00 | 2022-11-26 14:08 | N | Y | T6 will be isolated for repairs and maintenance | Transformer | Non-Significant Outage: T6 will be isolated for repairs and maintenance The following breakers will be operated: 6335 @ Plant 31 Substation 635 @ Plant 31 Substation The following disconnect switches will be operated: 634 @ Plant 31 Substation The following transformers will be isolated: T6 @ Plant 31 Substation The following generators will be islanded: G6 @ Plant 31 Substation |  | Restricts Generation
ENMAX | 1.7TR (SS-1) | 2022-11-21 08:00 | 2022-11-21 12:00 | N | N | oil sampling MT, TC, bushing, check reversing switch | Transformer | Oil Sampling MT, TC, Bushing. Check Reversing Switch |  | For Information Only
ENMAX | 162.3TR (SS-162), 162B138-RB85 (SS-162), 162B138-RB86 (SS-162), 162MD138-162.3TR (SS-162) | 2022-11-21 08:00 | 2022-11-23 18:00 | N | N | 162 sub 138 kV DFR installation, relay, lockout testing | Transformer, Circuit Breaker, Switch | 162 Sub 138kV DFR Installation. Relay, Lockout Testing. 162RLY138-162. C60-8, C60-16 |  | For Information Only
ENMAX | 5B138-5BT12 (SS-5) | 2022-11-21 08:00 | 2022-11-21 18:00 | N | N | 5 sub DFR commissioning | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, CascadeP | 1168L (39s Bickerdike - 1047s Whisky Jack), 1047s GS005 (1047s Whisky Jack), 1047s GS006 (1047s Whisky Jack), 1047s GD015 (1047s Whisky Jack) | 2022-11-21 08:00 | 2022-12-04 16:00 | N | Y | close open point 'F' | Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ALTALINK, CascadeP | 1084L (39s Bickerdike - 1047s Whisky Jack), 1047s GS003 (1047s Whisky Jack), 1047s GS002 (1047s Whisky Jack), 1047s GD006 (1047s Whisky Jack) | 2022-11-21 08:00 | 2022-12-07 16:00 | N | Y | close open point 'O' | Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2022-11-21 08:00 | 2022-11-28 17:00 | N | Y | line mitigation, cross arm replacement | Line |  | Line mitigation, Cross arm replacement | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 21.4TR (SS-21), 21.61L (SS-21 - SS-34), 15.60L (SS-15 - SS-21), 21B69-21.4TR (SS-21), 21B69-15.60 (SS-21), 21B69-21.61 (SS-21), 15B69-15.60 (SS-15), 34B69-21.61 (SS-34) | 2022-11-21 08:00 | 2022-11-24 16:00 | N | N | SS21 SW62 replacement and oil sampling 21.4TR MT and 15.60L tower inspections | Transformer, Line, Circuit Breaker | 21sub SW62 replacement. 21 Sub SW 63-Retrieve Nameplate Info. Oil Sampling 21.4TR MT. 15.60L tower inspections |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR, ATCO | 635EDD-1000 PT-1000 (635EDD-1000), 635EDD-1000 635-952-635PT-1000 (635EDD-1000), 635EDD-1000 635-752-635PT-1000 (635EDD-1000), 9520 (635EDD-1000), 2005s 1000D1 (2005s Secord) | 2022-11-21 08:00 | 2022-11-23 20:00 | N | Y | replace the leaking opening dashpot on the 260 kV breaker | Transformer, Circuit Breaker, Switch | Replace the leaking opening dashpot on the 260kV breaker |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 180L (928s East Stavely - 180AL tap), 180L (255s Vulcan - 928s East Stavely), 197L (349s Stavely - 928s East Stavely), 255s 34 (255s Vulcan), 349s Stavely, 928s East Stavely, 928s 180X (928s East Stavely), 349s 10 (349s Stavely), 349s 14 (349s Stavely), 349s 20 (349s Stavely), 349s 4044 (349s Stavely), 349s T1 (349s Stavely), 349s 197 (349s Stavely) | 2022-11-21 08:30 | 2022-11-21 15:30 | N | N | urgent 928s E Stavely 928s180X needs adustment | Line, Circuit Breaker, Station, Switch, Transformer | We are adding the following short notice outage to the schedule for Monday Nov 21st. This is to maintain system reliability as currently if the switch is opened due to real time events by our operators restoration will be delayed due to field staff & bucket trucks needing to be dispatched to assist closing the switch. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2022-11-21 09:30 | 2022-11-23 17:00 | N | Y | meter upgrade and P&C cutovers at Castledowns | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 848s 902T (848s Ruth Lake), 848s 604 (848s Ruth Lake), 848s 606 (848s Ruth Lake), 848s 402 (848s Ruth Lake), 848s 602TD (848s Ruth Lake) | 2022-11-21 10:00 | 2022-11-22 17:30 | N | Y | 72 kV rigid bus repair work | Transformer, Circuit Breaker, Switch |  | 72KV Rigid bus repair work. | 240 kV, Pre-Condition
ALTALINK | 202L (58s Edson - 178s Cynthia), 58s 202X (58s Edson), 178s 202N (178s Cynthia) | 2022-11-21 10:15 | 2022-11-25 17:00 | N | N | replacement of 58s202x CTs | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 89s 652 (89s Ellerslie) | 2022-11-21 11:30 | 2022-11-24 17:30 | N | Y | 1st trip & PRC5 maintenance & change leaking capacitors | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2022-11-21 12:00 | 2022-11-28 16:00 | N | Y | line mitigation | Line |  | Line Mitigation | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 720s 902 (720s Wabasca) | 2022-11-21 12:00 | 2022-11-22 17:00 | N | Y | 902 breaker SCADA control upgrade | Circuit Breaker |  | 720s SCADA control upgrades to 902 BKR | 240 kV, For Information Only
ALTALINK | 13s 138kV Bus 1 (13s Deerland), 808L (13s Deerland - 808AL tap), 13s 452 (13s Deerland), 13s 152 (13s Deerland), 13s 552 (13s Deerland), 13s 808N (13s Deerland) | 2022-11-21 12:00 | 2022-11-24 18:00 | N | N | component replacements | Bus, Line, Circuit Breaker, Switch | Component Replacement's 808L Str's Range 1-75, Bus outage required due to proximity |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 805L (86s Bigstone - 964s Pigeon Lake) | 2022-11-21 12:00 | 2022-11-22 18:00 | N | N | urgent repair on 805L2, 69, 89, 163 arm change | Line | URGENT *P5 Urgent Repair on 805L2, 69, 89, 163 Arm Change. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 320p 152 (320p Keephills) | 2022-11-21 12:30 | 2022-12-01 18:00 | N | Y | replacing breaker control and breaker fail relays with new C60 module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 657s T1 (657s Summerside) | 2022-11-22 07:00 | 2022-11-22 17:00 | N | Y | tap changer maintenance | Transformer | Summerside TX1 Tap Changer Maintenance |  | 240 kV, Pre-Condition
ALTALINK | 150L (20s Ghost - 150AL tap), 20s 150 (20s Ghost) | 2022-11-22 07:00 | 2022-11-29 18:00 | N | N | testing new line protection | Line, Circuit Breaker | Complete cutovers/End to end testing of new line protection and Breaker fail.CT contribution to B bus Diff |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 87s 2352 (87s Gaetz) | 2022-11-22 07:30 | 2022-11-22 12:30 | N | Y | investigate low oil/nitrogen situation | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 5B138-5BT7 (SS-5) | 2022-11-22 08:00 | 2022-11-22 18:00 | N | N | 5 sub DFR commissioning | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 40.1TR (SS-40) | 2022-11-22 08:00 | 2022-11-22 16:00 | N | N | oil sampling MT, TC. gas relays testing | Transformer | Oil Sampling MT, TC. Gas relays testing - 40.1TR |  | For Information Only
ALTALINK | 1080L (SS-25 - SS-65) | 2022-11-22 08:00 | 2022-12-12 08:00 | N | Y | urgent work to replace 1080L cables | Line | urgent work to replace 1080L cables into C25s - Taken OOS in real time on 22-10-13 |  | 240 kV, Pre-Condition
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 2022-11-22 11:00 | 2022-11-22 17:00 | N | Y | substation rebuild project | Line | 862S S. Bezanson Substation Rebuild Project, Tap down mobile 902s from 7L32. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
BHE | 719s Rattlesnake Ridge | 2022-11-22 13:00 | 2022-11-22 14:00 | N | N | communication outage | Station |  |  | Affects Visibility, Restricts Generation
ALTALINK | 13s Deerland | 2022-11-22 13:00 | 2022-11-22 15:00 | N | N | 1 to 2 hours outage to 13s station service | Station | 13s Station Service - De Energize Fortis taking a 1-2 hour outage on their feeder 7926T in order to allow Altalink to work on 808L STR 3 that is overtop of their Feeder. There will be a 1 to 2 hours outage to 13s station service during this time because the station service will be on the Fortis feed SST position as this overlaps with ongoing SAP 279975 808L &13s 138kV B1 - GOI Nov 21 - 25 |  | For Information Only
ALTALINK | 423L (212s N.E. Lacombe - 332s Ellis), 212s 423 (212s N.E. Lacombe), 332s 423 (332s Ellis) | 2022-11-22 13:00 | 2022-11-22 17:30 | N | N | replace tank heater | Line, Circuit Breaker | Transmission constraint record created |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap) | 2022-11-23 07:00 | 2022-11-25 18:00 | N | N | replace stub pole and install new ground rod at structure 30 and replace arms and insulators at structure 56 & 57 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21B69-21.4TR (SS-21), 21.1C (SS-21) | 2022-11-23 08:00 | 2022-11-24 16:00 | N | N | 21sub 138 kV bus differential protection outage and relay, protection testing - 21RLY138-21.Z31. 21 sub 94 circuit removal | Circuit Breaker, Shunts |  |  | Pre-Condition
ENMAX | 9.2TR (SS-9) | 2022-11-23 08:00 | 2022-11-23 16:00 | N | N | oil sampling, HV bushings, investigate & repair 9.2TR drag hand reset button | Transformer | Oil Sampling - 9.2TR - HV Bushings. Investigate & Repair 9.2TR Drag Hand Reset Button |  | For Information Only
ALTALINK | 421s T1 (421s Hays) | 2022-11-23 08:30 | 2022-11-23 13:30 | N | N | close open point 'A' | Transformer |  |  | For Information Only
ALTALINK | 74s T1 (74s Janet), 74s 16 (74s Janet) | 2022-11-23 09:30 | 2022-11-23 12:30 | N | Y | trip test 74s16 from new 2052 breaker fail relay | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 275s 2 (275s Jenner) | 2022-11-23 12:00 | 2022-11-23 16:00 | N | Y | circuit cutovers to new L5 B protection | Circuit Breaker | outage on breaker 275s2 (1452) for circuit cutovers to new L5 B protection |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 925L (63s Red Deer - 74s Janet), 74s 2152 (74s Janet), 74s 925N (74s Janet) | 2022-11-23 12:30 | 2022-11-23 15:30 | N | Y | trip test 74s2152 from new 2052 breaker fail relay | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s 2552 (74s Janet) | 2022-11-23 15:30 | 2022-11-23 18:30 | N | Y | trip test 74s2552 from new 2052 breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant Plant) | 2022-11-23 23:00 | 2022-11-24 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant Plant) | 2022-11-24 03:00 | 2022-11-24 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2022-11-24 07:00 | 2022-11-26 17:00 | N | Y | meter upgrade P&C cut-over | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
EPCOR | 657s T2 (657s Summerside) | 2022-11-24 07:00 | 2022-11-25 17:00 | N | Y | SU2T2 termination investigation (hot connection in cell) | Transformer | Summerside TX2: SU2T2 Termination Investigation (Hot Connection in Cell) |  | 240 kV, Pre-Condition
ALTALINK | 275s 5 (275s Jenner) | 2022-11-24 08:00 | 2022-11-28 17:00 | N | Y | C60 protection upgrade and L5 B protection circuit cutovers and testing | Circuit Breaker | Outage on breaker 275s5 (1552) for C60 protection upgrade and L5 B protection circuit cutovers and testing. |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 33s 3 (33s Spray) | 2022-11-24 08:00 | 2022-11-24 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2022-11-24 08:00 | 2022-11-24 16:00 | N | N | crossarm and insulator replacement | Line |  | We will continue our crossarm and insulator replacement project on 6L03 between D3-D4 during this permit. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L275 (799s Coleman - BCH Natal) | 2022-11-24 09:00 | 2022-11-24 19:00 | N | Y | NTL 1VT22 inspection/doble | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 74s 2752 (74s Janet) | 2022-11-24 09:30 | 2022-11-24 12:30 | N | Y | trip test 74s2752 from new 2052 breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s 3752 (74s Janet) | 2022-11-24 12:30 | 2022-11-24 15:30 | N | Y | trip test 74s3752 from new 2052 breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s 552 (74s Janet) | 2022-11-24 15:30 | 2022-11-24 18:30 | N | Y | trip test 74s552 from new 2052 breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap), 767s 701T (767s Oyen) | 2022-11-24 17:00 | 2022-11-28 16:59 | N | N | bring back into service144kV bus and connection to 7L760 and 7L132 will be restored | Line, Transformer | Transfer load to 2000S mobile sub to complete Protection Upgrade and new 700PT installation & 6L09D8 repair. Due to the AltaLink 275s5 OOS Nov 24  27, 2022  Nov 23, 2022 17:00 - Contract GOI to 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 701TD. Oyen 144kV bus will be brought back into service for this time and connection to 7L760 and 7L132 will be restored. Isolation points contracted to 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 701TD There is a small chance that the 144kV PT will not be in service by this time, so 7L132/7L760 zone 2 protection may be relied on for Oyen area outage for the duration of this outage. Nov 28, 2022 08:00 - Expand outage to original Isolation points; 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 7L132D1, & 767S 7L760D1 |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 39.1TR (SS-39) | 2022-11-25 08:00 | 2022-11-25 16:00 | N | N | relay, protection testing, firmware upgrade | Transformer | Relay, Protection Testing, Firmware upgrade - 39RLY138-39.1TR S SEL. |  | For Information Only
ATCO, ALBIAN | 920s 901T (920s Jackpine) | 2022-11-26 05:06 | 2022-12-02 18:00 | N | N | forced outage | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 32.2TR (SS-32) | 2022-11-26 07:00 | 2022-11-26 18:00 | N | N | install ground balls on cable side of SW25 for 32 sub cable trench repairs | Transformer |  |  | For Information Only
ALTALINK | 74s 2152 (74s Janet) | 2022-11-27 07:00 | 2022-12-01 16:30 | N | Y | replace 74s2152 breaker protection module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 895s T3 (895s Suffield) | 2022-11-27 08:00 | 2022-12-10 18:00 | N | Y | close open point at 895s47 to tie in new Fortis feeders at new SWGB and release for salvage required on old wooden 25kV bay | Transformer | Close Open Point at 895s47, tie in new Fortis feeders at new SWGB, release for salvage required on old wooden 25kV bay. Install of new station service tx. create open point on UG cables attached to 895s53. Demo of 895s47 and install continuous bus. |  | Restricts Generation
ENMAX | 32.1TR (SS-32) | 2022-11-27 08:00 | 2022-11-27 18:00 | N | N | fall substation washing 32s 8kV bus | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 320p 240kV Bus A (320p Keephills), 320p 2652 (320p Keephills), 320p 2752 (320p Keephills), 320p 2852 (320p Keephills), 320p PS2 (320p Keephills), 320p 552 (320p Keephills), 320p 152 (320p Keephills), 320p 2052 (320p Keephills) | 2022-11-28 06:30 | 2022-11-29 18:30 | N | Y | breaker fail trip testing | Bus, Circuit Breaker, Transformer | New C60 breaker fail trip testing on breakers 320p552, 320p2052, 320p2652, 320p2852. Commissioning breaker fail from above breakers to new 152 C60 module.. |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | T1 (EPCOR Hardisty) | 2022-11-28 07:00 | 2022-11-28 17:00 | N | N | leak repair | Transformer | Hardisty: TX1 Calisto Leak Repair |  | For Information Only, Pre-Condition
EPCOR | 557s T1 (557s Castle Downs) | 2022-11-28 07:00 | 2022-12-01 17:00 | N | Y | meter upgrade | Transformer | Castledowns: Meter Upgrade P&C Cut-Overs |  | 240 kV, Pre-Condition
ENMAX | 32.3TR (SS-32) | 2022-11-28 07:00 | 2022-11-30 18:00 | N | N | 32 sub cable trench repairs | Transformer |  |  | For Information Only, Pre-Condition
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s CK725 (987s Clover Bar), K724 (Kennedale) | 2022-11-28 07:00 | 2022-12-02 17:00 | N | N | maintenence | Line, Circuit Breaker | CK12: P&C Maintenance and Op Checks |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 5.7TR (SS-5) | 2022-11-28 08:00 | 2022-11-28 18:00 | N | N | 5 Sub DFR commissioning | Transformer |  |  | For Information Only
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain), 813s 705 (813s Little Smoky), 813s 706 (813s Little Smoky), 813s 7L46D1 (813s Little Smoky) | 2022-11-28 08:00 | 2022-12-05 17:00 | N | Y | 813s Little Smokey rebuild | Line, Circuit Breaker, Switch |  | 813S Little Smoky Rebuild Complete 7L46 wiring panel 7P2, 705, 706 CT/PT/P&C wiring. Demo existing wiring/cabling, remove old panel 7G, replace 705CT and 706CT junction boxes. Relay programming and functionality Commission control, alarms and status | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.82L (SS-1 - SS-5) | 2022-11-28 08:00 | 2022-11-30 18:00 | N | N | 1-5 sub DTT modification | Line |  |  | For Information Only
ENMAX | 162.4TR (SS-162), 162B138-RB94 (SS-162), 162B138-RB92 (SS-162) | 2022-11-28 08:00 | 2022-12-01 18:00 | N | N | 138kV DFR installation | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 9L46 (932s Pemukan - 959s Lanfine), 959s 904 (959s Lanfine), 959s 905 (959s Lanfine), 932s 905 (932s Pemukan), 932s 906 (932s Pemukan), 6L12 (774s Monitor - 6L25 tap), 6L12 (775s Sullivan Lake - 6L25 tap) | 2022-11-28 08:00 | 2022-12-15 10:00 | N | Y | line termination to 363S Sedalia on 9L46 Sharp Hills project - | Line, Circuit Breaker | Sharp Hills Wind Farm Project Outage for Line termination to 363S Sedalia on 9L46 |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 3.82L (SS-3 - SS-8), 8B138-6A0 (SS-8), 8B138-5A0 (SS-8), 5A01 (SS-8), 6A1 (SS-8), 5A10 (SS-8), 3B138-3.82 (SS-3) | 2022-11-28 08:00 | 2022-11-28 16:00 | N | N | GIS maintenance - 8B138-5A0, 8B138-6A0, attach breaker analyzer prior to opening breakers | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
BCH | T2 (BCH Natal), 60CB2 (BCH Natal) | 2022-11-28 09:00 | 2022-12-02 17:00 | N | Y | transformer inspection/ doble and non-electrical testing BC maintenance does not affect Alberta ATC | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 740L (39s Bickerdike - 58s Edson), 202L (58s Edson - 178s Cynthia), 58s T1 (58s Edson), 58s 1 (58s Edson), 58s 202X (58s Edson), 58s 740X (58s Edson), 58s 138kV East Bus (58s Edson) | 2022-11-28 09:15 | 2022-11-28 16:45 | N | N | replacement of 58s9 | Line, Transformer, Switch, Circuit Breaker, Bus | Stage 1 , Create open point A to allow replacement of 58s9 During West bus outage |  | Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 370s T3 (370s North Lethbridge), 370s 2152 (370s North Lethbridge), 370s 852 (370s North Lethbridge), 370s 1252 (370s North Lethbridge), 370s 25 (370s North Lethbridge) | 2022-11-28 11:00 | 2022-12-01 17:30 | N | Y | replacement of the 370s25 post insulators adjustment of switch | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell), 244s 152 (244s Bowmanton), 244s 252 (244s Bowmanton), 244s 1035 (244s Bowmanton) | 2022-11-28 12:00 | 2022-12-05 18:00 | N | Y | damper replacement between Structures #32-243 & 368-389 | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 997L (71s Lamoureux - 430s Ursus) | 2022-11-28 12:00 | 2022-12-02 18:00 | N | Y | component replacements on 997L | Line | Component Replacements on 997L ( Str's Range 9-22) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
BHE | 719s RTU/SCADA (719s Rattlesnake Ridge) | 2022-11-28 13:00 | 2022-12-01 14:00 | N | N | uploading updates | Terminal Equipment |  |  | Affects Visibility, Restricts Generation
ATCO | 767s 144kV Bus 700BS1 (767s Oyen), 7L760 (767s Oyen - 7LA760 tap), 6L09 (767s Oyen - 6L21 tap), 767s 701T (767s Oyen), 767s 601 (767s Oyen), 767s 701TD (767s Oyen), 767s 601TD (767s Oyen), 767s 701 (767s Oyen), 767s 702 (767s Oyen) | 2022-11-28 17:00 | 2022-12-09 17:00 | N | N | transfer load to 2000S mobile sub to complete protection upgrade and new 700PT installation & 6L09D8 repair | Bus, Line, Transformer, Circuit Breaker, Switch | Transfer load to 2000S mobile sub to complete Protection Upgrade and new 700PT installation & 6L09D8 repair. Due to the AltaLink 275s5 OOS Nov 24  27, 2022  Nov 23, 2022 17:00 - Contract GOI to 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 701TD. Oyen 144kV bus will be brought back into service for this time and connection to 7L760 and 7L132 will be restored. Isolation points contracted to 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 701TD There is a small chance that the 144kV PT will not be in service by this time, so 7L132/7L760 zone 2 protection may be relied on for Oyen area outage for the duration of this outage. Nov 28, 2022 08:00 - Expand outage to original Isolation points; 6L09 6L09D7,767S 501B, 767S 501X, 767S 502B, 767S 502X, 767S 7L132D1, & 767S 7L760D1 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 58s 138kV West Bus (58s Edson), 58s C1 (58s Edson), 890L (58s Edson - 207s Pinedale), 671L (39s Bickerdike - 58s Edson), 58s T2 (58s Edson), 58s 890 (58s Edson), 58s 671 (58s Edson), 58s 2 (58s Edson), 58s 3 (58s Edson) | 2022-11-29 07:15 | 2022-11-29 14:45 | N | N | stage 2: create open point B | Bus, Shunts, Line, Transformer, Circuit Breaker, Switch | Stage 2, Create open point B to allow restoration of 25kV Bus while replacing 58s3 |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 275s 2 (275s Jenner) | 2022-11-29 08:00 | 2022-11-29 15:00 | N | Y | circuit cutovers to new L5 B protection | Circuit Breaker |  | Outage on breaker 275s2 (1452) for circuit cutovers to new L5 B protection | 240 kV, Contingency Requires Mitigation
ALTALINK | 83s 67 (83s Taber), 83s C2 (83s Taber) | 2022-11-29 08:00 | 2022-11-29 17:30 | N | N | gas top up | Circuit Breaker, Shunts |  | Gas top up (Cap Bank currently out of service) | Pre-Condition
ENMAX | 1.85L (SS-1 - SS-8), 8B138-1A0 (SS-8), 8B138-2A0 (SS-8), 1A10 (SS-8), 2A1 (SS-8), 1A01 (SS-8) | 2022-11-29 08:00 | 2022-11-29 16:00 | N | N | maintenance GIS | Line, Circuit Breaker, Switch |  | GIS maintenance - 8B138-1A0, 8B138-2A0. Attach breaker analyzer prior to opening breakers. | Contingency Requires Mitigation, Firm Load Loss
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2022-11-29 08:00 | 2022-12-09 15:00 | N | N | cross arm & insulator replacement project | Line |  | GOI required on 7L760 for cross arm & insulator replacement project. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L82 (788s Hotchkiss - 855s Hamburg), 788s 705 (788s Hotchkiss) | 2022-11-29 09:30 | 2022-12-02 17:00 | N | Y | 705 breaker PRC005 and maintenance | Line, Circuit Breaker |  | 705 Breaker PRC005 and Maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 58s 138kV West Bus (58s Edson), 671L (39s Bickerdike - 58s Edson), 890L (58s Edson - 207s Pinedale), 58s T2 (58s Edson), 58s 890 (58s Edson), 58s 671 (58s Edson), 58s 2 (58s Edson), 58s C1 (58s Edson) | 2022-11-29 13:00 | 2022-12-07 09:30 | N | N | stage 3: replacement of switches and LA | Bus, Line, Transformer, Circuit Breaker, Switch, Shunts |  | Stage 3, Replacement of switches: 58s12, 58s143, 58s9, and 58s3. Also includes the replacement of single phase LA on 58s890 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Whisky Jack), 39s 26 (39s Bickerdike), 39s 29 (39s Bickerdike), 1047s GS001 (1047s Whisky Jack), 1047s GS002 (1047s Whisky Jack), 1047s GD003 (1047s Whisky Jack), 39s 1135 (39s Bickerdike) | 2022-11-29 16:00 | 2022-12-04 17:00 | N | Y | functional testing for new 1135L protections | Line, Circuit Breaker, Switch |  | Complete functional testing for new 1135L protections, | 240 kV
EPCOR | 657s T3 (657s Summerside) | 2022-11-30 07:00 | 2022-11-30 17:00 | N | Y | rad valve bolt install | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 320p 152 (320p Keephills), 320p 252 (320p Keephills) | 2022-11-30 07:30 | 2022-11-30 18:00 | N | Y | breaker fail trip testing | Circuit Breaker | New C60 breaker fail trip testing on breakers 320p252, 320p452, TAU G1 Shutdown scheme as well as commissioning main and backup breaker fail from above breakers to new 152 C60 module. Commissioning existing 240B G1 A/B protections to new 152 C60 module.. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ALTALINK | 275s 8 (275s Jenner) | 2022-11-30 08:00 | 2022-11-30 12:00 | N | Y | circuit cutovers and trip testing | Circuit Breaker | Outage on breaker 275s8 (1652) for circuit cutovers and trip testing to new 1552 breaker fail protection. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 20s T5 (20s Ghost), 20s 8 (20s Ghost) | 2022-11-30 08:00 | 2022-11-30 16:00 | N | N | trip testing from, replace cable to oil temp gauge | Transformer, Circuit Breaker | Trip testing from A Bus protection. Update T5 & VR1 NE Alarming to new standard, replace cable to Oil Temp gauge (if procured in time). Test new alarms to EMS. |  | For Information Only
ENMAX | 8.1TR (SS-8), 8.2TR (SS-8), 8B138-6A0 (SS-8), 8B138-7A0 (SS-8), 6A01 (SS-8), 6A02 (SS-8), 6A10 (SS-8), 7A1 (SS-8), 7A11 (SS-8) | 2022-11-30 08:00 | 2022-11-30 16:00 | N | N | GIS switch maintenance 8SW6A81 | Transformer, Circuit Breaker, Switch | GIS Switch maintenance 8SW6A81 |  | For Information Only
ALTALINK | 62s T3 (62s Brazeau Plant), 62s 31 (62s Brazeau Plant) | 2022-11-30 09:00 | 2022-11-30 17:30 | N | Y | urgent gas top up | Transformer, Circuit Breaker | Urgent 62s31 gas top up, low breaker. P5 urgent low gas situation. if the gas gets too low the breaker won't operate |  | 240 kV, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2022-11-30 11:00 | 2022-11-30 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 20s 452 (20s Ghost), 418L (20s Ghost - 189L tap) | 2022-11-30 13:00 | 2022-11-30 16:00 | N | N | complete functional testing from relocated A87/138B bus protection | Circuit Breaker, Line | Complete functional testing from relocated A87/138B Bus protection. |  | Pre-Condition, Affects Cranking Path
EPCOR | 657s SU2403 (657s Summerside) | 2022-12-01 07:00 | 2022-12-01 17:00 | N | Y | emergency - low SF6 gas | Circuit Breaker | 657s SU2403 (657s Summerside) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 665s T1 (665s Dome) | 2022-12-01 07:00 | 2022-12-01 17:00 | N | Y | surge arrestor measurements | Transformer | Dome TX1: Surge Arrestor Measurements w/Engineering |  | 240 kV, Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo) | 2022-12-01 07:15 | 2022-12-14 17:45 | N | Y | phase 3 of 927L project between structures 33-301 - replacing insulation, cold end hardware, OHSW assemblies, spacer assemblies, find, fix and splice the wire core between 33-44 | Line | Phase 3 of 927L project between Structures 33-301, (work include replacing insulation, replacing cold end hardware, replacing OHSW assemblies, replacing spacer assemblies, find, fix and splice the wire core between 33-44) |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek), 20s 859E (20s Ghost), AML 793s 859W (AML 793s Horse Creek) | 2022-12-01 08:00 | 2022-12-01 11:00 | N | N | complete CT contribution and functional testing to relocated A Bus protection | Line, Circuit Breaker | Complete CT contribution and functional testing to relocated A Bus protection. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 252 (74s Janet) | 2022-12-01 08:00 | 2022-12-01 12:30 | N | Y | dashpot top up and counter | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.84L (SS-1 - SS-5) | 2022-12-01 08:00 | 2022-12-02 18:00 | N | N | DTT modification | Line |  |  | For Information Only, Pre-Condition
ENMAX | 1.83L (SS-1 - SS-8), 8B138-3A0 (SS-8), 8B138-4A0 (SS-8), 3A01 (SS-8), 3A10 (SS-8), 4A1 (SS-8) | 2022-12-01 08:00 | 2022-12-01 16:00 | N | N |  | Line, Circuit Breaker, Switch | GIS Maintenance - 8B138-3A0, 8B138-4A0. 8MD138-4a02 would not open |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 250p 22 (250p Bighorn Plant) | 2022-12-01 09:00 | 2022-12-01 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 74s 2052 (74s Janet), 925L (63s Red Deer - 74s Janet), 63s 925X (63s Red Deer), 74s 925N (74s Janet) | 2022-12-01 09:30 | 2022-12-01 12:30 | N | Y | trip test 74s2052 from new 2152 breaker fail relay | Circuit Breaker, Line, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, ENMAX | 74s 2252 (74s Janet), 1003L (74s Janet - SS-25), 74s 1003X (74s Janet), 25MD240-1003 (SS-25) | 2022-12-01 12:30 | 2022-12-01 15:30 | N | Y | trip test 74s2252 from new 2152 breaker fail relay | Circuit Breaker, Line, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 113L (20s Ghost - 33s Spray), 20s 113 (20s Ghost), 33s 113 (33s Spray) | 2022-12-01 13:00 | 2022-12-01 16:00 | N | N | complete CT contribution and functional testing to relocated A Bus protection | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
ATCO | 959s SVC (959s Lanfine) | 2022-12-02 08:00 | 2023-01-25 11:40 | N | Y | svc tripped, out of service | Shunts |  |  | For Information Only
ALTALINK | 56L (20s Ghost - 245s Seebe), 20s 56 (20s Ghost) | 2022-12-02 08:00 | 2022-12-02 11:00 | N | N | cut over CT contribution to A87/138B summation module and functional testing to relocate A Bus protection | Line, Circuit Breaker | Cut over CT contribution to A87/138B summation module and functional testing to relocate A Bus protection. |  | Pre-Condition
ATCO | 7L128 (802s Michichi Creek - 963s Coyote Lake) | 2022-12-02 09:00 | 2022-12-02 15:26 | N | N | replace 2 switch blades, 1 jumper and paddle on 7L128D3 due to damage | Line |  | Replace 2 switch blades, 1 jumper and paddle on 7L128D3 due to damage. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 824s RTU/SCADA (824s Fieldgate), 834s RTU/SCADA (834s Wesley Creek), 659s RTU/SCADA (659s Pegasus Lake) | 2022-12-02 10:00 | 2022-12-02 17:00 | N | N | network maintenance | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 17s 8 (17s Benalto) | 2022-12-02 10:26 | 2022-12-05 18:00 | N | Y | emergency outage in real time operations | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2022-12-03 06:15 | 2022-12-06 20:25 | N | N | re-locating structures 281-285 with new structures | Line | Crews will be re-locating structures 281-285 with new structures | finished early. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 33s 6 (33s Spray) | 2022-12-03 07:00 | 2022-12-03 18:00 | N | Y | maintenance | Switch | TAU Requested Generator brushgear Outage |  | Restricts Generation
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 43B138-33.84 (SS-43), 33B138-33.84 (SS-33), SW84 (SS-33) | 2022-12-04 08:00 | 2022-12-08 16:00 | N | N | 33.84L relocation | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33B138-33.83 (SS-33), 41B138-33.83 (SS-41) | 2022-12-04 08:00 | 2022-12-04 16:00 | N | N | 33.84L relocation | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Whisky Jack), 1047s GS001 (1047s Whisky Jack), 1047s GS002 (1047s Whisky Jack), 1047s GD003 (1047s Whisky Jack) | 2022-12-04 17:30 | 2022-12-10 07:00 | N | Y | advice held until the customer at 1047s is ready to energize dates are TBA | Line, Circuit Breaker, Switch | Advice held until the customer at I_1047s is ready to energize dates are TBA |  | 240 kV
ALTALINK, CascadeP | 1168L (39s Bickerdike - 1047s Whisky Jack), 39s 1652 (39s Bickerdike), 39s 1752 (39s Bickerdike), 39s 1168 (39s Bickerdike), 1047s GD015 (1047s Whisky Jack), 1047s GS005 (1047s Whisky Jack), 1047s GS006 (1047s Whisky Jack) | 2022-12-04 17:30 | 2022-12-07 17:00 | N | Y | complete functional testing for new 1168L protections | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T2 (Meadowlark) | 2022-12-05 07:00 | 2022-12-07 17:00 | N | N | 15 kV bus decom work | Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.1TR (SS-32) | 2022-12-05 07:00 | 2022-12-07 18:00 | N | N | 32 sub cable trench repairs | Transformer |  |  | For Information Only
EPCOR | 816s T2 (816s Petrolia), 816s P2404 (816s Petrolia), 816s P2405 (816s Petrolia), 816s ELSP72 (816s Petrolia) | 2022-12-05 07:00 | 2022-12-09 17:00 | N | Y | Petrolia PDS8, PDS9 LCR | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | 987s T3 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2022-12-05 07:00 | 2022-12-05 17:00 | N | Y | Cloverbar: CDS22 repair | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.84L (SS-2 - SS-8), 8B138-1A0 (SS-8), 8B138-7A0 (SS-8), 7A1 (SS-8), 7A10 (SS-8), 7A01 (SS-8), 1A1 (SS-8) | 2022-12-05 08:00 | 2022-12-07 16:00 | N | N | GIS switch maintenance | Line, Circuit Breaker, Switch | GIS Switch maintenance. 8SW1A1, 8SW7A01_7A53, 8SW7A10_7A52, 8SW7A2, 8SW7A8, 8SW7A1_7A51 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 36.3TR (SS-36) | 2022-12-05 08:00 | 2022-12-08 16:00 | N | N | relay protection testing | Transformer | Relay, Protection Testing - 36RLY138-36.3TR B SEL, 36RLY138-36.3TR A GE |  | For Information Only
ENMAX | 65B138-D81 (SS-65) | 2022-12-05 08:00 | 2022-12-09 16:00 | N | N | trip circuit testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ENEL | GRZ1 Grizzly Bear Wind | 2022-12-05 08:00 | 2023-03-12 16:00 | N | N | P1250 Wild Run Grizzly Bear Wind. 120 MW. ISD December 01, 2022, P2065 Wild Run Grizzly Bear Wind Phase 2, 32 MW. ISD December 12, 2022 | Unit
ENMAX | 1.8TR (SS-1) | 2022-12-05 08:00 | 2022-12-06 19:02 | N | N | oil sampling | Transformer |  | Extended by TFO | For Information Only
ENMAX | 162B138-RB83 (SS-162) | 2022-12-05 08:00 | 2022-12-06 16:00 | N | N | relay protection testing | Circuit Breaker | Relay, Protection Testing - 162RLY138-162.C60-6 |  | Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2022-12-05 09:00 | 2022-12-15 20:00 | N | N |  | Line | 735L GOI is required for the Under-built Violations. Crews will also complete structure replacement on structures 735L 71-83 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 801s 701T (801s Anderson), 801s 711 (801s Anderson), 801S 701TD (801s Anderson) | 2022-12-05 10:00 | 2022-12-06 17:30 | N | N | repair leaks on breaker 711 | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ATCO | 7L92 (709s Vegreville - 7LA92 tap) | 2022-12-05 10:00 | 2022-12-08 17:00 | N | N | clearance mitigation | Line | {OUTAGE REASON: We require a GOI on 7L92 for clearance mitigation / pole change.} |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 330p RTU/SCADA (330p Genesee) | 2022-12-05 12:00 | 2022-12-05 18:00 | N | N | upgrades on the SCADA RTU | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2022-12-05 12:00 | 2022-12-12 16:00 | N | Y | line mitigation | Line | {OUTAGE REASON: Line Mitigation} |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2022-12-06 07:00 | 2022-12-08 14:00 | N | N | replace structures 97 and 9 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 611L (186s Dry Creek - 391S Balzac) | 2022-12-06 07:15 | 2022-12-08 17:45 | N | N | line move | Line | Line Move; moving Str53 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2022-12-06 08:00 | 2022-12-09 18:00 | N | Y | repair SVC thyristor fail | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2022-12-06 08:00 | 2022-12-12 17:00 | N | Y | line mitigation, cross arm replacement | Line | {OUTAGE REASON: Line mitigation, Cross arm replacement} |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
AESO-SC | OATI | 2022-12-06 18:00 | 2022-12-06 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2022-12-07 06:30 | 2022-12-08 16:30 | N | N | repair T1 leaks and site checks | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia) | 2022-12-07 07:00 | 2022-12-07 11:00 | N | Y | Petrolia: 1044L 240CVT67 repair | Line |  | Back early | 240 kV, For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft), RW727 (Rossdale), W725 (Woodcroft), WDS9 (Woodcroft) | 2022-12-07 07:00 | 2022-12-09 17:00 | N | N | RW3: P&C maintenance | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 58s 138kV West Bus (58s Edson), 671L (39s Bickerdike - 58s Edson), 890L (58s Edson - 207s Pinedale), 58s T2 (58s Edson), 58s C1 (58s Edson), 58s 671 (58s Edson), 58s 890 (58s Edson), 58s 2 (58s Edson), 58s 9 (58s Edson) | 2022-12-07 07:45 | 2022-12-07 14:45 | N | N | stage 4, close open point B on 25 kV side | Bus, Line, Transformer, Shunts, Circuit Breaker, Switch | Stage 4, Close Open Point B |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 162B138-RB84 (SS-162) | 2022-12-07 08:00 | 2022-12-08 16:00 | N | N | relay, protection testing - 162RLY138-162.C60-7 | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 12.1TR (SS-12) | 2022-12-07 08:00 | 2022-12-08 16:00 | N | N | tapchanger and switch maintenance | Transformer | Tapchanger maintenance. 12.1TR Investigate BA & BB Breaker Rosettes. Check Reversing Switch |  | For Information Only
ALTALINK | 336s T1 (336s Fincastle), 336s 752 (336s Fincastle) | 2022-12-07 08:00 | 2022-12-08 17:30 | N | N | replace old malfunctioning tapchanger controller on VR1 with newer model | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 102s 552 (102s Langdon) | 2022-12-07 08:30 | 2022-12-07 17:30 | N | Y | CT top up, inspections | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 719L (378s Shell Caroline - 719BL tap) | 2022-12-07 09:00 | 2022-12-07 17:00 | N | N | 719L required out of service due to slow fault clearing 9448R Leslieville Radio - 9263R Strachan radio repair | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ALTALINK | 244s 552 (244s Bowmanton), 251s 552 (251s Whitla) | 2022-12-07 09:30 | 2022-12-09 17:30 | N | Y | install/upgrade of 983L B Protection; B 983L protection cutovers to 244s552 & 251s552 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 405s C1 (405s Waupisoo) | 2022-12-07 09:30 | 2022-12-07 17:30 | N | N | investigate breaker trouble alarm, time & adjust breaker and reset timing alarm parameter | Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 213s T1 (213s Hughenden), 213s 352 (213s Hughenden) | 2022-12-07 10:00 | 2022-12-27 18:00 | N | N | replace feeder cables, install and commission new VT6 & breaker maintenance | Transformer, Circuit Breaker | Replace L7 feeder cables. Install and commission new VT6 & breaker maintenance switch 43M/2202. Install and test new settings on existing T1 'A', T1 'B', & L7 (213s2202) feeder protection. Commissioning and functional testing of new A27 module. RSLD1 to be implemented at the end of the outage. |  | For Information Only
ALTALINK, CascadeP | 1084L (39s Bickerdike - 1047s Whisky Jack), 1047s GS002 (1047s Whisky Jack), 1047s GS003 (1047s Whisky Jack), 1047s GD006 (1047s Whisky Jack), 39s 33 (39s Bickerdike), 39s 1052 (39s Bickerdike), 39s 1084 (39s Bickerdike) | 2022-12-07 16:00 | 2022-12-10 17:00 | N | Y | complete functional testing for new 1084L protections | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 701L (223s Strome - 7LA701 tap) | 2022-12-07 16:00 | 2022-12-12 16:00 | N | Y | forced outage | Line |  |  | For Information Only
ALTALINK, CascadeP | 1168L (39s Bickerdike - 1047s Whisky Jack), 1047s GD015 (1047s Whisky Jack) | 2022-12-07 17:30 | 2022-12-11 09:59 | N | Y | advice held until 1047s is ready to be energized | Line, Switch |  |  | 240 kV, For Information Only
ENMAX | 26.2TR (SS-26) | 2022-12-08 04:30 | 2022-12-15 16:00 | N | N | forced outage pressure relief device failure | Transformer |  |  | For Information Only
ALTALINK | 39s 752 (39s Bickerdike) | 2022-12-08 06:30 | 2022-12-08 18:00 | N | N | wire CT for L4 RAS relay from 752 for Cascade project | Circuit Breaker | Wire CT for L4 RAS relay from 752 for Cascade Project |  | Contingency Requires Mitigation
ALTALINK | 58s 138kV East Bus (58s Edson), 740L (39s Bickerdike - 58s Edson), 58s T1 (58s Edson), 58s 740X (58s Edson), 58s 1 (58s Edson), 39s 740 (39s Bickerdike), 202L (58s Edson - 178s Cynthia), 58s 202X (58s Edson) | 2022-12-08 07:15 | 2022-12-08 14:45 | N | N | Stage 5 , close open point A | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Restricts Generation,Affects Cranking Path
ENMAX | 21B69-21.4TR (SS-21), 21.1C (SS-21) | 2022-12-08 08:00 | 2022-12-08 16:00 | N | N | 138 kV bus differential relay Z31, Z31 86 lockout relay outage. relays, lockout testing 21RLY138-21.Z31 | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 281s 252(281s Johnson) | 2022-12-08 08:30 | 2022-12-08 17:30 | N | Y | repair heater | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 879L (368s Burdett - 879L tap), 368s 879 (368s Burdett) | 2022-12-08 11:30 | 2022-12-08 17:30 | N | Y | 1st trip with minor maintenance, fix DC ground, repair melted terminal blocks in breaker | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | EP 803s T3 (EP 803s Lambton) | 2022-12-09 07:00 | 2022-12-15 17:00 | N | Y | Lambton TX3 zone for scaffold install for emergency bushing replacement | Transformer |  |  | 240 kV, For Information Only
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 813L (146s MacDonald - 241s Uplands), 146s T1 (146s Macdonald), 241s 813L (241s Uplands), 370s 667 (370s North Lethbridge) | 2022-12-09 08:00 | 2022-12-09 12:00 | N | Y | energize transformer 146S T1 | Line, Transformer, Circuit Breaker | OPEN END OUTAGE TO ENERGIZE 146S T1 NEW TRANSFORMER |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L92 (777s Vilna - 7LA92 tap) | 2022-12-09 09:00 | 2022-12-09 17:00 | N | N | clearance mitigation / pole replacement | Line | {OUTAGE REASON: We require GOI on 7L92 for clearance mitigation / pole replacement.} |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2022-12-09 20:43 | 2022-12-10 15:27 | N | Y | forced outage | Shunts |  |  | Pre-Condition
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Whisky Jack), 39s 26 (39s Bickerdike), 39s 29 (39s Bickerdike), 39s 1135 (39s Bickerdike) | 2022-12-10 08:00 | 2022-12-10 09:00 | N | Y | open breakers in order to close 39s1135 to energize new 1047s substation via 1135L at 39s | Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen) | 2022-12-10 08:00 | 2022-12-11 17:00 | N | N | T&O to commission relays and settings | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon), 937L (5s East Calgary - 102s Langdon) | 2022-12-10 08:00 | 2022-12-11 16:00 | N | Y | line clearance mitigation | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 244s 652 (244s Bowmanton), 251s 652 (251s Whitla) | 2022-12-10 09:30 | 2022-12-12 17:30 | N | Y | install / upgrade of 983L B Protection; B 983L Protection Cutovers to 244s652 and 251s652 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L63 (788s Hotchkiss - 7LA63 tap), 7LA63 (783s Cadotte River - 7L63 tap), 788s 703 (788s Hotchkiss), 783s 701TD (783s Cadotte River) | 2022-12-10 10:00 | 2022-12-11 17:30 | N | Y | urgent - replace failed 7L63D2 switch | Line, Circuit Breaker, Switch |  |  | Over/Under Voltage, Pre-Condition
ALTALINK | 1084L (39s Bickerdike - 1047s Whisky Jack) | 2022-12-10 17:00 | 2022-12-11 07:00 | N | Y | advice held until 1047s is ready to be energized | Line |  |  | 240 kV, For Information Only
ALTALINK | 225L (225s Magrath - 225AL tap), 225L (67s Stirling - 225AL tap), 225s 225E (225s Magrath), 67s 225 (67s Stirling) | 2022-12-11 07:00 | 2022-12-20 15:12 | N | Y | 225s to 67s (225L) line protection replacement | Line, Circuit Breaker |  | Returned Early. | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK, CascadeP | 1084L (39s Bickerdike - 1047s Whisky Jack), 39s 33 (39s Bickerdike), 39s 1052 (39s Bickerdike), 39s 1084 (39s Bickerdike) | 2022-12-11 08:00 | 2022-12-11 09:00 | N | Y | open breakers in order to close 39s1084 to phase new 1084L at 39s while backfed from new 1047s | Line, Circuit Breaker, Switch | Email notification on Nov. 9th |  | 240 kV, Contingency Requires Mitigation
ALTALINK, CascadeP | 1168L (39s Bickerdike - 1047s Whisky Jack), 39s 1752 (39s Bickerdike), 39s 1652 (39s Bickerdike), 39s 1168 (39s Bickerdike) | 2022-12-11 10:00 | 2022-12-11 10:30 | N | Y | open breakers in order to close 39s1168 to phase new 1168L at 39s while backfed from new 1047s | Line, Circuit Breaker, Switch | Email notification on Nov. 9th |  | 240 kV, Pre-Condition
ALTALINK | 421s C1 (421s Hays) | 2022-12-12 03:10 | 2023-04-26 17:30 | N | N | forced outage due to breaker 421s 30 failure | Shunts | The capacitor bank at 421s Hays is out of service since October 26, 2022. 421s30 breaker is not working and we have to replace the breaker. To replace the 421s30 breaker we would have to trench new cables. AML is planning to do the trenching at the end of April or beginning of May when the frost is out of the ground. |  | Pre-Condition
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2022-12-12 07:00 | 2022-12-15 15:00 | N | Y | replace 2 of 3 external current transformers off of 60s50 | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
EPCOR | 1164L (816s Petrolia - EP Riverview), 816s PDS6 (816s Petrolia), 816s PDS7 (816s Petrolia), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia), 816s PDS12 (816s Petrolia) | 2022-12-12 07:00 | 2022-12-16 17:00 | N | Y | PDS6, PDS7 LCR's, PDS12 disconnect maintenance | Line, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 36.1TR (SS-36) | 2022-12-12 07:00 | 2022-12-14 18:00 | N | N | cable trench repairs | Transformer |  |  | For Information Only
ENMAX | 21B69-21.4TR (SS-21), 21.1C (SS-21), 21.4TR (SS-21) | 2022-12-12 08:00 | 2022-12-12 16:00 | N | N | 138kV bus differential relay Z31 | Circuit Breaker, Shunts, Transformer | 138kV Bus Differential Relay Z31. Remove/Install and 50L CT input. Altalink Request. 60s50 CT replacement at 60s/21s Aeroplane corner |  | Pre-Condition
ENMAX | 32.3TR (SS-32) | 2022-12-12 08:00 | 2022-12-13 16:00 | N | N | relay, protection testing | Transformer |  |  | For Information Only
ATCO | 7L760 (767s Oyen - 7LA760 tap), 767s 702 (767s Oyen) | 2022-12-12 08:00 | 2022-12-28 13:00 | N | N | cross arm & insulator replacement project | Line, Circuit Breaker | {OUTAGE REASON: GOI required on 7L760 for cross arm & insulator replacement project.} |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8B138-5A0 (SS-8) | 2022-12-12 08:00 | 2022-12-12 16:00 | N | N |  | Circuit Breaker | GIS maintenance - 8B138-5A0. Attach breaker analyzer prior to opening breaker. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB132 (SS-162), 162B240-RB133 (SS-162), 162MD240-918L (SS-162) | 2022-12-12 08:00 | 2022-12-13 18:00 | N | Y | 162 Sub 240kV DFR installation | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 240kV North Bus (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25B240-D138 (SS-25) | 2022-12-12 08:00 | 2022-12-19 13:00 | N | Y | replace 1080L cables preparation work | Bus, Circuit Breaker | Altalink Outage. Urgent work to replace 1080L cables into E25s. Extend existing GOI to include enmax 240kV West bus and 1080L diameter at E25s. Enmax to ground C25s on 240kV West bus as well as a set between SW146 and SW147 (1080L diameter). Expansion of GOI Zone for Urgent work to replace 1080L cables into C25s for scaffolding for cable pull. |  | 240 kV, For Information Only, Pre-Condition
ENMAX | 65B240-D132 (SS-65) | 2022-12-12 08:00 | 2022-12-12 12:00 | N | Y | trip circuit testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 837s 701T (837s Mahihkan), 837s 704 (837s Mahihkan) | 2022-12-12 09:45 | 2022-12-13 12:00 | N | N | RTXP switch replacements for 701T | Transformer, Circuit Breaker | {OUTAGE REASON: RTXP switch replacements for 701T} |  | For Information Only
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2022-12-12 10:00 | 2022-12-13 17:00 | N | N | crossarm and insulator replacement | Line | {OUTAGE REASON: We will continue our crossarm and insulator replacement project on 6L03 between D3-D4 during this permit.} |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 701L (223s Strome - 395s North Holden), 223s T2 (223s Strome), 223s T3 (223s Strome), 223s 39 (223s Strome), 223s 44 (223s Strome), 223s 51 (223s Strome), 395s 701X (395s North Holden) | 2022-12-12 10:00 | 2022-12-12 16:00 | N | N | repair 223s36 and 223s45 switches, repair 701L conductor connections to 223s45 | Line, Transformer, Circuit Breaker | Repair 701L conductor connections to 223s45. Disable 27/138B RAS protection to facilitate this outage |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 65B240-D133 (SS-65) | 2022-12-12 12:00 | 2022-12-12 16:00 | N | Y | trip circuit testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 650s 752 (650s Hansman Lake) | 2022-12-12 12:30 | 2022-12-18 07:59 | N | Y | replacement of 650s752 | Circuit Breaker | Replacement of 650s752. Transition to (282311) 650s 240kV Bus 1 & T1 - GOI. |  | 240 kV, Contingency Requires Mitigation
BHE | 719s RTU/SCADA (719s Rattlesnake Ridge) | 2022-12-12 13:00 | 2022-12-12 14:00 | N | N | uploading updates | Terminal Equipment |  |  | Affects Visibility, Restricts Generation
ALTALINK | 283s T1 (283s Violet Grove) | 2022-12-13 06:30 | 2022-12-16 18:00 | N | N | install new tap changer filter on T1. | Transformer | Replace T1 138kV LAs, install new tap changer filter on T1. |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 52s T2 (52s East Industrial) | 2022-12-13 07:00 | 2022-12-14 17:00 | N | Y | relay repair and disconnect maintenance | Transformer | East Industrial: TX2 Leaking Gas Relay Repair and E2T2GS Disconnect Maintenance |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 74s C4 (74s Janet) | 2022-12-13 08:00 | 2022-12-13 17:30 | N | Y | urgent - replace a leaking capacitor | Shunts | replace a leaking capacitor that is causing an imbalance with the cap bank |  | 240 kV, Pre-Condition
ALTALINK | 138s R1 (138s Windy Flats) | 2022-12-13 08:00 | 2022-12-13 17:30 | N | Y | urgent repair | Shunts | Urgent repair to fix oil temp alarms, replace with new temperature device RTD. |  | 240 kV
ENMAX | 34.1TR (SS-34) | 2022-12-13 08:00 | 2022-12-14 16:00 | N | N | relay protection testing | Transformer | Relay, Protection Testing, Firmware upgrade - 34RLY69-34.1TR B SEL. |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 37.2TR (SS-37) | 2022-12-13 08:00 | 2022-12-13 16:00 | N | N | Oil Sampling MT, TC. Check Reversing Switch | Transformer |  |  | Creates Radial Feeds, Firm Load Loss
Saskpower | SaskPower C1S | 2022-12-13 08:00 | 2022-12-15 18:00 | N | Y | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage C1S Line, PRPS 1 Unit, PRPS 2 Unit, CWPPS Wind, BHWPS WIND, GSWPS Wind |  | For Information Only, Limits ATC
ENMAX | 65B240-D134 (SS-65) | 2022-12-13 08:00 | 2022-12-13 12:00 | N | Y | trip circuit testing | Circuit Breaker | Trip Circuit Testing 65B240-D134 |  | For Information Only
ATCO | 959s SVC (959s Lanfine) | 2022-12-13 10:00 | 2022-12-16 17:30 | N | Y | fan replacemnet | Shunts | {OUTAGE REASON: - Replace Fan in Group 5 at 959S Lanfine SVC - Low Conductivity Alarm at 959S Lanfine SVC - Conductivity Sensor Fault at 959S Lanfine SVC - DI Tank 2 Depleted at 959 Lanfine SVC Isolate SVC trips as necessary} |  | For Information Only
ENMAX | 65B240-D135 (SS-65) | 2022-12-13 12:00 | 2022-12-13 16:00 | N | Y | trip circuit testing 65B240-D135 | Circuit Breaker |  |  | For Information Only
ATCO | 837s 702T (837s Mahihkan), 837s 705 (837s Mahihkan) | 2022-12-13 12:05 | 2022-12-14 17:00 | N | N | switch replacement | Transformer, Circuit Breaker | {OUTAGE REASON: RTXP switch replacements for 701T} |  | For Information Only
ALTALINK | 671L (39s Bickerdike - 58s Edson), 39s 37 (39s Bickerdike), 39s 38 (39s Bickerdike), 58s 671 (58s Edson), 39s 671 (39s Bickerdike) | 2022-12-14 07:00 | 2022-12-14 17:30 | N | N | complete CT cutovers for new RAS relays, wiring and status testing for new RAS relays, add new 43Ms to 39s37, 39s38, 58s671 | Line, Circuit Breaker, Switch | Complete CT cutovers for new RAS relays, Wiring and status testing for new RAS relays, Add new 43Ms to 39s37, 39s38, 58s671 |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK, ENMAX | 752L (653s Summit - 752AL tap), 653s 752 (653s Summit) | 2022-12-14 07:15 | 2022-12-15 17:45 | N | N | repair OHSW bond (str 107, 108, 110, 111, 113, 115) | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 162B240-RB135 (SS-162), 162B240-RB136 (SS-162), 162MD240-932L (SS-162) | 2022-12-14 08:00 | 2022-12-15 18:00 | N | Y | 162 Sub 240 kV DFR installation | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 6L03 (757s Battle River - 6L17 tap) | 2022-12-14 08:00 | 2022-12-15 16:00 | N | N | cross arm and insulator replacement on 6L03 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 949L (275s Jenner - 306s Halsbury), 306s 240CB1 (306s Halsbury), 275s 949 (275s Jenner), 306s 240MOD4 (306s Halsbury) | 2022-12-14 08:00 | 2022-12-14 17:00 | N | N | complete line construction deficiencies and clean up on customer owned portion of 949L | Line, Circuit Breaker, Switch | Customer request-Complete line construction deficiencies and clean up on customer owned portion of 949L |  | 240 kV, For Information Only
ENMAX | 65B138-D83 (SS-65) | 2022-12-14 08:00 | 2022-12-14 12:00 | N | N | trip circuit testing 65B138-D83 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 28s T1 (28s West Brooks) | 2022-12-14 08:30 | 2022-12-14 16:30 | N | Y | replace oil in T/C | Transformer |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 924L (102s Langdon - 356s Milo) | 2022-12-15 06:15 | 2022-12-15 18:45 | N | Y | changing out dead-end insulators on structures | Line | 924L (102s - 356s) GOI Phase 3 of 924L project between Structures 90, 92, (work include changing out dead-end insulators on structures) |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 36.2TR (SS-36) | 2022-12-15 07:00 | 2022-12-19 18:00 | N | N | 36 sub cable trench repairs | Transformer |  |  | For Information Only
ENMAX | 21.1C (SS-21), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21MD138-21.4TR (SS-21), SW64 (SS-21) | 2022-12-15 08:00 | 2022-12-15 16:00 | N | N | CT and protection work | Shunts, Transformer, Circuit Breaker, Switch | 21B69-21.4TR (SS-21). 21.1C (SS-21) 138kV Bus Differential Relay Z31. Remove/Install and 50L CT input. Altalink Request. 60s50 CT replacement at 60s/21s Aeroplane corner |  | Overload, Pre-Condition
ENMAX | 8B138-6A0 (SS-8) | 2022-12-15 08:00 | 2022-12-15 16:00 | N | N | relay lockout and protection testing | Circuit Breaker | Relay, Lockout Testing. 86BF-6a0. Relay, Protection Testing - 8RLY138-6A0-BKRFAIL |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 28s 22 (28s West Brooks) | 2022-12-15 09:00 | 2022-12-15 17:00 | N | N | replace heater | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow), 397s 720N (397s Benbow), 347s 720X (347s AML Fox Creek) | 2022-12-16 07:00 | 2022-12-16 17:30 | N | N | complete CT cutovers for new RAS relays | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2022-12-16 07:00 | 2022-12-16 18:00 | N | N | urgent repair replace broken guy wire 740L15 | Line |  |  | Pre-Condition
ATCO, WHEL | 7L85 (801s Anderson - ATC 803s Bullpound), 7L85 (804s Wintering Hills - 7LA85 tap), 7LA85 (981s Badlands - 7L85 tap), 981s Badlands, 804s 702 (804s Wintering Hills), ATC 803S 7L85D2 (ATC 803s Bullpound), ATC 803S 701TCS (ATC 803s Bullpound), ATC 803s 701T (ATC 803s Bullpound), 981s 144CB1 (981s Badlands), 981s T1 (981s Badlands) | 2022-12-16 08:00 | 2022-12-16 16:00 | N | Y |  | Line, Station, Circuit Breaker, Switch, Transformer | {OUTAGE REASON: Install switch whips on 7L85D2 & 7L85D3. Add whips to existing jaw assembly. 981S Badlands will be forced offline for the duration of this outage.} |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ENMAX | 8.4TR (SS-8) | 2022-12-16 08:00 | 2022-12-16 16:00 | N | N | 86 lockout protection relay testing | Transformer | 8.4TR 138kV 86 Lockout Protection. Relay, Lockout Testing. 138kV 86-8.4TR |  | For Information Only
ATCOP, BSPL | BLS1 Barlow Solar | 2022-12-16 08:00 | 2022-12-30 18:00 | N | N | P2459 ENMAX Barlow Park DER Solar, 27 MW. ISD December 23, 2023. | Unit
ALTALINK | 673L (131s Moon Lake - 283s Violet Grove), 283s 673 (283s Violet Grove) | 2022-12-16 16:30 | 2022-12-20 15:53 | N | N | replace CT at 283s673 | Line, Circuit Breaker |  | Outage returned early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon), 937L (5s East Calgary - 102s Langdon) | 2022-12-17 06:00 | 2022-12-18 17:00 | N | Y | line clearance mitigation | Line |  | 936L returned late on Dec 18. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 650s 240kV Bus 1 (650S Hansman Lake), 650s T1 (650s Hansman Lake), 650s 252 (650s Hansman Lake), 650s 452 (650s Hansman Lake), 650s 752 (650s Hansman Lake), 650s 1 (650s Hansman Lake), 650s 70 (650s Hansman Lake) | 2022-12-18 08:00 | 2022-12-18 17:00 | N | Y | breaker maintenance | Bus, Transformer, Circuit Breaker, Switch | 240kV Bus 1 outage to facilitate the replacement of 650s752. Reconductor breaker from 650s19 - 650s752. Repair 650s11. Energize 650s752 via 650s452. RSLD 1 to be implemented at the end of the outage. |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 650s 752 (650s Hansman Lake) | 2022-12-18 17:01 | 2022-12-30 16:00 | N | Y | replacement of 650s752 | Circuit Breaker | Replacement of 650s752. Transition to (282311) 650s 240kV Bus 1 & T1 - GOI. |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 199s C1 (199s East Airdrie) | 2022-12-19 07:00 | 2022-12-20 16:00 | N | N | function test new trip and block circuits from new T1 'B' protection | Shunts |  |  | Pre-Condition
EPCOR | 557s CD2403 (557s Castle Downs) | 2022-12-19 07:00 | 2022-12-19 17:00 | N | Y | phase 3 dashpot repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 199s 631 (199s East Airdrie), 631L (186s Dry Creek - 199s East Airdrie) | 2022-12-19 07:00 | 2022-12-19 16:00 | N | N | function test new trip and block circuits from new T1 'B' protection | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge), 733s 701 (733s Simonette), 740s 705 (740s H.R. Milner) | 2022-12-19 08:00 | 2022-12-22 17:00 | N | Y | line mitigation and cross arm replacement | Line, Circuit Breaker | {OUTAGE REASON: Line mitigation, Cross arm replacement} |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L224 (650s Hansman Lake - 774s Monitor) | 2022-12-19 08:00 | 2022-12-22 15:00 | N | Y | cross arm and insulator replacement on 7L224 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L22 (790s Poplar Hill - 7L88 tap), 790s 702 (790s Poplar Hill) | 2022-12-19 10:00 | 2022-12-19 11:00 | N | Y | protection upgrades | Line, Circuit Breaker | Northstone DG at 731S Elmworth Project Protection upgrades |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare), 790s 703 (790s Poplar Hill) | 2022-12-19 13:00 | 2022-12-19 14:00 | N | Y | protection upgrades | Line, Circuit Breaker | Northstone DG at 731S Elmworth Project Protection upgrades |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1080L (SS-25 - SS-65) | 2022-12-19 16:01 | 2023-01-23 07:59 | N | Y | urgent work to replace 1080L cables into C25s | Line |  |  | 240 kV
ATCO | 939s 240kV Bus 900BS2 (939s Livock), 939s 240kV Bus 900BS3 (939s Livock), 9L10 (876s Brintnell - 939s Livock), 939s 903T (939s Livock), 939s 910 (939s Livock), 939s 911 (939s Livock) | 2022-12-20 08:00 | 2022-12-20 17:02 | N | Y | Livock Pile Heaving Project: close jumper, bypass will stay in service 909A and 900D1 will be normally open | Bus, Line, Transformer, Circuit Breaker | {OUTAGE REASON: Livock Pile Heaving Project Close jumper, bypass will stay in service 909A and 900D1 will be normally Open} | Test 2 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 815S 703 (815s Goodfare) | 2022-12-20 09:00 | 2022-12-20 17:00 | N | N | RTXP test switch recall (replacement) - 21A and 21B/ 7L34 at 815s | Circuit Breaker |  |  | Firm Load Loss, Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton) | 2022-12-21 07:58 | 2023-06-14 07:59 | N | N |  | Shunts | 38s 3052 ( 38s East Edmonton) 38s C1 (38s East Edmonton) | Outage extended. | For Information Only, Pre-Condition
ALTALINK | 199s 688 (199s East Airdrie), 688L (199s East Airdrie - 688AL tap) | 2022-12-22 07:00 | 2022-12-22 16:00 | N | N | function test new trip and block circuits from new T1 'B' protection | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L275 (799s Coleman - BCH Natal) | 2022-12-28 09:15 | 2022-12-28 16:45 | N | Y | NTL 1CT22 hotspot repair | Line |  | NTL 1CT22 hotspot repair | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 954L (648s Metiskow - 650s Hansman Lake), 650s 752 (650s Hansman Lake), 650s 852 (650s Hansman Lake), 650s 954 (650s Hansman Lake), 648s T3 (648s Metiskow) | 2022-12-30 16:01 | 2022-12-30 17:00 | N | Y | to facilitate the energization of 650s752 | Line, Circuit Breaker, Switch, Transformer | Job Scope: Require 954L to be deenergized to facilitate the energization of 650s752. Open 650s954 and energize 650s752 via 650s852. RSLD 1 to be implemented at the end of the outage. |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2023-01-03 07:00 | 2023-01-08 16:00 | N | N | installing concrete foundations under existing 7L65 line | Line | {OUTAGE REASON: 7L65 Rebuild Project. Installing concrete foundations under existing 7L65 line} |  | Over/Under Voltage, Overload, Pre-Condition
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2023-01-03 09:00 | 2023-02-03 17:00 | Y | Y | replace end of life structures BC maintenance does not affect the Alberta ATC | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge), 733s 701 (733s Simonette) | 2023-01-03 10:00 | 2023-01-16 09:59 | N | Y | line mitigation, cross arm replacement | Line, Circuit Breaker | {OUTAGE REASON: Line mitigation, Cross arm replacement} | Extended Real Time | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 14.1C (SS-14) | 2023-01-03 12:00 | 2023-01-26 16:00 | N | N | forced outage | Shunts |  | extend | Pre-Condition
ENMAX | 14.2C (SS-14) | 2023-01-03 12:00 | 2023-08-18 00:05 | N | N |  | Shunts | Forced outage.Failed neutral CT | extend | Pre-Condition
AESO-SC | OATI | 2023-01-04 18:00 | 2023-01-04 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  | O | For Information Only
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-01-05 03:00 | 2023-01-05 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 671L (39s Bickerdike - 58s Edson), 58s 671 (58s Edson) | 2023-01-05 07:00 | 2023-01-05 18:00 | N | N | replace jumper stack corona ring on str 129 | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
TRANSALTA | 1045s Garden Plain | 2023-01-06 08:00 | 2023-01-08 18:00 | N | N | complete installation of capacitor banks and other work | Station | complete installation of capacitor banks and other work from January 6 0800 to January 8 1800, 2023 The site capacity will be 0MW. |  | For Information Only
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek), 288s 152 (288s Wolf Creek), 288s 352 (288s Wolf Creek), 288s 1083 (288s Wolf Creek) | 2023-01-07 07:00 | 2023-01-08 18:00 | N | Y | replace insulators at structures 92 & 133 | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 14.3TR (SS-14) | 2023-01-08 08:00 | 2023-01-11 16:00 | N | N | repairs | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion), 710s TLO1_N (710s Vermilion) | 2023-01-08 16:00 | 2023-01-15 17:30 | N | N | installing concrete foundations under existing 7L65 line | Line, Switch | {OUTAGE REASON: 7L65 Rebuild Project. Installing concrete foundations under existing 7L65 line} |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 945L (275s Jenner - 562s Cypress), 275s 5 (275s Jenner), 275s 8 (275s Jenner), 562s 152 (562s Cypress), 562s 252 (562s Cypress), 275s 945N (275s Jenner), 562s 945 (562s Cypress) | 2023-01-09 07:15 | 2023-01-16 13:45 | N | Y | B protection upgrade, reconfigure relay for new TPR circuits | Line, Circuit Breaker, Switch | 945L Outage for L4 B protection upgrade. Second scope - Reconfigure relay for new TPR circuits. | Outage was stopped to provide support due to the frosting event in the area. The planned word was not completed. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
WPHL | ERV5 eReserve5 Hughenden | 2023-01-09 08:00 | 2023-01-23 16:00 | N | N | P2498 Fortis Hughenden 213S DER Battery, ISD Jan 16, 2023 | Unit
ENMAX | 240kV North Bus (SS-162), 138kV North Bus (SS-162), 162.1TR (SS-162), 162B240-RB131 (SS-162), 162B240-RB134 (SS-162), 162B138-RB80 (SS-162), 162B138-RB86 (SS-162), 162B138-RB94 (SS-162), 162MD240-162.1TR (SS-162), 162MD138-162.1TR (SS-162) | 2023-01-09 08:00 | 2023-01-13 18:00 | N | Y | 162 sub 240 kV DFR installation | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 926L (17s Benalto - 310p Sundance) | 2023-01-09 09:30 | 2023-01-09 18:00 | N | Y | replace insulators on structure 464 | Line | Replace insulators on structure 464. See Also SAP:282947 995L (62s-68s-17s) - R/B Required due to proximity to 926L |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib) | 2023-01-09 16:00 | 2023-01-19 11:00 | N | N | cross arm replacement project | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove) | 2023-01-10 07:00 | 2023-01-11 18:00 | N | Y | install bird diverters on crossarms | Line | Install Bird Diverters on Crossarms at Structures 836L144, 145, 146, 147, 148, 149 & 150. |  | Contingency Requires Mitigation, Restricts Generation, Affects Cranking Path
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-01-10 07:30 | 2023-01-11 17:30 | N | Y | urgent replace failed dashpot, possible repair of main drive shaft if damaged | Switch |  |  | Restricts Generation
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2023-01-10 10:00 | 2023-01-16 12:00 | N | Y | pole changes line mitigation | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43) | 2023-01-11 08:00 | 2023-01-11 18:00 | N | N | need to cross the underground for fibre installation | Line |  | Completed early | Creates Radial Feeds, Firm Load Loss
ATCO | 7L121 (860s Crow - 7LA121 tap) | 2023-01-11 08:00 | 2023-02-09 12:00 | N | N | foundation install for new switch 7L121D3 near 2043S | Line | {OUTAGE REASON: 2043S Freer Sub Project Foundation install for new switch 7L121D3 near 2043S} |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s T1 (370s North Lethbridge), 370s 1652 (370s North Lethbridge) | 2023-01-11 08:00 | 2023-01-11 17:00 | N | N | trip test 370s1652 breaker initiated by different relays | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2023-01-12 08:00 | 2023-01-12 17:00 | N | Y | removing MVT1 on 1034L @ 244s | Line | Removing MVT1 on 1034L @ 244s |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale), 763s 603 (763s Hanna) | 2023-01-12 09:30 | 2023-01-13 17:30 | N | N | top up low oil on 603 | Line, Circuit Breaker | {OUTAGE REASON: Top up low oil on 603} |  | Creates Radial Feeds, Firm Load Loss
ALPAC | 282s RTU/SCADA (282s Grassland (Alpac)) | 2023-01-15 01:00 | 2023-01-15 05:00 | N | N | SCADA, internet and phone outage | Terminal Equipment |  |  | For Information Only
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 74s 37.82W (74s Janet) | 2023-01-15 10:00 | 2023-01-15 17:00 | N | Y | re-arranging the lightning arrestors | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Meadowlark) | 2023-01-16 07:00 | 2023-01-19 20:00 | N | N | remove M3T1 cable from Tx1 reactor | Transformer |  | Back early | For Information Only, Pre-Condition
ENMAX | 240kV South Bus (SS-162), 138kV South Bus (SS-162), 162.2TR (SS-162), 162B138-RB83 (SS-162), 162B138-RB84 (SS-162), 162B138-RB92 (SS-162), 162B240-RB133 (SS-162), 162B240-RB136 (SS-162), 162MD240-162.2TR (SS-162), 162MD138-162.2TR (SS-162) | 2023-01-16 08:00 | 2023-01-20 18:00 | N | Y | 240kV DFR installation | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 7.84L (SS-7 - SS-36), 36.81L (44s Bearspaw Plant - SS-36), 36.1TR (SS-36), 36.3TR (SS-36), 36B138-36.81 (SS-36), 36B138-7.84 (SS-36), 36B138-36BT3 (SS-36), 36MD138-36.1TR (SS-36), 36MD138-36.3TR (SS-36) | 2023-01-16 08:00 | 2023-01-19 18:00 | N | Y | maintenence | Line, Transformer, Circuit Breaker, Switch | HV SW Maint. SW81, SW82, SW83, SW87, SW88, SW89, SW90, MD-36.1TR, MD-36.3TR. SW82, SW89, SW90, -Retrieve Nameplate Info. SW82, SW89 stiff gearbox. Check Reversing Switch 36.1, 36.2 |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 808L (13s Deerland - 808AL tap) | 2023-01-16 09:00 | 2023-01-19 08:00 | N | N | component replacement | Line | Component Replacement's 808L Str's Range 1-75 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2023-01-16 10:00 | 2023-01-25 15:00 | N | Y | line mitigation, cross arm replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L153 (609s Wheatland - 804s Wintering Hills) | 2023-01-16 11:16 | 2023-01-22 16:00 | N | N | forced outage | Line | ATCO found three broken structures on the ground and it will be out of service for a few days while repairs are made. |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-01-16 12:00 | 2023-01-19 11:30 | N | N | rebuild 174L from existing structure 174L692 to 174L742 | Line, Circuit Breaker |  | Back early | Over/Under Voltage, Overload, Pre-Condition
ATCO | 720s 502R (720s Wabasca) | 2023-01-16 16:00 | 2023-01-23 16:00 | N | N | forced outage | Shunts | Switch 502RD was damaged during switching. |  | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2023-01-17 07:00 | 2023-01-18 17:30 | N | N | isolate line for Fortis to complete a salvage | Line |  | Isolate 202 Line for Fortis to complete a salvage of Fortis facilities that parallel 202 line in section 27, 28 and 33-52-17 W5. | Pre-Condition, Affects Cranking Path
ALTALINK | 895s T2 (895s Suffield) | 2023-01-17 07:00 | 2023-01-23 14:00 | N | N | connections to new 25kV switchgear building | Transformer |  | Connecting 895s53 and U/G Cable to the new 25kV Switchgear Building | For Information Only
ATCO | 730s 144kV Bus 1 (730s Rycroft), 7L73 (730s Rycroft - 829s Boucher Creek), 730s 703 (730s Rycroft), 730s 704 (730s Rycroft) | 2023-01-17 07:30 | 2023-01-17 17:30 | N | Y | 700BS1 OOS to create open jumper J2 | Bus, Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2023-01-17 08:00 | 2023-01-23 16:00 | N | N | forced outage | Line |  |  | For Information Only
ATCO | 730s 144kV 700BS1 (730s Rycroft), 730s 704 (730s Rycroft), 730s 701T (730s Rycroft), 730s 701TCS (730s Rycroft) | 2023-01-17 17:00 | 2023-01-30 07:29 | N | N | upgrade 700BS1 conductor | Bus, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L29 (946s Oakland - 963s Coyote Lake), 963s 901 (963s Coyote Lake), 963s 9L29D1 (963s Coyote Lake) | 2023-01-18 03:34 | 2023-01-25 18:00 | N | Y | forced outage | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-01-18 10:00 | 2023-01-18 14:00 | N | Y | maintenance | Switch | Advice for TransAlta - Brushgear maintenance |  | Restricts Generation
ATCO | 9L46 (932s Pemukan - 959s Lanfine) | 2023-01-19 07:59 | 2023-01-26 18:00 | N | Y | forced outage | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 13s 138kV Bus 1 (13s Deerland), 808L (13s Deerland - 808AL tap), 13s 152 (13s Deerland), 13s 452 (13s Deerland), 13s 552 (13s Deerland), 13s 808N (13s Deerland) | 2023-01-19 08:00 | 2023-01-21 18:00 | N | N | component replacement's 808L str's range 1-75 | Bus, Line, Circuit Breaker, Switch | Component Replacement's 808L Str's Range 1-75, Bus outage required due to proximity at str 1. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2023-01-19 10:00 | 2023-01-19 14:00 | N | Y | maintenance | Switch | Advice for TransAlta - Brushgear maintenance |  | Restricts Generation
ATCO | 7L50 (757s Battle River - 491L tap) | 2023-01-19 16:55 | 2023-01-19 20:18 | N | Y | forced outage | Line | 7L50 (757s Battle River - 7L50D1) | For a Conductor Check | For Information Only
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.2TR (SS-31), 31.3TR (SS-31), 31B138-24.81 (SS-31), 31B138-31.84 (SS-31), 32B138-31.84 (SS-32), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31), SW83 (SS-31) | 2023-01-21 08:00 | 2023-01-22 18:00 | N | N | HV switch maintenance | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 708L (71s Lamoureux - 708AL tap) | 2023-01-22 07:00 | 2023-01-22 18:00 | N | N | replace crossarms with post stack insulators at structure 29, hardware tighten structure 19 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72MG16 (Garneau - Meadowlark), G721 (Garneau), G726 (Garneau), GDS17 (Garneau) | 2023-01-23 07:00 | 2023-02-08 23:00 | N | N | P&C line protection upgrade cutovers | Line, Circuit Breaker, Switch |  | MG16: P&C Line Protection Upgrade Cutovers | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 803s T3 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton), EP 803s LAB3 (EP 803s Lambton) | 2023-01-23 07:00 | 2023-01-27 17:00 | N | Y | emergency repair | Transformer, Circuit Breaker, Switch | Lambton: Remove scaffold for Emergency Bushing Replacement and LAB3 Repair |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 162B138-RB80 (SS-162) | 2023-01-23 08:00 | 2023-01-24 16:00 | N | N | relay protection testing | Circuit Breaker |  | Relay, Protection Testing - 162RLY138-162.C60-4 | Contingency Requires Mitigation
Syncrude | 222 (Aurora) | 2023-01-23 08:00 | 2023-01-23 15:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 14.83L (SS-14 - SS-36), 14.4TR (SS-14), 14.2TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 36B138-14.83 (SS-36), 14B138-14.83 (SS-14), 14MD138-14.2TR (SS-14), 14MD138-14.4TR (SS-14), SW84 (SS-14) | 2023-01-23 08:00 | 2023-01-24 16:00 | N | N | hv sw maintenence | Line, Transformer, Shunts, Circuit Breaker, Switch | HV SW Maint. SW84, SW85, SW86, MD-14.4, MD-14.2 |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 65B138-D82 (SS-65) | 2023-01-23 08:00 | 2023-01-23 16:00 | N | N | trip circuit testing | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 240kV North Bus (SS-25), 1080L (SS-25 - SS-65), 25B240-D138 (SS-25), 25B240-D139 (SS-25), 25B240-D133 (SS-25), 25B240-D136 (SS-25), 25B240-D142 (SS-25) | 2023-01-23 08:00 | 2023-02-02 09:00 | N | Y | urgent work to replace 1080L cables into C25s for scaffolding for cable terminations | Bus, Line, Circuit Breaker | Expansion of GOI Zone for Urgent work to replace 1080L cables into C25s for scaffolding for cable terminations. |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2023-01-23 10:00 | 2023-01-30 12:00 | N | Y | pole changes line mitigation | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-01-23 12:00 | 2023-01-24 18:00 | N | N | rebuild 174L from existing structure | Line, Circuit Breaker | Rebuild 174L from existing structure 174L692 to 174L742. |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen) | 2023-01-23 12:15 | 2023-01-25 17:00 | N | N | emergency repair | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet) | 2023-01-23 12:30 | 2023-01-23 17:30 | N | N | emergency repair; investigate/test suspected instability on 74sC4 CT | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 275s 1852 (275s Jenner) | 2023-01-24 06:30 | 2023-01-24 12:00 | N | Y | remove old TPR trip from circuit | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SHELL | 847s 201-PTL260-2D1 (847s Muskeg River) | 2023-01-24 07:00 | 2023-01-25 17:00 | N | Y | bay swap to free up the existing 9L66 bay and connect to free bay at Muskeg River Sub for the new line builds for CNRL Horizon | Switch | Bay swap to free up the existing 9L66 bay and connect to free bay at Muskeg River Sub for the new line builds for CNRL Horizon. Contract Line crew will be adding in- line breakers to allow picking up sections of line hot when tapping on to 9L66. |  | 240 kV, Pre-Condition
ENMAX | 65B138-D85 (SS-65) | 2023-01-24 08:00 | 2023-01-24 12:00 | N | N | trip circuit testing 65B138-D85 | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 740s 701 (740s H.R. Milner), 740s 701B (740s H.R. Milner) | 2023-01-24 08:00 | 2023-02-27 17:00 | N | N | perform work on 701B | Circuit Breaker, Switch | COG for Maxim/Milner Power to perform work on 701B Milner Power requested work, They have water piping that ran across the line that they were working on and the piping collapsed onto the line. It has set them back significantly. | Customer outage. | For Information Only
ALTALINK | 275s T2 (275s Jenner), 275s 46 (275s Jenner), 275s 2252 (275s Jenner), 275s 47 (275s Jenner) | 2023-01-24 08:00 | 2023-01-31 12:00 | N | Y | install new reactors, re-configure bus work, install bushing monitors on T2 | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ENMAX | 6.4TR (SS-6) | 2023-01-24 08:00 | 2023-01-24 16:00 | N | N | ABB to inspect shutters | Transformer |  |  | For Information Only
ALTALINK | 275s 1952 (275s Jenner) | 2023-01-24 12:00 | 2023-01-24 17:30 | N | Y | remove old TPR trip from circuit. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 65B138-D84 (SS-65) | 2023-01-24 12:00 | 2023-01-24 16:00 | N | N | trip circuit testing 65B138-D84 | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 163s 1752 (163s Amoco Empress) | 2023-01-25 06:30 | 2023-01-25 12:00 | N | Y | remove old TPR trip from circuit | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
Saskpower | Sask Power PR903 | 2023-01-25 07:00 | 2023-01-26 18:01 | N | Y | maintenance | Circuit Breaker |  |  | Pre-Condition
ENMAX | 162B138-RB84 (SS-162) | 2023-01-25 08:00 | 2023-01-25 12:00 | N | N | trip circuit testing | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 47.1TR (SS-47), 47B138-771/1 (SS-47), 47B138-BT3 (SS-47), 47MD138-47.1TR (SS-47) | 2023-01-25 08:00 | 2023-01-26 18:00 | N | N | switch maintenance | Transformer, Circuit Breaker, Switch | HV SW Maint. SW85, SW84, MD-47.1TR. Check reversing switch 47.1TR. 47.1TR Replace Fan control relay (27-4). |  | For Information Only
ENMAX | 65B240-D130 (SS-65) | 2023-01-25 08:00 | 2023-01-25 12:00 | N | Y | trip circuit testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 162B138-RB86 (SS-162) | 2023-01-25 12:00 | 2023-01-25 16:00 | N | N | trip circuit testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 163s 1552 (163s Amoco Empress) | 2023-01-25 12:30 | 2023-01-25 17:30 | N | Y | remove old TPR trip from circuit | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson) | 2023-01-26 13:00 | 2023-01-26 15:00 | N | N | emergency repairs to restore broken OHSW | Line, Circuit Breaker | Emergency outage to Restore a broken OHSW from SE frost storm damages. Work will only proceed once 9L46 has been returned to service. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 65B240-D131 (SS-65) | 2023-01-27 08:00 | 2023-01-27 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2023-01-27 08:00 | 2023-01-29 17:00 | N | Y | emergency - repair broken shield wires | Line | Emergency outage require to repair broken shield wires on 13L50. Work will not happen until 9L29 and 9L46 are back in service. There are also High winds in the area and the 13L50 outage may need to be pushed if the winds dont die down. |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 1212L (12s Heartland - 89s Ellerslie) | 2023-01-29 07:00 | 2023-02-08 18:00 | N | Y | component replacements on 1212L (structure range 36-146) | Line | Component Replacements on 1212L (Structure Range 36-146) |  | 500 kV, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31.1C (SS-31), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31), SW84 (SS-31) | 2023-01-29 08:00 | 2023-01-29 18:00 | N | N | switch maintenance | Line, Transformer, Shunts, Circuit Breaker, Switch | HV SW Maint. SW84, SW85, SW86, SW89, MD-31.2TR, MD-31.1TR. Check reversing switch 31.1TR, 31.2TR |  | Pre-Condition
ATCO | 730s 144kV 700BS1 (730s Rycroft), 7L73 (730s Rycroft - 829s Boucher Creek), 730s 702T (730s Rycroft), 730s 700 (730s Rycroft), 730s 704 (730s Rycroft), 730s 702 (730s Rycroft), 730s 705 (730s Rycroft) | 2023-01-30 07:30 | 2023-01-31 17:30 | N | N | 700BS1 outage to remove Jumper J2 | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 36.3TR (SS-36) | 2023-01-30 08:00 | 2023-02-02 18:00 | N | N | 36 sub cable trench repairs | Transformer |  |  | For Information Only
ENMAX | 26.1TR (SS-26) | 2023-01-30 08:00 | 2023-01-31 16:00 | N | N | breaker maintenance 26B25-26.111, 26B25-26.112, 26BA25-26.1TR, 26B25-26BT1 | Transformer | 26BA25-26.1TR -Bkr appears misaligned and hard to rack in. LV Breaker Maintenance 26B25-26.111, 26B25-26.112, 26BA25-26.1TR, 26B25-26BT1 |  | For Information Only
ENMAX | 15.62L (SS-15 - SS-16), 16.60L (SS-16 - SS-34), 16.61L (SS-16 - SS-27), 16.1TR (SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27), 16MD69-16.1TR (SS-16), SW71 (SS-16) | 2023-01-30 08:00 | 2023-02-01 12:00 | N | N | HV switch maintenance | Line, Transformer, Circuit Breaker, Switch |  | HV SW Maint. SW61, SW62, SW63, SW67, SW68, SW71, MD-16.1TR | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | AL-1 (Aurora - D05), 211 (Aurora), 213 (Aurora), D05 517 (D05), D05 519 (D05), 89-215 (Aurora), D05 520 (D05), D05 517A (D05), D05 519B (D05) | 2023-01-30 08:00 | 2023-01-31 17:00 | N | Y | maintenance | Line, Circuit Breaker, Switch |  | Outage ended early | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 297s T1 (297s Rimbey) | 2023-01-30 08:00 | 2023-02-02 16:00 | N | N | istall and commission new B27 relay, update settings and commissioning on 5000L SEL351s relay | Transformer | Install and commission new B27 relay, update settings and commissioning on 5000L SEL351s relay. Transfer trip testing to DER client. Implement new undervoltage settings on T1 A protection and commissioning. |  | For Information Only
ATCO, BSRW | 9L46 (932s Pemukan - 959s Lanfine), 959s 904 (959s Lanfine), 959s 905 (959s Lanfine), 932s 905 (932s Pemukan), 932s 906 (932s Pemukan), 363s 52U1 (363s Sharp Hills Wind Farm), 959s 9L46D1 (959s Lanfine), 363s 89U1 (363s Sharp Hills Wind Farm), 932s 9L46D2 (932s Pemukan), 959s TLO-New (959s Lanfine), 932s TLO-New (932s Pemukan) | 2023-01-30 09:30 | 2023-02-10 17:30 | N | Y | tie in 9LA46 and 363s Sedalia to 9L46 | Line, Circuit Breaker, Switch |  | 9L46 outage to tie in 9LA46 and 363s Sedalia to 9L46. COG HAS BEEN REQUESTED FOR 89U1 at 363S. COG will be needed prior to re-energization of 9L46. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2023-01-30 10:00 | 2023-02-08 15:00 | N | Y | line mitigation, cross arm replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater), 808L75C (808AL tap) | 2023-01-30 12:00 | 2023-01-30 17:00 | N | N | gas top up on 171s808E | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-01-30 12:00 | 2023-02-03 18:00 | N | N | rebuild 174L from existing structure | Line, Circuit Breaker | Rebuild 174L from existing structure 174L692 to 174L742. |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L47 (718s Parsons Creek - 848s Ruth Lake), 718s 701 (718s Parsons Creek) | 2023-01-30 16:00 | 2023-02-09 11:00 | N | N | cross arm replacement project on 7L47 | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs), 557s CD2404 (557s Castle Downs), 557s CDDS14 (557s Castle Downs) | 2023-01-31 07:00 | 2023-02-01 17:00 | N | Y | emergency hot connection disconnect repair | Line, Circuit Breaker, Switch | Castledowns: CDDS9 and CDDS14 Emergency Hot Connection Disconnect Repair |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 321s 880 (321s Al Rothbauer), 523s 880 (523s Bullshead) | 2023-01-31 08:00 | 2023-01-31 17:00 | N | Y | implement new Init DDR | Line, Circuit Breaker | Implement new 'Init DDR' from A87L/21/L1, B87L/21/L1, & 11(96/79/25SC)/152. Implement new 'TPR Direct Trip Rx to DDR' from A87L/21/L & B87L/21/L1. Connect L1/152 CT from A87L/21/L1 to new DDR1. Implement 152 Status to new DDR1. Send transfer Trip for trip testing new outputs at 321s |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 1024s RTU/SCADA (1024s Granlea) | 2023-01-31 11:00 | 2023-01-31 15:00 | N | N | making modifications to its SCADA system to better process the setpoint received from the AESO's Wind and Solar Ramp Up Management algorithm | Terminal Equipment | During the window, FMGWGP plans to isolate the SCADA system responsible for distributing the allowed curtailment and perform testing of the added calculation methods. Site will be unresponsive to the curtailment setpoint signal. However, manual changes to the power setpoint is possible through manual operator actions, as required by AESO via ATCO SOC. |  | Affects Visibility
ATCO | 786s 702T (786s High Level) | 2023-02-01 06:46 | 2023-02-06 18:00 | N | N | forced outage | Transformer | The transformer was found spewing oil and had scorch marks on it. The techs are conducting repairs to piping and refilling the transformer. Once this is done, testing will need to be conducted on the transformer. |  | For Information Only
ENMAX | 26.1TR (SS-26) | 2023-02-01 08:00 | 2023-02-03 12:00 | N | N | breaker maintenance 26B25-26.121, 26B25-26.122, 26BB25-26.1TR, 26B25-26BT2 | Transformer | 26BB25-26.1TR -Bkr appears misaligned and hard to rack in. LV Breaker Maintenance 26B25-26.121, 26B25-26.122, 26BB25-26.1TR, 26B25-26BT2 | Extended to complete work. | For Information Only
TRANSALTA | 418s Ardenville | 2023-02-01 09:00 | 2023-02-01 10:00 | N | N | SCADA communication outage | Station | TransAlta is requesting a 1-hour turbine SCADA communication outage on February 1, 2023, at 0900 for server reboot after update. During this time, the site will not be able to follow WPM curtailments. The Wind Control Center will have control over the substation. |  | Affects Visibility
TRANSALTA | 1063s Windrise | 2023-02-01 10:00 | 2023-02-01 13:00 | N | N | communication outage | Station | TransAlta is requesting a 3-hour communication outage at Wind Rise 1053s on February 1 starting at 10:00, for maintenance on the backup electrical circuits the SCADA servers are on. During this time, the site will not respond to WPM curtailments and the Wind Control Center will not have visibility or control over the turbines. There will be personnel on site that can operate breakers in the substation in the event of an emergency. |  | Affects Visibility
TRANSALTA | 528s Blue Trail Wind Farm | 2023-02-01 11:00 | 2023-02-01 12:00 | N | N | SCADA communication outage | Station | TransAlta is requesting a 1-hour turbine SCADA communication outage on February 1, 2023, at 1100 for server reboot after update. During this time, the site will not be able to follow WPM curtailments. The Wind Control Center will have control over the substation |  | Affects Visibility
ENMAX | 16.63L (SS-16 - SS-36), 16.60L (SS-16 - SS-34), 15.62L (SS-15 - SS-16), 16.2TR (SS-16), 36.5TR (ENMAX 36), 16B69-16.60 (SS-16), 16B69-16.63 (SS-16), 34B69-16.60 (SS-34), 36B69-16.63/36.5TR (SS-36), 16MD69-16.2TR (SS-16), SW64 (SS-16) | 2023-02-01 12:00 | 2023-02-03 18:00 | N | N | HV SW maintenance check reversing switch 16.2TR | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354s Summerview | 2023-02-01 13:00 | 2023-02-01 14:00 | N | N | Summerview 2 - SCADA communication outage | Station | TransAlta is requesting a 1-hour turbine SCADA communication outage on February 1, 2023, at 1300 for server reboot after update. During this time, the site will not be able to follow WPM curtailments. The Wind Control Center will not have visibility or control over the turbines but will have control over the substation. |  | Affects Visibility
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2023-02-02 06:28 | 2023-03-23 12:00 | N | Y | forced outage | Shunts, Circuit Breaker |  | The SVC tripped due to loss of coolant, and multiple lane failures. The techs are on site and the vendor has been contacted to help diagnose the issue. | 240 kV, Pre-Condition
ALTALINK | 675L (244s Bowmanton - 321s Al Rothbauer), 244s 2552 (244s Bowmanton), 244s 2652 (244s Bowmanton), 321s 675 (321s Al Rothbauer), 244s 675 (244s Bowmanton) | 2023-02-02 08:00 | 2023-02-02 17:00 | N | Y | implement new Init DDR | Line, Circuit Breaker, Switch | Implement new 'Init DDR' from A21/85/RAS173/L3, B21/85/RAS173/L3, & 11(96/79/25SC)/352. Implement new 'TPR Direct Trip Rx to DDR' from A21/85/RAS173/L3, B21/85/RAS173/L3. Connect L3/152 CT from A21/85/RAS173/L3 to new DDR1. Implement 352 Status to new DDR1. Send transfer Trip for trip testing new outputs at 321s |  | Creates Radial Feeds, Pre-Condition, Affects Cranking Path
ALTALINK | 1080L (SS-25 - SS-65) | 2023-02-02 09:01 | 2023-02-06 07:59 | N | Y | urgent work to replace 1080L cables into C25s | Line | Urgent work to replace 1080L cables into C25s - Taken OOS in real time on 22-10-13 |  | 240 kV
VISIONREQ | 354s Summerview | 2023-02-02 12:00 | 2023-02-02 14:00 | N | N | Summerview 1 - SCADA outage | Station | TransAlta is requesting a 2-hour turbine SCADA outage at Summerview1 on February 2 starting at 1200 for turbine network inspection and maintenance. During this time, the Wind Control Center will not have visibility or control over the turbines but will be able to see and control the substation |  | Affects Visibility
ALTALINK | 132s 51 (132s Ware Junction) | 2023-02-02 12:30 | 2023-02-02 15:00 | N | Y | remove old TPR trip from circuit | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 132s 47 (132s Ware Junction) | 2023-02-02 15:00 | 2023-02-02 17:30 | N | Y | remove old TPR trip from circuit | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENEL, ATCO | 708s T1 (708s Grizzly Bear), 708s 52T1 (708s Grizzly Bear), 7LA65D1 (7LA65 tap) | 2023-02-04 09:00 | 2023-02-04 14:00 | N | N | breaker repairs | Transformer, Circuit Breaker, Switch |  |  | For Information Only, Restricts Generation
SUNCOR | 635EDD-1000 635PT-1003 (635EDD-1000), 635EDD-1000 635-752-142 (635EDD-1000), 635EDD-1000 635-752-143 (635EDD-1000) | 2023-02-05 08:00 | 2023-02-08 17:00 | N | N | downstream 72kV bus outage to tie-in new equipment | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty) | 2023-02-06 07:00 | 2023-02-17 17:00 | N | N | termination repair | Line | Cloverbar: CH11 Termination Repair and CH724 Breaker Fail Op Checks, CH11 Zone P&C Maintenance. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell) | 2023-02-06 07:15 | 2023-02-14 18:29 | N | Y | conductor replacement on 923L(Str 19-25) | Line |  | For 923L(Str 19-25) CRU work - Conductor replacement outage complete. | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, ENMAX | 1080L (SS-25 - SS-65), 65B240-D132 (SS-65), 65B240-D131 (SS-65), 25MD240-1080 (SS-25), 65MD240-1080 (SS-65) | 2023-02-06 08:00 | 2023-02-07 18:00 | N | Y | HV SW maintenance SW133, SW134, MD-1080 | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
SUNCOR | 1024s RTU/SCADA (1024s Granlea) | 2023-02-06 08:00 | 2023-02-07 16:00 | N | N | integrating FMG1's SCADA system with ATCO Control Center (SOC) part 1 | Terminal Equipment | During this window, FMGWGP plans to force a number of values in the plant SCADA system to check connectivity, analog scaling / polarity and binary states with ATCO's SOC. No setpoints / controls will be sent from SOC. The AESO and AltaLink may receive values through its SCADA display that are forced and not representative of real conditions recorded by systems at FMG1. The facility will be brought back online between February 06, 2023 at 04:00 pm and February 07, 2023 at 8:00 am. |  | Affects Visibility
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2023-02-06 08:00 | 2023-02-12 16:00 | N | N | remove falling pole, phasing required across SW85 (SS-26) | Line, Circuit Breaker | Remove falling pole in swamp. Phasing required across SW85@26sub. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 368s T1 (368s Burdett) | 2023-02-06 08:00 | 2023-02-06 16:00 | N | Y | reconfigure CT cores from T1 through the current summation module to A&B 27 and CT testing | Transformer | Reconfigure CT Cores from T1 through the current summation module to A&B 27, CT Testing. |  | Restricts Generation
BCH | 1L274 (BCH Elkford Tap - BCH Greenhills Tap) | 2023-02-06 09:00 | 2023-02-08 16:15 | N | Y | replace structure 23-2. BC maintenance does not affect the Alberta ATC | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK, TRANSALTA | 59s T1 (59s Peigan) | 2023-02-06 09:30 | 2023-02-07 14:30 | N | Y | correct deficiencies | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2023-02-06 10:00 | 2023-02-13 12:00 | N | Y | pole changes line mitigation | Line | Pole Changes Line Mitigation |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 813s 713 (813s Little Smoky), 813s 717 (813s Little Smoky), 813s 714C (813s Little Smoky), 813s 715C (813s Little Smoky), 813s 716C (813s Little Smoky) | 2023-02-06 10:00 | 2023-03-06 10:00 | N | N | wiring panels and relay programming | Circuit Breaker, Shunts | Complete wiring panels 1C/2C, 713, 717, 714, 715, 716, CT/PT/P&C wiring. Demo existing wiring/cabling. 61850 comm ccts. Complete 7L57 wiring panel 7P5, 717, 718 CT/PT/P&C wiring. Demo existing wiring/cabling, remove old panel 3G Relay programming and functionality Commission control, alarms and status |  | For Information Only
ATCO | 780s 705 (780s Lubicon) | 2023-02-06 11:00 | 2023-02-10 16:00 | N | N | RTXP test handle replacement for 50BF/ 705 relay, PRC-005 testing | Circuit Breaker | RTXP test handle replacement for 50BF/ 705 relay, testing PRC-005 Trip Coils |  | Pre-Condition
ALTALINK | 199s C1 (199s East Airdrie) | 2023-02-06 11:00 | 2023-02-07 16:00 | N | N | urgent outage to investigate cap. bank trouble | Shunts |  |  | Pre-Condition
ATCO | 780s 706C (780s Lubicon) | 2023-02-06 11:00 | 2023-02-10 16:00 | N | N | replacing RTXP test handle for all 706C and 706 relays, testing PRC-005 trip coils | Shunts |  |  | Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-02-06 12:00 | 2023-02-10 18:00 | N | N | rebuild 174L from existing structure 174L692 to 174L742 | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
Saskpower | SaskPower A1R | 2023-02-07 07:00 | 2023-02-08 18:00 | N | Y | planned outage | Line |  |  | Limits ATC, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana), 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte), 120s 1152S (120s Picture Butte) | 2023-02-07 07:00 | 2023-02-09 13:00 | Y | Y | PS1 OLTC filter replacement, repair leaks on filters, overload replacements (burnt out coils), complete PS1 A protection change | Line, Transformer, Shunts, Circuit Breaker, Switch | PS1 OLTC filter replacement, repair leaks on filters, overload replacements (burnt out coils). Complete PS1 A protection change out due to relay fail |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 368s T2 (368s Burdett), 368s 42 (368s Burdett) | 2023-02-07 08:00 | 2023-02-07 16:00 | N | Y | reconfigure CT Cores | Transformer, Switch |  | Reconfigure CT Cores from T1 through the current summation module to A&B 27/DER, CT Testing | For Information Only, Pre-Condition
NWE, BHE Canada, BHE | Marias South Series Capacitor, North Series Capacitor (BHE Hay Lake) | 2023-02-07 08:00 | 2023-02-09 15:51 | N | Y | replace circuit boards | Shunts |  |  | 240 kV, Limits ATC
ENMAX | 26.2TR (SS-26) | 2023-02-07 08:00 | 2023-02-07 16:00 | N | N | LV breaker maintenance, 26BA25-26.2TR, 26BB25-26.2TR | Transformer |  |  | For Information Only
ENMAX | 1.8TR (SS-1) | 2023-02-07 08:00 | 2023-02-07 18:00 | N | N | LV breaker maintenance | Transformer |  |  | For Information Only
ALTALINK | 28s T1 (28s West Brooks) | 2023-02-07 09:30 | 2023-02-07 17:00 | N | Y | replace probe (high temp alarms) | Transformer |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
AESO-SC | OATI | 2023-02-07 18:00 | 2023-02-07 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 1080L (SS-25 - SS-65) | 2023-02-07 18:01 | 2023-02-12 12:59 | N | Y | urgent work to replace 1080L cables into C25s | Line | Urgent work to replace 1080L cables into C25s - Taken OOS in real time on 22-10-13 |  | 240 kV
ENMAX | 47.2TR (SS-47), 47B138-771 (SS-47), 47B138-BT3 (SS-47), 47MD138-47.2TR (SS-47) | 2023-02-08 08:00 | 2023-02-09 18:00 | N | N | HV SW maintenance heck reversing switch | Transformer, Circuit Breaker, Switch | HV SW Maint. SW82, SW83, MD-47.2TR. Check reversing switch. |  | For Information Only
ALTALINK, ENMAX | 1080L (SS-25 - SS-65), 240kV West Bus (SS-25), 25B240-D139 (SS-25), 25B240-D142 (SS-25), 25B240-D133 (SS-25), 25B240-D136 (SS-25), 25B240-D138 (SS-25), 25MD240-1080 (SS-25) | 2023-02-08 13:00 | 2023-02-23 13:00 | N | Y | expansion of GOI zone for urgent work to replace 1080L cables into C25s for scaffolding for cable terminations | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T2 (Strathcona), S723 (Strathcona), SAB2 (Strathcona), S722 (Strathcona) | 2023-02-09 07:00 | 2023-02-24 17:00 | N | N | protection upgrade cutovers | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1206L (12s Heartland - 89s Ellerslie) | 2023-02-09 07:00 | 2023-02-17 18:00 | N | Y | component replacements on 1206L (structure range 2-144) | Line |  |  | 500 kV, Pre-Condition
SUNCOR | 635EDD-1000 635PT-1002 (635EDD-1000), 635EDD-1000 635-752-132 (635EDD-1000), 635EDD-1000 635-752-133 (635EDD-1000), 635EDD-1000 635PS-1041 (635EDD-1000) | 2023-02-09 08:00 | 2023-02-13 17:00 | N | N | downstream 72kV bus outage to tie-in new equipment | Transformer, Circuit Breaker, Switch |  | Extending outage to complete work. | Prevents Normal Events
NWE | NWE Great Falls | 2023-02-09 08:00 | 2023-02-10 17:00 | N | Y | maintenance - Great Falls to Landers Fork line | Station |  |  | 240 kV, Limits ATC, Pre-Condition
SUNCOR | 1024s Granlea | 2023-02-09 09:00 | 2023-02-09 17:00 | N | N | integrating FMG1's SCADA system with ATCO Control Center (SOC) part 2 | Station | During this window, FMGWGP plans to perform functional testing from SOC to ensure that control functions are verified. 1024S will be isolated from the AIES for the duration of this outage via the 240 kV circuit breaker 401-952-600001 and 240 kV motorized disconnect 401-PS-6000. |  | Restricts Generation
ATCO | 7L121 (2043s Freer - 7LA121 tap) | 2023-02-09 12:01 | 2023-03-06 07:59 | N | N | jumper 2 open until 7L121D3 is installed | Line |  |  | Creates Radial Feeds, Firm Load Loss
BHE Canada | MATL (120s Picture Butte - Montana), 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte), 120s 1152S (120s Picture Butte), 120s 1052S (120s Picture Butte) | 2023-02-12 08:00 | 2023-02-14 14:37 | Y | Y | forced outage | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK, ENMAX | 1080L (SS-25 - SS-65), 240kV West Bus (SS-25), 25B240-D139 (SS-25), 25B240-D142 (SS-25), 25B240-D133 (SS-25), 25B240-D136 (SS-25), 25B240-D138 (SS-25), 25MD240-1080 (SS-25) | 2023-02-12 13:00 | 2023-03-04 09:34 | N | Y | expansion of GOI zone for urgent work to replace 1080L cables into C25s for scaffolding for cable terminations | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T2 (Garneau), G725 (Garneau), G726 (Garneau), GAB2 (Garneau), GT2-O (GARNEAU) | 2023-02-13 07:00 | 2023-05-29 13:00 | N | N |  | Transformer, Circuit Breaker, Switch | Isolation point extension to 72 kV ring fro Tx2 Replacement |  | Creates Radial Feeds, Firm Load Loss
ATCO | PEC1 Lindbergh | 2023-02-13 08:00 | 2023-02-27 17:00 | N | N | P2575 ATCO Lindbergh Modification, 16 MW. Feb 20, 2023. | Unit
ENMAX | 14.83L (SS-14 - SS-36), 16.63L (SS-16 - SS-36), 36.2TR (SS-36), 36B138-36BT3 (SS-36), 16B69-16.63 (SS-16), 14B138-14.83 (SS-14), 36.5TR (ENMAX 36), 36B69-16.63/36.5TR (SS-36), 36B138-14.83 (SS-36), SW84 (SS-36), 36MD138-36.2TR (SS-36), 36MD138-36.5TR (SS-36) | 2023-02-13 08:00 | 2023-02-15 18:00 | N | N | switch maintenence | Line, Transformer, Circuit Breaker, Switch | HV SW Maint. SW61, SW84, SW85, SW86, MD-36.5TR, MD-36.2TR. Check Reversing Switch - 36.2 |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 17s 757N (17s Benalto), 757L (17s Benalto - 758L tap) | 2023-02-13 08:30 | 2023-02-16 16:30 | N | N | install anti-islanding relay | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L15 (763s Hanna - 775s Sullivan Lake), 763s 602 (763s Hanna), 775s 601 (775s Sullivan Lake) | 2023-02-13 09:30 | 2023-02-15 12:00 | N | N | ratio change on CT602 at 763s Hanna | Line, Circuit Breaker |  | Outage finished early | Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2023-02-13 10:00 | 2023-02-23 14:00 | N | Y | line mitigation, cross arm replacement | Line |  | Outage extended as per TFO. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek), 410s 952 (410s Josephburg), 410s 852 (410s Josephburg), 410s 776E (410s Josephburg) | 2023-02-13 11:00 | 2023-02-13 17:00 | N | N | line and breaker outage required for teleprotection upgrades | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-02-13 12:00 | 2023-02-16 18:00 | N | N | rebuild 174L from existing structure 174L692 to 174L742 | Line, Circuit Breaker | Rebuild 174L from existing structure 174L692 to 174L742 |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L71 (848s Ruth Lake - 2082s Dog Rib), 848s 7L71D1 (848s Ruth Lake), 848s 701 (848s Ruth Lake) | 2023-02-13 16:00 | 2023-02-17 16:00 | N | N | cross arm replacement project | Line, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2023-02-13 17:01 | 2023-02-16 08:00 | N | N | line outage required for teleprotection upgrades | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 881s 702T (881s Sturgeon), 813s 7L01D1 (813s Little Smoky) | 2023-02-14 09:00 | 2023-02-14 17:00 | N | N | breaker repair | Transformer, Switch | Heartland Generation as requested an emergency outage to 702T at 881S to make repairs to make repairs on their breaker. Momentary outages to 7L01 is needed to open and close 702TD at 881S. A condition of guarantee will be issued between ATCO and Heartland Generation. |  | Pre-Condition
ALTALINK | 725L (674s Bowron - 725AL tap), 725AL (618s Riverbend - 725L tap), 725L (111s Coalbanks - 725AL tap) | 2023-02-14 09:00 | 2023-02-14 13:00 | N | Y | emergency repairs to 674s12 | Line |  | emergency repairs to 674s12 (manual airbreak) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L990 (72s Leismer - 2049s Kettle River), 2049s 9L990D1 (2049s Kettle River) | 2023-02-14 10:00 | 2023-02-14 14:00 | N | Y | Chard Telecom work - open end 9L990 at 72s due to double TPR outage | Line, Switch | Chard Telecom outage - ATCO. Open end 9L990 @ 72s due to double TPR outage. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 780s 707C (780s Lubicon) | 2023-02-14 11:00 | 2023-02-23 14:30 | N | N | PRC-005 - trip coil testing- breaker 707 | Shunts | PRC-005 - TRIP COIL TESTING - BREAKER 707 @ 780S |  | Pre-Condition
ATCO | 7L12 (780s Lubicon - 7LA12 tap), 780s 702 (780s Lubicon), 780s 703 (780s Lubicon) | 2023-02-14 11:00 | 2023-02-16 15:00 | N | N | 21A/7L12 21B/7L12 50BF/702, 50BF/703 RTXP test switch replacement, breaker 702, 703 PRC-005 trip coil testing, 21A relay testing | Line, Circuit Breaker | 21A/7L12 21B/7L12 50BF/702, 50BF/703 RTXP test switch replacement, breaker 702, 703 PRC-005 Trip coil testing, 21A relay testing | Returned early | Creates Radial Feeds, Firm Load Loss
ALTALINK | 895s T3 (895s Suffield) | 2023-02-15 08:00 | 2023-02-16 16:00 | N | N | remove old wood beams and poles. | Transformer | Clearance issues for demolition of old wood bay. Outage required to remove old wood beams and poles. |  | Restricts Generation
BCH | T1 (BCH Natal), 13CX1 (BCH Natal) | 2023-02-15 08:00 | 2023-02-15 18:00 | N | Y | low oil alarm investigation BC maintenance does not affect the Alberta ATC | Transformer, Shunts | Natal T1 (BCH Natal) 60B1, 60CB11, 60CB15, 60CB1, SS1 OOS |  | Pre-Condition
ALTALINK | 892L (244s Bowmanton - 895s Suffield), 895s 892 (895s Suffield) | 2023-02-15 08:30 | 2023-02-17 08:59 | N | Y | migrate and commission 895s892 (652) & L1-892L at 895s associated line protections | Line, Circuit Breaker | Migrate and commission all 895s892 (652) & L1-892L at 895s Suffield associated line protections, Overload RAS, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Implement fault reporting on |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ENMAX | 9.80L (SS-9 - SS-31), 31.1C (SS-31), 31.1TR (SS-31), 31B138-9.80 (SS-31), 31MD138-31.1TR (SS-31), 9B138-9.80 (SS-9) | 2023-02-16 08:00 | 2023-02-16 18:00 | N | N | high resistance on south phase of SW89 at 31 sub | Line, Shunts, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek), 410s 952 (410s Josephburg), 410s 852 (410s Josephburg), 410s 776E (410s Josephburg) | 2023-02-16 08:01 | 2023-02-16 15:00 | N | N | line and breaker outage required for teleprotection upgrades | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
AESO-SC | OATI | 2023-02-16 15:00 | 2023-02-16 16:00 | N | N | OATI database servers updated from their current version to SQL 2019 | SCInternal |  |  | For Information Only
ALTALINK | 39s 752 (39s Bickerdike) | 2023-02-17 08:00 | 2023-02-17 15:00 | N | N | wire CT for L4 RAS relay from 752 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 892L (244s Bowmanton - 895s Suffield), 895s T2 (895s Suffield), 895s 892 (895s Suffield), 895s 45 (895s Suffield) | 2023-02-17 09:00 | 2023-02-17 17:30 | N | Y | switch 895s49 requires repairs | Line, Transformer, Circuit Breaker, Switch | Migrate and commission all 895s892 (652) & L1-892L at 895s Suffield associated line protections, Overload RAS, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Implement fault reporting on. Note that as 895s49 is currently being used an isolation point, the GOI zone will be expanded at ~0900 on Feb 17 when the crew arrives on site. The isolation points being used tomorrow will be 895s48, 895s50 & 895s43. |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ALTALINK | 974L (39s Bickerdike - 310p Sundance), 39s 1552 (39s Bickerdike), 39s 1652 (39s Bickerdike), 310p 152 (310p Sundance), 310p 252 (310p Sundance) | 2023-02-17 15:30 | 2023-02-17 18:00 | N | Y | fix corona ring on 39s61 | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 7L165 (718s Parsons Creek - 933s Tower Road) | 2023-02-17 16:30 | 2023-02-18 11:30 | N | N | repair deficiencies on 7L165 structures 32A12, 32A13, 32A14, 32A23, 32A26, 32A27 - replace broken insulators | Line | Repair deficiencies on 7L165 7L165 Structures 32A12, 32A13, 32A14, 32A23, 32A26, 32A27 - replace broken insulators |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib), 718s 702 (718s Parsons Creek) | 2023-02-18 11:31 | 2023-02-19 11:00 | N | N | cross arm replacement project | Line, Circuit Breaker | GOI required for cross arm replacement project |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s GT2 (987s Clover Bar) | 2023-02-19 07:00 | 2023-02-19 17:00 | N | N | maintenance | Transformer | CPC Request for G2 Borescope |  | Restricts Generation
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake), 63s 648 (63s Red Deer), 580s 648 (580s Sylvan Lake) | 2023-02-20 08:00 | 2023-02-24 16:00 | N | N | re-locate and resplice understrung OPGW between 648L96 and 648L97 to top of structures, and salvage old 80L crossing above | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | MH2 (Aurora - Aurora) | 2023-02-20 08:00 | 2023-02-20 20:00 | N | N | powerline outage | Line |  |  | For Information Only
Syncrude | MH1 (Aurora - Aurora) | 2023-02-20 08:00 | 2023-02-20 20:00 | N | N | powerline outage | Line |  |  | For Information Only
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap) | 2023-02-21 06:00 | 2023-02-21 18:00 | N | N | repair mid span conductor damage at structures 52 and 54 | Line |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72KN23 (Kennedale - Namao), 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale), K723 (Kennedale), KDS6 (Kennedale) | 2023-02-21 07:00 | 2023-02-21 20:00 | N | N | update 72KN23 P and C settings | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 752L (64s East Crossfield - 752AL tap), 752L (653s Summit - 752AL tap), 752AL (316s West Crossfield - 752L tap) | 2023-02-21 07:15 | 2023-02-23 17:45 | N | N | FRM component replacement (str 11-12) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 50L (44s Bearspaw Plant - SS-21) | 2023-02-21 07:15 | 2023-02-23 14:30 | N | Y | insulator and structure repair | Line | 50L FRM (STR 115-125) - Insulator & Structure repair |  | Pre-Condition
ENMAX | 24.2TR (SS-24) | 2023-02-21 08:00 | 2023-02-24 16:00 | N | N | relay, protection testing 24RLY138-24.2TR A GE, SEL-351S, 24BB25-24.2TR | Transformer | Relay, Protection Testing 24RLY138-24.2TR A GE, SEL-351S, 24BB25-24.2TR. |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-02-21 12:00 | 2023-03-16 18:00 | N | N | rebuild 174L from existing structure 174L692 to 174L742 | Line, Circuit Breaker | rebuild 174L from existing structure 174L692 to 174L742 |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 100L (498s Tilley - 895s Suffield), 895s 100 (895s Suffield), 498s 100X (498s Tilley), 658L (649s Chappice Lake - 658AL tap) | 2023-02-22 08:30 | 2023-02-23 16:30 | N | Y | migrate and commission at 895s Suffield | Line, Circuit Breaker | Migrate and commission all 895s100 (752) & L2-100L at 895s Suffield associated line protections, recloser, synch check, breakers, breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. Implement fault reporting on 100L. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2023-02-22 10:00 | 2023-02-24 12:00 | N | N | changing arms and pole repairs | Line | Changing Arms and Pole Repairs. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 895s 2272 (895s Suffield) | 2023-02-22 12:30 | 2023-02-22 15:30 | N | N | 25 kV breaker - L5 overcurrent protection maintenance | Circuit Breaker | Implement new standard DNP address on L5 overcurrent protection (50/51/79/96/L5) for communications with new SG-4260 RTU. Rebooting of L5 protection is required after changing of DNP address. L5 DNP controls testing (recloser and ground trip) after completing DNP address change. |  | For Information Only
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2023-02-22 15:00 | 2023-02-24 18:00 | N | N | emergency real time outage to repair shield wire broken on several structures | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-02-22 23:00 | 2023-02-23 03:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-02-23 03:00 | 2023-02-23 07:00 | N | N | maintenance | Switch |  |  | Restricts Generation
Syncrude | 14 (Aurora) | 2023-02-23 08:00 | 2023-02-25 20:00 | N | N | replace CT 14 | Circuit Breaker |  |  | For Information Only
ALTALINK | 234L (310p Sundance - 505L tap), 234L (133L tap - 505L tap), 505L (234L tap - 505L tap), 310P 234N (310p Sundance) | 2023-02-23 08:00 | 2023-02-23 17:00 | N | N | urgent repair 310p234N DC ground | Line, Circuit Breaker |  |  | Pre-Condition
ATCO, ALTALINK | 1241L (510s Sunnybrook - 939s Livock), 12L44 (939s Livock - 951s Thickwood Hills), 510s R3 (510s Sunnybrook), 939s 1213R (939s Livock), 951s 1213R (951s Thickwood HIlls), 939s 1214R (939s Livock), 939s 1216R (939s Livock), 510s 7689 (510s Sunnybrook), 939s 1213A (939s Livock), 951s 1213 (951s Thickwood Hills), 951s 1213A (951s Thickwood Hills), 939s 12L44D1 (939s Livock), 951s 12L44D1 (951s Thickwood Hills), 951s 1206A (951s Thickwood Hills), 951s 1205B (951s Thickwood Hills), 939s 1214 (939s Livock), 939s 1214A (939s Livock), 939s 1216 (939s Livock), 939s 1216A (939s Livock), 939s 1204A (939s Livock), 939s 1205B (939s Livock), 939s 1206A (939s Livock), 939s 1206B (939s Livock), 939s 1207A (939s Livock), 939s 1207B (939s Livock), 939s 1208A (939s Livock), 939s 1209B (939s Livock) | 2023-02-23 10:00 | 2023-02-24 10:00 | N | Y | urgent change out a lightning arrestor that has a 100 degree hotspot | Line, Shunts, Switch, Circuit Breaker |  |  | 500 kV, Pre-Condition
VISIONREQ | 354s RTU/SCADA (354s Summerview) | 2023-02-23 13:00 | 2023-02-23 15:00 | N | N | network updates on Summerview 1 | Terminal Equipment | During the outage, the Wind Control Center will not have control over the turbines but will have control over the substation. There will be personnel on site that can control the turbines in the case of an emergency. There will be no change to site AC. |  | Affects Visibility
ALTALINK | 74s C2 (74s Janet) | 2023-02-24 08:00 | 2023-08-31 16:00 | N | N |  | Shunts | 74s C2 (74s Janet) |  | Pre-Condition
Saskpower | SASK POWER P1C | 2023-02-25 08:00 | 2023-02-27 18:00 | N | Y | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage B3R Line, BR 406R, BR 902T, C1P Line-PQSS to L1, P1R Line, PA2 Line, PQ 800NPR, R1P Line, S1M-TCX Line |  | For Information Only, Limits ATC
ATCO | 7L94 (827s Cranberry Lake - 878s Kidney Lake) | 2023-02-25 09:00 | 2023-02-25 11:00 | N | N | insulator replacement on several poles | Line |  |  | Firm Load Loss, Pre-Condition
BCH | 1L274 (BCH Elkford tap - BCH Line Creek tap), 1L274 (BCH Elkford Tap - BCH Greenhills Tap), BCH Elkford | 2023-02-25 11:00 | 2023-02-25 12:00 | N | Y | de-energize and re-energize EFD substation remotely, does not affect the Alberta ATC | Line, Station | To De-energize and Re-energize EFD Substation remotely (from EFT if possible). This is to put EFD 25VR1 back into service following emergency repairs. |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ENMAX | 21.1TR (SS-21) | 2023-02-26 08:00 | 2023-02-26 11:00 | N | N | LV breaker maintenance | Transformer | LV Breaker Maintenance. |  | For Information Only
EPCOR | 72LS24 (EP 803s Lambton - Strathcona), 72LH8 (EP 803s Lambton - EP Hardisty), EP 803s T3 (EP 803s Lambton), S724 (Strathcona), EP 803s L721 (EP 803s Lambton), SDS10 (Strathcona), EP 803s LDS14 (EP 803s Lambton), EP 803s LAB3 (EP 803s Lambton) | 2023-02-27 07:00 | 2023-03-21 17:00 | N | Y | Strathcona/Lambton: Strathcona protection upgrade cut overs | Line, Transformer, Circuit Breaker, Switch | Strathcona/Lambton: Strathcona Protection Upgrade Cut Overs 72LS24 (LH8 Open Ended) @ Strathcona and Lambton and Hardisty |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Strathcona), S723 (Strathcona), SAB3 (Strathcona) | 2023-02-27 07:00 | 2023-03-21 17:00 | N | N | Strathcona: protection upgrade cut overs | Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 763AL (447s Enchant - 763L tap), 447s 763A (447s Enchant) | 2023-02-27 08:00 | 2023-02-28 16:00 | N | Y | install structure 98 and T-tap for future new 763CL | Line, Circuit Breaker | Outage needed to install Structure 98 & T-Tap for future new 763CL. New line will not be connected or built during this outage, just prep work with the new structures that tie in. 763L(28s  158s) breakers will be open for switching and immediately closed after opening 763AL1 at the beginning and end of the outage. |  | Pre-Condition, Restricts Generation
BCH | 5CB21 (BCH Cranbrook) | 2023-02-27 08:00 | 2023-03-03 16:00 | N | Y | BC protection work | Circuit Breaker | This is a breaker PM outage and associated PNs PM. As 1201L auto-reclose is off and will keep it off, the 5L94 PYPN and SYPN will be taken out one at a time. It should be no impact to your side. To coincide with outage on 5CB21. PNs below OOS PY and SY OAT. 12RX6 does not have a PY and SY, will require the RX OOS (12D26 Open). Alternatively can rely on T6 SYPN as back up PN and not overlap T6 SYPN and 12RX6 PN OOS. Will need 5L94 Reclosing OOS |  | 500 kV, For Information Only
ENMAX | 54.81L (SS-54 - SS-65), 65B138-D83 (SS-65), 65B138-D84 (SS-65), 54B138-54.81 (SS-54), 65MD138-54.81 (SS-65) | 2023-02-27 08:00 | 2023-02-28 18:00 | N | N | switch maintenence. | Line, Circuit Breaker, Switch | HV SW Maint. 65sub SW89, SW90, 65MD-54.81 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2023-02-27 09:00 | 2023-03-01 17:00 | N | Y | need to inspect three DS's within this zone | Line | 5L91 (Selkirk - Ashton Creek). Need to inspect three DS's within this zone |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 2075s 900SST1 (2075s Newell), 2075s 920 (2075s Newell), 2075s 921 (2075s Newell), 2075s 900SST1D1 (2075s Newell), 2075s 920B (2075s Newell), 2075s 921A (2075s Newell) | 2023-02-27 09:30 | 2023-03-01 12:00 | N | Y | 900SST1 PRD trip removal. | Transformer, Circuit Breaker, Switch | 900SST1 PRD trip removal. Transfer station service to alternate sources. |  | For Information Only
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2023-02-27 10:00 | 2023-03-08 15:00 | N | Y | line mitigation, cross arm replacement | Line | Line mitigation, Cross arm replacement |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L30 (732s Mitsue - 844s AEC Mill), 732s 704 (732s Mitsue), 732s 707 (732s Mitsue), 844s 703 (844s AEC Mill), 732s 7L30D1 (732s Mitsue) | 2023-02-27 10:00 | 2023-03-13 17:00 | N | N | 7L30 protection upgrade | Line, Circuit Breaker, Switch | 7L30 Protection upgrade. | Extension | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 743s 702T (743s Sarah Lake), 743s 706 (743s Sarah Lake) | 2023-02-28 14:30 | 2023-03-08 16:00 | N | N | forced outage | Transformer, Switch |  |  | For Information Only
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap) | 2023-03-01 06:00 | 2023-03-04 18:00 | N | N | 700L line relocation between structures 23 and 41 | Line |  |  | Creates Radial Feeds, Firm Load Loss
CNRL, ATCO | 75-PLH-901 (838s Horizon Mining - 849s Joslyn Creek), 849s 907 (849s Joslyn Creek), 838s 75-BC-1913 (838s Horizon Mining), 838s 75-BC-1914 (838s Horizon Mining), 838s 75-SD-1913A (838s Horizon Mining), 838s 75-SD-1914B (838s Horizon Mining), 838s 75-SD-901 (838s Horizon Mining), 849S 75-PLH-901D1 (849s Joslyn Creek) | 2023-03-01 07:30 | 2023-03-15 08:00 | N | Y | Horizon Project - disconnect existing 75-PLH-901 from former 75-PLH-901 bay to new 838S-900BS2 | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39) | 2023-03-01 08:00 | 2023-03-01 16:00 | N | N | 138-38.83-3 repair/replace insulator - contact with kite | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 31.3TR (SS-31) | 2023-03-01 08:00 | 2023-03-01 16:00 | N | N | auxiliary relay missing mounting base in 31.3TR relay panel | Transformer | Auxiliary relay missing mounting base in 31.3TR relay panel |  | For Information Only
SUNCOR | 29EDD-71 29PT-336 (29EDD-71), 29EDD-71 752-4651 (29EDD-71), 29EDD-71 752-4652 (29EDD-71), 29EDD-71 752-4654 (29EDD-71), 29EDD-71 29PS-434 (29EDD-71 Edd71Sub), 29EDD-71 29PS-430 (29EDD-71 Edd71Sub), 29EDD-71 30-252-12501 (29EDD-71) | 2023-03-01 08:00 | 2023-03-15 18:00 | N | Y | maintenance and testing | Transformer, Circuit Breaker, Switch |  |  | For Information Only, Restricts Generation
ATCO | 2075s 900SST2 (2075s Newell) | 2023-03-01 13:00 | 2023-03-02 11:30 | N | N | 900SST2 PRD trip removal | Transformer |  |  | 240 kV, For Information Only
EPCOR | 557s CD2403 (557s Castle Downs) | 2023-03-02 07:00 | 2023-03-02 17:00 | N | Y | emergency dashpot repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
CapitalPower | 1018s RTU/SCADA (1018s Shamrock) | 2023-03-02 08:00 | 2023-03-02 09:00 | N | N | communications-only outage to perform some updating on some of the equipment on the substation | Terminal Equipment |  |  | Affects Visibility
EPCOR | 330p RTU/SCADA (330p Genesee) | 2023-03-02 09:00 | 2023-03-02 11:00 | N | N | test the Telus MPLS SCADA network failover | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 17s C1 (17s Benalto) | 2023-03-02 09:30 | 2023-03-02 12:30 | N | Y | maintenance on PRC load readings and trip coil checks | Shunts | Commissioning request is to ensure that C1 cap bank can be energized so that PRC maintenance load readings and trip coil checks can be done on the following relays (C1 B50/51/60/27/59/C1 & C1 A50/51/60/27/59/C1). |  | 240 kV, Pre-Condition
ENMAX | 25B240-D140 (SS-25) | 2023-03-03 08:00 | 2023-03-03 12:00 | N | Y | HV breaker SF6 gas sample | Switch | HV breaker SF6 Gas Sample - 25B240-D140 |  | 240 kV, Contingency Requires Mitigation
ENMAX | 25B240-D141 (SS-25) | 2023-03-03 12:00 | 2023-03-03 16:00 | N | Y | HV breaker SF6 gas sample | Circuit Breaker | HV breaker SF6 Gas Sample - 25B240-D141 |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 1080L (SS-25 - SS-65) | 2023-03-04 09:35 | 2023-03-17 09:59 | N | Y | urgent work to replace 1080L cables into C25s | Line | Urgent work to replace 1080L cables into C25s - Taken OOS in real time on 22-10-13 |  | 240 kV
ENMAX | 25B240-D131 (SS-25) | 2023-03-05 08:00 | 2023-03-05 11:59 | N | Y | breaker SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 25B240-D132 (SS-25) | 2023-03-05 12:00 | 2023-03-05 16:00 | N | Y | breaker SF6 gas sample | Circuit Breaker | breaker SF6 gas sample - 25B240-D132. 25B240-D132 tank heaters not functioning |  | 240 kV, Pre-Condition
CapitalPower, ENMAXEC | EGC1 Shepard | 2023-03-05 20:30 | 2023-03-05 23:30 | N | N | communication outage to replace network switches | Unit |  |  | Affects Visibility
EPCOR | T4 (Rossdale) | 2023-03-06 07:00 | 2023-03-15 17:00 | N | N | UGT backfill replacement under low bus | Transformer | Rossdale: UGT Backfill Replacement under low BUS |  | For Information Only
EPCOR | T2 (Namao), N722 (Namao), N723 (Namao), NAB2 (Namao) | 2023-03-06 07:00 | 2023-03-10 17:00 | N | N | TX2 zone P&C maintenance | Transformer, Circuit Breaker, Switch | Namao: TX2 Zone P&C Maintenance |  | Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 1098L (EP 805s Jasper - Poundmaker), EP 805s J2407 (EP 805s Jasper), EP 805s J2401 (EP 805s Jasper) | 2023-03-06 07:00 | 2023-03-07 17:00 | N | Y | JDS1 disconnect maintenance | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 50L (44s Bearspaw Plant - SS-21) | 2023-03-06 07:15 | 2023-03-10 17:45 | N | Y | insulator and structure repair - (str 115-125) | Line | 50L FRM (STR 115-125) - Insulator & Structure repair |  | Overload, Pre-Condition
ENMAX | 25B240-D134 (SS-25) | 2023-03-06 08:00 | 2023-03-06 12:00 | N | Y | HV breaker SF6 gas sample | Circuit Breaker | HV breaker SF6 Gas Sample - 25B240-D134 |  | 240 kV, Contingency Requires Mitigation
ATCO | 2043s Freer, 7L121 (2043s Freer - 7LA121 tap), 7L121 (860s Crow - 7LA121 tap), 7LA121 (833s Mariana - 7L121 tap) | 2023-03-06 08:00 | 2023-03-09 19:00 | N | N | require a station outage to the newly commissioned 2043s to complete a few deficiencies | Station, Line |  | Outage extended by TFO | Creates Radial Feeds, Firm Load Loss
ENMAX | 162.4TR (SS-162) | 2023-03-06 08:00 | 2023-03-10 16:00 | N | N | relay, protection testing | Transformer | Relay, Protection Testing - 162RLY138-162.4TR. T60, SEL-387E, 162.4TR Filmax leak repair |  | For Information Only
ALTALINK | 746s T1 (746s Sherwood Park) | 2023-03-06 10:00 | 2023-03-06 16:00 | N | N | replace 746s48 | Transformer |  |  | For Information Only
ATCO | 780s 701 (780s Lubicon) | 2023-03-06 10:00 | 2023-03-06 13:00 | N | N | PRC-005 trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2023-03-06 10:00 | 2023-03-13 12:00 | N | N | changing arms and pole repairs | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 535s T2 (535s Joffre) | 2023-03-06 10:00 | 2023-03-06 14:00 | N | N | customer bus duct inspection | Transformer |  |  | For Information Only
ALTALINK | 40s T1 (40s Wetaskiwin) | 2023-03-06 11:00 | 2023-03-09 16:00 | N | N | T1 maintain, fix leaks, test, change out pin caps on low side switch/bushings | Transformer |  |  | For Information Only
ENMAX | 25B240-D135 (SS-25) | 2023-03-06 12:00 | 2023-03-06 16:00 | N | Y | breaker SF6 gas sample | Circuit Breaker | HV breaker SF6 Gas Sample - 25B240-D135 |  | 240 kV, Pre-Condition
ALTALINK | 945L (275s Jenner - 562s Cypress), 275s 5 (275s Jenner), 275s 8 (275s Jenner), 275s 945N (275s Jenner), 562s 152 (562s Cypress), 562s 252 (562s Cypress), 562s 945 (562s Cypress) | 2023-03-06 12:00 | 2023-03-09 10:00 | N | Y | complete functional testing and final acceptance on L4 A and L4 B protections at 275s Jenner. Second scope of work: Testing L4 A and L4 B teleprotections at 275s Jenner | Line, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 55s T1 (55s Olds) | 2023-03-06 12:30 | 2023-03-06 17:30 | N | N | T1 tap changer filter trouble (replace motor) | Transformer | T1 Tap Changer Filter Trouble (Replace Motor) |  | For Information Only
ALTALINK | 99s 138kV Bus (99s North St. Albert), 747L (99s North St. Albert - 711L tap), 99s T1 (99s North St. Albert), 99s 747X (99s North St. Albert), 99s 3 (99s North St. Albert), 747L3A (711L tap) | 2023-03-07 07:00 | 2023-03-07 18:00 | N | N | clean hot spot on 99s3 and 99s4 | Bus, Line, Transformer, Circuit Breaker, Switch | Clean hot spot on 99s3 and 99s4. With PT1 being deenergized 712L A21/L2 and B21/L2 relays will be disabled. 79/252 will be unavailable as well. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | Sask Power P2P | 2023-03-07 08:00 | 2023-03-07 18:00 | N | Y | maintenance | Line |  | P2P Line, A1P Line | Limits ATC
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2023-03-07 08:00 | 2023-03-07 13:00 | N | Y | emergency - repairing downed shield wire | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
TRANSALTA | 1045s Garden Plain | 2023-03-07 08:00 | 2023-03-08 18:00 | N | N | capacitor bank installation | Station | TransAlta is requesting an outage at Garden Plain 1045s for completion of capacitor bank installation. The outage is for March 7 starting at 0800 until March 8 at 1800. The site AC will be 0MW. |  | Restricts Generation
ATCO | 9L990 (72s Leismer - 2049s Kettle River), 2049s 9L990D1 (2049s Kettle River) | 2023-03-07 10:00 | 2023-03-07 14:00 | N | Y | Chard Telecom work - open end 9L990 at 72s due to double TPR outage | Line, Switch | Chard Telecom outage - ATCO. Open end 9L990 @ 72s due to double TPR outage. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
AESO-SC | OATI | 2023-03-07 18:00 | 2023-03-07 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
EPCOR | EP 805s J2404 (EP 805s Jasper) | 2023-03-08 07:00 | 2023-03-08 17:00 | N | Y | J2404 red button repair | Circuit Breaker | Jasper: J2404 Red Button Repair |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 557s CD2401 (557s Castle Downs) | 2023-03-08 07:00 | 2023-03-08 17:00 | N | Y | CastleDowns: NAIT tour switching demonstration | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 635EDD-1000 635-752-122 (635EDD-1000) | 2023-03-08 08:00 | 2023-03-08 17:00 | N | N | maintenance | Circuit Breaker | Outage on breaker 635-752-122 to replace merging unit, MU2-3. A protection of the following equipment will be disabled during this outage: -Transformer 635PT-1005( T60), -Line Protection 635PL7-1001( L90) -Bay Control (C60) B protection for all the above equipment will be in service |  | For Information Only
CLLP | CHP1 Chappice Lake | 2023-03-08 08:00 | 2023-05-24 15:00 | N | N | P2216 FortisAlberta Chappice Lake 649S DER Solar 15 MW. ISD April 19, 2023 | Unit
Saskpower | SASK POWER P2C | 2023-03-08 09:00 | 2023-03-14 18:00 | N | Y | maintenance | Line | P2C Line, GSWPS Wind, BHWPS Wind, PRPS 1 Unit, PRPS 2 Unit, CWPPS Wind outage |  | Pre-Condition
ATCO | 780s 702 (780s Lubicon) | 2023-03-08 10:00 | 2023-03-08 16:00 | N | N | PRC-005 trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-03-08 10:00 | 2023-03-08 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 535s T1 (535s Joffre) | 2023-03-08 10:00 | 2023-03-09 17:00 | N | N | customer bus maintenance | Transformer |  |  | For Information Only
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2023-03-09 08:00 | 2023-03-09 17:00 | N | Y | replace insulator on top phase jumper string on structure 18 | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 33s 2 (33s Spray) | 2023-03-09 08:00 | 2023-03-09 13:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 205s Castle Rock Ridge | 2023-03-09 08:00 | 2023-03-09 16:00 | N | N | feeder 1 of CRR1 outage to replace the transformer on turbine 21 | Station | Castle Rock Ridge I will be de-energizing Feeder 1 to replace the transformer on turbine 21. |  | Restricts Generation
ALTALINK | 250P 2 (250P Bighorn Plant) | 2023-03-09 10:00 | 2023-03-09 14:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ATCO | 780s 704 (780s Lubicon) | 2023-03-09 10:30 | 2023-03-09 16:00 | N | N | PRC- 005 trip coil testing, breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 940L (120s Picture Butte - 370s North Lethbridge) | 2023-03-10 08:00 | 2023-03-10 17:00 | N | Y | replace Insulators on structure 27 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap) | 2023-03-11 06:00 | 2023-03-20 16:30 | N | N | to complete portion of 700L line relocation between structures 23 and 41 | Line | GOI required to complete portion of 700L Line Relocation between structures 23 and 41. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2023-03-11 08:00 | 2023-03-11 17:00 | N | N | outage required for delivery of new 12TC1 transformer | Line | Outage required for delivery of new 12TC1 transformer |  | For Information Only
ENMAX | 2.83L (SS-13 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-5 - 2.83L tap) | 2023-03-11 08:00 | 2023-03-12 16:00 | N | N | tower climbing inspection | Line |  |  | Pre-Condition
ALTALINK | 1041L (370s North Lethbridge - 554s Travers), 370s 1041 (370s North Lethbridge) | 2023-03-11 08:00 | 2023-03-11 17:00 | N | Y | replace insulators on structure 254 | Line, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2023-03-11 08:00 | 2023-03-12 16:00 | N | N | tower climbing inspection | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2023-03-12 08:00 | 2023-03-12 17:00 | N | Y | change dead-end insulators on structures 250 & 251 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 151s T1 (151s Strathmore), 151s C1 (151s Strathmore) | 2023-03-12 10:00 | 2023-03-12 12:00 | N | Y | urgent repair for 151s21 hot switch | Line, Transformer, Shunts |  |  | Pre-Condition, Restricts Generation
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2023-03-13 07:00 | 2023-03-14 18:00 | N | Y | install loading resistors on breaker status input circuits. | Shunts |  |  | 500 kV, For Information Only, Pre-Condition
EPCOR, ALTALINK | 1164L (816s Petrolia - EP Riverview), 1044L (EP 805s Jasper - 816s Petrolia), 816s T2 (816s Petrolia), 816s P2404 (816s Petrolia), 816s P2403 (816s Petrolia), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS12 (816s Petrolia), 816s PDS14 (816s Petrolia) | 2023-03-13 07:00 | 2023-03-18 17:00 | N | Y | insulator replacement | Line, Transformer, Circuit Breaker, Switch | Petrolia: Apparatus- PDS10 LCR, 1164L CVT LCR. Aerial- 1164L Insulator Replacement |  | 240 kV, Contingency Requires Mitigation
ALTALINK, ENMAX | 1106L (237s Foothills - SS-65), 25B240-D131 (SS-25), 65B240-D130 (SS-65), 65MD240-1106 (SS-65) | 2023-03-13 08:00 | 2023-03-14 18:00 | N | Y | switch maintenance on SW131, SW132, MD-1106 | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 7L31 (732s Mitsue - 844s AEC MILL), 844s 704 (844s AEC Mill), 844s 701 (844s AEC Mill), 732s 701 (732s Mitsue), 732s 706 (732s Mitsue), 732s 7L31D1 (732s Mitsue) | 2023-03-13 08:00 | 2023-03-26 16:45 | N | N |  | Line, Circuit Breaker, Switch | 7L31 & 700PT1 outage required for protection upgrade. Ensure 2-70871 is switched back in prior to the start of this outage. March 12th 1pm - March 13th 5pm 700PT1 outage. Once PT work is completed shrink GOI to only 7L31 | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Restricts Generation
SUNCOR | 29PL9-16 (29EDD-1 Millennium - 29EDD-94 Voyageur), 29EDD-1 952-101 (29EDD-1 Millennium), 29EDD-1 952-102 (29EDD-1 Millennium), 29EDD-94 29-952-9701 (29EDD-94 Voyageur), 29EDD-94 29-952-9702 (29EDD-94 Voyageur), 29EDD-94 29-952-9706 (29EDD-94 Voyageur), 29EDD-94 29PS-397 (29EDD-94 Voyageur), 29EDD-94 29PS-387 (29EDD-94 Voyageur), 29EDD-94 29PS-386 (29EDD-94 Voyageur), 29EDD-94 29PS-385 (29EDD-94 Voyageur), 29EDD-94 29PS-396 (29EDD-94 Voyageur), 29EDD-1 29PS-409 (29EDD-1 Millennium) | 2023-03-13 08:00 | 2023-03-29 18:00 | N | Y | maintenance | Line, Circuit Breaker, Switch | corrective and preventative maintenance 29PL9-16, 29PP-97, 29PT-408, 29PT-412B(Align with CBR Outage) 29PL9-16 Line Outage To Support CBR Project Sync Panel Tie-in and IMS Panel Tie-in - Cut in 1 x F35 IMS relay at 29EDD-1X P&C building. - CT & PT tie-in to new IMS F35 relay at Millennium Substation. - Breaker status tie-in to IMS relay at Millennium Substation. - CT & PT tie-in to IMS relay at Voyageur Substation. - Disconnect switches status tie-in to IMS relay at Millennium Substation. - Breaker status tie-in to IMS relay at Voyageur Substation. - Breaker status tie-in to Sync Panel at Voyageur Substation. -Disconnect switches status tie-in to IMS relay at Voyageur Substation - PT tie-in to Sync Panel at Voyageur Substation. |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 2075s ACF22 (2075s Newell), 2075s ACF23 (2075s Newell), 2075s ACF24 (2075s Newell) | 2023-03-13 09:30 | 2023-03-15 11:10 | N | Y | filter bank inspections | Shunts |  |  | 240 kV, For Information Only, Pre-Condition
ATCO | 7L80 (733s Simonette - 857s Kakwa Ridge), 7L80 (740s H.R. Milner - 857s Kakwa Ridge) | 2023-03-13 10:00 | 2023-03-23 10:00 | N | Y | line mitigation, cross arm replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L54 (794s Valleyview - 813s Little Smoky), 813s 707 (813s Little Smoky), 813s 708 (813s Little Smoky), 794s 704 (794s Valleyview) | 2023-03-13 10:00 | 2023-03-21 10:00 | N | Y | breaker 707 and 708 P&C wiring | Line, Circuit Breaker | 813S Little Smoky Rebuild813S Little Smoky Rebuild BKR 703 and 704 P&C wiring, remove old panel 7G, set up new panel 7P4, prep work Relay programming and functionality Commission control, alarms and status |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 51s T4 (51s Wainwright) | 2023-03-13 13:00 | 2023-03-16 18:00 | N | N | fix leaks, maintain, test, install gas monitor, install bird cover | Transformer |  |  | For Information Only
ALTALINK | 1109L (SS-25 - SS-65) | 2023-03-13 17:49 | 2023-03-29 07:59 | N | Y | forced outage | Line |  |  | 240 kV
ATCO | 903s 701T (903s Loyalist) | 2023-03-14 05:30 | 2023-03-14 17:30 | N | N | replace RTXP on 87T/701T during outage | Transformer | GOI is for Trans Canada to access 701T NGR at 903s Loyalist ATCO will replace RTXP on 87T/701T during outage. |  | For Information Only
ATCO | 903s 701T (903s Loyalist), 903s 701 (903s Loyalist) | 2023-03-14 05:30 | 2023-03-14 17:30 | N | N | perform preventative maintenance and electrical inspections | Transformer, Circuit Breaker | A Station power outage is required so crews can perform preventative maintenance and electrical inspections. These inspections include: - Inspection and testing of medium voltage power distribution equipment - Access the substation to inspect/Test the NGR. |  | For Information Only
ALTALINK | 993s T1 (993s Abee), 993s T2 (993s Abee) | 2023-03-14 09:00 | 2023-03-14 14:00 | N | N | install grounding stirrups on their equipment | Transformer | Isolation for Customer to install grounding stirrups on their equipment. AltaLink to hang grounds to facilitate Customer's work. |  | For Information Only
Saskpower | SASK POWER P1C | 2023-03-15 08:00 | 2023-04-01 17:00 | N | Y | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage C1S Line, PRPS 1 Unit, PRPS 2 Unit, CWPPS Wind, BHWPS WIND, GSWPS Wind |  | For Information Only, Limits ATC
SUNCOR | 29EDD-71 29PT-237 (29EDD-71), 29EDD-71 752-4632 (29EDD-71), 29EDD-71 752-4631 (29EDD-71), 29EDD-71 29PS-249 (29EDD-71 Edd71Sub) | 2023-03-15 08:00 | 2023-04-11 16:00 | N | Y | maintenance | Transformer, Circuit Breaker, Switch | 29-752-4631 29-752-4632 30PP-122 29PT-237 30PT-253 30EDD241;30PP-122 SYSTEM;PM,12y 29PT-237 & 30PD-17 SYSTEM;PM 5y 30EDD244;30PT-253 SYSTEM; PM; 10y 29EDD71;29-752-4631 MAINT & TEST;PM 10y 29EDD71;29-752-4632 MAINT & TEST;PM 10y | Returned early | Contingency Requires Mitigation, Restricts Generation
ALTALINK, ENMAX | 1107L (237s Foothills - SS-65), 65B240-D134 (SS-65), 65B240-D133 (SS-65), 65MD240-1107 (SS-65) | 2023-03-15 08:00 | 2023-03-16 18:00 | N | Y | SW137, SW138, MD-1107 switch maintenance | Line, Circuit Breaker, Switch | HV SW Maint. SW137, SW138, MD-1107 |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 9L32 (838s Horizon Mining - 941s Bitumount), 9L66 (838s Horizon Mining - 847s Muskeg River) | 2023-03-15 08:00 | 2023-04-13 16:00 | N | N | P2179 - CNRL 9L32/66. ISD March 31, 2023. | Line
ATCO | 934s 905 (934s Blackfly), 9L77 (925s Green Stocking - 934s Blackfly) | 2023-03-15 08:00 | 2023-03-15 17:30 | N | Y | emergency outage to change out leaking density meter at breaker 905 and top off SF6 gas | Circuit Breaker, Line | Permit Number(s): 2-72597 Outage: 934S 905 Breaker OOS Scheduled Date(s): 2023-03-15 08:00-17:30 Isolation Points: 934S 905A & 934S 905B Description of activity: Emergency outage to change out leaking density meter at breaker 905 and top off SF6 gas. Reason for Emergency: If the SF6 circuit breaker hits its critical low pressure, its fault interrupting capability can be compromised. |  | 240 kV, Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 427L (63s Red Deer - 247s Piper Creek), 247s 427 (247s Piper Creek), 63s 427 (63s Red Deer) | 2023-03-15 08:30 | 2023-03-15 17:30 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 1012s T1 (1012s Deer Hill) | 2023-03-15 08:30 | 2023-03-15 15:30 | N | N | change out all 3 phases for insulators on 1012s10 | Transformer | 1012s T1 TX18918 - GOI Change out all 3 phases for insulators on 1012s10, middle phase failed and tripped the transformer, there is currently an open point A on the top side of the fuses to the bus. Fortis has their AMI disconnected until we can do the repairs. Crew will close open point on the AMI during this work. |  | For Information Only
SUNCOR | 29EDD-71 752-4651 (29EDD-71) | 2023-03-15 18:01 | 2024-05-06 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 551L (123s Banff - 945s Sunshine Village), 551L (945s Sunshine Village - 551GL tap), 551L (953s Lake Louise - 551GL tap) | 2023-03-16 | 2023-03-16 06:00 | N | N | installing bird protection (STR 63-152) | Line | Installing Bird Protection (STR 63-152) |  | Firm Load Loss
ATCO | 9L32 (849s Joslyn Creek - 941s Bitumount), 9L66 (847s Muskeg River - 849s Joslyn Creek) | 2023-03-16 08:00 | 2023-05-08 18:00 | N | Y | stage 2 for 9L66/9L32 reconnection | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage, Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34), 15.60L (SS-15 - SS-21), 21.4TR (SS-21), 15B69-15.60 (SS-15), 34B69-21.61 (SS-34), 21B69-21.4TR (SS-21), 21B69-21.61 (SS-21), 21B69-15.60 (SS-21), SW64 (SS-21), SW65 (SS-21) | 2023-03-16 08:00 | 2023-03-16 18:00 | N | N | inspect lattice structure | Line, Transformer, Circuit Breaker, Switch | Inspect Lattice Structure |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane) | 2023-03-16 09:15 | 2023-03-16 17:45 | N | N | install new double dead-end structure 110A | Line | Install new double dead-end structure 110A |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 20.82L (SS-20 - SS-21), 21.4TR (SS-21), 21.1TR (SS-21), 20B138-20.82 (SS-20), 21B69-21.4TR (SS-21), 21B138-20.82 (SS-21), 21B138-21.80 (SS-21), 21MD138-21.4TR (SS-21), 21MD138-21.1TR (SS-21) | 2023-03-17 08:00 | 2023-03-17 16:00 | N | Y | inspect lattice structure | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 951s 910 (951s Thickwood Hills), 951s 911 (951s Thickwood Hills) | 2023-03-17 10:00 | 2023-09-02 17:30 | N | Y |  | Circuit Breaker | Outage to 9L162 bay, to bring in the new line and OPGW to 951s Commissioning/testing protection end to ends with Suncor |  | 240 kV
ALTALINK, ENMAX | 1080L (SS-25 - SS-65), 25B240-D138 (SS-25), 25B240-D139 (SS-25) | 2023-03-17 10:00 | 2023-03-17 18:00 | N | Y | summer substation washing | Line, Circuit Breaker |  |  | 240 kV
ATCO | 951s 908 (951s Thickwood Hills), 951s 909 (951s Thickwood Hills) | 2023-03-17 10:00 | 2023-09-02 17:30 | N | Y |  | Circuit Breaker | Outage to 9L193 bay, to bring in the new line and OPGW to 951s Commissioning/testing protection end to ends with Suncor |  | 240 kV, For Information Only
ALTALINK | 1080L (SS-25 - SS-65) | 2023-03-17 18:01 | 2023-03-22 10:00 | N | Y | urgent work to replace 1080L cables into C25s | Line | Urgent work to replace 1080L cables into C25s - Taken OOS in real time on 22-10-13 |  | 240 kV
ALTALINK | 730L (285s East Camrose - 732L tap), 285s 730N (285s East Camrose) | 2023-03-18 07:00 | 2023-03-20 18:00 | N | N | replace structure 186, replace arms and insulators on structures 185 & 195, replace insulators on structure 198 | Line, Circuit Breaker | Replace structure 186. Replace arms and insulators on structures 185 & 195. Replace insulators on structure 198. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - SS-21), 21.2TR (SS-21), 21.1C (SS-21), 21MD138-21.2TR (SS-21), 60s50 (SS-21) | 2023-03-18 08:00 | 2023-03-18 16:00 | N | Y | inspect lattice structure | Line, Transformer, Shunts, Switch, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe) | 2023-03-20 07:15 | 2023-03-23 17:45 | N | N | component replacement (str12) | Line | FRM component replacement (str12) |  | Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14MD138-14.1TR (SS-14), 14MD138-14.3TR (SS-14), SW83 (SS-14), SW87 (SS-14) | 2023-03-20 08:00 | 2023-03-21 18:00 | N | N | maintenance on SW81, SW82, SW83, SW87, MD-14.3, MD-14.1. 14.3TR | Line, Transformer, Circuit Breaker, Shunts, Switch | HV SW Maint. SW81, SW82, SW83, SW87, MD-14.3, MD-14.1. 14.3TR west phase blade not rotated in jaw. |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 491L tap) | 2023-03-20 08:00 | 2023-03-20 13:00 | N | N | repair broken shield wire | Line | Emergency Repair Broken Shield Wire found during a Line Patrol |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 1.80L (SS-1 - SS-28) | 2023-03-20 08:00 | 2023-03-20 10:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47.1TR (SS-47) | 2023-03-20 08:00 | 2023-03-23 16:00 | N | N | LTC oil level issue - install spill containment, oil sampling MT, TC, gas monitor maintenance | Transformer |  |  | For Information Only
ENBRIDGE | 485s RTU/SCADA (485s Black Springs) | 2023-03-20 08:00 | 2023-03-20 12:00 | N | N | Vestas PPC 1a software upgrade | Terminal Equipment | Power will be cycled to the PPC 1a, causing a 15 minute telemetry outage. We have submitted a 4 hour window for this outage to allow site personnel the required time to prepare for the power cycle. Once the power cycle has started, the telemetry outage will be a maximum of 15 minutes Vestas needs to cycle the power for PPC 1a The 15 minute telemetry outage would cause the following visibility loss. In terms of MW, PPC1a would lose the following visibility: " 83 turbines for a total of 150 MW In terms of MVAr, PPC1a would lose the following visibility: " 83 turbines for a total of +33.2 to -49.8 MVAr " 2 Shunt Capacitors for a total of +28 MVAr " 1 DSTAT unit for a total of +/- 10 MVAr |  | Affects Visibility
ATCO | 813s SVC (813s Little Smoky) | 2023-03-20 09:00 | 2023-03-21 18:00 | N | Y | replacing the failed cards in the thyristor hall & CM work | Shunts | Replacing the failed cards in the Thyristor hall. CM work. |  | Pre-Condition
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 1055L (629s Argyll Transfer Station - 816s Petrolia), 816s T1 (816s Petrolia), 816s P2401 (816s Petrolia), 816s P2402 (816s Petrolia), 816s P2403 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS13 (816s Petrolia), 816s PDS11 (816s Petrolia), 816s PAB1 (816s Petrolia), 814s BDS20 (814s Bellamy) | 2023-03-20 09:30 | 2023-04-05 15:00 | N | Y | Petrolia PDS1, PDS11, PDS13, PDS16 LCR | Line, Transformer, Circuit Breaker, Switch |  | Returned to service early. | 240 kV, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 2075s ACF21 (2075s Newell) | 2023-03-20 09:30 | 2023-03-29 08:30 | N | Y | PRC-005 testing and HMI upgrades | Shunts | PRC-005 testing & HMI Upgrades. |  | 240 kV, For Information Only, Pre-Condition
ATCO | 7L69 (731s Elmworth - 815s Goodfare), 815s 704 (815s Goodfare), 731s 702 (731s Elmworth) | 2023-03-20 10:00 | 2023-03-21 16:00 | N | Y | PRC-005 trip coil testing breaker 704 | Line, Circuit Breaker | RTXP test port replacement 21A/7L69, 21B/7L69, PRC-005 trip coil testing breaker 704 |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2023-03-20 10:00 | 2023-03-27 12:00 | N | N | changing arms and pole repairs | Line | Changing Arms and Pole Repairs |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.81L (SS-1 - SS-20) | 2023-03-20 10:00 | 2023-03-20 11:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ENMAX | 1080L (SS-25 - SS-65), 240kV West Bus (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25MD240-1080 (SS-25) | 2023-03-20 10:00 | 2023-03-21 18:00 | N | Y | urgent work to replace 1080L cables into C25s | Line, Bus, Circuit Breaker, Switch | Urgent work to replace 1080L cables into C25s - Taken OOS in real time on 22-10-13 |  | 240 kV
ENMAX | 9.83L (SS-9 - SS-43) | 2023-03-20 11:00 | 2023-03-20 12:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt), 761L (38s East Edmonton - 71s Lamoureux) | 2023-03-20 12:00 | 2023-03-23 18:00 | N | Y | FRM component replacement (709L str 2-13) | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43) | 2023-03-20 12:00 | 2023-03-20 16:00 | N | N | spring pothead washing | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 285s T1 (285s East Camrose) | 2023-03-20 12:30 | 2023-03-30 17:30 | N | N | corrosive sulphur oil reclaim | Transformer |  |  | For Information Only
EPCOR | 987s T1 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s CCP7213 (987s Clover Bar) | 2023-03-21 07:00 | 2023-03-21 17:00 | N | Y | emergency - tap changer investigation and repair | Transformer, Circuit Breaker | Cloverbar: TX1 Emergency Tap Changer Investigation and Repair |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
GREENGATEP, ATCO, CapitalPower | 972s Tinchebray, 9L93 (615s Halkirk - 972s Tinchebray), 9L16 (755s Cordel - 972s Tinchebray), 972s 901 (972s Tinchebray), 972s 902 (972s Tinchebray), 972s 903 (972s Tinchebray), 755s 9L16D1 (755s Cordel), 615s 52T1 (615s Halkirk), 615s 9L93D2 (615s Halkirk) | 2023-03-21 08:00 | 2023-03-21 17:30 | N | N | inspect and repair damaged cables | Station, Line, Circuit Breaker, Switch | inspect and/or repair damaged cables in main cable tray coming out of the control building | Vandals broke into the 972S Tichebray substation last night and tried to pull all the main cables coming out of the control building with a pickup. They were unsuccessful but they damaged many of the cables. The station service has been disrupted and the Station is running on the Backup generator at this moment. The extent of the damage is unknown and cannot be properly identified until the Substation is De-energized. There is a chance that the sub may trip if any cables are moved at this time. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 15s Fort Macleod | 2023-03-21 08:00 | 2023-03-21 16:00 | N | N | station service isolation | Station | station service isolation required for reconfiguration of load side of transfer switch |  | For Information Only
ALTALINK | 2739s T1 (2739s Wabamun), 19s 124 (19s Wabamun) | 2023-03-21 08:00 | 2023-03-21 18:00 | N | N | urgent - repair/remove cross arm over T1 | Transformer, Circuit Breaker | Repair or remove cross arm over T1 as it is close to imminent failure. |  | For Information Only
ALTALINK | 701L (223s Strome - 395s North Holden) | 2023-03-21 08:30 | 2023-03-21 18:30 | N | N | urgent - replace arms and insulators, and repair damaged OHSW | Line | Urgent outage to replace arms and insulators at structure 55 & repair damaged OHSW at structures 73 & 77. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | T2 (BCH Cranbrook), T6 (BCH Cranbrook), 2D6 (BCH Cranbrook) | 2023-03-21 09:00 | 2023-03-23 17:00 | N | Y | disconnect inspection and hotspot repair | Transformer, Switch |  | AOP F23: disconnect inspection, and hotspot repair SJC Feb 15: need to have the 1368KV ties OPEN to protect against voltage collapse under the C_CBK T3/T7, as it will become the only source into the region. 1L274 & 1L275 in service. Extend tripping zone of CBK 2MB4 to cover CBK 2CB9 so that 2L258 & 2L113 will tripped and drop some loads so that NTL area load could be preserved. | Pre-Condition
ATCO | 7L56 (725s Goose River - 813s Little Smoky), 813s 708 (813s Little Smoky), 813s 709 (813s Little Smoky) | 2023-03-21 11:00 | 2023-04-03 09:00 | N | N | 813s Little Smoky rebuild: wiring panel and relay programming | Line, Circuit Breaker | 813S Little Smoky Rebuild Complete 7L56 wiring panel 7P4, 708, 709 CT/PT/P&C wiring. Demo existing wiring/cabling, remove old panel 5G Relay programming and functionality Commission control, alarms and status |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CNRL, ATCO, ATCOP | 75-PLH-902 (838s Horizon Mining - 849s Joslyn Creek), 849s 260kV Bus 900BS2 (849s Joslyn Creek), 849s 903 (849s Joslyn Creek), 849s 906 (849s Joslyn Creek), 838s 75-BC-1911 (838s Horizon Mining), 838s 75-BC-1912 (838s Horizon Mining), 838s 75-SD-1911A (838s Horizon Mining), 838s 75-SD-1912B (838s Horizon Mining), 838s 75-SD-902 (838s Horizon Mining) | 2023-03-22 07:30 | 2023-05-08 18:00 | N | Y | ATCO 9L32-9L66 CNRL- Horizon Project: disconnect existing 75-PLH-902 from Horizon substation 75 and connect new bus Horizon substation 75 | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10) | 2023-03-22 08:00 | 2023-03-23 17:00 | N | Y | retie OHSW at structures 10, 13 and 14 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 849s 901T (849s Joslyn Creek) | 2023-03-22 08:00 | 2023-05-09 14:00 | N | Y | outage to 901T at 849s in coordination with 75-PLH-902 to CNRL | Transformer |  |  | 240 kV, For Information Only
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.2TR (SS-9), 9.3TR (SS-9), 9B138-2.81 (SS-9), 9B138-9.83 (SS-9), SW84 (SS-9), SW83 (SS-9), 9MD138-9.2TR (SS-9), 9MD138-9.3TR (SS-9) | 2023-03-22 08:00 | 2023-03-22 16:00 | N | N | spring substation washing and maintenance | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 35.1TR (SS-35), 35B138-81 (SS-35), 35B138-82 (SS-35), 35MD138-35.1TR (SS-35), 35MD138-84 (SS-35), 35MD138-86 (SS-35) | 2023-03-22 08:00 | 2023-03-22 16:00 | N | N | investigate SF6 gas decomp, 35MD138-86(DS), replace gas | Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
Saskpower | SASK POWER P1C | 2023-03-22 08:00 | 2023-04-17 18:00 | N | Y | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage A6V Line, AS 801T, AS 805T, B3R Line, B4R Line, B5R Line, BR 406R, C1P Line-PQSS to L1, C1Q Line-QESS to L2, C1Q-CC to L1, ER 805P, F2B Line, GL7 Line, LY 401T, LY 901T, P1C Line, P1C Line-PQSS to L1, P1R Line, PA2 Line, PQ 901T, PQ 905T, R1F Line, R1P Line, R4R Line, R5R Line, S1M-TCX Line, TD4 Line |  | For Information Only, Limits ATC
ALTALINK | 228s T1 (228s T.M.P.L. Niton) | 2023-03-22 08:30 | 2023-03-22 15:30 | N | N | change 228s33 fuse cut-out to polymer style and T1 and VR1 leak mitigation | Transformer |  |  | For Information Only
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare), 815s 702 (815s Goodfare), 790s 703 (790s Poplar Hill) | 2023-03-22 10:00 | 2023-03-23 14:20 | N | Y | RTXP test port replacement 21A/7L07, 21B/7L07, 50BF/702, PRC-005 trip coil testing breaker 815S 702 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 256s T2 (256s Harmattan) | 2023-03-22 15:30 | 2023-03-23 12:00 | N | N | forced outage | Transformer |  |  | For Information Only
EPCOR | 72DS26 (665s Dome - Strathcona), T1 (Strathcona), S721 (Strathcona), S722 (Strathcona), SAB1 (Strathcona), 665s D721 (665s Dome), 665s DDS17 (665s Dome), 665s D2404 (665s Dome), 665s DAB3 (665s Dome), 665s T3 (665s Dome) | 2023-03-23 07:00 | 2023-04-11 17:00 | N | N | protection upgrade cutovers | Line, Transformer, Circuit Breaker, Switch | Strathcona/Dome: Strathcona Protection Upgrade Cut Overs |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33B138-33.83 (SS-33), 33MD138-33.1TR (SS-33), SW83 (SS-33) | 2023-03-23 08:00 | 2023-03-23 12:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.2TR (SS-2), 2B138-D86 (SS-2), 2B138-D87 (SS-2), MD91 (SS-2), MD92 (SS-2) | 2023-03-23 08:00 | 2023-03-23 16:00 | N | N | replace contactor on 2MD 92 ( DS ) | Transformer, Circuit Breaker, Switch | 2MD 92 ( DS ) Replace Contactor - NC contact not working. Check reversing switch. |  | Contingency Requires Mitigation
BCH | 5L51 (BPA Custer - BCH Ingledow) | 2023-03-23 09:00 | 2023-03-23 19:10 | N | Y | re-tension conductor at 5L51 STR 8-5 | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2023-03-23 10:30 | 2023-04-03 10:00 | N | Y | emergency breaker gas top up | Line, Circuit Breaker | Breaker gas top up due to low level alarm. Work is considered emergency maintenance. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition,Affects Cranking Path
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33B138-33.84 (SS-33), 33MD138-33.2TR (SS-33), SW84 (SS-33) | 2023-03-23 12:01 | 2023-03-23 18:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENEL | 708s 52-C11 (708s Grizzly Bear) | 2023-03-23 13:00 | 2023-03-23 17:00 | N | N | control test on capacitor banks | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo) | 2023-03-23 15:00 | 2023-03-26 18:00 | N | Y | forced outage | Line |  | Outage extended. | 240 kV, Affects Cranking Path
ALTALINK | 1075L (28s West Brooks - 132s Ware Junction) | 2023-03-23 18:16 | 2023-03-27 11:59 | N | Y | forced outage | Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | SS-65 | 2023-03-24 07:00 | 2023-03-25 16:00 | N | N | station service SSVT2 outage, 65 sub cable trench replacement | Station |  |  | For Information Only
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2023-03-24 08:00 | 2023-03-26 18:00 | N | N | oil sampling, sheath testing, power factor test LA's and potheads - 138-3.82 | Line, Circuit Breaker | Oil sampling, Sheath testing. Power Factor Test LA's and Potheads - 138-3.82 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2023-03-25 03:17 | 2023-04-01 11:30 | N | Y | forced outage | Shunts | 813S Little Smoky SVC tripped to lockout, cause unknown. Notified AESO and Tech (Wacey Maas). Tech to head to site in AM. Controller is not functioning properly. Reference voltage is locked at 144 kv. Replacement is being sourced. Will remain out till controller can be replaced. |  | Pre-Condition
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon), 937L (5s East Calgary - 102s Langdon) | 2023-03-25 07:30 | 2023-03-26 16:30 | N | N | safety requirement - working on 1080L urgent repair | Line |  |  | For Information Only,Affects Cranking Path
ALTALINK | 166L (256s Harmattan - 166AL tap) | 2023-03-25 08:00 | 2023-03-25 17:00 | N | N | re-tie OHSW at structure 107 & 109 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27) | 2023-03-25 08:00 | 2023-03-25 10:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16) | 2023-03-25 10:00 | 2023-03-25 12:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34) | 2023-03-25 12:00 | 2023-03-25 13:00 | N | N | spring transmission line washing - shared structure with 15.62L | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34) | 2023-03-25 13:00 | 2023-03-25 14:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21) | 2023-03-25 14:00 | 2023-03-25 15:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe) | 2023-03-26 08:00 | 2023-03-26 17:00 | N | N | hardware tighten structure 67 and replace STRs 55, 56 and add new STR 55A | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.2TR (SS-31), 31.3TR (SS-31), 31B138-24.81 (SS-31), 31B138-31.84 (SS-31), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31), SW83 (SS-31) | 2023-03-26 08:00 | 2023-03-26 13:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31.1C (SS-31), 31B138-9.80 (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31), SW84 (SS-31) | 2023-03-26 13:00 | 2023-03-26 18:00 | N | N | spring substation washing | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR | PM2405 (Poundmaker) | 2023-03-27 07:00 | 2023-03-30 10:00 | N | N | SF6 leak investigation | Circuit Breaker | SF6 leak investigation. Vendor to be onsite to locate SF6 leak on Phase C pole. |  | 240 kV, Contingency Requires Mitigation
EPCOR | 805s C1 (805s Jasper), EP 805s JAB2 (EP 805s Jasper) | 2023-03-27 07:00 | 2023-03-27 13:00 | N | Y | Jasper: P&C - capacitor bank repair | Shunts, Switch | Jasper: P&C - Capacitor Bank Repair | Returned early | 240 kV, Pre-Condition
ALTALINK | 54L (118s Canmore - 85L tap), 118s 54W (118s Canmore) | 2023-03-27 07:15 | 2023-03-28 17:20 | N | N | crossarm replacement | Line, Circuit Breaker | Crossarm replacement Str 157-158 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 172L (83s Taber - 172EL tap) | 2023-03-27 07:15 | 2023-03-29 15:45 | N | Y | FRM component replacement (str827) | Line | FRM Component Replacement (str827) | Returned Early | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 102s SVC (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon), 102s 7189 (102s Langdon) | 2023-03-27 07:30 | 2023-03-30 16:30 | N | Y | T4 maintenance, 102s252 low gas repairs, SVC maitenance | Shunts, Circuit Breaker, Switch | T4 maintenance, 102s252 low gas repairs, SVC VCS Cooling pipes exchange, Novec system work, HVAC annual work |  | 240 kV, Pre-Condition
ALTALINK | 421s C1 (421s Hays) | 2023-03-27 07:30 | 2023-04-26 17:30 | N | N | install new breaker, 421s30 | Shunts | Breaker Currently Out of Service. Demolish existing Breaker and CT's, install new concrete foundation, install new dead tank SF6 Breaker. Complete all related testing and commissioning |  | For Information Only, Pre-Condition
ENMAX | 24.1TR (SS-24) | 2023-03-27 08:00 | 2023-03-27 12:00 | N | N | Barlow DTT RTAC commissioning | Transformer | 24 SUB - Barlow DTT RTAC Commissioning. MD to be opened and closed multiple times to commistion RTAC. |  | For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB132 (SS-162), 162B240-RB133 (SS-162), 281s 918 (281s Johnson) | 2023-03-27 08:00 | 2023-03-28 18:00 | N | Y | relay protection testing | Line, Circuit Breaker, Switch | Relay, Protection Testing - 162RLY240-162.C60-2 |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ATCO | 7L69 (731s Elmworth - 815s Goodfare), 731s 702 (731s Elmworth), 815s 704 (815s Goodfare) | 2023-03-27 09:00 | 2023-03-27 17:00 | N | Y | PRC-005 - trip coil testing on breaker 702 | Line, Circuit Breaker | PRC-005 TRIP COIL TESTING ON BREAKER 702 |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1075L (28s West Brooks - 132s Ware Junction), 132s 40 (132s Ware Junction), 132s 44 (132s Ware Junction), 132s 1075 (132s Ware Junction) | 2023-03-27 12:00 | 2023-03-29 18:30 | N | Y | repairs after a forced outage | Line, Circuit Breaker, Switch | 1075L (28s West Brooks - 132s Ware Junction) | Extended one day | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt) | 2023-03-27 12:00 | 2023-03-29 16:00 | N | Y | FRM component replacement | Line | FRM component replacement (709L str 2-13) | Returned Early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ENMAX | 24.2TR (SS-24) | 2023-03-27 12:00 | 2023-03-27 16:00 | N | N | Barlow DTT RTAC commissioning | Transformer | 24 SUB - Barlow DTT RTAC Commissioning. MD to be opened and closed multiple times to commistion RTAC. |  | For Information Only
ALTALINK | 275s 2 (275s Jenner) | 2023-03-27 18:00 | 2023-04-16 16:00 | N | Y | forced outage | Circuit Breaker | 944L tripped out of service and returned the following day but 275s 2 is still out of service. |  | 240 kV
ALTALINK | 452L (367s Harry Smith - 434s Stony Plain) | 2023-03-28 07:00 | 2023-03-28 18:00 | N | N | replace crossarms and insulators on structure 9 | Line | replace crossarms and insulators on structure 9. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 161L (255s Vulcan - 504s Queenstown), 853L (504s Queenstown - 853AL tap) | 2023-03-28 07:30 | 2023-03-30 14:30 | N | Y | replace strain inuslators | Line | Replace strain insulators on 853L, replace post insulators on multiple bus support structures throughout the station |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9) | 2023-03-28 08:00 | 2023-03-28 18:00 | N | N | spring substation washing | Line, Transformer | Spring Substation Washing. South Phase 9.1TR MD Requires Maintenance. 9.1TR Hot Spot. Check Reversing Switch |  | For Information Only, Pre-Condition
AOSI | BRD1 Burdett Solar | 2023-03-28 08:00 | 2023-03-28 17:00 | N | N | installing lugs on termination points for transformers | Unit |  |  | For Information Only
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap) | 2023-03-28 08:00 | 2023-03-28 17:00 | N | N | 700L62/69 arm replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 24.82L (SS-24 - SS-65) | 2023-03-28 08:00 | 2023-03-28 10:00 | N | N | DTT RTAC commissioning. | Line | 24 SUB - Barlow DTT RTAC Commissioning. |  | For Information Only, Pre-Condition
ALTALINK | 336s T1 (336s Fincastle), 336s 752 (336s Fincastle) | 2023-03-28 08:30 | 2023-03-29 18:00 | N | N | 336s DGA increase investigation | Transformer, Circuit Breaker | 336s T1 & VR1 (25kV Bus 1) - GOI |  | For Information Only
ENMAX | 24B138-24BT3 (SS-24) | 2023-03-28 10:00 | 2023-03-28 12:00 | N | N | Barlow DTT RTAC commissioning | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 24.81L (SS-24 - SS-31) | 2023-03-28 12:00 | 2023-03-28 14:00 | N | N | DTT RTAC commissioning | Line | 24 SUB - Barlow DTT RTAC Commissioning. |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 162B240-RB135 (SS-162), 162B240-RB136 (SS-162) | 2023-03-29 08:00 | 2023-03-30 18:00 | N | Y | relay, protection testing - 162RLY240-162.C60-3 | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK, ENMAX | 1109L (SS-25 - SS-65), 1080L (SS-25 - SS-65), 240kV West Bus (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25MD240-1109 (SS-25), 25MD240-1080 (SS-25) | 2023-03-29 08:00 | 2023-03-30 17:00 | N | N | , switch configuration of the lines to take 1080L out-of-service and put 1109L in service | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 2739s T1 (2739s Wabamun) | 2023-03-30 08:00 | 2023-04-06 17:30 | N | N | forced outage | Transformer |  |  | For Information Only
SUNCOR | 29EDD-1 260kV North Bus 1 (29EDD-1 Millennium) | 2023-03-30 09:00 | 2023-03-31 17:15 | N | Y | forced outage to repair switch 72 | Bus | Suncor found an issue while returning 29PL9-16. The line is closed but an issues was found with Switch 72 and breaker 952_101 will remain out @ 29EDD-1. |  | 240 kV
TRANSALTA | 1063s Windrise | 2023-03-30 09:00 | 2023-03-30 13:00 | N | N | maintenance | Station | oil leaks on T1 |  | Restricts Generation
ALTALINK | 896L (19s Wabamun - 432s Carvel), 19s 896 (19s Wabamun) | 2023-03-30 09:00 | 2023-03-30 17:30 | N | N | change 3 grading capacitors 19s896 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 254s 443X (254s Coaldale) | 2023-03-30 10:00 | 2023-03-30 15:30 | N | N | relocating revenue meter for new future relay space | Switch |  |  | For Information Only, Restricts Generation
ALTALINK | 1080L (SS-25 - SS-65) | 2023-03-30 17:01 | 2023-04-13 08:59 | N | Y | forced outage | Line |  |  | 240 kV
ALTALINK | 69s T4 (69s North Barrhead), 69s 713 (69s North Barrhead) | 2023-03-31 03:30 | 2023-04-25 12:00 | N | Y | forced outage | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 944L (132s Ware Junction - 275s Jenner), 275s 2 (275s Jenner), 275s 5 (275s Jenner), 132s 944 (132s Ware Junction) | 2023-03-31 18:00 | 2023-04-02 18:00 | N | Y | prepare for replacement of failed 275s2 breaker | Line, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24), 74s 24.83X (74s Janet) | 2023-04-02 08:00 | 2023-04-02 12:00 | N | Y | 24 sub - Barlow DTT RTAC commissioning | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29PL9-17 (29EDD-1 Millennium - 29EDD-94 Voyageur), 29EDD-1 952-104 (29EDD-1 Millennium), 29EDD-1 952-105 (29EDD-1 Millennium), 29EDD-94 29-952-9706 (29EDD-94 Voyageur), 29EDD-94 29-952-9705 (29EDD-94 Voyageur), 29EDD-1 29PS-410 (29EDD-1 Millennium), 29EDD-94 29PS-398 (29EDD-94 Voyageur), 29EDD-94 29PS-395 (29EDD-94 Voyageur), 29EDD-94 29PS-394 (29EDD-94 Voyageur) | 2023-04-03 06:00 | 2023-04-17 18:00 | N | Y | CBR project sync panel tie-in and IMS panel tie-in and bus corrective and preventative maintenance | Line, Circuit Breaker, Switch | 29PL9-17 Line Outage To Support CBR Project Sync Panel Tie-in and IMS Panel Tie-in - Cut in 1 x F35 IMS relay at 29EDD-1X P&C building. - CT & PT tie-in to new IMS F35 relay at Millennium Substation. - Breaker status tie-in to IMS relay at Millennium Substation. - CT & PT tie-in to IMS relay at Voyageur Substation. - Disconnect switches status tie-in to IMS relay at Millennium Substation. - Breaker status tie-in to IMS relay at Voyageur Substation. - Breaker status tie-in to Sync Panel at Voyageur Substation. - Disconnect switches status tie-in to IMS relay at Voyageur Substation - PT tie-in to Sync Panel at Voyageur Substation. - Includes 29PP-97 |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 262s 870W (262s Rocky Mountain House) | 2023-04-03 07:00 | 2023-04-09 18:00 | N | Y | line clearance mitigation work | Line, Circuit Breaker | Line Clearance Mitigation (LCM) work on Structures #79, 104, 180, 181, 192, 195, 205, 207, 209, 217 & 218. Crew will be installing cross arm extensions and horizontal line posts to existing structures. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 987s CCP7213 (987s Clover Bar) | 2023-04-03 07:00 | 2023-04-04 17:00 | N | N | first day- apparatus CCP7213 breaker maintenance, second day- P&C CCP7213 breaker fail op checks | Circuit Breaker |  |  | For Information Only
EPCOR | EP 805s J2405 (EP 805s Jasper) | 2023-04-03 07:00 | 2023-04-03 17:00 | N | Y | P&C- maintenance and op checks | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 33.2TR (SS-33) | 2023-04-03 08:00 | 2023-04-05 18:00 | N | N | U/O voltage alarm, investigations and repairs and oil sampling MT, TC | Transformer |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays) | 2023-04-03 08:00 | 2023-04-03 17:00 | N | Y | replace cross arms and insulators at structure 350 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 916L (5s East Calgary - 42s Sarcee) | 2023-04-03 09:15 | 2023-04-05 15:45 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 1082L (63s Red Deer - 287s Hazelwood) | 2023-04-03 09:15 | 2023-04-05 17:45 | N | Y | replace glass and tower hardware str. 1-60 FRM | Line |  |  | 240 kV, Pre-Condition
ATCO | EX1-01L (402s Scotford Expansion One - 879s Upgrader), 879s 701T (879s Scottford Upgrader), 879s 152 (879s Upgrader), 879s 352 (879s Upgrader), 879s 701TD (879s Upgrader), 879s 52-LA (879s Upgrader) | 2023-04-03 10:00 | 2023-04-14 16:45 | N | Y | breaker maintenance 152 and 352, RTXP switch replacements for bus 1 PRC 005 relay and trip coil testing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 813s 709 (813s Little Smoky), 813s 710 (813s Little Smoky), 733s 702 (733s Simonette) | 2023-04-03 10:01 | 2023-04-07 15:29 | N | Y | emergency breaker gas top up and 813S Little Smoky rebuild - complete 7L40 wiring panel 7P5, 709, 710 CT/PT/P&C wiring, demo existing wiring/cabling, remove old panel 4G relay programming and functionality commission control, alarms and status | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
CMH, ALTALINK | 15L (MHS-7 Brier Park - MHS-9 South Saskatchewan), 882L (MHS-7 Brier Park - 321s Al Rothbauer), MHS-7 138-T71 (MHS-7 Brier Park), MHS-7 MH69-706 (MHS-7 Brier Park), MHS-7 MH138-707 (MHS-7 Brier Park) | 2023-04-04 07:00 | 2023-04-04 13:00 | N | N | replace CVT disconnect switches: REV_PT_A/B/C, 138CVT_72A/B/C, 138CVT_74A, 69CVT_75A | Line, Transformer, Circuit Breaker |  | *** CMH work has been planned to coincide with planned AltaLink 882L outage already on AESO schedule for approved outages (see below) *** | Pre-Condition, Restricts Generation, Affects Cranking Path
EPCOR | 330p 1208 (330p Genesee) | 2023-04-04 07:00 | 2023-04-04 17:00 | N | Y | emergency low gas top up | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 523s 138kV Bus 1 (523s Bullshead), 600L (404s Peace Butte - 523s Bullshead), 880L (321s Al Rothbauer - 523s Bullshead), 523s T1 (523s Bullshead), 523s C1 (523s Bullshead), 523s 552 (523s Bullshead), 523s 880 (523s Bullshead), 404s 600 (404s Peace Butte), 404s 12 (404s Peace Butte), 404s T2 (404s Peace Butte), 404s T1 (404s Peace Butte), 523s 1 (523s Bullshead) | 2023-04-04 07:30 | 2023-04-07 09:30 | N | N | 404sT1 Doble, maintenance, and leak fix, 404s600 breaker maintenance, 523s1, 523s17, & 523s18 switch replacements | Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 275s T3 (275s Jenner), 601L (230s Wardlow - 275s Jenner), 230s T1 (230s Wardlow), 230s 601 (230s Wardlow), 275s 83 (275s Jenner), 275s 601 (275s Jenner) | 2023-04-04 07:30 | 2023-04-05 18:00 | N | N | 230s T1 and 275s T3 doble and maintenance, repair 275s601 DC ground and 275s84 neutral and 275s83 breaker maintenance | Transformer, Line, Switch, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK, ENBRIDGE | 703L (377s AML Hardisty - 703BL tap), 703L (213s Hughenden - 703BL tap), 703BL (329s HRT Express - 703L tap), 377s 17 (377s AML Hardisty), 329s HRT-S2 (329s Hrt Express), 329s PTX-101 (329s Hrt Express) | 2023-04-04 07:30 | 2023-04-04 18:00 | N | N | fix 40-degree hotspot on 377s18 | Line, Switch, Transformer | Fix 40-degree hotspot on 377s18. 329s will be offline for the duration of the outage. |  | Creates Radial Feeds, Firm Load Loss
AOSI | BRD1 Burdett Solar | 2023-04-04 08:00 | 2023-04-05 17:00 | N | N | termination of MV Cable | Unit | - Termination of MV Cable - Install new card in 751 P&C Relay - P&C wiring changes-ground block - Synchro-transfer/trip proving - Synchro-ruggedcom (swap) & IP Addressing - P2-751 Injection testing post RTAC Update & Verify ground block |  | For Information Only
ALTALINK, CMH | 882L (MHS-7 Brier Park - 321s Al Rothbauer), 321s 252 (321s Al Rothbauer) | 2023-04-04 08:00 | 2023-04-04 17:00 | N | Y | implement new 'Init DDR' from 11(96/25SC)/252, connect L2/252 CT from A87/138B1 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation,Affects Cranking Path
ALTALINK | 190L (17s Benalto - 320p Keephills), 17s 1 (17s Benalto), 17s 2 (17s Benalto), 17s 190N (17s Benalto) | 2023-04-04 08:00 | 2023-04-04 18:00 | N | Y | urgent repairs to 17s190N | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 121s T2 (121s Brooks) | 2023-04-04 08:00 | 2023-04-04 16:00 | N | N | remove bird cover from 25 kV bushings on T2 transformer for measurement then re-install them | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 65s T3 (65s High River), 65s 54 (65s High River) | 2023-04-04 13:00 | 2023-04-13 17:00 | N | N | 65sVT8 leaking urgent replacement and replace failed 25 kV component | Transformer, Switch |  | Catastrophic failure on bus that was being worked on. | For Information Only
EPCOR | 113s T1 (113s Inland Cement) | 2023-04-04 19:00 | 2023-04-16 19:00 | N | N | transformer doble and bus-duct inspection | Transformer |  |  | For Information Only
ALTALINK | 749L (899s Edgerton - 749AL tap) | 2023-04-05 07:00 | 2023-04-05 18:00 | N | Y | re-tie OHSW at structure 267 and hardware tighten structure 269 | Line | Re-tie OHSW at structure 267 and hardware tighten structure 269. |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 121s T5 (121s Brooks) | 2023-04-05 08:00 | 2023-04-05 16:00 | N | N | remove bird cover | Transformer | Remove bird cover from 25kv bushings on T5 transformer for measurement then re-install them. Transmission Constraint record created. |  | For Information Only, Restricts Generation
ATCO | 848s 901T (848s Ruth Lake) | 2023-04-05 08:40 | 2023-04-06 19:54 | N | Y | forced outage | Transformer |  |  | 240 kV
ATCO | 815s 706C (815s Goodfare) | 2023-04-05 10:00 | 2023-04-05 12:00 | N | N | PRC-005 trip coil testing breaker 815S 706 | Shunts | PRC-005 trip coil testing breaker 815S 706 |  | Pre-Condition
ATCO | 815s 705C (815s Goodfare) | 2023-04-05 12:01 | 2023-04-05 14:00 | N | N | trip coil testing breaker 815S 705 (PRC-005) | Shunts |  |  | Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-04-05 23:00 | 2023-04-06 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-04-06 03:00 | 2023-04-06 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23), 23B138-2.80 (SS-23), 23MD138-23.3TR (SS-23), SW83 (SS-23) | 2023-04-06 08:00 | 2023-04-06 12:00 | N | N | spring substation washing, 23 Sub SW 82 - retrieve nameplate info, check reversing switch | Line, Transformer, Circuit Breaker, Switch | Spring Substation Washing. 23 Sub SW 82 -Retrieve Nameplate Info. Check reversing switch |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-34 29PT-340 (29EDD-34), 29EDD-34 29-952-133 (29EDD-34), 29EDD-34 29-952-132 (29EDD-34), 29EDD-34 29PS-0372 (29EDD-34), 29EDD-34 29PS-0378 (29EDD-34) | 2023-04-06 08:00 | 2023-04-11 18:00 | N | Y | upgrade ground fault relay and test for 29PT-340 | Transformer, Circuit Breaker, Switch | Upgrade SEL330 Ground fault relay and Test for 29PT-340. | Other pressing emergency issues occurred. | 240 kV, Contingency Requires Mitigation
Syncrude | 4345 (Syncrude Mildred Lake), 4435 (Syncrude Mildred Lake), 435 (Syncrude Mildred Lake) | 2023-04-06 08:00 | 2023-04-25 20:00 | N | N | maintenance and repairs | Circuit Breaker | Non-Significant Outage: T4 isolatin in Plant 31 to perform 6 year maintenance and repairs. The following breakers will be operated: CB - 435 and 4435, 4345 @ Plant 31 Substation The following disconnect switches will be operated: 434 @ Plant 31 Switchyard The following Transformer will be offline and isolated: T4 Transformer @ Plant 31 Switchyard |  | For Information Only, Restricts Generation
ALTALINK | 74s23_80 (23_80L) Open Advice for Enmax | 2023-04-06 12:00 | 2023-04-06 18:00 | N | N | spring substation washing | Terminal Equipment |  |  | For Information Only
AESO-SC | OATI | 2023-04-06 18:00 | 2023-04-06 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
ATCO | 848s 908 (848s Ruth Lake) | 2023-04-06 20:00 | 2023-04-15 17:00 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 394s T1 (394s Empress) | 2023-04-07 07:00 | 2023-04-12 17:00 | N | N | install new single-phase PT on the line side of 394s64, add CTs from T1 to new protections. | Transformer |  |  | For Information Only
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 813s 709 (813s Little Smoky), 813s 710 (813s Little Smoky) | 2023-04-07 15:30 | 2023-04-14 12:00 | N | Y | 813S Little Smoky rebuild - complete 7L40 wiring panel 7P5, 709, 710 CT/PT/P&C wiring, demo existing wiring/cabling, remove old panel 4G relay programming and functionality commission control, alarms and status | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27), 27.1TR (SS-27), 27MD69-27.1TR (SS-27), SW64 (SS-27) | 2023-04-08 08:00 | 2023-04-08 16:00 | N | N | maintenance required SW62 at 27 sub - blades not fully rotated in jaw | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 757s 704 (757s Battle River) | 2023-04-09 08:00 | 2023-04-22 17:00 | N | Y | customer work on 704B switch | Circuit Breaker |  |  | Restricts Generation
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.3TR (SS-31), 31.2TR (SS-31), 31B138-24.81 (SS-31), 31B138-31.84 (SS-31), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31), SW83 (SS-31) | 2023-04-09 08:00 | 2023-04-09 13:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.80L (SS-9 - SS-31), 31.1C (SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31B138-9.80 (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31), SW84 (SS-31) | 2023-04-09 13:01 | 2023-04-09 18:00 | N | N | spring substation washing | Line, Shunts, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain) | 2023-04-09 22:12 | 2023-04-11 02:20 | N | N | forced outage | Line |  | Line Returned To Service | Affects Cranking Path
SUNCOR | 29PL9-4 (29EDD-1 Millennium - 29EDD-3), 29EDD-3 29PT-5 (29EDD-3), 29EDD-1 29EDD1s252 (29EDD-1 Millennium), 29EDD-1 29EDD1s352 (29EDD-1 Millennium), 29EDD-1 29EDD1SPL9-4 (29EDD-1 Millennium), 29PS-15 (29EDD-3) | 2023-04-10 06:00 | 2023-05-09 18:00 | N | Y | replace 29PT-5 transformer and upgrade line protection relays | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ALTALINK, ENMAX | 1107L (237s Foothills - SS-65), 65B240-D134 (SS-65), 65B240-D133 (SS-65) | 2023-04-10 07:00 | 2023-04-15 16:00 | N | Y | 65 sub cable trench replacement | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 41.84L (SS-41 - SS-54), 41B138-41.84 (SS-41), 54B138-41.84 (SS-54) | 2023-04-10 08:00 | 2023-04-14 16:00 | N | N | sub 41 - 41B138-41.84 CT replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 944L (132s - 275s) - GOI, 275s 5 (275s Jenner), 275s 2 (275s Jenner) | 2023-04-10 11:00 | 2023-04-12 17:00 | N | Y | Urgent repair - Expand 275s2 GOI zone to include 944L for pile and breaker installation. After this outage zone will be reduced back to 275s2 only. | Terminal Equipment, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2023-04-11 06:15 | 2023-04-12 13:00 | N | N | remove existing cross arms and install horizontal line post due to clearance violations to the underbuild (str 393,395) | Line |  | Extended due to weather. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28), SW83 (SS-28), 28MD138-28.1TR (SS-28) | 2023-04-11 08:00 | 2023-04-11 11:59 | N | N | spring substation washing. | Line, Transformer, Circuit Breaker, Switch | Spring Substation Washing. SW 83 -Retrieve Nameplate Info. Check reversing switch. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 722L (107s Westfield - 368s Burdett), 107s T1 (107s Westfield) | 2023-04-11 08:00 | 2023-04-11 16:00 | N | Y | T1 requires lightning arrester grounding updates | Line, Transformer | T1 requires lightning arrester grounding updates |  | Restricts Generation
ATCO | 757s 702T (757s Battle River) | 2023-04-11 08:00 | 2023-04-17 18:00 | N | N | work on 702T | Transformer |  | Manpower issue | For Information Only
ATCO | 7L128 (802s Michichi Creek - 7LA128 tap), 802s 704 (802s Michichi Creek) | 2023-04-11 09:00 | 2023-04-12 15:00 | N | N | 144KV bus relay addition New 704CT input wiring | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 1082L (63s Red Deer - 287s Hazelwood) | 2023-04-11 09:15 | 2023-04-13 10:04 | N | Y | replace glass and tower hardware str. 1-60 FRM | Line |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook), 330p 1201 (330p Genesee), 330p 1202 (330p Genesee) | 2023-04-11 09:30 | 2023-04-13 17:00 | N | Y | 1238L zone CVT(1201)/arrestor(1201) doble | Line, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station), 240BA2 (629s Argyll Transfer Station - 814s Bellamy) | 2023-04-11 09:30 | 2023-04-14 17:00 | N | Y | Argyll: 240BA2 surge arrestor LCR and ADS1 disconnect maintenance | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28.2TR (SS-28), 28B138-28.80 (SS-28), 28MD138-28.2TR (SS-28), SW82 (SS-28) | 2023-04-11 12:00 | 2023-04-11 18:00 | N | Y | spring substation washing | Line, Transformer, Circuit Breaker, Switch | Spring Substation Washing. SW 80 -Retrieve Nameplate Info. Check reversing switch. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 61s T2 (61s Lodgepole) | 2023-04-11 12:00 | 2023-04-11 16:00 | N | N | urgent outage to repair 61s46 | Transformer | urgent outage to repair 61s46 |  | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake), 63s 648 (63s Red Deer) | 2023-04-11 12:30 | 2023-04-11 17:30 | N | N | 138kV Breaker Maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Meadowlark) | 2023-04-11 12:30 | 2023-04-12 17:00 | N | N | forced outage on T1 | Transformer | Reactor Repair. |  | For Information Only
ALTALINK | 535s 152 (535s Joffre) | 2023-04-11 13:00 | 2023-04-11 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALPAC | 282s RTU/SCADA (282s Grassland (Alpac)) | 2023-04-12 01:00 | 2023-04-12 05:00 | N | N | SCADA and phone outage | Terminal Equipment |  |  | For Information Only
CNRL | 7LPE1 (641s PES1 - 859s Primrose), 641s 701T (641s Primrose East), 641s 702 (641s PES1), 641s 702T (641s Primrose East), 641s 704 (641s PES1) | 2023-04-12 05:00 | 2023-04-12 19:00 | N | N | substation repairs and maintenance | Line, Transformer, Circuit Breaker |  | Outage returned early | For Information Only
ATCO | 7L35 (859s Primrose - 7L35 tap), 7L574 (822s Wolf Lake - 7L574 tap), 7L574 (970s Bourque - 7L574 tap), 822s 702 (822s Wolf Lake) | 2023-04-12 07:00 | 2023-04-12 23:00 | N | Y | 7L35 pole change | Line, Circuit Breaker | Require GOI on 7L35 for pole change. Change 144kV 67A & 82A as part of mitigation from test & treat for CNRL. |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 7L35 (859s Primrose - 7L35 tap) | 2023-04-12 07:00 | 2023-04-13 07:00 | N | Y | pole replacements | Line | Changing (2) 144kV Running Corner & Double Dead-End Corner Pole Replacements as part of mitigation from test & treat. Pole replacements will be done with the 7L35 OH line de-energized. ATCO Electric will be performing these pole replacements. |  | Restricts Generation
SUNCOR | 29EDD-34 29PT-341 (29EDD-34), 29EDD-34 29-952-142 (29EDD-34), 29EDD-34 29-952-143 (29EDD-34), 29EDD-34 29PS-0375 (29EDD-34), 29EDD-34 29PS-0383 (29EDD-34) | 2023-04-12 08:00 | 2023-04-18 18:00 | N | Y | upgrade ground fault relay | Transformer, Circuit Breaker, Switch | Upgrade SEL330 Ground fault relay and Test for 29PT-341 |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 535s T6 (535s Joffre) | 2023-04-12 08:00 | 2023-04-12 17:30 | N | N | replace tap changer pressure relay | Transformer |  |  | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake), 63s 648 (63s Red Deer), 580s 648 (580s Sylvan Lake) | 2023-04-12 08:00 | 2023-04-12 12:29 | N | N | 138kV breaker maintenance, changing LA's | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 22.1TR (SS-22), 22.3TR (SS-22), 22B138-13.82 (SS-22), 22B138-22BT8 (SS-22), 22MD138-22.1TR (SS-22), 22MD138-22.3TR (SS-22) | 2023-04-12 08:00 | 2023-04-12 12:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch | Spring Substation Washing. Check reversing switch 22.1(X,Y), 22.3. 22MD138-22.1TR - motor/manual contact - needs replacement |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 410s T2 (410s Josephburg) | 2023-04-12 09:00 | 2023-04-13 16:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22BT8 (SS-22), 22B138-22.81 (SS-22), 22MD138-22.2TR (SS-22), SW85 (SS-22) | 2023-04-12 12:01 | 2023-04-12 18:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch | Spring Substation Washing. Check reversing switch 22.2(X,Y) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake), 580s 637 (580s Sylvan Lake) | 2023-04-12 12:31 | 2023-04-12 17:30 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L25 (768s Rowley - 802s Michichi Creek), 802s 707 (802s Michichi Creek) | 2023-04-12 15:01 | 2023-04-14 16:00 | N | N | 144kV bus relay addition | Line, Circuit Breaker | 144KV Bus relay addition New 707CT input wiring |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T3 (Meadowlark), M723 (Meadowlark), M724 (Meadowlark), MAB3 (Meadowlark) | 2023-04-13 07:00 | 2023-04-16 17:00 | N | N | M723 breaker maintenance and CT Doble | Transformer, Circuit Breaker, Switch |  |  | Firm Load Loss, Pre-Condition
ALTALINK | 427L (63s Red Deer - 247s Piper Creek), 63s 427 (63s Red Deer), 247s 427 (247s Piper Creek) | 2023-04-13 08:00 | 2023-04-14 17:30 | N | N | gas leak repair | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), 9MD138-9.1TR (SS-9), SW89 (SS-9) | 2023-04-13 08:00 | 2023-04-13 18:00 | N | N | spring substation washing. | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 255s 34 (255s Vulcan), 928s 180N (928s East Stavely) | 2023-04-13 08:00 | 2023-04-17 08:00 | N | Y | demo old 180L line protections and install new A and B protections, add new maintenance switch 43M/452 (breaker 255s34) | Line, Circuit Breaker, Switch | Breaker Outage at 255s Vulcan to demo old 180L line protections and install new A and B protections. Add new maintenance switch 43M/452 (breaker 255s34) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 1080L (SS-25 - SS-65) | 2023-04-13 09:00 | 2023-05-04 09:45 | N | Y | civil work to replace 1080L Phase "C" cable | Line |  |  | 240 kV
ATCO | 840s McNeill Station | 2023-04-14 | 2023-05-17 13:00 | N | Y |  | Station |  |  | Limits ATC
SUNCOR | 29PL9-4 (29EDD-1 Millennium - 29EDD-3) | 2023-04-14 08:00 | 2023-04-18 20:00 | N | Y | Millennium 260 kV bus jumper replacement related to existing 29PL9-4 | Line |  | 260kV Section of ring bus related to GTG5(between 29EDD1S3 | 240 kV
EPCOR | T2 (Garneau) | 2023-04-14 08:00 | 2023-05-02 16:00 | N | N | P1649 Garneau upgrade. ISD Apr 25, 2023 | Transformer
ENMAX | 2.81L (SS-2 - SS-9), 9B138-2.81 (SS-9) | 2023-04-14 08:00 | 2023-04-17 16:00 | N | N | line clearance mitigation | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 237s T1 (237s Foothills) | 2023-04-15 08:30 | 2023-04-16 16:30 | N | Y | PRC5 doble maintenance and IDD | Transformer | PRC5 Doble Maintenance and IDD |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO, ENEL | 7L65 (709s Vegreville - 7LA65 tap), 7L65 (710s Vermilion - 7LA65 tap), 7LA65 (708s Grizzly Bear - 7L65 tap), 710s 703 (710s Vermilion), 708s 52T1 (708s Grizzly Bear), 708s 89-L1 (708s Grizzly Bear) | 2023-04-16 07:00 | 2023-04-25 17:00 | N | Y | 7L65 rebuild project | Line, Circuit Breaker, Switch | 7L65 Rebuild Project. Will need total line outage from Apr. 18 07:00 - 12:00, 2023 - Isolation points 709S 7L65D1, 710S 703A, 7LA65D1 Apr. 18 12:01 - Apr. 30 17:30, 2023 shrink GOI - Isolation points 710S 703A and Jumper J2 Apr. 30 07:00 - 11:59 Phase in new portion of 7L65 that feeds east - After phasing is confirmed, close 7L65D3 and breaker 703 at 710S. - Need to remove flying taps off of west portion to 709S Apr. 30 12:00 - 17:30 - Isolation Points 709S 7L65D1, 7L65D2 |  | Overload, Pre-Condition
ALTALINK | 227s Cutting Lake, 831L (121s Brooks - 831AL tap), 831L (339s Duchess - 831AL tap), 227s 831AW (227s Cutting Lake) | 2023-04-16 08:00 | 2023-04-16 17:00 | N | N | replace cross arms and insulators at structure 37 | Station, Line, Circuit Breaker | Replace crossarms and insulators at structure 37. 2nd scope @ 227s:T1 TX18320 leak repair, s831AW fluid leak, s1 bird nest |  | For Information Only, Pre-Condition
ALTALINK | 944L (132s Ware Junction - 275s Jenner), 275s 2 (275s Jenner), 275s 5 (275s Jenner), 275s 944W (275s Jenner) | 2023-04-16 11:00 | 2023-04-16 14:00 | N | Y | 275s2 re-energization | Line, Circuit Breaker, Switch | 944L outage required for 275s2 re-energization. |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 113s T2 (113s Inland Cement) | 2023-04-16 19:00 | 2023-04-27 17:59 | N | N | doble and bus-duct inspection | Transformer | Inland Cement: TX2 Doble and BUS-Duct Inspection |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy) | 2023-04-17 07:00 | 2023-04-19 17:00 | N | Y | disconnect maintenance and arrestor doble | Line | Argyll ADS2 Disconnect Maintenance, 240BA3 CT/Arrestor Doble and Petrolia 1055L CT/CVT/Arrestor Doble |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 987s T4 (987s Clover Bar), 987s C2408 (987s Clover Bar) | 2023-04-17 07:00 | 2023-04-21 17:00 | N | Y | transformer doble | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
ENMAX | 65B240-D135 (SS-65) | 2023-04-17 07:00 | 2023-04-18 16:00 | N | Y | 65 sub cable trench replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 510s ACF21 (510s Sunnybrook), 510s ACF22 (510s Sunnybrook), 510s 1952 (510s Sunnybrook), 510s 2052 (510s Sunnybrook), 510s 35 (510s Sunnybrook), 510s 36 (510s Sunnybrook), 510s 79 (510s Sunnybrook), 510s 80 (510s Sunnybrook) | 2023-04-17 07:30 | 2023-04-21 16:30 | N | Y | AC filter bank maintenance and inspection | Shunts, Circuit Breaker, Switch | Cap replacement, filter bank inspection, Breaker Dashpot Inspection, 6MD66 and TDC maintenance. |  | 500 kV, Pre-Condition
BCH | 5L94 (BCH Cranbrook - 102s Langdon) | 2023-04-17 08:00 | 2023-04-17 10:00 | Y | Y | isolate reactor at Cranbrook | Line |  | (1) 5D45 interrupter replacement (2) CBk 5RX5 non electrical PM | 500 kV, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32), 32.83L (SS-32 - SS-40), 32.1TR (SS-32), 32.2TR (SS-32), 32B138-32BT5 (SS-32), 32B138-26.81 (SS-32), 32B138-32.83 (SS-32), 32MD138-32.1TR (SS-32), 32MD138-32.2TR (SS-32), SW83 (SS-32), SW89 (SS-32) | 2023-04-17 08:00 | 2023-04-17 12:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  | Spring Substation Washing. SW 84, SW 85, SW 86, 32.2MD -Retrieve Nameplate Info. Check reversing switch 32.1, 32.2. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2023-04-17 08:00 | 2023-04-17 10:00 | Y | Y | to isolated CBK 5RX5 | Line |  |  | 500 kV, Affects Cranking Path
ENMAX | 162B138-RB81 (SS-162) | 2023-04-17 08:00 | 2023-04-17 12:00 | N | N | HV breaker SF6 gas sample, breaker dashpot checks | Circuit Breaker | HV breaker SF6 Gas Sample - 162B138-RB81. Breaker Dashpot Checks - 162B138-RB81 |  | Contingency Requires Mitigation
ENMAX | SS-7 | 2023-04-17 08:00 | 2023-04-17 16:00 | N | N | 7PT138-Z31 outage and power factor test | Station |  |  | For Information Only, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2023-04-17 08:00 | 2023-04-17 10:00 | Y | Y | align with 1201L outage | Line |  |  | 240 kV, Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 27B69-13.60 (SS-27), 13B69-13.60 (SS-13) | 2023-04-17 08:00 | 2023-04-21 16:00 | N | N | replace 13sub 69 kV PTs | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.1C (SS-31) | 2023-04-17 08:00 | 2023-04-17 16:00 | N | N | relay, protection testing | Shunts |  |  | Pre-Condition
ALTALINK | 180L (15s Fort Macleod - 180AL tap), 15s 180N (15s Fort Macleod) | 2023-04-17 08:01 | 2023-04-21 08:00 | N | Y | breaker outage | Line, Circuit Breaker |  | Breaker Outage at 15s Fort Macleod to demo old 180L line protections and install new A and B protections. Relocate B85/L5(15s 180L teleprotection logic processor) to new control building. Replace 15s180N breaker fail relay, trips to be tied in live and trip tested during later outages. Add new maintenance switch 43M/552 (breaker 15s180N) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
BCH | 5RXN5 (BCH Cranbrook) | 2023-04-17 09:00 | 2023-04-23 16:00 | N | Y |  | Shunts |  |  | 500 kV
ATCO | 802s 705C (802s Michichi Creek) | 2023-04-17 09:00 | 2023-04-18 16:00 | N | N | 144 kV bus relay addition, new 705CT input wiring | Shunts |  |  | Pre-Condition
ATCO, ALTALINK | 9L966 (650s Hansman Lake - 932s Pemukan), 966L (650s Hansman Lake - 932s Pemukan), 932s 904 (932s Pemukan), 932s 905 (932s Pemukan), 650s 452 (650s Hansman Lake), 650s 552 (650s Hansman Lake), 932s 9L966D1 (932s Pemukan), 650s 966 (650s Hansman Lake) | 2023-04-17 09:30 | 2023-04-21 17:30 | N | Y | modifications to RAS 201 to include 9L966/966L LTO | Line, Circuit Breaker, Switch |  |  | 240 kV, Overload, Pre-Condition
ATCO | ALC02L (409s Shell Scotford - 879s Upgrader), 879s 702T (879s Scotford Upgrader), 879s 352 (879s Upgrader), 879s 252 (879s Upgrader), 879s 52-1B (879s Upgrader), 879s 702TD (879s Upgrader) | 2023-04-17 10:00 | 2023-04-28 16:45 | N | Y | PRC 005 relay and trip coil testing, breaker maintenance, switch replacements | Line, Transformer, Circuit Breaker, Switch |  | 252, 352 Complete Breaker Maintenance RTXP Switch Replacements for Bus 2 PRC 005 Relay and trip coil testing | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 740s 701 (740s H.R. Milner), 740s 701B (740s H.R. Milner) | 2023-04-17 10:00 | 2023-06-05 16:00 | N | Y |  | Circuit Breaker, Switch | Replace Damaged switch Arm on 701B |  | Pre-Condition, Restricts Generation
ATCO | 848s 905 (848s Ruth Lake), 848s 905B (848s Ruth Lake) | 2023-04-17 10:00 | 2023-04-17 13:00 | N | Y | PRC trip coil testing | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 158s T2 (158s Vauxhall) | 2023-04-17 12:00 | 2023-04-23 18:00 | N | Y | bushing replacement and maintenance | Bus | 138kV Transformer Bushing replacement & maintenance |  | Restricts Generation
ALTALINK | 37s T3 (37s North Calder) | 2023-04-17 12:00 | 2023-04-20 18:00 | N | N | first trip and maintenance | Transformer |  | First trip and maintenance on 37s14, T3: fix leaks, replace LA standoffs, install bird cover upgrade. install coresense, fix leaks, doble | For Information Only
ENMAX | 162B138-RB82 (SS-162) | 2023-04-17 12:00 | 2023-04-17 16:00 | N | N | HV breaker SF6 gas sample, dashpot checks | Circuit Breaker | HV breaker SF6 Gas Sample - 162B138-RB82. Breaker Dashpot Checks - 162B138-RB82 |  | Contingency Requires Mitigation
ALTALINK | 276s 25 (276s Prentiss) | 2023-04-17 12:30 | 2023-04-20 17:30 | N | N | 138 kV CT replacement | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 42s 70 (42s Sarcee) | 2023-04-17 12:30 | 2023-04-17 17:30 | N | Y | urgent open breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32), 32B138-31.84 (SS-32), 32MD138-32.3TR (SS-32) | 2023-04-17 13:00 | 2023-04-17 18:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  | Spring Substation Washing. Check reversing switch | Pre-Condition
ATCO | 848s 907 (848s Ruth Lake), 848s 907B (848s Ruth Lake) | 2023-04-17 13:01 | 2023-04-17 16:00 | N | Y | PRC trip coil teting | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 729L (40s Wetaskiwin - 729AL tap), 40s 729E (40s Wetaskiwin) | 2023-04-17 14:00 | 2023-04-17 17:00 | N | N | 1st trip PRC5 maintenance on 40s 729E | Line, Circuit Breaker | 1st trip PRC5 maintenance on 40s729E |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge) | 2023-04-18 06:15 | 2023-04-21 17:45 | N | N | line move | Line | Line move; will install 2 new structures 62A & 63, and salvaged the existing structure 63 | outage extended. | Pre-Condition
CMH | MH-65L (MHS-7 Brier Park - Cancarb Energy Medicine Hat), MHS-7 Brier Park | 2023-04-18 07:00 | 2023-04-18 19:00 | N | Y | maintenance 69 kV disconnect switch | Line, Station | Maintenance on 69kV disconnect switch SW-900 ; Issue GOI | Cancarb 69 kV BKR-900 Breaker Cancarb 69 kV SW-900 Switch MH69-709 Breaker MH69-726 Switch 69CVT_76A Voltage Transformer (Disconnect Switch & Fuses) | Restricts Generation
CMH | MH-60L (MHS-5 NE Crescent Heights - MHS-7 Brier Park), MHS-5 MH69-514 (MHS-5 NE Crescent Heights) | 2023-04-18 08:00 | 2023-04-18 11:00 | N | N | replace disconnect switch | Line, Circuit Breaker |  |  | Restricts Generation
ENMAX | SS-7 | 2023-04-18 08:00 | 2023-04-18 16:00 | N | N | 7PT138-Z32 outage and power factor test | Station |  |  | For Information Only, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20), 20MD138-20.1TR (SS-20), SW83 (SS-20) | 2023-04-18 08:00 | 2023-04-18 12:00 | N | N | spring substation washing and check reversing switch | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 394s T2 (394s Empress) | 2023-04-18 09:00 | 2023-04-25 13:00 | N | N | replace 1907L power cables, add CTs from T2 to new protections, trip testing of 394s1152 | Transformer |  |  | For Information Only
ALTALINK | 256s 719N (256s Harmattan), 719L (256s Harmattan - 719CL tap) | 2023-04-18 09:00 | 2023-04-18 12:00 | N | N | prc 1st trip breaker testing and maintenance | Circuit Breaker, Line | PRC 1st Trip breaker testing and maintenance |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 930s Syn Condenser (930s Arcenciel), 930s 702T (930s Arcenciel), 930s 719 (930s Arcenciel), 930s 406 (930s Arcenciel), 930s 407 (930s Arcenciel) | 2023-04-18 09:30 | 2023-04-20 16:00 | N | Y | sync condenser maintenance, 406T maintenance, AHU fall service | Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake), 40s 858N (40s Wetaskiwin) | 2023-04-18 09:30 | 2023-04-18 18:00 | N | N | maintenance and repair | Line, Circuit Breaker | 1st trip PRC5 maintenance on 40s858N and repair 40s102 |  | Over/Under Voltage, Pre-Condition
ATCO | 848s 908 (848s Ruth Lake), 848s 908B (848s Ruth Lake) | 2023-04-18 10:00 | 2023-04-18 13:00 | N | Y | prc trip coil testing | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 20.82L (SS-20 - SS-21), 20.3TR (SS-20), 20B138-20.82 (SS-20), SW84 (SS-20), 20MD138-20.3TR (SS-20) | 2023-04-18 12:00 | 2023-04-18 18:00 | N | N | spring substation washing and check reversing switch | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 166L (256s Harmattan - 166AL tap), 256s 166E (256s Harmattan) | 2023-04-18 13:00 | 2023-04-18 16:00 | N | N | PRC 1st Trip breaker testing and maintenance | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 848s 913 (848s Ruth Lake), 848s 913B (848s Ruth Lake) | 2023-04-18 13:01 | 2023-04-18 16:00 | N | Y | prc trip coil testing | Circuit Breaker, Switch | PRC trip coil testing |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s RTU/SCADA (987s Clover Bar) | 2023-04-19 01:00 | 2023-04-19 02:00 | N | N | maintenance to our network equipment | Terminal Equipment | IT/Telus will be performing some maintenance to our network equipment, and during this time, our AESO communication connectivity will be disrupted. However, EMOC/Site can verbally communicate MW capacity and generation status. ADAMS dispatch communication will not be affected. Cloverbar Voip phones (780-392-5571, etc), site satellite phone (011 881 6 514 17753), and operator cell phones (780-935-5001 & 587-334-2389) will also be unaffected. |  | Affects Visibility
ENMAX | 65B240-D132 (SS-65) | 2023-04-19 07:00 | 2023-04-20 16:00 | N | Y | 65 sub cable trench replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap) | 2023-04-19 07:00 | 2023-04-19 18:00 | N | N | replace stub pole and install new ground rod at structure 30 | Line | Replace stub pole and install new ground rod at structure 30. |  | Creates Radial Feeds, Firm Load Loss
EPCOR | EP 511s Victoria T4 (EP 511s Victoria) | 2023-04-19 07:00 | 2023-04-21 17:00 | N | N | surge arrestor LCR | Transformer |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43) | 2023-04-19 08:00 | 2023-04-22 18:00 | N | N | oil sampling | Line, Circuit Breaker | Oil sampling, Sheath testing. Power Factor Test LA's and Potheads - 33.84. Power factor test 43B138-33.84 and CT. 33B138-33.84-CT |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.2TR (SS-2), 2B138-D86 (SS-2), 2B138-D87 (SS-2), 2MD138-2.2TR (SS-2), MD91 (SS-2), MD92 (SS-2) | 2023-04-19 08:00 | 2023-04-19 16:00 | N | N | summer substation washing | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ALTALINK | 320p 2089 (320p Keephills) | 2023-04-19 08:00 | 2023-05-02 19:00 | N | Y | maintenance | Switch |  |  | 500 kV, Restricts Generation
ALTALINK | 349s T1 (349s Stavely), 349s 197 (349s Stavely), 349s 20 (349s Stavely) | 2023-04-19 08:00 | 2023-04-23 17:00 | N | Y | replace 349s10 breaker and implement new AIS scheme for 349s14 | Transformer, Circuit Breaker, Switch | 1st Scope: Replace 349s10 breaker 2nd scope: Implement new AIS scheme for 349s14 |  | Pre-Condition, Restricts Generation
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 706 (802s Michichi Creek), 804s 701 (804s Wintering Hills) | 2023-04-19 09:00 | 2023-04-19 17:00 | N | N | 144 kV bus relay addition new 706CT input wiring | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 28s T1 (28s West Brooks) | 2023-04-19 09:00 | 2023-04-21 17:30 | N | Y | inspection and oil replacement | Transformer | LTC MR Diverter Oil Flush, Inspection, and Oil Replacement |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 720s 902 (720s Wabasca) | 2023-04-19 10:00 | 2023-04-20 16:00 | N | Y | commission control points to RTU | Circuit Breaker | Commission Control Points to RTU. Breaker 902 is the System Spare; 902B is Normally Open - no impact to the system. |  | 240 kV, Pre-Condition
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek), 20s 859E (20s Ghost), AML 793s 859W (AML 793s Horse Creek) | 2023-04-19 10:00 | 2023-04-19 14:00 | N | N | PRC 1st trip breaker testing and maintenance | Line, Circuit Breaker | PRC 1st Trip breaker testing and maintenance |  | Creates Radial Feeds, Firm Load Loss
ATCO | 848s 911 (848s Ruth Lake) | 2023-04-19 10:00 | 2023-04-19 13:00 | N | Y | PRC trip coil testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
TRANSALTA | 528s RTU/SCADA (528s Blue Trail Wind Farm) | 2023-04-19 12:00 | 2023-04-19 15:00 | N | N | turbine control software update | Terminal Equipment | TransAlta is requesting a communication outage at 528s Blue Trail April 19, 2023, from 1200 to 1500 for turbine control software update. During the outage there will be no control or monitoring of the turbines, the site will not be able to follow WPM. TransAlta will have control and monitoring of the substation. |  | Affects Visibility
ALTALINK | 702L (137s Sedgewick - 377s AML Hardisty), 377s 702W (377s AML Hardisty) | 2023-04-19 12:30 | 2023-04-19 17:30 | N | N | 1st trip and PRC5 maintenance on 377s702W | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ATCO | 848s 910 (848s Ruth Lake) | 2023-04-19 13:01 | 2023-04-19 16:00 | N | Y | PRC trip coil testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 854L (1012s Deer Hill - 854AL tap), 1012s 5 (1012s Deer Hill), 1012s 6 (1012s Deer Hill) | 2023-04-20 06:00 | 2023-04-25 18:00 | N | N | modify structures 161, 162, 167 and 168 from a H-frame tangent to a H-frame double dead-end due to clearance violation | Line, Switch | Arctic Arrow Requires a GOI on 854L to modify structures 161, 162, 167 & 168. Arctic will Modify the structure from a H-frame tangent to a H-frame Double dead-end due to clearance violation. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 35.2TR (SS-35) | 2023-04-20 08:00 | 2023-04-20 16:00 | N | N | replace oil temp RTD, oil sampling MT, TC, check reversing switch | Transformer | 35.2TR Replace Oil Temp RTD. Oil sampling MT, TC. Check reversing switch |  | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks), 678s 850 (678s Okotoks) | 2023-04-20 09:30 | 2023-04-20 16:00 | N | Y | PRC5 1st trip followed by maintenance | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 848s 606 (848s Ruth Lake) | 2023-04-20 10:00 | 2023-04-20 13:00 | N | N | PRC trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 22 (250p Bighorn Plant) | 2023-04-20 10:00 | 2023-04-20 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 848s 604 (848s Ruth Lake) | 2023-04-20 13:01 | 2023-04-20 16:00 | N | N | PRC trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 50L (44s Bearspaw Plant - SS-21) | 2023-04-21 07:00 | 2023-04-21 18:00 | N | Y | urgent repair - jumpers on structure 115 | Line |  |  | Pre-Condition
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2023-04-21 08:00 | 2023-04-21 17:30 | N | N | urgent - investigate and repair 5s 752 breaker | Shunts | 5s752 (C3) has locked out and the techs will need to take an outage to investigate/repair. |  | Pre-Condition
ENMAX | 2.84L (SS-2 - SS-8) | 2023-04-21 08:00 | 2023-04-21 19:00 | N | N | pump water out of manhole, take samples of MH2325 | Line |  | Returned early | For Information Only, Pre-Condition
ALTALINK, CLRS | 180L (15s Fort Macleod - 180AL tap), 180L (255s Vulcan - 928s East Stavely), 180L (928s East Stavely - 180AL tap), 180AL (604s Granum - 180L tap), 15s 180N (15s Fort Macleod), 255s 34 (255s Vulcan), 604s 152 (604s Granum), 604s T1 (604s Granum), 928s 180N (928s East Stavely), 928s 180X (928s East Stavely), 928s 197W (928s East Stavely) | 2023-04-21 08:01 | 2023-04-23 16:30 | N | Y | full commissioning and testing of new line relays at 15s and 255s on 180L, 15s B85/L5 (15s 180L teleprotection logic processor), and settings changes to 604s teleprotection relays | Line, Circuit Breaker, Transformer, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 848s 603 (848s Ruth Lake) | 2023-04-21 10:00 | 2023-04-21 13:00 | N | N | PRC trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 848s 607 (848s Ruth Lake) | 2023-04-21 13:01 | 2023-04-21 16:00 | N | N | PRC trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 72RG1 (Garneau - Rossdale), 72RV2 (EP 511s Victoria - Rossdale), 72 kV Bus 3 (Rossdale), RG7210 (Rossdale), RR729 (Rossdale), VHBB2 (Rossdale), RV728 (Rossdale), RR723 (Rossdale) | 2023-04-22 07:00 | 2023-04-22 17:00 | N | N | Rossdale: BUS 3 PT Doble | Line, Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31) | 2023-04-22 08:00 | 2023-04-23 16:00 | N | N | line clearance mitigation | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s J2405 (EP 805s Jasper), EP 805s JAB3 (EP 805s Jasper) | 2023-04-24 07:00 | 2023-04-28 17:00 | N | Y | tx3/CVT/arrestor doble and disconnect maintenance | Transformer, Circuit Breaker, Switch | Jasper: TX3/CVT/Arrestor Doble and JAB3/JDS9/JDS8/ Disconnect Maintenance | Returning a day early | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 665s T1 (665s Dome) | 2023-04-24 07:00 | 2023-04-26 17:00 | N | Y | surge arrestor LCR | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), EP 511s V721 (EP 511s Victoria), EP 511s V729 (EP 511s Victoria) | 2023-04-24 07:00 | 2023-04-24 17:00 | N | N | lighting upgrade spire #1 | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Meadowlark), M722 (Meadowlark), MAB1 (Meadowlark) | 2023-04-24 07:00 | 2023-05-02 17:00 | N | N | breaker maintenance, CT doble and P&C maintenance | Transformer, Circuit Breaker, Switch | Meadowlark: First Two Days Apparatus-M721 Breaker Maintenance and CT Doble, Last Four Days P&C- TX1 Zone Maintenance |  | For Information Only, Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), EP 805s J722 (EP 805s Jasper), M721 (Meadowlark) | 2023-04-24 07:00 | 2023-05-09 17:00 | N | N | JM18: P&C- line protection upgrade cut overs | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee), 330p 1208 (330p Genesee), 330p 1209 (330p Genesee) | 2023-04-24 07:00 | 2023-04-28 17:00 | N | Y | relay maintenance | Line, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 54.81L (SS-54 - SS-65), 65B138-D83 (SS-65), 65B138-D84 (SS-65), 54B138-54.81 (SS-54), 65MD138-54.81 (SS-65) | 2023-04-24 07:00 | 2023-04-28 16:00 | N | N | 65 sub cable trench replacement | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), H724 (EP Hardisty), 987s CH722 (987s Clover Bar) | 2023-04-24 07:00 | 2023-04-29 17:00 | N | N | breaker maintenance and P&C maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 511s SVC Plus (AML 511s Crossings) | 2023-04-24 08:00 | 2023-04-28 16:00 | N | Y | annual SVC plus inspection | Shunts | Annual SVC Plus inspection, VCS work, Fence repair |  | 240 kV, Pre-Condition
ATCO | 12L44 (939s Livock - 951s Thickwood Hills), 951s 1201T (951s Thickwood Hills), 951s 1201TA (951s Thickwood Hills), 951s 1205 (951s Thickwood Hills), 951s 1206 (951s Thickwood Hills), 951s 1201A (951s Thickwood Hills), 951s 1202TA (951s Thickwood Hills), 951s 1203B (951s Thickwood Hills), 951s 1204A (951s Thickwood Hills), 951s 1205A (951s Thickwood Hills), 951s 1205B (951s Thickwood Hills), 951s 1206A (951s Thickwood Hills), 951s 1206B (951s Thickwood Hills), 951s 1213A (951s Thickwood Hills), 951s 1213 (951s Thickwood Hills), 951s 12L44D1 (951s Thickwood Hills), 939s 1214 (939s Livock), 939s 1214A (939s Livock) | 2023-04-24 08:00 | 2023-04-27 17:30 | N | Y | breaker timing tests, PRC-005 trip coil tests and relay firmware upgrades | Line, Transformer, Switch, Circuit Breaker | Outage is contingent on external customer outage. PRC-005 trip coil tests & breaker timing tests on 1205, 1206, 1213. Relay firmware upgrades, password updates on multiple devices on site. |  | 500 kV, Pre-Condition
ENMAX | 5B138-5BT7 (SS-5) | 2023-04-24 08:00 | 2023-04-25 16:00 | N | N | power factor test 5B138-5BT7-2-CT, 5B138-5BT7-1-CT | Circuit Breaker | Power factor test 5B138-5BT7-2-CT, 5B138-5BT7-1-CT |  | Contingency Requires Mitigation
Syncrude | T4 (Aurora) | 2023-04-24 08:00 | 2023-06-12 20:00 | N | Y |  | Transformer | Significant Outage: G03 Substation 260/13.8KV 201-3-PTR260-4 Transformer Outage Following MOD's will be operated: 89-224 The Following Breakers will be operated: 52-221, 52-222 |  | Restricts Generation
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock), 510s 7689 (510s Sunnybrook), 939s 12L41D1 (939s Livock), 939s 1213A (939s Livock), 939s 1206 (939s Livock), 939s 1207 (939s Livock), 939s 1204A (939s Livock), 939s 1205B (939s Livock), 939s 1206A (939s Livock), 939s 1206B (939s Livock), 939s 1208A (939s Livock), 939s 1209B (939s Livock), 939s 1207B (939s Livock), 939s 1216 (939s Livock), 939s 1216A (939s Livock), 939s 1216R (939s Livock), 939s 1213R (939s Livock), 510s R3 (510s Sunnybrook) | 2023-04-24 08:00 | 2023-04-27 17:30 | N | Y | breaker timing tests, PRC-005 trip coil tests and relay firmware upgrades | Line, Switch, Circuit Breaker, Shunts | Outage is contingent on external customer outage. PRC-005 trip coil tests & breaker timing tests on 1206, 1207, 1214, & 1216. Relay firmware upgrades, password updates on multiple devices on site. |  | 500 kV, Pre-Condition
ENMAX | 12.2TR (SS-12) | 2023-04-24 08:00 | 2023-04-25 16:00 | N | N | tapchanger maintenance, oil sampling MT, TC, check reversing switch | Transformer | Tapchanger maintenance. Oil sampling MT, TC. Check reversing switch. |  | For Information Only
CODP | MCH1 Michichi Creek | 2023-04-24 08:00 | 2023-05-08 23:00 | N | N | P2248 ATCO Michichi Creek 802S DER Solar. ISD May 01, 2023. 14 MW | Unit
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (ENMAX 36), 36B69-16.63/36.5TR (SS-36), 16B69-16.63 (SS-16), SW61 (SS-36), SW66 (SS-16) | 2023-04-24 08:00 | 2023-04-28 16:00 | N | N | Replace 36sub 69kV PTs. | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson), 813s 701 (813s Little Smoky), 813s 702 (813s Little Smoky) | 2023-04-24 09:00 | 2023-05-01 10:00 | N | Y | 813S Little Smoky rebuild breaker 701 and 702 P&C wiring in panel 7P1 | Line, Circuit Breaker | 813S Little Smoky Rebuild BKR 701 and 702 P&C wiring in panel 7P1, prep work Demo panel 1G Relay programming and functionality Commission control, alarms and status |  | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 15s T2 (15s Fort Macleod) | 2023-04-24 10:30 | 2023-04-27 16:00 | N | N | inspection and diverted repair along with low oil top up | Transformer |  |  | For Information Only
ALTALINK | 778L (87s Gaetz - 217s North Red Deer), 217s 778E (217s North Red Deer) | 2023-04-24 10:45 | 2023-04-27 17:45 | N | N | 138kV breaker maintenance (217s778E), 138kV switch maintenance (217s12) | Line, Circuit Breaker | 138kV breaker maintenance (217s778E), 138kV switch maintenance (217s12) |  | Pre-Condition
ALTALINK | 74s T1 (74s Janet), 74s 16 (74s Janet) | 2023-04-24 12:00 | 2023-04-27 18:00 | N | Y | T1 maintenance, Doble, leak repairs, PRC5 work | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 338s T1 (338s Cherhill) | 2023-04-24 13:00 | 2023-04-27 17:00 | N | Y | transformer maintenance. | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 851L (253s Blackie - 525s Carseland) | 2023-04-25 06:15 | 2023-04-27 17:45 | N | Y | LCM - installing horizontal line posts on structures 184-186 and an arm extension on structure 182 | Line | LCM; installing Horizontal line posts on structures 184-186 and an Arm extension on structure 182 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | EP 511s Victoria T2 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), EP 511s V723 (EP 511s Victoria), EP 511s VAB2 (EP 511s Victoria) | 2023-04-25 07:00 | 2023-04-25 17:00 | N | N | lighting upgrade spire #2 | Transformer, Circuit Breaker, Switch | Victoria: Lighting Upgrade Spire #2 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 221s T1 (221s Sunken Lake), 221s 31 (221s Sunken Lake) | 2023-04-25 07:30 | 2023-04-28 16:00 | N | N | T1 tap changer maintenance and testing, 221s31 breaker maintenance | Transformer, Switch | T1 tap changer maintenance & testing. 221s31 breaker maintenance. |  | For Information Only
ALTALINK | 199s T2 (199s East Airdrie) | 2023-04-25 07:30 | 2023-04-26 17:30 | N | N | install bird cover | Transformer |  |  | For Information Only
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2023-04-25 08:00 | 2023-04-25 17:00 | N | Y | urgent repair - replace interphase spacer Str 173-174 | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | MH1 (Aurora - Aurora) | 2023-04-25 08:00 | 2023-04-30 20:00 | N | N | powerline outage | Line | Non-Significant Outage - MH1 72kV Powerline Outage: The following Circuit Breakers will be operated: 23 (G01 Substation) 24 (G01 Substation) The following MOD will be operated: 27 (G01Substation) Non-Significant Outage - MH1 72kV Powerline Outage: The following Circuit Breakers will be operated: 23 (G01 Substation) 24 (G01 Substation) The following MOD will be operated: 27 (G01Substation) |  | For Information Only
ALTALINK | 421s T1 (421s Hays) | 2023-04-25 08:00 | 2023-04-26 11:59 | N | N | upgrade and install bird cover on 25 kV Bus 2 (421s10, 421s12, 421s8, 421s5, VT1) | Transformer |  |  | For Information Only
ALTALINK | 308s Albchem Beaverhill Creek, 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s T1 (308s Albchem Beaverhill Creek), 308s 3 (308s Albchem Beaverhill Creek) | 2023-04-25 09:00 | 2023-04-27 16:30 | N | N | T1 - fix P5 leaks and oil temp gauge, top up oil, 308s776W fix gas leaks, 308s13 repair site glass | Station, Line, Transformer, Switch | T1: fix P5 leaks & oil temp gauge, top up oil, 308s776W fix gas leaks, 308s13 repair site glass |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 33s 3 (33s Spray) | 2023-04-25 09:00 | 2023-04-27 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 33s 6 (33s Spray) | 2023-04-25 09:00 | 2023-04-27 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 69s 240kV Bus (69s North Barrhead), 69s T4 (69s North Barrhead), 69s 713 (69s North Barrhead), 69s 913N (69s North Barrhead), 69s 42 (69s North Barrhead) | 2023-04-25 12:00 | 2023-04-25 17:00 | N | N | replace conductor from 69s42 - T4 and energize new 69sT4 | Bus, Transformer, Circuit Breaker, Switch | Replace conductor from 69s42 - T4 and energize new 69sT4. 69sT4 to soak overnight and will take load April 26th @ 10:00. RSLD 1 to be issued at the end of the outage. |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L65 (710s Vermilion - 7LA65 tap), 710s 703 (710s Vermilion) | 2023-04-25 17:01 | 2023-04-26 12:00 | N | Y | 7L65 rebuild project | Line, Circuit Breaker | 7L65 Rebuild Project. Will need total line outage from Apr. 18 07:00 - 12:00, 2023 - Isolation points 709S 7L65D1, 710S 703A, 7LA65D1 Apr. 18 12:01 - Apr. 30 17:30, 2023 shrink GOI - Isolation points 710S 703A and Jumper J2 Apr. 30 07:00 - 11:59 Phase in new portion of 7L65 that feeds east - After phasing is confirmed, close 7L65D3 and breaker 703 at 710S. - Need to remove flying taps off of west portion to 709S Apr. 30 12:00 - 17:30 - Isolation Points 709S 7L65D1, 7L65D2 |  | Overload, Pre-Condition, Restricts Generation
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria) | 2023-04-26 07:00 | 2023-04-26 17:00 | N | N | Victoria: lighting update | Line, Circuit Breaker | Victoria: Lighting Upgrade Spire #3 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2023-04-26 08:00 | 2023-04-26 16:00 | N | N | power factor test 5B138-2.82-CT | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ENMAX | 31.1TR (SS-31) | 2023-04-26 08:00 | 2023-04-27 16:00 | N | N | tapchanger maintenance, oil sampling MT, TC | Transformer |  |  | For Information Only
ATCO | 769s 704C (769s Stettler) | 2023-04-26 08:00 | 2023-08-18 17:00 | N | N |  | Shunts |  | Outage extended. | Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-04-26 10:00 | 2023-04-26 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 811s 701C (811s Clairmont Lake) | 2023-04-26 12:00 | 2023-06-30 17:00 | N | N |  | Shunts |  |  | For Information Only
ALTALINK | 421s T2 (421s Hays) | 2023-04-26 12:00 | 2023-05-01 17:30 | N | N | upgrade and install bird cover | Transformer |  | Upgrade and install bird cover on 25kV Bus 2 (421s37, 421s39, 421s38, 421s40, VT2) | Restricts Generation
EPCOR | EP 511s Victoria T4 (EP 511s Victoria), EP 511s V725 (EP 511s Victoria), EP 511s V726 (EP 511s Victoria) | 2023-04-27 07:00 | 2023-04-28 17:00 | N | N | upgrades and repair | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162B138-RB84 (SS-162) | 2023-04-27 08:00 | 2023-04-27 16:00 | N | N | breaker maintenance 162B138-RB84. breaker SF6 gas sample - | Circuit Breaker | HV breaker maintenance 162B138-RB84. HV breaker SF6 Gas Sample - 162B138-RB84. 162B138-RB84 Heaters not working - Investigate & Repair |  | Contingency Requires Mitigation
SUNCOR | 29PL7-5 (29EDD-18 Firebag - 29EDD-71), 29EDD-71 752-4613 (29EDD-71), 29EDD-71 752-4614 (29EDD-71) | 2023-04-27 08:00 | 2023-05-04 18:00 | N | N | breaker maintenance and testing | Line, Circuit Breaker | 29EDD71;29-752-4613 MAINT & TEST;PM 10y 29EDD71;29-752-4614 MAINT & TEST;PM 10y |  | For Information Only
ENMAX | 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5) | 2023-04-27 08:00 | 2023-04-27 16:00 | N | N | power factor test | Line, Circuit Breaker | Power factor test 5B138-2.83-CT |  | Pre-Condition
ALTALINK | 895s T3 (895s Suffield), 895s 952 (895s Suffield) | 2023-04-27 08:00 | 2023-04-27 17:00 | N | N | installing emergency protections | Transformer, Circuit Breaker | Permanently installing emergency protections |  | Restricts Generation
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 15s 463 (15s Fort Macleod) | 2023-04-27 08:00 | 2023-04-27 11:00 | N | Y | trip test from new 15s180N breaker fail | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 15s 452 (15s Fort Macleod) | 2023-04-27 11:01 | 2023-04-27 15:00 | N | N | trip test from new 15s180N breaker fail | Circuit Breaker | Trip test from new 15s180N breaker fail 2nd Scope: Commission Status of 15s452 to new Anti-Islanding-Scheme @ 349s14 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 711L (113s Inland Cement - 747L tap), 113s T1 (113s Inland Cement), 113s 711N (113s Inland Cement), 113s 5 (113s Inland Cement), 113s T2 (113s Inland Cement), 113s 1 (113s Inland Cement) | 2023-04-27 18:00 | 2023-04-28 | N | Y | emergency insulator repair | Line, Transformer, Circuit Breaker, Switch | 711L: Aerial: Emergency Insulator Repair (April 26th, 6pm to Mid-Night) |  | For Information Only
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2023-04-28 07:00 | 2023-04-28 18:00 | N | N | adding arm extension | Line |  | Adding an arm extension to the bottom phase on structures 2 & 12. | Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 14B138-14.83 (SS-14) | 2023-04-28 08:00 | 2023-04-28 16:00 | N | N | HV breaker maintenance 14B138-14.83 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-04-28 08:00 | 2023-05-28 18:00 | N | N | 30EDD-1 - 30PL2-48 system maintenance | Not In Model | 30EDD-1 30EDD-1;30PL2-48 SYSTEM;PM 5y |  | For Information Only
ALTALINK | AML 793s T2 (AML 793s Horse Creek) | 2023-04-29 11:30 | 2023-05-06 17:30 | N | N | doble, maintenance and leak mitigation | Transformer | 793sT2 Doble, TC Maintenance, leak mitigation, Assist with T2 Tap changer filter installation. |  | For Information Only
ALTALINK | AML 793s T1 (AML 793s Horse Creek) | 2023-04-29 11:30 | 2023-05-06 17:30 | N | N | replace 4.16kV bus insulators on X side of T1 transformer. | Transformer |  |  | For Information Only
ENMAXEC | 383s Kettles Hill Windfarm | 2023-05-01 07:00 | 2023-05-05 18:00 | N | Y | line maintenance on 616L (89s-59s  383s) | Station |  | #1. Asset: Kettles Hill wind farm Outage/Test: DVar PME #1 Outage Planned/Forced: Planned Timing: Tuesday June 7, 2022 8:00  18:00. AC: 0 MW or as provided in declaration #2. Asset: Kettles Hill wind farm Outage/Test: DVar PME #2 Outage Planned/Forced: Planned Timing: Tuesday June 7, 2022 8:00  18:00. AC: 0 MW or as provided in declaration Purpose: The outage is requested for equipment parts annual maintenance inspection/testing on voltage control units PME#1 and #2. Voltage site support will be reduced to 0% (0MVA dynamic support). | For Information Only, Restricts Generation
EPCOR | R721 (Rossdale) | 2023-05-01 07:00 | 2023-05-01 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-50L (MHS-2 North Industrial - MHS-5 NE Crescent Heights), MHS-2 MH69-212 (MHS-2 North Industrial), MHS-5 MH69-510 (MHS-5 NE Crescent Heights) | 2023-05-01 07:30 | 2023-06-14 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.1TR (SS-16) | 2023-05-01 08:00 | 2023-05-01 10:00 | N | N | SARM construction | Transformer | SARM Construction (16 Sub - DAP Server RTAC conv kit install - SCADA). |  | For Information Only
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 146s 823L (146s Macdonald), 593s 823L (593s Lakeview) | 2023-05-01 08:00 | 2023-05-11 14:00 | N | N | breaker replacement | Line, Circuit Breaker | LINE OUTAGE TO REPLACE 146S823L 138KV BREAKER |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
CMH | MHS-1 69kV South Bus (MHS-1 Power P Switchyard), MHS-1 MH69-42 (MHS-1 CMH Power Plant), MHS-1 MH69-T5 (MHS-1 CMH Power Plant), MHS-6 MH69-614 (MHS-6 CMH Riverview), MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview), MHS-1 MH69-10 (MHS-1 CMH Power Plant), MHS-1 MH69-21 (MHS-1 CMH Power Plant), MHS-1 MH69-31 (MHS-1 CMH Power Plant), MHS-1 MH69-38 (MHS-1 CMH Power Plant) | 2023-05-01 08:00 | 2023-05-11 08:30 | N | N | south bus outage | Bus, Circuit Breaker, Transformer, Line | Proposed South Bus (including Line 8L) outage is scheduled from May 2nd,2023 8.00 A.M until May 7th,2023, 8.30 A.M |  | For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33), 41B138-33.83 (SS-41) | 2023-05-01 08:00 | 2023-05-06 16:00 | N | N | ct replacement and sf6 gas sample | Line, Circuit Breaker | 41CT-33.83 Replacement. HV breaker SF6 Gas Sample - 33B138-33.83 | extended by ENMAX | Creates Radial Feeds, Firm Load Loss
ENMAX | 23.80L (74s Janet - SS-23), 23B138-23.80 (SS-23) | 2023-05-01 08:00 | 2023-05-10 16:00 | N | Y | pole relocation | Line, Circuit Breaker | Move 5 poles to expand 50 ave SE. TLR Construction (TLR - Great Plains Starfield Area 6 - 50 AV & 52 ST SE (east of 4948 52 ST SE) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 23.80L (74s Janet - SS-23). 23.4TR (SS-23), 23.80L (74s Janet - SS-23), 23MD138-23.4TR (SS-23) | 2023-05-01 08:00 | 2023-05-01 16:00 | N | Y | spring sub station washing | Terminal Equipment, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10), 10B138-693 (SS-10) | 2023-05-01 08:00 | 2023-05-01 12:00 | N | Y | sf6 gas sample | Line, Circuit Breaker | HV breaker SF6 Gas sample 10B138-693L |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 28.2TR (SS-28) | 2023-05-01 08:00 | 2023-05-02 16:00 | N | N | tap changer maintenence | Transformer | Tapchanger maintenance. Check reversing switch. Oil sampling MT, TC. Tap Changer Oil Filtration Maintenance - 28.2-TC |  | For Information Only
ATCO | 730s STATCOM (730s Rycroft) | 2023-05-01 08:30 | 2023-05-07 17:30 | N | Y | P1784 Addition of Voltage Support at Rycroft. ISD TBD (not before May 2023) | Shunts |  |  | Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2029s 1205 (2029s Heathfield), 2029s 1206 (2029s Heathfield), 2075s 916 (2075s Newell), 2075s 917 (2075s Newell) | 2023-05-01 09:00 | 2023-06-01 09:30 | N | Y |  | Line, Circuit Breaker | Note For OC: Check the availability of the substation ( 2075s Newell) for the use of SVS. Check if the SVS can be operated under reactive control mode. |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
BCH | 5L75 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2023-05-01 09:00 | 2023-05-05 17:00 | N | Y | replace end of life insulators BC maintenance does not affect the Alberta ATC | Line |  |  | 500 kV, Limits ATC
ENMAX | 16.2TR (SS-16) | 2023-05-01 10:00 | 2023-05-01 11:00 | N | N | SARM construction | Transformer | SARM Construction (16 Sub - DAP Server RTAC conv kit install - SCADA). |  | For Information Only
ATCO | 7L90 (813s Little Smoky - 7LA90 tap), 813s 702 (813s Little Smoky), 813s 703 (813s Little Smoky) | 2023-05-01 10:01 | 2023-05-31 12:59 | N | N |  | Line, Circuit Breaker | 813S Little Smoky Rebuild BKR 702 and 703 P&C wiring in panel 7P1, remove old panel 2G, prep work Relay programming and functionality Commission control, alarms and status |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L230 (69s North Barrhead - 888AL tap), 888AL (234s Fort Assiniboine - 7L230 tap), 7L230 (743s Sarah Lake - 888AL tap), 234s T1 (234s Fort Assiniboine), 234s T2 (234s Fort Assiniboine), 234s 888 (234s Fort Assiniboine), 234s 2 (234s Fort Assiniboine), 234s 3 (234s Fort Assiniboine) | 2023-05-01 11:00 | 2023-05-01 15:00 | N | Y | line mitigation work and open jumper J2 | Line, Transformer, Circuit Breaker, Switch |  |  | Over/Under Voltage, Overload, Pre-Condition
TRANSALTA | 1063s RTU/SCADA (1063s Windrise) | 2023-05-01 12:00 | 2023-05-01 15:00 | N | N | communication outage | Terminal Equipment | We were just informed of an internet outage at 1063s by our internet service provider on April 24, 2023, for 1 hour between the hours of 1200 and 1500. During this time, TransAlta will not have visibility of the turbines or the substation. AESO will have visibility and the WPM will still function normally. |  | For Information Only
ENMAX | 15.60L (SS-15 - SS-21), 21B69-15.60 (SS-21) | 2023-05-01 12:00 | 2023-05-01 16:00 | N | N | sf6 gas sample | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 867s T1 (867s Sundance Blow-Down), 521L (505L tap - 512L tap), 505L (234L tap - 505L tap), 521AL (867s Sundance Blow-Down - 521L tap) | 2023-05-01 12:00 | 2023-05-04 18:00 | N | N | fix T1 leaks, fix wooden structure, fix 72kV structure, repair guy wire | Transformer, Line | fix T1 leaks, fix wooden structure, fix 72kV structure, repair guy wire |  | For Information Only
ALTALINK | 305s T1 (305s Acheson) | 2023-05-01 12:00 | 2023-05-04 18:00 | N | N | fix leaks, maintain, doble | Transformer | T1: fix leaks, maintain, doble |  | For Information Only
ATCO | 7L33 (749s Flyingshot Lake - 7LA33 tap) | 2023-05-01 12:00 | 2023-05-03 16:00 | N | Y | replace damaged RTXP switches for 7L33 relays | Line | Replace Damaged RTXP switches for 7L33 relays |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 64s T1 (64s East Crossfield) | 2023-05-01 12:30 | 2023-05-09 17:30 | N | N | refurbish transformer and repair leaks | Transformer | Refurbish TX and repair leaks | Back early | For Information Only
ALTALINK | 320p 2952 (320p Keephills), 320p 3052 (320p Keephills), 320P 2989A (320p Keephills), 320P 3089A (320p Keephills) | 2023-05-01 12:30 | 2023-05-01 16:30 | N | Y | PRC-005 testing to breakers | Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation
ATCO | 813s SVC (813s Little Smoky) | 2023-05-01 12:40 | 2023-05-07 18:00 | N | Y | forced outage to repair glycol leak | Shunts | While filling Glycol several other leaks have been found that will the convertor to remain off line until they can be repaired. 813S SVC Forced outage to repair Glycol Leak |  | Pre-Condition
Saskpower | SaskPower C1S | 2023-05-01 13:00 | 2023-05-12 18:00 | N | Y | SPC maintenance | Line | Line(s) Out of Service During Outage or Part of Outage C1S Line, PRPS 1 Unit, PRPS 2 Unit, CWPPS Wind, BHWPS WIND, GSWPS Wind |  | Limits ATC
ATCO | 7L230 (743s Sarah Lake - 888AL tap) | 2023-05-01 15:01 | 2023-05-03 16:31 | N | Y | line mitigation work | Line | Line Mitigation Work 2023-04-24 12:00 to 14:00 - complete 7L230 outage, 234S Ft. Assiniboine will be without power Isolation points: 743S 7L230D1, 69s16 at 69S Barrhead and 234s1 at 234S Ft. Assiniboine ATCO to Open Jumper 7L230 J1 2023-04-24 14:00 to 2023-04-28 12:00 ATCO GOI on 7L230 Isolation points: 743S 7L230D1, 7L230 J1 2023-04-28 12:00-14:00 - complete l7L230 outage, 234S Ft. Assiniboine will be without power Isolation points: 743S 7L230D1, 69s16 at 69S Barrhead and 234s1 at 234S Ft. Assiniboine ATCO to Close Jumper 7L230 J1 7L230 restored to normal. |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 17s C1 (17s Benalto), 17s 16 (17s Benalto) | 2023-05-02 08:00 | 2023-05-03 17:30 | N | Y | repair closing dashpots | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 36B138-14.83 (SS-36) | 2023-05-02 08:00 | 2023-05-02 16:00 | N | N | breaker maintenance 36B138-14.83 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 262s 870W (262s Rocky Mountain House), 870L (262s Rocky Mountain House - 263s Strachan) | 2023-05-02 08:30 | 2023-05-02 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L89 (721s La Corey - 826s Marguerite Lake), 700s 703 (700s Bonnyville) | 2023-05-02 09:00 | 2023-05-03 16:00 | N | Y | 700S 703 maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L20 (740s H.R. Milner - 810s Dome Cutbank) | 2023-05-02 10:00 | 2023-05-04 16:00 | N | Y | line mitigation | Line | Line Mitigation |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO, ALBIAN | 920s 902T (920s Jackpine) | 2023-05-02 10:00 | 2023-05-04 17:30 | N | Y | leak mitigation on 902T | Transformer |  |  | 240 kV
AESO-SC | OATI | 2023-05-02 18:00 | 2023-05-02 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
ATCO | 7L81 (791s Rainbow Lake - BCH Harvest Energy FNC Tap) | 2023-05-03 05:25 | 2023-10-21 12:00 | N | Y |  | Line |  | Broken Structure  Emergency Repairs | For Information Only, Restricts Generation, Affects Cranking Path
ENMAX | 24.82L (SS-24 - SS-65), 65B138-D82 (SS-65), 65B138-D81 (SS-65), 24B138-24.82 (SS-24) | 2023-05-03 07:00 | 2023-05-11 16:00 | N | N | 65 sub cable trench replacement | Line, Circuit Breaker |  |  | Pre-Condition
VISIONREQ | 354s RTU/SCADA (354s Summerview) | 2023-05-03 07:00 | 2023-05-03 15:00 | N | N | network updates on Summerview 1 | Terminal Equipment |  |  | Affects Visibility
TRANSALTA | 1045s RTU/SCADA (1045s Garden Plain) | 2023-05-03 08:00 | 2023-05-03 16:00 | N | N | network equipment updates for GDP1 | Terminal Equipment |  |  | Affects Visibility
ATCO, ALTALINK | 7L114 (72s Leismer - 7LA114 tap) | 2023-05-03 08:00 | 2023-05-03 17:00 | N | N | customer communication test | Line | The customer at 658s Chard requested AltaLink to block 85-2/L8, B21/79/L8, & A21/L8 protections at 72s to facilitate comm trips from their site. A and B protections will be taken out of service one at a time. |  | For Information Only
ENMAX | 38.3TR (SS-38) | 2023-05-03 08:00 | 2023-05-04 16:00 | N | N | tapchanger maintenance | Transformer | Tapchanger maintenance. Check reversing switch. Oil sampling MT, TC. Tap Changer Oil Filtration Maintenance - 38.3-TC |  | For Information Only
ENMAX | 21.61L (SS-21 - SS-34), 34B69-21.61 (SS-34) | 2023-05-03 08:00 | 2023-05-03 16:00 | N | N | HV breaker maintenance 21B69-21.61. SF6 Gas Sample - 21B69-21.61 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 4R T1 (A.T. Plastics 4R), 5R T3 (A.T. Plastics 5Rs), ATP1381 (A.T. Plastics 4Rs), ATPAB1 (A.T. Plastics 4Rs), ATPAB2 (A.T. Plastics 4Rs) | 2023-05-04 07:00 | 2023-05-04 17:00 | N | N | R TX1 leak investigation and cleanin, ATPAB3 disconnect repair | Transformer, Circuit Breaker, Switch | AT Plastics: 4R TX1 Leak Investigation and Cleaning. ATPAB3 Disconnect Repair 4R (TX1) & 5R (TX3) @ AT Plastics E224S |  | For Information Only
ATCO | 700s 703T (700s Bonnyville), 700s 709 (700s Bonnyville) | 2023-05-04 09:00 | 2023-05-04 16:00 | N | N | 703T leak mitigation | Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 7L31 (732s Mitsue - 844s AEC MILL) | 2023-05-04 09:00 | 2023-05-04 16:00 | N | N | urgent - change broken crossarm at structure # 3 | Line | Emergency Outage to change broken Crossarm at structure # 3 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 240kV West Bus (SS-25), 1080L (SS-25 - SS-65), 25B240-D133 (SS-25), 25B240-D136 (SS-25), 25B240-D138 (SS-25), 25B240-D139 (SS-25), 25B240-D142 (SS-25), 25MD240-1080 (SS-25) | 2023-05-04 09:46 | 2023-05-08 10:00 | N | Y | expansion of GOI zone for urgent work to replace 1080L cables into C25s for scaffolding for cable terminations | Bus, Line, Circuit Breaker, Switch | Expansion of GOI Zone for Urgent work to replace 1080L cables into C25s for scaffolding for cable terminations |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 844L (358s Amoco Brazeau - 477s Amoco West Pembina), 477s 844X (477s Amoco West Pembina), 801L (294s Brazeau Outlet Works - 801AL tap), 801L (358s Amoco Brazeau - 801AL tap), 801AL (445s Elk River - 801L tap), 445s 801X (445s Elk River) | 2023-05-04 17:00 | 2023-06-04 16:36 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 156L (235s Entwistle - 156BL tap) | 2023-05-04 17:00 | 2023-05-12 09:00 | N | N | forced outage due to fire | Line | 744L (207s Pinedale - 228s T.M.P.L.Niton) |  | For Information Only
ALTALINK | 835L (283s Violet Grove - 835AL tap), 283s 835E (283s Violet Grove) | 2023-05-04 17:00 | 2023-05-23 13:00 | N | N |  | Line, Circuit Breaker |  | Outage complete | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2023-05-04 17:00 | 2023-05-05 14:00 | N | N | forced outage due to fire | Line |  |  | For Information Only
ALTALINK | 744L (207s Pinedale - 228s T.M.P.L. Niton) | 2023-05-04 17:00 | 2023-05-17 18:00 | N | N |  | Line | 744L (207s Pinedale - 228s T.M.P.L.Niton) |  | For Information Only
ATCO | 930s SVC (930s Arcenciel) | 2023-05-04 17:00 | 2023-05-07 21:22 | N | Y | forced outage due to fire | Shunts |  | Back in service early. | For Information Only, Pre-Condition
ALTALINK | 841L (477s Amoco West Pembina - 489s Petro-Canada Brazeau River) | 2023-05-04 17:00 | 2023-06-20 18:00 | N | N |  | Line |  |  | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel), 930s 702T (930s Arcenciel), 930s 719 (930s Arcenciel), 930s 406 (930s Arcenciel), 930s 407 (930s Arcenciel) | 2023-05-04 17:00 | 2023-06-08 11:12 | N | Y |  | Shunts, Transformer, Circuit Breaker |  | Back early | For Information Only, Pre-Condition
ALTALINK | 828L (178s Cynthia - 489s Petro-Canada Brazeau River), 178s 828X (178s Cynthia), 489s 828E (489s Petro-Canada Brazeau River) | 2023-05-04 17:00 | 2023-05-27 18:00 | N | N |  | Line, Circuit Breaker, Switch |  | Returned early | For Information Only
ATCO | 7L61 (780s Lubicon - 796s Nipisi) | 2023-05-05 08:00 | 2023-05-19 09:00 | N | N |  | Line | 7L61 (780s Lubicon - 796s Nipisi) | Breaker 701 maintenance | For Information Only
ATCO, ALTALINK | 7L230 (69s North Barrhead - 888AL tap), 888AL (234s Fort Assiniboine - 7L230 tap), 7L230 (743s Sarah Lake - 888AL tap), 234s T1 (234s Fort Assiniboine), 234s T2 (234s Fort Assiniboine), 234s 888 (234s Fort Assiniboine), 234s 2 (234s Fort Assiniboine), 234s 3 (234s Fort Assiniboine) | 2023-05-05 11:00 | 2023-05-05 15:00 | N | Y | line mitigation work and close jumper J2 | Line, Transformer, Circuit Breaker, Switch |  |  | Over/Under Voltage, Overload, Pre-Condition
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6), 41B138-6.82 (SS-41) | 2023-05-06 08:00 | 2023-05-06 16:00 | N | N | setting distribution pole underneath 6.82L, HV breaker SF6 gas sample - 6B138-6.82, SW 88 at 6 sub - status contact linkage broken, HV breaker power factor test 41B138-6.82 | Line, Circuit Breaker | Setting distribution pole underneath 6.82L. HV breaker SF6 Gas Sample - 6B138-6.82. SW 88 at 6 sub - status contact linkage broken. HV breaker power factor test 41B138-6.82 |  | Creates Radial Feeds, For Information Only
Lethbridge | 813L (146s MacDonald - 241s Uplands), 146s 813L (146s Macdonald), 241s 813L (241s Uplands) | 2023-05-06 08:00 | 2023-05-06 17:00 | N | N | install new protections, test/trip 146s 813L breaker | Line, Circuit Breaker | OPEN END TO INSTALL NEW PROTECTIONS ,TEST/TRIP 146S813L BREAKER |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake), 730s 704 (730s Rycroft), 811s 707 (811s Clairmont Lake) | 2023-05-06 09:00 | 2023-05-06 10:00 | N | N | testing 730S SVS reaction to loss of 7L68, remove 7L68PT2 as part of SVS addition project | Line, Circuit Breaker | Testing 730S SVS reaction to loss of 7L68 Remove 7L68PT2 as part of SVS addition project |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L75 (ATC 793s West Peace River - 800s Friedenstal), 800s 701 (800s Friedenstal), ATC 793s 702 (ATC 793s West Peace River) | 2023-05-06 10:01 | 2023-05-06 11:00 | N | Y | testing 730S SVS reaction to loss of 7L75 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, CascadeP | 1084L (39s Bickerdike - 1047s Whisky Jack), 1047s GD006 (1047s Whisky Jack) | 2023-05-06 14:00 | 2023-05-26 10:33 | N | Y |  | Line, Switch |  |  | 240 kV, For Information Only
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Whisky Jack), 1047s GD003 (1047s Whisky Jack) | 2023-05-06 14:00 | 2023-05-11 10:00 | N | Y | forced outage due to fire | Line, Switch |  |  | 240 kV, For Information Only
ALTALINK, CascadeP | 1168L (39s Bickerdike - 1047s Whisky Jack), 1047s GD015 (1047s Whisky Jack) | 2023-05-06 14:00 | 2023-05-11 10:00 | N | Y | forced outage due to fire | Line, Switch |  |  | 240 kV, For Information Only
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 146s 667 (146s Macdonald), 370s 667 (370s North Lethbridge) | 2023-05-07 08:00 | 2023-05-07 16:00 | N | Y | install new protections, test/trip 146s 667L breaker | Line, Circuit Breaker | OPEN END TO INSTALL NEW PROTECTIONS ,TEST/TRIP 146S667L BREAKER | Finished early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L99 (801s Anderson - 807s Sheerness), 807s 901T (807s Sheerness), 807S 901A (807s Sheerness), 807S 901B (807s Sheerness), 807S 904TD (807s Sheerness) | 2023-05-07 10:00 | 2023-05-25 10:00 | N | Y | maintenance work | Line, Transformer, Switch | Heartland Request to have 9L99 OOS for their work |  | 240 kV, Restricts Generation, Affects Cranking Path
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 72KN23 (Kennedale - Namao), K724 (Kennedale), K723 (Kennedale), KDS6 (Kennedale) | 2023-05-08 07:00 | 2023-05-12 17:00 | N | N | CT/CVT/arrestor doble and KDS7/KDS6/KDS8 disconnect maintenance | Line, Circuit Breaker, Switch |  | Kennedale: KN23 Zone CT/CVT/Arrestor Doble and KDS7/KDS6/KDS8 Disconnect Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2023-05-08 07:00 | 2023-05-12 17:00 | N | Y | doble | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 557s T1 (557s Castle Downs) | 2023-05-08 07:00 | 2023-05-08 17:00 | N | Y | measurements for engineering | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 28.2TR (SS-28) | 2023-05-08 08:00 | 2023-05-11 16:00 | N | N | transformer maintenance and testing | Transformer | Power factor test transformer. Secondary Cable Test. Transformer Maintenance. Relay Fault Pressure Test . Check reversing switch. Oil sampling MT, TC. |  | For Information Only
ATCO | 930s 717C (930s Arcenciel) | 2023-05-08 08:00 | 2023-05-24 18:00 | N | N |  | Shunts
ENMAX | 11.82L (SS-11 - SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14) | 2023-05-08 08:00 | 2023-05-08 16:00 | N | N | breaker SF6 gas sample | Line, Circuit Breaker | HV breaker SF6 Gas Sample |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib), 718s 702 (718s Parsons Creek) | 2023-05-08 08:00 | 2023-06-02 17:00 | N | N | replace switches and switch structures | Line, Circuit Breaker | Replace 718S 7L71D4 & 718S 702A switches and switch structures |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 12.1TR (SS-12) | 2023-05-08 08:00 | 2023-05-08 16:00 | N | N | transformer oil leak | Transformer | 12.1TR oil leak on gas relay piping between valve and relay |  | For Information Only
ALTALINK | 1080L (SS-25 - SS-65) | 2023-05-08 10:01 | 2023-05-23 08:00 | N | Y | urgent work to replace 1080L cables into C25s | Line |  | Reducing of GOI Zone for Urgent work to replace 1080L cables into C25s. 1080L OOS during real time failure | 240 kV, For Information Only
ALTALINK | 157s T1 (157s Lac La Biche) | 2023-05-08 12:00 | 2023-05-12 18:00 | N | N | T1 leaks, test, upgrade bird cover on bushings, fix IDD cable | Transformer |  |  | For Information Only
ALTALINK | 310p 1252 (310p Sundance) | 2023-05-08 12:30 | 2023-05-11 17:30 | N | Y | maintenance on 310p1252 including 1st trips | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation,
ATCO | 9L32 (838s Horizon Mining - 941s Bitumount), 9L66 (838s Horizon Mining - 847s Muskeg River) | 2023-05-08 18:01 | 2023-05-31 17:00 | N | Y | stage 3 for 9L66/9L32 reconnection | Line |  |  | 240 kV, Impacts RAS, Pre-Condition
ATCOP, CNRL | 838s 75-TR-2801 (838s Horizon Mining) | 2023-05-09 07:30 | 2023-05-16 07:29 | N | Y | 260kV 5YR PM | Transformer |  |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 301s T1 (301s Queensland), 301s 152 (301s Queensland) | 2023-05-09 07:30 | 2023-05-09 17:30 | N | N | maintain and test T1, calibrate tap indication | Transformer, Circuit Breaker |  |  | For Information Only
TRANSALTA | 1063s Windrise | 2023-05-09 08:00 | 2023-05-09 13:00 | N | N | repair lightning masts | Station | oil leaks on T1 |  | Restricts Generation
ENMAX | 13.1TR (SS-13) | 2023-05-09 08:00 | 2023-05-09 16:00 | N | N | investigate 13.1TR for the tapchanger replacement project | Transformer |  |  | For Information Only
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20), 8A9 (SS-1) | 2023-05-09 08:00 | 2023-05-09 12:00 | N | N | breaker SF6 gas sample - 20B138-1.81 | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
COSP | STV1 Stavely Solar | 2023-05-09 08:00 | 2023-07-21 22:00 | N | N |  | Unit
ALTALINK | 100L (498s Tilley - 895s Suffield), 895s 100 (895s Suffield), 498s 100X (498s Tilley) | 2023-05-09 09:30 | 2023-05-10 10:40 | N | Y | 895s100 gas analyze and top up | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK, TRANSALTA | 20s 138kV South Bus (20s Ghost), 113L (20s Ghost - 33s Spray), 150L (20s Ghost - 150AL tap), 859L (20s Ghost - AML 793s Horse Creek), 20s T1 (20s Ghost) | 2023-05-09 10:00 | 2023-05-09 16:00 | N | Y | complete wiring changes in CVT1 heads and JBCVT1 | Bus, Line, Transformer | 138kv South Bus outage to complete wiring changes in CVT1 heads and JBCVT1. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 20.82L (SS-20 - SS-21), 20B138-20.82 (SS-20), 21B138-20.82 (SS-21) | 2023-05-09 12:01 | 2023-05-09 16:00 | N | N | breaker SF6 gas sample - 20B138-20.82 | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L77 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2023-05-09 21:00 | 2023-05-12 17:00 | N | Y | replace end of life insulators | Line |  |  | Limits ATC, 500 kV
EPCOR | T2 (Meadowlark), M722 (Meadowlark), M723 (Meadowlark), MAB2 (Meadowlark) | 2023-05-10 07:00 | 2023-05-12 17:00 | N | N | breaker maintenence | Transformer, Circuit Breaker, Switch | Meadowlark: First Week Apparatus M722 Breaker Maintenance and Denimeter Repair and CT Doble, Second Week Apparatus CVT LCR and P&C TX2 Maintenance |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T3 (EP 511s Victoria) | 2023-05-10 07:00 | 2023-05-11 17:00 | N | N | emergency rap changer investigation | Transformer | Victoria: TX3 Emergency Tap changer Investigation |  | For Information Only
ENMAX | 41B138-41BT3 (SS-41) | 2023-05-10 08:00 | 2023-05-10 16:00 | N | N | breaker maintenance and SF6 gas sample | Circuit Breaker | HV breaker maintenance 41B138-BT3. SF6 Gas Sample - 41B138-BT3 |  | For Information Only
ALTALINK | 20s 138kV North Bus (20s Ghost), 56L (20s Ghost - 245s Seebe), 418L (20s Ghost - 189L tap), 20s T5 (20s Ghost) | 2023-05-10 09:00 | 2023-05-10 15:00 | N | N | 138kv north bus outage to complete wiring changes | Bus, Line, Transformer | 138kv North Bus outage to complete wiring changes in VT2 heads and JBVT2 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 9L933 (132s Ware Junction - 801s Anderson), 801s 907 (801s Anderson), 801s 908 (801s Anderson), 801S 908B (801s Anderson), 801S 907B (801s Anderson), 132s 933 (132s Ware Junction) | 2023-05-10 10:00 | 2023-05-10 17:30 | N | Y | operate 907 and 908 breakers to investigate multiple spring charge failures on 908 | Line, Circuit Breaker, Switch | Operate 907 & 908 breakers to investigate multiple spring charge failures on 908 |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 185s 152 (185s Bretville) | 2023-05-10 10:30 | 2023-05-10 15:30 | N | N | top up 185s152 breaker with SF6 | Circuit Breaker | URGENT Top up 185s152 breaker with SF6 |  | Creates Radial Feeds, Firm Load Loss
ATCO | 839s RTU/SCADA (839s Daishowa) | 2023-05-11 06:00 | 2023-05-13 18:00 | N | N | upgrade of our power supply for internal SCADA equipment | Terminal Equipment | Mercer Peace River Ltd(Asset DAI1) would like to inform you that there will be a SCADA outage on Thursday May 11,2023 from 600 hr to Saturday May 13,2023 1800 hr.This is due to upgrade of our power supply for internal SCADA equipment.Also during that time our Generators would be down for yearly shutdown maintenance. |  | For Information Only
ALTALINK | 221s T2 (221s Sunken Lake) | 2023-05-11 07:30 | 2023-05-11 18:00 | N | N | NGR replacement | Transformer | 221s T2 NGR replacement (Enbridge) |  | For Information Only
ALTALINK | 301s T1 (301s Queensland), 301s 152 (301s Queensland) | 2023-05-11 07:30 | 2023-05-11 17:30 | N | N | maintain and test T1, calibrate tap indication | Transformer, Circuit Breaker | Maintain and test T1, calibrate tap indication. 301s will be offline for the duration of the outage. |  | For Information Only
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 746s 700N (746s Sherwood Park) | 2023-05-11 08:00 | 2023-05-11 13:00 | N | N | urgent repair of hotspot on 746s30 | Line, Circuit Breaker | Replace stub pole and install new ground rod at structure 30. |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.80L (SS-9 - SS-31), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31) | 2023-05-11 08:00 | 2023-05-11 16:00 | N | N | HV breaker maintenance 31B138-9.80 | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 38.2TR (SS-38) | 2023-05-11 08:00 | 2023-05-11 12:00 | N | N | recording measurements in secondary cell | Transformer | Design consultant taking measurements in secondary cell. |  | For Information Only
ENMAX | 11.83L (SS-162 - SS-11), 11B138-11.83 (SS-11), 162MD138-11.83 (SS-162) | 2023-05-11 08:00 | 2023-05-11 16:00 | N | N | HV breaker maintenance 11B138-11.83 | Line, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 38.3TR (SS-38) | 2023-05-11 12:00 | 2023-05-11 16:00 | N | N | recording measurements in secondary cell | Transformer | Design consultant taking measurements in secondary cell. |  | For Information Only
ALTALINK | 54s 138kV West Bus (54s Fort Saskatchewan), 694L (54s Fort Saskatchewan - 422s Westwood), 706L (54s Fort Saskatchewan - 706AL tap), 54s C1 (54s Fort Saskatchewan), 54s T1 (54s Fort Saskatchewan), 54s 35 (54s Fort Saskatchewan), 422s 694 (422s Westwood) | 2023-05-11 13:01 | 2023-05-11 15:45 | N | N | urgent - hotspot repair | Bus, Line, Shunts, Transformer, Switch, Circuit Breaker |  | Install and commission additional 138kV bus protection on West Bus, install slip on bushing CTs on T1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
DAISHOWA | 147s RTU/SCADA (147s Daishowa Plant) | 2023-05-12 06:00 | 2023-05-13 18:00 | N | N | upgrade of power supply for internal SCADA equipment | Terminal Equipment | Mercer Peace River Ltd(Asset DAI1) would like to inform you the updated time of SCADA outage.The duration would be from Friday 12th May 600hr,2023 to Saturday May 13,2023 1800 hr.This is due to upgrade of our power supply for internal SCADA equipment.If you have any question please reach out to myself or Tom Riendeau at 780-618-6983. Our generators would be down during that time mentioned.The asset DAI1 would be importing power.There would be no visibility. |  | Affects Visibility
ENMAX | 65B138-D85 (SS-65) | 2023-05-12 07:00 | 2023-05-13 16:00 | N | N | 65 sub cable trench replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
EPCOR | EP 511s Victoria T2 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), EP 511s V723 (EP 511s Victoria), EP 511s VAB2 (EP 511s Victoria) | 2023-05-12 07:00 | 2023-05-13 17:00 | N | N | lighting upgrade spire #2 | Transformer, Circuit Breaker, Switch | Victoria: Lighting Upgrade Spire #2 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RG7 (Garneau - Rossdale) | 2023-05-12 18:00 | 2023-05-14 06:59 | N | N |  | Line |  |  | For Information Only
PANC, NEXENI | PCES02L (391s Balzac - Balzac Power Station), 52-211 (Balzac Power Station), 89-213BP (Balzac Power Station) | 2023-05-12 20:00 | 2023-05-14 17:00 | N | Y | transformer HV bushing replacement | Line, Circuit Breaker, Switch | 391s23 (PCES02L) customer Advice |  | Restricts Generation
ENMAX | 6.82L (SS-6 - SS-41) | 2023-05-13 08:00 | 2023-05-13 16:00 | N | N | setting distribution pole underneath 6.82L | Line |  |  | Creates Radial Feeds, Firm Load Loss, For Information Only
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2023-05-13 08:00 | 2023-06-09 18:00 | N | Y |  | Line |  |  | For Information Only
EPCOR | 557s CD2405 (557s Castle Downs) | 2023-05-14 07:00 | 2023-05-17 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, For Information Only, Over/Under Voltage, Pre-Condition
EPCOR | 72RW3 (Rossdale - Woodcroft), 72RV4 (EP 511s Victoria - Rossdale), 72RG7 (Garneau - Rossdale), VHBB1 (Rossdale), VHBB2 (Rossdale), RW727 (Rossdale), RV726 (Rossdale), RG725 (Rossdale) | 2023-05-14 07:00 | 2023-05-17 17:00 | N | N |  | Line, Circuit Breaker |  |  | Overload
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2023-05-14 10:00 | 2023-06-09 07:59 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, ENMAX | 1106L (237s Foothills - SS-65), 65B240-D130 (SS-65), 65B240-D131 (SS-65), 65MD240-1106 (SS-65) | 2023-05-15 07:00 | 2023-05-19 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2023-05-15 08:00 | 2023-05-19 18:00 | N | N |  | Line, Circuit Breaker |  | Oil sampling, Sheath testing. Power factor testing. Power Factor Test LA's and Potheads | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12B138-833L (SS-12) | 2023-05-15 08:00 | 2023-05-16 16:00 | N | Y | breaker maintenence | Line, Circuit Breaker | HV breaker maintenance 12B138-833L. |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
SUNCOR | 29EDD-94 29-952-9704 (29EDD-94 Voyageur), 29EDD-94 29-952-9705 (29EDD-94 Voyageur), 29EDD-94 29PS-400 (29EDD-94 Voyageur) | 2023-05-15 08:00 | 2023-05-30 18:00 | N | N | breaker mtce & test | Circuit Breaker, Switch | 29EDD94; Breaker MTCE & TEST, PM 10y on breakers, 29-452-8302, 29-452-8303, 29-452-8304, 29-452-8502, 29-452-8503,29-452-8504, 29-452-8505, 29-452-8506, 29-452-8507; 29PT-407, corrective work on 29PL4-244 |  | For Information Only
ALTALINK, CHDI | 863L (225s Magrath - 891L tap), 863L (618s Riverbend - 891L tap), 891L (226s Garden City - 863L tap), 225s T1 (225s Magrath), 618s 863X (618s Riverbend), 225s 4 (225s Magrath), 225s 863 (225s Magrath), Taylor Hydro Plant | 2023-05-15 08:00 | 2023-05-19 18:00 | N | Y | breaker maintenence | Line, Transformer, Circuit Breaker, Switch, Station | 618s863X CT replacement, 618s863X breaker maintenance, 225s863N circuit switcher maintenance, 225s2 switch maintenance, 863L protection upgrade, MPLS node upgrades (225s, 226s, 618s), PMU salvage @ 226s, 225s T1  tap-changer through neutral, 225s T1  Doble test, 225s T1  tap-changer maintenance, 225s T1  rad leak, 225s T1  fall arrest plates, 225s T1  oil leaks and 225s4 breaker maintenance |  | Impacts RAS, Pre-Condition, Restricts Generation
ENMAX | 2.1TR (SS-2) | 2023-05-15 08:00 | 2023-05-16 16:00 | N | N | 2.1TR oil level issue - install drip barrel | Transformer |  |  | For Information Only
ENMAX | 27.1TR (SS-27) | 2023-05-15 08:00 | 2023-05-15 16:00 | N | N | 27.1TR T-60 replace internal battery | Transformer |  |  | For Information Only
EHN | 226s Garden City | 2023-05-15 08:00 | 2023-05-15 18:00 | N | N | PMU cabinet removal, wiring from HV CTs and 20x pad mount transformer oil samplings | Station |  |  | For Information Only
ATCO | 6L12 (774s Monitor - 6L25 tap) | 2023-05-15 08:30 | 2023-05-18 15:00 | N | N | Climbing inspection / repair deficiency on 6L12 | Line |  |  | Creates Radial Feeds, Firm Load Loss, For Information Only
ATCO | 9L08 (849s Joslyn Creek - 888s Dover), 849s 905 (849s Joslyn Creek), 849s 906 (849s Joslyn Creek) | 2023-05-15 09:30 | 2023-05-28 17:00 | N | Y | 849s 9L08 protection upgrades | Line, Circuit Breaker |  | 849s 9L08 Protection upgrades, update existing 9L08 wiring and outputs to incorporate new DFR and new 900BS2 panels. Station service will be back fed through breaker 502 refer to permit 2-70530. demo and replace the 9L32 protection not 75-PLH-902. New 900BS2 panel will not be added | 240 kV, Pre-Condition
ATCO | 848s 608 (848s Ruth Lake) | 2023-05-15 10:00 | 2023-05-15 13:00 | N | N | prc trip coil testing | Circuit Breaker | PRC Trip Coil Testing
ALTALINK | 221s C1 (221s Sunken Lake) | 2023-05-15 13:30 | 2023-05-19 15:30 | N | N | urgent repair project | Shunts |  | Urgent repair project to upgrade failed A50/51/27/59/60/C1 C1 cap bank A protection. | Pre-Condition
ALTALINK | 44s T1 (44s Bearspaw Plant) | 2023-05-16 07:00 | 2023-05-18 17:00 | N | N | installation of lightning arrestors | Transformer | 44s T1 & VR1 (25kV Bus) : Installation of Lightning arresters on the high side of T1. Installation of Bird cover in the 25kv Bay area, including but not limited to VR1. |  | For Information Only
ATCOP, CNRL | 838s 75-TR-2801 (838s Horizon Mining), 838s 75-TR-1701 (838s Horizon Mining) | 2023-05-16 07:30 | 2023-05-26 18:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only, Pre-Condition
ATCO | 7L183 (2060s Engstrom - 7LA183 tap) | 2023-05-16 08:00 | 2023-05-19 10:00 | N | N |  | Line | 7L61 (780s Lubicon - 796s Nipisi) | Breaker 701 maintenance | For Information Only
ALTALINK | 38s T3 (38s East Edmonton) | 2023-05-16 08:00 | 2023-05-17 18:00 | N | N | tap changer maintenance, testing, fix gauge, replace LA bases | Transformer |  |  | For Information Only
ATCO | 7L133 (786s High Level - 828s Sulphur Point) | 2023-05-16 08:00 | 2023-05-18 14:59 | N | Y |  | Line |  |  | For Information Only
ATCO | 7L72 (795s Zama - 828s Sulphur Point), 828s 702 (828s Sulphur Point) | 2023-05-16 08:00 | 2023-05-22 16:10 | N | N |  | Line, Circuit Breaker |  | Breaker 701 maintenance | For Information Only
ALTALINK | 338s 552 (338s Cherhill) | 2023-05-16 08:00 | 2023-05-16 16:30 | N | Y | doble 3 CT's | Circuit Breaker | Doble 3 CT's and take oil samples on 338s552 CT's (CT5) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 154s 252 (154s Black Spruce) | 2023-05-16 08:30 | 2023-05-16 09:59 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO | 848s 605 (848s Ruth Lake) | 2023-05-16 09:00 | 2023-05-16 13:00 | N | N | breaker partial/trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 672L (131s Moon Lake - 235s Entwistle) | 2023-05-16 09:00 | 2023-05-18 18:00 | N | N |  | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 154s 352 (154s Black Spruce) | 2023-05-16 10:00 | 2023-05-16 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO | 848s 601 (848s Ruth Lake) | 2023-05-16 13:01 | 2023-05-16 16:00 | N | N |  | Circuit Breaker | PRC Trip Coil Testing
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s SU2401 (657s Summerside), 657s SU2402 (657s Summerside) | 2023-05-17 07:00 | 2023-05-19 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354s RTU/SCADA (354s Summerview) | 2023-05-17 07:00 | 2023-05-18 03:00 | N | N | SCADA communication outage on Summerview 2 | Terminal Equipment | TransAlta is requesting communication outage at Summerview 2 (IEW2) May 17 2023 for turbine controller update from 1300 to 1500. During this time there will be no communication to turbines and turbines will not respond to WPM. |  | Affects Visibility
TRANSALTA | 418s Ardenville | 2023-05-17 07:00 | 2023-05-18 03:00 | N | N | SCADA communication outage | Station | TransAlta is requesting communication outage at Ardenville (ARD) May 17 2023 for turbine controller update from 1300 to 1500. During this time there will be no communication to turbines and turbines will not respond to WPM. |  | Affects Visibility
CNRL, ATCOP | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading), 838s 75-SD-904B (838s Horizon Mining), 842s 75-TR-5701 (842s Horizon Upgrading), 842s 75-TR-8701 (842s Horizon Upgrading), 842s 75-904A (842s Horizon Upgrading), 842s 75-1902 (842s Horizon Upgrading), 842s 75-1902B (842s Horizon Upgrading), 842s 75-1901 (842s Horizon Upgrading), 842s 75-1901A (842s Horizon Upgrading), 842s 75-1901B (842s Horizon Upgrading), 842s 75-1906 (842s Horizon Upgrading), 842s 75-1906A (842s Horizon Upgrading), 842s 75-1906B (842s Horizon Upgrading), 842s 75-8701 (842s Horizon Upgrading), 842s 75-5701 (842s Horizon Upgrading) | 2023-05-17 07:30 | 2023-05-26 10:33 | N | Y |  | Line, Switch, Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12B138-832L (SS-12) | 2023-05-17 08:00 | 2023-05-18 16:00 | N | Y | breaker maintenance 12B138-832L | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 36.2TR (SS-36) | 2023-05-17 08:00 | 2023-05-18 16:00 | N | N | tap changer maintenance, check reversing switch, oil sampling MT, TC | Transformer | tapchanger maintenance, tap changer oil filtration Maintenance. Check reversing switch. Oil Sampling MT, TC. |  | For Information Only
ATCO | 848s 602 (848s Ruth Lake) | 2023-05-17 09:00 | 2023-05-17 16:00 | N | N | 602 breaker partial/trip coil testing | Circuit Breaker |  |  | Contingency Requires Mitigation
EPCOR | 72RG7 (Garneau - Rossdale), G722 (Garneau), G723 (Garneau) | 2023-05-17 17:01 | 2023-11-26 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-05-17 23:00 | 2023-05-18 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-05-18 03:00 | 2023-05-18 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21) | 2023-05-18 08:00 | 2023-05-18 16:00 | N | N | power factor test 15B69-15.60, 15B69-15.60-CT | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAXEC | 383s Kettles Hill Windfarm | 2023-05-18 08:00 | 2023-05-18 18:00 | N | Y | DVAr maintenance and testing | Station |  |  | For Information Only, Restricts Generation
CapitalPower | 615s DVAR2 (615s Halkirk) | 2023-05-18 08:00 | 2023-10-01 07:59 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 6L57 (727s Kinuso - 735s Swan River) | 2023-05-18 09:40 | 2023-05-23 19:20 | N | N |  | Line |  |  | For Information Only
ATCO | 7L113 (853s Ring Creek - 930s Arcenciel) | 2023-05-18 13:00 | 2023-06-18 17:00 | N | Y |  | Line
ATCO | 7L133 (786s High Level - 828s Sulphur Point) | 2023-05-18 15:00 | 2023-05-22 16:10 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 199L (347s AML Fox Creek - 199AL tap) | 2023-05-18 15:25 | 2023-05-19 12:29 | N | Y |  | Line |  |  | For Information Only
ATCO | 834s 902 (834s Wesley Creek) | 2023-05-18 15:30 | 2023-05-21 17:30 | N | Y |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 673L (131s Moon Lake - 283s Violet Grove) | 2023-05-18 18:00 | 2023-05-19 18:17 | N | N |  | Line |  | Returned to service early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 199L (347s AML Fox Creek - 199AL tap), 347s 199E (347s AML Fox Creek) | 2023-05-19 12:30 | 2023-05-19 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 653S 138kV Bus 2 (653s Summit), 752L (653s Summit - 752AL tap), 688L (653s Summit - 688AL tap), 653.2TR (653s Summit), 653s 138-653.2TR (653s Summit), 653s 752 (653s Summit), 653s 688 (653s Summit), 752L76 (752AL tap) | 2023-05-20 07:00 | 2023-05-20 19:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 635EDD-1000 635PT-1004 (635EDD-1000), 635EDD-1000 635-752-112 (635EDD-1000), 635EDD-1000 635-752-113 (635EDD-1000), 635EDD-1000 635PS-1037 (635EDD-1000) | 2023-05-20 08:00 | 2023-05-21 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK, ENMAX | 752L (653s Summit - 752AL tap), 653s 752 (653s Summit) | 2023-05-21 07:00 | 2023-05-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 1.82L (SS-1 - SS-5), 5.1TR (SS-5), 5.6TR (SS-5), 5.8TR (SS-5), 5B138-1.82 (SS-5), 5B138-5BT12 (SS-5), 5B138-5BT7 (SS-5), 5MD138-5.1TR (SS-5), 5MD138-5.6TR (SS-5), 5MD138-5.8TR (SS-5) | 2023-05-21 08:00 | 2023-05-21 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2023-05-23 07:00 | 2023-05-23 17:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 814s T2 (814s Bellamy), 814s B2406 (814s Bellamy), 814s B2402 (814s Bellamy), BR722 (Rossdale), 814s BAB2 (814s Bellamy) | 2023-05-23 07:00 | 2023-06-02 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Outage extended | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia) | 2023-05-23 07:00 | 2023-05-25 11:48 | N | Y |  | Line |  | back early. was sched. for 26 May 2023 | 240 kV, Affects Cranking Path
EPCOR | T2 (Rossdale), R721 (Rossdale), R723 (Rossdale), RAB2 (Rossdale) | 2023-05-23 07:00 | 2023-06-09 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 727L (678s Okotoks - 727AL tap), 678s T2 (678s Okotoks), 678s 727 (678s Okotoks), 678s 452 (678s Okotoks) | 2023-05-23 08:00 | 2023-05-23 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.2TR (SS-38) | 2023-05-23 08:00 | 2023-05-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.82L (SS-13 - SS-22), 22B138-13.82 (SS-22), 13B138-13.82 (SS-13) | 2023-05-23 08:00 | 2023-05-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 240kV West Bus (SS-25), 1080L (SS-25 - SS-65), 25B240-D138 (SS-25), 25B240-D139 (SS-25), 25B240-D142 (SS-25), 25B240-D133 (SS-25), 25B240-D136 (SS-25), 25MD240-1080 (SS-25), 65MD240-1080 (SS-65) | 2023-05-23 08:01 | 2023-06-08 13:00 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1C (SS-38), 38B138-38.1CAP (SS-38) | 2023-05-23 08:11 | 2023-05-25 16:00 | N | N |  | Shunts, Circuit Breaker |  | Cap servicable | For Information Only
ALTALINK | 102s 6452 (102s Langdon) | 2023-05-23 10:30 | 2023-05-24 17:30 | N | Y |  | Circuit Breaker |  | Outage extended to complete work. | 240 kV, Contingency Requires Mitigation
ATCO | 936s 701T (936s Norberg), 936s 701 (936s Norberg) | 2023-05-23 11:00 | 2023-05-26 14:30 | N | N |  | Transformer, Circuit Breaker | 701T Maintenance, Will require back up genset installed for station service. |  | For Information Only
ALTALINK | 234s T1 (234s Fort Assiniboine), 234s T2 (234s Fort Assiniboine), 234s 888 (234s Fort Assiniboine), 234s 3 (234s Fort Assiniboine) | 2023-05-23 12:00 | 2023-05-23 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 535s 110 (535s Joffre), 535s T6 (535s Joffre) | 2023-05-23 12:00 | 2023-06-02 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 650s T3 (650s Hansman Lake), 650s SVC (650s Hansman Lake) | 2023-05-23 13:30 | 2023-05-24 16:30 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2023-05-23 23:00 | 2023-05-25 07:00 | N | N |  | Transformer |  |  | Restricts Generation
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2023-05-24 07:00 | 2023-05-24 17:00 | N | N |  | Line |  |  | For Information Only
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2023-05-24 07:00 | 2023-05-25 07:00 | N | N |  | Transformer |  |  | Restricts Generation
Saskpower | Sask Power AS903, Sask Power AS902 | 2023-05-24 08:00 | 2023-05-24 17:00 | N | Y |  | Circuit Breaker |  |  | For Information Only
Saskpower | Sask Power AS905, Sask Power AS909 | 2023-05-24 08:00 | 2023-05-24 17:00 | N | Y |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 853L (504s Queenstown - 853AL tap), 504s 853E (504s Queenstown) | 2023-05-24 10:30 | 2023-05-25 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, ENBRIDGE | 769L (377s AML Hardisty - 769BL tap), 769L (296s Rosyth - 769AL tap), 769L (769AL tap - 769BL tap), 769AL (656s Clipper - 769L tap), 769BL (594s Battle Sands - 769L tap), 656s T1 (656s Clipper), 656s 420TX1CB (656s Clipper), 594s 430-TX-1 (594s Battle Sands), 594s 430-TX-2 (594s Battle Sands), 594s 430-TX1 (594s Battle Sands), 594s 430-TX2 (594s Battle Sands), 594s 430-TX1-IS (594s Battle Sands), 594s 430-TX2-IS (594s Battle Sands), 594s 430-SUB-1-MBKR (594s Battle Sands), 296s T1 (296s Rosyth), 296s T2 (296s Rosyth), 296s 152 (296s Rosyth), 296s 11 (296s Rosyth), 296s 4 (296s Rosyth), 296s 1 (296s Rosyth), 296s 2 (296s Rosyth), 296s T3 (296s Rosyth) | 2023-05-25 07:30 | 2023-05-25 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 296s T1 (296s Rosyth), 296s T2 (296s Rosyth), 296s T3 (296s Rosyth) | 2023-05-25 07:30 | 2023-05-26 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 37.81L (SS-37 - SS-38), 38B138-37.81 (SS-38) | 2023-05-25 08:00 | 2023-05-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32) | 2023-05-25 08:00 | 2023-05-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 635-752-621 (635EDD-1001) | 2023-05-25 08:00 | 2023-05-25 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 710s 701 (710s Vermilion), 7L117 (706s Irish Creek - 710s Vermilion) | 2023-05-25 09:00 | 2023-05-25 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BSRW | 1019s Woolchester | 2023-05-25 09:00 | 2023-05-25 15:00 | N | Y |  | Station |  |  | Restricts Generation
ALTALINK | 102s 6452 (102s Langdon) | 2023-05-25 09:05 | 2023-05-29 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 710s 707C (710s Vermilion) | 2023-05-25 13:00 | 2023-05-25 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, ENBRIDGE | 769L (377s AML Hardisty - 769BL tap), 769L (296s Rosyth - 769AL tap), 769L (769AL tap - 769BL tap), 769AL (656s Clipper - 769L tap), 769BL (594s Battle Sands - 769L tap), 656s T1 (656s Clipper), 656s 420TX1CB (656s Clipper), 594s 430-TX-1 (594s Battle Sands), 594s 430-TX-2 (594s Battle Sands), 594s 430-TX1 (594s Battle Sands), 594s 430-TX2 (594s Battle Sands), 594s 430-TX1-IS (594s Battle Sands), 594s 430-TX2-IS (594s Battle Sands), 594s 430-SUB-1-MBKR (594s Battle Sands), 594s 430-SUB-1-IS (594s Battle Sands), 296s T1 (296s Rosyth), 296s T2 (296s Rosyth), 296s T3 (296s Rosyth), 296s 152 (296s Rosyth), 296s 11 (296s Rosyth), 296s 4 (296s Rosyth), 296s 1 (296s Rosyth), 296s 2 (296s Rosyth) | 2023-05-25 18:01 | 2023-05-25 21:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ENMAX | 32.1TR (SS-32) | 2023-05-26 08:00 | 2023-05-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7.84L (SS-7 - SS-36), 36B138-7.84 (SS-36), 7B138-7.84 (SS-7) | 2023-05-26 08:00 | 2023-05-26 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L130 (705s Kitscoty - 710s Vermilion), 710s 702 (710s Vermilion), 705s 704 (705s Kitscoty) | 2023-05-26 09:00 | 2023-05-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 21B138-21.80 (SS-21), 42s 21 (42s Sarcee) | 2023-05-26 12:00 | 2023-05-26 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCOP, CNRL | 838s 75-TR-2701 (838s Horizon Mining), 838s 75-BC-1917 (838s Horizon Mining), 838s 75-BC-1918 (838s Horizon Mining) | 2023-05-27 07:30 | 2023-06-04 07:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition
ENMAX | 65B240-D131 (SS-65), 65B240-D132 (SS-65) | 2023-05-27 08:00 | 2023-05-27 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 482s T1 (482s Haynes), 482s 784AW (482s Haynes) | 2023-05-28 08:00 | 2023-06-04 09:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 484s T3 (484s Millar Western), 484s 4 (484s Millar Western) | 2023-05-28 16:00 | 2023-06-01 17:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ATCO | 9L09 (849s Joslyn Creek - 888s Dover), 849s 902 (849s Joslyn Creek), 849s 903 (849s Joslyn Creek) | 2023-05-28 17:01 | 2023-06-11 11:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 803s T1 (EP 803s Lambton), EP 803s L2401 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton) | 2023-05-29 07:00 | 2023-05-29 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 816s P2403 (816s Petrolia) | 2023-05-29 07:00 | 2023-05-30 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), T3 (EPCOR Hardisty), H724 (EP Hardisty), H723 (EP Hardisty), HAB3 (EP Hardisty) | 2023-05-29 07:00 | 2023-06-02 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft), T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft) | 2023-05-29 07:00 | 2023-06-03 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
CNRL | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading), 842s 75-TR-4701 (842s Horizon Upgrading), 842s 75-TR-7701 (842s Horizon Upgrading), 842s 75-1902 (842s Horizon Upgrading), 842s 75-1902A (842s Horizon Upgrading), 842s 75-1903 (842s Horizon Upgrading), 842s 75-1903A (842s Horizon Upgrading), 842s 75-1903B (842s Horizon Upgrading), 842s 75-4701 (842s Horizon Upgrading), 842s 75-1904 (842s Horizon Upgrading), 842s 75-1904A (842s Horizon Upgrading), 842s 75-1904B (842s Horizon Upgrading), 842s 75-7701 (842s Horizon Upgrading), 842s 75-1905 (842s Horizon Upgrading), 842s 75-1905A (842s Horizon Upgrading) | 2023-05-29 07:30 | 2023-06-07 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16), 16B69-15.62 (SS-16) | 2023-05-29 08:00 | 2023-05-31 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 484s T2 (484s Millar Western) | 2023-05-29 08:00 | 2023-05-31 17:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 635EDD-1001 635-752-631 (635EDD-1001) | 2023-05-29 08:00 | 2023-05-29 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 37.1TR (SS-37) | 2023-05-29 08:00 | 2023-05-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 41.2TR (SS-41) | 2023-05-29 08:00 | 2023-06-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38) | 2023-05-29 08:00 | 2023-05-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 9L11 (813s Little Smoky - 834s Wesley Creek) | 2023-05-29 08:19 | 2023-06-09 10:00 | N | Y |  | Line |  | Outage complete. Line returned to service but taken out of service for voltage control. | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 840s McNeill Station | 2023-05-29 08:20 | 2024-02-05 10:14 | N | Y |  | Station |  |  | Limits ATC
ENMAX | 3.82L (SS-3 - SS-8) | 2023-05-29 09:07 | 2023-05-29 11:41 | N | N |  | Line
ATCO | 7L794 (157s Lac La Biche - 819s Whitby Lake), 819s 702 (819s Whitby Lake) | 2023-05-29 10:00 | 2023-05-31 12:30 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 42s T1 (42s Sarcee), 42s 40 (42s Sarcee) | 2023-05-29 10:30 | 2023-06-01 16:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2085s 601T (2085s Sheridan), 2085s 601 (2085s Sheridan) | 2023-05-29 12:00 | 2023-05-30 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | EP 803s T2 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s LAB2 (EP 803s Lambton) | 2023-05-30 07:00 | 2023-05-31 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 275s T2 (275s Jenner), 275s 46 (275s Jenner), 275s 2252 (275s Jenner), 275s 47 (275s Jenner) | 2023-05-30 08:00 | 2023-06-01 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV
SUNCOR | 29PL9-3 (29EDD-1 Millennium - 29EDD-3), 29EDD-3 29PT-6 (29EDD-3) | 2023-05-30 08:00 | 2023-06-03 20:00 | N | Y |  | Line, Transformer | 260kV Section of ring bus related to GTG6(between 29EDD1S9 |  | 240 kV, Restricts Generation
ATCO, ALBIAN | 920s 901T (920s Jackpine), 9LJH1 (919s Hartley - 920s Jackpine) | 2023-05-30 08:00 | 2023-06-03 16:00 | N | Y |  | Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15) | 2023-05-30 08:00 | 2023-05-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 170s T2 (170s Pike) | 2023-05-30 08:30 | 2023-06-01 13:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L130 (705s Kitscoty - 710s Vermilion) | 2023-05-30 09:00 | 2023-05-30 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1164L (816s Petrolia - EP Riverview), 816s PDS12 (816s Petrolia), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia) | 2023-05-31 07:00 | 2023-06-04 17:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
CNRL | 859s 701T (859s Primrose) | 2023-05-31 07:00 | 2023-06-02 15:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 781L (71s Lamoureux - 172s Sherritt), 172s 781W (172s Sherritt) | 2023-05-31 07:00 | 2023-05-31 19:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 14B138-14.83 (SS-14), 36B138-14.83 (SS-36) | 2023-05-31 08:00 | 2023-05-31 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-05-31 08:00 | 2023-06-15 18:00 | N | N |  | Not In Model |  |  | For Information Only
ATCO | 2085s 602T (2085s Sheridan) | 2023-05-31 08:00 | 2023-06-01 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.4TR (SS-2) | 2023-05-31 08:00 | 2023-06-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, PR | 949L (275s Jenner - 306s Halsbury), 275s 949 (275s Jenner), 275s 2689 (275s Jenner), 306s 240CB1 (306s Halsbury) | 2023-05-31 08:00 | 2023-05-31 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 535s T5 (535s Joffre) | 2023-05-31 08:30 | 2023-06-05 10:00 | N | N |  | Transformer |  | Outage extended. | For Information Only
ATCO | 813s 702 (813s Little Smoky) | 2023-05-31 13:00 | 2023-07-10 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
Lafarge Canada | 985s 811TF01 (985s Exshaw), 985s 811TF02 (985s Exshaw), 985s T3 (985s Exshaw), 985s 811QC03 (985s Exshaw), 985s 811QC04 (985s Exshaw), 985s 811QS01 (985s Exshaw), 985s 811QS02 (985s Exshaw), L300 (1020s Exshaw extension - 985s Exshaw), 1020s T1 (1020s Exshaw Extension) | 2023-06-01 05:30 | 2023-06-01 17:30 | N | N |  | Transformer, Circuit Breaker, Switch, Line |  |  | For Information Only
ALTALINK | 512s T1 (512s Hartell), 512s 812AL (512s Hartell) | 2023-06-01 07:00 | 2023-06-01 19:00 | N | N |  | Transformer, Switch |  |  | For Information Only
IMPERIALOIL | 9900s 0040-871-TNS-9923 (9900s Kearl), 9900s 0040-871-CB-9900-5-Q0 (9900s Kearl), 9900s 2040-871-CB-9923-1-Q0 (9900s Kearl) | 2023-06-01 08:00 | 2023-06-04 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 146s 823L (146s Macdonald), 593s 823L (593s Lakeview) | 2023-06-01 08:00 | 2023-06-01 13:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Syncrude | Mildred T1 (Syncrude Mildred Lake), 1335 (Syncrude Mildred Lake), 135 (Syncrude Mildred Lake) | 2023-06-01 08:00 | 2023-06-11 20:00 | N | N |  | Transformer, Circuit Breaker |  |  | Restricts Generation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-06-01 08:00 | 2023-06-03 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) Line and Disconnect Switch Major Maintenance (includes 635-652-100203 Breaker) |  | For Information Only
ATCO | 9L101 (957s McClelland - 2005s Secord) | 2023-06-01 10:00 | 2023-06-01 12:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 7L228 (845s Big Mountain - 7L20 tap) | 2023-06-01 15:00 | 2023-06-05 18:00 | N | Y |  | Line |  | emergency outage - due to wildfires | For Information Only, Affects Cranking Path
ATCO | 845s 703 (845s Big Mountain) | 2023-06-02 09:00 | 2023-06-02 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage
ALTALINK | 38s 4152 (38s East Edmonton), 38s 62 (38s East Edmonton), 38s T1 (38s East Edmonton), 38s 138kV Bus 1 (38s East Edmonton), 38s 865N (38s East Edmonton), 38s 736E (38s East Edmonton), 38s C1 (38s East Edmonton), 38s 737N (38s East Edmonton), 38s C2 (38s East Edmonton), 38s 73 (38s East Edmonton), 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 293s T1 (293s Bernese), 736L (38s East Edmonton - 293s Bernese), 293s T2 (293s Bernese), 865L (38s East Edmonton - 216s Knightsbridge), 293s 152 (293s Bernese), 293s 252 (293s Bernese) | 2023-06-02 21:00 | 2023-06-04 20:00 | N | Y |  | Circuit Breaker, Transformer, Bus, Shunts, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 95s T2 (95s Imperial Oil Edmonton) | 2023-06-02 21:00 | 2023-06-04 20:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 29s T2 (29s Cascade) | 2023-06-03 07:00 | 2023-06-03 18:00 | N | N |  | Transformer |  | Fortis to replace & test 264T power cables, close 29s Open Point G, & energize N-16B6137U cubicle. Fortis to cut over 105L1 to N-105L1 and create 177s Open Point F. Fortis to cut over 238L1 to N-238L1 and create 177s Open Point E. Fortis to phase @ 16B6135. At the end of the outage 264T will be fed from 105L1. 177s RSLD 3 & 29s RSLD 2 to be issued at the end of the outage. | For Information Only, Pre-Condition
SUNCOR | 29EDD-71 29PS-243 (29EDD-71 Edd71Sub) | 2023-06-03 08:00 | 2023-06-03 18:00 | N | N |  | Switch |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 24B138-24BT3 (SS-24), 24.1TR (SS-24), 24.81L (SS-24 - SS-31), 24.83L (74s Janet - SS-24), 31B138-24.81 (SS-31), 24B138-24.81 (SS-24), 24B138-24.83 (SS-24) | 2023-06-03 08:00 | 2023-06-03 18:00 | N | Y |  | Circuit Breaker, Transformer, Line |  | Power factor test 24B138-24.81-CT, 24B138-24BT3-CT | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 33 (74s Janet) | 2023-06-03 08:00 | 2023-06-03 18:00 | N | N |  | Switch |  | Power factor test 24B138-24.81-CT, 24B138-24BT3-CT. | For Information Only
ALTALINK | 33s 6 (33s Spray) | 2023-06-03 09:00 | 2023-06-03 17:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43) | 2023-06-04 08:00 | 2023-06-05 16:00 | N | N |  | Line, Circuit Breaker |  | Power factor test 33B138-33.84-CT. Power Factor Test LA's and Potheads - 33.84 | Creates Radial Feeds, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-06-04 08:00 | 2023-06-13 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) Reclaim 635EDD-1017 Substation Major Maintenance |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-06-04 08:00 | 2023-06-07 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) Line and Disconnect Switch Major Maintenance (includes 635-652-100303 Breaker) |  | For Information Only
ATCOP, CNRL | 838s 75-TR-1801 (838s Horizon Mining), 838s 75-BC-1914 (838s Horizon Mining), 838s 75-SD-1801 (838s Horizon Mining) | 2023-06-04 13:00 | 2023-06-09 18:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Protective Relay Testing, CVT 5YR PM | 240 kV, Pre-Condition
ALTALINK | 844L (358s Amoco Brazeau - 477s Amoco West Pembina), 477s 844X (477s Amoco West Pembina) | 2023-06-04 16:37 | 2023-06-22 13:40 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | EP 803s T3 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton), 72LS24 (EP 803s Lambton - Strathcona), 72LH8 (EP 803s Lambton - EP Hardisty) | 2023-06-05 07:00 | 2023-06-16 17:00 | N | Y |  | Transformer, Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s C1 (805s Jasper), EP 805s J2408 (EP 805s Jasper) | 2023-06-05 07:00 | 2023-12-08 16:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV
ALTALINK | 394s T4 (394s Empress), 394s 41 (394s Empress) | 2023-06-05 07:00 | 2023-06-08 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy), BR721 (Rossdale), 814s B2407 (814s Bellamy), 814s B2401 (814s Bellamy) | 2023-06-05 07:00 | 2023-06-14 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 430L (330P Genesee - 510S Sunnybrook) | 2023-06-05 07:00 | 2023-06-13 17:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2023-06-05 07:30 | 2023-06-07 12:30 | N | Y |  | Shunts |  |  | 500 kV
ALTALINK | AML 511s FB Bus 1 (AML 511s Crossings), AML 511s T30 (AML 511s Crossings), AML 511s 5352 (AML 511s Crossings), AML 511s 5252 (AML 511s Crossings) | 2023-06-05 08:00 | 2023-06-08 16:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 15.62L (SS-15 - SS-16), 16.60L (SS-16 - SS-34), 16.1TR (SS-16), 16B69-16.61 (SS-16), 16B69-15.62 (SS-16) | 2023-06-05 08:00 | 2023-06-05 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.80L (SS-1 - SS-28), 28B138-1.80 (SS-28) | 2023-06-05 08:00 | 2023-06-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 162.1TR (SS-162), 162B138-RB94 (SS-162), 162B138-RB86 (SS-162), 162B138-RB80 (SS-162), 162MD138-162.1TR (SS-162) | 2023-06-05 08:00 | 2023-06-16 18:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 20.82L (SS-20 - SS-21) | 2023-06-05 08:00 | 2023-06-08 08:51 | N | N |  | Line |  | Back early | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.4TR (SS-14) | 2023-06-05 08:00 | 2023-06-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L01 (813s Little Smoky - 881s Sturgeon 2), 881s 701T (881s Sturgeon), 813s 7L01D1 (813s Little Smoky), 881s 702TD (881s Sturgeon 2), 881s 702T (881s Sturgeon), 881s 701TD (881s Sturgeon 2) | 2023-06-05 08:30 | 2023-06-05 09:30 | N | Y |  | Line, Transformer, Switch |  |  | For Information Only, Restricts Generation, Affects Cranking Path
BCH | T3 (BCH Natal) | 2023-06-05 09:00 | 2023-06-15 17:00 | N | Y |  | Transformer | Natal T3 (BCH Natal) |  | 240 kV
ALTALINK, EPCOR | 908L (38s East Edmonton - 908AL tap), 908L (89s Ellerslie - 908AL tap), 908AL (52S East Industrial - 908L tap), 89s 852 (89s Ellerslie), 89s 752 (89s Ellerslie), 52s T2 (52s East Industrial), 38s 7652 (38s East Edmonton), 38s 7552 (38s East Edmonton) | 2023-06-05 09:30 | 2023-06-16 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 881s 701T (881s Sturgeon) | 2023-06-05 09:31 | 2023-06-08 08:29 | N | N |  | Transformer |  |  | For Information Only, Restricts Generation
Saskpower | SaskPower P2A | 2023-06-05 10:00 | 2023-06-11 18:00 | N | Y |  | Line | P2A Line, PRPS 1 Unit, PRPS 2 Unit, |  | Pre-Condition
Saskpower | SASK POWER P2C | 2023-06-05 10:00 | 2023-06-09 18:00 | N | Y |  | Line | P2A Line, PRPS 1 Unit, PRPS 2 Unit, CKPS 1 Unit, CKPS 2 Unit |  | Pre-Condition
ALTALINK | 535s T3 (535s Joffre) | 2023-06-05 10:00 | 2023-06-27 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 535s T3 (535s Joffre) | 2023-06-05 10:30 | 2023-06-22 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 951s SVC (951s Thickwood) | 2023-06-05 12:00 | 2023-06-09 17:30 | N | Y |  | Shunts |  |  | Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 16.60L (SS-16 - SS-34), 15.62L (SS-15 - SS-16), 16.2TR (SS-16), 36B69-16.63/36.5TR (SS-36) | 2023-06-05 12:01 | 2023-06-05 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 535s T4 (535s Joffre) | 2023-06-05 12:30 | 2023-06-08 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 28s 81 (28s West Brooks) | 2023-06-05 12:30 | 2023-06-05 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 28.2TR (SS-28) | 2023-06-06 08:00 | 2023-06-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.60L (SS-15 - SS-21), 15.1TR (SS-15), 15B69-15.60 (SS-15) | 2023-06-06 08:00 | 2023-06-06 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 26.83L (SS-26 - SS-65), 26.2TR (SS-26), 26B138-26BT3 (SS-26), 26B138-26.83 (SS-26) | 2023-06-06 08:00 | 2023-06-06 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L47 (718s Parsons Creek - 848s Ruth Lake), 7L165 (718s Parsons Creek - 933s Tower Road), 718s 701 (718s Parsons Creek), 718s 703 (718s Parsons Creek), 718s 701T (718s Parsons Creek) | 2023-06-06 08:00 | 2023-06-06 12:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 65s 2088N (65s High River) | 2023-06-06 08:00 | 2023-06-06 17:00 | N | N |  | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 39s T1 (39s Bickerdike) | 2023-06-06 08:00 | 2023-06-07 10:00 | N | Y |  | Transformer |  | back early | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 121s T2 (121s Brooks) | 2023-06-06 08:00 | 2023-06-06 16:00 | N | Y |  | Transformer |  |  | For Information Only, Restricts Generation
SUNCOR | 29EDD-71 29PT-234 (29EDD-71), 29EDD-71 752-4622 (29EDD-71), 29EDD-71 752-4621 (29EDD-71), 29EDD-71 29PS-238 (29EDD-71 Edd71Sub), 29EDD-71 30-252-12101 (29EDD-71) | 2023-06-06 08:00 | 2023-06-30 18:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only, Restricts Generation
ATCO | 930s SVC (930s Arcenciel), 930s 718 (930s Arcenciel) | 2023-06-06 08:00 | 2023-06-08 11:14 | N | N |  | Shunts, Circuit Breaker |  | Back early | Pre-Condition
ALTALINK | 651s T1 (651s Kirby), 651s 152 (651s Kirby) | 2023-06-06 08:30 | 2023-06-07 17:58 | N | N |  | Transformer, Circuit Breaker |  | Back early | For Information Only
ALTALINK | 155s T2 (155s Blackmud) | 2023-06-06 08:30 | 2023-06-06 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 602s 2082N (602s Cold Creek) | 2023-06-06 09:30 | 2023-06-06 16:30 | N | N |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
ALTALINK | 172s T4 (172s Sherritt Gordon), 172s 74 (172s Sherritt) | 2023-06-06 09:30 | 2023-06-10 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 523s C1 (523s Bullshead) | 2023-06-06 09:30 | 2023-06-06 14:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 412L (396s Pincher Creek - 632s Russell), 632s 412 (632s Russell) | 2023-06-06 10:00 | 2023-06-06 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16), 15.2TR (SS-15), 15B69-15.62 (SS-15) | 2023-06-06 12:00 | 2023-06-06 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 718s 701 (718s Parsons Creek) | 2023-06-06 12:01 | 2023-06-30 14:00 | N | N |  | Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 632s 152 (632s Russell) | 2023-06-06 13:00 | 2023-06-06 15:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 121s T5 (121s Brooks) | 2023-06-07 08:00 | 2023-06-07 16:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 510s 43 (510s Sunnybrook), 1325L (510s Sunnybrook - AML 511s Crossings), 510s 4289 (510s Sunnybrook), 510s 41 (510s Sunnybrook) | 2023-06-07 08:00 | 2023-06-07 14:00 | N | Y |  | Switch, Line |  |  | 500 kV, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2023-06-07 08:00 | 2023-06-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27) | 2023-06-07 08:00 | 2023-06-08 14:28 | N | N |  | Line, Circuit Breaker |  | Back early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (SS-32 - SS-40), 40.1TR (SS-40), 40B138-32.83 (SS-40), 40MD138-40.1TR (SS-40), SW84 (SS-40) | 2023-06-07 08:00 | 2023-06-07 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 1L274 (B1s BCH Natal - 1D1L274) | 2023-06-07 09:00 | 2023-06-07 13:00 | N | Y |  | Line | Entered (43 MW) asTRM+ in Margo and posted. Then used the values for BC from the ITC Posting page to enter into the ATC and TTC values in the CROW record. |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 103s 452 (103s Goose Lake) | 2023-06-07 09:30 | 2023-06-07 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 40.81L (SS-40 - SS-41), 40.2TR (SS-40), 40B138-40.81 (SS-40), 40MD138-40.2TR (SS-40), SW83 (SS-40) | 2023-06-07 12:01 | 2023-06-07 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 510s ACF11 (510s Sunnybrook), 510s 1152 (510s Sunnybrook) | 2023-06-07 12:30 | 2023-06-07 12:31 | N | Y |  | Shunts, Circuit Breaker |  | Cancelled back on May 15/23 by scheduler. | 500 kV, Pre-Condition
BCH | 1L274 (EFT - 1D2L274) | 2023-06-07 13:01 | 2023-06-17 17:00 | N | Y |  | Line | Entered (43 MW) asTRM+ in Margo and posted. Then used the values for BC from the ITC Posting page to enter into the ATC and TTC values in the CROW record. |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove), 595s 712 (595s Spruce Grove) | 2023-06-08 06:00 | 2023-06-12 17:31 | N | N |  | Line, Circuit Breaker |  | Back early | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 36.81L (44s Bearspaw Plant - SS-36), 36B138-36.81 (SS-36), 44s 36.81E (44s Bearspaw Plant) | 2023-06-08 08:00 | 2023-06-08 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 41.84L (SS-41 - SS-54), 54.81L (SS-54 - SS-65), 54.1TR (SS-54), 54B138-41.84 (SS-54), 54B138-54.81 (SS-54) | 2023-06-08 08:00 | 2023-06-08 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L01 (813s Little Smoky - 881s Sturgeon 2), 813s 7L01D1 (813s Little Smoky), 881s 701TD (881s Sturgeon 2), 881s 701T (881s Sturgeon), 881s 702T (881s Sturgeon), 881s 702TD (881s Sturgeon 2) | 2023-06-08 08:30 | 2023-06-08 09:30 | N | Y |  | Line, Switch, Transformer |  |  | Restricts Generation, Affects Cranking Path
ATCO | 881s 702T (881s Sturgeon) | 2023-06-08 09:31 | 2023-06-10 16:00 | N | N |  | Transformer |  |  | Restricts Generation
BCH | 2L112 (BPA Boundary - BCH Nelway) | 2023-06-08 10:00 | 2023-06-08 16:00 | N | Y |  | Line |  | CaISO Outage Details: Originating System: BPAT_TOP Originating System Number: 23-01590 Priority: PLANNED Description: END-TO-END TRIP CHECKS WITH BC HYDRO Comments: CaISO Import equipment not found: RDFID: _78a55b4c-2216-2343-b756-74684ea7bfaa Originating System: BPAT_TOP CaISO Id: 12690881 | 240 kV, Pre-Condition
ALTALINK | 394s T3 (394s Empress), 394s 36 (394s Empress) | 2023-06-08 13:00 | 2023-06-16 15:00 | N | N |  | Transformer, Circuit Breaker | The delay is due to Customer underground cable issues. |  | For Information Only
ALTALINK | 385s T3 (385s Spring Coulee) | 2023-06-09 07:00 | 2023-06-16 11:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5CB4 (BCH Selkirk) | 2023-06-09 09:00 | 2023-06-09 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ATCO | 7L01 (813s Little Smoky - 881s Sturgeon 2), 813s 7L01D1 (813s Little Smoky), 881s 701T (881s Sturgeon), 881s 701TD (881s Sturgeon 2), 881s 702T (881s Sturgeon) | 2023-06-10 16:01 | 2023-06-10 17:00 | N | Y |  | Line, Switch, Transformer |  |  | For Information Only, Restricts Generation, Affects Cranking Path
ATCO | 7L64 (747s Bassett - 930s Arcenciel) | 2023-06-12 | 2024-02-29 10:01 | N | Y |  | Line |  | It didn't reflect in outage scheduler going to push it through | Affects Cranking Path
ALTALINK | 740L (39s Bickerdike - 740AL tap) | 2023-06-12 | 2023-06-12 15:00 | N | N |  | Line
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2023-06-12 | 2023-06-13 07:23 | N | Y |  | Line |  | return early
ATCO | 7L64 (747s Bassett - 930s Arcenciel), 7L113 (853s Ring Creek - 930s Arcenciel) | 2023-06-12 | 2024-02-21 13:15 | N | Y |  | Line |  |  | Restricts Generation, Affects Cranking Path
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2023-06-12 | 2023-08-11 23:59 | N | N |  | Line |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 847L (39s Bickerdike - 406s Fickle Lake) | 2023-06-12 | 2023-06-28 11:00 | N | Y |  | Line
EPCOR | 8L10 (330P Genesee - Fording Coal Mine), 330p 808 (330p Genesee) | 2023-06-12 07:00 | 2023-06-17 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 657s T2 (657s Summerside) | 2023-06-12 07:00 | 2023-06-12 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft) | 2023-06-12 07:00 | 2023-06-30 17:00 | N | N |  | Line |  |  | For Information Only
EPCOR | G723 (Garneau), G724 (Garneau), T3 (Garneau), GAB3 (Garneau), GT3 (Garneau) | 2023-06-12 07:00 | 2023-06-23 17:00 | N | N |  | Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 172s T3 (172s Sherritt Gordon), 172s 73 (172s Sherritt) | 2023-06-12 07:30 | 2023-06-15 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 431s T2 (431s Hussar) | 2023-06-12 08:00 | 2023-06-14 13:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34), 34B69-16.60 (SS-34), 16B69-16.60 (SS-16) | 2023-06-12 08:00 | 2023-06-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 36.3TR (SS-36) | 2023-06-12 08:00 | 2023-06-15 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | D05 71 (D05) | 2023-06-12 08:00 | 2023-06-13 18:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 20.82L (SS-20 - SS-21), 20B138-20.82 (SS-20), 21B138-20.82 (SS-21) | 2023-06-12 08:00 | 2023-06-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.80L (SS-1 - SS-28) | 2023-06-12 08:00 | 2023-06-23 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 20.1TR (SS-20) | 2023-06-12 08:00 | 2023-06-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 395s T1 (395s North Holden) | 2023-06-12 09:00 | 2023-06-16 17:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5CB5 (BCH Selkirk) | 2023-06-12 09:00 | 2023-06-12 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ATCO | 2075s ACF11 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell), 2075s 917 (2075s Newell), 2075s 918 (2075s Newell), 2075s 917B (2075s Newell), 2075s 918A (2075s Newell) | 2023-06-12 09:30 | 2023-06-30 17:30 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Prevents Normal Events
ALTALINK | 38s T2 (38s East Edmonton) | 2023-06-12 10:30 | 2023-06-15 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s 252 (77s Sagitawah), 77s 452 (77s Sagitawah) | 2023-06-12 11:00 | 2023-06-14 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet) | 2023-06-12 11:00 | 2023-06-13 17:00 | N | Y |  | Shunts | Replace the failed protection for C4 at 74s. C4 is already out of service due to failure. C3 will also be out of service during repair. |  | 240 kV, Pre-Condition
ALTALINK | 65s T2 (65s High River) | 2023-06-12 12:30 | 2023-06-18 18:00 | N | N |  | Transformer |  |  | Restricts Generation
ATCO | 856s 701 (856s Kinosis), 856s 902T (856s Kinosis), 856s 505R (856s Kinosis), 856s 706 (856s Kinosis), 856s 707C (856s Kinosis) | 2023-06-12 13:00 | 2023-06-16 14:00 | N | Y |  | Transformer, Circuit Breaker, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L224 (650s Hansman Lake - 774s Monitor), 774s 701 (774s Monitor), 650s 1752 (650s Hansman Lake) | 2023-06-12 13:00 | 2023-06-15 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 825s 901 (825s Whitefish Lake) | 2023-06-12 15:00 | 2023-06-22 15:45 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 24.82L (SS-24 - SS-65), 65MD138-24.82 (SS-65), 65B138-D81 (SS-65), 65B138-D82 (SS-65) | 2023-06-13 08:00 | 2023-06-13 12:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 651s T2 (651s Kirby), 651s 252 (651s Kirby) | 2023-06-13 08:30 | 2023-06-16 14:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
BCH | 5CB8 (BCH Selkirk) | 2023-06-13 09:00 | 2023-06-13 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ATCO | 7L31 (732s Mitsue - 844s AEC MILL), 7L30 (732s Mitsue - 844s AEC Mill), 844s 701T (844s AEC Mill), 844s 702T (844s AEC Mill), 844s 704 (844s AEC Mill), 732s 7L31D1 (732s Mitsue), 844s 701 (844s AEC Mill), 844s 401 (844s AEC Mill), 844s 702 (844s AEC Mill), 844s 703 (844s AEC Mill), 844s 402 (844s AEC Mill), 732s 7L30D1 (732s Mitsue), 844s 401TD (844s AEC Mill), 844s 402TD (844s AEC Mill), 844s 403 (844s AEC Mill), 844s G1 (844s AEC Mill), 844s G2 (844s AEC Mill), 844s G3 (844s AEC Mill), 844s M1 (844s AEC Mill), 844s M2 (844s AEC Mill) | 2023-06-13 09:00 | 2023-06-13 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap) | 2023-06-13 09:12 | 2023-06-14 18:00 | N | N |  | Line | 700L tripped at 9:12. Alta Link did a patrol and found 2 structures down ETA tomorrow at 18:00. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2023-06-13 09:54 | 2023-06-14 18:00 | N | Y |  | Line | 612L tripped at 9:54. Alta Link cannot get a crew there due to everyone working at Brazeau loop. They dont want to attempt a reclose due to their fire risk management plan. fertilizer lane took out shield wire which then came into contact with the line |  | For Information Only
ENMAX | 26.83L (SS-26 - SS-65), 65MD138-26.83 (SS-65), 65B138-D84 (SS-65), 65B138-D85 (SS-65) | 2023-06-13 12:01 | 2023-06-13 18:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 856s 901 (856s Kinosis) | 2023-06-13 16:00 | 2023-06-22 14:35 | N | Y |  | Circuit Breaker
ATCO | 2029s ACF12 (2029s Heathfield) | 2023-06-13 16:00 | 2023-06-15 16:00 | N | Y |  | Shunts
SNRL | HRV2 High River 2 DER | 2023-06-14 08:00 | 2023-06-28 17:00 | N | N |  | Unit
ENMAX | 33.1TR (SS-33) | 2023-06-14 08:00 | 2023-06-14 12:00 | N | N |  | Transformer |  |  | For Information Only
AGPL | EMP1 Empress Solar Park | 2023-06-14 08:00 | 2023-09-08 16:00 | N | N |  | Unit
AGPL | EMP1 Empress Solar Park | 2023-06-14 08:00 | 2023-09-15 16:00 | N | N |  | Unit
TRANSALTA | 240s McBride Lake | 2023-06-14 08:00 | 2023-06-14 17:00 | N | N |  | Station |  |  | Restricts Generation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-06-14 08:00 | 2023-06-23 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) Barge 635EDD-1012 Substation Major Maintenance |  | For Information Only
ENBRIDGE | 485s 35DSTAT1 (485s Blackspring) | 2023-06-14 08:00 | 2023-06-19 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 1106L (237s Foothills - SS-65), 65B240-D130 (SS-65), 65B240-D131 (SS-65), 65MD240-1106 (SS-65) | 2023-06-14 08:00 | 2023-06-14 12:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton) | 2023-06-14 08:00 | 2023-06-14 17:00 | N | N |  | Shunts | Delayed by a day due to lack of man power being utilized for wild fire work. |  | Pre-Condition
BCH | 5CB9 (BCH Selkirk) | 2023-06-14 09:00 | 2023-06-14 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ATCO | 969s 701T (969s Lindbergh), 969s 701 (969s Lindbergh), 969s 301 (969s Lindbergh), 969s 501 (969s Lindbergh) | 2023-06-14 09:30 | 2023-06-15 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
PGCP | PEC1 Lindbergh | 2023-06-14 09:30 | 2023-06-15 16:00 | N | N |  | Unit
ENMAX, ALTALINK | 1107L (237s Foothills - SS-65), 65B240-D134 (SS-65), 65B240-D133 (SS-65), 65MD240-1107 (SS-65) | 2023-06-14 12:00 | 2023-06-14 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 431s T1 (431s Hussar) | 2023-06-14 13:01 | 2023-06-16 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 803s T3 (EP 803s Lambton), EP 803s LAB3 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton) | 2023-06-15 07:00 | 2023-06-16 17:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 65.1TR (SS-65), 65B138-D83 (SS-65), 65B138-D81 (SS-65), 65B240-D130 (SS-65), 65B240-D133 (SS-65) | 2023-06-15 08:00 | 2023-06-15 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden) | 2023-06-15 08:30 | 2023-06-15 11:30 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville), 395s 77E (395s North Holden) | 2023-06-15 11:30 | 2023-06-15 14:30 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Restricts Generation
ALTALINK | 701L (223s Strome - 395s North Holden), 395s 701X (395s North Holden) | 2023-06-15 14:30 | 2023-06-15 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 8B138-5A0 (SS-8) | 2023-06-16 08:00 | 2023-06-16 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
BCH | T4 (BCH Natal) | 2023-06-16 09:00 | 2023-07-07 17:00 | N | Y |  | Transformer |  |  | 240 kV
ENMAX | 240kV West Bus (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25) | 2023-06-17 08:00 | 2023-06-17 13:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 240kV East Bus (SS-25), 25B240-D140 (SS-25), 25B240-D138 (SS-25), 25B240-D134 (SS-25), 25B240-D131 (SS-25) | 2023-06-17 13:01 | 2023-06-17 18:00 | N | Y |  | Bus, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L90 (813s Little Smoky - 7LA90 tap) | 2023-06-18 | 2023-06-22 18:00 | N | N |  | Line
ATCO, BluEarth | 7LA128 (572s Highland - 7L128 tap), 572S 35CB1 (572s Highland), 572S 35CB2 (572s Highland), 572S 35CB3 (572s Highland), 572S 35CB4 (572s Highland), 572S 35CB5 (572s Highland), 572S 144CB1 (572s Highland), 572S 144DSW1 (572s Highland) | 2023-06-19 06:00 | 2023-06-23 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Restricts Generation
EPCOR | 72RG7 (Garneau - Rossdale), RG725 (Rossdale), G722 (Garneau), G724 (Garneau) | 2023-06-19 07:00 | 2023-08-04 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK, ENEL | 205s T1 (205s Castle Rock Ridge), 205s 89T1 (205s Castle Rock Ridge), 205s 52M1 (205s Castle Rock Ridge), 205S 52F3 (205s Castle Rock Ridge), 205S 52F6 (205s Castle Rock Ridge), 205S 52F1 (205s Castle Rock Ridge), 205S 52F2 (205s Castle Rock Ridge), 205S 52F4 (205s Castle Rock Ridge), 205S 52F5 (205s Castle Rock Ridge) | 2023-06-19 07:30 | 2023-06-21 14:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | Restricts Generation
ENMAX | 162.2TR (SS-162) | 2023-06-19 08:00 | 2023-06-30 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 24.81L (SS-24 - SS-31), 31B138-24.81 (SS-31) | 2023-06-19 08:00 | 2023-06-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 36.3TR (SS-36) | 2023-06-19 08:00 | 2023-06-20 16:00 | N | N |  | Transformer | Tapchanger maintenance. Oil sampling MT, TC. Replace PRD Junction Box |  | For Information Only
REDDEER | 194s T1 (194s South Red Deer), 194s 15-81-1 (194s South Red Deer) | 2023-06-19 08:00 | 2023-06-20 16:30 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 194s 138kV Bus (194s South Red Deer), 425L (194s South Red Deer - 217s North Red Deer) | 2023-06-19 08:00 | 2023-06-20 16:30 | N | N |  | Bus, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 52s E2401 (52s East Industrial), 1059AL (52s East Industrial - 1059L tap), 1059L (38s East Edmonton - 1059AL tap), 1059L (EP 803s Lambton - 1059AL tap), EP 803s L2404 (EP 803s Lambton), EP 803s L2401 (EP 803s Lambton), 38s 7552 (38s East Edmonton), 38s 7452 (38s East Edmonton) | 2023-06-19 09:30 | 2023-06-30 17:00 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2023-06-19 10:00 | 2023-06-23 16:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 940s 702T (940s Beartrap), 940s 702 (940s Beartrap) | 2023-06-19 11:00 | 2023-06-22 12:00 | N | N |  | Transformer, Circuit Breaker |  | Extended | For Information Only
ALTALINK | 562s T2 (562s Cypress) | 2023-06-19 12:00 | 2023-06-22 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2023-06-19 12:00 | 2023-06-22 18:00 | N | N |  | Transformer | Replace SS1. Maintenance on 54s29. |  | For Information Only
ALTALINK | 256s T2 (256s Harmattan) | 2023-06-19 12:30 | 2023-06-28 18:00 | N | N |  | Transformer | Replace switch 256s37, 256s38. Replace breaker 256s148X. Hot switch repair 256s43, 256s51 |  | For Information Only
ALTALINK | 353s T1 (353s Plamondon) | 2023-06-19 13:00 | 2023-06-27 15:25 | N | N |  | Transformer | T1 oil reclaim, repair T1 & VR1 leaks, tap changer testing, doble, 25kV bushings | Outage completed early | For Information Only
ATCO | 7L128 (802s Michichi Creek - 7LA128 tap), 7L128 (963s Coyote Lake - 7LA128 tap) | 2023-06-19 13:00 | 2023-06-19 17:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
ATCO | 6L09 (767s Oyen - 6L21 tap), 767s 601 (767s Oyen) | 2023-06-19 16:00 | 2023-06-26 15:00 | N | N |  | Line, Circuit Breaker | pole / arm replace (28 poles to change between D7 & D8, 91 cross arms to change) |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29PL9-14 (29EDD-34 - 29EDD-56), 29EDD-34 29-952-141 (29EDD-34), 29EDD-34 29-952-142 (29EDD-34), 29EDD-34 29PS-227 (29EDD-34), 29EDD-56 952-1401 (29EDD-56), 29EDD-56 29PS-164 (29EDD-56) | 2023-06-20 06:00 | 2023-07-01 18:18 | N | Y |  | Line, Circuit Breaker, Switch |  | Work was completed early. | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 54.81L (SS-54 - SS-65), 65B138-D84 (SS-65), 65B138-D83 (SS-65) | 2023-06-20 08:00 | 2023-06-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
Lethbridge, ALTALINK | 146s 24 (146s Macdonald), 146s 813L (146s Macdonald), 146s 667 (146s Macdonald), 667L (146s MacDonald - 370s North Lethbridge), 813L (146s MacDonald - 241s Uplands) | 2023-06-20 08:00 | 2023-06-20 16:00 | N | N |  | Switch, Circuit Breaker, Line |  | NEED TO HAVE AN OPEN-END OUTAGE ON 667L AND 813L TO ALLOW FIELD CREWS TO ADJUST AND ALIGN 146S24. WE ARE PREPARED TO ADJUST START TIMES IF NECESSARY TO REDUCE LOADING AND VOLTAGE ISSUES | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 802s 705C (802s Michichi Creek) | 2023-06-20 08:30 | 2023-06-21 17:30 | N | N |  | Shunts |  |  | Pre-Condition
BCH | 5RX1 (BCH Vaseux Lake) | 2023-06-20 09:00 | 2023-06-22 17:00 | N | Y |  | Shunts |  | inspect, doble test, and check Non EL's on VAS 5RX1. Also certify the fall arrest anchor points BC maintenance does not affect the Alberta ATC | 500 kV, Pre-Condition
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2023-06-20 09:00 | 2023-06-20 09:30 | Y | Y |  | Line |  |  | Limits ATC, 500 kV
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2023-06-20 11:22 | 2023-06-21 17:00 | N | Y |  | Line | 973L (39s Bickerdike - 310p Sundance) |  | 240 kV
CMH | MHS-1 MH69-T3A (MHS-1 Power P Switchyard) | 2023-06-20 14:00 | 2023-06-28 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, ENEL | 205s T2 (205s Castle Rock Ridge), 205s C1 (205s Castle Rock Ridge), 205s 89T2 (205s Castle Rock Ridge), 205s 52M2 (205s Castle Rock Ridge), 205s 52F11 (205s Castle Rock Ridge), 205s 52F12 (205s Castle Rock Ridge), 205s 52F13 (205s Castle Rock Ridge), 205s 52R11 (205s Castle Rock Ridge), 205s 89F11 (205s Castle Rock Ridge), 205s 89F12 (205s Castle Rock Ridge), 205s 89F13 (205s Castle Rock Ridge), 205s 89M2 (205s Castle Rock Ridge), 205s 89R11 (205s Castle Rock Ridge) | 2023-06-21 07:30 | 2023-06-23 14:00 | N | Y |  | Transformer, Shunts, Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 65s 2088N (65s High River), 65s 52-1 (65s High River) | 2023-06-21 08:00 | 2023-06-21 17:00 | N | N |  | Circuit Breaker | DER Customer on this line must be offline while testing the new TPR for 65s63X as it will also trip this site. |  | Restricts Generation
ALTALINK | 150s T1 (150s Clyde) | 2023-06-21 08:00 | 2023-06-21 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 426L (63s Red Deer - 194s South Red Deer), 194s 426 (194s South Red deer), 63s 426 (63s Red Deer) | 2023-06-21 08:00 | 2023-06-21 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 36.1TR (SS-36) | 2023-06-21 08:00 | 2023-06-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162.2TR (SS-162), 162B138-RB83 (SS-162), 162B138-RB84 (SS-162), 162B138-RB92 (SS-162) | 2023-06-21 08:00 | 2023-06-21 18:00 | N | Y |  | Transformer, Circuit Breaker |  | Power Factor Test - 162PT138-T2. Breaker Dashpot Checks - 162B138-RB83, 162B138-RB84. 162.2TR already OOS | 240 kV, Contingency Requires Mitigation, Pre-Condition
REDDEER | 194s T2 (194s South Red Deer), 194s 15-81-2 (194s South Red Deer) | 2023-06-21 08:00 | 2023-06-21 16:30 | N | N |  | Transformer, Switch |  |  | For Information Only
EPCOR | 524s T1 (524s Owens Corning) | 2023-06-22 07:00 | 2023-06-22 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 247s 138kV Bus (247s Piper Creek), 427L (63s Red Deer - 247s Piper Creek), 247s 427 (247s Piper Creek) | 2023-06-22 08:00 | 2023-06-22 16:30 | N | N |  | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
REDDEER | 247s 17-89-1 (247s Piper Creek), 247s T1 (247s Piper Creek) | 2023-06-22 08:00 | 2023-06-22 16:30 | N | N |  | Switch, Transformer |  |  | For Information Only, Pre-Condition
ENMAX, ALTALINK | 1109L (SS-25 - SS-65), 25B240-D142 (SS-25), 25B240-D141 (SS-25), 25MD240-1109 (SS-25) | 2023-06-22 08:00 | 2023-06-22 09:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 706 (802s Michichi Creek), 804s 701 (804s Wintering Hills) | 2023-06-22 08:30 | 2023-06-23 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 940s 701T (940s Beartrap), 940s 701 (940s Beartrap) | 2023-06-22 09:00 | 2023-06-22 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | EP 511s Victoria T3 (EP 511s Victoria) | 2023-06-22 14:00 | 2023-06-28 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 385s T1 (385s Spring Coulee), 385s T2 (385s Spring Coulee) | 2023-06-23 07:30 | 2023-06-26 15:30 | N | N |  | Transformer |  |  | For Information Only
REDDEER | 247s 17-89-2 (247s Piper Creek), 247s T2 (247s Piper Creek) | 2023-06-23 08:00 | 2023-06-23 16:30 | N | N |  | Switch, Transformer |  |  | For Information Only
SRLP | SWP1 Stirling Wind Project | 2023-06-23 08:00 | 2023-10-05 17:00 | N | Y |  | Unit
ALTALINK | 247s 138kV Bus (247s Piper Creek), 755L (247s Piper Creek - 535s Joffre), 247s 755 (247s Piper Creek) | 2023-06-23 08:00 | 2023-06-23 16:30 | N | N |  | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 822s 701T (822s Wolf Lake), 822s 704 (822s Wolf Lake) | 2023-06-23 10:00 | 2023-11-24 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | T3 (Garneau) | 2023-06-23 17:01 | 2024-02-16 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 771L (SS-47 - SS-162), 47.1TR (SS-47), 47.2TR (SS-47), 162B138-RB82 (SS-162), 162B138-RB81 (SS-162), 162MD138-771L (SS-162), 47B138-BT3 (SS-47), 47B138-771/1 (SS-47), 47B138-771 (SS-47), 47MD138-47.1TR (SS-47), 47MD138-47.2TR (SS-47) | 2023-06-24 08:00 | 2023-06-25 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 325s 1552 (325s Leduc), 325s C1 (325s Leduc) | 2023-06-24 11:00 | 2023-07-05 18:00 | N | N |  | Circuit Breaker, Shunts |  |  | For Information Only, Pre-Condition
EPCOR | EP 511s Victoria T4 (EP 511s Victoria) | 2023-06-25 07:00 | 2023-06-25 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde), 191s 792N (191s N.W. Cardiff) | 2023-06-26 06:00 | 2023-06-28 19:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 657s SU2404 (657s Summerside) | 2023-06-26 07:00 | 2023-06-30 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3), 13B138-3.84 (SS-13) | 2023-06-26 08:00 | 2023-06-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | AL-1 (Aurora - D05), D05 520 (D05), D05 519 (D05), D05 517 (D05) | 2023-06-26 08:00 | 2023-06-27 20:00 | N | Y |  | Line, Switch, Circuit Breaker | Significant Outage: Require outage to replace the motor on MOD 520 in D05 substation. The following motor operated disconnect switches will be operated: 519B @ D05 Substation 520 @ D05 Substation 517A @ D05 Substation 215 @ G01 Substation |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 11.4TR (SS-11) | 2023-06-26 08:00 | 2023-07-03 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 22.81L (SS-22 - SS-39), 39B138-22.81 (SS-39), 22B138-22.81 (SS-22) | 2023-06-26 08:00 | 2023-06-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 820AL (315s Chin Chute - 820L tap), 820L (254s Coaldale - 820AL tap), 820BL (967s Redcoat - 820L tap), 820L (67s Stirling - 820BL tap), 820L (820AL tap - 820BL tap), 67s 2 (67s Stirling), 67s 820 (67s Stirling), 67s T2 (67s Stirling), 254s 820 (254s Coaldale) | 2023-06-26 09:00 | 2023-06-30 16:00 | N | Y |  | Line, Circuit Breaker, Switch, Transformer | Install and commissioning new D60 and SEL311 settings update, SCADA updates, new telecom equipment installed and commissioned and new RAS relays at 254s installed and commissioned. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
BCH | 5CB11 (BCH Selkirk) | 2023-06-26 09:00 | 2023-06-26 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ALTALINK, EPCOR | 1045L (EP 805s Jasper - 1045AL tap), 1045L (310p Sundance - 1045AL tap), 1045AL (320p Keephills - 1045L tap), EP 805s J2406 (EP 805s Jasper), EP 805s J2407 (EP 805s Jasper), 320p 1352 (320p Keephills) | 2023-06-26 09:30 | 2023-06-28 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-06-26 09:30 | 2023-06-28 18:00 | N | N |  | Line, Circuit Breaker | Install new foundations beside existing structures 77-81, 83-88, 90-99, 101-110, 120, 134, 145, & 151 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 863s 902T (863s Paintearth) | 2023-06-26 09:30 | 2023-06-28 12:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ATCO | 9L08 (849s Joslyn Creek - 888s Dover), 888s 902 (888s Dover) | 2023-06-26 10:00 | 2023-06-28 17:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV
ATCO | 956s 702T (956s Watt Lake), 956s 702 (956s Watt Lake) | 2023-06-26 12:00 | 2023-06-27 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | T1 (Kennedale) | 2023-06-27 07:00 | 2023-06-27 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 183s T1 (183s Underwood), 183s T2 (183s Underwood) | 2023-06-27 07:30 | 2023-06-27 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | SW89 (SS-22) | 2023-06-27 08:00 | 2023-06-27 16:00 | N | N |  | Switch |  | 22PT138-Z31 outage. 22PT138-Z31 - West phase oil level indicate - investigate. 22PT138-Z31 sec. fuses. 13.82L distance elements offline while PTs offline, line remains protected through differential protection. | For Information Only, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray), 20s 113 (20s Ghost), 33s 113 (33s Spray) | 2023-06-27 08:00 | 2023-06-27 17:00 | N | N |  | Line, Circuit Breaker |  | Install markerballs on OHSW at Hwy 1X crossing in structure 112 ahead span | Overload, Pre-Condition, Affects Cranking Path
ENMAX | 13.82L (SS-13 - SS-22), 22B138-13.82 (SS-22), 13B138-13.82 (SS-13) | 2023-06-27 08:00 | 2023-06-27 16:00 | N | N |  | Line, Circuit Breaker |  | power factor test 22B138-13.82, 22B138-13.82-CT | Creates Radial Feeds, Firm Load Loss
ATCO | 7L33 (845s Big Mountain - 7LA33 tap) | 2023-06-27 08:00 | 2023-06-29 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 810s 701T (810s Dome Cutbank), 810s Protection & Control (810s Dome Cutbank) | 2023-06-27 09:00 | 2023-06-27 17:00 | N | N |  | Transformer, Terminal Equipment |  |  | For Information Only
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2023-06-27 09:00 | 2023-06-27 17:00 | Y | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
BCH | 5CB3 (BCH Selkirk) | 2023-06-27 09:00 | 2023-06-27 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, For Information Only
ALTALINK | 749L (899s Edgerton - 749AL tap), 899s 749X (899s Edgerton) | 2023-06-27 09:30 | 2023-06-27 15:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 320p PS2 (320p Keephills), 320p 2652 (320p Keephills), 320p 2752 (320p Keephills) | 2023-06-27 09:30 | 2023-06-27 15:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK, ATCO | 347s 199E (347s AML Fox Creek), 347s 138kV Bus (347s Fox Creek), 347s 199W (347s AML Fox Creek), 347s 720X (347s AML Fox Creek), 397s 720N (397s Benbow), 720L (347s AML Fox Creek - 397s Benbow), 199L (347s AML Fox Creek - 199AL tap), 199L (347s AML Fox Creek - 741s ATC Fox Creek), 7L199 (347s AML Fox Creek - 741s ATC Fox Creek) | 2023-06-27 15:30 | 2023-07-05 11:00 | N | Y |  | Circuit Breaker, Bus, Line |  | Replace multiple post insulators, replace insulators on multiple switches, replace strain insulators on all 3 lines, install new 138kV LAs. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34), 34.2TR (SS-34), 34B69-16.60 (SS-34), 16B69-16.60 (SS-16) | 2023-06-28 08:00 | 2023-06-28 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | ML1 (D05 - Syncrude Mildred Lake), 72kV B Bus (D05), D05 78 (D05), D05 77 (D05), D05 76 (D05), D05 75 (D05) | 2023-06-28 08:00 | 2023-06-28 18:00 | N | N |  | Line, Bus, Circuit Breaker | SCL-Require an outage on the 72kV "B" Ring Bus @ D05 Substation to change the bus differential relay setting. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2023-06-28 08:30 | 2023-06-28 16:00 | N | N |  | Shunts |  |  | Pre-Condition
BCH | 2CB4 (BCH Nelway) | 2023-06-28 09:00 | 2023-06-28 12:59 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition
BCH | 1L275 (799s Coleman - BCH Natal) | 2023-06-28 09:00 | 2023-06-28 17:00 | N | Y |  | Line | BFPN testing BC maintenance does not affect the Alberta ATC |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 810s 702T (810s Dome Cutbank) | 2023-06-28 09:00 | 2023-06-30 19:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 320p PS2 (320p Keephills), 320p 2752 (320p Keephills), 320p 2652 (320p Keephills) | 2023-06-28 09:30 | 2023-06-28 15:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 650s 652 (650s Hansman Lake) | 2023-06-28 09:30 | 2023-06-28 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 956s 701T (956s Willingdon), 956s 701 (956s Watt Lake) | 2023-06-28 10:00 | 2023-06-30 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | 2L294 (BCH A. A. Lambert - BCH Nelway) | 2023-06-28 12:00 | 2023-06-28 17:00 | N | Y |  | Line | 2L294 (Nelway - A.A. Lambert) |  | Limits ATC, Pre-Condition
BCH | 2CB3 (BCH Nelway) | 2023-06-28 13:00 | 2023-06-28 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition
ATCO | 863s 901T (863s Paintearth) | 2023-06-28 13:00 | 2023-06-30 17:30 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 14.1C (SS-14) | 2023-06-29 08:00 | 2023-06-29 12:00 | N | N |  | Shunts |  |  | For Information Only, Pre-Condition
PACE | YNG1 Youngstown Solar | 2023-06-29 08:00 | 2023-07-29 18:00 | N | Y |  | Unit
ENMAX | 36B138-36BT3 (SS-36) | 2023-06-29 08:00 | 2023-06-29 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 9L29 (946s Oakland - 963s Coyote Lake), 963s 901T (963s Coyote Lake), 963s 901 (963s Coyote Lake), 963s 9L29D1 (963s Coyote Lake), 963s 901TD (963s Coyote Lake) | 2023-06-29 08:30 | 2023-06-30 17:30 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
BCH | 2CB2 (BCH Nelway) | 2023-06-29 09:00 | 2023-06-29 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 21.1C (SS-21) | 2023-06-29 12:00 | 2023-06-29 16:00 | N | N |  | Shunts |  |  | For Information Only, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28B138-28.80 (SS-28), 42s 28 (42s Sarcee) | 2023-06-30 08:00 | 2023-06-30 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 2CB3 (BCH Selkirk) | 2023-06-30 08:00 | 2023-06-30 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L47 (718s Parsons Creek - 848s Ruth Lake), 7L165 (718s Parsons Creek - 933s Tower Road), 718s 701T (718s Parsons Creek), 718s 701 (718s Parsons Creek), 718s 703 (718s Parsons Creek), 848s 702 (848s Ruth Lake) | 2023-06-30 13:01 | 2023-07-13 14:00 | N | N |  | Line, Transformer, Circuit Breaker |  | Completed early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 718s 700D1 (718s Parsons Creek) | 2023-06-30 17:01 | 2023-07-19 17:00 | N | N |  | Switch
EPCOR, ALTALINK | 1059AL (52s East Industrial - 1059L tap), 1059L (38s East Edmonton - 1059AL tap), 1059L (EP 803s Lambton - 1059AL tap), 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial), EP 803s L2404 (EP 803s Lambton), EP 803s L2401 (EP 803s Lambton) | 2023-06-30 17:01 | 2023-07-22 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12.2TR (SS-12), 12B138-833L (SS-12) | 2023-07-01 08:00 | 2023-07-01 12:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-07-01 08:00 | 2023-07-03 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 72kV Bus Major Maintenance (including bus side disconnects) |  | For Information Only
ENMAX | 2.83L (SS-13 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-5 - 2.83L tap), 13B138-2.83 (SS-13), 5B138-2.83 (SS-5) | 2023-07-01 08:00 | 2023-07-02 16:00 | N | N |  | Line, Circuit Breaker |  | Replace pole that was struck by lightning. | For Information Only, Pre-Condition
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12), 12B138-832L (SS-12), 10B138-832 (SS-10) | 2023-07-01 12:01 | 2023-07-01 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 16.63L (SS-16 - SS-36), 16.60L (SS-16 - SS-34), 16.2TR (SS-16), 15.62L (SS-15 - SS-16), 36B69-16.63/36.5TR (SS-36), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16), 16B69-16.63 (SS-16), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34), 36.5TR (SS-36) | 2023-07-03 08:00 | 2023-07-03 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 681s 1152 (681s Bannerman) | 2023-07-03 12:30 | 2023-07-03 16:15 | N | Y |  | Circuit Breaker |  | urgent testing 240kV CT11 suspected of internal arcing at the top inside the cap, need to perform a condition assessment on it. | 240 kV, For Information Only
ALTALINK, TAYLORPP | 256s T1 (256s Harmattan), 256s 2313W (256s Harmattan), 256s 228X (256s Harmattan), 148s AG-EB25A (148s Schantz), 148s AG-EB510B (148s Schantz), 148s AG-EB510C (148s Schantz), 148s AG-EB510D (148s Schantz), 148s T1 (148s Schantz), 148s T2 (148s Schantz), 148s T3 (148s Schantz) | 2023-07-03 12:30 | 2023-07-13 18:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  | Replace switch 256s18. T1 oil reclaim. 256s20, 256s23, 256s10, 256s7 new switch signs required. 256s39 hot switch. 256s228X new counter | Restricts Generation
ALTALINK | 263s T2 (263s Strachan) | 2023-07-03 12:30 | 2023-07-05 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 221s C1 (221s Sunken Lake) | 2023-07-04 07:30 | 2023-07-05 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 869L (163s Amoco Empress - 204s Sandy Point), 204s T1 (204s Sandypoint), 163s 869W (163s Amoco Empress), 204s 869E (204s Sandy Point) | 2023-07-04 08:00 | 2023-07-29 09:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2023-07-04 08:00 | 2023-07-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162.4TR (SS-162) | 2023-07-04 08:00 | 2023-07-04 16:00 | N | N |  | Transformer |  | 162.4TR RPRR Replacement. Repair leak on LTC piping. Check reversing switch. Gas Monitor Maintenance | For Information Only
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16) | 2023-07-04 08:00 | 2023-07-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 32.83L (SS-32 - SS-40), 40B138-32.83 (SS-40), 32B138-32.83 (SS-32) | 2023-07-04 08:00 | 2023-07-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
REDDEER | 194s T2 (194s South Red Deer) | 2023-07-04 08:00 | 2023-07-06 17:30 | N | N |  | Transformer | Salvage CTs, bus will be connected straight across from circuit switcher to T2. CTs are removed permanently. |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-07-04 08:00 | 2023-07-07 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 72kV Bus Major Maintenance (including bus side disconnects and Tie Breaker) |  | For Information Only
ALTALINK, GWPCORP | 603L (138s Windy Flats - 243s Soderglen), 243s 138CB1 (243s Soderglen) | 2023-07-04 09:00 | 2023-07-06 18:00 | N | Y |  | Line, Circuit Breaker | Maint. 603L between Structures #1 - 109 |  | 240 kV, Restricts Generation
BCH | T4 (BCH Natal), 60CB4 (BCH Natal) | 2023-07-04 09:00 | 2023-07-07 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 421s C1 (421s Hays), 421s 30 (421s Hays) | 2023-07-04 10:00 | 2023-07-05 12:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 732s 906 (732s Mitsue) | 2023-07-04 10:00 | 2023-07-05 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L69 (731s Elmworth - 815s Goodfare), 731s 702 (731s Elmworth), 815s 704 (815s Goodfare) | 2023-07-04 10:00 | 2023-07-05 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson) | 2023-07-04 13:00 | 2023-07-06 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 837s 701T (837s Mahihkan), 837s 704 (837s Mahihkan) | 2023-07-04 13:00 | 2023-07-13 13:00 | N | N |  | Transformer, Circuit Breaker |  | Completed early | For Information Only
SUNCOR | 29PL9-15 (29EDD-34 - 29EDD-56), 29EDD-34 29-952-131 (29EDD-34), 29EDD-34 29-952-132 (29EDD-34), 29EDD-56 952-501 (29EDD-56), 29EDD-56 29PS-163 (29EDD-56) | 2023-07-05 06:00 | 2023-07-13 10:00 | N | Y |  | Line, Circuit Breaker, Switch |  | Completed early. July 13,2023 | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 521AL (867s Sundance Blow-Down - 521L tap), 505L (234L tap - 505L tap), 521L2 (505L-521L tap), 867s T1 (867s Sundance Blow-Down) | 2023-07-05 06:30 | 2023-07-05 18:00 | N | N |  | Line, Switch, Transformer |  |  | For Information Only
ALTALINK | 234L (310p Sundance - 505L tap), 234L (133L tap - 505L tap) | 2023-07-05 06:30 | 2023-07-05 18:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 385s 67 (385s Spring Coulee), 225L (225s Magrath - 385s Spring Coulee) | 2023-07-05 07:30 | 2023-07-05 16:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2023-07-05 08:00 | 2023-07-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, GWPCORP | 603L (138s Windy Flats - 243s Soderglen), 243s 138CB1 (243s Soderglen) | 2023-07-05 08:00 | 2023-07-05 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Restricts Generation
ENMAX | 38B138-38.1CAP (SS-38), 38.1C (SS-38) | 2023-07-05 08:00 | 2023-07-05 16:00 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ENMAX | 40.1TR (SS-40) | 2023-07-05 08:00 | 2023-07-06 16:00 | N | N |  | Transformer |  |  | For Information Only
BHE | RTL1 Rattlesnake Ridge Wind | 2023-07-05 09:00 | 2023-07-05 17:00 | N | N |  | Unit
ATCO | 837s 701 (837s Mahihkan), 7L157 (837s Mahihkan - 970s Bourque) | 2023-07-05 10:00 | 2023-07-06 14:30 | N | N |  | Circuit Breaker, Line |  | Outage completed early. | Over/Under Voltage, Pre-Condition
ATCO | 6L12 (774s Monitor - 6L25 tap), 774s 601 (774s Monitor) | 2023-07-05 11:00 | 2023-07-06 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-07-05 23:00 | 2023-07-06 02:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-07-06 02:00 | 2023-07-06 07:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 385s 225 (385s Spring Coulee), 225L (229s Glenwood - 385s Spring Coulee) | 2023-07-06 07:30 | 2023-07-06 16:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 263s C1 (263s Strachan), 263s 35 (263s Strachan) | 2023-07-06 08:00 | 2023-07-06 10:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 162.81L (391s Balzac - SS-162), 162B138-RB80 (SS-162), 162B138-RB81 (SS-162), 162MD138-162.81 (SS-162), 391s 162.81 (391s Balzac) | 2023-07-06 08:00 | 2023-07-06 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 325s C1 (325s Leduc), 325s 1552 (325s Leduc) | 2023-07-06 08:00 | 2023-08-18 18:00 | N | N |  | Shunts, Circuit Breaker |  | Outage extended. Need parts. Get an exact date of return. | For Information Only, Pre-Condition
ENMAX | 40.81L (SS-40 - SS-41), 41B138-40.81 (SS-41), 40B138-40.81 (SS-40) | 2023-07-06 08:00 | 2023-07-06 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 431s C1 (431s Hussar), 431s 152 (431s Hussar) | 2023-07-06 08:00 | 2023-07-06 17:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2023-07-06 08:30 | 2023-07-06 14:30 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2023-07-06 08:30 | 2023-07-06 14:30 | N | Y |  | Line |  |  | 240 kV, For Information Only, Affects Cranking Path
ATCO | 813s 716C (813s Little Smoky), 813s 716 (813s Little Smoky) | 2023-07-06 10:00 | 2023-07-07 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 732s 701 (732s Mitsue) | 2023-07-06 10:00 | 2023-07-07 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ENMAX | 2.80L (SS-2 - SS-23), 23B138-2.80 (SS-23) | 2023-07-06 12:00 | 2023-07-06 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 28.1TR (SS-28) | 2023-07-07 08:00 | 2023-07-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCOP | DFT1 Deerfoot | 2023-07-07 08:00 | 2023-07-21 17:00 | N | Y |  | Unit
JALP, PR | JNR1 Jenner 1 | 2023-07-08 08:00 | 2023-08-31 17:00 | N | N |  | Unit
EPCOR | 816s T2 (816s Petrolia), 816s P2404 (816s Petrolia), 816s P2405 (816s Petrolia), 816s ELSP72 (816s Petrolia), 816s PV-1-1 (816s Petrolia), 816s BESS-1-1 (816s Petrolia) | 2023-07-10 | 2023-07-10 08:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1164L (816s Petrolia - EP Riverview), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia) | 2023-07-10 08:00 | 2023-07-14 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2023-07-10 08:00 | 2023-07-12 16:00 | N | N |  | Transformer |  |  | Firm Load Loss, For Information Only
ENMAX | 32.2TR (SS-32) | 2023-07-10 08:00 | 2023-07-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 65B240-D133 (SS-65) | 2023-07-10 08:00 | 2023-07-10 11:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-07-10 08:00 | 2023-07-16 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) OPTA 635EDD-1021 Substation Major Maintenance |  | For Information Only
ENMAX | 41.1C (SS-41) | 2023-07-10 08:00 | 2023-07-12 09:00 | N | N |  | Shunts |  |  | For Information Only
ENMAX | 43.1TR (SS-43) | 2023-07-10 08:00 | 2023-07-18 16:00 | N | N |  | Transformer |  |  | For Information Only
TRANSALTA | 239s Castle River | 2023-07-10 09:00 | 2023-07-10 17:00 | N | N |  | Station |  |  | Restricts Generation
ATCO | 787s 701T (787s High Prairie), 787s 701 (787s High Prairie) | 2023-07-10 10:00 | 2023-07-14 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | Firm Load Loss, For Information Only
ATCO | 7L90 (813s Little Smoky - 7LA90 tap), 813s 702 (813s Little Smoky), 813s 703 (813s Little Smoky) | 2023-07-10 10:00 | 2023-07-13 09:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake), 811s 707 (811s Clairmont Lake) | 2023-07-10 10:00 | 2023-07-12 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B138-D84 (SS-65) | 2023-07-10 11:00 | 2023-07-10 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 413L (239s Castle River - 632s Russell), 632s 413 (632s Russell) | 2023-07-10 12:30 | 2023-07-10 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ATCO | 7L143 (766s Nevis - 769s Stettler), 766s 703 (766s Nevis) | 2023-07-10 13:00 | 2023-07-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B138-D85 (SS-65) | 2023-07-10 13:00 | 2023-07-10 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 297s S5000 (297s Rimbey) | 2023-07-11 07:00 | 2023-07-12 15:30 | N | N |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
TRANSALTA | 418s Ardenville | 2023-07-11 07:00 | 2023-07-13 18:00 | N | N |  | Station |  |  | Restricts Generation
ATCO | 801s 901T (801s Anderson) | 2023-07-11 07:00 | 2023-07-14 17:00 | N | Y |  | Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 157s C1 (157s Lac La Biche) | 2023-07-11 07:30 | 2023-07-12 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 377s 473C (377s AML Hardisty), 377s 473C102 (377s AML Hardisty) | 2023-07-11 08:30 | 2023-07-12 17:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 14s 739E (14s Devon), 739L (14s Devon - 155s Blackmud), 155s 739 (155s Blackmud) | 2023-07-11 09:30 | 2023-07-11 15:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 244s 3152 (244s Bowmanton) | 2023-07-11 09:30 | 2023-07-11 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 730s 704 (730s Rycroft), 7L68 (730s Rycroft - 811s Clairmont Lake) | 2023-07-11 10:00 | 2023-07-11 17:30 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 225s 225E (225s Magrath), 225L (225s Magrath - 225AL tap) | 2023-07-11 12:00 | 2023-07-11 16:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 244s 3252 (244s Bowmanton) | 2023-07-11 14:00 | 2023-07-11 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 65B240-D135 (SS-65) | 2023-07-12 08:00 | 2023-07-12 11:00 | N | Y |  | Circuit Breaker | HV breaker SF6 Gas Sample - 65B240-D135 |  | 240 kV, Contingency Requires Mitigation
ENMAX | 24.1TR (SS-24) | 2023-07-12 08:00 | 2023-07-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.1C (SS-38), 38B138-38.1CAP (SS-38) | 2023-07-12 09:00 | 2023-07-12 12:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 244s 3752 (244s Bowmanton) | 2023-07-12 10:00 | 2023-07-12 17:00 | N | N |  | Circuit Breaker | 244s3752 First Trip and PRC 5 |  | Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-07-12 10:00 | 2023-07-12 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 65B240-D134 (SS-65) | 2023-07-12 11:00 | 2023-07-12 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 325s T2 (325s Leduc) | 2023-07-12 11:00 | 2023-07-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.1C (SS-31), 31B138-31CAP (SS-31) | 2023-07-12 12:00 | 2023-07-12 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 65B138-D81 (SS-65) | 2023-07-12 13:00 | 2023-07-12 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 803s T1 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton) | 2023-07-13 07:00 | 2023-07-13 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
TRANSALTA | 528s Blue Trail Wind Farm | 2023-07-13 07:00 | 2023-07-15 18:00 | N | N |  | Station |  |  | Restricts Generation
EPCOR | RW2402 (EP Riverview), RW2401 (EP Riverview), 1164L (816s Petrolia - EP Riverview), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia) | 2023-07-13 07:00 | 2023-07-14 17:00 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, For Information Only
ENMAX | 65B138-D82 (SS-65) | 2023-07-13 08:00 | 2023-07-13 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2023-07-13 10:00 | 2023-07-13 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2023-07-13 10:00 | 2023-07-13 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2023-07-13 10:00 | 2023-07-17 14:30 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 65B138-D83 (SS-65) | 2023-07-13 12:00 | 2023-07-13 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
SUNCOR | 29EDD-34 29-952-143 (29EDD-34), 29EDD-34 29-952-133 (29EDD-34), 29EDD-34 29-952-113 (29EDD-34), 29EDD-34 29-952-123 (29EDD-34) | 2023-07-14 06:00 | 2023-07-21 10:37 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 799s 138kV Bus (799s Coleman), 786L (799s Coleman - BCH Natal), 799s T1 (799s Coleman), 799s 786W (799s Coleman), 799s 26 (799s Coleman) | 2023-07-14 07:00 | 2023-07-17 16:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 217s T7 (217s North Red Deer) | 2023-07-14 10:30 | 2023-07-16 17:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 657s SU2402 (657s Summerside) | 2023-07-17 07:00 | 2023-07-20 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s T2 (987s Clover Bar), 987s CC721 (987s Clover Bar) | 2023-07-17 07:00 | 2023-07-27 22:48 | N | Y |  | Transformer, Circuit Breaker |  | Back early | 240 kV, Contingency Requires Mitigation
EPCOR | T3 (Woodcroft), W724 (Woodcroft), W722 (Woodcroft) | 2023-07-17 07:00 | 2023-07-21 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | T3 (Meadowlark) | 2023-07-17 07:00 | 2023-07-28 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | PM2405 (Poundmaker) | 2023-07-17 07:00 | 2023-07-20 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 574s T3 (574s Nilrem), 574s 1752 (574s Nilrem) | 2023-07-17 08:00 | 2023-07-22 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - SS-162) | 2023-07-17 08:00 | 2023-07-23 18:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ENMAX | 21.61L (SS-21 - SS-34), 34B69-21.61 (SS-34), 34.1TR (SS-34), 21B69-21.61 (SS-21), B8-34-1 (SS-34) | 2023-07-17 08:00 | 2023-07-18 16:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 918L (281s Johnson - SS-162) | 2023-07-17 08:00 | 2023-07-23 18:00 | N | Y |  | Line |  |  | 240 kV, Overload, Affects Cranking Path
REDDEER | 247s T2 (247s Piper Creek) | 2023-07-17 08:00 | 2023-07-27 16:00 | N | N |  | Transformer |  |  | For Information Only
TRANSALTA | 1063s Windrise | 2023-07-17 09:00 | 2023-07-17 18:00 | N | N |  | Station |  |  | Restricts Generation
ALTALINK | 753L (65s High River - 253s Blackie), 253s 753W (253s Blackie), 65s 753E (65s High River) | 2023-07-17 09:30 | 2023-07-17 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 787s 702T (787s High Prairie), 787s 702 (787s High Prairie) | 2023-07-17 10:00 | 2023-07-21 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 825s 906 (825s Whitefish Lake) | 2023-07-17 13:00 | 2023-07-19 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson) | 2023-07-17 13:00 | 2023-07-20 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 263s T1 (263s Strachan) | 2023-07-17 13:30 | 2023-07-20 14:30 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-07-18 08:00 | 2023-07-20 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) HT Booster 635EDD-1007 Substation Major Maintenance |  | For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - SS-162) | 2023-07-18 08:00 | 2023-07-18 15:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 5.1TR (SS-5) | 2023-07-18 08:00 | 2023-07-18 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - SS-162) | 2023-07-18 08:00 | 2023-07-18 15:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 7L27 (ATC 793s West Peace River - 834s Wesley Creek), ATC 793s 705 (ATC 793s West Peace River) | 2023-07-18 08:00 | 2023-07-18 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition, Affects Cranking Path
BCH | T2 (BCH Natal), 60CB2 (BCH Natal) | 2023-07-18 09:00 | 2023-07-19 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 275s T2 (275s Jenner), 275s 2252 (275s Jenner), 275s 46 (275s Jenner) | 2023-07-18 09:00 | 2023-07-18 16:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 320p 2852 (320p Keephills) | 2023-07-18 09:30 | 2023-07-18 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 2075s 902T (2075s Newell), 2075s ACF21 (2075s Newell), 2075s ACF22 (2075s Newell), 2075s ACF23 (2075s Newell), 2075s ACF24 (2075s Newell) | 2023-07-18 09:30 | 2023-07-20 08:30 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 903L (17s Benalto - 320p Keephills), 320p 2052 (320p Keephills), 320p 2152 (320p Keephills), 17s 903N (17s Benalto) | 2023-07-18 09:30 | 2023-07-18 15:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 691L (74s Janet - 419s Chestermere) | 2023-07-18 12:00 | 2023-07-18 18:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | ATC 793s 706C (ATC 793s West Peace River) | 2023-07-18 12:01 | 2023-07-18 16:00 | N | N |  | Shunts |  |  | For Information Only
ATCO | 7LA39 (728s Mercer Hill - 7L39 tap), 728s 701T (728s Mercer Hill) | 2023-07-19 05:41 | 2023-07-27 18:00 | N | Y |  | Line, Transformer |  | Back early | Restricts Generation
ALTALINK | 283s 835E (283s Violet Grove), 835L (283s Violet Grove - 835AL tap) | 2023-07-19 07:00 | 2023-07-27 15:00 | N | N |  | Circuit Breaker, Line |  | Returned early | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 6L09 (767s Oyen - 6L21 tap), 767s 601 (767s Oyen) | 2023-07-19 08:00 | 2023-07-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
WCEC | WLC1 Wilson Creek | 2023-07-19 08:00 | 2023-08-04 17:00 | N | N |  | Unit
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.3TR (SS-9), 9B138-2.81 (SS-9), 9B138-9.83 (SS-9), 9MD138-9.3TR (SS-9), 43B138-9.83 (SS-43), 2MD138-2.81 (SS-2) | 2023-07-19 08:00 | 2023-07-19 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 43.2TR (SS-43) | 2023-07-19 08:00 | 2023-07-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21) | 2023-07-19 08:00 | 2023-07-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 320p 2152 (320p Keephills) | 2023-07-19 09:30 | 2023-07-19 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 447s 408N (447s Enchant) | 2023-07-19 10:00 | 2023-07-19 12:00 | N | N |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
ALTALINK | 447s 322X (447s Enchant) | 2023-07-19 13:00 | 2023-07-19 15:00 | N | N |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
ALTALINK | 434L (65s High River - 237s Foothills), 65s 434 (65s High River), 237s 434 (237s Foothills) | 2023-07-20 07:30 | 2023-07-20 17:30 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
REDDEER | 217s T2 (217s North Red Deer) | 2023-07-20 08:00 | 2023-11-17 15:30 | N | N |  | Transformer |  | Extended | For Information Only
ALTALINK | 37s 138kV Bus (37s North Calder), 37s T6 (37s North Calder), 37s T5 (37s North Calder), 37s 4 (37s North Calder) | 2023-07-20 08:00 | 2023-07-20 12:30 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 6.82L (SS-6 - SS-41), 41B138-6.82 (SS-41), 6B138-6.82 (SS-6) | 2023-07-20 08:00 | 2023-07-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 16.63L (SS-16 - SS-36), 36.2TR (SS-36), 36B138-36BT3 (SS-36), 36B69-16.63/36.5TR (SS-36), 36B138-14.83 (SS-36), SW84 (SS-36), 14B138-14.83 (SS-14), 16B69-16.63 (SS-16) | 2023-07-21 08:00 | 2023-07-21 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 1109L (SS-25 - SS-65), 65B240-D134 (SS-65), 65B240-D135 (SS-65) | 2023-07-22 08:00 | 2023-07-23 18:00 | N | Y |  | Line, Circuit Breaker |  | Summer Substation Washing. HV SW Maint. SW139, SW140, 65MD-1109. | 240 kV, Contingency Requires Mitigation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-07-22 08:00 | 2023-07-24 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) HT Booster 635EDD-1008 Substation Major Maintenance |  | For Information Only
ATCO | 790s 701C (790s Poplar Hill) | 2023-07-23 20:19 | 2023-07-27 18:00 | N | N |  | Shunts |  | Back early. | Pre-Condition
SUNCOR | 635PL7-1003 (635EDD-1000 - 635EDD-1004) | 2023-07-24 04:00 | 2023-07-25 17:00 | N | N |  | Line |  |  | For Information Only
SUNCOR | 635PL7-1002 (635EDD-1000 - 635EDD-1004) | 2023-07-24 04:00 | 2023-07-25 17:00 | N | N |  | Line |  |  | For Information Only
EPCOR | 657s SU2401 (657s Summerside) | 2023-07-24 07:00 | 2023-07-26 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | T3 (Namao), 72CN10 (987s Clover Bar - Namao), N723 (Namao), N724 (Namao), NDS11 (Namao), NDS3 (Namao), 987s CN723 (987s Clover Bar) | 2023-07-24 07:00 | 2023-07-28 17:00 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34) | 2023-07-24 08:00 | 2023-07-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5) | 2023-07-24 08:00 | 2023-07-24 12:00 | N | N |  | Line |  |  | Overload, Pre-Condition
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-07-24 09:00 | 2023-07-28 16:00 | N | Y |  | Line |  |  | Limits ATC
ALTALINK | 309s T2 (309s Anthony Henday), 309s 252 (309s Anthony Henday) | 2023-07-24 09:00 | 2023-07-24 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 931s 701T (931s Bohn), 931s 701 (931s Bohn) | 2023-07-24 09:30 | 2023-07-25 19:00 | N | N |  | Terminal Equipment, Circuit Breaker |  |  | For Information Only
ATCO | 757s 605 (757s Battle River), 6L08 (756s Bigfoot - 757s Battle River), 756s Bigfoot | 2023-07-24 09:30 | 2023-07-25 17:30 | N | N |  | Circuit Breaker, Line, Station |  |  | Pre-Condition
ATCO | 813s SVC (813s Little Smoky), 813s 706 (813s Little Smoky), 813s 712 (813s Little Smoky), 813s 719 (813s Little Smoky) | 2023-07-24 10:00 | 2023-07-31 10:42 | N | Y |  | Shunts, Circuit Breaker |  | Back early | Contingency Requires Mitigation, Pre-Condition, Prevents Normal Events
ATCO | 813s 715 (813s Little Smoky), 813s 715C (813s Little Smoky) | 2023-07-24 10:00 | 2023-07-25 16:00 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 901L (63s Red Deer - 901AL tap), 901L (74s Janet - 901AL tap), 901AL (64s East Crossfield - 901L tap), 64s 240kV Bus (64s East Crossfield), 64s T2 (64s East Crossfield), 64s 901 (64s East Crossfield), 64s 30 (64s East Crossfield) | 2023-07-24 10:00 | 2023-08-03 18:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L587 (822s Wolf Lake - 826s Marguerite Lake), 822s 701 (822s Wolf Lake), 826s 7L587D1 (826s Marguerite Lake), 826s 710 (826s Marguerite Lake), 826s 707 (826s Marguerite Lake) | 2023-07-24 10:00 | 2023-07-25 17:00 | N | Y |  | Line, Circuit Breaker, Switch | Work on Breaker 822S 701 Cut over cabling and protection to new panel Commission new protection including teleprotection DTT to 826S |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-07-24 11:00 | 2023-08-11 17:00 | N | Y |  | Line |  |  | Limits ATC
ENMAX | 2.84L (SS-2 - SS-8) | 2023-07-24 12:01 | 2023-07-24 16:00 | N | N |  | Line |  |  | Overload, Pre-Condition
ALTALINK | 63s 852 (63s Red Deer) | 2023-07-24 12:30 | 2023-07-27 17:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 127s T2 (127s Bruderheim) | 2023-07-24 12:30 | 2023-07-27 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 939s 903T (939s Livock), 939s 910 (939s Livock), 939s 911 (939s Livock) | 2023-07-24 13:00 | 2023-08-04 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 325s C1 (325s Leduc) | 2023-07-25 07:30 | 2023-07-25 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 1036L (356s Milo - 554s Travers) | 2023-07-25 08:00 | 2023-07-26 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32) | 2023-07-25 08:00 | 2023-07-25 12:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | ATC 793s 707C (ATC 793s West Peace River) | 2023-07-25 08:00 | 2023-07-25 12:00 | N | N |  | Shunts |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43), 43B138-9.83 (SS-43) | 2023-07-25 08:00 | 2023-07-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.1TR (SS-33) | 2023-07-25 08:00 | 2023-07-27 16:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29EDD-94 29PP-97 260kV Bus (29EDD-94 Voyageur) | 2023-07-25 08:00 | 2023-08-02 18:00 | N | Y |  | Bus | Scope for this outage combined with 1-00404415 (which was scheduled for July 10, 2023, but cancelled) as per request from Suncor on July 7, 2023: "BP -29PP-97 Outage for CBR scope & Asset Tie-ins Perform tie-in and commissioning of CT circuits from 9707 & 9712 CTs to A87-B97 and 87B/50BF-B97 , 29PT-412 to 50BF/25SC-9707 & 9712 and A87-B97 and 87B/50BF-B97, 50BF/25SC-9707 & 9712 to breaker 9701 & 9706, circ mod on 9701 & 9706 & 9707 & 9712" |  | For Information Only
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-07-25 09:00 | 2023-07-28 17:00 | N | Y |  | Line |  |  | For Information Only, Limits ATC
ATCO, ALTALINK | 9L912 (63s Red Deer - 766s Nevis), 9L20 (755s Cordel - 766s Nevis), 7L16 (766s Nevis - 948s Heatburg), 7L143 (766s Nevis - 769s Stettler), 766s 901T (766s Nevis), 766s 701T (766s Nevis), 63s 912E (63s Red Deer), 755s 9L20D1 (755s Cordel), 766s 902 (766s Nevis), 766s 901 (766s Nevis) | 2023-07-25 10:00 | 2023-07-25 11:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ATCO | 710s 702T (710s Vermilion) | 2023-07-25 10:00 | 2023-07-25 17:00 | N | N |  | Transformer | {OUTAGE REASON: Load transfer 5L05 to 5L576 Connect temp CT's 500CT to 500D1} |  | For Information Only
ATCO | 766s 901T (766s Nevis) | 2023-07-25 11:01 | 2023-12-11 10:30 | N | Y |  | Transformer |  |  | Contingency Requires Mitigation, Impacts RAS, Overload, Pre-Condition, Restricts Generation
ATCO | 7L143 (766s Nevis - 769s Stettler), 7L16 (766s Nevis - 948s Heatburg), 766s 703 (766s Nevis), 766s 702 (766s Nevis), 769s 705 (769s Stettler) | 2023-07-25 11:01 | 2023-08-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2023-07-25 13:30 | 2023-07-31 14:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ATCO | 822s 144kV Bus (822s Wolf Lake), 7L574 (822s Wolf Lake - 7L574 tap), 822s 701T (822s Wolf Lake), 822s 702 (822s Wolf Lake), 822s 704 (822s Wolf Lake) | 2023-07-25 16:00 | 2023-09-26 17:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | ML2 (Syncrude Mildred Lake - UE-1 Syncrude Plant 30-2), 72kV A Bus (D05), UE-1 (D05 - UE-1 Syncrude Plant 30-2), D05 71 (D05), D05 73 (D05), D05 75 (D05), D05 75A (D05), D05 79 (D05), D05 80 (D05), LCF (D05), ML4 (D05) | 2023-07-26 08:00 | 2023-07-26 18:00 | N | N |  | Line, Bus, Circuit Breaker, Switch, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 13.2TR (SS-13) | 2023-07-26 08:00 | 2023-07-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 41.84L (SS-41 - SS-54) | 2023-07-26 08:00 | 2023-07-26 12:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 320p 652 (320p Keephills) | 2023-07-26 09:30 | 2023-07-27 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 813s 708 (813s Little Smoky) | 2023-07-26 10:00 | 2023-07-26 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 6L37 (724s Hines Creek - 800s Friedenstal), 6L16 (724s Hines Creek - 861s Eureka River), 800s 601 (800s Friedenstal), 724s 601 (724s Hines Creek) | 2023-07-26 10:00 | 2023-07-26 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2023-07-27 06:00 | 2023-07-27 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T2 (Poundmaker), PM2401 (Poundmaker), PM2405 (Poundmaker) | 2023-07-27 07:00 | 2023-07-28 17:00 | N | Y |  | Transformer, Circuit Breaker |  | Weather delays | 240 kV, Contingency Requires Mitigation
ENMAX | 31.84L (SS-31 - SS-32), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31) | 2023-07-27 08:00 | 2023-07-27 12:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 1.82L (SS-1 - SS-5) | 2023-07-27 08:00 | 2023-07-27 16:00 | N | N |  | Line |  |  | For Information Only
Syncrude | 72kV B Bus (D05), ML1 (D05 - Syncrude Mildred Lake), ML3 (D05 - N11 Syncrude), D05 78 (D05), D05 77 (D05), D05 76 (D05) | 2023-07-27 08:00 | 2023-07-27 18:00 | N | N |  | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 813s 709 (813s Little Smoky) | 2023-07-27 10:00 | 2023-07-27 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 848s 905 (848s Ruth Lake) | 2023-07-27 10:00 | 2023-07-28 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 32B138-32BT5 (SS-32) | 2023-07-27 12:00 | 2023-07-27 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-07-28 08:00 | 2023-07-30 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) FT Booster 635EDD-1010 Substation Major Maintenance |  | For Information Only
ENMAX | 1.84L (SS-1 - SS-5) | 2023-07-28 08:00 | 2023-07-28 16:00 | N | N |  | Line |  |  | For Information Only, Pre-Condition
ENMAX, ALTALINK | 1080L (SS-25 - SS-65), 240kV West Bus (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25B240-D138 (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25) | 2023-07-28 08:00 | 2023-07-28 18:00 | N | Y |  | Line, Bus, Circuit Breaker |  | Summer Substation Washing 25sub 1080PT, D138. Washing required on 240kV West bus insulators by 1080L | 240 kV, Contingency Requires Mitigation
ATCO | 710s 703T (710s Vermilion), 710s 705 (710s Vermilion) | 2023-07-28 10:00 | 2023-07-30 17:00 | N | N |  | Transformer, Circuit Breaker | {OUTAGE REASON: 710S 25kv Bus repair} |  | For Information Only
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), EP 805s J722 (EP 805s Jasper) | 2023-07-29 07:00 | 2023-07-30 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 557s CD2403 (557s Castle Downs) | 2023-07-29 07:00 | 2023-07-30 17:00 | N | Y |  | Circuit Breaker |  | Extended 1 day for parts. | 240 kV, Contingency Requires Mitigation
ENMAX | 12.1TR (SS-12) | 2023-07-29 08:00 | 2023-07-29 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 12.2TR (SS-12) | 2023-07-29 12:01 | 2023-07-29 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton) | 2023-07-31 07:00 | 2023-08-23 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 158s 763X (158s Vauxhall), 763L (158s Vauxhall - 257s Hull), 257s 763 (257s Hull) | 2023-07-31 07:30 | 2023-07-31 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 11.1TR (SS-11) | 2023-07-31 08:00 | 2023-08-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39), 38.1TR (SS-38), 38MD138-38.1TR (SS-38) | 2023-07-31 08:00 | 2023-08-17 19:00 | N | N |  | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ENMAX | 6B138-6.82 (SS-6), 6.82L (SS-6 - SS-41), 41B138-6.82 (SS-41) | 2023-07-31 08:00 | 2023-07-31 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 721s 701T (721s La Corey) | 2023-07-31 09:00 | 2023-08-04 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker) | 2023-07-31 09:30 | 2023-08-04 17:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 749s 705 (749s Flyingshot Lake) | 2023-07-31 10:00 | 2023-07-31 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain), 845s 710 (845s Big Mountain), 845s 709 (845s Big Mountain) | 2023-07-31 10:00 | 2023-08-02 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 834L (320p Keephills - 384s Keystone), 384s 834 (384s Keystone), 320p 834X (320p Keephills) | 2023-07-31 11:00 | 2023-08-03 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 159s T1 (159s Colinton) | 2023-07-31 12:00 | 2023-08-03 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 62s T3 (62s Brazeau Plant), 62s 31 (62s Brazeau Plant) | 2023-07-31 13:30 | 2023-08-03 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 38.1C (SS-38) | 2023-07-31 14:56 | 2024-09-18 10:15 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 158s 763N (158s Vauxhall), 763L (158s Vauxhall - 763AL tap) | 2023-08-01 07:30 | 2023-08-01 12:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.1TR (SS-15) | 2023-08-01 08:00 | 2023-08-01 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26) | 2023-08-01 08:00 | 2023-08-01 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 377s 473C (377s AML Hardisty) | 2023-08-01 08:30 | 2023-09-26 17:00 | N | N |  | Shunts
ATCO | 794s 703 (794s Valleyview), 7L48 (794s Valleyview - 7LA48 tap) | 2023-08-01 10:00 | 2023-08-01 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26B138-26BT3 (SS-26) | 2023-08-01 11:00 | 2023-08-01 13:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 15.2TR (SS-15) | 2023-08-01 12:01 | 2023-08-01 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 158s 821E (158s Vauxhall), 821L (158s Vauxhall - 421s Hays) | 2023-08-01 12:30 | 2023-08-01 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 26B138-26.83 (SS-26) | 2023-08-01 13:00 | 2023-08-01 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-02 08:00 | 2023-08-02 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) FT Booster 635EDD-1009 Substation Major Maintenance |  | For Information Only
Syncrude | 72kV A Bus (D05), D05 71 (D05), D05 71B (D05), D05 73 (D05), D05 73A (D05), D05 73B (D05), D05 75 (D05), D05 75A (D05), D05 75B (D05), D05 79 (D05), D05 79B (D05), D05 80 (D05), D05 80B (D05), UE-1 (D05 - UE-1 Syncrude Plant 30-2) | 2023-08-02 08:00 | 2023-08-02 20:00 | N | N |  | Bus, Circuit Breaker, Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2023-08-02 08:30 | 2023-08-02 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 668L (394s Empress - 562s Cypress) | 2023-08-02 08:30 | 2023-08-02 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 845s 703 (845s Big Mountain) | 2023-08-02 10:00 | 2023-08-04 16:00 | N | N |  | Circuit Breaker
ENMAX | 47B138-BT3 (SS-47) | 2023-08-02 12:00 | 2023-08-02 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10B138-832 (SS-10), 10.1TR (SS-10), 12B138-832L (SS-12) | 2023-08-03 08:00 | 2023-08-03 16:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
SUNCOR | 29EDD-94 29PP-98 260kV Bus (29EDD-94 Voyageur), 29EDD-94 29-952-9703 (29EDD-94 Voyageur), 29EDD-94 29-952-9704 (29EDD-94 Voyageur), 29EDD-94 29-952-9709 (29EDD-94 Voyageur), 29EDD-94 29-952-9710 (29EDD-94 Voyageur), 29EDD-94 29PS-390 (29EDD-94 Voyageur), 29EDD-94 29PS-391 (29EDD-94 Voyageur), 29EDD-94 29PS-633 (29EDD-94 Voyageur), 29EDD-94 29PS-634 (29EDD-94 Voyageur) | 2023-08-03 08:00 | 2023-08-15 18:00 | N | Y |  | Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
VISIONREQ | 354s RTU/SCADA (354s Summerview) | 2023-08-03 10:00 | 2023-08-03 12:00 | N | N |  | Terminal Equipment |  |  | Affects Visibility
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27) | 2023-08-05 08:00 | 2023-08-07 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCOP, CNRL | 838s 75-TR-1701 (838s Horizon Mining) | 2023-08-06 08:00 | 2023-08-06 08:01 | N | Y |  | Transformer |  | Cancelled - neither party was aware of this planned outage. | 240 kV, For Information Only
ALTALINK | 164L (103s Goose Lake - 415s Drywood), 385s 225 (385s Spring Coulee) | 2023-08-07 07:00 | 2023-08-08 16:00 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 92s T1 (92s Viscount) | 2023-08-08 06:00 | 2023-08-08 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B138-RB86 (SS-162) | 2023-08-08 08:00 | 2023-08-08 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 754L (437s Baymag - 742L tap) | 2023-08-08 08:00 | 2023-08-11 17:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 64s T1 (64s East Crossfield) | 2023-08-08 10:00 | 2023-08-10 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 825s 904 (825s Whitefish Lake) | 2023-08-08 10:00 | 2023-08-09 16:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 749s 702T (749s Flyingshot Lake) | 2023-08-08 10:00 | 2023-08-11 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial), 268s 797 (268s Whitecourt), 364s 797 (364s Whitecourt Industrial) | 2023-08-08 11:00 | 2023-08-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 895s T2 (895s Suffield) | 2023-08-08 12:30 | 2023-08-10 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 795s 701T (795s Zama) | 2023-08-08 14:00 | 2023-09-03 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays) | 2023-08-09 07:00 | 2023-08-11 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162B138-RB80 (SS-162) | 2023-08-09 08:00 | 2023-08-09 10:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
Saskpower | SaskPower A1R | 2023-08-09 08:00 | 2023-08-12 19:00 | N | Y |  | Line |  |  | Limits ATC, Pre-Condition
ALTALINK | 178s T1 (178s Cynthia) | 2023-08-09 08:00 | 2023-08-10 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 223L (150s Clyde - 159s Colinton), 150s 223N (150s Clyde), 159s 223 (159s Colinton) | 2023-08-09 08:30 | 2023-08-09 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162B138-RB83 (SS-162) | 2023-08-09 10:00 | 2023-08-09 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 162B138-RB85 (SS-162) | 2023-08-09 13:00 | 2023-08-09 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 385s T1 (385s Spring Coulee), 385s T2 (385s Spring Coulee) | 2023-08-10 07:00 | 2023-10-01 11:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 931L (28s West Brooks - 132s Ware Junction) | 2023-08-10 07:00 | 2023-08-10 18:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ENMAX | 162B138-RB92 (SS-162) | 2023-08-10 08:00 | 2023-08-10 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
Syncrude | Mildred T15 (Syncrude Mildred Lake), 1535 (Syncrude Mildred Lake) | 2023-08-10 08:00 | 2023-09-04 19:00 | N | N |  | Transformer, Circuit Breaker |  | Extended | For Information Only
ALTALINK | 89s 1552 (89s Ellerslie) | 2023-08-10 08:30 | 2023-08-10 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162B138-RB94 (SS-162) | 2023-08-10 12:00 | 2023-08-10 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1075L (28s West Brooks - 132s Ware Junction) | 2023-08-11 07:00 | 2023-08-11 18:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ENMAX | 31.1C (SS-31), 31B138-31CAP (SS-31) | 2023-08-12 08:00 | 2023-08-13 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 170s 152 (170s Pike) | 2023-08-12 09:10 | 2023-08-22 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 29s T2 (29s Cascade) | 2023-08-12 18:00 | 2023-11-28 10:00 | N | N |  | Transformer | Cutover and energize new 177s Switchgear. Close 29s Open Point A & 29s Open Point B. Create 29s Open Point J & 29s Open Point K. Phasing @ N-238L1 & N-16B6137U 2xyz. 177s RSLD4 & 29s RSLD 3 to be issued at the end of the outage. Issue Salvage Clearance on existing 177s switchgear and remove temporary naming of N-16B6137U, N-238L1, & N-105L1. 177s RSLD 5 & 29s RSLD 4 to be issued after switching complete. |  | For Information Only, Pre-Condition
Saskpower | SaskPower P2A | 2023-08-13 06:30 | 2023-08-13 13:00 | N | N |  | Line |  |  | Pre-Condition
EPCOR | 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial) | 2023-08-14 07:00 | 2023-08-14 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 557s CD2406 (557s Castle Downs) | 2023-08-14 07:00 | 2023-08-15 08:20 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
EPCOR | 72NW15 (Namao - Woodcroft), W723 (Woodcroft) | 2023-08-14 07:00 | 2023-08-25 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 510s ACF14 (510s Sunnybrook), 510s 1452 (510s Sunnybrook) | 2023-08-14 07:30 | 2023-08-17 16:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 500 kV, Pre-Condition
SUNCOR | 29EDD-18 29PT-101 (29EDD-18 Firebag) | 2023-08-14 08:00 | 2023-08-23 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 10.1TR (SS-10) | 2023-08-14 08:00 | 2023-08-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary), 2B138-D96 (SS-2), 2B138-D95 (SS-2), 2MD138-2.1CAP (SS-2), MD109 (SS-2), MD110 (SS-2) | 2023-08-14 08:00 | 2023-08-17 16:00 | N | N |  | Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 25B240-D140 (SS-25) | 2023-08-14 08:00 | 2023-08-14 10:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 64s 138kV Bus1 (64s East Crossfield), 901AL (64s East Crossfield - 901L tap), 64s T1 (64s East Crossfield), 64s T2 (64s East Crossfield), 64s 652 (64s East Crossfield), 64s 33 (64s East Crossfield), 64s 34 (64s East Crossfield) | 2023-08-14 09:00 | 2023-08-16 16:35 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  | Done Early | Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation
ATCO | 755s 903 (755s Cordel) | 2023-08-14 09:30 | 2023-08-16 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
ATCO | 796s 702T (796s Nipisi) | 2023-08-14 10:00 | 2023-08-18 16:00 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 25B240-D141 (SS-25) | 2023-08-14 10:00 | 2023-08-14 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 840s McNeill Station, 840s 701T (840s McNeill Station), 840s 901T (840s McNeill Station), 840s 901 (840s McNeill Station), 840s 701 (840s McNeill Station), 840s 702C (840s McNeill Station), 840s 703C (840s McNeill Station) | 2023-08-14 11:00 | 2023-08-18 17:30 | N | Y |  | Station, Transformer, Circuit Breaker, Shunts |  |  | Limits ATC, Pre-Condition
ENMAX | 5.8TR (SS-5) | 2023-08-14 11:00 | 2023-08-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 185L (379s Shell Canada Waterton - 415s Drywood), 379s 69kV Bus B2 (379S Shell Canada Waterton), 379s T2 (379s Shell Canada Waterton), 379s 185E (379s Shell Canada Waterton), 379s 452 (379s Shell Canada Waterton), 379s 289 (379s Shell Canada Waterton) | 2023-08-14 12:00 | 2023-08-19 17:00 | N | N |  | Line, Bus, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake), 40s 858N (40s Wetaskiwin) | 2023-08-14 12:00 | 2023-08-16 08:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 87s T1 (87s Gaetz) | 2023-08-14 13:00 | 2023-08-17 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 25B240-D142 (SS-25) | 2023-08-14 13:00 | 2023-08-14 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 6L03 (757s Battle River - 6L17 tap), 757s 603 (757s Battle River) | 2023-08-14 13:00 | 2023-08-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 62s Brazeau Plant), 61s 202X (61s Lodgepole), 62s 202 (62s Brazeau Plant) | 2023-08-15 07:00 | 2023-08-18 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 123L (19s Wabamun - 352s Onoway), 352s T1 (352s Onoway), 19s 123 (19s Wabamun), 352s 123 (352s Onoway), 352s 1 (352s Onoway) | 2023-08-15 07:00 | 2023-08-15 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, For Information Only
EPCOR | 908AL (52S East Industrial - 908L tap), 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2023-08-15 07:00 | 2023-08-15 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 754L (118s Canmore - 437s Baymag), 118s 754E (118s Canmore) | 2023-08-15 08:00 | 2023-08-17 15:15 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 25B240-D133 (SS-25) | 2023-08-15 08:00 | 2023-08-15 11:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 25B240-D136 (SS-25) | 2023-08-15 11:00 | 2023-08-15 14:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 384s T2 (384s Keystone) | 2023-08-16 06:00 | 2023-08-16 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 816s P2402 (816s Petrolia) | 2023-08-16 07:00 | 2023-08-18 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 13.2TR (SS-13) | 2023-08-16 08:00 | 2023-08-23 16:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29EDD-94 Voyageur | 2023-08-16 08:00 | 2023-08-22 18:00 | N | Y |  | Station |  |  | For Information Only
ENMAX | 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27) | 2023-08-16 08:00 | 2023-08-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 701L (223s Strome - 7LA701 tap) | 2023-08-16 10:00 | 2023-08-16 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 918s 701T (918s Bauer), 918s 701 (918s Bauer) | 2023-08-16 12:00 | 2023-08-18 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 814s T2 (814s Bellamy), BR722 (Rossdale), 814s B2402 (814s Bellamy), 814s B2406 (814s Bellamy) | 2023-08-17 07:00 | 2023-08-17 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 5.1TR (SS-5) | 2023-08-17 08:00 | 2023-08-17 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 1L274 (978s BCH Britt Creek - BCH Greenhills tap) | 2023-08-17 17:19 | 2023-08-24 17:00 | Y | N |  | Line | 1L274 (Britt Creek - 1D4L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
EPCOR | N721 (Namao), N725 (Namao), 72VN21 (EP 511s Victoria - Namao), 72NW15 (Namao - Woodcroft), 72KN23 (Kennedale - Namao) | 2023-08-17 23:00 | 2023-08-18 07:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65.2TR (SS-65), 65B138-D85 (SS-65), 65B138-D82 (SS-65), 65B240-D132 (SS-65), 65B240-D135 (SS-65), 138kV North Bus (SS-65), 240kV North Bus (SS-65) | 2023-08-18 08:00 | 2023-08-18 18:00 | N | Y |  | Transformer, Circuit Breaker, Bus |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
Syncrude | ML1 (D05 - Syncrude Mildred Lake), 915 (Syncrude Mildred Lake), D05 76 (D05) | 2023-08-19 08:00 | 2023-08-19 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 6.4TR (SS-6) | 2023-08-19 08:00 | 2023-08-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 526BL (659s Pegasus Lake - 526L tap), 526L (519L tap - 526BL tap), 659s Pegasus Lake, 659s 526B (659s Pegasus Lake), 659s T1 (659s Pegasus Lake), 659s T2 (659s Pegasus Lake), 659s 189 (659s Pegasus Lake), 659s 389 (659s Pegasus Lake) | 2023-08-19 09:00 | 2023-08-19 18:00 | N | Y |  | Line, Station, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 659s 526B (659s Pegasus Lake), 659s T1 (659s Pegasus Lake), 659s T2 (659s Pegasus Lake) | 2023-08-19 18:01 | 2023-08-26 08:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 199L (268s Whitecourt - 199AL tap), 268s 199N (268s Whitecourt) | 2023-08-20 06:00 | 2023-08-25 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 29PL9-17 (29EDD-1 Millennium - 29EDD-94 Voyageur), 29EDD-1 952-104 (29EDD-1 Millennium), 29EDD-1 952-105 (29EDD-1 Millennium), 29EDD-1 29PS-410 (29EDD-1 Millennium), 29EDD-94 29-952-9706 (29EDD-94 Voyageur), 29EDD-94 29-952-9705 (29EDD-94 Voyageur), 29EDD-94 29PS-395 (29EDD-94 Voyageur), 29EDD-94 29PS-394 (29EDD-94 Voyageur), 29EDD-94 29PS-398 (29EDD-94 Voyageur) | 2023-08-20 08:00 | 2023-08-25 23:59 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
Syncrude | Mildred T18 (Syncrude Mildred Lake) | 2023-08-20 08:00 | 2023-09-03 18:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | Mildred T17 (Syncrude Mildred Lake) | 2023-08-20 08:00 | 2023-09-03 18:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-20 08:00 | 2023-08-21 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
EPCOR | 657s T1 (657s Summerside) | 2023-08-21 07:00 | 2023-08-21 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 987s T1 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s CDS25 (987s Cloverbar) | 2023-08-21 07:00 | 2023-08-24 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 983AL (1019s Woolchester - 983L tap), 983L (244s Bowmanton - 983L tap), 983L (251s Whitla - 983L tap) | 2023-08-21 07:00 | 2023-08-25 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 24.82L (SS-24 - SS-65), 65B138-D81 (SS-65), 65B138-D82 (SS-65), 65MD138-24.82 (SS-65) | 2023-08-21 08:00 | 2023-08-22 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload
Syncrude | Mildred T4 (Syncrude Mildred Lake) | 2023-08-21 08:00 | 2023-09-04 18:00 | N | N |  | Transformer |  | Extended | For Information Only, Restricts Generation
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2023-08-21 08:00 | 2023-09-04 18:00 | N | N |  | Transformer |  | Extended | For Information Only, Restricts Generation
ENMAX | 34.1TR (SS-34) | 2023-08-21 08:00 | 2023-08-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 813s 709 (813s Little Smoky) | 2023-08-21 09:00 | 2023-08-21 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 754L (245s Seebe - 742L tap), 245s 754W (245s Seebe) | 2023-08-21 09:00 | 2023-08-21 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 557s CD2401 (557s Castle Downs), 557s CD2403 (557s Castle Downs), 557s CDDS13 (557s Castle Downs) | 2023-08-21 09:30 | 2023-08-28 15:35 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 796s 701T (796s Nipisi) | 2023-08-21 10:00 | 2023-08-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 825s 908C (825s Whitefish Lake), 825s 908R (825s Whitefish Lake) | 2023-08-21 10:00 | 2023-08-25 17:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 38s T2 (38s East Edmonton) | 2023-08-21 12:30 | 2023-08-22 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 575s T2 (575s Sundre) | 2023-08-21 13:00 | 2023-08-31 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 103s T1 (103s Goose Lake) | 2023-08-21 13:00 | 2023-08-23 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 379s 69kV Bus B1 (379S Shell Canada Waterton), 185L (379s Shell Canada Waterton - 396s Pincher Creek), 379s T1 (379s Shell Canada Waterton), 379s 185N (379s Shell Canada Waterton), 379s 352 (379s Shell Canada Waterton), 396s 185 (396s Pincher Creek) | 2023-08-21 13:00 | 2023-08-25 17:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 754L (245s Seebe - 742L tap), 245s 754W (245s Seebe) | 2023-08-21 13:01 | 2023-08-29 13:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 102s 6552 (102s Langdon) | 2023-08-21 23:00 | 2023-08-24 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK, Lethbridge | 734L (241s Uplands - 370s North Lethbridge), 370s 734X (370s North Lethbridge) | 2023-08-22 06:30 | 2023-08-22 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Mildred T5 (Syncrude Mildred Lake) | 2023-08-22 08:00 | 2023-09-03 18:00 | N | N |  | Transformer |  |  | Restricts Generation
ALTALINK | 935L (324s Cassils - 356s Milo) | 2023-08-22 08:00 | 2023-08-24 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 2MD138-833L (SS-2), 833L (SS-2 - SS-12) | 2023-08-22 08:00 | 2023-08-22 12:00 | N | Y |  | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-22 08:00 | 2023-08-23 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
Syncrude | Mildred Lake 72kV Bus A (Sycrude Mildred Lake), ML2 (Syncrude Mildred Lake - UE-1 Syncrude Plant 30-2) | 2023-08-22 08:00 | 2023-09-03 18:00 | N | N |  | Bus, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 170s T1 (170s Pike) | 2023-08-22 08:30 | 2023-08-24 13:30 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
BCH | 5L92 (BCH Cranbrook - BCH Selkirk), 5CB3 (BCH Selkirk), 5CB4 (BCH Selkirk) | 2023-08-22 09:00 | 2023-08-23 07:59 | Y | Y |  | Line, Circuit Breaker | 5L92 (Cranbrook - Selkirk) |  | Limits ATC, 500 kV
IMPERIALOIL, ATCO | 7L161 (909s Mahno - 942s Nabiye), 7L105 (837s Mahihkan - 909s Mahno), 837s 702 (837s Mahihkan), 942s Nabiye, 909s MAHNO | 2023-08-22 09:00 | 2023-09-06 17:00 | N | Y |  | Line, Circuit Breaker, Station | {OUTAGE REASON: RTXP switch replacements for 7L105} |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK, BHE Canada | 120s 152 (120s Picture Butte) | 2023-08-22 10:30 | 2023-08-22 14:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 35.81L (42s Sarcee - SS-35) | 2023-08-22 12:00 | 2023-08-22 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1058L (657s Summerside - EP 803s Lambton), 657s SUDS10 (657s Summerside), 657s SU2403 (657s Summerside), 657s SU2404 (657s Summerside), EP 803s L2403 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton) | 2023-08-23 07:00 | 2023-08-23 17:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L92 (BCH Cranbrook - BCH Selkirk) | 2023-08-23 08:00 | 2023-08-29 20:00 | Y | Y |  | Line | 5L92 (Cranbrook - Selkirk) |  | Limits ATC, 500 kV
WPHL | ERV4 Nilrem Battery Generator Test (2309L) | 2023-08-23 08:00 | 2023-08-24 17:00 | N | N |  | Unit
ATCO | 6L12 (774s Monitor - 6L25 tap), 6L25 (773s Coronation - 6L12 tap), 773s 601TD (773s Coronation), 775s 602 (775s Sullivan Lake) | 2023-08-23 08:00 | 2023-08-23 17:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | For Information Only, Pre-Condition
WPHL | ERV6 Nilrem Battery Generator Test (2035L) | 2023-08-23 08:00 | 2023-08-24 17:00 | N | N |  | Unit
ENMAX, ALTALINK | 932L (74s Janet - SS-162) | 2023-08-23 08:00 | 2023-08-23 15:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 26.83L (SS-26 - SS-65), 26B138-26.81 (SS-26), 65B138-D84 (SS-65), 65B138-D85 (SS-65) | 2023-08-23 08:00 | 2023-08-24 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 38s T3 (38s East Edmonton) | 2023-08-23 08:00 | 2023-08-23 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 83s C1 (83s Taber), 83s C2 (83s Taber) | 2023-08-23 08:30 | 2023-08-23 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 813s 719 (813s Little Smoky), 813s SVC (813s Little Smoky) | 2023-08-23 10:00 | 2023-08-24 16:00 | N | Y |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-08-23 12:00 | 2023-08-24 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-08-24 03:00 | 2023-08-24 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
EPCOR, ALTALINK | 330p 807 (330p Genesee), 430L (330P Genesee - 510S Sunnybrook) | 2023-08-24 07:00 | 2023-09-05 17:00 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only, Pre-Condition
ATCO | 7L24 (846s Grand Centre - 7LA24 tap) | 2023-08-24 08:00 | 2023-08-24 14:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-24 08:00 | 2023-08-25 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance (including Tie Breaker) |  | For Information Only
ENMAX | 11.82L (SS-11 - SS-14), 11B138-11.82 (SS-11) | 2023-08-24 08:00 | 2023-08-24 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 616L (59s Peigan - 616AL tap), 59s 616 (59s Peigan) | 2023-08-24 09:30 | 2023-08-24 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX, ALTALINK | 162.81L (391s Balzac - SS-162), 391s 162.81 (391s Balzac), 162B138-RB81 (SS-162), 162B138-RB80 (SS-162), 162MD138-162.81 (SS-162) | 2023-08-25 08:00 | 2023-08-25 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
SUNCOR | 29PL9-16 (29EDD-1 Millennium - 29EDD-94 Voyageur), 29EDD-1 952-101 (29EDD-1 Millennium), 29EDD-1 952-102 (29EDD-1 Millennium), 29EDD-94 29-952-9701 (29EDD-94 Voyageur), 29EDD-94 29-952-9702 (29EDD-94 Voyageur), 29EDD-1 29PS-409 (29EDD-1 Millennium), 29EDD-94 29PS-397 (29EDD-94 Voyageur), 29EDD-94 29PP-97 260kV Bus (29EDD-94 Voyageur), 29EDD-94 29-952-9706 (29EDD-94 Voyageur) | 2023-08-25 08:00 | 2023-09-01 18:00 | N | Y |  | Line, Circuit Breaker, Switch, Bus |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 501L (426s Coalspur - 501CL tap), 426s 501W (426s Coalspur) | 2023-08-25 09:30 | 2023-08-25 16:30 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
BCH | 1L274 (978s BCH Britt Creek - BCH Greenhills tap) | 2023-08-25 14:00 | 2023-08-27 18:00 | Y | N |  | Line | 1L274 (Britt Creek - 1D4L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-26 08:00 | 2023-08-27 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
ALTALINK | 659s Pegasus Lake, 526BL (659s Pegasus Lake - 526L tap), 526L (519L tap - 526BL tap), 659s T1 (659s Pegasus Lake), 659s T2 (659s Pegasus Lake), 659s 526B (659s Pegasus Lake) | 2023-08-26 09:00 | 2023-08-26 18:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 8L10 (330P Genesee - Fording Coal Mine), 330p 808 (330p Genesee) | 2023-08-27 07:00 | 2023-09-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 92s 792 (92s Viscount), 191s 792X (191s N.W. Cardiff) | 2023-08-28 06:00 | 2023-08-30 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2023-08-28 07:00 | 2023-08-28 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 72DS26 (665s Dome - Strathcona), 665s D721 (665s Dome), S721 (Strathcona), SDS3 (Strathcona) | 2023-08-28 07:00 | 2023-08-31 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 15.2TR (SS-15), 15MD69-15.2TR (SS-15) | 2023-08-28 08:00 | 2023-08-31 16:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 746s T1 (746s Sherwood Park) | 2023-08-28 08:00 | 2023-09-06 15:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-28 08:00 | 2023-08-29 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance (including Tie Breaker) |  | For Information Only
ENMAX | 1.8TR (SS-1) | 2023-08-28 08:00 | 2023-08-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 6.4TR (SS-6) | 2023-08-28 08:00 | 2023-09-05 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 710s 703T (710s Vermilion), 710s 705 (710s Vermilion) | 2023-08-28 09:30 | 2023-09-01 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 725L (111s Coalbanks - 725AL tap), 725L (674s Bowron - 725AL tap), 725AL (618s Riverbend - 725L tap), 618s 725 (618s Riverbend) | 2023-08-28 11:00 | 2023-08-31 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 58s T2 (58s Edson) | 2023-08-28 12:00 | 2023-08-31 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-08-28 12:00 | 2023-08-31 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 959s 701 (959s Lanfine) | 2023-08-28 13:00 | 2023-08-28 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2404 (987s Clover Bar), 987s CDS28 (987s Cloverbar) | 2023-08-29 07:00 | 2023-08-29 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Affects Cranking Path
ALTALINK | 502s T1 (502s Shell Waterton (#2)), 502s T2 (502s Shell Waterton (#2)) | 2023-08-29 08:00 | 2023-09-07 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCOP, CNRL | 838s 75-TR-2801 (838s Horizon Mining) | 2023-08-29 08:00 | 2023-09-02 16:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ATCO | 725s 701T (725s Goose River) | 2023-08-29 08:00 | 2023-08-30 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCOP, CNRL | 838s 75-TR-2801 (838s Horizon Mining) | 2023-08-29 08:35 | 2023-09-02 18:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 151s 244E (151s Strathmore) | 2023-08-29 09:00 | 2023-08-29 11:00 | N | N |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
ATCO | 959s 702 (959s Lanfine) | 2023-08-29 09:00 | 2023-08-29 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
BCH | 1L274 (BCH Elkford tap - BCH Line Creek tap) | 2023-08-29 10:00 | 2023-08-29 18:00 | N | N |  | Line | EFD 1D1 repair EFD 25D151 hotspot repair EFT 1D21 investigate/repair 1L274 (887L) will be sectionized at EFT 1D21. Thus loads of EFD, GRH and FRO will be fed by AltaLink. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.3TR (SS-13) | 2023-08-29 12:00 | 2023-08-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 804s 701 (804s Wintering Hills), 802s 706 (802s Michichi Creek) | 2023-08-29 13:00 | 2023-09-01 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 959s 703 (959s Lanfine) | 2023-08-29 13:00 | 2023-08-29 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 754L (245s Seebe - 742L tap), 245s 754W (245s Seebe) | 2023-08-29 13:01 | 2023-08-29 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2023-08-29 23:00 | 2023-08-31 07:00 | N | N |  | Switch |  |  | Restricts Generation
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-08-30 07:00 | 2023-08-31 07:00 | N | Y |  | Switch |  |  | Restricts Generation
EPCOR | W722 (Woodcroft) | 2023-08-30 07:00 | 2023-09-01 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2023-08-30 08:00 | 2023-10-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2023-08-30 08:00 | 2023-09-02 08:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-08-30 08:00 | 2023-08-31 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
ALTALINK | 395s T1 (395s North Holden) | 2023-08-30 09:00 | 2023-08-30 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 959s 706 (959s Lanfine) | 2023-08-30 09:00 | 2023-08-30 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 959S 722C (959S Lanfine) | 2023-08-30 13:00 | 2023-08-30 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel), 930s 702T (930s Arcenciel), 930s 719 (930s Arcenciel), 930s 406 (930s Arcenciel), 930s 407 (930s Arcenciel) | 2023-08-30 15:30 | 2023-09-01 09:29 | N | Y |  | Shunts, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2023-08-31 07:00 | 2023-08-31 17:00 | N | Y |  | Line |  |  | 240 kV, For Information Only
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar), 987s C2403 (987s Clover Bar), 987s C2405 (987s Clover Bar), 38s 915N (38s East Edmonton), 987s CDS36 (987s Cloverbar) | 2023-08-31 07:00 | 2023-08-31 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 502s T3 (502s Shell Waterton (#2)) | 2023-08-31 07:30 | 2023-08-31 17:30 | N | N |  | Transformer |  |  | For Information Only
BCH | 5RXN5 (BCH Cranbrook) | 2023-08-31 08:00 | 2023-09-05 18:00 | N | Y |  | Shunts |  |  | 500 kV
ATCO | 959S 723C (959S Lanfine) | 2023-08-31 09:00 | 2023-08-31 13:00 | N | N |  | Shunts |  |  | Pre-Condition
BCH | 5L92 (BCH Cranbrook - BCH Selkirk) | 2023-08-31 09:00 | 2023-08-31 17:00 | Y | Y |  | Line | 5L92 (Cranbrook - Selkirk) |  | Limits ATC, 500 kV
ATCO | 959s 906 (959s Lanfine) | 2023-08-31 13:00 | 2023-08-31 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde), 191s 792N (191s N.W. Cardiff) | 2023-09-01 06:00 | 2023-09-09 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 838L (14s Devon - 325s Leduc), 14s 838X (14s Devon), 325s 838 (325s Leduc) | 2023-09-01 06:00 | 2023-09-03 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 987s GB1B (987s Clover Bar) | 2023-09-01 07:00 | 2023-09-01 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
EPCOR | T4 (Rossdale) | 2023-09-01 07:00 | 2023-09-02 17:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-09-01 08:00 | 2023-09-02 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance (including Tie Breaker) |  | For Information Only
ATCO | 959s 919 (959s Lanfine) | 2023-09-01 09:00 | 2023-09-01 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2023-09-01 09:30 | 2023-09-06 16:15 | N | Y |  | Shunts |  |  | Pre-Condition
ATCO | 959s 920 (959s Lanfine) | 2023-09-01 13:00 | 2023-09-01 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
SUNCOR | 635EDD-1000 635PT-1001 (635EDD-1000), 635PL9-1001 (2005s Secord - 635EDD-1000) | 2023-09-02 08:00 | 2023-09-03 17:00 | N | Y |  | Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13.3TR (SS-13), 13B138-2.83 (SS-13), 13B138-3.84 (SS-13), 3B138-3.84 (SS-3), 13MD138-13.3TR (SS-13) | 2023-09-02 08:00 | 2023-09-03 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.1TR (SS-9) | 2023-09-02 08:00 | 2023-09-03 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.1TR (SS-13) | 2023-09-02 08:00 | 2023-11-17 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK, ENEL | 205s T1 (205s Castle Rock Ridge), 205s 89T1 (205s Castle Rock Ridge) | 2023-09-02 21:23 | 2023-09-15 14:00 | N | Y |  | Transformer, Switch |  |  | 240 kV, Restricts Generation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-09-03 08:00 | 2023-09-04 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
ENMAX | 1.82L (SS-1 - SS-5) | 2023-09-03 18:00 | 2023-10-26 16:00 | N | N |  | Line |  |  | Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36.2TR (SS-36), 36B138-14.83 (SS-36), 36B138-36BT3 (SS-36), 36B69-16.63/36.5TR (SS-36), 36MD138-36.5TR (SS-36), 36MD138-36.2TR (SS-36) | 2023-09-04 08:00 | 2023-09-04 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 665s D2401 (665s Dome), 665s D2404 (665s Dome), 665s T3 (665s Dome), 665s DDS13 (665s Dome) | 2023-09-05 07:00 | 2023-09-08 17:00 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | 240 kV, Creates Radial Feeds, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 814s T1 (814s Bellamy), BR721 (Rossdale), VHBB1 (Rossdale), RR723 (Rossdale), RV722 (Rossdale), 72RV6 (EP 511s Victoria - Rossdale) | 2023-09-05 07:00 | 2023-09-09 17:00 | N | N |  | Transformer, Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek), 379s 185N (379s Shell Canada Waterton), 396s 185 (396s Pincher Creek) | 2023-09-05 07:00 | 2023-09-15 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
REDDEER | 194s T1 (194s South Red Deer) | 2023-09-05 08:00 | 2023-09-07 17:00 | N | N |  | Transformer |  | Back early | For Information Only
ENMAX | 15.1TR (SS-15) | 2023-09-05 08:00 | 2023-09-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9) | 2023-09-05 08:00 | 2023-09-05 18:00 | N | N |  | Line, Transformer |  |  | For Information Only
ENMAX | 28.2TR (SS-28) | 2023-09-05 08:00 | 2023-09-07 16:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29EDD-1 260kV North Bus 2 (29EDD-1 Millennium), 29EDD-1 29EDD1s752 (29EDD-1 Millennium), 29EDD-1 29EDD1s952 (29EDD-1 Millennium), 29EDD-1 72kV North Bus (29EDD-1 Millennium), 29EDD-1 29EDD1s1152 (29EDD-1 Millennium), 29EDD-1 29EDD1s1552 (29EDD-1 Millennium), 29EDD-1 T2 (29EDD-1 Millennium) | 2023-09-05 08:00 | 2023-09-26 18:00 | N | Y |  | Bus, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-09-05 08:00 | 2023-09-06 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance (including Tie Breaker) |  | For Information Only
ENMAX | 33.2TR (SS-33) | 2023-09-05 08:00 | 2023-09-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 795s 702T (795s Zama) | 2023-09-05 09:00 | 2023-10-17 10:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2023-09-05 09:00 | 2023-09-07 17:00 | Y | Y |  | Line |  |  | Limits ATC, 500 kV
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2023-09-05 09:15 | 2023-09-08 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 710s 703 (710s Vermilion), 7L65 (710s Vermilion - 7LA65 tap) | 2023-09-05 09:30 | 2023-09-05 13:00 | N | Y |  | Circuit Breaker, Line |  |  | Overload, Pre-Condition, Restricts Generation
ATCO | 757s 710 (757s Battle River) | 2023-09-05 09:30 | 2023-09-06 17:30 | N | N |  | Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 2029s 1204 (2029s Heathfield), 2029s ACF11 (2029s Heathfield), 2029s ACF12 (2029s Heathfield), 2029s ACF13 (2029s Heathfield), 2029s ACF14 (2029s Heathfield) | 2023-09-05 09:30 | 2023-09-05 17:30 | N | Y |  | Circuit Breaker, Shunts |  |  | 500 kV, For Information Only
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2023-09-05 10:00 | 2023-09-11 17:30 | N | Y |  | Line |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 89s Ellerslie 240kV Bus 1, 89s T1 (89s Ellerslie), 89s 1352 (89s Ellerslie) | 2023-09-05 12:00 | 2023-09-05 18:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | 240 kV, 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-09-05 12:00 | 2023-09-07 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 394s T3 (394s Empress), 394s 36 (394s Empress) | 2023-09-05 12:30 | 2023-09-05 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 710s 704 (710s Vermilion), 7L129 (710s Vermilion - 7LA129 tap) | 2023-09-05 13:00 | 2023-09-05 17:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2023-09-05 13:00 | 2023-09-08 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 745L (602s Cold Creek - 745AL tap) | 2023-09-06 07:00 | 2023-09-07 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK, EPCOR | 71s 921X (71s Lamoureux), 921L (71s Lamoureux - 987s Clover Bar) | 2023-09-06 07:00 | 2023-10-18 17:00 | N | Y |  | Switch, Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 276s T3 (276s Union Carbide Prentiss) | 2023-09-06 07:00 | 2023-09-06 23:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar), 987s CDS31 (987s Clover Bar), 987s T2 (987s Clover Bar), 987s C2404 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s C2408 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s T4 (987s Clover Bar) | 2023-09-06 07:00 | 2023-10-18 17:00 | N | Y |  | Line, Switch, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
SUNCOR | 139s Hillridge | 2023-09-06 08:00 | 2023-09-07 13:00 | N | N |  | Station |  |  | For Information Only
ENMAX | 21.61L (SS-21 - SS-34), 34.1TR (SS-34) | 2023-09-06 08:00 | 2023-09-06 12:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 253s Blackie, 753L (65s High River - 253s Blackie), 851L (253s Blackie - 525s Carseland), 876L (179s Gleichen - 253s Blackie), 253s 753W (253s Blackie), 253s 851W (253s Blackie), 253s 876 (253s Blackie) | 2023-09-06 08:00 | 2023-09-19 15:00 | N | Y |  | Station, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood), 54s 694 (54s Fort Saskatchewan) | 2023-09-06 09:00 | 2023-09-06 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2029s ACF11 (2029s Heathfield), 2029s 1218 (2029s Heathfield) | 2023-09-06 09:30 | 2023-09-06 17:30 | N | Y |  | Shunts, Switch |  |  | 500 kV, Pre-Condition
ALTALINK | 37s 82 (37s North Calder) | 2023-09-06 09:30 | 2023-09-07 17:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 11.1TR (SS-11) | 2023-09-06 11:00 | 2023-09-06 16:04 | N | N |  | Transformer
ALTALINK | 275s 35 (275s Jenner), 275s T1 (275s Jenner) | 2023-09-06 12:00 | 2023-09-07 16:00 | N | Y |  | Switch, Transformer |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34), 34.2TR (SS-34) | 2023-09-06 12:00 | 2023-09-06 18:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s GT2 (987s Clover Bar) | 2023-09-07 02:00 | 2023-09-09 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 254s 413E (254s Coaldale) | 2023-09-07 07:30 | 2023-09-07 12:30 | N | N |  | Circuit Breaker |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-09-07 08:00 | 2023-09-08 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.3TR (SS-9), 9.2TR (SS-9), 9B138-9.83 (SS-9), 9B138-2.81 (SS-9), 43B138-9.83 (SS-43), 9MD138-9.2TR (SS-9), 9MD138-9.3TR (SS-9), SW83 (SS-9), SW84 (SS-9), 2MD138-2.81 (SS-2) | 2023-09-07 08:00 | 2023-09-07 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 834L (320p Keephills - 384s Keystone), 320p 834X (320p Keephills), 384s 834 (384s Keystone) | 2023-09-07 08:30 | 2023-09-07 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 2029s ACF12 (2029s Heathfield), 2029s 1219 (2029s Heathfield) | 2023-09-07 09:30 | 2023-09-07 17:30 | N | Y |  | Shunts, Switch |  |  | 500 kV, Pre-Condition
ALTALINK | 254s 414W (254s Coaldale) | 2023-09-07 12:30 | 2023-09-07 16:00 | N | N |  | Circuit Breaker | Transmission constraint record created |  | Restricts Generation
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake), 29EDD-1 260kV North Bus 1 (29EDD-1 Millennium), 29EDD-1 29EDD1s752 (29EDD-1 Millennium), 29EDD-1 29EDD1s152 (29EDD-1 Millennium), 29EDD-1 29EDD1s252 (29EDD-1 Millennium), 29EDD-1 29EDD1s452 (29EDD-1 Millennium), 29EDD-1 29EDD1s552 (29EDD-1 Millennium), 29EDD-1 952-101 (29EDD-1 Millennium), 29EDD-1 952-104 (29EDD-1 Millennium), 29EDD-1 29EDD1SPL9-1 (29EDD-1 Millennium), 29EDD-1 29EDD1SPL9-2 (29EDD-1 Millennium) | 2023-09-08 06:00 | 2023-09-29 18:00 | N | Y |  | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 14.83L (SS-14 - SS-36), 14.2TR (SS-14), 14.4TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14B138-14.83 (SS-14), 14MD138-14.2TR (SS-14), 14MD138-14.4TR (SS-14), SW84 (SS-14), SW87 (SS-14) | 2023-09-08 08:00 | 2023-09-08 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 848s 903 (848s Ruth Lake), 848s 906 (848s Ruth Lake) | 2023-09-08 09:30 | 2024-03-14 17:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO, SUNCOR | 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake) | 2023-09-08 09:30 | 2023-11-20 07:59 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 2029s ACF13 (2029s Heathfield), 2029s 1220 (2029s Heathfield) | 2023-09-08 09:30 | 2023-09-08 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 500 kV
ENMAX, ALTALINK | 7.84L (SS-7 - SS-36), 36.81L (44s Bearspaw Plant - SS-36), 36.3TR (SS-36), 36.1TR (SS-36), 36B138-36.81 (SS-36), 36B138-36BT3 (SS-36) | 2023-09-09 08:00 | 2023-09-09 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-09-09 08:00 | 2023-09-10 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance (including Tie Breaker) |  | For Information Only
ALTALINK | 610L (83s Taber - 336s Fincastle), 336s 610 (336s Fincastle), 83s 610 (83s Taber) | 2023-09-09 08:00 | 2023-09-11 09:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 29EDD-85 29PS-320 (29EDD-85) | 2023-09-09 08:00 | 2023-09-16 18:00 | N | N |  | Switch |  |  | For Information Only
ALTALINK | 673L (131s Moon Lake - 283s Violet Grove), 283s 673 (283s Violet Grove) | 2023-09-10 06:30 | 2023-09-11 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 29EDD-63 30-252-11301 (29EDD-63) | 2023-09-10 08:00 | 2023-09-28 18:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ENMAX | 38.83L (SS-38 - SS-39), 38.1TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 38B138-38.1CAP (SS-38), 38B138-38.83 (SS-38) | 2023-09-10 08:00 | 2023-09-10 12:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.1TR (SS-38) | 2023-09-10 14:54 | 2023-09-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker), PM2403 (Poundmaker), PM2404 (Poundmaker) | 2023-09-11 07:00 | 2023-09-13 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Overload, Pre-Condition, Prevents Normal Events, Affects Cranking Path
EPCOR | 665s D2401 (665s Dome), 665s D2402 (665s Dome), 665s T1 (665s Dome) | 2023-09-11 07:00 | 2023-09-14 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 803s T1 (EP 803s Lambton), EP 803s L2401 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton) | 2023-09-11 07:00 | 2023-09-15 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s CC13 (987s Clover Bar) | 2023-09-11 07:00 | 2023-09-11 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), AML 511s 4952 (AML 511s Crossings), AML 511s 4852 (AML 511s Crossings), 510s 2652 (510s Sunnybrook), 510s 2752 (510s Sunnybrook) | 2023-09-11 07:00 | 2023-09-16 09:32 | N | Y |  | Line, Circuit Breaker |  | back early | 500 kV, Pre-Condition
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 146s 667 (146s Macdonald), 370s 667 (370s North Lethbridge) | 2023-09-11 08:00 | 2023-09-25 10:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2023-09-11 08:00 | 2023-09-12 17:00 | N | N |  | Not In Model | Unmodeled Transmission Facility (Suncor) 35kV GIS Bus Major Maintenance |  | For Information Only
ENMAX | 65B138-D81 (SS-65) | 2023-09-11 08:00 | 2023-09-12 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 15.1TR (SS-15) | 2023-09-11 08:00 | 2023-09-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.60L (SS-15 - SS-21), 21.61L (SS-21 - SS-34), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21B69-21.61 (SS-21), 21B69-15.60 (SS-21) | 2023-09-11 08:00 | 2023-09-11 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 194s T2 (194s South Red Deer) | 2023-09-11 08:00 | 2023-09-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 746s T2 (746s Sherwood Park) | 2023-09-11 08:00 | 2023-09-20 15:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 730s 702T (730s Rycroft), 730s STATCOM (730s Rycroft), 730s 705 (730s Rycroft) | 2023-09-11 09:00 | 2023-09-11 17:30 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 808L (13s Deerland - 808AL tap) | 2023-09-11 09:30 | 2023-09-11 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 720s 901T (720s Wabasca), 720s 502R (720s Wabasca), 720s 504R (720s Wabasca) | 2023-09-11 10:00 | 2023-09-12 15:00 | N | Y |  | Transformer, Shunts |  | Outage returned early. | 240 kV, Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap), 767s 601 (767s Oyen) | 2023-09-11 13:00 | 2023-09-12 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s CC24 (987s Clover Bar) | 2023-09-12 07:00 | 2023-09-12 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-09-12 07:00 | 2023-09-13 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.2TR (SS-21), 60s50 (SS-21), 21.1C (SS-21) | 2023-09-12 08:00 | 2023-09-12 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 163s T2 (163s Amoco Empress) | 2023-09-12 08:30 | 2023-09-13 08:30 | N | Y |  | Transformer |  |  | 240 kV
ALTALINK | 77s 252 (77s Sagitawah) | 2023-09-12 09:00 | 2023-09-12 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 358s T1 (358s Amoco Brazeau) | 2023-09-12 09:00 | 2023-10-12 08:30 | N | N |  | Transformer | Shrink outage zone to 358s only. 358s652 breaker install, 358s12 PT replacement, T1 & VR1 maintenance, 25kV switch maintenance. RSLD 4 to be implemented at the end of the outage. |  | For Information Only
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek) | 2023-09-12 10:00 | 2023-09-12 12:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
CMH | MH-50L (MHS-2 North Industrial - MHS-5 NE Crescent Heights) | 2023-09-12 11:00 | 2023-09-12 11:30 | N | N |  | Line | Open 69kV MH-50L line to eliminate current from line CT's to facilitate wiring for modified CT ratio for bus protection relay. MH69-50L will remain energized but open at breaker MH69-221 to interrupt current/power flow for maximum 30 minutes to facilitate wiring modification work. |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s CK725 (987s Clover Bar) | 2023-09-13 07:00 | 2023-09-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, CapitalPower | 1148L (251s Whitla - 1018s Shamrock), 1018s Shamrock, 1018s 7290-CB-008 (1018s Shamrock), 1018s 7290-CB-001 (1018s Shamrock) | 2023-09-13 07:00 | 2023-09-13 17:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33MD138-33.1TR (SS-33), 33B138-33.83 (SS-33), SW83 (SS-33) | 2023-09-13 08:00 | 2023-09-13 12:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 65B138-D82 (SS-65) | 2023-09-13 08:00 | 2023-09-14 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
SUNCOR | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2023-09-13 08:00 | 2023-10-07 18:00 | N | N |  | Line |  |  | For Information Only
Saskpower | Sask Power SW 918 | 2023-09-13 09:00 | 2023-09-13 11:00 | N | Y |  | Circuit Breaker | SW 904BKR, SW 905BKR, SW 908BKR, SW 910BKR, SW 913BKR, SW 914BKR, SW 915BKR, SW 918BKR |  | Limits ATC
ALTALINK | 77s 40 (77s Sagitawah) | 2023-09-13 09:00 | 2023-09-13 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 163s T1 (163s Amoco Empress) | 2023-09-13 09:05 | 2023-09-14 16:30 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
CMH | MH69s2 T21 (MH69s2 North Industrial) | 2023-09-13 10:00 | 2023-09-13 10:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33B138-33.84 (SS-33), 33MD138-33.2TR (SS-33), SW84 (SS-33) | 2023-09-13 12:00 | 2023-09-13 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 1098L (EP 805s Jasper - Poundmaker), PM2401 (Poundmaker), PM2402 (Poundmaker) | 2023-09-14 07:00 | 2023-09-16 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 72CK13 (987s Clover Bar - Kennedale), 987s CK726 (987s Clover Bar) | 2023-09-14 07:00 | 2023-09-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 23B138-23.80 (SS-23), 74s 23.80W (74s Janet) | 2023-09-14 08:00 | 2023-09-14 12:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ATCO | 7L53 (706s Irish Creek - 7LA53 tap), 706s 702 (706s Irish Creek) | 2023-09-14 08:00 | 2023-09-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 816s PDS13 (816s Petrolia) | 2023-09-14 11:32 | 2023-09-16 17:00 | N | Y |  | Line, Switch |  |  | 240 kV
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23) | 2023-09-14 12:00 | 2023-09-14 18:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2023-09-15 07:00 | 2023-09-16 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72CN10 (987s Clover Bar - Namao), 987s CN723 (987s Clover Bar), N724 (Namao) | 2023-09-15 07:00 | 2023-09-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 27B69-16.61 (SS-27) | 2023-09-15 08:00 | 2023-09-15 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 13.4TR (SS-13), 27B69-13.60 (SS-27) | 2023-09-15 12:00 | 2023-09-15 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 814s BDS13 (814s Bellamy), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy), 814s BDS12 (814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy) | 2023-09-16 07:00 | 2023-09-16 17:00 | N | Y |  | Switch, Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 11.81L (SS-11 - SS-13), 11.4TR (SS-11), 11.1TR (SS-11), 11B138-BT5 (SS-11), 11MD138-11.4TR (SS-11), 11MD138-11.1TR (SS-11) | 2023-09-16 08:00 | 2023-09-16 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ATCO, ALBIAN, CNRL | 919s 906 (919s Hartley), 847s 901T (847s Muskeg River) | 2023-09-16 08:00 | 2023-09-19 14:00 | N | Y |  | Circuit Breaker, Transformer | CNRL/Heartland Request for Isolation for their GT-1 DUE to Emergency Oil Leak. Calculations were made and with the oil tank volume we can stay running until September 16th before we run into a low level condition on our tank and have to shut down. |  | 240 kV, Restricts Generation
ENMAX | 37.81L (SS-37 - SS-38), 37.1TR (SS-37), 37B138-37.81 (SS-37) | 2023-09-17 08:00 | 2023-09-17 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 1.7TR (SS-1) | 2023-09-17 08:00 | 2023-09-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 74s 37.82W (74s Janet), 37.82L (74s Janet - SS-37) | 2023-09-17 12:00 | 2023-09-17 18:00 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 37.2TR (SS-37), 37B138-37.82 (SS-37) | 2023-09-17 12:00 | 2023-09-17 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 170L (632s Russell - 799s Coleman), 799s 170E (799s Coleman) | 2023-09-18 07:00 | 2023-09-18 17:00 | N | Y |  | Line, Circuit Breaker |  | Replace strain glass on 170L on 799s A frame | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), 987s CH722 (987s Clover Bar), H724 (EP Hardisty) | 2023-09-18 07:00 | 2023-09-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Poundmaker), PM2401 (Poundmaker), PM2405 (Poundmaker) | 2023-09-18 07:00 | 2023-09-18 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | N722 (Namao) | 2023-09-18 07:00 | 2023-09-22 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | N721 (Namao), N722 (Namao), T1 (Namao) | 2023-09-18 07:00 | 2023-09-22 17:00 | N | N |  | Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 140s T1 (140s Thompson) | 2023-09-18 07:30 | 2023-09-18 17:30 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 30EDD-1 623T (30EDD-1), 30EDD-1 623 (30EDD-1), 30EDD-1 624 (30EDD-1), 30EDD-1 623TD (30EDD-1) | 2023-09-18 08:00 | 2023-09-28 18:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MH-30L (MHS-3 Southridge - MHS-5 NE Crescent Heights), MHS-5 MH69-T51 (MH69s5 NE Crescent Height), MHS-3 MH69-308 (MHS-3 Southridge), MHS-5 MH69-502 (MHS-5 NE Crescent Heights), MHS-5 MH69-503 (MHS-5 NE Crescent Heights), MHS-5 MH69-504 (MHS-5 NE Crescent Heights) | 2023-09-18 08:00 | 2023-09-27 11:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  | Returned early. | Creates Radial Feeds, Firm Load Loss
ENMAX | 65B138-D83 (SS-65) | 2023-09-18 08:00 | 2023-09-19 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 20.1TR (SS-20) | 2023-09-18 08:00 | 2023-09-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 41B138-41BT3 (SS-41) | 2023-09-18 08:00 | 2023-09-18 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 7L08 (830s Carmon - 834s Wesley Creek), 830s 701T (830s Carmon), 830s 701TCS (830s Carmon) | 2023-09-18 08:00 | 2023-10-13 17:00 | N | Y |  | Line, Transformer, Switch |  |  | For Information Only, Restricts Generation
ENMAX | 13.82L (SS-13 - SS-22), 22.1TR (SS-22), 22.3TR (SS-22), 22B138-22BT8 (SS-22), 22B138-13.82 (SS-22), 22MD138-22.1TR (SS-22), 22MD138-22.3TR (SS-22) | 2023-09-18 08:00 | 2023-09-18 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.3TR (SS-11) | 2023-09-18 08:00 | 2023-09-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 189L (373s Madden - 418L tap), 373s T1 (373s Madden), 373s 752 (373s Madden), 373s 25 (373s Madden) | 2023-09-18 09:00 | 2023-09-28 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 74s C1 (74s Janet), 74s C2 (74s Janet) | 2023-09-18 09:30 | 2023-09-18 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 665s D2403 (665s Dome), 310p 1352 (310p Sundance), 310p 1452 (310p Sundance) | 2023-09-18 09:30 | 2023-09-21 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 720s 901 (720s Wabasca) | 2023-09-18 10:00 | 2023-10-04 15:30 | N | Y |  | Circuit Breaker |  | Returned early | Pre-Condition
ATCO | 739s 702 (739s Edith Lake), 7L172 (739s Edith Lake - 743s Sarah Lake) | 2023-09-18 10:00 | 2023-09-18 17:00 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
ATCO | 826s 904 (826s Marguerite Lake) | 2023-09-18 10:00 | 2023-09-18 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22BT8 (SS-22), 22B138-22.81 (SS-22) | 2023-09-18 12:00 | 2023-09-18 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-09-18 12:00 | 2023-09-21 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 310p 2652 (310p Sundance) | 2023-09-18 13:30 | 2023-09-21 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 275s 8 (275s Jenner) | 2023-09-18 14:00 | 2023-09-21 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 790s 704 (790s Poplar Hill) | 2023-09-18 15:00 | 2023-09-27 18:00 | N | N |  | Circuit Breaker | Customer (Heartland) request for isolation to work on their 13.8kv bus during the Poplar Hill Generation Station Outage. |  | For Information Only, Restricts Generation
EPCOR | T2 (Poundmaker) | 2023-09-18 17:00 | 2023-09-21 17:00 | N | Y |  | Transformer |  |  | For Information Only
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), 987s CH724 (987s Clover Bar) | 2023-09-19 07:00 | 2023-09-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2023-09-19 07:00 | 2023-09-23 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2023-09-19 07:00 | 2023-10-01 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 330P 12TC2 (330p Genesee), 330p 809 (330p Genesee) | 2023-09-19 07:00 | 2023-10-21 07:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAXGPI | 134s 134.1TR (134s Taber Wind Farm), 134s 134.2TR (134s Taber Wind Farm) | 2023-09-19 07:00 | 2023-09-20 19:00 | N | N |  | Transformer | 134s T1 (134s Taber Wind Farm), 134s T2 (134s Taber Wind Farm) |  | Pre-Condition, Restricts Generation
ENMAX | 26.81L (SS-26 - SS-32), 32.83L (SS-32 - SS-40), 32.1TR (SS-32), 32.2TR (SS-32), 32B138-32BT5 (SS-32), 40B138-32.83 (SS-40), 26B138-26.81 (SS-26) | 2023-09-19 08:00 | 2023-09-19 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 36B138-14.83 (SS-36) | 2023-09-19 08:00 | 2023-09-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 38s T3 (38s East Edmonton) | 2023-09-19 08:30 | 2023-09-19 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L62 (789s Keg River - 797s Kemp River), 789s 702 (789s Keg River) | 2023-09-19 09:00 | 2023-09-19 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, BHE | 719s T1 (719s Rattlesnake Ridge), 879AL (719s Rattlesnake Ridge - 879L tap), 719s 138CB1 (719s Rattlesnake Ridge) | 2023-09-19 09:00 | 2023-09-22 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  | Delayed | Restricts Generation
ALTALINK | 912L (63s Red Deer - 766s Nevis) | 2023-09-19 09:30 | 2023-09-19 17:30 | N | Y |  | Line |  |  | For Information Only,Affects Cranking Path
ATCO | 9L20 (755s Cordel - 766s Nevis), 9L912 (63s Red Deer - 766s Nevis), 766s 9L912D1 (766s Nevis), 766s 902 (766s Nevis), 766s 9L20D2 (766s Nevis), 766s 901 (766s Nevis) | 2023-09-19 10:00 | 2023-09-19 17:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
VISIONREQ | 354s DVAR1 (354s Summerview) | 2023-09-19 10:00 | 2023-09-19 17:00 | N | N |  | Shunts |  |  | For Information Only, Pre-Condition
ATCO | 826s 702 (826s Marguerite Lake) | 2023-09-19 10:00 | 2023-09-20 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO, CapitalPower | 9L93 (615s Halkirk - 972s Tinchebray), 615s Halkirk, 972s 901 (972s Tinchebray), 972s 903 (972s Tinchebray), 615s 52T1 (615s Halkirk), 615s 52M1 (615s Halkirk) | 2023-09-19 10:00 | 2023-09-24 17:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | 240 kV, Restricts Generation
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek), 739s 701 (739s Edith Lake), 809s 704 (809s Louise Creek) | 2023-09-19 12:00 | 2023-10-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32) | 2023-09-19 12:00 | 2023-09-19 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | 987s C1 (987s Clover Bar), 987s C72C1 (987s Clover Bar) | 2023-09-20 07:00 | 2023-09-20 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 727L (65s High River - 727AL tap), 727L (678s Okotoks - 727AL tap), 727AL (142s Magcan - 727L tap), 142s 138kV Bus (142s Magcan), 142s C1 (142s Magcan) | 2023-09-20 07:00 | 2023-09-22 18:30 | N | N |  | Line, Bus, Shunts |  |  | Over/Under Voltage, Pre-Condition
ENMAX | 65B138-D84 (SS-65) | 2023-09-20 08:00 | 2023-09-21 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
FMGW, ALTALINK | 1024s Granlea, 964AL (1024s Granlea - 964L tap), 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s PS-6005 (1024s Granlea), 1024s PS-6006 (1024s Granlea), 1024s PS-6007 (1024s Granlea), 1024s PS-6008 (1024s Granlea) | 2023-09-20 08:00 | 2023-09-20 16:00 | N | Y |  | Station, Line, Transformer, Switch |  |  | Restricts Generation
ENMAX | 13.82L (SS-13 - SS-22), 22B138-13.82 (SS-22), 13B138-13.82 (SS-13) | 2023-09-20 08:00 | 2023-09-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43) | 2023-09-20 08:00 | 2023-09-20 10:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 38s T2 (38s East Edmonton) | 2023-09-20 08:30 | 2023-09-20 17:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43) | 2023-09-20 10:00 | 2023-09-20 12:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 766s 240kV Bus (766s Nevis), 766s 901 (766s Nevis), 766s 902 (766s Nevis) | 2023-09-20 10:00 | 2023-12-04 17:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK, TRANSALTA | 512L (310p Sundance - 521L tap), 234L (310p Sundance - 505L tap), 310p 69kV Bus (310p Sundance), 310p T30 (310p Sundance), 310P T31 (310P Sundance), 310P 512N (310p Sundance), 310P 234N (310p Sundance), 310P 3352 (310p Sundance), 310P 69 (310p Sundance), 310p 696 (310p Sundance) | 2023-09-20 12:00 | 2023-10-05 18:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 2023-09-21 07:00 | 2023-09-30 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, CNRL | 847s 902T (847s Muskeg River), 847s 902 (847s Muskeg River) | 2023-09-21 08:00 | 2023-09-24 12:00 | N | Y |  | Transformer, Circuit Breaker | CNRL/Heartland Isolation Request for their 520-GT-201 Generator Outage |  | 240 kV, For Information Only, Pre-Condition
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-09-21 09:00 | 2023-09-21 17:00 | N | N |  | Line |  |  | Limits ATC
ATCO | 7L51 (ATC 793s West Peace River - 927s Buchanan Creek) | 2023-09-21 09:00 | 2023-09-21 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16) | 2023-09-21 11:00 | 2023-09-21 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34) | 2023-09-21 13:00 | 2023-09-21 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27) | 2023-09-21 15:00 | 2023-09-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 38s T4 (38s East Edmonton), 38s 240kV Bus 2 (38s East Edmonton), 38s 18 (38s East Edmonton), 38s 7352 (38s East Edmonton), 38s 7452 (38s East Edmonton), 38s 12 (38s East Edmonton) | 2023-09-22 08:30 | 2023-09-24 18:00 | N | Y |  | Transformer, Bus, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L133 (786s High Level - 828s Sulphur Point) | 2023-09-22 17:46 | 2023-09-28 15:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 526BL (659s Pegasus Lake - 526L tap), 659s T1 (659s Pegasus Lake), 659s T2 (659s Pegasus Lake), 659s 526B (659s Pegasus Lake), 659s 389 (659s Pegasus Lake), 659s 189 (659s Pegasus Lake), 659s 289 (659s Pegasus Lake), 659s 489 (659s Pegasus Lake) | 2023-09-23 07:00 | 2023-09-23 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX | 38.83L (SS-38 - SS-39), 39.82L (SS-39 - SS-162), 39.1TR (SS-39), 39.3TR (SS-39), 39B138-38.83 (SS-39), 39B138-39.82 (SS-39), 39MD138-39.1TR (SS-39), 39MD138-39.3TR (SS-39) | 2023-09-23 08:00 | 2023-09-23 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 237s T2 (237s Foothills) | 2023-09-23 08:30 | 2023-09-24 16:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 39.82L (SS-39 - SS-162), 39.2TR (SS-39), 39.4TR (SS-39), 39B138-39.82 (SS-39), 39B138-22.81 (SS-39), 39MD138-39.2TR (SS-39), 39MD138-39.4TR (SS-39) | 2023-09-23 12:00 | 2023-09-23 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 659s T1 (659s Pegasus Lake), 659s 289 (659s Pegasus Lake) | 2023-09-23 17:00 | 2023-11-02 11:00 | N | N |  | Transformer, Switch |  |  | For Information Only
EPCOR | 557s CD2403 (557s Castle Downs) | 2023-09-24 07:00 | 2023-09-28 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 31.84L (SS-31 - SS-32), 24.81L (SS-24 - SS-31), 31.2TR (SS-31), 31.3TR (SS-31), 31B138-31.84 (SS-31), 31B138-24.81 (SS-31), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31) | 2023-09-24 08:00 | 2023-09-24 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.2TR (SS-31), 31.1TR (SS-31), 31.1C (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31) | 2023-09-24 12:00 | 2023-09-24 18:00 | N | N |  | Line, Transformer, Shunts, Switch |  |  | Pre-Condition
ALTALINK | 42s C2 (42s Sarcee), 42s 240kV North Bus (42s Sarcee), 928L (17s Benalto - 42s Sarcee), 42s T1 (42s Sarcee), 916L (5s East Calgary - 42s Sarcee), 42s 916E (42s Sarcee), 42s 928N (42s Sarcee), 42s 70 (42s Sarcee), 42s 40 (42s Sarcee) | 2023-09-25 00:01 | 2023-09-25 08:00 | N | Y |  | Shunts, Bus, Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T2 (Woodcroft), W725 (Woodcroft), W723 (Woodcroft), 72NW15 (Namao - Woodcroft) | 2023-09-25 07:00 | 2023-09-28 17:00 | N | N |  | Transformer, Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Poundmaker), PM2404 (Poundmaker), PM2405 (Poundmaker), PMAB3 (Poundmaker) | 2023-09-25 07:00 | 2023-09-25 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | N723 (Namao) | 2023-09-25 07:00 | 2023-09-29 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 415s T2 (415s Drywood) | 2023-09-25 08:00 | 2023-09-27 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2023-09-25 08:00 | 2023-10-02 13:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 41.2TR (SS-41) | 2023-09-25 08:00 | 2023-09-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 773s 601T (773s Coronation) | 2023-09-25 08:00 | 2023-09-29 14:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.4TR (SS-2) | 2023-09-25 08:00 | 2023-09-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 65B138-D85 (SS-65) | 2023-09-25 08:00 | 2023-09-26 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 510s ACF22 (510s Sunnybrook), 510s ACF21 (510s Sunnybrook), 510s 1952 (510s Sunnybrook), 510s 2052 (510s Sunnybrook), 510s 35 (510s Sunnybrook), 510s 36 (510s Sunnybrook) | 2023-09-25 08:30 | 2023-10-02 17:00 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | 500 kV, Pre-Condition
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-09-25 09:00 | 2023-09-29 17:00 | N | N |  | Line |  |  | 240 kV, Limits ATC
BCH | T4 (BCH Natal), 2CB2 (BCH Natal) | 2023-09-25 09:00 | 2023-10-27 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 33s 1 (33s Spray) | 2023-09-25 09:30 | 2023-09-26 16:00 | N | Y |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
ATCO | 2029s 1209 (2029s Heathfield) | 2023-09-25 09:30 | 2023-09-25 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-09-25 12:00 | 2023-09-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 170s T2 (170s Pike) | 2023-09-25 13:00 | 2023-09-27 14:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | T3 (Poundmaker) | 2023-09-25 17:01 | 2023-09-28 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2023-09-26 07:00 | 2023-10-02 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | AML 793s T1 (AML 793s Horse Creek) | 2023-09-26 08:00 | 2023-09-27 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.2TR (SS-26) | 2023-09-26 08:00 | 2023-09-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO, ALTALINK | 7L760D3 (7LA760 tap), 760L (760AL tap - 7LA760 tap) | 2023-09-26 08:00 | 2023-09-27 13:00 | N | Y |  | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 294s T1 (294s Brazeau Outlet Works) | 2023-09-26 08:30 | 2023-09-26 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, ATCO | 526s 152 (526s Buffalo Creek), 7L129 (526s Buffalo Creek - 7LA129 tap) | 2023-09-26 08:30 | 2023-09-26 12:30 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 2029s ACF21 (2029s Heathfield) | 2023-09-26 09:30 | 2023-09-26 17:30 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ALTALINK | 19s 49 (19s Wabamun), 19s T10 (19s Wabamun) | 2023-09-26 09:30 | 2023-09-26 16:30 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds, Over/Under Voltage, Pre-Condition
ALTALINK | 42s 70 (42s Sarcee) | 2023-09-26 09:30 | 2023-09-26 17:30 | N | Y |  | Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition
ALTALINK, ATCO | 526s 252 (526s Buffalo Creek), 7L50 (526s Buffalo Creek - 491L tap) | 2023-09-26 12:30 | 2023-09-26 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
Lethbridge | 146s 813L (146s Macdonald), 813L (146s MacDonald - 241s Uplands), 241s 813L (241s Uplands) | 2023-09-26 13:30 | 2023-09-26 19:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5RXN5 (BCH Cranbrook) | 2023-09-26 15:20 | 2023-10-07 18:00 | N | Y |  | Shunts | BC reactor leaking gas, emergency outage |  | 500 kV
ENMAX | 14.1C (SS-14) | 2023-09-26 23:00 | 2023-09-27 16:00 | N | N |  | Shunts | forced outage |  | Pre-Condition
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 146s 823L (146s Macdonald), 593s 823L (593s Lakeview) | 2023-09-27 07:00 | 2023-09-27 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 42s C2 (42s Sarcee), 42s C3 (42s Sarcee) | 2023-09-27 08:00 | 2023-09-27 17:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell), 356s 252 (356s Milo), 356s 352 (356s Milo) | 2023-09-27 09:30 | 2023-09-27 16:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ATCO | 2029s ACF22 (2029s Heathfield) | 2023-09-27 09:30 | 2023-09-27 17:30 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ALTALINK | 773L (127s Bruderheim - 308s Albchem Beaverhill Creek) | 2023-09-27 11:13 | 2023-09-29 14:00 | N | N |  | Line |  | Outage returned early. | For Information Only
ALTALINK | 310p 2352 (310p Sundance), 310p 2452 (310p Sundance) | 2023-09-27 12:00 | 2023-09-27 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition
ATCO | 7L760 (767s Oyen - 7LA760 tap), 767s 702 (767s Oyen) | 2023-09-27 13:30 | 2023-09-29 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 349s Stavely, 349s T1 (349s Stavely), 349s 20 (349s Stavely) | 2023-09-28 07:00 | 2023-10-02 17:00 | N | Y |  | Station, Transformer, Switch |  |  | Pre-Condition, Restricts Generation
ENMAX | 27.2TR (SS-27) | 2023-09-28 08:00 | 2023-09-28 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | T1 (BCH Natal), 13CX1 (BCH Natal), 60D1CB1 (BCH Natal), 60D1CB11 (BCH Natal), 60D1CB15 (BCH Natal) | 2023-09-28 09:00 | 2023-09-28 19:00 | N | Y |  | Transformer, Shunts, Switch | 60VT1 Insp/doble 60D1CB1/60D1CB11/60D1CB15 Inspections T1 Non Elec tests |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 2029s ACF23 (2029s Heathfield) | 2023-09-28 09:30 | 2023-09-28 17:30 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 7L587 (822s Wolf Lake - 826s Marguerite Lake), 826s 710 (826s Marguerite Lake), 826s 707 (826s Marguerite Lake), 822s 701 (822s Wolf Lake), 826s 7L587D1 (826s Marguerite Lake) | 2023-09-28 10:00 | 2023-09-29 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 275s T1 (275s Jenner), 275s 240kV Bus 1 (275s Jenner), 275s 1752 (275s Jenner), 275s 2 (275s Jenner), 275s 35 (275s Jenner), 275s 2152 (275s Jenner), 275s 39 (275s Jenner) | 2023-09-29 08:00 | 2023-09-29 11:00 | N | Y |  | Transformer, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 275s T2 (275s Jenner), 275s 240kV Bus 2 (275s Jenner), 949L (275s Jenner - 306s Halsbury), 275s 949 (275s Jenner), 275s 1952 (275s Jenner), 275s 8 (275s Jenner), 275s 46 (275s Jenner), 275s 36 (275s Jenner), 275s 2252 (275s Jenner) | 2023-09-29 12:00 | 2023-09-29 15:00 | N | Y |  | Transformer, Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
SUNCOR | 29PL6-5 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29PT-0084 (29EDD-22), 29PS-44 (29EDD-22) | 2023-09-29 20:00 | 2023-10-13 18:00 | N | N |  | Line, Transformer, Switch |  |  | For Information Only, Pre-Condition
Syncrude | 3145 (Syncrude Mildred Lake), 3235 (Syncrude Mildred Lake), Mildred T3 (Syncrude Mildred Lake) | 2023-09-30 08:00 | 2023-10-11 16:00 | N | Y |  | Circuit Breaker, Transformer |  |  | For Information Only, Restricts Generation
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake) | 2023-09-30 08:00 | 2023-11-01 08:00 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
CapitalPower | 615s DVAR2 (615s Halkirk) | 2023-10-01 08:00 | 2023-10-10 17:00 | N | N |  | Shunts
ALTALINK | 225L (225s Magrath - 385s Spring Coulee), 385s 67 (385s Spring Coulee), 385s 225 (385s Spring Coulee), 385s T3 (385s Spring Coulee), 225L (229s Glenwood - 385s Spring Coulee), 385s 69kV Bus (385s Spring Coulee), 385s T1 (385s Spring Coulee), 385s T2 (385s Spring Coulee), 225s 225W (225s Magrath) | 2023-10-01 09:00 | 2023-10-01 15:00 | N | N |  | Line, Circuit Breaker, Transformer, Bus |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 39s 1152 (39s Bickerdike) | 2023-10-01 09:30 | 2023-10-02 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 385s 69kV Bus (385s Spring Coulee), 385s T1 (385s Spring Coulee), 385s T2 (385s Spring Coulee), 385s T3 (385s Spring Coulee), 385s 225 (385s Spring Coulee), 385s 67 (385s Spring Coulee) | 2023-10-01 15:01 | 2023-10-29 06:59 | N | N |  | Bus, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
EPCOR | N721 (Namao) | 2023-10-02 07:00 | 2023-10-06 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 180AL (604s Granum - 180L tap), 180L (15s Fort Macleod - 180AL tap), 180L (928s East Stavely - 180AL tap) | 2023-10-02 07:00 | 2023-10-02 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | EP 511s Victoria T3 (EP 511s Victoria) | 2023-10-02 07:00 | 2023-10-06 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, BHE Canada | 120s 27 (120s Picture Butte) | 2023-10-02 07:00 | 2023-10-07 18:00 | N | Y |  | Switch |  |  | 240 kV, Limits ATC, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2023-10-02 07:30 | 2023-10-07 19:00 | Y | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38) | 2023-10-02 08:00 | 2023-10-02 18:00 | N | N |  | Line, Transformer, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-85 29PS-320 (29EDD-85) | 2023-10-02 08:00 | 2023-10-12 15:00 | N | N |  | Switch |  |  | For Information Only
Lethbridge, ALTALINK | 181s 172L (181s Chinook), 172L (181s Chinook - 370s North Lethbridge) | 2023-10-02 08:00 | 2023-10-02 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 189L (373s Madden - 418L tap), 373s T1 (373s Madden), 373s 752 (373s Madden), 373s 25 (373s Madden) | 2023-10-02 08:00 | 2023-10-06 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook), 786L (799s Coleman - BCH Natal), 887L (48s Pocaterra - 978s BCH Britt Creek) | 2023-10-02 09:00 | 2023-10-07 18:00 | Y | Y |  | Line |  |  | 500 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ALTALINK | 1114L (102s Langdon - 520s Bennett), 520s T1 (520s Bennett), 520s 1352 (520s Bennett), 520s 552 (520s Bennett) | 2023-10-02 09:00 | 2023-10-07 16:00 | Y | Y |  | Line, Transformer, Circuit Breaker |  |  | 500 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 391s T2 (391s Balzac), 391s 33 (391s Balzac) | 2023-10-02 09:00 | 2023-10-02 14:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 739s 701T (739s Edith Lake), 6L11 (739s Edith Lake - 854s Swan Dive), 6L97 (735s Swan River - 739s Edith Lake), 739s 601 (739s Edith Lake), 739s 602 (739s Edith Lake), 739s 603 (739s Edith Lake), 735s 603 (735s Swan River) | 2023-10-02 10:00 | 2023-10-26 17:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 847L236B (847AL tap) | 2023-10-02 10:30 | 2023-10-03 10:30 | N | Y |  | Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 19s 240kV Bus A (19S Wabamun), 19s 240kV Bus B (19S Wabamun), 19s 240kV Transfer Bus (19S Wabamun), 19s T10 (19s Wabamun), 905L (19s Wabamun - 37s North Calder), 902L (19s Wabamun - 310p Sundance), 310p 752 (310p Sundance), 310p 852 (310p Sundance), 19s 49 (19s Wabamun), 19s 902 (19s Wabamun), 19s 905 (19s Wabamun), 19s 52 (19s Wabamun), 19s 97 (19s Wabamun), 19s 50 (19s Wabamun) | 2023-10-02 12:30 | 2023-10-05 17:30 | N | Y |  | Bus, Transformer, Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 648s T3 (648s Metiskow), 954L (648s Metiskow - 650s Hansman Lake), 648s 29 (648s Metiskow) | 2023-10-02 14:30 | 2023-10-05 17:30 | N | Y |  | Transformer, Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14) | 2023-10-02 18:01 | 2023-10-16 13:31 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 735L (171s Redwater - 233s Beamer), 171s 735X (171s Redwater), 233s 735N (233s Beamer) | 2023-10-03 07:00 | 2023-10-03 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, DOW | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 54s 707N (54s Fort Saskatchewan), 166s 707X (166s Dow Chemical Fort Saskatchewan) | 2023-10-03 07:00 | 2023-10-03 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 657s T2 (657s Summerside) | 2023-10-03 07:00 | 2023-10-07 17:00 | N | Y |  | Transformer |  |  | For Information Only, Pre-Condition
Lethbridge | 463L (181s Chinook - 463AL tap), 181s 463L (181s Chinook) | 2023-10-03 08:00 | 2023-10-03 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ENMAX | 12.2TR (SS-12) | 2023-10-03 08:00 | 2023-10-03 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s 7252 (38s East Edmonton), 38s 7352 (38s East Edmonton), 946L (38s East Edmonton - 89s Ellerslie) | 2023-10-03 08:30 | 2023-10-06 17:30 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation
ATCO, ALTALINK | 7L696 (508s Lakesend - 892s Ribstone Creek), 508s T1 (508s Lakesend), 508s 696 (508s Lakesend) | 2023-10-03 09:00 | 2023-10-03 16:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
BCH | 5L94 (BCH Cranbrook - 102s Langdon) | 2023-10-03 09:00 | 2023-10-06 17:00 | Y | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 172L (83s Taber - 172EL tap), 83s 172W (83s Taber) | 2023-10-03 09:30 | 2023-10-05 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 847L236B (847AL tap) | 2023-10-03 10:00 | 2023-10-04 11:30 | N | Y |  | Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 12.1TR (SS-12) | 2023-10-03 12:00 | 2023-10-03 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 787L (71s Lamoureux - 787AL tap) | 2023-10-04 07:00 | 2023-10-04 18:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 905L (19s Wabamun - 37s North Calder), 37s 82 (37s North Calder), 37s 76 (37s North Calder), 19s 905 (19s Wabamun), 19s 98 (19s Wabamun) | 2023-10-04 07:30 | 2023-10-04 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
REDDEER | 247s T1 (247s Piper Creek) | 2023-10-04 08:00 | 2023-10-04 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge), 370s 207X (370s North Lethbridge) | 2023-10-04 08:00 | 2023-10-04 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 158s T2 (158s Vauxhall) | 2023-10-04 08:00 | 2023-10-04 12:00 | N | Y |  | Bus | Transmission constraint record created. |  | Restricts Generation
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson), ATC 803S 7L85D4 (ATC 803s Bullpound) | 2023-10-04 09:00 | 2023-10-04 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 875s 701T (875s Algar) | 2023-10-04 09:30 | 2023-10-05 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-10-04 10:00 | 2023-10-04 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 847L236B (847AL tap) | 2023-10-04 10:30 | 2023-10-04 17:30 | N | Y |  | Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 247s T2 (247s Piper Creek) | 2023-10-04 12:00 | 2023-10-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 39s 1552 (39s Bickerdike) | 2023-10-04 17:30 | 2023-10-05 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, DOW | 787L (166s Dow Chemical Fort Saskatchewan - 787AL tap), 166s 787W (166s Dow Chemical Fort Saskatchewan) | 2023-10-05 07:00 | 2023-10-05 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 95s T2 (95s Imperial Oil Edmonton), 38s 737N (38s East Edmonton) | 2023-10-05 07:00 | 2023-10-05 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.9TR (SS-5) | 2023-10-05 08:00 | 2023-10-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap) | 2023-10-05 08:00 | 2023-10-05 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2023-10-05 10:00 | 2023-10-05 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ATCO | 6L12 (774s Monitor - 6L25 tap), 774s 601 (774s Monitor), 774s 701T (774s Monitor), 774s 707 (774s Monitor) | 2023-10-05 11:30 | 2023-12-01 14:00 | N | N |  | Line, Circuit Breaker, Transformer |  | Back early I do not know when. | For Information Only
ALTALINK | 39s 1652 (39s Bickerdike) | 2023-10-05 17:30 | 2023-10-06 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station), 814s B2402 (814s Bellamy), 814s B2401 (814s Bellamy) | 2023-10-06 08:00 | 2023-10-06 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
SUNCOR | 29EDD-1 T1 (29EDD-1 Millennium), 29EDD-1 72kV South Bus (29EDD-1 Millennium), 29EDD-1 260kV South Bus 1 (29EDD-1 Millennium), 29EDD-1 260kV South Bus 2 (29EDD-1 Millennium), 29EDD-1 29EDD1S1452 (29EDD-1 Millennium), 29EDD-1 29EDD1s1852 (29EDD-1 Millennium), 29EDD-1 29EDD1s352 (29EDD-1 Millennium), 29EDD-1 29EDD1s652 (29EDD-1 Millennium), 29EDD-1 952-103 (29EDD-1 Millennium), 29EDD-1 952-106 (29EDD-1 Millennium), 29EDD-1 29EDD1s952 (29EDD-1 Millennium) | 2023-10-06 08:00 | 2023-10-15 18:00 | N | Y |  | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 186s T1 (186s Dry Creek) | 2023-10-06 08:30 | 2023-10-06 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 39s 1752 (39s Bickerdike) | 2023-10-06 17:30 | 2023-10-07 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 419s 765 (419s Chestermere) | 2023-10-07 07:00 | 2023-10-07 14:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27) | 2023-10-07 08:00 | 2023-10-07 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 665s D2402 (665s Dome), 665s D2403 (665s Dome), 665s T2 (665s Dome), 665s DAB2 (665s Dome), 665s DDS14 (665s Dome) | 2023-10-09 07:00 | 2023-10-12 15:00 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 65s 753E (65s High River), 753L (65s High River - 253s Blackie) | 2023-10-09 07:00 | 2023-10-09 18:00 | N | Y |  | Circuit Breaker, Line |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2023-10-09 07:13 | 2023-10-10 17:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 71s 152 (71s Lamoureux) | 2023-10-09 07:13 | 2023-10-27 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14B138-11.82 (SS-14), 14MD138-14.1TR (SS-14), 14MD138-14.3TR (SS-14) | 2023-10-09 08:00 | 2023-10-09 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36B69-16.63/36.5TR (SS-36), 16B69-16.63 (SS-16) | 2023-10-09 08:00 | 2023-10-14 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | 557s CD2405 (557s Castle Downs) | 2023-10-10 07:00 | 2023-10-14 17:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2023-10-10 07:00 | 2023-10-14 18:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
EPCOR | N724 (Namao), 72CN10 (987s Clover Bar - Namao) | 2023-10-10 07:00 | 2023-10-13 17:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 983L (244s Bowmanton - 983L tap), 983L (251s Whitla - 983L tap) | 2023-10-10 08:00 | 2023-10-10 13:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Whisky Jack) | 2023-10-10 08:00 | 2023-10-10 17:00 | N | Y |  | Line |  |  | 240 kV
ENMAX | 5.10TR (SS-5) | 2023-10-10 08:00 | 2023-10-10 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 8.6TR (SS-8) | 2023-10-10 08:00 | 2023-10-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s 7452 (38s East Edmonton) | 2023-10-10 08:30 | 2023-10-11 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap), 811s 708 (811s Clairmont Lake) | 2023-10-10 09:00 | 2023-10-10 09:01 | N | Y |  | Line, Circuit Breaker |  | Realtime conditions | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 189L (373s Madden - 418L tap), 373s T1 (373s Madden), 373s 752 (373s Madden), 373s 25 (373s Madden) | 2023-10-10 09:00 | 2023-10-23 07:59 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ATCO | 9L93 (615s Halkirk - 972s Tinchebray) | 2023-10-10 10:00 | 2023-10-10 17:00 | N | Y |  | Line |  |  | 240 kV, Restricts Generation
ATCO | 951s SVC (951s Thickwood) | 2023-10-10 10:00 | 2023-10-13 17:30 | N | Y |  | Shunts |  |  | For Information Only, Pre-Condition
ATCO | 786s 702T (786s High Level) | 2023-10-10 10:00 | 2023-10-17 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 419s T1 (419s Chestermere) | 2023-10-10 12:00 | 2023-10-12 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 9L15 (834s Wesley Creek - 876s Brintnell), 876s 904 (876s Brintnell), 876s 906 (876s Brintnell), 834s 909D1 (834s Wesley Creek) | 2023-10-10 12:00 | 2023-10-13 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-10-10 12:00 | 2023-10-12 15:05 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary), 5s 752 (5s East Calgary), 5s 852 (5s East Calgary) | 2023-10-10 12:30 | 2023-10-11 17:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 983L (251s Whitla - 983L tap) | 2023-10-10 13:01 | 2023-10-25 07:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 930s Syn Condenser (930s Arcenciel), 930s SVC (930s Arcenciel), 930s 718 (930s Arcenciel) | 2023-10-10 16:30 | 2023-10-26 16:00 | N | Y |  | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 62s 12 (62s Brazeau Plant) | 2023-10-10 23:00 | 2023-11-25 17:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
EPCOR | 72CN10 (987s Clover Bar - Namao), N724 (Namao), 987s CN723 (987s Clover Bar) | 2023-10-11 07:00 | 2023-10-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
SUNCOR | 29EDD-18 29-752-105 (29EDD-18 Firebag) | 2023-10-11 08:00 | 2023-10-11 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12B138-832L (SS-12) | 2023-10-11 08:00 | 2023-10-11 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 868s T1 (868s Keephills Make-Up) | 2023-10-11 08:30 | 2023-10-12 17:30 | N | N |  | Transformer |  |  | For Information Only
BCH | 5L51 (BPA Custer - BCH Ingledow) | 2023-10-11 08:30 | 2023-10-11 17:30 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 89s T2 (89s Ellerslie) | 2023-10-11 09:00 | 2023-10-13 09:30 | N | Y |  | Transformer |  | Realtime conditions, unsolved contingencies | 500 kV, Pre-Condition
ALTALINK | 760L (163s Amoco Empress - 394s Empress) | 2023-10-11 11:30 | 2023-10-11 15:30 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12B138-833L (SS-12) | 2023-10-11 12:00 | 2023-10-11 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2023-10-11 14:30 | 2023-10-20 18:00 | N | Y |  | Shunts | forced outage |  | 500 kV, For Information Only
ALTALINK | 62s 11 (62s Brazeau Plant) | 2023-10-12 03:00 | 2023-10-12 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 337s 138kV Bus (337s Canada Liquidair), 337s T1 (337s Canada Liquidair), 337s T2 (337s Canada Liquidair), 337s 746BW (337s Canadian Liquid Air) | 2023-10-12 06:00 | 2023-10-13 18:00 | N | N |  | Bus, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 749L (648s Metiskow - 749AL tap) | 2023-10-12 07:00 | 2023-10-12 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 358s Amoco Brazeau, 358s 138kV Bus (358s Amoco Brazeau), 844L (358s Amoco Brazeau - 477s Amoco West Pembina), 358s T1 (358s Amoco Brazeau), 358s C1 (358s Amoco Brazeau), 477s 844X (477s Amoco West Pembina), 358s 844W (358s Amoco Brazeau) | 2023-10-12 07:30 | 2023-10-12 17:30 | N | N |  | Station, Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 251s 252 (251s Whitla) | 2023-10-12 10:00 | 2023-10-12 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 251s 352 (251s Whitla) | 2023-10-12 13:00 | 2023-10-12 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe), 20s 56 (20s Ghost), 245s 56E (245s Seebe) | 2023-10-13 07:00 | 2023-10-16 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 251s 552 (251s Whitla), 251s 652 (251s Whitla) | 2023-10-13 07:00 | 2023-10-13 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 702L (137s Sedgewick - 377s AML Hardisty), 137s 702W (137s Sedgewick) | 2023-10-13 07:15 | 2023-10-13 17:45 | N | N |  | Line, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ATCO, CONS | 7L101 (790s Poplar Hill - 944s Lowe Lake), 790s 705 (790s Poplar Hill), 944s 7L101 (944s Lowe Lake) | 2023-10-14 08:00 | 2023-10-22 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation, Affects Cranking Path
ENMAX | 37.81L (SS-37 - SS-38), 37B138-37.81 (SS-37), 38B138-37.81 (SS-38) | 2023-10-14 08:00 | 2023-10-15 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 102s SVC (102s Langdon) | 2023-10-14 20:39 | 2023-10-18 18:00 | N | Y |  | Shunts | forced outage |  | 240 kV, Pre-Condition
ALTALINK | 801L (294s Brazeau Outlet Works - 801AL tap) | 2023-10-15 07:00 | 2023-10-15 18:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2023-10-15 07:00 | 2023-10-19 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
CascadeP | CAS1 Cascade 1 Generator Test, CAS2 Cascade 2 Generator Test | 2023-10-15 08:00 | 2023-10-17 17:00 | N | N |  | Unit
ALTALINK | 727L (65s High River - 727AL tap), 727L (678s Okotoks - 727AL tap), 727AL (142s Magcan - 727L tap), 65s 727N (65s High River), 678s 727 (678s Okotoks), 142s 138kV Bus (142s Magcan), 142s C1 (142s Magcan) | 2023-10-16 07:00 | 2023-10-25 16:00 | N | N |  | Line, Circuit Breaker, Bus, Shunts |  |  | Over/Under Voltage, Pre-Condition
EPCOR | N725 (Namao), 72VN21 (EP 511s Victoria - Namao) | 2023-10-16 07:00 | 2023-10-20 17:00 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 557s CD2401 (557s Castle Downs) | 2023-10-16 07:00 | 2023-10-20 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 710L (56s Boyle - 159s Colinton), 56s 710X (56s Boyle), 159s 710 (159s Colinton) | 2023-10-16 07:15 | 2023-10-16 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 510s ACF21 (510s Sunnybrook), 510s ACF22 (510s Sunnybrook), 510s 1952 (510s Sunnybrook), 510s 2052 (510s Sunnybrook), 510s 36 (510s Sunnybrook), 510s 35 (510s Sunnybrook) | 2023-10-16 07:30 | 2023-10-20 15:30 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39) | 2023-10-16 08:00 | 2023-10-20 15:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, BluEarth | 7LA128 (572s Highland - 7L128 tap), 572S 144CB1 (572s Highland), 572S 144DSW1 (572s Highland) | 2023-10-16 08:00 | 2023-10-18 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX | 38.1TR (SS-38), 38MD138-38.1TR (SS-38) | 2023-10-16 08:00 | 2023-10-20 15:30 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 310p 2752 (310p Sundance) | 2023-10-16 08:30 | 2023-10-25 14:59 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2023-10-16 09:00 | 2023-10-19 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 2L112 (BPA Boundary - BCH Nelway) | 2023-10-16 09:00 | 2023-10-27 17:00 | N | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ATCO, GREENGATEP | 9L16 (755s Cordel - 972s Tinchebray), 972s 902 (972s Tinchebray), 972s 903 (972s Tinchebray), 972s 9L16D2 (972s Tinchebray), 755s 904 (755s Cordel), 755s 905 (755s Cordel), 755s 904B (755s Cordel), 755s 905A (755s Cordel), 755s 9L16D1 (755s Cordel) | 2023-10-16 10:00 | 2023-10-23 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2023-10-16 10:00 | 2023-10-23 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 523s T1 (523s Bullshead) | 2023-10-16 11:00 | 2023-10-26 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 89s T1 (89s Ellerslie) | 2023-10-16 11:00 | 2023-10-19 18:00 | N | Y |  | Transformer |  |  | 240 kV, 500 kV, Pre-Condition
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2023-10-16 12:00 | 2023-10-18 16:32 | N | N |  | Line, Circuit Breaker |  | returned early | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 395s T1 (395s North Holden) | 2023-10-16 12:00 | 2023-10-24 13:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1012s T1 (1012s Deer Hill) | 2023-10-16 13:30 | 2023-10-19 17:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s GT2 (987s Clover Bar), 987s CGB2 (987s Clover Bar) | 2023-10-17 07:00 | 2023-10-19 10:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
EPCOR | 987s GT3 (987s Clover Bar), 987s CGB3 (987s Clover Bar) | 2023-10-17 07:00 | 2023-10-22 03:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
SUNCOR | 29EDD-34 29PT-341 (29EDD-34), 29EDD-34 29-952-143 (29EDD-34), 29EDD-34 29-952-142 (29EDD-34), 29EDD-34 29-652-10301 (29EDD-34), 29EDD-34 29PS-0375 (29EDD-34) | 2023-10-17 08:00 | 2023-10-24 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Outage ended early. | 240 kV, For Information Only
ENMAX | 8.3TR (SS-8) | 2023-10-17 08:00 | 2023-10-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 336s T1 (336s Fincastle), 336s 752 (336s Fincastle) | 2023-10-17 08:00 | 2023-10-17 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 368s T1 (368s Burdett) | 2023-10-17 08:00 | 2023-10-17 11:00 | N | Y |  | Transformer |  |  | For Information Only
ALTALINK | 723L (69s North Barrhead - 724L tap), 69s 723E (69s North Barrhead) | 2023-10-17 08:30 | 2023-10-17 11:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L146 (700s Bonnyville - 970s Bourque) | 2023-10-17 09:00 | 2023-10-17 10:00 | N | Y |  | Line | A fault on 7L146 may result in stability issues for the nearby cogeneration facilities. Open 7L146 for the duration of the telecom outage 1-00412701 |  | Pre-Condition
ALTALINK | 723L (69s North Barrhead - 724L tap), 69s 723E (69s North Barrhead) | 2023-10-17 10:30 | 2023-10-17 15:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 723L (69s North Barrhead - 724L tap), 69s 723E (69s North Barrhead) | 2023-10-17 15:00 | 2023-10-17 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 106s T1 (106s Paddle River), 106s 744 (106s Paddle River) | 2023-10-17 17:00 | 2023-10-18 17:00 | N | N |  | Transformer, Circuit Breaker |  | returned early | For Information Only
EPCOR | 987s CDS33 (987s Cloverbar) | 2023-10-18 07:00 | 2024-02-01 17:00 | N | Y |  | Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 788L (898s Heart Lake - 788AL tap) | 2023-10-18 07:15 | 2023-10-18 17:45 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2023-10-18 08:00 | 2023-10-18 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 11.81L (SS-11 - SS-13), 11B138-11.81 (SS-11), 13B138-11.81 (SS-13) | 2023-10-18 08:00 | 2023-10-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ENMAX | 65B240-D134 (SS-65) | 2023-10-18 08:00 | 2023-10-20 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2023-10-18 08:00 | 2023-10-18 12:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 719L (378s Shell Caroline - 575s Sundre) | 2023-10-18 08:00 | 2023-10-18 15:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
Saskpower | Sask Power S1C line | 2023-10-18 09:00 | 2023-10-18 12:00 | N | Y |  | Line | Outage Name: SW 811LM |  | Limits ATC
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2023-10-18 13:00 | 2023-10-18 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 825s 907 (825s Whitefish Lake) | 2023-10-19 09:30 | 2023-10-19 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK, TRANSALTA | 528s RTU/SCADA (528s Blue Trail Wind Farm) | 2023-10-19 10:00 | 2023-10-19 13:00 | N | N |  | Terminal Equipment | TransAlta is requesting a communication outage for firewall replacement at Blue Trail 528s on October 19, 2023, from 10:00 to 13:00. During this outage, the site will not be able to respond to WPM curtailments and the Wind Control Center will not be able to monitor or control the turbines, however we will have full control of the substation and the DVAR. |  | Affects Visibility
ALTALINK | 251s 252 (251s Whitla) | 2023-10-19 10:00 | 2023-10-19 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 368s 879 (368s Burdett), 879L (368s Burdett - 879L tap) | 2023-10-19 13:00 | 2023-10-19 16:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 251s 352 (251s Whitla) | 2023-10-19 13:00 | 2023-10-19 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 825s 905 (825s Whitefish Lake) | 2023-10-19 13:00 | 2023-10-20 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 408L (51s Wainwright - 252s Jarrow) | 2023-10-20 07:00 | 2023-10-20 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 251s 652 (251s Whitla), 251s 552 (251s Whitla) | 2023-10-20 07:00 | 2023-10-20 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 39.2TR (SS-39) | 2023-10-20 08:00 | 2023-10-20 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 330p 500kV Bus 2 (330p Genesee), 330P 12TC2 (330p Genesee), 330p 1209 (330p Genesee), 330p 1206 (330p Genesee), 330p 1203 (330p Genesee), 330p 809 (330p Genesee), 330p 12TC2D (330p Genesee) | 2023-10-21 07:00 | 2023-11-11 16:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 264s 240kV Bus 2 (264s Elkwater), 264s 352 (264s Elkwater), 264s 252 (264s Elkwater) | 2023-10-21 12:01 | 2023-11-18 16:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L106 (834s Wesley Creek - 905s Meikle), 834s 7L106D2 (834s Wesley Creek) | 2023-10-21 18:00 | 2023-10-26 14:30 | N | Y |  | Line, Switch
EPCOR | 8L10 (330P Genesee - Fording Coal Mine), 330p 808 (330p Genesee) | 2023-10-22 07:00 | 2023-10-22 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27), 27MD69-27.2TR (SS-27) | 2023-10-22 08:00 | 2023-10-22 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ENEL | 7L65 (709s Vegreville - 7LA65 tap), 7L65 (710s Vermilion - 7LA65 tap), 7LA65 (708s Grizzly Bear - 7L65 tap), 710s 703 (710s Vermilion), 709s 703 (709s Vegreville), 708s 52T1 (708s Grizzly Bear), 708s 89-L1 (708s Grizzly Bear) | 2023-10-22 08:00 | 2023-10-22 20:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Over/Under Voltage, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty) | 2023-10-23 07:00 | 2023-11-15 17:00 | N | N |  | Line |  |  | For Information Only, Pre-Condition
EPCOR | N726 (Namao), 72NW15 (Namao - Woodcroft) | 2023-10-23 07:00 | 2023-10-27 17:00 | N | N |  | Circuit Breaker, Line |  |  | For Information Only, Pre-Condition
ALTALINK | 189L (373s Madden - 418L tap), 373s Madden, 373s 752 (373s Madden), 373s 25 (373s Madden) | 2023-10-23 08:00 | 2023-10-31 09:00 | N | N |  | Line, Station, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 11.83L (SS-162 - SS-11), 11B138-11.83 (SS-11) | 2023-10-23 08:00 | 2023-10-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 24.2TR (SS-24) | 2023-10-23 08:00 | 2023-10-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2023-10-23 08:00 | 2023-11-28 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 491L tap), 526s 252 (526s Buffalo Creek) | 2023-10-23 09:00 | 2023-10-27 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 786s 703T (786s High Level), 786s SVC (786s High Level) | 2023-10-23 10:00 | 2023-10-25 15:00 | N | Y |  | Transformer, Shunts |  |  | Pre-Condition
ALTALINK | 320p T1 (320p Keephills), 320p 91 (320p Keephills) | 2023-10-23 12:00 | 2023-10-26 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 45s T1 (45s Bretona) | 2023-10-23 12:00 | 2023-10-26 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 722L (107s Westfield - 368s Burdett), 107s Westfield, 368s 722X (368s Burdett) | 2023-10-23 13:00 | 2023-10-27 12:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | For Information Only, Restricts Generation
ALTALINK | 370s 852 (370s North Lethbridge) | 2023-10-23 13:00 | 2023-10-23 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 185L (379s Shell Canada Waterton - 415s Drywood), 379s 185E (379s Shell Canada Waterton) | 2023-10-24 07:00 | 2023-10-31 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 12L41 (510s Sunnybrook - 939s Livock), 12L44 (939s Livock - 951s Thickwood Hills), 951s 1201T (951s Thickwood Hills), 951s 1201TA (951s Thickwood Hills), 951s 1205 (951s Thickwood Hills), 951s 1205A (951s Thickwood Hills), 951s 1205B (951s Thickwood Hills), 951s 1206 (951s Thickwood Hills), 951s 1206A (951s Thickwood Hills), 951s 1206B (951s Thickwood Hills), 951s 1213R (951s Thickwood HIlls), 951s 1213 (951s Thickwood Hills), 951s 1213A (951s Thickwood Hills), 951s 12L44D1 (951s Thickwood Hills), 951s 1204A (951s Thickwood Hills), 939s 12L44D1 (939s Livock), 939s 1213R (939s Livock), 939s 1214R (939s Livock), 939s 1216R (939s Livock), 939s 1206 (939s Livock), 939s 1207 (939s Livock), 939s 1214 (939s Livock), 939s 1216 (939s Livock), 939s 1204A (939s Livock), 939s 1205B (939s Livock), 939s 1206A (939s Livock), 939s 1206B (939s Livock), 939s 1207A (939s Livock), 939s 1207B (939s Livock), 939s 1208A (939s Livock), 939s 1209B (939s Livock), 939s 1213A (939s Livock), 939s 1214A (939s Livock), 939s 1216A (939s Livock), 939s 12L41D1 (939s Livock) | 2023-10-24 08:00 | 2023-10-26 13:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker, Shunts |  |  | 500 kV, Pre-Condition
ATCO, ALTALINK | 1241L (510s Sunnybrook - 939s Livock) | 2023-10-24 08:00 | 2023-10-27 17:30 | N | Y |  | Line |  |  | 500 kV, For Information Only
ALTALINK | 510s 4052 (510s Sunnybrook), 510s T1 (510s Sunnybrook) | 2023-10-24 08:00 | 2023-10-24 17:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 368s 612 (368s Burdett), 368s 138 kV Bus 2 (368s Burdett), 368s C1 (368s Burdett), 612L (336s Fincastle - 368s Burdett), 722L (107s Westfield - 368s Burdett), 368s 722X (368s Burdett), 368s T2 (368s Burdett) | 2023-10-24 09:00 | 2023-10-24 17:00 | N | Y |  | Circuit Breaker, Transformer, Shunts, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK, BHE Canada | 120s 452 (120s Picture Butte) | 2023-10-24 09:30 | 2023-10-24 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, Lethbridge | 824L (593s Lakeview - 618s Riverbend), 593s 824L (593s Lakeview), 618s 824 (618s Riverbend) | 2023-10-25 07:00 | 2023-10-25 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 983L (244s Bowmanton - 983L tap), 983L (251s Whitla - 983L tap), 983AL (1019s Woolchester - 983L tap), 244s 552 (244s Bowmanton), 244s 652 (244s Bowmanton), 251s 552 (251s Whitla), 251s 652 (251s Whitla), 244s 1074 (244s Bowmanton) | 2023-10-25 07:01 | 2023-10-25 12:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 9.3TR (SS-9) | 2023-10-25 08:00 | 2023-10-26 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | ML-3 (D05) | 2023-10-25 08:00 | 2023-10-26 08:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 510s 3852 (510s Sunnybrook), 510s T2 (510s Sunnybrook) | 2023-10-25 08:00 | 2023-10-25 17:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ENMAX | 27.1TR (SS-27) | 2023-10-25 08:00 | 2023-10-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 634s Shell Raven River, 634s T1 (634s Shell Raven River), 719BL (634s Shell Raven River - 719L tap), 634s 719 (634s Shell Raven River) | 2023-10-25 09:30 | 2023-10-26 16:30 | N | N |  | Station, Transformer, Line, Circuit Breaker |  |  | For Information Only
ALTALINK, BHE Canada | 120s 252 (120s Picture Butte) | 2023-10-25 09:30 | 2023-10-25 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO, GREENGATEP | 9L59 (972s Tinchebray - 9LA59 tap), 972s 901 (972s Tinchebray), 972s 902 (972s Tinchebray), 972s 9L59D2 (972s Tinchebray) | 2023-10-25 10:00 | 2023-10-27 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
SDLP | SDL1 Saddlebrook Solar Generator Test | 2023-10-25 10:20 | 2024-01-05 17:01 | N | N |  | Unit
ALTALINK | 989L (77s Sagitawah - 310p Sundance), 310p 2752 (310p Sundance), 77s 989X (77s Sagitawah) | 2023-10-25 15:00 | 2023-10-25 15:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 542s T1 (542s Ervick) | 2023-10-26 06:00 | 2023-10-26 18:00 | N | N |  | Transformer |  |  | For Information Only
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 593s 823L (593s Lakeview), 146s 823L (146s Macdonald) | 2023-10-26 07:00 | 2023-10-26 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2023-10-26 07:00 | 2023-11-03 14:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, For Information Only, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell) | 2023-10-26 07:00 | 2023-11-03 14:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 510s 3952 (510s Sunnybrook) | 2023-10-26 08:30 | 2023-10-26 16:30 | N | N |  | Switch |  |  | For Information Only
ALTALINK | 284s T1 (284s Nose Creek) | 2023-10-26 08:30 | 2023-10-30 12:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 754s 701T (754s Ksituan River) | 2023-10-26 11:00 | 2023-10-26 14:06 | N | N |  | Transformer |  | Done early | For Information Only
ALTALINK, ENMAX | 688L (199s East Airdrie - 688AL tap), 688AL (284s Nose Creek - 688L tap), 688L (653s Summit - 688AL tap), 199s 688 (199s East Airdrie), 653s 688 (653s Summit) | 2023-10-27 07:00 | 2023-10-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162B240-RB136 (SS-162) | 2023-10-27 08:00 | 2023-10-27 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Restricts Generation
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 781L (71s Lamoureux - 172s Sherritt), 71s 152 (71s Lamoureux), 71s 252 (71s Lamoureux), 71s 352 (71s Lamoureux), 71s T1 (71s Lamoureux), 71s 138kV West Bus (71s Lamoureux) | 2023-10-27 09:00 | 2023-10-27 16:00 | N | Y |  | Line, Circuit Breaker, Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 162B240-RB135 (SS-162), 2-GSU-XF-0002 (SS-162) | 2023-10-27 12:00 | 2023-10-27 16:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ATCO | 951s SVC (951s Thickwood), 951s 919 (951s Thickwood Hills) | 2023-10-27 16:00 | 2023-11-18 15:08 | N | Y |  | Shunts, Circuit Breaker |  |  | For Information Only, Pre-Condition
ERSP | SHH1 Sharp Hill Wind Generator Test | 2023-10-28 07:00 | 2024-01-30 14:00 | N | Y |  | Unit
ENMAX | 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13.3TR (SS-13), 13B138-2.83 (SS-13), 13B138-3.84 (SS-13), 3B138-3.84 (SS-3), 13MD138-13.3TR (SS-13) | 2023-10-28 08:00 | 2023-10-29 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.2TR (SS-21) | 2023-10-28 08:00 | 2023-10-28 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27) | 2023-10-28 08:00 | 2023-12-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.1TR (SS-21) | 2023-10-28 12:00 | 2023-10-28 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 225L (225s Magrath - 385s Spring Coulee), 225L (229s Glenwood - 385s Spring Coulee), 385s 69kV Bus (385s Spring Coulee), 385s T1 (385s Spring Coulee), 385s T3 (385s Spring Coulee), 385s 67 (385s Spring Coulee), 385s 225 (385s Spring Coulee) | 2023-10-29 07:00 | 2023-10-29 15:00 | N | N |  | Line, Bus, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 39.3TR (SS-39) | 2023-10-29 08:00 | 2023-10-29 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 39.4TR (SS-39) | 2023-10-29 12:00 | 2023-10-29 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 385s T1 (385s Spring Coulee) | 2023-10-29 15:01 | 2023-10-31 12:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T3 (Namao) | 2023-10-30 07:00 | 2023-10-31 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T2 (Rossdale), R721 (Rossdale), R723 (Rossdale), RAB2 (Rossdale) | 2023-10-30 07:00 | 2023-11-10 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Mildred T6 (Syncrude Mildred Lake), 635 (Syncrude Mildred Lake), 6245 (Syncrude Mildred Lake), 6335 (Syncrude Mildred Lake) | 2023-10-30 08:00 | 2023-11-09 20:00 | N | Y |  | Transformer, Circuit Breaker |  | Delayed due to another unit tripping off. Might have to find out if end date changes. | Restricts Generation
ENMAX | 26.1TR (SS-26) | 2023-10-30 08:00 | 2023-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.81L (SS-2 - SS-9), 9B138-2.81 (SS-9) | 2023-10-30 08:00 | 2023-11-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
Syncrude | Mildred T14 (Syncrude Mildred Lake) | 2023-10-30 08:00 | 2023-11-17 18:00 | N | N |  | Transformer |  | 5 year maintenance and repairs. Extended | For Information Only
ENMAX | 33.2TR (SS-33) | 2023-10-30 08:00 | 2023-11-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2023-10-30 09:00 | 2023-11-02 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe), 198s 461 (198s Blackfalds), 212s 461 (212s N.E. Lacombe) | 2023-10-30 09:30 | 2023-11-03 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 812L (65s High River - 812AL tap), 65s 812W (65s High River) | 2023-10-30 09:30 | 2023-10-30 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 739s 702T (739s Edith Lake) | 2023-10-30 10:00 | 2023-11-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2023-10-30 10:00 | 2023-11-06 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 722L (107s Westfield - 368s Burdett), 368s 722X (368s Burdett), 107s 722N (107s Westfield), 107s T1 (107s Westfield), 107s 2 (107s Westfield) | 2023-10-30 11:00 | 2023-11-03 12:00 | N | Y |  | Line, Circuit Breaker, Switch, Transformer |  |  | Restricts Generation
ATCO | 885s 704 (885s McMillan), 885s 902T (885s McMillan), 885S 702TD (885s McMillan) | 2023-10-30 11:00 | 2023-11-27 12:00 | N | Y |  | Circuit Breaker, Transformer, Switch | 885S McMillan sub Protection Upgrade: Complete protection cut over and Commissioning of new protection on 902T, 704/7L02 Line protection, 25kV Reactor protection. On Monday October 23, 2023 will extend GOI to new isolation points: 501A,502TD1,502TD1,703B,7L02D2,906B,902A,Switch @ Round Hill (Alta Link). The following will be OOS: 900BS2, 903,902,9L55,902T,704/7L02,144kV Bus. Complete cut over and Commissioning of new protection to 240kV bus, 903,902,9L55 line protection. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 283s T1 (283s Violet Grove) | 2023-10-30 12:30 | 2023-11-09 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799s T1 (799s Coleman) | 2023-10-30 13:00 | 2023-11-01 10:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 557s CD2401 (557s Castle Downs) | 2023-10-31 07:00 | 2023-10-31 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 65s 753E (65s High River), 753L (65s High River - 253s Blackie) | 2023-10-31 07:00 | 2023-10-31 12:59 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, WCLP | 763AL (447s Enchant - 763L tap), 763L (158s Vauxhall - 763AL tap), 763L (28s West Brooks - 763AL tap), 447s Enchant, 1039s Wheatcrest, 158s 763N (158s Vauxhall), 28s 31 (28s West Brooks), 28s 47 (28s West Brooks), 28s 763X (28s West Brooks), 447s 322X (447s Enchant), 447s 408N (447s Enchant), 447s 409W (447s Enchant), 447s 410W (447s Enchant), 447s 763A (447s Enchant) | 2023-10-31 08:00 | 2023-11-09 17:00 | N | Y |  | Line, Station, Circuit Breaker, Switch |  | Needed one more day to finish | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2023-10-31 08:00 | 2023-12-15 09:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.2C (SS-14), 14.1C (SS-14) | 2023-10-31 08:00 | 2023-10-31 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5) | 2023-10-31 08:00 | 2023-12-14 08:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 294s T1 (294s Brazeau Outlet Works) | 2023-10-31 08:30 | 2023-10-31 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 72s 752 (72s Leismer) | 2023-10-31 09:30 | 2023-10-31 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 65s 434 (65s High River), 434L (65s High River - 237s Foothills) | 2023-10-31 13:00 | 2023-10-31 18:00 | N | N |  | Circuit Breaker, Line |  |  | Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 1CB2 (BCH Natal), 799s 786W (799s Coleman) | 2023-11-01 07:00 | 2023-11-05 17:00 | N | Y |  | Line, Circuit Breaker | WebOMS ID: 14530104 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 926L (17s Benalto - 310p Sundance), 310p 2552 (310p Sundance), 310p 2652 (310p Sundance) | 2023-11-01 07:00 | 2023-11-14 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 26.2TR (SS-26) | 2023-11-01 08:00 | 2023-11-02 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 3.4TR (SS-3) | 2023-11-01 08:00 | 2023-11-01 12:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 65s T1 (65s High River), 65s 13N (65s High River), 13L (65s High River - 392s Black Diamond) | 2023-11-01 08:00 | 2023-11-01 13:00 | N | N |  | Transformer, Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 677L (305s Acheson - 595s Spruce Grove), 453L (305s Acheson - 367s Harry Smith), 305s T2 (305s Acheson), 305s 138kV Bus 2 (305s Acheson), 305s 677 (305s Acheson), 305s 1152 (305s Acheson), 305s 453 (305s Acheson), 305s Protection & Control (305s Acheson) | 2023-11-01 08:00 | 2023-11-01 18:00 | N | N |  | Line, Transformer, Bus, Circuit Breaker, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 29EDD-1 29EDD1s452 (29EDD-1 Millennium), 29EDD-1 29EDD1s552 (29EDD-1 Millennium), 29EDD-1 29EDD1SPL9-1 (29EDD-1 Millennium) | 2023-11-01 08:01 | 2023-11-23 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only, Affects Cranking Path
ALTALINK | 256s C1 (256s Harmattan) | 2023-11-01 08:30 | 2023-11-01 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 799s T1 (799s Coleman) | 2023-11-01 10:01 | 2023-11-06 08:59 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 24.82L (SS-24 - SS-65) | 2023-11-01 12:00 | 2023-11-03 16:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 65s T2 (65s High River) | 2023-11-01 13:00 | 2023-11-01 18:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
EPCOR | T2 (Namao) | 2023-11-02 07:00 | 2023-11-03 17:00 | N | N |  | Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 65s T3 (65s High River) | 2023-11-02 07:00 | 2023-11-02 13:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 37s T5 (37s North Calder) | 2023-11-02 07:00 | 2023-11-02 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 23.3TR (SS-23) | 2023-11-02 08:00 | 2023-11-02 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 691L (74s Janet - 419s Chestermere), 419s 691 (419s Chestermere), 74s 691 (74s Janet) | 2023-11-02 09:00 | 2023-11-03 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
SUNCOR | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2023-11-03 02:45 | 2023-11-07 18:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Restricts Generation
ALTALINK | 1082L (63s Red Deer - 287s Hazelwood), 63s 2652 (63s Red Deer), 63s 2752 (63s Red Deer), 63s 1082 (63s Red Deer) | 2023-11-03 07:00 | 2023-11-06 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV
ATCO | 7L129 (710s Vermilion - 7LA129 tap) | 2023-11-03 08:00 | 2023-11-07 19:30 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 983s T1 (983s Cadomin), 501L (426s Coalspur - 501CL tap) | 2023-11-03 09:00 | 2023-11-08 17:00 | N | N |  | Transformer, Line |  |  | Pre-Condition
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap), 811s 708 (811s Clairmont Lake), 7L22D2 (7L88 tap) | 2023-11-03 09:00 | 2023-11-03 15:00 | N | Y |  | Line, Circuit Breaker, Switch |  | Realtime conditions | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 162B240-RB133 (SS-162) | 2023-11-03 12:00 | 2023-11-03 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 987s GT3 (987s Clover Bar) | 2023-11-04 07:00 | 2023-11-07 11:00 | N | Y |  | Transformer |  |  | For Information Only
ALTALINK | 659s T1 (659s Pegasus Lake), 659s T2 (659s Pegasus Lake), 659s 526B (659s Pegasus Lake), 659s 189 (659s Pegasus Lake), 659s 389 (659s Pegasus Lake) | 2023-11-04 08:00 | 2023-11-04 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX | 39.82L (SS-39 - SS-162), 162B138-RB82 (SS-162), 162B138-RB83 (SS-162), 39B138-39.82 (SS-39) | 2023-11-04 08:00 | 2023-11-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
BCH | 5L77 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2023-11-05 11:00 | 2023-11-05 16:00 | N | Y |  | Line |  |  | Limits ATC, 500 kV
ALTALINK, Lethbridge | 824L (593s Lakeview - 618s Riverbend), 618s 824 (618s Riverbend), 593s 824L (593s Lakeview) | 2023-11-05 13:00 | 2023-11-08 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s Victoria T5 (EP 511s Victoria), EP 511s V728 (EP 511s Victoria), EP 511s V727 (EP 511s Victoria), EP 511s V2401 (EP 511s Victoria), EP 511s VDS20 (EP 511s Victoria) | 2023-11-06 07:00 | 2023-11-06 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 170L (632s Russell - 799s Coleman), 799s 170E (799s Coleman) | 2023-11-06 07:30 | 2023-11-06 09:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10.1TR (SS-10), 10B138-832 (SS-10), 10MD138-10.1TR (SS-10) | 2023-11-06 08:00 | 2023-11-06 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition, Affects Cranking Path
CMH | MHS-3 MH69-T31 (MHS-3 South Ridge) | 2023-11-06 08:00 | 2023-11-09 15:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.6TR (SS-1) | 2023-11-06 08:00 | 2023-11-06 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12B138-832L (SS-12) | 2023-11-06 08:00 | 2023-11-07 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
BCH | 1L274 (978s BCH Britt Creek - BCH Greenhills tap) | 2023-11-06 09:00 | 2023-11-06 17:00 | Y | N |  | Line | 1L274 (Britt Creek - 1D4L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
ALTALINK | 646L (237s Foothills - 678s Okotoks), 678s 646 (678s Okotoks) | 2023-11-06 09:30 | 2023-11-06 16:30 | N | N |  | Line, Circuit Breaker |  |  | Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 722L (107s Westfield - 368s Burdett), 368s 722X (368s Burdett), 107s 722N (107s Westfield), 107s T1 (107s Westfield), 107s 2 (107s Westfield) | 2023-11-06 11:00 | 2023-11-10 12:00 | N | Y |  | Line, Circuit Breaker, Switch, Transformer |  |  | Restricts Generation
ALTALINK | 151s T1 (151s Strathmore) | 2023-11-06 11:00 | 2023-11-13 10:59 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 1.5TR (SS-1) | 2023-11-06 12:01 | 2023-11-06 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
EPCOR | T1 (Namao), N721 (Namao), NDS8 (Namao), NAB1 (Namao) | 2023-11-07 07:00 | 2023-11-10 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 678s 850 (678s Okotoks), 850L (525s Carseland - 678s Okotoks) | 2023-11-07 07:00 | 2023-11-07 13:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.8TR (SS-1) | 2023-11-07 08:00 | 2023-11-07 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12) | 2023-11-07 08:00 | 2023-11-07 16:00 | N | Y |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 61s 138kV Bus 2 (61s Lodgepole), 202L (61s Lodgepole - 62s Brazeau Plant), 61s T2 (61s Lodgepole), 61s 202X (61s Lodgepole), 62s 202 (62s Brazeau Plant), 61s 11 (61s Lodgepole) | 2023-11-07 08:00 | 2023-11-07 17:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 31.3TR (SS-31) | 2023-11-07 08:00 | 2023-11-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 426s 501W (426s Coalspur), 426s T1 (426s Coalspur) | 2023-11-07 08:30 | 2023-11-07 17:30 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | ATC 793s 701 (ATC 793s West Peace River), 7L51 (ATC 793s West Peace River - 927s Buchanan Creek), 927s 7L51D4 (927s Buchanan Creek) | 2023-11-07 09:00 | 2023-11-07 12:00 | N | Y |  | Circuit Breaker, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 824s 701T (824s Fieldgate), 824s 701 (824s Fieldgate) | 2023-11-07 09:30 | 2023-11-07 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 7L75 (ATC 793s West Peace River - 800s Friedenstal), ATC 793s 702 (ATC 793s West Peace River), 800s 701 (800s Friedenstal) | 2023-11-07 12:01 | 2023-11-07 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 678s T1 (678s Okotoks), 678s 352 (678s Okotoks) | 2023-11-07 13:00 | 2023-11-07 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2023-11-08 07:00 | 2023-11-16 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 678s T2 (678s Okotoks), 678s 452 (678s Okotoks) | 2023-11-08 07:00 | 2023-11-08 13:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 6.1TR (SS-6) | 2023-11-08 08:00 | 2023-11-08 12:00 | N | N |  | Transformer |  |  | For Information Only
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 593s 823L (593s Lakeview), 146s 823L (146s Macdonald) | 2023-11-08 08:00 | 2023-11-08 13:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12B138-833L (SS-12), 2MD138-833L (SS-2) | 2023-11-08 08:00 | 2023-11-09 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 62s C1 (62s Brazeau Plant) | 2023-11-08 08:30 | 2023-11-08 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 151s 765W (151s Strathmore), 419s 765 (419s Chestermere) | 2023-11-08 09:00 | 2023-11-08 10:59 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 7L27 (ATC 793s West Peace River - 834s Wesley Creek), ATC 793s 705 (ATC 793s West Peace River) | 2023-11-08 09:00 | 2023-11-08 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2023-11-08 09:00 | 2023-11-08 15:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 790s 701T (790s Poplar Hill) | 2023-11-08 09:00 | 2023-11-26 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2023-11-08 09:00 | 2023-11-08 15:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 733L (151s Strathmore - 428S Namaka), 151s 733E (151s Strathmore), 428s 733N (428s Namaka) | 2023-11-08 11:00 | 2023-11-08 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Overload, Pre-Condition, Restricts Generation
ENMAX | 33.1TR (SS-33) | 2023-11-08 12:00 | 2023-11-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | ATC 793s 706C (ATC 793s West Peace River) | 2023-11-08 12:01 | 2023-11-08 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 678s T3 (678s Okotoks), 678s 552 (678s Okotoks) | 2023-11-08 13:00 | 2023-11-08 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 151s C1 (151s Strathmore) | 2023-11-08 14:00 | 2023-11-08 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 820L (254s Coaldale - 820AL tap), 820AL (315s Chin Chute - 820L tap), 820L (820AL tap - 820BL tap), 820BL (967s Redcoat - 820L tap), 820L (67s Stirling - 820BL tap), 254s 820 (254s Coaldale) | 2023-11-09 07:00 | 2023-11-17 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 11.82L (SS-11 - SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14) | 2023-11-09 08:00 | 2023-11-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 36.3TR (SS-36) | 2023-11-09 08:00 | 2023-11-09 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-11-09 09:00 | 2023-11-09 17:00 | N | Y |  | Line |  |  | 240 kV, Limits ATC
ATCO | 7L75 (ATC 793s West Peace River - 800s Friedenstal), 800s 701 (800s Friedenstal) | 2023-11-09 09:00 | 2023-11-09 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-11-09 09:00 | 2023-11-09 17:00 | N | N |  | Line |  |  | 240 kV, Limits ATC
ATCO | 800s 702 (800s Friedenstal), 7L73 (730s Rycroft - 829s Boucher Creek) | 2023-11-09 12:01 | 2023-11-09 15:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 719L (378s Shell Caroline - 719BL tap), 719L (378s Shell Caroline - 575s Sundre), 575s 719N (575s Sundre), 378s 719N (378s Shell Caroline), 378s 719X (378s Shell Caroline), 378s 552 (378s Shell Caroline), 378s 452 (378s Shell Caroline), 378s 652 (378s Shell Caroline) | 2023-11-10 08:00 | 2023-11-16 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 162B138-RB85 (SS-162) | 2023-11-10 08:00 | 2023-11-10 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 368s C2 (368s Burdett) | 2023-11-10 08:00 | 2023-11-10 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 800s 703C (800s Friedenstal) | 2023-11-10 09:00 | 2023-11-10 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 162B138-RB82 (SS-162) | 2023-11-10 12:00 | 2023-11-10 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T2 (Rossdale) | 2023-11-10 17:00 | 2024-04-09 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 199s T1 (199s East Airdrie) | 2023-11-11 07:00 | 2023-11-11 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 151s 765W (151s Strathmore), 419s 765 (419s Chestermere) | 2023-11-11 09:00 | 2023-11-11 12:59 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 733L (151s Strathmore - 428S Namaka), 151s 733E (151s Strathmore), 428s 733N (428s Namaka) | 2023-11-11 13:00 | 2023-11-11 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Overload, Pre-Condition, Restricts Generation
ALTALINK | 199s T2 (199s East Airdrie) | 2023-11-12 07:00 | 2023-11-12 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.3TR (SS-3) | 2023-11-12 08:00 | 2023-11-12 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.4TR (SS-3) | 2023-11-12 12:00 | 2023-11-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 631L (186s Dry Creek - 199s East Airdrie), 199s 631 (199s East Airdrie), 186s 631 (186s Dry Creek) | 2023-11-13 07:00 | 2023-11-13 11:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 987s GT2 (987s Clover Bar) | 2023-11-13 07:00 | 2023-11-16 10:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 199s C1 (199s East Airdrie) | 2023-11-13 07:00 | 2023-11-13 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32), 40B138-32.83 (SS-40) | 2023-11-13 08:00 | 2023-11-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14) | 2023-11-13 08:00 | 2023-11-14 10:48 | N | N |  | Line, Transformer, Circuit Breaker |  | Completed early | Creates Radial Feeds, Firm Load Loss
ALTALINK | 151s C1 (151s Strathmore) | 2023-11-13 09:00 | 2023-11-13 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 9L953 (574s Nilrem - 755s Cordel) | 2023-11-13 10:00 | 2023-11-16 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 151s T1 (151s Strathmore) | 2023-11-13 11:00 | 2023-11-16 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 612L (336s Fincastle - 368s Burdett), 368s 612 (368s Burdett), 336s 612 (336s Fincastle) | 2023-11-13 11:00 | 2023-11-23 12:06 | N | Y |  | Line, Circuit Breaker |  | Back Early | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 199s 688 (199s East Airdrie), 688L (199s East Airdrie - 688AL tap) | 2023-11-13 13:00 | 2023-11-13 17:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 89s 1852 (89s Ellerslie) | 2023-11-13 23:08 | 2023-12-21 14:45 | N | Y |  | Circuit Breaker |  |  | 500 kV
ALTALINK | 15s T1 (15s Fort Macleod) | 2023-11-14 07:00 | 2023-11-20 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T3 (Meadowlark) | 2023-11-14 07:00 | 2023-11-18 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.80L (SS-9 - SS-31), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31) | 2023-11-14 08:00 | 2023-11-14 12:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 275s T2 (275s Jenner), 275s 46 (275s Jenner), 275s 2252 (275s Jenner) | 2023-11-14 08:00 | 2023-11-16 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ATCO | 786s 701T (786s High Level) | 2023-11-14 09:00 | 2023-11-22 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 834s 707 (834s Wesley Creek) | 2023-11-14 09:00 | 2023-11-14 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2023-11-14 09:00 | 2023-11-14 13:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2023-11-14 09:00 | 2023-11-20 16:00 | N | Y |  | Line |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 234L (310p Sundance - 505L tap), 310P 234N (310p Sundance) | 2023-11-14 09:30 | 2023-11-21 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2023-11-14 10:00 | 2023-11-20 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 9.80L (SS-9 - SS-31), 31B138-9.80 (SS-31), 9B138-9.80 (SS-9) | 2023-11-14 12:01 | 2023-11-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 834s 702 (834s Wesley Creek) | 2023-11-14 12:01 | 2023-11-15 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 827s SVC (827s Cranberry Lake), 827s 703 (827s Cranberry Lake) | 2023-11-14 13:00 | 2023-11-19 17:30 | N | Y |  | Shunts, Circuit Breaker | Upgrade Valve Electronics, replace HMI 5-10 minutes loss of SCADA during updates | Back early | Pre-Condition
ALTALINK | 799s T1 (799s Coleman) | 2023-11-14 17:00 | 2023-11-15 09:59 | N | N |  | Transformer |  |  | For Information Only
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake) | 2023-11-14 18:01 | 2024-02-19 07:59 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ALTALINK | 170L (632s Russell - 799s Coleman), 799s 170E (799s Coleman), 632s 452 (632s Russell) | 2023-11-15 08:00 | 2023-11-20 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.81L (SS-11 - SS-13), 13B138-11.81 (SS-13), 11B138-11.81 (SS-11) | 2023-11-15 08:00 | 2023-11-15 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 37.2TR (SS-37) | 2023-11-15 08:00 | 2023-11-15 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L131 (834s Wesley Creek - 905s Meikle), 834s 708 (834s Wesley Creek), 834s 710 (834s Wesley Creek) | 2023-11-15 09:00 | 2023-11-15 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 13B138-13.82 (SS-13), 22B138-13.82 (SS-22) | 2023-11-15 12:00 | 2023-11-15 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.1TR (SS-162) | 2023-11-16 08:00 | 2023-11-16 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2023-11-16 09:00 | 2023-11-16 17:00 | N | Y |  | Line |  |  | 240 kV, Limits ATC
ALTALINK | 421s T2 (421s Hays), 421s 467E (421s Hays), 421s 52-1 (421s Hays), 421s 52-F01 (421s Hays), 421s 52-F02 (421s Hays) | 2023-11-16 09:00 | 2023-11-16 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 264s 252 (264s Elkwater) | 2023-11-16 10:00 | 2023-11-18 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ENMAX | 3.84L (SS-3 - SS-13), 13B138-3.84 (SS-13), 3B138-3.84 (SS-3) | 2023-11-16 12:00 | 2023-11-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.2TR (SS-162) | 2023-11-17 08:00 | 2023-11-17 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 151s T2 (151s Strathmore) | 2023-11-17 09:00 | 2023-11-22 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 922L (17s Benalto - 310p Sundance), 310p 1952 (310p Sundance), 310p 2052 (310p Sundance) | 2023-11-18 07:00 | 2023-11-28 13:30 | N | Y |  | Line, Circuit Breaker |  | Outage returned early | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 593s T2 (593s Lakeview), 593s 823L (593s Lakeview), 146s 823L (146s Macdonald) | 2023-11-18 08:00 | 2023-12-01 13:00 | N | N |  | Line, Transformer, Circuit Breaker |  | Good weather conditions | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 832s 701T (832s Blumenort) | 2023-11-18 09:00 | 2023-11-19 17:00 | N | N |  | Transformer | {OUTAGE REASON: " Tie 5L458 to 5L596 via 500D4 " Disconnect U/G cables from 501TD to 500D9} |  | For Information Only
ATCO | 813s 503R (813s Little Smoky) | 2023-11-18 15:08 | 2023-11-24 17:00 | N | N |  | Shunts | Atco has informed the SC that 401R @ 848s Ruth Lake will be unavailable until further notice. The breaker needs to be replaced and the earliest estimate is January 2023. Feb 2023 update: Breaker will not be replaced until the 848S Ruth Lake Substation Rebuild end of Q3 2024 |  | Pre-Condition
ENMAX | 13.3TR (SS-13) | 2023-11-19 08:00 | 2023-11-19 10:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 71s 552 (71s Lamoureux), 71s 652 (71s Lamoureux), 38s 761N (38s East Edmonton), 71s 761W (71s Lamoureux) | 2023-11-19 10:30 | 2023-11-22 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Overload, Pre-Condition, Prevents Normal Events
EPCOR | 987s GT1 (987s Clover Bar), 987s CGB1 (987s Clover Bar) | 2023-11-20 07:00 | 2023-11-22 10:00 | N | Y |  | Transformer, Circuit Breaker |  | In service and EPCOR has no record of it | Restricts Generation
EPCOR | T2 (Rossdale), R723 (Rossdale), R721 (Rossdale), RAB2 (Rossdale) | 2023-11-20 07:00 | 2023-12-05 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ENMAX | 752L (653s Summit - 752AL tap), 653s 752 (653s Summit) | 2023-11-20 07:00 | 2023-11-20 11:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 987s T2 (987s Clover Bar), 987s T4 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2408 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s CDS31 (987s Clover Bar), 987s CDS39 (987s Cloverbar) | 2023-11-20 07:00 | 2023-11-22 07:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 102s SVC (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon), 102s 7189 (102s Langdon) | 2023-11-20 07:30 | 2023-11-22 08:30 | N | Y |  | Shunts, Circuit Breaker, Switch |  | Back early | 240 kV, Pre-Condition
ENMAX | 32.3TR (SS-32) | 2023-11-20 08:00 | 2023-11-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47.1TR (SS-47) | 2023-11-20 08:00 | 2023-11-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.2TR (SS-13) | 2023-11-20 08:00 | 2023-11-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 391s T1 (391s Balzac), 391s 30 (391s Balzac) | 2023-11-20 09:30 | 2023-11-20 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L172 (739s Edith Lake - 743s Sarah Lake), 739s 702 (739s Edith Lake), 743s 704 (743s Sarah Lake) | 2023-11-20 10:00 | 2023-11-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 9L80 (755s Cordel - 757s Battle River), 757s 912T (757s Battle River), 757s 912 (757s Battle River), 757s 710 (757s Battle River), 755s 903 (755s Cordel), 755s 904 (755s Cordel), 757s 9L80D1 (757s Battle River), 755s 9L80D2 (755s Cordel) | 2023-11-20 10:00 | 2023-11-24 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2023-11-20 11:00 | 2023-11-24 17:30 | Y | Y |  | Station, Line |  |  | Limits ATC, Pre-Condition
ALTALINK, ENMAX | 688L (653s Summit - 688AL tap), 653s 688 (653s Summit) | 2023-11-20 13:00 | 2023-11-20 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 77s 51 (77s Sagitawah) | 2023-11-20 14:15 | 2023-11-24 14:45 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 989L (77s Sagitawah - 310p Sundance), 77s 26 (77s Sagitawah), 77s 29 (77s Sagitawah), 77s 989X (77s Sagitawah), 310p 2652 (310p Sundance), 310p 2752 (310p Sundance) | 2023-11-20 14:15 | 2023-11-30 14:45 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2023-11-21 07:00 | 2023-11-25 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2023-11-21 07:00 | 2023-11-29 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 9L953 (574s Nilrem - 755s Cordel) | 2023-11-21 07:00 | 2023-11-25 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 71s 1652 (71s Lamoureux) | 2023-11-21 07:30 | 2023-11-22 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, ATCO | 356s 240kV Bus1 (356s Milo), 1036L (356s Milo - 554s Travers), 356s 852 (356s Milo), 356s 752 (356s Milo), 356s 452 (356s Milo), 356s 152 (356s Milo), 356s 1036 (356s Milo) | 2023-11-21 08:00 | 2023-11-26 17:00 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47.2TR (SS-47) | 2023-11-21 08:00 | 2023-11-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.3TR (SS-13) | 2023-11-21 08:00 | 2023-11-21 16:00 | N | N |  | Transformer |  |  | For Information Only
WCLP | WCR1 Wheatcrest Generator Test | 2023-11-21 08:00 | 2024-03-26 16:00 | N | Y |  | Unit
ALTALINK | 719L (378s Shell Caroline - 575s Sundre), 719L (378s Shell Caroline - 719BL tap), 378s 452 (378s Shell Caroline), 378s 552 (378s Shell Caroline), 378s 652 (378s Shell Caroline), 575s 719N (575s Sundre), 378s 719N (378s Shell Caroline), 378s 719X (378s Shell Caroline) | 2023-11-21 08:00 | 2023-11-26 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX, ALTALINK | 653.1TR (653s Summit), 653s 138-653.1TR (653s Summit) | 2023-11-21 09:00 | 2023-11-21 15:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
BCH | T4 (BCH Natal) | 2023-11-21 09:00 | 2023-11-23 17:00 | N | Y |  | Transformer |  |  | 240 kV
ALTALINK | 250p 11 (250p Bighorn Plant) | 2023-11-21 10:00 | 2023-11-22 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2023-11-21 13:00 | 2023-11-21 17:00 | N | Y |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar), 987s T2 (987s Clover Bar), 987s T4 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s CDS31 (987s Clover Bar), 987s C2404 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s C2408 (987s Clover Bar), 987s CDS39 (987s Cloverbar) | 2023-11-22 07:00 | 2023-12-20 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, ENEL | 205s T1 (205s Castle Rock Ridge), 205s 89T1 (205s Castle Rock Ridge), 205s 52M1 (205s Castle Rock Ridge) | 2023-11-22 08:00 | 2023-11-23 16:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ENBRIDGE | 485s 35DSTAT2 (485s Blackspring) | 2023-11-22 08:00 | 2023-11-25 17:00 | N | N |  | Shunts |  |  | Pre-Condition
PACE | JFS1 Joffre Solar 1 Generator Test, JFS2 Joffre Solar 2 Generator Test | 2023-11-22 08:30 | 2023-12-07 17:00 | N | N |  | Unit
ALTALINK | 217s C1 (217s North Red Deer) | 2023-11-22 09:00 | 2023-11-22 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 653.3TR (653s Summit), 653s 138-653.3TR (653s Summit) | 2023-11-22 09:00 | 2023-11-22 15:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 250p 22 (250p Bighorn Plant) | 2023-11-22 23:00 | 2023-11-23 03:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 35B138-83 (SS-35) | 2023-11-23 08:00 | 2023-11-23 10:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162.4TR (SS-162) | 2023-11-23 08:00 | 2023-11-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2023-11-23 08:00 | 2023-11-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 151s T1 (151s Strathmore) | 2023-11-23 09:00 | 2023-11-23 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX, ALTALINK | 653.2TR (653s Summit), 653s 138-653.2TR (653s Summit) | 2023-11-23 09:00 | 2023-11-23 15:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 35B138-82 (SS-35) | 2023-11-23 10:01 | 2023-11-23 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 35B138-80 (SS-35) | 2023-11-23 12:01 | 2023-11-23 14:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 35B138-81 (SS-35) | 2023-11-23 14:01 | 2023-11-23 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 330P 12TC1 (330p Genesee), 330p 805 (330p Genesee) | 2023-11-24 07:00 | 2023-12-22 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 786L (799s Coleman - BCH Natal) | 2023-11-24 08:00 | 2023-11-24 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH, ALTALINK | 1L275 (799s Coleman - BCH Natal), 1CB2 (BCH Natal), 799s 786W (799s Coleman) | 2023-11-24 08:00 | 2023-11-24 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
WPHL | ERV8 eReserve8 (Wapiti) Generator Test | 2023-11-24 09:00 | 2024-01-31 17:00 | N | N |  | Unit
ENMAX | 13.3TR (SS-13) | 2023-11-24 09:00 | 2023-12-05 16:00 | N | N |  | Transformer
ENMAX | 31.2TR (SS-31) | 2023-11-25 08:00 | 2023-11-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1047L (574s Nilrem - 650s Hansman Lake) | 2023-11-26 07:00 | 2023-11-30 18:00 | N | Y |  | Line |  |  | For Information Only, Pre-Condition
EPCOR | T2 (Meadowlark), M722 (Meadowlark), M723 (Meadowlark), MAB2 (Meadowlark) | 2023-11-27 07:00 | 2023-12-02 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | 13 (Aurora) | 2023-11-27 08:00 | 2023-12-11 18:00 | N | N |  | Circuit Breaker |  | Outage extended. | Contingency Requires Mitigation
ENMAX | 32.2TR (SS-32) | 2023-11-27 08:00 | 2025-08-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 719L (378s Shell Caroline - 719BL tap) | 2023-11-27 08:00 | 2023-11-30 17:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 845s 701 (845s Big Mountain) | 2023-11-27 09:00 | 2023-11-27 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2023-11-27 09:00 | 2023-12-03 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 918L (281s Johnson - SS-162) | 2023-11-27 09:30 | 2023-12-10 19:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 730s STATCOM (730s Rycroft), 730s 702T (730s Rycroft) | 2023-11-27 09:30 | 2023-12-15 17:00 | N | Y |  | Shunts, Transformer |  |  | Pre-Condition
ALTALINK | 611L (186s Dry Creek - 391S Balzac), 391s 611 (391s Balzac) | 2023-11-27 09:30 | 2023-11-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 755s 903 (755s Cordel) | 2023-11-27 10:00 | 2023-11-27 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2023-11-27 10:00 | 2023-12-04 12:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 611L (186s Dry Creek - 391S Balzac), 186s 611 (186s Dry Creek) | 2023-11-27 10:00 | 2023-11-27 17:30 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 368s T1 (368s Burdett) | 2023-11-27 11:00 | 2023-11-27 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 9L56 (720s Wabasca - 876s Brintnell), 876s 902 (876s Brintnell), 876s 904 (876s Brintnell) | 2023-11-27 12:00 | 2023-12-06 12:37 | N | Y |  | Line, Circuit Breaker |  | Extended | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 9L55 (AML 852s Round Hill - 885s McMillan), 885s 902T (885s McMillan), 885s 260kV Bus 900BS2 (885s McMillan), 885s 902 (885s McMillan), 885s 903 (885s McMillan), 885S 902TD (885s McMillan), 885S 702TD (885s McMillan), 885s 704 (885s McMillan), 885s 501R (885s McMillan) | 2023-11-27 12:01 | 2023-12-11 13:00 | N | Y |  | Line, Transformer, Bus, Circuit Breaker, Switch, Shunts | 885S McMillan sub Protection Upgrade: Complete protection cut over and Commissioning of new protection on 902T, 704/7L02 Line protection, 25kV Reactor protection. On Monday October 23, 2023 will extend GOI to new isolation points: 501A,502TD1,502TD1,703B,7L02D2,906B,902A,Switch @ Round Hill (Alta Link). The following will be OOS: 900BS2, 903,902,9L55,902T,704/7L02,144kV Bus. Complete cut over and Commissioning of new protection to 240kV bus, 903,902,9L55 line protection. |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 845s 702 (845s Big Mountain) | 2023-11-27 12:01 | 2023-11-27 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 658L (562s Cypress - 658AL tap), 658L (649s Chappice Lake - 658AL tap), 658AL (662s Hilda - 658AL tap) | 2023-11-27 13:00 | 2023-11-27 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Restricts Generation
ALTALINK | 658L (649s Chappice Lake - 658AL tap) | 2023-11-27 17:01 | 2023-12-01 12:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 162.81L (391s Balzac - SS-162), 391s 162.81 (391s Balzac) | 2023-11-28 07:30 | 2023-11-28 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2023-11-28 08:00 | 2023-11-28 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 2075s 902T (2075s Newell), 2075s ACF21 (2075s Newell) | 2023-11-28 08:30 | 2023-11-30 17:00 | N | Y |  | Transformer, Shunts |  |  | 240 kV, For Information Only
ALTALINK | 29s T2 (29s Cascade), 29s 40 (29s Cascade) | 2023-11-28 13:00 | 2023-12-01 10:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 688L (199s East Airdrie - 688AL tap), 199s 688 (199s East Airdrie) | 2023-11-29 07:00 | 2023-12-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 391s T2 (391s Balzac), 391s 33 (391s Balzac) | 2023-11-29 07:30 | 2023-11-30 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 368s 879 (368s Burdett), 879L (368s Burdett - 879L tap) | 2023-11-29 08:00 | 2023-11-29 16:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
Lethbridge | 593s 12 (593s Lakeview) | 2023-11-29 08:00 | 2023-11-29 17:00 | N | N |  | Switch |  |  | For Information Only
BCH | T4 (BCH Natal) | 2023-11-29 09:00 | 2023-11-29 17:00 | N | Y |  | Transformer |  |  | 240 kV
ALTALINK | 520s R7 (520s Bennett) | 2023-11-29 20:20 | 2023-12-15 16:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 6L126 (743s Sarah Lake - 515L tap) | 2023-12-01 07:00 | 2023-12-01 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
BFAW | BFL3 Buffalo Atlee 3 Generator Test | 2023-12-01 08:00 | 2024-06-30 23:59 | N | N |  | Unit
ALTALINK | 368s T2 (368s Burdett) | 2023-12-01 08:00 | 2023-12-01 13:00 | N | Y |  | Transformer |  |  | Restricts Generation
BFAW | BFL2 Buffalo Atlee 2 Generator Test | 2023-12-01 08:00 | 2024-06-30 23:59 | N | N |  | Unit
BFAW | BFL1 Buffalo Atlee 1 Generator Test | 2023-12-01 08:00 | 2024-06-30 23:59 | N | N |  | Unit
BFAW | BFL4 Buffalo Atlee 4 Generator Test | 2023-12-01 08:00 | 2024-06-30 23:59 | N | N |  | Unit
ALTALINK | 658L (562s Cypress - 658AL tap), 658L (649s Chappice Lake - 658AL tap), 658AL (662s Hilda - 658AL tap), 662s 138CB1 (662s Hilda) | 2023-12-01 12:31 | 2023-12-01 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 929L (74S Janet - 287s Hazelwood) | 2023-12-02 07:00 | 2023-12-18 17:00 | N | Y |  | Line |  | Line returned early as per AML | 240 kV
ENMAX | 11.82L (SS-11 - SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14), 14.3TR (SS-14), 14.1TR (SS-14) | 2023-12-02 08:00 | 2023-12-03 18:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow), 397s 720N (397s Benbow), 347s 720X (347s AML Fox Creek) | 2023-12-04 07:00 | 2023-12-07 12:00 | N | N |  | Line, Circuit Breaker |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s Victoria T5 (EP 511s Victoria), EP 511s V2401 (EP 511s Victoria) | 2023-12-04 07:00 | 2023-12-16 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV
EPCOR | T2 (EP Riverview), RW2402 (EP Riverview), RW2403 (EP Riverview), RWAB2 (EP Riverview) | 2023-12-04 07:00 | 2023-12-08 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), T2 (EP Hardisty), H723 (EP Hardisty), H722 (EP Hardisty), H726 (EP Hardisty), HAB2 (EP Hardisty) | 2023-12-04 07:00 | 2023-12-13 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.1TR (SS-5) | 2023-12-04 08:00 | 2023-12-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34) | 2023-12-04 08:00 | 2023-12-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16) | 2023-12-04 08:00 | 2023-12-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s GT2 (987s Clover Bar), 987s CGB2 (987s Clover Bar) | 2023-12-04 08:30 | 2023-12-05 | N | Y |  | Transformer, Circuit Breaker
ALTALINK | 391s T1 (391s Balzac), 391s 30 (391s Balzac) | 2023-12-04 09:30 | 2023-12-05 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden), 197s 174E (197s Bardo), 395s 174W (395s North Holden) | 2023-12-04 10:00 | 2023-12-20 14:15 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, ATCO | 852s 152 (852s Round Hill), 852s 252 (852s Round Hill), 1085L (852s Round Hill - 885s McMillan) | 2023-12-04 10:00 | 2023-12-09 14:00 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain), 845s 709 (845s Big Mountain), 845s 708 (845s Big Mountain), 845S 7L46D2 (845s Big Mountain) | 2023-12-04 12:01 | 2023-12-09 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 658L (562s Cypress - 658AL tap), 658L (649s Chappice Lake - 658AL tap), 662s 138CB1 (662s Hilda) | 2023-12-04 13:00 | 2023-12-04 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 658L (562s Cypress - 658AL tap) | 2023-12-04 17:01 | 2023-12-14 12:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1047L (574s Nilrem - 650s Hansman Lake) | 2023-12-05 07:00 | 2023-12-13 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 704L (51s Wainwright - 478s Tucuman) | 2023-12-05 07:00 | 2023-12-06 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Overload, Pre-Condition
ATCO | 766s 903 (766s Nevis) | 2023-12-05 07:00 | 2023-12-11 10:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 72RG1 (Garneau - Rossdale), RG7210 (Rossdale) | 2023-12-05 07:00 | 2023-12-08 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK | 612L (336s Fincastle - 368s Burdett), 368s 612 (368s Burdett), 336s 612 (336s Fincastle) | 2023-12-05 08:00 | 2023-12-05 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 368s C2 (368s Burdett) | 2023-12-05 08:00 | 2023-12-05 12:00 | N | N |  | Shunts |  |  | Pre-Condition
WPHL | ERV7 eReserve7 (Wapiti) Generator Test | 2023-12-05 09:00 | 2024-01-31 17:00 | N | N |  | Unit
ALTALINK, Lethbridge | 824L (593s Lakeview - 618s Riverbend), 593s 824L (593s Lakeview), 618s 824 (618s Riverbend) | 2023-12-05 11:00 | 2023-12-05 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer), 171s 735X (171s Redwater), 233s 735N (233s Beamer) | 2023-12-06 07:00 | 2023-12-10 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 722L (107s Westfield - 368s Burdett), 368s 722X (368s Burdett) | 2023-12-06 08:00 | 2023-12-06 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 38s T2 (38s East Edmonton) | 2023-12-06 08:00 | 2023-12-06 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 813L (146s MacDonald - 241s Uplands), 146s 667 (146s Macdonald), 146s 813L (146s Macdonald), 146s T1 (146s Macdonald) | 2023-12-06 08:00 | 2023-12-06 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 217s 138kV Bus (217s North Red Deer), 778L (87s Gaetz - 217s North Red Deer), 444L (198s Blackfalds - 217s North Red Deer) | 2023-12-06 08:00 | 2023-12-07 16:00 | N | N |  | Bus, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, REDDEER | 444L (198s Blackfalds - 217s North Red Deer), 778L (87s Gaetz - 217s North Red Deer), 217s T2 (217s North Red Deer), 217s 14-81-2 (217s North Red Deer) | 2023-12-06 08:00 | 2023-12-07 16:00 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
FCSF, CODP | FCS1 Fox Coulee Solar Generator Test, MCH1 Michichi Creek Generator Test | 2023-12-06 08:00 | 2024-05-19 23:59 | N | Y |  | Unit
ENMAX | 8.5TR (SS-8) | 2023-12-06 08:00 | 2023-12-08 16:00 | N | N |  | Transformer |  |  | For Information Only
PWLP | PAW1 Paintearth Wind Project Generator Test | 2023-12-06 08:00 | 2024-01-05 17:00 | N | Y |  | Unit
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2075s T11 (2075s Newell) | 2023-12-06 15:30 | 2023-12-11 21:38 | N | Y |  | Line, Transformer |  |  | 500 kV
ALTALINK | 526L (519L tap - 526AL tap) | 2023-12-07 07:00 | 2023-12-10 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 927L (102s Langdon - 356s Milo) | 2023-12-07 07:00 | 2023-12-12 17:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 89s 752 (89s Ellerslie) | 2023-12-07 08:00 | 2023-12-07 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 38s T3 (38s East Edmonton) | 2023-12-07 08:00 | 2023-12-07 18:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 635EDD-1001 635PT-1038 (635EDD-1001) | 2023-12-07 08:00 | 2023-12-11 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 908L (38s East Edmonton - 908AL tap), 908L (89s Ellerslie - 908AL tap), 908AL (52S East Industrial - 908L tap), 52s T2 (52s East Industrial), 816s P2401 (816s Petrolia), 816s P2406 (816s Petrolia), 52s E2402 (52s East Industrial) | 2023-12-07 08:00 | 2023-12-07 08:30 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 368s T1 (368s Burdett) | 2023-12-07 09:00 | 2023-12-07 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 2085s 602T (2085s Sheridan), 2085s 602 (2085s Sheridan) | 2023-12-07 12:00 | 2023-12-07 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 964L (244s Bowmanton - 964L tap), 964L (251s Whitla - 964L tap), 964AL (1024s Granlea - 964L tap), 244s 252 (244s Bowmanton), 244s 352 (244s Bowmanton), 251s 252 (251s Whitla), 251s 352 (251s Whitla), 251s 964 (251s Whitla), 244s 964 (244s Bowmanton) | 2023-12-08 07:00 | 2023-12-10 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Prevents Normal Events, Restricts Generation
ALTALINK, ATCO, FMGW | 964AL (1024s Granlea - 964L tap), 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s PS-6005 (1024s Granlea), 1024s PS-6006 (1024s Granlea) | 2023-12-08 07:00 | 2023-12-10 17:00 | N | Y |  | Line, Transformer, Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 927L (102s Langdon - 356s Milo) | 2023-12-08 07:30 | 2023-12-08 17:30 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
ALTALINK, REDDEER | 217s 138kV Bus (217s North Red Deer), 425L (194s South Red Deer - 217s North Red Deer), 768L (209s Timberlands - 217s North Red Deer), 217s C1 (217s North Red Deer), 217s T7 (217s North Red Deer), 217s T1 (217s North Red Deer), 217s 14-81-1 (217s North Red Deer) | 2023-12-08 08:00 | 2023-12-08 16:00 | N | N |  | Bus, Line, Shunts, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 33s 2 (33s Spray) | 2023-12-09 08:00 | 2023-12-09 17:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2023-12-10 08:00 | 2023-12-13 08:50 | N | Y |  | Line |  | outage terminated on Dec 13, 2023 8:50 due to forced outage to 253s 138 kV bus resulting in 876L out of service | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
NVEL | WEM1 Wembley Generator Test | 2023-12-10 10:00 | 2023-12-10 15:00 | N | Y |  | Unit
ALTALINK | 964L (244s Bowmanton - 964L tap), 244s 252 (244s Bowmanton), 244s 352 (244s Bowmanton), 244s 964 (244s Bowmanton) | 2023-12-10 17:01 | 2023-12-17 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Prevents Normal Events, Restricts Generation
EPCOR | T1 (EP Riverview), RW2401 (EP Riverview), RW2405 (EP Riverview), RWAB1 (EP Riverview) | 2023-12-11 07:00 | 2023-12-15 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 13.1TR (SS-13) | 2023-12-11 08:00 | 2023-12-11 16:00 | N | N |  | Transformer |  |  | For Information Only
WPHL | ERV9 eReserve9 (Goodfare) Generator Test | 2023-12-11 09:00 | 2024-01-31 15:00 | N | N |  | Unit
ATCO | 7L03 (731s Elmworth - 7L09 tap) | 2023-12-11 09:00 | 2023-12-15 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 64s 240kV Bus (64s East Crossfield), 901AL (64s East Crossfield - 901L tap), 901L (63s Red Deer - 901AL tap), 901L (74s Janet - 901AL tap), 64s T2 (64s East Crossfield) | 2023-12-11 09:30 | 2023-12-21 18:00 | N | Y |  | Bus, Line, Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 9L10 (876s Brintnell - 939s Livock), 876s 901 (876s Brintnell), 876s 903 (876s Brintnell), 939s 911 (939s Livock) | 2023-12-11 14:00 | 2023-12-13 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Affects Cranking Path
ENMAX | 47.2TR (SS-47) | 2023-12-12 08:00 | 2023-12-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24), 24.81L (SS-24 - SS-31), 24.1TR (SS-24), 24B138-24.81 (SS-24), 24B138-24.83 (SS-24), 24B138-24B (SS-24), 31B138-24.81 (SS-31), 24MD138-24.1TR (SS-24) | 2023-12-12 08:00 | 2023-12-15 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 85L (35s Rundle Plant - 54L tap) | 2023-12-12 08:00 | 2023-12-12 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 197s 138kV Bus (197s Bardo), 730L (197s Bardo - 732L tap), 174L (197s Bardo - 289s Saunders Lake), 174L (197s Bardo - 395s North Holden), 197s 174W (197s Bardo), 197s 6 (197s Bardo) | 2023-12-12 09:00 | 2023-12-13 17:00 | N | N |  | Bus, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 526L (515s Fed Pipe Judy Creek - 6L126 Tap), 515s T1 (515s FedpipeJudy Creek), 515s 526 (515s Fed Pipe Judy Creek) | 2023-12-12 09:30 | 2023-12-12 14:30 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ALTALINK | 477s T1 (477s Amoco West Pembina) | 2023-12-12 09:30 | 2023-12-14 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 924L (102s Langdon - 356s Milo) | 2023-12-12 17:30 | 2023-12-17 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 10.1TR (SS-10) | 2023-12-13 08:00 | 2023-12-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 27.1TR (SS-27) | 2023-12-13 08:00 | 2023-12-13 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 832s 702T (832s Blumenort), 832s 702 (832s Blumenort) | 2023-12-13 09:00 | 2023-12-19 17:00 | N | N |  | Transformer, Circuit Breaker | {OUTAGE REASON: " Tie 5L397, 5L135, 5L596 to 5L458 via 500D3, 500D2, 500D4 " P&C review relay settings for 5L458 " Connect new 501/502/500PT2D to existing bus} |  | For Information Only
ENMAX | 7.1TR (SS-7) | 2023-12-14 08:00 | 2023-12-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 27.2TR (SS-27) | 2023-12-14 08:00 | 2023-12-14 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L14 (705s Kitscoty - 751s Hill) | 2023-12-14 09:00 | 2023-12-14 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ATCO | 930s SVC (930s Arcenciel) | 2023-12-14 12:00 | 2023-12-19 13:00 | N | Y |  | Shunts |  | RTS early | Pre-Condition
ALTALINK | 658AL (662s Hilda - 658AL tap), 658L (562s Cypress - 658AL tap), 658L (649s Chappice Lake - 658AL tap), 662s 138CB1 (662s Hilda) | 2023-12-14 12:01 | 2023-12-14 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
CSCL | SGC1 Spring Coulee Generator Test | 2023-12-15 07:00 | 2024-02-28 18:00 | N | Y |  | Unit
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2023-12-15 08:00 | 2023-12-19 17:00 | N | Y |  | Line |  | TFO updated twice | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 964L (244s Bowmanton - 964L tap), 964AL (1024s Granlea - 964L tap), 964L (251s Whitla - 964L tap), 244s 252 (244s Bowmanton), 244s 352 (244s Bowmanton), 244s 964 (244s Bowmanton), 251s 252 (251s Whitla), 251s 352 (251s Whitla), 251s 964 (251s Whitla) | 2023-12-17 17:01 | 2023-12-18 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
EPCOR | 72RV4 (EP 511s Victoria - Rossdale), RV726 (Rossdale) | 2023-12-18 07:00 | 2023-12-18 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3), 13B138-3.84 (SS-13) | 2023-12-18 08:00 | 2023-12-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, FMGW | 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s PS-6005 (1024s Granlea), 1024s PS-6006 (1024s Granlea), 1024s 952-600001 (1024s Granlea) | 2023-12-18 08:00 | 2023-12-18 18:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | 240 kV, Pre-Condition, Restricts Generation
ATCO | 7L03 (731s Elmworth - 7L09 tap) | 2023-12-18 09:00 | 2023-12-20 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L130 (705s Kitscoty - 710s Vermilion), 705s 704 (705s Kitscoty), 710s 702 (710s Vermilion) | 2023-12-18 10:00 | 2023-12-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, For Information Only, Over/Under Voltage, Overload, Pre-Condition
ATCO | 739s 602 (739s Edith Lake), 6L11 (739s Edith Lake - 854s Swan Dive) | 2023-12-18 18:10 | 2023-12-19 15:30 | N | N |  | Circuit Breaker, Line |  | RTS early | Pre-Condition
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), RV722 (Rossdale) | 2023-12-19 07:00 | 2023-12-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), M721 (Meadowlark) | 2023-12-19 07:00 | 2023-12-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 103s T1 (103s Goose Lake) | 2023-12-19 07:30 | 2023-12-20 16:30 | N | Y |  | Transformer |  | Extended due to issues with transformer. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 339s T1 (339s Duchess), 831L (339s Duchess - 831AL tap) | 2023-12-19 07:30 | 2023-12-19 16:30 | N | N |  | Transformer, Line |  |  | For Information Only
ENMAX | 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13B138-2.83 (SS-13), 13B138-3.84 (SS-13) | 2023-12-19 08:00 | 2023-12-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 876L (179s Gleichen - 253s Blackie) | 2023-12-20 07:00 | 2023-12-21 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | T1 (BCH Natal), 13CX1 (BCH Natal), 60CB1 (BCH Natal), 60CB11 (BCH Natal), 60D1CB1 (BCH Natal), 60D1CB11 (BCH Natal) | 2023-12-20 09:00 | 2023-12-20 17:00 | N | Y |  | Transformer, Shunts, Circuit Breaker, Switch |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 77s 40 (77s Sagitawah) | 2023-12-20 16:00 | 2023-12-20 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1212L (12s Heartland - 89s Ellerslie), 89s 1952 (89s Ellerslie), 89s 1852 (89s Ellerslie), 12s 952 (12s Heartland), 12s 852 (12s Heartland) | 2023-12-21 13:00 | 2023-12-21 14:45 | N | Y |  | Line, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
GLPC | SLR1 Sollair Solar Energy Plant Generator Test | 2023-12-24 09:00 | 2024-12-19 12:00 | N | Y |  | Unit
ENMAX | 36.3TR (SS-36) | 2023-12-24 16:20 | 2024-01-03 13:40 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 63s 652 (63s Red Deer) | 2023-12-24 20:00 | 2023-12-27 08:25 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (858s Narrows Creek - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap) | 2023-12-27 09:00 | 2023-12-27 15:00 | N | N |  | Line |  | back early | Creates Radial Feeds, Firm Load Loss
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2024-01-02 09:00 | 2024-01-08 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson), 811s 710 (811s Clairmont Lake) | 2024-01-02 09:00 | 2024-01-08 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 987s GT2 (987s Clover Bar), 987s CGB2 (987s Clover Bar) | 2024-01-03 07:00 | 2024-01-09 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon) | 2024-01-03 08:00 | 2024-01-03 17:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ATCO | 7L16 (766s Nevis - 948s Heatburg), 766s 702 (766s Nevis), 948s 703 (948s Heatburg) | 2024-01-03 08:00 | 2024-01-05 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 330p 1210 (330p Genesee), 330p 1211 (330p Genesee) | 2024-01-04 07:00 | 2024-01-16 10:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Pre-Condition
CapitalPower | GNR1 Genesee Repower 1 Generator Test | 2024-01-04 08:00 | 2024-04-28 16:00 | N | N |  | Unit
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2024-01-04 08:00 | 2024-01-05 17:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 827s SVC (827s Cranberry Lake), 827s 703 (827s Cranberry Lake) | 2024-01-04 17:00 | 2024-01-05 15:20 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen) | 2024-01-05 04:10 | 2024-01-05 15:40 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 1215 (330p Genesee) | 2024-01-05 07:00 | 2024-01-05 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2024-01-05 08:00 | 2024-01-10 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2024-01-06 07:00 | 2024-01-06 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1041L (370s North Lethbridge - 554s Travers), 370s 47 (370s North Lethbridge), 370s 51 (370s North Lethbridge) | 2024-01-06 08:00 | 2024-01-08 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 897L (38s East Edmonton - 45s Bretona), 38s 897 (38s East Edmonton), 45s 897 (45s Bretona) | 2024-01-07 07:15 | 2024-01-10 17:45 | N | N |  | Line, Circuit Breaker |  | Repair downlead at structures 49, 50, 52, 53, 80, 81, 82, 83 & 91. Install insulated guy links at structures 82 & 83. Replace arms and insulators at structures 84 & 85. Repair/Replace Pole boot on one of the poles on structure 97. | Creates Radial Feeds, Firm Load Loss
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen) | 2024-01-07 14:30 | 2024-01-12 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Rossdale), R721 (Rossdale), R723 (Rossdale), RAB2 (Rossdale) | 2024-01-08 07:00 | 2024-06-14 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CascadeP | CAS1 Cascade 1 Generator Test, CAS2 Cascade 2 Generator Test | 2024-01-08 08:00 | 2024-06-16 17:00 | N | N |  | Unit
ENMAX | 6.82L (SS-6 - SS-41), 6.1TR (SS-6), 6B138-6.82 (SS-6), 41B138-6.82 (SS-41), 6MD138-6.1TR (SS-6) | 2024-01-08 08:00 | 2024-01-09 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 849s 901 (849s Joslyn Creek), 849s 902 (849s Joslyn Creek) | 2024-01-08 10:00 | 2024-01-25 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ATCO | 9L155 (838s Horizon Mining - 849s Joslyn Creek), 849s 9L155D1 (849s Joslyn Creek) | 2024-01-08 10:00 | 2024-01-25 12:00 | N | Y |  | Line, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s 252 (77s Sagitawah), 77s 452 (77s Sagitawah) | 2024-01-09 06:00 | 2024-01-09 12:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 756L (87s Gaetz - 535s Joffre) | 2024-01-09 08:00 | 2024-01-09 17:00 | N | N |  | Line |  |  | Pre-Condition
ENMAX | 27.1TR (SS-27) | 2024-01-09 08:00 | 2024-01-09 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 2033s 703C (2033s Mowat) | 2024-01-09 09:00 | 2024-01-11 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 722s 703C (722s Crystal Lake), 722s 703 (722s Crystal Lake) | 2024-01-09 09:30 | 2024-01-09 17:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2024-01-09 12:01 | 2024-01-24 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 756L (87s Gaetz - 535s Joffre), 87s 138kV West Bus (87s Gaetz), 87s T1 (87s Gaetz), 87s 152 (87s Gaetz), 87s 252 (87s Gaetz), 87s 756E (87s Gaetz) | 2024-01-10 07:00 | 2024-01-10 18:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 845s 709 (845s Big Mountain) | 2024-01-10 08:00 | 2024-01-10 12:00 | N | N |  | Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2024-01-10 08:00 | 2024-01-10 17:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 27.2TR (SS-27) | 2024-01-10 08:00 | 2024-01-10 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 749s 701T (749s Flyingshot Lake) | 2024-01-10 09:30 | 2024-01-10 17:30 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ATCO | 845s 710 (845s Big Mountain) | 2024-01-10 12:01 | 2024-01-10 16:00 | N | N |  | Circuit Breaker |  |  | Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2024-01-11 15:05 | 2024-01-24 11:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2024-01-12 00:15 | 2024-01-19 18:00 | N | Y |  | Shunts |  | ATCO has extend the outage return to service date. This is only an estimate. | Pre-Condition
ATCO | 7L121 (2043s Freer - 7LA121 tap) | 2024-01-12 01:50 | 2024-01-15 11:40 | N | N |  | Line
EPCOR | EP 511s Victoria T2 (EP 511s Victoria), EP 511s VAB2 (EP 511s Victoria) | 2024-01-12 02:50 | 2024-01-15 08:00 | N | N |  | Transformer, Switch
ALTALINK | 237s 552 (237s Foothills) | 2024-01-12 05:00 | 2024-01-12 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 698s 552 (698s Jackfish) | 2024-01-12 05:00 | 2024-01-15 11:40 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | RW2405 (EP Riverview) | 2024-01-12 05:00 | 2024-01-30 08:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 526s C1 (526s Buffalo Creek) | 2024-01-12 05:00 | 2024-01-19 18:00 | N | N |  | Shunts |  |  | Pre-Condition
EPCOR | 72CN10 (987s Clover Bar - Namao), N724 (Namao), 987s CN723 (987s Clover Bar) | 2024-01-12 07:00 | 2024-04-10 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 162.1TR (SS-162) | 2024-01-12 08:00 | 2024-01-17 16:00 | N | Y |  | Transformer |  |  | 240 kV
REDDEER | 217s 14-81-1 (217s North Red Deer), 217s T1 (217s North Red Deer) | 2024-01-13 02:16 | 2024-03-15 16:00 | N | N |  | Switch, Transformer |  |  | For Information Only
ENMAX | 65B240-D135 (SS-65) | 2024-01-14 08:00 | 2024-01-15 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s T4 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2408 (987s Clover Bar) | 2024-01-15 07:00 | 2024-02-02 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
EPCOR | 113s T2 (113s Inland Cement) | 2024-01-15 07:00 | 2024-04-20 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 132s 12 (132s Ware Junction) | 2024-01-15 07:30 | 2024-01-15 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.2TR (SS-9), 9.3TR (SS-9), 9B138-2.81 (SS-9), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43), 9MD138-9.2TR (SS-9), 9MD138-9.3TR (SS-9), SW83 (SS-9), 2MD138-2.81 (SS-2) | 2024-01-15 08:00 | 2024-01-18 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s V722 (EP 511s Victoria) | 2024-01-15 08:01 | 2024-01-17 12:00 | N | N |  | Circuit Breaker
ALTALINK, Lethbridge | 824L (593s Lakeview - 618s Riverbend), 593s 824L (593s Lakeview), 618s 824 (618s Riverbend), 593s T1 (593s Lakeview) | 2024-01-15 11:00 | 2024-01-29 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 811s 701C (811s Clairmont Lake) | 2024-01-15 17:00 | 2024-02-23 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 873s 601T (873s Marion Lake), 873s 601 (873s Marion Lake) | 2024-01-16 08:00 | 2024-03-04 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2024-01-16 09:00 | 2024-01-22 16:00 | N | Y |  | Line |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2024-01-16 09:00 | 2024-01-24 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 722s 702T (722s Crystal Lake) | 2024-01-16 09:30 | 2024-01-25 17:30 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ATCO | 7L113 (853s Ring Creek - 930s Arcenciel) | 2024-01-16 10:00 | 2024-02-21 13:00 | N | Y |  | Line |  |  | Pre-Condition
ATCO | 2029s 1223 (2029s Heathfield), 2029s ACF22 (2029s Heathfield) | 2024-01-16 12:00 | 2024-02-28 09:58 | N | Y |  | Switch, Shunts |  | Back in service early. | Limits Ratings
ENMAX | 162B138-RB85 (SS-162) | 2024-01-16 12:00 | 2024-01-17 12:00 | N | N |  | Circuit Breaker
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2024-01-17 07:00 | 2024-01-17 17:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell) | 2024-01-17 08:00 | 2024-01-17 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 928L (17s Benalto - 42s Sarcee), 42s 928N (42s Sarcee) | 2024-01-17 08:00 | 2024-01-22 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 262s 870W (262s Rocky Mountain House), 263s 870E (263s Strachan) | 2024-01-17 08:00 | 2024-01-23 15:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 330P 12GT6D (330p Genesee) | 2024-01-17 15:30 | 2024-01-23 10:00 | N | Y |  | Transformer |  |  | 500 kV
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-01-17 23:00 | 2024-01-18 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-01-18 03:00 | 2024-01-25 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 113L (20s Ghost - 33s Spray), 33s 113 (33s Spray), 20s 113 (20s Ghost) | 2024-01-18 07:00 | 2024-01-22 17:30 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), 987s CH724 (987s Clover Bar), H725 (EP Hardisty) | 2024-01-18 07:00 | 2024-01-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 935L (324s Cassils - 356s Milo) | 2024-01-18 08:00 | 2024-01-20 13:30 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 788s 703 (788s Hotchkiss), 7L63 (788s Hotchkiss - 7LA63 tap) | 2024-01-18 12:00 | 2024-01-20 18:00 | N | Y |  | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 874L (45s Bretona - 522s Cooking Lake) | 2024-01-19 06:00 | 2024-01-19 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 228s T1 (228s T.M.P.L. Niton), 228s 31 (228s T.M.P.L. Niton) | 2024-01-19 08:00 | 2024-01-19 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 289s Saunders Lake), 197s 174W (197s Bardo) | 2024-01-20 06:00 | 2024-01-31 18:30 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
EPCOR | 330p 138kV Bus 1 (330p Genesee), 330p 138kV Bus 2 (330p Genesee) | 2024-01-20 07:00 | 2024-03-29 17:00 | N | N |  | Bus
ALTALINK, EPCOR | 430L (330P Genesee - 510S Sunnybrook), 330p 807 (330p Genesee) | 2024-01-20 07:00 | 2024-01-26 12:00 | N | Y |  | Line, Circuit Breaker |  | Delayed due to man power. | Pre-Condition
ALTALINK | 945L (275s Jenner - 562s Cypress) | 2024-01-20 08:00 | 2024-01-24 07:00 | N | Y |  | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 330P 12GT6D (330p Genesee) | 2024-01-20 13:00 | 2024-02-13 17:00 | N | Y |  | Transformer |  |  | 500 kV
EPCOR | T1 (Meadowlark) | 2024-01-22 07:00 | 2024-01-26 17:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
EPCOR | 330p 808 (330p Genesee), 8L10 (330P Genesee - Fording Coal Mine) | 2024-01-22 07:00 | 2024-01-27 17:00 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), 987s CH722 (987s Clover Bar), H724 (EP Hardisty) | 2024-01-22 07:00 | 2024-01-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.5TR (SS-8), 8.6TR (SS-8), 8B138-3A0 (SS-8), 2A01 (SS-8), 2A02 (SS-8), 3A1 (SS-8) | 2024-01-22 08:00 | 2024-01-26 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 1.85L (SS-1 - SS-8), 8B138-1A0 (SS-8), 8B138-2A0 (SS-8), 1A01 (SS-8), 1A10 (SS-8), 2A1 (SS-8) | 2024-01-22 08:00 | 2024-02-06 10:16 | N | N |  | Line, Circuit Breaker, Switch |  |  | Firm Load Loss, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27), SW64 (SS-27), 27MD69-27.1TR (SS-27) | 2024-01-22 08:00 | 2024-01-24 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2024-01-22 12:00 | 2024-01-25 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 730s STATCOM (730s Rycroft), 730s 705 (730s Rycroft), 730s 702T (730s Rycroft) | 2024-01-23 09:00 | 2024-01-25 16:00 | N | Y |  | Shunts, Circuit Breaker, Transformer |  |  | Pre-Condition
ALTALINK | 1002L (163s Amoco Empress - 275s Jenner) | 2024-01-24 07:01 | 2024-01-24 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo), APS# 175 Milo 356S  924L/927L Overload Mitigation Scheme | 2024-01-24 08:00 | 2024-01-24 17:00 | N | Y |  | Line, RAS |  |  | Contingency Requires Mitigation, Over/Under Voltage, Restricts Generation, Affects Cranking Path
ENMAX | 24.82L (SS-24 - SS-65) | 2024-01-24 08:00 | 2024-01-24 16:00 | N | N |  | Line |  |  | For Information Only
EPCOR | 330p 806 (330p Genesee) | 2024-01-24 08:30 | 2024-01-24 17:00 | N | N |  | Circuit Breaker
ENMAX | 5.7TR (SS-5) | 2024-01-24 10:00 | 2024-01-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 723s 252 (723s Christina Lake), 723s T2 (723s Christina Lake) | 2024-01-24 10:30 | 2024-01-24 16:30 | N | Y |  | Circuit Breaker, Transformer | Urgent Request |  | For Information Only
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 13.4TR (SS-13), 27B69-13.60 (SS-27), 13B69-13.60 (SS-13) | 2024-01-24 13:00 | 2024-01-26 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 995L (62s Brazeau Plant Plant - 995AL tap), 62s 240kV Bus (62s Brazeau Plant), 62s T5 (62s Brazeau Plant), 62s 995X (62s Brazeau Plant), 62s 31 (62s Brazeau Plant), 62s 207 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant) | 2024-01-24 23:00 | 2024-01-25 07:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, For Information Only, Over/Under Voltage, Affects Cranking Path
ALTALINK | 1002L (163s Amoco Empress - 275s Jenner), 944L (132s Ware Junction - 275s Jenner), 951L (132s Ware Junction - 275s Jenner), 945L (275s Jenner - 562s Cypress) | 2024-01-25 | 2024-01-25 01:00 | N | Y |  | Line
ALTALINK | 356s 240kV Bus1 (356s Milo), 356s 152 (356s Milo), 356s 452 (356s Milo), 356s 752 (356s Milo) | 2024-01-25 08:00 | 2024-02-01 14:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Prevents Normal Events
ATCO | 9L137 (838s Horizon Mining - 849s Joslyn Creek), 9L08 (849s Joslyn Creek - 888s Dover), 849s 903 (849s Joslyn Creek), 849s 904 (849s Joslyn Creek), 849s 905 (849s Joslyn Creek), 849s 906 (849s Joslyn Creek), 849s 9L137D1 (849s Joslyn Creek) | 2024-01-25 12:01 | 2024-02-04 07:59 | N | Y |  | Line, Circuit Breaker, Switch |  | extended | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, WCLP | 1039s 52-H1 (1039s Wheatcrest), 763A1L (1039s Wheatcrest - 763A1L tap), 1039s Wheatcrest | 2024-01-25 15:30 | 2024-01-31 17:00 | N | Y |  | Circuit Breaker, Line, Station |  |  | Restricts Generation
SUNCOR | 635EDD-1001 635-752-662 (635EDD-1001) | 2024-01-26 08:00 | 2024-01-26 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
Lethbridge | 593s 6 (593s Lakeview) | 2024-01-27 08:00 | 2024-01-27 17:00 | N | N |  | Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 309s T1 (309s Anthony Henday) | 2024-01-27 22:20 | 2024-02-09 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 330p 802 (330p Genesee), 330P SST1 (330P Genesee) | 2024-01-28 07:00 | 2024-02-09 17:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 394s T1 (394s Empress) | 2024-01-29 04:00 | 2024-02-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 157s T2 (157s Lac La Biche) | 2024-01-29 04:00 | 2024-01-31 15:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2024-01-29 06:00 | 2024-02-07 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Meadowlark) | 2024-01-29 07:00 | 2024-02-23 17:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy), 816s P2402 (816s Petrolia), 816s P2403 (816s Petrolia) | 2024-01-29 07:00 | 2024-02-02 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.2TR (SS-38) | 2024-01-29 08:00 | 2024-02-02 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28.2TR (SS-28), 28B138-28.80 (SS-28), 42s 28 (42s Sarcee) | 2024-01-29 08:00 | 2024-01-30 16:00 | N | Y |  | Line, Transformer, Circuit Breaker |  | HV SW Maint. MD-28.2TR, SW86, SW82, SW81, SW80. SW 80 -Retrieve Nameplate Info. Check reversing switch. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28) | 2024-01-29 08:00 | 2024-01-30 16:00 | N | Y |  | Line |  |  | Pre-Condition
SUNCOR | 29EDD-85 29PS-320 (29EDD-85), 29EDD-85 752-10030 (29EDD-85), 29EDD-85 752-10040 (29EDD-85) | 2024-01-29 08:00 | 2024-02-02 18:00 | N | N |  | Switch, Circuit Breaker |  |  | For Information Only
ATCO | 7L61 (780s Lubicon - 796s Nipisi) | 2024-01-29 10:00 | 2024-02-05 12:00 | N | N |  | Line |  |  | Over/Under Voltage, Pre-Condition
ATCO | 754s 701T (754s Ksituan River) | 2024-01-29 10:00 | 2024-02-09 17:30 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ATCO | 840s McNeill Station, 840s 701T (840s McNeill Station), 840s 901T (840s McNeill Station), 840s 901 (840s McNeill Station), 840s 701 (840s McNeill Station), 840s 702C (840s McNeill Station), 840s 703C (840s McNeill Station) | 2024-01-29 11:00 | 2024-02-02 17:30 | N | Y |  | Station, Transformer, Circuit Breaker, Shunts |  |  | Limits ATC, Pre-Condition
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2024-01-29 12:00 | 2024-02-01 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 262s T1 (262s Rocky Mountain House), 262s 870W (262s Rocky Mountain House), 262s 35 (262s Rocky Mountain House) | 2024-01-30 07:00 | 2024-01-30 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
FMGW | FMG1 Forty Mile Granlea | 2024-01-30 07:00 | 2024-01-30 23:00 | N | N |  | Unit
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 593s 823L (593s Lakeview) | 2024-01-30 08:00 | 2024-01-30 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 24.2TR (SS-24) | 2024-01-31 00:45 | 2024-02-04 06:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 908L (89s Ellerslie - 908AL tap), 908L (38s East Edmonton - 908AL tap) | 2024-01-31 07:00 | 2024-02-01 18:00 | N | Y |  | Line |  |  | 240 kV, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 908AL (52S East Industrial - 908L tap), 52s E2402 (52s East Industrial), 52s T2 (52s East Industrial) | 2024-01-31 07:00 | 2024-02-01 18:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2024-01-31 08:00 | 2024-02-01 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 2043s 701T (2043s Freer), 2043s 701 (2043s Freer) | 2024-01-31 08:00 | 2024-01-31 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28), SW83 (SS-28), 28MD138-28.1TR (SS-28) | 2024-01-31 08:00 | 2024-02-01 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
TRANSALTA | 418s T1 (418s Ardenville) | 2024-01-31 09:00 | 2024-01-31 15:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 2029s ACF22 (2029s Heathfield), 2029s 1223A (2029s Heathfield), 2029s ACF2D1 (2029s Heathfield) | 2024-02-01 02:00 | 2024-02-28 09:58 | N | Y |  | Shunts, Switch |  | Back early
EPCOR | 330P GT3 (330p Genesee), 330p 1207 (330p Genesee), 330p 1208 (330p Genesee) | 2024-02-01 07:00 | 2024-02-01 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 500 kV, Prevents Normal Events
ALTALINK | 71s 352 (71s Lamoureux) | 2024-02-01 14:15 | 2024-02-06 08:59 | N | N |  | Circuit Breaker
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2024-02-02 07:00 | 2024-02-02 18:00 | N | Y |  | Line |  |  | Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 310p 1352 (310p Sundance), 310p 1452 (310p Sundance), 665s D2403 (665s Dome) | 2024-02-02 07:00 | 2024-02-02 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1058L (657s Summerside - EP 803s Lambton) | 2024-02-03 07:00 | 2024-02-03 18:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1058L (657s Summerside - EP 803s Lambton) | 2024-02-03 07:00 | 2024-02-03 18:00 | N | Y |  | Line |  |  | 240 kV
EPCOR | 814s B2406 (814s Bellamy) | 2024-02-04 04:00 | 2024-02-06 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO, CNRL | 9L137 (838s Horizon Mining - 849s Joslyn Creek), 849s 904 (849s Joslyn Creek), 849s 905 (849s Joslyn Creek), 838s 904 (838s Horizon Mining), 838s 905 (838s Horizon Mining), 849s 9L137D1 (849s Joslyn Creek), 838s 9L137D2 (838s Horizon Mining) | 2024-02-04 08:00 | 2024-02-07 11:59 | N | Y |  | Line, Circuit Breaker, Switch |  | Due to 9L137 (from Feb 3) postponed | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 5.7TR (SS-5) | 2024-02-04 14:00 | 2024-02-08 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | H722 (EP Hardisty) | 2024-02-05 07:00 | 2024-02-06 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s T2 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s CDS31 (987s Clover Bar) | 2024-02-05 07:00 | 2024-02-26 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s C72C1 (987s Clover Bar), 987s C1 (987s Clover Bar) | 2024-02-05 07:00 | 2024-02-07 17:00 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ENMAX | 38.3TR (SS-38) | 2024-02-05 08:00 | 2024-02-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), SW89 (SS-9), 9MD138-9.1TR (SS-9), 31B138-9.80 (SS-31) | 2024-02-05 08:00 | 2024-02-07 13:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 443L (55s Olds - 214s Innisfail), 55s 443 (55S Olds), 214s 443 (214s Innisfail) | 2024-02-05 08:00 | 2024-02-08 17:23 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 133L (19s Wabamun - 234L tap), 19s 133 (19s Wabamun) | 2024-02-05 09:00 | 2024-02-05 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon), 5s 1552 (5s East Calgary), 5s 1652 (5s East Calgary), 5s 937 (5s East Calgary) | 2024-02-05 09:15 | 2024-02-08 16:45 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe), 198s 461 (198s Blackfalds), 212s 461 (212s N.E. Lacombe) | 2024-02-05 11:30 | 2024-02-16 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 808L (171s Redwater - 808AL tap), 171s 808E (171s Redwater) | 2024-02-05 12:00 | 2024-02-08 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 447s T2 (447s Enchant), 447s 410W (447s Enchant), 447s 409W (447s Enchant) | 2024-02-05 12:00 | 2024-02-05 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 174L (197s Bardo - 289s Saunders Lake), 197s 174W (197s Bardo) | 2024-02-06 06:00 | 2024-02-15 18:30 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 71s 352 (71s Lamoureux) | 2024-02-06 09:00 | 2024-02-08 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
TRANSALTA | 239s 138CB1 (239s Castle River) | 2024-02-06 10:00 | 2024-02-06 14:00 | N | N |  | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 896L (19s Wabamun - 432s Carvel), 19s 896 (19s Wabamun), 432s 896 (432s Carvel) | 2024-02-07 07:00 | 2024-02-08 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | H723 (EP Hardisty) | 2024-02-07 07:00 | 2024-02-08 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 35MD138-6.80 (SS-35), 6.80L (SS-6 - SS-35), 6.4TR (SS-6), 6B138-6.80 (SS-6), 6MD138-6.4TR (SS-6) | 2024-02-07 08:00 | 2024-02-09 18:00 | N | N |  | Switch, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | T4 (BCH Natal) | 2024-02-07 08:00 | 2024-02-08 16:00 | N | Y |  | Transformer |  |  | 240 kV
ALTALINK | 161L (255s Vulcan - 504s Queenstown) | 2024-02-07 21:50 | 2024-02-11 12:04 | N | N |  | Line |  | Back from storm damage early | For Information Only
EPCOR | 987s CC24 (987s Clover Bar) | 2024-02-08 07:00 | 2024-02-08 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 3.82L (SS-3 - SS-8) | 2024-02-08 08:00 | 2024-02-08 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 142s 138kV Bus (142s Magcan), 727AL (142s Magcan - 727L tap), 142s 3 (142s Magcan), 142s C1 (142s Magcan) | 2024-02-08 08:00 | 2024-02-08 15:30 | N | N |  | Bus, Line, Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 207s T2 (207S Pinedale) | 2024-02-08 09:00 | 2024-02-08 16:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s GB1B (987s Clover Bar) | 2024-02-09 07:00 | 2024-02-09 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
BCH | T2 (BCH Natal) | 2024-02-09 08:00 | 2024-02-09 16:00 | N | Y |  | Transformer |  |  | Pre-Condition
FORTIS | MON1 Monarch Generator Test | 2024-02-09 09:00 | 2024-06-21 12:00 | N | N |  | Unit
ENMAX | 6.4TR (SS-6) | 2024-02-09 18:00 | 2024-02-21 19:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 659s T1 (659s Pegasus Lake), 659s 289 (659s Pegasus Lake) | 2024-02-10 07:00 | 2024-02-11 18:00 | N | Y |  | Transformer, Switch |  |  | Restricts Generation
ENMAX | 5.8TR (SS-5) | 2024-02-11 07:00 | 2024-02-15 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2024-02-12 06:00 | 2024-02-21 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72LS24 (EP 803s Lambton - Strathcona), 72LH8 (EP 803s Lambton - EP Hardisty), H726 (EP Hardisty), EP 803s L721 (EP 803s Lambton), S724 (Strathcona), SDS10 (Strathcona) | 2024-02-12 07:00 | 2024-02-14 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 814s T2 (814s Bellamy), BR722 (Rossdale), 814s B2402 (814s Bellamy), 814s B2406 (814s Bellamy), 814s BAB2 (814s Bellamy) | 2024-02-12 07:00 | 2024-02-16 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Prevents Normal Events
ENMAX | 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5) | 2024-02-12 08:00 | 2024-03-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 35.2TR (SS-35) | 2024-02-12 08:00 | 2024-02-15 16:00 | N | N |  | Transformer
ENMAX | 5.5TR (SS-5) | 2024-02-12 08:00 | 2024-03-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.83L (SS-13 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5), 13B138-2.83 (SS-13) | 2024-02-12 08:00 | 2024-02-12 12:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2024-02-12 09:00 | 2024-02-18 16:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 9L40 (732s Mitsue - 809s Louise Creek) | 2024-02-12 09:00 | 2024-02-18 12:00 | N | Y |  | Line |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 916L (5s East Calgary - 42s Sarcee), 5s 1252 (5s East Calgary), 5s 1352 (5s East Calgary), 42s 916E (42s Sarcee) | 2024-02-12 09:30 | 2024-02-15 16:45 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 702L (137s Sedgewick - 377s AML Hardisty), 377s 702W (377s AML Hardisty) | 2024-02-12 12:15 | 2024-03-16 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
EPCOR | 330P SST3 (330P Genesee), 330p 801 (330p Genesee) | 2024-02-13 07:00 | 2024-02-17 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 15s 463 (15s Fort Macleod) | 2024-02-13 07:30 | 2024-02-13 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 8B138-7A0 (SS-8) | 2024-02-13 08:00 | 2024-02-13 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 47.1TR (SS-47) | 2024-02-13 08:00 | 2024-02-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 443L (55s Olds - 214s Innisfail), 55s 443 (55S Olds), 214s 443 (214s Innisfail) | 2024-02-13 08:00 | 2024-02-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound) | 2024-02-13 09:00 | 2024-02-19 12:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 744L (228s T.M.P.L. Niton - 744AL tap) | 2024-02-13 09:00 | 2024-02-20 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ERSP | SHH1 Sharp Hill Wind Generator Test | 2024-02-13 11:00 | 2024-02-13 12:00 | N | Y |  | Unit
ALTALINK | 180L (15s Fort Macleod - 180AL tap), 15s 180N (15s Fort Macleod) | 2024-02-14 07:30 | 2024-02-14 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 1081L (17s Benalto - 281s Johnson) | 2024-02-14 08:00 | 2024-02-19 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2024-02-14 08:00 | 2024-02-14 17:00 | N | Y |  | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 161L (255s Vulcan - 504s Queenstown), 255s 161 (255s Vulcan), 504s 161 (504s Queenstown) | 2024-02-16 08:00 | 2024-02-16 17:00 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2024-02-16 11:30 | 2024-02-23 15:00 | N | Y |  | Shunts |  |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32) | 2024-02-17 08:00 | 2024-02-17 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26) | 2024-02-17 12:00 | 2024-02-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 729L (542s Ervick - 729AL tap) | 2024-02-19 07:00 | 2024-02-19 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13B69-13.60 (SS-13), 27B69-13.60 (SS-27) | 2024-02-19 08:00 | 2024-03-02 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR, ATCO | 29EDD-1 260kV North Bus 1 (29EDD-1 Millennium), 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake), 29EDD-1 29EDD1s752 (29EDD-1 Millennium), 29EDD-1 29EDD1s452 (29EDD-1 Millennium), 29EDD-1 29EDD1s152 (29EDD-1 Millennium), 29EDD-1 29EDD1s252 (29EDD-1 Millennium), 29EDD-1 29EDD1s552 (29EDD-1 Millennium), 29EDD-1 952-101 (29EDD-1 Millennium), 29EDD-1 952-104 (29EDD-1 Millennium) | 2024-02-19 08:00 | 2024-03-15 18:00 | N | Y |  | Bus, Line, Circuit Breaker |  | Extended outage. | Affects Cranking Path
ATCO | 786s 703T (786s High Level), 786s SVC (786s High Level), 786s 703 (786s High Level) | 2024-02-19 10:00 | 2024-02-20 18:30 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L85 (803s ATC Bullpound - 7LA85 tap) | 2024-02-19 12:01 | 2024-02-22 17:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L27 (755s Cordel - 863s Paintearth), 863s 901 (863s Paintearth), 863s 9L27D2 (863s Paintearth) | 2024-02-19 14:30 | 2024-03-04 14:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station), 814s B2401 (814s Bellamy), 814s B2402 (814s Bellamy) | 2024-02-20 07:00 | 2024-02-21 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 39.2TR (SS-39) | 2024-02-20 07:00 | 2024-02-23 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s C1 (38s East Edmonton), 38s 3052 (38s East Edmonton), 38s Protection & Control (38s East Edmonton) | 2024-02-20 07:30 | 2024-03-08 17:30 | N | N |  | Shunts, Circuit Breaker, Terminal Equipment |  |  | Pre-Condition
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2024-02-20 08:00 | 2024-02-20 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 33.1TR (SS-33) | 2024-02-20 08:00 | 2024-02-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20) | 2024-02-20 08:00 | 2024-02-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon), 5s 1152 (5s East Calgary), 5s 1252 (5s East Calgary) | 2024-02-20 09:15 | 2024-02-22 16:45 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ATCO | 845s 705 (845s Big Mountain), 845s 705C (845s Big Mountain) | 2024-02-20 09:30 | 2024-02-23 17:30 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe), 212s 461 (212s N.E. Lacombe), 198s 461 (198s Blackfalds) | 2024-02-20 11:30 | 2024-03-01 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 744L (207s Pinedale - 228s T.M.P.L. Niton), 228s T1 (228s T.M.P.L. Niton) | 2024-02-20 15:00 | 2024-02-20 16:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 9L89 (885s McMillan - 2011s Dawes), 885s 901 (885s McMillan), 885s 902 (885s McMillan) | 2024-02-20 15:00 | 2024-03-04 09:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 289s Saunders Lake), 197s 174W (197s Bardo) | 2024-02-21 06:00 | 2024-03-01 18:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 330P 12TC2 (330p Genesee), 330p 809 (330p Genesee) | 2024-02-21 07:00 | 2024-03-05 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 330P SST2 (330P Genesee), 330p 803 (330p Genesee) | 2024-02-21 07:00 | 2024-03-02 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2024-02-21 07:00 | 2024-02-22 17:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | AML 511s T30 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings) | 2024-02-21 07:30 | 2024-02-21 15:30 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Pre-Condition
ATCO | 7L51 (ATC 793s West Peace River - 927s Buchanan Creek) | 2024-02-21 08:00 | 2024-02-21 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2024-02-21 08:00 | 2024-02-22 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
Saskpower | Sask Power PR901 | 2024-02-21 08:30 | 2024-02-21 09:30 | N | Y |  | Circuit Breaker |  |  | Limits ATC, Pre-Condition
ATCO | 780s 702 (780s Lubicon) | 2024-02-21 09:00 | 2024-02-21 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
Saskpower | Sask Power PR902 | 2024-02-21 10:00 | 2024-02-21 12:00 | N | Y |  | Circuit Breaker |  |  | Limits ATC, Pre-Condition
ATCO | 930s SVC (930s Arcenciel), 930s 718 (930s Arcenciel) | 2024-02-21 10:00 | 2024-02-23 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
Saskpower | Sask Power PR904 | 2024-02-21 10:30 | 2024-02-21 11:30 | N | Y |  | Circuit Breaker |  |  | Limits ATC, Pre-Condition
Lethbridge | 463L (181s Chinook - 463AL tap), 181s 463L (181s Chinook) | 2024-02-22 07:00 | 2024-02-22 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2024-02-22 08:00 | 2024-02-23 18:00 | N | Y |  | Line |  |  | Over/Under Voltage, Overload, Pre-Condition
ENMAX | 32.1TR (SS-32) | 2024-02-22 08:00 | 2024-02-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2024-02-22 08:00 | 2024-02-22 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 27.2TR (SS-27) | 2024-02-22 08:00 | 2024-02-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 71s 761W (71s Lamoureux), 71s 652 (71s Lamoureux), 71s 552 (71s Lamoureux), 38s 761N (38s East Edmonton) | 2024-02-22 08:00 | 2024-02-22 18:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | Pre-Condition, Prevents Normal Events
ALTALINK | 760L (163s Amoco Empress - 760AL tap), 163s 760N (163s Amoco Empress) | 2024-02-22 08:00 | 2024-02-29 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 27.1TR (SS-27) | 2024-02-23 08:00 | 2024-02-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 704L (51s Wainwright - 478s Tucuman), 478s 152 (478s Tucuman) | 2024-02-23 08:00 | 2024-02-23 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 6L02 (769s Stettler - 873s Marion Lake), 769s 601 (769s Stettler) | 2024-02-23 10:00 | 2024-02-23 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2024-02-26 06:00 | 2024-03-06 18:00 | N | N |  | Line |  |  | Pre-Condition
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s SU2401 (657s Summerside), 657s SU2402 (657s Summerside), S724 (Strathcona) | 2024-02-26 07:00 | 2024-02-28 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Garneau) | 2024-02-26 07:00 | 2024-03-22 17:00 | N | N |  | Transformer |  |  | Pre-Condition
ATCO | 806s 701T (806s Oldman River) | 2024-02-26 07:00 | 2024-02-28 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 2075s 906 (2075s Newell) | 2024-02-26 07:30 | 2024-02-26 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Prevents Normal Events
ENMAX | 36.2TR (SS-36) | 2024-02-26 08:00 | 2024-02-29 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 12L70 (12s Heartland - 2029s Heathfield), 2029s 1202B (2029s Heathfield), 2029s 1202 (2029s Heathfield), 2029s 1203 (2029s Heathfield), 2029s 1203A (2029s Heathfield) | 2024-02-26 08:00 | 2024-03-01 17:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | 500 kV, For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2024-02-26 09:00 | 2024-03-04 16:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 5s T1 (5s East Calgary), MD112 (SS-2) | 2024-02-26 09:30 | 2024-03-01 12:30 | N | Y |  | Transformer, Switch |  |  | 240 kV, Prevents Normal Events
ATCO | 2075S 912 (2075s Newell) | 2024-02-26 12:30 | 2024-02-26 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2024-02-27 06:30 | 2024-02-27 10:30 | N | N |  | Transformer | No need to request SLD. Open point 'A' is on the 25 kV bus (not modelled) |  | For Information Only
ALTALINK | 251s SR1 (251s Whitla) | 2024-02-27 07:30 | 2024-02-27 17:30 | N | Y |  | Shunts |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 2075s 922 (2075s Newell) | 2024-02-27 07:30 | 2024-02-27 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 5.7TR (SS-5) | 2024-02-27 08:00 | 2024-02-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 744L (207s Pinedale - 228s T.M.P.L. Niton), 207s 314 (207s Pinedale) | 2024-02-27 09:00 | 2024-03-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2024-02-27 10:30 | 2024-02-29 10:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L97 (933s Tower Road - 7LA97 tap), 933s 704 (933s Tower Road) | 2024-02-27 11:00 | 2024-02-29 16:00 | N | N |  | Line, Circuit Breaker | Emergency Real Time Failed relay - 5th Harmonic Protection Relay failed, will be blocked until a replacement can be installed | Equipment issues | Creates Radial Feeds, Firm Load Loss
ATCO | 2075s 919 (2075s Newell) | 2024-02-27 12:30 | 2024-02-27 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 780s 702 (780s Lubicon) | 2024-02-27 14:40 | 2024-03-01 18:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 103s 552 (103s Goose Lake) | 2024-02-28 05:00 | 2024-03-05 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 191s 792N (191s N.W. Cardiff), 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde) | 2024-02-28 06:00 | 2024-03-07 18:00 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 251s SR2 (251s Whitla) | 2024-02-28 07:30 | 2024-02-28 17:30 | N | Y |  | Shunts |  |  | Over/Under Voltage, Pre-Condition
ENMAX | 23.3TR (SS-23) | 2024-02-28 08:00 | 2024-02-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 54s C1 (54s Fort Saskatchewan) | 2024-02-28 08:00 | 2024-02-28 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2024-02-28 08:00 | 2024-02-28 16:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ATCO | 2075s 923 (2075s Newell) | 2024-02-28 08:30 | 2024-02-28 13:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
CMH | MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview) | 2024-02-28 10:00 | 2024-02-28 11:00 | N | N |  | Line |  |  | Overload
ALTALINK | 250p 11 (250p Bighorn Plant) | 2024-02-28 10:00 | 2024-02-28 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 37.2TR (SS-37) | 2024-02-29 08:00 | 2024-02-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5B138-5BT7 (SS-5) | 2024-02-29 08:00 | 2024-02-29 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 22 (250p Bighorn Plant) | 2024-02-29 10:00 | 2024-02-29 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2024-02-29 10:30 | 2024-02-29 13:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L64 (779s Chinchaga River - 789s Keg River), 789s 701 (789s Keg River) | 2024-02-29 12:00 | 2024-03-19 10:00 | N | Y |  | Line, Circuit Breaker |  | Completed early | Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 938L (77s Sagitawah - 809s Louise Creek) | 2024-03-01 07:00 | 2024-03-07 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 13L (65s High River - 392s Black Diamond), 65s 13N (65s High River) | 2024-03-01 08:00 | 2024-03-04 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L114 (907s Waddell - 7LA114 tap) | 2024-03-01 12:01 | 2024-03-05 07:00 | N | N |  | Line |  |  | Pre-Condition
ALTALINK | 793L (87s Gaetz - 535s Joffre) | 2024-03-02 08:00 | 2024-03-03 17:00 | N | N |  | Line |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 87s 138kV West Bus (87s Gaetz), 87s T1 (87s Gaetz), 87s 952 (87s Gaetz), 87s 552 (87s Gaetz), 87s 152 (87s Gaetz) | 2024-03-03 08:00 | 2024-03-03 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, GLPC | 688L (199s East Airdrie - 688BL tap), 688L (688AL tap - 688BL tap), 688BL (1055s Sollair - 688L tap), 199s 688 (199s East Airdrie), 1055s Sollair | 2024-03-04 07:00 | 2024-03-04 18:00 | N | Y |  | Line, Circuit Breaker, Station |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR, ALTALINK | 657s T1 (657s Summerside), 657s SU2404 (657s Summerside), 657s SU2405 (657s Summerside) | 2024-03-04 07:00 | 2024-03-08 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), H725 (EP Hardisty), 987s CH724 (987s Clover Bar) | 2024-03-04 07:00 | 2024-03-27 17:00 | N | N |  | Line, Circuit Breaker |  | back early | Creates Radial Feeds, Firm Load Loss, For Information Only
ALTALINK | 746s T1 (746s Sherwood Park) | 2024-03-04 08:00 | 2024-04-22 08:59 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 14.4TR (SS-14) | 2024-03-04 08:00 | 2024-03-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 37.1TR (SS-37) | 2024-03-04 08:00 | 2024-03-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.63L (SS-16 - SS-36), 36B69-16.63/36.5TR (SS-36), 16B69-16.63 (SS-16), 36.5TR (SS-36) | 2024-03-04 08:00 | 2024-03-07 18:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Pre-Condition
ENMAX | 5B138-2.82 (SS-5), 2.82L (SS-2 - SS-5) | 2024-03-04 08:00 | 2024-03-13 12:00 | N | N |  | Circuit Breaker, Line |  |  | Pre-Condition
ATCO | 7L760 (767s Oyen - 7LA760 tap), 767s 702 (767s Oyen) | 2024-03-04 09:00 | 2024-03-18 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 5s T2 (5s East Calgary), 138kV Bus Z32 (SS-2), 2B138-D84 (SS-2), 2B138-D88 (SS-2), 2B138-D91 (SS-2), 2B138-D96 (SS-2) | 2024-03-04 09:30 | 2024-03-08 12:30 | N | Y |  | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe), 212s 461 (212s N.E. Lacombe), 198s 461 (198s Blackfalds) | 2024-03-04 11:30 | 2024-03-07 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 948L (650s Hansman Lake - 863s Paintearth) | 2024-03-04 14:00 | 2024-03-18 15:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ATCO | 9L948 (650s Hansman Lake - 863s Paintearth), 863s 902 (863s Paintearth) | 2024-03-04 14:30 | 2024-03-18 15:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 289s Saunders Lake), 197s 174W (197s Bardo) | 2024-03-05 06:00 | 2024-03-22 18:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 910s 701T (910s Excel), 910s 701 (910s Excel) | 2024-03-05 07:00 | 2024-03-05 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 805L (86s Bigstone - 964s Pigeon Lake), 86s 152 (86s Bigstone) | 2024-03-05 08:30 | 2024-03-07 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L55 (743s Sarah Lake - 809s Louise Creek), 743s 701 (743s Sarah Lake), 809s 705 (809s Louise Creek) | 2024-03-05 09:00 | 2024-03-05 11:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
BCH | T1 (BCH Natal) | 2024-03-05 10:00 | 2024-03-05 16:00 | N | Y |  | Transformer |  |  | Pre-Condition
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee), 330p 1214 (330p Genesee), 330p 1210 (330p Genesee), 330p 12TC1D (330p Genesee), TLO1 (330p Genesee) | 2024-03-06 07:00 | 2024-04-04 17:00 | N | Y |  | Bus, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 74s 2152 (74s Janet) | 2024-03-06 07:30 | 2024-03-06 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 477s 138kV Bus (477s Amoco West Pembina), 841L (477s Amoco West Pembina - 489s Petro-Canada Brazeau River), 844L (358s Amoco Brazeau - 477s Amoco West Pembina), 477s T1 (477s Amoco West Pembina), 477s 844X (477s Amoco West Pembina), 477s 841X (477s Amoco West Pembina) | 2024-03-06 08:00 | 2024-03-07 07:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 74s 2252 (74s Janet) | 2024-03-06 13:00 | 2024-03-06 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-03-06 23:00 | 2024-03-07 03:00 | N | Y |  | Switch |  |  | For Information Only, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-03-07 03:00 | 2024-03-07 07:00 | N | Y |  | Switch |  |  | For Information Only, Restricts Generation
ALTALINK | 477s T1 (477s Amoco West Pembina) | 2024-03-07 06:30 | 2024-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 330P SST2 (330P Genesee) | 2024-03-07 08:00 | 2024-03-07 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 723L (69s North Barrhead - 724L tap), 69s 723E (69s North Barrhead) | 2024-03-08 07:00 | 2024-03-11 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 422s 700 (422s Westwood), 746s 700N (746s Sherwood Park) | 2024-03-08 08:30 | 2024-03-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 27.2TR (SS-27) | 2024-03-09 08:00 | 2024-03-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA | 33s T2 (33s Spray), 33s 2 (33s Spray) | 2024-03-09 08:00 | 2024-03-09 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2024-03-11 06:00 | 2024-03-20 18:00 | N | N |  | Line |  |  | Pre-Condition
EPCOR | EP 511s V727 (EP 511s Victoria) | 2024-03-11 07:00 | 2024-03-11 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T1 (805s Jasper) | 2024-03-11 07:00 | 2024-03-13 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ENMAX | 8B138-5A0 (SS-8) | 2024-03-11 08:00 | 2024-03-11 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 65B240-D135 (SS-65) | 2024-03-11 08:00 | 2024-03-11 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 349s T1 (349s Stavely), 349s 197 (349s Stavely), 349s 20 (349s Stavely) | 2024-03-11 08:00 | 2024-03-15 18:31 | N | Y |  | Transformer, Circuit Breaker, Switch | transmission constraint record is created. |  | Restricts Generation
ENMAX | 39.3TR (SS-39) | 2024-03-11 08:00 | 2024-03-14 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.1TR (SS-5) | 2024-03-11 08:00 | 2024-04-08 16:00 | N | N |  | Transformer |  |  | For Information Only
CMH | MH-20L (MHS-3 Southridge - MHS-6 CMH Riverview), MHS-3 MH138-T34 (MHS-3 Southridge), MHS-6 MH138-T63 (MHS-6 Riverview), MHS-3 MH138-317 (MHS-3 Southridge), MHS-6 MH138-620 (MHS-6 CMH Riverview) | 2024-03-11 09:00 | 2024-03-13 15:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L96 (BCH Selkirk - BCH Vaseux Lake) | 2024-03-11 09:00 | 2024-03-13 17:00 | N | Y |  | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 9L56 (720s Wabasca - 732s Mitsue), 720s 902 (720s Wabasca) | 2024-03-11 09:00 | 2024-03-15 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition, Prevents Normal Events, Affects Cranking Path
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 255s 34 (255s Vulcan) | 2024-03-11 09:30 | 2024-03-15 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Overload, Pre-Condition
ATCO, FMGW | 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s 952-600001 (1024s Granlea), 1024s PS-6005 (1024s Granlea), 1024s PS-6006 (1024s Granlea), 1024s PS-6007 (1024s Granlea), 1024s PS-6008 (1024s Granlea) | 2024-03-12 07:00 | 2024-03-13 18:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
EPCOR | EP 511s V728 (EP 511s Victoria) | 2024-03-12 07:00 | 2024-03-12 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK, REDDEER | 427L (63s Red Deer - 247s Piper Creek), 247s T1 (247s Piper Creek), 247s 427 (247s Piper Creek) | 2024-03-12 08:00 | 2024-03-12 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 162B240-RB136 (SS-162) | 2024-03-12 08:00 | 2024-03-12 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 287s 352 (287s Hazelwood) | 2024-03-12 08:00 | 2024-03-12 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 788L (898s Heart Lake - 788AL tap) | 2024-03-12 09:00 | 2024-03-12 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 744L (228s T.M.P.L. Niton - 744AL tap), 314L (207s Pinedale - 228s T.M.P.L. Niton), 228s T1 (228s T.M.P.L. Niton), 228s 314 (228s T.M.P.L. Niton), 228s 744 (228s T.M.P.L. Niton), 228s 30 (228s T.M.P.L. Niton), 228s 31 (228s T.M.P.L. Niton) | 2024-03-12 09:00 | 2024-03-19 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2024-03-12 09:30 | 2024-03-14 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 287s 552 (287s Hazelwood) | 2024-03-12 12:01 | 2024-03-12 17:00 | N | Y |  | Circuit Breaker | separate record to avoid overlap |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 191s 792N (191s N.W. Cardiff), 150s 792X (150s Clyde) | 2024-03-13 06:00 | 2024-03-21 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), RV722 (Rossdale) | 2024-03-13 07:00 | 2024-03-14 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 967L (138s Windy Flats - 370s North Lethbridge) | 2024-03-13 08:00 | 2024-03-14 17:00 | N | Y |  | Line |  |  | Pre-Condition
BCH, ALTALINK | 1L275 (799s Coleman - BCH Natal), 1CB2 (BCH Natal), 799s 786W (799s Coleman) | 2024-03-13 08:00 | 2024-03-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 786L (799s Coleman - BCH Natal) | 2024-03-13 09:00 | 2024-03-13 17:00 | N | Y |  | Line
ENMAX | 2.83L (SS-13 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5), 13B138-2.83 (SS-13) | 2024-03-13 13:00 | 2024-03-13 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload
ENMAX | 8.4TR (SS-8) | 2024-03-14 08:00 | 2024-03-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3), 13B138-3.84 (SS-13) | 2024-03-14 08:00 | 2024-03-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 275s 240kV Bus 1 (275s Jenner), 275s T1 (275s Jenner), 275s 2152 (275s Jenner), 275s 38 (275s Jenner) | 2024-03-15 08:00 | 2024-03-16 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 8.3TR (SS-8) | 2024-03-15 08:00 | 2024-03-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 6L03 (757s Battle River - 6L17 tap), 6L17 (759s Castor - 6L03 tap), 6L03 (775s Sullivan Lake - 6L17 tap), 757s 603 (757s Battle River) | 2024-03-15 09:30 | 2024-03-15 14:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-03-15 10:00 | 2024-03-15 14:00 | N | Y |  | Switch |  |  | Restricts Generation
EPCOR | 711L (113s Inland Cement - 747L tap), 113s T1 (113s Inland Cement), 113s T2 (113s Inland Cement) | 2024-03-16 07:00 | 2024-03-23 17:00 | N | N |  | Line, Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), 9MD138-9.1TR (SS-9) | 2024-03-16 08:00 | 2024-03-16 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.3TR (SS-31), 31.2TR (SS-31), 31B138-24.81 (SS-31), 31B138-31.84 (SS-31), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31) | 2024-03-17 08:00 | 2024-03-17 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.2TR (SS-31), 31.1C (SS-31), 31.1TR (SS-31), 31B138-9.80 (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31) | 2024-03-17 12:01 | 2024-03-17 16:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 702L (137s Sedgewick - 757s Battle River) | 2024-03-17 12:15 | 2024-03-24 17:45 | N | Y |  | Line |  |  | Over/Under Voltage, Restricts Generation
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2024-03-17 12:15 | 2024-03-24 17:45 | N | Y |  | Line |  |  | Pre-Condition
EPCOR, ALTALINK | 657s T2 (657s Summerside), 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside) | 2024-03-18 07:00 | 2024-03-22 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 39.4TR (SS-39) | 2024-03-18 08:00 | 2024-03-21 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21) | 2024-03-18 08:00 | 2024-04-03 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-94 29PP-97 260kV Bus (29EDD-94 Voyageur), 29PL9-162 (29EDD-94 Voyageur - 951s Thickwood Hills), 29PL9-193 (29EDD-94 Voyageur - 951s Thickwood Hills) | 2024-03-18 08:00 | 2024-04-01 18:00 | N | Y |  | Bus, Line |  | Completion of 1-00433729 outage. | 240 kV
REDDEER | 209T1 (209s Timberlands), 209s T1 (209s Timberlands) | 2024-03-18 08:00 | 2024-03-19 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 225L (225s Magrath - 225AL tap), 225L (67s Stirling - 225AL tap), 225AL (313s Raymond Reservoir - 225L tap), 67s 225 (67s Stirling), 225s 225E (225s Magrath) | 2024-03-18 08:00 | 2024-03-18 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8B138-5A0 (SS-8) | 2024-03-18 08:00 | 2024-03-18 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 32.83L (SS-32 - SS-40), 26.81L (SS-26 - SS-32), 32.1TR (SS-32), 32.2TR (SS-32), 32B138-32BT5 (SS-32), 32B138-32.83 (SS-32), 32B138-26.81 (SS-32) | 2024-03-18 08:00 | 2024-03-18 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.4TR (SS-21), 21.61L (SS-21 - SS-34), 15.60L (SS-15 - SS-21), 21B69-21.61 (SS-21), 21B69-15.60 (SS-21), 21B69-21.4TR (SS-21) | 2024-03-18 08:00 | 2024-03-20 16:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
WCLP | WCR1 Wheatcrest Generator Test | 2024-03-18 08:00 | 2024-03-18 16:00 | N | Y |  | Unit
BCH | 2L112 (BPA Boundary - BCH Nelway), T2 (BCH Natal) | 2024-03-18 09:00 | 2024-04-15 18:00 | N | Y |  | Line, Transformer |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 74s 102 (74s Janet), 74s 103 (74s Janet), 74s C3 (74s Janet), 74s C4 (74s Janet) | 2024-03-18 09:30 | 2024-03-19 17:30 | N | Y |  | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ATCO | 806s 701T (806s Oldman River) | 2024-03-18 11:00 | 2024-03-22 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32), 32B138-31.84 (SS-32) | 2024-03-18 12:00 | 2024-03-18 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 310p 1752 (310p Sundance) | 2024-03-18 12:30 | 2024-03-18 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 287s T1 (287s Hazelwood) | 2024-03-18 13:00 | 2024-03-21 17:30 | N | Y |  | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ATCO | 863s 902T (863s Paintearth) | 2024-03-18 14:30 | 2024-04-30 15:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana), 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte) | 2024-03-19 07:00 | 2024-03-19 18:30 | Y | Y |  | Line, Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Limits ATC, Pre-Condition
ENMAX | 32.1TR (SS-32) | 2024-03-19 08:00 | 2024-03-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.82L (SS-13 - SS-22), 22.3TR (SS-22), 22.1TR (SS-22), 22B138-22BT8 (SS-22), 22MD138-22.1TR (SS-22), 22MD138-22.3TR (SS-22), SW83 (SS-22), SW84 (SS-22) | 2024-03-19 08:00 | 2024-03-19 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 756L (87s Gaetz - 535s Joffre), 87s 152 (87s Gaetz), 87s 252 (87s Gaetz) | 2024-03-19 08:00 | 2024-03-19 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
WCLP | WCR1 Wheatcrest Generator Test | 2024-03-19 08:00 | 2024-03-19 09:00 | N | Y |  | Unit
ALTALINK | 435s T1 (435s Bassano), 435s 853A (435s Bassano) | 2024-03-19 08:30 | 2024-03-25 16:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky), 813s 703T (813s Little Smoky), 813s 719 (813s Little Smoky) | 2024-03-19 10:00 | 2024-03-21 17:30 | N | Y |  | Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | 557s CD2401 (557s Castle Downs) | 2024-03-20 07:00 | 2024-03-20 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
WCLP | WCR1 Wheatcrest Generator Test | 2024-03-20 08:00 | 2024-03-21 04:00 | N | Y |  | Unit
REDDEER | 194s T1 (194s South Red Deer), 194s T2 (194s South Red Deer) | 2024-03-20 08:00 | 2024-03-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 165s 156 (165s Gainford), 165s T1 (165s Gainford) | 2024-03-20 08:30 | 2024-03-20 13:30 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
BCH | 1L274 (978s BCH Britt Creek - BCH Greenhills tap) | 2024-03-20 09:00 | 2024-03-20 17:00 | Y | N |  | Line | 1L274 (Britt Creek - 1D4L274) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
ALTALINK | 38s 897 (38s East Edmonton), 897L (38s East Edmonton - 45s Bretona), 45s 897 (45s Bretona) | 2024-03-21 08:00 | 2024-03-21 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 789s 706C (789s Keg River) | 2024-03-21 09:00 | 2024-03-21 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2024-03-22 08:00 | 2024-03-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 310p 1852 (310p Sundance) | 2024-03-22 12:22 | 2024-04-22 06:59 | N | Y |  | Circuit Breaker |  |  | 240 kV
ENMAX | 8.1TR (SS-8) | 2024-03-24 08:00 | 2024-03-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2024-03-25 06:00 | 2024-03-28 18:00 | N | N |  | Line |  | In Early | Pre-Condition
ENMAX | 12.1TR (SS-12) | 2024-03-25 07:00 | 2024-03-28 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2024-03-25 07:00 | 2024-03-27 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
EPCOR | 987s T2 (987s Clover Bar), 987s T4 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2408 (987s Clover Bar), 987s CDS31 (987s Clover Bar), 987s CC721 (987s Clover Bar) | 2024-03-25 07:00 | 2024-04-23 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 54.1TR (SS-54) | 2024-03-25 08:00 | 2024-04-01 08:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43) | 2024-03-25 08:00 | 2024-03-25 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34), 15.60L (SS-15 - SS-21), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21B69-21.61 (SS-21), 34B69-21.61 (SS-34), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21), SW64 (SS-21), SW65 (SS-21) | 2024-03-25 08:00 | 2024-03-27 09:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 705s 703 (705s Kitscoty) | 2024-03-25 08:30 | 2024-03-25 11:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 932s 701 (932s Pemukan) | 2024-03-25 10:00 | 2024-03-25 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 33.84L (SS-33 - SS-43) | 2024-03-25 10:00 | 2024-03-25 11:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
WCLP | WCR1 Wheatcrest Generator Test | 2024-03-25 10:00 | 2024-03-25 14:00 | N | Y |  | Unit
ENMAX | 1.81L (SS-1 - SS-20) | 2024-03-25 11:00 | 2024-03-25 13:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 705s 704 (705s Kitscoty) | 2024-03-25 11:31 | 2024-03-25 15:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 244s 452 (244s Bowmanton) | 2024-03-25 12:00 | 2024-03-25 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 325s C1 (325s Leduc) | 2024-03-25 12:30 | 2024-03-25 15:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 89s 1852 (89s Ellerslie) | 2024-03-25 13:00 | 2024-03-25 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 1.80L (SS-1 - SS-28) | 2024-03-25 13:00 | 2024-03-25 14:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5CB1 (BCH Selkirk) | 2024-03-25 13:50 | 2024-05-31 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
CapitalPower | GNR2 Genesee Repower 2 Generator Test | 2024-03-25 19:00 | 2024-06-21 16:00 | N | N |  | Unit
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 37B138-37.82 (SS-37), 74s 37.82W (74s Janet) | 2024-03-25 22:00 | 2024-03-26 01:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 37B138-37.81 (SS-37), 38B138-37.81 (SS-38) | 2024-03-26 01:00 | 2024-03-26 05:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 172L (181s Chinook - 370s North Lethbridge), 370s 175 (370s North Lethbridge) | 2024-03-26 07:00 | 2024-03-26 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 244s 2652 (244s Bowmanton) | 2024-03-26 07:30 | 2024-03-26 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 932s 702 (932s Pemukan) | 2024-03-26 10:00 | 2024-03-26 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
WCLP | WCR1 Wheatcrest Generator Test | 2024-03-26 10:00 | 2024-03-26 14:00 | N | Y |  | Unit
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2024-03-26 10:30 | 2024-03-26 14:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek), 20s 859E (20s Ghost), AML 793s 859W (AML 793s Horse Creek) | 2024-03-26 12:00 | 2024-04-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s 352 (244s Bowmanton) | 2024-03-26 12:31 | 2024-03-26 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde), 191s 792N (191s N.W. Cardiff) | 2024-03-27 06:00 | 2024-04-05 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
Lethbridge, ALTALINK | 463L (181s Chinook - 463AL tap), 181s 463L (181s Chinook), 463L28 (463AL tap) | 2024-03-27 07:00 | 2024-03-27 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 244s 652 (244s Bowmanton) | 2024-03-27 07:30 | 2024-03-27 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 162B138-RB80 (SS-162) | 2024-03-27 08:00 | 2024-03-27 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22.81 (SS-22), 22B138-22BT8 (SS-22), 39B138-22.81 (SS-39), SW85 (SS-22), 22MD138-22.2TR (SS-22) | 2024-03-27 08:00 | 2024-03-27 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 207s T1 (207s Pinedale) | 2024-03-27 09:00 | 2024-03-27 16:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 932s 703 (932s Pemukan) | 2024-03-27 10:00 | 2024-03-27 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 244s 152 (244s Bowmanton) | 2024-03-27 12:30 | 2024-03-27 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 244s 2552 (244s Bowmanton) | 2024-03-28 07:30 | 2024-03-28 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO, ALTALINK | 7L230 (69s North Barrhead - 888AL tap), 888AL (234s Fort Assiniboine - 7L230 tap), 69s 230W (69s North Barrhead), 234s 888 (234s Fort Assiniboine) | 2024-03-29 07:00 | 2024-03-29 12:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO, ALTALINK | 7L230 (743s Sarah Lake - 888AL tap), 7L230 (69s North Barrhead - 888AL tap), 743s 703 (743s Sarah Lake) | 2024-03-29 08:00 | 2024-03-29 12:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 65.2TR (SS-65), 65B138-D85 (SS-65), 65B138-D82 (SS-65), 65B240-D132 (SS-65), 65B240-D135 (SS-65), 65MD138-65.2TR (SS-65), 65MD240-65.2TR (SS-65) | 2024-03-30 08:00 | 2024-04-01 18:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 3GSU-XF-001 (SS-25) | 2024-03-31 08:00 | 2024-04-19 16:00 | N | Y |  | Transformer |  |  | 240 kV
SUNCOR | 29EDD-71 29PT-235 (29EDD-71), 29EDD-71 752-4642 (29EDD-71), 29EDD-71 752-4641 (29EDD-71) | 2024-04-01 | 2024-05-01 | N | N |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 12.2TR (SS-12) | 2024-04-01 07:00 | 2024-04-04 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 8.5TR (SS-8), 8.6TR (SS-8), 8B138-2A0 (SS-8), 8B138-3A0 (SS-8), 2A10 (SS-8), 3A1 (SS-8) | 2024-04-01 08:00 | 2024-04-17 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
EPCOR | 814s T1 (814s Bellamy), 814s B2407 (814s Bellamy), 814s B2401 (814s Bellamy), 814s BAB1 (814s Bellamy), BR721 (Rossdale) | 2024-04-02 07:00 | 2024-04-02 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | T1 (Garneau), GT1 (Garneau) | 2024-04-02 07:00 | 2024-12-05 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), 657s SU2403 (657s Summerside), 657s SU2404 (657s Summerside), 657s SUDS10 (657s Summerside) | 2024-04-02 07:00 | 2024-04-04 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s 240kV Bus 1 (244s Bowmanton), 244s 138kV Bus 1 (244s Bowmanton), 244s T1 (244s Bowmanton), 244s 452 (244s Bowmanton), 244s 152 (244s Bowmanton), 244s 2552 (244s Bowmanton), 244s 2152 (244s Bowmanton), 244s 2589 (244s Bowmanton), 244s 2289 (244s Bowmanton), 244s 2189 (244s Bowmanton) | 2024-04-02 07:00 | 2024-04-02 18:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, ATCO | 702L (137s Sedgewick - 757s Battle River), 757s 708 (757s Battle River) | 2024-04-02 07:15 | 2024-04-08 17:45 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Restricts Generation
ALTALINK | 299s T1 (299s Kingman), 299s 732N (299s Kingman) | 2024-04-02 07:30 | 2024-04-03 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 221s T2 (221s Sunken Lake) | 2024-04-02 07:30 | 2024-04-02 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc), 325s 838 (325s Leduc), 14s 838X (14s Devon) | 2024-04-02 08:00 | 2024-04-02 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
SUNCOR | 29PL6-5 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-1 29EDD1s1652 (29EDD-1 Millennium), 29EDD-1 29EDD1s1752 (29EDD-1 Millennium), 29EDD-1 29PS-196 (29EDD-1 Millennium), 29PS-44 (29EDD-22) | 2024-04-02 08:00 | 2024-04-24 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ATCO, CNRL, ALBIAN | 847s 902T (847s Muskeg River), 919s 908 (919s Hartley) | 2024-04-02 08:00 | 2024-04-12 08:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5), 2MD138-2.82 (SS-2) | 2024-04-02 08:00 | 2024-04-10 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 65.1TR (SS-65), 65B138-D83 (SS-65), 65B138-D81 (SS-65), 65B240-D130 (SS-65), 65B240-D133 (SS-65), 65MD240-65.1TR (SS-65), 65MD138-65.1TR (SS-65) | 2024-04-02 08:00 | 2024-04-04 18:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 932s 722C (932s Pemukan) | 2024-04-02 10:00 | 2024-04-02 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 158s T2 (158s Vauxhall) | 2024-04-02 12:30 | 2024-04-11 16:00 | N | Y |  | Bus | transmission constraint record is created. |  | Restricts Generation
ALTALINK | 74s C1 (74s Janet), 74s C2 (74s Janet) | 2024-04-02 12:30 | 2024-04-03 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 103s 1752 (103s Goose Lake) | 2024-04-02 13:30 | 2024-04-02 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 221s T2 (221s Sunken Lake) | 2024-04-02 17:00 | 2024-04-04 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 244s 240kV Bus 2 (244s Bowmanton), 244s 138kV Bus 2 (244s Bowmanton), 244s T2 (244s Bowmanton), 244s 352 (244s Bowmanton), 244s 652 (244s Bowmanton), 244s 2652 (244s Bowmanton), 244s 2252 (244s Bowmanton), 244s 2389 (244s Bowmanton), 244s 2489 (244s Bowmanton) | 2024-04-03 07:00 | 2024-04-03 18:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 453L (305s Acheson - 367s Harry Smith), 305s 453 (305s Acheson), 367s 453 (367s Harry Smith) | 2024-04-03 07:00 | 2024-04-03 14:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy), 814s BDS20 (814s Bellamy), 816s PDS11 (816s Petrolia) | 2024-04-03 07:00 | 2024-04-03 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21) | 2024-04-03 08:00 | 2024-04-03 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | TL-2 (Aurora - Aurora) | 2024-04-03 08:00 | 2024-04-12 16:00 | N | N |  | Line |  |  | For Information Only
ENMAX | 22.81L (SS-22 - SS-39), 22B138-22.81 (SS-22), 39B138-22.81 (SS-39) | 2024-04-03 08:00 | 2024-04-03 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 631L (186s Dry Creek - 199s East Airdrie) | 2024-04-03 08:00 | 2024-04-03 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 613L (103s Goose Lake - 396s Pincher Creek), 396s 20 (396s Pincher Creek) | 2024-04-03 08:30 | 2024-04-03 17:30 | N | Y |  | Line, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 932s 723C (932s Pemukan) | 2024-04-03 10:00 | 2024-04-03 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34) | 2024-04-03 10:00 | 2024-04-03 13:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 161L (255s Vulcan - 504s Queenstown), 504s 161 (504s Queenstown), 255s 161 (255s Vulcan) | 2024-04-04 08:00 | 2024-04-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 194s T1 (194s South Red Deer), 194s T2 (194s South Red Deer) | 2024-04-04 08:00 | 2024-04-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 256s T2 (256s Harmattan) | 2024-04-04 08:00 | 2024-04-04 17:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | UT2 (Aurora) | 2024-04-04 08:00 | 2024-04-10 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 103s 1552 (103s Goose Lake) | 2024-04-04 08:30 | 2024-04-04 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 64s T2 (64s East Crossfield), 64s 240kV Bus (64s East Crossfield), 901AL (64s East Crossfield - 901L tap), 64s 901 (64s East Crossfield) | 2024-04-04 09:00 | 2024-04-04 16:45 | N | Y |  | Transformer, Bus, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16) | 2024-04-04 09:00 | 2024-04-04 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34) | 2024-04-04 10:01 | 2024-04-04 11:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 103s 1652 (103s Goose Lake) | 2024-04-04 12:31 | 2024-04-04 16:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO, PWLP | 973s 52-240 (973s Lanes Lake), 973s 89-T1 (973s Lanes Lake), 973s 89-T2 (973s Lanes Lake) | 2024-04-05 08:00 | 2024-04-06 12:00 | N | Y |  | Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX | 13.82L (SS-13 - SS-22), 13B138-13.82 (SS-13), 22B138-13.82 (SS-22) | 2024-04-05 08:00 | 2024-04-07 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 1109L (SS-25 - SS-65), 25B240-D141 (SS-25), 25B240-D142 (SS-25), 65B240-D135 (SS-65), 65B240-D134 (SS-65), 25MD240-1109 (SS-25), 65MD240-1109 (SS-65) | 2024-04-05 08:00 | 2024-04-06 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 2GSU-XF-001 (SS-25) | 2024-04-05 08:00 | 2024-04-11 15:00 | N | Y |  | Transformer |  |  | 240 kV
EPCOR | 330p 12GT7D (330p Genesee) | 2024-04-05 13:00 | 2024-05-28 17:00 | N | Y |  | Switch |  |  | For Information Only
ALTALINK | 792L (92s Viscount - 191s N.W. Cardiff), 92s 792 (92s Viscount), 191s 792X (191s N.W. Cardiff) | 2024-04-06 07:00 | 2024-04-06 16:28 | N | N |  | Line, Circuit Breaker |  | completed early. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 330p 12GT6D (330p Genesee), 330p 1210 (330p Genesee), 330p 1211 (330p Genesee) | 2024-04-07 07:00 | 2024-04-08 13:00 | N | Y |  | Switch, Circuit Breaker |  |  | 500 kV
ENMAX, ALTALINK | 1080L (SS-25 - SS-65), 25B240-D139 (SS-25), 25B240-D138 (SS-25), 65B240-D132 (SS-65), 65B240-D131 (SS-65) | 2024-04-07 08:00 | 2024-04-08 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 757s 705T (757s Battle River), 757s 705 (757s Battle River) | 2024-04-07 09:00 | 2024-04-12 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 64s 452 (64s East Crossfield), 752L (64s East Crossfield - 752AL tap) | 2024-04-07 10:30 | 2024-04-12 17:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 665s T3 (665s Dome), 665s D721 (665s Dome), 665s D2404 (665s Dome), S721 (Strathcona), 72DS26 (665s Dome - Strathcona) | 2024-04-08 07:00 | 2024-04-12 17:00 | N | Y |  | Transformer, Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 41.1TR (SS-41) | 2024-04-08 07:00 | 2024-04-11 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 330p 1201 (330p Genesee) | 2024-04-08 07:00 | 2024-04-19 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ALTALINK | 535s T4 (535s Joffre) | 2024-04-08 07:30 | 2024-04-12 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 41B138-33.83 (SS-41), 33B138-33.83 (SS-33) | 2024-04-08 08:00 | 2024-04-08 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.82L (SS-1 - SS-5), 5.1TR (SS-5), 5.6TR (SS-5), 5.8TR (SS-5), 5B138-5BT12 (SS-5), 5B138-5BT7 (SS-5), 5MD138-5.6TR (SS-5), 5MD138-5.8TR (SS-5), 5B138-1.82 (SS-5) | 2024-04-08 08:00 | 2024-04-27 09:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 2075s ACF11 (2075s Newell), 2075s 901T (2075s Newell), 2075S 927 (2075s Newell) | 2024-04-08 08:00 | 2024-04-12 17:00 | N | Y |  | Shunts, Transformer, Circuit Breaker |  |  | 240 kV
ATCO | 728s 701T (728s Mercer Hill), 728s 501TD (728s Mercer Hill), 728s 503 (728s Mercer Hill), 728s 52-1 (728s Mercer Hill), 728s 52-2 (728s Mercer Hill) | 2024-04-08 10:00 | 2024-04-19 16:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | Restricts Generation
ATCO | 786s SVC (786s High Level), 786s 703T (786s High Level), 786s 703 (786s High Level) | 2024-04-08 10:00 | 2024-04-17 16:20 | N | Y |  | Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 716s 701T (716s Lloydminster), 716s 703 (716s Lloydminster) | 2024-04-08 10:55 | 2024-06-04 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 716s 701C (716s Lloydminster) | 2024-04-08 11:00 | 2024-06-02 17:00 | N | N |  | Shunts | {OUTAGE REASON: 716S Lloyd sub rebuild 701C new relay install & commission} |  | Pre-Condition
ATCO | 716s 701 (716s Lloydminster) | 2024-04-08 11:00 | 2024-06-04 17:00 | N | N |  | Circuit Breaker | {OUTAGE REASON: 716S Lloyd sub rebuild 7L749 new line relay install & commission} | extended | Pre-Condition
ALTALINK | 710L (56s Boyle - 159s Colinton), 56s 138kV Bus 2 (56s Boyle), 56s T2 (56s Boyle), 56s 710X (56s Boyle), 159s 710 (159s Colinton), 56s C1 (56s Boyle) | 2024-04-08 12:15 | 2024-04-11 17:45 | N | N |  | Line, Bus, Transformer, Circuit Breaker, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 86s T1 (86s Bigstone) | 2024-04-08 13:00 | 2024-04-11 18:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 753L (65s High River - 253s Blackie), 65s 753E (65s High River), 253s 753W (253s Blackie) | 2024-04-08 13:00 | 2024-04-10 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
Lethbridge, ALTALINK | 674s 725W (674s Bowron), 725L (674s Bowron - 725BL tap) | 2024-04-09 07:00 | 2024-04-09 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33) | 2024-04-09 08:00 | 2024-04-09 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 240kV West Bus (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25) | 2024-04-09 08:00 | 2024-04-14 18:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 985L (74s Janet - SS-25), 25B240-D132 (SS-25), 25B240-D133 (SS-25), 25MD240-985 (SS-25) | 2024-04-09 08:00 | 2024-04-11 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 7L42 (716s Lloydminster - 751s Hill), 7L749 (716s Lloydminster - 7LB749 tap) | 2024-04-09 08:00 | 2024-04-09 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 89s T2 (89s Ellerslie) | 2024-04-09 08:00 | 2024-04-10 17:30 | N | Y |  | Transformer |  |  | 500 kV, Overload, Pre-Condition
ERSP | SHH1 Sharp Hill Wind Generator Test | 2024-04-09 09:30 | 2024-04-09 12:30 | N | Y |  | Unit
CMH | 4L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview) | 2024-04-09 10:00 | 2024-04-09 11:00 | N | N |  | Line |  |  | Overload
EPCOR | 330p 1206 (330p Genesee) | 2024-04-09 12:00 | 2024-04-09 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 404s Peace Butte, 600L (404s Peace Butte - 523s Bullshead), 523s 600 (523s Bullshead), 404s 12 (404s Peace Butte), 404s 600 (404s Peace Butte) | 2024-04-09 12:30 | 2024-04-09 17:30 | N | N |  | Station, Line, Circuit Breaker, Switch |  |  | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel), 930s 719 (930s Arcenciel), 930s 702T (930s Arcenciel) | 2024-04-09 13:00 | 2024-04-10 17:00 | N | Y |  | Shunts, Circuit Breaker, Transformer |  |  | Pre-Condition
ALTALINK | 151s C1 (151s Strathmore) | 2024-04-09 15:00 | 2024-06-18 16:30 | N | N |  | Shunts
EPCOR | 330p 1209 (330p Genesee) | 2024-04-10 07:00 | 2024-04-10 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
Lethbridge, ALTALINK | 674s 725E (674s Bowron), 725L (674s Bowron - 725AL tap) | 2024-04-10 07:00 | 2024-04-10 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 321s 880 (321s Al Rothbauer), 523s 880 (523s Bullshead) | 2024-04-10 07:00 | 2024-04-10 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 43.2TR (SS-43), 43B138-33.84 (SS-43), SW84 (SS-43), 43MD138-43.2TR (SS-43) | 2024-04-10 08:00 | 2024-04-11 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 5s 1552 (5s East Calgary) | 2024-04-10 08:00 | 2024-04-11 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
CMH | MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview) | 2024-04-10 10:00 | 2024-04-10 11:00 | N | N |  | Line |  |  | Overload, Pre-Condition
ENMAX | 1GSU-XF-001 (SS-25) | 2024-04-11 07:12 | 2024-04-17 15:00 | N | Y |  | Transformer |  |  | 240 kV
ALTALINK | 523s T1 (523s Bullshead) | 2024-04-11 07:30 | 2024-04-11 17:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 1003L (74s Janet - SS-25), 25B240-D136 (SS-25), 25B240-D135 (SS-25), 74s 1003X (74s Janet), 25MD240-1003 (SS-25) | 2024-04-11 08:00 | 2024-04-12 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
Syncrude | UT1 (Aurora) | 2024-04-11 08:00 | 2024-04-19 16:00 | N | N |  | Transformer |  | Outage returned early. | For Information Only
ALTALINK | 263s T1 (263s Strachan) | 2024-04-11 08:00 | 2024-04-11 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2024-04-11 09:00 | 2024-04-11 13:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 746L (700L tap - 746AL tap), 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2024-04-12 07:00 | 2024-04-14 18:00 | N | N |  | Line, Circuit Breaker | Outage date changed from Feb 28th,2024 because of land access issues |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 804L (40s 803L tap - 86s 803L tap), 804L (40s Wetaskiwin - 40s 803L tap), 804L (86s Bigstone - 86s 803L tap) | 2024-04-12 07:00 | 2024-04-14 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake) | 2024-04-12 07:00 | 2024-04-15 18:00 | N | N |  | Line |  |  | Over/Under Voltage, Pre-Condition
ALTALINK | 760L (163s Amoco Empress - 760AL tap), 163s 760N (163s Amoco Empress) | 2024-04-12 08:00 | 2024-04-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
Syncrude | 14 (Aurora) | 2024-04-12 08:00 | 2024-04-23 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39) | 2024-04-12 08:00 | 2024-04-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 924L (102s Langdon - 356s Milo) | 2024-04-13 07:00 | 2024-04-20 18:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 535s T5 (535s Joffre) | 2024-04-13 07:30 | 2024-04-17 18:00 | N | N |  | Transformer
ALTALINK | 611L (186s Dry Creek - 391S Balzac), 391s 611 (391s Balzac), 186s 611 (186s Dry Creek) | 2024-04-13 08:00 | 2024-04-19 16:00 | N | N |  | Line, Circuit Breaker |  | Outage returned early. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 669L (163s Amoco Empress - 562s Cypress), 163s 669 (163s Amoco Empress) | 2024-04-13 08:00 | 2024-04-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29PL9-6 (29EDD-1 Millennium - 29EDD-34), 29EDD-1 952-105 (29EDD-1 Millennium), 29EDD-1 952-106 (29EDD-1 Millennium), 29EDD-34 29-952-111 (29EDD-34), 29EDD-34 29-952-112 (29EDD-34) | 2024-04-13 08:00 | 2024-04-26 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 163s 760X (163s Amoco Empress), 760L (163s Amoco Empress - 394s Empress) | 2024-04-14 08:00 | 2024-04-14 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 814s T1 (814s Bellamy), BR721 (Rossdale), 814s B2407 (814s Bellamy), 814s B2401 (814s Bellamy) | 2024-04-15 07:00 | 2024-04-17 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2024-04-15 07:00 | 2024-04-18 12:00 | N | Y |  | Line |  |  | Pre-Condition
ENMAX | 41.2TR (SS-41) | 2024-04-15 07:00 | 2024-04-18 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 665s T1 (665s Dome), 665s D2401 (665s Dome), 665s D2402 (665s Dome) | 2024-04-15 07:00 | 2024-04-16 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 816s P2402 (816s Petrolia), 816s P2401 (816s Petrolia), 816s T1 (816s Petrolia) | 2024-04-15 07:00 | 2024-05-17 17:00 | N | Y |  | Circuit Breaker, Transformer | transmission constraint record is created. |  | 240 kV, Contingency Requires Mitigation, Restricts Generation
ENMAX | 32B138-26.81 (SS-32), 26.81L (SS-26 - SS-32), 26.1TR (SS-26), 26B138-26BT3 (SS-26), 26B138-26.81 (SS-26) | 2024-04-15 08:00 | 2024-04-15 16:00 | N | N |  | Circuit Breaker, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36B69-16.63/36.5TR (SS-36), 16B69-16.63 (SS-16) | 2024-04-15 08:00 | 2024-04-28 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 163s C1 (163s Amoco Empress), 163s C2 (163s Amoco Empress) | 2024-04-15 08:00 | 2024-04-15 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 1GSU-XF-001 (SS-25), 25B240-D132 (SS-25), 25B240-D131 (SS-25) | 2024-04-15 08:00 | 2024-04-15 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
BCH | 5L96 (BCH Selkirk - BCH Vaseux Lake) | 2024-04-15 09:00 | 2024-04-16 17:00 | N | Y |  | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
BCH | 5L96 (BCH Selkirk - BCH Vaseux Lake) | 2024-04-15 09:00 | 2024-04-16 17:00 | N | Y |  | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 48s T1 (48s Pocaterra), 48s T2 (48s Pocaterra) | 2024-04-15 10:00 | 2024-05-02 18:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt), 54s 709N (54s Fort Saskatchewan), 172s 709X (172s Sherritt) | 2024-04-15 10:00 | 2024-04-18 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ALTALINK | 3L (42s Sarcee - 272s Springbank), 42s 3W (42s Sarcee) | 2024-04-15 12:30 | 2024-04-15 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 28s T2 (28s West Brooks) | 2024-04-15 13:30 | 2024-04-18 12:00 | N | Y |  | Transformer |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ATCO | 790s 703T (790s Poplar Hill), 790s 704 (790s Poplar Hill) | 2024-04-15 15:00 | 2024-04-17 09:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 7L701 (757s Battle River - 7LA701 tap) | 2024-04-16 07:00 | 2024-04-30 18:00 | N | Y |  | Line |  |  | For Information Only
EPCOR | 330p 1214 (330p Genesee), 330p 1215 (330p Genesee), 330p 1215A (330p Genesee), 330p 1214B (330p Genesee) | 2024-04-16 07:00 | 2024-04-27 17:00 | N | Y |  | Circuit Breaker, Switch |  |  | 500 kV, For Information Only
ALTALINK, ENBRIDGE | 317s T2 (317s Baseline) | 2024-04-16 07:00 | 2024-04-16 19:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 701L (223s Strome - 7LA701 tap) | 2024-04-16 07:00 | 2024-04-30 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 788AL (140s Thompson - 788L tap), 140s T1 (140s Thompson), 140s 152 (140s Thompson) | 2024-04-16 07:30 | 2024-04-16 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 523s 552 (523s Bullshead) | 2024-04-16 07:30 | 2024-04-16 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 869L (163s Amoco Empress - 204s Sandy Point), 204s T1 (204s Sandypoint), 163s 869W (163s Amoco Empress), 204s 869E (204s Sandy Point) | 2024-04-16 08:00 | 2024-04-16 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 3GSU-XF-001 (SS-25), 25B240-D140 (SS-25), 25B240-D141 (SS-25) | 2024-04-16 08:00 | 2024-04-16 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 289s T1 (289s Saunders Lake) | 2024-04-16 08:30 | 2024-04-18 17:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 575s T1 (575s Sundre) | 2024-04-16 09:00 | 2024-04-25 15:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 42s 21 (42s Sarcee), 21B138-21.80 (SS-21) | 2024-04-16 09:00 | 2024-04-16 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 39s 252 (39s Bickerdike) | 2024-04-16 10:00 | 2024-04-18 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 42s 28 (42s Sarcee), 28B138-28.80 (SS-28) | 2024-04-16 13:00 | 2024-04-16 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 739L (14s Devon - 305s Acheson), 14s 739N (14s Devon), 305s 739 (305s Acheson) | 2024-04-17 07:00 | 2024-04-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt), 54s 709N (54s Fort Saskatchewan), 172s 709X (172s Sherritt) | 2024-04-17 07:00 | 2024-04-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2024-04-17 07:00 | 2024-04-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s C1 (523s Bullshead), 523s 33 (523s Bullshead) | 2024-04-17 07:30 | 2024-04-17 12:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 42s 150W (42s Sarcee), 150L (42s Sarcee - 150AL tap), 150L47 (150AL tap) | 2024-04-17 07:30 | 2024-04-17 17:30 | N | N |  | Circuit Breaker, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.83L (SS-9 - SS-43), 2.81L (SS-2 - SS-9), 9.3TR (SS-9), 9.2TR (SS-9), 9MD138-9.3TR (SS-9), 9MD138-9.2TR (SS-9), SW83 (SS-9), SW84 (SS-9) | 2024-04-17 08:00 | 2024-04-17 18:00 | N | N |  | Line, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen) | 2024-04-17 09:00 | 2024-04-26 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L09 (767s Oyen - 6L21 tap), 767s 601 (767s Oyen) | 2024-04-17 09:30 | 2024-04-26 14:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2024-04-17 10:00 | 2024-04-17 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 928L (17s Benalto - 42s Sarcee), 42s 928N (42s Sarcee), 17s 928X (17s Benalto) | 2024-04-17 12:30 | 2024-04-17 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ENMAX | 2GSU-XF-001 (SS-25), 25B240-D135 (SS-25), 25B240-D134 (SS-25), 25MD240-2GSU (SS-25) | 2024-04-18 08:00 | 2024-04-19 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10) | 2024-04-18 09:00 | 2024-04-18 13:00 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
ALTALINK, ENMAX | 42s 693 (42s Sarcee), 693L (42s Sarcee - SS-10), 10B138-693 (SS-10) | 2024-04-18 09:00 | 2024-04-18 13:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 7L61 (780s Lubicon - 796s Nipisi), 780s 703 (780s Lubicon), 780s 704 (780s Lubicon), 796s 701 (796s Nipisi) | 2024-04-18 10:00 | 2024-04-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 22 (250p Bighorn Plant) | 2024-04-18 10:00 | 2024-04-18 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 452L (367s Harry Smith - 434s Stony Plain), 434s 452 (434s Stony Plain) | 2024-04-19 08:00 | 2024-04-20 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane), 44s 860W (44s Bearspaw Plant), 291s 860 (291s Cochrane) | 2024-04-19 08:00 | 2024-04-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
FCSF | FCS1 Fox Coulee Solar Generator Test | 2024-04-19 08:30 | 2024-04-19 17:00 | N | Y |  | Unit
ENMAX | 240kV East Bus (SS-25), 25B240-D140 (SS-25), 25B240-D134 (SS-25), 25B240-D131 (SS-25), 25B240-D138 (SS-25) | 2024-04-20 08:00 | 2024-04-21 16:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1038L (237s Foothills - 266s SC1), 1038L (138s Windy Flats - 266s SC1), 266s 1038L FSC2 (266s SC1) | 2024-04-21 | 2024-04-24 17:00 | N | Y |  | Line, Shunts |  |  | 240 kV
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2024-04-21 07:00 | 2024-04-21 18:00 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
SUNCOR | 29EDD-71 752-4624 (29EDD-71) | 2024-04-21 08:00 | 2024-04-25 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 831L (121s Brooks - 831AL tap), 831L (339s Duchess - 831AL tap), 121s 831N (121s Brooks), 227s 831AW (227s Cutting Lake) | 2024-04-21 08:00 | 2024-04-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar), 987s CDS31 (987s Clover Bar) | 2024-04-21 12:00 | 2024-04-23 16:00 | N | Y |  | Transformer, Switch |  |  | 240 kV
ENMAX | 41.2TR (SS-41) | 2024-04-22 02:00 | 2024-04-23 07:59 | N | N |  | Transformer |  |  | For Information Only
ATCO | 2075s 900SST2 (2075s Newell) | 2024-04-22 02:00 | 2024-04-26 16:00 | N | Y |  | Transformer |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale), 987s CK725 (987s Clover Bar) | 2024-04-22 07:00 | 2024-04-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 665s T2 (665s Dome), 665s D2402 (665s Dome), 665s D2403 (665s Dome), 665s DDS14 (665s Dome), 665s DAB2 (665s Dome) | 2024-04-22 07:00 | 2024-04-26 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 310p 1852 (310p Sundance) | 2024-04-22 07:00 | 2024-04-25 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 14.3TR (SS-14) | 2024-04-22 07:00 | 2024-05-17 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 803s L2401 (EP 803s Lambton) | 2024-04-22 07:00 | 2024-04-22 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 330P SST3 (330P Genesee) | 2024-04-22 07:00 | 2024-04-26 17:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
EPCOR | 330P SST1 (330P Genesee) | 2024-04-22 07:00 | 2024-04-26 17:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
EPCOR | 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2024-04-22 07:00 | 2024-04-27 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 344s T2 (344s Warner) | 2024-04-22 08:00 | 2024-04-25 16:30 | N | N |  | Line, Transformer |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays), 121s 795X (121s Brooks), 421s 795N (421s Hays) | 2024-04-22 08:00 | 2024-04-22 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 13B138-13.82 (SS-13), 22B138-13.82 (SS-22) | 2024-04-22 08:00 | 2024-04-22 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 150A1L (180s Cope Creek - 150AL tap), 180s T1 (180s Cope Creek), 180s T2 (180s Cope Creek), 180s 152 (180s Cope Creek), 180s 252 (180s Cope Creek), 180s 189 (180s Cope Creek), 180s 289 (180s Cope Creek) | 2024-04-22 08:30 | 2024-04-22 17:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2024-04-22 09:00 | 2024-05-05 16:00 | N | Y |  | Line |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 636L (420s Broadmoor - 746s Sherwood Park), 746s T1 (746s Sherwood Park), 746s 636 (746s Sherwood Park), 746s 3 (746s Sherwood Park), 420s 636 (420s Broadmoor) | 2024-04-22 09:00 | 2024-04-23 16:59 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 163s 1352 (163s Amoco Empress) | 2024-04-22 10:00 | 2024-04-23 11:29 | N | Y |  | Circuit Breaker
ATCO | 869s 702T (869s Seal Lake), 869s 702 (869s Seal Lake) | 2024-04-22 10:00 | 2024-05-10 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 780s 704 (780s Lubicon) | 2024-04-22 10:00 | 2024-04-25 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 310p 352 (310p Sundance) | 2024-04-22 12:30 | 2024-04-22 14:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 727L (65s High River - 727AL tap), 65s 727N (65s High River) | 2024-04-22 13:00 | 2024-04-24 18:00 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 522s T1 (522s Cooking Lake), 522s 1252 (522s Cooking Lake) | 2024-04-22 13:30 | 2024-04-25 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 58s T1 (58s Edson) | 2024-04-22 13:30 | 2024-05-02 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 708L (71s Lamoureux - 708AL tap) | 2024-04-22 20:25 | 2024-04-25 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 330p 500kV Bus 2 (330p Genesee), 330p 12TC2 (330p Genesee), 330p 1203A (330p Genesee), 330p 1211 (330p Genesee), 330p 1215 (330p Genesee), 330p 1203 (330p Genesee), 330p 1206 (330p Genesee), 330p 1209 (330p Genesee) | 2024-04-23 07:00 | 2024-04-27 17:00 | N | Y |  | Bus, Transformer, Switch, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | EP 803s L2402 (EP 803s Lambton) | 2024-04-23 07:00 | 2024-04-23 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.84L (SS-3 - SS-13), 13B138-3.84 (SS-13), 3B138-3.84 (SS-3) | 2024-04-23 08:00 | 2024-04-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Syncrude Plant 30-2 72kV A Bus (UE-1 Syncrude Plant 30-2), Syncrude Plant 30-2 30-2PTR72-A1 (UE-1 Syncrude Plant 30-2), Syncrude Plant 30-2 30-2PTR72-A2 (UE-1 Syncrude Plant 30-2), UE-1 7201 (UE-1 Syncrude Plant 30-2), UE-1 7202 (UE-1 Syncrude Plant 30-2), UE-1 7203 (UE-1 Syncrude Plant 30-2), UE-1 7204 (UE-1 Syncrude Plant 30-2), UE-1 1509 (UE-1 Syncrude Plant 30-2), UE-1 72-11 (UE-1 Syncrude Plant 30-2), UE-1 72-01 (UE-1 Syncrude Plant 30-2), UE-1 72-02 (UE-1 Syncrude Plant 30-2), UE-1 72-03 (UE-1 Syncrude Plant 30-2), UE-1 72-04 (UE-1 Syncrude Plant 30-2), UE-1 72-14 (UE-1 Syncrude Plant 30-2), UE-1 72-15 (UE-1 Syncrude Plant 30-2), UE-1 72-09 (UE-1 Syncrude Plant 30-2), 1016 (Syncrude Mildred Lake) | 2024-04-23 08:00 | 2024-05-02 16:00 | N | N |  | Bus, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 41.2TR (SS-41) | 2024-04-23 08:00 | 2024-12-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 15s 463 (15s Fort Macleod) | 2024-04-23 08:30 | 2024-04-23 13:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 89s 1852 (89s Ellerslie) | 2024-04-23 08:30 | 2024-04-23 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ATCO | 755s 904 (755s Cordel) | 2024-04-23 11:00 | 2024-05-02 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 763L (28s West Brooks - 763AL tap), 28s 763X (28s West Brooks) | 2024-04-23 11:30 | 2024-04-23 14:00 | N | Y |  | Line, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 163s 1352 (163s Amoco Empress) | 2024-04-23 11:30 | 2024-04-24 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1037L (138s Windy Flats - 266s SC1), 1037L (237s Foothills - 266s SC1), 266s 252 (266s SC1) | 2024-04-23 12:00 | 2024-04-24 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2024-04-23 15:44 | 2024-05-06 16:20 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 746s T1 (746s Sherwood Park) | 2024-04-23 17:00 | 2024-04-27 07:59 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | EP 803s L2403 (EP 803s Lambton) | 2024-04-24 07:00 | 2024-04-24 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 60s50 (SS-21), 44s 50X (44s Bearspaw Plant) | 2024-04-24 07:30 | 2024-04-25 16:30 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 993s T2 (993s Abee) | 2024-04-24 07:30 | 2024-04-25 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 763L (158s Vauxhall - 763AL tap) | 2024-04-24 07:30 | 2024-04-24 17:30 | N | Y |  | Line |  |  | Pre-Condition
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 422s 700 (422s Westwood), 746s 700N (746s Sherwood Park) | 2024-04-24 08:00 | 2024-04-26 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34) | 2024-04-24 08:00 | 2024-04-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 89s 1752 (89s Ellerslie) | 2024-04-24 08:30 | 2024-04-24 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-04-24 23:00 | 2024-04-25 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-04-25 03:00 | 2024-04-25 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 522s 138kV Bus 1 (522s Cooking Lake), 874L (45s Bretona - 522s Cooking Lake), 522s T1 (522s Cooking Lake), 522s 874 (522s Cooking Lake), 522s 1252 (522s Cooking Lake), 45s 874 (45s Bretona) | 2024-04-25 07:15 | 2024-04-25 17:45 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 759L (87s Gaetz - 276s Prentiss), 276s 759W (276s Prentiss) | 2024-04-25 08:00 | 2024-04-25 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 162L (229s Glenwood - 415s Drywood), 415s 146E (415s Drywood) | 2024-04-25 08:00 | 2024-04-25 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 186s C1 (186s Dry Creek) | 2024-04-25 08:30 | 2024-04-25 13:30 | N | N |  | Shunts |  |  | For Information Only
ATCO | 951s 903 (951s Thickwood Hills) | 2024-04-25 10:00 | 2024-04-25 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 746s 700N (746s Sherwood Park), 700L (746s Sherwood Park - 746L tap) | 2024-04-25 12:00 | 2024-04-26 17:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 803s L2405 (EP 803s Lambton) | 2024-04-26 07:00 | 2024-04-26 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T4 (805s Jasper), EP 805s J2405 (EP 805s Jasper), EP 805s J2406 (EP 805s Jasper) | 2024-04-26 07:00 | 2024-05-10 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 890L (58s Edson - 207s Pinedale), 58s 890 (58s Edson), 207s 890 (207s Pinedale) | 2024-04-26 07:00 | 2024-04-26 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | Syncrude Plant 30-2 30-2PTR72-3 (UE-1 Syncrude Plant 30-2), UE-1 1509 (UE-1 Syncrude Plant 30-2), UE-1 72-09 (UE-1 Syncrude Plant 30-2) | 2024-04-26 08:00 | 2024-05-10 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
Syncrude | UE-1 1502 (UE-1 Syncrude Plant 30-2), UE-1 1521 (UE-1 Syncrude Plant 30-2), UE-1 1522 (UE-1 Syncrude Plant 30-2) | 2024-04-26 08:00 | 2024-05-12 16:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
SUNCOR | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-1 29EDD1s1152 (29EDD-1 Millennium), 29EDD-2 29PT-2 (29EDD-2 Tar Island) | 2024-04-26 08:00 | 2024-05-09 16:44 | N | N |  | Line, Circuit Breaker, Transformer | Suncor Dispatch Center (SDC) called the AESO SC today (April 25) at 12:31 for this delay. Reason for isolation delay is due to 29PL6-5 restoration and PT-84 transformer soaking. | Back early. | For Information Only
ENMAX | 13B138-3.84 (SS-13), 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3) | 2024-04-26 08:00 | 2024-04-26 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL9-5 (29EDD-1 Millennium - 29EDD-34), 29EDD-34 29-952-122 (29EDD-34), 29EDD-34 29-952-121 (29EDD-34), 29EDD-34 29PS-62 (29EDD-34), 29EDD-1 29PS-71 (29EDD-1 Millennium), 29EDD-1 952-103 (29EDD-1 Millennium), 29EDD-1 952-102 (29EDD-1 Millennium) | 2024-04-26 08:00 | 2024-05-06 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33MD138-33.1TR (SS-33), 33B138-33.83 (SS-33) | 2024-04-26 08:00 | 2024-04-26 12:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33MD138-33.2TR (SS-33), 33B138-33.84 (SS-33) | 2024-04-26 12:00 | 2024-04-26 16:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 746s 138kV East Bus (746s Sherwood Park), 636L (420s Broadmoor - 746s Sherwood Park), 746s T1 (746s Sherwood Park), 420s 636 (420s Broadmoor), 746s 3 (746s Sherwood Park) | 2024-04-27 08:00 | 2024-04-27 12:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2024-04-28 22:00 | 2024-05-23 22:00 | N | Y |  | Line | G3 & G4 will be OOS for annual maintenance, with LS2 OOS for Control Project. |  | 500 kV
ENMAX | 14.4TR (SS-14) | 2024-04-29 07:00 | 2024-05-02 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee), 330p 1214 (330p Genesee), 330p 1210 (330p Genesee) | 2024-04-29 07:00 | 2024-05-03 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | AML 511s FB Bus 1 (AML 511s Crossings), AML 511s ACF11 (AML 511s Crossings), AML 511s ACF12 (AML 511s Crossings), AML 511s ACF13 (AML 511s Crossings), AML 511s T30 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings), AML 511s 5352 (AML 511s Crossings), AML 511s 5252 (AML 511s Crossings), AML 511s 82 (AML 511s Crossings), AML 511s 81 (AML 511s Crossings) | 2024-04-29 07:30 | 2024-05-03 16:30 | N | Y |  | Bus, Shunts, Transformer, Circuit Breaker, Switch |  |  | 240 kV, For Information Only, Pre-Condition
ENMAX | 1.83L (SS-1 - SS-8), 8B138-3A0 (SS-8), 8B138-4A0 (SS-8), 3A1 (SS-8), 3A10 (SS-8), 4A1 (SS-8) | 2024-04-29 08:00 | 2024-05-09 11:26 | N | N |  | Line, Circuit Breaker, Switch |  | Back in service 1 day early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 1.84L (SS-1 - SS-5), 5.7TR (SS-5), 5.5TR (SS-5), 5B138-5BT7 (SS-5), 5B138-1.84 (SS-5), 5B138-2.82 (SS-5), 5MD138-5.5TR (SS-5), 5MD138-5.7TR (SS-5), 2MD138-2.82 (SS-2) | 2024-04-29 08:00 | 2024-05-18 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2024-04-29 08:00 | 2024-05-05 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 122s T3 (122s Alberta Newsprint) | 2024-04-29 09:00 | 2024-05-02 15:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 58s C1 (58s Edson) | 2024-04-29 09:30 | 2024-04-29 16:30 | N | N |  | Shunts |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2024-04-29 10:00 | 2024-05-06 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 951s SVC (951s Thickwood), 951s 919 (951s Thickwood Hills) | 2024-04-29 10:00 | 2024-05-03 16:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 297s T1 (297s Rimbey) | 2024-04-29 13:00 | 2024-05-02 17:30 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 55s T1 (55s Olds) | 2024-04-29 14:00 | 2024-05-09 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 865L (38s East Edmonton - 216s Knightsbridge) | 2024-04-30 08:00 | 2024-04-30 15:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | WPT1 Wapiti Generator Test | 2024-04-30 08:00 | 2024-05-02 18:00 | N | N |  | Unit
ALTALINK | 853L (504s Queenstown - 853AL tap) | 2024-04-30 08:00 | 2024-05-02 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2024-04-30 08:00 | 2024-05-11 16:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ATCO | 863s Paintearth, 863s 901 (863s Paintearth), 863s 902 (863s Paintearth), 863s 901A (863s Paintearth), 863s 9L27D2 (863s Paintearth), 863s 901TD (863s Paintearth), 863s 902A (863s Paintearth), 863s 902TD (863s Paintearth), 863s 9L948D4 (863s Paintearth) | 2024-04-30 08:30 | 2024-04-30 17:00 | N | Y |  | Station, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
FCSF | FCS1 Fox Coulee Solar Generator Test | 2024-04-30 08:30 | 2024-04-30 17:00 | N | Y |  | Unit
ALTALINK | 320p 2952 (320p Keephills) | 2024-04-30 08:30 | 2024-04-30 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ATCO | 863s 901T (863s Paintearth) | 2024-04-30 15:01 | 2024-06-10 17:00 | N | Y |  | Transformer | 863S Paintearth Protection Upgrade Generator required for SST to complete this work: Demo old wiring, from 504, demo 504/5L470 line protection panel, install new 5L470 protection, cut over 500PT2, and CT9 to new protection. Commission 504/5L570 line protection, 500PT2, and CT9. Remove generator from SST then Reduce GOI to complete the following: Demo old wiring, and old Transformer protection panel, install and terminate new wiring, and new Transformer protection panel. Commission new wiring/Transformer protection, and new Transformer protection panel. Once GOI is released 902TD will need to be commissioned. |  | 240 kV, Pre-Condition
ALTALINK, RESC | 1012L (326s Murray lake - 516s Forty Mile), 516s Forty Mile | 2024-05-01 | 2024-07-08 | N | Y |  | Line, Station
ALTALINK | 326s 240kV Bus 1 (326s Murray lake), 961L (326s Murray lake - 516s Forty Mile), 326s 152 (326s Murray Lake), 326s 352 (326s Murray Lake), 326s 1012 (326s Murray Lake) | 2024-05-01 07:00 | 2024-06-04 17:30 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 408L (51s Wainwright - 252s Jarrow), 51s 408N (51s Wainwright), 252s 408 (252s Jarrow) | 2024-05-01 07:00 | 2024-05-02 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-16L (MHS-2 North Industrial - MHS-16 Cousins), MHS2 MH69-T21 (MHS-2 North Industrial), MHS2 MH138-T23 (MHS-2 North Industrial), MHS-2 MH138-218 (MHS-2 North Industrial), MHS-16 16-69KV-BKR001 (MHS-16 Cousins), MHS-10 MH138-1002 (MHS-10 Box Springs), MHS-2 MH69-206 (MHS-2 North Industrial), MHS-2 MH69-224 (MHS-2 North Industrial), MHS-2 MH69-217 (MHS-2 North Industrial), CS21 (MHS-2 North Industrial) | 2024-05-01 07:00 | 2024-05-03 09:30 | N | N |  | Line, Transformer, Circuit Breaker, Shunts |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2024-05-01 08:00 | 2024-05-01 12:00 | N | N |  | Transformer
ALTALINK | 271s T1 (271s Shell Jumping Pound) | 2024-05-01 08:00 | 2024-05-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 753L (65s High River - 253s Blackie), 65s 753E (65s High River), 253s 753W (253s Blackie) | 2024-05-01 08:00 | 2024-05-07 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 24.1TR (SS-24) | 2024-05-01 08:00 | 2024-05-02 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 283s C1 (283s Violet Grove) | 2024-05-01 08:30 | 2024-05-01 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 320p 3052 (320p Keephills) | 2024-05-01 08:30 | 2024-05-01 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 5L52 (BPA Custer - BCH Ingledow) | 2024-05-01 09:00 | 2024-05-02 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 6L03 (757s Battle River - 6L17 tap), 6L17 (759s Castor - 6L03 tap), 6L03 (775s Sullivan Lake - 6L17 tap), 757s 603 (757s Battle River) | 2024-05-01 09:30 | 2024-05-01 15:30 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 489s T2 (489s Petro Canada Brazeau River) | 2024-05-01 12:30 | 2024-05-01 16:30 | N | N |  | Transformer
ALTALINK | 266s 1037L FSC1 (266s SC1), 266s 1038L FSC2 (266s SC1) | 2024-05-01 18:40 | 2024-06-08 18:00 | N | Y |  | Shunts |  | Outage extended again. Done a few days ago. | 240 kV, For Information Only
ENMAX, ALTALINK | 20.82L (SS-20 - SS-21), 21.80L (42s Sarcee - SS-21), 21.1TR (SS-21), 21.4TR (SS-21), 21B138-20.82 (SS-21), 21B138-21.80 (SS-21), 21B69-21.4TR (SS-21), SW64 (SS-21), 21MD138-21.1TR (SS-21), 21MD138-21.4TR (SS-21) | 2024-05-02 08:00 | 2024-05-02 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2024-05-02 08:30 | 2024-05-02 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 330p 430LD1 (330p Genesee), 330p 8L10D (330p Genesee) | 2024-05-03 07:00 | 2024-05-03 17:00 | N | N |  | Switch |  |  | Pre-Condition
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28), SW83 (SS-28), 28MD138-28.1TR (SS-28) | 2024-05-03 08:00 | 2024-05-03 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 821L (158s Vauxhall - 421s Hays) | 2024-05-03 08:00 | 2024-05-03 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28.2TR (SS-28), 28B138-28.80 (SS-28), SW82 (SS-28), 28MD138-28.2TR (SS-28) | 2024-05-03 12:00 | 2024-05-03 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 730L (285s East Camrose - 732L tap), 285s 730N (285s East Camrose) | 2024-05-04 07:00 | 2024-05-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37) | 2024-05-04 08:00 | 2024-05-05 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 271s T2 (271s Shell Jumping Pound) | 2024-05-05 08:00 | 2024-05-08 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 895s T2 (895s Suffield) | 2024-05-06 04:48 | 2024-05-13 07:59 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T3 (Meadowlark), M724 (Meadowlark), M723 (Meadowlark) | 2024-05-06 07:00 | 2024-05-09 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T1 (EP 511s Victoria) | 2024-05-06 07:00 | 2025-02-21 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s C2402 (987s Clover Bar) | 2024-05-06 07:00 | 2024-05-07 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 14.1TR (SS-14) | 2024-05-06 07:00 | 2024-05-09 18:00 | N | N |  | Transformer |  |  | For Information Only
CNRL | 1034s T2 (1034s Margie) | 2024-05-06 07:00 | 2024-05-08 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 330p 1208 (330p Genesee) | 2024-05-06 07:00 | 2024-05-07 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 10.2TR (SS-10) | 2024-05-06 08:00 | 2024-05-10 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2024-05-06 08:00 | 2024-05-07 16:00 | N | Y |  | Line |  |  | 500 kV
ALTALINK, TRANSALTA | 33s T2 (33s Spray), 33s 2 (33s Spray) | 2024-05-06 08:00 | 2024-05-10 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 13.1TR (SS-13) | 2024-05-06 08:00 | 2024-05-10 16:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR, FMGW | 29EDD-71 29PT-232 (29EDD-71), 29PT-232 29PT-240, 29EDD-71 29PS-242 (29EDD-71 Edd71Sub), 29EDD-71 752-4623 (29EDD-71), 29EDD-71 752-4622 (29EDD-71) | 2024-05-06 08:00 | 2024-05-15 15:00 | N | N |  | Transformer, Terminal Equipment, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 484s T2 (484s Millar Western) | 2024-05-06 08:00 | 2024-05-10 06:59 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.1TR (SS-15) | 2024-05-06 08:00 | 2024-05-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 37.81L (SS-37 - SS-38), 37B138-37.81 (SS-37), 38B138-37.81 (SS-38) | 2024-05-06 08:00 | 2024-05-11 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale), 763s 603 (763s Hanna) | 2024-05-06 09:00 | 2024-05-07 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s 916 (2075s Newell), 2075s 917 (2075s Newell) | 2024-05-06 09:00 | 2024-05-19 17:30 | N | Y |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 2029S BUILDING VALVE HALL, 2029s 1205 (2029s Heathfield), 2029s 1206 (2029s Heathfield), 12L70 (12s Heartland - 2029s Heathfield), 12L85 (12s Heartland - 2029s Heathfield) | 2024-05-06 09:00 | 2024-05-19 17:30 | N | Y |  | Terminal Equipment, Circuit Breaker, Line |  |  | 500 kV, Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2024-05-06 09:00 | 2024-05-17 19:15 | N | Y |  | Line | Note For OC: Check the availability of the substation ( 2075s Newell) for the use of SVS. Check if the SVS can be operated under reactive control mode. |  | 500 kV, Overload, Pre-Condition, Restricts Generation
ATCO | 769s 601 (769s Stettler), 6L02 (769s Stettler - 873s Marion Lake) | 2024-05-06 09:00 | 2024-05-08 15:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15B69-15.62 (SS-15), 16B69-15.62 (SS-16), 15.62L (SS-15 - SS-16) | 2024-05-06 09:00 | 2024-05-06 09:59 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 729L (285s East Camrose - 542s Ervick), 285s 729W (285s East Camrose) | 2024-05-06 09:00 | 2024-05-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 845s 707 (845s Big Mountain) | 2024-05-06 09:30 | 2024-05-09 09:10 | N | N |  | Circuit Breaker |  | Completed early | Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34) | 2024-05-06 10:00 | 2024-05-06 10:59 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21) | 2024-05-06 11:00 | 2024-05-06 11:59 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 13s T2 (13s Deerland), 13s 138kV Bus 2 (13s Deerland), 13s 101 (13s Deerland), 13s 452 (13s Deerland), 13s 852 (13s Deerland) | 2024-05-06 12:00 | 2024-05-09 18:00 | N | Y |  | Transformer, Bus, Switch, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34), 21B69-21.61 (SS-21), 34B69-21.61 (SS-34) | 2024-05-06 12:00 | 2024-05-06 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 367s T1 (367s Harry Smith) | 2024-05-06 14:00 | 2024-05-09 17:00 | N | Y |  | Transformer |  |  | 240 kV, Overload, Pre-Condition
ALTALINK | 574s T2 (574s Nilrem) | 2024-05-06 14:30 | 2024-05-09 17:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 653s 138-653.3TR (653s Summit) | 2024-05-07 07:00 | 2024-05-08 17:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
CMH | MHS-9 MH138-902 (MHS-9 South Saskatchewan), MH-15L (MHS-7 Brier Park - MHS-9 South Saskatchewan), MHS-7 MH138-702 (MHS-7 Brier Park) | 2024-05-07 07:00 | 2024-05-07 11:30 | N | N |  | Circuit Breaker, Line |  |  | Overload, Pre-Condition
ATCO, CNRL | 838s 75-TR-1801 (838s Horizon Mining) | 2024-05-07 07:00 | 2024-05-14 11:39 | N | Y |  | Transformer |  | Back early | For Information Only, Pre-Condition
CNRL | 1034s T1 (1034s Margie), 789BL (1034s Margie - 789L tap) | 2024-05-07 07:00 | 2024-05-08 18:00 | N | N |  | Transformer, Line |  |  | For Information Only
ALTALINK | 221s T1 (221s Sunken Lake), 221s 31 (221s Sunken Lake) | 2024-05-07 07:30 | 2024-05-08 09:00 | N | N |  | Transformer, Switch |  | ended early | For Information Only
ALTALINK, BCH | 1L274 (BCH Natal - BCH Line Creek tap) | 2024-05-07 08:00 | 2024-05-07 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
NWE | Great Falls Switchyard (NorthWestern Energy) - Highwood, Great Falls Switchyard (NorthWestern Energy) - Landers Fork | 2024-05-08 03:30 | 2024-05-08 20:55 | N | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
EPCOR | 330p 1202 (330p Genesee) | 2024-05-08 07:00 | 2024-05-09 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 15.2TR (SS-15) | 2024-05-08 08:00 | 2024-05-09 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 437s T1 (437s Baymag), 437s T2 (437s Baymag) | 2024-05-08 08:00 | 2024-05-08 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 727L (678s Okotoks - 727AL tap) | 2024-05-08 08:00 | 2024-05-10 13:30 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 6L15 (763s Hanna - 775s Sullivan Lake), 763s 602 (763s Hanna) | 2024-05-08 09:00 | 2024-05-09 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
BCH | 1L274 (BCH Elkford tap - BCH Line Creek tap) | 2024-05-08 09:00 | 2024-05-10 19:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
CNRL | 1034s T1 (1034s Margie) | 2024-05-08 18:01 | 2024-05-09 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 763L (28s West Brooks - 763AL tap), 28s 31 (28s West Brooks), 28s 47 (28s West Brooks), 28s 763X (28s West Brooks) | 2024-05-09 07:00 | 2024-05-10 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L07 (951s Thickwood Hills - 2011s Dawes), 2011s 9L07D1 (2011s Dawes), 951s 9L07D2 (951s Thickwood Hills) | 2024-05-09 17:00 | 2024-05-16 11:36 | N | Y |  | Line, Switch |  | Line placed back in service. | 240 kV
ENMAX, ALTALINK | 653s 138-653.1TR (653s Summit), 653.1TR (653s Summit) | 2024-05-10 07:00 | 2024-05-12 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | Restricts Generation
ALTALINK | 825L (77s Sagitawah - 484s Millar Western), 484s 138kV Bus (484s Millar Western), 484s 825 (484s Millar Western), 484s T1 (484s Millar Western), 484s T2 (484s Millar Western), 484s T3 (484s Millar Western), 484s 2 (484s Millar Western), 484s 3 (484s Millar Western), 484s 4 (484s Millar Western), 484s 10 (484s Millar Western) | 2024-05-10 07:00 | 2024-05-10 12:00 | N | Y |  | Line, Bus, Circuit Breaker, Transformer, Switch |  |  | Restricts Generation
ENMAX, ALTALINK | 653s 138-653.2TR (653s Summit), 653.2TR (653s Summit) | 2024-05-10 07:00 | 2024-05-12 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | Restricts Generation
ALTALINK | 763L (158s Vauxhall - 763AL tap), 158s 763N (158s Vauxhall) | 2024-05-11 07:00 | 2024-05-12 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L10 (754s Ksituan River - 7LA10 tap), 7L10 tap, 7L10 (730s Rycroft - 7LA10 tap), 7LA10 (2033s Mowat - 7L10 tap), 730s 702 (730s Rycroft) | 2024-05-11 08:00 | 2024-05-11 17:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | Restricts Generation
Syncrude | UE-1 (D05 - UE-1 Syncrude Plant 30-2), UE-1 7206 (UE-1 Syncrude Plant 30-2), UE-1 72-04 (UE-1 Syncrude Plant 30-2), UE-1 72-09 (UE-1 Syncrude Plant 30-2), UE-1 72-07 (UE-1 Syncrude Plant 30-2), UE-1 72-08 (UE-1 Syncrude Plant 30-2), UE-1 72-16 (UE-1 Syncrude Plant 30-2), UE-1 7204 (UE-1 Syncrude Plant 30-2), UE-1 7208 (UE-1 Syncrude Plant 30-2), UE-1 7207 (UE-1 Syncrude Plant 30-2) | 2024-05-12 08:00 | 2024-05-19 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 24.2TR (SS-24) | 2024-05-12 08:00 | 2024-05-12 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T1 (Woodcroft), 72JW19 (EP 805s Jasper - Woodcroft), W722 (Woodcroft), W721 (Woodcroft), EP 805s J724 (EP 805s Jasper), EP 805s JDS28 (EP 805s Jasper) | 2024-05-13 07:00 | 2024-05-17 12:00 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  | Completed early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 330p 1205 (330p Genesee) | 2024-05-13 07:00 | 2024-05-14 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Restricts Generation
ENMAX | 14.2TR (SS-14) | 2024-05-13 07:00 | 2024-05-16 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72LS24 (EP 803s Lambton - Strathcona), S724 (Strathcona), SDS10 (Strathcona) | 2024-05-13 07:00 | 2024-05-17 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
CMH | CS21 (MHS-2 North Industrial), MHS-2 East Bus (MHS-2 North Industrial), MHS-2 2S2-M (MHS-2 North Industrial), MHS-2 2S2-TB (MHS-2 North Industrial), MHS2 MH69-T22 (MHS-2 North Industrial), MH-50L (MHS-2 North Industrial - MHS-5 NE Crescent Heights), MHS-2 MH69-204 (MHS-2 North Industrial), MHS-2 MH69-207 (MHS-2 North Industrial), MHS-2 MH69-210 (MHS-2 North Industrial), MHS-2 MH69-214 (MHS-2 North Industrial), MHS-2 MH69-215 (MHS-2 North Industrial), MHS-2 MH69-221 (MHS-2 North Industrial), MHS-2 MH69-208 (MHS-2 North Industrial) | 2024-05-13 07:00 | 2024-05-17 15:00 | N | N |  | Shunts, Bus, Circuit Breaker, Transformer, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 557s T2 (557s Castle Downs), 557s CD2403 (557s Castle Downs), 557s CD2404 (557s Castle Downs) | 2024-05-13 07:00 | 2024-05-17 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 805s T3 (805s Jasper) | 2024-05-13 07:00 | 2024-06-14 15:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16), 27B69-16.61 (SS-27) | 2024-05-13 08:00 | 2024-05-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 13.2TR (SS-13) | 2024-05-13 08:00 | 2024-05-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 34.2TR (SS-34) | 2024-05-13 08:00 | 2024-05-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 895s T2 (895s Suffield) | 2024-05-13 08:00 | 2024-05-30 15:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 24.1TR (SS-24) | 2024-05-13 08:00 | 2024-05-22 16:00 | N | N |  | Transformer |  | Done early | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2024-05-13 08:00 | 2024-05-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L56 (763s Hanna - 802s Michichi Creek), 802s 701T (802s Michichi Creek), 802s 701 (802s Michichi Creek), 802s 606 (802s Michichi Creek) | 2024-05-13 08:30 | 2024-05-16 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition
ATCO | 7L155 (883s Gregoire - 2009s Willow Lake), 883s 701T (883s Gregoire), 883s Gregoire | 2024-05-13 09:00 | 2024-05-31 17:30 | N | N |  | Line, Transformer, Station |  |  | For Information Only
ALTALINK | 671L (39s Bickerdike - 58s Edson), 58s 671 (58s Edson) | 2024-05-13 12:00 | 2024-05-14 12:45 | N | N |  | Line, Circuit Breaker |  | back early | Overload, Pre-Condition, Restricts Generation
ALTALINK | 199s T2 (199s East Airdrie) | 2024-05-13 12:00 | 2024-05-16 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 254s T2 (254s Coaldale) | 2024-05-13 12:00 | 2024-05-16 17:30 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 542s T1 (542s Ervick) | 2024-05-13 13:30 | 2024-05-16 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 602s T2 (602s Cold Creek), 602s 16 (602s Cold Creek) | 2024-05-13 16:30 | 2024-05-16 17:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood), 422s 694 (422s Westwood), 54s 694 (54s Fort Saskatchewan) | 2024-05-14 07:00 | 2024-05-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162B240-RB136 (SS-162) | 2024-05-14 08:00 | 2024-05-15 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, PANC | 391s 23 (391s Balzac), 391s 25 (391s Balzac), PCES02L (391s Balzac - Balzac Power Station) | 2024-05-14 11:00 | 2024-05-15 17:30 | N | Y |  | Switch, Circuit Breaker, Line |  |  | Restricts Generation
CNRL, ATCO | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading), 838s 75-TR-2701 (838s Horizon Mining), 838s 75-TR-2801 (838s Horizon Mining), 842s 75-1903 (842s Horizon Upgrading), 842s 75-TR-4701 (842s Horizon Upgrading), 842s 75-TR-7701 (842s Horizon Upgrading), 838s 75-BC-1911 (838s Horizon Mining), 838s 75-BC-1916 (838s Horizon Mining), 838s 75-BC-1917 (838s Horizon Mining), 838s 75-BC-1918 (838s Horizon Mining), 838s 75-SD-1911B (838s Horizon Mining), 838s 75-SD-1917A (838s Horizon Mining), 838s 75-SD-1917B (838s Horizon Mining), 838s 75-SD-1918A (838s Horizon Mining), 838s 75-SD-1918B (838s Horizon Mining), 838s 75-SD-1916A (838s Horizon Mining), 838s 75-BC-2801 (838s Horizon Mining), 842s 75-1902 (842s Horizon Upgrading), 842s 75-1904 (842s Horizon Upgrading), 842s 75-1905 (842s Horizon Upgrading), 842s 75-1902A (842s Horizon Upgrading), 842s 75-1903A (842s Horizon Upgrading), 842s 75-1903B (842s Horizon Upgrading), 842s 75-1904A (842s Horizon Upgrading), 842s 75-1904B (842s Horizon Upgrading), 842s 75-1905B (842s Horizon Upgrading), 842s 75-903A (842s Horizon Upgrading) | 2024-05-15 07:30 | 2024-05-29 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
AGPL | EMP1 Empress Solar Park | 2024-05-15 08:00 | 2024-05-15 16:23 | N | N |  | Unit
SUNCOR | 29PL9-24 (29EDD-94 Voyageur - 29EDD-60 Inglis Island), 29PL9-25 (29EDD-94 Voyageur - 29EDD-61 Stony Island), 29EDD-60 29PT-702 (29EDD-60 Inglis Island), 29EDD-61 29PT-653 (29EDD-61 Stony Island), 29EDD-94 29PS-640 (29EDD-94 Voyageur), 29EDD-94 29PS-641 (29EDD-94 Voyageur) | 2024-05-15 08:00 | 2024-05-20 17:00 | N | Y |  | Line, Transformer, Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 425L (194s South Red Deer - 217s North Red Deer), 194s 425 (194s South Red deer) | 2024-05-15 08:00 | 2024-05-16 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 5.6TR (SS-5) | 2024-05-15 08:00 | 2024-05-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L81 (791s Rainbow Lake - BCH Harvest Energy FNC Tap) | 2024-05-15 08:00 | 2024-05-15 22:00 | N | Y |  | Line |  |  | Affects Cranking Path
ALTALINK | 847L (602s Cold Creek - 847AL tap), 602s 847 (602s Cold Creek) | 2024-05-15 09:00 | 2024-05-15 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
WFML | WWD1 Weldwood 20MW Steam Turb. | 2024-05-15 09:00 | 2024-05-15 16:00 | N | N |  | Unit
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2024-05-15 13:22 | 2024-05-17 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 816s P2401 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS13 (816s Petrolia) | 2024-05-16 07:00 | 2024-05-16 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
BCH | 5L75 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2024-05-16 08:00 | 2024-05-17 16:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC
ATCO | 7L228 (845s Big Mountain - 7L20 tap) | 2024-05-16 09:00 | 2024-05-16 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 10.1TR (SS-10) | 2024-05-16 09:50 | 2024-05-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 157s T2 (157s Lac La Biche) | 2024-05-16 10:00 | 2024-05-16 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2024-05-17 08:00 | 2024-05-18 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 16.61L (SS-16 - SS-27), 15.62L (SS-15 - SS-16), 16.60L (SS-16 - SS-34), 16.1TR (SS-16), 16.2TR (SS-16) | 2024-05-18 08:00 | 2024-05-18 16:00 | N | N |  | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 11.82L (SS-11 - SS-14), 14B138-11.82 (SS-14) | 2024-05-19 08:00 | 2024-05-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, BCH | 887L (48s Pocaterra - 978s BCH Britt Creek), 1L274 (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2024-05-19 08:00 | 2024-05-19 15:00 | Y | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power) | 2024-05-20 07:00 | 2024-05-25 08:56 | N | Y |  | Line |  |  | For Information Only, Restricts Generation
ENMAX | 26.83L (SS-26 - SS-65), 26B138-26.83 (SS-26) | 2024-05-20 07:00 | 2024-05-23 16:22 | N | N |  | Line, Circuit Breaker |  | back early | Creates Radial Feeds, Firm Load Loss
ENMAX | 13.3TR (SS-13) | 2024-05-20 08:00 | 2024-05-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2024-05-20 08:00 | 2024-05-26 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2024-05-20 08:00 | 2024-06-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 759L (87s Gaetz - 276s Prentiss), 276s T1 (276s Union Carbide Prentiss), 276s 138kV Center Bus (276s Union Carbide Prentiss), 276s 16 (276s Prentiss), 276s 25 (276s Prentiss), 276s 759W (276s Prentiss), 87s 759E (87s Gaetz), 276s 13 (276s Prentiss) | 2024-05-21 07:00 | 2024-05-26 17:00 | N | N |  | Line, Transformer, Bus, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 310P 512N (310p Sundance) | 2024-05-21 07:00 | 2024-05-21 18:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
EPCOR | 557s T1 (557s Castle Downs), 557s CD2401 (557s Castle Downs), 557s CD2406 (557s Castle Downs), 557s CDAB1 (557s Castle Downs) | 2024-05-21 07:00 | 2024-05-26 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 816s P2403 (816s Petrolia) | 2024-05-21 07:00 | 2024-06-20 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T3 (Woodcroft), W724 (Woodcroft), W722 (Woodcroft), WAB3 (Woodcroft), WDS6 (Woodcroft) | 2024-05-21 07:00 | 2024-05-26 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 701L (223s Strome - 395s North Holden), 395s 701X (395s North Holden) | 2024-05-21 07:00 | 2024-05-30 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 28s R1 (28s West Brooks) | 2024-05-21 08:30 | 2024-05-23 16:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2024-05-21 09:00 | 2024-05-27 16:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 522L (320p Keephills - 133L tap), 320p T5 (320p Keephills) | 2024-05-21 13:00 | 2024-05-21 17:30 | N | N |  | Line, Transformer |  |  | For Information Only
ALTALINK | 12s T1 (12s Heartland), 12s 1452 (12s Heartland), 12s 1752 (12s Heartland), 12s 3689 (12s Heartland) | 2024-05-21 13:30 | 2024-06-13 17:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 732s 701 (732s Mitsue) | 2024-05-21 13:40 | 2024-05-24 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ALTALINK | 310P 234N (310p Sundance), 234L (310p Sundance - 505L tap) | 2024-05-22 07:00 | 2024-05-22 18:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 409s 138kV Bus B1 (409s Shell Scotford), 409s T2 (409s Shell Scotford), 856L (409s Shell Scotford - 410s Josephburg), ALC01L (408s Air Liquide Scotford - 409s Shell Scotford), 409s 20 (409s Shell Scotford), 409s 107 (409s Shell Scotford), 409s 856W (409s Shell Scotford), 409s 9 (409s Shell Scotford) | 2024-05-22 07:00 | 2024-05-27 18:00 | N | Y |  | Bus, Transformer, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ALTALINK | 739L (14s Devon - 155s Blackmud), 14s T1 (14s Devon), 155s 739 (155s Blackmud), 14s 739E (14s Devon), 14s 24 (14s Devon) | 2024-05-22 07:15 | 2024-05-23 16:45 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 3.84L (SS-3 - SS-13), 13B138-3.84 (SS-13) | 2024-05-22 08:00 | 2024-05-22 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 646L (237s Foothills - 678s Okotoks), 678s 646 (678s Okotoks) | 2024-05-22 08:30 | 2024-05-22 12:30 | N | N |  | Line, Circuit Breaker |  |  | Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 288s T1 (288s Wolf Creek) | 2024-05-22 08:30 | 2024-06-03 17:30 | N | Y |  | Transformer |  | Extended due to lack of parts | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 338s 552 (338s Cherhill) | 2024-05-22 08:30 | 2024-05-22 13:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 727L (678s Okotoks - 727AL tap), 678s 727 (678s Okotoks) | 2024-05-22 12:30 | 2024-05-22 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 69s T2 (69s North Barrhead), 69s T5 (69s North Barrhead) | 2024-05-23 07:00 | 2024-05-28 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA | 310P 3352 (310p Sundance), 310P T31 (310P Sundance) | 2024-05-23 07:00 | 2024-05-24 18:00 | N | N |  | Circuit Breaker, Transformer |  | Breaker won't close due to relay lockout indication. Will troubleshoot in tomorrow. | For Information Only
ALTALINK | 732L (299s Kingman - 732AL tap), 299s T1 (299s Kingman), 299s 732N (299s Kingman), 732L-20A (732AL tap) | 2024-05-23 07:30 | 2024-05-23 18:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 7.84L (SS-7 - SS-36), 36B138-7.84 (SS-36) | 2024-05-23 08:00 | 2024-05-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 7.84L (SS-7 - SS-36), 7B138-7.84 (SS-7) | 2024-05-23 08:00 | 2024-05-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 54.81L (SS-54 - SS-65) | 2024-05-23 08:00 | 2024-05-23 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 526L (268s Whitecourt - 520L tap), 268s 69 (268s Whitecourt) | 2024-05-23 08:00 | 2024-05-23 14:30 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 291s 433 (291s Cochrane), 433L (291s Cochrane - AML 793s Horse Creek) | 2024-05-23 08:30 | 2024-05-23 12:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 291s T2 (291s Cochrane) | 2024-05-23 12:00 | 2024-05-23 17:30 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2024-05-24 08:00 | 2024-05-24 17:47 | N | N |  | Line, Circuit Breaker |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s GT1 (987s Clover Bar), 987s CGB1 (987s Clover Bar) | 2024-05-25 07:00 | 2024-05-27 10:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7), 7B138-7.82 (SS-7) | 2024-05-26 08:00 | 2024-05-26 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514L (513s Lundbreck - 514BL tap), 396s 514N (396s Pincher Creek) | 2024-05-26 08:00 | 2024-05-26 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK, DOW | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen), 166s 899N (166s Dow Chemical Fort Saskatchewan) | 2024-05-26 08:00 | 2024-06-10 13:30 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
CHDI | CRE3 Cowley Ridge | 2024-05-26 08:00 | 2024-05-26 18:00 | N | N |  | Unit
ALTALINK | 276s 138kV North Bus (276s Union Carbide Prentiss), 774L (276s Prentiss - 332s Ellis), 276s T2 (276s Union Carbide Prentiss), 276s C1 (276s Union Carbide Prentiss), 276s 16 (276s Prentiss), 276s 774N (276s Prentiss), 276s 8 (276s Prentiss), 276s 3 (276s Prentiss) | 2024-05-26 17:05 | 2024-05-31 18:00 | N | N |  | Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR, ALTALINK | 1059AL (52s East Industrial - 1059L tap), 1059L (38s East Edmonton - 1059AL tap), 1059L (EP 803s Lambton - 1059AL tap), EP 803s L2404 (EP 803s Lambton), EP 803s L2401 (EP 803s Lambton), 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial) | 2024-05-27 07:00 | 2024-06-07 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s C2402 (987s Clover Bar) | 2024-05-27 07:00 | 2024-05-28 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 916L (5s East Calgary - 42s Sarcee), 42s 916E (42s Sarcee) | 2024-05-27 07:00 | 2024-05-28 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 9.3TR (SS-9) | 2024-05-27 08:00 | 2024-05-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7.1TR (SS-7) | 2024-05-27 08:00 | 2024-05-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 36B138-36BT3 (SS-36) | 2024-05-27 08:00 | 2024-05-27 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 162.4TR (SS-162) | 2024-05-27 08:00 | 2024-05-30 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 2L294 (BCH A. A. Lambert - BCH Nelway) | 2024-05-27 09:00 | 2024-05-31 17:00 | N | Y |  | Line |  |  | Pre-Condition
CDVP | VCN1 Vulcan Solar Generator Test | 2024-05-27 09:00 | 2024-08-05 19:00 | N | N |  | Unit
ALTALINK, EPCOR | 1059L (38s East Edmonton - 1059AL tap) | 2024-05-27 09:30 | 2024-06-07 17:00 | N | Y |  | Line |  |  | For Information Only
ATCO | 767s 701 (767s Oyen), 767s Protection & Control (767s Oyen), 7L132 (767s Oyen - 959s Lanfine) | 2024-05-27 10:00 | 2024-05-29 11:30 | N | N |  | Circuit Breaker, Terminal Equipment, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 905s 701 (905s Meikle) | 2024-05-27 10:00 | 2024-05-29 11:59 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO, GREENGATEP | 9L16 (755s Cordel - 972s Tinchebray), 755s 905 (755s Cordel), 755s 904 (755s Cordel), 972s 902 (972s Tinchebray), 972s 903 (972s Tinchebray) | 2024-05-27 10:00 | 2024-06-10 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 890s 701 (890s Melito), 890s 701T (890s Melito) | 2024-05-27 17:00 | 2024-05-28 07:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
REDDEER | 217s T2 (217s North Red Deer) | 2024-05-28 08:00 | 2024-06-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe), 48s 777N (48s Pocaterra) | 2024-05-28 08:00 | 2024-05-29 11:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 39B138-38.83 (SS-39), 38B138-38.83 (SS-38) | 2024-05-28 08:00 | 2024-05-28 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s T7 (62s Brazeau Plant) | 2024-05-28 08:30 | 2024-06-02 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2024-05-28 23:00 | 2024-05-30 07:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12B138-833L (SS-12) | 2024-05-29 06:00 | 2024-05-30 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX, ALTALINK | 833L (SS-2 - SS-12) | 2024-05-29 06:00 | 2024-05-30 18:00 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
ALTALINK | 250p 22 (250p Bighorn Plant) | 2024-05-29 07:00 | 2024-05-30 07:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 23.3TR (SS-23) | 2024-05-29 08:00 | 2024-05-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7.84L (SS-7 - SS-36), 7B138-7.84 (SS-7) | 2024-05-29 08:00 | 2024-05-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 7L230 (69s North Barrhead - 888AL tap), 7L230 (743s Sarah Lake - 888AL tap) | 2024-05-29 09:00 | 2024-05-31 17:00 | N | N |  | Line |  |  | For Information Only
ATCO, ALTALINK | 7L230 (69s North Barrhead - 888AL tap), 888AL (234s Fort Assiniboine - 7L230 tap), 234s 2 (234s Fort Assiniboine), 234s 3 (234s Fort Assiniboine) | 2024-05-29 09:00 | 2024-05-30 17:00 | N | N |  | Line, Switch |  |  | For Information Only, Pre-Condition
CNRL, ATCO | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading), 838s 75-TR-1701 (838s Horizon Mining), 838s 75-TR-1801 (838s Horizon Mining), 842s 75-TR-8701 (842s Horizon Upgrading), 842s 75-TR-5701 (842s Horizon Upgrading), 842s 75-1904 (842s Horizon Upgrading), 838s 75-BC-1913 (838s Horizon Mining), 838s 75-BC-1914 (838s Horizon Mining), 838s 75-BC-1915 (838s Horizon Mining), 838s 75-BC-1916 (838s Horizon Mining), 838s 904 (838s Horizon Mining) | 2024-05-29 10:30 | 2024-06-04 12:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 905s 702 (905s Meikle) | 2024-05-29 12:00 | 2024-05-31 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 3L (245s Seebe - 3AL tap), 245s 3E (245s Seebe) | 2024-05-29 12:30 | 2024-05-30 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 6L09 (767s Oyen - 6L21 tap), 767s 601 (767s Oyen) | 2024-05-29 12:30 | 2024-05-30 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.6TR (SS-1) | 2024-05-29 15:00 | 2024-06-03 15:00 | N | N |  | Transformer |  | Returned to service
EPCOR | 524s T1 (524s Owens Corning) | 2024-05-30 08:00 | 2024-05-30 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7B138-7BT3 (SS-7) | 2024-05-30 08:00 | 2024-05-30 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-65 29-952-4813 (29EDD-65) | 2024-05-30 15:44 | 2024-06-02 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23), 23B138-2.80 (SS-23), 23MD138-23.3TR (SS-23), SW83 (SS-23) | 2024-05-31 08:00 | 2024-05-31 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, PWLP | 973s 52-240 (973s Lanes Lake), 973s 89-T1 (973s Lanes Lake), 973s 89-T2 (973s Lanes Lake) | 2024-05-31 08:00 | 2024-05-31 16:00 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43) | 2024-05-31 08:00 | 2024-05-31 17:30 | N | N |  | Line, Circuit Breaker |  | Done Early | Creates Radial Feeds, Firm Load Loss
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2024-05-31 08:00 | 2024-06-03 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34), 21B69-21.61 (SS-21), 34B69-21.61 (SS-34) | 2024-05-31 08:00 | 2024-05-31 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 23B138-23.80 (SS-23), SW84 (SS-23), 23MD138-23.4TR (SS-23) | 2024-05-31 12:00 | 2024-05-31 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 716s 7L42D2 (716s Lloydminster), 7L42 (716s Lloydminster - 751s Hill) | 2024-05-31 12:00 | 2024-05-31 18:00 | N | N |  | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24) | 2024-06-01 08:00 | 2024-06-01 12:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 276s 138kV South Bus (276s Union Carbide Prentiss), 276s T3 (276s Union Carbide Prentiss), 775L (276s Prentiss - 535s Joffre), 276s 27 (276s Prentiss), 276s 30 (276s Prentiss), 276s 25 (276s Prentiss), 276s 775X (276s Prentiss) | 2024-06-01 08:00 | 2024-06-05 18:00 | N | N |  | Bus, Transformer, Line, Switch, Circuit Breaker |  |  | Pre-Condition
ATCO, ALBIAN | 920s 901T (920s Jackpine), 920s 901 (920s Jackpine), 920s A1 (920s Jackpine) | 2024-06-01 08:00 | 2024-06-14 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 24.81L (SS-24 - SS-31), 24.83L (74s Janet - SS-24), 24.1TR (SS-24), 24B138-24BT3 (SS-24), 24MD138-24.1TR (SS-24), 24B138-24.83 (SS-24), 24B138-24.81 (SS-24) | 2024-06-01 08:00 | 2024-06-01 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 24.2TR (SS-24), 24.82L (SS-24 - SS-65), 24B138-24BT3 (SS-24), 24B138-24.82 (SS-24), 24MD138-24.2TR (SS-24) | 2024-06-01 12:01 | 2024-06-01 18:00 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 39.82L (SS-39 - SS-162), 39B138-39.82 (SS-39) | 2024-06-02 08:00 | 2024-06-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, TRANSALTA | 320p GT3 (320p Keephills), 320p 2089 (320p Keephills) | 2024-06-02 14:00 | 2024-06-05 11:30 | N | Y |  | Transformer, Switch |  |  | Restricts Generation
EPCOR | T1 (Namao), EP 511s Victoria T1 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria) | 2024-06-03 07:00 | 2024-08-30 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 557s CD2405 (557s Castle Downs) | 2024-06-03 07:00 | 2024-06-03 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 701L (223s Strome - 395s North Holden), 395s 701X (395s North Holden) | 2024-06-03 07:00 | 2024-06-16 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), EP 805s J722 (EP 805s Jasper) | 2024-06-03 07:00 | 2024-06-08 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 2MD138-2.82 (SS-2) | 2024-06-03 07:30 | 2024-06-04 18:00 | N | N |  | Line, Switch |  |  | Pre-Condition
ALTALINK | AML 511s T30 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings), AML 511s 1152 (AML 511s Crossings) | 2024-06-03 07:30 | 2024-06-06 16:30 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX, ALTALINK | 5s 752 (5s East Calgary), 5s C3 (5s East Calgary) | 2024-06-03 08:00 | 2024-06-03 09:00 | N | N |  | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX, ALTALINK | 5s 852 (5s East Calgary), 5s C4 (5s East Calgary) | 2024-06-03 08:00 | 2024-06-03 09:00 | N | N |  | Circuit Breaker, Shunts |  |  | For Information Only
SUNCOR | 29EDD-18 29PT-204 (29EDD-18 Firebag) | 2024-06-03 08:00 | 2024-06-10 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.63L (SS-16 - SS-36), 16B69-16.63 (SS-16) | 2024-06-03 08:00 | 2024-06-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary), 2MD138-2.1CAP (SS-2), MD109 (SS-2), MD111 (SS-2), MD108 (SS-2), MD110 (SS-2) | 2024-06-03 08:00 | 2024-06-03 09:00 | N | N |  | Shunts, Switch |  |  | Pre-Condition
ATCO | 2075s 901T (2075s Newell), 2075s ACF11 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell), 2075S 927 (2075s Newell), 2075S 928 (2075s Newell), 2075S 929 (2075s Newell), 2075S 934 (2075s Newell) | 2024-06-03 08:00 | 2024-06-14 16:00 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Prevents Normal Events
ENMAX | 9.3TR (SS-9) | 2024-06-03 08:00 | 2024-06-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7.1TR (SS-7) | 2024-06-03 08:00 | 2024-06-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 11.4TR (SS-11) | 2024-06-03 08:00 | 2024-06-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.63L (SS-16 - SS-36), 14.83L (SS-14 - SS-36), 36.5TR (SS-36), 36.2TR (SS-36), 16B69-16.63 (SS-16), 36MD138-36.5TR (SS-36), 36B69-16.63/36.5TR (SS-36), 36B138-36BT3 (SS-36) | 2024-06-03 08:00 | 2024-06-10 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  | Outage extended as per Enmax | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2024-06-03 09:00 | 2024-06-16 16:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 580s T2 (580s Sylvan Lake) | 2024-06-03 09:00 | 2024-06-07 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 5s T1 (5s East Calgary) | 2024-06-03 09:00 | 2024-06-03 10:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 5s T1 (5s East Calgary), 138kV Bus Z31 (SS-2), MD112 (SS-2), MD80 (SS-2), MD88 (SS-2), MD96 (SS-2), MD104 (SS-2) | 2024-06-03 09:00 | 2024-06-03 10:00 | N | Y |  | Transformer, Bus, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 772s 601T (772s Youngstown) | 2024-06-03 09:30 | 2024-06-06 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 730s STATCOM (730s Rycroft), 730s 705 (730s Rycroft) | 2024-06-03 10:00 | 2024-06-18 12:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Impacts RAS, Pre-Condition
ATCO | 905s 703 (905s Meikle) | 2024-06-03 10:00 | 2024-06-05 11:59 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 5s T2 (5s East Calgary), 138kV Bus Z32 (SS-2), MD113 (SS-2), MD87 (SS-2), MD95 (SS-2), MD103 (SS-2), MD111 (SS-2) | 2024-06-03 10:01 | 2024-06-03 11:00 | N | Y |  | Transformer, Bus, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 5s T2 (5s East Calgary) | 2024-06-03 10:01 | 2024-06-03 11:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ENMAX | 2.4TR (SS-2) | 2024-06-03 11:00 | 2024-06-03 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.3TR (SS-2) | 2024-06-03 12:00 | 2024-06-03 13:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 394s T3 (394s Empress), 394s 36 (394s Empress) | 2024-06-03 12:30 | 2024-06-06 13:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 2.2TR (SS-2) | 2024-06-03 13:00 | 2024-06-03 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 74s T2 (74s Janet), 74s 77 (74s Janet) | 2024-06-03 13:30 | 2024-06-08 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 2.1TR (SS-2) | 2024-06-03 14:00 | 2024-06-03 15:00 | N | N |  | Transformer |  |  | For Information Only
Lethbridge, ALTALINK | 111s 725LE (111s Coalbanks), 725L (111s Coalbanks - 725AL tap) | 2024-06-04 07:00 | 2024-06-04 17:00 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 1241L (510s Sunnybrook - 939s Livock) | 2024-06-04 07:00 | 2024-06-06 13:00 | N | Y |  | Line |  |  | Pre-Condition
ATCO | 12L44 (939s Livock - 951s Thickwood Hills), 951s 1201T (951s Thickwood Hills), 951s 1213R (951s Thickwood HIlls), 951s 1205 (951s Thickwood Hills), 951s 1206 (951s Thickwood Hills), 951s 1213 (951s Thickwood Hills), 951s 1201A (951s Thickwood Hills), 951s 1201TA (951s Thickwood Hills), 951s 1203B (951s Thickwood Hills), 951s 1204A (951s Thickwood Hills), 951s 1205A (951s Thickwood Hills), 951s 1206A (951s Thickwood Hills), 951s 1206B (951s Thickwood Hills), 951s 1213A (951s Thickwood Hills) | 2024-06-04 07:00 | 2024-06-06 13:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | 500 kV, Overload, Pre-Condition
ATCO | 939s 1216R (939s Livock) | 2024-06-04 07:00 | 2024-06-06 13:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 12L44 (939s Livock - 951s Thickwood Hills), 939s 1213R (939s Livock), 939s 1214A (939s Livock), 939s 1213A (939s Livock) | 2024-06-04 07:00 | 2024-06-06 13:00 | N | Y |  | Line, Shunts, Switch |  |  | 500 kV, Pre-Condition
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake), 63s 648 (63s Red Deer), 580s 648 (580s Sylvan Lake) | 2024-06-04 07:30 | 2024-06-04 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 183s T1 (183s Underwood), 183s T2 (183s Underwood), 183s 445 (183s Underwood), 445L (170s Pike - 183s Underwood) | 2024-06-04 07:30 | 2024-06-05 18:00 | N | N |  | Transformer, Circuit Breaker, Line |  |  | For Information Only
ALTALINK, ENEL | 205s T1 (205s Castle Rock Ridge) | 2024-06-04 07:30 | 2024-06-05 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 6.80L (SS-6 - SS-35), 6B138-6.80 (SS-6) | 2024-06-04 08:00 | 2024-06-04 09:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 172L (254s Coaldale - 370s North Lethbridge) | 2024-06-04 08:00 | 2024-06-07 18:00 | N | Y |  | Line |  |  | Overload, Pre-Condition
ALTALINK | 59s 452 (59s Peigan) | 2024-06-04 08:30 | 2024-06-06 16:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 35.81L (42s Sarcee - SS-35) | 2024-06-04 09:00 | 2024-06-04 10:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 42s 35 (42s Sarcee) | 2024-06-04 09:00 | 2024-06-04 10:00 | N | Y |  | Circuit Breaker |  |  | For Information Only
ENMAX | 35.2TR (SS-35) | 2024-06-04 10:00 | 2024-06-04 11:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47.1TR (SS-47) | 2024-06-04 10:53 | 2024-06-05 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 35.1TR (SS-35) | 2024-06-04 11:00 | 2024-06-04 12:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s GT3 (987s Clover Bar) | 2024-06-05 07:00 | 2024-06-09 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 14s T1 (14s Devon) | 2024-06-05 07:00 | 2024-06-05 17:00 | N | N |  | Transformer |  |  | For Information Only
Lethbridge, ALTALINK | 111s 207L (111s Coalbanks), 370s 207X (370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge) | 2024-06-05 07:00 | 2024-06-05 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5) | 2024-06-05 08:00 | 2024-06-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload
ENMAX | 11.81L (SS-11 - SS-13), 13B138-11.81 (SS-13), 11B138-11.81 (SS-11) | 2024-06-05 08:00 | 2024-06-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.5TR (SS-1) | 2024-06-05 08:00 | 2024-06-05 10:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7.2TR (SS-7) | 2024-06-05 08:00 | 2024-06-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 886L (428s Namaka - 431s Hussar), 431s C1 (431s Hussar), 431s 195 (431s Hussar), 431s 295 (431s Hussar) | 2024-06-05 08:00 | 2024-06-06 17:30 | N | N |  | Line, Shunts, Switch |  |  | Pre-Condition
ATCO | 769s 703T (769s Stettler), 769s 703 (769s Stettler), 769s 603 (769s Stettler) | 2024-06-05 08:30 | 2024-06-05 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 1.6TR (SS-1) | 2024-06-05 10:00 | 2024-06-05 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.7TR (SS-1) | 2024-06-05 12:00 | 2024-06-05 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 905s 706 (905s Meikle) | 2024-06-05 12:00 | 2024-06-07 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 1.8TR (SS-1) | 2024-06-05 14:00 | 2024-06-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, ENEL | 205s T2 (205s Castle Rock Ridge) | 2024-06-06 07:00 | 2024-06-07 16:30 | N | Y |  | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 886L (428s Namaka - 431s Hussar), 431s T1 (431s Hussar), 431s T2 (431s Hussar), 431s C1 (431s Hussar), 428s 886N (428s Namaka), 431s 195 (431s Hussar), 431s 295 (431s Hussar) | 2024-06-06 07:00 | 2024-06-06 17:30 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
CMH | MH-30L (MHS-3 Southridge - MHS-5 NE Crescent Heights) | 2024-06-06 07:00 | 2024-06-06 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 14s T3 (14s Devon) | 2024-06-06 07:00 | 2024-06-06 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake), 580s 637 (580s Sylvan Lake), 17s 637 (17s Benalto) | 2024-06-06 07:30 | 2024-06-06 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L121 (917s Horse River - 7LA121 tap) | 2024-06-06 08:00 | 2024-06-06 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.81L (SS-11 - SS-13), 11B138-11.81 (SS-11) | 2024-06-06 08:00 | 2024-06-06 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2024-06-06 08:00 | 2024-06-06 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 5B138-5BT12 (SS-5) | 2024-06-06 08:00 | 2024-06-06 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2024-06-07 08:00 | 2024-06-08 14:28 | N | N |  | Line, Circuit Breaker |  | Back Early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.9TR (SS-5) | 2024-06-07 08:00 | 2024-06-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 275s 1752 (275s Jenner) | 2024-06-08 | 2024-07-15 18:00 | N | Y |  | Circuit Breaker |  | Crews still working on repairs. | 240 kV, For Information Only
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 5B138-2.83 (SS-5) | 2024-06-08 08:00 | 2024-06-08 18:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2024-06-08 08:00 | 2024-06-08 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 2.83L (SS-5 - 2.83L tap), 5.9TR (SS-5), 5.10TR (SS-5), 5B138-2.83 (SS-5), 5B138-5BT12 (SS-5), 5MD138-5.9TR (SS-5) | 2024-06-08 08:00 | 2024-06-08 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Overload, Pre-Condition
ALTALINK | 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck) | 2024-06-09 08:00 | 2024-06-09 17:00 | N | N |  | Line, Transformer |  |  | For Information Only
EPCOR | 72NW15 (Namao - Woodcroft), N726 (Namao), W723 (Woodcroft) | 2024-06-10 07:00 | 2024-06-29 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1000 635-752-162 (635EDD-1000) | 2024-06-10 07:00 | 2024-06-10 18:00 | N | N |  | Circuit Breaker |  |  | For Information Only
EPCOR | 72DS26 (665s Dome - Strathcona), T1 (Strathcona), S721 (Strathcona), S722 (Strathcona), SAB1 (Strathcona) | 2024-06-10 07:00 | 2024-06-15 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 511s 240kV ACF 2 Bus (511s Crossings), AML 511s 5052 (AML 511s Crossings), AML 511s 4952 (AML 511s Crossings), AML 511s ACF21 (AML 511s Crossings), AML 511s ACF22 (AML 511s Crossings) | 2024-06-10 07:30 | 2024-06-13 12:57 | N | Y |  | Bus, Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK, NOVAC | 535s 5652 (535s Joffre), 535s 5552 (535s Joffre), 330L1 (535s Joffre - 330s Nova Joffre) | 2024-06-10 07:30 | 2024-06-14 18:00 | N | Y |  | Circuit Breaker, Line |  |  | Restricts Generation, Affects Cranking Path
ENMAX | 22B138-22BT8 (SS-22) | 2024-06-10 08:00 | 2024-06-10 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 8B138-6A0 (SS-8) | 2024-06-10 08:00 | 2024-06-18 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 38.3TR (SS-38) | 2024-06-10 08:00 | 2024-06-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 11.2TR (SS-11) | 2024-06-10 08:00 | 2024-06-11 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | 25 (Aurora), UT2 (Aurora) | 2024-06-10 08:00 | 2024-06-24 16:00 | N | N |  | Switch, Transformer |  |  | For Information Only
ENMAX | 41.84L (SS-41 - SS-54), 41B138-41.84 (SS-41) | 2024-06-10 08:00 | 2024-06-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514L (513s Lundbreck - 514BL tap) | 2024-06-10 08:00 | 2024-06-11 17:00 | N | Y |  | Line |  |  | Restricts Generation
ALTALINK | 871L (163s Amoco Empress - 341s Sand Hills), 163s 871X (163s Amoco Empress) | 2024-06-10 08:00 | 2024-06-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
CNRL, ATCO | 859s 52G (859s Primrose), 859s 701T (859s Primrose), 859s Protection & Control (859s Primrose) | 2024-06-10 08:00 | 2024-06-17 07:00 | N | Y |  | Circuit Breaker, Transformer, Terminal Equipment |  |  | Restricts Generation
ATCO, CNRL | 859s 501TD (859s Primrose) | 2024-06-10 08:00 | 2024-07-16 18:00 | N | N |  | Switch |  |  | For Information Only
ATCO | 863s 901 (863s Paintearth), 863s 902 (863s Paintearth), 863s 901T (863s Paintearth), 863s 902T (863s Paintearth) | 2024-06-10 08:30 | 2024-06-10 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 233s T2 (233s Beamer) | 2024-06-10 09:00 | 2024-06-12 18:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 161L (255s Vulcan - 504s Queenstown), 255s 138kV Bus 1 (255s Vulcan), 255s T1 (255s Vulcan), 255s 1152 (255s Vulcan), 504s 161 (504s Queenstown), 255s 352 (255s Vulcan) | 2024-06-10 09:30 | 2024-06-14 14:00 | N | N |  | Line, Bus, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
PGCP | PEC1 Lindbergh | 2024-06-10 09:30 | 2024-06-13 16:00 | N | N |  | Unit
ATCO | 7LA53 (969s Lindbergh - 7L53 tap), 969s 701T (969s Lindbergh), 969s 501 (969s Lindbergh), 969s 701 (969s Lindbergh), 969s 301 (969s Lindbergh) | 2024-06-10 09:30 | 2024-06-13 16:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 959s 901T (959s Lanfine) | 2024-06-10 10:00 | 2024-06-12 16:00 | N | Y |  | Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 905s 707 (905s Meikle) | 2024-06-10 10:00 | 2024-06-12 11:59 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 786s SVC (786s High Level), 786s 703T (786s High Level), 786s 703 (786s High Level) | 2024-06-10 10:00 | 2024-06-19 15:30 | N | Y |  | Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 746s T2 (746s Sherwood Park) | 2024-06-10 14:00 | 2024-06-13 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.82L (SS-2 - SS-5) | 2024-06-10 22:00 | 2024-06-11 06:00 | N | N |  | Line |  |  | Overload, Pre-Condition
ALTALINK | 787L (71s Lamoureux - 787AL tap) | 2024-06-11 07:00 | 2024-06-12 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Overload, Pre-Condition, Affects Cranking Path
ATCO | 844s 702T (844s AEC Mill), 844s 402 (844s AEC Mill), 844s 702 (844s AEC Mill) | 2024-06-11 07:00 | 2024-06-11 19:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 844s 701T (844s AEC Mill) | 2024-06-11 07:00 | 2024-06-11 19:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 993s T1 (993s Abee) | 2024-06-11 07:30 | 2024-06-11 20:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 36.1TR (SS-36) | 2024-06-11 08:00 | 2024-06-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 36.81L (44s Bearspaw Plant - SS-36), 36B138-36.81 (SS-36) | 2024-06-11 08:00 | 2024-06-12 16:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 36.3TR (SS-36) | 2024-06-11 08:00 | 2024-06-13 14:10 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 65B240-D134 (SS-65), 65B240-D135 (SS-65), 25B240-D142 (SS-25), 1109L (SS-25 - SS-65), 25B240-D141 (SS-25), 65MD240-1109 (SS-65), 25MD240-1109 (SS-25) | 2024-06-11 08:00 | 2024-06-11 16:00 | N | Y |  | Circuit Breaker, Line, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2024-06-11 08:00 | 2024-06-11 12:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 788s 701T (788s Hotchkiss), 788s 701TCS (788s Hotchkiss), 788s 702 (788s Hotchkiss) | 2024-06-11 08:00 | 2024-06-21 09:59 | N | N |  | Transformer, Switch, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 163s T5 (163s Amoco Empress), 163s 1552 (163s Amoco Empress), 163s 1252 (163s Amoco Empress), 163s T1 (163s Amoco Empress), 163s 989 (163s Amoco Empress), 163s 189 (163s Amoco Empress) | 2024-06-11 08:00 | 2024-06-13 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 24.81L (SS-24 - SS-31), 31B138-24.81 (SS-31) | 2024-06-11 08:00 | 2024-06-11 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 748L (267s Killarney Lake - 277s Hayter), 277s 138kV Bus 1 (277s Hayter), 277s T1 (277s Hayter), 277s 189 (277s Hayter), 277s 852 (277s Hayter), 277s 748 (277s Hayter), 277s 2 (277s Hayter), 277s 952 (277s Hayter) | 2024-06-11 08:30 | 2024-06-14 17:30 | N | N |  | Line, Bus, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 30EDD-1 623 (30EDD-1) | 2024-06-11 09:00 | 2024-06-11 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 1.80L (SS-1 - SS-28) | 2024-06-11 09:00 | 2024-06-11 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20) | 2024-06-11 10:00 | 2024-06-11 11:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 853s 704 (853s Ring Creek), 7L113 (853s Ring Creek - 930s Arcenciel) | 2024-06-11 10:00 | 2024-06-11 13:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.84L (SS-1 - SS-5) | 2024-06-11 11:01 | 2024-06-11 12:00 | N | N |  | Line |  |  | Pre-Condition
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2024-06-11 13:00 | 2024-06-11 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 853s 703 (853s Ring Creek), 7L82 (853s Ring Creek - 855s Hamburg) | 2024-06-11 13:01 | 2024-06-11 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L701 (757s Battle River - 7LA701 tap), 7LA701 (764s Heisler - 7L701 tap), 701L (223s Strome - 7LA701 tap) | 2024-06-11 18:45 | 2024-06-13 08:00 | N | Y |  | Line |  |  | For Information Only
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound) | 2024-06-11 18:55 | 2024-06-14 18:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L950 (132s Ware Junction - 801s Anderson) | 2024-06-11 19:08 | 2024-06-13 12:20 | N | Y |  | Line |  | breaker testing and maintenance | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK, GWPCORP | 603L (138s Windy Flats - 243s Soderglen), 243s T1 (243s Soderglen Wind Farm), 243s C1 (243s Soderglen Wind Farm), 243s 25CB1 (243s Soderglen), 243s 138DS1 (243s Soderglen) | 2024-06-12 07:00 | 2024-06-14 18:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Restricts Generation
SUNCOR | 29EDD-18 29PT-100 (29EDD-18 Firebag), 29EDD-18 29-752-102 (29EDD-18 Firebag), 29EDD-18 29-752-103 (29EDD-18 Firebag), 29EDD-18 29PS-0055 (29EDD-18 Firebag), 29EDD-18 29PS-0056 (29EDD-18 Firebag) | 2024-06-12 08:00 | 2024-06-22 18:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2024-06-12 08:00 | 2024-06-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.4TR (SS-162) | 2024-06-12 08:00 | 2024-06-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.83L (SS-38 - SS-39), 39B138-38.83 (SS-39), 38B138-38.83 (SS-38) | 2024-06-12 08:00 | 2024-06-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 161L (255s Vulcan - 504s Queenstown), 853L (504s Queenstown - 853AL tap), 504s 853E (504s Queenstown), 504s 161 (504s Queenstown), 255s 161 (255s Vulcan) | 2024-06-12 10:30 | 2024-06-12 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 905s 708 (905s Meikle) | 2024-06-12 12:00 | 2024-06-14 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-06-12 23:00 | 2024-06-13 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-06-13 03:00 | 2024-06-13 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 409s T1 (409s Shell Scotford) | 2024-06-13 07:00 | 2024-06-18 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, DOW | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 54s 707N (54s Fort Saskatchewan), 166s 707X (166s Dow Chemical Fort Saskatchewan) | 2024-06-13 07:00 | 2024-06-13 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 233s T1 (233s Beamer) | 2024-06-13 07:00 | 2024-06-20 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 816s P2403 (816s Petrolia), 816s P2402 (816s Petrolia), 816s PDS11 (816s Petrolia) | 2024-06-13 07:00 | 2024-06-14 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32), 32B138-26.81 (SS-32) | 2024-06-13 08:00 | 2024-06-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 6.80L (SS-6 - SS-35), 6.4TR (SS-6), 6B138-6.80 (SS-6) | 2024-06-13 08:00 | 2024-06-13 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, RESC | 326s 1012 (326s Murray Lake), 1012L (326s Murray lake - 516s Forty Mile), 516s Forty Mile | 2024-06-13 08:30 | 2024-06-15 09:15 | N | Y |  | Switch, Line, Station |  |  | 240 kV
ATCO | 7L81 (791s Rainbow Lake - BCH Harvest Energy FNC Tap), 791s 702 (791s Rainbow Lake) | 2024-06-13 10:30 | 2024-06-13 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 2.83L (SS-5 - 2.83L tap), 5B138-2.83 (SS-5) | 2024-06-14 08:00 | 2024-06-27 12:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38) | 2024-06-14 08:00 | 2024-06-14 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 5B138-2.83 (SS-5), 13B138-2.83 (SS-13) | 2024-06-14 08:00 | 2024-06-14 12:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 163s C1 (163s Amoco Empress), 163s C2 (163s Amoco Empress) | 2024-06-14 08:00 | 2024-06-14 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 163s T2 (163s Amoco Empress) | 2024-06-14 08:00 | 2024-06-16 17:00 | N | Y |  | Transformer |  |  | 240 kV
ENMAX | 7.84L (SS-7 - SS-36) | 2024-06-14 08:00 | 2024-06-15 12:00 | N | N |  | Line |  | Returned early | Creates Radial Feeds, Firm Load Loss
ENMAX | 13.82L (SS-13 - SS-22), 13B138-13.82 (SS-13) | 2024-06-14 12:00 | 2024-06-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2024-06-14 16:00 | 2024-06-28 15:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 277s T1 (277s Hayter), 277s 189 (277s Hayter), 277s 852 (277s Hayter), 277s 2 (277s Hayter) | 2024-06-14 17:31 | 2024-06-20 17:30 | N | N |  | Transformer, Switch, Circuit Breaker |  |  | For Information Only
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 37B138-37.81 (SS-37), SW83 (SS-38) | 2024-06-15 08:00 | 2024-06-15 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 39.82L (SS-39 - SS-162), 39B138-39.82 (SS-39), 162MD138-39.82 (SS-162) | 2024-06-16 08:00 | 2024-06-16 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 30EDD-1 624T (30EDD-1), 30EDD-1 627 (30EDD-1), 30EDD-1 628 (30EDD-1) | 2024-06-16 09:00 | 2024-06-20 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | Firm Load Loss
EPCOR | 1164L (816s Petrolia - EP Riverview), RW2401 (EP Riverview), RW2402 (EP Riverview), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia), RWDS11 (EP Riverview), 816s PDS12 (816s Petrolia) | 2024-06-17 06:00 | 2024-06-17 19:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | T1 (Kennedale) | 2024-06-17 07:00 | 2024-06-17 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 510s ACF11 (510s Sunnybrook), 510s ACF12 (510s Sunnybrook), 510s ACF13 (510s Sunnybrook), 510s ACF14 (510s Sunnybrook), 510s ACF14 - Spare (510s Sunnybrook), 510s 2552 (510s Sunnybrook), 510s 2652 (510s Sunnybrook), 510s 39 (510s Sunnybrook), 510s 40 (510s Sunnybrook) | 2024-06-17 07:30 | 2024-06-20 14:30 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | 500 kV, Pre-Condition
ENMAX | 21.1C (SS-21) | 2024-06-17 08:00 | 2024-06-18 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 54.1TR (SS-54) | 2024-06-17 08:00 | 2024-06-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.84L (SS-31 - SS-32), 31B138-31.84 (SS-31), 32B138-31.84 (SS-32) | 2024-06-17 08:00 | 2024-06-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20), 8A9 (SS-1) | 2024-06-17 08:00 | 2024-06-17 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 31.2TR (SS-31) | 2024-06-17 08:00 | 2024-06-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 2014s 701T (2014s Halfway), 2014s 701 (2014s Halfway) | 2024-06-17 09:00 | 2024-06-17 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, BHE | 879AL (719s Rattlesnake Ridge - 879L tap), 879L (368s Burdett - 879L tap), 879L (244s Bowmanton - 879AL tap), 368s 879 (368s Burdett) | 2024-06-17 09:00 | 2024-06-20 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L574 (822s Wolf Lake - 7L574 tap), 822s 702 (822s Wolf Lake) | 2024-06-17 09:00 | 2024-06-18 10:42 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
BHE | 719s T1 (719s Rattlesnake Ridge), 719s 138CB1 (719s Rattlesnake Ridge) | 2024-06-17 09:00 | 2024-06-21 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO, ALTALINK | 12L70 (12s Heartland - 2029s Heathfield), 2029s 1202 (2029s Heathfield), 2029s 1203 (2029s Heathfield), 12s 12L70 (12s Heartland), 2029s 1202B (2029s Heathfield), 2029s 1203A (2029s Heathfield) | 2024-06-17 09:30 | 2024-06-21 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, For Information Only
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson), 811s 710 (811s Clairmont Lake), 7L32D3 (862s South Bezanson) | 2024-06-17 09:30 | 2024-06-17 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 255s T2 (255s Vulcan), 255s 34 (255s Vulcan), 255s 352 (255s Vulcan), 255s 289 (255s Vulcan), 928s 180N (928s East Stavely) | 2024-06-17 09:30 | 2024-06-21 14:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 7L159 (770s Three Hills - 7L159 tap), 770s 703T (770s Three Hills), 770s 703 (770s Three Hills), 770s 704 (770s Three Hills) | 2024-06-17 10:00 | 2024-07-10 15:08 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 7L50 (757s Battle River - 491L tap), 757s 704T (757s Battle River), 757s 709 (757s Battle River) | 2024-06-17 10:00 | 2024-06-20 16:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 2014s 702T (2014s Halfway), 2014s 702 (2014s Halfway) | 2024-06-17 12:01 | 2024-06-17 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 799s T1 (799s Coleman) | 2024-06-17 13:30 | 2024-06-20 16:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 1098L (EP 805s Jasper - Poundmaker), EP 805s J2401 (EP 805s Jasper), EP 805s J2407 (EP 805s Jasper) | 2024-06-18 07:00 | 2024-06-21 11:55 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Affects Cranking Path
EPCOR | T2 (Kennedale) | 2024-06-18 07:00 | 2024-06-18 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 677L (305s Acheson - 595s Spruce Grove) | 2024-06-18 08:00 | 2024-06-27 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7), 7B138-7.82 (SS-7) | 2024-06-18 08:00 | 2024-06-18 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 26B138-26.83 (SS-26) | 2024-06-18 08:00 | 2024-06-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 151s C1 (151s Strathmore) | 2024-06-18 09:00 | 2024-06-18 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 2060s 701 (2060s Engstrom) | 2024-06-18 09:00 | 2024-06-18 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 7L39 (811s Clairmont Lake - 7LA39 tap), 811s 709 (811s Clairmont Lake) | 2024-06-18 09:30 | 2024-06-18 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 732s 901 (732s Mitsue) | 2024-06-18 10:00 | 2024-06-18 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2060s 702 (2060s Engstrom) | 2024-06-18 12:00 | 2024-06-18 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
TRANSALTA, ALTALINK | 528s Blue Trail Wind Farm, 608AL (528s Blue Trail Wind Farm - 608L tap), 528s 138CB1 (528s Blue Trail Wind Farm), 528s 138MDS3 (528s Blue Trail Wind Farm) | 2024-06-19 07:00 | 2024-06-19 16:00 | N | Y |  | Station, Line, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation
ALTALINK | 812L (65s High River - 812AL tap), 812L (392s Black Diamond - 812AL tap), 812AL (512s Hartell - 812L tap), 512s T1 (512s Hartell), 392s T3 (392s Black Diamond), 65s 812W (65s High River), 512s 812AL (512s Hartell), 392s 53 (392s Black Diamond) | 2024-06-19 07:00 | 2024-06-19 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 819L1 (819L Line) | 2024-06-19 07:30 | 2024-06-19 17:30 | N | N |  | Switch |  |  | For Information Only
ALTALINK | 732L (299s Kingman - 732AL tap), 299s T1 (299s Kingman), 299s 732N (299s Kingman), 732L-20A (732AL tap) | 2024-06-19 07:30 | 2024-06-19 18:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12), 12B138-832L (SS-12), 10B138-832 (SS-10), SW84 (SS-12) | 2024-06-19 08:00 | 2024-06-19 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6), 41B138-6.82 (SS-41) | 2024-06-19 08:00 | 2024-06-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, DOW | 166s 899N (166s Dow Chemical Fort Saskatchewan), 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen) | 2024-06-19 08:00 | 2024-06-20 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Pre-Condition, Restricts Generation
ATCO | 2060s 703 (2060s Engstrom) | 2024-06-19 09:00 | 2024-06-19 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap), 811s 708 (811s Clairmont Lake) | 2024-06-19 09:30 | 2024-06-20 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 732s 903 (732s Mitsue) | 2024-06-19 10:00 | 2024-06-19 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, Wild Rose Wind 2 | 264s 240kV Bus 2 (264s Elkwater), 264s 240kV Bus 3 (264s Elkwater), 264s T1 (264s Elkwater), 264s 352 (264s Elkwater), 264s 252 (264s Elkwater), 264s 52-L1 (264s Elkwater), 264s 89-B1 (264s Elkwater), 264s 89-L1 (264s Elkwater), 264s 289 (264s Elkwater) | 2024-06-19 12:00 | 2024-06-20 18:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ATCO | 2060S 704 (2060s Engstrom) | 2024-06-19 12:00 | 2024-06-19 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer), 171s 735X (171s Redwater), 233s 735N (233s Beamer) | 2024-06-20 07:00 | 2024-06-28 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 74s T2 (74s Janet), 74s 77 (74s Janet) | 2024-06-20 07:00 | 2024-06-26 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.84L (SS-31 - SS-32), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31) | 2024-06-20 08:00 | 2024-06-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 12.1TR (SS-12) | 2024-06-20 08:00 | 2024-06-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10B138-832 (SS-10), 12B138-832L (SS-12) | 2024-06-20 08:00 | 2024-06-20 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
SHELL | Shell Scotford Solar SHL2 Generator Test | 2024-06-20 08:00 | 2024-07-25 11:00 | N | N |  | Unit
Syncrude | 1315 (Syncrude Mildred Lake) | 2024-06-20 08:00 | 2024-10-07 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 834s 502R (834s Wesley Creek), 834s 501 (834s Wesley Creek), 834s 503 (834s Wesley Creek) | 2024-06-20 09:30 | 2024-06-20 15:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 732s 904 (732s Mitsue) | 2024-06-20 10:00 | 2024-06-20 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 2.83L (SS-5 - 2.83L tap), 5.9TR (SS-5), 5.10TR (SS-5), 5B138-2.83 (SS-5), 5B138-5BT12 (SS-5), 5MD138-5.9TR (SS-5) | 2024-06-21 08:00 | 2024-06-21 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Overload, Pre-Condition
ATCO | 788s 701T (788s Hotchkiss) | 2024-06-21 10:00 | 2024-07-17 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, ATCO | 252s Jarrow, 252s 138kV Bus (252s Jarrow), 408L (51s Wainwright - 252s Jarrow), 491L (252s Jarrow - 7L50 tap), 7L50 (526s Buffalo Creek - 491L tap), 7L50 (757s Battle River - 491L tap), 252s T2 (252s Jarrow), 252s 408 (252s Jarrow), 252s 2 (252s Jarrow) | 2024-06-22 08:00 | 2024-06-22 11:00 | N | Y |  | Station, Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 252s Jarrow, 252s 138kV Bus (252s Jarrow), 491L (252s Jarrow - 7L50 tap), 408L (51s Wainwright - 252s Jarrow), 252s T2 (252s Jarrow), 252s 408 (252s Jarrow), 252s 2 (252s Jarrow) | 2024-06-22 11:00 | 2024-06-27 11:00 | N | N |  | Station, Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 951s SVC (951s Thickwood) | 2024-06-22 20:09 | 2024-06-26 14:18 | N | Y |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24), 74s 24.83X (74s Janet) | 2024-06-23 07:00 | 2024-06-23 12:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
TRANSALTA | 240s McBride Lake | 2024-06-23 07:00 | 2024-06-26 17:00 | N | N |  | Station |  |  | Restricts Generation
ALTALINK, ENMAX | 74s 24.83X (74s Janet), 24.83L (74s Janet - SS-24) | 2024-06-23 07:00 | 2024-06-23 12:00 | N | Y |  | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 725BL (240s McBride Lake - 725L tap), 725BL54 (725BL tap) | 2024-06-23 10:00 | 2024-06-26 17:00 | N | Y |  | Line, Switch |  |  | For Information Only, Pre-Condition
ALTALINK, Lethbridge | 725L (674s Bowron - 725BL tap), 725L (15s Fort MacLeod - 725BL tap), 725BL (240s McBride Lake - 725L tap), 15s 725 (15s Fort Macleod), 674s 725W (674s Bowron) | 2024-06-23 10:00 | 2024-06-26 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK, ENMAX | 74s 23.80W (74s Janet), 23.80L (74s Janet - SS-23) | 2024-06-23 12:00 | 2024-06-23 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 74s 23.80W (74s Janet) | 2024-06-23 12:00 | 2024-06-23 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 805s C1 (805s Jasper) | 2024-06-24 07:00 | 2024-06-24 17:00 | N | Y |  | Shunts |  |  | Pre-Condition
EPCOR | T1 (EP Riverview), RW2405 (EP Riverview), RW2401 (EP Riverview), RWAB1 (EP Riverview) | 2024-06-24 07:00 | 2024-06-29 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss,
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS14 (816s Petrolia) | 2024-06-24 07:00 | 2024-07-12 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 793L (87s Gaetz - 535s Joffre), 535s 6052 (535s Joffre), 535s 6152 (535s Joffre) | 2024-06-24 07:30 | 2024-06-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 2075s 902T (2075s Newell), 2075S 930 (2075s Newell), 2075s ACF21 (2075s Newell) | 2024-06-24 08:00 | 2024-06-28 16:00 | N | Y |  | Transformer, Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 5.6TR (SS-5) | 2024-06-24 08:00 | 2024-06-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 20.1TR (SS-20) | 2024-06-24 08:00 | 2024-06-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 8.1TR (SS-8), 8.2TR (SS-8), 8B138-7A0 (SS-8), 8B138-6A0 (SS-8), 6A01 (SS-8), 6A02 (SS-8), 6A10 (SS-8), 7A1 (SS-8), 7A11 (SS-8) | 2024-06-24 08:00 | 2024-06-26 13:30 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ENMAX | 7.2TR (SS-7) | 2024-06-24 08:00 | 2024-06-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34), 34B69-16.60 (SS-34), 16B69-16.60 (SS-16) | 2024-06-24 08:00 | 2024-06-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 732s 705 (732s Mitsue) | 2024-06-24 09:00 | 2024-06-25 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 802s 703T (802s Michichi Creek), 802s 703 (802s Michichi Creek) | 2024-06-24 09:00 | 2024-06-27 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 826s 702 (826s Marguerite Lake) | 2024-06-24 09:00 | 2024-06-28 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 255s T1 (255s Vulcan) | 2024-06-24 09:30 | 2024-06-27 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 834s 901T (834s Wesley Creek), 834s 901 (834s Wesley Creek), 834s 904 (834s Wesley Creek), 834s 501 (834s Wesley Creek), 834s 701TD (834s Wesley Creek) | 2024-06-24 09:30 | 2024-06-28 17:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet), 74s 104 (74s Janet) | 2024-06-24 09:30 | 2024-06-25 17:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO, ALTALINK | 12L85 (12s Heartland - 2029s Heathfield), 2029s 1207 (2029s Heathfield), 2029s 1208 (2029s Heathfield), 12s 12L85 (12s Heartland), 2029s 1207B (2029s Heathfield), 2029s 1208A (2029s Heathfield) | 2024-06-24 09:30 | 2024-06-28 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, For Information Only
ATCO | 811s 701C (811s Clairmont Lake) | 2024-06-24 09:30 | 2024-06-25 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 74s 352 (74s Janet) | 2024-06-24 10:00 | 2024-06-24 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2024-06-24 10:00 | 2024-06-27 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 74s 76 (74s Janet) | 2024-06-24 12:00 | 2024-06-24 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 650s SVC (650s Hansman Lake), 650s 252 (650s Hansman Lake), 650s 352 (650s Hansman Lake), 650s 489 (650s Hansman Lake) | 2024-06-24 12:30 | 2024-06-28 12:30 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 20s T5 (20s Ghost), 20s 8 (20s Ghost) | 2024-06-24 13:00 | 2024-06-27 15:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
TRANSALTA | 239s T2 (239s Castle River) | 2024-06-24 13:45 | 2024-06-28 18:00 | N | N |  | Transformer |  |  | Restricts Generation
EPCOR | 330P GT3 (330p Genesee), 330p 1207 (330p Genesee), 330p 1208 (330p Genesee), 330p 12GT3D (330p Genesee) | 2024-06-25 07:00 | 2024-06-27 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 500 kV, Restricts Generation
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 262s 870W (262s Rocky Mountain House), 263s 870E (263s Strachan) | 2024-06-25 07:00 | 2024-06-28 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 74s 2252 (74s Janet) | 2024-06-25 07:00 | 2024-06-25 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s 2352 (74s Janet) | 2024-06-25 12:00 | 2024-06-25 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s 2852 (74s Janet) | 2024-06-26 07:00 | 2024-06-26 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 39.2TR (SS-39) | 2024-06-26 08:00 | 2024-06-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 21.61L (SS-21 - SS-34), 34B69-21.61 (SS-34), 21B69-21.61 (SS-21) | 2024-06-26 08:00 | 2024-06-27 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 35.2TR (SS-35) | 2024-06-26 08:00 | 2024-06-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31) | 2024-06-26 08:00 | 2024-06-27 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 732s 706 (732s Mitsue) | 2024-06-26 09:00 | 2024-06-27 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 957s 901 (957s McClelland) | 2024-06-26 10:00 | 2024-06-26 12:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 74s 3852 (74s Janet) | 2024-06-26 12:01 | 2024-06-26 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 957s 902 (957s McClelland) | 2024-06-26 12:01 | 2024-06-26 14:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 957s 903 (957s McClelland) | 2024-06-26 14:01 | 2024-06-26 16:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 770s 506C (770s Three Hills) | 2024-06-27 01:00 | 2024-06-27 14:00 | N | N |  | Shunts |  | 701T Maintenance | Pre-Condition
ALTALINK | 108s T2 (108s Amelia), 108s 452 (108s Amelia), 108s 352 (108s Amelia) | 2024-06-27 09:00 | 2024-06-27 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK, ATCO | 252s Jarrow, 252s 138kV Bus (252s Jarrow), 408L (51s Wainwright - 252s Jarrow), 491L (252s Jarrow - 7L50 tap), 7L50 (526s Buffalo Creek - 491L tap), 7L50 (757s Battle River - 491L tap), 252s T2 (252s Jarrow), 252s 408 (252s Jarrow), 252s 2 (252s Jarrow) | 2024-06-27 11:00 | 2024-06-27 17:30 | N | Y |  | Station, Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 2.83L (SS-5 - 2.83L tap), 13B138-2.83 (SS-13), 5B138-2.83 (SS-5) | 2024-06-27 13:00 | 2024-06-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2024-06-28 | 2024-06-28 23:00 | N | N |  | Transformer
BCH | 1L275 (799s Coleman - BCH Natal) | 2024-06-28 08:00 | 2024-06-28 17:00 | N | Y |  | Line |  |  | For Information Only
ENMAX | 6.82L (SS-6 - SS-41), 33.83L (SS-33 - SS-41), 41.1C (SS-41), 41.2TR (SS-41), 41B138-41BT3 (SS-41), SW83 (SS-41), SW87 (SS-41), 41B138-6.82 (SS-41), 33B138-33.83 (SS-33) | 2024-06-28 08:00 | 2024-06-28 18:00 | N | N |  | Line, Shunts, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, DOW | 54s 138kV East Bus (54s Fort Saskatchewan), 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 709L (54s Fort Saskatchewan - 172s Sherritt), 54s T3 (54s Fort Saskatchewan), 166s 707X (166s Dow Chemical Fort Saskatchewan), 172s 709X (172s Sherritt) | 2024-06-28 09:00 | 2024-06-28 15:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 816s P2406 (816s Petrolia) | 2024-06-28 17:00 | 2024-07-26 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s CGB3 (987s Clover Bar), 987s GT3 (987s Clover Bar) | 2024-06-29 07:00 | 2024-07-11 10:00 | N | Y |  | Circuit Breaker, Transformer |  |  | Restricts Generation
ATCO | 9L912 (63s Red Deer - 766s Nevis), 766s 902 (766s Nevis), 766s 9L912D1 (766s Nevis) | 2024-06-29 08:00 | 2024-07-01 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20), 20MD138-20.1TR (SS-20) | 2024-06-29 08:00 | 2024-06-29 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 20.82L (SS-20 - SS-21), 20.3TR (SS-20), 20B138-20.82 (SS-20), 20MD138-20.3TR (SS-20) | 2024-06-29 12:00 | 2024-06-29 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22.81 (SS-22), 22B138-22BT8 (SS-22) | 2024-06-30 08:00 | 2024-06-30 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 77s 40 (77s Sagitawah) | 2024-06-30 13:56 | 2024-07-02 13:54 | N | Y |  | Circuit Breaker |  | Breaker has been returned to service. | 240 kV
ENMAX | 31.3TR (SS-31) | 2024-07-01 08:00 | 2024-07-01 16:00 | N | N |  | Transformer |  |  | For Information Only
VREL | VBN1 Benalto 1 DER Generator Test | 2024-07-01 08:00 | 2024-07-19 18:00 | N | N |  | Unit
ENMAX | 22.3TR (SS-22) | 2024-07-01 12:00 | 2024-07-02 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 1150L (39s Bickerdike  345s Hornbeck) | 2024-07-01 15:18 | 2024-07-09 18:00 | N | N |  | Line |  |  | Firm Load Loss
ALTALINK | 745L (39s Bickerdike - 745AL tap) | 2024-07-01 16:18 | 2024-07-02 22:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | K721 (Kennedale), 72CK13 (987s Clover Bar - Kennedale), 987s CK726 (987s Clover Bar) | 2024-07-02 07:00 | 2024-07-05 17:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | T2 (Meadowlark), M722 (Meadowlark), M723 (Meadowlark), MAB2 (Meadowlark) | 2024-07-02 07:00 | 2024-07-06 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | EP 803s T2 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s LAB2 (EP 803s Lambton) | 2024-07-02 07:00 | 2024-07-02 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 701L (223s Strome - 7LA701 tap) | 2024-07-02 07:00 | 2024-07-07 18:00 | N | Y |  | Line
ATCO, ALTALINK | 701L (223s Strome - 7LA701 tap) | 2024-07-02 07:00 | 2024-07-07 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 535s C1 (535s Joffre) | 2024-07-02 07:30 | 2024-07-04 15:15 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2024-07-02 08:00 | 2024-07-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 40.81L (SS-40 - SS-41), 40B138-40.81 (SS-40), 41B138-40.81 (SS-41) | 2024-07-02 08:00 | 2024-07-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | Syncrude Plant 30-2 30-2PTR72-A1 (UE-1 Syncrude Plant 30-2), UE-1 1501 (UE-1 Syncrude Plant 30-2), UE-1 72-02 (UE-1 Syncrude Plant 30-2), UE-1 7202 (UE-1 Syncrude Plant 30-2) | 2024-07-02 08:00 | 2024-07-03 14:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  | returned early | Restricts Generation
ENMAX | 22.1TR (SS-22) | 2024-07-02 08:00 | 2024-07-09 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ATCO, SHELL | EX1-01L (402s Scotford Expansion One - 879s Upgrader), 879s 152 (879s Upgrader), 402s EX1-01LD1 (402s Scotford Expansion One) | 2024-07-02 09:00 | 2024-07-02 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 55s T2 (55s Olds), 55s 52 (55s Olds) | 2024-07-02 09:00 | 2024-07-10 10:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 15s 452 (15s Fort Macleod) | 2024-07-02 09:30 | 2024-07-05 15:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib), 718s 702 (718s Parsons Creek), 718s 702T (718s Parsons Creek), 718s 700D1 (718s Parsons Creek) | 2024-07-02 10:00 | 2024-07-03 16:00 | N | N |  | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 266s 1037L FSC1 (266s SC1) | 2024-07-02 10:30 | 2024-07-02 17:30 | N | Y |  | Shunts |  |  | 240 kV
ALTALINK | 214s T2 (214s Innisfail) | 2024-07-02 14:00 | 2024-07-12 17:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK, REDDEER | 217s 138kV Bus (217s North Red Deer), 768L (209s Timberlands - 217s North Red Deer), 425L (194s South Red Deer - 217s North Red Deer), 217s T1 (217s North Red Deer), 217s T7 (217s North Red Deer), 217s C1 (217s North Red Deer), 217s 425 (217s North Red Deer), 217s 768 (217s North Red Deer), 209s 768W (209s Timberlands), 194s 425 (194s South Red deer), 217s 14-81-1 (217s North Red Deer) | 2024-07-03 07:00 | 2024-07-03 16:00 | N | N |  | Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 233s 6 (233s Beamer) | 2024-07-03 07:30 | 2024-07-04 16:00 | N | N |  | Circuit Breaker |  | extended due to breaker issues | Creates Radial Feeds, Firm Load Loss
ENMAX | 40.81L (SS-40 - SS-41) | 2024-07-03 08:00 | 2024-07-03 16:00 | N | N |  | Line |  |  | For Information Only
REDDEER | 217s T1 (217s North Red Deer) | 2024-07-03 08:00 | 2024-07-11 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 40.81L (SS-40 - SS-41), 41B138-40.81 (SS-41) | 2024-07-03 08:00 | 2024-07-03 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 71s 452 (71s Lamoureux) | 2024-07-03 08:30 | 2024-07-03 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 331s T1 (331s Ponoka) | 2024-07-03 08:30 | 2024-07-03 16:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 732s 702 (732s Mitsue) | 2024-07-03 09:00 | 2024-07-03 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO, AIRLIQUIDE | ALC03L (402s Scotford Expansion One - 408s Air Liquide Scotford) | 2024-07-03 09:00 | 2024-07-03 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 774s 701 (774s Monitor), 7L224 (650s Hansman Lake - 774s Monitor) | 2024-07-03 10:00 | 2024-07-10 15:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 732s 703 (732s Mitsue) | 2024-07-03 12:00 | 2024-07-03 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 892L (244s Bowmanton - 895s Suffield), 895s 892 (895s Suffield) | 2024-07-03 12:00 | 2024-07-03 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 718s 701T (718s Parsons Creek), 718s 703 (718s Parsons Creek), 718s 701 (718s Parsons Creek) | 2024-07-03 16:01 | 2024-07-05 16:00 | N | N |  | Transformer, Circuit Breaker |  | Outage extended until 07/05/2024. | Pre-Condition
ALTALINK, SHELL | 409s T3 (409s Shell Scotford), 409s 1252 (409s Shell Scotford) | 2024-07-04 07:00 | 2024-07-05 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 510s 3752 (510s Sunnybrook) | 2024-07-04 07:30 | 2024-07-04 16:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 41.84L (SS-41 - SS-54), 54B138-41.84 (SS-54), 41B138-41.84 (SS-41) | 2024-07-04 08:00 | 2024-07-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.84L (SS-3 - SS-13), 13B138-3.84 (SS-13), 3B138-3.84 (SS-3) | 2024-07-04 08:00 | 2024-07-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 732s 704 (732s Mitsue) | 2024-07-04 09:00 | 2024-07-04 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
FORTIS | COL1 Coaldale (COL1) Generator test | 2024-07-04 09:00 | 2024-07-31 19:00 | N | N |  | Unit
ATCO | 732s 707 (732s Mitsue) | 2024-07-04 12:00 | 2024-07-04 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 344s T2 (344s Warner) | 2024-07-05 07:00 | 2024-07-08 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 443L (55s Olds - 214s Innisfail), 55s 443 (55S Olds), 214s 443 (214s Innisfail) | 2024-07-05 07:30 | 2024-07-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO, ALTALINK | ALC02L (409s Shell Scotford - 879s Upgrader), 409s 110 (409s Shell Scotford), 879s 252 (879s Upgrader) | 2024-07-06 07:00 | 2024-07-06 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 857L (409s Shell Scotford - 410s Josephburg), 409s 857W (409s Shell Scotford) | 2024-07-07 07:00 | 2024-07-07 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton) | 2024-07-08 07:00 | 2024-07-31 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), 72LS24 (EP 803s Lambton - Strathcona), EP 803s T3 (EP 803s Lambton), S724 (Strathcona), EP 803s L721 (EP 803s Lambton) | 2024-07-08 07:00 | 2024-07-19 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | EP 805s J2405 (EP 805s Jasper) | 2024-07-08 07:00 | 2024-07-11 17:00 | N | Y |  | Circuit Breaker | rescheduled: swap with Meadowlark TX3 outage because this outage could cause 72JM18 overloading. |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 417L (55s Olds - 281s Johnson), 281s 1152 (281s Johnson), 281s 1252 (281s Johnson), 55s 417 (55S Olds) | 2024-07-08 07:30 | 2024-07-08 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 784L (535s Joffre - 784AL tap), 535s 6352 (535s Joffre), 535s 6452 (535s Joffre) | 2024-07-08 07:30 | 2024-07-11 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
VISIONREQ | 354s DVAR1 (354s Summerview) | 2024-07-08 08:00 | 2024-07-09 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 21.1C (SS-21) | 2024-07-08 08:00 | 2024-07-08 16:00 | N | N |  | Shunts |  |  | For Information Only
ENMAX | 15.1TR (SS-15) | 2024-07-08 08:00 | 2024-07-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47.2TR (SS-47) | 2024-07-08 08:00 | 2024-07-11 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 721s 702T (721s La Corey), 721s 702 (721s La Corey) | 2024-07-08 08:30 | 2024-07-11 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 849s 902 (849s Joslyn Creek) | 2024-07-08 09:00 | 2024-07-09 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
BCH | 2L294 (BCH A. A. Lambert - BCH Cranbrook) | 2024-07-08 09:00 | 2024-07-10 14:55 | N | Y |  | Line |  |  | Pre-Condition
ATCO | 809s 902T (809s Louise Creek), 809s 910 (809s Louise Creek), 809s 911 (809s Louise Creek), 809s 702 (809s Louise Creek), 809S 902TD (809s Louise Creek) | 2024-07-08 09:00 | 2024-07-11 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 845s 709 (845s Big Mountain) | 2024-07-08 09:30 | 2024-07-09 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 808s 701T (808s Procter & Gamble), 808s 701 (808s Procter & Gamble), 808s 401 (808s Procter & Gamble) | 2024-07-08 09:30 | 2024-07-09 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 834s 902T (834s Wesley Creek), 834s 902 (834s Wesley Creek), 834s 903 (834s Wesley Creek), 834s 503 (834s Wesley Creek) | 2024-07-08 09:30 | 2024-07-12 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L42 (716s Lloydminster - 751s Hill), 751s 702 (751s Hill) | 2024-07-08 11:00 | 2024-07-08 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 191s T1 (191s N.W. Cardiff) | 2024-07-08 13:00 | 2024-08-01 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 59s 752 (59s Peigan) | 2024-07-08 14:30 | 2024-07-09 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 708L (233s Beamer - 708AL tap), 233s 708X (233s Beamer) | 2024-07-09 07:00 | 2024-07-11 18:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L749 (716s Lloydminster - 7LB749 tap), 716s 701 (716s Lloydminster) | 2024-07-09 07:30 | 2024-07-10 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | AML 511s ACF11 (AML 511s Crossings) | 2024-07-09 07:30 | 2024-07-10 15:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 31.1C (SS-31) | 2024-07-09 08:00 | 2024-09-17 15:20 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 562s 152 (562s Cypress) | 2024-07-09 08:30 | 2024-07-10 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 853L (28s West Brooks - 853AL tap), 28s 25 (28s West Brooks), 28s 28 (28s West Brooks), 28s 853W (28s West Brooks) | 2024-07-09 10:00 | 2024-07-09 15:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 771s 701T (771s Veteran) | 2024-07-09 13:00 | 2024-07-18 17:00 | N | N |  | Transformer |  |  | For Information Only
VISIONREQ | 354s DVAR2 (354s Summerview) | 2024-07-10 07:00 | 2024-07-11 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, Lethbridge | 172L (181s Chinook - 370s North Lethbridge), 370s 175 (370s North Lethbridge), 181s 172L (181s Chinook) | 2024-07-10 07:30 | 2024-07-10 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 993s T1 (993s Abee) | 2024-07-10 07:30 | 2024-07-11 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive), 743s 603 (743s Sarah Lake) | 2024-07-10 08:00 | 2024-07-16 12:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 22.2TR (SS-22) | 2024-07-10 08:00 | 2024-07-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 1CB2 (BCH Natal) | 2024-07-10 08:00 | 2024-07-11 16:00 | N | Y |  | Line, Circuit Breaker |  | Completed early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 849s 903 (849s Joslyn Creek) | 2024-07-10 09:00 | 2024-07-11 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 845s 701 (845s Big Mountain) | 2024-07-10 09:30 | 2024-07-11 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 7L749 (899s Edgerton - 7LB749 tap), 899s 749N (899s Edgerton) | 2024-07-10 16:31 | 2024-07-10 17:19 | N | Y |  | Line, Circuit Breaker |  | Done early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2024-07-10 21:31 | 2024-07-16 11:59 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 74s C4 (74s Janet) | 2024-07-11 | 2024-12-13 17:00 | N | Y |  | Shunts |  |  | For Information Only
SUNCOR | 635EDD-1001 144kV Bus 635PP-1006 (635EDD-1001), 635EDD-1001 635-752-621 (635EDD-1001), 635EDD-1001 635-752-611 (635EDD-1001), 635EDD-1001 635-752-631 (635EDD-1001), 635EDD-1001 635-752-642 (635EDD-1001), 635EDD-1001 635-752-651 (635EDD-1001), 635EDD-1001 635-752-661 (635EDD-1001) | 2024-07-11 07:00 | 2024-07-15 18:00 | N | N |  | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
ENMAX | 47B138-771/1 (SS-47) | 2024-07-11 08:00 | 2024-07-11 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 751s 701C (751s Hill) | 2024-07-11 17:00 | 2024-07-19 15:15 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 55s T1 (55s Olds) | 2024-07-12 07:30 | 2024-07-12 15:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47B138-771 (SS-47) | 2024-07-12 08:00 | 2024-07-12 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge), 254s 770 (254s Coaldale), 370s 770E (370s North Lethbridge) | 2024-07-15 07:00 | 2024-07-18 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 805s T1 (805s Jasper), 72JW19 (EP 805s Jasper - Woodcroft), 72JM18 (EP 805s Jasper - Meadowlark), EP 805s J2401 (EP 805s Jasper), EP 805s JAB1 (EP 805s Jasper), EP 805s J724 (EP 805s Jasper), EP 805s J722 (EP 805s Jasper) | 2024-07-15 07:00 | 2024-07-20 17:00 | N | Y |  | Transformer, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK | 472L (213s Hughenden - 472AL tap), 213s 472 (213s Hughenden) | 2024-07-15 07:00 | 2024-07-18 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 535s 1152 (535s Joffre) | 2024-07-15 07:30 | 2024-07-17 18:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 102s SVC (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon), 102s 7189 (102s Langdon) | 2024-07-15 08:00 | 2024-07-18 10:57 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15) | 2024-07-15 08:00 | 2024-07-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.1TR (SS-14) | 2024-07-15 08:00 | 2024-07-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAXEC, ALTALINK | 383s T1 (383s Kettles Hill Windfarm), 383s T2 (383s Kettles Hill Windfarm), 616AL (383s Kettles Hill Windfarm - 616L tap) | 2024-07-15 08:00 | 2024-07-19 18:00 | N | Y |  | Transformer, Line | 383s T1 (383s Kettles Hill Windfarm), 383s T2 (383s Kettles Hill Windfarm) |  | For Information Only, Restricts Generation
ENMAX | 5.1TR (SS-5) | 2024-07-15 08:00 | 2024-07-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.2TR (SS-15) | 2024-07-15 08:00 | 2024-07-20 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 5B138-2.83 (SS-5) | 2024-07-15 08:00 | 2024-08-09 16:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ATCO | 2029s ACF11 (2029s Heathfield), 2029s 1218 (2029s Heathfield) | 2024-07-15 08:30 | 2024-07-15 16:00 | N | Y |  | Shunts, Switch |  |  | 500 kV, Pre-Condition
ALTALINK | 233s 735N (233s Beamer), 735L (171s Redwater - 233s Beamer) | 2024-07-15 09:00 | 2024-07-15 17:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 616L (103s Goose Lake - 616AL tap), 616L (59s Peigan - 616AL tap), 59s 616 (59s Peigan) | 2024-07-15 09:00 | 2024-07-16 09:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 849s 906 (849s Joslyn Creek) | 2024-07-15 09:00 | 2024-07-16 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
Saskpower | Sask Power AS902 | 2024-07-15 09:00 | 2024-07-15 16:00 | N | Y |  | Circuit Breaker |  |  | Limits ATC, Pre-Condition
ATCO | 7L30 (732s Mitsue - 844s AEC Mill), 844s 703 (844s AEC Mill) | 2024-07-15 09:00 | 2024-07-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 845s 702 (845s Big Mountain) | 2024-07-15 09:30 | 2024-07-16 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 497L (138s Windy Flats - 1063s Windrise), 138s T1 (138s Windy Flats), 138s 138kV Bus 1 (138s Windy Flats), 138s 1889 (138s Windy Flats) | 2024-07-15 10:00 | 2024-07-24 15:00 | N | Y |  | Line, Transformer, Bus, Switch |  |  | 240 kV, Restricts Generation
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson) | 2024-07-15 11:00 | 2024-07-18 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 17s 11 (17s Benalto) | 2024-07-15 11:30 | 2024-07-15 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 42s T2 (42s Sarcee), 42s 60 (42s Sarcee) | 2024-07-15 11:30 | 2024-07-19 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 790L (434s Stony Plain - 790AL tap), 434s 790 (434s Stony Plain) | 2024-07-15 11:40 | 2024-07-18 17:00 | N | N |  | Line, Circuit Breaker
ALTALINK | 87s 552 (87s Gaetz) | 2024-07-15 12:30 | 2024-07-15 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 171s T2 (171s Redwater) | 2024-07-15 13:30 | 2024-07-18 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, CapitalPower | 1148L (251s Whitla - 1018s Shamrock), 1018s 7290-CB-001 (1018s Shamrock), 1018s 7290-CB-008 (1018s Shamrock) | 2024-07-16 06:00 | 2024-07-16 20:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Restricts Generation
ALTALINK | 305s 446 (305s Acheson), 446L (305s Acheson - 367s Harry Smith) | 2024-07-16 07:00 | 2024-07-16 17:30 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 514L (396s Pincher Creek - 514BL tap), 514BL (322s Cowley Ridge Windplant - 514L tap), 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck) | 2024-07-16 07:00 | 2024-07-17 13:00 | N | Y |  | Line, Transformer |  |  | Restricts Generation
ALTALINK | 223s T1 (223s Strome) | 2024-07-16 07:30 | 2024-07-17 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 807L (233s Beamer - 807AL tap), 233s 807X (233s Beamer) | 2024-07-16 07:30 | 2024-07-16 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 15s 463 (15s Fort Macleod) | 2024-07-16 08:00 | 2024-07-29 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 21.1TR (SS-21) | 2024-07-16 08:00 | 2024-07-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 87s 852 (87s Gaetz) | 2024-07-16 08:00 | 2024-07-16 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 2029s ACF12 (2029s Heathfield) | 2024-07-16 08:30 | 2024-07-16 16:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 700s 701 (700s Bonnyville), 7L70 (700s Bonnyville - 707s St. Paul) | 2024-07-16 08:30 | 2024-07-16 17:30 | N | Y |  | Circuit Breaker, Line |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 723s 252 (723s Christina Lake), 723s 240kV Bus 2 (723s Christina Lake), 723s T2 (723s Christina Lake), 723s 652 (723s Christina Lake) | 2024-07-16 08:30 | 2024-07-18 17:30 | N | Y |  | Circuit Breaker, Bus, Transformer |  |  | Contingency Requires Mitigation
BCH | 5L92 (BCH Cranbrook - BCH Selkirk) | 2024-07-16 09:00 | 2024-07-17 23:43 | Y | Y |  | Line | **FOR OC** 1. Enter TRMr+ = 466 MW in MARGO manual override 2. Check MARGO BC/MATL capability (ATC). The BC/MATL capability (ATC) = 103 MW (lowest number for the period of Jul 16, 2024 HE2). 3. In order to show 0 MW on S&D. Using max MATL Import ATC: 295 MW (No Restriction )  15 MW (MATL TRM ) = 280 MW, so the BC import ATC becomes 105 MW  280 MW = -175 MW (enter 0, instead of a negative number). |  | Limits ATC, 500 kV
ATCO | 834s 901 (834s Wesley Creek) | 2024-07-16 09:30 | 2024-07-17 17:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 827s SVC (827s Cranberry Lake), 827s 703 (827s Cranberry Lake) | 2024-07-16 10:00 | 2024-07-17 16:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
CNRL, ATCO | 859s 52G (859s Primrose), 859s 501TD (859s Primrose) | 2024-07-16 11:00 | 2024-07-16 13:00 | N | Y |  | Circuit Breaker, Switch |  |  | Restricts Generation
ALTALINK | 256s C1 (256s Harmattan) | 2024-07-16 12:00 | 2024-11-26 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 87s 252 (87s Gaetz) | 2024-07-16 13:00 | 2024-07-16 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 162.4TR (SS-162) | 2024-07-17 | 2024-07-26 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s CDS45 (987s Cloverbar), 987s C2410 (987s Clover Bar), 987s C2409 (987s Clover Bar) | 2024-07-17 07:00 | 2024-08-09 17:00 | N | Y |  | Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 180L (15s Fort Macleod - 180AL tap), 15s 180N (15s Fort Macleod) | 2024-07-17 07:30 | 2024-07-19 13:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 5.5TR (SS-5) | 2024-07-17 08:00 | 2024-07-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16) | 2024-07-17 08:00 | 2024-07-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2029s ACF13 (2029s Heathfield) | 2024-07-17 08:30 | 2024-07-17 16:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ATCO | 7L760 (767s Oyen - 7LA760 tap), 767s 702 (767s Oyen) | 2024-07-17 09:00 | 2024-07-18 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L31 (732s Mitsue - 844s AEC MILL), 844s 704 (844s AEC Mill) | 2024-07-17 09:00 | 2024-07-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain), 845s 708 (845s Big Mountain), 845s 709 (845s Big Mountain) | 2024-07-17 09:30 | 2024-07-18 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2024-07-17 10:00 | 2024-07-17 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 61s T1 (61s Lodgepole) | 2024-07-18 06:30 | 2024-07-18 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 834s 902 (834s Wesley Creek) | 2024-07-18 09:30 | 2024-07-19 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2024-07-18 10:00 | 2024-07-18 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ATCO | 763s 507C (763s Hanna) | 2024-07-18 20:49 | 2024-07-26 16:00 | N | N |  | Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 61s T2 (61s Lodgepole) | 2024-07-19 06:30 | 2024-07-19 17:30 | N | N |  | Transformer |  |  | For Information Only
TRANSALTA | 1063s Windrise | 2024-07-19 07:00 | 2024-07-22 18:00 | N | N |  | Station |  |  | Restricts Generation
ENMAX | 24.82L (SS-24 - SS-65), 24B138-24.82 (SS-24) | 2024-07-19 08:00 | 2024-07-19 12:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 24B138-24BT3 (SS-24) | 2024-07-19 12:00 | 2024-07-19 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2024-07-19 22:00 | 2024-07-20 08:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ATCO | 7L65 (710s Vermilion - 7LA65 tap), 7L129 (710s Vermilion - 7LA129 tap), 710s 704 (710s Vermilion), 710s 703 (710s Vermilion) | 2024-07-20 06:00 | 2024-07-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 29PL9-24 (29EDD-94 Voyageur - 29EDD-60 Inglis Island) | 2024-07-20 08:00 | 2024-07-28 18:00 | N | Y |  | Line |  |  | 240 kV
TRANSALTA, ALTALINK | 229s Glenwood, 225L (229s Glenwood - 385s Spring Coulee), 162L (229s Glenwood - 415s Drywood), 229s T1 (229s Glenwood), 229s T2 (229s Glenwood), 385s 225 (385s Spring Coulee), 415s 146E (415s Drywood), 229s 162 (229s Glenwood), 229s 17 (229s Glenwood), 229s 21 (229s Glenwood), 229s 225 (229s Glenwood) | 2024-07-20 08:30 | 2024-07-21 16:00 | N | N |  | Station, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2024-07-20 22:00 | 2024-07-21 07:59 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 718L (250p Bighorn Plant - 263s Strachan), 263s 718W (263s Strachan), 250p 718 (250p Bighorn Plant) | 2024-07-20 22:00 | 2024-07-21 06:00 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ENMAX | 9.80L (SS-9 - SS-31), 31.1C (SS-31), 31.1TR (SS-31), 31.2TR (SS-31), SW84 (SS-31), 31B138-9.80 (SS-31), 9B138-9.83 (SS-9) | 2024-07-21 08:00 | 2024-07-21 16:00 | N | N |  | Line, Shunts, Transformer, Switch, Circuit Breaker |  |  | Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16) | 2024-07-21 12:00 | 2024-08-04 16:00 | N | N |  | Line, Circuit Breaker |  | Work completed early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 229s T1 (229s Glenwood), 229s T2 (229s Glenwood) | 2024-07-21 16:00 | 2024-10-15 07:00 | N | N |  | Transformer |  |  | Pre-Condition, Prevents Normal Events
ENMAX | 2.82L (SS-2 - SS-5) | 2024-07-21 22:00 | 2024-07-22 08:00 | N | N |  | Line |  |  | Overload, Pre-Condition
ALTALINK | 172L (254s Coaldale - 370s North Lethbridge), 370s 172E (370s North Lethbridge), 254s 172W (254s Coaldale) | 2024-07-22 07:00 | 2024-07-25 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 535s 152 (535s Joffre) | 2024-07-22 07:30 | 2024-07-25 18:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 788s 703 (788s Hotchkiss), 7L63 (788s Hotchkiss - 7LA63 tap) | 2024-07-22 08:00 | 2024-08-03 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | 2.1TR (SS-2) | 2024-07-22 08:00 | 2024-07-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.2TR (SS-31) | 2024-07-22 08:00 | 2024-07-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 14.2TR (SS-14) | 2024-07-22 08:00 | 2024-07-25 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | T11 (Aurora) | 2024-07-22 08:00 | 2024-07-30 16:00 | N | Y |  | Transformer |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 5B138-5BT7 (SS-5) | 2024-07-22 08:00 | 2024-07-22 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 700s 702T (700s Bonnyville), 700s 710 (700s Bonnyville) | 2024-07-22 08:30 | 2024-07-25 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L131 (834s Wesley Creek - 905s Meikle), 834s 708 (834s Wesley Creek), 834s 710 (834s Wesley Creek) | 2024-07-22 09:00 | 2024-07-25 14:20 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
CODP | MCH1 Michichi Creek Generator Test | 2024-07-22 09:00 | 2024-08-29 12:00 | N | N |  | Unit
ATCO | 849s 901T (849s Joslyn Creek) | 2024-07-22 09:00 | 2024-07-26 17:00 | N | Y |  | Transformer |  |  | 240 kV
ATCO | 739s 601 (739s Edith Lake) | 2024-07-22 09:00 | 2024-07-24 17:00 | N | N |  | Circuit Breaker |  | Extended | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 813s 902T (813s Little Smoky), 813s 502TD (813s Little Smoky) | 2024-07-22 09:30 | 2024-07-27 14:00 | N | Y |  | Transformer, Switch |  | Returned Early | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson) | 2024-07-22 11:00 | 2024-07-26 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2024-07-22 12:12 | 2024-07-23 17:36 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 396s T2 (396s Pincher Creek) | 2024-07-22 13:30 | 2024-07-25 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 816s PDS13 (816s Petrolia), 816s P2401 (816s Petrolia), 816s P2406 (816s Petrolia) | 2024-07-23 07:00 | 2024-07-24 17:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2024-07-23 07:00 | 2024-07-23 10:00 | N | N |  | Transformer | No need to request SLD. Open point 'A' is on the 25 kV bus (not modelled) |  | For Information Only
ALTALINK | 754L (118s Canmore - 437s Baymag), 118s 754E (118s Canmore) | 2024-07-23 08:00 | 2024-07-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 6.80L (SS-6 - SS-35), 6B138-6.80 (SS-6) | 2024-07-23 08:00 | 2024-07-23 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-34 29PT-341 (29EDD-34), 29EDD-34 29-652-10301 (29EDD-34) | 2024-07-23 08:00 | 2024-07-23 20:00 | N | Y |  | Transformer, Circuit Breaker | Upgrade SEL330 Ground fault relay and Test for 29PT-340. | Other pressing emergency issues occurred. | 240 kV, For Information Only
ALTALINK | 606L (184s Petro-Canada Edmonton - 185s Bretville), 184s 606 (184s Petro-Canada Edmonton) | 2024-07-23 09:00 | 2024-07-23 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2024-07-23 10:01 | 2024-07-23 15:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2024-07-23 12:00 | 2024-07-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2024-07-23 15:00 | 2024-07-23 18:30 | N | N |  | Transformer | No need to request SLD. Open point 'A' is on the 25 kV bus (not modelled) |  | For Information Only
EPCOR | 72NW15 (Namao - Woodcroft), W723 (Woodcroft), N726 (Namao) | 2024-07-24 07:00 | 2024-07-25 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 24.81L (SS-24 - SS-31), 31B138-24.81 (SS-31) | 2024-07-24 08:00 | 2024-07-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 87s 652 (87s Gaetz) | 2024-07-24 08:00 | 2024-07-24 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive) | 2024-07-24 08:00 | 2024-07-30 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL9-25 (29EDD-94 Voyageur - 29EDD-61 Stony Island), 29EDD-61 29PT-653 (29EDD-61 Stony Island) | 2024-07-24 08:00 | 2024-07-31 16:40 | N | Y |  | Line, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 410s 552 (410s Josephburg) | 2024-07-24 08:30 | 2024-07-24 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 6L97 (735s Swan River - 739s Edith Lake), 739s 603 (739s Edith Lake), 735s 603 (735s Swan River) | 2024-07-24 09:00 | 2024-07-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 739L (14s Devon - 305s Acheson), 14s 739N (14s Devon) | 2024-07-24 16:12 | 2024-07-30 15:10 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 834s 502R (834s Wesley Creek) | 2024-07-24 20:00 | 2024-08-02 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2024-07-24 21:36 | 2024-07-25 16:00 | N | Y |  | Line |  |  | 240 kV, Overload
ALTALINK | 19s 69kV Bus (19S Wabamun), 352s T1 (352s Onoway), 124L (19s Wabamun - 2739s Wabamun), 123L (19s Wabamun - 352s Onoway), 133L (19s Wabamun - 234L tap) | 2024-07-25 06:00 | 2024-07-25 13:00 | N | N |  | Bus, Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS14 (816s Petrolia) | 2024-07-25 07:00 | 2024-07-26 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 14B138-14.83 (SS-14) | 2024-07-25 08:00 | 2024-07-25 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 87s 752 (87s Gaetz) | 2024-07-25 08:00 | 2024-07-25 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 11.83L (SS-162 - SS-11), 11B138-11.83 (SS-11) | 2024-07-25 12:01 | 2024-07-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 808L (171s Redwater - 808AL tap) | 2024-07-26 07:00 | 2024-07-26 17:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 826s 504R (826s Marguerite Lake) | 2024-07-26 10:00 | 2026-07-31 16:00 | N | N |  | Shunts
EPCOR | 987s GT1 (987s Clover Bar), 987s CGB1 (987s Clover Bar) | 2024-07-27 07:00 | 2024-07-27 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13B69-13.60 (SS-13), 27B69-13.60 (SS-27) | 2024-07-27 08:00 | 2024-07-27 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, CNRL | 859s 702T (859s Primrose) | 2024-07-27 12:00 | 2024-08-13 11:34 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29EDD-34 29PT-340 (29EDD-34), 29EDD-34 29-652-10201 (29EDD-34) | 2024-07-28 08:00 | 2024-07-28 17:00 | N | Y |  | Transformer, Circuit Breaker | Upgrade SEL330 Ground fault relay and Test for 29PT-340. | Other pressing emergency issues occurred. 29PT-340 returned early | 240 kV
ALTALINK | 238s T1 (238s Shell Harmattan) | 2024-07-28 08:00 | 2024-08-01 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5), 2MD138-2.82 (SS-2) | 2024-07-28 22:00 | 2024-07-30 08:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Overload, Pre-Condition
EPCOR | T3 (Rossdale) | 2024-07-29 07:00 | 2024-09-18 17:00 | N | N |  | Transformer |  | Work completed early. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 775L (276s Prentiss - 535s Joffre), 535s 6252 (535s Joffre), 535s 6352 (535s Joffre), 276s 775X (276s Prentiss), 535s 775X (535s Joffre) | 2024-07-29 07:30 | 2024-08-02 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ALTALINK, TRANSALTA | 64L (36s Three Sisters Plant - 35s Rundle Plant), 35s T3 (35s Rundle Plant), 35s T1 (35s Rundle Plant), 35s 3 (35s Rundle Plant), 35s 4 (35s Rundle Plant), 35s 64 (35s Rundle Plant), 36s 64L42 (36s Three Sisters Plant) | 2024-07-29 08:00 | 2024-07-29 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33), 41B138-33.83 (SS-41) | 2024-07-29 08:00 | 2024-07-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 54.81L (SS-54 - SS-65), 54B138-54.81 (SS-54) | 2024-07-29 08:00 | 2024-07-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s ACF21 (2029s Heathfield) | 2024-07-29 08:30 | 2024-07-30 12:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ENMAX | 11.1TR (SS-11) | 2024-07-29 08:30 | 2024-08-01 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 2015s 901T (2015s Yeo), 2015s 901 (2015s Yeo) | 2024-07-29 09:00 | 2024-08-02 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ATCO | 932s 901T (932s Pemukan) | 2024-07-29 09:00 | 2024-08-08 13:40 | N | Y |  | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 801s 901T (801s Anderson), 801s 704 (801s Anderson) | 2024-07-29 09:00 | 2024-08-01 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 813s 901 (813s Little Smoky) | 2024-07-29 09:30 | 2024-07-30 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 700s 703T (700s Bonnyville) | 2024-07-29 10:00 | 2024-08-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1140L (89s Ellerslie - 289s Saunders Lake) | 2024-07-29 11:00 | 2024-07-30 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 701T (801s Anderson), 801s 705 (801s Anderson), 801s 711 (801s Anderson), 801S 701TD (801s Anderson) | 2024-07-29 11:00 | 2024-08-01 15:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 1049L (59s Peigan - 138s Windy Flats), 59s 1152 (59s Peigan), 59s 1049 (59s Peigan), 138s 1049 (138s Windy Flats) | 2024-07-29 14:30 | 2024-07-30 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
SUNCOR | 29EDD-94 407T (29EDD-94 Voyageur), 29EDD-94 29-952-9705 (29EDD-94 Voyageur), 29EDD-94 29-952-9704 (29EDD-94 Voyageur), 29EDD-94 29PS-392 (29EDD-94 Voyageur), 29EDD-94 29PS-393 (29EDD-94 Voyageur), 29EDD-94 29PS-400 (29EDD-94 Voyageur) | 2024-07-30 08:00 | 2024-08-17 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ALTALINK | 14s 739N (14s Devon), 739L (14s Devon - 305s Acheson) | 2024-07-30 08:00 | 2024-07-30 15:10 | N | N |  | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | 41.84L (SS-41 - SS-54), 54B138-41.84 (SS-54), 41B138-41.84 (SS-41) | 2024-07-30 08:00 | 2024-07-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 194s T2 (194s South Red Deer) | 2024-07-30 08:00 | 2024-07-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 820L (254s Coaldale - 820AL tap), 254s 820 (254s Coaldale) | 2024-07-30 08:30 | 2024-07-30 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 283s C1 (283s Violet Grove) | 2024-07-30 09:00 | 2024-08-02 07:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 808s 702T (808s Procter & Gamble), 808s 702 (808s Procter & Gamble) | 2024-07-30 09:30 | 2024-07-30 15:10 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 9L45 (856s Kinosis - 2049s Kettle River) | 2024-07-30 10:00 | 2024-07-30 19:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 2029s ACF22 (2029s Heathfield) | 2024-07-30 12:01 | 2024-07-31 16:00 | N | Y |  | Shunts |  |  | Pre-Condition
ATCO | 6L15 (763s Hanna - 775s Sullivan Lake), 763s 602 (763s Hanna), 775s 601 (775s Sullivan Lake) | 2024-07-30 15:01 | 2024-07-30 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 820L (254s Coaldale - 820AL tap), 254s 820 (254s Coaldale) | 2024-07-30 17:03 | 2024-08-03 18:25 | N | N |  | Line, Circuit Breaker |  | Returned to service | Prevents Normal Events
ATCO, ALBIAN | 920s 902T (920s Jackpine), 920s 902 (920s Jackpine), 920s B1 (920s Jackpine) | 2024-07-30 17:25 | 2024-08-03 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
EPCOR | 987s T2 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s CDS31 (987s Clover Bar) | 2024-07-31 07:00 | 2024-08-02 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s GB1B (987s Clover Bar), 987s C1 (987s Clover Bar) | 2024-07-31 07:00 | 2024-07-31 17:00 | N | N |  | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK, BHE Canada | 120s 240kV Bus 1 (120s Picture Butte), MATL (120s Picture Butte - Montana), 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte), 120s 1152S (120s Picture Butte) | 2024-07-31 07:00 | 2024-07-31 19:00 | Y | Y |  | Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Limits ATC, Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 65B138-D85 (SS-65), 65B138-D84 (SS-65), 26B138-26.83 (SS-26) | 2024-07-31 08:00 | 2024-07-31 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 616L (59s Peigan - 616AL tap), 59s T1 (59s Peigan), 59s 616 (59s Peigan) | 2024-07-31 09:00 | 2024-07-31 14:15 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 813s 904 (813s Little Smoky) | 2024-07-31 09:30 | 2024-08-01 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2024-07-31 17:34 | 2024-08-03 10:00 | N | N |  | Line |  | Returned early | Prevents Normal Events
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-07-31 23:00 | 2024-08-01 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-08-01 03:00 | 2024-08-01 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
LOSC | CLD1 Lethbridge Solar Generator Test | 2024-08-01 08:00 | 2024-11-08 16:00 | N | N |  | Unit
ENMAX | 24.82L (SS-24 - SS-65), 65B138-D81 (SS-65), 65B138-D82 (SS-65), 24B138-24.82 (SS-24) | 2024-08-01 08:00 | 2024-08-01 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 20.82L (SS-20 - SS-21), 21B138-20.82 (SS-21), 20B138-20.82 (SS-20) | 2024-08-01 08:00 | 2024-08-01 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s ACF23 (2029s Heathfield) | 2024-08-01 08:30 | 2024-08-02 12:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ALTALINK | 283s 138kV Bus (283s Violet Grove), 836L (61s Lodgepole - 283s Violet Grove), 673L (131s Moon Lake - 283s Violet Grove), 283s T1 (283s Violet Grove), 61s 836N (61s Lodgepole), 131s 673 (131s Moon Lake) | 2024-08-02 06:30 | 2024-08-02 07:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 27B69-16.61 (SS-27), 27MD69-27.1TR (SS-27), SW64 (SS-27) | 2024-08-03 08:00 | 2024-08-04 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-65 260kV Bus 29PP-0048 (29EDD-65), 29EDD-65 29-952-4811 (29EDD-65), 29EDD-65 29-952-4821 (29EDD-65) | 2024-08-05 08:00 | 2024-08-17 18:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27), 27MD69-27.2TR (SS-27), SW65 (SS-27) | 2024-08-05 08:00 | 2024-08-06 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (EP Riverview), RW2405 (EP Riverview), RW2401 (EP Riverview), RWAB1 (EP Riverview) | 2024-08-06 07:00 | 2024-08-08 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, CLRS | 928s 180X (928s East Stavely), 180L (928s East Stavely - 180AL tap), 180AL (604s Granum - 180L tap), 180L (15s Fort Macleod - 180AL tap), 604s 152 (604s Granum), 604s 1 (604s Granum) | 2024-08-06 07:00 | 2024-08-06 17:00 | N | Y |  | Switch, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 775L (276s Prentiss - 535s Joffre), 535s 6252 (535s Joffre), 535s 6352 (535s Joffre), 276s 775X (276s Prentiss), 535s 775X (535s Joffre) | 2024-08-06 07:30 | 2024-08-08 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 1.6TR (SS-1) | 2024-08-06 08:00 | 2024-08-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B240-RB133 (SS-162) | 2024-08-06 08:00 | 2024-08-06 11:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO, CNRL | 859s 702T (859s Primrose), 859s 702 (859s Primrose), 859s 703 (859s Primrose) | 2024-08-06 08:00 | 2024-08-12 14:00 | N | N |  | Transformer, Circuit Breaker |  | returned early | For Information Only
ALTALINK, WINDYPWPL | 893AL (112s Windy Point - 893L tap), 112s Windy Point | 2024-08-06 08:00 | 2024-08-07 16:00 | N | Y |  | Line, Station |  |  | Restricts Generation
ENMAX | 47.2TR (SS-47) | 2024-08-06 08:00 | 2024-08-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 11.2TR (SS-11) | 2024-08-06 08:30 | 2024-08-09 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L128 (802s Michichi Creek - 7LA128 tap), 802s 704 (802s Michichi Creek) | 2024-08-06 08:30 | 2024-08-08 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload
ALTALINK | 171s T1 (171s Redwater) | 2024-08-06 09:00 | 2024-08-26 10:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L64 (779s Chinchaga River - 789s Keg River), 789s 701 (789s Keg River) | 2024-08-06 09:00 | 2024-08-14 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ATCO | 707s 702T (707s St. Paul), 707s 702 (707s St. Paul) | 2024-08-06 09:00 | 2024-08-08 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 1059L (38s East Edmonton - 1059AL tap), 1059L (EP 803s Lambton - 1059AL tap) | 2024-08-06 09:30 | 2024-08-29 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ATCO | 813s 905 (813s Little Smoky) | 2024-08-06 09:30 | 2024-08-07 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK, EPCOR | 1059L (EP 803s Lambton - 1059AL tap), 1059AL (52s East Industrial - 1059L tap), 1059L (38s East Edmonton - 1059AL tap), EP 803s L2401 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), 52s E2401 (52s East Industrial), 52s T1 (52s East Industrial) | 2024-08-06 09:30 | 2024-08-30 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 751s 701 (751s Hill) | 2024-08-06 10:00 | 2024-08-06 13:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 855s 701T (855s Hamburg) | 2024-08-06 10:00 | 2024-08-16 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 2075s ACF22 (2075s Newell), 2075s ACF23 (2075s Newell), 2075s ACF24 (2075s Newell) | 2024-08-06 10:00 | 2024-08-09 16:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition, Prevents Normal Events
ALTALINK | 83s C1 (83s Taber), 83s C2 (83s Taber) | 2024-08-06 11:00 | 2024-08-06 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 162B240-RB131 (SS-162) | 2024-08-06 11:00 | 2024-08-06 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 2015s 902T (2015s Yeo), 2015s 902 (2015s Yeo) | 2024-08-06 13:00 | 2024-08-09 17:00 | N | Y |  | Transformer, Circuit Breaker |  | outage re-instated | 240 kV
ATCO | 751s 702 (751s Hill) | 2024-08-06 13:01 | 2024-08-06 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 205s 252 (205s Castle Rock Ridge) | 2024-08-06 18:30 | 2024-08-08 15:16 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Restricts Generation
ENMAX | 162B138-RB94 (SS-162) | 2024-08-07 08:00 | 2024-08-08 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 489s 138kV Bus (489s Petro Canada Brazeau River), 828L (178s Cynthia - 489s Petro-Canada Brazeau River), 489s T1 (489s Petro Canada Brazeau River), 178s 828X (178s Cynthia), 489s 828E (489s Petro-Canada Brazeau River), 489s 16 (489s Petro-Canada Brazeau River) | 2024-08-07 08:30 | 2024-08-07 17:30 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 159s T2 (159s Colinton) | 2024-08-07 09:00 | 2024-08-07 12:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2024-08-07 09:00 | 2024-08-07 11:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 799s 786W (799s Coleman), 1CB2 (BCH Natal) | 2024-08-07 09:30 | 2024-08-08 17:00 | N | Y |  | Line, Circuit Breaker | WebOMS #: 16285993 |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2024-08-08 02:11 | 2024-08-08 17:00 | N | Y |  | Line |  |  | 240 kV
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive), 743s 603 (743s Sarah Lake) | 2024-08-08 08:00 | 2024-08-14 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 841L (477s Amoco West Pembina - 489s Petro-Canada Brazeau River), 489s T2 (489s Petro Canada Brazeau River), 477s 841X (477s Amoco West Pembina) | 2024-08-08 08:30 | 2024-08-08 17:30 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 751s 701C (751s Hill) | 2024-08-08 10:00 | 2024-08-08 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 42s 906N (42s Sarcee), 906L (17s Benalto - 42s Sarcee) | 2024-08-08 10:30 | 2024-08-08 15:30 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 526s C1 (526s Buffalo Creek), 526s 652 (526s Buffalo Creek) | 2024-08-08 13:00 | 2024-08-09 18:00 | N | N |  | Shunts, Circuit Breaker | Note: As per AltaLink, 526s652 breaker was removed from service on Aug 8 due to an alarm that was received. The issue was resolved on Aug 9 after their field techs responded. According to AltaLink's records AESO SC was notified of the cap bank being available and their records dont show breaker being unavailable on Aug 13/14. |  | Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton), 38s 3052 (38s East Edmonton) | 2024-08-09 07:30 | 2024-08-09 16:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5), 2MD138-2.82 (SS-2) | 2024-08-10 07:00 | 2024-11-10 10:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 11.3TR (SS-11) | 2024-08-11 08:30 | 2024-08-13 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, BPWF | 1097L (356s Milo  611s Amber), 611s T1 (611s Amber), 611s T2 (611s Amber), 356s 1097 (356s Milo), 611s 52-240-1 (611s Amber), 611s 52-240-2 (611s Amber), 356s 789 (356s Milo), 611s 89-B1 (611s Amber) | 2024-08-12 07:00 | 2024-08-20 13:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
EPCOR | 987s T1 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s CDS25 (987s Cloverbar) | 2024-08-12 07:00 | 2024-08-15 00:01 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Completed Early | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 535s T1 (535s Joffre) | 2024-08-12 07:30 | 2024-08-22 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 23.3TR (SS-23) | 2024-08-12 08:00 | 2024-08-20 16:00 | N | N |  | Transformer
ENMAX | 14.1TR (SS-14) | 2024-08-12 08:00 | 2024-08-15 16:00 | N | N |  | Transformer |  |  | For Information Only
REDDEER | 247s T1 (247s Piper Creek) | 2024-08-12 08:00 | 2024-08-16 11:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.7TR (SS-5) | 2024-08-12 08:00 | 2024-08-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 39.1TR (SS-39) | 2024-08-12 08:00 | 2024-08-17 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 28.1TR (SS-28) | 2024-08-12 08:00 | 2025-02-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2024-08-12 09:00 | 2024-08-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L146 (700s Bonnyville - 970s Bourque), 700s 704 (700s Bonnyville) | 2024-08-12 09:00 | 2024-08-16 17:30 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 813s 908 (813s Little Smoky) | 2024-08-12 09:30 | 2024-08-13 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2024-08-12 10:00 | 2024-08-15 17:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 706L (410s Josephburg - 706AL tap), 706L (54s Fort Saskatchewan - 706AL tap), 706AL (452s B.F. Goodrich Fort Saskatchewan - 706L tap), 452s T1 (452s B.F. Goodrich Fort Saskatchewan), 54s 706N (54s Fort Saskatchewan), 452s 10 (452s B.F. Goodrich Fort Saskatchewan), 706L72D (706AL tap), 706L72B (706AL tap), 452s 1 (452s B.F. Goodrich Fort Saskatchewan) | 2024-08-12 11:00 | 2024-08-15 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2024-08-12 13:30 | 2024-08-22 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 377s T1 (377s AML Hardisty) | 2024-08-12 14:30 | 2024-08-15 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 266s 1038L FSC2 (266s SC1), 266s 489 (266s SC1), 266s 589 (266s SC1) | 2024-08-13 08:00 | 2024-08-13 14:00 | N | Y |  | Shunts, Switch |  |  | 240 kV, Pre-Condition
ATCO | 786s 701T (786s High Level), 786s 505C (786s High Level), 786s 506C (786s High Level), 786s 701TCS (786s High Level) | 2024-08-13 08:30 | 2024-08-15 16:00 | N | N |  | Transformer, Shunts, Switch |  |  | Pre-Condition
ALTALINK | 103s 552 (103s Goose Lake) | 2024-08-13 08:30 | 2024-08-14 16:30 | N | Y |  | Circuit Breaker |  | Returned early. | 240 kV, Contingency Requires Mitigation
ALTALINK | 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2024-08-13 08:30 | 2024-08-13 12:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L19 (809s Louise Creek - 851s Morse River), 851s 702 (851s Morse River), 809s 706 (809s Louise Creek) | 2024-08-13 10:00 | 2024-08-13 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 562s 252 (562s Cypress) | 2024-08-13 11:00 | 2024-08-13 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L67 (824s Fieldgate - 851s Morse River), 851s 703 (851s Morse River), 824s 7L67D5 (824s Fieldgate) | 2024-08-13 12:01 | 2024-08-13 14:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), SW83 (SS-23), 2MD138-2.80 (SS-2) | 2024-08-14 08:00 | 2024-08-15 16:00 | N | N |  | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 531s T1 (531s Shell Schrader Creek) | 2024-08-14 08:00 | 2024-08-14 15:00 | N | N |  | Transformer |  |  | For Information Only
FORTIS | VNT1 Olds DER Gas Generator test | 2024-08-14 08:00 | 2024-08-18 17:00 | N | N |  | Unit
ATCO | 7L159 (770s Three Hills - 7L159 tap), 770s 704 (770s Three Hills) | 2024-08-14 08:00 | 2024-08-15 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 392s T2 (392s Black Diamond) | 2024-08-14 08:30 | 2024-08-14 16:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 11.4TR (SS-11) | 2024-08-14 08:30 | 2024-08-16 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 813s 701 (813s Little Smoky) | 2024-08-14 09:30 | 2024-08-15 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 822L (38s East Edmonton - 822AL tap), 822L (133s Stelco Edmonton - 822AL tap), 38s 822X (38s East Edmonton) | 2024-08-14 09:30 | 2024-08-14 15:30 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 562s 1152 (562s Cypress) | 2024-08-14 11:00 | 2024-08-14 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 1059L (38s East Edmonton - 1059AL tap), 1059L (EP 803s Lambton - 1059AL tap), 1059AL (52s East Industrial - 1059L tap), 38s 7552 (38s East Edmonton), 38s 7452 (38s East Edmonton) | 2024-08-15 07:00 | 2024-08-15 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 820s 507C1 (820s Hangingstone), 820s 507C2 (820s Hangingstone) | 2024-08-15 10:00 | 2024-08-15 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 14.1C (SS-14) | 2024-08-15 15:00 | 2024-08-22 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2024-08-17 07:15 | 2024-08-24 17:45 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 897L (38s East Edmonton - 45s Bretona), 38s 897 (38s East Edmonton), 45s 897 (45s Bretona) | 2024-08-17 07:30 | 2024-08-17 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake), 38s 780X (38s East Edmonton), 522s 780 (522s Cooking Lake) | 2024-08-17 12:31 | 2024-08-17 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 865L (38s East Edmonton - 216s Knightsbridge), 38s 865N (38s East Edmonton), 216s 865X (216s Knightsbridge) | 2024-08-18 07:30 | 2024-08-18 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 738L (38s East Edmonton - 738AL tap), 38s 738W (38s East Edmonton) | 2024-08-18 12:31 | 2024-08-18 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, OWF2 | 7L153 (609s Wheatland - 804s Wintering Hills), 804s 703 (804s Wintering Hills), 609s DS1 (609s Wheatland), 609s DS2 (609s Wheatland), 609s DS3 (609s Wheatland), 609s 101 (609s Wheatland), 609s 102 (609s Wheatland) | 2024-08-19 06:30 | 2024-08-23 15:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), T3 (EP Hardisty), H723 (EP Hardisty), H724 (EP Hardisty), HAB3 (EP Hardisty) | 2024-08-19 07:00 | 2024-08-21 20:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  | outage done early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 19s 240kV Bus A (19S Wabamun), 19s 240kV Transfer Bus (19S Wabamun) | 2024-08-19 07:00 | 2024-11-18 08:00 | N | Y |  | Bus |  |  | 240 kV, For Information Only
ALTALINK, EPCOR | 1239L (330p Genesee - 510s Sunnybrook), 330p 1205 (330p Genesee), 330p 1206 (330p Genesee) | 2024-08-19 07:00 | 2024-08-25 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 803s T1 (EP 803s Lambton) | 2024-08-19 07:00 | 2024-08-19 16:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 889L (535s Joffre - 536s Brookfield), 536s T1 (536s Brookfield), 535s 106 (535s Joffre), 536s 1 (536s Brookfield) | 2024-08-19 07:30 | 2024-08-22 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
SUNCOR | 29EDD-65 260kV Bus 29PP-0049 (29EDD-65), 29EDD-65 29-952-4813 (29EDD-65), 29EDD-65 29-952-4823 (29EDD-65) | 2024-08-19 08:00 | 2024-08-28 18:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2024-08-19 08:00 | 2024-08-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
Syncrude, AESO-SC | Mildred T2 (Syncrude Mildred Lake), 2345 (Syncrude Mildred Lake), G2-PSD-Load (Syncrude Mildred Lake) | 2024-08-19 08:00 | 2024-09-04 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
SUNCOR | 29EDD-94 29PP-98 260kV Bus (29EDD-94 Voyageur), 29EDD-94 406T (29EDD-94 Voyageur), 29EDD-94 29-952-9702 (29EDD-94 Voyageur), 29EDD-94 29-952-9703 (29EDD-94 Voyageur), 29EDD-94 29-952-9704 (29EDD-94 Voyageur), 29EDD-94 29-952-9709 (29EDD-94 Voyageur), 29EDD-94 29-952-9710 (29EDD-94 Voyageur), 29EDD-94 29PS-399 (29EDD-94 Voyageur), 29EDD-94 29PS-391 (29EDD-94 Voyageur), 29EDD-94 29PS-388 (29EDD-94 Voyageur), 29EDD-94 29PS-389 (29EDD-94 Voyageur), 29EDD-94 29PS-390 (29EDD-94 Voyageur), 29EDD-94 29PS-633 (29EDD-94 Voyageur), 29EDD-94 29PS-634 (29EDD-94 Voyageur), 29EDD-94 29PS-632 (29EDD-94 Voyageur), 29EDD-94 29PS-635 (29EDD-94 Voyageur) | 2024-08-19 08:00 | 2024-09-08 16:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 34.2TR (SS-34) | 2024-08-19 08:00 | 2024-08-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.8TR (SS-5) | 2024-08-19 08:00 | 2024-08-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 39.2TR (SS-39) | 2024-08-19 08:00 | 2024-08-22 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5) | 2024-08-19 08:00 | 2024-08-30 12:00 | N | N |  | Line |  |  | For Information Only
ATCO | 763s 507C (763s Hanna) | 2024-08-19 08:30 | 2024-08-20 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L48 (794s Valleyview - 7LA48 tap) | 2024-08-19 09:00 | 2024-08-23 11:00 | N | N |  | Line |  | Returned early | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 813s 704 (813s Little Smoky) | 2024-08-19 09:30 | 2024-08-20 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 796s 702T (796s Nipisi) | 2024-08-19 10:00 | 2024-08-22 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 535s 138kV Bus 2 (535s Joffre), 889L (535s Joffre - 536s Brookfield), 535s T1 (535s Joffre), 535s T3 (535s Joffre), 535s T5 (535s Joffre), 535s 6652 (535s Joffre), 535s 152 (535s Joffre), 535s 106 (535s Joffre), 535s 35 (535s Joffre), 535s 11 (535s Joffre), 535s 52 (535s Joffre) | 2024-08-19 10:30 | 2024-08-22 18:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 205s 452 (205s Castle Rock Ridge) | 2024-08-19 12:30 | 2024-08-20 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 83s T3 (83s Taber), 83s 64 (83s Taber) | 2024-08-19 12:30 | 2024-08-23 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 89s 952 (89s Ellerslie) | 2024-08-19 13:00 | 2024-08-22 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L159 (948s Heatburg - 7LA159 tap), 948s 704 (948s Heatburg) | 2024-08-19 13:00 | 2024-08-22 15:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 410s T1 (410s Josephburg) | 2024-08-19 13:30 | 2024-08-22 17:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 37s 82 (37s North Calder), 37s 88 (37s North Calder), 37s 87 (37s North Calder) | 2024-08-20 07:15 | 2024-08-31 16:45 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 995s T1 (995s Yarrow) | 2024-08-20 08:00 | 2024-08-20 17:00 | N | N |  | Transformer |  |  | For Information Only
BPWF | 611s T1 (611s Amber), 611s T2 (611s Amber) | 2024-08-20 08:00 | 2024-08-22 18:00 | N | Y |  | Transformer |  |  | For Information Only
SUNCOR | 29PL9-24 (29EDD-94 Voyageur - 29EDD-60 Inglis Island), 29EDD-60 29PT-702 (29EDD-60 Inglis Island), 29EDD-60 29PS-644 (29EDD-60 Inglis Island) | 2024-08-20 08:00 | 2024-09-01 18:00 | N | Y |  | Line, Transformer, Switch |  | Extended | 240 kV, Restricts Generation
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2024-08-20 08:00 | 2024-08-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L92 (BCH Cranbrook - BCH Selkirk) | 2024-08-20 09:00 | 2024-08-23 23:29 | Y | Y |  | Line | *FOR OC** 1. Enter TRMr+ = 466 MW in MARGO manual override 2. Check MARGO BC/MATL capability (ATC). The BC/MATL capability (ATC) = 99 MW (lowest number for the period of Aug 20-25, 2024 (Aug 21, 2024 HE1) 3. In order to show 0 MW on S&D. Using max MATL Import ATC: 310 MW (No Restriction )  15 MW (MATL TRM ) = 295 MW, so the BC import ATC becomes 99 MW  295 MW = -196 MW (enter 0, instead of a negative number). | Back Early | Limits ATC, 500 kV
ATCO | 834s 903 (834s Wesley Creek) | 2024-08-20 09:30 | 2024-08-21 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO, CNRL | 859s 702T (859s Primrose), 859s 703 (859s Primrose), 859s 702 (859s Primrose) | 2024-08-20 13:00 | 2024-08-23 18:00 | N | N |  | Transformer, Circuit Breaker |  | Done Early | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia), 58s 202X (58s Edson), 178s 202N (178s Cynthia) | 2024-08-21 07:15 | 2024-08-23 17:45 | N | N |  | Line, Circuit Breaker |  | Back Early | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive), 743s 603 (743s Sarah Lake) | 2024-08-21 08:00 | 2024-08-28 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 23.4TR (SS-23) | 2024-08-21 08:00 | 2024-08-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 22.1TR (SS-22) | 2024-08-21 08:00 | 2024-08-22 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 813s 707 (813s Little Smoky) | 2024-08-21 09:30 | 2024-08-22 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 74s 23.80W (74s Janet), 23.4TR (SS-23), 23B138-23.80 (SS-23), SW84 (SS-23), 23MD138-23.4TR (SS-23) | 2024-08-22 08:00 | 2024-08-23 16:00 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 834s 904 (834s Wesley Creek) | 2024-08-22 09:30 | 2024-08-23 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 820s 702 (820s Hangingstone), 7L97 (820s Hangingstone - 7LA97 tap) | 2024-08-22 10:00 | 2024-08-23 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L81 (791s Rainbow Lake - BCH Harvest Energy FNC Tap) | 2024-08-23 11:00 | 2024-08-23 15:00 | N | Y |  | Line |  |  | Restricts Generation, Affects Cranking Path
ALTALINK | 157s C1 (157s Lac La Biche) | 2024-08-23 13:45 | 2026-06-30 14:29 | N | N |  | Shunts |  |  | Pre-Condition
EPCOR | 330P SST3 (330P Genesee), 330p 801 (330p Genesee) | 2024-08-24 07:00 | 2024-08-25 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BPWF | BPW1 Buffalo Plains Generator Test | 2024-08-24 08:00 | 2025-02-25 16:00 | N | N |  | Unit
EPCOR | T4 (Poundmaker), PM2403 (Poundmaker), PM2402 (Poundmaker), PM721 (Poundmaker), 72PM25 (Poundmaker - Meadowlark), PMAB4 (Poundmaker), M726 (Meadowlark) | 2024-08-26 07:00 | 2024-08-30 21:00 | N | Y |  | Transformer, Circuit Breaker, Line, Switch |  | Back Early | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2024-08-26 07:00 | 2024-08-28 18:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 665s D2403 (665s Dome) | 2024-08-26 07:00 | 2024-08-26 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK, TRANSALTA | 876L (179s Gleichen - 253s Blackie), 179s 876 (179s Gleichen), 253s 876 (253s Blackie) | 2024-08-26 07:15 | 2024-08-28 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 535s T5 (535s Joffre) | 2024-08-26 07:30 | 2024-08-29 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162.3TR (SS-162) | 2024-08-26 08:00 | 2024-08-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.1TR (SS-9) | 2024-08-26 08:00 | 2024-08-27 16:00 | N | N |  | Transformer |  |  | For Information Only
REDDEER | 194s T2 (194s South Red Deer) | 2024-08-26 08:00 | 2024-08-29 09:00 | N | N |  | Transformer |  | Outage returned early. End Time updated to reflect this. | For Information Only
ENMAX | 31.3TR (SS-31) | 2024-08-26 08:00 | 2024-08-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 8B138-5A0 (SS-8), 8.3TR (SS-8), 8.4TR (SS-8), 8B138-4A0 (SS-8), 4A02 (SS-8), 4A01 (SS-8), 5A1 (SS-8), 4A10 (SS-8) | 2024-08-26 08:00 | 2024-10-03 11:30 | N | N |  | Circuit Breaker, Transformer, Switch |  | Work completed and back in service . | Contingency Requires Mitigation
ENMAX | 22.2TR (SS-22) | 2024-08-26 08:00 | 2024-08-27 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 710s 703T (710s Vermilion), 710s 705 (710s Vermilion) | 2024-08-26 08:30 | 2024-08-27 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake), 715s 702 (715s Leming Lake) | 2024-08-26 08:30 | 2024-08-27 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer), 171s T1 (171s Redwater), 171s 138kV Bus (171s Redwater), 171s 735X (171s Redwater), 171s 1 (171s Redwater), 233s 735N (233s Beamer) | 2024-08-26 09:00 | 2024-08-30 15:00 | N | N |  | Line, Transformer, Bus, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 813s 709 (813s Little Smoky) | 2024-08-26 09:30 | 2024-08-26 15:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7L159 (948s Heatburg - 7LA159 tap), 948s 704 (948s Heatburg) | 2024-08-26 11:00 | 2024-08-28 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 676L (244s Bowmanton - 523s Bullshead), 244s 2152 (244s Bowmanton), 244s 2252 (244s Bowmanton), 523s 676 (523s Bullshead), 244s 676 (244s Bowmanton) | 2024-08-26 11:00 | 2024-09-06 11:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 180L (15s Fort Macleod - 180AL tap), 15s 180N (15s Fort Macleod) | 2024-08-26 12:00 | 2024-08-26 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 523s T1 (523s Bullshead) | 2024-08-26 12:30 | 2024-08-28 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 92s T1 (92s Viscount) | 2024-08-26 12:30 | 2024-08-29 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 28s 5 (28s West Brooks) | 2024-08-26 12:30 | 2024-08-28 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow), 347s 720X (347s AML Fox Creek), 397s 720N (397s Benbow) | 2024-08-26 12:30 | 2024-08-26 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 32B138-32BT5 (SS-32) | 2024-08-27 07:00 | 2024-08-29 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 264s 240kV Bus 1 (264s Elkwater), 264s 452 (264s Elkwater) | 2024-08-27 07:30 | 2024-08-28 11:30 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 15s 452 (15s Fort Macleod) | 2024-08-27 07:30 | 2024-08-27 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2024-08-27 08:00 | 2024-08-27 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 562s 1052 (562s Cypress) | 2024-08-27 08:30 | 2024-08-28 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 347s 199W (347s AML Fox Creek), 199L (347s AML Fox Creek - 741s ATC Fox Creek) | 2024-08-27 08:30 | 2024-08-27 12:30 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | ATC 793s 701 (ATC 793s West Peace River), 7L51 (ATC 793s West Peace River - 927s Buchanan Creek), 927s 7L51D4 (927s Buchanan Creek) | 2024-08-27 09:30 | 2024-08-28 17:30 | N | Y |  | Circuit Breaker, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 244s C3 (244s Bowmanton) | 2024-08-27 10:00 | 2025-01-20 08:00 | N | Y |  | Shunts |  |  | For Information Only
ALTALINK | 244s C2 (244s Bowmanton) | 2024-08-27 10:00 | 2025-01-20 08:00 | N | Y |  | Shunts |  |  | For Information Only
ATCO | 9L39 (925s Green Stocking - 934s Blackfly), 925s 901T (925s Green Stocking), 925s 9L39D2 (925s Green Stocking) | 2024-08-27 10:00 | 2024-08-29 16:00 | N | Y |  | Line, Transformer, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 244s C1 (244s Bowmanton) | 2024-08-27 10:00 | 2025-01-20 08:00 | N | Y |  | Shunts |  |  | For Information Only
ENMAX | 3.4TR (SS-3) | 2024-08-27 12:00 | 2024-08-27 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 463L (15s Fort Macleod - 463AL tap), 15s 463 (15s Fort Macleod) | 2024-08-27 12:30 | 2024-08-27 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 347s 199E (347s AML Fox Creek), 199L (347s AML Fox Creek - 199AL tap) | 2024-08-27 13:00 | 2024-08-27 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ATCO | 2075s 922 (2075s Newell) | 2024-08-27 14:05 | 2024-08-28 11:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 250p 22 (250p Bighorn Plant), 250p 2 (250p Bighorn Plant) | 2024-08-27 23:00 | 2024-08-29 07:00 | N | Y |  | Switch, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 718L (250p Bighorn Plant - 263s Strachan), 263s 718W (263s Strachan), 250p 718 (250p Bighorn Plant) | 2024-08-28 07:00 | 2024-08-29 05:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant), 250p 1 (250p Bighorn Plant) | 2024-08-28 07:00 | 2024-08-29 07:00 | N | Y |  | Switch, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial), 268s 797 (268s Whitecourt), 364s 797 (364s Whitecourt Industrial) | 2024-08-28 08:00 | 2024-08-28 12:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20), SW83 (SS-20) | 2024-08-28 08:00 | 2024-08-29 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.3TR (SS-22) | 2024-08-28 08:00 | 2024-08-30 14:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 27.1TR (SS-27) | 2024-08-28 08:00 | 2024-08-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 54.1TR (SS-54) | 2024-08-28 08:00 | 2024-08-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake), 715s 703 (715s Leming Lake), 717s 702 (717s Ethel Lake) | 2024-08-28 08:30 | 2024-08-29 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 405s C1 (405s Waupisoo) | 2024-08-28 08:30 | 2024-08-28 11:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 770s 506C (770s Three Hills) | 2024-08-28 09:00 | 2024-08-29 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 813s 712 (813s Little Smoky) | 2024-08-28 09:30 | 2024-08-28 13:30 | N | N |  | Circuit Breaker |  | Returned early on Aug 28. End Date changed in record. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 405s C2 (405s Waupisoo) | 2024-08-28 11:00 | 2024-08-29 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 264s 240kV Bus 2 (264s Elkwater), 264s 352 (264s Elkwater) | 2024-08-28 12:00 | 2024-08-29 17:30 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK, NRGREEN | 199L (347s AML Fox Creek - 199AL tap), 199L (268s Whitecourt - 199AL tap), 199AL (259s Chickadee Creek - 199L tap), 347s 199E (347s AML Fox Creek), 268s 199N (268s Whitecourt), 259s 5200 (259s Chickadee Creek), 259s 5100 (259s Chickadee Creek) | 2024-08-28 13:01 | 2024-08-29 13:00 | N | Y |  | Line, Circuit Breaker, Switch |  | Outage returned early. End Date updated to reflect this. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 602 (739s Edith Lake), 854S 601TD (854s Swan Dive) | 2024-08-28 17:01 | 2024-08-29 14:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, Lethbridge | 725L (15s Fort MacLeod - 725BL tap), 725L (674s Bowron - 725BL tap), 725BL (240s McBride Lake - 725L tap), 15s 725 (15s Fort Macleod), 674s 725W (674s Bowron) | 2024-08-29 07:00 | 2024-08-29 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2024-08-29 07:00 | 2024-08-31 18:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-65 29-952-4812 (29EDD-65) | 2024-08-29 08:00 | 2024-09-01 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L85 (804s Wintering Hills - 7LA85 tap), 804s 702 (804s Wintering Hills) | 2024-08-29 08:00 | 2024-08-29 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 27.2TR (SS-27) | 2024-08-29 08:00 | 2024-08-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 237s 552 (237s Foothills) | 2024-08-29 08:30 | 2024-08-29 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7L82 (788s Hotchkiss - 855s Hamburg), 788s 705 (788s Hotchkiss) | 2024-08-29 09:30 | 2024-08-29 17:30 | N | Y |  | Line, Circuit Breaker |  | Outage returned early. End Date updated to reflect this. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 805s J2408 (EP 805s Jasper), 805s C1 (805s Jasper) | 2024-08-29 11:16 | 2024-12-05 15:30 | N | Y |  | Circuit Breaker, Shunts |  |  | Pre-Condition
RESC | FRM1 Forty Mile Wind Generator Test | 2024-08-30 08:00 | 2025-04-17 16:00 | N | N |  | Unit
CapitalPower | GNR1 Genesee Repower 1 Generator Test | 2024-08-31 | 2024-11-01 23:00 | N | N |  | Unit
ENMAX | 32.3TR (SS-32) | 2024-08-31 08:00 | 2024-08-31 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.82L (SS-3 - SS-8) | 2024-08-31 08:00 | 2024-08-31 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 23.3TR (SS-23) | 2024-09-01 08:00 | 2024-09-02 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2024-09-01 09:00 | 2024-09-01 17:00 | Y | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2024-09-01 09:00 | 2024-09-01 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 9L16 (755s Cordel - 972s Tinchebray) | 2024-09-01 10:00 | 2024-09-02 16:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 15.1TR (SS-15), 15B8-15.1TR (SS-15) | 2024-09-02 08:00 | 2024-09-04 11:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 171s T2 (171s Redwater) | 2024-09-03 07:00 | 2024-09-25 12:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR, ALTALINK | EP 803s T3 (EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton), 72LS24 (EP 803s Lambton - Strathcona), 72LH8 (EP 803s Lambton - EP Hardisty) | 2024-09-03 07:00 | 2024-09-07 17:00 | N | Y |  | Transformer, Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | M723 (Meadowlark), M724 (Meadowlark), T3 (Meadowlark), MAB3 (Meadowlark) | 2024-09-03 07:00 | 2024-09-08 17:00 | N | N |  | Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft), N726 (Namao), W723 (Woodcroft), W725 (Woodcroft), T2 (Woodcroft), WAB2 (Woodcroft), W722 (Woodcroft) | 2024-09-03 07:00 | 2024-09-17 11:00 | N | N |  | Line, Circuit Breaker, Transformer, Switch |  | outage complete | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 756L (87s Gaetz - 535s Joffre), 535s 5752 (535s Joffre), 535s 5852 (535s Joffre), 535s 756X (535s Joffre) | 2024-09-03 07:30 | 2024-09-06 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 37s 82 (37s North Calder) | 2024-09-03 07:30 | 2024-09-13 16:30 | N | Y |  | Circuit Breaker |  | Outage extended until September 13. | 240 kV, Contingency Requires Mitigation
ENMAX | 13.3TR (SS-13) | 2024-09-03 08:00 | 2024-09-04 16:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29PL9-4 (29EDD-1 Millennium - 29EDD-3), 29EDD-1 29EDD1s252 (29EDD-1 Millennium), 29EDD-1 29EDD1s352 (29EDD-1 Millennium) | 2024-09-03 08:00 | 2024-09-08 12:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation
SUNCOR | 29EDD-65 29-952-4822 (29EDD-65) | 2024-09-03 08:00 | 2024-09-06 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2024-09-03 08:00 | 2024-09-06 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28), SW83 (SS-28) | 2024-09-03 08:00 | 2024-09-03 13:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2024-09-03 08:00 | 2024-09-06 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO, ALTALINK | 9L960 (13s Deerland - 825s Whitefish Lake), 825s 901 (825s Whitefish Lake), 825s 902 (825s Whitefish Lake), 825s 902A (825s Whitefish Lake), 825s 901A (825s Whitefish Lake) | 2024-09-03 08:30 | 2024-09-05 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2024-09-03 09:00 | 2024-09-06 17:00 | N | Y |  | Line |  |  | Pre-Condition
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2024-09-03 09:00 | 2024-09-13 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 813s 713 (813s Little Smoky) | 2024-09-03 09:30 | 2024-09-04 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 733L (179s Gleichen - 428s Namaka), 428s 733X (428s Namaka) | 2024-09-03 12:30 | 2024-09-04 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Pre-Condition
ATCO | 7L137 (768s Rowley - 770s Three Hills), 768s 703 (768s Rowley), 770s 702 (770s Three Hills) | 2024-09-03 13:00 | 2024-09-05 14:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28B138-28.80 (SS-28) | 2024-09-03 13:01 | 2024-09-03 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 58s C1 (58s Edson), 58s 35 (58s Edson) | 2024-09-03 13:30 | 2024-09-03 18:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 367s T2 (367S Harry Smith) | 2024-09-03 14:00 | 2024-09-05 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar), 38s 7252 (38s East Edmonton), 38s 7152 (38s East Edmonton) | 2024-09-04 07:00 | 2024-09-04 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 434s T1 (434s East Stony Plain) | 2024-09-04 07:00 | 2024-09-04 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 349s T1 (349s Stavely), 349s 20 (349s Stavely), 349s 197 (349s Stavely) | 2024-09-04 07:30 | 2024-09-04 17:30 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 215L (286s Yasa - 215AL tap), 286s 215 (286s Yasa) | 2024-09-04 07:30 | 2024-09-04 12:15 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 39s 152 (39s Bickerdike) | 2024-09-04 08:00 | 2024-09-04 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23), 23B138-2.80 (SS-23), 23MD138-23.3TR (SS-23) | 2024-09-04 08:00 | 2024-09-04 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 77s 40 (77s Sagitawah) | 2024-09-04 09:00 | 2024-09-09 12:29 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 834s 704 (834s Wesley Creek) | 2024-09-04 09:30 | 2024-09-04 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 601L (230s Wardlow - 275s Jenner), 230s T1 (230s Wardlow), 275s T3 (275s Jenner), 275s 83 (275s Jenner), 275s 601 (275s Jenner), 230s 601 (230s Wardlow) | 2024-09-04 09:30 | 2024-09-04 17:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ATCO | 797s 701T (797s Kemp River) | 2024-09-04 09:30 | 2024-09-20 10:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 23MD138-23.4TR (SS-23), 23B138-23.80 (SS-23) | 2024-09-04 12:00 | 2024-09-04 18:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 23MD138-23.4TR (SS-23), 23B138-23.80 (SS-23) | 2024-09-04 12:00 | 2024-09-04 18:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 286s 352 (286s Yasa) | 2024-09-04 12:16 | 2024-09-04 16:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 39s 852 (39s Bickerdike) | 2024-09-04 13:00 | 2024-09-04 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 650s 224 (650s Hansman Lake) | 2024-09-05 06:00 | 2024-09-13 12:00 | N | Y |  | Switch |  |  | For Information Only, Pre-Condition
ATCO, ALTALINK | 7L224 (650s Hansman Lake - 774s Monitor), 650s 1752 (650s Hansman Lake), 774s 701 (774s Monitor) | 2024-09-05 06:00 | 2024-09-13 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 38s T2 (38s East Edmonton) | 2024-09-05 07:00 | 2024-09-05 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 38s 761N (38s East Edmonton) | 2024-09-05 07:00 | 2024-09-05 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Overload
ALTALINK | 605L (185s Bretville - 286s Yasa), 286s 605 (286s Yasa), 185s 605 (185s Bretville) | 2024-09-05 07:30 | 2024-09-05 16:30 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22BT8 (SS-22) | 2024-09-05 08:00 | 2024-09-05 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B138-D83 (SS-65) | 2024-09-05 08:00 | 2024-09-05 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 102s 6452 (102s Langdon) | 2024-09-05 08:30 | 2024-09-05 17:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 15.2TR (SS-15), 15B8-15.2TR (SS-15) | 2024-09-05 08:30 | 2024-09-08 14:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 102s 552 (102s Langdon) | 2024-09-05 10:30 | 2024-09-05 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 205s 152 (205s Castle Rock Ridge) | 2024-09-05 10:30 | 2024-09-05 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Restricts Generation
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 602 (739s Edith Lake), 854S 601TD (854s Swan Dive) | 2024-09-06 08:00 | 2024-09-09 19:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20), SW83 (SS-20), 20MD138-20.1TR (SS-20) | 2024-09-06 08:00 | 2024-09-06 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 20.82L (SS-20 - SS-21), 20.3TR (SS-20), 20B138-20.82 (SS-20), 20MD138-20.3TR (SS-20), SW84 (SS-20) | 2024-09-06 12:00 | 2024-09-06 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 781L (71s Lamoureux - 172s Sherritt), 172s 781W (172s Sherritt) | 2024-09-07 07:00 | 2024-09-07 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 32.3TR (SS-32) | 2024-09-07 08:00 | 2024-09-08 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 9L43 (874s McKay River - 888s Dover), 874s 89-1 (874s McKay River), 874s 89-2 (874s McKay River), 874s 89-3 (874s McKay River), 874s 89-4 (874s McKay River), 874s 52-1 (874s McKay River), 874s 52-T2 (874s McKay River), 874s 52-T3 (874s McKay River) | 2024-09-07 10:00 | 2024-09-14 10:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK, EPCOR | 38s T4 (38s East Edmonton), 38s 240kV Bus 2 (38s East Edmonton), 38s 18 (38s East Edmonton), 38s 7452 (38s East Edmonton), 38s 7352 (38s East Edmonton), 38s 12 (38s East Edmonton), 1059L (38s East Edmonton - 1059AL tap) | 2024-09-08 07:00 | 2024-09-08 12:30 | N | Y |  | Transformer, Bus, Circuit Breaker, Switch, Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 254s T1 (254s Coaldale), 254s 20 (254s Coaldale) | 2024-09-08 11:30 | 2024-09-12 17:30 | N | Y |  | Transformer, Switch |  |  | Restricts Generation
ALTALINK | 326s 240kV Bus 2 (326s Murray lake), 326s 452 (326s Murray Lake) | 2024-09-09 07:00 | 2024-09-11 17:30 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s Victoria T5 (EP 511s Victoria), EP 511s V2401 (EP 511s Victoria), 557s CD2405 (557s Castle Downs), 557s CD2406 (557s Castle Downs), EP 511s VDS25 (EP 511s Victoria) | 2024-09-09 07:00 | 2024-09-16 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  | Done early | Creates Radial Feeds, Firm Load Loss
ALTALINK | 790L (434s Stony Plain - 790AL tap), 434s 790 (434s Stony Plain) | 2024-09-09 07:00 | 2024-09-09 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 4R T1 (A.T. Plastics 4R), ATP1381 (A.T. Plastics 4Rs) | 2024-09-09 07:00 | 2024-09-20 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 755L (247s Piper Creek - 535s Joffre), 535s 5552 (535s Joffre), 535s 5452 (535s Joffre), 535s 755 (535s Joffre), 247s 755 (247s Piper Creek) | 2024-09-09 07:30 | 2024-09-13 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 7L69 (731s Elmworth - 815s Goodfare), 731s 702 (731s Elmworth), 815s 704 (815s Goodfare) | 2024-09-09 08:00 | 2024-09-12 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31) | 2024-09-09 08:00 | 2024-09-09 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 1B138-10A0 (SS-1) | 2024-09-09 08:00 | 2024-09-09 12:00 | N | N |  | Circuit Breaker |  |  | Prevents Normal Events
ATCO, ALTALINK | 9L961 (13s Deerland - 825s Whitefish Lake), 825s 903 (825s Whitefish Lake), 825s 904 (825s Whitefish Lake) | 2024-09-09 08:30 | 2024-09-13 17:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ATCO | 718s 702 (718s Parsons Creek), 7L71 (718s Parsons Creek - 2082s Dog Rib) | 2024-09-09 09:00 | 2024-09-11 16:00 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 867s T1 (867s Sundance Blow-Down), 234L (310p Sundance - 505L tap), 505L (234L tap - 505L tap) | 2024-09-09 09:00 | 2024-09-18 17:00 | N | N |  | Transformer, Line |  |  | For Information Only
ALTALINK | 502s T1 (502s Shell Waterton (#2)), 502s T2 (502s Shell Waterton (#2)) | 2024-09-09 09:00 | 2024-09-12 15:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 774s 702T (774s Monitor), 774s 702 (774s Monitor), 774s Protection & Control (774s Monitor) | 2024-09-09 09:00 | 2024-09-10 14:24 | N | N |  | Transformer, Circuit Breaker, Terminal Equipment |  |  | For Information Only
ATCO | 845s 705C (845s Big Mountain), 845s 701 (845s Big Mountain), 845s 707 (845s Big Mountain) | 2024-09-09 09:30 | 2024-09-09 13:33 | N | N |  | Shunts, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Prevents Normal Events
ENMAX | 1B138-9A0 (SS-1) | 2024-09-09 12:01 | 2024-09-09 16:00 | N | N |  | Circuit Breaker |  |  | Prevents Normal Events
ALTALINK | 370s T5 (370s North Lethbridge), 370s 2252 (370s North Lethbridge) | 2024-09-09 12:30 | 2024-09-12 14:27 | N | Y |  | Transformer, Circuit Breaker |  | Returned a day early on September 12. | 240 kV
ALTALINK | 77s 40 (77s Sagitawah) | 2024-09-09 12:30 | 2024-09-12 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L137 (768s Rowley - 770s Three Hills), 768s 703 (768s Rowley), 770s 702 (770s Three Hills) | 2024-09-09 13:00 | 2024-09-11 12:22 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 212s T1 (212s N.E.Lacombe), 461L (198s Blackfalds - 212s N.E. Lacombe), 423L (212s N.E. Lacombe - 332s Ellis), 212s 461 (212s N.E. Lacombe), 212s 423 (212s N.E. Lacombe), 212s 189 (212s N.E. Lacombe) | 2024-09-09 13:00 | 2024-09-13 17:00 | N | N |  | Transformer, Line, Circuit Breaker, Switch | Note: Requested AML to send the capital maintenance project details to the OPTRA team. |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 908L (38s East Edmonton - 908AL tap), 908L (89s Ellerslie - 908AL tap), 908AL (52S East Industrial - 908L tap), 38s 7652 (38s East Edmonton), 38s 7552 (38s East Edmonton), 38s 908W (38s East Edmonton), 52s E2402 (52s East Industrial), 52s EDS2 (52s East Industrial) | 2024-09-10 07:00 | 2024-09-10 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 344s T2 (344s Warner), 67s 508X (67s Stirling), 344s 1 (344s Warner), 344s 16 (344s Warner) | 2024-09-10 07:00 | 2024-09-11 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 523s 880 (523s Bullshead), 321s 880 (321s Al Rothbauer) | 2024-09-10 07:00 | 2024-09-18 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 818s C3 (818s Winefred) | 2024-09-10 08:00 | 2024-09-10 13:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive), 743s 603 (743s Sarah Lake) | 2024-09-10 08:00 | 2024-09-12 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 1B138-2A0 (SS-1) | 2024-09-10 08:00 | 2024-09-10 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 818s C1 (818s Winefred) | 2024-09-10 08:00 | 2024-09-10 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 21.61L (SS-21 - SS-34), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21B69-21.61 (SS-21), 21B69-15.60 (SS-21), 34B69-21.61 (SS-34) | 2024-09-10 08:00 | 2024-09-10 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 844s 701T (844s AEC Mill) | 2024-09-10 08:30 | 2024-09-11 15:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 834s 909R (834s Wesley Creek) | 2024-09-10 09:30 | 2024-09-11 12:22 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 172s T3 (172s Sherritt Gordon), 172s 73 (172s Sherritt) | 2024-09-10 09:30 | 2024-09-14 16:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 1B138-1A0 (SS-1) | 2024-09-10 12:01 | 2024-09-10 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 818s C2 (818s Winefred) | 2024-09-10 13:01 | 2024-09-10 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 946L (38s East Edmonton - 89s Ellerslie), 38s 7252 (38s East Edmonton), 38s 7352 (38s East Edmonton), 38s 946W (38s East Edmonton) | 2024-09-11 07:00 | 2024-09-11 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 223s T1 (223s Strome), 223s 43 (223s Strome) | 2024-09-11 07:30 | 2024-09-12 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 32.2TR (SS-32), 32.1TR (SS-32), 26.81L (SS-26 - SS-32), 32B138-32BT5 (SS-32) | 2024-09-11 08:00 | 2024-09-11 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1B138-4A0 (SS-1) | 2024-09-11 08:00 | 2024-09-11 12:00 | N | N |  | Circuit Breaker |  |  | Prevents Normal Events
ENMAX | 3.4TR (SS-3) | 2024-09-11 08:00 | 2024-09-11 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1B138-3A0 (SS-1) | 2024-09-11 12:00 | 2024-09-11 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition, Prevents Normal Events
ENMAX | 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27) | 2024-09-11 12:00 | 2024-09-11 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis), 766s 902 (766s Nevis) | 2024-09-11 13:00 | 2024-09-11 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Affects Cranking Path
ATCO | 7L47 (718s Parsons Creek - 848s Ruth Lake) | 2024-09-11 16:01 | 2024-09-11 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L71 (848s Ruth Lake - 2082s Dog Rib), 848s 701 (848s Ruth Lake) | 2024-09-11 16:01 | 2024-09-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 344s T2 (344s Warner) | 2024-09-11 18:00 | 2024-10-21 07:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-09-11 23:00 | 2024-09-12 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-09-12 03:00 | 2024-09-12 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 9.3TR (SS-9), 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.2TR (SS-9) | 2024-09-12 08:00 | 2024-09-12 18:00 | N | N |  | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L29 (791s Rainbow Lake - 850s Rainbow Co-Gen), 791s 705 (791s Rainbow Lake), 850s 701T (850s Rainbow Cogen), 850s 702T (850s Rainbow Cogen) | 2024-09-12 09:00 | 2024-09-22 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Restricts Generation, Affects Cranking Path
ENMAX | 13.60L (SS-13 - SS-27), 27B69-13.60 (SS-27) | 2024-09-12 12:00 | 2024-09-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder), 37s 76 (37s North Calder) | 2024-09-12 16:00 | 2024-09-12 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 938L (77s Sagitawah - 809s Louise Creek) | 2024-09-12 16:30 | 2024-09-12 17:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Overload
ALTALINK | 77s 552 (77s Sagitawah) | 2024-09-13 07:30 | 2024-09-16 14:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 15.62L (SS-15 - SS-16) | 2024-09-13 08:00 | 2024-09-13 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.5TR (SS-1) | 2024-09-13 08:00 | 2024-09-13 10:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 951s 920C (951s Thickwood) | 2024-09-13 10:00 | 2024-09-13 16:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34) | 2024-09-13 10:00 | 2024-09-13 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.6TR (SS-1) | 2024-09-13 10:00 | 2024-09-13 11:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.7TR (SS-1) | 2024-09-13 11:00 | 2024-09-13 13:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.8TR (SS-1) | 2024-09-13 13:00 | 2024-09-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s 138kV Bus 2 (38s East Edmonton), 761L (38s East Edmonton - 71s Lamoureux), 215L (38s East Edmonton - 215AL tap), 731L (38s East Edmonton - 746L tap), 38s T3 (38s East Edmonton), 38s 75 (38s East Edmonton), 38s 4252 (38s East Edmonton), 38s 62 (38s East Edmonton), 38s 4152 (38s East Edmonton), 38s 761N (38s East Edmonton), 38s 731E (38s East Edmonton), 38s 215N (38s East Edmonton) | 2024-09-13 16:00 | 2024-09-15 18:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 95s T2 (95s Imperial Oil Edmonton), 38s 737N (38s East Edmonton), 95s 8 (95s Imperial Oil Edmonton) | 2024-09-13 16:00 | 2024-09-15 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 38.1TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 38B138-38.83 (SS-38), 38B138-38.1CAP (SS-38) | 2024-09-14 08:00 | 2024-09-14 12:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.3TR (SS-32) | 2024-09-14 08:00 | 2024-09-15 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 38B138-37.81 (SS-38), 38B138-38.1CAP (SS-38) | 2024-09-14 12:01 | 2024-09-14 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330P GT1 (330p Genesee), 330p 1202 (330p Genesee), 330p 1203 (330p Genesee) | 2024-09-15 07:00 | 2024-09-19 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Restricts Generation
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.3TR (SS-31), 31.2TR (SS-31), 31B138-31.84 (SS-31), 31B138-24.81 (SS-31) | 2024-09-15 08:00 | 2024-09-15 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31.1C (SS-31), 31MD138-31.1TR (SS-31), 31B138-9.80 (SS-31) | 2024-09-15 12:00 | 2024-09-15 18:00 | N | N |  | Line, Transformer, Shunts, Switch, Circuit Breaker |  |  | Pre-Condition
EPCOR | 557s T1 (557s Castle Downs) | 2024-09-16 07:00 | 2024-12-20 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 511s V729 (EP 511s Victoria) | 2024-09-16 07:00 | 2024-09-18 17:00 | N | N |  | Circuit Breaker |  | Work was completed early. | Contingency Requires Mitigation, Pre-Condition
CMH | MHS-9 MH138-T11 (MHS9 Power Plant), MH-15L (MHS-7 Brier Park - MHS-9 South Saskatchewan), MH-6L (MHS-1 CMH Power Plant - MHS-9 South Saskatchewan), MHS-1 MH69-6 (MHS-1 CMH Power Plant), MHS-1 MH69-10 (MHS-1 CMH Power Plant), MHS-9 MH138-902 (MHS-9 South Saskatchewan) | 2024-09-16 07:30 | 2024-09-20 14:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 217s 652 (217s North Red Deer), 217s C1 (217s North Red Deer) | 2024-09-16 08:00 | 2024-09-20 17:00 | N | N |  | Switch, Shunts |  |  | Pre-Condition
ENMAX | 1B138-7A0 (SS-1) | 2024-09-16 08:00 | 2024-09-16 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7LA121 (833s Mariana - 7L121 tap), 7L121 (2043s Freer - 7LA121 tap), 7L121 (917s Horse River - 7LA121 tap) | 2024-09-16 08:00 | 2024-09-18 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2024-09-16 08:00 | 2024-09-19 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2024-09-16 08:00 | 2024-09-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 162B138-RB84 (SS-162) | 2024-09-16 08:00 | 2024-09-16 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 6.4TR (SS-6) | 2024-09-16 08:00 | 2024-09-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 11.81L (SS-11 - SS-13), 11.4TR (SS-11), 11.1TR (SS-11), 11B138-BT5 (SS-11), 11MD138-11.1TR (SS-11), 11MD138-11.4TR (SS-11) | 2024-09-16 08:00 | 2024-09-16 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 65.1TR (SS-65) | 2024-09-16 08:00 | 2024-09-24 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 2043s 701T (2043s Freer) | 2024-09-16 09:00 | 2024-09-20 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 813s 714 (813s Little Smoky), 813s 714C (813s Little Smoky) | 2024-09-16 09:30 | 2024-09-17 17:30 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 747L (37s North Calder - 711L tap), 37s 747W (37s North Calder) | 2024-09-16 11:30 | 2024-09-16 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1B138-8A0 (SS-1) | 2024-09-16 12:00 | 2024-09-16 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 368s 35 (368s Burdett), 368s 44 (368s Burdett), 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2024-09-16 12:30 | 2024-09-21 17:30 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 64s 138kV Bus1 (64s East Crossfield), 901AL (64s East Crossfield - 901L tap), 64s T2 (64s East Crossfield), 64s T1 (64s East Crossfield), 64s 652 (64s East Crossfield), 64s 33 (64s East Crossfield) | 2024-09-16 12:30 | 2024-09-19 16:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTAGAS | Lethbridge Burdett (ME03) | 2024-09-16 12:30 | 2024-09-21 17:30 | N | N |  | Unit
ALTALINK | 368s T2 (368s Burdett) | 2024-09-16 12:30 | 2024-09-21 17:30 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 927s 701T (927s Buchanan Creek), 927S 701 (927s Buchanan Creek) | 2024-09-16 14:00 | 2024-09-20 10:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENBRIDGE, BSRW | BSR1 Blackspring Ridge | 2024-09-17 07:00 | 2024-09-21 17:00 | N | N |  | Unit
ALTALINK, ENBRIDGE | 1042L (485s Blackspring Ridge - 554s Travers), 485s 240CB1 (485s Blackspring Ridge) | 2024-09-17 07:00 | 2024-09-18 18:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only, Restricts Generation
ATCO, ALBIAN, CNRL | 919s 906 (919s Hartley), 847s 901T (847s Muskeg River) | 2024-09-17 08:00 | 2024-09-18 08:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 325s 852 (325s Leduc) | 2024-09-17 08:00 | 2024-09-17 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33B138-33.83 (SS-33), SW83 (SS-33), 33MD138-33.1TR (SS-33) | 2024-09-17 08:00 | 2024-09-17 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 826s 908 (826s Marguerite Lake) | 2024-09-17 09:00 | 2024-09-17 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 780s 705 (780s Lubicon) | 2024-09-17 10:00 | 2024-09-17 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33B138-33.84 (SS-33), SW84 (SS-33), 33MD138-33.2TR (SS-33) | 2024-09-17 12:00 | 2024-09-17 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 523s 880 (523s Bullshead) | 2024-09-17 12:30 | 2024-09-17 16:30 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 602 (739s Edith Lake), 854S 601TD (854s Swan Dive) | 2024-09-17 13:00 | 2024-09-26 12:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72MG16 (Garneau - Meadowlark), 72PM25 (Poundmaker - Meadowlark), T3 (Meadowlark), M723 (Meadowlark), M724 (Meadowlark), M725 (Meadowlark), M726 (Meadowlark) | 2024-09-18 07:00 | 2024-09-27 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 23.3TR (SS-23) | 2024-09-18 08:00 | 2024-09-19 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 14.83L (SS-14 - SS-36), 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36.2TR (SS-36), 36B138-14.83 (SS-36), 36B138-36BT3 (SS-36), 36MD138-36.5TR (SS-36), 36MD138-36.2TR (SS-36), 36B69-16.63/36.5TR (SS-36) | 2024-09-18 08:00 | 2024-09-18 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5) | 2024-09-18 08:00 | 2024-09-18 16:00 | N | N |  | Line |  |  | For Information Only
ENMAX | 138kV South Bus (SS-65), 65B138-D81 (SS-65), 65B138-D83 (SS-65) | 2024-09-18 08:00 | 2024-09-19 16:00 | N | N |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 289s 552 (289s Saunders Lake) | 2024-09-18 08:30 | 2024-09-18 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 790s 703 (790s Poplar Hill), 7L07 (790s Poplar Hill - 815s Goodfare) | 2024-09-18 09:30 | 2024-09-19 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L63 (780s Lubicon - 812s Norcen), 780s 701 (780s Lubicon), 780s 702 (780s Lubicon) | 2024-09-18 10:00 | 2024-09-18 16:00 | N | Y |  | Line, Circuit Breaker |  | Work completed early. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s C1 (523s Bullshead) | 2024-09-18 12:30 | 2024-09-18 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 289s 652 (289s Saunders Lake) | 2024-09-18 12:31 | 2024-09-18 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1042L (485s Blackspring Ridge - 554s Travers) | 2024-09-18 18:01 | 2024-09-21 17:00 | N | Y |  | Line |  |  | 240 kV, Restricts Generation
ALTALINK | 19s 69kV Bus (19S Wabamun), 352s T1 (352s Onoway), 124L (19s Wabamun - 2739s Wabamun), 123L (19s Wabamun - 352s Onoway), 133L (19s Wabamun - 234L tap) | 2024-09-19 07:00 | 2024-09-19 18:00 | N | N |  | Bus, Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s T1 (523s Bullshead) | 2024-09-19 07:30 | 2024-09-19 12:30 | N | N |  | Transformer |  |  | For Information Only
CapitalPower | HAL2 Halkirk 2 Generator Test | 2024-09-19 08:00 | 2024-11-23 15:00 | N | N |  | Unit
ENMAX, ALTALINK | 7.84L (SS-7 - SS-36), 36.81L (44s Bearspaw Plant - SS-36), 36B138-36BT3 (SS-36), 36.1TR (SS-36), 36.3TR (SS-36), 36B138-36.81 (SS-36) | 2024-09-19 08:00 | 2024-09-19 16:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 36.81L (44s Bearspaw Plant - SS-36), 7.84L (SS-7 - SS-36), 36B138-36BT3 (SS-36), 36.1TR (SS-36), 36.2TR (SS-36), 36B138-36.81 (SS-36) | 2024-09-19 08:00 | 2024-09-19 16:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | For Information Only
ATCO | ATC 803S 7L85D5 (ATC 803s Bullpound), 7L85 (803s ATC Bullpound - 7LA85 tap) | 2024-09-19 09:00 | 2024-09-19 17:00 | N | Y |  | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 523s T2 (523s Bullshead) | 2024-09-19 11:30 | 2024-09-19 16:30 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 1.80L (SS-1 - SS-28) | 2024-09-20 08:00 | 2024-09-20 09:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 793s T1 (AML 793s Horse Creek) | 2024-09-20 09:00 | 2024-09-22 10:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.81L (SS-1 - SS-20) | 2024-09-20 09:01 | 2024-09-20 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43) | 2024-09-20 10:01 | 2024-09-20 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43) | 2024-09-20 12:01 | 2024-09-20 14:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 212s T1 (212s N.E.Lacombe), 212s 3 (212s N.E. Lacombe) | 2024-09-20 14:00 | 2024-09-20 15:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 38s 138kV Bus 2 (38s East Edmonton), 38s T3 (38s East Edmonton), 731L (38s East Edmonton - 746L tap), 215L (38s East Edmonton - 215AL tap), 761L (38s East Edmonton - 71s Lamoureux), 38s 75 (38s East Edmonton), 38s 4252 (38s East Edmonton), 38s 62 (38s East Edmonton), 38s 4152 (38s East Edmonton), 38s 761N (38s East Edmonton), 38s 731E (38s East Edmonton), 38s 215N (38s East Edmonton) | 2024-09-20 16:00 | 2024-09-22 18:00 | N | N |  | Bus, Transformer, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 95s T2 (95s Imperial Oil Edmonton), 38s 737N (38s East Edmonton), 95s 8 (95s Imperial Oil Edmonton), 95s 12 (95s Imperial Oil Edmonton) | 2024-09-20 16:00 | 2024-09-22 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | EP 511s V727 (EP 511s Victoria), EP 511s V728 (EP 511s Victoria), EP 511s Victoria T5 (EP 511s Victoria), CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s VDS25 (EP 511s Victoria) | 2024-09-21 07:00 | 2024-09-21 17:00 | N | Y |  | Circuit Breaker, Transformer, Line, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32), 32B138-31.84 (SS-32), 32MD138-32.3TR (SS-32) | 2024-09-21 08:00 | 2024-09-21 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 951s SVC (951s Thickwood) | 2024-09-21 12:30 | 2024-09-24 15:00 | N | Y |  | Shunts |  |  | Pre-Condition
SUNCOR | SCR1 Base Plant Generator Test | 2024-09-22 08:00 | 2025-04-28 17:00 | N | N |  | Unit
ENMAX | 13.2TR (SS-13) | 2024-09-22 13:00 | 2024-09-24 14:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72LS24 (EP 803s Lambton - Strathcona), S724 (Strathcona) | 2024-09-23 07:00 | 2024-09-27 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | PM2401 (Poundmaker) | 2024-09-23 07:00 | 2024-09-23 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 72CK12 (987s Clover Bar - Kennedale), T2 (Kennedale), K723 (Kennedale), K722 (Kennedale), KAB2 (Kennedale) | 2024-09-23 07:00 | 2024-09-28 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, BHE Canada | 120s 240kV Bus 1 (120s Picture Butte), 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1152 (120s Picture Butte), 120s 1252 (120s Picture Butte), 120s 1352 (120s Picture Butte) | 2024-09-23 07:00 | 2024-09-23 17:30 | N | Y |  | Bus, Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | 72VN21 (EP 511s Victoria - Namao), N725 (Namao) | 2024-09-23 07:00 | 2024-10-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks), 525s 850N (525s Carseland), 678s 850 (678s Okotoks) | 2024-09-23 07:00 | 2024-09-29 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 919L (77s Sagitawah - 310p Sundance), 310p 452 (310p Sundance), 310p 552 (310p Sundance) | 2024-09-23 07:15 | 2024-09-27 17:45 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 535s T3 (535s Joffre) | 2024-09-23 07:30 | 2024-09-27 18:00 | N | N |  | Transformer |  |  | Restricts Generation
ENMAX | 162B138-RB85 (SS-162) | 2024-09-23 08:00 | 2024-10-15 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO, SHELL | 402s 701T (402s Scotford Expansion 1) | 2024-09-23 08:00 | 2024-10-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 77s 14 (77s Sagitawah) | 2024-09-23 08:00 | 2024-10-03 17:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek) | 2024-09-23 08:00 | 2024-10-03 19:00 | N | Y |  | Line |  |  | Pre-Condition
ALTALINK, BCH, AESO-SC | 1201L (520s Bennett - BCH Cranbrook), 5D25 (BCH Cranbrook), 520S-Pseudo (520s Bennett) | 2024-09-23 08:00 | 2024-10-03 15:35 | Y | Y |  | Line, Switch |  |  | 500 kV, Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition, Affects Cranking Path
ENMAX | 2.3TR (SS-2) | 2024-09-23 08:00 | 2024-09-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 1CB2 (BCH Natal) | 2024-09-23 08:00 | 2024-10-03 15:35 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, AESO-SC | 520s T1 (520s Bennett), 520s 552 (520s Bennett), 520s R7 (520s Bennett), 520s 1352 (520s Bennett), 520s 12 (520s Bennett), 520s 13 (520s Bennett), 520s 1789 (520s Bennett), 102S-Pseudo (520s Bennett), 520S-Pseudo (520s Bennett) | 2024-09-23 08:30 | 2024-10-03 17:30 | N | Y |  | Transformer, Circuit Breaker, Shunts, Switch |  |  | 500 kV, Pre-Condition
ATCO | 7L16 (766s Nevis - 948s Heatburg), 766s 702 (766s Nevis), 948s 703 (948s Heatburg) | 2024-09-23 08:30 | 2024-09-24 11:02 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 715s 703T (715s Leming Lake), 715s 705 (715s Leming Lake) | 2024-09-23 08:30 | 2024-10-03 12:00 | N | N |  | Transformer, Circuit Breaker |  | Work completed early and back in service. | For Information Only
NWE, BHE Canada, BHE | Marias Shunt Capacitor, Hay Lake (NorthWestern Energy) - Marias (MATL), PDB2401 (BHE Hay Lake), PDB2402 (BHE Hay Lake), PDB2405 (BHE Hay Lake), SW2455N (BHE Hay Lake), SW2455S (BHE Hay Lake) | 2024-09-23 08:30 | 2024-09-23 17:30 | N | N |  | Shunts, Line, Circuit Breaker, Switch |  |  | Limits ATC
AESO | Path 1 (AIES Islanding) | 2024-09-23 09:00 | 2024-10-03 15:35 | Y | Y |  | Line |  |  | 240 kV, 500 kV, Limits ATC
ATCO | ATC 803s 701T (ATC 803s Bullpound) | 2024-09-23 09:00 | 2024-10-03 14:00 | N | N |  | Transformer |  |  | For Information Only
BHE Canada | MATL (120s Picture Butte - Montana) | 2024-09-23 09:00 | 2024-10-04 17:00 | Y | Y |  | Line |  |  | 240 kV, Limits ATC
ATCO | 806s 701T (806s Oldman River), 806s 152 (806s Oldman River) | 2024-09-23 10:00 | 2024-10-20 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 310p T30 (310p Sundance), 310P 69 (310p Sundance) | 2024-09-23 12:00 | 2024-09-26 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s 552 (523s Bullshead) | 2024-09-23 12:30 | 2024-09-23 16:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 799s T1 (799s Coleman) | 2024-09-23 13:30 | 2024-09-26 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 310p 2452 (310p Sundance) | 2024-09-23 13:30 | 2024-09-26 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 520s R7 (520s Bennett) | 2024-09-23 14:00 | 2024-10-03 16:00 | N | Y |  | Shunts |  |  | 500 kV, For Information Only
NWE, BHE Canada, BHE | Hay Lake (NorthWestern Energy) - Marias (MATL), North Series Capacitor (BHE Hay Lake) | 2024-09-23 18:00 | 2024-09-24 17:00 | N | N |  | Line, Shunts |  |  | Limits ATC
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2024-09-24 06:00 | 2024-09-24 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | PM2404 (Poundmaker) | 2024-09-24 07:00 | 2024-09-24 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 83s T1 (83s Taber), 83s 65 (83s Taber) | 2024-09-24 07:00 | 2024-09-26 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 523s T1 (523s Bullshead) | 2024-09-24 07:00 | 2024-10-03 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy) | 2024-09-24 07:00 | 2024-10-11 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
SUNCOR | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-2 29PT-3 (29EDD-2 Tar Island), 29EDD-1 29EDD1s1352 (29EDD-1 Millennium), 29EDD-1 29EDD1S1452 (29EDD-1 Millennium), 29EDD-1 29PS-0146 (29EDD-1 Millennium), 29EDD-2 29PS-6 (29EDD-2 Tar Island) | 2024-09-24 08:00 | 2024-10-08 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 27B69-16.61 (SS-27) | 2024-09-24 08:00 | 2024-09-24 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2024-09-24 08:30 | 2024-09-25 17:30 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 13.4TR (SS-13), 27B69-13.60 (SS-27) | 2024-09-24 12:00 | 2024-09-24 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 910L (288s Wolf Creek - 289s Saunders Lake) | 2024-09-25 06:15 | 2024-09-26 17:45 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 344s T2 (344s Warner), 67s 508X (67s Stirling) | 2024-09-25 07:00 | 2024-09-26 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
NWE, BHE, BHE Canada | NWE Great Falls, PDB2402 (BHE Hay Lake), PDB2405 (BHE Hay Lake), Great Falls Switchyard (NorthWestern Energy) - Marias (MATL), Hay Lake (NorthWestern Energy) - Marias (MATL) | 2024-09-25 07:30 | 2024-09-26 18:00 | N | Y |  | Station, Circuit Breaker, Line |  |  | Limits ATC
SUNCOR | 29PL7-10 (29EDD-18 Firebag - 29EDD-85), 29EDD-85 752-10010 (29EDD-85), 29EDD-85 752-10030 (29EDD-85), 29EDD-85 29PS-319 (29EDD-85), 29EDD-18 29PS-0043 (29EDD-18 Firebag) | 2024-09-25 08:00 | 2024-09-25 15:00 | N | N |  | Line, Circuit Breaker, Switch |  | ended early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 869s 702T (869s Seal Lake), 869s 702 (869s Seal Lake) | 2024-09-25 10:00 | 2024-09-25 15:30 | N | N |  | Transformer, Circuit Breaker |  | returned early | Pre-Condition
ATCO | 2091s 704 (2091s Thornton) | 2024-09-25 10:30 | 2024-09-25 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition, Prevents Normal Events
ALTALINK | 171s 138kV Bus (171s Redwater), 808L (171s Redwater - 808AL tap), 171s T2 (171s Redwater), 171s 808E (171s Redwater), 171s 30 (171s Redwater) | 2024-09-25 11:00 | 2024-10-01 13:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 27B69-13.60 (SS-27), 13B69-13.60 (SS-13), 13.4TR (SS-13) | 2024-09-26 06:00 | 2024-09-29 18:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 221s T1 (221s Sunken Lake) | 2024-09-26 07:00 | 2024-09-26 23:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1114L (102s Langdon - 520s Bennett), 102s 7552 (102s Langdon), 102s 7452 (102s Langdon), 102s 2689 (102s Langdon) | 2024-09-26 09:00 | 2024-09-26 14:00 | Y | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Affects Cranking Path
ATCO | 951S 902 (951s Thickwood Hills) | 2024-09-26 10:00 | 2024-09-26 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 914L (86s Bigstone - 87s Gaetz), 86s 1752 (86s Bigstone), 87s 1252 (87s Gaetz) | 2024-09-27 06:15 | 2024-10-02 13:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Affects Cranking Path
ENMAX | 11.81L (SS-11 - SS-13) | 2024-09-27 08:00 | 2024-09-27 16:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2024-09-27 08:00 | 2024-10-01 14:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 845s 709 (845s Big Mountain) | 2024-09-28 07:00 | 2024-09-29 19:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Prevents Normal Events
EPCOR | 987s GT1 (987s Clover Bar), 987s CGB1 (987s Clover Bar) | 2024-09-28 07:00 | 2024-09-28 15:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 11.82L (SS-11 - SS-14), 11.83L (SS-162 - SS-11), 11.3TR (SS-11), 11.2TR (SS-11), 11B138-11.83 (SS-11), 11B138-11.82 (SS-11), 11B138-BT5 (SS-11), 11MD138-11.2TR (SS-11), 11MD138-11.3TR (SS-11), SW84 (SS-11), SW83 (SS-11) | 2024-09-28 08:00 | 2024-09-28 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 65.2TR (SS-65) | 2024-09-28 08:00 | 2024-10-06 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 39.82L (SS-39 - SS-162), 39.3TR (SS-39), 39.1TR (SS-39) | 2024-09-29 08:00 | 2024-09-29 12:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 39.82L (SS-39 - SS-162), 39.2TR (SS-39), 22.81L (SS-22 - SS-39), 39.4TR (SS-39) | 2024-09-29 12:01 | 2024-09-29 18:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 535s T6 (535s Joffre), 535s 110 (535s Joffre) | 2024-09-30 07:30 | 2024-10-04 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 13.3TR (SS-13) | 2024-09-30 08:00 | 2024-10-03 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 760L (163s Amoco Empress - 760AL tap) | 2024-09-30 08:00 | 2024-10-12 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21) | 2024-09-30 08:00 | 2024-10-06 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L94 (BCH Cranbrook - 102s Langdon), 1L275 (799s Coleman - BCH Natal), 1L274 (48s Pocaterra - 978s BCH Britt Creek), 5RXN5 (BCH Cranbrook) | 2024-09-30 08:00 | 2024-10-03 15:35 | Y | Y |  | Line, Shunts |  |  | 500 kV, Creates Radial Feeds, Firm Load Loss, For Information Only, Limits ATC, Pre-Condition
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2024-09-30 09:00 | 2024-10-03 15:35 | Y | Y |  | Line |  |  | 500 kV, Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition, Affects Cranking Path
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton), 38s 737N (38s East Edmonton) | 2024-09-30 09:00 | 2024-10-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L54 (794s Valleyview - 813s Little Smoky), 794s 704 (794s Valleyview) | 2024-09-30 09:30 | 2024-10-01 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 832s 702T (832s Blumenort), 832s 702 (832s Blumenort) | 2024-09-30 09:30 | 2024-10-02 13:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L62 (797s Kemp River - 905s Meikle), 905s 708 (905s Meikle), 905s 703 (905s Meikle) | 2024-09-30 10:00 | 2024-10-07 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s ACF11 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell), 2075s 917 (2075s Newell), 2075s 918 (2075s Newell) | 2024-09-30 10:30 | 2024-10-02 15:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 7L23 (858s Narrows Creek - 7L23 tap), 796s 702 (796s Nipisi) | 2024-09-30 14:00 | 2024-10-04 16:34 | N | N |  | Line, Circuit Breaker |  | Outage completed early | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-71 29PT-336 (29EDD-71), 29EDD-71 752-4652 (29EDD-71), 29EDD-71 752-4651 (29EDD-71), 29EDD-71 29PS-430 (29EDD-71 Edd71Sub) | 2024-10-01 | 2024-11-01 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Completed early. | Restricts Generation
ATCO | 892s 701T (892s Ribstone Creek), 892s 701 (892s Ribstone Creek) | 2024-10-01 06:00 | 2024-10-03 13:20 | N | N |  | Transformer, Circuit Breaker |  | Work completed early and back in service. | For Information Only
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty) | 2024-10-01 07:00 | 2024-10-11 17:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2024-10-01 07:00 | 2024-10-11 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
EPCOR | 987s C2402 (987s Clover Bar) | 2024-10-01 07:00 | 2024-10-02 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 523s 880 (523s Bullshead) | 2024-10-01 07:00 | 2024-10-01 11:01 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | T2 (Meadowlark), M723 (Meadowlark), M722 (Meadowlark), MAB2 (Meadowlark) | 2024-10-01 07:00 | 2024-10-07 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker), 37s 81 (37s North Calder), 37s 76 (37s North Calder) | 2024-10-01 07:15 | 2024-10-01 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 162B240-RB134 (SS-162) | 2024-10-01 08:00 | 2024-10-01 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Syncrude, ATCO | RL1 (848s Ruth Lake - D05), 848s 910 (848s Ruth Lake), 848s 911 (848s Ruth Lake) | 2024-10-01 08:00 | 2024-10-02 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ENMAX | 40.81L (SS-40 - SS-41), 40B138-40.81 (SS-40), 41B138-40.81 (SS-41) | 2024-10-01 08:00 | 2024-10-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, CNRL | 838s 75-BC-1914 (838s Horizon Mining) | 2024-10-01 08:00 | 2024-10-03 12:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
VREL | VKW1 Kenilworth 1 Generator Test | 2024-10-01 08:00 | 2024-10-18 02:00 | N | Y |  | Unit
ALTALINK | 523s C1 (523s Bullshead) | 2024-10-01 11:00 | 2024-10-01 15:01 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 740L (39s Bickerdike - 58s Edson), 58s 740X (58s Edson) | 2024-10-01 12:00 | 2024-10-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 59s 352 (59s Peigan) | 2024-10-01 12:00 | 2024-10-04 15:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive), 743s 603 (743s Sarah Lake) | 2024-10-01 13:00 | 2024-10-02 19:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 289s T2 (289s Saunders Lake) | 2024-10-01 13:00 | 2024-10-03 17:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 867s T1 (867s Sundance Blow-Down), 234L (310p Sundance - 505L tap), 505L (234L tap - 505L tap), 521AL (867s Sundance Blow-Down - 521L tap), 310P 234N (310p Sundance) | 2024-10-01 13:30 | 2024-10-03 17:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 61s T2 (61s Lodgepole) | 2024-10-01 13:30 | 2024-10-03 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 523s 552 (523s Bullshead) | 2024-10-01 15:00 | 2024-10-01 19:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 37s 81 (37s North Calder) | 2024-10-01 16:01 | 2024-10-10 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 69s T2 (69s North Barrhead), 69s T5 (69s North Barrhead) | 2024-10-02 07:00 | 2024-10-10 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 676L (244s Bowmanton - 523s Bullshead), 523s 676 (523s Bullshead) | 2024-10-02 07:00 | 2024-10-02 10:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 805s C1 (805s Jasper), EP 805s J2403 (EP 805s Jasper), EP 805s J2404 (EP 805s Jasper) | 2024-10-02 07:00 | 2024-10-04 17:00 | N | Y |  | Line, Shunts, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
VREL | VNV1 Northern Valley 1 DER Generator Test | 2024-10-02 08:00 | 2024-11-29 11:00 | N | Y |  | Unit
ALTALINK | 202AL (359s Esso West Pembina - 202L tap), 359s T1 (359s Esso West Pembina), 359s T2 (359s Esso West Pembina) | 2024-10-02 08:00 | 2024-10-04 17:00 | N | Y |  | Line, Transformer |  |  | Restricts Generation
ENMAX | 41.1C (SS-41) | 2024-10-02 08:00 | 2024-10-02 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 834L (320p Keephills - 384s Keystone), 320p 834X (320p Keephills), 384s 834 (384s Keystone) | 2024-10-02 08:00 | 2024-10-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 3.4TR (SS-3) | 2024-10-02 08:00 | 2024-10-03 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 523s 600 (523s Bullshead), 600L (404s Peace Butte - 523s Bullshead), 404s T1 (404s Peace Butte), 404s T2 (404s Peace Butte) | 2024-10-02 08:00 | 2024-10-02 17:00 | N | N |  | Circuit Breaker, Line, Transformer |  |  | For Information Only
ATCO | 951s 906 (951s Thickwood Hills) | 2024-10-02 10:00 | 2024-10-02 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 919L (77s Sagitawah - 310p Sundance) | 2024-10-02 16:30 | 2024-10-02 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 987s C2404 (987s Clover Bar) | 2024-10-03 07:00 | 2024-10-04 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Prevents Normal Events
Lethbridge, ALTALINK | 181s 463L (181s Chinook), 463L (181s Chinook - 463AL tap) | 2024-10-03 07:30 | 2024-10-03 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1B138-4A0 (SS-1) | 2024-10-03 08:00 | 2024-10-03 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 9L01 (848s Ruth Lake - 951s Thickwood Hills), 848s 911 (848s Ruth Lake), 848s 913 (848s Ruth Lake) | 2024-10-03 08:00 | 2024-10-04 16:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14B138-11.82 (SS-14), 14MD138-14.1TR (SS-14), 14MD138-14.3TR (SS-14), SW83 (SS-14), SW87 (SS-14) | 2024-10-03 08:00 | 2024-10-03 12:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L94 (BCH Cranbrook - 102s Langdon), 1L274 (48s Pocaterra - 978s BCH Britt Creek), 1L275 (799s Coleman - BCH Natal), 5RXN5 (BCH Cranbrook) | 2024-10-03 09:00 | 2024-10-03 16:00 | Y | Y |  | Line, Shunts |  |  | 500 kV, Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ATCO | 9L56 (720s Wabasca - 876s Brintnell), 720s 901 (720s Wabasca) | 2024-10-03 10:00 | 2024-10-03 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ENMAX | 14.83L (SS-14 - SS-36), 14.4TR (SS-14), 14.2TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14B138-14.83 (SS-14), SW87 (SS-14), SW84 (SS-14), 14MD138-14.2TR (SS-14), 14MD138-14.1TR (SS-14) | 2024-10-03 12:00 | 2024-10-03 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1B138-3A0 (SS-1) | 2024-10-03 12:01 | 2024-10-03 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK, AESO | 394s T2 (394s Empress), 394s 1152 (394s Empress), 394s 1907 (394s Empress), 394s S142836 (394s Empress) | 2024-10-03 12:30 | 2024-10-03 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 602 (739s Edith Lake), 854S 601TD (854s Swan Dive) | 2024-10-03 13:00 | 2024-10-03 19:30 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L85 (803s ATC Bullpound - 7LA85 tap) | 2024-10-03 14:00 | 2024-10-03 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, CNRL | 838s 75-BC-1915 (838s Horizon Mining) | 2024-10-03 14:00 | 2024-10-04 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Prevents Normal Events
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station), 840s 701T (840s McNeill Station), 840s 901T (840s McNeill Station), 840s 702C (840s McNeill Station), 840s 703C (840s McNeill Station) | 2024-10-04 01:05 | 2025-02-09 23:59 | Y | Y |  | Station, Line, Transformer, Shunts |  |  | Limits ATC, Pre-Condition
ALTALINK | 254s T2 (254s Coaldale), 254s 35 (254s Coaldale), 254s 36 (254s Coaldale), 254s 15 (254s Coaldale) | 2024-10-04 08:00 | 2024-10-04 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ATCO | 6L11 (743s Sarah Lake - 854s Swan Dive), 743s 603 (743s Sarah Lake) | 2024-10-04 08:00 | 2024-10-06 19:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Mildred T1 (Syncrude Mildred Lake), 134 (Syncrude Mildred Lake), 135 (Syncrude Mildred Lake), 1335 (Syncrude Mildred Lake) | 2024-10-04 08:00 | 2024-10-22 16:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 523s 138kV Bus 2 (523s Bullshead), 523s T2 (523s Bullshead), 676L (244s Bowmanton - 523s Bullshead), 523s 552 (523s Bullshead), 523s 289 (523s Bullshead) | 2024-10-04 14:00 | 2024-10-18 18:00 | N | Y |  | Bus, Transformer, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
BHE Canada | 120s C1 (120s Picture Butte) | 2024-10-05 | 2025-05-28 10:29 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 26.2TR (SS-26), 26B138-26BT3 (SS-26), 65MD138-26.83 (SS-65) | 2024-10-05 08:00 | 2024-10-05 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, SUNCOR | 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake), 848s 901 (848s Ruth Lake), 848s 902 (848s Ruth Lake), 848s 901B (848s Ruth Lake), 848s 902B (848s Ruth Lake), 29EDD-1 29EDD1SPL9-2 (29EDD-1 Millennium) | 2024-10-05 08:00 | 2024-10-06 16:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX, ALTALINK | 20.82L (SS-20 - SS-21), 21.80L (42s Sarcee - SS-21), 21.1TR (SS-21), 21.4TR (SS-21), 20B138-20.82 (SS-20), 21B138-21.80 (SS-21), 21B69-21.4TR (SS-21), SW64 (SS-21), 21MD138-21.1TR (SS-21), 21MD138-21.4TR (SS-21) | 2024-10-05 08:00 | 2024-10-05 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Lethbridge, ALTALINK | 111s 138kV Bus (111s Coalbanks), 207L (111s Coalbanks - 370s North Lethbridge), 725L (111s Coalbanks - 725AL tap), 725AL (618s Riverbend - 725L tap), 111s T1 (111s Coalbanks), 111s T2 (111s Coalbanks), 111s T3 (111s Coalbanks), 111s 207L (111s Coalbanks), 111s 725LE (111s Coalbanks), 111s 1 (111s Coalbanks), 111s 2 (111s Coalbanks), 111s 3 (111s Coalbanks), 111s 28 (111s Coalbanks), 111s 29 (111s Coalbanks) | 2024-10-05 21:00 | 2024-10-06 08:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 22.3TR (SS-22), 22.1TR (SS-22), 22B138-13.82 (SS-22), 22B138-22BT8 (SS-22), SW83 (SS-22), SW84 (SS-22), 22MD138-22.1TR (SS-22), 22MD138-22.3TR (SS-22) | 2024-10-06 08:00 | 2024-10-06 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), AML 511s T11 (AML 511s Crossings), 510s T11 (510s Sunnybrook), AML 511s 4852 (AML 511s Crossings), AML 511s 4952 (AML 511s Crossings), 510s 2652 (510s Sunnybrook), 510s 2752 (510s Sunnybrook), AML 511s 1489 (AML 511s Crossings), AML 511s 74 (AML 511s Crossings), AML 511s 76 (AML 511s Crossings), 510s 41 (510s Sunnybrook), 510s 43 (510s Sunnybrook), 510s 4289 (510s Sunnybrook) | 2024-10-07 07:00 | 2024-10-16 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 500 kV, Overload, Pre-Condition
EPCOR | 524s T1 (524s Owens Corning) | 2024-10-07 07:00 | 2024-10-21 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 816s T2 (816s Petrolia), 816s P2404 (816s Petrolia), 816s P2405 (816s Petrolia), 816s PAB2 (816s Petrolia), 816s ELSP72 (816s Petrolia), 816s BESS-1-1 (816s Petrolia), 816s PV-1-1 (816s Petrolia) | 2024-10-07 07:00 | 2024-11-06 18:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Back in service. | 240 kV, Contingency Requires Mitigation, Restricts Generation
EPCOR | T3 (Namao) | 2024-10-07 07:00 | 2024-10-10 15:30 | N | N |  | Transformer |  |  | For Information Only
NOVAC, ALTALINK | 330L2 (330s Nova Joffre - 535s Joffre), 535s 5852 (535s Joffre), 535s 5952 (535s Joffre) | 2024-10-07 07:30 | 2024-10-11 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX, ALTALINK | 240kV West Bus (SS-25), 1109L (SS-25 - SS-65), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25B240-D141 (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25), 25MD240-1109 (SS-25) | 2024-10-07 08:00 | 2024-10-07 16:00 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 39.2TR (SS-39) | 2024-10-07 08:00 | 2024-10-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 602 (739s Edith Lake), 854S 601TD (854s Swan Dive) | 2024-10-07 08:00 | 2024-10-08 13:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 39B138-22.81 (SS-39), 22B138-22.81 (SS-22) | 2024-10-07 08:00 | 2024-10-09 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 846s 702T (846s Grand Centre) | 2024-10-07 08:30 | 2024-10-15 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 2L293 (BCH Nelway - BCH Selkirk) | 2024-10-07 09:00 | 2024-11-01 17:00 | N | Y |  | Line |  |  | 240 kV, Limits ATC
BCH | 2L112 (BPA Boundary - BCH Nelway) | 2024-10-07 09:00 | 2024-10-08 18:00 | N | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ATCO | 873s 601 (873s Marion Lake) | 2024-10-07 09:00 | 2024-10-07 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 7L20 (740s H.R. Milner - 810s Dome Cutbank), 740s 704 (740s H.R. Milner) | 2024-10-07 09:00 | 2024-10-16 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 9L100 (801s Anderson - 807s Sheerness), 807s 902T (807s Sheerness), 807s 902 (807s Sheerness), 801s 910 (801s Anderson), 801s 911 (801s Anderson), 801s 910A (801s Anderson), 801s 911A (801s Anderson), 801S 9L100D1 (801s Anderson), 807S 902B (807s Sheerness) | 2024-10-07 10:00 | 2024-11-07 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-10-07 10:00 | 2024-11-29 10:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 409s 110 (409s Shell Scotford), 409s 109 (409s Shell Scotford) | 2024-10-07 11:00 | 2024-10-07 15:00 | N | Y |  | Circuit Breaker, Switch |  |  | For Information Only
ATCO | ALC02L (409s Shell Scotford - 879s Upgrader), 879s 252 (879s Upgrader) | 2024-10-07 11:00 | 2024-10-07 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 320p 3052 (320p Keephills) | 2024-10-07 13:00 | 2024-10-10 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 9.2TR (SS-9) | 2024-10-07 13:00 | 2024-10-07 18:00 | N | N |  | Transformer |  |  | For Information Only
Keyera Wapiti | WPT1 Wapiti Generator Test | 2024-10-08 06:00 | 2025-03-15 18:00 | N | N |  | Unit
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12B138-832L (SS-12), 10B138-832 (SS-10) | 2024-10-08 06:00 | 2024-10-08 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 55s T1 (55s Olds) | 2024-10-08 06:00 | 2024-10-10 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 511s V725 (EP 511s Victoria) | 2024-10-08 07:00 | 2024-10-10 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 863L (618s Riverbend - 891L tap), 618s 863X (618s Riverbend) | 2024-10-08 07:00 | 2024-10-10 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), T1 (Meadowlark), M722 (Meadowlark), M721 (Meadowlark), EP 805s J722 (EP 805s Jasper) | 2024-10-08 07:00 | 2024-10-18 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
EHN | 226s Garden City | 2024-10-08 07:00 | 2024-10-10 10:00 | N | N |  | Station |  |  | Restricts Generation
ALTALINK | 501CL (983s Cadomin - 501L tap), 501L (426s Coalspur - 501CL tap), 426s VR1 (426s Coalspur), 426s 501W (426s Coalspur) | 2024-10-08 07:00 | 2024-10-10 20:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 740L (39s Bickerdike - 740AL tap) | 2024-10-08 07:00 | 2024-10-08 20:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 740L (426s Coalspur - 743L tap), 740L (740AL tap - 743L tap), 743L (527s Coal Valley - 740L tap), 762L2 (743L tap) | 2024-10-08 07:00 | 2024-10-10 20:00 | N | N |  | Line, Switch |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34), 34.2TR (SS-34), 34B69-16.60 (SS-34), SW64 (SS-34), 34MD69-34.2TR (SS-34) | 2024-10-08 08:00 | 2024-10-08 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5) | 2024-10-08 08:00 | 2024-10-08 16:00 | N | N |  | Line
ENMAX | 14.1C (SS-14) | 2024-10-08 08:00 | 2024-10-09 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 1B138-5A0 (SS-1) | 2024-10-08 08:00 | 2024-10-08 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 846s 701 (846s Grand Centre), 717s 701 (717s Ethel Lake) | 2024-10-08 08:30 | 2024-10-09 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 618s T1 (618s Riverbend), 618s VR1 (618s Riverbend) | 2024-10-08 08:30 | 2024-10-18 15:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 61s T1 (61s Lodgepole) | 2024-10-08 09:30 | 2024-10-10 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 786s 701 (786s High Level) | 2024-10-08 09:30 | 2024-10-09 17:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition, Prevents Normal Events
ATCO | 7L159 (770s Three Hills - 7L159 tap) | 2024-10-08 10:00 | 2024-10-18 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1B138-6A0 (SS-1) | 2024-10-08 12:01 | 2024-10-08 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 551L (945s Sunshine Village - 551GL tap), 551L (953s Lake Louise - 551GL tap), 953s T1 (953s Lake Louise), 953s T2 (953s Lake Louise), 945s 26 (945s Sunshine Village), 953s 47 (953s Lake Louise), 953s 50 (953s Lake Louise), 953s 46 (953s Lake Louise), 953s 48 (953s Lake Louise), 953s 49 (953s Lake Louise), 953s 51 (953s Lake Louise), 953s 238 (953s Lake Louise) | 2024-10-09 | 2024-10-09 06:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ATCO, ALTALINK | 7L696 (508s Lakesend - 892s Ribstone Creek), 508s T1 (508s Lakesend), 508s 696 (508s Lakesend) | 2024-10-09 07:00 | 2024-10-09 19:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 735L (171s Redwater - 233s Beamer), 171s 735X (171s Redwater), 233s 735N (233s Beamer) | 2024-10-09 07:00 | 2024-10-09 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1045L (EP 805s Jasper - 1045AL tap), 1045AL (320p Keephills - 1045L tap), 1045L (310p Sundance - 1045AL tap), EP 805s J2407 (EP 805s Jasper), EP 805s J2406 (EP 805s Jasper), 320p 1352 (320p Keephills) | 2024-10-09 07:00 | 2024-10-10 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | AML 511s T30 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings) | 2024-10-09 07:30 | 2024-10-11 16:30 | N | Y |  | Transformer, Shunts |  |  | 240 kV
ENMAX | 21.61L (SS-21 - SS-34), 21B69-21.61 (SS-21), 34B69-21.61 (SS-34) | 2024-10-09 08:00 | 2024-10-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L696 (508s Lakesend - 892s Ribstone Creek), 892s 702 (892s Ribstone Creek) | 2024-10-09 08:00 | 2024-10-09 22:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 786s 702 (786s High Level) | 2024-10-09 17:31 | 2024-10-10 15:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition, Prevents Normal Events
ALTALINK | 510s T2 (510s Sunnybrook), 510s 3852 (510s Sunnybrook) | 2024-10-10 07:00 | 2024-10-10 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 24.81L (SS-24 - SS-31), 31B138-24.81 (SS-31), 24B138-24.81 (SS-24) | 2024-10-10 08:00 | 2024-10-10 12:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29EDD-1 T1 (29EDD-1 Millennium), 29EDD-1 29EDD1s952 (29EDD-1 Millennium), 29EDD-1 29EDD1s1052 (29EDD-1 Millennium), 29EDD-1 29EDD1s852 (29EDD-1 Millennium), 29EDD-1 29EDD1S1452 (29EDD-1 Millennium), 29EDD-1 29EDD1s1852 (29EDD-1 Millennium), 29EDD-1 29EDD1S23 (29EDD-1 Millennium), 29EDD-1 29EDD1S24 (29EDD-1 Millennium) | 2024-10-10 08:00 | 2024-10-28 17:10 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 11.82L (SS-11 - SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14) | 2024-10-10 08:00 | 2024-10-11 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L24 (846s Grand Centre - 7LA24 tap), 846s 702 (846s Grand Centre) | 2024-10-10 08:30 | 2024-10-11 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 951s 905 (951s Thickwood Hills), 951s 905B (951s Thickwood Hills) | 2024-10-10 10:00 | 2024-10-10 16:00 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker) | 2024-10-10 16:00 | 2024-10-10 16:30 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Affects Cranking Path
ALTALINK | 510s T1 (510s Sunnybrook), 510s 4052 (510s Sunnybrook) | 2024-10-11 07:00 | 2024-10-11 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | EP 805s J2405 (EP 805s Jasper) | 2024-10-11 07:00 | 2024-10-11 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
Lethbridge | 813L (146s MacDonald - 241s Uplands), 241s 813L (241s Uplands), 146s 813L (146s Macdonald) | 2024-10-11 07:30 | 2024-10-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 191s 792N (191s N.W. Cardiff), 150s 792X (150s Clyde) | 2024-10-11 07:30 | 2024-10-15 17:30 | N | N |  | Line, Circuit Breaker |  | Completed Early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L117 (706s Irish Creek - 710s Vermilion), 706s 703 (706s Irish Creek), 710s 701 (710s Vermilion) | 2024-10-11 08:00 | 2024-10-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 171s T1 (171s Redwater) | 2024-10-11 11:00 | 2024-10-12 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2-GSU-XF-0002 (SS-162), 162B240-RB135 (SS-162), 162B240-RB134 (SS-162), 2-EHA-DS-0002 (SS-162) | 2024-10-12 07:00 | 2024-10-15 10:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 146s 667 (146s Macdonald), 370s 667 (370s North Lethbridge) | 2024-10-12 07:30 | 2024-10-12 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 24.81L (SS-24 - SS-31), 24.83L (74s Janet - SS-24), 24.1TR (SS-24), 74s 24.83X (74s Janet), 24B138-24BT3 (SS-24), 24B138-24.81 (SS-24), 31B138-24.81 (SS-31) | 2024-10-12 08:00 | 2024-10-13 16:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.1C (SS-21), 21.2TR (SS-21), 60s50 (SS-21) | 2024-10-12 08:00 | 2024-10-12 16:00 | N | Y |  | Line, Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2024-10-14 08:00 | 2024-10-18 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 13.1TR (SS-13) | 2024-10-14 08:00 | 2024-10-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2024-10-14 08:00 | 2024-10-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ATCO, ALTALINK | 1035L (244s Bowmanton - 2075s Newell), 244s 152 (244s Bowmanton), 244s 252 (244s Bowmanton) | 2024-10-14 12:00 | 2024-10-14 17:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12B138-833L (SS-12) | 2024-10-15 06:00 | 2024-10-15 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK, PR | 275s 240kV Bus 2 (275s Jenner), 949L (275s Jenner - 306s Halsbury), 275s T2 (275s Jenner), 275s 8 (275s Jenner), 275s 1952 (275s Jenner), 275s 949 (275s Jenner), 275s 46 (275s Jenner), 275s 2252 (275s Jenner), 275s 47 (275s Jenner), 275s 36 (275s Jenner), 275s 2689 (275s Jenner), 306s 240CB1 (306s Halsbury), 306s 240MDS1 (306s Halsbury), 306s 240MDS2 (306s Halsbury), 306s 240MDS3 (306s Halsbury), 306s 240MDS4 (306s Halsbury) | 2024-10-15 07:00 | 2024-10-17 10:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, TRANSALTA | 229s T1 (229s Glenwood), 162L (229s Glenwood - 415s Drywood), 225L (229s Glenwood - 385s Spring Coulee), 385s 225 (385s Spring Coulee), 415s 146E (415s Drywood) | 2024-10-15 07:00 | 2024-10-15 16:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 965L (326s Murray lake - 244s Bowmanton), 244s 252 (244s Bowmanton), 244s 352 (244s Bowmanton) | 2024-10-15 07:00 | 2024-10-15 12:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 905L (19s Wabamun - 37s North Calder), 37s 76 (37s North Calder), 37s 82 (37s North Calder), 37s 71 (37s North Calder), 19s 905 (19s Wabamun) | 2024-10-15 07:15 | 2024-10-24 16:45 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 535s T2 (535s Joffre) | 2024-10-15 07:30 | 2024-10-20 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.3TR (SS-38) | 2024-10-15 08:00 | 2024-10-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162.3TR (SS-162) | 2024-10-15 08:00 | 2024-10-15 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 36.3TR (SS-36) | 2024-10-15 08:00 | 2024-10-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 32.3TR (SS-32) | 2024-10-15 08:00 | 2024-10-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO, BSSL | 7L760 (767s Oyen - 7LA760 tap), 1004s T1 (1004s Bulleye), 767s 702 (767s Oyen), 1004s 52-L (1004s Bulleye), 1004s 89-L1 (1004s Bulleye) | 2024-10-15 08:00 | 2024-10-15 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 717s 701 (717s Ethel Lake) | 2024-10-15 08:30 | 2024-10-16 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 786s 702T (786s High Level), 786s 507C (786s High Level), 786s 508C (786s High Level) | 2024-10-15 08:30 | 2024-10-18 16:00 | N | N |  | Transformer, Shunts |  |  | Pre-Condition
ATCO | 706s 702T (706s Irish Creek), 706s 704 (706s Irish Creek) | 2024-10-15 09:00 | 2024-10-16 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 732s 901T (732s Mitsue), 732s 501R (732s Mitsue), 732s 701 (732s Mitsue), 732s 702 (732s Mitsue) | 2024-10-15 10:00 | 2024-10-18 16:00 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 735s 601T (735s Swan River), 735s 601 (735s Swan River) | 2024-10-15 10:00 | 2024-10-18 12:00 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
ATCO | 785s 701T (785s Judy Creek Gas Plant) | 2024-10-15 10:00 | 2024-10-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 522L (320p Keephills - 133L tap), 320p T5 (320p Keephills), 320p 169 (320p Keephills), 320p 170 (320p Keephills) | 2024-10-15 10:30 | 2024-11-05 16:00 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station), 840s 701T (840s McNeill Station), 840s 901T (840s McNeill Station), 840s 901 (840s McNeill Station), 840s 701 (840s McNeill Station), 840s 702C (840s McNeill Station), 840s 703C (840s McNeill Station) | 2024-10-15 11:00 | 2025-01-15 12:00 | Y | Y |  | Station, Line, Transformer, Circuit Breaker, Shunts |  |  | Limits ATC, Pre-Condition
ALTALINK | 244s 552 (244s Bowmanton), 244s 652 (244s Bowmanton), 1074L (244s Bowmanton - 1074AL Tap) | 2024-10-15 12:01 | 2024-10-15 17:30 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 89s 352 (89s Ellerslie) | 2024-10-15 13:00 | 2024-10-17 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1-GSU-XF-0001 (SS-162), 162B240-RB132 (SS-162), 162B240-RB131 (SS-162), 1-EHA-DS-0001 (SS-162) | 2024-10-15 16:00 | 2024-10-21 16:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L760 (767s Oyen - 7LA760 tap) | 2024-10-15 16:01 | 2024-10-30 21:00 | N | N |  | Line |  | Completed early | Creates Radial Feeds, Firm Load Loss
ALTALINK | 29s T2 (29s Cascade), 29s 40 (29s Cascade) | 2024-10-16 07:00 | 2024-11-19 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 746L (700L tap - 746AL tap), 746L (746AL tap - 746BL tap), 746AL (524s Owens Corning - 746L tap) | 2024-10-16 07:00 | 2024-10-16 17:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 1034L (244s Bowmanton - 324s Cassils), 244s 452 (244s Bowmanton), 244s 552 (244s Bowmanton) | 2024-10-16 07:30 | 2024-10-16 12:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 704L (51s Wainwright - 478s Tucuman), 478s 152 (478s Tucuman), 51s 704 (51s Wainwright) | 2024-10-16 08:00 | 2024-10-17 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 162B138-RB86 (SS-162) | 2024-10-16 08:00 | 2024-11-08 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 264s 252 (264s Elkwater) | 2024-10-16 08:30 | 2024-10-16 13:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 244s 2152 (244s Bowmanton), 244s 2252 (244s Bowmanton), 676L (244s Bowmanton - 523s Bullshead) | 2024-10-16 12:01 | 2024-10-16 17:30 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only
ATCO | 951s SVC (951s Thickwood) | 2024-10-16 20:00 | 2024-10-18 16:30 | N | Y |  | Shunts |  |  | Pre-Condition
ALTALINK | 965L (326s Murray lake - 244s Bowmanton), 244s 252 (244s Bowmanton), 244s 352 (244s Bowmanton) | 2024-10-16 23:00 | 2024-10-18 15:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
EPCOR | 72RW3 (Rossdale - Woodcroft), RW727 (Rossdale) | 2024-10-17 07:00 | 2024-11-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 765L (151s Strathmore - 419s Chestermere), 419s 765 (419s Chestermere), 151s 765W (151s Strathmore) | 2024-10-17 07:00 | 2024-10-18 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive), 739s 602 (739s Edith Lake) | 2024-10-17 08:00 | 2024-10-23 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2024-10-17 08:00 | 2024-10-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.5TR (SS-1) | 2024-10-17 08:00 | 2024-10-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1202L (89s Ellerslie - 320p Keephills), 320p 3152 (320p Keephills), 320p 3052 (320p Keephills), 320p 3089B (320p Keephills), 320p 4689 (320p Keephills) | 2024-10-17 09:00 | 2024-10-17 15:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L117 (706s Irish Creek - 710s Vermilion), 706s 703 (706s Irish Creek), 706s 701 (706s Irish Creek) | 2024-10-17 10:00 | 2024-10-17 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 892L (244s Bowmanton - 895s Suffield), 244s 2952 (244s Bowmanton), 244s 3052 (244S Bowmanton), 895s 892 (895s Suffield) | 2024-10-17 12:00 | 2024-10-17 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK, TRANSALTA | 229s T1 (229s Glenwood), 225L (229s Glenwood - 385s Spring Coulee), 162L (229s Glenwood - 415s Drywood), 415s 146E (415s Drywood), 385s 225 (385s Spring Coulee) | 2024-10-18 07:00 | 2024-10-19 17:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 244s 3052 (244S Bowmanton), 244s 3152 (244s Bowmanton), 674L (244s Bowmanton - 649s Chappice Lake) | 2024-10-18 07:30 | 2024-10-18 12:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
ATCO | 9L58 (848s Ruth Lake - 888s Dover), 848s 907 (848s Ruth Lake), 848s 908 (848s Ruth Lake) | 2024-10-18 08:00 | 2024-10-19 16:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 48s 887X (48s Pocaterra) | 2024-10-18 09:00 | 2024-10-18 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC
ALTALINK, EPCOR | 1203L (320p Keephills - 510s Sunnybrook), 320p 3452 (320p Keephills), 320p 2952 (320p Keephills), 320p 5189 (320p Keephills), 320p 2989B (320p Keephills), 320p 5289 (320p Keephills) | 2024-10-18 09:00 | 2024-10-18 15:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 951s 908 (951s Thickwood Hills) | 2024-10-18 10:00 | 2024-10-18 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p 2089 (320p Keephills) | 2024-10-18 20:00 | 2024-10-28 20:00 | N | Y |  | Switch |  |  | 500 kV
ALTALINK | 940L (120s Picture Butte - 370s North Lethbridge) | 2024-10-19 07:00 | 2024-10-19 18:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Restricts Generation
ALTALINK | 675L (244s Bowmanton - 321s Al Rothbauer), 244s 2552 (244s Bowmanton), 244s 2652 (244s Bowmanton), 321s 675 (321s Al Rothbauer) | 2024-10-19 07:30 | 2024-10-19 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 21.61L (SS-21 - SS-34), 34.1TR (SS-34), 34B69-21.61 (SS-34), 34MD69-34.1TR (SS-34) | 2024-10-19 08:00 | 2024-10-19 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 5B138-2.83 (SS-5), 13B138-2.83 (SS-13) | 2024-10-19 08:00 | 2024-10-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ENMAX | 26.1TR (SS-26) | 2024-10-19 08:00 | 2024-10-19 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s 240kV Bus 1 (38s East Edmonton), 38s T1 (38s East Edmonton), 38s 73 (38s East Edmonton), 38s 50 (38s East Edmonton), 38s 7652 (38s East Edmonton), 38s 7152 (38s East Edmonton) | 2024-10-20 07:30 | 2024-10-20 13:30 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 9L23 (848s Ruth Lake - 977s Salt Creek), 848s 905 (848s Ruth Lake), 848s 906 (848s Ruth Lake), 848s 905B (848s Ruth Lake), 848s 906B (848s Ruth Lake) | 2024-10-20 08:00 | 2024-10-21 16:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 37.1TR (SS-37) | 2024-10-20 08:00 | 2024-10-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.83L (SS-5 - 2.83L tap), 5.9TR (SS-5), 5.10TR (SS-5), 5B138-5BT12 (SS-5) | 2024-10-20 08:00 | 2024-10-20 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 48s 887X (48s Pocaterra) | 2024-10-20 09:00 | 2024-11-08 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC
ALTALINK | 244s 3252 (244s Bowmanton) | 2024-10-21 06:30 | 2024-10-21 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
EPCOR | PM2405 (Poundmaker) | 2024-10-21 07:00 | 2024-10-21 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 616L (59s Peigan - 616AL tap), 616L (103s Goose Lake - 616AL tap), 616AL (383s Kettles Hill Windfarm - 616L tap), 59s 616 (59s Peigan) | 2024-10-21 07:00 | 2024-10-21 13:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 820AL (315s Chin Chute - 820L tap), 820BL (967s Redcoat - 820L tap), 820L (254s Coaldale - 820AL tap), 820L (67s Stirling - 820BL tap), 820L (820AL tap - 820BL tap), 67s T2 (67s Stirling), 67s 2 (67s Stirling), 254s 820 (254s Coaldale) | 2024-10-21 07:00 | 2024-10-30 15:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | T1 (Rossdale), 814s T2 (814s Bellamy), R721 (Rossdale), RR723 (Rossdale), BR722 (Rossdale) | 2024-10-21 07:00 | 2024-10-25 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 12GT7D (330p Genesee) | 2024-10-21 07:00 | 2024-10-27 17:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 880L (321s Al Rothbauer - 523s Bullshead), 523s 880 (523s Bullshead), 321s 880 (321s Al Rothbauer) | 2024-10-21 07:30 | 2024-10-22 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.7TR (SS-1) | 2024-10-21 08:00 | 2024-10-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 20.82L (SS-20 - SS-21), 20B138-20.82 (SS-20), 21B138-20.82 (SS-21) | 2024-10-21 08:00 | 2024-10-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34) | 2024-10-21 08:00 | 2024-10-21 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.2C (SS-14) | 2024-10-21 08:00 | 2024-10-22 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16) | 2024-10-21 08:00 | 2024-11-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L583 (715s Leming Lake - 970s Bourque), 715s 701 (715s Leming Lake) | 2024-10-21 08:30 | 2024-10-23 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 38s C2 (38s East Edmonton) | 2024-10-21 09:00 | 2024-11-07 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 741s 504C (741s Fox Creek), 741S 504 (741s ATC Fox Creek) | 2024-10-21 10:00 | 2025-02-03 14:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 67s 508X (67s Stirling) | 2024-10-21 10:00 | 2024-10-25 15:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2024-10-21 10:00 | 2024-10-24 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 732s 902T (732s Mitsue), 732s 503R (732s Mitsue), 732s 503 (732s Mitsue), 732s 705 (732s Mitsue), 732s 704 (732s Mitsue) | 2024-10-21 10:00 | 2024-10-24 16:00 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 67s T2 (67s Stirling), 67s 820 (67s Stirling) | 2024-10-21 12:30 | 2024-10-25 17:30 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 244s 3752 (244s Bowmanton) | 2024-10-21 12:31 | 2024-10-21 16:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer) | 2024-10-21 13:00 | 2024-10-29 13:19 | N | Y |  | Transformer, Circuit Breaker |  | Work is completed early. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 28s 28 (28s West Brooks), 853AL tap | 2024-10-21 13:00 | 2024-10-26 17:30 | N | N |  | Circuit Breaker, Station |  |  | Contingency Requires Mitigation
ALTALINK | 616L (103s Goose Lake - 616AL tap) | 2024-10-21 13:00 | 2024-12-02 07:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2024-10-21 13:30 | 2024-10-24 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 535s 6652 (535s Joffre) | 2024-10-22 07:30 | 2024-10-24 18:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 729L (285s East Camrose - 542s Ervick), 285s 729W (285s East Camrose) | 2024-10-22 07:30 | 2024-10-22 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 38.2TR (SS-38) | 2024-10-22 08:00 | 2024-10-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.6TR (SS-1) | 2024-10-22 08:00 | 2024-10-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.4TR (SS-2) | 2024-10-22 08:00 | 2024-10-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.82L (SS-3 - SS-8) | 2024-10-22 08:00 | 2024-10-22 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, BPWF | 1097L (356s Milo  611s Amber), 611s T1 (611s Amber), 611s T2 (611s Amber), 356s 789 (356s Milo), 611s 89-B1 (611s Amber), 611s 89-T2 (611s Amber), 611s 52-240-2 (611s Amber), 611s 89-T1 (611s Amber), 611s 52-240-1 (611s Amber) | 2024-10-22 09:00 | 2024-10-24 19:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 1097L (356s Milo  611s Amber) | 2024-10-22 09:00 | 2024-10-24 19:00 | N | Y |  | Line |  |  | For Information Only
ATCO | 7L159 (770s Three Hills - 7L159 tap) | 2024-10-22 10:00 | 2024-10-26 10:05 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 38s 75 (38s East Edmonton), 38s 4252 (38s East Edmonton) | 2024-10-23 07:00 | 2024-10-23 18:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2024-10-23 07:00 | 2024-10-28 14:25 | N | Y |  | Line |  | Work was completed early | 240 kV
ALTALINK | 38s 738W (38s East Edmonton), 738L (38s East Edmonton - 738AL tap) | 2024-10-23 07:00 | 2024-10-23 18:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake) | 2024-10-23 07:15 | 2024-10-28 17:45 | N | N |  | Line |  |  | Limits Ratings, Over/Under Voltage, Pre-Condition
ALTALINK | 676L (244s Bowmanton - 523s Bullshead), 523s 676 (523s Bullshead), 244s 676 (244s Bowmanton), 244s 2252 (244s Bowmanton), 244s 2152 (244s Bowmanton) | 2024-10-23 07:30 | 2024-10-24 16:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 310P 3352 (310p Sundance) | 2024-10-23 08:00 | 2024-10-23 09:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-10-23 08:00 | 2024-10-23 16:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 1.8TR (SS-1) | 2024-10-23 08:00 | 2024-10-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.83L (SS-1 - SS-8) | 2024-10-23 08:00 | 2024-10-23 12:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 190L (17s Benalto - 320p Keephills), 320p 652 (320p Keephills), 320p 552 (320p Keephills), 17s 190N (17s Benalto) | 2024-10-23 09:00 | 2024-10-23 15:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Restricts Generation, Affects Cranking Path
ENMAX | 40.1TR (SS-40) | 2024-10-23 12:00 | 2024-10-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.85L (SS-1 - SS-8) | 2024-10-23 12:00 | 2024-10-23 16:00 | N | N |  | Line |  |  | Pre-Condition
EPCOR | T3 (Meadowlark), M724 (Meadowlark), M723 (Meadowlark) | 2024-10-24 07:00 | 2024-10-24 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 746L (700L tap - 746AL tap), 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2024-10-24 07:00 | 2024-10-24 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.81L (SS-11 - SS-13), 11B138-11.81 (SS-11), 13B138-11.81 (SS-13) | 2024-10-24 08:00 | 2024-10-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 1.82L (SS-1 - SS-5) | 2024-10-24 08:00 | 2024-10-24 16:00 | N | N |  | Line |  |  | For Information Only
ENMAX | 39.3TR (SS-39) | 2024-10-24 08:00 | 2024-10-24 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 903L (17s Benalto - 320p Keephills), 320p 2052 (320p Keephills), 320p 2152 (320p Keephills) | 2024-10-24 09:00 | 2024-10-24 15:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 39.4TR (SS-39) | 2024-10-24 12:00 | 2024-10-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.84L (SS-1 - SS-5) | 2024-10-25 08:00 | 2024-10-25 16:00 | N | N |  | Line |  |  | Pre-Condition
ALTALINK | 1045AL (320p Keephills - 1045L tap), 320p 1352 (320p Keephills) | 2024-10-25 09:00 | 2024-10-25 15:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV
ENMAX | 25B240-D140 (SS-25) | 2024-10-25 10:11 | 2024-11-04 10:45 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 14.1C (SS-14), 14.2C (SS-14) | 2024-10-26 08:00 | 2024-10-26 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20) | 2024-10-26 08:00 | 2024-10-26 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 1 (250p Bighorn Plant), 250p 11 (250p Bighorn Plant) | 2024-10-26 08:00 | 2024-10-26 12:00 | N | Y |  | Circuit Breaker, Switch |  |  | Restricts Generation
ALTALINK, TRANSALTA | 320p 3052 (320p Keephills), 320p 2952 (320p Keephills), 320p GT3 (320p Keephills) | 2024-10-26 09:00 | 2024-10-26 15:00 | N | Y |  | Circuit Breaker, Transformer |  |  | For Information Only, Restricts Generation
ENMAX | 1.80L (SS-1 - SS-28) | 2024-10-26 12:00 | 2024-10-26 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 22 (250p Bighorn Plant) | 2024-10-26 12:01 | 2024-10-26 16:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 827L (28s West Brooks - 121s Brooks) | 2024-10-26 17:30 | 2024-10-26 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 72RV4 (EP 511s Victoria - Rossdale), EP 511s V726 (EP 511s Victoria), EP 511s V727 (EP 511s Victoria) | 2024-10-27 07:00 | 2024-10-27 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.82L (SS-1 - SS-5), 5B138-1.82 (SS-5) | 2024-10-27 08:00 | 2024-10-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
CascadeP | 1047s T20 (1047s Whisky Jack), 1047s GS003 (1047s Whisky Jack), 1047s GS005 (1047s Whisky Jack) | 2024-10-27 08:00 | 2024-11-02 12:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK, EPCOR | 1043L (320p Keephills - 367s Harry Smith), 320p 252 (320p Keephills), 320p 352 (320p Keephills) | 2024-10-27 09:00 | 2024-11-05 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), EP 511s Victoria T1 (EP 511s Victoria), RV728 (Rossdale), EP 511s V729 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), EP 511s VDS1 (EP 511s Victoria), EP 511s VAB1 (EP 511s Victoria) | 2024-10-28 07:00 | 2024-11-07 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | EP 803s T3 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton) | 2024-10-28 07:00 | 2024-11-01 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | M723 (Meadowlark) | 2024-10-28 07:00 | 2024-11-02 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
NRGREEN | NRG3 NRGreen Cogen Generator Test | 2024-10-28 07:00 | 2025-01-15 16:30 | N | N |  | Unit
EPCOR | 1098L (EP 805s Jasper - Poundmaker), EP 805s J2407 (EP 805s Jasper), EP 805s J2401 (EP 805s Jasper) | 2024-10-28 07:00 | 2024-10-28 14:19 | N | Y |  | Line, Circuit Breaker |  | Work was completed early. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 24.1TR (SS-24) | 2024-10-28 08:00 | 2024-11-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.2TR (SS-33) | 2024-10-28 08:00 | 2024-10-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.1TR (SS-38) | 2024-10-28 08:00 | 2024-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2024-10-28 10:00 | 2024-10-31 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24), 74s 24.83X (74s Janet), 24B138-24.83 (SS-24) | 2024-10-28 12:30 | 2024-10-31 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 28s 25 (28s West Brooks), 853L (28s West Brooks - 853AL tap) | 2024-10-28 13:00 | 2024-11-02 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation
ALTALINK | 89s 1752 (89s Ellerslie) | 2024-10-28 13:30 | 2024-10-31 17:30 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39) | 2024-10-29 06:00 | 2024-10-29 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | GNR2 Genesee Repower 2 Generator Test | 2024-10-29 07:00 | 2024-11-30 19:00 | N | N |  | Unit
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake), 848s 903 (848s Ruth Lake), 848s 906 (848s Ruth Lake) | 2024-10-29 08:00 | 2024-10-30 16:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 763L (158s Vauxhall - 763AL tap), 763L (28s West Brooks - 763AL tap) | 2024-10-29 08:00 | 2024-10-29 08:16 | N | Y |  | Line |  |  | Pre-Condition
ENMAX | 3.3TR (SS-3) | 2024-10-29 08:00 | 2024-10-29 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 37.2TR (SS-37) | 2024-10-29 08:00 | 2024-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34) | 2024-10-29 08:00 | 2024-10-29 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 706 (802s Michichi Creek), 804s 701 (804s Wintering Hills) | 2024-10-29 09:00 | 2024-11-05 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 939s 1216R (939s Livock) | 2024-10-29 10:00 | 2024-10-29 16:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
ENMAX | 3.4TR (SS-3) | 2024-10-29 12:00 | 2024-10-29 16:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 25B240-D138 (SS-25) | 2024-10-30 08:00 | 2024-11-13 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 11.1TR (SS-11) | 2024-10-30 08:00 | 2024-10-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 215L (38s East Edmonton - 215AL tap), 38s 215N (38s East Edmonton) | 2024-10-30 08:00 | 2024-10-31 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 11 (250p Bighorn Plant) | 2024-10-30 09:00 | 2024-10-30 18:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK, EPCOR | 1043L (320p Keephills - 367s Harry Smith), 320p 352 (320p Keephills), 320p 252 (320p Keephills) | 2024-10-30 10:15 | 2024-11-05 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 763L (158s Vauxhall - 763AL tap), 763L (28s West Brooks - 763AL tap) | 2024-10-30 15:45 | 2024-10-30 16:01 | N | Y |  | Line |  |  | Pre-Condition
Syncrude, ATCO | RL2 (848s Ruth Lake - D05), 848s 902 (848s Ruth Lake), 848s 907 (848s Ruth Lake) | 2024-10-31 08:00 | 2024-11-01 16:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 103s 352 (103s Goose Lake) | 2024-10-31 09:00 | 2024-10-31 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 103s 652 (103s Goose Lake) | 2024-10-31 12:30 | 2024-10-31 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | K722 (Kennedale) | 2024-11-01 07:00 | 2024-11-01 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 37s 726E (37s North Calder) | 2024-11-01 07:15 | 2024-11-01 17:45 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 522L (320p Keephills - 133L tap), 320p T4 (320p Keephills), 320p T5 (320p Keephills), 320p 169 (320p Keephills), 320p 170 (320p Keephills) | 2024-11-02 07:30 | 2024-11-02 16:30 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ENMAX | 36B138-36BT3 (SS-36) | 2024-11-02 08:00 | 2024-11-02 12:00 | N | N |  | Circuit Breaker |  |  | For Information Only
BSSL | ACD1 Big Sky Solar Generator Test | 2024-11-02 08:00 | 2025-01-31 16:00 | N | N |  | Unit
ENMAX | 7.84L (SS-7 - SS-36), 36B138-7.84 (SS-36), 7B138-7.84 (SS-7) | 2024-11-02 12:00 | 2024-11-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CascadeP | 1047s T10 (1047s Whisky Jack), 1047s GS006 (1047s Whisky Jack), 1047s GS001 (1047s Whisky Jack) | 2024-11-02 13:00 | 2024-11-05 12:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 814L (28s West Brooks - 121s Brooks), 28s 814E (28s West Brooks) | 2024-11-02 17:30 | 2024-11-02 18:00 | N | N |  | Line, Switch |  |  | Over/Under Voltage, Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 11B138-11.82 (SS-11), 14B138-11.82 (SS-14), 14.1C (SS-14), 14.2C (SS-14), SW83 (SS-14), SW87 (SS-14), 14MD138-14.1TR (SS-14), 14MD138-14.3TR (SS-14) | 2024-11-03 08:00 | 2024-11-03 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Shunts, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 848s 902T (848s Ruth Lake) | 2024-11-04 07:00 | 2024-11-06 18:00 | N | Y |  | Transformer |  | Back in service | 240 kV
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 72KN23 (Kennedale - Namao), K723 (Kennedale), K724 (Kennedale), 987s CK725 (987s Clover Bar), KDS6 (Kennedale) | 2024-11-04 07:00 | 2024-11-07 19:39 | N | N |  | Line, Circuit Breaker, Switch |  | In service early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark), 72PM25 (Poundmaker - Meadowlark), M724 (Meadowlark), M725 (Meadowlark), M726 (Meadowlark), PM721 (Poundmaker), GDS17 (Garneau) | 2024-11-04 07:00 | 2024-11-08 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T4 (Rossdale) | 2024-11-04 07:00 | 2024-11-15 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 816s P2406 (816s Petrolia), EP 805s J2403 (EP 805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s JDS25 (EP 805s Jasper), 816s PDS14 (816s Petrolia) | 2024-11-04 07:00 | 2024-11-05 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s GT1 (987s Clover Bar) | 2024-11-04 07:00 | 2024-11-07 10:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR | 330P GT2 (330p Genesee), 330p 1204 (330p Genesee), 330p 1205 (330p Genesee), 330p 12GT2D (330p Genesee) | 2024-11-04 07:00 | 2024-11-08 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Restricts Generation
ALTALINK | 37s 138kV Bus (37s North Calder), 37s T5 (37s North Calder), 37s T6 (37s North Calder), 37s 4 (37s North Calder), 37s 1 (37s North Calder) | 2024-11-04 07:30 | 2024-11-06 15:30 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  | Done Early | 240 kV, For Information Only
ENMAX | 14.3TR (SS-14) | 2024-11-04 08:00 | 2024-11-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 344s T2 (344s Warner), 67s 508X (67s Stirling) | 2024-11-04 08:00 | 2024-11-05 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ATCO, CNRL | 838s 75-BC-1916 (838s Horizon Mining) | 2024-11-04 08:00 | 2024-11-06 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO | 7L760 (7LA760 tap - 7LC760 tap) | 2024-11-04 08:00 | 2024-11-07 21:22 | N | N |  | Line |  | Completed Early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CODP | MCH1 Michichi Creek Generator Test | 2024-11-04 08:00 | 2024-11-21 01:00 | N | N |  | Unit
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar), 987s C2403 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s CDS36 (987s Cloverbar) | 2024-11-04 09:30 | 2024-11-19 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar), 38s 7152 (38s East Edmonton), 38s 7252 (38s East Edmonton), 38s 915N (38s East Edmonton) | 2024-11-04 09:30 | 2024-11-19 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2024-11-04 10:00 | 2024-11-08 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 951s 901T (951s Thickwood Hills), 951s 902T (951s Thickwood Hills), 951s SVC (951s Thickwood), 951s 919 (951s Thickwood Hills) | 2024-11-04 10:00 | 2024-11-08 16:00 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 15s T2 (15s Fort Macleod) | 2024-11-05 07:30 | 2024-11-06 16:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel), 930s 719 (930s Arcenciel) | 2024-11-05 08:00 | 2024-11-08 16:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 610L (83s Taber - 336s Fincastle), 172L (83s Taber - 172EL tap), 83s T1 (83s Taber), 83s C2 (83s Taber), 83s 65 (83s Taber), 83s 610 (83s Taber), 83s 172W (83s Taber), 336s 610 (336s Fincastle) | 2024-11-05 09:00 | 2024-11-06 17:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2024-11-05 09:00 | 2024-11-08 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 421s C1 (421s Hays) | 2024-11-05 09:00 | 2024-11-12 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 557s CD2401 (557s Castle Downs), 557s CD2403 (557s Castle Downs), 37s 87 (37s North Calder) | 2024-11-06 07:00 | 2024-11-12 07:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 1164L (816s Petrolia - EP Riverview), RW2401 (EP Riverview), RW2402 (EP Riverview), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia), 816s PDS12 (816s Petrolia), RWDS11 (EP Riverview) | 2024-11-06 07:00 | 2024-11-08 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 14.4TR (SS-14) | 2024-11-06 08:00 | 2024-11-07 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s GT3 (987s Clover Bar) | 2024-11-07 07:00 | 2024-11-11 10:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 2.82L (SS-2 - SS-5), 2B138-D86 (SS-2), 2B138-D85 (SS-2), MD88 (SS-2), MD89 (SS-2), MD90 (SS-2), MD91 (SS-2) | 2024-11-07 08:00 | 2024-11-08 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO, CNRL | 838s 75-BC-1912 (838s Horizon Mining) | 2024-11-07 08:00 | 2024-11-08 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 925L (63s Red Deer - 74s Janet), 74s 2052 (74s Janet), 74s 2152 (74s Janet), 74s 925N (74s Janet) | 2024-11-07 09:00 | 2024-11-07 14:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV
ENMAX | 162.3TR (SS-162) | 2024-11-08 08:00 | 2024-11-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B240-RB131 (SS-162) | 2024-11-08 08:00 | 2024-11-08 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162B240-RB132 (SS-162) | 2024-11-08 12:00 | 2024-11-08 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 816s P2404 (816s Petrolia) | 2024-11-08 16:00 | 2025-02-07 17:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ALTALINK, Travers2SolarLP | 1005AL (991s Little Bow - 1005L tap), 1005L (120s Picture Butte - 1005AL tap), 1005L (356s Milo - 1005AL tap), 991s 240-1 (991s Little Bow) | 2024-11-08 17:00 | 2024-11-08 23:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Restricts Generation
ENMAX | 2.81L (SS-2 - SS-9), 9B138-2.81 (SS-9) | 2024-11-09 08:00 | 2024-11-09 12:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO, CNRL | 838s 75-BC-1911 (838s Horizon Mining) | 2024-11-09 08:00 | 2024-11-11 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 21.1C (SS-21) | 2024-11-09 08:00 | 2024-11-09 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33) | 2024-11-09 12:00 | 2024-11-09 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 38s C1 (38s East Edmonton) | 2024-11-09 16:50 | 2024-11-14 07:59 | N | N |  | Shunts |  |  | Pre-Condition
EPCOR | 987s GT2 (987s Clover Bar) | 2024-11-10 07:00 | 2024-11-19 10:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR | 987s SST2 (987s Clover Bar) | 2024-11-10 07:00 | 2024-11-11 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 41.84L (SS-41 - SS-54), 54B138-41.84 (SS-54), 41B138-41.84 (SS-41) | 2024-11-10 08:00 | 2024-11-10 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.81L (SS-40 - SS-41), 40B138-40.81 (SS-40), 41B138-40.81 (SS-41) | 2024-11-10 12:01 | 2024-11-10 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, BHE | 879L (244s Bowmanton - 879AL tap), 879L (368s Burdett - 879L tap), 879AL (719s Rattlesnake Ridge - 879L tap), 368s 879 (368s Burdett), 719s 138CB1 (719s Rattlesnake Ridge) | 2024-11-11 07:00 | 2024-11-11 11:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee), 330p 1208 (330p Genesee), 330p 1209 (330p Genesee), 330p 1209A (330p Genesee), 330p 1208B (330p Genesee), 330p 1209LD (330p Genesee) | 2024-11-11 07:00 | 2024-11-13 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 13.4TR (SS-13), 13.60L (SS-13 - SS-27), 13B69-13.60 (SS-13) | 2024-11-11 08:00 | 2024-11-14 14:00 | N | N |  | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 15s 138kV Bus1 (15s Fort Macleod), 180L (15s Fort Macleod - 180AL tap), 463L (15s Fort Macleod - 463AL tap), 15s T1 (15s Fort Macleod), 15s 180N (15s Fort Macleod), 15s 463 (15s Fort Macleod), 15s 452 (15s Fort Macleod), 15s 22 (15s Fort Macleod) | 2024-11-11 09:00 | 2024-11-22 12:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 879L (244s Bowmanton - 879AL tap) | 2024-11-11 11:01 | 2024-11-21 14:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
EPCOR | 816s P2402 (816s Petrolia) | 2024-11-12 07:00 | 2024-12-15 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | T1 (Garneau), G721 (Garneau), G722 (Garneau), G726 (Garneau), 72MG16 (Garneau - Meadowlark), M725 (Meadowlark) | 2024-11-12 07:00 | 2024-12-06 17:00 | N | N |  | Transformer, Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | CV5 (EP 511s Victoria - 557s Castle Downs), 920L (37s North Calder - 557s Castle Downs), 557s T1 (557s Castle Downs), 557s CD2403 (557s Castle Downs) | 2024-11-12 07:00 | 2024-11-15 13:27 | N | Y |  | Line, Transformer, Circuit Breaker |  | Outage returned early. | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 1041L (370s North Lethbridge - 554s Travers), 370s 51 (370s North Lethbridge), 370s 47 (370s North Lethbridge) | 2024-11-12 07:00 | 2024-11-14 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2024-11-12 07:00 | 2024-11-15 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 69s 723E (69s North Barrhead), 723L (69s North Barrhead - 724L tap) | 2024-11-12 07:30 | 2024-11-12 15:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 2.2TR (SS-2) | 2024-11-12 08:00 | 2024-11-13 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B240-RB134 (SS-162) | 2024-11-12 08:00 | 2024-11-12 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 32.3TR (SS-32) | 2024-11-12 08:00 | 2024-11-16 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47B138-771 (SS-47) | 2024-11-12 08:00 | 2024-11-12 12:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2024-11-12 08:30 | 2024-11-12 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 845s 703 (845s Big Mountain) | 2024-11-12 09:30 | 2024-11-12 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 37.1TR (SS-37), 37B138-37.81 (SS-37), 37MD138-37.1TR (SS-37) | 2024-11-12 11:00 | 2024-11-14 07:59 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 284s T1 (284s Nose Creek), 688L (653s Summit - 688AL tap), 688AL tap | 2024-11-12 12:00 | 2024-11-15 12:00 | N | N |  | Transformer, Line, Station |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 162B138-RB80 (SS-162) | 2024-11-12 12:01 | 2024-11-12 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47B138-771/1 (SS-47) | 2024-11-12 12:01 | 2024-11-12 18:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 545s T1 (545s Provost) | 2024-11-12 13:30 | 2024-11-20 15:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L47 (718s Parsons Creek - 848s Ruth Lake), 848s 702 (848s Ruth Lake) | 2024-11-13 08:00 | 2024-11-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 6.82L (SS-6 - SS-41), 41B138-6.82 (SS-41), 6B138-6.82 (SS-6) | 2024-11-13 08:00 | 2024-11-13 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29EDD-71 29PT-234 (29EDD-71) | 2024-11-13 08:00 | 2024-12-03 18:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 24.2TR (SS-24) | 2024-11-13 08:00 | 2024-11-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2024-11-13 08:00 | 2024-11-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.1TR (SS-162) | 2024-11-13 08:00 | 2024-11-13 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 9L59 (801s Anderson - 9LA59 tap), 801s 902 (801s Anderson), 801s 903 (801s Anderson) | 2024-11-13 09:00 | 2024-11-14 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 706 (802s Michichi Creek), 804s 701 (804s Wintering Hills) | 2024-11-13 09:00 | 2024-11-18 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L81 (791s Rainbow Lake - BCH Harvest Energy FNC Tap), 791s 702 (791s Rainbow Lake) | 2024-11-13 09:00 | 2024-11-22 11:14 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 244s 3152 (244s Bowmanton), 244s 3252 (244s Bowmanton), 879L (244s Bowmanton - 879AL tap) | 2024-11-13 12:00 | 2024-11-13 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 330p 1208 (330p Genesee) | 2024-11-14 07:00 | 2024-11-15 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 113L (20s Ghost - 33s Spray) | 2024-11-14 07:00 | 2024-11-17 16:25 | N | N |  | Line |  | Work Completed Early | Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 723L (150s Clyde - 438s Westlock), 150s 723W (150s Clyde) | 2024-11-14 07:30 | 2024-11-14 15:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton) | 2024-11-14 08:00 | 2024-11-30 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 37.1TR (SS-37), 37B138-37.81 (SS-37), 37MD138-37.1TR (SS-37) | 2024-11-14 08:00 | 2024-11-18 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 25B240-D142 (SS-25) | 2024-11-14 08:00 | 2024-11-14 12:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162.2TR (SS-162) | 2024-11-14 08:00 | 2024-11-15 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 212s T1 (212s N.E.Lacombe) | 2024-11-14 08:30 | 2024-11-14 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 732s 902T (732s Mitsue), 732s 901 (732s Mitsue), 732s 906 (732s Mitsue), 732s 503R (732s Mitsue) | 2024-11-14 09:00 | 2024-11-14 17:00 | N | Y |  | Transformer, Circuit Breaker, Shunts |  | . | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 31B138-31.84 (SS-31) | 2024-11-14 12:00 | 2024-11-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 164s T1 (164s Empress Liquids), 164s T2 (164s Empress Liquids), 164s 760A (164s Empress Liquids), 164s 3 (164s Empress Liquids), 164s 4 (164s Empress Liquids) | 2024-11-15 07:30 | 2024-11-15 17:30 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 25B240-D138 (SS-25) | 2024-11-15 08:00 | 2024-11-15 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-11-15 08:00 | 2024-11-15 12:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ATCO | 7L71 (848s Ruth Lake - 2082s Dog Rib), 848s 701 (848s Ruth Lake) | 2024-11-15 08:00 | 2024-11-15 14:42 | N | N |  | Line, Circuit Breaker |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L139 (819s Whitby Lake - 7LA139 tap) | 2024-11-15 09:00 | 2024-11-15 15:30 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L70 (801s Anderson - 946s Oakland), 801s 903 (801s Anderson), 801s 904 (801s Anderson), 801S 903B (801s Anderson), 801S 904B (801s Anderson), 946s 9L70D2 (946s Oakland) | 2024-11-15 09:00 | 2024-11-16 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 25B240-D139 (SS-25) | 2024-11-15 12:01 | 2024-11-15 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 8.5TR (SS-8) | 2024-11-16 08:00 | 2024-11-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7), 7B138-7.82 (SS-7), 42s 7 (42s Sarcee) | 2024-11-17 08:00 | 2024-11-17 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 9L950 (132s Ware Junction - 801s Anderson), 801s 911 (801s Anderson), 801s 912 (801s Anderson), 801S 911B (801s Anderson), 801S 912B (801s Anderson), 132s 950N (132s Ware Junction) | 2024-11-17 09:00 | 2024-11-18 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 7.84L (SS-7 - SS-36), 7B138-7.84 (SS-7), 36B138-7.84 (SS-36) | 2024-11-17 12:00 | 2024-11-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 805 (330p Genesee), 330p 1210 (330p Genesee), 330p 1214 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee), 330p 12TC1D (330p Genesee) | 2024-11-18 07:00 | 2024-11-19 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
EPCOR | EP 803s T2 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s LAB2 (EP 803s Lambton) | 2024-11-18 07:00 | 2024-11-22 10:50 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 72RV4 (EP 511s Victoria - Rossdale), RV726 (Rossdale), EP 511s V727 (EP 511s Victoria), EP 511s V726 (EP 511s Victoria), EP 511s VDS15 (EP 511s Victoria) | 2024-11-18 07:00 | 2024-11-29 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 19s 240kV Bus A (19S Wabamun), 902L (19s Wabamun - 310p Sundance), 905L (19s Wabamun - 37s North Calder), 19s T10 (19s Wabamun), 310p 752 (310p Sundance), 310p 852 (310p Sundance), 19s 49 (19s Wabamun), 19s 902 (19s Wabamun), 19s 905 (19s Wabamun), 19s 50 (19s Wabamun), 19s 52 (19s Wabamun), 19s 97 (19s Wabamun) | 2024-11-18 07:00 | 2024-11-21 18:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, DOW | 166s T1 (166s Dow Chemical Fort Saskatchewan) | 2024-11-18 07:00 | 2024-11-19 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK, TRANSALTA | 733L (179s Gleichen - 428s Namaka), 179s 733 (179s Gleichen), 428s 733X (428s Namaka) | 2024-11-18 07:30 | 2024-11-19 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 162.4TR (SS-162) | 2024-11-18 08:00 | 2024-11-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 344s T2 (344s Warner), 67s 508X (67s Stirling), 344s 1 (344s Warner), 344s 16 (344s Warner) | 2024-11-18 08:00 | 2024-11-22 13:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 31.3TR (SS-31) | 2024-11-18 08:00 | 2024-11-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 65B240-D130 (SS-65) | 2024-11-18 08:00 | 2024-11-18 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | 2024-11-18 10:00 | 2024-11-25 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 901L (74s Janet - 901AL tap), 901L (63s Red Deer - 901AL tap), 901AL (64s East Crossfield - 901L tap), 64s 901 (64s East Crossfield), 74s 2552 (74s Janet), 74s 2452 (74s Janet), 74s 901N (74s Janet) | 2024-11-18 11:30 | 2024-11-18 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 9L36 (825s Whitefish Lake - 826s Marguerite Lake), 825s 902 (825s Whitefish Lake), 825s 906 (825s Whitefish Lake), 825s 902B (825s Whitefish Lake), 825s 906A (825s Whitefish Lake), 826s 9L36D1 (826s Marguerite Lake) | 2024-11-18 13:00 | 2024-11-20 11:30 | N | Y |  | Line, Circuit Breaker, Switch |  | Back early | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s 2552 (74s Janet) | 2024-11-18 17:01 | 2024-11-22 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 789L (898s Heart Lake - 789BL tap) | 2024-11-19 07:00 | 2024-11-21 18:00 | N | Y |  | Line |  |  | For Information Only
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 74s 23.80W (74s Janet), 23B138-23.80 (SS-23) | 2024-11-19 07:00 | 2024-11-22 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65B240-D135 (SS-65) | 2024-11-19 08:00 | 2024-11-19 17:19 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 11.81L (SS-11 - SS-13), 13.82L (SS-13 - SS-22), 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13.2TR (SS-13), 11B138-11.81 (SS-11), 13B138-11.81 (SS-13), 13B138-13.82 (SS-13), 13B69-13.60 (SS-13), 27B69-13.60 (SS-27), 22B138-13.82 (SS-22), SW84 (SS-13), 13MD138-13.2TR (SS-13), 13MD138-13.4TR (SS-13) | 2024-11-19 08:00 | 2024-12-12 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2024-11-19 10:00 | 2024-11-24 16:00 | N | N |  | Line |  |  | For Information Only
EPCOR | 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial) | 2024-11-20 07:00 | 2024-11-22 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 648s T1 (648s Metiskow) | 2024-11-20 07:00 | 2024-12-02 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, DOW | 166s T2 (166s Dow Chemical Fort Saskatchewan), 166s CP234 (166s Dow Chemical Fort Saskatchewan) | 2024-11-20 07:00 | 2024-11-21 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), 72JW19 (EP 805s Jasper - Woodcroft), 805s T1 (805s Jasper), EP 805s J722 (EP 805s Jasper), EP 805s J724 (EP 805s Jasper), EP 805s J2401 (EP 805s Jasper), EP 805s J2403 (EP 805s Jasper), M721 (Meadowlark), W721 (Woodcroft), EP 805s JAB5 (EP 805s Jasper), EP 805s JAB1 (EP 805s Jasper), EP 805s JAB2 (EP 805s Jasper) | 2024-11-20 07:00 | 2024-11-22 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ATCO | 722s 702T (722s Crystal Lake) | 2024-11-20 08:00 | 2024-11-21 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.2TR (SS-16) | 2024-11-20 08:00 | 2024-11-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2024-11-20 08:30 | 2024-11-20 17:30 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar), 987s C2404 (987s Clover Bar), 987s C2406 (987s Clover Bar), 71s 1252 (71s Lamoureux), 71s 1352 (71s Lamoureux) | 2024-11-20 09:30 | 2024-12-06 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 1048L (59s Peigan - 138s Windy Flats), 59s 852 (59s Peigan), 59s 952 (59s Peigan), 138S 1048 (138s Windy Flats) | 2024-11-20 10:00 | 2024-11-21 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72RG7 (Garneau - Rossdale), RG725 (Rossdale) | 2024-11-20 12:00 | 2024-11-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 330p 500kV Bus 2 (330p Genesee), 330p 12TC2 (330p Genesee), 330p 1211 (330p Genesee), 330p 1215 (330p Genesee), 330p 809 (330p Genesee), 330p 1203 (330p Genesee), 330p 1206 (330p Genesee), 330p 1209 (330p Genesee), 330p 12TC2D (330p Genesee) | 2024-11-21 07:00 | 2024-11-22 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK, TRANSALTA | 876L (179s Gleichen - 253s Blackie), 179s 876 (179s Gleichen), 253s 876 (253s Blackie) | 2024-11-21 07:00 | 2024-11-25 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 65B240-D131 (SS-65) | 2024-11-21 08:00 | 2024-11-22 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook), 510s 2952 (510s Sunnybrook), 510s 3052 (510s Sunnybrook), 510s 49 (510s Sunnybrook), 510s 51 (510s Sunnybrook), 330p 1238LD (330p Genesee) | 2024-11-21 09:00 | 2024-11-21 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 716s 701 (716s Lloydminster) | 2024-11-21 10:00 | 2024-11-21 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK, BHE | 879L (244s Bowmanton - 879AL tap), 879L (368s Burdett - 879L tap), 879AL (719s Rattlesnake Ridge - 879L tap), 368s 879 (368s Burdett), 719S 35CB1 (719s Rattlesnake Ridge), 719s 138MDS1 (719s Rattlesnake Ridge) | 2024-11-21 14:00 | 2024-11-21 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Restricts Generation
BHE Canada | MATL (120s Picture Butte - Montana) | 2024-11-22 08:00 | 2024-11-22 14:00 | Y | Y |  | Line |  |  | 240 kV, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20), 8A9 (SS-1) | 2024-11-22 08:00 | 2024-11-22 12:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 783s 701T (783s Cadotte River) | 2024-11-22 09:00 | 2024-11-22 17:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 635EDD-1000 635-752-162 (635EDD-1000) | 2024-11-22 11:30 | 2024-11-22 13:50 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK, Lethbridge | 725L (674s Bowron - 725AL tap), 674s 725W (674s Bowron) | 2024-11-23 07:30 | 2024-11-25 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, TRANSALTA | 33s T2 (33s Spray), 33s 2 (33s Spray) | 2024-11-23 08:00 | 2024-11-23 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 37B138-37.82 (SS-37), 74s 37.82W (74s Janet) | 2024-11-23 08:00 | 2024-11-23 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon), 5s 1652 (5s East Calgary), 5s 1552 (5s East Calgary), 5s 937 (5s East Calgary) | 2024-11-23 08:00 | 2024-11-26 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 3.3TR (SS-3) | 2024-11-23 08:00 | 2024-11-23 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.4TR (SS-3) | 2024-11-24 08:00 | 2024-11-24 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 41.84L (SS-41 - SS-54), 41B138-41.84 (SS-41), 54B138-41.84 (SS-54) | 2024-11-24 08:00 | 2024-11-24 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 41.1C (SS-41), 41B138-41.1CAP (SS-41) | 2024-11-24 12:01 | 2024-11-24 18:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK, EPCOR | 1239L (330p Genesee - 510s Sunnybrook), 330p 1205 (330p Genesee), 330p 1206 (330p Genesee), 330p 1239LD (330p Genesee) | 2024-11-25 07:00 | 2024-11-29 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), M721 (Meadowlark), EP 805s J722 (EP 805s Jasper) | 2024-11-25 07:00 | 2024-11-30 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Rossdale), R721 (Rossdale), R723 (Rossdale) | 2024-11-25 07:00 | 2024-11-25 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow) | 2024-11-25 07:15 | 2024-12-01 09:45 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 2B138-D90 (SS-2), MD98 (SS-2), MD99 (SS-2) | 2024-11-25 08:00 | 2024-11-26 16:00 | N | N |  | Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK, ATCO | 702L (137s Sedgewick - 757s Battle River), 757s 708 (757s Battle River) | 2024-11-25 08:00 | 2024-12-07 18:27 | N | Y |  | Line, Circuit Breaker |  | 702L returned early on Dec.07, 2024. | Overload, Pre-Condition, Restricts Generation
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB133 (SS-162), 162B240-RB132 (SS-162) | 2024-11-25 08:00 | 2024-11-28 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 498s T2 (498s Tilley) | 2024-11-25 08:00 | 2024-11-26 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.1TR (SS-2) | 2024-11-25 08:00 | 2024-11-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47.2TR (SS-47) | 2024-11-25 08:00 | 2024-11-28 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 41B138-33.83 (SS-41), 33B138-33.83 (SS-33) | 2024-11-25 08:00 | 2024-11-25 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L157 (837s Mahihkan - 970s Bourque), 837s 701 (837s Mahihkan), 970s 7L157D2 (970s Bourque) | 2024-11-25 08:30 | 2024-11-28 14:30 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 74s 2452 (74s Janet) | 2024-11-25 09:30 | 2024-12-10 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 965L (326s Murray lake - 244s Bowmanton), 326s 352 (326s Murray Lake), 326s 452 (326s Murray Lake), 326s 965 (326s Murray Lake) | 2024-11-25 11:00 | 2024-11-27 14:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ENMAX | 40.81L (SS-40 - SS-41), 41B138-40.81 (SS-41), 40B138-40.81 (SS-40) | 2024-11-25 12:00 | 2024-11-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2024-11-25 12:30 | 2024-11-26 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 498s T1 (498s Tilley) | 2024-11-26 07:00 | 2024-11-26 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 15s 725 (15s Fort Macleod), 725L (15s Fort MacLeod - 725BL tap) | 2024-11-26 07:30 | 2024-11-28 07:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 62s 207 (62s Brazeau Plant), 62s T5 (62s Brazeau Plant), 62s T7 (62s Brazeau Plant), 62s 138kV South Bus (62s Brazeau Plant), 62s 209 (62s Brazeau Plant), 62s 210 (62s Brazeau Plant), 62s 215 (62s Brazeau Plant) | 2024-11-26 07:30 | 2024-11-26 16:30 | N | Y |  | Circuit Breaker, Transformer, Bus, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 738L (38s East Edmonton - 738AL tap), 38s 738W (38s East Edmonton) | 2024-11-26 07:30 | 2024-11-26 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2024-11-26 08:00 | 2024-11-26 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO, FMGW | 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s 952-600001 (1024s Granlea), 1024s PS-6005 (1024s Granlea), 1024s PS-6006 (1024s Granlea), 1024s PS-6007 (1024s Granlea), 1024s PS-6008 (1024s Granlea) | 2024-11-26 08:00 | 2024-11-28 17:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 523s 880 (523s Bullshead), 880L (321s Al Rothbauer - 523s Bullshead) | 2024-11-26 08:30 | 2024-11-26 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 804s 701 (804s Wintering Hills), 802s 706 (802s Michichi Creek) | 2024-11-26 09:00 | 2024-12-03 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L97 (801s Anderson - 946s Oakland), 801s 905 (801s Anderson), 801s 906 (801s Anderson), 801S 905B (801s Anderson), 801S 906B (801s Anderson) | 2024-11-26 09:00 | 2024-11-27 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 526s C1 (526s Buffalo Creek) | 2024-11-26 09:30 | 2024-11-26 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 100L (498s Tilley - 895s Suffield) | 2024-11-26 10:30 | 2024-11-26 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 26.83L (SS-26 - SS-65), 26B138-26.83 (SS-26), 32B138-26.81 (SS-32) | 2024-11-26 12:00 | 2024-11-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 719L (263s Strachan - 719AL tap), 263s 719 (263s Strachan) | 2024-11-27 07:00 | 2024-11-28 12:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 950L (132s Ware Junction - 801s Anderson), 132s 240kV North Bus (132s Ware Junction), 132s 24 (132s Ware Junction), 132s 18 (132s Ware Junction), 132s 6 (132s Ware Junction), 132s 3 (132s Ware Junction), 132s 37 (132s Ware Junction), 132s 47 (132s Ware Junction), 132s 950N (132s Ware Junction), 801s 912 (801s Anderson), 801s 911 (801s Anderson) | 2024-11-27 07:00 | 2024-11-27 14:00 | N | Y |  | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 64s T3 (64s East Crossfield) | 2024-11-27 07:30 | 2024-11-27 17:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon), 5s 1152 (5s East Calgary), 5s 1252 (5s East Calgary), 102s 5852 (102s Langdon), 102s 5652 (102s Langdon) | 2024-11-27 08:00 | 2024-11-30 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 8B138-1A0 (SS-8) | 2024-11-27 08:00 | 2024-11-27 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 2B138-D91 (SS-2), MD100 (SS-2), MD101 (SS-2) | 2024-11-27 08:00 | 2024-11-28 16:00 | N | N |  | Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss
BCH | T1 (BCH Natal), 60CB1 (BCH Natal) | 2024-11-27 10:00 | 2024-11-27 14:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2024-11-28 07:00 | 2024-11-28 17:30 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2024-11-28 07:00 | 2024-11-28 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK, Lethbridge, TRANSALTA | 725L (15s Fort MacLeod - 725BL tap), 725L (674s Bowron - 725BL tap), 725BL (240s McBride Lake - 725L tap), 15s 725 (15s Fort Macleod), 674s 725W (674s Bowron), 240s 138CB1 (240s McBride Lake) | 2024-11-28 07:35 | 2024-11-29 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ENMAX | 8B138-2A0 (SS-8) | 2024-11-28 08:00 | 2024-11-28 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L933 (132s Ware Junction - 801s Anderson), 801s 907 (801s Anderson), 801s 908 (801s Anderson) | 2024-11-28 09:00 | 2024-11-29 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 8B138-3A0 (SS-8) | 2024-11-28 12:01 | 2024-11-28 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L160 (837s Mahihkan - 970s Bourque), 837s 703 (837s Mahihkan) | 2024-11-28 14:31 | 2024-11-28 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 706L (410s Josephburg - 706AL tap), 410s 552 (410s Josephburg), 410s 1152 (410s Josephburg), 410s 706X (410s Josephburg) | 2024-11-29 07:00 | 2024-11-29 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
WINNIFRED | WIN1 Winnifred Wind Generator Test | 2024-11-29 08:00 | 2025-04-16 17:00 | N | N |  | Unit
ENMAX | 8B138-4A0 (SS-8) | 2024-11-29 08:00 | 2024-11-29 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2085s 601T (2085s Sheridan), 2085s 601 (2085s Sheridan) | 2024-11-29 11:00 | 2024-11-29 13:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
SUNCOR | 635EDD-1000 635-752-131 (635EDD-1000) | 2024-11-30 07:00 | 2024-11-30 17:00 | N | N |  | Circuit Breaker |  |  | Prevents Normal Events
ENMAX | 15.1TR (SS-15), 15B8-15.1TR (SS-15) | 2024-11-30 08:00 | 2024-11-30 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO, ALTALINK | 9L934 (132s Ware Junction - 801s Anderson), 801s 909 (801s Anderson), 801s 910 (801s Anderson), 801S 909B (801s Anderson), 801s 910B (801s Anderson), 132s 934N (132s Ware Junction) | 2024-11-30 09:00 | 2024-12-01 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 15.2TR (SS-15), 15B8-15.2TR (SS-15) | 2024-11-30 12:00 | 2024-11-30 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6), 41B138-6.82 (SS-41) | 2024-11-30 12:00 | 2024-11-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.1TR (SS-16) | 2024-12-01 08:00 | 2024-12-04 14:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34) | 2024-12-01 08:00 | 2024-12-04 14:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12), 12B138-832L (SS-12), 10B138-832 (SS-10) | 2024-12-02 07:00 | 2024-12-03 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK, Lethbridge | 734L (241s Uplands - 370s North Lethbridge), 241s 734L (241s Uplands), 370s 734X (370s North Lethbridge) | 2024-12-02 07:00 | 2024-12-11 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), RV722 (Rossdale), EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), EP 511s VDS9 (EP 511s Victoria) | 2024-12-02 07:00 | 2024-12-12 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft), T2 (Woodcroft), W725 (Woodcroft), W723 (Woodcroft), W722 (Woodcroft), WAB2 (Woodcroft) | 2024-12-02 07:00 | 2024-12-13 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | N721 (Namao) | 2024-12-02 07:00 | 2024-12-02 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook), 330p 1201 (330p Genesee), 330p 1202 (330p Genesee), 330p 1238LD (330p Genesee) | 2024-12-02 07:00 | 2024-12-06 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, ENMAXEC | 616L (59s Peigan - 616AL tap), 616L (103s Goose Lake - 616AL tap), 616AL (383s Kettles Hill Windfarm - 616L tap), 59s 616 (59s Peigan), 383s 52-S1 (383s Kettles Hill Windfarm), 383s 89-T1 (383s Kettles Hill Windfarm), 383s 89-T2 (383s Kettles Hill Windfarm) | 2024-12-02 07:00 | 2024-12-02 12:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation
ENMAX | 8B138-6A0 (SS-8) | 2024-12-02 08:00 | 2024-12-02 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2024-12-02 08:00 | 2024-12-08 | N | Y |  | Line |  | 7L20 tripped. 7L40 restored to energize 7L80 to get station service back to HR Milner as well as load restored at Kakwa Ridge | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 2.2TR (SS-2) | 2024-12-02 08:00 | 2024-12-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 745AL (411s Obed - 745A1L tap), 411s T1 (411s Obed), 411s 745A (411s Obed) | 2024-12-02 09:00 | 2024-12-10 18:00 | N | N |  | Line, Transformer, Switch |  |  | Pre-Condition
ALTALINK, TRANSALTA | 320p 852 (320p Keephills) | 2024-12-02 09:00 | 2024-12-05 14:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 277s T1 (277s Hayter), 277s 2 (277s Hayter) | 2024-12-02 09:30 | 2024-12-12 17:30 | N | N |  | Transformer, Switch |  |  | For Information Only
ENMAX | 8B138-7A0 (SS-8) | 2024-12-02 12:00 | 2024-12-02 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 164L (103s Goose Lake - 415s Drywood), 415s T1 (415s Drywood), 415s 164 (415s Drywood) | 2024-12-02 12:30 | 2024-12-07 19:00 | N | N |  | Line, Transformer, Switch |  |  | Over/Under Voltage, Pre-Condition
ALTALINK, ATCO | 760L (163s Amoco Empress - 760AL tap), 760L (760AL tap - 7LA760 tap), 164s T1 (164s Empress Liquids), 164s T2 (164s Empress Liquids), 164s 760A (164s Empress Liquids), 163s 760N (163s Amoco Empress), 760L41 (760AL tap), 164s 3 (164s Empress Liquids), 164s 4 (164s Empress Liquids) | 2024-12-03 07:00 | 2024-12-03 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T1 (EP Riverview), RW2401 (EP Riverview), RW2405 (EP Riverview), RWAB1 (EP Riverview) | 2024-12-03 07:00 | 2024-12-04 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow) | 2024-12-03 07:00 | 2024-12-12 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet), 74s 104 (74s Janet) | 2024-12-03 07:00 | 2024-12-20 15:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32), 32B138-26.81 (SS-32), 26B138-26.81 (SS-26) | 2024-12-03 08:00 | 2024-12-03 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s 2952 (244s Bowmanton) | 2024-12-03 08:30 | 2024-12-03 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 751s 701C (751s Hill) | 2024-12-03 09:30 | 2024-12-04 18:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7LA12 tap) | 2024-12-03 10:00 | 2024-12-08 16:00 | N | N |  | Line |  |  | For Information Only
ENMAX | 31.84L (SS-31 - SS-32), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31) | 2024-12-03 12:00 | 2024-12-03 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 244s 2252 (244s Bowmanton) | 2024-12-03 12:30 | 2024-12-03 16:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 100L (498s Tilley - 895s Suffield), 498s 100X (498s Tilley), 895s 100 (895s Suffield) | 2024-12-04 06:00 | 2024-12-08 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12.2TR (SS-12), 12B138-833L (SS-12), 12MD138-12.2TR (SS-12), SW83 (SS-12) | 2024-12-04 07:00 | 2024-12-05 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 5.6TR (SS-5) | 2024-12-04 08:00 | 2024-12-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 833L (SS-2 - SS-12), MD92 (SS-2), MD93 (SS-2), MD94 (SS-2), MD95 (SS-2) | 2024-12-04 08:00 | 2024-12-05 16:00 | N | Y |  | Line, Switch |  |  | Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2024-12-04 09:00 | 2024-12-04 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 786L (799s Coleman - BCH Natal) | 2024-12-04 09:00 | 2024-12-04 15:00 | N | Y |  | Line |  |  | Pre-Condition
ALTALINK, BCH | 1L274 (BCH Natal - BCH Line Creek tap) | 2024-12-04 09:00 | 2024-12-04 15:00 | N | N |  | Line |  |  | Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2024-12-04 09:00 | 2024-12-04 15:00 | Y | Y |  | Line |  |  | 240 kV, Limits ATC
AESO | Path 1 (AIES Islanding) | 2024-12-04 09:00 | 2024-12-04 15:00 | Y | Y |  | Line |  |  | 240 kV, 500 kV, Limits ATC
ALTALINK, BCH | 1201L (520s Bennett - BCH Cranbrook), 5D25 (BCH Cranbrook) | 2024-12-04 09:00 | 2024-12-04 15:00 | Y | Y |  | Line, Switch |  |  | 500 kV, Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition, Affects Cranking Path
ATCO | 7L137 (768s Rowley - 770s Three Hills), 770s 702 (770s Three Hills), 768s 703 (768s Rowley) | 2024-12-04 09:30 | 2024-12-04 14:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2024-12-04 10:00 | 2024-12-04 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 150L (20s Ghost - 150AL tap), 20s 150 (20s Ghost) | 2024-12-05 07:00 | 2024-12-09 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 38s 761N (38s East Edmonton) | 2024-12-05 07:15 | 2024-12-12 17:45 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, ATCO | 515s Fed Pipe Judy Creek, 526L (515s Fed Pipe Judy Creek - 6L126 Tap), 526L (526AL tap - 6L126 tap), 743s 601 (743s Sarah Lake), 126L1 (6L126 tap), 515s 526 (515s Fed Pipe Judy Creek), 515s 11 (515s Fed Pipe Judy Creek) | 2024-12-05 08:00 | 2024-12-05 16:00 | N | N |  | Station, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, TRANSALTA | 179s T1 (179s Gleichen) | 2024-12-05 09:30 | 2024-12-05 12:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 250p 22 (250p Bighorn Plant) | 2024-12-05 10:00 | 2024-12-05 14:00 | N | Y |  | Switch |  |  | Restricts Generation
ENMAX | 2.84L (SS-2 - SS-8), 2B138-D81 (SS-2), 2B138-D82 (SS-2), 7A01 (SS-8) | 2024-12-06 08:00 | 2024-12-07 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR | T1 (Garneau) | 2024-12-06 17:00 | 2024-12-18 18:00 | N | N |  | Transformer |  | Back Early | Pre-Condition
ALTALINK | 202L (61s Lodgepole - 202AL tap), 61s 202N (61s Lodgepole) | 2024-12-07 02:00 | 2024-12-10 07:29 | N | N |  | Line, Circuit Breaker
ENMAX | 41.1TR (SS-41) | 2024-12-07 08:00 | 2024-12-07 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA, CHDI | 514BL (322s Cowley Ridge Windplant - 514L tap), 514L (396s Pincher Creek - 514BL tap), 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck), 322s T3 (322s Cowley Ridge), 396s 514N (396s Pincher Creek), 513s 1 (513s Lundbreck), 322s 5 (322s Cowley Ridge Windplant), 322s 3252 (322s Cowley Ridge Windplant) | 2024-12-08 07:00 | 2024-12-08 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
EPCOR | 330p 1203 (330p Genesee) | 2024-12-09 07:00 | 2024-12-11 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
CMH | MHS-10 MH138-1005 (MHS-10 Box Springs) | 2024-12-09 08:00 | 2024-12-09 12:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.3TR (SS-2) | 2024-12-09 08:00 | 2024-12-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 40.1TR (SS-40) | 2024-12-09 08:00 | 2024-12-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.1TR (SS-33) | 2024-12-09 08:00 | 2024-12-10 18:00 | N | N |  | Transformer |  |  | For Information Only
BCH | T4 (BCH Natal) | 2024-12-09 09:00 | 2024-12-20 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain), 845s 710 (845s Big Mountain), 845s 709 (845s Big Mountain), 749s 7L44D2 (749s Flyingshot Lake) | 2024-12-09 09:30 | 2024-12-11 12:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 244s 240kV Bus 1 (244s Bowmanton), 244s 138kV Bus 1 (244s Bowmanton), 244s T1 (244s Bowmanton), 244s 152 (244s Bowmanton), 244s 452 (244s Bowmanton), 244s 2152 (244s Bowmanton), 244s 2552 (244s Bowmanton), 244s 2189 (244s Bowmanton), 244s 2289 (244s Bowmanton), 244s 2589 (244s Bowmanton) | 2024-12-09 12:00 | 2024-12-12 17:30 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 1CB2 (BCH Natal), 799s 786W (799s Coleman) | 2024-12-10 06:00 | 2024-12-10 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 926L (17s Benalto - 310p Sundance), 310p 2552 (310p Sundance), 310p 2652 (310p Sundance) | 2024-12-10 07:15 | 2024-12-11 17:45 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 202L (61s Lodgepole - 202AL tap), 202L335 (202AL tap), 61s 202N (61s Lodgepole) | 2024-12-10 07:30 | 2024-12-10 12:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 775L (276s Prentiss - 535s Joffre), 276s 775X (276s Prentiss) | 2024-12-10 07:30 | 2024-12-12 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
BCH | 2L112 (BPA Boundary - BCH Nelway), 2D24 (BCH Nelway), 2D2CB7 (BCH Nelway) | 2024-12-10 08:00 | 2024-12-10 13:00 | N | Y |  | Line, Switch |  |  | 240 kV, Pre-Condition
ENMAX | 40.2TR (SS-40) | 2024-12-10 08:00 | 2024-12-10 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 1L275 (799s Coleman - BCH Natal) | 2024-12-10 09:00 | 2024-12-10 17:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 723L (69s North Barrhead - 724L tap), 69s 723E (69s North Barrhead) | 2024-12-10 09:00 | 2024-12-10 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills), 802s 706 (802s Michichi Creek), 804s 701 (804s Wintering Hills) | 2024-12-10 09:00 | 2024-12-17 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 202AL tap), 61s 202N (61s Lodgepole) | 2024-12-10 11:30 | 2024-12-11 13:30 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2024-12-10 12:00 | 2024-12-11 18:00 | N | Y |  | Line |  | forced outage | For Information Only
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2024-12-10 12:00 | 2024-12-11 18:00 | N | Y |  | Line |  | forced outage | For Information Only
ALTALINK | 723L (150s Clyde - 438s Westlock), 150s 723W (150s Clyde) | 2024-12-10 13:00 | 2024-12-10 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 985L (74s Janet - SS-25) | 2024-12-10 16:30 | 2024-12-10 17:30 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 132s 240kV North Bus (132s Ware Junction), 950L (132s Ware Junction - 801s Anderson), 132s 24 (132s Ware Junction), 132s 18 (132s Ware Junction), 132s 6 (132s Ware Junction), 132s 3 (132s Ware Junction), 132s 950N (132s Ware Junction), 132s 37 (132s Ware Junction), 132s 47 (132s Ware Junction) | 2024-12-11 07:00 | 2024-12-11 14:00 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Affects Cranking Path
EPCOR | 330p 1204 (330p Genesee) | 2024-12-11 07:00 | 2024-12-13 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
SUNCOR | 635EDD-1000 635-752-132 (635EDD-1000) | 2024-12-11 07:00 | 2024-12-11 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 32.3TR (SS-32) | 2024-12-11 08:00 | 2024-12-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 162B240-RB135 (SS-162), 162B240-RB136 (SS-162) | 2024-12-11 08:00 | 2024-12-16 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 21B138-21.80 (SS-21), 42s 21 (42s Sarcee) | 2024-12-11 08:00 | 2024-12-16 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 2B138-D93 (SS-2), 2B138-D94 (SS-2) | 2024-12-11 08:00 | 2024-12-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2024-12-11 10:00 | 2024-12-11 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 845s 710 (845s Big Mountain) | 2024-12-11 12:31 | 2024-12-16 08:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 202L335 (202AL tap), 202L (61s Lodgepole - 202AL tap) | 2024-12-11 13:01 | 2024-12-11 17:30 | N | N |  | Switch, Line |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2024-12-11 18:30 | 2024-12-13 17:00 | N | N |  | Line
ATCO | VBR1 Generator Test | 2024-12-12 06:00 | 2024-12-20 18:00 | N | N |  | Unit
EPCOR | R723 (Rossdale) | 2024-12-12 07:00 | 2024-12-12 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 922L (17s Benalto - 310p Sundance), 310p 1952 (310p Sundance), 310p 2052 (310p Sundance) | 2024-12-12 07:15 | 2024-12-13 18:45 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2024-12-12 10:00 | 2024-12-12 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK, TRANSALTA | 616L (59s Peigan - 616AL tap), 59s T1 (59s Peigan), 59s 5 (59s Peigan), 59s 616 (59s Peigan) | 2024-12-12 13:30 | 2024-12-16 17:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker |  |  | Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2024-12-13 06:30 | 2024-12-13 15:30 | Y | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), RV728 (Rossdale) | 2024-12-13 07:00 | 2024-12-13 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 202L (61s Lodgepole - 202AL tap), 61s 202N (61s Lodgepole) | 2024-12-13 07:00 | 2024-12-13 20:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.84L (SS-3 - SS-13) | 2024-12-13 07:00 | 2024-12-13 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 6.1TR (SS-6) | 2024-12-13 08:00 | 2024-12-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 858S 701TD (858s Narrows Creek), 796s 702 (796s Nipisi) | 2024-12-13 10:00 | 2024-12-13 16:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon), 353s 552 (353s Plamondon), 157s 728W (157s Lac La Biche) | 2024-12-13 14:30 | 2024-12-14 17:19 | N | N |  | Line, Circuit Breaker
ALTALINK | 202L (58s Edson - 178s Cynthia), 178s 202N (178s Cynthia), 58s 202X (58s Edson) | 2024-12-14 07:00 | 2024-12-17 17:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 1206L (12s Heartland - 89s Ellerslie) | 2024-12-14 07:15 | 2024-12-16 17:45 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ENMAX | 7B138-7BT3 (SS-7) | 2024-12-14 08:00 | 2024-12-14 12:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22B138-22BT8 (SS-22) | 2024-12-14 12:00 | 2024-12-14 18:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 929L (74S Janet - 287s Hazelwood) | 2024-12-15 07:00 | 2024-12-19 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 59s 352 (59s Peigan) | 2024-12-15 07:30 | 2024-12-15 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 59s 752 (59s Peigan) | 2024-12-15 12:00 | 2024-12-15 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | W724 (Woodcroft) | 2024-12-16 07:00 | 2024-12-16 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only, Pre-Condition
EPCOR | 330p 1207 (330p Genesee) | 2024-12-16 07:00 | 2024-12-18 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
EPCOR | 72CN10 (987s Clover Bar - Namao), T3 (Namao), N723 (Namao), N724 (Namao) | 2024-12-16 07:00 | 2024-12-18 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 816s T2 (816s Petrolia), 816s P2404 (816s Petrolia), 816s P2405 (816s Petrolia), 816s PAB2 (816s Petrolia) | 2024-12-16 07:00 | 2024-12-17 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3), 13B138-3.84 (SS-13) | 2024-12-16 08:00 | 2024-12-16 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.4TR (SS-2) | 2024-12-16 08:00 | 2024-12-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 15.60L (SS-15 - SS-21), 21.61L (SS-21 - SS-34), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21B69-21.61 (SS-21), 21B69-15.60 (SS-21) | 2024-12-16 08:00 | 2024-12-16 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview), MH-20L (MHS-3 Southridge - MHS-6 CMH Riverview), 4L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview), MH-12L (MHS-8 Burnside - MHS-6 CMH Riverview), MHS-6 MH138-T63 (MHS-6 Riverview), MHS-6 MH69-T61(MHS-6 Riverview), MHS-6 MH69-T62 (MHS-6 Riverview) | 2024-12-16 08:30 | 2024-12-16 15:00 | N | N |  | Line, Transformer |  |  | Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21) | 2024-12-16 09:00 | 2024-12-16 10:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 171s 138kV Bus (171s Redwater), 808L (171s Redwater - 808AL tap), 171s T2 (171s Redwater), 171s 808E (171s Redwater) | 2024-12-16 09:00 | 2024-12-23 17:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK, TRANSALTA | 229s T1 (229s Glenwood), 229s 152 (229s Glenwood) | 2024-12-16 09:30 | 2024-12-16 13:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 1038L (138s Windy Flats - 266s SC1), 1038L (237s Foothills - 266s SC1), 266s 1038L FSC2 (266s SC1) | 2024-12-16 09:30 | 2024-12-17 18:00 | N | Y |  | Line, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 59s 1152 (59s Peigan), 1049L (59s Peigan - 138s Windy Flats), 138s 1049 (138s Windy Flats), 59s 1049 (59s Peigan) | 2024-12-16 09:30 | 2024-12-16 14:00 | N | Y |  | Circuit Breaker, Line, Switch |  |  | 240 kV, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21) | 2024-12-16 10:00 | 2024-12-16 12:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 244s 138kV Bus 2 (244s Bowmanton), 244s T2 (244s Bowmanton), 244s 240kV Bus 2 (244s Bowmanton), 244s 352 (244s Bowmanton), 244s 652 (244s Bowmanton), 244s 2389 (244s Bowmanton), 244s 2252 (244s Bowmanton), 244s 2652 (244s Bowmanton), 244s 2489 (244s Bowmanton) | 2024-12-16 12:00 | 2024-12-18 16:21 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  | Outage returned early. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
EPCOR | 987s GT2 (987s Clover Bar), 987s CGB2 (987s Clover Bar) | 2024-12-16 12:00 | 2024-12-16 15:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 3.84L (SS-3 - SS-13), 13B138-3.84 (SS-13) | 2024-12-16 12:01 | 2024-12-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Lethbridge | 813L (146s MacDonald - 241s Uplands), 241s 813L (241s Uplands), 146s 813L (146s Macdonald) | 2024-12-16 13:00 | 2024-12-16 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s GT2 (987s Clover Bar), 987s CGB2 (987s Clover Bar) | 2024-12-16 17:00 | 2024-12-16 20:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 28s 138kV Bus 1 (28s West Brooks), 853L (28s West Brooks - 853AL tap), 814L (28s West Brooks - 121s Brooks), 28s T1 (28s West Brooks), 121s 814W (121s Brooks), 28s 31 (28s West Brooks), 28s 28 (28s West Brooks), 28s 25 (28s West Brooks), 28s 22 (28s West Brooks), 28s 20 (28s West Brooks), 28s 814E (28s West Brooks), 28s 853W (28s West Brooks) | 2024-12-17 07:00 | 2024-12-17 18:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 874L (45s Bretona - 522s Cooking Lake), 45s 874 (45s Bretona), 522s 874 (522s Cooking Lake) | 2024-12-17 07:00 | 2024-12-18 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 914L (86s Bigstone - 87s Gaetz), 87s 1252 (87s Gaetz) | 2024-12-17 07:00 | 2024-12-17 21:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar), 71s 1352 (71s Lamoureux), 71s 1252 (71s Lamoureux), 71s 921X (71s Lamoureux) | 2024-12-17 07:00 | 2024-12-18 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 288s 152 (288s Wolf Creek), 288s 352 (288s Wolf Creek), 1083L (63s Red Deer - 288s Wolf Creek), 288s 1083 (288s Wolf Creek) | 2024-12-17 07:00 | 2024-12-17 21:00 | N | Y |  | Circuit Breaker, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 1212L (12s Heartland - 89s Ellerslie) | 2024-12-17 07:15 | 2024-12-18 17:45 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ENMAX | 21.1C (SS-21) | 2024-12-17 08:00 | 2024-12-17 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 33.2TR (SS-33) | 2024-12-17 08:00 | 2024-12-18 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s GT2 (987s Clover Bar) | 2024-12-17 08:00 | 2024-12-17 11:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 16.63L (SS-16 - SS-36), 36B69-16.63/36.5TR (SS-36) | 2024-12-17 09:00 | 2024-12-17 10:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 16B69-16.63 (SS-16) | 2024-12-17 10:01 | 2024-12-17 11:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16) | 2024-12-17 11:00 | 2024-12-17 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27) | 2024-12-17 12:01 | 2024-12-17 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 1037L (138s Windy Flats - 266s SC1), 1037L (237s Foothills - 266s SC1), 266s 1037L FSC1 (266s SC1) | 2024-12-18 07:00 | 2024-12-19 17:15 | N | Y |  | Line, Shunts |  | Outage returned early. | 240 kV, Pre-Condition
ALTALINK | 28s 240kV Bus 2 (28s West Brooks), 1052L (28s West Brooks - 324s Cassils), 28s T2 (28s West Brooks), 28s 2 (28s West Brooks), 28s 5 (28s West Brooks), 28s 52 (28s West Brooks), 324s 1952 (324s Cassils), 324s 2052 (324s Cassils), 324s 1389 (324s Cassils), 28s 289 (28s West Brooks) | 2024-12-18 07:00 | 2024-12-18 18:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation,Affects Cranking Path
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2024-12-18 07:00 | 2024-12-18 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 809L (320p Keephills - 510s Sunnybrook), 320p 809X (320p Keephills) | 2024-12-18 08:00 | 2024-12-18 17:30 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 2.83L (SS-2 - 2.83L tap), 2B138-D90 (SS-2), 2B138-D89 (SS-2), MD97 (SS-2), MD98 (SS-2) | 2024-12-18 08:00 | 2024-12-19 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 932L (74s Janet - SS-162) | 2024-12-18 08:00 | 2024-12-19 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 8B138-5A0 (SS-8) | 2024-12-18 08:00 | 2024-12-18 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 384s T2 (384s Keystone) | 2024-12-18 08:30 | 2024-12-18 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau Plant) | 2024-12-18 23:00 | 2024-12-19 03:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau Plant) | 2024-12-19 03:00 | 2024-12-19 07:00 | N | Y |  | Switch |  |  | 240 kV, Restricts Generation
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft), W721 (Woodcroft), EP 805s J724 (EP 805s Jasper) | 2024-12-19 07:00 | 2024-12-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1164L (816s Petrolia - EP Riverview), RW2401 (EP Riverview), RW2402 (EP Riverview), RWDS11 (EP Riverview) | 2024-12-19 07:00 | 2024-12-19 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2024-12-20 08:00 | 2024-12-23 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 502s T3 (502s Shell Waterton (#2)) | 2024-12-20 13:30 | 2024-12-20 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 74s C3 (74s Janet) | 2024-12-20 15:01 | 2025-01-10 17:00 | N | Y |  | Shunts |  | AltaLink operator estimated at least another week before the repairs are complete | 240 kV, Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2024-12-26 17:07 | 2025-03-20 07:59 | N | N |  | Shunts |  | Extended | Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton) | 2024-12-26 17:07 | 2025-02-13 07:59 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 150L (20s Ghost - 150AL tap), 20s 150 (20s Ghost) | 2025-01-04 07:00 | 2025-01-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 72MG16 (Garneau - Meadowlark), T2 (Garneau), G721 (Garneau), G725 (Garneau), G726 (Garneau), GDS17 (Garneau), GAB2 (Garneau), M725 (Meadowlark) | 2025-01-06 07:00 | 2025-01-24 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.10TR (SS-5) | 2025-01-06 08:00 | 2025-01-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L56 (738s Virginia Hills - 809s Louise Creek), 809s 707 (809s Louise Creek) | 2025-01-06 09:00 | 2025-01-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 150L (42s Sarcee - 150AL tap), 42s 150W (42s Sarcee) | 2025-01-06 09:30 | 2025-05-23 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 38.1TR (SS-38) | 2025-01-07 08:00 | 2025-01-07 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L90 (813s Little Smoky - 7LA90 tap) | 2025-01-07 08:00 | 2025-01-07 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 63s 452 (63s Red Deer) | 2025-01-07 08:30 | 2025-01-07 14:00 | N | Y |  | Circuit Breaker |  | done early | 240 kV, Contingency Requires Mitigation
ATCO | 801s 901T (801s Anderson), 801s 902 (801s Anderson), 801s 704 (801s Anderson) | 2025-01-07 09:00 | 2025-01-10 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 38.2TR (SS-38) | 2025-01-08 08:00 | 2025-01-08 12:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 9.3TR (SS-9) | 2025-01-08 08:00 | 2025-01-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.6TR (SS-5) | 2025-01-08 08:00 | 2025-01-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 54L (118s Canmore - 85L tap), 118s 54W (118s Canmore) | 2025-01-08 08:00 | 2025-01-09 19:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.3TR (SS-38) | 2025-01-09 08:00 | 2025-01-09 12:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ATCO | 7L85 (801s Anderson - ATC 803s Bullpound), 801s 705 (801s Anderson) | 2025-01-11 09:00 | 2025-01-12 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 33.1TR (SS-33) | 2025-01-12 08:00 | 2025-01-15 14:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s C2410 (987s Clover Bar), 987s C2409 (987s Clover Bar), 987s CC721 (987s Clover Bar), 987s CDS45 (987s Cloverbar), 987s CDS31 (987s Clover Bar) | 2025-01-13 07:00 | 2025-03-28 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | T1 (Meadowlark) | 2025-01-13 07:00 | 2025-02-07 17:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 13B138-2.83 (SS-13), 5B138-2.83 (SS-5) | 2025-01-13 08:00 | 2025-01-13 11:00 | N | N |  | Line, Circuit Breaker |  |  | Overload
ENMAX | 15.62L (SS-15 - SS-16), 15.2TR (SS-15), 15B69-15.62 (SS-15), 16B69-15.62 (SS-16), 15MD69-15.2TR (SS-15), SW64 (SS-15) | 2025-01-13 08:00 | 2025-01-14 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13.1TR (SS-13), 13.3TR (SS-13), 13B138-3.84 (SS-13), 13B138-2.83 (SS-13), 3B138-3.84 (SS-3), 13MD138-13.1TR (SS-13), 13MD138-13.3TR (SS-13), SW83 (SS-13) | 2025-01-13 08:00 | 2025-02-02 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload
REDDEER | 217s T2 (217s North Red Deer) | 2025-01-13 12:30 | 2025-01-16 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 754L (118s Canmore - 437s Baymag), 118s 754E (118s Canmore) | 2025-01-14 08:00 | 2025-01-15 19:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 987s GT3 (987s Clover Bar) | 2025-01-15 07:00 | 2025-01-15 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 15.60L (SS-15 - SS-21), 15.1TR (SS-15), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21), 15MD69-15.1TR (SS-15) | 2025-01-15 08:00 | 2025-01-16 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 37s T5 (37s North Calder) | 2025-01-15 08:00 | 2025-01-15 17:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), RV728 (Rossdale) | 2025-01-16 07:00 | 2025-01-16 16:00 | N | N |  | Line, Circuit Breaker |  | back early | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale) | 2025-01-16 07:00 | 2025-01-16 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 7L199 (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek), 741s 702 (741s ATC Fox Creek) | 2025-01-16 08:00 | 2025-01-16 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5), 5B138-1.84 (SS-5) | 2025-01-17 08:00 | 2025-01-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 5.9TR (SS-5), 5.10TR (SS-5), 5MD138-5.10TR (SS-5), 5MD138-5.9TR (SS-5), 5B138-5BT12 (SS-5), 5B138-2.83 (SS-5) | 2025-01-18 08:00 | 2025-01-19 18:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Pre-Condition
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), 987s CH722 (987s Clover Bar), H724 (EP Hardisty) | 2025-01-20 07:00 | 2025-01-20 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB132 (SS-162), 162B240-RB133 (SS-162), 162MD240-918L (SS-162) | 2025-01-20 07:30 | 2025-01-23 16:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Affects Cranking Path
ENMAX | 33.1TR (SS-33), 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33), 41B138-33.83 (SS-41), 33MD138-33.1TR (SS-33) | 2025-01-20 08:00 | 2025-01-21 16:00 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.2TR (SS-9) | 2025-01-20 08:00 | 2025-01-23 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16), 34B69-16.60 (SS-34) | 2025-01-20 08:00 | 2025-01-31 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB132 (SS-162), 162B240-RB133 (SS-162), 162MD240-918L (SS-162) | 2025-01-20 08:00 | 2025-01-23 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap) | 2025-01-20 10:00 | 2025-01-23 16:30 | N | Y |  | Line |  |  | For Information Only
ATCO | 840s McNeill Station | 2025-01-20 10:00 | 2025-01-21 11:20 | N | Y |  | Station |  |  | Limits ATC
ATCO | 741s 701T (741s Fox Creek), 741s 701 (741s ATC Fox Creek), 741s 702 (741s ATC Fox Creek), 741s 702T (741s Fox Creek), 741s 703 (741s ATC Fox Creek), 741s 704 (741s ATC Fox Creek), 741s 705C (741s Fox Creek), 741s 705 (741s ATC Fox Creek), 7L90 (741s ATC Fox Creek - 7LA90 tap), 7L199 (347s AML Fox Creek - 741s ATC Fox Creek) | 2025-01-20 10:00 | 2025-01-24 12:00 | N | Y |  | Transformer, Circuit Breaker, Shunts, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap), 526s 152 (526s Buffalo Creek) | 2025-01-20 10:00 | 2025-01-23 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2025-01-20 12:00 | 2025-01-21 18:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), 987s CH724 (987s Clover Bar), H725 (EP Hardisty) | 2025-01-20 12:00 | 2025-01-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 796s 702 (796s Nipisi), 858S 701TD (858s Narrows Creek) | 2025-01-20 14:00 | 2025-01-27 10:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s CK725 (987s Clover Bar), K724 (Kennedale) | 2025-01-21 07:00 | 2025-01-21 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L10 (876s Brintnell - 939s Livock), 939s 911 (939s Livock), 939s 912 (939s Livock) | 2025-01-21 09:00 | 2025-01-26 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72CK13 (987s Clover Bar - Kennedale), 987s CK726 (987s Clover Bar), K721 (Kennedale) | 2025-01-21 12:00 | 2025-01-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s C1 (987s Clover Bar) | 2025-01-22 07:00 | 2025-01-22 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43), 33MD138-33.2TR (SS-33) | 2025-01-22 08:00 | 2025-01-23 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2025-01-22 11:00 | 2025-01-22 15:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
EPCOR | 987s CC24 (987s Clover Bar) | 2025-01-22 12:00 | 2025-01-22 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | 72RV4 (EP 511s Victoria - Rossdale), RV726 (Rossdale) | 2025-01-23 07:00 | 2025-01-23 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.1C (SS-21), 21.2TR (SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2025-01-23 08:00 | 2025-01-23 15:00 | N | Y |  | Line, Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 74s C3 (74s Janet) | 2025-01-24 | 2025-07-17 08:29 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
EPCOR | 987s GB1B (987s Clover Bar) | 2025-01-24 07:00 | 2025-01-24 17:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
BCH | T1 (BCH Natal), 13CX1 (BCH Natal) | 2025-01-24 09:00 | 2025-01-24 15:00 | N | Y |  | Transformer, Shunts |  |  | Pre-Condition
ATCO | 741s 701T (741s Fox Creek), 741s 702T (741s Fox Creek), 741s 703 (741s ATC Fox Creek), 741s 704 (741s ATC Fox Creek) | 2025-01-24 12:01 | 2025-02-03 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2025-01-24 12:01 | 2025-01-29 17:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T3 (Garneau) | 2025-01-25 07:00 | 2025-01-25 17:00 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39) | 2025-01-26 06:00 | 2025-01-26 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.2TR (SS-33) | 2025-01-26 08:00 | 2025-01-29 14:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), RV722 (Rossdale), EP 511s VDS9 (EP 511s Victoria) | 2025-01-27 07:00 | 2025-01-27 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR | 72RG1 (Garneau - Rossdale), T2 (Garneau), G724 (Garneau), G725 (Garneau), G726 (Garneau), RG7210 (Rossdale), GAB2 (Garneau), GDS18 (Garneau) | 2025-01-27 07:00 | 2025-02-14 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
EPCOR | 72CN10 (987s Clover Bar - Namao), 987s CN723 (987s Clover Bar), N724 (Namao) | 2025-01-27 07:00 | 2025-01-28 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s C1 (244s Bowmanton), 244s C2 (244s Bowmanton) | 2025-01-27 08:00 | 2025-02-27 17:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 38.1TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 39B138-38.83 (SS-39), 38B138-38.83 (SS-38), 38MD138-38.3TR (SS-38), 38MD138-38.1TR (SS-38), SW84 (SS-38) | 2025-01-27 08:00 | 2025-01-29 16:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s C3 (244s Bowmanton) | 2025-01-27 08:00 | 2025-02-27 17:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ATCO | 7L137 (768s Rowley - 770s Three Hills), 770s 702 (770s Three Hills), 768s 703 (768s Rowley) | 2025-01-27 09:30 | 2025-01-27 14:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap) | 2025-01-27 10:00 | 2025-01-30 16:10 | N | Y |  | Line |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap), 526s 152 (526s Buffalo Creek) | 2025-01-27 10:00 | 2025-01-30 16:10 | N | Y |  | Line, Circuit Breaker |  | Outage returned to service early. | For Information Only
ATCO | 2075s ACF22 (2075s Newell) | 2025-01-27 11:00 | 2025-01-28 16:45 | N | Y |  | Shunts
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2025-01-27 12:30 | 2025-02-03 11:59 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ALTALINK | 62s T1 (62s Brazeau Plant) | 2025-01-28 08:00 | 2025-01-29 19:00 | N | Y |  | Transformer |  |  | Restricts Generation
CUB, ALTALINK | 672s 901T (672s Fengate Co-Generation), 430s 589 (430s Ursus) | 2025-01-28 09:00 | 2025-02-06 09:00 | N | Y |  | Transformer, Switch |  |  | 240 kV, For Information Only
EPCOR | RR723 (Rossdale) | 2025-01-29 07:00 | 2025-01-29 17:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 840s McNeill Station | 2025-01-29 09:00 | 2025-01-31 15:00 | N | Y |  | Station |  |  | Limits ATC, Pre-Condition
ENMAX | 240kV West Bus (SS-25), 25B240-D136 (SS-25), 25B240-D133 (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25) | 2025-01-29 10:00 | 2025-01-30 16:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Restricts Generation
ALTALINK | 62s T1 (62s Brazeau Plant) | 2025-01-29 23:00 | 2025-01-30 03:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 62s T2 (62s Brazeau Plant) | 2025-01-30 03:00 | 2025-01-30 07:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR | RR729 (Rossdale) | 2025-01-30 07:00 | 2025-01-31 17:00 | N | N |  | Circuit Breaker |  | Outage extended due to trip coil issues | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 38B138-37.81 (SS-38), 37B138-37.81 (SS-37), SW83 (SS-38), 38MD138-38.2TR (SS-38), 38MD138-38.3TR (SS-38) | 2025-01-30 08:00 | 2025-01-31 16:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 709s 701Ta (709s Vegreville), 709s 701 (709s Vegreville) | 2025-01-30 09:00 | 2025-01-30 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 237s 2252 (237s Foothills) | 2025-01-30 09:00 | 2025-01-30 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 709s 702T (709s Vegreville), 709s 702 (709s Vegreville) | 2025-01-30 12:01 | 2025-01-30 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | T3 (Poundmaker) | 2025-02-01 07:00 | 2025-02-01 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 955L (59s Peigan - 103s Goose Lake), 103s 552 (103s Goose Lake), 103s 452 (103s Goose Lake) | 2025-02-02 07:00 | 2025-02-02 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Overload
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 13B138-2.83 (SS-13), 5B138-2.83 (SS-5) | 2025-02-02 12:00 | 2025-02-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | T2 (Poundmaker), PM2405 (Poundmaker), PM2401 (Poundmaker) | 2025-02-03 07:00 | 2025-02-07 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), EP 511s Victoria T1 (EP 511s Victoria), EP 511s V729 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), RV728 (Rossdale) | 2025-02-03 07:00 | 2025-02-14 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  | Outage extended due to relay issues. Breaker cannot be closed. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36B69-16.63/36.5TR (SS-36), 16B69-16.63 (SS-16) | 2025-02-03 08:00 | 2025-02-07 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2025-02-03 09:00 | 2025-02-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 800s 601 (800s Friedenstal) | 2025-02-03 10:00 | 2025-02-14 18:00 | N | N |  | Circuit Breaker |  | Completed Early | Pre-Condition
ATCO | 7L129 (710s Vermilion - 7LA129 tap), 710s 704 (710s Vermilion) | 2025-02-03 10:00 | 2025-02-07 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2025-02-03 12:00 | 2025-02-07 18:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
EPCOR | 113s T1 (113s Inland Cement) | 2025-02-04 06:00 | 2025-02-06 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3) | 2025-02-04 08:00 | 2025-02-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 796s 702 (796s Nipisi) | 2025-02-04 09:00 | 2025-02-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2025-02-04 09:00 | 2025-02-16 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 657s T1 (657s Summerside) | 2025-02-05 07:00 | 2025-02-05 12:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 254s T2 (254s Coaldale) | 2025-02-05 07:30 | 2025-02-05 15:30 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2025-02-05 08:00 | 2025-02-05 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BHE Canada | MATL (120s Picture Butte - Montana), 120s 1052 (120s Picture Butte), 120s 1352 (120s Picture Butte) | 2025-02-05 08:00 | 2025-02-06 15:45 | Y | Y |  | Line, Circuit Breaker |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-02-05 10:00 | 2025-02-05 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR | 657s T2 (657s Summerside) | 2025-02-05 12:00 | 2025-02-05 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ATCO | 848s 401R (848s Ruth Lake), 848s 401 (848s Ruth Lake) | 2025-02-05 13:00 | 2025-02-14 15:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
Syncrude | 89-17 (Aurora), TL-1 (Aurora - Aurora) | 2025-02-06 08:00 | 2025-02-11 13:00 | N | N |  | Switch, Line |  |  | For Information Only
ALTALINK | 87s 1052 (87s Gaetz) | 2025-02-06 08:30 | 2025-02-06 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-02-06 10:00 | 2025-02-06 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR | 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2025-02-07 07:00 | 2025-02-07 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | EP 511s Victoria T1 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), EP 511s VAB1 (EP 511s Victoria) | 2025-02-07 17:00 | 2025-02-14 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 749L (648s Metiskow - 749AL tap), 648s 749E (648s Metiskow) | 2025-02-08 07:00 | 2025-02-08 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 39.82L (SS-39 - SS-162), 39B138-39.82 (SS-39) | 2025-02-08 08:00 | 2025-02-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2025-02-08 09:00 | 2025-02-10 06:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 31.1TR (SS-31) | 2025-02-08 10:00 | 2025-02-08 14:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 14.4TR (SS-14) | 2025-02-08 14:00 | 2025-02-08 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 749L (899s Edgerton - 7LB749 tap), 899s 749N (899s Edgerton) | 2025-02-09 07:00 | 2025-02-09 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T3 (Poundmaker), PM2404 (Poundmaker), PM2405 (Poundmaker), PMAB3 (Poundmaker) | 2025-02-10 07:00 | 2025-02-14 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.2TR (SS-21), 21.1C (SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21), 21B138-21.CAP (SS-21) | 2025-02-10 08:00 | 2025-02-10 12:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Overload, Pre-Condition
ENMAX | 162B138-RB92 (SS-162), 162.4TR (SS-162), 162B138-RB94 (SS-162), 162MD138-162.4TR (SS-162) | 2025-02-10 08:00 | 2025-02-11 16:00 | N | N |  | Circuit Breaker, Transformer, Switch |  |  | For Information Only
BCH | 2CB1 (BCH Natal) | 2025-02-10 09:00 | 2025-02-28 17:00 | N | Y |  | Circuit Breaker | 2CB1 (BCH Natal) OOS |  | 240 kV
ATCO | 7L92 (709s Vegreville - 7LA92 tap), 709s 705 (709s Vegreville) | 2025-02-10 09:00 | 2025-02-10 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, EPCOR | 1043L (320p Keephills - 367s Harry Smith), 320p 352 (320p Keephills), 320p 252 (320p Keephills) | 2025-02-10 09:00 | 2025-02-13 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
BCH | T3 (BCH Natal) | 2025-02-10 09:00 | 2025-03-14 17:00 | N | Y |  | Transformer |  |  | 240 kV
ATCO | 848s 604 (848s Ruth Lake), 848s 606 (848s Ruth Lake) | 2025-02-10 10:00 | 2025-02-13 15:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 21.1C (SS-21) | 2025-02-10 12:00 | 2025-02-13 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 903L (17s Benalto - 320p Keephills), 320p 2152 (320p Keephills), 320p 2052 (320p Keephills), 17s 8 (17s Benalto), 17s 7 (17s Benalto) | 2025-02-10 12:00 | 2025-02-14 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ENMAX | 21.4TR (SS-21) | 2025-02-10 12:00 | 2025-02-13 15:00 | N | N |  | Transformer |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 60s50 (SS-21) | 2025-02-10 12:01 | 2025-02-13 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 74s C3 (74s Janet) | 2025-02-10 12:30 | 2025-02-10 17:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 35.1TR (SS-35) | 2025-02-11 08:00 | 2025-02-11 12:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | 89-26 (Aurora) | 2025-02-11 08:00 | 2025-02-14 16:00 | N | N |  | Switch
ENMAX, ALTALINK | 1109L (SS-25 - SS-65), 240kV West Bus (SS-25), 25B240-D133 (SS-25), 25B240-D136 (SS-25), 25B240-D142 (SS-25), 25B240-D141 (SS-25), 25B240-D139 (SS-25), 65MD240-1109 (SS-65) | 2025-02-11 09:00 | 2025-02-24 16:00 | N | Y |  | Line, Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2025-02-11 12:00 | 2025-02-11 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T1 (Woodcroft) | 2025-02-12 07:00 | 2025-02-12 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 702L (137s Sedgewick - 377s AML Hardisty), 137s 169X (137s Sedgewick) | 2025-02-12 07:00 | 2025-02-14 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ENMAX, ALTALINK | 918L (281s Johnson - SS-162), 162B240-RB133 (SS-162), 162B240-RB132 (SS-162), 162MD240-918L (SS-162) | 2025-02-12 08:00 | 2025-02-13 16:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
Syncrude | 1435 (Syncrude Mildred Lake), Mildred T14 (Syncrude Mildred Lake) | 2025-02-12 08:00 | 2025-02-14 16:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
CMH | MHS-1 69kV South Bus (MHS-1 Power P Switchyard), MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview) | 2025-02-12 09:00 | 2025-02-12 17:00 | N | N |  | Bus, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CUB, ALTALINK | 672s 902T (672s Fengate Co-Generation), 430s 689 (430s Ursus) | 2025-02-12 09:00 | 2025-02-18 09:00 | N | Y |  | Transformer, Switch |  |  | 240 kV
ALTALINK | 38s C1 (38s East Edmonton) | 2025-02-13 08:00 | 2025-02-13 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.2TR (SS-21), 21.1C (SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2025-02-14 08:00 | 2025-02-14 12:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK, ATCO | 702L (137s Sedgewick - 757s Battle River), 137s 169X (137s Sedgewick), 757s 708 (757s Battle River) | 2025-02-15 07:00 | 2025-02-15 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Restricts Generation
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2025-02-15 07:00 | 2025-02-15 18:00 | N | Y |  | Line |  |  | For Information Only
ENMAX | 2.84L (SS-2 - SS-8), 7A01 (SS-8) | 2025-02-15 08:00 | 2025-02-15 16:00 | N | N |  | Line, Switch |  |  | Pre-Condition
ENMAX | 11.83L (SS-162 - SS-11), 162B138-RB85 (SS-162), 162B138-RB84 (SS-162), 11B138-11.83 (SS-11), 162MD138-11.83 (SS-162) | 2025-02-15 08:00 | 2025-02-23 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28B138-28.80 (SS-28), 42s 28 (42s Sarcee) | 2025-02-16 08:00 | 2025-02-16 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 763L (28s West Brooks - 763AL tap), 28s 31 (28s West Brooks), 28s 47 (28s West Brooks), 28s 763X (28s West Brooks) | 2025-02-17 07:30 | 2025-02-17 17:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 225L (67s Stirling - 225AL tap), 225L (225s Magrath - 225AL tap), 225AL (313s Raymond Reservoir - 225L tap), 67s 225 (67s Stirling), 225s 225E (225s Magrath) | 2025-02-17 10:00 | 2025-02-21 15:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 987s CC13 (987s Clover Bar) | 2025-02-18 07:00 | 2025-02-19 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RG7 (Garneau - Rossdale), T1 (Garneau), G722 (Garneau), G723 (Garneau), G721 (Garneau), GDS4 (Garneau), GAB1 (Garneau) | 2025-02-18 07:00 | 2025-03-10 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  | Breaker G723 needs to be adjusted/would not close | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 601L (230s Wardlow - 275s Jenner), 275s T3 (275s Jenner), 230s T1 (230s Wardlow), 275s 83 (275s Jenner), 275s 601 (275s Jenner), 230s 601 (230s Wardlow) | 2025-02-18 07:30 | 2025-02-18 17:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28), 28MD138-28.1TR (SS-28), SW83 (SS-28), 4A9 (SS-1) | 2025-02-18 08:00 | 2025-02-19 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 9L10 (876s Brintnell - 939s Livock), 939s 911 (939s Livock), 939s 910 (939s Livock), 939s 903T (939s Livock) | 2025-02-18 08:00 | 2025-02-28 15:30 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 796s 702 (796s Nipisi), 858S 701TD (858s Narrows Creek) | 2025-02-18 09:00 | 2025-02-24 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 741s 705C (741s Fox Creek) | 2025-02-18 10:00 | 2025-03-03 11:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 6L44 (769s Stettler - 778s Big Valley), 6L02 (769s Stettler - 873s Marion Lake), 769s 703T (769s Stettler), 778s 601T (778s Big Valley), 769s 703 (769s Stettler), 769s 603 (769s Stettler), 769s 602 (769s Stettler), 769s 601 (769s Stettler), 778s 601TD (778s Big Valley), 769s 503TD1 (769s Stettler) | 2025-02-18 10:00 | 2025-02-18 15:45 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 704L (51s Wainwright - 478s Tucuman), 478s 152 (478s Tucuman), 51s 704 (51s Wainwright) | 2025-02-19 08:30 | 2025-02-19 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L194 (2009s Willow Lake - 2011s Dawes) | 2025-02-19 09:00 | 2025-02-22 15:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 557s T2 (557s Castle Downs) | 2025-02-20 07:00 | 2025-02-20 17:00 | N | Y |  | Transformer |  |  | 240 kV
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), T2 (EP Hardisty), H723 (EP Hardisty), H722 (EP Hardisty), HAB2 (EP Hardisty) | 2025-02-20 07:00 | 2025-02-21 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 816s T1 (816s Petrolia) | 2025-02-20 07:00 | 2025-02-20 17:00 | N | Y |  | Transformer |  |  | 240 kV, Restricts Generation
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13B69-13.60 (SS-13) | 2025-02-20 08:00 | 2025-02-20 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville), 709s 704 (709s Vegreville) | 2025-02-20 10:00 | 2025-02-20 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L44 (769s Stettler - 778s Big Valley), 6L02 (769s Stettler - 873s Marion Lake), 769s 703T (769s Stettler), 778s 601T (778s Big Valley), 769s 703 (769s Stettler), 769s 603 (769s Stettler), 769s 602 (769s Stettler), 769s 601 (769s Stettler), 778s 601TD (778s Big Valley), 769s 503TD1 (769s Stettler) | 2025-02-20 10:00 | 2025-02-28 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Rossdale) | 2025-02-21 07:00 | 2025-02-21 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 816s T2 (816s Petrolia) | 2025-02-21 07:00 | 2025-02-21 17:00 | N | Y |  | Transformer |  |  | 240 kV, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 732s 704 (732s Mitsue) | 2025-02-21 09:00 | 2025-02-21 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 7L65 (709s Vegreville - 7LA65 tap), 709s 703 (709s Vegreville) | 2025-02-21 10:00 | 2025-02-21 12:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 7L92 (709s Vegreville - 7LA92 tap), 709s 705 (709s Vegreville) | 2025-02-21 12:01 | 2025-02-21 14:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 52s T1 (52s East Industrial) | 2025-02-22 07:00 | 2025-03-19 12:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK, TRANSALTA | 33s T2 (33s Spray), 33s 2 (33s Spray) | 2025-02-22 08:00 | 2025-02-22 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 895s T2 (895s Suffield), 895s 43 (895s Suffield) | 2025-02-24 06:00 | 2025-02-25 18:00 | N | N |  | Transformer, Switch |  |  | For Information Only
EPCOR | T2 (Meadowlark), M722 (Meadowlark), M723 (Meadowlark), MAB2 (Meadowlark) | 2025-02-24 07:00 | 2025-02-26 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | PM2405 (Poundmaker) | 2025-02-24 07:00 | 2025-02-24 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | T1 (EP Riverview), RW2401 (EP Riverview), RW2405 (EP Riverview), RWAB1 (EP Riverview) | 2025-02-24 07:00 | 2025-02-28 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 730s 701T (730s Rycroft) | 2025-02-24 07:00 | 2025-03-13 17:00 | N | Y |  | Transformer |  |  | For Information Only
ALTALINK | 234L (310p Sundance - 505L tap), 234L1 (234L tap), 505L (234L tap - 505L tap), 505L1 (505L-521L tap), 310p 693 (310p Sundance) | 2025-02-24 07:15 | 2025-02-28 17:45 | N | N |  | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L51 (BPA Custer - BCH Ingledow) | 2025-02-24 09:00 | 2025-02-28 15:30 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 14s T3 (14s Devon) | 2025-02-24 13:00 | 2025-02-25 17:00 | N | N |  | Transformer |  |  | Pre-Condition
ALTALINK | 430s 652 (430s Ursus) | 2025-02-25 07:00 | 2025-02-28 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Firm Load Loss
ATCO | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2025-02-25 09:00 | 2025-02-26 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 946s 901 (946s Oakland), 946s 901A (946s Oakland) | 2025-02-25 09:30 | 2025-02-25 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 895s T3 (895s Suffield), 895s 952 (895s Suffield) | 2025-02-26 06:00 | 2025-02-27 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 890L (58s Edson - 207s Pinedale), 58s 890 (58s Edson), 207s 890 (207s Pinedale) | 2025-02-26 07:15 | 2025-03-03 17:45 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2025-02-26 07:15 | 2025-03-03 17:45 | N | N |  | Line |  |  | Pre-Condition
ALTALINK | 521L (505L tap - 512L tap), 521L (505L tap - 521AL tap), 521L2 (505L-521L tap) | 2025-02-26 07:15 | 2025-02-26 17:45 | N | N |  | Line, Switch |  |  | Pre-Condition
Syncrude | 1735 (Syncrude Mildred Lake), Mildred T17 (Syncrude Mildred Lake) | 2025-02-26 08:00 | 2025-03-17 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
Syncrude | 1435 (Syncrude Mildred Lake), Mildred T14 (Syncrude Mildred Lake) | 2025-02-26 08:00 | 2025-02-27 16:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 946s 904 (946s Oakland) | 2025-02-26 09:30 | 2025-02-26 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO, SUNCOR | 9L162 (29EDD-94 Voyageur - 951s Thickwood Hills), 29EDD-94 29PS-643 (29EDD-94 Voyageur) | 2025-02-26 10:00 | 2025-02-27 17:00 | N | Y |  | Line, Switch |  |  | 240 kV, For Information Only
ALTALINK | 58s 890 (58s Edson) | 2025-02-27 08:00 | 2025-03-03 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 946s 908 (946s Oakland) | 2025-02-27 09:30 | 2025-02-27 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 700L (746s Sherwood Park - 746L tap), 746s 700N (746s Sherwood Park) | 2025-02-27 11:30 | 2025-02-27 15:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L146 (700s Bonnyville - 970s Bourque), 700s 704 (700s Bonnyville), 970s 7L146D2 (970s Bourque) | 2025-02-27 12:00 | 2025-02-27 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 6L02 (769s Stettler - 873s Marion Lake), 769s 601 (769s Stettler) | 2025-02-27 17:00 | 2025-03-10 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, SUNCOR | 9L193 (29EDD-94 Voyageur - 951s Thickwood Hills) | 2025-02-28 10:00 | 2025-02-28 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 320p 2089 (320p Keephills) | 2025-02-28 19:00 | 2025-03-07 19:00 | N | Y |  | Switch |  |  | 500 kV, Restricts Generation
ENMAX | 32.83L (SS-32 - SS-40), 40.1TR (SS-40), 32B138-32.83 (SS-32), 40B138-32.83 (SS-40), 40MD138-40.1TR (SS-40) | 2025-03-02 08:00 | 2025-03-06 14:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1098L (EP 805s Jasper - Poundmaker), EP 805s J2401 (EP 805s Jasper), EP 805s J2407 (EP 805s Jasper), PM2401 (Poundmaker), PM2402 (Poundmaker) | 2025-03-03 07:00 | 2025-03-07 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
EPCOR | T3 (Meadowlark), M723 (Meadowlark), M724 (Meadowlark), MAB3 (Meadowlark) | 2025-03-03 07:00 | 2025-03-04 16:15 | N | N |  | Transformer, Circuit Breaker, Switch |  | Outage completed early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 666L (28s West Brooks - 498s Tilley), 28s 60 (28s West Brooks), 28s 81 (28s West Brooks), 498s 666 (498s Tilley), 28s 666 (28s West Brooks) | 2025-03-03 07:00 | 2025-03-03 17:30 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition, Affects Cranking Path
EPCOR | 816s P2401 (816s Petrolia) | 2025-03-03 07:00 | 2025-03-07 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Restricts Generation
ENMAX | 240kV South Bus (SS-162), 138kV South Bus (SS-162), 162.2TR (SS-162), 162B240-RB133 (SS-162), 162B240-RB136 (SS-162), 162MD240-162.2TR (SS-162), 162B138-RB83 (SS-162), 162B138-RB84 (SS-162), 162B138-RB92 (SS-162), 162MD138-162.2TR (SS-162) | 2025-03-03 08:00 | 2025-03-09 16:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 796s 702 (796s Nipisi), 858S 701TD (858s Narrows Creek) | 2025-03-03 09:00 | 2025-03-10 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 746s T2 (746s Sherwood Park) | 2025-03-03 09:00 | 2025-03-20 12:59 | N | N |  | Transformer |  |  | For Information Only
ATCO | 946s 902 (946s Oakland), 946s 902B (946s Oakland) | 2025-03-03 09:30 | 2025-03-03 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV
ATCO | 734s 701T (734s Sturgeon), 734s 701 (734s Sturgeon) | 2025-03-03 09:30 | 2025-03-03 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap) | 2025-03-03 10:00 | 2025-03-06 15:48 | N | Y |  | Line |  | Ended early | For Information Only
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 7LA129 tap), 526s 152 (526s Buffalo Creek) | 2025-03-03 10:00 | 2025-03-06 15:48 | N | Y |  | Line, Circuit Breaker |  | Ended early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 700s 705C (700s Bonnyville), 700s 705 (700s Bonnyville) | 2025-03-03 10:00 | 2025-03-06 16:38 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2025-03-03 12:01 | 2025-03-12 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 741s 701T (741s Fox Creek), 741s 703 (741s ATC Fox Creek) | 2025-03-03 12:01 | 2025-03-31 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 892L (244s Bowmanton - 895s Suffield), 244s 2952 (244s Bowmanton), 244s 3052 (244S Bowmanton), 895s 892 (895s Suffield), 244s 892 (244s Bowmanton) | 2025-03-04 07:00 | 2025-03-06 12:00 | N | Y |  | Line, Circuit Breaker, Switch |  | Outage extended due to 895s 49 switch broken and requires repair. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 646L (237s Foothills - 678s Okotoks), 237s 552 (237s Foothills), 237s 652 (237s Foothills), 678s 646 (678s Okotoks), 237s 646 (237s Foothills) | 2025-03-04 07:00 | 2025-03-05 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2025-03-04 07:15 | 2025-03-11 15:22 | N | N |  | Line, Circuit Breaker |  | Returned to service early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 283s 138kV Bus (283s Violet Grove), 836L (61s Lodgepole - 283s Violet Grove), 673L (131s Moon Lake - 283s Violet Grove), 283s T1 (283s Violet Grove), 283s C1 (283s Violet Grove), 283s 31 (283s Violet Grove), 283s 836 (283s Violet Grove), 283s 673 (283s Violet Grove), 131s 673 (131s Moon Lake), 61s 836N (61s Lodgepole), 283s 30 (283s Violet Grove) | 2025-03-04 07:30 | 2025-03-04 18:30 | N | Y |  | Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 20.82L (SS-20 - SS-21), 21.80L (42s Sarcee - SS-21), 21.1TR (SS-21), 21.4TR (SS-21), 21B69-21.4TR (SS-21), 21MD138-21.1TR (SS-21), 21B138-20.82 (SS-21), 21B138-21.80 (SS-21), 21MD138-21.4TR (SS-21), 42s 21 (42s Sarcee), 20B138-20.82 (SS-20) | 2025-03-04 08:00 | 2025-03-14 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 744L (228s T.M.P.L. Niton - 744AL tap), 228s 744 (228s T.M.P.L. Niton) | 2025-03-04 08:00 | 2025-03-07 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 332s C1 (332s Ellis) | 2025-03-04 08:30 | 2025-03-04 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 946s 903 (946s Oakland), 946s 903B (946s Oakland) | 2025-03-04 09:30 | 2025-03-04 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 126L1 (6L126 tap), 515s 526 (515s Fed Pipe Judy Creek), 515s 11 (515s Fed Pipe Judy Creek) | 2025-03-05 08:00 | 2025-03-05 16:00 | N | N |  | Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L126 (743s Sarah Lake - 515L tap), 743s 601 (743s Sarah Lake) | 2025-03-05 08:00 | 2025-03-05 15:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2025-03-05 08:00 | 2025-03-06 10:00 | N | N |  | Transformer |  | Work complete. Ended a day early | For Information Only
ALTALINK | 422L (288s Wolf Creek - 331s Ponoka), 331s 422 (331s Ponoka), 288s 422 (288s Wolf Creek) | 2025-03-05 08:30 | 2025-03-05 17:30 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 216s 29 (216s Knightsbridge) | 2025-03-05 08:30 | 2025-03-05 17:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | SASK POWER P2C | 2025-03-05 09:00 | 2025-03-06 18:00 | N | Y |  | Line |  |  | Pre-Condition
ATCO | 946s 905 (946s Oakland), 946s 905B (946s Oakland) | 2025-03-05 09:30 | 2025-03-05 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 100L (498s Tilley - 895s Suffield), 498s 100X (498s Tilley), 895s 100 (895s Suffield) | 2025-03-06 07:00 | 2025-03-06 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 45s Bretona, 874L (45s Bretona - 522s Cooking Lake), 897L (38s East Edmonton - 45s Bretona), 45s T1 (45s Bretona), 45s 138kV Bus (45s Bretona), 45s 897 (45s Bretona), 45s 874 (45s Bretona), 45s 9 (45s Bretona), 522s 874 (522s Cooking Lake), 38s 897 (38s East Edmonton) | 2025-03-06 08:00 | 2025-03-06 16:00 | N | N |  | Station, Line, Transformer, Bus, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 865L (38s East Edmonton - 216s Knightsbridge), 216s 865X (216s Knightsbridge), 38s 865N (38s East Edmonton) | 2025-03-06 08:30 | 2025-03-06 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek), 396s 185 (396s Pincher Creek), 379s 185N (379s Shell Canada Waterton) | 2025-03-06 08:30 | 2025-03-06 11:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 946s 909 (946s Oakland), 946s 909B (946s Oakland) | 2025-03-06 09:30 | 2025-03-06 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge), 216s 32 (216s Knightsbridge), 184s 705W (184s Petro-Canada Edmonton) | 2025-03-06 12:30 | 2025-03-06 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 723L (69s North Barrhead - 724L tap) | 2025-03-08 07:15 | 2025-03-08 17:45 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L64 (747s Bassett - 930s Arcenciel), 7L64 (747s Bassett - 748s Haig River), 7L64 (748s Haig River - 779s Chinchaga River), 747s 701TD (747s Bassett), 748s 701TD (748s Haig River), 748s 701PT (748s Haig River) | 2025-03-08 09:00 | 2025-03-10 16:00 | N | Y |  | Line, Switch, Transformer |  |  | Pre-Condition, Affects Cranking Path
ENMAX | 40.81L (SS-40 - SS-41), 40.2TR (SS-40), 41B138-40.81 (SS-41), 40B138-40.81 (SS-40), 40MD138-40.2TR (SS-40) | 2025-03-09 08:00 | 2025-03-13 14:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | T3 (Garneau), 72RG7 (Garneau - Rossdale), G723 (Garneau), G724 (Garneau), G722 (Garneau), RG725 (Rossdale), GT3 (Garneau), GDS4 (Garneau), GAB3 (Garneau) | 2025-03-10 07:00 | 2025-03-30 12:59 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), M721 (Meadowlark), EP 805s J722 (EP 805s Jasper), EP 805s JDS29 (EP 805s Jasper) | 2025-03-10 07:00 | 2025-04-12 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 744L (228s T.M.P.L. Niton - 744AL tap), 228s 744 (228s T.M.P.L. Niton) | 2025-03-10 08:00 | 2025-03-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L53 (700s Bonnyville - 7LA53 tap), 700s 702 (700s Bonnyville) | 2025-03-10 10:00 | 2025-03-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 377s 473C (377s AML Hardisty) | 2025-03-11 | 2026-01-13 08:29 | N | N |  | Shunts |  |  | Pre-Condition
EPCOR | EP 511s V722 (EP 511s Victoria) | 2025-03-11 07:00 | 2025-04-04 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 702L (137s Sedgewick - 377s AML Hardisty), 377s 702W (377s AML Hardisty) | 2025-03-11 07:00 | 2025-03-12 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 344s T1 (344s Warner), 344s 508 (344s Warner) | 2025-03-11 07:00 | 2025-03-13 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 612L (336s Fincastle - 368s Burdett), 336s 612 (336s Fincastle), 368s 612 (368s Burdett) | 2025-03-11 08:00 | 2025-03-11 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 244s 1052 (244s Bowmanton), 244s C2 (244s Bowmanton) | 2025-03-11 08:00 | 2025-04-08 17:00 | N | Y |  | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 244s C3 (244s Bowmanton), 244s 952 (244s Bowmanton) | 2025-03-11 08:00 | 2025-03-13 17:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 786s 703T (786s High Level), 786s SVC (786s High Level), 786s 703 (786s High Level) | 2025-03-11 08:30 | 2025-03-11 16:00 | N | Y |  | Transformer, Shunts, Circuit Breaker |  | Returned early to service. | Pre-Condition
ALTALINK | 15s 138kV Bus2 (15s Fort Macleod), 725L (15s Fort MacLeod - 725BL tap), 15s T2 (15s Fort Macleod), 15s 452 (15s Fort Macleod), 15s 725 (15s Fort Macleod) | 2025-03-11 08:30 | 2025-03-11 17:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook), 510s 2952 (510s Sunnybrook), 510s 3052 (510s Sunnybrook), 510s 1238 (510s Sunnybrook), 510s 49 (510s Sunnybrook), 510s 51 (510s Sunnybrook), 330p 1238LD (330p Genesee) | 2025-03-11 09:00 | 2025-03-12 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L61 (780s Lubicon - 796s Nipisi), 796s 701 (796s Nipisi) | 2025-03-11 10:00 | 2025-03-11 16:43 | N | N |  | Line, Circuit Breaker |  | Returned early to service. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 507L (83s Taber - 257s Hull), 83s 138kV East Bus (83s Taber), 83s T3 (83s Taber), 83s 64 (83s Taber), 83s C1 (83s Taber), 83s 507 (83s Taber), 83s 61 (83s Taber) | 2025-03-12 07:00 | 2025-03-12 17:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Shunts |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 1L275 (799s Coleman - BCH Natal) | 2025-03-12 08:00 | 2025-03-12 19:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 242s T1 (242s Flat Lake) | 2025-03-12 08:00 | 2025-03-12 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 744L (235s Entwistle - 744AL tap), 235s 744W (235s Entwistle) | 2025-03-12 08:00 | 2025-03-13 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 162.3TR (SS-162), 162B138-RB85 (SS-162), 162B138-RB86 (SS-162), 162MD138-162.3TR (SS-162) | 2025-03-12 08:00 | 2025-03-13 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ATCO | 7L183 (2060s Engstrom - 7LA183 tap) | 2025-03-12 08:30 | 2025-03-13 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | RV728 (Rossdale), 72RV2 (EP 511s Victoria - Rossdale) | 2025-03-13 07:00 | 2025-03-13 17:00 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 199L (347s AML Fox Creek - 199AL tap), 347s 199E (347s AML Fox Creek) | 2025-03-13 07:00 | 2025-03-15 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 944L (132s Ware Junction - 275s Jenner), 275s 2 (275s Jenner), 275s 5 (275s Jenner) | 2025-03-13 07:00 | 2025-03-18 14:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | RW2405 (EP Riverview) | 2025-03-13 07:00 | 2025-03-13 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | T1 (Woodcroft) | 2025-03-13 07:00 | 2025-03-14 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 233s 735N (233s Beamer), 735L (171s Redwater - 233s Beamer) | 2025-03-13 08:30 | 2025-03-13 12:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 786s 505C (786s High Level) | 2025-03-13 09:00 | 2025-03-13 16:00 | N | N |  | Shunts |  |  | Pre-Condition
EPCOR | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 814s B2407 (814s Bellamy), 814s B2406 (814s Bellamy), 814s BDS20 (814s Bellamy) | 2025-03-14 07:00 | 2025-03-14 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 786s 506C (786s High Level) | 2025-03-14 09:00 | 2025-03-14 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 37.2TR (SS-37), 37B138-37.82 (SS-37), 74s 37.82W (74s Janet), SW84 (SS-37), 37MD138-37.2TR (SS-37) | 2025-03-15 08:00 | 2025-03-28 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.2TR (SS-21), 21.1C (SS-21), 60s50 (SS-21), 44s 50X (44s Bearspaw Plant), 21MD138-21.2TR (SS-21) | 2025-03-15 08:00 | 2025-03-24 16:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
ATCO | 786s 507C (786s High Level) | 2025-03-15 09:00 | 2025-03-15 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L65 (709s Vegreville - 7LA65 tap), 709s 703 (709s Vegreville) | 2025-03-15 10:00 | 2025-03-21 16:30 | N | N |  | Line, Circuit Breaker |  | Outage returned early. | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial), 364s 798 (364s Whitecourt Industrial) | 2025-03-16 07:00 | 2025-03-16 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 786s 508C (786s High Level) | 2025-03-16 09:00 | 2025-03-16 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 610L (83s Taber - 336s Fincastle), 83s 610 (83s Taber), 336s 610 (336s Fincastle) | 2025-03-17 07:00 | 2025-03-28 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 1037L (237s Foothills - 266s SC1), 1037L (138s Windy Flats - 266s SC1), 266s 1037L FSC1 (266s SC1) | 2025-03-17 07:00 | 2025-03-24 18:00 | N | Y |  | Line, Shunts |  |  | 240 kV, Overload, Pre-Condition
ALTALINK | 62s 138kV South Bus (62s Brazeau Plant), 202L (61s Lodgepole - 62s Brazeau Plant), 801L (62s Brazeau Plant - 294s Brazeau Plant Outlet Works), 62s T3 (62s Brazeau Plant), 62s T4 (62s Brazeau Plant), 62s T5 (62s Brazeau Plant), 62s T7 (62s Brazeau Plant), 62s C1 (62s Brazeau Plant), 62s 34 (62s Brazeau Plant), 62s 209 (62s Brazeau Plant), 62s 210 (62s Brazeau Plant), 62s 46 (62s Brazeau Plant) | 2025-03-17 07:30 | 2025-03-17 16:00 | N | Y |  | Bus, Line, Transformer, Shunts, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13.1TR (SS-13), 13.3TR (SS-13), 3B138-3.84 (SS-3), 13B138-2.83 (SS-13), 13B138-3.84 (SS-13), 13MD138-13.1TR (SS-13), 13MD138-13.3TR (SS-13), SW83 (SS-13) | 2025-03-17 08:00 | 2025-03-18 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 7L23 (858s Narrows Creek - 7L23 tap), 796s 702 (796s Nipisi), 858S 701TD (858s Narrows Creek) | 2025-03-17 09:00 | 2025-03-20 09:05 | N | N |  | Line, Circuit Breaker, Switch |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 133L (19s Wabamun - 234L tap), 19s 133 (19s Wabamun) | 2025-03-17 09:00 | 2025-03-20 09:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37) | 2025-03-17 09:30 | 2025-03-20 18:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 62s 138kV South Bus (62s Brazeau Plant), 202L (61s Lodgepole - 62s Brazeau Plant), 801L (62s Brazeau Plant - 294s Brazeau Plant Outlet Works), 62s T3 (62s Brazeau Plant), 62s T4 (62s Brazeau Plant), 62s 201 (62s Brazeau Plant), 62s 202 (62s Brazeau Plant), 62s 34 (62s Brazeau Plant) | 2025-03-17 16:01 | 2025-03-20 17:30 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 905L (19s Wabamun - 37s North Calder), 19s 905 (19s Wabamun) | 2025-03-18 07:00 | 2025-03-22 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), RV728 (Rossdale) | 2025-03-18 07:00 | 2025-03-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 913L (69s North Barrhead - 338s Cherhill), 913L (69s North Barrhead - 732s Mitsue), 69s T4 (69s North Barrhead), 69s 913N (69s North Barrhead), 69s 713 (69s North Barrhead), 69s 42 (69s North Barrhead), 69s 43 (69s North Barrhead) | 2025-03-18 08:00 | 2025-03-19 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 38s 75 (38s East Edmonton), 38s 4252 (38s East Edmonton), 95s 11 (95s Imperial Oil Edmonton) | 2025-03-18 08:30 | 2025-03-18 17:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 677L (305s Acheson - 595s Spruce Grove), 305s 677 (305s Acheson), 595s 677 (595s Spruce Grove) | 2025-03-18 09:00 | 2025-03-20 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 415s Drywood), 185AL (415s Drywood - 995s Yarrow), 995s T1 (995s Yarrow), 379s 185E (379s Shell Canada Waterton), 415s 352 (415s Drywood), 995s 185AN (995s Yarrow), 415s 185W (415s Drywood) | 2025-03-18 09:00 | 2025-03-19 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 217s C1 (217s North Red Deer) | 2025-03-18 14:00 | 2026-02-08 17:30 | N | N |  | Shunts |  | Work complete | Pre-Condition
ALTALINK | 610L (83s Taber - 336s Fincastle), 172L (83s Taber - 172EL tap), 83s T1 (83s Taber), 83s 65 (83s Taber), 83s 172W (83s Taber), 83s C2 (83s Taber) | 2025-03-19 07:00 | 2025-03-20 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Shunts |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 422s 700 (422s Westwood), 746s 700N (746s Sherwood Park) | 2025-03-19 08:00 | 2025-03-19 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 1107L (237s Foothills - SS-65), 65B240-D134 (SS-65), 65B240-D133 (SS-65) | 2025-03-19 08:00 | 2025-03-19 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 62s T3 (62s Brazeau Plant), 62s 31 (62s Brazeau Plant) | 2025-03-19 08:00 | 2025-03-19 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 35B138-80 (SS-35) | 2025-03-19 08:00 | 2025-03-21 16:00 | N | N |  | Circuit Breaker |  |  | Firm Load Loss
ALTALINK | 338s 252 (338s Cherhill) | 2025-03-19 09:30 | 2025-03-20 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Firm Load Loss
ATCO | 932s 723C (932s Pemukan) | 2025-03-19 09:30 | 2025-03-20 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-03-19 10:00 | 2025-03-19 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood), 422s 694 (422s Westwood), 54s 694 (54s Fort Saskatchewan) | 2025-03-19 12:30 | 2025-03-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2025-03-20 08:00 | 2026-05-29 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 263s C1 (263s Strachan) | 2025-03-20 08:00 | 2025-07-22 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-03-20 10:00 | 2025-03-20 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 746s 138kV East Bus (746s Sherwood Park), 700L (746s Sherwood Park - 746L tap), 700L (422s Westwood - 746L tap), 746s T2 (746s Sherwood Park), 746s 700N (746s Sherwood Park), 746s 33 (746s Sherwood Park), 422s 700 (422s Westwood) | 2025-03-20 13:00 | 2025-03-21 18:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-03-21 10:00 | 2025-03-21 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 34.1TR (SS-34) | 2025-03-22 08:00 | 2025-03-22 12:00 | N | N |  | Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 7L64 (779s Chinchaga River - 789s Keg River), 7L64 (748s Haig River - 779s Chinchaga River), 779s 701T (779s Chinchaga River), 789s 701 (789s Keg River), 779s 701TCS (779s Chinchaga River) | 2025-03-22 09:00 | 2025-03-22 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  | Outage returned early | Pre-Condition, Affects Cranking Path
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-03-22 10:00 | 2025-03-22 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 26.1TR (SS-26) | 2025-03-23 08:00 | 2025-03-25 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2025-03-23 08:00 | 2025-03-25 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32), 32B138-31.84 (SS-32), 32MD138-32.3TR (SS-32) | 2025-03-24 08:00 | 2025-03-24 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2025-03-24 08:00 | 2025-03-24 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ENMAX | 1.80L (SS-1 - SS-28) | 2025-03-24 08:00 | 2025-03-24 09:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20) | 2025-03-24 09:00 | 2025-03-24 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake), 715s 703 (715s Leming Lake), 717s 702 (717s Ethel Lake) | 2025-03-24 09:00 | 2025-03-24 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43) | 2025-03-24 10:00 | 2025-03-24 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 800s 501C1 (800s Friedenstal), 800s 501C2 (800s Friedenstal) | 2025-03-24 10:00 | 2025-03-31 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10), 42s 693 (42s Sarcee), 10B138-693 (SS-10) | 2025-03-24 11:30 | 2025-03-25 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 33.84L (SS-33 - SS-43) | 2025-03-24 12:00 | 2025-03-24 14:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 310p 1552 (310p Sundance) | 2025-03-24 12:30 | 2025-03-28 11:00 | N | Y |  | Circuit Breaker |  | Back in service. | 240 kV, For Information Only
ALTALINK | 1038L (138s Windy Flats - 266s SC1), 1038L (237s Foothills - 266s SC1), 266s 1038L FSC2 (266s SC1) | 2025-03-25 07:00 | 2025-03-29 15:00 | N | Y |  | Line, Shunts |  |  | 240 kV, Overload, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 37s 726E (37s North Calder) | 2025-03-25 07:15 | 2025-03-25 17:45 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 74s 2452 (74s Janet) | 2025-03-25 07:30 | 2025-03-25 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 20.82L (SS-20 - SS-21), 21.80L (42s Sarcee - SS-21), 50L (44s Bearspaw Plant - SS-21), 21.1TR (SS-21), 21.2TR (SS-21), 21.4TR (SS-21), 21MD138-21.2TR (SS-21), 21MD138-21.4TR (SS-21), 21MD138-21.1TR (SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21), 21B138-21.80 (SS-21), 21B138-20.82 (SS-21), 20B138-20.82 (SS-20), 42s 21 (42s Sarcee), 21.1C (SS-21) | 2025-03-25 08:00 | 2025-03-28 18:00 | N | Y |  | Line, Transformer, Switch, Circuit Breaker, Shunts |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21) | 2025-03-25 08:00 | 2025-03-28 18:00 | N | Y |  | Line |  |  | For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33MD138-33.1TR (SS-33), 33B138-33.83 (SS-33) | 2025-03-25 08:00 | 2025-03-25 12:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, ENMAX | 42s 22 (42s Sarcee), 21.80L (42s Sarcee - SS-21) | 2025-03-25 08:00 | 2025-03-28 18:00 | N | Y |  | Switch, Line |  |  | For Information Only
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake), 17s 637 (17s Benalto), 580s 637 (580s Sylvan Lake) | 2025-03-25 08:30 | 2025-03-25 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 123L (19s Wabamun - 352s Onoway), 352s T1 (352s Onoway), 352s 123 (352s Onoway), 352s 21 (352s Onoway), 352s 1 (352s Onoway) | 2025-03-25 09:30 | 2025-03-26 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43), 33.2TR (SS-33), 33MD138-33.2TR (SS-33), 33B138-33.84 (SS-33) | 2025-03-25 12:00 | 2025-03-25 18:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 636L (420s Broadmoor - 746s Sherwood Park), 420s 636 (420s Broadmoor), 746s 636 (746s Sherwood Park) | 2025-03-26 07:00 | 2025-04-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), 9MD138-9.1TR (SS-9) | 2025-03-26 08:00 | 2025-03-26 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 35B138-81 (SS-35) | 2025-03-26 08:00 | 2025-03-27 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
GLEI | GLE1 Gleichen Solar Generator Test | 2025-03-26 08:00 | 2025-06-20 22:00 | N | Y |  | Unit
ALTALINK, WINNIFRED | 498L (523s Bullshead - 1054s Holsom), 523s 498 (523s Bullshead), 1054s T1 (1054s Holsom), 1054s 138CB1 (1054s Holsom) | 2025-03-26 08:00 | 2025-03-27 17:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Restricts Generation
ATCO | 2075s 905 (2075s Newell) | 2025-03-26 09:00 | 2025-03-26 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 62s T2 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant) | 2025-03-26 23:00 | 2025-03-27 05:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 945s T2 (945s Sunshine Village), 945s 29 (945s Sunshine Village) | 2025-03-27 08:30 | 2025-03-28 16:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 846s 701 (846s Grand Centre), 717s 701 (717s Ethel Lake) | 2025-03-27 09:00 | 2025-03-27 14:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s 911 (2075s Newell), 2075s 911A (2075s Newell) | 2025-03-27 09:00 | 2025-03-27 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV
BCH | 2L113 (BCH Cranbrook - BCH Natal), T4 (BCH Natal) | 2025-03-27 10:30 | 2025-03-27 11:30 | N | Y |  | Line, Transformer |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 7L24 (846s Grand Centre - 7LA24 tap), 846s 702 (846s Grand Centre) | 2025-03-27 14:01 | 2025-03-28 14:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 240kV West Bus (SS-25), 1109L (SS-25 - SS-65), 25B240-D136 (SS-25), 25B240-D133 (SS-25), 25B240-D141 (SS-25), 25B240-D142 (SS-25), 25B240-D139 (SS-25), 25MD240-1109 (SS-25) | 2025-03-28 09:00 | 2025-04-30 14:00 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 2075s 920 (2075s Newell) | 2025-03-28 09:00 | 2025-03-28 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
ENMAX | 39.82L (SS-39 - SS-162), 39B138-39.82 (SS-39) | 2025-03-29 08:00 | 2025-03-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 72RG1 (Garneau - Rossdale), T3 (Garneau), G723 (Garneau), G724 (Garneau), G725 (Garneau), GT3 (Garneau), RG7210 (Rossdale), GDS18 (Garneau), GAB3 (Garneau) | 2025-03-30 13:00 | 2025-04-17 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK, ENMAX | 5s 240kV Bus 1 (5s East Calgary), 5s T1 (5s East Calgary), 5s 1152 (5s East Calgary), 5s 1652 (5s East Calgary), MD112 (SS-2) | 2025-03-31 07:00 | 2025-04-04 19:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 987s T1 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar) | 2025-03-31 07:00 | 2025-10-24 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16) | 2025-03-31 08:00 | 2025-03-31 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 769s 704C (769s Stettler) | 2025-03-31 09:00 | 2025-03-31 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34) | 2025-03-31 10:01 | 2025-03-31 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 977s 910R (977s Salt Creek) | 2025-03-31 11:00 | 2025-03-31 16:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 14s T3 (14s Devon) | 2025-03-31 12:00 | 2025-04-01 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 741s 702T (741s Fox Creek), 741s 704 (741s ATC Fox Creek) | 2025-03-31 12:01 | 2025-04-25 15:50 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 87s 952 (87s Gaetz) | 2025-03-31 12:30 | 2025-03-31 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Prevents Normal Events
ATCO | 7L143 (766s Nevis - 769s Stettler), 769s 705 (769s Stettler), 766s 703 (766s Nevis) | 2025-03-31 13:00 | 2025-03-31 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 814s T2 (814s Bellamy), 814s B2402 (814s Bellamy), 814s B2406 (814s Bellamy), BR722 (Rossdale) | 2025-04-01 07:00 | 2025-04-01 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 221s T3 (221s Sunken Lake), 221s 39 (221s Sunken Lake) | 2025-04-01 07:00 | 2025-04-01 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 23B138-23.80 (SS-23), 23MD138-23.4TR (SS-23) | 2025-04-01 08:00 | 2025-04-01 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s T1 (17s Benalto) | 2025-04-01 08:00 | 2025-04-02 18:30 | N | N |  | Transformer |  |  | For Information Only
REDDEER | 217s T1 (217s North Red Deer), 217s T2 (217s North Red Deer) | 2025-04-01 08:00 | 2025-04-03 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 170s T2 (170s Pike) | 2025-04-01 08:00 | 2025-04-02 17:04 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ENMAX | 15.60L (SS-15 - SS-21) | 2025-04-01 08:00 | 2025-04-01 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.1TR (SS-14) | 2025-04-01 08:00 | 2025-04-01 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 977s 901 (977s Salt Creek) | 2025-04-01 09:00 | 2025-04-01 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L701 (757s Battle River - 7LA701 tap), 757s 707 (757s Battle River) | 2025-04-01 09:00 | 2025-04-08 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 368s C1 (368s Burdett) | 2025-04-01 09:00 | 2025-04-01 17:00 | N | N |  | Shunts |  |  | Pre-Condition
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2025-04-01 09:00 | 2025-04-04 17:00 | Y | Y |  | Line |  |  | Limits ATC, 500 kV
ATCO, ALTALINK | 7L224 (650s Hansman Lake - 774s Monitor), 774s 701 (774s Monitor), 650s 1752 (650s Hansman Lake) | 2025-04-01 09:30 | 2025-04-01 16:00 | N | Y |  | Line, Circuit Breaker |  | Completed Early | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 869s 702T (869s Seal Lake), 869s 702 (869s Seal Lake) | 2025-04-01 09:30 | 2025-04-11 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 21.61L (SS-21 - SS-34) | 2025-04-01 10:01 | 2025-04-01 12:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23) | 2025-04-01 12:01 | 2025-04-01 18:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 977s 902 (977s Salt Creek) | 2025-04-01 12:30 | 2025-04-01 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2025-04-02 08:00 | 2025-04-02 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.2TR (SS-26) | 2025-04-02 08:00 | 2025-04-03 12:00 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 26B138-26.83 (SS-26) | 2025-04-02 08:00 | 2025-04-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 977s 904 (977s Salt Creek) | 2025-04-02 09:00 | 2025-04-02 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 749s 701 (749s Flyingshot Lake) | 2025-04-02 12:00 | 2025-04-03 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 7L24 (700s Bonnyville - 7LA24 tap), 700s 708 (700s Bonnyville) | 2025-04-02 12:00 | 2025-04-02 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 977s 905 (977s Salt Creek) | 2025-04-02 12:30 | 2025-04-02 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 23.4TR (SS-23) | 2025-04-02 13:00 | 2025-04-04 14:00 | N | N |  | Transformer |  |  | Pre-Condition
ATCO | 6L05 (764s Heisler - 843s Bigknife Creek) | 2025-04-03 08:00 | 2025-04-07 13:00 | N | N |  | Line |  |  | Pre-Condition
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary), MD109 (SS-2), MD110 (SS-2) | 2025-04-03 08:00 | 2025-04-04 16:00 | N | N |  | Shunts, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2025-04-03 08:00 | 2025-04-04 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 977s 901T (977s Salt Creek), 7L135 (820s Hangingstone - 977s Salt Creek) | 2025-04-03 09:00 | 2025-04-03 16:00 | N | Y |  | Transformer, Line |  |  | 240 kV, For Information Only
ATCO | 7L64 (779s Chinchaga River - 789s Keg River), 789s 701 (789s Keg River) | 2025-04-04 08:00 | 2025-04-04 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Pre-Condition, Affects Cranking Path
ICPCL, TRANSALTAGP | RYMD Raymond Reservoir Generator Test | 2025-04-04 08:00 | 2025-05-13 16:00 | N | N |  | Unit
ENMAX | 24.1TR (SS-24) | 2025-04-04 08:00 | 2025-04-12 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5CB2 (BCH Selkirk) | 2025-04-04 09:00 | 2025-04-04 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Limits ATC
ALTALINK, BHE | 879L (244s Bowmanton - 879AL tap), 879L (368s Burdett - 879L tap), 879AL (719s Rattlesnake Ridge - 879L tap), 368s 879 (368s Burdett), 719s 138CB1 (719s Rattlesnake Ridge) | 2025-04-04 10:00 | 2025-04-04 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 698s 452 (698s Jackfish) | 2025-04-04 13:00 | 2025-04-07 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 879L (368s Burdett - 879L tap), 368s 879 (368s Burdett) | 2025-04-04 13:01 | 2025-04-09 14:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX, ALTALINK | SS-47, 771L (SS-47 - SS-162), 47.1TR (SS-47), 47.2TR (SS-47), 162B138-RB81 (SS-162), 162B138-RB82 (SS-162), 47B138-771 (SS-47), 47B138-771/1 (SS-47), 47B138-BT3 (SS-47), 47MD138-47.1TR (SS-47), 47MD138-47.2TR (SS-47), 162MD138-771L (SS-162) | 2025-04-05 08:00 | 2025-04-06 16:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 113s T1 (113s Inland Cement) | 2025-04-06 06:30 | 2025-04-17 17:00 | N | N |  | Transformer
CMH | MHS-1 69kV South Bus (MHS-1 Power P Switchyard), MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview), MHS-1 MH69-10 (MHS-1 CMH Power Plant), MHS-1 MH69-21 (MHS-1 CMH Power Plant), MHS-1 MH69-31 (MHS-1 CMH Power Plant), MHS-1 MH69-42 (MHS-1 CMH Power Plant), MHS-6 MH69-614 (MHS-6 CMH Riverview) | 2025-04-06 07:30 | 2025-04-10 16:00 | N | N |  | Bus, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 6.80L (SS-6 - SS-35), 6B138-6.80 (SS-6), 35MD138-6.80 (SS-35) | 2025-04-06 08:00 | 2025-04-08 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft), T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft), EP 805s J724 (EP 805s Jasper), EP 805s JDS28 (EP 805s Jasper), WDS3 (Woodcroft), WAB1 (Woodcroft) | 2025-04-07 07:00 | 2025-05-02 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH, ALTALINK | 1L275 (799s Coleman - BCH Natal), 799s 786W (799s Coleman) | 2025-04-07 07:00 | 2025-04-14 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 665s T2 (665s Dome) | 2025-04-07 07:00 | 2025-04-08 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 7.84L (SS-7 - SS-36), 36B138-7.84 (SS-36), 7B138-7.84 (SS-7) | 2025-04-07 08:00 | 2025-04-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 162.81L (391s Balzac - SS-162), 162B138-RB80 (SS-162), 162B138-RB81 (SS-162), 391s 162.81 (391s Balzac), 162MD138-162.81 (SS-162) | 2025-04-07 08:00 | 2025-04-08 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 23.3TR (SS-23) | 2025-04-07 08:00 | 2025-04-09 14:00 | N | N |  | Transformer |  |  | For Information Only
CMH | MHS-3 MH69-T32 (MHS-3 Southridge), MHS-3 MH69-306 (MHS-3 Southridge) | 2025-04-07 08:00 | 2025-04-17 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 700s 706C (700s Bonnyville) | 2025-04-07 10:00 | 2025-04-11 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 20.1TR (SS-20) | 2025-04-07 11:00 | 2025-04-10 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 157s T1 (157s Lac La Biche) | 2025-04-07 14:00 | 2025-04-10 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, DOW | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen), 166s 899N (166s Dow Chemical Fort Saskatchewan) | 2025-04-08 06:30 | 2025-04-09 19:30 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 523s T1 (523s Bullshead) | 2025-04-08 07:00 | 2025-04-09 18:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 72s T1 (72s Leismer) | 2025-04-08 07:30 | 2025-04-12 10:30 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ATCO | 934s 240kV Bus 900BS1 (934s Blackfly), 934s 901 (934s Blackfly) | 2025-04-08 09:30 | 2025-04-08 17:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 6L02 (765s Mannix Mine - 873s Marion Lake) | 2025-04-08 11:00 | 2025-04-08 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
EPCOR | 665s T1 (665s Dome) | 2025-04-09 07:00 | 2025-04-10 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 535s 5752 (535s Joffre) | 2025-04-09 07:30 | 2025-04-09 12:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 508s T1 (508s Lakesend), 508s 696 (508s Lakesend) | 2025-04-09 08:00 | 2025-04-09 20:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 28.1TR (SS-28) | 2025-04-09 08:00 | 2025-04-10 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 263s T2 (263s Strachan) | 2025-04-09 08:00 | 2025-04-09 13:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29PL7-10 (29EDD-18 Firebag - 29EDD-85), 29EDD-85 752-10010 (29EDD-85), 29EDD-85 752-10030 (29EDD-85), 29EDD-18 29-752-101 (29EDD-18 Firebag), 29EDD-18 29-752-102 (29EDD-18 Firebag), 29EDD-18 29PS-0043 (29EDD-18 Firebag), 29EDD-85 29PS-319 (29EDD-85) | 2025-04-09 08:00 | 2025-04-17 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 162B240-RB135 (SS-162), 162B240-RB136 (SS-162), 162MD240-932L (SS-162) | 2025-04-09 08:00 | 2025-04-10 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation, Affects Cranking Path
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6), 41B138-6.82 (SS-41) | 2025-04-09 08:00 | 2025-04-11 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap), 725L (111s Coalbanks - 725AL tap), 725L (674s Bowron - 725AL tap), 618s 725 (618s Riverbend), 674s 725E (674s Bowron), 111s 725LE (111s Coalbanks) | 2025-04-09 09:00 | 2025-04-09 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 934s 901 (934s Blackfly) | 2025-04-09 10:00 | 2025-04-09 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 1045s RTU/SCADA (1045s Garden Plain) | 2025-04-09 10:00 | 2025-04-09 11:30 | N | N |  | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 535s 5552 (535s Joffre) | 2025-04-09 12:30 | 2025-04-09 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 934s 902 (934s Blackfly) | 2025-04-09 13:01 | 2025-04-09 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, BHE | 879L (244s Bowmanton - 879AL tap), 879L (368s Burdett - 879L tap), 368s 879 (368s Burdett), 719s 138CB1 (719s Rattlesnake Ridge) | 2025-04-09 14:01 | 2025-04-09 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 186s T2 (186s Dry Creek) | 2025-04-10 07:30 | 2025-04-10 18:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 635PL7-1004 (635EDD-1001 - 635EDD-1002), 635EDD-1001 635PS-1113 (635EDD-1001) | 2025-04-10 08:30 | 2025-04-10 12:00 | N | Y |  | Line, Switch |  |  | Pre-Condition, Restricts Generation
ATCO | 6L73 (729s Otauwau - 745s Slave Lake), 729s 702 (729s Otauwau), 729s 702T (729s Otauwau), 729s 601 (729s Otauwau) | 2025-04-10 09:00 | 2025-04-10 12:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
GWPCORP | 243s Soderglen | 2025-04-10 09:00 | 2025-04-13 18:00 | N | N |  | Station |  |  | Restricts Generation
ALTALINK | 197s 138kV Bus (197s Bardo), 174L (197s Bardo - 289s Saunders Lake), 174L (197s Bardo - 395s North Holden), 730L (197s Bardo - 732L tap), 197s 174W (197s Bardo), 197s 174E (197s Bardo), 395s 174W (395s North Holden), 197s 6 (197s Bardo), 289s 174 (289s Saunders Lake) | 2025-04-10 09:00 | 2025-04-10 18:00 | N | N |  | Bus, Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 934s 905 (934s Blackfly) | 2025-04-10 10:00 | 2025-04-10 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 20.3TR (SS-20) | 2025-04-10 12:30 | 2025-04-12 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 934s 906 (934s Blackfly) | 2025-04-10 13:01 | 2025-04-10 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAXGPI, ALTALINK | 134s Taber Wind Farm, 607AL (134s Taber Wind Farm - 607L tap), 134s 134.1TR (134s Taber Wind Farm), 134s 134.2TR (134s Taber Wind Farm), 134s B138-607AL (134s Taber Wind Farm), 134s B25-134.1TR (134s Taber Wind Farm), 134s B25-134.2TR (134s Taber Wind Farm), 134s MD138-607AL (134s Taber Wind Farm), 134s MD138-134.1TR (134s Taber Wind Farm), 134s MD138-134.2TR (134s Taber Wind Farm), 134s 134.2CAP (134s Taber Wind Farm), 134s 134.1CAP (134s Taber Wind Farm) | 2025-04-11 07:00 | 2025-04-14 18:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker, Switch, Shunts |  |  | Pre-Condition
EPCOR | T1 (Strathcona) | 2025-04-11 07:00 | 2025-04-11 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 135s Conrad, 607L (336s Fincastle - 607AL tap), 607L (135s Conrad - 607AL tap), 135s T1 (135s Conrad), 135s T2 (135s Conrad), 336s 607 (336s Fincastle), 135s 152 (135s Conrad), 135s 252 (135s Conrad), 135s 352 (135s Conrad), 135s 289 (135s Conrad), 135s 389 (135s Conrad), 135s 689 (135s Conrad) | 2025-04-11 07:00 | 2025-04-14 18:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.2TR (SS-9), 9.3TR (SS-9), 9BA8-9.3TR (SS-9), 9BB8-9.3TR (SS-9), 9B138-9.83 (SS-9), 9B138-2.81 (SS-9), 9MD138-9.3TR (SS-9), SW83 (SS-9), SW84 (SS-9), 2MD138-2.81 (SS-2) | 2025-04-11 08:00 | 2025-04-11 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-15L (MHS-7 Brier Park - MHS-9 South Saskatchewan), MH-6L (MHS-1 CMH Power Plant - MHS-9 South Saskatchewan), MHS-9 MH138-T11 (MHS9 Power Plant), MHS-7 MH138-722 (MHS-7 Brier Park) | 2025-04-11 08:00 | 2025-04-11 16:00 | N | N |  | Line, Transformer, Switch |  |  | Pre-Condition, Restricts Generation
BCH | 1L275 (799s Coleman - BCH Natal) | 2025-04-11 09:00 | 2025-04-11 17:00 | N | Y |  | Line |  |  | Pre-Condition
ALTALINK | 170s T2 (170s Pike) | 2025-04-12 09:00 | 2025-04-16 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO, ALBIAN | 9LJH1 (919s Hartley - 920s Jackpine), 920s 901T (920s Jackpine), 919s 905 (919s Hartley), 920s 9LJH-1D2 (920s Jackpine) | 2025-04-13 08:00 | 2025-04-23 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ATCO, ALBIAN | 920s 901T (920s Jackpine) | 2025-04-13 08:00 | 2025-04-23 16:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK, TRANSCANADA | 303s Saddlebrook, 142s Magcan, 303s 34.5V Bus B1 (303s Saddlebrook), 142s 138kV Bus (142s Magcan), 727A1L (303s Saddlebrook - 727AL tap), 727AL (142s Magcan - 727L tap), 727L (65s High River - 727AL tap), 727L (678s Okotoks - 727AL tap), 303s T1 (303s Saddlebrook), 303s CAP-1 (303s Saddlebrook), 142s C1 (142s Magcan), 303s 52T1 (303s Saddlebrook), 303s 52F1 (303s Saddlebrook), 303s 52F2 (303s Saddlebrook), 303s 52F3 (303s Saddlebrook), 142s 3 (142s Magcan), 678s 727 (678s Okotoks), 65s 727N (65s High River), 303s 89B1 (303s Saddlebrook), 303s 89T1 (303s Saddlebrook), 142s 727ALN (142s Magcan), 142s 11 (142s Magcan), 142s 2 (142s Magcan), 727L52N (727AL tap), 727L52S (727AL tap) | 2025-04-14 07:00 | 2025-04-16 18:00 | N | Y |  | Station, Bus, Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
EPCOR | R723 (Rossdale) | 2025-04-14 07:00 | 2025-04-14 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), H724 (EP Hardisty) | 2025-04-14 07:00 | 2025-04-14 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 52s E2402 (52s East Industrial), 52s T2 (52s East Industrial) | 2025-04-14 07:00 | 2025-05-23 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
CMH | MHS-1 69kV North Bus (MHS-1 Power P Switchyard), 4L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview), MHS-1 MH69-2 (MHS-1 CMH Power Plant), MHS-1 MH69-13 (MHS-1 CMH Power Plant), MHS-1 MH69-24 (MHS-1 CMH Power Plant), MHS-1 MH69-34 (MHS-1 CMH Power Plant), MHS-6 MH69-607 (MHS-6 CMH Riverview) | 2025-04-14 08:00 | 2025-04-17 17:00 | N | N |  | Bus, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 725L (674s Bowron - 725BL tap) | 2025-04-14 08:00 | 2025-04-15 17:00 | N | Y |  | Line |  |  | Pre-Condition
ENMAX | 162.4TR (SS-162) | 2025-04-14 08:00 | 2025-04-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 24.82L (SS-24 - SS-65), 24.2TR (SS-24), 24B138-24.82 (SS-24) | 2025-04-14 08:00 | 2025-04-14 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Overload, Pre-Condition
Lethbridge, ALTALINK | 674s 725W (674s Bowron), 725L (674s Bowron - 725BL tap), 674s T1 (674s Bowron) | 2025-04-14 08:00 | 2025-04-15 17:00 | N | Y |  | Circuit Breaker, Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2025-04-14 09:00 | 2025-04-23 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH, ALTALINK | 1L275 (799s Coleman - BCH Natal), 799s 786W (799s Coleman) | 2025-04-14 09:00 | 2025-04-14 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker), PM2403 (Poundmaker), PM2404 (Poundmaker), PMDS10 (Poundmaker) | 2025-04-14 09:30 | 2025-04-17 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 730s STATCOM (730s Rycroft), 730s 702T (730s Rycroft), 730s 705 (730s Rycroft) | 2025-04-14 09:30 | 2025-04-18 17:30 | N | Y |  | Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 700s 707C (700s Bonnyville), 700s 707 (700s Bonnyville) | 2025-04-14 10:00 | 2025-04-17 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 86s 852 (86s Bigstone), 40s 804W (40s Wetaskiwin), 804L (40s 803L tap - 86s 803L tap), 804L (40s Wetaskiwin - 40s 803L tap), 804L (86s Bigstone - 86s 803L tap) | 2025-04-14 14:00 | 2025-04-16 17:30 | N | N |  | Circuit Breaker, Line |  |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L101 (790s Poplar Hill - 944s Lowe Lake), 790s 705 (790s Poplar Hill) | 2025-04-15 07:00 | 2025-04-18 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 385s T1 (385s Spring Coulee), 385s T3 (385s Spring Coulee) | 2025-04-15 07:00 | 2025-04-16 17:00 | N | N |  | Transformer |  |  | Restricts Generation
EPCOR | R724 (Rossdale) | 2025-04-15 07:00 | 2025-04-15 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 430s 152 (430s Ursus) | 2025-04-15 07:00 | 2025-04-17 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), H725 (EP Hardisty), H723 (EP Hardisty), S724 (Strathcona) | 2025-04-15 07:00 | 2025-04-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 22.3TR (SS-22), 22.1TR (SS-22), 22B138-22BT8 (SS-22), 22B138-13.82 (SS-22) | 2025-04-15 08:00 | 2025-04-15 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 245s T2 (245s Seebe) | 2025-04-15 08:00 | 2025-04-15 17:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | Mildred T16 (Syncrude Mildred Lake), 1635 (Syncrude Mildred Lake) | 2025-04-15 08:00 | 2025-04-18 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | T4 (BCH Natal) | 2025-04-15 09:00 | 2025-05-05 20:00 | N | Y |  | Transformer |  |  | 240 kV
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22BT8 (SS-22), 22B138-22.81 (SS-22) | 2025-04-15 12:00 | 2025-04-15 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 802s 703T (802s Michichi Creek), 802s 703 (802s Michichi Creek) | 2025-04-16 08:00 | 2025-04-16 14:00 | N | N |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2025-04-16 08:00 | 2025-04-17 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK, Lethbridge | 725L (674s Bowron - 725AL tap), 674s 725E (674s Bowron) | 2025-04-16 08:00 | 2025-04-16 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Lethbridge | 674s 725E (674s Bowron) | 2025-04-16 08:00 | 2025-04-16 17:00 | N | Y |  | Circuit Breaker |  |  | For Information Only
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20) | 2025-04-16 08:00 | 2025-04-16 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 741s 504C (741s Fox Creek) | 2025-04-17 08:00 | 2025-04-17 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 12.2TR (SS-12) | 2025-04-17 08:00 | 2025-04-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 1003L (74s Janet - SS-25) | 2025-04-17 13:00 | 2025-04-20 18:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 2GSU-XF-001 (SS-25), 25B240-D134 (SS-25), 25B240-D135 (SS-25) | 2025-04-17 13:00 | 2025-04-20 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Restricts Generation
ENMAX | 47B138-BT3 (SS-47) | 2025-04-20 08:00 | 2025-04-20 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
CMH | MH69s2 T21 (MH69s2 North Industrial), MHS-2 MH69-206 (MHS-2 North Industrial) | 2025-04-21 08:00 | 2025-04-25 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
SUNCOR | Suncor Distribution Breaker | 2025-04-21 08:00 | 2025-04-27 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
SUNCOR | 29EDD-1 Millennium 260kV West Bus 1, 29EDD-1 29EDD1s1052 (29EDD-1 Millennium) | 2025-04-21 08:00 | 2025-04-28 17:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 879s 701T (879s Scottford Upgrader) | 2025-04-21 08:30 | 2025-05-05 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 63s T3 (63s Red Deer), 63s 26 (63s Red Deer) | 2025-04-21 08:30 | 2025-04-25 12:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, TRANSALTA | 20s T1 (20s Ghost) | 2025-04-21 12:30 | 2025-05-01 11:30 | N | Y |  | Transformer |  |  | For Information Only, Restricts Generation
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), RV728 (Rossdale) | 2025-04-22 07:00 | 2025-04-23 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | M725 (Meadowlark) | 2025-04-22 07:00 | 2025-04-23 10:00 | N | N |  | Circuit Breaker |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s J2405 (EP 805s Jasper) | 2025-04-22 07:00 | 2025-04-25 09:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 15.62L (SS-15 - SS-16), 15.2TR (SS-15), 15B69-15.62 (SS-15) | 2025-04-22 08:00 | 2025-04-22 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65.1TR (SS-65) | 2025-04-22 08:00 | 2025-04-30 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 2075s ACF22 (2075s Newell) | 2025-04-22 09:00 | 2025-04-23 17:30 | N | Y |  | Shunts |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2029s 500kV Bus 1200BS1 (2029s Heathfield), 2029s 1201 (2029s Heathfield), 2029s 1204 (2029s Heathfield), 2029s 1207 (2029s Heathfield), 2029s 1214 (2029s Heathfield) | 2025-04-22 09:30 | 2025-04-25 17:30 | N | Y |  | Bus, Circuit Breaker |  |  | 500 kV, For Information Only
ATCO | 7L22 (790s Poplar Hill - 7L88 tap), 790s 702 (790s Poplar Hill) | 2025-04-22 09:30 | 2025-04-22 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 790s 701C (790s Poplar Hill), 790s 701 (790s Poplar Hill) | 2025-04-22 12:01 | 2025-04-23 09:30 | N | N |  | Shunts, Circuit Breaker |  | back early | Pre-Condition
ALTALINK | 163s T1 (163s Amoco Empress) | 2025-04-22 13:00 | 2025-05-02 17:00 | N | Y |  | Transformer |  |  | For Information Only
ATCO | 939s 912 (939s Livock) | 2025-04-22 13:30 | 2025-04-22 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 185s T2 (185s Bretville) | 2025-04-23 06:00 | 2025-05-07 08:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 814s T2 (814s Bellamy), T1 (Rossdale), BR722 (Rossdale), RR723 (Rossdale), R721 (Rossdale) | 2025-04-23 07:00 | 2025-04-27 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24) | 2025-04-23 08:00 | 2025-04-24 16:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 729L (285s East Camrose - 542s Ervick), 542s 729W (542s Ervick), 285s 729W (285s East Camrose) | 2025-04-23 08:00 | 2025-04-23 17:00 | N | N |  | Line, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - SS-24), 24B138-24.83 (SS-24), 74s 24.83X (74s Janet) | 2025-04-23 08:00 | 2025-04-24 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 21.61L (SS-21 - SS-34), 34B69-21.61 (SS-34), 21B69-21.61 (SS-21) | 2025-04-23 08:00 | 2025-04-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5CB2 (BCH Selkirk) | 2025-04-23 09:00 | 2025-04-24 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Limits ATC
ALTALINK | 12s 952 (12s Heartland) | 2025-04-23 09:00 | 2025-04-23 16:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 939s 901 (939s Livock) | 2025-04-23 09:30 | 2025-04-23 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
EPCOR | M726 (Meadowlark), 72PM25 (Poundmaker - Meadowlark), PM721 (Poundmaker) | 2025-04-23 10:01 | 2025-04-23 17:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 939s 903 (939s Livock) | 2025-04-23 11:31 | 2025-04-23 14:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 32.83L (SS-32 - SS-40), 40B138-32.83 (SS-40), 32B138-32.83 (SS-32) | 2025-04-23 12:00 | 2025-04-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 939s 904 (939s Livock) | 2025-04-23 14:01 | 2025-04-23 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray), 20s 113 (20s Ghost), 33s 113 (33s Spray) | 2025-04-24 07:00 | 2025-04-29 18:00 | N | N |  | Line, Circuit Breaker |  | TFO has informed us that the outage has been extended until April.28/25. | Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 661s Laura Lake, 996s Imperial Oil Carson Lake, 526L (519L tap - 526AL tap), 519L (519AL tap - 526L tap), 526L (519L tap - 526BL tap), 519AL (661s Laura Lake - 519L tap), 519L (996s Imperial Oil Carson Lake - 519AL tap), 661s T1 (661s Laura Lake), 996s T1 (996s Imperial Oil Carson Lake), 661s 5 (661s Laura Lake), 526L365 (526AL tap), 996s 519 (996s Imperial Oil Carson Lake), 996s 5 (996s Imperial Oil Carson Lake), 661s 1 (661s Laura Lake) | 2025-04-24 08:00 | 2025-04-24 17:00 | N | N |  | Station, Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6) | 2025-04-24 08:00 | 2025-04-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.63L (SS-16 - SS-36), 36B69-16.63/36.5TR (SS-36), 36.5TR (SS-36) | 2025-04-24 08:00 | 2025-04-24 16:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | For Information Only, Pre-Condition
ATCO | 2075s ACF23 (2075s Newell) | 2025-04-24 09:00 | 2025-04-24 17:30 | N | Y |  | Shunts |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 746s T1 (746s Sherwood Park) | 2025-04-24 09:00 | 2025-04-24 15:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 939s 910 (939s Livock), 939s 911 (939s Livock), 939s 903T (939s Livock) | 2025-04-24 09:30 | 2025-04-24 15:30 | N | Y |  | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L104 (856s Kinosis - 989s Quigley) | 2025-04-24 10:00 | 2025-04-24 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 755L (247s Piper Creek - 535s Joffre), 247s 755 (247s Piper Creek) | 2025-04-24 10:00 | 2025-04-24 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2025-04-24 10:00 | 2025-04-24 14:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
ATCO, ALBIAN | 9LJH2 (919s Hartley - 920s Jackpine), 920s 902T (920s Jackpine), 919s 907 (919s Hartley), 920s 902 (920s Jackpine), 920s B1 (920s Jackpine), 919s 9LJH-2D1 (919s Hartley), 920s 9LJH-2D2 (920s Jackpine), 920s 902TD (920s Jackpine) | 2025-04-24 10:00 | 2025-05-02 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 749s 704 (749s Flyingshot Lake) | 2025-04-24 11:01 | 2025-04-24 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 749s 705 (749s Flyingshot Lake) | 2025-04-24 13:01 | 2025-04-24 15:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 805s J2404 (EP 805s Jasper) | 2025-04-25 07:00 | 2025-05-10 17:00 | N | Y |  | Circuit Breaker |  | parts arrival | 240 kV, Contingency Requires Mitigation
ENMAX | 162.1TR (SS-162), 138kV North Bus (SS-162), 162B138-RB94 (SS-162), 162B138-RB86 (SS-162), 162B138-RB80 (SS-162), 162MD138-162.1TR (SS-162), 162.2TR (SS-162) | 2025-04-25 08:00 | 2025-04-26 18:00 | N | Y |  | Transformer, Bus, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Impacts RAS, Overload, Pre-Condition
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2025-04-25 08:00 | 2025-04-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2075s ACF24 (2075s Newell) | 2025-04-25 09:00 | 2025-04-25 17:30 | N | Y |  | Shunts |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 20s T5 (20s Ghost), 20s 8 (20s Ghost) | 2025-04-26 07:00 | 2025-04-26 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 39.82L (SS-39 - SS-162), 162B138-RB82 (SS-162), 162B138-RB83 (SS-162), 39B138-39.82 (SS-39), 162MD138-39.82 (SS-162) | 2025-04-26 18:01 | 2025-04-28 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 330P GT6 (330p Genesee), 330p 12GT6D (330p Genesee) | 2025-04-27 07:00 | 2025-05-09 17:00 | N | Y |  | Transformer, Switch |  |  | 500 kV, Pre-Condition
ATCO | 7L86 (822s Wolf Lake - 1200s Foster Creek), 822s 703 (822s Wolf Lake) | 2025-04-27 07:00 | 2025-04-30 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12.2TR (SS-12), 12B138-833L (SS-12), 12MD138-12.2TR (SS-12) | 2025-04-27 08:00 | 2025-04-29 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft) | 2025-04-28 07:00 | 2025-04-30 17:00 | N | N |  | Line |  |  | For Information Only
EPCOR | 72PM25 (Poundmaker - Meadowlark), T4 (Poundmaker), PM2403 (Poundmaker), PM2402 (Poundmaker), PM721 (Poundmaker), M726 (Meadowlark), PMAB4 (Poundmaker) | 2025-04-28 07:00 | 2025-05-02 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 20.82L (SS-20 - SS-21), 20B138-20.82 (SS-20), 21B138-20.82 (SS-21) | 2025-04-28 08:00 | 2025-04-28 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MHS-5 MH69-T51 (MH69s5 NE Crescent Height), MHS-5 MH69-505 (MHS-5 NE Crescent Heights) | 2025-04-28 08:00 | 2025-05-02 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 2029s 500kV Bus 1200BS1 (2029s Heathfield), 2029s 1201 (2029s Heathfield), 2029s 1204 (2029s Heathfield), 2029s 1207 (2029s Heathfield), 2029s 1214 (2029s Heathfield), 2029s 1201A (2029s Heathfield), 2029s 1204A (2029s Heathfield), 2029s 1207A (2029s Heathfield), 2029s 1213A (2029s Heathfield), 2029s 1214A (2029s Heathfield) | 2025-04-28 08:00 | 2025-05-02 17:30 | N | Y |  | Bus, Circuit Breaker, Switch |  |  | 500 kV, For Information Only
BCH | T4 (BCH Natal) | 2025-04-28 09:00 | 2025-05-09 17:00 | N | Y |  | Transformer |  |  | 240 kV
ATCO | 2075s 902T (2075s Newell), 2075s ACF21 (2075s Newell), 2075S 930 (2075s Newell) | 2025-04-28 09:00 | 2025-05-02 17:30 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L23 (796s Nipisi - 7L23 tap), 7L23 (732s Mitsue - 7L23 tap), 796s 702 (796s Nipisi), 858S 701TD (858s Narrows Creek) | 2025-04-28 09:00 | 2025-04-29 14:30 | N | N |  | Line, Circuit Breaker, Switch |  | Line returned to service early. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station), 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 814s B2401 (814s Bellamy), 814s B2402 (814s Bellamy), 814s BDS19 (814s Bellamy) | 2025-04-28 09:30 | 2025-04-30 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2025-04-28 09:30 | 2025-04-30 17:00 | N | Y |  | Line |  |  | For Information Only
ATCO | 800s 701T (800s Friedenstal), 800s 711 (800s Friedenstal) | 2025-04-28 10:00 | 2025-05-05 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 800s 601 (800s Friedenstal) | 2025-04-28 10:00 | 2025-05-12 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 945s T1 (945s Sunshine Village), 945s 32 (945s Sunshine Village), 945s 33 (945s Sunshine Village) | 2025-04-28 10:30 | 2025-04-29 16:30 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 286s T1 (286s Yasa) | 2025-04-28 13:00 | 2025-05-05 11:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 478s 680 (478s Tucuman), 680L (478s Tucuman - 574s Nilrem) | 2025-04-28 13:30 | 2025-04-29 17:30 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek), 20s 859E (20s Ghost), AML 793s 859W (AML 793s Horse Creek) | 2025-04-29 07:00 | 2025-04-29 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 20.82L (SS-20 - SS-21), 21B138-20.82 (SS-21), 20B138-20.82 (SS-20) | 2025-04-29 08:00 | 2025-04-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34), 34B69-16.60 (SS-34), 16B69-16.60 (SS-16) | 2025-04-29 08:00 | 2025-04-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon), 353s 552 (353s Plamondon), 157s 728W (157s Lac La Biche) | 2025-04-29 08:00 | 2025-04-29 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
REDDEER | 194s T1 (194s South Red Deer), 194s T2 (194s South Red Deer) | 2025-04-29 08:00 | 2025-05-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162.3TR (SS-162), 162B138-RB86 (SS-162), 162B138-RB85 (SS-162), 162MD138-162.3TR (SS-162) | 2025-04-29 08:00 | 2025-05-01 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX, ALTALINK | 833L (SS-2 - SS-12) | 2025-04-29 09:00 | 2025-04-29 13:00 | N | Y |  | Line |  |  | Pre-Condition, Affects Cranking Path
ATCO, IMPERIALOIL | 7L95 (715s Leming Lake - 889s Mahkeses), 7L66 (715s Leming Lake - 717s Ethel Lake), 715s 703T (715s Leming Lake), 715s 703 (715s Leming Lake), 715s 704 (715s Leming Lake), 715s 705 (715s Leming Lake), 717s 702 (717s Ethel Lake), 889s 5CB-M1 (889s Mahkeses), 889s 5DS-M1 (889s Mahkeses) | 2025-04-29 09:00 | 2025-05-08 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 728L (353s Plamondon - 405s Waupisoo), 353s 452 (353s Plamondon), 405s 728 (405s Waupisoo) | 2025-04-29 12:31 | 2025-04-29 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe), 20s 56 (20s Ghost), 245s 56E (245s Seebe) | 2025-04-30 07:00 | 2025-04-30 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 190L (17s Benalto - 320p Keephills), 320p 552 (320p Keephills), 320p 652 (320p Keephills) | 2025-04-30 08:00 | 2025-04-30 14:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 679L (478s Tucuman - 574s Nilrem), 478s 679 (478s Tucuman) | 2025-04-30 08:00 | 2025-04-30 13:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12), 12B138-832L (SS-12), 10B138-832 (SS-10) | 2025-04-30 08:00 | 2025-05-02 15:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 21B138-21.80 (SS-21), 42s 21 (42s Sarcee) | 2025-04-30 08:00 | 2025-04-30 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29EDD-71 144kV Bus 29PP-46 (29EDD-71), 29EDD-71 752-4613 (29EDD-71), 29EDD-71 752-4621 (29EDD-71), 29EDD-71 752-4631 (29EDD-71), 29EDD-71 752-4641 (29EDD-71), 29EDD-71 752-4651 (29EDD-71) | 2025-04-30 08:00 | 2025-05-04 17:00 | N | N |  | Bus, Circuit Breaker |  | outage returned early. May 04, 2025 | Contingency Requires Mitigation, Restricts Generation
ATCO | 749s 703 (749s Flyingshot Lake) | 2025-04-30 09:30 | 2025-05-01 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-04-30 10:00 | 2025-04-30 14:00 | N | Y |  | Transformer |  |  | For Information Only, Restricts Generation
ALTALINK | 574s 952 (574s Nilrem) | 2025-04-30 13:00 | 2025-05-01 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2025-04-30 14:00 | 2025-05-23 14:00 | N | Y |  | Line |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2025-04-30 14:00 | 2025-05-23 14:00 | N | Y |  | Line |  |  | For Information Only
EPCOR | H723 (EP Hardisty) | 2025-05-01 07:00 | 2025-05-01 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | SS-54, 41.84L (SS-41 - SS-54), 54.81L (SS-54 - SS-65), 54.1TR (SS-54), 54B138-54.81 (SS-54), 54B138-41.84 (SS-54) | 2025-05-01 08:00 | 2025-05-01 18:00 | N | N |  | Station, Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 832L (SS-10 - SS-12) | 2025-05-01 08:00 | 2025-05-01 16:00 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2025-05-01 09:00 | 2025-05-02 17:00 | Y | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-05-01 10:00 | 2025-05-01 14:00 | N | Y |  | Transformer |  |  | For Information Only, Restricts Generation
EPCOR | H722 (EP Hardisty) | 2025-05-02 07:00 | 2025-05-02 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALBIAN, CNRL | 919s 906 (919s Hartley), 847s 901T (847s Muskeg River) | 2025-05-02 08:00 | 2025-05-09 08:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 15.60L (SS-15 - SS-21), 21B69-15.60 (SS-21), 15B69-15.60 (SS-15) | 2025-05-02 08:00 | 2025-05-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.82L (SS-3 - SS-8), 3.3TR (SS-3), 3B138-3.82 (SS-3), 3MD138-3.3TR (SS-3), SW83 (SS-3) | 2025-05-02 08:00 | 2025-05-02 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.81L (SS-11 - SS-13), 13.82L (SS-13 - SS-22), 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13.2TR (SS-13), 13B138-11.81 (SS-13), 13B138-13.82 (SS-13), 13MD138-13.2TR (SS-13), 13MD138-13.4TR (SS-13), 13B69-13.60 (SS-13) | 2025-05-03 08:00 | 2025-05-03 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2025-05-03 23:00 | 2025-05-07 17:00 | N | Y |  | Line |  | Returned to service early on May 7. | Affects Cranking Path
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain) | 2025-05-03 23:44 | 2025-05-06 11:00 | N | Y |  | Line |  |  | Affects Cranking Path
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.3TR (SS-31), 31.2TR (SS-31), 31MD138-31.2TR (SS-31), 31MD138-31.3TR (SS-31), 31B138-31.84 (SS-31), 31B138-24.81 (SS-31) | 2025-05-04 08:00 | 2025-05-04 12:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ATCOP | 2013s 501T (2013s Drummond), 2013s 502T (2013s Drummond) | 2025-05-04 08:00 | 2025-05-04 16:00 | N | N |  | Transformer |  |  | Restricts Generation
ENMAX | 26.2TR (SS-26) | 2025-05-04 08:30 | 2025-05-05 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.80L (SS-9 - SS-31), 31.1C (SS-31), 31.2TR (SS-31), 31.1TR (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31), 31B138-9.80 (SS-31) | 2025-05-04 12:01 | 2025-05-04 18:00 | N | N |  | Line, Shunts, Transformer, Switch, Circuit Breaker |  |  | Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2025-05-04 18:00 | 2025-05-05 18:08 | N | Y |  | Shunts |  | Outage returned to service.
ATCO | 7L70 (700s Bonnyville - 707s St. Paul) | 2025-05-04 20:16 | 2025-05-05 11:54 | N | N |  | Line
EPCOR | 72NW15 (Namao - Woodcroft), T2 (Woodcroft), W725 (Woodcroft), W723 (Woodcroft), N726 (Namao), WAB2 (Woodcroft) | 2025-05-05 07:00 | 2025-05-23 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | CV5 (EP 511s Victoria - 557s Castle Downs), EP 511s Victoria T5 (EP 511s Victoria), 557s CD2405 (557s Castle Downs), 557s CD2406 (557s Castle Downs), EP 511s V2401 (EP 511s Victoria), EP 511s V727 (EP 511s Victoria), EP 511s V728 (EP 511s Victoria), EP 511s VDS25 (EP 511s Victoria) | 2025-05-05 07:00 | 2025-05-17 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
CUB, ALTALINK | 672s 902T (672s Fengate Co-Generation), 430s 689 (430s Ursus) | 2025-05-05 07:00 | 2025-05-07 17:00 | N | Y |  | Transformer, Switch |  |  | 240 kV, Restricts Generation
ENMAX | 5B138-5BT12 (SS-5) | 2025-05-05 08:00 | 2025-05-05 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 240kV North Bus (SS-162), 162.1TR (SS-162), 162B240-RB131 (SS-162), 162B240-RB134 (SS-162), 162MD240-162.1TR (SS-162) | 2025-05-05 08:00 | 2025-05-09 16:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
ENMAX | 65B240-D131 (SS-65) | 2025-05-05 08:00 | 2025-05-06 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ICPCL, TRANSALTAGP | CHIN Chin Chute Generator Test | 2025-05-05 08:00 | 2025-05-10 14:00 | N | N |  | Unit
CMH | MHS-3 MH69-T31 (MHS-3 South Ridge), MHS-3 MH69-311 (MHS-3 Southridge) | 2025-05-05 08:00 | 2025-05-08 13:00 | N | N |  | Transformer, Circuit Breaker |  | Outage completed early | For Information Only
ALTALINK, Lethbridge | 725L (674s Bowron - 725BL tap), 674s T1 (674s Bowron), 674s 725W (674s Bowron), 674s 4 (674s Bowron) | 2025-05-05 08:00 | 2025-05-05 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 16.2TR (SS-16) | 2025-05-05 08:00 | 2025-05-10 16:00 | N | N |  | Transformer |  | no parts | For Information Only
ALTALINK | 74s C3 (74s Janet) | 2025-05-05 09:30 | 2025-05-05 17:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe), 20s 56 (20s Ghost), 245s 56E (245s Seebe) | 2025-05-05 09:30 | 2025-05-05 15:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 776s 601T (776s Richdale) | 2025-05-05 09:30 | 2025-05-09 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L90 (741s ATC Fox Creek - 7LA90 tap), 741s 701 (741s ATC Fox Creek) | 2025-05-05 11:00 | 2025-05-15 17:01 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALBIAN | 919s 906 (919s Hartley) | 2025-05-05 12:00 | 2025-05-09 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 320p T6 (320p Keephills), 320p PS2 (320p Keephills), 320p 2652 (320p Keephills), 320p 2752 (320p Keephills) | 2025-05-05 13:00 | 2025-05-08 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 500 kV, Pre-Condition
ATCO | 800s 702T (800s Friedenstal), 800s 712 (800s Friedenstal), 800s 602TD (800s Friedenstal), 800s 502TD (800s Friedenstal) | 2025-05-05 13:00 | 2025-05-12 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 286s T2 (286s Yasa) | 2025-05-05 16:00 | 2025-05-11 13:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 437s T2 (437s Baymag) | 2025-05-06 06:30 | 2025-05-07 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 437s T1 (437s Baymag) | 2025-05-06 06:30 | 2025-05-07 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake), 40s 858N (40s Wetaskiwin) | 2025-05-06 07:00 | 2025-05-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2025-05-06 07:00 | 2025-05-15 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T3 (Namao), N723 (Namao), N724 (Namao), 72CN10 (987s Clover Bar - Namao) | 2025-05-06 07:00 | 2025-05-08 13:00 | N | N |  | Transformer, Circuit Breaker, Line |  | Outage returned to service early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 83s T3 (83s Taber), 83s 138kV East Bus (83s Taber), 83s C1 (83s Taber), 507L (83s Taber - 257s Hull), 83s 64 (83s Taber), 83s 507 (83s Taber) | 2025-05-06 07:00 | 2025-05-07 07:00 | N | Y |  | Transformer, Bus, Shunts, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 804L (40s 803L tap - 86s 803L tap), 804L (40s Wetaskiwin - 40s 803L tap), 804L (86s Bigstone - 86s 803L tap), 86s 852 (86s Bigstone), 40s 804W (40s Wetaskiwin) | 2025-05-06 07:00 | 2025-05-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 299s T1 (299s Kingman), 299s 732N (299s Kingman) | 2025-05-06 07:00 | 2025-05-08 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 56L (20s Ghost - 245s Seebe), 245s 56E (245s Seebe), 20s 56 (20s Ghost) | 2025-05-06 07:30 | 2025-05-06 13:30 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29PL6-7 (30EDD-1 - 29EDD-5), 29PL6-4 (29EDD-1 Millennium - 30EDD-1), 30EDD-1 623T (30EDD-1), 30EDD-1 626T (30EDD-1), 30EDD-1 621T (30EDD-1), 30EDD-1 PSD-621-LOAD (30EDD-1), 30EDD-1 621 (30EDD-1), 30EDD-1 622 (30EDD-1), 30EDD-1 623 (30EDD-1), 30EDD-1 624 (30EDD-1), 30EDD-1 629 (30EDD-1), 30EDD-1 630 (30EDD-1), SPL6-7 (29EDD-5), 30EDD-1 622TD (30EDD-1), 30EDD-1 29PL6-4D1 (30EDD-1) | 2025-05-06 08:00 | 2025-05-16 20:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX | 11B138-BT5 (SS-11) | 2025-05-06 08:00 | 2025-05-06 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 72PM25 (Poundmaker - Meadowlark) | 2025-05-06 12:39 | 2025-05-10 18:00 | N | N |  | Line
ALTALINK | 58L (32s Barrier - 245s Seebe), 245s 58X (245s Seebe) | 2025-05-06 13:31 | 2025-05-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 808L (171s Redwater - 808AL tap) | 2025-05-06 15:36 | 2025-05-13 12:43 | N | N |  | Line |  | Returned early
EPCOR | 330p 12GT6D (330p Genesee), 330p 1210 (330p Genesee), 330p 1211 (330p Genesee) | 2025-05-07 07:00 | 2025-05-09 17:00 | N | Y |  | Switch, Circuit Breaker |  |  | 500 kV, Pre-Condition
ALTALINK | 185s 138kV Bus 2 (185s Bretville), 185s T2 (185s Bretville), 185s 452 (185s Bretville), 185s 252 (185s Bretville) | 2025-05-07 07:00 | 2025-05-08 18:00 | N | N |  | Bus, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 172L (83s Taber - 172EL tap), 610L (83s Taber - 336s Fincastle), 83s C2 (83s Taber), 83s T1 (83s Taber), 83s 65 (83s Taber), 83s 67 (83s Taber), 83s 138kV West Bus (83s Taber), 83s 172W (83s Taber), 83s 610 (83s Taber) | 2025-05-07 07:00 | 2025-05-07 17:00 | N | Y |  | Line, Shunts, Transformer, Circuit Breaker, Bus |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 754L (245s Seebe - 742L tap), 245s 754W (245s Seebe) | 2025-05-07 07:30 | 2025-05-07 13:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 23B138-23.80 (SS-23), 74s 23.80W (74s Janet) | 2025-05-07 08:00 | 2025-05-07 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 930s SVC (930s Arcenciel) | 2025-05-07 08:30 | 2025-05-08 10:40 | N | Y |  | Shunts |  | Outage returned to service early. | Pre-Condition
ATCO | 879s 702T (879s Scotford Upgrader), 879s 52-1B (879s Upgrader) | 2025-05-07 08:30 | 2025-05-16 17:00 | N | N |  | Transformer, Switch |  | Done early | Restricts Generation
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2025-05-07 13:30 | 2025-05-07 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 245s 3E (245s Seebe), 3L (245s Seebe - 3AL tap) | 2025-05-08 07:30 | 2025-05-08 13:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
Syncrude | 23 (Aurora), 24 (Aurora), 23B (Aurora), 24A (Aurora) | 2025-05-08 08:00 | 2025-05-08 18:00 | N | N |  | Circuit Breaker, Switch |  |  | For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10), 10B138-693 (SS-10) | 2025-05-08 08:00 | 2025-05-08 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
Syncrude | UE-1 1521 (UE-1 Syncrude Plant 30-2) | 2025-05-08 08:00 | 2025-05-09 16:00 | N | N |  | Circuit Breaker |  |  | Restricts Generation
ATCO | 7L95 (715s Leming Lake - 889s Mahkeses), 715s 704 (715s Leming Lake) | 2025-05-08 12:01 | 2025-05-13 10:00 | N | Y |  | Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 245s 87W (245s Seebe), 87L (2s Kananaskis - 245s Seebe) | 2025-05-08 13:31 | 2025-05-08 18:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.83L (SS-9 - SS-43), 43B138-9.83 (SS-43), 9B138-9.83 (SS-9) | 2025-05-09 08:00 | 2025-05-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13B69-13.60 (SS-13), 27B69-13.60 (SS-27) | 2025-05-09 08:00 | 2025-05-09 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
PANC, ALTALINK, NEXENI | PCES02L (391s Balzac - Balzac Power Station), 391s 25 (391s Balzac), 52-211 (Balzac Power Station), 89-213BP (Balzac Power Station) | 2025-05-09 08:00 | 2025-05-15 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Restricts Generation
ALTALINK | 799s T1 (799s Coleman), 799s T3 (799s Coleman) | 2025-05-09 10:00 | 2025-05-09 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 11.81L (SS-11 - SS-13), 13B138-11.81 (SS-13), 11B138-11.81 (SS-11) | 2025-05-09 12:01 | 2025-05-09 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7) | 2025-05-10 08:00 | 2025-05-10 12:00 | N | Y |  | Line |  |  | For Information Only
ENMAX | 5.9TR (SS-5) | 2025-05-10 08:00 | 2025-05-10 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7), 7.2TR (SS-7), 7B138-7.82 (SS-7), 7B138-7BT3 (SS-7), 7MD138-7.2TR (SS-7) | 2025-05-10 08:00 | 2025-05-10 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2025-05-10 09:30 | 2025-05-10 12:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 7.84L (SS-7 - SS-36), 7.1TR (SS-7), 7B138-7.84 (SS-7), 7B138-7BT3 (SS-7), 7MD138-7.1TR (SS-7) | 2025-05-10 12:00 | 2025-05-10 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.81L (SS-26 - SS-32), 26.1TR (SS-26), 26B138-26BT3 (SS-26), 26B138-26.81 (SS-26), 26MD138-26.1TR (SS-26) | 2025-05-11 08:00 | 2025-05-11 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALBIAN, CNRL | 919s 908 (919s Hartley), 847s 902T (847s Muskeg River) | 2025-05-11 08:00 | 2025-05-11 14:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Restricts Generation
ENMAX | 26.83L (SS-26 - SS-65), 26.2TR (SS-26), 26B138-26BT3 (SS-26), 26B138-26.83 (SS-26), 26MD138-26.2TR (SS-26) | 2025-05-11 12:01 | 2025-05-11 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 12GT7D (330p Genesee), 330p 1214 (330p Genesee), 330p 1215 (330p Genesee) | 2025-05-12 07:00 | 2025-05-16 17:00 | N | Y |  | Switch, Circuit Breaker |  | Outage returned early | 500 kV, Pre-Condition
EPCOR | 805s T4 (805s Jasper), EP 805s J2405 (EP 805s Jasper), EP 805s J2406 (EP 805s Jasper), EP 805s JAB4 (EP 805s Jasper) | 2025-05-12 07:00 | 2025-05-17 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft), N726 (Namao), W723 (Woodcroft) | 2025-05-12 07:00 | 2025-05-16 11:00 | N | N |  | Line, Circuit Breaker |  | ended early | Pre-Condition
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 1207 (330p Genesee), 330p 1204 (330p Genesee), 330p 1201 (330p Genesee), 330p 1210 (330p Genesee), 330p 1214 (330p Genesee), 330p 805 (330p Genesee), 330p 12TC1D (330p Genesee) | 2025-05-12 07:00 | 2025-05-16 11:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  | Ended early | 500 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), T1 (EP Hardisty), H725 (EP Hardisty), H722 (EP Hardisty), HAB1 (EP Hardisty), 987s CH724 (987s Clover Bar) | 2025-05-12 07:00 | 2025-05-12 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.1TR (SS-9) | 2025-05-12 08:00 | 2025-05-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 26.81L (SS-26 - SS-32), 32.2TR (SS-32), 32.1TR (SS-32), 32B138-32BT5 (SS-32), 32B138-32.83 (SS-32), 32MD138-32.1TR (SS-32), 32MD138-32.2TR (SS-32), 32B138-26.81 (SS-32), SW83 (SS-32), SW89 (SS-32) | 2025-05-12 08:00 | 2025-05-12 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 13.4TR (SS-13), 13B69-13.60 (SS-13), 27B69-13.60 (SS-27) | 2025-05-12 08:00 | 2025-05-14 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-6L (MHS-1 CMH Power Plant - MHS-9 South Saskatchewan), MHS-9 MH138-T11 (MHS9 Power Plant), MHS-9 MH138-902 (MHS-9 South Saskatchewan) | 2025-05-12 08:00 | 2025-05-18 07:00 | N | N |  | Line, Transformer, Circuit Breaker |  | Outage extended | Overload, Pre-Condition, Restricts Generation
SUNCOR | 635EDD-1000 635-752-131 (635EDD-1000) | 2025-05-12 08:00 | 2025-05-12 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 3.84L (SS-3 - SS-13), 3B138-3.84 (SS-3), 13B138-3.84 (SS-13) | 2025-05-12 08:00 | 2025-06-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | 12 (Aurora) | 2025-05-12 08:00 | 2025-05-22 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-05-12 09:00 | 2025-05-15 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 757s 701T (757s Battle River), 757s 606 (757s Battle River), 757s 701 (757s Battle River) | 2025-05-12 09:30 | 2025-05-16 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L89 (700s Bonnyville - 721s La Corey), 700s 703 (700s Bonnyville) | 2025-05-12 10:00 | 2025-05-15 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s T3 (987s Clover Bar), 987s T1 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s C2407 (987s Clover Bar), 987s CDS25 (987s Cloverbar) | 2025-05-13 07:00 | 2025-05-27 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 809L (320p Keephills - 510s Sunnybrook), 834L (320p Keephills - 384s Keystone), 400L (320p Keephills - 320p Keephills), 401L (320p Keephills - 320p Keephills), 767L (320p Keephills - 767CL tap), 320p T1 (320p Keephills), 320p T4 (320p Keephills), 320p 138kV Bus (320p Keephills), 320p 809X (320p Keephills), 320p 834X (320p Keephills), 320p 767N (320p Keephills), 320p 400 (320p Keephills), 320p 401 (320p Keephills), 320p 91 (320p Keephills), 320p 105 (320p Keephills) | 2025-05-13 07:00 | 2025-05-15 17:00 | N | Y |  | Line, Transformer, Bus, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 47B138-BT3 (SS-47), 47B138-771 (SS-47), 47.2TR (SS-47) | 2025-05-13 08:00 | 2025-05-13 16:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
BCH | T3 (BCH Natal) | 2025-05-13 08:00 | 2025-05-30 09:00 | N | Y |  | Transformer |  |  | 240 kV
ALTALINK | 163s T2 (163s Amoco Empress) | 2025-05-13 08:00 | 2025-05-22 17:00 | N | Y |  | Transformer |  |  | 240 kV
ENMAX | 32.3TR (SS-32) | 2025-05-13 08:00 | 2025-05-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 89s Ellerslie 240kV Bus 1, 1140L (89s Ellerslie - 289s Saunders Lake), 89s T1 (89s Ellerslie), 89s 1352 (89s Ellerslie), 89s 952 (89s Ellerslie), 89s 1789 (89s Ellerslie), 89s 652 (89s Ellerslie), 89s 252 (89s Ellerslie), 89s 1140 (89s Ellerslie) | 2025-05-13 08:00 | 2025-05-13 16:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO, FMGW | 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s 952-600001 (1024s Granlea), 1024s PS-6005 (1024s Granlea), 1024s PS-6006 (1024s Granlea), 1024s PS-6007 (1024s Granlea), 1024s PS-6008 (1024s Granlea) | 2025-05-13 08:30 | 2025-05-16 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 1D24 (BCH Natal), 799s 786W (799s Coleman) | 2025-05-13 12:17 | 2025-05-15 15:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 799s T1 (799s Coleman), 799s T3 (799s Coleman) | 2025-05-14 00:01 | 2025-05-14 04:00 | N | N |  | Transformer |  |  | Pre-Condition
ALTALINK | 799s T3 (799s Coleman) | 2025-05-14 04:01 | 2025-07-14 07:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 425L (194s South Red Deer - 217s North Red Deer), 217s 425 (217s North Red Deer), 194s 425 (194s South Red deer) | 2025-05-14 08:00 | 2025-05-15 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 41.84L (SS-41 - SS-54), 41B138-41.84 (SS-41), 54B138-41.84 (SS-54) | 2025-05-14 08:00 | 2025-05-15 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47.1TR (SS-47), 47B138-BT3 (SS-47), 47B138-771/1 (SS-47) | 2025-05-14 08:00 | 2025-05-14 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | 2L112 (BPA Boundary - BCH Nelway) | 2025-05-14 09:00 | 2025-05-14 17:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ATCO | 790s 703T (790s Poplar Hill), 790s 704 (790s Poplar Hill) | 2025-05-14 09:30 | 2025-05-16 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2025-05-14 23:00 | 2025-05-15 03:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 62s T2 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant) | 2025-05-15 03:00 | 2025-05-15 07:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
PGCP | ETL1 Ethel Lake DER Generator Test | 2025-05-15 08:00 | 2025-07-20 16:00 | N | N |  | Unit
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20B138-1.81 (SS-20), 20MD138-20.1TR (SS-20) | 2025-05-15 08:00 | 2025-05-15 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.1TR (SS-16) | 2025-05-15 08:00 | 2025-05-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28.2TR (SS-28), 28B138-28.80 (SS-28), 28MD138-28.2TR (SS-28) | 2025-05-16 08:00 | 2025-05-16 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 54.81L (SS-54 - SS-65), 54B138-54.81 (SS-54) | 2025-05-16 08:00 | 2025-05-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L03 (757s Battle River - 6L17 tap), 757s 603 (757s Battle River) | 2025-05-16 08:00 | 2025-05-18 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L51 (ATC 793s West Peace River - 927s Buchanan Creek), ATC 793s 701 (ATC 793s West Peace River) | 2025-05-16 09:00 | 2025-05-16 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ATCO | 9L101 (957s McClelland - 2005s Secord), 957s 901 (957s McClelland), 957s 902 (957s McClelland) | 2025-05-16 11:00 | 2025-05-16 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28), 28MD138-28.1TR (SS-28) | 2025-05-16 12:01 | 2025-05-16 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, BCH | 786L (799s Coleman - BCH Natal), 1D24 (BCH Natal), 799s 786W (799s Coleman) | 2025-05-16 17:00 | 2025-05-16 19:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 29PL6-7 (30EDD-1 - 29EDD-5), 29PL6-1 (30EDD-1 - 29EDD-55), 30EDD-1 621T (30EDD-1), 30EDD-1 626T (30EDD-1), 30EDD-1 622 (30EDD-1), 30EDD-1 621 (30EDD-1), 30EDD-1 628 (30EDD-1), 30EDD-1 629 (30EDD-1), 30EDD-1 630 (30EDD-1), SPL6-7 (29EDD-5), 30EDD-1 621TD (30EDD-1), 30EDD-1 626TD (30EDD-1), 30EDD-1 625TD (30EDD-1), 30EDD-1 29PL6-1CS (30EDD-1) | 2025-05-16 20:01 | 2025-05-28 20:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12B138-833L (SS-12), 12.2TR (SS-12), SW83 (SS-12), 12MD138-12.2TR (SS-12) | 2025-05-17 08:00 | 2025-05-17 12:00 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 12.1TR (SS-12), 12B138-832L (SS-12), SW84 (SS-12), 12MD138-12.1TR (SS-12) | 2025-05-17 12:01 | 2025-05-17 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 816s P2402 (816s Petrolia), 816s P2403 (816s Petrolia), 816s PDS11 (816s Petrolia) | 2025-05-18 07:00 | 2025-05-25 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 693L (42s Sarcee - SS-10), 10.2TR (SS-10), 10B138-693 (SS-10), SW84 (SS-10), 10MD138-10.2TR (SS-10), 42s 693 (42s Sarcee) | 2025-05-18 08:00 | 2025-05-18 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10.1TR (SS-10), 10B138-832 (SS-10), SW83 (SS-10), 10MD138-10.1TR (SS-10) | 2025-05-18 12:01 | 2025-05-18 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 6.80L (SS-6 - SS-35), 6B138-6.80 (SS-6), 6.4TR (SS-6), 6MD138-6.4TR (SS-6) | 2025-05-19 08:00 | 2025-05-19 12:00 | N | N |  | Line, Circuit Breaker, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 749s 706 (749s Flyingshot Lake) | 2025-05-19 09:30 | 2025-05-20 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6), 6.1TR (SS-6) | 2025-05-19 12:00 | 2025-05-19 18:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | T3 (Rossdale), R723 (Rossdale), R724 (Rossdale) | 2025-05-20 07:00 | 2025-06-13 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s CK725 (987s Clover Bar), K724 (Kennedale) | 2025-05-20 07:00 | 2025-05-21 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 330p 1202 (330p Genesee) | 2025-05-20 07:00 | 2025-05-20 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ALTALINK, ENEL | 205s T1 (205s Castle Rock Ridge), 205s 52M1 (205s Castle Rock Ridge), 205s 89T1 (205s Castle Rock Ridge) | 2025-05-20 07:30 | 2025-05-22 16:30 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
CMH | MHS2 MH69-T22 (MHS-2 North Industrial), MHS-2 MH69-215 (MHS-2 North Industrial) | 2025-05-20 08:00 | 2025-05-24 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 162.4TR (SS-162), 162B138-RB92 (SS-162), 162B138-RB94 (SS-162), 162MD138-162.4TR (SS-162) | 2025-05-20 08:00 | 2025-05-20 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 6.82L (SS-6 - SS-41), 41B138-6.82 (SS-41), 6B138-6.82 (SS-6) | 2025-05-20 08:00 | 2025-05-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 40.2TR (SS-40) | 2025-05-20 08:00 | 2025-05-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2025-05-20 09:00 | 2025-05-22 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
BCH | T3 (BCH Natal), 2CB1 (BCH A. A. Lambert) | 2025-05-20 09:00 | 2025-05-30 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 199L (347s AML Fox Creek - 741s ATC Fox Creek) | 2025-05-20 11:00 | 2025-05-26 17:00 | N | Y |  | Line |  |  | For Information Only
ATCO | 7L199 (347s AML Fox Creek - 741s ATC Fox Creek), 741s 702 (741s ATC Fox Creek) | 2025-05-20 11:00 | 2025-05-26 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 330p 1205 (330p Genesee) | 2025-05-21 07:00 | 2025-05-22 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
CENOVUS | 539s PCB-9203 (539s Sunday Creek) | 2025-05-21 08:00 | 2025-05-22 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 65s T2 (65s High River) | 2025-05-21 08:00 | 2025-05-21 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.1TR (SS-31) | 2025-05-21 09:00 | 2025-05-23 14:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29EDD-1 T2 (29EDD-1 Millennium) | 2025-05-21 09:00 | 2025-05-30 20:00 | N | Y |  | Transformer |  | Was cancelled and rescheduled according to Suncor. Outage extended by Suncor, trouble shooting required. May 28, 2025. | 240 kV, Contingency Requires Mitigation
ATCO, CNRL | 847s 902 (847s Muskeg River) | 2025-05-21 09:00 | 2025-05-21 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
ATCO | 789s 706C (789s Keg River) | 2025-05-21 11:00 | 2025-05-23 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO, CNRL | 847s 903 (847s Muskeg River) | 2025-05-21 13:00 | 2025-05-21 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | 72CK13 (987s Clover Bar - Kennedale), 987s CK726 (987s Clover Bar), K721 (Kennedale), KDS1 (Kennedale) | 2025-05-22 07:00 | 2025-05-23 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 736L (38s East Edmonton - 293s Bernese), 293s T1 (293s Bernese), 293s T2 (293s Bernese), 38s 736E (38s East Edmonton), 293s 152 (293s Bernese), 293s 252 (293s Bernese) | 2025-05-22 07:00 | 2025-05-22 19:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 38.3TR (SS-38) | 2025-05-22 08:00 | 2025-05-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26B138-26BT3 (SS-26) | 2025-05-22 08:00 | 2025-05-22 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 331s 422 (331s Ponoka), 422L (288s Wolf Creek - 331s Ponoka) | 2025-05-22 08:00 | 2025-05-22 17:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, CNRL | 847s 904 (847s Muskeg River) | 2025-05-22 09:00 | 2025-05-22 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 899s T3 (899s Edgerton) | 2025-05-22 11:00 | 2025-05-22 16:30 | N | N |  | Transformer |  |  | For Information Only
ATCO, CNRL | 847s 901 (847s Muskeg River) | 2025-05-22 13:00 | 2025-05-22 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2025-05-22 16:00 | 2025-05-26 17:00 | N | Y |  | Line
EPCOR | 330p 1208 (330p Genesee) | 2025-05-23 07:00 | 2025-05-24 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43) | 2025-05-23 08:00 | 2025-05-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, TRANSALTA | 33s 138kV Bus (33s Spray), 113L (20s Ghost - 33s Spray), 76L (33s Spray - 115s Mount Allan), 84L (33s Spray - 35s Rundle Plant), 33s T1 (33s Spray), 33s T2 (33s Spray), 33s 113 (33s Spray), 33s 76 (33s Spray), 33s 84 (33s Spray), 20s 113 (20s Ghost), 33s 1 (33s Spray), 33s 2 (33s Spray) | 2025-05-23 11:00 | 2025-05-23 17:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ENMAX, ALTALINK | 1109L (SS-25 - SS-65), 25B240-D136 (SS-25), 25B240-D139 (SS-25), 25B240-D133 (SS-25), 25B240-D141 (SS-25), 25B240-D142 (SS-25), 25MD240-1109 (SS-25) | 2025-05-23 14:00 | 2025-06-02 10:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 3.84L (SS-3 - SS-13), 3.4TR (SS-3), SW84 (SS-3), 3MD138-3.4TR (SS-3) | 2025-05-24 08:00 | 2025-05-24 18:00 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
EPCOR | 987s GT2 (987s Clover Bar) | 2025-05-25 07:00 | 2025-08-01 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 40.81L (SS-40 - SS-41), 41.84L (SS-41 - SS-54), 41.1TR (SS-41), 41B138-41.84 (SS-41), 41B138-41BT3 (SS-41), 41B138-40.81 (SS-41), SW84 (SS-41), 41MD138-41.1TR (SS-41) | 2025-05-25 08:00 | 2025-05-25 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 635-752-631 (635EDD-1001) | 2025-05-25 08:00 | 2025-05-25 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
NOVACORP | 330s 330-PTR-04 (330s Nova Corp) | 2025-05-25 09:00 | 2025-06-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 6L97 (735s Swan River - 739s Edith Lake) | 2025-05-25 14:25 | 2025-06-13 15:00 | N | N |  | Line
EPCOR | 987s GT3 (987s Clover Bar) | 2025-05-26 02:00 | 2025-05-26 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 122s T1 (122s Alberta Newsprint) | 2025-05-26 07:00 | 2025-05-29 17:30 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2025-05-26 07:00 | 2025-05-29 17:30 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), 987s CH724 (987s Clover Bar), H725 (EP Hardisty) | 2025-05-26 07:00 | 2025-05-27 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72JM18 (EP 805s Jasper - Meadowlark), 72JW19 (EP 805s Jasper - Woodcroft), 805s T1 (805s Jasper), 805s C1 (805s Jasper), EP 805s J2401 (EP 805s Jasper), EP 805s J2403 (EP 805s Jasper), EP 805s J2408 (EP 805s Jasper), EP 805s J724 (EP 805s Jasper), EP 805s J722 (EP 805s Jasper), M721 (Meadowlark), W721 (Woodcroft), EP 805s JAB1 (EP 805s Jasper), EP 805s JAB5 (EP 805s Jasper), EP 805s JAB2 (EP 805s Jasper) | 2025-05-26 07:00 | 2025-06-06 17:00 | N | Y |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
CMH | MH-9L (MHS-2 North Industrial - MHS-10 Box Springs), MH-10L (MHS-10 Box Springs - MHS-8 Burnside), MHS10 MH138-T101 (MHS-10 Box Springs), MHS10 MH138-T102 (MHS-10 Box Springs), MHS-8 MH138-T81 (MHS-8 Burnside), MHS2 MH138-T23 (MHS-2 North Industrial), MHS-8 MH138-803 (MHS-8 Burnside), MHS-2 MH138-218 (MHS-2 North Industrial) | 2025-05-26 08:00 | 2025-05-26 15:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.2TR (SS-33) | 2025-05-26 08:00 | 2025-05-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.10TR (SS-5) | 2025-05-26 08:00 | 2025-05-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 37.82L (74s Janet - SS-37), 37.2TR (SS-37), 74s 37.82W (74s Janet), 37B138-37.82 (SS-37) | 2025-05-26 08:00 | 2025-05-29 15:05 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 31B138-31.84 (SS-31), 32B138-31.84 (SS-32) | 2025-05-26 08:00 | 2025-05-27 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ENMAX | 12.1TR (SS-12) | 2025-05-26 08:00 | 2025-05-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2029s T11 (2029s Heathfield), 2075s T11 (2075s Newell) | 2025-05-26 09:00 | 2025-06-06 08:48 | N | Y |  | Line, Transformer | Note For OC: Check the availability of the substation ( 2075s Newell) for the use of SVS. Check if the SVS can be operated under reactive control mode. |  | 500 kV, Overload, Pre-Condition, Restricts Generation
ATCO | 2075s 916 (2075s Newell), 2075s 917 (2075s Newell), 2075s 916B (2075s Newell), 2075s 917A (2075s Newell) | 2025-05-26 09:00 | 2025-06-06 08:48 | N | Y |  | Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-05-26 09:00 | 2025-05-29 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2029s 1205 (2029s Heathfield), 2029s 1206 (2029s Heathfield), 2029s 1201 (2029s Heathfield), 2029s 1201A (2029s Heathfield), 2029s 1201B (2029s Heathfield), 2029s 1202 (2029s Heathfield), 2029s 1202A (2029s Heathfield), 2029s 1202B (2029s Heathfield), 2029s 1203 (2029s Heathfield), 2029s 1203A (2029s Heathfield), 2029s 1203B (2029s Heathfield), 2029s 1204 (2029s Heathfield), 2029s 1204A (2029s Heathfield), 2029s 1204B (2029s Heathfield), 2029s 1205A (2029s Heathfield), 2029s 1205B (2029s Heathfield), 2029s 1206A (2029s Heathfield), 2029s 1206B (2029s Heathfield), 2029s 1207 (2029s Heathfield), 2029s 1207A (2029s Heathfield), 2029s 1207B (2029s Heathfield), 2029s 1208 (2029s Heathfield), 2029s 1208A (2029s Heathfield), 2029s 1208B (2029s Heathfield), 2029s 1209 (2029s Heathfield), 2029s 1209A (2029s Heathfield), 2029s 1209B (2029s Heathfield), 2029s 1213A (2029s Heathfield), 2029s 1214 (2029s Heathfield), 2029s 1214A (2029s Heathfield), 2029s 1214B (2029s Heathfield), 2029s 1215 (2029s Heathfield), 2029s 1215A (2029s Heathfield), 2029s 1215B (2029s Heathfield), 2029s 1218A (2029s Heathfield), 2029s 1218 (2029s Heathfield), 2029s 1219 (2029s Heathfield), 2029s 1219A (2029s Heathfield), 2029s 1220 (2029s Heathfield), 2029s 1220A (2029s Heathfield), 2029s 1221 (2029s Heathfield), 2029s 1221A (2029s Heathfield), 2029s 1222 (2029s Heathfield), 2029s 1222A (2029s Heathfield), 2029s 1223 (2029s Heathfield), 2029s 1223A (2029s Heathfield), 2029s 1224 (2029s Heathfield), 2029s 1224A (2029s Heathfield), 2029s 1200SST1D1 (2029s Heathfield), 2029s 1200SST2D1 (2029s Heathfield), 2029s ACF1D1 (2029s Heathfield), 2029s ACF2D1 (2029s Heathfield) | 2025-05-26 09:00 | 2025-06-04 17:30 | N | Y |  | Circuit Breaker, Switch |  |  | 500 kV, For Information Only
ALTALINK | 102s T4 (102s Langdon), 102s SVC (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon) | 2025-05-26 11:30 | 2025-05-29 17:30 | N | Y |  | Transformer, Shunts, Circuit Breaker | Note for OC: BC wants to be aware of this outage and prefers to see in the interconnection report. OC to select the outage category as 'Interconnection' and select Interconnection as 'AB-BC', so that this outage shows up on the Interconnection report. |  | 240 kV, Pre-Condition
ATCO | 883s 701T (883s Gregoire), 883S 701TCS (883s Gregoire) | 2025-05-26 12:00 | 2025-05-29 17:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 83s T3 (83s Taber), 83s 64 (83s Taber) | 2025-05-26 12:30 | 2025-05-30 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 310p 452 (310p Sundance) | 2025-05-26 13:30 | 2025-05-29 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 967L (138s Windy Flats - 370s North Lethbridge), 138s 1152 (138s Windy Flats), 138s 1252 (138s Windy Flats), 370s 967 (370s North Lethbridge) | 2025-05-27 07:30 | 2025-05-27 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 150L (20s Ghost - 150AL tap), 20s 150 (20s Ghost) | 2025-05-27 07:30 | 2025-05-27 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2025-05-27 16:10 | 2025-05-28 18:35 | N | Y |  | Shunts
ATCO | 6L96 (735s Swan River - 743s Sarah Lake) | 2025-05-27 17:06 | 2025-06-17 16:18 | N | N |  | Line |  | Returned early. | Over/Under Voltage, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-05-27 23:00 | 2025-05-29 07:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO | 710s 707C (710s Vermilion) | 2025-05-28 | 2025-06-12 13:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-05-28 07:00 | 2025-05-31 15:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR, ALTALINK | 908AL (52S East Industrial - 908L tap), 908L (89s Ellerslie - 908AL tap), 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial), 52s EDS2 (52s East Industrial) | 2025-05-28 07:00 | 2025-05-28 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss,Affects Cranking Path
ALTALINK | 968L (138s Windy Flats - 370s North Lethbridge), 138s 852 (138s Windy Flats), 138s 952 (138s Windy Flats), 370s 968 (370s North Lethbridge) | 2025-05-28 07:30 | 2025-05-28 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 418L (20s Ghost - 189L tap), 20s 452 (20s Ghost) | 2025-05-28 07:30 | 2025-05-28 16:30 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
ENMAX | 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27), 16B69-16.61 (SS-16) | 2025-05-28 08:00 | 2025-05-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 29EDD-71 144kV Bus 29PP-47 (29EDD-71), 29EDD-71 752-4654 (29EDD-71), 29EDD-71 752-4644 (29EDD-71), 29EDD-71 752-4634 (29EDD-71), 29EDD-71 752-4624 (29EDD-71), 29EDD-71 752-4614 (29EDD-71) | 2025-05-28 08:00 | 2025-06-02 18:00 | N | N |  | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
SUNCOR, ATCO | 635EDD-1000 144kV Bus 635PP-1001 (635EDD-1000), 635PL9-1001 (2005s Secord - 635EDD-1000), 635EDD-1000 635PT-1001 (635EDD-1000), 635EDD-1000 635-752-163 (635EDD-1000), 635EDD-1000 635-752-153 (635EDD-1000), 635EDD-1000 635-752-143 (635EDD-1000), 635EDD-1000 635-752-133 (635EDD-1000), 635EDD-1000 635-752-123 (635EDD-1000), 635EDD-1000 635-752-113 (635EDD-1000), 635EDD-1000 635-752-635PT-1001 (635EDD-1000), 635EDD-1000 635PS-9521 (635EDD-1000), 635EDD-1000 635PS-1003 (635EDD-1000), 2005s 1001D1 (2005s Secord) | 2025-05-28 08:00 | 2025-06-02 16:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
BHE Canada | 120s C1 (120s Picture Butte) | 2025-05-28 10:30 | 2025-05-28 17:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2025-05-29 07:00 | 2025-05-29 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
BHE Canada | 120s MATL PST (120s Picture Butte), 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte), 120s 1052 (120s Picture Butte), 120s 1152S (120s Picture Butte) | 2025-05-29 07:00 | 2025-05-29 17:30 | N | Y |  | Transformer, Shunts, Circuit Breaker, Switch | Note for OC: 120s MATL PST is not mapped to Margo. OC to create an override record or add MATL as an element (which is mapped to Margo, please ensure "Limits ATC" flag is selected for the import ATC value to be posted to Margo). |  | 240 kV, Pre-Condition
ALTALINK | 1116L (167s Ipiatik Lake - 170s Pike) | 2025-05-29 07:23 | 2025-06-04 18:00 | N | Y |  | Line |  | Back in service.
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 30EDD-1), 30EDD-1 622T (30EDD-1), 30EDD-1 624T (30EDD-1), 30EDD-1 628 (30EDD-1), 30EDD-1 627 (30EDD-1), 30EDD-1 626 (30EDD-1), 30EDD-1 625 (30EDD-1), 30EDD-1 622TD (30EDD-1), 30EDD-1 624TD (30EDD-1) | 2025-05-29 08:00 | 2025-06-13 20:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
EPCOR | 524s T1 (524s Owens Corning) | 2025-05-29 08:00 | 2025-05-29 10:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 186s T2 (186s Dry Creek) | 2025-05-29 08:00 | 2025-05-29 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 445L (170s Pike - 183s Underwood) | 2025-05-29 10:10 | 2025-06-02 11:52 | N | N |  | Line |  | Line back in service.
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2025-05-29 10:33 | 2025-06-04 09:34 | N | Y |  | Line |  | Line back in service.
ATCO | 6L57 (727s Kinuso - 735s Swan River) | 2025-05-29 16:25 | 2025-06-06 13:02 | N | N |  | Line |  | Line returned to service
ATCO | 7L94 (827s Cranberry Lake - 878s Kidney Lake) | 2025-05-29 16:49 | 2025-05-30 10:47 | N | N |  | Line
ATCO | 7L60 (780s Lubicon - 827s Cranberry Lake) | 2025-05-29 16:49 | 2025-05-30 12:50 | N | N |  | Line
BHE Canada | 120s C1 (120s Picture Butte) | 2025-05-29 17:31 | 2025-07-29 16:00 | N | Y |  | Shunts |  | Extended: Altalink operator thinks this will be completed Sept 30/25. completed 29 Jul 2025-GSR | 240 kV, Pre-Condition
ATCO | 7L23 (796s Nipisi - 7L23 tap) | 2025-05-29 18:09 | 2025-06-01 12:23 | N | N |  | Line |  | Line is back in service
ATCO | 7L133 (786s High Level - 828s Sulphur Point) | 2025-05-29 18:49 | 2025-06-02 16:00 | N | Y |  | Line
ALTALINK | 971L (154s Black Spruce - 762s Conklin) | 2025-05-29 19:52 | 2025-06-10 21:30 | N | Y |  | Line
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2025-05-31 07:00 | 2025-06-07 17:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 276s 25 (276s Prentiss) | 2025-05-31 07:30 | 2025-06-10 17:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.2TR (SS-14) | 2025-05-31 08:00 | 2025-05-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43.1TR (SS-43), 43B138-9.83 (SS-43) | 2025-06-01 08:00 | 2025-06-01 12:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33), 43.2TR (SS-43), 43B138-33.84 (SS-43) | 2025-06-01 12:00 | 2025-06-01 18:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L94 (827s Cranberry Lake - 878s Kidney Lake) | 2025-06-01 14:44 | 2025-06-30 17:00 | N | N |  | Line |  |  | Firm Load Loss, Pre-Condition
EPCOR | 816s P2401 (816s Petrolia), 816s P2402 (816s Petrolia), 816s T1 (816s Petrolia), 816s PAB1 (816s Petrolia) | 2025-06-02 07:00 | 2025-06-07 17:00 | N | Y |  | Circuit Breaker, Transformer, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
EPCOR | 557s T1 (557s Castle Downs) | 2025-06-02 07:00 | 2025-07-07 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | AML 511s 240kV ACF 1 Bus (511s Crossings), AML 511s T30 (AML 511s Crossings), AML 511s SVC Plus (AML 511s Crossings), AML 511s ACF11 (AML 511s Crossings), AML 511s ACF12 (AML 511s Crossings), AML 511s ACF13 (AML 511s Crossings), AML 511s 5352 (AML 511s Crossings), AML 511s 82 (AML 511s Crossings), AML 511s 81 (AML 511s Crossings), AML 511s 5252 (AML 511s Crossings), AML 511s 148 (AML 511s Crossings), AML 511s 152 (AML 511s Crossings), AML 511s 153 (AML 511s Crossings), AML 511s 154 (AML 511s Crossings), AML 511s 1152 (AML 511s Crossings) | 2025-06-02 07:30 | 2025-06-06 16:30 | N | Y |  | Bus, Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ATCO, CNRL | 859s 701T (859s Primrose), 859s 701TD (859s Primrose), 859s 704 (859s Primrose), 859s 701 (859s Primrose) | 2025-06-02 08:00 | 2025-06-07 08:00 | N | Y |  | Transformer, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2025-06-02 08:00 | 2025-06-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 928L (17s Benalto - 42s Sarcee) | 2025-06-02 08:00 | 2025-06-12 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ENMAX | 9.2TR (SS-9) | 2025-06-02 08:00 | 2025-06-07 08:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 37.81L (SS-37 - SS-38), 37.1TR (SS-37), 37MD138-37.1TR (SS-37), 37B138-37.81 (SS-37) | 2025-06-02 08:00 | 2025-06-13 16:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | AL-1 (Aurora - D05), 260kV Bus 1 (D05), T1 (D05 Syncrude), D05 517 (D05), D05 519 (D05), 213 (Aurora), 211 (Aurora), D05 511 (D05), D05 71 (D05), D05 71A (D05), D05 511A (D05), D05 519A (D05), D05 510 (D05), D05 520 (D05), D05 517A (D05), 89-215 (Aurora), D05 519B (D05) | 2025-06-02 08:00 | 2025-06-16 16:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 38.2TR (SS-38) | 2025-06-02 08:00 | 2025-06-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 21.61L (SS-21 - SS-34), 21B69-21.61 (SS-21) | 2025-06-02 08:00 | 2025-06-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 41.1TR (SS-41) | 2025-06-02 08:00 | 2025-06-03 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2025-06-02 09:00 | 2025-06-12 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 700s 705C (700s Bonnyville) | 2025-06-02 09:00 | 2025-06-03 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s SU2402 (657s Summerside), 657s SU2401 (657s Summerside), 89s 452 (89s Ellerslie), 89s 352 (89s Ellerslie), 657s SUDS9 (657s Summerside), 89s 1057 (89s Ellerslie) | 2025-06-02 09:30 | 2025-06-02 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L48 (794s Valleyview - 7LA48 tap), 794s 703 (794s Valleyview) | 2025-06-02 09:30 | 2025-06-03 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 1109L (SS-25 - SS-65) | 2025-06-02 10:01 | 2025-06-03 12:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition
ALTALINK | 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck), 513s 1 (513s Lundbreck) | 2025-06-02 10:30 | 2025-06-02 14:30 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ATCO | 2082s 701 (2082s Dog Rib) | 2025-06-02 13:00 | 2025-06-02 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK, BCH | 1L274 (BCH Natal - BCH Line Creek tap), T1 (BCH Natal), T2 (BCH Natal) | 2025-06-03 06:00 | 2025-06-03 19:00 | N | Y |  | Line, Transformer |  |  | For Information Only
ALTALINK | 861L (71s Lamoureux - 258s Dow Hydrocarbons) | 2025-06-03 07:00 | 2025-06-03 15:26 | N | Y |  | Line |  | Outage returned early. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 76L (33s Spray - 115s Mount Allan), 33s 76 (33s Spray) | 2025-06-03 07:00 | 2025-06-03 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, ENEL | 205s T2 (205s Castle Rock Ridge), 205s C1 (205s Castle Rock Ridge), 205s 52M2 (205s Castle Rock Ridge), 205s 89T2 (205s Castle Rock Ridge), 205s 89F11 (205s Castle Rock Ridge), 205s 89F12 (205s Castle Rock Ridge), 205s 89F13 (205s Castle Rock Ridge), 205s 89R11 (205s Castle Rock Ridge) | 2025-06-03 07:30 | 2025-06-05 16:30 | N | Y |  | Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 491L (252s Jarrow - 7L50 tap) | 2025-06-03 08:00 | 2025-06-03 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, BCH | 1L274 (BCH Natal - BCH Line Creek tap) | 2025-06-03 08:00 | 2025-06-10 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L109 (791s Rainbow Lake - 930s Arcenciel), 791s 703 (791s Rainbow Lake), 930s 7L109D2 (930s Arcenciel) | 2025-06-03 08:30 | 2025-06-04 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 331s T2 (331s Ponoka) | 2025-06-03 09:00 | 2025-06-05 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib), 718s 702 (718s Parsons Creek) | 2025-06-03 09:00 | 2025-06-03 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, CascadeP | 1084L (39s Bickerdike - 1047s Whisky Jack), 1047s T10 (1047s Whisky Jack), 1047s GS001 (1047s Whisky Jack), 1047s GS002 (1047s Whisky Jack), 1047s GS003 (1047s Whisky Jack), 1047s GS006 (1047s Whisky Jack), 1047s GD003 (1047s Whisky Jack), 1047s GD006 (1047s Whisky Jack), 39s 1084 (39s Bickerdike), 39s 1135 (39s Bickerdike) | 2025-06-03 12:00 | 2025-06-03 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, For Information Only
ALTALINK | 38s 3152 (38s East Edmonton), 38s C2 (38s East Edmonton) | 2025-06-03 12:30 | 2025-06-03 17:30 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 888s 919C (888s Dover) | 2025-06-03 14:58 | 2025-06-14 | N | Y |  | Shunts |  |  | For Information Only
EPCOR | 987s GT3 (987s Clover Bar) | 2025-06-04 07:00 | 2025-06-08 10:00 | N | Y |  | Transformer |  | Ended early | Restricts Generation
SUNCOR | 29PL7-5 (29EDD-18 Firebag - 29EDD-71), 29EDD-71 752-4613 (29EDD-71), 29EDD-71 752-4614 (29EDD-71) | 2025-06-04 08:00 | 2025-06-09 16:00 | N | N |  | Line, Circuit Breaker |  | Outage completed early | For Information Only
ENMAX | 16.1TR (SS-16) | 2025-06-04 08:00 | 2025-06-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA | 245s 138kV North Bus (245s Seebe), 245s T1 (245s Seebe), 56L (20s Ghost - 245s Seebe), 87L (2s Kananaskis - 245s Seebe), 754L (245s Seebe - 742L tap), 245s 56E (245s Seebe), 20s 56 (20s Ghost), 245s 754W (245s Seebe) | 2025-06-04 09:00 | 2025-06-04 17:00 | N | Y |  | Bus, Transformer, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 718s 703 (718s Parsons Creek) | 2025-06-04 09:00 | 2025-06-04 17:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
Saskpower | SASK POWER P2C | 2025-06-04 09:00 | 2025-06-05 18:00 | N | Y |  | Line |  |  | Pre-Condition
ATCO | 813s 706 (813s Little Smoky) | 2025-06-04 09:30 | 2025-06-05 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
SUNCOR | 635EDD-1000 144kV Bus 635PP-1000 (635EDD-1000), 635EDD-1000 635PT-1000 (635EDD-1000), 635EDD-1000 635PS-1002 (635EDD-1000), 635EDD-1000 635PS-1004 (635EDD-1000), 635EDD-1000 635PS-1010 (635EDD-1000), 635EDD-1000 635PS-1022 (635EDD-1000), 635EDD-1000 635PS-1026 (635EDD-1000), 635EDD-1000 635PS-1030 (635EDD-1000), 635EDD-1000 635PS-1016 (635EDD-1000), 635EDD-1000 635-752-635PT-1000 (635EDD-1000), 635EDD-1000 635PS-9520 (635EDD-1000), 635EDD-1000 635-752-111 (635EDD-1000), 635EDD-1000 635-752-121 (635EDD-1000), 635EDD-1000 635-752-131 (635EDD-1000), 635EDD-1000 635-752-142 (635EDD-1000), 635EDD-1000 635-752-152 (635EDD-1000), 635EDD-1000 635-752-161 (635EDD-1000) | 2025-06-05 08:00 | 2025-06-10 18:00 | N | Y |  | Bus, Transformer, Switch, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 791s 701 (791s Rainbow Lake), 7L122 (791s Rainbow Lake - 930s Arcenciel) | 2025-06-05 08:30 | 2025-06-05 12:32 | N | N |  | Circuit Breaker, Line |  | Completed early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 718s 701 (718s Parsons Creek) | 2025-06-05 09:00 | 2025-06-05 12:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31) | 2025-06-05 09:00 | 2025-06-06 14:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 7L62 (797s Kemp River - 905s Meikle) | 2025-06-05 17:05 | 2025-06-15 16:00 | N | Y |  | Line |  | returned early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L58 (789s Keg River - 905s Meikle) | 2025-06-05 18:05 | 2025-06-06 15:30 | N | Y |  | Line |  |  | For Information Only,Affects Cranking Path
ALTALINK | 223L (150s Clyde - 159s Colinton), 150s 223N (150s Clyde), 159s 223 (159s Colinton) | 2025-06-07 07:00 | 2025-06-08 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL9-3 (29EDD-1 Millennium - 29EDD-3), 29EDD-1 29EDD1s552 (29EDD-1 Millennium), 29EDD-1 29EDD1s652 (29EDD-1 Millennium), 29EDD-1 29EDD1SPL9-3 (29EDD-1 Millennium) | 2025-06-07 08:00 | 2025-06-09 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  | Completed early | 240 kV, Restricts Generation
ENMAX | 9.2TR (SS-9) | 2025-06-07 08:00 | 2025-06-10 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 854L (39s Bickerdike - 854AL tap), 854AL (348s Marlboro - 854L tap), 854L (1012s Deer Hill - 854AL tap) | 2025-06-07 09:48 | 2025-06-07 16:00 | N | N |  | Line
ATCO | 9L15 (834s Wesley Creek - 876s Brintnell) | 2025-06-07 18:42 | 2025-06-17 10:12 | N | Y |  | Line |  | Returned early | 240 kV, Contingency Requires Mitigation
ALTALINK | 864AL (346s Kaybob - 864L tap), 864BL (355s Chevron Knight - 864L tap), 864L (397s Benbow - 864AL tap), 864L (551s Chevron Kaybob - 864BL tap), 551s T1 (551s Chevron Kaybob), 346s T1 (346s Kaybob), 355s T1 (355s Chevron Knight), 355s T2 (355s Chevron Knight) | 2025-06-08 08:00 | 2025-06-08 16:00 | N | N |  | Line, Transformer |  |  | For Information Only
ENMAX | 20.82L (SS-20 - SS-21), 20.3TR (SS-20), 21B138-20.82 (SS-21), SW84 (SS-20), 20MD138-20.3TR (SS-20) | 2025-06-08 08:00 | 2025-06-08 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31) | 2025-06-08 09:00 | 2025-06-10 09:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 355s T1 (355s Chevron Knight), 355s T2 (355s Chevron Knight) | 2025-06-08 15:00 | 2025-06-25 07:59 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 397s 864W (397s Benbow) | 2025-06-08 15:00 | 2025-11-25 15:30 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2025-06-08 16:47 | 2025-06-12 18:00 | N | Y |  | Shunts, Circuit Breaker |  | needed more time | Pre-Condition
Wild Rose Wind 2 | WIR1 Wild Rose Generator Test | 2025-06-09 | 2025-09-15 23:59 | N | Y |  | Unit
ATCO, CNRL | 859s 702 (859s Primrose) | 2025-06-09 07:00 | 2025-06-10 18:00 | N | N |  | Circuit Breaker |  |  | For Information Only
EPCOR | 72RG1 (Garneau - Rossdale), RG7210 (Rossdale), GDS18 (Garneau) | 2025-06-09 07:00 | 2025-06-13 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
EPCOR | 657s T2 (657s Summerside) | 2025-06-09 07:00 | 2025-06-20 17:00 | N | Y |  | Transformer |  |  | 240 kV
EPCOR | 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial) | 2025-06-09 07:00 | 2025-06-25 07:34 | N | Y |  | Transformer, Circuit Breaker |  | RTN early | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), 72LS24 (EP 803s Lambton - Strathcona), EP 803s T3 (EP 803s Lambton), T3 (Strathcona), EP 803s L721 (EP 803s Lambton), S724 (Strathcona), S723 (Strathcona), SDS10 (Strathcona), SAB3 (Strathcona) | 2025-06-09 07:00 | 2025-06-15 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, For Information Only, Pre-Condition
EPCOR | T3 (Woodcroft), W722 (Woodcroft) | 2025-06-09 07:00 | 2025-06-20 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.2TR (SS-13) | 2025-06-09 08:00 | 2025-06-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.1TR (SS-5) | 2025-06-09 08:00 | 2025-06-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 43.1TR (SS-43) | 2025-06-09 08:00 | 2025-06-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 41B138-33.83 (SS-41) | 2025-06-09 08:00 | 2025-06-09 17:00 | N | N |  | Line, Circuit Breaker |  | Completed early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L75 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2025-06-09 09:00 | 2025-06-13 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC
ATCO | 700s 707C (700s Bonnyville) | 2025-06-09 09:00 | 2025-06-10 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 764s 701T (764s Heisler) | 2025-06-09 09:30 | 2025-06-13 17:30 | N | N |  | Transformer |  |  | Pre-Condition
ATCO | 801s 902 (801s Anderson) | 2025-06-09 09:30 | 2025-06-10 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L92 (777s Vilna - 7LA92 tap) | 2025-06-09 09:30 | 2025-06-11 16:00 | N | N |  | Line |  | done early | Over/Under Voltage, Overload, Pre-Condition
ATCO | 813s Little Smoky 144kV Bus 1, 813s 901T (813s Little Smoky), 813s 701 (813s Little Smoky), 813s 705 (813s Little Smoky), 813s 707 (813s Little Smoky), 813s 718 (813s Little Smoky) | 2025-06-09 10:00 | 2025-06-10 17:30 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 951s SVC (951s Thickwood), 951s 919 (951s Thickwood Hills) | 2025-06-09 12:00 | 2025-06-12 17:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 723s 240kV Bus 2 (723s Christina Lake), 723s T2 (723s Christina Lake), 723s 252 (723s Christina Lake), 723s 652 (723s Christina Lake), 723s 12 (723s Christina Lake) | 2025-06-09 12:30 | 2025-06-11 19:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s 23 (370s North Lethbridge) | 2025-06-09 13:00 | 2025-06-13 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 716s 701C (716s Lloydminster) | 2025-06-09 13:30 | 2025-07-17 14:40 | N | N |  | Shunts |  | Outage returned to service. | Pre-Condition
EPCOR | T4 (Rossdale) | 2025-06-10 | 2025-06-11 23:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1012L (326s Murray Lake - 516s Forty Mile) | 2025-06-10 10:00 | 2025-06-22 09:00 | N | Y |  | Line |  |  | Restricts Generation
ATCO, CNRL | 859s 703 (859s Primrose), 859s 703B (859s Primrose) | 2025-06-11 07:00 | 2025-06-11 16:00 | N | N |  | Circuit Breaker, Switch |  | done early | Pre-Condition
ALTALINK | 912L (63s Red Deer - 766s Nevis) | 2025-06-11 08:00 | 2025-06-11 18:00 | N | Y |  | Line |  |  | Affects Cranking Path
ENMAX | 33.84L (SS-33 - SS-43), 43B138-33.84 (SS-43), 33B138-33.84 (SS-33) | 2025-06-11 08:00 | 2025-06-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 24.81L (SS-24 - SS-31), 31B138-24.81 (SS-31) | 2025-06-11 08:30 | 2025-06-12 14:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 801s 903 (801s Anderson) | 2025-06-11 09:30 | 2025-06-12 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 813s Little Smoky 144kV Bus 2, 813s 902T (813s Little Smoky), 813s 713 (813s Little Smoky), 813s 710 (813s Little Smoky), 813s 711 (813s Little Smoky), 813s 704 (813s Little Smoky) | 2025-06-11 10:00 | 2025-06-11 16:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  | done early | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 717s 701 (717s Ethel Lake), 846s 701 (846s Grand Centre) | 2025-06-11 10:00 | 2025-06-11 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 723s 240kV Bus 1 (723s Christina Lake), 723s T1 (723s Christina Lake), 723s 152 (723s Christina Lake), 723s 1652 (723s Christina Lake), 723s 4 (723s Christina Lake) | 2025-06-11 19:01 | 2025-06-14 16:15 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  | starting early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s GT1 (987s Clover Bar) | 2025-06-12 02:00 | 2025-06-12 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 758L (534s Eckville - 757L tap), 534s T1 (534s Eckville), 534s 758 (534s Eckville), 534s 40 (534s Eckville) | 2025-06-12 06:00 | 2025-06-12 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale) | 2025-06-12 07:00 | 2025-06-12 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 144kV Bus 635PP-1007 (635EDD-1001), 635EDD-1001 635-752-613 (635EDD-1001), 635EDD-1001 635-752-623 (635EDD-1001), 635EDD-1001 635-752-632 (635EDD-1001), 635EDD-1001 635-752-643 (635EDD-1001), 635EDD-1001 635-752-653 (635EDD-1001), 635EDD-1001 635-752-663 (635EDD-1001) | 2025-06-12 07:00 | 2025-06-17 17:00 | N | N |  | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 199L (347s AML Fox Creek - 199AL tap), 347s 199E (347s AML Fox Creek) | 2025-06-12 09:30 | 2025-06-12 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 123L (19s Wabamun - 352s Onoway), 352s T1 (352s Onoway), 352s 123 (352s Onoway), 19s 123 (19s Wabamun) | 2025-06-13 07:00 | 2025-06-13 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 14.83L (SS-14 - SS-36), 36B138-14.83 (SS-36) | 2025-06-13 08:00 | 2025-06-13 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 36.81L (44s Bearspaw Plant - SS-36), 36B138-36.81 (SS-36) | 2025-06-13 11:00 | 2025-06-13 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 36B138-36BT3 (SS-36) | 2025-06-13 13:00 | 2025-06-13 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
EPCOR | T3 (Rossdale) | 2025-06-13 17:00 | 2026-01-26 07:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29PL6-2 (30EDD-1 - 29EDD-55), 30EDD-1 622T (30EDD-1), 30EDD-1 626 (30EDD-1), 30EDD-1 625 (30EDD-1), 30EDD-1 624 (30EDD-1), 30EDD-1 622TD (30EDD-1), 30EDD-1 29PL6-2CS (30EDD-1) | 2025-06-13 20:01 | 2025-06-22 16:04 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ALTALINK | 38s C2 (38s East Edmonton) | 2025-06-14 08:00 | 2025-07-16 08:59 | N | N |  | Shunts |  | Extended: Altalink operator thinks this outage should be completed July.17/25 | Pre-Condition
ALTALINK | 170s 1352 (170s Pike) | 2025-06-14 08:00 | 2025-06-14 11:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 26.83L (SS-26 - SS-65), 65B138-D85 (SS-65), 65B138-D84 (SS-65), 65MD138-26.83 (SS-65), 26B138-26.83 (SS-26) | 2025-06-14 08:00 | 2025-06-14 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 170s 1452 (170s Pike) | 2025-06-14 11:01 | 2025-06-14 14:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 428L (167s Ipiatik Lake - 818s Winefred), 167s 2052 (167s Ipiatik Lake), 818s 428 (818s Winefred) | 2025-06-14 14:30 | 2025-06-14 19:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 789L (818s Winefred - 789BL tap), 818s C2 (818s Winefred), 818s C3 (818s Winefred), 818s T2 (818s Winefred), 818s 789 (818s Winefred), 818s 20 (818s Winefred) | 2025-06-15 08:30 | 2025-06-16 12:59 | N | N |  | Line, Shunts, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s GT1 (987s Clover Bar), 987s CGB1 (987s Clover Bar) | 2025-06-16 02:00 | 2025-06-16 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
EPCOR | 746AL (524s Owens Corning - 746L tap), 524s 6 (524s Owens Corning), 524s T1 (524s Owens Corning) | 2025-06-16 07:00 | 2025-06-21 17:00 | N | N |  | Line, Circuit Breaker, Transformer |  |  | For Information Only
EPCOR | 72 kV Bus 3 (Rossdale), 72RV2 (EP 511s Victoria - Rossdale), 72RG1 (Garneau - Rossdale), RG7210 (Rossdale), RR729 (Rossdale), RV728 (Rossdale), VHBB2 (Rossdale) | 2025-06-16 07:00 | 2025-06-18 17:00 | N | N |  | Bus, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), RV728 (Rossdale), EP 511s V721 (EP 511s Victoria), EP 511s V729 (EP 511s Victoria), EP 511s VDS1 (EP 511s Victoria) | 2025-06-16 07:00 | 2025-06-20 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, CNRL | 859s 702T (859s Primrose) | 2025-06-16 07:00 | 2025-06-23 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton), 133s 1 (133s Stelco Edmonton), 133s 2 (133s Stelco Edmonton) | 2025-06-16 07:00 | 2025-06-20 16:00 | N | N |  | Transformer, Switch |  |  | For Information Only
EPCOR | 1164L (816s Petrolia - EP Riverview), RW2402 (EP Riverview), RW2401 (EP Riverview), 816s P2403 (816s Petrolia), 816s P2404 (816s Petrolia) | 2025-06-16 07:00 | 2025-06-20 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ENMAX | 43.2TR (SS-43) | 2025-06-16 08:00 | 2025-06-19 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B138-RB80 (SS-162) | 2025-06-16 08:00 | 2025-06-16 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 31.1C (SS-31) | 2025-06-16 08:00 | 2025-07-23 16:00 | N | N |  | Shunts |  | done early | Pre-Condition
ENMAX | 27.2TR (SS-27) | 2025-06-16 08:00 | 2025-06-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | ATC 793s 706C (ATC 793s West Peace River) | 2025-06-16 09:00 | 2025-06-17 17:00 | N | N |  | Shunts |  |  | Pre-Condition
BCH | 5L77 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2025-06-16 09:00 | 2025-06-25 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC
ATCO | 959s 901T (959s Lanfine) | 2025-06-16 10:00 | 2025-06-19 15:45 | N | Y |  | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 650s SVC (650s Hansman Lake), 650s T3 (650s Hansman Lake), 650s 252 (650s Hansman Lake), 650s 352 (650s Hansman Lake), 650s 489 (650s Hansman Lake) | 2025-06-16 11:30 | 2025-06-20 16:30 | N | Y |  | Shunts, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ATCO | 885s 902T (885s McMillan), 885s 501R (885s McMillan) | 2025-06-16 12:00 | 2025-06-20 16:00 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 428L (167s Ipiatik Lake - 818s Winefred), 818s C1 (818s Winefred), 818s T3 (818s Winefred), 818s 428 (818s Winefred) | 2025-06-16 13:00 | 2025-06-17 18:00 | N | N |  | Line, Shunts, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 650s 240kV Bus 2 (650S Hansman Lake), 650s 352 (650s Hansman Lake), 650s 652 (650s Hansman Lake), 650s 952 (650s Hansman Lake) | 2025-06-17 08:00 | 2025-06-17 15:00 | N | Y |  | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 32.1TR (SS-32) | 2025-06-17 08:00 | 2025-06-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 808s 701T (808s Procter & Gamble), 808s 401 (808s Procter & Gamble), 808s 701 (808s Procter & Gamble) | 2025-06-17 08:00 | 2025-06-18 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
Syncrude | ML2 (Syncrude Mildred Lake - UE-1 Syncrude Plant 30-2), UE-1 7201 (UE-1 Syncrude Plant 30-2), 1015 (Syncrude Mildred Lake) | 2025-06-17 08:00 | 2025-06-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 845s 702 (845s Big Mountain) | 2025-06-17 08:00 | 2025-06-18 19:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
BPWF | BPW1 Buffalo Plains Generator Test | 2025-06-17 08:00 | 2025-08-10 16:00 | N | N |  | Unit
ATCO, ALTALINK | 7L696 (508s Lakesend - 892s Ribstone Creek), 508s T1 (508s Lakesend), 892s 702 (892s Ribstone Creek), 508s 696 (508s Lakesend), 508s 9 (508s Lakesend) | 2025-06-17 08:00 | 2025-06-17 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 163s T1 (163s Amoco Empress) | 2025-06-17 09:00 | 2025-06-21 09:00 | N | Y |  | Transformer |  |  | For Information Only
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-06-17 23:00 | 2025-06-17 23:30 | N | Y |  | Line |  |  | 500 kV
ALTALINK | 431s T1 (431s Hussar), 431s 195 (431s Hussar) | 2025-06-18 07:00 | 2025-06-18 12:00 | N | N |  | Transformer, Switch |  |  | Pre-Condition
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 38s 761N (38s East Edmonton) | 2025-06-18 07:00 | 2025-06-18 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX, ALTALINK | 5s C3 (5s East Calgary) | 2025-06-18 07:30 | 2025-06-18 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 39B138-22.81 (SS-39), 22B138-22.81 (SS-22) | 2025-06-18 08:00 | 2025-06-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 786L (799s Coleman - BCH Natal) | 2025-06-18 08:00 | 2025-06-20 17:00 | N | Y |  | Line | WebOMS Outage ID : 18114790 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 910s 701 (910s Excel), 910s 701T (910s Excel) | 2025-06-18 08:00 | 2025-06-18 18:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 551s T1 (551s Chevron Kaybob) | 2025-06-18 10:00 | 2025-06-18 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 431s T2 (431s Hussar), 431s 295 (431s Hussar) | 2025-06-18 12:05 | 2025-06-18 17:00 | N | N |  | Transformer, Switch |  |  | Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-06-18 14:00 | 2025-06-26 13:00 | N | Y |  | Line |  |  | 500 kV
ALTALINK, ENBRIDGE | 703L (213s Hughenden - 703BL tap), 213s 703 (213s Hughenden), 329s HRT-S2 (329s Hrt Express) | 2025-06-19 07:00 | 2025-06-20 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | GT3 (Garneau), T3 (Garneau) | 2025-06-19 07:00 | 2025-06-19 17:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
SUNCOR | 635EDD-1001 635PK-1003 (635EDD-1001), 635EDD-1001 635PS-1110 (635EDD-1001) | 2025-06-19 08:00 | 2025-06-24 16:00 | N | N |  | Shunts, Switch |  |  | Pre-Condition
ALTALINK | 421s T1 (421s Hays), 421s 2 (421s Hays) | 2025-06-19 08:00 | 2025-06-19 14:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ATCO | 845s 703 (845s Big Mountain) | 2025-06-19 08:00 | 2025-06-20 19:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 808s 702T (808s Procter & Gamble), 808s 702 (808s Procter & Gamble) | 2025-06-19 08:00 | 2025-06-20 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX | 162B138-RB81 (SS-162) | 2025-06-20 08:00 | 2025-06-20 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27), 13B69-13.60 (SS-13), 27MD69-27.2TR (SS-27), SW65 (SS-27) | 2025-06-20 08:00 | 2025-06-20 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude, ATCO | RL1 (848s Ruth Lake - D05), T2 (D05 Syncrude), D05 517 (D05), D05 516 (D05), D05 513 (D05), D05 78 (D05), D05 517B (D05), D05 516A (D05), D05 516B (D05), D05 513A (D05), D05 513B (D05), D05 509 (D05), D05 78A (D05), 848s RL-1D1 (848s Ruth Lake) | 2025-06-21 08:00 | 2025-07-08 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13.1TR (SS-13), 13.3TR (SS-13), 13B138-2.83 (SS-13), 13B138-3.84 (SS-13), 5B138-2.83 (SS-5), 3B138-3.84 (SS-3), SW83 (SS-13), 13MD138-13.1TR (SS-13), 13MD138-13.3TR (SS-13), 2MD138-2.83 (SS-2) | 2025-06-21 08:00 | 2025-06-21 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.2TR (SS-31) | 2025-06-22 09:00 | 2025-06-24 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, VISIONREQ | 354s PMU (354s Summerview), 354s 138DS4 (354s Summerview) | 2025-06-23 07:00 | 2025-06-26 18:00 | N | N |  | Terminal Equipment, Switch |  |  | Restricts Generation
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), 987s CH722 (987s Clover Bar), H724 (EP Hardisty) | 2025-06-23 07:00 | 2025-06-26 11:10 | N | N |  | Line, Circuit Breaker |  | RTN early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RV4 (EP 511s Victoria - Rossdale), EP 511s V726 (EP 511s Victoria), EP 511s V727 (EP 511s Victoria), RV726 (Rossdale) | 2025-06-23 07:00 | 2025-06-26 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | RR729 (Rossdale) | 2025-06-23 07:00 | 2025-06-27 17:00 | N | N |  | Circuit Breaker |  |  | Firm Load Loss, Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 16B69-16.63 (SS-16), 36B69-16.63/36.5TR (SS-36) | 2025-06-23 08:00 | 2025-06-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 38.3TR (SS-38) | 2025-06-23 08:00 | 2025-06-25 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 808s 702T (808s Procter & Gamble), 808s 702 (808s Procter & Gamble) | 2025-06-23 09:30 | 2025-06-27 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 757s 912T (757s Battle River), 757s 710 (757s Battle River), 757s 912 (757s Battle River), 755s 9L80D2 (755s Cordel) | 2025-06-23 09:30 | 2025-06-26 17:32 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Complete early | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 844s 701T (844s AEC Mill), 844s 701 (844s AEC Mill) | 2025-06-23 10:00 | 2025-06-24 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 9L29 (946s Oakland - 963s Coyote Lake), 7L128 (963s Coyote Lake - 7LA128 tap), 963s 901T (963s Coyote Lake), 963s 901 (963s Coyote Lake), 963s 701 (963s Coyote Lake), 963s 7L128D4 (963s Coyote Lake), 963s 9L29D1 (963s Coyote Lake), 946s 9L29D2 (946s Oakland) | 2025-06-23 10:00 | 2025-06-26 14:21 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  | Back Early | 240 kV, Creates Radial Feeds, Over/Under Voltage, Pre-Condition
ALTALINK | 89s T1 (89s Ellerslie) | 2025-06-23 11:30 | 2025-06-26 18:30 | N | Y |  | Transformer |  |  | 240 kV, 500 kV, Pre-Condition
REDDEER | 217s T2 (217s North Red Deer) | 2025-06-23 12:00 | 2025-07-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 848s 402R (848s Ruth Lake), 848s 403R (848s Ruth Lake), 848s 404R (848s Ruth Lake), 848s 402 (848s Ruth Lake) | 2025-06-23 12:00 | 2025-06-24 17:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 826s 901T (826s Marguerite Lake), 826s 502R (826s Marguerite Lake) | 2025-06-23 12:00 | 2025-07-04 16:00 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1140L (89s Ellerslie - 289s Saunders Lake), 89s 952 (89s Ellerslie), 89s 1052 (89s Ellerslie) | 2025-06-23 13:30 | 2025-06-26 18:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
BCH | 5L92 (BCH Cranbrook - BCH Selkirk), 5D44 (BCH Cranbrook) | 2025-06-23 19:00 | 2025-06-23 23:59 | Y | Y |  | Line, Switch | *FOR OC** 1. Enter TRMr+ = 466 MW in MARGO manual override 2. Check MARGO BC/MATL capability (ATC). The BC/MATL capability (ATC) = 99 MW (lowest number for the period of Jun 23, 2025 (HE20 - HE24), lowest value at Jun 23, 2025 HE24. 3. In order to show 0 MW on S&D. Using max MATL Import ATC: 310 MW (No Restriction )  15 MW (MATL TRM ) = 295 MW, so the BC import ATC becomes 99 MW  295 MW = -196 MW (enter 0, instead of a negative number). |  | Limits ATC, 500 kV
ALTALINK | 891L (226s Garden City - 863L tap) | 2025-06-24 08:00 | 2025-06-26 18:00 | N | Y |  | Line |  |  | Restricts Generation
ENMAX | 37.3TR (SS-37) | 2025-06-24 08:00 | 2025-06-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 510s 2552 (510s Sunnybrook) | 2025-06-24 08:00 | 2025-06-25 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, For Information Only
EHN, ALTALINK, ENBRIDGE | 226s Garden City, 891L (226s Garden City - 863L tap), 226s T1 (226s Garden City), 226s 52/T1 (226s Garden City) | 2025-06-24 08:00 | 2025-06-27 18:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker |  | Complete integration of Chin Chute substation and point to point testing. | Restricts Generation
ATCO | ATC 793s 701T (ATC 793s West Peace River) | 2025-06-24 08:30 | 2025-06-25 16:00 | N | N |  | Transformer |  |  | Pre-Condition
ALTALINK | 127s C1 (127s Bruderheim) | 2025-06-24 08:30 | 2025-06-24 14:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 356s 152 (356s Milo) | 2025-06-24 08:30 | 2025-06-24 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 863L (618s Riverbend - 891L tap), 618s 863X (618s Riverbend) | 2025-06-24 09:00 | 2025-06-24 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 844s 702T (844s AEC Mill), 844s 402 (844s AEC Mill) | 2025-06-24 15:30 | 2025-06-25 16:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 413L (239s Castle River - 632s Russell), 632s 413 (632s Russell) | 2025-06-25 07:00 | 2025-06-25 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2025-06-25 07:00 | 2025-06-26 18:00 | N | Y |  | Line |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 864L (397s Benbow - 864AL tap), 864L (864AL tap - 864BL tap), 864L (551s Chevron Kaybob - 864BL tap), 864AL (346s Kaybob - 864L tap), 864BL (355s Chevron Knight - 864L tap), 346s T1 (346s Kaybob), 355s T1 (355s Chevron Knight), 355s T2 (355s Chevron Knight), 551s T1 (551s Chevron Kaybob), 355s 2 (355s Chevron Knight), 355s 4 (355s Chevron Knight), 551s 864N (551s Chevron Kaybob), 346s 864AN (346s Kaybob) | 2025-06-25 08:00 | 2025-06-25 16:00 | N | N |  | Line, Transformer, Switch |  |  | Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34), 16B69-16.60 (SS-16) | 2025-06-25 08:00 | 2025-06-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL6-4 (29EDD-1 Millennium - 30EDD-1), 29EDD-1 29EDD1s1552 (29EDD-1 Millennium), 29EDD-1 29EDD1s1652 (29EDD-1 Millennium), 30EDD-1 622 (30EDD-1), 30EDD-1 623 (30EDD-1), 29EDD-1 29EDD1SPL6-4 (29EDD-1 Millennium), 30EDD-1 29PL6-4D1 (30EDD-1) | 2025-06-25 08:00 | 2025-07-03 20:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 36.2TR (SS-36) | 2025-06-25 08:00 | 2025-06-26 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 356s 552 (356s Milo) | 2025-06-25 08:30 | 2025-06-25 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK, TRANSALTA | 59s T1 (59s Peigan), 59s 138kV Bus (59s Peigan), 616L (59s Peigan - 616AL tap), 59s 616 (59s Peigan) | 2025-06-25 08:30 | 2025-06-25 16:30 | N | Y |  | Transformer, Bus, Line, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX | 31.3TR (SS-31) | 2025-06-25 09:00 | 2025-06-26 14:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ATCO | ATC 793s 702T (ATC 793s West Peace River) | 2025-06-25 16:15 | 2025-07-04 16:00 | N | N |  | Transformer |  |  | Pre-Condition
ATCO | 801s 701T (801s Anderson) | 2025-06-25 18:40 | 2025-07-04 11:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746L (700L tap - 746AL tap), 422s 700 (422s Westwood), 746s 700N (746s Sherwood Park) | 2025-06-26 07:30 | 2025-06-26 12:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 635PK-1002 (635EDD-1001), 635EDD-1001 635-752-642 (635EDD-1001), 635EDD-1001 635-752-643 (635EDD-1001) | 2025-06-26 08:00 | 2025-07-01 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 356s 652 (356s Milo) | 2025-06-26 08:30 | 2025-06-26 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 706L (410s Josephburg - 706AL tap) | 2025-06-26 12:31 | 2025-06-26 17:30 | N | N |  | Line |  |  | Overload, Pre-Condition, Affects Cranking Path
ENMAX | 26.81L (SS-26 - SS-32), 32B138-26.81 (SS-32), 26B138-26.81 (SS-26) | 2025-06-27 08:00 | 2025-06-27 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32), 40B138-32.83 (SS-40) | 2025-06-27 12:00 | 2025-06-27 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 37s 726E (37s North Calder) | 2025-06-27 12:00 | 2025-06-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO, ALTALINK | 766s 903T (766s Nevis), 766s 240kV Bus (766s Nevis), 9L20 (755s Cordel - 766s Nevis), 912L (63s Red Deer - 766s Nevis) | 2025-06-27 16:00 | 2025-06-27 22:00 | N | Y |  | Transformer, Bus, Line |  | Returned from forced | 240 kV, Affects Cranking Path
ENMAX | 7B138-7BT3 (SS-7) | 2025-06-28 08:00 | 2025-06-28 12:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 47B138-771 (SS-47) | 2025-06-28 12:00 | 2025-06-28 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 802s 702T (802s Michichi Creek), 802s 702 (802s Michichi Creek) | 2025-06-30 02:00 | 2025-07-19 17:00 | N | N |  | Transformer, Circuit Breaker |  | forced | For Information Only
ENMAX | 3.82L (SS-3 - SS-8), 3B138-3.82 (SS-3) | 2025-06-30 08:00 | 2025-07-15 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL7-2 (29EDD-18 Firebag - 29EDD-63), 29EDD-63 29PT-179 (29EDD-63 Firebag Co-Gen), 29EDD-63 30-252-11301 (29EDD-63) | 2025-06-30 08:00 | 2025-07-17 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Restricts Generation
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2025-06-30 10:00 | 2025-07-03 14:55 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L36 (820s Hangingstone - 2009s Willow Lake), 820s 701 (820s Hangingstone) | 2025-06-30 12:00 | 2025-06-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 28.1TR (SS-28) | 2025-07-01 08:00 | 2025-07-01 18:00 | N | N |  | Transformer |  |  | For Information Only
BCH | BCH Green Hills, 1D6L274 (BCH Green Hill tap) | 2025-07-01 09:00 | 2025-07-01 17:00 | N | N |  | Station, Switch |  |  | Pre-Condition
ALTALINK | 83s T1 (83s Taber), 83s 65 (83s Taber) | 2025-07-02 07:00 | 2025-07-02 16:30 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 786L (799s Coleman - BCH Natal), 799s 786W (799s Coleman) | 2025-07-02 07:00 | 2025-07-02 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 72DS26 (665s Dome - Strathcona), 665s T3 (665s Dome), 665s D2401 (665s Dome), 665s D2404 (665s Dome), 665s D721 (665s Dome), S721 (Strathcona), 665s DDS13 (665s Dome), 665s DAB3 (665s Dome), 665s DDS17 (665s Dome), SDS3 (Strathcona) | 2025-07-02 07:00 | 2025-07-06 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 89s 1052 (89s Ellerslie), 89s 1152 (89s Ellerslie) | 2025-07-02 07:00 | 2025-07-06 17:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, For Information Only, Affects Cranking Path
ALTALINK, ENEL | 205s T2 (205s Castle Rock Ridge), 205s 89T2 (205s Castle Rock Ridge) | 2025-07-02 08:00 | 2025-07-02 12:00 | N | Y |  | Transformer, Switch |  |  | 240 kV, Restricts Generation
ATCO | 7L97 (820s Hangingstone - 7LA97 tap), 820s 702 (820s Hangingstone) | 2025-07-02 09:00 | 2025-07-02 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 749s 702 (749s Flyingshot Lake) | 2025-07-02 09:30 | 2025-07-03 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 774s 705C (774s Monitor) | 2025-07-02 10:00 | 2025-07-03 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2025-07-02 10:30 | 2025-07-04 15:30 | N | Y |  | Line |  |  | Pre-Condition
ALTALINK | 799s 138kV Bus (799s Coleman), 170L (632s Russell - 799s Coleman), 799s 170E (799s Coleman) | 2025-07-02 12:01 | 2025-07-02 16:59 | N | Y |  | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L135 (820s Hangingstone - 977s Salt Creek), 820s 704 (820s Hangingstone) | 2025-07-02 12:30 | 2025-07-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2025-07-02 17:00 | 2025-07-02 20:00 | Y | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s T1 (62s Brazeau Plant) | 2025-07-02 23:00 | 2025-07-03 03:00 | N | Y |  | Transformer |  |  | 240 kV, Restricts Generation
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-02 23:00 | 2025-07-02 23:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 62s T2 (62s Brazeau Plant) | 2025-07-03 03:01 | 2025-07-03 07:00 | N | Y |  | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 704L (51s Wainwright - 478s Tucuman) | 2025-07-03 07:00 | 2025-07-04 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 83s T3 (83s Taber), 83s 64 (83s Taber) | 2025-07-03 07:00 | 2025-07-03 16:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 845s 703 (845s Big Mountain) | 2025-07-03 08:00 | 2025-07-04 19:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 86s 152 (86s Bigstone), 805L (86s Bigstone - 964s Pigeon Lake) | 2025-07-03 08:00 | 2025-07-03 17:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge), 370s 770E (370s North Lethbridge), 254s 770 (254s Coaldale) | 2025-07-03 08:00 | 2025-07-04 15:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge) | 2025-07-03 08:00 | 2025-07-03 15:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 808s 702T (808s Procter & Gamble), 808s 702 (808s Procter & Gamble) | 2025-07-03 08:00 | 2025-07-04 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | 2L293 (BCH Nelway - BCH Selkirk), 2D1CB3 (BCH Selkirk) | 2025-07-03 09:00 | 2025-07-03 17:00 | N | Y |  | Line, Switch |  |  | 240 kV, Pre-Condition
BCH | 2L113 (BCH Cranbrook - BCH Natal) | 2025-07-03 09:00 | 2025-07-03 21:44 | N | Y |  | Line |  | RTS early | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2025-07-04 06:30 | 2025-07-04 13:30 | N | N |  | Line |  |  | Affects Cranking Path
ALTALINK | 368s C1 (368s Burdett) | 2025-07-04 08:30 | 2025-07-04 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 845s 702 (845s Big Mountain) | 2025-07-05 08:00 | 2025-07-06 19:00 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 808s 701T (808s Procter & Gamble), 808s 701 (808s Procter & Gamble), 808s 401 (808s Procter & Gamble) | 2025-07-05 08:00 | 2025-07-06 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | 1315 (Syncrude Mildred Lake), 1314 (Syncrude Mildred Lake), 1316 (Syncrude Mildred Lake) | 2025-07-05 08:00 | 2025-07-05 16:00 | N | N |  | Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 729L (285s East Camrose - 542s Ervick), 285s 729W (285s East Camrose) | 2025-07-06 07:30 | 2025-07-06 12:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Pre-Condition
ENMAX | 9.1TR (SS-9) | 2025-07-06 08:00 | 2025-07-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden), 197s 174E (197s Bardo), 395s 174W (395s North Holden) | 2025-07-06 12:31 | 2025-07-06 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray), 33s 113 (33s Spray), 20s 113 (20s Ghost) | 2025-07-07 07:00 | 2025-07-12 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
CNRL | 641s 702T (641s Primrose East) | 2025-07-07 07:00 | 2025-07-14 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), H725 (EP Hardisty), 987s CH724 (987s Clover Bar) | 2025-07-07 07:00 | 2025-07-11 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s T1 (987s Clover Bar), 987s T3 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2407 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s CDS25 (987s Cloverbar) | 2025-07-07 07:00 | 2025-07-16 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 681s T2 (681s Bannerman) | 2025-07-07 07:00 | 2025-07-10 14:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
EPCOR | 908AL (52S East Industrial - 908L tap), 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2025-07-07 07:00 | 2025-07-13 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.4TR (SS-2) | 2025-07-07 08:00 | 2025-07-10 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 21.1TR (SS-21) | 2025-07-07 08:00 | 2025-09-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-07-07 09:00 | 2025-07-10 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 826s 903 (826s Marguerite Lake) | 2025-07-07 09:00 | 2025-07-09 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L20 (740s H.R. Milner - 810s Dome Cutbank), 740s 704 (740s H.R. Milner) | 2025-07-07 09:00 | 2025-07-08 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L80 (740s H.R. Milner - 857s Kakwa Ridge), 7L80 (733s Simonette - 857s Kakwa Ridge), 740s 705 (740s H.R. Milner), 733s 701 (733s Simonette) | 2025-07-07 09:00 | 2025-07-07 20:10 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel), 828s 701 (828s Sulphur Point), 930s 7L93D1 (930s Arcenciel) | 2025-07-07 09:00 | 2025-07-08 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 808s 701T (808s Procter & Gamble), 808s 701 (808s Procter & Gamble), 808s 401 (808s Procter & Gamble) | 2025-07-07 09:30 | 2025-07-11 19:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ATCO | 741s 701T (741s Fox Creek), 741s 703 (741s ATC Fox Creek) | 2025-07-07 10:00 | 2025-07-16 08:25 | N | N |  | Transformer, Circuit Breaker |  | Outage returned early. | For Information Only
GLPC | SLR1 Sollair Solar Energy Plant Generator Test | 2025-07-07 11:00 | 2025-07-09 18:00 | N | Y |  | Unit
ATCO | 820s 702T (820s Hangingstone), 820s 703 (820s Hangingstone) | 2025-07-07 12:00 | 2025-07-10 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 632s PS1 (632s Russell), 632s 452 (632s Russell), 632s 552 (632s Russell) | 2025-07-07 12:30 | 2025-07-10 16:30 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 433L (291s Cochrane - AML 793s Horse Creek), AML 793s 433 (AML 793s Horse Creek), 291s 433 (291s Cochrane) | 2025-07-07 12:30 | 2025-07-10 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 784AL (482s Haynes - 784L tap), 482s T1 (482s Haynes), 482s 784AW (482s Haynes) | 2025-07-07 13:00 | 2025-07-10 17:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 939s 903T (939s Livock), 939s 910 (939s Livock), 939s 911 (939s Livock), 939s 912 (939s Livock), 939s 900D1 (939s Livock), 939s 9L10D2 (939s Livock), 876S 9L10D1 (876s Brintnell) | 2025-07-07 13:30 | 2025-07-09 14:20 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 896L (19s Wabamun - 432s Carvel), 19s 896 (19s Wabamun), 432s 896 (432s Carvel) | 2025-07-07 13:30 | 2025-07-10 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 2052 (74s Janet) | 2025-07-08 06:30 | 2025-07-09 18:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 162L (229s Glenwood - 415s Drywood), 415s 146E (415s Drywood) | 2025-07-08 07:00 | 2025-07-08 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 510s ACF21 (510s Sunnybrook), 510s ACF22 (510s Sunnybrook), 510s 1952 (510s Sunnybrook), 510s 2052 (510s Sunnybrook), 510s 35 (510s Sunnybrook), 510s 36 (510s Sunnybrook), 510s 79 (510s Sunnybrook), 510s 80 (510s Sunnybrook) | 2025-07-08 07:00 | 2025-07-09 15:30 | N | Y |  | Shunts, Circuit Breaker, Switch |  |  | 500 kV, Pre-Condition
ALTALINK | 648s T1 (648s Metiskow) | 2025-07-08 07:00 | 2025-07-08 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 510s ACF13 (510s Sunnybrook) | 2025-07-08 08:00 | 2025-07-09 17:00 | N | Y |  | Shunts |  |  | 500 kV, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-08 09:00 | 2025-07-08 09:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ENMAX | 31.1TR (SS-31) | 2025-07-08 10:00 | 2025-07-08 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.2TR (SS-31) | 2025-07-08 12:30 | 2025-07-08 14:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.3TR (SS-31) | 2025-07-08 15:00 | 2025-07-08 17:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-08 16:30 | 2025-07-08 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 784L (535s Joffre - 784AL tap), 784AL (482s Haynes - 784L tap), 784L (332s Ellis - 784AL tap), 332s 784 (332s Ellis) | 2025-07-09 07:00 | 2025-07-09 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 133L (19s Wabamun - 234L tap), 19s 133 (19s Wabamun) | 2025-07-09 07:00 | 2025-07-09 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2025-07-09 08:00 | 2025-07-16 16:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-09 09:00 | 2025-07-09 09:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
BCH | 1D23 (978s BCH Britt Creek) | 2025-07-09 09:00 | 2025-07-22 16:00 | N | N |  | Switch |  |  | Firm Load Loss, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek) | 2025-07-09 11:00 | 2025-07-09 11:30 | N | Y |  | Line |  |  | Pre-Condition
ATCO | 826s 904 (826s Marguerite Lake) | 2025-07-09 12:01 | 2025-07-10 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 510s 2052 (510s Sunnybrook) | 2025-07-09 15:31 | 2025-07-09 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, For Information Only
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-09 16:30 | 2025-07-09 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 767L (767AL tap - 767CL tap) | 2025-07-10 07:00 | 2025-07-10 15:00 | N | N |  | Line |  |  | Pre-Condition, Affects Cranking Path
PR, ALTALINK | 306s Halsbury, 949L (275s Jenner - 306s Halsbury), 275s 949 (275s Jenner) | 2025-07-10 07:00 | 2025-07-13 18:00 | N | Y |  | Station, Line, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 55s T1 (55s Olds) | 2025-07-10 08:00 | 2025-07-10 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 133L (234L tap - 522L tap), 866s T1 (866s Sundance Make-Up), 868s T1 (868s Keephills Make-Up), 866s 1 (866s Sundance Make-Up), 868s 1 (868s Keephills Make-Up) | 2025-07-10 08:00 | 2025-07-10 16:00 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ALTALINK | 199L (347s AML Fox Creek - 199AL tap), 347s 199E (347s AML Fox Creek) | 2025-07-11 07:00 | 2025-07-17 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 767L (320p Keephills - 767CL tap), 320p 767N (320p Keephills) | 2025-07-11 07:00 | 2025-07-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove), 99s 712X (99s North St. Albert), 595s 712 (595s Spruce Grove) | 2025-07-12 07:00 | 2025-07-13 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.1C (SS-14), 14.2C (SS-14) | 2025-07-12 08:00 | 2025-10-07 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 2.1TR (SS-2) | 2025-07-13 09:00 | 2025-07-15 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72VN21 (EP 511s Victoria - Namao), EP 511s V728 (EP 511s Victoria), EP 511s V729 (EP 511s Victoria), N725 (Namao), NDS5 (Namao), EP 511s VDS16 (EP 511s Victoria) | 2025-07-14 07:00 | 2025-07-24 17:30 | N | N |  | Line, Circuit Breaker, Switch |  | Returned early | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 681s T1 (681s Bannerman) | 2025-07-14 07:00 | 2025-07-17 14:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 754L (437s Baymag - 742L tap) | 2025-07-14 07:00 | 2025-07-14 15:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 14B138-14.83 (SS-14), 36B138-14.83 (SS-36) | 2025-07-14 08:00 | 2025-08-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 799s 138kV Bus (799s Coleman), 170L (632s Russell - 799s Coleman), 799s T3 (799s Coleman) | 2025-07-14 08:00 | 2025-07-14 09:00 | N | Y |  | Bus, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | 5L96 (BCH Selkirk - BCH Vaseux Lake) | 2025-07-14 09:00 | 2025-07-18 17:00 | N | Y |  | Line | 5L96 (Selkirk - Vaseux Lake) |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-07-14 09:00 | 2025-07-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L133 (786s High Level - 828s Sulphur Point), 828s 703 (828s Sulphur Point), 786s 704 (786s High Level) | 2025-07-14 09:00 | 2025-07-15 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 826s 907 (826s Marguerite Lake) | 2025-07-14 09:00 | 2025-07-15 16:00 | N | Y |  | Circuit Breaker |  | RTS Early | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), 657s SU2403 (657s Summerside), 657s SU2404 (657s Summerside), 657s SUDS10 (657s Summerside) | 2025-07-14 09:30 | 2025-07-25 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L89 (700s Bonnyville - 721s La Corey), 700s 703 (700s Bonnyville) | 2025-07-14 10:30 | 2025-07-17 15:30 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 338s 452 (338s Cherhill) | 2025-07-14 11:30 | 2025-07-14 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Impacts RAS
ALTALINK | 17s T3 (17s Benalto), 17s 2852 (17s Benalto) | 2025-07-14 12:30 | 2025-07-16 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 151s C1 (151s Strathmore) | 2025-07-14 12:30 | 2025-07-17 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 725AL (618s Riverbend - 725L tap), 618s 725 (618s Riverbend) | 2025-07-14 12:30 | 2025-07-16 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 140s T1 (140s Thompson), 140s 152 (140s Thompson) | 2025-07-14 14:00 | 2025-07-17 15:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 37s T6 (37s North Calder), 37s 4 (37s North Calder) | 2025-07-15 07:30 | 2025-07-15 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 2081s 701T (2081s Meadow Creek), 7LA183 (2081s Meadow Creek - 7L183 tap) | 2025-07-15 08:00 | 2025-07-17 19:00 | N | N |  | Transformer, Line |  |  | For Information Only
ALTALINK | 510s 1952 (510s Sunnybrook) | 2025-07-15 08:00 | 2025-07-16 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV
ALTALINK | 338s 152 (338s Cherhill) | 2025-07-15 08:30 | 2025-07-15 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-15 09:00 | 2025-07-15 09:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 799s T3 (799s Coleman) | 2025-07-15 09:00 | 2025-07-17 08:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-15 16:30 | 2025-07-15 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ATCO | 7L16 (766s Nevis - 948s Heatburg), 766s 702 (766s Nevis), 948s 703 (948s Heatburg) | 2025-07-16 07:00 | 2025-07-19 19:00 | N | N |  | Line, Circuit Breaker |  | work done early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
NWE | 2366 (NWE Marias) | 2025-07-16 07:00 | 2025-12-01 23:55 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK, AESO-SC | 454s Buck Lake, 454s 138kV Bus (454s Buck Lake), 835L (283s Violet Grove - 835AL tap), 835L (384s Keystone - 835AL tap), 835AL (454s Buck Lake - 835L tap), 454s T1 (454s Buck Lake), 454s T2 (454s Buck Lake), 283s 835E (283s Violet Grove), 384s 835X (384s Keystone), 454s 835A (454s Buck Lake), 454s 1152 (454s Buck Lake), 454s 2134 (454s Buck Lake), 454s LOAD (454s Buck Lake), 454s 1652 (454s Buck Lake), 454s 4009 (454s Buck Lake), 454s 3400 (454s Buck Lake), 454s 19 (454s Buck Lake), 454s 18 (454s Buck Lake), 454s 16 (454s Buck Lake), 454s 17 (454s Buck Lake) | 2025-07-16 07:00 | 2025-07-24 17:00 | N | N |  | Station, Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
NWE, BHE Canada, BHE | Hay Lake (NorthWestern Energy) - Marias (MATL), North Series Capacitor (BHE Hay Lake) | 2025-07-16 07:00 | 2025-07-16 13:00 | N | Y |  | Line, Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 786L (799s Coleman - BCH Natal), 799s 1 (799s Coleman), 799s 786W (799s Coleman) | 2025-07-16 08:00 | 2025-07-17 08:00 | N | Y |  | Line, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Syncrude | Mildred T6 (Syncrude Mildred Lake), 635 (Syncrude Mildred Lake), 6335 (Syncrude Mildred Lake), 634 (Syncrude Mildred Lake) | 2025-07-16 08:00 | 2025-07-20 16:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ALTALINK | 338s T2 (338s Cherhill) | 2025-07-16 08:30 | 2025-07-17 17:30 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ENMAX | 2.2TR (SS-2) | 2025-07-16 09:00 | 2025-07-18 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s C2 (38s East Edmonton) | 2025-07-16 09:00 | 2025-07-17 16:00 | N | N |  | Shunts |  |  | Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-16 09:00 | 2025-07-16 09:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant), 250p 1 (250p Bighorn Plant) | 2025-07-16 10:00 | 2025-07-16 14:00 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
ATCO | 826s 908 (826s Marguerite Lake) | 2025-07-16 12:01 | 2025-07-18 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-16 16:30 | 2025-07-16 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
EPCOR | T4 (Rossdale) | 2025-07-17 | 2025-07-17 04:00 | N | N |  | Transformer |  |  | For Information Only
SUNCOR | 29PL6-1 (30EDD-1 - 29EDD-55), 30EDD-1 29PL6-1CS (30EDD-1) | 2025-07-17 08:00 | 2025-08-02 20:00 | N | N |  | Line, Switch |  | Outage extended | For Information Only
ALTALINK | 799s 138kV Bus (799s Coleman), 786L (799s Coleman - BCH Natal), 799s T1 (799s Coleman), 799s 786W (799s Coleman) | 2025-07-17 08:00 | 2025-07-30 15:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker |  | WebOMS Outage ID : 18278771 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C3 (74s Janet) | 2025-07-17 08:30 | 2025-08-27 14:45 | N | Y |  | Shunts |  | Cap is now available. | 240 kV, For Information Only
RESC | 516s T2 (516s Forty Mile), 516s 240CB2 (516s Forty Mile), 516s 5CAPCB2 (516s Forty Mile), 516s 35CB4 (516s Forty Mile), 516s 35CB5 (516s Forty Mile), 516s 35CB6 (516s Forty Mile) | 2025-07-17 09:00 | 2025-07-17 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant), 250p 2 (250p Bighorn Plant) | 2025-07-17 10:00 | 2025-07-17 14:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 632s PS1 (632s Russell), 632s 452 (632s Russell), 632s 552 (632s Russell) | 2025-07-17 14:11 | 2025-07-22 08:59 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ENMAX | 22B138-22BT8 (SS-22) | 2025-07-18 08:00 | 2025-07-18 12:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.81L (SS-22 - SS-39), 39B138-22.81 (SS-39), 22B138-22.81 (SS-22) | 2025-07-18 12:00 | 2025-07-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L15 (834s Wesley Creek - 876s Brintnell) | 2025-07-18 18:00 | 2025-07-26 13:48 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 1080L (SS-25 - SS-65), 65B240-D132 (SS-65), 65B240-D131 (SS-65), 65MD240-1080 (SS-65) | 2025-07-19 08:00 | 2025-07-19 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
CNRL | 641s 701T (641s Primrose East) | 2025-07-21 07:00 | 2025-07-28 18:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T2 (EP Riverview), RW2403 (EP Riverview), RW2402 (EP Riverview), RWAB2 (EP Riverview) | 2025-07-21 07:00 | 2025-07-25 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 805s C1 (805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s J2403 (EP 805s Jasper), EP 805s JDS25 (EP 805s Jasper) | 2025-07-21 07:00 | 2025-08-08 17:00 | N | Y |  | Line, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | G725 (Garneau) | 2025-07-21 07:00 | 2025-07-21 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 244s C2 (244s Bowmanton) | 2025-07-21 07:30 | 2025-07-24 16:30 | N | Y |  | Shunts |  | Returned early | 240 kV, Pre-Condition
ALTALINK | 244s C3 (244s Bowmanton) | 2025-07-21 07:30 | 2025-07-24 16:30 | N | Y |  | Shunts |  | Returned early | 240 kV, Pre-Condition
ALTALINK | 244s C1 (244s Bowmanton) | 2025-07-21 07:30 | 2025-07-24 16:30 | N | Y |  | Shunts |  | Returned early | 240 kV, Pre-Condition
ALTALINK | 1042L (485s Blackspring Ridge - 554s Travers), 554s 1042 (554s Travers) | 2025-07-21 08:00 | 2025-07-21 18:00 | N | Y |  | Line, Switch |  |  | 240 kV, For Information Only, Restricts Generation
ENMAX | 32B138-32BT5 (SS-32) | 2025-07-21 08:00 | 2025-07-21 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 786L (799s Coleman - BCH Natal), 799s 786W (799s Coleman) | 2025-07-21 08:00 | 2025-07-25 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 23.4TR (SS-23) | 2025-07-21 08:00 | 2025-07-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 658L (562s Cypress - 658AL tap), 658L (649s Chappice Lake - 658AL tap), 662s 138CB1 (662s Hilda) | 2025-07-21 08:00 | 2025-07-21 11:29 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
SUNCOR | 30PL2-1 (30EDD-1 - 30EDD-2) | 2025-07-21 08:00 | 2025-07-31 20:00 | N | N |  | Line |  |  | Restricts Generation
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2025-07-21 08:00 | 2025-07-24 16:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-07-21 09:00 | 2025-07-24 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 2L294 (BCH A. A. Lambert - BCH Nelway) | 2025-07-21 09:00 | 2025-07-31 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s 901T (2075s Newell), 2075s ACF11 (2075s Newell), 2075s ACF12 (2075s Newell), 2075s ACF13 (2075s Newell), 2075s ACF14 (2075s Newell) | 2025-07-21 09:00 | 2025-08-01 08:30 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Pre-Condition, Prevents Normal Events
ATCO | 7L31 (732s Mitsue - 844s AEC MILL), 732s 701 (732s Mitsue), 732s 706 (732s Mitsue), 844s 704 (844s AEC Mill) | 2025-07-21 09:00 | 2025-08-03 14:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 2029s ACF11 (2029s Heathfield), 2029s 1218 (2029s Heathfield) | 2025-07-21 09:00 | 2025-07-23 12:00 | N | Y |  | Shunts, Switch |  |  | 500 kV, Pre-Condition
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek), 809s 704 (809s Louise Creek), 739s 701 (739s Edith Lake) | 2025-07-21 09:30 | 2025-07-22 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 658L (649s Chappice Lake - 658AL tap) | 2025-07-21 11:30 | 2025-07-24 15:30 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Overload, Pre-Condition
ATCO | 2011s 901T (2011s Dawes) | 2025-07-21 12:00 | 2025-07-24 16:00 | N | Y |  | Transformer |  |  | 240 kV, Firm Load Loss, Pre-Condition
ALTALINK | 3L (245s Seebe - 3AL tap), 245s 3E (245s Seebe) | 2025-07-21 12:30 | 2025-07-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2025-07-21 16:00 | 2025-07-21 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark), G721 (Garneau), G726 (Garneau) | 2025-07-22 07:00 | 2025-07-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ENEL | 7L65 (709s Vegreville - 7LA65 tap), 7LA65 tap, 7L65 (710s Vermilion - 7LA65 tap), 708s T1 (708s Grizzly Bear), 710s 703 (710s Vermilion), 708s 52T1 (708s Grizzly Bear), 708s 89-L1 (708s Grizzly Bear), 708s 89M1 (708s Grizzly Bear), 709s 703 (709s Vegreville) | 2025-07-22 07:00 | 2025-07-23 16:00 | N | Y |  | Line, Station, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9B138-9.80 (SS-9), 31B138-9.80 (SS-31) | 2025-07-22 08:00 | 2025-07-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 6.80L (SS-6 - SS-35), 6B138-6.80 (SS-6) | 2025-07-22 08:00 | 2025-07-22 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 510s 2852 (510s Sunnybrook) | 2025-07-22 08:00 | 2025-07-23 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
Syncrude | ML1 (D05 - Syncrude Mildred Lake), T2 (D05 Syncrude), ML-3 (D05), D05 75 (D05), D05 76 (D05), D05 77 (D05), D05 78 (D05), 915 (Syncrude Mildred Lake), D05 513 (D05), D05 516 (D05), D05 78A (D05), D05 78B (D05), D05 77B (D05), D05 77A (D05), D05 513A (D05), D05 76B (D05), D05 76A (D05), D05 75B (D05), 916 (Syncrude Mildred Lake), D05 516A (D05) | 2025-07-22 08:00 | 2025-07-30 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  | Completed early. Was scheduled to return July.31/25 | For Information Only
ALTALINK | 846L (127s Bruderheim - 365s Canadianoxy Astotin Creek), 365s T1 (365s Canadianoxy Astotin Creek), 365s 1 (365s Canadianoxy Astotin Creek), 365s 846N (365s Canadianoxy Astotin Creek), 127s 846X (127s Bruderheim), 127s 26 (127s Bruderheim), 127s 25 (127s Bruderheim) | 2025-07-22 08:00 | 2025-07-25 17:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 263s C1 (263s Strachan) | 2025-07-22 08:30 | 2026-03-17 09:00 | N | N |  | Shunts |  | Returned to service from a forced outage | Pre-Condition
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2025-07-22 08:30 | 2025-07-22 13:30 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
ATCO | 940s 702T (940s Beartrap), 940s 702 (940s Beartrap) | 2025-07-22 09:00 | 2025-07-23 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-22 09:00 | 2025-07-22 09:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-22 09:00 | 2025-07-23 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ATCO | 861S 602T (861S Eurekariver), 861S 602 (861s Eureka River) | 2025-07-22 09:30 | 2025-07-24 16:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 356s 452 (356s Milo) | 2025-07-22 10:30 | 2025-07-22 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ENBRIDGE | 485s 35DSTAT1 (485s Blackspring) | 2025-07-22 12:30 | 2026-05-25 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 708L (71s Lamoureux - 708AL tap) | 2025-07-22 13:31 | 2025-07-22 18:30 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-22 16:30 | 2025-07-22 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 510s ACF21 (510s Sunnybrook) | 2025-07-23 07:00 | 2025-07-23 14:00 | N | Y |  | Shunts |  | done early | Pre-Condition
ALTALINK | 3L (245s Seebe - 3AL tap), 245s 3E (245s Seebe) | 2025-07-23 08:30 | 2025-07-23 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 37s 726E (37s North Calder) | 2025-07-23 08:30 | 2025-07-23 13:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-23 09:00 | 2025-07-23 09:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
BCH | 2L294 (BCH A. A. Lambert - BCH Cranbrook), T3 (BCH Cranbrook) | 2025-07-23 09:00 | 2025-07-31 17:00 | N | Y |  | Line, Transformer |  |  | Pre-Condition
ATCO | 809s 901T (809s Louise Creek), 809s 701 (809s Louise Creek) | 2025-07-23 09:30 | 2025-07-24 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 770s 705C (770s Three Hills) | 2025-07-23 09:30 | 2025-07-23 14:30 | N | N |  | Shunts |  | done early | Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe), 48s 777N (48s Pocaterra) | 2025-07-23 12:31 | 2025-07-23 18:00 | N | Y |  | Line, Circuit Breaker, Switch | Notes for OC: 1. Ensure the ' To Adjacent RC' flag is selected for this outage to show on the Report for Adjacent RC. 2. Ensure the Outage Category is set as 'Interconnection' and Interconnection 'AB-BC' is selected for this outage to show on the interconnection report. 3. Ensure WebOms entry is done. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 2029s ACF21 (2029s Heathfield) | 2025-07-23 13:00 | 2025-07-25 17:30 | N | Y |  | Shunts |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 235s 744W (235s Entwistle), 744L (235s Entwistle - 744AL tap) | 2025-07-23 13:00 | 2025-07-23 14:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 38s 761N (38s East Edmonton) | 2025-07-23 13:31 | 2025-07-23 18:30 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 228s 744 (228s T.M.P.L. Niton), 744L (228s T.M.P.L. Niton - 744AL tap) | 2025-07-23 14:31 | 2025-07-23 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-07-23 16:30 | 2025-07-23 17:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 744L (228s T.M.P.L. Niton - 744AL tap), 744L (235s Entwistle - 744AL tap), 106s T1 (106s Paddle River), 235s 744W (235s Entwistle), 228s 744 (228s T.M.P.L. Niton), 106s 744 (106s Paddle River) | 2025-07-24 07:00 | 2025-07-25 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 20.82L (SS-20 - SS-21), 21B138-20.82 (SS-21) | 2025-07-24 08:00 | 2025-07-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 809s 503R (809s Louise Creek) | 2025-07-24 09:30 | 2025-07-24 12:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 861s 603C (861s Eureka River) | 2025-07-24 09:30 | 2025-07-25 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 2011s 708 (2011s Dawes) | 2025-07-24 10:00 | 2025-07-24 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 809s 504R (809s Louise Creek) | 2025-07-24 12:01 | 2025-07-24 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 658L (562s Cypress - 658AL tap), 658L (649s Chappice Lake - 658AL tap), 658AL (662s Hilda - 658AL tap) | 2025-07-24 15:31 | 2025-07-24 18:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 732s 901T (732s Mitsue) | 2025-07-25 08:30 | 2025-07-25 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 809s 705 (809s Louise Creek), 7L55 (743s Sarah Lake - 809s Louise Creek) | 2025-07-25 09:30 | 2025-07-25 12:30 | N | N |  | Circuit Breaker, Line |  |  | For Information Only
EPCOR | T2 (EP Riverview) | 2025-07-25 17:01 | 2026-04-17 17:00 | N | Y |  | Transformer |  | outage extended. waiting on parts. | 240 kV
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 16B69-16.63 (SS-16), 36B69-16.63/36.5TR (SS-36) | 2025-07-26 08:00 | 2025-07-26 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | EP 511s Victoria T3 (EP 511s Victoria), EP 511s Victoria T4 (EP 511s Victoria) | 2025-07-27 04:00 | 2025-07-27 07:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), RV722 (Rossdale), EP 511s VDS9 (EP 511s Victoria) | 2025-07-28 07:00 | 2025-07-31 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | H722 (EP Hardisty) | 2025-07-28 07:00 | 2025-07-28 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2025-07-28 08:00 | 2025-07-31 16:00 | N | N |  | Line |  |  | Overload, Pre-Condition
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2025-07-28 08:00 | 2025-08-11 06:00 | N | Y |  | Transformer |  |  | Restricts Generation
ENMAX | 162B240-RB133 (SS-162) | 2025-07-28 08:00 | 2025-07-28 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet), 74s 104 (74s Janet) | 2025-07-28 08:30 | 2025-07-29 16:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 2029s ACF12 (2029s Heathfield), 2029s 1219 (2029s Heathfield) | 2025-07-28 09:00 | 2025-07-30 12:00 | N | Y |  | Shunts, Circuit Breaker |  |  | 500 kV, Pre-Condition, Prevents Normal Events
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain) | 2025-07-28 09:00 | 2025-07-30 16:00 | N | Y |  | Line |  | Returned early | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 256s C1 (256s Harmattan) | 2025-07-28 09:00 | 2025-07-30 17:00 | N | N |  | Shunts |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-07-28 09:00 | 2025-07-31 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 809s 902T (809s Louise Creek), 809s 910 (809s Louise Creek), 809s 911 (809s Louise Creek), 809s 702 (809s Louise Creek), 809S 902TD (809s Louise Creek), 809S 910A (809s Louise Creek) | 2025-07-28 09:30 | 2025-07-30 13:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  | Completed early. Was scheduled to return July.31/25 | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 2091s 701T (2091s Thornton) | 2025-07-28 09:30 | 2025-07-31 17:30 | N | N |  | Transformer |  |  | Pre-Condition
ALTALINK, EPCOR | 1059L (EP 803s Lambton - 1059AL tap), 1059L (38s East Edmonton - 1059AL tap), 52s T1 (52s East Industrial), EP 803s L2401 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), 52s E2401 (52s East Industrial) | 2025-07-28 09:30 | 2025-08-08 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2025-07-28 10:00 | 2025-07-31 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L110 (774s Monitor - 903s Loyalist), 774s 706 (774s Monitor) | 2025-07-28 10:00 | 2025-07-30 17:30 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ATCO | 903s 701 (903s Loyalist), 903s 701T (903s Loyalist) | 2025-07-28 10:00 | 2025-07-30 17:30 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 801L (62s Brazeau Plant - 294s Brazeau Plant Outlet Works), 62s 201 (62s Brazeau Plant) | 2025-07-28 10:00 | 2025-07-28 14:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 7L89 (721s La Corey - 826s Marguerite Lake) | 2025-07-28 10:30 | 2025-07-31 15:30 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 718s 704 (718s Parsons Creek), 718s 701T (718s Parsons Creek) | 2025-07-28 12:00 | 2025-07-30 08:59 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 71s T2 (71s Lamoureux) | 2025-07-28 12:00 | 2025-07-31 17:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 405s C1 (405s Waupisoo) | 2025-07-28 12:30 | 2025-07-31 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 172L (254s Coaldale - 370s North Lethbridge), 254s 172W (254s Coaldale), 370s 172E (370s North Lethbridge) | 2025-07-28 12:30 | 2025-07-29 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 159s T1 (159s Colinton) | 2025-07-28 12:30 | 2025-07-29 15:05 | N | N |  | Transformer |  | Came back on July 29 | For Information Only
ALTALINK | 28s 47 (28s West Brooks) | 2025-07-28 12:30 | 2025-07-29 16:30 | N | N |  | Circuit Breaker |  | back early | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 510s 3552 (510s Sunnybrook) | 2025-07-29 08:00 | 2025-07-30 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK, TRANSALTA | 33s 2 (33s Spray), 33s T2 (33s Spray) | 2025-07-29 08:00 | 2025-09-25 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | Restricts Generation
ENMAX | 37.3TR (SS-37) | 2025-07-29 08:00 | 2025-07-29 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L70 (700s Bonnyville - 707s St. Paul), 707s 704 (707s St. Paul), 700s 701 (700s Bonnyville) | 2025-07-29 08:30 | 2025-07-30 16:00 | N | N |  | Line, Circuit Breaker |  | Completed early. Was scheduled to return July.31/25 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 17s T3 (17s Benalto) | 2025-07-29 11:30 | 2025-07-29 17:30 | N | Y |  | Transformer |  |  | For Information Only
ALTALINK, ENBRIDGE | 741L (216s Knightsbridge - 317s Baseline), 317s T1 (317s Baseline), 317s T2 (317s Baseline), 317s 1 (317s Baseline), 317s 7 (317s Baseline), 216s 741X (216s Knightsbridge) | 2025-07-30 07:00 | 2025-07-30 23:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | For Information Only
SUNCOR | 29EDD-71 29PT-105 (29EDD-71), 29EDD-71 752-4642 (29EDD-71), 29EDD-71 752-4644 (29EDD-71), 29EDD-71 29PS-259 (29EDD-71 Edd71Sub) | 2025-07-30 08:00 | 2025-08-05 15:00 | N | N |  | Transformer, Circuit Breaker, Switch |  | done early | For Information Only
ALTALINK | 510s 2252 (510s Sunnybrook), 510s ACF22 (510s Sunnybrook) | 2025-07-30 08:00 | 2025-07-30 17:00 | N | Y |  | Circuit Breaker, Shunts |  | Returned early | 500 kV, Pre-Condition
ENMAX | 15B69-15.62 (SS-15), 15.62L (SS-15 - SS-16) | 2025-07-30 08:00 | 2025-07-31 16:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 893L (312s Fidler - 893AL tap) | 2025-07-30 08:00 | 2025-07-30 16:00 | N | Y |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L170 (875s Algar - 2011s Dawes), 875s 702 (875s Algar) | 2025-07-30 09:00 | 2025-07-30 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 718s 702T (718s Parsons Creek), 718s 705 (718s Parsons Creek) | 2025-07-30 09:00 | 2025-07-31 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 395s 701X (395s North Holden), 701L (223s Strome - 395s North Holden) | 2025-07-30 09:30 | 2025-07-30 17:00 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 103s 652 (103s Goose Lake) | 2025-07-30 10:00 | 2025-07-30 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 888AL (234s Fort Assiniboine - 7L230 tap), 234s 888 (234s Fort Assiniboine), 234s T1 (234s Fort Assiniboine), 234s T2 (234s Fort Assiniboine) | 2025-07-30 10:30 | 2025-07-30 16:30 | N | N |  | Line, Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 2029s ACF22 (2029s Heathfield) | 2025-07-30 13:00 | 2025-08-01 08:30 | N | Y |  | Shunts |  |  | Pre-Condition
ALTALINK, BCH | 799s T1 (799s Coleman), 799s 138kV Bus (799s Coleman), 786L (799s Coleman - BCH Natal), 799s 786W (799s Coleman), 1D24 (BCH Natal) | 2025-07-30 14:00 | 2025-08-19 18:00 | N | Y |  | Transformer, Bus, Line, Circuit Breaker, Switch | Notes for OC: 1. Ensure the ' To Adjacent RC' flag is selected for this outage to show on the Report for Adjacent RC. 2. Ensure the Outage Category is set as 'Interconnection' and Interconnection 'AB-BC' is selected for this outage to show on the interconnection report. 3. Ensure WebOms entry is done. |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, Travers2SolarLP | 1005AL (991s Little Bow - 1005L tap), 991s Little Bow, 991s 240-1 (991s Little Bow) | 2025-07-30 21:30 | 2025-08-01 04:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 17s 1652 (17s Benalto) | 2025-07-31 08:00 | 2025-07-31 17:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 1.8TR (SS-1) | 2025-07-31 08:00 | 2025-08-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 262s 717E (262s Rocky Mountain House) | 2025-07-31 08:30 | 2025-07-31 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L12 (774s Monitor - 6L25 tap), 774s 701T (774s Monitor), 774s 707 (774s Monitor), 774s 601 (774s Monitor) | 2025-07-31 10:00 | 2025-07-31 14:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 138s R2 (138s Windy Flats) | 2025-07-31 10:00 | 2025-07-31 16:30 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
EPCOR | T1 (Rossdale) | 2025-08-01 | 2025-08-01 04:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B138-RB83 (SS-162) | 2025-08-01 08:00 | 2025-08-01 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ACCIONA, ENBRIDGE, ICPCL | 139s C1 (139s Hillridge) | 2025-08-01 08:36 | 2025-08-15 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 294s T2 (294s Brazeau Outlet Works) | 2025-08-01 10:00 | 2025-09-02 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 9L15 (834s Wesley Creek - 876s Brintnell) | 2025-08-01 15:00 | 2025-08-04 18:00 | N | Y |  | Line |  | Back in service | 240 kV, Contingency Requires Mitigation
ENMAX | 1.82L (SS-1 - SS-5), 5.1TR (SS-5), 5.6TR (SS-5), 5.8TR (SS-5), 5B138-1.82 (SS-5), 5B138-5BT12 (SS-5), 5B138-5BT7 (SS-5) | 2025-08-02 08:00 | 2025-08-02 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 827s SVC (827s Cranberry Lake) | 2025-08-02 23:30 | 2025-11-19 12:20 | N | Y |  | Shunts |  | delayed | Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 1.84L (SS-1 - SS-5), 5.7TR (SS-5), 5.5TR (SS-5), 5B138-5BT7 (SS-5), 5B138-1.84 (SS-5), 5B138-2.82 (SS-5), 5MD138-5.5TR (SS-5), 5MD138-5.7TR (SS-5) | 2025-08-03 08:00 | 2025-08-03 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Overload, Pre-Condition
ATCO | 7L162 (729s Otauwau - 732s Mitsue), 732s 705 (732s Mitsue), 732s 706 (732s Mitsue), 729s 704 (729s Otauwau), 732s 7L162D1 (732s Mitsue) | 2025-08-03 14:01 | 2025-08-18 14:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 930s SVC (930s Arcenciel), 930s 701T (930s Arcenciel) | 2025-08-03 16:30 | 2025-08-08 18:00 | N | Y |  | Shunts, Transformer |  |  | Pre-Condition
EPCOR | 72RV4 (EP 511s Victoria - Rossdale), RV726 (Rossdale) | 2025-08-05 07:00 | 2025-08-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s GT2 (987s Clover Bar), 987s CC13 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CGB2 (987s Clover Bar), 987s CK725 (987s Clover Bar), 987s 72kV Bus 2 (987s Clover Bar) | 2025-08-05 07:00 | 2025-08-07 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Bus |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | EP 511s Victoria T4 (EP 511s Victoria), EP 511s V725 (EP 511s Victoria), EP 511s V726 (EP 511s Victoria), EP 511s VAB4 (EP 511s Victoria) | 2025-08-05 07:00 | 2025-08-09 15:00 | N | N |  | Transformer, Circuit Breaker, Switch |  | Finished early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark), G726 (Garneau), G721 (Garneau), M725 (Meadowlark), GDS17 (Garneau) | 2025-08-05 07:00 | 2025-08-09 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L03 (731s Elmworth - 7L09 tap) | 2025-08-05 08:00 | 2025-08-06 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 23B138-2.80 (SS-23) | 2025-08-05 08:00 | 2025-08-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2025-08-05 08:00 | 2025-08-11 09:59 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-08-05 09:00 | 2025-08-07 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L52 (BPA Custer - BCH Ingledow) | 2025-08-05 09:00 | 2025-08-08 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 2029s ACF13 (2029s Heathfield), 2029s 1220 (2029s Heathfield) | 2025-08-05 09:00 | 2025-08-06 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 500 kV
ATCO | 801s 912 (801s Anderson) | 2025-08-05 09:30 | 2025-08-07 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 931s 702T (931s Bohn), 931s 702 (931s Bohn) | 2025-08-05 13:00 | 2025-08-08 10:00 | N | N |  | Terminal Equipment, Circuit Breaker |  |  | For Information Only
ATCO | 7L85 (803s ATC Bullpound - 7LA85 tap) | 2025-08-05 13:00 | 2025-08-06 17:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, BHE | 879L (244s Bowmanton - 879AL tap), 879L (368s Burdett - 879L tap), 368s 879 (368s Burdett), 719s 138CB1 (719s Rattlesnake Ridge), 719s 138MDS1 (719s Rattlesnake Ridge) | 2025-08-06 07:00 | 2025-08-07 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, EPCOR | 1139L (367s Harry Smith - EP Riverview) | 2025-08-06 07:00 | 2025-08-06 18:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 434L (65s High River - 237s Foothills), 65s 434 (65s High River) | 2025-08-06 09:00 | 2025-08-07 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 809s 701C (809s Louise Creek), 809s 709 (809s Louise Creek) | 2025-08-06 09:30 | 2025-08-07 17:00 | N | N |  | Shunts, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 428s T2 (428s Namaka), 428s 652 (428s Namaka) | 2025-08-07 07:30 | 2025-08-07 15:30 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 162B240-RB134 (SS-162) | 2025-08-07 08:00 | 2025-08-07 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 632L (325s Leduc - 538s Buford), 325s 632 (325s Leduc) | 2025-08-07 08:30 | 2025-08-07 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 2029s ACF23 (2029s Heathfield) | 2025-08-07 09:00 | 2025-08-08 17:30 | N | Y |  | Shunts |  |  | Pre-Condition
ATCO | 707s 703 (707s St. Paul), 7L139 (707s St. Paul - 7LA139 tap) | 2025-08-07 09:00 | 2025-08-07 12:00 | N | N |  | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L133 (786s High Level - 828s Sulphur Point), 828s 703 (828s Sulphur Point), 786s 704 (786s High Level) | 2025-08-07 10:00 | 2025-08-11 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L70 (700s Bonnyville - 707s St. Paul), 707s 704 (707s St. Paul) | 2025-08-07 12:01 | 2025-08-07 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 838L (14s Devon - 325s Leduc), 325s 838 (325s Leduc) | 2025-08-07 13:00 | 2025-08-07 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL9-15 (29EDD-34 - 29EDD-56), 29EDD-56 29PT-190 (29EDD-56), 29EDD-56 952-501 (29EDD-56) | 2025-08-08 08:00 | 2025-08-18 20:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 812AL (512s Hartell - 812L tap), 812L (392s Black Diamond - 812AL tap), 812L (65s High River - 812AL tap), 512s T1 (512s Hartell), 392s T3 (392s Black Diamond), 512s 812AL (512s Hartell), 392s 53 (392s Black Diamond), 65s 812W (65s High River) | 2025-08-08 08:00 | 2025-08-13 18:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 41B138-33.83 (SS-41), 33B138-33.83 (SS-33) | 2025-08-08 08:00 | 2025-08-08 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L19 (809s Louise Creek - 851s Morse River), 809s 706 (809s Louise Creek), 851s 702 (851s Morse River) | 2025-08-08 09:30 | 2025-08-08 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.83L (SS-13 - 2.83L tap), 3.84L (SS-3 - SS-13), 13.1TR (SS-13), 13.3TR (SS-13), 13B138-3.84 (SS-13), 13B138-2.83 (SS-13), 13MD138-13.1TR (SS-13), 13MD138-13.3TR (SS-13) | 2025-08-09 08:00 | 2025-08-09 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2025-08-11 | 2025-08-21 17:00 | Y | Y |  | Line |  | Ended early | 500 kV, Limits ATC
EPCOR | EP 803s L2401 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s T1 (EP 803s Lambton), S724 (Strathcona) | 2025-08-11 07:00 | 2025-08-21 17:00 | N | Y |  | Circuit Breaker, Transformer |  | outage extension until Aug. 20 | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
EPCOR | 72VN21 (EP 511s Victoria - Namao), N725 (Namao) | 2025-08-11 07:00 | 2025-08-29 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | EP 511s Victoria T3 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), EP 511s V725 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria) | 2025-08-11 07:00 | 2025-08-22 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ALTALINK, EPCOR | 1045L (EP 805s Jasper - 1045AL tap), 1045L (310p Sundance - 1045AL tap), 1045AL (320p Keephills - 1045L tap), EP 805s J2407 (EP 805s Jasper), EP 805s J2406 (EP 805s Jasper), 320p 1352 (320p Keephills) | 2025-08-11 07:00 | 2025-08-15 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1045AL (320p Keephills - 1045L tap), 1045L (310p Sundance - 1045AL tap), 1045L (EP 805s Jasper - 1045AL tap) | 2025-08-11 07:00 | 2025-08-15 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition, Affects Cranking Path
EPCOR | 72RG1 (Garneau - Rossdale), G724 (Garneau), G725 (Garneau), RG7210 (Rossdale) | 2025-08-11 07:00 | 2025-08-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 657s T1 (657s Summerside), 657s SU2404 (657s Summerside), 657s SU2405 (657s Summerside) | 2025-08-11 07:00 | 2025-08-24 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK, TRANSALTA | 33s 138kV Bus (33s Spray), 33s T1 (33s Spray), 33s T2 (33s Spray), 33s 76 (33s Spray), 33s 113 (33s Spray), 33s 84 (33s Spray), 33s 2 (33s Spray), 33s 1 (33s Spray) | 2025-08-11 08:00 | 2025-08-14 13:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 217s C1 (217s North Red Deer) | 2025-08-11 08:00 | 2025-08-15 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-08-11 09:00 | 2025-08-21 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 802s 703T (802s Michichi Creek), 802s 703 (802s Michichi Creek) | 2025-08-11 09:00 | 2025-08-12 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 514AL tap, 514BL (322s Cowley Ridge Windplant - 514L tap), 514L (513s Lundbreck - 514BL tap), 514L (396s Pincher Creek - 514BL tap), 396s 514N (396s Pincher Creek) | 2025-08-11 09:00 | 2025-08-11 18:00 | N | Y |  | Station, Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ATCO | 7L92 (709s Vegreville - 7LA92 tap), 709s 705 (709s Vegreville) | 2025-08-11 09:30 | 2025-08-14 16:30 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ATCO | 813s 901T (813s Little Smoky) | 2025-08-11 10:00 | 2025-08-14 17:30 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 87s T2 (87s Gaetz) | 2025-08-11 10:30 | 2025-08-14 17:30 | N | Y |  | Transformer |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 876s 902T (876s Brintnell) | 2025-08-11 11:00 | 2025-08-13 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ATCO | 786s 144kV Bus 700BS2 (786s High Level), 786s 702T (786s High Level), 786s 702 (786s High Level), 786s 702TCS (786s High Level) | 2025-08-11 11:00 | 2025-08-12 16:00 | N | N |  | Bus, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L38 (875s Algar - 917s Horse River), 917s 704 (917s Horse River) | 2025-08-11 12:00 | 2025-08-12 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 233s T1 (233s Beamer) | 2025-08-11 12:00 | 2025-08-19 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 405s C2 (405s Waupisoo), 405s 23 (405s Waupisoo) | 2025-08-11 12:30 | 2025-08-14 17:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 410s T2 (410s Josephburg) | 2025-08-11 12:30 | 2025-08-15 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 252s 408 (252s Jarrow), 408L (51s Wainwright - 252s Jarrow) | 2025-08-11 13:30 | 2025-08-12 17:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BSRW | 1019s Woolchester | 2025-08-12 06:00 | 2025-08-12 18:00 | N | Y |  | Station |  |  | Restricts Generation
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), H725 (EP Hardisty), 987s CH724 (987s Clover Bar) | 2025-08-12 07:00 | 2025-08-13 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L56 (720s Wabasca - 876s Brintnell), 876s 902 (876s Brintnell), 876s 904 (876s Brintnell) | 2025-08-12 10:00 | 2025-08-13 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ENMAX | 21.61L (SS-21 - SS-34), 34B69-21.61 (SS-34), 21B69-21.61 (SS-21) | 2025-08-13 08:00 | 2025-08-14 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 767L (310p Sundance - 767AL tap), 310p 767X (310p Sundance) | 2025-08-13 08:00 | 2025-08-13 15:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ATCO | 786s 701TCS (786s High Level), 786s 701T (786s High Level), 786s 505C (786s High Level), 786s 506C (786s High Level) | 2025-08-13 08:30 | 2025-08-14 14:00 | N | N |  | Switch, Transformer, Shunts |  |  | Pre-Condition
ALTALINK | 526s C1 (526s Buffalo Creek) | 2025-08-13 08:30 | 2025-08-14 17:30 | N | N |  | Shunts |  |  | Pre-Condition
SUNCOR | 29PL6-2 (30EDD-1 - 29EDD-55) | 2025-08-13 09:00 | 2025-08-20 20:00 | N | N |  | Line |  |  | For Information Only
ATCO | 7L121 (917s Horse River - 7LA121 tap), 917s 705 (917s Horse River) | 2025-08-13 09:30 | 2025-08-14 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L05 (757s Battle River - 843s Bigknife Creek), 757s 602 (757s Battle River) | 2025-08-13 09:30 | 2025-08-14 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove), 99s 712X (99s North St. Albert), 595s 712 (595s Spruce Grove) | 2025-08-14 06:00 | 2025-08-16 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 21.1C (SS-21) | 2025-08-14 08:00 | 2025-08-21 16:00 | N | N |  | Shunts |  |  | Pre-Condition
SUNCOR | 29EDD-85 752-10020 (29EDD-85) | 2025-08-14 08:00 | 2025-08-19 18:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 20.82L (SS-20 - SS-21), 21.80L (42s Sarcee - SS-21), 21.1TR (SS-21), 21.4TR (SS-21), 21B138-20.82 (SS-21), 21B138-21.80 (SS-21) | 2025-08-14 08:00 | 2025-08-21 16:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21) | 2025-08-14 08:00 | 2025-08-21 16:00 | N | Y |  | Line |  |  | For Information Only
ALTALINK | 33s 3 (33s Spray) | 2025-08-14 14:00 | 2025-09-15 08:30 | N | Y |  | Switch |  |  | Restricts Generation
ALTALINK | 828L (178s Cynthia - 489s Petro-Canada Brazeau River), 178s 828X (178s Cynthia) | 2025-08-16 08:30 | 2025-08-16 14:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane), 291s 860 (291s Cochrane), 44s 860W (44s Bearspaw Plant) | 2025-08-17 06:00 | 2025-08-20 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Garneau), GT2 (Garneau) | 2025-08-18 07:00 | 2025-10-31 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX | 37.2TR (SS-37) | 2025-08-18 08:00 | 2025-08-28 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L56 (738s Virginia Hills - 809s Louise Creek), 809s 707 (809s Louise Creek) | 2025-08-18 08:00 | 2025-08-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO, AIRLIQUIDE | ALC03L (402s Scotford Expansion One - 408s Air Liquide Scotford), 408s 52-A45 (408s Air Liquide Scotford), 408s 52-A51 (408s Air Liquide Scotford) | 2025-08-18 08:00 | 2025-08-20 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK, TRANSALTA | 84L (33s Spray - 35s Rundle Plant), 85L (35s Rundle Plant - 54L tap), 64L (36s Three Sisters Plant - 35s Rundle Plant), 35s T1 (35s Rundle Plant), 35s T2 (35s Rundle Plant), 35s T3 (35s Rundle Plant), 36s T1 (36s Three Sisters Plant), 33s 84 (33s Spray), 35s 84 (35s Rundle Plant), 35s 85 (35s Rundle Plant), 35s 1 (35s Rundle Plant), 35s 52 (35s Rundle Plant), 35s 64 (35s Rundle Plant), 35s 2 (35s Rundle Plant), 35s 3 (35s Rundle Plant), 35s 4 (35s Rundle Plant), 35s 41 (35s Rundle Plant), 35s 8 (35s Rundle Plant), 35s 9 (35s Rundle Plant), 36s 64L42 (36s Three Sisters Plant), 36s 2600S1 (36s Three Sisters Plant), 36s 345S1 (36s Three Sisters Plant), 36s 1 (36s Three Sisters Plant) | 2025-08-18 08:00 | 2025-09-11 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 813s 717 (813s Little Smoky) | 2025-08-18 09:30 | 2025-08-18 14:34 | N | N |  | Circuit Breaker |  | Outage was completed early. | Contingency Requires Mitigation
ATCO | 6L03 (757s Battle River - 6L17 tap), 757s 603 (757s Battle River) | 2025-08-18 09:30 | 2025-08-19 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 801s 911 (801s Anderson) | 2025-08-18 09:30 | 2025-08-21 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 898s 902T (898s Heart Lake), 898s 704 (898s Heart Lake), 898s 708 (898s Heart Lake) | 2025-08-18 11:00 | 2025-08-24 12:00 | N | Y |  | Transformer, Circuit Breaker |  | Returned to service early | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L133 (786s High Level - 828s Sulphur Point), 786s 704 (786s High Level), 828s 703 (828s Sulphur Point) | 2025-08-18 11:00 | 2025-08-19 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 527s T1 (527s Coal Valley) | 2025-08-18 11:00 | 2025-08-18 15:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 917s 706C (917s Horse River) | 2025-08-18 12:00 | 2025-08-19 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 778L (87s Gaetz - 217s North Red Deer), 217s 778E (217s North Red Deer) | 2025-08-18 12:30 | 2025-08-27 11:18 | N | N |  | Line, Circuit Breaker |  | Outage returned early. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 325s T1 (325s Leduc) | 2025-08-18 12:30 | 2025-08-21 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 336s T1 (336s Fincastle), 336s 752 (336s Fincastle) | 2025-08-18 14:00 | 2025-08-22 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 732s 902T (732s Mitsue), 732s 503R (732s Mitsue), 732s 704 (732s Mitsue), 732s 705 (732s Mitsue), 732s 901 (732s Mitsue), 732s 906 (732s Mitsue), 732s 702TD (732s Mitsue), 732s 902TD (732s Mitsue), 732s 906A (732s MItsue), 732s 901A (732s MItsue) | 2025-08-18 14:01 | 2025-09-01 14:00 | N | Y |  | Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 69s T2 (69s North Barrhead), 69s T5 (69s North Barrhead) | 2025-08-19 07:00 | 2025-08-22 17:30 | N | N |  | Transformer |  |  | Pre-Condition
ATCO | 7L16 (766s Nevis - 948s Heatburg), 766s 702 (766s Nevis), 948s 703 (948s Heatburg) | 2025-08-19 07:00 | 2025-08-23 19:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
PR, ALTALINK | 306s Halsbury, 949L (275s Jenner - 306s Halsbury), 275s 949 (275s Jenner) | 2025-08-19 07:00 | 2025-08-22 18:00 | N | Y |  | Station, Line, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 807L (233s Beamer - 807AL tap), 233s 807X (233s Beamer) | 2025-08-19 07:30 | 2025-08-19 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
SUNCOR | 29EDD-56 29PT-191 (29EDD-56), 29PL9-14 (29EDD-34 - 29EDD-56), 29EDD-56 952-1401 (29EDD-56) | 2025-08-19 08:00 | 2025-09-03 20:00 | N | Y |  | Transformer, Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 178s T1 (178s Cynthia) | 2025-08-19 08:30 | 2025-08-27 14:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 325s C1 (325s Leduc) | 2025-08-19 08:30 | 2025-08-19 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis), 766s 902 (766s Nevis) | 2025-08-19 11:30 | 2025-08-21 18:06 | N | Y |  | Line, Circuit Breaker |  | Line returned to service early due to storm damage to system. | 240 kV, Affects Cranking Path
ATCO | 9L912 (63s Red Deer - 766s Nevis), 766s 9L912D1 (766s Nevis), 766s 902 (766s Nevis) | 2025-08-19 12:00 | 2025-08-23 14:00 | N | Y |  | Line, Switch, Circuit Breaker |  | cancel | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 708L (233s Beamer - 708AL tap), 233s 708X (233s Beamer) | 2025-08-20 07:30 | 2025-08-20 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 233s T2 (233s Beamer) | 2025-08-20 08:00 | 2025-08-26 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B240-RB131 (SS-162) | 2025-08-20 08:00 | 2025-08-20 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 29EDD-85 752-10040 (29EDD-85) | 2025-08-20 08:00 | 2025-08-24 18:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 799s 138kV Bus (799s Coleman), 170L (632s Russell - 799s Coleman), 799s T3 (799s Coleman), 799s 170E (799s Coleman) | 2025-08-20 08:00 | 2025-09-01 15:00 | N | Y |  | Bus, Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 731L (420s Broadmoor - 746L tap), 420s 731 (420s Broadmoor) | 2025-08-20 08:00 | 2025-08-26 20:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 786s 703T (786s High Level), 786s 703 (786s High Level), 786s SVC (786s High Level) | 2025-08-20 08:30 | 2025-08-20 16:37 | N | Y |  | Transformer, Circuit Breaker, Shunts |  |  | Pre-Condition
SUNCOR | 29PL9-4 (29EDD-1 Millennium - 29EDD-3), 29EDD-3 29PT-5 (29EDD-3) | 2025-08-20 09:00 | 2025-08-26 20:00 | N | Y |  | Line, Transformer |  |  | Restricts Generation
ATCO | 813s 718 (813s Little Smoky) | 2025-08-20 09:30 | 2025-08-20 15:15 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ATCO | 757s 607C (757s Battle River) | 2025-08-20 09:30 | 2025-08-21 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 917s 703C (917s Horse River) | 2025-08-20 09:30 | 2025-08-21 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 931L (28s West Brooks - 132s Ware Junction) | 2025-08-20 17:00 | 2025-10-11 11:00 | N | Y |  | Line | Sep 25 Update: Removing breakers from isolation zone as AML has confirmed via SCs that the line disconnect will now be used. | Forced | 240 kV, Affects Cranking Path
ALTALINK | 1075L (28s West Brooks - 132s Ware Junction) | 2025-08-20 17:00 | 2025-12-19 17:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
ALTALINK | 853AL (435s Bassano - 853L tap) | 2025-08-20 17:30 | 2025-08-25 15:00 | N | N |  | Line |  |  | For Information Only
ALTALINK | 1075L (28s West Brooks - 132s Ware Junction) | 2025-08-20 17:30 | 2025-08-29 16:59 | N | Y |  | Line |  |  | Affects Cranking Path
ATCO, ALTALINK | 7L760 (7LA760 tap - 7LC760 tap), 760AL (164s Empress Liquids - 760L tap), 760L (163s Amoco Empress - 760AL tap) | 2025-08-20 17:30 | 2025-08-24 10:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2025-08-20 23:00 | 2025-08-21 03:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 62s T2 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant) | 2025-08-21 03:01 | 2025-08-21 07:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ATCO, ALTALINK | ALC01L (408s Air Liquide Scotford - 409s Shell Scotford), 409s 107 (409s Shell Scotford) | 2025-08-21 07:30 | 2025-08-22 16:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 162B240-RB132 (SS-162) | 2025-08-21 08:00 | 2025-08-21 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 951s SVC (951s Thickwood) | 2025-08-21 09:00 | 2025-08-22 17:00 | N | Y |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2025-08-22 07:00 | 2025-08-26 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 60s50 (SS-21) | 2025-08-22 07:00 | 2025-08-26 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ATCO, CNRL | 838s 75-BC-1911 (838s Horizon Mining) | 2025-08-22 08:00 | 2025-08-24 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2075s ACF23 (2075s Newell) | 2025-08-22 09:00 | 2025-08-22 17:30 | N | Y |  | Shunts |  |  | Pre-Condition
EPCOR | 665s T1 (665s Dome), 665s D2401 (665s Dome), 665s D2402 (665s Dome) | 2025-08-23 07:00 | 2025-08-28 11:30 | N | Y |  | Transformer, Circuit Breaker |  | 665s T1 returned early. Aug. 28th | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), EP 805s J2403 (EP 805s Jasper), EP 805s J2404 (EP 805s Jasper) | 2025-08-25 07:00 | 2025-08-29 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO, BluEarth | 7LA128 tap, 572S 144DSW1 (572s Highland), 572S 144CB1 (572s Highland), 7LA128 (572s Highland - 7L128 tap) | 2025-08-25 08:00 | 2025-08-26 18:00 | N | Y |  | Station, Switch, Circuit Breaker, Line |  | Extended | Pre-Condition, Restricts Generation
ENMAX | 32.1TR (SS-32) | 2025-08-25 08:00 | 2026-02-24 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | 13 (Aurora), 13A (Aurora), 13B (Aurora) | 2025-08-25 08:00 | 2025-08-25 16:00 | N | N |  | Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 162B240-RB136 (SS-162) | 2025-08-25 08:00 | 2025-08-25 14:59 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | T1 (BCH Nelway) | 2025-08-25 09:16 | 2025-08-25 16:00 | N | N |  | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 815s 701T (815s Goodfare), 815s 701 (815s Goodfare) | 2025-08-25 09:30 | 2025-08-28 17:30 | N | Y |  | Transformer, Circuit Breaker |  | 815s 701T returned early. Aug. 28 | Pre-Condition, Restricts Generation
ATCO | 730s STATCOM (730s Rycroft), 730s 705 (730s Rycroft), 730s 702T (730s Rycroft) | 2025-08-25 09:30 | 2025-08-29 17:30 | N | Y |  | Shunts, Circuit Breaker, Transformer |  |  | Impacts RAS, Pre-Condition
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2025-08-25 09:30 | 2025-08-26 16:15 | N | Y |  | Line |  |  | For Information Only
ATCO | 757s 702 (757s Battle River), 757s 702T (757s Battle River) | 2025-08-25 09:30 | 2025-08-26 17:30 | N | N |  | Circuit Breaker, Transformer |  |  | Pre-Condition
ATCO | 801s 701T (801s Anderson), 801s 711 (801s Anderson), 801S 701TD (801s Anderson) | 2025-08-25 09:30 | 2025-08-28 17:30 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar), 987s C2403 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s CDS36 (987s Cloverbar) | 2025-08-25 09:30 | 2025-08-26 16:15 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 199s T1 (199s East Airdrie) | 2025-08-25 09:30 | 2025-08-25 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 6L02 (765s Mannix Mine - 873s Marion Lake) | 2025-08-25 10:00 | 2025-08-25 14:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 888s 919C (888s Dover) | 2025-08-25 12:00 | 2025-08-27 17:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ATCO | 917s 701T (917s Horse River), 917s 701 (917s Horse River) | 2025-08-25 12:00 | 2025-08-26 12:00 | N | N |  | Transformer, Circuit Breaker |  | Back early | Pre-Condition
ALTALINK | 294s T1 (294s Brazeau Outlet Works), 294s 1 (294s Brazeau Outlet Works), 294s 2 (294s Brazeau Outlet Works), 294s 24 (294s Brazeau Outlet Works) | 2025-08-26 08:00 | 2025-09-30 17:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ENMAX | 162B240-RB135 (SS-162) | 2025-08-26 08:00 | 2025-08-26 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet), 74s 104 (74s Janet) | 2025-08-26 08:30 | 2025-08-27 14:45 | N | Y |  | Shunts, Circuit Breaker |  | Both caps are now available | 240 kV, Pre-Condition
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-08-26 22:00 | 2025-08-26 22:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek) | 2025-08-27 07:00 | 2025-08-27 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 233s 6 (233s Beamer) | 2025-08-27 07:30 | 2025-08-27 16:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 15.60L (SS-15 - SS-21), 15B69-15.60 (SS-15) | 2025-08-27 08:00 | 2025-08-28 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
TRANSALTA | 528s Blue Trail Wind Farm | 2025-08-27 08:00 | 2025-08-27 16:00 | N | N |  | Station |  |  | Pre-Condition
ATCO | 819s 701 (819s Whitby Lake), 7L92 (777s Vilna - 819s Whitby Lake) | 2025-08-27 09:00 | 2025-08-29 16:00 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 56L (20s Ghost - 245s Seebe), 245s 56E (245s Seebe), 20s 56 (20s Ghost) | 2025-08-28 08:00 | 2025-08-28 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29PL9-24 (29EDD-94 Voyageur - 29EDD-60 Inglis Island), 29EDD-60 29PT-702 (29EDD-60 Inglis Island), 29EDD-60 30-252-400001 (29EDD-60 Inglis Island) | 2025-08-28 08:00 | 2025-10-08 15:45 | N | Y |  | Line, Transformer, Circuit Breaker |  | Completed early | 240 kV, Restricts Generation
ATCO | 848s 602 (848s Ruth Lake) | 2025-08-28 09:00 | 2025-08-29 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
EPCOR | T4 (Rossdale) | 2025-08-29 | 2025-08-29 04:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 2.83L (SS-5 - 2.83L tap), 2.83L (SS-2 - 2.83L tap), 2.83L (SS-13 - 2.83L tap), 5.9TR (SS-5), 5.10TR (SS-5), 5B138-2.83 (SS-5), 5B138-5BT12 (SS-5), 5MD138-5.10TR (SS-5), 5MD138-5.9TR (SS-5) | 2025-08-29 08:00 | 2025-08-29 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 759L (87s Gaetz - 276s Prentiss) | 2025-08-30 07:00 | 2025-09-08 18:00 | N | N |  | Line |  |  | For Information Only
ENMAX | 1.81L (SS-1 - SS-20), 20.1TR (SS-20), 20MD138-20.1TR (SS-20), 20B138-1.81 (SS-20) | 2025-08-31 08:00 | 2025-08-31 12:00 | N | N |  | Line, Transformer, Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 20.82L (SS-20 - SS-21), 20.3TR (SS-20), 20B138-1.81 (SS-20), 20MD138-20.1TR (SS-20) | 2025-08-31 12:01 | 2025-08-31 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 39.2TR (SS-39) | 2025-09-01 08:00 | 2025-10-03 18:00 | N | N |  | Transformer |  | Outage extended due to continued issues when trying to energize. | For Information Only
ATCO | 732s 902T (732s Mitsue), 732s 503R (732s Mitsue) | 2025-09-01 14:01 | 2025-09-15 14:00 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
SUNCOR | 29EDD-71 29PT-235 (29EDD-71), 29EDD-71 752-4642 (29EDD-71), 29EDD-71 752-4641 (29EDD-71), 29EDD-71 29PS-263 (29EDD-71 Edd71Sub) | 2025-09-01 16:00 | 2025-09-13 14:00 | N | N |  | Transformer, Circuit Breaker, Switch |  | Outage extended informed by Suncor | Restricts Generation
EPCOR | EP 803s T2 (EP 803s Lambton), EP 803s L2402 (EP 803s Lambton), EP 803s L2405 (EP 803s Lambton), EP 803s LAB2 (EP 803s Lambton) | 2025-09-02 07:00 | 2025-09-14 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 1036L (356s Milo - 554s Travers) | 2025-09-02 07:00 | 2025-09-10 18:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Namao), N723 (Namao), NAB2 (Namao) | 2025-09-02 07:00 | 2025-09-06 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | For Information Only
EPCOR | 805s T1 (805s Jasper) | 2025-09-02 07:00 | 2025-10-03 17:00 | N | Y |  | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft), W721 (Woodcroft), EP 805s J724 (EP 805s Jasper), EP 805s JDS28 (EP 805s Jasper) | 2025-09-02 07:00 | 2025-10-03 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 557s T2 (557s Castle Downs) | 2025-09-02 07:00 | 2025-10-09 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), AML 511s T11 (AML 511s Crossings), 510s T11 (510s Sunnybrook), AML 511s 4852 (AML 511s Crossings), AML 511s 4952 (AML 511s Crossings), 510s 2652 (510s Sunnybrook), 510s 2752 (510s Sunnybrook), AML 511s 1489 (AML 511s Crossings), AML 511s 74 (AML 511s Crossings), AML 511s 76 (AML 511s Crossings), 510s 41 (510s Sunnybrook), 510s 43 (510s Sunnybrook), 510s 4289 (510s Sunnybrook) | 2025-09-02 07:30 | 2025-09-12 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 500 kV, Overload, Pre-Condition
ENMAX | 38.1C (SS-38) | 2025-09-02 08:00 | 2026-01-14 16:00 | N | N |  | Shunts |  |  | Pre-Condition
Lethbridge | 813L (146s MacDonald - 241s Uplands), 241s 813L (241s Uplands), 146s 813L (146s Macdonald) | 2025-09-02 08:00 | 2025-09-05 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2025-09-02 09:00 | 2025-09-05 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 172s T3 (172s Sherritt Gordon), 172s 73 (172s Sherritt) | 2025-09-02 09:30 | 2025-09-08 17:00 | N | N |  | Transformer, Circuit Breaker |  | Extended by costumer. | For Information Only
ALTALINK | 801L (62s Brazeau Plant - 294s Brazeau Plant Outlet Works), 294s 201 (294s Brazeau Outlet Works) | 2025-09-02 11:00 | 2025-09-02 15:00 | N | Y |  | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK, GLPC | 1055s Sollair, 688L (199s East Airdrie - 688BL tap), 688BL (1055s Sollair - 688L tap), 1055s T1 (1055s Sollair), 199s 688 (199s East Airdrie), 1055s 52-L (1055s Sollair), 1055s 52-1 (1055s Sollair), 1055s 52-2 (1055s Sollair), 1055s 52-3 (1055s Sollair), 1055s 52-4 (1055s Sollair), 1055s 52-5 (1055s Sollair), 1055s 89-L1 (1055s Sollair), 1055s 89-L2 (1055s Sollair) | 2025-09-02 12:00 | 2025-09-02 17:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 859L (20s Ghost - AML 793s Horse Creek), AML 793s 859W (AML 793s Horse Creek), 20s 859E (20s Ghost) | 2025-09-02 13:30 | 2025-09-05 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 71s 138kV East Bus (71s Lamoureux), 71s 240kV East Bus (71s Lamoureux), 71s T2 (71s Lamoureux), 71s 852 (71s Lamoureux), 71s 452 (71s Lamoureux), 71s 1752 (71s Lamoureux), 71s 1452 (71s Lamoureux) | 2025-09-03 07:30 | 2025-09-03 12:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 16B69-16.61 (SS-16) | 2025-09-03 08:00 | 2025-09-11 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L58 (789s Keg River - 905s Meikle), 789s 704 (789s Keg River) | 2025-09-03 08:00 | 2025-09-03 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Affects Cranking Path
ATCO | 951S 907 (951s Thickwood Hills) | 2025-09-03 09:00 | 2025-09-11 08:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 802s 704 (802s Michichi Creek), 7L128 (802s Michichi Creek - 7LA128 tap) | 2025-09-03 09:30 | 2025-09-04 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload
ATCO | 873s 601T (873s Marion Lake), 873s 601 (873s Marion Lake) | 2025-09-03 09:30 | 2025-09-03 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 71s 138kV West Bus (71s Lamoureux), 71s 240kV West Bus (71s Lamoureux), 71s T1 (71s Lamoureux), 921L (71s Lamoureux - 987s Clover Bar), 781L (71s Lamoureux - 172s Sherritt), 71s 252 (71s Lamoureux), 71s 152 (71s Lamoureux), 71s 1352 (71s Lamoureux), 71s 1252 (71s Lamoureux), 71s 1552 (71s Lamoureux) | 2025-09-03 12:01 | 2025-09-03 15:30 | N | Y |  | Bus, Transformer, Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 217s C1 (217s North Red Deer) | 2025-09-03 13:00 | 2025-09-03 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 370s 2152 (370s North Lethbridge), 370s T3 (370s North Lethbridge) | 2025-09-03 13:30 | 2025-09-04 16:30 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Overload, Pre-Condition
ALTALINK, EPCOR | 71s 1552 (71s Lamoureux), 71s 1652 (71s Lamoureux), 920L (71s Lamoureux - 557s Castle Downs) | 2025-09-03 15:31 | 2025-09-03 17:30 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 657s SU2404 (657s Summerside) | 2025-09-04 07:00 | 2025-09-04 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove), 99s 712X (99s North St. Albert), 595s 712 (595s Spruce Grove) | 2025-09-04 07:15 | 2025-09-12 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 71s 552 (71s Lamoureux), 71s 652 (71s Lamoureux), 761L (38s East Edmonton - 71s Lamoureux) | 2025-09-04 07:30 | 2025-09-04 09:30 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.1TR (SS-14) | 2025-09-04 08:00 | 2025-09-04 10:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 263s C1 (263s Strachan) | 2025-09-04 08:30 | 2025-09-04 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 54s C1 (54s Fort Saskatchewan) | 2025-09-04 08:30 | 2025-09-04 13:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 71s 752 (71s Lamoureux) | 2025-09-04 09:31 | 2025-09-04 11:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2025-09-04 10:00 | 2025-09-04 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 71s 352 (71s Lamoureux) | 2025-09-04 11:01 | 2025-09-04 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.3TR (SS-14) | 2025-09-04 12:30 | 2025-09-04 14:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 71s C2 (71s Lamoureux) | 2025-09-04 12:31 | 2025-09-04 14:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 71s C1 (71s Lamoureux) | 2025-09-04 14:01 | 2025-09-04 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 14.4TR (SS-14) | 2025-09-04 14:30 | 2025-09-04 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 452L (367s Harry Smith - 434s Stony Plain), 434s 452 (434s Stony Plain) | 2025-09-05 07:00 | 2025-09-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | G21 (Aurora), T4 (Aurora), 89-224 (Aurora), 221 (Aurora), 222 (Aurora) | 2025-09-05 08:00 | 2025-09-05 14:30 | N | Y |  | Circuit Breaker, Transformer, Switch |  | outage returned early Sept. 5, 2025 | Restricts Generation
ENMAX | 1.85L (SS-1 - SS-8) | 2025-09-05 08:00 | 2025-11-28 16:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 1.83L (SS-1 - SS-8) | 2025-09-05 08:00 | 2025-11-28 16:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2025-09-05 13:00 | 2025-09-12 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 71s 552 (71s Lamoureux), 71s 652 (71s Lamoureux), 38s 761N (38s East Edmonton) | 2025-09-06 07:30 | 2025-09-06 12:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 14.2TR (SS-14), 14.4TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14B138-14.83 (SS-14), 36B138-14.83 (SS-36), SW84 (SS-14), 14MD138-14.1TR (SS-14), 14MD138-14.2TR (SS-14) | 2025-09-07 08:00 | 2025-09-07 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 305s T1 (305s Acheson) | 2025-09-07 08:30 | 2025-09-07 16:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 951s 1205 (951s Thickwood Hills) | 2025-09-07 09:00 | 2025-09-10 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, For Information Only
ALTALINK | 500s T1 (500s Flatbush) | 2025-09-08 07:00 | 2025-09-08 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar), 987s C2402 (987s Clover Bar), 987s C2404 (987s Clover Bar), 987s CDS28 (987s Cloverbar) | 2025-09-08 07:00 | 2025-09-11 12:00 | N | Y |  | Line, Circuit Breaker, Switch |  | Returning Early | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ENMAX | 14.1TR (SS-14) | 2025-09-08 07:00 | 2025-09-17 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR, ALTALINK | 657s T2 (657s Summerside), 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside), 657s SUAB2 (657s Summerside) | 2025-09-08 07:00 | 2025-09-13 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial) | 2025-09-08 07:00 | 2025-09-09 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 734L (241s Uplands - 370s North Lethbridge), 241s 734L (241s Uplands) | 2025-09-08 08:00 | 2025-09-09 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.3TR (SS-8) | 2025-09-08 08:00 | 2025-09-11 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 204s T1 (204s Sandypoint) | 2025-09-08 08:00 | 2025-09-17 13:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-09-08 09:00 | 2025-09-10 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BPA | Monroe-Custer 1 500kV Line (BPA) | 2025-09-08 09:00 | 2025-09-09 16:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
BCH | 5L92 (BCH Cranbrook - BCH Selkirk), T3 (BCH Cranbrook) | 2025-09-08 09:00 | 2025-09-18 20:00 | Y | Y |  | Line, Transformer | *FOR OC** 1. Enter TRMr+ = 466 MW in MARGO manual override 2. Check MARGO BC/MATL capability (ATC). The BC/MATL capability (ATC) = 99 MW (lowest number for the period of Sep 08-18, 2025 (Sep 09, 2025 HE6) 3. In order to show 0 MW on S&D. Using max MATL Import ATC: 310 MW (No Restriction )  15 MW (MATL TRM ) = 295 MW, so the BC import ATC becomes 99 MW  295 MW = -196 MW (enter 0, instead of a negative number). |  | Limits ATC, 500 kV
ATCO | 755s 902 (755s Cordel) | 2025-09-08 09:30 | 2025-09-08 15:30 | N | Y |  | Circuit Breaker |  | back early | 240 kV, Contingency Requires Mitigation
ATCO | 740s 703T (740s H.R.Milner), 740s 507C (740s H.R.Milner), 740s 703 (740s H.R. Milner), 740s 503 (740s H.R. Milner) | 2025-09-08 10:00 | 2025-09-17 10:30 | N | N |  | Transformer, Shunts, Circuit Breaker |  | Return Early. | Pre-Condition
ALTALINK | 359s T1 (359s Esso West Pembina), 359s 202AN (359s Esso West Pembina) | 2025-09-08 12:30 | 2025-09-10 17:30 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 17s 2 (17s Benalto) | 2025-09-08 12:30 | 2025-09-08 16:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 650s 252 (650s Hansman Lake) | 2025-09-09 07:30 | 2025-09-09 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV
ALTALINK | 760L (163s Amoco Empress - 760AL tap) | 2025-09-09 07:30 | 2025-09-10 18:30 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 63s T2 (63s Red Deer), 63s 25 (63s Red Deer) | 2025-09-09 07:30 | 2025-09-09 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 461L (198s Blackfalds - 212s N.E. Lacombe), 198s 461 (198s Blackfalds), 212s 461 (212s N.E. Lacombe) | 2025-09-09 08:00 | 2025-09-09 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 514BL (322s Cowley Ridge Windplant - 514L tap), 514L (513s Lundbreck - 514BL tap), 514L (396s Pincher Creek - 514BL tap) | 2025-09-09 08:00 | 2025-09-09 15:00 | N | Y |  | Line |  |  | Firm Load Loss, Pre-Condition, Restricts Generation
ATCO, ALBIAN | 9LJH2 (919s Hartley - 920s Jackpine), 920s 902T (920s Jackpine), 920s 902 (920s Jackpine), 920s B1 (920s Jackpine), 919s 907 (919s Hartley), 920s 9LJH-2D2 (920s Jackpine) | 2025-09-09 08:00 | 2025-09-16 14:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 142s 138kV Bus (142s Magcan), 727AL (142s Magcan - 727L tap), 142s C1 (142s Magcan) | 2025-09-09 08:30 | 2025-09-10 17:30 | N | N |  | Bus, Line, Shunts |  |  | Pre-Condition
ATCO, ALTALINK | 7L760 (7LA760 tap - 7LC760 tap), 760L (760AL tap - 7LA760 tap), 914s 701 (914s Bindloss), 893s 701 (893s Cavendish), 7L760D4 (7LA760 tap), 7L760D5 (7LA760 tap) | 2025-09-09 09:00 | 2025-09-10 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 650s 352 (650s Hansman Lake) | 2025-09-09 12:30 | 2025-09-09 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-09-09 23:00 | 2025-09-11 07:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow), 397s 720N (397s Benbow), 347s 720X (347s AML Fox Creek) | 2025-09-10 07:00 | 2025-09-10 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-09-10 07:00 | 2025-09-11 07:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 63s 352 (63s Red Deer) | 2025-09-10 07:30 | 2025-09-10 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 601s Buffalo Bird, 7L238 (959s Lanfine - 601s Bufallo Bird), MPT1 (601s Buffalo Bird), 601s 52H-1 (601s Buffalo Bird) | 2025-09-10 08:00 | 2025-09-10 14:00 | N | Y |  | Station, Line, Transformer, Circuit Breaker |  |  | Restricts Generation,Affects Cranking Path
Lethbridge, ALTALINK | 146s 667 (146s Macdonald), 667L (146s MacDonald - 370s North Lethbridge) | 2025-09-10 08:00 | 2025-09-11 17:00 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only
ATCO | 7L01 (813s Little Smoky - 881s Sturgeon 2) | 2025-09-10 09:00 | 2025-09-10 09:15 | N | Y |  | Line |  |  | Restricts Generation, Affects Cranking Path
ATCO | 881s 701T (881s Sturgeon) | 2025-09-10 09:00 | 2025-09-11 09:00 | N | N |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 535s 138kV Bus 4 (535s Joffre), 535s C1 (535s Joffre) | 2025-09-10 10:00 | 2025-09-10 16:00 | N | N |  | Bus, Shunts |  |  | Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ALTALINK, ATCO | 650s 1752 (650s Hansman Lake), 7L224 (650s Hansman Lake - 774s Monitor) | 2025-09-10 11:00 | 2025-09-10 12:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 199L (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek) | 2025-09-10 12:00 | 2025-09-10 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 932s 7L127D1 (932s Pemukan), 7L127 (774s Monitor - 932s Pemukan) | 2025-09-10 13:00 | 2025-09-10 14:00 | N | N |  | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 774s 704C (774s Monitor) | 2025-09-10 14:00 | 2025-09-10 15:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 199L (347s AML Fox Creek - 199AL tap), 347s 199E (347s AML Fox Creek) | 2025-09-10 15:00 | 2025-09-10 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 951s 240kV 900BS1 (951s Thickwood Hills), 951s 1201T (951s Thickwood Hills), 951s 920C (951s Thickwood), 951S 901 (951s Thickwood Hills), 951S 904 (951s Thickwood Hills), 951S 907 (951s Thickwood Hills), 951s 910 (951s Thickwood Hills), 951s 901TA (951s Thickwood Hills) | 2025-09-11 08:01 | 2025-09-11 13:00 | N | Y |  | Bus, Transformer, Shunts, Circuit Breaker, Switch |  |  | 240 kV, 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L01 (813s Little Smoky - 881s Sturgeon 2) | 2025-09-11 08:45 | 2025-09-11 09:00 | N | Y |  | Line |  |  | Restricts Generation, Affects Cranking Path
ATCO | 12L44 (939s Livock - 951s Thickwood Hills), 939s 1214R (939s Livock), 939s 1207 (939s Livock), 951s 1213R (951s Thickwood HIlls), 951s 1205 (951s Thickwood Hills), 951s 1206 (951s Thickwood Hills), 951s 1205B (951s Thickwood Hills), 951s 1206A (951s Thickwood Hills), 951s 12L44D1 (951s Thickwood Hills) | 2025-09-11 09:00 | 2025-09-11 13:00 | N | Y |  | Line, Shunts, Circuit Breaker, Switch |  |  | 240 kV, 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 700s 707C (700s Bonnyville) | 2025-09-11 09:00 | 2025-09-11 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 951s 240kV 900BS1 (951s Thickwood Hills), 951s 1201T (951s Thickwood Hills), 951S 907 (951s Thickwood Hills), 951S 904 (951s Thickwood Hills), 951s 910 (951s Thickwood Hills), 951S 901 (951s Thickwood Hills), 951s 1205 (951s Thickwood Hills), 951s 1206 (951s Thickwood Hills), 951s 1201TA (951s Thickwood Hills), 951s 901TA (951s Thickwood Hills) | 2025-09-11 13:01 | 2025-09-12 14:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, 500 kV, Pre-Condition
ALTALINK | 860L (44s Bearspaw Plant - 291s Cochrane), 291s 860 (291s Cochrane), 44s 860W (44s Bearspaw Plant) | 2025-09-12 06:00 | 2025-09-20 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185s T1 (185s Bretville) | 2025-09-12 07:00 | 2025-09-21 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L06 (784s Donnelly - 787s High Prairie), 787s 705 (787s High Prairie) | 2025-09-12 08:00 | 2025-09-12 12:00 | N | N |  | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 11.82L (SS-11 - SS-14), 14.1TR (SS-14), 14.3TR (SS-14), 14.1C (SS-14), 14.2C (SS-14), 14B138-11.82 (SS-14), 14MD138-14.1TR (SS-14), 14MD138-14.3TR (SS-14), 11B138-11.82 (SS-11) | 2025-09-12 08:00 | 2025-09-12 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.1TR (SS-33) | 2025-09-12 08:00 | 2026-06-19 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 199s T2 (199s East Airdrie) | 2025-09-12 09:00 | 2025-09-12 17:00 | N | N |  | Transformer |  |  | For Information Only
BCH | T4 (BCH Natal) | 2025-09-12 13:00 | 2025-09-26 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s GT1 (987s Clover Bar) | 2025-09-13 07:00 | 2025-09-15 10:00 | N | Y |  | Transformer |  |  | For Information Only, Restricts Generation
ALTALINK | 38s T1 (38s East Edmonton), 38s 73 (38s East Edmonton) | 2025-09-13 08:00 | 2025-09-13 13:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 37B138-37.81 (SS-37), 38B138-37.81 (SS-38) | 2025-09-13 08:00 | 2025-09-13 12:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 38.1TR (SS-38), 38.3TR (SS-38), 38.1C (SS-38), 39B138-38.83 (SS-39), 38B138-38.83 (SS-38) | 2025-09-13 12:00 | 2025-09-13 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 38s T4 (38s East Edmonton), 38s 18 (38s East Edmonton) | 2025-09-13 13:30 | 2025-09-13 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
Syncrude | G20 (Aurora), T3 (Aurora), 89-15 (Aurora) | 2025-09-14 | 2025-09-26 15:00 | N | N |  | Circuit Breaker, Transformer, Switch |  | Delayed and extended per SCL1 Suncor. Complete on the 26th of Sept. | For Information Only, Restricts Generation
ENMAX | 24.81L (SS-24 - SS-31), 31.84L (SS-31 - SS-32), 31.3TR (SS-31), 31.2TR (SS-31), 24B138-24.81 (SS-24), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31), 31B138-24.81 (SS-31) | 2025-09-14 08:00 | 2025-09-14 12:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 89s T2 (89s Ellerslie) | 2025-09-14 08:30 | 2025-09-14 18:30 | N | Y |  | Transformer |  |  | 500 kV, Overload, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31.1C (SS-31), 31B138-9.80 (SS-31), 9B138-9.80 (SS-9) | 2025-09-14 12:00 | 2025-09-14 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition
EPCOR | EP 511s Victoria T1 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria) | 2025-09-15 07:00 | 2025-09-26 17:00 | N | N |  | Transformer, Circuit Breaker |  | Outage extended. Epcor had issues when returning | Contingency Requires Mitigation, Pre-Condition
AESO-SC | AESO PDC | 2025-09-15 07:00 | 2025-09-17 18:00 | N | N |  | SCInternal |  |  | For Information Only
EPCOR | 52s T2 (52s East Industrial), 52s E2402 (52s East Industrial) | 2025-09-15 07:00 | 2025-09-16 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 987s T1 (987s Clover Bar), 987s T3 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s C2402 (987s Clover Bar) | 2025-09-15 07:00 | 2025-09-20 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
CMH | MH-10L (MHS-10 Box Springs - MHS-8 Burnside), MH-12L (MHS-8 Burnside - MHS-6 CMH Riverview), MHS-8 MH138-T81 (MHS-8 Burnside), MHS-8 MH138-803 (MHS-8 Burnside), MHS-8 MH69-802 (MHS-8 Burnside) | 2025-09-15 07:45 | 2025-09-15 15:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 421s T1 (421s Hays) | 2025-09-15 08:00 | 2025-09-15 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2025-09-15 08:30 | 2025-09-20 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-09-15 09:00 | 2025-09-18 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L06 (784s Donnelly - ATC 793s West Peace River), 784s 701T (784s Donnelly), ATC 793s 703 (ATC 793s West Peace River), 784s 701 (784s Donnelly), 784s 7L06D2 (784s Donnelly) | 2025-09-15 09:00 | 2025-09-26 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 708L (233s Beamer - 708AL tap), 233s 708X (233s Beamer) | 2025-09-15 09:00 | 2025-09-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 729s 703T (729s Otauwau), 729s 703 (729s Otauwau) | 2025-09-15 09:00 | 2025-10-03 17:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 665s T2 (665s Dome), 665s D2403 (665s Dome), 665s D2402 (665s Dome) | 2025-09-15 09:30 | 2025-09-21 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 33s 1 (33s Spray) | 2025-09-15 09:30 | 2025-09-18 12:30 | N | Y |  | Circuit Breaker |  |  | For Information Only, Restricts Generation
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome), 310p 1352 (310p Sundance), 310p 1452 (310p Sundance) | 2025-09-15 09:30 | 2025-09-21 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only, Affects Cranking Path
ATCO | 840s McNeill Station | 2025-09-15 10:00 | 2025-10-05 17:30 | N | Y |  | Station |  |  | Limits ATC, Pre-Condition
ALTALINK, TRANSALTA | 33s T1 (33s Spray) | 2025-09-15 10:30 | 2025-10-02 12:00 | N | Y |  | Transformer |  |  | For Information Only
ATCO | 860s 701T (860s Crow), 860s 301 (860s Crow) | 2025-09-15 12:00 | 2025-09-15 18:00 | N | N |  | Transformer, Circuit Breaker |  | Completed early | For Information Only
BCH | 2L112 (BPA Boundary - BCH Nelway) | 2025-09-15 13:00 | 2025-09-15 14:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck), 513s 1 (513s Lundbreck) | 2025-09-15 13:30 | 2025-09-19 17:30 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ATCO | 7L30 (732s Mitsue - 844s AEC Mill), 732s 704 (732s Mitsue), 732s 707 (732s Mitsue), 844s 703 (844s AEC Mill), 732s 7L30D1 (732s Mitsue) | 2025-09-15 14:01 | 2025-09-29 14:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L53 (700s Bonnyville - 7LA53 tap), 700s 702 (700s Bonnyville) | 2025-09-15 15:00 | 2025-09-18 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, HSLP | 421s T2 (421s Hays), 421s 467E (421s Hays), 421s 89-L1 (421s Hays), 421s 52-1 (421s Hays), 421s 52-F01 (421s Hays), 421s 52-F02 (421s Hays) | 2025-09-15 18:00 | 2025-09-18 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
BCH | 5L72 (BCH Mica G.S. - BCH Nicola) | 2025-09-15 23:00 | 2025-09-30 23:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ENMAX | 14.3TR (SS-14) | 2025-09-16 07:00 | 2025-09-16 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.80L (SS-1 - SS-28), 28B138-1.80 (SS-28) | 2025-09-16 07:00 | 2025-09-16 09:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 514L (396s Pincher Creek - 514BL tap), 514L (513s Lundbreck - 514BL tap), 322s T1 (322s Cowley Ridge), 396s 514N (396s Pincher Creek) | 2025-09-16 07:00 | 2025-09-17 18:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
ALTALINK | 735L (171s Redwater - 233s Beamer), 171s 735X (171s Redwater), 233s 735N (233s Beamer) | 2025-09-16 07:00 | 2025-09-16 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 16.60L (SS-16 - SS-34), 34.2TR (SS-34), 34B69-16.60 (SS-34), 34MD69-34.2TR (SS-34), 16B69-16.60 (SS-16) | 2025-09-16 08:00 | 2025-09-16 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20) | 2025-09-16 09:00 | 2025-09-16 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 478s T2 (478s Tucuman) | 2025-09-16 10:30 | 2025-09-18 17:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43) | 2025-09-16 11:00 | 2025-09-16 13:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 368s C1 (368s Burdett) | 2025-09-16 11:00 | 2025-09-18 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 14.4TR (SS-14) | 2025-09-16 12:00 | 2025-09-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 21.61L (SS-21 - SS-34), 34.1TR (SS-34), 34B69-21.61 (SS-34), 34MD69-34.1TR (SS-34) | 2025-09-16 12:00 | 2025-09-16 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43) | 2025-09-16 13:00 | 2025-09-16 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
TAYLORPP, ALTALINK | 148s T1 (148s Schantz), 148s T2 (148s Schantz), 148s T3 (148s Schantz), 256s 228X (256s Harmattan), 148s AG-EB25A (148s Schantz), 148s AG-EB510B (148s Schantz), 148s AG-EB510C (148s Schantz), 148s AG-EB510D (148s Schantz) | 2025-09-17 07:30 | 2025-09-18 18:30 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
SUNCOR | 29PL7-4 (29EDD-65 - 29EDD-71), 29EDD-65 29PS-0284 (29EDD-65 Edd65Sub), 29EDD-71 29PS-243 (29EDD-71 Edd71Sub), 29EDD-65 29PT-0257 (29EDD-65), 29EDD-71 752-4624 (29EDD-71), 29EDD-71 752-4623 (29EDD-71), 29EDD-71 29PS-244 (29EDD-71 Edd71Sub), 29EDD-65 29PS-0279 (29EDD-65 Edd65Sub), 29EDD-65 29-952-4812 (29EDD-65), 29EDD-65 29-952-4813 (29EDD-65) | 2025-09-17 08:00 | 2025-09-22 09:00 | N | Y |  | Line, Switch, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2.81L (SS-2 - SS-9), 9.83L (SS-9 - SS-43), 9.3TR (SS-9), 9.2TR (SS-9), 43B138-9.83 (SS-43), 9B138-9.83 (SS-9), 9B8-9.2TR (SS-9), 9MD138-9.2TR (SS-9), 9MD138-9.3TR (SS-9), 9BA8-9.3TR (SS-9), 9BB8-9.3TR (SS-9), 9B138-2.81 (SS-9), 2MD138-2.81 (SS-2) | 2025-09-17 08:00 | 2025-09-17 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s 31 (62s Brazeau Plant), 62s T3 (62s Brazeau Plant) | 2025-09-17 09:00 | 2025-09-18 17:30 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 142s C1 (142s Magcan) | 2025-09-17 11:30 | 2025-09-18 12:30 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 11.82L (SS-11 - SS-14), 14B138-11.82 (SS-14) | 2025-09-18 08:00 | 2025-09-18 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CNRL | 842s 75-1904 (842s Horizon Upgrading) | 2025-09-18 08:00 | 2025-09-20 16:00 | N | Y |  | Circuit Breaker |  | Completed early | 240 kV, Pre-Condition
ALTALINK | 62s T5 (62s Brazeau Plant), 62s 207 (62s Brazeau Plant) | 2025-09-18 09:00 | 2025-09-18 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2025-09-18 12:00 | 2025-09-18 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 421s T1 (421s Hays) | 2025-09-18 17:00 | 2025-09-19 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2025-09-19 07:00 | 2025-09-28 17:00 | Y | Y |  | Line |  |  | 500 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 786L (799s Coleman - BCH Natal), 799s 786W (799s Coleman) | 2025-09-19 07:00 | 2025-09-28 17:00 | N | Y |  | Line, Circuit Breaker | Notes for OC: 1. Ensure the ' To Adjacent RC' flag is selected for this outage to show on the Report for Adjacent RC. 2. Ensure the Outage Category is set as 'Interconnection' and Interconnection 'AB-BC' is selected for this outage to show on the interconnection report. 3. Ensure WebOms entry is done. |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 520s T1 (520s Bennett), 520s R7 (520s Bennett), 520s 552 (520s Bennett) | 2025-09-19 07:00 | 2025-09-25 17:00 | N | Y |  | Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition
AESO | Path 1 (AIES Islanding) | 2025-09-19 07:00 | 2025-09-28 17:00 | Y | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
BHE Canada | MATL (120s Picture Butte - Montana) | 2025-09-19 07:00 | 2025-09-28 17:00 | Y | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 887L (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2025-09-19 07:00 | 2025-09-28 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.81L (SS-11 - SS-13), 11.4TR (SS-11), 11.1TR (SS-11), 11B138-BT5 (SS-11), 11B138-11.81 (SS-11), 11MD138-11.1TR (SS-11), 11MD138-11.4TR (SS-11) | 2025-09-19 08:00 | 2025-09-19 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 410s T1 (410s Josephburg) | 2025-09-19 08:00 | 2025-09-19 13:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 5L94 (BCH Cranbrook - 102s Langdon), 5RXN5 (BCH Cranbrook) | 2025-09-19 09:00 | 2025-09-26 17:00 | Y | Y |  | Line, Shunts |  |  | 500 kV, For Information Only, Limits ATC, Pre-Condition
ALTALINK | 58s C1 (58s Edson) | 2025-09-19 09:30 | 2025-10-23 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 410s T2 (410s Josephburg) | 2025-09-19 13:01 | 2025-09-19 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, BHE Canada | 120s 27 (120s Picture Butte) | 2025-09-21 18:00 | 2025-09-26 17:30 | N | Y |  | Switch |  |  | 240 kV, Pre-Condition
EPCOR | 72RG7 (Garneau - Rossdale), G722 (Garneau), G723 (Garneau), RG725 (Rossdale), GDS4 (Garneau) | 2025-09-22 07:00 | 2025-09-26 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s GT3 (987s Clover Bar) | 2025-09-22 07:00 | 2025-09-26 10:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO, CNRL, ALBIAN | 847s 902T (847s Muskeg River), 919s 908 (919s Hartley) | 2025-09-22 08:00 | 2025-09-23 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 20.82L (SS-20 - SS-21), 21.4TR (SS-21), 21.1TR (SS-21), 42s 21 (42s Sarcee), 21B138-20.82 (SS-21), 21B138-21.80 (SS-21), 21B69-21.4TR (SS-21), 21MD138-21.1TR (SS-21), 20B138-20.82 (SS-20), 21MD138-21.4TR (SS-21) | 2025-09-22 08:00 | 2025-09-25 15:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-30L (MHS-3 Southridge - MHS-5 NE Crescent Heights), MHS-5 MH69-502 (MHS-5 NE Crescent Heights), MHS-3 MH69-308 (MHS-3 Southridge) | 2025-09-22 08:00 | 2025-09-25 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CDTP | TLE1 Tilley DER Solar Generator Test | 2025-09-22 08:00 | 2025-10-13 08:00 | N | N |  | Unit
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 146s 823L (146s Macdonald), 593s 823L (593s Lakeview) | 2025-09-22 08:00 | 2025-09-25 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 21.1C (SS-21) | 2025-09-22 08:00 | 2025-09-25 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 184s T3 (184s Petro-Canada Edmonton) | 2025-09-22 08:30 | 2025-09-29 14:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-09-22 09:00 | 2025-09-25 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake), 5RX1 (BCH Vaseux Lake) | 2025-09-22 09:00 | 2025-09-22 17:00 | Y | Y |  | Line, Shunts |  | Ended early | 500 kV, Limits ATC
ATCO | 740s 700 (740s H.R. Milner) | 2025-09-22 10:00 | 2025-09-22 17:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-09-22 11:00 | 2025-09-22 14:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 310p T30 (310p Sundance), 310P 69 (310p Sundance) | 2025-09-22 12:30 | 2025-09-25 16:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 1043L (320p Keephills - 367s Harry Smith), 320p 352 (320p Keephills), 320p 252 (320p Keephills), 320p 289 (320p Keephills) | 2025-09-22 13:00 | 2025-09-25 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 717s 701 (717s Ethel Lake), 846s 701 (846s Grand Centre) | 2025-09-22 13:00 | 2025-09-25 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 478s T1 (478s Tucuman) | 2025-09-22 14:00 | 2025-09-25 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 723L (150s Clyde - 438s Westlock), 723L (438s Westlock - 724L tap), 438s T1 (438s Westlock), 150s 723W (150s Clyde), 438s 552 (438s Westlock), 438s 723E (438s Westlock), 438s 723W (438s Westlock) | 2025-09-22 22:59 | 2025-09-23 06:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 8B138-3A0 (SS-8), 8B138-4A0 (SS-8) | 2025-09-23 08:00 | 2025-10-13 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
BCH | 5CB22 (BCH Vaseux Lake) | 2025-09-23 08:00 | 2025-09-24 09:06 | N | Y |  | Circuit Breaker |  |  | 500 kV, For Information Only
ACCIONA, ENBRIDGE | 139s Hillridge, 139s T1 (139s Hillridge), 139S 52/B1 (139s Hillridge) | 2025-09-23 08:00 | 2025-09-26 18:00 | N | N |  | Station, Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
ENMAX | 40.81L (SS-40 - SS-41), 41B138-40.81 (SS-41), 40B138-40.81 (SS-40) | 2025-09-23 08:00 | 2025-09-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 23.3TR (SS-23), 23B138-2.80 (SS-23), 23MD138-23.3TR (SS-23), SW83 (SS-23) | 2025-09-23 08:00 | 2025-09-23 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185s T1 (185s Bretville) | 2025-09-23 08:30 | 2025-09-24 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 740s 701 (740s H.R. Milner) | 2025-09-23 09:00 | 2025-09-24 17:30 | N | Y |  | Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler), 205s 352 (205s Castle Rock Ridge), 205s 452 (205s Castle Rock Ridge), 312s 1071 (312s Fidler) | 2025-09-23 09:30 | 2025-09-25 16:30 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 780s 701 (780s Lubicon) | 2025-09-23 09:30 | 2025-09-24 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 23.80L (74s Janet - SS-23), 23.4TR (SS-23), 23B138-23.80 (SS-23), 23MD138-23.4TR (SS-23), SW84 (SS-23) | 2025-09-23 12:00 | 2025-09-23 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 267s T1 (267s Killarney Lake) | 2025-09-23 12:30 | 2025-10-02 10:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 31B138-9.80 (SS-31), 9B138-9.80 (SS-9) | 2025-09-24 08:00 | 2025-09-24 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 223L (150s Clyde - 159s Colinton), 150s 223N (150s Clyde), 159s 223 (159s Colinton) | 2025-09-24 10:00 | 2025-09-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 780s 702 (780s Lubicon) | 2025-09-24 12:30 | 2025-09-25 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | RV726 (Rossdale), 72RV4 (EP 511s Victoria - Rossdale) | 2025-09-25 07:00 | 2025-09-25 17:00 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 710s 702T (710s Vermilion) | 2025-09-25 08:00 | 2025-09-27 17:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 740s 705 (740s H.R. Milner) | 2025-09-25 09:00 | 2025-09-26 17:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 728L (353s Plamondon - 405s Waupisoo), 405s 728 (405s Waupisoo), 353s 452 (353s Plamondon) | 2025-09-26 07:00 | 2025-09-26 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 864L (397s Benbow - 864AL tap), 397s 864W (397s Benbow) | 2025-09-26 07:00 | 2025-11-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2025-09-26 07:00 | 2025-09-26 17:00 | N | Y |  | Line |  |  | 240 kV, For Information Only
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 814s B2401 (814s Bellamy), 814s B2402 (814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2025-09-26 07:00 | 2025-09-26 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), EP 511s V723 (EP 511s Victoria), EP 511s V724 (EP 511s Victoria), RV722 (Rossdale), EP 511s VDS9 (EP 511s Victoria) | 2025-09-26 07:00 | 2025-09-26 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
CENOVUS | 539s PCB-9203 (539s Sunday Creek) | 2025-09-26 08:00 | 2025-09-28 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 38.83L (SS-38 - SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39) | 2025-09-26 08:00 | 2025-09-26 10:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
RESC | FRM1 Forty Mile Bow Island | 2025-09-26 09:00 | 2025-09-26 18:00 | N | Y |  | Unit |  |  | Restricts Generation
ENMAX | 37.81L (SS-37 - SS-38), 38B138-37.81 (SS-38), 37B138-37.81 (SS-37) | 2025-09-26 10:00 | 2025-09-26 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L06 (784s Donnelly - 787s High Prairie), 787s 705 (787s High Prairie) | 2025-09-26 12:00 | 2025-09-26 16:00 | N | N |  | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon), 353s 552 (353s Plamondon), 157s 728W (157s Lac La Biche) | 2025-09-26 13:01 | 2025-09-26 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 39.82L (SS-39 - SS-162), 39.2TR (SS-39), 22.81L (SS-22 - SS-39), 39.4TR (SS-39) | 2025-09-27 08:00 | 2025-09-27 18:00 | N | N |  | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia) | 2025-09-28 07:00 | 2025-09-28 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX | 11.83L (SS-162 - SS-11), 11B138-11.83 (SS-11) | 2025-09-28 08:00 | 2025-09-28 18:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L20 (740s H.R. Milner - 810s Dome Cutbank), 740s 704 (740s H.R. Milner) | 2025-09-28 09:00 | 2025-10-05 15:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
EPCOR | 816s P2404 (816s Petrolia), 816s P2405 (816s Petrolia), 816s T2 (816s Petrolia) | 2025-09-29 07:00 | 2025-10-05 17:00 | N | Y |  | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | T1 (Strathcona) | 2025-09-29 07:00 | 2025-10-02 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 557s T2 (557s Castle Downs), 557s CD2403 (557s Castle Downs), 557s CD2404 (557s Castle Downs) | 2025-09-29 07:00 | 2025-10-12 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 27.1TR (SS-27), 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27), 27MD69-27.1TR (SS-27), SW64 (SS-27) | 2025-09-29 07:30 | 2025-10-07 16:00 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 21.2TR (SS-21) | 2025-09-29 08:00 | 2025-11-07 16:00 | N | N |  | Transformer |  |  | For Information Only
CMH | MHS-8 MH69-802 (MHS-8 Burnside) | 2025-09-29 08:00 | 2025-09-29 14:00 | N | N |  | Circuit Breaker |  |  | For Information Only
SUNCOR | 635EDD-1001 635-752-662 (635EDD-1001), 635EDD-1001 635-752-663 (635EDD-1001), 635PL7-1005 (635EDD-1001 - 635EDD-1003) | 2025-09-29 08:00 | 2025-09-29 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Pre-Condition, Restricts Generation
ENMAX | 24.81L (SS-24 - SS-31), 24B138-24.81 (SS-24) | 2025-09-29 08:00 | 2025-09-29 12:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2025-09-29 09:00 | 2025-10-17 17:00 | Y | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 740s 704 (740s H.R. Milner) | 2025-09-29 10:00 | 2025-09-30 17:30 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ATCO | 751s 704C (751s Hill) | 2025-09-29 10:00 | 2025-09-29 11:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 339s T1 (339s Duchess) | 2025-09-29 11:00 | 2025-10-08 17:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33) | 2025-09-29 12:00 | 2025-09-29 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2025-09-29 13:00 | 2025-10-02 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 732s 701 (732s Mitsue), 732s 702 (732s Mitsue), 732s 901T (732s Mitsue), 732s 902 (732s Mitsue), 732s 903 (732s Mitsue) | 2025-09-29 14:01 | 2025-10-13 14:00 | N | Y |  | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, CLRS | 180AL (604s Granum - 180L tap), 180L (928s East Stavely - 180AL tap), 180L (15s Fort Macleod - 180AL tap), 604s 152 (604s Granum), 604s 252 (604s Granum), 604s 352 (604s Granum), 604s 452 (604s Granum), 604s 552 (604s Granum), 604s T1 (604s Granum), 15s 180N (15s Fort Macleod) | 2025-09-30 07:00 | 2025-10-01 18:00 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 935L (324s Cassils - 356s Milo) | 2025-09-30 07:00 | 2025-10-08 15:10 | N | Y |  | Line |  | Ended early | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
EPCOR | T1 Westmoreland Mines Distribution (330P Genesee), FCLCB1 (330p Genesee) | 2025-09-30 07:00 | 2025-09-30 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 67s T2 (67s Stirling), 67s 2 (67s Stirling) | 2025-09-30 07:30 | 2025-09-30 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK, TRANSALTA | 320p GT3 (320p Keephills), 320p 2952 (320p Keephills), 320p 3052 (320p Keephills) | 2025-09-30 16:00 | 2025-10-25 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
EPCOR | EP 511s V722 (EP 511s Victoria) | 2025-10-01 07:00 | 2025-10-04 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-10-01 07:00 | 2025-10-03 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, EPCOR | 1045L (310p Sundance - 1045AL tap), 1045L (EP 805s Jasper - 1045AL tap), 1045AL (320p Keephills - 1045L tap), EP 805s J2406 (EP 805s Jasper), EP 805s J2407 (EP 805s Jasper), 310p 1652 (310p Sundance), 310p 1752 (310p Sundance), 320p 1352 (320p Keephills) | 2025-10-01 07:00 | 2025-10-02 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1045AL (320p Keephills - 1045L tap), 1045L (310p Sundance - 1045AL tap), 1045L (EP 805s Jasper - 1045AL tap) | 2025-10-01 07:00 | 2025-10-02 18:00 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
ALTALINK | 67s T1 (67s Stirling) | 2025-10-01 07:30 | 2025-10-01 17:30 | N | N |  | Transformer |  |  | Pre-Condition, Restricts Generation
CMH | MHS-6 MH69-616 (MHS-6 CMH Riverview) | 2025-10-01 08:00 | 2025-10-01 10:30 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 1080L (SS-25 - SS-65), 25B240-D138 (SS-25), 25B240-D139 (SS-25), 65B240-D131 (SS-65), 65B240-D132 (SS-65), 25MD240-1080 (SS-25), 65MD240-1080 (SS-65) | 2025-10-01 08:00 | 2025-10-02 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 22.3TR (SS-22), 22.1TR (SS-22), 22B138-13.82 (SS-22), 22B138-22BT8 (SS-22), 22MD138-22.1TR (SS-22), SW83 (SS-22), 22MD138-22.3TR (SS-22), SW84 (SS-22) | 2025-10-01 08:00 | 2025-10-01 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 15.62L (SS-15 - SS-16), 16B69-15.62 (SS-16) | 2025-10-01 08:00 | 2025-10-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-12L (MHS-8 Burnside - MHS-6 CMH Riverview), MHS-6 MH69-602 (MHS-6 CMH Riverview) | 2025-10-01 11:00 | 2025-10-01 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 38s 7652 (38s East Edmonton) | 2025-10-01 11:00 | 2025-10-02 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s T2 (89s Ellerslie) | 2025-10-01 12:00 | 2025-10-03 18:30 | N | Y |  | Transformer |  |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22.81 (SS-22), 22B138-22BT8 (SS-22), SW85 (SS-22), 22MD138-22.2TR (SS-22) | 2025-10-01 12:00 | 2025-10-01 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s C1 (523s Bullshead) | 2025-10-01 16:00 | 2025-10-09 12:30 | N | N |  | Shunts |  |  | Pre-Condition
BHE Canada | 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte) | 2025-10-01 16:00 | 2025-10-15 18:00 | N | Y |  | Shunts |  | Back in service early as per Altalink | Pre-Condition
BCH | 5L75 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2025-10-01 23:00 | 2025-10-01 23:30 | N | Y |  | Line |  |  | 500 kV, Limits ATC
ALTALINK | 722L (107s Westfield - 368s Burdett), 368s 722X (368s Burdett), 107s 722N (107s Westfield), 107s T1 (107s Westfield) | 2025-10-02 07:00 | 2025-10-02 12:00 | N | Y |  | Line, Circuit Breaker, Switch, Transformer |  |  | Restricts Generation
ENMAX | 14.1C (SS-14), 14.2C (SS-14) | 2025-10-02 08:00 | 2025-10-07 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 632s 152 (632s Russell) | 2025-10-02 08:00 | 2025-10-02 12:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
CMH | MHS-6 MH69-614 (MHS-6 CMH Riverview), MH-8L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview) | 2025-10-02 08:00 | 2025-10-02 10:30 | N | N |  | Circuit Breaker, Line |  |  | Over/Under Voltage, Overload, Pre-Condition
BCH | 5CB14 (BCH Vaseux Lake) | 2025-10-02 08:00 | 2025-10-02 16:00 | N | Y |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 853L (28s West Brooks - 853AL tap), 853L75 (853AL tap), 28s 25 (28s West Brooks), 28s 28 (28s West Brooks), 28s 853W (28s West Brooks) | 2025-10-02 08:15 | 2025-10-02 16:30 | N | Y |  | Line, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 267s 138kV Bus (267s Killarney Lake), 267s T1 (267s Killarney Lake), 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake), 267s 748E (267s Killarney Lake), 267s 749A (267s Killarney Lake), 748L (267s Killarney Lake - 277s Hayter), 749AL (267s Killarney Lake - 749L tap) | 2025-10-02 10:00 | 2025-10-02 15:00 | N | N |  | Bus, Transformer, Shunts, Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 632s 412 (632s Russell), 412L (396s Pincher Creek - 632s Russell) | 2025-10-02 13:00 | 2025-10-02 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 38s 897 (38s East Edmonton), 897L (38s East Edmonton - 45s Bretona) | 2025-10-02 13:01 | 2025-10-02 17:30 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2025-10-03 07:00 | 2025-10-03 19:00 | Y | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 611L (186s Dry Creek - 391s Balzac), 391s 611 (391s Balzac), 186s 611 (186s Dry Creek) | 2025-10-03 08:00 | 2025-10-03 10:49 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
CMH | MHS-6 MH69-611 (MHS-6 CMH Riverview), MHS-6 MH138-T63 (MHS-6 Riverview), MHS-6 MH138-620 (MHS-6 CMH Riverview), MH-20L (MHS-3 Southridge - MHS-6 CMH Riverview) | 2025-10-03 08:00 | 2025-10-03 12:00 | N | N |  | Circuit Breaker, Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28B138-28.80 (SS-28) | 2025-10-03 08:00 | 2025-10-03 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 23.80L (74s Janet - SS-23), 23B138-23.80 (SS-23), 74s 23.80W (74s Janet) | 2025-10-03 08:00 | 2025-10-03 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 1052L (28s West Brooks - 324s Cassils), 28s 2 (28s West Brooks), 28s 289 (28s West Brooks), 28s 5 (28s West Brooks) | 2025-10-03 08:00 | 2025-10-03 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake), 38s 780X (38s East Edmonton) | 2025-10-03 09:00 | 2025-10-03 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 861L (71s Lamoureux - 258s Dow Hydrocarbons), 258s 152 (258s Dow Hydrocarbons), 258s 252 (258s Dow Hydrocarbons) | 2025-10-04 07:00 | 2025-10-05 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 6.82L (SS-6 - SS-41), 6B138-6.82 (SS-6), 41B138-6.82 (SS-41) | 2025-10-04 08:00 | 2025-10-04 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 39.82L (SS-39 - SS-162), 39.3TR (SS-39), 39.1TR (SS-39), 39B138-38.83 (SS-39), 39B138-39.82 (SS-39), 38B138-38.83 (SS-38) | 2025-10-05 08:00 | 2025-10-05 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 5L75 (BCH Ashton Creek - BCH Revelstoke G.S.) | 2025-10-05 23:00 | 2025-10-05 23:30 | N | Y |  | Line |  |  | 500 kV, Limits ATC
ALTALINK, DOW | 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydrocarbons), 166s 862N (166s Dow Chemical Fort Saskatchewan) | 2025-10-06 06:15 | 2025-10-08 17:45 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 72DS26 (665s Dome - Strathcona), 665s D721 (665s Dome), S721 (Strathcona), 665s T3 (665s Dome), 665s D2404 (665s Dome), 665s DAB3 (665s Dome), 665s DDS17 (665s Dome) | 2025-10-06 07:00 | 2025-10-06 17:00 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 1.8TR (SS-1) | 2025-10-06 07:00 | 2025-11-06 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | VHBB2 (Rossdale) | 2025-10-06 07:00 | 2025-10-10 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty) | 2025-10-06 07:00 | 2025-10-06 17:00 | N | N |  | Line |  |  | Overload, Pre-Condition
AESO-SC | AESO SDC | 2025-10-06 07:00 | 2025-10-10 20:00 | N | N |  | SCInternal |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft), W724 (Woodcroft), W725 (Woodcroft), RW727 (Rossdale) | 2025-10-06 07:00 | 2025-10-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MHS-7 138-T71 (MHS-7 Brier Park), MHS-7 MH69-706 (MHS-7 Brier Park), MHS-7 MH138-707 (MHS-7 Brier Park) | 2025-10-06 07:30 | 2025-10-06 10:30 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 21.1C (SS-21), 21.2TR (SS-21), 44s 50X (44s Bearspaw Plant), 60s50 (SS-21) | 2025-10-06 08:00 | 2025-10-17 16:00 | N | Y |  | Line, Shunts, Transformer, Circuit Breaker |  |  | Pre-Condition
ENMAX | 2.1TR (SS-2) | 2025-10-06 08:00 | 2025-10-13 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43) | 2025-10-06 08:00 | 2025-10-08 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 801L (62s Brazeau Plant - 294s Brazeau Plant Outlet Works), 62s 201 (62s Brazeau Plant) | 2025-10-06 08:00 | 2025-10-06 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L91 (BCH Ashton Creek - BCH Selkirk) | 2025-10-06 09:00 | 2025-10-10 17:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ATCO | 755s 901 (755s Cordel) | 2025-10-06 09:30 | 2025-10-07 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 102s SVC (102s Langdon), 102s T4 (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon) | 2025-10-06 10:00 | 2025-11-19 16:00 | N | Y |  | Shunts, Transformer, Circuit Breaker | Note for OC: BC wants to be aware of this outage and prefers to see in the interconnection report. OC to select the outage category as 'Interconnection' and select Interconnection as 'AB-BC', so that this outage shows up on the Interconnection report. |  | 240 kV, Pre-Condition
SUNCOR | 635EDD-1000 635PT-1003 (635EDD-1000) | 2025-10-06 12:02 | 2025-10-16 14:00 | N | N |  | Transformer |  | Done early | For Information Only
ALTALINK | 38s C2 (38s East Edmonton), 38s 3152 (38s East Edmonton) | 2025-10-06 12:30 | 2025-10-09 17:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 678s T3 (678s Okotoks), 678s 552 (678s Okotoks) | 2025-10-06 13:00 | 2025-10-07 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe), 77s 252 (77s Sagitawah), 77s 452 (77s Sagitawah), 77s 799X (77s Sagitawah) | 2025-10-06 13:00 | 2025-10-10 11:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 551s T1 (551s Chevron Kaybob) | 2025-10-06 14:30 | 2025-10-08 09:30 | N | N |  | Transformer |  | Salvage complete early | For Information Only
ATCO, ALTALINK | 7L79 (771s Veteran - 932s Pemukan), 7L79 (771s Veteran - 892s Ribstone Creek), 7L696 (508s Lakesend - 892s Ribstone Creek), 892s 701T (892s Ribstone Creek), 771s 701T (771s Veteran), 508s T1 (508s Lakesend), 508s 9 (508s Lakesend), 508s 696 (508s Lakesend), 892s 701 (892s Ribstone Creek), 892s 702 (892s Ribstone Creek), 771s 701 (771s Veteran) | 2025-10-07 07:00 | 2025-10-07 19:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
SUNCOR | 29EDD-2 29PT-2 (29EDD-2 Tar Island), 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-1 29PS-195 (29EDD-1 Millennium), 29EDD-1 29EDD1s1152 (29EDD-1 Millennium), 29EDD-1 29EDD1s1252 (29EDD-1 Millennium) | 2025-10-07 08:00 | 2025-10-08 19:59 | N | N |  | Transformer, Line, Switch, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
CMH | MH-60L (MHS-5 NE Crescent Heights - MHS-7 Brier Park), MHS-7 MH69-712 (MHS-7 Brier Park) | 2025-10-07 08:00 | 2025-10-07 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L228 (845s Big Mountain - 7L20 tap) | 2025-10-07 08:00 | 2025-10-16 02:00 | N | Y |  | Line |  | returned early | Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK, Lethbridge | 725L (15s Fort MacLeod - 725BL tap), 725L (674s Bowron - 725BL tap), 725BL (240s McBride Lake - 725L tap), 15s 725 (15s Fort Macleod), 674s 725W (674s Bowron) | 2025-10-07 08:00 | 2025-10-08 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 801L (294s Brazeau Outlet Works - 801AL tap), 294s 801X (294s Brazeau Outlet Works) | 2025-10-07 08:00 | 2025-10-07 17:30 | N | N |  | Line, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 421s T1 (421s Hays) | 2025-10-07 08:30 | 2025-10-07 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 320p PS2 (320p Keephills), 320p 2652 (320p Keephills), 320p 2752 (320p Keephills) | 2025-10-07 08:30 | 2025-10-07 17:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 780s 706C (780s Lubicon), 780s 706 (780s Lubicon) | 2025-10-07 09:30 | 2025-10-08 11:45 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 801s 907 (801s Anderson) | 2025-10-07 09:30 | 2025-10-07 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 800s 701T (800s Friedenstal), 800s 711 (800s Friedenstal) | 2025-10-07 10:00 | 2025-10-10 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2025-10-07 23:00 | 2025-10-08 07:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 914L (86s Bigstone - 87s Gaetz), 87s 240kV East Bus (87s Gaetz), 87s T2 (87s Gaetz), 87s 2352 (87s Gaetz), 87s 34 (87s Gaetz), 87s 1252 (87s Gaetz), 87s 914N (87s Gaetz) | 2025-10-08 07:00 | 2025-10-11 17:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 748L (267s Killarney Lake - 277s Hayter), 267s 748E (267s Killarney Lake), 277s 748 (277s Hayter) | 2025-10-08 07:15 | 2025-10-08 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
CMH | MHS-3 C-31 (MH69S-3) | 2025-10-08 08:00 | 2025-10-08 14:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 14.1TR (SS-14) | 2025-10-08 08:00 | 2025-10-09 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 39.1TR (SS-39) | 2025-10-08 08:00 | 2025-10-09 10:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27), 27MD69-27.2TR (SS-27) | 2025-10-08 08:30 | 2025-10-16 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 678s T1 (678s Okotoks), 678s 352 (678s Okotoks) | 2025-10-08 09:00 | 2025-10-10 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L228 (845s Big Mountain - 7L20 tap), 845s 703 (845s Big Mountain), 845s 710 (845s Big Mountain) | 2025-10-08 09:30 | 2025-10-09 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ATCO | 780s 707C (780s Lubicon) | 2025-10-08 12:00 | 2025-10-09 17:00 | N | N |  | Shunts |  |  | Pre-Condition
CMH | MHS-6 MH69-616 (MHS-6 CMH Riverview) | 2025-10-08 17:00 | 2025-10-25 10:00 | N | N |  | Circuit Breaker |  | Completed many days ago | Contingency Requires Mitigation
SUNCOR | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-2 29PT-2 (29EDD-2 Tar Island), 29EDD-2 252-5204 (29EDD-2 Tar Island), 352-02501A (29EDD-22), 352-02501C (29EDD-22), 29EDD-2 29PS-5 (29EDD-2 Tar Island) | 2025-10-08 20:00 | 2025-10-13 20:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 62s T2 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant) | 2025-10-09 03:00 | 2025-10-09 07:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK, DOW | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 54s 707N (54s Fort Saskatchewan), 166s 707X (166s Dow Chemical Fort Saskatchewan) | 2025-10-09 06:15 | 2025-10-10 17:45 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition, Affects Cranking Path
CMH | MHS-3 MH69-314 (MHS-3 Southridge), MHS-3 MH69-T33 (MHS-3 South Ridge) | 2025-10-09 08:00 | 2025-10-09 14:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2075s 916 (2075s Newell), 2075s 917 (2075s Newell), 2029s T11 (2029s Heathfield), 2075s T11 (2075s Newell) | 2025-10-09 08:00 | 2025-10-10 11:41 | N | Y |  | Line, Circuit Breaker, Transformer |  |  | 500 kV, Overload, Pre-Condition, Restricts Generation
ENMAX | 22.81L (SS-22 - SS-39), 39B138-22.81 (SS-39), 22B138-22.81 (SS-22) | 2025-10-10 08:00 | 2025-10-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 26.81L (SS-26 - SS-32), 32.83L (SS-32 - SS-40), 32.2TR (SS-32), 32.1TR (SS-32), 32B138-32BT5 (SS-32), 32B138-26.81 (SS-32), 32B138-32.83 (SS-32), 32MD138-32.1TR (SS-32), 32MD138-32.2TR (SS-32) | 2025-10-10 08:00 | 2025-10-10 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 787L (166s Dow Chemical Fort Saskatchewan - 787AL tap) | 2025-10-11 06:15 | 2025-10-13 17:45 | N | Y |  | Line |  |  | Overload, Pre-Condition, Affects Cranking Path
ENMAX | 31.84L (SS-31 - SS-32), 32.3TR (SS-32), 32B138-32BT5 (SS-32), 31B138-31.84 (SS-31), 32B138-31.84 (SS-32), 32MD138-32.3TR (SS-32) | 2025-10-11 08:00 | 2025-10-11 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ALTALINK | 914L (63s Red Deer - 87s Gaetz), 87s 240kV West Bus (87s Gaetz), 87s T1 (87s Gaetz), 87s 2352 (87s Gaetz), 87s 1652 (87s Gaetz), 87s 13 (87s Gaetz), 87s 914X (87s Gaetz) | 2025-10-12 07:00 | 2025-10-14 15:55 | N | Y |  | Line, Bus, Transformer, Circuit Breaker, Switch |  | Planned | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 987s T1 (987s Clover Bar), 987s C2401 (987s Clover Bar), 987s C2403 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar) | 2025-10-13 07:00 | 2025-10-24 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 69s T2 (69s North Barrhead) | 2025-10-13 07:30 | 2025-10-24 16:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 26B138-26.81 (SS-26), 32B138-26.81 (SS-32) | 2025-10-13 08:00 | 2025-10-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 732s 701 (732s Mitsue), 732s 702 (732s Mitsue), 732s 901T (732s Mitsue), 732s 501R (732s Mitsue) | 2025-10-13 14:01 | 2025-10-27 14:00 | N | Y |  | Circuit Breaker, Transformer, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T4 (805s Jasper) | 2025-10-14 07:00 | 2025-10-14 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton) | 2025-10-14 07:00 | 2025-10-18 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Namao), N721 (Namao) | 2025-10-14 07:00 | 2025-10-14 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 924L (102s Langdon - 356s Milo), 102s 6852 (102s Langdon), 102s 6952 (102s Langdon), 356s 952 (356s Milo), 356s 852 (356s Milo), 102s 924 (102s Langdon), 356s 924 (356s Milo) | 2025-10-14 07:00 | 2025-10-29 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Overload, Affects Cranking Path
ENMAX | 8B138-5A0 (SS-8) | 2025-10-14 07:30 | 2025-10-14 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 2.3TR (SS-2) | 2025-10-14 08:00 | 2025-10-17 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 824L (593s Lakeview - 618s Riverbend), 593s 824L (593s Lakeview) | 2025-10-14 08:00 | 2025-10-14 15:05 | N | Y |  | Line, Circuit Breaker |  | Planned | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 5.10TR (SS-5) | 2025-10-14 08:00 | 2025-10-15 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs), 557s CD2404 (557s Castle Downs), 557s CD2405 (557s Castle Downs), 557s CDDS14 (557s Castle Downs) | 2025-10-14 09:30 | 2025-10-17 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 845s 701 (845s Big Mountain) | 2025-10-14 09:30 | 2025-10-14 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 801s 910 (801s Anderson) | 2025-10-14 10:00 | 2025-10-14 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 840s McNeill Station | 2025-10-14 11:00 | 2025-10-29 13:35 | N | Y |  | Station |  |  | Limits ATC, Pre-Condition
ALTALINK | 749L (648s Metiskow - 749AL tap), 648s 749E (648s Metiskow) | 2025-10-14 12:00 | 2025-10-16 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 678s T2 (678s Okotoks) | 2025-10-14 12:00 | 2025-10-15 17:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 38s C1 (38s East Edmonton) | 2025-10-14 12:30 | 2025-10-15 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre), 717s 701 (717s Ethel Lake), 846s 701 (846s Grand Centre) | 2025-10-14 13:00 | 2025-10-16 16:00 | N | Y |  | Line, Circuit Breaker |  | Back in service a day early as per ATCO | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 753L (65s High River - 253s Blackie), 65s 753E (65s High River), 253s 753W (253s Blackie) | 2025-10-14 13:00 | 2025-10-18 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L132 (767s Oyen - 959s Lanfine), 767s 701 (767s Oyen) | 2025-10-14 13:00 | 2025-10-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 8B138-1A0 (SS-8), 8B138-2A0 (SS-8), 1A10 (SS-8), 2A1 (SS-8) | 2025-10-14 13:30 | 2025-11-04 16:00 | N | N |  | Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, WCLP | 763A1L (1039s Wheatcrest - 763AL tap), 763L (28s West Brooks - 763AL tap), 763AL (447s Enchant - 763A1L tap), 447s 763A (447s Enchant), 158s 763N (158s Vauxhall), 1039s 52-H1 (1039s Wheatcrest), 28s 763X (28s West Brooks), 1039s 89-L1 (1039s Wheatcrest) | 2025-10-14 17:00 | 2025-10-15 08:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 935L (324s Cassils - 356s Milo) | 2025-10-15 06:00 | 2025-10-19 18:00 | N | Y |  | Line |  | Outage extended due to inclement weather. | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ATCO, CNRL | 859s 701 (859s Primrose), 859s 704 (859s Primrose), 859s 701T (859s Primrose), 859s 701TD (859s Primrose) | 2025-10-15 06:30 | 2025-10-18 17:30 | N | Y |  | Circuit Breaker, Transformer, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, DOW | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen), 166s 899N (166s Dow Chemical Fort Saskatchewan) | 2025-10-15 07:00 | 2025-10-17 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
EPCOR | T4 (Poundmaker), 72PM25 (Poundmaker - Meadowlark), PM721 (Poundmaker) | 2025-10-15 07:00 | 2025-10-17 17:00 | N | Y |  | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MHS-6 MH69-604 (MHS-6 CMH Riverview), MHS-6 MH69-T61(MHS-6 Riverview) | 2025-10-15 08:00 | 2025-10-15 16:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 379s T2 (379s Shell Canada Waterton), 379s VR1 (379s Shell Canada Waterton) | 2025-10-15 08:30 | 2025-10-16 16:30 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 788AL (140s Thompson - 788L tap), 788L (898s Heart Lake - 788AL tap), 788L (157s Lac La Biche - 788AL tap), 140s 189 (140s Thompson), 140s 152 (140s Thompson), 140s T1 (140s Thompson) | 2025-10-15 09:00 | 2025-10-15 15:00 | N | Y |  | Line, Switch, Circuit Breaker, Transformer |  |  | Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, TRANSALTA | 245s T1 (245s Seebe) | 2025-10-15 09:00 | 2025-10-21 17:30 | N | N |  | Transformer |  |  | For Information Only
ATCO | 811s 707 (811s Clairmont Lake), 7L68 (730s Rycroft - 811s Clairmont Lake) | 2025-10-15 09:30 | 2025-10-15 17:30 | N | Y |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 801s 905 (801s Anderson) | 2025-10-15 09:30 | 2025-10-16 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 330P 12TC1 (330p Genesee), 330p 805 (330p Genesee) | 2025-10-15 12:00 | 2025-12-06 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 500 kV, Pre-Condition
CMH | MHS-3 MH69-316 (MHS-3 Southridge), MHS-3 C-31 (MH69S-3) | 2025-10-16 08:00 | 2025-10-16 15:00 | N | N |  | Circuit Breaker, Shunts |  |  | Pre-Condition
SUNCOR | 29EDD-61 29PT-653 (29EDD-61 Stony Island), 29EDD-61 30-252-500001 (29EDD-61 Stony Island) | 2025-10-16 08:00 | 2025-11-24 20:00 | N | Y |  | Transformer, Circuit Breaker |  | Delayed as per SUNCOR T&D | 240 kV, Restricts Generation
ENMAX | 5.9TR (SS-5) | 2025-10-16 08:00 | 2025-10-17 14:00 | N | N |  | Transformer |  | Outage returned early | For Information Only
CMH | MHS-6 MH69-608 (MHS-6 CMH Riverview), MHS-6 MH69-T62 (MHS-6 Riverview) | 2025-10-16 08:00 | 2025-10-16 16:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 338s 552 (338s Cherhill) | 2025-10-16 08:30 | 2025-10-16 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L22 (811s Clairmont Lake - 7L88 tap), 811s 708 (811s Clairmont Lake) | 2025-10-16 09:30 | 2025-10-16 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
BCH, ALTALINK | 1L274 (48s Pocaterra - 978s BCH Britt Creek), 48s 887X (48s Pocaterra) | 2025-10-17 07:00 | 2025-10-17 19:00 | Y | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
CMH | MH-12L (MHS-8 Burnside - MHS-6 CMH Riverview), MHS-6 MH69-602 (MHS-6 CMH Riverview) | 2025-10-17 08:00 | 2025-10-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27) | 2025-10-17 08:00 | 2025-10-17 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 749s 704 (749s Flyingshot Lake) | 2025-10-17 09:30 | 2025-10-17 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe), 245s 777X (245s Seebe) | 2025-10-18 07:00 | 2025-10-26 18:00 | N | Y |  | Line, Circuit Breaker | Notes for OC: 1. Ensure the ' To Adjacent RC' flag is selected for this outage to show on the Report for Adjacent RC. 2. Ensure the Outage Category is set as 'Interconnection' and Interconnection 'AB-BC' is selected for this outage to show on the interconnection report. 3. Ensure WebOms entry is done. | Extended due to vault somewhere on line | Creates Radial Feeds, For Information Only, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 7.84L (SS-7 - SS-36), 36.81L (44s Bearspaw Plant - SS-36), 36.1TR (SS-36), 36.3TR (SS-36), 36B138-36BT3 (SS-36), 36B138-36.81 (SS-36), 36B138-7.84 (SS-36), 7B138-7.84 (SS-7), SW83 (SS-36), SW89 (SS-36), SW90 (SS-36), 36MD138-36.1TR (SS-36), 36MD138-36.3TR (SS-36) | 2025-10-18 08:00 | 2025-10-18 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.83L (SS-14 - SS-36), 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36.2TR (SS-36), 36B138-14.83 (SS-36), 36B138-36BT3 (SS-36), 36MD138-36.5TR (SS-36), 36MD138-36.2TR (SS-36), SW84 (SS-36) | 2025-10-19 08:00 | 2025-10-19 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 612L (336s Fincastle - 368s Burdett), 368s 612 (368s Burdett), 336s 612 (336s Fincastle) | 2025-10-20 07:00 | 2025-10-25 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
EPCOR | 805s T3 (805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s J2405 (EP 805s Jasper) | 2025-10-20 07:00 | 2025-10-24 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station), 814s B2402 (814s Bellamy), 814s B2401 (814s Bellamy), 814s BDS19 (814s Bellamy) | 2025-10-20 07:00 | 2025-10-26 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.2TR (SS-11) | 2025-10-20 08:00 | 2025-10-24 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 21.4TR (SS-21), SW64 (SS-21) | 2025-10-20 08:00 | 2025-10-22 16:00 | N | N |  | Transformer, Switch |  |  | Pre-Condition
CMH | 4L (MHS-1 CMH Power Plant - MHS-6 CMH Riverview), MHS-6 MH69-607 (MHS-6 CMH Riverview) | 2025-10-20 08:00 | 2025-10-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition
REDDEER | 217s T1 (217s North Red Deer) | 2025-10-20 08:00 | 2025-10-23 17:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 21.1C (SS-21) | 2025-10-20 08:00 | 2025-10-22 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43) | 2025-10-20 08:00 | 2025-10-20 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 95s T1 (95s Imperal Oil Edmonton) | 2025-10-20 09:00 | 2025-10-23 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-10-20 09:00 | 2025-10-23 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L39 (811s Clairmont Lake - 7LA39 tap), 811s 709 (811s Clairmont Lake) | 2025-10-20 09:30 | 2025-10-20 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 951s SVC (951s Thickwood), 951s 919 (951s Thickwood Hills) | 2025-10-20 12:00 | 2025-10-23 17:00 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 151s T2 (151s Strathmore) | 2025-10-20 14:00 | 2025-10-22 13:00 | N | Y |  | Transformer |  | Returned Early | Restricts Generation
ALTALINK | 368s T2 (368s Burdett), 368s 42 (368s Burdett) | 2025-10-20 14:00 | 2025-10-30 16:00 | N | Y |  | Transformer, Switch |  |  | Restricts Generation
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2025-10-20 14:00 | 2025-10-30 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 759L (87s Gaetz - 276s Prentiss), 276s 759W (276s Prentiss), 87s 552 (87s Gaetz), 87s 652 (87s Gaetz), 87s 759E (87s Gaetz) | 2025-10-21 07:00 | 2025-10-23 18:00 | N | N |  | Line, Circuit Breaker, Switch |  | RTN Oct 23, 2025. | Contingency Requires Mitigation, Pre-Condition
EPCOR | PM2405 (Poundmaker) | 2025-10-21 07:00 | 2025-10-21 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis), 766s 902 (766s Nevis) | 2025-10-21 07:00 | 2025-11-02 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 526L (515s Fed Pipe Judy Creek - 6L126 Tap), 526L (526AL tap - 6L126 tap), 126L1 (6L126 tap), 515s 526 (515s Fed Pipe Judy Creek) | 2025-10-21 08:00 | 2025-10-22 19:00 | N | N |  | Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | Mildred T3 (Syncrude Mildred Lake), 335 (Syncrude Mildred Lake) | 2025-10-21 08:00 | 2025-10-21 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
CMH | MH-20L (MHS-3 Southridge - MHS-6 CMH Riverview), MHS-3 MH138-T34 (MHS-3 Southridge), MHS-6 MH138-T63 (MHS-6 Riverview), MHS-3 MH69-302 (MHS-3 Southridge), MHS-3 MH138-317 (MHS-3 Southridge), MHS-6 MH138-620 (MHS-6 CMH Riverview) | 2025-10-21 08:00 | 2025-10-21 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 13.2TR (SS-13) | 2025-10-21 08:00 | 2025-10-22 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek), 739s 701 (739s Edith Lake), 809s 704 (809s Louise Creek) | 2025-10-21 09:30 | 2025-10-22 17:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 646L (237s Foothills - 678s Okotoks), 678s 646 (678s Okotoks), 237s 646 (237s Foothills) | 2025-10-22 08:00 | 2025-10-22 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
CascadeP | CAS1 Cascade 1 Generator Test, CAS2 Cascade 2 Generator Test | 2025-10-23 00:01 | 2025-10-31 23:59 | N | N |  | Unit
ENMAX, ALTALINK | 21.80L (42s Sarcee - SS-21), 21B138-21.80 (SS-21), 42s 21 (42s Sarcee) | 2025-10-23 08:00 | 2025-10-23 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 723L (69s North Barrhead - 724L tap), 69s 723E (69s North Barrhead) | 2025-10-23 08:00 | 2025-10-23 11:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
SUNCOR | 635EDD-1001 635-752-661 (635EDD-1001) | 2025-10-23 08:00 | 2025-10-23 18:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 850L (525s Carseland - 678s Okotoks), 678s 850 (678s Okotoks), 525s 850N (525s Carseland) | 2025-10-23 08:00 | 2025-10-23 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ENMAX | 23.4TR (SS-23) | 2025-10-23 08:00 | 2025-10-24 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-10-23 10:00 | 2025-10-23 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 69s T4 (69s North Barrhead), 69s 713 (69s North Barrhead), 69s 42 (69s North Barrhead) | 2025-10-23 11:01 | 2025-10-23 14:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 20.82L (SS-20 - SS-21), 21B138-20.82 (SS-21), 20B138-20.82 (SS-20) | 2025-10-23 12:00 | 2025-10-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L230 (69s North Barrhead - 888AL tap), 69s 230W (69s North Barrhead) | 2025-10-23 14:01 | 2025-10-23 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 727L (678s Okotoks - 727AL tap), 678s 727 (678s Okotoks) | 2025-10-24 08:00 | 2025-10-24 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 987s GT2 (987s Clover Bar) | 2025-10-24 08:00 | 2025-10-24 15:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-10-24 10:00 | 2025-10-24 14:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 56L (20s Ghost - 245s Seebe) | 2025-10-24 15:00 | 2025-10-25 | N | N |  | Line |  | Returned early | For Information Only
EPCOR | 330P GT3 (330p Genesee), 330p 1208 (330p Genesee), 330p 1207 (330p Genesee), 330p 12GT3D (330p Genesee) | 2025-10-24 20:00 | 2025-11-10 12:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 500 kV, Contingency Requires Mitigation, Restricts Generation
EPCOR | 987s GT2 (987s Clover Bar) | 2025-10-25 08:00 | 2025-10-27 15:00 | N | Y |  | Transformer |  | Extended again | Restricts Generation
ENMAX | 11.81L (SS-11 - SS-13), 11.4TR (SS-11), 11.1TR (SS-11), 13B138-11.81 (SS-13), 11B138-11.81 (SS-11), 11B138-BT5 (SS-11), 11MD138-11.1TR (SS-11), 11MD138-11.4TR (SS-11) | 2025-10-25 08:00 | 2025-10-26 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition
ENMAX | 13.60L (SS-13 - SS-27), 27.2TR (SS-27), 27B69-13.60 (SS-27), 27MD69-27.2TR (SS-27) | 2025-10-25 08:00 | 2025-10-25 12:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 678s T2 (678s Okotoks), 678s 452 (678s Okotoks) | 2025-10-25 09:00 | 2025-10-25 17:30 | N | N |  | Transformer, Circuit Breaker |  | Completed early | For Information Only
ALTALINK | 77s 652 (77s Sagitawah), 484s Millar Western | 2025-10-25 09:00 | 2025-10-26 17:30 | N | N |  | Circuit Breaker, Station |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 27B69-16.61 (SS-27), 27MD69-27.1TR (SS-27) | 2025-10-25 12:00 | 2025-10-25 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 33.1TR (SS-33), 33B138-33.83 (SS-33) | 2025-10-26 08:00 | 2025-10-26 14:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 33B138-33.84 (SS-33) | 2025-10-26 14:01 | 2025-10-26 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 52s T1 (52s East Industrial), 52s E2401 (52s East Industrial) | 2025-10-27 07:00 | 2025-10-31 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
EPCOR | 72MG16 (Garneau - Meadowlark), G721 (Garneau), G726 (Garneau), M725 (Meadowlark) | 2025-10-27 07:00 | 2025-10-31 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2025-10-27 07:00 | 2025-11-03 07:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 27.2TR (SS-27) | 2025-10-27 08:00 | 2025-10-28 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 26.1TR (SS-26) | 2025-10-27 08:00 | 2025-10-27 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32), 40B138-32.83 (SS-40) | 2025-10-27 08:00 | 2025-11-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 23.3TR (SS-23) | 2025-10-27 08:00 | 2025-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude, ATCO | RL1 (848s Ruth Lake - D05), T2 (D05 Syncrude), D05 517 (D05), D05 513 (D05), D05 78 (D05), D05 518 (D05), D05 517A (D05), D05 513B (D05), D05 509 (D05), 848s RL-1D1 (848s Ruth Lake) | 2025-10-27 08:00 | 2025-10-28 17:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  | Extended by 1 day, | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ALTALINK, ENMAX | 752L (653s Summit - 752AL tap), 653s 752 (653s Summit) | 2025-10-27 08:30 | 2025-10-27 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2025-10-27 09:00 | 2025-11-04 17:00 | Y | Y |  | Line |  |  | 500 kV, Limits ATC
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2025-10-27 09:00 | 2025-11-02 17:00 | Y | N |  | Line |  | Delayed | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 2L112 (BPA Boundary - BCH Nelway), 2D24 (BCH Nelway), 2D2CB7 (BCH Nelway) | 2025-10-27 09:00 | 2025-11-05 17:00 | N | Y |  | Line, Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-10-27 09:00 | 2025-10-30 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 790L (432s Carvel - 790AL tap), 434s 790 (434s Stony Plain) | 2025-10-27 12:30 | 2025-10-30 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 727L (65s High River - 727AL tap), 65s 727N (65s High River) | 2025-10-27 13:00 | 2025-10-30 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L49 (729s Otauwau - 732s Mitsue), 732s 702 (732s Mitsue), 732s 703 (732s Mitsue), 729s 705 (729s Otauwau), 732s 7L49D1 (732s Mitsue) | 2025-10-27 15:00 | 2025-11-10 14:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy), 814s BDS20 (814s Bellamy) | 2025-10-27 19:00 | 2025-11-02 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  | 240BA2 needs to float until put back in service then 240BA3 will come out. | 240 kV, Over/Under Voltage, Pre-Condition
EPCOR | T4 (Rossdale) | 2025-10-28 | 2025-10-29 23:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 805s J2407 (EP 805s Jasper) | 2025-10-28 07:00 | 2025-10-28 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1047L (574s Nilrem - 650s Hansman Lake) | 2025-10-28 07:00 | 2025-10-28 18:00 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
ATCO, FMGW | 1024s PT-6001 (1024s Granlea), 1024s PT-6002 (1024s Granlea), 1024s 952-600001 (1024s Granlea) | 2025-10-28 07:00 | 2025-10-29 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 39s 252 (39s Bickerdike) | 2025-10-28 07:30 | 2025-10-28 12:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 6.82L (SS-6 - SS-41), 41B138-6.82 (SS-41), 6B138-6.82 (SS-6) | 2025-10-28 08:00 | 2025-10-31 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ENMAX | 688L (653s Summit - 688AL tap), 653s 688 (653s Summit) | 2025-10-28 08:30 | 2025-10-28 16:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2025-10-28 09:00 | 2025-10-29 17:00 | Y | Y |  | Line |  |  | Pre-Condition
ATCO | 930s 707 (930s Arcenciel) | 2025-10-28 12:00 | 2025-10-28 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 39s 152 (39s Bickerdike) | 2025-10-28 12:30 | 2025-10-28 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 854L (1012s Deer Hill - 854AL tap), 1012s 854 (1012s Deer Hill) | 2025-10-29 07:30 | 2025-10-29 12:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27), 27.1TR (SS-27), 27B69-16.61 (SS-27), 27MD69-27.1TR (SS-27), 16B69-16.61 (SS-16) | 2025-10-29 08:00 | 2025-10-31 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Lethbridge | 146s 823L (146s Macdonald), 823L (146s MacDonald - 593s Lakeview), 593s 823L (593s Lakeview) | 2025-10-29 08:00 | 2025-10-29 17:00 | N | N |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 31.2TR (SS-31) | 2025-10-29 08:00 | 2025-10-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 813s 705 (813s Little Smoky) | 2025-10-29 09:30 | 2025-10-29 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO, ALTALINK | 1036L (356s Milo - 554s Travers) | 2025-10-30 07:00 | 2025-11-06 18:00 | N | Y |  | Line |  | Start date moved from the 27th to the 29th due to 924L outage extension | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 12 (17s Benalto) | 2025-10-30 08:00 | 2025-10-30 17:30 | N | Y |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 666L (28s West Brooks - 498s Tilley), 498s 666 (498s Tilley) | 2025-10-30 08:30 | 2025-10-30 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition, Affects Cranking Path
ATCO | 813s 706 (813s Little Smoky) | 2025-10-30 09:30 | 2025-10-30 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2025-10-31 07:00 | 2025-11-04 18:00 | N | Y |  | Line |  | Outage extended | 240 kV, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 38.2TR (SS-38) | 2025-10-31 08:00 | 2025-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | UE-1 1521 (UE-1 Syncrude Plant 30-2) | 2025-10-31 08:00 | 2025-10-31 16:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ENMAX | 12.1TR (SS-12) | 2025-10-31 08:00 | 2025-10-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 44s T1 (44s Bearspaw Plant), 44s T2 (44s Bearspaw Plant), 44s 31 (44s Bearspaw Plant), 44s 32 (44s Bearspaw Plant) | 2025-10-31 08:00 | 2025-10-31 13:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | Restricts Generation
ENMAX | 11.82L (SS-11 - SS-14), 11.83L (SS-162 - SS-11), 11.3TR (SS-11), 11.2TR (SS-11), 11B138-11.82 (SS-11), 11B138-11.83 (SS-11), 11B138-BT5 (SS-11) | 2025-11-01 08:00 | 2025-11-02 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | AML 511s ACF12 (AML 511s Crossings) | 2025-11-01 12:00 | 2026-02-01 18:00 | N | Y |  | Shunts |  |  | For Information Only
ENMAX | 33.83L (SS-33 - SS-41), 33B138-33.83 (SS-33), 41B138-33.83 (SS-41) | 2025-11-02 09:00 | 2025-11-04 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L16 (755s Cordel - 972s Tinchebray) | 2025-11-03 06:00 | 2025-11-06 16:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 814s T1 (814s Bellamy), 814s B2401 (814s Bellamy), 814s B2407 (814s Bellamy), BR721 (Rossdale), 814s BAB1 (814s Bellamy) | 2025-11-03 07:00 | 2025-11-09 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 3.82L (SS-3 - SS-8), 3.3TR (SS-3), 3B138-3.82 (SS-3), 3MD138-3.3TR (SS-3) | 2025-11-03 07:00 | 2025-11-04 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (EP Hardisty) | 2025-11-03 07:00 | 2025-11-03 15:53 | N | N |  | Transformer |  | Planned | For Information Only
ENMAX | 2.3TR (SS-2) | 2025-11-03 08:00 | 2025-11-04 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 146s 667 (146s Macdonald) | 2025-11-03 08:00 | 2025-11-03 17:00 | N | Y |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 12.1TR (SS-12) | 2025-11-03 08:00 | 2025-11-04 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 477s 138kV Bus (477s Amoco West Pembina), 841L (477s Amoco West Pembina - 489s Petro-Canada Brazeau River), 844L (358s Amoco Brazeau - 477s Amoco West Pembina), 477s T1 (477s Amoco West Pembina), 477s 841X (477s Amoco West Pembina), 477s 844X (477s Amoco West Pembina), 477s 18 (477s Amoco West Pembina), 477s 19 (477s Amoco West Pembina) | 2025-11-03 09:00 | 2025-11-07 18:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2025-11-03 09:00 | 2025-11-10 16:00 | N | Y |  | Line |  |  | Over/Under Voltage, Overload, Pre-Condition
BCH | T3 (BCH Natal), 12CB23 (BCH Natal) | 2025-11-03 09:00 | 2025-11-06 09:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 38s C1 (38s East Edmonton), 38s 3052 (38s East Edmonton) | 2025-11-03 10:30 | 2025-11-06 17:30 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 749L (899s Edgerton - 749AL tap), 899s 749X (899s Edgerton) | 2025-11-03 12:00 | 2025-11-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 744L (235s Entwistle - 744AL tap), 235s 744W (235s Entwistle) | 2025-11-03 12:00 | 2025-11-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - SS-21), 44s 50X (44s Bearspaw Plant) | 2025-11-03 12:30 | 2025-11-03 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial), 77s 552 (77s Sagitawah), 77s 352 (77s Sagitawah), 364s 798 (364s Whitecourt Industrial), 77s 798N (77s Sagitawah) | 2025-11-03 13:00 | 2025-11-07 11:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 83s T3 (83s Taber), 83s 64 (83s Taber) | 2025-11-03 13:00 | 2025-11-06 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
Saskpower | SaskPower A1R | 2025-11-03 13:00 | 2025-11-06 15:00 | N | Y |  | Line |  | Outage ended early at 15:00 on November 6. | Limits ATC, Pre-Condition
ALTALINK, TRANSALTA | 33s 2 (33s Spray), 33s T2 (33s Spray) | 2025-11-03 14:00 | 2025-11-04 16:00 | N | Y |  | Circuit Breaker, Transformer |  |  | For Information Only, Restricts Generation
ALTALINK | 39s 26 (39s Bickerdike) | 2025-11-03 14:00 | 2025-11-04 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 409s T1 (409s Shell Scotford) | 2025-11-04 07:00 | 2025-11-10 10:00 | N | N |  | Transformer |  |  | For Information Only
Lethbridge | 813L (146s MacDonald - 241s Uplands), 146s 813L (146s Macdonald), 241s 813L (241s Uplands) | 2025-11-04 08:00 | 2025-11-04 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 330p 805 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 1214 (330p Genesee), 330p 1210 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee), 330p 500kV Bus 1 (330p Genesee) | 2025-11-04 08:00 | 2025-11-04 18:00 | N | Y |  | Circuit Breaker, Transformer, Bus |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 633L (56s Boyle - 405s Waupisoo), 405s 633 (405s Waupisoo) | 2025-11-04 08:00 | 2025-11-04 13:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 353s T1 (353s Plamondon), 353s 195 (353s Plamondon) | 2025-11-04 10:00 | 2025-11-04 18:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK | 728L (353s Plamondon - 405s Waupisoo), 405s 728 (405s Waupisoo), 353s 452 (353s Plamondon) | 2025-11-04 13:00 | 2025-11-04 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 72LH8 (EP 803s Lambton - EP Hardisty), T2 (EP Hardisty), H723 (EP Hardisty), H722 (EP Hardisty), HAB2 (EP Hardisty) | 2025-11-05 07:00 | 2025-11-07 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 796L (405s Waupisoo - 796AL tap), 796L (282s Grassland - 796AL tap), 796AL (242s Flat Lake - 796L tap), 405s 796 (405s Waupisoo) | 2025-11-05 08:00 | 2025-11-05 13:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ENMAX | 39.4TR (SS-39) | 2025-11-05 08:00 | 2025-11-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 12.2TR (SS-12) | 2025-11-05 08:00 | 2025-11-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, CascadeP | 1135L (39s Bickerdike - 1047s Whisky Jack), 39s 26 (39s Bickerdike), 39s 29 (39s Bickerdike) | 2025-11-05 08:00 | 2025-11-05 18:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV
ALTALINK, ENMAX | 688L (653s Summit - 688AL tap), 688AL (284s Nose Creek - 688L tap), 284s T1 (284s Nose Creek), 653s 688 (653s Summit) | 2025-11-05 08:00 | 2025-11-05 15:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L587 (822s Wolf Lake - 826s Marguerite Lake), 822s 701 (822s Wolf Lake) | 2025-11-05 09:00 | 2025-11-05 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 421s T1 (421s Hays) | 2025-11-05 09:30 | 2025-11-05 16:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 3.4TR (SS-3) | 2025-11-05 12:00 | 2025-11-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 405s C2 (405s Waupisoo), 405s 23 (405s Waupisoo) | 2025-11-05 13:00 | 2025-11-05 18:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 39s 29 (39s Bickerdike) | 2025-11-05 17:00 | 2025-11-06 18:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 729L (40s Wetaskiwin - 729AL tap), 729L (542s Ervick - 729AL tap), 6500s T1 (6500s Trueweld Grating), 40s 729E (40s Wetaskiwin) | 2025-11-06 07:00 | 2025-11-06 13:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 397s T2 (397s Benbow), 397s 31 (397s Benbow) | 2025-11-06 07:00 | 2025-11-06 13:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 40.1TR (SS-40) | 2025-11-06 08:00 | 2025-11-06 12:00 | N | N |  | Transformer |  |  | For Information Only
CDTP | TLE1 Tilley DER Solar Generator Test | 2025-11-06 08:00 | 2025-12-05 16:00 | N | N |  | Unit
ALTALINK | 405s C1 (405s Waupisoo), 405s 17 (405s Waupisoo) | 2025-11-06 08:00 | 2025-11-06 13:00 | N | N |  | Shunts, Circuit Breaker |  |  | For Information Only, Pre-Condition
BCH | 2L113 (BCH Cranbrook - BCH Natal) | 2025-11-06 09:00 | 2025-11-06 12:59 | N | Y |  | Line | MARGO override created on Oct 14, 2025 (JH) (combined with second 2L113 record) |  | Limits ATC, Pre-Condition
ENMAX | 6.1TR (SS-6) | 2025-11-06 12:00 | 2025-11-06 16:00 | N | N |  | Transformer |  |  | For Information Only
BCH | 2L113 (BCH Cranbrook - BCH Natal), T3 (BCH Natal), T4 (BCH Natal), 12CB23 (BCH Natal) | 2025-11-06 13:00 | 2025-11-18 17:00 | N | Y |  | Line, Transformer, Circuit Breaker | MARGO override created on Oct 14, 2025 (JH) (combined with second 2L113 record) |  | Limits ATC, Pre-Condition
ALTALINK | 40s T2 (40s Wetaskiwin) | 2025-11-06 13:00 | 2025-11-06 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L117 (706s Irish Creek - 710s Vermilion), 710s 701 (710s Vermilion), 706s 703 (706s Irish Creek) | 2025-11-07 08:00 | 2025-11-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 31.2TR (SS-31) | 2025-11-07 08:00 | 2025-11-07 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.3TR (SS-31) | 2025-11-07 12:01 | 2025-11-07 14:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.1TR (SS-31) | 2025-11-07 14:01 | 2025-11-07 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28.2TR (SS-28), 28B138-28.80 (SS-28), 42s 28 (42s Sarcee), 28MD138-28.2TR (SS-28), SW82 (SS-28) | 2025-11-08 08:00 | 2025-11-16 15:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.83L (SS-1 - SS-8), 8B138-3A0 (SS-8), 8B138-4A0 (SS-8), 4A1 (SS-8), 3A10 (SS-8), 3A01 (SS-8) | 2025-11-09 07:00 | 2025-11-10 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 41.84L (SS-41 - SS-54), 41B138-41.84 (SS-41), 54B138-41.84 (SS-54) | 2025-11-09 09:00 | 2025-11-15 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | T3 (Rossdale), R723 (Rossdale), R724 (Rossdale), RAB3 (Rossdale) | 2025-11-10 07:00 | 2025-11-19 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | M724 (Meadowlark) | 2025-11-10 07:00 | 2025-11-15 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 35.2TR (SS-35) | 2025-11-10 08:00 | 2025-11-10 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 32.83L (SS-32 - SS-40), 26.81L (SS-26 - SS-32), 32.1TR (SS-32), 32B138-26.81 (SS-32), 32B138-32.83 (SS-32) | 2025-11-10 08:00 | 2025-11-13 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge), 216s 32 (216s Knightsbridge), 184s 705W (184s Petro-Canada Edmonton) | 2025-11-10 11:00 | 2025-11-14 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 35.1TR (SS-35) | 2025-11-10 12:00 | 2025-11-10 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell) | 2025-11-11 07:00 | 2025-11-16 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow), 397s T1 (397s Benbow), 397s 138kV Bus 1 (397s Benbow), 347s 720X (347s AML Fox Creek), 397s 720N (397s Benbow), 397s 39 (397s Benbow) | 2025-11-11 09:00 | 2025-11-14 17:00 | N | N |  | Line, Transformer, Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 931L (28s West Brooks - 132s Ware Junction) | 2025-11-11 09:30 | 2025-11-13 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 805s T3 (805s Jasper) | 2025-11-12 07:00 | 2025-11-12 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 216s T3 (216s Knightsbridge), 216s 552 (216s Knightsbridge) | 2025-11-12 07:00 | 2025-11-13 23:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 987s CC24 (987s Clover Bar) | 2025-11-12 07:00 | 2025-11-12 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s 757N (17s Benalto) | 2025-11-12 07:00 | 2025-11-12 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.85L (SS-1 - SS-8), 8B138-1A0 (SS-8), 8B138-2A0 (SS-8) | 2025-11-12 07:00 | 2025-11-14 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2MD138-2.1CAP (SS-2), 2B138-D95 (SS-2), 2B138-D96 (SS-2), MD109 (SS-2), MD110 (SS-2) | 2025-11-12 08:00 | 2025-11-13 16:00 | N | N |  | Switch, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2025-11-12 08:00 | 2025-11-13 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 20.1TR (SS-20), 20BA8-20.1TR (SS-20), 20BB8-20.1TR (SS-20) | 2025-11-12 08:00 | 2025-12-19 16:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L85 (803s ATC Bullpound - 7LA85 tap) | 2025-11-12 14:00 | 2025-11-15 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 987s CC13 (987s Clover Bar) | 2025-11-13 07:00 | 2025-11-14 17:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 789L (898s Heart Lake - 789BL tap) | 2025-11-13 08:00 | 2025-11-13 17:45 | N | N |  | Line |  |  | For Information Only
ENMAX | 3.3TR (SS-3) | 2025-11-13 08:00 | 2025-11-13 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, Travers2SolarLP | 1005AL (991s Little Bow - 1005L tap), 1005L (120s Picture Butte - 1005AL tap), 1005L (356s Milo - 1005AL tap), 991s Little Bow, 991s 240-1 (991s Little Bow), 991s 34-1 (991s Little Bow), 991s 34-11 (991s Little Bow), 991s 34-13 (991s Little Bow), 991s 34-15 (991s Little Bow), 991s 34-17 (991s Little Bow), 991s 34-3 (991s Little Bow), 991s 34-5 (991s Little Bow), 991s 34-7 (991s Little Bow), 991s 34-9 (991s Little Bow) | 2025-11-13 08:00 | 2025-11-13 18:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 142s 138kV Bus (142s Magcan), 142s C1 (142s Magcan) | 2025-11-13 08:30 | 2025-11-13 17:30 | N | N |  | Bus, Shunts |  |  | Pre-Condition
ALTALINK | 1005L (356s Milo - 1005AL tap) | 2025-11-13 18:00 | 2025-11-24 12:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Pre-Condition
ALTALINK | 612L (336s Fincastle - 368s Burdett), 336s 612 (336s Fincastle), 368s 612 (368s Burdett) | 2025-11-14 07:00 | 2025-11-19 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1053L (132s Ware Junction - 324s Cassils) | 2025-11-14 09:30 | 2025-12-03 18:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.83L (SS-1 - SS-8), 8B138-3A0 (SS-8), 8B138-4A0 (SS-8) | 2025-11-15 07:00 | 2025-11-17 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 162B240-RB131 (SS-162), 162B240-RB132 (SS-162), 1-GSU-XF-0001 (SS-162) | 2025-11-15 08:00 | 2025-11-16 14:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L85 (804s Wintering Hills - 7LA85 tap), 804s 702 (804s Wintering Hills) | 2025-11-16 08:00 | 2025-11-16 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 814s T2 (814s Bellamy), 814s B2402 (814s Bellamy), 814s B2406 (814s Bellamy), BR722 (Rossdale) | 2025-11-17 07:00 | 2025-11-23 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 409s T2 (409s Shell Scotford) | 2025-11-17 07:00 | 2025-11-21 08:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 162B240-RB135 (SS-162), 162B240-RB134 (SS-162), 2-GSU-XF-0002 (SS-162) | 2025-11-17 08:00 | 2025-11-18 14:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | C1 (Aurora) | 2025-11-17 08:00 | 2025-11-18 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 24.82L (SS-24 - SS-65), 24.2TR (SS-24), 24B138-24.82 (SS-24), 65B138-D81 (SS-65), 65B138-D82 (SS-65), 24B138-24BT3 (SS-24) | 2025-11-17 08:00 | 2025-11-17 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
BCH | T3 (BCH Natal), 2CB1 (BCH Natal) | 2025-11-17 09:00 | 2025-11-18 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO, ALTALINK | 9L913 (69s North Barrhead - 732s Mitsue), 732s 903 (732s Mitsue), 732s 904 (732s Mitsue), 69s 913N (69s North Barrhead) | 2025-11-17 09:00 | 2025-11-20 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2025-11-17 09:00 | 2025-11-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 7L106 (834s Wesley Creek - 905s Meikle) | 2025-11-17 10:00 | 2025-11-21 12:20 | N | Y |  | Line |  | Planned outage. | For Information Only, Pre-Condition
ATCO | 7L90 (741s ATC Fox Creek - 7LA90 tap), 741s 701 (741s ATC Fox Creek) | 2025-11-17 10:00 | 2025-11-23 09:29 | N | N |  | Line, Circuit Breaker |  | Scheduled Outage | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L131 (834s Wesley Creek - 905s Meikle), 834s 708 (834s Wesley Creek), 834s 710 (834s Wesley Creek), 834s 7L131D2 (834s Wesley Creek) | 2025-11-17 10:00 | 2025-11-21 11:50 | N | Y |  | Line, Circuit Breaker, Switch |  | Planned outage. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 184s 34 (184s Petro-Canada Edmonton) | 2025-11-17 11:30 | 2025-11-21 10:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 225s T1 (225s Magrath), 863L (225s Magrath - 891L tap), 225s 4 (225s Magrath), 225s 863 (225s Magrath) | 2025-11-17 11:30 | 2025-11-18 16:30 | N | N |  | Transformer, Line, Circuit Breaker, Switch |  |  | Impacts RAS, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 29s T2 (29s Cascade) | 2025-11-17 12:00 | 2025-11-28 18:30 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7), 42s 7 (42s Sarcee) | 2025-11-17 14:00 | 2025-11-20 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 312s 852 (312s Fidler) | 2025-11-18 08:00 | 2025-11-18 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 16.61L (SS-16 - SS-27), 27B69-16.61 (SS-27), 16B69-16.61 (SS-16) | 2025-11-18 08:00 | 2025-11-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, BPWF | 1097L (356s Milo  611s Amber), 356s 1097 (356s Milo), 611s T1 (611s Amber), 611s T2 (611s Amber), 611s 52-240-1 (611s Amber), 611s 52-240-2 (611s Amber), 611s 89-B1 (611s Amber), 611s 89-T1 (611s Amber), 611s 89-T2 (611s Amber) | 2025-11-18 08:30 | 2025-11-18 12:30 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | 240 kV, Restricts Generation
BCH | T4 (BCH Natal) | 2025-11-18 13:00 | 2025-11-28 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L749 (716s Lloydminster - 7LB749 tap), 716s 701 (716s Lloydminster) | 2025-11-19 07:00 | 2025-11-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 312s 952 (312s Fidler) | 2025-11-19 08:00 | 2025-11-19 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 412s T1 (412s Shell Eagle Creek) | 2025-11-19 09:00 | 2025-11-19 15:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 312s 552 (312s Fidler) | 2025-11-20 08:00 | 2025-11-20 15:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
NWE, BHE Canada, BHE | Hay Lake (NorthWestern Energy) - Marias (MATL), North Series Capacitor (BHE Hay Lake), Marias Shunt Capacitor, 2302 (NWE Marias), 2305 (NWE Marias) | 2025-11-21 07:00 | 2025-11-25 18:00 | N | Y |  | Line, Shunts, Circuit Breaker | MARGO Override created on Nov 5, 2025 (GM) |  | 240 kV, Limits ATC
ENMAX | 3.3TR (SS-3) | 2025-11-21 08:00 | 2025-11-21 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.3TR (SS-38) | 2025-11-21 08:00 | 2026-01-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 678s T2 (678s Okotoks), 678s 452 (678s Okotoks) | 2025-11-21 08:30 | 2025-11-21 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | 2CB2 (BCH Nelway) | 2025-11-21 09:00 | 2025-11-21 15:06 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 9L56 (720s Wabasca - 732s Mitsue), 732s 904 (732s Mitsue), 732s 906 (732s Mitsue) | 2025-11-21 09:00 | 2025-11-24 16:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 7L65 (710s Vermilion - 7LA65 tap), 710s 703 (710s Vermilion) | 2025-11-21 09:30 | 2025-11-21 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon) | 2025-11-21 18:00 | 2025-11-23 08:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon), 5s 1552 (5s East Calgary), 5s 1652 (5s East Calgary) | 2025-11-21 18:00 | 2025-11-23 08:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L129 (710s Vermilion - 7LA129 tap), 710s 704 (710s Vermilion) | 2025-11-22 08:00 | 2025-12-03 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 562s 1352 (562s Cypress) | 2025-11-22 08:30 | 2025-11-22 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 562s 1452 (562s Cypress) | 2025-11-22 13:01 | 2025-11-22 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1041L (370s North Lethbridge - 554s Travers), 370s 1041 (370s North Lethbridge) | 2025-11-23 03:00 | 2025-11-23 20:40 | N | Y |  | Line, Switch |  | The line was returned to service early at 20:40 on November 23. | 240 kV, Contingency Requires Mitigation
ENMAX | 24.2TR (SS-24) | 2025-11-23 08:00 | 2025-11-23 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | AL-2 (Aurora - D05 Syncrude), 222 (Aurora), 223 (Aurora), D05 514 (D05), D05 511 (D05), D05 512 (D05), 222A (Aurora), 222B (Aurora), 223A (Aurora), 223B (Aurora), 89-225 (Aurora), D05 511A (D05), D05 511B (D05), D05 512A (D05), D05 512B (D05) | 2025-11-23 08:00 | 2025-11-29 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 562s 1652 (562s Cypress) | 2025-11-23 08:30 | 2025-11-23 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 40.81L (SS-40 - SS-41), 41B138-40.81 (SS-41), 40B138-40.81 (SS-40) | 2025-11-23 09:00 | 2025-11-26 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 562s 1752 (562s Cypress) | 2025-11-23 13:00 | 2025-11-23 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 864L (397s Benbow - 864AL tap), 397s 864W (397s Benbow) | 2025-11-23 16:01 | 2025-12-09 09:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK, EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia), 816s PDS14 (816s Petrolia) | 2025-11-24 07:00 | 2025-11-28 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10.1TR (SS-10), 10B138-832 (SS-10), 10MD138-10.1TR (SS-10) | 2025-11-24 07:00 | 2025-12-02 12:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 72NW15 (Namao - Woodcroft), W723 (Woodcroft), N726 (Namao) | 2025-11-24 07:00 | 2025-12-05 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 803s T3 (EP 803s Lambton), EP 803s L721 (EP 803s Lambton), 72LH8 (EP 803s Lambton - EP Hardisty), 72LS24 (EP 803s Lambton - Strathcona) | 2025-11-24 07:00 | 2025-11-30 17:00 | N | Y |  | Transformer, Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 14.83L (SS-14 - SS-36), 14B138-14.83 (SS-14) | 2025-11-24 08:00 | 2025-11-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 562s 1852 (562s Cypress) | 2025-11-24 08:30 | 2025-11-24 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 2075s ACF21 (2075s Newell), 2075s 902T (2075s Newell), 2075S 930 (2075s Newell) | 2025-11-24 09:00 | 2025-12-01 13:00 | N | Y |  | Shunts, Transformer, Circuit Breaker |  | Return to service Dec 01, 2025. | 240 kV, Pre-Condition
ALTALINK | 606L (184s Petro-Canada Edmonton - 185s Bretville), 184s 606 (184s Petro-Canada Edmonton) | 2025-11-24 11:00 | 2025-11-28 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, Travers2SolarLP | 1005AL (991s Little Bow - 1005L tap), 1005L (120s Picture Butte - 1005AL tap), 1005L (356s Milo - 1005AL tap), 991s Little Bow, 991s 240-1 (991s Little Bow), 991s 34-1 (991s Little Bow), 991s 34-11 (991s Little Bow), 991s 34-13 (991s Little Bow), 991s 34-15 (991s Little Bow), 991s 34-17 (991s Little Bow), 991s 34-3 (991s Little Bow), 991s 34-5 (991s Little Bow), 991s 34-7 (991s Little Bow), 991s 34-9 (991s Little Bow) | 2025-11-24 12:00 | 2025-11-24 18:00 | N | Y |  | Line, Station, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK, SHELL | 409s T3 (409s Shell Scotford), 409s 1252 (409s Shell Scotford) | 2025-11-24 12:00 | 2025-12-03 08:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 562s 2052 (562s Cypress) | 2025-11-24 13:00 | 2025-11-24 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 42s 80 (42s Sarcee) | 2025-11-24 13:30 | 2025-11-27 16:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7L129 (710s Vermilion - 7LA129 tap), 710s 704 (710s Vermilion) | 2025-11-24 14:00 | 2025-11-27 13:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 1005L (120s Picture Butte - 1005AL tap) | 2025-11-24 18:01 | 2025-12-04 08:30 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
NWE | 2366 (NWE Marias), 2365 (NWE Marias), 2302 (NWE Marias) | 2025-11-25 | 2026-01-07 | N | N |  | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 814s T1 (814s Bellamy), BR721 (Rossdale), 814s B2401 (814s Bellamy), 814s B2407 (814s Bellamy), 814s BAB1 (814s Bellamy) | 2025-11-25 07:00 | 2025-11-29 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 759L (87s Gaetz - 276s Prentiss), 87s 759E (87s Gaetz), 276s 759W (276s Prentiss), 87s 552 (87s Gaetz), 87s 652 (87s Gaetz) | 2025-11-25 07:00 | 2025-12-06 16:15 | N | N |  | Line, Switch, Circuit Breaker |  | RTS Early | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 391s 25 (391s Balzac) | 2025-11-25 07:30 | 2025-11-26 12:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 62s 31 (62s Brazeau Plant), 62s T3 (62s Brazeau Plant) | 2025-11-25 08:00 | 2025-11-25 13:00 | N | Y |  | Circuit Breaker, Transformer |  |  | 240 kV
CapitalPower | HAL2 Halkirk 2 Generator Test | 2025-11-25 08:00 | 2025-12-06 17:00 | N | N |  | Unit
ENMAX | 1.80L (SS-1 - SS-28), 28.1TR (SS-28), 28B138-1.80 (SS-28) | 2025-11-25 08:00 | 2025-11-25 14:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 562s 152 (562s Cypress) | 2025-11-25 08:30 | 2025-11-25 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 33s 5 (33s Spray) | 2025-11-25 09:00 | 2025-11-25 12:00 | N | Y |  | Switch |  |  | For Information Only, Restricts Generation
ATCO | 783s 701T (783s Cadotte River), 783s 701TD (783s Cadotte River) | 2025-11-25 10:30 | 2025-11-26 16:00 | N | N |  | Transformer, Switch |  |  | For Information Only
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2025-11-25 13:00 | 2025-11-25 16:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 562s 252 (562s Cypress) | 2025-11-25 13:00 | 2025-11-25 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s C1 (62s Brazeau Plant) | 2025-11-25 13:01 | 2025-11-25 18:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 876s 901T (876s Brintnell) | 2025-11-25 17:46 | 2026-09-18 18:00 | N | Y |  | Transformer |  | Extended til Jan 25, 2026 as per ATCO | 240 kV
ENMAX | 2B138-D86 (SS-2) | 2025-11-26 08:00 | 2025-11-26 10:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 62s 995X (62s Brazeau Plant), 995L (62s Brazeau Plant Plant - 995AL tap) | 2025-11-26 08:00 | 2025-11-26 17:30 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 562s 1052 (562s Cypress) | 2025-11-26 08:30 | 2025-11-26 13:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 13L50L2 (2029s Heathfield - 2075s Newell) | 2025-11-26 09:00 | 2025-11-28 16:00 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake) | 2025-11-26 09:00 | 2025-11-26 17:00 | Y | Y |  | Line |  |  | 500 kV, Limits ATC
ENMAX | 2B138-D87 (SS-2) | 2025-11-26 10:00 | 2025-11-26 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 562s 1152 (562s Cypress) | 2025-11-26 13:00 | 2025-11-26 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 2B138-D88 (SS-2) | 2025-11-26 13:00 | 2025-11-26 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s T1 (62s Brazeau Plant) | 2025-11-26 23:00 | 2025-11-27 03:00 | N | Y |  | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 62s T2 (62s Brazeau Plant) | 2025-11-27 03:00 | 2025-11-27 07:00 | N | Y |  | Transformer |  |  | 240 kV, Restricts Generation
ENMAX | 2B138-D89 (SS-2) | 2025-11-27 08:00 | 2025-11-27 10:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 409s 20 (409s Shell Scotford) | 2025-11-27 08:00 | 2025-11-27 11:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ENMAX | 33.84L (SS-33 - SS-43) | 2025-11-27 08:00 | 2025-12-01 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 790L (432s Carvel - 790AL tap), 432s 790 (432s Carvel) | 2025-11-27 08:00 | 2025-11-27 15:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2B138-D90 (SS-2) | 2025-11-27 10:01 | 2025-11-27 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2B138-D85 (SS-2) | 2025-11-27 13:01 | 2025-11-27 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, DOW | 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydrocarbons), 166s 862N (166s Dow Chemical Fort Saskatchewan) | 2025-11-28 06:15 | 2025-11-28 17:45 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 2B138-D83 (SS-2) | 2025-11-28 08:00 | 2025-11-28 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2025-11-28 08:00 | 2025-11-28 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2B138-D84 (SS-2) | 2025-11-28 12:01 | 2025-11-28 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon), 5s 1552 (5s East Calgary), 5s 1652 (5s East Calgary) | 2025-11-28 18:00 | 2025-11-30 12:47 | N | Y |  | Line, Circuit Breaker |  | Completed early | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ENMAX, ALTALINK | 936L (5s East Calgary - 102s Langdon) | 2025-11-28 18:00 | 2025-11-30 12:47 | N | Y |  | Line |  | Completed early | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
Syncrude, ATCO | RL2 (848s Ruth Lake - D05), D05 512 (D05), D05 513 (D05), D05 512B (D05), D05 513B (D05), 848s RL-2D1 (848s Ruth Lake) | 2025-11-30 08:00 | 2025-12-09 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L23 (732s Mitsue - 7L23 tap), 732s 703 (732s Mitsue), 732s 707 (732s Mitsue), 732s 7L23D4 (732s Mitsue), 796s 702 (796s Nipisi) | 2025-11-30 09:00 | 2025-12-03 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar), 987s C2404 (987s Clover Bar), 987s C2406 (987s Clover Bar) | 2025-12-01 07:00 | 2025-12-05 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2025-12-01 07:00 | 2025-12-04 17:00 | N | Y |  | Line |  |  | 240 kV, For Information Only
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 814s B2401 (814s Bellamy), 814s B2402 (814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2025-12-01 07:00 | 2025-12-04 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 31.84L (SS-31 - SS-32), 31B138-31.84 (SS-31), 32B138-31.84 (SS-32) | 2025-12-01 08:00 | 2025-12-17 10:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
ENMAX | 2B138-D81 (SS-2) | 2025-12-01 08:00 | 2025-12-01 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2025-12-01 08:00 | 2025-12-01 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 39.82L (SS-39 - SS-162), 22.81L (SS-22 - SS-39), 39.2TR (SS-39), 39.4TR (SS-39), 22B138-22.81 (SS-22), 39B138-22.81 (SS-39), 39B138-39.82 (SS-39), SW83 (SS-39), 39MD138-39.2TR (SS-39), 39MD138-39.4TR (SS-39) | 2025-12-01 08:00 | 2025-12-19 12:30 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (48s Pocaterra - 978s BCH Britt Creek) | 2025-12-01 09:00 | 2025-12-16 17:00 | Y | Y |  | Line |  | Delayed | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 428s T2 (428s Namaka), 428s 652 (428s Namaka) | 2025-12-01 09:30 | 2025-12-01 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 314L (207s Pinedale - 228s T.M.P.L. Niton), 207s 314 (207s Pinedale), 228s 314 (228s T.M.P.L. Niton) | 2025-12-01 09:30 | 2025-12-02 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 9L56 (720s Wabasca - 876s Brintnell), 876s 904 (876s Brintnell), 876s 902 (876s Brintnell), 876S 902B (876s Brintnell), 876S 904B (876s Brintnell), 720s 9L56D3 (720s Wabasca) | 2025-12-01 10:00 | 2025-12-02 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ENMAX | 2B138-D82 (SS-2) | 2025-12-01 12:01 | 2025-12-01 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Lafarge Canada | 985s T3 (985s Exshaw) | 2025-12-02 07:00 | 2025-12-02 19:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 607L (135s Conrad - 607AL tap), 135s T1 (135s Conrad), 135s T2 (135s Conrad), 135s Conrad, 135s 252 (135s Conrad), 135s 152 (135s Conrad), 135s 289 (135s Conrad), 135s 689 (135s Conrad), 135s 352 (135s Conrad), 135s 389 (135s Conrad) | 2025-12-02 07:00 | 2025-12-03 18:00 | N | Y |  | Line, Transformer, Station, Circuit Breaker, Switch |  |  | Pre-Condition, Restricts Generation
ALTALINK | 706L (410s Josephburg - 706AL tap) | 2025-12-02 07:15 | 2025-12-02 12:45 | N | N |  | Line |  |  | Pre-Condition, Affects Cranking Path
ENMAX | 26B138-26BT3 (SS-26) | 2025-12-02 08:00 | 2025-12-02 12:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ATCO | 9L99 (801s Anderson - 807s Sheerness), 801s 906 (801s Anderson), 801S 906A (801s Anderson), 801s 907 (801s Anderson), 801S 907A (801s Anderson) | 2025-12-02 08:30 | 2025-12-03 18:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Restricts Generation, Affects Cranking Path
ENMAX | 6.80L (SS-6 - SS-35), 6B138-6.80 (SS-6) | 2025-12-02 12:00 | 2025-12-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 422s 700 (422s Westwood), 746s 700N (746s Sherwood Park) | 2025-12-02 12:46 | 2025-12-02 18:15 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 10B138-693 (SS-10), 693L (42s Sarcee - SS-10), 10.2TR (SS-10), 10MD138-10.2TR (SS-10) | 2025-12-02 13:00 | 2025-12-11 13:00 | N | Y |  | Circuit Breaker, Line, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 706L (410s Josephburg - 706AL tap) | 2025-12-03 08:00 | 2025-12-03 12:00 | N | N |  | Line |  |  | Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock) | 2025-12-03 09:00 | 2025-12-03 17:30 | N | Y |  | Line |  |  | 500 kV, Pre-Condition
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock), 510s R3 (510s Sunnybrook), 510s 2852 (510s Sunnybrook), 510s 2952 (510s Sunnybrook), 510s 7689 (510s Sunnybrook), 510s 1241 (510s Sunnybrook), 939s 12L41D1 (939s Livock) | 2025-12-03 09:00 | 2025-12-03 17:30 | N | Y |  | Line, Shunts, Circuit Breaker, Switch |  |  | 500 kV, Overload, Pre-Condition
ALTALINK | 890L (58s Edson - 207s Pinedale), 58s 890 (58s Edson), 207s 890 (207s Pinedale) | 2025-12-03 09:30 | 2025-12-08 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux), 38s 761N (38s East Edmonton) | 2025-12-03 12:15 | 2025-12-03 17:45 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 233s 138kV Bus 1 (233s Beamer), 233s T1 (233s Beamer), 233s 6 (233s Beamer) | 2025-12-04 07:00 | 2025-12-04 15:00 | N | N |  | Bus, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 254s T2 (254s Coaldale), 254s 35 (254s Coaldale) | 2025-12-04 07:00 | 2025-12-04 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition
ATCO, ALTALINK | 807AL (402s Scotford Expansion One - 807L tap), 807L (233s Beamer - 807AL tap), 807L (410s Josephburg - 807AL tap), 233s 807X (233s Beamer) | 2025-12-04 07:00 | 2025-12-09 16:00 | N | N |  | Line, Circuit Breaker |  | Completed early | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 861L (71s Lamoureux - 258s Dow Hydrocarbons), 258s 152 (258s Dow Hydrocarbons), 258s 252 (258s Dow Hydrocarbons) | 2025-12-04 07:15 | 2025-12-04 13:45 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson), 811s 710 (811s Clairmont Lake) | 2025-12-04 08:00 | 2025-12-04 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, Travers2SolarLP | 1005AL (991s Little Bow - 1005L tap), 1005L (120s Picture Butte - 1005AL tap), 1005L (356s Milo - 1005AL tap), 991s 240-1 (991s Little Bow), 991s T1 (991s Little Bow), 991s T2 (991s Little Bow), 991s T3 (991s Little Bow), 991s T1B1 (991s Little Bow), 991s T2B1 (991s Little Bow), 991s T3B1 (991s Little Bow) | 2025-12-04 08:31 | 2025-12-04 15:00 | N | Y |  | Line, Circuit Breaker, Transformer, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 9L16 (755s Cordel - 972s Tinchebray) | 2025-12-04 09:00 | 2025-12-04 10:59 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 931L (28s West Brooks - 132s Ware Junction) | 2025-12-04 11:00 | 2025-12-19 18:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 665s T3 (665s Dome), 665s D2404 (665s Dome) | 2025-12-05 07:00 | 2025-12-05 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 703L (213s Hughenden - 703BL tap), 213s 703 (213s Hughenden) | 2025-12-05 07:15 | 2025-12-05 13:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2025-12-05 08:00 | 2025-12-05 16:00 | N | Y |  | Line | this is split from the record CROW #1-00498736 |  | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee), 330p 1210 (330p Genesee), 330p 1214 (330p Genesee), 330p 805 (330p Genesee) | 2025-12-06 07:00 | 2025-12-06 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 729L (285s East Camrose - 542s Ervick), 285s 729W (285s East Camrose) | 2025-12-06 07:15 | 2025-12-06 12:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 174L (197s Bardo - 395s North Holden), 395s 174W (395s North Holden), 197s 174E (197s Bardo) | 2025-12-06 12:46 | 2025-12-06 18:15 | N | N |  | Line, Circuit Breaker |  |  | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 801L (62s Brazeau Plant - 294s Brazeau Plant Outlet Works), 62s 201 (62s Brazeau Plant) | 2025-12-07 07:15 | 2025-12-07 13:45 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR, ALTALINK | 657s T3 (657s Summerside), 657s SU2401 (657s Summerside), 657s SU2405 (657s Summerside), 657s SUAB3 (657s Summerside) | 2025-12-08 07:00 | 2025-12-08 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR, ALTALINK | 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 1055L (629s Argyll Transfer Station - 816s Petrolia), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy), 814s BDS20 (814s Bellamy) | 2025-12-08 07:00 | 2025-12-11 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX | 2.80L (SS-2 - SS-23), 23B138-2.80 (SS-23) | 2025-12-08 08:00 | 2025-12-08 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (SS-16 - SS-27) | 2025-12-08 08:00 | 2025-12-08 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
FORTIS | DUS1 Duchess DER Solar Generator Test | 2025-12-08 08:00 | 2025-12-09 17:00 | N | N |  | Unit
ATCO | 7L135 (820s Hangingstone - 977s Salt Creek), 977s 901T (977s Salt Creek) | 2025-12-08 10:00 | 2025-12-09 17:30 | N | Y |  | Line, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 719L (263s Strachan - 719AL tap), 263s 719 (263s Strachan) | 2025-12-08 11:30 | 2025-12-08 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L40 (732s Mitsue - 809s Louise Creek), 732s 901 (732s Mitsue), 732s 902 (732s Mitsue), 732s 9L40D2 (732s Mitsue), 732s 902B (732s MItsue), 732s 901B (732s MItsue) | 2025-12-08 13:00 | 2025-12-11 17:13 | N | Y |  | Line, Circuit Breaker, Switch |  | Returned early | 240 kV, Contingency Requires Mitigation, Over/Under Voltage
EPCOR | T1 (Kennedale) | 2025-12-09 07:00 | 2025-12-09 17:00 | N | N |  | Transformer |  |  | Pre-Condition
EPCOR, ALTALINK | 657s T2 (657s Summerside), 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside) | 2025-12-09 07:00 | 2025-12-10 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 38s 7252 (38s East Edmonton) | 2025-12-09 07:00 | 2025-12-12 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, PR | 949L (275s Jenner - 306s Halsbury), 275s 949 (275s Jenner), 306s 240MDS4 (306s Halsbury) | 2025-12-09 07:00 | 2025-12-09 17:24 | N | Y |  | Line, Circuit Breaker, Switch |  | Back early | 240 kV, Restricts Generation
ALTALINK | 263s C1 (263s Strachan) | 2025-12-09 07:30 | 2025-12-09 12:30 | N | N |  | Shunts |  |  | For Information Only
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (SS-36) | 2025-12-09 08:00 | 2025-12-09 16:00 | N | N |  | Line, Transformer |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
BCH, BPA | 5L52 (BPA Custer - BCH Ingledow) | 2025-12-09 08:00 | 2025-12-17 16:00 | N | Y |  | Line |  |  | 500 kV, Limits ATC, Pre-Condition
ALTALINK | 864AL (346s Kaybob - 864L tap), 864BL (355s Chevron Knight - 864L tap), 864L (397s Benbow - 864AL tap), 864L (551s Chevron Kaybob - 864BL tap), 864L (864AL tap - 864BL tap), 685L (397s Benbow - 1012s Deer Hill), 551s T1 (551s Chevron Kaybob), 346s T1 (346s Kaybob), 355s T1 (355s Chevron Knight), 355s T2 (355s Chevron Knight), 1012s 685 (1012s Deer Hill), 397s 864W (397s Benbow), 397s 685 (397s Benbow) | 2025-12-09 08:00 | 2025-12-09 18:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 8.3TR (SS-8) | 2025-12-09 08:00 | 2025-12-09 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, ATCO | 830L (562s Cypress - 840s McNeill Station), 840s 901T (840s McNeill Station), 840s 701 (840s McNeill Station), 840s 703 (840s McNeill Station), 840s 701T (840s McNeill Station), 840s 702C (840s McNeill Station), 840s 703C (840s McNeill Station), 840S 7L830D1 (840s McNeill Station), 562s 830 (562s Cypress) | 2025-12-09 11:00 | 2025-12-09 16:00 | Y | Y |  | Line, Transformer, Circuit Breaker, Shunts, Switch |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 263s 870E (263s Strachan), 262s 870W (262s Rocky Mountain House) | 2025-12-09 12:30 | 2025-12-10 17:30 | N | N |  | Line, Circuit Breaker |  | Extended | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L130 (705s Kitscoty - 710s Vermilion), 710s 702 (710s Vermilion), 705s 704 (705s Kitscoty) | 2025-12-10 07:00 | 2025-12-11 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 263s 652 (263s Strachan) | 2025-12-10 07:30 | 2025-12-10 12:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16) | 2025-12-10 08:00 | 2025-12-10 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
RESC | FRM1 Forty Mile Bow Island | 2025-12-10 08:00 | 2025-12-10 19:00 | N | Y |  | Unit |  |  | Restricts Generation
CapitalPower | HAL2 Halkirk 2 Generator Test | 2025-12-10 08:00 | 2025-12-12 17:00 | N | N |  | Unit
ATCO | 7L22 (790s Poplar Hill - 7L88 tap), 790s 702 (790s Poplar Hill) | 2025-12-10 09:30 | 2025-12-10 17:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 700s 705C (700s Bonnyville) | 2025-12-10 10:00 | 2025-12-10 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 6L73 (729s Otauwau - 745s Slave Lake) | 2025-12-11 | 2025-12-17 18:00 | N | N |  | Line |  |  | Pre-Condition
EPCOR | T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft), WDS3 (Woodcroft) | 2025-12-11 07:00 | 2025-12-12 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 205s 352 (205s Castle Rock Ridge) | 2025-12-11 07:30 | 2025-12-11 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s T3 (63s Red Deer), 63s 26 (63s Red Deer) | 2025-12-11 08:00 | 2025-12-11 10:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 700s 706C (700s Bonnyville) | 2025-12-11 09:00 | 2025-12-11 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), 510s T11 (510s Sunnybrook), AML 511s T11 (AML 511s Crossings), 510s 2652 (510s Sunnybrook), 510s 2752 (510s Sunnybrook), 510s 41 (510s Sunnybrook), 510s 40 (510s Sunnybrook), 510s 43 (510s Sunnybrook), 510s 44 (510s Sunnybrook), 510s 4289 (510s Sunnybrook), AML 511s 1489 (AML 511s Crossings), 510s Protection & Control (510s Sunnybrook) | 2025-12-11 10:00 | 2025-12-11 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch, Terminal Equipment |  |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 205s 452 (205s Castle Rock Ridge) | 2025-12-11 12:31 | 2025-12-11 17:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 832L (SS-10 - SS-12), 10.1TR (SS-10), 10B138-832 (SS-10), 10MD138-10.1TR (SS-10), Protection & Control (SS-10) | 2025-12-11 14:00 | 2025-12-11 18:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 310p T30 (310p Sundance) | 2025-12-12 01:30 | 2026-01-20 18:00 | N | Y |  | Transformer |  | Extended | 240 kV
EPCOR | EP 511s V724 (EP 511s Victoria) | 2025-12-12 07:00 | 2025-12-12 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 205s 152 (205s Castle Rock Ridge) | 2025-12-12 07:30 | 2025-12-12 12:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21) | 2025-12-12 08:00 | 2025-12-12 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 20.82L (SS-20 - SS-21), 21.80L (42s Sarcee - SS-21), 21.1TR (SS-21), 21.4TR (SS-21), 21B138-20.82 (SS-21), 21B138-21.80 (SS-21), 21B69-21.4TR (SS-21), 20B138-20.82 (SS-20), 42s 21 (42s Sarcee), 21MD138-21.1TR (SS-21), 21MD138-21.4TR (SS-21), SW64 (SS-21) | 2025-12-13 08:00 | 2025-12-14 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-34 260kV Bus 29PP-45 (29EDD-34), 29PL9-13 (29EDD-34 - 29EDD-65), 29EDD-34 29-952-112 (29EDD-34), 29EDD-34 29-952-113 (29EDD-34), 29EDD-34 29-952-123 (29EDD-34), 29EDD-34 29-952-133 (29EDD-34), 29EDD-34 29-952-143 (29EDD-34), 29EDD-65 29PS-0266 (29EDD-65 Edd65Sub) | 2025-12-13 08:00 | 2025-12-16 16:00 | N | Y |  | Bus, Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43) | 2025-12-13 08:00 | 2025-12-13 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | AML 511s SVC Plus (AML 511s Crossings) | 2025-12-14 03:00 | 2025-12-21 17:00 | N | Y |  | Shunts |  |  | For Information Only
EPCOR | 72KN23 (Kennedale - Namao), 72CK12 (987s Clover Bar - Kennedale), K724 (Kennedale), K723 (Kennedale) | 2025-12-15 07:00 | 2025-12-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | RW2405 (EP Riverview) | 2025-12-15 07:00 | 2025-12-15 15:00 | N | Y |  | Circuit Breaker |  | Back Early | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 72 kV Bus 2 (Rossdale), 72RW3 (Rossdale - Woodcroft), 72RV4 (EP 511s Victoria - Rossdale), 72RG7 (Garneau - Rossdale), RW727 (Rossdale), VHBB1 (Rossdale), VHBB2 (Rossdale), RG725 (Rossdale), RV726 (Rossdale), EP 511s VDS15 (EP 511s Victoria), GDS4 (Garneau), G725 (Garneau), G722 (Garneau), M723 (Meadowlark) | 2025-12-15 07:00 | 2025-12-19 17:00 | N | N |  | Bus, Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 16.60L (SS-16 - SS-34) | 2025-12-15 08:00 | 2025-12-15 16:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.5TR (SS-5) | 2025-12-15 08:00 | 2025-12-15 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 833L (SS-2 - SS-12), 12.2TR (SS-12), 12B138-833L (SS-12), 12MD138-12.2TR (SS-12), SW83 (SS-12), 2MD138-833L (SS-2) | 2025-12-15 08:00 | 2025-12-15 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 744L (235s Entwistle - 744AL tap), 235s 744W (235s Entwistle) | 2025-12-15 09:00 | 2025-12-16 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 31.1C (SS-31) | 2025-12-15 09:00 | 2025-12-15 15:46 | N | N |  | Shunts |  | Back Early | Pre-Condition
Saskpower | SASK POWER P2C | 2025-12-15 09:00 | 2025-12-16 16:59 | N | Y |  | Line |  |  | Pre-Condition
ENMAX, ALTALINK | 833L (SS-2 - SS-12) | 2025-12-15 09:00 | 2025-12-15 16:00 | N | Y |  | Line |  |  | For Information Only, Affects Cranking Path
ATCO | 959s SVC (959s Lanfine), 959s 921 (959s Lanfine) | 2025-12-15 10:00 | 2025-12-16 17:30 | N | Y |  | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 535s 6452 (535s Joffre) | 2025-12-15 11:30 | 2025-12-15 17:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 58s C1 (58s Edson) | 2025-12-15 15:00 | 2026-01-07 15:45 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 225L (67s Stirling - 225AL tap), 67s 225 (67s Stirling) | 2025-12-16 08:00 | 2025-12-22 09:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (SS-33 - SS-41), 41B138-33.83 (SS-41), 33B138-33.83 (SS-33) | 2025-12-16 08:00 | 2025-12-16 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2025-12-16 08:00 | 2025-12-16 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.82L (SS-1 - SS-5) | 2025-12-16 09:00 | 2025-12-16 12:00 | N | N |  | Line
ALTALINK | 267s T1 (267s Killarney Lake), 267s 3 (267s Killarney Lake), 267s 2054X (267s Killarney Lake), 267s 2120W (267s Killarney Lake), 267s 14 (267s Killarney Lake) | 2025-12-16 11:00 | 2025-12-18 13:30 | N | N |  | Transformer, Switch, Circuit Breaker |  |  | For Information Only
ENMAX | 54.81L (SS-54 - SS-65), 54B138-54.81 (SS-54) | 2025-12-16 12:01 | 2025-12-16 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.84L (SS-1 - SS-5) | 2025-12-16 12:01 | 2025-12-16 16:00 | N | N |  | Line |  |  | Pre-Condition
SUNCOR | 29EDD-34 260kV Bus 29PP-45 (29EDD-34), 29EDD-34 29-952-113 (29EDD-34), 29EDD-34 29-952-123 (29EDD-34), 29EDD-34 29-952-133 (29EDD-34), 29EDD-34 29-952-143 (29EDD-34) | 2025-12-16 16:01 | 2026-01-04 07:59 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Saskpower | SASK POWER P2C | 2025-12-16 17:00 | 2025-12-16 22:00 | N | N |  | Line |  |  | Pre-Condition
ENMAX | 2B138-D91 (SS-2) | 2025-12-17 08:00 | 2025-12-17 11:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 744L (228s T.M.P.L. Niton - 744AL tap), 228s 744 (228s T.M.P.L. Niton) | 2025-12-17 09:00 | 2025-12-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 813s SVC (813s Little Smoky), 813s 719 (813s Little Smoky) | 2025-12-17 09:30 | 2025-12-17 15:10 | N | Y |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2025-12-17 10:00 | 2025-12-17 14:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ENMAX | 2B138-D93 (SS-2) | 2025-12-17 11:01 | 2025-12-17 13:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 2B138-D94 (SS-2) | 2025-12-17 13:01 | 2025-12-17 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (BCH Elkford - BCH Elkford tap) | 2025-12-17 21:00 | 2025-12-17 22:00 | N | N |  | Line | MARGO posting done Dec 11, 2025 (GM) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 1L274 (BCH Elkford - BCH Elkford tap) | 2025-12-18 04:00 | 2025-12-18 05:00 | N | N |  | Line | MARGO posting done Dec 11, 2025 (GM) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 2B138-D95 (SS-2) | 2025-12-18 08:00 | 2025-12-18 11:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2025-12-18 10:00 | 2025-12-18 14:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 199L (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek) | 2025-12-18 11:00 | 2025-12-18 13:55 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 2B138-D96 (SS-2) | 2025-12-18 11:00 | 2025-12-18 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
CMH | MH-30L (MHS-3 Southridge - MHS-5 NE Crescent Heights), MHS-3 MH69-308 (MHS-3 Southridge), MHS-5 MH69-502 (MHS-5 NE Crescent Heights) | 2025-12-19 06:00 | 2025-12-19 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAXGPI | CRS2 Summit- Crossfield Generator Test | 2025-12-19 07:00 | 2025-12-19 17:00 | N | N |  | Unit
ENMAX | 2.82L (SS-2 - SS-5), 5B138-2.82 (SS-5) | 2025-12-19 08:00 | 2025-12-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
NWE, BHE Canada, BHE | Hay Lake (NorthWestern Energy) - Marias (MATL), North Series Capacitor (BHE Hay Lake), Marias Shunt Capacitor, 2302 (NWE Marias), 2305 (NWE Marias) | 2025-12-19 08:00 | 2025-12-19 13:00 | N | N |  | Line, Shunts, Circuit Breaker | MARGO override event created December 16th, 2025. |  | 240 kV, Limits ATC
ENMAX | 1MD138-1.84 (SS-1) | 2025-12-22 08:00 | 2026-06-27 16:00 | N | N |  | Switch |  |  | For Information Only
ENMAX | 1MD138-1.82 (SS-1) | 2025-12-22 08:00 | 2026-06-27 16:00 | N | N |  | Switch |  |  | For Information Only
ENMAX | 1MD138-1.80 (SS-1) | 2025-12-22 08:00 | 2026-03-20 16:00 | N | N |  | Switch |  |  | For Information Only
ENMAX | 1MD138-1.81 (SS-1) | 2025-12-22 08:00 | 2026-03-20 16:00 | N | N |  | Switch |  |  | For Information Only
ENMAX | 7.84L (SS-7 - SS-36), 36B138-7.84 (SS-36) | 2025-12-22 08:00 | 2025-12-22 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ICPCL | 225L (225s Magrath - 225AL tap), 225L (67s Stirling - 225AL tap), 225AL tap, 313s T1 (313s Raymond Reservoir), 225s 225E (225s Magrath), 67s 225 (67s Stirling), 313s 52M (313s Raymond Reservoir) | 2025-12-22 09:01 | 2025-12-22 18:00 | N | N |  | Line, Station, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 102s SVC (102s Langdon), 102s T4 (102s Langdon), 102s 252 (102s Langdon), 102s 552 (102s Langdon), 102s 7189 (102s Langdon) | 2025-12-31 15:02 | 2026-01-06 09:22 | N | Y |  | Shunts, Transformer, Circuit Breaker, Switch | Note for OC: BC wants to be aware of this outage and prefers to see in the interconnection report. OC to select the outage category as 'Interconnection' and select Interconnection as 'AB-BC', so that this outage shows up on the Interconnection report. |  | 240 kV, Pre-Condition
Saskpower, ATCO | Sask Power S1M Line, 840s McNeill Station | 2025-12-31 20:20 | 2026-01-06 11:24 | N | Y |  | Line, Station |  |  | Limits ATC, Pre-Condition
SUNCOR | 29EDD-34 260kV Bus 29PP-45 (29EDD-34), 29EDD-34 29-952-113 (29EDD-34), 29EDD-34 29PS-216 (29EDD-34) | 2026-01-04 08:00 | 2026-09-02 16:00 | N | Y |  | Bus, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L48 (794s Valleyview - 7LA48 tap), 794s 703 (794s Valleyview) | 2026-01-05 08:00 | 2026-01-29 12:40 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 1.80L (SS-1 - SS-28), 28B138-1.80 (SS-28) | 2026-01-05 08:00 | 2026-03-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 1.81L (SS-1 - SS-20), 20B138-1.81 (SS-20) | 2026-01-05 08:00 | 2026-03-21 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 9L40 (732s Mitsue - 809s Louise Creek) | 2026-01-05 10:00 | 2026-01-12 17:00 | N | Y |  | Line |  | . | 240 kV, Over/Under Voltage
ATCO | 732s 902T (732s Mitsue), 732s 503R (732s Mitsue) | 2026-01-06 08:00 | 2026-01-09 17:00 | N | Y |  | Transformer, Shunts |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2026-01-06 19:46 | 2026-01-12 15:49 | Y | Y |  | Station, Line |  | Outage done early on January 12. | Limits ATC, Pre-Condition
ATCO | 7L92 (709s Vegreville - 7LA92 tap), 709s 705 (709s Vegreville) | 2026-01-07 08:00 | 2026-01-07 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 35.81L (42s Sarcee - SS-35), 35B138-81 (SS-35), 42s 35 (42s Sarcee), 35MD138-81 (SS-35), 35MD138-83 (SS-35), 35MD138-35.81 (SS-35) | 2026-01-07 08:00 | 2026-01-08 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 931L (28s West Brooks - 132s Ware Junction) | 2026-01-07 08:00 | 2026-01-20 18:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ATCO | 9L59 (801s Anderson - 9LA59 tap) | 2026-01-07 09:00 | 2026-01-07 11:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
Syncrude | 815 (Syncrude Mildred Lake), 816 (Syncrude Mildred Lake) | 2026-01-08 08:00 | 2026-01-19 16:00 | N | N |  | Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 5.1TR (SS-5) | 2026-01-08 08:00 | 2026-01-08 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 719L (263s Strachan - 719AL tap), 719L (719AL tap - 719BL tap), 764L (304s Shell Limestone - 581s Amoco Ricinus), 719AL (581s Amoco Ricinus - 719L tap), 719BL (634s Shell Raven River - 719L tap), 304s T1 (304s Shell Limestone), 304s T2 (304s Shell Limestone), 581s T1 (581s Amoco Ricinus), 634s T1 (634s Shell Raven River), 378s 719N (378s Shell Caroline) | 2026-01-08 09:00 | 2026-01-08 09:30 | N | N |  | Line, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2026-01-08 09:00 | 2026-01-08 11:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 719L (263s Strachan - 719AL tap), 263s 719 (263s Strachan) | 2026-01-08 09:31 | 2026-01-25 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L53 (700s Bonnyville - 7LA53 tap), 700s 702 (700s Bonnyville) | 2026-01-08 10:00 | 2026-01-08 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 42s C2 (42s Sarcee) | 2026-01-08 15:00 | 2026-03-30 14:00 | N | Y |  | Shunts |  | Delayed | 240 kV, Pre-Condition
ENMAX | 5.6TR (SS-5) | 2026-01-09 08:00 | 2026-01-09 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T1 (Namao), N721 (Namao), N722 (Namao), NDS8 (Namao), NAB1 (Namao) | 2026-01-12 07:00 | 2026-01-14 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 314L (207s Pinedale - 228s T.M.P.L. Niton), 207s 314 (207s Pinedale), 228s 314 (228s T.M.P.L. Niton) | 2026-01-12 07:15 | 2026-01-16 08:00 | N | N |  | Line, Circuit Breaker |  | Extended till Jan 16 08:00 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Overload, Pre-Condition
ENMAX | 33.84L (SS-33 - SS-43), 43.2TR (SS-43), 33B138-33.84 (SS-33), 43B138-33.84 (SS-43), 43MD138-43.2TR (SS-43), SW84 (SS-43) | 2026-01-12 08:00 | 2026-01-13 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.3TR (SS-32) | 2026-01-12 08:00 | 2026-01-30 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 264s 240kV Bus 2 (264s Elkwater), 264s 352 (264s Elkwater) | 2026-01-12 13:00 | 2026-01-15 17:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 827L (28s West Brooks - 121s Brooks), 121s 827W (121s Brooks) | 2026-01-12 13:00 | 2026-01-15 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
EPCOR | EP 511s V724 (EP 511s Victoria) | 2026-01-13 07:00 | 2026-01-13 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 799L (77s Sagitawah - 443s South Mayerthorpe) | 2026-01-13 07:00 | 2026-01-13 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, DOS Calldown, Firm Load Loss, Pre-Condition
ALTALINK | 377s 473C (377s AML Hardisty) | 2026-01-13 08:30 | 2026-01-15 17:00 | N | N |  | Shunts |  | extended outage by crew | Pre-Condition
ENMAX | 38.1TR (SS-38) | 2026-01-13 10:00 | 2026-01-13 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 38.2TR (SS-38) | 2026-01-13 12:30 | 2026-01-13 14:30 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 511s V722 (EP 511s Victoria) | 2026-01-14 07:00 | 2026-01-14 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2026-01-14 07:00 | 2026-01-31 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 43.1TR (SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43), SW83 (SS-43), 43MD138-43.1TR (SS-43) | 2026-01-14 08:00 | 2026-01-16 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 37.81L (SS-37 - SS-38), 38.2TR (SS-38), 38.3TR (SS-38), 38B138-37.81 (SS-38), 38.1C (SS-38), SW83 (SS-38) | 2026-01-14 08:00 | 2026-01-14 10:00 | N | N |  | Line, Transformer, Circuit Breaker, Shunts, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.2TR (SS-162) | 2026-01-14 11:00 | 2026-01-24 17:00 | N | Y |  | Transformer |  | Delayed a week as per Enmax | 240 kV
ALTALINK | 62s T1 (62s Brazeau Plant) | 2026-01-14 23:00 | 2026-01-15 03:00 | N | Y |  | Transformer |  |  | Restricts Generation
ALTALINK | 62s T2 (62s Brazeau Plant) | 2026-01-15 03:00 | 2026-01-15 07:00 | N | Y |  | Transformer |  |  | Restricts Generation
EPCOR | EP 511s V723 (EP 511s Victoria) | 2026-01-15 07:00 | 2026-01-15 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 267s T1 (267s Killarney Lake) | 2026-01-15 12:00 | 2026-01-15 15:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72VN21 (EP 511s Victoria - Namao), N725 (Namao) | 2026-01-16 07:00 | 2026-01-17 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 5.5TR (SS-5) | 2026-01-16 08:00 | 2026-01-16 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA | 33s T2 (33s Spray) | 2026-01-17 08:00 | 2026-01-18 17:00 | N | Y |  | Transformer |  |  | Restricts Generation
ATCO, ALTALINK | 840s McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2026-01-17 11:00 | 2026-01-24 17:00 | Y | Y |  | Station, Line
BHE Canada | 120s C2 (120s Picture Butte) | 2026-01-17 11:00 | 2026-04-30 17:00 | N | Y |  | Shunts |  | forced outage | Pre-Condition
ALTALINK | 831L (121s Brooks - 831AL tap), 831L (339s Duchess - 831AL tap), 831AL (227s Cutting Lake - 831L tap), 339s T1 (339s Duchess), 121s 831N (121s Brooks), 227s 831AW (227s Cutting Lake), 339s 831 (339s Duchess) | 2026-01-18 07:00 | 2026-01-18 15:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia), 178s 202N (178s Cynthia), 58s 202X (58s Edson) | 2026-01-19 06:00 | 2026-01-20 17:45 | N | N |  | Line, Circuit Breaker |  | Requested time change as per Altalink | Overload, Pre-Condition
EPCOR | 72CN10 (987s Clover Bar - Namao), T3 (Namao), N723 (Namao), N724 (Namao), NDS11 (Namao), NAB3 (Namao) | 2026-01-19 07:00 | 2026-01-21 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Overload, Pre-Condition
EPCOR | 711L (113s Inland Cement - 747L tap), 113s T1 (113s Inland Cement), 113s T2 (113s Inland Cement), 113s 711N (113s Inland Cement), 113s 1 (113s Inland Cement), 113s 5 (113s Inland Cement) | 2026-01-19 07:00 | 2026-01-29 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  | done early | For Information Only
EPCOR | 72RV2 (EP 511s Victoria - Rossdale), RV728 (Rossdale) | 2026-01-19 07:00 | 2026-01-23 17:00 | N | N |  | Line, Circuit Breaker |  |  | Overload
ENMAX | 5.10TR (SS-5) | 2026-01-19 08:00 | 2026-01-19 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 6.82L (SS-6 - SS-41), 33.83L (SS-33 - SS-41), 41.2TR (SS-41), 41.1C (SS-41), 41B138-41BT3 (SS-41), 41B138-6.82 (SS-41), 41B138-33.83 (SS-41), 6B138-6.82 (SS-6), 33B138-33.83 (SS-33), 41MD138-41.2TR (SS-41) | 2026-01-19 08:00 | 2026-01-22 16:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 12.2TR (SS-12) | 2026-01-19 08:00 | 2026-01-19 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 511s V721 (EP 511s Victoria) | 2026-01-20 07:00 | 2026-01-21 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2026-01-20 08:00 | 2026-01-20 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 5.9TR (SS-5) | 2026-01-20 08:00 | 2026-01-20 16:00 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 162B138-RB94 (SS-162) | 2026-01-20 08:00 | 2026-01-20 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 20.1TR (SS-20), 20BA8-20.1TR (SS-20), 20BB8-20.1TR (SS-20) | 2026-01-21 08:00 | 2026-01-22 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 5.7TR (SS-5) | 2026-01-21 08:00 | 2026-10-30 16:00 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 3.4TR (SS-3) | 2026-01-21 08:00 | 2026-01-21 12:00 | N | N |  | Transformer |  |  | Pre-Condition
ENMAX | 14.3TR (SS-14) | 2026-01-21 08:00 | 2026-01-23 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | EP 511s V729 (EP 511s Victoria) | 2026-01-22 07:00 | 2026-01-22 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 922L (17s Benalto - 310p Sundance), 310p 1952 (310p Sundance), 310p 2052 (310p Sundance) | 2026-01-22 07:00 | 2026-01-22 18:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 202L (61s Lodgepole - 62s Brazeau Plant), 61s 202X (61s Lodgepole), 62s 202 (62s Brazeau Plant) | 2026-01-22 07:15 | 2026-01-22 17:45 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Affects Cranking Path
BCH | 2CB9 (BCH Cranbrook) | 2026-01-22 08:00 | 2026-01-23 16:00 | N | Y |  | Circuit Breaker |  |  | For Information Only
BCH | 2L294 (BCH A. A. Lambert - BCH Cranbrook), T3 (BCH Cranbrook) | 2026-01-22 10:00 | 2026-01-22 17:00 | N | Y |  | Line, Transformer | MARGO updated: Jan 22, 2026 (GM) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 926L (17s Benalto - 310p Sundance), 310p 2552 (310p Sundance), 310p 2652 (310p Sundance) | 2026-01-22 19:00 | 2026-01-23 18:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
BCH | 5L98 (BCH Nicola - BCH Vaseux Lake), 5CB5 (BCH Nicola), 5CB25 (BCH Nicola) | 2026-01-23 09:00 | 2026-01-23 17:00 | Y | Y |  | Line, Circuit Breaker |  |  | 500 kV, Limits ATC
ATCO | 9L57 (939s Livock - 960s Birchwood Creek) | 2026-01-24 09:00 | 2026-01-26 08:59 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ENMAX | 20.3TR (SS-20) | 2026-01-25 08:00 | 2026-01-30 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 557s CD2403 (557s Castle Downs), 557s CD2401 (557s Castle Downs) | 2026-01-26 07:00 | 2026-01-30 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
NWE | NWMT Highwood-Judith Gap Auto 230kV Line | 2026-01-26 07:00 | 2026-01-30 16:30 | N | Y |  | Line |  |  | 240 kV, Pre-Condition
EPCOR | T2 (Namao), N722 (Namao), N723 (Namao), NAB2 (Namao) | 2026-01-26 07:00 | 2026-01-28 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Rossdale), R723 (Rossdale), R724 (Rossdale), RAB3 (Rossdale) | 2026-01-26 07:01 | 2026-02-19 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 314L (207s Pinedale - 228s T.M.P.L. Niton), 207s 314 (207s Pinedale), 228s 314 (228s T.M.P.L. Niton) | 2026-01-26 07:15 | 2026-01-29 17:45 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 13.82L (SS-13 - SS-22), 22.3TR (SS-22), 22.1TR (SS-22), 13B138-13.82 (SS-13), 22B138-22BT8 (SS-22), 22B138-13.82 (SS-22), 22MD138-22.1TR (SS-22), SW83 (SS-22), 22MD138-22.3TR (SS-22), SW84 (SS-22) | 2026-01-26 08:00 | 2026-01-28 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 35.1TR (SS-35), 35B138-81 (SS-35), 35B138-82 (SS-35), 35MD138-84 (SS-35), 35MD138-86 (SS-35), 35MD138-35.1TR (SS-35) | 2026-01-26 08:00 | 2026-01-27 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L57 (939s Livock - 960s Birchwood Creek) | 2026-01-26 09:00 | 2026-02-04 15:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 804L (40s 803L tap - 86s 803L tap), 804L (40s Wetaskiwin - 40s 803L tap), 804L (86s Bigstone - 86s 803L tap), 40s 804W (40s Wetaskiwin), 804L-Pseudo (86s Bigstone), 86s 852 (86s Bigstone) | 2026-01-26 09:00 | 2026-01-26 18:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 854L (39s Bickerdike - 854AL tap), 39s 152 (39s Bickerdike), 39s 252 (39s Bickerdike), 39s 854N (39s Bickerdike) | 2026-01-27 07:00 | 2026-01-27 13:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 207s T1 (207s Pinedale) | 2026-01-27 07:45 | 2026-01-27 13:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L574 (822s Wolf Lake - 7L574 tap), 822s 702 (822s Wolf Lake) | 2026-01-27 10:00 | 2026-01-30 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 740s 703T (740s H.R.Milner), 740s 507C (740s H.R.Milner), 740s 703 (740s H.R. Milner), 740s 503 (740s H.R. Milner) | 2026-01-27 14:00 | 2026-02-05 14:00 | N | N |  | Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2029s T11 (2029s Heathfield), 2075s T11 (2075s Newell), 2075s 916 (2075s Newell), 2075s 917 (2075s Newell), 2029s 1206 (2029s Heathfield), 2029s 1205 (2029s Heathfield) | 2026-01-27 14:00 | 2026-01-28 17:00 | N | Y |  | Line, Transformer, Circuit Breaker |  |  | 500 kV, Overload, Pre-Condition, Restricts Generation
ALTALINK | 618s 863X (618s Riverbend), 863L (618s Riverbend - 891L tap) | 2026-01-27 17:00 | 2026-01-29 19:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
EPCOR | EP 511s V728 (EP 511s Victoria) | 2026-01-28 07:00 | 2026-01-28 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | B138-85 (SS-1), B138-86 (SS-1) | 2026-01-28 07:30 | 2026-01-29 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ENMAX | 35.2TR (SS-35), 35B138-80 (SS-35), 35B138-83 (SS-35), 35MD138-80 (SS-35), 35MD138-90 (SS-35), 35MD138-92 (SS-35) | 2026-01-28 08:00 | 2026-01-29 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 9L59 (801s Anderson - 9LA59 tap) | 2026-01-28 09:00 | 2026-01-28 11:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
EPCOR | EP 511s V726 (EP 511s Victoria) | 2026-01-29 07:00 | 2026-01-29 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 22.81L (SS-22 - SS-39), 22.2TR (SS-22), 22B138-22BT8 (SS-22), SW85 (SS-22), 22B138-22.81 (SS-22), 22MD138-22.2TR (SS-22), 39B138-22.81 (SS-39) | 2026-01-29 08:00 | 2026-01-30 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 199L (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek), 741s 702 (741s ATC Fox Creek) | 2026-01-29 10:00 | 2026-01-29 11:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 854L (39s Bickerdike - 854AL tap) | 2026-01-29 11:00 | 2026-01-30 18:00 | N | N |  | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, ATCO | 199L (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek), 741s 702 (741s ATC Fox Creek) | 2026-01-31 10:00 | 2026-01-31 11:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs), 557s CD2405 (557s Castle Downs), 557s CD2404 (557s Castle Downs) | 2026-02-02 07:00 | 2026-02-06 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 72CH11 (987s Clover Bar - EP Hardisty), T1 (EP Hardisty), H725 (EP Hardisty), H722 (EP Hardisty), HAB1 (EP Hardisty) | 2026-02-02 07:00 | 2026-02-06 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 719L (719AL tap - 719BL tap) | 2026-02-02 07:00 | 2026-02-14 18:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 202AL tap), 61s 202N (61s Lodgepole) | 2026-02-02 07:30 | 2026-02-02 17:30 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 15.60L (SS-15 - SS-21), 21.61L (SS-21 - SS-34), 21.4TR (SS-21), 15B69-15.60 (SS-15), 21B69-15.60 (SS-21), 34B69-21.61 (SS-34), 21B69-21.61 (SS-21), 21B69-21.4TR (SS-21) | 2026-02-02 08:00 | 2026-02-04 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 6.80L (SS-6 - SS-35), 35B138-82 (SS-35), 35B138-83 (SS-35), 6B138-6.80 (SS-6), 35MD138-6.80 (SS-35), 35MD138-86 (SS-35), 35MD138-87 (SS-35), 35MD138-89 (SS-35), 35MD138-90 (SS-35) | 2026-02-02 08:00 | 2026-02-03 16:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.3TR (SS-3) | 2026-02-02 08:00 | 2026-02-02 12:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 770s 705C (770s Three Hills) | 2026-02-02 10:00 | 2026-02-04 13:00 | N | N |  | Shunts |  | Scheduled Outage | Pre-Condition
ALTALINK | 397s 138kV Bus 1 (397s Benbow), 720L (347s AML Fox Creek - 397s Benbow), 714L (397s Benbow  1117s South Kaybob), 397s T1 (397s Benbow), 347s 720X (347s AML Fox Creek) | 2026-02-02 10:00 | 2026-02-02 11:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 217s C1 (217s North Red Deer) | 2026-02-02 11:30 | 2026-02-06 16:30 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 202L (61s Lodgepole - 202AL tap), 61s 202N (61s Lodgepole) | 2026-02-02 16:15 | 2026-02-18 13:00 | N | N |  | Line, Circuit Breaker |  | Extended as per TFO request | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK, AESO-SC | 685L (397s Benbow - 1012s Deer Hill), 397s 685 (397s Benbow), 1012s 685 (1012s Deer Hill), 714L1 (714L tap), 685L-Pseudo (397s Benbow) | 2026-02-03 07:00 | 2026-02-18 09:59 | N | N |  | Line, Circuit Breaker, Switch |  | Extended as per TFO request | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | EP 511s V721 (EP 511s Victoria) | 2026-02-03 07:00 | 2026-02-03 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | EP 511s V722 (EP 511s Victoria) | 2026-02-04 07:00 | 2026-02-04 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47B138-771/1 (SS-47) | 2026-02-04 08:00 | 2026-02-05 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ENMAX | 14.1TR (SS-14) | 2026-02-04 08:00 | 2026-02-06 16:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 932s 705A (932s Pemukan), 932s 708B (932s Pemukan) | 2026-02-04 22:30 | 2026-02-07 14:00 | N | N |  | Switch |  |  | For Information Only
ATCO, ALTALINK | 9L913 (69s North Barrhead - 732s Mitsue), 69s 913N (69s North Barrhead) | 2026-02-05 07:00 | 2026-02-09 11:59 | N | Y |  | Line, Circuit Breaker |  | Poor weather conditions so work could not be completed on February 8th | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
EPCOR | EP 511s V723 (EP 511s Victoria) | 2026-02-05 07:00 | 2026-02-05 17:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 922L (17s Benalto - 310p Sundance), 310p 1952 (310p Sundance), 310p 2052 (310p Sundance) | 2026-02-05 07:00 | 2026-02-05 18:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 24.82L (SS-24 - SS-65), 65B138-D81 (SS-65), 65B138-D82 (SS-65) | 2026-02-05 08:00 | 2026-02-05 16:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 926L (17s Benalto - 310p Sundance), 310p 2552 (310p Sundance), 310p 2652 (310p Sundance) | 2026-02-05 19:00 | 2026-02-06 18:30 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe), 235s 799N (235s Entwistle) | 2026-02-08 07:00 | 2026-04-01 12:40 | N | N |  | Line, Circuit Breaker |  | Done early | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | T2 (EP Hardisty), H722 (EP Hardisty), H723 (EP Hardisty), HAB2 (EP Hardisty) | 2026-02-09 07:00 | 2026-02-13 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | G721 (Garneau) | 2026-02-09 07:00 | 2026-02-09 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
EPCOR | T2 (EP Riverview), RW2402 (EP Riverview), RW2403 (EP Riverview) | 2026-02-09 07:00 | 2026-02-14 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 14.2TR (SS-14) | 2026-02-09 08:00 | 2026-02-12 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | G722 (Garneau) | 2026-02-09 12:00 | 2026-02-09 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ATCO | 9L57 (939s Livock - 960s Birchwood Creek) | 2026-02-09 12:00 | 2026-02-18 13:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
Lafarge Canada | L300 (1020s Exshaw extension - 985s Exshaw), 1020s T1 (1020s Exshaw Extension), 985s 811QC04 (985s Exshaw) | 2026-02-10 07:00 | 2026-02-10 19:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | G723 (Garneau) | 2026-02-10 07:00 | 2026-02-10 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK | 714L (397s Benbow  1117s South Kaybob), 397s 714 (397s Benbow) | 2026-02-10 07:30 | 2026-02-10 12:30 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 26.81L (SS-26 - SS-32), 32B138-26.81 (SS-32), 26B138-26.81 (SS-26) | 2026-02-10 08:00 | 2026-02-10 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2026-02-10 09:30 | 2026-02-10 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L14 (705s Kitscoty - 751s Hill), 705s 703 (705s Kitscoty), 751s 701 (751s Hill) | 2026-02-10 10:00 | 2026-02-10 14:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | G724 (Garneau) | 2026-02-10 12:00 | 2026-02-10 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ENMAX | 32B138-32BT5 (SS-32) | 2026-02-10 12:00 | 2026-02-10 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | G725 (Garneau) | 2026-02-11 07:00 | 2026-02-11 12:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK | 397s 31 (397s Benbow), 397s T2 (397s Benbow) | 2026-02-11 07:30 | 2026-02-11 12:30 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ENMAX | 32.2TR (SS-32) | 2026-02-11 08:00 | 2026-02-11 12:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 250p 1 (250p Bighorn Plant) | 2026-02-11 10:00 | 2026-02-11 14:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
EPCOR | G726 (Garneau) | 2026-02-11 12:01 | 2026-02-11 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK | 397s T1 (397s Benbow), 397s 39 (397s Benbow) | 2026-02-11 12:31 | 2026-02-11 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only, Pre-Condition
ALTALINK | 700L (422s Westwood - 746L tap), 700L (746s Sherwood Park - 746L tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2026-02-12 07:00 | 2026-02-12 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 397s 864W (397s Benbow) | 2026-02-12 07:30 | 2026-02-12 12:30 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2026-02-12 08:00 | 2026-02-12 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX | 32.3TR (SS-32) | 2026-02-12 08:00 | 2026-02-12 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 13.2TR (SS-13) | 2026-02-12 08:00 | 2026-02-12 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 368s C2 (368s Burdett), 368s 44 (368s Burdett) | 2026-02-12 08:30 | 2026-02-12 12:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 250p 2 (250p Bighorn Plant) | 2026-02-12 10:00 | 2026-02-12 14:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ENMAX | 32.83L (SS-32 - SS-40), 32B138-32.83 (SS-32) | 2026-02-12 12:00 | 2026-02-12 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.1TR (SS-40) | 2026-02-13 08:00 | 2026-02-13 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 31.84L (SS-31 - SS-32), 32B138-31.84 (SS-32), 31B138-31.84 (SS-31) | 2026-02-13 12:01 | 2026-02-13 16:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition
Syncrude | 18215 (Syncrude Mildred Lake), 1834 (Syncrude Mildred Lake), 1835 (Syncrude Mildred Lake) | 2026-02-14 08:00 | 2026-02-22 15:00 | N | N |  | Circuit Breaker, Switch |  | Completed early. | For Information Only
EPCOR | 72CH9 (987s Clover Bar - EP Hardisty), T3 (EP Hardisty), H723 (EP Hardisty), H724 (EP Hardisty), HAB3 (EP Hardisty) | 2026-02-17 07:00 | 2026-02-20 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T2 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), EP 511s V723 (EP 511s Victoria) | 2026-02-17 07:00 | 2026-02-18 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft), 72JW19 (EP 805s Jasper - Woodcroft) | 2026-02-17 07:00 | 2026-03-04 17:00 | N | N |  | Transformer, Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L48 (794s Valleyview - 7LA48 tap), 794s 703 (794s Valleyview) | 2026-02-17 08:00 | 2026-02-26 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
BCH | T3 (BCH Natal) | 2026-02-17 08:00 | 2026-02-24 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.1TR (SS-31) | 2026-02-17 08:00 | 2026-02-17 11:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 832L (SS-10 - SS-12), 12.1TR (SS-12), 10B138-832 (SS-10), 12B138-832L (SS-12), 12MD138-12.1TR (SS-12) | 2026-02-17 08:00 | 2026-02-20 16:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 972s 240kV Bus 900BS1 (972s Tinchebray) | 2026-02-17 09:00 | 2026-03-03 17:00 | N | Y |  | Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.2TR (SS-31) | 2026-02-17 11:01 | 2026-02-17 14:00 | N | N |  | Transformer |  |  | For Information Only, Pre-Condition
ENBRIDGE | 485s 35DSTAT2 (485s Blackspring) | 2026-02-18 09:00 | 2026-02-20 17:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 720L (347s AML Fox Creek - 397s Benbow), 397s 720N (397s Benbow), 347s 720X (347s AML Fox Creek) | 2026-02-18 10:01 | 2026-02-18 17:30 | N | N |  | Line, Circuit Breaker |  | Postponed one day as per TFO request | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 202AL tap), 61s 202N (61s Lodgepole) | 2026-02-18 13:00 | 2026-02-24 12:00 | N | N |  | Line, Circuit Breaker |  | Postponed as per TFO request | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 852s T1 (852s Round Hill) | 2026-02-18 16:00 | 2026-02-20 16:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ATCO | 9L40 (732s Mitsue - 809s Louise Creek) | 2026-02-19 08:00 | 2026-02-22 16:00 | N | Y |  | Line |  |  | 240 kV, Over/Under Voltage
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2026-02-19 09:00 | 2026-02-19 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, DOW | 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydrocarbons), 166s 862N (166s Dow Chemical Fort Saskatchewan) | 2026-02-19 09:00 | 2026-02-19 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 508s T1 (508s Lakesend), 508s 696 (508s Lakesend) | 2026-02-19 10:00 | 2026-02-19 13:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 657s SU2403 (657s Summerside) | 2026-02-19 13:00 | 2026-02-20 12:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 39.2TR (SS-39) | 2026-02-20 08:00 | 2026-02-20 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 443L (55s Olds - 214s Innisfail), 55s 443 (55S Olds), 214s 443 (214s Innisfail) | 2026-02-22 10:00 | 2026-02-27 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | EP 511s Victoria T4 (EP 511s Victoria), EP 511s V725 (EP 511s Victoria), EP 511s V726 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria) | 2026-02-23 07:00 | 2026-02-27 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T3 (805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s J2405 (EP 805s Jasper) | 2026-02-23 07:00 | 2026-02-28 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T3 (805s Jasper) | 2026-02-23 07:00 | 2026-03-23 07:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
ENMAX | 20.1TR (SS-20) | 2026-02-23 08:00 | 2026-02-27 18:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 47B138-BT3 (SS-47) | 2026-02-23 08:00 | 2026-02-23 16:00 | N | N |  | Circuit Breaker |  |  | For Information Only
ENMAX | 40.81L (SS-40 - SS-41), 41.84L (SS-41 - SS-54), 41.1TR (SS-41), 41B138-41BT3 (SS-41), 41B138-40.81 (SS-41), 41B138-41.84 (SS-41), 40B138-40.81 (SS-40), 54B138-41.84 (SS-54) | 2026-02-23 08:00 | 2026-02-25 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake), 715s 702 (715s Leming Lake) | 2026-02-23 10:00 | 2026-02-24 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 330p 1209 (330p Genesee) | 2026-02-24 07:00 | 2026-02-24 17:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ENMAX | 39.1TR (SS-39) | 2026-02-24 08:00 | 2026-02-25 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 27.1TR (SS-27) | 2026-02-24 08:00 | 2026-02-24 16:00 | N | N |  | Transformer |  |  | For Information Only
Syncrude | 11 (Aurora), 12 (Aurora), 13 (Aurora), T3 (Aurora), UT1 (Aurora), 11A (Aurora), 11B (Aurora), 12A (Aurora), 12B (Aurora), 13A (Aurora), 13B (Aurora), 89-15 (Aurora), 89-16 (Aurora), G20 (Aurora) | 2026-02-24 08:00 | 2026-03-10 16:00 | N | Y |  | Circuit Breaker, Transformer, Switch |  |  | Restricts Generation
ALTALINK | 202L (178s Cynthia - 202AL tap), 178s 202X (178s Cynthia) | 2026-02-24 12:30 | 2026-02-25 14:00 | N | N |  | Line, Circuit Breaker |  | Issues with previous outage. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 254s T2 (254s Coaldale), 254s 35 (254s Coaldale) | 2026-02-25 07:00 | 2026-02-25 18:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ENMAX | B138-83 (SS-1), B138-84 (SS-1) | 2026-02-25 07:30 | 2026-02-26 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 523s C1 (523s Bullshead) | 2026-02-25 08:00 | 2026-02-25 17:30 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 7L137 (768s Rowley - 770s Three Hills), 770s 702 (770s Three Hills), 768s 703 (768s Rowley) | 2026-02-25 10:00 | 2026-02-25 17:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 202L (178s Cynthia - 202AL tap), 178s 202X (178s Cynthia) | 2026-02-25 14:00 | 2026-03-12 14:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 807L (410s Josephburg - 807AL tap), 807L (233s Beamer - 807AL tap), 807AL (402s Scotford Expansion One - 807L tap), 233s 807X (233s Beamer) | 2026-02-26 07:00 | 2026-03-06 18:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 15.62L (SS-15 - SS-16), 15.2TR (SS-15), 15B69-15.62 (SS-15), SW64 (SS-15), 15MD69-15.2TR (SS-15) | 2026-02-26 08:00 | 2026-02-26 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, DOW | 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydrocarbons), 166s 862N (166s Dow Chemical Fort Saskatchewan) | 2026-02-26 09:00 | 2026-02-26 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 706L (54s Fort Saskatchewan - 706AL tap), 54s 706N (54s Fort Saskatchewan) | 2026-02-26 09:00 | 2026-02-26 18:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 770s 703T (770s Three Hills), 770s 703 (770s Three Hills) | 2026-02-26 10:00 | 2026-02-27 17:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 35.1TR (SS-35), 35B138-81 (SS-35), 35B138-82 (SS-35), 35MD138-84 (SS-35), 35MD138-86 (SS-35) | 2026-02-27 08:00 | 2026-02-27 16:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ATCO | 840s McNeill Station | 2026-02-28 15:08 | 2026-03-02 18:18 | N | N |  | Station |  |  | Limits ATC
EPCOR | 987s GT2 (987s Clover Bar), 987s CGB2 (987s Clover Bar) | 2026-03-02 07:00 | 2026-03-06 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
EPCOR | 987s 72kV Bus 3 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale), 987s CGB2 (987s Clover Bar), 987s CC13 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CK725 (987s Clover Bar) | 2026-03-02 07:00 | 2026-03-04 17:00 | N | Y |  | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1044L (EP 805s Jasper - 816s Petrolia), EP 805s J2403 (EP 805s Jasper), EP 805s J2404 (EP 805s Jasper), 816s P2405 (816s Petrolia), 816s P2406 (816s Petrolia) | 2026-03-02 07:00 | 2026-03-03 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | T4 (Rossdale), R724 (Rossdale), RR729 (Rossdale), RAB4 (Rossdale) | 2026-03-02 07:00 | 2026-03-06 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T1 (EP 511s Victoria), EP 511s V721 (EP 511s Victoria), EP 511s V722 (EP 511s Victoria), EP 511s VAB1 (EP 511s Victoria) | 2026-03-02 07:00 | 2026-03-04 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Pre-Condition
EPCOR | 557s T2 (557s Castle Downs) | 2026-03-02 07:00 | 2026-03-06 17:00 | N | Y |  | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
NWE | 2302 (NWE Marias) | 2026-03-02 07:30 | 2026-03-03 17:00 | N | N |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 102s 552 (102s Langdon), 102s 252 (102s Langdon), 102s T4 (102s Langdon), 102s SVC (102s Langdon), 102s 7189 (102s Langdon) | 2026-03-02 08:00 | 2026-03-05 07:30 | N | Y |  | Circuit Breaker, Transformer, Shunts, Switch |  |  | 240 kV, Pre-Condition
ATCO | 7L48 (794s Valleyview - 7LA48 tap), 794s 703 (794s Valleyview) | 2026-03-02 08:00 | 2026-03-19 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 263s C1 (263s Strachan), 263s 35 (263s Strachan) | 2026-03-02 08:00 | 2026-03-06 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 32B138-32BT5 (SS-32) | 2026-03-02 08:00 | 2026-03-13 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 8.5TR (SS-8) | 2026-03-02 08:00 | 2026-03-14 16:00 | N | N |  | Transformer |  |  | For Information Only
Lethbridge | 813L (146s MacDonald - 241s Uplands), 146s 813L (146s Macdonald), 146s 1 (146s Macdonald), 241s 813L (241s Uplands) | 2026-03-02 09:00 | 2026-03-12 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 882s 701T (882s Triangle), 882s 701 (882s Triangle) | 2026-03-02 09:00 | 2026-03-16 12:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 250p 1 (250p Bighorn Plant) | 2026-03-02 10:00 | 2026-03-02 12:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ALTALINK, ATCO | 899s 749N (899s Edgerton), 749L (899s Edgerton - 7LB749 tap) | 2026-03-02 13:00 | 2026-03-05 16:00 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only, Pre-Condition
ATCO, ALTALINK | 749L (899s Edgerton - 7LB749 tap), 899s 749N (899s Edgerton) | 2026-03-02 13:00 | 2026-03-06 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 914s 701T (914s Bindloss), 914s 701 (914s Bindloss) | 2026-03-03 07:00 | 2026-03-03 18:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 31.1TR (SS-31) | 2026-03-03 08:00 | 2026-03-05 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 87s 152 (87s Gaetz) | 2026-03-03 08:00 | 2026-03-03 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 944L (132s Ware Junction - 275s Jenner), 132s 51 (132s Ware Junction), 132s 47 (132s Ware Junction), 275s 5 (275s Jenner), 275s 2 (275s Jenner), 132s 944 (132s Ware Junction), 275s 944W (275s Jenner) | 2026-03-03 08:00 | 2026-03-09 17:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1037L (138s Windy Flats - 266s SC1), 1037L (237s Foothills - 266s SC1), 266s 189 (266s SC1), 266s 289 (266s SC1), 266s 1037L FSC1 (266s SC1) | 2026-03-03 08:00 | 2026-03-05 17:00 | N | Y |  | Line, Switch, Shunts |  |  | Overload, Pre-Condition
ALTALINK | 508s T1 (508s Lakesend), 508s 696 (508s Lakesend) | 2026-03-03 08:30 | 2026-03-03 22:30 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
BCH | T7 (BCH Natal) | 2026-03-03 09:00 | 2026-03-05 13:00 | N | Y |  | Transformer |  |  | For Information Only
ALTALINK | 62s T2 (62s Brazeau Plant), 62s 2 (62s Brazeau Plant) | 2026-03-03 23:30 | 2026-03-04 06:30 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
EPCOR | 816s T1 (816s Petrolia), 816s P2402 (816s Petrolia), 816s P2401 (816s Petrolia), 816s PAB1 (816s Petrolia) | 2026-03-04 07:00 | 2026-03-06 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ALTALINK | 87s 552 (87s Gaetz) | 2026-03-04 08:00 | 2026-03-04 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2026-03-04 23:30 | 2026-03-05 02:30 | N | Y |  | Transformer, Circuit Breaker |  |  | For Information Only, Restricts Generation
ATCO, ALTALINK | 9L913 (69s North Barrhead - 732s Mitsue), 69s 913N (69s North Barrhead) | 2026-03-05 07:00 | 2026-03-09 12:00 | N | Y |  | Line, Circuit Breaker |  | Outage Delayed - as per TFO | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 87s 952 (87s Gaetz) | 2026-03-05 08:00 | 2026-03-05 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 523s C1 (523s Bullshead), 523s 33 (523s Bullshead) | 2026-03-05 09:00 | 2026-03-05 16:00 | N | N |  | Shunts, Circuit Breaker |  |  | Pre-Condition
EPCOR | 1098L (EP 805s Jasper - Poundmaker), EP 805s J2407 (EP 805s Jasper), EP 805s J2401 (EP 805s Jasper) | 2026-03-06 07:00 | 2026-03-06 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 87s 252 (87s Gaetz) | 2026-03-06 08:00 | 2026-03-06 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
BCH | T8 (BCH Natal) | 2026-03-06 16:00 | 2026-03-10 13:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | T1 (Woodcroft) | 2026-03-06 17:00 | 2026-11-13 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 33s 2 (33s Spray) | 2026-03-07 08:00 | 2026-03-07 16:00 | N | Y |  | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 87s 852 (87s Gaetz) | 2026-03-07 08:00 | 2026-03-07 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 87s 1052 (87s Gaetz) | 2026-03-08 08:00 | 2026-03-08 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2026-03-08 08:00 | 2026-03-08 17:00 | N | Y |  | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Rossdale), R723 (Rossdale), R724 (Rossdale) | 2026-03-08 08:00 | 2026-03-12 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 38.83L (SS-38 - SS-39), 39.3TR (SS-39), 39.1TR (SS-39), 38B138-38.83 (SS-38), 39B138-38.83 (SS-39), 39MD138-39.1TR (SS-39), 39MD138-39.3TR (SS-39) | 2026-03-08 08:30 | 2026-03-24 16:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia), 816s P2401 (816s Petrolia), 816s P2406 (816s Petrolia) | 2026-03-09 07:00 | 2026-03-10 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s GT3 (987s Clover Bar), 987s CGB3 (987s Clover Bar) | 2026-03-09 07:00 | 2026-03-13 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 749L (899s Edgerton - 749AL tap) | 2026-03-09 08:00 | 2026-03-13 17:00 | N | N |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove), 595s 712 (595s Spruce Grove), 99s 712X (99s North St. Albert) | 2026-03-09 08:00 | 2026-03-13 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 24.2TR (SS-24) | 2026-03-09 08:00 | 2026-03-09 18:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 308s 776W (308s Albchem Beaverhill Creek) | 2026-03-09 09:00 | 2026-03-13 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 305s C1 (305s Acheson) | 2026-03-09 11:30 | 2026-03-09 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 149s C1 (149s Nisku) | 2026-03-09 13:15 | 2026-03-09 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 63s 26 (63s Red Deer), 63s T3 (63s Red Deer) | 2026-03-09 13:30 | 2026-03-09 16:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 191s T1 (191s N.W. Cardiff) | 2026-03-09 14:00 | 2026-03-10 16:00 | N | N |  | Transformer |  |  | For Information Only
JOEP | RIM1 Rimbey Gas Generator Test | 2026-03-10 08:00 | 2026-04-27 19:30 | N | Y |  | Unit
ALTALINK | 432s 790 (432s Carvel) | 2026-03-10 08:30 | 2026-03-10 11:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 972s 240kV Bus 900BS2 (972s Tinchebray), 972s 903 (972s Tinchebray) | 2026-03-10 09:00 | 2026-04-14 17:00 | N | Y |  | Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 38s 738W (38s East Edmonton) | 2026-03-10 09:00 | 2026-03-10 11:30 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, For Information Only, Over/Under Voltage
ALTALINK | 310p 1752 (310p Sundance) | 2026-03-10 09:00 | 2026-03-10 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 428s 19 (428s Namaka), 428s T1 (428s Namaka) | 2026-03-10 10:00 | 2026-03-10 12:00 | N | N |  | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake), 38s 780X (38s East Edmonton) | 2026-03-10 13:30 | 2026-03-10 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 896L (19s Wabamun - 432s Carvel), 432s 896 (432s Carvel) | 2026-03-10 13:30 | 2026-03-10 16:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 897L (38s East Edmonton - 45s Bretona), 38s 897 (38s East Edmonton) | 2026-03-10 14:42 | 2026-03-20 17:00 | N | N |  | Line, Circuit Breaker |  | Emergency Outage: 39s 897 (leaking CT) | Creates Radial Feeds, Firm Load Loss
EPCOR | 557s CD2401 (557s Castle Downs) | 2026-03-11 07:00 | 2026-03-11 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 816s T2 (816s Petrolia), 816s P2404 (816s Petrolia), 816s P2405 (816s Petrolia), 816s PAB2 (816s Petrolia) | 2026-03-11 07:00 | 2026-03-13 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ALTALINK | 728L (353s Plamondon - 405s Waupisoo), 405s 728 (405s Waupisoo), 353s 452 (353s Plamondon) | 2026-03-11 08:00 | 2026-03-16 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L36 (820s Hangingstone - 2009s Willow Lake), 820s 701 (820s Hangingstone) | 2026-03-11 08:00 | 2026-03-15 17:00 | N | N |  | Line, Circuit Breaker |  | RTN early | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 410s 752 (410s Josephburg) | 2026-03-11 09:00 | 2026-03-11 11:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 535s 6052 (535s Joffre) | 2026-03-11 09:00 | 2026-03-11 11:30 | N | N |  | Circuit Breaker |  |  | For Information Only
ALTALINK | 310p 2052 (310p Sundance) | 2026-03-11 09:30 | 2026-03-11 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV
ATCO, ALTALINK | 199L (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek), 741s 702 (741s ATC Fox Creek) | 2026-03-11 11:00 | 2026-03-11 12:30 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 410s 852 (410s Josephburg) | 2026-03-11 13:30 | 2026-03-11 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 535s C1 (535s Joffre) | 2026-03-11 13:45 | 2026-04-10 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ENMAX, ALTALINK | 7.82L (42s Sarcee - SS-7), 42s 7 (42s Sarcee), 7B138-7.82 (SS-7) | 2026-03-12 08:00 | 2026-03-13 18:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 310p 552 (310p Sundance) | 2026-03-12 09:30 | 2026-03-12 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 202L (178s Cynthia - 202AL tap), 178s 202X (178s Cynthia) | 2026-03-12 14:00 | 2026-03-12 17:00 | N | N |  | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 72RG1 (Garneau - Rossdale), RG7210 (Rossdale) | 2026-03-13 07:00 | 2026-03-13 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia), 240BA3 (629s Argyll Transfer Station - 814s Bellamy), 814s B2406 (814s Bellamy), 814s B2407 (814s Bellamy) | 2026-03-13 07:00 | 2026-03-13 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 7L122 (791s Rainbow Lake - 930s Arcenciel), 791s 701 (791s Rainbow Lake) | 2026-03-13 16:00 | 2026-04-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
EPCOR | 330P 12TC1 (330p Genesee), 330p 1201 (330p Genesee), 330p 805 (330p Genesee) | 2026-03-14 07:00 | 2026-04-05 17:00 | N | Y |  | Transformer, Circuit Breaker
EPCOR | 330p 500kV Bus 1 (330p Genesee), 330P 12TC1 (330p Genesee), 330p 1207 (330p Genesee), 330p 1204 (330p Genesee), 330p 1201 (330p Genesee), 330p 1210 (330p Genesee), 330p 1214 (330p Genesee), 330p 12TC1D (330p Genesee), 330p 805 (330p Genesee) | 2026-03-14 07:00 | 2026-03-30 17:00 | N | Y |  | Bus, Transformer, Circuit Breaker, Switch | P7103 | Extended by a day for relay tech | 500 kV, Contingency Requires Mitigation
EPCOR | 330p 1210 (330p Genesee) | 2026-03-15 07:00 | 2026-04-05 17:00 | N | Y |  | Circuit Breaker
EPCOR | 330P GT6 (330p Genesee) | 2026-03-15 07:00 | 2026-04-01 17:00 | N | Y |  | Transformer |  |  | 500 kV, Pre-Condition, Restricts Generation
EPCOR | 330p 1211 (330p Genesee), 330p 1210 (330p Genesee) | 2026-03-15 07:00 | 2026-04-01 17:00 | N | Y |  | Circuit Breaker | P7103 |  | 500 kV, Pre-Condition
EPCOR | 665s T2 (665s Dome) | 2026-03-16 07:00 | 2026-03-20 17:00 | N | Y |  | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 816s P2403 (816s Petrolia) | 2026-03-16 07:00 | 2026-03-16 17:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s GT1 (987s Clover Bar), 987s CGB1 (987s Clover Bar) | 2026-03-16 07:00 | 2026-04-01 17:00 | N | Y |  | Transformer, Circuit Breaker |  |  | Restricts Generation
EPCOR | T2 (Poundmaker) | 2026-03-16 07:00 | 2026-03-20 17:00 | N | Y |  | Transformer |  |  | 240 kV, For Information Only
PGII | KAS1 Kaybob 3 Cogen South Generator Test | 2026-03-16 07:00 | 2026-05-05 18:30 | N | Y |  | Unit
EPCOR, ALTALINK | 1058L (657s Summerside - EP 803s Lambton), EP 803s L2403 (EP 803s Lambton), EP 803s L2404 (EP 803s Lambton), 657s SU2403 (657s Summerside), 657s SU2404 (657s Summerside) | 2026-03-16 07:00 | 2026-03-19 17:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2026-03-16 08:00 | 2026-03-20 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 305s 677 (305s Acheson), 595s 677 (595s Spruce Grove), 677L (305s Acheson - 595s Spruce Grove) | 2026-03-16 08:00 | 2026-03-17 17:00 | N | N |  | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 47B138-771/1 (SS-47) | 2026-03-16 08:00 | 2026-03-19 16:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ENMAX | 162.2TR (SS-162) | 2026-03-16 08:00 | 2026-03-19 16:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
CMH | MH-30L (MHS-3 Southridge - MHS-5 NE Crescent Heights), MHS-3 MH69-308 (MHS-3 Southridge), MHS-5 MH69-502 (MHS-5 NE Crescent Heights) | 2026-03-16 08:00 | 2026-03-20 15:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 87s 2352 (87s Gaetz), 87s 1652 (87s Gaetz), 87s T1 (87s Gaetz), 87s 240kV West Bus (87s Gaetz), 914L (63s Red Deer - 87s Gaetz), 87s 13 (87s Gaetz), 87s 914X (87s Gaetz) | 2026-03-16 08:00 | 2026-03-25 17:00 | N | Y |  | Circuit Breaker, Transformer, Bus, Line, Switch |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
BHE Canada | MATL (120s Picture Butte - Montana) | 2026-03-16 09:00 | 2026-03-19 17:00 | Y | Y |  | Line |  |  | 240 kV, Limits ATC, Pre-Condition
ALTALINK, BCH, AESO | 1201L (520s Bennett - BCH Cranbrook), Path 1 (AIES Islanding), 786L (799s Coleman - BCH Natal), 887L (48s Pocaterra - 978s BCH Britt Creek) | 2026-03-16 09:00 | 2026-03-17 13:55 | Y | Y |  | Line |  |  | 500 kV, Pre-Condition, Affects Cranking Path
BCH | 5L92 (BCH Cranbrook - BCH Selkirk) | 2026-03-16 09:00 | 2026-03-17 13:55 | Y | Y |  | Line |  |  | 500 kV, Limits ATC
ALTALINK | 763L (28s West Brooks - 763AL tap), 28s 47 (28s West Brooks), 28s 31 (28s West Brooks), 28s 763X (28s West Brooks) | 2026-03-16 09:00 | 2026-03-16 13:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), 308s 773E (308s Albchem Beaverhill Creek), 127s 773W (127s Bruderheim) | 2026-03-16 09:00 | 2026-04-10 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO, ALTALINK | 788L (898s Heart Lake - 788AL tap) | 2026-03-16 09:00 | 2026-03-19 16:00 | N | Y |  | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK, Lethbridge | 618s 824 (618s Riverbend), 824L (593s Lakeview - 618s Riverbend), 593s 824L (593s Lakeview), 593s 1 (593s Lakeview), 593s 3 (593s Lakeview) | 2026-03-16 10:00 | 2026-03-26 16:00 | N | Y |  | Circuit Breaker, Line, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 38s 897 (38s East Edmonton) | 2026-03-16 11:30 | 2026-03-16 16:00 | N | N |  | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s 705 (813s Little Smoky) | 2026-03-16 12:00 | 2026-03-20 07:59 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 163s 1752 (163s Amoco Empress), 163s 1552 (163s Amoco Empress), 1002L (163s Amoco Empress - 275s Jenner) | 2026-03-16 12:00 | 2026-03-20 12:00 | N | Y |  | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1325L (510s Sunnybrook - AML 511s Crossings), AML 511s T11 (AML 511s Crossings), 510s T11 (510s Sunnybrook), 510s 2652 (510s Sunnybrook), 510s 2752 (510s Sunnybrook), 510s 41 (510s Sunnybrook), 510s 43 (510s Sunnybrook), 510s 4289 (510s Sunnybrook), AML 511s 1489 (AML 511s Crossings) | 2026-03-16 13:18 | 2026-03-25 07:00 | N | Y |  | Line, Transformer, Circuit Breaker, Switch |  | outage ended early | 500 kV, Overload
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 17s 717W (17s Benalto), 262s 717E (262s Rocky Mountain House) | 2026-03-16 15:00 | 2026-03-26 12:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 394s T2 (394s Empress) | 2026-03-17 09:00 | 2026-03-26 18:00 | N | N |  | Transformer |  |  | For Information Only
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel), 828s 701 (828s Sulphur Point) | 2026-03-17 09:00 | 2026-03-17 11:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 890L (58s Edson - 207s Pinedale), 58s 890 (58s Edson), 207s 890 (207s Pinedale) | 2026-03-17 09:30 | 2026-03-17 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 89s 2052 (89s Ellerslie) | 2026-03-17 09:30 | 2026-03-17 16:00 | N | Y |  | Circuit Breaker |  |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 108s 352 (108s Amelia) | 2026-03-17 09:30 | 2026-03-17 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 574s 652 (574s Nilrem) | 2026-03-17 11:30 | 2026-03-17 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 108s 452 (108s Amelia) | 2026-03-17 13:30 | 2026-03-17 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.63L (SS-16 - SS-36), 36.5TR (SS-36), 36B69-16.63/36.5TR (SS-36), 16B69-16.63 (SS-16) | 2026-03-18 08:00 | 2026-03-19 16:00 | N | N |  | Line, Transformer, Circuit Breaker |  |  | Overload, Pre-Condition
ALTALINK | 163s 1752 (163s Amoco Empress), 163s 1552 (163s Amoco Empress), 1002L (163s Amoco Empress - 275s Jenner) | 2026-03-18 08:00 | 2026-03-19 17:00 | N | Y |  | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 28s T1 (28s West Brooks) | 2026-03-18 08:30 | 2026-03-18 17:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 574s 452 (574s Nilrem) | 2026-03-18 09:00 | 2026-03-18 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 314L (207s Pinedale - 228s T.M.P.L. Niton), 228s 314 (228s T.M.P.L. Niton), 207s 314 (207s Pinedale) | 2026-03-18 09:30 | 2026-03-18 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 108s 252 (108s Amelia) | 2026-03-18 09:30 | 2026-03-18 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1054L (12s Heartland - 13s Deerland), 13s 1552 (13s Deerland), 13s 1652 (13s Deerland), 13s 98 (13s Deerland) | 2026-03-18 10:00 | 2026-03-18 16:00 | N | Y |  | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 574s 552 (574s Nilrem) | 2026-03-18 13:30 | 2026-03-18 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 14s T3 (14s Devon) | 2026-03-18 15:00 | 2026-03-18 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 931L (28s West Brooks - 132s Ware Junction), 132s 51 (132s Ware Junction), 132s 55 (132s Ware Junction), 28s 5 (28s West Brooks), 28s 8 (28s West Brooks), 132s 931 (132s Ware Junction), 28s 931N (28s West Brooks) | 2026-03-19 08:00 | 2026-03-27 17:09 | N | Y |  | Line, Circuit Breaker, Switch |  | back early | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ATCO, ALTALINK | 923L (356s Milo - 2075s Newell) | 2026-03-19 08:00 | 2026-03-19 16:00 | N | Y |  | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 422s 694 (422s Westwood), 54s 694 (54s Fort Saskatchewan), 694L (54s Fort Saskatchewan - 422s Westwood), 422s T1 (422s Westwood), 422s 189 (422s Westwood) | 2026-03-19 10:00 | 2026-03-19 16:00 | N | N |  | Circuit Breaker, Line, Transformer, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 935L (324s Cassils - 356s Milo) | 2026-03-20 08:00 | 2026-03-20 17:00 | N | Y |  | Line |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ATCO | 813s 705 (813s Little Smoky), 7L46 (813s Little Smoky - 845s Big Mountain), 813s 706 (813s Little Smoky) | 2026-03-20 08:00 | 2026-03-20 17:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.1TR (SS-1) | 2026-03-21 08:00 | 2026-03-21 12:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 1.3TR (SS-1) | 2026-03-21 12:00 | 2026-03-21 16:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72JW19 (EP 805s Jasper - Woodcroft), T1 (Woodcroft), W721 (Woodcroft), W722 (Woodcroft), EP 805s J724 (EP 805s Jasper), WAB1 (Woodcroft), EP 805s JDS28 (EP 805s Jasper) | 2026-03-22 07:00 | 2026-04-02 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 31.1TR (SS-31), 31.2TR (SS-31), 31.1C (SS-31), 31B138-9.80 (SS-31), 31MD138-31.1TR (SS-31), 31MD138-31.2TR (SS-31), SW84 (SS-31) | 2026-03-22 08:00 | 2026-03-22 18:00 | N | N |  | Line, Transformer, Shunts, Circuit Breaker, Switch |  |  | Pre-Condition
BHE Canada | 120s C1 (120s Picture Butte), 120s C2 (120s Picture Butte) | 2026-03-22 13:00 | 2026-06-30 17:00 | N | Y |  | Shunts |  | forced outage | Pre-Condition
EPCOR | 805s T3 (805s Jasper), EP 805s J2404 (EP 805s Jasper), EP 805s J2405 (EP 805s Jasper), EP 805s JAB3 (EP 805s Jasper) | 2026-03-23 07:00 | 2026-03-27 17:00 | N | Y |  | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | EP 511s Victoria T1 (EP 511s Victoria) | 2026-03-23 07:00 | 2026-03-27 17:00 | N | N |  | Transformer |  |  | For Information Only
EPCOR | 72RV6 (EP 511s Victoria - Rossdale), RV722 (Rossdale), EP 511s VDS9 (EP 511s Victoria) | 2026-03-23 07:00 | 2026-03-27 17:00 | N | N |  | Line, Circuit Breaker, Switch |  |  | Pre-Condition
EPCOR | T2 (Rossdale), R721 (Rossdale), R723 (Rossdale), RAB2 (Rossdale) | 2026-03-23 07:00 | 2026-03-23 17:00 | N | N |  | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Kennedale) | 2026-03-23 07:00 | 2026-03-23 11:00 | N | N |  | Transformer |  | Back early | Firm Load Loss, Pre-Condition
EPCOR | T2 (Rossdale) | 2026-03-23 07:00 | 2026-03-27 17:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo), 405s 633 (405s Waupisoo), 56s 633 (56s Boyle) | 2026-03-23 07:15 | 2026-03-25 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 9.80L (SS-9 - SS-31), 9.1TR (SS-9), 9B138-9.80 (SS-9), SW89 (SS-9), 9MD138-9.1TR (SS-9) | 2026-03-23 08:00 | 2026-03-23 18:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - SS-28), 28B138-28.80 (SS-28), 42s 28 (42s Sarcee) | 2026-03-23 08:00 | 2026-03-23 12:00 | N | Y |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 514L (513s Lundbreck - 514BL tap), 513s T1 (513s Lundbreck), 513s 1 (513s Lundbreck) | 2026-03-23 08:00 | 2026-03-26 16:00 | N | N |  | Line, Transformer, Switch |  |  | For Information Only
ATCO | 7L48 (794s Valleyview - 7LA48 tap), 794s 703 (794s Valleyview) | 2026-03-23 08:00 | 2026-03-31 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 199L (347s AML Fox Creek - 741s ATC Fox Creek), 347s 199W (347s AML Fox Creek), 741s 702 (741s ATC Fox Creek) | 2026-03-23 08:00 | 2026-04-06 16:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162.1TR (SS-162) | 2026-03-23 08:00 | 2026-03-27 18:00 | N | Y |  | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Overload
ALTALINK | 834L (320p Keephills - 384s Keystone), 320p 834X (320p Keephills), 384s 834 (384s Keystone) | 2026-03-23 09:00 | 2026-03-27 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 430s 452 (430s Ursus) | 2026-03-23 12:00 | 2026-03-27 12:00 | N | Y |  | Circuit Breaker |  | outage extended | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Restricts Generation
ENMAX | 20.82L (SS-20 - SS-21), 20B138-20.82 (SS-20), 21B138-20.82 (SS-21) | 2026-03-23 12:00 | 2026-03-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 813s 706 (813s Little Smoky) | 2026-03-23 12:00 | 2026-03-26 17:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 2033s 704C (2033s Mowat) | 2026-03-23 13:00 | 2026-03-26 09:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK | 65s T3 (65s High River), 65s 812W (65s High River), 65s 46 (65s High River) | 2026-03-23 13:00 | 2026-03-27 16:12 | N | N |  | Transformer, Circuit Breaker, Switch | Transmission constraint record created - reference #1-00519772 | back early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, REDDEER | 768L (209s Timberlands - 217s North Red Deer), 217s 768 (217s North Red Deer), 209s 768W (209s Timberlands) | 2026-03-23 13:30 | 2026-03-23 16:00 | N | N |  | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 310p 1852 (310p Sundance) | 2026-03-23 14:00 | 2026-03-26 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Pre-Condition
ATCO | 7L89 (721s La Corey - 826s Marguerite Lake) | 2026-03-23 14:00 | 2026-03-27 14:00 | N | Y |  | Line |  | Outage returned early | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 89s T2 (89s Ellerslie) | 2026-03-23 14:00 | 2026-03-24 16:00 | N | Y |  | Transformer |  |  | 500 kV, Overload, Pre-Condition
ALTALINK | 747L (99s North St. Albert - 711L tap), 99s 747X (99s North St. Albert) | 2026-03-24 08:00 | 2026-03-29 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 700L (746s Sherwood Park - 746L tap), 746s 700N (746s Sherwood Park), 422s 700 (422s Westwood) | 2026-03-24 08:00 | 2026-03-24 17:00 | N | N |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 7.84L (SS-7 - SS-36), 36B138-7.84 (SS-36), 7B138-7.84 (SS-7) | 2026-03-24 08:00 | 2026-03-24 16:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 348s T1 (348s Marlboro), 348s 152 (348s Marlboro) | 2026-03-24 08:00 | 2026-03-24 17:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 703L (377s AML Hardisty - 703BL tap), 377s 703E (377s AML Hardisty) | 2026-03-24 09:30 | 2026-03-24 11:30 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | N722 (Namao) | 2026-03-25 07:00 | 2026-03-25 17:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 320p 552 (320p Keephills) | 2026-03-25 09:30 | 2026-03-25 11:30 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 574s 852 (574s Nilrem) | 2026-03-25 09:30 | 2026-03-25 11:30 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 856s 707C (856s Kinosis) | 2026-03-25 10:00 | 2026-03-26 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T1 (250p Bighorn Plant) | 2026-03-25 10:00 | 2026-03-25 14:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 574s 752 (574s Nilrem) | 2026-03-25 13:30 | 2026-03-25 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 320p 152 (320p Keephills) | 2026-03-26 01:30 | 2026-03-26 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 937L (5s East Calgary - 102s Langdon), 102s 6452 (102s Langdon), 102s 6552 (102s Langdon) | 2026-03-26 02:00 | 2026-03-31 15:00 | N | Y |  | Line, Circuit Breaker |  |  | 240 kV, Affects Cranking Path
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain), 813s 705 (813s Little Smoky), 813s 706 (813s Little Smoky), 845S 7L46D2 (845s Big Mountain) | 2026-03-26 08:00 | 2026-03-26 17:00 | N | Y |  | Line, Circuit Breaker, Switch
ALTALINK | 348s T2 (348s Marlboro), 348s 252 (348s Marlboro) | 2026-03-26 08:00 | 2026-03-27 08:00 | N | N |  | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 320p 752 (320p Keephills) | 2026-03-26 09:30 | 2026-03-26 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 478s C1 (478s Tucuman) | 2026-03-26 09:30 | 2026-03-26 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ATCO | 856s 708C (856s Kinosis) | 2026-03-26 10:00 | 2026-03-26 16:00 | N | N |  | Shunts |  |  | Pre-Condition
ALTALINK, TRANSALTA | 250p T2 (250p Bighorn Plant) | 2026-03-26 10:00 | 2026-03-26 14:00 | N | Y |  | Transformer |  |  | Pre-Condition, Restricts Generation
ALTALINK | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer) | 2026-03-26 10:00 | 2026-03-26 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 937L (5s East Calgary - 102s Langdon) | 2026-03-26 10:04 | 2026-04-14 17:00 | N | Y |  | Line |  |  | 240 kV, Affects Cranking Path
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s CK725 (987s Clover Bar) | 2026-03-27 07:00 | 2026-03-27 17:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.84L (SS-2 - SS-8) | 2026-03-27 07:00 | 2026-03-27 19:00 | N | N |  | Line |  |  | Overload, Pre-Condition
EPCOR | 987s T3 (987s Clover Bar), 987s C2407 (987s Clover Bar) | 2026-03-30 07:00 | 2026-03-31 16:00 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 914L (86s Bigstone - 87s Gaetz), 87s 240kV East Bus (87s Gaetz), 87s T2 (87s Gaetz), 87s 2352 (87s Gaetz), 87s 1252 (87s Gaetz), 87s 1652 (87s Gaetz), 87s 1952 (87s Gaetz), 87s 1352 (87s Gaetz), 87s 1552 (87s Gaetz) | 2026-03-30 07:00 | 2026-04-08 18:00 | N | Y |  | Line, Bus, Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
EPCOR | RR723 (Rossdale) | 2026-03-30 07:00 | 2026-04-03 17:00 | N | N |  | Circuit Breaker |  |  | For Information Only
EPCOR | 805s T1 (805s Jasper), 805s C1 (805s Jasper), EP 805s J2401 (EP 805s Jasper), EP 805s J2403 (EP 805s Jasper), EP 805s J724 (EP 805s Jasper), EP 805s J722 (EP 805s Jasper), 72JW19 (EP 805s Jasper - Woodcroft), 72JM18 (EP 805s Jasper - Meadowlark), EP 805s JDS28 (EP 805s Jasper), EP 805s JDS29 (EP 805s Jasper), M721 (Meadowlark), EP 805s JAB1 (EP 805s Jasper), EP 805s JAB5 (EP 805s Jasper), W721 (Woodcroft) | 2026-03-30 07:00 | 2026-03-31 17:00 | N | Y |  | Transformer, Shunts, Circuit Breaker, Line, Switch |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Impacts RAS, Pre-Condition
ALTALINK | 37s 138kV Bus (37s North Calder), 898L (37s North Calder - 92s Viscount), 747L (37s North Calder - 711L tap), 37s T3 (37s North Calder), 37s 747W (37s North Calder), 37s 726E (37s North Calder), 37s 898 (37s North Calder), 37s 12 (37s North Calder) | 2026-03-30 08:00 | 2026-03-30 14:00 | N | N |  | Bus, Line, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 37s 726E (37s North Calder) | 2026-03-30 08:00 | 2026-04-02 16:00 | N | N |  | Line, Circuit Breaker |  |  | Overload, Pre-Condition
ENMAX | 162.3TR (SS-162) | 2026-03-30 08:00 | 2026-04-01 16:00 | N | N |  | Transformer |  |  | For Information Only
ENMAX | 9.83L (SS-9 - SS-43), 9B138-9.83 (SS-9), 43B138-9.83 (SS-43) | 2026-03-30 08:00 | 2026-03-30 11:00 | N | N |  | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO, ALTALINK | 7L50 (757s Battle River - 491L tap), 757s 709 (757s Battle River) | 2026-03-30 08:00 | 2026-04-01 17:00 | N | Y |  | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 34.1TR (SS-34) | 2026-03-30 08:00 | 2026-03-31 16:00 | N | N |  | Transformer |  |  | For Information Only
ALTALINK | 62s T1 (62s Brazeau Plant), 62s 1 (62s Brazeau Plant) | 2026-03-30 08:30 | 2026-05-04 16:30 | N | Y |  | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
Lethbridge | 823L (146s MacDonald - 593s Lakeview), 146s T2 (146s Macdonald), 146s 823L (146s Macdonald), 593s 823L (593s Lakeview), 146s 9 (146s Macdonald) | 2026-03-30 09:00 | 2026-04-09 17:00 | N | N |  | Line, Transformer, Circuit Breaker, Switch |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 430s 652 (430s Ursus) | 2026-03-30 13:00 | 2026-04-02 16:00 | N | Y |  | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 42s C2 (42s Sarcee), 42s C3 (42s Sarcee) | 2026-03-30 14:01 | 2026-04-01 16:00 | N | Y |  | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 71s 252 (71s Lamoureux) | 2026-03-30 15:00 | 2026-04-01 16:00 | N | N |  | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 428s 733N (428s Namaka), 733L (151s Strathmore - 428S Namaka), 151s 733E (151s Strathmore) | 2026-03-31 09:00 | 2026-03-31 16:00 | N | Y |  | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 819s 702 (819s Whitby Lake) | 2026-03-31 09:00 | 2026-04-02 17:00 | N | N |  | Circuit Breaker