## Data
Owner | Name | Outage Start | Planned End | Tie Line | Significant Outage | Activity | Equipment Type | Outage Event | Outage Reason | Outage Condition
ALTALINK | 89s 2152 (89s Ellerslie) | 2013-04-28 18:00 | 2013-09-15 08:00 | N | Y | piling installation between 89s1852 & 500 kV Bus#2 | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ENBRIDGE | Hay Lake North Series Capacitor,Marias South Series Capacitor | 2013-06-26 08:00 | 2017-01-18 13:00 | N | Y | Series capacitor banks were removed from service due to the Subsynchronous Control Interaction (SSCI) with connected wind farm. | Shunts |  |  | 240 kV, Limits ATC
EPCOR | Rossdale C1 | 2013-07-17 06:38 | 2014-03-13 17:00 | N | Y | forced outage | Shunts |  |  | For Information Only
ATCO | 970S Bourque | 2013-07-20 08:00 | 2013-11-04 16:00 | N | N | Refer to the Op Plan binder for the commissioning plan. In service dates: 7L583 - July 24, 7L157 - July 31. | Station
ATCO | 720s 501R (720s Wabasca) | 2013-07-31 11:00 | 2016-02-29 18:00 | N | N | forced outage | Shunts |  | Forced outage | For Information Only
AESO-SC | 132s Ware Junction Reconfiguration | 2013-08-01 08:00 | 2013-11-30 16:00 | N | N | Refer to the Op Plan binder for the commissioning plan. | Terminal Equipment
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2013-08-06 08:00 | 2013-09-15 16:00 | N | N | re-locate line, doble test 31B138-31.84 & 32B138-31.84 | Line |  |  | Pre-Condition, For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32B138-31.84 (ENMAX 32) | 2013-08-06 08:00 | 2013-09-15 16:00 | N | N | breaker SF6 repair | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 310p 252 (310p Sundance),310p 352 (310p Sundance) | 2013-08-19 08:00 | 2013-09-17 17:00 | N | Y | replace 310p352 CTs & breaker fail protections | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 498s T1 (498s Tilley) | 2013-08-26 08:00 | 2013-10-22 08:00 | N | N | replace transformer with new 42 MVA | Transformer
EPCOR | 814s T1 (814s Bellamy) | 2013-09-03 08:00 | 2013-09-20 17:00 | N | Y | maintenance | Transformer |  |  | 240 kV
ALTALINK | 752AL (316s West Crossfield - 752L),752L (64s East Crossfield - 752L67),752L (653s Summit - 752L76) | 2013-09-03 10:00 | 2013-09-20 16:00 | N | N | line re-build | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | Sheerness 9L933/9L934/9L950 TPS | 2013-09-03 10:00 | 2013-10-03 23:00 | N | N | 807s Sheerness RAS/TPS maintenance | RAS |  |  | For Information Only, Impacts RAS
ATCO | 9L933 (28s West Brooks - 801s Anderson) | 2013-09-08 07:45 | 2013-09-13 18:15 | N | N | reterminating | Line
ALTALINK | 933L (28s West Brooks - 801s Anderson) | 2013-09-08 08:00 | 2013-09-13 19:00 | N | Y | move line to new alignment at 28s - Hanna project | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | Sask Power AS904T, AS901, AS903, AS804 and AS808 breakers | 2013-09-09 13:00 | 2013-09-13 13:00 | N | N |  | SCInternal |  |  | For Information Only
ATCO | 847s 902T (847s Muskeg River) | 2013-09-10 06:30 | 2013-09-21 16:00 | N | Y | maintenance | Transformer |  |  | 240 kV, Restricts Generation
EPCOR | 72MG16 (Meadowlark - Garneau) | 2013-09-12 08:00 | 2013-09-14 18:00 | N | N | Jasper P&C upgrade | Line
AESO-SC | MSAT test per SCP 12-Comm-03 | 2013-09-12 08:00 | 2013-09-12 17:00 | N | N | sometime during the day | SCInternal |  |  | For Information Only
ALTALINK | 535s 152 (535s Joffre) | 2013-09-12 17:00 | 2013-09-20 16:00 | N | N | breaker replacement | Circuit Breaker
ALTALINK | 370s T4 (370s North Lethbridge),370s45, 370s68 | 2013-09-13 15:00 | 2013-09-16 10:00 | N | N | test energize new T4 transformer | Transformer, Terminal Equipment
ALTALINK | 931L (132s Ware Junction - 28s West Brooks) | 2013-09-13 19:00 | 2013-09-18 07:59 | N | Y | move line to new alignment just outside of 28s - Hanna project | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | EnerNOC Platform maintenance | 2013-09-14 03:40 | 2013-09-14 19:40 | N | N |  | SCInternal |  |  | For Information Only
ALTALINK | 89s T2 (89s Ellerslie),89s 1852 (89s Ellerslie) | 2013-09-14 08:00 | 2013-09-14 18:00 | N | Y | gas pressure increase, close open point on bus - Heartland | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation, 500 kV
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2013-09-14 08:00 | 2013-09-14 19:00 | N | N | line washing | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1058L (657s Summerside - 803s Lambton) | 2013-09-14 08:00 | 2013-09-14 18:00 | N | Y | 803S doble & oil samples as required | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 7L101 (790s Poplar Hill - 944s Lowe Lake) | 2013-09-14 09:00 | 2013-09-14 16:00 | N | Y | change damaged jaw on 7L101D1 | Line |  |  | Restricts Generation
ENMAX | 771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington) | 2013-09-14 18:00 | 2013-09-14 21:00 | N | N | sub washing 162 sub | Line, Circuit Breaker
ALTALINK | 20s153 (20s Ghost) | 2013-09-15 08:00 | 2013-09-24 11:30 | N | Y | 13.2 kV bus prot upgrade & T1 maintenance | Terminal Equipment |  |  | Restricts Generation
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2013-09-16 07:00 | 2013-10-10 17:00 | N | N | 72 kV oil system upgrades | Line
ATCO | 7L97 (820s Hangingstone - 933s Tower Road) | 2013-09-16 08:00 | 2013-09-28 18:00 | N | N | install inline switches & connect tap to new sub | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 150AL (271s Shell Jumping Pound - 150L tap),150L (20s Ghost - 150L46),150L (42s Sarcee - 150L47) | 2013-09-16 08:00 | 2013-09-26 08:00 | N | N | connect 150AL1 to 150AL | Line
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2013-09-16 09:00 | 2013-09-24 16:00 | N | N | STR replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 69s T4 (69s North Barrhead) | 2013-09-16 13:00 | 2013-09-21 17:00 | N | Y | replace T4 protection, replace 69s713 CTs | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray),150L (20s Ghost - 150L46),56L (245s Seebe - 20s Ghost),80L (20s Ghost - 80L193A),859L (20s Ghost - T793s Horse Creek) | 2013-09-17 13:00 | 2013-09-21 16:00 | N | N | replace 138 kV switch, T5 Oil, 138 kV CT | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 814L (121s Brooks - 28s West Brooks),931L (132s Ware Junction - 28s West Brooks),28s 240 kV Bus #1 | 2013-09-18 08:00 | 2013-09-21 18:00 | N | Y | maintenance | Terminal Equipment, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 911L (74s Janet - 59s Peigan) | 2013-09-20 08:00 | 2013-10-02 12:00 | N | Y | cut in ENMAX 25 sub, P&C and telecom | Line |  |  | 240 kV, Overload
ALTALINK | 1003L (74s Janet - ENMAX 25) | 2013-09-20 08:00 | 2013-09-30 16:00 | N | N | Refer to the Op Plan binder for the commissioning plan. ISD: Sept 30, 2013. | Line
ALTALINK | 928L (17s Benalto - 42s Sarcee) | 2013-09-20 08:00 | 2013-09-29 18:00 | N | Y | WATL - reconfigure line | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ATCO | 7L104 (856s Kinosis - 989s Quigley) | 2013-09-20 08:00 | 2013-09-25 16:00 | N | N | conductor resag | Line |  |  | For Information Only
ALTALINK | 727L (74s Janet - 678s Okotoks) | 2013-09-20 08:00 | 2013-09-27 17:00 | N | N | cut over 1003L going to new ENMAX 25 sub | Line |  |  | Pre-Condition, Overload
ALTALINK | 841L (477s Amoco West Pembina - 489s Amoco Canada Brazeau River) | 2013-09-20 08:00 | 2013-09-22 17:00 | N | N | Replace 841L Line protections | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2013-09-20 12:00 | 2013-09-22 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 10.1TR (ENMAX 10),10.4TR (ENMAX 10),9.62L (ENMAX 10 - ENMAX 9) | 2013-09-20 21:00 | 2013-09-21 | N | N | sub washing 10 sub | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2013-09-21 07:00 | 2013-09-22 07:00 | N | N | road widening near 24.83L | Line
ALTALINK | 38s T4 (38s East Edmonton) | 2013-09-21 07:00 | 2013-09-22 17:00 | N | Y | replace 38s18 breaker control module | Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2013-09-21 07:00 | 2013-09-22 07:00 | N | N | road widening | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 803s T3 (803s Lambton),72LH8 (Hardisty - 803s Lambton),72LS24 (Strathcona - 803s Lambton) | 2013-09-21 08:00 | 2013-09-22 18:00 | N | Y | doble work maintenance on TX3 and ion meter commissioning | Transformer, Line |  |  | 240 kV, For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2013-09-21 08:00 | 2013-09-21 12:00 | N | N | pot head & line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),38s 731E (38s East Edmonton) | 2013-09-21 08:00 | 2013-11-01 00:01 | N | N | Forced Outage | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2013-09-21 08:00 | 2013-09-22 18:00 | N | N | Jasper P&C upgrade | Line
ALTALINK | 394s T3 (394s Empress),394s T4 (394s Empress) | 2013-09-21 09:00 | 2013-09-21 11:00 | N | N | Customer Testing their Manual Transfer Scheme | Transformer
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2013-09-21 13:00 | 2013-09-21 17:00 | N | N | pot head & line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 56L (245s Seebe - 20s Ghost),80L (20s Ghost - 80L193A),20s T5 (20s Ghost),20s Ghost 138 kV north bus | 2013-09-21 17:00 | 2013-09-27 17:00 | N | N | Replace 138kV Switches, T5 LA's | Line, Transformer, Bus |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2013-09-22 08:00 | 2013-09-22 12:00 | N | N | sub washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1055L (629s Argyll Transfer - 816s Petrolia) | 2013-09-22 08:00 | 2013-09-22 18:00 | N | Y | doble maintenance at 629s Argyll | Line |  |  | 240 kV
ENMAX | 32.82L (ENMAX 54 - ENMAX 32) | 2013-09-22 08:00 | 2013-12-23 16:00 | N | N | re-conductor | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L20 (766s Nevis - 755s Cordel) | 2013-09-22 08:00 | 2013-09-23 17:00 | N | Y | clearing 9L20 to allow dragline to walk through | Line |  |  | 240 kV, Pre-Condition, Restricts Generation
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2013-09-22 13:00 | 2013-09-22 17:00 | N | N | sub washing | Line, Transformer
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2013-09-22 17:00 | 2013-09-22 18:00 | N | N | pot head washing | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2013-09-22 19:00 | 2013-09-22 20:00 | N | N | pot head washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 69s T2 (69s North Barrhead),69s T4 (69s North Barrhead),69s North Barrhead 138kV Bus | 2013-09-23 07:00 | 2013-09-24 07:00 | N | Y | bus protection upgrade | Transformer, Bus |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 723L (69s North Barrhead - 723L133) | 2013-09-23 07:00 | 2013-09-24 15:00 | N | N | replace PTs/J-Box associated with 69s48 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s C1 (17s Benalto),17s T2 (17s Benalto),17s Benalto 240 kV South Bus 2 | 2013-09-23 07:30 | 2013-09-23 17:30 | N | Y | insulators replacement & 17s9 CT replacement | Bus, Shunts, Transformer |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2013-09-23 07:30 | 2013-09-23 18:00 | N | N | breaker CT doble | Line
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2013-09-23 08:00 | 2013-09-30 18:00 | N | N | erect new steel monopoles | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 939s 903T (939s Livock) | 2013-09-23 08:00 | 2013-10-31 16:00 | N | Y | Livock PST is unavailable for operation | Transformer |  |  | 240 kV
ALTALINK | 484S Millar Western,825L (484s Millar Western - 77s Sagitawah),77s 552 (77s Sagitawah),77s 652 (77s Sagitawah) | 2013-09-23 08:00 | 2013-09-23 19:00 | N | N | replace insulators | Line, Circuit Breaker, Station
EPCOR | 805s J2403 (805s Jasper) | 2013-09-23 08:00 | 2013-09-29 18:00 | N | Y | CT JB replacement for protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 650s 752 (650s Hansman Lake) | 2013-09-23 08:00 | 2013-09-24 18:00 | N | Y | add new sync check relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Saskpower | Sask Power S1C line | 2013-09-23 08:00 | 2013-09-25 08:00 | N | Y | install screw pile | Line |  |  | Limits ATC
EPCOR | 72CK12 (987s Clover Bar - Kennedale),987s Cloverbar 72kV Bus 3 | 2013-09-23 08:00 | 2013-09-23 18:00 | N | Y | maintenance & doble | Bus, Line
EPCOR | 814s T2 (814s Bellamy) | 2013-09-23 08:00 | 2013-10-25 17:00 | N | Y | bushing replacement | Transformer |  |  | 240 kV
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2013-09-23 08:00 | 2013-09-30 18:00 | N | N | Erect steel for new #10 sub | Line
ALTALINK | 77s T2 (77s Sagitawah),77s Sagitawah 138 kV East Bus | 2013-09-23 08:00 | 2013-09-27 17:00 | N | Y | replace insulators | Bus, Transformer |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 409s T2 (409s Shell Scotford),856L (409s Shell Scotford - 410s Josephburg),ALC01L (409s Shell Scotford - 408s Air Liquide Scotford),409s Shell Scotford 138 kV bus B1 | 2013-09-23 09:00 | 2013-09-27 15:00 | N | N | maintenance | Bus, Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 437s T1 (437s Baymag) | 2013-09-23 10:00 | 2013-09-24 16:00 | N | N | customer requested outage | Transformer
ALTALINK | 437s T2 (437s Baymag) | 2013-09-23 10:00 | 2013-09-26 17:00 | N | N | transformer oil leak | Transformer
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2013-09-23 10:00 | 2013-09-27 16:00 | N | Y | component replacement | Line |  |  | Pre-Condition, Restricts Generation
ATCO | 832s 701T (832s Blumenort) | 2013-09-23 11:00 | 2013-09-25 15:00 | N | N | repair oil leaks | Transformer
ATCO | 7L48 (A793s West Peace River - 784s Donnelly) | 2013-09-23 12:00 | 2013-09-27 12:00 | N | N | climbing inspection | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s 2652 (63s Red Deer) | 2013-09-23 12:00 | 2013-09-26 17:00 | N | Y | 240kV Breaker Maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | Genesee Network Disruption | 2013-09-23 23:00 | 2013-09-24 05:00 | N | N |  | SCInternal |  |  | Affects Visibility, For Information Only
ALTALINK | 150L (42s Sarcee - 150L47) | 2013-09-24 | 2013-09-24 05:00 | N | N | Wades House Moving Ltd high load move under 150L | Line
ATCO, ALTALINK | 723L (69s North Barrhead - 723L133),7L230 (69s North Barrhead - 7L230 tap),69s Partial 138kV Bus | 2013-09-24 07:00 | 2013-09-25 07:00 | N | N | replace 69s 138kV bus protection | Line, Terminal Equipment |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
AESO-SC | Alberta Newsprint load outage | 2013-09-24 07:00 | 2013-09-24 09:30 | N | N |  | SCInternal |  |  | For Information Only
ALTALINK | 928L (17s Benalto - 42s Sarcee),17s 9 (17s Benalto),17s 8 (17s Benalto) | 2013-09-24 07:30 | 2013-09-27 17:30 | N | N | 17s600 replacement & 17s9 CT replacement | Circuit Breaker, Line
ALTALINK | 934L (132s Ware Junction - 801s Anderson),132s Ware Junction 240 kV north bus | 2013-09-24 08:00 | 2013-09-27 19:00 | N | Y | move 934L back to original position at 132s - HATD CWJ | Line, Bus |  |  | 240 kV, Pre-Condition
ATCO | 7L31 (732s Mitsue - 844s AEC MILL) | 2013-09-24 08:00 | 2013-09-27 08:00 | N | N | to facilitate the replacement of 732s mitsue 701b | Line
ALTALINK | 422S Westwood | 2013-09-24 08:00 | 2013-09-24 18:00 | N | N | install animal cover up @ the AMI terminators and complete 25 kV bus protection modifications | Station
ALTALINK | 254s T1 (254s Coaldale),254s 35 (254s Coaldale) | 2013-09-24 09:00 | 2013-09-25 17:00 | N | N | maintain and doble transformer and perform ABB breaker maintenance | Transformer, Circuit Breaker
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap),6L12 (6L25 tap - 774s Monitor),6L25 (773s Coronation - 6L12 tap) | 2013-09-24 09:00 | 2013-09-24 16:00 | N | N | replace poles on 6L25, Maintenance on 6L12D3 | Line
ATCO, IPP | 6L05 (843s Bigknife Creek - 757s Battle River),7L701 (223s Strome - 7L701D1) | 2013-09-24 09:00 | 2013-09-24 17:00 | N | N | repair and remove CTs | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 409s Shell Scotford RTU/SCADA | 2013-09-24 09:00 | 2013-09-24 11:00 | N | N | Cutover of Supervisory Circuits to new MPLS Telecom System | Terminal Equipment |  |  | Affects Visibility
ATCO | 773s 601T (773s Coronation) | 2013-09-24 09:00 | 2013-09-24 16:00 | N | N | 601T maintenance | Transformer
ALTALINK | 113L (20s Ghost - 33s Spray),150L (20s Ghost - 150L46),20s Ghost 138 kV South Bus | 2013-09-24 12:00 | 2013-09-24 16:00 | N | N | testing 20s153 Interlock Scheme | Bus, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2013-09-25 01:30 | 2013-09-25 04:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 752s 701T (752s Albright&Wilson) | 2013-09-25 08:00 | 2013-10-10 08:00 | N | N | move grounding resistor, change neutral CTs | Transformer
EPCOR | 816s P2402 (816s Petrolia) | 2013-09-25 08:00 | 2013-09-25 16:00 | N | Y | CTs doble | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 63s 552 (63s Red Deer) | 2013-09-25 09:30 | 2013-09-25 10:30 | N | Y | switching training | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 840S McNeill Station | 2013-09-25 12:00 | 2013-09-25 20:00 | N | N | replacement / repair to a wave trap - SasPower work for 9LS1M | Station |  |  | Limits ATC
ALTALINK | 198s T2 (198s Blackfalds) | 2013-09-25 13:30 | 2013-09-25 14:30 | N | N | Altalink Switching Training | Transformer |  |  | For Information Only
DAISHOWA | 147s Daishowa Plant RTU/SCADA | 2013-09-25 23:00 | 2013-09-27 08:00 | N | N | TELUS repair work | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2013-09-26 01:30 | 2013-09-26 04:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 840S McNeill Station | 2013-09-26 07:00 | 2013-09-26 20:00 | N | N | replacement / repair to a wave trap - SasPower work for 9LS1M | Station |  |  | Limits ATC
EPCOR | RossdaleT1 (Rossdale) | 2013-09-26 07:30 | 2013-09-27 18:00 | N | N | TX1 SFRA | Transformer
EPCOR | 803s L2401 (803s Lambton) | 2013-09-26 08:00 | 2013-09-26 18:00 | N | Y | CTs doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 404S Peace Butte,600L (523s Bullshead - 404s Peace Butte) | 2013-09-26 09:00 | 2013-09-26 17:00 | N | N | circuit switcher latch replacement and re-attach line shield wire on switch | Line, Station
ALTALINK | 225s Magrath RTU/SCADA | 2013-09-26 09:00 | 2013-09-26 16:00 | N | N | preventative maintenance tasks on communication equipment | Terminal Equipment |  |  | Affects Visibility
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2013-09-26 14:00 | 2013-09-26 18:00 | N | N | Sub Washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2013-09-27 00:01 | 2013-10-23 17:00 | N | N | 25kV and T5 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L86 (822s Wolf Lake - 877s Foster Creek) | 2013-09-27 06:00 | 2013-09-28 20:00 | N | Y | change structures for road clearance | Line |  |  | Restricts Generation
Saskpower | Sask Power S1C line | 2013-09-27 07:00 | 2013-09-27 16:00 | N | N | install screw piles | Line |  |  | Limits ATC
ATCO | 7L49 (732s Mitsue - 729s Otauwau),7L23 (732s Mitsue - 858s Narrows Creek) | 2013-09-27 08:00 | 2013-09-30 08:00 | N | Y | 7L49 (732s Mitsue - 729s Otauwau),facilitate replacement of 702B | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 and 240 kV Bus 2 GOI | 2013-09-27 08:00 | 2013-09-27 16:00 | N | Y | correct phasing for putting 911L back in service | Terminal Equipment, Shunts |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2013-09-27 09:00 | 2013-09-27 16:00 | N | N | structure replacement to accommodate County road work | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2013-09-28 07:00 | 2013-09-28 19:00 | N | N | bridge move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2013-09-28 08:00 | 2013-09-30 16:00 | N | N | Refer to the Op Plan binder for the commissioning plan. ISD: Sept 30, 2013. | Line
ATCO | 7L587 (826s Marguerite Lake - 822s Wolf Lake) | 2013-09-28 08:00 | 2013-10-02 16:00 | N | N | In service date: Oct. 1, 2013 | Line
ATCO | 2014S Halfway | 2013-09-28 08:00 | 2013-10-02 16:00 | N | N | In service date: Oct. 1, 2013. | Station
ATCO | 936S Norberg | 2013-09-28 08:00 | 2013-10-02 16:00 | N | N | In service date: Oct 1, 2013 | Station
ALTALINK | 826L (701s Blue Ridge Lumber - 77s Sagitawah) | 2013-09-28 08:00 | 2013-09-29 18:00 | N | N | replace insulators | Line
ALTALINK | 933L (132s Ware Junction - 801s Anderson) | 2013-09-28 08:00 | 2013-10-04 17:00 | N | N | In service date: October 3, 2013 | Line
ALTALINK | 1075L (132s Ware Junction - 28s West Brooks) | 2013-09-28 08:00 | 2013-10-04 17:00 | N | N | In service date: October 3, 2013 | Line
ALTALINK | 28s R1 (28s West Brooks),28s T1 (28s West Brooks),814L (121s Brooks - 28s West Brooks),933L (28s West Brooks - 801s Anderson),28s 240kV Bus 1 (28s West Brooks) | 2013-09-28 08:00 | 2013-10-04 10:00 | N | Y | maintenance,re-align 933L just outside 28s,re-terminating 9L33 into 132s ware junction | Bus, Line, Transformer, Shunts |  |  | 240 kV, Overload, Restricts Generation
ALTALINK | 180S Cope Creek | 2013-09-28 08:00 | 2013-10-02 16:00 | N | N | In service date: Oct 1, 2013 | Station
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2013-09-28 08:00 | 2013-09-28 11:00 | N | N | line washing | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2013-09-28 13:00 | 2013-09-28 16:00 | N | N | line washing | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2013-09-28 13:00 | 2013-09-28 19:00 | N | N | sub washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1058L (657s Summerside - 803s Lambton) | 2013-09-29 08:00 | 2013-09-29 18:00 | N | Y | doble work oil maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.2TR (ENMAX 43),33.84L (ENMAX 43 - ENMAX 33) | 2013-09-29 08:00 | 2013-09-30 11:00 | N | N | sub washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 840S McNeill Station,830L (562s Cypress - 840s McNeill Station),840s 901T (840s MCNEILLSTATION),840s 701T (840s MCNEILLSTATION) | 2013-09-30 07:30 | 2013-10-11 16:00 | Y | Y | McNeill maintenance turnaround | Transformer, Station, Line |  |  | Limits ATC, For Information Only
ALTALINK | 17s 13 (17s Benalto) | 2013-09-30 08:00 | 2013-10-03 15:00 | N | Y | 17s13 CT replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2013-09-30 08:00 | 2013-10-04 16:00 | N | Y | LTC maintenance | Transformer |  |  | 240 kV, Overload
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat) | 2013-09-30 08:00 | 2013-09-30 10:00 | N | Y | connect 472s mobile to 880L | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 816s T1 (816s Petrolia) | 2013-09-30 08:00 | 2013-10-04 18:00 | N | Y | tapchanger maintenance and PRD replacement | Transformer |  |  | 240 kV, For Information Only
ATCO | 7L70 (700s Bonnyville - 819s Whitby Lake) | 2013-09-30 08:00 | 2013-09-30 17:00 | N | N | tap new 7LA139 to existing 7L70 at fly in jumpers | Line |  |  | For Information Only
ATCO | 801s Anderson RTU/SCADA | 2013-09-30 08:00 | 2013-10-02 12:00 | N | N | upgrade and changes | Terminal Equipment |  |  | Affects Visibility
ATCO | 851s Morse River RTU/SCADA | 2013-09-30 09:00 | 2013-10-01 17:00 | N | N | download updates for HMI | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2) | 2013-09-30 09:00 | 2013-09-30 16:30 | N | N | line mitigation | Line |  |  | Overload
ALTALINK | 171s T1 (171s Redwater) | 2013-09-30 10:00 | 2013-10-05 17:00 | N | N | oil reclaim | Transformer |  |  | For Information Only
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2013-09-30 10:00 | 2013-10-04 16:00 | N | Y | component replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 848s 906 (848s Ruth Lake) | 2013-09-30 10:00 | 2013-10-03 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 790s 702T (790s Poplar Hill) | 2013-09-30 10:00 | 2013-10-03 15:00 | N | N | tap changer | Transformer |  |  | For Information Only
ALTALINK | 19s 72 (19s Wabamun) | 2013-09-30 11:00 | 2013-10-03 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 33s5 (33s Spray) | 2013-09-30 11:00 | 2013-10-07 15:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2013-09-30 13:00 | 2013-09-30 19:00 | N | N | sub washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38) | 2013-10-01 07:30 | 2013-10-02 15:00 | N | Y | repair fuses | Shunts |  |  | Limits ATC
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2013-10-01 08:00 | 2013-10-02 18:00 | N | Y | install temp bypass to allow constrcution of 554s tap point on 1036L | Line |  |  | 240 kV, For Information Only
ATCO | 876s 901T (876s Brintnell) | 2013-10-01 08:00 | 2013-10-01 11:00 | N | Y | isolation of 901T to find and fix ground fault on gas relay | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 132s Ware Junction 240kV South Bus | 2013-10-01 08:00 | 2013-10-03 18:00 | N | Y | string 1075L into station | Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2013-10-01 08:00 | 2013-10-01 12:00 | N | N | sub washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2013-10-01 08:00 | 2013-10-04 17:00 | N | N | insulator washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 276s 16 (276s Un Carb Prentiss) | 2013-10-01 08:00 | 2013-10-10 17:00 | N | N | breaker replacement | Circuit Breaker
ATCO | 7L82 (788s Hotchkiss - 855s Hamburg) | 2013-10-01 09:30 | 2013-10-01 16:30 | N | N | complete PM on breaker 705 switching required at 788s | Line | will be performed by the peace river tech department.Would like to have the outage by opening 7L82. If 7L82D2 is closed for the outage then protection setting change will be required at West Peace, Hotchkiss and Ring Creek. |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 755s 903 (755s Cordel) | 2013-10-01 10:00 | 2013-10-01 14:00 | N | Y | maintenance & counter replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 729s 702T (729s Otauwau),6L73 (729s Otauwau - 745s Slave Lake) | 2013-10-01 10:00 | 2013-10-01 14:30 | N | N | offline oil reclamation of 702T | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek),347s 199E (347s Fox Creek) | 2013-10-01 11:00 | 2013-10-02 17:00 | N | N | breaker maintenance,maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 918L (17s Benalto - 162s Beddington) | 2013-10-02 07:30 | 2013-10-11 18:00 | N | Y | WATL - reconfigure line | Line |  |  | 240 kV, Pre-Condition, Limits ATC
EPCOR | NamaoT2 (Namao) | 2013-10-02 08:00 | 2013-10-02 18:00 | N | N | internal inspection | Transformer
ATCO | 9L933 (28s West Brooks - 801s Anderson) | 2013-10-02 08:00 | 2013-10-02 17:00 | N | N | testing with AltaLink to Ware Junction for new termination | Line
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2013-10-02 08:00 | 2013-10-04 16:00 | N | N | line inspection and install dampers | Line |  |  | Pre-Condition
EPCOR | 72RG1 (Rossdale - Garneau) | 2013-10-02 08:00 | 2013-10-02 18:00 | N | N | doble | Line
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2013-10-02 08:00 | 2013-10-05 16:00 | N | N | structure replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72NW15 (Namao - Woodcroft) | 2013-10-02 08:00 | 2013-10-02 18:00 | N | N | provide proper limits of approach | Line
ALTALINK | 966L (650s Hansman Lake - 932s Pemukan) | 2013-10-02 08:00 | 2013-10-02 14:00 | N | Y | switch repair | Line |  |  | 240 kV
ATCO | 755s 904 (755s Cordel) | 2013-10-02 10:00 | 2013-10-02 14:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 650s 752 (650s Hansman Lake) | 2013-10-02 14:00 | 2013-10-02 17:00 | N | Y | center phase has a low nitrogen alarm | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 523S 138 kV Bus | 2013-10-03 06:00 | 2013-10-03 08:00 | N | N | emergency bus repair | Bus |  |  | Pre-Condition
ENMAX | 9.61L (ENMAX 23 - ENMAX 9),23B69-9.61 (ENMAX 23) | 2013-10-03 08:00 | 2013-10-03 15:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),ENMAX 25 B240-D136 (ENMAX 25) | 2013-10-03 08:00 | 2013-10-03 09:00 | N | Y | CT ratio change | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
EPCOR | 557s T1 (557s Castle Downs) | 2013-10-03 08:00 | 2013-10-04 18:00 | N | Y | tap changer maintenance | Transformer |  |  | 240 kV, For Information Only
ATCO | 707S St.Paul | 2013-10-03 08:30 | 2013-10-03 16:30 | N | Y | 503VR apchanger maintenance | Station |  |  | For Information Only
ALTALINK | 895s Suffield RTU/SCADA | 2013-10-03 10:00 | 2013-10-03 12:00 | N | N | RTU points cleanup | Terminal Equipment |  |  | Affects Visibility
ATCO | 755s 905 (755s Cordel) | 2013-10-03 10:00 | 2013-10-03 14:00 | N | Y | breaker maintenance & counter replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat) | 2013-10-03 10:00 | 2013-10-03 12:00 | N | Y | remove 472s mobile from 880L | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz),86s 1752 (86s Bigstone) | 2013-10-04 07:30 | 2013-10-04 17:00 | N | Y | gas pressure increase | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Limits ATC
AESO-SC | Phone Outage | 2013-10-04 08:00 | 2013-10-04 16:00 | N | N | NX01 Nexen phone upgrade | SCInternal |  |  | For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2013-10-04 08:00 | 2013-10-06 16:00 | N | N | doble, breaker maintenance & line work | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 10.60L (ENMAX 10 - ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2013-10-05 07:00 | 2013-10-05 09:00 | N | N | 28 sub wash | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 5L92 (Cranbrook - Selkirk) | 2013-10-05 09:00 | 2013-10-11 21:00 | Y | Y | replace D/E insulators and install arcing horns | Line |  |  | Limits ATC, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),10.60L (ENMAX 10 - ENMAX 28) | 2013-10-05 09:00 | 2013-10-05 11:00 | N | N | 28 sub wash | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 86s T1 (86s Bigstone) | 2013-10-05 10:00 | 2013-10-05 17:00 | N | Y | maintenance | Transformer |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2013-10-05 13:00 | 2013-10-05 16:00 | N | N | oil sampling from potheads | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2013-10-06 08:00 | 2013-10-17 17:00 | N | Y | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 10.60L (ENMAX 10 - ENMAX 28) | 2013-10-06 08:00 | 2013-10-06 16:00 | N | N | line washing | Line
ENMAX | 65.1 TR (ENMAX 65) | 2013-10-06 08:00 | 2013-10-18 16:00 | N | N | forced outage | Transformer |  |  | 240 kV, For Information Only
ENMAX | 65.2 TR (ENMAX 65) | 2013-10-06 08:00 | 2013-10-11 16:00 | N | N | forced outage | Transformer |  |  | 240 kV, For Information Only
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2013-10-06 10:00 | 2013-10-06 14:00 | N | N | sub washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s97N (535s Joffre),330L1 (I-330s Nova Corp Plant - 535s Joffre) | 2013-10-06 11:00 | 2013-10-09 15:00 | N | N | customer requested outage | Switch, Line |  |  | Pre-Condition
ALTALINK | 482S Haynes | 2013-10-07 07:30 | 2013-10-07 16:30 | N | N | customer grounding request | Station
EPCOR | 330p 1201 (330p Genesee) | 2013-10-07 08:00 | 2013-11-01 18:00 | N | Y | breaker replacement | Circuit Breaker |  |  | Restricts Generation, Contingency Requires Mitigation, 500 kV
EPCOR | 809L (320p Keephills - 330p Genesee) | 2013-10-07 08:00 | 2013-11-08 18:00 | N | N | preparation work for the HVDC Project | Line
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2013-10-07 08:00 | 2013-10-18 17:00 | N | N | replace Tx feeding 551IL | Line
EPCOR | 805s T4 (805s Jasper) | 2013-10-07 08:00 | 2013-10-11 18:00 | N | Y | SFRA and LTC monitor | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2013-10-07 08:00 | 2013-10-07 17:00 | N | N | install bird protection / diverters | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2013-10-07 08:00 | 2013-10-08 16:00 | N | N | excavation around ducts at 5 Sub | Line
ENMAX | 13.82L (ENMAX 22 - ENMAX 13) | 2013-10-07 08:00 | 2013-10-13 16:00 | N | N | insulator changeout | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2406 (805s Jasper),805s J2405 (805s Jasper) | 2013-10-07 08:00 | 2013-10-11 18:00 | N | N | SFRA and LTC monitor | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Rossdale R724 (Rossdale) | 2013-10-07 08:00 | 2013-10-07 16:00 | N | N | doble CT's etc. | Circuit Breaker
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2013-10-07 08:00 | 2013-10-10 18:00 | N | N | insulator washing | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ATCO | 755s 906 (755s Cordel) | 2013-10-07 10:00 | 2013-10-07 14:00 | N | Y | maintenance and counter replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 856s 901 (856s Kinosis) | 2013-10-07 10:00 | 2013-10-08 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 970s 708 (970s Bourque),970s 705 (970s Bourque) | 2013-10-07 11:00 | 2013-10-11 16:00 | N | N | facilitate line protection work | Circuit Breaker |  |  | For Information Only
ATCO | 741s 702T (741s Fox Creek) | 2013-10-07 13:30 | 2013-10-30 16:00 | N | N | transformer replacement | Transformer |  |  | Creates Radial Feeds
ALTALINK | 719L (575s Sundre - 719L135W) | 2013-10-08 07:00 | 2013-10-09 17:00 | N | N | relocate 719LX to bus #2 | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 28s 2 (28s West Brooks) | 2013-10-08 07:00 | 2013-10-09 17:00 | N | Y | replace CT's | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 39s 29 (39s Bickerdike) | 2013-10-08 08:00 | 2013-10-08 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310P T36 (310p Sundance),310p T30 (310p Sundance),310p Sundance 240kV Bus C | 2013-10-08 08:00 | 2013-10-08 17:00 | N | Y | repair 55 degree hot spot 310p28C switch repair | Transformer, Bus |  |  | 240 kV, Pre-Condition
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2013-10-08 08:00 | 2013-10-21 16:00 | N | N | 72KV oil syatem Upgrades | Line
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2013-10-08 08:00 | 2013-10-11 16:00 | N | N | line inspection and install dampers | Line |  |  | Pre-Condition
ALTALINK | 121s T5 (121s Brooks) | 2013-10-08 08:00 | 2013-10-09 17:00 | N | N | bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden),197s 174E (197s Bardo) | 2013-10-08 08:00 | 2013-10-10 17:00 | N | N | Replace CT | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage
ATCO | 863s 901 (863s Paintearth) | 2013-10-08 10:00 | 2013-10-08 15:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2013-10-08 10:00 | 2013-10-11 16:00 | N | Y | component replacement | Line |  |  | Overload, Restricts Generation
ALTALINK | 650s 852 (650s Hansman Lake) | 2013-10-08 12:00 | 2013-10-08 14:00 | N | Y | Install low temperature alarm. | Circuit Breaker |  |  | 240 kV
ALTALINK | 650s 952 (650s Hansman Lake) | 2013-10-08 15:00 | 2013-10-08 17:00 | N | Y | install low temperature alarm. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p T4 (320p Keephills) | 2013-10-09 08:00 | 2013-10-11 17:00 | N | N | 138 kV and 25 kV bushing replacement | Transformer
ALTALINK | 38S East Edmonton | 2013-10-09 08:00 | 2013-10-09 17:00 | N | N | replace bus differential on the 138KV B1 | Station
EPCOR | 816s P2402 (816s Petrolia) | 2013-10-09 08:00 | 2013-10-09 16:00 | N | Y | oil samples | Circuit Breaker |  |  | 240 kV
ALTALINK | 650s T1 (650s Hansman Lake) | 2013-10-09 08:00 | 2013-10-10 17:00 | N | Y | Transformer maintenance | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 801L (294s Brazeau Outlet Works - 801L302 Tap) | 2013-10-09 08:30 | 2013-10-09 17:00 | N | N | replacing rotten cross arm | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1852 (310p Sundance) | 2013-10-09 10:00 | 2013-10-10 17:00 | N | Y | Replace leaking grading caps | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 788L (788L Tap - 898s Heart Lake) | 2013-10-09 13:00 | 2013-10-09 17:00 | Y | N | replacing broken insulators | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 551L (945s Sunshine Village - 123s Banff) | 2013-10-10 04:30 | 2013-10-10 06:00 | N | N | remove osprey nest | Line |  |  | For Information Only
ALTALINK | 28s 47 (28s West Brooks) | 2013-10-10 08:00 | 2013-10-10 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 709s Vegreville RTU/SCADA | 2013-10-10 08:00 | 2013-10-11 17:00 | N | N | download PLC & update HMI program | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2013-10-10 08:00 | 2013-10-11 17:00 | N | N | Fortis stringing 25kV beside 720L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 65 B240-D131 (ENMAX 65),ENMAX 65 B240-D134 (ENMAX 65) | 2013-10-10 08:00 | 2013-10-11 16:00 | N | Y | crane work to repair breaker | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 1352 (310p Sundance) | 2013-10-10 08:00 | 2013-10-10 17:00 | N | N | repair | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L92 (819s Whitby Lake - 777s Vilna) | 2013-10-10 09:00 | 2013-10-10 16:00 | N | N | wire and commission breaker failure transfer | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 330L1 (I-330s Nova Corp Plant - 535s Joffre),535s96N (535s Joffre) | 2013-10-10 11:00 | 2013-10-14 15:00 | N | N | customer requested outage | Switch, Line |  |  | Pre-Condition, For Information Only
ALTALINK | 64s East Crossfield RTU/SCADA | 2013-10-10 12:00 | 2013-10-10 17:00 | N | N | RTU configuration update | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2013-10-11 02:00 | 2013-10-11 04:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s Joffre 138kV Bus 4 | 2013-10-11 08:00 | 2013-10-11 14:00 | N | N | energize new cap bank at 535s | Bus |  |  | Contingency Requires Mitigation
ALTALINK | 522L (320p Keephills - 522L6),320pT5 (320p Keephills) | 2013-10-11 08:00 | 2013-10-11 17:00 | N | N | replace 69 kV LA | Transformer, Line
ALTALINK | 394s T3 (394s Empress),394s T4 (394s Empress) | 2013-10-11 09:00 | 2013-10-11 12:00 | N | N | customer testing their manual transfer scheme | Transformer
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2013-10-12 07:00 | 2013-10-12 19:00 | N | Y | install footings under line - WATL | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2013-10-12 08:00 | 2013-10-14 16:00 | N | N | 9B138-9.83 breaker maintenance | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
AESO-SC | 535s Joffre 50 MVAr Cap Bank | 2013-10-12 08:00 | 2013-10-18 17:00 | N | N | In service date: Oct. 15, 2013 | Shunts
Syncrude | D05 T2 (D05 Syncrude) | 2013-10-14 08:00 | 2013-10-21 17:00 | N | Y | transformer upgrade | Transformer |  |  | 240 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2013-10-15 06:16 | 2013-10-18 16:00 | N | Y | forced outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 28s 8 (28s West Brooks) | 2013-10-15 07:00 | 2013-10-16 17:00 | N | Y | replace CT's | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 942L (71s Lamoureux - 13s Deerland) | 2013-10-15 08:00 | 2013-10-24 17:00 | N | Y | re-string OHSW as OPGW - Heartland | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),197s 174W (197s Bardo) | 2013-10-15 08:00 | 2013-10-17 17:00 | N | N | replace CT | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 64s T2 (64s East Crossfield),901AL (64s East Crossfield - 901L tap) | 2013-10-15 08:00 | 2013-10-19 17:00 | N | Y | relay upgrade and SCADA equipment upgrade | Transformer, Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale R724 (Rossdale) | 2013-10-15 08:00 | 2013-10-15 16:00 | N | N | CT's doble tests | Circuit Breaker |  |  | For Information Only
ALTALINK | 132s 12 (132s Ware Junction),132s 15 (132s Ware Junction) | 2013-10-15 08:00 | 2013-10-23 19:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 809s 504R (809s Louise Creek) | 2013-10-15 08:15 | 2013-10-15 17:15 | N | N | major PM | Shunts |  |  | For Information Only
ATCO | 7L84 (722s Crystal Lake - 749s Flyinshot Lake) | 2013-10-15 09:00 | 2013-10-15 17:00 | N | N | raise crossing above highway | Line |  |  | Pre-Condition, Overload
ALTALINK | 58s T1 (58s Edson),202L (58s Edson - 178s Cynthia),740L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2013-10-15 10:00 | 2013-10-17 17:00 | N | N | bushing replacement,bushing replacement at 58s | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2013-10-15 10:00 | 2013-10-16 18:00 | N | N | replacing damaged cross arms | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 267s C3 (267s Killarney Lake) | 2013-10-15 10:00 | 2013-10-17 17:00 | N | N | replace existing CTs | Shunts |  |  | For Information Only
ALTALINK | 304s 195 (304s Shell Limestone) | 2013-10-15 10:00 | 2013-10-16 18:00 | N | N | temperature gauge repair, replace post insulator, breaker repair | Circuit Breaker |  |  | For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2013-10-15 10:00 | 2013-10-18 17:00 | N | Y | replace STRs 16,17 and 18. | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat) | 2013-10-15 10:00 | 2013-10-16 12:00 | N | Y | remove 472s mobile from 880L | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 757s 701T (757s Battle River) | 2013-10-15 10:00 | 2013-10-16 17:00 | N | N | transformer maintenance | Transformer
ALTALINK | 74s 2852 (74s Janet) | 2013-10-15 11:00 | 2013-10-17 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 421s T2 (421s Hays) | 2013-10-15 12:00 | 2013-10-17 17:00 | N | N | doble, maintenance, oil leak, SFRA | Transformer
Saskpower | Sask Power SW908 | 2013-10-15 12:00 | 2013-10-17 12:00 | N | Y | maintenance | Circuit Breaker |  |  | Limits ATC
ATCO | 7L70 (700s Bonnyville - 819s Whitby Lake) | 2013-10-15 13:00 | 2013-10-15 16:00 | N | N | to energize the new 936S Norberg substation | Line |  |  | Pre-Condition, For Information Only
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2013-10-15 17:01 | 2013-10-19 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2013-10-16 07:00 | 2013-10-16 17:00 | N | N | repair WDS10 switch | Line
ALTALINK | 929L (63s Red Deer - 74s Janet) | 2013-10-16 07:30 | 2013-10-25 17:00 | N | Y | WATL - reconfigure line at crossing point | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ATCO | 875s 701 (875s Algar) | 2013-10-16 08:00 | 2013-10-16 17:00 | N | N | maintain 701 breaker | Circuit Breaker |  |  | Pre-Condition
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2013-10-16 08:00 | 2013-10-18 16:00 | N | N | line inspection and install wire dampers | Line |  |  | Pre-Condition
ALTALINK | 310p 2452 (310p Sundance) | 2013-10-16 08:00 | 2013-10-20 17:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome) | 2013-10-16 08:00 | 2013-10-16 16:00 | N | Y | doble oil samples | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 526L (268s Whitecourt - 526DL185),526L (526DL365 - 526DL208) | 2013-10-16 08:00 | 2013-10-17 18:00 | N | N | replacement of air break 526DL208 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1752 (310p Sundance) | 2013-10-16 08:00 | 2013-11-08 17:00 | N | Y | replace breaker & CTs | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 33s 1 (33s Spray) | 2013-10-16 09:00 | 2013-10-16 17:00 | N | Y | 33s3 switch adjustments | Circuit Breaker |  |  | Restricts Generation
SUNCOR | Suncor RTU/SCADA | 2013-10-16 10:00 | 2013-10-16 12:00 | N | N | data concentrator | Terminal Equipment |  |  | Affects Visibility
CapitalPower | 615s Halkirk RTU/SCADA | 2013-10-16 11:00 | 2013-10-16 15:00 | N | N | remote tripping of breakers | Terminal Equipment |  |  | Affects Visibility, Impacts RAS
EPCOR | 805s T3 (805s Jasper) | 2013-10-17 08:00 | 2013-10-17 17:00 | N | N | doble oil samples | Transformer |  |  | 240 kV, For Information Only
ATCO | 732S Mitsue,732s 901T (732s Mitsue) | 2013-10-17 09:00 | 2013-10-17 14:00 | N | N | replace faulted 500PT1 | Station, Transformer
EPCOR | 805s C1 (805s Jasper) | 2013-10-18 08:00 | 2013-10-18 17:00 | N | Y | doble oil samples | Shunts |  |  | 240 kV
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge),725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron),370s179 (370s North Lethbridge) | 2013-10-18 22:00 | 2013-10-21 06:00 | N | N | level bus | Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia) | 2013-10-19 08:00 | 2013-10-20 18:00 | N | Y | CVT & SA doble and CTs at Argyll | Line |  |  | 240 kV
ALTALINK | 719L (256s Harmattan - 719L135X) | 2013-10-19 08:00 | 2013-10-19 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2013-10-19 08:00 | 2013-10-19 19:00 | N | N | protection upgrades | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 851L (525s Carseland - 253s Blackie) | 2013-10-19 08:00 | 2013-10-24 18:00 | N | N | rebuild line from structure 97 to structure 115 | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 80L (152s Didsbury - 80L194A) | 2013-10-20 08:00 | 2013-10-24 15:00 | N | N | replacing structures | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 30.2TR (ENMAX 30),30.81L (42s Sarcee - ENMAX 30) | 2013-10-20 08:00 | 2013-10-20 19:00 | N | N | switch maintenance & transformer repairs | Transformer, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2013-10-20 10:00 | 2013-10-20 19:00 | N | N | Oil sample and sheath test | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 907L (77s Sagitawah - 122s Alberta Newsprint) | 2013-10-21 07:00 | 2013-10-25 07:00 | N | N | protection upgrade | Line |  |  | 240 kV
EPCOR | 805s J2403 (805s Jasper) | 2013-10-21 08:00 | 2013-10-25 16:00 | N | Y | CT replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 672L (235s Entwistle - 131s Moon Lake) | 2013-10-21 08:00 | 2013-10-24 17:00 | N | N | connecting mobile at 474s | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38) | 2013-10-21 08:00 | 2013-10-24 19:00 | N | N | switches and bushings | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton) | 2013-10-21 08:00 | 2013-10-23 17:00 | N | N | insulator washing | Line |  |  | For Information Only
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2013-10-21 08:00 | 2013-10-24 16:00 | N | N | line inspection and install wire dampers | Line |  |  | Pre-Condition
ALTALINK | 38s T2 (38s East Edmonton) | 2013-10-21 08:00 | 2013-10-26 17:00 | N | N | protection replacement | Transformer |  |  | For Information Only
ALTALINK | 551GL1 (551GL) Advice | 2013-10-21 08:00 | 2013-11-01 16:00 | N | N | replace transformer feeding 551GL | Terminal Equipment |  |  | For Information Only
ALTALINK | 752L (64s East Crossfield - 752L67),64s 752X (64s East Crossfield) | 2013-10-21 08:00 | 2013-10-21 18:00 | N | N | relay upgrade | Circuit Breaker, Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds, Impacts RAS
EPCOR | Rossdale RG725 (Rossdale) | 2013-10-21 08:00 | 2013-10-21 18:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
ATCO | 9L80 (757s Battle River - 755s Cordel) | 2013-10-21 09:00 | 2013-11-07 16:00 | N | Y | ATCO maintenance | Line |  |  | 240 kV
ALTALINK | 58L (245s Seebe - 32s Barrier),90L (115s Mt. Allan - 32s Barrier) | 2013-10-21 11:00 | 2013-10-22 19:00 | N | N | removal/cleanup of 32s | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s T1 (370s North Lethbridge) | 2013-10-21 11:00 | 2013-10-21 17:00 | N | N | maintenance | Transformer |  |  | For Information Only
ATCO | 7L23 (858s Narrows Creek - 796s Nipisi),7L23 (732s Mitsue - 858s Narrows Creek) | 2013-10-21 13:00 | 2013-10-25 17:00 | N | N | maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (945s Sunshine Village - 123s Banff) | 2013-10-22 04:30 | 2013-10-22 06:00 | N | N | remove osprey nest | Line
ALTALINK | 80L (194s South Red Deer - 63s Red Deer),194s 80X (194s South Red Deer) | 2013-10-22 07:00 | 2013-10-22 11:00 | N | N | T2 protection testing | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 575s T1 (575s Sundre) | 2013-10-22 08:00 | 2013-10-26 17:30 | N | N | oil reclaim | Transformer
ALTALINK | 359s T1 (359s Esso West Pembina) | 2013-10-22 08:00 | 2013-10-22 17:00 | N | N | SFRA test | Transformer
NAKODA, ENMAX | 162.1TR (ENMAX 162 Beddington),162.81L (ENMAX 162 Beddington - 391S Balzac),162s 138-RB81 (162s Beddington),162s 138-RB80 (162s Beddington),162s 138-RB85 (162s Beddington) | 2013-10-22 08:00 | 2013-10-25 09:00 | N | Y | line relocation | Circuit Breaker, Transformer, Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RG7 (Rossdale - Garneau) | 2013-10-22 08:00 | 2013-10-22 16:00 | N | N | breaker/CTs arrestors, doble | Line
ALTALINK | 199L (268s Whitecourt - 199L187B) | 2013-10-22 09:30 | 2013-10-22 18:00 | N | N | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (194s South Red Deer - 217s North Red Deer),194s 80N (194s South Red Deer) | 2013-10-22 11:30 | 2013-10-22 13:30 | N | N | transformer protections testing | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 100L (895s Suffield - 498s Tilley),498s 100X (498s Tilley) | 2013-10-22 12:00 | 2013-10-22 16:00 | N | N | functional testing - T1 upgrade | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 156L (235s Entwistle - 156L 86A),235s 156E (235s Entwistle) | 2013-10-23 08:00 | 2013-10-25 17:00 | N | N | 235s32 138kV PT replacement | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 514L (396s Pincher Creek - 514BL tap),396s 514N (396s Pincher Creek) | 2013-10-23 08:00 | 2013-10-23 17:00 | N | N | upgrading TPR circuit | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 142S Magcan,727AL (142s Magcan - 727L39S),142s C1 (142s Magcan) | 2013-10-23 08:00 | 2013-10-23 12:00 | N | N | RTU replacement | Station, Line, Shunts |  |  | For Information Only
ALTALINK | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2013-10-23 08:00 | 2013-12-20 17:00 | N | N | outage required for approach to install new sewer/water lines | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 498s C1 (498s Tilley),498s T1 (498s Tilley),666L (498s Tilley - 28s West Brooks),498s 138 kV bus 1 (498s Tilley) | 2013-10-23 08:00 | 2013-10-23 17:00 | N | Y | functional test from T1 - energize T1 | Bus, Line, Shunts, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L92 (819s Whitby Lake - 777s Vilna) | 2013-10-23 08:00 | 2013-10-23 16:00 | N | N | ATCO connecting mobile | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 421s C1 (421s Hays) | 2013-10-23 09:00 | 2013-10-23 17:00 | N | Y | breaker maintenance | Shunts |  |  | For Information Only
ALTALINK | 258s 252 (258s Dow Hydrocarbons) | 2013-10-23 10:00 | 2013-10-23 11:00 | N | N | low gas repair | Circuit Breaker |  |  | For Information Only
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2013-10-24 08:00 | 2013-10-24 17:00 | N | N | insulator washing | Line |  |  | Overload, Over/Under Voltage
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2013-10-24 08:00 | 2013-10-24 16:00 | N | N | sub washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 25B240-D135 (ENMAX 25) | 2013-10-24 08:00 | 2013-10-24 16:00 | N | Y | inspection and adjustment | Circuit Breaker |  |  | 240 kV
ATCO | 939s 903T (939s Livock) | 2013-10-24 08:00 | 2013-10-24 16:00 | N | N | refer to Op Plan for commissioning plan | Transformer
ATCO | 711S Willingdon | 2013-10-24 09:00 | 2013-10-24 16:00 | N | N | maintenance | Station
ALTALINK | 968L (59s Peigan - 370s North Lethbridge),59s 1152 (59s Peigan) | 2013-10-24 09:00 | 2013-10-24 17:00 | N | Y | 240kV breaker maintenance and spring charge fail | Line, Circuit Breaker |  |  | 240 kV, Overload
ALTALINK | 131s T1 (131s Moon Lake) | 2013-10-24 12:00 | 2013-11-12 17:00 | N | N | installing new 25 kV metal clad switchgear | Transformer |  |  | Firm Load Loss
ENMAX | 23.1TR (ENMAX 23),23.2TR (ENMAX 23),23.3TR (ENMAX 23),23.80L (74s Janet - ENMAX 23),9.61L (ENMAX 23 - ENMAX 9) | 2013-10-24 19:00 | 2013-10-24 22:00 | N | N | sub washing | Line, Transformer |  |  | Overload, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),1003L (74s Janet - ENMAX 25),74s Janet 240kV Bus 2 | 2013-10-25 08:00 | 2013-10-28 18:00 | N | Y | ECTP: new wire. Commission new slack span. In conjunction with 74s Bus 2 outage | Transformer, Bus, Line, Shunts |  |  | Overload, Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ALTALINK | 850L (74s Janet - 525s Carseland) | 2013-10-25 08:00 | 2013-10-25 18:00 | N | N | ECTP: New 1003L slac span installation to A frame. | Line |  |  | Over/Under Voltage
ALTALINK | 780L (38s East Edmonton - 149s Nisku),38s11 (38s East Edmonton) | 2013-10-25 10:00 | 2013-10-25 11:00 | N | N | trip breaker to test 38sT2 protection upgrade | Switch, Line |  |  | Overload, Over/Under Voltage
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s79 (38s East Edmonton) | 2013-10-26 06:00 | 2013-10-26 06:45 | N | N | trip breaker to test 38sT2 protection upgrade | Switch, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 86s T1 (86s Bigstone),804L (86s Bigstone - 40s Wetaskiwin),805L (964s Pigeon Lake - 86s Bigstone),86s Bigstone 138kV bus | 2013-10-26 07:00 | 2013-10-26 17:00 | N | Y | installation of power PTs | Bus, Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1TR (ENMAX 21),21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),20.82L (ENMAX 21 - ENMAX 20),21.61L (ENMAX 21 - ENMAX 34),21.80L (42s Sarcee - ENMAX 21) | 2013-10-26 08:00 | 2013-10-26 16:00 | N | N | sub washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia) | 2013-10-26 08:00 | 2013-10-27 18:00 | N | Y | CVT"s, doble and CTs at Argyll | Line |  |  | 240 kV
ALTALINK | 33s3 (33s Spray) | 2013-10-26 08:00 | 2013-10-26 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 956S Watt Lake | 2013-10-26 08:00 | 2013-11-01 16:00 | N | N | In service date: Nov 1, 2013 | Station
AESO-SC | 276s C1 (276s Prentiss) | 2013-10-26 08:00 | 2013-10-31 17:00 | N | N | In service date: October 31, 2013 | Shunts
ALTALINK | 67s T2 (67s Stirling),820L (67s Stirling - 820AL tap),67s 2 (67s Stirling) | 2013-10-26 09:00 | 2013-10-26 17:00 | N | N | bushing doble, DGA and moisture test | Circuit Breaker, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L92 (819s Whitby Lake - 777s Vilna) | 2013-10-26 14:00 | 2013-10-26 16:30 | N | N | remove 750S mobile substation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 795L (121s Brooks - 421s Hays),121s 795X (121s Brooks) | 2013-10-28 07:00 | 2013-11-01 17:00 | N | N | protection upgrade | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2013-10-28 08:00 | 2013-11-22 16:00 | N | N | replace RV728 breaker | Line
ALTALINK | 942L (71s Lamoureux - 13s Deerland) | 2013-10-28 08:00 | 2013-11-08 17:00 | N | Y | re-string OHSW as OPGW & terminate 942L @ 12s - Heartland | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 747L (99s North St. Albert - 747DL4) | 2013-10-28 08:00 | 2013-10-30 17:00 | N | N | insulator washing | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 9L80 (757s Battle River - 755s Cordel) | 2013-10-28 08:00 | 2013-10-29 17:00 | N | N | test 9L80 A & B protection logic | Line
ALTALINK | 121s T5 (121s Brooks) | 2013-10-28 08:00 | 2013-10-29 18:00 | N | N | bushing replacement and 121s38 motor replacement | Transformer |  |  | For Information Only
ALTALINK | 132s Ware Junction 240kV North Bus | 2013-10-28 08:00 | 2013-11-01 19:00 | N | Y | replace switches 132s7 & 132s19. HATD - CWJ. | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 324s Cassils 240kV Bus 1 | 2013-10-28 08:00 | 2013-11-01 17:00 | N | Y | string 1053L into 324s - HATD CWJ | Bus |  |  | 240 kV
ALTALINK | 77s Sagitawah 138 kV West Bus | 2013-10-28 08:30 | 2013-11-01 17:00 | N | N | installation of Power PTs | Bus |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 6L79 (711s Willingdon - 707s St.Paul) | 2013-10-28 09:00 | 2013-10-28 17:00 | N | N | reset poles | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 778L (217s North Red Deer - 87s Gaetz),217s 778E (217s North Red Deer) | 2013-10-28 10:00 | 2013-10-29 17:00 | N | Y | 138kV breaker maintenance, dashpot oil top up | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 80L (152s Didsbury - 80L194A) | 2013-10-28 10:00 | 2013-11-03 17:00 | N | N | replacing structures | Line
ATCO | 844s 701T (844s AEC Mill) | 2013-10-28 11:00 | 2013-11-01 11:00 | N | N | replace gaskets at rads upper and lower | Transformer |  |  | For Information Only
ATCO | 718s 702T (718s Parsons Creek) | 2013-10-28 12:00 | 2013-11-04 15:00 | N | N | replace the foundation | Transformer |  |  | For Information Only
AESO-SC | 473c102 (Mobile Cap) | 2013-10-28 13:00 | 2013-10-29 17:00 | N | N | P.O.W. controller troubleshooting | Shunts |  |  | For Information Only
ALTALINK | 851L (525s Carseland - 253s Blackie) | 2013-10-29 07:00 | 2013-11-17 18:00 | N | N | rebuild line from structure 97 to structure 115 | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2013-10-29 08:00 | 2013-10-31 15:30 | N | N | inspect and install conductor vibration dampers | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 657s SU2404 (657s Summerside) | 2013-10-29 08:00 | 2013-10-29 16:00 | N | N | SF6 gas filling | Circuit Breaker |  |  | 240 kV
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2013-10-29 08:00 | 2013-10-29 19:00 | N | N | hydrovac at ENMAX 5 | Line
ALTALINK | 276s T2 (276s Union Carbide Prentiss),774L (276s Prentiss - 332s Ellis),276s 16 (276s Un Carb Prentiss),276s Union Carbide Prentiss 138 kV North Bus | 2013-10-29 08:00 | 2013-10-31 16:30 | N | Y | breaker replacement | Bus, Circuit Breaker, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2013-10-29 08:00 | 2013-10-30 19:00 | N | N | relay maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2013-10-29 08:00 | 2013-10-30 19:00 | N | N | replace SW84 | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1036L (370s North Lethbridge - 356s Milo) | 2013-10-29 08:00 | 2013-11-06 11:00 | N | Y | install footings to allow construction of 554s tap point | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ATCO | 801s 909 (801s Anderson) | 2013-10-29 08:30 | 2013-11-01 16:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 100L (895s Suffield - 498s Tilley),498s 100X (498s Tilley) | 2013-10-29 12:00 | 2013-10-29 16:00 | N | N | trip testing from new T1 protections | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s T1 (58s Edson) | 2013-10-30 07:00 | 2013-10-31 17:00 | N | N | bushing replacement | Transformer
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2013-10-30 07:30 | 2013-11-13 17:00 | N | Y | WATL - reconfigure line at crossing point | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2013-10-30 08:00 | 2013-10-30 19:00 | N | N | hydrovac at 5 Sub | Line
ALTALINK | 747L (99s North St. Albert - 747DL4) | 2013-10-30 08:00 | 2013-10-30 14:00 | N | N | SCADA control interposing relays move | Line
ALTALINK | 498s C1 (498s Tilley),498s T1 (498s Tilley),666L (498s Tilley - 28s West Brooks),498s 138 kV bus 1 (498s Tilley) | 2013-10-30 08:00 | 2013-10-30 17:00 | N | Y | functional test from T1 - energize T1 | Bus, Line, Shunts, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225L (225s Magrath - 225AL tap),225s 225E (225s Magrath) | 2013-10-30 09:00 | 2013-10-30 17:00 | N | N | 69kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Creates Radial Feeds
ATCO | 741s Fox Creek RTU/SCADA | 2013-10-30 09:00 | 2013-10-30 17:00 | N | N | 702T replacement - RTU/HMI updates | Terminal Equipment |  |  | Affects Visibility
ENMAX | 162.2TR (ENMAX 162 Beddington),39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington),162s 138-RB84 (162s Beddington) | 2013-10-30 11:00 | 2013-10-30 14:00 | N | N | sub washing | Circuit Breaker, Transformer, Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 310p 552 (310p Sundance) | 2013-10-30 13:00 | 2013-10-30 14:30 | N | N | force current flow through 310p652 to test CTs | Circuit Breaker |  |  | 240 kV
DAISHOWA | 147s Daishowa Plant RTU/SCADA | 2013-10-30 23:00 | 2013-10-31 06:00 | N | N | Telus equipment updgrade | Terminal Equipment |  |  | Affects Visibility
EPCOR | 330P 12TC1 (330p Genesee),330P Genesee 500 kV Bus 1 | 2013-10-31 07:30 | 2013-10-31 17:00 | N | Y | commissioning of 1201 breaker | Transformer, Bus |  |  | Contingency Requires Mitigation, 500 kV
ATCO | 7L104 (856s Kinosis - 989s Quigley) | 2013-10-31 08:00 | 2013-10-31 15:00 | N | N | resag conductor over pipe line | Line |  |  | Pre-Condition
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2013-10-31 08:00 | 2013-10-31 14:00 | N | N | SCADA control interposing relays move from D20 to SEL2440 and actual equipment control modules | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2013-10-31 08:00 | 2013-11-08 19:00 | N | N | replace switches & bushings & doble 39.2TR | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s T5 (37s North Calder) | 2013-10-31 08:00 | 2013-11-06 15:00 | N | N | replace T5 protections | Transformer
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2013-10-31 08:00 | 2013-10-31 12:00 | N | N | hydrovac at 5 Sub | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 72RG1 (Rossdale - Garneau),Rossdale 72 kV Bus 4 | 2013-10-31 08:00 | 2013-10-31 17:00 | N | N | provide proper limits of approach for RV728 Breaker installation | Line, Bus |  |  | For Information Only
ALTALINK | 370s 66 (370s North Lethbridge) | 2013-10-31 08:00 | 2013-10-31 17:00 | N | N | dashpot in mech leaking | Circuit Breaker |  |  | For Information Only
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 2 - 2.83L tap),2.83L (ENMAX 13 - 2.83L tap) | 2013-10-31 12:00 | 2013-10-31 19:00 | N | N | hydrovac at 5 Sub | Line |  |  | Pre-Condition, Overload
ATCO | 7L583 (970s Bourque - 715s Leming Lake) | 2013-11-01 08:00 | 2013-11-01 14:00 | N | N | install standoffs on deadend pole | Line
ALTALINK | 701L (395s North Holden - 223s Strome) | 2013-11-01 08:00 | 2013-11-01 10:00 | N | N | connect mobile sub | Line |  |  | Overload
ALTALINK | 1054L (13s Deerland - 12s Heartland) | 2013-11-01 08:00 | 2013-11-08 16:00 | N | N | In service date: Nov. 8, 2013 | Line |  |  | 240 kV
AESO-SC | Winter Raings Implementation | 2013-11-01 08:00 | 2013-11-01 10:00 | N | N | Switch to winter ratings | SCInternal
ALTALINK, ATCO | 395s T1 (395s North Holden),174L (197s Bardo - 395s North Holden),7L77 (395s North Holden - 709s Vegreville),701L (395s North Holden - 223s Strome),395s North Holden 138 kV Bus | 2013-11-01 12:00 | 2013-11-04 16:00 | N | N | replace 395s1, replace 138kV PTs, replace 138kV insulators | Bus, Transformer, Line |  |  | Pre-Condition, Over/Under Voltage
ENMAX | Enmax 8 B138-3A0 (ENMAX 8) | 2013-11-02 08:00 | 2013-11-22 16:00 | N | N | breaker maintenance | Circuit Breaker
ALTALINK | 603L (243s Soderglen Wind Farm - 59s Peigan) | 2013-11-02 08:00 | 2013-11-02 11:00 | N | Y | urgent repairs: jumper replacement at STR 97 | Line |  |  | Restricts Generation
ATCO | 7L97 (820s Hangingstone - 933s Tower Road) | 2013-11-02 09:00 | 2013-11-02 19:00 | N | N | repair 7L97D2 & bird proof 2014s Halfway | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320P Keephills | 2013-11-02 09:00 | 2013-11-02 17:00 | N | N | damaged 500 kV control cables | Station |  |  | For Information Only
ATCO | 2014s 701T (2014s Halfway),2014s 702T (2014s Halfway) | 2013-11-02 09:00 | 2013-11-02 19:00 | N | N | bird proofing | Transformer
ALTALINK | 1201L (102s Langdon - BCH) | 2013-11-03 08:00 | 2013-11-03 18:00 | Y | Y | trouble corrective: tower steel repairs at STR;436, 445, and defective insulators at STR 213 | Line |  |  | Pre-Condition, Limits ATC, 500 kV
EPCOR | 805s C1 (805s Jasper),805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2013-11-03 08:00 | 2013-11-09 18:00 | N | Y | protection upgrade | Transformer, Shunts, Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2013-11-04 07:00 | 2013-11-07 17:00 | N | Y | insulators replacement | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ALTALINK | 17s Benalto 240 kV North Bus 1,17S T3 (17s Benalto) | 2013-11-04 07:00 | 2013-11-04 17:00 | N | Y | insulators replacement | Bus, Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 132s Ware Junction 240kV South Bus | 2013-11-04 08:00 | 2013-11-10 19:00 | N | Y | replace switch 132s11 & add switch 132s34. String 1053L into 132s | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 80L (55s Olds - 152s Didsbury) | 2013-11-04 08:00 | 2013-11-07 17:00 | N | Y | replacing structures | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 6L79 (711s Willingdon - 707s St.Paul) | 2013-11-04 08:00 | 2014-03-10 23:59 | N | N | open ended at 707s during winter season | Line |  |  | Pre-Condition, For Information Only
ALTALINK | 324s 1752 (324s Cassils),324s 1852 (324s Cassils),324s 2052 (324s Cassils),324s 2152 (324s Cassils) | 2013-11-04 08:30 | 2013-11-07 18:00 | N | N | end  end testing of 1034L & 1035L | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2013-11-04 08:30 | 2013-11-08 16:00 | N | N | inspection and install conductor damper between 7L45D2and 813S Little Smokey | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s C1 (83s Taber),83s C2 (83s Taber),83s 61 (83s Taber),83s 67 (83s Taber) | 2013-11-04 10:00 | 2013-11-15 16:00 | N | Y | replace 83s61 & protections | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 923L (324s Cassils - 356s Milo) | 2013-11-04 10:00 | 2014-01-22 18:00 | N | Y | re-conductor STRs 87 - 104. | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 701L (395s North Holden - 223s Strome) | 2013-11-04 16:01 | 2013-11-13 14:00 | N | N | replace 395s12, install bird coverup, replace LAs, replace 25kV bushings on T1, replace 395s8 PTs | Line |  |  | Overload, Over/Under Voltage
ALTALINK | 122S Alberta Newsprint,907L (77s Sagitawah - 122s Alberta Newsprint),77s 51 (77s Sagitawah),77s 54 (77s Sagitawah) | 2013-11-05 07:00 | 2013-11-07 21:00 | N | Y | protection upgrades | Station, Circuit Breaker, Line |  |  | 240 kV, Firm Load Loss
ALTALINK | 285s T2 (285s East Camrose) | 2013-11-05 08:00 | 2013-11-05 17:30 | N | N | winding resistance test, gas detection test, hot spots | Transformer
ALTALINK | 324S Cassils | 2013-11-05 08:00 | 2013-11-07 18:00 | N | N | relay | Station |  |  | For Information Only
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2013-11-05 08:00 | 2013-11-05 15:00 | N | N | replace structure / maintenance | Line |  |  | Pre-Condition
ALTALINK | 13s 1252 (13s Deerland) | 2013-11-05 08:00 | 2013-11-08 18:00 | N | Y | the trip testing from the new protections | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor) | 2013-11-05 08:00 | 2013-11-05 16:00 | N | N | reconfigure 746L to reflect new P&C setting changes | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2013-11-05 08:00 | 2013-11-05 16:00 | N | N | crane work install 8 kV gear | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2013-11-05 08:00 | 2013-11-08 18:00 | N | N | erect new steel monopoles | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 741s 701T (741s Fox Creek) | 2013-11-05 13:00 | 2013-11-07 16:00 | N | N | GOI for remote tap changer installation | Transformer
ALTALINK | 747L (37s North Calder - 711L tap),37s 747W (37s North Calder),37s41 (37s North Calder) | 2013-11-06 05:00 | 2013-11-06 06:00 | N | N | perform test trip for new T5 protection | Circuit Breaker, Line, Terminal Equipment |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
DAISHOWA | 147s Daishowa Plant RTU/SCADA | 2013-11-06 06:00 | 2013-11-06 06:30 | N | N | DMI network upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 898L (37s North Calder - 92s Viscount),37s 898 (37s North Calder),37s41 (37s North Calder) | 2013-11-06 06:01 | 2013-11-06 07:00 | N | N | perform breaker test trip for new T5 protection | Circuit Breaker, Line, Terminal Equipment |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 726L (37s North Calder - 71s Lamoureux),37s 726E (37s North Calder),37s 5 (37s North Calder) | 2013-11-06 07:01 | 2013-11-06 08:00 | N | N | perform test trip for new T5 protection | Circuit Breaker, Line, Switch |  |  | Over/Under Voltage
ALTALINK | 500S Flatbush | 2013-11-06 08:00 | 2013-11-06 15:00 | N | N | new SCADA system | Station |  |  | For Information Only
ALTALINK | 38s T3 (38s East Edmonton),761L (71s Lamoureux - 38s East Edmonton),865L (216s Knightsbridge - 38s East Edmonton) | 2013-11-06 08:00 | 2013-11-07 17:00 | N | N | replace 38s34 and work on Bus 2 | Line, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s T6 (37s North Calder),37s 4 (37s North Calder),37s 3 (37s North Calder) | 2013-11-06 08:01 | 2013-11-06 09:00 | N | N | Perform test trip for new T5 protection. | Circuit Breaker, Transformer, Switch |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 827s SVC (827s Cranberry Lake) | 2013-11-06 11:00 | 2013-11-06 14:00 | N | Y | replace a blown thyristor | Shunts |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2013-11-06 23:00 | 2013-11-07 04:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
DAISHOWA | 147s Daishowa Plant RTU/SCADA | 2013-11-07 02:00 | 2013-11-07 06:00 | N | N | Telus network outage | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 62s12 (62s Brazeau) | 2013-11-07 04:00 | 2013-11-07 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 37s T3 (37s North Calder),37s12 (37s North Calder) | 2013-11-07 08:00 | 2013-11-07 10:00 | N | N | perform breaker test trip for new T5 protection | Transformer, Switch
ALTALINK | 575s T2 (575s Sundre) | 2013-11-07 09:00 | 2013-11-08 15:00 | N | N | bird proof east bus 25 kV feeders | Transformer
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2013-11-07 11:00 | 2013-11-07 12:00 | N | Y | energization plan to restore NTL 2CB1 to service | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
Saskpower | Sask Power SW905 | 2013-11-07 12:00 | 2013-11-07 14:00 | N | Y | repair a gas leak | Circuit Breaker |  |  | Limits ATC
ATCO | 766s Nevis RTU/SCADA | 2013-11-07 12:30 | 2013-11-07 17:00 | N | N | terminate wires for new security card readers | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 1045L (310p Sundance - 805s Jasper) | 2013-11-08 13:10 | 2013-11-08 14:50 | N | Y | test energize 310p1752 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 310p 1852 (310p Sundance) | 2013-11-08 14:10 | 2013-11-08 14:40 | N | Y | trip testing from new 310p1752 breaker fail relay | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 1652 (310p Sundance) | 2013-11-08 15:00 | 2013-11-29 18:00 | N | Y | beaker replacement | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 575s T1 (575s Sundre) | 2013-11-08 15:00 | 2013-11-08 17:00 | N | N | re-issue trip settings and trip test feeders | Transformer
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2013-11-09 07:00 | 2013-11-10 19:00 | N | N | repair and washing | Line |  |  | Pre-Condition
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2013-11-09 08:00 | 2013-11-09 19:00 | N | N | Sheath Testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 708L (233s Beamer - 708L88N) | 2013-11-11 08:00 | 2013-11-22 15:00 | N | Y | 233s708X breaker replacement | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2013-11-11 08:00 | 2013-11-11 16:00 | N | N | sheath testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 23.80L (74s Janet - ENMAX 23) | 2013-11-11 08:00 | 2013-11-11 11:00 | N | N | top up gas | Line |  |  | Pre-Condition, Overload
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2013-11-11 11:00 | 2013-11-11 16:00 | N | N | re-adjust nitrogen pressure | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 338s Cherhill 240kV Bus 2 | 2013-11-12 07:00 | 2013-11-26 10:00 | N | Y | install, test & commission breaker 338s552, install, test & commission VT8 (338s35), install test a | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 80L (55s Olds - 152s Didsbury) | 2013-11-12 08:00 | 2013-11-21 17:00 | N | N | replacing structures | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 657s SU2404 (657s Summerside) | 2013-11-12 08:00 | 2013-11-12 16:00 | N | N | SU2404:Repair:Top up SF6 gas | Circuit Breaker |  |  | 240 kV
Saskpower | SaskPower C1S | 2013-11-12 08:00 | 2013-11-14 17:00 | N | N | maintenance | Line |  |  | For Information Only
ALTALINK | 920L (71s Lamoureux - 557s Castle Downs) | 2013-11-12 08:00 | 2013-11-13 12:00 | N | Y | 71s1652 protection upgrade, trip tests to EPCOR & 71s1552 | Line |  |  | 240 kV, Overload
ALTALINK | 672L (235s Entwistle - 131s Moon Lake) | 2013-11-12 10:30 | 2013-11-13 17:00 | N | N | disonnecting Mobile (474s) | Line |  |  | Firm Load Loss, Creates Radial Feeds
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2013-11-13 08:00 | 2013-11-13 12:00 | N | N | take measurements for new switch | Line |  |  | Firm Load Loss, Creates Radial Feeds
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2013-11-13 08:00 | 2013-11-13 12:00 | N | N | Lethbridge line outage | Line |  |  | For Information Only
ALTALINK | 310p 2052 (310p Sundance) | 2013-11-13 08:00 | 2013-11-14 18:00 | N | Y | warranty checks by manufacturer | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 185L (415s Drywood - 379s Shell Canada Waterton),415s 352 (415s Drywood) | 2013-11-13 08:00 | 2013-11-14 17:00 | N | N | 185L protections replacement | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),72CK13 (987s Clover Bar - Kennedale),987S Clover Bar 72 kV Bus 4 | 2013-11-13 08:00 | 2013-11-13 16:00 | N | N | replace expansion joints | Line, Bus |  |  | Restricts Generation, For Information Only
DAISHOWA | 147s Daishowa Plant RTU/SCADA | 2013-11-13 08:00 | 2013-11-13 12:00 | N | N | Telus network outage | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 964s T3 (964s Pigeon Lake) | 2013-11-13 08:00 | 2013-11-13 17:00 | N | N | 25 kV bus outage to install B phase metering PT | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2013-11-13 08:00 | 2013-11-14 18:00 | N | N | 7L65 T Maintenance Inspection | Line |  |  | Over/Under Voltage
AESO-SC | BUCC activation | 2013-11-13 09:00 | 2013-11-13 16:00 | N | N | ENMAX BUCC bi-annual evacuation drill | SCInternal |  |  | For Information Only
ALTALINK | 1045L (310p Sundance - 805s Jasper) | 2013-11-13 13:10 | 2013-11-13 14:50 | N | Y | trip test on 310p1752 | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 310p 1852 (310p Sundance) | 2013-11-13 14:10 | 2013-11-13 14:40 | N | Y | trip testing from new 310p1752 breaker fail relay | Circuit Breaker |  |  | 240 kV
ALTALINK | 268s T3 (268s Whitecourt) | 2013-11-13 23:59 | 2013-11-14 06:00 | N | N | repair on 268s213 and replace 268s80 | Transformer |  |  | For Information Only
ALTALINK | 89s 1652 (89s Ellerslie) | 2013-11-14 08:00 | 2013-11-14 12:30 | N | Y | troubleshoot relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 766s Nevis RTU/SCADA | 2013-11-14 09:00 | 2013-11-21 17:00 | N | N | commissioning RTU/Physical Security control cabinet | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 180s Cope Creek RTU/SCADA | 2013-11-14 09:00 | 2013-11-14 11:00 | N | N | replace components in the TX path | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 89s 252 (89s Ellerslie) | 2013-11-14 12:30 | 2013-11-14 17:00 | N | Y | replace power supply | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L59 (786s High Level - 789s Keg River) | 2013-11-15 08:00 | 2013-12-02 14:00 | N | N | replace crossarms | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau T1 (Garneau) | 2013-11-15 08:00 | 2013-11-16 18:00 | N | N | RTU commissioning | Transformer
ENMAX | 21.4TR (ENMAX 21) | 2013-11-15 08:00 | 2013-11-15 12:00 | N | N | bushing DGA sample | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 2.81L (ENMAX 2 - ENMAX 9),833L (ENMAX 2 - ENMAX 12) | 2013-11-16 08:00 | 2013-11-17 18:00 | N | N | ECTP: transport new T2 to 5s new transformer pad | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2013-11-16 08:00 | 2013-11-17 18:00 | N | N | Altalink Request - move T2 to 5S transformer pad | Line
ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2013-11-16 08:00 | 2013-11-17 18:00 | N | N | Altalink request - Move T2 to 5S transformer pad | Line
ENMAX | Enmax 1 B138-7A0 (ENMAX 1) | 2013-11-16 08:00 | 2013-12-06 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2013-11-17 07:00 | 2013-11-18 21:00 | N | N | ENMAX sub washing & maintenance | Transformer
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 240 kV North Bus | 2013-11-17 07:00 | 2013-11-17 21:00 | N | Y | sub washing & maintenance | Bus, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 757s 702 (757s Battle River) | 2013-11-17 08:00 | 2013-12-20 16:00 | N | N | replacement | Circuit Breaker
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2013-11-18 07:00 | 2013-11-18 17:00 | N | N | replace insulators | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau T1 (Garneau) | 2013-11-18 08:00 | 2013-11-19 18:00 | N | N | RTU commission | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2013-11-18 08:00 | 2013-11-21 18:00 | N | N | maintenance Inspection | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 753L (65s High River - 253s Blackie) | 2013-11-18 08:00 | 2013-11-21 18:00 | N | N | replace insulators, structures and arms | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 199L (268s Whitecourt - 199L187B) | 2013-11-19 07:00 | 2013-11-19 18:00 | N | N | install new radio tower | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | Suncor (Millennium) Islanding RAS (IRAS) | 2013-11-19 08:00 | 2013-12-10 20:59 | N | N | RAS upgrade | RAS |  |  | Impacts RAS
ALTALINK | 698s 552 (698s Jackfish) | 2013-11-19 08:00 | 2013-11-20 17:00 | N | Y | replace B phase CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 330P SST1 (330P Genesee) | 2013-11-19 08:00 | 2013-11-20 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 650s SVC (650s Hansman Lake),650s 252 (650s Hansman Lake),650s 352 (650s Hansman Lake) | 2013-11-19 13:00 | 2013-11-20 14:00 | N | Y | work on the 600V station service - need SVC offline | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2013-11-20 02:00 | 2013-11-20 04:00 | N | N | high load move | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (256s Harmattan - 719L135X) | 2013-11-20 07:00 | 2013-11-20 17:00 | N | N | trouble corrective | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 284s T1 (284s Nose Creek) | 2013-11-20 08:00 | 2013-11-20 15:00 | N | N | new SCADA system | Transformer
ALTALINK | 798L (364s Whitecourt Industrial - 77s Sagitawah) | 2013-11-20 08:00 | 2013-12-12 18:00 | N | N | line relocation at 364s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RG1 (Rossdale - Garneau) | 2013-11-20 08:00 | 2013-11-20 18:00 | N | N | 72RG1:RTU commission | Line
ATCO | 801s 910 (801s Anderson) | 2013-11-20 08:30 | 2013-11-20 17:00 | N | Y | top up the poles with N2 so that they are in the safe operating levels | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 233s T2 (233s Beamer),735L (171s Redwater - 233s Beamer),233s Beamer 138 kV Bus 2 | 2013-11-20 09:00 | 2013-11-20 14:00 | N | N | 233s 708L Bus side riser replacement | Line, Bus, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2013-11-21 07:00 | 2013-11-23 18:00 | N | Y | protection settings changes and end to end testing | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 14s T1 (14s Devon) | 2013-11-21 08:00 | 2013-11-21 12:00 | N | N | update ground overcurrent protection setting | Transformer |  |  | Firm Load Loss
EPCOR | 72RG7 (Rossdale - Garneau) | 2013-11-21 08:00 | 2013-11-21 18:00 | N | N | RTU commission | Line |  |  | For Information Only
ATCO | 732s 503R (732s Mitsue) | 2013-11-21 08:00 | 2014-07-27 20:50 | N | Y | Forced Outage | Shunts |  |  | For Information Only
ALTALINK | 698s 252 (698s Jackfish) | 2013-11-21 08:00 | 2013-11-21 11:00 | N | Y | deficiency clean-up | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 801s 911 (801s Anderson) | 2013-11-21 08:30 | 2013-11-21 17:00 | N | Y | top up gas for safe operating zone. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 5s C3 (5s East Calgary),5s C2 (5s East Calgary) | 2013-11-21 11:30 | 2013-11-21 17:00 | N | Y | 138kV C/S maintenance | Shunts |  |  | Limits ATC
EPCOR | 987S Clover Bar 72 kV Bus 4 | 2013-11-21 23:30 | 2013-11-22 07:00 | N | N | replace 72 kV bus expansion joints | Bus
ALTALINK | 118s C1 (118s Canmore) | 2013-11-22 08:00 | 2013-11-23 17:00 | N | Y | 138kV CT replacement | Shunts |  |  | For Information Only
AESO-SC | 332s Ellis 27.6 MVAr Cap Bank | 2013-11-22 08:00 | 2013-11-29 17:00 | N | N | In service date: November 29, 2013 | Shunts
EPCOR | 72MG16 (Meadowlark - Garneau) | 2013-11-22 08:00 | 2013-11-22 18:00 | N | N | RTU commission | Line
ALTALINK | 38s 75 (38s East Edmonton) | 2013-11-22 08:01 | 2013-11-22 09:00 | N | N | test trip of 38s75 for new 38sT3 protections | Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 370s T1 (370s North Lethbridge) | 2013-11-22 09:00 | 2013-11-22 17:30 | N | N | swap primary/standby transformers | Transformer
ALTALINK | 734L (241s Lethbridge Uplands - 370s North Lethbridge),370s 734X (370s North Lethbridge) | 2013-11-22 09:00 | 2013-11-22 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker, Line
ALTALINK | 761L (38s East Edmonton - 189s Celanese),38s 897 (38s East Edmonton) | 2013-11-22 09:01 | 2013-11-22 10:00 | N | N | test trip of 38s761N for 38sT3 protections | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 865L (216s Knightsbridge - 38s East Edmonton),38s48 (38s East Edmonton) | 2013-11-22 10:01 | 2013-11-22 11:00 | N | N | test trip of 38s865N for 38sT3 protections | Switch, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2013-11-22 10:30 | 2013-11-22 16:30 | N | N | repair CT | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s 62 (38s East Edmonton),38s34 (38s East Edmonton) | 2013-11-22 11:01 | 2013-12-11 18:00 | N | N | test trip of 38s62 for 38sT3 protections | Circuit Breaker, Switch |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | NamaoT2 (Namao) | 2013-11-23 07:30 | 2013-12-20 16:00 | N | N | new switchgear installation | Transformer
ATCO | 9L32 (849s Joslyn Creek - 941s Bitumount),9L69 (934s Black Fly - 957s McClelland),957s McClelland,9L32 (941s Bitumount -957s McClelland) | 2013-11-23 08:00 | 2013-11-29 16:00 | N | N | In service date: Nov. 29, 2013 | Line, Transformer |  |  | 240 kV
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2013-11-23 08:00 | 2013-11-29 16:00 | N | N | In service date: Nov. 26, 2013. Refer to the Op Plan binder for the commissioning plan. | Line |  |  | 240 kV
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 7L50D2),526s 252 (526s Buffalo Creek) | 2013-11-23 08:00 | 2013-11-23 14:00 | N | N | maintenance | Line, Circuit Breaker
ALTALINK | 1035L (244s Bowmanton - 324s Cassils) | 2013-11-23 08:00 | 2013-11-29 16:00 | N | N | In service date: Nov. 26, 2013. Refer to the Op Plan binder for the commissioning plan. | Line |  |  | 240 kV
ALTALINK, ENMAX | 2.81L (ENMAX 2 - ENMAX 9),833L (ENMAX 2 - ENMAX 12) | 2013-11-23 08:00 | 2013-11-24 18:00 | N | N | ECTP: transport new T2 to 5s new transformer pad | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2013-11-23 08:00 | 2013-11-23 12:00 | N | N | sheath and oil testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 294s T1 (294s Brazeau Outlet Works),801L (62s Brazeau - 294s Brazeau Outlet Works),801L (294s Brazeau Outlet Works - 801L302 Tap),294s Brazeau Outletworks 138 kV Bus | 2013-11-23 08:00 | 2013-11-23 19:00 | N | Y | replace 138kV bus insulators & various maintenance | Transformer, Line, Bus |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 428s T2 (428s Namaka) | 2013-11-23 08:30 | 2013-11-23 16:00 | N | N | tapchanger fitting leak repair | Transformer
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2013-11-23 09:00 | 2013-11-23 11:00 | N | N | moving 735L protection circuits | Line
ALTALINK | 1054L (13s Deerland - 12s Heartland) | 2013-11-24 08:00 | 2013-11-28 19:00 | N | Y | Complete OHSW replacement with OPGW - Heartland | Line |  |  | 240 kV, Overload, Over/Under Voltage
EPCOR | 557s T1 (557s Castle Downs) | 2013-11-25 07:30 | 2013-11-29 18:00 | N | Y | tap changer maintenance and bushing monitors | Transformer |  |  | 240 kV
ALTALINK | 38s T3 (38s East Edmonton) | 2013-11-25 08:00 | 2013-11-30 17:00 | N | N | protection replacement on T3, 38s87 & 38s45 | Transformer |  |  | For Information Only
Syncrude | Aurora T1 | 2013-11-25 08:00 | 2013-11-26 16:00 | N | N | relay setting for tap changer | Transformer |  |  | Creates Radial Feeds
EPCOR | 805s C1 (805s Jasper),805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2013-11-25 08:00 | 2013-11-27 18:00 | N | Y | protection upgrade | Transformer, Shunts, Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 1.5TR (ENMAX 1) | 2013-11-25 08:00 | 2013-11-25 16:00 | N | N | PRD measurements | Transformer
ALTALINK | 807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap) | 2013-11-25 08:00 | 2013-12-06 15:00 | N | N | 233s807X breaker replacement | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37) | 2013-11-25 08:00 | 2013-11-29 19:00 | N | N | MD repalcement,MD replacement | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 632L (325s Leduc - 538s Buford) | 2013-11-25 09:00 | 2013-11-27 10:00 | N | N | connect 472s/MR1 mobile to 632L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 332s T2 (332s Ellis),784L (535s Joffre - 332s Ellis),332s Ellis 138 kV North Bus | 2013-11-26 07:00 | 2013-11-28 17:00 | N | Y | connect new cap bank | Bus, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 330P SST1 (330P Genesee) | 2013-11-26 07:30 | 2013-11-27 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 1044L (805s Jasper - 816s Petrolia) | 2013-11-26 07:30 | 2013-11-27 16:00 | N | Y | aerial maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 803s T1 (803s Lambton) | 2013-11-26 08:00 | 2013-11-26 16:00 | N | N | inspect the back of the 15KV cell for SWGR upgrade | Transformer |  |  | For Information Only
ALTALINK | 108s 152 (108s Amelia) | 2013-11-26 08:00 | 2013-11-26 13:30 | N | Y | add sync check to breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 805s J2403 (805s Jasper) | 2013-11-26 08:00 | 2013-11-26 13:00 | N | Y | CTs replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L92 (777s Vilna - 709s Vegreville) | 2013-11-26 08:00 | 2013-12-01 17:00 | N | N | to complete the inline switches and install the tap from the line | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie) | 2013-11-26 08:00 | 2013-12-05 18:00 | N | N | replace insulators, structures and arms | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 930s SVC (930s Arcenciel) | 2013-11-26 08:30 | 2013-11-26 16:30 | N | N | maintenance | Shunts |  |  | For Information Only
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2013-11-26 09:30 | 2013-11-26 15:00 | N | N | emergency replacement of 603A | Line |  |  | Firm Load Loss, Creates Radial Feeds
STROBE | 240s T3 (240s McBride Lake) | 2013-11-26 10:00 | 2013-11-26 12:00 | N | N | investigate transformer alarm | Transformer |  |  | For Information Only
ALTALINK | 317s T2 (317s Baseline) | 2013-11-27 07:00 | 2013-11-27 17:00 | N | N | customer request | Transformer
EPCOR | 803s L2403 (803s Lambton) | 2013-11-27 07:30 | 2013-11-27 16:00 | N | N | inspect and repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2013-11-27 08:00 | 2013-11-27 11:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 786s SVC (786s High Level) | 2013-11-27 08:30 | 2013-11-27 16:30 | N | N | blower maintenance & repair, PLC program changes | Shunts |  |  | For Information Only
ALTALINK | 632L (325s Leduc - 538s Buford),837L (964s Pigeon Lake - 538s Burford) | 2013-11-27 10:00 | 2013-12-09 10:00 | N | N | replace control building, upgrade P&C and SCADA schemes | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 338s T1 (338s Cherhill) | 2013-11-28 06:00 | 2013-11-29 18:00 | N | Y | close open point C . (25kv Bus Tie) | Transformer |  |  | 240 kV
ALTALINK | 150L (42s Sarcee - 150L47) | 2013-11-28 07:00 | 2013-12-01 13:00 | N | N | high load move under 150L | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),72CK13 (987s Clover Bar - Kennedale),987S Clover Bar 72 kV Bus 4 | 2013-11-28 08:00 | 2013-11-29 07:00 | N | N | replace expansion joints (Heating) | Bus, Line
ALTALINK | 162L (415s Drywood - 229s Glenwood) | 2013-11-28 08:00 | 2013-12-18 18:00 | N | N | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | Fort McMurray Area Operation | 2013-11-28 08:00 | 2013-12-13 16:00 | N | N | McClelland project | SCInternal |  |  | For Information Only
ATCO | 766s Nevis RTU/SCADA | 2013-11-28 08:00 | 2013-11-29 16:00 | N | N | download and update RTU programs | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 14s T3 (14s Devon) | 2013-11-28 08:00 | 2013-11-28 12:00 | N | N | update ground overcurrent protection setting | Transformer
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2013-11-28 08:00 | 2013-11-29 16:00 | N | N | repair Hot Switch KDS9 at Kennedale | Line
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia),909L (320p Keephills - 665s Dome) | 2013-11-28 10:00 | 2013-12-01 17:00 | N | Y | installing a monopole mid span | Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 252 (77s Sagitawah),77s30 (77s Sagitawah) | 2013-11-28 10:00 | 2013-11-28 11:45 | N | N | function check the breaker from 77s352 breaker protection | Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ALTALINK | 526L (515s Fed Pipe Judy Creek - 526L418) | 2013-11-28 11:00 | 2013-12-10 07:00 | N | N | to allow new IPP at 659s Pegasus Lake to come online | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 26 (77s Sagitawah),77s27 (77s Sagitawah) | 2013-11-28 13:00 | 2013-11-28 14:45 | N | Y | function check the breaker from 77s352 breaker protection | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 77s 51 (77s Sagitawah),77s52 (77s Sagitawah) | 2013-11-28 15:00 | 2013-11-28 17:00 | N | Y | function check the breaker from 77s352 breaker protection | Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 731L (420s Broadmoor - 7746DL8) | 2013-11-29 08:00 | 2013-11-29 17:00 | N | N | re-string/splice understrung fibre optic cable after line modifications for Heartland | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2152 (74s Janet) | 2013-11-29 08:30 | 2013-11-29 17:30 | N | Y | Slow breaker operation time | Circuit Breaker |  |  | 240 kV
IMPERIALOIL | 9900S Kearl | 2013-11-30 08:00 | 2013-12-06 16:00 | N | N | In service date: Dec 1, 2013 | Station |  |  | 240 kV
AESO-SC | Mildred Lake 2 x 20 MVAr cap bank | 2013-11-30 08:00 | 2013-12-06 16:00 | N | N | In service date: Dec. 1, 2013 | Shunts |  |  | For Information Only
ATCO | 2060S Engstrom | 2013-11-30 08:00 | 2013-12-02 16:00 | N | N | In service date: Dec. 1, 2013 | Station |  |  | For Information Only
ENMAX | 23.80L (74s Janet - ENMAX 23) | 2013-11-30 08:00 | 2013-11-30 16:00 | N | N | isolate to split trip coils on 23B138-23.80 | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Aurora C1 (20 MVAr cap bank) | 2013-11-30 08:00 | 2013-12-06 16:00 | N | N | In service date: Dec. 1, 2013 | Shunts |  |  | For Information Only
ENMAX | 23.80L (74s Janet - ENMAX 23) | 2013-11-30 08:00 | 2013-11-30 16:00 | N | N | ENMAX trip coils on 23B138-23.80 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 56L (245s Seebe - 20s Ghost) | 2013-11-30 08:00 | 2013-12-01 17:30 | N | N | replacing dead end insulators on multiple structures. | Line
ALTALINK | 253s C1 (253s Blackie),161L (255s Vulcan - 253s Blackie),851L (525s Carseland - 253s Blackie),852L (253s Blackie - 504s Queenstown),253S Blackie 138 kV bus | 2013-11-30 08:00 | 2013-12-01 17:00 | N | Y | bus protection relay change-out,bus protection relay change-out. | Bus, Line, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2013-12-01 08:00 | 2013-12-01 19:00 | N | N | separating trip contacts | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 253s 182 (253s Blackie) | 2013-12-01 09:00 | 2013-12-01 17:30 | N | Y | 138kV C/S maintenance | Circuit Breaker
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2013-12-02 08:00 | 2013-12-05 18:00 | N | N | 7L65 T maintenance inspection | Line |  |  | Overload
ATCO | 9L32 (849s Joslyn Creek - 941s Bitumount) | 2013-12-02 08:00 | 2013-12-09 17:00 | N | Y | install a permanent structure on 9L32 outside of McClelland sub | Line |  |  | 240 kV
EPCOR | 557s T1 (557s Castle Downs) | 2013-12-02 08:00 | 2013-12-03 16:00 | N | Y | tapchanger maintenance | Transformer |  |  | 240 kV
ALTALINK | 89s 1352 (89s Ellerslie),89s 1452 (89s Ellerslie) | 2013-12-02 08:00 | 2013-12-16 17:00 | N | Y | connect temp 240 kV line for 1206L/1212L | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2013-12-02 08:30 | 2013-12-04 17:00 | N | N | inspection and install conductor damper between 7L45D2 and 813s | Line |  |  | Creates Radial Feeds
ATCO | 7L162 (732s Mitsue - 729s Otauwau) | 2013-12-02 10:00 | 2013-12-05 16:00 | N | N | 729s Ottauwau bkr 704 o/s to replace the 21b relay | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 61L (252s Jarrow - 61DL386),252s 61 (252s Jarrow) | 2013-12-03 08:00 | 2013-12-03 17:00 | N | N | tank heater replacement | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 799s T3 (799s Coleman) | 2013-12-03 08:00 | 2013-12-03 10:00 | N | N | perform a noise measurement | Transformer |  |  | For Information Only
ENMAX | 14.2C (ENMAX 14) | 2013-12-03 09:00 | 2013-12-03 10:00 | N | Y | bus diff CT rewire | Shunts |  |  | Limits ATC
ALTALINK | 310p Sundance 240kV Bus B | 2013-12-04 08:00 | 2013-12-04 17:00 | N | Y | replace insulators & trip testing for 310p1652 | Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
EPCOR | 557s T2 (557s Castle Downs) | 2013-12-04 08:00 | 2013-12-06 16:00 | N | N | Tapchanger Maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 310p 2552 (310p Sundance) | 2013-12-04 08:00 | 2013-12-05 17:00 | N | Y | replace leaky CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 840S 502 | 2013-12-04 09:00 | 2013-12-05 16:00 | N | N | replace breaker mech and Vac bottles | Terminal Equipment |  |  | For Information Only
ATCO | 840S McNeill Station | 2013-12-04 09:00 | 2013-12-04 16:00 | N | N | ATCO replace fire sensor valve hall. | Station
ATCO | 840S McNeill Station | 2013-12-04 09:00 | 2013-12-04 16:00 | N | Y | replace fire sensor valve hall | Station |  |  | Limits ATC
ALTALINK | 807L (233s Beamer - 807L tap),233s Beamer 138 kV Bus 1 | 2013-12-04 09:00 | 2013-12-04 14:00 | N | N | 233s 807L bus side riser replacement | Bus, Line |  |  | Pre-Condition, Firm Load Loss
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2013-12-05 08:00 | 2013-12-05 12:00 | N | N | moving high load move under 717L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L45 (845s Big Mountain - 798s Bridge Creek),7L45 (798s Bridge Creek - 813s Little Smoky) | 2013-12-05 08:30 | 2013-12-06 17:00 | N | N | inspection & install conductor damper | Line
ALTALINK | 310p 1752 (310p Sundance) | 2013-12-05 17:00 | 2013-12-05 18:00 | N | Y | trip test from 310p1652 | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 1071L (103s Goose Lake - 312s Fidler) | 2013-12-06 08:00 | 2013-12-13 17:00 | N | N | replace step bolts on towers and fix minor deficiencies | Line |  |  | 240 kV, Creates Radial Feeds
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2013-12-06 08:00 | 2013-12-06 17:00 | N | Y | sheath test | Line |  |  | Overload
EPCOR | Rossdale C1,Rossdale C2,72RG7 (Rossdale - Garneau),72RV4 (Rossdale - 511s Victoria),72RW3 (Rossdale - Woodcroft) | 2013-12-07 08:00 | 2013-12-13 16:00 | N | N | replace BD1W Switch | Line, Shunts |  |  | Pre-Condition
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake),602s 847E (602s Cold Creek) | 2013-12-09 07:30 | 2013-12-12 17:00 | N | N | 847L A&B protection replacement | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2013-12-09 08:00 | 2013-12-15 16:00 | N | N | SW84, 39.3Tr Bushings and MD | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 352 (310p Sundance) | 2013-12-09 08:00 | 2013-12-09 17:00 | N | N | control circuit work | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s T2 (63s Red Deer),929L (63s Red Deer - 74s Janet),63s Red Deer 240kV South Bus | 2013-12-09 09:00 | 2013-12-12 17:00 | N | Y | replace 63s929X | Bus, Line, Transformer |  |  | 240 kV, Pre-Condition, Limits ATC, Contingency Requires Mitigation
ALTALINK | 632L (325s Leduc - 538s Buford) | 2013-12-09 10:01 | 2013-12-11 10:00 | N | N | remove 472s/MR1 mobile to 632L | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 339s T1 (339s Duchess) | 2013-12-09 14:00 | 2013-12-12 17:00 | N | N | add a third metering PT, relocate station service transformer and replace two existing metering | Transformer
EPCOR | 803s T2 (803s Lambton) | 2013-12-10 05:00 | 2013-12-10 12:00 | N | N | Hydrovac work | Transformer |  |  | 240 kV
ATCO | 7L137 (770s Three Hills - 768s Rowley) | 2013-12-10 07:00 | 2013-12-10 19:00 | N | N | install dampeners | Line |  |  | Over/Under Voltage
ATCO | 7L104 (856s Kinosis - 989s Quigley) | 2013-12-10 08:00 | 2013-12-12 17:00 | N | N | Quigley phase 2 final commissioning | Line
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2013-12-10 08:00 | 2013-12-10 18:00 | N | N | 14 sub bus diff upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L80 (857s Kakwaridge - 733s Simonette) | 2013-12-10 08:00 | 2013-12-12 17:00 | N | N | 7L80 mitigation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2013-12-10 08:00 | 2013-12-11 17:00 | N | Y | replace PTs @ 310p, Replace 310p129 with new fuses | Line |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
AESO | 526L (526DL365 - 526AL tap) | 2013-12-10 08:00 | 2013-12-13 17:00 | N | N | switch replacement 526DL365 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2013-12-10 08:00 | 2013-12-10 18:00 | N | N | maintenance inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK, ATCO | 69s T4 (69s North Barrhead),723L (69s North Barrhead - 723L133),7L230 (69s North Barrhead - 7L230 tap) | 2013-12-10 08:00 | 2013-12-15 16:00 | N | Y | replace 38s34 | Line, Transformer |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 964s T3 (964s Pigeon Lake) | 2013-12-10 09:00 | 2013-12-10 15:00 | N | N | emergency outage to replace switch 964s5 | Transformer |  |  | For Information Only
ALTALINK | 38s T3 (38s East Edmonton),761L (38s East Edmonton - 189s Celanese),865L (216s Knightsbridge - 38s East Edmonton),38s34 (38s East Edmonton),38s East Edmonton 138 kV Bus 2 | 2013-12-11 07:00 | 2013-12-13 17:00 | N | N | replace 38s34 | Switch, Transformer, Line, Bus |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 276s T1 (276s Union Carbide Prentiss),759L (87s Gaetz - 276s Prentiss),276s Union Carbide Prentiss 138 kV Center Bus | 2013-12-11 08:00 | 2013-12-12 16:00 | N | N | upgrade 138kV bus differential | Transformer, Bus, Line
ALTALINK | 250p11 (250p Bighorn) | 2013-12-11 08:00 | 2013-12-11 12:00 | N | N | maintenance | Switch |  |  | Restricts Generation
EPCOR | 805s J2404 (805s Jasper) | 2013-12-11 08:00 | 2013-12-11 15:00 | N | N | meter commissioning | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2013-12-11 08:00 | 2013-12-12 18:00 | N | Y | buss diff upgrade | Shunts |  |  | Limits ATC
ATCO | 6L68 (734s Sturgeon - 787s High Prairie) | 2013-12-11 09:00 | 2013-12-11 17:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (28s West Brooks - 158s Vauxhall),83s38 (83s Taber) | 2013-12-11 09:00 | 2013-12-11 10:00 | N | N | test trip of 83s763N for 38s61 breaker fail | Switch, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 610L (336s Fincastle - 83s Taber),83s2 (83s Taber) | 2013-12-11 10:01 | 2013-12-11 11:00 | N | N | test trip of 83s610 for 38s61 breaker fail | Switch, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 172L (83s Taber - 172L944A),83s36 (83s Taber) | 2013-12-11 11:01 | 2013-12-11 12:00 | N | N | test trip of 83s172W for 38s61 breaker fail | Switch, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2013-12-11 12:00 | 2013-12-11 16:00 | N | N | maintenance | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 89s 2052 (89s Ellerslie) | 2013-12-12 08:00 | 2013-12-12 09:00 | N | Y | trip tests | Circuit Breaker |  |  | Overload, Contingency Requires Mitigation, 500 kV
ATCO | 825s 905 (825s Whitefish) | 2013-12-12 08:00 | 2013-12-13 16:00 | N | Y | low gas levels | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 77s T1 (77s Sagitawah),77s Sagitawah 138 kV West Bus | 2013-12-12 08:00 | 2013-12-12 11:00 | N | Y | function check the breaker 77s352 from air breaks 77s64 & 77s11 | Bus, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 924L (102s Langdon - 356s Milo) | 2013-12-12 08:00 | 2013-12-13 16:00 | N | Y | conductor repairs at STR 182, and other trouble corrective work | Line |  |  | 240 kV
ALTALINK | 89s 252 (89s Ellerslie) | 2013-12-12 09:00 | 2013-12-12 10:00 | N | Y | trip test from 89s1352 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 652 (89s Ellerslie) | 2013-12-12 10:00 | 2013-12-12 11:00 | N | Y | trip test from 89s1352 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 952 (89s Ellerslie) | 2013-12-12 11:00 | 2013-12-12 12:00 | N | Y | trip test from 89s1352 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 77s 252 (77s Sagitawah),77s30 (77s Sagitawah) | 2013-12-12 12:00 | 2013-12-12 16:00 | N | N | function check the breaker from 77s352 breaker protection | Circuit Breaker, Switch
ATCO | 6L11 (854s Swan Dive - 742s Freeman Lake) | 2013-12-12 12:00 | 2013-12-12 16:00 | N | N | repair flashed insulators | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome) | 2013-12-13 07:00 | 2013-12-13 17:00 | N | Y | trouble corrective str 111 and 112 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),746L (746L - 746DL8),420s Broadmoor RTU/SCADA | 2013-12-13 08:00 | 2013-12-13 17:00 | N | N | re-string/splice understrung fibre optic cable | Line, Terminal Equipment |  |  | Overload, Affects Visibility, Firm Load Loss, Creates Radial Feeds
ATCO | 7L32 (862s South Bezanson - 813s Little Smoky) | 2013-12-13 08:30 | 2013-12-13 17:00 | N | Y | relocate pole to accommodate road widening | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 223s 39 (223s Strome),701L (395s North Holden - 223s Strome) | 2013-12-13 10:00 | 2013-12-13 17:00 | N | N | low/leaking gas on breaker | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2013-12-13 17:01 | 2013-12-18 08:00 | N | Y | replace step bolts on towers and fix minor deficiencies | Line |  |  | 240 kV, Firm Load Loss
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2013-12-14 02:00 | 2013-12-14 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload
ALTALINK | 1045L (310p Sundance - 805s Jasper) | 2013-12-14 07:00 | 2013-12-14 17:00 | N | Y | trouble corrective structures 117 and 118 | Line |  |  | 240 kV, Pre-Condition, Overload
EPCOR | 803s T2 (803s Lambton) | 2013-12-14 07:30 | 2013-12-15 16:00 | N | Y | install new AC Control secondary external power supply and P&C work | Transformer |  |  | 240 kV, For Information Only
EPCOR | 816s P2404 (816s Petrolia) | 2013-12-14 08:00 | 2013-12-18 17:00 | N | Y | CT teplacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2013-12-14 08:00 | 2013-12-14 12:00 | N | N | commissioning new ion metering on 72LH8 | Line
ALTALINK | 832L (ENMAX 10 - ENMAX 12) | 2013-12-14 08:00 | 2013-12-18 16:00 | N | N | In service date: Dec. 18, 2013 | Line |  |  | For Information Only
ENMAX | 693L (42s Sarcee - ENMAX 10) | 2013-12-14 08:00 | 2013-12-18 16:00 | N | N | In service date: Dec 18, 2013 | Line |  |  | For Information Only
ALTALINK | 747L (99s North St. Albert - 747DL4),99s 747X (99s North St Albert) | 2013-12-16 07:00 | 2013-12-19 17:00 | N | N | replace 99s747X Breaker | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (746s Sherwood Park - 700L TAP),746s 700N (746s Sherwood Park) | 2013-12-16 07:00 | 2013-12-19 17:00 | N | N | CT replacement | Circuit Breaker, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L137 (770s Three Hills - 768s Rowley) | 2013-12-16 07:00 | 2013-12-16 19:00 | N | N | to install dampners | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2013-12-16 08:00 | 2013-12-19 17:00 | N | N | Structure Replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 1201 (330p Genesee) | 2013-12-16 08:00 | 2013-12-18 15:00 | N | Y | replacement of the trip coil | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 892L (895s Suffield - 41s Medicine Hat),895s 892 (895s Suffield) | 2013-12-16 08:00 | 2013-12-16 11:00 | N | Y | CT ratio change and trip test as part of 498s UV protection implementation | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2013-12-16 08:00 | 2013-12-17 19:00 | N | Y | leaking CVT & B protection outage | Line |  |  | 240 kV
ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2013-12-16 08:00 | 2013-12-18 19:00 | N | N | ENMAX repairing leaking CVT | Line |  |  | For Information Only
ATCO | 9L56 (720s Wabasca - 732s Mitsue) | 2013-12-16 08:30 | 2013-12-18 12:00 | N | N | ATCO Change CT Ratios for 9L56 Protection | Line |  |  | For Information Only
ATCO | 764s 602T (764s Heisler) | 2013-12-16 09:00 | 2013-12-16 16:00 | N | N | replace vacuum bottles on 502TD and test | Transformer |  |  | For Information Only
ATCO | 7L20 (810s Dome Cutbank - 740s H.R.Milner) | 2013-12-16 10:00 | 2013-12-19 17:00 | N | N | set poles in line for mitigation | Line |  |  | Restricts Generation, Creates Radial Feeds
ALTALINK | 100L (895s Suffield - 498s Tilley),895s 52 (895s Suffield) | 2013-12-16 11:00 | 2013-12-16 12:00 | N | N | trip test as part of 498s UV protection implementation | Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 813s SVC (813s Little Smoky) | 2013-12-16 13:00 | 2013-12-16 17:00 | N | Y | top up coolant | Shunts |  |  | Pre-Condition, For Information Only
EPCOR | Strathcona S722 (Strathcona) | 2013-12-17 08:00 | 2013-12-17 15:00 | N | N | heater repair | Circuit Breaker |  |  | Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2013-12-17 08:00 | 2013-12-18 18:00 | N | N | 7L65 maintenance inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2013-12-17 08:00 | 2013-12-21 18:00 | N | N | string slack span the first connection from Str#1/832L to Enmax 10 Sub A-Frame (Sub-B) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 575s T1 (575s Sundre) | 2013-12-17 08:00 | 2013-12-18 17:00 | N | N | oil leak repair | Transformer
ALTALINK | 774L (276s Prentiss - 332s Ellis),276s C1 (276s Prentiss),276s Union Carbide Prentiss 138 kV North Bus | 2013-12-18 07:00 | 2013-12-19 17:00 | N | Y | upgrade 138kV Bus Differential | Bus, Shunts, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2013-12-18 08:00 | 2013-12-18 12:00 | N | N | Wades House Moving high load move under 717L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2013-12-18 08:00 | 2013-12-19 16:00 | N | Y | replace pole heater blanket | Circuit Breaker |  |  | 240 kV
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2013-12-18 08:00 | 2013-12-18 12:00 | N | N | install SWAGE connections | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 14 14B138-11.82 (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2013-12-18 08:00 | 2013-12-18 18:00 | N | N | 14 sub bus diff upgrade | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 1852 (89s Ellerslie) | 2013-12-18 08:00 | 2014-05-02 12:00 | N | Y | Heartland project | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 33s5 (33s Spray) | 2013-12-18 09:00 | 2013-12-18 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2013-12-18 23:00 | 2013-12-19 04:00 | N | Y | outage | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 268s T3 (268s Whitecourt),797L (364s Whitecourt industrial - 268s Whitecourt) | 2013-12-18 23:59 | 2013-12-19 06:00 | N | N | motor Mech Repair on 268s213 and replace 268s80 | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2013-12-19 04:00 | 2013-12-19 07:00 | N | Y | maiintenance | Switch |  |  | 240 kV, Restricts Generation, For Information Only
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2013-12-19 08:30 | 2013-12-19 15:00 | N | N | repair damaged control wiring within RV728 breaker | Line
ALTALINK | 216s Knightsbridge RTU/SCADA | 2013-12-19 09:00 | 2013-12-19 12:00 | N | N | RTU update | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2013-12-20 07:00 | 2013-12-24 18:00 | N | N | modify structures 17 to 22 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX | ENMAX 25 B240-D134 (ENMAX 25) | 2013-12-20 08:00 | 2013-12-21 16:00 | N | Y | replace pole heater blanket | Circuit Breaker |  |  | 240 kV
ALTALINK | 77s T1 (77s Sagitawah),77s Sagitawah 138 kV West Bus | 2013-12-20 08:00 | 2013-12-20 11:00 | N | Y | function check the breaker 77s352 from air breaks 77s64 & 77s11 | Bus, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 557s 2406 (557s Castle Downs) | 2013-12-20 08:30 | 2013-12-20 16:00 | N | N | investigate and remove positive dc ground | Circuit Breaker |  |  | 240 kV
ALTALINK | 77s30 (77s Sagitawah) | 2013-12-20 11:30 | 2013-12-20 16:00 | N | N | function check the breaker 77s352 from 77s252 | Switch |  |  | Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2013-12-21 08:00 | 2013-12-21 16:00 | N | N | sheath test | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2013-12-22 08:00 | 2013-12-22 16:00 | N | N | Sheath Test | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Aurora T1,Aurora T-11 | 2013-12-23 08:00 | 2013-12-27 16:00 | N | Y | relay setting for tap changer | Transformer |  |  | 240 kV
ALTALINK | 258s 252 (258s Dow Hydrocarbons) | 2013-12-23 10:00 | 2013-12-23 12:00 | N | N | add SF6 | Circuit Breaker |  |  | Firm Load Loss
ALTALINK | 77s 752 (77s Sagitawah) | 2013-12-23 10:00 | 2013-12-23 12:00 | N | N | add SF6 | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 77s 452 (77s Sagitawah) | 2013-12-23 12:00 | 2013-12-23 14:00 | N | N | add Sf6 | Circuit Breaker |  |  | For Information Only
ALTALINK | 1206L (89s Ellerslie - 12s Heartland),1212L (89s Ellerslie - 12s Heartland) | 2013-12-27 08:00 | 2013-12-27 17:00 | N | N | 1206L/1212 will be tied and energized at 240 kV. | Line |  |  | 240 kV, For Information Only
ATCO | 6L05 (764s Heisler - 843s Bigknife Creek) | 2013-12-30 09:30 | 2013-12-31 16:00 | N | N | maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 928L (17s Benalto - 42s Sarcee) | 2014-01-06 07:30 | 2014-01-06 17:00 | N | N | ENMAX crews working on distribution in area | Line
ALTALINK | 928L (17s Benalto - 42s Sarcee) | 2014-01-06 07:30 | 2014-01-06 17:00 | N | Y | EPSC Working 36.111 | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-01-06 08:00 | 2014-01-09 18:00 | N | N | climbing inspection | Line |  |  | Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2014-01-06 08:00 | 2014-01-09 16:00 | N | N | bird mitigation and deficencies | Shunts |  |  | For Information Only
ENMAX | 26.81L (ENMAX 54 - ENMAX 26) | 2014-01-06 08:00 | 2014-01-13 16:00 | N | N | re-conductor | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2014-01-06 08:00 | 2014-01-07 16:00 | N | N | top-up gas on A6-II GIS breaker | Line |  |  | Overload
EPCOR | 803s T1 (803s Lambton) | 2014-01-07 05:00 | 2014-01-07 11:30 | N | Y | prep work in preparation of transformer replacement | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),364s Whitecourt Industrial 138 kV Bus 1 | 2014-01-07 07:01 | 2014-02-07 18:00 | N | N | re-configure 797L at 364s | Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.82L (ENMAX 54 - ENMAX 32) | 2014-01-07 08:00 | 2014-01-10 16:00 | N | N | maintneance | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | Natal overpower RAS3 | 2014-01-07 09:00 | 2014-01-07 17:00 | N | N | maintenance & timing tests on 1L274 | Terminal Equipment
ATCO | 822S Wolf Lake | 2014-01-07 10:00 | 2014-01-07 14:00 | N | N | 7L574 relay protection | Station
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2014-01-07 10:00 | 2014-01-07 14:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 803s T2 (803s Lambton) | 2014-01-07 12:00 | 2014-01-07 18:00 | N | Y | prep work in preparation of transformer replacement | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 108s 352 (108s Amelia) | 2014-01-07 13:00 | 2014-01-07 17:00 | N | Y | correct deficiency on breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 58L (245s Seebe - 32s Barrier),90L (115s Mt. Allan - 32s Barrier) | 2014-01-08 08:00 | 2014-04-30 19:00 | N | N | salvage 58L/90L and 32s re-build | Line |  |  | Overload
ALTALINK | 161L (255s Vulcan - 253s Blackie),253s 161 (253s Blackie) | 2014-01-08 08:00 | 2014-01-08 17:00 | N | N | replace faulty relay | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 108s 152 (108s Amelia) | 2014-01-08 08:00 | 2014-01-10 18:00 | N | Y | add sync check | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 80L (194s South Red Deer - 63s Red Deer) | 2014-01-08 10:00 | 2014-01-08 12:00 | N | N | connect mobile to 80L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s T1 (63s Red Deer),63s T3 (63s Red Deer),80L (194s South Red Deer - 63s Red Deer),63s Red Deer 138 kV North Bus | 2014-01-08 12:00 | 2014-01-11 12:00 | N | Y | replace 138kV PT's, replace 138kV LAs on T3 | Transformer, Line, Bus |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-01-09 01:30 | 2014-01-09 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload
ATCO | 930s SVC (930s Arcenciel) | 2014-01-09 08:00 | 2014-01-09 16:00 | N | Y | to allow testing on the Sync Condenser at 930S | Shunts |  |  | For Information Only
ALTALINK | 14s Devon RTU/SCADA | 2014-01-09 08:00 | 2014-01-09 17:00 | N | N | RTU reconfig | Terminal Equipment |  |  | Affects Visibility
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-01-10 01:00 | 2014-01-10 04:00 | N | N | high load move | Line
ATCO | 7L70 (819s Whitby Lake - 936s Norberg) | 2014-01-10 08:00 | 2014-01-11 17:00 | N | N | install the foundation for the new breaker | Line |  |  | For Information Only
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2014-01-11 08:00 | 2014-01-11 16:00 | N | N | replace failing heater | Circuit Breaker
ALTALINK | 80L (194s South Red Deer - 63s Red Deer) | 2014-01-11 12:01 | 2014-01-11 14:00 | N | N | remove mobile from 80L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L92 (819s Whitby Lake - 777s Vilna) | 2014-01-12 09:00 | 2014-01-20 16:00 | N | N | installation of foundation for new breakers | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PL7-1 (29EDD-34 - 29EDD-85) | 2014-01-12 09:00 | 2014-01-13 09:00 | N | N | reconfigure transmission line | Line
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2014-01-13 08:00 | 2014-01-31 16:00 | N | N | contractor digging under line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2014-01-13 08:00 | 2014-01-24 16:00 | N | N | line diff upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-01-13 08:30 | 2014-01-16 16:00 | N | N | climbing inspection | Line |  |  | Overload, Over/Under Voltage
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-01-14 01:30 | 2014-01-14 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2014-01-14 08:00 | 2014-01-16 16:00 | N | N | ENMAX re-conductoring | Line
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2014-01-14 08:00 | 2014-01-18 16:00 | N | N | switch repairs | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2014-01-14 08:00 | 2014-01-16 16:00 | N | N | reconductor | Line
ENMAX | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24),24B138-24BT3 (ENMAX 24) | 2014-01-14 08:00 | 2014-01-16 16:00 | N | N | breaker maintenance | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (268s Whitecourt - 526DL185),268s 69 (268s Whitecourt) | 2014-01-14 08:00 | 2014-01-14 17:00 | N | N | new tank heater required | Circuit Breaker, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2014-01-15 07:30 | 2014-01-20 17:00 | N | Y | replace step bolts on towers and fix minor deficiencies | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 320p 252 (320p Keephills) | 2014-01-15 08:00 | 2014-01-15 14:00 | N | Y | replacement switch is required (standard current FT switch) | Circuit Breaker |  |  | 240 kV
ALTALINK | 61s Lodgepole RTU/SCADA,454s Buck Lake RTU/SCADA | 2014-01-15 09:00 | 2014-01-15 11:00 | N | N | cutover of supervisory communications to new MPLS telecom System | Terminal Equipment |  |  | Affects Visibility
ATCO | 6L02 (765s Mannix Mine - 757s Battle River) | 2014-01-15 10:30 | 2014-01-15 13:00 | N | N | move large shovel under 6L02 | Line
ATCO | 936s 701T (936s Norberg) | 2014-01-16 08:00 | 2014-01-17 16:00 | N | N | Switch failure | Transformer
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2014-01-16 08:00 | 2014-01-17 16:00 | N | N | sub wash | Line, Transformer |  |  | For Information Only
ATCO | 932s 904 (932s Pemukan) | 2014-01-16 09:30 | 2014-01-16 13:30 | N | Y | replace a pressure guage | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 69s T2 (69s North Barrhead) | 2014-01-16 12:00 | 2014-01-16 16:00 | N | N | transfer Load from T2 over to T5 for commissioning checks | Transformer
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-01-17 02:00 | 2014-01-17 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX | 31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2014-01-17 08:00 | 2014-01-17 16:00 | N | N | wash sub 31 | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
AESO | 5L98 (BCH Nicola - Vaseux Lake) | 2014-01-17 09:00 | 2014-01-17 17:00 | Y | N | POW testing | Line |  |  | Limits ATC
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-01-17 23:00 | 2014-01-18 03:00 | N | N | high load move | Line |  |  | For Information Only
ENMAX | 24.82L (ENMAX 65 - ENMAX 24) | 2014-01-18 08:00 | 2014-01-18 19:00 | N | N | replace mech | Line
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2014-01-18 08:00 | 2014-01-18 12:00 | N | N | sub washing 9s | Line, Transformer
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2014-01-18 08:00 | 2014-01-18 16:00 | N | N | switch maintenance | Line, Transformer |  |  | Overload, Creates Radial Feeds
ENMAX | 23.4TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2014-01-18 12:00 | 2014-01-18 16:00 | N | N | Sub washing 23s | Line, Transformer |  |  | Creates Radial Feeds
ENMAX | 22.2TR (ENMAX 22),22.3TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2014-01-19 08:00 | 2014-01-19 12:00 | N | Y | sub washing 22s | Line, Transformer |  |  | Overload, Firm Load Loss
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2014-01-19 08:00 | 2014-01-19 16:00 | N | N | switch maintenance @ 27s | Transformer, Line |  |  | Overload, Firm Load Loss
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2014-01-19 08:00 | 2014-01-19 19:00 | N | Y | replace mech | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 777s 701T (777s Vilna) | 2014-01-19 10:00 | 2014-01-19 14:00 | N | N | oil leak & 7L92D2 repair | Transformer
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2014-01-19 12:00 | 2014-01-19 16:00 | N | N | sub washing 22s | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2014-01-20 07:00 | 2014-03-15 17:00 | N | N | rebuild 164L( 2nd stage) from Str #65 to Str #173. | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L87 (822s Wolf Lake - 826s Marguerite Lake) | 2014-01-20 07:00 | 2014-01-30 17:00 | N | N | line re-route and install new disconnect | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 37.82L (74s Janet - ENMAX 37) | 2014-01-20 08:00 | 2014-02-19 16:00 | N | N | ECTP work | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L48 (784s Donnelly - 7L48D5) | 2014-01-20 08:00 | 2014-01-22 16:00 | N | N | forced outage | Line |  |  | For Information Only
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2014-01-20 08:00 | 2014-01-23 16:00 | N | N | 847L A/B protection replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-01-20 08:30 | 2014-01-23 16:00 | N | N | climbing inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 834L (384s Keystone - 320p Keephills) | 2014-01-20 09:00 | 2014-01-23 15:00 | N | N | changing structures | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2014-01-20 09:00 | 2014-01-20 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 650s 352 (650s Hansman Lake) | 2014-01-20 11:00 | 2014-01-20 16:00 | N | N | correct deficiency | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 786s SVC (786s High Level) | 2014-01-21 08:30 | 2014-01-21 13:30 | N | Y | blower PM and the replacement and setup of the motor for blower #2. | Shunts |  |  | For Information Only
ATCO | 757s 911A (757s Battle River),757s 9L79D1 (757s Battle River) | 2014-01-21 09:00 | 2014-01-21 18:00 | N | N | hot spot repair | Switch |  |  | 240 kV, For Information Only
CNRL | 75PHL-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2014-01-22 07:00 | 2014-01-23 16:00 | N | Y | to complete line maintenance | Line |  |  | 240 kV, For Information Only
EPCOR | 814s T1 (814s Bellamy) | 2014-01-22 08:00 | 2014-01-22 13:00 | N | Y | analyzer training for SF6 gas analysis | Transformer |  |  | 240 kV
SUNCOR | 29EDD-94 407T (29EDD-94) | 2014-01-22 09:00 | 2014-01-22 18:00 | N | N | oil top-up | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-01-23 02:00 | 2014-01-23 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-94 406T (29EDD-94) | 2014-01-23 09:00 | 2014-01-23 18:00 | N | Y | oil top-up | Transformer |  |  | 240 kV, For Information Only
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2014-01-24 08:00 | 2014-01-24 12:00 | N | N | Wash 33 Sub | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 946s 905 (946s Oakland) | 2014-01-24 09:00 | 2014-01-24 16:00 | N | Y | breaker control repair | Circuit Breaker |  |  | 240 kV
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2014-01-24 12:00 | 2014-01-24 16:00 | N | N | wash 33 Sub | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | EMS | 2014-01-25 08:00 | 2014-01-25 16:00 | N | N | DT upgrades | SCInternal |  |  | For Information Only
ENMAX | 23.3TR (ENMAX 23),9.61L (ENMAX 23 - ENMAX 9) | 2014-01-25 08:00 | 2014-01-25 12:00 | N | N | Wash 23 Sub | Transformer, Line |  |  | For Information Only
ENMAX | Enmax 8 B138-4A0 (ENMAX 8) | 2014-01-25 08:00 | 2014-02-14 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 32.82L (ENMAX 54 - ENMAX 32) | 2014-01-25 13:00 | 2014-01-25 16:00 | N | N | wash | Line |  |  | Overload
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2014-01-26 07:30 | 2014-01-26 16:00 | N | Y | wash 31 Sub | Transformer, Shunts, Line |  |  | Overload, Limits ATC
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7) | 2014-01-26 08:00 | 2014-01-26 16:00 | N | N | maintenance @ 7s | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 330P Genesee RTU/SCADA | 2014-01-26 10:15 | 2014-01-26 10:30 | N | N | Telus communication outage | Terminal Equipment |  |  | Affects Visibility
GREENGATEP | 615s Halkirk RTU/SCADA | 2014-01-26 10:45 | 2014-01-26 11:00 | N | N | Telus network outage | Terminal Equipment |  |  | Affects Visibility
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-01-27 08:00 | 2014-01-27 16:00 | N | N | heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
EPCOR | 816s P2405 (816s Petrolia) | 2014-01-27 08:00 | 2014-01-31 18:00 | N | Y | CTs replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 923L (324s Cassils - 356s Milo) | 2014-01-27 13:30 | 2014-02-03 10:00 | N | Y | to complete inter-phase spacer install | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 156L (235s Entwistle - 156L 86A),235s 156E (235s Entwistle) | 2014-01-28 07:00 | 2014-01-30 17:00 | N | N | replace 138kv CVT (VT6) | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | EMS | 2014-01-28 08:00 | 2014-01-28 10:00 | N | N | ALF Release 4.1.1 | SCInternal |  |  | For Information Only
ALTALINK | 356s 352 (356s Milo) | 2014-01-28 08:00 | 2014-01-28 15:00 | N | Y | add gas - urgent | Circuit Breaker |  |  | 240 kV
ALTALINK | 368s C2 (368s Burdett) | 2014-01-28 10:00 | 2014-01-28 17:00 | N | Y | cap. bank maintenance | Shunts |  |  | Pre-Condition
EPCOR, ALTALINK | 909L (89s Ellerslie - 665s Dome),665s D2401 (665s Dome) | 2014-01-29 08:00 | 2014-01-29 15:00 | N | Y | BF relay maintenance checks | Circuit Breaker, Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader),409s 110 (409s Shell Scotford) | 2014-01-29 10:00 | 2014-01-29 16:00 | N | N | center phase not closing all the way - urgent | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2014-01-29 11:00 | 2014-01-29 16:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn) | 2014-01-30 08:00 | 2014-01-30 13:00 | N | N | requested breaker outage | Switch |  |  | Restricts Generation
ENMAX | 36B138-36.BT3 (ENMAX 36) | 2014-01-30 08:00 | 2014-01-30 16:00 | N | N | heater repair | Circuit Breaker |  |  | Overload
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2014-01-30 08:00 | 2014-01-30 15:00 | N | N | bus repair | Line |  |  | Creates Radial Feeds
EPCOR | 665s D2402 (665s Dome) | 2014-01-30 08:00 | 2014-01-30 15:00 | N | Y | BF Relay mtc: Op Checks | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
EPCOR, ALTALINK | 665s D2403 (665s Dome),909L (320p Keephills - 665s Dome) | 2014-01-31 08:00 | 2014-01-31 15:00 | N | N | BF relay maintenance | Circuit Breaker, Line |  |  | 240 kV, Overload
AESO-SC | Sask Power PR903 | 2014-01-31 10:00 | 2014-01-31 14:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Limits ATC
AESO-SC | EMS | 2014-01-31 10:10 | 2014-01-31 10:40 | N | N | DDST SRs Deployment | SCInternal |  |  | For Information Only
ALTALINK | 320p 752 (320p Keephills),320p 652 (320p Keephills) | 2014-01-31 17:00 | 2014-03-05 12:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 1201L (102s Langdon - BCH) | 2014-02-01 07:30 | 2014-02-01 18:00 | Y | Y | disconnect reactors so they can be moved to 520s - WATL | Line |  |  | Over/Under Voltage, Limits ATC, 500 kV
ENBRIDGE, MONTANA | MATL (120s Picture Butte - Montana),120s MATL | 2014-02-01 07:30 | 2014-02-01 18:00 | N | Y | install test switches on the metering panel & replace gas sensors | Station, Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 102s R7 (102s Langdon) | 2014-02-01 08:00 | 2014-03-14 11:00 | N | Y | move reactors from 102s to 520s - affects 1201L reclosing - WATL | Shunts |  |  | Over/Under Voltage, 500 kV
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2014-02-01 09:00 | 2014-02-01 18:00 | N | N | 6L12 outage to remove conductor (7L98) | Line
DAISHOWA | 147S Daishowa Plant | 2014-02-02 08:00 | 2014-02-02 14:00 | N | N | ETS 7 ADAMS outage | Station |  |  | For Information Only
ATCO | 840S McNeill Station | 2014-02-03 07:09 | 2014-02-06 12:00 | N | Y | burned cross-arm (forced outage) | Station |  |  | Limits ATC
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-02-03 08:00 | 2014-02-06 16:00 | N | N | climbing inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia) | 2014-02-03 08:00 | 2014-02-07 16:00 | N | Y | CT replacement at Petrolia 816s | Line |  |  | 240 kV
ALTALINK | 310p 2052 (310p Sundance) | 2014-02-03 09:00 | 2014-02-13 17:00 | N | Y | warranty repairs on breaker | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 935L (324s Cassils - 356s Milo) | 2014-02-03 10:30 | 2014-03-17 09:00 | N | Y | re conductor STRs #87 to #104 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 616L (103s Goose Lake - 616AL tap),616L (59s Peigan - 616AL tap) | 2014-02-04 07:00 | 2014-02-04 16:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-02-04 08:00 | 2014-02-04 16:00 | N | N | resplicingfFiber | Line
AESO-SC | DT | 2014-02-04 10:10 | 2014-02-04 10:30 | N | N | DT Upgrades release ¦ Production Deployment | SCInternal |  |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2014-02-05 08:00 | 2014-02-07 16:00 | N | N | oil leak repair | Transformer
ATCO | 834s 708 (834s Wesley Creek) | 2014-02-05 13:35 | 2014-02-06 20:00 | N | N | low SF6 gas (emergency repair) | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 62s12 (62s Brazeau) | 2014-02-05 23:00 | 2014-02-06 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s11 (62s Brazeau) | 2014-02-06 03:00 | 2014-02-06 07:00 | N | Y | maintenace | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 26.81L (ENMAX 54 - ENMAX 26) | 2014-02-06 08:00 | 2014-02-06 16:00 | N | N | emergency breaker heather repair | Line |  |  | Overload
ALTALINK | 161L (255s Vulcan - 253s Blackie),253s 161 (253s Blackie) | 2014-02-06 08:00 | 2014-02-06 17:00 | N | N | update relay settings | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO | 827s SVC (827s Cranberry Lake) | 2014-02-06 08:00 | 2014-02-06 17:00 | N | N | 703T and SVC coordinated work | Shunts |  |  | For Information Only
ALTALINK | 924L (102s Langdon - 356s Milo),927L (102s Langdon - 356s Milo) | 2014-02-08 08:00 | 2014-02-08 17:00 | N | Y | remove span of old 1201L from over 924L & 927L - WATL | Line |  |  | 240 kV, Overload, Over/Under Voltage
ENMAX | 36B138-36BT3 (ENMAX 36) | 2014-02-08 08:00 | 2014-02-08 16:00 | N | N | repair failed heater | Circuit Breaker
ATCO | 9L990 (72s Leismer - 2049s Kettle River) | 2014-02-09 07:00 | 2014-02-17 17:00 | N | N | ATCO request to deenergize 9L990 | Line |  |  | 240 kV, For Information Only
ATCO | 9L990 (72s Leismer - 2049s Kettle River) | 2014-02-09 07:00 | 2014-02-17 17:00 | N | Y | connect new 9L990/9L45 in/out to Kettle substation | Line |  |  | 240 kV, Restricts Generation, Creates Radial Feeds
ALTALINK | 924L (102s Langdon - 356s Milo) | 2014-02-09 08:00 | 2014-02-13 17:00 | N | Y | remove span of old 1201L from over 924L & 927L - WATL, line repairs | Line |  |  | 240 kV
EPCOR | E511s VictoriaT3 (511s Victoria),Victoria V725 (Victoria),Victoria V724 (Victoria) | 2014-02-10 08:00 | 2014-02-15 17:00 | N | N | P&C relay maintenance & upgrades | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 25B240-D142 (ENMAX 25),25B240-D139 (ENMAX 25),ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D133 (ENMAX 25),25PT240-Z42 | 2014-02-10 08:00 | 2014-02-11 16:00 | N | Y | change taps on CVT | Circuit Breaker, Terminal Equipment |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 920L (71s Lamoureux - 557s Castle Downs) | 2014-02-10 08:00 | 2014-02-15 16:00 | N | Y | P&C maintenance | Line |  |  | 240 kV, Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8) | 2014-02-10 08:00 | 2014-02-11 16:00 | N | N | repair switch 1-1a51 and 1-1a101 | Line |  |  | For Information Only
ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2014-02-10 08:00 | 2014-02-11 18:00 | N | N | 12s bus differential CT circuit test/wire change | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-02-10 08:30 | 2014-02-13 16:00 | N | N | climbing inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 823S Wapiti | 2014-02-10 10:00 | 2014-02-13 15:00 | N | N | work on 25kV portion | Station
ALTALINK | 410s 152 (410s Josephburg) | 2014-02-10 13:00 | 2014-02-11 17:00 | N | Y | HGF breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-02-11 01:30 | 2014-02-11 04:00 | N | N | high load move | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2014-02-11 08:00 | 2014-02-11 10:30 | N | N | RV728 breaker op checks | Line |  |  | For Information Only
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge),370s179 (370s North Lethbridge) | 2014-02-11 08:00 | 2014-02-12 16:00 | N | N | City of Lethbridge to test line protection relays at 111s | Switch, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 384s T1 (384s Keystone) | 2014-02-11 08:00 | 2014-02-12 16:00 | N | N | install NGR; relay settings changes | Transformer |  |  | For Information Only
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24) | 2014-02-11 08:00 | 2014-02-12 16:00 | N | N | 24MD138-24.2TR repair, switch maintenance, doble | Transformer, Line
ALTALINK | 798L (364s Whitecourt Industrial - 77s Sagitawah),364s Whitecourt Industrial 138kV Bus 2,364s T2 (364s Whitecourt Industrial) | 2014-02-11 09:00 | 2014-02-11 15:00 | N | N | re-Fusing bus 2 PT's and re-fusing 798L CVT; connect 'heaters' in line CVT and bus PT's | Bus, Line, Transformer |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 733L (151s Strathmore - 428S Namaka),428s 733N (428s Namaka) | 2014-02-11 09:00 | 2014-02-11 17:00 | N | N | 138 kV breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21),44s 50X (44s Bearspaw) | 2014-02-11 09:00 | 2014-02-11 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2014-02-11 10:30 | 2014-02-11 12:00 | N | N | RV722 breaker op checks | Line |  |  | Pre-Condition
EPDG | GN3 Genesee #3 Generator Test | 2014-02-12 07:00 | 2014-02-14 21:00 | N | N | RATA test | Unit
ENMAX | 1.6TR (ENMAX 1) | 2014-02-12 08:00 | 2014-02-12 16:00 | N | N | repair Switch 1-5a82 and 1-6a101 and Switch maintenance | Transformer |  |  | For Information Only
EPCOR | 72RS5 (Rossdale - Strathcona) | 2014-02-12 08:00 | 2014-02-12 10:30 | N | N | RV724 breaker op checks | Line |  |  | For Information Only
ALTALINK | 535s C1 (535s Joffre) | 2014-02-12 08:00 | 2014-02-18 17:00 | N | Y | quality assurance check | Shunts |  |  | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2014-02-12 08:00 | 2014-02-12 10:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2014-02-12 08:00 | 2014-02-15 16:00 | N | N | Fortis work | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2014-02-12 08:00 | 2014-02-12 16:00 | N | N | removal of an existing steel tower | Line |  |  | Overload, Restricts Generation, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 7L70 (819s Whitby Lake - 936s Norberg) | 2014-02-12 08:00 | 2014-02-13 16:00 | N | N | Install A frame gantry and switch for New 7L139 in 819S Whitby Sub | Line |  |  | Pre-Condition
ALTALINK | A840s McNeill ATCO Outage - Info | 2014-02-12 09:00 | 2014-02-12 16:00 | N | N | ATCO complete station shut down to replace fire sensors in the Valve Hall | Terminal Equipment |  |  | For Information Only
ENMAX, ALTALINK | 44s 36_81E (44s Bearspaw),36.81L (44s Bearspaw - ENMAX 36) | 2014-02-12 09:00 | 2014-02-12 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
EPCOR | 930L (37s North Calder - Poundmaker) | 2014-02-12 09:00 | 2014-02-12 17:00 | N | Y | remove wave trap from CVT | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s C1 (157s Lac La Biche) | 2014-02-12 09:00 | 2014-02-12 12:30 | N | N | 157s23 west phase leak | Shunts |  |  | For Information Only
ALTALINK | 410s 252 (410s Josephburg) | 2014-02-12 09:00 | 2014-02-13 17:00 | N | Y | HGF breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 840S McNeill Station | 2014-02-12 09:00 | 2014-02-12 16:00 | N | Y | replace fire sensor valve hall | Station |  |  | Limits ATC
ALTALINK | 368s C2 (368s Burdett),368s 44 (368s Burdett) | 2014-02-12 09:00 | 2014-02-12 17:00 | N | Y | breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 33s5 (33s Spray) | 2014-02-12 09:00 | 2014-02-12 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 72RG1 (Rossdale - Garneau) | 2014-02-12 10:30 | 2014-02-12 12:00 | N | N | RV7210 Breaker Op checks | Line |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2014-02-12 13:00 | 2014-02-12 15:00 | N | N | RV727 breaker op checks | Line |  |  | For Information Only
AESO | 788L (157s Lac La Biche - 788L Tap) | 2014-02-12 13:00 | 2014-02-12 16:00 | Y | N | 157s18 switching cleaning / adjustments | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RG7 (Rossdale - Garneau) | 2014-02-12 15:00 | 2014-02-12 17:00 | N | N | RV725 Breaker Op checks | Line |  |  | For Information Only
ALTALINK, ENMAX | 42s T1 (42s Sarcee),21.80L (42s Sarcee - ENMAX 21),7.82L (42s Sarcee - ENMAX 7),832L (42s Sarcee - ENMAX 12),42s43 (42s Sarcee),42s 693 (42s Sarcee),42s Sarcee 138 kV North Bus | 2014-02-13 07:00 | 2014-02-13 08:00 | N | Y | 138kV switch maintenance | Switch, Transformer, Line, Circuit Breaker, Bus |  |  | 240 kV, Pre-Condition, Overload
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2014-02-13 08:00 | 2014-03-31 16:00 | N | N | replacing 138kv structures | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale VHBB1 (Rossdale) | 2014-02-13 08:00 | 2014-02-13 10:30 | N | N | VHBB1 checks | Circuit Breaker
EPCOR | Woodcroft W722 (Woodcroft) | 2014-02-13 08:00 | 2014-02-13 12:00 | N | N | bus Inspection | Circuit Breaker
ALTALINK | 77s T1 (77s Sagitawah),77s 252 (77s Sagitawah),77s 352 (77s Sagitawah),77s65 (77s Sagitawah),77s30 (77s Sagitawah) | 2014-02-13 09:00 | 2014-02-13 12:00 | N | Y | functional testing breaker | Switch, Circuit Breaker, Transformer |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 821L (158s Vauxhall - 421s Hays),158s 821E (158s Vauxhall) | 2014-02-13 10:00 | 2014-02-13 17:00 | N | N | leaking dashpot | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 728L (405s Waupisoo - 353s Plamondon),353s23 (353s Plamondon) | 2014-02-13 10:00 | 2014-02-13 15:00 | N | Y | switch adjustment | Line, Switch |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale VHBB2 (Rossdale) | 2014-02-13 10:30 | 2014-02-13 12:00 | N | N | VHBB2 checks. | Circuit Breaker |  |  | Pre-Condition
EPCOR | Woodcroft W723 (Woodcroft),Woodcroft W725 (Woodcroft),Woodcroft Trans #2 | 2014-02-13 12:00 | 2014-02-13 17:00 | N | N | bus inspection for woodcroft T2 | Circuit Breaker, Terminal Equipment
EPCOR | Rossdale C1 | 2014-02-13 13:00 | 2014-02-13 15:00 | N | Y | R72C1 breaker checks | Shunts |  |  | For Information Only
EPCOR | Rossdale C2 | 2014-02-13 15:00 | 2014-02-13 17:00 | N | Y | R72C2 breaker checks | Shunts |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2014-02-14 08:00 | 2014-02-14 17:00 | N | N | bus inspection | Line |  |  | Creates Radial Feeds
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2014-02-14 08:00 | 2014-02-15 17:00 | N | Y | removal of bird nests | Line |  |  | 240 kV, Overload
GREENGATEP | 615s DVAR (615s Halkirk) | 2014-02-14 09:00 | 2014-02-14 17:00 | N | N | oil sampling on transfoerms | Shunts |  |  | For Information Only
ALTALINK | 1071L (103s Goose Lake - 312s Fidler) | 2014-02-15 07:30 | 2014-02-24 17:00 | N | Y | erect new tower for new line to 312s Fidler | Line |  |  | 240 kV
ALTALINK | 526L (268s Whitecourt - 526DL185),268s 69 (268s Whitecourt) | 2014-02-15 08:00 | 2014-02-15 09:00 | N | N | test operation to commission new DG transfer trip scheme | Line, Circuit Breaker
ALTALINK | 920L (37s North Calder - 557s Castle Downs) | 2014-02-17 08:00 | 2014-02-21 16:00 | N | N | Epcor Work At E557s | Line
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-02-18 02:00 | 2014-02-18 04:00 | N | N | high load move | Line |  |  | Contingency Requires Mitigation
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2014-02-18 04:01 | 2014-02-21 15:00 | N | N | changing structures | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 2L294 (Nelway - A.A. Lambert) | 2014-02-18 07:00 | 2014-02-19 16:30 | N | Y | replacing defective timbers and insulators | Line |  |  | 240 kV, Limits ATC, Contingency Requires Mitigation
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32B138-32BT5 (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),Z31 PT | 2014-02-18 08:00 | 2014-02-19 16:00 | N | N | Z31 equipment outage | Transformer, Line, Terminal Equipment, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2014-02-18 08:00 | 2014-02-27 17:00 | N | N | climbing inspection line | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | RossdaleT1 (Rossdale) | 2014-02-18 08:00 | 2014-02-18 17:00 | N | N | relay maintenance op check | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-02-18 08:00 | 2014-02-19 16:00 | N | N | climbing inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 814s T2 (814s Bellamy) | 2014-02-18 08:00 | 2014-02-18 17:00 | N | N | Rossdale T1 relay maintenance op check | Transformer |  |  | 240 kV, For Information Only
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2014-02-18 08:00 | 2014-02-19 16:00 | N | N | switch maintenance | Line |  |  | For Information Only
ATCO | 766s Nevis RTU/SCADA | 2014-02-18 09:00 | 2014-02-18 11:00 | N | N | MPLS supervisory circuit cutover | Terminal Equipment |  |  | Affects Visibility
EPCOR | 52s T2 (52s East Industrial) | 2014-02-18 09:00 | 2014-02-18 11:00 | N | N | breaker maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 310p 452 (310p Sundance) | 2014-02-18 09:00 | 2014-02-21 17:00 | N | Y | warranty repair - replace A phase CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 43 (159s Colinton) | 2014-02-18 13:00 | 2014-02-18 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),1.81L (ENMAX 20 - ENMAX 1) | 2014-02-18 15:00 | 2014-02-18 17:00 | N | N | Spring Pothead Washing (2 hrs) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 710L (159s Colinton - 56s Boyle),159s 48 (159s Colinton) | 2014-02-19 08:00 | 2014-02-19 14:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac),391s 28 (391s Balzac) | 2014-02-19 08:00 | 2014-02-19 17:00 | N | N | 391s28 switch repair | Line, Switch |  |  | Overload, Restricts Generation, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 814s T1 (814s Bellamy) | 2014-02-19 08:00 | 2014-02-19 11:00 | N | Y | Rossdale:BR721 BF maintenance Op - Check | Transformer |  |  | 240 kV
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2014-02-19 08:00 | 2014-02-19 17:00 | N | N | test auto recloser logic | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 893AL (893AL3 - 354s Summerview) | 2014-02-19 08:00 | 2014-02-22 18:00 | N | Y | install footings for new 112s connection point | Line |  |  | Restricts Generation
AESO | 551CL1 (945s Sunshine - 551CL1 Tap) | 2014-02-19 08:00 | 2014-02-20 18:00 | N | N | PT replacement and new platform construction | Line |  |  | For Information Only
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2014-02-19 08:00 | 2014-02-20 18:00 | N | N | 12s bus differential CT circuit test / wire change | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 71s 252 (71s Lamoureux) | 2014-02-19 08:00 | 2014-02-19 12:00 | N | N | Dashpot leaking and low on oil. | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 1036L (370s North Lethbridge - 356s Milo) | 2014-02-19 09:00 | 2014-02-19 17:30 | N | Y | trouble corrective:urgent conductor repairs at STR# 100. | Line |  |  | 240 kV
ATCO | 772s Youngstown RTU/SCADA | 2014-02-19 10:30 | 2014-02-19 14:00 | N | N | Crews will be relocating antennae dish at Pllockville tower | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 71s 352 (71s Lamoureux) | 2014-02-19 13:00 | 2014-02-20 12:00 | N | N | dashpot leaking and low on oil. | Circuit Breaker |  |  | Contingency Requires Mitigation
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2014-02-20 07:00 | 2014-02-21 16:30 | N | Y | replacing defective D/E insulators - BC maintenance does not affect AB ATC | Line |  |  | 240 kV, Limits ATC, Contingency Requires Mitigation
EPCOR | RossdaleT4 (Rossdale) | 2014-02-20 08:00 | 2014-02-20 17:00 | N | N | relay maintenance op-checks | Transformer
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 46 (159s Colinton) | 2014-02-20 08:00 | 2014-02-20 14:00 | N | N | latch replacement and oil leak inside the cabinet | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2014-02-20 08:00 | 2014-02-28 18:00 | N | Y | conductor repairs | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 38 B138-38.83 (ENMAX 38) | 2014-02-20 08:00 | 2014-02-20 16:00 | N | N | top up SF6 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 127s 815N (127s Bruderheim),815L (13s Deerland - 127s Bruderheim) | 2014-02-20 09:00 | 2014-02-20 17:00 | N | N | HGF breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 30.81L (42s Sarcee - ENMAX 30),42s 30 (42s Sarcee) | 2014-02-20 09:00 | 2014-02-20 17:00 | N | N | heater fail | Circuit Breaker, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L38 (875s Algar - 917s Horse River) | 2014-02-20 09:00 | 2014-02-20 17:00 | N | N | add SF6 to breaker | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 916L (42s Sarcee - 5s East Calgary),917L (74s Janet - 5s East Calgary) | 2014-02-21 08:00 | 2014-03-01 17:00 | N | Y | ECTP: 5s  Remove bypass, install 916L slack spans, north bus, P&C etc. | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 5s T1 (East Calgary) | 2014-02-21 08:00 | 2014-02-28 16:00 | N | Y | working under 138KV side of 5sT1, breaker maintenance (5S8) | Transformer |  |  | 240 kV, Overload
ENMAX | ENMAX 25 B240-D136 (ENMAX 25) | 2014-02-21 08:00 | 2014-03-13 16:00 | N | Y | repair SF6 leak on 1 Pole | Circuit Breaker |  |  | 240 kV
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2014-02-21 15:00 | 2014-02-21 17:00 | N | N | Spring Pothead Washing (2 hrs) | Line |  |  | Creates Radial Feeds
ENMAX, ALTALINK | 2.81L (ENMAX 2 - ENMAX 9),833L (ENMAX 2 - ENMAX 12) | 2014-02-22 07:00 | 2014-02-22 18:00 | N | N | string new overhead conductor from 916L | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2014-02-22 07:00 | 2014-02-22 18:00 | N | N | ECTP: string new overhead conductor from 916L to "A" frame over 2.81L & 833L. | Line
ALTALINK | 5s T2 (5s East Calgary) | 2014-02-22 08:00 | 2014-02-28 16:00 | N | N | comissioning- ISD = Feb 28, 2014 | Transformer
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),21.61L (ENMAX 21 - ENMAX 34) | 2014-02-22 08:00 | 2014-02-22 16:00 | N | N | spring line washing and errect distribution pole | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2014-02-22 16:00 | 2014-02-22 17:00 | N | N | spring pot head washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2014-02-22 18:01 | 2014-02-23 18:00 | N | Y | string new overhead conductor from 916L | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2014-02-24 08:00 | 2014-02-25 15:00 | N | N | changing structures | Line |  |  | Overload, Over/Under Voltage
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2014-02-24 08:00 | 2014-02-25 16:00 | N | N | GIS switch maintenance | Line |  |  | Overload
ENMAX | 65.1 TR (ENMAX 65) | 2014-02-24 08:00 | 2014-02-27 16:00 | N | Y | switch maintenance | Transformer |  |  | 240 kV
ALTALINK | 235s14 (235s Entwistle) | 2014-02-24 13:00 | 2014-02-24 15:00 | N | N | replace 235s14 25kV PT fuse blown | Not In Model |  |  | For Information Only
ALTALINK | 310p 2252 (310p Sundance) | 2014-02-25 08:00 | 2014-02-25 17:00 | N | Y | test pole discrepancy function | Circuit Breaker |  |  | 240 kV
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome),89s 1052 (89s Ellerslie),89s 1152 (89s Ellerslie) | 2014-02-25 08:00 | 2014-02-25 14:00 | N | Y | 89s909W hot spot repairs | Line, Circuit Breaker |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2014-02-25 15:00 | 2014-02-26 16:00 | N | Y | forced outage | Shunts |  |  | Limits ATC
EPCOR | 511s Victoria T1 (511s Victoria) | 2014-02-26 08:00 | 2014-02-26 15:00 | N | N | VDS5 repair | Transformer
ALTALINK | 755L (535s Joffre - 247s Piper Creek) | 2014-02-26 08:00 | 2014-02-26 14:00 | N | N | high load move, move reactor to Nova Joffre plant site | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2014-02-26 08:00 | 2014-02-26 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2014-02-26 08:00 | 2014-02-27 16:00 | N | N | switch maintenance and transformer repairs | Transformer
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-02-26 08:30 | 2014-02-27 16:00 | N | N | 7L65 climbing inspection | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-02-26 08:30 | 2014-02-27 16:00 | N | N | ATCO climbing inspection | Line
ALTALINK | 275s 2 (275s Jenner) | 2014-02-26 10:00 | 2014-02-26 17:00 | N | Y | low gas on north phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 (ENMAX 54) | 2014-02-27 06:00 | 2014-02-27 11:00 | N | N | replace heaters | Circuit Breaker, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2552 (74s Janet) | 2014-02-27 08:00 | 2014-02-27 17:00 | N | Y | repair oil leak on grading caps | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 511s Victoria T2 (511s Victoria) | 2014-02-27 08:00 | 2014-02-27 15:00 | N | N | VDS6 repair | Transformer
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2014-02-27 08:30 | 2014-02-27 13:00 | N | N | spring line washing | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 28s 31 (28s West Brooks) | 2014-02-27 09:00 | 2014-02-27 17:00 | N | N | low gas level on east phase | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-02-27 11:01 | 2014-02-28 18:00 | N | N | bushing replacement & draw lead extension on 39.3TR, check reversing switch | Line |  |  | Pre-Condition
EPCOR | E511s VictoriaT3 (511s Victoria) | 2014-02-28 08:00 | 2014-02-28 15:00 | N | N | VDS7 repair | Transformer |  |  | For Information Only
EPCOR | 52s T2 (52s East Industrial) | 2014-02-28 08:00 | 2014-02-28 15:00 | N | N | protection work | Transformer |  |  | 240 kV, For Information Only
ENMAX | ENMAX 25 B240-D136 (ENMAX 25) | 2014-02-28 08:00 | 2014-03-13 16:00 | N | Y | fix leaking SF6 problem | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 163s C1 (163s Amoco Empress) | 2014-02-28 08:40 | 2014-05-15 16:00 | N | Y | unavailable due to failed switch of 163s63 (forced outage) | Shunts |  |  | For Information Only
ALTALINK | 908L (89s Ellerslie - 38s East Edmonton) | 2014-02-28 09:00 | 2014-02-28 13:00 | N | Y | relay maintenance and operational checks on EDS2 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | GEN6 Judy Creek Generator | 2014-03-01 08:00 | 2014-03-07 16:00 | N | N | commissioning- ISD= March 1, 2014 | Unit
ALTALINK, ENMAX | 12.1TR (ENMAX 12),12.2TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12),833L (ENMAX 2 - ENMAX 12) | 2014-03-01 08:00 | 2014-03-01 16:00 | N | N | Bus Differential & Auto Switching Functional Testing | Line, Transformer |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2014-03-01 08:00 | 2014-03-07 10:30 | N | Y | forced outage | Shunts |  |  | Limits ATC
ENMAX | 38.1C (ENMAX 38) | 2014-03-01 08:00 | 2014-06-04 11:00 | N | Y | low SF6 (forced outage) | Shunts |  |  | Limits ATC
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 38 B138-38.83 (ENMAX 38) | 2014-03-02 08:00 | 2014-03-02 16:00 | N | N | top up SF6 | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-03-02 08:00 | 2014-03-02 16:00 | N | N | ENMAX: Remove 25B240-D136, MD/SW Mtce. | Line |  |  | 240 kV
ALTALINK | 778L (217s North Red Deer - 87s Gaetz),80L (198s Blackfalds - 217s North Red Deer),217s7 (217s North Red Deer) | 2014-03-02 09:00 | 2014-03-02 13:00 | N | N | 138 kV switch maintenance | Switch, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 814s T1 (814s Bellamy) | 2014-03-03 08:00 | 2014-03-03 11:00 | N | Y | Rossdale: BR721 BF maintenance Op - Check | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2014-03-03 08:00 | 2014-03-12 15:00 | N | N | oil pumping station upgrades at 987S Clover Bar | Line |  |  | For Information Only
ALTALINK | 163s T1 (163s Amoco Empress) | 2014-03-03 08:00 | 2014-03-06 10:00 | N | N | Customer requested outage | Transformer |  |  | For Information Only
ENMAX | 65.2 TR (ENMAX 65) | 2014-03-03 08:00 | 2014-03-05 16:00 | N | Y | SW maint SW 135,Sw141, 65MD240-65.2TR, 65MD138-65.2TR, SW 87, SW86, SW93 | Transformer |  |  | 240 kV, For Information Only
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2014-03-03 08:00 | 2014-03-13 17:00 | N | N | line & conductor inspections/arm changes | Line |  |  | Firm Load Loss, Creates Radial Feeds
Lethbridge | 813L (241s Lethbridge Uplands - 146s Lethbridge MacDonald) | 2014-03-03 08:00 | 2014-03-31 16:00 | N | N | replacing 138kV structures | Line |  |  | Creates Radial Feeds
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2014-03-03 08:00 | 2014-03-03 16:00 | N | N | install corona rings on structures 48 & 49 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2014-03-03 08:00 | 2014-03-04 16:00 | N | N | GIS SW maint 1-9A1, 1-9A101, 1-9A51, 1-9A81, 1-9A82, 1-9A91, 1-9A92 | Line |  |  | For Information Only
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2014-03-03 08:00 | 2014-03-11 15:00 | N | N | oil pumping station upgrades at 987S Clover Bar | Line |  |  | For Information Only
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2014-03-03 08:00 | 2014-03-03 15:00 | N | N | VDS8 repair | Line |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-03-03 09:00 | 2014-03-03 16:00 | N | N | replace broken cross arm | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 320p 852 (320p Keephills) | 2014-03-03 11:00 | 2014-03-03 17:00 | N | Y | CT Leak and gauge level low | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 526L (526L367 - 526L418) | 2014-03-03 14:00 | 2014-08-31 12:00 | N | N | temporarily open 526L418 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),1.81L (ENMAX 20 - ENMAX 1) | 2014-03-03 15:00 | 2014-03-03 17:00 | N | N | spring pothead washing | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 523s Bullshead RTU/SCADA,107s Westfield RTU/SCADA,41s Medicine Hat RTU/SCADA,368s Burdett RTU/SCADA | 2014-03-04 08:00 | 2014-03-04 17:00 | N | N | radio upgrade | Terminal Equipment |  |  | Affects Visibility
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2014-03-04 08:00 | 2014-03-04 15:00 | N | N | VDS10 repair | Line |  |  | For Information Only
ENMAX | 37.82L (74s Janet - ENMAX 37) | 2014-03-04 13:00 | 2014-03-05 16:00 | N | N | forced outage | Line
ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-03-05 07:00 | 2014-04-05 18:00 | N | Y | L to J: 1003L rebuild L9 diameter - new switchs, CT, CVT - P&C, SCADA & telecom | Line |  |  | 240 kV
ALTALINK | 1071L (103s Goose Lake - 312s Fidler) | 2014-03-05 07:30 | 2014-05-15 17:00 | N | Y | string new 1071L & 994L to 312s Fidler | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville) | 2014-03-05 07:30 | 2014-03-05 16:30 | N | N | install switch foundations for the new Bear Trap Substation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 258s T2 ( 258s Dow Hydro Carbons) | 2014-03-05 08:00 | 2014-03-05 17:00 | N | N | low oil level investigation | Transformer |  |  | For Information Only
EPCOR | E511s VictoriaT3 (511s Victoria) | 2014-03-05 08:00 | 2014-03-06 15:00 | N | N | VDS11 repair | Transformer |  |  | For Information Only
ENMAX | 3.82L (ENMAX 3 - ENMAX 8),ENMAX 3 B138-3.82 (ENMAX 3) | 2014-03-05 08:00 | 2014-03-05 16:00 | N | N | heater repair | Line, Circuit Breaker |  |  | Overload
ALTALINK | 33s 4 (33s Spray) | 2014-03-05 09:00 | 2014-03-05 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 159s T1 (159s Colinton),710L (159s Colinton - 56s Boyle),159s 51 (159s Colinton) | 2014-03-05 13:00 | 2014-03-05 17:00 | N | N | 159s51 Latch replacement | Circuit Breaker, Line, Transformer |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2014-03-06 07:30 | 2014-03-17 19:00 | N | Y | string 1325L over 903L & 190L - WATL | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2014-03-06 08:00 | 2014-03-06 11:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36B138-36BT3 (ENMAX 36) | 2014-03-06 08:00 | 2014-03-06 16:00 | N | N | heater repair | Circuit Breaker
ALTALINK | 258s T1 (258s Dow Hydro Carbons) | 2014-03-06 08:00 | 2014-03-06 17:00 | N | N | low oil level investigation | Transformer
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21),44s 50X (44s Bearspaw) | 2014-03-06 09:00 | 2014-03-06 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2014-03-06 09:30 | 2014-03-06 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 755s Cordel RTU/SCADA | 2014-03-06 10:00 | 2014-03-08 17:30 | N | N | download updates | Terminal Equipment |  |  | Affects Visibility
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2014-03-06 15:00 | 2014-03-06 17:00 | N | N | spring pothead washing (2 hrs) | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-03-07 08:00 | 2014-03-07 16:00 | N | N | ENMAX work: 74s1003X (Janet), SW 142, SW 139, 25PT240-1003 Secondary Fuses | Line |  |  | 240 kV
EPCOR | E511s VictoriaT4 (511s Victoria) | 2014-03-07 08:00 | 2014-03-07 15:00 | N | N | VDS13 repair | Transformer
ENMAX | 14.2C (ENMAX 14) | 2014-03-07 10:30 | 2014-06-17 15:00 | N | Y | forced outage | Shunts |  |  | Limits ATC
ALTALINK | 743L (527s Coal Valley - 743L1A) | 2014-03-07 13:00 | 2014-03-07 16:00 | N | N | trouble corrective | Line |  |  | Firm Load Loss
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2014-03-07 15:00 | 2014-03-07 17:00 | N | N | spring pothead washing (2 hrs) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2014-03-08 07:00 | 2014-03-08 15:00 | N | Y | L to J project: create open point A for bus construction expansion and re-energize T2 | Transformer, Bus, Shunts |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 23.4TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2014-03-08 08:00 | 2014-03-11 16:00 | N | N | ECTP 2s | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s 104 (74s Janet) | 2014-03-08 15:30 | 2014-04-16 10:00 | N | Y | L to J project: B2 bus ampacity upgrade and replace 74s22X,74s21X,74s47,74s1003,74s23X and 74s28X | Circuit Breaker, Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 225s16 (225s Magrath) | 2014-03-09 14:00 | 2014-04-20 14:00 | N | Y | customer requested outage | Switch |  |  | Restricts Generation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2014-03-09 15:00 | 2014-03-09 16:00 | N | N | pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2014-03-09 16:00 | 2014-03-09 17:00 | N | N | pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),36PT138-Z32,69KV PT | 2014-03-10 08:00 | 2014-03-10 12:00 | N | N | substation washing | Transformer, Line, Terminal Equipment |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark T1 (Meadowlark) | 2014-03-10 08:00 | 2014-03-14 16:00 | N | N | P&C relay maintenance | Transformer |  |  | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2014-03-10 08:00 | 2014-03-18 15:00 | N | N | P&C upgrades on J722 breaker at Jasper | Line |  |  | For Information Only
ATCO | 7L70 (819s Whitby Lake - 936s Norberg) | 2014-03-10 08:00 | 2014-03-12 16:00 | N | N | installing a new swich 704A | Line
EPCOR | Garneau T1 (Garneau) | 2014-03-10 08:00 | 2014-03-10 16:00 | N | N | P&C Relay Maintenance | Transformer |  |  | For Information Only
EPCOR | E511s VictoriaT4 (511s Victoria) | 2014-03-10 08:00 | 2014-03-10 15:00 | N | N | VDS14 repair | Transformer |  |  | For Information Only
ALTALINK | 410s 752 (410s Josephburg) | 2014-03-10 10:00 | 2014-03-10 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36),36PT138-Z31,7PT138-7.84 | 2014-03-10 12:00 | 2014-03-10 16:00 | N | N | substation washing | Line, Transformer, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s T5 (62s Brazeau),62s 207 (62s Brazeau) | 2014-03-10 13:00 | 2014-03-11 17:00 | N | Y | breaker maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Restricts Generation, Creates Radial Feeds
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2014-03-10 13:00 | 2014-03-10 17:00 | N | N | repair 71s5 hot spot | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 77s 51 (77s Sagitawah) | 2014-03-10 13:00 | 2014-03-13 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 708L (71s Lamoureux - 708L88X),71s708 (71s Lamoureux) | 2014-03-11 08:00 | 2014-03-11 17:00 | N | N | hot spot | Switch, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 189L (373s Madden - 189L2) | 2014-03-11 08:00 | 2014-03-13 17:00 | N | N | replace dead-end structures #12 and #13 | Line
EPCOR | Garneau T2 (Garneau) | 2014-03-11 08:00 | 2014-03-11 16:00 | N | N | P&C relay maintenance | Transformer
BCH | 5L91 (Selkirk - Ashton Creek) | 2014-03-11 08:00 | 2014-03-20 16:00 | N | Y | line maintenance (spacers and acring horns) | Line |  |  | Pre-Condition, Limits ATC, 500 kV
ENMAX | 25B240-D135 (ENMAX 25),ENMAX 25 B240-D134 (ENMAX 25),ENMAX 25 B240-D133 (ENMAX 25),25B240-D132 (ENMAX 25) | 2014-03-11 08:00 | 2014-03-12 16:00 | N | Y | switch maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 410s 852 (410s Josephburg) | 2014-03-11 08:00 | 2014-03-11 15:00 | N | N | 138 kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2014-03-11 08:00 | 2014-03-11 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 223s 39 (223s Strome),701L (395s North Holden - 223s Strome) | 2014-03-11 09:00 | 2014-03-14 17:00 | N | N | 138kV breaker replacement | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2014-03-11 12:00 | 2014-03-11 16:00 | N | N | substation washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 68s T1 (68s Willesden Green) | 2014-03-11 19:00 | 2014-03-12 18:00 | N | Y | install bus 1 bird cover, replace LA and insulators | Transformer |  |  | 240 kV, For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-03-12 01:00 | 2014-03-12 03:00 | N | N | high load | Line |  |  | For Information Only
Saskpower | Sask Power A1P | 2014-03-12 07:00 | 2014-03-15 20:00 | N | N | structure change | Line |  |  | Limits ATC, For Information Only
EPCOR | Garneau G723 (Garneau) | 2014-03-12 08:00 | 2014-03-12 12:00 | N | N | P&C relay maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2014-03-12 08:00 | 2014-03-12 10:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2014-03-12 08:00 | 2014-03-24 16:00 | N | N | oil pumping station upgrades at 987S Clover Bar | Line |  |  | For Information Only
EPCOR | 511s Victoria T2 (511s Victoria),Victoria V722 (Victoria),Victoria V723 (Victoria) | 2014-03-12 08:00 | 2014-03-14 15:00 | N | N | VDS6 repair | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 77s 552 (77s Sagitawah) | 2014-03-12 08:00 | 2014-03-12 14:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 1036L (370s North Lethbridge - 356s Milo) | 2014-03-12 08:00 | 2014-03-28 12:00 | N | Y | re-terminate at 554s Travers - BSR | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2014-03-12 08:00 | 2014-03-12 17:00 | N | N | 71s726W switch repairs | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 410s 952 (410s Josephburg) | 2014-03-12 08:00 | 2014-03-12 15:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2014-03-12 08:00 | 2014-03-24 16:00 | N | N | oil pumping station upgrades at 987S Clover Bar | Line |  |  | For Information Only
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),Z31 PT | 2014-03-12 08:00 | 2014-03-14 16:00 | N | N | Z31 equipment outage, remove jumpers on CT wires, substation washing | Transformer, Line, Terminal Equipment |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 840s 509 (840s McNeill) | 2014-03-12 10:00 | 2014-03-12 12:00 | N | N | breaker repair | Circuit Breaker |  |  | Limits ATC
EPCOR | Garneau G724 (Garneau) | 2014-03-12 12:30 | 2014-03-12 16:00 | N | N | P&C relay maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | 814s B2401 (814s Bellamy) | 2014-03-13 08:00 | 2014-03-13 15:00 | N | N | SF6 gas testing and pressure maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 77s T1 (77s Sagitawah),77s 51 (77s Sagitawah),77s 26 (77s Sagitawah),77s 14 (77s Sagitawah) | 2014-03-13 08:00 | 2014-03-13 17:00 | N | Y | switch repairs | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 202L (178s Cynthia - 202AL tap),178s 202X (178s Cynthia) | 2014-03-13 08:00 | 2014-03-13 14:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 708L (71s Lamoureux - 708L88X),71s 852 (71s Lamoureux),71s 752 (71s Lamoureux) | 2014-03-13 08:00 | 2014-03-13 14:00 | N | N | switch hot spot repair | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 68s T2 (68s Willesden Green) | 2014-03-13 08:00 | 2014-03-14 17:00 | N | N | install bus bird coverup | Transformer |  |  | 240 kV
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2014-03-13 08:00 | 2014-03-13 12:00 | N | N | substation washing | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 25B240-D139 (ENMAX 25),ENMAX 25 B240-D138 (ENMAX 25) | 2014-03-13 08:00 | 2014-03-14 16:00 | N | N | SW/MD maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
SUNCOR | 29EDD-94 952-9705 (29EDD-94) | 2014-03-13 09:00 | 2014-03-13 19:00 | N | N | low gas pressure alarm - emergency repair | Circuit Breaker |  |  | 240 kV
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2014-03-14 08:00 | 2014-03-14 15:00 | N | N | replacing structure # 116 | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 102s R7 (102s Langdon) | 2014-03-14 11:00 | 2014-04-28 07:00 | N | Y | move reactors from 102s to 520s - affects 1201L reclosing - WATL | Shunts |  |  | Over/Under Voltage, 500 kV
ALTALINK | 41s T11 (41s Medicine Hat) | 2014-03-15 07:00 | 2014-03-20 17:00 | N | N | maintenance | Transformer |  |  | Pre-Condition
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville) | 2014-03-15 07:30 | 2014-03-26 18:00 | N | N | 7l24 outage to install switches for Bear Trap sub | Line |  |  | Creates Radial Feeds
ALTALINK | 216s T3 (216s Knightsbridge) | 2014-03-15 08:00 | 2014-03-21 16:00 | N | N | Commissioning - ISD = March 18, 2014 | Transformer
ENMAX | 23.1TR (ENMAX 23),23.2TR (ENMAX 23),23.3TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2014-03-15 08:00 | 2014-03-15 16:00 | N | N | Substation Washing | Line, Transformer
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2014-03-15 08:30 | 2014-03-16 17:00 | N | N | line washing & cross arm repair | Line |  |  | Overload, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2014-03-16 08:00 | 2014-03-16 16:00 | N | N | substation washing | Transformer, Shunts, Line |  |  | Limits ATC
ALTALINK | 310p 452 (310p Sundance) | 2014-03-17 07:30 | 2014-03-17 12:00 | N | Y | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 310p452. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 77s 14 (77s Sagitawah) | 2014-03-17 07:30 | 2014-03-17 12:00 | N | Y | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 77s14. | Circuit Breaker |  |  | 240 kV
ENMAX | ENMAX 25 240kV South Bus | 2014-03-17 08:00 | 2014-03-20 16:00 | N | Y | SW/MD maintenance (151, 150, 149, 145, 137, 131) | Bus |  |  | 240 kV
EPCOR | NamaoT1 (Namao) | 2014-03-17 08:00 | 2014-03-21 14:00 | N | N | 72Kv Bus reconfiguration NDS8 Switch move | Transformer |  |  | For Information Only
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2014-03-17 08:00 | 2014-03-17 16:00 | N | N | GIS SW maintenance | Line
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2014-03-17 09:00 | 2014-03-17 12:00 | N | N | High Load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (526L367 - 526L418) | 2014-03-17 10:00 | 2014-03-21 15:00 | N | N | replacing structures, crossarms | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 48 (77s Sagitawah) | 2014-03-17 12:30 | 2014-03-17 17:00 | N | Y | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 77s48. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 552 (310p Sundance) | 2014-03-17 12:30 | 2014-03-17 17:00 | N | Y | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 310p552 | Circuit Breaker |  |  | 240 kV
ALTALINK | 89s 1552 (89s Ellerslie) | 2014-03-17 13:00 | 2014-03-18 14:00 | N | Y | 240kV Breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),1.81L (ENMAX 20 - ENMAX 1) | 2014-03-17 15:00 | 2014-03-17 17:00 | N | N | pothead washing | Line |  |  | Overload, Firm Load Loss
ATCO | 7L51 (788s Hotchkiss - A793s West Peace River) | 2014-03-18 07:30 | 2014-03-18 18:00 | N | N | to cut in 927s Buchanan Creek | Line |  |  | For Information Only
ALTALINK | 216s T2 (216s Knightsbridge),705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2014-03-18 08:00 | 2014-03-21 05:00 | N | N | connect new T3 to 216s | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 26 (77s Sagitawah) | 2014-03-18 08:00 | 2014-03-18 12:00 | N | N | circuitry work at breaker cabinet 77s26 | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 310p 2752 (310p Sundance) | 2014-03-18 08:00 | 2014-03-18 12:00 | N | Y | circuitry work at breaker cabinet 310p2752 | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 77s 29 (77s Sagitawah) | 2014-03-18 13:00 | 2014-03-18 17:00 | N | Y | circuitry work at breaker cabinet 77s29 | Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 310p 2652 (310p Sundance) | 2014-03-18 13:00 | 2014-03-18 17:00 | N | Y | circuitry work at breaker cabinet 310p2652 | Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2014-03-19 08:00 | 2014-03-23 16:00 | N | N | remove underground portion of cable and pot heads replace with overhead | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2014-03-19 08:00 | 2014-03-28 16:00 | N | N | P&C upgrades on J724 breaker at Jasper | Line
ENMAX | 1.5TR (ENMAX 1) | 2014-03-19 08:00 | 2014-03-21 16:00 | N | N | switch maintenance and transformer repairs | Transformer
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2014-03-19 08:00 | 2014-03-20 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-03-19 08:00 | 2014-03-19 16:00 | N | N | heater repairs D84 | Circuit Breaker |  |  | Contingency Requires Mitigation
TRANSALTAW | 418s Ardenville | 2014-03-19 08:00 | 2014-03-19 14:00 | N | Y | power pole replacement | Station |  |  | Restricts Generation
ALTALINK | 151s T2 (151s Strathmore) | 2014-03-19 08:00 | 2014-03-20 17:00 | N | N | transformer leak from conservator piping | Transformer
ATCO | 826s 502R (826s Marguerite Lake) | 2014-03-19 08:00 | 2014-03-31 16:00 | N | N | forced outage due to breaker linkage problems | Shunts
ALTALINK | 535s 6452 (535s Joffre) | 2014-03-19 09:00 | 2014-03-19 17:00 | N | N | heater replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2014-03-19 13:00 | 2014-03-19 15:00 | N | N | pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2014-03-19 15:00 | 2014-03-19 17:00 | N | N | pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-03-20 08:00 | 2014-03-20 16:00 | N | N | heater repairs D81 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 87s 152 (87s Gaetz) | 2014-03-20 08:00 | 2014-03-20 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 77s 26 (77s Sagitawah) | 2014-03-20 09:00 | 2014-03-21 17:00 | N | Y | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 77s26 | Circuit Breaker |  |  | 240 kV
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2014-03-21 08:00 | 2014-03-21 15:00 | N | N | straightening structure # 57 & replacing cross-arm | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO | 983L (244S Bowmanton - 251S Whitla),964L (244s Bowmanton - 251s Whitla) | 2014-03-22 08:00 | 2014-03-28 16:00 | N | N | ISD: March 25, 2014 | Line
Alberta Newspri | Alberta Newsprint Generators | 2014-03-22 08:00 | 2014-05-11 16:00 | N | N | commissioning, 10 x 6.5 MW generators, in service date: March 28, 2014 | Unit
EPCOR | 746AL (524s Fiberglass - 746L tap) | 2014-03-23 07:00 | 2014-03-23 11:00 | N | N | E524s Epcor Maintenance | Line
EPCOR | 524S Fiberglas | 2014-03-23 07:00 | 2014-03-23 11:00 | N | N | maintenance | Station
ALTALINK | 250p11 (250p Bighorn) | 2014-03-23 08:00 | 2014-03-23 12:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn) | 2014-03-23 12:00 | 2014-03-23 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | NamaoT2 (Namao) | 2014-03-24 08:00 | 2014-03-28 16:00 | N | N | 72 kV bus reconfiguration NDS10 switch move | Transformer
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2014-03-24 08:00 | 2014-03-28 16:00 | N | N | remove underground portion of cable and pot heads replace with overhead | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-03-24 08:00 | 2014-03-26 16:00 | N | Y | switch maintenance & doble | Line
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2014-03-24 08:00 | 2014-03-27 17:00 | N | N | line maintenenance | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2014-03-24 08:00 | 2014-03-25 16:00 | N | N | switch maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L46 (932s Pemukan - 959s Lanfine) | 2014-03-24 08:00 | 2014-03-26 18:00 | N | Y | forced outage | Line |  |  | 240 kV, For Information Only
EPCOR | 557s T1 (557s Castle Downs) | 2014-03-24 08:00 | 2014-03-30 16:00 | N | Y | P&C bus differential replacement | Transformer |  |  | 240 kV, For Information Only
ATCO | 7L14 (710s Vermilion - 751s Hill),710s 702 (710s Vermilion) | 2014-03-24 09:00 | 2014-03-28 14:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2014-03-24 10:00 | 2014-03-27 15:00 | N | Y | conductor repair | Line |  |  | 240 kV, Pre-Condition, Overload
ATCO | 7L86 (822s Wolf Lake - 877s Foster Creek) | 2014-03-25 07:00 | 2014-03-25 18:00 | N | N | breaker maintenance in conjunction with RAS scheme commissioning | Line |  |  | Restricts Generation
EPCOR | 511s Victoria T2 (511s Victoria) | 2014-03-25 08:00 | 2014-03-26 16:00 | N | N | SFRA maintenance testing | Transformer |  |  | For Information Only
ALTALINK | 17s 6 (17s Benalto) | 2014-03-25 08:00 | 2014-03-27 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 720L (347s Fox Creek - 397s Benbow),347s 720X (347s Fox Creek) | 2014-03-25 08:30 | 2014-03-25 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 844s 702T (844s AEC Mill) | 2014-03-26 07:00 | 2014-03-27 07:00 | N | N | to gather oil samples | Transformer |  |  | For Information Only
ATCO | 844s 701T (844s AEC Mill) | 2014-03-26 07:00 | 2014-03-27 07:00 | N | N | gather oil samples | Transformer |  |  | For Information Only
ENMAX | 1.83L (ENMAX 1 - ENMAX 8) | 2014-03-26 08:00 | 2014-03-28 16:00 | N | N | maintenance of 3a2, 3a01 & 3a8 | Line
ALTALINK | 62s11 (62s Brazeau) | 2014-03-26 23:00 | 2014-03-27 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2014-03-27 03:00 | 2014-03-27 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 77s 51 (77s Sagitawah) | 2014-03-27 07:30 | 2014-03-27 13:00 | N | Y | functional trips to this breaker from 919/989L RAS | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 805s J2401 (805s Jasper) | 2014-03-27 08:00 | 2014-03-27 16:00 | N | Y | breaker fail installation | Circuit Breaker |  |  | 240 kV
ALTALINK | 77s T2 (77s Sagitawah) | 2014-03-27 08:00 | 2014-03-28 16:00 | N | Y | T2 Maintenance | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 283s C1 (283s Violet Grove),283s 31 (283s Violet Grove) | 2014-03-27 08:00 | 2014-03-27 14:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ENMAX | 9.1TR (ENMAX 9),9.2TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2014-03-27 08:00 | 2014-03-27 14:00 | N | Y | Substation Washing | Line, Transformer
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2014-03-27 08:00 | 2014-03-27 12:00 | N | Y | replacing rotten crossarms | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2552 (310p Sundance) | 2014-03-27 08:30 | 2014-03-27 09:00 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 848L (17s Benalto - 848L490E),17s 848X (17s Benalto) | 2014-03-27 09:00 | 2014-03-27 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 54 (77s Sagitawah) | 2014-03-27 09:00 | 2014-03-27 10:30 | N | Y | functional trips to this breaker from 919/989L RAS | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 77s 552 (77s Sagitawah) | 2014-03-27 10:30 | 2014-03-27 12:00 | N | Y | functional trips to this breaker from 919/989L RAS | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 1652 (310p Sundance) | 2014-03-27 11:00 | 2014-03-27 11:30 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1352 (310p Sundance) | 2014-03-27 12:00 | 2014-03-27 12:30 | N | N | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 172L (15s Fort Macleod - 172L1251),15s 172E (15s Fort Macleod) | 2014-03-27 12:00 | 2014-03-27 17:00 | N | Y | functional test as part of WAGF RAS | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 652 (77s Sagitawah) | 2014-03-27 12:30 | 2014-03-27 14:00 | N | Y | functional trips to this breaker from 19/989L RAS | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 310p 1052 (310p Sundance) | 2014-03-27 13:00 | 2014-03-27 13:30 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 752 (310p Sundance) | 2014-03-27 14:00 | 2014-03-27 14:30 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 77s 752 (77s Sagitawah) | 2014-03-27 14:00 | 2014-03-27 15:30 | N | N | functional trips to this breaker from 919/989L RAS | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 452 (310p Sundance) | 2014-03-27 15:00 | 2014-03-27 15:30 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 152 (310p Sundance) | 2014-03-27 16:00 | 2014-03-27 16:30 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2852 (310p Sundance) | 2014-03-27 17:00 | 2014-03-27 17:30 | N | Y | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 16.63L (ENMAX 16 - ENMAX 36) | 2014-03-28 08:00 | 2014-05-21 16:00 | N | N | forced outage due to a cable failure | Line
EPCOR | 805s J2403 (805s Jasper) | 2014-03-28 08:00 | 2014-03-28 16:00 | N | Y | breaker fail installation | Circuit Breaker |  |  | 240 kV
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2014-03-28 08:00 | 2014-03-28 10:00 | N | Y | trip test to 310p2052, energize new 310p1952 & CTs | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
Saskpower | BE906T | 2014-03-28 08:00 | 2014-03-28 15:00 | N | Y | maintenance | Transformer |  |  | Limits ATC
ALTALINK | 310p 2252 (310p Sundance) | 2014-03-28 08:00 | 2014-03-28 08:30 | N | N | trip test from 310p1952 new breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | SW909 | 2014-03-28 10:00 | 2014-03-28 14:00 | N | Y | maintenance | Circuit Breaker |  |  | Limits ATC
Saskpower | BE906T | 2014-03-29 06:00 | 2014-03-29 10:00 | N | Y | replace oil switch and find ground fault | Transformer |  |  | Limits ATC
ATCO | 927S Buchanan Creek | 2014-03-29 08:00 | 2014-04-04 18:00 | N | N | Commissioning - ISD = April 1, 2014 | Station
ATCO | Foster Creek & Primrose RAS update | 2014-03-29 08:00 | 2014-04-04 16:00 | N | N | Commissioning- ISD= April 1 | Terminal Equipment
ATCO | 940S Beartrap | 2014-03-29 08:00 | 2014-04-04 16:00 | N | N | Comissioning - ISD = April 1, 2014 | Station
BSRW | Blackspring Ridge | 2014-03-29 08:00 | 2014-04-04 16:00 | N | N | Commissioning- ISD = March 31, 2014 | Unit
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2014-03-29 08:00 | 2014-03-31 16:00 | N | Y | remove temporary bypass - BSR | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 557s T2 (557s Castle Downs) | 2014-03-31 08:00 | 2014-04-06 16:00 | N | Y | P&C bus differential replacement | Transformer |  |  | 240 kV
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2014-03-31 08:00 | 2014-03-31 17:00 | N | N | hot work on the 25 kV Bus | Line |  |  | Firm Load Loss
ENMAX | 162s 240-136 (162s Beddington) | 2014-03-31 08:00 | 2014-04-01 16:00 | N | Y | dashpot maint on 162B240-RB136 | Circuit Breaker |  |  | 240 kV
EPCOR | 511s Victoria T1 (511s Victoria) | 2014-03-31 08:00 | 2014-04-01 16:00 | N | N | Repair VDS4 & VDS5 Plus Trans testing | Transformer
EPCOR | Namao N722 (Namao) | 2014-03-31 08:00 | 2014-04-27 17:00 | N | N | breaker replacement | Circuit Breaker
EPCOR | 805s C1 (805s Jasper),805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2014-03-31 08:00 | 2014-03-31 17:00 | N | Y | Breaker Fail Installation | Transformer, Shunts, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 667L (370s North Lethbridge - 146s Lethbridge MacDonald),370s 75 (370s North Lethbridge) | 2014-03-31 08:00 | 2014-03-31 16:00 | N | Y | impedance testing | Line, Switch |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 896L (19s Wabamun - 432s Carvel),432s 896 (432s Carvel) | 2014-03-31 10:00 | 2014-03-31 17:00 | N | Y | 138kV Breaker Maintenance | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2014-03-31 16:00 | 2014-05-30 16:00 | N | N | contractor digging under line | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2014-03-31 16:01 | 2014-04-04 17:00 | N | N | switch replacement JDS15, JDS16, & JDS21 | Transformer, Line |  |  | 240 kV
ALTALINK | 344s T2 (344s Warner) | 2014-04-01 08:00 | 2014-04-03 17:00 | N | N | replace UG cables on low side of T2 | Transformer |  |  | For Information Only
ALTALINK | 739L (434s Stony Plain - 432s Carvel),432s 739 (432s Carvel) | 2014-04-01 08:00 | 2014-04-01 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),36B138-36BT3 (ENMAX 36),36PT138-Z32 (ENMAX 36),69 KV PT (ENMAX 36) | 2014-04-01 08:00 | 2014-04-01 16:00 | N | N | Repair SW 84 @ 36 sub | Line, Circuit Breaker, Terminal Equipment, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 7L129 (526s Buffalo Creek - 918s Bauer),526s 152 (526s Buffalo Creek) | 2014-04-01 08:30 | 2014-04-01 17:00 | N | N | replace tank heater | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 149s C1 (149s Nisku),149s T1 (149s Nisku),858L (149s Nisku - 40s Wetaskiwin) | 2014-04-01 09:00 | 2014-04-01 17:00 | N | N | T1 bushing check & 149s1 mech repairs | Line, Transformer, Shunts |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville) | 2014-04-01 09:00 | 2014-04-01 11:00 | N | N | prepare for 940s Bear Trap substation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 650s T1 (650s Hansman Lake) | 2014-04-01 09:00 | 2014-04-01 17:00 | N | N | 650s70 replace Latch | Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 719L (575s Sundre - 378s Shell Caroline),575s 719N (575s Sundre) | 2014-04-01 13:00 | 2014-04-01 15:30 | N | N | 719L TPR work | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-04-02 08:00 | 2014-04-03 16:00 | N | N | factory rep site visit for heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 1.6TR (ENMAX 1) | 2014-04-02 08:00 | 2014-04-02 16:00 | N | N | switch maintenance on 1-5A101, 1-5a91, 1-5a92, 1-6a101, 1-6a16 | Transformer
ALTALINK | 137S Sedgewick | 2014-04-02 08:00 | 2014-04-02 12:00 | N | N | switch repairs on the 25kV breaker | Station
ALTALINK | 410s T1 (410s Josephburg) | 2014-04-02 08:00 | 2014-04-03 16:00 | N | Y | replace 138kV CT on T1 secondary | Transformer |  |  | 240 kV, For Information Only
ATCO | 9L55 (885s McMillan - 852s Round Hill) | 2014-04-02 09:00 | 2014-04-05 16:00 | N | Y | forced outage | Line |  |  | Restricts Generation, For Information Only
ALTALINK | 149s C1 (149s Nisku),604L (149s Nisku - 155s Blackmud),780L (38s East Edmonton - 149s Nisku),149s Nisku 138kV North Bus | 2014-04-02 09:00 | 2014-04-02 17:00 | N | N | switch hot spots | Bus, Line, Shunts |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 421s C1 (421s Hays) | 2014-04-02 09:00 | 2014-04-02 17:00 | N | Y | leak investigation | Shunts |  |  | For Information Only
ALTALINK | 155S Blackmud | 2014-04-02 09:00 | 2014-04-02 14:00 | N | N | outage on a 25kV U/G cable for bus hot spots repair | Station
ATCO | 7L51 (788s Hotchkiss - A793s West Peace River) | 2014-04-02 10:00 | 2014-04-02 12:00 | N | N | testing protection relay settings on 21A and 67N at 793s | Line
EPCOR | 511s Victoria T2 (511s Victoria) | 2014-04-02 12:00 | 2014-04-03 16:00 | N | N | repair VDS6 & VDS7 Plus Trans testing | Transformer
SUNCOR | 29PL7-8 (29EDD-85 - 29EDD-160),29PL7-7 (29EDD-85 - 29EDD-160) | 2014-04-03 07:00 | 2014-04-04 20:00 | N | N | energizining new line | Line
ALTALINK | 478s T1 (478s Tucuman) | 2014-04-03 08:00 | 2014-04-04 17:00 | N | N | TC leaking from lid | Transformer
ALTALINK | 189L (373s Madden - 189L2) | 2014-04-03 08:00 | 2014-04-08 16:00 | N | N | urgent trouble corrective conductor repair and structure replacement | Line
ATCO | 7L92 (777s Vilna - 7L92D2) | 2014-04-03 08:00 | 2014-04-03 16:00 | N | N | install microwave tower in Whitby Lake substation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2014-04-03 08:00 | 2014-04-03 12:00 | N | N | remove ravens nest on bus | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s 1752 (275s Jenner) | 2014-04-03 08:00 | 2014-04-03 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2014-04-05 08:00 | 2014-04-05 16:00 | N | N | Install corona rings | Line
ALTALINK | 38s T4 (38s East Edmonton) | 2014-04-05 09:00 | 2014-04-06 17:00 | N | Y | replace breaker control module on 38s18 | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 2 - 2.83L tap),2.83L (ENMAX 13 - 2.83L tap) | 2014-04-06 08:00 | 2014-04-08 16:00 | N | N | 5s rebuild, New location of 2.83L feeds 5.9, 5.10. | Line |  |  | Overload
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2014-04-06 08:00 | 2014-04-27 16:00 | N | N | ECTP 2s build new 2.80L from 2s - 23s | Line |  |  | For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-04-07 02:00 | 2014-04-07 04:00 | N | N | high load move | Line |  |  | Pre-Condition
EPCOR | 72RG7 (Rossdale - Garneau) | 2014-04-07 07:00 | 2014-04-11 19:00 | N | N | de-gassing cable oil | Line
ALTALINK | 305s T2 (305s Acheson),712L (99s North St. Albert - 305s Acheson),739L (305s Acheson - 434s Stony Plain),305s Acheson 138 kV West Bus | 2014-04-07 08:00 | 2014-04-08 17:00 | N | N | replace 305s1, create open point 'A', repair 305s24 hotspot | Line, Transformer, Bus |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s Bowmanton 240 kV Bus 1 | 2014-04-07 08:00 | 2014-04-10 13:00 | N | N | civil construction in proximity to 240kV bus 2 | Bus |  |  | 240 kV
ALTALINK | 133S Stelco Edmonton | 2014-04-07 08:00 | 2014-04-10 12:00 | N | N | customer request | Station
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2014-04-07 08:00 | 2014-04-07 16:00 | N | N | Substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 765L (74s Janet - 151s Strathmore) | 2014-04-07 08:00 | 2014-04-11 17:00 | N | N | install CVT & synchronizer on 151s765W | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2014-04-07 08:00 | 2014-04-08 16:00 | N | N | Repair VDS8 Switch | Line
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2014-04-07 08:00 | 2014-04-08 16:00 | N | N | maintenance on SW 8-5a01, 8-5a10, 8-5a2, 8-5a51, 8-5a52, 8-5a8, 8-6a1, 8-6a51, 8-6a52 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 757s 701T (757s Battle River) | 2014-04-07 08:00 | 2014-04-11 17:00 | N | N | install new setting | Transformer
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat),41s 880 (41s Medicine Hat) | 2014-04-07 11:00 | 2014-04-08 17:00 | N | Y | 138kV Breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 789s 701 (789s Keg River) | 2014-04-07 11:00 | 2014-04-08 13:00 | N | N | perform breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 72s 852 (72s Leismer) | 2014-04-07 14:00 | 2014-04-08 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 17s 9 (17s Benalto) | 2014-04-08 08:00 | 2014-04-10 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 773L (127s Bruderheim - 308s Albchem Beaverhill Creek),127s 773W (127s Bruderheim) | 2014-04-08 08:00 | 2014-04-08 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 216s T3 (216s Knightsbridge) | 2014-04-08 08:00 | 2014-04-08 17:00 | N | N | install new ground resistor bushing cover | Transformer |  |  | For Information Only
ATCO | 6L79 (711s Willingdon - 709s Vegreville),6L79 (711s Willingdon - 707s St.Paul) | 2014-04-08 08:00 | 2014-04-12 17:00 | N | N | 6L79 o/s to install temp bypass | Line |  |  | Affects Visibility, Firm Load Loss, Creates Radial Feeds
ALTALINK | 28s 41 (28s West Brooks) | 2014-04-08 08:00 | 2014-04-10 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 790s 704 (790s Poplar Hill) | 2014-04-08 10:30 | 2014-04-08 14:30 | N | Y | low SF6 gas | Circuit Breaker |  |  | Restricts Generation
Saskpower | SaskPower V57R (MH) | 2014-04-08 12:00 | 2014-04-09 08:00 | N | Y | maintenance | Line |  |  | Limits ATC
ATCO | 789s 702 (789s Keg River) | 2014-04-08 13:00 | 2014-04-09 16:00 | N | N | maintenance and testing | Circuit Breaker |  |  | Pre-Condition, For Information Only
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2014-04-08 16:01 | 2014-04-29 16:00 | N | N | 5s rebuild, New location of 2.83L feeds 5.9, 5.10. | Line |  |  | For Information Only
ALTALINK | 305s C1 (305s Acheson),739L (14s Devon - 305s Acheson),305s Acheson 138 kV East Bus | 2014-04-09 06:00 | 2014-04-15 08:00 | N | Y | replace 305s3 & 305s4, repair 305s23 hotspot | Line, Bus, Shunts |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s T2 (275s Jenner) | 2014-04-09 08:00 | 2014-04-11 17:00 | N | Y | transformer and switch maintenance | Transformer |  |  | 240 kV
EPCOR | E511s VictoriaT3 (511s Victoria) | 2014-04-09 08:00 | 2014-04-10 16:00 | N | N | repair VDS11 Switch | Transformer
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2014-04-09 08:00 | 2014-04-10 16:00 | N | N | maintenance on SW 8-1a52, 8-1a8, 8-1a1 | Line
ALTALINK | 818s C2 (818s Winefred) | 2014-04-09 09:00 | 2014-04-09 17:00 | N | Y | investigate C2 Alarm | Shunts |  |  | For Information Only
ALTALINK | 71s 852 (71s Lamoureux) | 2014-04-09 09:00 | 2014-04-10 17:00 | N | N | 138kV Breaker Maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162s 240-RB135 (162s Beddington) | 2014-04-09 17:30 | 2014-07-24 18:10 | N | Y | forced outage due to safety concern | Circuit Breaker |  |  | 240 kV
ALTALINK | 127s 815N (127s Bruderheim),815L (13s Deerland - 127s Bruderheim) | 2014-04-10 08:00 | 2014-04-10 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-04-10 08:00 | 2014-04-11 16:00 | N | N | factory rep site visit for heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 405s C1 (405s Waupisoo),405s 17 (405s Waupisoo) | 2014-04-10 08:00 | 2014-04-10 12:00 | N | Y | cap bank blown fuse | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 244s Bowmanton 240 kV Bus 2 | 2014-04-10 14:00 | 2014-04-15 17:00 | N | Y | civil construction in proximity to 240 kV bus 2 | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 28s 55 (28s West Brooks) | 2014-04-11 08:00 | 2014-04-11 13:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 39s T2 (39s Bickerdike),39s Bickerdike 138kV Bus 2 | 2014-04-11 08:00 | 2014-04-11 13:00 | N | Y | fix SS2 PT bolts on head | Bus, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B),54s 706N (54s Fort Saskatchewan) | 2014-04-11 09:00 | 2014-04-11 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2014-04-11 09:30 | 2014-04-11 17:00 | N | N | 56s633 138kV breaker maintenance | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (28s West Brooks - 763L257A) | 2014-04-11 13:00 | 2014-04-11 17:00 | N | N | 28s14 138kV switch maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 757s 701 (757s Battle River) | 2014-04-11 17:00 | 2014-05-05 08:00 | N | N | replacement | Circuit Breaker
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2014-04-13 08:00 | 2014-04-17 17:00 | N | N | install temporary bypass | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 911L RAS,180L RAS,911L (59s Peigan - ENMAX 65),853L RAS | 2014-04-13 12:00 | 2014-04-13 13:00 | N | Y | test RAS system | Line, RAS |  |  | 240 kV, Limits ATC, Impacts RAS
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2014-04-14 08:00 | 2014-04-20 16:00 | N | N | oil pumping station upgrades and Mods | Line
ALTALINK | 77s 552 (77s Sagitawah) | 2014-04-14 08:00 | 2014-04-14 09:00 | N | N | functional trips to this breaker from 919/989L RAS | Circuit Breaker
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2014-04-14 08:00 | 2014-04-25 17:30 | N | N | line move from; STRs 66A - 71 | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | NamaoT1 (Namao) | 2014-04-14 08:00 | 2014-04-14 16:00 | N | N | doble SFRA testing | Transformer
EPCOR | Meadowlark T2 (Meadowlark) | 2014-04-14 08:00 | 2014-04-15 12:00 | N | N | relay maintenance | Transformer
EPCOR | 72RS5 (Rossdale - Strathcona) | 2014-04-14 08:00 | 2014-05-09 16:00 | N | N | replace RS724 breaker | Line
ALTALINK | 733L (151s Strathmore - 428S Namaka),151s 733E (151s Strathmore) | 2014-04-14 08:00 | 2014-04-17 17:00 | N | N | replace 733L 'A' protections | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 252 (77s Sagitawah) | 2014-04-14 09:15 | 2014-04-14 12:15 | N | N | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 77s252 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 746s T1 (746s Sherwood Park) | 2014-04-14 10:00 | 2014-04-16 17:00 | N | N | transformer doble, SFRA, leaks & T/C repair | Transformer
ALTALINK | 253s C1 (253s Blackie),161L (255s Vulcan - 253s Blackie),851L (525s Carseland - 253s Blackie),852L (253s Blackie - 504s Queenstown),253S Blackie 138 kV bus | 2014-04-14 10:00 | 2014-04-16 12:00 | N | Y | 138kV switch and breaker maintenance | Bus, Line, Shunts |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 6L37 (800s Friedenstal - 724s Hines Creek),800s 601 (800s Friedenstal) | 2014-04-14 10:00 | 2014-04-15 15:30 | N | N | complete 601 Partial PM and Contact Replacement | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 77s 452 (77s Sagitawah) | 2014-04-14 13:00 | 2014-04-14 16:30 | N | N | 919/989L RAS Scheme Sund.310p - circuitry work at breaker cabinet 77s452 | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 77s 652 (77s Sagitawah) | 2014-04-14 16:45 | 2014-04-14 18:00 | N | N | functional trips to this brk from 919/989L RAS | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2014-04-15 07:00 | 2014-04-15 17:00 | N | Y | circuitry work on 77s989X | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2014-04-15 08:00 | 2014-04-15 14:00 | N | Y | T2 transformer maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 63s 252 (63s Red Deer) | 2014-04-15 08:00 | 2014-04-15 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 8 (17s Benalto) | 2014-04-15 08:00 | 2014-04-15 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 337s T1 (337s Canada Liquidair),746BL (337s Canada Liquidair - 746DL17) | 2014-04-15 08:00 | 2014-04-15 17:00 | N | N | transformer & breaker maintenance | Transformer, Line
ALTALINK | 305s T2 (305s Acheson),712L (99s North St. Albert - 305s Acheson),739L (305s Acheson - 434s Stony Plain),305s Acheson 138 kV West Bus | 2014-04-15 08:01 | 2014-04-16 17:00 | N | N | close open point 'A' | Line, Bus, Transformer |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 122s T1 (122s Alberta Newsprint) | 2014-04-15 14:30 | 2014-04-15 18:30 | N | Y | T1 transformer maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 989L (310p Sundance - 77s Sagitawah) | 2014-04-15 18:00 | 2014-04-16 04:00 | N | Y | circuitry work on 77s989X | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 72LH8 (Hardisty - 803s Lambton) | 2014-04-15 18:00 | 2014-04-23 16:00 | N | N | line repair after pole fire (forced outage) | Line
ALTALINK | 61L (252s Jarrow - 61DL386),704L (252s Jarrow - 704L tap),704L (252s Jarrow - 7L50 tap) | 2014-04-16 07:00 | 2014-04-16 17:00 | N | N | 138kV PT replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 8.5TR (ENMAX 8),8.6TR (ENMAX 8) | 2014-04-16 08:00 | 2014-04-18 16:00 | N | N | GIS switch maintenance | Transformer
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2014-04-16 08:00 | 2014-04-16 16:00 | N | N | ENMAX: repair SW 81 at 20s | Line
TRANSALTA | 59s 952 (59s Peigan) | 2014-04-16 08:00 | 2014-04-16 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2014-04-16 08:00 | 2014-04-16 16:00 | N | N | repair SW 81 at 20s | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 733L (151s Strathmore - 428S Namaka),428s 733N (428s Namaka) | 2014-04-16 08:00 | 2014-04-16 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line
ALTALINK | 337s T2 (337s Canada Liquidair) | 2014-04-16 08:00 | 2014-04-16 17:00 | N | N | transformer & hydran work | Transformer
ALTALINK | 151s C1 (151s Strathmore),151s 44 (151s Strathmore) | 2014-04-16 08:00 | 2014-04-16 13:00 | N | Y | migrate breaker control, status, alarms to new SCADA RTU system | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),174L (197s Bardo - 395s North Holden),730L (197s Bardo - 730L61) | 2014-04-16 09:00 | 2014-04-16 14:00 | N | N | RTU replacement | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt) | 2014-04-16 09:00 | 2014-04-16 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | Meadowlark T2 (Meadowlark) | 2014-04-16 12:00 | 2014-04-17 16:00 | N | N | relay maintenance | Transformer
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2014-04-16 12:30 | 2014-04-16 16:00 | N | Y | L to J project: B2 bus construction expansion complete, close open point A, test energize(commission) new B2 bus | Transformer, Bus, Shunts |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 937L (102s Langdon - 74s Janet) | 2014-04-17 07:30 | 2014-05-02 09:00 | N | Y | move line from old 102s 240 kV Bus to new 102s 240 kV Bus - WATL | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Limits ATC
ALTALINK | 917L (74s Janet - 5s East Calgary) | 2014-04-17 15:00 | 2014-04-20 16:00 | N | Y | termination of new 23.80L | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2014-04-18 08:00 | 2014-04-29 16:00 | N | N | ENMAX 5s rebuild | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
BLACKSPRING | 485S Black Springs | 2014-04-21 08:00 | 2014-05-03 16:00 | N | N | DSATCOMS comissioning | Station |  |  | For Information Only
ENMAX | 16.2TR (ENMAX 16) | 2014-04-21 08:00 | 2014-05-02 16:00 | N | N | LTC & transformer maintenance, doble & test | Transformer
ENMAX | 2.81L (ENMAX 2 - ENMAX 9),ENMAX 9 B138-2.81 (ENMAX 9) | 2014-04-21 08:00 | 2014-04-21 16:00 | N | N | breaker maintenance | Circuit Breaker, Line
EPCOR | 557s 2406 (557s Castle Downs) | 2014-04-22 07:00 | 2014-06-14 16:00 | N | Y | P&C upgrades and commissioning | Circuit Breaker |  |  | 240 kV
AESO, ALTALINK | 983L (244S Bowmanton - 251S Whitla),964L (244s Bowmanton - 251s Whitla),251s SR1 (251s Whitla),251s SR2 (251s Whitla) | 2014-04-22 07:30 | 2014-04-23 17:30 | N | Y | move centre span off substation | Line, Shunts |  |  | 240 kV, For Information Only
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47) | 2014-04-22 08:00 | 2014-05-01 16:00 | N | N | maintenance | Transformer, Line |  |  | For Information Only
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2014-04-22 08:00 | 2014-05-01 16:00 | N | N | replace two structures on the sought side of 32s prior to spring runoff | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 99s T1 (99s North St. Albert),747L (99s North St. Albert - 747DL4) | 2014-04-22 08:00 | 2014-04-22 17:00 | N | N | move CT circuits to new bus protection and perform trip tests | Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 557s T1 (557s Castle Downs) | 2014-04-22 08:00 | 2014-04-22 09:30 | N | N | facilitate the isolation of C2406 Breaker | Transformer |  |  | 240 kV, For Information Only
ENMAX | 771L (162s Beddington - ENMAX 47) | 2014-04-22 08:00 | 2014-04-23 16:00 | N | N | maintenance and wash | Line |  |  | For Information Only
EPCOR | NamaoT1 (Namao) | 2014-04-22 08:00 | 2014-04-22 16:00 | N | N | doble SFRA testing | Transformer |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper) | 2014-04-22 08:00 | 2014-04-25 16:00 | N | Y | CVT replacement | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 63s T1 (63s Red Deer) | 2014-04-22 10:00 | 2014-04-22 17:00 | N | Y | 240 kV transformer maintenance | Transformer |  |  | 240 kV
ALTALINK | 727L (65s High River - 727L39S),65s 727N (65s High River) | 2014-04-22 11:00 | 2014-04-23 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (28s West Brooks - 158s Vauxhall),83s 763N (83s Taber) | 2014-04-22 11:00 | 2014-04-22 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 310p 2752 (310p Sundance) | 2014-04-22 13:00 | 2014-04-24 17:00 | N | Y | 240kV breaker maintenance & CT doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-04-23 01:30 | 2014-04-23 03:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2014-04-23 07:00 | 2014-04-25 18:00 | N | N | install mono pole screw pile foundations for 712L/ & future 677L | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 1201L (102s Langdon - BCH),1113L (102s Langdon - 520s Bennett) | 2014-04-23 07:30 | 2014-04-24 18:00 | Y | Y | terminate 1113AL at new Langdon, string 937L over 1113L - WATL | Line |  |  | Limits ATC, 500 kV
EPCOR | Namao N721 (Namao),Namao N722 (Namao) | 2014-04-23 08:00 | 2014-04-23 16:00 | N | N | relay op checks required and re-energize the CVTs | Circuit Breaker
EPCOR | 511s Victoria T2 (511s Victoria) | 2014-04-23 08:00 | 2014-04-24 16:00 | N | N | SFRA testing and doble test | Transformer
ALTALINK | 42s 80 (42s Sarcee) | 2014-04-23 08:00 | 2014-04-23 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker
ATCO | 9L990 (72s Leismer - 2049s Kettle River) | 2014-04-23 08:00 | 2014-04-29 12:00 | N | Y | connect new 9L990/0L45 in/out to Kettle sub | Line |  |  | 240 kV, Restricts Generation, Creates Radial Feeds
ALTALINK | 99s T2 (99s North St. Albert),712L (99s North St. Albert - 305s Acheson) | 2014-04-23 08:00 | 2014-04-23 17:00 | N | N | move CT circuits to new bus protection and perform trip tests | Line, Transformer |  |  | Creates Radial Feeds
ATCO | 741s 702T (741s Fox Creek) | 2014-04-23 08:00 | 2014-04-23 12:00 | N | N | repair oil leak (urgent) | Transformer
EPCOR | 746AL (524s Fiberglass - 746L tap) | 2014-04-24 07:00 | 2014-04-24 13:00 | N | N | maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 746AL (524s Fiberglass - 746L tap) | 2014-04-24 07:00 | 2014-04-24 13:00 | N | N | E524s Epcor maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz),87s 1252 (87s Gaetz) | 2014-04-24 07:30 | 2014-04-24 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload
Saskpower | Sask Power AS904T | 2014-04-24 08:00 | 2014-04-25 18:00 | N | Y | maintenance | Transformer |  |  | Limits ATC, For Information Only
ALTALINK | 746L (746DL8 - 746DL17) | 2014-04-24 08:00 | 2014-05-30 17:00 | N | N | opening jumpers on structure 18 on the 746DL17 side | Line |  |  | For Information Only
ALTALINK | 370s 56 (370s North Lethbridge) | 2014-04-24 08:00 | 2014-04-24 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 99s273X | 2014-04-24 08:00 | 2014-04-24 12:00 | N | N | move CT circuits to new bus protection and perform trip test at 25kV | Terminal Equipment
ALTALINK | 256s C1 (256s Harmattan),256s 53 (256s Harmattan) | 2014-04-24 08:00 | 2014-04-24 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Shunts
ALTALINK | 258s 252 (258s Dow Hydrocarbons) | 2014-04-24 09:00 | 2014-04-24 11:00 | N | N | Investigate breaker low gas alarm | Circuit Breaker
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2014-04-25 07:30 | 2014-04-25 10:00 | N | N | emergency top up SF6 gas | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 108s T1 (108s Amelia) | 2014-04-25 09:00 | 2014-04-25 17:00 | N | Y | doble & maintenance on T1 - TX18716 | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 703L (213s Hughenden - 703AL tap) | 2014-04-25 10:00 | 2014-04-25 14:00 | N | N | repair handle on switch and operate to ensure proper operation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 611L (391S Balzac - 186s Dry Creek),391s 611 (391s Balzac) | 2014-04-25 14:00 | 2014-04-26 18:00 | N | N | leaking breaker (emergency) | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
TRANSCANADA | BCR2 Bear Creek Cogen Plant | 2014-04-26 08:00 | 2014-05-02 16:00 | N | N | MC increase - ISD= April 29, 2014 | Unit
ALTALINK | 38s C1 (38s East Edmonton),38s C2 (38s East Edmonton),38s T1 (38s East Edmonton),215L (38s East Edmonton - 286s Yasa),731L (38s East Edmonton - 420s Broadmoor),737L (95s Imperial Oil Edmonton - 38s East Edmonton),38s East Edmonton 138 kV Bus 1,38s East Edmonton 240 kV Bus 1 | 2014-04-26 08:00 | 2014-04-27 17:00 | N | Y | replace 38s31 | Transformer, Bus, Line, Shunts |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
AESO-SC | Minimum Acceptable Voltage Determination | 2014-04-26 08:00 | 2014-06-30 16:00 | N | N |  | SCInternal
ALTALINK | 763L (28s West Brooks - 158s Vauxhall) | 2014-04-27 08:00 | 2014-05-05 18:00 | N | N | connect new substation 257s(Hull) | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2407 (805s Jasper) | 2014-04-28 07:00 | 2014-04-28 16:00 | N | Y | dashpot repair | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 511s Victoria T2 (511s Victoria) | 2014-04-28 07:00 | 2014-04-28 16:00 | N | N | SFRA tests and Doble | Transformer |  |  | For Information Only
ALTALINK | 1201L (102s Langdon - BCH) | 2014-04-28 07:30 | 2014-05-01 18:00 | Y | Y | re-terminate 1201L at 520s (permanent) - WATL | Line |  |  | Pre-Condition, Limits ATC, 500 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2014-04-28 07:30 | 2014-05-01 18:00 | N | Y | annual equipment maintenance checks/activities | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2014-04-28 08:00 | 2014-05-02 17:00 | N | N | Install 3 new CTs /PTs for metering purposes | Transformer
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37) | 2014-04-28 08:00 | 2014-05-06 16:00 | N | N | advice for ENMAX: ECTP, Complete 37.82L rebuild at Janet. P & C upgrade | Line
ENMAX | 1.6TR (ENMAX 1) | 2014-04-28 08:00 | 2014-05-02 16:00 | N | N | PRD, oil samples(bushing/LTC), check reversing switch | Transformer
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37) | 2014-04-28 08:00 | 2014-05-07 09:00 | N | N | ECTP 23s | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary),5s C2 (5s East Calgary),5s 7 (5s East Calgary) | 2014-04-28 08:00 | 2014-05-02 16:00 | N | Y | ENMAX: pile installation underneath the overhead conductor | Circuit Breaker, Shunts |  |  | Limits ATC
ATCO | 706s Irish Creek RTU/SCADA | 2014-04-28 08:00 | 2014-05-02 12:15 | N | N | RTU upgrade and test | Terminal Equipment |  |  | Affects Visibility
ATCO | 707s 505C (707s St. Paul) | 2014-04-28 08:00 | 2014-04-28 12:00 | N | Y | removed from service for drilling piles. | Shunts |  |  | For Information Only
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),746BL (337s Canada Liquidair - 746DL17) | 2014-04-28 08:00 | 2014-05-30 17:00 | N | N | build a new portion line between 731L and 746BL,work on the piece of line between 746DL17 and 746BL tap | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 813s SVC (813s Little Smoky) | 2014-04-28 09:00 | 2014-04-30 17:00 | N | Y | maintenance | Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 64s T2 (64s East Crossfield),901AL (64s East Crossfield - 901L tap),64s 901 (64s East Crossfield) | 2014-04-28 11:00 | 2014-05-01 17:00 | N | Y | 240kV transformer and breaker maintenance | Circuit Breaker, Transformer, Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 3 (17s Benalto) | 2014-04-28 11:00 | 2014-04-30 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 852 (89s Ellerslie) | 2014-04-28 12:00 | 2014-05-01 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | E511s VictoriaT4 (511s Victoria) | 2014-04-29 07:00 | 2014-05-01 16:00 | N | N | SFRA tests and Doble Plus repair VDS13 | Transformer |  |  | For Information Only
ALTALINK | 151s T1 (151s Strathmore) | 2014-04-29 08:00 | 2014-04-29 16:00 | N | N | migrate breaker control, status, alarms to new SCADA RTU system, install new metering | Transformer
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge),370s 770E (370s North Lethbridge) | 2014-04-29 08:00 | 2014-04-29 10:00 | N | N | protection upgrade, trip testing | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ATCO | 2049S Kettle River,9L45 (856s Kinosis - 2049s Kettle River) | 2014-04-29 08:00 | 2014-05-03 16:00 | N | N | ISD: April 29 | Station, Line
ALTALINK | 69s T5 (69s North Barrhead) | 2014-04-29 08:00 | 2014-04-29 12:00 | N | N | T5 Doble | Transformer
ATCO | 700s 705C (700s Bonnyville),700s 706C (700s Bonnyville),700s 707C (700s Bonnyville) | 2014-04-29 08:00 | 2014-04-29 17:00 | N | Y | exercise and clean disconnect 700D3 to ensure that it is ok to carry all bypass load when 7L24 and 7L53 are tied together | Shunts |  |  | For Information Only
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2014-04-29 08:00 | 2014-04-30 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1115L (154s Black Spruce - 170s Pike),154s Black Spruce 240 kV Bus 2 | 2014-04-29 08:00 | 2014-05-03 17:00 | N | Y | bring in new 1115 line to existing 'A' frame in 154s | Bus, Line |  |  | 240 kV, For Information Only
EPCOR | Strathcona T1 (Strathcona) | 2014-04-29 08:00 | 2014-05-02 16:00 | N | N | purpose of this outage is to perform relay maintenance and op-checks | Transformer
ATCO | 7L67 (851s Morse River - 824s Fieldgate),7L67 (824s Fieldgate - 743s Sarah Lake) | 2014-04-29 08:30 | 2014-04-29 14:30 | N | N | 702 bkr commissioning new RAS for GENALTA TFO | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s T4 (370s North Lethbridge),370s 2552 (370s North Lethbridge) | 2014-04-29 10:00 | 2014-04-29 12:00 | N | Y | protection upgrade, trip testing | Circuit Breaker, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 172L (370s North Lethbridge - 172L1238),370s 175 (370s North Lethbridge) | 2014-04-29 14:00 | 2014-04-29 15:00 | N | N | protection upgrade, trip testing | Circuit Breaker, Line |  |  | Over/Under Voltage
ALTALINK | 69s T2 (69s North Barrhead) | 2014-04-30 08:00 | 2014-04-30 17:00 | N | N | T2 doble | Transformer |  |  | For Information Only
ALTALINK | 151s T2 (151s Strathmore) | 2014-04-30 08:00 | 2014-04-30 14:00 | N | N | migrate breaker control, status, alarms to new SCADA RTU system, install new metering, add SCADA | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge),370s 207X (370s North Lethbridge) | 2014-04-30 08:00 | 2014-04-30 10:00 | N | N | protection upgrade, trip testing | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 931S Bohn,7L05 (931s Bohn - 2049s Kettle River) | 2014-04-30 08:00 | 2014-05-02 16:00 | N | N | ISD: April 30 | Station, Line
ALTALINK | 392s T2 (392s Black Diamond) | 2014-04-30 08:00 | 2014-05-01 17:00 | N | N | transformer oil leak | Transformer |  |  | For Information Only
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2014-04-30 08:00 | 2014-05-01 16:00 | N | N | maintenance on SW 8-1a52, 8-1a8, 8-1a1 | Line |  |  | For Information Only
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2014-04-30 08:00 | 2014-04-30 16:00 | N | N | RAS testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-04-30 08:00 | 2014-05-01 16:00 | N | N | factory rep site visit for heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 739s Edith Lake RTU/SCADA | 2014-04-30 09:00 | 2014-05-01 15:45 | N | N | find source of reboot error | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 787L (71s Lamoureux - 787L29) | 2014-04-30 09:30 | 2014-04-30 11:00 | N | Y | high load move | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s T1 (370s North Lethbridge) | 2014-04-30 10:00 | 2014-04-30 11:00 | N | N | protection upgrade, trip testing | Transformer |  |  | For Information Only
ALTALINK | 370s T3 (370s North Lethbridge),370s 2152 (370s North Lethbridge) | 2014-04-30 11:00 | 2014-04-30 13:00 | N | Y | protection upgrade, trip testing | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2014-05-01 07:00 | 2014-05-02 18:00 | N | N | install mono pole screw pile foundations for 712L/ & future 677L | Line |  |  | Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2014-05-01 08:00 | 2014-05-01 17:00 | N | N | to connect 700S temporary 144 kV bypass to 7L53 line to enable construction groups to upgrade 144 kV bus capacity, change out rotten poles and remove overhead shield wires | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2014-05-01 08:00 | 2014-05-02 16:00 | N | N | replace single line CVT | Line |  |  | Over/Under Voltage
ENMAX | 47.2TR (ENMAX 47) | 2014-05-01 08:00 | 2015-05-07 16:00 | N | N | 47s major capital | Transformer
ALTALINK | 913L (69s North Barrhead - 732s Mitsue),69s45 (69s North Barrhead) | 2014-05-01 08:00 | 2014-05-01 14:00 | N | Y | 69s45 hot spot | Line, Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 184s Petro-Canada Edmonton RTU/SCADA | 2014-05-01 14:00 | 2014-05-01 14:15 | N | N | RTU config update | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 89s T2 (89s Ellerslie),89s Ellerslie 500kV Bus 2 | 2014-05-02 06:30 | 2014-05-02 12:00 | N | Y | motorize 89s2689 - Heartland | Bus, Transformer |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation, Creates Radial Feeds, 500 kV
EPCOR | 987s CCP7214 (987s Clover Bar) | 2014-05-02 07:00 | 2014-05-02 16:00 | N | N | doble CVT's | Circuit Breaker
ALTALINK | 924L (102s Langdon - 356s Milo) | 2014-05-02 08:00 | 2014-05-10 08:00 | N | Y | move line from old 102s 240 kV bus to new 102s 240 kV bus - WATL | Line |  |  | 240 kV, Pre-Condition, Overload
ENMAX, ALTALINK | 2.81L (ENMAX 2 - ENMAX 9),23.80L (74s Janet - ENMAX 23) | 2014-05-02 08:00 | 2014-05-06 16:00 | N | N | ECTP 2s, 23s, move to new location on east bus, breaker repair at 23s | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville) | 2014-05-02 12:00 | 2014-05-02 17:00 | N | N | connection of 835s mobile substation to 7L24 line in preparation of supporting 702T at 700s Bonnyville when 701T is out of service | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s T1 (89s Ellerslie),89s Ellerslie 500kV Bus 1 | 2014-05-02 12:01 | 2014-05-03 18:00 | N | Y | conservator oil level issues | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation, Creates Radial Feeds, 500 kV
ATCO | 847s 902T (847s Muskeg River) | 2014-05-03 01:00 | 2014-05-04 16:00 | N | N | maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 765L (74s Janet - 151s Strathmore) | 2014-05-03 06:00 | 2014-05-03 09:00 | N | N | ECTP - Remove Slack Span for 23.80 @ Janet | Line |  |  | Creates Radial Feeds
ENMAX | 138 KV PT (ENMAX 13) | 2014-05-03 08:00 | 2014-05-03 16:00 | N | N | Doble | Terminal Equipment |  |  | For Information Only
ALTALINK | 86s T1 (86s Bigstone) | 2014-05-03 08:00 | 2014-05-04 17:00 | N | N | Transformer Doble & Leak Repairs & LTC Maintenance | Transformer |  |  | 240 kV, Over/Under Voltage
ALTALINK | 763L (158s Vauxhall - 257s Hull),507L (257s Hull - 83s Taber) | 2014-05-03 08:00 | 2014-05-12 16:00 | N | N | ISD= May 5, 2014 | Line
ALTALINK | 51s T3 (51s Wainwright) | 2014-05-03 08:00 | 2014-05-08 17:00 | N | N | Oil Reclaim & Replace PRD Switch | Transformer |  |  | For Information Only
ALTALINK | 508L (344s Warner - 67s Stirling),820L (67s Stirling - 820AL tap) | 2014-05-03 10:00 | 2014-05-03 11:00 | N | N | 508L Repair | Line |  |  | Creates Radial Feeds
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee) | 2014-05-04 06:30 | 2014-05-15 18:00 | N | Y | Epcor Sunnybrook Project | Line |  |  | Pre-Condition, Overload, Limits ATC, Restricts Generation, Creates Radial Feeds, 500 kV
EPCOR | 814s T2 (814s Bellamy) | 2014-05-05 07:30 | 2014-05-06 16:00 | N | Y | BR722 breaker maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 914L (86s Bigstone - 87s Gaetz),86s 1752 (86s Bigstone) | 2014-05-05 08:00 | 2014-05-05 15:00 | N | Y | SCADA equipment upgrade | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 993S Abee | 2014-05-05 08:00 | 2014-05-05 18:00 | N | N | customer maintenance | Station |  |  | For Information Only
ATCO | 757s 701T (757s Battle River) | 2014-05-05 08:00 | 2014-05-15 17:00 | N | N | protection upgrades, setting changes | Transformer |  |  | For Information Only
ATCO | 700s 702T (700s Bonnyville),7L24 (846s Grand Centre - 700s Bonnyville),7L89 (721s La Corey - 700s Bonnyville) | 2014-05-05 08:00 | 2014-05-20 17:00 | N | N | upgrade the existing 144kv bus to a higher capacity | Transformer, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D141 (ENMAX 25),ENMAX 25 B240-D140 (ENMAX 25) | 2014-05-05 08:00 | 2014-05-05 16:00 | N | Y | preliminaty outage on the 240KV ring prior to back energization | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 258s 152 (258s Dow Hydrocarbons) | 2014-05-05 10:00 | 2014-05-06 17:00 | N | N | rebuild breaker head | Circuit Breaker |  |  | For Information Only
ALTALINK | 63s 352 (63s Red Deer) | 2014-05-05 13:00 | 2014-05-08 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2014-05-05 13:00 | 2014-05-12 16:00 | N | N | breaker inspection | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 37s 81 (37s North Calder) | 2014-05-05 13:00 | 2014-05-08 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 612L (336s Fincastle - 368s Burdett),368s 612 (368s Burdett) | 2014-05-05 13:00 | 2014-05-07 17:00 | N | N | standard breaker maintenance | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 854L (397s Benbow - 854L229),397s 854X (397s Benbow) | 2014-05-05 14:00 | 2014-05-06 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P2C | 2014-05-05 17:00 | 2014-05-05 22:00 | N | N | spar replacement | Line
AESO-SC | EMS | 2014-05-05 18:00 | 2014-05-05 19:30 | N | N | Microsoft Office SP2 Rollout for Production Terminal Windows Servers | SCInternal |  |  | For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-05-06 02:00 | 2014-05-06 04:00 | N | Y | High load move | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss
AESO | 8L10 (330P Genesee - Fording Coal Mine) | 2014-05-06 07:00 | 2014-05-10 18:00 | N | N | Sunnybrook Aerial line construction Project HVDC/WATL (Plus 138 Kv Substation Mtce - Doble work & Trans Mtce). | Line
EPCOR | 330p 808 (330p Genesee) | 2014-05-06 07:00 | 2014-05-10 16:00 | N | N | manitenance | Circuit Breaker
ALTALINK | 914L (86s Bigstone - 89s Ellerslie),86s 1252 (86s Bigstone) | 2014-05-06 08:00 | 2014-05-06 15:00 | N | Y | SCADA Equipment Upgrade Project | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2014-05-06 08:00 | 2014-05-09 17:30 | N | Y | Trouble corrective: Replacing badly damaged insulators. | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 6L02 (765s Mannix Mine - 757s Battle River),6L02 (873s Marion Lake - 765s Mannix Mine),6L02 (873s Marion Lake - 769s Stettler) | 2014-05-06 09:00 | 2014-05-07 17:00 | N | N | install phase riser | Line
ALTALINK | 368s 44 (368s Burdett) | 2014-05-06 09:00 | 2014-05-06 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker |  |  | For Information Only
AESO-SC | WECCNet Messaging System Outage | 2014-05-06 11:00 | 2014-05-06 12:00 | N | N | Upgrade WECCNet Messaging computer | SCInternal |  |  | Affects Visibility, Prevents Normal Events
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2014-05-06 16:01 | 2014-05-16 16:00 | N | N | ENMAX: ECTP , 23s major move to old 37.82L bay, breaker repair @ 23s and P & C upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 864L (397s Benbow - 714L tap),397s17 (397s Benbow) | 2014-05-06 18:00 | 2014-05-07 14:00 | N | Y | Cutting over trips from T1 A Protection to 397s864W | Line, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 221s T1 (221s Sunken Lake) | 2014-05-07 07:00 | 2014-05-07 19:00 | N | N | customer 221s26 work | Transformer
EPCOR | Rossdale C2,Rossdale R72C1 (Rossdale) | 2014-05-07 07:30 | 2014-05-07 16:00 | N | Y | breaker maintenance R72C1,maintenance | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone),86s 152 (86s Bigstone) | 2014-05-07 08:00 | 2014-05-07 15:00 | N | N | SCADA equipment upgrade project | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s 66 (370s North Lethbridge) | 2014-05-07 08:00 | 2014-05-08 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker
ALTALINK | 996S Imperial Oil Carson Lake | 2014-05-07 08:00 | 2014-05-07 17:00 | N | N | T1 doble test & gauge replacements | Station
ENMAX | 5.2TR (ENMAX 5),5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2014-05-07 08:00 | 2014-05-10 16:00 | N | N | maintenance | Transformer, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 258s 252 (258s Dow Hydrocarbons) | 2014-05-07 08:00 | 2014-05-08 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker
SUNCOR | 29EDD-1 29EDD1S1752 (29EDD-1) | 2014-05-07 08:00 | 2014-05-09 20:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
AESO-SC | EMS | 2014-05-07 10:10 | 2014-05-07 10:50 | N | N | SC Workbook Production PI Deployment - NTSR Loss Optimization | SCInternal |  |  | Affects Visibility
EPCOR | Rossdale C1 | 2014-05-08 07:30 | 2014-05-08 16:00 | N | Y | breaker maintenance | Shunts |  |  | For Information Only
EPCOR | Rossdale RV722 (Rossdale) | 2014-05-08 07:30 | 2014-05-08 11:55 | N | N | breaker inspection | Circuit Breaker
ALTALINK | 879L (368s Burdett - 523s Bullshead),368s 879 (368s Burdett) | 2014-05-08 08:00 | 2014-05-08 17:00 | N | N | standard breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
NAKODA | 162s 138-RB80 (162s Beddington) | 2014-05-08 08:00 | 2014-05-08 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 77s T1 (77s Sagitawah) | 2014-05-08 08:00 | 2014-05-08 17:00 | N | Y | repair out of step condition | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 89s3089 (89s Ellerslie) | 2014-05-08 09:00 | 2014-05-08 17:00 | N | N | service advisory repair | Switch |  |  | For Information Only
EPCOR | Rossdale RV726 (Rossdale) | 2014-05-08 13:00 | 2014-05-08 16:00 | N | N | breaker inspection | Circuit Breaker
ALTALINK | 89s 1752 (89s Ellerslie) | 2014-05-09 04:30 | 2014-05-09 08:00 | N | N | repair for low gas | Circuit Breaker |  |  | Pre-Condition, Overload, Restricts Generation
EPCOR | 72RV2 (Rossdale - 511s Victoria),Rossdale RV728 (Rossdale) | 2014-05-09 07:30 | 2014-05-09 11:55 | N | N | breaker inspection | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 397s T1 (397s Benbow),720L (347s Fox Creek - 397s Benbow),397s 720N (397s Benbow) | 2014-05-09 08:00 | 2014-05-09 12:00 | N | N | cutting over trips from T1 A protection | Circuit Breaker, Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PL7-1 (29EDD-34 - 29EDD-85) | 2014-05-09 09:00 | 2014-05-17 17:00 | N | N | raise 6 poles on the existing 144kV line. The six poles will be new 10 meter poles to provide 18 meter clearance for vehicles | Line
ATCO | 709s 702 (709s Vegreville) | 2014-05-09 11:30 | 2014-05-23 16:00 | N | N | emergency repair of breaker bushing | Circuit Breaker |  |  | Pre-Condition
EPCOR | 72RS5 (Rossdale - Strathcona),Strathcona S721 (Strathcona) | 2014-05-09 13:00 | 2014-05-09 16:00 | N | N | breaker inspection | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 911L RAS,180L RAS,853L RAS | 2014-05-10 07:30 | 2014-05-10 12:00 | N | Y | change the inputs from 924L & 927L | RAS |  |  | Limits ATC, Impacts RAS
SUNCOR | 29EDD-1 29EDD1S1852 (29EDD-1) | 2014-05-10 08:00 | 2014-05-13 20:00 | N | N | maintenance | Circuit Breaker
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2014-05-10 08:00 | 2014-05-11 16:00 | N | N | 20B138-20.82 breaker maintenance. 21B138-20.82 breaker maintenance & doble | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 312S Fidler | 2014-05-10 08:00 | 2014-06-27 16:00 | N | N | Energization of 240 kV side of Fidler 312S - soaking of transformer at Fidler 312S in preparation for stage 2 - split line 1071L into 994L between Fidler 312S and Goose Lake 103S and 1071L between CRR 205S and Fidler 312S Current planned completion date: May 15, 2014 Completion of 624L to connect Fidler 312S and Summerview 354S. - connection of Windy Point 112S to 893L fed from Goose Lake 103S. - Current planned completion date: May 27, 2014 Reconductor section of 893L between Summerview 354S and Windy Point 112S tap point. - Completion of 624L to connect Fidler 312S and Summerview 354S. Current planned completion date: June 27, 2014 | Station
ATCO | 6L05 (843s Bigknife Creek - 757s Battle River) | 2014-05-10 08:00 | 2014-05-14 16:00 | N | N | open ended line at 757s to replace CT's on breaker 757s602. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 927L (102s Langdon - 356s Milo) | 2014-05-10 10:30 | 2014-05-16 18:00 | N | Y | move line from old 102s 240 kV Bus to new 102s 240 kV Bus - WATL | Line |  |  | 240 kV, Overload
ALTALINK | 606L (184s Petro-Canada Edmonton - 185s Bretville) | 2014-05-11 07:30 | 2014-05-12 17:00 | N | N | line move and pole replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2014-05-12 04:00 | 2014-05-14 01:00 | N | Y | maintenance | Line |  | Maintenance 65MD240-1080, SW 133, SW134, Doble PT & LA @ 65s. Maint 25MD240-1080, SW 152, 153 @ 25s, 240KV Doble PT & LA | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 1204 (330p Genesee),330p 1205 (330p Genesee) | 2014-05-12 07:00 | 2014-05-17 18:00 | N | Y | commissioning | Circuit Breaker |  |  | For Information Only, 500 kV
EPCOR | Strathcona T1 (Strathcona) | 2014-05-12 07:30 | 2014-05-16 16:00 | N | N | relay and breaker maintenance | Transformer |  |  | For Information Only
EPCOR | Woodcroft W724 (Woodcroft) | 2014-05-12 07:30 | 2014-05-12 12:00 | N | N | breaker inspection | Circuit Breaker |  |  | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2014-05-12 08:00 | 2014-05-16 18:00 | N | N | for 760L outage at 163s Amoco Empress | Line |  |  | Creates Radial Feeds
ATCO | 6L79 (711s Willingdon - 707s St.Paul) | 2014-05-12 08:00 | 2014-05-14 17:00 | N | N | install temporary bypass | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 760L (163s Amoco Empress - 760L41),869L (204s Sandy Point - 163s Amoco Empress),163s 869W (163s Amoco Empress) | 2014-05-12 08:00 | 2014-05-13 17:00 | N | N | replace 163s869W | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2014-05-12 08:00 | 2014-05-13 15:39 | N | Y | replacing badly damaged insulators | Line |  |  | Over/Under Voltage, Affects Visibility, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek) | 2014-05-12 08:00 | 2014-05-12 17:00 | N | N | transformer Doble, SFRA, & leak Inspection | Transformer |  |  | For Information Only
EPCOR | Victoria V721 (Victoria) | 2014-05-12 08:00 | 2014-05-12 16:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2014-05-12 08:00 | 2014-05-21 16:00 | N | N | installation of the overhead bypass for 16.63L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin),86s 852 (86s Bigstone) | 2014-05-12 09:00 | 2014-05-12 16:00 | N | N | SCADA equipment upgrade project | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 71s T2 (71s Lamoureux) | 2014-05-12 10:00 | 2014-05-12 17:00 | N | Y | doble and fix temp gauge | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 939s 903T (939s Livock) | 2014-05-12 11:00 | 2014-05-12 13:00 | N | N | to re-wire an alarm contact | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 394s T1 (394s Empress) | 2014-05-12 12:00 | 2014-05-13 17:00 | N | N | doble and SFRA test | Transformer |  |  | For Information Only
ALTALINK | 38s 7152 (38s East Edmonton) | 2014-05-12 13:00 | 2014-05-15 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 221s T1 (221s Sunken Lake) | 2014-05-13 07:00 | 2014-05-13 19:00 | N | N | customer 221s26 work | Transformer
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2014-05-13 07:00 | 2014-05-16 18:00 | N | N | install mono pole screw pile foundations for 712L/ & future 677L | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 761L (38s East Edmonton - 189s Celanese),38s 761N (38s East Edmonton) | 2014-05-13 08:00 | 2014-05-14 17:00 | N | N | move breaker control cables to new building | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2014-05-13 08:00 | 2014-05-14 17:00 | N | N | remove old PTs & CTs, install some bird cover-up | Transformer
ATCO | 7L29 (850s Rainbow Cogen - 791s Rainbow Lake) | 2014-05-13 08:00 | 2014-05-13 16:00 | N | Y | breaker 705 work | Line |  |  | Restricts Generation
ALTALINK | 310p 2152 (310p Sundance) | 2014-05-13 09:00 | 2014-05-15 17:00 | N | N | 240kV breaker maintenance / replace counter | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 359s T1 (359s Esso West Pembina),359s13 (359s Esso West Pembina) | 2014-05-13 09:00 | 2014-05-13 16:00 | N | N | 25 kV breaker & U/G work | Transformer, Switch
ALTALINK | 359s T2 (359s Esso West Pembina) | 2014-05-14 08:00 | 2014-05-14 16:00 | N | N | T1, metal clad & U/G work | Transformer
SUNCOR | 29EDD-1 29EDD1S1152 (29EDD-1) | 2014-05-14 08:00 | 2014-05-16 20:00 | N | N | maintenance | Circuit Breaker
EPCOR | Woodcroft W725 (Woodcroft) | 2014-05-14 08:00 | 2014-05-15 16:00 | N | N | maintenance and doble tests | Circuit Breaker
ENMAX | 33.1TR (ENMAX 33) | 2014-05-14 08:00 | 2014-05-16 16:00 | N | Y | maintenance on transformer and 138kV bus | Transformer
ALTALINK | 515S Fedpipe Judy Creek | 2014-05-14 08:00 | 2014-05-14 18:00 | N | N | Altalink & customer work | Station |  |  | For Information Only
ALTALINK | 76L (115s Mt. Allan - 33s Spray),33s 76 (33s Spray) | 2014-05-15 06:00 | 2014-05-15 14:00 | N | N | Trip test from new 32s protections | Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 162s 138-RB80 (162s Beddington) | 2014-05-15 08:00 | 2014-05-15 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 959s 901T (959s Lanfine) | 2014-05-15 08:00 | 2014-05-16 16:59 | N | Y | emergent outage | Transformer |  |  | 240 kV
ALTALINK | 33s5 (33s Spray) | 2014-05-15 09:00 | 2014-05-15 11:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 452S B.F. Goodrich Fort Saskatchewan | 2014-05-15 09:00 | 2014-05-15 17:00 | N | N | 452s10 latch replacement | Station |  |  | For Information Only
ALTALINK | 936L (102s Langdon - 74s Janet) | 2014-05-16 07:30 | 2014-05-26 17:00 | N | Y | move line from old 102s 240 kV Bus to new 102s 240 kV Bus - WATL | Line |  |  | Pre-Condition, Overload, Limits ATC
EPCOR | Poundmaker T2 (Poundmaker) | 2014-05-16 08:00 | 2014-05-23 16:00 | N | Y | OLTC repair | Transformer |  |  | 240 kV
ALTALINK | 89s 1852 (89s Ellerslie),89s 1952 (89s Ellerslie) | 2014-05-16 08:00 | 2014-05-16 14:00 | N | Y | install EATL RAS & working on CT circuits | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 310P Sundance | 2014-05-16 16:00 | 2014-07-05 16:00 | N | N | hot switch & closing Issue | Station |  |  | 240 kV
ALTALINK, ATCO | 6L09 (767s Oyen - 6L21 tap),760L (163s Amoco Empress - 760L41),869L (204s Sandy Point - 163s Amoco Empress),163s 869W (163s Amoco Empress) | 2014-05-16 17:00 | 2014-05-16 18:00 | N | N | replace 163s869W | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1S1252 (29EDD-1) | 2014-05-17 08:00 | 2014-05-19 20:00 | N | N | maintenance | Circuit Breaker
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 38 B138-38.83 (ENMAX 38) | 2014-05-19 08:00 | 2014-05-19 16:00 | N | N | Doble Breaker 38B138-38.83 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2014-05-20 07:00 | 2014-06-24 18:00 | N | N | Oil De-gassification | Line |  |  | For Information Only
ALTALINK | 285s T1 (285s East Camrose) | 2014-05-20 07:00 | 2014-05-23 16:00 | N | N | 25kV Feeder Cable replacements | Transformer |  |  | For Information Only
ATCO | 700s 705C (700s Bonnyville),700s 706C (700s Bonnyville),700s 707C (700s Bonnyville),7L24 (846s Grand Centre - 700s Bonnyville) | 2014-05-20 08:00 | 2014-05-20 13:00 | N | Y | to disconnect the high side of the mobile sub ; connect 7l24 to temp bypass | Shunts, Line |  |  | For Information Only
ATCO | 9L20 (766s Nevis - 755s Cordel) | 2014-05-20 08:00 | 2014-05-21 18:00 | N | Y | install EATL RAS and breaker maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation, Impacts RAS
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2014-05-20 08:00 | 2014-05-30 16:00 | N | N | 28s PT Install, remove 28.3TR MD, Install new SW for 138KV PT | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L105 (837s Mahihkan - 909s Mahno) | 2014-05-20 08:00 | 2014-06-06 16:00 | N | N | to install new line PT 7L105PT1 on H-frame structure and make primary connection | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2014-05-20 08:00 | 2014-06-02 16:00 | N | N | doble (31s) | Line
ALTALINK | 754L (437s Baymag - 754L72) | 2014-05-20 09:00 | 2014-05-21 18:00 | N | N | Insulator change at STRs 90, 91 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P2C | 2014-05-20 10:00 | 2014-05-20 20:00 | N | N | spar work | Line |  |  | Limits ATC
ALTALINK | 434s T1 (434s East Stony Plain) | 2014-05-20 11:00 | 2014-05-20 17:00 | N | N | doble and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 250p11 (250p Bighorn) | 2014-05-20 11:00 | 2014-05-22 13:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 285s East Camrose RTU/SCADA | 2014-05-20 12:00 | 2014-05-21 12:30 | N | N | update RTU Configuration | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 39s 252 (39s Bickerdike) | 2014-05-20 13:00 | 2014-05-22 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-05-21 02:30 | 2014-05-21 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2014-05-21 06:00 | 2014-05-22 06:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 115s T1 (115s Mt.Allan) | 2014-05-21 07:30 | 2014-05-21 17:00 | N | N | Replace 138kV LA's | Transformer
EPCOR | Victoria V724 (Victoria) | 2014-05-21 08:00 | 2014-05-21 18:00 | N | N | maintenance | Circuit Breaker
ALTALINK | 893AL (893AL3 - 354s Summerview) | 2014-05-21 08:00 | 2014-05-25 17:00 | N | Y | Re-terminate 893AL @ 312s; Renumber line to 624L | Line |  |  | Restricts Generation
ALTALINK | 19s T8 (19s Wabamun) | 2014-05-21 08:00 | 2014-05-21 18:00 | N | N | T8 Doble & O-Ring Change Out | Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft | 2014-05-21 08:00 | 2014-05-22 18:00 | N | N | T2 SFRA testing and doble tests | Station
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2014-05-21 08:00 | 2014-05-23 16:00 | N | N | maintenance on SW | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1S1352 (29EDD-1) | 2014-05-21 08:00 | 2014-05-23 20:00 | N | N | maintenance | Circuit Breaker
ATCO | 959s 722 (959s Lanfine),959s 723 (959s Lanfine) | 2014-05-21 08:00 | 2014-05-22 16:00 | N | N | test the Energization waveforms for the Cap banks at 959S Lanfine | Circuit Breaker
Saskpower | SASK POWER P2C | 2014-05-21 09:00 | 2014-05-21 20:00 | N | N | spar work | Line |  |  | Limits ATC
ALTALINK | 83s C2 (83s Taber),83s T1 (83s Taber) | 2014-05-21 10:00 | 2014-06-04 16:00 | N | N | replace 83s12, s13, s14, s16, s17, s18, s21, s22, s23, s24 & s40, replace 25kV LA's, install bird cover-up, replace insulators on 83s6 & 83s27, create open point 'A' on 25kV bus tie | Transformer, Shunts |  |  | Restricts Generation
ALTALINK, ATCO | 6L09 (767s Oyen - 6L21 tap),760L (163s Amoco Empress - 760L41),869L (204s Sandy Point - 163s Amoco Empress),163s 869W (163s Amoco Empress) | 2014-05-21 14:00 | 2014-05-21 19:00 | N | N | Continue work to replace 163s869W | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L79 (711s Willingdon - 707s St.Paul) | 2014-05-21 17:01 | 2014-05-22 17:00 | N | N | attach risers across jumper J1 @ 707S St Paul | Line |  |  | Pre-Condition
ALTALINK | 115s T2 (115s Mt.Allan) | 2014-05-22 07:30 | 2014-05-22 17:00 | N | N | replace 138kV LA's | Transformer
ALTALINK | 754L (118s Canmore - 437s Baymag) | 2014-05-22 08:00 | 2014-05-23 17:00 | N | N | Insulator change at STRs 92,97,98,100,101,105,114, 122. | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 746AL (524s Fiberglass - 746L tap) | 2014-05-22 08:00 | 2014-05-22 14:00 | N | N | replace structure 18 - tap structure between 746L & 746AL | Line
ALTALINK | 370s T3 (370s North Lethbridge),370s 2152 (370s North Lethbridge) | 2014-05-22 08:00 | 2014-05-23 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 61s Lodgepole RTU/SCADA | 2014-05-22 08:00 | 2014-05-22 18:00 | N | N | Complete Oil Leaks on B Phase Bushing Turret | Terminal Equipment |  |  | Affects Visibility
ATCO | 9L912 (766s Nevis - 63s Red Deer) | 2014-05-22 08:00 | 2014-05-23 18:00 | N | Y | install EATL RAS | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation, Impacts RAS
ALTALINK | 14s T3 (14s Devon) | 2014-05-22 09:00 | 2014-05-22 14:00 | N | N | Transformer Doble | Transformer |  |  | For Information Only
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2014-05-22 10:00 | 2014-05-22 16:00 | N | N | Breaker maintenance 6L12D3 closed for duration of outage | Line |  |  | Pre-Condition
ALTALINK, Lethbridge | 172L (370s North Lethbridge - 172L1238),207L (111s Coalbanks - 370s North Lethbridge),770L (254s Coaldale - 370s North Lethbridge) | 2014-05-22 13:00 | 2014-05-22 14:00 | N | Y | 138kV breaker maintenance & cut open point on 138kV bus | Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 172L (370s North Lethbridge - 172L1238),207L (111s Coalbanks - 370s North Lethbridge),770L (254s Coaldale - 370s North Lethbridge) | 2014-05-23 06:00 | 2014-05-23 09:00 | N | N | 138kV breaker maintenance & restore open point on 370s 138kV bus | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P2C | 2014-05-23 08:00 | 2014-05-23 19:00 | N | N | spar work | Line |  |  | Limits ATC
ALTALINK | 5s East Calgary 240kV Bus 2 | 2014-05-23 11:00 | 2014-05-23 11:30 | N | Y | ECTP: test energize T2 | Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
AWE | Oldman River Wind Farm | 2014-05-24 08:00 | 2014-07-29 16:00 | N | N | In service date: May 26, 2014. Refer to the Op Plan binder for the commissioning plan. | Not In Model
SUNCOR | 29EDD-1 29EDD1S1452 (29EDD-1) | 2014-05-24 08:00 | 2014-05-27 20:00 | N | N | maintenance | Circuit Breaker
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2014-05-24 08:00 | 2014-05-25 16:00 | N | N | oil sample, contamination found | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 893L (806s Oldman River - 103s Goose Lake) | 2014-05-24 12:00 | 2014-05-27 17:00 | N | Y | terminate 893L at 112s Windy Point, functional testing from 103s | Line |  |  | Restricts Generation
ALTALINK | 63s 952 (63s Red Deer) | 2014-05-26 07:00 | 2014-05-26 12:00 | N | Y | EATL interface: protection addition to L4 (912L) for 13L50 RAS | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 285s T2 (285s East Camrose) | 2014-05-26 07:00 | 2014-05-29 16:00 | N | N | breaker addition 285s3203 & 25kV cable replacements | Transformer |  |  | For Information Only
ALTALINK | 107s T1 (107s Westfield),722L (368s Burdett - 107s Westfield) | 2014-05-26 07:00 | 2014-05-26 17:00 | N | N | replace 25kV bus PTs | Line, Transformer |  |  | For Information Only
EPCOR | Strathcona T1 (Strathcona),Strathcona S722 (Strathcona) | 2014-05-26 07:30 | 2014-05-30 16:00 | N | N | relay and breaker maintenance | Circuit Breaker, Transformer |  |  | For Information Only
EPCOR | Garneau T3 (Garneau) | 2014-05-26 07:30 | 2014-05-28 17:00 | N | N | op checks and RTU indications cutover | Transformer |  |  | For Information Only
EPCOR | 557s T1 (557s Castle Downs) | 2014-05-26 07:30 | 2014-06-07 16:00 | N | Y | breaker fail panel | Transformer |  |  | 240 kV, For Information Only
ALBIAN | 920s 902T (920s Jackpine) | 2014-05-26 08:00 | 2014-05-29 17:00 | N | Y | maintenance | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2014-05-26 08:00 | 2014-05-26 17:00 | N | N | breaker maintenance | Line |  |  | For Information Only
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2014-05-26 08:00 | 2014-05-26 17:00 | N | N | breaker maintenance CK726 AT 987S | Line |  |  | For Information Only
EPCOR | Rossdale C2 | 2014-05-26 08:00 | 2014-05-26 17:00 | N | Y | maintenance | Shunts |  |  | For Information Only
EPCOR | Rossdale VHBB1 (Rossdale) | 2014-05-26 08:00 | 2014-05-28 17:00 | N | N | doble and maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 162s 138-RB80 (162s Beddington) | 2014-05-26 08:00 | 2014-05-27 00:01 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 310p 2452 (310p Sundance) | 2014-05-26 09:00 | 2014-05-26 14:00 | N | Y | trip dashpot empty | Circuit Breaker |  |  | 240 kV, For Information Only
BCH | 5L91 (Selkirk - Ashton Creek) | 2014-05-26 09:00 | 2014-06-02 17:00 | N | Y | maintenance | Line |  |  | Limits ATC
ALTALINK | 754L (118s Canmore - 437s Baymag) | 2014-05-26 09:00 | 2014-05-30 17:00 | N | N | insulator change | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 391s T2 (391s Balzac) | 2014-05-26 11:00 | 2014-05-26 17:00 | N | N | 25kV switch repair | Transformer |  |  | For Information Only
ALTALINK | 320p 752 (320p Keephills) | 2014-05-26 12:00 | 2014-05-27 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 63s 852 (63s Red Deer) | 2014-05-26 12:00 | 2014-05-26 17:00 | N | Y | EATL interface: protection addition to L4 (912L) for 13L50 RAS | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),174L (197s Bardo - 395s North Holden),730L (197s Bardo - 730L61) | 2014-05-26 13:00 | 2014-05-26 14:00 | N | N | take oil samples | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2014-05-26 13:00 | 2014-06-05 17:00 | N | Y | 138kV breaker maintenance & hot spots | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 959S 722C (959S Lanfine),959S 723C (959S Lanfine) | 2014-05-27 07:00 | 2014-06-06 16:00 | N | Y | wiring changes | Shunts |  |  | For Information Only
ATCO | 700s 604T (700s Bonnyville),700s 605T (700s Bonnyville),700s 701T (700s Bonnyville),6L82 (700s Bonnyville - 707s St.Paul),7L24 (846s Grand Centre - 700s Bonnyville),700s 701 (700s Bonnyville),700s 702 (700s Bonnyville),7L70 (700s Bonnyville - 936s Norberg) | 2014-05-27 07:00 | 2014-06-13 17:00 | N | N | reconductor the 144 kV bus | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2014-05-27 07:30 | 2014-05-29 06:59 | N | Y | FATD - SFTP: BYPASS # 1. Relocate a portion of 911L off of existing ROW to allow for new 1037/1038L | Line |  |  | 240 kV, Limits ATC
ALTALINK | 545s T1 (545s Provost) | 2014-05-27 08:00 | 2014-05-28 17:00 | N | N | 545s1, T1 leak repair, 545s9 maintenance & 545s13 replacement | Transformer |  |  | For Information Only
ATCO | 850s 702T (850s Rainbow Cogen) | 2014-05-27 08:00 | 2014-05-29 16:00 | N | N | major testing and maintenance | Transformer |  |  | For Information Only
ALTALINK | 911L RAS,180L RAS,911L (59s Peigan - ENMAX 65),853L RAS | 2014-05-27 08:00 | 2014-05-27 12:00 | N | Y | test RAS system | Line, RAS |  |  | 240 kV, Limits ATC, Impacts RAS
ATCO | 7L29 (850s Rainbow Cogen - 791s Rainbow Lake) | 2014-05-27 08:00 | 2014-05-27 16:00 | N | Y | to coincide with the scheduled outage of 702T at 850s | Line |  |  | Restricts Generation, For Information Only
ATCO | 813s 503R (813s Little Smoky) | 2014-05-27 08:00 | 2014-05-27 17:00 | N | Y | test reactor breaker | Shunts |  |  | For Information Only
ALTALINK | 650s 1352 (650s Hansman Lake) | 2014-05-27 08:00 | 2014-05-27 17:00 | N | N | 138kV breaker low gas top up | Circuit Breaker |  |  | For Information Only
ALTALINK | 310p 1352 (310p Sundance),310p 1452 (310p Sundance) | 2014-05-27 09:00 | 2014-05-27 17:00 | N | N | switch Adjustment 310p13A | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 945S Sunshine Village | 2014-05-27 20:00 | 2014-05-28 04:00 | N | N | install bird coverup on 69kV Bus | Station |  |  | For Information Only
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2014-05-27 20:00 | 2014-05-28 04:00 | N | N | repair damaged crossarms & conductor on 551L | Line |  |  | For Information Only
ENMAX | 162s 138-RB82 (162s Beddington) | 2014-05-28 08:00 | 2014-05-28 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
SUNCOR | 29EDD-1 29EDD1S1552 (29EDD-1) | 2014-05-28 08:00 | 2014-05-30 20:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 348s T2 (348s Marlboro) | 2014-05-28 08:00 | 2014-05-28 19:00 | N | N | Customer Equipment Repairs | Transformer |  |  | For Information Only
ATCO | 813s 501R (813s Little Smoky) | 2014-05-28 08:00 | 2014-05-28 17:00 | N | Y | testing reactor breaker | Shunts |  |  | For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2014-05-28 08:00 | 2014-05-29 16:00 | N | N | 11B138-11.82 & 14B138-11.82 doble & maintenance | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek),809s 704 (809s Louise Creek) | 2014-05-28 08:00 | 2014-05-28 16:30 | N | N | breaker 704 maintenance | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 320p 152 (320p Keephills) | 2014-05-28 09:00 | 2014-05-29 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 310P 69 (310p Sundance),310p T30 (310p Sundance) | 2014-05-28 09:00 | 2014-05-28 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1053L (132s Ware Junction - 324s Cassils) | 2014-05-29 07:00 | 2014-05-29 19:00 | N | Y | EATL interface: ATCO installing 13L50 Str # 1327 | Line |  |  | 240 kV
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely),911L (59s Peigan - ENMAX 65) | 2014-05-29 07:00 | 2014-06-16 17:00 | N | Y | FATD - SFTP: bypass # 1. Relocate a portion of 911L off of existing ROW to allow for new 1037/1038L. 180L rebuild. | Line |  |  | Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 267s C1 (267s Killarney Lake),267s C3 (267s Killarney Lake),749L (899s Edgerton - 749L118AN),267s C2 (267s Killarney Lake) | 2014-05-29 08:00 | 2014-05-29 17:00 | N | Y | repairs to center phase stop | Shunts, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s T2 (305s Acheson) | 2014-05-29 08:00 | 2014-05-29 17:00 | N | N | doble, maintenance., SFRA, oil leak and switch adjustment | Transformer |  |  | For Information Only
EPCOR | Rossdale VHBB2 (Rossdale) | 2014-05-29 08:00 | 2014-05-31 17:00 | N | N | doble and maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 312s Fidler RTU/SCADA | 2014-05-29 08:00 | 2014-05-29 12:00 | N | N | Fix analog issues with RTU. | Terminal Equipment |  |  | Affects Visibility
EPCOR | 72LH8 (Hardisty - 803s Lambton) | 2014-05-29 08:00 | 2014-06-09 18:00 | N | N | pole replacement | Line |  |  | For Information Only
ENMAX | 162s 138-RB83 (162s Beddington) | 2014-05-29 08:00 | 2014-05-29 16:00 | N | N | breaker maintenance | Circuit Breaker
ALTALINK | 869L (204s Sandy Point - 163s Amoco Empress),163s 869W (163s Amoco Empress) | 2014-05-29 10:00 | 2014-05-29 17:00 | N | N | to fix some deficiencies | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 162s 138-RB84 (162s Beddington) | 2014-05-30 08:00 | 2014-05-30 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ATCO | 840S McNeill Station,840s 901T (840s MCNEILLSTATION),840s 701T (840s MCNEILLSTATION) | 2014-05-30 08:00 | 2015-02-09 23:59 | N | Y | upgrade McNeill HVDC controls | Station, Transformer |  | Upgrade McNeill HVDC Controls | Limits ATC
ATCO | 791s 701T (791s Rainbow Lake),791s 706 (791s Rainbow Lake) | 2014-05-30 08:00 | 2014-06-01 16:00 | N | N | testing on 701T and maintenance on breaker 706. | Transformer, Circuit Breaker
ALTALINK | 310P Sundance | 2014-05-30 18:00 | 2014-06-02 06:00 | N | N | maintenaance | Station |  |  | 240 kV, Restricts Generation, For Information Only
SUNCOR | 29EDD-1 29EDD1S1652 (29EDD-1) | 2014-05-31 08:00 | 2014-06-02 20:00 | N | N | maintenance | Circuit Breaker
ENMAX | 6.80L (ENMAX 30 - ENMAX 6),30B138-6.80 (ENMAX 30),ENMAX 6 B138-6.80 (ENMAX 6) | 2014-05-31 08:00 | 2014-06-01 16:00 | N | N | Perform breaker maintenance. | Line, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 271s T2 (271s Shell Jumping Pound) | 2014-05-31 08:00 | 2014-06-06 15:00 | N | N | Customer requested outage | Transformer |  |  | For Information Only
ALTALINK | 893L (806s Oldman River - 103s Goose Lake) | 2014-06-01 07:00 | 2014-06-07 18:00 | N | N | complete restringing of new conductor between str 48J (893AL tap)& 65J connection to new portion of 893L) | Line |  |  | Restricts Generation
ALTALINK | 1206L (89s Ellerslie - 12s Heartland),1212L (89s Ellerslie - 12s Heartland) | 2014-06-01 08:00 | 2014-07-15 17:00 | N | Y | convert from 240 kV to 500 kV - Heartland & EATL | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 31.1C (ENMAX 31) | 2014-06-01 08:00 | 2014-06-17 14:00 | N | Y | Forced outage. | Shunts |  |  | Limits ATC
ALTALINK | 54s 694 (54s Fort Saskatchewan) | 2014-06-01 17:00 | 2014-06-02 15:00 | N | N | low gas (forced outage) | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2014-06-02 07:00 | 2014-06-05 17:00 | N | N | Replace step bolts, correct minor deficiencies, change protection settings due to 312s addition. | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz),86s 1752 (86s Bigstone) | 2014-06-02 07:30 | 2014-06-02 15:00 | N | Y | SCADA Equipment Upgrade Project | Line, Circuit Breaker |  |  | 240 kV, Limits ATC
ALTALINK | 812L (392s Black Diamond - 65s High RIver) | 2014-06-02 08:00 | 2014-06-02 17:00 | N | N | Change out structures # 49 and 71. Using live line methods. | Line |  |  | For Information Only
BCH | Natal T2 (BCH Natal) | 2014-06-02 08:00 | 2014-06-06 17:00 | N | N | maintenance | Transformer |  |  | For Information Only
Syncrude | D05 72kV Bus A | 2014-06-02 08:00 | 2014-06-07 16:00 | N | N | MLMR project 1375 | Bus
ATCO | 791s 702T (791s Rainbow Lake) | 2014-06-02 08:00 | 2014-06-03 16:00 | N | N | testing | Transformer |  |  | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2014-06-02 08:00 | 2014-06-02 16:00 | N | N | Breaker Mtc | Circuit Breaker |  |  | Creates Radial Feeds
EPCOR | 72LH8 (Hardisty - 803s Lambton) | 2014-06-02 08:00 | 2014-06-02 16:00 | N | N | Hardisty TX2 relay Op-checks on transformer protection | Line |  |  | For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2014-06-02 08:00 | 2014-06-05 10:00 | N | N | maintenance | Switch |  |  | Restricts Generation
EPCOR | 330p 1204 (330p Genesee) | 2014-06-02 08:00 | 2014-06-30 18:00 | N | Y | breaker replacement | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ATCO | 932s 906 (932s Pemukan) | 2014-06-02 09:30 | 2014-06-02 13:00 | N | N | replace faulty SF6 density. | Circuit Breaker |  |  | 240 kV
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2014-06-02 10:00 | 2014-06-04 16:00 | N | N | climbing inspection | Line |  | BX 7L760D1 D2 FOR A CLIMBING INSPECTION6L09 WILL BE OPEN ENDED @ 767S OYEN FOR CONTINGENCY PURPOSES | Creates Radial Feeds
ATCO | 932s 905 (932s Pemukan) | 2014-06-02 13:15 | 2014-06-02 16:30 | N | N | replace faulty SF6 density. | Circuit Breaker |  |  | 240 kV
ALTALINK | 28S West Brooks | 2014-06-03 07:00 | 2014-06-03 17:30 | N | N | Station Service: replace 25kv LAs associated with 28s35 | Station |  |  | For Information Only
ALTALINK | 678s T2 (678s Okotoks) | 2014-06-03 08:00 | 2014-06-05 17:00 | N | N | Bird cover-up install, 25kV metering upgrade | Transformer |  |  | For Information Only
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2014-06-03 08:00 | 2014-06-05 17:30 | N | N | structure change #273,#274, and #275 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2014-06-03 08:00 | 2014-06-04 16:00 | N | N | Doble 6B138-6.82 & 6PT138-6.82, Breaker Maintenance on 41B138-6.82 | Line
ALTALINK | 89s 452 (89s Ellerslie) | 2014-06-03 08:00 | 2014-06-05 17:00 | N | Y | Standard Breaker Maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 28s R1 (28s West Brooks) | 2014-06-03 09:00 | 2014-06-03 17:00 | N | Y | Doble, SFRA Test | Shunts |  |  | 240 kV
ATCO | 932s 904 (932s Pemukan) | 2014-06-03 09:30 | 2014-06-03 13:30 | N | N | replace faulty SF6 density. | Circuit Breaker |  |  | 240 kV
ATCO | 740s H.R.Milner RTU/SCADA | 2014-06-03 10:00 | 2014-06-03 14:00 | N | N | Radio work at Smokey River Twr | Terminal Equipment |  |  | Affects Visibility
EPCOR | Rossdale C1 | 2014-06-03 11:15 | 2015-07-29 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2014-06-04 07:00 | 2014-06-16 18:00 | N | N | string 13L50 over 6L09 | Line
SUNCOR | 29EDD-1 29EDD1s 152 (29EDD-1 Millennium) | 2014-06-04 08:00 | 2014-06-06 20:00 | N | Y | mainetanance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 703L (377s Hardisty - 703L),377s 703E (377s Hardisty) | 2014-06-04 08:00 | 2014-06-11 17:00 | N | N | 817L1 replacement | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 355s T1 (355s Chevron Knight) | 2014-06-04 08:00 | 2014-06-04 14:00 | N | N | transformer doble and maintenance | Transformer
ALTALINK | 28s T3 (28s West Brooks) | 2014-06-04 09:00 | 2014-06-04 17:00 | N | N | doble | Transformer
ALTALINK | 355s T2 (355s Chevron Knight) | 2014-06-04 14:00 | 2014-06-04 18:00 | N | N | investigate/repair low oil/temperature alarm | Transformer
ATCO | 959s 921 (959s Lanfine) | 2014-06-05 06:00 | 2014-06-05 18:00 | N | Y | connect SVC to 240kV bus | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2014-06-05 08:00 | 2014-06-06 16:00 | N | N | doble & breaker maintenance on 40B138-40.81 | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CDS7 (987s Clover Bar) | 2014-06-05 08:00 | 2014-06-05 16:00 | N | N | switch repair | Switch
ALTALINK | 905L (19s Wabamun - 37s North Calder),19s T10 (19s Wabamun) | 2014-06-05 08:00 | 2014-06-05 16:00 | N | Y | commission 19s52 control module | Line, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 33s 4 (33s Spray) | 2014-06-05 09:00 | 2014-06-05 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 810s Dome Cutbank RTU/SCADA | 2014-06-05 10:00 | 2014-06-05 17:00 | N | N | upgrade the RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 83s T3 (83s Taber) | 2014-06-05 10:00 | 2014-06-20 16:00 | N | N | replace 83s53, s57, s58, s59, s60, s62 & s63, replace 25kV LA's, install bird cover-up, replace UG cables between 83s62 & 83s28, move 83s263E breaker | Transformer
ALTALINK | 271s T1 (271s Shell Jumping Pound) | 2014-06-05 15:00 | 2014-06-10 15:00 | N | N | customer requested outage | Transformer
ENMAX, NAKODA | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington) | 2014-06-06 08:00 | 2014-06-06 16:00 | N | N | substation washing 162s | Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 635s 10 (635s Rose Valley) | 2014-06-06 08:00 | 2014-06-06 17:00 | N | N | customer equipment work | Switch |  |  | For Information Only
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2014-06-06 08:00 | 2014-06-12 17:00 | N | Y | Complete construction on 1115L | Line |  |  | 240 kV
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2014-06-06 09:00 | 2014-06-06 16:00 | N | N | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s12 (62s Brazeau) | 2014-06-06 12:00 | 2014-06-08 10:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ATCO | 707s 505C (707s St. Paul) | 2014-06-06 14:00 | 2014-06-06 18:00 | N | Y | remove it from breaker 501 Bay | Shunts |  |  | For Information Only
ALTALINK | 310P Sundance | 2014-06-06 18:00 | 2014-06-09 06:00 | N | Y | maintenance | Station |  |  | 240 kV, For Information Only
SUNCOR | 29EDD-1 29EDD1s 252 (29EDD-1 Millennium) | 2014-06-07 08:00 | 2014-06-09 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 522AL (868s Keephills Make-Up - 522L tap),522L (320p Keephills - 522L6),522L (866s Sundance Make-Up - 522AL tap) | 2014-06-07 08:00 | 2014-06-07 20:00 | N | N | switch replacement - 522L6 | Line
ALTALINK | 5s T1 (East Calgary) | 2014-06-07 08:00 | 2014-06-08 16:00 | N | N | ENMAX-ECTP: working underneath 138 kV | Transformer
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2014-06-07 08:00 | 2014-06-08 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 5s T1 (East Calgary),5s 8 (ENMAX 2) | 2014-06-07 08:00 | 2014-06-08 16:00 | N | Y | ECTP working underneath overhead 138 kV line | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | Shepard RAS | 2014-06-07 08:00 | 2014-07-09 16:00 | N | N | RAS sequence test: June 9  13; Interface with AltaLink: June 16  20; System element validation: July 2  4 | RAS
ENMAX | 162s 240-RB131 (162s Beddington),162s 240-RB132 (162s Beddington) | 2014-06-07 08:00 | 2014-06-07 16:00 | N | Y | substations washing | Circuit Breaker |  |  | 240 kV, Restricts Generation, For Information Only
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2014-06-07 08:00 | 2014-06-07 17:30 | N | N | test new logic & settings for 21A & 21B | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2014-06-07 08:00 | 2014-06-07 16:00 | N | N | W725 breaker repair | Line
NRGREEN | NRG3 NRGreen Cogen | 2014-06-07 08:00 | 2014-07-02 16:00 | N | N | In service date: June 7, 2014. Refer to the OpPlan binder for the commissioning plan. (19 MW) | Unit
ATCO | 707s 601T (707s St. Paul),707s 602T (707s St. Paul) | 2014-06-07 08:00 | 2014-07-21 12:00 | N | N | work on 600BS1 to salvage 601T, 602T, 501VR and 502VR | Transformer |  | 707S ST PAUL 600BS1 O/S TO SALVAGE 601T, 602T 501VR, 502VR | For Information Only
ENMAX | ENMAX 25 B240-D141 (ENMAX 25),ENMAX 25 B240-D140 (ENMAX 25) | 2014-06-07 08:00 | 2014-06-07 16:00 | N | Y | preliminary outage on the 240 kV ring prior to back energization GSU 3 | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 763L (28s West Brooks - 763L257A),28s 31 (28s West Brooks) | 2014-06-09 07:00 | 2014-06-14 17:30 | N | N | replace 28s31 with new SF6 dead tank breaker and add line LAs. | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s T2 (5s East Calgary) | 2014-06-09 08:00 | 2014-06-16 16:00 | N | Y | Crews working in proximity to open point F | Transformer |  |  | 240 kV
ENMAX | 1.7TR (ENMAX 1) | 2014-06-09 08:00 | 2014-06-13 16:00 | N | N | PRD, oil samples(Bushing/LTC), check reversing sw | Transformer |  |  | For Information Only
ENMAX | 14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2014-06-09 08:00 | 2014-06-13 16:00 | N | N | maintenance | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred_915 (Syncrude Mildred Lake) | 2014-06-09 08:00 | 2014-06-15 16:00 | N | N | 5 year maintenance | Circuit Breaker |  |  | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap),7L760 (7L760D2 - 767s Oyen) | 2014-06-09 08:00 | 2014-06-12 16:00 | N | N | maintenance | Line |  | maintenance | Firm Load Loss, Creates Radial Feeds
ALTALINK | 833L (ENMAX 2 - ENMAX 12),5s 833W (5s East Calgary) | 2014-06-09 08:00 | 2014-06-14 16:00 | N | N | ENMAX: ECTP 2s, reconfig bypass structure. | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | RossdaleT1 (Rossdale) | 2014-06-09 08:00 | 2014-06-13 18:00 | N | N | doble/SFRA.S.As172/73/74 and CVT99 | Transformer |  |  | For Information Only
EPCOR | 72VN21 (Namao - 511s Victoria) | 2014-06-09 08:00 | 2014-06-09 16:00 | N | N | Namao N725 breaker inspection | Line |  |  | For Information Only
ALTALINK | 678s T1 (678s Okotoks) | 2014-06-09 08:00 | 2014-06-12 17:00 | N | N | replace 678s4, s5, s6, Bird cover-up install, 25kV metering upgrade | Transformer |  |  | For Information Only
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2014-06-09 08:00 | 2014-06-12 16:00 | N | N | ECTP 2s, reconfig bypass structure. | Line
ALTALINK | 522AL (868s Keephills Make-Up - 522L tap),522L (320p Keephills - 522L6),522L (522L8 - 522L tap),522L (866s Sundance Make-Up - 522AL tap) | 2014-06-09 08:00 | 2014-06-10 13:00 | N | N | switch replacement - 522L8 | Line |  |  | For Information Only
BCH | 5L91 (Selkirk - Ashton Creek) | 2014-06-09 08:00 | 2014-06-18 16:00 | N | Y | replace spacer dampers & install arcing horn | Line |  |  | Limits ATC
ATCO | 969s Lindbergh RTU/SCADA | 2014-06-09 11:00 | 2014-06-11 15:00 | N | N | RTU upgrades | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 431S Hussar | 2014-06-09 11:00 | 2014-06-09 17:00 | N | N | customer request outage | Station
ALTALINK | 214s T2 (214s Innisfail) | 2014-06-09 11:00 | 2014-06-10 17:00 | N | N | doble and maintenance | Transformer |  |  | For Information Only
ALTALINK | 431S Hussar,886L (431s Hussar - 428s Namaka),428s 886N (428s Namaka) | 2014-06-09 11:00 | 2014-06-09 17:00 | N | N | 138kV breaker maintenance @ 428s | Line, Circuit Breaker, Station |  |  | Pre-Condition, For Information Only
ALTALINK | 178s Cynthia RTU/SCADA | 2014-06-09 12:00 | 2014-06-11 17:00 | N | N | work at 9342R  routine maintenance, calibration, testing | Terminal Equipment |  |  | For Information Only
ALTALINK | 77s 752 (77s Sagitawah) | 2014-06-09 13:00 | 2014-06-10 17:00 | N | N | breaker maintenance and head gasket replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 163s T1 (163s Amoco Empress) | 2014-06-09 13:00 | 2014-06-11 17:00 | N | Y | doble, maintenance, conductor repair | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 727L (678s Okotoks - 727L39N) | 2014-06-10 07:00 | 2014-06-11 18:00 | N | N | new 646L breaker bay addition at 678s | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2014-06-10 07:30 | 2014-06-12 17:30 | N | Y | install inter phase spacers, and conductor repairs from STRs # 289  293 | Line |  |  | 240 kV, Limits ATC
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2014-06-10 08:00 | 2014-06-10 16:00 | N | Y | 240 kV ring. Geotech to bore a test hole for the future receiving structure | Circuit Breaker |  |  | 240 kV
GREENGATEP | 615S Halkirk | 2014-06-10 09:00 | 2014-06-10 13:00 | N | N | DSTATCOM software upgrade | Station |  |  | For Information Only
ATCO | 755s 901 (755s Cordel) | 2014-06-10 09:00 | 2014-06-10 16:00 | N | Y | open 901 to add contacts to MOD 901B | Circuit Breaker |  | ADD CONTACTS TO MOD 901B - REQUIRES DISABLING 901B AND 901 OPEN | Contingency Requires Mitigation, For Information Only
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek) | 2014-06-10 10:00 | 2014-06-10 17:00 | N | N | maintenance at 730s Rycroft | Line |  | 7L73 OPEN ENDED @ 739s RYCROFT FOR MAINT. ON BREAKER 703 INFORM DEVON CANADA OF LINE BEING OPENED AND TO CALL BEFORE STARTING LARGE MOTOR STARTS | Firm Load Loss, Creates Radial Feeds
ATCO | 940s Beartrap RTU/SCADA | 2014-06-10 13:00 | 2014-06-11 15:00 | N | N | RTU upgrades | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 1113L (102s Langdon - 520s Bennett) | 2014-06-11 07:30 | 2014-06-18 16:00 | Y | N | for internal S&D calculation purprose | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ALTALINK | 102s SVC (102s Langdon),1113L (102s Langdon - 520s Bennett) | 2014-06-11 07:30 | 2014-06-18 16:00 | Y | Y | cut SVC free of old 102s252 & 102s552, bypass 102s1113, change controls to 102s7352 - WATL | Shunts, Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ALTALINK | 3AL (43s Shell Canada Jumping Pound jct - 3L tap),3L (42s Sarcee - 272s Springbank) | 2014-06-11 08:00 | 2014-06-13 17:00 | N | N | replace 138kV and 25kV LAs on T1, replace switch insulators and strain insulators on 43s3ALN | Line |  |  | Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1s 352 (29EDD-1 Millennium) | 2014-06-11 08:00 | 2014-06-13 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2014-06-11 08:00 | 2014-06-11 16:00 | N | N | RV722 breaker inspection | Line |  |  | For Information Only
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2014-06-11 08:00 | 2014-06-11 17:00 | N | Y | Air-Break Adjustment | Line |  |  | 240 kV, Overload
ALTALINK | 759L (87s Gaetz - 276s Prentiss),276s 759W (276s Un Carb Prentiss) | 2014-06-11 08:00 | 2014-06-11 14:00 | N | N | required for TPR testing | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 216S Knightsbridge | 2014-06-11 08:00 | 2014-06-11 12:00 | N | N | Perform In-situ test on T1 & T2 metering equipment | Station |  |  | For Information Only
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood),54s 694 (54s Fort Saskatchewan) | 2014-06-11 08:00 | 2014-06-12 17:00 | N | N | replace head gaskets | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 286s T2 (286s Yasa) | 2014-06-11 08:30 | 2014-06-11 17:00 | N | N | T2 transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 320p 552 (320p Keephills) | 2014-06-11 09:00 | 2014-06-12 17:00 | N | Y | standard breaker maintenance | Circuit Breaker |  |  | 240 kV
SUNCOR | 29EDD-18 Firebag RTU/SCADA | 2014-06-11 14:30 | 2014-06-11 15:00 | N | N | RTU maintenance | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 428s T1 (428s Namaka),428sVR1 (428s Namaka) | 2014-06-12 08:00 | 2014-06-12 17:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 163s 669 (163s Amoco Empress),163s57 (163s Amoco Empress),669L (163s Amoco Empress - 562s Cypress) | 2014-06-12 08:00 | 2014-06-12 17:00 | N | N | breaker and switch maintenance | Circuit Breaker, Switch, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2014-06-12 08:00 | 2014-06-12 11:59 | N | N | RV726 breaker: contact "a" issue investigation by mitsubishi | Line |  |  | For Information Only
ALTALINK | 938L (77s Sagitawah - 809s Louise Creek) | 2014-06-12 08:00 | 2014-06-12 14:00 | N | Y | repair hot spot on airbreak 77s49 | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 286s T1 (286s Yasa) | 2014-06-12 08:30 | 2014-06-12 17:00 | N | N | T1 transformer maintenance. | Transformer |  |  | For Information Only
ALTALINK | 787L (71s Lamoureux - 787L29) | 2014-06-12 09:00 | 2014-06-12 11:00 | N | N | High load move. | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2014-06-12 12:59 | 2014-06-12 18:00 | N | N | RV728 breaker: contact "a" issue investigation by mitsubishi | Line |  |  | For Information Only
Lethbridge, ALTALINK | 734L (241s Lethbridge Uplands - 370s North Lethbridge),813L (241s Lethbridge Uplands - 146s Lethbridge MacDonald),241s 734L (241s Lethbridge Uplands),241s 813L (241s Lethbridge Uplands) | 2014-06-12 13:00 | 2014-06-12 16:00 | N | N | re-connect risers to the transformer | Circuit Breaker, Line |  |  | For Information Only
AESO | 971L (762s Conklin - 154s Spruce) | 2014-06-13 07:00 | 2014-06-13 19:00 | N | Y | repair surge arrestor | Line |  |  | 240 kV, Restricts Generation
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville),7L53 (700s Bonnyville - 706s Irish Creek) | 2014-06-13 08:00 | 2014-06-13 19:00 | N | N | to disconnect temporary 144kv bypass at 700s Bonnyville | Line |  | To disconnect temporary 144kv bypass at 700s Bonnyville | Overload, Over/Under Voltage
ENMAX | 1.8TR (ENMAX 1) | 2014-06-13 12:00 | 2014-06-13 16:00 | N | N | oil sample LTC, check reversing switch | Transformer
ALTALINK | 489s T2 (489s Petro Canada Brazeau River) | 2014-06-13 12:30 | 2014-06-13 15:30 | N | N | inspect NGR & cables leaving station | Transformer
ALTALINK | 1034L (244s Bowmanton - 324s Cassils),1035L (244s Bowmanton - 324s Cassils),1088L (324s Cassils - 2075s Newell) | 2014-06-14 07:00 | 2014-11-21 18:00 | N | Y | EATL Interface: Line cut in and out | Line |  |  | 240 kV, Pre-Condition
EPCOR | 814s T2 (814s Bellamy) | 2014-06-14 08:00 | 2014-06-14 18:00 | N | N | emergency repair disconnect switches | Transformer |  |  | 240 kV
ALTALINK | 250p22 (250p Bighorn) | 2014-06-14 08:00 | 2014-06-14 15:30 | N | N | maintenance | Switch |  |  | Restricts Generation
SUNCOR | 29EDD-1 29EDD1s 452 (29EDD-1 Millennium) | 2014-06-14 08:00 | 2014-06-17 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
SUNCOR | 29EDD-1 29EDD1S1352 (29EDD-1) | 2014-06-14 08:00 | 2014-06-17 20:00 | N | N | maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2014-06-15 07:00 | 2014-06-20 18:00 | N | Y | L to J : Replace 74s21N, PTs, CTs and footings. | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Restricts Generation
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2014-06-15 08:00 | 2014-06-19 16:00 | N | N | Doble, Secondary cable test | Transformer, Line
EPCOR | 809L (320p Keephills - 330p Genesee) | 2014-06-16 07:00 | 2014-07-12 18:00 | N | N | Sunnybrook Project HVDC/WATL Project (Plus 138 Kv Substation Mtce - Doble work & Trans Mtce). | Line |  |  | For Information Only
ALTALINK | 835AL (454s Bucklake - 835L tap),835L (283s Violet Grove - 835L tap),835L (384s Keystone - 835L tap) | 2014-06-16 08:00 | 2014-06-20 17:00 | N | N | building by-pass for the temporary line to 454s | Line |  |  | For Information Only
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2014-06-16 08:00 | 2014-06-29 16:00 | N | N | Point Trotter phase 2 | Line
EPCOR | RossdaleT2 (Rossdale) | 2014-06-16 08:00 | 2014-06-20 18:00 | N | N | Trans Maintenance. Doble/SFRA:Sas 175/176/177,CVT100.. | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge),813L (241s Lethbridge Uplands - 146s Lethbridge MacDonald) | 2014-06-16 08:00 | 2014-06-18 13:00 | N | N | Lethbridge protection testing. | Line |  |  | For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2014-06-16 08:00 | 2014-06-16 16:00 | N | N | Doble and Bkr maint | Line |  |  | Creates Radial Feeds
Syncrude | D05 72kV Bus B | 2014-06-16 08:00 | 2014-06-25 16:00 | N | N | MLMR project 1375 | Bus |  |  | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2014-06-16 08:00 | 2014-06-16 16:00 | N | N | Breaker Mtc | Circuit Breaker |  |  | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap),7L760 (7L760D2 - 767s Oyen) | 2014-06-16 08:00 | 2014-06-19 14:00 | N | N | climbing inspection | Line |  | A PORTION OF 7L760 WILL BE REMOVED FROM SERVICE BX 7L760D1 & D2 FOR A CLIMBING INSPECTION 6L09 WILL BE OPEN between 763S HANNA AND 6L09D2 AT 776S RICHDALE FOR CONTINGENCY PURPOSES A PORTION OF 7L760 WILL BE REMOVED FROM SERVICE BX 7L760D3 & 760l41D2 FOR A CLIMBING INSPECTION 6L09 WILL BE OPEN ENDED AT 767S OYEN FOR CONTINGENCY PURPOSES Climbing Inspection | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR, ALTALINK | 809L (320p Keephills - 330p Genesee),320p96 (320p Keephills),320p98 (320p Keephills) | 2014-06-16 08:00 | 2014-06-24 08:00 | N | N | EPCOR to start line maintenance prior to connectionof 510s 138 kV equipment. | Line, Switch |  |  | For Information Only
ENMAX | 162s 138-RB82 (162s Beddington) | 2014-06-16 08:00 | 2014-06-16 16:00 | N | N | gas sample | Circuit Breaker |  |  | For Information Only
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2014-06-16 10:00 | 2014-06-19 12:30 | N | Y | Change STRs for Road improvements. STRs #174, and new # 174A. | Line |  |  | Creates Radial Feeds
ALTALINK | 17s 7 (17s Benalto) | 2014-06-16 12:00 | 2014-06-18 17:00 | N | Y | 240kV Breaker Maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2014-06-16 17:01 | 2014-06-25 14:30 | N | Y | FATD - SFTP: BYPASS # 1. Relocate a portion of 911L off of existing ROW to allow for new 1037/1038L | Line |  |  | 240 kV, Limits ATC
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-06-17 02:30 | 2014-06-17 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville),7L53 (700s Bonnyville - 706s Irish Creek) | 2014-06-17 07:00 | 2014-06-17 18:00 | N | N | to disconnect temporary 144kv bypass at 700s Bonnyville | Line |  | To disconnect temporary 144kv bypass at 700s Bonnyville | Overload, Over/Under Voltage
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2014-06-17 08:00 | 2014-06-18 16:00 | N | Y | cap switcher maintenance | Shunts |  |  | Limits ATC
ALTALINK | 370s 51 (370s North Lethbridge) | 2014-06-17 08:00 | 2014-06-17 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 746s T1 (746s Sherwood Park) | 2014-06-17 08:00 | 2014-06-19 17:00 | N | N | Bushing replacement, doble, SFRA, T/C issues & oil leaks | Transformer |  |  | For Information Only
ALTALINK | 89s 2152 (89s Ellerslie),89s 2252 (89s Ellerslie) | 2014-06-17 08:00 | 2014-06-19 17:00 | N | Y | 1206L end to end testing in preparation for 1206L energization at 500 kV. | Circuit Breaker |  |  | Pre-Condition, Overload, 500 kV
EPCOR | 987s C1 (987s Clover Bar),987s C72C1 (987s Clover Bar) | 2014-06-17 08:00 | 2014-06-17 16:00 | N | Y | breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | 987s CCP7214 (987s Clover Bar) | 2014-06-17 08:00 | 2014-06-17 12:00 | N | N | op checks on bus diff | Circuit Breaker |  |  | For Information Only
BLACKSPRING | 485s C2 (485s Blackspring) | 2014-06-17 12:30 | 2014-06-17 17:00 | N | Y | troubleshoot and repair | Shunts |  |  | For Information Only
ALTALINK | 477s T1 (477s Amoco West Pembina) | 2014-06-18 07:30 | 2014-06-19 20:00 | N | N | replace UG cables between 477s9 and 477s10 | Transformer
ENMAX | 41.1C (ENMAX 41),6.82L (ENMAX 6 - ENMAX 41) | 2014-06-18 08:00 | 2014-06-19 16:00 | N | Y | cap switcher maintenance | Shunts, Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ATCO | 7L70 (819s Whitby Lake - 936s Norberg) | 2014-06-18 08:00 | 2014-06-25 16:00 | N | N | Move 7L70 to new 7L139 bay, new breaker 704 at 819S Whitby Lake | Line |  | Move 7L70 to New 7L139 Bay, new breaker 704 at 819S Whitby Lake, new SLD HOP for 7L794 on permit 2-27012 | Pre-Condition
SUNCOR | 29EDD-1 29EDD1s 552 (29EDD-1 Millennium) | 2014-06-18 08:00 | 2014-06-20 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 7L30 (732s Mitsue - 844s AEC Mill),7L31 (732s Mitsue - 844s AEC MILL) | 2014-06-18 08:00 | 2014-06-18 17:00 | N | N | breaker test | Line |  | TESTING 844S AEC MILL BKRS 701, 702 AND RETRIEVING OIL SAMPLES FROM 700PT1 DURING PLANNED MILL SHUTDOWN THIS WORK IS IN CONJUNCTION WITH CROW #2-28364 | For Information Only
EPCOR | 987s CC24 (987s Clover Bar) | 2014-06-18 08:00 | 2014-06-18 12:00 | N | N | op checks on bus diff | Circuit Breaker
ALTALINK | 305s T2 (305s Acheson) | 2014-06-18 08:00 | 2014-06-18 17:00 | N | N | Doble and maintenance | Transformer |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2014-06-18 08:00 | 2014-06-18 16:00 | N | N | breaker maintenance | Line
ALTALINK | 331s T2 (331s Ponoka) | 2014-06-18 08:00 | 2014-06-18 17:00 | N | N | Investigate high-temp, suspicious RTD temperature sensor | Transformer |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2014-06-18 12:00 | 2014-06-20 15:00 | N | N | relay testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2014-06-18 12:00 | 2014-06-18 16:00 | N | N | CK726 op checks on bus diff | Line
ALTALINK | 102s SVC (102s Langdon),1113L (102s Langdon - 520s Bennett) | 2014-06-18 16:01 | 2014-06-19 10:00 | Y | Y | cut SVC free of old 102s252 & 102s552, bypass 102s1113, change controls to 102s7352 - WATL | Shunts, Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
EPCOR | 746AL (524s Fiberglass - 746L tap) | 2014-06-19 07:00 | 2014-06-19 13:00 | N | N | AltaLink - aerial transmission line work | Line
ALTALINK | 118s T2 (118s Canmore) | 2014-06-19 08:00 | 2014-06-19 17:00 | N | N | maintenance and replace filter hoses | Transformer
EPCOR | Strathcona S723 (Strathcona) | 2014-06-19 08:00 | 2014-06-19 16:00 | N | N | relay and breaker maintenance | Circuit Breaker
ALTALINK | 256s C1 (256s Harmattan),256s 53 (256s Harmattan) | 2014-06-19 08:00 | 2014-06-19 17:00 | N | Y | dashpot rebuild | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 83s C2 (83s Taber),83s 67 (83s Taber) | 2014-06-19 08:00 | 2014-06-19 16:00 | N | Y | maintenance | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 799s T1 (799s Coleman) | 2014-06-19 09:00 | 2014-06-19 17:00 | N | N | transformer doble and SFRA test | Transformer
ATCO | 749s 701 (749s Flyingshot Lake) | 2014-06-19 10:00 | 2014-06-19 17:00 | N | N | min oil HLR partial testing | Circuit Breaker |  | BREAKER 701 MIN OIL HLR PARTIAL TESTING | Contingency Requires Mitigation
BLACKSPRING | 485s C1 (485s Blackspring) | 2014-06-20 08:00 | 2014-06-20 12:00 | N | Y | troubleshoot and repair | Shunts |  |  | For Information Only
EPCOR | 987s CDS7 (987s Clover Bar) | 2014-06-20 08:00 | 2014-06-20 16:00 | N | N | sw repair | Switch
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2014-06-20 08:00 | 2014-06-20 16:00 | N | N | breaker maintenance | Line
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2014-06-20 08:30 | 2014-06-20 11:30 | N | N | inspect NGR & cables leaving station | Transformer
ALTALINK | 13L (65s High River - 392s Black Diamond),158L (65s High River - 392s Black Diamond) | 2014-06-20 14:55 | 2014-07-21 17:00 | N | N | forced outage due to flooding | Line |  |  | For Information Only
ENMAX | ENMAX 25 B240-D141 (ENMAX 25),ENMAX 25 B240-D140 (ENMAX 25),25PT240-Z44 (ENMAX 25) | 2014-06-20 18:00 | 2014-06-21 16:00 | N | Y | preliminary outage on the 240kV ring prior to back energization of GSU 3 and MD maint by EPC crews | Circuit Breaker, Terminal Equipment |  |  | 240 kV, For Information Only
ALTALINK | 310p 1852 (310p Sundance),310p 1752 (310p Sundance) | 2014-06-21 06:00 | 2014-06-21 18:00 | N | Y | trip test | Circuit Breaker |  |  | 240 kV
ALTALINK | 841L (477s Amoco West Pembina - 489s Amoco Canada Brazeau River) | 2014-06-21 07:00 | 2014-06-21 12:00 | N | N | test trip 477s841X breaker for bus protection upgrade that occurred June 18/19 | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2014-06-21 08:00 | 2014-06-21 16:00 | N | N | oil sample and contamination found | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1s 652 (29EDD-1 Millennium) | 2014-06-21 08:00 | 2014-06-24 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2014-06-21 08:00 | 2014-06-22 16:00 | N | N | breaker maintenance on 11B138-11.83 | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 844L (358s Amoco Brazeau - 477s Amoco West Pembina),477s 844X (477s Amoco West Pembina) | 2014-06-21 12:01 | 2014-06-21 16:00 | N | N | test trip breaker for bus protection upgrade that occurred June 18/19 | Circuit Breaker, Line
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake),157s21 (157s Lac La Biche) | 2014-06-22 08:00 | 2014-06-23 17:00 | N | N | to lift an A frame in to place as well as perform breaker tests on 702 | Switch, Line
ATCO | 7L794 (157s Lac La Biche - 819s Whitby Lake) | 2014-06-22 08:00 | 2014-06-23 17:00 | N | N | to lift an A frame in to place as well as perform breaker tests on 702 | Line |  | to lift an A frame in to place as well as perform breaker tests on 702 | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1115L (154s Black Spruce - 170s Pike),154s Black Spruce 240 kV Bus 2 | 2014-06-22 08:00 | 2014-06-30 08:00 | N | Y | test/commission new 1115L protections, close open point B | Bus, Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 170S Pike | 2014-06-22 08:00 | 2014-06-30 08:00 | N | N | isolate 170s to close open points & complete work prior to energization | Station
ALTALINK | 103s 1752 (103s Goose Lake) | 2014-06-23 08:00 | 2014-06-23 12:00 | N | N | Isolate B protection CT | Circuit Breaker |  |  | For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2014-06-23 08:00 | 2014-06-27 16:00 | N | N | 8.5TC upgrade ASEA - UZERT 550/300 tapchanger | Transformer |  |  | For Information Only
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2014-06-23 08:00 | 2014-06-23 16:00 | N | N | breaker maintenance & gas sample on 36B138-7.84 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2014-06-23 08:00 | 2014-07-18 16:00 | N | N | line differential, MD-capital, doble, and breaker inspection | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41),ENMAX 40 B138-40.81 (ENMAX 40) | 2014-06-23 08:00 | 2014-07-04 16:00 | N | N | MD-Capital(EPSC), LTC Mtce | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2014-06-23 08:00 | 2014-06-27 17:00 | N | Y | energization plan to restore NTL 2CB1 to service | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
Syncrude | Mildred_1015 (Syncrude Mildred Lake) | 2014-06-23 08:00 | 2014-06-29 16:00 | N | N | 5 year maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | RossdaleT3 (Rossdale) | 2014-06-23 08:00 | 2014-06-27 18:00 | N | N | trans maintenance -doble/SFRA.SAs178/179/180 and CVT101 | Transformer |  |  | For Information Only
EPCOR | 557s 2405 (557s Castle Downs) | 2014-06-23 08:00 | 2014-06-28 17:00 | N | Y | cutover new BF protection panel | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2014-06-23 09:00 | 2014-06-23 16:15 | N | N | high load move | Line |  | FOR HIGH LOAD MOVE | Over/Under Voltage, Creates Radial Feeds
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2014-06-23 09:00 | 2014-06-25 17:00 | N | N | pole changes | Line |  | POLE CHANGES | For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa) | 2014-06-23 10:00 | 2014-06-26 15:00 | N | N | line maintenance - insulator replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2014-06-23 10:00 | 2014-06-27 17:30 | N | Y | change STRs for Road improvements. STRs #174, and new # 174A | Line |  |  | Creates Radial Feeds
ALTALINK | 83s T1 (83s Taber) | 2014-06-23 10:00 | 2014-06-23 16:00 | N | N | close open point 'A' | Transformer |  |  | For Information Only
ALTALINK | 103s 1652 (103s Goose Lake) | 2014-06-23 12:30 | 2014-06-23 16:30 | N | N | Isolate B protection CT | Circuit Breaker |  |  | For Information Only
EPCOR | 809L (320p Keephills - 330p Genesee) | 2014-06-24 07:00 | 2014-07-05 16:00 | N | N | doble testing | Line |  |  | For Information Only
EPCOR | 809L (320p Keephills - 330p Genesee) | 2014-06-24 08:00 | 2014-07-10 18:00 | N | N | terminate at 510s for station service - WATL | Line |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays),121s 795X (121s Brooks) | 2014-06-24 08:00 | 2014-06-24 17:00 | N | N | 138kV SF6 breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary),5s C2 (5s East Calgary),5s 7 (5s East Calgary) | 2014-06-24 08:00 | 2014-07-30 16:00 | N | Y | ENMAX: cable pull & Structure installation | Circuit Breaker, Shunts |  |  | Limits ATC
ATCO | 741s 504C (741s Fox Creek) | 2014-06-24 08:00 | 2014-06-25 09:00 | N | N | replacement of the old capacitor bank after it has been OOS for a year | Shunts |  |  | For Information Only
ALTALINK | 38s 738W (38s East Edmonton) | 2014-06-24 08:00 | 2014-07-13 17:00 | N | N | rewire CTs in prep for 293s line moves | Circuit Breaker |  |  | For Information Only
ALTALINK | 310p 1852 (310p Sundance) | 2014-06-24 08:00 | 2014-06-26 17:00 | N | Y | HPF breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 55s T1 (55s Olds) | 2014-06-24 08:00 | 2014-06-25 17:00 | N | N | transformer doble and maintenance | Transformer
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-06-24 08:00 | 2014-06-25 16:00 | N | N | doble test 11B138-11.81 | Line |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2014-06-24 08:00 | 2014-06-25 12:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX | 21.80L (42s Sarcee - ENMAX 21),ENMAX 21 B138-21.80 (ENMAX 21) | 2014-06-24 08:00 | 2014-06-24 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
GREENGATEP | 615S Halkirk | 2014-06-24 09:00 | 2014-06-24 13:00 | N | N | DSTATCOM software upgrade | Station |  |  | For Information Only
EPCOR | Hardisty T3 (Hardisty),72CH9 (Hardisty - 987s Clover Bar) | 2014-06-25 06:00 | 2014-06-25 12:00 | N | N | op-checks on transformer protection | Transformer, Line |  |  | Creates Radial Feeds
EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia),240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2014-06-25 07:00 | 2014-11-15 18:00 | N | Y | reterminate and rebuild as required on the 240 Kv oil filled cable at 629s | Line |  |  | 240 kV, Pre-Condition
AESO | 893L (103s Goose Lake - 893BL tap),893BL (806s Oldman River Dam - 893BL tap),893L (893BL tap - 893AL tap),893L (312s Fidler - 893AL tap),893AL (112s Windy Point - 893AL tap) | 2014-06-25 08:00 | 2014-06-27 17:00 | N | N | complete connection to 312s, 893L will become normally open at 103s | Line |  |  | Restricts Generation
ALTALINK | 254s 172W (254s Coaldale),172L (370s North Lethbridge - 254s Coaldale) | 2014-06-25 08:00 | 2014-06-25 17:00 | N | N | 138kV SF6 breaker maintenance | Line, Circuit Breaker |  |  | Over/Under Voltage
ALTALINK | 624L (354s Summerview - 312s Fidler) | 2014-06-25 08:00 | 2014-06-25 10:00 | N | N | replace defective OHSW grip | Line |  |  | Restricts Generation
SUNCOR | 29EDD-1 29EDD1s 752 (29EDD-1 Millennium) | 2014-06-25 08:00 | 2014-06-27 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 103s 1652 (103s Goose Lake),103s 1752 (103s Goose Lake) | 2014-06-25 08:00 | 2014-07-04 17:00 | N | N | replace old line protections | Circuit Breaker |  |  | Pre-Condition, Overload, Impacts RAS
ATCO | 749s 702 (749s Flyingshot Lake) | 2014-06-25 10:00 | 2014-06-25 16:00 | N | N | breaker maintenance | Circuit Breaker |  | 749S FLYINGSHOT LAKE BKR 702 O/S FOR MTCE | Contingency Requires Mitigation
ALTALINK | 911L RAS,180L RAS,853L RAS | 2014-06-25 10:00 | 2014-06-25 11:00 | N | Y | Test the tripping to 485s Blackspring Ridge. | RAS |  |  | Limits ATC, Impacts RAS
ALTALINK | 62s12 (62s Brazeau) | 2014-06-25 12:00 | 2014-06-26 17:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 768L (217s North Red Deer - 87s Gaetz),217s 768 (217s North Red Deer) | 2014-06-26 08:00 | 2014-06-26 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 5s T2 (5s East Calgary) | 2014-06-26 08:00 | 2014-06-30 16:00 | N | Y | tie into 138 kV GIS @ 2s and close open point F | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 632PS (632s Russell) | 2014-06-26 08:00 | 2014-06-26 17:00 | N | Y | repair/investigate transformer leak | Transformer |  |  | For Information Only
AESO | 7L92 (819s Whitby Lake - 7L92D2) | 2014-06-26 08:00 | 2014-06-27 17:00 | N | N | upgrade breaker protection | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2014-06-26 08:00 | 2014-06-26 16:00 | N | N | breaker maintenance & gas sample on 20B138-1.81 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 755s 902 (755s Cordel) | 2014-06-26 09:00 | 2014-06-26 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO | 733s Simonette RTU/SCADA,813s Little Smoky RTU/SCADA | 2014-06-26 11:00 | 2014-06-26 15:00 | N | N | radio maintenance | Terminal Equipment |  |  | Affects Visibility
EPCOR | 987S Clover Bar 72 kV Bus 3 | 2014-06-27 | 2014-06-27 19:00 | N | N | maintenance | Bus
SUNCOR | 29EDD-1 29EDD1s 852 (29EDD-1 Millennium) | 2014-06-28 08:00 | 2014-07-01 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 2049S Kettle River | 2014-06-28 08:00 | 2014-07-04 16:00 | N | N | In service date: July 1, 2014 | Station
ALTALINK | 170S Pike | 2014-06-28 08:00 | 2014-07-04 16:00 | N | N | In service date: July 1, 2014 | Station
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2014-06-28 12:00 | 2014-06-28 16:00 | N | N | maintenance | Line
EPCOR | 987s T2 (987s Clover Bar),72CN10 (987s Clover Bar - Namao) | 2014-06-29 08:00 | 2014-06-29 22:00 | N | N | 72 kV bus 1 outage | Line, Transformer
ENMAX | 41.1TR (ENMAX 41) | 2014-06-30 08:00 | 2014-07-04 16:00 | N | N | MD-capital (EPSC) | Transformer
SUNCOR | 29EDD-1-T2 (29EDD-1 Millennium) | 2014-06-30 08:00 | 2014-07-07 19:00 | N | N | maintenance | Transformer |  |  | 240 kV, For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2014-06-30 08:00 | 2014-07-01 16:00 | N | N | doble and breaker maintenance | Line |  |  | Creates Radial Feeds
ENMAX | 8.1TR (ENMAX 8) | 2014-06-30 08:00 | 2014-07-04 16:00 | N | N | doble, secondary cable test, check reversing sw, gas relay test | Transformer |  |  | For Information Only
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2014-07-02 08:00 | 2014-07-03 15:00 | N | N | pole replacement on 6L12 | Line |  | Pole replacement on 6L12 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1s 952 (29EDD-1 Millennium) | 2014-07-02 08:00 | 2014-07-04 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
EPCOR | Rossdale C2,Rossdale R72C2 (Rossdale) | 2014-07-02 08:00 | 2014-07-04 16:00 | N | Y | inspection and repair | Shunts, Circuit Breaker |  |  | For Information Only
ATCO | 7L129 (526s Buffalo Creek - 710s Vermilion),710s 704 (710s Vermilion) | 2014-07-02 09:00 | 2014-07-03 17:00 | N | N | 710S - 704 breaker testing | Line, Circuit Breaker |  | 710S - 704 BREAKER BULK OIL KSO PARTIAL TESTING | Firm Load Loss, Creates Radial Feeds
ALTALINK | 605L (286s Yasa - 185s Bretville) | 2014-07-02 10:00 | 2014-07-03 17:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 151s T1 (151s Strathmore) | 2014-07-02 11:00 | 2014-07-04 17:00 | N | N | repair oil leaks | Transformer |  |  | For Information Only
ALTALINK | 55s T2 (55s Olds) | 2014-07-02 12:00 | 2014-07-03 17:00 | N | N | transformer doble and maintenance | Transformer |  |  | For Information Only
ALTALINK | 370s 47 (370s North Lethbridge) | 2014-07-03 08:00 | 2014-07-04 12:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2014-07-03 09:00 | 2014-07-03 16:00 | N | N | insulator pin replacement | Line |  |  | 240 kV, Overload
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2014-07-03 15:00 | 2014-07-03 17:00 | N | N | to replace a pole that was struck by lightning | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-07-04 07:00 | 2014-07-06 18:00 | N | Y | ECTP: install inter-phase spacers | Line |  |  | 240 kV, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (87s Gaetz - 63s Red Deer),87s 1652 (87s Gaetz) | 2014-07-04 07:30 | 2014-07-04 17:00 | N | Y | 240kV Breaker Maintenance | Line, Circuit Breaker |  |  | 240 kV, Limits ATC
ALTALINK | 199s C1 (199s East Ardrie) | 2014-07-04 08:00 | 2014-07-04 17:00 | N | Y | cap bank testing | Shunts |  |  | For Information Only
ALTALINK | 989L (310p Sundance - 77s Sagitawah) | 2014-07-04 09:00 | 2014-07-04 17:00 | N | N | insulator pin replacement | Line |  |  | 240 kV, Overload
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2014-07-05 08:00 | 2014-07-05 16:00 | N | N | Breaker maint at 15 sub , Breaker Doble at 21 sub | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2014-07-05 08:00 | 2014-07-05 19:00 | N | Y | end to end testing Z1 and Z2 trip between 162 and Altalink | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1s 1052 (29EDD-1 Millennium) | 2014-07-05 08:00 | 2014-07-08 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-07-07 02:30 | 2014-07-07 04:00 | N | N | High load move | Line |  |  | Creates Radial Feeds
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2014-07-07 07:30 | 2014-08-14 18:00 | N | Y | SFTP: Crossing #1, lower a portion of 911L to allow for new 1037/1038L to cross over top | Line |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2014-07-07 08:00 | 2014-07-07 16:00 | N | N | 31B138-9.80 BKR maint | Line
ENMAX | ENMAX 39 | 2014-07-07 08:00 | 2014-07-07 16:00 | N | N | 39 sub 138 kV PT- PTs doble | Station |  |  | For Information Only
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2014-07-07 08:00 | 2014-07-07 17:00 | N | N | change out rotten pole slated for change out & one O.H. guy pole vehicle struck & broke/ damper travel / damaged conductor & breaker maintenenance | Line |  | change out rotten pole slated for change out & one O.H. Guy pole vehicle struck & broke./ Damper travel / damaged conductor. | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Strathcona S723 (Strathcona) | 2014-07-07 08:00 | 2014-07-07 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | Kennedale T2 (Kennedale) | 2014-07-07 08:00 | 2014-07-11 16:00 | N | N | tapchanger repair | Transformer |  |  | For Information Only
EPCOR | Hardisty T2 (Hardisty) | 2014-07-07 08:00 | 2014-07-11 16:00 | N | N | doble/SFRA | Transformer |  |  | For Information Only
EPCOR | 557s T2 (557s Castle Downs) | 2014-07-07 08:00 | 2014-07-11 17:00 | N | Y | cutover new BF protection panel | Transformer |  |  | 240 kV, For Information Only
ENMAX | 34.1TR (ENMAX 34),34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2014-07-07 08:00 | 2014-07-11 16:00 | N | N | MD-capital, LTC maintenance, breaker inspection, doble, check reversing switch | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 898s 902T (898s Heart Lake) | 2014-07-07 10:00 | 2014-07-10 15:00 | N | N | ATCO info: transformer maintenance | Transformer
ALTALINK | 63s 152 (63s Red Deer) | 2014-07-07 10:00 | 2014-07-07 17:00 | N | Y | breaker maintenance, east and north phases low nitrogen | Circuit Breaker |  |  | 240 kV
TRANSALTA | 245s T2 (245s Seebe) | 2014-07-07 12:00 | 2014-07-09 17:00 | N | N | bushing oil leak | Transformer
ALTALINK | 185L (396s Pincher Creek - 379s Shell Canada Waterton) | 2014-07-07 12:00 | 2014-07-08 17:00 | N | N | 69kV breaker maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 410s T1 (410s Josephburg),410s Josephburg 138kV Bus 2 | 2014-07-07 13:00 | 2014-07-07 17:00 | N | Y | remove excess oil on SST2 to more appropriate level | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2014-07-07 14:30 | 2014-07-07 16:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 284s T1 (284s Nose Creek) | 2014-07-08 07:00 | 2014-07-08 19:00 | N | N | oil leak repair on T1 and customer switching | Transformer |  |  | For Information Only
ALTALINK | 172EL (139s Hillridge - 172EL1) | 2014-07-08 07:00 | 2014-07-08 18:00 | N | N | maintenance | Line |  |  | Restricts Generation
ALTALINK | 104s T1 (104s Watson Creek),104s 615 (104s Watson Creek) | 2014-07-08 08:00 | 2014-07-08 17:00 | N | N | T1 maintainteance/doble/oil leaks, hydran/idd/bushing monitor failure & breaker maintenance | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek) | 2014-07-08 08:00 | 2014-07-08 17:00 | N | N | Doble, maintenance, SFRA and leaks | Transformer |  |  | For Information Only
ALTALINK | 349S Stavely,197L (349s Stavely - 928s East Stavely) | 2014-07-08 08:00 | 2014-07-10 17:00 | N | Y | SFTP: lower a portion of 197L to allow for new 1037/1038L to cross over top | Line, Station |  |  | Restricts Generation, For Information Only
ALTALINK | 397s T1 (397s Benbow),720L (347s Fox Creek - 397s Benbow),397s Benbow 138kV Bus 1 | 2014-07-08 08:00 | 2014-07-08 17:00 | N | N | 397s1 & 397s2 switch adjustments | Bus, Transformer, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 767L (310p Sundance - 767L50),310p 767X (310p Sundance) | 2014-07-08 08:00 | 2014-07-09 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 410s T2 (410s Josephburg),410s Josephburg 240kV Bus 1,410s4 (410s Josephburg),410s14 (410s Josephburg) | 2014-07-08 08:00 | 2014-07-10 17:00 | N | Y | repair 240kV Disconnect 410s4 and 410s14 | Transformer, Bus, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2014-07-08 08:30 | 2014-07-09 17:30 | N | N | repair/replace poiles | Line |  | REPAIR/REPLACE POLES
ALTALINK | 170s Pike RTU/SCADA | 2014-07-08 11:00 | 2014-07-08 12:00 | N | N | upload SCADA file to RTU | Terminal Equipment
SUNCOR | 139S Hillridge | 2014-07-08 21:30 | 2014-10-03 19:00 | N | N | reactive power capability reduction | Station |  |  | For Information Only
ALTALINK | 58s T1 (58s Edson) | 2014-07-09 08:00 | 2014-07-09 17:00 | N | N | breaker maintenance and hot spot switches & bent switch repairs | Transformer
ENMAX | ENMAX 65 SW80 (ENMAX 65) | 2014-07-09 08:00 | 2014-07-09 16:00 | N | N | doble station service PT | Switch |  |  | For Information Only
EPCOR | 987s C1 (987s Clover Bar) | 2014-07-09 08:00 | 2014-07-09 18:00 | N | Y | C72C1 breaker maintenance | Shunts |  |  | For Information Only
ALTALINK | 217s C1 (217s North Red Deer) | 2014-07-09 08:00 | 2014-07-09 17:00 | N | N | cap bank emergency repair | Shunts |  |  | For Information Only
ALTALINK | 928S East Stavely,180L (255s Vulcan - 928s East Stavely),180L (15s Fort Macleod - 928s East Stavely),197L (349s Stavely - 928s East Stavely) | 2014-07-09 08:00 | 2014-07-09 17:00 | N | N | 928s180N and 928s180X both have low gas pressure | Station, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 865L (216s Knightsbridge - 38s East Edmonton) | 2014-07-09 08:00 | 2014-07-09 16:00 | N | N | 38s Partial 138kV Bus #2, install jumpers between 38s39 & 38s40 | Line |  |  | Creates Radial Feeds
ALTALINK | 221S Sunken Lake,703AL (221s Sunken Lake - 703L),703L (213s Hughenden - 703AL tap),703L (648s Metiskow - 703L) | 2014-07-09 08:00 | 2014-07-09 17:00 | N | N | energize new 221s T3, close open points | Station, Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 952_102 (29EDD-1 Millennium) | 2014-07-09 08:00 | 2014-07-11 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 38s T3 (38s East Edmonton) | 2014-07-09 08:00 | 2014-07-09 17:00 | N | N | oil leak, winding temperature gauge repair and wash | Transformer |  |  | For Information Only
ALTALINK | 170S Pike | 2014-07-09 08:00 | 2014-07-28 08:00 | N | N | replace radiators & adjust tap changer on TX 18888, repair oil relief valve on TX 18889, finish placing insulation gravel working offpunch list items | Station
ALTALINK | 183s Underwood | 2014-07-09 10:00 | 2014-07-28 08:00 | N | N | complete construction, close 183s open points | Station
ALTALINK | 1120L (410s Josephburg - 108s Amelia),410s 352 (410s Josephburg) | 2014-07-10 08:00 | 2014-07-10 15:00 | N | Y | repair 240kV disconnect 410s6 and CT valve leak 410s 352 | Circuit Breaker, Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 106s T1 (106s Paddle River),106s 744 (106s Paddle River) | 2014-07-10 08:00 | 2014-07-10 17:00 | N | N | T1 doble, maintenance, leaks, wash & breaker maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2014-07-10 08:00 | 2014-07-10 13:00 | N | N | pole replacement | Line |  | Pole Replacement 6L12 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 | 2014-07-10 08:00 | 2014-07-10 16:00 | N | N | SSV2 doble station service PT | Station |  |  | For Information Only
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2014-07-10 08:00 | 2014-07-10 16:00 | N | N | breaker maintenance 31B138-9.80 | Line |  |  | Overload, For Information Only
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek) | 2014-07-10 08:00 | 2014-07-10 17:30 | N | N | maintenance on line | Line |  | Install and or replace poles using digger derricks and or boom trucks. Add or replace crossarms. Add or replace insulators. replace str.219. OUTAGE TO BE IN CONJUNCTION WITH BKR 703@730S OUTAGE CROW # 2-28799.
ATCO | 7L97 (820s Hangingstone - 933s Tower Road) | 2014-07-10 08:00 | 2014-07-14 20:00 | N | N | repair & maintenance | Line |  | 7L97 WILL BE REMOVED FROM SERVICE TO OPEN TEMP JUMPER "J1" ENBRIDGE HAS BEEN INFORMED AND IS READY FOR THIS OUTAGE A PORTION OF 7L79 WILL BE REMOVED FROM SERVICE BX 7L97D1 & J1 TO REPLACE 7L97D2 WITH A NEW LS/LD SWITCH 7L97 WILL BE REMOVED FROM SERVICE TO CLOSE TEMP JUMPER "J1" ENBRIDGE HAS BEEN INFORMED AND IS READY FOR THIS OUTAGE | Firm Load Loss, Creates Radial Feeds
ALTALINK | 21S Marion | 2014-07-10 08:00 | 2014-07-10 17:00 | N | N | investigate recent NGR related trip | Station |  |  | For Information Only
ALTALINK | 268S Whitecourt | 2014-07-10 08:00 | 2014-07-10 17:00 | N | N | VR1 maintenance and doble | Station |  |  | Pre-Condition, For Information Only
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek),730s 703 (730s Rycroft) | 2014-07-10 10:00 | 2014-07-10 16:00 | N | N | maintenance | Circuit Breaker, Line |  | 730S 703 BREAKER SF6 HGF PARTIAL TESTING. OUTAGE TO BE IN CONJUNCTION WITH 7L73 LINE OUTAGE CROW # 2-28798. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 885s 501R (885s McMillan) | 2014-07-10 10:29 | 2014-07-10 17:00 | N | Y | breaker maintenance | Shunts |  | breaker maintenance | Pre-Condition, Over/Under Voltage
ALTALINK | 17s C1 (17s Benalto),17s 16 (17s Benalto) | 2014-07-11 08:00 | 2014-07-11 17:00 | N | Y | cap bank testing and vegetation control | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 410s T1 (410s Josephburg) | 2014-07-11 08:00 | 2014-07-11 17:00 | N | Y | Transformer maintenance. | Transformer |  |  | 240 kV
ATCO | 6L73 (729s Otauwau - 745s Slave Lake) | 2014-07-11 09:00 | 2014-07-11 11:00 | N | N | immediate replacement due to lightning struck pole | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2014-07-12 08:00 | 2014-07-13 16:00 | N | N | breaker maintenance & gas sample 37B138-37.81, relay testing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.80L (42s Sarcee - ENMAX 28) | 2014-07-12 08:00 | 2014-07-12 16:00 | N | N | breaker doble | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 952_103 (29EDD-1 Millennium) | 2014-07-12 08:00 | 2014-07-15 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 987S Clover Bar 72 kV Bus 3 | 2014-07-14 05:00 | 2014-07-14 20:00 | N | N | 987S 72 kV bus #2 off loading 72CK12 to be backfed from Kennedale | Bus |  |  | Restricts Generation
EPCOR | 987s CCP7214 (987s Clover Bar) | 2014-07-14 08:00 | 2014-07-14 16:00 | N | N | doble as required | Circuit Breaker |  |  | For Information Only
EPCOR | Rossdale VHBB1 (Rossdale) | 2014-07-14 08:00 | 2014-07-14 16:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 608L (59s Peigan - 528s Blue Trail Wind Farm),608L (418s Ardenville - 608L72) | 2014-07-14 08:00 | 2014-07-17 17:00 | N | Y | correct leaning structures | Line |  |  | Restricts Generation
ALTALINK | 215L (38s East Edmonton - 286s Yasa) | 2014-07-14 08:00 | 2014-07-18 17:00 | N | N | move 215L over to the next bay in substation | Line |  |  | Creates Radial Feeds
ENMAX | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24),24B138-24BT3 (ENMAX 24) | 2014-07-14 08:00 | 2014-07-14 16:00 | N | N | switch maintenance on 24.1TR MD | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),16.60L (ENMAX 34 - ENMAX 16) | 2014-07-14 08:00 | 2014-07-23 16:00 | N | N | replace wood pole anchor with a steel mono pole | Line |  |  | Creates Radial Feeds
ENMAX | ENMAX 14 ,14.1C (ENMAX 14),14.2C (ENMAX 14),14.3TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2014-07-14 08:00 | 2014-07-25 16:00 | N | N | MD-Capital 14.1TR & 14.3TR (EPSC), Doble (14.1) | Station, Transformer, Line, Shunts |  |  | Pre-Condition, Overload
ATCO | 7L97 (820s Hangingstone - 933s Tower Road) | 2014-07-14 08:00 | 2014-07-14 20:00 | N | N | close jumper | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred_1225 (Syncrude Mildred Lake) | 2014-07-14 08:00 | 2014-07-20 16:00 | N | N | 5 year maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2014-07-14 08:00 | 2014-07-18 16:30 | N | Y | repalce 310p22A, beakers at 39s will also be out-of-service | Line |  |  | 240 kV, Over/Under Voltage
ALTALINK | 723L (438s Westlock - 150s Clyde) | 2014-07-14 09:00 | 2014-07-18 15:00 | N | N | replace PTs/J-Box associated with 69s48 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 789s 702 (789s Keg River) | 2014-07-14 13:00 | 2014-07-15 16:00 | N | N | 789s Keg River breaker 702 maintenance | Circuit Breaker |  | 789S KEG RIVER BKR 702 O/S FOR MTCE 7L62D2 WILL BE CLOSED TYING 7L62 & 7L64 TOGETHER FOR THE DURATION THEREFORE RELAY SETTINGS WILL NEED TO BE CHANGED @ 905S MEIKLE & 930S ARCENCIEL THIS PERMIT HAS BEEN RE-SCHEDULED | Pre-Condition
ATCO | 789s 702 (789s Keg River) | 2014-07-14 13:00 | 2014-07-15 16:00 | N | N | maintenance and testing | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 254s T1 (254s Coaldale) | 2014-07-14 13:00 | 2014-07-17 17:00 | N | N | maintain and doble transformer and perform ABB breaker maintenance | Transformer
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2014-07-14 13:00 | 2014-07-15 01:00 | Y | N | point of wave test on new breaker | Line |  |  | Pre-Condition
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2014-07-14 13:00 | 2014-07-17 17:00 | N | N | maintenance, doble, SFRA leaks, filter trouble and gauge replacement | Transformer
ATCO | 700s 705C (700s Bonnyville),700s 706C (700s Bonnyville),700s 707C (700s Bonnyville) | 2014-07-15 07:00 | 2014-07-19 12:00 | N | Y | salvage 700D3 disconnect and connect 7L24 to new location | Shunts |  | Salvage 700D3 disconnect Connect new 7L24 bay to existing 144kv buss at 700D3's old location. | Pre-Condition, For Information Only
ALTALINK | 185L (396s Pincher Creek - 379s Shell Canada Waterton) | 2014-07-15 08:00 | 2014-07-15 17:00 | N | N | install screw pile for future mobile connection point | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2014-07-15 08:00 | 2014-07-15 17:00 | N | N | change out damaged poles and conductor | Line |  | change out rotten pole slated for change out & one O.H. Guy pole vehicle struck & broke./ Damper travel / damaged conductor. ADVISE DEVON CANADA OF OUTAGE AND NO MOTOR STARTS. (POSSIBLE VOLTAGE ISSUES). THEY CAN BE CONTACTED AT 780-835-5059. PLEASE GIVE THEM A HEADS UP PRIOR TO THE OUTAGE. | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2014-07-15 08:00 | 2014-07-15 16:00 | N | N | transfer of open point to allow coble testing | Line |  |  | For Information Only
ENMAX | 21.1C (ENMAX 21),ENMAX 21 B138-21.CAP (ENMAX 21) | 2014-07-15 08:00 | 2014-07-15 16:00 | N | Y | breaker maintenance | Shunts, Circuit Breaker |  |  | Limits ATC
ALTALINK | 310P T36 (310p Sundance) | 2014-07-15 08:00 | 2014-07-17 17:00 | N | Y | bushing replacement and valve leak repair | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-07-15 08:00 | 2014-07-15 16:00 | N | N | doble breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 1212L (89s Ellerslie - 12s Heartland),89s 1852 (89s Ellerslie),89s 1952 (89s Ellerslie) | 2014-07-15 08:00 | 2014-07-23 08:00 | N | Y | line to remain out of service while 1206L is energized. Need to have 89s 500 kV Bus #2 outage to facilitate final connection of line | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 551s T1 (551s Chevron Kaybob) | 2014-07-15 08:00 | 2014-07-15 17:00 | N | N | bushing replacement. | Transformer |  |  | For Information Only
ATCO | 795s 701T (795s Zama) | 2014-07-15 09:30 | 2014-07-15 15:00 | N | N | complete bird proofing repairs | Transformer |  | Complete Bird Proofing Repairs REplace Damged Bird Proofing and confirm Regulator Schematic Diagram/Operation -------- Load Transfer -------- 795S 5L364 Peak Load =1.5 MVA 795S 5L200 Peak Load = 1.5 MVA 795S 5L364 Relay Settings: 8.66 mva 795S 5L200 Relay Settings: 6.93 mva -------- Load Transfer -------- | For Information Only
ALTALINK | 54s C1 (54s Fort Saskatchewan) | 2014-07-15 12:00 | 2014-07-15 13:00 | N | Y | weed control | Shunts
ATCO | 6L05 (764s Heisler - 843s Bigknife Creek),7L701 (757s Battle River - 7L701D2) | 2014-07-16 06:30 | 2014-07-16 17:00 | N | N | realign blade stops and set blades on disconnect 707Y | Line
ATCO | 6L05 (764s Heisler - 843s Bigknife Creek),7L701 (757s Battle River - 7L701D2) | 2014-07-16 06:30 | 2014-07-16 17:00 | N | N | maintenance | Line |  | A PORTION OF 7L701 WILL BE REMOVED FROM SERVICE TO PERFORM MTCE ON 757S 707Y 764S HEISLER BKR 601 WILL BE OPENED FOR CONTINGENCY PURPOSES PRIOR TO THE OUTAGE PROCEEDING | Pre-Condition, Overload, Over/Under Voltage
ENMAX | 162s 138-RB81 (162s Beddington) | 2014-07-16 08:00 | 2014-07-16 16:00 | N | N | breaker maintenance and gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2014-07-16 08:00 | 2014-07-16 16:00 | N | N | breaker doble | Circuit Breaker
VISIONREQ | 354s DVAR1 (354s Summerview),354s DVAR2 (354s Summerview) | 2014-07-16 08:00 | 2014-07-16 16:00 | N | N | DVAR anti islanding upgrade | Shunts |  |  | For Information Only
ALTALINK | 331s T1 (331s Ponoka) | 2014-07-16 08:00 | 2014-07-16 17:00 | N | N | repair oil leak | Transformer
ALTALINK | 320pT5 (320p Keephills) | 2014-07-16 08:00 | 2014-07-16 17:00 | N | N | replace 69 kV LA's | Transformer
SUNCOR | 29EDD-1 952_105 (29EDD-1 Millennium) | 2014-07-16 08:00 | 2014-07-18 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 7L47 (848s Ruth Lake - 718s Parsons Creek),848s 702 (848s Ruth Lake) | 2014-07-16 08:30 | 2014-07-16 17:30 | N | N | breaker maintenance | Line, Circuit Breaker |  | BREAKER 702 MAINT. | Pre-Condition
ATCO | 789s 701R (789s Keg River) | 2014-07-16 09:00 | 2014-07-16 16:15 | N | Y | partial breaker maintenance | Shunts |  | Partial Breaker 705 PM | For Information Only
ATCO | 795s 702T (795s Zama) | 2014-07-16 09:30 | 2014-07-16 15:00 | N | N | repair bird proofing material & complete repairs | Transformer |  | Repair Bird Proofing Material Comlpete Repairs to missing/damaged birdproofing material, also the regulator control will be changed and commisioned during this outage. -------- Load Transfer -------- 795S 5L200 Peak Load = 1.50 MVA 795S 5L364 Peak Load = 1.50 MVA 795S 5L178 Peak Load = 1.50 MVA 795S 5L200 Relay Settings:6.93 MVA 795S 5L178 Relay Settings: 6.93 MVA 795S 5L364 Relay Settings:8.66 MVA -------- Load Transfer --------
ENMAX | 162s 138-RB82 (162s Beddington) | 2014-07-17 08:00 | 2014-07-17 16:00 | N | N | breaker maintenance and gas sample | Circuit Breaker |  |  | For Information Only
ALTALINK | 38s 75 (38s East Edmonton) | 2014-07-17 10:00 | 2014-07-17 10:30 | N | N | trip test 38s75 for new 38s215N breaker fail | Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton),38s 761N (38s East Edmonton) | 2014-07-17 11:00 | 2014-07-17 11:30 | N | N | trip test 38s761N for new 38s215N breaker fail | Line, Circuit Breaker |  |  | Pre-Condition, Overload
EPCOR | Strathcona S722 (Strathcona) | 2014-07-18 08:00 | 2014-07-18 18:00 | N | N | breaker maintenance | Circuit Breaker
ALTALINK | 89s T2 (89s Ellerslie),89s Ellerslie 500kV Bus 2 | 2014-07-18 08:00 | 2014-07-22 17:00 | N | Y | final connection of 1212L to diameter bus work at 89s. *** Per ID 2013-004R, the amount of curtailment will be calculated based on expected conditions and reflected on the 24 Month Supply and Demand graph.*** | Transformer, Bus |  |  | Pre-Condition, Overload, 500 kV
ENMAX | 26.81L (ENMAX 54 - ENMAX 26) | 2014-07-19 08:00 | 2014-07-20 16:00 | N | N | doble 26B138-26.81, 26B138-BT3, 26PT138-Z31, and 26PT138-26.81 at 26 sub & Gas sample on 26B138-26.81, 26B138-BT3 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2014-07-19 08:00 | 2014-07-20 16:00 | N | N | sheath/oil testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 952_106 (29EDD-1 Millennium) | 2014-07-19 08:00 | 2014-07-21 20:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK, AESO | 332s 784E (332s Ellis),784L (332s Ellis - 784AL tap) | 2014-07-20 08:00 | 2014-07-20 17:00 | N | N | trouble repair | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2014-07-21 07:00 | 2014-08-09 09:00 | N | N | line rebuild( 2nd phase) | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 434s T3 (434s East Stony Plain) | 2014-07-21 08:00 | 2014-07-26 17:00 | N | N | doble and transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 32B138-32BT5 (ENMAX 32) | 2014-07-21 08:00 | 2014-07-21 16:00 | N | N | breaker maintenance and gas sample | Circuit Breaker
EPCOR | Rossdale VHBB2 (Rossdale) | 2014-07-21 08:00 | 2014-07-25 16:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2014-07-21 08:00 | 2014-07-21 16:00 | N | N | doble as required | Line
Syncrude | Mildred_1315 (Syncrude Mildred Lake) | 2014-07-21 08:00 | 2014-07-27 16:00 | N | N | 5 year maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198) | 2014-07-21 09:00 | 2014-07-21 17:00 | N | N | customer annual maintenance | Line |  |  | Pre-Condition, Restricts Generation, For Information Only
ALTALINK | 723L (69s North Barrhead - 723L133) | 2014-07-21 09:00 | 2014-07-25 15:00 | N | N | line maintenance - structure replacement | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
SHELL | 402s T1 (402s Shell Expansion 1) | 2014-07-21 10:00 | 2014-07-23 12:00 | N | N | transformer testing | Transformer |  | 402S - 701T TRANSFORMER CLASS1 MAJOR TESTING | For Information Only
ATCO | 848s 605 (848s Ruth Lake) | 2014-07-21 10:00 | 2014-07-22 17:00 | N | N | breaker maintenance | Circuit Breaker |  | 848S RUTH LAKE BKR 605 O/S FOR MTCE | For Information Only
ATCO | 959S SVC (959s Lanfine),959S 900BS3 | 2014-07-21 11:00 | 2014-07-25 17:00 | N | Y | testing & commissioning | Terminal Equipment, Shunts |  | 959S Lanfine - Equipment Logic testing on 900BS3 Tie in interconnects between SVC side and Substation Side. - Commission Wiring between SVC and Substation - Perform Logic testing between SVC and Substation | 240 kV
ALTALINK | 866s T1 (866s Sundance Make-Up) | 2014-07-21 11:00 | 2014-07-23 12:30 | N | N | Doble, leaks and maintenance | Transformer |  |  | For Information Only
ALTALINK | 56s C1 (56s Boyle) | 2014-07-21 12:00 | 2014-07-21 13:00 | N | Y | weed spraying | Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 370s 23 (370s North Lethbridge) | 2014-07-21 12:00 | 2014-07-23 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 123s T1 (123s Banff) | 2014-07-21 13:00 | 2014-07-22 17:00 | N | N | maintenance & doble | Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2014-07-21 13:00 | 2014-07-24 12:00 | N | N | pole replacement | Line |  | Pole Repl 6L09 Replace pole on 6L09 | Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-07-22 02:00 | 2014-07-22 04:00 | N | N | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 138-RB80 (162s Beddington) | 2014-07-22 08:00 | 2014-07-22 16:00 | N | N | Gas sample | Circuit Breaker
EPCOR | 987s C1 (987s Clover Bar),987s C72C1 (987s Clover Bar) | 2014-07-22 08:00 | 2014-07-22 16:00 | N | Y | Doble as required | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2014-07-22 08:00 | 2014-07-24 17:00 | N | N | transformer doble, maintenance & leak repair | Transformer
ENMAX | 30.81L (42s Sarcee - ENMAX 30),ENMAX 30 B138-30.81 (ENMAX 30) | 2014-07-22 08:00 | 2014-07-22 16:00 | N | N | dole breaker | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 786s SVC (786s High Level) | 2014-07-22 08:30 | 2014-07-22 16:30 | N | Y | Semi-annual maintenance and some PLC program changes. | Shunts |  | Semi-annual cooling maintenance will be completed along with some PLC program changes. PLC Changes will be commissioned. Transformer is seeping oil, leak will be investigated and cleaned/repaired. Sask Power will also be present for a site visit with Adam Burlock. | Pre-Condition
ATCO | 820s 505C1 (820s Hangingstone),820s 505C2 (820s Hangingstone),820s 701T (820s Hangingstone),7L97 (820s Hangingstone - 933s Tower Road) | 2014-07-23 08:00 | 2014-07-24 17:00 | N | Y | maintenance | Transformer, Line, Shunts |  | 701T WILL BE REMOVED FROM SERVICE & 7L97 WILL BE OPEN ENDED @ 820S HANGINGSTONE FOR MTCE ON 701TCS & BKR 702 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
TRANSALTA | 59s 852 (59s Peigan) | 2014-07-23 08:00 | 2014-07-23 17:00 | N | N | 240kV breaker maintenance | Circuit Breaker
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2014-07-23 08:00 | 2014-07-23 16:00 | N | N | doble 65B138-D85 | Circuit Breaker
ALTALINK | 123s T2 (123s Banff) | 2014-07-23 08:00 | 2014-07-24 17:00 | N | N | maintenance, doble | Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2014-07-23 08:00 | 2014-07-24 16:00 | N | N | BKR maint 6B138-6.82 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2014-07-23 08:05 | 2014-09-26 16:00 | N | N | forced outage due to a cable fault | Line |  |  | For Information Only
ATCO | 749s 704 (749s Flyingshot Lake) | 2014-07-23 09:00 | 2014-07-23 17:00 | N | N | maintenance | Circuit Breaker |  | 749S FLYINGSHOT LAKE BKR 704 O/S FOR MTCE
ATCO | 6L11 (742s Freeman Lake - 743s Sarah Lake) | 2014-07-23 09:00 | 2014-07-23 13:00 | N | N | 6L11 WILL BE OPEN ENDED @ 743S SARAH LAKE FOR MTCE ON BKR 603 | Line |  | 6L11 WILL BE OPEN ENDED @ 743S SARAH LAKE FOR MTCE ON BKR 603 | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
SHELL | 402s T2 (402s Shell Expansion 1) | 2014-07-23 13:00 | 2014-07-25 16:00 | N | N | COG FROM SHELL / 52-1B AND SECONDARY PT's OPEN AND TAGGED | Transformer |  | COG FROM SHELL / 52-1B AND SECONDARY PT's OPEN AND TAGGED
ATCO | 706s 703 (706s Irish Creek) | 2014-07-24 08:00 | 2014-07-24 12:00 | N | N | test trip/close circuit addition from breaker fail 704 relay Test and operate 703 before 7L53/7L117 bypass is removed and after 702 is closed in permit #2-27849 | Circuit Breaker |  | test trip/close circuit addition from breaker fail 704 relay Test and operate 703 before 7L53/7L117 bypass is removed and after 702 is closed in permit #2-27849 | For Information Only
ATCO | 6L97 (735s Swan River - 739s Edith Lake),739s 603 (739s Edith Lake),735s 603 (735s Swan River) | 2014-07-24 08:00 | 2014-07-24 13:00 | N | N | breaker maitenance | Line, Circuit Breaker |  | 6L97 WILL BE REMOVED FROM SERVICE @ 739S EDITH LAKE FOR MTCE ON BKR 603 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 19s T8 (19s Wabamun) | 2014-07-24 08:00 | 2014-07-24 17:00 | N | N | bushing replacement | Transformer |  |  | Contingency Requires Mitigation
ALTALINK | 821L (158s Vauxhall - 421s Hays),421s 821W (421s Hays) | 2014-07-24 08:00 | 2014-07-24 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 6,6.1TR (ENMAX 6) | 2014-07-24 08:00 | 2014-07-24 16:00 | N | N | doble 138KV PT's, test gas relay and bushing DGA | Station, Transformer |  |  | For Information Only
ALTALINK | 739L (305s Acheson - 434s Stony Plain),434s 739E (434s Stony Plain) | 2014-07-24 09:00 | 2014-07-24 13:00 | N | N | repair 434s2 | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 56s T2 (56s Boyle) | 2014-07-24 14:00 | 2014-08-04 12:00 | N | N | replace T2 transformer | Transformer
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-07-25 23:00 | 2014-07-26 02:00 | N | N | high load move | Line |  |  | Pre-Condition
ALTALINK | 454s T2 (454s Buck Lake) | 2014-07-26 08:00 | 2014-08-01 16:00 | N | N | ISD= July 29, 2014 | Transformer
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2014-07-26 08:00 | 2014-07-26 16:00 | N | N | doble 11B138-11.83 | Line |  |  | Pre-Condition, Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2014-07-26 08:00 | 2014-07-27 16:00 | N | N | sheath/oil testing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s 4 (33s Spray) | 2014-07-27 19:00 | 2014-08-01 17:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21),ENMAX 21 60S50 (ENMAX 21) | 2014-07-28 07:00 | 2014-08-09 17:00 | N | N | line protection upgrade & breaker CT replacement | Line, Circuit Breaker |  |  | For Information Only
Syncrude | Syncrude Mildred Lake | 2014-07-28 08:00 | 2014-08-02 16:00 | N | N | 2 X 10 MVAr 13.8 kV Cap Bank, In service date: August 1, 2014 | Station
ALTALINK | 434s T1 (434s East Stony Plain) | 2014-07-28 08:00 | 2014-07-31 12:00 | N | N | replace 434s29, bird cover-up install | Transformer
EPCOR | 557s T2 (557s Castle Downs) | 2014-07-28 08:00 | 2014-07-28 16:00 | N | Y | P&C control cable installation | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 420s 2032 (420s Broadmoor) | 2014-07-28 08:00 | 2014-08-07 17:00 | N | N | install new PTs, CTs, metering etc for new 420s2032 breaker at 25kV | Circuit Breaker
ENMAX | 16.61L (ENMAX 16 - ENMAX 27),16B69-16.61 (ENMAX 16) | 2014-07-28 08:00 | 2014-07-28 16:00 | N | N | maintenance | Circuit Breaker, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 826s 503R (826s Marguerite Lake),826s 504R (826s Marguerite Lake),826s 902T (826s Marguerite Lake) | 2014-07-28 09:00 | 2014-07-30 16:00 | N | Y | repair leak | Shunts, Transformer |  | 826S MARGUERITE LAKE 902T O/S TO REPAIR LEAK STATION WILL BE ON ALTERNATE STATION SERVICE FROM 822S WOLF LAKE 5L263 | For Information Only
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2014-07-28 11:00 | 2014-07-28 15:00 | N | N | replace pole | Line |  | A PORTION OF 6L03 WILL BE REMOVED FROM SERVICE BX 775S SULLIVAN LAKE TO 6L03D3 T-TAP TO REPLACE A POLE | Firm Load Loss, Creates Radial Feeds
ATCO | 813s 501R (813s Little Smoky),813s 901T (813s Little Smoky) | 2014-07-28 13:00 | 2014-07-30 17:00 | N | Y | maintenance | Transformer, Shunts |  | 813S LITTLE SMOKY 901T O/S FOR MTCE | 240 kV, For Information Only
ALTALINK | 89s 952 (89s Ellerslie) | 2014-07-28 13:00 | 2014-07-31 17:00 | N | Y | breaker maintenance & replace capacitor | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 396s C1 (396s Pincher Creek) | 2014-07-28 13:00 | 2014-07-28 14:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
Syncrude | Syncrude Plant 30-2 | 2014-07-29 08:00 | 2014-08-02 16:00 | N | N | 1 X 20 MVAr cap bank (Aurora), In service date: August 1, 2014 | Station
ENMAX | 16.61L (ENMAX 16 - ENMAX 27),16B69-16.61 (ENMAX 16) | 2014-07-29 08:00 | 2014-07-29 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds
ALTALINK | 498s T1 (498s Tilley) | 2014-07-29 08:00 | 2014-07-29 16:30 | N | N | control cabinet wiring corrections | Transformer |  |  | For Information Only
ALTALINK | 310p 1552 (310p Sundance) | 2014-07-29 08:00 | 2014-07-31 17:00 | N | Y | breaker HPF maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 445s T1 (445s Elk River) | 2014-07-29 08:00 | 2014-07-29 17:00 | N | N | SCADA equipment upgrade project | Transformer |  |  | For Information Only
ALTALINK | 421s C1 (421s Hays) | 2014-07-29 08:00 | 2014-07-29 09:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
AESO | 788L (157s Lac La Biche - 788L Tap) | 2014-07-29 08:00 | 2014-07-29 16:00 | Y | N | emergency repair 788L106B | Line |  |  | For Information Only
ALTALINK | 310P T36 (310p Sundance) | 2014-07-29 08:00 | 2014-07-29 17:00 | N | N | install bushing monitors | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress) | 2014-07-29 08:00 | 2014-07-31 16:00 | N | Y | SCADA equipment upgrade project | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 183s Underwood | 2014-07-29 08:00 | 2014-08-02 16:00 | N | N | In service date: August 1, 2014 | Transformer
ATCO | 959S 722C (959S Lanfine),959S 723C (959S Lanfine) | 2014-07-29 08:00 | 2014-07-30 16:00 | N | Y | improving closing sequence for the capacitor banks | Shunts |  | Improving closing sequence for the capacitor banks. | For Information Only
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek) | 2014-07-29 08:00 | 2014-07-29 17:30 | N | N | install and or replace poles using digger derricks and or boom trucks. Add or replace crossarms, add or replace insulators, replace str.219 | Line |  | Install and or replace poles using digger derricks and or boom trucks. Add or replace crossarms. Add or replace insulators. replace str.219. | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2014-07-29 08:00 | 2014-07-29 16:00 | N | N | maintenance K721 breaker at Kennedale | Line |  |  | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2014-07-29 08:00 | 2014-07-29 16:00 | N | N | maintenance on CH724 breaker at 987S Clover Bar | Line |  |  | For Information Only
ALTALINK | 723L (69s North Barrhead - 723L133) | 2014-07-29 09:00 | 2014-07-30 17:00 | N | N | line maintenance - structure replacement | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 732s 703 (732s Mitsue) | 2014-07-29 09:30 | 2014-07-30 15:30 | N | N | maintenance | Circuit Breaker |  | 732S MITSUE BKR 703 O/S FOR MTCE | For Information Only
ALTALINK | 498s C1 (498s Tilley),498s 33 (498s Tilley) | 2014-07-29 11:00 | 2014-07-29 12:00 | N | Y | cap bank weed control work | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 431s C1 (431s Hussar),431s 152 (431s Hussar) | 2014-07-29 14:00 | 2014-07-29 15:00 | N | Y | cap bank weed control work | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 183s Underwood | 2014-07-29 16:00 | 2014-08-01 09:00 | N | N | Isolate 183s until Aug 1 ISD | Transformer |  |  | For Information Only
ENMAX | 21.1C (ENMAX 21),ENMAX 21 B138-21.CAP (ENMAX 21) | 2014-07-30 08:00 | 2014-07-30 16:00 | N | Y | beaker maintenance | Shunts, Circuit Breaker |  |  | Limits ATC, For Information Only
EPCOR | Kennedale T2 (Kennedale) | 2014-07-30 08:00 | 2014-07-30 16:00 | N | N | doble testing. | Transformer |  |  | For Information Only
ENMAX | 26.83L (ENMAX 65 - ENMAX 26),26B138-26.83 (ENMAX 26),ENMAX 65 B138-D85 (ENMAX 65),ENMAX 65 B138-D84 (ENMAX 65) | 2014-07-30 08:00 | 2014-07-30 16:00 | N | N | doble 65PT138-26.83 and doble 65LA138-26.83L-C | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 445s T2 (445s Elk River) | 2014-07-30 08:00 | 2014-07-30 17:00 | N | N | SCADA equipment upgrade | Transformer |  |  | For Information Only
ALTALINK | 83s C1 (83s Taber),83s 61 (83s Taber) | 2014-07-30 08:00 | 2014-07-30 09:00 | N | Y | cap bank weed control work | Shunts, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 498s T2 (498s Tilley) | 2014-07-30 08:00 | 2014-07-30 16:30 | N | N | control cabinet wiring corrections | Transformer |  |  | For Information Only
ATCO | 834s 502R (834s Wesley Creek),834s502 (834s Wesley Creek) | 2014-07-30 08:00 | 2014-07-30 16:30 | N | Y | breaker maintenance | Shunts, Circuit Breaker |  | At 834s 502R will be out of service because of work on 502 breaker. | Pre-Condition, For Information Only
ALTALINK | 83s C2 (83s Taber),83s 67 (83s Taber) | 2014-07-30 09:00 | 2014-07-30 10:00 | N | Y | capacitor bank weed control | Shunts, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 523s C1 (523s Bullshead),523s 33 (523s Bullshead) | 2014-07-30 12:00 | 2014-07-30 13:00 | N | Y | Capacitor band weed control. | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
EPCOR | NamaoT3 (Namao),Namao N723 (Namao) | 2014-07-30 12:00 | 2014-07-30 14:00 | N | N | Emergency transformer wiring changes. | Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 7L89 (721s La Corey - 700s Bonnyville) | 2014-07-31 07:00 | 2014-08-03 17:00 | N | N | lower 7L89 line in order to maintain phase clearances crossing of new 7L146 to 700s Bonnyville | Line |  | Lower 7L89 line in order to maintain phase clearances crossing of new line 7L146 going to 700s Bonnyville substation | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 723L (438s Westlock - 723L) | 2014-07-31 08:00 | 2014-07-31 15:00 | N | N | Line maintenance - structure replacement | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2014-07-31 08:00 | 2014-07-31 16:00 | N | N | doble, maintenance at ENMAX 26 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (58s Edson - 178s Cynthia),178s27 (178s Cynthia) | 2014-07-31 08:30 | 2014-07-31 14:00 | N | N | 178s27 switch repairs | Line, Switch |  |  | Pre-Condition
ATCO | 732s 706 (732s Mitsue) | 2014-07-31 09:00 | 2014-07-31 16:00 | N | N | miantenance | Circuit Breaker |  | 732S MITSUE BKR 706 O/S FOR MTCE | For Information Only
ALTALINK | 163s C1 (163s Amoco Empress) | 2014-07-31 11:00 | 2014-07-31 12:00 | N | N | cap bank weed control work | Shunts |  |  | For Information Only
ALTALINK | 163s C2 (163s Amoco Empress) | 2014-07-31 12:00 | 2014-07-31 13:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
ALTALINK | 434s T3 (434s East Stony Plain) | 2014-07-31 12:01 | 2014-07-31 17:00 | N | N | close open point 'A' | Transformer |  |  | For Information Only
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2014-08-01 08:00 | 2014-08-01 17:00 | N | N | clearance for new 144 kV lnes | Line |  | GOI FOR CLEARENCE FROM 6L82 TO NEW 144KV LINES | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 183s Underwood | 2014-08-01 09:00 | 2014-08-01 11:00 | N | N | re-energize 183s underwood | Station
ATCO | 732s 703 (732s Mitsue) | 2014-08-01 15:00 | 2014-08-05 16:00 | N | N | forced outage | Circuit Breaker |  |  | Pre-Condition, For Information Only
ATCO | 732s 703 (732s Mitsue) | 2014-08-01 15:00 | 2014-08-05 16:00 | N | N | forced outage | Circuit Breaker
ENMAX | 22.81L (ENMAX 22 - ENMAX 39),22B138-22.81 (ENMAX 22) | 2014-08-02 08:00 | 2014-08-03 16:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2014-08-02 08:00 | 2014-08-03 16:00 | N | N | sheath test | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville) | 2014-08-04 07:00 | 2014-08-06 19:00 | N | N | swing over 7L24 into newly constructed 144 kV bay to make room for 7L146 | Line |  | Swing over 7L24 into newly constructed 144kv Bay to make room for 7L146. | Firm Load Loss, Creates Radial Feeds
BCH | 2L112 (Nelway - Boundary) | 2014-08-04 09:00 | 2014-08-08 17:00 | N | N | BPA work | Line |  |  | Limits ATC
ALTALINK | 56s T2 (56s Boyle) | 2014-08-04 13:00 | 2014-08-28 08:00 | N | N | build new switch gear equipment | Transformer
ATCO | 716s 701T (716s Lloydminster) | 2014-08-05 07:00 | 2014-08-05 17:00 | N | N | investigate and test relay (emergency) | Transformer
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2014-08-05 07:30 | 2014-08-07 17:00 | N | Y | replace 914L 'B' protection, 'A' protection to remain in place at all times | Line |  |  | 240 kV, Limits ATC
ATCO | 7L42 (751s Hill - 716s Lloydminster),751s 702 (751s Hill) | 2014-08-05 08:00 | 2014-08-06 15:00 | N | N | breaker testing | Circuit Breaker, Line |  | 751S - 702 BREAKER SF6 HGF COMPLETE TESTING | For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-08-05 08:00 | 2014-08-22 16:00 | N | N | line differential (EPSC) | Line
ALTALINK | 865L (216s Knightsbridge - 38s East Edmonton) | 2014-08-05 08:00 | 2014-08-09 17:00 | N | N | move 865L over to the next bay in substation (old 215L position) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 945L (275s Jenner - 562s Cypress) | 2014-08-05 08:00 | 2014-08-07 16:00 | N | Y | SCADA Equipment Upgrade Project | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 10 | 2014-08-05 08:00 | 2014-08-08 16:00 | N | N | tie the new 138 kV bus into SW 84 | Station |  |  | For Information Only
ALTALINK | 37s 76 (37s North Calder) | 2014-08-05 08:00 | 2014-08-08 15:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 26.81L (ENMAX 54 - ENMAX 26),54B138-26.81 (ENMAX 54) | 2014-08-05 08:00 | 2014-08-05 16:00 | N | N | breaker maintenance 54B138-26.81 | Circuit Breaker, Line |  |  | Overload
ENMAX | 31.1C (ENMAX 31) | 2014-08-05 08:00 | 2014-08-05 16:00 | N | Y | doble 31B138.31.1Cap | Shunts |  |  | Limits ATC
ALTALINK | 33s5 (33s Spray) | 2014-08-05 08:30 | 2014-08-05 18:00 | N | N | maintenance | Switch |  |  | For Information Only
ATCO | 775s 604C (775s Sullivan Lake),775s 604 (775s Sullivan Lake) | 2014-08-05 09:00 | 2014-08-05 16:00 | N | Y | breaker maintenance | Shunts, Circuit Breaker |  | Bkr 604 Maintenance | For Information Only
ATCO | 809s 911 (809s Louise Creek) | 2014-08-05 09:00 | 2014-08-07 15:00 | N | Y | breaker maintenace | Circuit Breaker |  | 809S LOUISE CREEK BKR 911 O/S FOR MTCE | 240 kV, Contingency Requires Mitigation
ATCO | 785s 701T (785s Judy Creek Gas Plant) | 2014-08-05 09:00 | 2014-08-05 14:00 | N | N | change and commission CT ratio and relay settings, 701T @ 785S | Transformer |  | Change and Commission CT ratio and relay settings, 701T @ 785S | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),ENMAX 31 B138-31.84 (ENMAX 31) | 2014-08-05 09:21 | 2014-08-05 15:42 | N | N | forced outage; return date is unknown,open-ended at ENMAX 31 | Circuit Breaker, Line |  |  | For Information Only
ATCO | 7L42 (751s Hill - 716s Lloydminster) | 2014-08-05 10:00 | 2014-08-07 16:00 | N | N | climbing inspection | Line |  | 7L42 WILL BE REMOVED FROM SERVICE FOR A CLIMBING INSPECTION | Firm Load Loss, Creates Radial Feeds
ATCO | 845s 705C (845s Big Mountain),845s 705 (845s Big Mountain) | 2014-08-05 10:00 | 2014-08-06 16:00 | N | Y | breaker maintenance | Shunts, Circuit Breaker |  | 845S BIG MTN 705C O/S FOR MTCE ON BKR 705 | For Information Only
ALTALINK | 142s C1 (142s Magcan) | 2014-08-05 11:00 | 2014-08-05 12:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
ATCO | 790s 509C1 (790s Poplar Hill),790s 702T (790s Poplar Hill) | 2014-08-05 11:00 | 2014-08-06 16:00 | N | Y | 702T maintenance | Transformer, Shunts |  | 790S POPLAR HILL 702T O/S FOR MTCE | For Information Only
ALTALINK | 62s C1 (62s Brazeau) | 2014-08-05 12:00 | 2014-08-05 13:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
ALTALINK | 151s C1 (151s Strathmore) | 2014-08-05 14:00 | 2014-08-05 15:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
ALTALINK | 133S Stelco Edmonton,822AL (133s Stelco Edmonton - 822L tap),822L (133s Stelco Edmonton - 38s East Edmonton) | 2014-08-06 07:00 | 2014-08-06 19:00 | N | N | change out insulators on 133s1 and 133s2 | Station, Line
ALTALINK | 62s T4 (62s Brazeau),202L (61s Lodgepole - 62s Brazeau),801L (62s Brazeau - 294s Brazeau Outlet Works) | 2014-08-06 08:00 | 2014-08-06 17:00 | N | Y | T4 & 62s34 switch work | Transformer, Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11),ENMAX 11 B138-11.81 (ENMAX 11) | 2014-08-06 08:00 | 2014-08-06 16:00 | N | N | doble 11B138-11.81 | Line, Circuit Breaker
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 (ENMAX 54) | 2014-08-06 08:00 | 2014-08-06 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 825s 906 (825s Whitefish) | 2014-08-06 09:00 | 2014-08-07 16:00 | N | Y | maintenance | Circuit Breaker |  | 825S WHITEFISH LAKE BKR 906 O/S FOR MTCE | 240 kV, Contingency Requires Mitigation
ATCO | 757s 607C (757s Battle River),757s 607 (757s Battle River) | 2014-08-06 09:00 | 2014-08-06 16:00 | N | Y | breaker maintenance | Circuit Breaker, Shunts |  | Bkr 607 Maintenance | For Information Only
ALTALINK | 186s C1 (186s Dry Creek),186s 17 (186s Dry Creek) | 2014-08-06 09:00 | 2014-08-06 10:00 | N | Y | cap bank weed control work | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 199s C1 (199s East Ardrie) | 2014-08-06 11:00 | 2014-08-06 12:00 | N | Y | cap bank weed control work | Shunts |  |  | Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2014-08-06 14:00 | 2014-08-06 15:00 | N | Y | cap bank weed control work | Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 74s C1 (74s Janet) | 2014-08-07 07:30 | 2014-08-07 09:00 | N | Y | cap bank weed control work | Shunts |  |  | Limits ATC, For Information Only
ALTALINK | 62s C1 (62s Brazeau),62s T5 (62s Brazeau),62s T7 (62s Brazeau) | 2014-08-07 08:00 | 2014-08-07 17:00 | N | Y | 62s210 switch & T7 work | Transformer, Shunts |  |  | 240 kV, Pre-Condition, Restricts Generation, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11),ENMAX 11 B138-11.81 (ENMAX 11) | 2014-08-07 08:00 | 2014-08-07 16:00 | N | N | doble 13B138-11.81 | Circuit Breaker, Line
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2014-08-07 08:00 | 2014-08-07 16:00 | N | N | repair hot spot | Line |  |  | Overload
ALTALINK | 447s T2 (447s Enchant) | 2014-08-07 08:00 | 2014-08-07 17:00 | N | N | repair deficiency to the core ground | Transformer
ALTALINK | 703L (213s Hughenden - 703AL tap) | 2014-08-07 08:00 | 2014-08-07 14:00 | N | N | to install Mobile 472s & MR1(regulator) to feed 213s Hughenden | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 138-RB83 (162s Beddington) | 2014-08-07 08:00 | 2014-08-07 16:00 | N | N | breaker maintenance 162B138-RB83 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 947L (89s Ellerslie - 987s Clover Bar) | 2014-08-07 08:00 | 2014-08-07 17:00 | N | Y | doble testing | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 74s C2 (74s Janet) | 2014-08-07 09:00 | 2014-08-07 10:00 | N | Y | cap bank weed control work | Shunts |  |  | Limits ATC, For Information Only
ALTALINK | 33s5 (33s Spray) | 2014-08-07 10:30 | 2014-08-07 15:30 | N | N | removing testing equipment | Switch |  |  | Restricts Generation
ALTALINK | 74s C3 (74s Janet) | 2014-08-07 11:00 | 2014-08-07 12:00 | N | Y | cap bank weed control work | Shunts |  |  | Limits ATC, For Information Only
ALTALINK | 74s C4 (74s Janet) | 2014-08-07 12:00 | 2014-08-07 13:00 | N | Y | cap bank weed control work | Shunts |  |  | Limits ATC, For Information Only
ALTALINK, AESO | 703L (213s Hughenden - 703AL tap),703L (213s Hughenden - 703BL tap) | 2014-08-07 14:00 | 2014-09-03 17:00 | N | N | station upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 118s C1 (118s Canmore) | 2014-08-07 15:00 | 2014-08-07 16:00 | N | Y | cap bank weed control work | Shunts |  |  | For Information Only
ALTALINK | 915L (38s East Edmonton - 987s Clover Bar) | 2014-08-08 08:00 | 2014-08-08 17:00 | N | Y | doble testing | Line |  |  | 240 kV, Pre-Condition
ATCO | 716s 701T (716s Lloydminster) | 2014-08-08 08:00 | 2014-08-14 16:00 | N | N | forced outage due to failure of the protection relays | Transformer
ALTALINK | 447S Enchant,447s T1 (447s Enchant) | 2014-08-08 08:00 | 2014-08-08 17:00 | N | N | close open point E between 447s26 and 25kV Bus #1 | Station, Transformer
ALTALINK | 931L (132s Ware Junction - 28s West Brooks) | 2014-08-09 07:00 | 2014-08-10 18:00 | N | Y | EATL interface: Erection of tower 1327. | Line |  |  | 240 kV
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2014-08-09 08:00 | 2014-08-16 16:00 | N | N | re-insulate 16.63L | Transformer, Line |  |  | Overload
IMPERIALOIL | Imperial Oil | 2014-08-09 08:00 | 2014-08-20 16:00 | N | N | 86 MW (Kearl), In service date: August 15, 2014 | Unit
SUNCOR | 29EDD-1 29EDD1s 652 (29EDD-1 Millennium),29EDD-1 29EDD1s 552 (29EDD-1 Millennium) | 2014-08-09 08:00 | 2014-08-25 16:00 | N | N | maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2014-08-09 09:00 | 2014-08-09 16:00 | N | N | To allow construction of new 144 kV lines. | Line |  | TO ALLOW CONSTRUCTION ON NEW 144KV LINES | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2014-08-10 07:30 | 2014-08-10 18:00 | Y | Y | urgent trouble corrective: replace shot insulators at STR 463, and change Corona Rings / support insulators at STR 359. | Line |  |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK | 250p22 (250p Bighorn) | 2014-08-10 08:00 | 2014-08-10 13:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-08-10 08:00 | 2014-08-10 16:00 | N | N | replace faulty hardware, Doble 39B138-39.82 and Sub Wash 162s | Line |  |  | Pre-Condition, Overload
EPCOR | Rossdale C2 | 2014-08-10 08:00 | 2014-08-10 17:00 | N | N | outage required to repair 72RC1 Cap Bank | Shunts |  |  | For Information Only
EPCOR | 557s T2 (557s Castle Downs) | 2014-08-10 08:00 | 2014-08-16 17:00 | N | Y | cutover new Tx2 protection panel | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 37s 81 (37s North Calder) | 2014-08-11 08:00 | 2014-08-14 15:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 7L224 (774s Monitor - 650s Hansman Lake) | 2014-08-11 08:00 | 2014-08-11 14:00 | N | N | 702A switch repairs | Line |  | 7L224 WILL BE OPEN ENDED @ 774S MONITOR TO REPAIR 702A SEQUENCE 1. OPEN END 7L224 AT 774S 2.HOP (2-29011) CREATE J1 BETWEEN UPPER AND LOWER BUS 3.COMPLETE SWITCHING AND ISSUE GOI AFTER SWITCH REPAIR / GOI RELEASED 4..HOP (2-29011) TO RECONECT RISERS BETWEEN UPPER AND LOWER BUS 5. CLOSE 7L224 LINE AT 774S | Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 1205 (330p Genesee),330p 1206 (330p Genesee) | 2014-08-11 08:00 | 2014-09-19 16:00 | N | Y | for the prep work for the 1238 & 1239 lines for the Sunnybrook 511S project | Circuit Breaker |  |  | 500 kV
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198) | 2014-08-11 08:00 | 2014-08-11 13:00 | N | N | Install Zena protection on arm, remove twigs, tighten hardware on Str# 145. | Line |  |  | Restricts Generation
ENMAX | ENMAX 65 B240-D132 (ENMAX 65) | 2014-08-11 08:00 | 2014-08-13 16:00 | N | Y | First year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV
CapitalPower | 615S Halkirk | 2014-08-11 08:00 | 2014-08-17 18:00 | N | Y | sub maitntenance | Station |  |  | Restricts Generation
ALTALINK | 33s5 (33s Spray) | 2014-08-11 08:30 | 2014-08-11 18:00 | N | Y | Maintenance. | Switch |  |  | Restricts Generation
AESO-SC | EMS | 2014-08-11 10:00 | 2014-08-11 11:30 | N | N | Critical app migration from PDC to SDC | SCInternal |  |  | For Information Only
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2014-08-11 10:00 | 2014-08-15 15:00 | N | N | Line maintenance, replace 526L185 | Line |  |  | Pre-Condition
ATCO | 794s 701T (794s Valleyview) | 2014-08-11 11:00 | 2014-08-11 17:00 | N | N | to replace tem gauge | Transformer |  | 794S VALLEYVIEW 701T O/S TO REPLACE TEMP GUAGE | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde),150s 223N (150s Clyde) | 2014-08-11 13:00 | 2014-08-11 16:00 | N | N | Hot Spots on Breaker CT's | Circuit Breaker, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome),320p T1 (320p Keephills),320p Keephills 240kV Bus B | 2014-08-11 13:00 | 2014-08-11 17:00 | N | Y | 320p213 switch adjustment | Line, Transformer, Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
AESO-SC | EMS | 2014-08-11 14:15 | 2014-08-11 14:20 | N | N | Automate Maintenance Restarts of WL Admin Servers. | SCInternal
STROBE | 239s T1 (239s Castle River) | 2014-08-11 17:01 | 2014-08-12 17:00 | N | Y | T1 & breaker maintenance | Transformer |  |  | Restricts Generation, For Information Only
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2014-08-11 20:00 | 2014-08-12 | N | N | urgent trouble corrective: Repair damaged crossarm & insulator | Line |  |  | For Information Only
ALTALINK | 635s 10 (635s Rose Valley) | 2014-08-12 07:00 | 2014-08-12 16:00 | N | N | Customer Equipment Work | Switch
ALTALINK | 538S Buford,632L (325s Leduc - 538s Buford),837L (964s Pigeon Lake - 538s Burford) | 2014-08-12 08:00 | 2014-08-12 17:00 | N | N | Transformer & Switch Hot Spot Repairs | Station, Line
ATCO | 7L127 (774s Monitor - 932s Pemukan) | 2014-08-12 08:00 | 2014-08-12 14:00 | N | N | ATCO SWITCH REPAIR | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO, ALTALINK | 157s 788N (157s Lac La Biche),788L (157s Lac La Biche - 788L Tap) | 2014-08-12 08:00 | 2014-08-13 17:00 | N | N | 157s18 switching cleaning / adjustments | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 813s 704 (813s Little Smoky) | 2014-08-12 08:00 | 2014-08-12 17:00 | N | N | 704 breaker SF6 HGF partial testing | Circuit Breaker |  | 813S 704 BREAKER SF6 HGF PARTIAL TESTING
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2014-08-12 08:00 | 2014-08-14 16:00 | N | Y | SCADA equipment upgrade project | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 162L (415s Drywood - 229s Glenwood),415s 146E (415s Drywood) | 2014-08-12 08:00 | 2014-08-14 17:00 | N | N | Replace B protection | Line, Circuit Breaker |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L19 (809s Louise Creek - 851s Morse River) | 2014-08-12 08:30 | 2014-08-12 14:30 | N | N | breaker SF6 HGF partial testing 702 @ 851s | Line |  | BREAKER SF6 HGF PARTIAL TESTING, 702 @ 851 | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2014-08-12 08:30 | 2014-08-13 16:00 | N | N | maintenance | Line |  | 7L66 WILL BE REMOVED FROM SERVICE FOR MTCE ON 715S LEMING LAKE BKR 703 & 717S ETHEL LAKE BKR 702 | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (198s Blackfalds - 217s North Red Deer),194s 80N (194s South Red Deer) | 2014-08-12 09:00 | 2014-08-14 17:00 | N | N | transformer protections testing | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 286s T2 (286s Yasa) | 2014-08-12 09:00 | 2014-08-12 17:00 | N | N | T2 Transformer Maintenance | Transformer
ALTALINK | 867s T1 (867s Sundance Blow-Down) | 2014-08-12 09:00 | 2014-08-12 17:00 | N | N | Doble, oil leak and cracked glass | Transformer
ALTALINK | 384s T1 (384s Keystone) | 2014-08-12 09:00 | 2014-08-12 17:00 | N | N | T1 Oil Leak Repairs | Transformer
ALTALINK | 394s T1 (394s Empress) | 2014-08-12 13:00 | 2014-08-18 17:00 | N | N | HV bushing replacement, rad leak | Transformer
ATCO | 813s SVC (813s Little Smoky) | 2014-08-13 03:00 | 2014-08-13 15:00 | N | Y | 813S SVC Off line to change leaking pump in cooling system | Shunts |  | 813S SVC Off line to Change pump Change leaking pump in cooling system | Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2014-08-13 08:00 | 2014-08-13 13:00 | N | Y | Breaker Low Gas Repairs | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 500s T1 (500s Flatbush) | 2014-08-13 08:00 | 2014-08-13 09:00 | N | N | change T1 from tap 1 to tap 2 | Transformer
ATCO | 7L51 (788s Hotchkiss - A793s West Peace River) | 2014-08-13 08:00 | 2014-08-13 17:30 | N | N | pole change .......Structure change out rotten & str. design change to angle from t-w-440 to t-w-402 2 - 15 degree angle | Line |  | pole change .......Structure change out rotten & str. design change to angle from t-w-440 to t-w-402 2 - 15 degree angle
ATCO | 794s 702T (794s Valleyview) | 2014-08-13 08:00 | 2014-08-13 17:00 | N | N | breaker SF6 LTB145D1/B partial testing | Transformer |  | 794S 702 BREAKER SF6 LTB145D1/B PARTIAL TESTING
ATCO | 7L67 (824s Fieldgate - 743s Sarah Lake) | 2014-08-13 08:00 | 2014-08-13 16:30 | N | N | breaker SF6 HGF partial testing | Line |  | BREAKER SF6 HGF PARTIAL TESTING, 703 @ 851S | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D141 (ENMAX 25) | 2014-08-13 08:00 | 2014-08-15 16:00 | N | Y | First year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 1059L (38s East Edmonton - 803s Lambton) | 2014-08-13 08:00 | 2014-08-13 17:00 | N | Y | AltaLink work at 38S switch repair | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2014-08-13 12:30 | 2014-08-13 14:30 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 2152 (320p Keephills) | 2014-08-13 13:00 | 2014-08-13 17:00 | N | Y | repair breaker low gas | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 33s5 (33s Spray) | 2014-08-13 14:30 | 2014-08-13 19:30 | N | Y | Maintenance. | Switch |  |  | Restricts Generation
STROBE | 240s T1 (240s McBride Lake) | 2014-08-13 17:01 | 2014-08-14 17:00 | N | Y | T1 maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2014-08-13 23:00 | 2014-08-14 03:00 | N | N | brushgear work | Switch |  |  | Restricts Generation
ALTALINK | 62s11 (62s Brazeau) | 2014-08-14 03:00 | 2014-08-14 07:00 | N | N | brushgear work | Switch |  |  | Restricts Generation
ALTALINK | 61s T2 (61s Lodgepole) | 2014-08-14 07:00 | 2014-08-14 17:00 | N | N | deficiency work | Transformer |  |  | For Information Only
ALTALINK | 12s T1 (12s Heartland) | 2014-08-14 08:00 | 2014-08-14 16:00 | N | N | change taps from 0% to +2.5%. | Transformer |  |  | 240 kV, Overload, 500 kV
ALTALINK | 946L (89s Ellerslie - 38s East Edmonton) | 2014-08-14 08:00 | 2014-08-14 15:00 | N | Y | 38s946W switch adjustment | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2014-08-14 08:00 | 2014-08-15 17:00 | N | N | Replace 805L CTs | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 813s 707 (813s Little Smoky) | 2014-08-14 08:30 | 2014-08-14 17:00 | N | N | breaker testing | Circuit Breaker |  | 813S 707 BREAKER SF6 HGF PARTIAL TESTING | For Information Only
ALTALINK | 310p 2252 (310p Sundance) | 2014-08-14 09:00 | 2014-08-14 17:00 | N | Y | breaker testing | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 727L (678s Okotoks - 727L39N) | 2014-08-14 09:00 | 2014-08-14 17:00 | N | N | 138kV Switch Repair | Line |  |  | Overload, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2014-08-15 06:30 | 2014-08-15 11:00 | N | Y | L to J project. Cut Open Point and release T2 in preparation for Tie in South Bus Extension. | Transformer, Bus, Shunts |  |  | 240 kV, Limits ATC
AESO-SC | EMS | 2014-08-15 09:30 | 2014-08-15 11:30 | N | N | EMS - PDC Infrastructure servers Microsoft Patching | SCInternal |  |  | For Information Only
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s Janet 240kV Bus 2 | 2014-08-15 10:30 | 2014-08-23 11:59 | N | Y | L to J project. Tie in South Bus Extension, P & C and test energize new equip. | Bus, Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 701S Blue Ridge Lumber,826L (701s Blue Ridge Lumber - 77s Sagitawah) | 2014-08-16 08:00 | 2014-08-16 17:00 | N | N | switch replacements, transformer/breaker maintenance | Station, Line
ENMAX | 162s 240-RB131 (162s Beddington) | 2014-08-16 08:00 | 2014-08-17 16:00 | N | Y | maintenance, SF6 sample & install new position indicator | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2014-08-16 08:00 | 2014-08-16 16:00 | N | N | doble 32PT138-Z32 | Line, Transformer
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2014-08-16 08:00 | 2014-08-23 17:00 | N | N | replace 138kV breaker & line protections, add breaker fail function | Line |  |  | Over/Under Voltage
ATCO | 7L146 (970s Bourque - 700s Bonnyville) | 2014-08-16 08:00 | 2014-08-22 16:00 | N | N | In service date: August 20, 2014 | Line
ENMAX | 21.80L (42s Sarcee - ENMAX 21),ENMAX 21 B138-21.80 (ENMAX 21) | 2014-08-17 08:00 | 2014-08-17 16:00 | N | Y | doble breaker | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | 805s T4 (805s Jasper) | 2014-08-18 07:00 | 2014-09-19 17:00 | N | Y | oil refurbishing | Transformer |  |  | 240 kV
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41) | 2014-08-18 08:00 | 2014-08-22 16:00 | N | N | MD replacement 40.2TR | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s 82 (37s North Calder) | 2014-08-18 08:00 | 2014-08-21 15:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 65 B240-D135 (ENMAX 65) | 2014-08-18 08:00 | 2014-08-20 16:00 | N | Y | first year check/maintenance (first 2 days), Doble (3rd day), SF6 Sample, install new position indicator | Circuit Breaker |  |  | 240 kV
ATCO | 848s 902 (848s Ruth Lake) | 2014-08-18 08:00 | 2014-08-18 17:00 | N | Y | perform maintenance on 902Breaker | Circuit Breaker |  | 848S 902 BKR PARTIAL TESTING Perform maintenance on 902Breaker @ 848S Ruth Lake | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2452 (310p Sundance) | 2014-08-18 08:15 | 2014-08-18 08:45 | N | Y | breaker fail test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 826s 701 (826s Marguerite Lake) | 2014-08-18 08:30 | 2014-08-18 16:30 | N | N | breaker maintenance | Circuit Breaker |  | 826S MARGUERITE LAKE BKR 701 O/S FOR MTCE | Contingency Requires Mitigation
ATCO | 6L05 (843s Bigknife Creek - 757s Battle River),757s 602 (757s Battle River) | 2014-08-18 08:30 | 2014-08-18 16:00 | N | N | breaker testing | Circuit Breaker, Line |  | 757s - BKR 602 BREAKER MIN OIL HLC PARTIAL TESTING | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2152 (310p Sundance) | 2014-08-18 09:00 | 2014-08-18 09:30 | N | Y | breaker fail test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1852 (310p Sundance) | 2014-08-18 09:45 | 2014-08-18 10:15 | N | Y | breaker fail test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1552 (310p Sundance) | 2014-08-18 10:30 | 2014-08-18 11:00 | N | Y | breaker fail test | Circuit Breaker |  |  | 240 kV
ALTALINK | 519L (519AL tap - 519L2),526L (526DL365 - 526DL208 ) | 2014-08-18 11:00 | 2014-08-18 14:00 | N | Y | open Jumpers on str 216 to allow new switch to be installed at str 221 | Line |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 310p 1252 (310p Sundance) | 2014-08-18 11:15 | 2014-08-18 11:45 | N | Y | breaker fail test | Circuit Breaker |  |  | 240 kV
ALTALINK | 63s 852 (63s Red Deer) | 2014-08-18 12:00 | 2014-08-18 17:00 | N | Y | dashpot repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2014-08-18 12:00 | 2014-08-20 17:00 | N | N | Altalink request - 42s693 breaker maintenance | Line
ALTALINK, ENMAX | 832L (ENMAX 10 - ENMAX 12),693L (42s Sarcee - ENMAX 10),42s 693 (42s Sarcee) | 2014-08-18 12:00 | 2014-08-20 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds
ALTALINK | 310p 952 (310p Sundance) | 2014-08-18 12:30 | 2014-08-18 13:00 | N | Y | breaker fail test from 310p2752 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 652 (310p Sundance) | 2014-08-18 13:15 | 2014-08-18 13:45 | N | Y | breaker fail test from 310p2752 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 352 (310p Sundance) | 2014-08-18 14:00 | 2014-08-18 14:30 | N | Y | breaker fail test from 310p2752 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
AESO | 526L (526DL365 - 526AL tap) | 2014-08-18 14:00 | 2014-08-22 11:00 | N | N | work on 526L365 & install new switch 526L221 | Line |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 310p412 (310p Sundance) | 2014-08-18 14:45 | 2014-08-18 15:15 | N | N | breaker fail test | Circuit Breaker |  |  | For Information Only
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2014-08-19 08:00 | 2014-08-21 16:00 | N | Y | SCADA equipment upgrade project | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s T1 (89s Ellerslie),89s Ellerslie 500kV Bus 1,89s Ellerslie 240kV Bus 1 | 2014-08-19 08:00 | 2014-08-19 17:00 | N | Y | switch repairs - 89s 240/500kV West Bus & T1 | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload, 500 kV
ENMAX | ENMAX 36 B138-36.81 (ENMAX 36),36.81L (44s Bearspaw - ENMAX 36) | 2014-08-19 08:00 | 2014-08-19 16:00 | N | N | doble | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ATCO | 826s 704 (826s Marguerite Lake) | 2014-08-19 08:30 | 2014-08-19 16:30 | N | N | maintenance | Circuit Breaker |  | 826S MARGUERITE LAKE BKR 704 O/S FOR MTCE | Contingency Requires Mitigation
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2014-08-19 08:30 | 2014-08-21 17:00 | N | Y | energization plan to restore NTL 2CB1 to service | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2014-08-19 08:30 | 2014-08-19 10:00 | N | N | high load move | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 250p22 (250p Bighorn) | 2014-08-19 10:00 | 2014-08-19 14:00 | N | Y | maintenance | Switch |  |  | Pre-Condition, For Information Only
ALTALINK | 13s 1552 (13s Deerland) | 2014-08-19 11:00 | 2014-08-20 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2652 (310p Sundance) | 2014-08-19 18:00 | 2014-09-03 14:00 | N | Y | replace breaker fail protection | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 89s 2052 (89s Ellerslie) | 2014-08-20 08:00 | 2014-08-20 17:00 | N | Y | 500kV Breaker Maintenance | Circuit Breaker |  |  | 500 kV
ENMAX | ENMAX 25 B240-D140 (ENMAX 25) | 2014-08-20 08:00 | 2014-08-22 16:00 | N | Y | first year check/maintenance (first 2 days), doble (3rd day), SF6 sample, install new position indicator | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | Rossdale RR729 (Rossdale) | 2014-08-20 08:00 | 2014-08-20 16:00 | N | N | doble as required | Circuit Breaker |  |  | For Information Only
ALTALINK | 5s T2 (5s East Calgary) | 2014-08-20 08:00 | 2014-08-22 16:00 | N | Y | ECTP ENMAX: To close open point and test energize 138kV ring bus in GIS | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 256s C1 (256s Harmattan) | 2014-08-20 08:00 | 2014-08-20 17:00 | N | N | rebuild dashpot | Shunts |  |  | For Information Only
ALTALINK | 410s 152 (410s Josephburg) | 2014-08-20 08:00 | 2014-08-20 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 171s T2 (171s Redwater) | 2014-08-20 08:00 | 2014-08-20 17:00 | N | N | urgent inspection | Transformer |  |  | For Information Only
ALTALINK | 650s T1 (650s Hansman Lake) | 2014-08-20 08:00 | 2014-08-20 15:00 | N | Y | SCADA equipment upgrade project | Transformer |  |  | 240 kV, For Information Only
ATCO | 791s 702T (791s Rainbow Lake) | 2014-08-20 08:00 | 2014-08-21 16:00 | N | N | maintenance | Transformer |  | 791S RAINBOW LAKE 701T & BKR 707 WILL BE REMOVED FROM SERVICE FOR MTCE THIS IS A RE-SCHEDULE AND THERE IS SWITCHING THAT HAS ALREADY BEEN WRITTEN | For Information Only
ALTALINK | 170s Pike 138kV Bus 1 | 2014-08-20 08:00 | 2014-08-22 12:00 | N | N | repair 170s33 so it opens past 90 | Bus |  |  | For Information Only
ATCO | 757s 706 (757s Battle River) | 2014-08-20 08:30 | 2014-08-20 16:00 | N | N | partial testing | Circuit Breaker |  | 757s - 706 BREAKER MIN OIL HPF PARTIAL TESTING | For Information Only
ATCO | 826s 707 (826s Marguerite Lake) | 2014-08-20 08:30 | 2014-08-20 16:30 | N | N | maintenance | Circuit Breaker |  | 826S MARGUERITE LAKE BKR 707 O/S FOR MTCE | For Information Only
ALTALINK | 250p11 (250p Bighorn) | 2014-08-20 10:00 | 2014-08-20 14:00 | N | Y | maintenance | Switch |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays) | 2014-08-20 15:00 | 2014-08-21 20:00 | N | N | forced outage due to broken structure | Line |  |  | Pre-Condition
ENMAX, ALTALINK | ENMAX 12 ,12.1TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12),693L (42s Sarcee - ENMAX 10) | 2014-08-21 08:00 | 2014-08-21 16:00 | N | Y | doble PT's | Station, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s T2 (89s Ellerslie),89s Ellerslie 500kV Bus 2 | 2014-08-21 08:00 | 2014-08-21 14:00 | N | Y | Switch Repairs | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload, 500 kV
ATCO | 826s 710 (826s Marguerite Lake) | 2014-08-21 08:30 | 2014-08-21 16:30 | N | N | maintenance | Circuit Breaker |  | 826S MARGUERITE LAKE BKR 710 O/S FOR MTCE | For Information Only
ATCO | 7L16 (766s Nevis - 948s Heatburg),766s 702 (766s Nevis) | 2014-08-21 08:30 | 2014-08-21 14:00 | N | N | breaker testing | Circuit Breaker, Line |  | 766s - 702 BREAKER SF6 LTB145D1/B PARTIAL TESTING | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 26 (77s Sagitawah) | 2014-08-21 09:00 | 2014-08-21 14:00 | N | Y | breaker low oil | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 370s 56 (370s North Lethbridge) | 2014-08-21 10:00 | 2014-08-21 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 127s C1 (127s Bruderheim),127s 33 (127s Bruderheim) | 2014-08-21 12:00 | 2014-08-21 13:00 | N | N | cap bank vegetation control | Shunts, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 33s3 (33s Spray) | 2014-08-21 13:00 | 2015-03-01 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 526L (526DL365 - 526DL208 ) | 2014-08-22 11:00 | 2014-08-22 15:00 | N | N | close jumpers on str 216 after new switch installed at str 221 | Line |  |  | Pre-Condition
ENMAX | 162s 240-RB132 (162s Beddington) | 2014-08-23 08:00 | 2014-08-24 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
CNRL | 842s 75-1902 (842s Horizon Upgrading),842s 75-1903 (842s Horizon Upgrading),842s 75-1904 (842s Horizon Upgrading) | 2014-08-23 08:00 | 2014-09-06 16:00 | N | N | maintenance and test | Circuit Breaker |  | -AUTO Synchronizing test to be performed across 75-BC-1903 during Generator Run Up. Requires 260kV breakers to be isolated when generator runs up | 240 kV, For Information Only
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2014-08-23 08:00 | 2014-08-24 17:00 | N | N | Fortis requested for underbuild work | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
CNRL | 838s 75-TR-1701 (838s Horizon Mining),75-TR-1801 (838s Horizon Mining),75-TR-2701 (838s Horizon Mining),75-TR-2801 (838s Horizon Mining),838s 75-BC-1911 (838s Horizon Mining),838s 75-BC-1918 (838s Horizon Mining) | 2014-08-23 08:00 | 2014-09-06 16:00 | N | N | maintenance and testing | Transformer, Circuit Breaker |  | -Opening the 260kV ring bus to allow for the Transformers to be isolated and removed from service for maintenance and testing. Approximately 3.5days per transformer. -AUTO Synchronizing test to be performed across 75-BC-1911 during Generator Run Up. Requires 260kV breakers to be isolated when generator runs up. | 240 kV, For Information Only
Syncrude | Mildred_1225 (Syncrude Mildred Lake) | 2014-08-23 08:00 | 2014-09-02 18:00 | N | N | 72kV Upgrade | Circuit Breaker |  |  | For Information Only
SUNCOR | Suncor (Millennium) Islanding RAS (IRAS) | 2014-08-23 09:00 | 2014-08-23 19:00 | N | N | IMS/RAS will be disabled as require for the CT ratio work | RAS |  | IMS/RAS will be disabled as require for the CT ratio work that is part of GTG #6 outage | For Information Only
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2014-08-23 12:00 | 2014-08-24 12:00 | N | Y | L to J project. Close Open Point and restore T2 to normal in completion for South Bus Extension commissioning. | Transformer, Bus, Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 74s 2852 (74s Janet),74s 2352 (74s Janet) | 2014-08-24 18:01 | 2014-09-05 18:00 | N | Y | L to J: P&C work for future 985L (L10) bay | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2014-08-25 08:00 | 2014-08-25 16:00 | N | N | Doble 21B69-15.60 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 56s C1 (56s Boyle),710L (159s Colinton - 56s Boyle),56s Boyle 138 kV bus | 2014-08-25 08:00 | 2014-08-29 14:00 | N | N | breaker trip test | Shunts, Line, Bus
EPCOR | Hardisty T2 (Hardisty) | 2014-08-25 08:00 | 2014-08-27 16:00 | N | N | doble as required | Transformer
ALTALINK | 356s 352 (356s Milo) | 2014-08-25 08:00 | 2014-08-26 07:59 | N | Y | gas leak repair, ABB inspection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2014-08-25 08:00 | 2014-08-27 16:00 | N | Y | first year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 727L (74s Janet - 678s Okotoks) | 2014-08-25 08:00 | 2014-08-28 17:00 | N | N | NFTP: Cut in 727L into new Temporary(1140s) Sub. | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (378s Shell Caroline - 719214X),378s 552 (378s Shell Caroline),378s 452 (378s Shell Caroline) | 2014-08-25 08:00 | 2014-08-29 16:00 | N | N | replacement of A and B protections on 719L | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred_235 (Syncrude Mildred Lake) | 2014-08-25 08:00 | 2014-08-31 18:00 | N | N | 72kV Upgrade | Circuit Breaker
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2014-08-25 08:30 | 2014-08-29 17:00 | N | Y | energization plan to restore NTL 2CB1 to service | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
AESO | 701L (223s Strome - 7L701D1) | 2014-08-25 09:00 | 2014-08-25 12:00 | N | N | high load move | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet) | 2014-08-25 09:30 | 2014-08-25 17:00 | N | Y | gauge leak repair | Shunts |  |  | Limits ATC
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2014-08-25 10:00 | 2014-08-28 16:00 | N | N | line vibration dampers | Line |  | 7L46 Line Vibration Dampers | Pre-Condition
ATCO | 706s Irish Creek RTU/SCADA | 2014-08-25 11:00 | 2014-08-29 11:00 | N | N | 706S Substation RTU Config for 702T Addition | Terminal Equipment |  |  | Affects Visibility
ENMAX | 30.81L (42s Sarcee - ENMAX 30) | 2014-08-25 12:00 | 2014-08-25 17:00 | N | Y | 138kV 42s56 switch hotspot repair | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s T3a (535s Joffre) | 2014-08-25 12:00 | 2014-08-26 17:00 | N | N | oil leak repair | Transformer
ALTALINK | 310p 952 (310p Sundance) | 2014-08-25 13:00 | 2014-08-28 17:00 | N | Y | breaker repairs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 39s 33 (39s Bickerdike) | 2014-08-25 13:00 | 2014-08-26 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 89s 1752 (89s Ellerslie) | 2014-08-25 13:00 | 2014-08-28 17:00 | N | Y | breaker stack re - gasket | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 827L (121s Brooks - 28s West Brooks),28s 57 (28s West Brooks) | 2014-08-26 07:00 | 2014-08-27 17:00 | N | N | Replace PTs | Switch, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 42s C1 (42s Sarcee) | 2014-08-26 07:30 | 2014-08-28 17:00 | N | Y | 138kV breaker maintenance | Shunts |  |  | Limits ATC
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7),42s 7 (42s Sarcee) | 2014-08-26 07:30 | 2014-08-28 16:00 | N | Y | 42s7 breaker maintenance | Line, Circuit Breaker |  |  | Overload
ALTALINK | 356s 652 (356s Milo) | 2014-08-26 08:00 | 2014-08-27 07:59 | N | Y | Gas Leak Repair, ABB inspection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 940s Beartrap RTU/SCADA | 2014-08-26 08:00 | 2014-08-28 14:00 | N | N | 940S RTU Upgrades & Changes | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 275s T3 (275s Jenner),275s 64 (275s Jenner) | 2014-08-26 08:00 | 2014-08-28 16:00 | N | N | SCADA Equipment Upgrade Project | Transformer, Switch
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2014-08-26 08:00 | 2014-08-28 16:00 | N | N | Relay Maintenance, Doble 37B138-37.81 | Line
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2014-08-26 08:30 | 2014-08-26 16:30 | N | N | maintenance | Line |  | 7L91 WILL BE OPEN ENDED @ 715S LEMING LAKE FOR MTCE ON BKR 702 | Pre-Condition
ALTALINK | 520L (887s Mobil Oil Carson Creek - 520L1),526L (268s Whitecourt - 526DL185),526BL (659s Pegasus Lake - 526L tap),526L (526DL185 - 526DL208) | 2014-08-26 10:00 | 2014-08-26 14:00 | N | N | Open Jumpers on str 188 & str 204 | Line |  |  | Pre-Condition
REDDEER | 194s T1 (194s South Red Deer) | 2014-08-27 07:00 | 2014-08-27 17:00 | N | N | Install bushing extenders on transformer secondary. | Transformer |  |  | For Information Only
ALTALINK | 5s C3 (5s East Calgary),5s C2 (5s East Calgary) | 2014-08-27 07:30 | 2014-09-02 16:00 | N | Y | ECTP 2s, Remove the slack span from the AIS (2.82L) directly overtop of the cap bank | Shunts |  |  | Limits ATC
ENMAX | ENMAX 25 B240-D133 (ENMAX 25) | 2014-08-27 08:00 | 2014-08-29 16:00 | N | Y | maintenance checks and install new position indicator | Circuit Breaker |  |  | 240 kV
ALTALINK | 356s 852 (356s Milo) | 2014-08-27 08:00 | 2014-08-28 08:00 | N | Y | Gas Leak Repair, ABB inspection | Circuit Breaker |  |  | 240 kV
ATCO | 751s 701C (751s Hill),751s 703 (751s Hill) | 2014-08-27 08:00 | 2014-08-28 17:00 | N | N | Breaker testing. | Circuit Breaker, Shunts
SUNCOR | 29EDD-94 952_9702 (29EDD-94),29EDD-94 952_9701 (29EDD-94) | 2014-08-27 08:00 | 2014-08-28 08:00 | N | Y | Annual maintenance/inspections and function testing. | Circuit Breaker |  |  | 240 kV
AESO-SC | IT Related Changes | 2014-08-27 10:10 | 2014-08-27 10:50 | N | N | CROW Production will be migrated to SDC | SCInternal |  |  | For Information Only
EPCOR | 987S Cloverbar,987s T2 (987s Clover Bar),72CN10 (987s Clover Bar - Namao),987s Clover Bar 72 kV Bus 2 | 2014-08-28 | 2014-08-28 06:00 | N | Y | doble as required | Station, Transformer, Bus, Line |  |  | 240 kV, Pre-Condition, Restricts Generation
SUNCOR | 29EDD-94 952_9703 (29EDD-94),29EDD-94 952_9704 (29EDD-94) | 2014-08-28 08:00 | 2014-08-29 08:00 | N | Y | annual maintenance/inspections and function testing | Circuit Breaker |  |  | 240 kV
ALTALINK | 39s 352 (39s Bickerdike) | 2014-08-28 09:00 | 2014-08-28 12:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 520L (887s Mobil Oil Carson Creek - 520L1),526L (268s Whitecourt - 526DL185) | 2014-08-28 11:00 | 2014-08-28 15:00 | N | N | close jumpers on str 188 & str 204 AFTER new switch installed at str 190 | Line |  |  | Pre-Condition
ALTALINK | 72s Leismer RTU/SCADA | 2014-08-28 12:00 | 2014-08-28 12:30 | N | N | update RTU configuration | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L06 (784s Donnelly - 787s High Prairie) | 2014-08-29 08:00 | 2014-09-05 16:00 | N | N | In service date: August 30, 2014 | Line
ALTALINK | 180s T2 (180s Cope Creek) | 2014-08-29 08:00 | 2014-08-31 18:00 | N | N | warranty work on TX | Transformer |  |  | For Information Only
SUNCOR | 29EDD-94 952-9705 (29EDD-94),29EDD-94 952-9706 (29EDD-94) | 2014-08-29 08:00 | 2014-08-30 08:00 | N | Y | annual maintenance/inspections and function testing | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 1140s Temporary Station | 2014-08-30 08:00 | 2014-09-01 16:00 | N | N | In service date: August 31, 2014 | Transformer
ALTALINK | 821L (158s Vauxhall - 421s Hays),421s 821W (421s Hays) | 2014-08-30 08:00 | 2014-08-30 20:00 | N | N | remove old and install new protection for T1 | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2014-08-30 08:00 | 2014-08-30 16:00 | N | N | hot spot repairs | Line, Transformer |  |  | For Information Only
ENMAX | 162s 240-133 (162s Beddington) | 2014-08-30 08:00 | 2014-08-31 16:00 | N | Y | maintenance, SF6 sample and install new position indicator | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 421s C1 (421s Hays),421s 30 (421s Hays) | 2014-08-31 08:00 | 2014-08-31 20:00 | N | N | remove old and install new protection for T1 | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 6L68 (734s Sturgeon - 787s High Prairie) | 2014-09-01 07:00 | 2014-09-04 17:00 | N | N | start the salvage on 6L68 once the new 144 kV sub is up and running | Line |  | This outage is to start the salvage on 6L68 once the new 144kv sub is up and running | Firm Load Loss, Creates Radial Feeds
ATCO | 942S Nabiye | 2014-09-01 08:00 | 2014-09-26 16:00 | N | N | In service date: Sept 25, 2014 with 7L161 | Station |  |  | For Information Only
ATCO | 721S La Corey,7L89 (721s La Corey - 700s Bonnyville),7L89 (826s Marguerite Lake - 721s La Corey) | 2014-09-01 08:00 | 2014-09-01 16:00 | N | N | install mobile sub 835S on 7L89 at 721S Lacorey | Line, Station |  | Install mobile sub 835S on 7L89 at 721S Lacorey between 7L89D2 and 7L89D1 Mobile will be energized at the end of the day from the 144kv Check phasing across 500D3, Ensure mobile sub settings installed, ensure 826S 7L89 temporary settings installed for 835S Ensure 701T Bus Differencial protection is blocked prior to closing 500D3, Pick up 721S load on Aug 29 See GOI for 721S Lacorey 144kv bus to install new 144kv PT's and 702A disconnect, Aug 29 to Sep 10 | Pre-Condition
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2014-09-01 08:00 | 2014-09-03 16:00 | N | Y | first year check/maintenance (first 2 days), doble (3rd day), SF6 sample, install new position indicator | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Syncrude | Mildred_1015 (Syncrude Mildred Lake),ML2 (Syncrude Mildred Lake - UE_1 Syncrude Plant 30-2) | 2014-09-01 08:00 | 2014-09-07 18:00 | N | N | breaker 1015 - 72kV upgrade | Line, Circuit Breaker
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-09-01 10:00 | 2014-09-01 14:00 | N | N | off peak substation washing | Line, Transformer |  |  | Pre-Condition, Overload
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-09-02 02:00 | 2014-09-02 06:00 | N | N | off peak substation washing | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 814L (121s Brooks - 28s West Brooks),28s 22 (28s West Brooks) | 2014-09-02 07:00 | 2014-09-07 17:00 | N | N | replace 28s22 breaker with new SF6 breaker and install new LAs | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2014-09-02 07:30 | 2014-09-14 17:00 | Y | Y | in conjunction L to J: maintenance, jumper repairs, inspection and barehand training | Line |  |  | Limits ATC, 500 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2014-09-02 07:30 | 2014-09-14 17:00 | N | Y | meter replacement as well as install some marker balls in the US section of the line | Line |  |  | 240 kV, Limits ATC
ALTALINK | 936L (102s Langdon - 74s Janet) | 2014-09-02 07:30 | 2014-09-06 18:00 | N | Y | L to J: 936L bay swap from L12 to L17 | Line |  |  | 240 kV, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 610L (336s Fincastle - 83s Taber) | 2014-09-02 08:00 | 2014-09-08 17:00 | N | Y | 138kV breaker replacement and add LAs to 610L | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 520s Bennett | 2014-09-02 08:00 | 2014-09-14 17:00 | N | N | connect tertiary station service to transformers | Station |  |  | 240 kV, For Information Only, 500 kV
ALTALINK | 795L (121s Brooks - 421s Hays),421s 795N (421s Hays) | 2014-09-02 08:00 | 2014-09-02 20:00 | N | N | remove old and install new protection for T1 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale RR729 (Rossdale) | 2014-09-02 08:00 | 2014-09-03 18:00 | N | N | doble of 72CT321, 322,323 | Circuit Breaker |  |  | For Information Only
EPCOR | 987s C2402 (987s Clover Bar) | 2014-09-02 08:00 | 2014-09-05 18:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2014-09-02 08:30 | 2014-09-04 16:30 | N | Y | climbing patrol | Line |  | 7L77 WILL BE REMOVED FROM SERVICE FOR A CLIMBING PATROL | For Information Only
ALTALINK | 310p 1852 (310p Sundance) | 2014-09-02 08:30 | 2014-09-05 16:30 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 835L (384s Keystone - 835L tap),384s 835X (384s Keystone) | 2014-09-02 09:00 | 2014-09-04 14:00 | N | N | install new air break on east side of 835L tap | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PL6-4 (836s Steepbank - 29EDD-1) | 2014-09-02 09:00 | 2014-09-03 19:00 | N | N | isolation of line 29PL6-4 for ATCO to repair MOD 29PL6-4D1 @ 836s Steepbank | Line |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39),22PT138-Z7 (ENMAX 22) | 2014-09-02 10:00 | 2014-09-02 14:00 | N | N | off peak substation washing | Line, Transformer, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 801s 902 (801s Anderson) | 2014-09-02 10:00 | 2014-09-05 16:00 | N | Y | breaker inspection | Circuit Breaker |  | 902 Breaker Interrupter Inspection @ 801S Anderson We have been directed by the equipment manufacturer to inspect the interrupters in this breaker due to its inability to clear a fault before the breaker fail protection is initiated. | 240 kV, For Information Only
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),420s 636 (420s Broadmoor) | 2014-09-02 11:00 | 2014-09-02 18:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s C1 (157s Lac La Biche) | 2014-09-02 13:00 | 2014-09-02 18:00 | N | N | cap bank repair | Shunts |  |  | For Information Only
ALTALINK | 163s T5 (163s Amoco Empress) | 2014-09-02 13:00 | 2014-09-11 17:00 | N | Y | 240kV/138kV bushing replacements | Transformer |  |  | 240 kV, For Information Only
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13),22PT138-Z7 (ENMAX 22) | 2014-09-02 18:00 | 2014-09-02 22:00 | N | N | off peak substation washing | Transformer, Line, Terminal Equipment |  |  | For Information Only
ALTALINK | 727L (74s Janet - 678s Okotoks) | 2014-09-03 07:00 | 2014-09-05 18:00 | N | N | L to J: accommodate 936L line swap from 74s L12 to L17 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2014-09-03 08:00 | 2014-09-03 17:00 | N | N | line maintenance - structure replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 32,31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2014-09-03 08:00 | 2014-09-03 10:00 | N | N | substation washing | Station, Line, Transformer
ENMAX | 25B240-D132 (ENMAX 25) | 2014-09-03 08:00 | 2014-09-05 16:00 | N | Y | first year check/maintenance, doble, SF6 sample, install new position indicator | Circuit Breaker |  |  | 240 kV
ATCO | 716s 701 (716s Lloydminster) | 2014-09-03 08:00 | 2014-09-04 17:00 | N | N | breaker SF6 testing | Circuit Breaker |  | 716S - 701 BREAKER SF6 HGF COMPLETE TESTING THIS PERMIT HAS BEEN RE-SCHEDULED | Pre-Condition
ATCO | 809s 902T (809s Louise Creek) | 2014-09-03 08:00 | 2014-09-04 16:00 | N | Y | repair broken MOD, lightning arrestors and 702B | Transformer |  | 809S Louise Creek 902T Outage and Worklist -Repair U/G Cable from 500D1 to J1 -Re-install J1 -Repair broken MOD 500D3 -Replace 902T Lightning Arrestors -Repair/Adjust 702B | 240 kV
ATCO, IMPERIALOIL | 7L105 (837s Mahihkan - 909s Mahno) | 2014-09-03 08:00 | 2014-09-03 18:00 | N | Y | connecting 7L161 at Mahno | Line |  | -Request Atco to open breaker 702 in Mahihkan Sub 837s de-energizing 7L105 ESSO IS CONNECTING 7L161 AT 909S MOHNO
ALTALINK | 183s T2 (183s Underwood) | 2014-09-03 08:00 | 2014-09-04 12:00 | N | N | replace Qualitrol 930 (fast gas monitor) & clean transformer pit | Transformer
ALTALINK | 409s T1 (409s Shell Scotford) | 2014-09-03 08:00 | 2014-09-04 17:00 | N | N | transformer oil leak repairs | Transformer
ALTALINK | 359s T2 (359s Esso West Pembina) | 2014-09-03 08:00 | 2014-09-04 17:00 | N | N | repair bushing cracks | Transformer
ALTALINK | 89s 2252 (89s Ellerslie) | 2014-09-03 08:00 | 2014-09-05 17:30 | N | Y | investigate CT SF6 level | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
IMPERIALOIL | 7L161 (909s Mahno - 942s Nabiye) | 2014-09-03 08:00 | 2014-09-03 18:00 | N | N | preparation for commissioning | Line |  |  | For Information Only
ATCO | 7L583 (970s Bourque - 715s Leming Lake) | 2014-09-03 08:30 | 2014-09-03 16:30 | N | N | breaker mainteneance | Line |  | 7L583 WILL BE OPEN ENDED @ 715S LEMING LAKE FOR MTCE ON BKR 701
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2014-09-03 09:00 | 2014-09-04 17:00 | N | N | transformer maintenance | Transformer
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),32PT138-Z31 (ENMAX 32),54PT138-32.82 (ENMAX 54) | 2014-09-03 10:00 | 2014-09-03 14:00 | N | N | substation washing (wash structure #1) | Transformer, Line, Terminal Equipment |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2014-09-03 18:00 | 2014-09-03 22:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2014-09-03 22:00 | 2014-09-04 02:00 | N | N | off peak substation washing & 11.83L 21 relay outage | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | EGC1 Shepard Generator Test | 2014-09-04 08:00 | 2015-03-10 16:00 | N | N | First synch: September 04, 2014. Refer to the Op Plan binder for the commissioning plan. | Unit
ENMAX | 5.2TR (ENMAX 5),5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2014-09-04 08:00 | 2014-09-04 11:00 | N | N | substation washing | Transformer, Line |  |  | Overload
ALTALINK | 454s1 (454s BuckLake) | 2014-09-04 08:00 | 2014-09-04 17:00 | N | N | salvage the slack span into the old Buck Lake sub | Switch |  |  | For Information Only
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2014-09-04 08:00 | 2014-09-04 17:00 | N | Y | 138kV breaker maintenance andfuse alarm | Shunts, Circuit Breaker |  |  | Limits ATC
EPCOR | 987s C1 (987s Clover Bar),72CH9 (Hardisty - 987s Clover Bar),987s Cloverbar 72kV Bus 2 | 2014-09-04 08:00 | 2014-09-05 18:00 | N | N | doble of 72CVT56,57,58 | Bus, Shunts, Line |  |  | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2014-09-04 10:00 | 2014-09-04 14:00 | N | N | at 56s remove 475s mobile (HS) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2014-09-04 11:00 | 2014-09-04 14:00 | N | N | substation washing | Transformer, Line |  |  | Overload
ENMAX | 2.83L (ENMAX 13 - 2.83L tap),5.9TR (ENMAX 5),5.10TR (ENMAX 5) | 2014-09-04 14:00 | 2014-09-04 16:00 | N | N | substation washing | Transformer, Line
ALTALINK | 102s SVC (102s Langdon),102s T4 (102s Langdon) | 2014-09-05 07:30 | 2014-09-05 17:00 | N | Y | doble | Transformer, Shunts |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41),41MD138-41.2TR (ENMAX 41) | 2014-09-05 08:00 | 2014-09-05 16:00 | N | N | substation washing & emergency switch repairs | Transformer, Line, Switch |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1),20PT138-Z31 (ENMAX 20) | 2014-09-05 08:00 | 2014-09-05 10:00 | N | N | substation washing | Transformer, Line, Terminal Equipment |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 452s T1 (452s B.F. Goodrich Fort Saskatchewan) | 2014-09-05 09:00 | 2014-09-05 17:00 | N | N | T1 oil leak and clean | Transformer
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2014-09-05 10:00 | 2014-09-05 12:00 | N | N | substation washing | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2014-09-05 10:00 | 2014-09-05 11:00 | N | N | transducer checks | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2014-09-05 11:00 | 2014-09-05 12:00 | N | N | transducer checks | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2752 (310p Sundance) | 2014-09-05 14:30 | 2014-09-05 15:00 | N | N | trip test from 310p2652 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2552 (310p Sundance) | 2014-09-05 15:15 | 2014-09-05 15:45 | N | N | trip test from 310p2652 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 74s 2352 (74s Janet) | 2014-09-05 18:01 | 2014-10-28 18:00 | N | Y | L to J: P&C work for future 985L(L10) bay | Circuit Breaker |  |  | 240 kV
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome) | 2014-09-06 07:00 | 2014-09-06 12:00 | N | Y | doble of line CT | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-RB134 (162s Beddington) | 2014-09-06 08:00 | 2014-09-07 16:00 | N | Y | maintenance, SF6 Sample, install new position indicator | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2014-09-06 08:00 | 2014-09-06 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 184s T3 (184s Petro-Canada Edmonton) | 2014-09-06 08:00 | 2014-09-12 17:00 | N | N | metering upgrade | Transformer
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2014-09-06 12:00 | 2014-09-06 18:00 | N | Y | doble of line CT's | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2014-09-06 12:00 | 2014-09-06 16:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition
ALTALINK | 74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2014-09-07 06:00 | 2014-09-07 15:00 | N | Y | ECTP and L to J: String new 985L(L10 Bay) twin curlew slack span over B2 Bus and roll phases to correct phasing for the temp 937L bay(L12). In conjunction with 937L line move. | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 721s 701T (721s La Corey),7L89 (721s La Corey - 700s Bonnyville) | 2014-09-07 08:00 | 2014-09-21 08:00 | N | N | Install 700PT1 and 702A Temp mobile substation will be carrying all 25 kV load | Line, Transformer |  | Install 700PT1 and 702A Temp mobile substation will be carrying all 25 kV load | Pre-Condition, For Information Only
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2014-09-07 08:00 | 2014-09-07 12:00 | N | N | Substation Washing | Transformer, Line |  |  | For Information Only
ATCO | 721S La Corey,7L89 (721s La Corey - 700s Bonnyville) | 2014-09-07 08:00 | 2014-09-07 16:00 | N | N | To Maintain LOA to Install risers on 500D3 for the mobile substation | Station, Line |  | To Maintain LOA to Install risers on 500D3 for the mobile substation | Prevents Normal Events
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2014-09-07 08:00 | 2014-09-07 18:00 | N | N | Doble of line CT's @ Lambton & Breaker maint on S724 @ Strathcona | Line
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2014-09-07 12:00 | 2014-09-07 16:00 | N | N | Substation Washing | Line, Shunts, Transformer |  |  | For Information Only
ALTALINK | 727L (74s Janet - 1140s Temp) | 2014-09-08 07:00 | 2014-09-11 18:00 | N | N | L to J: accommodate 937L line swap from 74s L10 to L12 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 937L (102s Langdon - 74s Janet) | 2014-09-08 07:00 | 2014-09-13 18:00 | N | Y | L to J: 937L bay swap from L10 to old 936L bay L12. Close Open Point T and create Open point D. | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 5s C3 (5s East Calgary),5s C2 (5s East Calgary) | 2014-09-08 07:30 | 2014-09-16 09:30 | N | Y | ECTP - remove the slack span from 2.82L | Shunts |  |  | Limits ATC
EPCOR | Hardisty T3 (Hardisty) | 2014-09-08 08:00 | 2014-09-12 08:10 | N | N | relay & apparatus maintenance as required | Transformer |  |  | For Information Only
ALTALINK | 275s 1852 (275s Jenner) | 2014-09-08 08:00 | 2014-09-08 17:00 | N | Y | gas leak | Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2014-09-08 08:00 | 2014-09-12 17:00 | N | N | temperature monitor installation | Line |  |  | For Information Only
ALTALINK, EPCOR | 1059AL (52s East Industrial - 1059L tap),1059L (38s East Edmonton - 803s Lambton) | 2014-09-08 08:00 | 2014-09-08 08:10 | N | Y | facilitate the opening of EDS1 240 kV air break at 52S | Line |  |  | 240 kV, For Information Only
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2014-09-08 08:00 | 2014-09-19 16:00 | N | N | ECTP, Swap AIS to GIS | Line |  |  | Overload, Contingency Requires Mitigation
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2014-09-08 08:00 | 2014-09-08 12:00 | N | N | Substation Washing | Transformer, Line |  |  | Overload, Contingency Requires Mitigation
ENMAX | 23.3TR (ENMAX 23),ENMAX 23 138 kV West Bus | 2014-09-08 08:00 | 2014-09-20 16:00 | N | N | install new MD for 23.3TR | Transformer, Bus
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2014-09-08 08:00 | 2014-09-10 17:00 | N | N | Woodcroft Bus replacement | Line
ENMAX | 65.2 TR (ENMAX 65) | 2014-09-08 08:00 | 2014-09-12 16:00 | N | Y | doble work | Transformer |  |  | 240 kV
ENMAX | ENMAX 25 B240-D139 (ENMAX 25) | 2014-09-08 08:00 | 2014-09-10 16:00 | N | Y | First year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 199s C1 (199s East Ardrie),631L (199s East Airdrie - 186s Dry Creek),688L (199s East Airdrie - 688DL23) | 2014-09-08 08:00 | 2014-09-08 12:00 | N | N | create open point on north side of bus to facilitate replacement of 199s15 | Shunts, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T2 (987s Clover Bar),987s C2406 (987s Clover Bar) | 2014-09-08 08:00 | 2014-09-08 12:00 | N | Y | momentary outage to de-energize C2408 | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 987s T4 (987s Clover Bar),987s C2405 (987s Clover Bar) | 2014-09-08 08:00 | 2014-09-12 18:00 | N | Y | breaker maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 816s T2 (816s Petrolia) | 2014-09-08 08:00 | 2014-09-21 18:00 | N | N | Replacement of PAB2 and Doble of TX, SA's, & CVT. | Transformer |  |  | 240 kV
EPCOR | 52s T1 (52s East Industrial) | 2014-09-08 08:00 | 2014-09-12 18:00 | N | N | Doble and protection work. | Transformer |  |  | 240 kV, For Information Only
SUNCOR | 29EDD-1 Millennium 260 kV West Bus 1 | 2014-09-08 08:00 | 2014-09-14 19:00 | N | Y | bus relay maintenance | Bus |  |  | 240 kV
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2014-09-08 08:30 | 2014-09-08 16:30 | N | N | climbing patrol | Line |  |  | Pre-Condition
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2014-09-08 08:30 | 2014-09-12 17:30 | N | N | Line maintenance. (Also see CROW #2-29662 -7L45) | Line |  | LINE MAINT. (SEE ALSO CROW #2-29662 -7L45) | Pre-Condition
ATCO, IMPERIALOIL | 7L105 (837s Mahihkan - 909s Mahno),837s 702 (837s Mahihkan) | 2014-09-08 09:00 | 2014-09-19 17:00 | N | Y | replacement of breaker 702 | Line, Circuit Breaker |  | Replacement of 702 Breaker. SEVERE OIL LEAK. 7L105 WILL BE OPEN ENDED AT 837S WHILE BY PASS IS IN PLACE related permits 2-29717, 2-2-718, 2-29720 | For Information Only
ATCO | 7L157 (837s Mahihkan - 970s Bourque) | 2014-09-08 09:00 | 2014-09-08 18:00 | N | N | allow live tap to 7L105 | Line |  | Line Outage on 7L157 Allowing Live tap to 7L105 see long.... The line will be isolated between the substations 970S and 837S and at the crossing in the field were 7L105 passes above 7L157 The TAP to the LIVE 7L105 Line will be made. The line crew will require isolation of the bottom 7L157 CCT to allow they remove the outside phase allowing access to the center tap. Allowance will be required to complete the work within the GOI points requested 7L157D2 at 970S and 7L157D1 at 837s Mahihkan. Phasing will occur at the 970S Bourque line end prior to placing the line in service from the 970S End. Protection changes will be made to both the 7L157 A & B protection prior to the work in a planned CSP on Sept 2&3 in preparation for the work. This will allow 7L105 to be open ended at 837S breaker 702 and intended open terminal 7L157 Breaker 701 @ 837S Mahihkan. Protection Modifications are under investigation for the closed terminal current 7L105 Feed Breaker 702 at 837S and Parallel feed terminal 7L157 Breaker 701 at Mahihkan RELATED PERMITS 2-29717, 2-29718, 2-29292
ALTALINK | 74s 2452 (74s Janet) | 2014-09-08 11:00 | 2014-10-28 17:00 | N | Y | 240kV breaker maintenance & replace caps | Circuit Breaker |  |  | 240 kV
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13),ENMAX 27 69kV Bus | 2014-09-08 12:00 | 2014-09-08 16:00 | N | N | Substation Washing | Transformer, Line, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 359s T1 (359s Esso West Pembina) | 2014-09-08 13:00 | 2014-09-09 17:00 | N | N | repair bushing cracks | Transformer
ALTALINK | 121s T2 (121s Brooks),795L (121s Brooks - 421s Hays),827L (121s Brooks - 28s West Brooks),121s4 (121s Brooks),121s Brooks 138kV South Bus | 2014-09-08 13:00 | 2014-09-12 17:00 | N | N | Replace 121s4 PT's | Transformer, Line, Switch, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 835L (283s Violet Grove - 835L tap) | 2014-09-08 15:00 | 2014-09-08 15:00 | N | N | isolating 835L up to the tap point so SNC can install a new air break on the west side of the tap point | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2014-09-09 07:00 | 2014-09-11 06:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 30.1TR (ENMAX 30),6.80L (ENMAX 30 - ENMAX 6),ENMAX 6 B138-6.80 (ENMAX 6) | 2014-09-09 08:00 | 2014-09-09 10:00 | N | N | Substation washing | Transformer, Line, Circuit Breaker |  |  | Overload
ALTALINK | 275s T2 (275s Jenner) | 2014-09-09 08:00 | 2014-09-11 16:00 | N | Y | SCADA Equipment upgrade Project | Transformer |  |  | 240 kV
ALTALINK | 712L (99s North St. Albert - 305s Acheson),99s 712X (99s North St Albert) | 2014-09-09 08:30 | 2014-09-11 17:00 | N | N | replace 712L A & B Protections | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
AESO, ATCO | 6L05 (764s Heisler - 843s Bigknife Creek),701L (223s Strome - 7L701D1) | 2014-09-09 09:00 | 2014-09-09 11:00 | N | N | high load move | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 879s 352 (879s Scotford Upgrader) | 2014-09-09 09:00 | 2014-09-10 17:00 | N | N | Breaker testing | Circuit Breaker |  | 879S - 352 BREAKER SF6 GL212 COMPLETE TESTING Breaker 352 will be out of service for the duration of work | For Information Only
ALTALINK | 749L (899s Edgerton - 749L118AN) | 2014-09-09 10:00 | 2014-09-12 15:00 | N | Y | Line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 722s 702T (722s Crystal Lake) | 2014-09-09 10:00 | 2014-09-11 17:00 | N | N | maintenance | Transformer |  | 722S CRYSTAL LAKE 702T O/S FOR MTCE
ALTALINK | 852s 252 (852s Round Hill) | 2014-09-09 13:00 | 2014-09-09 17:00 | N | N | faulty heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 835L (384s Keystone - 835L tap),384s 13 (384s Keystone) | 2014-09-09 14:00 | 2014-09-12 10:00 | N | N | isolating 835 Line up to the tap point so SNC can install a new air break on the east side of the tap point. | Switch, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 757L (297s Rimbey - 757L69),297s 757 (297s Rimbey) | 2014-09-10 00:01 | 2014-09-10 04:01 | N | N | replacing tank heater | Circuit Breaker, Line
ALTALINK | 250p22 (250p Bighorn) | 2014-09-10 06:00 | 2014-09-11 06:00 | N | N | brushgear work | Switch |  |  | Restricts Generation
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2014-09-10 07:30 | 2014-09-10 12:00 | N | Y | Substation Washing | Shunts, Transformer, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 245S Seebe | 2014-09-10 08:00 | 2014-09-12 17:00 | N | N | replace old VT3 with 3 new metering PTs | Station
ALTALINK | 310p 2652 (310p Sundance) | 2014-09-10 08:00 | 2014-09-10 10:00 | N | Y | connect/test for fail initiate from line protection (urgent), 989L A protection will be affected | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 38s T2 (38s East Edmonton) | 2014-09-10 08:00 | 2014-09-10 17:00 | N | N | hot switch repairs | Transformer
ENMAX | ENMAX 25 B240-D138 (ENMAX 25) | 2014-09-10 08:00 | 2014-09-12 16:00 | N | Y | first year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV
ALTALINK | 698s T2 (698s Jackfish) | 2014-09-10 09:00 | 2014-09-10 17:00 | N | N | transformer doble | Transformer |  |  | 240 kV, For Information Only
SUNCOR | Suncor RTU/SCADA | 2014-09-10 10:00 | 2014-09-10 12:00 | N | N | Add a few additional points into the DNP maps to AESO. These points need to be added into the DNP mapping to keep it synchronized with the ICCP mapping for redundancy. | Terminal Equipment |  |  | Affects Visibility
ATCO | 795s 702T (795s Zama) | 2014-09-10 11:15 | 2014-09-10 12:00 | N | N | 50/51/51N Relay Settings Change and Test | Transformer |  | 795S 702T 50/51/51N Relay Settings Change and Test 702T O/S DURING WORK SEE GOI #2-28945
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2014-09-10 12:00 | 2014-09-10 16:00 | N | Y | Substation Washing | Shunts, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2014-09-10 14:00 | 2014-09-10 16:00 | N | N | connect mobile to 735L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-09-11 03:00 | 2014-09-11 03:59 | N | N | high load | Line |  |  | Pre-Condition, For Information Only
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2014-09-11 04:00 | 2014-09-11 05:00 | N | N | high load | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 524s T1 (524s Owen Corning) | 2014-09-11 07:00 | 2014-09-11 12:00 | N | N | repair of hot connection on 15kv fuses | Transformer
ALTALINK | 723s 652 (723s Christina Lake) | 2014-09-11 08:00 | 2014-09-11 12:00 | N | Y | low gas alarm / close indicator | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2014-09-11 08:00 | 2014-09-11 16:00 | N | N | 65LA138-26.83L-C | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7),7PT138-Z31,7PT138-Z31 (ENMAX 7) | 2014-09-11 08:00 | 2014-09-11 10:00 | N | N | substation washing | Transformer, Line, Terminal Equipment |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 171s T2 (171s Redwater) | 2014-09-11 09:00 | 2014-09-25 09:00 | N | N | install new 25 kV breaker, metering upgrade | Transformer
ATCO | 7L16 (766s Nevis - 948s Heatburg),766s 702 (766s Nevis) | 2014-09-11 09:00 | 2014-09-11 16:00 | N | N | breaker partial testing | Line, Circuit Breaker |  | 766s - 702 BREAKER SF6 LTB145D1/B PARTIAL TESTING | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7),7PT138-Z31 (ENMAX 7) | 2014-09-11 10:00 | 2014-09-11 12:00 | N | Y | substation washing | Transformer, Terminal Equipment, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199s T1 (199s East Airdrie),631L (199s East Airdrie - 186s Dry Creek) | 2014-09-11 12:01 | 2014-09-15 08:00 | N | N | replacement of 199s15 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 940S Beartrap,940s 701 (940s Beartrap) | 2014-09-11 14:00 | 2014-09-11 19:00 | N | N | add trips & block closes from 50BF/702 | Circuit Breaker, Station |  | GOI for 701 Bay-Enbridge is planning an outage for themselves on Sept 11 for 7 hours starting at 14:00. When they go offline, I need to get a GOI for 701 breaker as I need to add in some trips and block closes which comes from 50BF/702. I will need it for about 5 hours.
EPCOR | 987S Cloverbar | 2014-09-11 23:30 | 2014-09-12 06:00 | N | Y | doble of SA's & CVT's | Station |  |  | Restricts Generation
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-09-12 02:30 | 2014-09-12 05:00 | N | N | high load move | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 850L (74s Janet - 525s Carseland) | 2014-09-12 07:00 | 2014-09-23 17:00 | N | N | ECTP: Tie Down Line to facilitate 985L installation for ENMAX Sheppard Generation. Tie into Temp 1140s and create open point @ Tap Stru# | Line |  |  | Creates Radial Feeds
ALTALINK | 17s T2 (17s Benalto),848L (17s Benalto - 848L490E),17s 85 (17s Benalto) | 2014-09-12 07:00 | 2014-09-17 17:00 | N | Y | install new screw piles | Circuit Breaker, Transformer, Line |  |  | 240 kV
ENMAX | 1.5TR (ENMAX 1) | 2014-09-12 08:00 | 2014-09-12 10:00 | N | N | Substation Washing | Transformer |  |  | For Information Only
ALTALINK | 113L (20s Ghost - 33s Spray) | 2014-09-12 08:00 | 2014-09-12 17:00 | N | N | Emergency repair on the line | Line |  |  | For Information Only
ATCO | 7L97 (933s Tower Road - 7LA97) | 2014-09-12 08:00 | 2014-09-12 16:00 | N | N | Emergency repair. Insulators. | Line |  |  | Creates Radial Feeds
ALTALINK, ENMAX | 832L (ENMAX 10 - ENMAX 12),693L (42s Sarcee - ENMAX 10) | 2014-09-12 08:00 | 2014-09-14 17:30 | N | Y | Change insulation on structure #1 / remove span that is between structure 1 and structure 23 on 693L. | Line |  |  | Pre-Condition
ALTALINK | 172s T1 (172s Sherritt Gordon),172s 71 (172s Sherrit) | 2014-09-12 08:30 | 2014-09-12 12:30 | N | N | Transformer & Breaker Maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2014-09-12 09:00 | 2014-09-12 11:00 | N | N | Connect mobile to 805L | Line |  |  | Creates Radial Feeds
ENMAX | 1.6TR (ENMAX 1) | 2014-09-12 10:00 | 2014-09-12 12:00 | N | N | Substation Washing | Transformer |  |  | For Information Only
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone),837L (964s Pigeon Lake - 538s Burford) | 2014-09-12 11:01 | 2014-09-12 17:00 | N | N | Create isolation for 964s mobile install | Line |  |  | Creates Radial Feeds
EPCOR | 987s T2 (987s Clover Bar) | 2014-09-12 12:00 | 2014-09-12 18:00 | N | N | momentary outage to energize C2408 without operation | Transformer |  |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2014-09-12 12:00 | 2014-09-12 14:00 | N | N | Substation Washing | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2014-09-12 14:00 | 2014-09-12 16:00 | N | N | Substation Washing | Transformer |  |  | For Information Only
ALTALINK | 172s T2 (172s Sherritt Gordon),172s 72 (172s Sherrit) | 2014-09-12 14:30 | 2014-09-12 19:00 | N | N | Transformer & Breaker Maintenance | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 185L (396s Pincher Creek - 379s Shell Canada Waterton) | 2014-09-12 15:00 | 2014-09-14 18:00 | N | N | real-time urgent repair | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss
EPCOR, ALTALINK | 1059AL (52s East Industrial - 1059L tap),1059L (38s East Edmonton - 803s Lambton) | 2014-09-12 16:00 | 2014-09-12 16:10 | N | Y | require the 1059 Line De-energized in order to facilitate the closing of EDS1 240 Kv Air Break at 52S | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 837L (964s Pigeon Lake - 538s Burford) | 2014-09-12 17:01 | 2014-09-19 09:00 | N | N | replace 138kV LA's, add 25kV LA's, replace 964s4 & s24, replace 964s UG Cables, replace 964s837W | Line |  |  | Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38),38PT138-Z5 (ENMAX 38) | 2014-09-13 07:30 | 2014-09-13 12:00 | N | Y | substation washing | Line, Transformer, Shunts, Terminal Equipment |  |  | Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 172L (83s Taber - 172L944A),83s 172W (83s Taber) | 2014-09-13 08:00 | 2014-09-14 18:00 | N | Y | replace 138kV CTs on breaker 83s172W | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 26.81L (ENMAX 54 - ENMAX 26) | 2014-09-13 08:00 | 2014-09-13 16:00 | N | N | breaker maintenance 54B138-26.81 | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | NamaoT3 (Namao) | 2014-09-13 08:00 | 2014-09-14 18:00 | N | N | repair of NAB3 disconnect | Transformer
ALTALINK | 74s 552 (74s Janet) | 2014-09-13 08:00 | 2014-09-13 09:00 | N | Y | P & C functional test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Woodcroft T1 (Woodcroft) | 2014-09-13 08:00 | 2014-09-14 18:00 | N | N | doble as required | Transformer
SUNCOR | 29EDD-71 Edd71Sub | 2014-09-13 08:00 | 2014-09-15 08:00 | N | Y | 29EDD-71 PS-235 Adjustment Required (ISO) | Station |  |  | Restricts Generation
ALTALINK | 320p 3052 (320p Keephills) | 2014-09-13 08:00 | 2014-09-13 16:00 | N | Y | Breaker urgent maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2014-09-13 08:00 | 2014-09-13 16:00 | N | N | sheath/oil testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2052 (74s Janet) | 2014-09-13 11:00 | 2014-09-13 12:00 | N | Y | P & C functional test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37),38PT138-Z5 (ENMAX 38) | 2014-09-13 12:01 | 2014-09-13 16:00 | N | Y | substation washing | Terminal Equipment, Line, Transformer, Shunts |  |  | Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2552 (74s Janet) | 2014-09-13 13:00 | 2014-09-13 14:00 | N | Y | P & C functional test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 918L (17s Benalto - 162s Beddington) | 2014-09-14 07:30 | 2014-09-14 09:59 | N | Y | substation washing - 162 Sub | Line |  |  | Pre-Condition, Limits ATC, Contingency Requires Mitigation
EPCOR | 557s T2 (557s Castle Downs) | 2014-09-14 08:00 | 2014-09-20 17:00 | N | Y | P&C maintenance as required | Transformer |  |  | 240 kV
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2014-09-14 08:00 | 2014-09-14 16:00 | N | N | check contact status on Z32 MD's | Transformer, Line |  |  | Pre-Condition
ALTALINK | 932L (74s Janet - 162s Beddington) | 2014-09-14 10:00 | 2014-09-14 11:59 | N | Y | substation washing - 162 sub | Line |  |  | 240 kV, Overload, Limits ATC
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2014-09-14 12:00 | 2014-09-14 13:59 | N | Y | substation washing - 162 Sub | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2014-09-14 14:00 | 2014-09-14 15:59 | N | N | substation washing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-09-14 16:00 | 2014-09-14 18:00 | N | N | substation washing | Line |  |  | Pre-Condition
EPCOR | NamaoT3 (Namao) | 2014-09-14 18:00 | 2014-10-05 18:00 | N | N | reconfiguration of Tx#3 secondary cables into new bus | Transformer |  |  | For Information Only
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2014-09-15 07:30 | 2014-10-19 18:00 | N | Y | FATD - SFTP: bypass #3 # 4 & Crossing, relocate a portion of 911L off of existing ROW to allow for new 1037/1038 | Line |  |  | 240 kV, Overload, Limits ATC
ALTALINK | 908L (89s Ellerslie - 38s East Edmonton) | 2014-09-15 08:00 | 2014-09-15 08:10 | N | N | advice for Epcor work at E52s | Line
ENMAX | 162s 240-RB135 (162s Beddington) | 2014-09-15 08:00 | 2014-09-17 16:00 | N | Y | maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 52s T2 (52s East Industrial) | 2014-09-15 08:00 | 2014-09-19 17:00 | N | Y | doble/SFRA and P&C work on A protection | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 65s T3 (65s High River) | 2014-09-15 08:00 | 2014-09-15 10:00 | N | N | FATD:Foothills 138kV Projects: remove CT contribution for new 138 kV bus protection upgrade | Transformer |  |  | For Information Only
ALTALINK | 820L (67s Stirling - 820AL tap) | 2014-09-15 08:00 | 2014-09-19 17:00 | N | N | replace 67s2 breaker | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 65.1 TR (ENMAX 65) | 2014-09-15 08:00 | 2014-09-19 16:00 | N | Y | doble, check Rev SW, LTC DGA | Transformer |  |  | 240 kV
ALTALINK | 149s T1 (149s Nisku) | 2014-09-15 08:00 | 2014-09-18 17:00 | N | N | bird cover-up & LA's | Transformer
ENMAX | 65.1 TR (ENMAX 65),ENMAX 65 240 kV South Bus | 2014-09-15 08:00 | 2014-09-15 16:00 | N | Y | FATD | Transformer, Bus |  |  | 240 kV, For Information Only
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2014-09-15 08:00 | 2014-09-19 16:00 | N | Y | installation of receiving structure | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2014-09-15 08:00 | 2014-09-24 17:00 | N | Y | line crossing - WATL | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 437s T1 (437s Baymag) | 2014-09-15 08:00 | 2014-09-16 16:00 | N | N | customer requested outage for annual maintenance | Transformer
SUNCOR | 29EDD-1 Millennium 260 kV North Bus 2 | 2014-09-15 08:00 | 2014-10-01 16:00 | N | Y | bus maintenance | Bus |  |  | 240 kV, For Information Only
NRGREEN | NRG3 NRGreen Cogen | 2014-09-15 08:00 | 2014-10-31 16:00 | N | N | In service date: Sept 16, 2014. Refer to the Op Plan binder fort the commissioning plan. (15 MW) | Unit
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor) | 2014-09-15 08:00 | 2014-09-19 17:00 | N | N | move 731L over to the next bay in substation (old 865L position) | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 983L (251s Whitla - 244s Bowmanton),964L (251s Whitla - 244s Bowmanton) | 2014-09-15 08:00 | 2014-11-21 17:00 | N | Y | step bolt replacement - deficiency from construction - SATR BW | Line |  |  | 240 kV, For Information Only
ALTALINK | 908L (89s Ellerslie - 38s East Edmonton) | 2014-09-15 08:00 | 2014-09-15 08:10 | N | Y | momentary outage to isolate 52sT2 | Line |  |  | 240 kV, Pre-Condition
EPCOR | 72RS5 (Rossdale - Strathcona) | 2014-09-15 08:00 | 2014-09-16 18:00 | N | N | replacement of breaker S721 bushing | Line |  |  | For Information Only
EPCOR | 803s L2401 (803s Lambton) | 2014-09-15 08:00 | 2014-10-10 18:00 | N | Y | replace CT's | Circuit Breaker |  |  | 240 kV
ATCO | 706S 505,706S 506 | 2014-09-15 08:00 | 2014-09-19 16:00 | N | N | wiring and test the trip circuit for 7L53 RAS addition | Terminal Equipment |  | Wiring and test the trip circuit of 506 for 7L53 RAS addition Release COG on 500MT2D and put in service 500MT2 End to End checks with SCC on 502TD
ALTALINK | 199s C1 (199s East Ardrie),199s T1 (199s East Airdrie),199s T2 (199s East Airdrie),631L (199s East Airdrie - 186s Dry Creek),688L (199s East Airdrie - 688DL23),199s East Airdrie 138kV bus | 2014-09-15 08:01 | 2014-09-15 17:00 | N | N | Close open point on north side of bus after replacement of 199s15, final adjustment of 199s15 | Bus, Shunts, Transformer, Line |  |  | Creates Radial Feeds
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2014-09-15 08:30 | 2014-09-19 17:30 | N | N | inspection and install conductor damper | Line |  | A portion of 7L45 will be removed from service for inspection and install conductor damper between 7L45D2 and 813S LITTLE SMOKEY | Restricts Generation, Creates Radial Feeds
ALTALINK | 310p 1352 (310p Sundance),310p 1452 (310p Sundance) | 2014-09-15 08:30 | 2014-10-17 17:00 | N | Y | replace 310p1352, replace 310p1352 CTs, replace 310p1452 CTs, replace 310p1352 breaker fail protection, replace PTs | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 42s T2 (42s Sarcee) | 2014-09-15 11:00 | 2014-09-18 17:00 | N | Y | bushing replacement | Transformer |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 507L (257s Hull - 83s Taber),83s 507 (83s Taber) | 2014-09-15 12:00 | 2014-09-15 17:00 | N | N | tank heater replacement | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 233s T2 (233s Beamer),708L (233s Beamer - 708L88N),735L (171s Redwater - 233s Beamer) | 2014-09-15 12:00 | 2014-09-19 16:00 | N | N | bus protection upgrade & transformer maintenance | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 378s 552 (378s Shell Caroline) | 2014-09-15 12:00 | 2014-09-15 17:00 | N | N | replace roll pin and test switch on 378s9 | Circuit Breaker
ALTALINK | 501L (426s Coalspur - 501CL tap) | 2014-09-15 13:00 | 2014-09-16 17:00 | N | N | breaker & regulator maintenance | Line
EPCOR | 805s J2404 (805s Jasper) | 2014-09-15 13:30 | 2014-09-17 16:00 | N | Y | switching demonstration for NAIT students | Circuit Breaker |  |  | 240 kV, For Information Only
TRANSCANADAP | 903S Loyalist | 2014-09-16 07:00 | 2014-09-16 19:00 | N | N | maintenance | Station |  | TRANSCANADA REQUEST SUBSTATION OUTAGE FOR TRANS CANADA MAINTENANCE ON THEIR EQUIPMENT | For Information Only
ALTALINK | 104S Watson Creek | 2014-09-16 07:00 | 2014-09-16 19:00 | N | N | transformer maintenance | Station |  |  | For Information Only
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),ENMAX 36 138kV Bus (ENMAX 36) | 2014-09-16 08:00 | 2014-09-16 12:00 | N | N | substation washing | Transformer, Line, Bus |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 716s 701C (716s Lloydminster) | 2014-09-16 08:00 | 2014-09-17 17:00 | N | N | isolate and test breaker | Shunts |  | ISOLATE AND TEST BREAKER 701C will be out of service for the duration of work THIS PERMIT HAS BEEN RE-SCHEDULED | For Information Only
ALTALINK | 429s Nelson Lake RTU/SCADA | 2014-09-16 08:00 | 2014-09-17 17:00 | N | N | RTU replacement project | Terminal Equipment |  |  | For Information Only
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2014-09-16 08:00 | 2014-09-16 10:00 | N | N | pothead washing | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 723L (69s North Barrhead - 723L133),7L230 (69s North Barrhead - 7L230 tap),69s North Barrhead 138kV Bus | 2014-09-16 08:00 | 2014-09-16 17:00 | N | Y | 69s20 & 69s13 switch repairs | Bus, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L36 (820s Hangingstone - 7L36 tap),820s 701 (820s Hangingstone) | 2014-09-16 08:00 | 2014-10-09 17:00 | N | N | CT wiring changes, installation and testing of new 21A/21B relays 7L36 phasing will be done on this permit | Line, Circuit Breaker |  | CT wiring changes, installation and testing of new 21A/21B relays 7L36 phasing will be done on this permit. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s T1 (370s North Lethbridge) | 2014-09-16 08:00 | 2014-09-16 17:00 | N | N | doble 138 kV bushings | Transformer |  |  | For Information Only
ALTALINK | 284S Nose Creek,688AL (284s Nosecreek - 688L tap) | 2014-09-16 08:00 | 2014-09-16 14:00 | N | N | customer requested outage | Station, Line |  |  | For Information Only
ATCO | 876s 902T (876s Brintnell) | 2014-09-16 08:30 | 2014-09-18 17:00 | N | Y | testing | Transformer |  | 876S BRINTNELL 902T O/S FOR TESTING | 240 kV
AESO-SC | DT | 2014-09-16 10:00 | 2014-09-16 11:00 | N | N | Change for Wind project will be deployed | SCInternal |  |  | For Information Only
ATCO | 810s 701T (810s Dome Cutbank) | 2014-09-16 10:00 | 2014-09-18 16:00 | N | N | maintenance | Transformer |  | Load will be transfered to 702T. Sub will be de-rated. this is to be coordinated with oilfield outage. | For Information Only
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36),ENMAX 36 138kV Bus (ENMAX 36) | 2014-09-16 12:00 | 2014-09-16 16:00 | N | Y | substation washing | Transformer, Line, Bus |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L47 (848s Ruth Lake - 718s Parsons Creek) | 2014-09-16 12:00 | 2014-09-16 16:00 | N | N | move pole #185 for infrastructure | Line |  | Move pole #185 for infrastructure | Overload
ALTALINK | 727AL (142s Magcan - 727L39N),727L (65s High River - 727L39S),727L (678s Okotoks - 727L39N) | 2014-09-17 05:00 | 2014-09-17 08:00 | N | N | create open point | Line
ALTALINK | 388s 1 (388s Riverside) | 2014-09-17 06:00 | 2014-09-18 12:00 | N | Y | Customer Maintenance | Switch |  |  | Restricts Generation
ALTALINK | 65s T1 (65s High River),65s T2 (65s High River),753L (65s High River - 253s Blackie),65s High River 138kV Bus 1 | 2014-09-17 07:00 | 2014-09-27 17:00 | N | N | replace 138kV bus and bus protection relays & prepare for new 434L bay | Transformer, Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1),ENMAX 20 B138-1.81 (ENMAX 20) | 2014-09-17 07:00 | 2014-09-17 10:00 | N | N | top up SF6 gas | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 41s T11 (41s Medicine Hat) | 2014-09-17 07:00 | 2014-09-17 11:00 | N | N | set relay settings for the MH138 Tie transformer upgrade | Transformer
AESO-SC | EMS | 2014-09-17 08:00 | 2014-09-17 16:00 | N | N | EMS Q3 Release - Wind particiating in energy market. | SCInternal |  |  | For Information Only
ATCO | 2082S Dog Rib,7L71 (718s Parsons Creek - 2082s Dog Rib) | 2014-09-17 08:00 | 2014-09-17 12:00 | N | N | moving a pole to accommodate new infrastructure | Line, Station |  | Moving a pole to accommodate new infrastructure. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 983S Cadomin,983s T1 (983s Cadomin) | 2014-09-17 08:00 | 2014-09-17 17:00 | N | N | full meter upgrade | Transformer, Station
ENMAX | 25B240-D135 (ENMAX 25) | 2014-09-17 08:00 | 2014-09-19 16:00 | N | Y | maintenance and doble | Circuit Breaker |  |  | 240 kV
ALTALINK | 410s T1 (410s Josephburg) | 2014-09-17 08:00 | 2014-09-17 17:00 | N | Y | transformer maintenance and IDD connection troubleshooting | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 834s 502R (834s Wesley Creek),834s502 (834s Wesley Creek) | 2014-09-17 08:30 | 2014-09-17 16:30 | N | N | breaker maintenance | Shunts, Circuit Breaker |  | At 834s 502R will be out of service because of work on 502 breaker. | For Information Only
ALTALINK | 698s 552 (698s Jackfish),698s T1 (698s Jackfish) | 2014-09-17 08:30 | 2014-09-17 15:00 | N | Y | warranty work | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 734s 701T (734s Sturgeon),736s 601T (736s Valleyview P.R.O.P.L.) | 2014-09-17 09:00 | 2014-09-17 17:00 | N | N | 734S 701T maintenance | Transformer |  | 734S STURGEON 701T O/S FOR MTCE 736S PROPL 601T SHOULD BE REMOVED FROM SERVICE FIRST UNDER CROW #2-29027 PRIOR TO LETTING THIS OUTAGE COMMENCE APPROX 4 MW OF LOAD WILL BE REQUIRED TO BE TRANSFERRED FROM 787S HIGH PRAIRIE TO 882S TRIANGLE PRIOR TO THIS OUTAGE TAKING PLACE UNDER CROW #2-XXXXX
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2014-09-18 08:00 | 2014-09-18 10:00 | N | N | pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 37 (39s Bickerdike) | 2014-09-18 08:00 | 2014-09-18 10:00 | N | N | low gas | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 744L (228s T.M.P.L.Niton - 207s Pinedale),207s 744 (207s Pinedale) | 2014-09-18 08:00 | 2014-09-18 17:00 | N | N | breaker maintenance & cracked silicone | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 554s Travers 240 kV Bus 2 | 2014-09-18 08:00 | 2014-09-18 13:00 | N | Y | Install new corona rings | Bus |  |  | 240 kV
ALTALINK | 921L (71s Lamoureux - 987s Clover Bar) | 2014-09-18 09:00 | 2014-09-18 15:00 | N | Y | replace cracked insulator hanger bracket (urgent repair) | Line |  |  | 240 kV
ALTALINK | 71s C1 (71s Lamoureux),71s 952 (71s Lamoureux) | 2014-09-18 09:00 | 2014-09-18 15:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 39s 152 (39s Bickerdike) | 2014-09-18 10:00 | 2014-09-18 12:00 | N | N | low gas | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 1120L (410s Josephburg - 108s Amelia),410s6 (410s Josephburg) | 2014-09-18 11:30 | 2014-09-18 17:00 | N | Y | 240kV switch adjustment | Switch, Line |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1042L (485s Blacksprings - 554s Travers),554s Travers 240 kV Bus 1 | 2014-09-18 14:00 | 2014-09-18 17:00 | N | Y | install new corona rings | Bus, Line |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
EPCOR | 987S Cloverbar,72CH11 (Hardisty - 987s Clover Bar),72CK12 (987s Clover Bar - Kennedale),72CK13 (987s Clover Bar - Kennedale),987s Cloverbar 72kV Bus 3,987S Clover Bar 72 kV Bus 4 | 2014-09-18 23:30 | 2014-09-19 06:00 | N | Y | doble of bus #3 PT's | Bus, Line, Station |  |  | Restricts Generation
ALTALINK | 215L (38s East Edmonton - 286s Yasa),731L (38s East Edmonton - 420s Broadmoor),761L (71s Lamoureux - 38s East Edmonton),38s East Edmonton 138 kV Bus 2 | 2014-09-19 08:00 | 2014-09-19 17:00 | N | N | Rewire 38s227 PT for new ground alarm modules | Line, Bus |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (58s Edson - 178s Cynthia),740L (58s Edson - 39s Bickerdike),58s Edson 138kV East Bus | 2014-09-19 08:00 | 2014-09-19 14:00 | N | N | 58s33 switch adjustment | Bus, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2014-09-19 09:00 | 2014-09-19 11:00 | N | N | remove mobile from 805L | Line |  |  | Overload, Over/Under Voltage
ENMAX | 1.81L (ENMAX 20 - ENMAX 1),ENMAX 20 B138-1.81 (ENMAX 20) | 2014-09-19 16:00 | 2014-10-02 16:00 | N | N | SF6 leak repair with assistance from HVB rep | Circuit Breaker, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 908L (89s Ellerslie - 908AL tap),908L (38s East Edmonton - 908AL tap) | 2014-09-19 16:00 | 2014-09-19 17:00 | N | Y | momentary outage to isolate Tx#2 @ East Industrial | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 908L (89s Ellerslie - 908AL tap),908L (38s East Edmonton - 908AL tap) | 2014-09-19 17:00 | 2014-09-19 17:10 | N | Y | opening EDS2 breaker at 52s | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2014-09-20 03:00 | 2014-09-20 05:00 | N | N | high load | Line |  |  | Pre-Condition
EPCOR | At-Plastics-4Rs, At-Plastics-5Rs,738AL (A. T. Plastics 4R - A. T. Plastics 5R - 738AL1) | 2014-09-20 07:00 | 2014-09-21 17:00 | N | N | outage for AltaLink work on the 738L and Doble/SFRA of Tx and equipment, relay maintenance and breaker maintenance | Station, Line |  |  | Firm Load Loss, For Information Only
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2014-09-20 08:00 | 2014-09-21 17:00 | N | N | line washing | Line |  |  | Pre-Condition, Overload, Creates Radial Feeds
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24),24PT138-Z32 | 2014-09-20 08:00 | 2014-09-20 10:00 | N | N | substation washing | Line, Transformer, Terminal Equipment |  |  | For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona) | 2014-09-20 08:00 | 2014-09-21 18:00 | N | N | line raise over Whitemud Dr. | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 738L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2014-09-20 08:00 | 2014-09-21 17:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-136 (162s Beddington) | 2014-09-20 08:00 | 2014-09-21 16:00 | N | Y | maintenance, SF6 Sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 38s T2 (38s East Edmonton),38s T4 (38s East Edmonton),738L (38s East Edmonton - 95s Imperial Oil Edmonton),780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona),822L (133s Stelco Edmonton - 38s East Edmonton) | 2014-09-20 08:00 | 2014-09-20 17:00 | N | Y | Rewire 38s8 PT for new ground alarm modules | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),1.81L (ENMAX 20 - ENMAX 1) | 2014-09-20 08:00 | 2014-09-20 10:00 | N | N | pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (28s West Brooks - 763L257A),763L (158s Vauxhall - 763L259) | 2014-09-20 10:00 | 2014-09-20 13:00 | N | N | repair 763L257A and maintenance on 763L259, 763AL1 & 763AL. | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ENMAX | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24),24PT138-Z31 | 2014-09-20 10:00 | 2014-09-20 12:00 | N | Y | substation washing | Line, Transformer, Terminal Equipment |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 26.1TR (ENMAX 26),26.81L (ENMAX 54 - ENMAX 26),26B138-26.81 (ENMAX 26),26PT138-Z31 | 2014-09-20 12:00 | 2014-09-20 14:00 | N | N | substation washing | Circuit Breaker, Line, Transformer, Terminal Equipment |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26),26B138-26.83 (ENMAX 26) | 2014-09-20 14:00 | 2014-09-20 16:00 | N | N | substation washing | Circuit Breaker, Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 708AL (388s Riverside - 708L tap),388s 1 (388s Riverside) | 2014-09-21 06:00 | 2014-09-21 18:00 | N | Y | customer maintenance | Switch, Line
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),47.2 TR (ENMAX 47) | 2014-09-21 08:00 | 2014-09-21 14:00 | N | N | Substation Washing | Transformer, Line |  |  | For Information Only
ATCO | 721S La Corey | 2014-09-21 08:00 | 2014-09-21 12:00 | N | N | To maintain LOA from the 25kv while removing the mobile substation | Station |  | To maintain LOA from the 25kv while removing the mobile substation
ATCO | 7L89 (721s La Corey - 700s Bonnyville) | 2014-09-21 08:00 | 2014-09-21 16:00 | N | N | After 144kv bus GOI at 721S is returned, Transfer load back to 701T at 721S and remove 835S mobile | Line |  | After 144kv bus GOI at 721S is returned, Transfer load back to 701T at 721S and remove 835S mobile | Pre-Condition
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2014-09-21 08:00 | 2014-09-21 16:00 | N | N | Doble PT's | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 876s 901 (876s Brintnell) | 2014-09-21 08:00 | 2014-09-21 18:00 | N | Y | testing | Circuit Breaker |  | 876S BRINTNELL BKR 901 O/S FOR TESTING THIS PERMIT HAS BEEN RE-SCHEDULED | 240 kV
ENMAX | 162.1TR (ENMAX 162 Beddington),162s 240-RB131 (162s Beddington),162s 240-RB134 (162s Beddington),162s 138-RB80 (162s Beddington),162s 138-RB85 (162s Beddington),162s Beddington 240 kV North Bus,162s Beddington 138 kV North Bus | 2014-09-21 14:00 | 2014-09-21 16:00 | N | Y | Substation Washing | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 162.2TR (ENMAX 162 Beddington),162s 240-133 (162s Beddington),162s 240-136 (162s Beddington),162s 138-RB83 (162s Beddington),162s 138-RB84 (162s Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2014-09-21 16:00 | 2014-09-21 18:00 | N | Y | Substation Washing | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D131 (ENMAX 25) | 2014-09-22 08:00 | 2014-09-24 16:00 | N | Y | First year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-09-22 08:00 | 2014-09-22 13:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 118s C1 (118s Canmore),118s T1 (118s Canmore),54L (118s Canmore - 54L172),118s Canmore 138 kV Bus 1 | 2014-09-22 08:00 | 2014-09-22 17:00 | N | N | Removal of bus protections & short CTs | Shunts, Transformer, Line, Bus |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.80L (ENMAX 2 - ENMAX 23),ENMAX 23 RTU/SCADA,23PT138-Z31 (ENMAX 23) | 2014-09-22 08:00 | 2014-10-01 16:00 | N | N | AIS - GIS Swap. ECTP 2s, 23s | Line, Terminal Equipment, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 56L (245s Seebe - 20s Ghost),245s 56E (245s Seebe) | 2014-09-22 08:00 | 2014-09-25 17:00 | N | N | Replace 56L A&B line protections | Line, Circuit Breaker |  |  | Overload
EPCOR | 557s T1 (557s Castle Downs) | 2014-09-22 08:00 | 2014-09-27 17:00 | N | Y | Cutover new BF protection panel | Transformer |  |  | 240 kV
ALTALINK | 172L (370s North Lethbridge - 172L1238) | 2014-09-22 08:00 | 2014-10-29 14:00 | N | N | rebuild str# 1196-1201A (river crossing) | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 149s T3 (149s Nisku) | 2014-09-22 08:00 | 2014-09-25 17:00 | N | N | Bird Cover-Up & LA's | Transformer
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2014-09-22 08:00 | 2014-09-26 16:00 | N | Y | Installation of receiving structure | Circuit Breaker |  |  | 240 kV
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2014-09-22 08:30 | 2014-09-25 17:00 | N | N | 7L45 install viration dampers | Line |  | 7L45 install viration dampers A portion of 7L45 will be removed from service for inspection and install conductor damper between 7L45D2 and 813S LITTLE SMOKEY GOI WILL BE ISSUED 8:30-17:00 DAILY BUT RELEASED EACH EVENING. LINE WILL REMAIN DE-ENERGIZED UNLESS NEEDED. ALSO SEE HOP FOR 7L46 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L91 (Selkirk - Ashton Creek) | 2014-09-22 09:00 | 2014-09-26 17:00 | N | Y | replace spacer dampers & install arcing horn - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC
ALTALINK | 233s T1 (233s Beamer),807L (410s Josephburg - 807L tap),233s Beamer 138 kV Bus 1 | 2014-09-22 09:00 | 2014-09-26 17:00 | N | N | Protection Upgrade & Transformer Maintenance | Bus, Transformer, Line |  |  | Overload
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2014-09-22 10:00 | 2014-09-25 15:00 | N | N | Replace Poles on 6L12 | Line |  | Replace Poles on 6L12
ALTALINK | 378s 552 (378s Shell Caroline) | 2014-09-22 12:00 | 2014-09-22 17:00 | N | N | Replace roll pin and test switch on 378s9 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 68s T2 (68s Willesden Green) | 2014-09-22 12:00 | 2014-10-03 17:00 | N | Y | Oil Reclaim | Transformer |  |  | 240 kV, For Information Only
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-09-22 13:00 | 2014-09-22 18:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 723L (69s North Barrhead - 723L133),69s 723E (69s North Barrhead) | 2014-09-22 15:00 | 2014-09-23 17:00 | N | Y | forced outage due to CT failure | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225L (385s Spring Coulee - 225s Magrath) | 2014-09-23 07:00 | 2014-09-23 12:00 | N | N | connect 471s & MR1 Mobile | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (28s West Brooks - 763L257A),28s 31 (28s West Brooks) | 2014-09-23 07:00 | 2014-09-29 17:00 | N | N | replace 28s31 with new SF6 dead tank breaker and add line LAs | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s T1 (305s Acheson) | 2014-09-23 08:00 | 2014-09-23 17:00 | N | N | 394L Line LA failure | Transformer |  |  | For Information Only
ALTALINK | 513S Range. Pipe Lundbreck | 2014-09-23 08:00 | 2014-09-25 17:00 | N | N | substation maintenance upgrades | Station |  |  | For Information Only
ALTALINK | 650s SVC (650s Hansman Lake) | 2014-09-23 08:00 | 2014-09-25 17:00 | N | Y | SVC yearly inspection | Shunts |  |  | 240 kV, For Information Only
EPCOR | Victoria V726 (Victoria) | 2014-09-23 08:00 | 2014-09-23 18:00 | N | N | SF6 breaker maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 24.82L (ENMAX 65 - ENMAX 24) | 2014-09-23 08:00 | 2014-09-23 16:00 | N | N | doble work | Line |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2014-09-23 08:00 | 2014-09-23 12:00 | N | N | Substation Washing | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (305s Acheson - 434s Stony Plain) | 2014-09-23 08:00 | 2014-09-23 18:00 | N | N | insulator washing with helicopter and ground crew | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 118S Canmore,754L (118s Canmore - 437s Baymag) | 2014-09-23 08:00 | 2014-10-02 12:00 | N | N | replace bus and 754L protections | Station, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s T1 (275s Jenner) | 2014-09-23 08:00 | 2014-09-25 16:00 | N | Y | SCADA equipment upgrade project | Transformer |  |  | 240 kV, For Information Only
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River),A793s 701 (A793s West Peace) | 2014-09-23 08:00 | 2014-09-23 16:00 | N | N | breaker testing | Line, Circuit Breaker |  | 793S 701 BREAKER SF6 HPL PARTIAL TESTING 7L51 WILL BE OPEN ENDED AT 793S | Firm Load Loss, Creates Radial Feeds
ATCO | 7L146 (970s Bourque - 700s Bonnyville) | 2014-09-23 08:00 | 2014-09-24 17:00 | N | N | perform 700BS2 - 704A conductor upgrade | Line |  | 7L146 is required to be out of service in order for Hotline crew to perform 700BS2 - 704A conductor upgrade from 266acsr to 795acsr. Once risers are disconnected from upper 700BS2 to 704A this will create J1 which is required for hotline crew to perform their cross arm change and buss upgrade. | For Information Only
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2014-09-23 08:00 | 2014-09-23 13:00 | N | N | heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 794s 701T (794s Valleyview) | 2014-09-23 09:00 | 2014-09-24 16:00 | N | N | transformer oil leak repair | Transformer |  | 794S VALLEYVIEW 701T WILL BE REMOVED FROM SERVICE TO REPAIR OIL LEAK | For Information Only
ALTALINK | 216s T2 (216s Knightsbridge) | 2014-09-23 10:00 | 2014-09-23 18:00 | N | N | install new protections between T2 & T3 | Transformer |  |  | For Information Only
ATCO | 879s 352 (879s Scotford Upgrader) | 2014-09-23 10:00 | 2014-09-24 16:00 | N | N | breaker testing | Circuit Breaker |  | 879S - 352 BREAKER SF6 GL212 COMPLETE TESTING Breaker 352 will be out of service for the duration of work | For Information Only
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13),ENMAX 27 69kV Bus | 2014-09-23 12:00 | 2014-09-23 16:00 | N | N | Substation Washing | Transformer, Line, Bus |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2014-09-23 13:00 | 2014-09-23 18:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 385S Spring Coulee,225L (229s Glenwood - 385s Spring Coulee) | 2014-09-23 14:00 | 2014-10-16 15:00 | N | N | install new T3 bay | Station, Line |  |  | Over/Under Voltage, Creates Radial Feeds
WINDPOWER | 205S Castle Rock Ridge | 2014-09-24 08:00 | 2014-09-26 17:00 | N | Y | annual sub maintenance | Station |  |  | Restricts Generation, For Information Only
ENMAX | ENMAX 25 B240-D134 (ENMAX 25) | 2014-09-24 08:00 | 2014-09-26 16:00 | N | Y | First year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV
ALTALINK | 99s T2 (99s North St. Albert),712L (99s North St. Albert - 305s Acheson) | 2014-09-24 08:00 | 2014-09-24 17:00 | N | N | 138kV switch maintenance (99s20, 99s21) | Transformer, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 30.1TR (ENMAX 30),6.80L (ENMAX 30 - ENMAX 6) | 2014-09-24 08:00 | 2014-09-24 10:00 | N | N | Substation Washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 798L (364s Whitecourt Industrial - 77s Sagitawah) | 2014-09-24 08:00 | 2014-09-24 18:00 | N | N | insulator washing with helicopter and ground crew | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2014-09-24 08:00 | 2014-10-12 18:00 | N | N | rebuild portion 164L: structure replacement and re-conductor. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s 4 (33s Spray) | 2014-09-24 09:00 | 2014-09-24 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 30.2TR (ENMAX 30),30.81L (42s Sarcee - ENMAX 30) | 2014-09-24 10:00 | 2014-09-24 12:00 | N | Y | Substation Washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36B138-36BT3 (ENMAX 36) | 2014-09-24 13:00 | 2014-09-24 18:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker |  |  | For Information Only
ATCO | 743s 702T (743s Sarah Lake) | 2014-09-24 14:30 | 2014-09-26 12:30 | N | N | to repair oil leak | Transformer |  | 743S SARAH LAKE 702T WILL BE REMOVED FROM SERVICE TO REPAIR OIL LEAK | For Information Only
EPCOR | 330P 12TC2 (330p Genesee),330p 1203 (330p Genesee),330p 1206 (330p Genesee),330p 1209 (330p Genesee),330p Genesee 500kV Bus 2 | 2014-09-25 07:00 | 2014-09-25 18:00 | N | Y | Doble of CVT's | Bus, Circuit Breaker, Transformer |  |  | 500 kV
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.1TR (ENMAX 14),ENMAX 14 138kV Bus 1,14PT138-Z5 (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2014-09-25 07:30 | 2014-09-25 12:00 | N | N | Substation Washing | Bus, Not In Model, Line, Transformer, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 787L (71s Lamoureux - 787L29),71s 452 (71s Lamoureux),71s 352 (71s Lamoureux),71s787X (71s Lamoureux) | 2014-09-25 08:00 | 2014-09-25 17:00 | N | N | 138kV Switch Adjustment | Line, Switch, Circuit Breaker
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2014-09-25 08:00 | 2014-09-25 17:00 | N | N | Line Washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 191S N.W.Cardiff | 2014-09-25 08:00 | 2014-09-25 17:00 | N | N | Repair 25kV 191s9 switch hot spot | Station
ALTALINK | 316s T1 (316s West Crossfield) | 2014-09-25 08:00 | 2014-09-25 17:00 | N | N | Doble | Transformer
ATCO | 959S SVC (959s Lanfine) | 2014-09-25 08:00 | 2015-01-20 16:00 | N | Y | In service date: Jan 19, 2015. Refer to the Op Plan binder for the commissioning plan. | Shunts
ALTALINK | 739L (434s Stony Plain - 739L216A),434s 739W (434s Stony Plain),434s Stony Plain 138kV Bus 1 | 2014-09-25 08:00 | 2014-09-27 17:00 | N | N | CT Replacement, CT contributions for new bus protections (T1 & 434s739W) / Trip Test 434s739W | Circuit Breaker, Bus, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2014-09-25 08:00 | 2014-09-25 18:00 | N | N | Insulator washing with helicopter and ground crew. | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2014-09-25 08:00 | 2014-09-25 12:00 | N | N | High load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 171s T1 (171s Redwater) | 2014-09-25 09:01 | 2014-10-09 09:00 | N | N | Install new 25kV breaker, 25kV feeder metering upgrade, replace SS Tx | Transformer
REDDEER | 247s T1 (247s Piper Creek) | 2014-09-25 12:00 | 2014-09-25 14:00 | N | N | emergency repair/replace module | Transformer
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36),14PT138-Z5 (ENMAX 14),ENMAX 14 138kV Bus 2 | 2014-09-25 12:01 | 2014-09-25 16:00 | N | N | Substation Washing | Not In Model, Bus, Line, Transformer, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 330P 12TC1 (330p Genesee) | 2014-09-26 07:00 | 2014-09-26 18:00 | N | Y | Tapchanger maintenance & Hydran replacement | Transformer |  |  | 500 kV
EPCOR | 330p 1201 (330p Genesee),330p 1204 (330p Genesee),330p 1207 (330p Genesee),330P Genesee 500 kV Bus 1 | 2014-09-26 07:00 | 2014-09-26 18:00 | N | Y | Doble of CVT's . repair of 1204 OLM | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
Syncrude | Mildred_135 (Syncrude Mildred Lake) | 2014-09-26 08:00 | 2014-10-05 18:00 | N | N | Breaker 435 - 72kV Upgrade | Circuit Breaker
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2014-09-26 08:00 | 2014-09-26 18:00 | N | N | insulator washing with helicopter and ground crew | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 5L87 (Kelly Lake - Nicola) | 2014-09-27 07:00 | 2014-09-29 21:00 | N | Y | BCH maintenance: does not impact Alberta ATC | Line |  |  | Limits ATC
EPCOR | 72RG1 (Rossdale - Garneau),72RV2 (Rossdale - 511s Victoria),Rossdale 72 kV Bus 3 | 2014-09-27 07:00 | 2014-09-27 18:00 | N | N | doble of PT's & SA's & repair of BD2W disconnect | Bus, Line
ALTALINK | 293S Bernese | 2014-09-27 08:00 | 2014-10-03 16:00 | N | N | In service date: Oct. 1, 2014 | Station
ENMAX | ENMAX 2,ENMAX 2 B138-D86 (ENMAX 2),2B138-D89 (ENMAX 2),2B138-D93 (ENMAX 2) | 2014-09-27 08:00 | 2014-09-27 16:00 | N | N | route current of 2.82L through sections ( 2A, 4A, 4B, 4C & 4D ) to check load on all differential elements | Station, Circuit Breaker
ALTALINK | 739L (434s Stony Plain - 739L216A) | 2014-09-27 08:00 | 2014-09-27 18:00 | N | N | Insulator washing with helicopter and ground crew | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 727L (65s High River - 727L39S),727L (678s Okotoks - 727L39N) | 2014-09-27 17:00 | 2014-09-27 19:00 | N | N | to close open point @ 65s 894L1 junction for 65s | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s Beddington,11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2014-09-27 22:00 | 2014-09-28 03:00 | N | N | substation washing, off peak wash | Station, Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale C1 | 2014-09-28 07:00 | 2014-09-28 18:00 | N | N | For work on Bus #2 @ Rossdale | Shunts |  |  | For Information Only
EPCOR | Rossdale 72 kV Bus 2 | 2014-09-28 07:00 | 2014-09-28 18:00 | N | N | Doble of PT's & SA's & Repair of BD2E disconnect | Bus |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2014-09-28 07:00 | 2014-09-28 18:00 | N | N | For work on Bus #2 @ Rossdale | Line |  |  | For Information Only
ALTALINK | 900L (63s Red Deer - 17s Benalto) | 2014-09-28 07:00 | 2014-10-07 19:00 | N | Y | 1325L stringing over 900L - WATL | Line |  |  | Limits ATC
EPCOR | 72RG7 (Rossdale - Garneau) | 2014-09-28 07:00 | 2014-09-28 18:00 | N | N | Doble Testing on Rossdale end | Line |  |  | For Information Only
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2014-09-28 07:00 | 2014-09-28 18:00 | N | N | For work on Bus #2 @ Rossdale | Line |  |  | For Information Only
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake) | 2014-09-28 07:30 | 2014-10-07 18:00 | N | N | String 1325L over 637L - WATL | Line |  |  | Pre-Condition
ENMAX | 8.4TR (ENMAX 8) | 2014-09-28 08:00 | 2014-11-10 16:00 | N | N | doble, transformer wash, facilities equipment inspection | Transformer |  |  | For Information Only
ALTALINK | 65s T3 (65s High River) | 2014-09-28 08:00 | 2014-09-28 17:00 | N | N | FATD:Foothills 138kV Projects: Add CT contribution to new 138 KV bus protection. | Transformer |  |  | For Information Only
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38),38PT138-Z5 (ENMAX 38) | 2014-09-28 08:00 | 2014-09-28 12:00 | N | Y | Substation Washing | Terminal Equipment, Line, Transformer, Shunts |  |  | Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 15s T1 (15s Fort Macleod) | 2014-09-28 09:00 | 2014-09-28 12:00 | N | N | switch 15s30A hotspot repair | Transformer |  |  | For Information Only
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37),38PT138-Z5 (ENMAX 38) | 2014-09-28 12:01 | 2014-09-28 16:00 | N | Y | substation washing | Terminal Equipment, Line, Transformer, Shunts |  |  | Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-09-29 06:00 | 2014-09-29 18:00 | N | N | heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2014-09-29 07:00 | 2014-10-01 17:00 | N | N | overhead line to replace underground cable. doble & Gas Sample 21B69-21.61, Inspection 34B69-21.61 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 291s T1 (291s Cochrane) | 2014-09-29 07:00 | 2014-10-02 17:00 | N | N | switch/arrestor replacement & bird coverup | Transformer
EPCOR | Meadowlark T3 (Meadowlark) | 2014-09-29 07:00 | 2014-10-19 18:00 | N | N | repair of leaking tapchanger gasket | Transformer
EPCOR | 72NW15 (Namao - Woodcroft) | 2014-09-29 07:00 | 2014-10-03 18:00 | N | N | line maintenance | Line
ALTALINK | 40s T2 (40s Wetaskiwin) | 2014-09-29 07:30 | 2014-09-29 17:00 | N | N | implementation of new 138kV Bus Differential & Replace T2 Arrestors | Transformer
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-09-29 08:00 | 2014-09-29 13:00 | N | N | heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D142 (ENMAX 25) | 2014-09-29 08:00 | 2014-10-01 16:00 | N | Y | First year check/Maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.81L (44s Bearspaw - ENMAX 36) | 2014-09-29 08:00 | 2014-10-02 10:00 | N | Y | 36.1TR HV Bushing Replacement | Transformer, Line
ALTALINK, EPCOR | 330p 1205 (330p Genesee),330p 1206 (330p Genesee),1239L (510s Sunnybrook - 330p Genesee) | 2014-09-29 08:00 | 2014-10-01 17:00 | N | Y | To perform End to End Test for New 1239L protection to Sunnybrook | Line, Circuit Breaker |  |  | For Information Only, 500 kV
EPCOR | 330p 1207 (330p Genesee) | 2014-09-29 08:00 | 2014-09-29 18:00 | N | Y | 1207CVT Doble of CVT | Circuit Breaker |  |  | For Information Only, 500 kV
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2014-09-29 08:00 | 2014-11-22 17:30 | N | Y | line rebuild strs #189 to #243 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B240-D131 (ENMAX 65),ENMAX 65 B240-D134 (ENMAX 65),65.1 TR (ENMAX 65),ENMAX 65 240kV South Bus | 2014-09-29 08:00 | 2014-09-29 16:00 | N | Y | FATD | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 30PL2-1 (30EDD-1 - 30EDD-2) | 2014-09-29 09:00 | 2014-10-01 20:00 | N | N | 5yr PM on 30PL2-1 and associated equipment including breaker, VT's, reactor, cable, protection and metering. | Line
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2014-09-29 09:00 | 2014-10-03 15:00 | N | N | Line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2014-09-29 09:30 | 2014-09-29 16:00 | N | N | Check N.O. 6L12D3 is closed. 773S Coronation Will be radially fed from 774S Monitor Reason: Replace Pole on 6L12 | Line |  | Check N.O. 6L12D3 is closed. 773S Coronation Will be radially fed from 774S Monitor Reason: Replace Pole on 6L12 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2014-09-29 11:00 | 2014-09-29 17:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 276s 652 (276s Un Carb Prentiss),276s C1 (276s Prentiss) | 2014-09-29 12:00 | 2014-09-29 17:00 | N | N | Tank heater replacement,Tank heater replacement. | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome),320p212 (320p Keephills) | 2014-09-29 13:00 | 2014-09-29 17:00 | N | Y | Hot Switch Repair | Line, Switch |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 835L (384s Keystone - 835L tap),384s 835X (384s Keystone) | 2014-09-29 13:00 | 2014-09-29 17:00 | N | N | Repair 384s13 Hot Spot | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 729L (40s Wetaskiwin - 729L13A) | 2014-09-30 07:30 | 2014-09-30 12:00 | N | N | Implementation of new 138kV Bus Differential | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 252s T1 (252s Jarrow) | 2014-09-30 08:00 | 2014-09-30 17:00 | N | N | 252s61 Tank Heater | Transformer |  |  | For Information Only
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2014-09-30 08:00 | 2014-09-30 13:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker |  |  | For Information Only
ALTALINK | 38s C2 (38s East Edmonton) | 2014-09-30 08:00 | 2014-09-30 17:00 | N | N | Breaker Maintenance | Shunts |  |  | For Information Only
ALTALINK | 310p 352 (310p Sundance) | 2014-09-30 08:00 | 2014-09-30 17:00 | N | Y | Oil Leak Repair | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 151s T2 (151s Strathmore),733L (151s Strathmore - 428S Namaka) | 2014-09-30 08:00 | 2014-09-30 17:00 | N | N | 138kV switch repair | Transformer, Line |  |  | Creates Radial Feeds
ALTALINK | 861L (71s Lamoureux - 258s Dow Hydro Carbons) | 2014-09-30 08:00 | 2014-09-30 17:00 | N | Y | 138kV Switch Adjustment | Line |  |  | Pre-Condition
ALTALINK | 164L (103s Goose Lake - 415s Drywood),415s 21 (415s Drywood) | 2014-09-30 08:00 | 2014-09-30 17:00 | N | N | 69kV Breaker Maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2014-09-30 08:00 | 2014-09-30 12:00 | N | N | Substation Washing | Transformer, Line |  |  | Creates Radial Feeds
BCH | 5L79 (Ashton Creek - Nicola) | 2014-09-30 09:00 | 2014-10-12 17:00 | N | N | replacing space damper and CVT | Line |  |  | For Information Only
ALTALINK | 62s T3 (62s Brazeau) | 2014-09-30 10:00 | 2014-10-01 17:00 | N | Y | Transformer & Breaker Maintenance | Transformer |  |  | 240 kV
ATCO | 7L224 (774s Monitor - 650s Hansman Lake) | 2014-09-30 10:00 | 2014-09-30 15:00 | N | Y | REMOVE JUMPER J2 | Line |  | REMOVE JUMPER J2 CREATE JUMPER J1 FOR SWITCH 702A MAINTENANCE SEQUENCE 1.OPEN END 7L224 AT 774S (2-29013) 2.HOP TO CREATE J1 BETWEEN UPPER AND LOWER BUS 3.COMPLETE SWITCHING AND ISSUE GOI BETWEEN 7L224D1 AND 7L98D4 (CLOSE J2) 4..HOP TO RECONECT RISERS BETWEEN UPPER AND LOWER BUS 5. CLOSE 7L224 LINE AT 774S | Pre-Condition, Creates Radial Feeds
ENMAX | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2014-09-30 12:00 | 2014-09-30 16:00 | N | Y | Substation Washing | Transformer, Line |  |  | Creates Radial Feeds
ALTALINK | 858L (149s Nisku - 40s Wetaskiwin) | 2014-09-30 12:01 | 2014-09-30 17:00 | N | N | Implementation of new 138kV Bus Differential | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2014-09-30 13:01 | 2014-09-30 18:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker |  |  | Pre-Condition
ATCO | 729s 703T (729s Otauwau) | 2014-09-30 13:30 | 2014-10-02 14:30 | N | N | 729S 703T O/S FOR MTCE | Transformer |  | 729S 703T O/S FOR MTCE | For Information Only
ALTALINK | 956L (103s Goose Lake - 59s Peigan) | 2014-10-01 07:00 | 2014-10-05 17:00 | N | N | replacing stepbolts | Line |  |  | 240 kV
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin),40s 804W (40s Wetaskiwin) | 2014-10-01 07:30 | 2014-10-01 12:00 | N | N | implementation of new 138kV Bus Differential | Circuit Breaker, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8),3B138-3.82 | 2014-10-01 08:00 | 2014-10-01 13:00 | N | N | Heater repair with assistance from manufacturer | Line, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36B138-36BT3 (ENMAX 36) | 2014-10-01 08:00 | 2014-10-01 18:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker
ENMAX | 23.4TR (ENMAX 23),MD138_23_4TR (ENMAX 23) | 2014-10-01 08:00 | 2014-11-21 16:00 | N | N | transformer replacement | Switch, Transformer |  |  | For Information Only
ALTALINK | 123s T1 (123s Banff) | 2014-10-01 08:00 | 2014-10-01 17:00 | N | N | maintenance/Doble | Transformer |  |  | For Information Only
ALTALINK | 618s T1 (618s Riverbend) | 2014-10-01 08:00 | 2014-10-01 17:00 | N | N | Doble/SFRA | Transformer |  |  | For Information Only
ENMAX | ENMAX 25 B240-D136 (ENMAX 25) | 2014-10-01 08:00 | 2014-10-03 16:00 | N | Y | First year check/maintenance (first 2 days), Doble (3rd day), SF6 Sample, Install new position indicator | Circuit Breaker |  |  | 240 kV
ENMAX | 1.5TR (ENMAX 1) | 2014-10-01 08:00 | 2014-10-01 10:00 | N | N | Substation washing | Transformer |  |  | For Information Only
EPCOR | Namao N725 (Namao) | 2014-10-01 08:00 | 2014-10-01 18:00 | N | N | Breaker Fail Op-Checks 72NW15, 72 VN21 & 72KN23 | Circuit Breaker |  |  | For Information Only
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2014-10-01 08:00 | 2014-10-02 18:00 | N | N | insulator washing with helicopter and ground crew | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 71s C1 (71s Lamoureux),71s 1052 (71s Lamoureux) | 2014-10-01 08:00 | 2014-10-01 17:00 | N | N | Breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 310P 69 (310p Sundance),310p T30 (310p Sundance) | 2014-10-01 08:00 | 2014-10-01 17:00 | N | Y | 310p69 Breaker Maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 837s 701T (837s Mahihkan) | 2014-10-01 09:00 | 2014-10-03 16:30 | N | N | maintenance | Transformer |  | 837S MAHIHKAN 701T O/S FOR TC MTCE | For Information Only
ATCO | 808s 701T (808s Procter & Gamble) | 2014-10-01 09:00 | 2014-10-03 17:00 | N | N | replace tap changer. | Transformer |  | 808S 701T TRANSFORMER CLASS2 TAP CHANGER
EPCOR | 330P Genesee RTU/SCADA | 2014-10-01 10:00 | 2014-10-01 12:00 | N | N | RTU validations | Terminal Equipment |  |  | Affects Visibility
ENMAX | 1.6TR (ENMAX 1) | 2014-10-01 10:00 | 2014-10-01 12:00 | N | N | Substation washing | Transformer |  |  | For Information Only
ATCO | 7L85 (804s Wintering Hills - 803s Bullpound),7L85 (803s Bullpound - 801s Anderson) | 2014-10-01 10:30 | 2014-10-02 14:00 | N | N | repair various deficiencies found on helicopter patrols. | Line |  | Repair various deficiencies found on helicopter patrols. No N-1 or N-2 Concerns with this outage | Creates Radial Feeds
ALTALINK | 716L (40s Wetaskiwin - 331s Ponoka),40s 81 (40s Wetaskiwin) | 2014-10-01 12:01 | 2014-10-01 17:00 | N | N | implementation of new 138kV Bus Differential | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.8TR (ENMAX 1) | 2014-10-01 14:00 | 2014-10-01 16:00 | N | N | Substation washing | Transformer |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2014-10-01 23:00 | 2014-10-02 06:30 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2014-10-01 23:00 | 2014-10-02 06:30 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 40s T1 (40s Wetaskiwin) | 2014-10-02 07:30 | 2014-10-02 17:00 | N | N | Implementation of new 138kV Bus differential | Transformer
ENMAX | 26.81L (ENMAX 54 - ENMAX 26),54B138-26.81 (ENMAX 54) | 2014-10-02 08:00 | 2014-10-02 13:00 | N | N | Heater repair with assistance from manufacturer | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 391s T1 (391s Balzac) | 2014-10-02 08:00 | 2014-10-02 12:30 | N | N | Remove Tx protections | Transformer |  |  | For Information Only
ALTALINK | 123s T2 (123s Banff) | 2014-10-02 08:00 | 2014-10-02 17:00 | N | N | Maintenance/Doble | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 527S Coal Valley | 2014-10-02 08:00 | 2014-10-02 18:00 | N | N | Substation Maintenance and SCADA Visibility | Station |  |  | Affects Visibility
ALTALINK | 19s T8 (19s Wabamun) | 2014-10-02 09:00 | 2014-10-02 17:00 | N | N | Transformer Oil Sample | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7),7PT138-Z31 (ENMAX 7),ENMAX 7 138 kV Bus | 2014-10-02 10:01 | 2014-10-02 12:00 | N | N | Substation Washing | Transformer, Line, Terminal Equipment, Bus |  |  | Pre-Condition, Overload
ALTALINK | 80L (198s Blackfalds - 217s North Red Deer) | 2014-10-02 12:00 | 2014-10-02 13:00 | N | N | RATD - connect 474s mobile at 217s | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 118s C1 (118s Canmore),54L (118s Canmore - 54L172),118s Canmore 138 kV Bus 1 | 2014-10-02 12:01 | 2014-10-03 17:00 | N | N | Install new bus protection | Shunts, Line, Bus |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7),7PT138-Z31 (ENMAX 7),ENMAX 7 138 kV Bus | 2014-10-02 12:01 | 2014-10-02 16:00 | N | N | Substation Washing | Transformer, Line, Terminal Equipment, Bus |  |  | Pre-Condition, Overload
ALTALINK | 391s T2 (391s Balzac) | 2014-10-02 12:31 | 2014-10-02 17:00 | N | N | Remove Tx protections | Transformer |  |  | For Information Only
ALTALINK | 812L (65s High River - 812L tap),65s 812W (65s High River) | 2014-10-02 13:00 | 2014-10-02 16:00 | N | N | Add CT contribution to New 138 KV bus protection and perform trip testing to breaker from New 138 KV bus,Add CT contribution to New 138 KV bus protection and perform trip testing to breaker from New 138 KV bus Protection | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 | 2014-10-02 13:00 | 2014-10-02 18:00 | N | N | Heater repair with assistance from manufacturer | Line, Terminal Equipment |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 217s C1 (217s North Red Deer),768L (217s North Red Deer - 87s Gaetz),80L (194s South Red Deer - 217s North Red Deer) | 2014-10-02 14:00 | 2014-10-07 10:00 | N | N | RATD - Install V drops on bus & Bus diff replacement | Shunts, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2014-10-03 08:00 | 2014-10-04 18:00 | N | N | Insulator washing with helicopter and ground crew | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32B138-32BT5 (ENMAX 32) | 2014-10-03 08:00 | 2014-10-03 16:00 | N | N | heater repair with assistance from manufacturer | Circuit Breaker
ALTALINK | 611L (391S Balzac - 186s Dry Creek),391s 611 (391s Balzac) | 2014-10-03 08:00 | 2014-10-03 11:00 | N | N | remove protections | Line, Circuit Breaker
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s 25 (391s Balzac) | 2014-10-03 08:00 | 2014-10-05 16:00 | N | Y | switch 23 maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Restricts Generation
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s 25 (391s Balzac) | 2014-10-03 11:01 | 2014-10-03 14:00 | N | Y | remove protections | Circuit Breaker, Line |  |  | For Information Only
ENMAX, ALTALINK | 162.81L (ENMAX 162 Beddington - 391S Balzac),391s 162_81 (391s Balzac) | 2014-10-03 14:01 | 2014-10-03 17:00 | N | Y | remove protections | Line, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 99s T1 (99s North St. Albert),747L (99s North St. Albert - 747DL4) | 2014-10-03 16:00 | 2014-10-05 17:00 | N | Y | replace 99s6 PT1 | Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 227S Cutting Lake | 2014-10-04 08:00 | 2014-10-05 17:00 | N | N | T1 bushing replacement, remove bird nest, leaks | Station |  | VR1 doble/maintenance. 227s2125 breaker maintenance
EPCOR | Meadowlark T2 (Meadowlark) | 2014-10-04 08:00 | 2014-10-04 18:00 | N | N | doble CVT on bus & Replace oil plugs in the bushings | Transformer
SUNCOR | Suncor (Millennium) Islanding RAS (IRAS) | 2014-10-04 08:00 | 2014-10-08 16:00 | N | N | RAS modifications | RAS |  |  | Impacts RAS
ENMAX, ALTALINK | 2.4TR (ENMAX 2),5s T1 (East Calgary) | 2014-10-04 10:00 | 2014-10-04 12:00 | N | Y | substation washing, wash off peak | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 5s 61 (5s East Calgary) | 2014-10-04 10:00 | 2014-10-04 12:00 | N | Y | ENMAX: washing 138 kV # 2 sub | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX, ALTALINK | 5s C3 (5s East Calgary),5s C2 (5s East Calgary),2.2TR (ENMAX 2),2.81L (ENMAX 2 - ENMAX 9),833L (ENMAX 2 - ENMAX 12) | 2014-10-04 12:01 | 2014-10-04 16:00 | N | Y | substation washing, wash off peak | Transformer, Line, Shunts |  |  | Pre-Condition, Limits ATC
ENMAX | 2.1TR (ENMAX 2),2.3TR (ENMAX 2),2.83L (ENMAX 13 - 2.83L tap) | 2014-10-04 16:01 | 2014-10-04 20:00 | N | N | substation washing, wash off peak | Transformer, Line |  |  | Pre-Condition
ENMAX | 5.2TR (ENMAX 5),5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2014-10-05 | 2014-10-05 04:00 | N | N | off peak substation washing | Transformer, Line
EPCOR | 805s C1 (805s Jasper) | 2014-10-05 08:00 | 2014-10-05 18:00 | N | Y | doble as required | Shunts |  |  | 240 kV, For Information Only
ATCO | 882s 701T (882s Triangle) | 2014-10-05 08:00 | 2014-10-16 16:00 | N | N | 701T, 701 wiring changes/commissiong new SCADA alarms and controls. 882S load transferred to 835S mobile sub | Transformer |  | 701T, 701 wiring changes/commissiong new SCADA alarms and controls. 882S load transfered to 835S mobile sub. | For Information Only
ALTALINK | 133S Stelco Edmonton,133s T1 (133s Stelco Edmonton),133s T2 (133s Stelco Edmonton) | 2014-10-05 08:00 | 2014-10-10 10:00 | N | N | customer request for grounded advice | Station, Transformer |  |  | For Information Only
CapitalPower | 615S Halkirk | 2014-10-05 08:00 | 2014-11-25 08:00 | N | Y | DSTATCOM trasnfomer | Station |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2014-10-05 08:00 | 2014-10-05 16:00 | N | N | sheath/oil testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 611L (391S Balzac - 186s Dry Creek),391s 611 (391s Balzac) | 2014-10-05 08:00 | 2014-10-05 11:00 | N | N | Wire in new protection modules & trip test breaker | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s97N (535s Joffre),330L2 (535s Joffre - I-330s Nova Corp Plant) | 2014-10-05 11:00 | 2014-10-16 15:00 | N | Y | customer requested outage | Switch, Line |  |  | For Information Only
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s 25 (391s Balzac) | 2014-10-05 11:01 | 2014-10-05 14:00 | N | Y | wire in new protection modules & trip test breaker | Circuit Breaker, Line |  |  | Restricts Generation
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac),162s 138-RB81 (162s Beddington),162s 138-RB80 (162s Beddington) | 2014-10-05 12:00 | 2014-10-05 14:00 | N | Y | substation washing & SCADA function checks | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.1TR (ENMAX 162 Beddington),162s 240-RB131 (162s Beddington),162s 240-RB134 (162s Beddington),162s 138-RB80 (162s Beddington),162s 138-RB85 (162s Beddington),162s 138_RB94 (162s Beddington) | 2014-10-05 14:00 | 2014-10-05 16:00 | N | N | substation washing | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac),391s 162_81 (391s Balzac),162s 138-RB81 (162s Beddington),162s 138-RB80 (162s Beddington) | 2014-10-05 14:01 | 2014-10-05 17:00 | N | Y | wire in new protections & trip test breaker | Circuit Breaker, Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington),162s 240-133 (162s Beddington),162s 240-136 (162s Beddington),162s 138-RB83 (162s Beddington),162s 138-RB84 (162s Beddington),162s 138_RB92 (162s Beddington) | 2014-10-05 17:01 | 2014-10-05 19:00 | N | N | substation washing | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 11.83L (162s Beddington - ENMAX 11),162s 138-RB85 (162s Beddington),162s 138-RB84 (162s Beddington) | 2014-10-06 | 2014-10-06 02:00 | N | N | off peak substation washing and SCADA function checks | Line, Circuit Breaker |  |  | Overload
EPCOR | NamaoT3 (Namao) | 2014-10-06 01:00 | 2014-10-08 01:00 | N | N | complete op-checks for new 15Kv buss retrofit | Transformer |  |  | For Information Only
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2014-10-06 02:00 | 2014-10-06 04:00 | N | N | off peak substation washing and SCADA function checks | Circuit Breaker, Line |  |  | Overload
EPCOR | 330p Genesee 138kV Bus 1 | 2014-10-06 07:00 | 2014-10-06 12:00 | N | N | doble of VT's | Bus
ALTALINK | 901L (63s Red Deer - 901AL tap),901L (74s Janet - 901AL tap) | 2014-10-06 07:30 | 2014-10-16 17:00 | N | Y | replace structures 307 and 309 with steel H frames | Line |  |  | 240 kV, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 391s T1 (391s Balzac) | 2014-10-06 08:00 | 2014-10-06 12:30 | N | N | install new protections & trip test breakers | Transformer
ATCO | 820s 702T (820s Hangingstone),820s 703 (820s Hangingstone) | 2014-10-06 08:00 | 2014-10-09 17:00 | N | N | tie in 701 BF protection into 703 trip/block close ccts | Transformer, Circuit Breaker |  | Tie in 701 BF protection into 703 trip/block close ccts. | For Information Only
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-10-06 08:00 | 2014-10-06 16:00 | N | N | heater repair | Circuit Breaker |  |  | For Information Only
ALTALINK | 320p 3452 (320p Keephills) | 2014-10-06 08:00 | 2014-10-11 08:00 | N | Y | replace breaker control module | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 172s T3 (172s Sherritt Gordon) | 2014-10-06 08:00 | 2014-10-13 17:00 | N | N | replace cables between TX & bus, upgrade metering. | Transformer
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2014-10-06 08:00 | 2014-10-06 18:00 | N | N | insulator washing with helicopter and ground crew | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 825L (484s Millar Western - 77s Sagitawah),77s Sagitawah 138 kV East Bus | 2014-10-06 08:00 | 2014-10-06 20:00 | N | N | SCADA equipment upgrade/TT install/insulator replacement | Bus, Line
ALTALINK | 484s T1 (484s Millar Western) | 2014-10-06 08:00 | 2014-10-07 17:00 | N | N | doble/SFRA/LTC maintenance/Oil leaks/wash | Transformer |  |  | For Information Only
ENMAX | ENMAX 25 B240-D141 (ENMAX 25),ENMAX 25 B240-D140 (ENMAX 25) | 2014-10-06 08:30 | 2014-10-06 09:00 | N | Y | replace PTs | Circuit Breaker |  |  | 240 kV, Restricts Generation
ATCO | 7L129 (918s Bauer - 710s Vermilion) | 2014-10-06 09:00 | 2014-10-06 17:00 | N | Y | to replace poles | Line |  | A PORTION OF 7L129 WILL BE REMOVED FROM SERVICE BX 710S VERMILION & 7L129D2 A PORTION OF 7L129 WILL BE REMOVED FROM SERVICE BX 526S BUFFALO CREEK & 7L129D3 TO REPLACE POLES | Overload, Firm Load Loss, Creates Radial Feeds
BCH | 5L77 (Revelstoke - Ashton Creek) | 2014-10-06 09:00 | 2014-10-10 17:00 | N | N | replacing CVT- BC maintenance does not affect AB ATC | Line |  |  | For Information Only
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap),775s 603 (775s Sullivan Lake) | 2014-10-06 09:00 | 2014-10-13 16:00 | N | N | 67N line protection upgrade | Line, Circuit Breaker |  | 6L03_67N _Line Protection Upgrade. The techs are working on the 67N Line protection but require access to 603 BKR thus the GOI requirement. | Firm Load Loss, Creates Radial Feeds
ATCO | 826s 503R (826s Marguerite Lake),826s 504R (826s Marguerite Lake),826s 902T (826s Marguerite Lake) | 2014-10-06 09:00 | 2014-10-09 16:00 | N | Y | repair leak on transformer | Shunts, Transformer |  | 826S MARGUERITE LAKE 902T O/S TO REPAIR LEAK STATION WILL BE ON ALTERNATE STATION SERVICE FROM 822S WOLF LAKE 5L263 | 240 kV, For Information Only
ALTALINK | 74s 152 (74s Janet) | 2014-10-06 10:00 | 2014-10-08 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 63s 852 (63s Red Deer) | 2014-10-06 10:00 | 2014-10-06 17:00 | N | Y | dashpot repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 37s T6 (37s North Calder) | 2014-10-06 10:00 | 2014-10-09 17:00 | N | Y | replace 138 & 240kV Tx bushings | Transformer |  |  | 240 kV, Overload, Over/Under Voltage
ALTALINK | 391s T2 (391s Balzac) | 2014-10-06 12:31 | 2014-10-06 17:00 | N | N | wire in new protections and trip test breakers | Transformer |  |  | For Information Only
ALTALINK | 37s T5 (37s North Calder) | 2014-10-06 13:00 | 2014-10-09 17:00 | N | N | install tap change filter | Transformer
ALTALINK | 58s T1 (58s Edson) | 2014-10-06 13:00 | 2014-10-07 17:00 | N | N | 58s37 switch repairs | Transformer
ATCO | 735s 602T (735s Swan River) | 2014-10-06 13:00 | 2015-01-20 09:00 | N | N | construction on new 25 kV bays and require equipment clearance near 602TD | Transformer |  | Construction on new 25kv bays and require equipment clearance near 602TD. No added risk to the system. 601T Is for contingency only and is normally open. | For Information Only
EPCOR | 330p Genesee 138kV Bus 2 | 2014-10-07 07:00 | 2014-10-07 18:00 | N | N | doble of VT's | Bus |  |  | For Information Only
ALTALINK, ATCO | 6L126 (515L tap - 743s Sarah Lake),526L (515s Fed Pipe Judy Creek - 526L418) | 2014-10-07 08:00 | 2014-10-07 16:30 | N | N | replace 526L420, switch will not be functional after this outage, will be functional after Oct 10 outage | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 807L (410s Josephburg - 807L tap),410s 652 (410s Josephburg),410s 752 (410s Josephburg),410s24 (410s Josephburg) | 2014-10-07 08:00 | 2014-10-07 17:00 | N | N | 138kV switch adjustment | Line, Switch, Circuit Breaker
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2014-10-07 08:00 | 2014-10-07 16:00 | N | N | heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 678s T2 (678s Okotoks),727L (678s Okotoks - 1140s Temp),678s Okotoks 138kV Bus 2 | 2014-10-07 08:00 | 2014-10-07 17:00 | N | N | 138kV switch repair (678s35) | Transformer, Bus, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27),ENMAX 16 69kV Bus,8KV PT (ENMAX 16),69 kV PT (ENMAX 16) | 2014-10-07 08:00 | 2014-10-07 10:00 | N | N | substation washing | Transformer, Not In Model, Line, Bus |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 1L275 (799s Coleman - Natal) | 2014-10-07 09:00 | 2014-10-09 17:00 | N | N | BCH work on 1L275 structure replacement - BC maintenance does not affect AB ATC | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 786L (799s Coleman - Natal) | 2014-10-07 09:00 | 2014-10-09 17:00 | N | Y | line maintenance - BC Hydro | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 522s Cooking Lake) | 2014-10-07 10:00 | 2014-10-07 13:00 | N | N | replace faulty VSR | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.2TR (ENMAX 16),16.60L (ENMAX 34 - ENMAX 16),16.63L (ENMAX 16 - ENMAX 36),ENMAX 16 69kV Bus,8KV PT (ENMAX 16),69 kV PT (ENMAX 16) | 2014-10-07 10:01 | 2014-10-07 12:00 | N | N | substation washing | Not In Model, Transformer, Line, Bus |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (198s Blackfalds - 217s North Red Deer),217s 80N (217s North Red Deer) | 2014-10-07 12:30 | 2014-10-07 14:30 | N | N | RATD - functional trips on 217s80N & disconnect mobile sub | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 874L (522s Cooking Lake - 45s Bretona) | 2014-10-07 14:00 | 2014-10-07 17:00 | N | N | Replace Faulty VSR | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 778L (217s North Red Deer - 87s Gaetz),217s 778E (217s North Red Deer) | 2014-10-07 14:30 | 2014-10-07 16:00 | N | N | functional trips | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 17s T1 (17s Benalto),637L (17s Benalto - 580s Sylvan Lake),717L (17s Benalto - 262s Rocky Mountain House),757L (17s Benalto - 757L69),757L (297s Rimbey - 757L69),17S T3 (17s Benalto) | 2014-10-08 07:00 | 2014-10-10 17:00 | N | Y | RATD - replace 17s53 | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2014-10-08 07:30 | 2014-10-08 16:00 | N | Y | substation washing - 21 sub | Line, Transformer, Shunts |  |  | Limits ATC
ALTALINK | 917L (74s Janet - 5s East Calgary) | 2014-10-08 08:00 | 2014-10-25 17:00 | N | Y | ECTP: 917L flyover 23s line swap | Line |  |  | 240 kV, Overload
ALTALINK | 320p T6 (320p Keephills),320p Keephills 500kV Bus B | 2014-10-08 08:00 | 2014-10-09 18:00 | N | Y | doble test T6, switch maintenance - 320p4189, 320p4789, 320p5389 | Bus, Transformer |  |  | Creates Radial Feeds, 500 kV
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2014-10-08 08:00 | 2014-10-08 16:00 | N | N | heater repair with assistance from manufacturer | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 58s C1 (58s Edson),671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale),58s Edson 138kV West Bus | 2014-10-08 08:00 | 2014-10-09 17:00 | N | N | switch replacements & maintenance work | Bus, Line, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 875s 701T (875s Algar) | 2014-10-08 08:00 | 2014-10-08 09:00 | N | N | repair bent arc horn on 701A | Transformer |  | REPAIR BENT ARC HORN ON 701A @ 875S THIS WORK WILL TAKE PLACE DURING 7L36 ISOLATION SWITCHING (SEE PERMIT 2-29938) 30-60 MIN CUSTOMER OUTAGE, CO-ORDINATED WITH PEMBINA | Firm Load Loss
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2014-10-08 08:00 | 2014-10-08 12:00 | N | N | substation washing, wash after 16.60L returns | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 256s T2 (256s Harmattan) | 2014-10-08 08:00 | 2014-10-08 17:00 | N | N | EMSpec alarm | Transformer
ATCO | 7L36 (875s Algar - 820s Hangingstone) | 2014-10-08 08:00 | 2014-10-10 16:00 | N | N | tie in Willow Creek sub & remove temporary by pass | Line |  | Tie in Willow Creek sub and remove temporary bypass Two short 10 min outages to 3L204 Pembine Pipeline required to Open/Close 7L36D4 at Algar. 5L304 Suncor @ 875S ALGAR will be offloaded to an adjacent sub prior to start 7L36 WILL BE OPEN ENDED AT HANGINGSTONE PRIOR TO START. SEP 16-18 STUDY ATTACHED. CONDITIONS ARE THE SAME FOR OCT 8-10 OUTAGE. | Firm Load Loss, Creates Radial Feeds
ATCO | 7L50 (526s Buffalo Creek - 7L50D2) | 2014-10-08 08:30 | 2014-10-08 17:00 | N | Y | replace pole | Line |  | A PORTION OF 7L50 WILL BE REMOVED FROM SERVICE BX 526S BUFFALO CREEK & 7L50D2 TO REPLACE POLES A PORTION OF 7L50 BX 757S BATTLE RIVER & 7L50D1 WILL BE REMOVED FROM SERVICE TO REPLACE POLES | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 854L (397s Benbow - 854L229) | 2014-10-08 09:00 | 2014-10-09 15:00 | N | N | replace damaged insulators | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 74s 352 (74s Janet) | 2014-10-09 07:00 | 2014-10-09 08:00 | N | Y | testing 2852 BF trip to 74s352 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Prevents Normal Events
ALTALINK | 74s T2 (74s Janet),74s 77 (74s Janet) | 2014-10-09 08:00 | 2014-10-09 09:00 | N | Y | protection testing | Circuit Breaker, Transformer |  |  | 240 kV, Overload
ENMAX | 15.1TR (ENMAX 15),15.60L (ENMAX 21 - ENMAX 15) | 2014-10-09 08:00 | 2014-10-09 10:00 | N | N | substation washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36B138-36BT3 (ENMAX 36) | 2014-10-09 08:00 | 2014-10-09 16:00 | N | N | heater repair | Circuit Breaker |  |  | Overload
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2014-10-09 08:30 | 2014-10-09 10:00 | N | Y | testing 2852 BF trip to cap bank breaker | Circuit Breaker, Shunts |  |  | 240 kV, Limits ATC
ATCO | 7L50 (7L50D1 - 757s Battle River) | 2014-10-09 08:30 | 2014-10-09 17:00 | N | Y | ATCO replacing poles | Line |  |  | Overload, Firm Load Loss
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2014-10-09 09:01 | 2014-10-09 11:00 | N | N | remove mobile from 735L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C4 (74s Janet),74s 103 (74s Janet) | 2014-10-09 10:00 | 2014-10-09 11:00 | N | Y | testing 2852 BF trip to cap bank breaker 74s103 | Circuit Breaker, Shunts |  |  | 240 kV, Limits ATC
ENMAX | 15.2TR (ENMAX 15),15.62L (ENMAX 15 - ENMAX 16) | 2014-10-09 10:01 | 2014-10-09 12:00 | N | N | substation washing | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2252 (74s Janet) | 2014-10-09 11:00 | 2014-10-09 12:00 | N | Y | testing 2852 BF trip of 74s2252 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2014-10-09 12:00 | 2014-10-09 14:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 34.1TR (ENMAX 34),34.3TR (ENMAX 34),34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2014-10-09 14:01 | 2014-10-09 16:00 | N | N | substation washing | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 25B240-D140 (ENMAX 25),25B240-D141 (ENMAX 25) | 2014-10-09 16:00 | 2014-10-09 16:30 | N | Y | PT replacement | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK, ATCO | 6L126 (515L tap - 743s Sarah Lake),526L (515s Fed Pipe Judy Creek - 526L418) | 2014-10-10 08:00 | 2014-10-10 16:30 | N | N | replace 526L420- get functional after being replaced on Oct 7 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21) | 2014-10-10 08:00 | 2014-10-10 16:00 | N | N | doble 21B69-21.4TR, DGA on 21.4TR bushings | Transformer |  |  | Overload
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2014-10-10 08:00 | 2014-10-10 16:00 | N | N | heater repair | Circuit Breaker
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2014-10-11 06:30 | 2014-10-11 19:00 | N | Y | ENMAX:OH crews working on distribution on feeder 25-36.112 | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 956L (103s Goose Lake - 59s Peigan) | 2014-10-11 07:00 | 2014-10-13 17:00 | N | Y | trouble corrective: replace step bolts | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2014-10-11 07:00 | 2014-10-11 19:00 | N | N | Advice for ENMAX:OH crews working on Distribution on feeder 25-36.112 | Line
ALTALINK, EPCOR | 1203L (320p Keephills - 330p Genesee) | 2014-10-11 07:30 | 2014-10-22 18:00 | N | Y | cut 1203L in/out of 510s, energize 500 kV equipment at end of outage - WATL | Line |  |  | Pre-Condition, Limits ATC, Creates Radial Feeds, 500 kV
ATCO | 7L135 (820s Hangingstone - 977s Salt Creek) | 2014-10-11 08:00 | 2014-10-12 17:00 | N | N | 7L36 and 7L97 must be in service @ 820s prior to start Tie in 701 BF protection into 704 trip/block close ccts | Line |  | 7L36 and 7L97 must be in service @ 820s prior to start Tie in 701 BF protection into 704 trip/block close ccts. | Pre-Condition, Overload
ALTALINK, EPCOR | 1203L (320p Keephills - 330p Genesee),1238L (510s Sunnybrook - 330p Genesee),1239L (510s Sunnybrook - 330p Genesee) | 2014-10-11 08:00 | 2014-11-14 16:00 | N | N | 1239L/1203L ISD - Oct 22, 2014, 510s Sunnybrook AC switchyar will be energized. 1238L ISD - Nov. 5, 2014. | Line
ENMAX | ENMAX 47,47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington) | 2014-10-11 08:00 | 2014-10-11 16:00 | N | N | substation washing | Station, Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 8.1TR (ENMAX 8) | 2014-10-12 08:00 | 2014-10-25 16:00 | N | N | doble, transformer wash, facilities equipment inspection | Transformer
EPCOR | 557s 2406 (557s Castle Downs) | 2014-10-13 07:00 | 2014-10-19 19:00 | N | Y | retrofit of the Alstom breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 80L (194s South Red Deer - 63s Red Deer),80L (194s South Red Deer - 217s North Red Deer) | 2014-10-13 08:00 | 2014-10-13 12:00 | N | N | remove OHSW that crosses over top of station | Line |  |  | Pre-Condition, Overload
Syncrude | Aurora T1 | 2014-10-13 08:00 | 2014-10-14 18:00 | N | N | tap changer settings | Transformer |  |  | 240 kV
ATCO | 706s 701T (706s Irish Creek),706s 701 (706s Irish Creek) | 2014-10-13 08:00 | 2014-10-17 17:00 | N | N | test 701 tripping logic new settings/logic for 500BS1 protection | Circuit Breaker, Transformer |  | Test 701 tripping logic new settings/logic for 500BS1 proteciton
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2014-10-13 08:00 | 2014-10-17 17:00 | N | Y | replacing insulators at CBK/AAL/NLY - BC maintenance does not affect AB ATC | Line |  |  | 240 kV, Limits ATC, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D139 (ENMAX 25) | 2014-10-13 08:00 | 2014-10-15 16:00 | N | Y | doble, SF6 sample & install new position indicator & first year check/maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
AESO, EPCOR | 330p 808 (330p Genesee),8L10 (330P Genesee - Fording Coal Mine) | 2014-10-14 06:00 | 2014-10-17 18:00 | N | N | Sunnybrook Project HVDC/WATL project & breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
EPCOR | Rossdale C2 | 2014-10-14 07:00 | 2014-10-14 18:00 | N | N | doble CT's on R72C2 | Shunts |  |  | For Information Only
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2014-10-14 08:00 | 2014-10-17 15:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 769s 704 (769s Stettler),769s 704C (769s Stettler) | 2014-10-14 08:00 | 2014-10-14 09:00 | N | N | setting changes | Circuit Breaker, Shunts |  | SETTINGS CHANGES ARE REQUIRED ON THE 704C POW RELAY AFTER THE CHANGES ARE DONE THE BREAKER WILL HAVE TO BE CLOSED AND THEN OPENED IN ORDER TO OBTAIN A SIGNWAVE FROM THE SEL RELAY TO OBSERVE THE POINT ON THE WAVE WHERE THE BREAKER ACTUALLY CLOSES. BKR 704 WILL HAVE TO BE OPENED WHILE DOING THE SETTING CHANGES | Pre-Condition
ATCO | 7L89 (721s La Corey - 700s Bonnyville),700s 703 (700s Bonnyville) | 2014-10-14 08:00 | 2014-10-17 16:00 | N | N | change 703CT ratio and change 7L89 protections | Circuit Breaker, Line |  | To change 703CT ratio and to test 703CT and 7L89 protections that will be effected by the 703CT ratio change | Pre-Condition
ALTALINK | 310p 2852 (310p Sundance) | 2014-10-14 08:00 | 2014-10-17 17:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, Pre-Condition
BCH | 5L75 (Revelstoke - Ashton Creek) | 2014-10-14 09:00 | 2014-10-18 17:00 | N | N | replacing CVT - BC maintenance does not affect AB ATC | Line |  |  | For Information Only
ATCO | 743s 701T (743s Sarah Lake) | 2014-10-14 09:30 | 2014-10-15 17:00 | N | N | repair ground fault on oil level circuit on 701T | Transformer |  | Repair ground fault on oil level circuit on 701T... PCB Sample Equipment under outage | Over/Under Voltage, Contingency Requires Mitigation
ATCO | 789s 701R (789s Keg River),789S 705 | 2014-10-14 10:00 | 2014-10-14 16:00 | N | N | breaker testing | Terminal Equipment, Shunts |  | 789S 705 BREAKER SF6 HGF PARTIAL TESTING Reactor Bank 701R out fo service for the duration of the work | Pre-Condition
ALTALINK | 922L (310p Sundance - 17s Benalto),17s922N (17s Benalto) | 2014-10-14 10:30 | 2014-10-14 17:00 | N | Y | hot switch repair | Switch, Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ATCO | 932s 722 (932s Pemukan),932s 722C (932s Pemukan) | 2014-10-14 11:30 | 2014-10-14 12:30 | N | N | setting changes | Circuit Breaker, Shunts |  | SETTINGS CHANGES ARE REQUIRED ON THE 722C POW RELAY AFTER THE CHANGES ARE DONE THE BREAKER WILL HAVE TO BE CLOSED AND THEN OPENED IN ORDER TO OBTAIN A SIGNWAVE FROM THE SEL RELAY TO OBSERVE THE POINT ON THE WAVE WHERE THE BREAKER ACTUALLY CLOSES. BKR 722 WILL HAVE TO BE OPEN DURING SETTING CHANGES | Pre-Condition, For Information Only
ALTALINK | 866S Sundance Make-Up | 2014-10-14 12:00 | 2014-10-14 14:00 | N | N | meter module replacement | Station |  |  | For Information Only
ATCO | 932s 723 (932s Pemukan),932s 723C (932s Pemukan) | 2014-10-14 13:00 | 2014-10-14 14:30 | N | N | relay setting changes | Circuit Breaker, Shunts |  | SETTINGS CHANGES ARE REQUIRED ON THE 723C POW RELAY AFTER THE CHANGES ARE DONE THE BREAKER WILL HAVE TO BE CLOSED AND THEN OPENED IN ORDER TO OBTAIN A SIGNWAVE FROM THE SEL RELAY TO OBSERVE THE POINT ON THE WAVE WHERE THE BREAKER ACTUALLY CLOSES. BKR 723 WILL HAVE TO BE OPEN DURING SETTING CHANGES | Pre-Condition, For Information Only
ALTALINK | 478s C1 (478s Tucuman),478s 552 (478s Tucuman) | 2014-10-14 13:00 | 2014-10-14 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2014-10-15 07:00 | 2014-10-16 17:00 | N | N | 149s19 switch replacement and 138 kV bus diff protetion upgrade | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 69s T2 (69s North Barrhead),69s T4 (69s North Barrhead) | 2014-10-15 07:00 | 2014-10-16 17:00 | N | Y | 138 kV switch replacement (69s24) | Transformer |  |  | Creates Radial Feeds
ALTALINK | 701L (223s Strome - 7L701D1) | 2014-10-15 07:00 | 2014-10-15 19:00 | N | Y | close open points, energize new 223s T3 & test protections | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 876s 502 (876s Brintnell) | 2014-10-15 07:30 | 2014-10-15 17:00 | N | N | SF6 SF1 partial testing | Circuit Breaker |  | 876S 502 BREAKER SF6 SF1 PARTIAL TESTING -------- Load Transfer -------- 876S 5L532 Peak Load =13 MVA 876S 5L533 Peak Load = 12 MVA 876S 5L532 Relay Settings:25.98 MVA 876S 5L533 Relay Settings:23.4MVA -------- Load Transfer -------- | For Information Only
ALTALINK | 659s T1 (659s Pegasus Lake) | 2014-10-15 07:30 | 2014-10-15 17:30 | N | Y | install new PTs and JB for metering upgrade | Transformer |  |  | Restricts Generation
Syncrude | Aurora T-11 | 2014-10-15 08:00 | 2014-10-16 18:00 | N | Y | tap changer settings | Transformer |  |  | 240 kV
ENMAX | ENMAX 25 B240-D138 (ENMAX 25) | 2014-10-15 08:00 | 2014-10-17 16:00 | N | Y | doble, SF6 sample & install new position indicator, first year check/maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 223s T1 (223s Strome) | 2014-10-15 08:00 | 2014-10-15 13:00 | N | N | customer request for grounded advice | Transformer |  |  | For Information Only
ATCO | 706s 701T (706s Irish Creek),706s 701 (706s Irish Creek) | 2014-10-15 08:00 | 2014-10-15 16:00 | N | N | add/test trips to breaker 701 from breaker fail relay 50BF/704 | Transformer, Circuit Breaker |  | Add/test trips to breaker 701 from breaker fail relay 50BF/704 | For Information Only
ALTALINK | 13s T2 (13s Deerland),13s 852 (13s Deerland),13s 452 (13s Deerland) | 2014-10-15 08:00 | 2014-10-15 17:00 | N | Y | bus dampers coming out of bus | Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L122 (791s Rainbow Lake - 930s Arcenciel),791s 701 (791s Rainbow Lake) | 2014-10-15 08:30 | 2014-10-15 16:30 | N | N | breaker partial testing | Line, Circuit Breaker |  | 791S 701 BREAKER SF6 LTB145D1/B PARTIAL TESTING 7L122 WILL BE OPEN ENDED AT 791S DURING THIS WORK | Pre-Condition, Creates Radial Feeds
ATCO | 7L80 (740s H.R.Milner - 857s Kakwaridge) | 2014-10-15 09:00 | 2014-10-15 17:00 | N | N | urgent repairs, broken shield wire, repair conductor, replace broken insulators | Line |  | URGENT REPAIRS TO 7L80 broken shield wire, repair conductor, replace broken insulators | Firm Load Loss, Creates Radial Feeds
ATCO | 6L02 (765s Mannix Mine - 757s Battle River),757s 604 (757s Battle River) | 2014-10-15 09:00 | 2014-10-15 17:00 | N | N | air leak down test | Circuit Breaker, Line |  | BKR 604 AIR LEAK DOWN TESTS 6L02 WILL BE OPEN ENDED AT BATTLE RIVER | Firm Load Loss, Creates Radial Feeds
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2014-10-15 12:00 | 2014-10-16 21:00 | N | N | repair GIS switchgear cable end unit - emergency outage | Line |  |  | Overload
ALTALINK | 701L (223s Strome - 757s Battle River) | 2014-10-15 19:01 | 2014-10-16 17:00 | N | Y | install new bus protections and trip test breakers | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (746s Sherwood Park - 700L TAP),746s 700N (746s Sherwood Park) | 2014-10-16 07:00 | 2014-10-16 11:00 | N | N | relocate DC feed to breaker | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199L (268s Whitecourt - 199L187B) | 2014-10-16 08:00 | 2014-10-17 15:00 | N | Y | Fortis requested outage | Line |  |  | Over/Under Voltage
ALTALINK | 216s T3 (216s Knightsbridge) | 2014-10-16 08:00 | 2014-10-16 17:00 | N | N | Enbridge to connect to Altalink bus and close Open Point 'B' | Transformer
ALTALINK | 310p 152 (310p Sundance) | 2014-10-16 08:30 | 2014-10-16 09:00 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 452 (310p Sundance) | 2014-10-16 09:15 | 2014-10-16 09:45 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 752 (310p Sundance) | 2014-10-16 10:00 | 2014-10-16 10:30 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1052 (310p Sundance) | 2014-10-16 10:45 | 2014-10-16 11:15 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1652 (310p Sundance) | 2014-10-16 11:30 | 2014-10-16 12:00 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),746s 636 (746s Sherwood Park) | 2014-10-16 12:00 | 2014-10-16 16:00 | N | N | relocate DC feed to breaker | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1952 (310p Sundance) | 2014-10-16 12:45 | 2014-10-16 13:15 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 2252 (310p Sundance) | 2014-10-16 13:30 | 2014-10-16 14:00 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2552 (310p Sundance) | 2014-10-16 14:15 | 2014-10-16 14:45 | N | Y | complete trip test from 310p1352 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162s SW143 (162s Beddington),162s SW142 (162s Beddington),162s PTZ42 (162s Beddington) | 2014-10-17 07:00 | 2014-10-18 19:00 | N | Y | maintenance | Switch, Terminal Equipment |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 225s T1 (225s Magrath),225L (67s Stirling - 225AL tap),225L (225s Magrath - 225AL tap),225L (385s Spring Coulee - 225s Magrath) | 2014-10-17 08:00 | 2014-11-22 14:00 | N | N | remove 225s 69kV wood bus structure and install new metal structure | Transformer, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 730L (285s East Camrose - 730L62) | 2014-10-17 08:00 | 2014-10-17 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2014-10-17 14:30 | 2014-10-17 15:30 | N | Y | to create an open point on 725L | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | RossdaleT2 (Rossdale) | 2014-10-18 07:00 | 2014-10-18 18:00 | N | N | clearance for 72RG7 SA doble | Transformer
EPCOR | 72RG7 (Rossdale - Garneau) | 2014-10-18 07:00 | 2014-10-18 18:00 | N | N | doble SA's on Rossdale end | Line
ALTALINK | 914L (86s Bigstone - 89s Ellerslie),86s 1252 (86s Bigstone) | 2014-10-18 07:30 | 2014-10-19 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2014-10-18 08:00 | 2014-10-19 16:00 | N | Y | repair bus connections and structures (L111s) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p1205A (330p Genesee),330p1206A (330p Genesee) | 2014-10-18 08:00 | 2014-10-22 18:00 | N | Y | to perform final end to end test for new 1239L protection to Sunnybrook | Switch |  |  | Contingency Requires Mitigation, 500 kV
ENMAX | 2.83L (ENMAX 2 - 2.83L tap) | 2014-10-18 08:00 | 2014-10-18 16:00 | N | N | ENMAX: wash Enmax 2.83L portion 2 sub bus. | Line
ATCO | 6L08 (757s Battle River - 756s Bigfoot) | 2014-10-18 08:00 | 2014-10-18 16:00 | N | N | dragline move , outage to remove temp box for drag line walk through 6L08 | Line |  | 6L08 Dragline move Outage to remove temp box for drag line walk through 6L08
ENMAX | 2.1TR (ENMAX 2),2.3TR (ENMAX 2),2.83L (ENMAX 2 - 2.83L tap) | 2014-10-18 08:00 | 2014-10-18 16:00 | N | N | off peak substation washing | Transformer, Line
Syncrude | ML2 (Syncrude Mildred Lake - UE_1 Syncrude Plant 30-2) | 2014-10-18 08:00 | 2014-10-28 18:00 | N | N | breaker 1015 - 72kV upgrade | Line |  |  | For Information Only
BCH | 5L96 (Selkirk - Vaseux Lake) | 2014-10-18 09:00 | 2014-10-18 19:00 | N | Y | test disconnect - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC
ALTALINK | 33s6 (33s Spray) | 2014-10-18 13:00 | 2014-10-18 17:00 | N | N | maintenance | Switch |  |  | Restricts Generation
EPCOR | 72RG1 (Rossdale - Garneau),72RV2 (Rossdale - 511s Victoria),Rossdale 72 kV Bus 3 | 2014-10-19 07:00 | 2014-10-19 18:00 | N | N | doble of PT's & SA's & repair of BD2W disconnect | Bus, Line
Syncrude | Mildred_335 (Syncrude Mildred Lake) | 2014-10-19 08:00 | 2014-10-28 18:00 | N | N | breaker 335 - 72kV Upgrade | Circuit Breaker |  |  | For Information Only
BCH | 2L293 (Selkirk - Nelway) | 2014-10-19 09:00 | 2014-10-19 13:00 | N | N | PCB oil sampling - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC
ALTALINK | 15s T1 (15s Fort Macleod) | 2014-10-19 09:00 | 2014-10-19 12:00 | N | N | 30deg hotspot repair | Transformer
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2014-10-19 14:00 | 2014-10-19 16:00 | N | Y | substation washing | Transformer |  |  | 240 kV
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2014-10-19 16:30 | 2014-10-19 17:30 | N | Y | to close open point on 725L | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T3 (987s Clover Bar),987sC2407 (987s Clover Bar) | 2014-10-20 07:00 | 2014-10-25 18:00 | N | Y | retrofit breaker | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 69s T2 (69s North Barrhead) | 2014-10-20 07:00 | 2014-10-23 17:00 | N | N | 25kV switch replacement | Transformer |  |  | For Information Only
EPCOR | Kennedale T2 (Kennedale) | 2014-10-20 07:00 | 2014-10-24 18:00 | N | N | repair of tapchanger and doble test | Transformer |  |  | For Information Only
EPCOR | Garneau T1 (Garneau) | 2014-10-20 07:00 | 2014-11-09 18:00 | N | N | transformer oil recoditioning | Transformer |  |  | For Information Only
ATCO | 7L59 (786s High Level - 789s Keg River) | 2014-10-20 07:00 | 2014-10-30 09:00 | N | N | pole changes | Line |  | - complete all inspections / pole enforcers installs / pole changes / crossarm changes OCT/20 7:00-9:00 7L59 OOS TO OPEN TEMP JUMPER "J1" AND CREATE ISOLATING POINT. (786s - 7L59D4 AND 7L59D5, 789s - 7L59D1 AND 7L59D2, 890s - 7LA59D1, OCT. 20 - 30 PORTION OF 7L59 WILL BE OOS TO REPLACE CROSSARMS (7L59 J1, 789s - 7L59D1 AND 7L59D2) OCT.30 7:00-9:00 7L59 OOS TO MAKE UP JUMPER 7L59 J1. (786s - 7L59D4 AND 7L59D5, 789s - 7L59D1 AND 7L58D2, 890s - 7LA59D1) Call rick pierce 780-841-3629 (rick.pierce@ainsworth.ca) | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 912L (63s Red Deer - 766s Nevis) | 2014-10-20 07:30 | 2014-10-23 17:00 | N | Y | replace 63s58 PT & switch work | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 739L (14s Devon - 305s Acheson),14s 739N (14s Devon) | 2014-10-20 08:00 | 2014-10-23 16:00 | N | N | 138kV CT replacement | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 32s T1 (32s Barrier),32s 22 (32s Barrier) | 2014-10-20 08:00 | 2014-10-23 17:00 | N | Y | install new CTs at 32s22 | Transformer, Circuit Breaker |  |  | Restricts Generation
ENMAX | 24.82L (ENMAX 65 - ENMAX 24) | 2014-10-20 08:00 | 2014-10-20 16:00 | N | N | Install conductor monitoring device | Line |  |  | Pre-Condition, For Information Only
ENMAX | ENMAX 33,33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2014-10-20 08:00 | 2014-10-20 12:00 | N | N | substation washing | Station, Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (14s Devon - 305s Acheson) | 2014-10-20 08:00 | 2014-10-20 17:00 | N | N | insulator washing with ground crew | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 172s T3 (172s Sherritt Gordon) | 2014-10-20 08:00 | 2014-10-27 12:00 | N | N | replace cables and metering | Transformer
EPCOR | Rossdale C2 | 2014-10-20 08:00 | 2015-04-22 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2014-10-20 08:00 | 2014-10-20 16:00 | N | N | move dragline under 6L02 | Line |  | MOVE DRAGLINE UNDER 6L02 | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2014-10-20 08:00 | 2014-10-20 16:00 | N | N | heater repair | Circuit Breaker |  |  | Contingency Requires Mitigation
EPCOR | Rossdale C1,Rossdale C2 | 2014-10-20 08:00 | 2014-12-19 18:00 | N | N | protection upgrade | Shunts |  |  | For Information Only
ALTALINK | 727L (65s High River - 727L39S),65s 727N (65s High River) | 2014-10-20 08:00 | 2014-10-24 17:00 | N | N | Replace CT at breaker 65s727N | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 5L76 (Ashton Creek - Nicola) | 2014-10-20 09:00 | 2014-11-06 17:00 | N | N | replacing CVT - BC maintenance does not affect AB ATC | Line |  |  | For Information Only
ALTALINK | 85L (35s Rundle - 85L12),35s 85 (35s Rundle) | 2014-10-20 11:00 | 2014-10-25 17:00 | N | N | 138kV breaker replacement, add LAs | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 820s 702T (820s Hangingstone),7L97 (820s Hangingstone - 7LA97),820s 702 (820s Hangingstone) | 2014-10-20 12:00 | 2014-10-26 17:00 | N | N | protection wiring cut-in into 701TCS & 702 | Circuit Breaker, Line, Transformer |  | 7L97 WILL BE OPEN ENDED (2014S AND 933S RADIAL FED VIA 7L165). 701T WILL BE OFFLOADED TO 702T. 7L36 AND 7L135 WILL REMAIN IN SERVICE. 701 BF PROTECTION WIRING CUT-IN INTO 701TCS & 702 TRIP/BLOCK CLOSE CCTS | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 33,33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2014-10-20 12:01 | 2014-10-20 16:00 | N | N | substation washing | Station, Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2014-10-21 07:00 | 2014-10-21 17:00 | N | N | repair of CDS5 | Line
ALTALINK | 521AL (867s Sundance Blow-Down - 521L tap),521L (521L2 - 505L tap) | 2014-10-21 07:00 | 2014-10-22 17:00 | N | N | work at 867s | Line
EPCOR | 987s CN723 (987s Clover Bar) | 2014-10-21 07:00 | 2014-10-21 17:00 | N | N | cutover of new ION meter which provides analog indication to control | Circuit Breaker
ALTALINK | 956L (103s Goose Lake - 59s Peigan) | 2014-10-21 07:30 | 2014-10-26 17:00 | N | Y | replace step bolts | Line |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 25B240-D142 (ENMAX 25) | 2014-10-21 08:00 | 2014-10-21 16:00 | N | Y | first year check/maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 | 2014-10-21 08:00 | 2014-10-21 16:00 | N | N | heater repair, doble 54LA138-32.82C | Line, Terminal Equipment |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2014-10-21 08:00 | 2014-10-21 17:00 | N | Y | replace oil gauge, Doble, hot spot and o-ring replacement | Transformer |  |  | 240 kV
ALTALINK | 38s T2 (38s East Edmonton) | 2014-10-21 08:00 | 2014-10-22 17:00 | N | N | replace 25kV Protections | Transformer
ALTALINK | 39s T1 (39s Bickerdike),39s Bickerdike 240kV Bus 1 | 2014-10-21 08:00 | 2014-10-21 17:00 | N | Y | 39s34 switch repairs | Bus, Transformer |  |  | 240 kV, Over/Under Voltage
ALTALINK | 344s T1 (344s Warner) | 2014-10-21 09:00 | 2014-10-21 17:00 | N | N | TX leak repair | Transformer
ALTALINK | 397s T2 (397s Benbow) | 2014-10-22 07:00 | 2014-10-30 12:00 | N | N | install NGR, T2 AMI work, 25kV Bus Tie Manual (397s40), 25 kV Low side MOD (397s25), new 4150L feeder | Transformer
EPCOR | 803s T2 (803s Lambton) | 2014-10-22 07:00 | 2014-10-23 18:00 | N | Y | replace PT | Transformer |  |  | 240 kV, For Information Only
EPCOR | 987s T1 (987s Clover Bar) | 2014-10-22 07:00 | 2014-10-22 17:00 | N | Y | cutover of new ION meter & Replacement of bushing plug | Transformer |  |  | 240 kV
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7),ENMAX 7 138 kV Bus | 2014-10-22 08:00 | 2014-10-22 12:00 | N | N | substation washing | Transformer, Line, Bus |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 268s T1 (268s Whitecourt),503L (268s Whitecourt - 323s Whitecourt Power),526L (268s Whitecourt - 526DL185),268s Whitcourt 69 kV bus | 2014-10-22 08:00 | 2014-10-23 17:00 | N | N | 268s T1 And switch Repairs | Transformer, Bus, Line |  |  | Pre-Condition
ENMAX | 32B138-32BT5 (ENMAX 32) | 2014-10-22 08:00 | 2014-10-22 16:00 | N | N | heater repair | Circuit Breaker
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power) | 2014-10-22 08:00 | 2014-10-23 17:00 | N | Y | install grounds For 323sCustomer | Line
ENMAX | 162s 240-136 (162s Beddington) | 2014-10-22 08:00 | 2014-10-22 16:00 | N | Y | maintenance, SF6 sample | Circuit Breaker |  |  | 240 kV
ALTALINK | 132s 15 (132s Ware Junction) | 2014-10-22 08:00 | 2014-10-22 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L583 (970s Bourque - 715s Leming Lake) | 2014-10-22 08:30 | 2014-10-22 16:30 | N | N | open ended @ 715s Leming lake for maintenance | Line |  | 7L583 WILL BE OPEN ENDED @ 715S LEMING LAKE FOR MTCE ON BKR 701
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2014-10-22 09:00 | 2014-10-22 12:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7),ENMAX 7 138 kV Bus | 2014-10-22 12:01 | 2014-10-22 16:00 | N | Y | substation washing | Transformer, Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1238L (510s Sunnybrook - 330p Genesee) | 2014-10-23 00:01 | 2014-11-05 23:00 | N | N | under commission | Line |  |  | 500 kV
ALTALINK | 14s T3 (14s Devon) | 2014-10-23 07:00 | 2014-10-23 12:00 | N | N | bus protection replacement | Transformer
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2014-10-23 07:30 | 2014-10-23 17:00 | N | Y | breaker maintenance | Shunts, Circuit Breaker |  |  | Limits ATC, For Information Only
ALTALINK | 901L (74s Janet - 901AL tap) | 2014-10-23 07:30 | 2014-10-24 16:00 | N | Y | L to J: L8 - Tie Ct 24 inputs to L8 "A" & "B" line protections, BF trip 2452 to 2552, tele-protection. | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 21.1C (ENMAX 21),21.1TR (ENMAX 21),21.4TR (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20),21.80L (42s Sarcee - ENMAX 21),ENMAX 21 138kV Bus | 2014-10-23 07:30 | 2014-10-23 16:00 | N | Y | substation washing | Bus, Line, Shunts, Transformer |  |  | Overload, Limits ATC
ENMAX | 28.1TR (ENMAX 28) | 2014-10-23 08:00 | 2014-10-23 16:00 | N | N | substation washing | Transformer
ENMAX | 3.82L (ENMAX 3 - ENMAX 8),ENMAX 3 B138-3.82 (ENMAX 3) | 2014-10-23 08:00 | 2014-10-23 16:00 | N | N | heater repair | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D134 (ENMAX 25) | 2014-10-23 08:00 | 2014-10-23 16:00 | N | Y | first year check/Maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 198s T2 (198s Blackfalds) | 2014-10-23 08:00 | 2014-10-23 17:00 | N | N | replace T2 Tap Changer | Transformer
ALTALINK | 668L (394s Empress - 562s Cypress) | 2014-10-23 08:00 | 2014-11-01 15:40 | N | N | remove old 5/16 O.H.S.W. and install new O.P.G.W. | Line |  |  | Creates Radial Feeds
ALTALINK | 421s C1 (421s Hays),421s 30 (421s Hays) | 2014-10-23 08:00 | 2014-10-23 20:00 | N | N | work in capacitor bank yard | Circuit Breaker, Shunts |  |  | For Information Only
MONTANA | Great Falls Switchyard (NorthWestern Energy) - Marias (MATL) | 2014-10-23 09:00 | 2014-10-23 10:00 | N | N | Emergency repair of Northwestern Energy 230kV switch | Line |  |  | 240 kV, Limits ATC
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek),48s 887X (48s Pocaterra) | 2014-10-23 09:30 | 2014-10-23 17:00 | N | Y | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2014-10-23 12:30 | 2014-10-23 18:00 | N | N | line maintenance & insulator washing with ground crew | Line |  |  | Creates Radial Feeds
ALTALINK | 858L (149s Nisku - 40s Wetaskiwin),149s 858X (149s Nisku) | 2014-10-24 07:00 | 2014-10-24 17:00 | N | N | required for transformer protection checks. | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 700L (746s Sherwood Park - 700L TAP),746s 700N (746s Sherwood Park) | 2014-10-24 07:00 | 2014-10-24 16:00 | N | N | Add breaker 746s700N trips & status to new diff. protection and ratio change on CT's | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 9L20 (766s Nevis - 755s Cordel) | 2014-10-24 07:30 | 2014-10-25 17:00 | N | Y | dragline walk | Line |  | 9L20 O/S FOR DRAGLINE WALK | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 7L130 (710s Vermilion - 705s Kitscoty),7L14 (705s Kitscoty - 751s Hill) | 2014-10-25 08:00 | 2014-11-05 16:00 | N | N | In service date: Nov. 1, 2014 | Line
ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2014-10-25 08:00 | 2014-10-30 16:00 | N | N | In service date: Oct. 30, 2014 | Line
ALTALINK | 86s T1 (86s Bigstone),86s Bigstone 138kV bus | 2014-10-25 08:00 | 2014-10-26 17:00 | N | Y | oil gauge, switch hot spots | Transformer, Bus |  |  | 240 kV, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-RB131 (162s Beddington) | 2014-10-25 08:00 | 2014-10-25 12:00 | N | N | SCADA function checks | Circuit Breaker |  |  | 240 kV
ENMAX | 162s 240-RB134 (162s Beddington) | 2014-10-25 12:00 | 2014-10-25 16:00 | N | N | SCADA function checks | Circuit Breaker |  |  | 240 kV
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),936L (102s Langdon - 74s Janet),74s Janet 240kV Bus 2 | 2014-10-26 06:30 | 2014-10-26 18:00 | N | Y | 74s T2 and 240 kV Bus 2 GOI ¦ ECTP and L to J: Install new double curlew slack span bay going into new 985L(old 937L) bay.,ECTP and L to J: Install new double curlew slack span bay going into new 985L(old 937L) bay. | Line, Transformer, Bus, Shunts |  |  | 240 kV, Limits ATC, Contingency Requires Mitigation
ENMAX | 2.80L (ENMAX 2 - ENMAX 23) | 2014-10-26 08:00 | 2014-10-27 16:00 | N | N | commission 23.3TR MD, re-commission 138KV bus differential, substation wash, doble 23PT138-Z31 | Line |  |  | Pre-Condition
ALTALINK | 74s C2 (74s Janet),74s 54 (74s Janet) | 2014-10-27 06:30 | 2014-11-14 17:00 | N | Y | cap bank replacement, 74s53 (C2) advice | Circuit Breaker, Shunts |  |  | Limits ATC, For Information Only
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),746s 636 (746s Sherwood Park) | 2014-10-27 07:00 | 2014-10-27 16:00 | N | N | add breaker 746s636 trips & status to new diff. protection and ratio change on CT's | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T4 (987s Clover Bar),987s C2408 (987s Clover Bar) | 2014-10-27 07:00 | 2014-11-01 18:00 | N | Y | retrofit of the Alstom breaker C2408 | Circuit Breaker, Transformer |  |  | 240 kV
ALTALINK | 929L (63s Red Deer - 74s Janet) | 2014-10-27 07:30 | 2014-10-31 17:00 | N | Y | complete line reconfiguration for 1325L crossing | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2014-10-27 08:00 | 2014-11-11 17:00 | N | Y | replace shackle bolts | Line |  |  | 500 kV
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),16B69-16.63 (ENMAX 16),69 KV PT (ENMAX 36) | 2014-10-27 08:00 | 2014-10-27 16:00 | N | N | SF6 gasket seal check & shroud modification, heater check | Transformer, Line, Circuit Breaker, Terminal Equipment |  |  | Pre-Condition
ENMAX | 21.1C (ENMAX 21) | 2014-10-27 08:00 | 2014-10-27 16:00 | N | Y | breaker maintenance | Shunts |  |  | Limits ATC
ALTALINK | 739L (14s Devon - 155s Blackmud),14s 739E (14s Devon) | 2014-10-27 08:00 | 2014-10-30 12:00 | N | N | 138kV CT Replacement,insulator washing with ground crew, planned with 14s739E breaker outage. | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie) | 2014-10-27 08:00 | 2014-10-31 17:00 | N | N | replace CT at breaker 65s753E | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1152 (310p Sundance) | 2014-10-27 08:30 | 2014-11-14 15:00 | N | Y | replace CTs and breaker fail protection | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel) | 2014-10-27 08:30 | 2014-10-30 16:30 | N | Y | complete annual inspections and maintenance. ABB to provide isolation. | Shunts |  | Complete Annual Inspections and Maintenance. ATCO to shut down Sync Condenser, ABB to provide isolation. Hand over from ABB should occur during the return to normal of this permit. Ensure updated SLD Received. | Pre-Condition
ALTALINK | 744L (235s Entwistle - 744L88C) | 2014-10-27 09:00 | 2014-10-31 15:00 | N | N | line maintenance. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge),254s 770 (254s Coaldale) | 2014-10-27 10:00 | 2014-10-27 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 199s C1 (199s East Ardrie),199s T2 (199s East Airdrie),688L (199s East Airdrie - 688DL23),199s East Airdrie 138kV 1/2 Bus | 2014-10-27 11:00 | 2014-10-29 17:00 | N | Y | transformer maintenance (doble, IDD replacement), hot spot repair (199s25) | Shunts, Line, Bus, Transformer |  |  | Creates Radial Feeds
ALTALINK | 63s T1 (63s Red Deer) | 2014-10-27 12:00 | 2014-11-06 17:00 | N | Y | bushing replacement & oil leaks | Transformer |  |  | 240 kV, Overload, Over/Under Voltage
ALTALINK | 250p22 (250p Bighorn),250P 2 (250P Bighorn Plant) | 2014-10-27 12:00 | 2014-10-27 16:00 | N | Y | outage on 250p22 disconnect | Circuit Breaker, Switch |  |  | Restricts Generation
ALTALINK | 410s T1 (410s Josephburg),410s Josephburg 138kV Bus 2 | 2014-10-27 13:00 | 2014-10-27 17:00 | N | N | station service transformer maintenance | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 54L (118s Canmore - 54L172) | 2014-10-27 16:00 | 2014-10-29 16:00 | N | N | faulty CT (forced outage0 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250P 1 (250P Bighorn Plant) | 2014-10-28 07:00 | 2014-10-29 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 42s C1 (42s Sarcee),42s 31 (42s Sarcee) | 2014-10-28 07:30 | 2014-10-29 17:00 | N | Y | investigate mechanical trouble | Circuit Breaker, Shunts |  |  | Limits ATC
ATCO | 741s 505 (741s Fox Creek) | 2014-10-28 07:45 | 2014-10-28 17:00 | N | N | installing a new cap bank to replace the old capacitor bank | Terminal Equipment |  | 504C Capacitor Bank had been removed from service, we are now installing a new cap bank to replace the old capacitor bank We need to dismantle the old structure and install the new structure then install the wafers and reconnect the risers to the old breaker 504. Load Transferred to 506 to allow room for picker truck access -------- Load Transfer -------- 741S 5L425 Peak Load = 3.6 MVA 741S 5L195 Peak Load = 7.6 MVA 741S 5L425 Relay Settings: 13.9 MVA 741S 5L195 Relay Settings:13.9 MVA -------- Load Transfer -------- | For Information Only
ENMAX | 14B138-11.82 (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2014-10-28 08:00 | 2014-10-28 16:00 | N | N | SF6 gasket seal check & shroud modification, heater check | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 244S Bowmanton,1034L (244s Bowmanton - 324s Cassils),1035L (244s Bowmanton - 324s Cassils),983L (251s Whitla - 244s Bowmanton),964L (251s Whitla - 244s Bowmanton) | 2014-10-28 08:00 | 2014-11-26 08:00 | N | Y | 240/138Kv bus & close In Open points A & B | Station, Line |  |  | 240 kV, For Information Only
ALTALINK | 165s T1 (165s T.M.P.L.Gainford) | 2014-10-28 08:00 | 2014-10-28 17:00 | N | N | transformer oil leak | Transformer |  |  | For Information Only
EPCOR | RossdaleT4 (Rossdale) | 2014-10-28 08:00 | 2014-10-31 18:00 | N | N | replace PT | Transformer |  |  | For Information Only
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2014-10-28 08:00 | 2014-10-28 18:00 | N | N | insulator washing with ground crew | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2014-10-28 08:00 | 2014-10-29 16:00 | N | N | maintenance | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 23.80L (74s Janet - ENMAX 23),765L (74s Janet - 151s Strathmore) | 2014-10-28 08:00 | 2014-10-31 16:00 | N | N | L to J: required for clearance to string new 1077L conductor | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.82L (ENMAX 21 - ENMAX 20),ENMAX 20 B138-20.82 (ENMAX 20) | 2014-10-28 08:00 | 2014-10-29 16:00 | N | N | SF6 gasket seal check & shroud modification, heater check | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 746s T2 (746s Sherwood Park) | 2014-10-28 09:00 | 2014-10-28 17:00 | N | N | LTC not working in auto | Transformer
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2014-10-28 09:00 | 2014-10-28 12:00 | N | N | high load move | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 746s T2 (746s Sherwood Park) | 2014-10-29 07:00 | 2014-10-29 16:00 | N | N | add CT's to new differential protection | Transformer
ALTALINK | 14s T1 (14s Devon) | 2014-10-29 07:00 | 2014-10-29 10:00 | N | N | 138 kV bus protection replacement | Transformer
REDDEER | 247s T1 (247s Piper Creek) | 2014-10-29 07:30 | 2014-10-29 16:30 | N | N | repair switch 17-89-1 | Transformer |  |  | For Information Only
ALTALINK | 618s T1 (618s Riverbend) | 2014-10-29 08:00 | 2014-10-30 16:00 | N | N | RTU replacement project and metering upgrade | Transformer
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2014-10-29 08:00 | 2014-10-29 16:00 | N | N | gas sample 5B138-1.84 | Line
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2014-10-29 08:00 | 2014-10-29 17:00 | N | Y | bond in marker cones on Old Man River crossing span | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 602s T2 (602s Cold Creek) | 2014-10-29 13:00 | 2014-10-30 14:00 | N | N | 602s16 install Emspec Kit | Transformer
ALTALINK | 792L (191s N.W. Cardiff - 92s Viscount) | 2014-10-30 07:00 | 2014-11-12 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
REDDEER | 247s T2 (247s Piper Creek) | 2014-10-30 07:30 | 2014-10-30 16:30 | N | N | repair switch 17-89-2 | Transformer |  |  | For Information Only
ALTALINK | 115s T2 (115s Mt.Allan) | 2014-10-30 08:00 | 2014-10-30 17:00 | N | N | 25kV switch repair (115s11) and doble T2 | Transformer |  |  | Firm Load Loss
AESO | 994L (103s Goose Lake - 312s Fidler) | 2014-10-30 08:00 | 2014-10-30 17:00 | N | Y | bond in marker cones on Old Man River crossing span | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 310p 252 (310p Sundance) | 2014-10-30 08:00 | 2014-10-30 17:00 | N | Y | investigate limit switch | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 368s T1 (368s Burdett) | 2014-10-30 08:00 | 2014-10-30 11:00 | N | N | repair filter oil leaks | Transformer
ALTALINK | 33S Spray,113L (20s Ghost - 33s Spray),76L (115s Mt. Allan - 33s Spray),84L (35s Rundle - 33s Spray) | 2014-10-30 08:00 | 2014-11-13 17:00 | N | N | install new control building, expand fence, new access road, replace 33sPT1, replace insulators, new SS feed; install new line protection | Line, Station |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s C2 (83s Taber),83s 67 (83s Taber) | 2014-10-30 08:00 | 2014-10-30 17:00 | N | N | mechanical issues (breaker currently out-of-service) | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 17s C1 (17s Benalto),17s 16 (17s Benalto) | 2014-10-30 08:30 | 2014-10-30 17:00 | N | Y | capacitor bank testing | Circuit Breaker, Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 215L (38s East Edmonton - 286s Yasa),286s 215 (286s Yasa) | 2014-10-30 08:30 | 2014-10-30 12:00 | N | N | install metering circuit for 215L | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO | 7L53 (700s Bonnyville - 706s Irish Creek),700s 702 (700s Bonnyville) | 2014-10-30 09:00 | 2014-10-30 11:00 | N | N | 700S 702 Breaker heater repair / 7L53 will be open ended / Irish Creek feeding 969S | Circuit Breaker, Line |  | 700S 702 Breaker heater repair / 7L53 will be open ended / Irish Creek feeding 969S | Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 700s 701 (700s Bonnyville),7L70 (700s Bonnyville - 936s Norberg) | 2014-10-30 11:00 | 2014-10-30 13:00 | N | N | 700S 701 Breaker heater repair / 7L70 will be open ended AT 700S | Circuit Breaker, Line |  | 700S 701 Breaker heater repair / 7L70 will be open ended AT 700S | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 838L (14s Devon - 325s Leduc),14s 838X (14s Devon) | 2014-10-30 12:00 | 2014-10-30 16:00 | N | N | trip test for 138kV bus protection replacement | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2014-10-30 12:30 | 2014-10-30 16:30 | N | N | disconnect 475s mobile | Line |  |  | Creates Radial Feeds
ALTALINK | 605L (286s Yasa - 185s Bretville),286s 605 (286s Yasa) | 2014-10-30 12:30 | 2014-10-30 16:30 | N | N | install metering circuit for 605L | Circuit Breaker, Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 604L (149s Nisku - 155s Blackmud),149s 604 (149s Nisku) | 2014-10-31 07:00 | 2014-10-31 18:00 | N | N | required for transformer protection checks & insulator washing | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 955L (59s Peigan - 103s Goose Lake) | 2014-10-31 07:30 | 2014-11-01 18:00 | N | Y | replace step bolts | Line |  |  | 240 kV, Pre-Condition, Overload
ATCO | 898s904A (898s Heart Lake),898s906B (898s Heart Lake),898s900PT3 (898s Heart Lake) | 2014-10-31 08:00 | 2015-06-21 16:00 | N | Y | demolition of existing flex bus & structures, install new piles, structures & apparatus for switches | Terminal Equipment, Switch |  | Isolation on a portion of the 240KV ring bus between 904A and 906B. This isolation will be in effect for a period of 8 months to perform demolition of the existing flex bus and structures, install new piles, structures and apparatus for 240KV Switches 904B, 905A, 905B, 906A, 906B 240KV Breakers 904, 905, 906 and 240KV CT's 904, 905 and 906. | 240 kV, Contingency Requires Mitigation
ENMAX | 2.81L (ENMAX 2 - ENMAX 9),ENMAX 9 B138-2.81 (ENMAX 9) | 2014-10-31 08:00 | 2014-10-31 16:00 | N | N | SF6 gasket seal check & shroud modification, heater check | Circuit Breaker, Line |  |  | Pre-Condition, Overload
ALTALINK | 74s 2852 (74s Janet) | 2014-10-31 08:00 | 2014-10-31 16:00 | N | N | L to J: P&C work for future 1064L Bay. | Circuit Breaker |  |  | 240 kV
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2014-11-01 08:00 | 2014-11-01 16:00 | N | N | doble 65PT138-24.82C & 65LA138-24.82L-C | Line
ENMAX | 5.2TR (ENMAX 5),5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2014-11-01 08:00 | 2014-11-01 12:00 | N | N | substation washing off peak | Transformer, Line
ENMAX | 162s 138-RB83 (162s Beddington) | 2014-11-01 08:00 | 2014-11-01 16:00 | N | N | breaker maintenance & SF6 gas sample 162B138-RB83 | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 2.83L (ENMAX 2 - 2.83L tap) | 2014-11-01 12:00 | 2014-11-01 16:00 | N | N | ENMAX: wash Enmax 2.83L portion 2 sub bus | Line
ENMAX | 2.1TR (ENMAX 2),2.3TR (ENMAX 2),2.83L (ENMAX 2 - 2.83L tap) | 2014-11-01 12:00 | 2014-11-01 16:00 | N | N | substation washing off peak | Transformer, Line
ALTALINK | 968L (59s Peigan - 370s North Lethbridge) | 2014-11-02 07:30 | 2014-11-03 17:30 | N | Y | replace step bolts, will not start until 955L is returned | Line |  |  | 240 kV, Pre-Condition
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26),ENMAX 26 B138-26BT3 (ENMAX 26),26PT138-26.83 (ENMAX 26) | 2014-11-02 08:00 | 2014-11-02 12:00 | N | N | substation washing,coble 65LA138-26.83L-C | Transformer, Circuit Breaker, Terminal Equipment, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 8.1TR (ENMAX 8) | 2014-11-02 08:00 | 2014-11-15 16:00 | N | N | doble, transformer wash, fire alarm modification | Transformer
ALTALINK, ENMAX | 918L (17s Benalto - 162s Beddington),162s 240-RB132 (162s Beddington),162s 240-133 (162s Beddington),17s918X (17s Benalto) | 2014-11-02 11:30 | 2014-11-02 16:00 | N | Y | substation washing, SCADA function checks | Line, Switch, Circuit Breaker |  |  | Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 149s C1 (149s Nisku),149s 3 (149s Nisku) | 2014-11-03 07:00 | 2014-11-03 17:00 | N | N | transformer prot checks | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 746s T1 (746s Sherwood Park) | 2014-11-03 07:00 | 2014-11-03 16:00 | N | N | add CT's to new differential protection | Transformer |  |  | For Information Only
ALTALINK | 107s T1 (107s Westfield),722L (368s Burdett - 107s Westfield) | 2014-11-03 07:00 | 2014-11-06 17:00 | N | N | replace 25kV bus PTs, change CT ratios | Transformer, Line |  |  | Firm Load Loss, For Information Only
ALTALINK | 150L (42s Sarcee - 150L47),42s 150W (42s Sarcee) | 2014-11-03 07:00 | 2014-11-04 17:00 | N | N | replace CVT | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CGB3 (987s Clover Bar) | 2014-11-03 07:00 | 2014-11-28 18:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation, For Information Only
ALTALINK | 102s 6652 (102s Langdon) | 2014-11-03 07:30 | 2014-11-04 16:00 | N | Y | CT SF6 leak repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2014-11-03 08:00 | 2014-11-07 16:00 | N | N | switch replacement | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 154s Black Spruce 240 kV Bus 2 | 2014-11-03 08:00 | 2014-11-07 17:00 | N | Y | add SS VT and connect to 240kV bus 2 | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 434s T3 (434s East Stony Plain),739L (305s Acheson - 434s Stony Plain),434s 739E (434s Stony Plain) | 2014-11-03 08:00 | 2014-11-05 07:59 | N | N | CT contributions and trip Test s739E | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor) | 2014-11-03 08:00 | 2014-11-03 17:00 | N | N | install corona rings | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 (ENMAX 54) | 2014-11-03 08:00 | 2014-11-03 16:00 | N | N | heater repair, doble 54LA138-32.82C | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D136 (ENMAX 25) | 2014-11-03 08:00 | 2014-11-05 16:00 | N | N | doble work | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | E511s VictoriaT3 (511s Victoria) | 2014-11-03 08:00 | 2014-11-07 18:00 | N | N | replace pressure relief device | Transformer
SUNCOR | 29EDD-71 752_4631 (29EDD-71),29EDD-71 752_4621 (29EDD-71),29EDD-71 752_4613 (29EDD-71),29EDD-71 752_4651 (29EDD-71),29EDD-71 752_4641 (29EDD-71),29EDD-71 144kV Bus 29PP-46 | 2014-11-03 09:00 | 2014-11-05 19:00 | N | N | Switch maintenance. | Bus, Circuit Breaker
ALTALINK | 397s T1 (397s Benbow) | 2014-11-03 11:00 | 2014-11-13 15:00 | N | N | Install 397s39 Breaker, install 397s27 MOD, upgrade 2045L and 220L feeder cables, upgrade SST1 | Transformer |  |  | For Information Only
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2014-11-03 11:00 | 2014-11-13 08:00 | N | N | install new equipments | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOREP | SCR3 Suncor Chin Chute | 2014-11-03 16:00 | 2014-11-10 18:00 | N | N | automatic dispatch signal | Unit |  |  | For Information Only
EPCOR | Hardisty T2 (Hardisty) | 2014-11-04 04:00 | 2014-11-04 09:00 | N | N | EMERGENCY replacement of CT cable inside HT2 cell | Transformer
ALTALINK | 901L (63s Red Deer - 901AL tap),901L (74s Janet - 901AL tap) | 2014-11-04 06:30 | 2014-11-10 18:00 | N | Y | L to J : replace 74s901N, PTs, CTs and footings, in conjunction with north B1 bus outage | Line |  |  | 240 kV, Limits ATC
ALTALINK | 80L (194s South Red Deer - 217s North Red Deer) | 2014-11-04 08:00 | 2015-04-05 03:10 | N | N | rebuild and will be renamed to 425L; for RATD | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2014-11-04 08:00 | 2014-11-24 08:00 | N | N | line differential | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s T3 (38s East Edmonton) | 2014-11-04 08:00 | 2014-11-05 17:00 | N | N | replace 25kV Protections | Transformer
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake) | 2014-11-04 08:00 | 2015-03-25 08:00 | N | N | line rebuild; for RATD | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (305s Acheson - 434s Stony Plain) | 2014-11-04 08:00 | 2014-11-04 18:00 | N | N | insulator washing with ground crew, planned with 434s739E breaker outage. | Line
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2014-11-04 08:00 | 2014-11-05 16:00 | N | N | climbing inspection | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO | 736L (38s East Edmonton - 293s Bernese) | 2014-11-04 08:00 | 2014-11-04 17:00 | N | N | install corona rings | Line
ALTALINK | 331s T2 (331s Ponoka) | 2014-11-04 08:00 | 2014-11-04 19:00 | N | N | replace defective ETM unit | Transformer
ALTALINK | 202L (58s Edson - 178s Cynthia),58s 202X (58s Edson) | 2014-11-04 08:00 | 2014-11-04 17:00 | N | N | test recloser | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 868s T1 (868s Keephills Make-Up) | 2014-11-04 09:00 | 2014-11-04 17:00 | N | N | transformer doble | Transformer
ALTALINK | 744L (228s T.M.P.L.Niton - 744L89B) | 2014-11-04 09:00 | 2014-11-07 15:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek) | 2014-11-04 10:00 | 2014-11-04 17:00 | N | N | emergency wire repair due to ice storm | Line |  |  | Pre-Condition
ALTALINK | 370s 23 (370s North Lethbridge) | 2014-11-05 06:30 | 2014-11-05 07:30 | N | Y | replace breaker protection & control module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
REDDEER | 194s T1 (194s South Red Deer) | 2014-11-05 07:30 | 2014-11-05 16:30 | N | N | switch repair 15-81-1 | Transformer |  |  | For Information Only
ALTALINK | 223s T3 (223s Strome) | 2014-11-05 08:00 | 2014-11-10 12:00 | N | N | isolate transformer for warranty work, re-energize | Transformer
ALTALINK | 194s3 (194s South Red Deer) | 2014-11-05 08:00 | 2014-11-05 18:00 | N | N | 194s 15-81-1 maintenance | Switch
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2014-11-05 08:00 | 2014-11-05 11:00 | N | N | high load move | Line |  |  | Creates Radial Feeds
ALTALINK | 17s 637 (17s Benalto) | 2014-11-05 08:00 | 2015-03-25 08:00 | N | N | RATD - replace 17s54 & add LA's | Circuit Breaker |  |  | For Information Only
ALTALINK | 824L (593s Lethbridge Lakeview - 618s Riverbend),618s 824 (618s Riverbend) | 2014-11-05 08:00 | 2014-11-06 16:00 | N | Y | RTU replacement project and 824L CT ratio change upgrade project | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 434s T1 (434s East Stony Plain),739L (434s Stony Plain - 739L216A),434s 739W (434s Stony Plain) | 2014-11-05 08:00 | 2014-11-06 17:00 | N | N | CT contributions (T1 & s739W) / trip test 739W | Transformer, Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 893L (806s Oldman River - 103s Goose Lake) | 2014-11-05 08:00 | 2014-11-05 10:00 | N | N | open Jumpers on str 5 to facilitate bird divertor installation | Line |  |  | Restricts Generation
ALTALINK | 739L (434s Stony Plain - 739L216A) | 2014-11-05 08:00 | 2014-11-06 17:00 | N | N | insulator washing with ground crew, planned with 434s739W breaker outage | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2014-11-05 08:00 | 2014-11-05 13:00 | N | N | SF6 sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-11-05 09:00 | 2014-11-06 17:00 | N | N | replacing crossarms on 7L65 | Line |  | Replacing crossarms on 7L65 | Pre-Condition, Overload, Over/Under Voltage
BCH | 1L274 (Line Creek - Elkford) | 2014-11-05 10:00 | 2014-11-07 17:00 | N | N | replacing the structures | Line |  |  | Limits ATC
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2014-11-06 07:00 | 2014-11-09 18:00 | N | Y | string new 13L50 line | Line |  | String new 13L50 line over 9L59 Between Towers 882 & 883 @ NW 18-34-13-4. Work cannot be done using live line techniques due to clearance limitations AESO Derates may apply @ Sheerness depending on system and wind conditions | 240 kV, Pre-Condition, Creates Radial Feeds
SUNCOR | 29PL6-4 (836s Steepbank - 29EDD-1) | 2014-11-06 08:00 | 2014-11-06 20:00 | N | N | remove line markers, fix broken strands | Line
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2014-11-06 08:00 | 2014-11-06 16:00 | N | N | SF6 sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 21.1C (ENMAX 21),21.4TR (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20),21.80L (42s Sarcee - ENMAX 21) | 2014-11-06 08:00 | 2014-11-06 16:00 | N | Y | substation washing | Line, Shunts, Transformer |  |  | Overload, Limits ATC, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAXGPI | 134S Taber Wind Farm | 2014-11-06 08:00 | 2014-11-07 17:00 | N | N | installing a new relay | Station |  |  | Restricts Generation
ALTALINK | 678s T2 (678s Okotoks) | 2014-11-06 08:00 | 2014-11-06 17:00 | N | N | Install bird cover-up | Transformer |  |  | For Information Only
ALTALINK | 55s T2 (55s Olds),55s52 (55s Olds),55s51 (55s Olds) | 2014-11-06 09:00 | 2014-11-06 10:00 | N | N | remove broken blade | Switch, Transformer
SUNCOR | 29EDD-71 752_4634 (29EDD-71),29EDD-71 752_4624 (29EDD-71),29EDD-71 752_4614 (29EDD-71),29EDD-71 752_4654 (29EDD-71),29EDD-71 752_4644 (29EDD-71),29EDD-71 144kV Bus 29PP-47 | 2014-11-06 09:00 | 2014-11-08 19:00 | N | N | maintenance on switch in 29EDD-71 | Bus, Circuit Breaker |  |  | For Information Only
ATCO | 6L57 (735s Swan River - 727s Kinuso),6L97 (735s Swan River - 739s Edith Lake) | 2014-11-06 10:00 | 2014-11-06 14:00 | N | Y | install jumpers J4 as per staged SLD # 3 drawing | Line |  | Install Jumpers J4 as per staged SLD # 3 drawing J4 will stay open until Dec 8 | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 55s T2 (55s Olds),55s Olds 138kV T2 Bus | 2014-11-06 10:01 | 2014-11-06 14:00 | N | N | install new connector | Transformer, Bus
ALTALINK | 574s T3 (574s Nilrem) | 2014-11-06 13:00 | 2014-12-01 09:00 | N | N | complete the construction on 574s51, 574s1752, 574sT3, 574sSS3, new AMI including cables, 25kV bus and install Fortis feeder cables on 2035L, 2309L, 2474L and 2244L | Transformer |  |  | For Information Only
ALTALINK | 55s T2 (55s Olds),55s52 (55s Olds) | 2014-11-06 14:01 | 2014-11-06 17:00 | N | N | close in 55s51 | Switch, Transformer
ALTALINK | 893L (103s Goose Lake - 893BL tap),893BL (806s Oldman River Dam - 893BL tap) | 2014-11-06 15:00 | 2014-11-06 17:00 | N | Y | close jumpers on str 5 after bird divertor installation | Line |  |  | Restricts Generation
ENMAX | 162s 138-RB80 (162s Beddington) | 2014-11-07 08:00 | 2014-11-07 12:00 | N | N | SF6 sample | Circuit Breaker
ALTALINK | 739L (432s Carvel - 739L214B) | 2014-11-07 08:00 | 2014-11-07 18:00 | N | N | insulator washing with ground crew | Line |  | planned with 434s739E breaker outage. | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 138-RB85 (162s Beddington) | 2014-11-07 12:01 | 2014-11-07 16:00 | N | N | SF6 sample | Circuit Breaker
ALTALINK | 154S Black Spruce | 2014-11-07 15:00 | 2014-11-07 17:00 | N | N | close open point for new station service load SS2 | Station
ALTALINK, Lethbridge | 370s T5 (370s North Lethbridge),734L (241s Lethbridge Uplands - 370s North Lethbridge),172L (370s North Lethbridge - 254s Coaldale),370s North Lethbridge 138kV Bus 2 | 2014-11-08 07:00 | 2014-11-09 17:00 | N | Y | replace bus protection | Line, Transformer, Bus |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 395s North Holden),730L (197s Bardo - 730L61),197s 174W (197s Bardo),197s Bardo 138kV Bus | 2014-11-08 08:00 | 2014-11-08 17:00 | N | N | replace B phase on bus VT | Circuit Breaker, Bus, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
SUNCOR | Suncor RTU/SCADA | 2014-11-08 22:00 | 2014-11-08 23:59 | N | N | BLAN network and telephone upgrades | Terminal Equipment |  |  | Affects Visibility
ENMAX | 14.3TR (ENMAX 14) | 2014-11-09 08:00 | 2014-11-09 16:00 | N | N | oil top up | Transformer
ALTALINK | 370s 51 (370s North Lethbridge) | 2014-11-09 13:00 | 2014-11-09 15:00 | N | Y | wire new bus differential & function trips | Circuit Breaker |  |  | 240 kV
ALTALINK | 370s 1152 (370s North Lethbridge) | 2014-11-09 15:01 | 2014-11-09 17:00 | N | Y | wire new bus diff & function trips. | Circuit Breaker |  |  | 240 kV
ALTALINK | 225S Magrath | 2014-11-10 08:00 | 2014-11-20 17:00 | N | N | station service: isolate 225s SS and Fortis 18L to allow for 69kV line moves | Station
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2014-11-10 09:00 | 2014-11-17 18:00 | N | N | Gantry structure replacement | Line
SUNCOR | 30PL2-1 (30EDD-1 - 30EDD-2) | 2014-11-10 09:00 | 2014-11-12 20:00 | N | N | maintenance on breaker, VT, cable, reactor, relays and meters associated with 30PL2-2 | Line |  |  | For Information Only
ALTALINK | 936L (102s Langdon - 74s Janet) | 2014-11-11 06:30 | 2014-11-14 18:00 | N | Y | 74s Janet bypass energization work | Line |  |  | 240 kV, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2014-11-11 07:00 | 2014-11-16 13:00 | N | N | cut 712L in and out of 595s but leaving jumpers off of switch. Install flying jumpers at road in order to restore 712L | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 428s T1 (428s Namaka) | 2014-11-11 07:00 | 2014-11-13 17:00 | N | N | replace SS1, 428s14 and 428s15 | Transformer |  |  | For Information Only
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2014-11-11 08:00 | 2014-11-14 16:00 | N | N | In service date: Nov. 14, 2014 | Line
SUNCOR | Suncor RTU/SCADA | 2014-11-11 09:00 | 2014-11-11 13:00 | N | N | 29EDD-22 RTU and HMI for 29PT-84 | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 968L (59s Peigan - 370s North Lethbridge) | 2014-11-12 07:30 | 2014-11-24 17:30 | N | Y | replace step bolts | Line |  |  | 240 kV, Pre-Condition
ENMAX | 162s 138-RB83 (162s Beddington) | 2014-11-12 08:00 | 2014-11-12 16:00 | N | N | breaker maintenance & SF6 gas sample 162B138-RB83 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 744L (228s T.M.P.L.Niton - 744L89B) | 2014-11-12 09:00 | 2014-11-14 15:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (Line Creek - Elkford) | 2014-11-12 09:00 | 2014-11-14 17:00 | N | N | replacing the structures | Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ATCO | 710s 702T (710s Vermilion) | 2014-11-12 09:00 | 2014-11-13 16:00 | N | N | repair 702T oil seap on tertiary | Transformer |  |  | For Information Only
ALTALINK | 535s Joffre RTU/SCADA | 2014-11-12 10:00 | 2014-11-12 14:00 | N | N | Telus work in IP address | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 35s 85 (35s Rundle) | 2014-11-12 13:00 | 2014-11-12 15:00 | N | Y | trip test breaker for new 84L protections | Circuit Breaker |  |  | Restricts Generation
ALBIAN | 920s T (920s Jackpine),920s 901T (920s Jackpine) | 2014-11-13 08:00 | 2014-11-17 17:00 | N | Y | perform sensing resistor testing | Circuit Breaker, Transformer |  | 901T Outage @ 920S (Shell to perform sensing resistor testing) / 902T @ 920S Inservice CARRYING SUB LOAD APPROXEMATELY 50MVA TRANSFORMER RATED 150 MVA | 240 kV, Creates Radial Feeds
ALTALINK | 51s T3 (51s Wainwright) | 2014-11-13 08:00 | 2014-11-13 17:00 | N | N | T/C Hose Leaks | Transformer
Medicine Hat | Medicine Hat 41s Power and Undervoltage Scheme | 2014-11-13 08:00 | 2014-11-13 17:00 | N | Y | emergency repair | RAS |  |  | Impacts RAS
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2014-11-13 08:00 | 2014-11-19 17:00 | N | Y | 1115L OPGW re-working | Line |  |  | 240 kV
ALTALINK | 854L (397s Benbow - 854L229),397s 854X (397s Benbow) | 2014-11-13 09:00 | 2014-11-13 11:00 | N | N | trip testing from 397s39 | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 864L (397s Benbow - 714L tap),397s 864W (397s Benbow) | 2014-11-13 12:00 | 2014-11-13 14:00 | N | N | trip testing from 397s39 | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (575s Sundre - 378s Shell Caroline),378s9 (378s Shell Caroline) | 2014-11-14 08:00 | 2014-11-14 17:00 | N | N | repair broken switch | Switch, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 385s T3 (385s Spring Coulee) | 2014-11-14 08:00 | 2014-11-14 17:00 | N | N | warranty work, replacement of 25 kV CT, conductors between bushings and disconnect switch, bird cover, underground cable connectors, SCADA point commissioning | Transformer
ATCO | 834s 707 (834s Wesley Creek) | 2014-11-14 08:30 | 2014-11-14 12:00 | N | N | wire and commission 834S 707 52b contact into the Genalta DTT protection circuit | Circuit Breaker |  | Wire and commission 834S 707 52b contact into the Genalta DTT Protection Circuit. | Contingency Requires Mitigation
ATCO | 834s 708 (834s Wesley Creek) | 2014-11-14 12:00 | 2014-11-14 16:30 | N | N | wire and commission 834S 708 52b contact into the Genalta DTT protection circuit | Circuit Breaker |  | Wire and commission 834S 708 52b contact into the Genalta DTT Portection Circuit. | Contingency Requires Mitigation
ATCO | 881s 702T (881s Sturgeon),7L01 (813s Little Smoky - 881s Sturgeon) | 2014-11-14 13:00 | 2014-11-14 14:00 | N | Y | CT ratio chnage | Transformer, Line |  | ATCO POWER REQUEST - CT RATIO CHANGES, WILL REQUIRE TWO SHORT OUTAGES TO 7L01 TO OPEN AND CLOSE 702TDAS THIS SWITCH IS RATED (DLO) OPERATED DE-ENERGIZED. | Restricts Generation
ALTALINK | 1046L (310p Sundance - 338s Cherhill),310p 1052 (310p Sundance) | 2014-11-14 14:00 | 2014-11-14 15:00 | N | Y | complete trip test from 310p1152 breaker fail | Circuit Breaker, Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1252 (310p Sundance) | 2014-11-14 15:00 | 2014-11-14 16:00 | N | Y | complete trip test from 310p1152 breaker fail | Circuit Breaker |  |  | 240 kV
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2014-11-15 06:30 | 2014-11-15 18:00 | N | Y | L to J: clearance required for phase roll over on 937L line move. | Transformer, Bus, Shunts |  |  | 240 kV, Limits ATC
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-11-15 07:00 | 2014-11-15 18:00 | N | Y | ECTP: change laminated pole and Install inter-phase spacers | Line |  |  | 240 kV
ENMAX | 23.1TR (ENMAX 23),23.2TR (ENMAX 23) | 2014-11-15 08:00 | 2014-11-15 16:00 | N | N | CT wiring on the bus sides of 23B8-23.1TR & 23B8-23.2TR | Transformer |  |  | For Information Only
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2014-11-15 08:00 | 2014-11-23 18:00 | N | N | line maintenance | Line |  |  | Creates Radial Feeds
ALTALINK | 937L (102s Langdon - 74s Janet) | 2014-11-16 06:30 | 2014-11-18 18:00 | N | Y | preparing to bypass Janet 74s | Line |  |  | 240 kV, Overload, Limits ATC, Contingency Requires Mitigation
ENMAX | 1.6TR (ENMAX 1) | 2014-11-17 07:00 | 2014-11-18 17:00 | N | N | building lighting upgrade | Transformer
EPCOR | 987s CH722 (987s Clover Bar) | 2014-11-17 07:00 | 2014-11-17 17:00 | N | N | cutover of new ION meter which provides analog indication to control | Circuit Breaker
EPCOR | 330P 12TC2 (330p Genesee) | 2014-11-17 07:00 | 2014-11-17 18:00 | N | Y | repair of tapchanger RTD | Transformer |  |  | Contingency Requires Mitigation, 500 kV
EPCOR | 72CH9 (Hardisty - 987s Clover Bar),987s C72C1 (987s Clover Bar) | 2014-11-17 07:00 | 2014-11-17 17:00 | N | N | repair of CDS3 & CDS4 | Line, Circuit Breaker
ALTALINK | 54s T3 (54s Fort Saskatchewan),707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan),709L (54s Fort Saskatchewan - 172s Sherritt),54s Fort Saskatchewan 138 kV East Bus | 2014-11-17 08:00 | 2014-11-20 16:00 | N | N | replacing T3 protection, 138kV East Bus protection, replace T3 LA's, remove 54s38 | Bus, Transformer, Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 245s T2 (245s Seebe) | 2014-11-17 08:00 | 2014-11-18 17:00 | N | N | replace old VT3 with 3 new metering PTs, Replace 245s79W breaker bushing | Transformer
ALTALINK | 1206L (89s Ellerslie - 12s Heartland),89s 2152 (89s Ellerslie),89s 2252 (89s Ellerslie) | 2014-11-17 08:00 | 2014-11-22 17:00 | N | Y | shackle bolts on line; CT replacement on 89s2252, Lightning spire installation in station | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 172L (370s North Lethbridge - 172L1238) | 2014-11-17 08:00 | 2014-12-21 18:00 | N | N | line rebuild | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 214s T1 (214s Innisfail) | 2014-11-17 08:00 | 2014-11-21 16:00 | N | N | T1 LA's and noise wall installation | Transformer
ALTALINK | 310p 1252 (310p Sundance) | 2014-11-17 08:00 | 2014-11-21 17:30 | N | Y | replace 310p1252 CTs. Please note that some redundant protections will have out of service 1 at a time to facilitate the replacement of the CTs. | Circuit Breaker |  |  | 240 kV
ENMAX | 162s 240-RB131 (162s Beddington),162s 240-RB132 (162s Beddington),162s 240-133 (162s Beddington),162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington),162s 240-136 (162s Beddington),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington),162s 138-RB85 (162s Beddington),162s 138-RB84 (162s Beddington) | 2014-11-17 08:00 | 2014-11-18 16:00 | N | Y | SCADA function checks | Circuit Breaker |  |  | 240 kV
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-11-17 09:00 | 2014-11-18 17:00 | N | N | replacing cross arms on 7L65 | Line |  | Replacing cross arms on 7L65 | Pre-Condition, Over/Under Voltage
ALTALINK | 744L (228s T.M.P.L.Niton - 744L89B) | 2014-11-17 09:00 | 2014-11-21 15:00 | N | N | line maintenance | Line |  |  | Creates Radial Feeds
ALTALINK | 454s T1 (454s Buck Lake) | 2014-11-17 10:00 | 2014-11-23 17:00 | N | N | oil reclaim / doble / temp gauge | Transformer
ALTALINK | 115s T1 (115s Mt.Allan) | 2014-11-17 10:00 | 2014-11-20 17:00 | N | N | repair T1 leaks | Transformer
EPCOR | 814s T1 (814s Bellamy),72RS5 (Rossdale - Strathcona),72RV6 (Rossdale - 511s Victoria) | 2014-11-18 07:00 | 2014-11-18 18:00 | N | N | repair of BD1E | Line, Transformer |  |  | Overload
EPCOR | 330P 12TC2 (330p Genesee) | 2014-11-18 07:00 | 2014-11-21 18:00 | N | Y | repair of tapchanger RTD & Hydran change out | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 840S McNeill Station | 2014-11-18 08:00 | 2015-02-09 23:59 | N | N | Emergency Assistance Energy | Station |  | TEST THE TRANSFER CAPABILITY | For Information Only
ALTALINK | 832L (42s Sarcee - ENMAX 12) | 2014-11-18 08:00 | 2014-11-22 16:00 | N | N | ENMAX 69kV Conversion Project | Line |  |  | For Information Only
ALTALINK | 65s T3 (65s High River),812L (65s High River - 812L tap) | 2014-11-18 08:00 | 2014-11-19 17:00 | N | N | replace 65s46 | Transformer, Line |  |  | Pre-Condition
ALTALINK | 221s T3 (221s Sunken Lake) | 2014-11-18 08:00 | 2014-11-18 14:00 | N | N | fix T3 metering polarity issue | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 10.2TR (ENMAX 10),832L (ENMAX 10 - ENMAX 12) | 2014-11-18 08:00 | 2014-11-22 16:00 | N | Y | remove T-Tap & terminate new 693L & 832L, forward energize 10.2TR via 693L & 832L at return | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 221s C1 (221s Sunken Lake) | 2014-11-18 08:00 | 2014-11-25 17:00 | N | N | replace circuit switcher 221s32 | Shunts |  |  | Pre-Condition
TRANSALTAW | 418s Ardenville DVAr | 2014-11-18 08:00 | 2014-11-18 12:00 | N | Y | minor repair | Terminal Equipment |  |  | For Information Only
ALTALINK | 56L (245s Seebe - 20s Ghost),20s 56 (20s Ghost) | 2014-11-18 09:00 | 2014-11-18 10:00 | N | N | 56L TPR circuit cutover to MPLS network | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 859L (20s Ghost - T793s Horse Creek),20s 859E (20s Ghost) | 2014-11-18 12:00 | 2014-11-18 13:00 | N | N | 859L TPR circuit cutover to MPLS network | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 421s T1 (421s Hays) | 2014-11-18 15:00 | 2014-11-20 14:00 | N | N | disconnect temporary cables | Transformer
ALTALINK | 150L (20s Ghost - 150L46),20s 150 (20s Ghost) | 2014-11-18 15:00 | 2014-11-18 16:00 | N | Y | 150L TPR circuit cutover to MPLS network | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2014-11-18 16:00 | 2014-11-21 16:00 | N | N | 'A' protection outage | Line
ALTALINK | 710L (159s Colinton - 56s Boyle),56s 710X (56s Boyle) | 2014-11-19 07:00 | 2014-11-27 17:00 | N | N | 138kV breaker replacement | Line, Circuit Breaker |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 814s B2402 (814s Bellamy) | 2014-11-19 08:00 | 2014-11-22 18:00 | N | Y | hydraulic maintenance by manufacturer | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2014-11-19 08:00 | 2014-11-19 13:00 | N | N | 14B138-11.82 shroud modification | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s T1 (74s Janet),74s Janet 240kV Bus 1 | 2014-11-19 08:00 | 2014-11-28 18:00 | N | Y | L to J project: tie in North Bus extension | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2014-11-19 09:00 | 2014-11-19 17:00 | N | N | move DC feed for breaker to new control building | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 735S Swan River | 2014-11-19 15:00 | 2014-12-07 09:00 | N | N | mobile substation #2, isolate mobile while waiting for next outage (also remove old 25KV lines 5L211 and 5L214 | Station |  | Isolate Mobile while waiting for next outage (also remove old 25KV lines 5L211 and 5L214)
ALTALINK | 62s11 (62s Brazeau) | 2014-11-19 23:00 | 2014-11-20 04:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2014-11-20 01:00 | 2014-11-29 01:00 | N | N | repair of CDS2 | Line
ALTALINK | 62s12 (62s Brazeau) | 2014-11-20 04:00 | 2014-11-20 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ATCO | 7L48 (882s Triangle - 794s Valleyview) | 2014-11-20 07:00 | 2014-11-26 18:00 | N | N | new line construction | Line |  | 882s, 787s, 784s WILL BE RADIAL FED FROM 793S WEST PEACE VIA 7L06, NEW LINE CONSTRUCTION | Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21),860L (291s Cochrane - 44s Bearspaw Plant),36.81L (44s Bearspaw - ENMAX 36) | 2014-11-20 07:00 | 2014-11-20 17:00 | N | Y | replace bus insulators, arrestors,VT & P&C | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2014-11-20 08:00 | 2014-11-20 16:00 | N | N | 13B138-3.84 shroud modification | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 969S Lindbergh | 2014-11-20 08:00 | 2015-01-31 16:00 | N | N | Pegrowth 2 x 7.5 MW distribution generator. Synch date: Nov. 20, 2014. | Station
EPCOR | RossdaleT1 (Rossdale) | 2014-11-20 08:00 | 2014-11-20 18:00 | N | N | repair of CT connection in protection and bushing plug replacement | Transformer
EPCOR | 987s T2 (987s Clover Bar),987s CDS2 (987s Clover Bar) | 2014-11-20 08:00 | 2014-11-20 18:00 | N | Y | repair of CDS2 | Transformer, Switch |  |  | 240 kV, For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2014-11-20 08:00 | 2014-11-20 16:00 | N | N | replacing cross arms on 7L65 | Line |  | Replacing cross arms on 7L65 | Pre-Condition, Over/Under Voltage
ALTALINK | 17s 4 (17s Benalto) | 2014-11-20 12:00 | 2014-11-20 17:00 | N | Y | low gas (east phase) top up | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 244s Bowmanton T1,244s T2 (244s Bowmanton) | 2014-11-22 08:00 | 2014-11-28 17:00 | N | N | In service date: Nov. 26, 2014 | Transformer
ATCO | 721s 702T (721s La Corey) | 2014-11-22 08:00 | 2014-11-28 16:00 | N | N | LaCorey Area capacity increase project - ISD = November 28, 2014 | Transformer
ENMAX | 5.1TR (ENMAX 5) | 2014-11-22 08:00 | 2015-02-19 16:00 | N | N | Transformer Replacement | Transformer
ENMAX | 26.81L (ENMAX 54 - ENMAX 26),54B138-26.81 (ENMAX 54) | 2014-11-22 08:00 | 2014-11-22 16:00 | N | N | breaker maintenance 54B138-26.81 | Circuit Breaker, Line |  |  | Prevents Normal Events, Creates Radial Feeds
ALTALINK | 744L (228s T.M.P.L.Niton - 207s Pinedale) | 2014-11-22 09:00 | 2014-11-28 15:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 735s 601T (735s Swan River),735s 602T (735s Swan River) | 2014-11-22 16:00 | 2014-11-27 15:00 | N | N | work on the existing 25 kV underground cables and salvage existing 25 kV bay | Transformer |  | Risk low, sub load will be transferred onto mobile sub 835s during 601T/602T outage. Work will be to remove 601T 25kV underground cables and reconnect to 501TD2 New, connect 601T and 602T secondary's to new 25kV bay, salvage existing 25kV bay. Sequence Nov 22-27 Isolate 601T and 602T for work on the existing 25kV underground cables and salvage existing 25kV bay Nov 27 Shrink GOI to include 602T only. Load on 835s will be transferred back onto 601T Nov 28-Dec 16 Work on 502TD and 602T 25kV bus up to J2 Dec 17 Expand 602T GOI to include 500BS2 so jumper J2 can be closed/removed (602T final configuration). 25kV load will be transferred to 500BS1
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2014-11-22 17:01 | 2014-12-08 17:30 | N | Y | shackle bolts on line | Line |  |  | 500 kV
ALTALINK | 162L (415s Drywood - 229s Glenwood) | 2014-11-23 08:00 | 2015-01-22 17:00 | N | N | phase 2 re-build: structure and conductor replacement | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26),26PT138-26.83 (ENMAX 26),ENMAX 26 138kV Bus | 2014-11-23 08:00 | 2014-11-23 12:00 | N | N | substation washing and doble of 65LA138-26.83L-C | Transformer, Terminal Equipment, Bus, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2014-11-23 08:00 | 2014-11-24 14:00 | N | Y | move line onto temp structures to facilitate tower raise | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 816s P2401 (816s Petrolia) | 2014-11-24 07:00 | 2014-12-05 18:00 | N | Y | replacement of 2 sets of PTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 25B240-D132 (ENMAX 25),ENMAX 25 B240-D131 (ENMAX 25) | 2014-11-24 07:00 | 2014-11-24 16:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 54s C1 (54s Fort Saskatchewan),54s T1 (54s Fort Saskatchewan),694L (54s Fort Saskatchewan - 422s Westwood),706L (54s Fort Saskatchewan - 706L72B) | 2014-11-24 08:00 | 2014-11-27 16:00 | N | N | protection replacement | Transformer, Line, Shunts |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 (ENMAX 54) | 2014-11-24 08:00 | 2014-11-25 16:00 | N | N | heater repair | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 214s T2 (214s Innisfail) | 2014-11-24 08:00 | 2014-11-28 16:00 | N | N | T2 noise wall installation | Transformer |  |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2014-11-24 08:00 | 2015-03-13 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 787s C3 (787ss High Prairie) | 2014-11-24 08:00 | 2014-11-25 17:00 | N | N | online testing | Shunts |  |  | For Information Only
EPCOR | 814sB2406 (814s Bellamy) | 2014-11-24 08:00 | 2014-11-26 12:00 | N | Y | hydraulic maintenance by manufacturer | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2014-11-24 08:00 | 2015-02-05 16:00 | N | Y | installation of receiving structure | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 26.1TR (ENMAX 26) | 2014-11-24 08:00 | 2014-11-25 16:00 | N | N | oil leak | Transformer |  |  | For Information Only
ALTALINK | 310p 152 (310p Sundance) | 2014-11-24 08:30 | 2014-12-12 16:30 | N | Y | replace 310p152 breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2014-11-24 14:01 | 2014-11-26 17:30 | N | Y | move line onto temp structures to facilitate tower raise | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 421s T1 (421s Hays) | 2014-11-24 15:00 | 2014-11-26 14:00 | N | N | disconnect temporary cables | Transformer |  |  | For Information Only
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2014-11-25 07:00 | 2014-11-28 17:00 | N | N | Stampede project: install bottom sections of pothead structures | Line |  |  | Overload
ALTALINK | 150L (20s Ghost - 150L46),20s 150 (20s Ghost) | 2014-11-25 08:00 | 2014-11-25 17:00 | N | N | routine TPR maintenance on 20s150 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2014-11-25 08:00 | 2014-11-26 17:00 | N | N | install bird cover-up | Transformer |  |  | For Information Only
ALTALINK | 158s T2 (158s Vauxhall),821L (158s Vauxhall - 421s Hays) | 2014-11-25 08:00 | 2014-12-06 08:00 | N | N | install new control building, replace protections, metering upgrade | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-34 952_141 (29EDD-34) | 2014-11-25 09:00 | 2014-11-26 19:00 | N | Y | gauge replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 36.1TR (ENMAX 36) | 2014-11-25 09:00 | 2014-11-25 15:00 | N | N | substation washing, confirm with Bearspaw | Transformer |  |  | For Information Only
BCH | 5L96 (Selkirk - Vaseux Lake) | 2014-11-25 09:00 | 2014-11-26 19:00 | N | Y | repair 500KV line reactor - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC
ATCO | 875S Algar | 2014-11-25 10:00 | 2015-01-27 07:00 | N | N | install new breaker | Station |  | INSTALL NEW BREAKER AND GSW | For Information Only
EPCOR | 511s Victoria T5 (511s Victoria),CV5 (557s Castle Downs - 511s Victoria) | 2014-11-26 07:00 | 2014-12-09 18:00 | N | Y | manhole inspections | Line, Transformer |  |  | 240 kV
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21),860L (291s Cochrane - 44s Bearspaw Plant),36.81L (44s Bearspaw - ENMAX 36) | 2014-11-26 07:00 | 2014-11-27 17:00 | N | Y | replace bus insulators | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 12s T1 (12s Heartland) | 2014-11-26 08:00 | 2014-11-27 18:00 | N | Y | replace bushing connectors, repair oil leak | Transformer |  |  | 500 kV
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2014-11-26 08:00 | 2014-11-27 17:30 | N | Y | replace shackle bolts | Line |  |  | 500 kV
ENMAX | 5.8TR (ENMAX 5) | 2014-11-26 08:00 | 2014-11-30 16:00 | N | N | oil processing | Transformer
ATCO | EX1-01 (879s Scotford Upgrader - 402s Scotford Expansion) | 2014-11-26 08:00 | 2014-12-05 17:00 | N | N | relocate 701TD and install foundation for the new 701T location | Line |  | Relocate 701TD and install foundation for the new 701T location | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.1TR (ENMAX 40) | 2014-11-26 08:00 | 2014-11-27 16:00 | N | N | 138 kV bus differential upgrade, CT ratio change, CT commissioning, short bus differential CT's, install temporary transformer protection. | Transformer
ENMAX | 22.2TR (ENMAX 22) | 2014-11-26 08:00 | 2014-11-26 16:00 | N | N | gas sample LTC and LTC PRD | Transformer
ATCO | 840S McNeill Station | 2014-11-26 08:30 | 2014-11-27 12:00 | N | N | unavailable for energy transfer | Station |  |  | Prevents Normal Events
ALTALINK | 421s T2 (421s Hays) | 2014-11-26 16:00 | 2014-11-29 17:00 | N | N | close 421s open point D & 421s open point E (to connect 421s5700 & 421s6100) | Transformer
ENMAX | 23.3TR (ENMAX 23) | 2014-11-27 08:00 | 2014-11-28 08:00 | N | N | commissioning: backenergize for 24hrs then forward energize | Transformer
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2014-11-27 08:00 | 2014-11-27 16:00 | N | N | SF6 gasket seal check and Schroud modification, heater check | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),174L (197s Bardo - 395s North Holden),197s 174E (197s Bardo),197s 174W (197s Bardo) | 2014-11-27 08:00 | 2014-11-27 09:00 | N | N | trip test | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 730L (197s Bardo - 730L61),197s 6 (197s Bardo) | 2014-11-27 09:00 | 2014-11-27 10:00 | N | N | trip Test 197s6 switch | Switch, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 729L (285s East Camrose - 542s Ervick),285s 729W (285s East Camrose) | 2014-11-27 11:00 | 2014-11-27 12:00 | N | N | trip test 285s730N breaker | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 730L (285s East Camrose - 730L62),285s 730N (285s East Camrose) | 2014-11-27 12:00 | 2014-11-27 13:00 | N | N | trip test 285s730N breaker | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 735s 602T (735s Swan River) | 2014-11-27 15:01 | 2014-12-04 14:00 | N | N | work on 502TD and 602T 25kV bus up to J2 | Transformer |  | Risk low, sub load will be transferred onto mobile sub 835s during 601T/602T outage. Work will be to remove 601T 25kV underground cables and reconnect to 501TD2 New, connect 601T and 602T secondary's to new 25kV bay, salvage existing 25kV bay. Sequence Nov 22-27 Isolate 601T and 602T for work on the existing 25kV underground cables and salvage existing 25kV bay Nov 27 Shrink GOI to include 602T only. Load on 835s will be transferred back onto 601T Nov 28-Dec 16 Work on 502TD and 602T 25kV bus up to J2 Dec 17 Expand 602T GOI to include 500BS2 so jumper J2 can be closed/removed (602T final configuration). 25kV load will be transferred to 500BS1
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),14B138-14.83 (ENMAX 14) | 2014-11-28 08:00 | 2014-11-28 16:00 | N | N | compressor maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2014-11-29 08:00 | 2014-11-29 16:00 | N | N | gas top up 20B138-1.81 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (158s Vauxhall - 763L259),763L (158s Vauxhall - 257s Hull) | 2014-11-29 08:00 | 2014-11-29 12:00 | N | N | temp wiring on 158s31 PT secondary (1 fuse to be removed at a time) | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s SVC (102s Langdon),102s 7352 (102s Langdon) | 2014-11-29 08:00 | 2014-11-29 12:30 | N | Y | create open point to facilitate construction of new breaker 102s7452 | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Limits ATC
AESO-SC | Genalta Power | 2014-11-29 08:00 | 2015-03-31 16:00 | N | N | 5 x 4 MW generator. In service dates: Jan 15 | Unit
ALTALINK | 63s 152 (63s Red Deer) | 2014-12-01 07:00 | 2014-12-04 17:00 | N | Y | breaker fail replacement | Circuit Breaker |  |  | 240 kV
ALTALINK | 633L (56s Boyle - 405s Waupisoo),56s 633 (56s Boyle) | 2014-12-01 07:00 | 2014-12-05 17:00 | N | N | 138kV breaker replacement | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2014-12-01 08:00 | 2014-12-31 16:00 | N | N | line differential | Line
ENMAX | 162s 240-RB132 (162s Beddington) | 2014-12-01 08:00 | 2014-12-02 16:00 | N | Y | maintenance, SF6 sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Victoria V725 (Victoria) | 2014-12-01 08:00 | 2014-12-04 18:00 | N | N | wiring repair | Circuit Breaker |  |  | For Information Only
ALTALINK | 1058L (657s Summerside - 803s Lambton) | 2014-12-01 08:00 | 2014-12-07 18:00 | N | Y | protection & control upgrade | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2014-12-01 08:00 | 2014-12-03 17:00 | N | Y | ECTP: upgrade CT ratio(CT ratio changes in L9 bay) | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 574s T3 (574s Nilrem),574s T2 (574s Nilrem),574s Nilrem 240kV Bus 2,574s Nilrem 138kV Bus 2 | 2014-12-01 10:00 | 2014-12-15 17:00 | N | Y | close point A, cut In and function test 138kV bus #2 A & B" protection, T2 protection upgrade, cut in and function test 574s1752 breaker fail functional | Transformer, Bus |  |  | 240 kV, Creates Radial Feeds
ATCO | 7L36 (820s Hangingstone - 2009s Willow Lake),9L23 (848s Ruth Lake - 977s Salt Creek) | 2014-12-02 07:00 | 2014-12-02 17:00 | N | N | emergency repairs to the shield wire | Line |  |  | 240 kV, Pre-Condition, Restricts Generation
ALTALINK | 923L (324s Cassils - 356s Milo) | 2014-12-02 07:30 | 2014-12-09 18:00 | N | Y | line maintenance - interphase spacers | Line |  |  | 240 kV, Overload
ALTALINK | 968L (59s Peigan - 370s North Lethbridge) | 2014-12-02 08:00 | 2014-12-12 17:00 | N | Y | replace step bolts | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | Victoria V725 (Victoria),Victoria V726 (Victoria) | 2014-12-02 08:00 | 2014-12-02 18:00 | N | N | hot spot repair VAB4 | Circuit Breaker |  |  | For Information Only
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2) | 2014-12-02 08:00 | 2014-12-02 17:30 | N | N | 7L03 pole change out/ to change out double circuit 25 kV | Line |  | 7L03 pole change out/ to change out double circuit 25 KV | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 927L (102s Langdon - 356s Milo) | 2014-12-02 08:00 | 2014-12-07 19:00 | N | N | forced outage | Line |  |  | 240 kV
ALTALINK | 700L (422s Westwood - 746L tap),700L (746s Sherwood Park - 700L TAP) | 2014-12-02 08:00 | 2014-12-06 16:00 | N | N | 700L 'A' and 'B' protection replacement and addition of C60 breaker control | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 744L (228s T.M.P.L.Niton - 744L89B) | 2014-12-02 09:00 | 2014-12-05 15:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Creates Radial Feeds
AESO-SC | EMS | 2014-12-02 09:30 | 2014-12-02 11:30 | N | N | PI EMS - SDC System 1 Microsoft patching | SCInternal |  |  | For Information Only
ENMAX | 36.2TR (ENMAX 36) | 2014-12-02 10:00 | 2014-12-02 15:00 | N | N | substation washing, confirm with Bearspaw | Transformer |  |  | For Information Only
AESO-SC | CROW | 2014-12-02 10:00 | 2014-12-02 11:00 | N | N | CROW Prod Migration from SDC to PDC | SCInternal |  |  | For Information Only
ALTALINK, ENMAX | 3L (42s Sarcee - 272s Springbank),693L (42s Sarcee - ENMAX 10) | 2014-12-02 23:00 | 2014-12-03 06:00 | N | N | high load move | Line |  |  | Creates Radial Feeds
ENMAX | 7.82L (42s Sarcee - ENMAX 7) | 2014-12-03 02:00 | 2014-12-03 04:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 575s T1 (575s Sundre) | 2014-12-03 08:00 | 2014-12-03 17:00 | N | N | urgent oil leak repair | Transformer |  |  | For Information Only
ENMAX | 9.80L (ENMAX 31 - ENMAX 9),Enmax 31 B138-9.80 (ENMAX 31) | 2014-12-03 08:00 | 2014-12-03 16:00 | N | N | compressor maintenance | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ALTALINK | 275s T1 (275s Jenner) | 2014-12-03 08:00 | 2014-12-03 18:00 | N | Y | Install bird coverup | Transformer |  |  | 240 kV, For Information Only
TRANSALTA | 229s T1 (229s Glenwood) | 2014-12-03 09:00 | 2014-12-03 16:00 | N | N | standard relay maintenance | Transformer |  |  | For Information Only
ATCO | 2060s 702T (2060s Engstrom) | 2014-12-03 17:00 | 2014-12-08 14:00 | N | N | protection cutovers for 7L183 addition, attach risers to 703A | Transformer |  |  | For Information Only
SUNCOR | 29PL6-4 (836s Steepbank - 29EDD-1) | 2014-12-04 08:00 | 2014-12-04 20:00 | N | N | remove line markers, fix broken strands | Line |  |  | For Information Only
ALTALINK | 63s 452 (63s Red Deer) | 2014-12-04 08:00 | 2014-12-04 09:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 275s T2 (275s Jenner) | 2014-12-04 08:00 | 2014-12-04 18:00 | N | Y | install bird coverup | Transformer |  |  | 240 kV
ENMAX | 832L (ENMAX 10 - ENMAX 12) | 2014-12-04 08:00 | 2014-12-04 16:00 | N | N | emergency heater repair | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 454s T2 (454s Buck Lake) | 2014-12-04 08:00 | 2014-12-04 12:00 | N | N | replace bird cover on U/G terminator | Transformer
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),14B138-14.83 (ENMAX 14) | 2014-12-04 08:00 | 2014-12-04 16:00 | N | N | compressor maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | DT | 2014-12-04 08:00 | 2014-12-04 10:30 | N | N | DT Database partitions for 2015 and adding new settlement Intervals records | SCInternal |  |  | For Information Only
ALTALINK | 63s 2652 (63s Red Deer) | 2014-12-04 09:00 | 2014-12-04 10:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap) | 2014-12-04 09:00 | 2014-12-04 15:00 | N | Y | circuit interrupts low gas alarm | Line |  |  | Restricts Generation
ALTALINK | 63s 752 (63s Red Deer) | 2014-12-04 10:01 | 2014-12-04 11:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s T1 (63s Red Deer),63s 24 (63s Red Deer) | 2014-12-04 11:01 | 2014-12-04 12:00 | N | Y | 63s24 breaker trip test | Transformer, Circuit Breaker |  |  | 240 kV, Overload, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 816s T1 (816s Petrolia) | 2014-12-04 12:00 | 2014-12-04 18:00 | N | N | energizing of P2401 CT's | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 63s 252 (63s Red Deer) | 2014-12-04 12:01 | 2014-12-04 13:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 735s 601T (735s Swan River) | 2014-12-04 14:00 | 2014-12-17 13:00 | N | N | load transferred to mobile sub 835S, need to remove under ground 72Kv cables, then install O/H line | Transformer |  | Load transferred to mobile sub 835S, Need to remove under ground 72Kv cables, then install O/H line
ATCO | 735s 601T (735s Swan River),735s 602T (735s Swan River) | 2014-12-04 14:01 | 2015-01-14 17:00 | N | N | work on 502TD and 602T 25kV bus up to J2 | Transformer |  | Risk low, sub load will be transferred onto mobile sub 835s during 601T/602T outage. Work will be to remove 601T 25kV underground cables and reconnect to 501TD2 New, connect 601T and 602T secondary's to new 25kV bay, salvage existing 25kV bay. Sequence Nov 22-27 Isolate 601T and 602T for work on the existing 25kV underground cables and salvage existing 25kV bay Nov 27 Shrink GOI to include 602T only. Load on 835s will be transferred back onto 601T Nov 28-Dec 16 Work on 502TD and 602T 25kV bus up to J2 Dec 17 Expand 602T GOI to include 500BS2 so jumper J2 can be closed/removed (602T final configuration). 25kV load will be transferred to 500BS1
ATCO | 7L48 (784s Donnelly - 7L48D5) | 2014-12-05 07:00 | 2014-12-08 18:00 | N | N | remove switches | Line |  | 784S RADIAL FED VIA 7L06 FROM WPEACE, 882S, 787S RADIAL FED FROM 7L48 FROM 794S VALLEYVIEW, REMOVING 7L48D5, 7L48D6, 7L06D8 | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2014-12-05 08:00 | 2014-12-05 16:00 | N | N | pothead oil sample, contamination found | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 158s T2 (158s Vauxhall) | 2014-12-06 08:00 | 2014-12-08 08:00 | N | N | install new control building, replace Tx protections | Transformer
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2014-12-06 08:00 | 2014-12-06 16:00 | N | Y | substation washing, wet wash if weather permits | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (158s Vauxhall - 763L259) | 2014-12-06 08:00 | 2014-12-06 17:00 | N | N | trip test breaker, "A" and "B" line protections will also be OOS (158s end only) | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 746s T1 (746s Sherwood Park) | 2014-12-06 14:00 | 2014-12-06 15:00 | N | N | new breaker fail initiate testing to 700N (protection outage) | Transformer
ALTALINK | 746s T2 (746s Sherwood Park) | 2014-12-06 15:00 | 2014-12-06 16:00 | N | N | new breaker fail initiate testing to 700N (protection outage) | Transformer
ENMAX | ENMAX 5 5B138-5BT12 (ENMAX 5) | 2014-12-07 08:00 | 2014-12-07 16:00 | N | N | heater repair | Circuit Breaker |  |  | Overload
ALTALINK | 763L (158s Vauxhall - 257s Hull),158s25 (158s Vauxhall) | 2014-12-07 08:00 | 2014-12-07 17:00 | N | N | wire bus protection CTs, trip test breaker, "A" and "B" line protections will also be out-of-service (158s end only) | Line, Circuit Recloser |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR, ALTALINK | 909L (89s Ellerslie - 665s Dome),665s D2401 (665s Dome) | 2014-12-08 07:00 | 2014-12-08 18:00 | N | Y | repair hot connections on DDS1 | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
EPCOR | 665s TX1 (665s Dome),665s D2402 (665s Dome) | 2014-12-08 07:00 | 2014-12-08 18:00 | N | Y | repair hot connections on DDS3 | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 63s 252 (63s Red Deer) | 2014-12-08 07:00 | 2014-12-11 16:00 | N | Y | breaker fail replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 6L97 (735s Swan River - 739s Edith Lake) | 2014-12-08 08:00 | 2014-12-08 17:00 | N | N | install and remove jumper | Line |  | 735s radial fed via 6L96, 727s radial fed via 6L99, voltages will be low at 735s, 5MW of 25kV load to be transferred off of 735s to assist voltages. 6L57 and 6L97 will be tied together via Jumper J4. 735s will be T-Tapped to 6L57/6L97 via breaker 602. This permit is to install and later remove jumper J4. Relay settings will be temporarily changed at Edith Lk and Kinuso for tying the 2 lines together. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (158s Vauxhall - 257s Hull) | 2014-12-08 08:00 | 2014-12-16 07:59 | N | N | cut over line protections for 763L to new control building | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2014-12-08 08:00 | 2014-12-18 17:30 | N | Y | trouble corrective line maintenance | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1034L (244s Bowmanton - 324s Cassils),1035L (244s Bowmanton - 324s Cassils) | 2014-12-08 08:00 | 2015-06-16 12:00 | N | Y | RAVI bolt replacement - deficiency from construction - SATR BW | Line |  |  | 240 kV, For Information Only
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),746s 636 (746s Sherwood Park) | 2014-12-08 08:00 | 2014-12-08 16:00 | N | N | 746L (25kV) new C60 breaker fail function tests | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 983L (251s Whitla - 244s Bowmanton) | 2014-12-08 08:00 | 2015-08-05 17:00 | N | Y | RAVI Bolt replacement - deficiency from construction - SATR BW | Line |  |  | 240 kV, For Information Only
EPCOR | 805s T3 (805s Jasper) | 2014-12-08 08:00 | 2014-12-12 18:00 | N | Y | install temperature gauges | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 275s 2 (275s Jenner) | 2014-12-08 08:00 | 2014-12-11 18:00 | N | Y | replace CTs at 275s2 | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 983L (251s Whitla - 244s Bowmanton) | 2014-12-08 08:00 | 2015-09-23 12:00 | N | Y | RAVI bolt replacement - deficiency from construction - SATR BW | Line |  |  | 240 kV
ALTALINK | 719L (378s Shell Caroline - 719214X),378s 552 (378s Shell Caroline),378s 452 (378s Shell Caroline) | 2014-12-08 08:00 | 2014-12-12 16:00 | N | N | Replacement of A and B protections on 719L | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2014-12-08 08:00 | 2014-12-21 18:00 | N | N | rebuild portion 164L: structure replacement. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 240 kV North Bus,162s Beddington 138 kV North Bus | 2014-12-08 08:00 | 2014-12-09 16:00 | N | Y | tie in new control wiring to existing panels, DGA tapchanger & bushings | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 30.1TR (ENMAX 30) | 2014-12-08 08:00 | 2014-12-13 16:00 | N | N | 30.1TR HV bushing replacement, LTC DGA, RTN | Transformer
ENMAX | 25MD240-2GSU (ENMAX 25) | 2014-12-08 08:00 | 2014-12-09 16:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ENMAX | 25MD240-3GSU (ENMAX 25) | 2014-12-08 08:00 | 2014-12-09 16:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
EPCOR | 805s T3 (805s Jasper),805s J2404 (805s Jasper),805s J2405 (805s Jasper) | 2014-12-08 08:00 | 2014-12-08 18:00 | N | Y | repair hotspot on JAB3 | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 330p 1204 (330p Genesee) | 2014-12-08 08:00 | 2014-12-08 18:00 | N | Y | replace OLM transducer | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ATCO | 898s 501R (898s Heart Lake) | 2014-12-08 08:00 | 2014-12-12 17:00 | N | N | maintenance | Shunts |  | 501R 20MVAR reactor will be unavailable, need to place crane boom above 500SST2 and under 25kV bus to replace 500SST2, Limits of approach issues require need to isolate conductor bus above 500SST2 and 500PT2, 501R OOS as 902T 59N/500BS2 protection will be disabled with 500PT2 OOS, Station AC service will be maintained by a standby generator | For Information Only
ALTALINK | 744L (235s Entwistle - 228s T.M.P.L.Niton) | 2014-12-08 09:00 | 2014-12-12 15:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 703L (377s Hardisty - 703L) | 2014-12-08 10:00 | 2014-12-12 10:00 | N | N | build temp bypass for 769L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 2049s 902 (2049s Kettle River) | 2014-12-08 11:00 | 2014-12-08 16:00 | N | Y | emergency replacement | Circuit Breaker |  | Emergency - Replace Failed Densimeter on BKR 902. The Densimeter on BKR 902 has failed, a replacement unit is on the way. We will need to take an outage on BKR 902 to Replace it. 903, 905, and 906 to Remain In-Service | 240 kV, Creates Radial Feeds
ALTALINK | 916L (42s Sarcee - 5s East Calgary),42s 916E (42s Sarcee) | 2014-12-08 11:00 | 2014-12-11 17:00 | N | Y | 240kV breaker maintenance, replace 4 grading caps | Circuit Breaker, Line |  |  | 240 kV
EPCOR | Hardisty T1 (Hardisty) | 2014-12-09 08:00 | 2014-12-09 16:00 | N | N | temperature probe measurement & testing | Transformer |  |  | For Information Only
ALTALINK | 943L (13s Deerland - 108s Amelia),108s 943 (108s Amelia) | 2014-12-09 08:00 | 2014-12-09 18:00 | N | Y | line deficiency clean-up at 108s | Line, Switch |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR, ALTALINK | 665s D2403 (665s Dome),909L (320p Keephills - 665s Dome) | 2014-12-09 08:00 | 2014-12-09 18:00 | N | Y | Repair CT's hot connections. | Circuit Breaker, Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.3TR (ENMAX 14) | 2014-12-09 08:00 | 2014-12-09 16:00 | N | N | run through neutral | Transformer
ENMAX | 13.2TR | 2014-12-09 08:00 | 2014-12-09 16:00 | N | N | run through neutral | Terminal Equipment |  |  | For Information Only
ENMAX | 26.1TR (ENMAX 26) | 2014-12-09 08:00 | 2014-12-12 16:00 | N | N | leak repair | Transformer |  |  | For Information Only
ENMAX | 14.2TR (ENMAX 14) | 2014-12-09 08:00 | 2014-12-09 16:00 | N | N | gas relay test, LTC DGA | Transformer |  |  | For Information Only
ATCO | 9L07 (885s McMillan - 888s Dover) | 2014-12-09 09:00 | 2014-12-09 15:00 | N | Y | emergency repair of broken shield wire that has fallen between the phases | Line |  | 9L07 emergency repairs are required, that will require 9L07 to be taken out of service, December 09, 2014 09:00 -15:00. The emergency is due to a broken shield wire that has fallen between the phases. | 240 kV, Restricts Generation
ATCO | 2049s 905 (2049s Kettle River) | 2014-12-09 11:00 | 2014-12-09 15:00 | N | Y | Emergency - replace failed Densimeter. | Circuit Breaker |  | Emergency - Replace Failed Densimeter on BKR 905. The Densimeter on BKR 905 has failed, a replacement unit is on the way. We will need to take an outage on BKR 905 to Repalce it. 902, 903, and 906 to Remain In-Service | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1152 (310p Sundance) | 2014-12-09 13:32 | 2014-12-17 16:00 | N | Y | repair (forced outage) | Circuit Breaker |  |  | 240 kV
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap) | 2014-12-09 15:00 | 2014-12-09 17:00 | N | Y | circuit interrupts low gas alarm | Line |  |  | Restricts Generation
EPCOR | At-Plastics-4Rs | 2014-12-10 06:00 | 2014-12-10 16:00 | N | N | cleanup after a Control Pressure Release rained Carbon deposits on 4R equipment | Station |  |  | For Information Only
ALTALINK | 935L (324s Cassils - 356s Milo) | 2014-12-10 07:30 | 2014-12-19 18:00 | N | Y | line maintenance - interphase spacers | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 217s C1 (217s North Red Deer) | 2014-12-10 08:00 | 2014-12-12 17:00 | N | N | ground grid installation - RATD | Shunts |  |  | For Information Only
ALTALINK | 202L (61s Lodgepole - 62s Brazeau),801L (62s Brazeau - 294s Brazeau Outlet Works),62s Brazeau 138 kV South Bus | 2014-12-10 08:00 | 2014-12-11 17:00 | N | Y | 138kV bus PT replacement | Line, Bus |  |  | Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1120L (410s Josephburg - 108s Amelia) | 2014-12-10 08:00 | 2014-12-10 18:00 | N | Y | line deficiency clean-up at 108s | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2014-12-10 08:00 | 2014-12-10 16:00 | N | N | tie in new control wiring to existing panels, DGA tapchanger & bushings | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | DT | 2014-12-10 08:00 | 2014-12-10 10:40 | N | N | DT Database partitions for 2015 and adding new settlement Intervals records | SCInternal |  |  | For Information Only
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2014-12-10 09:00 | 2014-12-10 17:00 | N | N | 7L51 deficiency repairs adding stand-off insulator to hold jumper clearance from str. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s 23 (370s North Lethbridge) | 2014-12-11 07:00 | 2014-12-12 17:00 | N | Y | protection upgrade | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 37.1TR (ENMAX 37) | 2014-12-11 08:00 | 2014-12-11 16:00 | N | N | run through neutral | Transformer
ENMAX | 2.2TR (ENMAX 2) | 2014-12-11 08:00 | 2014-12-11 16:00 | N | N | HV bushing DGA | Transformer
ALTALINK | 63s 152 (63s Red Deer) | 2014-12-11 16:00 | 2014-12-11 16:30 | N | Y | 63s152 Breaker Trip Test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s 352 (63s Red Deer) | 2014-12-11 16:31 | 2014-12-11 17:00 | N | Y | 63s352 breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 370s T6 (370s North Lethbridge),370s 852 (370s North Lethbridge),370s 2352 (370s North Lethbridge) | 2014-12-12 07:00 | 2014-12-12 11:00 | N | Y | protection upgrade | Transformer, Circuit Breaker |  |  | 240 kV
ENMAX | 21.2TR (ENMAX 21) | 2014-12-12 08:00 | 2014-12-12 16:00 | N | N | run through neutral | Transformer
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2014-12-12 08:00 | 2014-12-13 16:00 | N | Y | move line from temp structures after tower raise | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 795L (121s Brooks - 421s Hays),421s 795N (421s Hays) | 2014-12-12 08:00 | 2014-12-12 20:00 | N | N | removal of redundant protection and control cabling pertaining to 421s795N | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1TR (ENMAX 21) | 2014-12-12 08:00 | 2014-12-12 16:00 | N | N | run through neutral | Transformer
ATCO | 840S McNeill Station | 2014-12-12 08:00 | 2014-12-15 16:00 | N | N | unavailable for energy transfer or tests | Station |  |  | For Information Only
ENMAX | 16.2TR (ENMAX 16) | 2014-12-12 08:00 | 2014-12-12 16:00 | N | N | Gas Relay Test | Transformer
ALTALINK | 55s52 (55s Olds),55s51 (55s Olds) | 2014-12-12 09:00 | 2014-12-12 10:00 | N | N | remove broken blade | Switch
ALTALINK | 703L (377s Hardisty - 703L),769L (377s Hardisty - 769AL tap) | 2014-12-12 10:00 | 2014-12-16 10:00 | N | N | raise line for pipeline road crossing; load will be connected to 703L and energized from 648s end | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 55s T2 (55s Olds),55s52 (55s Olds),55s51 (55s Olds) | 2014-12-12 10:01 | 2014-12-12 14:00 | N | N | install new connector at 55s, partial 138 kV | Switch, Transformer
ALTALINK | 55s52 (55s Olds) | 2014-12-12 14:01 | 2014-12-12 17:00 | N | N | close in 55s51 | Switch
ALTALINK | 55s2 (55s Olds) | 2014-12-12 17:00 | 2014-12-12 19:00 | N | N | test new motor mech | Switch
ALTALINK | 712L (99s North St. Albert - 305s Acheson) | 2014-12-13 07:00 | 2014-12-15 13:00 | N | N | Close open point "B" and energize new 595s Spruce Grove substation. | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 821L (158s Vauxhall - 421s Hays),421s 821W (421s Hays) | 2014-12-13 08:00 | 2014-12-13 20:00 | N | N | removal of redundant protection and control cabling pertaining to 421s821W. | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 595sT1 (595s Spruce Grove) | 2014-12-13 08:00 | 2014-12-19 16:00 | N | N | In service date: Dec. 15, 2014 | Transformer
ENMAX | 31.1TR (ENMAX 31) | 2014-12-13 08:00 | 2014-12-13 16:00 | N | N | LTC DGA | Transformer |  |  | For Information Only
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2014-12-13 17:00 | 2014-12-15 16:00 | N | Y | move line from temp structures after tower raise. | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 23.4TR (ENMAX 23) | 2014-12-14 08:00 | 2014-12-14 16:00 | N | N | substation washing | Transformer |  |  | For Information Only
ALTALINK | 595sT1 (595s Spruce Grove) | 2014-12-14 17:00 | 2014-12-15 09:00 | N | N | to complete station and prepare to energize at 09:00 on Dec 15,2014 | Transformer
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-12-15 01:00 | 2014-12-15 02:00 | N | N | high load | Line
ALTALINK | 63s 452 (63s Red Deer) | 2014-12-15 07:00 | 2014-12-18 16:00 | N | Y | breaker fail replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72NK23 (Kennedale - Namao),72NW15 (Namao - Woodcroft),72VN21 (Namao - 511s Victoria),Namao NDS3 (Namao) | 2014-12-15 07:00 | 2014-12-15 18:00 | N | N | repair of NDS3 | Line, Switch
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 138 kV North Bus | 2014-12-15 07:00 | 2014-12-16 19:00 | N | Y | north bus extension & tie in new control wiring to existing panels | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 816s T2 (816s Petrolia) | 2014-12-15 07:00 | 2014-12-19 18:00 | N | Y | change oil level gauges | Transformer |  |  | 240 kV
EPCOR | 816s T2 (816s Petrolia) | 2014-12-15 07:00 | 2014-12-15 18:00 | N | Y | repair disconnect connection | Transformer |  |  | 240 kV
ENMAX | 693L (42s Sarcee - ENMAX 10) | 2014-12-15 07:00 | 2014-12-16 17:00 | N | Y | Remove CT's and replace with insulators | Line |  |  | Pre-Condition, Overload
IMPERIALOIL | Imperial Oil | 2014-12-15 08:00 | 2015-03-12 16:00 | N | N | Nabiye GTG: 2 x 85 MW, Unit 1 in-service date - Dec 16, 2014, Unit 2 in-service date - Jan 1, 2015. | Unit
ALTALINK | 967L (59s Peigan - 370s North Lethbridge) | 2014-12-15 08:00 | 2014-12-19 17:00 | N | Y | Replace step bolts. | Line |  |  | 240 kV, Pre-Condition, Overload
EPCOR | NamaoT1 (Namao) | 2014-12-15 08:00 | 2014-12-15 17:00 | N | N | Temperature Probe measurement & Testing | Transformer
ENMAX | ENMAX 10 B138-693 (ENMAX 10) | 2014-12-15 08:00 | 2014-12-16 16:00 | N | Y | Kelmen test (timing test) | Circuit Breaker |  |  | Pre-Condition
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2014-12-15 09:00 | 2014-12-15 14:00 | N | N | RMTS requested operational checks of the 94 Tripping relay on breaker 606. | Line |  | RMTS requested operational checks of the 94 Tripping relay on breaker 606 which was suspected to have not operated during the last line fault causing a transformer lockout. A real time T&O was not feasible, so work is being schedule for a later date. Test and Operate Protection Trips | Pre-Condition
ALTALINK | 853L (504s Queenstown - 853L76A) | 2014-12-15 20:25 | 2014-12-23 16:00 | N | N | forced outage due to iccing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2014-12-16 07:00 | 2014-12-16 17:00 | N | N | remove CT's and replace with insulators | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (158s Vauxhall - 763L259) | 2014-12-16 08:00 | 2014-12-19 17:00 | N | N | cut over line protections for 763L to new control building | Line |  |  | Overload
ENMAX | 15.2TR (ENMAX 15) | 2014-12-16 08:00 | 2014-12-16 12:00 | N | N | Transformer maintenance | Transformer
ALTALINK | 698s T1 (698s Jackfish) | 2014-12-16 08:00 | 2014-12-16 12:00 | N | N | repair 25kV VT Ground Connections | Transformer |  |  | 240 kV
EPCOR | 805s T1 (805s Jasper) | 2014-12-16 08:00 | 2014-12-19 18:00 | N | Y | temperature monitor install | Transformer |  |  | 240 kV
ALTALINK | 650s SVC (650s Hansman Lake) | 2014-12-16 08:30 | 2014-12-17 17:00 | N | Y | Investigate Alarms | Shunts |  |  | 240 kV
ENMAX | 1.7TR (ENMAX 1) | 2014-12-16 12:00 | 2014-12-16 16:00 | N | N | Run through Neutral | Transformer |  |  | For Information Only
ALTALINK | 698s T2 (698s Jackfish) | 2014-12-16 13:00 | 2014-12-16 17:00 | N | N | repair 25kV VT Ground Connections | Transformer |  |  | 240 kV
ENMAX, ALTALINK | 2.4TR (ENMAX 2),5s T1 (East Calgary),5s 8 (ENMAX 2) | 2014-12-16 23:00 | 2014-12-17 07:00 | N | Y | emergency repair a broken MD | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2014-12-17 00:07 | 2014-12-21 16:00 | N | N | forced outage due to icing issue | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 58L (245s Seebe - 32s Barrier),90L (115s Mt. Allan - 32s Barrier) | 2014-12-17 07:00 | 2014-12-17 12:00 | N | Y | complete wiring of 33s76L breaker fail trip and to move the Com Fail from a direct trip to a timed delayed trip. trip tests,complete wiring of 33s76L breaker fail trip and to move the Com Fail from a direct trip to a timed delayed trip. trip testsbarrier | Line |  |  | Restricts Generation
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 138 kV South Bus | 2014-12-17 07:00 | 2014-12-18 19:00 | N | Y | south bus extension & tie in new control wiring to existing panels | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet) | 2014-12-17 07:30 | 2014-12-17 17:00 | N | Y | density gauge replacement/gas leak repair | Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2014-12-17 08:00 | 2014-12-22 08:00 | N | Y | 1115L OPGW re-working | Line |  |  | 240 kV
ATCO | 6L126 (515L tap - 743s Sarah Lake),743s 601 (743s Sarah Lake) | 2014-12-17 08:00 | 2014-12-18 12:00 | N | N | test the communication and functionality of the SEL-2506 relay at 743s Sarah Lake for the Carson project | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 183s T2 (183s Underwood) | 2014-12-17 08:00 | 2014-12-22 09:00 | N | N | modify conservator tank gauge, install proper amount of oil, install and commission ITM | Transformer
ENMAX | 34.3TR (ENMAX 34) | 2014-12-17 08:00 | 2014-12-17 12:00 | N | N | LTC DGA | Transformer
ALTALINK | 310p 2552 (310p Sundance) | 2014-12-17 08:15 | 2014-12-17 09:00 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2252 (310p Sundance) | 2014-12-17 09:15 | 2014-12-17 09:45 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1952 (310p Sundance) | 2014-12-17 10:00 | 2014-12-17 10:30 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1652 (310p Sundance) | 2014-12-17 10:45 | 2014-12-17 11:15 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 250p11 (250p Bighorn) | 2014-12-17 11:00 | 2014-12-17 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 310p 1352 (310p Sundance) | 2014-12-17 11:30 | 2014-12-17 12:00 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 11.3TR (ENMAX 11) | 2014-12-17 12:00 | 2014-12-17 16:00 | N | N | run through neutral | Transformer
ALTALINK | 310p 1052 (310p Sundance) | 2014-12-17 12:45 | 2014-12-17 13:15 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 752 (310p Sundance) | 2014-12-17 13:30 | 2014-12-17 14:00 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 452 (310p Sundance) | 2014-12-17 14:15 | 2014-12-17 14:45 | N | Y | complete trip test from 310p152 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2852 (310p Sundance) | 2014-12-17 15:00 | 2014-12-17 15:30 | N | Y | complete trip test from 310p152 breaker fail, 767L will be placed into service to accommodate this short outage | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX, ALTALINK | 2.4TR (ENMAX 2),5s T1 (East Calgary),5s 8 (ENMAX 2) | 2014-12-17 23:00 | 2014-12-18 07:00 | N | Y | emergency repair a broken MD | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2014-12-18 08:00 | 2014-12-18 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 974L (39s Bickerdike - 310p Sundance),310p 252 (310p Sundance) | 2014-12-18 14:30 | 2014-12-18 16:00 | N | Y | complete trip test from 310p152 breaker fail. Breakers open only @ 39s. Energize new 310p152 at end of this outage | Circuit Breaker, Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 63s 552 (63s Red Deer) | 2014-12-18 16:00 | 2014-12-18 17:00 | N | N | 63s552 breaker trip test | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 63s 752 (63s Red Deer) | 2014-12-18 16:00 | 2014-12-18 17:00 | N | N | 63s752 breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s 152 (63s Red Deer) | 2014-12-18 16:00 | 2014-12-18 17:00 | N | N | 63s152 breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s T1 (63s Red Deer),63s 24 (63s Red Deer) | 2014-12-18 16:00 | 2014-12-18 17:00 | N | Y | 63s24 breaker trip test | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 63s 2652 (63s Red Deer) | 2014-12-18 16:00 | 2014-12-18 17:00 | N | N | 63s2652 breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 8.6TR (ENMAX 8) | 2014-12-19 08:00 | 2014-12-19 12:00 | N | N | run through neutral | Transformer |  |  | For Information Only
VISIONREQ | 354s DVAR2 (354s Summerview) | 2014-12-19 08:00 | 2014-12-19 18:00 | N | N | DVAR repairs | Shunts |  |  | For Information Only
ENMAX | 12.2TR (ENMAX 12) | 2014-12-19 12:00 | 2014-12-19 16:00 | N | N | run through neutral | Transformer |  |  | For Information Only
VISIONREQ | 354s DVAR1 (354s Summerview) | 2014-12-19 15:45 | 2014-12-23 16:00 | N | N | DVAr repairs | Shunts |  |  | For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2014-12-20 01:00 | 2014-12-20 02:00 | N | N | high load | Line
ALTALINK | 763L (158s Vauxhall - 763L259),763L (158s Vauxhall - 257s Hull) | 2014-12-20 08:00 | 2014-12-20 12:00 | N | N | remove temp wiring on 158s31 PT secondary | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.3TR (ENMAX 31) | 2014-12-20 08:00 | 2014-12-23 16:00 | N | N | LTC DGA issue | Transformer
ALTALINK | 821L (158s Vauxhall - 421s Hays),158s29 (158s Vauxhall) | 2014-12-20 12:01 | 2014-12-20 14:00 | N | N | 158s29 breaker trip tests | Line, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D133 (ENMAX 25) | 2014-12-22 08:00 | 2014-12-23 16:00 | N | Y | heater repair | Circuit Breaker |  |  | 240 kV
ALTALINK | 421s T1 (421s Hays) | 2014-12-22 08:00 | 2014-12-22 17:00 | N | N | install bird cover on feeders and MOD | Transformer |  |  | For Information Only
EPCOR | RossdaleT1 (Rossdale) | 2014-12-22 08:00 | 2014-12-22 18:00 | N | N | repair of CT connection in protection panel and bushing plug replacement | Transformer
ENMAX | 32.2TR (ENMAX 32) | 2014-12-22 08:00 | 2014-12-22 16:00 | N | N | PRD contact repair | Transformer |  |  | For Information Only
ALTALINK | 310p 2152 (310p Sundance) | 2014-12-22 10:00 | 2014-12-22 17:00 | N | Y | high priority breaker low oil repairs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 6L05 (843s Bigknife Creek - 757s Battle River) | 2014-12-22 10:00 | 2014-12-22 15:00 | N | N | installing station class lightIning arresters on 6L05 between 6L05D3 and 6L05D4 at 764S Heisler | Line |  | Installing station class lightIning arresters on 6L05 between 6L05D3 and 6L05D4 at 764S Heisler | Firm Load Loss, Creates Radial Feeds
ATCO | 9L24 (959s Lanfine - 946s Oakland) | 2014-12-23 07:00 | 2014-12-23 16:00 | N | Y | accommodate testing of new 959s Lanfine SVC | Line |  | 9L24 IS REQUIRED TO BE OPEN ENDED @ 959S LANFINE TO ACCOMMODATE TESTING OF THE NEW SVC. ALTALINK WILL ONLY ALLOW 9L24 & 948L TO BE REMOVED FROM SERVICE AT THE SAME TIME FOR APPROX 5 MIN PLEASE REFER TO THE ATTACHED RISK ASSESSMENTS THIS WORK IS IN CONJUNCTION WITH CROW #2-28060 | 240 kV, Pre-Condition
ALTALINK | 703L (648s Metiskow - 703L),648s 703W (648s Metiskow) | 2014-12-23 10:00 | 2014-12-23 14:00 | N | N | low oil no gas | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 240 kV North Bus,162s Beddington 138 kV North Bus | 2014-12-30 07:00 | 2014-12-30 12:00 | N | Y | low oil emergency outage | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 337s T2 (337s Canada Liquidair) | 2014-12-30 08:00 | 2014-12-30 17:00 | N | N | repair T2 Oil Leak | Transformer
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2014-12-30 08:30 | 2014-12-30 17:00 | N | Y | 138 kV breaker maintenance | Circuit Breaker, Shunts |  |  | Limits ATC
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2014-12-30 12:00 | 2014-12-30 16:00 | N | Y | low oil emergency outage | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2015-01-02 07:00 | 2015-01-02 16:00 | N | Y | low oil emergency outage | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 387S Shepard | 2015-01-03 16:00 | 2015-01-08 16:00 | N | N | PSS outage | Station |  |  | For Information Only
ALTALINK | 74s 2252 (74s Janet) | 2015-01-05 08:00 | 2015-01-08 17:00 | N | Y | CT22 CT ratio change to south bus protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 8.1TR (ENMAX 8),8.2TR (ENMAX 8) | 2015-01-05 08:00 | 2015-01-08 16:00 | N | N | switch maintenance on 8-6a01, 8-6a02, 8-6a10, 8-6a81, 8-6a82, 8-7a11, 8-1a15 | Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 9.1TR (ENMAX 9),9.2TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2015-01-05 08:00 | 2015-01-08 16:00 | N | N | 9.1TR MD, 9.2TR MD, SW 83, 84, 85, 86, 89, 90 maintenance | Line, Transformer |  |  | For Information Only
ATCO | 720s 901 (720s Wabasca) | 2015-01-05 11:00 | 2015-01-05 13:00 | N | Y | oil fill | Circuit Breaker |  | The dashpots on breaker 901 need to be filled with oil. I would like the breaker to be open and in the Local/Remote switch in Local for personal safety. | Pre-Condition
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2015-01-05 13:00 | 2015-01-06 16:00 | N | Y | install J4 and accommodate relay setting change | Line |  | Install J4 so we can have a outage on 600BS2 We need to switch out 6L57 on the 5th of Jan to allow us to change the relay settings and we will need to have 6L57 open on the 8th to change the settings back to normal See CSP 2 - 31414 6L97 can be switched out on Jan 6th at 7 am | Pre-Condition, Creates Radial Feeds
ATCO | 6L57 (735s Swan River - 727s Kinuso),6L97 (735s Swan River - 739s Edith Lake) | 2015-01-05 16:01 | 2015-01-06 16:00 | N | Y | accommodate 6L96 outage & tie in jumper | Line |  |  | Pre-Condition, Creates Radial Feeds
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2015-01-06 08:00 | 2015-01-08 12:00 | N | Y | replace arms, saddles, and pole | Line |  | Replace arms, saddles, and pole. | Creates Radial Feeds
ATCO | 735s Swan River 72kV Bus 1 | 2015-01-06 08:00 | 2015-01-07 13:00 | N | N | remove 600D2 and structure and old CT's | Bus |  | Remove 600D2 and structure and old CT's
ATCO | 827s SVC (827s Cranberry Lake) | 2015-01-06 11:00 | 2015-01-07 14:00 | N | Y | investigate blower and start-up | Shunts |  | INVESTIGATE BLOWER AND START-UP | Pre-Condition
ATCO | 735s Swan River 600BS2,6L96 (735s Swan River - 6L96 Tap) | 2015-01-06 16:01 | 2015-01-07 16:00 | N | N | installing new fused disconnects for 600PT1 ( 600PT1X & Y) | Bus, Line |  | installing new fused disconnects for 600PT1 ( 600PT1X & Y) | Pre-Condition, Over/Under Voltage
EPCOR | 987s T2 (987s Clover Bar),987s T4 (987s Clover Bar),987s CDS31 (987s Clover Bar) | 2015-01-07 07:00 | 2015-01-07 18:00 | N | Y | repair CDS31 disconnect | Transformer, Switch |  |  | 240 kV
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2015-01-07 08:00 | 2015-01-17 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 9L23 (848s Ruth Lake - 977s Salt Creek) | 2015-01-07 08:00 | 2015-01-10 18:00 | N | Y | install foundations under the line | Line |  | Install foundations under the line | 240 kV, Pre-Condition
ATCO | 6L57 (735s Swan River - 727s Kinuso),6L97 (735s Swan River - 739s Edith Lake) | 2015-01-07 16:01 | 2015-01-08 16:00 | N | Y | accommodate 6L96 outage | Line |  |  | Pre-Condition, Creates Radial Feeds
ATCO | 6L97 (735s Swan River - 739s Edith Lake),735s 603 (735s Swan River) | 2015-01-07 16:01 | 2015-01-09 12:00 | N | N | transfer controls to new building | Circuit Breaker, Line |  | Transfer controls to New building | Pre-Condition, Over/Under Voltage
ALTALINK | 62s12 (62s Brazeau) | 2015-01-07 23:00 | 2015-01-08 04:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s11 (62s Brazeau) | 2015-01-08 04:00 | 2015-01-08 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
TRANSALTAGP | BRA Brazeau Hydro Generator Test | 2015-01-08 04:00 | 2015-01-08 06:00 | N | N | unit 2 black start test | Unit
EPCOR | 814s T2 (814s Bellamy),RossdaleT1 (Rossdale),Rossdale BR722 (Rossdale),Rossdale RR723 (Rossdale) | 2015-01-08 07:00 | 2015-01-08 18:00 | N | Y | Repair of CT connection in protection PNL and Bushing plug replacement | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2015-01-08 16:00 | 2015-01-23 16:00 | N | N | line differential | Line |  |  | For Information Only
ATCO | 774s 701T (774s Monitor) | 2015-01-09 08:00 | 2015-01-20 16:00 | N | N | project work - capacity increase to sub, to facilitate install of new conductor on 25 kV bus and install of new 702T | Transformer |  |  | For Information Only
ATCO | 774S Monitor,6L12 (6L25 tap - 774s Monitor),774S 701T,774S 600PT1 | 2015-01-09 08:00 | 2015-09-11 16:00 | N | N | move 701T and install 707 and 707A. | Line, Station, Terminal Equipment |  | 6L12 will be open between D3 and 774s, 773s Coronation sub will be radial fed from 775s, 774s 25kV load will be fed from 902T mobile sub at 774s. Move 701T, salvage 701TCS, Install new 707, 707A, Replace 501TD GSW with 501TD MOD, Replace 600PT1. Once jumper J1 (144kV upper to lower bus) has been opened under HOP 2-30655, then move 701T isolation point from 701TCS to J1.
ATCO | 735s 604 (735s Swan River),6L96 (735s Swan River - 6L96 Tap) | 2015-01-09 13:00 | 2015-01-14 09:00 | N | N | transfer 604 controls & protection to new building | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2015-01-10 06:00 | 2015-01-11 17:00 | N | N | install top two sections of the north pothead structure, salvage existing lattice structure #13 | Line |  |  | For Information Only
EPCOR | 816s T1 (816s Petrolia) | 2015-01-12 07:00 | 2015-01-17 18:00 | N | Y | change oil Level gauges | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 727L (65s High River - 727L39S) | 2015-01-12 07:00 | 2015-01-17 18:00 | N | N | Foothils 138kV: install Caissons,footings and bases under portion of 727L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap) | 2015-01-12 07:30 | 2015-01-17 17:30 | N | N | line flattening at str 67 - 681s Bannerman project | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2015-01-12 07:30 | 2015-01-12 17:30 | N | Y | bond marker cones on Oldman River crossing | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.1TR (ENMAX 15),15.60L (ENMAX 21 - ENMAX 15) | 2015-01-12 08:00 | 2015-01-13 16:00 | N | N | 15.1TR MD, SW 61, 62, 63 maintenance | Line, Transformer |  |  | Pre-Condition, Overload
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2015-01-12 08:00 | 2015-01-13 16:00 | N | N | SW maint 8-1a10, 8-1a52, 8-1a8, 8-1a01, 8-1a51 | Line
EPCOR | 805s T4 (805s Jasper) | 2015-01-12 08:00 | 2015-01-16 18:00 | N | Y | change oil Level gauges | Transformer |  |  | 240 kV
ALTALINK | 172L (370s North Lethbridge - 254s Coaldale) | 2015-01-12 09:00 | 2015-01-15 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 322s T1 (322s Cowley Ridge) | 2015-01-12 09:30 | 2015-01-12 15:30 | N | Y | 25kV distribution padmount inspection and possible replacement | Transformer |  |  | Restricts Generation
AESO-SC | EMS | 2015-01-12 10:00 | 2015-01-12 16:00 | N | N | EMS project Microsoft patching | SCInternal |  |  | For Information Only
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2015-01-13 07:30 | 2015-01-13 17:30 | N | Y | bond marker cones on Oldman River crossing | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 927L (102s Langdon - 356s Milo),356s 552 (356s Milo),356s 652 (356s Milo) | 2015-01-13 08:00 | 2015-01-15 17:00 | N | Y | install WATL RAS, test breakers | Line, Circuit Breaker |  |  | 240 kV, Overload, Over/Under Voltage
ALTALINK | 185L (415s Drywood - 379s Shell Canada Waterton) | 2015-01-13 08:00 | 2015-01-15 17:00 | N | N | upgrade dead-end structure to allow the 164L re-build to occur in the future, this structure shares existing guy wires with 164L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 24.83L (74s Janet - ENMAX 24) | 2015-01-13 08:00 | 2015-01-14 16:00 | N | N | point trotter phase 2 ptB salvage | Line
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2015-01-13 08:00 | 2015-01-15 16:00 | N | N | inspect insulators and install dampers | Line |  | inspect insulators and install dampers | Restricts Generation, Creates Radial Feeds
ATCO | 7L129 (526s Buffalo Creek - 918s Bauer) | 2015-01-13 08:30 | 2015-01-13 16:00 | N | Y | replace vacuum bottles on 7L129D3 | Line |  | Replace Vacuum bottles on 7L129D3 | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 8.1TR (ENMAX 8),8.2TR (ENMAX 8) | 2015-01-13 09:00 | 2015-01-13 17:00 | N | N | maintenance | Transformer
ALTALINK | 739L (432s Carvel - 739L214B),432s 739 (432s Carvel) | 2015-01-13 10:00 | 2015-01-13 12:00 | N | N | emergency work: low SF6 | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
AESO-SC | EMS | 2015-01-13 10:30 | 2015-01-13 16:30 | N | N | system 2 Microsoft patching | SCInternal |  |  | For Information Only
ENMAX | 15.2TR (ENMAX 15),15.62L (ENMAX 15 - ENMAX 16) | 2015-01-14 08:00 | 2015-01-15 16:00 | N | N | maintenance and doble | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
STROBE | 239s 25CB1 (239s Castle River) | 2015-01-14 08:00 | 2015-01-14 17:00 | N | N | emergency retermination | Circuit Breaker |  |  | For Information Only
ENMAX | 8.3TR (ENMAX 8),8.4TR (ENMAX 8) | 2015-01-14 09:00 | 2015-01-15 17:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK, TRANSALTA | 229s T1 (229s Glenwood),162L (415s Drywood - 229s Glenwood) | 2015-01-14 09:00 | 2015-01-14 15:00 | N | N | install new slack spans into 229s on 162L. | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 6L57 (735s Swan River - 727s Kinuso),735s 602 (735s Swan River) | 2015-01-14 10:00 | 2015-01-21 14:00 | N | Y | transfer 602 controls to new building | Circuit Breaker, Line |  | Transfer 602 controls to new building, 6L97 and 6L96 will remain in service | Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2015-01-15 08:00 | 2015-01-15 16:00 | N | N | Urgent repair structure 19. If structure fails, line could drop on road | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 924L (102s Langdon - 356s Milo),356s 852 (356s Milo),356s 952 (356s Milo) | 2015-01-15 18:00 | 2015-01-17 17:00 | N | Y | Install WATL RAS protection into CT circuits and test breaker & airbreak status to protection. | Line, Circuit Breaker |  |  | 240 kV, Overload
ENMAX | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2015-01-16 08:00 | 2015-01-16 16:00 | N | N | SW 82, 86 maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.83L (ENMAX 1 - ENMAX 8) | 2015-01-16 08:00 | 2015-01-16 16:00 | N | N | maintenance | Line |  |  | For Information Only
IMPERIALOIL | Imperial Oil | 2015-01-17 08:00 | 2015-05-15 16:00 | N | N | Kearl behind the fence generator: 86 MW. Refer to the Op Plan binder for the commissioning plan. | Unit
AESO-SC | BCH Generator Testing | 2015-01-17 08:00 | 2015-01-19 16:00 | N | N | BCH MCA G5 commission test | SCInternal |  |  | Pre-Condition
ATCO | 774s 702T (774s Monitor) | 2015-01-17 08:00 | 2015-01-23 16:00 | N | N | commissioning - ISD: Jan 21 | Transformer |  |  | For Information Only
ALTALINK | 172L (370s North Lethbridge - 172L1238) | 2015-01-18 07:30 | 2015-01-29 17:00 | N | N | line re-conductor - str 1201A - str 1206 | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199L (347s Fox Creek - 741s Fox Creek) | 2015-01-18 08:00 | 2015-01-19 17:30 | N | Y | line maintenance | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Hardisty H726 (Hardisty Epcor) | 2015-01-19 07:00 | 2015-01-19 18:00 | N | N | protection maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 150L (42s Sarcee - 150L47) | 2015-01-19 07:30 | 2015-01-30 17:30 | N | N | line maintenance - structure replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2015-01-19 08:00 | 2015-01-23 16:00 | N | N | CT upgrades - City of Lethbridge | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 580s 637 (580s Sylvan Lake) | 2015-01-19 08:00 | 2015-03-15 13:00 | N | N | protection work on 580s637 | Circuit Breaker
ALTALINK | 574s T3 (574s Nilrem) | 2015-01-19 08:00 | 2015-01-19 17:00 | N | N | install grounds, test CTs within TX 18885 | Transformer |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1),ENMAX 1 B138-6A0 (ENMAX 1) | 2015-01-19 08:00 | 2015-01-21 16:00 | N | N | difficult to operate 6a101 (adjustments needed) | Transformer, Circuit Breaker
ALTALINK | 80L (194s South Red Deer - 217s North Red Deer),217s 80X (217s North Red Deer) | 2015-01-19 08:00 | 2015-03-15 13:00 | N | N | protection work on 217s80X | Line, Circuit Breaker
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky) | 2015-01-19 08:00 | 2015-01-22 17:00 | N | N | install line vibration dampers / line inspection and tighten hardware | Line |  | Install Line Vibration Dampers / line inspection and Tighten hardware | Pre-Condition
ALTALINK, AESO | 595s677 (595s Spruce Grove),677L (305s Acheson  595s Spruce Grove) | 2015-01-19 09:00 | 2015-01-19 16:00 | N | N | complete further investigation (trouble-shooting) related to the breaker trouble/fail issues | Circuit Recloser, Line |  |  | Overload, Over/Under Voltage
ALTALINK | 526L (268s Whitecourt - 526DL185),268s 69 (268s Whitecourt) | 2015-01-19 09:00 | 2015-01-19 16:00 | N | N | protection testing | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2015-01-19 09:00 | 2015-01-19 13:00 | N | N | repair damaged overhead shield wire | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2) | 2015-01-19 10:00 | 2015-01-19 16:30 | N | N | 7L03 Str. 80 from line mitigation to be changed out double circuit 25 KV, replace arms with post insulators | Line |  | 7L03 Str. 80 from line mitigation to be changed out double circuit 25 KV. Replace arms with post insulators
ALTALINK | 275s 5 (275s Jenner) | 2015-01-19 12:00 | 2015-01-19 17:00 | N | Y | breaker repair (spring charge fail alarm) | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 840S McNeill Station | 2015-01-19 13:00 | 2015-02-01 15:00 | N | N | 15 MW to 150 MW import/export tests | Station |  | TEST THE TRANSFER CAPABILITY | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),Hardisty H725 (Hardisty Epcor) | 2015-01-20 07:00 | 2015-01-20 12:00 | N | N | protection maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 526L (526L367 - 526L418) | 2015-01-20 08:00 | 2015-02-20 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
WINDPOWER | 205s 452 (205s Castle Rock),205s Castle Rock Ridge 240 kV Bus 2 | 2015-01-20 09:00 | 2015-01-21 12:00 | N | Y | installation of MVT1 to 240kV bus 2 | Circuit Breaker, Bus |  |  | 240 kV, For Information Only
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove),595s 712 (595s Spruce Grove) | 2015-01-20 09:00 | 2015-01-20 16:00 | N | N | complete further investigation (trouble-shooting) related to the breaker trouble/fail issues | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH9 (Hardisty - 987s Clover Bar),Hardisty H724 (Hardisty Epcor) | 2015-01-20 12:00 | 2015-01-20 16:00 | N | N | protection maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 41s T11 (41s Medicine Hat) | 2015-01-20 16:30 | 2015-01-23 11:30 | N | N | PT MH69-107 failed. | Transformer
EPCOR | 330P Genesee | 2015-01-21 01:00 | 2015-01-21 05:00 | N | N | telephone system outage | Station |  |  | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2015-01-21 08:00 | 2015-01-21 12:00 | N | N | protection maintenance | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
NPC | NPC2 JL Landry | 2015-01-21 08:00 | 2015-02-06 16:00 | N | N | In service date: Jan 21, 2015. Refer to the Op Plan binder for the commissioning plan. (9 MW) | Unit
ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2015-01-21 08:00 | 2015-01-30 18:00 | N | Y | L to J: stringing into new 1080L ENMAX 25 sub bay. | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 31.3TR (ENMAX 31) | 2015-01-21 08:00 | 2015-01-21 16:00 | N | N | isolate and ground transformer for training purposes | Transformer
EPCOR | Hardisty H723 (Hardisty Epcor) | 2015-01-21 12:00 | 2015-01-21 16:00 | N | N | protection maintenance | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 749s 701 (749s Flyingshot Lake),749s701A (749s Flyingshot Lake) | 2015-01-22 09:00 | 2015-01-22 10:00 | N | N | 701A switch test | Switch, Circuit Breaker |  | Arc horn on 701A looks welded. we require a test and operate permit to attempt to operate the switch and then get the jaw to seat properly BKR 701 must be opened | Contingency Requires Mitigation
AESO-SC | BCH Generator Testing | 2015-01-22 09:00 | 2015-01-23 | N | N | BCH WAX G2 test | SCInternal |  |  | Pre-Condition
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2015-01-24 07:30 | 2015-01-25 17:30 | N | N | line maintenance - structure replacement | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13),22PT138-Z7 (ENMAX 22) | 2015-01-24 08:00 | 2015-01-25 16:00 | N | N | switch & MD maintenance and gas sample | Terminal Equipment, Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
DAISHOWA | 147S Daishowa Plant,147s Daishowa Plant RTU/SCADA | 2015-01-24 08:30 | 2015-01-24 19:30 | N | N | SCADA & ADAMS outage due to switch installation | Station, Terminal Equipment |  |  | Affects Visibility
EPCOR | 330P Genesee | 2015-01-26 01:00 | 2015-01-26 05:00 | N | N | telephone system outage | Station |  |  | For Information Only
EPCOR | Hardisty T1 (Hardisty) | 2015-01-26 07:00 | 2015-10-02 18:00 | N | N | 15kV switchgear at Hardisty is being replaced | Transformer |  |  | For Information Only
Lethbridge | 813L (241s Lethbridge Uplands - 146s Lethbridge MacDonald) | 2015-01-26 08:00 | 2015-01-30 16:00 | N | N | CT upgrades | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1TR (ENMAX 14) | 2015-01-26 08:00 | 2015-01-27 16:00 | N | N | working on low voltage switches | Transformer |  |  | For Information Only
ATCO | 720s 901 (720s Wabasca) | 2015-01-26 10:00 | 2015-01-26 14:00 | N | Y | breaker dashpots need oil | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2015-01-27 07:30 | 2015-01-27 17:00 | N | N | urgent repair | Line |  |  | Restricts Generation
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2015-01-27 08:00 | 2015-01-28 17:00 | N | N | forced outage | Line
ALTALINK | 310p 252 (310p Sundance) | 2015-01-27 08:00 | 2015-01-27 11:00 | N | Y | extend CT secondary circuit to revise metering module | Circuit Breaker |  |  | 240 kV, For Information Only
STROBE | 239s 25CB1 (239s Castle River) | 2015-01-27 09:00 | 2015-01-27 13:00 | N | N | emergency retermination | Circuit Breaker |  |  | For Information Only
ALTALINK | 205s Castle Rock Ridge 240 kV Bus 2 | 2015-01-27 09:00 | 2015-01-27 17:00 | N | Y | removal of MVT1 from 240kV Bus 2 | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 352 (310p Sundance) | 2015-01-27 13:00 | 2015-01-27 16:00 | N | Y | extend CT secondary circuit to revise metering module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 65.2 TR (ENMAX 65),ENMAX 65 240 kV North Bus | 2015-01-28 08:00 | 2015-01-30 18:00 | N | Y | extend existing 1080L GOI to include North bus at ENMAX 65 sub, to allow crew to roll phases on 1080L A-frame | Bus, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 310p 552 (310p Sundance) | 2015-01-28 08:00 | 2015-01-28 11:00 | N | Y | extend CT secondary circuit to rev metering module | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 14.2TR (ENMAX 14) | 2015-01-28 08:00 | 2015-01-29 16:00 | N | N | LV switches at 14 sub SW 10, SW 15, SW 16 & SW 17 | Transformer |  |  | For Information Only
ALTALINK | 310p 652 (310p Sundance) | 2015-01-28 13:00 | 2015-01-28 16:00 | N | Y | extend CT secondary circuit to revise metering module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 987s CGB3 (987s Clover Bar) | 2015-01-29 04:00 | 2015-02-01 16:00 | N | N | G3 motor change out | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 672L (235s Entwistle - 131s Moon Lake) | 2015-01-29 08:00 | 2015-01-29 12:00 | N | N | connecting mobile 475s | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | Enmax 1 B138-5A0 (ENMAX 1) | 2015-01-29 08:00 | 2015-02-17 16:00 | N | N | GIS breaker maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s CK726 (987s Clover Bar) | 2015-01-29 08:00 | 2015-01-29 12:00 | N | N | CK726 relay maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 818s C2 (818s Winefred),818s 17 (818s Winefred) | 2015-01-29 08:00 | 2015-01-29 17:00 | N | N | replace heater and thermostat on 818s17 | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | 987s CC24 (987s Clover Bar) | 2015-01-29 11:59 | 2015-01-29 16:00 | N | N | CC24 relay maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 131s T1 (131s Moon Lake) | 2015-01-29 14:00 | 2015-02-27 17:00 | N | N | station upgrade | Transformer |  |  | For Information Only
EPCOR | 987S Clover Bar 72 kV Bus 1 | 2015-01-30 08:00 | 2015-02-02 16:00 | N | N | offload 72CN10 cable from Clover Bar | Bus |  | offload for G3 Start up. Offload 72CN10 cable from Cloverbar . - Switching needed: open CN723 breaker @ Cloverbar and back feed cable from Namao - - Offload Tx2 at Cloverbar - - Switching needed: transfer all bus sections to Tx1 and open CC721 breaker @ Cloverbar S/S | Creates Radial Feeds, For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2015-01-30 08:00 | 2015-01-30 12:00 | N | N | CK725 relay maintenance | Line |  |  | Creates Radial Feeds, For Information Only
EPCOR | 987s CDS13 (987s Cloverbar) | 2015-01-30 11:59 | 2015-01-30 16:00 | N | N | CC13 relay maintenance | Terminal Equipment |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39),22PT138-Z7 (ENMAX 22) | 2015-01-31 08:00 | 2015-01-31 16:00 | N | N | switch maintenance on 84, 85, 86, 87 & 88. MD maintenance on 22.2TR & 22.3TR at 22s | Line, Transformer, Terminal Equipment |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 454s T2 (454s Buck Lake) | 2015-02-01 07:00 | 2015-02-01 19:00 | N | N | replace HV arrestor | Transformer
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2015-02-01 08:00 | 2015-02-14 18:00 | N | Y | relocate a portion of 911L for 1106/1107L construction. | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ENMAX | 13.1TR (ENMAX 13),13.3TR (ENMAX 13),2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 2 - 2.83L tap),2.83L (ENMAX 13 - 2.83L tap),3.84L (ENMAX 13 - ENMAX 3) | 2015-02-01 08:00 | 2015-02-01 16:00 | N | N | SW 81 maintenance | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2015-02-02 07:00 | 2015-02-02 12:00 | N | N | relay maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 102s SVC (102s Langdon),102s Langdon 240 kV West Bus | 2015-02-02 07:30 | 2015-02-20 18:00 | N | Y | connect SVC to new diameter (102s252 & 102s552) | Bus, Shunts |  |  | 240 kV, Pre-Condition, Limits ATC, Contingency Requires Mitigation
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2015-02-02 08:00 | 2015-02-03 16:00 | N | N | 33.2TR MD, SW 84, 85, 86 maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Lethbridge | 674s Lethbridge Bowron RTU/SCADA | 2015-02-02 08:00 | 2015-02-02 16:00 | N | N | data point upgrades | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2015-02-02 08:00 | 2015-02-06 17:00 | N | Y | line rebuid | Line |  |  | Restricts Generation
ATCO | 7L36 (820s Hangingstone - 2009s Willow Lake) | 2015-02-02 08:00 | 2015-02-05 17:00 | N | N | 2015 climbing inspection 7L36 | Line |  | 2015-Climbing inspection 7L36 WILL REQUIRE A CONTINUOUS GOI FROM FEB 2 TO FEB 5 | Firm Load Loss, Creates Radial Feeds
ATCO | 2060s 701T (2060s Engstrom) | 2015-02-02 08:00 | 2015-02-05 16:00 | N | N | risk low, load transferred to 702T, commissioning for 7L183 addition | Transformer |  | Risk low, Load transferred to 702T , Commisioning for 7L183 addition
ENMAX | 24.2TR (ENMAX 24) | 2015-02-02 08:00 | 2015-02-05 16:00 | N | N | oil leak repairs | Transformer
EPCOR | 987s GB1B (987s Clover Bar) | 2015-02-02 12:00 | 2015-02-02 16:00 | N | N | relay maintenance | Circuit Breaker |  |  | For Information Only
ATCO | 840S McNeill Station | 2015-02-03 | 2015-02-09 23:59 | N | N | trial operations | Station |  |  | For Information Only
ALTALINK | 931L (132s Ware Junction - 28s West Brooks),28s931N (28s West Brooks) | 2015-02-03 08:00 | 2015-02-03 17:00 | N | Y | 28s931N switch adjustment | Line, Switch |  |  | 240 kV
STROBE | 239s 25CB1 (239s Castle River) | 2015-02-03 08:00 | 2015-02-03 17:00 | N | N | emergency maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 225L (385s Spring Coulee - 225s Magrath) | 2015-02-03 08:00 | 2015-02-03 17:00 | N | N | install new risers to LA's | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood),700L (422s Westwood - 746L tap) | 2015-02-03 09:00 | 2015-02-03 17:00 | N | N | PT inspection at 422s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 428s T1 (428s Namaka) | 2015-02-04 07:00 | 2015-02-05 17:00 | N | N | 25kV switch adjustment and SS1 upgrade | Transformer |  |  | For Information Only
ALTALINK | 807L (233s Beamer - 807L tap),233s 807X (233s Beamer) | 2015-02-04 07:30 | 2015-02-05 18:00 | N | N | installing poles near 807L | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ALTALINK | 225L (67s Stirling - 225AL tap),225L (225s Magrath - 225AL tap) | 2015-02-04 08:00 | 2015-02-04 17:00 | N | N | install new risers to LA's | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2015-02-04 08:00 | 2015-02-04 12:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2015-02-04 08:00 | 2015-02-04 16:00 | N | N | switch maintenance | Transformer, Line |  |  | For Information Only
ALTALINK | 74s C2 (74s Janet),74s 54 (74s Janet) | 2015-02-04 08:30 | 2015-02-04 17:00 | N | Y | breaker maintenance | Circuit Breaker, Shunts |  |  | Limits ATC
ALTALINK | 250p22 (250p Bighorn) | 2015-02-04 12:00 | 2015-02-04 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | Hardisty H726 (Hardisty Epcor) | 2015-02-05 07:00 | 2015-02-05 16:00 | N | N | DC panel work | Circuit Breaker
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2015-02-05 07:00 | 2015-02-09 18:00 | N | Y | string new 13L50 line over 9L59 between towers 882 & 883 @ NW 18-34-13-4 | Line |  | String new 13L50 line over 9L59 Between Towers 882 & 883 @ NW 18-34-13-4. Work cannot be done using live line techniques due to clearance limitations AESO Derates may apply @ Sheerness depending on system and wind conditions | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2015-02-05 08:00 | 2015-03-25 18:00 | N | N | line maintenance - rebuild | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2015-02-05 12:00 | 2015-04-03 16:00 | N | Y | installation of receiving structure for new 1107L, new 65B240-D133, SW 137, SW 138, 65PT240-1107 & 65MD240-1107 | Circuit Breaker |  |  | 240 kV
ATCO | 2060s 702T (2060s Engstrom) | 2015-02-06 08:00 | 2015-02-09 16:00 | N | N | load will be transferred to 701T, commissioning for 7L183 addition | Transformer |  | Load will be transferred to 701T, Commissioning for 7L183 addition
MONTANA | Great Falls Switchyard (NorthWestern Energy) - Marias (MATL) | 2015-02-06 09:00 | 2015-02-06 13:00 | N | N | Emergency replacement of MATL line metering unit | Line |  |  | 240 kV, Limits ATC
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2015-02-07 07:00 | 2015-02-07 19:00 | N | N | emergency line washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38) | 2015-02-07 08:00 | 2015-02-07 16:00 | N | N | switch maintenance on 85 @ 39s, doble 39B138-38.83 (weather permitting) | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987S Clover Bar 72 kV Bus 4,987s CDS12 (987s Clover Bar) | 2015-02-07 08:00 | 2015-02-07 14:00 | N | N | CDS12 emergency repair - ASAP | Line, Bus, Switch |  |  | Pre-Condition, Restricts Generation
ALTALINK | 901L (63s Red Deer - 901AL tap),901L (74s Janet - 901AL tap) | 2015-02-08 07:30 | 2015-02-08 12:00 | N | Y | Install helicopter aerial markers on 901L near the 1325L crossing - WATL | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2015-02-08 12:30 | 2015-02-08 17:00 | N | Y | install helicopter aerial markers on 925L near the 1325L crossing - WATL | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 708L (233s Beamer - 708L88N),233s 708X (233s Beamer) | 2015-02-09 07:00 | 2015-02-10 17:00 | N | N | work on new 942L/1061L & 807L in vicinity - NWR | Circuit Breaker, Line |  | Customer wants breaker open to eliminate risk to plant. | Overload, Over/Under Voltage
ENMAX | ENMAX 9,2.81L (ENMAX 2 - ENMAX 9),ENMAX 9 RTU/SCADA | 2015-02-09 08:00 | 2015-02-20 16:00 | N | N | ECTP 2s. Salvage structure's #4- 2s, Swap AIS - GIS. Breaker inspection (9s) | Station, Terminal Equipment, Line |  |  | Pre-Condition, Affects Visibility
ATCO | 770s 506C (770s Three Hills),770s 701T (770s Three Hills) | 2015-02-09 08:00 | 2015-02-13 16:00 | N | N | replace 501TD, Breaker 504 and 505 | Shunts, Transformer |  | Replace 501TD, 701T Load will be transferred to 702T, Breaker 504 and 505 load will be transferred to breaker 503, 5MVAR Cap 506C will be unavailable during outage. -------- Load Transfer -------- 770S 5L513 Peak Load = 4.21 MVA 770S 5L278 Peak Load = 4.22 MVA 770S 5L170 Peak Load = 2.98 MVA 770S 5L513 Relay Settings: 13.86 MVA 770S 5L278 Relay Settings: 13.8 MVA 770S 5L170 Relay Settings: 13.8 MVA ADJUST ON SITE AS REQD -------- Load Transfer -------- | For Information Only
ENMAX | 5.5TR (ENMAX 5) | 2015-02-09 08:00 | 2015-07-06 16:00 | N | N | transformer replacement | Transformer
ENMAX | 15.1TR (ENMAX 15) | 2015-02-09 08:00 | 2015-02-10 16:00 | N | N | LV switches @ 15 sub SW 10, SW 11, SW 12, SW 13 & SW 14 - 15.1TR Transformer maintenance | Transformer |  |  | For Information Only
ENMAX | Enmax 8 B138-3A0 (ENMAX 8) | 2015-02-09 08:00 | 2015-02-12 16:00 | N | N | repair hydraulic pump (excessive operations) | Circuit Breaker
ALTALINK | 727L (65s High River - 727L39S) | 2015-02-09 08:00 | 2015-02-14 18:00 | N | N | Foothills 138kV: rebuild portion of 727L and new 434L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2015-02-09 08:00 | 2015-02-13 17:00 | N | Y | replace structures | Line |  |  | Restricts Generation
ENMAX | 20.1TR (ENMAX 20) | 2015-02-09 08:00 | 2015-02-09 16:00 | N | N | fan repair | Transformer
AESO-SC | CROW | 2015-02-09 10:00 | 2015-02-09 11:00 | N | N | CROW will be unavailable for 20-30 minutes, during the 1 hour change window. | SCInternal |  |  | For Information Only
ALTALINK | 574s T3 (574s Nilrem) | 2015-02-09 11:00 | 2015-02-10 16:00 | N | N | install grounds, test CTs within TX 18885 | Transformer
ATCO | 9L32 (941s Bitumount - 957s McClelland) | 2015-02-10 07:00 | 2015-02-20 18:00 | N | Y | line move for Fort Hills Project | Line |  | LINE MOVE FOR FORT HILLS PROJECT (55578) / The OPGW will be re-spliced at the same time (and another route for telecom/Kearl data traffic will be temporarily provided). The line Crew will also require a GOI on 9L32 Feb 14 7:00-18:00 for a high load move. | 240 kV, Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (20s Ghost - 150L46),20s 150 (20s Ghost) | 2015-02-10 08:00 | 2015-02-10 09:00 | N | N | 150L TPR circuit cutover to MPLS network | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 391s T1 (391s Balzac),391s9 (391s Balzac) | 2015-02-10 08:00 | 2015-02-10 17:00 | N | N | Transformer & 25kV Breaker maintenance | Circuit Breaker, Transformer
ALTALINK | 223s T3 (223s Strome) | 2015-02-10 08:00 | 2015-02-10 17:00 | N | N | close open points on T3 | Transformer
ALTALINK | 293s T1 (293s Bernese) | 2015-02-10 08:00 | 2015-02-18 13:00 | N | N | complete bus connection to Enbridge and all interface testing | Transformer |  |  | For Information Only
ALTALINK | 244s Bowmanton T1,244s T2 (244s Bowmanton) | 2015-02-10 08:00 | 2015-03-18 17:00 | N | N | Warranty Repairs | Transformer |  |  | 240 kV
ENMAX | 65.1 TR (ENMAX 65) | 2015-02-10 08:00 | 2015-02-10 16:00 | N | Y | oil leak repair initial inspection by manufacturer | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2015-02-10 08:30 | 2015-02-10 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | Limits ATC
ALTALINK | 719L (263s Strachan - 719L259C),263s 719X (263s Strachan) | 2015-02-10 10:00 | 2015-02-12 17:00 | N | N | replace CT modify str. | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 859L (20s Ghost - T793s Horse Creek),20s 859E (20s Ghost) | 2015-02-10 11:00 | 2015-02-10 12:00 | N | N | 859L TPR circuit cutover to MPLS network | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.2TR (ENMAX 15) | 2015-02-11 08:00 | 2015-02-12 16:00 | N | N | switch maintenance | Transformer
ATCO, IMPERIALOIL | 7L105 (837s Mahihkan - 909s Mahno) | 2015-02-12 09:00 | 2015-02-12 18:00 | N | N | emergency outage | Line |  |  | Restricts Generation
ATCO | 9L36 (826s Marguerite Lake - 825s Whitefish Lake) | 2015-02-12 10:00 | 2015-02-12 12:00 | N | Y | need to wire and test 52 contacts on 907 Breaker, 908 Breaker, and 9L36D1 (89 contact) | Line |  | This work is to be done in conjunction to the CSP 2-31474 Will require a test and operate to: Need to wire and test 52 contacts on 907 Bkr, 908Bkr, and 9L36D1 (89 contact) 2 Will not require to do any work on the HV side so do not require a GOI. 9L36 will be out of service for duration of the work. So marguerite lake will only have the one 240KV Line in service (9L37), | 240 kV, Over/Under Voltage
ALTALINK | 223s T3 (223s Strome) | 2015-02-12 11:00 | 2015-02-12 12:00 | N | N | verify trip signal from new NGR relay | Transformer |  |  | For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2015-02-12 11:00 | 2015-02-12 12:00 | N | N | emergency wash due to tracking | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2015-02-12 14:00 | 2015-02-12 18:00 | N | N | emergency wash due to tracking | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 900L (63s Red Deer - 17s Benalto) | 2015-02-15 07:30 | 2015-02-15 12:00 | N | Y | install helicopter aerial markers on 900L near the 1325L crossing - WATL | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ALTALINK | 727L (74s Janet - 1140s Temp) | 2015-02-15 08:00 | 2015-02-15 18:00 | N | N | L to J: setting monopole deadends in close proximity to 727L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2015-02-15 13:00 | 2015-02-15 17:00 | N | Y | install helicopter aerial markers on 190L near the 1325L crossing - WATL | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
SUNCOR | 226s 52_F1 (226s Garden City) | 2015-02-15 16:15 | 2015-02-15 19:00 | N | N | cable splice fault | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 727L (65s High River - 727L39S) | 2015-02-16 08:00 | 2015-02-25 18:00 | N | N | rebuild portion of 727L and new 434L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 33.1TR (ENMAX 33) | 2015-02-16 08:00 | 2015-02-16 12:00 | N | N | 138 kV bus differential upgrade | Transformer |  |  | For Information Only
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2015-02-16 08:00 | 2015-02-16 12:00 | N | Y | Install helicopter aerial markers on 190L near the 1325L crossing - WATL | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ATCO | 770s 703T (770s Three Hills) | 2015-02-16 08:00 | 2015-02-20 16:00 | N | N | replace switch 503TD | Transformer |  |  | For Information Only
ENMAX | 33.2TR (ENMAX 33) | 2015-02-16 12:00 | 2015-02-16 16:00 | N | N | 138 kV bus differential upgrade | Transformer |  |  | For Information Only
EPCOR | 803s T1 (803s Lambton) | 2015-02-17 07:00 | 2015-02-17 18:00 | N | Y | inspection | Transformer |  |  | 240 kV, For Information Only
AESO-SC | Cargill Camrose | 2015-02-17 08:00 | 2015-03-18 16:00 | N | N | Behind The Fence. Gross installed capacity is estimated to be 10.35MW. The net plant output capacity is estimated at 3 MW. Cargill will export up to 4.9MW onto the grid. | Unit
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan),263s 870E (263s Strachan) | 2015-02-17 08:00 | 2015-02-19 17:00 | N | N | replace CT | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2015-02-17 08:00 | 2015-02-17 12:00 | N | N | 138 kV bus differential upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 883L (331s Ponoka - 429s Nelson Lake) | 2015-02-17 08:00 | 2015-02-18 19:00 | N | N | install foundations, under 883L at new 288s | Line |  |  | Firm Load Loss, For Information Only
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2015-02-17 09:00 | 2015-02-27 17:30 | N | Y | line rebuild | Line |  |  | Restricts Generation
ALTALINK | 71s 552 (71s Lamoureux) | 2015-02-17 09:00 | 2015-02-17 17:00 | N | N | CT inspection/repair | Circuit Breaker |  |  | Contingency Requires Mitigation
AESO-SC | DT | 2015-02-17 10:00 | 2015-02-17 11:00 | N | N | Implement ADaMS enhancements to incorporate new business rules and improve the application usability. | SCInternal |  |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc) | 2015-02-17 10:00 | 2015-02-18 17:00 | N | N | breaker maintenance & switch repair | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 711s 601T (711s Willingdon) | 2015-02-17 10:00 | 2015-02-19 15:00 | N | N | investigate and repair leaks as required | Transformer |  | 711S - 601T Leak Repair Isolate, investigate and repair leaks as required. Complete 501 Breaker PM at same time 602T and Breaker 502 will carry all of the load for the duration of the work 500D1 Station Service will have to be transfered to the other 25kV bus for the duration of work. -------- Load Transfer -------- 711S 5L344 Peak Load = 3 MVA 711S 5L42 Peak Load = 3 MVA 711S 5L344 Relay Settings :C-09 RELAY 8.66 MVA 711S 5L42 Relay Settings: C-09 RELAY 8.7 MVA -------- Load Transfer -------- | Pre-Condition, For Information Only
ALTALINK | 738L (38s East Edmonton - 738AL1),38s 738W (38s East Edmonton) | 2015-02-17 10:00 | 2015-02-17 15:00 | N | N | run new DC supply to breaker 2552 | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | CROW | 2015-02-17 11:00 | 2015-02-17 12:00 | N | N | CROW Prod Migration from SDC to PDC | SCInternal |  |  | For Information Only
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2015-02-17 12:00 | 2015-02-17 16:00 | N | N | bus differential upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7LA53 (969s Lindbergh - 7LA53D1) | 2015-02-18 08:00 | 2015-02-18 16:00 | N | N | line raise for customer Pengrowth | Line |  | Line Raise for Customer Pengrowth. / ATCO Distribution has coordinated this outage with the customers at 969S Lindbergh.
AESO-SC | Phone Outage | 2015-02-18 08:00 | 2015-02-18 19:30 | N | N | DOW Chemical Phone Outage | SCInternal |  |  | For Information Only
ALTALINK | 42s C2 (42s Sarcee),42s 74 (42s Sarcee) | 2015-02-18 08:00 | 2015-02-18 17:00 | N | N | unbalance alarm (emergency repair) | Circuit Breaker, Shunts |  |  | Limits ATC
ATCO | 917s 706 (917s Horse River) | 2015-02-18 08:00 | 2015-02-18 17:00 | N | N | emergency outage on 706C capacitor to refill SF6 | Circuit Breaker |  |  | For Information Only
ALTALINK | 478s T1 (478s Tucuman) | 2015-02-18 08:00 | 2015-02-18 12:00 | N | N | breaker maintenance | Transformer
ENMAX | 15.2TR (ENMAX 15) | 2015-02-18 08:00 | 2015-02-19 16:00 | N | N | transformer maintenance | Transformer
ENMAX | ENMAX 25 B240-D138 (ENMAX 25) | 2015-02-18 08:00 | 2015-02-19 16:00 | N | Y | to do tests on it to ensure integrity | Circuit Breaker |  |  | 240 kV, For Information Only
TRANSALTA | 239s T1 (239s Castle River),239s 25CB1 (239s Castle River) | 2015-02-18 10:00 | 2015-02-18 14:00 | N | N | circuit breaker leveling | Circuit Breaker, Transformer |  | relevel circuit breaker, due to frost issues | Affects Visibility
ALTALINK | 293s T2 (293s Bernese) | 2015-02-18 14:00 | 2015-02-24 16:00 | N | N | complete bus connection to Enbridge and all interface testing | Transformer |  |  | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),Hardisty H725 (Hardisty Epcor) | 2015-02-19 08:00 | 2015-02-19 16:00 | N | N | cable work | Line, Circuit Breaker |  |  | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2015-02-19 08:00 | 2015-02-19 16:00 | N | N | cable work | Circuit Breaker |  |  | For Information Only
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2015-02-19 08:00 | 2015-02-19 16:00 | N | N | CN723 relay maintenance | Line |  |  | For Information Only
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21),ENMAX 21 60s50 (ENMAX 21) | 2015-02-19 10:00 | 2015-02-19 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2015-02-20 07:00 | 2015-04-03 18:00 | N | N | splice repair | Line |  |  | For Information Only
ENMAX | 5.1TR (ENMAX 5) | 2015-02-20 08:00 | 2015-02-20 16:00 | N | N | Energize new 5.1TR | Transformer
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2015-02-20 08:00 | 2015-02-22 18:00 | N | Y | urgent repair | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 80L (152s Didsbury - 80L194A) | 2015-02-20 08:00 | 2015-02-20 12:00 | N | N | install aerial obstruction markers | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 166L (152s Didsbury - 166L50) | 2015-02-20 13:00 | 2015-02-20 17:00 | N | N | install aerial obstruction markers | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 937L (102s Langdon - 74s Janet) | 2015-02-21 06:30 | 2015-02-25 18:00 | N | Y | L to J: Move 937L from existing structure 48 to temporarily hold 937L on new 1064L55 to allow for later outages on 936L to configure 936/937L into new orientation with 1064/1065L. | Line |  |  | 240 kV, Limits ATC
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-02-21 07:00 | 2015-02-21 12:00 | N | N | line washing | Line |  |  | Creates Radial Feeds
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2015-02-21 08:00 | 2015-02-22 16:00 | N | Y | RTU Replacement Project | Line |  |  | Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2015-02-21 08:00 | 2015-02-21 12:00 | N | N | 13B13-11.81 SF6 Gas Sample | Line
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-02-21 12:00 | 2015-02-21 17:00 | N | N | line washing | Line |  |  | Creates Radial Feeds
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2015-02-21 12:00 | 2015-02-21 16:00 | N | N | SF6 gas sample 6B138-6.82 | Line |  |  | Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2015-02-22 07:00 | 2015-02-22 10:00 | N | N | pothead washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | RL1 (848s Ruth Lake - D05 Syncrude) | 2015-02-22 08:00 | 2015-02-26 12:00 | N | Y | CT ratio upgrade | Line |  |  | 240 kV, Pre-Condition
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13),22PT138-Z7 (ENMAX 22) | 2015-02-22 08:00 | 2015-02-22 12:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39),22PT138-Z7 (ENMAX 22) | 2015-02-22 12:00 | 2015-02-22 16:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 33,33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2015-02-23 08:00 | 2015-02-23 12:00 | N | N | substation washing | Line, Transformer, Station |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 216s T3 (216s Knightsbridge) | 2015-02-23 08:00 | 2015-02-23 17:00 | N | N | repair bird coverup on switch 216s39 | Transformer |  |  | For Information Only
ATCO | 802s 703T (802s Michichi Creek) | 2015-02-23 08:00 | 2015-03-01 16:00 | N | N | replace MOD 503TD, 703T load will be transferred to 702T | Transformer |  | Replace MOD 503TD, 703T load will be transferred to 702T -------- Load Transfer Steps 2&10-------- 802S 5L160 Peak Load = 3.54 MVA 802S 5L37 Peak Load = 4.26 MVA 802S 5L53 Peak Load = 7.35 MVA 802S 5L350 Peak Load = 2.45 MVA 802S 5L160 Relay Settings: 27.02 MVA 802S 5L37 Relay Settings: 15.59 MVA 802S 5L53 Relay Settings: 18.19 MVA 802S 5L350 Relay Settings: 15.59 MVA Adjust on site as reqd -------- Load Transfer -------- -------- Load Transfer Step 5-------- 802S 5L160 Peak Load = 3.54 MVA 802S 5L160 Relay Settings: 27.02 MVA 802S 5L37 Relay Settings: 15.59 MVA Adjust on site as reqd -------- Load Transfer --------
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),34B69-16.60 (ENMAX 34) | 2015-02-23 08:00 | 2015-02-24 16:00 | N | N | 34s breaker fail modification | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 836s 626T (836s Steep Bank) | 2015-02-23 08:30 | 2015-02-23 16:30 | N | N | relay testing | Transformer |  | 87T / 626T (Siemens 7UT5135)
ATCO | 7L194 (875s Algar - 2009s Willow Lake) | 2015-02-23 09:00 | 2015-02-26 17:00 | N | N | climbing patrol, 875s will be radial fed via 7L38 from 917s Horse River | Line |  | Climbing Patrol, 875s will be radial fed via 7L38 from 917s Horse Rv | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 854L (397s Benbow - 854L229) | 2015-02-23 10:00 | 2015-02-25 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 33,33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2015-02-23 12:01 | 2015-02-23 16:00 | N | N | Substation washing | Line, Transformer, Station |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1),20PT138-Z31 (ENMAX 20) | 2015-02-24 08:00 | 2015-02-24 12:00 | N | N | substation washing | Transformer, Line, Terminal Equipment |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 447s T2 (447s Enchant) | 2015-02-24 08:00 | 2015-02-24 16:00 | N | N | replace HV arrestor | Transformer
ATCO | 836s 623T (836s Steep Bank),836s 624T (836s Steep Bank) | 2015-02-24 08:30 | 2015-02-24 16:30 | N | N | relay testing | Transformer |  | 87T / 623T (Siemens 7UT5135) 87T / 624T (Siemens 7UT5135) | For Information Only
ALTALINK | 56L (245s Seebe - 20s Ghost) | 2015-02-24 09:00 | 2015-02-24 17:00 | N | N | 20s56 138kV breaker maintenance | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 650s SVC (650s Hansman Lake) | 2015-02-24 09:00 | 2015-02-25 17:00 | N | Y | repair coolant leak on cooling towers | Shunts |  |  | 240 kV
ATCO | 7L61 (780s Lubicon - 796s Nipisi) | 2015-02-24 09:15 | 2015-02-24 16:15 | N | N | line maintenance | Line |  | Line is out of service under permit 2-31427 at Nipisi for 701TCS replacement.
ENMAX | 20.3TR (ENMAX 20),20PT138-Z31 (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2015-02-24 12:00 | 2015-02-24 16:00 | N | N | substation washing | Transformer, Terminal Equipment, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s 152 (63s Red Deer) | 2015-02-25 08:00 | 2015-02-25 10:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34),34B69-21.61 (ENMAX 34) | 2015-02-25 08:00 | 2015-02-26 16:00 | N | N | breaker fail modification | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47) | 2015-02-25 08:00 | 2015-02-25 16:00 | N | N | substation washing | Transformer, Line |  |  | For Information Only
ENMAX | 33.1TR (ENMAX 33) | 2015-02-25 08:00 | 2015-02-28 16:00 | N | N | bus differential upgrade | Transformer |  |  | For Information Only
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2015-02-25 08:00 | 2015-03-03 16:00 | N | N | Burnco re-route | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (20s Ghost - 80L193A),20s 80 (20s Ghost) | 2015-02-25 09:00 | 2015-02-25 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 217s C1 (217s North Red Deer),217s 652 (217s North Red Deer) | 2015-02-25 09:00 | 2015-02-25 17:00 | N | N | breaker maintenance | Shunts, Switch |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky) | 2015-02-25 10:00 | 2015-02-25 17:00 | N | Y | to change out pump | Shunts |  | Shut down SVC to change out pump. | Pre-Condition
ALTALINK | 63s 252 (63s Red Deer) | 2015-02-25 10:01 | 2015-02-25 12:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 63s 452 (63s Red Deer) | 2015-02-25 13:00 | 2015-02-25 15:00 | N | Y | breaker trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 62s12 (62s Brazeau) | 2015-02-25 23:00 | 2015-02-26 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s11 (62s Brazeau) | 2015-02-26 03:00 | 2015-02-26 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 155s T2 (155s Blackmud) | 2015-02-26 08:00 | 2015-02-26 12:00 | N | N | breaker maintenance | Transformer
ALTALINK | 150L (20s Ghost - 150L46),20s 150 (20s Ghost) | 2015-02-26 09:00 | 2015-02-26 17:00 | N | N | 138kV Breaker Maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO, ALTALINK | 9L960 (13s Deerland - 825s Whitefish Lake),13s 1652 (13s Deerland),13s 1752 (13s Deerland) | 2015-02-26 09:00 | 2015-02-26 13:00 | N | Y | This work is to be done in conjunction with 9L960 Quadrahmo replacement and relay Test and operate | Line, Circuit Breaker |  | This work is to be done in conjunction with CSP 2-31467 825s 9L960 Quadrahmo replacement T&O Will require a test and operate to: Need to wire and test 52 contacts on 901 Bkr, 902Bkr, and 9L960D1. Will not require to do any work on the HV side so do not require a GOI. 9L960 and the 825S Loop feed ability will be out for the duration of the work. | 240 kV, Pre-Condition, Overload
ALTALINK | 854L (39s Bickerdike - 854L230) | 2015-02-26 10:00 | 2015-02-27 17:00 | N | N | Line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
Syncrude | RL2 (848s Ruth Lake - D05 Syncrude) | 2015-02-26 12:30 | 2015-03-02 18:00 | N | Y | CT ratio upgrade | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 368s T1 (368s Burdett) | 2015-02-26 13:00 | 2015-02-26 16:00 | N | N | oil leak repair | Transformer
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-02-27 07:00 | 2015-02-27 12:00 | N | N | Line Washing | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2015-02-27 08:00 | 2015-02-27 12:00 | N | N | substation washing | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 672L (235s Entwistle - 131s Moon Lake) | 2015-02-27 12:00 | 2015-02-27 16:00 | N | N | disconnect mobile 475s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2015-02-27 12:00 | 2015-02-27 16:00 | N | Y | substation washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-02-27 12:01 | 2015-02-27 17:00 | N | N | line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2015-02-28 08:00 | 2015-02-28 16:00 | N | N | SW 91, 92 & 65MD138-26.83 maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s C2 (83s Taber),172L (83s Taber - 172L944A),610L (336s Fincastle - 83s Taber),83s Taber 138kV West Bus | 2015-02-28 08:00 | 2015-03-01 17:00 | N | Y | replace PT and copper risers on bus side on 83s610 | Shunts, Line, Bus |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-03-01 07:00 | 2015-03-02 17:00 | N | N | spring line washing, lane closure needed | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33) | 2015-03-01 08:00 | 2015-03-03 16:00 | N | N | 138 kV bus differential upgrade, CT, bus differential & auto switching commissioning | Transformer
TRANSALTAW, ALTALINK, VISIONREQ | 354s DVAR1 (354s Summerview),354s DVAR2 (354s Summerview),528s TDVAR1 (528s Blue Trail Wind Farm),528s TDVAR2 (528s Blue Trail Wind Farm),528s TDVAR3 (528s Blue Trail Wind Farm),418s Ardenville DVAr | 2015-03-01 08:00 | 2015-03-31 16:00 | N | Y | minor filter repalcement/maintenance | Shunts, Transformer |  |  | For Information Only
ENMAX | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2015-03-01 08:00 | 2015-03-01 12:00 | N | N | spring substation washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2015-03-01 12:00 | 2015-03-01 16:00 | N | N | spring substation washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-03-02 07:00 | 2015-03-06 18:00 | N | N | FATD - NFTP: stringing of the north side of the new triple circuit 1106L ,1107L & 850L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 9L57 (888s Dover - 939s Livock) | 2015-03-02 07:00 | 2015-03-09 17:30 | N | Y | connect 960S Birchwood to 240kV system (9L57/9L74 in/out) and commission new line protection settings at Livock and Dover, on return to normal 9L57 will be split into 9L57 and new line 9L74 | Line |  | Connect 960S Birchwood to 240kV system (9L57/9L74 in/out) and commission new line protection settings at Livock and Dover. On return to normal 9L57 will be split into 9L57 and new line 9L74. | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK, ENMAX | 918L (17s Benalto - 162s Beddington),162s 240-RB132 (162s Beddington),162s 240-133 (162s Beddington) | 2015-03-02 07:30 | 2015-03-02 16:00 | N | Y | switch maintenance on SW 134 & 135, MD maintenance on 162MD240-918L | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia) | 2015-03-02 08:00 | 2015-03-08 17:00 | N | Y | new distance protection upgrade and commissioning 11 -D - 057, 58, & 60 | Line |  |  | 240 kV
EPCOR | 557s T1 (557s Castle Downs) | 2015-03-02 08:00 | 2015-03-02 12:00 | N | Y | upgrade power supply | Transformer |  |  | 240 kV, For Information Only
ATCO | 960S Birchwood Creek | 2015-03-02 08:00 | 2015-03-09 17:00 | N | N | In service date: March 9, 2015 | Station |  |  | For Information Only
ENMAX | 162.4TR (ENMAX 162 Beddington) | 2015-03-02 08:00 | 2015-03-14 16:00 | N | N | repair SF6 leak in 25 kV switchgear, deficiencies on 162.4TR | Transformer
ENMAX | 832L (ENMAX 10 - ENMAX 12) | 2015-03-02 08:00 | 2015-03-04 16:00 | N | N | remove scaffolding from 10.1TR | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2015-03-02 08:00 | 2015-03-02 17:30 | N | N | Helicopter marker cones | Line |  |  | Restricts Generation
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2015-03-02 08:00 | 2015-03-02 16:00 | N | N | bushing Inspection | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 83s C2 (83s Taber),83s 67 (83s Taber) | 2015-03-02 10:00 | 2015-03-02 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
EPCOR | 557s T2 (557s Castle Downs) | 2015-03-02 12:01 | 2015-03-02 18:00 | N | Y | upgrade power supply | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2015-03-02 13:00 | 2015-03-02 17:00 | N | N | replace rotten crossarm | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 121s T2 (121s Brooks),795L (121s Brooks - 421s Hays),827L (121s Brooks - 28s West Brooks),121s Brooks 138kV South Bus | 2015-03-03 08:00 | 2015-03-05 17:00 | N | N | 138kV switch replacement | Transformer, Line, Bus |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.3TR (ENMAX 9) | 2015-03-03 08:00 | 2015-03-03 16:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ATCO | 836s 626T (836s Steep Bank),836s 630 (836s Steepbank) | 2015-03-03 08:30 | 2015-03-03 17:00 | N | N | relay testing | Transformer, Circuit Breaker |  | 95 / 630 (SEL 2BFR) 59N / 626T (Basler)
ALTALINK | 835L (384s Keystone - 835L tap),384s 835X (384s Keystone) | 2015-03-03 09:00 | 2015-03-03 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2015-03-03 10:00 | 2015-03-06 17:00 | N | Y | line maintenance - crossarm replacement | Line |  |  | Pre-Condition, Restricts Generation
ALTALINK | 917L (74s Janet - 5s East Calgary) | 2015-03-04 07:00 | 2015-03-07 18:00 | N | Y | L to J: replacing contaminated insulators to new synthetic insulators, in preparation for new 937L bypass | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2015-03-04 07:30 | 2015-03-04 14:00 | N | Y | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32) | 2015-03-04 08:00 | 2015-03-04 16:00 | N | N | spring substation washing | Transformer
ALTALINK | 778L (217s North Red Deer - 87s Gaetz) | 2015-03-04 08:00 | 2015-03-04 17:30 | N | N | install concrete pile | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 54s T3 (54s Fort Saskatchewan),707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan),709L (54s Fort Saskatchewan - 172s Sherritt),54s Fort Saskatchewan 138 kV East Bus | 2015-03-04 08:00 | 2015-03-04 12:00 | N | N | add supervisory controls to 54s24 | Bus, Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.10TR (ENMAX 5) | 2015-03-04 08:00 | 2015-03-04 16:00 | N | N | unshort qualitrol CT wiring | Transformer
ENMAX | 8.3TR (ENMAX 8),8.4TR (ENMAX 8) | 2015-03-04 08:00 | 2015-03-06 16:00 | N | N | switch maintenance on 8-4a01, 8-4a02, 8-4a10, 8-5a1 | Transformer
Saskpower | Sask Power PR903 | 2015-03-04 08:00 | 2015-03-04 12:00 | N | N | add oil to CT | Circuit Breaker |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2015-03-04 08:00 | 2015-03-07 16:00 | N | N | 138 kV bus differential upgrade, CT, bus differential & auto switching commissioning | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L23 (858s Narrows Creek - 796s Nipisi),7L23 (732s Mitsue - 858s Narrows Creek) | 2015-03-04 09:00 | 2015-03-06 18:00 | N | Y | high load move, 7L32D4 repairs | Line |  | High load move, 7L32D4 @ 732s requires repairs thus 144kV ring will be open to provide 7L23 isolation, 7L61 HOP will occur subsequent to this outage, 796s will be radial fed from 7L61, 858s Narrows Ck will be OOS but has generator backup. | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power A1P | 2015-03-04 12:00 | 2015-03-06 15:00 | N | N | replace structures | Line |  |  | For Information Only
ALTALINK | 162L (415s Drywood - 229s Glenwood) | 2015-03-05 07:30 | 2015-03-25 18:00 | N | N | line maintenance - rebuild 164L, string next to and over 162L | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2015-03-05 08:00 | 2015-03-05 16:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ALTALINK | 54s C1 (54s Fort Saskatchewan),54s T1 (54s Fort Saskatchewan),694L (54s Fort Saskatchewan - 422s Westwood),706L (54s Fort Saskatchewan - 706L72B),54s Fort Saskatchewan 138 kV West Bus | 2015-03-05 08:00 | 2015-03-05 12:00 | N | N | add supervisory controls to 54s35 | Transformer, Line, Shunts, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 404S Peace Butte,600L (523s Bullshead - 404s Peace Butte),523s 600 (523s Bullshead) | 2015-03-05 08:00 | 2015-03-05 17:00 | N | N | 138kV breaker maintenance | Line, Station, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 768L (217s North Red Deer - 87s Gaetz) | 2015-03-05 08:00 | 2015-03-06 17:30 | N | N | install concrete piles for 209s | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2015-03-05 09:00 | 2015-03-05 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 767AL (21s Marion - 767L tap),767CL (635s Rose Valley - 767L tap) | 2015-03-05 10:00 | 2015-03-05 14:00 | N | N | open jumpers on str 54 and maintenance on Str 51 | Line
ALTALINK | 767L (310p Sundance - 767L50) | 2015-03-05 14:00 | 2015-03-19 10:00 | N | N | line move | Line |  |  | For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2015-03-07 08:00 | 2015-03-07 16:00 | N | Y | tap changer indicator repair | Transformer |  |  | 240 kV
ALTALINK | 1053L (132s Ware Junction - 324s Cassils) | 2015-03-07 08:00 | 2015-03-08 18:00 | N | Y | urgent conductor repair and spacer damper inspection | Line |  |  | 240 kV
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2015-03-07 08:00 | 2015-03-07 16:00 | N | N | bushing inspection | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | ENMAX 23 | 2015-03-07 08:00 | 2015-03-07 12:00 | N | N | 8 kV bus spring substation washing | Station
ALTALINK | 932L (74s Janet - 162s Beddington) | 2015-03-08 07:30 | 2015-03-08 16:00 | N | Y | SW 144 & 145 MD maintenance on 162MD240-932L & spring substation washing | Line |  |  | 240 kV, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 985s T3 (985s Exshaw) | 2015-03-08 08:00 | 2015-03-08 18:00 | N | N | switch repair | Transformer
ALTALINK | 63s 152 (63s Red Deer) | 2015-03-09 07:00 | 2015-03-19 17:00 | N | Y | replace 240kv breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-03-09 07:00 | 2015-03-12 18:00 | N | N | FATD - NFTP: stringing of the north side of the new triple circuit 1106L ,1107L & 850L | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station),240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2015-03-09 07:00 | 2015-03-15 18:00 | N | Y | B2401 & B2402 breaker fail upgrade | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap),942L (681s Bannerman - 71s Lamoureux) | 2015-03-09 07:30 | 2015-03-30 18:00 | N | Y | preparation for new 681s Bannerman | Line |  |  | 240 kV, Pre-Condition
Saskpower | Sask Power PR903 | 2015-03-09 08:00 | 2015-03-09 13:00 | N | N | add oil to CT | Circuit Breaker |  |  | For Information Only
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2015-03-09 08:00 | 2015-03-12 16:00 | N | N | 138KV Bus Differential Upgrade. CT, Bus Differential & Auto Switching commissioning | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2015-03-09 08:00 | 2015-03-11 16:00 | N | N | Sw maint 8-1A10, 8-1A51 | Line |  |  | For Information Only
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2015-03-09 08:00 | 2015-03-10 17:30 | N | Y | urgent conductor repair and spacer damper inspection | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 202L335) | 2015-03-09 10:00 | 2015-03-10 17:00 | N | N | line maintenance - crossarm replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1120L (410s Josephburg - 108s Amelia) | 2015-03-09 18:00 | 2015-03-23 18:00 | N | Y | line reconfiguration - 681s Bannerman project | Line |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power P2P | 2015-03-10 06:00 | 2015-03-12 17:00 | N | N | bus installations | Line |  |  | For Information Only
ALTALINK | 80L (63s Red Deer - 214s Innisfail),214s Innisfail 138kV Bus 1 | 2015-03-10 08:00 | 2015-03-10 17:00 | N | N | switch repairs & sound wall installation | Bus, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 989L (310p Sundance - 77s Sagitawah) | 2015-03-10 08:00 | 2015-03-13 17:30 | N | Y | 240kV CT replacement | Line |  |  | 240 kV, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47) | 2015-03-10 08:00 | 2015-03-10 16:00 | N | N | spring substation washing | Transformer, Line |  |  | For Information Only
Saskpower | 9LS1M (840s McNeil - Swift Current) | 2015-03-10 09:00 | 2015-03-10 12:00 | Y | Y | SaskPower line outage - McNeill unavailable | Line |  |  | 240 kV, Limits ATC
BCH | 5L92 (Cranbrook - Selkirk) | 2015-03-10 09:00 | 2015-03-20 17:00 | Y | Y | replace spacers and install arcing horns - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC, Contingency Requires Mitigation
ALTALINK | 739L (432s Carvel - 739L214B),432s 739 (432s Carvel) | 2015-03-10 09:00 | 2015-03-10 17:00 | N | N | Replace gas density meter | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 214s T1 (214s Innisfail) | 2015-03-10 17:00 | 2015-03-14 16:00 | N | N | T1 noise wall installation and 25kV bus outage | Transformer
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2015-03-10 19:00 | 2015-03-10 23:00 | N | Y | radio upgrade and TPR circuit cutover to MPLS | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),36PT138-Z32 (ENMAX 36) | 2015-03-11 | 2015-03-11 07:00 | N | N | spring substation washing | Terminal Equipment, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 14s T1 (14s Devon),739L (14s Devon - 155s Blackmud),14s Devon 138kV South Bus | 2015-03-11 08:00 | 2015-03-11 12:00 | N | N | add supervisory controls to 14s24 | Transformer, Bus, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2015-03-11 08:00 | 2015-03-11 17:30 | N | Y | urgent conductor repair and spacer damper inspection | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 35s T2 (35s Rundle) | 2015-03-11 08:00 | 2015-03-11 17:00 | N | Y | change faulty fiber to the optical CT on T2 (emergency work) | Transformer |  |  | Restricts Generation
Medicine Hat | MH69s2 MH69_206 (MH69s2 North Industrial) | 2015-03-11 08:00 | 2015-03-11 12:00 | N | N | inspection and maintenance | Circuit Breaker |  |  | For Information Only
ATCO | 6L05 (843s Bigknife Creek - 757s Battle River) | 2015-03-11 10:00 | 2015-03-11 15:00 | N | N | installing station class lightIning arresters | Line |  | Installing station class lightIning arresters on 6L05 between 6L05D3 and 6L05D4 at 764S Heisler | Firm Load Loss, Creates Radial Feeds
STROBE | 240s T1 (240s McBride Lake) | 2015-03-11 11:00 | 2015-03-11 13:00 | N | N | relay programming | Transformer |  |  | Restricts Generation
ATCO | 824S Field Gate | 2015-03-11 11:30 | 2015-03-12 16:30 | N | N | 25kV work on 5L355 and 501 breaker | Station |  | BREAKER SF6 SFA COMPLETE TESTING, 501 Complete Testing of Breaker 501 Must close 500D1 & set relay settings to alt GENALTA CONTACT INFO IS AS FOLLOWS MIKE CHIMMA - CELL 780-239-4952 - FIELD OPERATOR (CALL FIRST) K.B. - CELL - 780-246-1661 - FIELD OPERATOR APPROVALS FOR MARCH 11-12 GENALTA OUTAGE CAME FROM K.B. ON JANUARY 28 @ 850 -------- Load Transfer -------- 824S 5L355 Peak Load = 4 MVA 824S 5L376 Peak Load = 1 MVA 824S 5L355 Relay Settings: SEL RELAY - 26 MVA 824S 5L376 Relay Settings: SEL RELAY - 25.98 MVA -------- Load Transfer -------- | For Information Only
ENMAX | 30.2TR (ENMAX 30) | 2015-03-11 12:00 | 2015-03-13 16:00 | N | N | relay maintenance | Transformer
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2015-03-12 06:30 | 2015-03-24 18:00 | N | Y | L to J: Remove old 936L Struc#48, install new 936L Struc#49, String 936L into new orientation @ 102s and P&C work. | Line |  |  | 240 kV, Limits ATC
ALTALINK | 14s T3 (14s Devon),739L (14s Devon - 305s Acheson),838L (14s Devon - 325s Leduc) | 2015-03-12 08:00 | 2015-03-12 16:00 | N | N | add supervisory controls to 14s29 & 14s838X | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2015-03-12 09:00 | 2015-03-13 17:00 | N | N | maintenance - crossarm replacement | Line |  |  | Pre-Condition
ALTALINK | 392s T2 (392s Black Diamond),158L (65s High River - 392s Black Diamond) | 2015-03-12 09:00 | 2015-03-12 17:00 | N | N | arcing whip not resetting | Line, Transformer |  |  | For Information Only
ENMAX | 21.2TR (ENMAX 21) | 2015-03-13 08:00 | 2015-03-31 16:00 | N | N | secondary bushing & cable replacement, LTC conservator - capital | Transformer
ALTALINK | 310P Sundance | 2015-03-13 15:00 | 2015-04-21 09:00 | N | Y | maintenance | Station |  |  | 240 kV
ALTALINK | 910L (89s Ellerslie - 63s Red Deer) | 2015-03-14 06:30 | 2015-03-19 17:00 | N | Y | install foundation in preparation for 288s | Line |  |  | 240 kV, Overload, Over/Under Voltage, Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-03-14 07:00 | 2015-03-14 12:00 | N | N | line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTAGAS | HMT1 ALP | 2015-03-14 08:00 | 2015-03-27 16:00 | N | N | In service date: March 10, 2015 (14.9 MVA). Refer to the Op Plan binder for the commissioning plan. | Unit
ENMAX | 1.6TR (ENMAX 1) | 2015-03-14 08:00 | 2015-03-14 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-03-14 12:00 | 2015-03-15 17:00 | N | N | spring line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L23 (848s Ruth Lake - 977s Salt Creek) | 2015-03-15 07:00 | 2015-03-27 12:00 | N | Y | line re-route for new highway | Line |  | LINE REROUTE FOR NEW HWY | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-03-16 07:00 | 2015-03-19 18:00 | N | N | FATD - NFTP: stringing of the north side of the new triple circuit 1106L ,1107L & 850L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 33s 4 (33s Spray) | 2015-03-16 07:00 | 2015-03-16 19:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 55s T2 (55s Olds) | 2015-03-16 07:00 | 2015-03-19 17:00 | N | N | replace 138kv LAs on T2 | Transformer |  |  | For Information Only
ALTALINK | 33s5 (33s Spray) | 2015-03-16 07:00 | 2015-03-16 19:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 580s T2 (580s Sylvan Lake),580s Sylvan Lake 138 kV Bus 2 | 2015-03-16 07:30 | 2015-03-20 17:00 | N | N | replacing bus differential | Transformer, Bus |  |  | Pre-Condition, For Information Only
ALTALINK | 89s 1152 (89s Ellerslie) | 2015-03-16 08:00 | 2015-03-19 14:00 | N | Y | change CTs next to 89s1152 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
CMH | CMH1 Medicine Hat #1 | 2015-03-16 08:00 | 2015-03-30 16:00 | N | N | CMH #12 testing/commissioning of control system and voltage regulator. Refer to the Op Plan binder for the commissioning plan. | Unit
ALTALINK | 852s T2 (852s Round Hill) | 2015-03-16 08:00 | 2015-03-20 17:30 | N | Y | tie in new switchgear & T2 | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2015-03-16 08:00 | 2015-03-20 17:00 | N | N | line maintenance - crossarm replacement | Line |  |  | Pre-Condition
Syncrude | Mildred Lake 72kV Bus 4 (Sycrude Mildred Lake) | 2015-03-16 08:00 | 2015-03-24 18:00 | N | N | preventative maintenance | Bus |  |  | For Information Only
ENMAX | 7.1TR (ENMAX 7) | 2015-03-16 08:00 | 2015-03-18 12:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
ENMAX | 8.1TR (ENMAX 8),8.2TR (ENMAX 8),Enmax 8 B138-1A0 (ENMAX 8) | 2015-03-16 08:00 | 2015-03-16 16:00 | N | N | maintenance 8-1A1 | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 7L38 (875s Algar - 917s Horse River) | 2015-03-16 09:00 | 2015-03-18 17:00 | N | N | climbing patrol on 7L38 | Line |  | 2015 climbing patrol 7L38-GOI GOI on 7L38 Feb17 to Feb,19 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 703L (648s Metiskow - 703L),648s 703W (648s Metiskow) | 2015-03-16 09:00 | 2015-03-27 16:00 | N | N | replacement of 703W breaker, including new pad | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 732L (299s Kingman - 730L tap) | 2015-03-17 07:00 | 2015-03-18 19:00 | N | N | cut new structure | Line |  |  | Firm Load Loss
ALTALINK | 299s T1 (299s Kingman) | 2015-03-17 07:00 | 2015-03-17 19:00 | N | N | Enbridge working on their equipment during 732L outage | Transformer |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy),Rossdale BR721 (Rossdale) | 2015-03-17 08:00 | 2015-03-18 17:00 | N | Y | BR721 breaker fail & upgrade | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 1.83L (ENMAX 1 - ENMAX 8),Enmax 8 B138-3A0 (ENMAX 8) | 2015-03-17 08:00 | 2015-03-17 16:00 | N | N | maintenance 8-3A52 | Line, Circuit Breaker
CapitalPower | 615s DVAR (615s Halkirk) | 2015-03-17 08:00 | 2015-05-12 16:00 | N | Y | maintenance | Shunts |  |  | For Information Only
ALTALINK | 71s T2 (71s Lamoureux),71s Lamoureux 138 kV East Bus | 2015-03-17 08:00 | 2015-03-17 16:00 | N | Y | add supervisory controls to 71s31 | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 922L (310p Sundance - 17s Benalto),17s922N (17s Benalto) | 2015-03-17 08:30 | 2015-03-17 17:00 | N | Y | 240kV switch hotspot repair | Line, Switch |  |  | 240 kV, Overload, Limits ATC, Contingency Requires Mitigation
ALTALINK | 74s T1 (74s Janet),74s 16 (74s Janet) | 2015-03-17 09:00 | 2015-03-17 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Transformer |  |  | Overload, Contingency Requires Mitigation
ATCO | 754s 702C (754s Ksituan River),754s 701T (754s Ksituan River) | 2015-03-17 11:00 | 2015-03-17 15:00 | N | N | check operation of 501TD1 | Shunts, Transformer |  | Transfer Load from 754S 701T to 902s Mobile Sub. / Check operation of 501TD1 and Transmission crew to change insulators on isolated portion of 7L10. | Pre-Condition
AESO-SC | EMS | 2015-03-17 15:00 | 2015-03-17 23:00 | N | N | SC monitor Vid-Wall controller implementation | SCInternal |  |  | For Information Only
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),36PT138-Z32 (ENMAX 36) | 2015-03-18 | 2015-03-18 07:00 | N | N | substation washing | Transformer, Terminal Equipment, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 730L (197s Bardo - 730L61),730L (285s East Camrose - 730L62),732L (299s Kingman - 730L tap) | 2015-03-18 07:00 | 2015-03-18 19:00 | N | N | connect 301s | Line |  | Line outage to connect 301s to 732L & close open point 'A'. New section of line & 301s will be energized from 285s730N. Breaker will be operated multiple times for commissioning. Open points B will be closed at a future date. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 929L (63s Red Deer - 74s Janet) | 2015-03-18 08:00 | 2015-03-18 17:00 | N | Y | hotspot repair | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 71s C1 (71s Lamoureux),71s C2 (71s Lamoureux),71s T1 (71s Lamoureux),71s 1052 (71s Lamoureux),71s 552 (71s Lamoureux),71s 952 (71s Lamoureux),71s 152 (71s Lamoureux),71s Lamoureux 138 kV West Bus | 2015-03-18 08:00 | 2015-03-18 16:00 | N | Y | add supervisory controls to 71s12 & 17s13 | Bus, Transformer, Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2015-03-18 08:00 | 2015-03-18 16:00 | N | N | maintenance | Line |  |  | Contingency Requires Mitigation
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2015-03-18 09:00 | 2015-03-18 17:00 | N | N | 138kV switch adjustment | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 395s North Holden),730L (197s Bardo - 730L61) | 2015-03-18 11:00 | 2015-03-18 17:00 | N | N | 197s6 maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7) | 2015-03-18 12:00 | 2015-03-20 16:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
EPCOR | 814s T2 (814s Bellamy),Rossdale BR722 (Rossdale) | 2015-03-19 08:00 | 2015-03-20 17:00 | N | Y | BR722 breaker fail upgrade | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 840S McNeill Station | 2015-03-19 08:00 | 2015-03-19 17:00 | N | Y | investigate cause non lock-out trips | Station |  |  | Limits ATC
ALTALINK | 71s T1 (71s Lamoureux),71s Lamoureux 240 kV West Bus | 2015-03-19 08:00 | 2015-03-19 16:00 | N | Y | add supervisory controls to 71s14 | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 9L22 (898s Heart Lake - 825s Whitefish Lake) | 2015-03-19 09:00 | 2015-03-19 13:00 | N | Y | Quadrahmo replacement, test & operatecontacts on breaker | Line |  | This work is in conjunction with CSP 2-31473 825S 9L22 21-1 Quadrahmo Replacement T & O Will require a test and operate to: Need to wire and test 52 contacts on 901 Bkr, 907Bkr, and 9L22D1 (89 contact). Will not require to do any work on the HV side so do not require a GOI. 9L22 and Portion of 825S bus will be out of service for duration of work. | 240 kV, Overload, Restricts Generation
ALTALINK | 74s 352 (74s Janet) | 2015-03-19 09:00 | 2015-03-19 14:00 | N | Y | leaking grading capacitor repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 767AL (21s Marion - 767L tap),767L (767L166A - 767L50) | 2015-03-19 10:00 | 2015-03-19 14:00 | N | N | close jumpers at str 54 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L130 (710s Vermilion - 705s Kitscoty),7L14 (710s Vermilion - 751s Hill) | 2015-03-19 12:00 | 2015-03-19 17:00 | N | N | install bird diverters on double circuit poles | Line |  | INSTALL BIRD DIVERTERS ON DOUBLE CIRCUIT POLES | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L14 (705s Kitscoty - 751s Hill) | 2015-03-19 12:00 | 2015-03-19 17:00 | N | N | ATCO work | Line
ALTALINK | 294s T2 (294s Brazeau Outlet Works) | 2015-03-19 16:00 | 2015-04-19 15:59 | N | N | metering upgrade | Transformer |  |  | For Information Only
ALTALINK | 33s 4 (33s Spray) | 2015-03-20 07:00 | 2015-03-20 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAXGPI | 134S Taber Wind Farm | 2015-03-20 08:00 | 2015-03-20 17:00 | N | N | replace multiple arrestors on 25Kv | Station |  |  | Restricts Generation
EPCOR | E511s VictoriaT3 (511s Victoria) | 2015-03-20 08:00 | 2015-03-20 17:00 | N | N | replace tapchanger filtration unit | Transformer
ALTALINK | 71s T2 (71s Lamoureux),71s Lamoureux 240 kV East Bus | 2015-03-20 08:00 | 2015-03-20 16:00 | N | Y | add supervisory controls to 71s32 | Bus, Transformer |  |  | 240 kV
ATCO | 718s 701T (718s Parsons Creek),7L165 (718s Parsons Creek - 933s Tower Road),7L47 (848s Ruth Lake - 718s Parsons Creek) | 2015-03-20 08:00 | 2015-03-21 18:00 | N | N | setting pole structure | Transformer, Line |  | Setting a two pole structure in line at the tap off point of line reroute for project E17230 - the work to be done on this outage will be a back-to-back dead-end feed through  no new line will be energized. / The rerouted line construction will be tied in at a later date. | Pre-Condition
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-03-21 07:00 | 2015-03-21 12:00 | N | N | spring line washing, tower maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft T1 (Woodcroft) | 2015-03-21 08:00 | 2015-03-21 17:00 | N | N | inspection | Transformer
ALTALINK | 852S Round Hill | 2015-03-21 08:00 | 2015-03-23 17:30 | N | N | 25 kV bus 1 tie in new switchgear building,B1 protection cutover | Station
ENMAX | 11.1TR (ENMAX 11) | 2015-03-21 08:00 | 2015-03-21 12:00 | N | N | urgent substation wash | Transformer
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-03-21 12:00 | 2015-03-22 17:00 | N | N | spring line washing, tower maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11) | 2015-03-21 12:00 | 2015-03-21 16:00 | N | N | urgent substation wash | Transformer
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32),32PT138-Z32 (ENMAX 32) | 2015-03-22 08:00 | 2015-03-22 12:00 | N | N | spring substation washing | Transformer, Terminal Equipment, Line
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),32PT138-Z31 (ENMAX 32),54PT138-32.82 (ENMAX 54) | 2015-03-22 12:00 | 2015-03-22 16:00 | N | N | spring substation washing | Terminal Equipment, Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 163s 1752 (163s Amoco Empress) | 2015-03-23 07:00 | 2015-03-26 17:00 | N | Y | 240kV CT replacement | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24) | 2015-03-23 07:00 | 2015-03-27 17:00 | N | Y | AltaLink request | Line |  |  | Pre-Condition, Overload
EPCOR | 72RS5 (Rossdale - Strathcona) | 2015-03-23 07:00 | 2015-04-03 18:00 | N | N | cable monitor installation | Line
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-03-23 07:00 | 2015-03-29 18:00 | N | N | FATD - NFTP: stringing of the north side of the new triple circuit 1106L ,1107L & 850L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 55s T1 (55s Olds) | 2015-03-23 07:00 | 2015-03-26 17:00 | N | N | replace 138kv LAs on T1, strain insulators between T1 and 25kv bus, LAs on 25kv feeders | Transformer
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant),44s 860W (44s Bearspaw) | 2015-03-23 07:00 | 2015-03-26 17:00 | N | N | install new scada, A&B prot, new brealer control | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),Hardisty H725 (Hardisty Epcor) | 2015-03-23 08:00 | 2015-03-27 17:00 | N | N | control cable de-commissioning | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary),5s 7 (5s East Calgary),5s C4 (5s East Calgary) | 2015-03-23 08:00 | 2015-05-07 16:00 | N | Y | ENMAX: 2s cap bank ECTP, swap AIS 5s7 to C2sGIS | Circuit Breaker, Shunts |  |  | Pre-Condition, Limits ATC
EPCOR, ALTALINK | 665s TX1 (665s Dome),909L (89s Ellerslie - 665s Dome) | 2015-03-23 08:00 | 2015-03-24 19:00 | N | Y | relay maintenance | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2015-03-23 10:00 | 2015-03-27 15:00 | N | N | line maintenance - crossarm replacement | Line |  |  | Pre-Condition
ALTALINK | 5s 1152 (5s East Calgary) | 2015-03-23 11:00 | 2015-03-23 17:00 | N | Y | routine testing of the breaker control/fail relay | Circuit Breaker |  |  | 240 kV
ALTALINK | 852S Round Hill | 2015-03-24 08:00 | 2015-03-27 17:30 | N | N | tie in new switchgear for 25 kV bus | Station |  |  | For Information Only
ATCO, ALTALINK | 7L760 (7L760D2 - 767s Oyen),760L (7L760D3 - 760L41) | 2015-03-24 08:00 | 2015-03-24 17:00 | N | N | 7L760D2 repair | Line |  | 7L760D2 Repair, 914s Blindloss will be without power during this outage Line maintenance, 914s Blindloss will be radial fed from 163s Amoco | Firm Load Loss, Creates Radial Feeds
ALTALINK | 834L (384s Keystone - 320p Keephills) | 2015-03-24 08:00 | 2015-03-24 17:00 | N | N | repair existing cable | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (55s Olds - 152s Didsbury),55s 80X (55s Olds) | 2015-03-24 08:00 | 2015-03-24 17:00 | N | N | RAS settings change | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28) | 2015-03-24 08:00 | 2015-03-24 16:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2015-03-24 08:00 | 2015-03-24 16:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ALTALINK | 115s T2 (115s Mt.Allan) | 2015-03-24 08:00 | 2015-03-26 17:00 | N | N | oil leak repair | Transformer |  |  | For Information Only
ALTALINK | 526s C1 (526s Buffalo Creek) | 2015-03-24 09:00 | 2015-03-24 17:00 | N | N | investigating alarm | Shunts |  |  | Pre-Condition, For Information Only
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2015-03-24 09:00 | 2015-03-27 17:00 | N | Y | mark ball replacement | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ATCO | 7L03 (7L03D3 - 731s Elmworth) | 2015-03-24 09:00 | 2015-03-24 17:00 | N | N | change CT ratios on 7L03 for line mitigation | Line |  | 7L03 open ended Change CT ratios on 7L03 for line mitigation Str. 79 from line mitigation to be changed out arms to station post over double circuit 25 KV 5L333 | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 937L (102s Langdon - 74s Janet) | 2015-03-25 07:00 | 2015-03-31 17:00 | N | Y | L to J: remove 937L from temporary attachment on 1064L onto new Str# 49, string new 937L into final orientation at 102s | Line |  |  | 240 kV, Overload, Over/Under Voltage, Limits ATC
ATCO | 9L79 (757s Battle River - 755s Cordel),757s 911 (757s Battle River),757s 911A (757s Battle River),757s 9L79D1 (757s Battle River),757s 911PT (757s Battle River),757s 9L79PT (757s Battle River),757s 9L79GS1 (757s Battle River) | 2015-03-25 07:00 | 2015-04-30 17:30 | N | Y | maintenance | Line, Terminal Equipment, Switch, Circuit Breaker |  | Battle River does not want to hold the GOI for the tech's any longer than required to do maintenance on 911A. Once 911A work is complete, we will have 2 separate GOI's with 911A as the common point. We will require a Transfer of Authority up to but not including 911A and a COG from Battle River on 911A. | 240 kV
REDDEER | 194s T2 (194s South Red Deer) | 2015-03-25 07:30 | 2015-03-25 18:30 | N | N | replace pressure gas release device | Transformer |  |  | For Information Only
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2015-03-25 08:00 | 2015-04-24 16:00 | N | Y | modification of protection systems for the new 1106L bay | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK, ATCO | 174L (197s Bardo - 395s North Holden),7L77 (395s North Holden - 709s Vegreville),395s 174W (395s North Holden),395s 77E (395s North Holden),395s 3 (395s North Holden) | 2015-03-25 08:00 | 2015-03-31 09:30 | N | N | 395s8 PT replacement | Line, Circuit Breaker, Switch |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.2TR (ENMAX 28),ENMAX 28 8kV Bus | 2015-03-25 08:00 | 2015-03-25 16:00 | N | N | spring substation washing | Transformer, Bus |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar),987s CC721 (987s Clover Bar) | 2015-03-25 08:00 | 2015-03-25 17:00 | N | Y | relay maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 665s TX2 (665s Dome),909L (320p Keephills - 665s Dome) | 2015-03-25 08:00 | 2015-03-26 19:00 | N | Y | relay maintenance | Line, Transformer |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2),749s 702 (749s Flyingshot Lake),749s 703 (749s Flyingshot Lake) | 2015-03-25 09:00 | 2015-03-25 17:00 | N | N | changes to the poles / CT ratio for line mitigation | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan),262s34 (262s Rocky Mountain House) | 2015-03-25 09:00 | 2015-03-25 17:00 | N | N | 138kV switch maintenance | Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 10 (17s Benalto) | 2015-03-25 09:00 | 2015-03-25 17:00 | N | Y | investigate breaker status change to the EMS | Circuit Breaker |  |  | 240 kV
ALTALINK | 580s T1 (580s Sylvan Lake),648L (63s Red Deer - 580s Sylvan Lake),580s Sylvan Lake 138 kV Bus 1 | 2015-03-25 09:01 | 2015-03-27 16:00 | N | N | replace bus differential | Bus, Transformer, Line
ATCO | 827s SVC (827s Cranberry Lake) | 2015-03-25 10:30 | 2015-03-25 15:00 | N | Y | investigate SVC cooling transfer and control system can operate with SVC out of service | Shunts |  | Investigate 827S SVC Cooling Transfer and Controls System can operate with SVC out of service. | Pre-Condition
ATCO | 7L63 (812s Norcen - 780s Lubicon) | 2015-03-26 08:00 | 2015-03-30 17:00 | N | N | climbing inspection | Line |  | Climbing Inspection Line 7L63, 783s Cadotte Rv and 812s Norcen will be radial fed from 788s Hotchkiss | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s 252 (244s Bowmanton) | 2015-03-26 08:00 | 2015-04-30 17:00 | N | Y | part of 244s152 outage | Circuit Breaker |  |  | 240 kV
ALTALINK | 601L (275s Jenner - 230s Wardlow),275s 601 (275s Jenner) | 2015-03-26 08:00 | 2015-03-26 14:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | For Information Only
ATCO | 9L37 (826s Marguerite Lake - 825s Whitefish Lake) | 2015-03-26 08:00 | 2015-03-26 12:30 | N | Y | replace 9L37 | Line |  | 825S/826S Quadrahmo Replace 9L37 Line Outage / Commission 9L37 21A Relay Aux inputs @ both ends / 9L37 will be out of service for duration of the work | 240 kV, For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2015-03-26 08:00 | 2015-03-27 16:00 | N | N | 23.4TR relay replacement | Transformer
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2015-03-26 09:00 | 2015-03-26 17:00 | N | N | 138kV switch maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 856s 505R (856s Kinosis) | 2015-03-26 09:00 | 2015-03-26 14:00 | N | N | 51-51N-59/505R relay testing | Shunts |  | 51-51N-59/505R Relay Testing./ Test and Operate on BKR 505 Required because of insufficient Back-up Protection. | Pre-Condition
ENMAX | 2.2TR (ENMAX 2) | 2015-03-27 08:00 | 2015-05-05 16:00 | N | N | ECTP: dissasemble/move/assemble/fill/comission | Transformer
ATCO | 9L930 (72s Leismer - 825s Whitefish Lake) | 2015-03-27 13:00 | 2015-04-05 16:00 | N | Y | line construction | Line |  | Line Construction, | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L183 (856s Kinosis - 2060s Engstrom) | 2015-03-28 08:00 | 2015-03-31 16:00 | N | N | In service date: March 31, 2015 | Line
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2015-03-28 08:00 | 2015-03-28 12:00 | N | N | spring substation washing. 9.83L pothead washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 937S Amr02 | 2015-03-28 08:00 | 2015-04-03 16:00 | N | N | In service date: April 1, 2015 | Station
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2015-03-29 08:00 | 2015-03-29 12:00 | N | N | washing due to fault trip | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2015-03-29 08:00 | 2015-03-29 16:00 | N | N | maintenance | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2015-03-29 12:01 | 2015-03-29 14:00 | N | N | washing due to fault trip | Line |  |  | Pre-Condition, For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2015-03-29 12:01 | 2015-03-29 16:00 | N | N | washing due to fault trip | Transformer
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2015-03-29 14:01 | 2015-03-29 16:00 | N | N | washing due to fault trip | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 657s Summerside T1 (657s Summerside) | 2015-03-30 06:00 | 2015-03-31 18:00 | N | Y | Relay testing | Transformer |  |  | 240 kV
EPCOR | 330P 12TC1 (330p Genesee),330P Genesee 500 kV Bus 1 | 2015-03-30 06:00 | 2015-03-30 18:00 | N | Y | Relay testing | Transformer, Bus |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 291s T1 (291s Cochrane) | 2015-03-30 07:00 | 2015-05-01 17:30 | N | N | T1 replace, VR1 remove, & 25kv bus reconfig | Transformer |  |  | For Information Only
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2015-03-30 07:00 | 2015-03-31 08:00 | N | N | Calgary Stampede project | Line
ALTALINK | 163s C1 (163s Amoco Empress) | 2015-03-30 07:00 | 2015-04-02 17:00 | N | N | CT Replacements | Shunts |  |  | Pre-Condition
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-03-30 07:00 | 2015-04-30 17:00 | N | N | FATD - NFTP: stringing of the north side of the new triple circuit 1106L ,1107L & 850L | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D132 (ENMAX 25) | 2015-03-30 08:00 | 2015-03-31 16:00 | N | Y | heater repair | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 7L47 (848s Ruth Lake - 718s Parsons Creek) | 2015-03-30 08:00 | 2015-04-01 17:00 | N | N | climbing inspection | Line |  | 2015 climbing inspection 7L47 | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 41.1TR (ENMAX 41) | 2015-03-30 08:00 | 2015-04-02 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 885L (648s Metiskow - 650s Hansman Lake) | 2015-03-30 08:00 | 2015-04-08 16:00 | N | N | replacement of 648s885 breaker, add LA's | Line |  |  | For Information Only
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2015-03-30 08:00 | 2015-03-30 18:00 | N | Y | maintenance - BC maintenance does not affect AB ATC | Line |  |  | 240 kV, Limits ATC, Contingency Requires Mitigation
ENMAX | 27.1TR (ENMAX 27) | 2015-03-30 08:00 | 2015-03-30 16:00 | N | N | investigate miswired control circuitry | Transformer |  |  | For Information Only
ALTALINK | 310p 1352 (310p Sundance),310p 1452 (310p Sundance) | 2015-03-30 08:00 | 2015-04-02 09:00 | N | Y | repair 310p14B prior to new breaker 310p1452 being energized | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2015-03-30 09:00 | 2015-03-30 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 648s 36 (648s Metiskow) | 2015-03-30 10:00 | 2015-04-14 15:00 | N | N | replace s36 switch and associated structure modifications | Switch |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746L tap),700L (746s Sherwood Park - 700L TAP) | 2015-03-30 10:00 | 2015-04-01 15:00 | N | N | line maintenance | Line |  |  | Creates Radial Feeds
ALTALINK | 798L (364s Whitecourt Industrial - 77s Sagitawah) | 2015-03-30 10:01 | 2015-04-01 16:00 | N | N | SCADA upgrade project | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2015-03-31 | 2015-03-31 06:00 | N | N | repair hot spot | Transformer, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 330P 12TC2 (330p Genesee) | 2015-03-31 06:00 | 2015-03-31 18:00 | N | Y | relay testing | Transformer |  |  | 240 kV, Contingency Requires Mitigation, 500 kV
ENMAX | 27.2TR (ENMAX 27) | 2015-03-31 08:00 | 2015-03-31 16:00 | N | N | investigate miswired control circuitry | Transformer
WINDYPWPL | 112S Windy Point | 2015-03-31 08:00 | 2015-04-02 16:00 | N | N | capacitor bank testing | Station |  |  | Pre-Condition, For Information Only
ALTALINK | 778L (217s North Red Deer - 87s Gaetz) | 2015-03-31 08:00 | 2015-04-01 17:30 | N | N | replace 87s778 switch | Line |  |  | Pre-Condition, Over/Under Voltage
REDDEER, ALTALINK | 194s T1 (194s South Red Deer),80L (194s South Red Deer - 217s North Red Deer) | 2015-03-31 08:00 | 2015-04-05 03:10 | N | N | replace bus | Transformer, Line
ALTALINK | 37s T5 (37s North Calder) | 2015-03-31 08:00 | 2015-03-31 18:00 | N | N | repair Leaks | Transformer
ALTALINK | 395s T1 (395s North Holden) | 2015-03-31 09:00 | 2015-03-31 16:00 | N | N | cut over trips and current contributions | Transformer |  |  | Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer),233s13 (233s Beamer) | 2015-03-31 09:00 | 2015-03-31 17:00 | N | N | insulator replacement | Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek) | 2015-03-31 10:00 | 2015-03-31 14:00 | N | N | 8.7m high load move | Line |  | 8.7m high load move | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2015-03-31 11:00 | 2015-03-31 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 330p 1202 (330p Genesee) | 2015-04-01 06:00 | 2015-04-01 18:00 | N | Y | Relay testing | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
REDDEER | 194s T1 (194s South Red Deer) | 2015-04-01 07:30 | 2015-04-01 18:30 | N | N | replace sudden pressure gas release protective device | Transformer |  |  | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2015-04-01 07:30 | 2015-06-26 17:00 | N | N | RATD - create open points at both ends to facilitate 648 rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2015-04-01 08:00 | 2015-04-01 13:00 | N | N | maintenance | Switch |  |  | Restricts Generation
VISIONREQ | 354s DVAR1 (354s Summerview) | 2015-04-01 08:00 | 2015-04-02 16:00 | N | N | maintenance | Shunts |  |  | For Information Only
ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2015-04-01 08:00 | 2015-04-01 16:00 | N | N | move 2.2TR to new bay | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7) | 2015-04-01 08:00 | 2015-04-01 16:00 | N | N | rewire FT isolation blades | Transformer |  |  | For Information Only
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2015-04-01 09:00 | 2015-04-01 17:00 | N | N | relay settings change | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 744L (228s T.M.P.L.Niton - 207s Pinedale),890L (58s Edson - 207s Pinedale) | 2015-04-01 09:30 | 2015-04-01 17:00 | N | N | 207sVT1 oil sample | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 776L (410s Josephburg - 308s Albchem Beaverhill Creek),308s 776W (308s Albchem Beaverhill Creek) | 2015-04-01 10:00 | 2015-04-01 12:00 | N | N | top up the breaker with SF6 gas - urgent | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36) | 2015-04-01 12:00 | 2015-04-01 16:00 | N | Y | substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s C1 (58s Edson),58s T2 (58s Edson),671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2015-04-01 13:00 | 2015-04-01 17:00 | N | N | breaker work - urgent | Line, Shunts, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 898s Heart Lake 240 kV 900 Bus | 2015-04-02 08:00 | 2015-04-04 16:00 | N | Y | stringing bus conductor over south section of bus | Bus |  | No added risk to system, Stringing bus conductor over south section of bus. | 240 kV, For Information Only
ENMAX | 22.81L (ENMAX 22 - ENMAX 39),ENMAX 39 B138-22.81 (ENMAX 39),ENMAX 22 B138-22.81 (ENMAX 22) | 2015-04-02 08:00 | 2015-04-02 16:00 | N | N | HV breaker doble | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2015-04-02 08:00 | 2015-04-02 16:00 | N | N | spring substation washing | Line, Transformer |  |  | For Information Only
ATCO, ALTALINK | 9L961 (13s Deerland - 825s Whitefish Lake) | 2015-04-02 09:00 | 2015-04-02 13:00 | N | Y | Protection work | Line |  | This work is to be done in conjunction with CSP 2-31472 825S 9L961 21A Quadrahmo Replacement T&O Will require a test and operate to: Need to wire and test 52 contacts on 903 Bkr, 904Bkr, and 9L961D1 (89 contact). Will not require to do any work on the HV side so do not require a GOI. For duration of work 9L961 and 825S loop feed capability will be out. | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 13s 1452 (13s Deerland),13s 1352 (13s Deerland) | 2015-04-02 09:00 | 2015-04-02 13:00 | N | Y | Relay Test and Operate | Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 871L (341s Sand Hills - 163s Amoco Empress) | 2015-04-02 12:00 | 2015-04-02 17:00 | N | N | 'A' protection troubleshooting at 163s | Line |  | The A prot (871L A87/L7 LFCB123) on 871L between 163s and 341s is cycling into alarm. Techs would like to disable the protections and troubleshoot this issue. | For Information Only
ENMAX | 65.1 TR (ENMAX 65),ENMAX 65 240kV South Bus | 2015-04-03 08:00 | 2015-04-03 16:00 | N | Y | harmonic monitoring addition. wiring changes to 65PT240-Z41 | Bus, Transformer |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2015-04-03 08:00 | 2015-04-03 16:00 | N | N | HV breaker doble | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2015-04-04 06:30 | 2015-04-06 18:00 | N | Y | L to J: removal of existing SS tower in close proximity to 936L | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 166L (152s Didsbury - 166L50) | 2015-04-04 07:00 | 2015-04-06 17:00 | N | N | install foundations under 166L at 281s | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2015-04-04 08:00 | 2015-04-04 12:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2015-04-04 12:01 | 2015-04-04 16:00 | N | Y | sub washing | Line, Shunts, Transformer |  |  | Pre-Condition, Overload, Limits ATC, Contingency Requires Mitigation
REDDEER, ALTALINK | 194s T2 (194s South Red Deer),80L (194s South Red Deer - 63s Red Deer) | 2015-04-05 03:00 | 2015-04-12 03:00 | N | N | replace bus diff and replace 194s3 | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, AESO | ENMAX 5 B138-2.82 (ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2015-04-05 07:00 | 2015-05-01 12:00 | N | N | transfer and dead end 2.82L to pothead structure | Circuit Breaker, Line |  |  | For Information Only
ATCO | 898s 501R (898s Heart Lake),898s 902T (898s Heart Lake),898s Heart Lake 240 kV 900 Bus | 2015-04-05 08:00 | 2015-04-07 16:00 | N | Y | stringing conductor bus over 240kV north bus | Transformer, Shunts, Bus |  | 902T will be OOS during bus outage, AML will be asked to close 602L1 to supply 818s from 788L, portable genset will be installed to maintain AC station service, 501R 20 MVAR reactor will be unavailable for dispatch, stringing conductor bus over 240kV north bus | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2015-04-06 08:00 | 2015-04-06 12:00 | N | Y | spring substation washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 814s B2402 (814s Bellamy) | 2015-04-06 08:00 | 2015-04-07 17:00 | N | Y | cutover breaker fail upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 778L (217s North Red Deer - 87s Gaetz) | 2015-04-06 08:00 | 2015-04-07 17:30 | N | N | install structure for new 209s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 28.80L (42s Sarcee - ENMAX 28),42s 28 (42s Sarcee) | 2015-04-06 08:00 | 2015-04-06 12:00 | N | Y | ENMAX: wash 20 sub | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ENMAX | 10.2TR (ENMAX 10) | 2015-04-06 08:00 | 2015-04-06 16:00 | N | N | low oil alarm | Transformer
BCH | 5L77 (Revelstoke - Ashton Creek) | 2015-04-06 09:00 | 2015-04-17 17:00 | N | N | replace REV SA and CVTs | Line |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2015-04-06 12:00 | 2015-04-06 16:00 | N | N | spring substation washing | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 163s C2 (163s Amoco Empress) | 2015-04-07 07:00 | 2015-04-10 17:00 | N | N | CT replacements | Shunts |  |  | For Information Only
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2015-04-07 07:00 | 2015-04-10 17:00 | N | Y | install new L8 prot module,& breaker control | Line |  |  | For Information Only
ATCO | 879s T1 (879s Scotford Upgrader),EX1-01 (879s Scotford Upgrader - 402s Scotford Expansion) | 2015-04-07 07:00 | 2015-05-11 17:30 | N | N | install new 701TD and 701T | Line, Transformer |  | No system concerns, Install new 701TD and 701T. ALCO1S and 879s radial fed, EX1-O1L will be open ended at 879s, Shell Scotford generation output limited to 90 MW When 701TD install is complete April 16, GOI zone will be reduced to 701TD so EX1OIL and 144kV bus 1.can be re-energized. | Restricts Generation, Creates Radial Feeds
ALTALINK | 846L (127s Bruderheim - 365s Canadian Oxy Astotin Creek) | 2015-04-07 07:00 | 2015-04-07 21:00 | N | N | 365s station & breaker work at 127s | Line |  |  | For Information Only
ALTALINK | 918L (17s Benalto - 162s Beddington) | 2015-04-07 07:30 | 2015-04-11 18:00 | N | Y | install foundation under 918L | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2015-04-07 08:00 | 2015-04-07 12:00 | N | N | spring substation washing | Line, Transformer |  |  | For Information Only
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2015-04-07 08:00 | 2015-04-13 18:00 | N | Y | FATD - NFTP: string to structure 14 on 1106/1107L | Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 316S West Crossfield | 2015-04-07 08:00 | 2015-04-11 17:00 | N | N | station equipment replacements | Station |  |  | For Information Only
ALTALINK | 172L (370s North Lethbridge - 172L1238) | 2015-04-07 08:00 | 2015-04-30 18:00 | N | N | line rebuild | Line |  |  | Over/Under Voltage
ALTALINK | 286s T1 (286s Yasa) | 2015-04-07 08:00 | 2015-04-14 13:00 | N | N | customer request for T1 outage | Transformer |  |  | For Information Only
ALTALINK | 151s T2 (151s Strathmore) | 2015-04-07 08:00 | 2015-04-08 16:00 | N | N | install new SCADA metering | Transformer |  |  | For Information Only
ALTALINK | 700L (422s Westwood - 746L tap),700L (746s Sherwood Park - 700L TAP) | 2015-04-07 10:00 | 2015-04-09 15:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 415s 352 (415s Drywood) | 2015-04-07 10:00 | 2015-04-07 17:00 | N | N | heater upgrade/replacement | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 162L (415s Drywood - 229s Glenwood),415s 146E (415s Drywood) | 2015-04-07 13:00 | 2015-04-07 15:00 | N | N | perform test operations on 229s162 switch | Line, Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2015-04-07 14:00 | 2015-04-09 17:00 | N | N | repair leaks | Transformer
ATCO | 9L24 (959s Lanfine - 946s Oakland) | 2015-04-08 07:00 | 2015-04-14 19:00 | N | Y | testing of the Lanfine SVC | Line |  | In order to facilitate testing of the Lanfine SVC in the capacitive range, requesting the ability to open end 9L24 as required between April 11 through to and including April 19. If we do not need to have the line opened on a particular day, we will not request it. We should only require the line to be opened between the hours of 7:00 am and 19:00 pm. | 240 kV, Pre-Condition
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2015-04-08 08:00 | 2015-04-08 13:00 | N | N | repair 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 768L (217s North Red Deer - 87s Gaetz) | 2015-04-08 08:00 | 2015-04-09 17:30 | N | N | install STR. for 209s | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2015-04-08 08:00 | 2015-04-09 16:00 | N | N | HV breaker inspection | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 959S SVC (959s Lanfine) | 2015-04-08 08:00 | 2015-04-14 17:00 | N | N | In service date: April 14, 2015. Refer to the Op Plan binder for the commissioning plan. | Shunts |  |  | 240 kV
EPCOR | 814s T2 (814s Bellamy) | 2015-04-08 08:00 | 2015-04-10 17:00 | N | Y | cutover breaker fail upgrade | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 28.2TR (ENMAX 28) | 2015-04-08 08:00 | 2015-04-08 16:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2015-04-08 08:00 | 2015-04-08 16:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
TRANSALTA | 59s 752 (59s Peigan) | 2015-04-08 09:00 | 2015-04-09 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2015-04-08 13:00 | 2015-04-08 18:00 | N | Y | repair 52HS device | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L183 (856s Kinosis - 2060s Engstrom) | 2015-04-09 08:00 | 2015-04-30 16:00 | N | N | protection testing | Line |  | 7L183 construction between 7L183D3 and 2060s, end to end protection testing between 2081s, 856s, and 2060s, 144kV ring will be open @ 2060s | For Information Only
ALTALINK | 3L (272s Springbank - 3L147) | 2015-04-09 08:00 | 2015-04-27 17:00 | N | N | rebuild line - structure 148 - 229 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO | 703L (213s Hughenden - 703BL tap) | 2015-04-09 09:00 | 2015-04-09 11:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L194 (875s Algar - 2009s Willow Lake) | 2015-04-10 07:30 | 2015-04-10 17:30 | N | N | re-tension a slack span | Line |  | Re-tension a slack span | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 30.81L (42s Sarcee - ENMAX 30),ENMAX 30 B138-30.81 (ENMAX 30) | 2015-04-10 08:00 | 2015-04-10 16:00 | N | Y | HV breaker inspection | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2015-04-10 09:00 | 2015-04-10 11:00 | N | Y | test new radial connection | Line |  |  | Limits ATC
ALTALINK | 924L (102s Langdon - 356s Milo) | 2015-04-10 09:00 | 2015-04-10 18:00 | N | Y | replace broken interphase spacers that are rubbing on conductor | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 814s B2406 (814s Bellamy) | 2015-04-11 08:00 | 2015-04-12 17:00 | N | Y | cutover breaker fail upgrade | Circuit Breaker |  |  | 240 kV
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13),22PT138-Z7 (ENMAX 22) | 2015-04-11 08:00 | 2015-04-11 12:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 67s T2 (67s Stirling),820L (67s Stirling - 820AL tap),67s 820 (67s Stirling) | 2015-04-11 08:00 | 2015-04-11 17:00 | N | N | T2 & 67s820 maintenance | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau T2 (Garneau) | 2015-04-11 09:00 | 2015-04-11 21:00 | N | N | switchgear maintenance | Transformer
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39),22PT138-Z7 (ENMAX 22) | 2015-04-11 12:00 | 2015-04-11 16:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
REDDEER | 194s T2 (194s South Red Deer) | 2015-04-11 12:00 | 2015-04-11 17:00 | N | N | 194s 15-B-T2 functional tests | Transformer
ALTALINK | 336S Fincastle | 2015-04-12 | 2015-04-12 00:01 | N | N | Fortis to replace damaged 25kv switching cubicle | Station
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2015-04-12 01:00 | 2015-04-12 07:00 | N | N | spring substation washing | Transformer, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
REDDEER, AESO | 194s T1 (194s South Red Deer),425L (194s South Red Deer - 217s North Red Deer) | 2015-04-12 03:01 | 2015-04-12 15:00 | N | N | close open point on 138kv bus | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2015-04-12 07:30 | 2015-04-27 13:00 | N | Y | line repair | Line |  |  | 240 kV, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2015-04-12 07:30 | 2015-04-25 18:00 | Y | Y | move 1114L protections to new 102s7452 | Line |  | Update BCH RAS with new 102s Bus/Line configuration. Move 936L. WATL & FATD. | Limits ATC, 500 kV
ALTALINK | 520s T1 (520s Bennett) | 2015-04-12 07:30 | 2015-04-25 18:00 | N | Y | connect 1114L protection to new 102s7452 | Transformer |  |  | 500 kV
ALTALINK | 102s Langdon 240 kV East Bus | 2015-04-12 08:00 | 2015-04-14 08:00 | N | Y | connect bus to new diameter (102s252 & 102s552) - WATL | Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 34.1TR (ENMAX 34) | 2015-04-12 08:00 | 2015-04-12 16:00 | N | N | low oil alarm requires top up | Transformer
ALTALINK | 63s T2 (63s Red Deer) | 2015-04-12 10:00 | 2015-04-22 17:00 | N | Y | bushing replacement & oil reclamation | Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK, ENMAX | 44s 36_81E (44s Bearspaw),36.81L (44s Bearspaw - ENMAX 36) | 2015-04-13 07:00 | 2015-04-16 17:00 | N | Y | replace breaker control | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 511s Victoria T1 (511s Victoria) | 2015-04-13 08:00 | 2015-04-13 17:00 | N | N | relay calibration | Transformer |  |  | For Information Only
ATCO | 826s 503R (826s Marguerite Lake),826s 504R (826s Marguerite Lake),826s 902T (826s Marguerite Lake) | 2015-04-13 08:00 | 2015-04-17 16:30 | N | Y | Racid relay replacement | Transformer, Shunts |  | 826S Marguerite Lake 902T OOS for Racid relay replacement (Replacing 2 electronic Racid relay 51H,51Y and 2 electro mechanical relays 59N, and 51Y-N; with 2 microprocessor based relays)., 901T will carry all load, 504R and 505R will be unavailable for system voltage control. | 240 kV, For Information Only
ALTALINK | 100L (895s Suffield - 498s Tilley),498s 100X (498s Tilley) | 2015-04-13 08:00 | 2015-04-16 17:00 | N | Y | replace 100L A&B protections | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 41.2TR (ENMAX 41) | 2015-04-13 08:00 | 2015-04-16 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake),755L (63s Red Deer - 247s Piper Creek),80L (63s Red Deer - 214s Innisfail),63s Red Deer 138 kV South Bus | 2015-04-13 08:00 | 2015-04-22 17:00 | N | N | 138kV south bus outage to add new 63sT4 and switchgear | Line, Bus |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.4TR (ENMAX 2) | 2015-04-13 08:00 | 2015-04-13 16:00 | N | N | energization of this new transformer | Transformer |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 41 B138-33.83 (ENMAX41) | 2015-04-13 08:00 | 2015-04-13 16:00 | N | N | HV Breaker Doble | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1TR (ENMAX 21) | 2015-04-13 08:00 | 2015-04-14 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 729L (542s Ervick - 729L13A) | 2015-04-13 10:00 | 2015-04-17 15:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
AESO, ALTALINK | 677L (305s Acheson  595s Spruce Grove),305s 677 (305s Acheson),305s25 (305s Acheson) | 2015-04-13 10:00 | 2015-04-15 17:00 | N | N | breaker 677 & switch 25 maintenance | Line, Circuit Breaker, Switch |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale RR723 (Rossdale) | 2015-04-14 07:00 | 2015-04-14 18:00 | N | N | breaker fail upgrade | Circuit Breaker
ATCO | 9L79 (757s Battle River - 755s Cordel),755s 901 (755s Cordel),755s 902 (755s Cordel) | 2015-04-14 07:00 | 2015-04-17 17:30 | N | Y | commission new protection package | Circuit Breaker, Line |  | Commission new protection package. During BR 5 turnaround. | 240 kV, Restricts Generation
ALTALINK | 337s T1 (337s Canada Liquidair),337s T2 (337s Canada Liquidair),746BL (337s Canada Liquidair - 746DL17) | 2015-04-14 07:00 | 2015-04-17 17:00 | N | N | customer request for Grounding & Switching | Line, Transformer |  |  | For Information Only
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2015-04-14 08:00 | 2015-04-14 15:00 | N | N | high load move | Line |  |  | Creates Radial Feeds
ALTALINK | 939L (77s Sagitawah - 809s Louise Creek) | 2015-04-14 08:00 | 2015-04-16 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Pre-Condition, Overload
ENMAX | ENMAX 65 240kV South Bus | 2015-04-14 08:00 | 2015-04-18 17:00 | N | Y | NFTP: string 1106L and 1107L slack span into ENMAX 65SS | Bus |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 511s Victoria T2 (511s Victoria) | 2015-04-14 08:00 | 2015-04-14 17:00 | N | N | relay calibration | Transformer
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2015-04-14 16:30 | 2015-04-20 17:00 | N | Y | L to J: removal of existing SS tower in close proximity to 936L | Line |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ALTALINK | 185s T1 (185s Bretville) | 2015-04-15 06:00 | 2015-04-15 18:00 | N | N | customer NGR & maintenance work | Transformer
EPCOR | Rossdale R721 (Rossdale) | 2015-04-15 07:00 | 2015-04-15 18:00 | N | N | breaker fail protection upgrade | Circuit Breaker
EPCOR | Kennedale T1 (Kennedale) | 2015-04-15 07:00 | 2015-04-15 18:00 | N | N | TX gassing investigation | Transformer
ALTALINK | 185s 152 (185s Bretville) | 2015-04-15 08:00 | 2015-04-15 17:00 | N | N | breaker maintenance / SF6 leak | Circuit Breaker
ENMAX | 21.2TR (ENMAX 21) | 2015-04-15 08:00 | 2015-04-16 16:00 | N | N | switch maintenance | Transformer
EPCOR | E511s VictoriaT4 (511s Victoria) | 2015-04-15 08:00 | 2015-04-16 17:00 | N | N | relay calibration | Transformer
ALTALINK | 310p 552 (310p Sundance) | 2015-04-15 09:00 | 2015-04-15 17:00 | N | Y | replacing faulty AVT | Circuit Breaker |  |  | 240 kV
ALTALINK | 885L (648s Metiskow - 650s Hansman Lake) | 2015-04-15 10:30 | 2015-04-15 12:30 | N | N | connect mobile to 885L | Line |  |  | Pre-Condition, For Information Only
ALTALINK | 648s T1 (648s Metiskow),648s T3 (648s Metiskow),703L (648s Metiskow - 703L),954L (648s Metiskow - 650s Hansman Lake),648s 749E (648s Metiskow) | 2015-04-15 11:01 | 2015-04-22 14:00 | N | Y | replace bus protection | Line, Circuit Breaker, Transformer |  | Replace bus protection, perform trip tests & VR tap changer filter, replace 648s4 (RET), TX, VR & breaker maintenance, repair 648s26, 25kV maintenance (Altalink) | 240 kV, Creates Radial Feeds
ATCO | 845s 702 (845s Big Mountain) | 2015-04-15 17:00 | 2015-04-22 16:00 | N | N | forced outage | Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 62s12 (62s Brazeau) | 2015-04-15 23:00 | 2015-04-16 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
CapitalPower | 615S Halkirk | 2015-04-16 | 2015-04-22 00:01 | N | N | wind farm frequency test | Station |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2015-04-16 03:00 | 2015-04-16 07:00 | N | Y | Maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 286s T2 (286s Yasa) | 2015-04-16 08:00 | 2015-04-24 08:00 | N | N | customer request for T2 outage | Transformer |  |  | For Information Only
ALTALINK | 310p Sundance 240kV Bus A | 2015-04-16 08:30 | 2015-04-16 17:00 | N | Y | repair 310p24A, & 310p2452 | Bus |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 411s T1 (411s Obed) | 2015-04-17 09:00 | 2015-04-17 17:00 | N | N | measurements for future bushing replacement | Transformer
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2015-04-18 | 2015-04-18 07:00 | N | N | high load move | Line |  |  | Pre-Condition
EPCOR | 113S Inland-Cement | 2015-04-18 07:00 | 2015-04-18 18:00 | N | N | aerial maintenance - customer work | Station |  |  | For Information Only
ALTALINK | 747L (99s North St. Albert - 747DL4),898L (37s North Calder - 92s Viscount) | 2015-04-18 07:00 | 2015-04-19 18:00 | N | N | line maintenance | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 918L (17s Benalto - 162s Beddington) | 2015-04-18 07:30 | 2015-04-18 16:00 | N | Y | switch maintenance on SW 134 & 135, 62MD240-918L, spring substation washing | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2015-04-18 08:00 | 2015-04-18 12:00 | N | N | spring substation washing | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau T3 (Garneau) | 2015-04-18 09:00 | 2015-04-18 21:00 | N | N | swichgear maintenance | Transformer
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2015-04-18 12:01 | 2015-04-18 16:00 | N | N | spring substation washing | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2015-04-19 08:00 | 2015-04-19 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2015-04-19 08:00 | 2015-04-19 12:00 | N | Y | brush gear work | Switch |  |  | Restricts Generation
ALTALINK | 87s 2352 (87s Gaetz) | 2015-04-19 08:30 | 2015-04-19 15:00 | N | Y | emergency repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 62s12 (62s Brazeau) | 2015-04-19 12:00 | 2015-04-19 16:00 | N | N | brush gear work | Switch |  |  | Restricts Generation
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2015-04-19 12:00 | 2015-04-19 16:00 | N | Y | spring substation washing | Line, Shunts, Transformer |  |  | Pre-Condition, Limits ATC
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works) | 2015-04-19 14:00 | 2015-04-19 16:00 | N | Y | remove mobile from 801L | Line |  |  | Restricts Generation
SUNCOR | 29PL9-5 (29EDD-1 Millennium - 29EDD-34) | 2015-04-20 07:00 | 2015-04-21 20:00 | N | Y | address phase A ground fault issue | Line |  |  | 240 kV, For Information Only
EPCOR | 72CN10 (987s Clover Bar - Namao),Namao N724 (Namao) | 2015-04-20 07:00 | 2015-04-24 18:00 | N | N | bushing replacement | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy) | 2015-04-20 07:00 | 2015-06-01 18:00 | N | Y | bushing replacement | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 814s T1 (814s Bellamy),814s B2401 (814s Bellamy),Rossdale BR721 (Rossdale),814s B2407 (814s Bellamy) | 2015-04-20 07:00 | 2015-04-27 18:00 | N | Y | breaker fail upgrade | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 44S Bearspaw Plant,44s T1 (44s Bearspaw Plant) | 2015-04-20 07:00 | 2015-04-30 17:00 | N | N | install T1 prot, install new feeder prot module | Transformer, Station |  |  | For Information Only
ENMAX | 20.1TR (ENMAX 20) | 2015-04-20 08:00 | 2015-04-21 16:00 | N | N | hot spot on switch 82 at ENMAX 20 | Transformer |  |  | For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2015-04-20 08:00 | 2015-04-24 16:00 | N | N | oil leak containment | Transformer |  |  | For Information Only
ENMAX | ENMAX 20,1.81L (ENMAX 20 - ENMAX 1) | 2015-04-20 08:00 | 2015-05-04 16:00 | N | N | line differential | Station, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),ENMAX 14 B138-14.83 (ENMAX 14) | 2015-04-20 08:00 | 2015-04-21 16:00 | N | N | breaker Inspection | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.1TR (ENMAX 40) | 2015-04-20 08:00 | 2015-04-24 16:00 | N | N | doble and LV cable test | Transformer |  |  | For Information Only
ATCO | 836s 626T (836s Steep Bank),836s 630 (836s Steepbank) | 2015-04-20 08:30 | 2015-04-20 17:00 | N | N | relay testing | Circuit Breaker, Transformer |  |  | For Information Only
BCH | 5L75 (Revelstoke - Ashton Creek) | 2015-04-20 09:00 | 2015-05-01 17:00 | N | N | REV SA and CVT replacement | Line |  |  | For Information Only
ALTALINK | 896L (19s Wabamun - 432s Carvel),19s203 (19s Wabamun) | 2015-04-20 10:00 | 2015-04-20 17:00 | N | N | Switch repair | Line, Switch |  |  | Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK, ATCO | 723L (69s North Barrhead - 723L133),7L230 (69s North Barrhead - 7L230 tap),69s North Barrhead 138kV Bus,69s 138kV Bus & T5 - Advice | 2015-04-20 10:00 | 2015-04-23 17:00 | N | N | Replace 69s17 138kV PT | Bus, Terminal Equipment, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2015-04-20 10:00 | 2015-04-23 17:00 | N | N | line maintenance | Line |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 421s T2 (421s Hays) | 2015-04-20 12:00 | 2015-04-24 17:00 | N | N | oil leak repair | Transformer |  |  | For Information Only
ALTALINK | 937L (102s Langdon - 74s Janet) | 2015-04-20 17:30 | 2015-04-25 17:00 | N | Y | L to J: Remove 937L from temporary attachment on 1064L onto new Str# 49. String new 937L into final orientation @ 102s. | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2015-04-21 07:30 | 2015-04-22 18:00 | N | N | line repair from rebuild - broken anchor | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 170s 1452 (170s Pike) | 2015-04-21 08:00 | 2015-04-22 16:00 | N | N | install heaters on breaker 1452 pole tanks | Circuit Breaker |  |  | Firm Load Loss
ALTALINK | 754L (118s Canmore - 437s Baymag),118s 754E (118s Canmore) | 2015-04-21 08:00 | 2015-04-23 16:00 | N | N | replace breaker CT modify str | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2015-04-21 08:00 | 2015-04-22 12:00 | N | Y | warranty work | Circuit Breaker, Shunts |  |  | Limits ATC
ALTALINK | 938L (77s Sagitawah - 809s Louise Creek) | 2015-04-21 08:00 | 2015-04-23 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
SUNCOREP | SCR4 Wintering Hills | 2015-04-21 08:00 | 2015-04-23 17:00 | N | N | frequency test | Unit |  |  | For Information Only
TRANSCANADAP | 910s 701T (910s Excel) | 2015-04-21 08:00 | 2015-04-21 23:59 | N | N | bird proofing instatllation | Transformer |  | Installation of Bird Proofing on 4160 volt bus COG required from TCP on 4160 volt breaker and 4160 Volt PT
ALTALINK | 325s T1 (325s Leduc) | 2015-04-21 08:30 | 2015-04-21 17:00 | N | N | repair leaks on T1 | Transformer |  |  | For Information Only
ALTALINK | 310P Sundance | 2015-04-21 09:00 | 2015-04-24 09:00 | N | Y | repairs to 310p | Station |  |  | Restricts Generation, For Information Only
AESO-SC | DDST | 2015-04-21 09:30 | 2015-04-21 10:30 | N | N | DDST application will be down during this outage 09:30-10:30 for the new EAR file to be deployed | SCInternal |  | In this DDST System Enhancement Release, a number of enhancements have be implemented to improve the accuracy of the asset ramping for normal and quick-start assets and add a new expired asset ramping trend in the dashboard to capture all the assets continuing to ramp after their dispatch times have been expired. | For Information Only
ALBIAN | 919s 908 (919s Hartley) | 2015-04-22 06:30 | 2015-06-02 06:30 | N | Y | maintenance | Circuit Breaker |  | Shell Albian Sands request a COG they will be shutting down GT#2 for turnaround Issue Permit to Control room - 1-780-713-4745 | 240 kV, Restricts Generation
ENMAX | 2.1TR (ENMAX 2) | 2015-04-22 08:00 | 2015-06-09 16:00 | N | N | energization of this new transformer and autoswitching checks | Transformer |  |  | For Information Only
ALTALINK | 452S B.F. Goodrich Fort Saskatchewan | 2015-04-22 08:00 | 2015-04-22 16:00 | N | N | customer performing checks for future project | Station |  |  | For Information Only
ALTALINK | 74s C2 (74s Janet),74s 54 (74s Janet) | 2015-04-22 13:00 | 2015-04-23 17:00 | N | Y | warranty work | Circuit Breaker, Shunts |  |  | Limits ATC
ALTALINK | 885L (648s Metiskow - 650s Hansman Lake) | 2015-04-22 14:00 | 2015-04-22 16:00 | N | N | remove mobile from 885L | Line |  |  | For Information Only
ALTALINK | 80L (194s South Red Deer - 63s Red Deer),194s 80X (194s South Red Deer),63s 80N (63s Red Deer) | 2015-04-23 07:00 | 2015-05-29 12:59 | N | N | line rebuild, protection work & renaming as 426L | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (55s Olds - 152s Didsbury) | 2015-04-23 07:00 | 2015-04-25 17:00 | N | N | install foundation 417L for new Johnson poles | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 997L (71s Lamoureux - 410s Josephburg),71s47 (71s Lamoureux) | 2015-04-23 08:30 | 2015-04-23 17:00 | N | Y | Switch repair | Line, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2015-04-23 08:30 | 2015-04-23 13:00 | N | N | repair 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 162L (415s Drywood - 229s Glenwood) | 2015-04-23 08:30 | 2015-04-23 18:00 | N | N | line repair from rebuild - straighten structure | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
BENIGN | 383s Kettles Hill Windfarm RTU/SCADA | 2015-04-23 09:00 | 2015-04-23 17:00 | N | N | SCADA software relay upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2015-04-23 13:00 | 2015-04-23 17:00 | N | N | repair 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 310P Sundance | 2015-04-24 06:00 | 2015-05-02 16:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ALTALINK | 729L (40s Wetaskiwin - 729L13A) | 2015-04-24 08:00 | 2015-04-24 15:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2015-04-24 08:00 | 2015-04-24 16:00 | N | N | spring sub washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (432s Carvel - 739L214B),432s 739 (432s Carvel) | 2015-04-24 09:00 | 2015-04-24 17:00 | N | N | replace gas density meter | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2015-04-25 | 2015-04-28 03:30 | N | N | spring line washing (night washing) | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 65.2 TR (ENMAX 65),ENMAX 65 240kV North Bus | 2015-04-25 08:00 | 2015-04-27 16:00 | N | Y | harmonic monitoring addition | Transformer, Bus |  |  | 240 kV, Pre-Condition
EPCOR | Garneau T1 (Garneau) | 2015-04-25 09:00 | 2015-04-25 21:00 | N | N | swichgear maintenance | Transformer
EPCOR | 113S Inland-Cement | 2015-04-26 07:00 | 2015-04-26 18:00 | N | N | plant outage for EPCOR aerial maintenance | Station
ALTALINK | 80L (198s Blackfalds - 217s North Red Deer),217s 80N (217s North Red Deer) | 2015-04-26 09:00 | 2015-04-26 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2015-04-26 12:00 | 2015-04-26 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199s T2 (199s East Airdrie) | 2015-04-27 07:00 | 2015-04-29 17:00 | N | N | LA's replacements, meter module replacment, create Open Point 'A' | Transformer |  |  | For Information Only
ALTALINK | 63s T3 (63s Red Deer) | 2015-04-27 07:00 | 2015-05-04 12:00 | N | N | complete removal of 262L overhead, connect bus tie cables ,trip tests | Transformer |  |  | For Information Only
EPCOR | 72RS5 (Rossdale - Strathcona),Rossdale RS724 (Rossdale) | 2015-04-27 07:00 | 2015-04-27 18:00 | N | N | breaker fail upgrade | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 72RV4 (Rossdale - 511s Victoria),Rossdale RV726 (Rossdale) | 2015-04-27 07:00 | 2015-05-01 18:00 | N | N | Bushing Replacement | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 510s T1 (510s Sunnybrook) | 2015-04-27 08:00 | 2015-04-30 08:00 | N | N | connect HVDC station service | Transformer |  |  | For Information Only
SUNCOR | 29PL6-4 (836s Steepbank - 29EDD-1) | 2015-04-27 08:00 | 2015-04-30 20:00 | N | N | PM work on CVT, Disconnects, Motorized Disconnect & Lightning Arrestor | Line |  |  | For Information Only
ENMAX | ENMAX 1,Enmax 1 B138-9A0 (ENMAX 1),Enmax 1 B138-8A0 (ENMAX 1) | 2015-04-27 08:00 | 2015-05-04 16:00 | N | N | Line differential, Function test new protection tripping.,Partial 138kV Bus and 138kv Bus PT (8a2); Line differential, Function test new protection tripping. | Station, Circuit Breaker |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2015-04-27 08:00 | 2015-05-01 16:00 | N | N | doble, LV cable test | Transformer |  |  | For Information Only
ENMAX | 14.2TR (ENMAX 14) | 2015-04-27 08:00 | 2015-04-29 12:30 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 826s 502R (826s Marguerite Lake),826s 901T (826s Marguerite Lake) | 2015-04-27 08:30 | 2015-05-01 10:00 | N | Y | 826S Marguerite Lake 901T | Transformer, Shunts |  | 826S Marguerite Lake 901T Racid Replacement This is related to CSP 2-31887 We are replacing electronic racid relays 51H and 51Y, as well as Electromechanical relay 59N and 51N-Y; with 2 Microprocessor based relays. During the Duration of the Work 826S will only have one of the transformer in service. And will not have capability to use 502R. (503R and 504R will be in service) | 240 kV, For Information Only
ALTALINK | 377s C101 (377s Hardisty),377s 473C102 (377s Hardisty) | 2015-04-27 10:00 | 2015-05-01 10:00 | N | N | 138kV CT replacement | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 297s T1 (297s Rimbey) | 2015-04-27 11:00 | 2015-04-27 17:00 | N | N | T1 PRD Switch Failed | Transformer |  |  | For Information Only
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2015-04-27 12:00 | 2015-04-28 17:00 | N | N | connect mobile to 733L | Line |  |  | Pre-Condition
ALTALINK | 377s C1 (377s Hardisty),377s 34 (377s Hardisty) | 2015-04-27 12:00 | 2015-04-27 17:00 | N | N | CT ratio change | Shunts, Circuit Breaker |  |  | For Information Only
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2015-04-28 03:30 | 2015-04-28 07:00 | N | N | spring line washing | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 989L (310p Sundance - 77s Sagitawah) | 2015-04-28 06:30 | 2015-04-30 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 681L (377s Hardisty - 478s Tucuman),377s 681 (377s Hardisty) | 2015-04-28 07:00 | 2015-04-28 12:00 | N | N | CT ratio change | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | Rossdale VHBB1 (Rossdale) | 2015-04-28 07:00 | 2015-04-28 18:00 | N | N | breaker fail upgrade | Circuit Breaker |  |  | For Information Only
ALTALINK | 498s C1 (498s Tilley),498s 33 (498s Tilley) | 2015-04-28 08:00 | 2015-04-29 12:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 310p 952 (310p Sundance),310p 852 (310p Sundance) | 2015-04-28 08:00 | 2015-04-30 17:00 | N | Y | replace CVT and secondary junction box | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK, AESO | 820AL (315s Chin Chute - 820L tap),820L (67s Stirling - 820AL tap),820L (254s Coaldale - 820AL tap) | 2015-04-28 08:00 | 2015-04-29 17:00 | N | Y | urgent maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge) | 2015-04-28 08:00 | 2015-04-29 17:00 | N | N | critical maintenance | Line |  |  | Pre-Condition
ALTALINK | 166L (256s Harmattan - 166L52) | 2015-04-28 09:00 | 2015-04-28 17:00 | N | N | 138kV switch adjustment at 256s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (Line Creek - Elkford) | 2015-04-28 09:00 | 2015-04-28 17:00 | N | N | conductor repair | Line |  |  | Limits ATC
ALTALINK | 702L (377s Hardisty - 137s Sedgewick),377s 702W (377s Hardisty) | 2015-04-28 12:01 | 2015-04-28 17:00 | N | N | CT ratio change | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 703L (377s Hardisty - 703L),377s 703E (377s Hardisty) | 2015-04-29 07:00 | 2015-04-29 12:00 | N | N | CT ratio change | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 44s T1 (44s Bearspaw Plant) | 2015-04-29 07:00 | 2015-05-07 17:00 | N | N | install T1 protection and new feeder protection module | Transformer
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River),A793s 701 (A793s West Peace) | 2015-04-29 08:00 | 2015-04-29 16:30 | N | N | 701 breaker testing | Line, Circuit Breaker |  | 793S 701 BREAKER SF6 HPL PARTIAL TESTING 7L51 WILL BE OPEN ENDED AT 793S, 927S Buchanan radial fed from 788s. | Firm Load Loss, Creates Radial Feeds
TRANSALTA | 179s T1 (179s Gleichen) | 2015-04-29 08:00 | 2015-05-21 07:59 | N | N | replace 179s23N, 179s24X & 179s23E, feeder protections, replace 25kV bus PT's, metering upgrade | Transformer
ALTALINK | 100L (895s Suffield - 498s Tilley),895s 100 (895s Suffield) | 2015-04-29 08:00 | 2015-04-29 12:00 | N | Y | transfer trip install project, cut-in/function test | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2015-04-29 08:00 | 2015-04-29 12:00 | N | N | spring substation washing | Transformer, Line |  |  | Overload, Creates Radial Feeds
ATCO | 7L56 (725s Goose River - 738s Virginia Hills) | 2015-04-29 09:00 | 2015-04-29 17:00 | N | N | emergency outage to a portion of 7L56 | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2015-04-29 09:00 | 2015-05-01 17:00 | N | Y | mark ball replacement | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23),74s 23.80W (74s Janet) | 2015-04-29 12:00 | 2015-04-29 16:00 | N | Y | spring substation washing | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 377s 769X (377s Hardisty),769L (377s Hardisty - 769AL tap) | 2015-04-29 12:00 | 2015-04-29 17:00 | N | N | CT ratio change | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO | 703L (213s Hughenden - 703BL tap) | 2015-04-29 12:00 | 2015-04-29 14:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 892L (895s Suffield - 41s Medicine Hat),895s 892 (895s Suffield) | 2015-04-29 12:30 | 2015-04-29 16:30 | N | Y | transfer trip install project, cut-in/function test | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1TR (ENMAX 14) | 2015-04-29 12:30 | 2015-05-01 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 431s C1 (431s Hussar),431s 152 (431s Hussar) | 2015-04-29 13:00 | 2015-04-30 17:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ENMAX | 22.2TR (ENMAX 22) | 2015-04-29 13:00 | 2015-05-29 16:00 | N | N | high levels of heating gasses detected in "X" winding, tap changer needs repair | Transformer
ATCO | 931S Bohn,7L05 (931s Bohn - 2049s Kettle River) | 2015-04-30 06:00 | 2015-04-30 18:00 | N | N | install marker cones and bird diverters | Line, Station |  | Install marker cones and bird diverters. 12 hour outage to 931s Bohn, outage has been co-ordinated with the customer. | For Information Only
ALTALINK | 263s C1 (263s Strachan) | 2015-04-30 08:00 | 2015-04-30 17:00 | N | N | replace failed capacitor & fuse | Shunts |  |  | For Information Only
ALTALINK | 377s T1 (377s Hardisty) | 2015-04-30 08:00 | 2015-04-30 16:00 | N | N | CT ratio change | Transformer |  |  | For Information Only
ALTALINK | 610L (336s Fincastle - 83s Taber) | 2015-04-30 08:00 | 2015-05-01 15:00 | N | Y | Line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 149s C1 (149s Nisku),149s T1 (149s Nisku),858L (149s Nisku - 40s Wetaskiwin) | 2015-04-30 09:00 | 2015-04-30 17:00 | N | N | reinforce switch base | Shunts, Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 291s T1 (291s Cochrane) | 2015-05-01 08:00 | 2015-06-08 18:00 | N | N | T1 replacement | Transformer
MFG1 | MFG1 Mazeppa Gas Plant | 2015-05-01 08:00 | 2015-06-29 16:00 | N | N | 5 x 3.3 MW, In service date: May 11, 2015 (refer to the Op Plan binder for the commissioning plan) | Unit
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 2 - 2.83L tap),2.83L (ENMAX 13 - 2.83L tap),ENMAX 5 B138-2.83 (ENMAX 5),ENMAX 13 B138-2.83 (ENMAX 13),ENMAX 13 RTU/SCADA,ENMAX 5 RTU/SCADA | 2015-05-01 12:00 | 2015-05-15 16:00 | N | N | ECTP 2s (3 terminal P&C), swap AIS to GIS & breaker inspection 13B138-2.83 & 5B138-2.83 | Terminal Equipment, Circuit Breaker, Line |  |  | Pre-Condition, Affects Visibility
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2015-05-03 07:30 | 2015-05-03 12:00 | N | Y | static wire removal from 936L to 2.83L | Line |  |  | 240 kV, Pre-Condition, Limits ATC
EPCOR | 987s C2408 (987s Clover Bar) | 2015-05-04 07:00 | 2015-05-08 18:00 | N | Y | Alstrom retrofit of breaker | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2015-05-04 07:00 | 2015-05-08 18:00 | N | N | trans #1 protection commissioning | Line |  |  | For Information Only
ALTALINK | 77s T2 (77s Sagitawah),825L (484s Millar Western - 77s Sagitawah),77s Sagitawah 138 kV East Bus | 2015-05-04 07:00 | 2015-05-05 17:00 | N | Y | 138kV insulator replacements | Bus, Line, Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 511s Victoria T2 (511s Victoria) | 2015-05-04 07:00 | 2015-05-08 18:00 | N | N | doble testing | Transformer |  |  | For Information Only
ALTALINK | 199S East Airdrie,199s T1 (199s East Airdrie) | 2015-05-04 07:00 | 2015-05-22 12:00 | N | N | LA's replacements, multi 25kV switch replacements, multi 25kV insulator replacements, T1 bushing replacement, meter module replacement | Transformer, Station |  |  | For Information Only
ENMAX | ENMAX 8 | 2015-05-04 08:00 | 2015-05-04 16:00 | N | N | 8.1 distribution cap bank maintenance | Station |  |  | For Information Only
ALTALINK | 603L (243s Soderglen Wind Farm - 59s Peigan) | 2015-05-04 08:00 | 2015-05-04 18:00 | N | Y | Windy Flats: create open point at str 603L97 | Line |  |  | Restricts Generation
ENMAX | 43.1TR (ENMAX 43) | 2015-05-04 08:00 | 2015-05-08 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | ENMAX 2 B138-D95 (ENMAX 2),ENMAX 2 B138-D96 (ENMAX 2) | 2015-05-04 08:00 | 2015-05-05 16:00 | N | N | function test BMR8 relay | Circuit Breaker |  |  | For Information Only
ALTALINK | 41S Medicine Hat | 2015-05-04 08:00 | 2015-05-24 17:00 | N | N | MH69 69kV breaker maintenace (one at a time) | Station |  | Between May 04 and May 24 2015 breaker maintenance will be performed in the MH-69 KV yard. The following breakers will be taken out of service for maintenance (one breaker at a time) MH69-2, MH69-6, MH69-10, MH69-13, MH69-17, MH69-21, MH69-24, MH69-28, MH69-31, MH69-34, MH69-38, MH69-42. Each breaker will be out of service for approx. 1-1.5 days. This breaker maintenance will not affect our plant generation or our ability to import or export. MH69-6 will be removed from service May 09 and MH69-10 will be removed from service May 10th. The system Operator for AESO will be contacted before we open the MH69-6 and MH69-10 breakers to confirm proper breaker status when they are removed from service. | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41),ENMAX 41 B138-6.82 (ENMAX 41) | 2015-05-04 08:00 | 2015-05-05 10:00 | N | N | dashpot repairs, DC ground investigate | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 15 ,15.1TR (ENMAX 15) | 2015-05-04 08:00 | 2015-05-15 16:00 | N | N | 8kV bus outage. SEL 351 feeder relay upgrade | Station, Transformer |  |  | For Information Only
ATCO | 859s 702 (859s Primrose) | 2015-05-04 09:00 | 2015-05-04 17:00 | N | N | breaker maintenance | Circuit Breaker
ATCO | 977s 902 (977s Salt Creek) | 2015-05-04 09:00 | 2015-05-05 13:00 | N | Y | breaker testing | Circuit Breaker |  | Test and operate 902 BKR @ 977S Salt Creek, Ring will be open no line outages. | 240 kV, Contingency Requires Mitigation
ALTALINK | 610L (336s Fincastle - 83s Taber) | 2015-05-04 10:00 | 2015-05-08 15:00 | N | Y | line maintenance | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 977s 905 (977s Salt Creek) | 2015-05-04 13:00 | 2015-05-05 17:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and operate 902 BKR @ 977S Salt Creek, Ring will be open, no line outages. | 240 kV, Contingency Requires Mitigation
ALTALINK | 302S Cardinal River | 2015-05-05 07:00 | 2015-05-06 17:00 | N | N | install 69kV LA's | Station |  |  | For Information Only
ALTALINK | 799s T3 (799s Coleman),170L (632s Russell - 799s Coleman) | 2015-05-05 07:00 | 2015-05-06 17:00 | N | Y | 799s34 PT Replacement | Line, Transformer |  |  | Overload, Creates Radial Feeds
ATCO | 859s 703 (859s Primrose) | 2015-05-05 08:00 | 2015-05-05 17:00 | N | N | breaker maintenance | Circuit Breaker
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank) | 2015-05-05 08:00 | 2015-05-08 20:00 | N | N | lightning arrester PM (29PLA-189A,B&C) | Line |  |  | For Information Only
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2015-05-05 08:00 | 2015-05-07 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 812AL (512s Hartell - 812L tap),812L (392s Black Diamond - 65s High RIver) | 2015-05-05 08:00 | 2015-05-07 17:00 | N | N | replace VT2, remove a section of temp fence | Line |  |  | Creates Radial Feeds
ALTALINK | 523s C1 (523s Bullshead) | 2015-05-05 08:00 | 2015-05-06 12:00 | N | N | warranty work | Shunts |  |  | For Information Only
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725BL54),725L (15s Fort MacLeod - 725BL54) | 2015-05-05 08:00 | 2015-05-08 19:00 | N | Y | Windy Flats: install caissons for new strs 608L9 and 725BL40 | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 650s 452 (650s Hansman Lake) | 2015-05-05 08:00 | 2015-05-05 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 929L (63s Red Deer - 74s Janet),63s 2752 (63s Red Deer),63s 2652 (63s Red Deer) | 2015-05-05 08:30 | 2015-05-05 17:00 | N | Y | adjust 63s26X switch | Line, Circuit Breaker |  |  | 240 kV, Limits ATC
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2015-05-05 09:00 | 2015-05-05 12:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 825L (484s Millar Western - 77s Sagitawah) | 2015-05-05 09:00 | 2015-05-05 17:00 | N | N | 138kV breaker maintenance | Line |  |  | For Information Only
ALTALINK | 186s T2 (186s Dry Creek) | 2015-05-05 10:00 | 2015-05-05 16:00 | N | N | T2 Scada auto/manual testing | Transformer |  |  | For Information Only
ALTALINK | 1116L (170s Pike - 167s Ipiatik Lake) | 2015-05-05 17:01 | 2015-05-08 17:00 | N | Y | Bring 1116L into 167s up to Open Point A | Line |  |  | For Information Only
Medicine Hat | MH69S-2 North Industrial | 2015-05-06 07:00 | 2015-05-08 16:00 | N | N | transformer T-21 maintenance | Station |  | Transformer T-21(69kV/13.8kV) is located in MH69S-2 North Industrial Substation. | For Information Only
ATCO | 7L38 (875s Algar - 917s Horse River) | 2015-05-06 07:00 | 2015-05-12 17:30 | N | N | allow construction of 9L07 and 9L89 | Line |  | Allow construction of 9L07 and 9L89, no concerns. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p T6 (320p Keephills),320p Keephills 500kV Bus B | 2015-05-06 08:00 | 2015-05-06 18:00 | N | Y | install WATL RAS | Bus, Transformer |  | Redundant protections may be taken out of service one at a time for functional testing. | For Information Only, 500 kV
ALTALINK, ATCO | 650s 1752 (650s Hansman Lake),7L224 (774s Monitor - 650s Hansman Lake) | 2015-05-06 08:00 | 2015-05-06 17:00 | N | Y | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 859s 701 (859s Primrose),859s 704 (859s Primrose) | 2015-05-06 08:00 | 2015-05-06 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 133L (19s Wabamun - 133L697A),19s 133 (19s Wabamun) | 2015-05-06 08:30 | 2015-05-06 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 71s C1 (71s Lamoureux),71s C2 (71s Lamoureux),71s 1052 (71s Lamoureux) | 2015-05-06 08:30 | 2015-05-06 17:00 | N | N | repair 71s45, replace 71s1052 52HS device | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 888s 907 (888s Dover) | 2015-05-06 09:00 | 2015-05-06 13:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and operate 902 BKR @ 977S Salt Creek, Ring will be open no line outages. | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 44s T2 (44s Bearspaw Plant),50L (44s Bearspaw Plant - ENMAX 21),860L (291s Cochrane - 44s Bearspaw Plant),36.81L (44s Bearspaw - ENMAX 36) | 2015-05-06 10:00 | 2015-05-07 15:00 | N | Y | maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 368s C2 (368s Burdett),368s 44 (368s Burdett) | 2015-05-06 13:00 | 2015-05-07 17:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 888s 908 (888s Dover) | 2015-05-06 13:00 | 2015-05-06 17:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and Operate BKR 908 @ 888S Dover., Ring will be open, no line outages. | 240 kV, For Information Only
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2015-05-06 14:00 | 2015-05-06 16:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 668L (394s Empress - 562s Cypress) | 2015-05-07 07:00 | 2015-05-07 17:00 | N | N | OPGW spire installation on top of A frame | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 330P Genesee | 2015-05-07 07:00 | 2015-05-31 18:00 | N | Y | bus diff upgrade | Station |  |  | Restricts Generation, 500 kV
ALTALINK | 1238L (510s Sunnybrook - 330p Genesee),1239L (510s Sunnybrook - 330p Genesee),1203L (320p Keephills - 510s Sunnybrook) | 2015-05-07 07:30 | 2015-05-09 17:00 | N | Y | install WATL RAS | Line |  |  | Limits ATC, Restricts Generation, Firm Load Loss, Creates Radial Feeds, 500 kV
ALTALINK | 608L (418s Ardenville - 608L72) | 2015-05-07 08:00 | 2015-05-08 18:00 | N | Y | Windy Flats: install caissons for new strs 608L21 and temp guy on 608L9 | Line |  |  | Restricts Generation
ALTALINK | 185L (415s Drywood - 379s Shell Canada Waterton),415s185W (415s Drywood) | 2015-05-07 08:00 | 2015-05-07 17:00 | N | N | 69kV switch repair | Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
STROBE | 240S McBride Lake | 2015-05-07 08:00 | 2015-05-08 16:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ALTALINK | 739L (434s Stony Plain - 739L216A),432s 739 (432s Carvel) | 2015-05-07 08:00 | 2015-05-07 09:00 | N | N | top up gas in breaker due to low gas alarm | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.3TR (ENMAX 2) | 2015-05-07 08:00 | 2015-05-07 16:00 | N | N | move 2.1TR to new bay. 2.83L must be oos at this time | Transformer
ALTALINK | 5S East Calgary | 2015-05-07 08:00 | 2015-05-07 16:00 | N | N | 5s43, move 2.1TR to new bay. 2.83L must be oos at this time | Station
ALTALINK | 650s 1352 (650s Hansman Lake) | 2015-05-07 08:00 | 2015-05-07 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 19s T8 (19s Wabamun) | 2015-05-07 08:30 | 2015-05-07 17:00 | N | N | replace X3 bushing | Transformer |  |  | Pre-Condition
ENMAXGPI | 134s Taber Wind Farm RTU/SCADA | 2015-05-07 11:00 | 2015-05-07 13:00 | N | N | router internet software upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 74s T1 (74s Janet),74s Janet 240kV Bus 1 | 2015-05-09 08:00 | 2015-05-10 17:00 | N | Y | replace PTs 74s48 and strain insulators | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 727L (74s Janet - 1140s Temp) | 2015-05-09 08:00 | 2015-05-13 18:00 | N | N | L to J: stringing new 1064/1065L in close proximity to line | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 373S Madden | 2015-05-11 07:00 | 2015-05-11 19:00 | N | N | transformer,switchgear, station upgrade | Station |  |  | For Information Only
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2015-05-11 07:00 | 2015-05-14 17:00 | N | N | full metering upgrade | Transformer |  |  | For Information Only
EPCOR | Poundmaker 2403 (Poundmaker) | 2015-05-11 07:00 | 2015-05-13 18:00 | N | Y | Alstrom retrofit of breaker | Circuit Breaker |  |  | 240 kV
EPCOR | 72RV6 (Rossdale - 511s Victoria),Rossdale RV722 (Rossdale) | 2015-05-11 07:00 | 2015-05-11 18:00 | N | N | breaker fail upgrade | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee) | 2015-05-11 07:30 | 2015-05-14 17:00 | N | Y | install WATL RAS, aerial maintenance and upgrading, RAS scheme panel | Line |  |  | Over/Under Voltage, Restricts Generation, Creates Radial Feeds, 500 kV
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan) | 2015-05-11 08:00 | 2015-05-14 17:30 | N | N | install slip on CTs on T1, install new T1 A; protection | Transformer |  |  | For Information Only
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2015-05-11 08:00 | 2015-05-15 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2015-05-11 08:00 | 2015-05-14 16:00 | N | N | replace main breaker contacts | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32) | 2015-05-11 08:00 | 2015-05-15 16:00 | N | N | doble | Transformer |  |  | For Information Only
EPCOR | E511s VictoriaT3 (511s Victoria) | 2015-05-11 08:00 | 2015-05-15 17:00 | N | N | doble testing | Transformer |  |  | For Information Only
ATCO | 800s 701T (800s Friedenstal) | 2015-05-11 09:00 | 2015-05-12 16:00 | N | N | major testing PM and PCB samples | Transformer |  | Complete 701T Major Testing PM and PCB Samples Work will entail major electrical testing of the transformer as well as testing the non-elecrical protection for the unit. Also the bushing are suspected to have >50ppm PCB, an attempt will be made to obtain a sample from each bushing. Station load will be fed from 702T for the duration of the work | For Information Only
ATCO | 776s 601T (776s Richdale) | 2015-05-11 09:00 | 2015-05-11 16:00 | N | N | PCB sample from 601T maintenance tank and bushings | Transformer |  | 776S Richdale - PCB Sample from 601T Main Tank and Bushings | For Information Only
ALTALINK | 89s 1052 (89s Ellerslie) | 2015-05-11 10:00 | 2015-05-14 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 151s T2 (151s Strathmore),733L (151s Strathmore - 428S Namaka) | 2015-05-11 11:00 | 2015-05-12 17:00 | N | N | doble, SFRA, LTC maintenance | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 781L (172s Sherritt - 71s Lamoureux),172s 781W (172s Sherrit) | 2015-05-12 08:00 | 2015-05-12 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 276s 652 (276s Un Carb Prentiss),276s C1 (276s Prentiss) | 2015-05-12 08:00 | 2015-05-13 12:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 834L (384s Keystone - 320p Keephills),384s 834 (384s Keystone) | 2015-05-12 08:00 | 2015-05-13 16:00 | N | N | B protection replacement | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L11 (834s Wesley Creek - 813s Little Smoky) | 2015-05-12 08:25 | 2015-05-15 16:00 | N | N | forced outage | Line |  |  | 240 kV
ATCO | 930s SVC (930s Arcenciel) | 2015-05-12 09:00 | 2015-05-12 16:00 | N | Y | emergency repairs | Shunts |  | EMERGENCY REPAIRS required as both blowers were installed at the same time and have an equivalent amount of hours on each. (concern of second failure) Blower #1 is currently out of service due to worn bearings. Repair/Replace Blower #1 Bearings The Parts have now arrived 930S SVC Out of Service for the duration of the work | Pre-Condition
ATCO | 934s 901 (934s Blackfly) | 2015-05-12 09:00 | 2015-05-13 13:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and Operate BKR 901 at 934S Black Fly, Ring will be open no line outages. | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 934s 902 (934s Blackfly) | 2015-05-12 13:00 | 2015-05-13 17:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and Operate BKR 902 at 934S Black Fly, Ring will be open, no line outages. | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2015-05-13 01:00 | 2015-05-15 05:00 | N | N | spring line night washing | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2015-05-13 07:30 | 2015-05-15 18:00 | N | Y | L to J: install twin curlew slack span on future 1064L(L12) bay | Transformer, Bus, Shunts |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ALTALINK | 296s T3 (296s Rosyth) | 2015-05-13 08:00 | 2015-05-13 20:00 | N | N | Enbridge request to repair 296s28 | Transformer |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27) | 2015-05-13 08:00 | 2015-05-14 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 31.1C (ENMAX 31) | 2015-05-13 08:00 | 2015-05-15 16:00 | N | N | maintenance and hot spot repair | Shunts |  |  | Limits ATC
ENMAX | 5.1TR (ENMAX 5) | 2015-05-13 08:00 | 2015-05-14 16:00 | N | N | leak repair by manufacturer (Hico) | Transformer
ATCO | 802s 705C (802s Michichi Creek),802s 705 (802s Michichi Creek) | 2015-05-13 08:00 | 2015-05-13 12:00 | N | N | POW setting changes relay setting changes | Circuit Breaker, Shunts |  | 802S Michichi Creek - 705 POW Setting Changes Relay Setting Changes on BKR 705 POW Controller Breaker 705 must be open. Breaker 705 must remain open until setting changes are complete. | Pre-Condition, For Information Only
ALTALINK | 223s T1 (223s Strome) | 2015-05-13 08:00 | 2015-05-13 20:00 | N | N | Enbridge request for T1 isolation to remove equipment from their bus | Transformer |  |  | For Information Only
ALTALINK | 299s T1 (299s Kingman) | 2015-05-13 08:00 | 2015-05-13 12:00 | N | N | Enbridge request for T1 isolation | Transformer |  |  | For Information Only
ALTALINK | 108s T1 (108s Amelia) | 2015-05-13 08:00 | 2015-05-13 16:00 | N | N | install two new breaker into switchgear | Transformer |  |  | For Information Only
ATCO | 7L73 (829s Boucher Creek - 800s Friedenstal),800s 702 (800s Friedenstal) | 2015-05-13 08:30 | 2015-05-13 16:00 | N | N | complete partial PM on breaker 702 | Circuit Breaker, Line |  | Complete Partial PM on Breaker 702, 7L73 open ended for the duration of the work | Firm Load Loss, Creates Radial Feeds
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt),172s 709X (172s Sherrit) | 2015-05-13 08:30 | 2015-05-13 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 202L335) | 2015-05-13 10:11 | 2015-05-16 17:00 | N | N | forced outage due to fire in the area | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 368s T1 (368s Burdett) | 2015-05-13 12:00 | 2015-05-13 17:00 | N | N | TX filter oil leak and bird cover repair | Transformer
ALTALINK | 63s 1952 (63s Red Deer) | 2015-05-13 13:00 | 2015-05-13 17:00 | N | N | removing LTC low oil trip from the TX 4 | Circuit Breaker |  |  | For Information Only
ALTALINK | 535s 6552 (535s Joffre),535s C1 (535s Joffre) | 2015-05-13 13:00 | 2015-05-14 17:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition, Over/Under Voltage
ATCO | 770s 705C (770s Three Hills),770s 705 (770s Three Hills) | 2015-05-13 13:00 | 2015-05-13 16:00 | N | N | BKR 705 POW Relay Setting Changes. | Circuit Breaker, Shunts |  | BKR 705 POW Relay Setting Changes. BKR 705 must remain open until setting changes are complete. Breaker can be restored in 10 minutes. | Pre-Condition, For Information Only
EPCOR | Poundmaker 2401 (Poundmaker) | 2015-05-14 07:00 | 2015-05-16 18:00 | N | Y | retrofit of breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
BCH | 5L92 (Cranbrook - Selkirk) | 2015-05-14 07:00 | 2015-05-17 19:00 | Y | Y | replace insulators -- BC maintenance does not affect AB ATC | Line
ALTALINK | 897L (38s East Edmonton - 45s Bretona),45s 897 (45s Bretona) | 2015-05-14 08:30 | 2015-05-14 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 934s 905 (934s Blackfly) | 2015-05-14 09:00 | 2015-05-14 13:00 | N | Y | test | Circuit Breaker |  | Test and Operate BKR 905 at 934S Black Fly, Ring will be open no line outages. | 240 kV, Contingency Requires Mitigation
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal),800s 701 (800s Friedenstal) | 2015-05-14 09:00 | 2015-05-14 16:00 | N | N | complete partial PM on breaker 701, 7L75 open ended for the duration of the work | Line, Circuit Breaker |  | Complete Partial PM on Breaker 701, 7L75 open ended for the duration of the work | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 108S Amelia | 2015-05-14 10:00 | 2015-05-14 18:00 | N | N | install two new 25kV breakers into switchgear | Station
ATCO | 934s 906 (934s Blackfly) | 2015-05-14 13:01 | 2015-05-14 17:00 | N | Y | test | Circuit Breaker |  | Test and Operate BKR 906 at 934S Black Fly, Ring will be open, no line outages. | 240 kV, Contingency Requires Mitigation
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2015-05-14 14:00 | 2015-05-14 16:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 800s 501C (800s Friedenstal),800s 502C (800s Friedenstal),800s 501 (800s Friedenstal) | 2015-05-15 08:30 | 2015-05-15 15:00 | N | N | breaker testing and maintenance and testing the capacitor bank for failed wafers | Shunts, Circuit Breaker |  | Risk Assessment: No concern. Complete a Partial PM on Breaker 501...Breaker testing and maintenance will be completed as well as testing the capacitor bank for failed wafers. /Capacitor bank out of service for the duration of the work | For Information Only
ALTALINK, ENMAX | 37.82L (74s Janet - ENMAX 37),765L (74s Janet - 151s Strathmore),917L (74s Janet - 5s East Calgary) | 2015-05-16 07:00 | 2015-05-19 18:00 | N | Y | L to J: re-name line to new 937L bypass(917L no longer in service) & required for clearance to string new 937L bypass conductor over 37.82L & 765L | Line |  |  | 240 kV, Overload, Over/Under Voltage
ALTALINK | 668L (394s Empress - 562s Cypress) | 2015-05-16 08:00 | 2015-05-17 18:00 | N | N | 394s customer installing structure piling in close proximity to line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1064L (102s Langdon - 74s Janet) | 2015-05-16 08:00 | 2015-05-22 16:00 | N | N | In service date: May 22, 2015 | Line |  |  | 240 kV
ALTALINK | 528s T2 (528s Blue Trail Wind Farm) | 2015-05-16 08:00 | 2015-05-16 17:00 | N | Y | oil leak repair | Transformer |  |  | Restricts Generation
VISIONREQ | 354s T1 (354s Summerview) | 2015-05-17 08:00 | 2015-05-17 17:00 | N | Y | oil leak repair | Transformer |  |  | Restricts Generation
ALTALINK | 310P Sundance,902L (19s Wabamun - 310p Sundance) | 2015-05-17 20:00 | 2015-05-17 21:00 | N | Y | check and tests | Line, Station |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 879s T2 (879s Scotford Upgrader),ALC02L (409s Shell Scotford - 879s Scotford Upgrader) | 2015-05-18 07:00 | 2015-05-30 17:30 | N | N | replace switches | Transformer, Line |  | No system concerns, Replace 702TD and 702T., ALCO1S, 879s, and 402s will be radial fed. ALCO2L will be opened at 409S SCOTFORD, When 702TD install and BKR 252 maintenance is complete on May 30th, we will shrink the GOI down to 702TD and and re-energize ALC-02L and 144kV Bus 2.
ALTALINK | 409s 110 (409s Shell Scotford) | 2015-05-18 07:00 | 2015-05-30 17:30 | N | N | 702TD & ALC02 outage at 879s | Circuit Breaker
ATCO | 879s T2 (879s Scotford Upgrader) | 2015-05-18 08:00 | 2015-08-04 17:30 | N | N | replace switches | Transformer |  | No system concerns, Replace 702TD and 702T., ALCO1S, 879s, and 402s will be radial fed. ALCO2L will be opened at 409S SCOTFORD, When 702TD install and BKR 252 maintenance is complete on May 30th, we will shrink the GOI down to 702TD and and re-energize ALC-02L and 144kV Bus 2.
VISIONREQ | 354s T3 (354s Summerview) | 2015-05-18 08:00 | 2015-05-18 17:00 | N | Y | oil leak repair | Transformer |  |  | Restricts Generation
ENMAX | 15.2TR (ENMAX 15) | 2015-05-18 08:00 | 2015-05-29 16:00 | N | N | SEL 351 feeder relay upgrade | Transformer
ALTALINK | 396s T1 (396s Pincher Creek),185L (396s Pincher Creek - 379s Shell Canada Waterton),514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198) | 2015-05-19 07:00 | 2015-05-28 17:00 | N | Y | station switches & PT replacement project | Transformer, Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker 2401 (Poundmaker) | 2015-05-19 07:00 | 2015-05-24 18:00 | N | Y | retrofit of breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s C1 (17s Benalto),17s 16 (17s Benalto) | 2015-05-19 07:30 | 2015-05-21 17:00 | N | Y | 240 kV breaker maintenance | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2015-05-19 08:00 | 2015-05-26 14:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 942L (681s Bannerman - 71s Lamoureux) | 2015-05-19 08:00 | 2015-06-02 17:00 | N | Y | cut in new 681s Bannerman, renumber portion of line between 681s - 12s as 1061L | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2015-05-19 08:00 | 2015-05-21 16:00 | N | N | SCADA upgrade project | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.2TR (ENMAX 37) | 2015-05-19 08:00 | 2015-05-22 16:00 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 43.2TR (ENMAX 43) | 2015-05-19 08:00 | 2015-05-22 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 36.81L (44s Bearspaw - ENMAX 36) | 2015-05-19 08:00 | 2015-05-19 16:00 | N | N | spring substation washing | Line
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2015-05-19 08:00 | 2015-06-02 16:00 | N | Y | replace PT2221 & 19s246, and switch 19s98 | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
STROBE | 239s T2 (239s Castle River) | 2015-05-19 08:00 | 2015-05-19 17:00 | N | Y | oil leak repair | Transformer |  |  | Restricts Generation
EPCOR | E511s VictoriaT3 (511s Victoria) | 2015-05-19 08:00 | 2015-05-22 17:00 | N | N | doble testing | Transformer |  |  | For Information Only
ALTALINK | 54L (123s Banff - 177s West Cascade) | 2015-05-19 09:00 | 2015-05-19 14:00 | N | N | commission motor mech on 177s20 | Line
ATCO | 934s 905 (934s Blackfly) | 2015-05-19 09:00 | 2015-05-19 13:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and Operate BKR 905 at 934S Black Fly, Ring will be open no line outages. | 240 kV, Contingency Requires Mitigation
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2015-05-19 09:00 | 2015-05-20 18:00 | N | N | bird cover-up install | Transformer |  |  | For Information Only
ATCO | 6L97 (735s Swan River - 739s Edith Lake),739s 603 (739s Edith Lake) | 2015-05-19 10:00 | 2015-05-19 15:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | 6L97 WILL BE REMOVED FROM SERVICE @ 739S EDITH LAKE FOR MTCE ON BKR 603 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 702L (137s Sedgewick - 757s Battle River) | 2015-05-19 10:00 | 2015-05-22 15:00 | N | Y | line maintenance - component replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s 47 (370s North Lethbridge) | 2015-05-19 10:00 | 2015-05-19 17:00 | N | Y | breaker failed to open | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 250p11 (250p Bighorn) | 2015-05-19 11:59 | 2015-05-21 06:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 262S Rocky Mountain House,262s T2 (262s Rocky Mountain House) | 2015-05-19 12:00 | 2015-05-22 17:00 | N | N | full metering upgrade | Station, Transformer |  |  | For Information Only
ATCO | 934s 906 (934s Blackfly) | 2015-05-19 13:00 | 2015-05-19 17:00 | N | Y | test and operate breaker | Circuit Breaker |  | Test and Operate BKR 906 at 934S Black Fly, Ring will be open, no line outages. | 240 kV, Contingency Requires Mitigation
ALTALINK | 434s T3 (434s East Stony Plain) | 2015-05-19 13:00 | 2015-05-21 17:00 | N | N | repair leaks | Transformer |  |  | For Information Only
ALTALINK | 514L (513s Lundbreck - 514L198) | 2015-05-20 07:00 | 2015-05-23 18:00 | N | N | station switches & PT replacement project | Line |  |  | Pre-Condition
ALTALINK | 332s 352 (332s Ellis),332s C1 (332s Ellis) | 2015-05-20 07:00 | 2015-05-21 17:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 708L (233s Beamer - 708L88N) | 2015-05-20 07:30 | 2015-05-20 17:30 | N | N | install helicopter markers | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2015-05-20 08:00 | 2015-06-05 16:00 | N | N | Glenmore & Ogden overpass, line relocation install new steel double circuit structures | Line
ALTALINK | 370s 56 (370s North Lethbridge) | 2015-05-20 08:00 | 2015-05-21 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 803s T1 (803s Lambton) | 2015-05-20 08:00 | 2015-06-03 18:00 | N | Y | capacity upgrade project. transformers replacement project | Transformer |  |  | 240 kV
ATCO | 914s 701T (914s Bindloss) | 2015-05-20 08:00 | 2015-05-20 23:59 | N | N | bird proofing | Transformer |  | 914S Bindloss Outage Request for Bird Proofing
ALTALINK | 17s 92 (17s Benalto) | 2015-05-20 08:00 | 2015-05-20 17:00 | N | N | breaker maintenance | Circuit Breaker
ALTALINK | 917L (74s Janet - 5s East Calgary),5s 1652 (5s East Calgary),5s 1552 (5s East Calgary) | 2015-05-20 18:01 | 2015-05-27 17:00 | N | Y | L to J: re-name line to new 937L bypass(917L no longer in service) & required for clearance to string new 937L bypass conductor over | Line, Circuit Breaker |  |  | 240 kV
EPCOR | 987S Cloverbar | 2015-05-21 04:00 | 2015-05-29 16:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ATCO | 7L194 (875s Algar - 2009s Willow Lake) | 2015-05-21 07:00 | 2015-05-25 17:30 | N | N | tie in new sections of 7L194 and the new 7L170 with jumpers close to Dawes sub | Line |  | Tie in new sections of 7L194 and the new 7L170 with jumpers close to Dawes sub. Install temporary protection settings only if required. | Pre-Condition
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2015-05-21 07:00 | 2015-05-21 18:00 | N | Y | ECTP: replace jumper on QQ tower near 74s | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2015-05-21 08:00 | 2015-05-22 12:00 | N | N | remove mobile from 733L | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 170L (632s Russell - 799s Coleman) | 2015-05-21 08:00 | 2015-05-21 16:00 | N | Y | replace broken crossarm | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds, Impacts RAS
ATCO | 7L80 (740s H.R.Milner - 857s Kakwaridge) | 2015-05-21 09:00 | 2015-05-24 17:00 | N | N | line clearance issue mitigation | Line |  |  | Limits Ratings, Firm Load Loss
ALTALINK | 510s T2 (510s Sunnybrook) | 2015-05-21 12:00 | 2015-05-22 12:00 | N | N | connect HVDC station service | Transformer
ALTALINK | 967L (59s Peigan - 370s North Lethbridge),968L (59s Peigan - 370s North Lethbridge) | 2015-05-22 08:00 | 2015-05-29 18:00 | N | Y | preparation for 967L/968L cut-in for Windy Flats project | Line |  | Windy Flats: Salvage tangent and install two QQ towers to enable 967/968L to be cut into Windy Flats. 968L will not be strung into Windy Flats on this outage but will be jumpered through. | 240 kV, Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 937L (102s Langdon - 74s Janet) | 2015-05-23 06:30 | 2015-05-27 18:00 | N | Y | L to J: 937L bay swap from L17 to new 937L 240kv U/G bypass. In conjunction with 917L outage and renaming (new 1064L in service, ATC not affected) | Line |  |  | 240 kV
ALTALINK | 727L (74s Janet - 1140s Temp) | 2015-05-23 06:30 | 2015-05-26 19:00 | N | N | L to J: stringing new portion of 937L in close proximity to line | Line |  |  | Over/Under Voltage
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2015-05-23 07:00 | 2015-05-24 17:00 | N | N | 74s IP work: Replace 74s57 and strain insulators and 74s93. | Transformer, Bus, Shunts |  |  | 240 kV
ALTALINK | 826L (701s Blue Ridge Lumber - 77s Sagitawah),77s 752 (77s Sagitawah),77s 452 (77s Sagitawah) | 2015-05-23 08:00 | 2015-05-23 17:00 | N | N | SCADA upgrade project | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 1107L (ENMAX 65 - 237s Foothills),1106L (ENMAX 65 - 237s Foothills) | 2015-05-23 08:00 | 2015-05-26 16:00 | N | N | In service date: May 25, 2015 | Line |  |  | 240 kV
ALTALINK | 237S Foothills | 2015-05-23 08:00 | 2015-05-26 16:00 | N | N | In service date: May 25, 2015 | Station |  |  | 240 kV
EPCOR | 987s T2 (987s Clover Bar),987s T4 (987s Clover Bar),987s C2405 (987s Clover Bar),987s C2406 (987s Clover Bar) | 2015-05-23 08:00 | 2015-05-23 14:00 | N | Y | emergency pole repair | Transformer, Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 183s T1 (183s Underwood) | 2015-05-23 08:00 | 2015-05-25 18:00 | N | N | replace conservator tank | Transformer |  |  | For Information Only
ALTALINK | 701s T1 (701s Blue Ridge Lumber) | 2015-05-23 08:00 | 2015-05-23 17:00 | N | N | doble, SFRA | Transformer |  |  | For Information Only
ATCO | 767s 602T (767s Oyen) | 2015-05-24 08:00 | 2015-05-24 15:00 | N | N | transformer testing | Transformer |  | 767S Oyen TRANSFORMER CLASS2 MAJOR TESTING | For Information Only
ALTALINK | 133S Stelco Edmonton | 2015-05-25 07:00 | 2015-05-29 16:00 | N | N | customer request for grounding and switching | Station |  |  | For Information Only
EPCOR | Poundmaker 2402 (Poundmaker) | 2015-05-25 07:00 | 2015-05-30 18:00 | N | Y | Alstrom retrofit of breaker | Circuit Breaker |  |  | 240 kV
ALTALINK | 5s T1 (East Calgary),833L (ENMAX 2 - ENMAX 12),5s 833W (5s East Calgary) | 2015-05-25 08:00 | 2015-06-09 16:00 | N | Y | move 833L to new ENMAX C2sGIS | Line, Circuit Breaker, Transformer |  | a. Transfer and dead end exg. 833L to pothead structure. Salvage 3 spans of exg. 833L into 2 sub. HV Breaker Inspection (2 days/BKR maint on 12B138-833L) b. Disconnection of slack span to old 2sub Note: 5sT1 will remain OOS until it is energized to the new GIS | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 133L (19s Wabamun - 133L697A) | 2015-05-25 08:00 | 2015-05-28 16:00 | N | N | replace switch 19s1334 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.2TR (ENMAX 34) | 2015-05-25 08:00 | 2015-05-29 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2015-05-25 08:00 | 2015-05-25 12:00 | N | N | installing traffic signal structures on intersection near line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2752 (74s Janet) | 2015-05-25 08:00 | 2015-05-26 17:00 | N | N | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 166s T2 (166s Dow Chemical Fort Saskatchewan) | 2015-05-25 08:00 | 2015-05-29 17:30 | N | N | protection work | Transformer |  | Install slip-on CTs and wiring to Xmer cabinet, Cutover and commission of T1 protection system and slip on CTs. Trip checks from T2A & T1A prot to CP234 | For Information Only
ALTALINK | 238S Shell Harmattan | 2015-05-25 09:00 | 2015-05-27 12:00 | N | N | customer request for station outage | Station |  |  | For Information Only
ALTALINK | 69s T5 (69s North Barrhead) | 2015-05-25 09:00 | 2015-05-28 17:00 | N | N | attach temp cables | Transformer |  |  | For Information Only
ALTALINK | 702L (377s Hardisty - 137s Sedgewick) | 2015-05-25 10:00 | 2015-05-29 15:00 | N | Y | line maintenance - component replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L85 (804s Wintering Hills - 803s Bullpound),7L85 (803s Bullpound - 801s Anderson) | 2015-05-25 10:00 | 2015-05-29 15:00 | N | N | 7L85 protection upgrade | Line |  | 801S Anderson 7L85 Protection Upgrade... Removal of existing 7L85 Distance Protection. Installation and commissioning of new protection. | Creates Radial Feeds
ALTALINK | 746s T1 (746s Sherwood Park) | 2015-05-25 10:00 | 2015-05-28 17:00 | N | N | transformer, breaker & switch maintenance | Transformer |  |  | For Information Only
ATCO | 849s 902 (849s Joslyn Creek) | 2015-05-25 13:00 | 2015-05-26 17:00 | N | Y | breaker test | Circuit Breaker |  | Test and Operate BKR 902 at 849S Joslyn, Ring will be open, no line outages. | 240 kV
Medicine Hat | MH69s2 MH69_202 (MH69s2 North Industrial),MH69s6 MH69_602 (MH69s6 Riverview) | 2015-05-26 07:00 | 2015-05-26 11:00 | N | N | emergency repair on a single structure | Circuit Breaker
ATCO | 7L03 (7L03D3 - 731s Elmworth) | 2015-05-26 07:00 | 2015-05-27 18:00 | N | N | emergency outage to fix some structure issues | Line |  | Emergency outage to fix some structure issues once fix is in will be able to issue the higher rating for the line. | Pre-Condition, Overload
ALTALINK | 534S Eckville | 2015-05-26 08:00 | 2015-06-05 08:01 | N | N | Fortis request for advice to open feed to 3684T line and install switch for planned mobile install | Station
ENMAX | ENMAX 11,11.4TR (ENMAX 11) | 2015-05-26 08:00 | 2015-05-26 16:00 | N | N | taking measurements on the 25kV switchgear for future cell addition | Station, Transformer
ALTALINK | 225L (385s Spring Coulee - 225s Magrath) | 2015-05-26 09:00 | 2015-05-26 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225AL (313s Raymond Reservoir - 225L tap),225L (67s Stirling - 225AL tap),225L (225s Magrath - 225AL tap) | 2015-05-26 12:00 | 2015-05-26 15:00 | N | Y | high load move | Line |  |  | Restricts Generation, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2015-05-27 08:00 | 2015-05-27 18:00 | N | Y | L to J: install twin curlew slack span on future 1065L(L17) bay | Transformer, Shunts, Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 77s 752 (77s Sagitawah) | 2015-05-27 08:00 | 2015-05-27 16:00 | N | N | SCADA Upgrade Project | Circuit Breaker |  |  | For Information Only
ATCO | 849s 903 (849s Joslyn Creek) | 2015-05-27 09:00 | 2015-05-28 13:00 | N | Y | test and operate breaker 902 at 849S Joslyn | Circuit Breaker |  | Test and Operate BKR 902 at 849S Joslyn, Ring will be open, no line outages. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 869s 701T (869s Seal Lake) | 2015-05-27 09:00 | 2015-05-27 15:30 | N | N | emergency outage to investigate high oil indication on conservator tank | Transformer
ATCO | 849s 906 (849s Joslyn Creek) | 2015-05-27 13:00 | 2015-05-28 17:00 | N | Y | test and operate breaker 906 at 849S Joslyn | Circuit Breaker |  | Test and Operate BKR 906 at 849S Josyln, Ring will be open no line outages. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 727L (74s Janet - 1140s Temp) | 2015-05-28 06:30 | 2015-05-29 18:30 | N | N | L to J: stringing new portion of 1065L in close proximity to line | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 35s T2 (35s Rundle) | 2015-05-28 07:00 | 2015-05-28 17:00 | N | Y | failed CT | Transformer |  |  | Restricts Generation
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2015-05-28 07:30 | 2015-05-28 17:30 | N | Y | remove marker cones over river valley | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2015-05-28 08:00 | 2015-05-28 16:00 | N | N | repair switch 87 | Line
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),B138-3.84 (ENMAX 13) | 2015-05-28 08:00 | 2015-05-28 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2752 (74s Janet) | 2015-05-28 08:00 | 2015-05-28 17:00 | N | N | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2) | 2015-05-28 08:00 | 2015-05-29 19:00 | N | N | emergency outage to fix some structure issues | Line |  | Emergency outage to fix some structure issues once fix is in will be able to issue the higher rating for the line. | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),72CK13 (987s Clover Bar - Kennedale) | 2015-05-29 07:00 | 2015-05-29 17:00 | N | N | offload bus 4 | Line |  |  | Pre-Condition
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2015-05-29 07:30 | 2015-05-29 17:30 | N | Y | remove marker cones over river valley | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
NOVAC | 330L2 (535s Joffre - I-330s Nova Corp Plant) | 2015-05-29 08:00 | 2015-06-03 16:00 | N | Y | complete tie in work - Nova expansion project | Line
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s 25 (391s Balzac) | 2015-05-29 08:30 | 2015-05-29 17:00 | N | Y | replace dead end insulators off 391s25 | Circuit Breaker, Line |  |  | Restricts Generation
ALTALINK | 80L (194s South Red Deer - 63s Red Deer),194s 80X (194s South Red Deer),63s 80N (63s Red Deer) | 2015-05-29 13:00 | 2015-06-08 23:59 | N | N | line rebuild, protection work & renaming as 426L | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 968L (59s Peigan - 370s North Lethbridge) | 2015-05-29 18:01 | 2015-06-04 17:00 | N | Y | Emergency 240kV switch repair on Jun 4 | Line |  |  | 240 kV, Overload, Over/Under Voltage
ALTALINK, ENMAX | 74s C2 (74s Janet),74s C1 (74s Janet),74s T1 (74s Janet),37.82L (74s Janet - ENMAX 37),765L (74s Janet - 151s Strathmore),727L (74s Janet - 1140s Temp),813s Little Smoky 144kV Bus 1 | 2015-05-30 05:00 | 2015-05-30 08:00 | N | Y | disconnect PTs from bus to allow addition of new station service PTs to bus & create open point A | Transformer, Bus, Line, Shunts |  |  | 240 kV, Pre-Condition, Overload, Limits ATC
ALTALINK, NOVAC | 535s 5952 (535s Joffre),535s 5852 (535s Joffre),330L2 (535s Joffre - I-330s Nova Corp Plant) | 2015-05-30 07:00 | 2015-06-03 17:00 | N | Y | channel 'B' and 'B' line protection upgrade | Circuit Breaker, Line |  |  | Restricts Generation
ALTALINK | 535s97N (535s Joffre) | 2015-05-30 07:00 | 2015-06-03 17:00 | N | N | cut in 196s (new Nova sub) | Switch
ALTALINK | 74s C2 (74s Janet),74s C1 (74s Janet),74s T1 (74s Janet),765L (74s Janet - 151s Strathmore),74s 76 (74s Janet) | 2015-05-30 08:00 | 2015-05-31 21:00 | N | Y | disconnect PTs from bus to allow addition of new station service PTs to bus | Transformer, Line, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1065L (102s Langdon - 74s Janet) | 2015-05-30 08:00 | 2015-06-02 16:00 | N | N | In service date: June 1, 2015 | Line |  |  | 240 kV
ALTALINK | 681S Bannerman | 2015-05-30 08:00 | 2015-06-03 16:00 | N | N | In service date: June 2, 2015 | Station |  |  | 240 kV
ENMAX | 13.2TR (ENMAX 13) | 2015-05-31 08:00 | 2015-06-30 16:00 | N | N | 13.2TR HV bushing replacement | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 74s C2 (74s Janet),74s C1 (74s Janet),74s T1 (74s Janet),37.82L (74s Janet - ENMAX 37),765L (74s Janet - 151s Strathmore),74s 76 (74s Janet),727L (74s Janet - 1140s Temp),813s Little Smoky 144kV Bus 1 | 2015-05-31 21:00 | 2015-05-31 23:59 | N | Y | Close Open Point A and energize new PTs and SS2 | Transformer, Bus, Line, Shunts, Circuit Breaker |  |  | 240 kV, Limits ATC
EPCOR | Poundmaker 2404 (Poundmaker) | 2015-06-01 07:00 | 2015-06-06 18:00 | N | Y | Alstrom retrofit of breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Syncrude | Aurora T1 | 2015-06-01 07:30 | 2015-06-14 20:00 | N | Y | T1 transformer outage due to cap banks project energization | Transformer |  |  | 240 kV, For Information Only
CNRL | 838s 75_BC_1801 (838s Horizon Mining) | 2015-06-01 08:00 | 2015-06-07 15:00 | N | Y | maintenance, electrical testing and protection testing | Circuit Breaker
ALTALINK | 89s 652 (89s Ellerslie) | 2015-06-01 08:00 | 2015-06-04 17:00 | N | Y | replacement of breaker fail protection for 89s652 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 163s T1 (163s Amoco Empress) | 2015-06-01 08:00 | 2015-06-21 16:00 | N | Y | customer request | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 902L (19s Wabamun - 310p Sundance),905L (19s Wabamun - 37s North Calder),19S Wabamun 240kV Bus B | 2015-06-01 08:00 | 2015-06-02 16:00 | N | Y | test and exercise SCADA control of 19s51, 19s52, 19s94. | Bus, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 918L (17s Benalto - 162s Beddington) | 2015-06-01 08:00 | 2015-06-04 09:00 | N | Y | outage to cut in new Altalink sub 281s Johnson | Line |  |  | 240 kV
ENMAX | 15.1TR (ENMAX 15) | 2015-06-01 08:00 | 2015-06-02 16:00 | N | N | install oil dry out processor on transformer | Transformer |  |  | For Information Only
ENMAX | 32.2TR (ENMAX 32) | 2015-06-01 08:00 | 2015-06-05 16:00 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 43.1TR (ENMAX 43) | 2015-06-01 08:00 | 2015-06-05 16:00 | N | N | LTC maintenance on X and Y windings | Transformer |  |  | For Information Only
ALTALINK | 172s T2 (172s Sherritt Gordon),172s 72 (172s Sherrit) | 2015-06-01 08:00 | 2015-06-04 17:00 | N | N | bushing replacement | Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 310p 2152 (310p Sundance),310p 2052 (310p Sundance) | 2015-06-01 08:00 | 2015-06-30 16:00 | N | Y | replace breaker control modules, breaker fail relays, and replace CTs | Circuit Breaker |  |  | 240 kV
NOVAC | 330L4 (196s Nova - 330L2 tap) | 2015-06-01 08:00 | 2015-06-05 16:00 | N | N | In service date: June 3, 2015 | Line
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2015-06-01 08:30 | 2015-06-01 10:30 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 849s 904 (849s Joslyn Creek) | 2015-06-01 09:00 | 2015-06-02 13:00 | N | Y | test and operate 904 at 849S Joslyn | Circuit Breaker |  | Test and Operate BKR 904 at 849S Joslyn, Ring will be open, no line outages. | 240 kV
ATCO | 728s 701T (728s Mercer Hill),728s 701 (728s Mercer Hill) | 2015-06-01 09:00 | 2015-06-04 15:00 | N | N | commission bus lockout relay | Transformer, Circuit Breaker |  | Commission bus lockout relay. maint on 701T and 701 June 1 -switch mobile sub into service (WO # 4375899) -GOI 701T and 701 isolation points 501TD and 7LA39D2 (WO # 4375899) June 4 | For Information Only
ALTALINK | 708L (71s Lamoureux - 708L88X) | 2015-06-01 09:00 | 2015-06-03 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
CNRL | 838s 75-TR-1701 (838s Horizon Mining) | 2015-06-01 10:00 | 2015-06-07 15:00 | N | Y | maintneance | Transformer |  |  | 240 kV
ALTALINK | 150L (20s Ghost - 150L46),20s 150 (20s Ghost) | 2015-06-01 10:00 | 2015-06-01 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 1652 (89s Ellerslie) | 2015-06-01 10:00 | 2015-06-02 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, TRANSALTA | 166s T1 (166s Dow Chemical Fort Saskatchewan),862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons),899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen) | 2015-06-01 10:00 | 2015-06-06 07:59 | N | N | replace 166s16 PTs, 138 bus differential replacement | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 849s 905 (849s Joslyn Creek) | 2015-06-01 13:00 | 2015-06-02 17:00 | N | Y | test and operate breaker 905 at 849S Josyln | Circuit Breaker |  | Test and Operate BKR 905 at 849S Josyln, Ring will be open no line outages. | 240 kV, Contingency Requires Mitigation
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2015-06-02 08:00 | 2015-06-03 17:00 | N | N | change some poles that are bad | Line |  | GOI for 7L171 to change some poles that are bad. | Creates Radial Feeds
ALTALINK | 164s T2 (164s Empress Liquids) | 2015-06-02 08:00 | 2015-06-03 17:00 | N | N | oil leak repair | Transformer |  |  | For Information Only
ENMAX | 162s 138-RB82 (162s Beddington) | 2015-06-02 08:00 | 2015-06-02 12:00 | N | N | dashpot check | Circuit Breaker |  |  | For Information Only
ATCO | 859s 702T (859s Primrose) | 2015-06-02 08:00 | 2015-06-02 19:00 | N | N | inpsection | Transformer |  |  | For Information Only
VISIONREQ | 354s DVAR1 (354s Summerview) | 2015-06-02 08:00 | 2015-06-03 16:00 | N | Y | reapir | Shunts |  |  | For Information Only
ALTALINK | 510s T1 (510s Sunnybrook) | 2015-06-02 08:00 | 2015-06-03 17:00 | N | N | connect HVDC station service | Transformer
ALTALINK | 853L (504s Queenstown - 853L76A) | 2015-06-02 08:00 | 2015-06-08 18:00 | N | N | line component replacement | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 138-RB83 (162s Beddington) | 2015-06-02 12:00 | 2015-06-02 16:00 | N | N | dashpot check | Circuit Breaker |  |  | For Information Only
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2015-06-02 16:00 | 2015-06-16 16:00 | N | Y | replace PT1096 & 19s243, Replace 19s902 CTs and switch 19s53 | Line |  |  | 240 kV, Pre-Condition, Overload
ATCO | 849s 907 (849s Joslyn Creek),75-PLH-901 (838s Horizon Mining - 849s Joslyn) | 2015-06-03 07:00 | 2015-06-03 17:30 | N | N | SPS modifications and testing | Circuit Breaker, Line |  | 75-PLH-901 will be open ended at 849s, Special protection scheme (SPS) modifications and testing to Bkr 907. No Study Concerns | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 814s T2 (814s Bellamy) | 2015-06-03 07:00 | 2015-06-05 18:00 | N | N | A protection emergency repair | Transformer
ALTALINK | 159s T2 (159s Colinton) | 2015-06-03 07:00 | 2015-06-04 17:30 | N | N | drilling environmental test holes beside transformer | Transformer
ATCO | 875S Algar,7L194 (875s Algar - 2009s Willow Lake),7L38 (875s Algar - 917s Horse River) | 2015-06-03 07:00 | 2015-06-07 17:30 | N | N | complete construction wiring, commissioning & maintenance | Station, Line |  | complete substation outage to complete construction wiring, commissioning and maintenance. 5L304 load will be transferred to another sub on the 25kV system, Alternate AC source will be provided to supply site station service, Pembina Pipeline will be OOS (co-ordinated with the customer). No further risk to the system as 7L194 already OOS under permit 2-32346 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 844s 701T (844s AEC Mill),844s 702T (844s AEC Mill) | 2015-06-03 07:00 | 2015-06-03 20:00 | N | N | breaker maintenance | Transformer |  | Maintenance on Bkr 703, 704, 701T, 702T AND 13.8KV BUS @ 844S Proceed after issuing Condition guarantee 2-32955
EPCOR | Rossdale RV722 (Rossdale) | 2015-06-03 07:00 | 2015-06-03 18:00 | N | N | breaker fail upgrade/bushing inspection | Circuit Breaker |  |  | Pre-Condition
Saskpower | Sask Power A1P,Sask Power P2P | 2015-06-03 08:00 | 2015-06-10 18:00 | N | N | stringing new PQ4 conductor | Line
ENMAX | 162s 138-RB84 (162s Beddington) | 2015-06-03 08:00 | 2015-06-03 12:00 | N | N | dashpot check | Circuit Breaker
NOVAC | 330L1 (I-330s Nova Corp Plant - 535s Joffre) | 2015-06-03 08:00 | 2015-06-08 16:00 | N | Y | complete tie in work - Nova expansion project | Line |  |  | For Information Only
ENMAX | 162s 138-RB85 (162s Beddington) | 2015-06-03 12:00 | 2015-06-03 16:00 | N | N | dashpot check | Circuit Breaker |  |  | For Information Only
ALTALINK | 74s C2 (74s Janet) | 2015-06-03 13:00 | 2015-06-04 08:59 | N | N | warranty work | Shunts |  |  | Limits ATC
ALTALINK, NOVAC | 535s 5652 (535s Joffre),535s 5552 (535s Joffre),330L1 (I-330s Nova Corp Plant - 535s Joffre),535s96N (535s Joffre) | 2015-06-03 17:10 | 2015-06-08 17:00 | N | Y | channel 'A' and 'B' line protection upgrade & cut in new 196s Nova sub | Circuit Breaker, Line, Switch
ALTALINK | 515S Fedpipe Judy Creek | 2015-06-04 07:00 | 2015-06-05 19:00 | N | N | Customer request for isolation to add equipment | Station
ALTALINK | 708L (233s Beamer - 708L88N) | 2015-06-04 08:00 | 2015-06-05 15:00 | N | N | line maintenance | Line |  |  | Overload, Creates Radial Feeds
ALTALINK | 89s 252 (89s Ellerslie) | 2015-06-04 08:00 | 2015-06-04 10:00 | N | Y | trip test for new 89s652 breaker fail protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 510s T2 (510s Sunnybrook) | 2015-06-04 08:00 | 2015-06-05 17:00 | N | N | connect HVDC station service | Transformer |  |  | For Information Only
ALTALINK | 534s T1 (534s Eckville) | 2015-06-04 08:00 | 2015-06-30 17:00 | N | N | connect mobile to 758L | Transformer
ENMAX | 162s 138-RB80 (162s Beddington) | 2015-06-04 08:00 | 2015-06-04 12:00 | N | N | dashpot check | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 74s C2 (74s Janet) | 2015-06-04 09:00 | 2015-06-04 17:00 | N | N | warranty work | Shunts |  |  | For Information Only
AESO, Medicine Hat | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2015-06-04 09:00 | 2015-06-04 12:00 | N | N | high load escort | Line |  |  | For Information Only
CNRL | 838s 75-BC-1911 (838s Horizon Mining) | 2015-06-04 09:00 | 2015-06-04 11:00 | N | Y | perform auto synchronization | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 918L (17s Benalto - 162s Beddington) | 2015-06-04 09:01 | 2015-06-13 17:00 | N | Y | outage to cut in new Altalink sub 281s Johnson | Line |  |  | 240 kV
ALTALINK | 89s 952 (89s Ellerslie) | 2015-06-04 10:01 | 2015-06-04 12:00 | N | Y | trip test for new 89s652 breaker fail protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
CNRL | 842s 75-1903 (842s Horizon Upgrading) | 2015-06-04 11:00 | 2015-06-04 13:00 | N | Y | perform auto synchronization | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 162s 138-RB81 (162s Beddington) | 2015-06-04 12:00 | 2015-06-04 16:00 | N | N | dashpot check | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 89s 1352 (89s Ellerslie) | 2015-06-04 12:01 | 2015-06-04 14:00 | N | Y | trip test for new 89s652 breaker fail protection | Circuit Breaker |  |  | 240 kV
ALTALINK | 89s 1752 (89s Ellerslie) | 2015-06-04 14:01 | 2015-06-04 16:00 | N | Y | trip test for new 89s652 breaker fail protection | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 2052 (89s Ellerslie) | 2015-06-04 16:01 | 2015-06-04 17:00 | N | Y | trip test for new 89s652 breaker fail protection | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 752 (89s Ellerslie) | 2015-06-04 17:01 | 2015-06-04 19:00 | N | Y | trip test for new 89s652 breaker fail protection | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 767L (320p Keephills - 767L167A) | 2015-06-05 07:00 | 2015-06-05 19:00 | N | N | required for drag line move | Line
ALTALINK | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2015-06-05 07:00 | 2015-07-13 18:00 | N | Y | line refurbishment / upgrade | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 33s6 (33s Spray) | 2015-06-05 09:00 | 2015-06-05 16:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
CNRL | 838s 75-TR-2801 (838s Horizon Mining) | 2015-06-06 08:00 | 2015-06-08 15:00 | N | Y | maintenance, electrical testing and protection testing | Circuit Breaker |  |  | 240 kV
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24) | 2015-06-06 08:00 | 2015-06-06 16:00 | N | Y | 24.1TR MD maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
NOVAC | 196S Nova Chem | 2015-06-06 08:00 | 2015-06-09 16:00 | N | N | In service date: June 8, 2015 | Station
SUNCOR | SCR1 Poplar Creek Generator Test | 2015-06-06 08:00 | 2015-06-06 16:00 | N | N | unit 5 test after major overhaul | Unit
ALTALINK | 281S Johnson | 2015-06-06 08:00 | 2015-06-12 16:00 | N | N | In service date: June 11, 2015 | Station |  |  | 240 kV
ALTALINK, TRANSALTA | 166s T1 (166s Dow Chemical Fort Saskatchewan),166s T2 (166s Dow Chemical Fort Saskatchewan),707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan),862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons),899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen) | 2015-06-06 08:00 | 2015-06-09 07:59 | N | N | remove bus protection from service, perform CT cutovers & Trip test of equipment for new bus protection | Line, Transformer |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2015-06-06 16:00 | 2015-07-17 16:00 | N | N | breaker racked out | Line
EPCOR | NamaoT3 (Namao) | 2015-06-08 07:00 | 2015-06-14 18:00 | N | N | replace damaged cap disc | Transformer |  |  | For Information Only
ALTALINK | 725BL (725BL54 - 240s McBride Lake),725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2015-06-08 07:00 | 2015-06-09 18:00 | N | Y | Windy Flats: install new strs 608L9 and 725BL40 | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L38 (875s Algar - 917s Horse River) | 2015-06-08 07:00 | 2015-06-19 17:30 | N | N | 7L38 protection CT changes | Line |  | 7L38 protection CT changes. | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9),Enmax 31 B138-9.80 (ENMAX 31) | 2015-06-08 08:00 | 2015-06-15 21:00 | N | N | relocate existing 9.80L & 31.84L | Circuit Breaker, Line |  | Glenmore & Ogden Overpass. Relocate existing 9.80L & 31.84L. Install 8 new steel single circuit & 9 new steel double circuit structures. Salvage 26 spans of existing 9.80L & 31.84L. (** Same as 31.84L ) HV Breaker Inspection, Dashpot Inspection. Bulk oil | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.3TR (ENMAX 34) | 2015-06-08 08:00 | 2015-06-12 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 7.1TR (ENMAX 7) | 2015-06-08 08:00 | 2015-06-12 16:00 | N | N | doble test | Transformer
ALTALINK | 63s T2 (63s Red Deer) | 2015-06-08 08:00 | 2015-07-27 09:00 | N | Y | forced out | Transformer |  |  | 240 kV
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11) | 2015-06-08 08:00 | 2015-06-12 08:00 | N | N | transformer spill containment | Transformer
TRANSALTAGP | BOW1 Bow River Hydro | 2015-06-08 08:00 | 2015-06-23 23:00 | N | N | Spray 1 generator testing. Refer to the Op Plan binder for the commissioning plan. | Unit
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2015-06-08 08:00 | 2015-06-08 16:00 | N | N | breaker maintenance | Circuit Breaker
VISIONREQ, TRANSALTAW, ALTALINK | 354s DVAR1 (354s Summerview),354s DVAR2 (354s Summerview),528s TDVAR1 (528s Blue Trail Wind Farm),528s TDVAR2 (528s Blue Trail Wind Farm),528s TDVAR3 (528s Blue Trail Wind Farm),418s Ardenville DVAr | 2015-06-08 08:00 | 2015-06-30 16:00 | N | Y | maintenance | Shunts, Transformer |  |  | For Information Only
ALTALINK | 234s T2 (234s Fort Assiniboine) | 2015-06-08 10:00 | 2015-06-08 11:00 | N | N | obtaining harmonic measurements | Transformer
ALTALINK | 234s T1 (234s Fort Assiniboine) | 2015-06-08 11:00 | 2015-06-08 12:00 | N | N | obtaining harmonic measurements | Transformer
ALTALINK | 234s T2 (234s Fort Assiniboine) | 2015-06-08 12:30 | 2015-06-08 13:30 | N | N | measuring harmonic distortion | Transformer
ALTALINK | 80L (194s South Red Deer - 63s Red Deer),194s 80X (194s South Red Deer),63s 80N (63s Red Deer) | 2015-06-09 01:00 | 2015-07-30 17:00 | N | N | line rebuild, protection work & 80L renaming as 426L | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 793s T1 (T793s Horse Creek) | 2015-06-09 07:00 | 2015-06-09 19:00 | N | N | replace Voltage Regulator | Transformer
ALTALINK | 793s T2 (T793s Horse Creek) | 2015-06-09 07:00 | 2015-06-09 19:00 | N | N | customer requested outage | Transformer
ALTALINK | 170s 1052 (170s Pike),170s 1152 (170s Pike) | 2015-06-09 09:00 | 2015-06-14 17:00 | N | Y | end to end protection testing for 1116L | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2015-06-09 09:00 | 2015-06-09 16:00 | N | N | replace 6L11PT2 standoff insulator | Line |  | Replace 6L11PT2 Standoff Insulator 6L11 marker cone replacement. replace marker cone 6L11D4 is DLO 742S FREEMAN LAKE WILL BE SUBJECTED TO A MOMENTARY OUTAGE TO OPEN 6L11D4 AMOCO -PENN WEST 1 780 809 0877 PENN WEST IS STARTING A PLANT SHUTDOWN ON JUNE 5 TO APPROX JUNE 15TH PLEASE CALL ON THE DAY TO LET THEM KNOW OF THE MOMENTARY OUTAGE | Over/Under Voltage, Creates Radial Feeds
ATCO | 946s 909 (946s Oakland) | 2015-06-09 10:00 | 2015-06-09 16:00 | N | N | Station Major Alarm, Low SF6 on east pole of 909 BKR. Need outage to top up SF6. | Circuit Breaker |  |  | 240 kV
ATCO | 9L07 (885s McMillan - 888s Dover) | 2015-06-10 07:00 | 2015-06-13 17:30 | N | Y | tie in new sections of 9L07 and the new 9L89 with jumpers close to Dawes sub | Line |  | Tie in new sections of 9L07 and the new 9L89 with jumpers close to Dawes sub. | 240 kV, Pre-Condition, Restricts Generation
ENMAX | 31.3TR (ENMAX 31) | 2015-06-10 08:00 | 2015-06-11 16:00 | N | N | apprentice training | Transformer |  |  | For Information Only
ALTALINK | 753L (65s High River - 253s Blackie) | 2015-06-10 08:00 | 2015-06-11 18:00 | N | N | Foothills 138kV: salvage OHSW and string new 434L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 957s 901 (957s McClelland) | 2015-06-10 09:00 | 2015-06-11 13:00 | N | Y | breaker test and operate | Circuit Breaker |  | 957S 901 BKR Test and Operate 957S 903 BKR Inservice 957S 901 BKR Test and Operate 957S 901 BKR OOS. 957S 903 BKR Inservice | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 19s T8 (19s Wabamun) | 2015-06-10 09:00 | 2015-06-10 17:00 | N | N | replace H3 bushing | Transformer |  |  | Pre-Condition
ATCO | 957s 903 (957s McClelland) | 2015-06-10 13:00 | 2015-06-11 17:00 | N | Y | breaker test and operate | Circuit Breaker |  | 957S 903 BKR Test and Operate 957S 901 BKR Inservice 957S 903 BKR Test and Operate 957S 903 BKR OOS. 957S 901 BKR Inservice | 240 kV, Contingency Requires Mitigation
ATCO | 785s 701T (785s Judy Creek Gas Plant) | 2015-06-10 13:00 | 2015-06-12 10:00 | N | N | install bird mitigation on 501 and 701T | Transformer |  | Install Bird Mitigation on 501 and 701T @ 785S Install Bird Mitigation on substation test protective relays on 701T, 25KV and 6900 volt system Condition Guarantee that Judy Creek Gas plant is off line. Customer has contacted FMS to notify that the Gas plant would be down for annual maintenance . Would like to capitalize on the substation outage | For Information Only
ALTALINK | 5s C3 (5s East Calgary),5s 7 (5s East Calgary),5s C4 (5s East Calgary) | 2015-06-11 08:00 | 2015-06-11 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 412S Shell Eagle Creek,719CL (412s Shell Eagle Creek - 719CL0) | 2015-06-11 08:00 | 2015-06-11 17:00 | N | N | customer requested outage (NGR testing) | Station, Line
ALTALINK | 291s T1 (291s Cochrane),860L (291s Cochrane - 44s Bearspaw Plant),291s 860 (291s Cochrane),291s Cochrane 138kV Bus 1 | 2015-06-11 12:00 | 2015-06-19 17:30 | N | N | install new bus VT,install bus tie bkr, install new bus prot. | Bus, Line, Circuit Breaker, Transformer
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2015-06-12 07:00 | 2015-06-12 12:00 | N | Y | to create open point A | Transformer, Bus, Shunts |  |  | 240 kV, Pre-Condition, Overload
ATCO | 7L183 (856s Kinosis - 2060s Engstrom) | 2015-06-12 08:00 | 2015-06-22 16:00 | N | N | install 7L15 bypass (7L183D5 + 7L183 taps) | Line |  | Install 7L15 bypass (7L183D5 + 7L183 taps), 7L183 is presently not carrying any load, risk minimal | For Information Only
ALTALINK | 74s T1 (74s Janet),74s Janet 240kV Bus 1 | 2015-06-13 07:00 | 2015-06-14 17:00 | N | Y | replace PTs 74s48, 74s19 and strain insulators | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload
EPCOR | Celanese | 2015-06-15 06:00 | 2015-06-25 18:00 | N | N | plant electrical maintenance | Station |  |  | For Information Only
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2015-06-15 07:00 | 2015-06-15 12:00 | N | Y | to close open point A and restore T2 & B2 bus back to normal, job scope change for safety clearance | Transformer, Bus, Shunts |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 5s T1 (East Calgary) | 2015-06-15 07:00 | 2015-06-17 18:00 | N | N | ECTP project - remove 2 pole structures for clearance to prepare for transformer replacement | Transformer |  |  | 240 kV
ALTALINK | 910L (89s Ellerslie - 63s Red Deer) | 2015-06-15 07:30 | 2015-06-18 15:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 698s T2 (698s Jackfish) | 2015-06-15 08:00 | 2015-06-16 15:00 | N | N | warranty work including paint | Transformer |  |  | For Information Only
ATCO | 784s 701T (784s Donnelly) | 2015-06-15 08:00 | 2015-06-15 16:30 | N | N | bird mitigation install and hot spot repair | Transformer |  | Bird Mitigation Install and Hot Spot Repair. / All load carried on 835S Mobile Substation.
Lethbridge | 813L (241s Lethbridge Uplands - 146s Lethbridge MacDonald) | 2015-06-15 08:00 | 2015-06-15 18:00 | N | N | maintenance | Line |  |  | Creates Radial Feeds
ATCO, ALTALINK | 9L930 (72s Leismer - 825s Whitefish Lake) | 2015-06-15 08:00 | 2015-06-29 16:00 | N | Y | 9L930 line reconfiguration/reroute 9L930/9L81 in/out at 898s | Line |  | 9L930 line reconfiguration/reroute (9L930/9L81 in/out @ 898s) | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 967L (59s Peigan - 370s North Lethbridge) | 2015-06-15 08:00 | 2015-06-30 18:00 | N | Y | 138s Windy Flats cut-in | Line |  |  | 240 kV, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 898s 501R (898s Heart Lake),898s 902T (898s Heart Lake),898s Heart Lake 240 kV 900 Bus | 2015-06-15 08:00 | 2015-06-29 16:00 | N | Y | bus outage | Transformer, Bus, Shunts |  | 902T will be OOS during bus outage, AML will be asked to close 602L1 to supply 818s from 788L, portable genset will be installed to maintain AC station service, 501R 20 MVAR reactor will be unavailable for dispatch, 240kV buss connections, string 9L930, 9L81, and 1117L into sub | 240 kV, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 27.1TR (ENMAX 27) | 2015-06-15 08:00 | 2015-06-19 16:00 | N | N | doble | Transformer
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2015-06-15 08:00 | 2015-06-15 16:00 | N | N | birds nest needs to be removed | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 5.2TR (ENMAX 5) | 2015-06-15 08:00 | 2015-06-15 12:00 | N | N | rework DC circuits | Transformer |  |  | For Information Only
ATCO, ALTALINK | 9L930 (72s Leismer - 825s Whitefish Lake) | 2015-06-15 08:00 | 2015-06-26 17:00 | N | Y | request to cut 9L930 in and out of A898s | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 845s 702 (845s Big Mountain) | 2015-06-15 08:30 | 2015-06-15 17:00 | N | N | relay work | Circuit Breaker |  | 845S BIG MTN GOI FOR BRK 702 ( 52/b ADDITION TO 21 RELAY) | For Information Only
ATCO | 957s 901 (957s McClelland) | 2015-06-15 09:00 | 2015-06-15 13:00 | N | Y | 957s901 breaker test | Circuit Breaker |  | 957S 901 BKR Test and Operate 957S 901 BKR OOS. 957S 902 BKR Inservice 957S 901 BKR Test and Operate CONSTRAINT 901 BKR OOS. | 240 kV, Contingency Requires Mitigation
ATCO | 957s 902 (957s McClelland) | 2015-06-15 13:00 | 2015-06-15 17:00 | N | Y | 957S 902 breaker test and operate | Circuit Breaker |  | 957S 902 BKR Test and Operate 957S 901 BKR will be In service 957S 902 BKR Test and Operate BREAKER 240KV 4KA HPL-300-B1 957S 903 BKR will be In service 957S 902 BKR Test and Operate 957S 902 BKR OOS. 957S 903 BKR Inservice | 240 kV, Pre-Condition
ALTALINK | 478s T1 (478s Tucuman) | 2015-06-15 13:00 | 2015-06-16 17:00 | N | N | repairing oil leaks & doble maintenance | Transformer |  |  | For Information Only
ALTALINK | 74s 2552 (74s Janet) | 2015-06-15 13:00 | 2015-06-18 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 305s T1 (305s Acheson) | 2015-06-16 07:00 | 2015-06-16 17:00 | N | N | bird coverup & cut open point 'A' next to 305s28 | Transformer
ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2015-06-16 07:00 | 2015-06-30 18:00 | N | Y | Altalink string 1109L & doble 65LA240-1080L-C & 25LZ240-1080L-C | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 77s T1 (77s Sagitawah) | 2015-06-16 08:00 | 2015-06-18 16:00 | N | Y | SCADA upgrade project | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 445S Elk River | 2015-06-16 08:00 | 2015-06-19 17:00 | N | N | SCADA upgrade & TX protection upgrade | Station
ALTALINK | 186s C1 (186s Dry Creek),186s 17 (186s Dry Creek) | 2015-06-16 08:00 | 2015-06-17 12:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 784s 701T (784s Donnelly) | 2015-06-16 08:00 | 2015-06-17 12:00 | N | N | complete 701T major testing and 701 partial | Transformer |  | Complete 701T Major Testing and 701 Partial PM, Station fed from 835S mobile sub for the duration of the work
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2015-06-16 08:00 | 2015-06-16 18:00 | N | N | maintenance | Line |  |  | Overload, Contingency Requires Mitigation
ATCO | 845s 703 (845s Big Mountain) | 2015-06-16 08:30 | 2015-06-16 17:00 | N | N | relay work | Circuit Breaker |  | 845S BIG MTN GOI FOR BRK 703 ( 52/b ADDITION TO 21 RELAYS) | Contingency Requires Mitigation
ALTALINK | 305S Acheson,305s T2 (305s Acheson) | 2015-06-17 07:00 | 2015-06-17 17:00 | N | N | 25kV west bus - bird coverup | Station, Transformer |  |  | For Information Only
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2015-06-17 08:00 | 2015-06-18 15:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 740s 507C (740s H.R.Milner),740S 507 | 2015-06-17 08:00 | 2015-06-17 12:00 | N | N | breaker testing | Terminal Equipment, Shunts |  | BREAKER 507 BULK OIL FKP PARTIAL TESTING Cap bank not available | Pre-Condition
ATCO | 6L97 (735s Swan River - 739s Edith Lake),735s 603 (735s Swan River) | 2015-06-17 08:00 | 2015-06-17 16:00 | N | N | 6L97 will be open ended at 739s Edith Lake, deficiency work on 603CTs | Line, Circuit Breaker |  | 6L97 will be open ended at 739s Edith Lk, Deficiency work on 603CTs | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36) | 2015-06-17 08:00 | 2015-06-19 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 845s 707 (845s Big Mountain) | 2015-06-17 08:30 | 2015-06-17 17:00 | N | N | relay work | Circuit Breaker |  | 845S BIG MTN GOI FOR BRK 707 ( 52/b ADDITION FOR 21 RELAYS) | Contingency Requires Mitigation
ALTALINK | 650s 752 (650s Hansman Lake) | 2015-06-17 08:30 | 2015-06-17 14:00 | N | Y | add nitrogen, inspect for leaks, replace counter - urgent | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, TRANSALTA | 179S Gleichen,733L (179s Gleichen - 428s Namaka) | 2015-06-17 09:00 | 2015-06-17 14:00 | N | N | 471s Mobile Removal,471s Mobile Removal, affects 179s23N | Line, Station |  |  | Pre-Condition
ATCO | 6L97 (735s Swan River - 739s Edith Lake),739s 603 (739s Edith Lake) | 2015-06-17 10:00 | 2015-06-17 14:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | 6L97 WILL BE REMOVED FROM SERVICE @ 739S EDITH LAKE FOR MTCE ON BKR 603
ALTALINK | 199s C1 (199s East Ardrie),199s 41 (199s East Airdrie) | 2015-06-17 13:00 | 2015-06-18 17:00 | N | N | warranty work | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | 803s T2 (803s Lambton) | 2015-06-17 18:01 | 2015-10-02 18:00 | N | Y | transformers replacement project Part 1 | Transformer |  |  | 240 kV
ALTALINK | 62s12 (62s Brazeau) | 2015-06-17 23:00 | 2015-06-18 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s11 (62s Brazeau) | 2015-06-18 03:00 | 2015-06-18 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2015-06-18 08:00 | 2015-06-19 16:00 | N | N | doble 14CS138-14.1CAP & 14CS138-14.2CAP | Shunts |  |  | For Information Only
ATCO | 735s 604 (735s Swan River),6L96 (735s Swan River - 6L96 Tap) | 2015-06-18 08:00 | 2015-06-18 16:00 | N | N | deficiency work | Line, Circuit Breaker |  | 6L96 WILL BE OPEN ENDED AT 735S, 604CT DEFICIENCY WORK | Pre-Condition, Over/Under Voltage
ALTALINK | 305s T1 (305s Acheson) | 2015-06-18 08:00 | 2015-06-18 12:00 | N | N | bird coverup & close open point 'A' next to 305s28 | Transformer
ATCO | 845s 708 (845s Big Mountain) | 2015-06-18 08:30 | 2015-06-18 17:00 | N | N | maintenance | Circuit Breaker |  | 845S BIG MTN GOI FOR BKR 708 ( 52/b ADDITION TO 21 RELAY) | Contingency Requires Mitigation
ATCO | 6L11 (742s Freeman Lake - 743s Sarah Lake),6L11 (854s Swan Dive - 742s Freeman Lake) | 2015-06-18 09:00 | 2015-06-18 14:00 | N | N | Emergency replace leaking CTs on metering tank | Line |  |  | Creates Radial Feeds
ALTALINK | 348S Marlboro | 2015-06-18 09:00 | 2015-06-18 17:00 | N | N | customer 5kV Bus, 348s13, 348s14, 348s15 maintenance | Station
ALTALINK | 922L (310p Sundance - 17s Benalto),926L (310p Sundance - 17s Benalto) | 2015-06-19 05:30 | 2015-06-19 19:00 | N | Y | required for drag line move | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
SUNCOR | 29PL9-4 (29EDD-1 Millennium - 29EDD-3) | 2015-06-19 08:00 | 2015-07-17 20:00 | N | Y | PM work on transformer 29PT-5, CT's , CVT's , disconnects, circuit breakers, DD1S6, 29EDD1SPL9-4, 29PLA-181 | Line |  |  | 240 kV, Restricts Generation
ALTALINK | 1048L (138s Windy Flats - 59s Peigan) | 2015-06-19 08:00 | 2015-06-22 16:00 | N | Y | In service date: June 20, 2015 | Line |  |  | 240 kV
ALTALINK | 310p 1952 (310p Sundance) | 2015-06-19 09:00 | 2015-06-19 10:00 | N | Y | trip test from 310p2052, coordinated with 922L outage | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 291s T2 (291s Cochrane),433L (291s Cochrane - T793s Horse Creek),291s 433 (291s Cochrane),291s Cochrane 138kV Bus 2 | 2015-06-20 07:00 | 2015-06-29 17:30 | N | N | install 25kV breakers,T2 & 25kV bus protection, complete 138 kV bus protection | Transformer, Bus, Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L194 (875s Algar - 2009s Willow Lake) | 2015-06-20 07:00 | 2015-07-10 17:30 | N | N | cut in and out of new 2011s Dawes substation | Line |  | Horse Rv and Algar radial fed from Crow, Willow radial fed from Hanging Stone, Cut in 7L194/7L170 in/out into Dawes (Line 7L194 between Algar and Dawes will be renamed 7L170. Line 7L194 will be from Willow Lake to Dawes). On RTN switching 144kV bus @ 2011s Dawes will be energized. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2015-06-20 07:00 | 2015-06-20 19:00 | N | N | exploratory investigation into the underground cable section per condo development requests | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-18 Firebag RTU/SCADA | 2015-06-20 09:00 | 2015-06-21 17:00 | N | N | two 10 mins outages to RTU | Terminal Equipment |  |  | Affects Visibility
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2015-06-20 21:00 | 2015-06-21 09:00 | N | N | dielectric spectroscopy, sheath test, DGA | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (214s Innisfail - 55s Olds),55s83 (55s Olds) | 2015-06-21 09:00 | 2015-06-21 11:00 | N | N | functional testing" of new breaker fail trip to 55s80N | Switch, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2015-06-21 21:00 | 2015-06-22 09:00 | N | N | dielectric spectroscopy, sheath test, DGA | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CC13 (987s Clover Bar) | 2015-06-22 07:00 | 2015-06-22 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 727L (65s High River - 727L39S) | 2015-06-22 07:00 | 2015-06-23 19:00 | N | N | Foothills 138kV: install caissons, footings and bases and poles | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 910L (89s Ellerslie - 63s Red Deer) | 2015-06-22 07:00 | 2015-07-06 20:00 | N | Y | install foundation in preparation for 288s | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 856s 701 (856s Kinosis) | 2015-06-22 07:00 | 2015-06-28 17:00 | N | N | tie in new 144kV bus and equipment | Circuit Breaker |  | Tie in new 144kV bus and equipment, add 701PTX1, 7L15 will be fed from 7L183, risk minimal Jun 22 - 26 Isolate 144kV bus between 701PT, 701A, 7L15D1 (2-31720A) Jun 26 - 28 Shrink GOI to 701A, 701B (2-31720B) Work activities Construction: Connect newly installed 703, 703A, 703B, 7L183D1, 704B, 703PTX1, 703PTX2, 703PTY1, 703PTY2 to 144kv buss (700BS1) in preparation for energizing new 7L183 to 2060s Engstrom. Adding new 703CT cables into 7L15 'A & 7L15 'B' protections Replace old 701PT 3-gang switch assembly with 4-gang switch assembly Commissioning: Perform all CT, PT & logic tests and control on 701, 703, 7L183D1 | For Information Only
EPCOR | 330p 1202 (330p Genesee) | 2015-06-22 07:00 | 2015-07-27 18:00 | N | Y | breaker replacement | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
EPCOR | At-Plastics-4Rs | 2015-06-22 07:30 | 2015-06-24 18:00 | N | N | electrical maintenance | Station
Syncrude | Aurora 31 (Aurora),Aurora 32 (Aurora) | 2015-06-22 07:30 | 2015-06-22 19:30 | N | N | cap bank work | Circuit Breaker |  |  | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2015-06-22 08:00 | 2015-06-22 12:00 | N | N | remove oil dry out processor on transformer | Transformer
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2015-06-22 08:00 | 2015-06-25 16:00 | N | N | replace PT at 11s | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | NAT1 Ralston | 2015-06-22 08:00 | 2015-06-30 16:00 | N | N | 2 x 10 MW DG. Refer to the Op Plan binder for the commissioning plan. | Unit
ENMAX | 34.1TR (ENMAX 34) | 2015-06-22 08:00 | 2015-06-26 16:00 | N | N | repair oil leak | Transformer
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2015-06-22 08:00 | 2015-06-22 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 63s T4 (63s Red Deer) | 2015-06-22 08:00 | 2015-06-22 13:00 | N | N | removing LTC low oil trip from the TX | Transformer
ATCO | 6L79 (711s Willingdon - 707s St.Paul) | 2015-06-22 08:00 | 2015-06-22 17:00 | N | N | deficiencies work | Line |  | 6L79 Line Deficiencies THIS LINE IS REQUIRED IN-SERVICE FOR THE NEXT DAY JUNE 23. TO ACCOMMODATE A HIGH LOAD MOVE BETWEEN ST PAUL AND BONNYVILLE | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11) | 2015-06-22 08:00 | 2015-06-26 16:00 | N | N | doble transformer | Transformer
ALTALINK | 71s 1352 (71s Lamoureux) | 2015-06-22 08:00 | 2015-06-25 15:00 | N | Y | 240kV CT replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 30.1TR (ENMAX 30) | 2015-06-22 08:00 | 2015-06-26 16:00 | N | N | LTC maintenace | Transformer
ENMAX | 162s 138-RB82 (162s Beddington) | 2015-06-22 08:00 | 2015-06-24 16:00 | N | N | doble breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 562s T1 (562s Cypress),668L (394s Empress - 562s Cypress),562s 138 kV Bus 1 (562s Cypress) | 2015-06-22 08:00 | 2015-06-23 17:00 | N | Y | install OPGW line over top of 138kV bus,install OPGW line over top of 138kV bus 1 | Transformer, Line, Bus |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 749s 703 (749s Flyingshot Lake) | 2015-06-22 08:30 | 2015-06-22 17:00 | N | N | maintenance | Circuit Breaker |  | 749S FLYINGSHOT GOI FOR BRK 703 ( 52/b ADDITION FOR 21 RELAYS) | Contingency Requires Mitigation
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2015-06-22 09:00 | 2015-06-26 17:00 | N | Y | install arcing horns | Line |  |  | Over/Under Voltage, Limits ATC, Contingency Requires Mitigation
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2015-06-22 09:00 | 2015-06-26 15:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 74s 2452 (74s Janet) | 2015-06-22 10:00 | 2015-06-22 17:00 | N | Y | 240kV breaker maintenance and capacitor replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 15.2TR (ENMAX 15) | 2015-06-22 12:00 | 2015-06-22 16:00 | N | N | install oil dry out processor on transformer | Transformer |  |  | For Information Only
ALTALINK | 445s T2 (445s Elk River) | 2015-06-22 14:00 | 2015-06-26 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2015-06-22 21:00 | 2015-06-23 09:00 | N | N | dielectric spectroscopy, sheath test, DGA | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2015-06-22 22:00 | 2015-06-23 06:30 | N | N | high load move | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72NW15 (Namao - Woodcroft),Woodcroft W723 (Woodcroft) | 2015-06-23 07:00 | 2015-06-23 18:00 | N | N | doble testing | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | 987s CC24 (987s Clover Bar) | 2015-06-23 07:00 | 2015-06-23 18:00 | N | N | breaker maintenance | Circuit Breaker
Syncrude | AL-1 (D05 Syncrude - Aurora) | 2015-06-23 07:30 | 2015-06-25 12:00 | N | Y | CT ratio upgrade for AL-1 | Line |  |  | 240 kV
ALTALINK | 478s C1 (478s Tucuman),478s 552 (478s Tucuman) | 2015-06-23 08:00 | 2015-06-24 12:00 | N | N | maintenance warranty work | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 77s T2 (77s Sagitawah),77s Sagitawah 240 kV East Bus | 2015-06-23 08:00 | 2015-06-25 16:00 | N | Y | SCADA upgrade project and 240kV switch maintenance (77s37) | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 773s 601T (773s Coronation) | 2015-06-23 08:00 | 2015-06-23 17:00 | N | N | raise 25kV bus to prevent bird outages as experienced in past | Transformer |  | Raise 25kV bus to prevent bird outages as experienced in past. Station Outage 25kV load will have to be offloaded to adjacent substations.
ATCO | 741s 701T (741s Fox Creek) | 2015-06-23 08:00 | 2015-06-24 12:00 | N | N | fan addition | Transformer |  | 741S 701T Fan Addition 2nd stage fans are being added. All load transferred to 702T
ALTALINK | 760AL (164s Empress Liquids - 760L41),760L (163s Amoco Empress - 760L41),760L (7L760D3 - 760L41) | 2015-06-23 08:00 | 2015-06-23 17:00 | N | N | isolate line/switch for switch maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 364s T1 (364s Whitecourt Industrial) | 2015-06-23 08:00 | 2015-06-24 17:00 | N | N | regulator & switch maintenance | Transformer
EPCOR | Strathcona T2 (Strathcona) | 2015-06-23 08:00 | 2015-06-24 18:00 | N | N | doble testing | Transformer
ATCO | 717s 703T (717s Ethel Lake),717s 603 (717s Ethel Lake) | 2015-06-23 08:30 | 2015-06-24 16:00 | N | N | test | Circuit Breaker, Transformer |  | While 603 is being tested, there will be a station service outage. Station will be running on substation batteries for up to 5 hours. All Distribution load will be transferred to adjacent substation on June 22, 2015 LD Transfer 2-33268 & 2-33266
ALTALINK | 368s T1 (368s Burdett) | 2015-06-23 08:30 | 2015-06-23 17:00 | N | N | filter oil leak and bird cover repair | Transformer
ATCO | 930s Syn Condenser (930s Arcenciel) | 2015-06-23 08:30 | 2015-06-25 16:30 | N | Y | maintenance and repair | Shunts |  | Complete Sync Cond. Maintenance and Repairs 1. Machine maintenance 2. VFD maintenance 3. ABB-REG650 Setting change. | For Information Only
ATCO | 749s 704 (749s Flyingshot Lake) | 2015-06-23 08:30 | 2015-06-23 17:00 | N | N | 52/B addition 21 relays | Circuit Breaker |  | 749S FLYINGSHOT GOI FOR BRK 704 ( 52/b ADDITION TO 21 RELAYS) | Contingency Requires Mitigation
ATCO | 717s 602T (717s Ethel Lake) | 2015-06-23 09:00 | 2015-06-24 16:00 | N | N | 717S 602T complete testing | Transformer |  | 717S 602T Complete testing. The sub will only be carrying station service at the time. All Distribution load will be transferred to adjacent substation on June 22, 2015. LD Transfer 2-33268 & 2-33266
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2015-06-23 09:00 | 2015-06-23 15:00 | N | N | high load move | Line |  | 6L82 de-energized on June 23 2015 between 707S St Paul and 700s Bonnyville to escort high load move down Hwy 28. I cannot confirm exactly what time we will be crossing but the load will start around 9:00 and I am guessing to be completed the whole move by 15:00. Please send any switching to St Paul service, Bonnyville service and Vegreville service. WILL REQUIRE THE RESTORATION OF 6L79 (CROW 2-31412) AND THE LINE NEEDS TO BE RESTORED BACK TO THE STATE IT WAS FOUND IN. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2015-06-23 21:00 | 2015-06-24 09:00 | N | N | dielectric spectroscopy & sheath test & DGA | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 987s CCP7214 (987s Clover Bar) | 2015-06-24 07:00 | 2015-06-24 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 428s T2 (428s Namaka),733L (151s Strathmore - 428S Namaka),886L (431s Hussar - 428s Namaka) | 2015-06-24 08:30 | 2015-06-24 17:00 | N | N | 138kV switch maintenance | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2015-06-24 09:00 | 2015-06-24 17:00 | N | Y | reinstall lightning spires on the 'A' frame | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 790s 701C (790s Poplar Hill),790s 701 (790s Poplar Hill) | 2015-06-24 09:00 | 2015-06-24 16:00 | N | N | test breaker, 701 cap bank not available | Circuit Breaker, Shunts |  | Test breaker, 701 cap bank not available | For Information Only
ALTALINK | 62s T7 (62s Brazeau) | 2015-06-24 10:00 | 2015-06-25 17:00 | N | N | repair leaks | Transformer |  |  | For Information Only
ALTALINK | 377s C1 (377s Hardisty),377s 34 (377s Hardisty) | 2015-06-24 13:00 | 2015-06-25 17:00 | N | N | breaker maintenance; Mitsubishi warranty work | Shunts, Circuit Breaker |  |  | For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2015-06-24 21:00 | 2015-06-25 09:00 | N | N | dielectric spectroscopy, sheath test, DGA, breaker maintenance on 9B138-9.83 | Line |  |  | For Information Only
ALTALINK | 80L (63s Red Deer - 214s Innisfail) | 2015-06-25 07:00 | 2015-06-28 17:00 | N | N | install pole phase risers to 80L south to allow 648L to cross under old 80L south | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 727L (65s High River - 727L39S) | 2015-06-25 07:00 | 2015-06-27 19:00 | N | N | Foothills 138kV: install caissons,footings and bases and poles | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
GWPCORP | 243S Soderglen Wind Farm | 2015-06-25 08:00 | 2015-07-10 16:00 | N | N | repair | Station |  |  | Restricts Generation, For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2015-06-25 08:00 | 2015-06-25 16:00 | N | N | oil leak investigation | Transformer
EPCOR | Strathcona T1 (Strathcona),72RS5 (Rossdale - Strathcona) | 2015-06-25 08:00 | 2015-06-25 18:00 | N | N | doble testing lighting arrestors | Line, Transformer
ENMAX | ENMAX 25 240kV North Bus | 2015-06-25 08:00 | 2015-06-25 16:00 | N | Y | maintenance | Bus |  |  | 240 kV, Pre-Condition
ALTALINK | 394s T1 (394s Empress) | 2015-06-25 08:30 | 2015-06-25 17:00 | N | N | SFRA testing | Transformer
ALTALINK | 183s T2 (183s Underwood) | 2015-06-25 09:00 | 2015-06-25 19:00 | N | N | customer request for isolation to adjust 420-BUS-2-TIS | Transformer
ALTALINK | 729L (285s East Camrose - 542s Ervick),542s729E (542s Ervick) | 2015-06-25 09:00 | 2015-06-25 17:00 | N | N | 138kV motor mech repair | Line, Switch |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2015-06-25 12:30 | 2015-06-28 19:30 | N | Y | CT ratio upgrade | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354S Summerview | 2015-06-25 13:00 | 2015-06-26 12:00 | N | Y | repairs | Station |  |  | Restricts Generation, For Information Only
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2015-06-26 07:00 | 2015-06-26 17:00 | N | N | strain insulator replacements 347s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 856S Kinosis,856s 701 (856s Kinosis) | 2015-06-26 08:00 | 2015-06-28 16:00 | N | N | 7L15 will be tied to 7L183 via a temp bypass | Station, Circuit Breaker |  | 7L15 will be tied to 7L183 via a temp bypass, During testing a portion of the 144kV bus @ 856s will be energized each time 7L15D1 is closed, Commissioning 7L15D1 logic and function testing. | For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21),ENMAX 21 B138-21.80 (ENMAX 21) | 2015-06-26 08:00 | 2015-06-26 16:00 | N | N | SF6 gas sample | Line, Circuit Breaker
ALTALINK | 755L (63s Red Deer - 247s Piper Creek) | 2015-06-26 12:00 | 2015-06-26 18:30 | N | N | remove 63sT2 safely out of substation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L930 (898s Heartlake - 72s Leismer) | 2015-06-27 08:00 | 2015-07-03 16:00 | N | N | In service date: June 30, 2015 | Line |  |  | 240 kV
ENMAX | 2.80L (ENMAX 2 - ENMAX 23),ENMAX 23 B138-2.80 (ENMAX 23) | 2015-06-27 08:00 | 2015-06-27 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2015-06-27 08:00 | 2015-07-03 16:00 | N | N | In service date: June 30, 2015 | Line |  |  | 240 kV
ATCO | 9L81 (898s Heartlake - 825s Whitefish) | 2015-06-27 08:00 | 2015-07-03 16:00 | N | N | In service date: June 30, 2015 | Line
EPCOR | 987s T2 (987s Clover Bar),72CN10 (987s Clover Bar - Namao),987s Cloverbar 72kV Bus 1 | 2015-06-27 13:00 | 2015-06-27 17:00 | N | N | offload bus prior to first run up | Bus, Line, Transformer |  |  | For Information Only
ALTALINK | 758L (534s Eckville - 758L1) | 2015-06-28 05:00 | 2015-06-28 10:00 | N | N | energize new 534s T1 via 758L1, planned power outage arranged with Fortis, not all load can be moved off of 534s prior to outage | Line
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37),ENMAX 38 B138-37.81 (ENMAX 38) | 2015-06-28 08:00 | 2015-06-28 16:00 | N | N | switch 81, 82, 83 maintenance at 37 sub, HV breaker doble at 38 sub | Circuit Breaker, Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Kennedale T2 (Kennedale) | 2015-06-29 07:00 | 2015-06-29 17:00 | N | N | inspection for flange | Transformer
ALTALINK | 727L (65s High River - 727L39S) | 2015-06-29 07:00 | 2015-06-29 19:00 | N | N | Foothills 138kV: install caissons, footings and bases and poles | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 310p 2752 (310p Sundance) | 2015-06-29 08:00 | 2015-06-29 08:30 | N | Y | trip test from 310p2752 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 71s C2 (71s Lamoureux),71s 1052 (71s Lamoureux) | 2015-06-29 08:00 | 2015-07-02 17:00 | N | N | 138kV CT replacement | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 34.3TR (ENMAX 34) | 2015-06-29 08:00 | 2015-07-03 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 28.2TR (ENMAX 28) | 2015-06-29 08:00 | 2015-06-29 16:00 | N | N | re-wire FT switches | Transformer
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2015-06-29 08:00 | 2015-07-02 16:00 | N | N | 7L65 check and fix conductors found by heat scan | Line
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2015-06-29 08:00 | 2015-06-30 16:00 | N | N | 7L65 check and fix conductors found by heat scan | Line |  | 7L65 check and fix conductors found by heat scan | Pre-Condition, Overload, Over/Under Voltage
CMH | CMH1 Medicine Hat #1 | 2015-06-29 08:00 | 2015-06-30 16:00 | N | N | Unit 12 Control Upgrade. Testing: June 30 - 05:00-06:00H, City of Medicine Hat will be isolated from the system. | Unit
ALTALINK | 719L (263s Strachan - 719L259C) | 2015-06-29 08:00 | 2015-07-02 17:00 | N | N | relocation of H structure and installation of 138kV screw piles | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2452 (310p Sundance) | 2015-06-29 08:45 | 2015-06-29 09:15 | N | Y | trip test from 310p2452 | Circuit Breaker |  |  | 240 kV
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2015-06-29 09:00 | 2015-06-30 15:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 310p 1852 (310p Sundance) | 2015-06-29 09:30 | 2015-06-29 10:00 | N | Y | trip test from 310p1852 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L06 (784s Donnelly - 787s High Prairie) | 2015-06-29 10:00 | 2015-06-30 17:30 | N | N | remove 3 way gang switch and rebuild | Line |  | remove 3 way gang switch and rebuild | Creates Radial Feeds
ALTALINK | 310p 1552 (310p Sundance) | 2015-06-29 10:15 | 2015-06-29 10:45 | N | Y | trip test from 310p1552 | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 1252 (310p Sundance) | 2015-06-29 11:00 | 2015-06-29 11:30 | N | Y | trip test from 310p1252 | Circuit Breaker |  |  | 240 kV
ATCO | 840S McNeill Station | 2015-06-29 11:30 | 2015-06-30 16:05 | N | Y | forced outage | Station |  |  | Limits ATC
ALTALINK | 310p 952 (310p Sundance) | 2015-06-29 13:00 | 2015-06-29 13:30 | N | Y | trip test from 310p952 | Circuit Breaker |  |  | 240 kV
ALTALINK | 1120L (410s Josephburg - 108s Amelia) | 2015-06-29 13:00 | 2015-06-30 17:00 | N | Y | switch repair | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 405s C1 (405s Waupisoo) | 2015-06-29 13:00 | 2015-06-29 16:00 | N | N | urgent repair: replace blown fuse or possibly capacitor | Shunts |  |  | For Information Only
ATCO | 705s 601T (705s Kitscoty) | 2015-06-29 13:00 | 2015-07-03 13:00 | N | N | oil reclaim on 601T, 601T does not normally carry any load, all sub load on normally fed on 701T | Transformer |  | Oil Reclaim on 601T, 601T does not normally carry any load. All sub Load on normally fed on 701T.
ALTALINK | 310p 652 (310p Sundance) | 2015-06-29 13:45 | 2015-06-29 14:15 | N | Y | trip test from 310p652 | Circuit Breaker |  |  | 240 kV
ALTALINK | 121s 1052 (121s Brooks) | 2015-06-29 14:00 | 2015-06-30 15:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 352 (310p Sundance) | 2015-06-29 14:30 | 2015-06-29 15:00 | N | Y | trip test from 310p2152 | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p412 (310p Sundance) | 2015-06-29 15:15 | 2015-06-29 15:45 | N | Y | trip test from 310p412 | Circuit Breaker |  |  | For Information Only
ALTALINK | 133L (19s Wabamun - 133L697A),19s 133 (19s Wabamun) | 2015-06-30 08:00 | 2015-06-30 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 281s T1 (281s Johnson) | 2015-06-30 08:00 | 2015-07-08 16:00 | N | Y | investigate potential oil leak | Transformer |  |  | 240 kV, For Information Only
AESO-SC | PSS | 2015-06-30 08:00 | 2015-06-30 16:00 | N | N | Suncor GT10 - PSS will be disabled for 10 min. before the unit will be off-line. | Terminal Equipment
ALTALINK | 142s 3 (142s Magcan),142s C1 (142s Magcan) | 2015-06-30 09:00 | 2015-06-30 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna),775s 601 (775s Sullivan Lake) | 2015-06-30 09:00 | 2015-06-30 15:00 | N | N | emergency inspection & repairs due to mis-operation | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (14s Devon - 155s Blackmud),14s 739E (14s Devon) | 2015-06-30 09:00 | 2015-06-30 15:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 727L (65s High River - 727L39S) | 2015-07-01 07:00 | 2015-07-04 19:00 | N | N | Foothills 138kV: install caissons, footings and bases and poles | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2015-07-01 08:00 | 2015-07-05 16:00 | N | N | In service date: July 3, 2015 | Line |  |  | 240 kV
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek) | 2015-07-01 08:00 | 2015-07-05 16:00 | N | N | In service date: July 3, 2015 | Line |  |  | 240 kV
ALTALINK | 288S Wolf Creek | 2015-07-01 08:00 | 2015-07-05 16:00 | N | N | In service date: July 3, 2015 | Station |  |  | 240 kV
ENMAX | 1.82L (ENMAX 1 - ENMAX 5),B138-1.82 (ENMAX 5) | 2015-07-02 08:00 | 2015-07-02 12:00 | N | N | SF6 gas sample on 5B138-1.82 | Line, Circuit Breaker |  |  | Overload
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant),44s 860W (44s Bearspaw) | 2015-07-02 09:00 | 2015-07-02 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds
ATCO | 722s 701T (722s Crystal Lake) | 2015-07-02 09:00 | 2015-07-03 12:00 | N | N | 722s704 breaker SF6 GL212 partial testing | Transformer |  | 722S 704 BREAKER SF6 GL212 PARTIAL TESTING 25KV load transferred to 702T (NOTED 722S WAS LOADED AT 37 MVA ON JUNE 04) | For Information Only
ENMAX | 1.84L (ENMAX 1 - ENMAX 5),B138-1.84 (ENMAX 5) | 2015-07-02 12:01 | 2015-07-02 16:00 | N | N | SF6 gas sample on 5B138-1.84 | Line, Circuit Breaker |  |  | Pre-Condition, Overload
NEXENI | I-PCES02S Balzac | 2015-07-03 09:30 | 2015-07-03 10:30 | N | N | communications system maintenance | Station |  |  | Affects Visibility
ALTALINK | 528S Blue Trail Wind Farm | 2015-07-04 08:00 | 2015-07-16 16:00 | N | N | communication time delay | Station |  |  | For Information Only
ALTALINK, Lethbridge | 725BL (725BL54 - 240s McBride Lake),725L (674s Lethbridge Bowron - 725BL54),725L (15s Fort MacLeod - 725BL54) | 2015-07-04 08:00 | 2015-07-15 18:00 | N | Y | Windy Flats: rebuild double circuit | Line |  |  | Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s T3 (63s Red Deer) | 2015-07-06 07:00 | 2015-07-16 16:30 | N | N | replace LA's and switch | Transformer
ALTALINK | 727L (65s High River - 727L39S) | 2015-07-06 07:00 | 2015-07-11 19:00 | N | N | Foothills 138 kV install caissons, footings, bases and poles | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2015-07-06 07:00 | 2015-07-09 17:00 | N | N | T1 LA, & bushing monitor | Transformer
ATCO | 7L104 (856s Kinosis - 989s Quigley) | 2015-07-06 08:00 | 2015-07-10 16:00 | N | N | cut-in protection ccts into 706PT | Line |  | 989s, 2081s, and 2060s will be radial fed from 856s via 7L183.144kV Bus expansion @ 856s (705B bus connection to 705), cut-in protection ccts into 706PT. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2015-07-06 08:00 | 2015-07-08 14:57 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2015-07-06 08:00 | 2015-07-10 17:00 | N | N | salvage out 6L68 line (E17193) which involves 30 spans of conductor and arms to be removed | Line |  | Purpose is to salvage out 6L68 line (E17193) which involves 30 spans of conductor and arms to be removed. | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 71s T2 (71s Lamoureux) | 2015-07-06 08:00 | 2015-07-09 17:00 | N | Y | 138 kV/240 kV bushing replacements | Transformer |  |  | 240 kV, For Information Only
ATCO | 2009s 703 (2009s Willow Lake),2009s 704 (2009s Willow Lake) | 2015-07-06 08:00 | 2015-07-10 16:00 | N | N | test 7L194 protection trips to 703, 704 | Circuit Breaker |  | Test 7L194 protection trips to 703, 704, 144kV ring bus will be open, AOC 7L182 and 7L126 each radial fed, risk minimal. | Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2015-07-06 08:00 | 2015-07-10 16:00 | N | N | doble transformer | Transformer
EPCOR | R724 Rossdale | 2015-07-06 08:00 | 2015-07-10 18:00 | N | N | breaker maintenance | Terminal Equipment |  |  | Pre-Condition
EPCOR | Namao N721 (Namao) | 2015-07-06 08:00 | 2015-07-06 18:00 | N | N | CT cutover | Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 38.3TR (ENMAX 38) | 2015-07-06 08:00 | 2015-07-07 16:00 | N | N | LTC maintenance | Transformer
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2015-07-06 08:00 | 2015-07-10 17:00 | N | N | re-align structures | Line
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11) | 2015-07-06 08:00 | 2015-07-14 07:00 | N | N | transformer spill containment | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24) | 2015-07-06 08:00 | 2015-07-17 16:00 | N | N | replace 24B138-24.81 with 24B138-24BT3 | Line, Transformer |  | Replace 24B138-24.81 with 24B138-24BT3 and bypass 24BT3 with temporary jumpers. Protection settings changes. | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 370s T1 (370s North Lethbridge) | 2015-07-06 10:00 | 2015-07-11 17:00 | N | N | replace 138/25kV bushings and surge arrestors | Transformer
ATCO | 813s 708 (813s Little Smoky) | 2015-07-06 11:00 | 2015-07-06 16:00 | N | N | breaker partial maintenance | Circuit Breaker |  | Breaker partial maintenance, Ring open | Contingency Requires Mitigation
ALTALINK | 728L (353s Plamondon - 157s Lac La Biche),157s 728W (157s Lac La Biche) | 2015-07-06 12:00 | 2015-07-10 16:30 | N | N | breaker replacement | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2015-07-06 13:00 | 2015-07-08 17:00 | N | Y | 138 kV breaker maintenance | Switch |  |  | Restricts Generation
ALTALINK | 275s T2 (275s Jenner) | 2015-07-06 13:00 | 2015-07-12 17:00 | N | Y | 240kV bushing replacement, oil leaks & tap changer maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 40s T2 (40s Wetaskiwin) | 2015-07-07 07:00 | 2015-07-08 17:00 | N | N | install sound wall In vicinity of T2 & T2 maintenance | Transformer
ALTALINK | 72s C1 (72s Leismer),72s 2052 (72s Leismer) | 2015-07-07 08:00 | 2015-07-08 12:00 | N | N | MEPPI warranty work on breaker. | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 77s T2 (77s Sagitawah),77s Sagitawah 138 kV East Bus | 2015-07-07 08:00 | 2015-07-07 11:00 | N | Y | SCADA upgrade project | Bus, Transformer |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 813s 710 (813s Little Smoky) | 2015-07-07 08:00 | 2015-07-07 12:00 | N | N | breaker partial maintenance, ring open | Circuit Breaker |  | Breaker partial maintenance, Ring open | Overload, Contingency Requires Mitigation
ALTALINK | 80L (152s Didsbury - 80L194A) | 2015-07-07 08:00 | 2015-07-18 14:00 | N | N | close open point "J" and cut 80L free from 152s | Line |  |  | Pre-Condition, For Information Only
ATCO | 740s H.R.Milner RTU/SCADA,810s Dome Cutbank RTU/SCADA | 2015-07-07 10:00 | 2015-07-07 12:00 | N | N | Smoky River tower routine radio maintenance | Terminal Equipment |  | RADIO DIGITAL LEDR 900S PM @ SMOKY RIVER ROUTINE MAINTENANCE ON THE LEDR RADIO FROM SMOKY RIVER TOWER TO KAKWA TOWER THERE WILL BE SEVERAL 5 MINUTE OUTAGES TO HR MILNER SUB AND DOME CUTBANK SUB SCADA WHILE POWER MEASUREMENTS ARE TAKEN. TIME TO RESTORE IN THE EVENT OF A FAILURE IS 15-20 MINUTES. | Affects Visibility
ATCO | 813s 713 (813s Little Smoky) | 2015-07-07 11:00 | 2015-07-07 17:00 | N | N | breaker partial maintenance, ring open | Circuit Breaker |  | Breaker partial maintenance, Ring open | Pre-Condition, Contingency Requires Mitigation
ATCO | 7L06 (A793s West Peace River - 784s Donnelly) | 2015-07-07 12:01 | 2015-07-09 14:30 | N | N | crossarm replacements, pole changes | Line |  | crossarm replacements, pole changes | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s T1 (77s Sagitawah),77s Sagitawah 138 kV West Bus | 2015-07-08 08:00 | 2015-07-08 11:00 | N | Y | SCADA upgrade project | Bus, Transformer |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 9L89 (885s McMillan - 2011s Dawes) | 2015-07-08 08:00 | 2015-07-11 16:00 | N | N | In service date: July 11, 2015 | Line
ENMAX | 39.2TR (ENMAX 39) | 2015-07-08 08:00 | 2015-07-10 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 166L (281s Johnson - 166L50) | 2015-07-08 08:00 | 2015-07-10 16:00 | N | N | In service date: July 9, 2015 | Line
ATCO | 813s 714C (813s Little Smoky),813s 714 (813s Little Smoky) | 2015-07-08 08:00 | 2015-07-08 12:00 | N | N | breaker partial maintenance, 714C not available | Shunts, Circuit Breaker |  | Breaker partial maintenance, 714C not available | Pre-Condition
ATCO | 9L07 (888s Dover - 2011s Dawes) | 2015-07-08 08:00 | 2015-07-11 16:00 | N | N | In service date: July 10, 2015 | Line
ATCO | 803s 701T (803s Bullpound),7L85 (804s Wintering Hills - 803s Bullpound),7L85 (803s Bullpound - 801s Anderson) | 2015-07-08 08:00 | 2015-07-08 16:00 | N | N | breaker replacement, install breaker fail protection & bird proofing | Transformer, Line |  | As part of the upcoming project E18644, 25KV Breaker replacement, One task was the installation of a breaker fail protection for 701TCS. And as such we will be required to tie into an existing CT circuit. The 701T transformer, due to age doesnt have the capabilities of allowing us to short the CTs So for us to tie into the circuit we need to de-energize 701T. Outage will be kept to a minimal time period as all prep work will be done prior to outage. 4 CT wires will need to be tied in, as there are no approved CT shorting devices on 701T Also to Tie in the protection to the lockout circuit. And then new breaker fail protection end to end functional tests will be done. During this time period, Another crew will be installing bird proofing on the 25KV bus work. | Firm Load Loss, Creates Radial Feeds
ATCO | 2011s Dawes | 2015-07-08 08:00 | 2015-07-11 16:00 | N | N | In service date: July 11, 2015 | Transformer
GREENGATEP | 972s 901 (972s Tinchebray) | 2015-07-08 09:00 | 2015-07-08 12:00 | N | Y | test the new status points brought to the 9L93 21A and 21B relays | Circuit Breaker |  | Breaker 901 will be operated to test the new status points brought to the 9L93 21A and 21B relays. | 240 kV, Contingency Requires Mitigation
GREENGATEP | 972s 903 (972s Tinchebray) | 2015-07-08 12:30 | 2015-07-08 16:00 | N | Y | test the new status points brought to the 9L93 21A and 21B relays | Circuit Breaker |  | Breaker 903 will be operated to test the new status points brought to the 9L93 21A and 21B relays. | 240 kV, Contingency Requires Mitigation
ATCO | 813s 715C (813s Little Smoky),813s 715 (813s Little Smoky) | 2015-07-08 13:00 | 2015-07-08 17:00 | N | N | breaker partial maintenance, 715C not available | Shunts, Circuit Breaker |  | Breaker partial maintenance, 715C not available | Pre-Condition, For Information Only
ALTALINK | 72s C2 (72s Leismer),72s 3052 (72s Leismer) | 2015-07-08 13:00 | 2015-07-09 17:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 40s T1 (40s Wetaskiwin) | 2015-07-09 07:00 | 2015-07-10 17:00 | N | N | install sound wall vicinity of T1 | Transformer |  |  | For Information Only
ALTALINK | 438S Westlock,438s T1 (438s Westlock) | 2015-07-09 07:00 | 2015-09-08 16:00 | N | N | replace T1, VR1 and 25kV switches,replace T1, VR1 and 25kV switchesv | Transformer, Station |  |  | For Information Only
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2015-07-09 08:00 | 2015-07-09 10:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 813s 716C (813s Little Smoky),813s 716 (813s Little Smoky) | 2015-07-09 08:00 | 2015-07-09 12:00 | N | N | breaker partial maintenance, 716C not available | Shunts, Circuit Breaker |  | Breaker partial maintenance, 716C not available | For Information Only
ALTALINK | 171s Redwater RTU/SCADA | 2015-07-09 11:30 | 2015-07-09 16:00 | N | N | required for breaker replacement | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 3AL (43s Shell Canada Jumping Pound jct - 3L tap),3L (245s Seebe - 3L145),3L (272s Springbank - 3L147) | 2015-07-10 08:00 | 2015-07-10 12:00 | N | N | switch maintenance - 3L145 & 3L147 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.82L (ENMAX 21 - ENMAX 20),ENMAX 21 B138-20.82 (ENMAX 21) | 2015-07-10 08:00 | 2015-07-10 16:00 | N | N | SF6 gas sample | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 940s 701T (940s Beartrap) | 2015-07-10 08:00 | 2015-07-10 16:00 | N | N | weather cover & bushing replacement | Transformer |  | 940S 701T NGR weather cover and 301 bushing replacement 701T and 301 at 940S will be out of service for the duration of the work Enbridge will be having a scheduled 8 hr outage on July 10th, 2015 Shawn Wentz will confirm with Dave Sokorinski 940S 701T NGR Weather guard installation 940S 301 bushing replacement 940S 301A hotspot investigate
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2015-07-10 08:00 | 2015-07-10 16:00 | N | N | HV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L48 (882s Triangle - 794s Valleyview) | 2015-07-10 08:00 | 2015-07-13 16:00 | N | N | pole changes | Line |  | Pole changes, 882s, 787s, and 784s radial fed from 793s | Firm Load Loss, Creates Radial Feeds
ALTALINK | 417L (55s Olds - 281s Johnson) | 2015-07-10 08:00 | 2015-07-12 16:00 | N | N | In service date: July 11, 2015 | Line
ALTALINK | 12s 852 (12s Heartland) | 2015-07-10 08:00 | 2015-07-10 16:00 | N | N | inspect/repair the T-chamber operating lever | Circuit Breaker |  |  | For Information Only
ALTALINK | 3L (272s Springbank - 3L147) | 2015-07-10 12:00 | 2015-07-22 17:00 | N | N | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72VN21 (Namao - 511s Victoria) | 2015-07-11 07:00 | 2015-07-11 18:00 | N | N | Doble Testing | Line |  |  | For Information Only
ATCO | 9L07 (885s McMillan - 888s Dover) | 2015-07-11 07:00 | 2015-07-23 16:00 | N | Y | tie in 2011s Dawes substation | Line |  | 9L07/9L89 In/out Tie in into 2011s Dawes sub. No jumpers will be installed and line will be completed in to the substation. On RTN switching the 240kV bus @ 2011s will be energized, Line number 9L07 will be retained for Dover to Dawes line. New line number 9L89 will used for the Dawes to McMillan line. | 240 kV, Restricts Generation
AESO-SC | 318s Scoria | 2015-07-11 08:00 | 2015-07-17 16:00 | N | N | In service date: July 15, 2015 | Transformer
TRANSALTAW, ALTALINK, STROBE, CHDI, GWPCORP, VISIONREQ | 528S Blue Trail Wind Farm,418s Ardenville,239S Castle River,240S McBride Lake,243S Soderglen Wind Farm,354S Summerview,CRE3 Cowley Ridge | 2015-07-11 08:00 | 2015-07-11 10:00 | N | N | internet outage | Station, Unit |  |  | For Information Only
EPCOR | 72RS5 (Rossdale - Strathcona) | 2015-07-13 07:00 | 2015-08-07 18:00 | N | N | termination replacement | Line |  |  | For Information Only
ALTALINK | 727L (65s High River - 727L39S) | 2015-07-13 07:00 | 2015-07-18 19:00 | N | N | Foothills 138kV: install caissons, footings, bases and poles | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2015-07-13 08:00 | 2015-07-16 16:30 | N | N | replace 54s32 | Transformer |  |  | For Information Only
ALTALINK | 71s C1 (71s Lamoureux),71s 952 (71s Lamoureux) | 2015-07-13 08:00 | 2015-07-15 17:00 | N | N | 138kV CT Replacement | Shunts, Circuit Breaker |  |  | For Information Only
ATCO | 7L92 (7L92D3 - 709s Vegreville) | 2015-07-13 08:00 | 2015-07-16 17:00 | N | N | 7L92 2015 climbing inspection | Line |  | 7L92 2015 climbing inspection | Firm Load Loss, Creates Radial Feeds
ALTALINK | 942L (681s Bannerman - 71s Lamoureux) | 2015-07-13 08:00 | 2015-07-16 17:00 | N | Y | 240kV 71s49 switch replacement | Line |  |  | 240 kV
EPCOR | Rossdale R723 (Rossdale) | 2015-07-13 08:00 | 2015-07-17 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2015-07-13 08:00 | 2015-07-13 16:00 | N | N | condo development piping underneath a section of the underground cable | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s T1 (275s Jenner) | 2015-07-13 08:00 | 2015-07-16 17:00 | N | Y | 240kV bushing replacement, oil leaks & doble maintenance | Transformer |  |  | 240 kV, For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),16B69-16.60 (ENMAX 16) | 2015-07-13 08:00 | 2015-07-17 16:00 | N | N | HV Breaker Inspection, dashpot Inspection, bulk oil. | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 8.3TR (ENMAX 8),8.4TR (ENMAX 8),Enmax 8 B138-4A0 (ENMAX 8),Enmax 8 B138-5A0 (ENMAX 8) | 2015-07-13 08:00 | 2015-07-17 16:00 | N | N | TR differential commissioning | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation
ALTALINK | 33S Spray,113L (20s Ghost - 33s Spray),76L (115s Mt. Allan - 33s Spray),84L (35s Rundle - 33s Spray) | 2015-07-13 08:00 | 2015-07-14 16:00 | N | N | testing | Station, Line |  |  | Creates Radial Feeds
ENMAX | 41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41),B138-40.81 (ENMAX 41) | 2015-07-13 08:00 | 2015-07-21 16:00 | N | N | SW's 85 @ 41s replacement, 41.1TR HV bushing replacement | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 1011L (163s Amoco Empress - 562s Cypress) | 2015-07-13 09:00 | 2015-07-16 15:00 | N | Y | line maintenance | Line |  |  | 240 kV, Over/Under Voltage
ATCO | 861s 601T (861s Eureka River) | 2015-07-13 09:30 | 2015-07-16 12:00 | N | N | 861S 25kV Bus birdproofing | Transformer |  | 861S 25kV BUS BIRDPROOFING Bird Mitigation Install, Arrestor Replace, Xmer Maintenance Station Load fed from 750S, (Mobile Sub #1) all feeders tied together and fed from 511 | For Information Only
ATCO | 754S 702 | 2015-07-13 10:00 | 2015-07-13 16:00 | N | N | breaker testing | Terminal Equipment |  | 754S 702 BREAKER SF6 HPL PARTIAL TESTING 702C not available | For Information Only
ALTALINK | 12s 852 (12s Heartland) | 2015-07-13 11:00 | 2015-07-18 17:00 | N | Y | operating lever replacement | Circuit Breaker |  |  | For Information Only, 500 kV
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake),157s 794X (157s Lac La Biche) | 2015-07-13 12:00 | 2015-07-17 16:00 | N | Y | breaker replacement | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ALTALINK | 28s R1 (28s West Brooks),28s 44 (28s West Brooks) | 2015-07-13 12:00 | 2015-07-21 17:00 | N | Y | oil reclaim, Bushing replacement | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 74s 2352 (74s Janet) | 2015-07-13 12:00 | 2015-07-16 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 796s 701T (796s Nipisi) | 2015-07-13 13:00 | 2015-07-14 16:00 | N | N | maintenance | Transformer |  | 796S 701T Oil Reclaim START THEY WILL BE FIXING SOME LEAKS BEFORE RECLAIMING THE OIL During GOI all sub load will be on 702T AS OF JUNE 10, THE SUB HAS 26 MVA TOTAL | For Information Only
SUNCOR | 226S Garden City | 2015-07-14 06:00 | 2015-07-15 18:00 | N | Y | annual outage | Station |  |  | Restricts Generation, For Information Only
CNRL | 842s Horizon Upgrading RTU/SCADA | 2015-07-14 07:00 | 2015-07-14 18:00 | N | N | upgrade | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L06 (A793s West Peace River - 784s Donnelly) | 2015-07-14 07:30 | 2015-07-16 14:30 | N | N | replace structures, crossarm replacements, pole changes | Line |  | Replace structures, crossarm replacements, pole changes | Creates Radial Feeds
Syncrude | D05 T2 (D05 Syncrude),D05 72kV Bus B | 2015-07-14 07:30 | 2015-07-15 19:30 | N | Y | D05 72 kV BUS 'B' & T2 Tranformer will be taken offline for PM work | Transformer, Bus |  |  | 240 kV, For Information Only
ALTALINK | 301s T1 (301s Queensland) | 2015-07-14 08:00 | 2015-07-14 16:00 | N | N | enable push button control on the airbreak switches | Transformer
ATCO | 7L81 (FNG Fort Nelson - 791s Rainbow Lake),791s 702 (791s Rainbow Lake) | 2015-07-14 08:00 | 2015-07-14 17:00 | N | Y | breaker maintenance and testing | Line, Circuit Breaker |  | Breaker 702 Maintenance and Testing / 7L81 OOS for the duration. | Restricts Generation
ALTALINK | 405s C1 (405s Waupisoo),405s 17 (405s Waupisoo) | 2015-07-14 08:00 | 2015-07-15 12:00 | N | N | MEPPI warranty work | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 608L (418s Ardenville - 608L72) | 2015-07-14 08:00 | 2015-07-25 18:00 | N | Y | Windy Flats:build and install new airbreaks | Line |  |  | Restricts Generation
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11) | 2015-07-14 08:00 | 2015-07-24 16:00 | N | N | transformer spill containment | Transformer |  |  | For Information Only
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2015-07-14 08:00 | 2015-07-14 11:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station),1055L (816s Petrolia - 629s Argyll Transfer Station) | 2015-07-14 08:00 | 2015-07-16 15:00 | N | Y | Line maintenance - replace structure | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
AESO-SC | PSS | 2015-07-14 21:00 | 2015-07-14 22:00 | N | N | Suncor GT10 - PSS will be disabled for 1 hr. | Terminal Equipment
ALTALINK | 528S Blue Trail Wind Farm | 2015-07-15 08:00 | 2015-07-16 17:00 | N | Y | substation work | Station |  |  | Restricts Generation
ALTALINK | 277s T2 (277s Hayter) | 2015-07-15 08:00 | 2015-07-23 12:00 | N | N | connect new T2 | Transformer |  | connect new T2 to 138/25kV busses, connect new AMI, upgrade cables on 2187L & 464L, create open point on UG bypass bus cables, install bird coverup, close open points B, D, E & F
ATCO | 959S SVC (959s Lanfine) | 2015-07-15 08:00 | 2015-07-16 16:00 | N | Y | Lanfine SVC training | Shunts |  | Lanfine SVC Training | 240 kV, For Information Only
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2015-07-15 10:00 | 2015-07-16 15:00 | N | N | line maintenance - damaged insulator replacement | Line
ALTALINK | 405s C2 (405s Waupisoo),405s 23 (405s Waupisoo) | 2015-07-15 13:00 | 2015-07-16 17:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ATCO | 813s 711 (813s Little Smoky) | 2015-07-15 13:00 | 2015-07-15 17:00 | N | N | breaker partial maintenance & ring open | Circuit Breaker |  | Breaker partial maintenance, Ring open | Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2015-07-15 19:00 | 2015-07-16 16:00 | N | N | urgent hotspot repair | Line |  |  | Pre-Condition
ATCO | 960s 908 (960s Birchwood Creek) | 2015-07-16 07:00 | 2016-02-04 17:30 | N | Y | construct 240kV breaker bay for new 9L144 line to 2015S Yeo substation | Circuit Breaker |  | Construct 240kV breaker bay for new 9L144 line to 2015S Yeo substation, ring bus @ 960s will be open at 9L57 side, 9L57 will be protected by one breaker (909) @ 960s | 240 kV
ENMAX | 15.2TR (ENMAX 15) | 2015-07-16 08:00 | 2015-07-16 12:00 | N | N | remove oil dry out processor on transformer | Transformer
ATCO | 813s 702 (813s Little Smoky) | 2015-07-16 08:00 | 2015-07-16 15:00 | N | N | breaker partial maintenance | Circuit Breaker |  | Breaker partial maintenance, Ring open | Contingency Requires Mitigation
ALTALINK | 250P Bighorn Plant RTU/SCADA | 2015-07-16 12:00 | 2015-07-16 14:00 | N | N | RTU outage | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 63s T2 (63s Red Deer),63s Red Deer 240kV South Bus | 2015-07-17 07:00 | 2015-07-17 17:30 | N | N | replacing risers from 63s10 to T2, CT contributions to A87/T2-0 and 240kV protections | Transformer, Bus |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2015-07-18 07:00 | 2015-07-19 16:00 | N | Y | Doble 65LA240-1080L-C & 25LZ240-1080L-C | Line |  |  | 240 kV
ALTALINK | 1049L (59s Peigan - 138s Windy Flats) | 2015-07-18 08:00 | 2015-07-24 16:00 | N | N | In service date: July 21, 2015 | Line |  |  | 240 kV
ALTALINK | 968L (370s North Lethbridge - 138s Windy Flats) | 2015-07-18 08:00 | 2015-07-24 16:00 | N | N | In service date: July 21, 2015 | Line |  |  | 240 kV
ENMAX | 37.81L (ENMAX 38 - ENMAX 37),ENMAX 37 B138-37.81 (ENMAX 37) | 2015-07-18 08:00 | 2015-07-18 16:00 | N | Y | HV breaker, repair faulty clutch on 37B138-37.81 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 80L (20s Ghost - 80L193A) | 2015-07-19 07:00 | 2015-07-25 17:00 | N | N | setting changes & renaming as 418L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 2.82L (ENMAX 2 - ENMAX 5),B138-2.82 (ENMAX 5) | 2015-07-19 08:00 | 2015-07-19 16:00 | N | N | breaker doble 5B138-2.82 | Line, Circuit Breaker |  |  | For Information Only
ENMAXGPI | 134S Taber Wind Farm | 2015-07-20 06:00 | 2015-07-21 17:00 | N | Y | substation maintenance | Station |  |  | Restricts Generation
ALTALINK | 430L (330P Genesee - 510S Sunnybrook) | 2015-07-20 07:00 | 2015-08-07 17:00 | N | N | line upgrades | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 883L (331s Ponoka - 429s Nelson Lake) | 2015-07-20 07:00 | 2015-07-25 19:00 | N | N | relocate 883L from (331s - 429s) to (288s - 429s) | Line |  |  | For Information Only
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2015-07-20 08:00 | 2015-07-21 17:00 | N | N | 7L92 2015 climbing inspection | Line |  | 7L92 2015 climbing inspection | Creates Radial Feeds
ALTALINK | 71s 1652 (71s Lamoureux) | 2015-07-20 08:00 | 2015-07-23 13:30 | N | Y | 240kV CT replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Saskpower | Sask Power SW905 | 2015-07-20 08:00 | 2015-07-20 19:00 | N | N | replace SW 905 Y CT & repair corona discharge | Circuit Breaker
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),74s 2152 (74s Janet),74s 2252 (74s Janet),ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D135 (ENMAX 25) | 2015-07-20 08:00 | 2015-07-24 17:00 | N | Y | ECTP: 1003L SPTR (single pole trip reclose) implementation | Line, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 30.1TR (ENMAX 30) | 2015-07-20 08:00 | 2015-07-21 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34),34B69-21.61 (ENMAX 34) | 2015-07-20 08:00 | 2015-07-20 16:00 | N | N | HV breaker inspection. ENMAX 34 breaker fail modification | Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 23.4TR (ENMAX 23) | 2015-07-20 08:00 | 2015-07-24 16:00 | N | N | doble test 23.4TR | Transformer |  |  | For Information Only
ENMAX | ENMAX 65 B240-D131 (ENMAX 65),ENMAX 65 B240-D130 (ENMAX 65) | 2015-07-20 08:00 | 2015-07-21 16:00 | N | Y | settings changes | Circuit Breaker |  |  | 240 kV
EPCOR | 665s TX1 (665s Dome) | 2015-07-20 08:00 | 2015-07-24 18:00 | N | Y | doble testing | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 12s 852 (12s Heartland) | 2015-07-20 08:30 | 2015-07-24 09:30 | N | Y | inspect/repair the T-chamber operating lever | Circuit Breaker |  |  | For Information Only, 500 kV
EPCOR | 1055L (816s Petrolia - 629s Argyll Transfer Station) | 2015-07-20 09:00 | 2015-07-23 15:00 | N | Y | line maintenance - replace structure | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress) | 2015-07-20 09:00 | 2015-07-23 15:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 915L (38s East Edmonton - 987s Clover Bar) | 2015-07-20 10:00 | 2015-07-23 17:00 | N | Y | replace 240kV PT 38s140 | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 291s T1 (291s Cochrane) | 2015-07-20 12:00 | 2015-07-27 17:00 | N | N | install 25kV feeder | Transformer |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky) | 2015-07-20 13:00 | 2015-07-22 17:00 | N | Y | maintenance | Shunts |  | 813S SVC GLYCOL COOLED MAINTENANCE SVC main, 703T oil leaks SVC not available | Pre-Condition
ALTALINK | 895s T2 (895s Suffield) | 2015-07-20 13:00 | 2015-07-23 17:00 | N | N | VR1 25kV bushings (source/load sides), tap changer maintenance, 895s43 switch adjustment | Transformer |  |  | For Information Only
ALTALINK | 17s 7 (17s Benalto) | 2015-07-20 13:00 | 2015-07-20 17:00 | N | Y | add nitrogen, inspect for leaks | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 115s T1 (115s Mt.Allan) | 2015-07-20 13:00 | 2015-07-21 17:00 | N | N | SFRA, doble test | Transformer |  |  | For Information Only
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2015-07-20 14:00 | 2015-07-20 17:00 | N | Y | required for TPR outage on both channels A & B | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 391s T1 (391s Balzac) | 2015-07-21 07:00 | 2015-07-22 17:30 | N | N | install bird cover-up | Transformer
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),15B69-15.62 (ENMAX 15),16B69-15.62 (ENMAX 16) | 2015-07-21 08:00 | 2015-07-22 16:00 | N | N | breaker inspection | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 706AL (452s B.F. Goodrich Fort Saskatchewan - 706L tap),706L (54s Fort Saskatchewan - 706L72B),706L (410s Josephburg - 706L72D) | 2015-07-21 08:00 | 2015-07-21 18:00 | N | N | replace 452s1, replace 138kV insulators | Line
ATCO | 869s 702T (869s Seal Lake) | 2015-07-21 08:30 | 2015-07-21 16:30 | N | N | major testing and maintenance | Transformer |  | 702T Major Testing and Maintenance, BKR 702 Partial PM, 702T LTC Conservator Top Up.Station load will be limited to 701T rating (13.3MVA) for the duration of the work. Techs to monitor 701T loading. Restore 702T or Shed 25kv load if required
ALTALINK | 62s C1 (62s Brazeau),62s 215 (62s Brazeau) | 2015-07-21 08:30 | 2015-07-22 11:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 883L (331s Ponoka - 429s Nelson Lake),331s 883E (331s Ponoka),331s Ponoka 138kV Bus | 2015-07-21 08:30 | 2015-07-21 17:00 | N | N | switch maintenance | Circuit Breaker, Line, Bus |  |  | For Information Only
ALTALINK | 33s6 (33s Spray) | 2015-07-21 09:00 | 2015-07-21 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 746s T2 (746s Sherwood Park) | 2015-07-21 10:00 | 2015-07-23 17:00 | N | N | T2 replacement, bushing monitor,& Hydran install | Transformer
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek),914L (86s Bigstone - 87s Gaetz) | 2015-07-21 19:39 | 2015-08-03 18:58 | N | Y | damaged structures due to storm (forced outage) | Line |  |  | 240 kV, Pre-Condition, Overload
ENMAXEC | 383S Kettles Hill Windfarm | 2015-07-22 07:00 | 2015-07-24 17:00 | N | Y | substation maintenance | Station |  |  | Restricts Generation
ATCO | 7L06 (A793s West Peace River - 784s Donnelly) | 2015-07-22 07:00 | 2015-08-01 17:30 | N | N | replace structures, D/C mitigation | Line |  | Replace structures. D/C mitigation. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 452S B.F. Goodrich Fort Saskatchewan,706AL (452s B.F. Goodrich Fort Saskatchewan - 706L tap) | 2015-07-22 08:00 | 2015-07-24 18:00 | N | N | replace T1 138kV / 25kV LA's | Station, Line
ENMAX | 14.2C (ENMAX 14) | 2015-07-22 08:00 | 2015-07-22 16:00 | N | N | doble 14CS138-14.2CAP | Shunts |  |  | For Information Only
ALTALINK | 310p 1852 (310p Sundance) | 2015-07-22 08:00 | 2015-07-24 11:00 | N | Y | urgent repair - replace leaking CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 65 B240-D134 (ENMAX 65),ENMAX 65 B240-D133 (ENMAX 65) | 2015-07-22 08:00 | 2015-07-23 16:00 | N | Y | settings changes to implement TPLR triple pole line reclosing on 1107L prior to the ISD of July 28th | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36) | 2015-07-22 08:00 | 2015-07-23 16:00 | N | N | LTC maintenance | Transformer
ATCO | 819s 701 (819s Whitby Lake),7L92 (819s Whitby Lake - 7L92D2) | 2015-07-22 08:30 | 2015-07-23 16:00 | N | N | breaker maintenance & climbing inspection | Line, Circuit Breaker |  | Breaker Maintenance to be done in conjunction with 7L92 GOI 2-33518. | Pre-Condition
ALTALINK | 429S Nelson Lake,883L (331s Ponoka - 429s Nelson Lake) | 2015-07-22 08:30 | 2015-07-23 17:00 | N | N | U/G cable maintenance | Station, Line
ALTALINK | 580s T2 (580s Sylvan Lake) | 2015-07-22 08:30 | 2015-07-23 17:00 | N | N | repair multiple leaks on T2 | Transformer
ATCO | 7L127 (774s Monitor - 932s Pemukan),774s 703 (774s Monitor) | 2015-07-22 09:00 | 2015-07-22 15:30 | N | N | breaker maintenance & partial testing | Line, Circuit Breaker |  | Bkr 703 Maintenance, BREAKER SF6 LTB145D1/B PARTIAL TESTING | Firm Load Loss, Creates Radial Feeds
ATCO | 7L127 (774s Monitor - 932s Pemukan) | 2015-07-22 09:00 | 2015-07-22 15:30 | N | N | Atco work | Line
ATCO | 735s 602T (735s Swan River) | 2015-07-22 10:00 | 2015-07-22 16:00 | N | N | PCB sampling | Transformer |  | 602T Outage for PCB Sampling / 602T not in service (hot stand-by) 601T carrying all sub load
ALTALINK | 178s C1 (178s Cynthia),178s 652 (178s Cynthia) | 2015-07-22 13:00 | 2015-07-23 17:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 62s12 (62s Brazeau) | 2015-07-22 23:00 | 2015-07-23 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s11 (62s Brazeau) | 2015-07-23 03:00 | 2015-07-23 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 391s T2 (391s Balzac) | 2015-07-23 07:00 | 2015-07-23 17:30 | N | N | install bird cover-up | Transformer
ALTALINK | 967L (370s North Lethbridge - 138s Windy Flats),1048L (138s Windy Flats - 59s Peigan),968L (370s North Lethbridge - 138s Windy Flats),138s Windy Flats 240kV Bus 2,138s 352 (138s Windy Flats),138s 1252 (138s Windy Flats) | 2015-07-23 08:00 | 2015-07-23 09:00 | N | Y | test energize 138sT2 | Line, Bus, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),B138-3.84 (ENMAX 13) | 2015-07-23 08:00 | 2015-07-23 16:00 | N | N | HV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2015-07-23 09:00 | 2015-07-23 17:00 | N | N | stops out of alignment | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-3 29PT-6 | 2015-07-23 09:00 | 2015-08-04 18:30 | N | N | maintenance | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 616L (103s Goose Lake - 616AL tap),616L (59s Peigan - 616AL tap) | 2015-07-23 10:00 | 2015-07-23 14:00 | N | N | customer requested outage | Line |  |  | Overload, Restricts Generation
AESO-SC | PSS | 2015-07-23 19:00 | 2015-07-23 20:00 | N | N | Suncor GT11 - PSS will be disabled for 1 hr | Terminal Equipment
ALTALINK | 185L (396s Pincher Creek - 379s Shell Canada Waterton) | 2015-07-24 08:00 | 2015-07-24 17:00 | N | N | repalce insulators | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 418L (20s Ghost - 281s Johnson) | 2015-07-24 08:00 | 2015-07-26 16:00 | N | N | In service date: July 25, 2015 | Line
ALTALINK | 725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2015-07-24 08:00 | 2015-07-24 17:00 | N | N | windy flats: repair deficiencies. | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 12s 752 (12s Heartland) | 2015-07-24 08:30 | 2015-08-21 17:00 | N | Y | operating lever replacement | Circuit Breaker |  |  | 500 kV
ALTALINK | 1212L (89s Ellerslie - 12s Heartland),12s 852 (12s Heartland) | 2015-07-24 08:30 | 2015-07-24 09:30 | N | Y | operate 12s952 and 12s752 circuit breakers | Line, Circuit Breaker |  |  | 500 kV
ALTALINK | 12s 952 (12s Heartland),12s Heartland 500kV Bus 2 | 2015-07-24 08:30 | 2015-08-21 17:00 | N | Y | operating lever replacement | Bus, Circuit Breaker |  |  | 500 kV
ALTALINK | 1238L (510s Sunnybrook - 330p Genesee) | 2015-07-25 07:00 | 2015-07-27 18:00 | N | Y | 1202 Breaker Replacement (1202 reaker Commissioning reqiuires an increase area of isolation) | Line |  |  | 500 kV
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm) | 2015-07-25 08:00 | 2015-07-25 16:00 | N | N | In service date: July 25, 2015 | Line
ALTALINK | 608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm) | 2015-07-25 08:00 | 2015-07-25 16:00 | N | N | In service date: July 25, 2015 | Line
ALTALINK | 883L (288s Wolf Creek - 429s Nelson Lake) | 2015-07-25 08:00 | 2015-07-25 17:00 | N | N | In service date: July 25, 2015 | Line
DAISHOWA | 147S Daishowa Plant | 2015-07-26 08:00 | 2015-07-26 18:30 | N | N | ADAMS dispatch interruption due to urgent network correction | Station |  |  | For Information Only
ALTALINK | 603L (59s Peigan - 243s Soderglen - 138s Windy Flats) | 2015-07-26 08:00 | 2015-07-28 18:00 | N | N | 138s Windy Flats sub: Cut 603L from 59s and energize from 138s | Line |  |  | Restricts Generation
EPCOR | RossdaleT1 (Rossdale) | 2015-07-27 07:00 | 2015-07-27 18:00 | N | N | TX secondary inspection | Transformer |  |  | For Information Only
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-07-27 07:00 | 2015-07-31 18:00 | N | N | Foothills 138kV: foundation work | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 42s C3 (42s Sarcee) | 2015-07-27 07:00 | 2015-07-27 17:30 | N | Y | review for future bird coverup | Shunts |  |  | 240 kV, For Information Only
ATCO | 7L92 (777s Vilna - 709s Vegreville) | 2015-07-27 08:00 | 2015-07-30 17:00 | N | N | 7L92 2015 climbing inspection | Line |  | 7L92 2015 climbing inspection | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar),71s 1352 (71s Lamoureux),71s 1252 (71s Lamoureux) | 2015-07-27 08:00 | 2015-07-29 17:00 | N | Y | 240kV CT replacement | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 11.81L (ENMAX 13 - ENMAX 11),B138-11.81 (ENMAX 13) | 2015-07-27 08:00 | 2015-07-27 16:00 | N | N | resample SF6 | Line, Circuit Breaker |  |  | For Information Only
GWPCORP | 243S Soderglen Wind Farm | 2015-07-27 08:00 | 2015-07-28 17:00 | N | N | annual maintenance | Station |  |  | Restricts Generation
ENMAX | 1.7TR (ENMAX 1) | 2015-07-27 08:00 | 2015-07-31 16:00 | N | N | LTC maintenance Rienhausen well type | Transformer |  |  | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2015-07-27 08:00 | 2015-07-31 16:00 | N | N | doble | Transformer |  |  | For Information Only
GWPCORP | 243S Soderglen Wind Farm | 2015-07-27 08:00 | 2015-07-28 17:00 | N | N | customers annual outage | Station |  |  | For Information Only
ALTALINK | 719L (263s Strachan - 719L259C) | 2015-07-27 08:00 | 2015-07-30 17:00 | N | N | relocation of H structure and installation of 138kV screw piles | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 215L (38s East Edmonton - 286s Yasa) | 2015-07-27 09:00 | 2015-07-31 15:00 | N | N | Line raise for pipeline crossing - back-up dates. | Line |  |  | Creates Radial Feeds
BCH | 5L91 (Selkirk - Ashton Creek) | 2015-07-27 09:00 | 2015-07-28 17:00 | N | Y | replace flashed and broken insulators | Line |  |  | Limits ATC
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap),775s 602 (775s Sullivan Lake) | 2015-07-27 09:00 | 2015-07-28 16:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | Bkr 602 Maintenance, No System concerns N.O. 6L12D3 will be closed and 773S Coronation will be fed from 774S Monitor. | Pre-Condition
ALTALINK | 17s 5 (17s Benalto) | 2015-07-27 10:00 | 2015-07-28 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
TRANSALTA | 59s 352 (59s Peigan) | 2015-07-27 10:00 | 2015-07-28 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 946L (89s Ellerslie - 38s East Edmonton) | 2015-07-27 10:00 | 2015-07-30 17:00 | N | Y | replace 240kV PT 38s141 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 74s 76 (74s Janet) | 2015-07-27 10:00 | 2015-07-28 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 358s C1 (358s Amoco Brazeau),358s 552 (358s Amoco Brazeau) | 2015-07-27 13:00 | 2015-07-28 17:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 786s 701T (786s High Level) | 2015-07-27 13:00 | 2015-07-29 16:00 | N | N | install jumper | Transformer |  | Load to be transferred to 702T (transformer paralleling required), a temporary jumper J1 will be cut open between 701TCS and the 144kV bus to maintain 144kV bus integrity. 786S 701TCS CCT SWITCHER COMPLETE MAINTENANCE | Pre-Condition, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2015-07-27 19:00 | 2015-07-28 07:00 | N | N | high load move | Line |  |  | Pre-Condition, Creates Radial Feeds
AESO, Medicine Hat, CMH | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview),20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2015-07-28 07:00 | 2015-07-28 15:00 | N | N | high load escort | Line |  |  | For Information Only
EPCOR | RossdaleT2 (Rossdale) | 2015-07-28 07:00 | 2015-07-28 18:00 | N | N | TX secondary inspection | Transformer |  |  | For Information Only
ALTALINK | 42s C2 (42s Sarcee) | 2015-07-28 07:00 | 2015-07-28 17:30 | N | Y | review for future bird coverup | Shunts |  |  | 240 kV
BLACKSPRING | 485S Black Springs | 2015-07-28 07:00 | 2015-07-29 19:00 | N | Y | substation annual maintneance | Station |  |  | Restricts Generation
ALTALINK | 3L (272s Springbank - 3L147) | 2015-07-28 07:30 | 2015-08-10 12:00 | N | N | line rebuild | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1042L (485s Blacksprings - 554s Travers),554s1042 (554s Travers) | 2015-07-28 08:00 | 2015-07-28 18:00 | N | Y | maintenance | Switch, Line |  |  | 240 kV, Restricts Generation
ALTALINK | 217s C1 (217s North Red Deer) | 2015-07-28 08:00 | 2015-07-28 14:00 | N | N | replace blown capacitor | Shunts |  |  | Pre-Condition
Millar Weste | Millar Western | 2015-07-28 08:00 | 2015-07-28 16:00 | N | N | In service date: July 28, 2015 (2 x 2.72 MW) behind the fence | Unit
ATCO | 7L38 (875s Algar - 917s Horse River),875s 701 (875s Algar) | 2015-07-28 08:00 | 2015-07-28 16:30 | N | N | alarm wiring change | Line, Circuit Breaker |  | The existing wiring for the breaker 701 alarms are tied to the trip circuit. The positive voltage should be coming from a terminal from the tele-control panel. This wiring needs to be changed. A wiring change has to be made and ensure alarms are still coming in. | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2015-07-28 08:00 | 2015-07-28 16:00 | N | N | HV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 16.1TR (ENMAX 16) | 2015-07-28 08:00 | 2015-07-28 16:00 | N | N | hook up oil processor | Transformer |  |  | For Information Only
ALTALINK | 171s T1 (171s Redwater) | 2015-07-28 08:30 | 2015-07-30 17:00 | N | N | 138kV and 25kV bushing replacement | Transformer |  |  | For Information Only
ATCO | 939s 904 (939s Livock) | 2015-07-28 12:00 | 2015-07-30 12:58 | N | N | Emergency Breaker maintenance GOI - Low SF6 Gas BKR 904 | Circuit Breaker |  | Emergency Breaker maintenance GOI - Low SF6 Gas BKR 904 | 240 kV, Contingency Requires Mitigation
EPCOR | RossdaleT3 (Rossdale) | 2015-07-29 07:00 | 2015-07-29 18:00 | N | N | secondary inspection | Transformer
ALTALINK | 74s 850E (74s Janet) | 2015-07-29 08:00 | 2015-07-30 17:00 | N | N | breaker maintenance | Circuit Breaker
ENMAX | 31.1C (ENMAX 31) | 2015-07-29 08:00 | 2015-07-29 16:00 | N | N | hot spot repair | Shunts |  |  | For Information Only
ALTALINK | 277s T1 (277s Hayter) | 2015-07-29 08:00 | 2015-07-30 12:00 | N | N | create open point 'M' | Transformer
ENMAX | 15.60L (ENMAX 21 - ENMAX 15),15B69-15.60 (ENMAX 15) | 2015-07-29 08:00 | 2015-07-30 16:00 | N | N | breaker inspection | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 59s 1152 (59s Peigan) | 2015-07-29 08:30 | 2015-07-29 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 602s C1 (602s Cold Creek),602s 852 (602s Cold Creek) | 2015-07-29 10:00 | 2015-07-30 14:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 256s T2 (256s Harmattan) | 2015-07-29 13:00 | 2015-07-30 17:00 | N | N | doble & maintenance | Transformer
ATCO | 787s 702T (787s High Prairie) | 2015-07-29 13:30 | 2015-07-29 16:30 | N | N | push new settings and test 702T 50/51N | Transformer |  | Push New Settings and Test 702T 50/51N, 702T 87 Relay will remain in service.
ALTALINK | 63s T1 (63s Red Deer),63s T3 (63s Red Deer),426L (194s South Red Deer - 63s Red Deer) | 2015-07-30 08:00 | 2015-09-04 10:00 | N | Y | reconductor bus and replace bus diff | Transformer, Line |  |  | 240 kV
ENMAX | ENMAX 1 | 2015-07-30 08:00 | 2015-07-30 16:00 | N | N | hot spot repair | Station
ALTALINK | 277s T1 (277s Hayter) | 2015-07-30 12:00 | 2015-08-26 13:00 | N | N | install MOD on 277s748W and commission | Transformer
ALTALINK | 426L (194s South Red Deer - 63s Red Deer) | 2015-07-30 18:01 | 2015-09-04 10:00 | N | N | line rebuild, protection work & 80L renaming as 426L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale C1,Rossdale C2 | 2015-07-31 07:00 | 2015-07-31 18:00 | N | N | measurement on C1 cap bank | Shunts |  |  | For Information Only
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2015-07-31 08:00 | 2015-07-31 16:00 | N | N | Resample SF6 Gas Sample on 5B138-1.84 | Line
EPCOR | Rossdale C1 (Rossdale) | 2015-07-31 18:01 | 2018-09-04 17:00 | N | N | forced outage | Shunts |  |  | For Information Only
FORTIS | 1020s Exshaw Extension | 2015-08-01 08:00 | 2015-08-07 16:00 | N | N | In service date: August 5, 2015 | Transformer
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 13 - 2.83L tap),ENMAX 5 B138-2.83 (ENMAX 5),32B138-32.83 (ENMAX 32) | 2015-08-01 08:00 | 2015-08-01 16:00 | N | N | HV breaker maintenance on 13B138-2.83. SF6 gas sample on 5B138-2.83 | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 2032S Sweetheart Lake | 2015-08-01 08:00 | 2015-08-04 16:00 | N | N | In service date: August 1, 2015 | Station |  |  | 240 kV
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River),788s 703 (788s Hotchkiss) | 2015-08-01 10:54 | 2015-08-05 12:00 | N | N | forced outage - farmer hit a pole | Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41) | 2015-08-02 08:00 | 2015-08-02 16:00 | N | N | HV switch maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 920L (71s Lamoureux - 557s Castle Downs),71s 1652 (71s Lamoureux),71s 1552 (71s Lamoureux) | 2015-08-03 08:00 | 2015-08-05 17:00 | N | Y | 240 kV CT replacement at 71s | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 40.1TR (ENMAX 40),ENMAX 40 B138-32.83 (ENMAX 40),32.83L (ENMAX 32 - ENMAX 40) | 2015-08-03 08:00 | 2015-08-03 16:00 | N | N | maintenance | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 447s T2 (447s Enchant) | 2015-08-03 10:00 | 2015-08-10 15:00 | N | N | warranty repair work | Transformer
ALTALINK | 700L (422s Westwood - 746L tap),746s Sherwood Park 138kV East Bus | 2015-08-04 07:00 | 2015-08-07 12:00 | N | N | install bird cover-up & replace 746s36 PT | Line, Bus |  |  | Overload, Creates Radial Feeds
ALTALINK | 932L (74s Janet - 162s Beddington) | 2015-08-04 07:00 | 2015-08-16 15:00 | N | Y | salvage old 917L Bay and associated equipment | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 856s 902 (856s Kinosis),856s 904 (856s Kinosis),9L45 (856s Kinosis - 2049s Kettle River) | 2015-08-04 08:00 | 2015-08-10 18:00 | N | Y | construction to accommodate new design for 900BS2 and protection work | Circuit Breaker, Line |  | Construction, 856s Kinosis will be radial fed from 9L85, 2049s Kettle will be radial fed from 9L990, 240kV ring bus @ 856s will be open between 902B and 904A Scope of Work: Construction -Connect 903B to 900BS3 -Construction electrical cutovers to accommodate new design for 900BS2 and 903 -Perform cutovers on 9L45 21'A' & 21'B' protection -Commissioning on all new and modified logic circuits | 240 kV, Contingency Requires Mitigation
ENMAX | 5.5TR (ENMAX 5) | 2015-08-04 08:00 | 2015-08-04 16:00 | N | N | fix deficiencies | Transformer
ENMAX | 13.1TR (ENMAX 13) | 2015-08-04 08:00 | 2015-08-20 16:00 | N | N | LTC maintenance, gas relay, temp gauge alarms | Transformer
ENMAX | 21.1C (ENMAX 21) | 2015-08-04 08:00 | 2015-08-05 16:00 | N | N | cap bank maintenance | Shunts |  |  | For Information Only
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2015-08-04 08:00 | 2015-08-07 16:30 | N | N | replace 54s39 | Transformer
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2015-08-04 08:30 | 2015-08-06 16:30 | N | N | breaker maintenance | Line |  | Breaker Maintenance @ 717S and 846S two crews. 7L28 will be out of service for the duration of work | Pre-Condition, Overload, Creates Radial Feeds
Syncrude | Aurora 52-222 (Aurora) | 2015-08-04 09:00 | 2015-08-07 16:30 | N | N | repair gas leak | Circuit Breaker
ALTALINK | 701L (395s North Holden - 223s Strome) | 2015-08-04 10:00 | 2015-08-06 18:01 | N | N | line maintenance | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 38 (39s Bickerdike) | 2015-08-04 13:00 | 2015-08-05 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 198s T1 (198s Blackfalds) | 2015-08-04 13:00 | 2015-08-06 17:00 | N | N | T1 bushing replacement | Transformer
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2015-08-04 13:00 | 2015-08-06 16:00 | N | N | 7L171-straighten #750 and #751-splice wire in | Line |  | 7L171-straighten #750 and #751-Splice wire In | Firm Load Loss, Creates Radial Feeds
ALTALINK | 752L (64s East Crossfield - 752L67) | 2015-08-05 08:00 | 2015-08-07 17:30 | N | N | Line maintenance | Line |  |  | Pre-Condition, Overload, Restricts Generation
ALTALINK | 983L (251s Whitla - 244s Bowmanton),244s 983 (244s Bowmanton) | 2015-08-05 08:00 | 2015-08-05 17:00 | N | Y | emergency 240kV switch repair | Switch, Line |  |  | 240 kV
ALTALINK | 433L (291s Cochrane - T793s Horse Creek) | 2015-08-05 09:00 | 2015-08-05 14:00 | N | N | required for TPR outage on both channels A & B | Line |  |  | Pre-Condition, Creates Radial Feeds
ATCO | 802s 701T (802s Michichi Creek),6L56 (763s Hanna - 802s Michichi Creek) | 2015-08-05 09:00 | 2015-08-05 16:00 | N | N | bushing oil Samples & 606 partial | Line, Transformer |  | 6L56 will be open ended @ 802s, 701T Outage for Bushing Oil Samples & 606 Partial | Pre-Condition, Over/Under Voltage
ATCO | 7L30 (732s Mitsue - 844s AEC Mill),844s 703 (844s AEC Mill) | 2015-08-05 09:00 | 2015-08-05 16:00 | N | N | maintenance | Circuit Breaker, Line |  | BKR 703 Maintenance | Creates Radial Feeds
ALTALINK | 985S Exshaw | 2015-08-05 10:00 | 2015-08-06 10:00 | N | N | energizing new substation 1020s | Station
ALTALINK | 359s T2 (359s Esso West Pembina) | 2015-08-05 10:00 | 2015-08-05 12:00 | N | N | replacing breaker | Transformer
SUNCOR | 29PL6-5 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2015-08-05 15:00 | 2015-08-12 18:00 | N | N | 29PL6-5 72kV line emergency work | Line |  |  | For Information Only
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station) | 2015-08-06 07:00 | 2015-08-06 18:00 | N | Y | leaking pothead | Line |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 58s C1 (58s Edson),58s 35 (58s Edson) | 2015-08-06 08:00 | 2015-08-06 17:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition
VISIONREQ | 354S Summerview | 2015-08-06 08:00 | 2015-08-07 17:00 | N | Y | annual sub maintenance | Station |  |  | Restricts Generation
ALTALINK | 56L (245s Seebe - 20s Ghost) | 2015-08-06 08:00 | 2015-08-06 17:00 | N | N | emergency cross-arm repair/replacement | Line
ALTALINK | 71s C2 (71s Lamoureux),71s 1052 (71s Lamoureux) | 2015-08-06 08:30 | 2015-08-06 17:00 | N | N | breaker maintenance & replace 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 756s 602T (756s Bigfoot) | 2015-08-06 09:00 | 2015-08-06 17:00 | N | N | customer outage | Transformer
ATCO | 6L97 (735s Swan River - 739s Edith Lake),735s 603 (735s Swan River) | 2015-08-06 10:00 | 2015-08-06 13:00 | N | N | repair leak on 603 | Circuit Breaker, Line |  | 6L97 will be open ended @ 735s, Repair Leak on 603 | Pre-Condition, Over/Under Voltage
ATCO | 772s 601T (772s Youngstown) | 2015-08-06 11:00 | 2015-08-06 16:00 | N | N | 25kV load will be transferred to adjacent substations, oil samples from bushings for PCB value | Transformer |  | 25kV load will be transferred to adjacent substations, Oil samples from 601T Bushings for PCB value
EPCOR | 987s CGB2 (987s Clover Bar) | 2015-08-07 08:00 | 2015-08-17 18:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
PETROFUND | 114S Ghost Pine | 2015-08-07 22:00 | 2015-08-08 | N | N | ICCP and network connectivity | Station |  |  | Affects Visibility
ENMAX | 6.80L (ENMAX 30 - ENMAX 6),30B138-6.80 (ENMAX 30),ENMAX 6 B138-6.80 (ENMAX 6) | 2015-08-09 08:00 | 2015-08-09 16:00 | N | N | HV breaker inspection & SF6 sample on 6B138-6.80 & 30B138-6.80 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 746s T1 (746s Sherwood Park) | 2015-08-10 07:00 | 2015-08-13 17:00 | N | N | install bird cover-up | Transformer |  |  | For Information Only
EPCOR | CV5 (557s Castle Downs - 511s Victoria) | 2015-08-10 07:00 | 2015-08-21 18:00 | N | Y | manhole inspections | Line |  |  | 240 kV, Overload
ALTALINK | 77s 652 (77s Sagitawah) | 2015-08-10 08:00 | 2015-08-10 16:00 | N | N | SCADA upgrade project | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 752L (653s Summit - 752L76) | 2015-08-10 08:00 | 2015-08-14 17:30 | N | N | airbreak replacement | Line |  |  | Pre-Condition, Prevents Normal Events, Creates Radial Feeds
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),16B69-16.60 (ENMAX 16),34B69-16.60 (ENMAX 34) | 2015-08-10 08:00 | 2015-08-11 16:00 | N | N | HV breaker inspection 34B69-16.60, finish maintenance on 16B69-16.60 | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 820s 505C1 (820s Hangingstone),820s 505C2 (820s Hangingstone),820s 505 (820s Hanging Stone) | 2015-08-10 08:00 | 2015-08-10 17:30 | N | N | partial maintenance on 505 breaker | Shunts, Circuit Breaker |  | Loss of use of 10MVAR of capacitor banks for 25kv V control, Partial Maintenance on 505 BKR | For Information Only
ATCO | 856s 902 (856s Kinosis) | 2015-08-10 08:00 | 2015-08-23 18:00 | N | Y | construction and commissioning for 240kV bus expansion | Circuit Breaker |  | Construction and commissioning for 240kV bus expansion, 240kV ring bus will be open, no added risk, 903T will be placed in service on the RTN switching for this permit. Sequence 1. Aug 8 Issue this permit 2. Aug 8 Release permit 2-31828 (energize 9L45) 3. Aug 8-19 Construction 4. Aug 19 Confirm permit 2-xxxxx RTN switching complete (energize 9L85) 5 Aug 23 Issue 2-31834 (240kV partial ) 6. Aug 23 Release this permit. 7. Aug 23 Energize and soak 903T from 9L45 side of 240kV bus 8. Aug 24 Release COG 2-32192 on 703TD 9. Aug 24 Release COG 2-32196 on 703B 10. Aug 24 Chk phasing 11. Aug 24 Switch to parallel 903T to 902T and transfer load onto 903T | 240 kV
ENMAX | 36.2TR (ENMAX 36) | 2015-08-10 08:00 | 2015-08-11 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2015-08-10 08:00 | 2015-08-14 16:00 | N | N | doble 23.4TR | Transformer |  |  | For Information Only
ALTALINK | 54s C1 (54s Fort Saskatchewan),54s T1 (54s Fort Saskatchewan),694L (54s Fort Saskatchewan - 422s Westwood),706L (54s Fort Saskatchewan - 706L72B),54s Fort Saskatchewan 138 kV West Bus | 2015-08-10 08:00 | 2015-08-20 16:30 | N | N | replace 54s45 ,install new cap bank protection | Bus, Transformer, Line, Shunts |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L24 (846s Grand Centre - 700s Bonnyville),846s 702 (846s Grand Centre) | 2015-08-10 09:15 | 2015-08-11 16:00 | N | N | breaker 702 at 846s partial maintenance | Circuit Breaker, Line |  | Breaker 702 @ 846S Partial Maintenance - 7L24 will be open ended for the duration of the work. | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 385s T2 (385s Spring Coulee) | 2015-08-10 11:00 | 2015-08-10 17:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ALTALINK | 183s Underwood,445L (183s Underwood - 170s Pike),183s T2 (183s Underwood),183s T1 (183s Underwood) | 2015-08-10 11:00 | 2015-08-14 17:00 | N | N | T2 H2 IDD repairs, check X2 current for oil seepage, replace gaskets on T1 X0 bushing | Line, Transformer, Station |  |  | For Information Only
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2015-08-10 13:00 | 2015-08-14 17:00 | N | Y | make up new splices and complete testing | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 478s T2 (478s Tucuman) | 2015-08-10 13:00 | 2015-08-11 17:00 | N | N | replacing H2 bushing | Transformer |  |  | For Information Only
ALTALINK | 294s T1 (294s Brazeau Outlet Works) | 2015-08-10 14:00 | 2015-08-13 17:00 | N | N | 138kV and 15kV bushings replacement | Transformer |  |  | For Information Only
Saskpower | Sask Power SW908 | 2015-08-11 07:00 | 2015-08-11 17:00 | N | Y | air system maintenance | Circuit Breaker |  |  | Limits ATC
ALTALINK | 40s T2 (40s Wetaskiwin) | 2015-08-11 08:00 | 2015-08-13 17:00 | N | N | repairing oil leaks & maintenance | Transformer
ALTALINK | 77s 51 (77s Sagitawah) | 2015-08-11 08:00 | 2015-08-11 16:00 | N | Y | SCADA upgrade project | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 876s 902T (876s Brintnell) | 2015-08-11 08:00 | 2015-08-12 18:00 | N | Y | major testing / 901T will be carrying the load | Transformer |  | 876S BRINTNELL 902T O/S FOR Major testing. / 901T will be carrying the load
ALTALINK | 370s T1 (370s North Lethbridge) | 2015-08-11 08:00 | 2015-08-11 17:00 | N | N | repair bushing cap on one bushing that was just recently installed | Transformer
ALTALINK | 118s T2 (118s Canmore) | 2015-08-11 09:00 | 2015-08-11 17:00 | N | N | switch replacement | Transformer
ATCO | 732s 704 (732s Mitsue) | 2015-08-11 09:00 | 2015-08-11 16:00 | N | N | partial testing, maintenance & CT leak repair | Circuit Breaker |  | BREAKER SF6 HPL PARTIAL TESTING, 704 @ 732S Perform maint on 704 and 704 CT leak repair Open 144 Ring during duration of Repair | Contingency Requires Mitigation
ATCO | 770s 703T (770s Three Hills),7L159 (7L16 - 770s Three Hills),770s 704 (770s Three Hills),770s 703 (770s Three Hills) | 2015-08-11 10:00 | 2015-08-13 15:00 | N | N | transformer L/A replacement & breaker partial maintenance | Circuit Breaker, Transformer, Line |  | 770s, 768s, 114s, and 948s on radial feed, all 703T load at 770s will be transferred to 701T, 703T L/A replacement, 704 & 703 Partial PM's | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal) | 2015-08-12 07:00 | 2015-08-12 17:00 | N | Y | line mitigation | Line |  | Line mitigation | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39) | 2015-08-12 08:00 | 2015-08-13 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 701L (395s North Holden - 223s Strome) | 2015-08-12 08:00 | 2015-08-13 15:00 | N | N | line maintenance | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 138-RB83 (162s Beddington) | 2015-08-12 08:00 | 2015-08-12 16:00 | N | N | heater repairs | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 33s5 (33s Spray) | 2015-08-12 09:00 | 2015-08-12 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 170L (632s Russell - 799s Coleman),799s 170E (799s Coleman) | 2015-08-12 09:00 | 2015-08-12 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 732s 706 (732s Mitsue) | 2015-08-12 09:00 | 2015-08-12 14:00 | N | N | breaker maintenance | Circuit Breaker |  | Breaker maintenance - Ring Bus will remain open for the duration | Contingency Requires Mitigation
SUNCOR | 226S Garden City | 2015-08-13 08:00 | 2015-08-13 16:00 | N | N | swap of backup ISP provider & replacing ISP radios | Station
ALTALINK | 163s Amoco Empress RTU/SCADA | 2015-08-13 15:00 | 2015-08-13 15:20 | N | N | update RTU config | Terminal Equipment |  |  | 240 kV, Affects Visibility
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat) | 2015-08-14 07:00 | 2015-08-22 18:00 | N | Y | re-route line to new ROW between structures 2 - 5 & change insulators on structures 2, 7, 8, 21, 23, 41, 50 & 55 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2404 (805s Jasper) | 2015-08-14 12:00 | 2015-08-14 16:00 | N | Y | switching demonstration for commercial | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 138S R1 (138s Windy Flats),138S R2 (138s Windy Flats),1037L (138s Windy Flats - 237s Foothills),1038L (138s Windy Flats - 266s Foothills) | 2015-08-15 08:00 | 2015-08-21 16:00 | N | N | In service date: August 20, 2015 | Line, Shunts |  |  | 240 kV
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2015-08-15 08:00 | 2015-08-15 16:00 | N | Y | doble 25LA240-1003L-C | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2015-08-16 08:00 | 2015-08-16 16:00 | N | Y | doble 25LA240-985L-C | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
DAISHOWA | 147S Daishowa Plant | 2015-08-16 08:00 | 2015-08-16 18:30 | N | N | ADAMS dispatch interruption due to urgent network correction | Station |  |  | For Information Only
ENMAX | ENMAX 25 B240-D133 (ENMAX 25) | 2015-08-16 08:00 | 2015-08-21 16:00 | N | Y | ALSTOM 240KV breaker modification. Doble test. | Circuit Breaker |  |  | 240 kV
EPCOR | 816s T1 (816s Petrolia) | 2015-08-17 07:00 | 2015-08-17 12:00 | N | Y | measure flange | Transformer |  |  | 240 kV
ALTALINK | 63s T1 (63s Red Deer),63s Red Deer 240kV North Bus | 2015-08-17 07:00 | 2015-08-18 17:00 | N | Y | trip testing of 138kV bus protection | Bus, Transformer |  |  | 240 kV, Firm Load Loss, Prevents Normal Events, Creates Radial Feeds
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2015-08-17 08:00 | 2015-08-21 17:30 | N | Y | Telus cell tower antenna upgrades | Line |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 13.82L (ENMAX 22 - ENMAX 13),ENMAX 22 B138-13.82 (ENMAX 22) | 2015-08-17 08:00 | 2015-08-18 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 23.4TR (ENMAX 23) | 2015-08-17 08:00 | 2015-08-18 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 1.6TR (ENMAX 1) | 2015-08-17 08:00 | 2015-08-21 16:00 | N | N | Doble | Transformer |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27) | 2015-08-17 08:00 | 2015-08-17 16:00 | N | N | breaker close circuit repair | Transformer |  |  | For Information Only
ALTALINK | 752L (64s East Crossfield - 752L67) | 2015-08-17 08:00 | 2015-08-28 17:30 | N | Y | line maintenance | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds, Impacts RAS
ATCO | 9L85 (856s Kinosis - 977s Salt Creek) | 2015-08-17 08:00 | 2015-08-22 16:00 | N | Y | construction work. 856s, 2049s, and T72S will be radial fed via 9L990 | Line |  | Construction, 856s, 2049s, and T72S will be radial fed via 9L990 | 240 kV, Restricts Generation, Creates Radial Feeds
ALTALINK | 681s T2 (681s Bannerman) | 2015-08-17 09:00 | 2015-10-09 12:00 | N | Y | connect cables from transformer to customer GIS, interface testing | Transformer |  |  | 240 kV
ALTALINK | 681s T1 (681s Bannerman) | 2015-08-17 09:00 | 2015-10-09 12:00 | N | Y | connect cables from transformer to customer GIS, interface testing | Transformer |  |  | 240 kV
ALTALINK | 701L (395s North Holden - 223s Strome) | 2015-08-17 10:00 | 2015-08-20 15:00 | N | N | line maintenance | Line |  |  | Over/Under Voltage
ATCO | 6L09 (767s Oyen - 6L21 tap),763s 603 (763s Hanna) | 2015-08-17 12:30 | 2015-08-17 16:00 | N | N | 776s, 772s, and Empress Pipeline radial fed from 767s, Breaker 603 Partial PM | Circuit Breaker, Line |  | 776s, 772s, and Empress Pipeline radial fed from 767s, Breaker 603 Partial PM | Creates Radial Feeds
ALTALINK | 923L (324s Cassils - 356s Milo) | 2015-08-17 13:00 | 2015-08-17 14:00 | N | Y | EATL interface: test open line terminal into RAS relay for 923L | Line |  |  | 240 kV, Overload
ATCO | 796s 702T (796s Nipisi) | 2015-08-17 13:00 | 2015-08-18 16:00 | N | N | 796S 702T oil reclaim start | Transformer |  | 796S 702T Oil Reclaim Start Sub Load on 701T during GOI. AS OF JUNE 10, THE LOAD WAS AT 24 MVA | For Information Only
ALTALINK | 103s 1152 (103s Goose Lake) | 2015-08-17 13:00 | 2015-08-18 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 302S Cardinal River | 2015-08-18 07:00 | 2015-08-19 17:00 | N | N | install 69kV LA's | Station |  |  | For Information Only
ALTALINK | 336s T1 (336s Fincastle Sub) | 2015-08-18 07:00 | 2015-08-19 17:00 | N | N | replace SS1 Transformer, 336s13, & 336s12 fuses | Transformer |  |  | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2015-08-18 08:00 | 2015-08-18 16:00 | N | N | breaker close circuit repair | Transformer |  |  | For Information Only
ALTALINK | 89s 1252 (89s Ellerslie) | 2015-08-18 08:30 | 2015-08-18 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L160 (837s Mahihkan - 970s Bourque),837s 703 (837s Mahihkan) | 2015-08-18 09:00 | 2015-08-19 16:00 | N | N | breaker maintenance,breaker maintenance. | Circuit Breaker, Line |  | 837S 703 breaker maintenance - 7L160 will be out of service for duration of work.
ALTALINK | 838L (14s Devon - 325s Leduc) | 2015-08-18 12:00 | 2015-08-18 15:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 1065L (102s Langdon - 74s Janet) | 2015-08-19 07:00 | 2015-08-19 15:00 | N | Y | L to J: install of corona rings on 240kV lightning arrestors on 1065L bay | Line |  |  | 240 kV, Overload
ALTALINK | 1117L (898s Heart Lake - 167s Ipiatik Lake) | 2015-08-19 08:00 | 2015-08-22 16:00 | N | N | In service date: August 21, 2015 | Line |  |  | 240 kV
ALTALINK | 1116L (170s Pike - 167s Ipiatik Lake) | 2015-08-19 08:00 | 2015-08-22 16:00 | N | N | In service date: August 21, 2015 | Line |  |  | 240 kV
EPCOR | Strathcona T2 (Strathcona) | 2015-08-19 08:00 | 2015-08-21 18:00 | N | N | doble testing | Transformer
ENMAX | ENMAX 25 B240-D135 (ENMAX 25) | 2015-08-19 08:00 | 2015-08-24 16:00 | N | Y | ALSTOM 240 kV breaker modification, doble | Circuit Breaker |  |  | 240 kV
ALTALINK | 528S Blue Trail Wind Farm | 2015-08-19 08:00 | 2015-08-21 16:00 | N | N | Trip test Feeder 2 at Blue Trail | Station |  |  | Restricts Generation
ENMAX | 20PT138-Z31 (ENMAX 20) | 2015-08-19 08:00 | 2015-08-19 12:00 | N | N | HICO to repair PT secondary circuits | Terminal Equipment
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24),Enmax 24 B138-24.82 (ENMAX 24) | 2015-08-19 08:00 | 2015-08-20 16:00 | N | N | HV breaker inspection, doble, correctives on 24.2TR | Line, Transformer, Circuit Breaker |  |  | Overload
ALTALINK | 167S Ipiatik Lake | 2015-08-19 08:00 | 2015-08-22 16:00 | N | N | In service date: August 21, 2015 | Station
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),ENMAX 14 B138-14.83 (ENMAX 14) | 2015-08-19 08:00 | 2015-08-19 16:00 | N | N | breaker close circuit repair | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 746s T1 (746s Sherwood Park) | 2015-08-19 08:30 | 2015-08-19 17:00 | N | N | Inspection. High gas level | Transformer |  |  | For Information Only
ALTALINK | 320p 3452 (320p Keephills) | 2015-08-19 08:30 | 2015-08-20 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 103s 1252 (103s Goose Lake) | 2015-08-19 08:30 | 2015-08-20 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.3TR (ENMAX 2) | 2015-08-19 12:00 | 2015-08-19 16:00 | N | N | HICO to repair PT secondary circuits | Transformer
ALTALINK | 744L (228s T.M.P.L.Niton - 744L89B) | 2015-08-19 15:00 | 2015-08-19 18:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | PSS | 2015-08-19 19:00 | 2015-08-19 20:00 | N | N | Suncor GT9 - PSS will be disabled for 1 hr. | Terminal Equipment
ALTALINK | 1064L (102s Langdon - 74s Janet) | 2015-08-20 07:00 | 2015-08-20 15:00 | N | Y | L to J: install of corona rings on 240kv lightning arrestors on 1064L bay | Line |  |  | 240 kV, Overload
ALTALINK | 55s T2 (55s Olds) | 2015-08-20 08:00 | 2015-08-20 17:00 | N | N | installation of Hydran and bushing monitor | Transformer |  |  | For Information Only
ALTALINK | 138s Windy Flats R1,138s Windy Flats R2 | 2015-08-20 08:00 | 2015-08-21 16:00 | N | N | In service date: August 21, 2015 | Shunts
ALTALINK | 659S Pegasus Lake | 2015-08-20 10:00 | 2015-08-31 17:00 | N | N | station expansion - add new TX, add regulator to existing TX, change 25 kV Bus configuration. Utilizing mobile substation to supply Fortis load. | Station |  |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc) | 2015-08-20 12:00 | 2015-08-20 15:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 751s 701T (751s Hill) | 2015-08-21 07:00 | 2015-09-18 17:30 | N | N | protection upgrade | Transformer |  | Protection upgrade
ALTALINK | 167S Ipiatik Lake,1116L (170s Pike - 167s Ipiatik Lake),1117L (898s Heart Lake - 167s Ipiatik Lake) | 2015-08-21 08:00 | 2015-08-22 17:00 | N | Y | energize new 167s and 240kV loop between 170s and A898s | Station, Line |  |  | 240 kV
ALTALINK | 911L (59s Peigan - ENMAX 65) | 2015-08-21 08:00 | 2015-08-21 16:00 | N | Y | change from 911L to 1109L (ISD Nov 2015), Modification of Shepard RAS | Line |  |  | 240 kV, For Information Only
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2015-08-21 13:00 | 2015-08-21 14:00 | N | Y | Open and close airbreak 89s1206 to test status into RAS relay at 89s. | Line |  |  | Pre-Condition, 500 kV
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2015-08-21 14:00 | 2015-08-21 15:00 | N | Y | open and close airbreak 89s1212 to test status into RAS relay at 89s | Line |  |  | Pre-Condition, 500 kV
EPCOR | 511s Victoria T1 (511s Victoria),Victoria V721 (Victoria) | 2015-08-22 07:00 | 2015-08-22 18:00 | N | N | doble testing | Transformer, Circuit Breaker
ENMAX, ALTALINK | 37.2TR (ENMAX 37),37.82L (74s Janet - ENMAX 37) | 2015-08-22 08:00 | 2015-08-23 16:00 | N | Y | replace and inspect hardware, install dampers if time permits, switch maintenance | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L749 (716s Lloydminister - 7L749D2) | 2015-08-22 11:00 | 2015-08-22 16:00 | N | N | emergency repair to damaged conductors due to a metal grain bin contacting the line | Line |  | Emergency Repair to Damaged conductors Due to a Metal Grain Bin contacting the line (wind storm?) | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2015-08-23 07:00 | 2015-08-23 18:00 | N | N | doble testing | Line |  |  | For Information Only
ATCO | 856s Kinosis 240kV Bus 900 | 2015-08-23 08:00 | 2015-09-06 17:30 | N | Y | new 240kV construction, 240kV ring bus open between 906A and 902B | Bus |  | New 240KV Construction, 240kV ring bus open between 906A and 902B | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 1090L (723s Christina Lake - 698s Jackfish) | 2015-08-23 08:00 | 2015-09-01 17:00 | N | Y | install new disconnect 723s34 and MOD 723s1090 and update protection | Line |  |  | 240 kV, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D132 (ENMAX 25) | 2015-08-23 08:00 | 2015-08-28 16:00 | N | Y | ALSTOM 240kV breaker modification and doble | Circuit Breaker |  |  | 240 kV
ALTALINK | 763L (28s West Brooks - 763L257A),28s 47 (28s West Brooks) | 2015-08-24 07:00 | 2015-08-27 18:00 | N | N | replace 28s47 breaker CT | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR, ALTALINK | 909L (89s Ellerslie - 665s Dome),665s D2401 (665s Dome) | 2015-08-24 07:00 | 2015-08-28 18:00 | N | Y | breaker maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 27.1TR (ENMAX 27) | 2015-08-24 08:00 | 2015-08-26 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 162s 240-RB132 (162s Beddington) | 2015-08-24 08:00 | 2015-08-24 16:00 | N | Y | HV breaker inspection | Circuit Breaker |  |  | 240 kV
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2015-08-24 08:00 | 2015-09-18 18:00 | N | N | degassing | Line |  |  | Contingency Requires Mitigation
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2015-08-24 08:00 | 2015-08-26 17:00 | N | Y | replace shackle bolts - warranty | Line |  |  | For Information Only, 500 kV
ALTALINK | 723s T1 (723s Christina Lake) | 2015-08-24 08:00 | 2015-08-24 12:00 | N | N | remove existing trips L1 A&B protection 723s152 | Transformer |  |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703BL tap),703L (377s Hardisty - 703BL tap) | 2015-08-24 08:00 | 2015-08-25 17:00 | N | N | put new transformer at 329s HRT Express | Line |  | August 21st, 2015 (08:00  17:00) 703L (213s  377s) will be removed from service to assist Spectra Energy located @ 329s HRT Express while they put their new transformer into service. | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32) | 2015-08-24 08:00 | 2015-09-04 16:00 | N | N | doble test | Transformer |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2015-08-24 08:00 | 2015-08-25 16:00 | N | N | 138kV bus differential upgrade, CT ratio change, CT commissioning, short bus differential CT's, install temporary transformer protection | Transformer |  |  | For Information Only
ALTALINK | 44s T2 (44s Bearspaw Plant) | 2015-08-24 08:00 | 2015-08-28 17:00 | N | N | maintenance on 44s31, 44s T2 | Transformer |  |  | Restricts Generation
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis),766s 902 (766s Nevis) | 2015-08-24 09:00 | 2015-08-28 16:00 | N | Y | 766s 902 maintenance, EATL RAS, and cell antenna work | Line, Circuit Breaker |  | Bkr 902 Maintenance, 9L912 will be out of service EATL RAS to be confirmed when 902 LTO @ 755s. Cell antenna work - remove/replace and new cabling | 240 kV
ATCO, ALTALINK | 9L960 (13s Deerland - 825s Whitefish Lake) | 2015-08-24 09:00 | 2015-08-24 16:00 | N | Y | remove polymeric insulators for analysis | Line |  | GOI to remove Polymeric Insulators for analysis | 240 kV, For Information Only
ALTALINK | 74s 2852 (74s Janet) | 2015-08-24 12:00 | 2015-08-27 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 723s T2 (723s Christina Lake) | 2015-08-24 13:00 | 2015-08-24 17:00 | N | N | remove existing trips L1 A&B protection 723s252 | Transformer |  |  | For Information Only
ALTALINK | 920L (71s Lamoureux - 557s Castle Downs) | 2015-08-24 14:00 | 2015-08-25 10:07 | N | Y | 240kV switch replacement | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2015-08-25 06:00 | 2015-08-25 10:00 | N | N | repair deficiencies on 2MD138-2.81 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2015-08-25 06:00 | 2015-08-25 07:00 | N | N | outage to remove 27.1 LTC door | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 234L (310p Sundance - 234L1),512L (310p Sundance - 521L tap),310p T30 (310p Sundance),310P Sundance 69kV Bus,310P T31 (310P Sundance),310P T33 (310P Sundance) | 2015-08-25 07:00 | 2015-08-25 19:00 | N | Y | 310p696 switch & transformer maintenance | Bus, Transformer, Line |  |  | 240 kV, Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO | 879s 701T (879s Scottford Upgrader) | 2015-08-25 07:00 | 2015-09-18 17:30 | N | N | install FCL (Fault Current Limiter) on 501R bay | Transformer |  | Install FCL (Fault Current Limiter) on 501R bay.
Saskpower | Sask Power SW909 | 2015-08-25 07:00 | 2015-08-25 17:00 | N | Y | system maintenance | Circuit Breaker |  |  | Limits ATC
ALTALINK | 28s R1 (28s West Brooks),28s 44 (28s West Brooks) | 2015-08-25 07:00 | 2015-08-27 19:30 | N | Y | 28s44 POW relay installation | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 223s T2 (223s Strome) | 2015-08-25 08:00 | 2015-09-03 17:00 | N | N | replace 25kV and 138kV bushings on TX18436 | Transformer
ALTALINK | 953s T1 (953s Lake Louise) | 2015-08-25 08:00 | 2015-08-26 16:00 | N | N | RTU replacement project | Transformer
ENMAX | 16.1TR (ENMAX 16) | 2015-08-25 08:00 | 2015-08-25 12:00 | N | N | remove trojan oil processor | Transformer
ENMAX | 6.80L (ENMAX 30 - ENMAX 6),ENMAX 6 B138-6.80 (ENMAX 6) | 2015-08-25 10:00 | 2015-08-25 12:00 | N | N | HV breaker inspection, SF6 gas sample | Line, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 54s C1 (54s Fort Saskatchewan) | 2015-08-25 11:00 | 2015-08-25 17:00 | N | N | repair blown capacitors | Shunts |  |  | Pre-Condition
ENMAX | 16.2TR (ENMAX 16) | 2015-08-25 12:00 | 2015-08-25 16:00 | N | N | set up trojan oil processor | Transformer
ENMAX | 40.1TR (ENMAX 40) | 2015-08-26 08:00 | 2015-08-27 16:00 | N | N | 138kV bus differential upgrade | Transformer |  | 138KVbus Differential Upgrade, CT ratio change, CT commissioning, Short bus differential CT's, Install temporary
ENMAX | ENMAX 25 B240-D134 (ENMAX 25) | 2015-08-26 08:00 | 2015-08-31 16:00 | N | Y | ALSTOM 240kV breaker modification and doble | Circuit Breaker |  |  | 240 kV
ATCO | 7L172 (739s Edith Lake - 743s Sarah Lake),739s 702 (739s Edith Lake) | 2015-08-26 09:00 | 2015-08-26 15:30 | N | N | repair deficiency - commission 702 breaker lockouts- 7L172 open ended | Circuit Breaker, Line |  | Repair deficiency - Commission 702 Bkr lockouts- 7L172 open ended
ENMAX | 36.2TR (ENMAX 36) | 2015-08-26 12:00 | 2015-08-28 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2015-08-27 05:00 | 2015-09-03 17:00 | N | Y | replace shackle bolts - warranty | Line |  |  | Pre-Condition, 500 kV
ATCO | 6L06 (705s Kitscoty - 751s Hill) | 2015-08-27 08:00 | 2015-08-27 17:00 | N | N | change pole due to storm damage | Line |  | Change pole due to storm Damage. 6L06 is on hot standby for 7L14/7L130 Contingency / 6L06 OOS has no impact to electrical system.
ATCO | 720s 902T (720s Wabasca),720s 240kV Bus 2 (720s Wabasca) | 2015-08-28 07:00 | 2015-10-12 17:30 | N | Y | replace 902A, 902B upgrade transformer protection and auto-sectionalizing scheme. | Transformer, Bus |  | Replace 902A, 902B upgrade transformer protection and auto-sectionalizing scheme. J1 will be created between 902B and 9L56 | 240 kV
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2015-08-29 07:00 | 2015-08-29 18:00 | N | N | Doble Testing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 32.83L (ENMAX 32 - ENMAX 40) | 2015-08-29 08:00 | 2015-08-30 16:00 | N | N | 138KV bus differential upgrade | Line |  | 138KV Bus Differential Upgrade, CT ratio change, CT commissioning, Short bus differential CT's, Install temporary | Firm Load Loss, Creates Radial Feeds
ALTALINK | 723s T1 (723s Christina Lake) | 2015-08-29 08:00 | 2015-08-29 12:00 | N | Y | Tie in and test trips from the new 96/1652 to 723s152 | Transformer |  |  | For Information Only
ALTALINK | 723s T2 (723s Christina Lake) | 2015-08-29 13:00 | 2015-08-29 17:00 | N | Y | Tie in and test trips from the new 96/1652 to 723s252 | Transformer |  |  | For Information Only
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2015-08-30 07:00 | 2015-08-30 18:00 | N | N | Doble Testing | Line |  |  | Overload
ENMAX | ENMAX 25 B240-D131 (ENMAX 25) | 2015-08-30 08:00 | 2015-09-04 16:00 | N | Y | ALSTOM 240KV breaker modification.Doble | Circuit Breaker |  |  | 240 kV
ALTALINK | 74s 2552 (74s Janet) | 2015-08-31 07:00 | 2015-09-03 17:00 | N | Y | replace CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 665s D2402 (665s Dome),909L (320p Keephills - 665s Dome) | 2015-08-31 07:00 | 2015-09-05 18:00 | N | Y | breaker maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 39.4TR (ENMAX 39) | 2015-08-31 08:00 | 2015-08-31 16:00 | N | N | transformer temperature alarm replacements | Transformer
ENMAX | 36.1TR (ENMAX 36) | 2015-08-31 08:00 | 2015-08-31 16:00 | N | N | LV cell insulator repairs | Transformer |  |  | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2015-08-31 08:00 | 2015-09-04 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 54s C1 (54s Fort Saskatchewan),54s 45 (54s Fort Saskatchewan) | 2015-08-31 08:00 | 2015-09-03 17:00 | N | N | install new DC cable | Circuit Breaker, Shunts |  |  | Pre-Condition
EPCOR | Rossdale R721 (Rossdale) | 2015-08-31 08:00 | 2015-09-04 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 752L (64s East Crossfield - 752L67) | 2015-08-31 08:00 | 2015-09-04 17:30 | N | Y | Line maintenance | Line |  | AltaLink has provided overload rating on 688L for this outage period. See 752L risk assessment sent on Aug 20, 2015 | Pre-Condition, Firm Load Loss, Creates Radial Feeds, Impacts RAS
ENMAX | 38.1TR (ENMAX 38) | 2015-08-31 08:00 | 2015-09-04 16:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2015-08-31 08:00 | 2015-09-01 16:00 | N | N | CT and protection upgrades | Line |  |  | Creates Radial Feeds
ATCO | 848s 703T (848s Ruth Lake) | 2015-08-31 08:00 | 2015-09-03 14:00 | N | N | 703T transformer maintenance | Transformer |  | 703T transformer maintenance in coordination with the work on 7L47. Refer to study for 7L47. Breaker 506 will need to be energized or 500d4 closed and 605t to supply 25kv load Alternate station service will be utilized | For Information Only
ATCO | 7L47 (848s Ruth Lake - 718s Parsons Creek) | 2015-08-31 08:00 | 2015-09-03 14:30 | N | N | 7L47 climbing inspection on 7L47 Ruth Lake to Parson Creek | Line |  | 7L47 climbing inspection on 7L47 Ruth Lake to Parson Creek | Pre-Condition
ALTALINK | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2015-08-31 09:00 | 2015-09-04 17:00 | N | Y | line maintenance - replace structure | Line |  |  | 240 kV
ALTALINK | 310p 252 (310p Sundance) | 2015-08-31 11:00 | 2015-08-31 17:00 | N | Y | replace auxiliary voltage transformer | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 69s T5 (69s North Barrhead) | 2015-08-31 11:00 | 2015-09-01 09:00 | N | N | install temporary U/G cables | Transformer |  |  | For Information Only
ALTALINK | 262S Rocky Mountain House,262s T2 (262s Rocky Mountain House) | 2015-08-31 12:00 | 2015-09-03 12:00 | N | N | 25 kv meter upgrade project | Transformer, Station |  |  | For Information Only
ALTALINK | 288s T1 (288s Wolf Creek),288s T2 (288s Wolf Creek),288s Wolf Creek 138kV Bus 1,883L (288s Wolf Creek - 429s Nelson Lake) | 2015-09-01 07:00 | 2015-09-03 09:00 | N | N | install fibre optic cable (OPGW) over 883L and 288s 138kV Bus 1 | Transformer, Bus, Line |  |  | 240 kV, For Information Only
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2015-09-01 08:00 | 2015-09-01 17:00 | N | N | install bird coverup / replace one bus connector | Transformer
ALTALINK | 99s T2 (99s North St. Albert) | 2015-09-01 08:00 | 2015-09-02 17:30 | N | N | upgrade protection settings on T2 | Transformer
ALTALINK | 953s T2 (953s Lake Louise) | 2015-09-01 08:00 | 2015-09-02 16:00 | N | N | RTU replacement project | Transformer |  |  | For Information Only
ALTALINK | 370s 1252 (370s North Lethbridge) | 2015-09-01 08:00 | 2015-09-02 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2015-09-01 09:00 | 2015-09-01 17:00 | N | N | move str 691 for road construction widening 7L68 line | Line |  | move str 691 for road construction widening 7L68 line | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 240BA2 (814s Bellamy - 629s Argyll Transfer Station),814s B2401 (814s Bellamy),814s B2402 (814s Bellamy) | 2015-09-01 09:00 | 2015-09-03 17:00 | N | Y | doble test line | Line, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 551L (945s Sunshine Village - 123s Banff),123s551W (123s Banff) | 2015-09-01 09:00 | 2015-09-01 17:00 | N | N | 69kV breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ATCO | 809s 911 (809s Louise Creek) | 2015-09-01 09:30 | 2015-09-03 15:30 | N | Y | perform major maintenance | Circuit Breaker |  | Perform Major Maintenance on 911 Breaker. 240KV Ring opened at 809S | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 69s T2 (69s North Barrhead) | 2015-09-01 10:00 | 2015-09-03 09:00 | N | N | repair bypass U/G terminations & install extension plates at 69s51 | Transformer |  |  | For Information Only
ALTALINK | 678s T1 (678s Okotoks),727L (678s Okotoks - 1140s Temp),678s Okotoks 138kV Bus 1 | 2015-09-02 05:00 | 2015-09-02 07:00 | N | N | Foothills 138kV: Create open point "I" in 138kV Bus #2, between 138kV high bus support structure & 678s1 | Line, Transformer, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 678s T1 (678s Okotoks),727L (678s Okotoks - 727L39N),678s Okotoks 138kV Bus 1 | 2015-09-02 07:00 | 2015-09-12 05:00 | N | N | Foothills 138kV: replace 678s1 & 678s30 | Line, Transformer, Bus |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D140 (ENMAX 25) | 2015-09-02 08:00 | 2015-09-07 16:00 | N | Y | ALSTOM 240KV Breaker Modification. Doble | Circuit Breaker |  |  | 240 kV
ATCO | 9L85 (856s Kinosis - 977s Salt Creek) | 2015-09-02 08:00 | 2015-09-07 12:00 | N | Y | ATCO bus configuration and protection changes | Line |  |  | 240 kV, Restricts Generation, Creates Radial Feeds
ENMAX | 41.1C (ENMAX 41),41.2TR (ENMAX 41),33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41),ENMAX 6 B138-6.82 (ENMAX 6) | 2015-09-02 08:00 | 2015-09-11 16:00 | N | N | switch replacement at Enmax 41, breaker 6B138-6.82 inspection | Line, Shunts, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 10.2TR (ENMAX 10) | 2015-09-02 08:00 | 2015-09-04 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 856s 901T (856s Kinosis),856s 902T (856s Kinosis) | 2015-09-02 08:00 | 2015-10-06 16:00 | N | Y | bus configuration and protection changes | Transformer |  | Isolate 901T and 902T for bus configuration and protection changes, 25kV load will be supplied by 835s Mobile sub, 144kV load will be supplied by 903T, 856s will be radial fed from 9L45, 240kV ring bus will OOS except for 9L45 corner, On Sep 6 the 240kV GOI points will be condensed to allow 9L85 to be placed back in service. After Sept 6th 901T will be available but remain OOS due to tap changer differences with 903T. | 240 kV, For Information Only
ATCO | 7L128 (963s Coyote Lake - 802s Michichi Creek),802s 704 (802s Michichi Creek) | 2015-09-02 08:00 | 2015-09-02 16:00 | N | N | 7L128 open ended / Breaker 704 Partial PM | Line, Circuit Breaker |  | 7L128 open ended / Breaker 704 Partial PM | For Information Only
ATCO | 7L794 (157s Lac La Biche - 819s Whitby Lake),819s 702 (819s Whitby Lake) | 2015-09-02 09:00 | 2015-09-03 16:00 | N | Y | breaker maintenance / breaker 702 | Circuit Breaker, Line |  | Breaker maintenance / breaker 702 out of service for the duration of the work / 7L794 open ended for the duration of the work | For Information Only
ALTALINK, ATCO | 794L (157s Lac La Biche - 819s Whitby Lake),7L794 (157s Lac La Biche - 819s Whitby Lake) | 2015-09-02 09:00 | 2015-09-03 16:00 | N | Y | breaker maintenance | Line |  |  | Overload, Over/Under Voltage
VISIONREQ | 354s Summerview RTU/SCADA | 2015-09-02 09:00 | 2015-09-02 17:00 | N | N | upgrading SCADA system | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2015-09-03 08:00 | 2015-09-03 17:00 | N | N | Line maintenance  urgent repair | Line |  |  | For Information Only
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198) | 2015-09-03 09:00 | 2015-09-03 12:00 | N | N | Replace crossarm  urgent repair | Line |  |  | Restricts Generation, Firm Load Loss
ALTALINK | 69s T5 (69s North Barrhead) | 2015-09-03 09:00 | 2015-09-03 17:00 | N | N | remove temp cables | Transformer |  |  | For Information Only
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2015-09-04 08:00 | 2015-09-09 17:00 | N | Y | Replace shackle bolts - warranty | Line |  |  | For Information Only, 500 kV
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2015-09-05 08:00 | 2015-09-05 16:00 | N | N | SF6 Gas Sample 39B138-39.82 | Line |  |  | Overload, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D139 (ENMAX 25) | 2015-09-06 08:00 | 2015-09-11 16:00 | N | Y | ALSTOM 240KV Breaker Modification. Doble | Circuit Breaker |  |  | 240 kV
ATCO | 856s 901T (856s Kinosis),856s 902T (856s Kinosis) | 2015-09-06 08:00 | 2015-09-30 16:00 | N | Y | 902T will already be OOS under permit 2-33212, no added risk to the system Connect 902T to new 240kV bus, protection changes, change 700PT1 902T will be placed back in service Sep 25 on RTN switching. | Transformer |  | 902T will already be OOS under permit 2-33212, no added risk to the system Connect 902T to new 240kV bus, protection changes, change 700PT1 902T will be placed back in service Sep 25 on RTN switching. | 240 kV
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2015-09-06 08:00 | 2015-09-06 12:00 | N | Y | SF6 Gas Sample on 7B138-7.82 | Line |  |  | Creates Radial Feeds
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2015-09-06 12:00 | 2015-09-06 16:00 | N | N | SF6 gas sample on 7B138-7.84 | Line |  |  | Pre-Condition, Creates Radial Feeds
ATCO | 856s 708 (856s Kinosis),856s 708C (856s Kinosis) | 2015-09-07 08:00 | 2015-09-07 16:00 | N | N | deficiency work | Circuit Breaker, Shunts |  | Deficiency work | For Information Only
ALTALINK | 957L (72s Leismer - 723s Christina Lake) | 2015-09-07 12:00 | 2015-10-02 17:00 | N | Y | install disconnect & end to end testing | Line |  | 723s957, breakers 723s1652, 723s1752 & CVT 723s33. Replace L1 A Prot at 72s and 723s. 957L end to end testing. Remove motor mechs from 957s15 & s16 | 240 kV, Firm Load Loss, Creates Radial Feeds
SUNCOR | 226S Garden City | 2015-09-08 06:00 | 2015-09-09 18:00 | N | N | annual outage | Station |  |  | Restricts Generation
ALTALINK | 929L (63s Red Deer - 74s Janet) | 2015-09-08 07:00 | 2015-09-10 17:00 | N | Y | replace 74s929N | Line |  |  | 240 kV
EPCOR | 330p 1205 (330p Genesee) | 2015-09-08 07:00 | 2015-10-05 18:00 | N | Y | breaker replacement | Circuit Breaker |  |  | 500 kV
ALTALINK, EPCOR | 665s D2403 (665s Dome),909L (320p Keephills - 665s Dome) | 2015-09-08 07:00 | 2015-09-13 18:00 | N | Y | breaker maintenance | Line, Circuit Breaker |  |  | 240 kV, Overload
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin) | 2015-09-08 07:30 | 2015-09-08 12:00 | N | N | create open point between 804L and 810L1 to facilitate 810L1 replacement. | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 396s T1 (396s Pincher Creek),514L (396s Pincher Creek - 514BL tap) | 2015-09-08 08:00 | 2015-09-08 17:00 | N | N | 185L strain insulators replacements | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2015-09-08 08:00 | 2015-09-11 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D133 (ENMAX 25),ENMAX 25 B240-D139 (ENMAX 25),ENMAX 25 B240-D142 (ENMAX 25),ENMAX 25 240kV North Bus | 2015-09-08 08:00 | 2015-09-08 16:00 | N | Y | Adjustments required on SW 142. Switch not opening past 90 degrees | Bus, Circuit Breaker |  |  | 240 kV
ENMAX | ENMAX 2 B138-D86 (ENMAX 2),ENMAX 2 B138-D95 (ENMAX 2),ENMAX 2 B138-D84 (ENMAX 2),ENMAX 2 B138-D88 (ENMAX 2),ENMAX 2 B138-D83 (ENMAX 2),ENMAX 2 B138-D87 (ENMAX 2),ENMAX 2 B138-D91 (ENMAX 2) | 2015-09-08 08:00 | 2015-09-18 16:00 | N | N | only 1 breaker out at a time to reduce gas pressure | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Prevents Normal Events, Creates Radial Feeds
AESO | 9L32 (849s Joslyn Creek - 957s McClelland) | 2015-09-08 08:00 | 2015-09-17 16:00 | N | Y | reroute 9L32 in/out of 2005s Secord | Line |  | Reroute 9L32 In/Out of 2005s Secord. On RTN 9L32 will exist between 849s and 2005s, and 9L101 will exist between 957s and 2005s. 2005s will be energized on RTN switching. T/P End To End testing 9L32 and 9L101 Telecom Fiber Splicing | 240 kV, Restricts Generation
ENMAX | 27.2TR (ENMAX 27) | 2015-09-08 08:00 | 2015-09-11 16:00 | N | N | Doble | Transformer |  |  | For Information Only
ALTALINK | 99s T1 (99s North St. Albert) | 2015-09-08 08:00 | 2015-09-10 17:30 | N | N | install new 99s2024 breaker and update settings on T1 | Transformer |  |  | For Information Only
ALTALINK | 417L (55s Olds - 281s Johnson),418L (20s Ghost - 281s Johnson),281s T1 (281s Johnson),166L (281s Johnson - 166L50) | 2015-09-08 08:00 | 2015-09-10 17:00 | N | N | repair bushing leaks on transformer | Transformer, Line |  |  | Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L06 (A793s West Peace River - 784s Donnelly) | 2015-09-08 08:00 | 2015-09-14 16:00 | N | N | replace structures, crossarm replacements, pole changes | Line |  | Replace structures, crossarm replacements, pole changes | Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2015-09-08 08:00 | 2015-09-15 17:00 | N | N | structure replacement and insulator changes | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 276s T3 (276s Union Carbide Prentiss) | 2015-09-08 08:30 | 2015-09-10 17:00 | N | N | doble/float calibration | Transformer |  |  | For Information Only
ATCO | 732s 503R (732s Mitsue),732s 902T (732s Mitsue) | 2015-09-08 08:30 | 2015-09-09 16:30 | N | Y | 902T setting changes | Transformer, Shunts |  | 902T 87A CT Settings Change at 732S...Master GOI to change 902T primary CT ratio and test Transfer all load to 901T 502R will not be available for the duration | 240 kV, Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 42s 31 (42s Sarcee) | 2015-09-08 10:00 | 2015-09-08 17:00 | N | N | investigate breaker trouble alarms | Circuit Breaker |  |  | For Information Only
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2015-09-08 12:30 | 2015-09-08 17:30 | N | N | create open point between 805L and 810L1 to facilitate 810L1 replacement. | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 87s T1 (87s Gaetz),87s 552 (87s Gaetz),87s 152 (87s Gaetz),87s 952 (87s Gaetz),87s Gaetz 138kV West Bus | 2015-09-09 07:00 | 2015-09-13 17:00 | N | Y | 87s10 PT & T1 bushing replacements | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 606L (184s Petro-Canada Edmonton - 185s Bretville) | 2015-09-09 07:00 | 2015-09-09 19:00 | N | N | Replace Strain Insulators | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s 4 (33s Spray) | 2015-09-09 08:00 | 2015-09-09 17:00 | N | Y | maintenance | Switch |  |  | For Information Only
ENMAX | ENMAX 25 B240-D141 (ENMAX 25) | 2015-09-09 08:00 | 2015-09-14 16:00 | N | Y | ALSTOM 240KV breaker modification, doble | Circuit Breaker |  |  | 240 kV, Pre-Condition
SUNCOR | 609S Wheatland | 2015-09-09 08:00 | 2015-09-09 18:00 | N | N | sub maintenance | Station |  |  | Restricts Generation
ALTALINK | 1239L (510s Sunnybrook - 330p Genesee),510s 3652 (510s Sunnybrook),510s 3752 (510s Sunnybrook) | 2015-09-09 08:00 | 2015-09-10 17:00 | N | Y | Corona deficiencies and DC cabling | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ATCO | 940s 701T (940s Beartrap) | 2015-09-09 08:00 | 2015-09-10 16:00 | N | N | 701T NGR weather cover and 301 bushing replacement | Transformer |  | 940S 701T NGR weather cover and 301 bushing replacement 701T and 301 at 940S will be out of service for the duration of the work Enbridge will be having a scheduled 12 hr outage daily on July 9 and10th, 2015. Customer load on 3L226 will be picked up on 702T by customer closing in 410-BUS-1/2 -TIS. Shawn Wentz will confirm with Dave Sokorinski 940S 701T NGR Weather guard installation 940S 301 bushing replacement 940S 301A hotspot investigate | For Information Only
ALTALINK | 613L (396s Pincher Creek - 103s Goose Lake) | 2015-09-09 08:00 | 2015-09-09 17:00 | N | N | urgent repair | Line
ATCO | 709s 603T (709s Vegreville),709s 604T (709s Vegreville) | 2015-09-09 08:00 | 2015-09-09 15:00 | N | N | sampling bushings for PCB | Transformer |  | 709S - 603T and 604T Sampling Bushings for PCB | For Information Only
ATCO | 778s 601T (778s Big Valley) | 2015-09-09 09:00 | 2015-09-09 16:00 | N | N | maintenance & bushing PCB samples | Transformer |  | 778S - TRANSFORMER CLASS2 MAJOR TESTING 601T Maintenance & Bushing PCB Samples | For Information Only
BCH | 5L92 (Cranbrook - Selkirk) | 2015-09-09 09:00 | 2015-09-10 17:00 | Y | Y | replace Insulators and spacers | Line
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2015-09-09 12:00 | 2015-09-09 15:00 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 810L1 (86s Bigstone) | 2015-09-09 17:30 | 2015-09-16 08:00 | N | N | 810L1 replacement | Switch |  |  | For Information Only
Syncrude | Mildred T1 (Syncrude Mildred Lake),Mildred T2 (Syncrude Mildred Lake),Mildred T3 (Syncrude Mildred Lake) | 2015-09-10 06:00 | 2015-09-18 11:00 | N | N | transformer preventative maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2015-09-10 07:00 | 2015-09-10 19:00 | N | N | Replace Strain Insulators | Line |  |  | Creates Radial Feeds
ATCO | 7L85 (803s Bullpound - 801s Anderson),801s 705 (801s Anderson) | 2015-09-10 07:30 | 2015-09-11 16:00 | N | N | 801S 705 breaker testing | Line, Circuit Breaker |  | 801S Anderson - BREAKER SF6 LTB145D1/B PARTIAL TESTING Complete Breaker 705 Partial Maintenance. 7L85 Open Ended | Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2015-09-10 08:00 | 2015-09-10 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 20.1TR (ENMAX 20) | 2015-09-10 08:00 | 2015-09-10 16:00 | N | N | test oil temperature probe | Transformer |  |  | For Information Only
ALTALINK | 301S Queensland,301s T1 (301s Queensland) | 2015-09-10 08:00 | 2015-09-10 17:00 | N | N | station outage for grounding cable repair | Transformer, Station |  |  | For Information Only
FORTIS | 140S Thompson | 2015-09-10 08:30 | 2015-09-10 15:30 | N | N | customer working on their neutral ground resistor located within 140s | Station |  |  | For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2015-09-10 13:00 | 2015-09-10 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | Kennedale T2 (Kennedale) | 2015-09-11 07:00 | 2015-10-15 18:00 | N | N | tap changer maintenance. | Transformer |  |  | For Information Only
SUNCOR | 29PT-237 (29EDD-71) | 2015-09-11 08:00 | 2015-09-12 20:00 | N | Y | repair oil leak on transformer | Terminal Equipment |  |  | Restricts Generation
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2015-09-11 09:00 | 2015-09-11 17:00 | Y | N | replace damaged insulators | Line |  |  | Limits ATC
ALTALINK | 678s T2 (678s Okotoks),727L (678s Okotoks - 1140s Temp),678s Okotoks 138kV Bus 2 | 2015-09-12 05:00 | 2015-09-12 07:00 | N | N | Foothills 138kV: close open point "I" | Line, Transformer, Bus |  |  | Over/Under Voltage, Creates Radial Feeds
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2015-09-12 08:00 | 2015-09-14 08:00 | N | Y | transmission relocation | Line |  | 68th and 17th ave se. Transmission relocation. 37.81L Excavate holes and Install bottom sections of 2 new steel D.D.E. structures. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 821S Sundance,512L (310p Sundance - 521L tap),512L (821s Sundance - 521L tap) | 2015-09-12 08:00 | 2015-09-12 17:00 | N | N | replacement of 69kV station components | Line, Station |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2015-09-12 08:00 | 2015-09-12 16:00 | N | N | concrete sidewalk removal | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 5L96 (Selkirk - Vaseux Lake) | 2015-09-12 09:00 | 2015-09-12 17:00 | N | N | replace damaged insulators | Line |  |  | Limits ATC
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2015-09-13 08:00 | 2015-09-13 16:00 | N | N | Doble test 38PT138-Z5 and take photos of 138kV PT nameplates | Line, Shunts, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D138 (ENMAX 25) | 2015-09-13 08:00 | 2015-09-18 16:00 | N | Y | 240 kV breaker modification and doble | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis),9L20 (766s Nevis - 755s Cordel) | 2015-09-14 07:00 | 2015-09-14 07:15 | N | Y | required to open disconnect 766s 901TD | Line |  |  | 240 kV, Overload
ATCO | 7L183 (856s Kinosis - 2060s Engstrom) | 2015-09-14 07:00 | 2015-09-18 16:00 | N | N | remove 144kV risers between 7L183 and 7L183D5 | Line |  | crew to remove 144kv risers between 7L183 to 7L183D5 | Firm Load Loss, Creates Radial Feeds
ATCO | 7L14 (710s Vermilion - 751s Hill),751s 701 (751s Hill) | 2015-09-14 07:00 | 2015-09-28 17:30 | N | N | 7L14 protection upgrade | Circuit Breaker, Line |  | 7L14 Protection Upgrade | Firm Load Loss, Creates Radial Feeds
EPCOR | 816s P2403 (816s Petrolia) | 2015-09-14 07:00 | 2015-09-18 18:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2015-09-14 08:00 | 2015-09-25 16:00 | N | N | line differential | Line |  |  | For Information Only
ALTALINK, ENMAX | 12.2TR (ENMAX 12),833L (ENMAX 2 - ENMAX 12),ENMAX 12 B138-833L (ENMAX 12) | 2015-09-14 08:00 | 2015-09-25 16:00 | N | Y | SW's 81, 82 & 83 and 12.2TR MD replacement at ENMAX 12 | Line, Circuit Breaker, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1-T1 (29EDD-1 Millennium),29EDD-1 Millennium 260kV South Bus 2 | 2015-09-14 08:00 | 2015-10-04 20:00 | N | Y | maintenance | Transformer, Bus |  |  | Creates Radial Feeds, For Information Only
ENMAX | ENMAX 65 240kV North Bus | 2015-09-14 08:00 | 2015-09-19 17:00 | N | Y | replace 911L termination for final 1109L alignment and complete OPGW stringing | Bus |  |  | 240 kV
ALTALINK, REDDEER | 217s T2 (217s North Red Deer),778L (217s North Red Deer - 87s Gaetz),80L (198s Blackfalds - 217s North Red Deer) | 2015-09-14 08:00 | 2015-09-25 15:30 | N | N | to facilitate City of Red Deer replacement of 14-81-2 | Line, Transformer |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | ENMAX 36 B138-36.81 (ENMAX 36),36.81L (44s Bearspaw - ENMAX 36) | 2015-09-14 08:00 | 2015-09-25 16:00 | N | Y | line differential, SF6 gas sample on 36B138-36.81 | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-09-14 08:00 | 2015-09-16 16:00 | N | N | replace damaged lattice tower st 28 & 31 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s 752 (63s Red Deer) | 2015-09-14 08:00 | 2015-09-29 16:30 | N | Y | 240kV breaker & CT replacement | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.1TR (ENMAX 13) | 2015-09-14 08:00 | 2015-09-28 16:00 | N | N | transformer spill containment | Transformer
ENMAX | 2.3TR (ENMAX 2) | 2015-09-14 08:00 | 2015-09-16 16:00 | N | N | fall arrest plate installation | Transformer |  |  | For Information Only
ENMAX | 34.4TR (ENMAX 34) | 2015-09-14 08:00 | 2015-09-20 16:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2015-09-14 08:00 | 2015-09-15 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 172L (254s Coaldale - 172L944C),254s 172E (254s Coaldale) | 2015-09-14 11:00 | 2015-09-14 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Overload
ALTALINK | 89s 1352 (89s Ellerslie) | 2015-09-14 11:00 | 2015-09-14 17:00 | N | Y | correct the pole disagreement circuit | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 447s T1 (447s Enchant) | 2015-09-14 11:00 | 2015-09-14 17:00 | N | N | 138kV/25kV transformer maintenance & doble | Transformer
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis),9L20 (766s Nevis - 755s Cordel) | 2015-09-14 14:30 | 2015-09-16 14:45 | N | Y | required to close disconnect 766s 901TD | Line |  |  | 240 kV, Overload
ENMAX | 38.1C (ENMAX 38) | 2015-09-15 08:00 | 2015-09-15 16:00 | N | N | maintenance | Shunts |  |  | For Information Only
ATCO | 700s 705C (700s Bonnyville),700s 705 (700s Bonnyville) | 2015-09-15 08:00 | 2015-09-15 16:00 | N | N | breaker maintenance | Shunts, Circuit Breaker |  | Breaker Maintenance - 705C OOS for Duration | For Information Only
ALTALINK | 396s T2 (396s Pincher Creek),185L (396s Pincher Creek - 379s Shell Canada Waterton),514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198),396s61 (396s Pincher Creek) | 2015-09-15 08:00 | 2015-09-15 16:00 | N | N | switch repair | Switch, Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader) | 2015-09-15 08:00 | 2015-09-21 17:00 | N | Y | ATCO outage | Line
ATCO | 732s 501R (732s Mitsue),732s 901T (732s Mitsue) | 2015-09-15 08:30 | 2015-09-16 16:30 | N | Y | change primary CT ratio | Shunts, Transformer |  | 901T 87A CT Settings Change at 732S...Master GOI to change 901T primary CT ratio and test Transfer station service, load on to 902T 501R will not be available for the duration | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 9L43 (888s Dover - 874s McKay River) | 2015-09-15 09:00 | 2015-09-24 17:00 | N | Y | maintenance activities | Line |  | TransCanada request (GFO). It does not follow >30 days notice. Performing preventative and corrective maintenance activities | 240 kV, Restricts Generation
ALTALINK | 777L (245s Seebe - 48s Pocaterra),887L (48s Pocaterra - BCH Britt Creek) | 2015-09-15 13:00 | 2015-09-17 17:00 | N | Y | replace 48s26 PT & 138kV strain insulators | Line |  |  | Over/Under Voltage
ATCO | 751s 701TD (751s Hill) | 2015-09-16 07:00 | 2015-09-16 17:30 | N | N | test new control wiring | Switch |  | Test new control wiring.
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs),37s 83 (37s North Calder),37s 87 (37s North Calder) | 2015-09-16 08:00 | 2015-09-16 17:00 | N | Y | switch maintenance | Line, Switch |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 709s 603T (709s Vegreville),709s 604T (709s Vegreville) | 2015-09-16 08:00 | 2015-09-16 15:00 | N | N | sampling bushings for PCB | Transformer |  | 709S - 603T and 604T Sampling Bushings for PCB
ALTALINK | 33s5 (33s Spray) | 2015-09-16 08:00 | 2015-09-16 17:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 33s 4 (33s Spray) | 2015-09-16 08:00 | 2015-09-16 17:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ATCO | 700s 707C (700s Bonnyville),700s 707 (700s Bonnyville) | 2015-09-16 08:00 | 2015-09-16 16:00 | N | N | breaker maintenance | Shunts, Circuit Breaker |  | Breaker Maintenance - 707C OOS for Duration
ENMAX | 36.2TR (ENMAX 36) | 2015-09-16 08:00 | 2015-09-17 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 43S Shell Canada Jumpingpound Jct,3L (42s Sarcee - 272s Springbank) | 2015-09-16 08:00 | 2015-09-19 17:00 | N | N | replace transformer | Station, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz),86s 1752 (86s Bigstone) | 2015-09-16 09:00 | 2015-09-16 14:00 | N | Y | breaker oil refill | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 414s T1 (414s Gulf Robb) | 2015-09-16 10:00 | 2015-09-17 17:00 | N | N | transformer & regulator maintenance | Transformer
ALTALINK | 35s T1 (35s Rundle) | 2015-09-16 10:00 | 2015-09-16 16:00 | N | N | connect CT cores in TX to AML revenue meter | Transformer
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-09-17 08:00 | 2015-09-19 16:00 | N | N | replace damaged lattice tower st 28 & 31 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 13.3TR (ENMAX 13) | 2015-09-17 08:00 | 2015-09-24 08:00 | N | N | transformer spill containment | Transformer
ALTALINK | 703L (213s Hughenden - 703BL tap),703L (377s Hardisty - 703BL tap) | 2015-09-17 08:00 | 2015-09-17 17:00 | N | N | put new transformer at 329s HRT Express | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2015-09-17 08:30 | 2015-09-17 13:00 | N | N | repair 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2015-09-17 13:00 | 2015-09-17 17:00 | N | N | repair 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2015-09-17 17:01 | 2015-09-18 18:00 | N | Y | line maintenance | Line |  |  | Over/Under Voltage
EPCOR | 987s CC13 (987s Clover Bar) | 2015-09-18 07:00 | 2015-09-18 18:00 | N | N | breaker Fail | Circuit Breaker |  |  | For Information Only
EPCOR | Meadowlark M722 (Meadowlark) | 2015-09-19 07:00 | 2015-09-19 18:00 | N | N | doble testing | Circuit Breaker |  |  | For Information Only
EPCOR | 987s CCP7213 (987s Clover Bar) | 2015-09-19 07:00 | 2015-09-19 18:00 | N | N | breaker fail | Circuit Breaker |  |  | For Information Only
ALTALINK | 457L (651s Kirby - 167s Ipiatik Lake) | 2015-09-19 08:00 | 2015-09-25 16:00 | N | N | In service date: Sept 24, 2015 | Line
ENMAX | 13.3TR (ENMAX 13) | 2015-09-19 08:00 | 2015-09-20 16:00 | N | N | transformer spill containment | Transformer |  |  | For Information Only
ATCO | 9L32 (941s Bitumount - 2005s Secord) | 2015-09-19 08:00 | 2015-09-22 16:00 | N | N | In service date: Sept 21, 2015 | Line
ATCO | 9L101 (2005s Secord - 957s McClelland) | 2015-09-19 08:00 | 2015-09-22 16:00 | N | N | In service date: Sept 21, 2015 | Line
ALTALINK | 38s T4 (38s East Edmonton) | 2015-09-19 08:00 | 2015-09-20 17:00 | N | Y | replace 138kV bushings | Transformer |  |  | 240 kV, Overload
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2015-09-19 08:00 | 2015-09-21 08:00 | N | N | 68th and 17th Ave SE transmission relocation. install 2 new steel D.D.E. structures and 2 new wood and salvage 5 existing wood | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 237s T1 (237s Foothills),237s T2 (237s Foothills) | 2015-09-19 08:00 | 2015-09-22 16:00 | N | N | In service date: Sept 21, 2015 | Transformer
EPCOR | Meadowlark T1 (Meadowlark) | 2015-09-20 07:00 | 2015-09-20 18:00 | N | N | tapchanger maintenance | Transformer |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),31.84L (ENMAX 31 - ENMAX 32) | 2015-09-20 08:00 | 2015-09-20 16:00 | N | N | 138kV PT outage required for 24.81L protection upgrade | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D142 (ENMAX 25) | 2015-09-20 08:00 | 2015-09-25 16:00 | N | Y | breaker modification and Doble | Circuit Breaker |  |  | 240 kV
EPCOR | Meadowlark M724 (Meadowlark) | 2015-09-21 07:00 | 2015-09-25 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 55s T2 (55s Olds) | 2015-09-21 07:00 | 2015-09-25 17:00 | N | N | replace 138kV LAs on T2 | Transformer |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale),987s CK725 (987s Clover Bar) | 2015-09-21 07:00 | 2015-09-22 18:00 | N | N | breaker fail | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s 2052 (74s Janet) | 2015-09-21 07:00 | 2015-09-24 17:00 | N | Y | IP work: replace CTs | Circuit Breaker |  |  | 240 kV
ALTALINK | 74s T1 (74s Janet),74s Janet 240kV Bus 1 | 2015-09-21 07:00 | 2015-09-24 17:00 | N | Y | replace 240kv insulators and CT ratio changes on 3752, 2752, 2552, 2052, 552 and T1. | Bus, Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2015-09-21 08:00 | 2015-09-21 09:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds
ALTALINK | 310p 2852 (310p Sundance),310P T36 (310p Sundance),310p T30 (310p Sundance) | 2015-09-21 08:00 | 2015-09-23 08:00 | N | Y | circuit breaker replacement | Circuit Breaker, Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.1TR (ENMAX 38) | 2015-09-21 08:00 | 2015-09-25 16:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ATCO | 848s 606 (848s Ruth Lake) | 2015-09-21 08:00 | 2015-09-22 17:00 | N | N | 606 circuit breaker partial maintenance | Circuit Breaker |  | 606 BKR Partial Maintenance | For Information Only
ALTALINK | 681s 252 (681s Bannerman),681s 1152 (681s Bannerman) | 2015-09-21 08:00 | 2015-09-25 16:00 | N | N | trip tests from customer protections | Circuit Breaker |  | Trip tests from customer protections, expanding existing transformer isolation to allow operation of 681s289 & 681s252/681s1152 | 240 kV
ENMAX | 23.4TR (ENMAX 23) | 2015-09-21 08:00 | 2015-09-22 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2015-09-21 09:00 | 2015-09-21 10:00 | N | N | fall pothead washing | Line |  |  | For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-09-21 09:00 | 2015-09-25 17:00 | N | Y | line rebuild and 138kV CT & strain insulator replacements | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap),775s 602 (775s Sullivan Lake) | 2015-09-21 09:00 | 2015-09-22 16:00 | N | N | 705s 602 circuit breaker maintenance | Line, Circuit Breaker |  | Bkr 602 Maintenance, No System concerns N.O. 6L12D3 will be closed and 773S Coronation will be fed from 774S Monitor. | Creates Radial Feeds
ALTALINK | 285s T1 (285s East Camrose) | 2015-09-21 10:00 | 2015-10-01 17:00 | N | N | doble maintenance, bushing replacement, oil reclaim/Leak repair, LA replacement | Transformer
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2015-09-21 10:00 | 2015-09-21 12:00 | N | N | fall pothead washing | Line |  |  | Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2015-09-21 12:00 | 2015-09-21 14:00 | N | N | fall pothead washing | Line |  |  | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 43 (159s Colinton) | 2015-09-21 13:00 | 2015-09-21 17:00 | N | N | replacing damaged silicone around tank heaters | Line, Circuit Breaker |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 205s13 (205s Castle Rock Ridge) | 2015-09-22 07:00 | 2015-09-22 15:30 | N | Y | annual maintenance | Switch |  |  | Restricts Generation
ALTALINK | 102s SVC (102s Langdon) | 2015-09-22 08:00 | 2015-09-22 17:00 | N | Y | SVC annual maintenance | Shunts |  |  | Over/Under Voltage, Limits ATC
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2015-09-22 08:00 | 2015-09-23 17:00 | N | N | Insulator washing - helicopter | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 205s T1 (205s Castle Rock Ridge) | 2015-09-22 08:00 | 2015-09-22 15:30 | N | Y | maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 739L (14s Devon - 305s Acheson),14s 739N (14s Devon) | 2015-09-22 08:30 | 2015-09-22 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage
ALTALINK | 37s 81 (37s North Calder) | 2015-09-22 08:30 | 2015-09-22 17:00 | N | Y | 240kV Breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
BLACKSPRING | 485s C1 (485s Blackspring),485s DVAR1 (485s Blacksprings) | 2015-09-22 09:00 | 2015-09-22 17:00 | N | N | maintenance | Shunts
ALTALINK | 723L (69s North Barrhead - 723L133) | 2015-09-22 09:00 | 2015-10-01 09:30 | N | N | line maintenance | Line |  |  | Overload, Creates Radial Feeds
ALTALINK | 159s T1 (159s Colinton) | 2015-09-22 09:00 | 2015-09-23 17:00 | N | N | 138kV bushing replacement | Transformer
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s CK726 (987s Clover Bar) | 2015-09-23 07:00 | 2015-09-24 18:00 | N | N | meter cutover | Circuit Breaker, Line
ALTALINK | 310p 2852 (310p Sundance) | 2015-09-23 08:00 | 2015-10-06 16:00 | N | Y | circuit breaker replacement | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 820s 702T (820s Hangingstone),820s 703 (820s Hangingstone) | 2015-09-23 08:00 | 2015-09-23 17:00 | N | N | maintenance | Circuit Breaker, Transformer |  | 703 BKR PARTIAL PM, transfer load to 701T
ENMAX | ENMAX 65 B240-D132 (ENMAX 65) | 2015-09-23 08:00 | 2015-09-28 16:00 | N | Y | 240KV breaker modification & doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 447s T2 (447s Enchant) | 2015-09-23 08:00 | 2015-09-23 14:00 | N | N | install bird cover | Transformer
ALTALINK | 908L (89s Ellerslie - 816s Petrolia),89s 12 (89s Ellerslie) | 2015-09-23 08:30 | 2015-09-23 17:00 | N | Y | switch maintenance | Line, Switch |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2015-09-24 04:17 | 2015-10-06 17:00 | N | Y | forced outage | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
EPCOR | Garneau T2 (Garneau) | 2015-09-24 07:00 | 2015-09-25 18:00 | N | N | cutover for protection upgrade | Transformer |  |  | Overload
ALTALINK | 723s T1 (723s Christina Lake) | 2015-09-24 08:00 | 2015-09-24 12:00 | N | Y | remove existing trips from 96/652 & L2 A & B protection to 723s152 | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 379s 452 (379s Shell Waterton) | 2015-09-24 08:00 | 2015-09-24 17:00 | N | N | 69kV breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703AL tap) | 2015-09-24 08:00 | 2015-09-25 17:00 | N | N | insulator washing - helicopter | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 786s 507C (786s High Level),786s507 (786s High Level) | 2015-09-24 10:00 | 2015-09-24 13:00 | N | N | install bushing and wire bird proofing material | Shunts, Circuit Breaker |  | Install Bushing and Wire Bird Proofing Material. /507C Out of service for the duration of the work | Pre-Condition, For Information Only
DAISHOWA | 147S Daishowa Plant | 2015-09-24 12:00 | 2015-09-24 12:30 | N | N | ADAMS dispatch interruption due to urgent network correction | Station |  |  | For Information Only
ALTALINK | 723s T2 (723s Christina Lake) | 2015-09-24 13:00 | 2015-09-24 17:00 | N | Y | remove existing trips from 96/652 & L2 A & B Prot to 723s252 | Transformer |  |  | 240 kV
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain),845s 710 (845s Big Mountain),845s 709 (845s Big Mountain),749s 706 (749s Flyingshot Lake),749s 705 (749s Flyingshot Lake) | 2015-09-25 07:00 | 2015-10-09 17:30 | N | Y | replace line protection and add breaker fail protection at 845S | Line, Circuit Breaker |  | Replace line protection and add breaker fail protection at 845S. | Pre-Condition, Overload
EPCOR | 987s CGB2 (987s Clover Bar) | 2015-09-25 07:00 | 2015-09-27 18:00 | N | Y | breaker fail | Circuit Breaker |  |  | Restricts Generation
CAPPOWERLP | ENC2 Cloverbar #2 | 2015-09-25 07:00 | 2015-09-27 18:00 | N | N | EPCOR GCG2 breaker outage | Unit
ALTALINK | 133S Stelco Edmonton,822L (133s Stelco Edmonton - 38s East Edmonton) | 2015-09-25 10:30 | 2015-10-02 18:00 | N | N | customer request for grounding and switching & add Altalink supervisory controls to 133s1 and 133s2 | Station, Line
EPCOR | 330P SST3 (330P Genesee) | 2015-09-26 07:00 | 2015-09-27 18:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 80L (331s Ponoka - 958s West Lacombe) | 2015-09-26 07:00 | 2015-10-16 12:00 | N | N | prep work for 80L and P&C work | Line |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 331s T2 (331s Ponoka),331s Ponoka 138kV East Bus | 2015-09-26 07:00 | 2015-10-01 12:00 | N | N | prep work for 80L and P&C | Bus, Transformer |  |  | For Information Only
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2015-09-26 08:00 | 2015-09-27 18:00 | N | Y | urgent repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.3TR (ENMAX 13) | 2015-09-26 08:00 | 2015-09-28 07:30 | N | N | transformer spill containment | Transformer
ALTALINK | 701L (395s North Holden - 223s Strome) | 2015-09-26 08:00 | 2015-09-28 17:00 | N | N | insulator washing - helicopter | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2015-09-26 08:00 | 2015-09-26 12:00 | N | N | fall substation washing | Line, Shunts, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
AESO, ALTALINK | 217s C1 (217s North Red Deer),217s T7 (217s North Red Deer),768L (217s North Red Deer - 87s Gaetz),425L (194s South Red Deer - 217s North Red Deer) | 2015-09-26 08:00 | 2015-10-02 12:00 | N | N | to facilitate City of Red Deer to replace 14-81-1 | Line, Shunts, Transformer |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 320p 401 (320p Keephills) | 2015-09-26 08:30 | 2015-09-26 17:00 | N | N | replace burnt out tank heater | Circuit Breaker
AESO-SC | Genesee Network Disruption | 2015-09-26 09:00 | 2015-09-26 11:00 | N | N | testing of wireless redundant network | SCInternal
EPCOR | 330P Genesee | 2015-09-26 09:00 | 2015-09-26 15:00 | N | N | GN1, GN2, GN3 phone lines | Station |  |  | For Information Only
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2015-09-26 12:00 | 2015-09-26 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2015-09-27 08:00 | 2015-09-27 12:00 | N | N | fall substation washing | Transformer, Line |  |  | Creates Radial Feeds
ENMAX | ENMAX 65 B240-D133 (ENMAX 65) | 2015-09-27 08:00 | 2015-10-02 16:00 | N | N | 240 kV breaker modification and doble | Circuit Breaker |  |  | 240 kV
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2015-09-27 12:00 | 2015-09-27 16:00 | N | N | fall substation washing | Transformer, Line |  |  | Pre-Condition
ALTALINK | 535s T1 (535s Joffre),535s T3a (535s Joffre),535s T5 (535s Joffre),889L (535s Joffre - 536s Brookfield),535s Joffre 138kV Bus 2 | 2015-09-28 06:00 | 2015-09-29 17:00 | N | N | switching needs to be done for 7:00. change 535s10 PT, change out L/As on T1 and T5, and commission protection on bus 2 | Transformer, Bus, Line |  |  | Pre-Condition
ATCO | 751s 702 (751s Hill) | 2015-09-28 07:00 | 2015-10-05 17:30 | N | N | 7L42 Protection upgrade | Circuit Breaker |  | 7L42 Protection Upgrade | Pre-Condition
ALTALINK | 373S Madden | 2015-09-28 07:00 | 2015-09-30 17:00 | N | N | remove temp cables & energize new transformer, switchgear, station equipment | Station
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1) | 2015-09-28 07:00 | 2015-10-05 08:00 | N | Y | FATD: close open point A & C, test energize new 266s1ABC(VT1) and deficiencies repairs. | Line, Shunts |  |  | 240 kV
EPCOR | Namao N721 (Namao) | 2015-09-28 07:00 | 2015-10-02 18:00 | N | N | emergency bushing replacement | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 1044L (805s Jasper - 816s Petrolia),908L (89s Ellerslie - 816s Petrolia) | 2015-09-28 07:00 | 2015-09-28 07:15 | N | N | 15 mins outage due to switching assistance | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 65s T1 (65s High River),65s T2 (65s High River),13L (65s High River - 392s Black Diamond),158L (65s High River - 392s Black Diamond),753L (65s High River - 253s Blackie) | 2015-09-28 07:00 | 2015-10-01 18:00 | N | N | Foothills 138kV: connect and test energize new 434L bay | Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 816s P2406 (816s Petrolia) | 2015-09-28 07:00 | 2015-09-29 18:00 | N | N | emergency repair of P2406 dashpot | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 657s Summerside T1 (657s Summerside) | 2015-09-28 07:00 | 2015-10-01 18:00 | N | Y | doble/tapchanger | Transformer |  |  | 240 kV, For Information Only
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2015-09-28 08:00 | 2015-09-28 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 892L (895s Suffield - 41s Medicine Hat) | 2015-09-28 08:00 | 2015-09-30 17:00 | N | Y | add new structure | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.2TR (ENMAX 13) | 2015-09-28 08:00 | 2015-10-27 16:00 | N | N | transformer spill containment & secondary cable deficiency fix | Transformer
ALTALINK | 681s 152 (681s Bannerman),681s 1052 (681s Bannerman) | 2015-09-28 08:00 | 2015-10-02 16:00 | N | Y | trip tests from customer protections, expanding existing transform isolation to allow operation of 681s389 & 681s152/681s1052 | Circuit Breaker |  |  | 240 kV
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2015-09-28 08:00 | 2015-10-07 08:00 | N | N | transformer spill containment &13.60L washing (Oct 2-4). CT ratio change and SEL relay settings | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 12.1TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12) | 2015-09-28 08:00 | 2015-10-09 13:00 | N | Y | SW's 84, 85 & 86 replacement | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-09-28 09:00 | 2015-10-02 17:00 | N | Y | line rebuild | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation
ATCO | 801s 906 (801s Anderson) | 2015-09-28 09:00 | 2015-09-29 16:00 | N | Y | mantenance | Circuit Breaker |  | 801S Anderson - BREAKER MIN OIL HLR PARTIAL TESTING Partial Maint on Breaker 906 Breaker 906 not available | 240 kV, Contingency Requires Mitigation
ATCO | 863s 901 (863s Paintearth) | 2015-09-28 09:00 | 2015-09-28 16:00 | N | Y | maintenance | Circuit Breaker |  | Bkr 901 O/S for maintenance. Switch 900D1 will be closed tying 9L27 to 9L948, Settings will need to be changed @ 650s Hansman Lake & 755s Cordel | 240 kV, Pre-Condition
ATCO | 732s 904 (732s Mitsue) | 2015-09-28 09:00 | 2015-10-01 16:00 | N | Y | breaker testing | Circuit Breaker |  | BREAKER MIN OIL HPF COMPLETE TESTING, 904 @ 732S | 240 kV, Contingency Requires Mitigation
ATCO | 740s 703T (740s H.R.Milner) | 2015-09-28 11:00 | 2015-09-28 14:00 | N | N | take bushing PCB samples | Transformer |  | Take Bushing PCB samples
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2015-09-28 12:01 | 2015-09-28 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 536s T1 (536s Brookfield) | 2015-09-28 13:00 | 2015-09-29 16:00 | N | N | SCADA replacement project and T1 relay maintenance | Transformer
ALTALINK | 650s SVC (650s Hansman Lake) | 2015-09-28 13:00 | 2015-10-01 17:00 | N | Y | annual maintenance | Shunts |  |  | 240 kV
ALTALINK | 77s Sagitawah RTU/SCADA | 2015-09-28 15:00 | 2015-09-28 15:20 | N | N | update RTU config | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 150L (42s Sarcee - 150L47) | 2015-09-28 17:00 | 2015-09-29 08:00 | N | N | high load move | Line |  |  | Pre-Condition
ALTALINK | 501CL (983s Cadomin - 501L tap),501L (426s Coalspur - 501CL tap) | 2015-09-29 07:00 | 2015-10-01 16:00 | N | N | 983s LA replacements | Line
ALTALINK | 122s T1 (122s Alberta Newsprint),122s T2 (122s Alberta Newsprint) | 2015-09-29 07:00 | 2015-09-30 12:00 | N | Y | replace T1 & T2 tap changer controller | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 291s T1 (291s Cochrane) | 2015-09-29 07:00 | 2015-10-01 17:00 | N | N | Repair transformer leaks. | Transformer |  |  | For Information Only
ALTALINK | 723s T1 (723s Christina Lake) | 2015-09-29 08:00 | 2015-09-29 12:00 | N | Y | tie in and test trips from the new 96/652 to 723s152 | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 702L (137s Sedgewick - 757s Battle River) | 2015-09-29 08:00 | 2015-09-30 17:00 | N | N | insulator washing - helicopter | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 277s T2 (277s Hayter) | 2015-09-29 09:00 | 2015-09-29 16:00 | N | N | fix deficiencies on 277s28 | Transformer
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2015-09-29 12:00 | 2015-09-29 16:00 | N | Y | fall substation washing | Line, Transformer, Shunts |  |  | For Information Only
ALTALINK | 723s T2 (723s Christina Lake) | 2015-09-29 13:00 | 2015-09-29 17:00 | N | Y | tie in and test trips from the new 96/652 to 723s252 | Transformer |  |  | 240 kV
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2015-09-29 20:00 | 2015-09-30 06:00 | N | N | night fall substation washing | Line, Transformer, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 482S Haynes | 2015-09-30 06:30 | 2015-10-04 18:00 | N | N | maintenance and metering work | Station |  |  | For Information Only
ATCO | 745s 601T (745s Slave Lake) | 2015-09-30 07:00 | 2015-12-02 17:00 | N | N | station rebuild | Transformer |  | Station rebuild
ENMAX | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington) | 2015-09-30 07:00 | 2015-10-01 13:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
EPCOR | 805s J2404 (805s Jasper) | 2015-09-30 07:00 | 2015-09-30 16:00 | N | Y | switching demonstration | Circuit Breaker |  |  | 240 kV, Firm Load Loss
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2015-09-30 08:00 | 2015-09-30 16:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 437s T1 (437s Baymag),437s T2 (437s Baymag) | 2015-09-30 08:00 | 2015-10-01 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 1107L (ENMAX 65 - 237s Foothills),ENMAX 65 B240-D135 (ENMAX 65),ENMAX 65 B240-D134 (ENMAX 65) | 2015-09-30 08:00 | 2015-10-09 17:00 | N | N | emergency work in preparation of 1109L | Line, Circuit Breaker
ALTALINK | 616L (103s Goose Lake - 616AL tap),616L (59s Peigan - 616AL tap) | 2015-09-30 08:00 | 2015-09-30 12:00 | N | Y | open jumpers on 59s side of 383s tap | Line |  |  | Pre-Condition, Restricts Generation, For Information Only
ENMAX | 24.1TR (ENMAX 24) | 2015-09-30 08:00 | 2015-09-30 16:00 | N | N | top up oil level | Transformer |  |  | For Information Only
ALTALINK | 616L (59s Peigan - 616AL tap) | 2015-09-30 12:00 | 2015-10-12 13:00 | N | N | line maintenance | Line |  |  | Pre-Condition
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2015-09-30 20:00 | 2015-10-01 02:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2015-10-01 02:00 | 2015-10-01 06:00 | N | Y | night fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 240 kV North Bus | 2015-10-01 07:00 | 2015-10-01 13:00 | N | Y | maintenance outage, 240 kV washing | Transformer, Bus |  |  | 240 kV, Restricts Generation
EPCOR | Garneau T1 (Garneau) | 2015-10-01 07:00 | 2015-10-02 18:00 | N | N | cutover for protection upgrade | Transformer
ALTALINK | 674L (649s Chappice Lake - 41s Medicine Hat) | 2015-10-01 07:00 | 2015-10-16 18:00 | N | Y | re-route 674L in to Bowmanton | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1239L (510s Sunnybrook - 330p Genesee) | 2015-10-01 07:00 | 2015-10-05 18:00 | N | Y | Epcor breaker replacement - 1205 testing | Line |  |  | 500 kV
ALTALINK | 322S Cowley Ridge | 2015-10-01 08:00 | 2015-12-01 17:00 | N | Y | update substation component names | Station |  |  | Restricts Generation
ALTALINK | 701L (223s Strome - 7L701D1) | 2015-10-01 08:00 | 2015-10-01 17:00 | N | N | insulator washing - helicopter | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 331s T1 (331s Ponoka),421L (331s Ponoka - 288s Wolf Creek),716L (40s Wetaskiwin - 331s Ponoka),80L (331s Ponoka - 958s West Lacombe) | 2015-10-01 12:30 | 2015-10-09 12:00 | N | N | cut free 716L & 80L from 331s, bus upgrade, P&C commissioning tests | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-RB131 (162s Beddington),162s 240-RB132 (162s Beddington) | 2015-10-01 13:01 | 2015-10-03 13:00 | N | Y | maintenance outage | Circuit Breaker |  |  | 240 kV, Restricts Generation
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37) | 2015-10-01 20:00 | 2015-10-02 02:00 | N | N | night fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 37.2TR (ENMAX 37),37.82L (74s Janet - ENMAX 37) | 2015-10-02 02:00 | 2015-10-02 06:00 | N | Y | night fall substation washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 657s Summerside T2 (657s Summerside) | 2015-10-02 07:00 | 2015-10-05 18:00 | N | Y | doble/tapchanger maintenance | Transformer |  |  | 240 kV, For Information Only
ATCO | 7L47 (848s Ruth Lake - 718s Parsons Creek),7L71 (718s Parsons Creek - 2082s Dog Rib) | 2015-10-02 07:00 | 2015-10-08 17:00 | N | N | line move for new highway | Line |  | Line move for new highway, Parsons Creek, Dog Rib, Tower Rd, and Halfway on a radial feed | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-10-02 07:00 | 2015-10-03 17:00 | N | N | Foothills 138kV: cut over new 850L on 1106L/1107L triple circuit section | Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 535s 1152 (535s Joffre),535s Joffre 138kV Bus 3 | 2015-10-02 07:00 | 2015-10-04 17:00 | N | Y | cutover and commissioning of breaker fail on 535s1152 function trip tests | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 793s 707C (A793s West Peace),A793s 707 (A793s West Peace) | 2015-10-02 08:00 | 2015-10-02 15:30 | N | N | partial PM | Circuit Breaker, Shunts |  | 793S 707 Partial PM. / 707C out of service for the duration of the work | For Information Only
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24) | 2015-10-02 08:00 | 2015-10-02 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 38s 75 (38s East Edmonton) | 2015-10-02 08:30 | 2015-10-02 17:00 | N | N | replace burnt out tank heater | Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s 252 (102s Langdon),102s Langdon 240 kV West Bus,102s 7352 (102s Langdon),102s 5652 (102s Langdon),102s 6452 (102s Langdon),102s 6752 (102s Langdon) | 2015-10-02 09:00 | 2015-10-06 08:00 | N | Y | connect HVDC AC bus to existing bus | Circuit Breaker, Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 221s C1 (221s Sunken Lake) | 2015-10-02 09:00 | 2015-10-02 17:00 | N | N | investigate DC ground | Shunts |  |  | For Information Only
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24) | 2015-10-02 12:00 | 2015-10-02 16:00 | N | Y | fall substation washing | Line, Transformer
ENMAX, ALTALINK | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),32PT138-Z31 (ENMAX 32),54PT138-32.82 (ENMAX 54) | 2015-10-02 20:00 | 2015-10-03 06:00 | N | N | night fall substation washing | Line, Transformer, Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
AESO, ENMAX | 5.2TR (ENMAX 5),5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2015-10-03 08:00 | 2015-10-03 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Overload, For Information Only
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2015-10-04 01:00 | 2015-10-04 05:00 | N | N | night fall substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2015-10-04 08:00 | 2015-10-04 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.2TR (ENMAX 22),22.3TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39),22PT138-Z7 (ENMAX 22) | 2015-10-04 12:00 | 2015-10-04 16:00 | N | N | fall substation washing | Line, Transformer, Terminal Equipment |  |  | Creates Radial Feeds
ALTALINK | 535s T2 (535s Joffre),535s T4 (535s Joffre),535s T6 (535s Joffre),535s Joffre 138kV Bus 1 | 2015-10-05 05:00 | 2015-10-07 17:00 | N | N | commission B1 bus protection | Transformer, Bus |  |  | Pre-Condition
EPCOR | 803s T1 (803s Lambton) | 2015-10-05 07:00 | 2015-10-19 18:00 | N | Y | oil containment pit construction | Transformer |  |  | 240 kV
ALTALINK | 852L (253s Blackie - 504s Queenstown) | 2015-10-05 07:00 | 2015-10-09 15:00 | N | N | Blackie Project: 852L re-config. 852L will be ready to re- energize @ the end of each day | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 149s T1 (149s Nisku) | 2015-10-05 07:00 | 2015-10-05 17:30 | N | N | riser replacements, integrate 149s22 to 138kV bus protection | Transformer |  |  | For Information Only
ENMAX | ENMAX 41,41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41) | 2015-10-05 08:00 | 2015-10-05 12:00 | N | N | fall substation washing | Line, Transformer, Station |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 849s 901T (849s Joslyn Creek) | 2015-10-05 08:00 | 2015-10-07 16:00 | N | Y | maintenance | Transformer |  | 901T MAJOR PM | 240 kV, For Information Only
SUNCOR | 226S Garden City | 2015-10-05 08:00 | 2015-10-09 18:00 | N | Y | customer annual maintenance | Station |  |  | Restricts Generation
ALTALINK | 138s 752 (138s Windy Flats),138s 852 (138s Windy Flats),1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1),237s 2352 (237s Foothills),237s 2252 (237s Foothills) | 2015-10-05 08:00 | 2015-10-10 16:00 | N | Y | FATD: close open point A & C, test energize new 266s1ABC(VT1) and deficiencies repairs | Shunts, Circuit Breaker, Line |  |  | 240 kV
ATCO, SUNCOR | 29PL9-1 (29EDD-1 Millennium - 848s Ruth Lake) | 2015-10-05 08:00 | 2015-10-09 20:00 | N | Y | 29PL9-1, 29EDD-1 260kV line outage | Line |  |  | 240 kV, For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-10-05 09:00 | 2015-10-09 17:00 | N | Y | line rebuild and replacement of protection | Line
MONTANA | Great Falls Switchyard (NorthWestern Energy) - Marias (MATL) | 2015-10-05 09:00 | 2015-10-08 14:30 | N | N | move relay and control from old control house to new one | Line |  |  | Limits ATC
ATCO | 801s 903 (801s Anderson) | 2015-10-05 09:00 | 2015-10-08 17:00 | N | Y | breaker testing | Circuit Breaker |  | 801S Anderson - BREAKER MIN OIL HLR COMPLETE TESTING, 240Kv ring open between 903A and 903B, 9L59 and 9L70 on a radial bus @ 801s | 240 kV, Contingency Requires Mitigation
ALTALINK | 370s T3 (370s North Lethbridge) | 2015-10-05 10:00 | 2015-10-08 17:00 | N | Y | bushing replacements | Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 789s 701R (789s Keg River) | 2015-10-05 10:30 | 2015-10-05 16:00 | N | N | repair leaks on radiator and bushings | Shunts |  | Repair Leaks on Radiator and Bushings. /701R out of service for the duration of the work 1. Leak Repairs 2. Investigate Failed Oil Temp Gauge 3. Obtain PCB Samples from Bushings and Main Tank | Pre-Condition
ENMAX | ENMAX 41,41.1C (ENMAX 41),41.2TR (ENMAX 41),33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41) | 2015-10-05 12:00 | 2015-10-05 16:00 | N | N | fall substation washing | Line, Transformer, Shunts, Station |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 858S Narrows Creek | 2015-10-06 07:00 | 2015-10-09 17:00 | N | N | communication | Station |  | Replace 29 KVA transformer with a 50 KVA transformer. Add feed for Roger's Communication tower, portable AC generator will supply Narrows Ck Tower during outage.
EPCOR | 657s SU2401 (657s Summerside) | 2015-10-06 07:00 | 2015-10-06 18:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 330p 1202 (330p Genesee) | 2015-10-06 07:00 | 2015-10-06 18:00 | N | Y | install OLM | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 42s C3 (42s Sarcee) | 2015-10-06 07:00 | 2015-10-06 17:30 | N | Y | bird cover up installation | Shunts |  |  | 240 kV
ALTALINK | 226S Garden City | 2015-10-06 08:00 | 2015-10-07 13:00 | N | N | customer annual maintenance | Station |  |  | Restricts Generation
ALTALINK | 698s T1 (698s Jackfish) | 2015-10-06 08:00 | 2015-10-06 12:00 | N | Y | installing bird mitigation | Transformer |  |  | 240 kV, For Information Only
AESO, ALTALINK | 54AL (29s Cascade - 54L tap),54L (123s Banff - 177s West Cascade),54L (177s West Cascade - 54L268A) | 2015-10-06 08:00 | 2015-10-06 17:00 | N | Y | replace main bearing and commission 177s20 motor mech | Line |  |  | Pre-Condition
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28),42s 28 (42s Sarcee) | 2015-10-06 08:00 | 2015-10-06 12:00 | N | Y | Fall substation washing | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 786s 702 (786s High Level) | 2015-10-06 08:30 | 2015-10-06 16:30 | N | N | partial PM & setting changes | Circuit Breaker |  | 786S 702 Partial PM. 7L76 & 7L59 tied together for the duration of the work. | Pre-Condition
VISIONREQ | 354s DVAR2 (354s Summerview) | 2015-10-06 09:00 | 2015-10-06 17:00 | N | N | minor maintenance | Shunts |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2015-10-06 12:01 | 2015-10-06 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 698s T2 (698s Jackfish) | 2015-10-06 12:30 | 2015-10-06 17:00 | N | Y | installing bird mitigation | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2015-10-06 13:00 | 2015-10-07 12:00 | N | N | insulator washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 657s SU2402 (657s Summerside) | 2015-10-07 07:00 | 2015-10-07 18:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32),32PT138-Z32 (ENMAX 32) | 2015-10-07 08:00 | 2015-10-07 16:00 | N | N | fall substation washing | Line, Transformer, Terminal Equipment
ENMAX | ENMAX 65 B240-D130 (ENMAX 65) | 2015-10-07 08:00 | 2015-10-12 16:00 | N | Y | breaker modification and doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 767AL (21s Marion - 767L tap) | 2015-10-07 08:00 | 2015-10-07 13:00 | N | N | connect Mobile 475s To 21s | Line
ALTALINK | 431s T1 (431s Hussar) | 2015-10-07 08:00 | 2015-10-07 17:00 | N | N | customer requested outage | Transformer
ATCO | 7L109 (791s Rainbow Lake - 930s Arcenciel),791s 703 (791s Rainbow Lake) | 2015-10-07 09:00 | 2015-10-07 16:00 | N | N | 791S 703 Partial PM as well PCB samples on 7L109PT and Breaker CT's | Line, Circuit Breaker |  | 791S 703 Partial PM as well PCB samples on 7L109PT and Breaker CT's, 7L109 open ended for the duration of the work | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 118s T2 (118s Canmore) | 2015-10-07 10:00 | 2015-10-07 17:00 | N | N | 25kV fused switch replacement | Transformer
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood) | 2015-10-07 13:00 | 2015-10-08 12:00 | N | N | insulator washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 21S Marion | 2015-10-07 14:00 | 2015-11-29 09:00 | N | N | replace / upgrade station equipment | Station
EPCOR | 665s TX1 (665s Dome) | 2015-10-08 07:00 | 2015-10-08 18:00 | N | Y | tapchanger repair | Transformer |  |  | 240 kV
EPCOR | 657s SU2403 (657s Summerside) | 2015-10-08 07:00 | 2015-10-08 18:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 42s C2 (42s Sarcee) | 2015-10-08 07:00 | 2015-10-08 17:30 | N | Y | bird cover up installation | Shunts |  |  | 240 kV
ALTALINK | 1035L (244s Bowmanton - 324s Cassils) | 2015-10-08 08:00 | 2015-10-29 12:00 | N | Y | EATL interface: ATCO  remove jumper between 1035L and 1088L, tie lines into sub, close open jumpers in on the line | Line | Altalink  protection upgrade changes. Atco/Altalink  teleprotection end to end testing. |  | 240 kV
ALTALINK | 431s T1 (431s Hussar) | 2015-10-08 08:00 | 2015-10-08 17:00 | N | N | customer requested outage | Transformer |  |  | For Information Only
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),420s 731 (420s Broadmoor) | 2015-10-08 13:00 | 2015-10-08 15:00 | N | N | top up SF6 gas (low gas alarm) | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),420s 636 (420s Broadmoor) | 2015-10-08 15:00 | 2015-10-08 17:00 | N | N | top up SF6 gas (low gas alarm) | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 657s SU2404 (657s Summerside) | 2015-10-09 07:00 | 2015-10-09 18:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV
ATCO | 9L57 (939s Livock - 960s Birchwood Creek) | 2015-10-09 07:00 | 2015-10-18 17:30 | N | Y | modify line to attach new 2015S Yeo substation to Birchwood | Line |  | Modify line to attach new 2015S Yeo substation to Birchwood. | 240 kV, Pre-Condition
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2015-10-09 08:00 | 2015-10-09 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 237s T2 (237s Foothills) | 2015-10-09 08:00 | 2015-10-09 18:00 | N | Y | repair oil leak | Transformer |  |  | 240 kV
ALTALINK | 716L (40s Wetaskiwin - 331s Ponoka),80L (331s Ponoka - 958s West Lacombe) | 2015-10-09 10:00 | 2015-10-16 12:00 | N | N | jumper 80L & 716L together to form line from 40s to 958s | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 34.1TR (ENMAX 34),34.3TR (ENMAX 34),34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2015-10-09 12:00 | 2015-10-09 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1099L (698s Jackfish - 154s Black Spruce) | 2015-10-10 08:00 | 2015-10-16 08:00 | N | Y | upgrade 1099L A protection and convert to single pole tripping and reclosing | Line |  |  | 240 kV, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2015-10-10 08:00 | 2015-10-10 11:00 | N | N | fall substation washing | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 1109L (ENMAX 65 - ENMAX 25) | 2015-10-10 08:00 | 2015-10-13 16:00 | N | N | In service date: Oct. 12, 2015 | Line
ATCO | 845s 703 (845s Big Mountain) | 2015-10-10 08:00 | 2015-10-10 17:00 | N | N | test and operate for breaker 703 to test 50BF/710 part of breaker fail scheme and blocking close | Circuit Breaker |  | - Test and operate for breaker 703 to test 50BF/710 part of breaker fail scheme and blocking close. | Pre-Condition, Contingency Requires Mitigation
ALBIAN | 920s 902T (920s Jackpine) | 2015-10-10 08:00 | 2015-10-13 17:00 | N | N | customer generated outage (updating protection ) | Transformer |  | Customer generated outage (updating protection ) | 240 kV, For Information Only
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2015-10-10 11:00 | 2015-10-10 15:00 | N | N | fall substation washing | Transformer, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2015-10-10 15:00 | 2015-10-10 19:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-RB135 (162s Beddington) | 2015-10-11 08:00 | 2015-10-16 16:00 | N | Y | ALSTOM 240kV breaker modification, doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2015-10-12 06:00 | 2015-10-12 18:00 | N | N | line maintenance | Line
Syncrude | Aurora T4 (Aurora) | 2015-10-12 06:00 | 2015-10-21 19:30 | N | Y | insulator replacement | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 526L (268s Whitecourt - 526DL185),268s 69 (268s Whitecourt) | 2015-10-12 07:30 | 2015-10-26 17:00 | N | N | upgrade 526L protections | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2015-10-12 08:00 | 2015-10-12 10:00 | N | N | fall substation washing | Transformer
ENMAX | 16.1TR (ENMAX 16) | 2015-10-12 08:00 | 2015-10-16 16:00 | N | N | doble transformer | Transformer
ENMAX | 1.6TR (ENMAX 1) | 2015-10-12 10:00 | 2015-10-12 12:00 | N | N | fall substation washing | Transformer
ENMAX | 1.7TR (ENMAX 1) | 2015-10-12 12:00 | 2015-10-12 14:00 | N | N | fall substation washing | Transformer
ALTALINK | 616L (103s Goose Lake - 616AL tap),616L (59s Peigan - 616AL tap) | 2015-10-12 13:00 | 2015-10-12 17:00 | N | Y | close jumpers on 59s side of 383s tap | Line |  |  | Restricts Generation
ENMAX | 1.8TR (ENMAX 1) | 2015-10-12 14:00 | 2015-10-12 16:00 | N | N | fall substation washing | Transformer
ENMAX | ENMAX 1 | 2015-10-12 16:00 | 2015-10-12 18:00 | N | N | 1.1 cap bank fall substation washing | Station
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36) | 2015-10-12 20:00 | 2015-10-13 08:00 | N | Y | night fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 802s 703T (802s Michichi Creek) | 2015-10-13 07:00 | 2015-10-22 14:00 | N | N | replace transformer pad and install oil containment | Transformer |  | Replace transformer pad and install oil containment.
ATCO | 751s 702T (751s Hill) | 2015-10-13 07:00 | 2015-10-23 17:30 | N | N | upgrade 702T protection | Transformer |  | Upgrade 702T protection. Will Require 10 MVA of load transferred off
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2015-10-13 07:00 | 2015-10-19 18:00 | N | Y | install CT & disconnect replacement | Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV2 (Rossdale - 511s Victoria),Rossdale RV728 (Rossdale) | 2015-10-13 07:00 | 2015-10-16 18:00 | N | N | bushing repair | Line, Circuit Breaker |  |  | For Information Only
ATCO | 7L46 (845s Big Mountain - 813s Little Smoky),813s 706 (813s Little Smoky),813s 705 (813s Little Smoky),845s 708 (845s Big Mountain),845s 709 (845s Big Mountain) | 2015-10-13 07:00 | 2015-10-26 17:30 | N | Y | replace line protection | Line, Circuit Breaker |  | Replace line protection. | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss
ALTALINK | 5s T1 (East Calgary),5s 1652 (5s East Calgary),5s East Calgary 240kV Bus 1,5s 1152 (5s East Calgary) | 2015-10-13 07:00 | 2015-10-19 15:00 | N | N | ECTP: close open point A | Transformer, Bus, Circuit Breaker |  |  | 240 kV
ATCO | 749s 702T (749s Flyingshot Lake),749s 705 (749s Flyingshot Lake),749s 704 (749s Flyingshot Lake) | 2015-10-13 07:00 | 2015-10-30 17:00 | N | N | Protection changes to 704, 705, 505, 506, 507, repair 502TD | Transformer, Circuit Breaker |  | Protection changes to 704, 705, 505, 506, 507, repair 502TD, All 25kV load already transferred to 701T, 5L568, 5L291, 5L292 load being transferred onto bkr 503, 144kV bus @ 749s will be open, 5L333 Aquatera Utilities generator must be offline for duration of outage, 500MT2 will be OOS. -------- Load Transfer -------- 749S 5L568 Peak Load = 1.86 MVA 749S 5L292 Peak Load = 8.35 MVA 749S 5L291 Peak Load = 7.04 MVA 749S 5L290 Peak Load = 2.16 MVA 749S 5L568 Relay Settings: 25.98 MVA 749S 5L292 Relay Settings: 25.98 MVA 749S 5L291 Relay Settings: 17.3 MVA 749S 5L290 Relay Settings: 21.65 MVA -------- Load Transfer -------- | Pre-Condition
ALTALINK | 138s 1052 (138s Windy Flats),138s 1152 (138s Windy Flats),1038L (138s Windy Flats - 266s Foothills),237s 2552 (237s Foothills),237s 2652 (237s Foothills) | 2015-10-13 07:00 | 2015-10-24 17:00 | N | Y | FATD: close open point B & D, test energize new 266s4ABC(VT2) and deficiencies repairs | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | ENMAX 25 B240-D131 (ENMAX 25),ENMAX 25 B240-D132 (ENMAX 25),25MD240-1GSU (ENMAX 25) | 2015-10-13 08:00 | 2015-10-14 16:00 | N | Y | maintenance | Circuit Breaker, Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 413L (239s Castle River - 632s Russell) | 2015-10-13 08:00 | 2015-10-13 17:00 | N | Y | maintenance | Line |  |  | Restricts Generation
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2015-10-13 08:00 | 2015-12-10 16:00 | N | N | In service date: Dec. 10, 2015. Refer to the Op Plan binder for the commissioning plan. | Line
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2015-10-13 08:00 | 2015-10-18 17:00 | N | Y | IP: replace 240kV insulators, 74s57 and C3 and C4 bird cover up | Bus, Transformer, Shunts |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 212S Lacombe | 2015-10-13 08:00 | 2015-10-15 16:00 | N | N | 212s17/18 PT replacement & metering upgrade | Station |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2015-10-13 08:00 | 2015-10-13 16:00 | N | N | HV CS maintenance | Shunts |  |  | For Information Only
ALTALINK | 754L (118s Canmore - 437s Baymag),118s 754E (118s Canmore) | 2015-10-13 08:00 | 2015-10-15 17:00 | N | N | B protection upgrade | Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 11.4TR (ENMAX 11) | 2015-10-13 08:00 | 2015-10-16 16:00 | N | N | replace reg PT | Transformer
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake) | 2015-10-13 08:00 | 2015-10-13 17:00 | N | N | install conductor dampers on 637L | Line |  |  | Creates Radial Feeds
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2015-10-13 08:00 | 2015-10-16 18:00 | N | N | insulator washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
TRANSALTA | 239S Castle River | 2015-10-13 08:00 | 2015-10-14 17:00 | N | N | sub maintenance | Station |  |  | Restricts Generation
ENMAX | ENMAX 2 B138-D81 (ENMAX 2),ENMAX 2 B138-D85 (ENMAX 2),ENMAX 2 B138-D89 (ENMAX 2),ENMAX 2 B138-D93 (ENMAX 2),ENMAX 2 138kV Z31 Bus | 2015-10-13 08:00 | 2015-10-20 16:00 | N | Y | 5sT1 to north bus connection | Bus, Circuit Breaker |  |  | For Information Only
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington),47.2 TR (ENMAX 47) | 2015-10-13 08:00 | 2015-10-13 16:00 | N | N | fall substation washing. SF6 gas sample and switch maintenance | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
SUNCOR | 29PL9-2 (29EDD-1 Millennium - 848s Ruth Lake) | 2015-10-13 08:00 | 2015-10-16 20:00 | N | Y | 29PL9-2, 29EDD-1 260kV line outage | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2015-10-13 09:00 | 2015-10-16 17:00 | N | Y | line rebuild | Line |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 370s 23 (370s North Lethbridge) | 2015-10-13 09:00 | 2015-10-15 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 411S Obed | 2015-10-13 09:00 | 2015-10-20 17:00 | N | N | T1 oil reclaim & station LA / bushing replacements | Station
ALTALINK | 13s 1252 (13s Deerland) | 2015-10-13 13:00 | 2015-10-23 16:00 | N | Y | Forced out - breaker fail protection not in service | Circuit Breaker |  |  | 240 kV
ALTALINK | 62s11 (62s Brazeau) | 2015-10-13 23:00 | 2015-11-27 14:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ATCO | 9L19 (937s AMR02 - 960s Birchwood Creek),9L28 (937s AMR02 - 960s Birchwood Creek) | 2015-10-14 05:30 | 2015-10-15 17:00 | N | N | Emergency outage - low SF6 breaker | Line |  |  | 240 kV, For Information Only
ATCO | 907S Waddell,907s 701T (907s Waddell) | 2015-10-14 08:00 | 2015-10-14 17:00 | N | N | 7L114 will already be de-energized due to AML maintenance on 72sT2 at 72s Leismer, no added risk, outage has been coordinated with the customer, install bird protection on 701T and 25kV bus at 907s | Station, Transformer |  | 7L114 will already be de-energized due to AML maintenance on 72sT2 @ 72s Leismer, no added risk, outage has been co-ordinated with the customer, install bird protection on 701T and 25kV bus @ 907s
ALTALINK | 72s T2 (72s Leismer) | 2015-10-14 08:00 | 2015-10-14 17:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV
ALTALINK | 5s C3 (5s East Calgary),5s 7 (5s East Calgary),5s C4 (5s East Calgary) | 2015-10-14 08:00 | 2015-10-14 17:00 | N | N | ECTP: wiring changes in DC | Circuit Breaker, Shunts |  |  | Pre-Condition
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2015-10-14 08:00 | 2015-10-19 16:00 | N | Y | ALSTOM 240kV breaker modification, doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 827s SVC (827s Cranberry Lake) | 2015-10-14 09:00 | 2015-10-15 15:00 | N | Y | Replace failed thyristor | Shunts |  | The following work will be performed on the SVC at 827S Cranberry Lake: - Replace failed thyristor - Replace HMI screen - Inspect and repair cooling system - Inspect and repair leak on 703T | Pre-Condition, For Information Only
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2015-10-14 12:00 | 2015-10-14 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 240kV North Bus | 2015-10-15 08:00 | 2015-10-15 16:00 | N | Y | adjustments required on SW 142, switch not opening past 90 degrees | Bus |  |  | 240 kV
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2015-10-15 08:00 | 2015-10-15 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
TRANSALTA | 240s McBride Lake RTU/SCADA | 2015-10-15 08:00 | 2015-10-15 16:00 | N | N | firmware upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 674L (244s Bowmanton - 649s Chappice Lake) | 2015-10-15 08:00 | 2015-10-17 16:00 | N | N | In service date: Oct. 16, 2015 | Line
ALTALINK | 172L (370s North Lethbridge - 172L1238) | 2015-10-15 12:00 | 2015-10-25 17:00 | N | N | line rebuild | Line |  |  | Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2015-10-15 12:00 | 2015-10-15 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power SW904 | 2015-10-16 08:00 | 2015-11-15 16:00 | N | Y | breaker overhaul | Circuit Breaker |  |  | Limits ATC
ALTALINK | 154s 152 (154s Black Spruce) | 2015-10-16 10:00 | 2015-10-16 12:00 | N | Y | remove RAS trips and statuses from 152 breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2015-10-16 12:00 | 2015-10-16 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 154s 552 (154s Black Spruce) | 2015-10-16 13:00 | 2015-10-16 15:00 | N | Y | remove RAS trips and statuses from 652 breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 674L (649s Chappice Lake - 41s Medicine Hat) Old Line | 2015-10-16 17:30 | 2016-04-23 18:00 | N | Y | to build new 675L (41s - 244s) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 718s 701T (718s Parsons Creek),7L165 (718s Parsons Creek - 933s Tower Road),7L47 (848s Ruth Lake - 718s Parsons Creek) | 2015-10-17 07:00 | 2015-10-28 17:30 | N | N | 7L165D2 and 703A and their structures need to be replaced. | Line, Transformer |  | 7L165D2 and 703A and their structures need to be replaced. | Creates Radial Feeds
EPCOR | Garneau T3 (Garneau) | 2015-10-17 07:00 | 2015-10-18 18:00 | N | N | Cutover for protection upgrade | Transformer |  |  | For Information Only
AESO, ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2015-10-17 08:00 | 2015-10-17 16:00 | N | N | fall substation Washing | Line, Transformer |  |  | For Information Only
ALTALINK | 5s T1 (5s East Calgary) | 2015-10-17 08:00 | 2015-10-21 16:00 | N | N | In service date: Oct 20, 2015. Refer to the Op Plan binder for the commissioning plan. | Transformer
ALTALINK | 428L (818s Winefred - 651s Kirby) | 2015-10-17 08:00 | 2015-10-23 16:00 | N | N | In service date: Oct 22, 2015 | Line
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2015-10-17 08:00 | 2015-10-18 17:00 | N | N | Connect mobile to 658L | Line |  |  | Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2015-10-18 01:00 | 2015-10-18 05:00 | N | N | night fall substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 1057L (89s Ellerslie - 657s Summerside) | 2015-10-18 07:00 | 2015-10-18 18:00 | N | Y | Doble | Line |  |  | 240 kV, Creates Radial Feeds
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2015-10-18 07:00 | 2015-10-18 11:00 | N | N | Fall Substation Washing. ***Line must be in service by 11:00am** | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D136 (ENMAX 25) | 2015-10-18 08:00 | 2015-10-23 16:00 | N | Y | 240KV breaker modification & doble test | Circuit Breaker |  |  | 240 kV
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2015-10-18 11:00 | 2015-10-18 16:00 | N | N | fall substation washing. 3 structures to wash on 16.61L. | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 649S Chappice Lake,658L (649s Chappice Lake - 562s Cypress),674L (244s Bowmanton - 649s Chappice Lake) | 2015-10-18 17:00 | 2015-10-24 08:00 | N | Y | transformer & switch maintenance | Station, Line |  |  | For Information Only
ENMAX, ALTALINK | 21.1TR (ENMAX 21),21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34),21.80L (42s Sarcee - ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2015-10-18 23:00 | 2015-10-19 06:00 | N | N | night fall substation washing | Line, Transformer |  |  | For Information Only
EPCOR | RV722 Rossdale (Offload 72RV6) | 2015-10-19 07:00 | 2015-10-19 18:00 | N | N | Bushing inspection | Terminal Equipment |  |  | Pre-Condition
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2015-10-19 07:00 | 2015-10-23 18:00 | N | Y | install CT | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | Kennedale T1 (Kennedale) | 2015-10-19 07:00 | 2015-11-10 18:00 | N | N | internal inspection | Transformer |  |  | For Information Only
EPCOR | 805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2015-10-19 07:00 | 2015-10-23 18:00 | N | Y | disconnect replacement & doble JAB5 | Transformer, Line |  |  | 240 kV
ALTALINK | 149s T3 (149s Nisku) | 2015-10-19 07:00 | 2015-10-22 17:30 | N | N | bus protections & replace T1 CT's | Transformer |  |  | For Information Only
ALTALINK | 1090L (723s Christina Lake - 698s Jackfish) | 2015-10-19 08:00 | 2015-10-20 17:00 | N | Y | Adjustments on the motor of 723s1090 | Line |  |  | 240 kV, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.3TR (ENMAX 11) | 2015-10-19 08:00 | 2015-10-23 16:00 | N | N | PRD Install | Transformer |  |  | For Information Only
ENMAX | 31.1C (ENMAX 31),31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2015-10-19 08:00 | 2015-10-23 16:00 | N | N | PT replacement harmonic monitoring | Line, Transformer, Shunts |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 322s T1 (322s Cowley Ridge) | 2015-10-19 08:00 | 2015-10-19 17:00 | N | Y | relay upgrade | Transformer |  |  | Restricts Generation
ENMAX | 34.4TR (ENMAX 34) | 2015-10-19 08:00 | 2015-10-23 16:00 | N | N | Doble transformer sec. Cables | Transformer |  |  | For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-10-19 09:00 | 2015-10-23 17:00 | N | Y | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 840S McNeill Station | 2015-10-19 09:00 | 2015-10-30 18:00 | N | Y | replace 18 25 KV switches and all arrestors | Station |  | Replace 18 25 KV switches and all arrestors. | Limits ATC
ALTALINK | 74s 252 (74s Janet) | 2015-10-19 11:00 | 2015-10-22 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 526s C1 (526s Buffalo Creek),526s 652 (526s Buffalo Creek) | 2015-10-19 13:00 | 2015-10-20 17:00 | N | N | MEPPI warranty work | Circuit Breaker, Shunts |  |  | Pre-Condition
EPCOR | Victoria V725 (Victoria) | 2015-10-20 07:00 | 2015-10-20 18:00 | N | N | breaker maintenance | Circuit Breaker
TRANSCANADAP, ATCO | 508S Lakesend,7L696 (508s Lakesend - 892s Ribstone Creek) | 2015-10-20 08:00 | 2015-10-20 17:00 | N | N | station maintenance | Station, Line | Station Maintenance; TX18767 (DOBLE, SFRA, Bushing Monitor Repair, TC Maintenance), 138kV Breaker Maintenance (508s696)
ALTALINK | 616L (103s Goose Lake - 616AL tap),616L (59s Peigan - 616AL tap) | 2015-10-20 08:00 | 2015-10-20 12:00 | N | Y | open Jumpers on 59s side of 383s tap | Line |  |  | Restricts Generation
ALTALINK | 320p52 (320p Keephills) | 2015-10-20 08:00 | 2015-10-22 12:00 | N | N | maintenance | Switch
ATCO | 6L02 (873s Marion Lake - 769s Stettler),769s 601 (769s Stettler) | 2015-10-20 08:30 | 2015-10-20 12:00 | N | N | 769S - Bkr 601 Counter Replacement, 6L02 will be open ended @ 769s | Line, Circuit Breaker |  | 769S - Bkr 601 Counter Replacement, 6L02 will be open ended @ 769s | Creates Radial Feeds
ALTALINK | 92s T1 (92s Viscount) | 2015-10-20 10:00 | 2015-10-20 17:00 | N | N | add Supervisory Controls to T1 Tap changer | Transformer
ALTALINK | 616L (59s Peigan - 616AL tap) | 2015-10-20 12:00 | 2015-10-28 08:00 | N | Y | line maintenance | Line |  |  | Creates Radial Feeds
ALTALINK | 426L (194s South Red Deer - 63s Red Deer) | 2015-10-21 07:00 | 2015-11-04 17:00 | N | N | line rebuild, protection work & 80L renaming as 426L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (263s Strachan - 719L259C),848L (17s Benalto - 848L490E),17s 848X (17s Benalto),263s 719X (263s Strachan) | 2015-10-21 08:00 | 2015-10-21 17:00 | N | Y | infrared scan of 717L | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 602s Cold Creek RTU/SCADA | 2015-10-21 08:00 | 2015-10-21 11:00 | N | N | to replace a faulty board in the RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 320p 401 (320p Keephills) | 2015-10-21 08:00 | 2015-10-21 17:00 | N | N | replace burnt out tank heater | Circuit Breaker
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power),526L (268s Whitecourt - 526DL185),268s 268 (268s Whitecourt) | 2015-10-21 10:00 | 2015-10-22 17:00 | N | Y | MEPPI warranty work | Line, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 789L (818s Winefred - 898s Heart Lake) | 2015-10-22 10:01 | 2015-11-09 17:00 | N | N | install VT5 (818s50), line protections, install bus diff, perform functionals | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 227S Cutting Lake | 2015-10-24 07:00 | 2015-11-03 19:00 | N | N | feeder protection on 2125L | Station |  |  | For Information Only
ALTALINK | 266s 1037L FSC (266s SC1) | 2015-10-24 08:00 | 2015-10-30 16:00 | N | N | In service date: Oct. 26, 2015. Refer to the Op Plan binder for the commissioning plan. | Shunts
ALTALINK, ATCO | 1088L (324s Cassils - 2075s Newell),1035L (2075s Newell - 244s Bowmanton) | 2015-10-24 08:00 | 2015-10-30 16:00 | N | N | In service date: Oct 29, 2015 | Line
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2015-10-24 08:00 | 2015-10-24 12:00 | N | N | remove mobile from 658L | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 266s 1038L FSC (266s SC1) | 2015-10-24 08:00 | 2015-10-27 16:00 | N | N | 1038L FSC commissioning. In service date: Oct. 26, 2015. Refer to the op plan binder for the commissioning plan | Shunts
ALTALINK | 266s 1038L FSC (266s SC1) | 2015-10-24 08:00 | 2015-10-30 16:00 | N | N | In service date: October 27, 2015. Refer to the Op Plan binder for the commissioning plan. | Shunts
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1) | 2015-10-24 08:00 | 2015-10-24 16:00 | N | N | inspect and repair deficiencies on the 1037L FSC1 A/B piercing bolts | Line, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 266s 1037L FSC (266s SC1) | 2015-10-24 08:00 | 2015-10-27 16:00 | N | N | 1037L FSC commissioning. In service date: Oct. 26, 2015. Refer to the op plan binder for the commissioning plan | Shunts
ALTALINK, ENMAX | 281s 918(281s Johnson),918L (281s Johnson - 162s Beddington) | 2015-10-24 12:00 | 2015-10-24 14:00 | N | Y | fall substation washing | Switch, Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2015-10-24 12:01 | 2015-11-02 17:00 | N | N | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 932L (74s Janet - 162s Beddington) | 2015-10-24 14:01 | 2015-10-24 16:00 | N | Y | fall substation washing | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 162.1TR (ENMAX 162 Beddington),162s 240-RB131 (162s Beddington),162s 240-RB134 (162s Beddington),162s 138-RB80 (162s Beddington),162s Beddington 240 kV North Bus,162s Beddington 138 kV North Bus,162s 138_RB94 (162s Beddington) | 2015-10-24 16:01 | 2015-10-24 18:00 | N | Y | fall substation washing | Transformer, Circuit Breaker, Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 11.83L (162s Beddington - ENMAX 11),162s 138-RB85 (162s Beddington),162s 138-RB84 (162s Beddington) | 2015-10-25 08:00 | 2015-10-25 10:00 | N | N | fall substation washing | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ALTALINK | SC1 1037L FSC | 2015-10-25 08:00 | 2015-10-27 16:00 | N | N | In service date: October 26, 2015 | Shunts
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2015-10-25 10:00 | 2015-10-25 12:00 | N | Y | fall substation washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington),162s 240-133 (162s Beddington),162s 240-136 (162s Beddington),162s 138-RB83 (162s Beddington),162s 138-RB84 (162s Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus,162s 138_RB92 (162s Beddington) | 2015-10-25 12:00 | 2015-10-25 16:00 | N | Y | fall substation washing | Bus, Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 72RS5 (Rossdale - Strathcona) | 2015-10-26 07:00 | 2015-11-01 18:00 | N | N | degassing | Line
EPCOR | 816s P2402 (816s Petrolia) | 2015-10-26 07:00 | 2015-11-01 18:00 | N | Y | install CT | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 858s Narrows Creek RTU/SCADA | 2015-10-26 07:00 | 2015-10-29 17:00 | N | N | Narrows Creek tower & 858S 701PT: replace 29 KVA transformer with a 50 KVA transformer | Terminal Equipment |  | Replace 29 KVA transformer with a 50 KVA transformer. Add feed for Roger's Communication tower, SOC will see Tower alarms when Stn service transfers over to generator. | Affects Visibility
EPCOR | Namao N721 (Namao) | 2015-10-26 07:00 | 2015-10-30 18:00 | N | N | install disconnect NDS6 | Circuit Breaker |  |  | For Information Only
EPCOR | Rossdale RS724 (Rossdale) | 2015-10-26 07:00 | 2015-10-30 18:00 | N | N | bushing repair | Circuit Breaker |  |  | For Information Only
ALTALINK | 377s C1 (377s Hardisty),377s T1 (377s Hardisty),681L (377s Hardisty - 478s Tucuman),702L (377s Hardisty - 137s Sedgewick),769L (377s Hardisty - 296s Rosyth),703L (377s Hardisty - 703BL tap) | 2015-10-26 07:00 | 2015-10-29 17:00 | N | N | replacing 377s8 | Line, Shunts, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 924L (102s Langdon - 356s Milo),927L (102s Langdon - 356s Milo) | 2015-10-26 07:00 | 2015-10-30 15:00 | N | Y | 266s series capacitor commissioning on 1037L/1038L | Line |  |  | 240 kV, Pre-Condition, Overload
EPCOR | NamaoT1 (Namao) | 2015-10-26 07:00 | 2015-10-30 18:00 | N | N | commission protection for tapchanger controls | Transformer |  |  | For Information Only
ATCO | 9L32 (849s Joslyn Creek - 941s Bitumount),9L32 (941s Bitumount - 2005s Secord) | 2015-10-26 07:00 | 2015-10-30 13:30 | N | Y | install new structures to increase road clearance for the Fort Hills project | Line |  | Install new structures to increase road clearance for the Fort Hills project. This work will take place on 9L32 NEW between 849s and 2005s. | 240 kV
ALTALINK | 763L (28s West Brooks - 763L257A) | 2015-10-26 07:30 | 2015-10-26 17:30 | N | N | urgent repair - sleeve repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 262s T1 (262s Rocky Mountain House),870L (262s Rocky Mountain House - 263s Strachan) | 2015-10-26 08:00 | 2015-10-26 09:00 | N | N | remove CT contributions to bus diff | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1038L (138s Windy Flats - 266s Foothills),266s 1038L FSC (266s SC1) | 2015-10-26 08:00 | 2015-10-26 19:00 | N | Y | in conjunction for 1037L FSC1 testing during the day. | Line, Shunts |  |  | 240 kV
ATCO, SUNCOR | 6L32 (29EDD-1 Millennium - 737s Horseshoe) | 2015-10-26 08:00 | 2015-10-30 20:00 | N | Y | PM work on CVT, disconnects, lightning arrestor | Line |  |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2015-10-26 08:00 | 2015-10-29 16:00 | N | N | PRD install | Transformer
ALTALINK | 89s 752 (89s Ellerslie) | 2015-10-26 08:00 | 2015-10-29 16:00 | N | Y | repalce 89s752 CT's | Circuit Breaker |  |  | 240 kV
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38) | 2015-10-26 08:00 | 2015-10-31 16:00 | N | N | PT replacement harmonic monitoring, SF6 gas sample on 38B138-38.83 | Line, Shunts, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2015-10-26 08:00 | 2015-10-26 16:00 | N | N | DGA, transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 11.4TR (ENMAX 11) | 2015-10-26 08:00 | 2015-10-29 16:00 | N | N | replace reg PT | Transformer
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2015-10-26 08:00 | 2015-10-28 16:00 | N | N | heater retrofit | Circuit Breaker |  |  | For Information Only
ENMAX | Calgary Area UVLS Program | 2015-10-26 08:00 | 2015-10-30 16:00 | N | N | UVLS maintenance | RAS |  |  | For Information Only
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2015-10-26 09:00 | 2015-10-30 13:00 | N | N | line rebuild | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-10-26 09:00 | 2015-10-30 17:00 | N | Y | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 262s T2 (262s Rocky Mountain House),717L (17s Benalto - 262s Rocky Mountain House) | 2015-10-26 09:01 | 2015-10-29 16:00 | N | N | replace CT8 beside 262s717E | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 428s T1 (428s Namaka) | 2015-10-26 13:00 | 2015-11-05 17:00 | N | N | 138kV/25kV bushing replacement, LA's,oil reclaim | Transformer |  |  | For Information Only
ALTALINK | 74s 76 (74s Janet) | 2015-10-27 06:30 | 2015-11-01 18:00 | N | N | replace CT's | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 763L (158s Vauxhall - 763L259) | 2015-10-27 07:30 | 2015-10-27 17:30 | N | N | urgent repair - sleeve repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 62s Brazeau),61s 202X (61s Lodgepole) | 2015-10-27 08:00 | 2015-10-27 16:00 | N | Y | DDR install project | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 898L (37s North Calder - 92s Viscount) | 2015-10-27 08:00 | 2015-10-29 18:00 | N | N | insulator washing - coordinated with breaker replacement outage at 37s | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 678s T1 (678s Okotoks),727L (678s Okotoks - 727L39N),678s Okotoks 138kV Bus 1 | 2015-10-27 08:00 | 2015-11-02 16:00 | N | N | close open point "A" & replace 678s29 | Bus, Line, Transformer |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 856s 901T (856s Kinosis) | 2015-10-27 08:00 | 2015-10-29 17:00 | N | Y | safety concern with 501TD configuration | Transformer |  | Safety Concern with 501TD configuration. Switch orientation to be modified during the outage so switch blades do not remain energized when transformer 901T is out of service. Salvage of protection circuits to 501, 502, 503, 504 originally scheduled under permits 2-31838, 2-31839, 2-31840, 2-31841, can now be completed under one outage to 25KV bay, 25kV load @ 856s will be offloaded/transferred to adjacent substations, site station service will be supplied via 500SST2 fed from new 902T. 240Kv ring will be temporarily opened to open 901TD. | 240 kV, Pre-Condition, For Information Only
ALTALINK | 535s T3a (535s Joffre) | 2015-10-27 08:00 | 2015-10-27 17:00 | N | N | Weschler replacement | Transformer
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2015-10-27 08:00 | 2015-10-28 12:00 | N | N | DGA, transformer maintenance, run through neutral | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 595sT1 (595s Spruce Grove) | 2015-10-27 08:00 | 2015-10-27 16:00 | N | N | replace 2 inch bottom valve on transformer main tank and trip Coil on 595s1525 and repairs to ground bar in switchgear builiding | Transformer
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1) | 2015-10-27 08:00 | 2015-10-27 19:00 | N | Y | 1038L FSC2 testing during the day | Line, Shunts |  |  | 240 kV
ATCO | 786s SVC (786s High Level) | 2015-10-27 08:30 | 2015-10-27 16:30 | N | Y | air cooling maintenance and inspection | Shunts |  | Complete Air Cooling Maintenance and Inspection, SVC Out of service for the duration of the work | For Information Only
ALTALINK | 42s T1 (42s Sarcee),42s 40 (42s Sarcee) | 2015-10-27 09:00 | 2015-10-29 17:00 | N | Y | 138kV breaker maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 3.4TR (ENMAX 3) | 2015-10-27 12:00 | 2015-10-27 16:00 | N | N | DGA, transformer maintenance, run through neutral | Transformer
EPCOR | 987s CGB2 (987s Clover Bar) | 2015-10-28 | 2015-10-28 06:00 | N | N | wiring changes in CGB2 control wiring | Circuit Breaker |  |  | Restricts Generation
Syncrude | Aurora 222 (Aurora) | 2015-10-28 07:00 | 2015-10-29 19:00 | N | Y | breaker repairs | Circuit Breaker |  |  | 240 kV
ATCO | 7L70 (700s Bonnyville - 936s Norberg) | 2015-10-28 07:00 | 2015-10-30 17:00 | N | N | install footings for new tap to St Paul | Line |  | Install footings for new tap to St Paul | Creates Radial Feeds
ALTALINK | 535s T6 (535s Joffre) | 2015-10-28 08:00 | 2015-10-28 17:00 | N | N | Weschler replacement | Transformer |  |  | For Information Only
ALTALINK | 250p11 (250p Bighorn) | 2015-10-28 08:00 | 2015-10-28 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 6.1TR (ENMAX 6) | 2015-10-28 08:00 | 2015-10-28 16:00 | N | N | transformer maint, run through neutral | Transformer |  |  | For Information Only
ENMAX | ENMAX 5 5B138-5BT12 (ENMAX 5) | 2015-10-28 08:00 | 2015-10-30 16:00 | N | N | heater retrofit | Circuit Breaker |  |  | Overload, Creates Radial Feeds
ALTALINK | 616L (103s Goose Lake - 616AL tap) | 2015-10-28 08:00 | 2015-11-02 12:00 | N | N | close jumpers on 59s side and open jumpers on 103s side of 616AL tap for line maintenance | Line |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 818s C3 (818s Winefred) | 2015-10-28 08:00 | 2015-10-28 17:00 | N | N | install pile for new 818s VT5 (inside LOA) | Shunts |  |  | Pre-Condition
ALTALINK | 92s 898 (92s Viscount) | 2015-10-28 08:30 | 2015-10-28 17:00 | N | N | replacing 2 burnt out tank heaters | Circuit Breaker |  |  | For Information Only
ATCO | 930s SVC (930s Arcenciel) | 2015-10-28 09:00 | 2015-10-28 16:00 | N | Y | complete air cooling maintenance and inspection | Shunts |  | Complete Air Cooling Maintenance and Inspection | Pre-Condition, Over/Under Voltage
ALTALINK | 250p22 (250p Bighorn) | 2015-10-28 13:00 | 2015-10-28 18:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 434L (65s High River - 237s Foothills) | 2015-10-29 08:00 | 2015-11-01 16:00 | N | N | In service date: Oct 30, 2015 | Line
ALTALINK | 454s T2 (454s Buck Lake) | 2015-10-29 08:00 | 2015-10-29 19:00 | N | N | doble test HV arrestors, replace arrestor if required | Transformer
ALTALINK | 263s C1 (263s Strachan),263s34 (263s Strachan) | 2015-10-29 08:00 | 2015-10-29 11:00 | N | N | verify new 263s652 breaker fail protection and control | Shunts, Switch |  |  | Pre-Condition, For Information Only
ENMAX | 10.2TR (ENMAX 10) | 2015-10-29 08:00 | 2015-10-29 16:00 | N | N | top up oil level | Transformer
ENMAX | 36.1TR (ENMAX 36) | 2015-10-29 08:00 | 2015-10-29 16:00 | N | N | DGA, transformer maintenance, run through neutral | Transformer
ALTALINK | 262s T1 (262s Rocky Mountain House),870L (262s Rocky Mountain House - 263s Strachan) | 2015-10-29 16:01 | 2015-11-02 12:00 | N | N | replace CT7 beside 262s870W | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | EPCOR Control Centre | 2015-10-30 05:00 | 2015-10-30 05:30 | N | N | Planned outage of communications will be limited to a 30 minute window or less. AESO will be notified prior to commencing repairs | Not In Model |  |  | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2015-10-30 08:00 | 2015-10-30 16:00 | N | N | replace inoperable 43 switch | Transformer |  |  | For Information Only
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan),263s 870E (263s Strachan) | 2015-10-30 08:00 | 2015-10-30 11:00 | N | N | verify new 263s652 breaker fail protection and control | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 818s C1 (818s Winefred),818s C2 (818s Winefred),818s C3 (818s Winefred) | 2015-10-30 08:00 | 2015-11-03 17:00 | N | N | install bus diff & functional | Shunts |  |  | For Information Only
ALTALINK | 266s 1038L FSC (266s SC1) | 2015-10-30 08:00 | 2015-10-30 17:00 | N | N | Refer to the Op Plan binder for the commissioning plan. | Shunts
ENMAX | 11.1TR (ENMAX 11) | 2015-10-30 08:00 | 2015-10-30 16:00 | N | N | DGA, transformer maintenance. Run through neutral. | Transformer |  |  | For Information Only
ALTALINK | 526L (526L90 - 520L tap) | 2015-10-30 17:00 | 2015-11-06 17:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 840S McNeill Station | 2015-10-31 06:00 | 2015-11-03 19:00 | N | Y | McNeill System unavailable for commercial use due to testing | Station |  | McNeill System unavailable for commercial use due to transfer testing | For Information Only
ALTALINK | 74s C2 (74s Janet),74s C1 (74s Janet),74s T2 (74s Janet),74s 76 (74s Janet),74s 23.80W (74s Janet),74s 24.83X (74s Janet),74s Janet 138kV South Bus | 2015-10-31 07:00 | 2015-11-01 18:00 | N | Y | replace 74s58 and strain insulators | Transformer, Bus, Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2015-10-31 08:00 | 2015-10-31 16:00 | N | N | fall Substation Washing | Line, Shunts, Transformer |  |  | Pre-Condition, Overload
ENMAX | 23.4TR (ENMAX 23) | 2015-10-31 08:00 | 2015-10-31 16:00 | N | N | repair SW3. feeder needs to be tied away 1 day ahead | Transformer |  |  | For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2015-10-31 09:00 | 2015-10-31 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 751s 704C (751s Hill),751s 704 (751s Hill) | 2015-11-01 08:00 | 2015-11-04 16:00 | N | N | Hill protection upgrade project | Shunts, Circuit Breaker |  | To allow wiring changes to 704 breaker circuits as part of the Hill Protection Upgrade project. 704C Unavailable during outage | Pre-Condition
ENMAX | 5.8TR (ENMAX 5) | 2015-11-01 08:00 | 2015-11-13 16:00 | N | N | oil processing, doble test and switch maintenance | Transformer |  |  | For Information Only
EPCOR | Hardisty T3 (Hardisty) | 2015-11-02 07:00 | 2015-11-13 18:00 | N | N | commission protection | Transformer |  |  | For Information Only
EPCOR | 511s Victoria T5 (511s Victoria),CV5 (557s Castle Downs - 511s Victoria) | 2015-11-02 07:00 | 2015-11-02 18:00 | N | Y | activate LTC -40*C lockout function | Line, Transformer |  |  | 240 kV
ALTALINK | 852L (253s Blackie - 504s Queenstown) | 2015-11-02 07:00 | 2016-03-16 17:00 | N | N | Blackie project: cut free and salvage 852L in prep for the new line re-config | Line |  |  | Pre-Condition, Over/Under Voltage
EPCOR | NamaoT3 (Namao),72CN10 (987s Clover Bar - Namao),Namao N723 (Namao),Namao N724 (Namao) | 2015-11-02 07:00 | 2015-11-06 18:00 | N | N | install disconnect NDS11 | Transformer, Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 932L (74s Janet - 162s Beddington) | 2015-11-02 07:00 | 2015-11-05 18:00 | N | Y | replace 74s101 | Line |  |  | 240 kV, Pre-Condition, Overload
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2015-11-02 07:00 | 2015-11-23 10:30 | N | N | H724 breaker replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s C1 (58s Edson) | 2015-11-02 07:00 | 2015-11-10 17:00 | N | N | replace CT's on 58s35 | Shunts |  |  | For Information Only
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2015-11-02 07:30 | 2015-11-16 18:00 | N | Y | line repairs | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 12s 752 (12s Heartland),12s 652 (12s Heartland),12s 152 (12s Heartland),12s 252 (12s Heartland) | 2015-11-02 08:00 | 2015-11-13 17:00 | N | Y | final trip testing between ATCO Heathfield & AltaLink prior to energization | Circuit Breaker |  |  | 500 kV
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2015-11-02 08:00 | 2015-11-03 12:00 | N | Y | install outdoor lighting on 138kV bus structure, DGA on bushings and LTC | Transformer |  |  | 240 kV
ALTALINK | 199s T2 (199s East Airdrie) | 2015-11-02 08:00 | 2015-11-02 12:00 | N | N | create open point 'A' on 25kV bus | Transformer |  |  | For Information Only
ALTALINK | 310p 2152 (310p Sundance) | 2015-11-02 08:00 | 2015-11-05 17:00 | N | Y | replace CT's | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-11-02 08:00 | 2015-11-06 16:00 | N | N | CT ratio change and SEL relay settings | Line |  |  | Creates Radial Feeds
ALTALINK | 511s 5252 (511s Crossings),511s 5352 (511s Crossings),FB Bus 1 (511s Crossings) | 2015-11-02 08:00 | 2015-11-06 17:00 | N | Y | Switch checks and deficiency clean up | Circuit Breaker, Bus |  |  | 240 kV, For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2015-11-02 08:00 | 2015-11-12 16:00 | N | N | line differential, breaker maintenance on 9B138-9.83 and 43B138-9.83 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1064L (102s Langdon - 74s Janet) | 2015-11-02 08:00 | 2015-11-07 18:30 | N | Y | L to J: install interphase spacers | Line |  |  | 240 kV
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2015-11-02 08:00 | 2015-11-02 16:00 | N | Y | L to J: overhead shield wire grounding install for complete length of gantry | Line |  |  | 240 kV, Pre-Condition, Overload
ATCO | 885s 501R (885s McMillan),885s 902T (885s McMillan) | 2015-11-02 08:00 | 2015-11-05 17:00 | N | Y | transformer major testing | Transformer, Shunts |  | Transformer Major Testing | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 852 (89s Ellerslie) | 2015-11-02 08:00 | 2015-11-06 16:00 | N | Y | replace 89s852 CT's | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1238L (510s Sunnybrook - 330p Genesee),510s Sunnybrook 500kV A Bus,510s Sunnybrook 500kV B Bus | 2015-11-02 08:00 | 2015-11-14 08:00 | N | Y | connect HVDC AC bus to existing bus | Bus, Line |  |  | 500 kV
ALTALINK, Lethbridge | 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2015-11-02 08:00 | 2015-11-05 16:00 | N | Y | line maintenance | Line | Studied with no wind generation (conservative assumption). |  | Firm Load Loss, Creates Radial Feeds
CMH | MH69_60LMH_60L (MH69s5 North East Cresent Heights - Cancarb) | 2015-11-02 08:00 | 2015-11-04 17:00 | N | N | working in the vicinity of MH60L to salvage old 674L | Line
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-11-02 09:00 | 2015-11-06 17:00 | N | Y | line rebuild | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna),775s 601 (775s Sullivan Lake) | 2015-11-02 09:00 | 2015-11-02 12:00 | N | N | breaker mechanical checks | Line, Circuit Breaker |  | 775S - BKR 601 MECH CHECKS | Firm Load Loss, Creates Radial Feeds
BCH | 5L76 (Ashton Creek - Nicola) | 2015-11-02 09:00 | 2015-11-02 17:00 | N | N | urgent work to repair severely damaged insulator - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2015-11-02 09:30 | 2015-11-02 13:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
TRANSALTA | 229s T2 (229s Glenwood) | 2015-11-02 11:00 | 2015-11-05 17:00 | N | N | doble and rad leak repair on transformer | Transformer
ALTALINK | 616L (59s Peigan - 616AL tap) | 2015-11-02 12:00 | 2015-11-02 17:00 | N | N | close jumpers on 59s side of 383s tap | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 775s 604C (775s Sullivan Lake) | 2015-11-02 12:00 | 2015-11-02 17:00 | N | N | low SF6 on east phase requires topping up | Shunts |  | Bkr 604 - Low SF6 on East Phase requires topping up | For Information Only
ATCO | 7L27 (834s Wesley Creek - A793s West Peace River) | 2015-11-02 13:00 | 2015-11-05 12:00 | N | Y | line clearance mitigation | Line |  | Line clearance mitigation | Pre-Condition, Over/Under Voltage
ALTALINK | 199s T1 (199s East Airdrie) | 2015-11-02 13:00 | 2015-11-05 12:00 | N | N | 25kV switch replacement (199s16) | Transformer |  |  | For Information Only
ALTALINK, ATCO | 409s T1 (409s Shell Scotford),857L (409s Shell Scotford - 410s Josephburg),ALC02L (409s Shell Scotford - 879s Scotford Upgrader) | 2015-11-03 08:00 | 2015-11-04 17:30 | N | Y | Connect the new section of bus to the 138kV Bus B2 (close open point A) | Transformer, Line |  |  | Creates Radial Feeds
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2015-11-03 09:00 | 2015-11-05 17:00 | N | Y | maintenance - BC maintenance does not affect AB ATC | Line |  |  | 240 kV, Limits ATC, Contingency Requires Mitigation
AESO-SC | Northwestern Energy BUCC test | 2015-11-03 09:00 | 2015-11-03 13:30 | N | N | backup control center test | Station |  |  | For Information Only
ATCO | 6L12 (6L25 tap - 774s Monitor),774S 701T | 2015-11-03 10:00 | 2015-11-03 15:00 | N | N | 774S - 501TD operating shaft seal replacement | Line, Terminal Equipment |  | 774S - 501TD Operating Shaft Seal Replacement, 6L12 will be open ended at 774s, 25kV load presently carried by 702T | Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2015-11-03 12:00 | 2015-11-04 16:00 | N | Y | install outdoor lighting on 138kV bus structure & DGA on bushings and LTC | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | SC2 1038L FSC | 2015-11-04 07:00 | 2015-11-07 17:00 | N | Y | SFTP: Repair grout on FSC2 platform foundations | Shunts |  |  | 240 kV, For Information Only
ALTALINK | 818s T3 (818s Winefred) | 2015-11-04 08:00 | 2015-11-04 17:00 | N | N | install bus diff CT contributions | Transformer
ALTALINK | 266s 1038L FSC (266s SC1) | 2015-11-04 08:00 | 2015-11-04 17:00 | N | Y | footing work | Shunts |  |  | 240 kV, For Information Only
ALTALINK | 409s T3 (409s Shell Scotford) | 2015-11-04 08:00 | 2016-04-12 17:00 | N | N | install and dress new T3 and change isolation points to continue prep work on T3 | Transformer
ALTALINK | 61s T1 (61s Lodgepole) | 2015-11-04 08:00 | 2015-11-04 16:00 | N | N | DDR install project | Transformer
ALTALINK | 724L (500s Flatbush - 724L1) | 2015-11-04 09:00 | 2015-11-04 13:00 | N | N | repair damaged strain insulators | Line |  |  | For Information Only
EPCOR | 814s T2 (814s Bellamy) | 2015-11-05 07:00 | 2015-11-06 18:00 | N | Y | op checks | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 818s T2 (818s Winefred) | 2015-11-05 08:00 | 2015-11-05 17:00 | N | N | install bus differential CT contributions | Transformer
ALTALINK | 778L (217s North Red Deer - 87s Gaetz) | 2015-11-05 08:00 | 2015-11-05 18:00 | N | N | remove existing suspension clamps & add new clamps | Line |  |  | Overload
ALTALINK | 61s T2 (61s Lodgepole) | 2015-11-05 08:00 | 2015-11-05 16:00 | N | N | DDR install project | Transformer
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),47.2 TR (ENMAX 47) | 2015-11-05 08:00 | 2015-11-06 16:00 | N | N | fall substation washing & SF6 gas sample | Line, Transformer |  |  | Pre-Condition, For Information Only
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2015-11-05 08:00 | 2015-11-05 18:00 | N | N | high load move | Line |  | We have a high load coming through from Peace River to Slave Lake & would like to take an outage on 7L23 from Mitsue to Nipisi subs / line will only be out long enough to allow load to pass under line approximately .5 to 1 hour | Firm Load Loss, Creates Radial Feeds
ATCO | 959s 901T (959s Lanfine) | 2015-11-05 11:00 | 2015-11-05 16:00 | N | Y | rad leak repairs | Transformer |  | remove 901T from service to allow for xmer rad leak repairs | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199s T2 (199s East Airdrie) | 2015-11-05 12:00 | 2015-11-05 17:00 | N | N | close open point 'A' on 25kV bus | Transformer
ALTALINK | 511s 4952 (511s Crossings),511s 5052 (511s Crossings),FB Bus 2 (511s Crossings) | 2015-11-05 12:00 | 2015-11-10 12:00 | N | N | switch checks and deficiency clean up | Circuit Breaker, Bus
EPCOR | EPCOR Control Centre | 2015-11-06 05:00 | 2015-11-06 05:30 | N | N | Planned outage of communications will be limited to a 30 minute window or less. AESO will be notified prior to commencing repairs | Not In Model |  |  | For Information Only
EPCOR | 930L (37s North Calder - Poundmaker) | 2015-11-06 07:00 | 2015-11-09 17:00 | N | Y | line maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 851L (525s Carseland - 253s Blackie) | 2015-11-06 07:30 | 2015-11-06 18:00 | N | N | structure urgent repair | Line |  |  | Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2015-11-06 08:00 | 2015-11-17 17:00 | N | N | line maintnenace | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 768L (217s North Red Deer - 87s Gaetz) | 2015-11-06 08:00 | 2015-11-08 18:00 | N | N | install deadend conductor, attach new opgw, install temporary jumper. | Line |  |  | Overload, Contingency Requires Mitigation
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2015-11-06 08:00 | 2015-12-13 17:00 | N | N | In service date: December 13, 2015. Refer to the Op Plan binder for the commissioning plan. | Line
ATCO | 834s 708 (834s Wesley Creek) | 2015-11-06 08:00 | 2015-11-06 16:30 | N | N | low SF6 - urgent | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2015-11-06 08:00 | 2015-11-06 17:00 | N | Y | cut pothead free on underground cable, repair OHSW and recloser logic deficiencies | Line |  |  | 240 kV
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2015-11-06 17:00 | 2015-11-20 17:00 | N | N | complete protection upgrade and battery bank upgrade | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 74s T1 (74s Janet),37.82L (74s Janet - ENMAX 37),727L (74s Janet - 1140s Temp),813s Little Smoky 144kV Bus 1 | 2015-11-07 07:00 | 2015-11-08 18:00 | N | Y | replace 138kV string Insulators and salvage 74s850E | Bus, Line, Transformer |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 12L85 (12s Heartland - 2029s Heathfield) | 2015-11-07 08:00 | 2015-11-13 16:00 | N | N | In service date: Nov 13, 2015 | Line
ATCO | 12L70 (12s Heartland - 2029s Heathfield) | 2015-11-07 08:00 | 2015-11-13 16:00 | N | N | In service date: Nov 13, 2015 | Line
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2015-11-07 08:00 | 2015-11-07 14:00 | N | N | fall substation washing | Line, Transformer |  |  | Overload
ALTALINK | 255s T1 (255s Vulcan) | 2015-11-07 10:00 | 2015-11-07 14:00 | N | N | repair transformer oil leak | Transformer
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),5.9TR (ENMAX 5),5.10TR (ENMAX 5) | 2015-11-07 14:00 | 2015-11-07 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Overload
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2015-11-08 08:00 | 2015-11-08 14:00 | N | N | fall substation washing | Line |  |  | Pre-Condition, Overload
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2015-11-08 14:00 | 2015-11-08 18:00 | N | N | fall substation washing | Line |  |  | Creates Radial Feeds
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2015-11-08 14:00 | 2015-11-08 18:00 | N | N | ENMAX: washing 162.81L bay @ 162 sub | Line
EPCOR | NamaoT2 (Namao),72VN21 (Namao - 511s Victoria) | 2015-11-09 05:00 | 2015-11-10 22:00 | N | N | Hot connector repair | Line, Transformer
ALTALINK | 74s T1 (74s Janet),74s Janet 240kV Bus 1 | 2015-11-09 07:00 | 2015-11-09 10:00 | N | Y | create open point A on 240kV bus 1 | Transformer, Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
EPCOR | NamaoT2 (Namao) | 2015-11-09 07:00 | 2015-11-10 18:00 | N | N | commission protection for tap changer controls | Transformer |  |  | For Information Only
EPCOR | 803s L2402 (803s Lambton) | 2015-11-09 07:00 | 2015-11-20 18:00 | N | Y | install CT | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 426L (194s South Red Deer - 63s Red Deer) | 2015-11-09 07:00 | 2015-12-16 17:00 | N | N | pull and install 426L underground cables | Line |  |  | Pre-Condition, Overload
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36),14PT138-Z5 (ENMAX 14) | 2015-11-09 07:30 | 2015-11-13 16:00 | N | N | PT replacement harmonic monitoring | Line, Shunts, Transformer, Not In Model |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2015-11-09 08:00 | 2015-11-13 16:00 | N | N | CT ratio change and SEL relay settings | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 352 (89s Ellerslie) | 2015-11-09 08:00 | 2015-11-12 16:00 | N | Y | replace 89s352 CT's | Circuit Breaker |  |  | 240 kV
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2015-11-09 08:00 | 2015-11-21 16:00 | N | Y | line differential | Line |  |  | For Information Only
ATCO, ALTALINK | 1087L (324s Cassils - 2075s Newell),923L (2075s Newell - 356s Milo) | 2015-11-09 08:00 | 2015-11-21 16:00 | N | N | In service date: Nov 21, 2015 | Line
ALTALINK | 853L (504s Queenstown - 853L76A) | 2015-11-09 08:00 | 2015-11-10 18:00 | N | N | line rebuild | Line | 3. Studied with Cavalier = 3 MW. |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 727L (65s High River - 727L39S),727L (678s Okotoks - 727L39N),142s C1 (142s Magcan) | 2015-11-09 08:00 | 2015-12-01 08:00 | N | N | complete the rebuild portion of 727L | Line, Shunts |  |  | Over/Under Voltage
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome),320p T1 (320p Keephills),320p Keephills 240kV Bus B | 2015-11-09 08:00 | 2015-11-09 16:00 | N | Y | repair 320p213, maintain other switches on bus | Bus, Line, Transformer | 4. Studied with net generation Sundance= 2150 MW, Keephills = 1245 MW, Genesee = 1255 MW, Ft. Saskatchewan= 200 MW, and the 320p PST at neutral (Refer to Internal Comments 2, 3 and 4). 2. Lower Sundance generation may alleviate amount of overload for next contingency. 3. Lower KEG area generation may increase amount of overload for next contingency. 4. Lower Ft. Saskatchewan area generation may increase amount of overload for next contingency. |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s T1 (5s East Calgary) | 2015-11-09 08:00 | 2015-11-13 17:00 | N | Y | ECTP: repair oil leak | Transformer |  |  | 240 kV, For Information Only
ENMAX | 11.4TR (ENMAX 11) | 2015-11-09 08:00 | 2015-11-11 12:00 | N | N | metering rewire on 25kV bus | Transformer
ATCO, ALTALINK | 1087L (324s Cassils - 2075s Newell),923L (2075s Newell - 356s Milo) | 2015-11-09 08:00 | 2015-11-20 12:00 | N | Y | EATL: ATCO to remove jumper between 923L and 1087L and tie lines into 2075s Newell sub | Line |  | EATL interface: ATCO  remove jumper between 923L and 1087L, tie lines into sub, close open jumpers in on the line.Altalink  protection upgrade changes.Atco/Altalink  teleprotection end to end testing.On return to normal 923L will become 923L/1087L in/out to Newell(2075s). | 240 kV, For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2015-11-09 08:00 | 2015-11-21 16:00 | N | Y | ENMAX: line differential, heater retrofit, 21s DFR relocate | Line |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2015-11-09 08:00 | 2015-11-09 16:00 | N | N | maintenance | Transformer
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2015-11-09 08:30 | 2015-11-10 17:00 | N | Y | do climbing inspection | Line |  | do climbing inspection 7L77 | Overload
BCH | 5L96 (Selkirk - Vaseux Lake) | 2015-11-09 09:00 | 2015-11-10 17:00 | N | N | maintenance | Line |  |  | Limits ATC
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-11-09 09:00 | 2015-11-13 17:00 | N | Y | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 325s T1 (325s Leduc) | 2015-11-09 09:00 | 2015-11-13 17:00 | N | N | repair leaks | Transformer
ALTALINK | 929L (63s Red Deer - 74s Janet),63s 2752 (63s Red Deer),63s 2652 (63s Red Deer) | 2015-11-09 10:00 | 2015-11-12 17:00 | N | Y | PT replacement | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 373s T1 (373s Madden) | 2015-11-09 10:00 | 2015-11-09 12:00 | N | N | repair significant transformer leak | Transformer
ALTALINK | 929L (63s Red Deer - 74s Janet),932L (74s Janet - 162s Beddington),74s 552 (74s Janet),74s 352 (74s Janet),74s 252 (74s Janet) | 2015-11-09 10:00 | 2015-11-12 17:00 | N | Y | replace 74s929N | Line, Circuit Breaker |  |  | 240 kV, Overload
ALTALINK | 74s 552 (74s Janet) | 2015-11-09 10:00 | 2015-11-13 10:00 | N | Y | in conjunction with 74s929N replacement | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 719L (263s Strachan - 719L259C),263s T2 (263s Strachan) | 2015-11-09 12:01 | 2015-11-30 17:00 | N | N | connection of 719L to new 138kV bus #2 and complete all 138 kV bus connections to new T2, bus tie breaker and PTs | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 320p 1352 (320p Keephills),909L (320p Keephills - 665s Dome) | 2015-11-09 16:01 | 2015-11-15 16:00 | N | Y | replace 1352 CTs | Line, Circuit Breaker | 1. Studied with net generation Sundance= 2150 MW, Keephills = 1245 MW, Genesee = 1255 MW, Ft. Saskatchewan= 200 MW, and the 320p PST at neutral (Refer to Internal Comments 2, 3 and 4). 2. Results of next contingencies depend on Sundance and KEG generation. 3. Lower Sundance generation may alleviate amount of overload for next contingency. 4. Lower KEG area generation may increase amount of overload for next contingency. 5. Lower Ft. Saskatchewan area generation may increase amount of overload for next contingency. |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2015-11-10 07:30 | 2015-11-23 17:30 | N | N | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 202L335),61s 202N (61s Lodgepole) | 2015-11-10 08:00 | 2015-11-10 16:00 | N | Y | DDR install project | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.1TR (ENMAX 26) | 2015-11-10 08:00 | 2015-11-10 12:00 | N | N | maintenance | Transformer
ALTALINK | 887S Carson Creek | 2015-11-10 09:00 | 2015-11-10 13:00 | N | N | repair leak on transformer | Station |  |  | For Information Only
ALTALINK | 887s T1 (887s Mobil Oil Carson Creek) | 2015-11-10 09:00 | 2015-11-10 13:00 | N | N | repair a leak on the transformer - urgent | Transformer
ENMAX | 26.2TR (ENMAX 26) | 2015-11-10 12:00 | 2015-11-10 16:00 | N | N | maintenance | Transformer
ALTALINK | 74s 2052 (74s Janet) | 2015-11-10 14:00 | 2015-11-17 18:00 | N | Y | failed 74s20X breaker remain open | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 858S Narrows Creek,ATCO Radio Tower | 2015-11-12 07:00 | 2015-11-14 17:00 | N | N | replace station service transformer, upgrade communication feed | Terminal Equipment, Station |  | Replace 29 KVA transformer with a 50 KVA transformer. Add feed for Roger's Communication tower, SOC will see Tower alarms when Stn service transfers over to generator. | Affects Visibility
ALTALINK | 378s 452 (378s Shell Caroline) | 2015-11-12 08:00 | 2015-11-12 12:00 | N | N | verify new 263s and 378s BF and Distance protection and control | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 288s T2 (288s Wolf Creek) | 2015-11-12 08:00 | 2015-12-23 11:00 | N | Y | new transformer connection | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 1065L (102s Langdon - 74s Janet) | 2015-11-12 08:00 | 2015-11-21 18:30 | N | Y | L to J: install interphase spacers | Line | 2. Studied with Shepard net generation = 870 MW, high Calgary area generation, Export to BC-MATL = 330 MW, and wind generation = 0 MW (conservative assumption). 3. Results of next contingencies depend on BC-MATL export/import, Shepard and Calgary area generations. |  | 240 kV
ENMAX | 5.1TR (ENMAX 5) | 2015-11-12 08:00 | 2015-11-12 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 28s 81 (28s West Brooks) | 2015-11-12 10:00 | 2015-11-12 11:00 | N | N | check status for transfer trip scheme | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 378s 552 (378s Shell Caroline) | 2015-11-12 12:01 | 2015-11-12 16:00 | N | N | verify new 263s and 378s BF and distance protection and control | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 74s T1 (74s Janet),74s Janet 240kV Bus 1 | 2015-11-13 07:00 | 2015-11-13 10:00 | N | Y | close open point A on 240 kV B1 | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 31.2TR (ENMAX 31) | 2015-11-13 08:00 | 2015-11-13 16:00 | N | N | maintenance | Transformer
ENMAX, ALTALINK | 40.1TR (ENMAX 40),40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41),32.83L (ENMAX 32 - ENMAX 40) | 2015-11-13 22:00 | 2015-11-15 16:00 | N | N | commission new 138kV bus differential protection, auto switching, breaker fail and CT loop checks | Line, Transformer |  |  | Pre-Condition
ALTALINK | 291s T1 (291s Cochrane) | 2015-11-14 07:00 | 2015-11-15 17:00 | N | N | repair transformer leaks | Transformer
ALTALINK | 150L (42s Sarcee - 150L47) | 2015-11-14 08:00 | 2015-11-21 15:00 | N | N | line maintenance | Line | Studied with Big = 6 MW - no concerns. |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.1C (ENMAX 21),21.1TR (ENMAX 21),21.4TR (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20),21.80L (42s Sarcee - ENMAX 21) | 2015-11-14 08:00 | 2015-11-14 16:00 | N | N | repair disconnect SW84 | Line, Transformer, Shunts |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2015-11-15 07:00 | 2015-11-15 17:00 | N | Y | line upgrades | Line | Studied with both full SD and min SD generation - no impact to amount of voltage concerns. |  | Pre-Condition, Over/Under Voltage
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2015-11-15 14:00 | 2015-11-18 18:00 | N | N | correct protection relay failure | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | NamaoT1 (Namao) | 2015-11-16 07:00 | 2015-11-20 18:00 | N | N | NDS8 replacement | Transformer
EPCOR | E511s VictoriaT4 (511s Victoria) | 2015-11-16 07:00 | 2015-11-20 18:00 | N | N | cable taping | Transformer
ATCO | 802s 703T (802s Michichi Creek) | 2015-11-16 07:00 | 2015-12-04 17:00 | N | N | replace transformer pad and install oil containment | Transformer |  | Replace transformer pad and install oil containment, 703T load will be transferred to 702T.
ATCO | 6L09 (767s Oyen - 6L21 tap),767s 601 (767s Oyen) | 2015-11-16 07:00 | 2015-11-20 17:30 | N | N | replace line protection | Line, Circuit Breaker |  | Replace line protection | Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 252 (310p Sundance) | 2015-11-16 08:00 | 2015-11-16 12:30 | N | Y | replacing aux voltage transformer | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2015-11-16 08:00 | 2015-11-20 16:00 | N | N | PT replacement harmonic monitoring | Line, Transformer |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 452 (89s Ellerslie) | 2015-11-16 08:00 | 2015-11-19 16:00 | N | Y | replace 89s452 CT's | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
TRANSALTAW | 418s Ardenville | 2015-11-16 08:00 | 2016-01-15 16:00 | N | N | troubleshoot DC ground fault | Station |  |  | For Information Only
ALTALINK | 320p PS2 (320p Keephills),320p 2652 (320p Keephills),320p 2752 (320p Keephills) | 2015-11-16 08:00 | 2015-11-23 16:00 | N | Y | migrate SCADA from old to new system | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-11-16 08:00 | 2015-11-19 16:00 | N | N | CT ratio change and SEL relay settings | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 396s 514N (396s Pincher Creek) | 2015-11-16 08:00 | 2015-11-17 17:00 | N | Y | 69 kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 121s T5 (121s Brooks) | 2015-11-16 08:00 | 2015-11-27 17:00 | N | N | oil reclaim | Transformer
ALTALINK | 288s Wolf Creek 138kV Bus 2 | 2015-11-16 08:00 | 2015-11-26 08:00 | N | N | swinging new parts onto new transformer in close proximity of 138kV bus 2 | Bus |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 3.4TR (ENMAX 3) | 2015-11-16 08:00 | 2015-11-16 16:00 | N | N | maintenance | Transformer
ALTALINK | 983L (251s Whitla - 244s Bowmanton) | 2015-11-16 08:00 | 2015-12-05 18:00 | N | Y | damper spacer replacement | Line |  |  | 240 kV, For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2015-11-16 09:00 | 2015-11-20 17:00 | N | Y | line rebuild | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2652 (310p Sundance) | 2015-11-16 12:30 | 2015-11-16 17:00 | N | Y | replacing aux voltage transformer | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L33 (7L33D2 - 845s Big Mountain),845s 708 (845s Big Mountain),845s 707 (845s Big Mountain) | 2015-11-17 07:00 | 2015-11-30 17:30 | N | Y | install new breaker control cables and protection | Line, Circuit Breaker |  | Install new breaker control cables and protection. | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 895s Suffield RTU/SCADA | 2015-11-17 07:00 | 2015-11-17 17:00 | N | N | RTU update | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 409s T2 (409s Shell Scotford) | 2015-11-17 08:00 | 2015-11-24 17:00 | N | N | measure out 25kV cables and test connect to 409s 25kV bus attached to T2 | Transformer
ALTALINK | 1036L (554s Travers - 356s Milo) | 2015-11-17 08:00 | 2015-11-20 17:00 | N | Y | miscellaneous maintenance, spacers, dampers, insulators, conductor | Line | 1. Studied with AB-MATL import = 200 MW, AB-BC import = 255 MW and SW wind generation = 1320 MW, Medicine Hat import = 26 MW (conservative assumptions, refer to Internal Comment 1). 1. Higher wind, AB-MATL import and AB-BC import may increase amount of overload on 172L and 180L for next contingency. |  | 240 kV, Pre-Condition
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2015-11-17 08:00 | 2015-11-17 16:00 | N | Y | switch repair | Line | Studied with SOK flow = 1135 MW. |  | 240 kV, Pre-Condition
ENMAX | 33.1TR (ENMAX 33) | 2015-11-17 08:00 | 2015-11-17 12:00 | N | N | maintenance | Transformer
ALTALINK | 650s SVC (650s Hansman Lake) | 2015-11-17 08:00 | 2015-11-19 17:00 | N | Y | replacing insulators - urgent | Shunts |  |  | 240 kV
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2015-11-17 09:00 | 2015-11-17 14:00 | N | Y | repair bushing leak - urgent | Transformer |  |  | 240 kV, For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2015-11-17 12:00 | 2015-11-17 16:00 | N | N | maintenance | Transformer
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2015-11-17 13:30 | 2015-11-18 17:00 | N | Y | replace failed dampers | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 657s Summerside T1 (657s Summerside) | 2015-11-18 07:00 | 2015-11-20 18:00 | N | Y | bushing monitors | Transformer
ALTALINK | 61s T2 (61s Lodgepole) | 2015-11-18 08:00 | 2015-11-18 16:00 | N | N | DDR install project | Transformer
ENMAX | ENMAX 5 5B138-5BT12 (ENMAX 5) | 2015-11-18 08:00 | 2015-11-20 16:00 | N | N | heater retrofit | Circuit Breaker |  |  | For Information Only
ATCO | 7L92 (819s Whitby Lake - 7L92D2) | 2015-11-18 08:00 | 2015-11-19 17:00 | N | N | climbing inspection | Line |  | 7L92 2015 climbing inspection | Overload, Creates Radial Feeds
ALTALINK | 156L (19s Wabamun - 156L84A) | 2015-11-18 08:00 | 2015-11-20 14:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 396s C1 (396s Pincher Creek) | 2015-11-19 08:00 | 2015-11-19 17:00 | N | N | replace faulty SR760 relay on cap bank | Shunts |  |  | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2015-11-19 08:00 | 2015-11-19 16:00 | N | N | maintenance | Transformer
ALTALINK | MUX Radio | 2015-11-19 08:00 | 2015-11-19 16:00 | N | N | replacing SFPs on 9159R - urgent | Terminal Equipment
ENMAX | 2.2TR (ENMAX 2) | 2015-11-19 08:00 | 2016-01-12 16:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
MONTANA | 120s 452 (120s Picture Butte) | 2015-11-19 08:00 | 2015-11-19 17:00 | N | Y | CT leaking west phase | Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 44s T2 (44s Bearspaw Plant) | 2015-11-19 09:00 | 2015-11-19 15:00 | N | N | maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 61s T1 (61s Lodgepole) | 2015-11-19 10:00 | 2015-11-19 11:00 | N | N | DDR install | Transformer
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2015-11-19 10:00 | 2015-11-20 16:00 | N | N | replace faulted relay | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 1044L (805s Jasper - 816s Petrolia) | 2015-11-20 07:00 | 2015-11-23 17:00 | N | Y | upgrades/insulation repair | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 1041L (370s North Lethbridge - 554s Travers) | 2015-11-20 12:30 | 2015-11-29 18:00 | N | Y | line repairs | Line | Studied with wind generation = 1100 MW. |  | 240 kV, Over/Under Voltage
ALTALINK | 156L (235s Entwistle - 156L 86A) | 2015-11-20 15:30 | 2015-11-24 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ENMAX, ALTALINK | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2015-11-21 08:00 | 2015-11-22 16:00 | N | N | fall substation washing and switch maintenance | Line, Transformer | Studied with wind generation = 1100 MW. |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 936L (102s Langdon - 5s East Calgary),102s936 (102s Langdon) | 2015-11-21 08:00 | 2015-11-21 08:15 | N | Y | test airbreak status into WATL RAS | Switch, Line |  |  | 240 kV
ALTALINK | 937L (102s Langdon - 5s East Calgary),102s937 (102s Langdon) | 2015-11-21 08:15 | 2015-11-21 08:30 | N | Y | test airbreak status into WATL RAS | Switch, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 924L (102s Langdon - 356s Milo),102s924 (102s Langdon) | 2015-11-21 08:30 | 2015-11-21 08:45 | N | Y | test airbreak status into WATL RAS | Switch, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo),102s927 (102s Langdon) | 2015-11-21 08:45 | 2015-11-21 09:00 | N | Y | test airbreak status into WATL RAS | Switch, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 102s 6552 (102s Langdon) | 2015-11-21 09:30 | 2015-11-21 11:30 | N | Y | test breaker status into WATL RAS | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 102s 6852 (102s Langdon) | 2015-11-21 12:00 | 2015-11-21 14:00 | N | Y | test breaker status into WATL RAS | Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 102s 7452 (102s Langdon) | 2015-11-21 14:30 | 2015-11-21 16:30 | N | Y | test breaker status into WATL RAS | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 150L (20s Ghost - 150L46) | 2015-11-21 15:30 | 2015-11-23 17:00 | N | N | line maintenance | Line | Studied with BOW = 6 MW. |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1064L (102s Langdon - 74s Janet),102s1064 (102s Langdon) | 2015-11-21 18:00 | 2015-11-21 18:15 | N | Y | test operation to WATL RAS protection | Switch, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 225L (67s Stirling - 225s Magrath) | 2015-11-23 07:00 | 2015-11-26 17:00 | N | Y | 225AL protection replacement ('A' and 'B') | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation
EPCOR | Woodcroft T1 (Woodcroft) | 2015-11-23 07:00 | 2015-11-27 18:00 | N | N | LTC install | Transformer
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2015-11-23 07:00 | 2015-11-24 17:00 | N | Y | CT ratio changes on A21-L11, B21-L11, 96-2052 metering change | Line |  |  | 240 kV
ALTALINK | 113L (20s Ghost - 33s Spray) | 2015-11-23 08:00 | 2015-11-27 17:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2015-11-23 08:00 | 2015-11-27 16:00 | N | N | CT ratio change and SEL relay settings. HV Breaker Inspection 16B69-16.63 | Line, Transformer |  |  | Pre-Condition
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2015-11-23 08:00 | 2015-12-04 16:00 | N | Y | PT replacement harmonic monitoring | Line, Transformer, Shunts |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2015-11-23 08:00 | 2015-11-23 16:00 | N | N | maintenance | Transformer
ALTALINK | 850L (1140s Temp - 525s Carseland) | 2015-11-23 08:00 | 2015-11-29 18:00 | N | N | relocate 850L out of 1140s & into 678s P&C settings changes | Line |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ENMAX | 41.1C (ENMAX 41),6.82L (ENMAX 6 - ENMAX 41),ENMAX 6 B138-6.82 (ENMAX 6) | 2015-11-23 08:00 | 2015-11-24 16:00 | N | N | heater retrofit, replace pole on circuit switcher | Line, Shunts, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale C2 | 2015-11-23 08:00 | 2015-12-07 16:00 | N | N | emergency outage - hot spot | Shunts |  |  | For Information Only
ALTALINK | 277s T2 (277s Hayter) | 2015-11-23 09:00 | 2015-11-23 12:00 | N | N | install correct nameplates on VT3 | Transformer
ALTALINK | 39s T1 (39s Bickerdike),39s 152 (39s Bickerdike),39s Bickerdike 138kV Bus 1 | 2015-11-23 10:00 | 2015-12-03 10:00 | N | Y | replacing CT's associated with 39s152 & 138kV bus #1 protection | Transformer, Circuit Breaker, Bus |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib) | 2015-11-23 12:00 | 2015-11-25 16:00 | N | N | climbing inspection | Line |  | climbing inspection-7L71 from dog rib to Parsons creek | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2015-11-24 07:00 | 2015-11-24 19:00 | N | N | Suncor request to remove T1 from service | Transformer |  |  | For Information Only
ALTALINK | 454S Buck Lake | 2015-11-24 07:00 | 2015-11-24 13:00 | N | N | replace fuses on 454s14 and PT distribution module | Station |  |  | For Information Only
REDDEER | 217s T2 (217s North Red Deer) | 2015-11-24 08:00 | 2015-11-24 15:00 | N | N | City of Red Deer work | Transformer |  |  | For Information Only
ALTALINK | 33s 1 (33s Spray) | 2015-11-24 08:00 | 2015-11-25 16:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 602s T2 (602s Cold Creek) | 2015-11-24 08:00 | 2015-11-24 17:00 | N | N | repair leaks | Transformer |  |  | For Information Only
ALTALINK | 72s 552 (72s Leismer) | 2015-11-24 08:00 | 2015-11-24 12:00 | N | N | protection settings change, perform function tests | Circuit Breaker |  |  | 240 kV
ALTALINK, Lethbridge | 725BL (725BL54 - 240s McBride Lake),725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2015-11-24 08:00 | 2015-11-24 16:00 | N | Y | line maintenance | Line |  |  | Restricts Generation, Creates Radial Feeds
SUNCOR | 609S Wheatland | 2015-11-24 08:00 | 2015-11-24 17:00 | N | Y | relay upgrades | Station |  |  | Restricts Generation
ENMAX | 8.2TR (ENMAX 8) | 2015-11-24 08:00 | 2015-11-24 16:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 856L (409s Shell Scotford - 410s Josephburg),409s 856W (409s Shell Scotford) | 2015-11-24 09:00 | 2015-11-24 10:00 | N | N | trip test beaker from new 409s T2 protections | Line, Circuit Breaker |  |  | For Information Only
ATCO, ALTALINK | ALC01L (409s Shell Scotford - 408s Air Liquide Scotford),409s 107 (409s Shell Scotford) | 2015-11-24 10:01 | 2015-11-24 11:00 | N | N | trip test breaker from new 409s T2 protections | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 409s 20 (409s Shell Scotford) | 2015-11-24 11:01 | 2015-11-24 12:00 | N | N | trip test breaker from new 409s T2 protections | Circuit Breaker |  |  | For Information Only
ALTALINK | 72s 652 (72s Leismer) | 2015-11-24 12:01 | 2015-11-24 16:00 | N | N | protection settings change | Circuit Breaker |  |  | 240 kV
ALTALINK | 901L (74s Janet - 901AL tap) | 2015-11-25 07:00 | 2015-11-26 17:00 | N | Y | CT ratio changes on A21-L8, B21-L8, 96-2552 Metering Change | Line |  |  | 240 kV
ENMAX | 34.1TR (ENMAX 34) | 2015-11-25 08:00 | 2015-11-25 12:00 | N | N | DGA, RTN and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 277s T1 (277s Hayter) | 2015-11-25 09:00 | 2015-11-25 12:00 | N | N | termination of control cables (currently spares) | Transformer |  |  | For Information Only
ATCO | 741s 702T (741s Fox Creek) | 2015-11-25 10:00 | 2015-11-26 15:00 | N | N | change ETM (temp. monitor) and test | Transformer |  | Change ETM (temp. monitor) and test, transfer load to 701T for the duration of the outage. | For Information Only
ENMAX | 34.4TR (ENMAX 34) | 2015-11-25 12:00 | 2015-11-25 16:00 | N | N | DGA, RTN and transformer maintenance | Transformer |  |  | For Information Only
ATCO | 6L126 (515L tap - 743s Sarah Lake) | 2015-11-25 15:00 | 2015-11-25 16:00 | N | N | burnt pole (emergency) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2015-11-26 08:00 | 2015-11-27 16:00 | N | N | In service date: Nov 27, 2015 | Line
ENMAX | 1.84L (ENMAX 1 - ENMAX 5),B138-1.84 (ENMAX 5) | 2015-11-26 08:00 | 2015-11-26 16:00 | N | N | SF6 gas sample on 5B138-1.84 | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 26.1TR (ENMAX 26) | 2015-11-26 08:00 | 2015-11-26 12:00 | N | N | maintenance | Transformer |  |  | For Information Only
ATCO | 946s 909 (946s Oakland) | 2015-11-26 09:00 | 2015-11-26 16:00 | N | Y | breaker in SF6 alarm | Circuit Breaker |  |  | 240 kV
ENMAX | 26.2TR (ENMAX 26) | 2015-11-26 12:00 | 2015-11-26 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
CMH | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview),20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2015-11-26 13:00 | 2015-11-26 17:00 | N | N | high load escort | Line
ALTALINK | 1115L (154s Black Spruce - 170s Pike) | 2015-11-27 08:00 | 2015-11-30 17:00 | N | Y | OPGW splices | Line |  |  | 240 kV, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39) | 2015-11-27 08:00 | 2015-11-27 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2015-11-27 08:00 | 2015-11-27 12:00 | N | N | o ring replacement | Transformer |  |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2015-11-27 12:00 | 2015-11-27 16:00 | N | N | o ring replacement | Transformer |  |  | For Information Only
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2015-11-28 07:00 | 2015-11-28 08:00 | N | N | RTU replacement, test OAC & CAC relays for 27B138-13.60 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2015-11-28 08:00 | 2015-11-28 09:00 | N | N | RTU replacement, test OAC & CAC relays for 27B138-16.61 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37),38.83L (ENMAX 39 - ENMAX 38) | 2015-11-28 08:00 | 2015-11-28 16:00 | N | N | investigate 38s 138kV bus differential trip | Line, Shunts, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2015-11-29 08:00 | 2015-11-29 16:00 | N | N | fall substation washing, wash 138-32.83-1, switch maintenance | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2015-11-29 08:00 | 2015-11-29 14:00 | N | Y | fall substation washing | Line |  |  | Pre-Condition, Overload, Restricts Generation
ALTALINK | 21S Marion,767AL (21s Marion - 767L tap) | 2015-11-29 08:30 | 2015-11-29 17:30 | N | N | remove mobile 475s from 21s & close open points 'A' & 'B' | Line, Station
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2015-11-29 14:00 | 2015-11-29 18:00 | N | Y | fall substation washing | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72NW15 (Namao - Woodcroft) | 2015-11-30 07:00 | 2015-12-14 17:00 | N | N | line upgrades | Line |  |  | For Information Only
EPCOR | Hardisty T2 (Hardisty) | 2015-11-30 07:00 | 2015-12-11 18:00 | N | N | commission protection | Transformer |  |  | For Information Only
ALTALINK | 320p 2852 (320p Keephills) | 2015-11-30 08:00 | 2015-12-03 16:00 | N | Y | migrate SCADA from old to new systems | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2015-11-30 08:00 | 2015-12-04 16:00 | N | N | CT ratio change and SEL relay settings | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22) | 2015-11-30 08:00 | 2015-12-04 16:00 | N | N | PRD install | Transformer |  |  | For Information Only
ALTALINK | 322s T1 (322s Cowley Ridge) | 2015-11-30 08:00 | 2015-12-01 17:00 | N | Y | install new relay | Transformer |  |  | Restricts Generation
ENMAX | 3.82L (ENMAX 3 - ENMAX 8),ENMAX 3 B138-3.82 (ENMAX 3) | 2015-11-30 08:00 | 2015-12-02 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | Heater retrofit. O Ring Replacement at 3s. Repair oil leak in manhole | Firm Load Loss, Creates Radial Feeds
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2015-11-30 13:00 | 2015-12-01 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 845s 708 (845s Big Mountain) | 2015-11-30 17:30 | 2015-12-02 16:00 | N | N | forced outage post 7L33 return | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2015-12-01 07:30 | 2015-12-19 17:30 | N | N | line rebuild - conductor stringing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 727L (678s Okotoks - 727L39N),142s C1 (142s Magcan) | 2015-12-01 08:00 | 2015-12-15 17:00 | N | N | Foothills 138kV projects: complete the rebuild portion of 727L | Line, Shunts |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
VISIONREQ | 354S Summerview | 2015-12-01 08:00 | 2015-12-31 16:00 | N | N | verify remote operation of breakers & check relay mapping | Station |  |  | For Information Only
ENMAX | 26.2TR (ENMAX 26) | 2015-12-01 08:00 | 2015-12-01 16:00 | N | N | DGA, RTN and transformer maintenance | Transformer
ALTALINK | 310p 2652 (310p Sundance) | 2015-12-01 09:00 | 2015-12-01 17:00 | N | Y | verify the A/R settings - emergency work | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 32s8 (32s Barrier) | 2015-12-01 09:00 | 2015-12-01 16:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 678s T1 (678s Okotoks) | 2015-12-01 09:00 | 2015-12-01 17:00 | N | N | Fortis request to change over current protection settings | Transformer
ALTALINK | 263s T1 (263s Strachan) | 2015-12-01 13:00 | 2015-12-01 17:00 | N | N | connect new transfer switch to existing station load, close OP 'H' | Transformer
ALTALINK | 263s T1 (263s Strachan) | 2015-12-01 17:01 | 2015-12-07 17:00 | N | N | close open points A & B, replace SS1, replace 263s3 with new MOS switch | Transformer
CMH, Medicine Hat | MH69s6 MH69_604 (MH69s6 Riverview),MH69s6 MH69_607 (MH69s6 Riverview),MH69s6 MH69_616 (MH69s6 Riverview),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2015-12-02 07:00 | 2015-12-02 16:00 | N | N | install ground connection points on breaker | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 763L (28s West Brooks - 763L257A) | 2015-12-02 08:00 | 2015-12-02 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20) | 2015-12-02 08:00 | 2015-12-02 16:00 | N | N | repair temperature alarm sensor | Transformer
ALTALINK | 924L (102s Langdon - 356s Milo) | 2015-12-02 08:00 | 2015-12-02 18:00 | N | Y | trip 924L to confirm WATL HVDC runback | Line |  |  | 240 kV
ALTALINK | 33s6 (33s Spray) | 2015-12-02 09:00 | 2015-12-02 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 508S Lakesend,696L (508s Lakesend - 892s Ribstone Creek) | 2015-12-03 06:00 | 2015-12-03 12:00 | N | N | customer work | Station, Line |  |  | For Information Only
CMH, Medicine Hat | MH69s6 MH69_608 (MH69s6 Riverview),MH69s6 MH69_611 (MH69s6 Riverview),MH69s6 MH69_614 (MH69s6 Riverview),MH69s6 MH69_616 (MH69s6 Riverview),20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2015-12-03 07:00 | 2015-12-03 16:00 | N | N | install grounding connection points on breakers | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 12.1TR (ENMAX 12) | 2015-12-03 08:00 | 2015-12-03 12:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 763L (158s Vauxhall - 763L259) | 2015-12-03 08:00 | 2015-12-03 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 12L85 (12s Heartland - 2029s Heathfield) | 2015-12-03 08:00 | 2015-12-04 16:00 | N | Y | tele-protection fiber testing, 87L-21A/12L85 and 87L-21B/12L85 relays | Line |  |  | 500 kV
ALTALINK | 251s 252 (251s Whitla) | 2015-12-03 10:00 | 2015-12-03 14:00 | N | N | urgent repair | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2015-12-04 07:30 | 2015-12-04 16:00 | N | Y | high load move | Line |  | High Load Move | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 935L (324s Cassils - 356s Milo) | 2015-12-05 07:00 | 2015-12-06 17:00 | N | Y | EATL interface: function line airbreaks and connect CT wires to RAS relays for 935L | Line |  |  | 240 kV
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198),613L (396s Pincher Creek - 103s Goose Lake) | 2015-12-05 08:00 | 2015-12-05 17:00 | N | Y | cross arm replacement, urgent conductor repairs, & breaker maintenance | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2015-12-05 08:00 | 2015-12-05 16:00 | N | N | repair SW 86 at 32 sub | Line, Transformer | 1. Studied with wind generation = 1125 MW, CEC = 0 MW, Carseland = 0 MW, Cavalier = 120 MW (refer to Internal Comments 1 - 4). 1. Lower wind generation may alleviate amount of overload on 24.81L for next contingency. 2. Higher CEC generation may alleviate amount of overload on 24.81L for next contingency. 3. Higher Carseland generation may increase amount of overload on 24.81L for next contingency. 4. Lower Cavalier may alleviate amount of overload on 24.81L for next contingency. |  | Firm Load Loss, Creates Radial Feeds
FORTIS | Bull Creek Wind Power | 2015-12-05 08:00 | 2015-12-13 16:00 | N | N | In service date: Dec. 6, 2015 (29.155 MW) | Unit
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2015-12-06 | 2015-12-07 06:00 | N | N | transfer NAMAO S/S from 72CN10 to 72VN21 | Line |  |  | For Information Only
ALTALINK | 179s T1 (179s Gleichen) | 2015-12-06 00:01 | 2015-12-06 06:00 | N | N | repair transformer leak | Transformer |  |  | For Information Only
EPCOR | 657s Summerside T2 (657s Summerside) | 2015-12-07 07:00 | 2015-12-11 18:00 | N | Y | bushing monitors | Transformer |  |  | 240 kV, For Information Only
EPCOR | Woodcroft T3 (Woodcroft) | 2015-12-07 07:00 | 2015-12-11 18:00 | N | N | install PRD | Transformer |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper) | 2015-12-07 07:00 | 2015-12-11 18:00 | N | Y | tapchanger maint | Transformer |  |  | 240 kV, For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2015-12-07 08:00 | 2015-12-14 16:00 | N | N | bus outage to replace SW 1 | Transformer |  |  | For Information Only
ENMAX | 2.81L (ENMAX 2 - ENMAX 9),ENMAX 9 B138-2.81 (ENMAX 9) | 2015-12-07 08:00 | 2015-12-11 16:00 | N | N | heater retrofit, structure #30 straightening | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2015-12-07 08:00 | 2015-12-08 12:00 | N | N | relocate ENMAX 21 DFR | Transformer |  |  | For Information Only
ALTALINK | 526L (268s Whitecourt - 526DL185),268s 69 (268s Whitecourt) | 2015-12-07 08:00 | 2015-12-11 17:00 | N | N | complete protection replacement and battery bank installation | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2015-12-07 08:00 | 2015-12-07 12:00 | N | N | relocation of ENMAX 21 DFR | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p T1 (320p Keephills) | 2015-12-07 08:00 | 2015-12-11 12:00 | N | Y | migrate SCADA from old to new systems | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2015-12-07 08:00 | 2015-12-07 12:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 38.2TR (ENMAX 38) | 2015-12-07 08:00 | 2015-12-07 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2015-12-07 08:00 | 2015-12-18 16:00 | N | Y | replace spacer dampers | Line |  |  | 240 kV, Over/Under Voltage
ENMAX, ALTALINK | ENMAX 65 B240-D132 (ENMAX 65),ENMAX 65 B240-D131 (ENMAX 65),1080L (ENMAX 65 - ENMAX 25),ENMAX 25 B240-D138 (ENMAX 25),ENMAX 25 B240-D139 (ENMAX 25) | 2015-12-07 08:00 | 2015-12-11 16:00 | N | Y | test & commission single pole reclosing | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 92s T1 (92s Viscount) | 2015-12-07 08:00 | 2015-12-07 17:00 | N | N | add supervisory controls to tap changer | Transformer |  |  | For Information Only
ALTALINK | 58s C1 (58s Edson),58s T2 (58s Edson),671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale),58s Edson 138kV West Bus,58s9 (58s Edson) | 2015-12-07 09:00 | 2015-12-07 15:00 | N | N | replacing west bus protections & function testing breakers | Line, Transformer, Shunts, Bus, Switch |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2015-12-07 12:00 | 2015-12-07 16:00 | N | N | 21s DFR relocate (unshort CT cct) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s9 (58s Edson) | 2015-12-07 15:00 | 2015-12-08 09:00 | N | N | required during protection upgrades | Switch |  | this switch needs to be left open until the upgrade has been completed on Dec 8th, 2015 | Pre-Condition
EPCOR | 987s T1 (987s Clover Bar) | 2015-12-08 07:00 | 2015-12-08 18:00 | N | Y | investigate oil leak | Transformer |  |  | 240 kV, Creates Radial Feeds
ENMAX | 34.1TR (ENMAX 34) | 2015-12-08 08:00 | 2015-12-08 12:00 | N | N | DGA, RTN and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2015-12-08 08:00 | 2015-12-08 16:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 250p11 (250p Bighorn) | 2015-12-08 08:00 | 2015-12-08 19:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 263s C1 (263s Strachan),263s T1 (263s Strachan),718L (250p Bighorn Plant - 263s Strachan),870L (262s Rocky Mountain House - 263s Strachan) | 2015-12-08 08:00 | 2015-12-08 16:00 | N | Y | urgent replacement of 138kV PT (263s25) | Line, Shunts, Transformer |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2015-12-08 09:00 | 2015-12-08 11:00 | N | N | replace 138kV bus protection-cutover current contribution and functional test breaker | Line |  |  | Pre-Condition
ALTALINK | 58s T1 (58s Edson) | 2015-12-08 09:00 | 2015-12-08 15:00 | N | N | replace East bus protections and East SS transformer & function testing breakers | Transformer |  |  | Pre-Condition
ALTALINK | 740L (58s Edson - 39s Bickerdike) | 2015-12-08 11:00 | 2015-12-08 13:00 | N | N | replace 138kV bus protection-cutover current contribution and functional test breaker | Line |  |  | Pre-Condition
ENMAX | 21.2TR (ENMAX 21) | 2015-12-08 12:00 | 2015-12-08 16:00 | N | N | relay maintenance transformer differential | Transformer |  |  | For Information Only
ENMAX | 34.4TR (ENMAX 34) | 2015-12-08 12:01 | 2015-12-08 16:00 | N | N | DGA, RTN and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2015-12-09 07:00 | 2015-12-10 16:00 | N | Y | high priority move 347s7 PT to new support structure & footing | Line |  |  | Over/Under Voltage, Restricts Generation, Creates Radial Feeds
ATCO | 848s 901T (848s Ruth Lake) | 2015-12-09 08:00 | 2015-12-10 17:00 | N | Y | emergency repairs | Transformer |  |  | 240 kV
ALTALINK | 3L (245s Seebe - 3L145) | 2015-12-09 08:00 | 2015-12-09 17:00 | N | N | create Open Point 'A' and 3L145 switch maintenance | Line | 8:00  10:00 Create Open Point 'A' (proximity required GOI) 10:00  15:00 138kV switch maintenance (3L145) 15:00  17:00 Close Open Point 'A' (proximity required GOI) |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2015-12-10 02:00 | 2015-12-10 04:00 | N | Y | 21s DFR relocate (unshort CT cct) | Line |  |  | For Information Only
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2015-12-10 04:00 | 2015-12-10 06:00 | N | N | 21s DFR relocate (unshort CT cct) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 2152 (320p Keephills) | 2015-12-10 08:00 | 2015-12-10 09:30 | N | Y | trip testing from 320p T1 protection | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 180s T2 (180s Cope Creek) | 2015-12-10 08:00 | 2015-12-10 17:00 | N | N | repair transformer oil leaks | Transformer |  |  | For Information Only
ALTALINK | 3L (272s Springbank - 3L147) | 2015-12-10 08:00 | 2015-12-10 17:00 | N | N | create open point 'A' (proximity required GOI) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 352 (320p Keephills) | 2015-12-10 10:00 | 2015-12-10 11:30 | N | Y | trip testing from 320p T1 protection | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2015-12-10 10:00 | 2015-12-10 12:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 320p 752 (320p Keephills) | 2015-12-10 12:30 | 2015-12-10 14:00 | N | Y | trip testing from 320p T1 protection | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2015-12-10 16:00 | 2015-12-10 18:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24),ENMAX 24 B138-24.83 (ENMAX 24) | 2015-12-11 08:00 | 2015-12-21 16:00 | N | Y | transmission relocation | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2015-12-11 08:00 | 2015-12-11 10:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2015-12-11 14:00 | 2015-12-11 16:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 646L (678s Okotoks - 237s Foothills) | 2015-12-12 08:00 | 2015-12-16 16:00 | N | N | In service date: Dec 15, 2015 | Line
EPCOR | E511s VictoriaT3 (511s Victoria) | 2015-12-14 07:00 | 2015-12-14 18:00 | N | N | replace oil filter | Transformer |  |  | For Information Only
ALTALINK | 727L (74s Janet - 1140s Temp),727L (678s Okotoks - 1140s Temp) | 2015-12-14 07:00 | 2015-12-18 18:00 | N | N | remove 727L from 1140s and 678s and salvage 1140s | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds, Impacts RAS
EPCOR | 72RS5 (Rossdale - Strathcona) | 2015-12-14 07:00 | 2015-12-14 19:00 | N | N | emergency repair of leaking pothead | Line |  |  | For Information Only
ENMAX | 7.84L (ENMAX 36 - ENMAX 7),ENMAX 7 B138-7.84 (ENMAX 7) | 2015-12-14 08:00 | 2015-12-18 16:00 | N | N | heater retrofit and Doble ENMAX 7 B138-7.84 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 1109L (ENMAX 65 - ENMAX 25),ENMAX 65 B240-D135 (ENMAX 65),ENMAX 65 B240-D134 (ENMAX 65),ENMAX 25 B240-D141 (ENMAX 25),ENMAX 25 B240-D142 (ENMAX 25) | 2015-12-14 08:00 | 2015-12-18 16:00 | N | Y | test & commission single pole reclosing | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 27.1TR (ENMAX 27) | 2015-12-14 08:00 | 2015-12-14 11:00 | N | N | RTU replacement and test relays | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2015-12-14 08:00 | 2015-12-15 16:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 1038L (138s Windy Flats - 266s Foothills),266s 1038L FSC (266s SC1) | 2015-12-14 08:00 | 2015-12-15 18:00 | N | Y | repair 266s489 and faulty wiring on FSC2 | Line, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2015-12-14 08:00 | 2015-12-21 08:00 | N | N | replace 3 structures | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2015-12-14 08:00 | 2015-12-17 17:00 | N | N | deficiency clean-up/Inspection | Line |  |  | 500 kV
ENMAX | 27.2TR (ENMAX 27) | 2015-12-14 11:01 | 2015-12-14 13:00 | N | N | RTU replacement and test relays | Transformer |  |  | For Information Only
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2015-12-15 07:00 | 2015-12-15 19:00 | N | N | customer request | Transformer |  |  | For Information Only
ALTALINK | 296s T1 (296s Rosyth) | 2015-12-15 07:00 | 2015-12-15 19:00 | N | N | customer request for isolation | Transformer |  |  | For Information Only
EPCOR | E511s VictoriaT4 (511s Victoria) | 2015-12-15 07:00 | 2015-12-15 18:00 | N | N | tap changer maintenance | Transformer |  |  | For Information Only
ALTALINK | 296s T3 (296s Rosyth) | 2015-12-15 07:00 | 2015-12-15 19:00 | N | N | Enbridge outage request to enable repairs to 296s28 (410-BUS- 3-IS) | Transformer |  |  | For Information Only
ALTALINK | 883L (288s Wolf Creek - 429s Nelson Lake) | 2015-12-15 07:30 | 2015-12-17 18:00 | N | N | replace structure for road widening | Line |  |  | Pre-Condition
ALTALINK, TRANSALTA | 255s Vulcan RTU/SCADA,179s Gleichen RTU/SCADA | 2015-12-15 08:00 | 2015-12-15 17:00 | N | N | repair an intermittent radio link between 255s and 9282R | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 183s T1 (183s Underwood) | 2015-12-15 08:00 | 2015-12-15 19:00 | N | N | fix bleeder leaks on 25 kV bushing turrets | Transformer |  |  | For Information Only
ENMAX | 54.1TR (ENMAX 54) | 2015-12-15 08:00 | 2015-12-15 16:00 | N | N | verify device 90 PT connected to A phase | Transformer |  |  | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2015-12-15 08:00 | 2015-12-15 16:30 | N | Y | repair pole brace | Line |  |  | 240 kV, Limits ATC
ATCO | 752s 701T (752s Albright&Wilson) | 2015-12-16 08:00 | 2015-12-16 17:00 | N | N | outage to commission new relay trips and remove an external CT | Transformer |  | Outage to commission new relay trips and remove an external CT. Total Substation Outage. ERCO has chosen Dec 16 for the outage. | For Information Only
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1) | 2015-12-16 08:00 | 2015-12-17 18:00 | N | Y | repair faulty wiring on FSC2 | Line, Shunts |  |  | 240 kV
ENMAX | 10.2TR (ENMAX 10) | 2015-12-16 08:00 | 2015-12-18 16:00 | N | N | LTC low oil alarm | Transformer |  |  | For Information Only
ALTALINK | 818s C2 (818s Winefred),818s 17 (818s Winefred) | 2015-12-16 08:00 | 2015-12-16 17:00 | N | N | repair failed tank heaters | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 418L (281s Johnson - 418L194A) | 2015-12-16 08:00 | 2015-12-16 17:00 | N | N | create Open Point 'A' and Switch Maintenance (418L194A) | Line | 8:00  10:00 Create Open Point 'A' (proximity required GOI) 10:00  15:00 138kV Switch Maintenance (418L194A) 15:00  17:00 Close Open Point 'A' (proximity required GOI) |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (432s Carvel - 739L214B),432s 739 (432s Carvel) | 2015-12-16 08:30 | 2015-12-16 12:00 | N | N | removing gas since breaker is over pressured | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 410s T1 (410s Josephburg),410s Josephburg 138kV Bus 1 | 2015-12-16 08:30 | 2015-12-16 17:00 | N | Y | repair leaks on SST2 | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 251s 252 (251s Whitla) | 2015-12-16 09:00 | 2015-12-16 17:00 | N | Y | low gas repairs on 240kV breaker | Circuit Breaker |  |  | 240 kV
BLACKSPRING | 485s DVAR1 (485s Blacksprings) | 2015-12-16 09:00 | 2015-12-17 17:00 | N | N | maintenance | Shunts
ATCO | 959S SVC (959s Lanfine) | 2015-12-16 16:21 | 2015-12-21 17:00 | N | N | forced outage | Shunts |  |  | 240 kV, Limits Ratings, Prevents Normal Events
ALTALINK | 62s12 (62s Brazeau) | 2015-12-16 23:00 | 2015-12-17 04:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 237s T2 (237s Foothills),237s Foothills 240kV Bus 2 | 2015-12-17 08:00 | 2015-12-17 17:00 | N | Y | Foothills: Adjust switch 237s1089 | Transformer, Bus |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 183s T2 (183s Underwood) | 2015-12-17 08:00 | 2015-12-18 19:00 | N | N | fix CT junction box leaks | Transformer |  |  | For Information Only
ALTALINK | 727L (65s High River - 727L39S),727L (678s Okotoks - 727L39N) | 2015-12-17 08:00 | 2015-12-18 16:00 | N | N | reconfigured 727L. In service date: Dec 18, 2015 | Line
ALTALINK | 258s 652 (258s Dow Hydrocarbons) | 2015-12-17 14:00 | 2015-12-17 16:00 | N | N | topping up gas | Circuit Breaker |  |  | For Information Only
CENOVUS | 1200S Foster Creek Station | 2015-12-18 08:00 | 2015-12-18 16:00 | N | N | 1200SST2 will be out of service | Station |  | Please note field crews have requested a portion of the 500kV bus open between 1214A, 1215B, and 1200SST1 @ 2029s on Dec 18 8-16:00 to repair corona bells on 1214B and 1215A. As a result 1200SST2 will be OOS. 2029s AC station service will be fed from 1200SST1. | For Information Only
ATCO | 7L137 (770s Three Hills - 768s Rowley) | 2015-12-18 08:00 | 2015-12-18 12:00 | N | N | emergency repair of a broken shield wire | Line |  |  | Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L224 (774s Monitor - 650s Hansman Lake) | 2015-12-18 10:00 | 2015-12-18 18:00 | N | Y | emergency repair of a broken shield wire | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Hardisty T2 (Hardisty) | 2015-12-18 18:00 | 2015-12-19 06:00 | N | N | bus 2 -3 separation | Transformer |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2015-12-19 07:30 | 2015-12-19 16:00 | Y | Y | urgent conductor repair | Line |  | Emergency Line Maintenance | Pre-Condition, Limits ATC, 500 kV
ENMAX | 23.4TR (ENMAX 23) | 2015-12-20 08:00 | 2015-12-20 12:00 | N | N | SR760 relay replacement | Transformer |  |  | For Information Only
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2015-12-20 12:00 | 2015-12-20 16:00 | N | N | SR760 relay replacement | Transformer, Line |  |  | Pre-Condition
ENMAX | 5.7TR (ENMAX 5) | 2015-12-21 08:00 | 2015-12-21 16:00 | N | N | gas relay testing | Transformer |  |  | For Information Only
ENMAX | 5.1TR (ENMAX 5) | 2015-12-21 08:00 | 2015-12-21 16:00 | N | N | due to a low oil alarm | Transformer |  |  | For Information Only
BCH | 1L275 (799s Coleman - Natal) | 2015-12-21 09:00 | 2015-12-22 16:00 | N | Y | repair failed tank heater - BC maintenance does not affect AB ATC | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ENMAX, ALTALINK | ENMAX 23,2.80L (ENMAX 2 - ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2015-12-22 04:00 | 2015-12-22 06:00 | N | N | station outage is required to isolate 23.4TR MD | Line, Station |  |  | Firm Load Loss
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2015-12-22 06:01 | 2015-12-22 14:00 | N | N | urgent outage on 23.80L & 23.4TR to investigate/repair 23.4TR MD | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.2TR (ENMAX 37) | 2015-12-22 08:00 | 2015-12-22 16:00 | N | N | SR760 relay replacement | Transformer |  |  | For Information Only
ENMAX | 39.4TR (ENMAX 39) | 2015-12-22 08:00 | 2015-12-22 16:00 | N | N | DGA, run through neutral and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 288s Wolf Creek 240kV Bus 2 | 2015-12-22 10:00 | 2015-12-22 10:15 | N | N | energizing T2 | Bus |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 288s Wolf Creek 138kV Bus 2 | 2015-12-23 10:00 | 2015-12-23 10:15 | N | N | loading 288s T2 | Bus |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (Line Creek - Natal) | 2015-12-28 09:00 | 2015-12-29 17:00 | N | Y | replace failed tank heater on NTL 1CB1 | Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 919L (310p Sundance - 77s Sagitawah),77s 48 (77s Sagitawah),77s 14 (77s Sagitawah) | 2015-12-30 09:00 | 2015-12-30 15:00 | N | Y | replacing bus connector to repair hotspot on 77s919X bus connection | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
TRANSALTA | 179s Gleichen RTU/SCADA | 2015-12-30 09:00 | 2015-12-30 17:00 | N | N | add surge protection to the RTU | Terminal Equipment |  |  | Affects Visibility
ENMAX | 10.2TR (ENMAX 10),693L (42s Sarcee - ENMAX 10),ENMAX 10 B138-693 (ENMAX 10) | 2016-01-04 08:00 | 2016-01-08 16:00 | N | Y | heater retrofit, HV SW/MD maintenance, 10.2TR MD | Transformer, Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2016-01-04 08:00 | 2016-01-25 08:00 | N | Y | replace spacer dampers | Line |  |  | 240 kV, Over/Under Voltage
ENMAX | 1.8TR (ENMAX 1) | 2016-01-04 08:00 | 2016-01-04 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ENMAX | 21.2TR (ENMAX 21) | 2016-01-04 12:00 | 2016-01-05 16:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2016-01-05 07:00 | 2016-01-18 17:30 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin) | 2016-01-05 07:00 | 2016-01-05 12:00 | N | N | close open point between 804L and 810L2 after replacement | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 285s T2 (285s East Camrose) | 2016-01-05 08:00 | 2016-01-05 17:00 | N | N | replace breather and inpsect | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 32.1TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2016-01-05 08:00 | 2016-01-05 16:00 | N | N | repair 32MD138-32.1TR and maintain SW31 | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2016-01-05 12:30 | 2016-01-05 17:30 | N | N | close open point between 804L and 810L2 after replacement. | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2016-01-06 08:00 | 2016-01-06 18:00 | N | N | replace pole # 34 - H frame pole of 7L66 | Line |  | Replace Pole # 34 - H Frame pole of 7L66 | Pre-Condition, Overload, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2016-01-06 08:00 | 2016-01-06 16:00 | N | N | maintenance SW32 at 8kV bus | Transformer |  |  | For Information Only
ALTALINK | 80L (63s Red Deer - 214s Innisfail),63s 80X (63s Red Deer) | 2016-01-06 09:00 | 2016-01-06 17:00 | N | N | top up the breaker with oil | Line, Circuit Breaker |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 281s Johnson RTU/SCADA | 2016-01-06 09:00 | 2016-01-06 17:00 | N | N | techs will require an approx 1 Hour supervisory outage @ 281s. This is to repair an intermittent IED alarm at the ACC. | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare),790s 703 (790s Poplar Hill) | 2016-01-06 09:30 | 2016-01-06 16:00 | N | N | breaker gas top-up | Line, Circuit Breaker |  | low SF6 gas alarms on 703 at 790s Poplar Hill | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 263s Strachan RTU/SCADA | 2016-01-07 08:00 | 2016-01-07 18:00 | N | N | techs will be removing 263s RTU from service for deficiency cleanup and remote access testing. There will be intermittent loss of visibility & control during the course of this work. | Terminal Equipment |  |  | Affects Visibility
ENMAX | 11.4TR (ENMAX 11) | 2016-01-07 08:00 | 2016-01-07 16:00 | N | N | top up low oil in LTC | Transformer |  |  | For Information Only
ENMAX | 5.1TR (ENMAX 5) | 2016-01-07 08:00 | 2016-01-07 16:00 | N | N | low oil alarm - top up required | Transformer |  |  | For Information Only
ATCO, ALTALINK | 923L (2075s Newell - 356s Milo) | 2016-01-08 07:00 | 2016-01-16 12:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2016-01-08 08:00 | 2016-01-14 17:30 | N | Y | replace insulators and arms on various structures | Line |  |  | Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2016-01-08 12:00 | 2016-01-08 16:00 | N | Y | top up tap changer conservator | Transformer |  |  | 240 kV
ENMAX | 38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2016-01-09 08:00 | 2016-01-09 16:00 | N | N | switch & MD matinance | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2016-01-10 00:07 | 2016-01-13 16:00 | N | Y | forced outage due to 2sT1 trip | Line |  |  | Restricts Generation
ALTALINK | 253s C1 (253s Blackie),161L (255s Vulcan - 253s Blackie),753L (65s High River - 253s Blackie),851L (525s Carseland - 253s Blackie),253s 753W (253s Blackie),253s 851W (253s Blackie),253S Blackie 138 kV bus | 2016-01-11 07:00 | 2016-01-13 18:00 | N | N | removal of 253s99, remove old 852L OHSW going into 253s and install new OHSW for 161L | Bus, Shunts, Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 102s SVC (102s Langdon) | 2016-01-11 07:30 | 2016-01-12 12:20 | N | Y | replace CVTs (VT28) | Shunts |  |  | 240 kV
ALTALINK | 17s 4 (17s Benalto) | 2016-01-11 08:00 | 2016-01-21 17:00 | N | Y | 240kV breaker replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1107L (ENMAX 65 - 237s Foothills) | 2016-01-11 08:00 | 2016-01-16 17:00 | N | Y | damper inspection | Line |  |  | 240 kV, Pre-Condition
ENMAX | 43.1TR (ENMAX 43),9.83L (ENMAX 43 - ENMAX 9) | 2016-01-11 08:00 | 2016-01-12 16:00 | N | N | maintenance | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 320p 3152 (320p Keephills) | 2016-01-11 08:00 | 2016-01-12 16:00 | N | Y | migrate SCADA from old to new systems | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ATCO | 7L121 (917s Horse River-7L121D2) | 2016-01-11 12:00 | 2016-01-14 17:00 | N | N | climbing inspection | Line |  | 2015 Climbing Inspection | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2016-01-12 07:00 | 2016-01-12 12:00 | N | Y | create open point A on 74s 240 kV B2 bus | Transformer, Bus, Shunts |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 812S Norcen,7L63 (783s Cadotte River - 812s Norcen) | 2016-01-12 07:00 | 2016-02-01 17:30 | N | N | station outage, bus upgrade | Station, Line |  | Complete station outage, 701T replacement, 25 KV bus upgrade, move 700PT1. All Station load transferred onto 902s mobile sub, 783s Cadot Rv and 902s mobile radial fed from 788S, Harvest DG will be offline. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 54L (118s Canmore - 54L172),118s 54W (118s Canmore) | 2016-01-12 08:00 | 2016-01-14 17:00 | N | N | replace 138kV CT's between 118s54W and 118s1 | Circuit Breaker, Line | Studied with BOW = 180 MW and no concerns. |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 616L (103s Goose Lake - 616AL tap),103s 1452 (103s Goose Lake),103s 1552 (103s Goose Lake) | 2016-01-12 09:00 | 2016-01-13 12:00 | N | N | removal of 616L protections | Circuit Breaker, Line | Studied with southwest wind generation = 546 MW. |  | Pre-Condition, Over/Under Voltage
ATCO | 9L100 (801s Anderson - 807s Sheerness) | 2016-01-13 07:00 | 2016-01-13 19:00 | N | Y | high load move | Line |  |  | 240 kV, Restricts Generation
ALTALINK | 320p 3052 (320p Keephills) | 2016-01-13 08:00 | 2016-01-15 12:00 | N | Y | migrate SCADA from old to new systems | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, 500 kV
ALTALINK | 74s T1 (74s Janet),929L (63s Red Deer - 74s Janet),932L (74s Janet - 162s Beddington),74s Janet 240kV Bus 1 | 2016-01-13 08:00 | 2016-01-14 17:00 | N | Y | replace string insulators at 74s19, 932L and 929L | Bus, Transformer, Line |  |  | 240 kV, Overload
ALTALINK | 739L (432s Carvel - 739L214B),432s 739 (432s Carvel) | 2016-01-13 09:00 | 2016-01-13 12:00 | N | N | removing gas from breaker | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2016-01-13 09:00 | 2016-01-13 16:00 | N | Y | fix construction deficiencies | Line |  | Construction deficiencies, Station requested in block mode, EATL unavailable for transfer, no permit issuance | For Information Only, 500 kV
ATCO | 2029s 1205 (2029s Heathfield) | 2016-01-13 09:30 | 2016-01-13 11:30 | N | Y | update sync check relay software | Circuit Breaker |  |  | For Information Only, 500 kV
ATCO | 2029s 1206 (2029s Heathfield) | 2016-01-13 11:30 | 2016-01-13 13:30 | N | Y | update sync check relay software | Circuit Breaker |  |  | For Information Only, 500 kV
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2016-01-14 07:00 | 2016-01-14 19:00 | N | N | Construction work in Suncor's substation | Transformer |  |  | For Information Only
IMPERIALOIL | 7L161 (909s Mahno - 942s Nabiye) | 2016-01-14 08:00 | 2016-01-14 18:00 | N | Y | partial discharge testing on 144 kV cable | Line |  |  | For Information Only
ALTALINK | 528s TDVAR1 (528s Blue Trail Wind Farm),528s TDVAR2 (528s Blue Trail Wind Farm),528s TDVAR3 (528s Blue Trail Wind Farm) | 2016-01-14 09:00 | 2016-01-14 12:00 | N | N | remove 1 capacitor switcher | Transformer |  |  | For Information Only
TRANSALTAW | 418s Ardenville DVAr | 2016-01-14 12:00 | 2016-01-14 16:00 | N | N | remove 1 capacitor switcher | Shunts |  |  | For Information Only
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2016-01-14 16:00 | 2016-01-18 18:30 | N | N | cooling pump issue | Line |  |  | 500 kV
ALTALINK | 320p 2952 (320p Keephills) | 2016-01-14 17:00 | 2016-01-15 12:00 | N | Y | 320p2952 switch repair | Circuit Breaker |  |  | Restricts Generation, 500 kV
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s T2 (74s Janet),74s Janet 240kV Bus 2 | 2016-01-15 07:00 | 2016-01-15 12:00 | N | Y | close open point A on 74s 240 kV B2 bus | Bus, Transformer, Shunts |  |  | 240 kV, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 526L (526L220 - 526L365) | 2016-01-15 09:00 | 2016-02-26 07:00 | N | N | rebuild section between A/B 526L220 and A/B 526L365 | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 426L (194s South Red Deer - 63s Red Deer) | 2016-01-15 10:00 | 2016-02-09 10:00 | N | N | pull and install 426L underground cables | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2016-01-16 08:00 | 2016-01-17 16:00 | N | Y | HV SW/MD maintenance | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 935L (324s Cassils - 356s Milo) | 2016-01-16 13:00 | 2016-01-25 18:00 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition
ATCO | 2075s ACF14 (2075s Newell) | 2016-01-17 08:00 | 2016-01-18 16:00 | N | Y | change out CT due to minor leak | Shunts |  | change out a CT, once this outage starts it will be unavailable until the fix is complete, 106MVAR cap bank unavailable for dispatch | 240 kV
ENMAX | ENMAX 1 B138-6A0 (ENMAX 1) | 2016-01-17 08:00 | 2016-02-06 16:00 | N | N | GIS breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 767L (320p Keephills - 767L167A),320p 767N (320p Keephills) | 2016-01-18 08:00 | 2016-01-29 17:00 | N | N | replace breaker 320p809X due to proximity and access | Line, Circuit Breaker |  |  | For Information Only
EPCOR, ALTALINK | 320p 809X (320p Keephills),809L (320p Keephills - 510s Sunnybrook) | 2016-01-18 08:00 | 2016-01-29 17:00 | N | N | replace breaker | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 1106L (ENMAX 65 - 237s Foothills) | 2016-01-18 08:00 | 2016-01-23 17:00 | N | Y | NFTP: damper inspection | Line |  |  | 240 kV, Pre-Condition
ENMAX | 43.2TR (ENMAX 43),33.84L (ENMAX 43 - ENMAX 33) | 2016-01-18 08:00 | 2016-01-19 16:00 | N | N | switch maintenace SW 84, 85, 86, 43.2TR MD | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 8.5TR (ENMAX 8) | 2016-01-18 08:00 | 2016-01-22 16:00 | N | N | urgent repair cooling fan | Transformer |  |  | For Information Only
ENMAX | 2.80L (ENMAX 2 - ENMAX 23),ENMAX 23 B138-2.80 (ENMAX 23) | 2016-01-18 08:00 | 2016-01-20 14:08 | N | N | heater retrofit (replace with proper heaters) | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 2952 (320p Keephills) | 2016-01-18 08:00 | 2016-01-19 16:00 | N | Y | migrate SCADA from old to new systems | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ENMAX | 40.1TR (ENMAX 40) | 2016-01-18 08:00 | 2016-01-19 16:00 | N | N | RTU annunciator panel replacement | Transformer |  |  | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2016-01-18 08:00 | 2016-01-18 16:00 | N | N | replace current transducer for 34 Sub end | Line |  |  | Creates Radial Feeds
ATCO | 7L121 (833s Mariana - 860s Crow) | 2016-01-18 12:00 | 2016-01-21 17:00 | N | N | climbing inspection | Line |  | 2015 Climbing Inspection | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2016-01-19 07:00 | 2016-01-19 17:00 | N | Y | install bird cover | Shunts, Circuit Breaker |  |  | 240 kV
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome) | 2016-01-19 08:00 | 2016-01-19 15:00 | N | N | as per Epcor: repair hot connection | Line
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2016-01-19 08:00 | 2016-01-20 16:00 | N | N | investigate control circuit anomalies | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 2075s SVC2 (2075s Newell) | 2016-01-19 08:00 | 2016-01-21 16:00 | N | Y | installing bird mitigation on 21kV outdoor equipment and adjusting the infrared cameras in the valve hall | Shunts |  |  | 240 kV, For Information Only
ALTALINK, EPCOR | 665s TX2 (665s Dome),909L (320p Keephills - 665s Dome) | 2016-01-19 08:00 | 2016-01-19 15:00 | N | Y | repair hot connection at DDS4 | Line, Transformer |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C4 (74s Janet),74s 103 (74s Janet) | 2016-01-20 07:00 | 2016-01-20 17:00 | N | Y | install bird cover | Circuit Breaker, Shunts |  |  | 240 kV
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2016-01-20 08:00 | 2016-01-21 16:00 | N | Y | HV SW/MD maintenance | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 320p 1352 (320p Keephills),909L (320p Keephills - 665s Dome) | 2016-01-20 08:00 | 2016-01-20 09:30 | N | Y | Keephills trip testing from 320p T1 A protection | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 40.2TR (ENMAX 40) | 2016-01-20 08:00 | 2016-01-21 16:00 | N | N | RTU annunciator panel replacement | Transformer
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28) | 2016-01-20 08:00 | 2016-01-21 16:00 | N | N | ENMAX maintenance | Line
TRANSALTA | 59s T1 (59s Peigan) | 2016-01-20 09:00 | 2016-01-21 16:00 | N | Y | removal of T1 RAS protections | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 31.3TR (ENMAX 31) | 2016-01-20 12:00 | 2016-01-20 16:00 | N | N | isolate and ground transformer for training purposes | Transformer
ALTALINK | 17s C1 (17s Benalto),17s 9 (17s Benalto),17s 3 (17s Benalto),17s 13 (17s Benalto),17s 16 (17s Benalto),17s 1652 (17s Benalto),17s Benalto 240 kV South Bus 2 | 2016-01-21 13:00 | 2016-01-21 17:00 | N | Y | test energize new breaker, 17s4,Test energize new breaker, 17s4. | Bus, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Restricts Generation, Contingency Requires Mitigation
Medicine Hat | MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2016-01-22 07:00 | 2016-01-22 16:00 | N | N | complete an inspection of disconnect switch MH69-511 | Line |  | Purpose of the outage is to complete an inspection of disconnect switch MH69-511. | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2016-01-22 08:00 | 2016-01-22 16:00 | N | N | replace MVAr transducer | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 251s SR2 (251s Whitla),251s Whitla 240kV Bus 2 | 2016-01-22 08:30 | 2016-01-25 08:00 | N | Y | replace spacers on 964L slack spans; coordinated with 964L & 983L outages | Bus, Shunts |  |  | 240 kV, Pre-Condition
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2016-01-22 11:00 | 2016-01-22 15:00 | N | N | emergency work to replace & repair conductor due to frost storm damage | Line |  | MOVE DRAGLINE UNDER 6L02 | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2016-01-23 07:00 | 2016-01-23 16:00 | N | N | Road construction crew working near cable | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.6TR (ENMAX 1),1.84L (ENMAX 1 - ENMAX 5),Enmax 1 B138-5A0 (ENMAX 1),ENMAX 1 B138-6A0 (ENMAX 1),Enmax 1 B138-7A0 (ENMAX 1) | 2016-01-23 08:00 | 2016-02-06 16:00 | N | N | GIS breaker maintenance for 1B138-6a0 | Line, Transformer, Circuit Breaker |  |  | Overload
ALTALINK | 854L (397s Benbow - 854L229) | 2016-01-24 06:00 | 2016-01-24 16:00 | N | N | install in-line dead end transmission structure for new 1012s station | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2016-01-24 23:00 | 2016-01-25 05:00 | N | N | RTU replacement. test and commission new CAC and OAC relays for 69kV breakers | Transformer, Line |  |  | Pre-Condition, Overload, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20),ENMAX 20 B138-20.82 (ENMAX 20),ENMAX 21 B138-20.82 (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2016-01-25 08:00 | 2016-01-26 16:00 | N | N | switch maintenance. Doble PT | Line, Transformer, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 1052 (89s Ellerslie) | 2016-01-25 08:00 | 2016-01-28 17:00 | N | Y | replace breaker control and breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2016-01-25 08:00 | 2016-01-29 16:00 | N | N | heater retrofit | Circuit Breaker |  |  | For Information Only
ALTALINK | 17s 1 (17s Benalto) | 2016-01-25 08:00 | 2016-02-04 17:00 | N | Y | breaker replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 41.1TR (ENMAX 41) | 2016-01-25 08:00 | 2016-01-29 16:00 | N | N | inspect and/or repair tap changer | Transformer |  |  | For Information Only
ALTALINK | 39s 152 (39s Bickerdike) | 2016-01-25 08:00 | 2016-01-26 17:00 | N | N | test new teleprotection scheme on 854L | Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 983L (251s Whitla - 244s Bowmanton) | 2016-01-25 08:00 | 2016-02-23 08:00 | N | Y | replace spacer dampers | Line |  |  | 240 kV, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2016-01-25 09:00 | 2016-01-25 13:00 | N | Y | work on Heathfield cooling system | Line |  |  | For Information Only, 500 kV
BCH | 1L275 (799s Coleman - Natal) | 2016-01-25 09:00 | 2016-02-03 17:00 | N | Y | complete structure replacements - BC maintenance does not affect AB ATC | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 251s SR2 (251s Whitla),251s Whitla 240kV Bus 2 | 2016-01-25 09:00 | 2016-01-26 12:00 | N | Y | replace spacers on 983L slack spans;coordinated with 964L & 983L outages | Bus, Shunts |  |  | 240 kV, For Information Only
ATCO | 813s 503R (813s Little Smoky),813s 902T (813s Little Smoky),813s503 (813s Little Smoky) | 2016-01-25 10:00 | 2016-01-26 14:00 | N | Y | repairs to 507T station service transformer | Shunts, Transformer, Circuit Breaker |  | Emergency fire repairs to 507T stn service transformer, Station service fed by Alternate feed, 503R 20 MVAR reactor will be unavailable for V control, 902T will be OOS due to limits of approach within work area, all load transferred to 901T | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 150L (42s Sarcee - 150L47) | 2016-01-25 18:00 | 2016-01-26 06:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2016-01-25 22:00 | 2016-01-26 06:00 | N | Y | high load move under line at 69st & HWY 8 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2016-01-26 07:00 | 2016-01-30 17:30 | N | N | structure replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (272s Springbank - 3L147) | 2016-01-26 07:00 | 2016-02-08 17:30 | N | N | line re-build | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2404 (805s Jasper) | 2016-01-26 07:00 | 2016-01-26 18:00 | N | Y | NAIT switch demonstration | Circuit Breaker |  |  | 240 kV, Firm Load Loss
ATCO | 2075s ACF22 (2075s Newell),2075s ACF24 (2075s Newell) | 2016-01-26 08:00 | 2016-01-28 16:00 | N | Y | find blown capacitor and replace | Shunts |  | Find blown capacitor and replace, this should not limit the amount of power flow available on the DC line with healthy voltages | 240 kV
ALTALINK | 433L (291s Cochrane - T793s Horse Creek) | 2016-01-26 08:00 | 2016-01-30 17:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D138 (ENMAX 25) | 2016-01-26 08:00 | 2016-01-27 16:00 | N | Y | repair heater fail | Circuit Breaker |  |  | For Information Only
ENMAX | 39.4TR (ENMAX 39) | 2016-01-26 08:00 | 2016-01-26 16:00 | N | N | run through neutral, oil sampling | Transformer |  |  | For Information Only
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2016-01-26 08:45 | 2016-01-27 16:45 | N | N | 7L40 Nova pole raise, pole move for pipeline | Line |  | 7L40 Nova pole raise, pole move for pipeline | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | DT | 2016-01-26 10:00 | 2016-01-26 11:00 | N | N | PI Historian project for DT | SCInternal |  |  | Pre-Condition
TRANSALTA | 239S Castle River | 2016-01-27 07:00 | 2016-01-27 08:00 | N | N | repair hot spot on switch | Station |  |  | Restricts Generation
ALTALINK | 39s 252 (39s Bickerdike) | 2016-01-27 08:00 | 2016-01-28 17:00 | N | N | end to end testing for new tele-protection scheme on 854L | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake),157s21 (157s Lac La Biche) | 2016-01-27 09:00 | 2016-01-28 17:00 | N | Y | climbing patrol | Line, Switch
ATCO, ALTALINK | 7L794 (157s Lac La Biche - 819s Whitby Lake),157s21 (157s Lac La Biche) | 2016-01-27 09:00 | 2016-01-28 17:00 | N | Y | climbing patrol | Line, Switch |  | 7L794 Climbing Patrol 2016 Climbing Patrol Jan,25 to Jan,28 continuous THIS WORK IS BEING PLANNED AS THE MATERIAL FOR THE 7L65 WORK MAY NOT HAVE ARRIVED IN TIME (7L65 WORK WILL TAKE THE PRECEDENCE) | Pre-Condition, Over/Under Voltage
ENMAX | 32.3TR (ENMAX 32) | 2016-01-28 08:00 | 2016-01-28 16:00 | N | N | LTC low oil top up | Transformer |  |  | For Information Only
ENMAX | 2.3TR (ENMAX 2) | 2016-01-28 08:00 | 2016-01-28 16:00 | N | N | LTC low oil top up | Transformer |  |  | For Information Only
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek) | 2016-01-28 09:00 | 2016-01-28 12:00 | N | Y | trip test 89s952 breaker and test operate 89s910X from new 89s1052 breaker fail protections | Line |  |  | 240 kV, Overload
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2016-01-28 13:00 | 2016-01-28 16:00 | N | Y | prove 89s909W block close function from new 89s1052 breaker fail, test trip 89s1152 | Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 935L (324s Cassils - 356s Milo) | 2016-01-28 13:00 | 2016-02-10 10:30 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2016-01-29 08:00 | 2016-01-30 16:30 | N | N | maintenance | Transformer |  | Suncor request to remove T1 from service | For Information Only
ALTALINK | 324s 1252 (324s Cassils) | 2016-01-29 14:00 | 2016-02-01 12:00 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV
ALTALINK | 854L (397s Benbow - 854L229) | 2016-01-30 06:00 | 2016-01-30 19:00 | N | N | complete transmission line termination & energize new 1012s substation | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 2075s SVC2 (2075s Newell) | 2016-01-30 08:00 | 2016-01-30 12:00 | N | Y | hydraulic and valve issue on refill tank pump | Shunts |  | Hydraulic and valve issue on refill tank pump, SVC 2 to be off/unavailable while work is on going Only one SVC will be available while each CSP is open, therefore in the event that the running SVC trips off it will trip our power flow | 240 kV
ATCO | 2075s SVC1 (2075s Newell) | 2016-01-30 12:30 | 2016-01-30 17:00 | N | Y | hydraulic and valve issue on refill tank pump | Shunts |  | Hydraulic and valve issue on refill tank pump, SVC1 to be off/unavailable while work is on going. Only one SVC will be available while each CSP is open, therefore in the event that the running SVC trips off it will trip our power flow | 240 kV
ATCO | 6L03 (6L17 tap - 757s Battle River) | 2016-01-31 13:30 | 2016-01-31 15:00 | N | N | emergency work to tighten loose hardware on an angle pin | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft WDS6 (Woodcroft) | 2016-02-01 07:00 | 2016-02-01 17:00 | N | N | repair hot connection | Switch
ALTALINK | 74s 727X (74s Janet) | 2016-02-01 07:00 | 2016-02-04 17:00 | N | N | remove and salvage 74s727X circuit breaker and 74s50 switch | Circuit Breaker |  |  | For Information Only
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2016-02-01 08:00 | 2016-02-11 17:00 | N | N | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1116L (170s Pike - 167s Ipiatik Lake) | 2016-02-01 08:00 | 2016-02-08 08:00 | N | Y | replace deficient compression dead ends | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.1TR (ENMAX 6),6.82L (ENMAX 6 - ENMAX 41),ENMAX 6 B138-6.82 (ENMAX 6) | 2016-02-01 08:00 | 2016-02-05 16:00 | N | N | heater retrofit | Line, Circuit Breaker, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1012s Deer Hill | 2016-02-01 08:00 | 2016-02-03 17:00 | N | N | in service date: Feb 1, 2016. 854L (397s Benbow - 348s Marlboro - 39s Bickerdike) will be renamed to 854L ( 1012s Deer Hill - 348s Marlboro - 39s Bickerdike) and 685L (397s Benbow - 1012s Deer Hill) will be added. | Station
ALTALINK | 89s 952 (89s Ellerslie) | 2016-02-01 08:00 | 2016-02-05 17:00 | N | Y | replace 89s952 breaker control and breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 11.3TR (ENMAX 11) | 2016-02-01 08:00 | 2016-02-05 16:00 | N | N | feeder addition and install new revenue PTs and CTs | Transformer
ATCO | 7L794 (157s Lac La Biche - 819s Whitby Lake) | 2016-02-01 09:00 | 2016-02-04 17:00 | N | Y | cross arm change | Line |  | 7L794 Cross Arm Change | Overload, Over/Under Voltage
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1) | 2016-02-02 07:00 | 2016-02-02 17:00 | N | Y | 266s1C CVT replacement | Line, Shunts |  |  | 240 kV
EPCOR | 72RG1 (Rossdale - Garneau) | 2016-02-02 07:00 | 2016-02-02 17:00 | N | N | calibrate relay | Line |  |  | For Information Only
BLACKSPRING | 485s DVAR1 (485s Blacksprings) | 2016-02-02 08:00 | 2016-02-12 17:00 | N | N | DSTATCOM system outage for corrective maintenance | Shunts |  |  | For Information Only
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2016-02-02 11:00 | 2016-02-02 15:00 | N | N | replace and repair conductor | Line |  | After the Frost Storm we found damaged wire on 5L495 Line and on 6L02 Line. To replace and repair. the conductor we need to have an Emergency Outage on Fri. Jan.22 from 11:00 am to 15:00 pm On 6L02 Line between 873 Marion Lake Sub 6L02 D5 and (Mannix Mine) 6L02 D4. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2016-02-02 12:00 | 2016-02-02 17:00 | N | Y | outage | Switch |  | TAU: BH1 generator brushgear outage | Restricts Generation
ATCO | 939s 904 (939s Livock) | 2016-02-02 12:00 | 2016-02-04 17:00 | N | Y | emergency breaker maintenance low SF6 gas | Circuit Breaker |  | Emergency Breaker maintenance GOI - Low SF6 Gas BKR 904 | 240 kV, Contingency Requires Mitigation
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2016-02-03 07:00 | 2016-02-08 17:30 | N | N | line rebuild | Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 21.1C (ENMAX 21),ENMAX 21 B138-21.CAP (ENMAX 21) | 2016-02-03 08:00 | 2016-02-04 16:00 | N | N | inspect 21B138-21CAP spring charge alarm issues | Shunts, Circuit Breaker |  |  | For Information Only
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1),ENMAX 20 B138-1.81 (ENMAX 20) | 2016-02-03 08:00 | 2016-02-05 16:00 | N | N | switch maintenance | Line, Circuit Breaker, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2016-02-03 08:00 | 2016-02-03 13:00 | N | Y | outage | Switch |  | TAU: BH2 generator brushgear outage | Restricts Generation
ALTALINK | 759L (87s Gaetz - 276s Prentiss),276s 759W (276s Un Carb Prentiss) | 2016-02-03 09:00 | 2016-02-03 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 17s Benalto 240 kV North Bus 1 | 2016-02-04 13:00 | 2016-02-04 17:00 | N | Y | test energize new breaker 17s1 | Bus |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 7 (17s Benalto) | 2016-02-04 14:43 | 2016-03-24 17:00 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek) | 2016-02-05 08:00 | 2016-02-05 10:00 | N | Y | trip test 89s1052 breaker & test operate 89s910X from new 89s1052 breaker fail protections | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 89s 252 (89s Ellerslie) | 2016-02-05 10:00 | 2016-02-05 11:00 | N | N | trip test breaker from new 89s952 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 652 (89s Ellerslie) | 2016-02-05 11:01 | 2016-02-05 12:00 | N | Y | trip test breaker from new 89s952 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 1352 (89s Ellerslie) | 2016-02-05 13:00 | 2016-02-05 14:00 | N | Y | trip test breaker from new 89s952 breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 1752 (89s Ellerslie) | 2016-02-05 15:00 | 2016-02-05 16:00 | N | Y | trip test breaker from new 89s952 breaker fail | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 2052 (89s Ellerslie) | 2016-02-05 16:01 | 2016-02-05 17:00 | N | Y | trip test breaker from new 89s952 breaker fail | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 320p PS2 (320p Keephills),320p T6 (320p Keephills) | 2016-02-06 08:00 | 2016-02-11 17:00 | N | Y | migrate all SCADA points to new SCADA system | Transformer |  |  | 240 kV, 500 kV
ENMAX | 8.1TR (ENMAX 8),8.2TR (ENMAX 8),3.82L (ENMAX 3 - ENMAX 8),ENMAX 8 B138-6A0 (ENMAX 8) | 2016-02-06 08:00 | 2016-02-25 16:00 | N | N | GIS breaker maintenance | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2016-02-06 16:01 | 2016-02-16 15:22 | N | Y | forced outage | Line |  |  | For Information Only, 500 kV
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2016-02-06 16:01 | 2016-02-12 18:00 | N | N | forced outage | Line |  |  | 500 kV
ENMAX | 40.1TR (ENMAX 40),40.2TR (ENMAX 40) | 2016-02-07 08:00 | 2016-02-07 12:00 | N | N | RTU replacement, test & commission new relays for motorized disconnects | Transformer |  |  | For Information Only
ENMAX | ENMAX 40 B138-32.83 (ENMAX 40),32.83L (ENMAX 32 - ENMAX 40) | 2016-02-07 12:00 | 2016-02-07 14:00 | N | N | RTU replacement, test & commission relays for 138 kV breakers | Circuit Breaker, Line | Studied with wind generation = 1270 MW (no concerns). |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 40.81L (ENMAX 40 - ENMAX 41),ENMAX 40 B138-40.81 (ENMAX 40) | 2016-02-07 14:00 | 2016-02-07 16:00 | N | N | RTU replacement, test & commission relays for 138 kV breakers | Circuit Breaker, Line | Studied with wind generation = 1270 MW (no concerns). |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 720s 501R (720s Wabasca) | 2016-02-08 07:00 | 2016-02-08 17:30 | N | N | salvage reactor | Shunts |  | Salvage reactor. Submit new SLD showing 501RD as NO and reactor removed. | For Information Only
ALTALINK | 225s16 (225s Magrath) | 2016-02-08 07:00 | 2016-02-11 17:00 | N | Y | switch and install grounds | Switch |  | Switch & Install Grounds for CHD1s Customer. | Restricts Generation, For Information Only
ALTALINK | 102s SVC (102s Langdon) | 2016-02-08 07:30 | 2016-02-12 08:00 | N | Y | replace CVTs (VT28) | Shunts |  |  | 240 kV
ENMAX | 11.4TR (ENMAX 11) | 2016-02-08 08:00 | 2016-02-19 16:00 | N | N | new feeder addition | Transformer
ALTALINK | 89s 1152 (89s Ellerslie) | 2016-02-08 08:00 | 2016-02-11 17:00 | N | Y | replace 89s1152 breaker control and breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 26 B138-26BT3 (ENMAX 26) | 2016-02-08 08:00 | 2016-02-12 16:00 | N | N | heater retrofit | Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.2TR (ENMAX 22) | 2016-02-08 08:00 | 2016-03-14 16:00 | N | N | tap changer replacement and PRD install | Transformer |  |  | For Information Only
ALTALINK | 1117L (898s Heart Lake - 167s Ipiatik Lake) | 2016-02-08 08:01 | 2016-02-18 17:00 | N | Y | replace deficient compression dead ends | Line |  |  | 240 kV, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 677L (305s Acheson  595s Spruce Grove) | 2016-02-08 10:00 | 2016-02-08 15:00 | N | N | TPR outage | Line |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 595s Spruce Grove RTU/SCADA | 2016-02-08 10:00 | 2016-02-08 15:00 | N | N | radio software upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 13s 152 (13s Deerland) | 2016-02-08 10:30 | 2016-02-08 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 6L09 (767s Oyen - 6L21 tap),767s 601 (767s Oyen) | 2016-02-08 10:30 | 2016-02-12 13:00 | N | N | replace line protection relays | Line, Circuit Breaker |  | Replace existing line protection relays for 6L09 at 767S Oyen. 6L09 open @ 767S Oyen and Breaker 601 out of service. | Firm Load Loss, Creates Radial Feeds
ATCO | 2075s 900SST1 (2075s Newell) | 2016-02-09 08:00 | 2016-02-11 16:00 | N | Y | install bird mitigation on 25kV outdoor equipment | Transformer |  | GOI on MV1 bay- Install bird mitigation on 25kV outdoor equipment, 900SST2 will remain in service | 240 kV
ENMAX | 13.2TR (ENMAX 13) | 2016-02-09 08:00 | 2016-02-10 16:00 | N | N | maintain 8kV bus switches | Transformer |  |  | For Information Only
ALTALINK | 28s R1 (28s West Brooks),28s 44 (28s West Brooks) | 2016-02-09 09:00 | 2016-02-09 17:00 | N | Y | replace motor in breaker | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ATCO | 840S McNeill Station | 2016-02-09 13:30 | 2016-02-09 15:00 | N | Y | to repair the transfer switch on the Alta Side and replacement of Sask. Lane 1 M2 protection CIB 1 at the same time | Station |  |  | Limits ATC
ATCO | 720S Wabasca | 2016-02-10 07:00 | 2016-02-11 17:30 | N | N | test 25 kV bus protection upgrades | Station |  | Test 25 kv bus protection upgrades. | For Information Only
ALTALINK | 768L (217s North Red Deer - 87s Gaetz),425L (194s South Red Deer - 217s North Red Deer) | 2016-02-10 08:00 | 2016-02-18 16:30 | N | N | swap A&B protections on 425L & 768L at 217s North Red Deer | Line |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 13s 552 (13s Deerland) | 2016-02-10 08:30 | 2016-02-10 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 62s11 (62s Brazeau) | 2016-02-10 23:00 | 2016-02-11 04:00 | N | Y | maintance/test | Switch |  | TAU:BR1 generator brushgear outage & AESO blackstart test | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2016-02-11 04:00 | 2016-02-11 07:00 | N | Y | outage/test | Switch |  | TAU:BR2 generator brushgear outage | 240 kV, Restricts Generation
EPCOR | 72RS5 (Rossdale - Strathcona) | 2016-02-11 07:00 | 2016-02-11 12:00 | N | N | op checks | Line |  |  | For Information Only
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2016-02-11 09:00 | 2016-02-11 12:00 | N | Y | test trip 89s1052 and test 89s909W block close function | Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-22 RTU/SCADA | 2016-02-11 10:00 | 2016-02-11 11:00 | N | N | download new configuration | Terminal Equipment |  | to download a new configuration to RTU at 29EDD-22 and also change the CPU batteries. The new configuration is to allow protection relay failure alarms in failsafe mode. Loss of visibiility will be for approx 1 hr." | Affects Visibility
EPCOR | Rossdale C1,Rossdale C2 | 2016-02-11 12:00 | 2016-02-11 17:00 | N | N | operations checks | Shunts |  |  | For Information Only
ALTALINK | 946L (89s Ellerslie - 38s East Edmonton) | 2016-02-11 13:00 | 2016-02-11 16:00 | N | Y | test trip 89s1252 and test 89s946 block close function | Line |  |  | 240 kV, Pre-Condition
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2016-02-12 07:00 | 2016-02-12 12:00 | N | N | operational checks | Line |  |  | For Information Only
EPCOR | Rossdale RR723 (Rossdale) | 2016-02-12 12:00 | 2016-02-12 17:00 | N | N | operational checks | Circuit Breaker |  |  | For Information Only
ATCO | 2075s 900SST2 (2075s Newell) | 2016-02-13 08:00 | 2016-02-15 16:00 | N | Y | install bird mitigation on 25kV outdoor equipment | Transformer |  | GOI on MV2 bay- Install bird mitigation on 25kV outdoor equipment, 900SST1 will remain in service | 240 kV, Pre-Condition
ENMAX | 6.4TR (ENMAX 6),6.80L (ENMAX 30 - ENMAX 6),ENMAX 6 B138-6.80 (ENMAX 6) | 2016-02-15 08:00 | 2016-02-18 16:30 | N | N | heater retrofit | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale VHBB1 (Rossdale) | 2016-02-16 07:00 | 2016-02-16 12:00 | N | N | op checks | Circuit Breaker |  |  | Pre-Condition
ATCO | 720s 501R (720s Wabasca),720s 901T (720s Wabasca),720s 901 (720s Wabasca),720s 502R (720s Wabasca),720s 504R (720s Wabasca) | 2016-02-16 07:00 | 2016-04-21 17:30 | N | Y | re-wire 901T cables to new building | Transformer, Circuit Breaker, Shunts |  | 901T Remove cables to old building and install new cables to new building, 901TD1 Remove cables in old tray and install new cables to new building, all load transferred to 902T (50 MVA limit), 15 MVAR of reactance unavailable for dispatch, There will be no ARECL for bkr 902. | 240 kV, Pre-Condition
EPCOR | Kennedale T2 (Kennedale) | 2016-02-16 07:00 | 2016-02-16 17:00 | N | N | fix hot connection on KAB2 | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (272s Springbank - 3L147) | 2016-02-16 07:00 | 2016-02-29 18:00 | N | N | line re-build | Line |  |  | Creates Radial Feeds
ATCO | 7L31 (732s Mitsue - 844s AEC MILL),732s 701 (732s Mitsue),732s 706 (732s Mitsue) | 2016-02-16 08:00 | 2016-02-18 16:30 | N | N | change and test ct ratios for 701CT & 706CT | Line, Circuit Breaker |  | To change and test ct ratios for 701CT & 706CT, we will also need to change protection settings for 7L31 protections that will correspond with these CT ratio changes. | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 525s 850N (525s Carseland),850L (525s Carseland - 678s Okotoks) | 2016-02-16 08:00 | 2016-02-19 17:00 | N | N | Foothills 138kV projects | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 853L (504s Queenstown - 853L76A) | 2016-02-16 08:00 | 2016-03-31 16:00 | N | N | rebuild from structures 202-265 | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 405s C2 (405s Waupisoo) | 2016-02-16 08:00 | 2016-02-16 16:00 | N | N | ddr install | Shunts |  |  | For Information Only
ALTALINK | 89s 1452 (89s Ellerslie) | 2016-02-16 08:00 | 2016-02-19 17:00 | N | Y | replace 89s1452 breaker control and breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2016-02-16 08:30 | 2016-02-18 17:00 | Y | Y | repair damage sections; discovered from 2015 | Line |  |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK | 702L (137s Sedgewick - 757s Battle River) | 2016-02-16 10:00 | 2016-02-16 17:30 | N | N | replace partially burnt crossarm | Line | Studied with maximum Battle River generation and different central wind generation (0%, 80% and 100%). |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 191s T2 (191s N.W.Cardiff) | 2016-02-16 10:30 | 2016-02-16 17:00 | N | N | 25kV breaker maintenance | Transformer |  |  | For Information Only
EPCOR | Rossdale VHBB2 (Rossdale) | 2016-02-16 12:00 | 2016-02-16 17:00 | N | N | op checks | Circuit Breaker |  |  | For Information Only
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2016-02-17 07:00 | 2016-02-17 17:00 | N | N | repair hot connection on pothead | Line
ATCO | 863s 901T (863s Paintearth) | 2016-02-17 07:00 | 2016-04-14 17:00 | N | Y | install risers to re-attach 901T, 901T has been removed from site since June 2015, no added system risk | Transformer |  | Install risers to re-attach 901T, 901T has been removed from site since June 2015, no added system risk | 240 kV, For Information Only
EPCOR | 72RG7 (Rossdale - Garneau) | 2016-02-17 07:00 | 2016-02-17 17:00 | N | N | op checks | Line
ATCO | 786s 701T (786s High Level) | 2016-02-17 07:00 | 2016-02-18 12:00 | N | N | move protection panel, 701T load will be transferred to 702T | Transformer |  | Move protection panel, 701T load will be transferred to 702T | Pre-Condition
ATCO | 2029s 1221 (2029s Heathfield),2029s ACF14 (2029s Heathfield) | 2016-02-17 08:00 | 2016-02-17 12:00 | N | N | check on the status of oil leak near the lid of the shunt reactor | Shunts, Circuit Breaker |  |  | For Information Only, 500 kV
STROBE | 240S McBride Lake | 2016-02-17 08:00 | 2016-02-29 23:00 | N | N | update relay on low wind day | Station |  |  | For Information Only
ATCO | 2075s SVC1 (2075s Newell) | 2016-02-17 08:00 | 2016-02-17 16:00 | N | Y | deficiency repairs | Shunts |  |  | 240 kV, For Information Only
ALTALINK | 728L (405s Waupisoo - 353s Plamondon),405s 728 (405s Waupisoo) | 2016-02-17 08:00 | 2016-02-17 16:00 | N | N | DDR install | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L130 (710s Vermilion - 705s Kitscoty) | 2016-02-17 08:00 | 2016-02-17 17:00 | N | N | pole replacment/reinforcement | Line |  | LINE 7L130 VERMILION 710S TO KITSCOTY 705S 7L130 pole repl/reinforce | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 233s T2 (233s Beamer) | 2016-02-17 09:00 | 2016-02-18 15:00 | N | N | Agrium request to remove T2 from service | Transformer
ALTALINK | 536S Brookfield | 2016-02-17 09:00 | 2016-02-17 19:00 | N | N | customer requested maintenance | Station
ALTALINK | 331s T1 (331s Ponoka) | 2016-02-17 09:00 | 2016-02-17 17:00 | N | N | 25kV breaker maintenance | Transformer
ALTALINK | 745L (602s Cold Creek - 745L482) | 2016-02-18 04:17 | 2016-02-18 18:00 | N | N | forced outage | Line
EPCOR | Rossdale RR729 (Rossdale) | 2016-02-18 07:00 | 2016-02-18 17:00 | N | N | op checks | Circuit Breaker |  |  | For Information Only
ALTALINK, ATCO | 650s T1 (650s Hansman Lake),715L (648s Metiskow - 650s Hansman Lake),885L (648s Metiskow - 650s Hansman Lake),7L224 (774s Monitor - 650s Hansman Lake),650S Hansman Lake 138kV Bus | 2016-02-18 08:00 | 2016-02-18 16:00 | N | Y | remove one of SS3 vts for leak repairs | Line, Bus, Transformer |  | remove one of SS3 vts for leak repairs. 648s36 will be closed to keep the 545s load energized. Arc Flash mitigation on 650s86 & 650s96 | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 633L (56s Boyle - 405s Waupisoo),405s 633 (405s Waupisoo) | 2016-02-18 08:00 | 2016-02-18 16:00 | N | N | DDR install | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 2075s SVC2 (2075s Newell) | 2016-02-18 08:00 | 2016-02-18 16:00 | N | Y | deficiency repairs | Shunts |  | Hydraulic and valve issue on refill tank pump, SVC 2 to be off/unavailable while work is on going Only one SVC will be available while each CSP is open, therefore in the event that the running SVC trips off it will trip our power flow | 240 kV
ENMAX | 2.3TR (ENMAX 2) | 2016-02-18 08:00 | 2016-02-19 16:00 | N | N | LTC low oil top up | Transformer |  |  | For Information Only
ATCO | 786s 702T (786s High Level),786s High Level 144kV Bus 700BS2 | 2016-02-18 13:00 | 2016-03-09 13:00 | N | N | 702T transformer protection upgrade | Bus, Transformer |  | 702T Transformer protection upgrade. Add two fused disconnects to 700PT1 secondary, 701T will carry all 25kV load. Temporary relay setting change at 789S Keg River | Pre-Condition
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2016-02-19 08:00 | 2016-02-19 16:00 | N | N | ENMAX maintenance (modification to line protection (SEL) outputs) | Line
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2016-02-19 08:00 | 2016-02-19 16:00 | N | N | modification to line protection (SEL) outputs | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 89s 1352 (89s Ellerslie) | 2016-02-19 09:00 | 2016-02-19 12:00 | N | Y | prove 89s1089 block close function from new 89s1452 breaker fail, test trip 89s1352 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 914L (86s Bigstone - 89s Ellerslie) | 2016-02-19 09:00 | 2016-02-19 16:00 | N | Y | trip test 89s1552 breaker & test operate 89s914X from new 89s1452 breaker fail protections | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 39s T2 (39s Bickerdike),39s Bickerdike 138kV Bus 2 | 2016-02-19 11:00 | 2016-02-19 17:30 | N | Y | replace 39s99 fuse | Bus, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss
ALTALINK | 851L (525s Carseland - 253s Blackie) | 2016-02-20 07:00 | 2016-02-23 18:00 | N | N | installation new dead-end structure outside of the 253s Blackie | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 198s T1 (198s Blackfalds) | 2016-02-20 07:00 | 2016-02-21 17:00 | N | N | Blackfalds upgrade project: install new 138kV 19s40 and piles for 138kV tie breaker | Transformer |  |  | For Information Only
ALTALINK | 433L (291s Cochrane - T793s Horse Creek) | 2016-02-20 09:00 | 2016-02-20 10:00 | N | N | close 793s16 | Line | 1. Studied with 44s Bearspaw generation offline and Bow generation = 65 MW - no concerns. | 433L  Open Breaker Advice has been added to the schedule on February 20, 2016 0900 - 1000. This is an urgent request as 793s16 (line switch) is not properly closed. | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1C (ENMAX 21),ENMAX 21 B138-21.CAP (ENMAX 21) | 2016-02-21 19:00 | 2016-02-22 05:00 | N | N | RTU replacement, test and commission new relays for 138kV cap breaker | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 21.1TR (ENMAX 21),21.2TR (ENMAX 21) | 2016-02-21 19:00 | 2016-02-21 22:00 | N | N | RTU replacement, test and commission new CAC and OAC relays for 138 kV motorized disconnect | Transformer
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21),ENMAX 21 60s50 (ENMAX 21) | 2016-02-21 22:00 | 2016-02-21 23:00 | N | Y | RTU replacement | Line, Circuit Breaker |  |  | For Information Only
ENMAX | ENMAX 21 B138-20.82 (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2016-02-21 23:00 | 2016-02-21 23:59 | N | N | RTU replacement, test and commission new CAC and OAC relays for 138kV breaker | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21) | 2016-02-21 23:59 | 2016-02-22 05:00 | N | N | RTU replacement, test and commission new relays for 69kV motorized disconnect | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21),ENMAX 21 B138-21.80 (ENMAX 21) | 2016-02-22 | 2016-02-22 01:00 | N | Y | RTU replacement, test and commission new relays for 138kV breaker | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 156L (235s Entwistle - 156L 86A),235s 156E (235s Entwistle) | 2016-02-22 07:00 | 2016-03-03 17:00 | N | N | replace 235s156E breaker | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
EPCOR | 72VN21 (Namao - 511s Victoria),Namao N725 (Namao) | 2016-02-22 07:00 | 2016-02-23 17:00 | N | N | bushing cleaning | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2016-02-22 07:00 | 2016-02-22 12:00 | N | N | op checks | Line |  |  | Pre-Condition, Creates Radial Feeds
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2016-02-22 08:00 | 2016-02-26 16:00 | N | Y | construction deficiencies | Line |  | DC yard outage @ 2029s Heathfield, 13L50 OOS for Construction Deficiciencies, EATL will be unavailable for power transfer -Converter transformer cooling permanent solution implementation -Deficiencies identified during trial run to be fixed -Multiple software update. -Equipment inspection. -Replace the primary labels on one of the Heathfield neutral CTs | 500 kV
ATCO | 9L913 (69s North Barrhead - 732s Mitsue) | 2016-02-22 08:00 | 2016-02-29 18:00 | N | Y | replace rotten crossarms, poles | Line |  | replace rotten crossarms, poles | 240 kV, Pre-Condition
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2016-02-22 08:00 | 2016-02-22 16:00 | N | N | switch maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 1552 (89s Ellerslie) | 2016-02-22 08:00 | 2016-02-26 17:00 | N | Y | replace 89s1552 breaker control and breaker fail | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 947L (89s Ellerslie - 987s Clover Bar) | 2016-02-22 08:00 | 2016-02-23 16:00 | N | Y | isolation extension for 89s 1552 breaker outage due to switch issue | Line |  |  | 240 kV, For Information Only
ALTALINK | 288s T2 (288s Wolf Creek) | 2016-02-22 10:00 | 2016-03-13 17:00 | N | Y | repair oil leak | Transformer |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 233s T1 (233s Beamer),807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap),410s 652 (410s Josephburg),410s 752 (410s Josephburg) | 2016-02-22 10:30 | 2016-02-22 17:00 | N | N | switch repair / adjustment | Circuit Breaker, Line, Transformer |  |  | For Information Only
ALTALINK | 38s T3 (38s East Edmonton) | 2016-02-22 10:30 | 2016-02-23 17:00 | N | N | repair multiple hot spots, repair T3 leaks, winding temp gauge | Transformer |  |  | For Information Only
ALTALINK | 874L (522s Cooking Lake - 45s Bretona),45s 874 (45s Bretona) | 2016-02-22 10:30 | 2016-02-22 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 418L (20s Ghost - 418L193A),20s 452 (20s Ghost),20s 81 (20s Ghost) | 2016-02-22 11:00 | 2016-02-22 17:00 | N | N | 138 kV breaker and switch maintenance | Line, Circuit Breaker, Switch |  |  | Pre-Condition, For Information Only
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2016-02-22 12:00 | 2016-02-22 17:00 | N | N | op checks | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2016-02-22 15:00 | 2016-02-25 17:00 | N | Y | WATL out of service test and repairs | Line |  |  | 500 kV
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2016-02-23 07:00 | 2016-02-25 17:00 | N | N | line re-build | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 804S Wintering Hills | 2016-02-23 08:00 | 2016-02-24 17:00 | N | N | WPRM outage | Station |  |  | For Information Only
ATCO | 2075s SVC2 (2075s Newell) | 2016-02-23 08:00 | 2016-02-23 17:00 | N | Y | fence replacement | Shunts |  | SVC2 will be unavailable for dispatch, SVC1 will be in service, fence replacement. | 240 kV, For Information Only
ALTALINK | 405s C1 (405s Waupisoo),405s 17 (405s Waupisoo) | 2016-02-23 08:00 | 2016-02-23 16:00 | N | N | DDR install | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 63s T2 (63s Red Deer),648L (63s Red Deer - 580s Sylvan Lake),755L (63s Red Deer - 247s Piper Creek),80L (63s Red Deer - 214s Innisfail),63s Red Deer 138 kV South Bus,63s T4 (63s Red Deer) | 2016-02-23 08:00 | 2016-03-18 10:00 | N | Y | re-conductor bus and replace bus differential | Transformer, Line, Bus |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 5 5B138-5BT12 (ENMAX 5) | 2016-02-23 08:00 | 2016-02-24 16:00 | N | N | heater retrofit (replace with proper heaters) | Circuit Breaker
ATCO | 2075s SVC1 (2075s Newell) | 2016-02-23 08:00 | 2016-02-23 17:00 | N | Y | SVC1 will be unavailable for dispatch, SVC2 will be in service, fence replacement | Shunts |  | SVC1 will be unavailable for dispatch, SVC2 will be in service, fence replacement. | 240 kV, For Information Only
ALTALINK | 185s 252 (185s Bretville) | 2016-02-23 08:30 | 2016-02-23 17:00 | N | N | maintenance | Circuit Breaker
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2016-02-23 09:00 | 2016-02-25 17:00 | N | Y | replace spacer dampers | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1120L (410s Josephburg - 108s Amelia),410s1120 (410s Josephburg) | 2016-02-23 09:00 | 2016-02-23 17:00 | N | Y | switch repair / adjustment & leaking CT repair | Switch, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 478s T1 (478s Tucuman) | 2016-02-23 09:00 | 2016-02-23 16:00 | N | N | add bird cover up to T1 | Transformer
ALTALINK | 757L (17s Benalto - 758L1),17s 757N (17s Benalto) | 2016-02-23 11:00 | 2016-02-23 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2016-02-24 07:00 | 2016-02-24 19:00 | N | N | customer request to remove T1 from service | Transformer |  |  | For Information Only
EPCOR | 52s T1 (52s East Industrial) | 2016-02-24 07:00 | 2016-02-24 17:00 | N | Y | repair oil leak (emergency) | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK13 (987s Clover Bar - Kennedale),Kennedale K721 (Kennedale) | 2016-02-24 07:00 | 2016-02-24 17:00 | N | N | op checks | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CN10 (987s Clover Bar - Namao),Namao N724 (Namao) | 2016-02-24 07:00 | 2016-02-25 17:00 | N | N | bushing cleaning | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 13.3TR (ENMAX 13) | 2016-02-24 08:00 | 2016-02-25 16:00 | N | N | maintenance on 13B8-13.18 | Transformer |  |  | For Information Only
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2016-02-24 08:00 | 2016-02-24 17:00 | N | N | replace str #163 | Line |  | 7L28 Replace str#163 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 185s 352 (185s Bretville) | 2016-02-24 08:30 | 2016-02-24 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 276s 652 (276s Un Carb Prentiss),276s C1 (276s Prentiss) | 2016-02-24 09:00 | 2016-02-24 17:00 | N | N | 138 kV breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 857L (409s Shell Scotford - 410s Josephburg),410s 857N (410s Josephburg) | 2016-02-24 09:00 | 2016-02-24 17:00 | N | N | switch repair / adjustment | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 773L (127s Bruderheim - 308s Albchem Beaverhill Creek),308s 773E (308s Albchem Beaverhill Creek) | 2016-02-24 09:00 | 2016-02-24 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 478s T2 (478s Tucuman) | 2016-02-24 09:00 | 2016-02-24 16:00 | N | N | add bird cover | Transformer
ATCO | 2029s 1200SST1 (2029s Heathfield) | 2016-02-25 08:00 | 2016-02-26 17:00 | N | N | install bird mitigation on 25kV outdoor equipment | Transformer |  | Siemens is performing bird mitigation installation and installing permanent signage on all 25kV structures. | For Information Only, 500 kV
ENMAX | 1.84L (ENMAX 1 - ENMAX 5),Enmax 1 B138-7A0 (ENMAX 1) | 2016-02-25 08:00 | 2016-03-02 10:00 | N | N | repair grounding switch 6a8 | Line, Circuit Breaker |  |  | For Information Only
ATCO | 7L129 (526s Buffalo Creek - 918s Bauer) | 2016-02-25 08:00 | 2016-02-25 17:00 | N | Y | change pole and arm and x braces | Line |  | change pole and arm and x braces due to test and treat 2015 | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 835L (283s Violet Grove - 835L tap),283s 835E (283s Violet Grove) | 2016-02-25 08:30 | 2016-02-25 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 185s 452 (185s Bretville) | 2016-02-25 08:30 | 2016-02-25 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 42s C1 (42s Sarcee),42s 31 (42s Sarcee) | 2016-02-25 09:00 | 2016-02-25 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 776L (410s Josephburg - 308s Albchem Beaverhill Creek),410s 776E (410s Josephburg) | 2016-02-25 09:00 | 2016-02-25 17:00 | N | N | switch repair / adjustment | Line, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 927L (102s Langdon - 356s Milo) | 2016-02-25 09:00 | 2016-02-25 12:00 | N | Y | emergency 927L repair | Line |  | emergency 927L repair; Repair & Replace Rubbers on Interphase Spacer between Str's 208 & 209 | 240 kV
ALTALINK | 172L (15s Fort Macleod - 172L1251) | 2016-02-25 09:00 | 2016-02-25 16:00 | N | N | connect mobile to 172L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 946s 902 (946s Oakland) | 2016-02-25 09:00 | 2016-02-25 16:00 | N | Y | recharge SF5 and repair leak | Circuit Breaker |  |  | 240 kV
EPCOR | 72NW15 (Namao - Woodcroft) | 2016-02-25 09:00 | 2016-04-13 17:00 | N | N | line maintenance | Line |  |  | For Information Only
ALTALINK | 56s 17 (56s Boyle) | 2016-02-25 10:30 | 2016-02-25 15:00 | N | N | install extension plates on switch | Switch |  |  | For Information Only
ALTALINK | 924L (102s Langdon - 356s Milo) | 2016-02-25 14:00 | 2016-02-26 18:00 | N | Y | emergency 924L repair | Line |  | 924L: Emergency 924L repair; Repair & Replace Rubbers on Interphase Spacer between Str's 169 & 170, Splice Out Conductor & Replace Bundle Spacers between Str's 299 & 300 | 240 kV
ALTALINK | 15s T1 (15s Fort Macleod),180L (15s Fort Macleod - 928s East Stavely),725L (15s Fort MacLeod - 725BL54),15s Fort Macleod 138kV Bus | 2016-02-25 16:00 | 2016-03-09 07:59 | N | N | replace 15s31 PTs, replace 15s28, s181, s179, s22, s26 replace strain insulators, replace bus insulators | Transformer, Bus, Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | EC01 Cavalier | 2016-02-25 17:00 | 2016-02-27 16:00 | N | N | max. net to grid generation: 90 MW | Unit |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1),Enmax 1 B138-5A0 (ENMAX 1),ENMAX 1 B138-6A0 (ENMAX 1) | 2016-02-26 07:44 | 2016-03-09 09:30 | N | N | investigate differential trip 1.6TR | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek),755L (63s Red Deer - 247s Piper Creek) | 2016-02-26 08:00 | 2016-04-30 23:59 | N | Y | rebuild 1083L,rebuild 755L | Line |  | Rebuild portion of 1083L from 63s That parallels 755L | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 263s T2 (263s Strachan) | 2016-02-26 08:00 | 2016-02-26 17:00 | N | N | install additional bird cover | Transformer |  |  | For Information Only
ALTALINK | 681s T1 (681s Bannerman) | 2016-02-26 08:00 | 2016-03-10 16:00 | N | Y | isolate and install grounds for customer work on cables | Transformer |  |  | 240 kV
ENMAX | 2.80L (ENMAX 2 - ENMAX 23),ENMAX 23 B138-2.80 (ENMAX 23) | 2016-02-26 08:00 | 2016-02-26 12:00 | N | N | top up SF6 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
PANC, ALTALINK | 611L (391S Balzac - 186s Dry Creek),PCES02L (391s Balzac - PCES02S Balzac Power Station),391s 25 (391s Balzac) | 2016-02-26 09:00 | 2016-02-28 19:00 | N | Y | maintenance | Line, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 89s Ellerslie) | 2016-02-26 09:00 | 2016-02-26 12:00 | N | Y | trip test 89s1452 breaker & test operate 89s914X from new 89s1552 breaker fail protections | Line |  |  | 240 kV, Overload
ALTALINK | 947L (89s Ellerslie - 987s Clover Bar) | 2016-02-26 13:00 | 2016-02-26 16:00 | N | Y | trip test 89s1652 breaker & test operate 89s947 from new 89s1552 breaker fail protections | Line |  |  | 240 kV
ALTALINK | 526L (526L220 - 526L365) | 2016-02-26 17:01 | 2016-03-28 17:00 | N | N | rebuild section between A/B 526L220 and A/B 526L365 | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
EPCOR | Garneau T3 (Garneau) | 2016-02-27 06:00 | 2016-02-27 17:00 | N | N | oil leak and operating checks | Transformer
ALTALINK, ENMAX | 74s T2 (74s Janet),23.80L (74s Janet - ENMAX 23),24.83L (74s Janet - ENMAX 24),74s Janet 138kV South Bus | 2016-02-27 07:00 | 2016-02-28 17:00 | N | Y | replace 138 kV string insulators | Transformer, Line, Bus |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2016-02-27 08:00 | 2016-02-28 16:00 | N | Y | high voltage switch maintenance | Line, Transformer, Shunts |  |  | For Information Only
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2016-02-27 08:00 | 2016-02-27 17:00 | N | Y | damper replacement | Line |  |  | 240 kV, Pre-Condition
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23),ENMAX 23 138 kV East Bus | 2016-02-27 09:00 | 2016-02-28 16:00 | N | N | spring substation washing | Transformer, Line, Bus |  |  | For Information Only
ATCO | 1035L (2075s Newell - 244s Bowmanton) | 2016-02-28 08:00 | 2016-02-29 17:00 | N | Y | damper replacement | Line |  |  | 240 kV
EPCOR | 72CK12 (987s Clover Bar - Kennedale),Kennedale K724 (Kennedale) | 2016-02-29 06:30 | 2016-02-29 09:00 | N | N | op checks | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker T3 (Poundmaker) | 2016-02-29 07:00 | 2016-03-06 17:00 | N | Y | op checks | Transformer |  |  | 240 kV
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2016-02-29 07:00 | 2016-03-11 17:00 | N | N | clearance for right of way crew | Line | Higher EATL North to South flow may increase amount of overload on 749L. | Clearance for right of Way crew. Altalink requires 7L65 Back i/s for march 8th for a 650S 138kv outage. | Pre-Condition, Overload, Over/Under Voltage
ATCO | 786s 507C (786s High Level),786s 508C (786s High Level) | 2016-02-29 08:00 | 2016-02-29 17:30 | N | N | vacuum bottle repair / setup / replace | Shunts |  | Expand Permit 2-33708 Jeff Cowden will work under Brent Jacobson, Capacitor 507C & 508C Unavailable during outage. 502TD Vacuum Bottle Repair/Setup/Replace 5L363 & 5L134 tied onto - 5L143 for the duration of the work, John Bingham asked for the settings to be reviewed by P&C and temporary setting issued if required. -------- Load Transfer -------- 786S 5L143 Peak Load = 0 MVA 786S 5L363 Peak Load = 0 MVA 786S 5L134 Peak Load = 0 MVA 786S 5L363 Relay Settings: 786S 5L143 Relay Settings: 786S 5L134 Relay Settings: -------- Load Transfer -------- | For Information Only
ATCO | 2029s 1200SST2 (2029s Heathfield) | 2016-02-29 08:00 | 2016-03-02 17:00 | N | Y | Siemens is performing bird mitigation installation and installing permanent signage on 25 kV structures | Transformer |  | Siemens is performing bird mitigation installation and installing permanent signage on all 25kV structures. | 500 kV
ENMAX, ALTALINK | 30.81L (42s Sarcee - ENMAX 30),ENMAX 30 B138-30.81 (ENMAX 30) | 2016-02-29 08:00 | 2016-03-02 16:00 | N | Y | end to end test, bench test | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 21 B138-20.82 (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2016-02-29 08:00 | 2016-03-04 16:00 | N | N | heater retrofit | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p Sundance 240kV Bus A | 2016-02-29 09:00 | 2016-03-03 17:00 | N | Y | replace A & B protection, functional testing to breakers | Bus | Studied with full SD generation. |  | 240 kV, Contingency Requires Mitigation
EPCOR | Namao N723 (Namao) | 2016-02-29 09:00 | 2016-03-01 17:00 | N | N | bushing cleaning | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 434s T1 (434s East Stony Plain),739L (434s Stony Plain - 739L216A) | 2016-02-29 10:00 | 2016-03-03 17:00 | N | N | replace 434s8 138kV bus PTs | Transformer, Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK, EPCOR | 320p 1352 (320p Keephills),909L (320p Keephills - 665s Dome) | 2016-02-29 10:30 | 2016-03-01 17:00 | N | Y | breaker maintenance | Circuit Breaker, Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 718s 701T (718s Parsons Creek),848s 703T (848s Ruth Lake),7L165 (718s Parsons Creek - 933s Tower Road),7L47 (848s Ruth Lake - 718s Parsons Creek) | 2016-02-29 11:00 | 2016-03-03 17:00 | N | N | breaker maintenance | Transformer, Line |  | 7L47 20 Arms install 2016 ADDITIONAL WORK BUNDLED INTO OUTAGE. PM ON BKR 701, 704 AND 501 AT 718S PARSONS CREEK AND PM ON BKR 702, 600PT3 AT 848S RUTH LAKE | Creates Radial Feeds
ALTALINK | 650s 452 (650s Hansman Lake) | 2016-02-29 12:00 | 2016-03-02 17:00 | N | Y | replace breaker CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 149s T1 (149s Nisku) | 2016-03-01 07:00 | 2016-03-01 17:00 | N | N | required for bus protection upgrade | Transformer |  |  | For Information Only
ATCO | 9L1035 (2075s Newell - 244s Bowmanton),2075s 922 (2075s Newell),2075s 923 (2075s Newell) | 2016-03-01 08:00 | 2016-03-01 16:00 | N | Y | test and operate 21A/9L1035 relay | Circuit Breaker, Line |  | Test & Operate 21A/9L1035 Relay trips to breakers 922 and 923, 9L1035D1 and 922A will be opened to prevent system load swings, EATL will be limited to 650MW during this work, work done in conjunction with CSP 2-36217. | 240 kV
ENMAX | 2.1TR (ENMAX 2) | 2016-03-01 08:00 | 2016-03-01 16:00 | N | N | replace winding temp relay | Transformer |  |  | For Information Only
ALTALINK | 171s T1 (171s Redwater) | 2016-03-01 09:00 | 2016-03-01 15:00 | N | N | add bird cover up to T1 and cut open Point A | Transformer |  |  | For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa),286s 215 (286s Yasa) | 2016-03-01 09:00 | 2016-03-01 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
IMPERIALOIL | 7L161 (909s Mahno - 942s Nabiye) | 2016-03-01 10:00 | 2016-03-01 17:00 | N | Y | urgent D25 configuration update | Line |  |  | For Information Only
ALTALINK | 149s T3 (149s Nisku) | 2016-03-02 07:00 | 2016-03-02 17:00 | N | N | required for bus protection upgrade | Transformer |  |  | For Information Only
EPCOR | 72RV4 (Rossdale - 511s Victoria),Rossdale RV726 (Rossdale) | 2016-03-02 07:00 | 2016-03-03 17:00 | N | N | bushing cleaning | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2016-03-02 08:00 | 2016-03-04 16:00 | N | N | ENMAX maintenance (add isolation switch to relay BF outputs. end to end testing) | Line |  |  | For Information Only
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38),ENMAX 38 B138-38.83 (ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2016-03-02 08:00 | 2016-03-04 16:00 | N | N | add isolation switch to relay BF outputs, end to end testing | Line, Shunts, Transformer, Circuit Breaker | Shepard = 400 MW and Wind = 1156 MW |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 728L (353s Plamondon - 157s Lac La Biche) | 2016-03-02 08:00 | 2016-03-02 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 171s T2 (171s Redwater) | 2016-03-02 09:00 | 2016-03-02 15:00 | N | N | add bird cover up to 171s38 | Transformer |  |  | For Information Only
ALTALINK | 286s 352 (286s Yasa) | 2016-03-02 09:00 | 2016-03-02 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
AESO | 788L (157s Lac La Biche - 788L Tap) | 2016-03-02 12:01 | 2016-03-02 15:00 | N | N | high load move | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 171s T1 (171s Redwater) | 2016-03-03 08:00 | 2016-03-03 12:00 | N | N | close open point A | Transformer
ATCO | 725s 701T (725s Goose River),7L56 (725s Goose River - 7L56D3) | 2016-03-03 08:00 | 2016-03-03 17:00 | N | N | replace station service transformer and relocate station service | Line, Transformer |  | Replace station service 3 kva xmer with 25 kva. Relocate station service.
ALTALINK | 500s T1 (500s Flatbush) | 2016-03-03 08:00 | 2016-03-03 16:00 | N | N | repairing transformer leaks | Transformer
ALTALINK | 605L (286s Yasa - 185s Bretville),286s 605 (286s Yasa) | 2016-03-03 09:00 | 2016-03-03 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 718s 702T (718s Parsons Creek),7L71 (718s Parsons Creek - 2082s Dog Rib) | 2016-03-04 08:00 | 2016-03-08 17:00 | N | N | install arm | Transformer, Line |  | 7L71 20 Arms install 2016. FMS is also taking out 702T at Parsons creek to complete PM requirements. this work will be done with no additional impact | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2016-03-05 01:00 | 2016-03-07 05:00 | N | Y | spring substation washing night | Line, Transformer | Studied with Crossfield net generation = 120 MW, CEC net generation = 250 MW, and Balzac net generation = 105 MW, Lower Crossfield, CEC and Balzac generation may alleviate amount of overload on 39.82L for next contingencies. - no concerns. |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2016-03-05 07:00 | 2016-03-06 12:00 | N | N | spring transmission line washing | Line | Studied with UofC net generation = 0 MW. |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11),ENMAX 11 B138-11.81 (ENMAX 11) | 2016-03-05 08:00 | 2016-03-05 10:00 | N | N | spring substation washing | Circuit Breaker, Line | Studied with Cavalier = 115 MW, Balzac = 90 MW, Carseland = 80 MW, Shepard = 800 MW and CEC = 230 MW - no concerns. |  | Pre-Condition
ENMAX | 11.83L (162s Beddington - ENMAX 11),ENMAX 11 B138-11.83 (ENMAX 11) | 2016-03-05 10:00 | 2016-03-05 12:00 | N | Y | spring substation washing | Circuit Breaker, Line |  |  | Pre-Condition, Overload
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11) | 2016-03-05 12:00 | 2016-03-05 14:00 | N | N | spring substation washing | Transformer
ENMAX, AESO | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2016-03-05 12:00 | 2016-03-05 20:00 | N | N | repair hotspot on SW91 at 5 sub | Line, Transformer |  |  | Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2016-03-05 12:00 | 2016-03-06 17:00 | N | N | spring transmission line washing | Line | Studied with UofC generation = 0 MW - no concerns. |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2016-03-05 14:00 | 2016-03-05 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2016-03-06 08:00 | 2016-03-06 12:00 | N | N | spring substation washing | Line, Transformer | Studied with wind generation = 1000 MW, CEC = 250 MW, Crossfield = 0 MW, Balzac = 115 MW, Shepard = 600 MW, Carseland = 80 MW, and Cavalier = 115 MW - no concerns.
ALTALINK | 310P Sundance | 2016-03-06 08:00 | 2016-04-07 17:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2016-03-06 12:00 | 2016-03-06 16:00 | N | N | spring substation washing | Line, Transformer | Studied with wind generation = 1000 MW - no concerns. |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2016-03-06 23:00 | 2016-03-08 05:00 | N | N | spring transmission line washing night | Line | Studied with UofC generation = 0 MW (no concerns). |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s T1 (74s Janet),925L (63s Red Deer - 74s Janet),74s 2052 (74s Janet),74s 552 (74s Janet),74s 2752 (74s Janet),74s 2552 (74s Janet),74s 2152 (74s Janet),74s 3752 (74s Janet),74s Janet 240kV Bus 1 | 2016-03-07 07:00 | 2016-03-11 17:00 | N | Y | replace string insulators on 925L, 74s925N, 74s20X and 74s20N | Line, Bus, Transformer, Circuit Breaker |  |  | 240 kV, Overload
ATCO | 9L100 (801s Anderson - 807s Sheerness) | 2016-03-07 07:00 | 2016-03-14 16:00 | N | N | re-installation auxiliary transformer | Line |  |  | 240 kV, Restricts Generation
EPCOR | 72RV2 (Rossdale - 511s Victoria),Rossdale RV728 (Rossdale) | 2016-03-07 07:00 | 2016-03-08 17:00 | N | N | bushing cleaning | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 913L (69s North Barrhead - 732s Mitsue) | 2016-03-07 08:00 | 2016-03-14 17:30 | N | N | changing out X-arms | Line |  |  | Pre-Condition
ATCO | 9L913 (69s North Barrhead - 732s Mitsue) | 2016-03-07 08:00 | 2016-03-14 17:30 | N | Y | replace rotten crossarms, poles | Line |  | replace rotten crossarms, poles | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 832L (ENMAX 10 - ENMAX 12),ENMAX 10 B138-832 (ENMAX 10) | 2016-03-07 08:00 | 2016-03-11 16:00 | N | N | heater retrofit | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 707s St.Paul RTU/SCADA | 2016-03-07 08:45 | 2016-03-07 16:00 | N | N | download PLC & update HMI program | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 510s Sunnybrook RTU/SCADA | 2016-03-07 09:00 | 2016-03-08 17:30 | N | N | firmware upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | AltaLink Radio Tower | 2016-03-07 09:00 | 2016-03-07 11:00 | N | N | 510s to 9320R radio - firmware upgrade | Terminal Equipment |  |  | For Information Only
ALTALINK | 768L (217s North Red Deer - 87s Gaetz) | 2016-03-07 09:00 | 2016-03-17 15:00 | N | N | cut-in new 209s Timberlands | Line |  |  | Overload
ALTALINK | 28s R1 (28s West Brooks),28s 44 (28s West Brooks) | 2016-03-07 09:00 | 2016-03-07 18:00 | N | Y | 28s44 POW relay installation | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK, EPCOR | 1045L (310p Sundance - 805s Jasper),310p 1752 (310p Sundance),310p 1652 (310p Sundance) | 2016-03-07 10:00 | 2016-03-10 15:00 | N | Y | replace PTs on CVT-L6 and 310p132 junction box | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove),99s21 (99s North St Albert) | 2016-03-07 10:30 | 2016-03-07 17:00 | N | N | switch repair / adjustment | Line, Switch |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 652 (77s Sagitawah) | 2016-03-07 11:00 | 2016-03-07 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s Sunnybrook RTU/SCADA | 2016-03-07 14:30 | 2016-03-07 16:30 | N | N | PMU upgrade firmware 510s Sunnybrook | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 858L (149s Nisku - 40s Wetaskiwin),149s 858X (149s Nisku) | 2016-03-08 07:00 | 2016-03-08 17:00 | N | N | required for bus protection upgrade | Circuit Breaker, Line |  |  | Pre-Condition, Overload
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2016-03-08 08:00 | 2016-03-09 10:00 | N | N | spring transmission line washing potheads | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 650s 752 (650s Hansman Lake) | 2016-03-08 08:00 | 2016-03-10 14:00 | N | Y | replace breaker CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p 2952 (320p Keephills) | 2016-03-08 08:30 | 2016-03-08 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 138s 552 (138s Windy Flats) | 2016-03-08 09:00 | 2016-03-08 17:00 | N | Y | replacement of under voltage relay 27.5 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2016-03-08 10:00 | 2016-03-09 12:00 | N | N | spring transmission line washing potheads | Line |  |  | For Information Only
ALTALINK | 310p 552 (310p Sundance) | 2016-03-08 12:30 | 2016-03-08 14:00 | N | Y | replace defective gas density gauges | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2016-03-08 13:00 | 2016-03-09 14:00 | N | N | spring transmission line washing potheads | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2016-03-08 14:00 | 2016-03-09 15:00 | N | N | spring transmission line washing potheads | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2016-03-09 07:00 | 2016-03-09 19:00 | N | N | customer request | Transformer |  |  | For Information Only
TRANSALTAW, ALTALINK, VISIONREQ | 354s DVAR1 (354s Summerview),354s DVAR2 (354s Summerview),528s TDVAR1 (528s Blue Trail Wind Farm),528s TDVAR2 (528s Blue Trail Wind Farm),528s TDVAR3 (528s Blue Trail Wind Farm),418s Ardenville DVAr | 2016-03-09 08:00 | 2016-03-09 16:00 | N | N | maintenance on DVARS | Shunts, Transformer
ALTALINK | 89s 1352 (89s Ellerslie) | 2016-03-09 08:30 | 2016-03-09 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 138s 352 (138s Windy Flats) | 2016-03-09 09:00 | 2016-03-10 17:00 | N | Y | remove gas, replace pressure gauge and replace SF6 Gas | Circuit Breaker |  |  | 240 kV
ALTALINK | 172L (15s Fort Macleod - 172L1251) | 2016-03-09 12:00 | 2016-03-09 15:00 | N | N | remove mobile from 172L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 237s T1 (237s Foothills) | 2016-03-10 07:00 | 2016-03-11 17:00 | N | Y | top up transformer oil through conservator tank | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28),42s 28 (42s Sarcee) | 2016-03-10 08:00 | 2016-03-10 12:00 | N | Y | spring substation washing | Transformer, Line, Circuit Breaker |  |  | Creates Radial Feeds
BLACKSPRING | 485s C1 (485s Blackspring) | 2016-03-10 08:00 | 2016-03-10 17:00 | N | N | finish installation of replacement bus bars and isolators in Cap Bank 1 | Shunts |  |  | For Information Only
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2016-03-10 08:30 | 2016-03-10 13:00 | N | Y | 240 kV switch repair/adjustment | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 535s 6052 (535s Joffre) | 2016-03-10 10:00 | 2016-03-10 15:00 | N | N | breaker repair | Circuit Breaker |  | 535s6052  GOI has been added to the schedule on March 10, 2016 1000 - 1500. This is an urgent request as 535s6052 has a leak and is getting low on gas where the breaker may trip | For Information Only
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2016-03-10 12:00 | 2016-03-10 16:00 | N | N | spring substation washing | Transformer, Line |  |  | Creates Radial Feeds
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2016-03-11 08:00 | 2016-03-11 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 2 - 2.83L tap),2.83L (ENMAX 13 - 2.83L tap) | 2016-03-11 22:00 | 2016-03-12 04:00 | N | N | 12st bridge transmission work | Line
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2016-03-12 | 2016-03-13 06:00 | N | N | spring transmission line washing | Line, Transformer | 1. Studied with UofC generation = 0 MW (refer to Internal Comment 1). 1. Higher UofC generation may alleviate amount of overload on 36.5TR for next contingency. - no overload concerns for loss of 21.4TR contingency on 36.5TR due to the load transfer. |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2016-03-12 04:00 | 2016-03-22 22:00 | N | N | 12st bridge transmission work, 5B138-2.83 HLR HV inspection | Line | Studied with 1215 MW wind - no concerns. |  | For Information Only
ALTALINK | 3L (272s Springbank - 3L147) | 2016-03-12 07:00 | 2016-03-21 10:00 | N | N | line re-build | Line | Studied with BOW = 150 MW and 35 MW - no concerns. |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 37.81L (ENMAX 38 - ENMAX 37),ENMAX 37 B138-37.81 (ENMAX 37),ENMAX 38 B138-37.81 (ENMAX 38) | 2016-03-12 08:00 | 2016-03-12 16:00 | N | N | add isolation switch to relay BF outputs and change out insulators | Line, Circuit Breaker | Studied with Crossfield net generation =0 MW, Balzac net generation = 0 MW, CEC net generation = 0 MW - no concerns. |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2016-03-12 08:00 | 2016-03-12 12:00 | N | N | spring substation washing | Line, Transformer | Studied with Cavalier net generation = 120 MW, Balzac net generation = 70 MW, Carseland net generation = 80 MW, CEC = 0 MW, Shepard net generation = 600 MW, wind generation = 1160 MW - no concerns. |  | For Information Only
ALTALINK | 33s6 (33s Spray) | 2016-03-13 08:00 | 2016-03-20 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 36.5TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2016-03-13 08:00 | 2016-03-13 12:00 | N | N | spring substation washing | Line, Transformer | 5. Studied with UofC generation offline. |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36) | 2016-03-13 12:00 | 2016-03-13 16:00 | N | Y | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary),5s 7 (5s East Calgary),5s C4 (5s East Calgary) | 2016-03-14 | 2016-03-14 17:00 | N | N | breaker POW settings change | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2016-03-14 07:00 | 2016-03-21 11:30 | N | N | replace conductor. this has been deemed an emergency repair | Line |  | Replace conductor. This has been deemed an emergency repair. | Pre-Condition
ATCO | 772s 601T (772s Youngstown) | 2016-03-14 07:00 | 2016-03-18 17:00 | N | N | upgrade 601T transformer protection | Transformer |  | Upgrade 601T transformer protection, all 772s 25kV load must be transferred to adjacent substations , a portable AC genset will be required to maintain site stn service. | For Information Only
ATCO | 845s 705C (845s Big Mountain),845s 701 (845s Big Mountain),845s 707 (845s Big Mountain),845s 705 (845s Big Mountain) | 2016-03-14 07:00 | 2016-03-24 12:00 | N | N | replace protection and install new control | Shunts, Circuit Breaker |  | Replace 705C protection/Install new control cables, 705C 30MVAR Cap unavailable for area VAR support, 144kV ring open @ 845s | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 1098L (805s Jasper - Poundmaker) | 2016-03-14 07:00 | 2016-03-20 17:00 | N | Y | operational checks | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 604L (149s Nisku - 155s Blackmud),149s 604 (149s Nisku) | 2016-03-14 07:00 | 2016-03-14 17:00 | N | N | required for Bus protection upgrade | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 749s 701T (749s Flyingshot Lake),749s 706 (749s Flyingshot Lake),749s 701 (749s Flyingshot Lake) | 2016-03-14 07:00 | 2016-03-27 17:30 | N | Y | protection changes | Transformer, Circuit Breaker |  | Protection changes to 701, 706, 501, 502, 503, All 25kV load transferred to 702T and/or adjacent subs, 144kV bus @ 749s will be open, 5L333 Aquatera Utilities generator must be offline for duration of outage, 500MT1 and Stn Service # 1 will be OOS. | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s CK726 (987s Clover Bar) | 2016-03-14 07:00 | 2016-03-15 17:00 | N | N | bushing cleaning | Circuit Breaker, Line |  |  | Pre-Condition
ATCO, ALTALINK | 923L (2075s Newell - 356s Milo),2075s 905 (2075s Newell),2075s 906 (2075s Newell) | 2016-03-14 08:00 | 2016-03-14 16:00 | N | Y | test & Operate 21A/9L923 relay trips to breakers 905 and 906 | Circuit Breaker, Line |  | Test & Operate 21A/9L923 Relay trips to breakers 905 and 906, 9L923D1 and 906B will be opened to prevent system load swings, EATL will be limited to 650MW during this work, work done in conjunction with CSP 2-36218. | 240 kV, Pre-Condition
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood),706L (54s Fort Saskatchewan - 706L72B),54s Fort Saskatchewan 138 kV West Bus | 2016-03-14 08:00 | 2016-03-17 17:00 | N | N | replace 54s35 | Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie) | 2016-03-14 08:00 | 2016-03-18 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8),Enmax 8 B138-3A0 (ENMAX 8),Enmax 8 B138-4A0 (ENMAX 8) | 2016-03-14 08:00 | 2016-03-15 16:00 | N | N | GIS switch maintenance on 4a52, 4a51, 3a10 and 3a51 | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 409s 20 (409s Shell Scotford) | 2016-03-14 08:30 | 2016-03-14 13:00 | N | N | trip checks from new T3 protection | Circuit Breaker
ALTALINK | 28s R1 (28s West Brooks) | 2016-03-14 09:00 | 2016-03-14 18:00 | N | Y | 28s44 POW relay installation | Shunts |  |  | 240 kV, Pre-Condition
BCH | 1L275 (799s Coleman - Natal) | 2016-03-14 09:00 | 2016-03-20 17:00 | N | Y | structure replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ATCO | 710s 703 (710s Vermilion) | 2016-03-14 09:00 | 2016-03-24 16:00 | N | N | breaker maintenance | Circuit Breaker |  | 703 breaker will be out of service for the duration of work. 7L65 line is scheduled to be out of service by line crew for repairs at the same time. Permit # 2-35407 | For Information Only
ALTALINK | 922L (310p Sundance - 17s Benalto),310p 1952 (310p Sundance),310p 2052 (310p Sundance) | 2016-03-14 10:00 | 2016-03-17 15:00 | N | Y | replace PTs on CVT-L7 & 310p133 junction box | Line, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 879L (368s Burdett - 523s Bullshead),523s 879 (523s Bullshead) | 2016-03-14 10:00 | 2016-03-14 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 69s T5 (69s North Barrhead) | 2016-03-14 13:00 | 2016-03-17 17:00 | N | N | bushing replacement (25kV & 138kV) & 69sT5 138kV LAs | Transformer |  |  | For Information Only
ALTALINK | 410s 352 (410s Josephburg) | 2016-03-14 13:00 | 2016-03-15 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 63s 652 (63s Red Deer),63s Red Deer 240kV South Bus | 2016-03-15 07:00 | 2016-03-18 10:00 | N | Y | 240kV breaker replacement,functional trips to 240kv breakers and breaker fail relay | Bus, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2016-03-15 07:00 | 2016-03-15 17:00 | N | N | pole change structure no 65509 | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku),149s 780N (149s Nisku) | 2016-03-15 07:00 | 2016-03-15 17:00 | N | N | bus protection upgrade & 149s19 switch adjustments | Line, Circuit Breaker |  |  | Overload, Over/Under Voltage
ALTALINK | 650s 852 (650s Hansman Lake) | 2016-03-15 08:00 | 2016-03-17 08:00 | N | Y | replace breaker CTs | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1203L (320p Keephills - 510s Sunnybrook) | 2016-03-15 08:00 | 2016-03-16 18:00 | N | Y | bus corona deficiency corrections, 510s1203 airbreak status to HVDC system | Line |  |  | Pre-Condition, Overload, 500 kV
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2016-03-15 08:00 | 2016-03-15 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat),523s 880 (523s Bullshead) | 2016-03-15 08:00 | 2016-03-15 17:00 | N | N | 138kV circuit breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 2029s 1200SST2 (2029s Heathfield) | 2016-03-15 08:00 | 2016-04-26 16:00 | N | Y | emergency excavation near 25kV trench to repair water line | Transformer
ATCO, ALTALINK | ALC02L (409s Shell Scotford - 879s Scotford Upgrader),409s 110 (409s Shell Scotford) | 2016-03-15 08:30 | 2016-03-15 15:00 | N | Y | trip checks from new T3 protection | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 829s 701T (829s Boucher Creek) | 2016-03-15 09:30 | 2016-03-15 15:30 | N | N | 829S emergency replacement - commission resistor - CT commission test | Transformer |  | 829S Emergency Racid Replacement - Commission Resistor CT Commission test the NGR CT for emergency replacement relay 829S OOS for duration of the work We need to test the CT circuit on the neutral grounding resistor in order to verify the ratio and polarity for proper connection to the emergency replacement relay. | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2016-03-16 07:00 | 2016-03-17 17:00 | N | N | bushing cleaning | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s T1 (74s Janet),901AL (64s East Crossfield - 901L tap),901L (63s Red Deer - 901AL tap),901L (74s Janet - 901AL tap),74s 2052 (74s Janet),74s 552 (74s Janet),74s 2752 (74s Janet),74s 2452 (74s Janet),74s 2552 (74s Janet),74s Janet 240kV Bus 1 | 2016-03-16 07:00 | 2016-03-16 17:00 | N | Y | replace string insulators | Bus, Line, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 251s SR2 (251s Whitla) | 2016-03-16 08:00 | 2016-03-16 17:00 | N | Y | high temp alarm repairs on cap bank | Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2016-03-16 08:00 | 2016-03-16 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 8.5TR (ENMAX 8),8.6TR (ENMAX 8),ENMAX 8 138kV Bus | 2016-03-16 08:00 | 2016-03-17 16:00 | N | N | GIS switch maintenance on 2a10 | Transformer, Bus |  |  | Pre-Condition
ENMAX | 2.1TR (ENMAX 2) | 2016-03-16 08:00 | 2016-03-17 16:00 | N | N | replace winding temperature relay | Transformer |  |  | For Information Only
ALTALINK | 857L (409s Shell Scotford - 410s Josephburg),409s 857W (409s Shell Scotford) | 2016-03-16 08:30 | 2016-03-16 15:00 | N | N | trip checks from new T3 protection | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2016-03-16 08:30 | 2016-03-16 17:00 | N | N | repair/replace faulty 52HS eevice | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 410s 452 (410s Josephburg) | 2016-03-16 09:00 | 2016-03-17 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2016-03-16 09:00 | 2016-03-16 12:00 | N | N | conenct 474s mobile to 805L | Line |  |  | Over/Under Voltage, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),33.84L. 33.2TR. 33PT138-Z31 | 2016-03-16 12:00 | 2016-03-16 16:00 | N | N | spring substation washing | Line, Terminal Equipment |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 964s T3 (964s Pigeon Lake) | 2016-03-16 17:01 | 2016-03-22 08:00 | N | N | install mobile and bird coverup on 25 kV bus | Transformer |  |  | For Information Only
ALTALINK | 149s C1 (149s Nisku) | 2016-03-17 07:00 | 2016-03-17 17:00 | N | N | required for bus protection upgrade | Shunts |  |  | For Information Only
ATCO, SUNCOR | 6L32 (29EDD-1 Millennium - 737s Horseshoe) | 2016-03-17 08:00 | 2016-03-17 20:00 | N | N | relay maintenance work on 6L32 | Line
REDDEER | 209S Timberlands | 2016-03-17 08:00 | 2016-03-19 16:00 | N | N | 209s Timberlands In-service date is Mar 17. 768L (87s Gaetz  217s North Red Deer) will be replaced with 768L (209s Timberlands -217s North Red Deer) and 464L (87s Gaetz - 209s Timberlands). | Station
ALTALINK | 250p11 (250p Bighorn) | 2016-03-17 08:00 | 2016-03-17 12:00 | N | Y | maintneance | Switch |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn) | 2016-03-17 12:00 | 2016-03-17 16:00 | N | Y | maintneance | Switch |  |  | Restricts Generation
ALTALINK | 63s 652 (63s Red Deer) | 2016-03-17 19:00 | 2016-03-29 15:00 | N | Y | 240kV breaker replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 8.1TR (ENMAX 8),Enmax 8 MD138-7A11 (ENMAX 8),Enmax 8 MD138-1A1 (ENMAX 8),ENMAX 8 138kV Bus | 2016-03-18 08:00 | 2016-03-18 16:00 | N | N | maintenance on switch 1a15 - partial bus outage | Switch, Bus, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2016-03-19 00:01 | 2016-03-20 06:00 | N | N | spring transmission line washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2016-03-19 08:00 | 2016-03-19 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2016-03-19 12:00 | 2016-03-19 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2016-03-20 08:00 | 2016-03-20 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2016-03-20 12:00 | 2016-03-20 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s5 MH69-T51 (MH69s5 NE Crescent Height),MH69s5 MH69-T52 (MH69s5 NE Crescent Height) | 2016-03-21 07:00 | 2016-03-24 17:00 | N | N | tap changer maintenance | Transformer |  |  | For Information Only
EPCOR | 72LH8 (Hardisty - 803s Lambton),Hardisty H726 (Hardisty Epcor) | 2016-03-21 07:00 | 2016-03-22 17:00 | N | N | bushing cleaning | Circuit Breaker, Line |  |  | Pre-Condition, Overload
EPCOR | 511s Victoria T1 (511s Victoria) | 2016-03-21 07:00 | 2016-03-21 12:00 | N | N | relay op checks | Transformer
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2016-03-21 07:00 | 2016-03-23 17:00 | N | Y | op checks & setting update | Line |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Poundmaker T2 (Poundmaker) | 2016-03-21 07:00 | 2016-03-27 17:00 | N | Y | op checks | Transformer |  |  | 240 kV, For Information Only
TRANSALTA | 59s 603 (59s Peigan) | 2016-03-21 08:00 | 2016-04-07 17:00 | N | N | associated redundant protections will be removed from service one at a time as part of the trip testing | Circuit Breaker |  | Exchange breaker with 59s616.
ALTALINK | 753L (65s High River - 253s Blackie) | 2016-03-21 08:00 | 2016-03-23 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition
ENMAX | 41.2TR (ENMAX 41) | 2016-03-21 08:00 | 2016-04-01 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2016-03-21 08:00 | 2016-03-27 16:00 | N | N | City of Calgary waterworks digging around line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | Enmax 8 B138-1A0 (ENMAX 8),Enmax 8 MD138-7A11 (ENMAX 8),ENMAX 8 138kV Bus | 2016-03-21 08:00 | 2016-03-21 16:00 | N | N | GIS switch maintenance on 1a15 | Switch, Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
TRANSALTA, ALTALINK | 59s T1 (59s Peigan),1049L (59s Peigan - 138s Windy Flats),59s Peigan 240kV Bus 1,59s Peigan 138kV Bus | 2016-03-21 08:00 | 2016-03-24 17:00 | N | Y | replace 138 kV PTs, 138 kV Bus differential protection and trip tests to 59s1152, 59s752 & 59s352 | Bus, Transformer, Line | Associated redundant protections will be removed from service one at a time as part of the trip testing. Affects 1049L (59s - 138s) |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 902L (19s Wabamun - 310p Sundance),310p 752 (310p Sundance),310p 852 (310p Sundance) | 2016-03-21 10:00 | 2016-03-24 15:00 | N | Y | replace PTs and 310p122 junction box | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 171s 808E (171s Redwater),808L (171s Redwater - 808L75C) | 2016-03-21 10:30 | 2016-03-21 18:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (14s Devon - 155s Blackmud),155s 739 (155s Blackmud) | 2016-03-21 10:30 | 2016-03-21 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 258s 552 (258s Dow Hydrocarbons) | 2016-03-21 10:30 | 2016-03-21 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 71s C2 (71s Lamoureux),71s 1052 (71s Lamoureux) | 2016-03-21 10:30 | 2016-03-22 17:00 | N | N | repair/replace faulty 52HS device | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 331s T1 (331s Ponoka),421L (331s Ponoka - 288s Wolf Creek),331s Ponoka 138kV East Bus | 2016-03-21 11:00 | 2016-03-22 17:00 | N | N | T1 maintenance & 331s18 couple/decouple issue | Transformer, Line, Bus |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 511s Victoria T2 (511s Victoria) | 2016-03-21 12:01 | 2016-03-21 16:00 | N | N | op checks | Transformer
EPCOR | E511s VictoriaT3 (511s Victoria) | 2016-03-22 07:00 | 2016-03-22 12:00 | N | N | op checks | Transformer |  |  | For Information Only
ALTALINK | 89s 652 (89s Ellerslie) | 2016-03-22 08:00 | 2016-03-22 16:00 | N | Y | correct deficiency related to the 89s652 C60 SCADA alarms, install cable and test redundant recloser status | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 11.4TR (ENMAX 11) | 2016-03-22 08:00 | 2016-03-23 16:00 | N | N | failed differential protection relay | Transformer |  |  | For Information Only
ATCO | 2029s ACF21 (2029s Heathfield) | 2016-03-22 08:00 | 2016-03-22 16:00 | N | Y | replace relay contacts | Shunts |  | 2029S - ACF21 replace K8 and K75 Relays ACF21 will be out of service for duration of work Replace K8 and K75 relays on breaker 1222 as they have had sticking issues in the past. Operate the breaker a few times to test the function of the new contacts. | For Information Only, 500 kV
ALTALINK | 42s C2 (42s Sarcee) | 2016-03-22 08:30 | 2016-03-22 17:00 | N | Y | correct unbalance alarm on cap bank | Shunts |  |  | 240 kV, For Information Only
ALTALINK | 13s 1352 (13s Deerland) | 2016-03-22 08:30 | 2016-03-22 18:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2016-03-22 09:00 | 2016-03-22 17:00 | N | N | remove mobile from 805L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 651s T2 (651s Kirby) | 2016-03-22 09:00 | 2016-03-22 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 258s 652 (258s Dow Hydrocarbons) | 2016-03-22 09:00 | 2016-03-23 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 384s T2 (384s Keystone) | 2016-03-22 09:00 | 2016-03-22 17:00 | N | N | test airbreak auxiliary switches to Z relay functional | Transformer |  |  | For Information Only
EPCOR | E511s VictoriaT4 (511s Victoria) | 2016-03-22 12:01 | 2016-03-22 16:00 | N | N | op checks | Transformer |  |  | For Information Only
ENMAX | 2.83L (ENMAX 13 - ENMAX 2) | 2016-03-22 22:00 | 2016-03-23 04:00 | N | N | ENMAX maintenance | Line
ENMAX | 2.83L (ENMAX 13 - ENMAX 2) | 2016-03-22 22:00 | 2016-03-23 04:00 | N | N | 12st bridge transmission work | Line |  |  | For Information Only
EPCOR | Woodcroft W724 (Woodcroft) | 2016-03-23 07:00 | 2016-03-24 17:00 | N | N | bushing cleaning | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 331s T2 (331s Ponoka),422L (331s Ponoka - 288s Wolf Creek),331s Ponoka 138kV East Bus,331s 422 (331s Ponoka) | 2016-03-23 08:00 | 2016-03-23 17:00 | N | N | switch maintenance | Line, Circuit Breaker, Transformer, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 14s T1 (14s Devon) | 2016-03-23 08:00 | 2016-03-23 13:00 | N | N | techs to complete standard relay maintenance on 50/51/T1-81 | Transformer |  |  | For Information Only
ALTALINK | 251s 252 (251s Whitla) | 2016-03-23 08:30 | 2016-03-23 17:00 | N | Y | repair breaker leak | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 13s 1452 (13s Deerland) | 2016-03-23 08:30 | 2016-03-23 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 30.81L (42s Sarcee - ENMAX 30),42s 30 (42s Sarcee) | 2016-03-23 09:00 | 2016-03-23 17:00 | N | Y | breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 14s T3 (14s Devon) | 2016-03-23 13:00 | 2016-03-23 17:00 | N | N | techs to adjust contact input threshold | Transformer |  |  | For Information Only
ALTALINK | 17s 11 (17s Benalto),17s 10 (17s Benalto),17s 7 (17s Benalto),17s 6 (17s Benalto),17s 1 (17s Benalto),17s Benalto 240 kV North Bus 1,17S T3 (17s Benalto) | 2016-03-23 15:00 | 2016-03-24 17:00 | N | Y | test energize new breaker 17s7 | Bus, Transformer, Circuit Breaker | 30 days waived due to relation with 17s 7 forced outage. |  | 240 kV, For Information Only
EPCOR | 987s C2401 (987s Clover Bar) | 2016-03-24 07:00 | 2016-03-24 17:00 | N | Y | op checks | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 845s 702 (845s Big Mountain) | 2016-03-24 12:01 | 2016-03-24 16:00 | N | N | test and operate breaker | Circuit Breaker | PH TMR is required due to 749s706, 749s701, and 749s701T (749s Flyingshot Lake) outage on 3/14 - 3/27. | Once 705C/144kV ring at 845s placed back in service (permit 2-32705), a Test and Operate will be reqd on breaker 702 to complete wiring and testing of the new breaker fail scheme for 50BF/701, the 144kV ring will be open during this permit.. Actual work will only be 1 day within the allotted window. | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2016-03-26 08:00 | 2016-03-26 16:00 | N | N | ENMAX maintenance (substation washing 32.83-wash structure 1) | Line
AESO, ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2016-03-26 08:00 | 2016-03-26 16:00 | N | N | repair hotspot on SW91 at 5 sub | Line, Transformer |  |  | For Information Only
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2016-03-26 08:00 | 2016-03-26 16:00 | N | N | substation washing 32.83-wash structure 1 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2016-03-27 08:00 | 2016-03-27 16:00 | N | N | ENMAX maintenance (spring substation washing) | Line
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2016-03-27 08:00 | 2016-03-27 16:00 | N | N | spring substation washing | Line, Shunts, Transformer |  |  | For Information Only
Medicine Hat | MH69s6 MH69-T31 (MH69s6 Riverview),MH69s6 MH69-T32 (MH69s6 Riverview),MH69s6 MH69-T33 (MH69s6 Riverview) | 2016-03-28 07:00 | 2016-04-01 17:00 | N | N | tap changer maintenance | Transformer |  | From March 28 to April 1, 2016 the City of Medicine Hat will be taking outages on substations transformer T-31, 32 & 33 located at MH69S-3 Southridge Substation. Scope of work will be to complete tap changer maintenance and high voltage power factor testing of each unit. Only one transformer will be out of service at a time, once work is completed on T-33 crews will switch over to T-31 and then T-32. Outage time will be estimated at approximately 48 hours per unit , outages will start at 07:00 on March 28, 2016. | For Information Only
IMPERIALOIL, ATCO | 7L105 (837s Mahihkan - 909s Mahno),7L161 (909s Mahno - 942s Nabiye) | 2016-03-28 08:00 | 2016-04-08 17:00 | N | Y | emergency replacement of 144kV cable | Line |  | emergency replacement of 144kV cable on M1 service in Nabiye Substation 942S | Pre-Condition, Restricts Generation
ALTALINK | 434L (65s High River - 237s Foothills),65s 434(65s Highriver) | 2016-03-28 09:00 | 2016-03-28 17:00 | N | N | Foothills 138kV project: replace breaker tank heaters | Line, Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 987s C2403 (987s Clover Bar) | 2016-03-29 07:00 | 2016-03-29 17:00 | N | Y | operational checks | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker),Poundmaker 2403 (Poundmaker),Poundmaker 2404 (Poundmaker) | 2016-03-29 07:00 | 2016-04-03 17:00 | N | Y | 930L operational checks | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie) | 2016-03-29 08:00 | 2016-04-01 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition
ATCO | 848s 606T (848s Ruth Lake) | 2016-03-29 08:00 | 2016-04-25 16:00 | N | N | 606T Transformer Swap | Transformer |  | 606T Transformer Swap 25kv load to be transferred to alternate source. Isolate / Ground on 606T Disconnect Risers / Control Wiring Remove Existing 606T Place New 606T Reconnect Control Wiring / Risers Commission Return Transformer Protection to Normal / Test Return 606T to Service. | For Information Only
ENMAX | 24.2TR (ENMAX 24) | 2016-03-29 08:00 | 2016-03-31 16:00 | N | N | leak repairs | Transformer |  |  | For Information Only
TRANSALTA | 59s T1 (59s Peigan),59s 616 (59s Peigan) | 2016-03-29 08:00 | 2016-04-07 17:00 | N | Y | exchange breaker with 59s603 | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2016-03-29 08:00 | 2016-03-30 16:00 | N | N | lock & unlock coil circuit modification on 9B138-9.80 & 31B138-9.80 | Line |  |  | For Information Only
SHELL | 402s T1 (402s Shell Expansion 1) | 2016-03-29 08:00 | 2016-03-29 16:00 | N | N | Shell requires 701T in the 402s substation isolated and high side grounds installed for maintenance on 52-1A cell | Transformer |  | Shell requires 701T in the 402S Substation isolated and High Side Grounds installed for maintenance on 52-1A cell | For Information Only
ATCO | 819s 701 (819s Whitby Lake),7L92 (819s Whitby Lake - 7L92D2) | 2016-03-29 08:00 | 2016-03-30 16:00 | N | N | 813s relay replacement | Circuit Breaker, Line |  | 21A Relay Replacement, 701CT Ratio Change, 7L92 will be open ended at 819s, 956s will be radial fed from 709s | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 108s 152 (108s Amelia) | 2016-03-29 09:00 | 2016-03-29 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan),166s 707X (166s Dow Chem Fort Saskatchewan) | 2016-03-29 10:30 | 2016-03-29 18:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Overload, Restricts Generation
ALTALINK | 63s T2 (63s Red Deer),901AL (64s East Crossfield - 901L tap),901L (63s Red Deer - 901AL tap),901L (74s Janet - 901AL tap),63s 2752 (63s Red Deer),63s 952 (63s Red Deer),63s 552 (63s Red Deer),63s 352 (63s Red Deer),63s 652 (63s Red Deer),63s Red Deer 240kV South Bus | 2016-03-29 15:00 | 2016-04-06 17:00 | N | Y | replace 63s901X switch and 63s39 PT's | Transformer, Line, Bus, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1452 (310p Sundance),310p 1552 (310p Sundance) | 2016-03-29 16:00 | 2016-04-01 08:00 | N | Y | zone will be expanded for AML crews to repair switch | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALBIAN | 920s 902T (920s Jackpine) | 2016-03-30 07:00 | 2016-04-03 17:00 | N | Y | customer generated outage (updating protection ) | Transformer |  | Customer generated outage (updating protection ) | 240 kV
EPCOR | 987s C2405 (987s Clover Bar) | 2016-03-30 07:00 | 2016-03-30 17:00 | N | Y | op checks | Circuit Breaker |  |  | 240 kV
ATCO | 7L20 (845s Big Mountain - 810s Dome Cutbank),845s 710 (845s Big Mountain),845s 703 (845s Big Mountain) | 2016-03-30 07:00 | 2016-04-10 17:30 | N | Y | replace line protection and add breaker fail protection | Line, Circuit Breaker |  | Replace line protection and add breaker fail protection. 740s HRM radial fed via 7L80, 7L80 limited to winter operating limit of 145MW. | Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | Enmax 8 B138-1A0 (ENMAX 8),Enmax 8 MD138-7A11 (ENMAX 8),ENMAX 8 138kV Bus | 2016-03-30 08:00 | 2016-03-30 16:00 | N | N | GIS switch maintenance on 1a15 | Bus, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 184s 34 (184s Petro Canada Edmonton) | 2016-03-30 09:00 | 2016-03-30 18:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 792L (191s N.W. Cardiff - 92s Viscount),92s 792 (92s Viscount) | 2016-03-30 09:00 | 2016-03-30 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 946s 909 (946s Oakland) | 2016-03-30 09:00 | 2016-03-31 17:00 | N | N | real time SF6 pressure adjustment | Circuit Breaker |  |  | 240 kV
EPCOR | 987s C2406 (987s Clover Bar) | 2016-03-31 07:00 | 2016-03-31 17:00 | N | Y | op checks | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 720s Wabasca RTU/SCADA | 2016-03-31 08:00 | 2016-04-04 16:00 | N | N | emergency repair 720s RTU | Terminal Equipment |  | We have had repeated failure on the RTU at 720S Wabasca and are planning to take the RTU off line to troubleshoot and repair. We have a permit # 2-37075 set up for this work from Mar 31 (8:00) to Apr 4 (16:00), 2016. The RTU will be off line for several short 1-2 minutes periods over the time scheduled. Thanks Freman Johnstone Transmission Control Senior Scheduler Vegreville Ab E mail "scheduling@atco.com" 1-780-632-5950 / 5951/ 5949 1-780-632-5742 FAX | Affects Visibility
ENMAX | 24.81L (ENMAX 31 - ENMAX 24),ENMAX 31 B138-24.81 (ENMAX 31),ENMAX 24 B138-24.81 (ENMAX 24) | 2016-03-31 08:00 | 2016-04-01 16:00 | N | N | lock and unlock coil circuit modification on 24B138-24.81 & 31B138-24.81 | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2016-03-31 08:00 | 2016-03-31 17:00 | N | N | urgent crossarm replacement on structures 371, 241, 255 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.8TR (ENMAX 1) | 2016-03-31 08:00 | 2016-03-31 16:00 | N | N | LV breaker maintenance 1B8-1.8TR | Transformer |  |  | For Information Only
ALTALINK | 827L (121s Brooks - 28s West Brooks),121s 827W (121s Brooks) | 2016-03-31 08:00 | 2016-03-31 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 7L129 (526s Buffalo Creek - 918s Bauer),526s 152 (526s Buffalo Creek) | 2016-03-31 08:00 | 2016-03-31 12:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2016-03-31 09:00 | 2016-03-31 19:00 | Y | Y | maintenance on 1L274/887L transfer trip RAS | Line |  |  | For Information Only
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek),48s 887X (48s Pocaterra) | 2016-03-31 09:00 | 2016-03-31 19:00 | N | Y | BC Hydro work | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge),184s 705W (184s Petro Canada Edmonton) | 2016-03-31 09:00 | 2016-03-31 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s T4 (370s North Lethbridge) | 2016-03-31 10:00 | 2016-04-14 07:30 | N | N | T4 protections work for 370s40 and 370s30 breaker replacement project | Transformer
ALTALINK, ATCO | 7L50 (526s Buffalo Creek - 7L50D2),526s 252 (526s Buffalo Creek) | 2016-03-31 12:01 | 2016-03-31 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
SUNCOR | 29PL6-5 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2016-03-31 14:00 | 2016-04-17 20:00 | N | N | 5 yr PM maintenance and testing, relay upgrade | Line |  |  | For Information Only
EPCOR | 987s T3 (987s Clover Bar) | 2016-04-01 07:00 | 2016-04-01 17:00 | N | Y | op checks | Transformer |  |  | For Information Only
ENMAX | 32.3TR (ENMAX 32) | 2016-04-01 08:00 | 2016-04-01 16:00 | N | N | adjust oil level in LTC conservator - inspect the oil level gauge float | Transformer |  |  | For Information Only
ALTALINK | 198s T2 (198s Blackfalds) | 2016-04-02 07:00 | 2016-04-05 17:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39),ENMAX 39 B138-22.81 (ENMAX 39) | 2016-04-02 08:00 | 2016-04-02 16:00 | N | N | breaker inspection | Line, Transformer, Circuit Breaker |  |  | For Information Only
ATCO | 6L79 (711s Willingdon - 707s St.Paul) | 2016-04-03 07:30 | 2016-04-05 17:00 | N | N | Stringing new 144kv Line over 6L79 | Line |  | Stringing new 144kv Line over 6L79 | For Information Only
ENMAX | 2.83L (ENMAX 13 - 2.83L tap),ENMAX 13 B138-2.83 (ENMAX 13) | 2016-04-03 08:00 | 2016-04-03 16:00 | N | N | Doble test breaker, PT's and CT's | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1),Enmax 1 B138-5A0 (ENMAX 1),Enmax 1 B138-4A0 (ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2016-04-03 08:00 | 2016-04-06 16:00 | N | N | overhead install for Sarcee Glenmore interchange | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 162L (415s Drywood - 229s Glenwood),415s 146E (415s Drywood) | 2016-04-03 16:00 | 2016-04-08 17:00 | N | N | breaker replacement & arrestor replacement | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
PANC, ALTALINK | PCES01L (PCES01S Cavalier - 428s Namaka),428s 23 (428s Namaka) | 2016-04-04 05:00 | 2016-04-07 10:00 | N | Y | customer requested outage | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
EPCOR | 330p 806 (330p Genesee) | 2016-04-04 07:00 | 2016-04-05 17:00 | N | N | CT secondary isolation | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader),879s 352 (879s Scotford Upgrader),879s 702T (879s Scotford Upgrader),879s Bus 2 (879s Scotford Upgrader) | 2016-04-04 07:00 | 2016-04-10 17:30 | N | Y | ALC02L line protection relay upgrade | Transformer, Circuit Breaker, Line, Bus |  | ALC-02L Line Protection relay upgrade, add new 702PTY2 secondary disconnect switch. ALC-02L outage is being planned in conjunction with AML ALC-02L line outage for protection relay upgrade @ AML 409s, 879s will be radial fed via EX1-O1L, 701T @ 879s will carry all Shell generation/load (Shell generation must be limited so as not to exceed 701T base MW ratings). | Pre-Condition, Restricts Generation, Creates Radial Feeds
Medicine Hat | MH69s6 MH69-T61(MH69s6 Riverview),MH69s6 MH69-T62 (MH69s6 Riverview) | 2016-04-04 07:00 | 2016-04-06 19:00 | N | N | tap changer maintenance and high voltage testing | Transformer |  | From April 4 to April 6, 2016 the City of Medicine Hat will be taking outages on substations transformer T-61 & 62 located at MH69S-6 Riverview Substation. Scope of work will be to complete tap changer maintenance and high voltage power factor testing of each unit. Only one transformer will be out of service at a time, once work is completed on T-61 crews will switch over to T-62. Outage time will be estimated at approximately 30 hours per unit , outages will start at 07:00 on April 4, 2016 and will be completed by 19:00 on April 6, 2016. | For Information Only
EPCOR | 814s T1 (814s Bellamy),Rossdale BR721 (Rossdale) | 2016-04-04 07:00 | 2016-04-04 12:00 | N | Y | breaker operation check | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | 987s T4 (987s Clover Bar) | 2016-04-04 07:00 | 2016-04-04 17:00 | N | Y | Op Checks | Transformer |  |  | For Information Only
ALTALINK | 851L (525s Carseland - 253s Blackie),253s 851W (253s Blackie) | 2016-04-04 08:00 | 2016-04-08 14:00 | N | N | replace 253s851W circuit breaker | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.1TR (ENMAX 26) | 2016-04-04 08:00 | 2016-04-08 16:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ALTALINK | 198s T2 (198s Blackfalds) | 2016-04-04 08:00 | 2016-04-06 16:00 | N | N | In service date: Apr 4th. Transformer replacement. | Transformer
ALTALINK | 648s 749E (648s Metiskow) | 2016-04-04 08:00 | 2016-04-08 07:59 | N | Y | breaker replacement | Circuit Breaker |  | Breaker replacement - will move into bus outage on April 8 to replace risers and energize. Will be closing 648s36 to keep 749L in service. Alternate settings at 899s and 650s. | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 32.1TR (ENMAX 32) | 2016-04-04 08:00 | 2016-04-08 16:00 | N | N | repair oil leak in CT junction box | Transformer |  |  | For Information Only
ALTALINK | 898L (37s North Calder - 92s Viscount),37s 898 (37s North Calder) | 2016-04-04 08:00 | 2016-04-08 17:00 | N | N | 37s breaker replacement | Line, Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 33 B138-33.83 (ENMAX 33),ENMAX 41 B138-33.83 (ENMAX 41) | 2016-04-04 08:00 | 2016-04-20 16:00 | N | N | interchange MacLeod & 162 Ave | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21),ENMAX 21 B138-21.80 (ENMAX 21),42s 21 (42s Sarcee) | 2016-04-04 08:00 | 2016-04-06 16:00 | N | Y | overhead install. Sarcee-Glenmore interchange | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK, ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader),409s 110 (409s Shell Scotford) | 2016-04-04 08:00 | 2016-04-10 17:00 | N | Y | replace 'B' line protection | Circuit Breaker, Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 56L (245s Seebe - 20s Ghost),245s 56E (245s Seebe) | 2016-04-04 09:00 | 2016-04-07 16:00 | N | N | replace breaker control and breaker fail protection | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden),197s 174E (197s Bardo) | 2016-04-04 09:00 | 2016-04-04 11:00 | N | N | required for check 'A' status | Line, Circuit Breaker |  | Check for future 285s DG Addition | Pre-Condition, Over/Under Voltage
ALTALINK | 87s T1 (87s Gaetz),914L (87s Gaetz - 63s Red Deer),87s 2352 (87s Gaetz) | 2016-04-04 10:00 | 2016-04-04 17:00 | N | Y | 240 kV switch maintenance | Transformer, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House),17s 717W (17s Benalto) | 2016-04-04 11:00 | 2016-04-04 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 54 (77s Sagitawah) | 2016-04-04 13:00 | 2016-04-05 17:00 | N | Y | 240kV circuit breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 62s 11 (62s Brazeau) | 2016-04-04 23:00 | 2016-04-08 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2016-04-05 03:00 | 2016-04-05 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 987s CC24 (987s Clover Bar) | 2016-04-05 07:00 | 2016-04-05 17:00 | N | N | Op Checks | Circuit Breaker |  |  | Pre-Condition, Overload
ALTALINK | 753L (65s High River - 253s Blackie) | 2016-04-05 08:00 | 2016-04-06 17:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.1TR (ENMAX 27) | 2016-04-05 08:00 | 2016-04-05 16:00 | N | N | lock & unlock coil circuit modifcation | Transformer |  |  | For Information Only
ATCO | 959S SVC (959s Lanfine) | 2016-04-05 08:00 | 2016-04-08 12:00 | N | Y | 959S Lanfine SVC outage | Shunts |  | 959S Lanfine SVC Outage Request The following works should be done during the outage: 1. Replacement of faulty Thyristor 2. Fixing issue with RTU system 3. Fixing issue with Siemens protection relay 4. Installation and termination of the cable for Calisto. 5. Clean up the site. | 240 kV, For Information Only
SHELL | 402s T2 (402s Shell Expansion 1) | 2016-04-05 08:00 | 2016-04-06 16:00 | N | N | customer requires 702T isolated | Transformer |  | Shell requires 702T in the 402S Substation isolated and High Side Grounds installed for maintenance on 52-1B cell | For Information Only
ALTALINK | 995L (62s Brazeau - 995AL tap),62s 995X (62s Brazeau) | 2016-04-05 08:30 | 2016-04-05 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 435s T1 (435s Bassano) | 2016-04-05 09:00 | 2016-04-05 14:00 | N | N | transformer oil sample | Transformer |  |  | For Information Only
ALTALINK | 17s 92 (17s Benalto) | 2016-04-05 09:00 | 2016-04-05 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm),608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm),138S T2 (138s Windy Flats) | 2016-04-05 11:00 | 2016-04-05 15:00 | N | Y | investigate slow oil leak | Transformer, Line |  |  | 240 kV, Pre-Condition, Restricts Generation
EPCOR | 330P 12TC1 (330p Genesee),330p 805 (330p Genesee) | 2016-04-06 07:00 | 2016-04-07 17:00 | N | Y | CT secondary isolation | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, 500 kV
EPCOR | 987s CCP7214 (987s Clover Bar) | 2016-04-06 07:00 | 2016-04-06 17:00 | N | N | operation checks | Circuit Breaker
ALTALINK | 276s 25 (276s Un Carb Prentiss) | 2016-04-06 08:00 | 2016-04-06 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 848s 606 (848s Ruth Lake) | 2016-04-06 08:00 | 2016-04-11 08:00 | N | N | forced outage | Circuit Breaker
ENMAX | 27.2TR (ENMAX 27) | 2016-04-06 08:00 | 2016-04-06 16:00 | N | N | lock & unlock coil circuit modification | Transformer |  |  | For Information Only
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1) | 2016-04-06 08:00 | 2016-04-06 17:00 | N | Y | urgent repair on Loose helix dampers and conductor damage | Line, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 744L (235s Entwistle - 744L88C),235s 744W (235s Entwistle) | 2016-04-06 08:00 | 2016-04-06 16:00 | N | N | DDR install | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (58s Edson - 178s Cynthia),178s 202N (178s Cynthia) | 2016-04-06 08:30 | 2016-04-06 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 77s 57 (77s Sagitawah) | 2016-04-06 09:00 | 2016-04-07 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s T1 (17s Benalto) | 2016-04-06 09:00 | 2016-04-20 17:00 | N | N | replace T1 arrestors | Transformer |  | Replace T1 arrestors, replace 25kV bus arrestors, replace regulator bypass switch (17s18), replace 25kV switches (17s20, 17s61, 17s62, 17s63, 17s64, 17s65, 17s66, 17s55, 17s72), upgrade metering and protection schemes for 17s46N & 17s2819N, replace 17s70 PT, replace strain insulators between 17s18 & 17s19, replace underground cable between 17s55 & 17s98/17s97, remove 17s98 and associated station service transformers, remove 17s71 & underground cable. | For Information Only
EPCOR | 987s CC721 (987s Clover Bar) | 2016-04-07 07:00 | 2016-04-07 17:00 | N | Y | operation checks | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 253s C1 (253s Blackie),161L (255s Vulcan - 253s Blackie),753L (65s High River - 253s Blackie),851L (525s Carseland - 253s Blackie),253S Blackie 138 kV bus | 2016-04-07 07:00 | 2016-04-11 17:00 | N | N | Blackie Project: adjustment of tension on overhead line conductors | Bus, Line, Shunts |  | Blackie Project: Adjustment of tension on overhead line conductors from the new 851L deadend structure into the existing terminal which supports the 851L. These conductors will be adjusted to be slack spans.Replacement of overhead conductor insulators. Possible adjustment of lower strain bus which is attached to the 851L and the OLD 852L terminal structures.Removal of existing retired 852L conductors from terminal structure. Adjustment of terminal structure down guys. | Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s2 MH69-T21(North Industrial substation) | 2016-04-07 07:00 | 2016-04-08 13:00 | N | N | tap changer maintenance and high voltage power factor testing | Transformer |  | From April 7 to April 8, 2016 the City of Medicine Hat will be taking an outage on substations transformer T-21 located at MH69S-2 North Industrial Substation. Scope of work will be to complete tap changer maintenance and high voltage power factor testing of each unit. Outage time will be estimated at approximately 30 hours, outages will start at 07:00 on April 8, 2016 and will be completed by 13:00 on April 8, 2016. | For Information Only
ALTALINK | 672L (235s Entwistle - 131s Moon Lake),235s 672 (235s Entwistle) | 2016-04-07 08:00 | 2016-04-07 16:00 | N | N | DDR install | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 730L (285s East Camrose - 730L62),285s 730N (285s East Camrose) | 2016-04-07 08:00 | 2016-04-13 08:00 | N | N | breaker replacement | Circuit Breaker, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 775L (535s Joffre - 276s Prentiss),276s 775X (276s Un Carb Prentiss) | 2016-04-07 08:00 | 2016-04-07 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 1038L (138s Windy Flats - 237s Foothills),266s 1038L FSC (266s SC1) | 2016-04-07 08:00 | 2016-04-07 17:00 | N | Y | urgent repair on Loose helix dampers and conductor damage | Line, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 178s 828X (178s Cynthia), 828L (178s Cynthia - 489s Petro Canada Brazeau River) | 2016-04-07 08:30 | 2016-04-07 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 245s 10 (245s Seebe) | 2016-04-07 10:00 | 2016-04-07 12:00 | N | N | replace breaker control and breaker fail protection on 245s56E - trip testing | Circuit Breaker |  |  | Pre-Condition
ATCO | 1035L (2075s Newell - 244s Bowmanton) | 2016-04-07 13:00 | 2016-04-12 16:00 | N | N | forced outage - center phase switch repair | Line |  |  | 240 kV
ALTALINK | 754L (245s Seebe - 754L65A),245s 754W (245s Seebe) | 2016-04-07 15:00 | 2016-04-07 17:00 | N | N | replace breaker control and breaker fail protection on 245s56E - trip testing | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 72VN21 (Namao - 511s Victoria) | 2016-04-08 07:00 | 2016-04-08 17:00 | N | N | operation checks | Line |  |  | Contingency Requires Mitigation, Firm Load Loss
EPCOR | Woodcroft T2 (Woodcroft) | 2016-04-08 07:00 | 2016-04-08 17:00 | N | N | operation checks | Transformer |  |  | For Information Only
EPCOR | 330P 12TC2 (330p Genesee),330p 809 (330p Genesee) | 2016-04-08 07:00 | 2016-04-09 17:00 | N | Y | CT secondary isolation | Circuit Breaker, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
EPCOR | 987s CH722 (987s Clover Bar) | 2016-04-08 07:00 | 2016-04-08 17:00 | N | N | breaker operation checks | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 648s T3 (648s Metiskow),703L (648s Metiskow - 703L),954L (648s Metiskow - 650s Hansman Lake),648s 749E (648s Metiskow) | 2016-04-08 08:00 | 2016-04-08 17:00 | N | Y | replace risers on 648s749E and energize new breaker | Transformer, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21),ENMAX 21 B138-21.80 (ENMAX 21),42s 21 (42s Sarcee) | 2016-04-08 08:00 | 2016-04-10 16:00 | N | Y | underground cable tie in. Sarcee-Glenmore interchange | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28),ENMAX 28 B138-28.80 (ENMAX 28),42s 28 (42s Sarcee) | 2016-04-08 08:00 | 2016-04-10 16:00 | N | Y | Underground cable tie in. Sarcee Glenmore interchange. SWRR PH2 | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Creates Radial Feeds
ATCO | 845s 702 (845s Big Mountain) | 2016-04-08 08:00 | 2016-04-10 20:00 | N | Y | terminate 703BF trip wires in 702 breaker trip circuit and test | Circuit Breaker |  | Terminate 703BF trip wires in 702 breaker trip circuit and test, Confirm permit 2-32708 complete (7L20 back in service) prior to start, 7L13 will be fed from 703 only, 7L45 will be fed from 701 only, 144kV ring bus will be open. | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 719L (256s Harmattan - 719L135X),256s 719N (256s Harmattan),256s1 (256s Harmattan),256s Harmattan 138kV Bus | 2016-04-08 12:00 | 2016-04-10 17:00 | N | N | replace 138kV PT - partial bus outage | Switch, Bus, Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ENMAX | 26.2TR (ENMAX 26) | 2016-04-09 08:00 | 2016-04-09 16:00 | N | N | repair hotspot on 26.2TR high side bushing | Transformer
EPCOR | 987s CGB1 (987s Clover Bar) | 2016-04-10 07:00 | 2016-04-13 17:00 | N | N | op checks & protection cut over | Circuit Breaker |  |  | Restricts Generation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),16.60L (ENMAX 34 - ENMAX 16) | 2016-04-10 08:00 | 2016-04-10 16:00 | N | N | remove birds nest | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2016-04-10 08:00 | 2016-04-10 16:00 | N | N | repair SW84 at 22 Sub | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s 6852 (102s Langdon) | 2016-04-10 08:00 | 2016-04-10 12:00 | N | Y | urgent CT leak repairs | Switch |  |  | 240 kV, For Information Only
EPCOR | Rossdale R721 (Rossdale) | 2016-04-11 07:00 | 2016-04-17 17:00 | N | N | CT replacement | Circuit Breaker |  |  | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2016-04-11 07:00 | 2016-04-11 17:00 | N | N | breaker op checks | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 802 (330p Genesee) | 2016-04-11 07:00 | 2016-04-12 17:00 | N | N | CT secondary isolation | Circuit Breaker |  |  | For Information Only
EPCOR | Woodcroft T3 (Woodcroft) | 2016-04-11 07:00 | 2016-04-11 17:00 | N | N | operation checks | Transformer |  |  | For Information Only
Medicine Hat | MH69s2 MH69-T22(North Industrial Substation) | 2016-04-11 07:00 | 2016-04-15 16:00 | N | N | tap changer maintenance | Transformer |  | From April 11 to April 15, 2016 the City of Medicine Hat will be taking an outage on substation transformer T-22 located at MH69S-2 North Industrial Substation. Scope of work will be: - Complete tap changer maintenance - High voltage power factor testing transformer - Repair damaged pressure relief device - Reclaim transformer main tank oil. Outage time will be estimated at approximately 5 days, outages will start at 07:00 on April 11, 2016 and will be completed by 16:00 on April 15, 2016. | For Information Only
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2016-04-11 07:00 | 2016-04-12 07:00 | N | Y | change T2 tap changer controller | Transformer |  |  | 240 kV, For Information Only
ATCO | 9L37 (826s Marguerite Lake - 825s Whitefish Lake) | 2016-04-11 07:00 | 2016-04-15 17:00 | N | Y | upgrade 9L37 line protection both ends | Line |  | Upgrade 9L37 line protection both ends, 240kV ring will be open @ 825s and 826s on April 13 only April 11 & 12  Would like the GOI to be from 9L37D1 to 9L37D2 (which will allow the 240KV loops to be restored) April 13 AM  I would like to extend the GOI to 903A & 904A @ 826S, and 903A & 905B @ 825S (for any commissioning of soft point) April 13 PM - 15  I would like to go back to the original GOI from 9L37D1 to 9L37D2 (till all Direct Transfer Trip commissioning is completed) | 240 kV, Pre-Condition
ENMAX | 3.3TR (ENMAX 3) | 2016-04-11 08:00 | 2016-04-15 16:00 | N | N | Doble transformer | Transformer |  |  | For Information Only
ALTALINK, ATCO | 857L (409s Shell Scotford - 410s Josephburg),ALC02L (409s Shell Scotford - 879s Scotford Upgrader),409s 20 (409s Shell Scotford),409s 857W (409s Shell Scotford),409s 110 (409s Shell Scotford),409s Shell Scotford 138 kV Bus 2,409s10 (409s Shell Scotford),409s389 (409s Shell Scotford) | 2016-04-11 08:00 | 2016-04-12 17:00 | N | Y | bus outage to perform T3 protection testing to 409s100 & 409s 138kV breakers | Bus, Line, Circuit Breaker, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 37.1TR (ENMAX 37) | 2016-04-11 08:00 | 2016-04-15 16:00 | N | N | PRD Install & LTC maintenance | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 42s T1 (42s Sarcee),21.80L (42s Sarcee - ENMAX 21),7.82L (42s Sarcee - ENMAX 7),693L (42s Sarcee - ENMAX 10),42s Sarcee 138 kV North Bus | 2016-04-11 08:00 | 2016-04-29 17:00 | N | Y | replace strain insulators, replace switches, connect new cap bank switch | Bus, Transformer, Line |  | Replace strain insulators, Replace switches 42s90, 42s91, 42s19, 42s22, 42s39, 42s82, connect new cap bank switch. | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11) | 2016-04-11 08:00 | 2016-04-15 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 409s T3 (409s Shell Scotford) | 2016-04-11 08:00 | 2016-04-12 17:00 | N | N | close open point F, energize T3 to 409s1252 | Transformer |  |  | For Information Only
Syncrude | Mildred T2 (Syncrude Mildred Lake) | 2016-04-11 08:00 | 2016-04-24 18:00 | N | N | maintenance | Transformer |  |  | Restricts Generation
ENMAX | 28.1TR (ENMAX 28) | 2016-04-11 08:00 | 2016-04-11 16:00 | N | N | install maintenance mode | Transformer |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2016-04-11 08:00 | 2016-04-11 16:00 | N | N | HV breaker inspection | Circuit Breaker, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain),845s 710 (845s Big Mountain),845s710B (845s Big Mountain) | 2016-04-11 09:00 | 2016-04-12 16:00 | N | Y | adjust switch 710B so all blades open fully | Line, Switch, Circuit Breaker |  | Adjust switch 710B so all blades open fully, check hand crank | Pre-Condition, Overload
ALTALINK | 415s T1 (415s Drywood),164L (103s Goose Lake - 415s Drywood),415s 21 (415s Drywood) | 2016-04-11 09:30 | 2016-04-15 17:00 | N | N | breaker replacement - 415s21 | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 707s 505C (707s St. Paul) | 2016-04-11 10:00 | 2016-04-15 16:00 | N | N | 25kV-cut over breaker 505 to new control building protection | Shunts |  | Cut over BKR 505 to new control building protection. 505C WILL BE OUT OF SERVICE FOR THE DURATION OF WORK | For Information Only
ALTALINK | 63s T1 (63s Red Deer),63s 2652 (63s Red Deer),63s 752 (63s Red Deer),63s 552 (63s Red Deer),63s 152 (63s Red Deer),63s 452 (63s Red Deer),63s Red Deer 240kV North Bus,63s11 (63s Red Deer) | 2016-04-11 10:00 | 2016-04-14 17:00 | N | Y | replace 1083L strain insulators and replace 63s37 PT's | Bus, Circuit Breaker, Switch, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 730s 702 (730s Rycroft) | 2016-04-11 11:00 | 2016-04-22 14:30 | N | N | relay change and commission | Circuit Breaker |  | 730S 702 Relay change and Commission BREAKER 702 OUTAGE ONLY 7L68D3 CLOSED NO LINE OUTAGE | Pre-Condition
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2016-04-11 11:45 | 2016-04-14 13:45 | N | Y | replace rotten cross arms | Line |  | 7L199 replace rotten cross arms | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 40s T1 (40s Wetaskiwin) | 2016-04-11 12:00 | 2016-04-12 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 77s 48 (77s Sagitawah) | 2016-04-11 13:00 | 2016-04-12 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 6L06 (705s Kitscoty - 751s Hill) | 2016-04-11 13:00 | 2016-04-13 17:00 | N | N | change poles due to test and treat 2015 | Line |  | 6L06 Change poles due to test and treat 2015 | For Information Only
EPCOR | 987s CS2 (987s Clover Bar) | 2016-04-12 07:00 | 2016-04-12 17:00 | N | N | op checks | Circuit Breaker |  |  | For Information Only
ALTALINK | 198s T1 (198s Blackfalds) | 2016-04-12 07:00 | 2016-05-26 17:00 | N | N | T1 replacement, remove VR1 and add new transformer | Transformer |  |  | For Information Only
ALTALINK | 161L (255s Vulcan - 253s Blackie) | 2016-04-12 07:00 | 2016-04-28 17:00 | N | N | Blackie project work | Line |  | Blackie Project:Complete span into Blackie for 876L Line At Blackie Dead-End complete Temporary re-route of 161L from Vulcan to Queenstown Substation.Implement temporary relay setting at Vulcan Substation.Check phasing. | Firm Load Loss, Creates Radial Feeds
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2016-04-12 07:00 | 2016-04-12 17:00 | N | N | op checks | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.2TR (ENMAX 28) | 2016-04-12 08:00 | 2016-04-12 16:00 | N | N | 28.2TR install maintenance mode | Transformer |  |  | For Information Only
ALTALINK | 122S Alberta Newsprint,907L (77s Sagitawah - 122s Alberta Newsprint),122s 907N (122s Alberta Newsprint) | 2016-04-12 08:00 | 2016-04-12 16:00 | N | Y | 122s2 & finish T2 tap changer work,77s907W repairs | Line, Circuit Breaker, Station |  |  | 240 kV, Restricts Generation, Firm Load Loss
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 138 kV North Bus | 2016-04-12 08:00 | 2016-04-12 12:00 | N | Y | switch maintenance on SW 92 | Transformer, Bus |  |  | 240 kV
ALTALINK | 730L (197s Bardo - 730L61) | 2016-04-12 08:00 | 2016-04-12 16:00 | N | N | temporary settings on the protection at 197s on 730L | Line |  |  | For Information Only
ATCO | 802s 701T (802s Michichi Creek),6L56 (763s Hanna - 802s Michichi Creek) | 2016-04-12 09:00 | 2016-04-15 15:00 | N | N | 6L56 will be open ended @ 802s, 701T Outage for Bushing oil samples & 606 partial | Transformer, Line |  | 6L56 will be open ended @ 802s, 701T Outage for Bushing Oil Samples & 606 Partial | Pre-Condition
ALTALINK | 767L (310p Sundance - 767L50) | 2016-04-12 09:00 | 2016-04-12 17:00 | N | N | connect mobile for 821s load during 512L rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 138 kV South Bus | 2016-04-12 12:00 | 2016-04-12 16:00 | N | Y | switch maintenance on SW 89 | Transformer, Bus |  |  | 240 kV
ATCO | 778S Big Valley,6L44 (769s Stettler - 778s Big Valley) | 2016-04-12 13:00 | 2016-04-12 17:00 | N | N | pole replace/reinforce 6L44 | Line, Station |  | Pole Replace/Reinforce 6L44- 2016, change poles from test and treat 2 poles, 778s 25kV load requires offload to adjacent subs, some load shed will be necessary. | For Information Only
ATCO | 9L80 (757s Battle River - 755s Cordel) | 2016-04-12 13:00 | 2016-04-12 14:00 | N | Y | MPLS upgrade | Line |  | MPLS Upgrade TPS OOS - requires 9L80 line out during upgrade to protect generators in case of a Fault. | 240 kV, Pre-Condition, Overload, Over/Under Voltage
EPCOR | 72CK12 (987s Clover Bar - Kennedale),987s CK725 (987s Clover Bar) | 2016-04-13 07:00 | 2016-04-13 17:00 | N | N | operations check | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 430L (330P Genesee - 510S Sunnybrook) | 2016-04-13 07:00 | 2016-04-18 07:00 | N | N | CT isolation | Line
ENMAX | 918L (281s Johnson - 162s Beddington) | 2016-04-13 07:00 | 2016-04-13 16:00 | N | Y | switch maintenance on 162MD240-918L | Line |  |  | 240 kV
ALTALINK | 244s Bowmanton 138kV Bus 3,244s Bowmanton 138kV Bus 4,674L (244s Bowmanton - 649s Chappice Lake),244s Bowmanton 138kV Bus 1,244s Bowmanton 138kV Bus 2 | 2016-04-13 07:00 | 2016-04-23 18:00 | N | N | close open points 'D and I', protection and control work | Line, Bus |  |  | Creates Radial Feeds
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2016-04-13 07:00 | 2016-04-13 17:00 | N | N | operations check | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2016-04-13 08:00 | 2016-04-14 17:00 | N | Y | line maintenance | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 409s T2 (409s Shell Scotford) | 2016-04-13 08:00 | 2016-04-13 17:00 | N | N | close open point C & G, energize to 25kV409s1152 | Transformer |  |  | For Information Only
ALTALINK | 122s T3 (122s Alberta Newsprint) | 2016-04-13 08:00 | 2016-04-14 16:00 | N | Y | change 122sT3 tap changer controller | Transformer |  |  | 240 kV, For Information Only
ATCO | 843s 601T (843s Bigknife Creek) | 2016-04-13 09:00 | 2016-04-13 13:00 | N | N | ATCO Power to change underground cables from 301TD | Transformer |  | ATCO Power to change underground cables from 301TD | For Information Only
ALTALINK | 512L (310p Sundance - 521L tap),512L (821s Sundance - 521L tap) | 2016-04-13 09:00 | 2016-05-11 09:00 | N | N | Line rebuild and station equipment maintenance. | Line |  | Line rebuild and station equipment maintenance. Will be ustilizing mobile substation connected to 767L to feed load. | For Information Only
TRANSALTA, ALTALINK | 255s Vulcan RTU/SCADA,179s Gleichen RTU/SCADA | 2016-04-13 09:00 | 2016-04-13 10:00 | N | N | update RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 729L (285s East Camrose - 542s Ervick),285s 729W (285s East Camrose) | 2016-04-13 10:00 | 2016-04-19 17:00 | N | N | breaker replacement, PT replacement | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2016-04-13 13:00 | 2016-04-13 14:00 | N | Y | LonePine_T-telecom,Tinchebray_T-telecom - MPLS upgrade | Line |  | LonePine_T-telecom,Tinchebray_T-telecom - MPLS Upgrade TPS OOS - requires 9L59 line out during upgrade due to stability concerns. | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s CK726 (987s Clover Bar) | 2016-04-14 07:00 | 2016-04-14 17:00 | N | N | op checks CK726 | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO | 790s 704 (790s Poplar Hill) | 2016-04-14 07:00 | 2016-04-14 12:00 | N | Y | 704 circuit breaker gas filling | Circuit Breaker |  | Bkr 704 gas filling, This work is considered urgent as 704 gas levels are very low, Atco Power G1 will be reqd offline, Atco Power have agreed to the outage | Restricts Generation
ALTALINK | 370s T1 (370s North Lethbridge),370s T4 (370s North Lethbridge) | 2016-04-14 08:00 | 2016-04-14 18:00 | N | N | finish replacing 370s30 (25kV) & replace risers to 25kV Bus for 370s40 (25kV) and 370s30 (25kV) | Transformer |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2016-04-14 08:00 | 2016-04-14 12:00 | N | N | DPAC2 CAC/OAC replacement | Transformer |  |  | For Information Only
ENMAX | 21.1C (ENMAX 21),138-21.CAP (ENMAX 21) | 2016-04-14 08:00 | 2016-04-14 16:00 | N | N | install new motor and compare spring charging current to the one currently installed | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 415s T1 (415s Drywood),415s T2 (415s Drywood),162L (415s Drywood - 229s Glenwood),415s 352 (415s Drywood) | 2016-04-14 08:00 | 2016-04-14 16:00 | N | N | replace risers on 415s21 & 415s146E | Line, Transformer, Circuit Breaker |  |  | Over/Under Voltage, Restricts Generation, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2016-04-14 09:30 | 2016-04-14 14:30 | N | Y | urgent repairs | Line |  |  | 240 kV, Limits ATC
ENMAX | 28.2TR (ENMAX 28) | 2016-04-14 12:00 | 2016-04-14 16:00 | N | N | DPAC2 CAC/OAC replacement | Transformer |  |  | For Information Only
ATCO | 9L32 (849s Joslyn Creek - 2005s Secord) | 2016-04-15 05:30 | 2016-04-20 17:30 | N | Y | moving line for customer in the area | Line |  | Move line so customer can continue mining area. | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
SHELL, ATCO | 9L66 (847s Muskeg River - 849s Joslyn Creek),847s 902 (847s Muskeg River),847s 904 (847s Muskeg River) | 2016-04-15 05:30 | 2016-04-17 18:30 | N | Y | move 9L66 so customer can complete mine | Circuit Breaker, Line |  | Move 9L66 so customer can complete mine, Build 9L66 bypass to 201-PTL260-2, Install Jumper J1 on 201-PTL260-1, The 240kV ring will be reqd open between 902 to 904 to create safe working limits of approach for work crews. | 240 kV, Restricts Generation, Firm Load Loss
ATCO | 863s 902T (863s Paintearth) | 2016-04-15 07:00 | 2016-05-06 18:00 | N | Y | upgrade protection | Transformer |  | UPGRADE 902T PROTECTION | 240 kV
ALTALINK, ENMAX | 74s T1 (74s Janet),37.82L (74s Janet - ENMAX 37),765L (74s Janet - 151s Strathmore),74s Janet 138kV North Bus | 2016-04-15 07:00 | 2016-04-17 17:00 | N | Y | replace 138 kV string insulators and salvage 74s29452 & 74s43 | Transformer, Line, Bus |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 711L (Inland Cement - 747L tap) | 2016-04-15 07:00 | 2016-04-17 17:00 | N | N | breaker & line maintenance & repair DC supply | Line |  |  | Firm Load Loss
ALTALINK | 747L (37s North Calder - 99s North St Albert) | 2016-04-15 08:00 | 2016-04-17 17:00 | N | Y | replace 747DL4 | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 808 (330p Genesee) | 2016-04-16 07:00 | 2016-04-17 17:00 | N | N | CT secondary isolation | Circuit Breaker |  |  | Creates Radial Feeds
ATCO | 7L33 (7L33D3 - 749s Flyinshot Lake),749s 703 (749s Flyingshot Lake),749s 704 (749s Flyingshot Lake) | 2016-04-16 08:00 | 2016-04-24 16:00 | N | Y | protection upgrade, 144 kV ring open at 749s | Line, Circuit Breaker |  | Protection upgrade, CG&E radial fed from 845s, 144kV ring open at 749s | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
TRANSALTA, ALTALINK | 229s T1 (229s Glenwood),162L (415s Drywood - 229s Glenwood) | 2016-04-18 00:01 | 2016-04-18 05:00 | N | N | adjust air break | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 511s Victoria T2 (511s Victoria) | 2016-04-18 07:00 | 2016-05-22 17:00 | N | N | isolation for hydovacing | Transformer |  |  | For Information Only
ATCO | 9L36 (826s Marguerite Lake - 825s Whitefish Lake),826s 908 (826s Marguerite Lake),826s 907 (826s Marguerite Lake),825s 902A (825s Whitefish),825s 906B (825s Whitefish) | 2016-04-18 07:00 | 2016-04-22 17:00 | N | Y | protection upgrades at both ends | Line, Switch, Circuit Breaker |  | Protection upgrades at both ends, 240kV ring will be open at 825s and 826s April 20 only. April 18 & 19  Would like the GOI to be from 9L36D1 to 9L36D2 (which will allow the 240KV loops to be restored) April 20  I would like to extend the GOI to 907A & 908A @ 826S, and 902A & 906B @ 825S (for any commissioning of soft point) April 20-22  I would like to go back to the original GOI from 9L36D1 to 9L36D2 (till all Direct Transfer Trip commissioning is completed) | 240 kV, Pre-Condition
SHELL, AIRLIQUIDE | ALC03L (408s Air Liquide Scotford - 402s Scotford Expansion),402s 352 (402s Scotford Expansion),402s 452 (402s Scotford Expansion),402s (402s AOSP1) 144kV Bus | 2016-04-18 07:00 | 2016-04-24 17:30 | N | Y | protection upgrade. | Circuit Breaker, Bus, Line |  | Protection upgrade. | Creates Radial Feeds, For Information Only
ALTALINK | 44s T1 (44s Bearspaw Plant),44s T2 (44s Bearspaw Plant) | 2016-04-18 07:00 | 2016-04-22 17:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
EPCOR | Rossdale RR723 (Rossdale) | 2016-04-18 07:00 | 2016-04-18 17:00 | N | N | remove birds nest | Circuit Breaker |  |  | For Information Only
EPCOR | 816s P2402 (816s Petrolia) | 2016-04-18 07:00 | 2016-04-22 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
EPCOR | NamaoT1 (Namao) | 2016-04-18 07:00 | 2016-04-22 17:00 | N | N | doble | Transformer |  |  | Creates Radial Feeds, For Information Only
EPCOR | 987s GB1B (987s Clover Bar) | 2016-04-18 07:00 | 2016-04-18 17:00 | N | N | op checks | Circuit Breaker
ENMAX | 3.4TR (ENMAX 3) | 2016-04-18 08:00 | 2016-04-22 16:00 | N | N | doble test transformer | Transformer |  |  | For Information Only
ENMAX | 41.2TR (ENMAX 41) | 2016-04-18 08:00 | 2016-04-22 16:00 | N | N | install replacement LTC contacts | Transformer |  |  | For Information Only
ENMAX | 8.3TR (ENMAX 8) | 2016-04-18 08:00 | 2016-04-29 16:00 | N | N | noise complaint, investigate and/or repair | Transformer |  |  | For Information Only
ENMAX | 22.1TR (ENMAX 22) | 2016-04-18 08:00 | 2016-04-22 16:00 | N | N | PRD install | Transformer |  |  | For Information Only
SUNCOR | 29EDD-2 Tar Island,29EDD-2 252-5204 | 2016-04-18 08:00 | 2016-04-25 20:00 | N | Y | maintenance work | Circuit Breaker, Station |  | TG4 and 29EDD-2 will be offline as part of Suncors Major Mtce. for TG4 to 29PT-2 connect. SLD - SL30-P-141-119 | For Information Only
ALTALINK | 41s T1 (41s Medicine Hat),41s 98 (41s Medicine Hat),41s Cap1 (41s Medicine Hat),41s Cap2 (41s Medicine Hat),41s Cap3 (41s Medicine Hat),41s49 | 2016-04-18 08:00 | 2016-04-19 16:00 | N | N | transfer of 15 kV switchyard | Switch, Transformer, Shunts |  |  | Creates Radial Feeds, For Information Only
ALTALINK, EPCOR | 71s T1 (71s Lamoureux),920L (71s Lamoureux - 557s Castle Downs),921L (71s Lamoureux - 987s Clover Bar),71s 1652 (71s Lamoureux),71s 1352 (71s Lamoureux),71s Lamoureux 240 kV West Bus,71s 920W (71s Lamoureux) | 2016-04-18 08:00 | 2016-04-22 17:00 | N | Y | 920L/921L strain insulator and 240kV switch (71s920W) replacements | Line, Transformer, Switch, Bus, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 41.1C (ENMAX 41) | 2016-04-18 08:00 | 2017-08-05 07:59 | N | N | forced outage | Shunts
ALTALINK | 867S Sundance Blow-Down,234L (310p Sundance - 234L1),505L (505L1 - 234L tap),521AL (867s Sundance Blow-Down - 521L tap),521L (521L2 - 505L tap),310P 234N (310p Sundance) | 2016-04-18 09:00 | 2016-04-20 16:00 | N | N | 505L1 & 521L2 switch replacement | Line, Station, Circuit Breaker |  |  | Firm Load Loss, For Information Only
ATCO | 707s 506C (707s St. Paul) | 2016-04-18 10:00 | 2016-04-22 16:00 | N | N | cut over breaker 506 to new control building protection | Shunts |  | Cut over BKR 506 to new control building protection. 506C will be unavailable for the duration | For Information Only
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek),268s 199N (268s Whitecourt) | 2016-04-18 11:30 | 2016-04-18 17:00 | N | Y | 138 kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354s DVAR2 (354s Summerview) | 2016-04-18 12:00 | 2016-04-29 16:00 | N | N | permanent repairs on fibre optic cables | Shunts |  | low wind outage at our Summerview 2 DVAR From April 18th to April 29th. The outage will only be about 30 mins and we will still have some voltage support from our Summerview 1 DVAR trailer. Need to make permanent repairs on some fibre optic cables that were previously damaged and were temporarily fixed. | For Information Only
ATCO | 720s 901T (720s Wabasca),720s 901 (720s Wabasca) | 2016-04-18 12:30 | 2016-04-29 17:30 | N | N | 901, 900D1 and 901B circuit logic testing | Circuit Breaker, Transformer |  | 901, 900D1 and 901B circuit logic testing. Testing to be done after GOI 2-32176 released and before 901T is put back into service. 901T is still OOS, 901A and 901TD1 will be open to prevent 901T energizing during testing. | 240 kV, For Information Only
ALTALINK | 1041L (370s North Lethbridge - 554s Travers) | 2016-04-19 07:00 | 2016-04-19 17:30 | N | Y | replace leaking 554s8 VT | Line |  |  | Creates Radial Feeds
EPCOR | 72CN10 (987s Clover Bar - Namao),987s CN723 (987s Clover Bar) | 2016-04-19 07:00 | 2016-04-19 17:00 | N | N | op checks | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 803 (330p Genesee) | 2016-04-19 07:00 | 2016-04-20 17:00 | N | N | CT secondary isolation | Circuit Breaker |  |  | For Information Only
ALTALINK | 225L (67s Stirling - 225AL tap),67s 225 (67s Stirling) | 2016-04-19 08:00 | 2016-04-20 17:00 | N | N | 69 kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 13L50 (DC LINK),2029s T11 (2029s Heathfield),2075s T11 (2075s Newell) | 2016-04-19 08:00 | 2016-04-25 16:00 | N | Y | T11 valve hall deficiencies, EATL will be earthed and unavailable for transfer | Terminal Equipment, Transformer |  | T11 Valve hall deficiencies, EATL will be earthed and unavailable for transfer | 500 kV
ALTALINK | 159s T2 (159s Colinton),223L (159s Colinton - 150s Clyde),159s 138 kV Bus 2 (159s Colinton) | 2016-04-19 08:00 | 2016-04-19 17:00 | N | N | to stage for construction isolation | Bus, Transformer, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 2075s SVC2 (2075s Newell),2075s SVC1 (2075s Newell) | 2016-04-19 08:00 | 2016-04-25 16:00 | N | Y | siemens is performing construction deficiencies on SVC2 and SVC1 | Shunts |  | Siemens is performing construction deficiencies on SVC1, SVC2 will remain in service. 13L50 will be OOS during this work | 240 kV, For Information Only
SHELL | 847s 902 (847s Muskeg River),847s 903 (847s Muskeg River),847s 904 (847s Muskeg River) | 2016-04-19 08:00 | 2016-04-20 16:00 | N | Y | customer request | Circuit Breaker |  |  | 240 kV, Restricts Generation, Firm Load Loss
ALTALINK, ATCO | 715L (545s Provost - 650s Hansman Lake),885L (648s Metiskow - 650s Hansman Lake),7L224 (774s Monitor - 650s Hansman Lake),650S Hansman Lake 138kV Bus | 2016-04-19 08:00 | 2016-04-19 17:00 | N | Y | remove one of SS3 voltage transformes for leak repairs | Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 652 (77s Sagitawah) | 2016-04-19 08:30 | 2016-04-19 17:30 | N | N | 138 kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 504s Queenstown RTU/SCADA | 2016-04-19 09:00 | 2016-04-19 10:00 | N | N | update RTUs | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 310p 2152 (310p Sundance),310p 2052 (310p Sundance) | 2016-04-19 09:00 | 2016-04-19 15:30 | N | Y | urgent repair hotspot on switch | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 243s Soderglen Wind Farm RTU/SCADA | 2016-04-19 10:00 | 2016-04-19 12:00 | N | N | change some parameters on RTU at Soderglen 243s | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 397s T2 (397s Benbow),397s 31 (397s Benbow) | 2016-04-19 10:00 | 2016-04-22 16:00 | N | N | replace 397s31 | Circuit Breaker, Transformer |  |  | For Information Only
EPCOR | 987s C1 (987s Clover Bar),987s C72C1 (987s Clover Bar) | 2016-04-20 07:00 | 2016-04-20 17:00 | N | N | op checks | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | 72RV6 (Rossdale - 511s Victoria) | 2016-04-20 07:00 | 2016-04-22 17:00 | N | N | VT replacement | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2016-04-20 07:30 | 2016-04-20 17:00 | N | N | replace a structure | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 268s T3 (268s Whitecourt) | 2016-04-20 08:00 | 2016-04-20 17:00 | N | N | Doble T3, repairs on 268s88. terminators, riser, coverup. | Transformer |  |  | For Information Only
ALTALINK | 291s T2 (291s Cochrane) | 2016-04-20 08:00 | 2016-04-20 17:00 | N | N | repair transformer oil leaks | Transformer |  |  | For Information Only
ALTALINK | 277s T1 (277s Hayter) | 2016-04-20 08:00 | 2016-04-21 17:00 | N | N | transformer maintenance, doble and leak repair | Transformer |  |  | For Information Only
ALTALINK | 156L (235s Entwistle - 156L 86A),235s 156E (235s Entwistle) | 2016-04-20 08:00 | 2016-04-20 16:00 | N | N | DDR install | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CC13 (987s Clover Bar) | 2016-04-21 07:00 | 2016-04-21 17:00 | N | N | op checks | Circuit Breaker
ALTALINK | 876L (179s Gleichen - 504s Queenstown) | 2016-04-21 07:00 | 2016-05-10 17:00 | N | N | demo existing 876 line into Queenstown & complete 876 line construction adjacent to Queenstown 504s P&C / SCADA | Line |  | Modifications at Gleichen & Blackie for reconfigured lines Check Phasing. Energize NEW 876L from Gleichen to Blackie. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 675L (244s Bowmanton - 41s Medicine Hat) | 2016-04-21 08:00 | 2016-04-24 16:00 | N | N | In-service date: Apr 23, 2016. Once in-service, enable 1034L/1035L EATL RAS. | Line
ALTALINK | 851L (525s Carseland - 253s Blackie),253s 851W (253s Blackie) | 2016-04-22 07:00 | 2016-04-22 11:00 | N | N | Blackie project: trip circuits to 253s851W and function | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CCP7213 (987s Clover Bar) | 2016-04-22 07:00 | 2016-04-22 17:00 | N | N | breaker op checks | Circuit Breaker
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2016-04-22 07:30 | 2016-04-29 17:00 | N | N | new line construction | Line |  | NEW LINE CONSTRUCTION ST Paul load will need to be fed from 6L79 | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2016-04-22 08:00 | 2016-05-06 08:00 | N | N | install shield wire and salvage; test and DGA on cable | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2016-04-22 08:00 | 2016-05-06 16:00 | N | Y | install shield wire, salvage and switch maintenance | Line |  | Install top sections of the double deadend shield wire and salvage. No restoration possible for 4 days. HV SW MTCE on SW 81. Altalink required to move their isolation from SW81 to SW82 @ 21 Sub
ALTALINK | 253s C1 (253s Blackie),253s 182 (253s Blackie) | 2016-04-22 11:00 | 2016-04-22 14:00 | N | N | Blackie project: trip circuits to 253s182 and function | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 753L (65s High River - 253s Blackie),253s 753W (253s Blackie) | 2016-04-22 14:00 | 2016-04-22 17:00 | N | N | Blackie project: trip circuits to 253s753W and function | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 511s Victoria T5 (511s Victoria),CV5 (557s Castle Downs - 511s Victoria) | 2016-04-25 07:00 | 2016-05-02 17:00 | N | Y | UGT manhole inspection / relay maintenamce | Transformer, Line |  |  | 240 kV, Pre-Condition
EPCOR | NamaoT2 (Namao) | 2016-04-25 07:00 | 2016-04-29 07:00 | N | N | Doble test | Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss
EPCOR | 72RS5 (Rossdale - Strathcona) | 2016-04-25 07:00 | 2016-04-29 17:00 | N | N | VT replacement | Line |  |  | Pre-Condition, Firm Load Loss
EPCOR | 72CK12 (987s Clover Bar - Kennedale),Kennedale K723 (Kennedale) | 2016-04-25 07:00 | 2016-04-29 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D135 (ENMAX 25) | 2016-04-25 08:00 | 2016-04-25 17:00 | N | Y | cable fault location test | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 6.1TR (ENMAX 6) | 2016-04-25 08:00 | 2016-04-29 16:00 | N | N | Doble test transformer | Transformer |  |  | For Information Only
ATCO | 845s 702 (845s Big Mountain) | 2016-04-25 08:00 | 2016-04-29 11:00 | N | Y | Big Mountain protection upgrade | Circuit Breaker |  | Big Mountain Protection Upgrade; 7L13 fed from 703 only. | Pre-Condition, Over/Under Voltage, Firm Load Loss
ALTALINK | 906s T3 (906s Ross Creek) | 2016-04-25 08:00 | 2016-05-02 17:00 | N | N | replacement of T3 metering, 13.8kv VT2 & associated CT's | Transformer |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41) | 2016-04-25 08:00 | 2016-04-25 16:00 | N | N | setting new distribution pole, doble PT 40PT138-Z31 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 38.1TR (ENMAX 38) | 2016-04-25 08:00 | 2016-04-26 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 2.1TR (ENMAX 2) | 2016-04-25 08:00 | 2016-04-29 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2016-04-25 09:00 | 2016-04-29 16:00 | N | Y | 826S 7L91 RFL replacement construction 21B install | Line |  | 826S 7L91 RFL Replacement Construction 21B Install April 25 & 26  Would like the GOI to be from 7L91D1 to 702A (which will allow the 144KV loops to be restored) Note - Significant line (Cold Lk Cutplane) April 27  I would like to extend the GOI to 702B & 704AA @ 826S, and 702A @ 715S (PT Ratio Change) April 27-29  I would like to go back to the original GOI from 7L91D1 to 702A (till all Direct Transfer Trip commissioning is completed) | Pre-Condition
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2016-04-25 09:00 | 2016-04-25 12:00 | N | N | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 896L (19s Wabamun - 432s Carvel),19s 896 (19s Wabamun) | 2016-04-25 10:30 | 2016-04-26 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 852 (310p Sundance) | 2016-04-25 11:00 | 2016-04-25 15:00 | N | Y | CT secondary work | Circuit Breaker |  | - new Unit #3 metering | 240 kV, Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 612L (336s Fincastle - 368s Burdett),368s 612 (368s Burdett) | 2016-04-25 13:00 | 2016-04-25 14:00 | N | N | investigate why breaker failed to operate during a fault | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 235s T4 (235s Entwistle) | 2016-04-26 00:01 | 2016-04-26 06:00 | N | N | DDR install | Transformer
EPCOR | RossdaleT2 (Rossdale),Rossdale R723 (Rossdale),Rossdale R721 (Rossdale) | 2016-04-26 07:00 | 2016-04-26 17:00 | N | N | CVT replacement | Circuit Breaker, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 892L (895s Suffield - 41s Medicine Hat) | 2016-04-26 07:00 | 2016-05-04 15:00 | N | Y | close open points "H" and create new open point on old 892L toward 41s | Line |  |  | Pre-Condition
ALTALINK | 681s T1 (681s Bannerman) | 2016-04-26 07:45 | 2016-04-26 16:00 | N | Y | replace paralleling scheme, transformers will be switch out-of-service one at a time. | Transformer |  | The transformers will also be switched into service 1 at time. (No line outages). | 240 kV, For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2016-04-26 08:00 | 2016-04-26 14:00 | N | Y | urgent tightening of hardware corona ring on breaker 510s2252 | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 669L (163s Amoco Empress - 562s Cypress) | 2016-04-26 08:00 | 2016-04-26 12:00 | N | N | wire into CT circuits for PMU relay install on 163s L3 | Line |  |  | For Information Only
Syncrude | AL-1 (D05 Syncrude - Aurora) | 2016-04-26 08:00 | 2016-04-26 13:00 | N | Y | balance fiber optic cable | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK, ATCO | 715L (648s Metiskow - 650s Hansman Lake),885L (648s Metiskow - 650s Hansman Lake),7L224 (774s Monitor - 650s Hansman Lake),650S Hansman Lake 138kV Bus | 2016-04-26 08:00 | 2016-04-26 16:00 | N | Y | replace one of SS3 vts after leak repairs | Line, Bus | 6. Studied with Battle River(net)= 190 MW, Wind = 720 MW, WATL= 100 MW, 320p PST at neutral, 3. Higher Battle River generation may increase overloads on 704L (478s Tucuman - 704L tap). 4. Higher Wind (Central) may increase overloads on 704L (478s Tucuman - 704L tap). 5. Higher 320p transfer from the 240 kV to the 500 kV (using the 320p PST) may decrease overloads on 704L (478s Tucuman - 704L tap). |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 681s T2 (681s Bannerman) | 2016-04-26 08:00 | 2016-04-26 16:15 | N | Y | replace paralleling scheme, transformers will be switch out-of-service one at a time. | Transformer |  | The transformers will also be switched into service 1 at time. (No line outages). | 240 kV, For Information Only
ALTALINK | 172L (15s Fort Macleod - 172L1251) | 2016-04-26 09:30 | 2016-04-27 17:00 | N | N | replace 15s27 and strain insulators at 15s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 952 (310p Sundance) | 2016-04-26 10:00 | 2016-04-26 14:00 | N | Y | CT secondary work | Circuit Breaker |  | - new Unit #3 metering | 240 kV, Contingency Requires Mitigation
ALTALINK | 1011L (163s Amoco Empress - 562s Cypress),163s 1252 (163s Amoco Empress),163s 1352 (163s Amoco Empress) | 2016-04-26 13:00 | 2016-04-26 17:00 | N | Y | wire into CT circuits for PMU relay install on L5 | Circuit Breaker, Line |  |  | 240 kV, Creates Radial Feeds
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2016-04-26 13:00 | 2016-04-26 16:00 | N | Y | balance fiber optic cable | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
EPCOR | 330p 801 (330p Genesee) | 2016-04-27 07:00 | 2016-04-27 17:00 | N | N | CT secondary isolation | Circuit Breaker |  |  | For Information Only
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress),163s 1552 (163s Amoco Empress),163s 1752 (163s Amoco Empress) | 2016-04-27 08:00 | 2016-04-27 12:00 | N | Y | Wire into CT circuits for PMU relay install on L6 | Circuit Breaker, Line |  |  | 240 kV, Firm Load Loss
ENMAX | 38.3TR (ENMAX 38) | 2016-04-27 08:00 | 2016-04-28 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 225L (67s Stirling - 225AL tap),67s 225 (67s Stirling) | 2016-04-27 08:00 | 2016-05-07 16:00 | N | N | emergency repair | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 954L (648s Metiskow - 650s Hansman Lake) | 2016-04-27 08:00 | 2016-04-28 17:00 | N | Y | CT7 and CT8 ratio change and 954L relay settings change at 650s and 648s. | Line |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 155s T2 (155s Blackmud) | 2016-04-27 08:30 | 2016-04-27 17:00 | N | N | SIE/MR, VRC 138/26.5kV conservator piping leaks | Transformer |  |  | For Information Only
ALTALINK | 21S Marion | 2016-04-27 09:00 | 2016-04-27 17:00 | N | N | repair leak in CT block | Station |  |  | For Information Only
ALTALINK | 133S Stelco Edmonton | 2016-04-27 09:00 | 2016-04-27 17:00 | N | N | to allow AltaSteel to repair a bad connector on 35kV bus. | Station |  |  | For Information Only
ALTALINK | 83s C1 (83s Taber),610L (336s Fincastle - 83s Taber),507L (257s Hull - 83s Taber),83s Taber 138kV East Bus | 2016-04-27 09:00 | 2016-04-27 17:00 | N | Y | create open Point 'A' between 83s37 and 138kV W.Bus | Line, Bus, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1452 (310p Sundance) | 2016-04-27 10:00 | 2016-04-27 14:00 | N | Y | CT secondary work | Circuit Breaker |  | - new Unit #4 metering | 240 kV, Creates Radial Feeds
ALTALINK | 760L (163s Amoco Empress - 760L41),163s 760N (163s Amoco Empress) | 2016-04-27 13:00 | 2016-04-27 17:00 | N | N | wire into CT circuits for PMU relay install on L1 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s C1 (83s Taber),610L (336s Fincastle - 83s Taber),507L (257s Hull - 83s Taber),83s Taber 138kV East Bus | 2016-04-27 17:00 | 2016-04-30 08:00 | N | N | replace 138kV switch (83s37) | Bus, Line, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 15s Fort MacLeod),725L (15s Fort MacLeod - 725BL54) | 2016-04-28 07:00 | 2016-04-28 08:00 | N | Y | create open point 'A' on 725L | Line |  |  | Restricts Generation, Creates Radial Feeds
AESO | 161L (255s Vulcan - 504s Queenstown) | 2016-04-28 08:00 | 2016-04-29 16:00 | N | N | in-service date: Apr 28, 2016 | Line
ALTALINK | 760L (394s Empress - 163s Amoco Empress),163s 760X (163s Amoco Empress) | 2016-04-28 08:00 | 2016-04-28 12:00 | N | N | wire into CT circuits for PMU relay install on L2 | Circuit Breaker, Line |  |  | Creates Radial Feeds, For Information Only
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2016-04-28 08:00 | 2016-04-29 16:00 | N | N | HV breaker inspection (32B138-32.83 & 40B138-32.83), SF6 gas sample (32B138-32.83 & 40B138-32.83) | Line |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 15s 725 (15s Fort Macleod) | 2016-04-28 08:01 | 2016-04-28 17:00 | N | Y | replace strain insulators @ 15s | Circuit Breaker |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2016-04-28 08:30 | 2016-04-28 17:00 | N | N | VR1 doble and TC maintenance, 191s2 bird cover repair, 25kV bus 1 and T1 leak repair | Transformer |  |  | For Information Only
ALTALINK | 898L (37s North Calder - 92s Viscount),92s 898 (92s Viscount) | 2016-04-28 09:00 | 2016-04-28 17:00 | N | N | gas density switch replacement | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 310p 1552 (310p Sundance) | 2016-04-28 10:00 | 2016-04-28 14:00 | N | Y | CT secondary work | Circuit Breaker |  | - new Unit #4 metering | 240 kV
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2016-04-28 11:00 | 2016-04-28 13:00 | N | N | emergency repair of Crossarm brace and tighten hardware | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 15s Fort MacLeod),725L (15s Fort MacLeod - 725BL54) | 2016-04-28 17:01 | 2016-04-28 18:00 | N | N | close open point 'A' on 725L | Line |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 74s C2 (74s Janet),74s C1 (74s Janet),74s 56 (74s Janet),74s 54 (74s Janet) | 2016-04-29 07:00 | 2016-04-29 17:00 | N | N | function tests | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2016-04-29 07:00 | 2016-05-12 17:00 | N | N | replace conductor | Line |  | Replace conductor. | Pre-Condition, Overload
ALTALINK | 484s T2 (484s Millar Western) | 2016-04-29 09:00 | 2016-05-06 17:00 | N | N | oil reclaim, leak in main cabinet | Transformer |  |  | For Information Only
ALTALINK | 42s 80 (42s Sarcee) | 2016-04-29 17:00 | 2016-05-01 20:00 | N | N | replace strain insulators, replace switches, connect new cap bank switch | Circuit Breaker |  |  | For Information Only
ALTALINK, ENMAX | 44s T2 (44s Bearspaw Plant),50L (44s Bearspaw Plant - ENMAX 21),860L (291s Cochrane - 44s Bearspaw Plant),36.81L (44s Bearspaw - ENMAX 36) | 2016-04-29 17:00 | 2016-05-01 20:00 | N | N | repair 44s 33 switch | Line, Transformer |  |  | Overload, Restricts Generation, Creates Radial Feeds
ENMAX | 22.81L (ENMAX 22 - ENMAX 39),ENMAX 39 B138-22.81 (ENMAX 39),ENMAX 22 B138-22.81 (ENMAX 22) | 2016-04-30 08:00 | 2016-05-01 16:00 | N | N | HV breaker inspection HLR 22B138-22.81, HV breaker inspection 39B138-22.81 (Apr 30) | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ALTALINK | 610L (336s Fincastle - 83s Taber) | 2016-04-30 08:30 | 2016-04-30 17:00 | N | N | close open point 'A' between 83s37 and 138kV bus | Line |  |  | For Information Only
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek),755L (63s Red Deer - 247s Piper Creek) | 2016-05-01 | 2016-09-06 07:29 | N | Y | rebuild 1083L,rebuild 755L | Line |  | Rebuild portion of 1083L from 63s That parallels 755L | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s3 (33s Spray) | 2016-05-01 08:00 | 2016-05-10 14:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ATCO | ATCO Satellite Phone | 2016-05-01 12:00 | 2016-05-01 14:00 | N | N | SOC monthly satellite phone testing | SCInternal |  | SOC MONTHLY SATELLITE PHONE TESTING | For Information Only
ALTALINK, ENMAX | 42s T1 (42s Sarcee),21.80L (42s Sarcee - ENMAX 21),7.82L (42s Sarcee - ENMAX 7),693L (42s Sarcee - ENMAX 10),42s Sarcee 138 kV North Bus | 2016-05-01 20:00 | 2016-05-06 15:00 | N | Y | replace strain insulators, replace switches, connect new cap bank switch | Bus, Transformer, Line |  | Replace strain insulators, Replace switches 42s90, 42s91, 42s19, 42s22, 42s39, 42s82, connect new cap bank switch. | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T2 (987s Clover Bar) | 2016-05-02 07:00 | 2016-05-06 17:00 | N | Y | Doble test | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK12 (987s Clover Bar - Kennedale),Kennedale K724 (Kennedale) | 2016-05-02 07:00 | 2016-05-06 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal) | 2016-05-02 07:00 | 2016-05-08 17:00 | N | Y | line mitigation repairs, 861s, 724s, 829s, 754s, & 730s radial fed via 7L68 from 811s Clairmont | Line |  | Line mitigation repairs, 861s, 724s, 829s, 754s, & 730s radial fed via 7L68 from 811s Clairmont | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 511s Victoria T5 (511s Victoria),CV5 (557s Castle Downs - 511s Victoria) | 2016-05-02 07:01 | 2016-05-06 17:00 | N | Y | underground manhole inspection / relay maintenance | Line, Transformer |  |  | 240 kV, Pre-Condition, Firm Load Loss
ATCO | 845s 703 (845s Big Mountain) | 2016-05-02 08:00 | 2016-05-08 16:30 | N | N | Big Mountain protection upgrade | Circuit Breaker |  | Big Mountain Protection Upgrade; 7L13 line fed from 702 only, | Contingency Requires Mitigation
ALTALINK | 787AL (906s Ross Creek - 787L tap),906s 787AE (906s Ross Creek) | 2016-05-02 08:00 | 2016-05-02 17:00 | N | N | breaker maintenance, install grading capacitors | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 5.8TR (ENMAX 5) | 2016-05-02 08:00 | 2016-05-05 16:00 | N | N | control umbilical change out on 5B25-117, 5B25-118, 5B25-5.8TR. 5.118 relay settings changes | Transformer |  |  | For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2016-05-02 08:00 | 2016-05-06 16:00 | N | N | Doble test | Transformer |  |  | For Information Only
ALTALINK | 906s T1 (906s Ross Creek) | 2016-05-02 08:00 | 2016-05-06 17:00 | N | N | replace T1 bushing, metering upgrade | Transformer |  |  | For Information Only
ENMAX | 6.1TR (ENMAX 6) | 2016-05-02 08:00 | 2016-05-03 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 600L (523s Bullshead - 404s Peace Butte),880L (523s Bullshead - 41s Medicine Hat),404s 12 (404s Peace Butte) | 2016-05-02 08:00 | 2016-05-02 18:00 | N | N | jumper 880L and 600L together and connect Mobile Sub | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 5L92 (Cranbrook - Selkirk) | 2016-05-02 09:00 | 2016-05-06 17:00 | Y | Y | insulator replacements & arcing horn installations - various locations - BC maintenance does not affect AB ATC | Line |  |  | Pre-Condition, 500 kV
ALTALINK | 199s T2 (199s East Airdrie) | 2016-05-02 11:00 | 2016-05-02 17:00 | N | N | tap changer oil replacement | Transformer |  |  | For Information Only
ALTALINK | 214s T1 (214s Innisfail) | 2016-05-02 12:00 | 2016-05-05 17:00 | N | N | transformer maintenance, doble and leak repair | Transformer |  |  | For Information Only
ALTALINK | 484s T3 (484s Millar Western) | 2016-05-02 13:00 | 2016-05-05 17:00 | N | N | replace 13.8kV bushings, 13.8kV & 138kV lightning arrestors | Transformer |  |  | For Information Only
ATCO | 7L97 (933s Tower Road - 7LA97) | 2016-05-02 13:33 | 2016-05-18 18:54 | N | N | forced outage due to Fort MacMurrary forest fire | Line
ALTALINK | 320p PS2 (320p Keephills) | 2016-05-02 14:00 | 2016-05-04 15:00 | N | Y | replace PS2 series TX H2 bushing | Transformer |  |  | 240 kV
ATCO | 2029s ACF11 (2029s Heathfield) | 2016-05-03 08:00 | 2016-05-05 17:00 | N | Y | to perform testing and maintenance on ACF11 | Shunts |  | ACF11 Outage @ 2029S Heathfield To perform testing and Maintenance on ACF11 Filter Equipment ACF11 Filter will be unavailable for service during outage. ACF21 will remain in service and will be available for dispatch. Power Transfer operations/Availability will not be affected. | 240 kV, For Information Only
Syncrude | AL-1 (D05 Syncrude - Aurora) | 2016-05-03 08:00 | 2016-05-03 13:00 | N | Y | balance fiber optic cable | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 405s T1 (405s Waupisoo) | 2016-05-03 08:00 | 2016-05-03 16:00 | N | N | DDR install | Transformer |  |  | For Information Only
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2016-05-03 08:00 | 2016-06-07 11:29 | N | N | cranes and backhoes to approach safe working limits if line is energized therefore de-energization is required | Line |  |  | For Information Only
AESO | 892L (895s Suffield - 244s Bowmanton) | 2016-05-03 08:00 | 2016-05-05 16:00 | N | N | New 892L in-service date: May 4. Old 892L will be salvaged. | Line
ALTALINK | 523s C1 (523s Bullshead),523s T1 (523s Bullshead),879L (368s Burdett - 523s Bullshead),523s 879 (523s Bullshead) | 2016-05-03 08:00 | 2016-05-16 08:00 | N | N | replace 523s15 & 523s16 switches | Line, Circuit Breaker, Shunts, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 746s T2 (746s Sherwood Park) | 2016-05-03 09:00 | 2016-05-06 17:00 | N | N | T2 and associated 25 kV Bus forced out-of-service. | Transformer |  |  | For Information Only
AESO-SC | CROW | 2016-05-03 10:00 | 2016-05-03 11:00 | N | N | CROW Prod Migration from PDC to SDC | SCInternal |  |  | For Information Only
ATCO | 9L23 (848s Ruth Lake - 977s Salt Creek) | 2016-05-03 10:25 | 2016-06-05 15:49 | N | Y | forced outage due to Fort MacMurray fire | Line |  |  | 240 kV
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2016-05-03 13:00 | 2016-05-03 16:00 | N | Y | balance fiber optic cable | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ENMAX | 9.2TR (ENMAX 9) | 2016-05-04 08:00 | 2016-05-05 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 575s T2 (575s Sundre) | 2016-05-04 08:00 | 2016-05-05 17:00 | N | N | transformer maintenance, doble, bird cover and valve leak repair | Transformer |  | transformer maintenance, doble, bird cover and valve leak repair | For Information Only
ALTALINK | 235s Entwistle RTU/SCADA | 2016-05-04 08:00 | 2016-05-04 16:00 | N | N | RTU configuration and alarm checks | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 102s 6552 (102s Langdon) | 2016-05-04 08:00 | 2016-05-04 12:00 | N | Y | CT leak repairs | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 704L (478s Tucuman - 704L tap) | 2016-05-04 09:30 | 2016-05-04 17:00 | N | N | urgent repair conductor damage-H Frame change | Line |  |  | Pre-Condition
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2016-05-04 11:00 | 2016-05-04 13:00 | N | N | IR scan | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 185L (396s-379s) - Open Breaker Advice | 2016-05-04 13:00 | 2016-05-04 15:00 | N | N | IR scan | Terminal Equipment |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L36 (820s Hangingstone - 2009s Willow Lake) | 2016-05-04 18:17 | 2016-05-09 16:05 | N | N | forced outage due to Fort MacMurray fire | Line
ATCO | 9L85 (856s Kinosis - 977s Salt Creek) | 2016-05-05 03:05 | 2016-05-15 17:55 | N | Y | forced outage due to Fort MacMurrary fire | Line |  |  | 240 kV
ALTALINK | 704L (252s Jarrow - 704L tap) | 2016-05-05 08:00 | 2016-05-05 17:00 | N | N | urgent repair conductor damage | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2016-05-05 08:00 | 2016-05-09 12:00 | N | N | relocation of transmission poles and re-stringing line to allow for site expansion | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 138s 952 (138s Windy Flats) | 2016-05-05 10:00 | 2016-05-05 14:00 | N | Y | replacement of under voltage relay 27.1 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L15 (841s Long Lake - 856s Kinosis) | 2016-05-06 00:36 | 2016-05-24 16:00 | N | N | forced outage due to Fort MacMurrary fire | Line
ALTALINK | 180L (255s Vulcan - 928s East Stavely),255s 34 (255s Vulcan) | 2016-05-06 08:00 | 2016-05-06 12:00 | N | N | trip circuits from 11/152 protection to 255s34 and function | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.83L (162s Beddington - ENMAX 11),ENMAX 11 B138-11.83 (ENMAX 11) | 2016-05-07 08:00 | 2016-05-08 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 845s 701 (845s Big Mountain) | 2016-05-08 17:00 | 2016-05-08 21:00 | N | N | terminate 50BF/702 wires into 701 trip cct and test | Circuit Breaker |  | terminate 50BF/702 wires into 701 trip cct and test This T&O will be requested after all GOI and CSPs related to 7L13 line will be released and 702 and 703 are both back in service, 144kV ring will only be open for 20-30 min during 701 testing, 7L45 will remain in service | Pre-Condition, Contingency Requires Mitigation
ATCO | 7L84 (722s Crystal Lake - 749s Flyinshot Lake),749s 702 (749s Flyingshot Lake),749s 701 (749s Flyingshot Lake) | 2016-05-09 07:00 | 2016-05-22 17:00 | N | Y | replace 7L84 protection relays | Line, Circuit Breaker |  | Replace 7L84 protection relays, 144kV ring will be open @ 749s. | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2016-05-09 07:00 | 2016-05-13 17:00 | N | Y | CT replacement | Line |  |  | 240 kV
EPCOR | Meadowlark M723 (Meadowlark) | 2016-05-09 07:00 | 2016-05-09 17:00 | N | N | doble test | Circuit Breaker |  |  | For Information Only
EPCOR | 52s T2 (52s East Industrial) | 2016-05-09 07:00 | 2016-05-13 17:00 | N | Y | Doble | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72JW19 (805s Jasper - Woodcroft),805s J724 (805s Jasper) | 2016-05-09 07:00 | 2016-05-13 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7) | 2016-05-09 08:00 | 2016-05-13 16:00 | N | N | Doble transformer | Transformer |  |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc),325s T2 (325s Leduc),325s Leduc 138kV Bus 2 | 2016-05-09 08:00 | 2016-05-24 08:00 | N | N | close open points B and C in preparation for energization on May 24 | Transformer, Line, Bus |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2016-05-09 08:00 | 2016-05-10 12:00 | N | N | maintenance | Switch |  |  | Pre-Condition, Restricts Generation
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 33 B138-33.84 (ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2016-05-09 08:00 | 2016-05-11 16:00 | N | N | HV breaker inspection (33B138-33.84), SF6 gas sample (33B138-33.84), breaker inspection HLR (43B138-33.84). Sheath test & DGA on LPOF 138kV cable | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.2TR (ENMAX 26) | 2016-05-09 08:00 | 2016-05-20 16:00 | N | N | repair hotspot on 26.2TR high side bushing | Transformer |  |  | For Information Only
ENMAX | 33.2TR (ENMAX 33) | 2016-05-09 08:00 | 2016-05-09 16:00 | N | N | 33PT138-Z31 Doble Test PT | Transformer |  |  | For Information Only
AESO | 876L (179s Gleichen - 253s Blackie) | 2016-05-09 08:00 | 2016-05-10 16:00 | N | N | In-service date: May 10. | Line
ENMAX | 11.3TR (ENMAX 11) | 2016-05-09 08:00 | 2016-05-10 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),ENMAX 25 240kV North Bus | 2016-05-09 08:00 | 2016-06-16 18:00 | N | Y | L to J: 1003L cable fault - replacement | Bus, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 787L (71s Lamoureux - 787L29),861L (71s Lamoureux - 258s Dow Hydro Carbons) | 2016-05-09 09:00 | 2016-05-10 16:00 | N | Y | move TPR channel to MPLS system and perform trip tests to confirm functionality | Line |  |  | Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s 88 (37s North Calder) | 2016-05-09 10:30 | 2016-05-12 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 225L (67s Stirling - 225AL tap),67s 225 (67s Stirling) | 2016-05-09 11:00 | 2016-05-14 17:00 | N | N | urgent replace 69 kV breaker | Circuit Breaker, Line |  |  | Creates Radial Feeds
ALTALINK | 17s 757N (17s Benalto) | 2016-05-09 11:00 | 2016-05-09 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 869L (204s Sandy Point - 163s Amoco Empress),163s 869W (163s Amoco Empress) | 2016-05-09 12:00 | 2016-05-09 17:00 | N | N | wire into CT circuits for PMU relay install on L4 | Circuit Breaker, Line |  |  | Firm Load Loss
ALTALINK | WATL (510s Sunnybrook - 511s Crossings) | 2016-05-09 14:06 | 2016-05-11 18:59 | N | N | forced outage | Line |  | WATL forced outage due to voltage divider failure. | For Information Only
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft T1 (Woodcroft) | 2016-05-10 07:00 | 2016-05-10 17:00 | N | N | op checks | Transformer, Line
ALTALINK | 205s13 (205s Castle Rock Ridge) | 2016-05-10 07:00 | 2016-05-12 17:00 | N | Y | customer request to open high side switch in AltaLink yard | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 205S Castle Rock Ridge | 2016-05-10 07:00 | 2016-05-12 17:00 | N | Y | maintenance | Station |  |  | Restricts Generation
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark M724 (Meadowlark) | 2016-05-10 07:00 | 2016-05-10 17:00 | N | N | doble | Circuit Breaker, Line
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2016-05-10 07:30 | 2016-05-20 17:00 | N | Y | insulator replacements and arcing horn installations | Line |  |  | Pre-Condition
ALTALINK | 159s T2 (159s Colinton),223L (159s Colinton - 150s Clyde),159s 43 (159s Colinton),159s 46 (159s Colinton) | 2016-05-10 08:00 | 2016-05-10 17:00 | N | N | install new 25 kV switchgear building and salvage T2 | Line, Transformer, Circuit Breaker |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 854L (39s Bickerdike - 854L230) | 2016-05-10 08:00 | 2016-05-11 08:00 | N | N | repair structures #261, 268 & 288 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 204s T1 (204s Sandypoint),869L (204s Sandy Point - 163s Amoco Empress) | 2016-05-10 08:00 | 2016-05-11 17:00 | N | N | doble on T1, CTs and PTs | Transformer, Line |  |  | Firm Load Loss
ENMAX | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2016-05-10 08:00 | 2016-05-11 16:00 | N | N | replace 1 heater on 10B138-832 to complete HVB heater retro-fit | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2016-05-10 08:00 | 2016-05-15 18:00 | N | N | land development, breaker and SF6 gas sample on breakers | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 118s T1 (118s Canmore) | 2016-05-10 08:30 | 2016-05-10 17:00 | N | N | transformer maintenance and doble | Transformer
ALTALINK | 310p 252 (310p Sundance),310p 352 (310p Sundance) | 2016-05-10 09:00 | 2016-05-10 17:00 | N | Y | urgent repair hotspot | Circuit Breaker |  |  | 240 kV, Restricts Generation
TRANSALTA | 59s 352 (59s Peigan),59s 452 (59s Peigan) | 2016-05-10 09:00 | 2016-05-10 16:00 | N | Y | demo the 911L relay for the MATL RAS scheme in order to remove the CT contributions | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 40s T1 (40s Wetaskiwin) | 2016-05-10 09:00 | 2016-05-11 15:00 | N | N | transformer maintenance | Transformer
ALTALINK | 256s 1 (256s Harmattan) | 2016-05-10 10:00 | 2016-05-10 12:00 | N | N | emergency work to replace controller to allow for remote switch operation, operate switch to test new controller card | Switch |  |  | Restricts Generation
ALTALINK | 281s T1 (281s Johnson) | 2016-05-10 10:00 | 2016-05-12 15:00 | N | Y | inspect and repair oil leak on neutral bushing | Transformer |  |  | 240 kV
EPCOR | 72MG16 (Meadowlark - Garneau) | 2016-05-11 07:00 | 2016-05-11 17:00 | N | N | doble | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 803s T2 (803s Lambton) | 2016-05-11 07:00 | 2016-05-12 17:00 | N | Y | repair | Transformer |  |  | 240 kV
ALTALINK | 504S Queenstown,161L (255s Vulcan - 504s Queenstown),255s 161 (255s Vulcan) | 2016-05-11 07:05 | 2016-05-19 17:05 | N | N | complete construction of the 161L at Queenstown | Circuit Breaker, Line, Station |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2016-05-11 08:00 | 2016-05-11 16:00 | N | N | mainetenace on SW 88 @ 13 sub | Line |  |  | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2016-05-11 08:00 | 2016-05-11 16:00 | N | N | install Trojan oil processor | Transformer |  |  | For Information Only
REDDEER | 247s T1 (247s Piper Creek) | 2016-05-11 08:00 | 2016-05-11 17:00 | N | N | power diagnostic testing | Transformer |  |  | For Information Only
TRANSALTA, ALTALINK | 733L (179s Gleichen - 428s Namaka),179s 733 (179s Gleichen) | 2016-05-11 08:00 | 2016-05-11 12:00 | N | N | trip circuits from 11/152 protection to 179s733 and function | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.4TR (ENMAX 11) | 2016-05-11 08:00 | 2016-05-12 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 225L (67s Stirling - 225AL tap) | 2016-05-11 08:00 | 2016-05-13 17:00 | N | N | RAS setting changes | Line |  |  | For Information Only
ALTALINK | 854L (1012s Deer Hill - 854L229) | 2016-05-11 08:01 | 2016-05-11 17:00 | N | N | repair structure #194 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant),291s 860 (291s Cochrane) | 2016-05-11 08:30 | 2016-05-11 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Over/Under Voltage, Creates Radial Feeds
ALTALINK | 862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons) | 2016-05-11 09:00 | 2016-05-12 16:00 | N | Y | move TPR channel to MPLS system and perform trip tests to confirm functionality | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 767L (310p Sundance - 767L50) | 2016-05-11 09:00 | 2016-05-11 17:00 | N | N | disconnect mobile from 767L after 512L rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2016-05-11 23:00 | 2016-05-12 03:00 | N | Y | maintenace | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2016-05-12 03:00 | 2016-05-12 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 6.82L (ENMAX 6 - ENMAX 41),ENMAX 41 B138-6.82 (ENMAX 41) | 2016-05-12 08:00 | 2016-05-13 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2016-05-12 08:00 | 2016-05-12 16:00 | N | N | HV SW maintenance on SW 85 @ 21 sub | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 685L (397s Benbow - 1012s Deer Hill) | 2016-05-12 08:00 | 2016-05-12 17:00 | N | N | urgent component replacements (insulators & crossarm) | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 574s 552 (574s Nilrem) | 2016-05-12 08:00 | 2016-05-12 13:00 | N | Y | SF6 gauge needs replacement | Circuit Breaker |  |  | 240 kV
ALTALINK | 291s T2 (291s Cochrane),433L (291s Cochrane - T793s Horse Creek),291s 433 (291s Cochrane),291s Cochrane 138kV Bus 2 | 2016-05-12 08:30 | 2016-05-12 17:00 | N | N | 138 kV switch repairs | Line, Circuit Breaker, Bus, Transformer |  |  | Creates Radial Feeds
ALTALINK | 616L (103s Goose Lake - 616AL tap),103s 1452 (103s Goose Lake),103s 1552 (103s Goose Lake) | 2016-05-12 09:00 | 2016-05-12 16:00 | N | N | SATR: install a metering relay for 616L | Line, Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 243s Soderglen Wind Farm RTU/SCADA | 2016-05-12 11:00 | 2016-05-12 14:00 | N | N | update RTU network properties | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L70 (700s Bonnyville - 936s Norberg) | 2016-05-13 07:00 | 2016-05-27 17:00 | N | N | install new 144 kV tap to 707s and line construction | Line |  | Install new 144kV T tap to St Paul, 707s will be energized via 7L70 approx. 2 days after 7L70 is re-energized, 936s Norberg will be radial fed from 819s Whitby Lk, 707S supplied by 6L82 | Pre-Condition, Creates Radial Feeds
ENMAX | 2.83L (ENMAX 13 - ENMAX 2) | 2016-05-14 00:01 | 2016-05-14 06:00 | N | N | Calgary Zoo is installing a berm under the line (remove jumper to 5 sub) | Line |  |  | For Information Only
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2016-05-14 06:01 | 2016-05-15 22:00 | N | N | Calgary Zoo is installing a berm under the line | Line |  |  | Pre-Condition
ENMAX | 40.1TR (ENMAX 40),32.83L (ENMAX 32 - ENMAX 40) | 2016-05-14 08:00 | 2016-05-14 16:00 | N | N | Doble 40PT138-Z31 PT | Line, Transformer |  |  | Pre-Condition
ENMAX | 9.1TR (ENMAX 9),9.2TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2016-05-15 08:00 | 2016-05-15 16:00 | N | N | hotspot repair required on SW83 | Line, Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2016-05-15 18:00 | 2016-05-15 22:00 | N | N | DPAC1 CAC/OAC replacement | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2016-05-15 22:00 | 2016-05-16 02:00 | N | N | DPAC1 CAC/OAC replacement. Installation of cable under line downtown | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 2.83L (ENMAX 13 - ENMAX 2) | 2016-05-15 22:00 | 2016-05-16 04:00 | N | N | Calgary Zoo is installing a berm under the line (install jumper to 5 sub) | Line |  |  | Pre-Condition
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2016-05-16 07:00 | 2016-05-20 17:00 | N | Y | replace strain insulators over 42s21 | Line |  |  | Pre-Condition, Overload
ALTALINK | 1059L (38s East Edmonton - 1059AL tap),38s 7452 (38s East Edmonton),38s 7552 (38s East Edmonton) | 2016-05-16 07:00 | 2016-05-16 07:15 | N | Y | EPCOR requires 1059L de-energized in order to isolate T1 at E52s East Industrial | Line, Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 52s E2401 (52s East Industrial) | 2016-05-16 07:00 | 2016-05-21 17:00 | N | Y | breaker maintenance & Doble | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 198s T1 (198s Blackfalds),80L (198s Blackfalds - 958s West Lacombe),198s Blackfalds 138kV Bus 1 | 2016-05-16 07:00 | 2016-05-26 17:00 | N | N | Blackfalds upgrade project: GOI expansion in prep to energize new transformer and 25kV feeder | Transformer, Bus, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale R723 (Rossdale) | 2016-05-16 07:00 | 2016-05-18 17:00 | N | N | circuit breaker maintenance and doble | Circuit Breaker |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27) | 2016-05-16 08:00 | 2016-05-16 16:00 | N | N | Doble 69kV PT | Transformer
ENMAX | 39.2TR (ENMAX 39) | 2016-05-16 08:00 | 2016-05-20 16:00 | N | N | Doble | Transformer
ENMAX | 5.7TR (ENMAX 5) | 2016-05-16 08:00 | 2016-05-19 16:00 | N | N | control umbilical change out on 5B25-111, 5B25-112, 5B25-5.7TR | Transformer
ALTALINK, ENMAX | 42s T2 (42s Sarcee),150L (42s Sarcee - 150L47),28.80L (42s Sarcee - ENMAX 28),30.81L (42s Sarcee - ENMAX 30),3L (42s Sarcee - 272s Springbank),42s Sarcee 138 kV South Bus | 2016-05-16 08:00 | 2016-06-17 16:00 | N | Y | replace strain insulators, switches and move capbank to north bus | Line, Bus, Transformer |  | Replace strain insulators, replace switches 42s149, 42s151, 42s59, 42s66, 42s67, 42s54, 42s56, 42s27, 42s29, 42s81, 42s31, disconnect cap bank for move to north bus | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 2029s ACF13 (2029s Heathfield) | 2016-05-16 08:00 | 2016-05-17 17:00 | N | Y | filter inspection and maintenance | Shunts |  | Filter Inspection and Maintenance on ACF13, redundant filter will remain in service, no impact to EATL transfer limits Perform Scheduled bi annual inspection/maintenance/testing on ACF13 equipment. | For Information Only, 500 kV
ATCO | 800s 702T (800s Friedenstal),800s 712 (800s Friedenstal) | 2016-05-16 09:00 | 2016-05-17 15:00 | N | N | complete major testing PM 702T | Transformer, Circuit Breaker |  | 800S 702T TRANSFORMER CLASS2 MAJOR TESTING Complete Major Testing PM 702T Out of Service for the duration of the work | For Information Only
ATCO | 809s 701C (809s Louise Creek),809s 709 (809s Louise Creek) | 2016-05-16 10:00 | 2016-05-16 16:00 | N | N | partial maintenance on breaker 709@809S, 701C capacitor unavailable during outage | Circuit Breaker, Shunts |  | Partial Maintenance on Breaker 709@809S, 701C Capacitor unavailable during outage | For Information Only
ALTALINK | 213s T1 (213s Hughenden) | 2016-05-16 10:00 | 2016-05-16 12:00 | N | N | urgent replace 25kV PT and cabling to 213s8 | Transformer
ALTALINK | 1054L (13s Deerland - 12s Heartland) | 2016-05-16 10:00 | 2016-05-17 17:00 | N | Y | urgent repair of helix dampers | Line |  |  | 240 kV, Overload
ALTALINK | 37s T5 (37s North Calder) | 2016-05-16 10:30 | 2016-05-19 17:00 | N | N | breaker maintenance and bird cover up | Transformer |  |  | For Information Only
ALTALINK | 404S Peace Butte | 2016-05-16 11:00 | 2016-05-16 12:00 | N | N | to remove bypass between 880L and 600L | Station |  |  | For Information Only
NOVAC | 330L1 (I-330s Nova Corp Plant - 535s Joffre) | 2016-05-17 05:00 | 2016-05-18 19:00 | N | N | maintenance | Line |  |  | For Information Only
ALTALINK | 1037L (138s Windy Flats - 237s Foothills) | 2016-05-17 08:00 | 2016-05-17 17:00 | N | Y | emergency repair; loose helix dampers and conductor damage | Line |  |  | 240 kV
ENMAX | 16.1TR (ENMAX 16) | 2016-05-17 08:00 | 2016-05-17 16:00 | N | N | doble and repair 69kV PT | Transformer |  |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2016-05-17 08:00 | 2016-05-19 17:00 | N | N | relocated 703L structure, 703L198B for future 216s expansion | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36) | 2016-05-17 08:00 | 2016-05-18 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 510s ACF21 (510s Sunnybrook) | 2016-05-17 08:00 | 2016-05-17 16:00 | N | N | urgent repair | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt),364s 797 (364s Whitecourt Industrial) | 2016-05-17 09:00 | 2016-05-17 12:00 | N | N | upgrading firmware on radio hop at 364s and 9269R | Line, Circuit Breaker |  | Upgrading firmware on radio hop bx 364s & 9269R; all of the TPR on both lines will be out of service for approx 2 hours; SPV @ 364s will also be affected for the same period of time. | Over/Under Voltage, Creates Radial Feeds
ATCO | 7L55 (809s Louise Creek - 743s Sarah Lake),809s 705 (809s Louise Creek) | 2016-05-17 09:00 | 2016-05-17 15:00 | N | N | partial maintenance on breaker 705 at 809s | Line, Circuit Breaker |  | Partial Maintenance on Breaker 705@809S, 7L55 open ended at 809S Louise Creek | Over/Under Voltage, For Information Only
ALTALINK | 33s3 (33s Spray) | 2016-05-17 09:00 | 2016-05-17 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 1061L (12s Heartland - 681s Bannerman) | 2016-05-18 08:00 | 2016-05-19 17:00 | N | Y | urgent repair of helix dampers | Line |  |  | 240 kV
ATCO | 2029s ACF23 (2029s Heathfield) | 2016-05-18 08:00 | 2016-05-19 17:00 | N | Y | filter inspection and maintenance | Shunts |  | Filter Inspection and Maintenance on ACF23, redundant filter will remain in service, no impact to EATL transfer limits Perform Scheduled bi annual inspection/maintenance/testing on ACF23 equipment. | For Information Only, 500 kV
MONTANA | 120s 452 (120s Picture Butte) | 2016-05-18 08:00 | 2016-05-18 17:00 | N | Y | repair CT leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1038L (138s Windy Flats - 266s Foothills),1038L (138s Windy Flats - 237s Foothills),266s 1038L FSC (266s SC1) | 2016-05-18 08:00 | 2016-05-18 17:00 | N | Y | emergency repair; loose helix dampers | Line, Shunts |  |  | 240 kV
ENMAX | 16.61L (ENMAX 16 - ENMAX 27),16B69-16.61 (ENMAX 16),27B69-16.61 (ENMAX 27) | 2016-05-18 08:00 | 2016-05-19 16:00 | N | N | HV breaker inspection & doble | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 863s 902T (863s Paintearth) | 2016-05-18 09:00 | 2016-05-18 17:00 | N | N | bird guard can also be installed on 902T | Transformer |  |  | 240 kV
ALTALINK | 69s T4 (69s North Barrhead) | 2016-05-18 09:00 | 2016-05-19 17:00 | N | Y | repair multiple leaks on T4 | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek) | 2016-05-19 08:00 | 2016-05-19 17:00 | N | N | repair on loose dampers and conductor damage on line | Line |  |  | Creates Radial Feeds
ALTALINK | 1202L (89s Ellerslie - 320p Keephills),320p 3052 (320p Keephills),320p 3152 (320p Keephills) | 2016-05-19 09:00 | 2016-05-19 16:00 | N | Y | migrate airbreak 320P1202 to the new SCADA system and test | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds, 500 kV
ALTALINK | 746s T2 (746s Sherwood Park) | 2016-05-19 09:00 | 2016-05-19 12:00 | N | N | repair a PT | Transformer |  |  | For Information Only
DAISHOWA | 147S Daishowa Plant | 2016-05-19 17:00 | 2016-05-19 17:10 | N | N | ADAMS dispatch interruption due to forced reboot to address UPS issue | Station |  |  | For Information Only
ATCO | 800s 703C (800s Friedenstal),800s 703 (800s Friedenstal) | 2016-05-20 09:00 | 2016-05-20 15:00 | N | N | breaker SF6 HPL partial testing | Circuit Breaker, Shunts |  | 800S 703 BREAKER SF6 HPL PARTIAL TESTING, 703C 15 MVA capbank unavailable for dispatch
ENMAX | 2.83L (ENMAX 13 - ENMAX 2) | 2016-05-20 22:00 | 2016-05-21 04:00 | N | N | Calgary Zoo is installing a berm under the line (remove jumper to 5 sub) | Line |  |  | Pre-Condition
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2016-05-21 04:00 | 2016-05-22 22:00 | N | N | Calgary Zoo is installing a berm under the line | Line |  |  | Pre-Condition
ALTALINK | 1059L (38s East Edmonton - 1059AL tap),38s 7452 (38s East Edmonton),38s 7552 (38s East Edmonton) | 2016-05-21 17:00 | 2016-05-21 17:15 | N | Y | EPCOR requires 1059L de-energized in order to restore T1 @ E52s East Industrial | Line, Circuit Breaker |  |  | 240 kV
ATCO | 7L47 (848s Ruth Lake - 718s Parsons Creek) | 2016-05-22 08:00 | 2016-05-22 16:00 | N | N | pole replacement | Line |  |  | Pre-Condition
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 13 - ENMAX 2) | 2016-05-22 22:00 | 2016-05-23 04:00 | N | N | Calgary Zoo is installing a berm under the line (install jumper to 5 sub) | Line |  |  | Pre-Condition
ATCO | 9L07 (888s Dover - 2011s Dawes) | 2016-05-23 08:00 | 2016-05-23 16:00 | N | Y | depending on weather - complete insulator cleaning on 2 phases identified | Line |  |  | Pre-Condition
ATCO | 7L71 (848s Ruth Lake - 2082s Dog Rib) | 2016-05-23 08:00 | 2016-05-23 16:00 | N | N | pole replacement | Line |  |  | Pre-Condition
ENMAX | 9.1TR (ENMAX 9) | 2016-05-23 08:00 | 2016-05-27 16:00 | N | N | Doble | Transformer
ENMAX | 11.83L (162s Beddington - ENMAX 11),ENMAX 11 B138-11.83 (ENMAX 11) | 2016-05-23 08:00 | 2016-05-23 16:00 | N | Y | replace circuit breaker charging spring contacts | Line, Circuit Breaker |  |  | Pre-Condition
EPCOR | 557s 2401 (557s Castle Downs) | 2016-05-24 07:00 | 2016-05-28 17:00 | N | Y | breaker maintenance and doble | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
EPCOR | 72RV6 (Rossdale - 511s Victoria),Rossdale RV722 (Rossdale) | 2016-05-24 07:00 | 2016-05-28 17:00 | N | N | bushing refurbishment | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 646L (678s Okotoks - 237s Foothills) | 2016-05-24 07:00 | 2016-05-27 17:00 | N | N | replace dampers between structures #143 and #159 | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 159S Colinton | 2016-05-24 07:00 | 2016-05-26 07:00 | N | N | salvage 159s232 (25kV) and its protection | Station |  |  | For Information Only
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2016-05-24 08:00 | 2016-05-26 16:00 | N | Y | install new PT structure, install risers onto new 138kV SW | Line, Transformer, Shunts |  | install new PT structure. Harmonic Monitoring. Install risers onto new 138kV SW | For Information Only
ATCO | 2029s ACF21 (2029s Heathfield) | 2016-05-24 08:00 | 2016-05-27 17:00 | N | Y | perform maintenance on filter ACF21/breaker 1222 | Shunts |  | Perform maintenance on Filter ACF21/Breaker 1222 | For Information Only
ALTALINK | 421s C1 (421s Hays),421s 30 (421s Hays) | 2016-05-24 08:00 | 2016-05-27 17:00 | N | N | 138kV CT replacement | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 263s T1 (263s Strachan) | 2016-05-24 08:00 | 2016-05-26 08:00 | N | N | trip testing from new 138 kV bus differential | Transformer |  |  | For Information Only
ENMAX | 8.1TR (ENMAX 8) | 2016-05-24 08:00 | 2016-05-26 12:00 | N | N | transformer leak repair | Transformer |  |  | For Information Only
ALTALINK | 511s ACF12 (511s Crossings) | 2016-05-24 08:00 | 2016-05-25 17:00 | N | Y | inspection, clean insualtors, CTs and associated equipment | Shunts |  |  | 240 kV, For Information Only
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2016-05-24 08:00 | 2016-05-26 16:00 | N | Y | SCADA upgrade project | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2016-05-24 08:00 | 2016-05-24 16:00 | N | Y | repair 162MD240-162.2TR | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L165 (718s Parsons Creek - 933s Tower Road) | 2016-05-24 08:00 | 2016-05-24 16:00 | N | N | pole replacement | Line |  |  | For Information Only
ALTALINK | 263s C1 (263s Strachan),263s 35 (263s Strachan) | 2016-05-24 08:00 | 2016-06-02 16:30 | N | N | cut over CT contributions and trip testing from new 138 kV bus protections. replace CTs | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 32PT138-Z31 (ENMAX 32) | 2016-05-24 08:00 | 2016-05-24 16:00 | N | N | doble Test 138kV PT's & CT's | Terminal Equipment |  |  | For Information Only
EPCOR | Strathcona T1 (Strathcona) | 2016-05-24 08:00 | 2016-05-27 12:00 | N | N | doble test | Transformer |  |  | For Information Only
ATCO | 7L138 (788s Hotchkiss - 905s Meikle),788s 701 (788s Hotchkiss) | 2016-05-24 09:00 | 2016-05-24 14:30 | N | N | 788s 701 circuit breaker SF6 LTB145D1/B partial testing 7L138 open ended for the duration of the work | Line, Circuit Breaker |  | 788S 701 BREAKER SF6 LTB145D1/B PARTIAL TESTING 7L138 Open ended for the duration of the work | For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2016-05-24 09:00 | 2016-05-26 04:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 12s T1 (12s Heartland) | 2016-05-24 10:00 | 2016-06-02 17:00 | N | Y | SFRA, level pad | Transformer |  |  | 500 kV
SHELL | 402s 252 (402s Scotford Expansion) | 2016-05-24 10:00 | 2016-05-25 13:00 | N | N | breaker SF6 partial testing | Circuit Breaker |  | 402S - 252 BREAKER SF6 GL212 PARTIAL TESTING | For Information Only
ATCO | 7L97 (933s Tower Road - 7LA97) | 2016-05-24 16:00 | 2016-06-04 17:00 | N | N | to complete Athabasca river crossing | Line |  |  | For Information Only
ALTALINK | 250p11 (250p Bighorn) | 2016-05-25 06:00 | 2016-07-27 06:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 7L45 (845s Big Mountain - 798s Bridge Creek),845s 701 (845s Big Mountain),845s 702 (845s Big Mountain) | 2016-05-25 07:00 | 2016-06-05 17:30 | N | Y | replace line protection and add breaker fail protection | Line, Circuit Breaker |  | Replace line protection and add Breaker Fail protection, 144kV ring bus open @ 845s, 798s bridge ck will be radial fed from 813s. | Pre-Condition, Overload, Over/Under Voltage
ATCO | 6L82 (700s Bonnyville - 707s St.Paul) | 2016-05-25 07:00 | 2016-05-25 17:30 | N | N | cut 6L82 free from 6L82D2 at 707s St Paul | Line |  | Cut 6L82 free from 6L82D2 @ 707S St Paul. | Firm Load Loss, Creates Radial Feeds
ATCO | 707S St.Paul | 2016-05-25 07:00 | 2016-06-20 17:30 | N | N | rebuild 25kV bus | Station |  | Close jumper J3, rebuild 25 kv bus, remove 503VR connection to 25 kv bus, connect 501TD 505C, 506C1, and 505C2 will be OOS and unavailable for dispatch. | For Information Only
ALTALINK | 263s C1 (263s Strachan),718L (250p Bighorn Plant - 263s Strachan),870L (262s Rocky Mountain House - 263s Strachan),263s Strachan 138kV Bus 1,250p Bighorn 138kV Bus | 2016-05-25 07:00 | 2016-05-26 03:00 | N | Y | replace protection work | Line, Shunts, Bus |  | Coordinated with TransAlta & Fortis replace 263s718W CTs, replace 718L protections, replace 263s718W breaker fail, replace bus protection | Restricts Generation, Creates Radial Feeds
ENMAX | 771L (162s Beddington - ENMAX 47) | 2016-05-25 08:00 | 2016-05-25 16:00 | N | N | ENMAX maintenance (spring substation washing) | Line |  |  | For Information Only
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47) | 2016-05-25 08:00 | 2016-05-25 16:00 | N | N | spring substation washing | Line, Transformer |  |  | For Information Only
ATCO | 9L45 (856s Kinosis - 2049s Kettle River) | 2016-05-25 08:00 | 2016-05-27 16:00 | N | Y | pole replacement | Line |  |  | Pre-Condition
ALTALINK | 650s SVC (650s Hansman Lake) | 2016-05-25 08:00 | 2016-05-25 17:00 | N | Y | ABB warranty work on 650s T3 | Shunts |  |  | 240 kV
ALTALINK | 325s T1 (325s Leduc),632L (325s Leduc - 538s Buford),325s Leduc 138kV Bus 1 | 2016-05-25 08:00 | 2016-05-30 17:00 | N | N | close open points G, H and I and commission new 325s852 138 kV tie breaker | Bus, Line, Transformer |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L51 (927s Buchanan Creek - 788s Hotchkiss),788s 702 (788s Hotchkiss) | 2016-05-25 09:00 | 2016-05-25 14:30 | N | N | breaker SF6 partial testing | Line, Circuit Breaker |  | 788S 702 BREAKER SF6 LTB145D1/B PARTIAL TESTING 7L51 Open ended for the duration of the work | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 133S Stelco Edmonton,822L (133s Stelco Edmonton - 38s East Edmonton) | 2016-05-25 09:00 | 2016-05-25 17:00 | N | N | replace lightning arrestor on 133sT1 | Line, Station |  |  | Pre-Condition
ATCO | 735s 602T (735s Swan River) | 2016-05-25 09:30 | 2016-05-26 14:00 | N | N | testing on 602T and 502VR, equipment is intended for emergency only, no load carried. | Transformer |  | Testing on 602T and 502VR, Equipment is intended for emergency only, no load carried. | For Information Only
ALTALINK | 412L (396s Pincher Creek - 632s Russell) | 2016-05-25 12:00 | 2016-05-26 13:00 | N | Y | install 472s mobile at 396s | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 995S Rangelandyarrow | 2016-05-25 12:00 | 2016-05-25 14:00 | N | N | customer request to install a new breaker in their switchgear building | Station |  |  | For Information Only
SHELL | 402s 552 (402s Scotford Expansion) | 2016-05-25 13:00 | 2016-05-26 13:00 | N | N | breaker SF6 partial testing | Circuit Breaker |  | 402S - 552 BREAKER SF6 GL212 PARTIAL TESTING | Creates Radial Feeds
ALTALINK | 263s 870E (263s Strachan) | 2016-05-26 09:00 | 2016-05-26 12:00 | N | N | trip testing from new 138 kV bus differential protection if not completed during bus outage | Circuit Breaker |  |  | Pre-Condition, Overload, Creates Radial Feeds
ATCO | 717s 703T (717s Ethel Lake) | 2016-05-26 10:00 | 2016-05-26 16:00 | N | N | replace insulator pin and lightning shield ground on the 72kV Bus | Transformer |  |  | For Information Only
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2016-05-26 11:00 | 2016-06-09 17:00 | N | N | bushing replacement and oil reclamation | Transformer |  |  | For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2016-05-26 12:00 | 2016-05-27 16:00 | N | N | transformer leak repair | Transformer |  |  | For Information Only
ALTALINK | 263s 652 (263s Strachan) | 2016-05-26 12:00 | 2016-05-26 15:00 | N | N | trip testing from new 138 kV bus differential protection if not completed during bus outage | Circuit Breaker |  |  | Pre-Condition, Creates Radial Feeds
SHELL | 402s 652 (402s Scotford Expansion) | 2016-05-26 13:00 | 2016-05-27 15:00 | N | N | 402S - 652 breaker SF6 GL212 partial testing | Circuit Breaker |  | 402S - 652 BREAKER SF6 GL212 PARTIAL TESTING | For Information Only
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2016-05-26 20:56 | 2016-06-02 16:00 | N | N | forced outage | Line |  | Forced outage due to lightening. | For Information Only
ALTALINK | 396s T1 (396s Pincher Creek),396s T2 (396s Pincher Creek),396s T3 (396s Pincher Creek),412L (396s Pincher Creek - 632s Russell),613L (396s Pincher Creek - 103s Goose Lake) | 2016-05-27 08:00 | 2016-06-06 18:00 | N | Y | fix awitches & replace 138kV Bus PT | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1037L (138s Windy Flats - 237s Foothills) | 2016-05-27 08:00 | 2016-05-27 17:00 | N | Y | emergency damper replacement | Line |  |  | 240 kV, Overload
EPCOR | Garneau T1 (Garneau) | 2016-05-28 07:00 | 2016-05-28 12:00 | N | N | breaker operation checks | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2016-05-28 08:00 | 2016-05-31 16:00 | N | N | forced outage | Line
EPCOR | Garneau T2 (Garneau) | 2016-05-28 12:00 | 2016-05-28 17:00 | N | N | breaker operation checks | Transformer |  |  | For Information Only
EPCOR | Garneau T3 (Garneau) | 2016-05-29 07:00 | 2016-05-29 17:00 | N | N | gas relay repair | Transformer |  |  | Pre-Condition
EPCOR | Strathcona S722 (Strathcona) | 2016-05-30 07:00 | 2016-05-30 17:00 | N | N | Doble | Circuit Breaker |  |  | For Information Only
EPCOR | 72RV2 (Rossdale - 511s Victoria) | 2016-05-30 07:00 | 2016-07-29 17:00 | N | N | isolation for hydovacing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 557s 2403 (557s Castle Downs) | 2016-05-30 07:00 | 2016-06-04 17:00 | N | Y | breaker maintenance and Doble | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ATCO | 2029s ACF22 (2029s Heathfield) | 2016-05-30 08:00 | 2016-06-03 17:00 | N | Y | scheduled maintenance and inspection on ACF22 filter equipment and breaker 1223 | Shunts |  | Perform Scheduled Maintenance and Inspection on ACF22 filter equipment and breaker 1223, redundant filter will remain in service, no impact to EATL transfer capability | Pre-Condition, 500 kV
ENMAX | 31.1TR (ENMAX 31) | 2016-05-30 08:00 | 2016-06-03 16:00 | N | N | Doble transformer | Transformer |  |  | For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2016-05-30 08:00 | 2016-05-31 16:00 | N | N | LTC maintnenance | Transformer |  |  | For Information Only
ENMAX | 693L (42s Sarcee - ENMAX 10) | 2016-05-30 08:00 | 2016-06-03 16:00 | N | Y | replace strain insulators over 42s693 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 795L (121s Brooks - 421s Hays),421s 795N (421s Hays) | 2016-05-30 10:00 | 2016-06-02 17:00 | N | N | 138kV CT replacement | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 217s C1 (217s North Red Deer),217s 652 (217s North Red Deer) | 2016-05-30 10:30 | 2016-05-30 11:30 | N | N | de-energize cap bank for weed spraying | Switch, Shunts |  |  | Pre-Condition
ALTALINK | 42s C2 (42s Sarcee),42s 74 (42s Sarcee) | 2016-05-30 11:00 | 2016-06-09 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 151s C1 (151s Strathmore),151s 44 (151s Strathmore) | 2016-05-30 11:00 | 2016-05-30 17:00 | N | N | 138kV breaker maintenance and weed spraying | Circuit Breaker, Shunts |  |  | Pre-Condition
EPCOR | Strathcona S723 (Strathcona) | 2016-05-31 07:00 | 2016-05-31 17:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
ALTALINK | 325s T2 (325s Leduc) | 2016-05-31 07:00 | 2016-06-01 17:00 | N | N | close open points J and phase new switchgear building U/G cables | Transformer |  |  | For Information Only
EPCOR | 987s GB1B (987s Clover Bar) | 2016-05-31 07:00 | 2016-05-31 17:00 | N | N | breaker fail protection upgrade | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2016-05-31 08:00 | 2016-05-31 16:00 | N | Y | repair transformer tap changer mechanism | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 394s T1 (394s Empress),394s T3 (394s Empress),394s T4 (394s Empress),760L (394s Empress - 163s Amoco Empress),394s Empress 138kV Bus | 2016-05-31 08:00 | 2016-06-01 08:00 | N | N | tie in CT contributions from T4, T1, 760L, T3 for bus protection and test functionality | Transformer, Line, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),36B138-14.83 (ENMAX 36),ENMAX 14 B138-14.83 (ENMAX 14) | 2016-05-31 08:00 | 2016-06-01 16:00 | N | N | SF6 gas sample, lock & unlock coil circuit modification | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCOP | HSM1 House Mountain | 2016-05-31 08:00 | 2016-06-18 16:00 | N | N | In-service date: Jun 13, 2016 | Unit
ALTALINK | 394s T4 (394s Empress) | 2016-05-31 08:00 | 2016-06-01 08:00 | N | N | tie in CT contributions from T4 for bus protection and test | Transformer |  |  | For Information Only
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2016-05-31 08:00 | 2016-06-02 16:00 | N | Y | SCADA upgrade project | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss
ENMAX | 13.1TR (ENMAX 13) | 2016-05-31 08:00 | 2016-05-31 12:00 | N | N | remove trojan oil processor | Transformer |  |  | For Information Only
ALTALINK | 993S Abee,993s 701T (993s Abee) | 2016-05-31 09:00 | 2016-05-31 17:00 | N | N | repair leak on transformer | Transformer, Station |  |  | For Information Only
ALTALINK | 228S T.M.P.L.Niton,228s T1 (228s T.M.P.L.Niton) | 2016-05-31 10:00 | 2016-05-31 16:00 | N | N | techs will be testing protection | Transformer, Station |  |  | For Information Only
ENMAX | 13.2TR (ENMAX 13) | 2016-05-31 12:00 | 2016-05-31 16:00 | N | N | install trojan oil processor | Transformer |  |  | For Information Only
EPCOR | Garneau T2 (Garneau) | 2016-06-01 05:00 | 2016-06-01 11:00 | N | N | critical cable report | Transformer |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 420s 138kV Bus 2 (420s Broadmoor),731L (420s Broadmoor - 731L tap) | 2016-06-01 07:00 | 2016-06-02 17:30 | N | N | install screwpiles for 420s20 switch and 420s852 breaker | Bus, Line |  | Install screwpiles for 420s20 switch & 420s852 brkr, place brkr on piles (NOT connected to system), install 420s20 switch and connect to 138kV bus | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | Strathcona T1 (Strathcona),72RS5 (Rossdale - Strathcona) | 2016-06-01 07:00 | 2016-06-01 17:00 | N | N | doble | Transformer, Line |  |  | For Information Only
EPCOR | 987s CC13 (987s Clover Bar) | 2016-06-01 07:00 | 2016-06-01 17:00 | N | N | breaker fail protection upgrade | Circuit Breaker |  |  | For Information Only
EPCOR | 987s CGB2 (987s Clover Bar) | 2016-06-01 07:00 | 2016-06-01 17:00 | N | Y | breaker operation checks | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 394s T3 (394s Empress) | 2016-06-01 08:00 | 2016-06-02 08:00 | N | N | tie in contributions for bus protection | Transformer |  |  | For Information Only
ALTALINK | 267s C1 (267s Killarney Lake) | 2016-06-01 08:00 | 2016-06-01 09:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2016-06-01 08:00 | 2016-06-02 16:00 | N | N | LTC Maintenance | Transformer |  |  | For Information Only
ALTALINK | 394s T2 (394s Empress),394s T4 (394s Empress),668L (394s Empress - 562s Cypress),394s Empress 138kV Bus | 2016-06-01 08:30 | 2016-06-01 15:00 | N | N | tie in CT contributions from T2 and 668L for bus protection,tie in CT contributions from T2 and 668L for bus protection. | Transformer, Bus, Line |  | Tie in CT contributions from T2 and 668L for bus protection. Trip test 394s668 breaker from bus protection. Tie in CT contributions from T4 for T2 protections. Trip test 394s41 for T2 protections. Test 394s32 control module functionality. | Creates Radial Feeds
ALTALINK | 267s C2 (267s Killarney Lake) | 2016-06-01 09:00 | 2016-06-01 10:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 267s C3 (267s Killarney Lake) | 2016-06-01 10:00 | 2016-06-01 11:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 221s C1 (221s Sunken Lake) | 2016-06-01 12:30 | 2016-06-01 13:30 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 394s T3 (394s Empress) | 2016-06-01 15:00 | 2016-06-02 08:00 | N | N | T3 isolated overnight to reduce switching the morning of June 2 | Transformer |  |  | For Information Only
ALTALINK | 394s T2 (394s Empress) | 2016-06-01 15:15 | 2016-06-20 17:00 | N | N | T2 replacement | Transformer |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar),987s CC721 (987s Clover Bar) | 2016-06-02 07:00 | 2016-06-02 17:00 | N | Y | BF protection upgrade | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 524S Fiberglas | 2016-06-02 07:00 | 2016-06-02 11:00 | N | N | Customer outage | Station |  |  | For Information Only
ALTALINK | 394s T3 (394s Empress),394s 35 (394s Empress) | 2016-06-02 08:00 | 2016-06-03 16:00 | N | N | T3 and T2 cutovers and trip tests | Transformer, Switch |  |  | For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15),15B69-15.60 (ENMAX 15) | 2016-06-02 08:00 | 2016-06-02 16:00 | N | N | HV breaker inspection - HV maintenance on SW 67 @ 21 sub | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 161L (255s Vulcan - 504s Queenstown),504s 161 (504s Queenstown) | 2016-06-02 08:00 | 2016-06-02 17:00 | N | N | 138 kV breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 431s C1 (431s Hussar),431s 152 (431s Hussar) | 2016-06-02 10:00 | 2016-06-02 11:00 | N | N | de-energize cap bank for weed spraying | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 253s C1 (253s Blackie),253s 182 (253s Blackie) | 2016-06-02 12:30 | 2016-06-02 13:30 | N | N | de-energize cap bank for weed spraying | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 142s 3 (142s Magcan),142s C1 (142s Magcan) | 2016-06-02 14:00 | 2016-06-02 15:00 | N | N | de-energize cap bank for weed spraying | Shunts, Circuit Breaker |  |  | For Information Only
EPCOR | 72CN10 (987s Clover Bar - Namao),987s CN723 (987s Clover Bar) | 2016-06-03 07:00 | 2016-06-03 17:00 | N | N | BF protection upgrade | Circuit Breaker, Line |  |  | Creates Radial Feeds
ALTALINK | 394s T2 (394s Empress) | 2016-06-03 08:00 | 2016-06-04 17:00 | N | N | jack and roll existing transformer out and new one in | Transformer |  |  | For Information Only
ATCO | 845s 703 (845s Big Mountain) | 2016-06-03 08:00 | 2016-06-05 16:00 | N | N | remove shorts and grounding | Circuit Breaker |  | This T&O will be requested after all GOI and CSPs related to 7L45 line will be released and 701 and 702 are both back in service @ 845s, 144kV ring will be open for 20-30 min, 7L13, 7L20 will remain in service Remove shorts and grounding in 703CT junction box for ION/7L13. CT circuits are prepared but ION relay will not be install until 7L45 outage due to limited space in the panel. | For Information Only
Saskpower | Sask Power RE901T | 2016-06-03 17:00 | 2016-06-24 15:40 | N | Y | Test from a lock out trip | Transformer |  |  | Limits ATC
ACCIONA | 226S Magrath DVAr | 2016-06-06 00:45 | 2016-06-06 17:27 | N | N | forced outage due to communication failure | Terminal Equipment |  |  | For Information Only
ENMAX | 31.1C (ENMAX 31) | 2016-06-06 03:07 | 2016-06-07 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
EPCOR | 330p 806 (330p Genesee) | 2016-06-06 07:00 | 2016-06-12 17:00 | N | N | protection upgrade | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 198s T2 (198s Blackfalds) | 2016-06-06 07:00 | 2016-06-17 17:00 | N | N | Blackie upgrade project: T2 transformer replacement | Transformer |  |  | For Information Only
EPCOR | Rossdale RR723 (Rossdale) | 2016-06-06 07:00 | 2016-06-10 17:00 | N | N | breaker maintenance & doble | Circuit Breaker
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2),749s 702 (749s Flyingshot Lake),749s 703 (749s Flyingshot Lake) | 2016-06-06 07:00 | 2016-06-19 17:30 | N | Y | replace line protection | Circuit Breaker, Line |  | Replace line protection., 7L03 will be open ended at 749s, 144kV ring will be open @ 749s | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L135 (820s Hangingstone - 977s Salt Creek) | 2016-06-06 08:00 | 2016-06-07 20:00 | N | N | emergency pole replacement | Line |  |  | Pre-Condition
ALTALINK | 377s T1 (377s Hardisty) | 2016-06-06 08:00 | 2016-08-19 17:00 | N | N | relocating 25kV feeders inside of new switch gear building and salvaging existing 25kV gear | Transformer |  |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),15B69-15.62 (ENMAX 15),16B69-15.62 (ENMAX 16) | 2016-06-06 08:00 | 2016-06-08 16:00 | N | N | breaker inspection and doble | Line, Circuit Breaker |  | HV Breaker Inspection (16B69-15.62 & 15B69-15.62), Doble Test HV Breaker 16B69-15.62 Jun7 . Tower Inspection | Firm Load Loss, Creates Radial Feeds
ENMAX | 8.1TR (ENMAX 8) | 2016-06-06 08:00 | 2016-06-07 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 36.2TR (ENMAX 36) | 2016-06-06 08:00 | 2016-06-10 16:00 | N | N | Doble test | Transformer |  |  | For Information Only
ALTALINK | 1203L (320p Keephills - 510s Sunnybrook) | 2016-06-06 08:00 | 2016-06-06 10:00 | N | Y | urgent repair on structure 2 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 821L (158s Vauxhall - 421s Hays),421s 821W (421s Hays) | 2016-06-06 10:00 | 2016-06-09 17:00 | N | N | 138 kV CT replacement | Line, Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 760L (394s Empress - 163s Amoco Empress),394s 760N (394s Empress) | 2016-06-06 10:00 | 2016-06-06 12:00 | N | N | trip test T2 protection | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO | 729s 703T (729s Otauwau) | 2016-06-06 10:00 | 2016-06-07 16:00 | N | N | perform major maintenance on 703T | Transformer |  | Perform Major Maintenance on 703T, 25KV load carried by 701T by closing N.O. 500D3 | For Information Only
ALTALINK | 434s T3 (434s East Stony Plain) | 2016-06-06 11:00 | 2016-06-08 17:00 | N | N | urgent repair a bad leak on the transformer | Transformer
ALTALINK | 668L (394s Empress - 562s Cypress),394s 668 (394s Empress) | 2016-06-06 13:00 | 2016-06-06 15:00 | N | N | trip test T2 protection | Line, Circuit Breaker |  | Trip test T2 protectionScheduled By: Mohamed Maremi Issue to: Tyson Eckel Contact #: 403-818-8343 | Pre-Condition, Creates Radial Feeds
ALTALINK | 341S Sand Hills Sub | 2016-06-06 13:00 | 2016-06-06 17:00 | N | N | customer moving AC power feeding panel for RTU | Station |  |  | For Information Only
EPCOR, ALTALINK | 665s TX1 (665s Dome),909L (89s Ellerslie - 665s Dome),665s D2401 (665s Dome),665s D2402 (665s Dome) | 2016-06-07 07:00 | 2016-06-16 17:30 | N | Y | upgrade of 240 kV BF protection | Transformer, Circuit Breaker, Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome),89s 1052 (89s Ellerslie),89s 1152 (89s Ellerslie) | 2016-06-07 07:00 | 2016-06-07 07:30 | N | Y | EPCOR work @ 665s, requires 909L de-energized to open isolation points as per their procedure | Line, Circuit Breaker |  |  | 240 kV, Overload
ALTALINK | 1075L (132s Ware Junction - 28s West Brooks) | 2016-06-07 08:00 | 2016-06-09 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV
ALTALINK | 796L (405s Waupisoo - 796L28),405s 796 (405s Waupisoo) | 2016-06-07 08:00 | 2016-06-07 16:00 | N | Y | DDR install | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 852s Round Hill RTU/SCADA | 2016-06-07 08:00 | 2016-06-07 16:00 | N | N | upgrade the firmware on one of the stations IEDs to repair a cycling issue | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 28s West Brooks RTU/SCADA | 2016-06-07 08:00 | 2016-06-07 16:00 | N | N | download new configuration file to the RTU at West Brooks 28s | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 341s T1 (341s Sand Hills Sub) | 2016-06-07 08:30 | 2016-06-07 17:00 | N | N | transformer maintenance and doble | Transformer |  |  | For Information Only
ALTALINK | 355s T1 (355s Chevron Knight) | 2016-06-07 08:30 | 2016-06-07 17:00 | N | N | transformer doble test | Transformer |  |  | For Information Only
ALTALINK | 434L (65s High River - 237s Foothills) | 2016-06-07 09:00 | 2016-06-07 17:00 | N | N | replace breaker tank heaters and add corona rings on str 434L116. | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 871L (341s Sand Hills - 163s Amoco Empress),163s 871X (163s Amoco Empress) | 2016-06-07 09:00 | 2016-06-07 13:00 | N | N | wire into CT circuits for PMU relay install on L7 | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 412L (396s Pincher Creek - 632s Russell) | 2016-06-07 11:00 | 2016-06-07 18:00 | N | Y | install 472s mobile at 396s | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 760L (163s Amoco Empress - 760L41) | 2016-06-07 13:30 | 2016-06-09 16:00 | N | Y | replace 163s2 PT | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2016-06-08 08:00 | 2016-06-11 15:00 | N | Y | rewire of DC power cable to 510s1452 | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 28s 12 (28s West Brooks) | 2016-06-08 08:00 | 2016-06-09 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 132s 12 (132s Ware Junction) | 2016-06-08 08:00 | 2016-06-08 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 34.2TR (ENMAX 34) | 2016-06-08 08:00 | 2016-06-09 16:00 | N | N | LTC maintnenance | Transformer |  |  | For Information Only
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2016-06-08 09:00 | 2016-06-10 17:00 | N | Y | deadend insulator replacements | Line |  |  | Limits ATC
ALTALINK | 396s C1 (396s Pincher Creek) | 2016-06-08 10:00 | 2016-06-08 11:00 | N | N | de-energize for weed spraying in cap bank area | Shunts |  |  | For Information Only
ALTALINK | 661S Laura Lake | 2016-06-09 08:00 | 2016-06-09 17:00 | N | N | techs to perform standard relay maintenance on 50/51/27/79/L1 L1 | Station |  |  | For Information Only
ALTALINK | 377s 769X (377s Hardisty) | 2016-06-09 08:00 | 2016-06-09 15:00 | N | N | tank heater replacement | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.4TR (ENMAX 39) | 2016-06-09 08:00 | 2016-06-09 16:00 | N | N | investigate and repair liquid temp gauge | Transformer |  |  | For Information Only
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2016-06-09 10:00 | 2016-06-09 14:00 | N | N | High load move under 890L and 671L | Line |  | High load move under 890L and 671L | Firm Load Loss, Creates Radial Feeds
ALTALINK | 54L (118s Canmore - 54L172) | 2016-06-09 13:00 | 2016-06-09 14:00 | N | N | urgent repair to str 146 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2016-06-09 17:00 | 2016-06-10 07:30 | N | N | High load move under 746L | Line |  | High load move under 746L | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station),1055L (816s Petrolia - 629s Argyll Transfer Station) | 2016-06-10 07:00 | 2016-07-05 17:00 | N | Y | tower refurbishment | Line |  |  | 240 kV, Over/Under Voltage
ALTALINK | 854L (1012s Deer Hill - 854L229) | 2016-06-10 07:00 | 2016-06-10 17:00 | N | N | replace hardware on flying taps outside of 1012s | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 703L (377s Hardisty - 703BL tap) | 2016-06-10 08:00 | 2016-06-10 17:00 | N | N | maintenance repairs on structures 1,2,7 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington) | 2016-06-11 06:30 | 2016-06-19 08:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 685L (397s Benbow - 1012s Deer Hill) | 2016-06-11 07:00 | 2016-06-11 17:00 | N | N | replace hardware on flying taps outside 1012s | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 444L (198s Blackfalds - 217s North Red Deer),198s 444 (198s Blackfalds) | 2016-06-11 09:00 | 2016-06-11 10:00 | N | N | Blackfalds Project: complete functional tests to T1 | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CN723 (987s Clover Bar) | 2016-06-13 07:00 | 2016-06-13 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Creates Radial Feeds
EPCOR | 805s J2406 (805s Jasper) | 2016-06-13 07:00 | 2016-06-14 17:00 | N | Y | Doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34),34B69-21.61 (ENMAX 34) | 2016-06-13 08:00 | 2016-06-14 16:00 | N | N | HV breaker inspection. HV SW maintenance on SW 61 @ 21 sub | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 8.5TR (ENMAX 8) | 2016-06-13 08:00 | 2016-06-17 16:00 | N | N | doble Tx | Transformer |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2016-06-13 08:00 | 2016-06-17 16:00 | N | N | LTC maintenance (Reinhausen type 3) | Transformer |  |  | For Information Only
ENMAX | 32PT138-Z31 (ENMAX 32) | 2016-06-13 08:00 | 2016-06-13 16:00 | N | N | Doble test PT's & CT's | Terminal Equipment |  |  | For Information Only
ALTALINK | 681s T1 (681s Bannerman),681s 252 (681s Bannerman),681s 1152 (681s Bannerman) | 2016-06-13 08:30 | 2016-06-16 17:00 | N | Y | funtional testing to prove all trips are working correctly | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ATCO | 757s 706 (757s Battle River) | 2016-06-13 09:00 | 2016-06-16 16:00 | N | N | min oil HPF complete testing | Circuit Breaker |  | 757S - 706 BREAKER MIN OIL HPF COMPLETE TESTING Floating breaker will be out of service | For Information Only
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2016-06-13 09:00 | 2016-06-23 17:00 | N | Y | insulator replacements and arcing horn installations | Line |  |  | Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2016-06-13 10:00 | 2016-06-13 16:00 | N | Y | salvage telecom tower at 37s that is in close proximity | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2016-06-13 10:00 | 2016-06-17 17:00 | N | N | line maintenance & repairs | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s 76 (37s North Calder) | 2016-06-13 11:00 | 2016-06-16 17:00 | N | Y | 240kV breaker maintenance and replace ops counter | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 163s T1 (163s Amoco Empress) | 2016-06-13 12:30 | 2016-07-05 14:00 | N | Y | replace 163s T1 bushings, T1 maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 478s T1 (478s Tucuman) | 2016-06-13 13:00 | 2016-06-13 17:00 | N | N | installing upgraded bird coverup | Transformer |  |  | For Information Only
ALTALINK | 163s C1 (163s Amoco Empress) | 2016-06-13 13:00 | 2016-06-13 14:00 | N | N | de-energize for cap bank area weed spraying. | Shunts |  |  | For Information Only
ALTALINK | 163s C2 (163s Amoco Empress) | 2016-06-13 14:00 | 2016-06-13 15:00 | N | N | de-energize for cap bank area weed spraying | Shunts |  |  | For Information Only
ALPAC | 282S Grassland (Alpac) | 2016-06-13 17:00 | 2016-06-13 20:00 | N | N | telephone system upgrade | Station |  |  | For Information Only
ATCO | 844s 701T (844s AEC Mill) | 2016-06-14 07:00 | 2016-06-14 14:00 | N | N | coordinated with customer outage. Install new parts for oil filter | Transformer |  | Coordinated with customer outage see CROW# 2-37214. Fix Oil Leak Near Filter Connection, Install new Parts for Oil filter. | For Information Only
ALTALINK | 198s T2 (198s Blackfalds),198s Blackfalds 138kV Bus 2,444L (198s Blackfalds - 217s North Red Deer),198s 352 (198s Blackfalds) | 2016-06-14 07:00 | 2016-06-17 17:00 | N | N | add new 25kV breaker, new 138kV PTs-VT4 and new 138kV tie breaker | Line, Circuit Breaker, Transformer, Bus |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 284S Nose Creek | 2016-06-14 07:00 | 2016-06-16 12:00 | N | N | customer maintenance on switchgear building | Station |  |  | For Information Only
ALTALINK | 377s C1 (377s Hardisty) | 2016-06-14 08:00 | 2016-06-14 17:00 | N | N | maintenance on 473s102, cap bank capacitor replacement & weed spraying | Shunts |  |  | For Information Only
ALTALINK | 945s T1 (945s Sunshine Village) | 2016-06-14 08:00 | 2016-06-16 17:00 | N | N | repair oil leaks on transformer | Transformer |  |  | For Information Only
ALTALINK | 123s T1 (123s Banff) | 2016-06-14 08:00 | 2016-06-14 16:00 | N | N | ACC visibility enhancements, T1 gas relay replacement, repair broken conduit, investigate T1/T2 out of step alarm | Transformer |  |  | Creates Radial Feeds
ALTALINK | 931L (132s Ware Junction - 28s West Brooks),132s 55 (132s Ware Junction),132s 51 (132s Ware Junction) | 2016-06-14 08:00 | 2016-06-16 16:00 | N | Y | SCADA upgrade project | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 162s 240-RB131 (162s Beddington),162s 240-RB132 (162s Beddington) | 2016-06-15 06:30 | 2016-06-17 18:00 | N | N | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
EPCOR | 805s J2405 (805s Jasper) | 2016-06-15 07:00 | 2016-06-17 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s CK726 (987s Clover Bar) | 2016-06-15 07:00 | 2016-06-15 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Creates Radial Feeds
EPCOR | 557s 2404 (557s Castle Downs) | 2016-06-15 07:00 | 2016-06-17 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 221s T2 (221s Sunken Lake) | 2016-06-15 08:00 | 2016-06-15 22:00 | N | N | transformer maintenance, 221s28 protection and doble | Transformer |  |  | For Information Only
ENMAX | 162s 240-RB131 (162s Beddington),162s 240-RB132 (162s Beddington),162s Beddington 240 kV North Bus | 2016-06-15 08:00 | 2016-06-15 16:00 | N | Y | fall substation washing | Bus, Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 118s C1 (118s Canmore) | 2016-06-15 08:00 | 2016-06-15 09:00 | N | N | de-energize capacitor bank for weed spraying | Shunts |  |  | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),34B69-16.60 (ENMAX 34) | 2016-06-15 08:00 | 2016-06-16 16:00 | N | N | HV breaker inspection | Circuit Breaker, Line |  |  | Creates Radial Feeds
ALTALINK | 216s T1 (216s Knightsbridge) | 2016-06-15 08:30 | 2016-06-15 21:00 | N | N | Enbridge requirement for maintenance | Transformer |  |  | For Information Only
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely),15s 180N (15s Fort Macleod) | 2016-06-15 10:00 | 2016-06-15 12:00 | N | N | demo downstream CT contribution from Bus protection 15s180N CTs to L5, 180L A RAS module and demo RAS relay | Circuit Breaker, Line |  | Take Bus Protection out of service and demo downstream CT contribution from Bus protection 15s180N to L5 180L A RAS module and demo RAS Relay.80N | Creates Radial Feeds
ALTALINK | 671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale) | 2016-06-15 13:00 | 2016-06-15 17:00 | N | N | high load move under 671L,high load move under 890L | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CCP7214 (987s Clover Bar) | 2016-06-16 07:00 | 2016-06-16 17:00 | N | N | breaker maintenance | Circuit Breaker
AESO-SC | Critical application migration | 2016-06-16 07:00 | 2016-06-16 12:00 | N | N | migration | SCInternal |  |  | For Information Only
ENMAX | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington) | 2016-06-16 08:00 | 2016-06-16 16:00 | N | Y | fall substation washing | Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
ATCO | 834s 701 (834s Wesley Creek) | 2016-06-16 08:30 | 2016-06-16 15:00 | N | N | breaker 701 partial PM | Circuit Breaker |  | Breaker 701 Partial PM, 144kV Ring Open for the duration of the work | Contingency Requires Mitigation
ALTALINK | 89s 1052 (89s Ellerslie),89s 1152 (89s Ellerslie) | 2016-06-16 17:00 | 2016-06-16 17:30 | N | Y | requires 909L de-energized to close isolation points as per procedure | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28) | 2016-06-17 16:00 | 2016-06-26 16:00 | N | N | installing transmission line duct bank | Line |  |  | Creates Radial Feeds
ENMAX | 43.1TR (ENMAX 43),9.83L (ENMAX 43 - ENMAX 9),ENMAX 9 B138-9.83 (ENMAX 9) | 2016-06-18 08:00 | 2016-06-19 16:00 | N | N | maintenance | Line, Circuit Breaker, Transformer |  | HV SW MTCE on SW 83 @ 43 sub. Sheath Test & DGA on LPOF 138KV cable. HV Breaker Inspection 9B138-9.83 (HLR) | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2016-06-18 08:00 | 2016-06-19 16:00 | N | N | lock & unlock coil circuit modification | Line |  | Lock & Unlock coil circuit modifcation on 11B138-11.82 & 14B138-11.82, Repair corona issues on deadend, 4 insulators to change out. | Creates Radial Feeds
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2016-06-18 08:00 | 2016-06-19 16:00 | N | N | ENMAX maintenance | Line |  | (Lock & Unlock coil circuit modifcation on 11B138-11.82 & 14B138-11.82, Repair corona issues on deadend, 4 insulators to change out)
EPCOR | 330P 12TC1 (330p Genesee),330P Genesee 500 kV Bus 1 | 2016-06-19 07:00 | 2016-06-28 17:00 | N | Y | protection upgrade | Transformer, Bus |  |  | Contingency Requires Mitigation, 500 kV
ENMAX, ALTALINK | 36.81L (44s Bearspaw - ENMAX 36) | 2016-06-20 07:00 | 2016-06-21 16:00 | N | Y | lock and unlock coil circuit modification on 36B138-36.81 and change insulator on structure #20 | Line |  |  | For Information Only
Medicine Hat | MH69s3 MH69_314 (MH69s3 South Ridge),MH69s3 MH69_316 (MH69s3 South Ridge) | 2016-06-20 07:00 | 2016-06-24 16:00 | N | N | to replace disconnect switch MH69-315 | Circuit Breaker |  |  | For Information Only
EPCOR | 557s 2405 (557s Castle Downs) | 2016-06-20 07:00 | 2016-06-24 17:00 | N | Y | breaker maintenance and doble | Circuit Breaker |  |  | 240 kV
EPCOR | 805s J2404 (805s Jasper) | 2016-06-20 07:00 | 2016-06-21 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s GB1B (987s Clover Bar) | 2016-06-20 07:00 | 2016-07-15 17:00 | N | N | breaker replacement | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Limits Ratings, Firm Load Loss, Creates Radial Feeds
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky),813s 704 (813s Little Smoky),813s 703 (813s Little Smoky) | 2016-06-20 07:00 | 2016-07-07 17:00 | N | Y | replace line protection and add breaker fail protection | Circuit Breaker, Line |  | Replace line protection and add Breaker Fail protection, 144kV ring bus open @ 813s, 798s bridge ck will be radial fed from 845s. | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR, ALTALINK | 665s TX2 (665s Dome),320p 1352 (320p Keephills),909L (320p Keephills - 665s Dome) | 2016-06-20 07:00 | 2016-06-29 17:00 | N | Y | upgrade of 240 kV breaker fail protection | Transformer, Line, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31B138-31CAP (ENMAX 31) | 2016-06-20 08:00 | 2016-06-21 16:00 | N | N | investigate cap bank trip | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 322s T3 (322s Cowley Ridge) | 2016-06-20 08:00 | 2016-06-24 16:00 | N | N | isolate internal pad mount transformer | Transformer |  | require couple minutes to open 69CS3 to open the disconnect 35DS3. | For Information Only
ATCO | 7L70 (700s Bonnyville - 707s St.Paul) | 2016-06-20 08:00 | 2016-06-21 16:00 | N | N | line construction | Line |  | Line construction, 7L139 will radial feed 707s, on RTN 701T @ 707s will be placed in service | Firm Load Loss, Creates Radial Feeds
ALTALINK | 669L (163s Amoco Empress - 562s Cypress) | 2016-06-20 08:00 | 2016-06-28 12:00 | N | N | replace 163s669 breaker, current transformers,and add new surge arresters | Line |  |  | For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2016-06-20 08:00 | 2016-06-24 16:00 | N | N | doble transformer | Transformer |  |  | For Information Only
CENOVUSFCCL, CENOVUS | CL01 Christina Lake Generator Test | 2016-06-20 08:00 | 2016-08-06 18:00 | N | N | commissioning test | Unit
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),ENMAX 31 B138-31.84 (ENMAX 31) | 2016-06-20 08:00 | 2016-06-23 16:00 | N | N | HV breaker inspection and SF6 gas sample | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 681s T2 (681s Bannerman),681s 152 (681s Bannerman),681s 1052 (681s Bannerman) | 2016-06-20 08:00 | 2016-06-21 15:58 | N | Y | functional testing | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 452S B.F. Goodrich Fort Saskatchewan | 2016-06-20 08:00 | 2016-06-20 17:00 | N | N | station bird cover-up installation | Station |  |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2016-06-20 08:00 | 2016-06-21 16:00 | N | N | photos and measurements of CT's | Transformer |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14) | 2016-06-20 08:00 | 2016-06-21 16:00 | N | N | relay testing | Shunts |  |  | For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa) | 2016-06-20 09:00 | 2016-06-20 17:00 | N | N | structure 6 pole raise for future high load move | Line |  |  | Creates Radial Feeds
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2016-06-20 10:00 | 2016-06-24 17:00 | N | N | 3L structure repair (42s - 272s) | Line |  |  | Creates Radial Feeds
ALTALINK | 703L (213s Hughenden - 703AL tap) | 2016-06-20 10:00 | 2016-06-24 17:00 | N | N | line maintenance and repairs | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2016-06-20 10:00 | 2016-06-27 08:00 | N | N | line maintenance | Line |  |  | Creates Radial Feeds
ALTALINK | 69s T2 (69s North Barrhead) | 2016-06-20 13:00 | 2016-06-23 17:00 | N | N | 138kV bushing replacement | Transformer |  |  | For Information Only
ENMAX | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7) | 2016-06-21 05:00 | 2016-06-21 10:00 | N | N | repair SW89 at ENMAX 36 | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 720S Wabasca | 2016-06-21 07:00 | 2016-06-21 17:30 | N | N | rewire station service | Station |  | Rewire Station Service; remove AC feed to old building. AC will be restored once cable is removed safely; outage will last 2 hr maximum. AC Fail and Station Major will be active during outage. | For Information Only
ALTALINK | 1053L (132s Ware Junction - 324s Cassils) | 2016-06-21 08:00 | 2016-06-23 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Overload
ALTALINK | 72s T1 (72s Leismer) | 2016-06-21 08:00 | 2016-06-21 20:00 | N | Y | replace T1 bushings, add bird cover-Up, 72s3 fuse repairs, 72s319W maintenance, 72s319E maintenance | Transformer |  |  | 240 kV
ALTALINK | 133S Stelco Edmonton,38s 822X (38s East Edmonton),822L (133s Stelco Edmonton - 38s East Edmonton) | 2016-06-21 08:00 | 2016-06-23 16:00 | N | N | AltaSteel work | Station, Line, Circuit Breaker |  |  | Firm Load Loss
ENMAX | 43.2TR (ENMAX 43) | 2016-06-21 08:00 | 2016-06-21 16:00 | N | N | photos and measurements of CT's & PT's | Transformer |  |  | For Information Only
ALTALINK | 83s C1 (83s Taber) | 2016-06-21 08:30 | 2016-06-21 09:30 | N | N | de-energize for weed spraying in cap bank area. | Shunts |  |  | For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt),364s 797 (364s Whitecourt Industrial) | 2016-06-21 09:00 | 2016-06-21 12:00 | N | N | both TPR Channels will be out of service for an MPLS firmware upgrade between 268s & 9269R | Line, Circuit Breaker |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 394s T1 (394s Empress) | 2016-06-21 09:00 | 2016-06-28 10:00 | N | N | taking T2 load readings | Transformer |  |  | For Information Only
ALTALINK | 83s C2 (83s Taber) | 2016-06-21 09:30 | 2016-06-21 10:30 | N | N | de-energize for weed spraying in cap bank area. | Shunts |  |  | Pre-Condition
ALTALINK | 421s C1 (421s Hays),421s 30 (421s Hays) | 2016-06-21 11:00 | 2016-06-21 12:00 | N | N | de-energize for weed spraying in cap bank area | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 701L (395s North Holden - 223s Strome) | 2016-06-21 11:00 | 2016-06-22 18:00 | N | N | forced outage due to relay issues | Line
ENMAX | 36.1TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),ENMAX 36 138kV Bus | 2016-06-22 05:00 | 2016-06-22 10:00 | N | N | repair 36MD138-36.1TR at ENMAX 36 | Line, Transformer, Bus |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2403 (805s Jasper) | 2016-06-22 07:00 | 2016-06-23 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 72s 552 (72s Leismer) | 2016-06-22 08:00 | 2016-06-23 17:00 | N | Y | 240kV circuit breaker maintenance | Circuit Breaker |  |  | 240 kV
ENMAX | 13.3TR (ENMAX 13) | 2016-06-22 08:00 | 2016-06-22 16:00 | N | N | install trojan oil processor | Transformer |  |  | For Information Only
ENMAX | 14.2C (ENMAX 14) | 2016-06-22 08:00 | 2016-06-23 16:00 | N | N | relay testing | Shunts |  |  | For Information Only
ATCO | 840S McNeill Station | 2016-06-22 09:00 | 2016-06-22 17:00 | N | Y | to upgrade the communications at 840S McNeill | Station |  |  | For Information Only
ALTALINK | 985s 811QC03 (985s Exshaw) | 2016-06-23 08:00 | 2016-06-27 16:00 | N | N | install new cable | Circuit Breaker |  |  | For Information Only
ATCO | 732s 906 (732s Mitsue) | 2016-06-23 08:30 | 2016-06-24 14:00 | N | Y | partial PM on circuit breaker 906 | Circuit Breaker |  | Partial PM on Bkr 906, 240kV ring will be open | 240 kV, For Information Only
ALTALINK | 1107L (ENMAX 65 - 237s Foothills),1106L (ENMAX 65 - 237s Foothills) | 2016-06-24 08:00 | 2016-06-24 14:00 | N | Y | emergency damper replacement | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 310p 2452 (310p Sundance),310p 2352 (310p Sundance),310p 6G (310p Sundance) | 2016-06-24 21:00 | 2016-06-26 21:00 | N | N | repair hot spot | Switch, Circuit Breaker |  |  | Restricts Generation
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37),ENMAX 37 B138-37.81 (ENMAX 37) | 2016-06-25 08:00 | 2016-06-26 16:00 | N | N | breaker inspection and Doble PT | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1037L (138s Windy Flats - 237s Foothills),1038L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1),266s 1038L FSC (266s SC1) | 2016-06-25 09:00 | 2016-06-25 17:00 | N | Y | emergency damper replacement | Line, Shunts |  |  | 240 kV, Pre-Condition
EPCOR | 805s J2401 (805s Jasper) | 2016-06-27 07:00 | 2016-06-28 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 322s T2 (322s Cowley Ridge) | 2016-06-27 08:00 | 2016-06-30 16:00 | N | N | work on low side | Transformer |  |  | For Information Only
ENMAX | 31.1C (ENMAX 31) | 2016-06-27 08:00 | 2016-06-28 16:00 | N | N | HV breaker inspection, | Shunts |  |  | Pre-Condition
ENMAX | 41.1TR (ENMAX 41) | 2016-06-27 08:00 | 2016-06-28 16:00 | N | N | LTC maintenance, LV bushing investigation | Transformer |  |  | For Information Only
ATCO | 757S Battle River | 2016-06-27 09:00 | 2017-05-15 16:00 | N | N | cracked insulators maintenance on main bus | Station |  | We have found some insulators on the main bus at Battle River that are cracked and Engineering would like us to switch over to the transfer bus before we have a failure and cause an outage. It might stay like that for a few months as they are going to order enough to change all the insulators on the main bus. | Pre-Condition
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s T1 (42s Sarcee),916L (42s Sarcee - 5s East Calgary),928L (17s Benalto - 42s Sarcee),42s Sarcee 240kV North Bus | 2016-06-27 10:00 | 2016-06-27 17:00 | N | Y | Open jumpers on North bus to facilitate insulator replacement. 916L will remain out of service until all insulators are replaced and North Bus jumpers are restored on July 15 | Line, Bus, Shunts, Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2016-06-27 10:00 | 2016-06-27 17:00 | N | N | urgent repair on conductor | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (746s Sherwood Park - 700L TAP),700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2016-06-27 10:00 | 2016-06-27 17:00 | N | N | line Move -str 111 moving approximately 25m south | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 827s SVC (827s Cranberry Lake),827s 703 (827s Cranberry Lake) | 2016-06-27 10:00 | 2016-06-28 15:00 | N | Y | partial PM's on 703 and 401 Breakers, SVC offline during testing | Shunts, Circuit Breaker |  | Partial PM's on 703 and 401 Breakers, SVC offline during testing | For Information Only
ALTALINK | 89s 952 (89s Ellerslie) | 2016-06-27 10:30 | 2016-06-27 17:00 | N | Y | rebuilding trip dashpot | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 12s 1652 (12s Heartland) | 2016-06-27 11:00 | 2016-06-27 17:00 | N | Y | install new spring and 62 relay | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 320p 91 (320p Keephills),320p T1 (320p Keephills) | 2016-06-27 13:00 | 2016-06-29 17:00 | N | Y | 138kV circuit breaker maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s T2 (42s Sarcee),906L (17s Benalto - 42s Sarcee),916L (42s Sarcee - 5s East Calgary),42s Sarcee 240kV South Bus | 2016-06-27 17:00 | 2016-07-18 12:00 | N | Y | 916L remains out of service due to jumpers opened on 42s North 240kV Bus,replace strain insulators, open jumpers on 240 kV South Bus to create open point 'D' | Line, Bus, Transformer, Shunts |  |  | 240 kV, Overload, Contingency Requires Mitigation
EPCOR | Meadowlark T3 (Meadowlark) | 2016-06-28 07:00 | 2016-06-28 17:00 | N | N | oil leak repair | Transformer |  |  | For Information Only
REDDEER | 247s T2 (247s Piper Creek) | 2016-06-28 07:30 | 2016-06-29 17:00 | N | N | transformer oil containment repair work | Transformer |  |  | For Information Only
ALTALINK | 933L (132s Ware Junction - 801s Anderson) | 2016-06-28 08:00 | 2016-06-30 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 786s SVC (786s High Level),786s 703T (786s High Level) | 2016-06-28 08:30 | 2016-06-29 15:30 | N | Y | 401 partial PM & testing, repair 703T leaking from top flange | Shunts, Transformer |  | 401 Partial PM & Testing, Repair 703T Leaking from top flange. / SVC Offline for the duration of the work. | For Information Only
ATCO | 7L133 (786s High Level - 828s Sulphur Point),786s 701T (786s High Level) | 2016-06-28 08:30 | 2016-06-29 15:30 | N | N | complete 701TCS maintenance and testing | Line, Transformer |  | Complete 701TCS Maintenance and testing. SVC also out same time ( 2-37159) so 7L133 will be open ended as well. / 25kv load fed from 702T for duration of the work. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 191s T2 (191s N.W.Cardiff) | 2016-06-28 09:30 | 2016-06-28 17:30 | N | N | Doble and bushing leak investigation/repair | Transformer |  |  | For Information Only
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan) | 2016-06-28 10:00 | 2016-06-29 17:00 | N | N | component replacements and structure repair | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 37 (39s Bickerdike) | 2016-06-28 10:00 | 2016-06-28 11:00 | N | N | topping up with gas | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 394s T1 (394s Empress),394s 4 (394s Empress) | 2016-06-28 13:30 | 2016-06-28 15:30 | N | N | repair solder on control module | Transformer, Switch |  |  | For Information Only
EPCOR | 511s Victoria T1 (511s Victoria) | 2016-06-29 07:00 | 2016-07-25 17:00 | N | N | isolation for hydovacing | Transformer
ATCO | 827s 701T (827s Cranberry Lake) | 2016-06-29 08:00 | 2016-06-30 14:30 | N | N | major testing on 701T and 501VR | Transformer |  | Major Testing on 701T and 501VR, Equipment is for emergency only - no load being carried | For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2016-06-29 08:00 | 2016-06-30 16:00 | N | N | leak repair by the Colt Group | Transformer
ENMAX | 38.1C (ENMAX 38),ENMAX 38 CS138-38.CAP (ENMAX 38) | 2016-06-29 08:00 | 2016-06-30 16:00 | N | N | weeds need to be removed from area | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 37s T3 (37s North Calder) | 2016-06-29 09:00 | 2016-06-29 17:00 | N | N | replace broken insulators on s581 and perform maintenance on 37s14 | Transformer
ALTALINK | 38s 7452 (38s East Edmonton) | 2016-06-29 09:00 | 2016-06-29 14:30 | N | Y | rebuilding trip dashpot | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 37s T3 (37s North Calder) | 2016-06-29 09:00 | 2016-06-29 17:00 | N | N | to offload 25R to facilitate AltaLink work | Transformer
EPCOR | Poundmaker 2404 (Poundmaker) | 2016-06-30 07:00 | 2016-06-30 17:00 | N | Y | repair auxilary contact | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 786s 702T (786s High Level) | 2016-06-30 08:30 | 2016-06-30 16:30 | N | N | complete 702T testing and maintenance | Transformer |  | Complete 702T testing and maintenance. / 25kV Load fed from 701T for the duration of the work | For Information Only
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2016-06-30 09:00 | 2016-06-30 12:00 | N | N | urgent work to replace damaged pole | Line |  |  | Creates Radial Feeds
ENMAX | 2.82L (ENMAX 2 - ENMAX 5),B138-2.82 (ENMAX 5) | 2016-07-02 08:00 | 2016-07-03 16:00 | N | N | HV Breaker inspection HLR | Line, Circuit Breaker |  |  | Overload
EPCOR | Woodcroft W723 (Woodcroft) | 2016-07-04 07:00 | 2016-07-10 17:00 | N | N | cutover of new BF/Sync check relay to W723 breaker | Circuit Breaker |  |  | For Information Only
EPCOR | Rossdale RR729 (Rossdale) | 2016-07-04 07:00 | 2016-07-04 17:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
REDDEER | 217s T1 (217s North Red Deer) | 2016-07-04 07:30 | 2016-07-05 17:00 | N | N | transformer bushing replacement | Transformer |  |  | For Information Only
ENMAX | 7.1TR (ENMAX 7) | 2016-07-04 08:00 | 2016-07-05 16:00 | N | N | LTC maintenance | Transformer
ALTALINK | 58s T1 (58s Edson) | 2016-07-04 08:00 | 2016-07-08 17:00 | N | N | replacing 58s377E with new V/B and urgent repair breaker replacement | Transformer |  |  | For Information Only
ALTALINK | 434L (65s High River - 237s Foothills),65s 434(65s Highriver) | 2016-07-04 09:00 | 2016-07-04 17:00 | N | N | replace breaker tank heaters | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 732s 901 (732s Mitsue) | 2016-07-04 09:30 | 2016-07-06 14:00 | N | Y | partial PM | Circuit Breaker |  | Partial PM on Bkr 901, 240kV ring will be open | 240 kV, Contingency Requires Mitigation
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan) | 2016-07-04 10:00 | 2016-07-07 17:00 | N | N | component replacements | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
TRANSALTA, ALTALINK | 59s T1 (59s Peigan),616L (59s Peigan - 616AL tap),59s Peigan 138kV Bus | 2016-07-04 11:00 | 2016-07-10 17:00 | N | Y | transformer bushing replacement | Transformer, Line, Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 1057L (89s Ellerslie - 657s Summerside) | 2016-07-04 12:00 | 2016-07-07 16:00 | N | Y | RTU replacement project | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 394s T2 (394s Empress) | 2016-07-04 12:00 | 2016-07-05 14:00 | N | N | install bird covers | Transformer |  |  | For Information Only
EPCOR | Rossdale R724 (Rossdale) | 2016-07-05 07:00 | 2016-07-05 17:00 | N | N | Doble | Circuit Breaker |  |  | For Information Only
EPCOR | 330P 12TC2 (330p Genesee),330p Genesee 500kV Bus 2 | 2016-07-05 07:00 | 2016-07-15 17:00 | N | Y | protection upgrade | Bus, Transformer |  |  | Contingency Requires Mitigation, 500 kV
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2016-07-05 08:00 | 2016-07-07 16:00 | N | N | HV breaker maintenance 14CS138-14.2CAP. capacitor bank maintenance | Shunts |  |  | For Information Only
ALTALINK | 743L (527s Coal Valley - 743L1A) | 2016-07-05 08:00 | 2016-07-07 17:00 | N | N | component insulator changes | Line |  |  | Firm Load Loss
ENMAX | 27.1TR (ENMAX 27) | 2016-07-05 08:00 | 2016-07-06 16:00 | N | N | equipment outage in order to test relays | Transformer
ALTALINK | 934L (132s Ware Junction - 801s Anderson) | 2016-07-05 08:00 | 2016-07-07 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 13s Deerland 138kV Bus 1 | 2016-07-05 09:00 | 2016-07-07 17:00 | N | N | replace 13s CVT17 | Bus |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 511s SS1 (511s Crossings),511s SS2 (511s Crossings) | 2016-07-05 10:00 | 2016-07-05 11:00 | N | Y | commission elevator | Terminal Equipment |  |  | For Information Only
ALTALINK | 310p 2352 (310p Sundance) | 2016-07-05 10:00 | 2016-07-05 12:00 | N | Y | CT repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 724s 601 (724s Hines Creek) | 2016-07-05 10:00 | 2016-07-06 16:00 | N | N | breaker 601 complete PM & testing | Circuit Breaker |  | Breaker 601 Complete PM & Testing, GSW 6L37D2 to be closed to feed Eureka Rv | Pre-Condition
BLACKSPRING | 485S Black Springs | 2016-07-06 06:00 | 2016-07-07 19:00 | N | N | annual maintenance | Station |  |  | For Information Only
ALTALINK | 1042L (485s Blacksprings - 554s Travers),554s Travers 240 kV Bus 1,554s1042 (554s Travers) | 2016-07-06 06:00 | 2016-07-07 19:00 | N | Y | customer request for station maintenance | Bus, Switch, Line |  |  | 240 kV, Restricts Generation, For Information Only
ATCO | 7L56 (809s Louise Creek - 738s Virginia Hills) | 2016-07-06 08:00 | 2016-07-06 16:00 | N | Y | high load move | Line |  | High load move, 738s and 725s radial fed from 813s | Overload, Contingency Requires Mitigation
ENMAX | 7.2TR (ENMAX 7) | 2016-07-06 08:00 | 2016-07-07 16:00 | N | N | LTC maintenance | Transformer
CNRL, ATCO | 842s 75-TR-4701 (842s Horizon Upgrading),838s 75-BC-1911 (838s Horizon Mining),838s 75-BC-1912 (838s Horizon Mining),842s 75-1902 (842s Horizon Upgrading),842s 75-1903 (842s Horizon Upgrading),75PHL-902 (838s Horizon Mining - 849s Joslyn Creek),75PHL-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2016-07-07 08:00 | 2016-07-09 15:00 | N | Y | testing of voltage transformers | Line, Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2016-07-07 08:00 | 2016-07-08 16:00 | N | N | equipment outage in order to test relays | Transformer
CNRL | 842s 75-TR-4701 (842s Horizon Upgrading) | 2016-07-07 08:00 | 2016-08-03 09:40 | N | Y | maintenance | Transformer |  |  | 240 kV, For Information Only
CNRL | 75-TR-8701 (842s Horizon Upgrading) | 2016-07-07 08:00 | 2016-08-03 09:40 | N | Y | maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 276s 652 (276s Un Carb Prentiss),276s C1 (276s Prentiss) | 2016-07-07 08:00 | 2016-07-07 17:00 | N | N | replace damaged tank heater | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2016-07-07 08:00 | 2016-07-07 16:00 | N | N | repair SW 65 at 34 sub | Line, Transformer |  |  | Creates Radial Feeds
ATCO | 75PHL-902 (838s Horizon Mining - 849s Joslyn Creek) | 2016-07-07 08:00 | 2016-07-10 17:00 | N | Y | make settings changes and testing | Line |  | the following plans to make settings changes and testing July 7th -10th 75-PLH-902 will be open ended for equipment testing. | 240 kV, For Information Only
CNRL | 75-TR-5701 (842s Horizon Upgrading) | 2016-07-07 08:00 | 2016-08-03 09:40 | N | Y | maintenance | Transformer |  |  | 240 kV, For Information Only
CNRL | 75-TR-7701 (842s Horizon Upgrading) | 2016-07-07 08:00 | 2016-08-03 09:40 | N | Y | maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2016-07-07 09:00 | 2016-07-07 13:00 | N | N | oil leak investigation | Switch |  |  | Restricts Generation
ALTALINK | 215L (38s East Edmonton - 286s Yasa),38s 215N (38s East Edmonton) | 2016-07-07 09:00 | 2016-07-07 17:00 | N | N | repair CT leak | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250P T40 (250P Bighorn Plant) | 2016-07-08 06:00 | 2016-08-04 08:00 | N | N | breaker replacement 250p32, TX protection replacement - T40 | Transformer |  |  | For Information Only
EPCOR, ALTALINK | 1056L (89s Ellerslie - 629s Argyll Transfer Station),240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2016-07-08 07:00 | 2016-08-02 17:00 | N | Y | tower refurbishment / degassing | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 58s Edson RTU/SCADA | 2016-07-08 08:00 | 2016-07-08 17:00 | N | N | download new RTU configuration | Terminal Equipment |  | On July 8, 2016 there will be a couple of supervisory outages to update the RTUs configuration for the breaker replacement of 58s377E. On July 8, 2016 the the Supervisory Control Switch will be placed in "Local" so the points and controls can be Tested. RTU can be put in remote on a minutes notice. | Affects Visibility
ALTALINK | 510s SS3 (510s Sunnybrook),510s SS4 (510s Sunnybrook) | 2016-07-09 10:00 | 2016-07-09 11:00 | N | N | commission elevator | Terminal Equipment |  |  | For Information Only
EPCOR | 72RW3 Offloaded and Isolated @ Woodcroft S/S | 2016-07-11 07:00 | 2016-07-17 17:00 | N | N | cutover of new BF/Sync check relay to W725 breaker | Terminal Equipment |  |  | For Information Only
ALTALINK, EPCOR | 803s L2401 (803s Lambton),803s L2404 (803s Lambton),1059L (38s East Edmonton - 803s Lambton) | 2016-07-11 07:00 | 2016-07-11 17:00 | N | Y | doble (EPCOR) | Line, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2407 (805s Jasper) | 2016-07-11 07:00 | 2016-07-15 17:00 | N | Y | breaker maintenance @ doble | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 21.1C (ENMAX 21) | 2016-07-11 08:00 | 2016-07-12 16:00 | N | N | HV breaker inspection, 21CAP maintenance | Shunts |  |  | For Information Only
ENMAX | 26.2TR (ENMAX 26) | 2016-07-11 08:00 | 2016-07-15 16:00 | N | N | doble Tx | Transformer |  |  | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2016-07-11 08:00 | 2016-07-15 16:00 | N | N | repair LTC | Transformer |  |  | For Information Only
ATCO | 6L99 (727s Kinuso - 745s Slave Lake),727s 603 (727s Kinuso) | 2016-07-11 09:00 | 2016-07-11 14:00 | N | N | bkr 603 partial breaker maintenance | Line, Circuit Breaker |  | BKR 603 Partial Breaker Maintenance | Firm Load Loss, Creates Radial Feeds
BCH | 2L293 (Selkirk - Nelway) | 2016-07-11 09:00 | 2016-07-15 17:00 | N | Y | markerball installations - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC, For Information Only
ATCO | 863s 902T (863s Paintearth) | 2016-07-11 09:00 | 2016-07-15 17:00 | N | Y | 863S - 902T testing and leak repair | Transformer |  | 863S - 902T Testing and Leak Repair 901T is in service and will carry the load for the duration of the outage | For Information Only
ALTALINK | 434s T3 (434s East Stony Plain) | 2016-07-11 10:00 | 2016-07-13 17:30 | N | N | leak repair & wash | Transformer |  |  | For Information Only
ALTALINK | 727L (678s Okotoks - 142s Magcan - 65s High River) | 2016-07-11 10:00 | 2016-07-11 17:00 | N | N | 138kV airbrake replacements | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan) | 2016-07-11 10:00 | 2016-08-16 17:00 | N | N | component replacements | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 252 (310p Sundance) | 2016-07-11 10:30 | 2016-07-14 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 74s 2252 (74s Janet) | 2016-07-11 11:00 | 2016-07-14 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 180s T2 (180s Cope Creek) | 2016-07-11 13:00 | 2016-07-12 17:00 | N | N | repair oil leaks | Transformer |  |  | For Information Only
ALTALINK | 718L (250p Bighorn Plant - 263s Strachan),263s 718W (263s Strachan),250p Bighorn 138kV Bus | 2016-07-12 06:00 | 2016-07-12 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line, Bus |  |  | Restricts Generation
EPCOR | 524S Fiberglas | 2016-07-12 07:00 | 2016-07-12 11:00 | N | N | customer outage | Station |  |  | For Information Only
ALTALINK | 950L (132s Ware Junction - 801s Anderson) | 2016-07-12 08:00 | 2016-07-14 16:00 | N | Y | SCADA upgrade project | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 2075s SVC1 (2075s Newell) | 2016-07-12 08:00 | 2016-07-14 17:00 | N | Y | 504A mechanical repair | Shunts |  | 504A Mechanical Repair, SVC2 will remain in service while SVC1 is out of service. No restrictions to the DC or AC system while it is out of service. | For Information Only
ATCO | 840S McNeill Station | 2016-07-12 08:00 | 2016-07-15 17:00 | N | Y | emergency work to repair Glycol pump | Station |  | 840S McNeill - McNeill to Standby - Station Service work Transfer will be unavailable for the duration Remove old station service wiring for new installation of station service McNeill can be restored in 2 hours | Limits ATC
Syncrude | Aurora T3 (Aurora) | 2016-07-12 09:00 | 2016-07-24 16:30 | N | N | maintenance | Transformer |  |  | For Information Only
TRANSALTA | 59s 14 (59s Peigan) | 2016-07-12 10:00 | 2016-07-22 17:00 | N | N | remove 59s14 switch, install old 59s7 switch during planned 616L outage | Switch |  |  | For Information Only
ALTALINK | 157s C1 (157s Lac La Biche) | 2016-07-12 10:00 | 2016-07-12 11:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 405s C1 (405s Waupisoo) | 2016-07-12 12:30 | 2016-07-12 13:30 | N | N | weed spraying | Shunts |  |  | For Information Only
ATCO | 6L09 (763s Hanna - 776s Richdale) | 2016-07-12 13:00 | 2016-07-12 15:30 | N | N | line repairs | Line |  | The wire we need to re-sag is at NE22-30-13-4 it is between Hanna Sub 763S & Gang Switch 6L09D2, 772s, 776s and Express Pipeline will be radial fed from 767s Oyen | Firm Load Loss, Creates Radial Feeds
ALTALINK | 56s C1 (56s Boyle) | 2016-07-12 14:30 | 2016-07-12 15:30 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 43 (159s Colinton) | 2016-07-13 07:00 | 2016-07-13 17:00 | N | N | isolate 152 to remove existing bus differential circuit. rename 159s46 to 159s295 & 159s43 to 159s223 | Circuit Breaker, Line |  |  | Contingency Requires Mitigation
ALTALINK | 325s T2 (325s Leduc) | 2016-07-13 08:00 | 2016-07-13 17:30 | N | N | test energize new 25kV ABB switchgear spare breaker (325s1052) | Transformer |  |  | For Information Only
ALTALINK | 250P Bighorn Plant | 2016-07-13 08:00 | 2016-07-24 16:00 | N | N | stator replacement commissioning test, scheduled in-service-date: Jul 23 | Station
ALTALINK | 716L/80L (40s Wetaskiwin - 958s West Lacombe) | 2016-07-13 08:30 | 2016-07-13 11:00 | N | N | high load move for McConnell building movers | Line |  |  | Contingency Requires Mitigation
ALTALINK | 283s C1 (283s Violet Grove) | 2016-07-13 09:00 | 2016-07-13 10:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 58s C1 (58s Edson) | 2016-07-13 12:30 | 2016-07-13 13:30 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 305s C1 (305s Acheson) | 2016-07-13 15:30 | 2016-07-13 16:30 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 746s T1 (746s Sherwood Park) | 2016-07-14 09:00 | 2016-07-15 17:00 | N | N | repair TC/MT leak, TC maintenance, TC contacts replacement, drain valve replacement | Transformer |  |  | For Information Only
ALTALINK | 54s C1 (54s Fort Saskatchewan) | 2016-07-14 09:00 | 2016-07-14 10:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 71s C1 (71s Lamoureux) | 2016-07-14 10:30 | 2016-07-14 11:30 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 71s C2 (71s Lamoureux) | 2016-07-14 11:30 | 2016-07-14 12:30 | N | N | weed spraying | Shunts |  |  | Pre-Condition
ALTALINK | 38s C1 (38s East Edmonton) | 2016-07-14 14:00 | 2016-07-14 15:00 | N | N | weed spraying | Shunts |  |  | For Information Only
ALTALINK | 38s C2 (38s East Edmonton) | 2016-07-14 15:00 | 2016-07-14 16:00 | N | N | weed spraying | Shunts |  |  | Pre-Condition
ALTALINK | 56s T2 (56s Boyle) | 2016-07-15 10:00 | 2016-07-15 12:00 | N | N | A protection relay | Transformer |  |  | For Information Only
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24) | 2016-07-16 08:00 | 2016-07-16 16:00 | N | N | doble test HV breaker (24B138-24.82), doble PT | Line, Transformer |  |  | For Information Only
ENMAX | 13.3TR (ENMAX 13) | 2016-07-16 08:00 | 2016-07-16 12:00 | N | N | remove trojan oil processor | Transformer
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2016-07-16 08:30 | 2016-07-17 17:00 | N | N | repair TC/MT leak | Transformer
ENMAX | 13.2TR (ENMAX 13) | 2016-07-16 12:00 | 2016-07-16 16:00 | N | N | install trojan oil processor | Transformer
ATCO | 9L58 (888s Dover - 848s Ruth Lake),848s 907 (848s Ruth Lake),848s 908 (848s Ruth Lake),888s 908 (888s Dover),888s 909 (888s Dover) | 2016-07-18 07:00 | 2016-07-29 17:00 | N | Y | upgrade 21 A & 21B/9L58 protection on both ends | Circuit Breaker, Line |  | Upgrade 21 A & 21B/9L58 protection on both ends, 240kV partial bus outage at both ends, 848s is a breaker and a third scheme, 888s is a breaker and a half scheme. | 240 kV, Contingency Requires Mitigation
ATCO | 715s 702T (715s Leming Lake) | 2016-07-18 07:00 | 2016-08-12 18:00 | N | N | 702T maintenance and protection upgrade | Transformer |  | 702T maintenance and protection upgrade, 25kV load will be transferred to 701T and 703T. | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2016-07-18 08:00 | 2016-07-18 16:00 | N | N | measurements needed for ladder installation | Transformer |  |  | For Information Only
ENMAX | 16.2TR (ENMAX 16) | 2016-07-18 08:00 | 2016-07-21 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAXEC | 383S Kettles Hill Windfarm | 2016-07-18 08:00 | 2016-07-22 16:00 | N | Y | substation maintenance | Station |  |  | Restricts Generation
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2016-07-18 08:00 | 2016-07-29 16:00 | N | Y | line protection upgrade. replace 138kV CTs, 13s UVLS. 3s & 13s 138KV bus differential protection | Line |  |  | Pre-Condition, Overload, Creates Radial Feeds
ENMAX | 8.2TR (ENMAX 8) | 2016-07-18 08:00 | 2016-07-22 16:00 | N | N | doble Tx | Transformer |  |  | For Information Only
TRANSALTA, ALTALINK | 59s T1 (59s Peigan),59s 616 (59s Peigan),616L (59s Peigan - 103s Goose Lake) | 2016-07-18 08:00 | 2016-07-22 16:00 | N | Y | 59s7 replacement | Circuit Breaker, Line, Transformer |  |  | For Information Only
ALTALINK | 38s T2 (38s East Edmonton) | 2016-07-18 08:00 | 2016-07-19 17:00 | N | N | install screw pile for riser structure in close proximity to T2 | Transformer |  |  | For Information Only
ATCO | 809s 503R (809s Louise Creek),809s 504R (809s Louise Creek),809s 901T (809s Louise Creek) | 2016-07-18 09:30 | 2016-07-20 16:00 | N | Y | transformer class1 major testing and maintenance on 901T, 701 Breaker | Transformer, Shunts |  | TRANSFORMER CLASS1 MAJOR TESTING, 901T, 503R and 504R also OOS for the Duration. Maint on 901T, 701 Breaker All Load being fed from 902T, Station service fed from Alt supply. | For Information Only
ALTALINK | 17s T2 (17s Benalto) | 2016-07-18 10:00 | 2016-07-28 17:00 | N | Y | replace 138/240kV bushings | Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 749s 702T (749s Flyingshot Lake) | 2016-07-18 10:00 | 2016-07-19 16:00 | N | N | test transformer | Transformer |  | Test transformer | For Information Only
ALTALINK | 348s T2 (348s Marlboro) | 2016-07-18 10:00 | 2016-07-19 16:00 | N | N | TransCanada request to remove T2 from service | Transformer |  |  | For Information Only
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2016-07-18 10:30 | 2016-07-19 17:30 | N | N | repair TC/MT leak, transformer doble | Transformer |  |  | For Information Only
ALTALINK | 773L (127s Bruderheim - 308s Albchem Beaverhill Creek),308s 773E (308s Albchem Beaverhill Creek) | 2016-07-18 11:00 | 2016-07-18 17:00 | N | N | rebuild dashpot | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 256s C1 (256s Harmattan),256s 53 (256s Harmattan) | 2016-07-18 11:00 | 2016-07-18 12:00 | N | N | de-energize for cap bank weed spraying | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 946L (89s Ellerslie - 38s East Edmonton) | 2016-07-18 12:00 | 2016-07-21 16:00 | N | Y | RTU replacement project | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s T1 (42s Sarcee),916L (42s Sarcee - 5s East Calgary),928L (17s Benalto - 42s Sarcee),42s Sarcee 240kV North Bus | 2016-07-18 13:00 | 2016-07-29 08:00 | N | Y | insulator replacement and close Open Point B and C | Line, Bus, Shunts, Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 217s C1 (217s North Red Deer),217s 652 (217s North Red Deer) | 2016-07-18 13:30 | 2016-07-18 14:30 | N | N | de-energize for weed spraying | Switch, Shunts |  |  | For Information Only
ALTALINK, AESO-SC | 377s 473C102 (377s Hardisty),473c102 (Mobile Cap) | 2016-07-18 16:00 | 2016-07-18 17:00 | N | N | de-energize for weed spraying | Circuit Breaker, Shunts |  |  | For Information Only
TRANSALTA | Transalta Wind Control Centre | 2016-07-18 17:00 | 2016-07-18 20:00 | N | N | communication outage | SCInternal |  |  | For Information Only
ALTALINK, ATCO | 950L (132s Ware Junction - 801s Anderson),9L950 (132s Ware Junction - 801s Anderson) | 2016-07-18 21:34 | 2016-07-24 11:37 | N | N | forced | Line |  |  | 240 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2016-07-19 07:50 | 2016-07-21 18:00 | N | Y | urgent repairs | Line |  |  | 240 kV, Limits ATC
ALTALINK | 1109L (ENMAX 65 - ENMAX 25) | 2016-07-19 08:00 | 2016-07-19 16:00 | N | Y | HV SW/MD maintenance 25MD240-1109 | Line |  |  | 240 kV, For Information Only
ALTALINK | 508s T1 (508s Lakesend) | 2016-07-19 08:00 | 2016-07-19 20:00 | N | N | 508s T1(TX18767) GOI | Transformer |  | TransCanada request | Firm Load Loss
ALTALINK | 341s T1 (341s Sand Hills Sub) | 2016-07-19 08:00 | 2016-07-19 17:00 | N | N | replace H3 bushing | Transformer |  |  | For Information Only
ALTALINK | 364s 3052 (364s Whitecourt Industrial) | 2016-07-19 09:00 | 2016-07-19 17:00 | N | N | replace faulty tank heaters | Circuit Breaker |  | AltaLink 364s3052 - GOI. Replace faulty tank heaters | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 741S 504,741S 504C | 2016-07-19 15:00 | 2016-07-20 15:00 | N | N | 504 breaker complete maintenance, 504C not available during this outage | Terminal Equipment |  | 504 Breaker complete maintenance, 504C Not available during this outage. | For Information Only
ALTALINK | 348s T1 (348s Marlboro) | 2016-07-19 16:00 | 2016-07-20 16:00 | N | N | 348s T1(TX18693) - GOI | Transformer |  | TransCanada request to remove T1 from service | For Information Only
CENOVUS | 539S Sunday Creek | 2016-07-20 01:00 | 2016-07-20 06:00 | N | N | planned network outage | Station |  |  | For Information Only
EPCOR | 665s D2402 (665s Dome) | 2016-07-20 07:00 | 2016-07-22 17:00 | N | Y | emergency duct line repair | Circuit Breaker |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
TRANSALTA | 59s 852 (59s Peigan) | 2016-07-20 08:00 | 2016-07-21 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 798L (364s Whitecourt Industrial - 77s Sagitawah),364s 798 (364s Whitecourt Industrial) | 2016-07-20 08:00 | 2016-07-20 17:00 | N | N | replace faulty tank heaters | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 38s T3 (38s East Edmonton) | 2016-07-20 08:00 | 2016-07-21 17:00 | N | N | install screw pile for riser structure in close proximity to T3 | Transformer |  |  | For Information Only
ATCO | 7L56 (809s Louise Creek - 738s Virginia Hills) | 2016-07-20 08:00 | 2016-07-20 16:00 | N | N | high load move, 738s and 725s radial fed from 813s | Line |  | High load move, 738s and 725s radial fed from 813s | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 75PHL-901 (838s Horizon Mining - 849s Joslyn Creek) | 2016-07-20 08:00 | 2016-07-23 18:00 | N | Y | open ended at 838s for testing of B protection | Line | 75-PLH-901 Open Ended at 838s | Testing of B protection. | 240 kV, Creates Radial Feeds
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),ENMAX 25 240kV West Bus | 2016-07-20 09:00 | 2016-08-24 17:00 | N | Y | L to J: 1003L cable fault - replacement | Line, Bus |  |  | 240 kV, Pre-Condition
ALTALINK | PMU | 2016-07-20 09:00 | 2016-07-20 13:00 | N | N | 163s PMU-software upgrade at 9282R Buffalo Hill 7750 MPLS router | Terminal Equipment |  |  | For Information Only
ATCO | 722s 701T (722s Crystal Lake) | 2016-07-21 08:00 | 2016-07-25 16:00 | N | N | CT ratio changes on the primary side. | Transformer |  | 701T reqd OOS fo CT ratio changes on the primary side, 701T load will be transferred onto 702T, CSP 2-38005 will be done in conjunction with this GOI. | For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),364s 797 (364s Whitecourt Industrial) | 2016-07-21 10:00 | 2016-07-21 17:00 | N | N | replace faulty tank heaters | Circuit Breaker, Line |  |  | Over/Under Voltage, Creates Radial Feeds
REDDEER | 209s T1 (209s Timberlands),209s 768W (209s Timberlands),209s 464E (209s Timberlands) | 2016-07-22 07:30 | 2016-07-22 17:00 | N | N | urethane injection in duck bank to seal water seepage into control | Transformer, Circuit Breaker | SOKac = 800 MW |  | Pre-Condition
ATCO | 7L85 (803s Bullpound - 801s Anderson) | 2016-07-22 08:00 | 2016-07-22 17:00 | N | N | emergency repair to structure on 7L85 | Line |  |  | Creates Radial Feeds
ALTALINK | 434L (65s High River - 237s Foothills) | 2016-07-23 08:00 | 2016-07-27 18:00 | N | N | emergency install bird diverters | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX | ENMAX 13 SW89 (ENMAX 13) | 2016-07-23 08:00 | 2016-07-23 16:00 | N | N | wiring changes for new 3.84L protection | Switch |  |  | Pre-Condition
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2016-07-23 08:00 | 2016-07-23 16:00 | N | N | road work on 9th Ave. | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.83L (ENMAX 43 - ENMAX 9),ENMAX 9 B138-9.83 (ENMAX 9),ENMAX 43 B138-9.83 (ENMAX 43) | 2016-07-24 08:00 | 2016-07-24 16:00 | N | N | breaker inspection | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ALTALINK | 397s T1 (397s Benbow) | 2016-07-25 07:00 | 2016-09-29 08:00 | N | N | replace 138/25kV T1 and VR1 and upgrade to 42 MVA 138/25kV LTC transformer | Transformer |  |  | For Information Only
EPCOR | 803s L2403 (803s Lambton) | 2016-07-25 07:00 | 2016-07-27 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354S Summerview | 2016-07-25 07:30 | 2016-07-29 08:00 | N | N | 34kV switching | Station |  |  | For Information Only
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2016-07-25 08:00 | 2016-07-26 17:00 | N | Y | adjust risers | Transformer, Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 41.2TR (ENMAX 41) | 2016-07-25 08:00 | 2016-07-29 16:00 | N | N | doble | Transformer
ATCO | 7L32 (862s South Bezanson - 813s Little Smoky) | 2016-07-25 08:00 | 2016-07-28 17:00 | N | Y | 7L32 replace rotten crossarms | Line |  | 7L32 replace rotten crossarms | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 199s T1 (199s East Airdrie) | 2016-07-25 12:00 | 2016-07-25 17:00 | N | N | voltage regulator maintenance | Transformer
ALTALINK | 632PS (632s Russell) | 2016-07-25 12:00 | 2016-07-25 17:00 | N | Y | phase shifter doble test | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK, EPCOR | 908AL (52S East Industrial - 908L Tap),908L (89s Ellerslie - 38s East Edmonton) | 2016-07-25 12:00 | 2016-07-28 16:00 | N | Y | RTU replacement project | Line |  |  | 240 kV, For Information Only
ALTALINK | 89s 1752 (89s Ellerslie) | 2016-07-25 13:00 | 2016-07-27 17:30 | N | Y | replacing accessory port to repair leak | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 285s T2 (285s East Camrose) | 2016-07-25 13:00 | 2016-07-26 17:00 | N | N | doble test and replace the 138kV bushings | Transformer |  | Altalink:The latest test results have raised alarms and our Operational Engineering Group has asked that this be taken care of as soon as possible (Urgent Request) | For Information Only
VISIONREQ | 354S Summerview | 2016-07-25 16:30 | 2016-07-29 17:00 | N | N | 34kV switching | Station |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar),987s T4 (987s Clover Bar) | 2016-07-26 07:00 | 2016-07-27 17:00 | N | Y | CDS1 repair | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 103s 1252 (103s Goose Lake) | 2016-07-26 08:00 | 2016-07-27 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 681s T1 (681s Bannerman) | 2016-07-26 08:00 | 2016-07-27 17:00 | N | Y | retest paralleling scheme | Transformer |  | Retest paralleling scheme, transformers will be switch out of service 1 at a time. The transformers will also be switched into service 1 at time. (No line outages). | 240 kV, Pre-Condition
ALTALINK | 391s T1 (391s Balzac),611L (391S Balzac - 186s Dry Creek) | 2016-07-26 08:00 | 2016-07-27 17:00 | N | N | replace T1 bushings and repair 391s16 switch | Line, Transformer |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 722s 702T (722s Crystal Lake) | 2016-07-26 08:00 | 2016-07-30 16:00 | N | N | CT ratio changes on the primary side | Transformer |  | 702T reqd OOS fo CT ratio changes on the primary side, CSP 2-38010 will be done in conjunction with this GOI. | For Information Only
ENMAX | 9.3TR (ENMAX 9) | 2016-07-26 08:00 | 2016-07-26 16:00 | N | N | repair a major oil leak | Transformer |  |  | For Information Only
SUNCOR | 139S Hillridge | 2016-07-26 08:00 | 2016-07-26 18:00 | N | N | to perform maintenance and testing of protection system | Station |  | To perform maintenance and testing of Hillridge Substation 139Ss Protection Systems. CCWF will be out of service during this Operation | For Information Only
ALTALINK, ATCO | 1047L (650s Hansman Lake - 574s Nilrem),9L953 (574s Nilrem - 755s Cordel),953L (574s Nilrem - 755s Cordel) | 2016-07-26 08:00 | 2016-07-29 17:00 | N | N | emergency damper replacement | Line |  | 953L/9L953: 574s953, A755s9L953D1 1047L: 574s1047, 650s1047 | 240 kV, Pre-Condition
ALTALINK | 867S Sundance Blow-Down | 2016-07-26 08:30 | 2016-07-26 17:00 | N | N | repair station grounding / bonding deficiencies | Station |  |  | Pre-Condition, Firm Load Loss
ALTALINK | 681s T2 (681s Bannerman) | 2016-07-26 08:30 | 2016-07-27 17:30 | N | Y | retest paralleling scheme | Transformer |  | Retest paralleling scheme, transformers will be switch out of service 1 at a time. The transformers will also be switched into service 1 at time. (No line outages). | 240 kV, Pre-Condition
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2016-07-26 10:00 | 2016-07-26 17:00 | N | N | relocate pole for road move | Line |  | Relocate pole for road move | Firm Load Loss, Creates Radial Feeds
EPCOR | 72NW15 (Namao - Woodcroft),Woodcroft W723 (Woodcroft) | 2016-07-27 07:00 | 2016-07-27 17:00 | N | N | doble | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 513s T1 (513s Range Lundbreck) | 2016-07-28 08:00 | 2016-07-28 17:00 | N | N | replace guide pins on switch | Transformer |  | AltaLink 513s1 - GOI - Replace guide pins on switch | For Information Only
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2016-07-28 08:00 | 2016-07-28 09:00 | N | N | de-energize for cap bank weed spraying | Circuit Breaker, Shunts |  | AltaLink 74s56 (C1) - GOI - De-energize for cap bank weed spraying. | Pre-Condition
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33),ENMAX 33 B138-33.84 (ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2016-07-28 08:00 | 2016-07-29 16:00 | N | N | breaker inspection and SF6 gas sample,HLR timing test,inspections and tests | Line, Circuit Breaker, Transformer |  | 33.84L. 33B138-33.84. 43B138-33.84. 33.2TR. 33PT138-Z31 - HV Breaker Inspection (33B138-33.84), HLR timing test on 43B138-33.84. SF6 Gas Sample (33B138-33.84), 33PT138-Z31 Doble Test PT. Paint Potheads at 43 sub. | Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21),138-21.CAP (ENMAX 21) | 2016-07-28 08:00 | 2016-07-28 16:00 | N | Y | install PT for harmonic monitoring | Line, Transformer, Circuit Breaker |  | 21s. 50L. 21.2TR. 21CAP - Install PT for Harmonic Monitoring. Special return switching instructions required for PT energization. | Pre-Condition
ALTALINK | 953s T2 (953s Lake Louise) | 2016-07-28 08:30 | 2016-07-28 17:00 | N | N | regulator repairs | Transformer
ALTALINK | 74s C2 (74s Janet),74s 54 (74s Janet) | 2016-07-28 09:00 | 2016-07-28 10:00 | N | N | de-energize for cap bank weed spraying | Circuit Breaker, Shunts |  | AltaLink 74s54 (C2) - GOI - De-energize for cap bank weed spraying. | Pre-Condition
ALTALINK | 89s 352 (89s Ellerslie) | 2016-07-28 09:00 | 2016-07-28 14:00 | N | Y | rebuilding trip dashpot | Circuit Breaker |  | AltaLink 89s352 - GOI - Rebuilding trip dashpot. | 240 kV
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2016-07-28 10:00 | 2016-07-28 11:00 | N | Y | de-energize for cap bank weed spraying | Circuit Breaker, Shunts |  | AltaLink 74s102 (C3) - De-energize for cap bank weed spraying. | 240 kV, Pre-Condition
ALTALINK | 74s C4 (74s Janet),74s 103 (74s Janet) | 2016-07-28 11:00 | 2016-07-28 12:00 | N | Y | de-energize for cap bank weed spraying | Circuit Breaker, Shunts |  | AltaLink 74s103 (C4) - De-energize for cap bank weed spraying. | 240 kV, Pre-Condition
EPCOR | 511s Victoria T2 (511s Victoria) | 2016-07-29 07:00 | 2016-08-09 17:00 | N | N | Isolation for hydovacing | Transformer |  |  | For Information Only
ENMAX | 5.7TR (ENMAX 5) | 2016-07-29 08:00 | 2016-07-29 16:00 | N | N | site visit to investigate future replacement of 5B25-5.113. 5B25-5.7TR to be viewed for comparison | Transformer |  |  | For Information Only
ALTALINK | 42s C3 (42s Sarcee),42s T2 (42s Sarcee),906L (17s Benalto - 42s Sarcee),42s Sarcee 240kV South Bus | 2016-07-29 09:00 | 2016-07-29 16:00 | N | Y | close jumpers on 240 kV South bus to close Open Point 'D' | Line, Shunts, Bus, Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 987s T1 (987s Clover Bar),72CK12 (987s Clover Bar - Kennedale),987s CDS17 (987s Clover Bar),987s CDS19 (987s Clover Bar) | 2016-07-30 07:00 | 2016-07-30 23:59 | N | N | CDS17, CDS19 repair | Switch, Transformer, Line |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2016-07-30 08:00 | 2016-07-30 12:00 | N | N | commission DPAC 1, operate CAC & OAC | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2016-07-30 08:00 | 2016-07-31 16:00 | N | Y | breaker inspection | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO | 463L (370s North Lethbridge - 463L28) | 2016-07-30 09:30 | 2016-07-30 13:00 | N | N | 172L/463L emergency conductor repair | Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2016-07-30 12:00 | 2016-07-30 16:00 | N | N | commission DPAC 1 and operate CAC & OAC | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 950L (132s Ware Junction - 801s Anderson) | 2016-07-30 19:52 | 2016-08-06 15:41 | N | Y | forced outage; 10 structures down due to storm | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2016-08-01 08:00 | 2016-08-01 16:00 | N | N | hot spot repair on SW 97 | Line |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft),Rossdale RW727 (Rossdale) | 2016-08-02 07:00 | 2016-08-03 15:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
EPCOR | RossdaleT1 (Rossdale),Rossdale R721 (Rossdale),Rossdale RR723 (Rossdale) | 2016-08-02 07:00 | 2016-08-06 17:00 | N | N | installing new tap changer control relays | Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2016-08-02 07:00 | 2016-08-09 15:52 | N | N | line rebuild | Line |  |  | Pre-Condition, Creates Radial Feeds
SHELL | 847s 901 (847s Muskeg River),847s 902 (847s Muskeg River) | 2016-08-02 07:00 | 2016-08-29 17:30 | N | Y | replace optical CT's with 2 new conventional CT's | Circuit Breaker |  | Replace optical CT's with 2 new conventional CT's. Add PT secondary fused disconnect 902PTX2. Upgrade protection, 240kV ring will be open @ 847s. | 240 kV, Pre-Condition
VISIONREQ | 354S Summerview | 2016-08-02 07:30 | 2016-08-04 08:00 | N | N | 34kV switching | Station |  |  | For Information Only
ENMAX | 3.3TR (ENMAX 3) | 2016-08-02 08:00 | 2016-08-12 16:00 | N | N | install new LTC | Transformer |  |  | For Information Only
ATCO | 855s 701T (855s Hamburg) | 2016-08-02 08:00 | 2016-08-02 16:00 | N | N | complete 701T major testing and maintenance | Transformer |  | Complete 701T Major Testing and Maintenance The transformer PM will be completed as well as replacing damaged/missing bird mitigation hardware. 855S will be OOS for the duration of the work. | For Information Only
ENMAX | 21.1C (ENMAX 21) | 2016-08-02 08:00 | 2016-08-05 16:00 | N | N | HV breaker inspection, SS21 capacitor maintenance | Shunts |  |  | For Information Only
ALTALINK | 946L (89s Ellerslie - 38s East Edmonton) | 2016-08-02 08:00 | 2016-08-04 12:10 | N | Y | Telus co-locate work on tower structures | Line |  |  | 240 kV, For Information Only
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome),89s 1052 (89s Ellerslie),89s 1152 (89s Ellerslie),665s DDS13 (665s Dome) | 2016-08-02 08:00 | 2016-08-04 16:00 | N | Y | RTU replacement project | Line, Circuit Breaker, Switch |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BLACKSPRING | 485s DVAR1 (485s Blacksprings),485s DVAR2 (485s Blacksprings) | 2016-08-02 08:00 | 2016-08-04 17:00 | N | N | DSTATCOM system outage for corrective maintenance | Shunts, Not In Model |  |  | For Information Only
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2016-08-02 09:00 | 2016-08-16 17:00 | N | Y | insulator replacements and arcing horn installations | Line |  |  | Pre-Condition
ATCO | 7L73 (829s Boucher Creek - 800s Friedenstal),800s 702 (800s Friedenstal) | 2016-08-02 09:00 | 2016-08-02 16:00 | N | Y | complete partial PM on breaker 702, 7L73 open ended for the duration of the work | Circuit Breaker, Line |  | Complete Partial PM on Breaker 702, 7L73 open ended for the duration of the work | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2016-08-02 10:00 | 2016-08-02 13:00 | N | Y | data radio replacement | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 185s 152 (185s Bretville) | 2016-08-02 11:00 | 2016-08-04 18:00 | N | N | replace leaking rupture disk | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX, ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21),ENMAX 21 60S50 (ENMAX 21) | 2016-08-02 11:00 | 2016-08-02 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 5s C4 (5s East Calgary) | 2016-08-02 11:00 | 2016-08-02 12:00 | N | N | de-energize for weed spraying in cap bank area. | Shunts |  |  | Pre-Condition
ALTALINK | 394s T2 (394s Empress) | 2016-08-02 11:00 | 2016-08-09 13:00 | N | N | T2 oil containment installation | Transformer |  |  | For Information Only
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2016-08-02 11:00 | 2016-08-11 17:00 | N | N | protection changes for new L181s (CoL; Chinook) | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary) | 2016-08-02 12:00 | 2016-08-02 13:00 | N | N | de-energize for weed spraying in capacitor bank area | Shunts |  |  | Pre-Condition
ALTALINK | 275s 1952 (275s Jenner) | 2016-08-02 13:00 | 2016-08-03 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 151s 44 (151s Strathmore) | 2016-08-02 14:30 | 2016-08-02 15:30 | N | N | cap bank weed spraying | Circuit Breaker |  |  | For Information Only
VISIONREQ | 354S Summerview | 2016-08-02 16:30 | 2016-08-03 17:00 | N | N | 34kV switching | Station |  |  | For Information Only
ALTALINK | 103s 1252 (103s Goose Lake),103s 352 (103s Goose Lake),103s 652 (103s Goose Lake) | 2016-08-03 08:00 | 2016-08-05 16:00 | N | Y | forced outage; breaker inoperable and PT failure | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 755s 902 (755s Cordel) | 2016-08-03 09:00 | 2016-08-03 16:00 | N | Y | breaker SF6 GL315 partial testing | Circuit Breaker |  | 755S - BREAKER 902 SF6 GL315 PARTIAL TESTING 755S ring bus will be open | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s 1752 (89s Ellerslie) | 2016-08-03 09:00 | 2016-08-04 17:00 | N | Y | replacing accessory port to repair leak | Circuit Breaker |  | This work was cancelled this week (July 25  27) due to field worker illness. This is considered URGENT as the breaker is leaking gas that may result in lockout. | Contingency Requires Mitigation, 500 kV
ATCO | 957s 901 (957s McClelland) | 2016-08-04 07:00 | 2016-08-05 17:00 | N | Y | commission Kearl RAS trip logic | Circuit Breaker |  | Commission Kearl RAS trip logic. L9900 will be fed from 903 only, 240kV ring at 957s will be open | 240 kV, Pre-Condition
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar),71s 1352 (71s Lamoureux),71s 1252 (71s Lamoureux) | 2016-08-04 07:00 | 2016-08-04 17:00 | N | Y | doble | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 557s T2 (557s Castle Downs) | 2016-08-04 07:00 | 2016-08-31 17:00 | N | Y | oil reclamation | Transformer |  |  | 240 kV
ALTALINK | 879L (368s Burdett - 523s Bullshead) | 2016-08-04 08:00 | 2016-08-05 17:00 | N | Y | Install new foundation under existing 879L for future 676/879L outside of 523s | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm),608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm),138S T2 (138s Windy Flats) | 2016-08-04 08:00 | 2016-08-04 15:00 | N | Y | replace missing site glass | Line, Transformer |  |  | 240 kV, Restricts Generation
ATCO | 791s 702T (791s Rainbow Lake) | 2016-08-04 08:00 | 2016-08-04 17:00 | N | N | emergency work to repair oil leak | Transformer |  |  | For Information Only
IMPERIALOIL | Kearl L9900 RAS | 2016-08-04 08:00 | 2016-09-01 16:00 | N | N | Voltage Instability RAS commissioning ISD: Sep 1, 2016 | RAS
IMPERIALOIL | Kearl Islanding RAS | 2016-08-04 08:00 | 2016-08-15 17:00 | N | N | installation of a new IOL Load RAS scheme | RAS |  |  | Impacts RAS
ALTALINK | 384s T1 (384s Keystone) | 2016-08-04 08:30 | 2016-08-04 17:00 | N | N | doble testing and TC maintenance | Transformer |  |  | For Information Only
ALTALINK | 523s C1 (523s Bullshead),523s 33 (523s Bullshead) | 2016-08-04 09:30 | 2016-08-04 10:30 | N | N | de-energize for cap bank weed spraying. | Circuit Breaker, Shunts |  |  | Pre-Condition
VISIONREQ | 354S Summerview | 2016-08-04 13:00 | 2016-08-05 14:00 | N | N | 34kV switching | Station |  |  | For Information Only
ATCO | 957s 903 (957s McClelland) | 2016-08-06 07:00 | 2016-08-07 17:00 | N | Y | commission Kearl RAS trip logic | Circuit Breaker |  | Commission Kearl RAS trip logic. L9900 will be fed from 903 only, 240kV ring at 957s will be open | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 330p 802 (330p Genesee) | 2016-08-07 07:00 | 2016-08-11 17:00 | N | N | protection upgrade | Circuit Breaker |  |  | For Information Only
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11) | 2016-08-08 01:00 | 2016-08-08 05:00 | N | Y | repair SW 83 @ 11 sub, substation wash | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft W724 (Woodcroft) | 2016-08-08 07:00 | 2016-08-11 17:00 | N | N | cutover of new BF/sync check relay to W724 breaker | Circuit Breaker |  |  | Creates Radial Feeds
EPCOR | RossdaleT3 (Rossdale) | 2016-08-08 07:00 | 2016-08-09 17:00 | N | N | installing new Tap changer control relays | Transformer |  |  | Pre-Condition
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome) | 2016-08-08 07:00 | 2016-08-18 17:00 | N | Y | relay testing and teleprotection cutover for line relocation to Keephills | Line |  |  | 240 kV, Overload, Creates Radial Feeds
REDDEER | 217s T1 (217s North Red Deer) | 2016-08-08 07:30 | 2016-08-09 17:00 | N | N | transformer 14T1 138kV bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 909L (310p Sundance - 665s Dome) | 2016-08-08 08:00 | 2016-08-18 16:00 | N | N | In-service-date: Aug 18, 2016. 909L (320p Keephills - 665s Dome) will be de-energized and re-terminated at 310p Sundance. | Line |  |  | 240 kV, For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2016-08-08 08:00 | 2016-08-09 12:00 | N | N | louver replacements in 8.5TR and 8.6TR bays (safety watch required) | Transformer |  |  | For Information Only
ALTALINK | 1038L (138s Windy Flats - 237s Foothills) | 2016-08-08 08:00 | 2016-08-14 18:00 | N | Y | emergency damper replacements | Line |  |  | 240 kV, Pre-Condition
ENMAX | 8.6TR (ENMAX 8) | 2016-08-08 08:00 | 2016-08-09 12:00 | N | N | louver replacements in 8.5TR and 8.6TR bays (safety watch required) | Transformer |  |  | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2016-08-08 08:00 | 2016-08-09 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 38s 738W (38s East Edmonton) | 2016-08-08 08:00 | 2016-08-09 17:00 | N | N | raise 738L structure # 1 | Circuit Breaker | Altalink will be creating an open point on 738L and working on the span line going into 38s East Edmonton. |  | For Information Only
ATCO | 793s 701T (A793s West Peace) | 2016-08-08 08:30 | 2016-08-09 16:30 | N | N | 701TCS complete maintenance and testing | Transformer |  | 701TCS Complete Maintenance and Testing, 701T load will be transferred to 702T. Jumper J1 will be created between 701TCS and the 144kV bus. | For Information Only
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome),320p T1 (320p Keephills),320p Keephills 240kV Bus B | 2016-08-08 09:00 | 2016-08-09 17:00 | N | Y | switch maintenance on 320p213, 320p3B, 320p7B, 320p9B, 320p90; disconnect 909L TPR from 320p | Transformer, Bus, Line | 3. Results of next contingencies depend on Sundance and KEG generation. |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 740L (58s Edson - 39s Bickerdike) | 2016-08-08 10:00 | 2016-08-10 17:00 | N | N | line component replacements | Line |  |  | Pre-Condition
ALTALINK | 404s T1 (404s Peace Butte) | 2016-08-08 10:00 | 2016-08-11 17:00 | N | N | replace 25kV and 138kV bushings, transformer maintenance, doble, neutral, breather and fan repairs | Transformer |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky) | 2016-08-08 11:00 | 2016-08-11 15:00 | N | Y | annual main, change leaking pump, check thyrister fail | Shunts |  | Annual main, change leaking pump, check thyrister fail SVC not available | Pre-Condition
ALTALINK | 40s T1 (40s Wetaskiwin) | 2016-08-08 12:00 | 2016-08-12 17:00 | N | N | 25kV bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2016-08-08 12:00 | 2016-08-10 17:00 | N | Y | replacing failed capacitor cans in the filter bank | Shunts |  |  | For Information Only
ALTALINK | 68s T2 (68s Willesden Green) | 2016-08-08 13:00 | 2016-08-18 17:00 | N | Y | replace tap selector switch | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 159s T2 (159s Colinton) | 2016-08-09 07:30 | 2016-08-11 07:00 | N | N | installation of Fortis underground cables | Transformer |  |  | For Information Only
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2016-08-09 08:00 | 2016-08-09 16:00 | N | N | sheath test and DGA on LPOF 138KV cable, doble test 3PT138-Z31 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 123s T1 (123s Banff) | 2016-08-09 08:00 | 2016-08-09 16:00 | N | N | ACC visibility enhancements | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 908L (89s Ellerslie - 816s Petrolia) | 2016-08-09 08:00 | 2016-08-11 16:00 | N | Y | RTU replacement project | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2016-08-09 08:00 | 2016-08-14 17:00 | N | Y | emergency damper repair | Line |  |  | For Information Only, 500 kV
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2016-08-09 08:00 | 2016-08-09 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | For Information Only
ALTALINK | 61s T1 (61s Lodgepole) | 2016-08-09 08:30 | 2016-08-10 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO | 732s 902 (732s Mitsue) | 2016-08-09 09:30 | 2016-08-10 14:00 | N | Y | partial on breaker 902, 240kV ring will remain open | Circuit Breaker |  | Partial on Breaker 902, 240kV ring will remain open | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 909L (320p Keephills - 665s Dome),320p1352 (909L) - GOI | 2016-08-09 17:00 | 2016-08-15 08:00 | N | Y | switch maintenance 320p212, disconnect 909L slack span and add new jumpers to VT13,AES to complete disconnection of 909L protections | Terminal Equipment, Line |  | Switch maintenance 320p212, disconnect 909L slack span and add new jumpers to VT13, AES to complete disconnection of 909L protections, end to end TPR checks with EPCOR, setting changes on old 909L protections at 320p (if time allows). Redundant protections will be taken out of service one at a time. | 240 kV, For Information Only
ALTALINK | 320p 252 (320p Keephills),320p 352 (320p Keephills) | 2016-08-09 17:00 | 2016-08-11 17:00 | N | Y | switch maintenance - 320p2A, 320p3A, 320p289 | Circuit Breaker |  |  | 240 kV
EPCOR | RossdaleT4 (Rossdale) | 2016-08-10 07:00 | 2016-08-11 17:00 | N | N | installing new tap changer control relays | Transformer |  |  | Pre-Condition
ALTALINK | 325s T2 (325s Leduc) | 2016-08-10 08:00 | 2016-08-10 17:30 | N | N | test energize new 25kv ABB switchgear spare breaker (325s1052) | Transformer |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2016-08-10 08:00 | 2016-08-10 16:00 | N | N | sheath test, DGA LPOF | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 40.81L (ENMAX 40 - ENMAX 41),ENMAX 41 B138-40.81 (ENMAX 41) | 2016-08-10 08:00 | 2016-08-12 16:00 | N | N | breaker inspection & grading capacitor replacement on 41B138-40.81 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 123s T2 (123s Banff) | 2016-08-10 08:00 | 2016-08-10 16:00 | N | N | ACC Visibility Enhancements | Transformer |  |  | Creates Radial Feeds
ATCO | 793s 702T (A793s West Peace) | 2016-08-10 08:30 | 2016-08-12 16:30 | N | N | 702TCS complete maintenance and testing | Transformer |  | 702TCS Complete Maintenance and Testing, 702T load will be transferred to 701T. Jumper J2 will be created between 702TCS and the 144kV bus. | For Information Only
AESO-SC | DT | 2016-08-10 08:30 | 2016-08-10 11:30 | N | N | DT release | SCInternal |  |  | For Information Only
ALTALINK | 159s T2 (159s Colinton),223L (159s Colinton - 150s Clyde) | 2016-08-11 07:30 | 2016-08-11 17:30 | N | N | installation of risers on T2 | Transformer, Line |  | installation of risers on T2, close 159s OP'C', 159s OP'E' | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ATCO | 6L06 (705s Kitscoty - 751s Hill) | 2016-08-11 08:00 | 2016-08-12 17:00 | N | N | urgent change poles | Line |  | Need an emergency GOI on 6L06 to change some poles that the county dug up, to build the road, they are on mounds and they never left enough soil around them. | For Information Only
ALTALINK | 61s T1 (61s Lodgepole),202L (61s Lodgepole - 202L335),836L (61s Lodgepole - 283s Violet Grove) | 2016-08-11 10:00 | 2016-08-14 17:00 | N | N | forced outage | Line, Transformer |  | Forced outage of 61s T1. 61s Bus 1 (along with 836L, 202L to 202L335 tap and 61s T1) had to be taken out of service. | Overload, Restricts Generation
ATCO | 813s SVC (813s Little Smoky) | 2016-08-12 08:00 | 2016-08-17 10:00 | N | Y | forced outage | Shunts |  | Annual main, change leaking pump, check thyrister fail SVC not available | Pre-Condition
ENMAX | 8.3TR (ENMAX 8),8.4TR (ENMAX 8) | 2016-08-12 12:00 | 2016-08-15 12:00 | N | N | louver replacements in transformer bays | Transformer |  | Louver Replacements in 8.3TR and 8.4TR bays (safety watch required) | For Information Only
ATCO | 7L749 (716s Lloydminister - 7L749D2) | 2016-08-13 07:00 | 2016-08-14 19:00 | N | Y | install poles for line mitigation | Line |  | Install poles for Line mitigation, these structures cannot be done with a HOP | Overload, Creates Radial Feeds
ENMAX | 13.4TR (ENMAX 13),11.81L (ENMAX 13 - ENMAX 11),13.60L (ENMAX 27 - ENMAX 13),13.82L (ENMAX 22 - ENMAX 13) | 2016-08-13 08:00 | 2016-08-14 16:00 | N | N | substation washing and maintenance at 13 sub | Line, Transformer |  | 13.82L. 11.81L. 13.4TR. 13.60L - -Sub washing. 138kV SW maint @ 13 Sub. Paint bus structure. Emergency replacement on str. 57, 59 13.60L. GOI for 13.4TR/13.60L on return | Pre-Condition, Creates Radial Feeds
Lethbridge | 172L (370s North Lethbridge - 181s Chinook),463L (15s Fort Macleod - 181s Chinook) | 2016-08-14 08:00 | 2016-08-26 16:00 | N | N | In-service-date: Aug 23, 2016. Cut in 181s Chinook. | Line |  |  | For Information Only
ENMAX | 8.1TR (ENMAX 8),8.2TR (ENMAX 8) | 2016-08-14 12:00 | 2016-08-18 12:00 | N | N | louver replacements in 8.1TR and 8.2TR bays | Transformer |  |  | For Information Only
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2016-08-14 16:00 | 2016-08-18 16:00 | N | N | replacement on structures and substation maintenance | Line, Transformer |  | 13.4TR. 13.60L - Emergency replacement on structures 57 and 59. 69kV HV SW Maint. HV Breaker Maint 27B69-13.60L. SF6 Sample 13B69-13.60/ PRD installation on 13.4TR. Doble 69kV PTs. Multilin relay testing 13.4TR. SEL321 13.60L @ 27 Sub. | Pre-Condition, Creates Radial Feeds
ATCO | 715s 701T (715s Leming Lake) | 2016-08-15 07:00 | 2016-08-26 18:00 | N | N | transformer maintenance and protection upgrade | Transformer |  | Transformer maintenance and protection upgrade. | For Information Only
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198) | 2016-08-15 07:00 | 2016-08-18 18:00 | N | Y | 7 structure replacements & bird proof | Line |  | 7 structure replacements & bird proof 2 Str's on 514L (Str's 104 to 146) | Restricts Generation, Firm Load Loss
EPCOR | RossdaleT2 (Rossdale) | 2016-08-15 07:00 | 2016-08-19 17:00 | N | N | installing new tap changer control relays | Transformer |  |  | For Information Only
ALTALINK | 159s T1 (159s Colinton),710L (159s Colinton - 56s Boyle),159s 48 (159s Colinton),159s 138kV Bus 1 (159s Colinton) | 2016-08-15 07:30 | 2016-08-16 17:00 | N | N | salvage of 138KV bus differential, install new bus differential | Bus, Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2016-08-15 08:00 | 2016-08-17 17:00 | N | Y | replacing failed capacitor cans in the filter bank | Shunts |  | Replacing failed capacitor cans in the filter bank; redundant filter bank will be in service | For Information Only, 500 kV
ENMAX | 27.2TR (ENMAX 27),ENMAX 27 69kV Bus | 2016-08-15 08:00 | 2016-08-15 16:00 | N | N | sub washing half of 27s | Transformer, Bus |  |  | For Information Only
CNRL | CNR5 CNRL Horizon | 2016-08-15 08:00 | 2016-08-25 16:00 | N | N | In-Service-Date: Aug 25. A new gas-fired generator (MC of 87.6 MW) commissioning at 842s Horizon Upgrading | Unit |  |  | Pre-Condition
ALTALINK, EPCOR | 310p 1352 (310p Sundance),310p 1452 (310p Sundance),320p 1352 (320p Keephills),909L (320p Keephills - 665s Dome),909L (310p Sundance - 665s Dome) | 2016-08-15 08:00 | 2016-08-15 17:00 | N | Y | complete line configuration, AES to complete end to end functional testing with EPCOR | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 1037L (138s Windy Flats - 237s Foothills) | 2016-08-15 08:00 | 2016-08-20 18:00 | N | Y | install bird diverters, Replace spacer dampers | Line |  |  | 240 kV, Pre-Condition
ENMAX | 14.3TR (ENMAX 14) | 2016-08-15 08:00 | 2016-08-16 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 743s 702 (743s Sarah Lake),743s 703 (743s Sarah Lake),743s Sarah Lake 144kV Bus | 2016-08-15 08:00 | 2016-08-31 17:30 | N | N | remove 702TCS, replace with breaker 706, switch 706A, 700PT2, install new protection in new building. | Bus, Circuit Breaker |  | Remove 702TCS, add breaker 706, switch 706A, 700PT2, install new protection in new building. When 706A has been commissioned issue COG on 706A, then release this permit, then restore 7L67/7L230 bypass to normal. | Pre-Condition
ALTALINK | 38S East Edmonton | 2016-08-15 08:00 | 2016-08-18 17:00 | N | N | salvage 38s20 breaker | Station |  |  | For Information Only
ATCO | 793s 701T (A793s West Peace) | 2016-08-15 09:30 | 2016-08-17 16:00 | N | N | complete tap changer maintenance & check 501VRX | Transformer |  | Complete Tap Changer Maintenance & Check 501VRX | For Information Only
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress),163s 1552 (163s Amoco Empress),163s 1752 (163s Amoco Empress) | 2016-08-15 10:00 | 2016-08-25 15:00 | N | Y | replace 163s1552 breaker and current transformers | Line, Circuit Breaker |  |  | 240 kV, Overload, Over/Under Voltage
ALTALINK | 1047L (650s Hansman Lake - 574s Nilrem),953L (574s Nilrem - 755s Cordel) | 2016-08-15 10:00 | 2016-08-16 17:00 | N | Y | damper repair | Line |  |  | 240 kV, Pre-Condition
Lethbridge | 172L (370s North Lethbridge - 181s Chinook),463L (15s Fort Macleod - 181s Chinook) | 2016-08-15 11:00 | 2016-08-25 17:00 | N | Y | cut-in to new CoL Chinook (L181s) substation | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2016-08-15 12:00 | 2016-08-18 16:00 | N | Y | RTU replacement project | Line |  |  | 240 kV
ALTALINK | 123s551W (123s Banff) | 2016-08-15 12:00 | 2016-08-18 16:00 | N | N | ACC visibility enhancements | Circuit Breaker |  |  | For Information Only
ALTALINK | 38s 7252 (38s East Edmonton) | 2016-08-15 13:00 | 2016-08-18 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 652 (310p Sundance) | 2016-08-15 13:00 | 2016-08-18 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s C1 (17s Benalto),17s 16 (17s Benalto) | 2016-08-15 13:00 | 2016-08-15 15:00 | N | Y | de-energize for weed spraying. | Circuit Breaker, Shunts |  |  | 240 kV, For Information Only
ALTALINK | 310p 1352 (310p Sundance),310p 1452 (310p Sundance),909L (310p Sundance - 665s Dome) | 2016-08-15 17:00 | 2016-08-18 16:00 | N | Y | switch maintenance 320p212, disconnect 909L slack span and add new jumpers to VT13,AES to complete disconnection of 909L protections | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 320p 1352 (320p Keephills),1043L (320p - OJ @ Str 13) GOI | 2016-08-15 17:00 | 2016-08-18 17:00 | N | N | disconnect 1043L from L13 bay and connect to L10 bay | Terminal Equipment, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 945s T2 (945s Sunshine Village) | 2016-08-16 08:00 | 2016-08-18 17:00 | N | N | repair transformer leaks | Transformer |  |  | For Information Only
ATCO, TRANSCANADAP, ALTALINK | 910s 701T (910s Excel),7L116 (910s Excel - 959s Lanfine),910s 701 (910s Excel) | 2016-08-16 08:00 | 2016-08-16 16:00 | N | N | Breaker maintenance | Line, Circuit Breaker, Transformer |  | Breaker maintenance, Customer has agreed to 3L218 outage, 910s stn service will be OOS | For Information Only
ENMAX | 6.4TR (ENMAX 6),6.80L (ENMAX 30 - ENMAX 6) | 2016-08-16 08:00 | 2016-08-16 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 396s T1 (396s Pincher Creek),396s T2 (396s Pincher Creek),185L (396s Pincher Creek - 379s Shell Canada Waterton) | 2016-08-16 08:00 | 2016-08-17 16:00 | N | N | replace 396s61 switch | Transformer, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2016-08-16 08:00 | 2016-08-26 17:00 | N | Y | damper repair | Line |  |  | Overload, 500 kV
VISIONREQ | 354s DVAR2 (354s Summerview) | 2016-08-16 08:00 | 2016-08-31 16:00 | N | N | communication upgrade | Shunts |  |  | For Information Only
ATCO | 743s 702T (743s Sarah Lake) | 2016-08-16 08:00 | 2016-09-27 17:30 | N | N | 743s 502 and 502VR also out of service, remove 702TCS, add breaker 706, switch 706A, 700PT2, install new protection in new building. | Transformer |  |  | For Information Only
ENMAX | 6.1TR (ENMAX 6),6.82L (ENMAX 6 - ENMAX 41) | 2016-08-16 12:01 | 2016-08-16 16:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2016-08-16 14:00 | 2016-08-16 18:00 | N | Y | emergency line repairs | Line |  | High Load Move | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 159s T2 (159s Colinton),223L (159s Colinton - 150s Clyde),159s 138 kV Bus 2 (159s Colinton),159s 223 (159s Colinton) | 2016-08-17 07:30 | 2016-08-17 17:00 | N | N | isolate 152 to remove existing bus differential and install CT from 152 and T2 to new bus differential | Line, Circuit Breaker, Bus, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 370s 1152 (370s North Lethbridge) | 2016-08-17 08:00 | 2016-08-18 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 733s 702T (733s Simonette) | 2016-08-17 08:00 | 2016-08-19 16:00 | N | N | set up mobile sub parallel to 733s702T | Transformer |  | set up of mobile substation 835s, leads to Stage 2 of attached SLDs On return to normal; Soak 835s for 24hrs Parallel 835s to 702T @ 733s Transfer all 25kV load to 835s (see 2-38451) Proceed to GOI 2-33249 | For Information Only
ENMAX | 14.4TR (ENMAX 14) | 2016-08-17 08:00 | 2016-08-18 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 767L (320p Keephills - 767L167A) | 2016-08-17 08:00 | 2016-08-19 10:00 | N | N | remove portion of old 909L from over line | Line |  |  | For Information Only
ALTALINK | 834L (384s Keystone - 320p Keephills) | 2016-08-17 08:00 | 2016-08-18 16:00 | N | N | remove portion of old 909L from over line | Line |  |  | Creates Radial Feeds
ALTALINK | 514L (513s Lundbreck - 514L198) | 2016-08-17 08:00 | 2016-08-18 17:00 | N | Y | line maintenance | Line |  |  | Firm Load Loss
ALTALINK | 681L (377s Hardisty - 478s Tucuman),702L (377s Hardisty - 137s Sedgewick),377s 473C102 (377s Hardisty) | 2016-08-17 08:00 | 2016-08-17 17:00 | N | N | change settings to accommodate the new transformer at 377s | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK, EPCOR | 809L (320p Keephills - 510s Sunnybrook) | 2016-08-17 10:00 | 2016-08-19 08:00 | N | Y | remove portion of old 909L from over line | Line |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2016-08-17 23:00 | 2016-08-18 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 688L (199s East Airdrie - 688DL23),199s 688 (199s East Airdrie) | 2016-08-18 08:00 | 2016-08-18 17:00 | N | N | create open point 'A' on 688L (str15), 284s to remain online | Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2016-08-18 08:00 | 2016-08-18 12:00 | N | Y | fall substation washing | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2016-08-18 12:00 | 2016-08-18 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 8.6TR (ENMAX 8) | 2016-08-18 12:00 | 2016-08-21 16:00 | N | N | louver replacements in 8.5TR and 8.6TR bays | Transformer |  |  | For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2016-08-18 12:00 | 2016-08-21 16:00 | N | N | louver replacements in 8.5TR and 8.6TR bays | Transformer |  |  | For Information Only
ATCO | 840S McNeill Station | 2016-08-18 12:30 | 2016-08-18 14:30 | N | Y | emergency. Make PLC change for valve cooling | Station |  | We require the McNeill Convertor to Standby for a couple hours to fix the PLC Cooling system. There is a problem with the system under large ramps and in warm ambient conditions that could cause a the convertor to Trip. | Limits ATC
ALTALINK | 320p 1352 (320p Keephills) | 2016-08-18 16:00 | 2016-10-08 17:00 | N | Y | setting changes on old 909L protections at 320p | Circuit Breaker |  | Redundant protections will be removed from service one at a time. | 240 kV, For Information Only
ALTALINK | 688L (199s East Airdrie - 688DL23) | 2016-08-18 17:01 | 2016-10-10 18:15 | N | Y | line rebuild | Line |  |  | Creates Radial Feeds
ALTALINK | 520L (887s Mobil Oil Carson Creek - 520L1),526L (268s Whitecourt - 526DL185) | 2016-08-19 08:00 | 2016-08-19 09:00 | N | N | create open point 'A' at structure 6 on 520L | Line |  |  | Firm Load Loss, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2016-08-19 08:00 | 2016-09-02 17:30 | N | Y | annual maintenance | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 13.1TR (ENMAX 13),13.3TR (ENMAX 13),2.83L (ENMAX 13 - 2.83L tap),3.84L (ENMAX 13 - ENMAX 3) | 2016-08-19 08:00 | 2016-08-19 16:00 | N | N | substation washing | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 520L (887s Mobil Oil Carson Creek - 520L1),526L (268s Whitecourt - 526DL185),526L (526L90 - 520L tap) | 2016-08-19 09:01 | 2016-08-25 16:00 | N | N | replace 520L1 and structures on 526L | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station) | 2016-08-19 17:01 | 2016-09-02 17:00 | N | Y | degassing | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ALTALINK, ENMAX | 42s T1 (42s Sarcee),42s T2 (42s Sarcee),21.80L (42s Sarcee - ENMAX 21),7.82L (42s Sarcee - ENMAX 7),693L (42s Sarcee - ENMAX 10),42s Sarcee 138 kV North Bus | 2016-08-20 08:00 | 2016-08-21 17:00 | N | Y | replace strain insulators over 42s60, connect 42s32 to north bus | Bus, Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 733s 702T (733s Simonette),7L40 (813s Little Smoky - 733s Simonette),733s 701 (733s Simonette),733s 702 (733s Simonette),7L80 (740s H.R.Milner - 733s Simonette) | 2016-08-21 07:00 | 2016-08-26 17:30 | N | N | reconfigure 144 kv bus, remove old 702T /502VR and install new 702T | Circuit Breaker, Line, Transformer |  | Construction (Reconfigure 144 kv bus, remove old 702T and 502VR. Finish new 702T install), 7L40 and 7L80 open ended @ 733s until Aug 26, 835s connected to 7L80 and will carry all 733s 25kV load. Aug 21 Confirm 835s GOI RTN switching complete Confirm alternate stn service supply installed Parallel 702T w/ 835s Transfer 733s load to 835s (see load transfer 2-38451) Isolate as reqd (7L40/7L80 will be open ended @ 733s) Aug 26 Confirm COG issued on 703A Shrink GOI down GOI to 500D1, 500D2, 500D7, 503A, 502A, J1 Issue GOI 2-33249B Energize 144kV bus @ 733s / Restore 7L40/7L80 to normal Sep 2-3 Refer to attached wplan for 702T energization sequence | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 803 (330p Genesee) | 2016-08-22 07:00 | 2016-08-28 17:00 | N | N | protection upgrade | Circuit Breaker |  |  | For Information Only
ALTALINK | 985s T3 (985s Exshaw) | 2016-08-22 08:00 | 2016-08-24 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3),3.84L (ENMAX 13 - ENMAX 3) | 2016-08-22 08:00 | 2016-08-22 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Saskpower | SaskPower C1S | 2016-08-22 08:00 | 2016-08-24 18:00 | N | N | change spars and sway braces | Line |  |  | Limits ATC
ALTALINK | 1106L (ENMAX 65 - 237s Foothills) | 2016-08-22 08:00 | 2016-08-24 17:00 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
ENMAX | 10.2TR (ENMAX 10) | 2016-08-22 08:00 | 2016-08-23 16:00 | N | N | LTC maintenance | Transformer
ENMAX | 13.3TR (ENMAX 13) | 2016-08-22 08:00 | 2016-08-26 16:00 | N | N | Doble | Transformer
ALTALINK | 55s T1 (55s Olds) | 2016-08-22 09:00 | 2016-08-25 15:00 | N | N | bird cover to be installed on various pieces of equipment | Transformer
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2016-08-22 09:30 | 2016-09-02 17:30 | Y | Y | line maintenance and install bird diverters | Line |  |  | Pre-Condition, Limits ATC, Creates Radial Feeds, 500 kV
ALTALINK | 511s ACF12 (511s Crossings) | 2016-08-22 10:00 | 2016-08-22 17:00 | N | Y | replace failed contacts | Shunts |  |  | 240 kV, For Information Only
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2016-08-22 12:00 | 2016-08-22 16:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 71s 1352 (71s Lamoureux) | 2016-08-22 12:30 | 2016-08-22 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 356s 652 (356s Milo) | 2016-08-22 13:00 | 2016-08-23 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 650s SVC (650s Hansman Lake),650s T3 (650s Hansman Lake) | 2016-08-22 15:00 | 2016-08-25 17:00 | N | Y | SVC maintenance | Shunts, Transformer |  |  | 240 kV
ALTALINK | 159s T1 (159s Colinton) | 2016-08-23 07:30 | 2016-09-06 07:30 | N | N | add new SS1, add 25kV PT at VT4, salvage old SS1 TX, add AMI feed, install Fortis U/G feed to 232L, close open point 'F', open point 'G', open point 'H', salvage old 389L, old 469L slack spans, 25KV bus 1 bypass and install 159s189 | Transformer |  | add new SS1, add 25kV PT at VT4, salvage old SS1 TX, add AMI feed, install Fortis U/G feed to 232L, close Open Point 'F', Open Point 'G', Open Point 'H', salvage old 389L, old 469L slack spans, 25KV bus 1 Bypass, 25kV reg. Bypass and install 159s189 | For Information Only
ALTALINK | 887S Carson Creek | 2016-08-23 08:00 | 2016-08-24 16:00 | N | N | install a new line side single phase PPT and decommission and salvage the existing station service VT (SS1) | Station |  | install a new line side single phase PPT and decommission and salvage the existing station service VT (SS1). | For Information Only
ATCO | 876s 906 (876s Brintnell) | 2016-08-23 08:00 | 2016-08-23 16:00 | N | Y | replace failed densimeters, open ring bus | Circuit Breaker |  | Replace Failed Densimeters, Open Ring Bus, Short Notice EmergencyFix | 240 kV, Contingency Requires Mitigation
ALTALINK | 879L (368s Burdett - 523s Bullshead) | 2016-08-23 08:00 | 2016-08-23 17:00 | N | N | structure replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | ENMAX 20 B138-20.82 (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2016-08-23 08:00 | 2016-08-23 16:00 | N | N | top up SF6 | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 925L (63s Red Deer - 74s Janet),63s 252 (63s Red Deer),63s 352 (63s Red Deer) | 2016-08-23 08:30 | 2016-08-23 17:00 | N | Y | adjust 240kV switch | Circuit Breaker, Line |  |  | 240 kV
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2016-08-23 09:00 | 2016-08-23 15:00 | N | N | migration of TPR circuits to new radio at 793s and 9286R, affects 859L TPR | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2352 (310p Sundance) | 2016-08-23 11:00 | 2016-08-24 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | SC workbook | 2016-08-23 13:00 | 2016-08-23 14:00 | N | N | remove KEG table | SCInternal |  |  | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2016-08-24 08:00 | 2016-08-25 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 262s T1 (262s Rocky Mountain House),870L (262s Rocky Mountain House - 263s Strachan),262s35 (262s Rocky Mountain House) | 2016-08-24 08:00 | 2016-08-24 11:30 | N | N | switch maintenance | Line, Switch, Transformer |  | Switch maintenance on 262s35 and 262s44 | Pre-Condition, Creates Radial Feeds
ALTALINK | 131s Moon Lake RTU/SCADA | 2016-08-24 08:00 | 2016-08-25 17:00 | N | N | repair the failing radio link to 9516R Tomahawk | Terminal Equipment |  |  | Affects Visibility
ATCO | 930s Syn Condenser (930s Arcenciel) | 2016-08-24 08:00 | 2016-08-24 12:00 | N | Y | emergency repairs to the air handling unit | Shunts |  | the Arcenciel Synchronous Condenser will be required to be shut down between 08:00-12:00 to make emergency repairs to the Air handling unit. The repairs should only take a couple of hours. The reason this needs to be turned off is because when they are changing units, there is a high risk of tripping the SC offline. | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2016-08-24 08:00 | 2016-08-25 19:00 | N | N | damper replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),ENMAX 3 B138-3.84 (ENMAX 3) | 2016-08-24 08:00 | 2016-08-24 16:00 | N | N | change DFR CT ratio | Line, Circuit Breaker |  | 3.84L 13B138-3.84 - Change DFR CT ratio from 800/5 to 1200/5 and update DFR settings accordingly | Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s 252 (244s Bowmanton) | 2016-08-24 08:00 | 2016-08-24 17:00 | N | Y | investigate A phase issue | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 263s C1 (263s Strachan),263s 35 (263s Strachan) | 2016-08-24 08:30 | 2016-08-24 11:30 | N | N | de-energize for cap bank weed spraying | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 165S T.M.P.L. Gainford | 2016-08-24 08:30 | 2016-08-24 17:30 | N | N | transformer and breaker maintenance | Terminal Equipment |  | 165s Station - GOI - Transformer and breaker mtce | Firm Load Loss
ALTALINK | 835L (384s Keystone - 835L tap),384s 835X (384s Keystone) | 2016-08-24 09:30 | 2016-08-24 17:00 | N | N | investigate and repair line reclosing issue | Line, Circuit Breaker |  | 384s835X (835L) - GOI - Investigate/repair line reclosing issue | Firm Load Loss, Creates Radial Feeds
ATCO | 939s 903 (939s Livock) | 2016-08-24 10:00 | 2016-08-25 14:00 | N | Y | change faulty densimeter | Circuit Breaker |  | Change Faulty Densimeter, 903 Bkr @ 939S Livock RING BUS WILL BE OPEN FOR THE DURATION OF THE WORK | 240 kV, Contingency Requires Mitigation
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2016-08-24 11:30 | 2016-09-01 17:45 | N | N | transformer oil reclaim | Transformer |  | 262s T1 (TX18419) - GOI - Transformer oil reclaim | For Information Only
ALTALINK | 887S Carson Creek | 2016-08-24 16:01 | 2016-08-25 17:00 | N | N | repair T1 leaks and replace H2 stud connector | Station |  | 887s Station GOI - Repair 887s T1 leaks, replace H2 stud connector | For Information Only
ALTALINK | 661S Laura Lake,661s T1 (661s Laura Lake) | 2016-08-25 08:00 | 2016-08-25 17:00 | N | N | 25kV relay maintenance | Transformer, Station |  |  | For Information Only
ALTALINK | 1107L (ENMAX 65 - 237s Foothills) | 2016-08-25 08:00 | 2016-08-27 17:00 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
ENMAX | 26.1TR (ENMAX 26),26.81L (ENMAX 54 - ENMAX 26) | 2016-08-25 08:00 | 2016-08-25 12:00 | N | N | substation washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 879L (368s Burdett - 523s Bullshead) | 2016-08-25 08:00 | 2016-08-28 17:00 | N | N | structure replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 1054L (13s Deerland - 12s Heartland),13s 1054 (13s Deerland) | 2016-08-25 09:00 | 2016-08-25 17:00 | N | Y | repairing hotspot | Line, Switch |  |  | 240 kV, Pre-Condition, Overload
ATCO | 847s 201-PTL260-2D1 (847s Muskeg) | 2016-08-25 12:00 | 2016-08-26 16:00 | N | Y | test logic to 201-PTL260-2D1 and test statuses for 201-PTL260-2GS1 | Switch |  | To test logic to 201-PTL260-2D1 and test statuses for 201-PTL260-2GS1. This T&O will be opened right after the GOI for this outage is released since 201-PTL260-2D1 is an isolation point for the GOI. | For Information Only
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26) | 2016-08-25 12:00 | 2016-08-25 16:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 520L (887s Mobil Oil Carson Creek - 520L1),526L (268s Whitecourt - 526DL185),526L (526L90 - 520L tap) | 2016-08-25 16:01 | 2016-08-25 17:00 | N | N | close open point 'A' at structure 6 on 520L, re-energize 520/526L | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.1TR (ENMAX 40),32.83L (ENMAX 32 - ENMAX 40),ENMAX 40 SW83 (ENMAX 40) | 2016-08-26 08:00 | 2016-08-26 12:00 | N | N | substation washing | Line, Transformer, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41),ENMAX 40 SW84 (ENMAX 40) | 2016-08-26 12:00 | 2016-08-26 16:00 | N | N | substation washing | Line, Transformer, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.83L (ENMAX 43 - ENMAX 9),ENMAX 43 B138-9.83 (ENMAX 43) | 2016-08-27 08:00 | 2016-08-28 16:00 | N | N | breaker inspection | Line, Circuit Breaker |  | 9.83L. 43B138-9.83 - HV Breaker Inspection HLR breaker. | Creates Radial Feeds
ALTALINK | 983L (251s Whitla - 244s Bowmanton) | 2016-08-28 07:30 | 2016-08-28 17:30 | N | Y | emergency damper repair | Line |  |  | 240 kV, Creates Radial Feeds
SHELL | 847s 901 (847s Muskeg River),847s 904 (847s Muskeg River),847s 9L66D2 (847s Muskeg River) | 2016-08-29 07:00 | 2016-09-27 17:30 | N | Y | protection upgrades (904 / 9L66D2 / 901PT wiring changes, 904BF and 21B/9L66 relay replacements) | Circuit Breaker, Terminal Equipment |  | OUTAGE # 2 - Protection upgrades (904 / 9L66D2 / 901PT wiring changes, 904BF and 21B/9L66 relay replacements), 9L66 fed via temporary bypass | 240 kV, Pre-Condition
ALTALINK | 1037L (138s Windy Flats - 237s Foothills) | 2016-08-29 07:00 | 2016-08-29 17:00 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake) | 2016-08-29 07:00 | 2016-09-02 17:30 | N | Y | protection upgrade | Line |  | Protection upgrade | Overload, Creates Radial Feeds
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2016-08-29 07:00 | 2016-09-02 17:00 | N | N | close open points A, B, C | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72NW15 (Namao - Woodcroft),Woodcroft W723 (Woodcroft),Woodcroft T2 (Woodcroft) | 2016-08-29 07:00 | 2016-08-29 17:00 | N | N | WDS11& WDS4 repair | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 330p 1205 (330p Genesee) | 2016-08-29 07:00 | 2016-08-30 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
EPCOR | 330p 806 (330p Genesee) | 2016-08-29 07:00 | 2016-09-02 17:00 | N | N | breaker & doble | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 848s 605T (848s Ruth Lake),848s 603 (848s Ruth Lake),848s 604 (848s Ruth Lake),848s Ruth Lake 72kV Bus 1 | 2016-08-29 07:01 | 2016-09-09 17:00 | N | N | install new bus tie switch 500D15 and modify 602T transformer protection | Bus, Transformer, Circuit Breaker |  | Install new bus tie switch 500D15 and modify 602T transformer protection, 25kV load will be offloaded to adjacent sub and/or to 606T, 72kV ring bus will be open between 603A and 604A. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 8.6TR (ENMAX 8) | 2016-08-29 08:00 | 2016-09-02 16:00 | N | N | doble Tx | Transformer |  |  | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook),510s ACF21 (510s Sunnybrook) | 2016-08-29 08:00 | 2016-09-01 18:00 | N | Y | replacing spacers to reduce corona | Shunts |  |  | For Information Only
SUNCOR | 29EDD1SPL9-3,29PL9-3 (29EDD-1 Millennium - 29EDD-3) | 2016-08-29 08:00 | 2016-09-12 20:00 | N | Y | maintenance | Switch, Line |  | 260kV Line 29PL9-3 29EDD-1 // 29EDD1S11 Replace Blade (ISO) | 240 kV, Restricts Generation
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32B138-32.83 (ENMAX 32),32B138-32.82 (ENMAX 32),32B138-32BT5 (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2016-08-29 08:00 | 2016-09-02 16:00 | N | N | replace switches 83 & 89 | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 397s T1 (397s Benbow),720L (347s Fox Creek - 397s Benbow),397s Benbow 138kV Bus 1 | 2016-08-29 08:00 | 2016-09-07 17:00 | N | N | testing trips to breakers for new T1. | Transformer, Bus, Line |  |  | Creates Radial Feeds
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2016-08-29 08:00 | 2016-09-04 17:00 | N | Y | damper repair | Line |  |  | 500 kV
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2016-08-29 08:00 | 2016-08-29 17:00 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ENMAX | 13.1TR (ENMAX 13) | 2016-08-29 08:00 | 2016-08-30 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 947s 701T (947s Weasel Creek) | 2016-08-29 08:00 | 2016-08-29 16:00 | N | N | isolate 701T ngr for customer | Transformer |  | ISOLATE 701T NGR FOR CUSTOMER, Customer outage reqd | For Information Only
ALTALINK | 55s T2 (55s Olds) | 2016-08-29 09:00 | 2016-09-01 13:00 | N | N | bird cover to be installed on various pieces of equipment, replace 2 PTs attached to 55s63 | Transformer |  |  | For Information Only
ENMAX | ENMAX 25 240kV West Bus | 2016-08-29 09:00 | 2016-09-09 08:00 | N | Y | HiPot testing | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1109L (ENMAX 65 - ENMAX 25) | 2016-08-29 09:00 | 2016-08-31 08:00 | N | Y | 1109L hi pot testing | Line |  |  | 240 kV, For Information Only
ALTALINK | 17s Benalto 240 kV South Bus 2 | 2016-08-29 09:00 | 2016-09-01 17:45 | N | Y | replace SEL 387 protection module | Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p 252 (320p Keephills),320p 352 (320p Keephills) | 2016-08-29 10:00 | 2016-09-26 10:00 | N | Y | pre-commissioning of new 1043L protections | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 74s 352 (74s Janet) | 2016-08-29 11:00 | 2016-09-01 17:30 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Saskpower | SaskPower C1S | 2016-08-29 12:00 | 2016-09-01 18:00 | N | N | replace spars and sway braces | Line |  |  | Limits ATC
ALTALINK | 89s 1452 (89s Ellerslie) | 2016-08-29 13:00 | 2016-09-01 17:00 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1038L (138s Windy Flats - 237s Foothills) | 2016-08-30 07:00 | 2016-08-30 17:00 | N | Y | damper replacements | Line | 3. Run a real-time study prior to the outage to determine if next contingency of losing 1037L (237s Foothills  266s SC1  138s Windy Flats) will overload 786L (799s Coleman  B1s BCH Natal) more than 109MVA (~110% of 99MVA), if so - adjust EATL setpoints to transfer more power from south to north. - If still required, then adjust 632s Russell PST. |  | 240 kV, Overload
ALTALINK | 519AL (519L tap - 661s Laura Lake),519L (519AL tap - 996s Imperial Oil Carson Lake) | 2016-08-30 08:00 | 2016-08-31 16:00 | N | N | install a new line side single phase PPT and decommission and salvage the existing station service VT (SS1) | Line |  |  | For Information Only
TRANSCANADAP | 903s 701 (903s Loyalist) | 2016-08-30 08:00 | 2016-08-30 17:00 | N | N | testing and maintenance | Circuit Breaker |  | 903S - 701 BREAKER SF6 GL312 PARTIAL TESTING Bkr 701 Maintenance, 701T LTC Low Temp Alarm Replacement | For Information Only
AESO | 893L (312s Fidler - 893AL tap),893AL (112s Windy Point - 893AL tap) | 2016-08-30 08:00 | 2016-08-30 14:00 | N | Y | customer request | Line |  |  | Restricts Generation
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2016-08-30 08:00 | 2016-08-30 17:00 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 133S Stelco Edmonton | 2016-08-30 08:00 | 2016-08-31 10:00 | N | N | emergency switching and grounding to perform repairs | Station |  |  | Firm Load Loss
ALTALINK | 914s 701 (914s Bindloss) | 2016-08-30 08:00 | 2016-08-30 16:00 | N | N | breaker maintenance | Circuit Breaker |  | Breaker maintenance
ALTALINK | 356s 752 (356s Milo) | 2016-08-30 12:00 | 2016-08-30 17:00 | N | Y | re-position site glass on centre phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
WINDYPWPL | 112s CAP1 (112s Windy Point) | 2016-08-31 02:59 | 2017-03-31 16:00 | N | N | forced outage; blown capacitor | Shunts |  |  | Pre-Condition, For Information Only
EPCOR | 330p 1208 (330p Genesee) | 2016-08-31 07:00 | 2016-09-01 17:00 | N | Y | Doble | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds, 500 kV
ALTALINK | 1053L (132s Ware Junction - 324s Cassils) | 2016-08-31 07:30 | 2016-09-02 17:30 | N | Y | emergency damper replacements | Line |  |  | 240 kV, Pre-Condition
REDDEER | 209s T1 (209s Timberlands) | 2016-08-31 07:30 | 2016-08-31 16:30 | N | N | repair transformer bushing oil leak | Transformer |  |  | For Information Only
ALTALINK | 356s 852 (356s Milo) | 2016-08-31 08:00 | 2016-09-01 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 39.2TR (ENMAX 39) | 2016-08-31 08:00 | 2016-09-01 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ATCO | 6L06 (705s Kitscoty - 751s Hill) | 2016-08-31 08:00 | 2017-01-31 16:00 | N | N | crews working in close proximity to 6L06 | Line |  | CREWS WORKING IN CLOSE PROXIMITY TO 6L06 | For Information Only
ENMAX | 13.2TR (ENMAX 13) | 2016-08-31 08:00 | 2016-08-31 12:00 | N | N | remove Trojan oil processor | Transformer |  |  | For Information Only
ALTALINK, ATCO | 7L230 (69s North Barrhead - 7L230 tap),69s 230W (69s North Barrhead) | 2016-08-31 08:00 | 2016-08-31 17:00 | N | N | changing the relay settings back to normal | Circuit Breaker, Line |  |  | Pre-Condition, Overload
ENMAX, ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2016-08-31 09:00 | 2016-09-02 08:00 | N | Y | 1080L hi pot testing | Line |  |  | 240 kV, Pre-Condition
ENMAX | 20.3TR (ENMAX 20),ENMAX 21 B138-20.82 (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2016-09-01 08:00 | 2016-09-01 12:00 | N | N | fall substation washing | Circuit Breaker, Line, Transformer |  |  | Overload, Creates Radial Feeds
ALTALINK | 397s T2 (397s Benbow) | 2016-09-01 08:30 | 2016-09-01 14:00 | N | N | functional trip tests to breakers | Transformer |  |  | For Information Only
ATCO | A793s West Peace RTU/SCADA | 2016-09-01 09:00 | 2016-09-02 17:00 | N | N | commissioning for installing DG | Terminal Equipment |  | Commissioning for Customer is installing a DG and has requested this done to meet their deadline. | Affects Visibility
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2016-09-01 12:00 | 2016-09-01 16:00 | N | N | ENMAX maintenance (fall substation washing) | Line
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1),Enmax 1 MD138-8A9 (ENMAX 1) | 2016-09-01 12:00 | 2016-09-01 16:00 | N | N | fall substation washing | Switch, Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 55s T1 (55s Olds) | 2016-09-01 14:30 | 2016-09-01 17:00 | N | N | close Open Point 'A' | Transformer |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2016-09-03 08:00 | 2016-09-03 09:00 | N | N | fall Pothead Washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2016-09-03 09:00 | 2016-09-03 10:00 | N | N | fall Pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2016-09-03 10:00 | 2016-09-03 12:00 | N | N | fall Pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2016-09-03 12:00 | 2016-09-03 14:00 | N | N | fall Pothead washing | Line |  |  | Restricts Generation, Creates Radial Feeds
ENMAX, ALTALINK | 21.1TR (ENMAX 21),21.4TR (ENMAX 21),21.80L (42s Sarcee - ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2016-09-04 08:00 | 2016-09-11 16:00 | N | Y | replace switches, maintenance and fall sub washing | Line, Transformer |  | Replace SW 84, SW 85 & 21.4TR MD. 21.4TR (PRD, Transformer MTCE, Gas Relay, Doble), 138KV SW & MD MTCE. HV Breaker Inspection 21B69-21.4TR. Fall Substation Washing | Pre-Condition, Overload, Creates Radial Feeds
ATCO, CUPCAN | 850s 701T (850s Rainbow Cogen),850s 702T (850s Rainbow Cogen),791s 705 (791s Rainbow Lake) | 2016-09-05 07:00 | 2016-09-06 17:00 | N | Y | stage 1: Rainbow Husky load move project | Circuit Breaker, Transformer |  | Rainbow Husky Load move Project. RB4&RB5 unavailable on Sept 5th-6th, RB4 Unavailable for the duration of the outage. Install and commission breaker fail relays for new breaker 433. | Restricts Generation
CUPCAN, ATCO | 850s 702T (850s Rainbow Cogen),850s 443 (850s Rainbow Cogen) | 2016-09-05 07:00 | 2016-09-06 16:00 | N | N | test and operate 443, will be done in conjunction with COG 2-38556 | Circuit Breaker, Transformer |  | Test and Operate 443, will be done in conjunction with COG 2-38556 | Restricts Generation
ALTALINK | 71s 920W (71s Lamoureux) | 2016-09-06 07:00 | 2016-09-06 17:30 | N | Y | EPCOR CVT work @ Castle Downs | Switch |  |  | 240 kV
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2016-09-06 07:00 | 2016-09-06 17:00 | N | Y | doble | Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 805s J722 (805s Jasper) | 2016-09-06 07:00 | 2016-09-09 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2016-09-06 07:00 | 2016-10-11 17:00 | N | Y | bushing replacement | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2016-09-06 07:30 | 2016-09-19 17:00 | N | Y | rebuild 1083L | Line |  | Rebuild portion of 1083L from 63s That parallels 755L | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 332S Ellis | 2016-09-06 07:30 | 2016-11-30 17:30 | N | N | working outside LOA but in close proximity to switch 332s 40 | Station |  |  | For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2016-09-06 07:30 | 2016-09-08 17:30 | N | N | insulator washing | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK, REDDEER | 247s T1 (247s Piper Creek),755L (63s Red Deer - 247s Piper Creek),247s 427 (247s Piper Creek) | 2016-09-06 07:30 | 2016-09-10 14:30 | N | N | rebuild 755L/427L, rebuild and start 247s bus | Line, Circuit Breaker, Transformer |  |  | Creates Radial Feeds
ALTALINK | 1038L (138s Windy Flats - 237s Foothills) | 2016-09-06 07:30 | 2016-09-15 19:00 | N | Y | install bird diverters, replace spacer dampers | Line |  |  | 240 kV, Overload
Lethbridge, ALTALINK | 172L (370s North Lethbridge - 181s Chinook),463L (181s Chinook - 463L28) | 2016-09-06 08:00 | 2016-09-06 17:00 | N | Y | energize 181sT1 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 909L (310p Sundance - 665s Dome) | 2016-09-06 08:30 | 2016-09-06 19:30 | N | Y | urgent repair to 909L structure #156, which shares structure with 1045L | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 418L (20s Ghost - 418L193A) | 2016-09-06 08:45 | 2016-09-09 17:45 | N | N | clearance mitigation | Line |  |  | Pre-Condition
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2016-09-06 09:00 | 2016-09-07 10:00 | N | Y | L to J: hi pot testing | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 217s T7 (217s North Red Deer) | 2016-09-06 11:00 | 2016-09-08 17:05 | N | N | T7 bushings (25kV & 138kV) and adding supervisory controls to 217s289 | Transformer |  |  | For Information Only
ALTALINK | 392s T3 (392s Black Diamond),812L (392s Black Diamond - 812L tap) | 2016-09-06 12:15 | 2016-09-08 17:45 | N | N | maintenance, doble test and leak repair on transformer and voltage regulator | Line, Transformer |  |  | For Information Only
CUPCAN | 850s 701T (850s Rainbow Cogen) | 2016-09-07 07:00 | 2016-09-17 17:00 | N | Y | stage 2 Rainbow Husky load move project | Transformer |  | Stage 2; Sept. 7-17, 2016, RB4 Unavailable, RB5 Available. Isolation shrunk down to include RB4 and 701T. ATCO Electric to issue the COG to ATCO Power they will further isolate as required and issue a GOI to their workers. | Restricts Generation
EPCOR, ALTALINK | 909L (89s Ellerslie - 665s Dome),665s DDS13 (665s Dome) | 2016-09-07 07:00 | 2016-09-07 17:00 | N | Y | install new coupling | Switch, Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1054L (13s Deerland - 12s Heartland) | 2016-09-07 07:30 | 2016-09-08 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs),37s 83 (37s North Calder) | 2016-09-07 08:00 | 2016-09-08 17:30 | N | Y | repairing switch | Line, Switch |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 56S Boyle | 2016-09-07 08:00 | 2016-09-15 16:00 | N | N | Station upgrade, breaker/transformer additions. In service date: Sept 14, 2016 | Station
ALTALINK | 786L (799s Coleman - Natal),799s 786W (799s Coleman) | 2016-09-07 08:30 | 2016-09-07 17:30 | N | Y | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 840S McNeill Station | 2016-09-07 10:00 | 2016-09-07 16:00 | N | Y | emergency: fix the L2 comm to VBE fail | Station |  | We require the McNeill Convertor to Standby for a few hours to fix the L2 comm to VBE fail. | Limits ATC
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2016-09-07 10:00 | 2016-09-07 14:00 | N | N | bridge piling on RR 32 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2016-09-07 11:00 | 2016-09-09 08:00 | N | Y | L to J: 1003L high Pot testing | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 159s T1 (159s Colinton) | 2016-09-07 14:10 | 2016-09-13 15:00 | N | N | add new SS1, add 25kV PT at VT4, salvage old SS1 TX, add AMI feed, install Fortis U/G feed to 232L | Transformer |  |  | For Information Only
BCH | RAS3 - 786L RAS | 2016-09-07 17:00 | 2017-02-04 08:30 | N | N | forced outage | RAS |  |  | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo),56s Boyle 138kV Bus 1 | 2016-09-08 07:00 | 2016-09-15 12:00 | N | N | boyle upgrade project:close open points B, D, E, and F. relocate 56s633. | Bus, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 907L (77s Sagitawah - 122s Alberta Newsprint),122s 907N (122s Alberta Newsprint) | 2016-09-08 08:30 | 2016-09-08 12:30 | N | Y | topping up breaker with gas | Circuit Breaker, Line |  |  | 240 kV, Restricts Generation, Firm Load Loss
ALTALINK | 668L (394s Empress - 562s Cypress),669L (163s Amoco Empress - 562s Cypress) | 2016-09-08 09:00 | 2016-09-08 15:00 | N | N | 562s Telecom - TPR: replace defective MPLS card | Line
ALTALINK | 122S Alberta Newsprint | 2016-09-08 10:00 | 2016-09-08 14:00 | N | Y | maintenance | Station |  |  | Restricts Generation, For Information Only
ATCO | 9L80 (757s Battle River - 755s Cordel) | 2016-09-08 11:00 | 2016-09-08 12:00 | N | Y | software upgrade to the Battle River to Cordel eclipse radio link firmware | Line |  | Software Upgrade to the Battle River to Cordel Eclipse radio link firmware. Switching Only, coordinate with Comm techs to remove line prior to upgrading radios - see CSP 2-38661 | 240 kV, Pre-Condition, Overload
ALTALINK | 217s T7 (217s North Red Deer) | 2016-09-08 17:01 | 2016-09-15 18:00 | N | N | T7 LAs, T7 oil reclaim full metering upgrade | Transformer |  |  | For Information Only
EPCOR | 330p 801 (330p Genesee),330P SST3 (330P Genesee) | 2016-09-09 07:00 | 2016-09-18 17:00 | N | N | protection upgrade | Circuit Breaker, Transformer |  | 801 BKR & SST3 @ Genesee - Protection Upgrade | For Information Only
ALTALINK | 604L (149s Nisku - 155s Blackmud) | 2016-09-09 07:30 | 2016-09-09 17:30 | N | N | insulator washing | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 942L (681s Bannerman - 71s Lamoureux) | 2016-09-09 07:30 | 2016-09-10 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),72CK12 (987s Clover Bar - Kennedale),72CK13 (987s Clover Bar - Kennedale),987S Clover Bar 72 kV Bus 3,987S Clover Bar 72 kV Bus 4 | 2016-09-09 22:00 | 2016-09-11 18:00 | N | N | multiple projects | Bus, Line |  | Bus 3&4 @ Cloverbar - Multiple projects | Restricts Generation, Creates Radial Feeds
ATCO | 716s 701 (716s Lloydminster),7L749 (716s Lloydminister - 7L749D2) | 2016-09-10 07:00 | 2016-09-11 19:00 | N | Y | install poles for line mitigation | Line, Circuit Breaker |  | Install poles for Line mitigation, these structures cannot be done with a HOP | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 214s T1 (214s Innisfail),80L (63s Red Deer - 214s Innisfail),63s 80X (63s Red Deer) | 2016-09-10 07:15 | 2016-09-11 17:45 | N | N | install foundations for 419L under 214s 138kV bus 1 | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 807L (233s Beamer - 807L tap),807L (410s Josephburg - 402s Scotford Expansion) | 2016-09-10 07:30 | 2016-09-11 17:30 | N | N | damper replacements | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2016-09-10 08:00 | 2016-09-10 20:00 | N | N | 69kV switch maintenance. 69kV PT doble. Fall substation washing | Line, Transformer |  |  | Pre-Condition
ALTALINK, REDDEER | 247s T2 (247s Piper Creek),755L (535s Joffre - 247s Piper Creek),535s Joffre 138kV Bus 4,535s C1 (535s Joffre) | 2016-09-10 14:45 | 2016-09-12 17:45 | N | N | cut 755L out of 535s and start rebuild, complete 247s bus differential replacement | Line, Bus, Shunts, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 1061L (12s Heartland - 681s Bannerman) | 2016-09-11 07:30 | 2016-09-14 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen),166s 899N (166s Dow Chem Fort Saskatchewan) | 2016-09-11 07:30 | 2016-09-12 12:30 | N | N | replace SS1 transformer | Line, Circuit Breaker |  |  | Restricts Generation
ATCO | 878s 701T (878s Kidney Lake),7L94 (878s Kidney Lake - 827s Cranberry Lake) | 2016-09-11 12:15 | 2016-09-11 16:00 | N | N | maintenance on 878s 701T/701TCS | Line, Transformer |  | Major Maintenance on 701T/701TCS, 878S KIDNEY LK OOS, customer outage reqd | Firm Load Loss
EPCOR | 803s T3 (803s Lambton) | 2016-09-12 07:00 | 2016-10-01 17:00 | N | Y | oil reclamation | Transformer |  |  | 240 kV, Overload
EPCOR | Woodcroft W722 (Woodcroft) | 2016-09-12 07:00 | 2016-09-16 15:00 | N | N | cutover of new BF/Sync check relay to W722 breaker | Circuit Breaker |  |  | For Information Only
ALTALINK | 33s6 (33s Spray) | 2016-09-12 07:00 | 2016-09-16 18:00 | N | Y | PT-CT replacement | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 214s T2 (214s Innisfail),80L (214s Innisfail - 55s Olds),55s 80N (55s Olds) | 2016-09-12 07:15 | 2016-09-13 17:45 | N | N | install foundations for 419L under 138kV bus 2 | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs),557s 2403 (557s Castle Downs),557s 2401 (557s Castle Downs) | 2016-09-12 07:30 | 2016-09-12 17:00 | N | Y | repair disconnect CDDS13 | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
REDDEER | 217s T1 (217s North Red Deer) | 2016-09-12 07:30 | 2016-09-13 17:00 | N | N | maintain gang switch 14-T1-2 | Transformer |  | maintain gang switch 14-T1-2 by dismantling the switch, clean, apply new grease and reassemble/adjust the switch | For Information Only
ALTALINK | 739L (14s Devon - 305s Acheson) | 2016-09-12 07:30 | 2016-09-12 17:30 | N | N | insulator washing | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28) | 2016-09-12 08:00 | 2016-10-09 10:00 | N | Y | (SWCRR)-Allteck 28.80 OOS #1 Aug 16  23rd for Cable pulling and training / racking. Relay settings and testing required. Altalink required to install an remove grounds on bottom of line side switches at 42s for Valard | Line |  | (SWCRR)-Allteck 28.80 OOS #1 Aug 16  23rd for Cable pulling and training / racking. Relay settings and testing required. Altalink required to install an remove grounds on bottom of line side switches at 42s for Valard. Altalink required to remove grounds on bottom of line side switches at 42s for Valard. Switching and phasing required. Start of 24hr soak. 28.80L to carry load Oct 9th 12pm. | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 420s T2 (420s Broadmoor) | 2016-09-12 08:00 | 2016-09-20 07:59 | N | N | bring Fortis U/G cables into station & connect to new switchgear building | Transformer |  |  | For Information Only
ENMAX | 1.5TR | 2016-09-12 08:00 | 2016-09-16 16:00 | N | N | PRD install & LTC maintenance | Terminal Equipment |  |  | For Information Only
ALTALINK | 257s Hull RTU/SCADA | 2016-09-12 08:00 | 2016-09-14 17:00 | N | N | repair communication issue with the RTU | Terminal Equipment |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2016-09-12 08:30 | 2016-09-15 17:00 | Y | Y | emergency line repair | Line |  |  | Pre-Condition, Limits ATC, Creates Radial Feeds, 500 kV
ALTALINK | 418L (20s Ghost - 418L193A) | 2016-09-12 08:45 | 2016-09-16 17:45 | N | N | clearance mitigation | Line |  |  | Pre-Condition
ATCO | 729s 701T (729s Otauwau) | 2016-09-12 09:00 | 2016-09-16 16:00 | N | N | oil Reclaim on 701T @ 729S | Transformer |  | Oil Reclaim on 701T @ 729S | For Information Only
ATCO | 801s 901T (801s Anderson) | 2016-09-12 09:00 | 2016-09-16 16:00 | N | Y | 901T major maintenance required | Transformer |  | 901T Major Maintenance required | Firm Load Loss, Creates Radial Feeds
ATCO | 791s 456 (791s Rainbow Lake),791s 462 (791s Rainbow Lake) | 2016-09-12 09:00 | 2016-12-27 13:00 | N | Y | ATCO Power work | Circuit Breaker |  | COG for ATCO Power Work | Restricts Generation, For Information Only
ALTALINK | 102s SVC (102s Langdon) | 2016-09-12 09:45 | 2016-09-12 16:15 | N | Y | weed spraying in SVC fenced area | Shunts |  |  | 240 kV
ATCO | 845s 705C (845s Big Mountain),845s 705 (845s Big Mountain) | 2016-09-12 10:00 | 2016-09-12 16:00 | N | N | 845s 705 breaker sf6 hpl partial testing | Circuit Breaker, Shunts |  | 845S 705 BREAKER SF6 HPL PARTIAL TESTING 705C Capacitor out of service | Over/Under Voltage
ALTALINK | 320p 152 (320p Keephills),320p 252 (320p Keephills) | 2016-09-12 10:00 | 2016-10-05 11:37 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 28s T1 (28s West Brooks) | 2016-09-12 11:30 | 2016-09-15 17:00 | N | Y | maintenance and doble on transformer | Transformer |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 266s 1038L FSC (266s SC1) | 2016-09-12 12:15 | 2016-09-14 12:45 | N | Y | FSC2 maintenance | Shunts |  |  | 240 kV
ALTALINK, REDDEER | 247s T2 (247s Piper Creek),755L (535s Joffre - 247s Piper Creek) | 2016-09-12 17:15 | 2016-09-14 17:45 | N | N | rebuild 755L, complete 247s bus differential replacement | Line, Transformer |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK, ATCO | 409s T1 (409s Shell Scotford),857L (409s Shell Scotford - 410s Josephburg),ALC02L (409s Shell Scotford - 879s Scotford Upgrader),409s Shell Scotford 138 kV Bus 2,409s T3 (409s Shell Scotford) | 2016-09-13 07:15 | 2016-09-22 17:45 | N | Y | replace T1 bushings and LA's, replace 409s6, 409s8 & 409s10 switches, replace 409s12 PTs, replace T1 protections, 138kV Bus insulator replacements | Line, Bus, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen) | 2016-09-13 07:30 | 2016-09-15 17:30 | N | Y | move TPR channel to MPLS system and perform trip tests | Line |  | Move TPR channel to MPLS system and perform trip tests to confirm functionality. Coordinated with customer shutdown. Associated redundant protections will be taken out of service 1 at a time. | Restricts Generation
ALTALINK | 739L (14s Devon - 155s Blackmud),14s 739E (14s Devon) | 2016-09-13 07:30 | 2016-09-15 17:30 | N | N | insulator washing | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 299S Kingman,301S Queensland,732AL (301s Queensland - 732L2),732L (299s Kingman - 732L2) | 2016-09-13 07:30 | 2016-09-14 18:00 | N | N | transformer and switch maintenance | Station, Line |  | 299s and 301s Stations (732L and 732AL) - transformer and switch maintenance | Firm Load Loss
ALTALINK | 1116L (170s Pike - 167s Ipiatik Lake),170s1116 (170 Pike),167s1116 (167s Ipiatik Lake) | 2016-09-13 07:30 | 2016-09-14 17:00 | N | Y | clean and cold galvanize outboard arms at structures 24, 26, and 28 | Switch, Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 925s 902T (925s Green Stocking) | 2016-09-13 08:00 | 2016-09-13 17:00 | N | Y | urgent repair of faulty close circuit on breaker 502 | Transformer |  |  | 240 kV
ALTALINK | 427L (63s Red Deer - 247s Piper Creek) | 2016-09-13 08:00 | 2016-09-16 16:00 | N | N | In-service-date is Sep 15, 2016. 755L (63s Red Deer - 247s Piper Creek) is salvaged and renamed to 427L. | Line
ATCO | 707s 505C (707s St. Paul) | 2016-09-13 08:30 | 2016-09-13 15:30 | N | N | breaker maintenance | Shunts |  | Breaker 505 maintenance, 505C will be out of service for the duration of the work | For Information Only
ATCO | 845s 707 (845s Big Mountain) | 2016-09-13 09:00 | 2016-09-13 16:00 | N | Y | 845S 707 breaker SF6 LTB145D1/B partial testing, 144 KV ring open | Circuit Breaker |  | 845S 707 BREAKER SF6 LTB145D1/B PARTIAL TESTING 144 KV Ring open | Pre-Condition, Contingency Requires Mitigation
ATCO | 786s 505C (786s High Level),786s 506C (786s High Level),786s 701T (786s High Level),786s High Level 25kV Bus 500BS2 | 2016-09-13 10:00 | 2016-09-13 16:30 | N | N | bird proofing installation | Transformer, Bus, Shunts |  | 786S 25kV 500BS2 Bird Proofing Installation Transmission Hot Line Crew will be installing bird mitigation material on 500BS2 Station Fed from 500BS1 CAPACITORS 505C AND 506C WILL BE OOS FOR THE DURATION OF THE WORK -------- Load Transfer -------- 786S 5L276 Peak Load = 1.3 MVA 786S 5L143 Peak Load = 3.1 MVA 786S 5L134 Peak Load = 2.0 MVA 786S 5L276 Relay Settings: SEL RELAY 10.39 MVA 786S 5L143 Relay Settings: SEL RELAY 10.39 MVA 786S 5L134 Relay Settings: SEL RELAY 9.87 MVA -------- Load Transfer -------- | For Information Only
ATCO | 749s 702T (749s Flyingshot Lake) | 2016-09-13 10:00 | 2016-09-14 16:00 | N | N | test transformer | Transformer |  | Test transformer, all load to 701T | For Information Only
ALTALINK | 510s 3852 (510s Sunnybrook),510s 4052 (510s Sunnybrook) | 2016-09-13 13:00 | 2016-09-13 14:00 | N | N | HVDC crew requires an open breaker | Circuit Breaker |  |  | For Information Only
ALTALINK | 510s Sunnybrook 500kV B Bus,510s ACF22 (510s Sunnybrook),510s ACF21 (510s Sunnybrook) | 2016-09-14 08:00 | 2016-10-01 12:00 | N | Y | switch adjustments to help eliminate corona | Bus, Shunts |  | 510s 500kV 'B' Bus and AC Filter Bank #2 - Switch adjustments to help eliminate corona | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 216s T1 (216s Knightsbridge) | 2016-09-14 08:00 | 2016-09-14 22:00 | N | N | customer to perform maintenance | Transformer |  |  | For Information Only
ATCO | 786s 507C (786s High Level),786s 508C (786s High Level),786s 702T (786s High Level),786s High Level 25kV Bus 500BS1 | 2016-09-14 08:30 | 2016-09-14 16:30 | N | N | install bird mitigation material | Transformer, Shunts, Bus |  | Install Bird Mitigation Material on 500BS1, Station fed from 701T. Capacitors 507C and 508C will be unavailable for the duration of the work -------- Load Transfer -------- 786S 5L363 Peak Load = 8.5 MVA 786S 5L134 Peak Load = 2.0 MVA 786S 5L143 Peak Load = 3.0 MVA 786S 5L363 Relay Settings: 12.99 MVA 786S 5L134 Relay Settings: 9.87 MVA 786S 5L143 Relay Settings:10.39 MVA Alt settings required -------- Load Transfer -------- | For Information Only
ATCO | 707s 506C (707s St. Paul) | 2016-09-14 08:30 | 2016-09-14 15:30 | N | N | breaker maintenance | Shunts |  | Breaker 506 maintenance, 506C will be out of service for the duration of the work | For Information Only
ATCO | 845s 708 (845s Big Mountain) | 2016-09-14 09:00 | 2016-09-14 16:00 | N | Y | 845S 708 breaker SF6 HPL partial testing 144 KV ring open | Circuit Breaker |  | 845S 708 BREAKER SF6 HPL PARTIAL TESTING 144 KV Ring open | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2016-09-14 09:30 | 2016-09-14 14:30 | N | N | bridge piling on RR 32 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 266s 1037L FSC (266s SC1) | 2016-09-14 11:15 | 2016-09-15 17:45 | N | Y | FSC1 maintenance | Shunts |  |  | For Information Only
ALTALINK | 755L (535s Joffre - 247s Piper Creek) | 2016-09-14 17:46 | 2017-02-27 17:00 | N | N | complete 755L rebuild | Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 5.9TR (ENMAX 5),5.10TR (ENMAX 5),2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2016-09-14 23:59 | 2016-09-15 06:00 | N | N | fall substation washing | Line, Transformer |  | 2.83L. 5.9TR. 5.10TR - Fall Substation Washing. All of 2.83L out of service, wash up to SW81 at 13 Sub as well (if required) | For Information Only
REDDEER | 247s T1 (247s Piper Creek) | 2016-09-15 07:30 | 2016-09-15 16:30 | N | N | replace existing 17T1 revenue meter with backup revenue meter having a 2020 seal | Transformer |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34) | 2016-09-15 08:00 | 2016-09-15 16:00 | N | N | install trojan oil processor | Transformer |  |  | For Information Only
ATCO | 845s 709 (845s Big Mountain) | 2016-09-15 09:00 | 2016-09-15 16:00 | N | Y | 845S 709 breaker SF6 HPL partial testing 144 KV ring open | Circuit Breaker |  | 845S 709 BREAKER SF6 HPL PARTIAL TESTING 144 KV Ring open | Pre-Condition, Contingency Requires Mitigation
ATCO | 813s 501R (813s Little Smoky),813s 901T (813s Little Smoky) | 2016-09-15 09:00 | 2016-09-15 16:00 | N | Y | investigate ground fault on gas detector circuit | Transformer, Shunts |  | Urgent work - Investigate ground fault on Gas detector circuit, all load onto 902T, 501R 20 MVAR cap OOS and unavailable for V dispatch, 240kV and 144kV rings will be opened momentarily during isolation switching and again during RTN switching | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 728L (405s Waupisoo - 353s Plamondon) | 2016-09-15 12:01 | 2016-09-15 19:00 | N | N | 472s mobile install | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 56s 652 (56s Boyle) | 2016-09-15 19:01 | 2016-09-16 06:59 | N | N | 56s Boyle does not have bus protection. Expected in service on Sep 19 | Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 56s C1 (56s Boyle),56s T2 (56s Boyle),710L (159s Colinton - 56s Boyle),56s 710X (56s Boyle) | 2016-09-16 07:00 | 2016-09-19 17:00 | N | N | 56s Boyle upgrade project: trip test breakers and tie in breaker fails | Line, Shunts, Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ATCO | 9L46 (932s Pemukan - 959s Lanfine) | 2016-09-16 10:00 | 2016-09-16 13:00 | N | Y | emergency repair OPGW | Line |  | Description of activity: Temporarily secure a severely damaged OPGW (optical fiber composite overhead ground wire) until a permanent repair can be completed. Last week we made an attempt to install some repair rods under a Hold Off (Reclose Block) but the damage was too severe for that. We are going to install some preform dead ends on either side of the damage and take up the tension with a chain hoist. That should keep the tension without a fear of a complete failure on the OPGW | 240 kV
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2016-09-17 07:00 | 2016-09-17 10:00 | N | N | substation washing | Line, Transformer |  |  | Overload, Contingency Requires Mitigation
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2016-09-17 10:00 | 2016-09-17 14:00 | N | N | substation washing | Line, Transformer |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2016-09-18 08:00 | 2016-09-18 16:00 | N | N | substation and line washing | Line, Transformer |  |  | For Information Only
EPCOR | Woodcroft W721 (Woodcroft) | 2016-09-19 07:00 | 2016-09-25 17:00 | N | N | cutover of new BF/Sync Check Relay to W721 breaker | Circuit Breaker |  |  | For Information Only
EPCOR | 330p 808 (330p Genesee) | 2016-09-19 07:00 | 2016-09-24 17:00 | N | N | protection upgrade | Circuit Breaker |  |  | For Information Only
ATCO | 848s 606T (848s Ruth Lake),848s 605 (848s Ruth Lake),848s 606 (848s Ruth Lake) | 2016-09-19 07:00 | 2016-09-30 17:00 | N | N | modify and commission 606T transformer | Transformer, Circuit Breaker |  | Modify and commission 606T transformer, bus and 25 kv protection, 25kV load will be offloaded to adjacent sub and/or to 605T, 72kV ring bus will be open between 605A and 606A. | For Information Only
ALTALINK | 305s T1 (305s Acheson) | 2016-09-19 07:15 | 2016-09-28 14:00 | N | N | replacing transformer 'A' protection | Transformer |  |  | For Information Only
ALTALINK | 38s T3 (38s East Edmonton) | 2016-09-19 07:15 | 2016-09-26 08:45 | N | N | cut over feed from T3 from existing 25kV bay to new switchgear building energize new 25kV breakers | Transformer |  | Requested by: Mike Des Roches Contact #: (403) 554-2068 Issue to: Kyle Black @ RET Contact #: (403) 369-4696 | For Information Only
ALTALINK | 739L (14s Devon - 155s Blackmud),14s 739E (14s Devon) | 2016-09-19 07:30 | 2016-09-20 17:30 | N | N | insulator washing | Line, Circuit Breaker |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 676L (523s Bullshead - 244s Bowmanton) | 2016-09-19 07:30 | 2016-10-19 07:30 | N | N | to allow to install ground and keep working on 676L between these open points under a GOI | Line |  | MED 676L( Open Point 'C' - Open Point 'M) - To allow to install ground and keep working on 676L between these open points under a GOI. | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2016-09-19 08:00 | 2016-09-20 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 33.2TR (ENMAX 33) | 2016-09-19 08:00 | 2016-09-27 16:00 | N | N | HV bushing replacement and transformer differential CT addition | Transformer |  |  | For Information Only
ALTALINK | 244s 3152 (244s Bowmanton),244s 69 (244s Bowmanton) | 2016-09-19 08:00 | 2016-11-10 08:30 | N | N | close open point 'G' | Circuit Breaker, Switch |  |  | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2016-09-19 08:00 | 2016-09-19 16:00 | N | N | fall line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 43.1TR (ENMAX 43),9.83L (ENMAX 43 - ENMAX 9) | 2016-09-19 08:00 | 2016-09-19 12:00 | N | N | replace CAC/OAC relays for new RTU | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1-T2 (29EDD-1 Millennium),29EDD-1 Millennium 72 kV North Bus | 2016-09-19 08:00 | 2016-09-23 20:00 | N | Y | maintenance | Bus, Transformer |  | T2, Replace Dissolved Gas Monitor (WW) T2, Replace Conservator Level Gauge(ISO) 29CVT-15 oil level gauge 29EDD1s18 Replace Sw. Mechanism (ISO) | 240 kV, For Information Only
ALTALINK | 418L (20s Ghost - 418L193A) | 2016-09-19 08:45 | 2016-09-21 17:45 | N | N | clearance mitigation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 770s 701T (770s Three Hills) | 2016-09-19 09:00 | 2016-09-20 16:00 | N | N | install bird proofing in 25kV 500BS1 | Transformer |  | Install bird proofing in 25kV 500BS1. -------- Load Transfer -------- 770S 5L278 Peak Load = 3.4 MVA 770S 5L513 Peak Load = 3.0 MVA 770S 5L170 Peak Load = 2.0 MVA 770S 5L278 Relay Settings:13.8 MVA (C09) 770S 5L513 Relay Settings:13.86 MVA (C09) 770S 5L170 Relay Settings:13.8 MVA (C09) -------- Load Transfer -------- | For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2016-09-19 09:30 | 2016-10-28 17:30 | N | Y | line maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 845s 710 (845s Big Mountain) | 2016-09-19 10:00 | 2016-09-19 16:00 | N | Y | 845S 710 breaker SF6 HPL partial testing | Circuit Breaker |  | 845S 710 BREAKER SF6 HPL PARTIAL TESTING 144 KV Ring open | Contingency Requires Mitigation
ALTALINK | 74s T1 (74s Janet) | 2016-09-19 10:30 | 2016-09-29 17:30 | N | Y | transformer maintenance, doble, repair oil leaks and repair buck/boost dials | Transformer |  |  | Contingency Requires Mitigation
ATCO | 741s 701T (741s Fox Creek),741s 703 (741s Fox Creek) | 2016-09-19 11:00 | 2016-10-03 18:00 | N | N | 741S 703 breaker testing and maintenance | Circuit Breaker, Transformer |  | 741S 703 BREAKER MIN OIL HLD PARTIAL TESTING 703 partial main, 701T oil leak | For Information Only
ALTALINK | 377s 473C102 (377s Hardisty) | 2016-09-19 11:30 | 2016-09-20 17:30 | N | N | capacitor bank maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 43.2TR (ENMAX 43),33.84L (ENMAX 43 - ENMAX 33) | 2016-09-19 12:00 | 2016-09-19 16:00 | N | N | replace CAC/OAC relays for new RTU | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2016-09-19 12:30 | 2016-09-20 17:30 | N | N | 138kV breaker maintenance | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2016-09-19 12:30 | 2016-09-21 17:30 | N | N | 184sT1 138kV bushing replacement and bushing monitor pre-wire | Transformer |  |  | For Information Only
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39),ENMAX 39 SW83 (ENMAX 39) | 2016-09-19 22:00 | 2016-09-20 01:00 | N | Y | fall substation washing | Line, Switch, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39),ENMAX 39 SW84 (ENMAX 39) | 2016-09-20 01:00 | 2016-09-20 04:00 | N | Y | fall substation washing | Line, Transformer, Switch | 2. Studied with CEC generation = 350 MW and Balzac = 80 MW |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2016-09-20 04:00 | 2016-09-20 07:00 | N | Y | fall substation washing | Line, Circuit Breaker |  |  | For Information Only
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2016-09-20 06:00 | 2016-09-21 17:00 | N | N | tower refurbishment | Line |  |  | For Information Only
EPCOR | At-Plastics-4Rs | 2016-09-20 06:00 | 2016-09-22 16:00 | N | N | plant shutdown | Station |  |  | For Information Only
EPCOR | Woodcroft WDS1 (Woodcroft) | 2016-09-20 07:00 | 2016-09-20 17:00 | N | N | disconnect repair | Switch |  |  | For Information Only
ALTALINK | 353s T1 (353s Plamondon),728L (353s Plamondon - 157s Lac La Biche),353s 138 kV Bus 1 (353s Plamondon) | 2016-09-20 07:00 | 2016-09-30 17:00 | N | N | install new MOD and mobilize new xmer in place | Line, Transformer, Bus |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 437s T1 (437s Baymag),437s T2 (437s Baymag) | 2016-09-20 07:15 | 2016-09-20 17:15 | N | N | customer requested outage for annual maintenance | Transformer |  |  | For Information Only
ALTALINK | 818s C2 (818s Winefred),818s 17 (818s Winefred) | 2016-09-20 08:00 | 2016-09-20 13:00 | N | N | disassemble the latch, replace the spring and spring motor. | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 191s T2 (191s N.W.Cardiff) | 2016-09-20 08:15 | 2016-09-20 17:45 | N | N | TX Doble, bushing leak investigation/repair | Transformer |  |  | For Information Only
ALTALINK | 48s Pocaterra RTU/SCADA,49s Interlakes RTU/SCADA | 2016-09-20 09:00 | 2016-09-20 12:00 | N | N | satellite install, backup comms for SCADA during 777L rebuild | Terminal Equipment |  |  | For Information Only
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare),790s 703 (790s Poplar Hill) | 2016-09-20 10:00 | 2016-09-20 16:00 | N | N | 703 breaker SF6 top up breaker gas pressure | Line, Circuit Breaker |  | 703 BREAKER SF6 Top up breaker gas pressure | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 720s 900D1 (720s Wabasca) | 2016-09-20 10:00 | 2016-09-20 12:00 | N | Y | repair motor drive on 900D1 @ 720S Wabasca | Switch |  | Repair Motor Drive on 900D1 @ 720S Wabasca, decouple 900D1 during repairs, operate switch after repairs Breakers 901 and 902 be closed during T&O permit Switch is good condition, just need to replace the damaged motor and operate to confirm. | 240 kV, For Information Only
ALTALINK | 510S Sunnybrook,511s Crossing,1238L (510s Sunnybrook - 330p Genesee),1325L (510s Sunnybrook - 511s Crossings) | 2016-09-20 12:00 | 2016-10-01 09:00 | N | Y | valve reactor replacement and project deficiencies | Line, Station |  |  | 500 kV
ALTALINK | 818s C3 (818s Winefred),818s 41 (818s Winefred) | 2016-09-20 12:30 | 2016-09-20 17:30 | N | N | disassemble the latch, replace the spring and spring motor. | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36) | 2016-09-20 22:00 | 2016-09-21 02:00 | N | Y | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36),36.5TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2016-09-21 02:00 | 2016-09-21 06:00 | N | N | fall substation washing | Line, Transformer |  |  | For Information Only
ALTALINK | 51s T3 (51s Wainwright) | 2016-09-21 07:15 | 2016-09-21 17:45 | N | N | maintenance | Transformer |  |  | For Information Only
ATCO | 770s 703T (770s Three Hills) | 2016-09-21 08:00 | 2016-09-22 16:00 | N | N | install bird proofing in 25kV 500BS2. | Transformer |  | Install bird proofing in 25kV 500BS2. -------- Load Transfer -------- 770S 5L349 Peak Load = 3.5 MVA 770S 5L170 Peak Load = 2.0 MVA 770S 5L350 Peak Load = 3.6 MVA 770S 5L278 Peak Load = 3.4 MVA 770S 5L349 Relay Settings:13.8 MVA (C09) 770S 5L170 Relay Settings:13.8 MVA (C09) 770S 5L350 Relay Settings:12.1 MVA (SEL) 770S 5L278 Relay Settings:13.8 MVA (C09) -------- Load Transfer -------- | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2016-09-21 08:00 | 2016-09-22 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 818s C1 (818s Winefred),818s 14 (818s Winefred) | 2016-09-21 08:00 | 2016-09-21 14:30 | N | N | disassemble the latch, replace the spring and spring motor | Shunts, Circuit Breaker |  |  | For Information Only
ATCO | 7L69 (815s Goodfare - 731s Elmworth),815s 704 (815s Goodfare) | 2016-09-21 10:00 | 2016-09-21 16:00 | N | N | partial breaker maintenance | Line, Circuit Breaker |  | Partial main | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 353s Plamondon RTU/SCADA | 2016-09-21 10:30 | 2016-09-21 11:30 | N | N | download new RTU configuration in to the RTU | Terminal Equipment |  |  | Affects Visibility
ALPAC | 282s Grassland (Alpac) RTU/SCADA | 2016-09-21 20:00 | 2016-09-22 06:00 | N | N | update software for RTUat 282s | Terminal Equipment |  |  | Affects Visibility
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2016-09-21 20:00 | 2016-09-22 01:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11),11.83L (162s Beddington - ENMAX 11),162s 138-RB85 (162s Beddington),162s 138-RB84 (162s Beddington) | 2016-09-22 01:00 | 2016-09-22 05:30 | N | Y | fall substation washing | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2016-09-22 07:30 | 2016-09-22 17:30 | N | N | install new pile at base of 705L support structure. Mount PT on pile | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2016-09-22 10:00 | 2016-09-22 16:00 | N | N | bridge piling on RR 32 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 749s 705 (749s Flyingshot Lake) | 2016-09-22 10:00 | 2016-09-22 16:00 | N | N | breaker SF6 HPL partial test | Circuit Breaker |  | 749S 705 BREAKER SF6 HPL PARTIAL TESTING 144KV ring open | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 421s T1 (421s Hays) | 2016-09-22 13:15 | 2016-09-23 15:45 | N | N | warranty repair work | Transformer
ALTALINK | 244s 3152 (244s Bowmanton),244s 3252 (244s Bowmanton) | 2016-09-22 14:00 | 2016-11-18 08:30 | N | N | to allow crew to install grounds and keep working on 879L between 244s and open point "L" | Circuit Breaker |  | To allow crew to install grounds and keep working on 879L between 244s and open point "L" under a GOI | For Information Only
ATCO, ALTALINK | 409s T2 (409s Shell Scotford),856L (409s Shell Scotford - 410s Josephburg),ALC01L (409s Shell Scotford - 408s Air Liquide Scotford),409s 20 (409s Shell Scotford) | 2016-09-23 07:15 | 2016-10-04 08:00 | N | Y | replace switches, CVT. T2 'S" protection and 138kV insulator replacements. | Line, Transformer, Circuit Breaker |  | Replace 409s4, 409s5, 409s9 switches, replace 409s11 CVTs, replace T2 'S' protection, 138kV insulator replacements | Pre-Condition, Creates Radial Feeds
ENMAX | 26.1TR (ENMAX 26),26.81L (ENMAX 54 - ENMAX 26) | 2016-09-23 08:00 | 2016-09-23 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 263s C1 (263s Strachan),263s 35 (263s Strachan) | 2016-09-23 08:30 | 2016-09-23 11:30 | N | N | cap bank weed spraying | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 409s T3 (409s Shell Scotford) | 2016-09-23 09:30 | 2016-09-29 17:30 | N | N | Shell request for isolation on T3 to allow them to work on their switchgear | Transformer |  |  | For Information Only
TRANSALTA, ALTALINK | 59s T1 (59s Peigan),1049L (59s Peigan - 138s Windy Flats),59s Peigan 240kV Bus 1 | 2016-09-24 07:00 | 2016-09-24 17:00 | N | Y | remove 911L slack span in preparation to salvage remainder of line | Bus, Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2016-09-24 08:00 | 2016-09-24 12:00 | N | N | fall substation washing | Line, Transformer |  |  | For Information Only
ALTALINK | 1043L (320p Keephills - 816s Petrolia) | 2016-09-24 08:00 | 2016-09-30 16:00 | N | N | In service date: Sept 28, 2016. | Line
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),32.83L (ENMAX 32 - ENMAX 40) | 2016-09-24 12:00 | 2016-09-24 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38) | 2016-09-25 08:00 | 2016-09-25 12:00 | N | N | fall substation washing | Line, Transformer, Shunts | 2. Studied with CEC = 0 MW and Balzac = 0 MW (refer to Internal Comment 1). 1. Higher generation at CEC or Balzac may alleviate amount of overloads for next contingency. |  | Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2016-09-25 12:00 | 2016-09-25 16:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Creates Radial Feeds
EPCOR | Kennedale T1 (Kennedale) | 2016-09-26 06:00 | 2016-10-01 17:00 | N | N | PRV install | Transformer |  |  | Firm Load Loss, For Information Only
ALTALINK | 41s T11 (41s Medicine Hat) | 2016-09-26 07:00 | 2016-10-04 18:00 | N | Y | maintenance | Transformer |  |  | Pre-Condition
EPCOR | 816s P2403 (816s Petrolia),816s P2404 (816s Petrolia) | 2016-09-26 07:00 | 2016-09-29 17:00 | N | Y | op-checks to P2403 and P2404 breaker as part of 1043L energization after termination to Keephills | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 776s 601T (776s Richdale) | 2016-09-26 07:00 | 2016-12-02 17:00 | N | N | replace 601T, station service and upgrade protection | Transformer |  | Replace 601T, Station Service and upgrade protection. Sep 23 - Offload 776s 25kV to 801s Sep 26 - 6L09 will be opened between D2 and D3, then 776s sub taps removed Sep 26 - shrink GOI to jumper J1, then return 6L09 to normal Sep 26-Nov 11 - Construction Nov 11 - expand GOI to 6L09D2 & D3, close jumper J1, restore 6L09 to normal Nov 11-14 - Soak new 601T, 501VR Nov 14 - return 25kV load from 801s to 776s | Pre-Condition, For Information Only
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2016-09-26 07:00 | 2016-09-30 17:00 | N | N | close open points A, B, C | Line |  |  | Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.3TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2016-09-26 07:00 | 2016-09-26 11:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Pre-Condition, Creates Radial Feeds
SUNCOR | 29PL9-16 (29EDD-1 Millennium - 29EDD-94 Voyageur) | 2016-09-26 08:00 | 2016-10-03 20:00 | N | Y | maintenance | Line |  | 5YR PM 952-101 CT-952-101A/B/C 29PS-406 29PS-405 CT-952-102A/B/C 952-102 29PLA-108A/B/C 29PT-418A/B/C 29PL9-16 and associated equipment | 240 kV, Creates Radial Feeds
ENMAX | 26.2TR (ENMAX 26) | 2016-09-26 08:00 | 2016-09-27 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 511s ACF12 (511s Crossings),511s SVC Plus (511s Crossings),511s ACF13 (511s Crossings),511s ACF11 (511s Crossings) | 2016-09-26 08:00 | 2016-09-30 17:00 | N | Y | update software in SVC plus HMI, check covers on AC filters and breaker fail settings upgrades | Shunts |  |  | For Information Only
ALTALINK | 511s ACF22 (511s Crossings),511s ACF21 (511s Crossings) | 2016-09-26 08:00 | 2016-09-29 17:00 | N | Y | check covers on AC filters and breaker fail settings upgrades | Shunts |  |  | For Information Only
VISIONREQ | 354s DVAR1 (354s Summerview),354s DVAR2 (354s Summerview) | 2016-09-26 08:00 | 2016-10-15 16:00 | N | Y | DVAR maintenance | Shunts |  |  | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2016-09-26 08:00 | 2016-09-30 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2016-09-26 09:30 | 2016-09-26 16:30 | N | N | bridge work on RR 32 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2016-09-26 11:00 | 2016-09-26 16:00 | N | N | fall substation washing | Transformer, Line, Shunts |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 418L (20s Ghost - 418L193A) | 2016-09-26 11:30 | 2016-09-30 17:45 | N | N | clearance mitigation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2016-09-26 12:30 | 2016-09-29 17:30 | N | N | T2 138kV & 25kV bushing replacements & bushing monitor pre- wire | Transformer |  |  | For Information Only
ALTALINK | 310p 352 (310p Sundance) | 2016-09-26 12:30 | 2016-09-29 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  | 310p3A, 310p3B | 240 kV
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2016-09-27 06:00 | 2016-09-28 20:00 | N | Y | excavation work in the proximity | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK, EPCOR | 330p 807 (330p Genesee),430L (330P Genesee - 510S Sunnybrook) | 2016-09-27 07:00 | 2016-10-05 17:00 | N | Y | protection upgrade | Line, Circuit Breaker |  |  | For Information Only
ATCO | 790s 703T (790s Poplar Hill) | 2016-09-27 07:00 | 2016-09-29 19:00 | N | Y | transformer maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 784L (535s Joffre - 332s Ellis) | 2016-09-27 07:00 | 2016-09-27 17:00 | N | N | create open point 'A' | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALBIAN, SHELL | 847s 901 (847s Muskeg River),847s 903 (847s Muskeg River),847s 904 (847s Muskeg River),919s 907 (919s Hartley),919s 908 (919s Hartley) | 2016-09-27 07:00 | 2016-10-10 17:30 | N | Y | protection upgrade | Circuit Breaker |  | Protection upgrade, see schedule below & attached wplan; Sep 27-Oct 7 (2-32415A) Isolate between 903, 901, 9L66D2, 900D2, 901PT, 904PT Oct 7-8 (2-32415B) Expand GOI zone from 900D2 to 9LJH-2D1 and 902TD @ 919s Oct 9-10 (2-32415C) Reduce GOI zone back to 903, 901, 9L66D2, 900D2, 901PT, 904PT | 240 kV, Pre-Condition
ATCO | 743s 701T (743s Sarah Lake) | 2016-09-27 07:00 | 2016-12-05 17:30 | N | N | remove 701TCS, add 705, 705A, 700PT1, install new protection in new building | Transformer |  | Remove 701TCS, add 705, 705A, 700PT1, install new protection in new building, 7L172, 7L55, 6L126, 6L11, and 6L96 will be separated from 743s, 702T will carry all 25kV load. | Over/Under Voltage
ALTALINK | 123s T1 (123s Banff) | 2016-09-27 07:15 | 2016-09-28 17:45 | N | N | repair tap changer | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 824s 701T (824s Fieldgate) | 2016-09-27 08:00 | 2016-09-30 17:00 | N | N | perform major maintenance on 701T and change CT ratios | Transformer |  | Perform Major Maintenance on 701T and change CT Ratios During the Outage all load will be carried by Mobile Substation 835S. | Pre-Condition
ATCO | 2029s 1204 (2029s Heathfield) | 2016-09-27 08:00 | 2016-09-30 17:00 | N | Y | 1204 breaker wiring fix @ 2029s Heathfield | Circuit Breaker |  | 1204 breaker wiring fix @ 2029s Heathfield | For Information Only, 500 kV
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),47.2 TR (ENMAX 47) | 2016-09-27 08:00 | 2016-09-27 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2016-09-27 08:00 | 2016-09-28 17:00 | N | Y | urgent outage to investigate/mitigate teleprotection mis-operations | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2016-09-27 08:00 | 2016-10-01 16:00 | N | N | relocate line for Burnco | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 127s T2 (127s Bruderheim) | 2016-09-27 08:30 | 2016-09-27 17:30 | N | N | installing new transformer qualitrol monitor | Transformer |  |  | For Information Only
ALTALINK | 765L (74s Janet - 151s Strathmore) | 2016-09-27 11:30 | 2016-09-27 15:30 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s J2404 (805s Jasper) | 2016-09-28 07:00 | 2016-09-28 16:00 | N | Y | switching demonstation | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 305s C1 (305s Acheson) | 2016-09-28 07:15 | 2016-09-28 08:45 | N | N | testing on 305s32 | Shunts |  | 305s32 (C1) - Functional testing of 305s32 for the replacement of T1 'A' protection | For Information Only
ENMAX | 8.1TR (ENMAX 8) | 2016-09-28 08:00 | 2016-09-29 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2016-09-28 08:00 | 2016-09-28 12:00 | N | N | substation washing | Line, Transformer |  |  | Overload, Creates Radial Feeds
ALTALINK | 739L (14s Devon - 305s Acheson),305s 739X (305s Acheson) | 2016-09-28 08:45 | 2016-09-28 10:15 | N | N | testing of 305s739X | Line, Circuit Breaker |  | 305s739X (739L) - Functional testing of 305s739X for the replacement of T1 'A' protection | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 739L (305s Acheson - 434s Stony Plain),305s 739W (305s Acheson) | 2016-09-28 10:15 | 2016-09-28 11:45 | N | N | functional testing of breaker | Line, Circuit Breaker |  | 305s739W (739L) - Functional testing of 305s739W for the replacement of T1 'A' protection | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 930s Syn Condenser (930s Arcenciel) | 2016-09-28 11:00 | 2016-09-28 15:00 | N | Y | emergency repair a failed DC power supply | Shunts |  |  | For Information Only
ALTALINK | 677L (305s Acheson  595s Spruce Grove),305s 677 (305s Acheson) | 2016-09-28 11:45 | 2016-09-28 13:15 | N | N | functional testing of breaker | Line, Circuit Breaker |  | 305s677 (677L) - Functional testing of 305s677 for the replacement of T1 'A' protection | Pre-Condition, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2016-09-28 12:00 | 2016-09-28 16:00 | N | Y | substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
CMH | MH69_60LMH_60L (MH69s5 North East Cresent Heights - Cancarb) | 2016-09-29 07:00 | 2016-09-29 18:00 | N | N | temp bypass line for new substation construction. | Line |  |  | For Information Only
BCH | 2L293 (Selkirk - Nelway) | 2016-09-29 08:00 | 2016-09-29 16:00 | N | Y | install new flexible leads on SEL 2D1CB | Line |  |  | Limits ATC, For Information Only
ENMAX | 34.1TR (ENMAX 34),34.3TR (ENMAX 34),34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2016-09-29 08:00 | 2016-09-29 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2016-09-29 12:00 | 2016-09-29 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
CMH | MH69_60LMH_60L (MH69s5 North East Cresent Heights - Cancarb) | 2016-09-30 07:00 | 2016-09-30 18:00 | N | N | temp bypass line for new substation construction. | Line |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2016-09-30 08:00 | 2016-09-30 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2016-09-30 12:00 | 2016-09-30 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 349S Stavely,928S East Stavely,180L (255s Vulcan - 928s East Stavely),180L (15s Fort Macleod - 928s East Stavely),197L (349s Stavely - 928s East Stavely) | 2016-10-01 07:00 | 2016-10-01 17:00 | N | N | maintenance on 180L sectionalizer at 928s | Line, Station |  | 180L/197L (349s/928s Station) - GOI - Perform maintenance on 180L sectionalizer at 928s. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.1TR (ENMAX 43),9.83L (ENMAX 43 - ENMAX 9) | 2016-10-01 08:00 | 2016-10-01 12:00 | N | N | substation washing | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | WATL (510s Sunnybrook - 511s Crossings) | 2016-10-01 09:00 | 2016-10-01 18:00 | N | N | testing | Line |  | 7.) October 1st  7th, 2016 (09:00  09:00) 510s/511s & 1325L HVDC Testing a) 511s Long open converter test - October 1st (09:00 - 11:00) b) 510s Long open converter test - October 1st (11:00 - 13:00) c) Open line test from 510s - October 1st (13:00 - 14:00) d) De-block no power reversal for 2-3 days N to S October 1st  4th (14:00 - 09:00) CANCELLED e) Heat Run N to S @ 1,000MW - October 3rd (08:00 - 20:00) CANCELLED f) De-block no power reversal for 2-3 days S to N October 4th - 7th (09:00 - 09:00) CANCELLED | For Information Only, 500 kV
ENMAX | 43.2TR (ENMAX 43),33.84L (ENMAX 43 - ENMAX 33) | 2016-10-01 12:00 | 2016-10-01 16:00 | N | N | substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2016-10-02 08:00 | 2016-10-02 12:00 | N | N | substation washing | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 420S Broadmoor | 2016-10-02 08:00 | 2016-10-04 16:00 | N | N | In service date: Oct 3, 2016. 420s T2 will be energized. | Station
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2016-10-02 12:00 | 2016-10-02 16:00 | N | N | substation washing | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2016-10-03 05:30 | 2016-10-14 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.3TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2016-10-03 06:00 | 2016-10-03 11:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft T1 (Woodcroft) | 2016-10-03 06:00 | 2016-10-07 17:00 | N | N | PRV install | Transformer |  |  | For Information Only
EPCOR | Hardisty T2 (Hardisty) | 2016-10-03 07:00 | 2016-10-09 17:00 | N | N | TX2 transformer protection re-configuration and energization of bus 2 switchgear | Transformer |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy),814s B2401 (814s Bellamy),Rossdale BR721 (Rossdale),814s B2407 (814s Bellamy) | 2016-10-03 07:00 | 2016-10-08 17:00 | N | Y | DGA monitor install | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2016-10-03 07:30 | 2016-10-14 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Creates Radial Feeds
SUNCOR | 29PL9-17 (29EDD-1 Millennium - 29EDD-94 Voyageur) | 2016-10-03 08:00 | 2016-10-10 20:00 | N | Y | maintenance | Line |  | 5YR PM 952-104 CT-952-104A/B/C 29PS-408 29PS-407 CT-952-105A/B/C 952-105 29PLA-109A/B/C 29PT-419A/B/C 29PL9-17 and associated equipment | 240 kV, Creates Radial Feeds
ATCO | 797S Kempriver,797s 701T (797s Kemp River),7L62 (789s Keg River - 797s Kemp River),7L62 (797s Kemp River - 905s Meikle) | 2016-10-03 08:00 | 2016-11-03 14:30 | N | Y | replace 7L62D4 structure and switch then replace 7L62D3, 4160 metering tank, repair clearance issues in the 4160 bay and upgrade protection | Station, Line, Transformer |  | Replace 7L62D4 structure and switch. refer to attached work sequence Oct 3 (4 hrs) - 7L62 Open ended @ 797s to create jumper J1, 797s Outage Oct 3 PM - Oct 19 - 7L62 Open between 905s and 797s, 797s radial fed from 789s Oct 19 (4 hrs) - 7L62 OOS to connect mobile sub 750s, 797s Outage Oct 19 PM - Release 2-33777C, 750s energized on RTN switching, 750s radial fed by 7L62 from 905s | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43),33.1TR (ENMAX 33) | 2016-10-03 08:00 | 2016-10-17 16:00 | N | N | HV bushing replacement & transformer differential CT addition | Line, Circuit Breaker, Transformer |  | HV bushing replacement & transformer differential CT addition. Adjust 43B138-33.84 operating stroke. Shrink outage on 33.84L as required for crane & breaker work | Creates Radial Feeds
ENMAX | 26.1TR (ENMAX 26) | 2016-10-03 08:00 | 2016-10-04 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 271s T1 (271s Shell Jumping Pound) | 2016-10-03 09:15 | 2016-10-06 17:45 | N | N | replace bushings and LA's | Transformer |  |  | For Information Only
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2016-10-03 09:30 | 2016-10-05 17:30 | N | N | insulator washing | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek) | 2016-10-03 09:30 | 2016-10-07 17:30 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary),5s C4 (5s East Calgary) | 2016-10-03 10:00 | 2016-10-03 14:00 | N | N | fence repair; capacitor bank grounding required by Altalink | Shunts |  |  | For Information Only
ALTALINK | 5s C3 (5s East Calgary),5s C4 (5s East Calgary) | 2016-10-03 10:00 | 2016-10-03 14:00 | N | N | ENMAX maintenance (fence repair) | Shunts |  |  | For Information Only
ALTALINK | 420s 138kV Bus 2 (420s Broadmoor),731L (420s Broadmoor - 731L tap),420s T2 (420s Broadmoor) | 2016-10-03 10:30 | 2016-10-06 12:00 | N | N | connect T2 and new feeders to the system | Line, Bus, Transformer |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2016-10-03 11:00 | 2016-10-03 16:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s T1 (77s Sagitawah) | 2016-10-03 12:15 | 2016-10-11 17:45 | N | Y | replace T1 bushings | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 741s 701T (741s Fox Creek),741s 703 (741s Fox Creek) | 2016-10-03 14:00 | 2016-10-05 15:00 | N | N | repair damaged switch | Transformer, Circuit Breaker |  | Repair damaged Switch 703A, Load has been transferred to 702T already. | For Information Only
ALTALINK | 702L (377s Hardisty - 137s Sedgewick) | 2016-10-04 07:00 | 2016-10-05 18:00 | N | N | replace 2 structures 354,355, replace arms and glass on structures 359,360 | Line |  | 1. Studied with Battle River generation = 495 MW (net to grid), SE wind = 200 MW, EATL = 100 MW and WATL = 100 MW. | Creates Radial Feeds
ALTALINK | 602s T1 (602s Cold Creek) | 2016-10-04 07:00 | 2016-10-04 17:00 | N | N | installing bird mitigation & replacing 3 25kV insulators on the 25kV bus along with installing interphase barriers on 602s10 | Transformer |  |  | For Information Only
ALTALINK | 51s T3 (51s Wainwright) | 2016-10-04 07:15 | 2016-10-04 15:45 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 84L (35s Rundle - 33s Spray),85L (35s Rundle - 85L12),35s 41 (35s Rundle),35s 8 (35s Rundle) | 2016-10-04 07:30 | 2016-10-04 17:30 | N | Y | emergency repair switch,emergency repair swtich | Switch, Line |  |  | Overload, Restricts Generation, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2016-10-04 07:30 | 2016-10-07 17:30 | N | Y | damper replacement | Line |  |  | 500 kV
ENMAX | 10.2TR (ENMAX 10) | 2016-10-04 08:00 | 2016-10-04 12:00 | N | N | replace and test CAC/OAC relays for new RTU | Transformer |  |  | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2016-10-04 08:00 | 2016-10-05 16:00 | N | N | transformer diff. and OC relay testing | Transformer |  |  | For Information Only
ENMAX | 1.5TR (ENMAX 1) | 2016-10-04 08:00 | 2016-10-04 10:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ALTALINK | 388S Riverside,708AL (388s Riverside - 708L tap),388s 708A (388s Riverside) | 2016-10-04 08:30 | 2016-10-05 19:00 | N | Y | topping up breaker with gas | Station, Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2016-10-04 08:30 | 2016-10-04 12:30 | N | N | measurements between over/underbuild required for upcoming high load move - Fortis requested outage | Line |  |  | Creates Radial Feeds
ENMAX | 1.6TR (ENMAX 1) | 2016-10-04 10:00 | 2016-10-04 12:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ALTALINK | 708AL (388s Riverside - 708L tap),708L (71s Lamoureux - 708L88X),708L (233s Beamer - 708L88N) | 2016-10-04 10:00 | 2016-10-04 18:00 | N | N | 708L(233s - 71s) de-energized, this line needs to be de-energized since both TPR channels A and B will be removed from service at the same time for an 233s and 388s MPLS upgrade | Line |  | 4. Studied with AIES load = 9634 MW, Red Water generation = 0 MW and DOWG = 200 MW | Restricts Generation
ENMAX | 1.7TR (ENMAX 1) | 2016-10-04 12:00 | 2016-10-04 14:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2016-10-04 12:00 | 2016-10-04 16:00 | N | N | replace and test CAC/OAC relays for new RTU | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2016-10-04 14:00 | 2016-10-04 16:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ALTALINK | 602s T2 (602s Cold Creek) | 2016-10-05 07:00 | 2016-10-05 14:00 | N | N | install bird mitigation on 602s T2 LV bushings & interphase barriers on 602s16 | Transformer |  |  | For Information Only
ALTALINK, ATCO | 9L960 (13s Deerland - 825s Whitefish Lake),13s 1652 (13s Deerland),13s 1752 (13s Deerland) | 2016-10-05 07:00 | 2016-10-06 18:00 | N | Y | replace failed protection - urgent repair | Circuit Breaker, Line |  | 2. Studied with Fort McMurray export flow = 480 MW. | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 916L (42s Sarcee - 5s East Calgary),42s 916E (42s Sarcee) | 2016-10-05 07:30 | 2016-10-06 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 34.2TR (ENMAX 34) | 2016-10-05 08:00 | 2016-10-05 12:00 | N | N | remove trojan oil processor | Transformer |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2016-10-05 08:00 | 2016-10-05 12:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Creates Radial Feeds
ENMAX | 23.2TR (ENMAX 23) | 2016-10-05 08:00 | 2016-10-06 16:00 | N | N | LTC maintenance (spare) | Transformer |  |  | For Information Only
ALTALINK | 304s T2 (304s Shell Limestone),304s 295 (304s Shell Limestone) | 2016-10-05 08:30 | 2016-10-05 17:30 | N | N | transformer doble and maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 263s 652 (263s Strachan) | 2016-10-05 10:30 | 2016-10-06 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Creates Radial Feeds
Saskpower | Sask Power S1M Line | 2016-10-05 11:00 | 2016-10-05 15:00 | N | N | high load move | Line |  |  | Limits ATC
ENMAX | 34.3TR (ENMAX 34) | 2016-10-05 12:00 | 2016-10-05 16:00 | N | N | install trojan oil processor | Transformer |  |  | For Information Only
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2016-10-05 12:30 | 2016-10-06 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2016-10-05 23:00 | 2016-10-06 03:00 | N | Y | maintenance | Switch |  | The following outage has been added to the schedule as requested by TAU Hydro. | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2016-10-06 03:00 | 2016-10-06 07:00 | N | Y | maintenance | Switch |  | The following outage has been added to the schedule as requested by TAU Hydro. | 240 kV, Restricts Generation
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2016-10-06 07:30 | 2016-10-07 16:30 | N | Y | emergency work due to water leak 510s T11 | Line |  |  | For Information Only, 500 kV
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2016-10-06 08:00 | 2016-10-06 16:00 | N | N | line protection testing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 304s T2 (304s Shell Limestone),304s 295 (304s Shell Limestone) | 2016-10-06 08:30 | 2016-10-06 17:30 | N | N | 138kV breaker maintenance and latch replacement | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 905L (19s Wabamun - 37s North Calder),920L (37s North Calder - 557s Castle Downs),37s 76 (37s North Calder),37s 82 (37s North Calder),37s 87 (37s North Calder) | 2016-10-06 09:15 | 2016-10-06 17:45 | N | Y | test recloser logic circuits for 905L and 920L, require both breakers to test reclose logic | Line, Circuit Breaker, Switch |  |  | 240 kV, Overload, Creates Radial Feeds
ATCO | 7L20 (845s Big Mountain - 810s Dome Cutbank) | 2016-10-07 07:00 | 2016-10-17 17:30 | N | Y | Thornton project, salvage structures/conductor on 7L20, erect new switch and structures, tie into 7L20 and commission | Line |  | Thornton project, Salvage structures/conductor on 7L20, erect new switch and structures, tie into 7L20 and commission, 740s HRM and Dome cutbank radial fed via 7L80. | Restricts Generation, Creates Radial Feeds
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2016-10-07 07:30 | 2016-10-07 14:30 | N | N | insulator washing | Line |  |  | Creates Radial Feeds
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2016-10-07 08:00 | 2016-10-07 16:00 | N | Y | fall substation washing | Line, Transformer, Shunts |  |  | Overload
ALTALINK | 706L (410s Josephburg - 706L72D) | 2016-10-07 14:31 | 2016-10-07 17:30 | N | N | insulator washing | Line |  |  | Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2016-10-08 05:00 | 2016-10-08 10:00 | N | N | fall substation washing at night | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ALBIAN | 919s 908 (919s Hartley) | 2016-10-08 08:00 | 2016-10-09 16:00 | N | Y | test new logic | Circuit Breaker |  | Test new logic from 847S Muskeg to 908 at 919S Hartley. 902TD will already be open under GOI# 2-32415. | 240 kV, For Information Only
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2016-10-10 08:00 | 2016-10-10 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition
ENMAX | ENMAX 65 B138-D84 (ENMAX 65),ENMAX 65 B138-D81 (ENMAX 65),65.1 TR (ENMAX 65) | 2016-10-10 08:00 | 2016-10-17 10:00 | N | Y | FATDSC-installation of 54.81L receiving structure | Transformer, Circuit Breaker |  | (FATDSC)-Installation of 54.81L receiving structure. Special switching steps required on re-energization. 138kV Vertical bus pieces removed from jaw side (south side) of SW81. 138kV Bus on Jaw Side of SW88 on schematic opened. | 240 kV, For Information Only
SUNCOR | 505s 635pT_1000 (505s Fort Hills) | 2016-10-10 09:00 | 2016-10-11 17:00 | N | Y | check PRD switch on transformer 635PT-1000 and replace it if required | Transformer |  | The same model of transformer 635PT-1001 in the same substation experienced the faulse trip on September 21, 2016. The cause of this trip has been identified and the corrective action has been completed. The outage of 635PT-1000 is required to check if there is same issue and any corrctive action is needed. | For Information Only
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2016-10-10 12:01 | 2016-10-10 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, For Information Only
ATCO | 7L157 (837s Mahihkan - 970s Bourque),837s 701 (837s Mahihkan) | 2016-10-11 07:00 | 2016-10-21 17:00 | N | N | replace HLD breaker | Line, Circuit Breaker |  | Replace HLD breaker, 7L157 will be open ended @ 837s, 837s connected to grid radial on 7L160 | Firm Load Loss, Creates Radial Feeds
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2016-10-11 07:00 | 2016-10-24 17:30 | N | Y | station outage, 2075S 1300PT1 and 2023s 1300PT1, Siemens to provide new dividers to replace existing in service devices | Line |  | Station outage, EATL will be unavailable for transfer. Siemens to provide new dividers to replace existing in service devices. | Pre-Condition, 500 kV
EPCOR | RossdaleT3 (Rossdale),Rossdale R724 (Rossdale),Rossdale R723 (Rossdale) | 2016-10-11 07:00 | 2016-10-23 17:00 | N | N | cutting over and commissioning new transformer protection | Transformer, Circuit Breaker |  |  | Pre-Condition, Overload
ATCO | 741s 702T (741s Fox Creek) | 2016-10-11 07:00 | 2016-10-14 17:00 | N | N | construction, attach new breaker 507 to 500BS2 | Transformer |  | Construction, attach new breaker 507 to 500BS2, all load transferred from 702T to 701T, 5MVA capbank 504C will be unavailable for V control. | For Information Only
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2016-10-11 07:30 | 2016-10-12 17:30 | N | N | Inspect and tighten spacers at road crossings in 1206L circuit | Line |  |  | For Information Only, 500 kV
ALTALINK | 688DL23 (688L) - Open AirBreak Advice | 2016-10-11 07:30 | 2016-10-11 17:30 | N | Y | close open point 'A' on 688L (str15), 284s to remain online | Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2016-10-11 07:30 | 2016-11-30 12:00 | N | Y | emergency outage | Shunts, Transformer |  |  | 240 kV, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s 752 (29EDD-1 Millennium),29EDD-1 29EDD1s 852 (29EDD-1 Millennium),29EDD-1 29EDD1s 552 (29EDD-1 Millennium),29EDD-1 29EDD1s 452 (29EDD-1 Millennium),29EDD-1 29EDD1s 152 (29EDD-1 Millennium),29EDD-1 29EDD1s 252 (29EDD-1 Millennium),29EDD-1 29EDD1s 352 (29EDD-1 Millennium) | 2016-10-11 08:00 | 2016-10-28 20:00 | N | Y | rebuild dashpots | Circuit Breaker |  | S152 REBUILD DASHPOTS (AW)(ISO) S152 REBUILD DASHPOTS (AW)(ISO) S152 REBUILD DASHPOTS (AW)(ISO) S252 REBUILD DASHPOTS (AW)(ISO) S252 REBUILD DASHPOTS (AW)(ISO) S252 REBUILD DASHPOTS (AW)(ISO) S352 REBUILD DASHPOTS (AW)(ISO) S452 REBUILD DASHPOTS (AW)(ISO) S752 REBUILD DASHPOTS (AW)(ISO) S852 REBUILD DASHPOTS (AW)(ISO) 29EDD-1 Replace 29CT-5A 29EDD1s552 Replace Dash-pot Piston Rods | 240 kV, For Information Only
ENMAX | 27.1TR (ENMAX 27) | 2016-10-11 08:00 | 2016-10-11 16:00 | N | N | inspect/repair liquid/winding temp gauges. low oil in LTC. tanker required | Transformer |  |  | For Information Only
EPCOR | 511s Victoria T2 (511s Victoria) | 2016-10-11 08:00 | 2016-10-14 15:00 | N | N | TX#2 Victoria clearance for contractor | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2016-10-11 08:00 | 2016-10-21 09:00 | N | Y | SWCRR - cable pulling | Line |  | (SWCRR)- Allteck 21.80 OOS #1 Aug 8th  15th for Cable pulling and training / racking Termination/testing/completion. Relay settings upgrade and testing required. Altalink required to install an remove grounds on bottom of line side switches at 42s for Valard. Altalink required to remove grounds on bottom of line side switches at 42s for Valard. Switching and phasing required. Start of 24hr soak. 21.80L to carry load Oct 20th 12pm. | For Information Only
BCH | 5L72 (Mica Creek - Nicola) | 2016-10-11 09:00 | 2016-10-19 19:00 | N | N | Switching outage to close MCA 5D34. | Line |  |  | Limits ATC, 500 kV
ALTALINK | 271s T2 (271s Shell Jumping Pound) | 2016-10-11 09:15 | 2016-10-14 17:45 | N | N | replace bushings and LA's | Transformer |  |  | For Information Only
BCH | 2L112 (Nelway - Boundary) | 2016-10-11 09:30 | 2016-10-11 16:30 | N | N | BPA work | Line |  |  | Limits ATC
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek) | 2016-10-11 09:30 | 2016-10-14 17:30 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 159s T1 (159s Colinton) | 2016-10-11 11:15 | 2016-10-13 13:00 | N | N | install cantega cover | Transformer |  |  | For Information Only
ALTALINK | 74s T2 (74s Janet),74s 77 (74s Janet) | 2016-10-11 11:30 | 2016-10-13 17:30 | N | Y | 138kV breaker maintenance | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 526s T1 (526s Buffalo Creek) | 2016-10-11 12:15 | 2016-10-19 10:45 | N | N | transformer maintenance | Transformer |  |  | For Information Only
SHELL, ALBIAN | 847s 901T (847s Muskeg River),847s 902 (847s Muskeg River),847s 903 (847s Muskeg River),919s 905 (919s Hartley) | 2016-10-12 07:00 | 2016-10-26 17:30 | N | Y | replace cabling | Transformer, Circuit Breaker |  | Disconnect and remove 903 optical CT's Install new 903CT Remove cabling, install new and terminate Bkr 903 Remove cabling, install new and terminate 903PT Complete cable install and terminate 903CT poles Reconnect bus Commission protection and control - Logic, Telecontrol, Telecom | 240 kV, For Information Only
ALTALINK | 310P 69 (310p Sundance),310p T30 (310p Sundance) | 2016-10-12 07:00 | 2016-10-14 09:00 | N | Y | replace breaker 310p69 | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 791s 702T (791s Rainbow Lake) | 2016-10-12 07:00 | 2016-10-15 17:00 | N | N | remove sub feeder # 2, Bus T1 and T2 load on 701T | Transformer |  | Remove sub feeder # 2, Bus T1 and T2 load on 701T | For Information Only
EPCOR | 72NW15 (Namao - Woodcroft),Namao N726 (Namao) | 2016-10-12 07:00 | 2016-11-03 14:30 | N | N | breaker replacement | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 72s T1 (72s Leismer) | 2016-10-12 07:45 | 2016-10-12 14:45 | N | Y | replace broken stand off insulators on LA's | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 780L (38s East Edmonton - 149s Nisku),149s 780N (149s Nisku) | 2016-10-12 08:00 | 2016-10-12 17:30 | N | N | investigate/repair line reclosing issue | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 975s T1 (975s Dalehurst) | 2016-10-12 08:15 | 2016-10-12 13:45 | N | N | replacing two fuse disconnects | Transformer
ALTALINK | 412S Shell Eagle Creek | 2016-10-12 09:00 | 2016-10-12 13:00 | N | N | customer repairs to a heater on the bus | Station |  |  | For Information Only
ALTALINK | 397s T2 (397s Benbow) | 2016-10-12 10:15 | 2016-10-12 13:45 | N | N | commission SCADA points and controls to 397s31 | Transformer |  |  | For Information Only
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2016-10-12 17:31 | 2016-10-14 17:30 | N | N | Inspect and tighten spacers at road crossings in 1212L circuit | Line |  |  | For Information Only, 500 kV
ALBIAN | 919s 906 (919s Hartley) | 2016-10-13 06:30 | 2016-10-27 16:00 | N | Y | Shell Albian Sands request | Circuit Breaker |  | Shell Albian Sands request a COG they will be shutting down GT#1 for turnaround Issue Permit to Control room - 1-780-713-4745 | 240 kV, Creates Radial Feeds
ALTALINK | 216s T1 (216s Knightsbridge) | 2016-10-13 07:00 | 2016-10-14 12:00 | N | N | customer requires isolation to perform maintenance | Transformer |  |  | For Information Only
EPCOR | 72NW15 (Namao - Woodcroft),72VN21 (Namao - 511s Victoria),Namao N721 (Namao),Namao N726 (Namao),Namao N725 (Namao),72KN23 (Namao - Kennedale) | 2016-10-13 07:00 | 2016-10-15 17:00 | N | N | breaker replacement N726 | Line, Circuit Breaker |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 123s T3 (123s Banff),54L (123s Banff - 177s West Cascade),123s 54E (123s Banff) | 2016-10-13 07:15 | 2016-10-13 17:45 | N | N | inspect transformer tap changer and change hydran sensor. | Transformer, Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 108s 352 (108s Amelia) | 2016-10-13 08:00 | 2016-10-13 13:00 | N | Y | tighten all hardware on breaker | Circuit Breaker |  |  | 240 kV
ENMAX | 11.1TR (ENMAX 11) | 2016-10-13 08:00 | 2016-10-13 12:00 | N | N | fall substation washing. | Transformer |  |  | For Information Only
ATCO | 813s 716C (813s Little Smoky) | 2016-10-13 08:00 | 2016-10-13 17:00 | N | N | emergency outage | Shunts |  |  | Pre-Condition
ALTALINK | 410s T1 (410s Josephburg) | 2016-10-13 08:30 | 2016-10-13 12:30 | N | Y | Repair IDD bushing connector on H2 | Transformer |  |  | 240 kV
ALTALINK | 551L (123s Banff - 953s Lake Louise) | 2016-10-13 09:00 | 2016-10-13 16:00 | N | N | structure replacement, area loads offline for the duration | Line |  |  | For Information Only
ENMAX | 11.4TR (ENMAX 11) | 2016-10-13 12:01 | 2016-10-14 16:00 | N | N | fall substation washing. | Transformer |  |  | For Information Only
ALTALINK | 108s 452 (108s Amelia) | 2016-10-13 13:01 | 2016-10-13 17:30 | N | Y | tighten all hardware on breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 525s 850N (525s Carseland),850L (525s Carseland - 678s Okotoks) | 2016-10-14 08:00 | 2016-10-14 11:00 | N | N | add recloser control | Line, Circuit Breaker |  |  | Overload, Creates Radial Feeds
ENMAX | 25MD240-3GSU (ENMAX 25),25B240-D140 (ENMAX 25),25B240-D141 (ENMAX 25) | 2016-10-14 08:00 | 2016-10-14 16:00 | N | Y | MD maintenance on 25MD240-3GSU | Circuit Breaker, Switch |  |  | 240 kV
ALTALINK | 851L (525s Carseland - 253s Blackie),525s 851X (525s Carseland) | 2016-10-14 11:01 | 2016-10-14 14:00 | N | N | add recloser control,add relcoser control | Line, Circuit Breaker |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 681s T1 (681s Bannerman) | 2016-10-14 12:00 | 2016-10-17 14:00 | N | Y | retest paralleling scheme | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 681s T2 (681s Bannerman) | 2016-10-14 12:00 | 2016-10-17 14:00 | N | Y | retest paralleling scheme | Transformer |  |  | 240 kV, For Information Only
ENMAX | 31.1C (ENMAX 31) | 2016-10-15 12:00 | 2016-10-15 16:00 | N | N | fall substation washing, hot spot repair SW86 @ 31 Sub | Shunts |  |  | For Information Only
ALTALINK | 932L (74s Janet - 162s Beddington) | 2016-10-16 07:00 | 2016-10-16 10:00 | N | Y | Fall substation washing | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 791S Rainbow Lake | 2016-10-16 07:00 | 2016-10-28 17:30 | N | N | Bus T2, Bus B @791S, Husky feeders 2, 4, 6 out of service | Station |  | Bus T2, Bus B @791S, Husky feeders 2, 4, 6 out of service Disconnect existing and reconnect new protection/control/metering cabling. Disconnect RB2 from Bus T2 Bkr 462 @ 791S (decommissioned) Connect new RB4 feeder to Bus T2 Bkr 459 @ 791S Complete commissioning P&C Inspect and test tapchangers on Husky's 401T, 409T, and 411T. Restore all Bus T2 feeders | For Information Only
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2016-10-16 10:01 | 2016-10-16 12:00 | N | Y | Fall substation washing | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2016-10-16 12:00 | 2016-10-16 14:00 | N | Y | Fall substation washing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2016-10-16 14:01 | 2016-10-16 16:00 | N | Y | Fall substation washing | Line |  |  | Pre-Condition
EPCOR | E511s VictoriaT3 (511s Victoria) | 2016-10-17 06:00 | 2016-10-28 17:00 | N | N | ETM install | Transformer |  |  | For Information Only
EPCOR | 1098L (805s Jasper - Poundmaker) | 2016-10-17 06:00 | 2016-10-21 17:00 | N | Y | line maintenance | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2016-10-17 06:00 | 2016-10-21 17:00 | N | Y | line maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s T3 (805s Jasper) | 2016-10-17 06:00 | 2016-10-21 17:00 | N | Y | ETM install | Transformer |  |  | 240 kV, For Information Only
ATCO | 2075s SVC2 (2075s Newell),2075s 930A (2075s Newell) | 2016-10-17 07:00 | 2016-10-20 17:00 | N | Y | online pump addition/cold start upgrade | Shunts, Switch |  | Online Pump Addition/Cold Start Upgrade SVC1 will remain in service while SVC2 is out of service. This will provide no restrictions to the DC or AC system while it is out of service. | 240 kV
EPCOR | 987s C2406 (987s Clover Bar) | 2016-10-17 07:00 | 2016-10-21 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 1035L (2075s Newell - 244s Bowmanton) | 2016-10-17 07:30 | 2016-10-26 17:30 | N | Y | damper replacements | Line |  |  | 240 kV
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2016-10-17 07:30 | 2016-10-28 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),420s 138kV Bus 1 (420s Broadmoor),420s T1 (420s Broadmoor),420s 20 (420s Broadmoor) | 2016-10-17 08:00 | 2016-10-19 09:00 | N | N | commission new protections, install permanent risers between 420s852 and 420s4, install 420s1452 breaker | Switch, Transformer, Line, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 834s 902T (834s Wesley Creek) | 2016-10-17 08:00 | 2016-10-21 15:00 | N | Y | tapchanger vibro-acoustic measurements | Transformer |  | tapchanger vibro-acoustic measurements | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 41.1TR (ENMAX 41) | 2016-10-17 08:00 | 2016-10-26 16:00 | N | N | LV bushing replacement | Transformer |  |  | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2016-10-17 08:00 | 2016-10-21 16:00 | N | N | PRD install | Transformer |  |  | For Information Only
ALTALINK | 551L (123s Banff - 953s Lake Louise) | 2016-10-17 09:00 | 2016-10-17 16:00 | N | N | structure replacement, area loads offline for the duration | Line |  |  | For Information Only
ALTALINK | 244s T2 (244s Bowmanton),244s 2389 (244s Bowmanton) | 2016-10-17 09:15 | 2016-10-18 17:45 | N | Y | crew to repair 240kV switch | Switch, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 62s T4 (62s Brazeau) | 2016-10-17 10:00 | 2016-10-28 17:00 | N | N | replace 4160V switchgear | Transformer |  |  | For Information Only
ENMAX | ENMAX 65 B138-D84 (ENMAX 65),ENMAX 65 138 kV South Bus | 2016-10-17 10:00 | 2016-12-14 16:00 | N | N | (FATDSC) - install 65MD138-54.81, SW 89, 65B138-D83 | Bus, Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 14.2TR (ENMAX 14),14.4TR (ENMAX 14) | 2016-10-17 11:00 | 2016-10-17 16:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2016-10-17 11:00 | 2016-10-17 16:00 | N | N | fall substation washing | Shunts |  |  | For Information Only
ALTALINK | 89s 1052 (89s Ellerslie),89s 952 (89s Ellerslie),910L (89s Ellerslie - 288s Wolf Creek) | 2016-10-17 11:30 | 2016-10-20 14:30 | N | Y | replace failed 910L A protection | Line, Circuit Breaker |  | Urgent outage to replace failed 910L A Protection. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku),38s 780X (38s East Edmonton) | 2016-10-17 12:30 | 2016-10-17 15:30 | N | N | gas top up | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 310p 352 (310p Sundance) | 2016-10-17 12:30 | 2016-10-19 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  | It is considered urgent repair. See email from AltaLink Fri 2016-10-07 11:01 AM | 240 kV
ALTALINK | 320p 2152 (320p Keephills) | 2016-10-17 13:00 | 2016-10-17 16:00 | N | Y | gas top up | Circuit Breaker |  |  | 240 kV
ALTALINK | 726L (37s North Calder - 71s Lamoureux),37s 726E (37s North Calder) | 2016-10-18 06:30 | 2016-10-18 17:00 | N | N | urgent arm change on 726L, structure 132 | Line, Circuit Breaker |  |  | Over/Under Voltage
ALTALINK | 74s 2152 (74s Janet) | 2016-10-18 07:30 | 2016-10-20 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 851L (525s Carseland - 253s Blackie),525s 851X (525s Carseland) | 2016-10-18 07:30 | 2016-10-20 17:30 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 16.1TR (ENMAX 16) | 2016-10-18 08:00 | 2016-10-18 16:00 | N | N | LTC oil top up | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24),ENMAX 24 B138_24BT3 (ENMAX 24) | 2016-10-18 08:00 | 2016-10-28 16:00 | N | Y | reinstall breaker protection settings changes (24s 138KV bus differential, 24s auto switching),remove temp jumpers across 24BT3 and reinstall breaker protection settings changes (24s 138KV bus differential, 24s auto switching) | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 286s T1 (286s Yasa) | 2016-10-18 08:15 | 2016-10-18 17:45 | N | N | installing new transformer Qualitrol monitor | Transformer |  |  | For Information Only
ALTALINK | 108s 252 (108s Amelia) | 2016-10-18 08:30 | 2016-10-18 12:30 | N | Y | replace faulty gas density gauge | Circuit Breaker |  | 108s252 - GOI - Replace faulty gas density gauge | 240 kV, For Information Only
ALTALINK | 703L (648s Metiskow - 703L),648s 703W (648s Metiskow),648s 472 (648s Metiskow) | 2016-10-19 07:15 | 2016-10-19 17:45 | N | N | change 648s703W to 648s472 | Line, Circuit Breaker |  | 648s703W (703L - 212s) - GOI - Outage required to change 648s703W to 648s472 | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 913L (69s North Barrhead - 732s Mitsue) | 2016-10-19 07:30 | 2016-10-25 10:30 | N | Y | replace insulators and perform maintenance | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 742L (985s Exshaw - 754L72),742L (985s Exshaw - 754L65A),754L (245s Seebe - 754L65A),754L (437s Baymag - 754L72) | 2016-10-19 07:30 | 2016-10-20 17:30 | N | Y | customer requested line move | Line |  |  | Pre-Condition, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2016-10-19 07:30 | 2016-10-19 12:00 | N | N | add supervisory control to 262s35 and 262s44 | Transformer |  |  | For Information Only
ALTALINK | 420S Broadmoor | 2016-10-19 08:00 | 2016-10-20 13:00 | N | N | 25kV Bus 2 - close open point 'P' | Station |  |  | For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2016-10-19 08:00 | 2016-10-20 16:00 | N | N | leak repair by the Colt Group | Transformer |  |  | For Information Only
ALTALINK | 676L (523s Bullshead - 244s Bowmanton),244s Bowmanton 138kV Bus 1,244s T1 (244s Bowmanton) | 2016-10-19 08:00 | 2016-10-23 18:30 | N | Y | close open Point "C" at 244s | Transformer, Bus, Line |  |  | 240 kV
ALTALINK | 385s T3 (385s Spring Coulee) | 2016-10-19 08:15 | 2016-10-20 17:45 | N | N | transformer maintenance and doble | Transformer |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2016-10-19 08:30 | 2016-10-19 17:30 | N | N | urgent repair on deteriorated arms structures 392, 387 | Line |  |  | Over/Under Voltage
ALTALINK | 244s Bowmanton 138kV Bus 4 | 2016-10-19 09:15 | 2016-11-19 15:30 | N | N | extend existing GOI to open Point "K | Bus |  |  | For Information Only
ATCO | 925s 902T (925s Green Stocking) | 2016-10-19 10:00 | 2016-10-19 16:00 | N | Y | urgent repairs on breaker 502 | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 61L (252s Jarrow - 61DL386) | 2016-10-19 10:30 | 2016-10-19 14:30 | N | N | urgent replacement of arm on 61L structure 202 | Line |  |  | For Information Only
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2016-10-19 12:30 | 2016-10-19 17:00 | N | N | add supervisory control to 262s54 and 262s56 | Transformer |  |  | For Information Only
ALTALINK | 310p Sundance 240kV Bus B | 2016-10-20 07:00 | 2016-10-21 12:00 | N | Y | replace PT2375 and 310p123 | Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 323S Whitecourt Power,503L (268s Whitecourt - 323s Whitecourt Power),268s 503 (268s Whitecourt) | 2016-10-20 08:00 | 2016-10-20 17:30 | N | Y | 69kV Breaker maintenance & 268s24 switch maintenance | Circuit Breaker, Line, Station |  |  | For Information Only
BCH | 5L71 (Mica Creek - Nicola) | 2016-10-20 08:00 | 2016-10-21 19:00 | N | N | POW testing on MCA 5CB11 | Line |  |  | Limits ATC, For Information Only, 500 kV
ALTALINK | 635S Rose Valley,635s T1 (635s Rose Valley) | 2016-10-20 08:15 | 2016-10-20 17:45 | N | N | doble and maintenance | Transformer, Station |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 522s Cooking Lake) | 2016-10-20 08:30 | 2016-10-20 17:30 | N | N | urgent crossarm replacement, imminent failure | Line |  |  | Over/Under Voltage
BCH | 5L91 (BCH Selkirk - Ashton Creek) | 2016-10-20 09:00 | 2016-10-21 17:00 | N | Y | ACK 5D1CB4, 5D2CB3, 5D44 Inspections. FLAR wiring for ACK 5CVT3 | Line |  |  | Limits ATC
ATCO | 741s 705A (741s Fox Creek) | 2016-10-20 09:00 | 2016-10-20 12:00 | N | N | test operate 705A to check it's condition | Switch |  | Test operate 705A to check it's condition. | For Information Only
ALTALINK | 275s 1952 (275s Jenner) | 2016-10-21 08:00 | 2016-10-22 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 285s T1 (285s East Camrose) | 2016-10-21 08:15 | 2016-10-22 17:45 | N | N | fix tapchanger leaks | Transformer |  |  | For Information Only
ALTALINK | 874L (522s Cooking Lake - 45s Bretona) | 2016-10-21 08:30 | 2016-10-21 17:30 | N | N | urgent arm and insulator change on structures 111 and 115 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28) | 2016-10-21 09:00 | 2016-10-22 16:00 | N | N | add support bracket to cable | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,918L (281s Johnson - 162s Beddington) | 2016-10-22 07:00 | 2016-10-22 10:00 | N | Y | fall substation washing | Bus, Line, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2016-10-22 08:00 | 2016-10-24 16:00 | N | N | City of Calgary working near lines for sheath testing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s 75 (38s East Edmonton) | 2016-10-22 08:00 | 2016-10-22 17:30 | N | N | replace burnt up tank heaters | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 749L118AN,749L118AX,749AL0 | 2016-10-22 10:00 | 2016-11-07 17:00 | N | N | replace 749L118AN, 749L118AX & 749AL0 air-breaks | Switch |  |  | For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 240 kV North Bus,162s Beddington 138 kV North Bus | 2016-10-22 10:00 | 2016-10-22 14:00 | N | Y | fall substation washing | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162.4TR (ENMAX 162 Beddington) | 2016-10-22 14:00 | 2016-10-22 16:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2016-10-23 05:00 | 2016-10-23 10:00 | N | N | fall substation washing | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2016-10-23 07:30 | 2016-10-29 17:30 | N | Y | replace insulators and perform maintenance | Line |  |  | 240 kV, Overload
ALTALINK | 38s T2 (38s East Edmonton) | 2016-10-23 08:00 | 2016-11-03 08:00 | N | N | cut over feed from T2 from existing 25kV bay to new switchgear building, test protections & commission | Transformer |  |  | For Information Only
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),Enmax 36 MD138-36.5TR (ENMAX 36) | 2016-10-23 08:00 | 2016-10-23 16:00 | N | N | HV breaker inspection, SF6 gas sample, doble PT | Switch, Line, Transformer |  | HV Breaker Inspection (16B69-16.63), SF6 Gas Sample (36B69-16.63/36.5TR), Doble PT 3. Studied with UofC generation offline. | Pre-Condition, For Information Only
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2016-10-23 10:00 | 2016-10-23 15:00 | N | Y | fall substation washing | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 676L (523s Bullshead - 244s Bowmanton) | 2016-10-23 13:30 | 2016-11-19 17:00 | N | N | Close 676L Open Point 'M' and P&C work | Line |  |  | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2016-10-24 07:00 | 2016-10-24 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.4TR (ENMAX 39) | 2016-10-24 08:00 | 2016-10-28 16:00 | N | N | PRD install | Transformer |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2016-10-24 08:00 | 2016-10-28 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
BCH | 5L71 (Mica Creek - Nicola) | 2016-10-24 09:00 | 2016-11-04 19:00 | N | N | Clearance required for spacer replacement and arcing horn install | Line |  |  | Limits ATC, For Information Only, 500 kV
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2016-10-24 09:30 | 2016-10-28 17:00 | N | Y | CT replacement | Line |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 37s 87 (37s North Calder) | 2016-10-24 09:30 | 2016-10-28 17:30 | N | Y | EPCOR CT replacement | Switch |  |  | 240 kV, For Information Only
ALTALINK | 161L (255s Vulcan - 504s Queenstown) | 2016-10-24 09:30 | 2016-10-25 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2016-10-24 09:30 | 2016-10-28 17:30 | N | Y | line maintenance | Line |  | 2. Monitor RTCA during the outage to determine if next contingency of losing 914L (86s Bigstone - 89s Ellerslie) would overload 780L (38s East Edmonton  149s Nisku) more than 115%, then operate 320p Keephills PST to transfer power from the 500 kV side to the 240 kV side (retard mode) without violating any operating limits. If it is not possible, then open 716L (40s Wetaskiwin  331s Ponoka) only if the flow is out of 40s Wetaskiwin. 3. Studied with KEG generation = 2428 MW (net), SOK flow = 1400 MW; FM export = 593 MW. | 240 kV, Pre-Condition
ALTALINK | 428L (818s Winefred - 167s Ipiatik Lake) | 2016-10-24 14:00 | 2016-10-24 18:00 | N | N | replace failed tank heater | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s 202 (62s Brazeau) | 2016-10-24 23:00 | 2016-10-24 23:59 | N | Y | trip testing from /to new 4160V equipment | Circuit Breaker |  | Coordinated with TransAlta unit outage. | Pre-Condition, For Information Only
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works),62s 201 (62s Brazeau) | 2016-10-25 00:01 | 2016-10-25 01:00 | N | Y | trip testing | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2016-10-25 03:00 | 2016-10-25 07:00 | N | N | trip test from RAS protections | Switch |  |  | 240 kV, Restricts Generation, For Information Only
ATCO | 840S McNeill Station | 2016-10-25 07:00 | 2016-10-27 15:00 | N | Y | SaskPower. SW SS breaker maintenance | Station |  |  | Limits ATC
ATCO | 2029s 1209 (2029s Heathfield) | 2016-10-25 07:00 | 2016-11-18 17:00 | N | Y | 1209 breaker wiring fix @ 2029s Heathfield | Circuit Breaker |  | 1209 breaker wiring fix @ 2029s Heathfield | Contingency Requires Mitigation, Prevents Normal Events, 500 kV
ALTALINK | 796L (282s Grassland (Alpac) - 796L28) | 2016-10-25 07:30 | 2016-10-26 17:30 | N | N | urgent outage to repair 796L OPGW | Line |  | 796L (796L28s-282s) GOI - Urgent outage as 796L span 216-217 OPGW has been damaged and needs to be replaced | Pre-Condition, Restricts Generation
ALTALINK | 752L (64s East Crossfield - 752L67),64s 752X (64s East Crossfield),64s 37 (64s East Crossfield) | 2016-10-25 07:30 | 2016-10-27 17:30 | N | Y | 138kV breaker maintenance, replace contacts, replace light above 64s37. | Line, Circuit Breaker, Switch |  | 64s752X - 138kV breaker maintenance, replace contacts, replace light above 64s37. | Restricts Generation, Creates Radial Feeds
ATCO | 6L126 (515L tap - 743s Sarah Lake),743s 601 (743s Sarah Lake) | 2016-10-25 08:00 | 2016-10-26 17:00 | N | N | change B protection settings | Line, Circuit Breaker |  | 526L/6L126 Open end at 743s - Change 526L B protection settings back to normal after 743s bypass removed. 743s601 needs to be opened to avoid protection mis-coordination while breaker fail protection is out of service. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21),44s 50X (44s Bearspaw) | 2016-10-25 08:00 | 2016-10-25 16:00 | N | N | fall substation washing | Line, Transformer, Shunts, Circuit Breaker |  |  | For Information Only
ATCO | 9L46 (932s Pemukan - 959s Lanfine) | 2016-10-25 08:00 | 2016-10-29 17:00 | N | Y | OPGW repair | Line |  | OPGW repair - String/splice new OPGW section, 9L46 TPR A & B will be OOS, All other fiber traffic will be rerouted | 240 kV, For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2016-10-25 08:00 | 2016-10-25 10:00 | N | Y | SSR testing | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 789L (818s Winefred - 898s Heart Lake),818s 789 (818s Winefred) | 2016-10-25 08:00 | 2016-10-25 17:30 | N | Y | replace failed tank heater | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 152 (39s Bickerdike) | 2016-10-25 09:30 | 2016-10-25 12:30 | N | N | top up gas on breaker | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 159s T2 (159s Colinton) | 2016-10-25 11:30 | 2016-10-26 16:30 | N | N | fix weld on transformer support beam | Transformer |  | 159s Tx18921 (T2) GOI - Jack and weld transformer to fix weld on support beam. Control cabinet wiring (as required) | For Information Only
ATCO | 918s 701 (918s Bauer) | 2016-10-26 07:00 | 2016-10-27 19:30 | N | N | test protection and attach risers for new transformer bay | Circuit Breaker |  | Test Protection and attach risers for new transformer bay. | For Information Only
EPCOR | 330p 1207 (330p Genesee),330p 1208 (330p Genesee) | 2016-10-26 07:00 | 2016-10-31 17:00 | N | Y | inter-trip checks | Circuit Breaker |  |  | Pre-Condition, 500 kV
ALTALINK | 138S T2 (138s Windy Flats),138s Windy Flats 138kV Bus 2 | 2016-10-26 07:00 | 2016-10-26 18:00 | N | N | replace missing site glass and repair oil leaks | Bus, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 83s T1 (83s Taber) | 2016-10-26 07:15 | 2016-10-26 17:45 | N | Y | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc),325s 838 (325s Leduc) | 2016-10-26 08:30 | 2016-10-26 13:30 | N | N | replace cracked heater sealant | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 612L (336s Fincastle - 368s Burdett),368s 612 (368s Burdett) | 2016-10-26 08:30 | 2016-10-26 17:30 | N | N | wiring changes to 612L line protection | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 602s T2 (602s Cold Creek) | 2016-10-26 10:00 | 2016-10-26 17:00 | N | N | install bird mitigation on 602s T2 and interphase barriers on 602s16 (25 kV) | Transformer |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2016-10-26 10:00 | 2016-10-26 16:00 | N | N | fall substation sashing | Line, Transformer, Shunts |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2016-10-26 17:00 | 2016-10-27 16:00 | N | N | salvaging neutral on understrung 5L495, upgrading arms, maintenance | Line |  | Salvaging neutral on understrung 5L495, upgrading arms, maintenance | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 5s 1252 (5s East Calgary) | 2016-10-27 07:30 | 2016-10-27 14:30 | N | N | high priority SF6 gas top up | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2016-10-27 07:30 | 2016-10-27 12:00 | N | N | add supervisory control to 262s35 and 262s44 | Transformer |  |  | For Information Only
ALTALINK | 1042L (485s Blacksprings - 554s Travers) | 2016-10-27 07:30 | 2016-10-27 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Restricts Generation
ENMAX | 36.1TR (ENMAX 36) | 2016-10-27 08:00 | 2016-10-27 16:00 | N | N | oil sample HV bushings | Transformer |  |  | For Information Only
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2016-10-27 08:30 | 2016-10-27 17:30 | N | N | 138 kV breaker maintenance | Shunts, Circuit Breaker |  |  | Pre-Condition
ATCO | 848s 402R (848s Ruth Lake),848s 402 (848s Ruth Lake) | 2016-10-27 09:00 | 2016-10-27 16:00 | N | N | breaker maintenance on breaker 402 | Shunts, Circuit Breaker |  | Breaker Maintenance on BKR 402, Reactor 402 OOS | Pre-Condition
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2016-10-27 09:00 | 2016-10-27 12:00 | N | N | fall substation washing | Line |  |  | Pre-Condition, Overload
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 223 (159s Colinton) | 2016-10-27 09:30 | 2016-10-27 14:30 | N | N | replace cracked heater sealant | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2016-10-27 12:30 | 2016-10-27 17:00 | N | N | add supervisory control to 262s54 and 262s56 | Transformer |  |  | Pre-Condition
ATCO | 848s 401R (848s Ruth Lake),848s 401 (848s Ruth Lake) | 2016-10-28 09:00 | 2016-10-28 16:00 | N | N | Breaker Maintenance on BKR 401, Reactor 401 OOS | Shunts, Circuit Breaker |  | Breaker Maintenance on BKR 401, Reactor 401 OOS | Pre-Condition
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2016-10-28 12:00 | 2016-10-28 16:00 | N | N | fall substation washing | Shunts |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32),ENMAX 31 B138-31.84 (ENMAX 31),ENMAX 24 B138-24.81 (ENMAX 24) | 2016-10-29 08:00 | 2016-10-29 13:00 | N | N | fall substation washing and hotspot repair SW82 at 31 sub | Line, Transformer, Circuit Breaker |  |  | Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2016-10-29 13:00 | 2016-10-29 16:00 | N | N | fall substation washing and hotspot repair SW86 at 31 sub | Line, Shunts, Transformer |  |  | For Information Only
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2016-10-30 08:00 | 2016-10-30 12:00 | N | N | fall substation washing and replace sleeves | Line, Transformer |  |  | For Information Only
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2016-10-30 12:00 | 2016-10-30 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds
ATCO, ALTALINK | 704L (252s Jarrow - 7L50D2),7L50 (526s Buffalo Creek - 7L50D2) | 2016-10-31 06:30 | 2016-11-20 18:30 | N | N | ATCO climbing inspection and replacing cross arms | Line |  | 7L50 & 704L - ATCO Advice - Climbing inspection and replacing cross arms on 7L50 | For Information Only
ATCO | 2075s ACF11 (2075s Newell),2075s 901T (2075s Newell) | 2016-10-31 07:00 | 2016-11-03 14:30 | N | Y | online pump addition/cold start upgrade | Shunts, Transformer |  | Online Pump Addition/Cold Start Upgrade SVC2 (20K02-ACF21) will remain in service while SVC1 (20K01-ACF11) is out of service. This will provide no restrictions to the DC or AC system while it is out of service. | 240 kV, For Information Only
ATCO, ALTALINK | 7L50 (757s Battle River - 526s Buffalo Creek) | 2016-10-31 07:00 | 2016-11-20 18:00 | N | Y | climbing Inspection and replace rotten cross arms | Line |  | Climbing Inspection and replace rotten cross arms. the line will be released daily line will also be subject to real time evaluation too. Along with the climbing inspection, planning on replacing rotten cross arms as we find them. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 837s 702T (837s Mahihkan) | 2016-10-31 07:00 | 2016-10-31 17:00 | N | N | move metering | Transformer |  | Move 702T metering. | For Information Only
ATCO | 791s 701T (791s Rainbow Lake) | 2016-10-31 07:00 | 2016-11-04 08:00 | N | N | remove sub feeder # 1, Bus T1 and T2 load on 702T | Transformer |  | Remove sub feeder # 1, Bus T1 and T2 load on 702T | For Information Only
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2016-10-31 07:30 | 2016-11-03 14:30 | N | Y | damper replacement | Line |  |  | For Information Only, 500 kV
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 138 kV North Bus | 2016-10-31 08:00 | 2016-10-31 16:00 | N | Y | fall substation washing | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41) | 2016-10-31 08:00 | 2016-11-04 16:00 | N | N | 138kV PT replacement for harmonic monitoring | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2016-10-31 08:00 | 2016-11-04 16:00 | N | N | (FATDSC) structure work | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 830L (562s Cypress - 840s McNeill Station) | 2016-10-31 09:30 | 2016-11-10 18:00 | Y | N | McNeil Station fall turnaround | Line |  | 562s830 (830L) - ATCO Advice - 840s MacNeil HVDC Station will be on its Fall 2016 T/A | Limits ATC
ALTALINK | 190L (17s Benalto - 320p Keephills),320p 652 (320p Keephills),320p 552 (320p Keephills) | 2016-10-31 12:30 | 2016-11-04 17:30 | N | Y | line maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 914L (86s Bigstone - 89s Ellerslie),86s 1252 (86s Bigstone) | 2016-10-31 12:30 | 2016-11-03 17:30 | N | Y | 240kV breaker maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2016-10-31 12:30 | 2016-10-31 14:00 | N | Y | trip testing of 245s56W breaker fail | Line |  | 245s87W Advice - Trip testing of 245s56W breaker fail - outage unavailable earlier in year. | Restricts Generation
ALTALINK | 9L (3s Horseshoe - 245s Seebe) | 2016-10-31 14:00 | 2016-10-31 15:30 | N | Y | trip testing of 245s56W breaker fail | Line |  | 3s6 Advice - Trip testing of 245s56W breaker fail - outage unavailable earlier in year. | Restricts Generation
EPCOR | 330P 12TC1 (330p Genesee),330p 805 (330p Genesee),330p 805D1 (330p Genesee),330p 805D2 (330p Genesee) | 2016-11-01 07:00 | 2016-11-03 17:00 | N | N | replace motor 805 nitrogen leak repair | Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation, 500 kV
EPCOR | 72CK13 (987s Clover Bar - Kennedale),Kennedale T1 (Kennedale) | 2016-11-01 07:00 | 2016-11-07 17:00 | N | N | cutover and commissioning of new transmission protection | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 755L (535s Joffre - 247s Piper Creek),535s Joffre 138kV Bus 4,535s C1 (535s Joffre) | 2016-11-01 07:00 | 2016-11-02 15:00 | N | N | string new 755L slack pan to "A" frame at 535s, stations crew to install new LAs | Line, Bus, Shunts |  | String new 755L slack pan to "A" frame at 535s. Stations crew to install new LAs | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 138S 1037 (138s Windy Flats),1037L (138s Windy Flats - 237s Foothills),266s 1037L FSC (266s SC1),237s 1037 (237s Foothills) | 2016-11-01 07:30 | 2016-11-12 17:30 | N | Y | damper replacements | Line, Switch, Shunts |  |  | 240 kV, Pre-Condition
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2016-11-01 07:30 | 2016-11-04 15:00 | N | N | structure upgrades | Line |  |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2016-11-01 08:00 | 2016-11-01 16:00 | N | N | test D21 TR diff relay | Transformer |  |  | For Information Only
ENMAX | 771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington),ENMAX 47 B138-771 (ENMAX 47),ENMAX 47 SW86 (ENMAX 47) | 2016-11-01 08:00 | 2016-11-01 16:00 | N | N | fall substation washing | Circuit Breaker, Line, Switch |  |  | Contingency Requires Mitigation
ENMAX | 1.5TR (ENMAX 1) | 2016-11-01 08:00 | 2016-11-04 16:00 | N | N | PRD deficiency fix | Transformer |  |  | For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2016-11-01 08:00 | 2016-11-02 16:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 16.1TR (ENMAX 16) | 2016-11-01 08:00 | 2016-11-01 16:00 | N | N | LTC oil Top up | Transformer |  |  | For Information Only
ALTALINK | 286s T2 (286s Yasa) | 2016-11-01 08:15 | 2016-11-01 17:45 | N | N | installing new transformer | Transformer |  |  | For Information Only
ALTALINK | 74s C1 (74s Janet) | 2016-11-01 08:30 | 2016-11-01 17:30 | N | N | 138kV breaker maintenance | Shunts |  |  | For Information Only
TRANSALTA | 59s 952 (59s Peigan) | 2016-11-01 10:30 | 2016-11-02 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2016-11-02 06:30 | 2016-11-04 18:00 | N | N | structure replacement | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31) | 2016-11-02 08:00 | 2016-11-02 16:00 | N | N | test D21 TR diff relay | Transformer |  |  | For Information Only
ENMAX | 47.1TR (ENMAX 47) | 2016-11-02 08:00 | 2016-11-02 16:00 | N | N | troubleshoot LTC alarm | Transformer |  |  | For Information Only
ATCO | 730s Rycroft 144kV Bus | 2016-11-02 12:00 | 2016-11-03 10:00 | N | N | 144kV bus outage between J1 and 7L10D1 | Bus |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 254s T1 (254s Coaldale) | 2016-11-02 13:00 | 2016-11-23 15:15 | N | N | add supervisory control to 254s1 | Transformer |  |  | For Information Only
ALTALINK | 535s 5452 (535s Joffre),535s 5552 (535s Joffre) | 2016-11-02 14:00 | 2016-11-07 17:30 | N | N | installation of jumpers onto 755L and on the surge arrestors and support beam | Circuit Breaker |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2016-11-02 22:00 | 2016-11-03 05:00 | Y | Y | forced outage | Line |  |  | Pre-Condition, Limits ATC, Creates Radial Feeds, 500 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2016-11-02 22:00 | 2016-11-03 05:00 | N | Y | 1201L forced outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 728L (405s Waupisoo - 353s Plamondon) | 2016-11-03 07:00 | 2016-11-03 18:00 | N | N | disconnect mobile sub from 728L | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 688L (653s Summit - 688DL23),653s 138-653.3TR (653s Summit),653s 84 (653s Summit),653s 688 (653s Summit) | 2016-11-03 07:00 | 2016-11-04 21:00 | N | Y | Enmax 653B138-653.3TR breaker maintenance | Line, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 103s 252 (103s Goose Lake) | 2016-11-03 08:00 | 2016-11-03 13:00 | N | Y | gas top up | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 34.2TR (ENMAX 34) | 2016-11-03 08:00 | 2016-11-03 12:00 | N | N | remove trojan oil processor | Transformer |  |  | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2016-11-03 08:00 | 2016-11-03 16:00 | N | N | test D21 TR diff relay | Transformer |  |  | For Information Only
ALTALINK | 103s 552 (103s Goose Lake) | 2016-11-03 13:01 | 2016-11-03 17:30 | N | Y | gas top up | Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ATCO | 946s 909 (946s Oakland) | 2016-11-03 14:20 | 2016-11-04 13:28 | N | Y | forced outage: gas issue | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 62s11 (62s Brazeau),62s12 (62s Brazeau) | 2016-11-03 23:00 | 2016-11-04 07:00 | N | Y | work on 4160V | Switch |  |  | Restricts Generation
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2016-11-04 08:00 | 2016-11-04 16:00 | N | N | fall substation washing and sheath test, DGA and LPOF | Line, Transformer |  |  | For Information Only
ALTALINK | 21s T1 (21s Marion) | 2016-11-04 08:15 | 2016-11-04 17:15 | N | N | repair leak in CT block | Transformer |  |  | For Information Only
ATCO | 939s 904 (939s Livock) | 2016-11-04 12:00 | 2016-11-04 14:00 | N | Y | emergency: low SF6 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 653s 83 (653s Summit),653s 84 (653s Summit),653s bus 2 (653s Summit) | 2016-11-05 06:00 | 2016-11-05 21:00 | N | Y | Enmax 653B138-653.2TR Breaker maintenance | Bus, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2016-11-05 06:30 | 2016-11-05 19:30 | N | N | structure replacement | Line |  |  | Creates Radial Feeds
ENMAX | 1.83L (ENMAX 1 - ENMAX 8) | 2016-11-05 08:00 | 2016-11-05 16:00 | N | N | sheath test, DGA LPOF | Line |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2016-11-05 08:00 | 2016-11-05 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2016-11-05 12:01 | 2016-11-05 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 653s 83 (653s Summit),653s 752 (653s Summit),653S bus 1 (653s Summit) | 2016-11-06 07:00 | 2016-11-06 21:00 | N | Y | Enmax 653B138-653.1TR Breaker maintenance | Bus, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2016-11-06 08:00 | 2016-11-06 14:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2016-11-06 14:00 | 2016-11-06 18:00 | N | N | fall substation washing | Line |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 2029s ACF23 (2029s Heathfield),2029s 1224 (2029s Heathfield) | 2016-11-07 07:00 | 2016-11-09 17:00 | N | Y | ACF23 outage and inspection at 2029s Heathfield, breaker1224 (10BF23) at 2029S | Shunts, Circuit Breaker |  | ACF23 outage and inspection @ 2029s Heathfield BREAKER 1224 (10BF23) @ 2029S breaker has found to have wiring issues from Siemens installation. requires outage to fix wiring before ground faults occur. fitler ( Type C) will be out of service. filter is only used during high power transfer, its redundant fitler will be available. during breaker outage, filter maintenance will be performed. | For Information Only
ALTALINK | 754L (437s Baymag - 754L72) | 2016-11-07 07:30 | 2016-11-10 07:30 | N | N | customer requested line move | Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2016-11-07 08:00 | 2016-11-11 16:00 | N | N | replace SW 83 | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2016-11-07 08:00 | 2016-11-11 16:00 | N | N | PRD Install and DGA samples | Transformer |  |  | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2016-11-07 08:00 | 2016-11-07 16:00 | N | N | fall substation washing | Shunts |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2016-11-07 08:00 | 2016-11-07 16:00 | N | N | oil sample 31.2TC | Transformer |  |  | For Information Only
ENMAX | 26.81L (ENMAX 54 - ENMAX 26) | 2016-11-07 08:00 | 2016-11-10 16:00 | N | N | work required on pole for FATD | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),420s 138kV Bus 1 (420s Broadmoor),420s T1 (420s Broadmoor) | 2016-11-07 08:00 | 2016-11-09 17:00 | N | N | commission new protections, install permanent risers between 420s852 and 420s4, install 420s1452 breaker | Line, Transformer, Bus |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 5L71 (Mica Creek - Nicola) | 2016-11-07 08:30 | 2016-11-07 09:00 | N | N | switching outage to close MCA 5D34 | Line |  |  | For Information Only
ENMAXEC | 383S Kettles Hill Windfarm | 2016-11-07 09:00 | 2016-11-07 10:00 | N | N | emergency DVAR outage for software upgrade | Station |  |  | For Information Only
ALTALINK | 212S Lacombe | 2016-11-07 09:30 | 2016-11-08 14:30 | N | N | RATD setting up 472s mobile at 212s - setup, test, commission mobile, roll out 25kV cables | Station |  |  | For Information Only
ALTALINK | 632PS (632s Russell) | 2016-11-07 10:00 | 2016-11-09 17:00 | N | Y | bushing change on the transformer. | Transformer |  | 632s2, 632s3 | Pre-Condition, For Information Only
ATCO | 7L33 (7L33D2 - 845s Big Mountain),845s 708 (845s Big Mountain),845s 707 (845s Big Mountain) | 2016-11-07 10:00 | 2016-11-09 10:15 | N | Y | 7L33 ARECL circuit deficiencies | Line, Circuit Breaker |  | 7L33 ARECL circuit deficiencies | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 186s C1 (186s Dry Creek) | 2016-11-07 11:30 | 2016-11-07 17:30 | N | N | gas top up | Shunts |  |  | For Information Only
ALTALINK | 190L (17s Benalto - 320p Keephills),320p 652 (320p Keephills),320p 552 (320p Keephills) | 2016-11-07 12:30 | 2016-11-10 17:30 | N | Y | line maintenance | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 733L (151s Strathmore - 428S Namaka) | 2016-11-08 00:15 | 2016-11-09 16:00 | N | N | forced outage | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2016-11-08 00:30 | 2016-11-08 04:30 | N | N | house move under 739 Line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 2029s 1200SST2 (2029s Heathfield),2029s 1215 (2029s Heathfield),2029s 1214 (2029s Heathfield) | 2016-11-08 07:00 | 2016-11-10 17:00 | N | Y | corona discharge @ 2029s Heathfield | Transformer, Circuit Breaker |  | Corona Discharge @ 2029s Heathfield HEAVY CORONA DISCHARGE ON CONNECTORS LOCATED NEAR 1215A, 1200SST2D1 AND 1200SST2. THEREFORE BUS OUTAGE IS REQUIRED TO CHECK CONDUCTOR SPACERS, BUS CONNECTORS AND CONNECTIONS WHICH ARE GENERATING CORONA (APPROX 6 LOCATIONS WHERE AUDIBLE CORONA IS GETTING LOUD) 1200SST2 WILL BE OUT OF SERVICE DURING THIS OUTAGE. ONLY ONE POWER SUPPLY WILL BE DOWN AT THIS TIME. REDUNDANT STATION SERVICE WILL BE IN SERVICE DURING THIS TIME. HEATHFIELD HAS 4 LATERALS THAT TIE BOTH 1200BS1 TO 1200BS2. ONLY ONE LATERAL WILL BE OUT OF SERVICE AT THIS TIME. | For Information Only, 500 kV
ATCO | 6L79 (711s Willingdon - 707s St.Paul),6L82 (700s Bonnyville - 707s St.Paul) | 2016-11-08 07:00 | 2016-11-09 17:00 | N | N | disconnect 6L79 north of Willingdon to St Paul and 6L82 south of Bonnyville to St Paul and de commission and turn over to distribution | Line |  | Disconnect 6L79 north of Willingdon to St Paul and 6L82 south of Bonnyville to St Paul and de commission and turn over to distribution, 711s radial fed from 709s | Firm Load Loss, Creates Radial Feeds
ALTALINK | 213S Hughenden,472L (213s Hughenden - 472AL tap) | 2016-11-08 08:00 | 2016-11-30 16:00 | N | N | remove old 25kV bus add new breaker 213s472 | Line, Station | remove old 25kV Bus, Add new breaker 213s472, Fortis salvage old feeder gear, AML Salvage old 25kV Bus Equipment |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 34.3TR (ENMAX 34) | 2016-11-08 08:00 | 2016-11-08 16:00 | N | N | oil sample 34.3TC | Transformer |  |  | For Information Only
ALTALINK | 995S Rangelandyarrow | 2016-11-08 08:30 | 2016-11-08 14:30 | N | N | customer request | Station |  |  | For Information Only
ALTALINK | 275s 2 (275s Jenner) | 2016-11-08 09:30 | 2016-11-08 14:30 | N | Y | change tank heaters | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 121s T2 (121s Brooks),795L (121s Brooks - 421s Hays),827L (121s Brooks - 28s West Brooks),121s Brooks 138kV South Bus | 2016-11-09 07:30 | 2016-11-10 17:30 | N | N | urgent repairs 121s2 motor mechanism | Bus, Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.2TR (ENMAX 37) | 2016-11-09 08:00 | 2016-11-09 16:00 | N | N | sample oil | Transformer |  |  | For Information Only
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House),262s 717E (262s Rocky Mountain House) | 2016-11-09 08:00 | 2016-11-09 16:00 | N | N | 262s717E gas leak | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 294s T1 (294s Brazeau Outlet Works),294s 201 (294s Brazeau Outlet Works) | 2016-11-09 08:00 | 2016-11-10 16:00 | N | N | work on 13.8kV bus and pothead testing | Transformer, Switch |  |  | For Information Only
ALTALINK | 742L (985s Exshaw - 754L72),754L (245s Seebe - 754L65A),754L (437s Baymag - 754L72) | 2016-11-10 07:30 | 2016-11-10 17:30 | N | N | customer requested line move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 38.2TR (ENMAX 38) | 2016-11-10 08:00 | 2016-11-10 16:00 | N | N | oil sample HV Bushings | Transformer |  |  | For Information Only
ALTALINK | 394s T1 (394s Empress) | 2016-11-10 10:00 | 2016-11-11 10:00 | N | N | 394s transferring station load from T1 | Transformer |  |  | For Information Only
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2016-11-11 08:00 | 2016-11-11 16:00 | N | N | fall substation washing, 1.84L sheath test and DGA LPOF | Line, Transformer |  |  | For Information Only
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2016-11-12 08:00 | 2016-11-12 16:00 | N | N | sheath test, DGA LPOF | Line |  |  | Pre-Condition, For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2016-11-12 08:00 | 2016-11-14 16:00 | N | N | emergency repair oil leak | Transformer |  |  | For Information Only
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),Enmax 36 MD138-36.5TR (ENMAX 36) | 2016-11-12 08:00 | 2016-11-12 16:00 | N | N | low SF6 Alarm 36B69-16.63/36.5TR | Line, Transformer, Switch |  |  | Pre-Condition, For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2016-11-12 08:00 | 2016-11-12 16:00 | N | N | O-ring replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2016-11-13 08:00 | 2016-11-13 16:00 | N | N | sheath test, DGA LPOF | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2016-11-13 08:00 | 2016-11-13 16:00 | N | N | O-ring replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2016-11-14 03:13 | 2016-11-17 14:07 | N | N | forced outage | Line |  | 180L forced out, AltaLink reported 8-10 structures damaged due to high winds. | For Information Only
EPCOR | E511s VictoriaT4 (511s Victoria) | 2016-11-14 06:00 | 2016-11-25 17:00 | N | N | ETM install | Transformer |  |  | For Information Only
EPCOR | RossdaleT4 (Rossdale) | 2016-11-14 07:00 | 2016-11-25 17:00 | N | N | cutting over and commissioning new Transformer Protection | Transformer |  |  | Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft) | 2016-11-14 07:00 | 2016-12-16 15:00 | N | N | line maintenance | Line |  |  | For Information Only
BCH | Cranbrook T2 | 2016-11-14 07:00 | 2016-11-25 16:00 | N | N | open end cranbrook T2 for BCH maintenance | Transformer |  |  | For Information Only
EPCOR | Kennedale T2 (Kennedale) | 2016-11-14 07:00 | 2016-11-20 17:00 | N | N | cutover and commissioning of new TX protection | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 2029s ACF14 (2029s Heathfield),2029s ACF11 (2029s Heathfield),2029s ACF12 (2029s Heathfield),2029s ACF13 (2029s Heathfield) | 2016-11-14 07:00 | 2016-11-18 17:00 | N | Y | multiple switches on filter bays have corona discharge to be cleaned up | Shunts |  | A, B and C type filters (ACF11, ACF12, ACF13) out of service. Shunt reactor will be out of service as well (ACF14). May cause power limit on EATL. system study to confirm. Multiple switches on filter bays have corona discharge to be cleaned up, 1219, 1220, 1221 breakers have been identified as having wiring issues and require Multiple fixes on these breakers. filter inspections on all filters required by Siemens warranty. | Pre-Condition, Limits Ratings, 500 kV
EPCOR | Strathcona T1 (Strathcona) | 2016-11-14 07:00 | 2016-11-18 17:00 | N | N | relay maintenance and breaker op-checks | Transformer |  |  | For Information Only
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2016-11-14 07:30 | 2016-11-25 17:30 | N | Y | install foundations for Hazelwood line in/out | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 38s T3 (38s East Edmonton) | 2016-11-14 07:30 | 2016-11-16 17:30 | N | N | T3 outage to connect 38s SS (38s16) to new buswork, close open point 'S' and install bird coverup | Transformer |  |  | For Information Only
ALTALINK | 929L (63s Red Deer - 74s Janet) | 2016-11-14 07:30 | 2016-11-25 17:30 | N | Y | install foundations for Hazelwood line in/out | Line |  |  | 240 kV, Pre-Condition
ATCO | 9L29 (946s Oakland - 963s Coyote Lake),946s 909 (946s Oakland) | 2016-11-14 08:00 | 2016-11-15 16:00 | N | Y | emergency repair for leaking SF6 gas problem | Circuit Breaker, Line |  |  | 240 kV, For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2016-11-14 08:00 | 2016-11-14 16:00 | N | N | DGA 21.1TC (W) & 21.1TC E | Transformer |  |  | For Information Only
ATCO | 2015s YEO | 2016-11-14 08:00 | 2016-11-15 16:00 | N | N | In service date: Nov 14, 2016. | Station
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36) | 2016-11-14 08:00 | 2016-11-18 16:00 | N | N | HV & LV bushing replacement | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALBIAN | 920s 901T (920s Jackpine) | 2016-11-14 08:00 | 2016-11-16 17:00 | N | Y | check and correct wiring in the sensing resistor cabinet of the NGR in 920S 901T and 902T and Shell will be working on the 72kV incoming circuit breakers charging motors | Transformer |  | Shell is requesting an outage and require a Condition Of Guarantee to check and correct some wiring in the sensing resistor cabinet of the NGR in 920S 901T and 902T. Shell will also be working on the 72kV incoming circuit breakers charging motors (cone coupling repair is required in all breakers due to fault design component). | 240 kV, Creates Radial Feeds
ATCO | 7L03 (749s Flyinshot Lake - 7L03D2),749S 144kv BUS | 2016-11-14 08:00 | 2016-11-17 16:00 | N | Y | 749S 7L03 reclosing changes | Line, Terminal Equipment |  | 749S 7L03 Reclosing Changes, 144kV ring will be open @ 749s, 823s Wapiti radial fed from 731s Elmworth | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2016-11-14 09:30 | 2016-11-18 17:30 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 39s T2 (39s Bickerdike),974L (39s Bickerdike - 310p Sundance),39s 29 (39s Bickerdike),39s 1052 (39s Bickerdike),39s 452 (39s Bickerdike),39s 852 (39s Bickerdike) | 2016-11-14 09:45 | 2016-11-17 15:38 | N | Y | forced outage,upgrading bus protections | Transformer, Circuit Breaker, Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 391s T1 (391s Balzac) | 2016-11-14 11:00 | 2016-11-14 14:30 | N | N | add supervisory control to 391s16 | Transformer |  |  | For Information Only
ALTALINK | 164S Empress Liquids,760AL (164s Empress Liquids - 760L41) | 2016-11-14 12:00 | 2016-11-23 14:00 | N | N | remove interconnection 6.9kV bus between 164s and ATCO Midstream | Station, Line |  | Remove interconnection 6.9kV bus between 164s and ATCO Midstream, remove PT1 and PT2, short circuit bus CTs and tie to ground and disconnect ground grid between 164s and ATCO Midstream. | Firm Load Loss, For Information Only
ATCO | 752S Albright & Wilson | 2016-11-15 07:00 | 2016-11-16 17:30 | N | N | GOI to connect 902s mobile sub secondarys to 25kV bus on 752S A&W | Station |  | GOI to connect 902s mobile sub secondarys to 25kV bus on 752S A&W Leave 510TD open on RTN (see HOP 2-37576 for phase checks) | For Information Only
ATCO | 715s 701T (715s Leming Lake),7L583 (970s Bourque - 715s Leming Lake) | 2016-11-15 07:30 | 2016-11-23 18:00 | N | Y | 701T and 7L583 OOS to replace 701TCS and connect line risers between 7L583 and 7L583/7L91 bypass | Transformer, Line |  | 701T and 7L583 OOS to replace 701TCS and connect line risers between 7L583 and 7L583/7L91 bypass, 7L583 is a Cold Lk cutplane | Pre-Condition
ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap) | 2016-11-15 09:00 | 2016-11-15 17:00 | N | N | MPLS upgrade @ 402s & 410s | Line |  |  | Firm Load Loss
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia),89s 908W (89s Ellerslie),816s PDS13 (816s Petrolia) | 2016-11-15 09:30 | 2016-11-15 17:30 | N | Y | adjusting switch | Switch, Line |  |  | 240 kV
REDDEER, ALTALINK | 464L (87s Gaetz - 209s Timberlands),768L (217s North Red Deer - 87s Gaetz),209s T1 (209s Timberlands) | 2016-11-15 11:00 | 2016-11-23 11:00 | N | N | maintain transmission facilities | Transformer, Line |  | 1. Redo the conduit duct sealant on ductbank 765L in the basement (third-party contractor). 2. Redo the conduit duct sealant on duckbank 464L in the basement (third-party contractor). 3. Redo the conduit duct sealant on ductbank 209T1 in the basement (third-party contractor). 4. Close conservator valve, drain down oil, Replace the secondary X3 bushing gasket, refill oil, restore valves (Cana HV). | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 377s 703E (377s Hardisty) | 2016-11-15 11:00 | 2016-11-17 18:00 | N | N | outage required for protection changes as part of 213s expansion project | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 946s 909 (946s Oakland) | 2016-11-15 16:00 | 2016-11-19 16:00 | N | Y | emergency repair for leaking SF6 gas problem | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 6L79 (711s Willingdon - 709s Vegreville),6L79 (711s Willingdon - 707s St.Paul) | 2016-11-16 07:00 | 2016-11-17 17:00 | N | N | decommission 6L79 & 711s 711s Willingdon sub | Line |  | Decommission 6L79 & 711s Willingdon sub Futher isolate 500PT1X, 500PT2X, 500PT2Y, and stn service secondaries as reqd | For Information Only
AESO | 892L (895s Suffield - 244s Bowmanton) | 2016-11-16 07:30 | 2016-11-18 17:30 | N | N | install anchors on str.# 144/892L and re-sag conductor | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 946s 903 (946s Oakland) | 2016-11-16 08:00 | 2016-11-16 17:00 | N | Y | emergency repair for leaking SF6 gas problem | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.7TR (ENMAX 1) | 2016-11-16 08:00 | 2016-11-16 16:00 | N | N | DGA HV bushings & TC | Transformer |  |  | For Information Only
ALTALINK | 776L (410s Josephburg - 308s Albchem Beaverhill Creek),308s 776W (308s Albchem Beaverhill Creek) | 2016-11-16 08:00 | 2016-11-17 16:30 | N | N | testing the breaker to insure that the new distance relay is working properly | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L79 (771s Veteran - 892s Ribstone Creek),7L79 (771s Veteran - 932s Pemukan) | 2016-11-16 10:00 | 2016-11-17 15:00 | N | N | to repair shot out and cracked insulators on 8 structures on the line | Line |  | This outage is required to repair shot out and cracked insulators on 8 structures on the line. (These bad insulators have been causing some trips on the line during inclement weather) This outage will result in a complete outage to the 892S Ribstone substation for the duration of the work. | Firm Load Loss, For Information Only
ALTALINK | 80AL (212s N.E.Lacombe - 958s West Lacombe) | 2016-11-16 11:00 | 2016-12-15 17:00 | N | N | crate open point 'Z', replace SS, add new 138kV bus and breakers, relocate 80AL to new A frame, and string in new 423L line into 212s | Line |  |  | Pre-Condition, For Information Only
ENMAX | 16.1TR (ENMAX 16) | 2016-11-17 08:00 | 2016-11-17 16:00 | N | N | LTC oil top up | Transformer |  |  | For Information Only
ALBIAN | 920s 902T (920s Jackpine) | 2016-11-17 08:00 | 2016-11-19 17:00 | N | Y | check and correct wiring in the sensing resistor cabinet of the NGR in 920S 901T and 902T. Shell will also be working on the 72kV incoming circuit breakers charging motors | Transformer |  | Shell is requesting an outage and require a Condition Of Guarantee to check and correct some wiring in the sensing resistor cabinet of the NGR in 920S 901T and 902T. Shell will also be working on the 72kV incoming circuit breakers charging motors (cone coupling repair is required in all breakers due to fault design component). | 240 kV, Creates Radial Feeds
ALTALINK | 879L (368s Burdett - 523s Bullshead) | 2016-11-17 08:30 | 2016-11-17 12:30 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie),253s 753W (253s Blackie) | 2016-11-17 08:30 | 2016-11-17 13:30 | N | N | add recloser controls to 253s753W | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 39s T2 (39s Bickerdike),39s 29 (39s Bickerdike),39s 1052 (39s Bickerdike),39s 452 (39s Bickerdike),39s 852 (39s Bickerdike) | 2016-11-17 15:39 | 2016-11-25 17:00 | N | Y | upgrading bus protections | Transformer, Circuit Breaker |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 752s 701T (752s Albright&Wilson) | 2016-11-18 07:00 | 2016-12-07 17:30 | N | N | replace 701TCS | Transformer |  | Replace 701TCS | For Information Only
ATCO | 2091s Thornton | 2016-11-18 08:00 | 2016-11-19 16:00 | N | N | In service date: Nov 18, 2016. | Station
ENMAXGPI | 134s Taber Wind Farm RTU/SCADA | 2016-11-18 08:00 | 2016-11-18 16:00 | N | N | modify RTU configuration | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat),523s 880 (523s Bullshead) | 2016-11-18 08:30 | 2016-11-18 13:30 | N | Y | re-wiring CTs and functional trips | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 850s 702T (850s Rainbow Cogen) | 2016-11-18 13:00 | 2016-12-01 04:15 | N | N | forced outage | Transformer
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2016-11-19 06:30 | 2016-11-20 16:00 | N | N | flood mitigation work by ISL for Zoo | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 879L (368s Burdett - 523s Bullshead),523s 879 (523s Bullshead) | 2016-11-19 07:30 | 2016-12-15 15:00 | N | N | create Open Point to disconnect 879L from 523s to facilitated the installation of 676L at 523s | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 34.1TR (ENMAX 34) | 2016-11-19 08:00 | 2016-11-19 18:00 | N | N | emergency repair oil leak | Transformer |  |  | For Information Only
ALTALINK | 523s C1 (523s Bullshead),523s 33 (523s Bullshead) | 2016-11-19 12:30 | 2016-11-19 17:30 | N | N | re-wiring CTs and functional trips | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 368s 879 (368s Burdett),244s Bowmanton 138kV Bus 4,244s 3152 (244s Bowmanton),244s 3252 (244s Bowmanton),244s 69 (244s Bowmanton) | 2016-11-19 13:30 | 2016-12-09 14:30 | N | Y | close open point 'K', and P and C work | Bus, Circuit Breaker, Switch |  | Existing 879L(244s- Open point 'K') will be returned once new GOI has been issued. | For Information Only
ALTALINK | 244s 2152 (244s Bowmanton),244s 2252 (244s Bowmanton),523s 676 (523s Bullshead) | 2016-11-19 16:45 | 2016-12-05 11:00 | N | N | close open point 'J' and P&C work | Circuit Breaker |  | Connect new 676L into 244s and 523s. | For Information Only
ALTALINK | 523s T1 (523s Bullshead) | 2016-11-20 01:00 | 2016-11-20 04:00 | N | N | re-wiring CTs | Transformer |  |  | For Information Only
ENMAX | 2.4TR (ENMAX 2) | 2016-11-20 08:00 | 2016-11-20 16:00 | N | N | DGA HV Bushings | Transformer |  |  | For Information Only
BCH | 5L75 (Revelstoke - Ashton Creek) | 2016-11-20 11:00 | 2016-11-20 16:00 | N | N | 5L75 out of service for blackstart testing | Line |  |  | For Information Only
EPCOR | Strathcona T2 (Strathcona) | 2016-11-21 07:00 | 2016-11-25 17:00 | N | N | relay maintenance and breaker op-checks | Transformer |  |  | For Information Only
EPCOR | Meadowlark M723 (Meadowlark) | 2016-11-21 07:00 | 2016-11-21 17:00 | N | N | repair broken skirt | Circuit Breaker |  |  | For Information Only
EPCOR | Woodcroft W722 (Woodcroft) | 2016-11-21 07:00 | 2016-11-21 17:00 | N | N | heater repair | Circuit Breaker |  |  | For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2016-11-21 08:00 | 2016-11-22 12:00 | N | Y | DGA sampling | Transformer |  |  | 240 kV, Overload
ENMAX | 28.2TR (ENMAX 28) | 2016-11-21 08:00 | 2016-11-25 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
ATCO | 789s 706C (789s Keg River) | 2016-11-21 08:00 | 2017-06-29 18:00 | N | N | forced out - repair oil leak on CT | Shunts |  |  | For Information Only
ATCO | Ruth Lake (848S) 703T, 704T, 901T, and 902T Overload Remedial Action Scheme | 2016-11-21 08:00 | 2016-12-02 16:00 | N | N | set-up / commission new RTU | RAS |  | Set-up / Commission new RTU: Visibility and Control will be limited during commission phases and while personal is on-site. Existing RTU will be put back in service overnight when no personal on-site. Power up and establish communication with new RTU. Pre-commission Points with HMI / STG. Complete End-to-end Commissioning with Operator (Nov 28 - Dec 2) Loss of visibility and control while downloading (approx. 1-2 minutes). | Impacts RAS
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),B138-3.84 (ENMAX 13) | 2016-11-21 08:00 | 2016-11-21 16:00 | N | N | 3.84L panel move required at 3 Sub | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 636L (746s Sherwood Park - 420s Broadmoor),420s 138kV Bus 1 (420s Broadmoor),420s T1 (420s Broadmoor) | 2016-11-21 08:00 | 2016-11-22 16:00 | N | N | commission new protections, install permanent risers between 420s852 and 420s4, install 420s1452 breaker | Transformer, Bus, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s T2 (17s Benalto),848L (17s Benalto - 848L490E),17s Benalto 138 kV Bus 4 | 2016-11-21 09:30 | 2016-11-25 15:30 | N | Y | add new 138kV Bus PT | Bus, Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2016-11-21 09:30 | 2016-11-25 17:30 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 1038L (138s Windy Flats - 237s Foothills) | 2016-11-21 18:00 | 2016-12-07 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2016-11-22 06:30 | 2016-12-04 14:30 | N | N | line rebuild | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 67s 225 (67s Stirling),225L (67s Stirling - 225s Magrath) | 2016-11-22 07:15 | 2016-11-23 17:00 | N | N | lightning arrestor installation at 67s | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 433L (291s Cochrane - T793s Horse Creek) | 2016-11-22 07:30 | 2016-11-29 17:30 | N | N | structure replacement | Line |  |  | Creates Radial Feeds
ALTALINK | 852s 252 (852s Round Hill) | 2016-11-22 09:00 | 2016-11-22 14:00 | N | Y | gas top up and replace burnt out cabinet heater | Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 528s Blue Trail Wind Farm RTU/SCADA | 2016-11-22 10:00 | 2016-11-22 11:00 | N | N | communication time delay | Terminal Equipment |  |  | Affects Visibility
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2016-11-22 12:00 | 2016-11-23 16:00 | N | Y | DGA Sampling | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 254s T1 (254s Coaldale),254s20 (254s Coaldale) | 2016-11-23 06:15 | 2016-11-23 17:45 | N | N | replaced railed 254s3 switch | Transformer, Switch |  |  | For Information Only
ENMAX | 14.4TR (ENMAX 14) | 2016-11-23 08:00 | 2016-11-23 16:00 | N | N | test D202 TR diff relay | Transformer |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),ENMAX 31 B138-31.84 (ENMAX 31) | 2016-11-23 08:00 | 2016-11-24 16:00 | N | N | breaker mechanism transducer calibration | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 420S Broadmoor | 2016-11-23 17:01 | 2016-11-25 13:00 | N | N | 25kV Bus 2 outage to close open point 'P' | Station |  |  | For Information Only
ATCO | 2029s 1201 (2029s Heathfield) | 2016-11-24 07:00 | 2016-11-25 16:00 | N | Y | 1201 breaker wiring fix @ 2029s Heathfield, breaker will be out of service at this time | Circuit Breaker |  | 1201 breaker wiring fix @ 2029s Heathfield, breaker will be out of service at this time. repair damaged wiring from heater/rubbing within breaker mechanical cabinets.required to remove wiring from pre made bundled wiring, re-commission wiring and inspection of apparatus.not known how many wire require re-termination or fixing. will only know once we start and perform a detailed inspection of the breaker. | 500 kV
ALTALINK | 600L (523s Bullshead - 404s Peace Butte) | 2016-11-24 07:30 | 2016-11-24 17:30 | N | N | stringing new 676L and 879L over 600L and re-wiring, functional tests on 523s600 | Line |  |  | For Information Only
ALTALINK | 723s T2 (723s Christina Lake),723s 252 (723s Christina Lake) | 2016-11-24 08:45 | 2016-11-24 17:00 | N | Y | gas top up | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 774s 601 (774s Monitor) | 2016-11-24 14:30 | 2016-12-24 16:00 | N | N | troubleshoot and test breaker close circuit | Circuit Breaker |  | Low risk since we have 6L12 is sectionalized BKR 601 T and O Trouble shoot and test bkr close circuit | For Information Only
ALTALINK | 749L (899s Edgerton - 7L749D3) | 2016-11-26 06:30 | 2016-11-27 18:30 | N | Y | line maintenance and mitigation | Line |  | Line maintenance and mitigation. HOLD OFFS ARE NOT AN OPTION Need to replace 15 poles with 2 H frames structure and most of the structures are right by the hill side and can only be accessed by track machine equipment. WILL BE REQUIRED TO BE ABLE TO RETURN EVENINGS IF NEEDED | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 26.83L (ENMAX 65 - ENMAX 26),ENMAX 65 B138-D85 (ENMAX 65),ENMAX 65 B138-D84 (ENMAX 65) | 2016-11-26 08:00 | 2016-11-26 16:00 | N | N | commissioning and testing breaker circuits | Line, Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 22.1TR (ENMAX 22) | 2016-11-26 08:00 | 2016-11-26 16:00 | N | N | tapchanger DGA sample required | Transformer |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),20.82L (ENMAX 21 - ENMAX 20) | 2016-11-27 07:00 | 2016-11-27 19:00 | N | N | remove Bell cell tower from structure | Line |  |  | Creates Radial Feeds
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2016-11-27 08:00 | 2016-11-27 16:00 | N | N | commissioning and testing breaker circuits | Circuit Breaker |  |  | For Information Only
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville),395s 77E (395s North Holden) | 2016-11-28 07:00 | 2016-12-06 17:30 | N | Y | replace 395s77E, 395s6 and line protections, add lightning arresters | Line, Circuit Breaker
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2016-11-28 07:00 | 2016-11-28 12:00 | N | Y | install bypass | Line |  | Install bypass | Pre-Condition
ENMAX | 14.1TR (ENMAX 14) | 2016-11-28 08:00 | 2016-11-28 16:00 | N | N | test D202 TR diff relay | Transformer |  |  | For Information Only
ENMAX | 30.2TR (ENMAX 30) | 2016-11-28 08:00 | 2016-11-28 16:00 | N | N | transformer maintenance DGA HV bushings | Transformer |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2016-11-28 08:00 | 2016-12-02 16:00 | N | N | HV bushing replacement | Line, Transformer |  |  | Creates Radial Feeds
EPCOR | 557s T1 (557s Castle Downs) | 2016-11-28 09:00 | 2016-11-28 15:00 | N | Y | cutover and commissioning of new DFR | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 151s T2 (151s Strathmore),733L (151s Strathmore - 428S Namaka),151s 733E (151s Strathmore) | 2016-11-28 09:30 | 2016-11-30 17:00 | N | N | replace 151s28 | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2016-11-28 09:30 | 2016-12-02 17:30 | N | Y | line maintenance | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 39s T1 (39s Bickerdike),39s Bickerdike 138kV Bus 1,39s Bickerdike 240kV Bus 1 | 2016-11-28 10:30 | 2016-12-02 15:45 | N | Y | upgrading bus protections | Transformer, Bus |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 159s T2 (159s Colinton) | 2016-11-28 12:30 | 2016-11-29 12:30 | N | N | doble test on H0 and X0 bushings | Transformer |  |  | For Information Only
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2016-11-28 17:00 | 2016-11-29 16:00 | N | Y | BCH work: expanded work zone for CBK 2CB7 replacement | Line |  |  | Pre-Condition
ENMAX | 14.2TR (ENMAX 14) | 2016-11-29 08:00 | 2016-11-29 16:00 | N | N | test D202 TR diff relay | Transformer |  |  | For Information Only
ALTALINK | 964L (244s Bowmanton - 251s Whitla) | 2016-11-29 08:00 | 2016-11-29 17:30 | N | Y | install marker cone on OHWS | Line |  |  | 240 kV
Lethbridge | 181s172 (181s Chinook),172L (370s North Lethbridge - 181s Chinook) | 2016-11-29 08:00 | 2016-11-30 17:00 | N | Y | repair gas leak on breaker | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ENMAX | 30.1TR (ENMAX 30) | 2016-11-29 08:00 | 2016-11-29 16:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO | 959S SVC (959s Lanfine) | 2016-11-29 08:30 | 2016-12-02 17:00 | N | Y | inspect TSC and TCR, install fiber for Xmer ETM. | Shunts |  | Inspect TSC and TCR, install fiber for Xmer ETM. | For Information Only
EPCOR | 557s T2 (557s Castle Downs) | 2016-11-29 09:00 | 2016-11-29 15:00 | N | Y | cutover and commissioniong of new DFR | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 252s 2 (252s Jarrow),704L (252s Jarrow - 7L50 tap) | 2016-11-29 09:00 | 2016-11-29 16:30 | N | N | Techs will be investigating the auto reclose malfunction of this breaker | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 720s 900D1 (720s Wabasca) | 2016-11-29 10:00 | 2016-11-29 15:00 | N | Y | repair motor drive on 900D1 at 720S Wabasca | Switch |  | Repair Motor Drive on 900D1 @ 720S Wabasca, decouple 900D1 during repairs, operate switch after repairs Breakers 901 and 902 be closed during T&O permit Switch is good condition, just need to replace the damaged motor and operate to confirm. | 240 kV, Pre-Condition
ALTALINK | 723s T2 (723s Christina Lake),723s 252 (723s Christina Lake) | 2016-11-29 11:15 | 2016-11-29 18:15 | N | Y | gas top up | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2016-11-30 07:30 | 2016-11-30 10:30 | N | N | DDR install | Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 715s 702T (715s Leming Lake),715s 700D1 (715s Leming Lake) | 2016-11-30 07:30 | 2016-12-14 15:00 | N | Y | 715s 702T and 144kV partial bus (split bus) out-of-service | Transformer, Switch |  | 702T and 144kV partial bus (split bus) OOS for 702TCS replacement, 7L91 will be open ended at 715s and tied to 5L583 (temp bypass), 25kV load will be transferred to 701T and 703T, Jumper J1 will be created to separate 702T and 702 from the 715S 144kV bus. This will be done via HOP 2-39702. If work cannot be safely done using a HOP, than a second 144kV partial bus (split bus) outage will be required to open the jumpers. Each 144kV bus outage will pose an islanding risk to Makeses as 7L95 and 7L66 will be on a long radial configuration to 700s Bonnyville | Pre-Condition, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31) | 2016-11-30 08:00 | 2016-11-30 16:00 | N | N | DGA sample 31.2TC | Transformer |  |  | For Information Only
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2016-11-30 09:00 | 2016-11-30 17:00 | N | Y | BCH work: test energization of the new CBK 2CB7/2D1CB7 | Line |  |  | Pre-Condition
EPCOR | CV5 (557s Castle Downs - 511s Victoria),Victoria V725 (Victoria) | 2016-11-30 09:00 | 2016-11-30 15:00 | N | Y | cutover and commissioniong of new DFR | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 405s C2 (405s Waupisoo) | 2016-11-30 11:00 | 2016-11-30 15:00 | N | N | DDR install | Shunts |  |  | For Information Only
ALTALINK | 702L (377s Hardisty - 137s Sedgewick),137s 702E (137s Sedgewick) | 2016-11-30 14:00 | 2016-12-15 18:00 | N | N | outage required for protections changes as part of 213s expansion project for setting changes on 702L | Line, Switch |  | Outage required for protections changes as part of 213s expansion project for setting changes on 702L | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 2005s 901 (2005s Secord) | 2016-12-01 07:00 | 2016-12-01 18:00 | N | Y | install Fort Hills RAS scheme, 240kV ring will be open | Circuit Breaker |  | Install Fort Hills RAS scheme, 240kV ring will be open @ 2005s. | 240 kV, Contingency Requires Mitigation
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2016-12-01 07:30 | 2016-12-03 17:30 | N | N | structure replacement | Line |  |  | Prevents Normal Events, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11) | 2016-12-01 08:00 | 2016-12-01 16:00 | N | N | DGA sample 11.1TC | Transformer |  |  | For Information Only
ALTALINK | 37s 87 (37s North Calder) | 2016-12-01 08:30 | 2016-12-01 15:30 | N | Y | EPCOR cutover and commissioning of new DFR | Switch |  | 37s87 (920L) Advice for EPCOR | 240 kV
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2016-12-01 09:00 | 2016-12-01 15:00 | N | Y | cutover and commissioning of new DFR | Line | 2. Studied with AIL = 10,920 MW, Sundance Generation = 2150 MW and full KEG generation. | 920L-W outage @ Castle Downs S/S and 37S - Cutover and Commissioning of new DFR | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 395s North Holden),395s 174W (395s North Holden) | 2016-12-01 11:00 | 2016-12-01 12:00 | N | N | trip test from new protections | Line, Circuit Breaker |  | 395s173 (174W Brkr) Advice - trip test from new 395s77E protections | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 2005s 902 (2005s Secord) | 2016-12-02 07:00 | 2016-12-02 18:00 | N | Y | install Fort Hills RAS scheme | Circuit Breaker |  | Install Fort Hills RAS scheme, 240kV ring will be open @ 2005s. | 240 kV, Contingency Requires Mitigation
ATCO | 808s 701T (808s Procter & Gamble) | 2016-12-02 07:00 | 2016-12-14 15:00 | N | N | replace 701TCS | Transformer |  | Replace 701TCS | For Information Only
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2016-12-02 09:00 | 2016-12-02 15:00 | N | Y | cutover and commissioniong of new DFR | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1045L (310p Sundance - 805s Jasper),310p 1752 (310p Sundance),310p 1652 (310p Sundance),805s J2406 (805s Jasper),805s J2407 (805s Jasper) | 2016-12-03 06:00 | 2016-12-05 17:00 | N | N | line maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 2005s 905 (2005s Secord) | 2016-12-03 07:00 | 2016-12-03 18:00 | N | Y | install Fort Hills RAS scheme, 240kV ring will be open @ 2005s | Circuit Breaker |  | Install Fort Hills RAS scheme, 240kV ring will be open @ 2005s. | 240 kV, Contingency Requires Mitigation, For Information Only
ENMAX | 36.5TR (ENMAX 36),16.63-36.5TR (ENMAX 36) | 2016-12-03 08:00 | 2016-12-03 16:00 | N | N | transformer maintenance | Transformer, Circuit Breaker |  |  | Overload
ATCO | 2005s 906 (2005s Secord) | 2016-12-04 07:00 | 2016-12-04 18:00 | N | Y | install Fort Hills RAS scheme, 240kV ring will be open @ 2005s | Circuit Breaker |  | Install Fort Hills RAS scheme, 240kV ring will be open @ 2005s | 240 kV, Pre-Condition
ALTALINK | 65s T3 (65s High River) | 2016-12-04 08:15 | 2016-12-04 13:45 | N | N | 25kV bus outage to safely disconnect UG cables from 65s53 | Transformer |  |  | Restricts Generation
ALTALINK | 65s T3 (65s High River) | 2016-12-04 13:01 | 2016-12-20 10:59 | N | N | disconnect UG cables from 65s53 and begin excavation work for 25kV bus expansion | Transformer |  |  | For Information Only
ALTALINK | 688L (199s East Airdrie - 688DL23) | 2016-12-05 06:30 | 2016-12-07 18:00 | N | Y | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 6L54 (736s Valleyviewp.R.O.P.L. - 734s Sturgeon),734s 603 (734s Sturgeon),734s 601 (734s Sturgeon) | 2016-12-05 07:00 | 2016-12-28 10:00 | N | N | converting to distribution level | Line, Circuit Breaker |  | 6L54 and the 734S 72 KV bus will be salvaged. 6L54 will be turned over to Distribution at the end of this project. | For Information Only
ATCO | 734s 701T (734s Sturgeon),734s 704 (734s Sturgeon) | 2016-12-05 07:00 | 2017-01-09 17:30 | N | N | converting to distribution level | Transformer, Circuit Breaker |  | 6L54 and the 734S 72 KV bus will be salvaged. 6L54 will be turned over to Distribution at the end of this project. | For Information Only
ALTALINK | 84L (35s Rundle - 33s Spray),33s 84 (33s Spray) | 2016-12-05 07:30 | 2016-12-08 18:30 | N | Y | replace OHSW with OPGW (str 1c to 4) | Line, Circuit Breaker |  |  | Overload, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2016-12-05 07:30 | 2016-12-07 17:30 | N | Y | QA/QC on recent damper replacements | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2016-12-05 08:00 | 2016-12-05 16:00 | N | N | maintenance work | Switch |  | 33s6 (Unit 2) TAU - Advice | Restricts Generation, For Information Only
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal) | 2016-12-05 08:00 | 2016-12-09 17:00 | N | Y | line mitigation repairs | Line |  | Line mitigation repairs, 861s, 724s, 829s, 754s, & 730s radial fed via 7L68 from 811S Clairmont | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 676L (523s Bullshead - 244s Bowmanton),879L (368s Burdett - 244s Bowmanton) | 2016-12-05 08:00 | 2016-12-06 16:00 | N | N | In service date:Dec 5, 2016. | Line
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2016-12-05 08:00 | 2016-12-22 16:00 | N | N | line protection upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2016-12-05 11:00 | 2016-12-05 14:00 | N | N | 262s T2 and 262s168N connect temporary cables | Transformer |  |  | For Information Only
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2016-12-05 14:00 | 2016-12-05 17:00 | N | N | 262s T1 & 262s63 connect temporary cables | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker),37s 72 (37s North Calder) | 2016-12-06 07:00 | 2016-12-07 17:00 | N | Y | line maintenance | Line, Switch |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant) | 2016-12-06 07:30 | 2016-12-18 13:00 | N | N | Structure Replacments, Re-Sag/Re-Dead End Center Phase Conductor between Str 101-107 | Line |  |  | Creates Radial Feeds
ALTALINK | 792L (191s N.W. Cardiff - 92s Viscount) | 2016-12-06 07:30 | 2016-12-06 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 138s 1652 (138s Windy Flats),138S R1 (138s Windy Flats) | 2016-12-06 08:00 | 2016-12-06 18:00 | N | Y | repair qualitrol (parts replacement) | Circuit Breaker, Shunts |  |  | Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 12.2TR (ENMAX 12) | 2016-12-06 08:00 | 2016-12-06 16:00 | N | N | LTC low oil alarm - requires top up | Transformer |  |  | For Information Only
ALTALINK | 33s3 (33s Spray) | 2016-12-06 08:00 | 2016-12-09 16:00 | N | N | maintenance work | Switch |  |  | Restricts Generation, For Information Only
ATCO | 786s 701 (786s High Level) | 2016-12-06 08:34 | 2016-12-22 12:00 | N | N | forced outage on 701A switch | Circuit Breaker |  |  | For Information Only
ALTALINK | 395s T1 (395s North Holden) | 2016-12-06 09:00 | 2016-12-06 09:15 | N | N | trip test 395s77E via T1 electrical protections | Transformer |  |  | For Information Only
ATCO | 752S Albright & Wilson | 2016-12-07 07:00 | 2016-12-07 17:30 | N | N | disconnect J2 and pack up mobile substation #3 | Station |  | Disconnect J2 Pack up mobile | For Information Only
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2016-12-07 07:30 | 2016-12-08 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
BLACKSPRING | 485s DVAR1 (485s Blacksprings) | 2016-12-07 08:00 | 2016-12-07 17:00 | N | N | repair | Shunts |  |  | For Information Only
ENMAX | 14.3TR (ENMAX 14) | 2016-12-07 08:00 | 2016-12-21 16:00 | N | N | protection upgrade, replace diff relay | Transformer |  |  | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2016-12-07 08:00 | 2016-12-07 12:30 | N | Y | repair of an oil leak on a meter located at the Great Falls substation | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 12.1TR (ENMAX 12) | 2016-12-07 08:00 | 2016-12-07 16:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO, ALTALINK | 948L (650s Hansman Lake - 863s Paintearth),9L948 (650s Hansman Lake - 863s Paintearth) | 2016-12-07 09:30 | 2016-12-08 14:30 | N | Y | emergency outage to repair switch 9L948D4 at 863s Paintearth | Line |  | ATCO Electric is Requesting an emergency outage to repair Switch 9L948D4 at 863S Paintearth. The hot spot is hot enough that is should be repaired within a week. | 240 kV, Overload, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2016-12-07 23:00 | 2016-12-08 03:00 | N | N | maintenance | Switch |  | TAU Requested Generator Outage | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2016-12-08 03:00 | 2016-12-08 07:00 | N | Y | maintenace | Switch |  |  | Restricts Generation
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),731L (420s Broadmoor - 746L8A) | 2016-12-08 07:30 | 2016-12-09 17:30 | N | N | install new structure to facilitate future pipe rack under line | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1071L (205s Castle Rock Ridge - 312s Fidler) | 2016-12-08 07:30 | 2016-12-11 17:30 | N | Y | QA/QC on recent damper replacements | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.3TR (ENMAX 2) | 2016-12-08 08:00 | 2016-12-08 16:00 | N | N | urgent: Oil Level Alarm. Check reversing switch | Transformer |  |  | For Information Only
ENMAX | 36.1TR (ENMAX 36) | 2016-12-08 11:00 | 2016-12-08 16:00 | N | N | test ASEA RADSE relay and SEL 351 | Transformer |  |  | For Information Only
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2016-12-09 07:30 | 2016-12-15 18:30 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2016-12-09 08:00 | 2016-12-09 12:00 | N | N | 262s T1 and 262s63 disconnect temporary cables | Transformer |  |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2016-12-09 08:00 | 2016-12-09 12:00 | N | N | 10.1TC Oil Top Up | Transformer |  |  | For Information Only
ATCO, ALTALINK | 948L (650s Hansman Lake - 863s Paintearth),9L27 (863s Paintearth - 755s Cordel) | 2016-12-09 11:00 | 2016-12-09 12:00 | N | N | urgent work - add jumpers to bypass failed switches | Line |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 865L (216s Knightsbridge - 38s East Edmonton) | 2016-12-09 11:30 | 2016-12-11 17:30 | N | N | kick saddles on 731L and install new structure inline to allow for new pipe rack underneath line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 10.2TR (ENMAX 10) | 2016-12-09 12:00 | 2016-12-09 16:00 | N | N | 10.2TC Oil Top Up | Transformer
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2016-12-09 13:00 | 2016-12-09 17:00 | N | N | 262s T2 and 262s168N disconnect temporary cables | Transformer |  |  | For Information Only
ALTALINK | 28s 12 (28s West Brooks) | 2016-12-09 13:40 | 2016-12-10 16:10 | N | N | emergency repair | Circuit Breaker |  |  | 240 kV
ENMAX | 15.1TR (ENMAX 15) | 2016-12-10 08:00 | 2016-12-10 12:00 | N | N | oil top pp. check reversing switch | Transformer
ENMAX | 21.1C (ENMAX 21) | 2016-12-10 08:00 | 2016-12-16 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2016-12-10 12:00 | 2016-12-10 16:00 | N | N | oil top pp. check reversing switch | Transformer |  |  | For Information Only
ENMAX | 32.3TR (ENMAX 32) | 2016-12-11 08:00 | 2016-12-11 16:00 | N | N | low oil levels require top up | Transformer |  |  | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2016-12-11 08:00 | 2016-12-11 16:00 | N | N | oil top up | Transformer |  |  | For Information Only
BCH | 1L274 (Line Creek - Elkford) | 2016-12-12 07:00 | 2016-12-13 18:00 | N | N | BC Hydro work | Line |  |  | Pre-Condition, Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36) | 2016-12-12 08:00 | 2016-12-12 16:00 | N | N | test ASEA RADSE Relay | Transformer |  |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2016-12-12 08:00 | 2016-12-12 16:00 | N | N | LTC low oil repair | Transformer |  |  | For Information Only
ATCO | 7L128 (963s Coyote Lake - 802s Michichi Creek),802s 704 (802s Michichi Creek) | 2016-12-12 08:30 | 2016-12-14 15:00 | N | N | 802S Michichi Creek, 7L128 CT Ratio changes | Circuit Breaker, Line |  | 802S Michichi Creek, 7L128 CT Ratio Changes.... CT Ratio Changes 704CT - 7L128 | Firm Load Loss, Creates Radial Feeds
ATCO | 834s 708 (834s Wesley Creek) | 2016-12-12 09:00 | 2016-12-14 12:00 | N | Y | forced outage - low SF6 | Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2016-12-12 09:30 | 2016-12-15 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2016-12-13 06:30 | 2016-12-21 18:00 | N | N | line rebuild | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal) | 2016-12-13 08:00 | 2016-12-16 17:00 | N | Y | Line mitigation repairs, 861s, 724s, 829s, 754s, & 730s radial fed via 7L68 from 811S Clairmont | Line |  | Line mitigation repairs, 861s, 724s, 829s, 754s, & 730s radial fed via 7L68 from 811S Clairmont | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 180s T2 (180s Cope Creek) | 2016-12-13 08:00 | 2016-12-13 17:30 | N | N | repair T2 oil leak | Transformer |  |  | For Information Only
ALTALINK | 396s C1 (396s Pincher Creek),396s 56 (396s Pincher Creek) | 2016-12-13 09:00 | 2016-12-13 17:00 | N | N | setting changes to C1 protection | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 288s T2 (288s Wolf Creek) | 2016-12-13 09:30 | 2016-12-15 10:00 | N | Y | investigate and repair oil leak | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 37 (39s Bickerdike) | 2016-12-13 11:00 | 2016-12-13 14:00 | N | N | gas top up | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 445L (183s Underwood - 170s Pike) | 2016-12-13 12:30 | 2016-12-13 17:30 | N | N | replace tank heaters on 183s445 CB | Line |  |  | For Information Only
ENMAX | 41.2TR (ENMAX 41) | 2016-12-14 08:00 | 2016-12-14 16:00 | N | N | test D21 differential relay | Transformer |  |  | For Information Only
ENMAX | 65.1 TR (ENMAX 65),ENMAX 65 240kV South Bus,ENMAX 65 138 kV South Bus | 2016-12-14 08:00 | 2016-12-14 16:00 | N | Y | re-install vertical bus pieces and test protection | Bus, Transformer |  | 65.1TR. 65s 138KV South Bus - Re-install vertical bus pieces on 138kV bus jaw side of SW81. 138kV back to normal on re-energization. Function test diff circuits for D130 and D133 | 240 kV, Contingency Requires Mitigation
ALTALINK | C65s 65.1TR - Enmax Info | 2016-12-14 08:00 | 2016-12-14 16:00 | N | N | ENMAX maintenance | Terminal Equipment |  | C65s 65.1TR - Enmax Info - ENMAX maintenance (Re-install vertical bus pieces on 138kV bus jaw side of SW81) | For Information Only
ALTALINK | 632s 152 (632s Russell) | 2016-12-14 08:30 | 2016-12-14 13:00 | N | N | replace tank heaters | Circuit Breaker |  | 632s152 - GOI - Replace tank heaters on 632s152 | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 412L (396s Pincher Creek - 632s Russell),632s 412 (632s Russell) | 2016-12-14 13:00 | 2016-12-14 17:00 | N | N | replace center phase heater on 632s412 | Line, Circuit Breaker |  | 632s412(412L) - GOI - Replace center phase heater on 632s412 | Pre-Condition, Creates Radial Feeds
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2016-12-14 16:01 | 2017-04-07 17:00 | N | N | (FATDSC) - install 65MD138-54.81, SW 89, 65B138-D83 | Circuit Breaker |  |  | Pre-Condition
AESO | 1L274 (B1s BCH Natal - 1D1L274) | 2016-12-15 07:00 | 2016-12-15 17:00 | N | N | BC Hydro work | Line |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 244s 2152 (244s Bowmanton) | 2016-12-15 10:00 | 2016-12-15 12:00 | N | N | replace failed tank heaters | Circuit Breaker |  |  | For Information Only
ALTALINK | 244s 2652 (244s Bowmanton) | 2016-12-15 12:30 | 2016-12-15 14:30 | N | N | replace failed tank heaters | Circuit Breaker |  |  | For Information Only
ALTALINK | 244s 3152 (244s Bowmanton) | 2016-12-15 15:00 | 2016-12-15 17:00 | N | N | replace failed tank heaters | Circuit Breaker |  |  | For Information Only
ALTALINK | 989L (310p Sundance - 77s Sagitawah) | 2016-12-16 07:30 | 2016-12-21 18:30 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2016-12-16 08:00 | 2016-12-16 16:00 | N | N | TLC top up (alarming) | Transformer |  |  | Pre-Condition, Overload
ENMAX | 26.81L (ENMAX 54 - ENMAX 26) | 2016-12-16 08:00 | 2016-12-16 16:00 | N | N | investigate protection alarm | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s T1 (77s Sagitawah),989L (310p Sundance - 77s Sagitawah),77s Sagitawah 240 kV West Bus | 2016-12-16 09:00 | 2016-12-16 18:00 | N | N | top up oil on 77s 26 circuit breaker and hot spot on 77s22 | Transformer, Bus, Line |  |  | 240 kV, Pre-Condition
ENMAX | 37.2TR (ENMAX 37) | 2016-12-17 08:00 | 2016-12-17 10:00 | N | N | roxtek plug installation | Transformer |  |  | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2016-12-17 11:00 | 2016-12-17 14:00 | N | N | roxtek plug installation | Transformer |  |  | For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2016-12-17 14:00 | 2016-12-17 17:00 | N | N | roxtek plug installation | Transformer |  |  | For Information Only
ENMAX | 36.1TR (ENMAX 36) | 2016-12-18 08:00 | 2016-12-18 16:00 | N | N | DGA samples required on HV bushings | Transformer |  |  | For Information Only
ALTALINK | 86s T1 (86s Bigstone),804L (86s Bigstone - 40s Wetaskiwin),805L (964s Pigeon Lake - 86s Bigstone) | 2016-12-18 08:00 | 2016-12-18 17:00 | N | Y | repairing hotspot on switch 86s804X | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ENMAX | 36.5TR (ENMAX 36),16.63-36.5TR (ENMAX 36) | 2016-12-18 08:00 | 2016-12-18 16:00 | N | N | transformer maintenance and checks | Transformer, Circuit Breaker |  |  | Overload
ALTALINK | 433L (291s Cochrane - T793s Horse Creek) | 2016-12-18 13:30 | 2016-12-19 17:30 | N | N | insulator replacement | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2016-12-19 07:30 | 2016-12-21 18:00 | N | N | component replacement including insulators, downleads, crossarms | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 715s 702T (715s Leming Lake) | 2016-12-19 08:00 | 2016-12-19 12:00 | N | N | oil leak, risk of environmental spill and/or 702T trip | Transformer |  |  | For Information Only
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2016-12-19 08:30 | 2016-12-20 18:00 | N | N | Line maintenance | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L127 (774s Monitor - 932s Pemukan),774s 703 (774s Monitor) | 2016-12-19 09:00 | 2016-12-19 15:00 | N | N | emergency 703CT ratio change/cable removal | Line, Circuit Breaker |  | Emergency 703CT Ratio Change/Cable removal | Firm Load Loss, Creates Radial Feeds
ATCO | 786s SVC (786s High Level),7L133 (786s High Level - 828s Sulphur Point),786s 701T (786s High Level) | 2016-12-19 10:00 | 2016-12-19 15:00 | N | Y | required to isolate 700BS1 bus to create jumper J1 | Shunts, Line, Transformer |  | Required to Isolate 700BS1 bus to create jumper J1 to repair 701A @ 786S, 786S SVC OOS and 7L133 open ended @ 786s High Level All Load transferred to 702T | Pre-Condition, Over/Under Voltage
ALTALINK | 77s T1 (77s Sagitawah),989L (310p Sundance - 77s Sagitawah),77s Sagitawah 240 kV West Bus | 2016-12-19 12:00 | 2016-12-19 18:00 | N | N | top up oil on 77s 26 circuit breaker and hot spot on 77s22 | Transformer, Bus, Line |  |  | 240 kV, Pre-Condition
ATCO | 715s 703T (715s Leming Lake) | 2016-12-19 13:00 | 2016-12-22 17:00 | N | N | install differential protection, protection upgrade | Transformer |  | Install differential protection, Protection upgrade - Tie 700BS Lockout into 705 Trip and Block Close, 702T and 701T will carry 703T load For duration of work. | For Information Only
ATCO | 786s 701T (786s High Level),786s 701A (786s High Level) | 2016-12-19 15:00 | 2016-12-22 12:00 | N | N | replace & commission failed switch 701A and epair 701A broken insulator stack | Transformer, Switch |  | Replace & Commission Failed Switch 701A....Repair 701A Broken Insulator Stack | For Information Only
ATCO | 840S McNeill Station | 2016-12-20 07:00 | 2016-12-21 17:00 | N | Y | outage to CC800WP Bus (CC904T) | Station |  | CC800WP must be taken out of service to fix 87/800WP. | Limits ATC
ENMAX | 21.1C (ENMAX 21) | 2016-12-20 08:00 | 2017-01-03 15:22 | N | N | forced outage | Shunts |  |  | For Information Only
ALTALINK | 237s 2152 (237s Foothills) | 2016-12-20 09:00 | 2016-12-20 13:00 | N | N | replace SF6 gauges on CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 826s 701 (826s Marguerite Lake) | 2016-12-20 09:00 | 2016-12-21 16:00 | N | N | low gas pressure repairs | Circuit Breaker |  | We are planning to do Emergency BREAKER 701 LOW GAS PRESSURE Repairs at 826S MARGUERITE LAKE December 20th -21nd, 2016. 09:00 to 16:00 In order to repair the Breaker - Breaker 701 will be OOS for the duration of the work, will require 24 hour wait time for gas sampling prior to re-energization after filling - 144kV ring bus will be opened for the duration of the work | Contingency Requires Mitigation
ATCO | 932s 701 (932s Pemukan) | 2016-12-20 09:00 | 2016-12-20 12:00 | N | N | CT ratio change | Circuit Breaker |  | 932s - 701CT Ratio Change | Contingency Requires Mitigation
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2016-12-20 09:30 | 2016-12-20 17:00 | N | N | protection setting change | Line |  | 526L(268s - A743s) - Open Breaker Advice - protection setting change 526L will need to be open ended @ 268s for the techs to implement permanent settings change on B21/96/25SC/79/L3; once the settings have been changed at both ends and the RTU updated then 526L220 will be opened to sectionalize 526L; 526L220 will become a Normally Open switch with alternate settings available for when the switch is required to be closed for future outages in the area. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T3 (65s High River) | 2016-12-20 11:00 | 2016-12-20 16:00 | N | Y | safely re-connect UG cables to 65s53 and restore transformer | Transformer |  | 65s T3 (Tx18516) & 25kV South Bus GOI - Bus outage to safely re-connect UG cables to 65s53 & restore T3 over the holidays. | Restricts Generation, For Information Only
ATCO | 932s 702 (932s Pemukan) | 2016-12-20 12:00 | 2016-12-20 15:00 | N | N | CT ratio change | Circuit Breaker |  | 932s - 702CT Ratio Change | Contingency Requires Mitigation
ALTALINK | 237s 2452 (237s Foothills) | 2016-12-20 12:30 | 2016-12-20 14:30 | N | N | replace SF6 gauges on CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 932s 703 (932s Pemukan) | 2016-12-21 09:00 | 2016-12-21 13:00 | N | N | 932s - 703CT ratio change | Circuit Breaker |  | 932s - 703CT Ratio Change | Firm Load Loss, Creates Radial Feeds
ATCO | 786s SVC (786s High Level),7L133 (786s High Level - 828s Sulphur Point),786s 701T (786s High Level) | 2016-12-21 12:00 | 2016-12-21 17:00 | N | Y | required to Isolate 700BS1 bus to restore jumper J1 | Line, Shunts, Transformer |  | Required to Isolate 700BS1 bus to restore jumper J1 | Pre-Condition, Over/Under Voltage
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2016-12-22 08:00 | 2016-12-23 12:40 | N | N | forced outage | Line |  |  | For Information Only
ATCO | 794s 701T (794s Valleyview) | 2016-12-28 08:00 | 2016-12-29 16:00 | N | N | replace over current relay | Transformer |  |  | For Information Only
ENMAX | 11.3TR (ENMAX 11) | 2016-12-28 08:00 | 2016-12-28 16:00 | N | N | top up the tap changer oil level | Transformer |  |  | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2016-12-29 07:00 | 2016-12-29 16:00 | N | Y | emergency line repair | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2017-01-04 06:30 | 2017-01-11 18:00 | N | N | Line rebuild | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T3 (65s High River) | 2017-01-04 07:00 | 2017-01-30 14:30 | N | N | south 25KV bus upgrades and expansion, install new Fortis feeders for 63L, 2361L, 2362L and AMI cables upto fenceline | Transformer |  |  | Restricts Generation
ALTALINK | 1106L (ENMAX 65 - 237s Foothills) | 2017-01-04 07:30 | 2017-02-02 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 1037L (237s Foothills - 138 Windy Flats) | 2017-01-04 07:30 | 2017-03-03 17:30 | N | Y | damper replacement | Line |  |  | 240 kV
ATCO | 7L583 (970s Bourque - 715s Leming Lake) | 2017-01-04 10:00 | 2017-01-04 13:00 | N | Y | remove remnants of bypass and salvage bypass structures | Line |  | Remove remnants of bypass and salvage bypass structures | Pre-Condition, Restricts Generation
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2017-01-04 14:00 | 2017-01-04 17:00 | N | Y | remove remnants of bypass and salvage bypass structures | Line |  | Remove remnants of bypass and salvage bypass structures | Pre-Condition, Restricts Generation
ALTALINK | 1043L (320p Keephills - 816s Petrolia) | 2017-01-05 07:30 | 2017-02-17 17:30 | N | Y | damper replacements | Line |  |  | 240 kV
ALTALINK | 853L (504s Queenstown - 853L76A) | 2017-01-05 07:30 | 2017-03-20 16:30 | N | N | line rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek) | 2017-01-05 07:30 | 2017-01-05 17:30 | N | N | str.44 insulators replacment, str.73 conductor repair | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26) | 2017-01-05 08:00 | 2017-01-06 16:00 | N | N | SF6 gas sample and maintenance | Line, Transformer |  | SF6 gas sample 26B138-26.83, doble 26PT138-Z32. HV SW/MD maintenance 26.2MD, SW81, SW82, SW83 | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 183s 445 (183s Underwood) | 2017-01-06 08:30 | 2017-01-06 17:30 | N | N | replace tank heaters | Circuit Breaker |  |  | For Information Only
ALTALINK, ENMAX | 23.80L (74s Janet - ENMAX 23),74s 23.80W (74s Janet) | 2017-01-08 09:00 | 2017-01-08 13:00 | N | N | add supervisory control to recloser | Circuit Breaker, Line |  | add supervisory control to recloser, coordinated with ENMAX's 23.80L outage. | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 2029s 1208 (2029s Heathfield) | 2017-01-09 07:00 | 2017-01-13 17:00 | N | Y | breaker wiring repairs | Circuit Breaker |  | 1208 breaker wiring repairs, 12L85 and ACF2 radial fed | Pre-Condition, For Information Only, 500 kV
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2017-01-09 07:30 | 2017-01-12 17:30 | N | N | replace the 138kV CTs on C1 | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 765L (74s Janet - 151s Strathmore),74s 765E (74s Janet) | 2017-01-09 08:30 | 2017-01-09 13:30 | N | N | add supervisory control to recloser | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 1L275 (799s Coleman - Natal) | 2017-01-09 09:00 | 2017-01-13 17:00 | N | Y | required for BC maintenance on 60 kV at Natal | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan) | 2017-01-09 09:30 | 2017-01-19 10:00 | N | N | component replacements | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2017-01-09 09:30 | 2017-01-12 17:00 | N | Y | replace PT's 63s38 | Line |  |  | 240 kV
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2017-01-09 09:30 | 2017-01-13 17:30 | N | N | pole maintenance | Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 286s 352 (286s Yasa) | 2017-01-09 11:00 | 2017-01-09 17:30 | N | N | top up the breaker with gas | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 789s 701R (789s Keg River),789s 705 (789s Keg River) | 2017-01-10 07:00 | 2017-01-17 10:10 | N | N | install new 705 CT | Shunts, Circuit Breaker |  | Install new 705CT, 701R will be unavailable for dispatch | For Information Only
ATCO | 732s 902T (732s Mitsue) | 2017-01-10 17:00 | 2017-03-27 10:00 | N | Y | forced outage. transformer tap changer | Transformer |  | 902T Tap changer blew up Jan 10. Estimated time of repair is presently Apr 30. | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCOP | OWF1 Oldman 2 Wind Farm 1 | 2017-01-11 07:00 | 2017-01-11 15:00 | N | N | software update on automatic voltage control | Unit |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2017-01-11 08:00 | 2017-01-11 16:00 | N | N | urgent low SF6 gas | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO | 749s 701 (749s Flyingshot Lake) | 2017-01-12 08:00 | 2017-01-12 16:00 | N | N | remove maintenance switch.144kV ring bus will be open at 749s | Circuit Breaker |  | Remove Maintenance Switch (close circuit modification), 144kV ring will be open | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
MONTANA | MATL (120s Picture Butte - Montana) | 2017-01-13 07:30 | 2017-01-15 17:30 | N | Y | align with 1201L outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook),520s T1 (520s Bennett) | 2017-01-13 07:30 | 2017-01-15 17:30 | Y | Y | urgent: remove the 20kV Bus & repair leaks on R7 and testing of the in service T1 units | Transformer, Line |  |  | Pre-Condition, Limits ATC, Creates Radial Feeds, 500 kV
ATCO | 7L749 (716s Lloydminister - 7L749D2) | 2017-01-14 07:00 | 2017-01-15 18:00 | N | Y | line maintenance and mitigation | Line |  | Line maintenance and mitigation. Hold Offs are not an option Need to replace structures that are right by the hill side and can only be accessed by track machine equipment. WILL BE REQUIRED TO BE ABLE TO RETURN EVENINGS IF NEEDED | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32),32.82L (ENMAX 54 - ENMAX 32),54B138-32.82 (ENMAX 54),32.83L (ENMAX 32 - ENMAX 40),ENMAX 32 SW89 (ENMAX 32) | 2017-01-14 08:00 | 2017-01-14 16:00 | N | N | SF6 gas sample, doble, HV SW/MD maintenance | Line, Transformer, Circuit Breaker, Switch |  | SF6 Gas Sample 54B138-32.82, Doble 32B138-32.83, HV SW/MD Maintenance 32.1MD | Creates Radial Feeds
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37),74s 37.82W (74s Janet) | 2017-01-15 08:30 | 2017-01-15 13:30 | N | N | add supervisory control to recloser | Line, Circuit Breaker |  |  | Pre-Condition, Creates Radial Feeds
EPCOR | 511s Victoria T1 (511s Victoria) | 2017-01-16 07:00 | 2017-01-20 17:00 | N | N | new switchgear project | Transformer |  |  | For Information Only
EPCOR | 330p 1203 (330p Genesee) | 2017-01-16 07:00 | 2017-01-16 17:00 | N | Y | breaker inspection | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, 500 kV
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft T1 (Woodcroft) | 2017-01-16 07:00 | 2017-01-20 17:00 | N | N | temperature gauge install | Transformer, Line |  |  | For Information Only
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2017-01-16 07:30 | 2017-01-19 17:30 | N | N | replace the 138kV CTs on C2 | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX, ALTALINK | 30.81L (42s Sarcee - ENMAX 30) | 2017-01-16 08:00 | 2017-01-20 17:00 | N | Y | SWCRR: installation of 1 double termination wooden pole and line jumpers | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 9L20 (766s Nevis - 755s Cordel),755s 901 (755s Cordel),755s 906 (755s Cordel) | 2017-01-16 08:00 | 2017-01-18 17:00 | N | Y | 755S - 901 breaker SF6 GL315 partial testing bkr 901 maintenance | Circuit Breaker, Line |  | 755S - 901 BREAKER SF6 GL315 PARTIAL TESTING Bkr 901 Maintenance RFL Relay Commissioning - 9L20 21A Protection at 755S Cordel & 766S Nevis - Operate breakers / MOD's on both ends to test status to new relays | 240 kV, Pre-Condition, Overload
Saskpower | SASK POWER P2C | 2017-01-16 08:00 | 2017-01-19 18:00 | N | N | IP - outage needed for RAS commissioning and spar changes | Line |  |  | Limits ATC
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24) | 2017-01-16 08:00 | 2017-01-16 16:00 | N | N | HV SW/MD maintenance 24.2TR | Transformer, Line |  |  | For Information Only
BCH | 2L294 (Nelway - A.A. Lambert) | 2017-01-16 09:00 | 2017-01-17 17:00 | N | Y | structure and timber replacements | Line |  |  | Pre-Condition
ATCO | 700s 702T (700s Bonnyville) | 2017-01-17 07:00 | 2017-01-30 17:00 | N | N | close jumper J2 (ties 500BS2 to 500BS3), rebuild 504 and 505 structures, recable 702T, 702TCS, 502TD | Transformer |  | Close jumper J2 (ties 500BS2 to 500BS3), rebuild 504 and 505 structures, recable 702T, 702TCS, 502TD, all 702T load on 703T. | For Information Only
EPCOR | 113s T2 (113s Inland Cement) | 2017-01-17 07:00 | 2017-01-18 17:00 | N | N | isolation of T2 at 113s Inland (113s Inland -711L) for critical repairs to protection equipment | Transformer |  | isolation of T2 @ Inland  113s (711L) for critical repairs to protection equipment | For Information Only
ALTALINK | 199L (268s Whitecourt - 199L187B) | 2017-01-17 07:30 | 2017-01-19 17:30 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2017-01-17 07:30 | 2017-01-24 17:30 | N | Y | damper replacement | Line |  |  | 500 kV
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),36B138-14.83 (ENMAX 36),ENMAX 14 B138-14.83 (ENMAX 14) | 2017-01-17 08:00 | 2017-01-17 16:00 | N | N | doble 14B138-14.83 (KSO), SW86 at 36 Sub | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 317s T1 (317s Baseline) | 2017-01-17 08:15 | 2017-01-17 16:45 | N | N | relay maintenance | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 24.83L (74s Janet - ENMAX 24),74s 24.83X (74s Janet) | 2017-01-17 08:30 | 2017-01-17 13:30 | N | Y | add supervisory control to recloser | Circuit Breaker, Line |  |  | Contingency Requires Mitigation
ALTALINK | 276s 652 (276s Un Carb Prentiss),276s C1 (276s Prentiss) | 2017-01-17 10:00 | 2017-01-17 17:00 | N | N | replace heater on 276s652 | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 430-TX2 (317s Baseline) | 2017-01-17 16:45 | 2017-01-18 16:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
GWPCORP | 243S Soderglen Wind Farm | 2017-01-18 07:00 | 2017-01-18 12:00 | N | Y | substation maintenance | Station |  |  | Restricts Generation
ALTALINK | 377s 703E (377s Hardisty),703L (377s Hardisty - 703BL tap) | 2017-01-18 08:00 | 2017-01-18 17:30 | N | N | investigate control and protection wiring issues and modify annunciate seal-in circuits | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 36.3TR (ENMAX 36),36.81L (44s Bearspaw - ENMAX 36) | 2017-01-18 08:00 | 2017-01-18 16:00 | N | Y | switch maintenance | Line, Transformer |  |  | For Information Only
ATCO | 946s 902 (946s Oakland) | 2017-01-18 08:00 | 2017-01-19 16:00 | N | Y | emergency repair of SF6 leak | Circuit Breaker |  | EMERGENCY REPAIRS 946S Oakland Brk 902 West Pole, SF6 leak. | 240 kV, Pre-Condition, For Information Only
ALTALINK | 898L (37s North Calder - 92s Viscount),92s 898 (92s Viscount) | 2017-01-18 08:30 | 2017-01-18 12:30 | N | N | top up breaker SF6 gas | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 845s 705C (845s Big Mountain) | 2017-01-18 09:00 | 2017-01-18 15:00 | N | N | relay maintenance | Shunts |  | Relay maintenance, Capacitor 705C will be unavailable for the duration of the work. | For Information Only
ALTALINK | 250p11 (250p Bighorn) | 2017-01-18 11:00 | 2017-01-18 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 814s T1 (814s Bellamy) | 2017-01-19 07:00 | 2017-01-20 17:00 | N | Y | Calisto install | Transformer |  |  | 240 kV, Over/Under Voltage
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2017-01-19 07:45 | 2017-01-19 17:45 | N | N | fix wiring issues in T1 to 191s335W and 191s338N trip circuits | Transformer |  |  | For Information Only
ALTALINK | 511s ACF12 (511s Crossings) | 2017-01-19 08:00 | 2017-01-19 16:00 | N | Y | inspection and investigate Pole discrepancy alarm which occurred on Jan 1st when control system attempted to close breaker on power ramp | Shunts
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2017-01-19 08:00 | 2017-01-19 16:00 | N | N | switch maintenance | Line |  | HV SW/MD Maintenance SW87 | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 610L (336s Fincastle - 83s Taber),336s 610 (336s Fincastle) | 2017-01-19 08:30 | 2017-01-19 17:00 | N | N | firmware upgrades and setting changes to 610L B21/79/L6 URD60 relay | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2017-01-19 09:00 | 2017-01-19 13:00 | N | N | maintenance | Switch
ALTALINK | 412L (396s Pincher Creek - 632s Russell),632s 412 (632s Russell) | 2017-01-19 10:00 | 2017-01-19 17:00 | N | Y | replace heater on 632s412 | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2017-01-21 07:00 | 2017-01-22 19:00 | N | N | replace pole | Line, Transformer |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),39B138-38.83 | 2017-01-21 08:00 | 2017-01-21 16:00 | N | N | low pressure alarm - requires top up. SF6 Gas Sample. Investigate leak (East Pole) | Terminal Equipment, Line |  |  | Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32),32B138-32BT5 (ENMAX 32),ENMAX 32 SW89 (ENMAX 32) | 2017-01-22 08:00 | 2017-01-22 16:00 | N | N | urgent repair contact of relay for auto switching | Circuit Breaker, Transformer, Switch |  | Repair contact 9+10 on 32MD138-32.2TR that sends closed status to the C30 Relay, which effects the function of the Auto Switching. | Creates Radial Feeds
Medicine Hat | MH69s3 MH69_311 (MH69s3 South Ridge),MH69s3 MH69_308 (MH69s3 South Ridge),MH69s3 T31 (MH69s3 South Ridge),MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2017-01-23 07:00 | 2017-01-27 16:00 | N | N | replace disconnect switch MH69-309 & MH69-310 | Circuit Breaker, Transformer, Line |  |  | Creates Radial Feeds
ALTALINK | 915L (38s East Edmonton - 987s Clover Bar),946L (89s Ellerslie - 38s East Edmonton) | 2017-01-23 07:15 | 2017-01-24 17:45 | N | Y | replace strain insulators at 38s | Line |  |  | 240 kV, For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 240 kV North Bus,162s Beddington 138 kV North Bus | 2017-01-23 08:00 | 2017-01-24 16:00 | N | Y | doble 162PT240-Z43 and HV sw/md maintenance | Transformer, Bus | doble 162PT240-Z43, HV SW/MD Maintenance 162.1TR 138kV & 240kV MDs, SW81, SW131, SW141. |  | 240 kV, Contingency Requires Mitigation
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2017-01-23 08:00 | 2017-02-03 16:00 | N | N | line protection upgrade | Line |  |  | Creates Radial Feeds
ENMAX | 14.2TR (ENMAX 14) | 2017-01-23 08:00 | 2017-01-23 12:00 | N | N | roxtek plug installation in cable ducts | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2017-01-23 08:00 | 2017-02-03 17:00 | N | N | line work to install conductor splice at each structure and construction to construct bypass to build T Tap for new 2019s Vincent sub | Line |  | There will be 2 permit holders Line work - To install conductor splice at each structure Construction - construct bypass to build T Tap for new 2019s Vincent sub on Jan 23 | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 803s T1 (803s Lambton),803s L2401 (803s Lambton),803s L2402 (803s Lambton) | 2017-01-24 07:00 | 2017-01-24 17:00 | N | Y | disconnect switch repair | Circuit Breaker, Transformer |  | disconnect switch repair - LDS3 at 803s Lambton | 240 kV, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20) | 2017-01-24 08:00 | 2017-01-24 16:00 | N | N | measurements for HV bushing & CT replacement | Transformer |  |  | For Information Only
ALTALINK | 892L (895s Suffield - 244s Bowmanton) | 2017-01-25 06:30 | 2017-01-30 17:30 | N | N | replace saddles | Line |  |  | Creates Radial Feeds
ATCO | 2029s ACF11 (2029s Heathfield) | 2017-01-25 07:00 | 2017-02-08 09:00 | N | Y | repair poor connections to fix corona noise | Shunts |  | Repair poor connections to fix corona noise due to landowner complaints , the outage is scheduled to happen at the same time as the 13L50 DC Line outage. | 240 kV, For Information Only
ATCO | 2075S Newell,13L50 (2029s Heathfield - 2075s Newell),2029s Heathfield | 2017-01-25 07:00 | 2017-02-09 15:30 | N | Y | install new/refurbished valve hall reactors | Line, Station |  | 13L50 needs to be taken out of service to install new/refurbished valve hall reactors due to a factory recall on the original reactors at the same time we will be changing out 1300PT1 at Newell in order to hopefully be able to operate the line at full voltage as per design. install new/refurbished valve hall reactors due to a factory recall on the original reactors at the same time we will be changing out 1300PT1 at Newell in order to hopefully be able to operate the line at full voltage as per design. | Pre-Condition, Overload, 500 kV
ATCO | 2029s Heathfield | 2017-01-25 07:00 | 2017-02-08 09:00 | N | Y | removing valve hall reactors and replacing them with refurbished ones | Station |  | Removing valve hall reactors and replacing them with refurbished ones from the factory due to a recall on the originally installed reactors, HVDC will be unavailable for transfer | For Information Only, 500 kV
ATCO | 2075s ACF11 (2075s Newell),2075s ACF21 (2075s Newell) | 2017-01-25 07:00 | 2017-02-08 09:00 | N | Y | repair faulty connections on the AC filter bus #1 inspect filter banks and SVC | Shunts |  | repair faulty connections on the AC filter bus #1 inspect filter banks and svc, the outage is schedule to happen at the same time as the 13L50 DC Line outage. | 240 kV, For Information Only
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2017-01-25 07:30 | 2017-02-06 13:50 | N | Y | damper replacement | Line |  |  | 500 kV
NAKODA, ENMAX | 162s T2 (162s Three Bands),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2017-01-25 08:00 | 2017-01-26 16:00 | N | Y | doble Z44PT. HV SW/MD maintenance 162.2RT 138kV & 240kV MDs, SW88, SW136, SW146 | Transformer, Bus |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 62s 11 (62s Brazeau) | 2017-01-25 23:00 | 2017-01-26 04:00 | N | Y | maintenance | Switch |  | TAU BR1 generator brushgear outage & blackstart test. | Restricts Generation, For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2017-01-26 04:01 | 2017-01-26 07:00 | N | Y | maintenance | Switch |  | TAU BR2 generator brushgear outage. | Restricts Generation, For Information Only
ATCO | 931S Bohn,7L05 (931s Bohn - 2049s Kettle River) | 2017-01-26 07:00 | 2017-01-26 19:00 | N | N | line work | Station, Line |  | Line work - Attach 7L05D3 to 7L05 at 931S Bohn, Test BF/DTT to 2049s Kettle, 7L05 radially feeds 931s, Customer outage reqd on 3L227 | Creates Radial Feeds
ALTALINK | 535s 5552 (535s Joffre) | 2017-01-26 07:30 | 2017-01-26 11:30 | N | N | function test breaker from 755L a and b protection | Circuit Breaker |  |  | For Information Only
ALTALINK | 834L (384s Keystone - 320p Keephills),384s 834 (384s Keystone) | 2017-01-26 08:30 | 2017-01-26 17:30 | N | N | replace tank heaters | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 535s 5452 (535s Joffre) | 2017-01-26 11:35 | 2017-01-26 14:00 | N | N | function test breaker from 755L a and b protection | Circuit Breaker |  |  | For Information Only
ATCO | 931s 7L05D3 (931s Bohn),931s 702T (931s Bohn) | 2017-01-26 16:00 | 2017-02-08 17:00 | N | N | In service date:Feb 1, 2017. | Switch, Terminal Equipment |  | Construction, see energization steps for RTN. Jan 26-31 - Construction Jan 31 - Release COG, energize 702T, soak Feb 8 - Confirm COG on 3L232D1 released by Enbridge - Switch to energize Enbridge 4160v bus to 3L232D1 - Check Phasing across 3L232D1 - Switch to Parallel 701T/702T - 702T online load testing - Switch to seperate 701T/702T and reopen Enbridge tie switch 410-BUS-1/2-TIS | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2017-01-27 07:30 | 2017-02-10 17:30 | N | N | damper replacements | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 766s 701T (766s Nevis),766s 901T (766s Nevis),7L143 (766s Nevis - 769s Stettler),7L16 (766s Nevis - 948s Heatburg) | 2017-01-28 09:00 | 2017-01-31 16:00 | N | Y | replace 701T and sample 700PT1 | Transformer, Line |  | Replace 701T, 700PT1, Salvage 501VR & associated 25 kv bus, maint on 701TCS, 7L16 and 7L143 will be open ended @ 766s Jan 28-Feb 3, 750s Mobile sub will carry all 766s 25kV load Work Sequence Jan 27 - Energize 750s up to 511TD, check phasing across 511TD, Open 511 @ soak 750s overnight Jan 28 - transfer all 701T load to 750s Jan 28 - Feb 3 Issue GOI 2-37175A to Isolate 144kV bus, 25kV bus, 701T Isolation Pts - 701A, 702A, 703A, 701T secondaries, 5L44D1, 5L30D1, 5L235D1, 500PT1D, 500MT1D, 500D3 Feb 3 - Shrink GOI to 701TCS, issue GOI 2-37175B, and then place 144kV bus, 7L16, 7L143 in service @ 766s Isolation Pts - 701TCS, 5L44D1, 5L30D1, 5L235D1, 500PT1D, 500MT1D, 500D3 Feb 3 - Release GOI 2-37175A Feb 10 - Release GOI 2-37175B Feb 10 - Energize 701T, check phasing @ 5L244D1, soak overnight Feb 11 - Transfer 5L30 & 5L235 from 750s to 701T, 5L244 to remain on 750s Feb 11 - Issue HOP 2-40490 on 5L244 to create new jumper J1 (separates 5L244 from 25kV bus) Feb 11- Issue GOI 2-40492 on 25kV bus between 501B, 500D1, J1 @ 766s to change pole near 500D1) Feb 11 - Release GOI 2-40492, leave 501B, 500D1 open Feb 11 - Close jumper J1, Feb 11 - Release HOP 2-40490 Feb 11 - Transfer 5L244 load from 750s to 701T Feb 11 - Open 711TD and 511TD (750s) and remove taps from 7L16 & 5L244 (see HOP 2-40146 and 2-xxxxx) | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s2 MH69_202 (MH69s2 North Industrial),MH69s6 MH69_602 (MH69s6 Riverview),MH69s6 MH69_604 (MH69s6 Riverview),MH69s6 MH69_607 (MH69s6 Riverview),MH69s6 MH69_616 (MH69s6 Riverview) | 2017-01-30 07:00 | 2017-02-01 16:00 | N | N | inspection and maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 800s 701T (800s Friedenstal) | 2017-01-30 07:00 | 2017-04-28 17:00 | N | N | replace 701T | Transformer |  | Replace 701T | Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 352 (39s Bickerdike) | 2017-01-30 07:30 | 2017-02-10 17:30 | N | N | replacing existing breaker with a new SF6 breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 65s T3 (65s High River) | 2017-01-30 14:31 | 2017-02-07 17:30 | N | N | T3 outage to connect temp cables to low-side | Transformer |  |  | Restricts Generation
ENMAX | 23.3TR (ENMAX 23) | 2017-01-31 08:00 | 2017-01-31 12:00 | N | N | plug installation | Transformer |  |  | For Information Only
BCH | 2L112 (Nelway - Boundary) | 2017-01-31 10:30 | 2017-01-31 12:30 | N | N | BPA work | Line |  |  | Limits ATC
ENMAX | 23.4TR (ENMAX 23) | 2017-01-31 12:00 | 2017-02-01 16:00 | N | N | test TR diff relay | Transformer |  |  | For Information Only
ATCO | 959S SVC (959s Lanfine) | 2017-01-31 13:00 | 2017-02-03 16:00 | N | N | forced outage | Shunts |  |  | 240 kV
ATCO | 766s 701T (766s Nevis) | 2017-01-31 16:31 | 2017-02-13 12:00 | N | N | reconfigure 25 kV bus and soak 701T | Transformer |  | Replace 701T, 700PT1, Salvage 501VR & associated 25 kv bus, maint on 701TCS, 7L16 and 7L143 will be open ended @ 766s Jan 28-Feb 3, 750s Mobile sub will carry all 766s 25kV load Work Sequence Jan 27 - Energize 750s up to 511TD, check phasing across 511TD, Open 511 @ soak 750s overnight Jan 28 - transfer all 701T load to 750s Jan 28 - Feb 3 Issue GOI 2-37175A to Isolate 144kV bus, 25kV bus, 701T Isolation Pts - 701A, 702A, 703A, 701T secondaries, 5L44D1, 5L30D1, 5L235D1, 500PT1D, 500MT1D, 500D3 Feb 3 - Shrink GOI to 701TCS, issue GOI 2-37175B, and then place 144kV bus, 7L16, 7L143 in service @ 766s Isolation Pts - 701TCS, 5L44D1, 5L30D1, 5L235D1, 500PT1D, 500MT1D, 500D3 Feb 3 - Release GOI 2-37175A Feb 10 - Release GOI 2-37175B Feb 10 - Energize 701T, check phasing @ 5L244D1, soak overnight Feb 11 - Transfer 5L30 & 5L235 from 750s to 701T, 5L244 to remain on 750s Feb 11 - Issue HOP 2-40490 on 5L244 to create new jumper J1 (separates 5L244 from 25kV bus) Feb 11- Issue GOI 2-40492 on 25kV bus between 501B, 500D1, J1 @ 766s to change pole near 500D1) Feb 11 - Release GOI 2-40492, leave 501B, 500D1 open Feb 11 - Close jumper J1, Feb 11 - Release HOP 2-40490 Feb 11 - Transfer 5L244 load from 750s to 701T Feb 11 - Open 711TD and 511TD (750s) and remove taps from 7L16 & 5L244 (see HOP 2-40146 and 2-xxxxx) | Pre-Condition, For Information Only
EPCOR | 113s T2 (113s Inland Cement) | 2017-02-01 07:00 | 2017-02-02 17:00 | N | N | protection repair | Transformer |  |  | For Information Only
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-02-01 07:30 | 2017-02-02 14:30 | N | N | emergency repair; structure replacement | Line |  |  | For Information Only
ENMAX | 33.1TR (ENMAX 33) | 2017-02-01 08:00 | 2017-02-01 16:00 | N | N | CT and PT measurements required | Transformer |  |  | For Information Only
ENMAX | 7.2TR (ENMAX 7) | 2017-02-01 08:00 | 2017-02-01 16:00 | N | N | maintenance | Transformer |  | Switchgear needs to be cleaned (health hazard) | For Information Only
ENMAX | 14.1TR (ENMAX 14) | 2017-02-01 08:00 | 2017-02-01 12:00 | N | N | install Roxtek plugs in ducts | Transformer |  |  | For Information Only
CMH | MHS-6 MH69-608 (MHS-6 CMH Riverview), MHS-6 MH69-611 (MHS-6 CMH Riverview), MHS-6 MH69-614 (MHS-6 CMH Riverview), MHS-6 MH69-616 (MHS-6 CMH Riverview), MHS-3 MH69-302 (MHS-3 Southridge), 8L (MH69S-1 Power Plant - MH69S-6 Riverview), MH-20L (MH69S-3 South Ridge - MH69S-6 Riverview) | 2017-02-02 07:00 | 2017-02-07 16:00 | N | N | inspection and maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 1107L (ENMAX 65 - 237s Foothills) | 2017-02-03 07:30 | 2017-03-04 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2017-02-04 07:00 | 2017-02-04 16:00 | N | N | outage required to drill holes for overhead road signs | Line |  |  | Pre-Condition, For Information Only
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2017-02-04 08:00 | 2017-02-05 16:00 | N | N | SF6 gas sample and switch maintenance | Line, Transformer |  | Gas sample 11B138-11.82, 14B138-11.82. 11s SW/MD maintenance 11.2MD, 11.3MD, SW84, SW85, SW86 11.3TR maintenance - future outage | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 170L (632s Russell - 799s Coleman) | 2017-02-04 08:30 | 2017-02-04 17:30 | N | Y | emergency repair; str33 crossarm replacement, str68 OHSW repair | Line |  | emergency repair; str33 crossarm replacement, str68 OHSW repair | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | RAS3 - 786L RAS | 2017-02-04 17:30 | 2017-03-08 09:00 | N | N | forced outage | RAS |  |  | For Information Only
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2017-02-05 07:00 | 2017-02-06 17:15 | N | Y | replace anchors on structures and perform maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
EPCOR, ALTALINK | 1056L (89s Ellerslie - 629s Argyll Transfer Station),240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2017-02-06 07:00 | 2017-02-06 17:00 | N | Y | low pressure SF6 | Line |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Hardisty T3 (Hardisty) | 2017-02-06 07:00 | 2017-10-17 17:00 | N | N | switchgear replacement | Transformer |  |  | For Information Only
ATCO | 7L97 (820s Hangingstone - 7LA97),820s 702 (820s Hangingstone) | 2017-02-06 07:00 | 2017-02-16 17:00 | N | N | replace 701TCS with Breaker 705 and switch 705A | Line, Circuit Breaker |  | Feb 6-16 Issue 2-36720A to replace 701TCS with Breaker 705 and switch 705A, 7L97 open ended @ 820s, All load on 702T Feb 16 - Shrink GOI to 500D3 and 705A, Issue 2-36720B, Release 2-36720A, restore 7L97 and 700BS1 to normal Feb 16- Mar 13 - complete construction | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 785S Judy Creek Gas Plant,785s 701T (785s Judy Creek Gas Plant),7L78 (785s Judy Creek - 851s Morse River) | 2017-02-06 07:00 | 2017-02-23 17:30 | N | N | replace 701TCS | Transformer, Line, Station |  | Replace 701TCS. | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2017-02-06 08:00 | 2017-03-03 16:00 | N | Y | relocated a section of 7.82 L around the new planned intersection at 69Str SW and the SWCRR(HW8) | Line |  |  | Pre-Condition, For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2017-02-06 08:00 | 2017-02-06 16:00 | N | N | MT/ conservator pipe repair | Transformer |  |  | For Information Only
ALTALINK | 38s 62 (38s East Edmonton) | 2017-02-06 08:45 | 2017-02-06 09:30 | N | N | verify breaker disconnect switch operation for future bus outage | Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2017-02-06 09:30 | 2017-02-08 17:30 | N | N | replace leaking pole of breaker | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, ATCO | 913L (69s North Barrhead - 732s Mitsue),913L (69s North Barrhead - 338s Cherhill),9L913 (69s North Barrhead - 732s Mitsue),69s North Barrhead 240kV Bus | 2017-02-06 17:16 | 2017-02-11 17:45 | N | Y | replace insulators on structures and perform maintenance | Line, Bus |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2017-02-07 07:30 | 2017-02-09 16:30 | N | N | line mitigation | Line |  | replace str 509 and 511, 796s radial fed from Lubicon | Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T2 (65s High River) | 2017-02-07 17:31 | 2017-02-14 07:59 | N | N | connect new 25kV bus to existing south bus, replace SS2, replace 63L overhead conductor | Transformer |  |  | For Information Only
ENMAX | 41.1C (ENMAX 41),41.2TR (ENMAX 41),33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41),ENMAX 41 B138-6.82 (ENMAX 41),ENMAX 41 B138-33.83 (ENMAX 41) | 2017-02-08 06:00 | 2017-02-08 12:00 | N | N | RTU replacement | Line, Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Lethbridge, ALTALINK | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron),674s 725E (674s Lethbridge Bowron) | 2017-02-08 08:00 | 2017-02-08 12:00 | N | N | replacing dampner | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 671L (58s Edson - 39s Bickerdike),58s 671 (58s Edson) | 2017-02-08 09:30 | 2017-02-10 08:33 | N | N | repair OPGW at structure 69 | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ENMAX | 41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41),ENMAX 41 B138-40.81 (ENMAX 41) | 2017-02-08 12:00 | 2017-02-08 18:00 | N | N | RTU replacement | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L129 (526s Buffalo Creek - 918s Bauer) | 2017-02-09 07:00 | 2017-02-11 17:00 | N | N | urgent work - inspection and arm/brace replacement | Line |  | Urgent work - Inspection and Arm/Brace Replacement, 918s radial fed from 710s Vermillion, 526s radial fed from 757s | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 9L55 (885s McMillan - 852s Round Hill) | 2017-02-09 07:30 | 2017-02-09 17:30 | N | Y | damper replacement | Line |  |  | 240 kV, Pre-Condition, Creates Radial Feeds
ALTALINK | 38s 75 (38s East Edmonton) | 2017-02-09 08:00 | 2017-02-09 08:45 | N | N | verify breaker disconnect switch operation ahead of future bus outage | Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss
ENMAX | 26.1TR (ENMAX 26),26.81L (ENMAX 54 - ENMAX 26),26B138-26.81 (ENMAX 26),ENMAX 26 B138-26BT3 (ENMAX 26),54B138-26.81 (ENMAX 54) | 2017-02-09 08:00 | 2017-02-11 16:00 | N | N | SF6 gas sample 26B138-26.81, 54B138-26.81. HV SW/MD maintenance 26.1MD | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 901AL (64s East Crossfield - 901L tap),901L (63s Red Deer - 74s Janet) | 2017-02-09 08:00 | 2017-02-09 17:00 | N | Y | repair of hot spots on 901N | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 847L (39s Bickerdike - 406s Fickle Lake) | 2017-02-10 10:00 | 2017-02-10 11:00 | N | Y | required to energize new 39s352 | Line
ALTALINK | 1061L (12s Heartland - 681s Bannerman) | 2017-02-11 07:30 | 2017-02-22 17:30 | N | Y | damper replacements, QA/QC checks | Line |  |  | 240 kV, Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2017-02-12 07:30 | 2017-02-12 17:00 | N | N | emergency outage to address conductor conditions | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
Syncrude | Aurora C1 (Aurora) | 2017-02-13 06:00 | 2017-02-22 18:00 | N | N | preventive maintenace | Shunts |  |  | For Information Only
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2017-02-13 06:30 | 2017-02-20 17:30 | N | N | replace saddles | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | NamaoT1 (Namao) | 2017-02-13 07:00 | 2017-02-17 17:00 | N | N | Temperature Gauge install | Transformer |  |  | For Information Only
ATCO | 706s 701T (706s Irish Creek) | 2017-02-13 07:00 | 2017-02-17 17:00 | N | N | move protection panels for Capacitor bank install | Transformer |  | Move protection panels for Capacitor bank install, all 706s load to be transferred to 702T | For Information Only
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2017-02-13 07:30 | 2017-02-14 17:30 | N | N | replace 1 pole of breaker | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2017-02-13 08:00 | 2017-02-13 12:00 | N | N | substation washing | Line, Transformer, Shunts |  | Spring Substation Washing (Weather Permitting) | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2017-02-13 08:00 | 2017-02-13 16:00 | N | N | MT/ conservator pipe repair | Transformer |  |  | For Information Only
ATCO | 9L938 (77s Sagitawah - 809s Louise Creek) | 2017-02-13 09:30 | 2017-02-17 17:00 | N | Y | protection upgrade on both ends, both Altalink and ATCO will hold GOIs on the line, 240kV ring will be open @ 809s | Line |  | Protection upgrade on both ends, Both Altalink and ATCO will hold GOIs on the line, 240kV ring will be open @ 809s. | For Information Only
ALTALINK | 938L (77s Sagitawah - 809s Louise Creek) | 2017-02-13 10:00 | 2017-02-17 17:00 | N | Y | A / B protection replacement projects | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 286s 352 (286s Yasa) | 2017-02-13 11:00 | 2017-02-13 17:30 | N | N | top-up SF6 gas | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 420s T2 (420s Broadmoor) | 2017-02-13 11:30 | 2017-02-16 14:30 | N | N | investigate / repair 420s AMI UG cable issue | Transformer |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2017-02-13 12:00 | 2017-02-13 16:00 | N | N | substation washing | Line, Transformer |  | Spring Substation Washing (Weather Permitting) | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2017-02-14 07:00 | 2017-02-14 18:00 | N | N | spring substation washing (weather permitting) | Line, Transformer, Shunts |  |  | For Information Only
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2017-02-14 07:00 | 2017-02-14 18:00 | N | N | outage required to drill holes for overhead road signs | Line |  | outage required to drill holes for overhead road signs (Graham Construction) | For Information Only
ALTALINK | 1088L (324s Cassils - 2075s Newell) | 2017-02-14 07:30 | 2017-02-14 17:30 | N | Y | damper replacement | Line |  |  | 240 kV
ALTALINK | 65s T3 (65s High River) | 2017-02-14 08:00 | 2017-02-27 17:30 | N | N | remove temp cables attached to T3 | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 608AL (528s Blue Trail Wind Farm - 608L tap) | 2017-02-14 08:00 | 2017-02-14 12:00 | N | N | old SFTP: add guy wires to str 608AL35 | Line |  |  | Restricts Generation
ALTALINK | 63s 51 (63s Red Deer) | 2017-02-14 08:30 | 2017-02-14 15:00 | N | N | 138kV breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2017-02-14 12:00 | 2017-02-14 16:00 | N | N | spring substation washing (weather permitting) | Line, Transformer |  |  | For Information Only
ATCO | 7L129 (918s Bauer - 710s Vermilion) | 2017-02-15 07:00 | 2017-02-18 17:00 | N | N | urgent work - inspection and arm/brace replacement | Line |  | Urgent work - Inspection and Arm/Brace Replacement, 526s radial fed from 757s BR, 918s radial fed from 526s Confirm Altalink 897L returned to service prior to start | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2017-02-15 07:30 | 2017-02-16 17:30 | N | N | replace post insulators | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 34.1TR (ENMAX 34) | 2017-02-15 08:00 | 2017-02-16 16:00 | N | N | oil leak control | Transformer |  |  | For Information Only
ENMAX | 26.81L (ENMAX 54 - ENMAX 26),26B138-26.81 (ENMAX 26),54B138-26.81 (ENMAX 54) | 2017-02-15 08:00 | 2017-02-19 19:00 | N | N | to string over top of line | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 426L (194s South Red Deer - 63s Red Deer),63s 426 (63s Red Deer) | 2017-02-15 08:30 | 2017-02-15 15:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 676L (523s Bullshead - 244s Bowmanton) | 2017-02-16 06:30 | 2017-03-02 17:30 | N | Y | replace saddles (more details to follow) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 708L (71s Lamoureux - 708L88X) | 2017-02-16 07:00 | 2017-02-21 12:00 | N | N | line is being cutover to newly constructed section | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2017-02-16 08:30 | 2017-02-16 16:30 | N | Y | remove 725CL from back of 725L57 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2017-02-16 09:00 | 2017-02-16 15:00 | N | N | emergency maintenance | Line |  |  | Pre-Condition
ATCO | 820s 701T (820s Hangingstone) | 2017-02-16 17:01 | 2017-03-20 17:00 | N | N | protection upgrade | Transformer |  | Feb 6-16 Issue 2-36720A to replace 701TCS with Breaker 705 and switch 705A, 7L97 open ended @ 820s, All load on 702T Feb 16 - Shrink GOI to 500D3 and 705A, Issue 2-36720B, Release 2-36720A, restore 7L97 and 700BS1 to normal Feb 16- Mar 13 - complete construction | For Information Only
ATCO | 2029s ACF22 (2029s Heathfield) | 2017-02-17 08:00 | 2017-03-10 16:00 | N | N | forced outage | Shunts |  |  | 240 kV
ENMAX | 1.84L (ENMAX 1 - ENMAX 5),B138-1.84 (ENMAX 5) | 2017-02-18 08:00 | 2017-02-19 16:00 | N | N | doble breaker and CTs, LA's, potheads | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 637L (17s Benalto - 580s Sylvan Lake) | 2017-02-20 07:30 | 2017-02-20 12:25 | N | N | relocate dampers | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L913 (69s North Barrhead - 732s Mitsue) | 2017-02-20 08:00 | 2017-02-26 17:00 | N | Y | replace rotten crossarms, poles | Line |  | replace rotten crossarms, poles | 240 kV, Pre-Condition, Overload
ALTALINK | 913L (69s North Barrhead - 732s Mitsue) | 2017-02-20 08:00 | 2017-02-26 17:00 | N | N | ATCO maintenance (replace crossarms/poles) | Line |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2017-02-20 11:00 | 2017-02-20 16:00 | N | N | remove 40.81L guy wire from in between phases | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2017-02-20 12:30 | 2017-02-20 17:30 | N | N | relocate dampers | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark T3 (Meadowlark) | 2017-02-21 07:00 | 2017-02-21 17:00 | N | N | PRD flange measurments | Transformer |  |  | Firm Load Loss
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 7L50D2),526s 252 (526s Buffalo Creek) | 2017-02-21 07:00 | 2017-02-24 17:00 | N | Y | urgent work - inspection and arm/brace replacement | Line, Circuit Breaker |  | Urgent work - Inspection and Arm/Brace Replacement, 704L radial fed from 757s BR, 526s radial fed from 710s Verm | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton) | 2017-02-21 07:15 | 2017-02-21 17:45 | N | N | replace strain insulators | Line |  |  | For Information Only
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works),62s 201 (62s Brazeau),294s 801N (294s Brazeau Outlet Works) | 2017-02-21 07:30 | 2017-03-06 17:30 | N | Y | replace structures, replace insulators, repair guy wires, general line maintenance | Line, Circuit Breaker, Switch |  |  | Restricts Generation, Creates Radial Feeds
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2017-02-21 08:00 | 2017-02-23 12:00 | N | N | urgent replacement of failed capacitors | Shunts |  |  | 500 kV
ALTALINK | 902L (19s Wabamun - 310p Sundance),310p 752 (310p Sundance),310p 852 (310p Sundance) | 2017-02-21 09:00 | 2017-02-23 17:30 | N | Y | modify and test protection for recloser addition | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 929L (63s Red Deer - 74s Janet),74s 352 (74s Janet),74s 252 (74s Janet) | 2017-02-21 09:30 | 2017-02-24 17:30 | N | N | replacing 'A' protection | Line, Circuit Breaker |  |  | 240 kV
EPCOR | RossdaleT1 (Rossdale) | 2017-02-22 07:00 | 2017-02-22 17:00 | N | N | PRD flange measurments | Transformer |  |  | For Information Only
ATCO, ALTALINK | 9L961 (13s Deerland - 825s Whitefish Lake),13s 1452 (13s Deerland),13s 1352 (13s Deerland) | 2017-02-22 07:15 | 2017-03-01 15:45 | N | Y | replacing CT's and wiring/control changes to A & B protection | Line, Circuit Breaker |  |  | 240 kV, Overload
ENMAX | 5.10TR (ENMAX 5) | 2017-02-22 08:00 | 2017-02-22 16:00 | N | N | low oil, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 320p 2952 (320p Keephills) | 2017-02-22 08:00 | 2017-02-22 12:30 | N | Y | setting changes on 500 G3 bus protection | Circuit Breaker |  |  | 500 kV
ALTALINK | 786L (799s Coleman - Natal) | 2017-02-22 11:00 | 2017-02-22 18:00 | N | Y | BCH 1L275 work | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 320p 3052 (320p Keephills) | 2017-02-22 12:31 | 2017-02-22 17:30 | N | Y | setting changes on 500 G3 bus protection | Circuit Breaker |  |  | Pre-Condition, 500 kV
ENMAX | 162s 138-RB80 (162s Beddington) | 2017-02-23 08:00 | 2017-02-23 10:30 | N | N | SF6 sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 37.1TR (ENMAX 37) | 2017-02-23 08:00 | 2017-02-23 16:00 | N | N | low oil & check reversing switch | Transformer |  |  | For Information Only
ATCO | 882s 701T (882s Triangle),882s 701 (882s Triangle) | 2017-02-23 10:00 | 2017-03-28 16:00 | N | N | Breaker 701 Breaker Replacement | Circuit Breaker, Transformer |  | Breaker 701 Breaker Replacement @ 882S Triangle, 25kV will be offloaded to High Prairie, 25kV bus will remain energized @ 882s for stn service. On Feb 27 expand outage to include 7L48 between D2 and D3 to attach new risers and check operation of 701A On last day of outage GOI will be expanded to include 25kV bus (AC stn service outage) to install bird guard on 25kV bus. | For Information Only
ENMAX | 162s 138-RB81 (162s Beddington) | 2017-02-23 10:30 | 2017-02-23 13:30 | N | N | SF6 gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162s 138-RB82 (162s Beddington) | 2017-02-23 13:30 | 2017-02-23 16:00 | N | N | SF6 Gas Sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 510s ACF12 GOI | 2017-02-23 14:00 | 2017-02-25 17:00 | N | Y | urgent replacement of failed capacitors | Terminal Equipment |  |  | 240 kV
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-02-25 07:30 | 2017-02-25 10:00 | N | N | create open point | Line |  |  | For Information Only
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2017-02-25 07:30 | 2017-02-26 16:30 | N | Y | install bird diverters | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2017-02-25 07:30 | 2017-02-25 12:30 | N | N | repair SF6 leak | Circuit Breaker, Line |  | The crew replaced the pole on Feb 13 & 14, but there are still some issues with this breaker. They were able to troubleshoot some of the issues and those issues can be dealt with this weekend. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-02-25 10:00 | 2017-02-25 14:30 | N | N | switch maintenance | Line |  | The open point is created for the 150L outage because the switch needs to be repaired first, before the switch maintenance. The Advice is created to create the open point for crews to make repairs and the GOI is for the switch maintenance. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-02-25 14:30 | 2017-02-25 17:30 | N | N | close open point | Line |  |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc),325s T2 (325s Leduc),325s Leduc 138kV Bus 2 | 2017-02-26 10:00 | 2017-03-02 14:00 | N | N | close Open Point 'A' and tie in new C1 to 138B2 | Bus, Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 6G (310p Sundance) | 2017-02-26 14:00 | 2017-04-03 17:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 1053L (132s Ware Junction - 324s Cassils) | 2017-02-27 05:30 | 2017-04-05 17:30 | N | Y | damper replacements, QA/QC checks | Line |  |  | 240 kV, Pre-Condition
EPCOR | 816s P2403 (816s Petrolia) | 2017-02-27 07:00 | 2017-03-01 17:00 | N | Y | relay maintenance and repairs to P2403 BF relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 966L (650s Hansman Lake - 932s Pemukan) | 2017-02-27 07:30 | 2017-03-13 17:30 | N | Y | damper replacements, QA/QC checks | Line |  |  | 240 kV, For Information Only
ATCO | 7L48 (787s High Prairie - 794s Valleyview) | 2017-02-27 08:00 | 2017-02-27 16:00 | Y | N | attach new risers and check operation of 701A | Line |  |  | For Information Only
ALTALINK | 755L (535s Joffre - 247s Piper Creek) | 2017-02-27 08:00 | 2017-02-28 16:00 | N | N | In service date:Feb 27, 2017 | Line
ALTALINK | 65S High River | 2017-02-27 08:00 | 2017-02-27 17:30 | N | N | connect temp cables to 65s16E (16L) for 25kV bus outage | Station |  |  | For Information Only
ATCO, ALTALINK | 7L50 (757s Battle River - 526s Buffalo Creek) | 2017-02-27 09:30 | 2017-03-03 17:00 | N | N | inspection and arm/brace replacement,7L50D1 repairs | Line |  | Urgent work - Inspection and Arm/Brace Replacement,7L50D1 Repairs, work may be cancelled or delayed depending on real time weather conditions. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 310p 2452 (310p Sundance),310p 2352 (310p Sundance) | 2017-02-27 09:30 | 2017-04-02 15:30 | N | Y | replacement of breaker control modules, maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2017-02-27 09:30 | 2017-03-01 17:30 | N | N | line rebuild | Line |  |  | Creates Radial Feeds
ALTALINK | 939L (77s Sagitawah - 809s Louise Creek) | 2017-02-27 10:00 | 2017-03-03 15:00 | N | Y | A / B protection replacement projects | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 102s SVC (102s Langdon) | 2017-02-27 12:00 | 2017-03-02 18:00 | N | Y | isolation of network equipment for diagnostic tools and diagnostic maintenance | Shunts |  | Diagnostic maintenance of proprietary SVC equipment for CIP compliance. Network equipment to be removed from network and isolated for diagnostic tools. Hands-on training for testing SVC I/O, facilitating the creation of system maintenance program. | 240 kV
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2017-02-27 14:01 | 2017-03-01 15:00 | N | Y | line construction | Line |  | Line construction, Melito will be radial fed from 786s | Pre-Condition, Over/Under Voltage
ALTALINK | 65s T2 (65s High River) | 2017-02-27 17:31 | 2017-03-28 07:59 | N | N | replace SS1, SS2, 65s49 & 65s35, replace bus work, bring new 2088L UG conductor into station | Transformer |  |  | For Information Only
ALTALINK | 310p 2152 (310p Sundance) | 2017-02-28 07:30 | 2017-02-28 17:30 | N | Y | urgent repair  oil leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 39.3TR (ENMAX 39) | 2017-02-28 08:00 | 2017-02-28 16:00 | N | N | LV breaker maintenance | Transformer |  |  | For Information Only
ALTALINK | 551lL (953s Lake Louise) | 2017-02-28 09:00 | 2017-03-02 15:30 | N | N | structure replacement (loads disconnected) | Line |  |  | For Information Only
ATCO | 754s 702C (754s Ksituan River) | 2017-02-28 10:00 | 2017-02-28 15:00 | N | N | investigate relay | Shunts |  | During maintenance it was found that the relay would not operate for certain tests. A spare relay has been sent. The sub relay will be tested again to confirm operation. If it does not test properly the relay will need to be changed and tested. If the relay needs to be changed, the cap bank 702C would need to be OOS, unavailable for dispatch. | Over/Under Voltage
ALTALINK | 822L (133s Stelco Edmonton - 38s East Edmonton) | 2017-03-01 07:30 | 2017-03-01 17:30 | N | N | replace strain insulators | Line |  |  | Firm Load Loss, For Information Only
ENMAX | 39.4TR (ENMAX 39) | 2017-03-01 08:00 | 2017-03-01 16:00 | N | N | investigate 01 switch on 39MD138-39.4TR Panel. DGA HV bushings | Transformer |  |  | For Information Only
ENMAX | 37.81L (ENMAX 38 - ENMAX 37),ENMAX 37 B138-37.81 (ENMAX 37),ENMAX 38 B138-37.81 (ENMAX 38) | 2017-03-01 08:00 | 2017-03-12 16:00 | N | N | line protection upgrade. CT replacement | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 61L (252s Jarrow - 61DL386) | 2017-03-01 09:00 | 2017-03-01 17:00 | N | N | cut open points to salvage 61AL-10 tap and the 3.2kM portion at the tap going north | Line |  |  | For Information Only
ALTALINK | 310p 1852 (310p Sundance) | 2017-03-01 09:30 | 2017-03-01 17:30 | N | N | urgent repair  oil leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 612L (336s Fincastle - 368s Burdett),336s 612 (336s Fincastle) | 2017-03-02 09:00 | 2017-03-02 15:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | J2404 BKR @ Jasper | 2017-03-02 13:00 | 2017-03-02 15:00 | N | Y | Nait Tour | Terminal Equipment |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 675L (244s Bowmanton - 41s Medicine Hat) | 2017-03-03 06:30 | 2017-03-08 17:30 | N | Y | replace saddles | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2017-03-03 07:30 | 2017-03-03 17:30 | N | N | damper replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),21.61L (ENMAX 21 - ENMAX 34) | 2017-03-04 07:00 | 2017-03-04 16:00 | N | N | move line anchors on a pole common to 16.60L and 21.61L | Line |  | 34 Sub outage required. Line anchors on a pole common to 16.60L and 21.61L are required to be moved for University District. UofC generation will be affected. | Pre-Condition, Restricts Generation
ALTALINK | 1038L (138s Windy Flats - 237s Foothills) | 2017-03-04 07:30 | 2017-04-12 17:30 | N | Y | damper replacement, QA/QC checks | Line |  |  | 240 kV, Pre-Condition
ATCO | 7L749 (899s Edgerton - 7L749D3) | 2017-03-04 11:00 | 2017-03-04 14:00 | N | Y | line mitigation | Line |  | Line mitigation, AML 899s Edgerton will be radial fed from 749L, 880s Briker will be radial fed from 716s Lloyd | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 5.7TR (ENMAX 5) | 2017-03-05 06:00 | 2017-03-07 18:00 | N | N | relay 87-D21 and LV breaker maintenance | Transformer |  |  | For Information Only
ENMAX | ENMAX 5 | 2017-03-05 08:00 | 2017-03-10 16:00 | N | N | 25kV 5B25-117 breaker maintenance | Station |  |  | For Information Only
EPCOR | 511s Victoria T2 (511s Victoria),Victoria V722 (Victoria),Victoria V723 (Victoria) | 2017-03-06 07:00 | 2017-06-29 17:00 | N | N | TX replacement | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 803s L2401 (803s Lambton) | 2017-03-06 07:00 | 2017-03-10 17:00 | N | Y | performing breaker op-checks as part of relay maintenance and repairs to L2401 BF relay | Circuit Breaker |  | L2401 Breaker Outage and L2401 BF Protection Outage @ Lambton S/S. Performing Breaker op-checks as part of relay maintenance and repairs to L2401 BF relay. Isolation required LDS1 and LDS2. Repair required to BF relay as part of relay manufacturer bulletin. | 240 kV, Contingency Requires Mitigation
ATCO, ALTALINK | 9L960 (13s Deerland - 825s Whitefish Lake),13s 1652 (13s Deerland),13s 1752 (13s Deerland) | 2017-03-06 07:15 | 2017-03-09 17:45 | N | Y | replacing CT's and wiring/control changes to A & B protection | Line, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 7L92 (7L92D3 - 7L92D4) | 2017-03-06 08:00 | 2017-03-09 17:00 | N | N | replace cross arms and insulators, 777s radial fed from 819s, 956s radial fed from 709s | Line |  | replace cross arms and insulators, 777s radial fed from 819s, 956s radial fed from 709s | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2017-03-06 08:00 | 2017-03-06 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 922L (310p Sundance - 17s Benalto),17s Benalto 240 kV North Bus 1,17S T3 (17s Benalto) | 2017-03-06 09:00 | 2017-03-16 17:00 | N | Y | replace insulators on the 240kV north bus, replace 17s700 CVT, replace 17s922N & 17s35 switches | Bus, Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),522s3 (522s Cooking Lake) | 2017-03-06 09:00 | 2017-04-21 12:00 | N | N | 522s expansion, install new 138KV high bay structure | Line, Switch |  |  | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 765L (74s Janet - 151s Strathmore) | 2017-03-06 11:00 | 2017-03-06 17:00 | N | N | adjust 151s23, maintain 138kV HGF breaker SF6 gas 151s765W, mitigate broken glass on north phase of 151s765W | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1202L (89s Ellerslie - 320p Keephills) | 2017-03-06 11:00 | 2017-03-09 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 896L (19s Wabamun - 432s Carvel),432s 896 (432s Carvel) | 2017-03-06 11:00 | 2017-03-06 17:00 | N | N | check bushings hot spots and repair | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 728L (405s Waupisoo - 353s Plamondon) | 2017-03-07 07:00 | 2017-03-07 18:00 | N | N | urgent conductor repair on structure 195 | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s C2 (83s Taber),83s T1 (83s Taber),172L (83s Taber - 172L944A),610L (336s Fincastle - 83s Taber),83s Taber 138kV West Bus | 2017-03-07 07:15 | 2017-03-08 15:00 | N | Y | replace 83s3 PT's | Bus, Transformer, Line, Shunts |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (20s Ghost - 150L46) | 2017-03-07 07:30 | 2017-03-08 12:30 | N | N | emergency structure replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 720L (347s Fox Creek - 397s Benbow),397s 720N (397s Benbow) | 2017-03-07 08:30 | 2017-03-07 17:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 825s 901 (825s Whitefish) | 2017-03-07 09:00 | 2017-03-08 12:00 | N | Y | troubleshoot 901 Ph C pole discrepancy issue | Circuit Breaker |  | During 9L960 RFL relay replacement troubleshoot 901 Ph C pole discrepancy issue, permit will be released nightly so 240kV bus loop can be restored if needed. | 240 kV, For Information Only
ALTALINK | 733L (151s Strathmore - 428S Namaka) | 2017-03-07 09:00 | 2017-03-07 16:00 | N | Y | adjust 151s19, breaker maintenance on 151s733E | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
REDDEER | 209s T1 (209s Timberlands) | 2017-03-07 10:00 | 2017-03-10 15:30 | N | N | maintain transmission facilities | Transformer |  | Transformer oil continues to weep from the secondary bushing (X3) and tracking down the secondary incomer cables. The manufacturer (Siemens) has requested to inspect and plan remedial action provided under the transformer warranty. | For Information Only
ALTALINK | 715L (648s Metiskow - 650s Hansman Lake) | 2017-03-07 10:30 | 2017-03-07 12:30 | N | N | issue temp settings for 885L GOI | Line |  |  | For Information Only
ENMAX | 5.8TR (ENMAX 5) | 2017-03-08 06:00 | 2017-03-10 18:00 | N | N | relay maintenance 87-D21. DGA 5.8TC. 5.8TR maintenance, LV breaker maintenance | Transformer |  |  | For Information Only
ALTALINK | 133L (19s Wabamun - 133L697A) | 2017-03-08 06:30 | 2017-03-08 14:30 | N | N | urgent conductor repair | Line |  |  | Pre-Condition
ALTALINK | 83s C2 (83s Taber),83s 67 (83s Taber) | 2017-03-08 07:00 | 2017-03-08 17:00 | N | N | Tech to perform C2 Cap Bank protection maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 885L (648s Metiskow - 650s Hansman Lake) | 2017-03-08 07:00 | 2017-03-09 17:30 | N | N | Damper replacements | Line |  |  | Overload
ALTALINK | 77s 452 (77s Sagitawah) | 2017-03-08 07:30 | 2017-03-08 17:30 | N | N | Breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 6.4TR (ENMAX 6) | 2017-03-08 08:00 | 2017-03-09 16:00 | N | N | shutters do not lift in time to clear breaker rosette's when racking in; bus and transformer outage are required to complete this repair | Transformer |  |  | For Information Only
ALTALINK | 310p 352 (310p Sundance) | 2017-03-08 09:00 | 2017-03-08 10:00 | N | Y | Trip test from 310p2452 breaker fail protection. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 80L (214s Innisfail - 55s Olds),55s 80N (55s Olds) | 2017-03-08 09:00 | 2017-03-08 16:00 | N | N | breaker maintenance on 55s80N (CB598) BO 138kV KSO bulk oil | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 170L (632s Russell - 799s Coleman) | 2017-03-08 09:00 | 2017-03-08 17:30 | N | Y | emergency repair; str33 crossarm replacement, str68 OHSW repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 652 (310p Sundance) | 2017-03-08 10:00 | 2017-03-08 11:00 | N | Y | trip test from 310p2452 breaker fail protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 250p11 (250p Bighorn) | 2017-03-08 11:00 | 2017-03-08 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 310p 952 (310p Sundance) | 2017-03-08 11:00 | 2017-03-08 12:00 | N | Y | trip test from 310p2452 breaker fail protection | Circuit Breaker |  |  | 240 kV
ALTALINK | 310p 1252 (310p Sundance) | 2017-03-08 12:00 | 2017-03-08 13:00 | N | Y | trip test from 310p2452 breaker fail protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1552 (310p Sundance) | 2017-03-08 13:00 | 2017-03-08 14:00 | N | Y | trip test from 310p2452 breaker fail protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1852 (310p Sundance) | 2017-03-08 14:00 | 2017-03-08 15:00 | N | Y | Trip test from 310p2452 breaker fail protection. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 2752 (310p Sundance) | 2017-03-08 15:00 | 2017-03-08 16:00 | N | Y | trip test from 310p2452 breaker fail protection | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
BCH | RAS3 - 786L RAS | 2017-03-08 17:30 | 2017-04-11 17:00 | N | N | forced outage | RAS |  |  | For Information Only
EPCOR | 816s T1 (816s Petrolia),816s P2401 (816s Petrolia),816s P2402 (816s Petrolia) | 2017-03-09 07:00 | 2017-03-17 17:00 | N | Y | relay maintenance and repairs | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2017-03-09 07:30 | 2017-03-22 16:30 | N | N | line rebuild (str1-114) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 212s 423 (212s Lacombe) | 2017-03-09 08:30 | 2017-03-13 09:00 | N | N | complete 423L new build between 212s and open point "H" at 332s | Circuit Breaker |  |  | For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2017-03-09 09:00 | 2017-03-09 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 417L (55s Olds - 281s Johnson),55s 417 (55S Olds) | 2017-03-09 09:00 | 2017-03-09 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 784L (332s Ellis - 784AL tap) | 2017-03-09 09:00 | 2017-03-09 13:30 | N | N | create open point I on 784L | Line |  |  | Creates Radial Feeds
ATCO | 939s 904 (939s Livock) | 2017-03-09 11:30 | 2017-03-09 14:30 | N | N | top up gas level to prevent low gas lockout | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ATCO | 700s 701T (700s Bonnyville),700s 703T (700s Bonnyville) | 2017-03-09 12:00 | 2017-03-11 07:00 | N | N | remove temp bypass between 701TD2 and 709A | Transformer |  | GOI on 144kV bus to remove temp bypass between 701TD2 and 709A | For Information Only
ALTALINK | 332s 784E (332s Ellis),784L (332s Ellis - 784AL tap) | 2017-03-09 13:30 | 2017-03-13 09:00 | N | N | complete 423L new build between 212s and open point "H" at 332s | Line, Circuit Breaker |  |  | Creates Radial Feeds
ALTALINK | 715L (648s Metiskow - 650s Hansman Lake) | 2017-03-09 17:30 | 2017-03-09 19:30 | N | N | remove temp settings for 885L GOI | Line |  |  | For Information Only
ATCO, ALTALINK | 9L961 (13s Deerland - 825s Whitefish Lake),13s 1452 (13s Deerland),13s 1352 (13s Deerland) | 2017-03-10 07:30 | 2017-03-10 12:30 | N | Y | change CT ratios | Line, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 285s T1 (285s East Camrose),730L (285s East Camrose - 730L62),285s 1 (285s East Camrose),285s East Camrose 138kV Partial Bus | 2017-03-10 10:00 | 2017-03-13 12:00 | N | N | repair 285s 1 | Bus, Line, Switch, Transformer |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 913L (69s North Barrhead - 732s Mitsue),913L (69s North Barrhead - 338s Cherhill),9L913 (69s North Barrhead - 732s Mitsue),69s North Barrhead 240kV Bus | 2017-03-13 06:00 | 2017-03-14 08:00 | N | Y | replace 240kV bus strain insulators and dead end structures for both sections of 913L and protection replacement for 913L - A732s coordinated with ATCO, replace 852 CT cables. | Bus, Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1059L (38s East Edmonton - 803s Lambton) | 2017-03-13 07:00 | 2017-03-13 07:15 | N | Y | de-energized to facilitate opening E52sEDS1 | Line
EPCOR | 52s T1 (52s East Industrial) | 2017-03-13 07:00 | 2017-03-17 17:00 | N | Y | relay operation checks | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 7L36 (820s Hangingstone - 2009s Willow Lake),820s 701 (820s Hangingstone) | 2017-03-13 07:00 | 2017-03-15 17:00 | N | N | install and test breaker fail protection, 7L36 will be open ended @ 820s | Circuit Breaker, Line |  | Install and test breaker fail protection, 7L36 will be open ended @ 820s. | For Information Only
ALTALINK | 310p 1852 (310p Sundance),310p 1752 (310p Sundance) | 2017-03-13 07:00 | 2017-03-19 17:30 | N | N | transformer maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | 803s L2402 (803s Lambton) | 2017-03-13 07:15 | 2017-03-17 16:45 | N | Y | breaker op-checks as part of relay maintenance and repairs to L2402 BF relay | Circuit Breaker |  |  | 240 kV, Firm Load Loss
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek) | 2017-03-13 07:30 | 2017-03-17 18:30 | N | N | line move & raise over Hwy 567 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2017-03-13 08:00 | 2017-03-19 16:00 | N | N | repair SF6 leak | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 332s T2 (332s Ellis),332s 784E (332s Ellis),332s 152 (332s Ellis),332s 352 (332s Ellis),332s Ellis 138 kV North Bus,332s C1 (332s Ellis),784L (332s Ellis - 784AL tap),212s 423 (212s Lacombe) | 2017-03-13 08:30 | 2017-04-18 17:00 | N | N | 423L new build and partial 784L re-build | Circuit Breaker, Line, Bus, Transformer, Shunts |  | Continue foundation work new 423/784L Mono pole, 423L new build, partial 784L re-build and relocate to new bay @ 332s. Close 423L Open Points "Y&H", and 784L Open Points "A&B" @ 332s. New 423L surge arrestor foundations, bus upgrade and P&C work | Creates Radial Feeds
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee) | 2017-03-13 11:00 | 2017-03-16 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 638S Esso Judy Creek | 2017-03-13 11:30 | 2017-03-15 17:30 | N | N | station maintenance | Station |  |  | For Information Only
Syncrude | Mildred_1015 (Syncrude Mildred Lake),UE_1 7201 (UE_1 Syncrude Plant 30-2),ML2 (Syncrude Mildred Lake - UE_1 Syncrude Plant 30-2) | 2017-03-14 07:00 | 2017-03-14 18:00 | N | N | cleaning and inspection on underground cable | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 305s1152 (305s Acheson) | 2017-03-14 08:00 | 2017-03-16 16:00 | N | N | in-service-date: Mar 14, 2017 | Circuit Breaker
ATCO | 7L92 (7L92D3 - 7L92D4) | 2017-03-14 08:00 | 2017-03-15 17:00 | N | N | replace cross arms and insulators, 777s radial fed from 819s, 956s radial fed from 709s | Line |  | replace cross arms and insulators, 777s radial fed from 819s, 956s radial fed from 709s | Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 34.4TR (ENMAX 34) | 2017-03-14 08:00 | 2017-03-21 16:00 | N | N | re-route 34.4TR secondary cables into 34B8-34.1TR cell | Transformer |  |  | For Information Only
ENMAX | 3.3TR (ENMAX 3) | 2017-03-14 08:00 | 2017-03-14 16:00 | N | N | relay testing | Transformer |  |  | For Information Only
ATCO, ALTALINK | 913L (69s North Barrhead - 732s Mitsue),9L913 (69s North Barrhead - 732s Mitsue) | 2017-03-14 08:01 | 2017-03-19 17:00 | N | Y | upgrade protection at both ends and AltaLink replace JB CT852 CT cables | Line |  | Upgrade protection at both ends. | 240 kV, Pre-Condition, Overload
ALTALINK | 45s T1 (45s Bretona) | 2017-03-14 08:30 | 2017-03-14 17:30 | N | N | replace TX equipment | Transformer |  |  | For Information Only
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2017-03-15 07:30 | 2017-03-16 16:00 | N | N | replace 283s9 VT2 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, REDDEER | 194s T1 (194s South Red Deer),194s3 (194s South Red Deer),425L (194s South Red Deer - 217s North Red Deer),194s 138kV Bus (194s South Red Deer) | 2017-03-15 07:30 | 2017-03-24 17:30 | N | N | to replace 138kV motor operated disconnects (MOD) 15-81-1 | Switch, Bus, Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX, NAKODA | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),47.2 TR (ENMAX 47),ENMAX 162 771 (ENMAX 162 Beddington) | 2017-03-15 08:00 | 2017-03-17 16:00 | N | N | SF6 gas sample 47BT3, doble 47B138-771, doble 47PT138-Z31, HV SW/MD maintenance 47.1MD, 47.2MD, SW81, SW82, SW83, SW84, SW85, SW86 | Line, Transformer, Switch |  |  | Contingency Requires Mitigation
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2017-03-15 08:00 | 2017-03-17 08:00 | N | N | upgrade the existing 69kV 13.60L line to 138kV | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.4TR (ENMAX 3) | 2017-03-15 08:00 | 2017-03-15 16:00 | N | N | relay testing | Transformer |  |  | For Information Only
ALTALINK | 377s 703E (377s Hardisty),703L (213s Hughenden - 703BL tap) | 2017-03-15 08:00 | 2017-03-16 17:00 | N | N | replace failing protections | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 562s 1652 (562s Cypress) | 2017-03-15 08:30 | 2017-03-15 15:30 | N | N | breaker maintenance 138kV SF6 Mitsubishi | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 54s 40 (54s Fort Saskatchewan) | 2017-03-15 08:30 | 2017-03-15 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 310P T33 (310P Sundance),310p 696 (310p Sundance) | 2017-03-15 08:30 | 2017-03-20 17:30 | N | Y | transformer maintenance | Transformer, Switch |  |  | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2017-03-15 08:30 | 2017-03-15 17:30 | N | N | urgent structure repair | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 526s C1 (526s Buffalo Creek),526s 652 (526s Buffalo Creek) | 2017-03-15 09:00 | 2017-03-15 16:30 | N | N | urgent breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 7L135 (820s Hangingstone - 977s Salt Creek),820s 704 (820s Hangingstone) | 2017-03-16 07:00 | 2017-03-18 17:00 | N | N | install and commission breaker fail protection | Circuit Breaker, Line |  | Install and commission breaker fail protection, 7L135 will be open ended @ 820s | For Information Only
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2017-03-16 08:00 | 2017-03-16 17:00 | N | N | replace cross arms and insulators, 777s and 956s radial fed from 819s | Line |  | replace cross arms and insulators, 777s & 956s radial fed from 819s | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 13s 452 (13s Deerland) | 2017-03-16 08:30 | 2017-03-16 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 14s T1 (14s Devon) | 2017-03-16 08:30 | 2017-03-16 17:30 | N | N | replace failing T1 protection | Transformer |  |  | For Information Only
ALTALINK | 186s T1 (186s Dry Creek) | 2017-03-16 12:30 | 2017-03-16 17:00 | N | N | replace broken insulator | Transformer |  | Urgent repair: Replace a broken insulator that is connected to a riser on underground cable, also shorten a 500mcm riser from the station service underground that is bent over and getting too close to the structure. | For Information Only
ATCO | 959S SVC (959s Lanfine) | 2017-03-16 16:00 | 2017-11-10 16:00 | N | Y | forced outage | Shunts |  |  | 240 kV
ATCO | 820s 505C1 (820s Hangingstone),820s 505C2 (820s Hangingstone),820s 505 (820s Hanging Stone) | 2017-03-17 07:00 | 2017-03-17 17:30 | N | N | Install and commission breaker fail protection | Circuit Breaker, Shunts |  | Loss of use of 10MVAR of capacitor banks for 25kv V control. Install and commission breaker fail protection | For Information Only
ENMAX | 1.81L (ENMAX 20 - ENMAX 1),ENMAX 20 B138-1.81 (ENMAX 20) | 2017-03-17 08:00 | 2017-03-17 16:00 | N | N | SF6 Gas Sample. Sheath test, DGA LPOF | Circuit Breaker, Line
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27) | 2017-03-17 08:00 | 2017-03-17 16:00 | N | N | urgent repairs on a damaged Switch 62 @ 16 Sub | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s SVC (102s Langdon) | 2017-03-17 08:00 | 2017-03-17 17:00 | N | Y | isolation of network equipment for diagnostic tools and diagnostic maintenance | Shunts |  | Diagnostic maintenance of proprietary SVC equipment for CIP compliance. Network equipment to be removed from network and isolated for diagnostic tools. Hands-on training for testing SVC I/O, facilitating the creation of system maintenance program. | 240 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2017-03-17 09:00 | 2017-03-19 16:30 | N | Y | align with 1201L outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook),520s T1 (520s Bennett) | 2017-03-17 09:00 | 2017-03-19 16:30 | Y | Y | swap out transformers back to normal T1-4 to T1-3 | Transformer, Line |  |  | Limits ATC, 500 kV
ALTALINK | 1059L (38s East Edmonton - 803s Lambton) | 2017-03-17 16:45 | 2017-03-17 17:00 | N | Y | EPCOR requires 1059L de-energized to facilitate closing E52sEDS1 | Line |  |  | 240 kV, Pre-Condition
ATCO | 820s 505C1 (820s Hangingstone),820s 505C2 (820s Hangingstone),820s 505 (820s Hanging Stone) | 2017-03-18 07:00 | 2017-03-18 17:30 | N | N | install and commission breaker fail protection | Circuit Breaker, Shunts |  | Loss of use of 10MVAR of capacitor banks for 25kv V control. Install and commission breaker fail protection
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2017-03-18 07:30 | 2017-03-19 17:30 | N | N | urgent post insulator repair on structure 147, replace structure 148 | Line |  |  | Creates Radial Feeds
ENMAX | 162s 240-RB134 (162s Beddington) | 2017-03-18 08:00 | 2017-03-18 10:30 | N | Y | SF6 gas re - sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 34.1TR (ENMAX 34) | 2017-03-18 08:00 | 2017-03-28 16:00 | N | N | forced outage and replace transformer | Transformer |  | 34.4TR out of service to transfer load from 34.1TR until Mar 23/17. 34.1TR forced outage and requires transformer to be replaced. | For Information Only
ENMAX | 162s 240-RB135 (162s Beddington) | 2017-03-18 10:30 | 2017-03-18 13:30 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 162s 240-RB132 (162s Beddington) | 2017-03-18 13:30 | 2017-03-18 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28),42s 28 (42s Sarcee),ENMAX 28 SW83 (ENMAX 28) | 2017-03-19 08:00 | 2017-03-19 12:00 | N | Y | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2017-03-19 12:00 | 2017-03-19 16:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s T3 (805s Jasper) | 2017-03-20 07:00 | 2017-03-25 17:00 | N | Y | performing Breaker op-checks as part of relay maintenance | Transformer |  |  | 240 kV, For Information Only
EPCOR | 803s L2403 (803s Lambton) | 2017-03-20 07:00 | 2017-03-24 17:00 | N | Y | performing Breaker op-checks as part of relay maintenance and repairs to L2403 BF relay | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 52s T2 (52s East Industrial) | 2017-03-20 07:00 | 2017-03-25 17:00 | N | Y | performing relay op-checks, Cutover of new ION meter | Transformer |  |  | 240 kV, For Information Only
EPCOR, ALTALINK | 908AL (52S East Industrial - 908L Tap),908L (89s Ellerslie - 908AL tap),908L (38s East Edmonton - 908AL tap) | 2017-03-20 07:00 | 2017-03-20 07:15 | N | Y | EPCOR requires 908L de-energized to facilitate opening E52sEDS2 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1),20PT138-Z31 (ENMAX 20) | 2017-03-20 08:00 | 2017-03-20 12:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.60L (ENMAX 27 - ENMAX 13) | 2017-03-20 08:00 | 2017-05-29 13:50 | N | N | upgrade the existing 69kV 13.60L line to 138kV | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 294S Brazeau Outletworks | 2017-03-20 08:00 | 2017-03-21 16:00 | N | N | maintenance | Station |  |  | For Information Only
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2017-03-20 08:00 | 2017-03-26 17:00 | N | N | line maintenance | Line |  | replace cross arms and insulators, 777s & 956s radial fed from 819s | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 973L (39s Bickerdike - 310p Sundance),310p Sundance 240kV Bus B | 2017-03-20 08:00 | 2017-03-23 17:00 | N | Y | insulator replacement and switch maintenance | Bus, Line |  |  | 240 kV, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 16.1TR (ENMAX 16) | 2017-03-20 08:00 | 2017-03-20 16:00 | N | N | relay maintenance. | Transformer |  |  | For Information Only
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2017-03-20 11:00 | 2017-03-23 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 500 kV
ENMAX | 20.3TR (ENMAX 20),20PT138-Z31 (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2017-03-20 12:00 | 2017-03-20 16:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 672L (235s Entwistle - 131s Moon Lake) | 2017-03-20 12:30 | 2017-03-20 17:30 | N | N | switch maintenance - 235s157 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2017-03-20 16:00 | 2017-03-21 11:30 | N | Y | TPR outage | Line |  |  | 240 kV, For Information Only
ENMAX | 8.2TR (ENMAX 8) | 2017-03-21 06:00 | 2017-03-22 18:00 | N | N | 8.2TC maintenance/inspection | Transformer |  |  | For Information Only
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark T3 (Meadowlark) | 2017-03-21 07:00 | 2017-03-21 17:00 | N | N | replace faulty bushing | Transformer, Line |  |  | For Information Only
EPCOR | Strathcona T3 (Strathcona) | 2017-03-21 07:00 | 2017-03-31 17:00 | N | N | cable repair | Transformer |  |  | For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2017-03-21 07:00 | 2017-03-21 18:00 | N | N | urgent repair on line | Line |  |  | Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 37s T6 (37s North Calder) | 2017-03-21 07:30 | 2017-03-21 17:30 | N | Y | replace slack span insulators on secondary bus between T6 and 37s4 | Transformer |  |  | Overload, Over/Under Voltage
ATCO | 7L27 (834s Wesley Creek - A793s West Peace River) | 2017-03-21 08:00 | 2017-03-23 16:00 | N | N | replace rotten crossarms | Line |  | replace rotten crossarms | Pre-Condition
ALTALINK | 906L (17s Benalto - 42s Sarcee),17s 34 (17s Benalto) | 2017-03-21 08:00 | 2017-03-23 17:00 | N | Y | replace 17s34 airbreak | Switch, Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 16.2TR (ENMAX 16) | 2017-03-21 08:00 | 2017-03-21 16:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
ALTALINK | 368s C1 (368s Burdett),368s 35 (368s Burdett) | 2017-03-21 09:00 | 2017-03-21 17:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
Lethbridge | 172L (370s North Lethbridge - 181s Chinook) | 2017-03-21 09:00 | 2017-04-09 18:30 | N | Y | line rebuild | Line |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ATCO | 748s 701PT (748s Haig River) | 2017-03-21 09:30 | 2017-03-21 15:00 | N | N | secondary wiring changes | Transformer |  |  | For Information Only
ALTALINK | 740L (58s Edson - 39s Bickerdike),58s 740X (58s Edson) | 2017-03-21 12:30 | 2017-03-21 17:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 8.4TR (ENMAX 8) | 2017-03-22 06:00 | 2017-03-24 18:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 890L (58s Edson - 207s Pinedale),58s 890 (58s Edson) | 2017-03-22 08:00 | 2017-03-22 17:30 | N | N | Maintain breaker | Circuit Breaker, Line |  |  | Creates Radial Feeds
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2017-03-22 08:00 | 2017-04-07 15:00 | N | N | structure upgrades | Line |  |  | For Information Only
ALTALINK | 370s T4 (370s North Lethbridge) | 2017-03-22 09:00 | 2017-03-22 17:00 | N | N | adjust 370s44 switch | Transformer |  | Adjust 370s44 switch, won't go past 90 degrees on open.
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2017-03-22 13:00 | 2017-03-22 14:00 | N | N | Spring Transmission Line Washing Potheads | Line |  |  | Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2017-03-22 14:00 | 2017-03-22 15:00 | N | N | Spring Transmission Line Washing Potheads | Line |  |  | Creates Radial Feeds
ALTALINK | 739L (14s Devon - 305s Acheson),305s 739X (305s Acheson) | 2017-03-22 16:00 | 2017-03-26 17:30 | N | N | Install new breaker fail trips and cross tripping module | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
Saskpower | SASK POWER P1C | 2017-03-23 04:00 | 2017-04-05 19:00 | N | N | remove portion of 138kV bus between 805B and 803A, CH805 nbr and CT test | Line |  |  | Limits ATC
ALTALINK | 244s T2 (244s Bowmanton),244s T1 (244s Bowmanton) | 2017-03-23 08:00 | 2017-03-23 17:00 | N | Y | investigate paralleling issues for T1 and T2 | Transformer |  | investigate paralleling issues for T1 and T2 Out of step relay operates when both transformers are on tap 1 and shouldn't. | 240 kV, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36) | 2017-03-23 08:00 | 2017-03-23 12:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),36B138-14.83 (ENMAX 36),ENMAX 14 B138-14.83 (ENMAX 14) | 2017-03-23 08:00 | 2017-03-23 12:00 | N | N | spring substation washing | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s 47 (370s North Lethbridge) | 2017-03-23 09:00 | 2017-03-23 12:00 | N | N | priority is critical for this heater to be fixed, heater replacement in south phase cabinet | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 36.1TR (ENMAX 36),36.3TR (ENMAX 36) | 2017-03-23 12:00 | 2017-03-23 18:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ENMAX | 7.84L (ENMAX 36 - ENMAX 7),ENMAX 36 B138-7.84 (ENMAX 36),ENMAX 7 B138-7.84 (ENMAX 7) | 2017-03-23 12:00 | 2017-03-23 14:00 | N | N | spring substation washing | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | ENMAX 36 B138-36.81 (ENMAX 36),44s 36_81E (44s Bearspaw),36.81L (44s Bearspaw - ENMAX 36) | 2017-03-23 14:00 | 2017-03-23 18:00 | N | N | spring substation washing | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2017-03-24 06:00 | 2017-05-15 16:30 | N | N | line rebuild (str1-114) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 801S Anderson,801s 701T (801s Anderson),801s 711 (801s Anderson) | 2017-03-24 07:00 | 2017-04-28 17:00 | N | N | 701T protection upgrade, maintenance on 701T, 711, and 501TD and 25 kV switches | Circuit Breaker, Transformer, Station |  | 701T protection upgrade, maint. on 701T, 711, and 501TD, 25kV offloaded to adjacent subs | For Information Only
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 ( 38s East Edmonton) | 2017-03-24 08:00 | 2017-03-24 13:30 | N | N | urgent breaker repair | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal) | 2017-03-24 08:00 | 2017-03-26 17:00 | N | Y | line mitigation | Line |  | LINE MITIGATION | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225AL (313s Raymond Reservoir - 225L tap),225L (67s Stirling - 225AL tap),225L (225s Magrath - 225AL tap) | 2017-03-25 07:00 | 2017-03-25 17:30 | N | N | repair broken strand | Line |  |  | Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2017-03-25 08:00 | 2017-03-25 16:00 | N | N | breaker Inspection | Line, Circuit Breaker |  |  | Creates Radial Feeds
EPCOR, ALTALINK | 908AL (52S East Industrial - 908L Tap),908L (89s Ellerslie - 908AL tap),908L (38s East Edmonton - 908AL tap) | 2017-03-25 16:45 | 2017-03-25 17:00 | N | Y | EPCOR requires 908L de-energized to facilitate closing E52sEDS2 | Line |  |  | 240 kV, Creates Radial Feeds
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2017-03-26 08:00 | 2017-03-26 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2017-03-26 12:00 | 2017-03-26 16:00 | N | Y | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 251s Whitla,983L (251s Whitla - 244s Bowmanton),964L (251s Whitla - 244s Bowmanton) | 2017-03-27 05:30 | 2017-03-28 19:30 | N | Y | emergency damper repair | Line, Station |  |  | 240 kV, Pre-Condition
EPCOR | 816s T2 (816s Petrolia),816s P2404 (816s Petrolia),816s P2405 (816s Petrolia) | 2017-03-27 07:00 | 2017-04-04 17:00 | N | Y | performing breaker op-checks as part of relay maintenance and repairs to P2404 BF and P2405 BFrelay. | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 805s T4 (805s Jasper),805s J2406 (805s Jasper),805s J2405 (805s Jasper) | 2017-03-27 07:00 | 2017-03-31 17:00 | N | Y | performing breaker op-checks as part of relay maintenance. | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 820s 702T (820s Hangingstone),820s 703 (820s Hangingstone) | 2017-03-27 07:00 | 2017-03-30 17:00 | N | N | CT ratio change and breaker fail protection install | Circuit Breaker, Transformer |  | CT ratio change and breaker fail protection install and commission, all load onto 701T | For Information Only
ATCO | 766s 701T (766s Nevis) | 2017-03-27 08:00 | 2017-03-27 08:15 | N | N | relay setting change - event report setting to capture loss of potential values | Transformer |  |  | For Information Only
ENMAX | 8.3TR (ENMAX 8) | 2017-03-27 08:00 | 2017-03-28 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 3.3TR (ENMAX 3) | 2017-03-27 08:00 | 2017-03-27 16:00 | N | N | relay testing | Transformer |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2017-03-27 08:00 | 2017-03-28 16:00 | N | N | 6BA25-6.4TR. shutters do not lift in time to clear breaker rosette's when racking in | Transformer |  |  | For Information Only
ALTALINK | 86s T1 (86s Bigstone) | 2017-03-27 08:00 | 2017-04-07 17:30 | N | Y | replace 240 kV / 138 kV bushings and misc TX maintenance | Transformer |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 310p 2152 (310p Sundance) | 2017-03-27 09:00 | 2017-03-27 10:00 | N | Y | trip test from 310p2452 breaker fail protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1206L (89s Ellerslie - 12s Heartland),89s 2152 (89s Ellerslie),89s 2252 (89s Ellerslie) | 2017-03-27 11:00 | 2017-03-30 17:00 | N | Y | SCADA equipment upgrade | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation, 500 kV
ALTALINK | 364s T2 (364s Whitecourt Industrial) | 2017-03-27 12:00 | 2017-03-27 16:00 | N | N | installing bird cover-up | Transformer |  |  | For Information Only
ALTALINK | 69s T5 (69s North Barrhead) | 2017-03-27 12:30 | 2017-03-28 17:30 | N | N | switch maintenance - 69s50 | Transformer |  |  | For Information Only
ALTALINK | 258s 652 (258s Dow Hydrocarbons) | 2017-03-27 13:30 | 2017-03-27 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ATCO | 6L12 (6L25 tap - 774s Monitor),774S 701T,774s 707 (774s Monitor) | 2017-03-28 07:00 | 2017-05-11 17:30 | N | N | replacing transformer | Line, Terminal Equipment, Circuit Breaker |  | Replacing transformer, 6L12 will be open ended at 774s, 773s radial fed from 775s. | Creates Radial Feeds
ALTALINK | 1064L (102s Langdon - 74s Janet) | 2017-03-28 07:30 | 2017-04-03 17:30 | N | Y | damper replacements | Line |  |  | 240 kV
ALTALINK | 65s T3 (65s High River) | 2017-03-28 08:00 | 2017-03-29 17:30 | N | N | remove temporary cables attached to T3 | Transformer |  |  | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2017-03-28 08:00 | 2017-03-28 16:00 | N | N | relay testing | Transformer |  |  | For Information Only
ALTALINK | 364s T1 (364s Whitecourt Industrial) | 2017-03-28 08:00 | 2017-03-30 16:00 | N | N | 364s T1 and 25 kV bus 1 - installing bird cover-up | Transformer |  |  | For Information Only
ALTALINK | 65s 16E (65s High River) | 2017-03-28 08:00 | 2017-03-28 17:30 | N | N | remove temp cables from breaker | Circuit Breaker |  |  | For Information Only
ALTALINK | 54L (118s Canmore - 54L172),118s 54W (118s Canmore) | 2017-03-28 08:30 | 2017-03-28 17:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
BCH | 5L71 (Mica Creek - Nicola) | 2017-03-28 09:00 | 2017-03-28 17:00 | N | N | complete nerc testing of 5CX1 pn's (py and sy) associated with cap banks to be blocked oat during testing, no platform access required | Line |  |  | Limits ATC, 500 kV
BCH | 5L96 (Selkirk - Vaseux Lake) | 2017-03-28 09:00 | 2017-03-31 17:00 | N | Y | replace marker balls, shot insulators and damaged conductor | Line |  |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK | 678s T1 (678s Okotoks),646L (678s Okotoks - 237s Foothills),678s Okotoks 138kV Bus 1,850L (525s Carseland - 678s Okotoks) | 2017-03-28 10:00 | 2017-04-13 14:00 | N | N | connect 678s47 bus tie switch & VT5, install new 678s352 (mechanically locked out), connect 678s52 to 138kV bus | Line, Bus, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 3.4TR (ENMAX 3) | 2017-03-28 12:00 | 2017-03-29 16:00 | N | N | relay testing | Transformer |  |  | For Information Only
Syncrude | Mildred T6 (Syncrude Mildred Lake),Mildred 635 (Syncrude Mildred Lake),Mildred 13.8 kV Bus 6 (Syncrude Mildred lake) | 2017-03-29 07:00 | 2017-04-12 18:00 | N | N | 5 year PM | Transformer, Circuit Breaker, Bus |  |  | For Information Only
EPCOR | 814s T1 (814s Bellamy) | 2017-03-29 07:00 | 2017-03-29 17:00 | N | Y | repair | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 723L (69s North Barrhead - 723L133),69s 723E (69s North Barrhead) | 2017-03-29 07:30 | 2017-03-29 17:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 8.6TR (ENMAX 8) | 2017-03-29 08:00 | 2017-03-30 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28),42s 28 (42s Sarcee),ENMAX 28 SW83 (ENMAX 28) | 2017-03-29 08:00 | 2017-03-29 12:00 | N | Y | spring substation washing | Line, Transformer, Circuit Breaker, Switch |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.2TR (ENMAX 15) | 2017-03-29 08:00 | 2017-03-29 16:00 | N | N | relay testing | Transformer |  |  | For Information Only
ENMAX | 26.2TR (ENMAX 26) | 2017-03-29 08:00 | 2017-03-30 16:00 | N | N | 26BB25-26.2TR maintenance | Transformer |  | 26BB25-26.2TR maintenance. Check Alignment to Bus Stabs & Shutter Operation. Bus Outage Required | For Information Only
ALTALINK | 71s 252 (71s Lamoureux) | 2017-03-29 08:30 | 2017-03-29 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
BCH | 5L72 (Mica Creek - Nicola) | 2017-03-29 09:00 | 2017-03-29 17:00 | N | N | complete NERC testing of 5CX2 | Line |  | complete nerc testing of 5CX2, pn's (py and sy) associated with cap banks to be blocked oat during testing, no platform access required | Limits ATC, 500 kV
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2017-03-29 12:00 | 2017-03-29 16:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2017-03-30 07:30 | 2017-03-30 16:30 | N | N | emergency repairs to OHSW Str 529-530; lightning damage | Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2017-03-30 08:00 | 2017-03-30 12:00 | N | N | spring substation washing | Transformer, Line |  |  | Creates Radial Feeds
AESO-SC | Northwestern Energy BUCC test | 2017-03-30 08:00 | 2017-03-30 12:00 | N | N | BUCC test | Station |  |  | Affects Visibility
ALTALINK | 56s C1 (56s Boyle) | 2017-03-30 08:30 | 2017-03-30 17:30 | N | N | repair SF6 leak - urgent & maintenance on 56s27 after repair | Shunts |  |  | Pre-Condition
Saskpower | Sask Power S1C line | 2017-03-30 11:00 | 2017-03-30 19:00 | N | N | commission CH804 bkr to new bus | Line |  |  | Limits ATC
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2017-03-30 12:00 | 2017-03-30 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2017-03-31 08:00 | 2017-03-31 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds
ATCO | 730s 701A (730s Rycroft) | 2017-03-31 08:00 | 2017-04-24 18:00 | N | N | install new 704 between 701A and 7L68D2 @ 730s | Switch |  | 7L68 Breaker 704 addition & breaker fail protection @ 730s, 7L68 line protection upgrade, 7L68 will be tied to 7L10 via bypass 7L68D3 Mar 31-Apr 24, GOI will be expanded to 7L68D3, 701A @ 730s and 707A @ 811s Apr 24 PM - May 5. Work sequence Mar 30 1. CSP - 7L68 21A/21B relay setting changes at 811s Mar 31 2. CSP - 7L10 21A/21B relay setting changes at 730s 3. Close 7L68D3 @ 730s (7L68 tied to 7L10) 4. Isolate 144kV bus @ 730s (Isolation Pts 701A, 7L68D2 @ 730s) 5. Issue GOI 2-34339A Apr 24 6. Expand GOI (Isolation pts 701A, 7L68D3 @ 730s, 707A @ 811s), 7L68 OOS, 754s, 730s radial fed from 800s 7. Issue GOI 2-34339B, release 2-34339B 8. Release CSP - 7L68 21A/21B relay setting changes at 811s 9. Release CSP - 7L10 21A/21B relay setting changes at 730s May 8 10. Release GOI 2-34339B, place 7L68 back in service 2. Close bypass switch 7L68D3 3. Issue GOI 34339A (Isol. pts - 701A, 7L68D2) - breaker 704 install 4. Return 811s 7L68 relay settings to normal 5. Return 730s 7L10 relay settings to normal | Pre-Condition
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2017-03-31 12:00 | 2017-03-31 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX | 162s 138-RB85 (162s Beddington) | 2017-04-01 08:00 | 2017-04-01 12:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | For Information Only
ALTALINK | 86s T1 (86s Bigstone),914L (86s Bigstone - 89s Ellerslie),914L (86s Bigstone - 87s Gaetz),86s 1252 (86s Bigstone),86s 1752 (86s Bigstone) | 2017-04-01 08:00 | 2017-04-02 17:30 | N | Y | breaker 86s1752 and switch 86s12A maintenance | Transformer, Line, Circuit Breaker |  |  | 240 kV, Overload
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),ENMAX 14 B138-14.83 (ENMAX 14) | 2017-04-01 11:03 | 2017-05-15 17:00 | N | N | forced outage | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 932L (74s Janet - 162s Beddington),162s 240-RB135 (162s Beddington),162s 240-136 (162s Beddington) | 2017-04-01 12:00 | 2017-04-01 16:00 | N | Y | double PT 932L | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 805s C1 (805s Jasper),805s T1 (805s Jasper),805s J2403 (805s Jasper),805s J2401 (805s Jasper) | 2017-04-03 07:00 | 2017-04-07 17:00 | N | Y | breaker op-checks as part of relay maintenance | Transformer, Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 803s L2404 (803s Lambton) | 2017-04-03 07:00 | 2017-04-04 15:00 | N | Y | relay maintenance and repairs | Circuit Breaker |  | Performing Breaker op-checks as part of relay maintenance and repairs to L2404 BF relay. | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s T1 (89s Ellerslie) | 2017-04-03 07:00 | 2017-04-06 17:00 | N | Y | SCADA equipment upgrade | Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ENMAX | 16.1TR (ENMAX 16) | 2017-04-03 08:00 | 2017-04-03 16:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
ENMAX | 22.1TR (ENMAX 22) | 2017-04-03 08:00 | 2017-04-06 16:00 | N | N | LTC maintenance on X & Y windings and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 905L (19s Wabamun - 37s North Calder),37s 82 (37s North Calder),37s79 (37s North Calder) | 2017-04-03 10:30 | 2017-04-05 06:03 | N | Y | maintenance on switch 37s79 and breaker 37s82 | Line, Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 205s 352 (205s Castle Rock) | 2017-04-03 13:00 | 2017-04-03 16:00 | N | Y | heater replacement on centre phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 89s T1 (89s Ellerslie),89s 1352 (89s Ellerslie),89s 652 (89s Ellerslie),89s 252 (89s Ellerslie),89s 952 (89s Ellerslie),89s Ellerslie 240kV Bus 1 | 2017-04-04 07:00 | 2017-04-04 18:00 | N | Y | switch maintenance - 89s1 and 89s9 | Bus, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1065L (102s Langdon - 74s Janet) | 2017-04-04 07:30 | 2017-04-08 17:30 | N | Y | damper replacements | Line |  |  | 240 kV
ALTALINK | 428s T2 (428s Namaka) | 2017-04-04 09:00 | 2017-04-04 16:00 | N | N | install new weschler temperature monitor for the transformer | Transformer
ALTALINK | 71s 552 (71s Lamoureux) | 2017-04-05 08:30 | 2017-04-06 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 324s 1752 (324s Cassils) | 2017-04-05 09:30 | 2017-04-05 12:00 | N | Y | heater replacement on the west phase | Circuit Breaker |  | Priority is critical for this heater to be fixed. Heater replacement on the west phase. | 240 kV
ATCO | 789s 701R (789s Keg River),789s 706C (789s Keg River),789s 700 Bus 1 (789s Keg River) | 2017-04-05 12:00 | 2017-04-06 12:00 | N | N | connect new sub to old sub, 701R and 706C will be out-of-service and unavailable for dispatch | Bus, Shunts |  | Connect new sub to old sub, 701R and 706C will be OOS and unavailable for dispatch | Pre-Condition
ALTALINK | 708AL (388s Riverside - 708L tap),388s 708A (388s Riverside) | 2017-04-05 12:30 | 2017-04-05 13:30 | N | N | customer replacing 125 Vdc breakers, 388s708A opened for safety - no tripping power | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 324s 2052 (324s Cassils) | 2017-04-05 13:00 | 2017-04-05 17:00 | N | Y | heater replacement on the east phase | Circuit Breaker |  | Priority is critical for this heater to be fixed. Heater replacement on the east phase. | 240 kV
ENMAX | 34.4TR (ENMAX 34) | 2017-04-06 07:00 | 2017-04-06 12:00 | N | N | measurements for CT install | Transformer
ENMAX | 31.3TR (ENMAX 31) | 2017-04-06 08:00 | 2017-04-06 16:00 | N | N | maintenance | Transformer
ALTALINK | 71s C2 (71s Lamoureux),71s 1052 (71s Lamoureux) | 2017-04-06 11:15 | 2017-04-06 13:45 | N | N | urgent repair | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 34.2TR (ENMAX 34) | 2017-04-06 12:00 | 2017-04-06 17:00 | N | N | measurements for CT install | Transformer
ALTALINK | 71s C1 (71s Lamoureux),71s 952 (71s Lamoureux) | 2017-04-06 13:45 | 2017-04-06 16:15 | N | N | urgent repair | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 739L (305s Acheson - 434s Stony Plain),305s Acheson 138 kV West Bus,677L (305s Acheson  595s Spruce Grove) | 2017-04-07 07:15 | 2017-04-21 17:45 | N | N | install new breaker | Line, Bus |  | Install new breaker s1152, creating 138B1/138B2 and install new protection on the 138KV system | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
DAISHOWA | 147S Daishowa Plant | 2017-04-07 18:00 | 2017-04-07 19:00 | N | N | ADAMS dispatch interruption for bandwidth upgrade | Station |  |  | For Information Only
ALTALINK, EPCOR | 1043L (320p Keephills - 816s Petrolia) | 2017-04-08 07:30 | 2017-04-18 17:30 | N | Y | install foundations for future line tap to new 289s | Line |  |  | 240 kV
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2017-04-08 08:00 | 2017-04-08 16:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2017-04-09 07:30 | 2017-04-10 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Overload
EPCOR | 803s L2405 (803s Lambton) | 2017-04-10 07:00 | 2017-04-14 17:00 | N | Y | performing breaker checks as part of relay maintenance and repairs to L2405 breaker fail relay | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Medicine Hat | MH69s2 MH69_212 (MH69s2 North Industrial),MH69s2 MH69_215 (MH69s2 North Industrial),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights),MH69s2 MH69-T22(North Industrial Substation) | 2017-04-10 07:00 | 2017-04-10 16:00 | N | N | connection of new 69 kV disconnect switch | Transformer, Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47),3L (42s Sarcee - 272s Springbank) | 2017-04-10 07:15 | 2017-04-17 18:45 | N | N | SWCRR: install new foundations for future line structures | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),16B69-15.62 (ENMAX 16) | 2017-04-10 08:00 | 2017-04-11 16:00 | N | N | breaker inspection | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 12.1TR (ENMAX 12) | 2017-04-10 08:00 | 2017-04-11 16:00 | N | N | LTC maintenance and check reversing software | Transformer |  |  | For Information Only
Lethbridge, ALTALINK | 725L (674s Lethbridge Bowron - 725BL54),674s 725W (674s Lethbridge Bowron) | 2017-04-10 08:00 | 2017-04-11 18:00 | N | Y | L674s725W breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.7TR (ENMAX 1) | 2017-04-10 08:00 | 2017-04-13 16:00 | N | N | doble 1.7TR | Transformer |  |  | For Information Only
ATCO | 709s 603T (709s Vegreville),709s 604T (709s Vegreville),709s 702T (709s Vegreville),709s 601 (709s Vegreville),709s 602 (709s Vegreville) | 2017-04-10 09:00 | 2017-04-21 16:00 | N | N | salvage 601 breaker | Circuit Breaker, Transformer |  | 709S - 601 Breaker Salvage Isolate Breaker 601 and decommission 702T, 603T and 604T will be out of service for the duration of work. These can be returned to service in an emergency situation in approximately 3 hours. | For Information Only
EPCOR | 814s T2 (814s Bellamy) | 2017-04-10 09:00 | 2017-04-10 13:00 | N | Y | urgent repair  remove birds nest | Transformer |  | URGENT REPAIR - REMOVE BIRD'S NEST - ENCROACHING ON LIMITS & BLOCKING FANS | 240 kV, Contingency Requires Mitigation
ALTALINK | 171s T1 (171s Redwater) | 2017-04-10 11:00 | 2017-04-10 18:00 | N | N | remove raven nest and repair hot spot on 171s6 | Transformer |  |  | For Information Only
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove),61s 836N (61s Lodgepole) | 2017-04-10 11:00 | 2017-04-10 18:30 | N | Y | maintenance on 61s211 and 61s836N | Line, Circuit Breaker |  |  | Overload, Restricts Generation
ALTALINK | 83s T3 (83s Taber) | 2017-04-10 12:00 | 2017-04-11 17:00 | N | N | doble and maintain | Transformer |  |  | For Information Only
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove),61s 836N (61s Lodgepole) | 2017-04-11 07:30 | 2017-04-11 14:30 | N | Y | breaker maintenance if not completed on April 10 | Line, Circuit Breaker |  |  | Overload, Restricts Generation
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2017-04-11 07:30 | 2017-04-12 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Overload
ALTALINK | 324s 1752 (324s Cassils) | 2017-04-11 08:00 | 2017-04-11 12:00 | N | Y | heater replacement | Circuit Breaker |  | Priority is critical for this heater to be fixed. Heater replacement on the west phase . | 240 kV, Pre-Condition
ALTALINK | 221s T2 (221s Sunken Lake) | 2017-04-11 08:00 | 2017-04-11 17:30 | N | N | setting change on protections | Transformer |  |  | For Information Only
ENMAX | 14.1TR (ENMAX 14) | 2017-04-11 08:00 | 2017-04-11 12:00 | N | N | measure transformer bushing turret | Transformer |  |  | For Information Only
ALTALINK | 368s T2 (368s Burdett) | 2017-04-11 08:30 | 2017-04-11 17:00 | N | N | techs to change low oil alarm on the tap changer to a trip | Transformer |  |  | For Information Only
ALTALINK | 368s C2 (368s Burdett),368s Burdett RTU/SCADA | 2017-04-11 08:30 | 2017-04-11 17:00 | N | N | change SCADA configuration to poll the relay | Terminal Equipment, Shunts |  |  | For Information Only
ALTALINK | 150s T1 (150s Clyde) | 2017-04-11 08:30 | 2017-04-11 14:30 | N | N | transformer bushing hot spot | Transformer |  |  | For Information Only
ALTALINK | 512S Hartell,812L (392s Black Diamond - 65s High RIver) | 2017-04-11 08:30 | 2017-04-12 17:00 | N | N | adjust 138kV switch 392s812X and fix 512sT1 oil leak | Line, Station |  |  | Pre-Condition
ATCO | 7L56 (813s Little Smoky - 725s Goose River) | 2017-04-11 09:00 | 2017-04-11 15:00 | N | N | 813S 7L56 21 relay microprocessor based complete testing | Line |  | 813S 7L56 21 relay microprocessor based complete Testing 67N Relay in service | Pre-Condition
NOVACORP | 330s BR_50 (330s Nova Corp),330s Nova Corp 138kV Bus 1B | 2017-04-11 09:00 | 2017-04-13 17:00 | N | Y | maintenance on BR-50 | Bus, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 121s T5 (121s Brooks) | 2017-04-11 11:00 | 2017-04-12 17:00 | N | N | doble and maintain 121sT5 Tx18407 | Transformer |  |  | For Information Only
ALTALINK | 324s 2052 (324s Cassils) | 2017-04-11 13:00 | 2017-04-11 17:00 | N | Y | heater replacement | Circuit Breaker |  | Priority is critical for this heater to be fixed. Heater replacement on the east phase . | 240 kV, Pre-Condition
ALTALINK, REDDEER | 194s T2 (194s South Red Deer),194s3 (194s South Red Deer),426L (194s South Red Deer - 63s Red Deer),63s 426 (63s Red Deer),194s 138kV Bus (194s South Red Deer) | 2017-04-12 07:30 | 2017-04-21 17:30 | N | N | replace 138kV motor operated disconnects (MOD) 15-81-2, ALM to do maintenance on switches,CT, and breaker at 194s | Line, Bus, Switch, Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | Enmax 1 B138-4A0 (ENMAX 1) | 2017-04-12 08:00 | 2017-04-13 16:00 | N | N | repair close coil | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),15B69-15.62 (ENMAX 15) | 2017-04-12 08:00 | 2017-04-13 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker |  |  | For Information Only
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2017-04-12 08:00 | 2017-04-13 18:00 | N | Y | breaker maintenance,city of Lethbridge requesting breaker open advice | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 417L (55s Olds - 281s Johnson),55s 417 (55S Olds) | 2017-04-12 09:00 | 2017-04-12 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power S1C line | 2017-04-12 11:00 | 2017-04-13 19:00 | N | Y | commission CH804 bkr to new bus | Line |  |  | Limits ATC
ALTALINK | 83s T1 (83s Taber) | 2017-04-12 13:00 | 2017-04-12 16:30 | N | N | remove birds nest | Transformer |  | remove birds nest in 25kV bus above 83s313N | Restricts Generation
SUNCOR | 29EDD-71 Edd71Sub | 2017-04-14 06:00 | 2017-05-01 18:00 | N | N | switch and breaker maintenance | Station |  | Turnaround activities, taking opportunity to do maintenance activities on switches (29PS-240, 29PS-241, 29PS-239, 29PS-242, 29PS-243, 29PS-250, 29PS-251, 29PS-252, 29PS-253, 29PS-254), breakers (752-4622, 752-4623, 752-4632, 752-4633) and transformers (29PT-232, 29PT233). Each element will be isolated during maintenance activities, no change to power flow. | For Information Only
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap) | 2017-04-14 07:00 | 2017-04-14 17:00 | N | Y | line maintenance and upgrades | Line |  |  | Firm Load Loss
ATCO | 715s 701T (715s Leming Lake) | 2017-04-14 08:00 | 2017-05-30 16:00 | N | N | tripped to lock-out due to 63T gas detector | Transformer |  | 701T Tripped to Lock-out due to 63T Gas Detector. Requires isolation for testing. | For Information Only
ALTALINK | 676L (523s Bullshead - 244s Bowmanton) | 2017-04-16 06:30 | 2017-04-21 16:00 | N | Y | replace saddles | Line |  |  | Creates Radial Feeds
ALTALINK, EPCOR | 1238L (510s Sunnybrook - 330p Genesee),1325L (510s Sunnybrook - 511s Crossings) | 2017-04-16 11:00 | 2017-04-26 12:00 | N | Y | WATL warranty work and maintenance | Line |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2017-04-17 18:46 | 2017-04-23 08:00 | N | N | SWCRR: install new foundations for future line structures | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | ML1 (Syncrude Mildred Lake - D05 Syncrude) | 2017-04-18 07:00 | 2017-04-18 18:00 | N | N | PM - insulator cleaning and inspection | Line |  |  | Creates Radial Feeds
EPCOR, ALTALINK | 816s P2403 (816s Petrolia),816s P2404 (816s Petrolia),816s PDS12 (816s Petrolia),320P 289 (320p Keephills) | 2017-04-18 07:00 | 2017-04-18 17:30 | N | Y | repair - hot switch | Circuit Breaker, Switch |  |  | 240 kV
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23),ENMAX 2 MD138-2.83 (ENMAX 2) | 2017-04-18 08:00 | 2017-04-18 16:00 | N | N | SF6 gas sample,Doble CT, HV maintenance 23.3MD, SW81, SW82, SW83 | Line, Transformer, Switch |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s 1152 (535s Joffre) | 2017-04-18 09:30 | 2017-04-18 16:00 | N | N | maintain 138kV SF6 breaker | Circuit Breaker |  |  | For Information Only
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2017-04-18 09:30 | 2017-05-26 17:30 | N | Y | relocate structures | Line |  |  | Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
Saskpower | Sask Power S1C line | 2017-04-18 10:00 | 2017-04-19 16:00 | N | Y | commission CH804 bkr to new bus | Line |  |  | Limits ATC
ALTALINK | 245s 1 (245s Seebe) | 2017-04-18 11:00 | 2017-04-28 14:30 | N | N | TAU request | Switch |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 42s T1 (42s Sarcee) | 2017-04-18 12:30 | 2017-04-28 06:59 | N | Y | bushing replacements and doble testing | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 58s C1 (58s Edson),58s T2 (58s Edson),671L (58s Edson - 39s Bickerdike),890L (58s Edson - 207s Pinedale),58s Edson 138kV West Bus | 2017-04-18 13:00 | 2017-04-18 18:00 | N | N | switch maintenance - 58s36, 58s145 | Transformer, Bus, Line, Shunts |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 492s T1 (492s Monarch) | 2017-04-18 13:00 | 2017-04-18 16:00 | N | N | hot spot on 25kV switch(492s2), clean and lube up the switch and adjust if needed | Transformer |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2017-04-18 23:00 | 2017-04-19 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ATCO | EX1-01 (879s Scotford Upgrader - 402s Scotford Expansion),879s 701T (879s Scottford Upgrader) | 2017-04-19 07:00 | 2017-04-28 17:30 | N | N | 879s 701T and 879S 501R: install disconnect switch for FCL (fault current limiter) | Transformer, Line |  | Install disconnect switch for FCL (Fault Current Limiter), EX1-01L will be open ended @ 879s 5-10 min Apr 19 and again Apr 28 for 701T switching in/out of service | Creates Radial Feeds
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia),816s P2405 (816s Petrolia),816s P2406 (816s Petrolia) | 2017-04-19 07:00 | 2017-04-24 15:02 | N | Y | EPCOR performing breaker op-checks as part of relay maintenance and repairs to P2406 BF relay | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, For Information Only
ALTALINK | 39s 37 (39s Bickerdike) | 2017-04-19 07:30 | 2017-04-19 13:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 23.80L Enmax Advice | 2017-04-19 07:30 | 2017-04-19 16:30 | N | N | HV SW maintenance SW84, SW87, 23.4MD, SW88 | Terminal Equipment
ALTALINK | 5s C3 (5s East Calgary),5s 7 (5s East Calgary),5s C4 (5s East Calgary) | 2017-04-19 08:00 | 2017-04-19 16:00 | N | N | breaker maintenance | Shunts, Circuit Breaker |  | Breaker maintenance SF6 breaker | For Information Only
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2017-04-19 08:00 | 2017-04-19 16:00 | N | Y | HV SW maintenance | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 39s 38 (39s Bickerdike) | 2017-04-19 13:00 | 2017-04-19 18:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek) | 2017-04-19 13:00 | 2017-04-20 17:00 | N | Y | replace poles for road crossing | Line |  | replace poles for road crossing | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 62s12 (62s Brazeau) | 2017-04-19 23:00 | 2017-04-20 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 737L (95s Imperial Oil Edmonton - 38s East Edmonton) | 2017-04-20 07:15 | 2017-04-21 19:15 | N | N | component replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s T1 (58s Edson),202L (58s Edson - 178s Cynthia),740L (58s Edson - 39s Bickerdike),58s Edson 138kV East Bus | 2017-04-20 07:30 | 2017-04-20 16:30 | N | N | switch maintenance 58s201 | Bus, Line, Transformer |  |  | Over/Under Voltage
ALTALINK | 159s T2 (159s Colinton) | 2017-04-20 10:30 | 2017-04-21 15:30 | N | N | T2 warranty work | Transformer |  |  | For Information Only
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2017-04-21 08:00 | 2017-04-21 12:00 | N | N | change out street light davit | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 874L (522s Cooking Lake - 45s Bretona) | 2017-04-21 12:01 | 2017-04-23 16:00 | N | N | 522s reconfiguration | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s C1 (305s Acheson),305s32 (305s Acheson) | 2017-04-21 17:01 | 2017-05-10 07:59 | N | N | move 305s32 and C1 to new location | Shunts, Switch |  |  | Pre-Condition
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap) | 2017-04-22 07:00 | 2017-04-23 17:00 | N | Y | EPCOR - line maintenance and upgrades | Line |  |  | Firm Load Loss
ALTALINK | 320p 752 (320p Keephills),320p 652 (320p Keephills) | 2017-04-22 07:30 | 2017-05-08 16:30 | N | Y | maintenance and operational testing of 320p589 and CT replacement on 320p852 | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton) | 2017-04-22 08:00 | 2017-04-22 16:00 | N | N | emergency repair on structure 73 | Line |  |  | For Information Only
ENMAX | 37.81L (ENMAX 38 - ENMAX 37),ENMAX 37 B138-37.81 (ENMAX 37) | 2017-04-22 08:00 | 2017-04-23 16:00 | N | N | breaker maintenance (HLR) | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72LH8 (Hardisty - 803s Lambton),72LS24 (Strathcona - 803s Lambton) | 2017-04-23 04:00 | 2017-04-23 10:00 | N | N | performing relay op-checks as part of relay maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 803s T3 (803s Lambton) | 2017-04-23 04:00 | 2017-04-23 10:00 | N | Y | performing relay op-checks as part of relay maintenance | Transformer |  | Repairs to L2404 BF relay as part of relay manufacturer bulletin. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s T4 (38s East Edmonton) | 2017-04-23 05:00 | 2017-04-24 08:00 | N | Y | begin removal of T4 | Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
ALTALINK, EPCOR | 1059L (38s East Edmonton - 803s Lambton),38s East Edmonton 240 kV Bus 2 | 2017-04-23 08:00 | 2017-04-29 10:00 | N | Y | replace insulators on 240kV bus 2 and 1059L | Line, Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
CMH | CMH1 Medicine Hat #1 Generator Test | 2017-04-23 08:00 | 2017-04-24 06:59 | N | N | CMH#14 commissioning test after AVR replaced | Unit
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-04-23 08:01 | 2017-04-27 18:45 | N | N | SWCRR: install new foundations for future line structures | Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2017-04-24 06:30 | 2017-04-24 18:44 | N | Y | replace saddles | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1059AL (52s East Industrial - 1059L tap),1059L (38s East Edmonton - 803s Lambton) | 2017-04-24 07:00 | 2017-04-24 07:15 | N | Y | EPCOR requires 1059L de-energized to facilitate opening E52sEDS1 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s T2 (89s Ellerslie) | 2017-04-24 07:00 | 2017-04-27 17:00 | N | Y | SCADA equipment upgrade | Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
EPCOR | 52s T1 (52s East Industrial) | 2017-04-24 07:00 | 2017-04-28 17:00 | N | Y | doble | Transformer |  |  | 240 kV, For Information Only
EPCOR | RossdaleT2 (Rossdale) | 2017-04-24 07:00 | 2017-05-05 12:00 | N | N | cutting over and commissioning new transformer protection | Transformer |  |  | Pre-Condition
Medicine Hat | MH69s2 MH69_215 (MH69s2 North Industrial),MH69s2 MH69-T22 (North Industrial Substation) | 2017-04-24 07:00 | 2017-04-28 16:00 | N | N | process the oil in Transformer | Transformer, Circuit Breaker |  | From April 24  April 28, 2017 the City of Medicine Hat Electric Distribution will be taking an outage on transformer T-22 located at MH-2S North Industrial Substations. The equipment included as part of the outage is: Transformer T-22 Disconnect Switch  MH69-214 Circuit Breakers  MH69-215 & 2S2-Main (15kV Circuit breaker) Scope of work will be to process the oil in Transformer T-22. | For Information Only
ENMAX | 3.3TR (ENMAX 3) | 2017-04-24 08:00 | 2017-05-08 16:00 | N | N | TR bushing/CT replacement and TR diff relay replacement | Transformer |  |  | For Information Only
ALTALINK | 133S Stelco Edmonton | 2017-04-24 08:00 | 2017-05-10 17:00 | N | N | maintenance | Station |  |  | Firm Load Loss
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake),811s 707 (811s Clairmont Lake),730s 701A (730s Rycroft) | 2017-04-24 08:00 | 2017-05-05 16:00 | N | N | 7L68 Breaker 704 addition & breaker fail protection @ 730s, 7L68 line protection upgrade | Line, Circuit Breaker, Switch |  | 7L68 Breaker 704 addition & breaker fail protection @ 730s, 7L68 line protection upgrade, 7L68 will be tied to 7L10 via bypass 7L68D3 Mar 31-Apr 24, GOI will be expanded to 7L68D3, 701A @ 730s and 707A @ 811s Apr 24 PM - May 5. Work sequence Mar 30 1. CSP - 7L68 21A/21B relay setting changes at 811s Mar 31 2. CSP - 7L10 21A/21B relay setting changes at 730s 3. Close 7L68D3 @ 730s (7L68 tied to 7L10) 4. Isolate 144kV bus @ 730s (Isolation Pts 701A, 7L68D2 @ 730s) 5. Issue GOI 2-34339A Apr 24 6. Expand GOI (Isolation pts 701A, 7L68D3 @ 730s, 707A @ 811s), 7L68 OOS, 754s, 730s radial fed from 800s 7. Issue GOI 2-34339B, release 2-34339B 8. Release CSP - 7L68 21A/21B relay setting changes at 811s 9. Release CSP - 7L10 21A/21B relay setting changes at 730s May 8 10. Release GOI 2-34339B, place 7L68 back in service 2. Close bypass switch 7L68D3 3. Issue GOI 34339A (Isol. pts - 701A, 7L68D2) - breaker 704 install 4. Return 811s 7L68 relay settings to normal 5. Return 730s 7L10 relay settings to normal | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 166s T3 (166s Dow Chemical Fort Saskatchewan),787L (166s Dow Chemical Fort Saskatchewan - 787L33),166s Dow Chemical Fort Saskatchewan 138kV Bus 1 | 2017-04-24 08:00 | 2017-05-01 17:00 | N | Y | work on Bus & PT2 coordinated with 166s T3 outage | Bus, Line, Transformer |  |  | Pre-Condition, Overload, Restricts Generation
ALTALINK | 38s T2 (38s East Edmonton),38s T4 (38s East Edmonton),780L (38s East Edmonton - 149s Nisku),897L (38s East Edmonton - 45s Bretona),822L (133s Stelco Edmonton - 38s East Edmonton),38s East Edmonton 138 kV Bus 3 | 2017-04-24 08:01 | 2017-05-01 17:00 | N | Y | replace T4, replace 38s1, replace insulators on 138kV bus 3 east portion | Transformer, Line, Bus |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 268s T1 (268s Whitecourt),503L (268s Whitecourt - 323s Whitecourt Power),526L (268s Whitecourt - 526DL185),268s Whitcourt 69 kV bus | 2017-04-24 09:00 | 2017-04-28 13:00 | N | N | replace 69B, A87/T1 and B87/T1 protections. rewire T1 and VR1 to new control building, coordinated with 323s shutdown | Transformer, Line, Bus |  | replace 69B, A87/T1 and B87/T1 protections. rewire T1 and VR1 to new control building, coordinated with 323s shutdown. Redundant protections associated with this equipment will be taken out of service one at a time. | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s 5552 (535s Joffre) | 2017-04-24 11:00 | 2017-04-24 16:30 | N | N | replace tank heater and replace sensor in hydran for T1 | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 719L (575s Sundre - 378s Shell Caroline),575s 719N (575s Sundre) | 2017-04-24 11:30 | 2017-04-28 17:00 | N | N | replace 575s719N breaker CT's and line protections A and B | Circuit Breaker, Line |  |  | Creates Radial Feeds
ALTALINK | 880L (523s Bullshead - 41s Medicine Hat),523s 880 (523s Bullshead) | 2017-04-24 12:00 | 2017-04-24 17:30 | N | Y | wire & test trip relay for future station expansion project | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P1C | 2017-04-25 06:00 | 2017-04-25 07:00 | N | N | remove portion of 138kV bus between 805B and 803A, CH805 nbr and CT test | Line |  |  | Limits ATC
ALTALINK | 214s T1 (214s Innisfail) | 2017-04-25 07:00 | 2017-04-26 09:00 | N | N | RATD 214s SS1 and 25kV Bus 1 - reference number change from 253592 create open point between 25kV bus and 214s37, close open between 25kv bus and new 214s61 | Transformer |  |  | For Information Only
ALTALINK | 266s 1037L FSC (266s SC1) | 2017-04-25 08:00 | 2017-04-28 16:00 | N | Y | repair gas leak | Shunts |  |  | Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2017-04-25 08:00 | 2017-05-31 12:00 | N | Y | sync condenser turnaround, unavailable for dispatch | Shunts |  | Sync Condenser turnaround, unavailable for dispatch | For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2017-04-25 12:30 | 2017-04-25 17:30 | N | N | Switch maintenance - 268s212 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 352s Onoway RTU/SCADA,191s N.W.Cardiff RTU/SCADA | 2017-04-26 07:00 | 2017-04-26 17:00 | N | N | investigate & resolve minor alarm on single channel MDS radio | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 77s 452 (77s Sagitawah) | 2017-04-26 07:30 | 2017-04-26 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2017-04-26 08:30 | 2017-04-26 17:30 | N | N | urgent structure repair (112, 113) | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 214S Innisfail | 2017-04-26 09:15 | 2017-04-27 16:00 | N | Y | 25kV Bus 2: create open point between 25kV bus and 214s16, close open point between 25kV bus and new 214s58 | Station |  |  | Restricts Generation
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt) | 2017-04-26 10:00 | 2017-04-26 12:00 | N | N | trip testing from new 69 kV protections | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2017-04-26 11:00 | 2017-04-26 15:00 | N | Y | maintenance | Switch |  |  | Pre-Condition, Restricts Generation
ALTALINK | 268s 199N (268s Whitecourt),199L (268s Whitecourt - 199L187B) | 2017-04-26 12:00 | 2017-04-26 14:00 | N | N | trip testing from new 69 kV protections | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2017-04-26 12:01 | 2017-04-28 19:00 | N | Y | WATL warranty work and maintenance | Line |  |  | 500 kV
ALTALINK | 523s C1 (523s Bullshead),523s 33 (523s Bullshead) | 2017-04-27 07:00 | 2017-04-27 12:30 | N | N | wire & test trip relay for future station expansion project | Circuit Breaker, Shunts |  |  | Pre-Condition
Syncrude | ML2 (Syncrude Mildred Lake - UE_1 Syncrude Plant 30-2) | 2017-04-27 07:00 | 2017-04-27 18:00 | N | N | insulator cleaning and inspection | Line |  |  | Creates Radial Feeds
Medicine Hat | MH69s2 MH69_212 (MH69s2 North Industrial),MH69s2 MH69_215 (MH69s2 North Industrial),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights),MH69s2 MH69-T22 (North Industrial Substation),MH69S-2 East Bus (MH69S- 2 North Industrial) | 2017-04-27 07:00 | 2017-04-27 16:00 | N | N | connection of new 69 kV disconnect switch | Transformer, Line, Bus, Circuit Breaker |  | On Tuesday April 25, 2017 the City of Medicine Hat Electric Distribution will be taking an outage on the East 69kV Bus at MH-2S North Industrial substations. The equipment included as part of the outage will be: Transformer T-22 Disconnect Switch  MH69-210, 214, 213, & 211 Circuit Breakers  MH69-212 & 215 Scope of work; Connection of new 69 kV Disconnect Switch. Outage Start time will be 07:00 Outage End time will be 16:00 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 989L (310p Sundance - 77s Sagitawah),77s 29 (77s Sagitawah),77s 26 (77s Sagitawah),77s989X (77s Sagitawah) | 2017-04-27 07:30 | 2017-04-27 15:30 | N | Y | switch maintenance - 77s989X | Line, Switch, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12),ENMAX 10 B138-832 (ENMAX 10) | 2017-04-27 08:00 | 2017-04-27 16:00 | N | Y | SF6 Gas Sample 10B138-832, Doble 12B138-832 | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2017-04-27 09:00 | 2017-04-27 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s T1 (42s Sarcee),916L (42s Sarcee - 5s East Calgary),928L (17s Benalto - 42s Sarcee),42s 70 (42s Sarcee),42s Sarcee 240kV North Bus | 2017-04-28 07:00 | 2017-04-28 17:00 | N | Y | Installing pollution monitors | Transformer, Bus, Line, Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
BCH | 5L71 (Mica Creek - Nicola) | 2017-04-28 09:00 | 2017-04-28 17:00 | N | Y | Replacement of insulators, arcing horns & Spacers | Line |  |  | Limits ATC, 500 kV
ATCO | 800s 702T (800s Friedenstal) | 2017-04-29 07:00 | 2017-04-29 17:00 | N | N | attach temp 72 kv u/g bypass cables | Transformer |  | Attach temp 72 kv u/g bypass cables, all load transferred to 701T.
ENMAX | 13.2TR (ENMAX 13),13.4TR (ENMAX 13),11.81L (ENMAX 13 - ENMAX 11),13.60L (ENMAX 27 - ENMAX 13),13.82L (ENMAX 22 - ENMAX 13) | 2017-04-29 08:00 | 2017-04-30 16:00 | N | N | maintenance | Line, Transformer |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK, EPCOR | 1059AL (52s East Industrial - 1059L tap),1059L (38s East Edmonton - 1059AL tap),1059L (38s East Edmonton - 803s Lambton) | 2017-04-29 16:45 | 2017-04-29 17:00 | N | Y | EPCOR requires 1059L de-energized to facilitate closing E52sEDS1 | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO, CENOVUS | 1200S Foster Creek Station,7L86 (822s Wolf Lake - 877s Foster Creek) | 2017-04-30 08:00 | 2017-04-30 12:00 | N | Y | inspection and testing | Line, Station |  |  | Restricts Generation, For Information Only
ALTALINK | 675L (244s Bowmanton - 41s Medicine Hat),895s 892 (895s Suffield),892L (895s Suffield - 244s Bowmanton),41s 675 (41s Medicine Hat) | 2017-05-01 06:30 | 2017-05-05 19:30 | N | Y | replace 892s saddles & relocation of 675L to future 321s Al Rothbauer | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1045L (310p Sundance - 805s Jasper) | 2017-05-01 07:00 | 2017-05-04 08:30 | N | Y | breaker op-checks as part of relay maintenance and cutover over new line metering | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
EPCOR | 72CH9 (Hardisty - 987s Clover Bar),987s CH722 (987s Clover Bar) | 2017-05-01 07:00 | 2017-05-30 17:00 | N | N | breaker replacement | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T3 (987s Clover Bar) | 2017-05-01 07:00 | 2017-05-01 17:00 | N | Y | breaker op-checks as part of relay maintenance | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
CMH | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2017-05-01 08:00 | 2017-06-02 15:00 | N | N | structure upgrades | Line |  |  | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),ENMAX 16 B69-16.60 (ENMAX 16) | 2017-05-01 08:00 | 2017-05-01 16:00 | N | N | HV breaker inspection | Line, Circuit Breaker
ENMAX | 1.5TR (ENMAX 1) | 2017-05-01 08:00 | 2017-05-05 16:00 | N | N | doble and maintenance and replace O-rings on potheads | Transformer |  |  | For Information Only
BCH | 5L71 (Mica Creek - Nicola) | 2017-05-01 09:00 | 2017-05-12 17:00 | N | Y | replacement of insulators, arcing horns & spacers | Line |  |  | Limits ATC, 500 kV
BCH | 5L92 (Cranbrook - Selkirk) | 2017-05-01 09:00 | 2017-05-02 18:00 | Y | Y | CBK 5CVT4 replacement - - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC, 500 kV
ATCO | 6L97 (735s Swan River - 739s Edith Lake),739s 603 (739s Edith Lake),735s 603 (735s Swan River) | 2017-05-01 10:00 | 2017-05-01 16:00 | N | N | 735s breaker oil testing and 739s breaker maintenance | Circuit Breaker, Line |  | BREAKER MIN OIL HLC PARTIAL TESTING, 603 @ 735S Ensure 72KV System is stable. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 434s T3 (434s East Stony Plain) | 2017-05-01 10:30 | 2017-05-02 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 600L (523s Bullshead - 404s Peace Butte),523s 600 (523s Bullshead) | 2017-05-01 12:00 | 2017-05-01 17:30 | N | N | wire & test trip relay for future station expansion project | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, For Information Only
ATCO | 800s 701T (800s Friedenstal),800s 601 (800s Friedenstal) | 2017-05-01 12:00 | 2017-06-06 17:00 | N | N | replace 601, 601TD and 600PT's | Circuit Breaker, Transformer |  | Replace 601, 601TD and 600PT's, load to remain on 702T May 1-12. May 12-Jun 1 - GOI will be shrunk down to 72KV bus (Isolation points - 601TD, 602TD2, J1), 25 KV load will be transferred back from 702T to 701T (See SLD notes). | For Information Only
ALTALINK | 38s T2 (38s East Edmonton),822L (133s Stelco Edmonton - 38s East Edmonton),38s East Edmonton 138 kV Partial Bus 3 | 2017-05-01 17:01 | 2017-05-08 17:00 | N | N | replace insulators on 138kV bus 3 and associated lines | Bus, Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 738L (38s East Edmonton - 95s Imperial Oil Edmonton),780L (38s East Edmonton - 149s Nisku) | 2017-05-01 17:01 | 2017-05-03 17:00 | N | N | replace insulators on 138kV bus 3 and associated lines | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-85 | 2017-05-02 06:00 | 2017-05-16 18:00 | N | N | maintenance | Station |  | Turnaround activities, taking opportunity to do maintenance activities on switches (29PS-426, 29PS-420, 29PS-428, 29PS-427, 29PS-425, 29PS-320, 29PS-322, 29PS-421, 29PS-422, 29PS-423, 29PS-424, 29PS-319) and breakers (752-10040, 752-10020, 752-10030, 752-10010). Each element will be isolated during maintenance activities, no change to power flow. | For Information Only
EPCOR | 987s T2 (987s Clover Bar),987s T4 (987s Clover Bar),987s C2405 (987s Clover Bar),987s C2406 (987s Clover Bar) | 2017-05-02 07:00 | 2017-05-02 17:00 | N | Y | performing breaker op-checks as part of relay maintenance | Circuit Breaker, Transformer |  |  | 240 kV
ALTALINK | 379s T1 (379s Shell Canada Waterton),185L (396s Pincher Creek - 379s Shell Canada Waterton),379s 185N (379s Shell Waterton),379s 352 (379s Shell Waterton),379S Shell Canada Waterton 69 kV Bus | 2017-05-02 07:00 | 2017-05-11 18:00 | N | Y | partial bus outage - replace bus #1 protection, replace breaker 185N and 379s325, and replace transformer T1 "A" protection | Circuit Breaker, Transformer, Line, Bus |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 515S Fedpipe Judy Creek,526L (515s Fed Pipe Judy Creek - 526L420) | 2017-05-02 07:00 | 2017-05-02 16:00 | N | N | remove 515s12 & 515s13 and install new 515s17 PT on the line side of 515s11 | Station, Line |  |  | Firm Load Loss, For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),34B69-16.60 (ENMAX 34) | 2017-05-02 08:00 | 2017-05-03 16:00 | N | N | HV breaker inspection | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 454s 2134 (454s Bucklake) | 2017-05-02 08:30 | 2017-05-02 16:00 | N | N | replace revenue meter | Circuit Breaker |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2017-05-02 08:30 | 2017-05-03 16:33 | N | N | urgent repair on structure 437, saddle on top right phase is not properly hooked to the insulators | Line |  | 174L (395s  197s) - GOI Job Scope: Urgent repair on structure 437, saddle on top right phase is not properly hooked to the insulators. Scheduled By: Scott Robinson Isolation Points: 197s3, 395s175 Outage start: May 2, 0830 Outage end: May 2, 1130 | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 502s T1 (502s Shell Waterton (#2)),502s T2 (502s),502s T3 (502s Shell Waterton (#2)),591L (379s Shell Canada Waterton - 502s Shell Waterton (#2)),379S Shell Canada Waterton 69 kV Bus | 2017-05-02 09:00 | 2017-05-08 17:30 | N | N | 379s 69 kV partial bus outage | Bus, Line, Transformer |  |  | Firm Load Loss
ALTALINK | 753L (65s High River - 253s Blackie),253s 753W (253s Blackie) | 2017-05-02 09:00 | 2017-05-02 16:00 | N | N | adjust 65s40 138kV switch and remove birds nests from closing dashpots on all 3 poles | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ATCO | 853s 702T (853s Ring Creek) | 2017-05-02 11:00 | 2017-05-19 13:00 | N | N | 702T oil reclaiming, major testing; 502VR major testing | Transformer |  | 853S 702T TRANSFORMER CLASS2 MAJOR TESTING 702T Oil reclaiming, 702T major testing; 502VR major testing Load will be carried by 701T and 501VR ON MAY 10 2017 (08:30 to 17:00) EXPAND THE 702T GOI TO INCLUDE 700D1; 7L113D2; 700PT2X1; 700PT2X2; 700PT2Y 7L113 open ended, all load still on 701T at the end of the day on May 10 the GOI will shrink back down to the original points | For Information Only
Saskpower | Sask Power SW903T | 2017-05-02 14:00 | 2017-05-12 14:45 | N | N | 100 - WT - SW903T - SW903T maintenance, protection upgrades, SW806 BKR (TOG-2017- 21) | Circuit Breaker |  |  | Limits ATC
ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader),879S 702T,879s 502R (879s Scotford Upgrader) | 2017-05-03 07:00 | 2017-05-12 17:30 | N | N | install disconnect switch for fault current limiter | Terminal Equipment, Line, Shunts |  | Install disconnect switch for FCL (Fault Current Limiter), ALC-02L will be open ended @ 879s 5-10 min May 3 and again May 12 for 702T switching in/out of service | Creates Radial Feeds
ALTALINK, ENMAX | 916L (42s Sarcee - 5s East Calgary),693L (42s Sarcee - ENMAX 10) | 2017-05-03 07:15 | 2017-05-11 18:45 | N | Y | SWCRR: foundation work for future U/G riser structures | Line |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 42s 31 (42s Sarcee) | 2017-05-03 07:30 | 2017-10-01 13:30 | N | N | SWCRR - install new foundations for future 693L | Circuit Breaker |  |  | For Information Only
ALTALINK | 394s T1 (394s Empress) | 2017-05-03 07:30 | 2017-05-03 17:00 | N | N | connect temp cables between 394sT1 & 394s18 | Transformer |  |  | For Information Only
ALTALINK | 445s T2 (445s Elk River) | 2017-05-03 08:30 | 2017-05-03 12:45 | N | N | TX hot spot maintenance | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 28s 60 (28s West Brooks) | 2017-05-03 08:30 | 2017-05-03 17:00 | N | N | maintain 138kV HPL ABB minumum oil breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2017-05-03 10:00 | 2017-05-03 11:00 | N | N | fix a hot spot on a control cable identified via infrared assessment | Line |  |  | 500 kV
ATCO | 881s 701T (881s Sturgeon),7L01 (813s Little Smoky - 881s Sturgeon) | 2017-05-03 11:00 | 2017-05-04 13:00 | N | Y | bus maintenance | Transformer, Line |  | ATCO POWER is doing 13.8KV bus maint @ VVIEW PLANT, 7L01 must be momentarily taken OOS to open 701TD, then re-energized. On RTN May 5 7L01 will again be momentarily opened to close 701TD @ 881s and open 702TD (see GOI 2-41853) | Restricts Generation, For Information Only
ALTALINK | 445s T1 (445s Elk River) | 2017-05-03 12:45 | 2017-05-03 17:30 | N | N | TX hot spot maintenance | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | UE-1 30-2PTR72-3 (UE-1) | 2017-05-04 06:00 | 2017-05-17 19:00 | N | N | 5 year maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 394s T1 (394s Empress),394s T2 (394s Empress) | 2017-05-04 07:15 | 2017-05-08 17:15 | N | N | replace U/G cables between T2 & VR1, replace 394s32 with MOS | Transformer |  |  | For Information Only
ATCO, ALTALINK | 7L230 (69s North Barrhead - 7L230 tap),69s 230W (69s North Barrhead) | 2017-05-04 07:30 | 2017-05-04 16:30 | N | Y | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Overload
ENMAX | 8.4TR (ENMAX 8) | 2017-05-04 08:00 | 2017-05-05 16:00 | N | N | fix LTC tank valve - fabricated part required | Transformer |  |  | For Information Only
ALTALINK | 28s 12 (28s West Brooks) | 2017-05-04 08:00 | 2017-05-04 14:00 | N | Y | check % of SF6 gas in breaker and adjust as required | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | Enmax 5 B138-5BT7 (Enmax 5) | 2017-05-04 08:00 | 2017-05-04 16:00 | N | N | SF6 Gas Sample, Doble 5B138-5BT7, Doble 138kV East & West CTs | Circuit Breaker |  |  | For Information Only
ENMAX | 65.1 TR (ENMAX 65),ENMAX 65 138 kV South Bus | 2017-05-04 08:00 | 2017-05-05 16:00 | N | Y | bus outage required to string 54.81L from structure #1 to dead end structure at 65sub | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 310p 1252 (310p Sundance) | 2017-05-04 08:30 | 2017-05-04 14:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 881s 702T (881s Sturgeon),7L01 (813s Little Smoky - 881s Sturgeon) | 2017-05-04 13:00 | 2017-05-06 15:00 | N | Y | bus maintenance | Transformer, Line |  | ATCO POWER is doing 13.8KV bus maint @ VVIEW PLANT, 702TD will be opened on GOI 2-41852 RTN switching. On RTN May 6 7L01 will be momentarily opened to close 702TD @ 881s | Restricts Generation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2017-05-04 22:00 | 2017-05-05 03:00 | N | N | remove support pole installed during water main break | Line |  |  | Creates Radial Feeds
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2017-05-05 07:00 | 2017-05-07 17:00 | N | N | LRT project upgrades | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 651S Kirby,457L (651s Kirby - 167s Ipiatik Lake) | 2017-05-05 07:00 | 2017-05-05 19:00 | N | N | replace leaking 138 kV CVT, maintenance | Station, Line
EPCOR | 72RV6 (Rossdale - 511s Victoria),Rossdale RV722 (Rossdale) | 2017-05-07 07:00 | 2017-05-07 09:00 | N | N | relay operation checks | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss
EPCOR | 72RV4 (Rossdale - 511s Victoria),Rossdale RV726 (Rossdale) | 2017-05-07 09:15 | 2017-05-07 11:15 | N | N | relay operation checks | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
EPCOR | Rossdale VHBB1 (Rossdale) | 2017-05-07 12:30 | 2017-05-07 14:30 | N | N | relay operation checks | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 42s T2 (42s Sarcee),42s 60 (42s Sarcee) | 2017-05-07 13:30 | 2017-05-11 18:00 | N | Y | doble test and maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | Rossdale VHBB2 (Rossdale) | 2017-05-07 14:30 | 2017-05-07 16:30 | N | N | relay operation checks | Circuit Breaker |  |  | Pre-Condition
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2017-05-08 06:00 | 2017-05-21 21:00 | N | Y | Tie-Ins for various infrastructure system | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 908L (89s Ellerslie - 38s East Edmonton) | 2017-05-08 07:00 | 2017-05-08 07:15 | N | Y | EPCOR requires 908L de-energized to facilitate opening E52sEDS2 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 950S Germain,939s 901T (939s Livock),7L125 (950s Germain - 939s Livock) | 2017-05-08 07:00 | 2017-05-12 17:00 | N | Y | erect station service structures for new 500 KV Thickwood substation station service | Station, Transformer, Line |  | Erect station service structures for new 500 KV Thickwood substation station service, 901T OOS for 2 hrs May 8 to create jumper J1 (7L125, 950s OOS, 2-33724A), then reduce GOI to 25kV bus May 8-12 (500SST1X, J1, 500PT1 secondaries) issue 2-33724B and then place 901T back in service, 901T OOS for 2 hrs May 12 to close jumper J1 (7L125, 950s OOS, 2-33724C) 240kV bus will be open briefly four times while switching 901T in/out of service, 939s station service fed from Alternate Standby generator | 240 kV
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2017-05-08 07:00 | 2017-05-12 17:00 | N | Y | CT replacements | Line |  |  | 240 kV, For Information Only
EPCOR | 52s T2 (52s East Industrial) | 2017-05-08 07:00 | 2017-05-12 17:00 | N | Y | doble | Transformer |  |  | 240 kV, For Information Only
EPCOR | 1098L (EP 805s Jasper - Poundmaker) | 2017-05-08 07:00 | 2017-05-12 17:00 | N | Y | cutover over new line metering | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds,Affects Cranking Path
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar),987s C2403 (987s Clover Bar),987s C2405 (987s Clover Bar) | 2017-05-08 07:00 | 2017-05-08 14:00 | N | Y | performing breaker op-checks as part of relay maintenance | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | CV5 (557s Castle Downs - 511s Victoria) | 2017-05-08 07:00 | 2017-05-14 17:00 | N | Y | inspection and repair | Line |  |  | 240 kV, For Information Only
ENMAX | 3.4TR (ENMAX 3) | 2017-05-08 08:00 | 2017-05-19 16:00 | N | N | TR bushing/CT replacement - TR differential relay replacement | Transformer |  | TR Bushing/CT replacement. TR DIFF Relay Replacement | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2017-05-08 08:00 | 2017-05-12 16:00 | N | N | doble TR, change O rings in potheads | Transformer |  | Doble TR. Change O rings in potheads. Measurements for Ladder - Inform Paul K | For Information Only
ENMAX | 12.1TR (ENMAX 12) | 2017-05-08 08:00 | 2017-05-09 16:00 | N | N | LTC maintenance and check reversing SW | Transformer |  |  | For Information Only
ALTALINK | 676L (523s Bullshead - 244s Bowmanton),523s Bullshead 138 kV Bus 2 | 2017-05-08 09:30 | 2017-05-17 13:00 | N | Y | re-terminate 676L to new breaker bay, rename existing 523s676 breaker, connect/energize new 138kV Bus 2, T2 & new Fortis 122L | Bus, Line |  |  | Creates Radial Feeds
ATCO | 730s 702 (730s Rycroft) | 2017-05-08 10:00 | 2017-05-10 13:00 | N | N | 702 breaker fail testing | Circuit Breaker |  | 702 Breaker fail testing, 7L10 fed from 7L68. | For Information Only
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan),54s 707N (54s Fort Saskatchewan) | 2017-05-08 10:30 | 2017-05-08 17:30 | N | Y | replace damaged conductor on 707L attached to 54s19 | Line, Circuit Breaker |  |  | Overload, Restricts Generation
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek) | 2017-05-08 11:00 | 2017-05-11 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 394s T1 (394s Empress) | 2017-05-08 13:00 | 2017-07-13 17:00 | N | N | isolate T1 in prep for addition of new 25kV bus | Transformer |  |  | For Information Only
ALTALINK | 793s T3 (T793s Horse Creek) | 2017-05-09 06:00 | 2017-05-11 17:30 | N | N | required for substation maintenance work & SCADA upgrade | Transformer |  |  | For Information Only
ALTALINK | 285s T1 (285s East Camrose) | 2017-05-09 07:00 | 2017-05-18 17:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
ALTALINK | 715L (648s Metiskow - 650s Hansman Lake),715L (545s Provost - 650s Hansman Lake) | 2017-05-09 07:30 | 2017-05-09 16:30 | N | N | component replacement | Line |  |  | For Information Only
ALTALINK | 122S Alberta Newsprint,907L (77s Sagitawah - 122s Alberta Newsprint) | 2017-05-09 07:30 | 2017-05-09 20:30 | N | Y | replacing CVT & junction box | Station, Line |  |  | 240 kV, Restricts Generation
ALTALINK | 394s T1 (394s Empress) | 2017-05-09 07:30 | 2017-05-09 13:00 | N | N | remove temp cables between 394sT1 & 394s18 | Transformer |  | Remove temp cables between 394sT1 & 394s18 | For Information Only
ALTALINK | 33S Spray,113L (20s Ghost - 33s Spray),76L (115s Mt. Allan - 33s Spray),84L (35s Rundle - 33s Spray) | 2017-05-09 08:00 | 2017-05-10 14:00 | N | Y | 33s1 breaker maintenance and 33s5 adjustment | Station, Line |  | 138 kV bus outage for 33s1 breaker maintenance and 33s5 adjustment that is not closing properly | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2017-05-09 08:00 | 2017-05-09 16:00 | N | N | SW66@27s maintenance | Line, Transformer |  | SW66@27s Maint. Contact Jeremy Bridge prior to switching he holds current GOI on 13.60L, his crews will temporarily step away from 13.60L while GOI is being altered. Once SW66@27Sub has been maintained return GOI to original points SW66@27s & SW68@13s. | For Information Only
TRANSALTA | 239S Castle River | 2017-05-09 08:00 | 2017-05-26 17:00 | N | N | install new settings in relays | Station |  |  | Restricts Generation
ENMAX | ENMAX 65 B138-D84 (ENMAX 65),ENMAX 65 B138-D83 (ENMAX 65) | 2017-05-09 08:00 | 2017-05-18 16:00 | N | N | (FATDSC)-bus outage required to complete MD-bus riser and commission new 54.81L | Circuit Breaker |  | (FATDSC)-Bus outage required to complete MD-bus riser and commission new 54.81L. 54.81L in-service on return, phasing required across SW91. | For Information Only
ALTALINK | 604L (149s Nisku - 155s Blackmud),155s 604 (155s Blackmud) | 2017-05-09 08:30 | 2017-05-09 17:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 13s 1452 (13s Deerland) | 2017-05-09 08:30 | 2017-05-10 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L33 (7L33D3 - 749s Flyinshot Lake),749s 703 (749s Flyingshot Lake),749s 704 (749s Flyingshot Lake) | 2017-05-09 09:30 | 2017-05-10 14:05 | N | Y | sync bypass demo/remove sync circuit bypass switches | Line, Circuit Breaker |  | 749S 7L33 Sync Bypass Demo / Maint Sw Removal Remove Sync Circuit bypass switches and Maintenance Switch CG&E to be fed radially from 845S | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | DT | 2017-05-09 09:30 | 2017-05-09 11:30 | N | N | DT Q2 Release - PROD Deployment | SCInternal |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2017-05-09 12:00 | 2017-05-09 16:00 | N | N | performing relay op-checks for relay maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | DT | 2017-05-09 14:00 | 2017-05-09 15:00 | N | N | DT Migration to Primary Data Center post DT Q2 release | SCInternal |  |  | For Information Only
ENMAX | 41.2TR (ENMAX 41) | 2017-05-09 16:00 | 2017-06-07 08:00 | N | N | (FATDSC) west bus modifications | Transformer |  |  | Pre-Condition
ATCO | 7L85 (804s Wintering Hills - 803s Bullpound) | 2017-05-10 07:00 | 2017-05-11 17:00 | N | N | climbing inspection | Line |  | will need a GOI on 7L85-May 10,11th,2017 - climbing inspection WO# E08814-85300 7;00am to 17:00pm from 804S to 803S | Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s C1 (305s Acheson),305s T1 (305s Acheson),739L (14s Devon - 305s Acheson),305s Acheson 138 kV East Bus | 2017-05-10 07:15 | 2017-05-18 17:45 | N | N | bus reconfig, connect C1 to new bay, install new bus PT, connect new 305s739 breaker, install foundation for new 739L structure (SWEATD) | Bus, Line, Shunts, Transformer |  |  | Pre-Condition, Over/Under Voltage
ENMAX | 12.2TR (ENMAX 12) | 2017-05-10 08:00 | 2017-05-12 16:00 | N | N | LTC maintenance and check reversing SW | Transformer |  |  | For Information Only
ENMAX | 26.81L (ENMAX 54 - ENMAX 26),32.82L (ENMAX 54 - ENMAX 32),41.84L (ENMAX 54 - ENMAX 41),54.81L (ENMAX 54 - ENMAX 65),26.81L (ENMAX 32 - ENMAX 26) | 2017-05-10 08:00 | 2017-05-18 16:00 | N | N | In-service-date: May 16, 2017,In-service-date: May 18, 2017,out-service-date: May 15, 2017 | Line
ATCO | 853s 702T (853s Ring Creek),7L113 (853s Ring Creek - 930s Arcenciel) | 2017-05-10 08:30 | 2017-05-10 17:00 | N | Y | perform maintenance on 702TCS | Line, Transformer |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746L tap),700L (746s Sherwood Park - 700L TAP),746L (700L TAP - 746DL19 TAP) | 2017-05-10 12:30 | 2017-05-10 16:30 | N | N | emergency outage to remove kite from line | Line |  |  | Overload, Creates Radial Feeds
ALTALINK | 602s C1 (602s Cold Creek),602s 852 (602s Cold Creek) | 2017-05-10 12:30 | 2017-05-10 17:30 | N | N | work on sequence controller for 602s852 | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | Rossdale R72C1 (Rossdale) | 2017-05-11 07:00 | 2017-05-11 12:00 | N | N | performing relay op-checks for relay maintenance | Circuit Breaker |  |  | For Information Only
EPCOR | 987s GDS1 (987s Cloverbar) | 2017-05-11 07:00 | 2017-05-15 17:00 | N | N | maintenance | Switch |  |  | For Information Only
ALTALINK | 13s 452 (13s Deerland) | 2017-05-11 08:30 | 2017-05-11 17:30 | N | N | Breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2017-05-11 09:00 | 2017-05-11 14:30 | N | Y | high Load move | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale C2,Rossdale R72C2 (Rossdale) | 2017-05-11 12:00 | 2017-05-11 16:00 | N | N | performing relay op-checks for relay maintenance | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | 987s CGB1 (987s Clover Bar) | 2017-05-12 07:00 | 2017-05-12 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Restricts Generation
EPCOR | Rossdale RR723 (Rossdale) | 2017-05-12 07:00 | 2017-05-12 12:00 | N | N | performing relay op-checks for relay maintenance | Circuit Breaker
ALTALINK, EPCOR | 908AL (52S East Industrial - 908L Tap),908L (89s Ellerslie - 38s East Edmonton) | 2017-05-12 07:00 | 2017-05-12 17:00 | N | Y | doble | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RG7 (Rossdale - Garneau),Rossdale RG725 (Rossdale) | 2017-05-14 04:00 | 2017-05-14 08:00 | N | N | operation checks for relay maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 395S North Holden,395s T1 (395s North Holden) | 2017-05-14 07:15 | 2017-05-14 15:45 | N | N | 25kV bus repair, T1 doble and repair, 395s25 hotspot, 395s12 adjust | Transformer, Station |  |  | Pre-Condition, For Information Only
ALTALINK, ATCO | 7L77 (395s North Holden - 709s Vegreville),395s 77E (395s North Holden) | 2017-05-14 07:30 | 2017-05-14 15:30 | N | N | add a second 94 relay to T1 and complete trip testing for 395s77E | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 1107L (ENMAX 65 - 237s Foothills) | 2017-05-14 07:30 | 2017-05-17 18:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 648s 749E (648s Metiskow) | 2017-05-14 09:30 | 2017-05-26 17:30 | N | N | replacing 'A' & 'B' protection on 749L | Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 379s T2 (379s Shell Canada Waterton),185L (415s Drywood - 379s Shell Canada Waterton),379s 452 (379s Shell Waterton) | 2017-05-15 07:00 | 2017-05-24 14:00 | N | Y | replace bus #2 protection, breakers 185E & 452, transformer T2 protection, and PTs 396s11 & 13 | Line, Transformer, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2017-05-15 07:00 | 2017-05-16 16:00 | N | N | HV breaker inspection (HPL), doble breaker and CT | Line |  |  | Overload, Contingency Requires Mitigation
Saskpower | Sask Power SW901T | 2017-05-15 07:00 | 2017-06-09 18:00 | N | N | 403s-WT-SW901T maintenance, protection upgrades, install SW901C Isol, SW806 BKR (TOG# T2017-24) | Circuit Breaker |  |  | Limits ATC
EPCOR | Poundmaker T3 (Poundmaker) | 2017-05-15 07:00 | 2017-05-19 17:00 | N | Y | doble | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2017-05-15 07:30 | 2017-05-16 18:30 | N | N | damper replacements | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 38s T3 (38s East Edmonton) | 2017-05-15 08:00 | 2017-05-18 17:00 | N | N | bushing replacement | Transformer |  |  | For Information Only
ENMAX | 54.1TR (ENMAX 54) | 2017-05-15 08:00 | 2017-05-15 16:00 | N | N | Oil sample MT and LTC | Transformer |  | Oil sample MT and LTC. Run through neutral. 54sub will already be tied away for FATD | For Information Only
ENMAX | 39.1TR (ENMAX 39) | 2017-05-15 08:00 | 2017-05-16 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 12.2TR (ENMAX 12) | 2017-05-15 08:00 | 2017-05-19 16:00 | N | N | doble TR | Transformer |  |  | For Information Only
ATCO | 7L22 (811s Clairmont Lake - 7L22D2),811s 708 (811s Clairmont Lake) | 2017-05-15 10:00 | 2017-05-16 17:00 | N | N | 811S 708 breaker complete main and commissioning | Line, Circuit Breaker |  | 811S 708 BREAKER MIN OIL HLR COMPLETE TESTING Breaker complete main and commissioning 7L22 open ended | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 89s Ellerslie) | 2017-05-15 11:00 | 2017-05-18 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 924L (102s Langdon - 356s Milo) | 2017-05-15 11:00 | 2017-05-18 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 708L (71s Lamoureux - 708L88X) | 2017-05-15 12:30 | 2017-05-19 17:30 | N | N | component replacement | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 803s Bullpound | 2017-05-15 13:00 | 2017-05-15 16:00 | N | N | 803s station service | Station |  | 803S 500PT1D | For Information Only
ALTALINK | 433L (291s Cochrane - T793s Horse Creek),793s 433 (793s Horse Creek) | 2017-05-16 06:00 | 2017-05-18 17:30 | N | N | station SCADA upgrade and substation maintenance work | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 172L (83s Taber - 172L944A) | 2017-05-16 07:15 | 2017-05-19 08:44 | N | N | line maintenance | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s T1 (5s East Calgary) | 2017-05-16 07:30 | 2017-05-20 16:00 | N | N | oil leak | Transformer |  |  | 240 kV, Pre-Condition, Overload, For Information Only
ENMAX | 2.2TR (ENMAX 2) | 2017-05-16 08:00 | 2017-08-05 16:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2017-05-16 08:00 | 2017-05-16 17:00 | N | N | Conductor repairs | Line |  | Conductor repairs | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 364s T1 (364s Whitecourt Industrial),797L (364s Whitecourt industrial - 268s Whitecourt),364s Whitecourt Industrial 138 kV Bus 1 | 2017-05-16 08:30 | 2017-05-16 17:00 | N | N | switch maintenance - 364s5, 364s16 | Line, Bus, Transformer |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 2029s 1200SST2 (2029s Heathfield) | 2017-05-16 09:00 | 2017-05-19 17:30 | N | Y | clean and replace grounding saddles and bus connectors in area | Transformer |  | SST2 Outage @ 2029s Heathfield, increase of corona discharge in area. clean and replace grounding saddles and bus connectors in area. if time allows, transformer and regulator inspections and maintenance, Plant station service will be transferred to redundant/alternate supply | For Information Only, 500 kV
ALTALINK | 364s T1 (364s Whitecourt Industrial) | 2017-05-16 17:00 | 2017-05-17 17:30 | N | N | switch maintenance - 364s7 and install wildlife cover | Transformer |  |  | For Information Only
ALTALINK | 677L (305s Acheson  595s Spruce Grove),305s 26 (305s Acheson) | 2017-05-17 06:50 | 2017-05-17 08:00 | N | N | trip tests to breaker 305s677 from new 130B1 and 1052 protections | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39) | 2017-05-17 08:00 | 2017-05-18 16:00 | N | N | LTC Maintenance | Transformer |  |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),15B69-15.62 (ENMAX 15) | 2017-05-17 08:00 | 2017-05-18 16:00 | N | N | HV Breaker Inspection | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 739L (305s Acheson - 434s Stony Plain),305s 1 (305s Acheson) | 2017-05-17 08:01 | 2017-05-17 09:15 | N | N | trip tests to breaker 305s739W from new 130B1 and 1052 protections. | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 931s 702T (931s Bohn) | 2017-05-17 09:00 | 2017-05-18 16:00 | N | N | 931S replace 300SST2 B phase TX | Terminal Equipment |  | 931S REPLACE 300SST2 B PHASE TX | For Information Only
ALTALINK | 769L (377s Hardisty - 296s Rosyth) | 2017-05-17 09:00 | 2017-05-18 15:00 | N | N | remove and replace existing A-frame at 296s and place new breaker | Line |  |  | For Information Only
ALTALINK | 1037L (237s Foothills - 138 Windy Flats) | 2017-05-18 07:00 | 2017-05-20 18:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition
EPCOR | 524S Fiberglas | 2017-05-18 07:00 | 2017-05-18 17:00 | N | N | customer outage | Station |  |  | Firm Load Loss, For Information Only
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake),157s 794X (157s Lac La Biche) | 2017-05-18 07:30 | 2017-05-18 18:30 | N | N | install new piles for TX addition project | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 305s 739 (305s Acheson) | 2017-05-18 17:01 | 2017-06-26 08:00 | N | N | keep new 305s739 breaker under outage until 739L ready to be swung over from 305s739X breaker | Circuit Breaker |  |  | For Information Only
EPCOR | Poundmaker T3 (Poundmaker),Poundmaker PMDS7 (Poundmaker),Poundmaker PMDS2 (Poundmaker) | 2017-05-19 07:00 | 2017-05-19 17:00 | N | Y | doble | Transformer, Switch |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 33 B138-33.83 (ENMAX 33) | 2017-05-19 08:00 | 2017-05-19 16:00 | N | N | spring substation washing, SF6 gas sample, doble 33B138-33.83, wash potheads | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 185AL (415s Drywood - 995s Yarrow) | 2017-05-19 08:30 | 2017-05-19 17:30 | N | N | replace cracked insulators | Line |  |  | Firm Load Loss, For Information Only
ALTALINK | 172L (254s Coaldale - 172L944C) | 2017-05-19 08:45 | 2017-05-22 08:44 | N | N | line maintenance | Line |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 942L (681s Bannerman - 71s Lamoureux) | 2017-05-20 07:30 | 2017-05-21 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (410s Josephburg - 402s Scotford Expansion) | 2017-05-20 07:30 | 2017-05-23 17:30 | N | Y | damper replacements | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 739L (305s Acheson - 434s Stony Plain) | 2017-05-20 07:30 | 2017-05-30 17:30 | N | N | install foundation for new structure | Line |  |  | Pre-Condition
ALTALINK | 423L (212s N.E.Lacombe - 332s Ellis) | 2017-05-20 08:00 | 2017-05-25 16:00 | N | N | In service date: May 25, 2017 | Line
ALTALINK | 1106L (ENMAX 65 - 237s Foothills) | 2017-05-21 07:30 | 2017-05-27 18:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2017-05-21 08:00 | 2017-05-21 16:00 | N | N | investigate circulating currents between 1s & 5s | Line |  |  | For Information Only
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2017-05-21 08:00 | 2017-05-21 16:00 | N | N | investigate circulating currents between 1s & 5s | Line |  |  | For Information Only
Syncrude | AL-1 (D05 Syncrude - Aurora) | 2017-05-22 06:00 | 2017-06-03 21:00 | N | Y | tie-Ins for various infrastructure system | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 1061L (12s Heartland - 681s Bannerman) | 2017-05-22 07:30 | 2017-05-23 17:30 | N | Y | damper replacements, QA/QC checks | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9),ENMAX 9 B138-9.80 (ENMAX 9),Enmax 31 B138-9.80 (ENMAX 31) | 2017-05-22 08:00 | 2017-05-23 16:00 | N | N | breaker inspection on 31B138-9.80 and 9B138-9.80 | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ENMAX | 20.1TR (ENMAX 20) | 2017-05-22 08:00 | 2017-05-26 16:00 | N | N | transformer CT and 138 kV Bus differential relay replacement | Transformer |  |  | For Information Only
ALTALINK | 172L (370s North Lethbridge - 254s Coaldale) | 2017-05-22 08:45 | 2017-05-28 17:45 | N | N | line maintenance | Line |  |  | Pre-Condition
ALTALINK | 648s T3 (648s Metiskow),954L (648s Metiskow - 650s Hansman Lake),648s 29 (648s Metiskow) | 2017-05-22 10:00 | 2017-05-22 12:30 | N | Y | testing required for 648s749E protection replacement | Circuit Breaker, Line, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 678s T1 (678s Okotoks),646L (678s Okotoks - 237s Foothills),678s Okotoks 138kV Bus 1,850L (525s Carseland - 678s Okotoks),678s T3 (678s Okotoks) | 2017-05-22 10:00 | 2017-06-05 17:00 | N | N | install and commission T1 single phase slip, 678s S2, 678s352 and commission T3 and T3 25kv new equipment and feeders | Transformer, Bus, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2017-05-22 12:31 | 2017-05-22 17:30 | N | N | testing required for 648s749E protection replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2017-05-23 06:00 | 2017-05-25 17:30 | N | N | required for station SCADA upgrade and substation maintenance work, and 793s859W breaker CT replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L85 (803s Bullpound - 801s Anderson) | 2017-05-23 07:00 | 2017-06-01 17:00 | N | N | protection upgrade, install & commission new protection | Line |  | 801S Anderson 7L85 Protection Upgrade. Removal of existing 7L85 Distance Protection. Installation and commissioning of new protection. Transmission Maint will piggyback on to this work to cover off their maint requirements. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 935L (324s Cassils - 356s Milo) | 2017-05-23 07:00 | 2017-05-25 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 240 kV
ALTALINK | 89s 1352 (89s Ellerslie),89s 1452 (89s Ellerslie) | 2017-05-23 07:00 | 2017-05-25 17:00 | N | Y | SCADA equipment upgrade | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 814s T2 (814s Bellamy),RossdaleT1 (Rossdale) | 2017-05-23 07:00 | 2017-07-02 17:00 | N | Y | retrofit rossdale TX | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 523s T1 (523s Bullshead) | 2017-05-23 07:00 | 2017-05-31 13:00 | N | N | decommision and remove old 523s122 breaker, connect bypass cables, replace VR bypass with new 523s389, replace 406L & 381L UG cables | Transformer |  |  | For Information Only
ALTALINK | 214s T2 (214s Innisfail),80L (214s Innisfail - 55s Olds),214s Innisfail 138kV Bus 2 | 2017-05-23 07:00 | 2017-06-29 09:00 | N | N | connect 214s52,VT5,new 443L bay,new 420L bay, replace and install protections, etc. | Transformer, Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 217s C1 (217s North Red Deer),425L (194s South Red Deer - 217s North Red Deer),217s North Red Deer 138 kV Bus,444L (198s Blackfalds - 217s North Red Deer),768L (217s North Red Deer - 209s Timberlands) | 2017-05-23 07:15 | 2017-05-24 17:15 | N | N | to replace 138kV circuit switcher interrupters on 14-81-1 | Line, Bus, Shunts |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 514L (513s Lundbreck - 514L198) | 2017-05-23 07:30 | 2017-05-26 16:30 | N | N | replacing insulators and repairing grounding on structures 199 - 448 | Line |  |  | Pre-Condition
ALTALINK, ENMAX | 30.81L (42s Sarcee - ENMAX 30),42s 30 (42s Sarcee),42s 56 (42s Sarcee) | 2017-05-23 07:30 | 2017-06-06 16:30 | N | N | SWCRR - temporary tie in to ENMAX 35, energization of HV switchgear,temporary 35.81L from 35s to 42s, protection work | Circuit Breaker, Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.1TR (ENMAX 13) | 2017-05-23 08:00 | 2017-05-24 12:00 | N | N | LTC maintenance | Transformer
ENMAX | 14.2C (ENMAX 14) | 2017-05-23 08:00 | 2017-05-25 16:00 | N | N | capacitor bank maintenance | Shunts |  |  | Pre-Condition
ALTALINK | 885L (648s Metiskow - 650s Hansman Lake),648s 885 (648s Metiskow) | 2017-05-23 08:30 | 2017-05-23 12:30 | N | N | trip testing required for 648s749E protection replacement | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 434s T1 (434s East Stony Plain) | 2017-05-23 09:30 | 2017-05-25 18:00 | N | N | replace U/G terminators on 2218L cables | Transformer |  |  | For Information Only
ALTALINK | 526s C1 (526s Buffalo Creek),526s 652 (526s Buffalo Creek) | 2017-05-23 09:30 | 2017-05-23 16:00 | N | N | urgent breaker maintenance | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ATCO | 6L56 (763s Hanna - 802s Michichi Creek),763s 601 (763s Hanna) | 2017-05-23 10:00 | 2017-05-23 16:00 | N | N | emergency top up of oil | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage
ATCO | 720s 902 (720s Wabasca) | 2017-05-23 10:00 | 2017-05-24 15:00 | N | Y | breaker SF6 hgf complete,902 @ 720S perform major PM on spare breaker | Circuit Breaker |  | BREAKER SF6 HGF COMPLETE,902 @ 720S...Complete Perform Major PM on Spare Breaker 902 Breaker is normally out of service | 240 kV, For Information Only
ALTALINK | 205s 352 (205s Castle Rock) | 2017-05-23 12:00 | 2017-05-23 16:00 | N | Y | heater replacement on centre phase | Circuit Breaker |  | Priority is critical for this heater to be fixed. Heater replacement on centre phase. | 240 kV, Contingency Requires Mitigation
ALTALINK | 511s ACF12 (511s Crossings),511s SVC Plus (511s Crossings),511s ACF13 (511s Crossings),511s ACF11 (511s Crossings) | 2017-05-23 12:00 | 2017-05-23 18:30 | N | Y | 2017 CIP 007 maintenance | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 250p11 (250p Bighorn) | 2017-05-24 07:00 | 2017-05-25 07:00 | N | Y | spring test | Switch |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn) | 2017-05-24 07:00 | 2017-05-29 05:00 | N | Y | spring test | Switch |  |  | Restricts Generation
ALTALINK | 1054L (13s Deerland - 12s Heartland) | 2017-05-24 07:30 | 2017-05-30 17:54 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 786s 702T (786s High Level) | 2017-05-24 08:00 | 2017-05-24 16:30 | N | N | testing and maintenance | Transformer |  | Complete 702T testing and maintenance. / 25kV Load fed from 701T for the duration of the work | For Information Only
ALTALINK | 526s T2 (526s Buffalo Creek) | 2017-05-24 08:00 | 2017-05-25 15:00 | N | N | transformer maintenance and doble | Transformer |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3),3.84L (ENMAX 13 - ENMAX 3),ENMAX 3 B138-3.84 (ENMAX 3) | 2017-05-24 08:00 | 2017-05-25 16:00 | N | N | doble 3B138-3.84 and HV SW/MD maintenance | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 675L (244s Bowmanton - 41s Medicine Hat) | 2017-05-24 08:10 | 2017-05-26 16:00 | N | N | forced outage | Line |  |  | For Information Only
ALTALINK | 511s ACF22 (511s Crossings),511s ACF21 (511s Crossings) | 2017-05-24 08:30 | 2017-05-24 12:30 | N | Y | 2017 CIP 007 maintenance | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 1090L (723s Christina Lake - 698s Jackfish),698s T1 (698s Jackfish),698S Jackfish 240kV Bus 1 | 2017-05-24 08:30 | 2017-05-24 12:30 | N | Y | damper replacements (crossing over bus work) | Line, Transformer, Bus |  |  | 240 kV, Creates Radial Feeds
ATCO | 813s SVC (813s Little Smoky) | 2017-05-24 09:00 | 2017-05-25 17:00 | N | Y | SVC maintenance | Shunts |  | SVC maintenance, SVC not available for dispatch | Pre-Condition
AESO-SC | DT | 2017-05-24 09:00 | 2017-05-24 11:00 | N | N | new user cert for DT ADaMS to be deployed to F5 servers | SCInternal |  |  | For Information Only
ENMAX | 13.2TR (ENMAX 13) | 2017-05-24 12:00 | 2017-05-25 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook),510s ACF21 (510s Sunnybrook) | 2017-05-24 12:30 | 2017-05-24 18:30 | N | Y | 2017 CIP 007 maintenance | Shunts |  |  | Pre-Condition, 500 kV
ALTALINK | 1099L (698s Jackfish - 154s Black Spruce),698s T1 (698s Jackfish),698S Jackfish 240kV Bus 1 | 2017-05-24 13:30 | 2017-05-24 17:30 | N | Y | damper replacements (crossing over bus work) | Line, Transformer, Bus |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, REDDEER | 217s T2 (217s North Red Deer),778L (217s North Red Deer - 87s Gaetz),217s North Red Deer 138 kV Bus,444L (198s Blackfalds - 217s North Red Deer),217s4 (217s North Reddeer) | 2017-05-25 07:30 | 2017-05-26 18:30 | N | N | to replace 138kV circuit switcher interrupters | Bus, Transformer, Line, Switch |  | From Red Deer submission: Replace 14-81-2 138kV circuit switcher interrupters. Manufacture notice If ambient temperatures drop to -23°C or below before the interrupters on an affected 40-kA Series 2000 Circuit-Switcher are replaced, the Circuit-Switcher should not be operated while personnel are in the substation. extreme cold may affect the properties of a grease applied during assembly of the lost-motion contact assembly, resulting in possible improper operation of the Circuit-Switcher in extreme cold conditions. | Overload, Over/Under Voltage, Creates Radial Feeds
CENOVUS | 539s PCB_9201 (539s Sunday Creek) | 2017-05-25 07:30 | 2017-06-22 17:00 | N | Y | CT-9205 replacement | Circuit Breaker |  |  | 240 kV
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),ENMAX 3 B138-3.84 (ENMAX 3) | 2017-05-25 08:00 | 2017-05-25 16:00 | N | N | HB breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 744s 601T (744s Federated Pipelines) | 2017-05-25 08:00 | 2017-05-25 16:00 | N | N | transformer leak repair | Transformer |  |  | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook),510s 2052 (510s Sunnybrook) | 2017-05-25 08:30 | 2017-05-25 12:30 | N | Y | 2017 CIP 007 maintenance | Shunts, Circuit Breaker |  | Devices in group DCY, T11 and VH are not impacted by ACF or breaker outages. These are additional items in the entire site work package and individual protection outages. | Pre-Condition, 500 kV
ALTALINK | 898L (37s North Calder - 92s Viscount),92s 898 (92s Viscount) | 2017-05-25 08:30 | 2017-05-25 12:30 | N | N | breaker maintenance - pressure gauge | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1099L (698s Jackfish - 154s Black Spruce),154s Black Spruce 240 kV Bus 2 | 2017-05-25 08:30 | 2017-05-25 12:30 | N | Y | damper replacements (crossing over bus work) | Bus, Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 1115L (154s Black Spruce - 170s Pike),154s Black Spruce 240 kV Bus 2 | 2017-05-25 13:30 | 2017-05-25 17:30 | N | Y | damper replacements (crossing over bus work) | Bus, Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s T2 (42s Sarcee),906L (17s Benalto - 42s Sarcee),42s Sarcee 240kV South Bus | 2017-05-26 07:00 | 2017-05-26 18:00 | N | Y | installing pollution monitors | Bus, Line, Transformer, Shunts |  |  | 240 kV, Pre-Condition, Overload
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2017-05-26 08:00 | 2017-05-27 16:00 | N | N | SF6 gas sample, Maintenance and test | Line, Transformer |  | SF6 gas sample 3B138-3.82. HV SW/MD Maintenance 3.3MD, SW81, SW82, SW83, SW87G, Sheath Test & DGA on LPOF 138KV cable. | For Information Only
ATCO | 861s 601T (861s Eureka River) | 2017-05-26 08:01 | 2017-06-20 13:00 | N | N | new transformer installation construction | Transformer |  | Isolate 861S 72 KV and 25kV bus for new transformer installation construction, all 25kV load on 750s, Stn service on alternate supply | For Information Only
ALTALINK | 379s 289 (379s Shell Waterton),379s 189 (379s Shell Waterton) | 2017-05-26 11:00 | 2017-05-26 12:00 | N | N | customer request to open 379s189 & 379s289 to perform dead-bus test | Switch |  |  | For Information Only
ALTALINK | 150L (42s Sarcee - 150L47),3L (42s Sarcee - 272s Springbank) | 2017-05-27 07:15 | 2017-06-02 15:30 | N | N | SWCRR foundation work | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1053L (132s Ware Junction - 324s Cassils),132s Ware Junction 240kV South Bus | 2017-05-27 08:30 | 2017-05-27 12:30 | N | Y | damper replacements (crossing over bus work) | Line, Bus |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 939s Livock RTU/SCADA | 2017-05-27 09:30 | 2017-05-27 10:30 | N | N | urgent replacement of RTU batteries | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 484s T1 (484s Millar Western) | 2017-05-28 06:30 | 2017-05-31 16:30 | N | N | metering upgrade and transmission maintenance | Transformer |  |  | For Information Only
ALTALINK | 484s T3 (484s Millar Western) | 2017-05-28 06:30 | 2017-06-01 16:30 | N | N | replace oil, test transformer and metering upgrade | Transformer |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2017-05-28 08:00 | 2017-05-28 16:00 | N | N | top up SF6 gas pressure | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 665s TX1 (665s Dome) | 2017-05-29 07:00 | 2017-05-29 17:00 | N | Y | repair | Transformer |  |  | 240 kV, Pre-Condition
EPCOR | 816s T1 (816s Petrolia) | 2017-05-29 07:00 | 2017-06-03 17:00 | N | Y | doble | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
Medicine Hat, CMH | MH69s2 MH69_202 (MH69s2 North Industrial),MH69s2 MH69_206 (MH69s2 North Industrial),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview),MH69s2 MH69-T21(North Industrial substation) | 2017-05-29 07:00 | 2017-06-01 16:00 | N | N | modifications to 69 kV west bus | Transformer, Circuit Breaker, Line |  | From May 29  June 9, 2017 the City of Medicine Hat Electric Distribution will be taking an outage on MH-2S North Industrial west 69 kV overhead bus. The equipment included as part of the outage is: Transformer T-21 Disconnect Switch  MH69-205, 204, 203 & 201 Circuit Breakers  MH69-206 & 202 | Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 42s T2 (42s Sarcee),28.80L (42s Sarcee - ENMAX 28),42s Sarcee 138 kV South Bus | 2017-05-29 07:00 | 2017-05-30 17:00 | N | Y | installing pollution monitors | Transformer, Line, Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 966L (650s Hansman Lake - 932s Pemukan) | 2017-05-29 07:30 | 2017-05-30 18:30 | N | Y | damper replacement | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ATCO | 7L130 (710s Vermilion - 705s Kitscoty) | 2017-05-29 08:00 | 2017-06-01 17:00 | N | N | salvage under-strung 25 kV line | Line |  | Salvage 25 kV portion of Vermilion nav. Water Cannot access the 25 kV under-strung without encroaching the 144 KV | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2017-05-29 08:00 | 2017-07-06 20:30 | N | Y | contractor digging under 138kv line | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24),ENMAX 24 B138-24.83 (ENMAX 24),74s 24.83X (74s Janet) | 2017-05-29 08:00 | 2017-06-09 16:00 | N | Y | line protection upgrade on 24.83L | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation
ENMAX | 24.1TR (ENMAX 24) | 2017-05-29 08:00 | 2017-06-02 16:00 | N | N | replace dev 90 PT | Transformer |  |  | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2017-05-29 08:00 | 2017-06-02 16:00 | N | N | doble TR and transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 716L/80L (40s Wetaskiwin - 958s West Lacombe) | 2017-05-29 08:30 | 2017-05-29 17:00 | N | N | salvage 80L/716L from 958s-40s | Line |  |  | For Information Only
BCH | 5L72 (Mica Creek - Nicola) | 2017-05-29 09:00 | 2017-06-09 17:00 | N | N | arcing horn install and spacer replacement - BC maintenance does not affect AB ATC | Line | Peak RC#: 1-00483762, 1-00483763 | complete nerc testing of 5CX2, pn's (py and sy) associated with cap banks to be blocked oat during testing, no platform access required | Limits ATC, 500 kV
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2017-05-29 09:00 | 2017-05-30 18:00 | N | Y | CBK 2CVT3 replacement and replace defective insulators | Line | Peak RC#: 1-00483759, 1-00483761 |  | Limits ATC
ATCO | 790s 701T (790s Poplar Hill) | 2017-05-29 10:00 | 2017-05-31 15:00 | N | N | 790S 701T class2 major testing, all load transferred to 702T | Transformer |  | 790S 701T TRANSFORMER CLASS2 MAJOR TESTING, all load transferred to 702T -------- Load Transfer -------- 790S 5L375 Peak Load = 10.15 MVA 790S 5L422 Peak Load = 5.34 MVA 790S 5L375 Relay Settings: 27.02 MVA SEL 790S 5L422 Relay Settings: 17.4 MVA SEL Setting change reqd -------- Load Transfer -------- | For Information Only
ALTALINK | 1036L (554s Travers - 356s Milo) | 2017-05-29 11:00 | 2017-06-01 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 102s 6652 (102s Langdon) | 2017-05-29 11:00 | 2017-05-29 17:00 | N | Y | Urgent: breaker does not operate properly, need to replace auxiliary contacts. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 489s T2 (489s Petro Canada Brazeau River) | 2017-05-30 06:30 | 2017-05-31 18:00 | N | N | replace 138kV and 4.16kV arrestors on transformer | Transformer |  |  | For Information Only
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2017-05-30 07:00 | 2017-05-30 17:00 | N | N | mine shut-down | Line |  |  | For Information Only
ATCO | 7L130 (710s Vermilion - 705s Kitscoty),710s 702 (710s Vermilion) | 2017-05-30 08:00 | 2017-05-30 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | 43.1TR (ENMAX 43) | 2017-05-30 08:00 | 2017-05-30 16:00 | N | N | test TR diff relay | Transformer |  |  | For Information Only
ALTALINK | 551S Chevron Kaybob,346S Kaybob,355S Chevronknight,864AL (346s Kaybob - 864L tap),864BL (355s Chevron Knight - 864L tap),864L (397s Benbow - 551s Chevron Kaybob),397s Benbow 138kV Bus 3,685L (397s Benbow - 1012s Deer Hill) | 2017-05-30 08:00 | 2017-06-03 17:00 | N | N | perform maintenance & project work | Line, Bus, Station |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAXEC | 383s T1 (383s Kettles Hill Windfarm),383s T2 (383s Kettles Hill Windfarm) | 2017-05-30 08:00 | 2017-05-30 18:00 | N | Y | transformer maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 212s T1 (212s N.E.Lacombe),423L (212s N.E.Lacombe - 332s Ellis),80AL (958s West Lacombe - 212s N.E Lacombe) | 2017-05-30 08:00 | 2017-05-30 11:00 | N | N | remove 212s189 interlock | Line, Transformer |  |  | For Information Only
ATCO | 7L574 (970s Bourque - 7L574 tap) | 2017-05-30 09:00 | 2017-05-31 16:00 | N | N | 7L574 TPR, RTU work, radio link replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 1086L/9L47 (898s Heart Lake - 852s Round Hill) | 2017-05-30 10:00 | 2017-05-30 12:00 | N | Y | 1085L/9L55 & 1086L/9L47 TPR upgrade | Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 1L275 (799s Coleman - Natal) | 2017-05-30 19:00 | 2017-06-06 19:00 | N | Y | required for BC maintenance on 60 kV at Natal | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 149s C1 (149s Nisku),149s T1 (149s Nisku),858L (149s Nisku - 40s Wetaskiwin),149s Nisku 138kV South Bus | 2017-05-31 07:15 | 2017-06-01 15:30 | N | N | create T1 bypass and create open points "C" & "D | Bus, Line, Transformer, Shunts |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 519AL (519L tap - 661s Laura Lake),519L (519AL tap - 519L2),519L (519AL tap - 996s Imperial Oil Carson Lake) | 2017-05-31 07:30 | 2017-05-31 17:30 | N | N | component replacement | Line |  |  | For Information Only
ENMAX | 43.2TR (ENMAX 43) | 2017-05-31 08:00 | 2017-05-31 16:00 | N | N | test TR diff relay | Transformer |  |  | For Information Only
ENMAX | 47.1TR (ENMAX 47) | 2017-05-31 08:00 | 2017-06-01 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 391s T1 (391s Balzac) | 2017-05-31 08:00 | 2017-06-01 17:00 | N | N | doble and maintain transformer | Transformer |  |  | For Information Only
ATCO | 2033s Mowat | 2017-05-31 08:00 | 2017-06-02 16:00 | N | N | In-service-date: Jun 1, 2017 | Station
ENMAX | 162s 138-RB82 (162s Beddington) | 2017-05-31 08:00 | 2017-05-31 16:00 | N | N | low dashpot oil | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ENMAX | 41.84L (ENMAX 54 - ENMAX 41) | 2017-05-31 18:00 | 2017-06-01 08:00 | N | N | overnite outage for Graham Construction work; grounds required | Line |  |  | Pre-Condition, For Information Only
SUNCOR | 29EDD-18 Firebag,29EDD-18 752_101 (29EDD-18 Firebag),29EDD18 752_106 (29EDD18 Firebag) | 2017-06-01 06:00 | 2017-06-21 18:00 | N | N | maintenance | Station, Circuit Breaker |  | Turnaround activities, taking opportunity to do maintenance activities on switches (29PS-58, 29PS-57, 29PS-60, 29PS-202, 29PS-203, 29PS-204), breakers (752-101, 752-106) and transformers (29PT-101, 29PT204). Each element will be isolated during maintenance activities, no change to power flow. | For Information Only
ATCO, SUNCOR | 635PL9-1000 (2005s Secord - 635EDD-1000),2005s 901 (2005s Secord),2005s 905 (2005s Secord) | 2017-06-01 07:00 | 2017-06-03 17:00 | N | N | change CT ratios | Circuit Breaker, Line |  | 240kV partial bus outage to change CT ratios (Ring bus will be open), Complete co-ordinated SPS/IMS installation and commissioning in conjunction with Suncor. | 240 kV, Contingency Requires Mitigation
ATCO | 725S 701T | 2017-06-01 08:00 | 2017-06-01 16:00 | N | N | change the taps and seal some leaks | Terminal Equipment |  | 725S GOOSE RIVER To change the taps and seal some leaks. Since 5L174 is a radial feed (no source of back-feed). No isolation point will be required from the secondary side. | For Information Only
ENMAX | 11.83L (162s Beddington - ENMAX 11),ENMAX 11 B138-11.83 (ENMAX 11),162s 138-RB85 (162s Beddington),162s 138-RB84 (162s Beddington) | 2017-06-01 08:00 | 2017-06-01 16:00 | N | N | repair hot spot on 162MD138-11.83 east phase hinge side contact | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 611L (391S Balzac - 186s Dry Creek) | 2017-06-01 09:00 | 2017-06-01 12:00 | N | N | X-ray sleeves | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek) | 2017-06-01 12:01 | 2017-06-01 14:30 | N | N | X-ray sleeves | Line |  | 186s1, 186s2, 199s14, 199s2 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 149s C1 (149s Nisku) | 2017-06-01 15:31 | 2017-06-09 07:14 | N | N | 149s bus reconfig | Shunts |  |  | Pre-Condition
ALTALINK | 149s T3 (149s Nisku),604L (149s Nisku - 155s Blackmud),780L (38s East Edmonton - 149s Nisku) | 2017-06-01 15:31 | 2017-06-09 07:14 | N | N | replace switches 149s16, 149s18, associated bus & T3 fan replacement | Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 816s T1 (816s Petrolia),816s P2401 (816s Petrolia),816s P2402 (816s Petrolia) | 2017-06-02 07:01 | 2017-06-03 17:00 | N | Y | doble | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO, SUNCOR | 635PL9-1001 (2005s Secord - 635EDD-1000),2005s 902 (2005s Secord),2005s 906 (2005s Secord) | 2017-06-04 07:00 | 2017-06-06 17:00 | N | Y | 240kV partial bus outage to change CT ratios (ring bus will be open), complete co-ordinated SPS/IMS installation and commissioning in conjunction with Suncor | Circuit Breaker, Line |  | 240kV partial bus outage to change CT ratios (Ring bus will be open), Complete co-ordinated SPS/IMS installation and commissioning in conjunction with Suncor. | 240 kV, Contingency Requires Mitigation
SUNCOR | 635PL9-1001 (2005s Secord - 635EDD-1000),635PT-1001 (635EDD-1000) | 2017-06-04 08:00 | 2017-06-06 17:00 | N | Y | Fort Hills IMS and load shed system field equipment tie-in and testing ABB relays card change | Line, Transformer |  | 1. Fort Hills Islanding Managemen System (IMS) and LoadShed System Field Equipment Tie-in and Testing 2 . ABB Relays Card Change | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 789s 705R (789s Keg River) | 2017-06-04 08:00 | 2017-06-06 16:00 | N | N | In-service-date: Jun 5, 2017 | Shunts
ALTALINK | 793s T1 (T793s Horse Creek),793s T2 (T793s Horse Creek),793s T3 (T793s Horse Creek),433L (291s Cochrane - T793s Horse Creek),859L (20s Ghost - T793s Horse Creek),793s 433 (793s Horse Creek),793s 859W (793s Horse Creek) | 2017-06-05 06:00 | 2017-06-08 17:30 | N | N | replace PT 793s33, rewire 793s859W, migrate SCADA Controls, add controls to 793s14,SCADA upgrade, substation maintenance, 793s33 CVT replacement, customer T1/T2 cable testing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RS5 (Rossdale - Strathcona) | 2017-06-05 07:00 | 2017-06-09 17:00 | N | N | performing relay calibration and op-checks for relay maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 816s P2401 (816s Petrolia) | 2017-06-05 07:00 | 2017-06-06 17:00 | N | Y | doble test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2075S Newell,13L50 (2029s Heathfield - 2075s Newell),2029s Heathfield | 2017-06-05 07:00 | 2017-06-15 14:08 | N | Y | valve hall outages for repair of dividers and other maintenance | Station, Line |  | Valve hall out of service to repair 1300PT1 divider @ 2029s Heathfield from previous outage. perform maintenance tasks and inspections as per Siemens recommendations. | Pre-Condition, 500 kV
ENMAX | 39.4TR (ENMAX 39) | 2017-06-05 08:00 | 2017-06-09 16:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ENMAX | 13.82L (ENMAX 22 - ENMAX 13),ENMAX 22 B138-13.82 (ENMAX 22) | 2017-06-05 08:00 | 2017-06-06 16:00 | N | N | HV breaker inspection (HLR) | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2017-06-05 08:00 | 2017-06-05 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 5.7TR (ENMAX 5) | 2017-06-05 08:00 | 2017-06-14 16:00 | N | N | bushing replacement (HV&LV) | Transformer |  |  | For Information Only
ALTALINK | 172s T4 (172s Sherritt Gordon) | 2017-06-05 09:00 | 2017-06-05 14:00 | N | N | repair bushing hot spot | Transformer |  |  | For Information Only
ALTALINK | 275s T2 (275s Jenner) | 2017-06-05 09:30 | 2017-06-05 17:00 | N | Y | installing temporary 25 kV cable | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 276s 25 (276s Un Carb Prentiss) | 2017-06-05 10:00 | 2017-06-12 07:00 | N | N | P&C breaker fail upgrade and perform test trips | Circuit Breaker |  |  | Firm Load Loss
ATCO, ALTALINK | 923L (2075s Newell - 356s Milo) | 2017-06-05 11:00 | 2017-06-08 17:00 | N | Y | SCADA equipment upgrade | Line |  |  | 240 kV
ALTALINK | 338s 252 (338s Cherhill) | 2017-06-05 11:30 | 2017-06-06 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2029s ACF14 (2029s Heathfield),2029s ACF11 (2029s Heathfield),2029s ACF12 (2029s Heathfield),2029s ACF13 (2029s Heathfield) | 2017-06-05 12:00 | 2017-06-16 12:00 | N | Y | inspections and maintenance | Shunts |  | inspections and maintenance as per manufacturer recommendations, ACF1 will already be OOS for 13L50/Convertor OOS @ 2029s | For Information Only
ATCO | 2029s 1200SST1 (2029s Heathfield) | 2017-06-05 12:00 | 2017-06-13 12:00 | N | Y | maintenance and inspection | Transformer |  | Maintenance activities include bus bar clamp inspections, gang switch inspections, 1200SST1 inspection and RCVT maintenance testing. EATL will be OOS during this time. SST2 will provide station supply with generator as redundant backup 12L70 still in service which will feed 1200BS2 | For Information Only, 500 kV
ATCO | 12L85 (12s Heartland - 2029s Heathfield),2029s ACF21 (2029s Heathfield),2029s ACF23 (2029s Heathfield),2029s ACF22 (2029s Heathfield) | 2017-06-05 12:00 | 2017-06-17 12:00 | N | Y | maintenance and inspections on 12L85 disconnect and ACF2 filters @ 2029s Heathfield | Line, Shunts |  | performing maintenance and inspections on 12L85 disconnect and ACF2 Filters @ 2029s Heathfield, Convertor station will already be OOS, 12L70 will remain in service | Firm Load Loss, Creates Radial Feeds, 500 kV
ATCO | 2075S Newell | 2017-06-05 12:00 | 2017-06-08 16:00 | N | Y | inspect 240 kV bus between 905A and 906B | Station |  | 240KV BUS PORTION OOS FOR CORONA INSPECTION AND REPAIRS, 9L923 and HVDC converter will already be OOS | 240 kV, For Information Only
ALTALINK | 172s T3 (172s Sherritt Gordon) | 2017-06-05 14:30 | 2017-06-08 16:30 | N | N | replace failed T3 "A" protection. | Transformer |  |  | For Information Only
ALTALINK | 678s T1 (678s Okotoks),678s Okotoks 138kV Bus 1,850L (525s Carseland - 678s Okotoks),678s T3 (678s Okotoks) | 2017-06-05 17:01 | 2017-06-05 18:00 | N | N | install and commission T1 single phase slip, 678s S2, 678s352 and commission T3 and T3 25kV new equipment and feeders | Line, Transformer, Bus |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 678s T1 (678s Okotoks) | 2017-06-05 18:01 | 2017-06-13 08:00 | N | N | continue work on 678s352 breaker install | Transformer |  |  | For Information Only
ATCO | 844s 701T (844s AEC Mill),844s 702T (844s AEC Mill) | 2017-06-06 06:00 | 2017-06-06 20:00 | N | N | isolate transformer 701T and 702T | Transformer |  | Isolate Transformer 701T, 702T as per Customer Request Close Breaker 702 to put station Service back on @ 844S AEC Mill. | Restricts Generation, For Information Only
ALTALINK | 213s T1 (213s Hughenden),703L (213s Hughenden - 703BL tap),213s Hughenden 138 kV bus | 2017-06-06 06:30 | 2017-06-07 17:30 | N | N | replace control handles on 213s30 & 213s33 | Line, Transformer, Bus |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 808s 702T (808s Procter & Gamble),808s 702 (808s Procter Gamble) | 2017-06-06 07:00 | 2017-06-06 17:30 | N | N | install and commission breaker fail protection | Circuit Breaker, Transformer |  | Install and commission breaker fail protection. | For Information Only
ATCO | 2075s 900BS1 240kV bus ( 2075s Newell) | 2017-06-06 07:00 | 2017-06-06 17:00 | N | Y | 900BS1 (bus N-1) inspection and corona repairs at 2075S Newell | Bus |  | 900BS1 (BUSN-1) INSPECTION & CORONA REPAIRS @ 2075S NEWELL, one side 240kV breaker and a half scheme will be open, all lines and filter banks radial tied to 900BS2, Convertor stn will already be OOS While the Bus is in service the AC yard will be running on a single bus for all four lines coming into the station. this will not limit any power flow to 13L50 in any way. Plan to restore the bus before the end of the shift, so that ALTALINK and ATCO do not have to worry about running the lines on one buss overnight. | 240 kV
Medicine Hat, CMH | MH69s2 MH69_202 (MH69s2 North Industrial),MH69s2 MH69_206 (MH69s2 North Industrial),MH69s2 MH69_212 (MH69s2 North Industrial),MH69s2 MH69_215 (MH69s2 North Industrial),MH69s5 MH69_510 (MH69s5 NE Crescent Height),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights),MH69s2 MH69-T21(North Industrial substation),MH69s2 MH69-T22 (North Industrial Substation) | 2017-06-06 07:00 | 2017-06-06 11:00 | N | N | removal of overhead substations shield wire | Transformer, Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 212s T1 (212s N.E.Lacombe),423L (212s N.E.Lacombe - 332s Ellis),80AL (212s N.E.Lacombe - 958s West Lacombe) | 2017-06-06 07:15 | 2017-06-06 17:30 | N | N | remove 212s189 interlock | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 35.81L (42s Sarcee - ENMAX 35),30.81L (ENMAX 35 - ENMAX 30) | 2017-06-06 08:00 | 2017-06-07 16:00 | N | N | in-service-date: Jun 6, 2017 | Line
ALTALINK | 39s 38 (39s Bickerdike) | 2017-06-06 08:00 | 2017-06-06 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 428s T1 (428s Namaka),428s 19 (428s Namaka) | 2017-06-06 09:00 | 2017-06-06 17:00 | N | N | techs to perform wiring changes on B138B1 59/138B MIV relay | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 39s T1 (39s Bickerdike),39s Bickerdike 138kV Bus 1,854L (39s Bickerdike - 854L228A) | 2017-06-06 12:00 | 2017-06-06 18:00 | N | Y | insulator replacement | Bus, Line, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 800s 702T (800s Friedenstal) | 2017-06-06 12:00 | 2017-06-08 17:00 | N | N | remove temp 72 kv u/g bypass cables | Transformer |  | Remove temp 72 kv u/g bypass cables, confirm all load on 701T | Firm Load Loss, Creates Radial Feeds
CMH | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2017-06-06 13:30 | 2017-06-06 14:30 | N | N | high load move | Line |  |  | For Information Only
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2017-06-06 14:30 | 2017-06-06 15:30 | N | N | high load move | Line |  |  | For Information Only
EPCOR | 987s CGB3 (987s Clover Bar),987s GDS3 (987s Cloverbar) | 2017-06-07 02:00 | 2017-06-19 14:00 | N | N | disconnect repair and breaker maintenance | Switch, Circuit Breaker |  |  | Restricts Generation, For Information Only
EPCOR | 816s P2402 (816s Petrolia) | 2017-06-07 07:00 | 2017-06-08 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 523s T1 (523s Bullshead) | 2017-06-07 07:00 | 2017-06-07 14:00 | N | N | re-install the primary connections on VR1 | Transformer |  |  | For Information Only
ALTALINK | 854L (39s Bickerdike - 854L228A) | 2017-06-07 07:15 | 2017-06-08 16:00 | N | N | maintenance repairs | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 527s T1 (527s Coal Valley) | 2017-06-07 08:00 | 2017-06-07 18:30 | N | N | 138kV strain insulators cracked and 527s T1 broken Xo conductor | Transformer |  |  | For Information Only
ALTALINK | 740AL (414s Gulf Robb - 740AL1),740L (39s Bickerdike - 740AL1),740L (426s Coalspur - 740L tap),743L (527s Coal Valley - 743L1A),762L (101s Cheviot - 762L2) | 2017-06-07 08:00 | 2017-06-07 18:30 | N | N | replace insulators | Line |  |  | Firm Load Loss
ENMAX | 162s 240-RB134 (162s Beddington) | 2017-06-07 08:00 | 2017-06-07 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41) | 2017-06-07 08:00 | 2017-06-16 16:00 | N | N | install temporary jumpers between 33.83L & 6.82L | Line |  | (FATDSC)-Install temporary jumpers between 33.83L & 6.82L. Line protection to be updated. 41CAP Switcher Replacement. | Creates Radial Feeds
ENMAX | 41.1C (ENMAX 41),41.2TR (ENMAX 41),ENMAX 41 138 kV West Bus | 2017-06-07 08:00 | 2017-08-05 16:00 | N | N | west bus modifications - new 41B138-41BT3, 41PT138-Z32 energized on return | Bus, Transformer, Shunts |  |  | For Information Only
SUNCOR | 635PL7-1005 (635EDD-1001 - 635EDD-1003) | 2017-06-07 08:00 | 2017-10-09 12:00 | N | N | co-gen and line protection testing and commissioning activities | Line |  | Fort Hills: Co-Gen and Line Protection Testing and Commissioning activities (Ongoing for 10 weeks) | For Information Only
ALTALINK | 71s C1 (71s Lamoureux),71s 952 (71s Lamoureux) | 2017-06-07 08:30 | 2017-06-09 12:00 | N | Y | replace CT cabling between 71s952 JB and the building | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 338s T1 (338s Cherhill) | 2017-06-07 08:30 | 2017-06-08 17:30 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, For Information Only
ATCO | 790s 509 (790s Poplar Hill),790s 509C (790s Poplar Hill) | 2017-06-07 09:00 | 2017-06-07 14:00 | N | N | breaker SF6 FB4 partial testing | Circuit Breaker, Shunts |  | 790S 509 BREAKER SF6 FB4 PARTIAL TESTING Cap bank not available | Pre-Condition
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2017-06-07 09:00 | 2017-06-08 19:00 | N | Y | CBK 2CVT3 replacement and replace defective insulators | Line | Peak RC COS Path #: 1-00484839, 1-00484840 Peak RC COS Outage # (BCH outage): 1-00484717 |  | Limits ATC
ALTALINK | 62s 1 (62s Brazeau) | 2017-06-07 23:00 | 2017-06-08 03:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 2 (62s Brazeau) | 2017-06-08 03:01 | 2017-06-08 07:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation, For Information Only
ALTALINK | 472L (213s Hughenden - 472AL tap) | 2017-06-08 06:30 | 2017-06-08 17:30 | N | N | replace control handles on 213s36 | Line |  |  | Firm Load Loss, Creates Radial Feeds
Medicine Hat, CMH | MH69s2 MH69_202 (MH69s2 North Industrial),MH69s2 MH69_206 (MH69s2 North Industrial),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2017-06-08 07:00 | 2017-06-08 16:00 | N | N | emergency bus outage | Circuit Breaker, Line |  | Required modifications to 69 kV west bus structure.
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2017-06-08 07:00 | 2017-06-08 16:00 | N | N | connect 472s mobile to 525s & maintenance, project & customer work | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2017-06-08 07:30 | 2017-06-08 18:00 | N | N | bushing change - H2 | Transformer
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24),ENMAX 24 B138-24.83 (ENMAX 24) | 2017-06-08 08:00 | 2017-06-08 16:00 | N | Y | doble breaker | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 7L19 (809s Louise Creek - 851s Morse River),809s 706 (809s Louise Creek) | 2017-06-08 09:00 | 2017-06-08 16:00 | N | N | partial maintenance on breaker | Line, Circuit Breaker |  | Partial Maintenance on Breaker 706@809S, 7L19 open ended at 809S Louise Creek | Pre-Condition
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2017-06-08 15:24 | 2017-06-14 17:00 | N | Y | forced outage due to downed structure (tractor) | Line |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 793s T1 (T793s Horse Creek),793s T2 (T793s Horse Creek),433L (291s Cochrane - T793s Horse Creek),793s 433 (793s Horse Creek),793s 138kV Bus T1/T2 - Advice | 2017-06-08 17:31 | 2017-06-13 17:30 | N | N | SCADA upgrade and substation maintenance work | Terminal Equipment, Line, Transformer, Circuit Breaker |  | required for station SCADA upgrade and Substation Maintenance work, and 793s33 CVT Like for Like Replacement,Customer T1/T2 Cable Testing | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia) | 2017-06-09 07:00 | 2017-06-21 17:00 | N | Y | steel pole refurbishment | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, EPCOR | 1043L (320p Keephills - 816s Petrolia) | 2017-06-09 07:00 | 2017-06-09 17:00 | N | Y | doble | Line |  |  | 240 kV
ALTALINK | 149s C1 (149s Nisku),149s T1 (149s Nisku),858L (149s Nisku - 40s Wetaskiwin),149s Nisku 138kV South Bus | 2017-06-09 07:15 | 2017-06-16 17:45 | N | N | remove 874L  T1 bypass, close open points "C" & "D", replace switches 149s9, 149s17, associated bus & replace T1 fans | Shunts, Line, Bus, Transformer |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2017-06-09 08:00 | 2017-06-10 16:00 | N | N | forced outage | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2017-06-09 08:00 | 2017-06-09 19:00 | N | Y | CBK 2CVT3 replacement and replace defective insulators | Line | Peak RC COS Path #: 1-00484839, 1-00484840 Peak RC COS Outage # (BCH outage): 1-00484717 |  | Limits ATC
ENMAX | 13.2TR (ENMAX 13),13.4TR (ENMAX 13),11.81L (ENMAX 13 - ENMAX 11),13.60L (ENMAX 27 - ENMAX 13),13.82L (ENMAX 22 - ENMAX 13) | 2017-06-10 08:00 | 2017-06-11 16:00 | N | N | finish painting bus structure. 22B138-13.82 HV breaker inspection (HLR) | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 929L (63s Red Deer - 74s Janet),63s 2752 (63s Red Deer),63s 2652 (63s Red Deer) | 2017-06-12 06:30 | 2017-06-15 17:30 | N | Y | change in scope to 63s2652 & 63s2752 bkr control wiring only | Line, Circuit Breaker |  | Change in scope to 63s2652 & 63s2752 bkr control wiring only - QQ towers to be installed at a later date | 240 kV, Contingency Requires Mitigation
EPCOR | 805s T4 (805s Jasper) | 2017-06-12 07:00 | 2017-06-16 17:00 | N | Y | CVT replacements | Transformer |  |  | 240 kV, Contingency Requires Mitigation
MONTANA | MATL (120s Picture Butte - Montana) | 2017-06-12 07:00 | 2017-06-12 20:00 | N | Y | maintenance | Line | Peak RC Path Outage ID: 1-00484863, 1-00484865 Peak RC Outage ID: 1-00484858 |  | 240 kV, Pre-Condition, Limits ATC
ATCO | 801s 901T (801s Anderson),801s Anderson 240kV BUS #1 | 2017-06-12 07:00 | 2017-07-28 17:00 | N | Y | construction - Protection upgrade | Bus, Transformer |  | 901T and 240kV bus # 1 OOS for Construction - Protection upgrade, 7L85 will be open ended @ 801s and radial feeding 25kV load, Breaker and a third bus configuration at 801s will be open at one end, 801s AC stn service on alternate supply. | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 816s P2403 (816s Petrolia) | 2017-06-12 07:00 | 2017-06-13 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2017-06-12 08:00 | 2017-06-16 16:00 | N | N | LTC maintenance - Reinhausen Type H | Transformer |  |  | For Information Only
ALTALINK | 786L (799s Coleman - Natal) | 2017-06-12 08:00 | 2017-06-15 16:48 | N | N | forced outage due to RAS problem | Line
ALTALINK | 775L (535s Joffre - 276s Prentiss),276s Union Carbide Prentiss 138 kV Center Bus | 2017-06-12 08:00 | 2017-06-12 17:00 | N | N | P&C breaker fail upgrade and perform test trips, add supervisory controls to 276s27 | Line, Bus |  |  | Pre-Condition
ENMAX | 14.3TR (ENMAX 14) | 2017-06-12 08:00 | 2017-06-16 16:00 | N | N | doble & TR maintenance | Transformer |  |  | For Information Only
ENMAX | 24.81L (ENMAX 31 - ENMAX 24),ENMAX 24 B138-24.81 (ENMAX 24) | 2017-06-12 08:00 | 2017-06-12 16:00 | N | N | doble | Line, Circuit Breaker |  |  | Pre-Condition
ATCO | 848s 901T (848s Ruth Lake) | 2017-06-12 09:00 | 2017-06-16 17:00 | N | Y | 901T Major testing and Maintenance at 848S Ruth Lake | Transformer |  | 901T Major testing and Maintenance at 848S Ruth Lake | 240 kV, Over/Under Voltage
ALTALINK | 678S Okotoks,678s T1 (678s Okotoks) | 2017-06-12 10:00 | 2017-07-06 17:30 | N | N | 25kV bus 1- add T1 low side 25kV breaker, modify existing 25kV bus 1 AMI and tie in cables | Transformer, Station |  |  | For Information Only
ALTALINK | 410s 652 (410s Josephburg) | 2017-06-12 10:00 | 2017-06-12 17:30 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 927L (102s Langdon - 356s Milo),356s 552 (356s Milo),356s 652 (356s Milo) | 2017-06-12 11:00 | 2017-06-15 17:00 | N | Y | SCADA equipment upgrade | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 228S T.M.P.L.Niton,228s T1 (228s T.M.P.L.Niton) | 2017-06-12 12:00 | 2017-06-15 18:00 | N | N | meter upgrade & maintenance | Transformer, Station |  |  | For Information Only
BCH | 5L71 (Mica Creek - Nicola) | 2017-06-12 12:30 | 2017-06-30 17:00 | N | Y | clearance required to install arcing horns and replace spacers | Line | BC Peak RC COS#: 1-00487379 AB Peak RC COS# : 1-00490857 (W-E), 1-00490858 (E-W) |  | Limits ATC, 500 kV
ALTALINK | 276s T1 (276s Union Carbide Prentiss),759L (87s Gaetz - 276s Prentiss),276s Union Carbide Prentiss 138 kV Center Bus | 2017-06-12 18:00 | 2017-06-16 12:00 | N | N | trip tests as part of the P&C breaker fail upgrade, add supervisory controls to 276s13 | Bus, Line, Transformer |  |  | Pre-Condition
ALTALINK, ENBRIDGE | 656S Clipper,296S Rosyth,769L (377s Hardisty - 296s Rosyth) | 2017-06-13 06:00 | 2017-06-13 21:00 | N | N | install new breaker, salvage faulting switch, motorize 296s1 & 296s2,install new breaker, salvage faulting switch, motorize 296s1 & 296s2 at | Line, Station |  |  | Firm Load Loss
ALTALINK, TRANSCANADA | 525S Carseland,782L (525s Carseland - 269s Wyndham),851L (525s Carseland - 253s Blackie) | 2017-06-13 07:00 | 2017-06-15 17:00 | N | Y | bus protection upgrade and maintenance work | Line, Station |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
ENBRIDGE | Hay Lake North Series Capacitor,Marias South Series Capacitor | 2017-06-13 07:00 | 2017-06-13 20:00 | N | Y | series capacitor banks were removed from service | Shunts |  |  | 240 kV, Limits ATC
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2017-06-13 07:30 | 2017-06-15 17:00 | N | N | conductor repairs, 873s will be radial fed from Stettler | Line |  | Conductor repairs, 873s will be radial fed from Stettler | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 108s T1 (108s Amelia) | 2017-06-13 08:00 | 2017-06-13 17:30 | N | Y | transformer maintenance | Transformer |  | Transformer maintenance - temperature monitor | 240 kV, For Information Only
ATCO | 7L06 (A793s West Peace River - 784s Donnelly),A793s 703 (A793s West Peace) | 2017-06-13 08:00 | 2017-06-13 16:30 | N | N | breaker maintenance | Circuit Breaker, Line |  | 793S 703 BREAKER MIN OIL HLR PARTIAL TESTING Complete Breaker Maintenance 703 Out if Service for the Duration of the Work | Creates Radial Feeds
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek),268s 199N (268s Whitecourt) | 2017-06-13 08:30 | 2017-06-13 14:00 | N | N | full trip tests from T1 A & B protection as well as 138 kV bus protection | Circuit Breaker, Line |  | Complete full trip tests from T1 A & B protection as well as 138 kV Bus protection. Redundant protections one at a time. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 61s T1 (61s Lodgepole) | 2017-06-13 09:30 | 2017-06-13 17:30 | N | N | bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 793s T2 (T793s Horse Creek) | 2017-06-13 18:00 | 2017-06-16 17:30 | N | N | SCADA upgrade | Transformer |  |  | For Information Only
ALTALINK | 234L (310p Sundance - 234L1),505L (505L1 - 234L tap) | 2017-06-14 07:00 | 2017-06-14 18:00 | N | N | urgent repair on cross arm of structure 45 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant) | 2017-06-14 07:15 | 2017-06-19 13:00 | N | N | hardware on insulators replacements, marker balls installation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 510S Sunnybrook | 2017-06-14 08:00 | 2017-06-14 16:00 | N | N | DC filter to repair damaged capacitors and remove dead birds | Station
ATCO | 7L27 (834s Wesley Creek - A793s West Peace River),A793s 705 (A793s West Peace) | 2017-06-14 08:00 | 2017-06-14 16:30 | N | Y | 793S 705 breaker SF6 HGF partial testing | Circuit Breaker, Line |  | 793S 705 BREAKER SF6 HGF PARTIAL TESTING 7L27 Open ended for the duration of the work | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
CMH, Medicine Hat | MH69s6 MH69_602 (MH69s6 Riverview),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2017-06-14 08:00 | 2017-06-14 15:00 | N | N | crews need to inspect and make changes to the 13.8KV under build along the new 10L line | Line, Circuit Breaker |  |  | For Information Only
EPCOR | Meadowlark T2 (Meadowlark) | 2017-06-14 08:00 | 2017-06-16 16:00 | N | N | urgent tapchanger repair | Transformer
ENMAX | 21.1C (ENMAX 21) | 2017-06-14 08:00 | 2017-06-14 16:00 | N | N | repair fence grounds | Shunts |  | ENMAX would like to schedule an outage to 21CAP for next week. The fence grounds have been stolen & need to be repaired/replaced. | For Information Only
ALTALINK | 445s T2 (445s Elk River) | 2017-06-14 08:30 | 2017-06-14 13:00 | N | N | bushing hot spot, cracked insulator replacement | Transformer |  |  | For Information Only
ALTALINK | 74s 104 (74s Janet) | 2017-06-14 09:00 | 2017-06-15 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV
ATCO | 809s 912 (809s Louise Creek) | 2017-06-14 10:00 | 2017-06-15 12:00 | N | Y | breaker min oil HLR partial | Circuit Breaker |  | BREAKER MIN OIL HLR PARTIAL, 912 @ 809S...Master Perform Minor Maintenance, Breaker 912 240 KV ring will be open for duration | 240 kV, Contingency Requires Mitigation
ATCO | 734s 702T (734s Sturgeon) | 2017-06-14 11:00 | 2017-06-15 16:00 | N | N | transformer maintenance | Transformer |  | Transformer maintenance 25kv Load transferred to 701T | For Information Only
ATCO | 809s 906 (809s Louise Creek) | 2017-06-14 12:30 | 2017-06-15 15:00 | N | Y | breaker min oil HPF partial | Circuit Breaker |  | BREAKER MIN OIL HPF PARTIAL, 906 @ 809S Perform Partial Maint on 906 Breaker 240 KV ring will be open | 240 kV, Contingency Requires Mitigation
ALTALINK | 445s T1 (445s Elk River) | 2017-06-14 13:00 | 2017-06-14 17:30 | N | N | T1 bushing hot spot | Transformer |  |  | For Information Only
ATCO | 793s 706C (A793s West Peace),A793s 706 (A793s West Peace) | 2017-06-15 08:00 | 2017-06-15 16:30 | N | N | breaker SF6 HPL and testing | Circuit Breaker, Shunts |  | 793S 706 BREAKER SF6 HPL PARTIAL TESTING 706C Out of Service for the Duration of the Work | Pre-Condition
ENMAX | 5.8TR (ENMAX 5),ENMAX 5 MD138-5.8TR (ENMAX 5) | 2017-06-15 08:00 | 2017-06-22 16:00 | N | N | TR bushing replacement | Transformer, Circuit Breaker |  | TR bushing replacement (HV) network crew required to switch alternates | For Information Only
ATCO | 786s SVC (786s High Level) | 2017-06-15 08:00 | 2017-06-15 16:00 | N | Y | filter bank oil leaks | Shunts |  |  | Pre-Condition
Medicine Hat, CMH | MH69s6 MH69_602 (MH69s6 Riverview),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2017-06-15 10:00 | 2017-06-15 15:00 | N | N | crews need to inspect and make changes to the 13.8KV under build along the new 10L line | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 228S T.M.P.L.Niton,744L (228s T.M.P.L.Niton - 744L89B),744L (228s T.M.P.L.Niton - 207s Pinedale) | 2017-06-15 10:30 | 2017-06-15 17:30 | N | N | Doble test 228s VT2 | Line, Station |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 276s T2 (276s Union Carbide Prentiss),774L (276s Prentiss - 332s Ellis),276s C1 (276s Prentiss),276s Union Carbide Prentiss 138 kV North Bus | 2017-06-16 13:00 | 2017-06-18 19:00 | N | N | trip tests as part of the P&C breaker fail upgrade and add supervisory controls to 276s3 | Bus, Line, Transformer, Shunts |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 906L (17s Benalto - 42s Sarcee),928L (17s Benalto - 42s Sarcee) | 2017-06-17 07:30 | 2017-07-08 18:30 | N | Y | SWCRR relocate section of 906L to new alignment | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 739L (434s Stony Plain - 739L216A) | 2017-06-17 07:30 | 2017-06-22 17:15 | N | N | line move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),16B69-16.63 (ENMAX 16) | 2017-06-17 08:00 | 2017-06-17 18:00 | N | N | HV breaker inspection & replace 3-way filling valve | Line, Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2017-06-18 08:00 | 2017-06-18 16:00 | N | N | repair / adjust SW82 (only on weekend or off peak season) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 861s 603C (861s Eureka River) | 2017-06-18 08:00 | 2017-06-19 16:00 | N | N | in-service-date: Jun 19, 2017. | Shunts
ALTALINK, EPCOR | 1059L (38s East Edmonton - EP 803s Lambton), 1059AL (52s East Industrial - 1059L tap) | 2017-06-19 07:00 | 2017-06-19 07:15 | N | Y | de-energize 1059L to allow EPCOR to open EDS1 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 850L (525s Carseland - 678s Okotoks) | 2017-06-19 07:00 | 2017-06-19 17:00 | N | N | required to connect 472s mobile to 525s substation maintenance | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 816s P2405 (816s Petrolia) | 2017-06-19 07:00 | 2017-06-20 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 52s T1 (52s East Industrial) | 2017-06-19 07:00 | 2017-06-23 17:00 | N | Y | doble | Transformer |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2017-06-19 08:00 | 2017-06-22 17:00 | N | N | replace cross arms and insulators | Line |  | replace cross arms and insulators | Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 3.4TR (ENMAX 3) | 2017-06-19 08:00 | 2017-06-30 16:00 | N | N | diff relay replacement | Transformer |  |  | For Information Only
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2017-06-19 08:00 | 2017-06-23 16:00 | N | N | investigate and repair leak (east pole) | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 14.4TR (ENMAX 14) | 2017-06-19 08:00 | 2017-06-23 16:00 | N | N | doble and maintenance | Transformer |  |  | For Information Only
ATCO | 848s 902T (848s Ruth Lake) | 2017-06-19 08:00 | 2017-06-23 17:00 | N | Y | transformer maintenance | Transformer |  | transformer maint, all load transferred to 901T | 240 kV, Over/Under Voltage
ENMAX | 21.1TR (ENMAX 21) | 2017-06-19 08:00 | 2017-06-25 16:00 | N | N | LTC maintenance and replace LV bushing gaskets | Transformer |  |  | For Information Only
ALTALINK | 38s T3 (38s East Edmonton) | 2017-06-19 09:00 | 2017-06-23 19:30 | N | N | install new pile for switch gear riser structure | Transformer |  |  | For Information Only
ALTALINK | 611L (391S Balzac - 186s Dry Creek) | 2017-06-19 10:00 | 2017-06-19 12:00 | N | N | repair hubell sleeves with star clamps | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | NamaoT1 (Namao),Namao N721 (Namao),Namao N722 (Namao) | 2017-06-19 10:00 | 2017-06-19 17:00 | N | N | substation switching for training purposes | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2017-06-19 10:30 | 2017-06-21 14:00 | N | Y | replace failed capacitors | Shunts |  |  | Pre-Condition, 500 kV
ALTALINK | 74s C4 (74s Janet),74s 103 (74s Janet) | 2017-06-19 11:00 | 2017-06-27 17:00 | N | Y | breaker maintennace | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 1005L (120s Picture Butte - 356s Milo),356s 252 (356s Milo),356s 152 (356s Milo) | 2017-06-19 11:00 | 2017-06-22 17:00 | N | Y | SCADA equipment upgrade | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek) | 2017-06-19 12:00 | 2017-06-19 14:00 | N | N | repair hubell sleeves with star clamps | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 411s T1 (411s Obed) | 2017-06-19 12:30 | 2017-06-19 17:00 | N | N | tight JB control cables | Transformer |  |  | Firm Load Loss, For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2017-06-19 15:00 | 2017-06-20 18:00 | N | Y | align with 1201L outage | Line | Peak RC Path Outage ID Peak RC Outage ID: |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2017-06-19 15:00 | 2017-06-20 18:00 | Y | Y | repair broken jumpers | Line | Peak RC COS # (W-E): 1-00489958 Peak RC COS # (E-W): 1-00489959 |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK | 433L (291s Cochrane - T793s Horse Creek) | 2017-06-20 06:30 | 2017-06-20 17:00 | N | N | kick insulators on structures 40-41 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CN10 (987s Clover Bar - Namao),987s CN723 (987s Clover Bar),Namao N724 (Namao) | 2017-06-20 07:00 | 2017-07-07 17:00 | N | N | degassing | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 707s 701T (707s St. Paul) | 2017-06-20 07:30 | 2017-06-22 16:30 | N | N | repair oil leak to CT junction box | Transformer |  | Repair Oil Leak to CT Junction Box, 707S Load will be fed from 702T for Duration of outage | For Information Only
ALTALINK | 668L (394s Empress - 562s Cypress),AltaLink Radio Tower | 2017-06-20 08:00 | 2017-06-20 17:00 | N | N | 668L MPLS/TPR - upgrade the 7705 MPLS Node A, B and C at 562s Cypress | Terminal Equipment, Line |  | Netcom will be upgrading the 7705 MPLS Node A, B and C at 562 Cypress. Similarly, during this upgrade, SPV 835, TPR 149 (ATCO), TPR 833 and TPR 834 will be out of service for 1 hour, one channel at a time. TPR 1011 will be out for 2 hours one channel at a time. TPR 832 will out of service. There could be PW_FAIL alarms on the lines during the upgrade. 394s upgrade will be happening at the same time with the upgrade. | Affects Visibility, Firm Load Loss, Creates Radial Feeds
ALTALINK | 755L (535s Joffre - 247s Piper Creek),247s 755E (247s Piper Creek) | 2017-06-20 08:00 | 2017-06-20 17:00 | N | N | breaker maintenance 138kV SF6 HGF | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 411S Obed,975s T1 (975s Dalehurst),745A1L (975s Dalehurst - 745L tap),745AL (745AL - 745L tap),745AL (411s Obed - 745AL4),745L (39s Bickerdike - 602s Cold Creek) | 2017-06-20 08:00 | 2017-06-20 12:00 | N | N | component/insulator replacement, create Open Point 'A', 975s T1 doble, maintenance work | Line, Transformer, Station |  | component/insulator replacement, create Open Point 'A'. 975s: T1(TX18073) doble, OBG2 leak, relay maintenance; OCR maintenance, battery/battery charger maintenance | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L75 (Revelstoke - Ashton Creek) | 2017-06-20 09:00 | 2017-06-23 17:00 | N | Y | ACK 5CB6 inspection and Doble test, 5D25 and 5D1CB8 inspections | Line |  | ACK 5CB6 inspection and Doble test, 5D25 and 5D1CB8 inspections - BC maintenance does not affect AB ATC | For Information Only
ALTALINK | 411S Obed,745AL (411s Obed - 745AL4) | 2017-06-20 12:01 | 2017-06-23 08:30 | N | N | component replacement, 745AL4 switch adjustment | Line, Station |  |  | Firm Load Loss, For Information Only
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2017-06-20 19:00 | 2017-06-21 20:00 | N | N | forced outage due to conductor damage | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 776L (410s Josephburg - 308s Albchem Beaverhill Creek) | 2017-06-20 21:08 | 2017-06-22 16:02 | N | N | forced outage | Line |  |  | Firm Load Loss
Saskpower | Sask Power S1C line | 2017-06-21 06:00 | 2017-06-21 19:00 | N | Y | TransCanada Keystone Herbert want to be isolated | Line |  |  | Limits ATC
ENMAX | 34.1TR (ENMAX 34),34.4TR (ENMAX 34) | 2017-06-21 07:00 | 2017-06-21 12:00 | N | N | take measurements for CT install. | Transformer |  | Take measurements for CT install. Bus Outage Required - must coordinate with U of C | For Information Only
ALTALINK | 352S Onoway,123L (19s Wabamun - 352s Onoway) | 2017-06-21 07:00 | 2017-06-21 19:00 | N | N | installing 471s & MR1 and replacing 352s20 | Station, Line |  |  | Pre-Condition, For Information Only
ALTALINK | 83s C1 (83s Taber),83s 61 (83s Taber) | 2017-06-21 07:30 | 2017-06-22 17:30 | N | N | replace faulty gas valve on 83s61 | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 873s 601T (873s Marion Lake) | 2017-06-21 08:00 | 2017-07-07 12:00 | N | N | 601T maintenance, bkr 601 replacement, all load onto 750s | Circuit Breaker |  | 601T maint., Bkr 601 Replacement, all load onto 750s | For Information Only
ATCO | 7L159 (7L16 - 948s Heatburg) | 2017-06-21 08:00 | 2017-06-22 12:00 | N | N | Isolated, four structures down - forced outage | Line |  | 770s, 768s, 114s, and 948s on radial feed, all 703T load at 770s will be transferred to 701T, 703T L/A replacement, 704 & 703 Partial PM's | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 156BL (165s T.M.P.L.Gainford - 156L tap),165S T.M.P.L. Gainford | 2017-06-21 08:30 | 2017-06-21 14:30 | N | N | transformer maintenance and maintain 165s18. | Line, Terminal Equipment |  |  | For Information Only
ALTALINK | 104s T1 (104s Watson Creek) | 2017-06-21 08:30 | 2017-06-21 13:30 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO | 749s 701T (749s Flyingshot Lake),749s 706 (749s Flyingshot Lake),749s 701 (749s Flyingshot Lake) | 2017-06-21 09:00 | 2017-06-21 17:00 | N | N | 706B repairs, 701T oos. | Transformer, Circuit Breaker |  | 706B repairs, 701T OOS for Oil Top up, 25KV load transferred to 702T, 144KV ring open Repair hot spot on 706B, Top up 701T conservator, Top up 701CT; Partial main. 706 | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2017-06-21 09:00 | 2017-06-28 15:00 | N | N | 7L40 x-arm / insulator replacement | Line |  | 7L40 X-arm / Insulator Replacement approximately 170 cross-arms to replace | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 2L112 (Nelway - Boundary) | 2017-06-21 09:00 | 2017-06-22 17:00 | N | Y | gas relay and protection maintenance - BC maintenance does not affect AB ATC | Line |  |  | Limits ATC
ATCO | 827s 702T (827s Cranberry Lake) | 2017-06-21 11:00 | 2017-06-22 15:00 | N | N | major testing on 702T | Transformer |  | TRANSFORMER CLASS2 MAJOR TESTING Major Testing on 702T at 827S Cranberry Lake Transfer all Load onto 701T/501VR | For Information Only
ALTALINK | 165s T1 (165s T.M.P.L.Gainford),165s 156 (165s TMPL Gainford) | 2017-06-21 14:30 | 2017-06-22 17:30 | N | N | transformer maintenance | Circuit Breaker, Transformer |  |  | Firm Load Loss, For Information Only
ALTALINK | 510s ACF21 (510s Sunnybrook) | 2017-06-21 14:30 | 2017-06-23 17:30 | N | Y | replace failed capacitors | Shunts |  |  | 500 kV
ALTALINK | 352s T1 (352s Onoway) | 2017-06-21 19:00 | 2017-07-10 08:00 | N | N | replacing 352s123 and upgrading line protection | Transformer |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34) | 2017-06-22 07:00 | 2017-06-22 12:00 | N | N | take measurements for CT install | Transformer |  |  | For Information Only
EPCOR | 1056L (Argyll - Bellamy) | 2017-06-22 07:00 | 2017-07-06 17:00 | N | Y | steel pole refurbishment | Terminal Equipment |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2017-06-22 12:00 | 2017-06-22 18:00 | N | N | repair leaning pole | Line |  |  | Firm Load Loss, Creates Radial Feeds
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2017-06-22 13:30 | 2017-06-22 13:45 | N | N | high load move | Line |  |  | For Information Only
ALTALINK | 924L (102s Langdon - 356s Milo) | 2017-06-22 15:11 | 2017-06-29 07:00 | N | Y | forced outage, damaged conductors | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 365S Canadian Oxyastotin Creek | 2017-06-23 08:00 | 2017-06-27 18:00 | N | N | transformer and breaker maintenance | Station |  |  | For Information Only
ENMAX | 31.1C (ENMAX 31),138-31.CAP (ENMAX 31) | 2017-06-23 08:00 | 2017-06-23 16:00 | N | N | weed removal | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 411S Obed,745AL (411s Obed - 745AL4) | 2017-06-23 08:31 | 2017-06-23 12:30 | N | N | close Open Point 'A' | Line, Station |  |  | Firm Load Loss, For Information Only
BCH | 2L294 (Cranbrook - Nelway) | 2017-06-23 09:00 | 2017-07-11 17:00 | N | Y | BCH- replace end-of-life insulators and install arcing horns - BC maintenance does not affect AB ATC | Line |  |  | Pre-Condition
ALTALINK, EPCOR | 1059AL (52s East Industrial - 1059L tap),1059L (38s East Edmonton - 803s Lambton) | 2017-06-23 16:45 | 2017-06-23 17:00 | N | N | de-energize 1059L to allow EPCOR to open EDS1 | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 11 B138-11.82 (ENMAX 11),ENMAX 14 14B138-11.82 (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2017-06-24 08:00 | 2017-06-25 16:00 | N | N | SF6 gas sample 14B138-11.82 (HVB), breaker inspection 14B138-11.82 and 11B138-11.82 (re-tye o/h shield wire, replace cracked insulators | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.1TR (ENMAX 24) | 2017-06-24 08:00 | 2017-06-24 16:00 | N | N | investigate issues with breaker racking mechanism and control circuit | Transformer |  |  | For Information Only
ALTALINK | 575s T1 (575s Sundre) | 2017-06-24 10:00 | 2017-06-24 12:00 | N | N | check individual CT contributions to bus protection for loose connections, insulation failures or grounds | Transformer
ALTALINK | 719L (575s Sundre - 719L135W),575s 719X (575s Sundre) | 2017-06-24 10:00 | 2017-06-24 12:00 | N | N | check individual CT contributions to bus protection for loose connections, insulation failures or grounds | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (575s Sundre - 378s Shell Caroline),575s 719N (575s Sundre) | 2017-06-24 13:00 | 2017-06-24 15:00 | N | N | check individual CT contributions to bus protection for loose connections, insulation failures or grounds | Circuit Breaker, Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 575s T2 (575s Sundre) | 2017-06-24 15:00 | 2017-06-24 17:00 | N | N | check individual CT contributions to bus protection for loose connections, insulation failures or grounds | Transformer
ATCO | 2029s 1207 (2029s Heathfield) | 2017-06-24 23:15 | 2017-06-27 17:00 | N | N | bad coil trip (forced outage) | Circuit Breaker |  |  | 240 kV
STROBE | 240S McBride Lake | 2017-06-26 | 2017-07-14 23:59 | N | N | repair high voltage cables on feeder L21 | Station |  |  | For Information Only
EPCOR | 816s P2406 (816s Petrolia) | 2017-06-26 07:00 | 2017-06-30 17:00 | N | Y | CT replacement and maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 739L (14s Devon - 305s Acheson) | 2017-06-26 07:30 | 2017-06-29 17:30 | N | N | install new structure, move 739L to new bay at 305s | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 305s C1 (305s Acheson),305s T1 (305s Acheson),739L (14s Devon - 305s Acheson),305s Acheson 138 kV Bus 1 | 2017-06-26 07:30 | 2017-06-26 17:30 | N | N | re-install new bus clamps for bus 1 | Shunts, Transformer, Bus, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 798s 701T (798s Bridge Creek) | 2017-06-26 08:00 | 2017-06-28 16:00 | N | Y | 701T Transformer maintenance, transfer load to 902s | Transformer |  | 701T Transformer maintenance, Transfer load to 902S | Restricts Generation
ENMAX | 21.2TR (ENMAX 21) | 2017-06-26 08:00 | 2017-06-30 16:00 | N | N | LTC maintenance (reinhausen type 3-D1 400) | Transformer |  |  | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2017-06-26 08:00 | 2017-06-30 16:00 | N | N | doble | Transformer |  |  | For Information Only
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2017-06-26 08:00 | 2017-06-29 17:00 | N | N | replace cross arms and insulators | Line |  | replace cross arms and insulators | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20) | 2017-06-26 08:00 | 2017-07-07 16:00 | N | N | TR bushing/CT replacement and 138kV bus DIFF relay replacement | Transformer |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2017-06-26 08:00 | 2017-06-27 16:00 | N | N | HV breaker inspection 28B138-1.80 | Line, Circuit Breaker |  | HV Breaker Inspection 28B138-1.80 (HPF - 2 Day Outage) | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 848s 704T (848s Ruth Lake),7L71 (848s Ruth Lake - 2082s Dog Rib) | 2017-06-26 08:00 | 2017-06-29 17:00 | N | N | 704T maintenance and major testing | Transformer, Line |  | 704T Maintenance and major testing | Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2017-06-26 10:30 | 2017-06-28 17:30 | N | Y | replace failed capacitors | Shunts |  |  | 500 kV
ALTALINK | 700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2017-06-26 23:23 | 2017-06-27 18:00 | N | N | forced outage | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 526AL (638s Esso Judy Creek - 526L tap),526L(526L367 - 526L220) | 2017-06-27 07:30 | 2017-06-28 17:30 | N | N | maintenance on structure 366 and 365 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm) | 2017-06-27 09:00 | 2017-06-27 12:00 | N | Y | netcom will be upgrading the radios and MPLS on 603L and 608L | Line |  |  | Restricts Generation
ALTALINK | 608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm) | 2017-06-27 13:00 | 2017-06-27 16:00 | N | Y | wiring changes, commissioning and function testing | Line |  | Wiring changes, commissioning and function testing involving the tying in of new 608L B TPR equipment into existing 608L line protections and breaker control C60 modules from 138S Windy Flats to 418S Ardenville. | Restricts Generation
ALTALINK | RATD 214s2047W advice | 2017-06-27 14:45 | 2017-06-27 15:45 | N | Y | 214s2047W - functional testing of new protection trips | Terminal Equipment |  |  | Restricts Generation, For Information Only
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),ENMAX 3 B138-3.84 (ENMAX 3),ENMAX 13 B138-3.84 (ENMAX 13) | 2017-06-28 08:00 | 2017-06-29 16:00 | N | N | doble 3B138-3.84 and inspect 13B138-3.84 | Line, Circuit Breaker |  |  | Overload, Creates Radial Feeds
ALTALINK | 765L (74s Janet - 151s Strathmore),151s 765W (151s Strathmore) | 2017-06-28 13:00 | 2017-06-28 17:00 | N | N | replace trip coil 2 | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s T2 (275s Jenner),275s Jenner 240kV Bus 2 | 2017-06-28 16:30 | 2017-06-30 18:00 | N | Y | remove temporary 25kV cable; 240kV protection testing and final bus installation at 275s47 and 275s2252; cutting over 240kV trip ccts. to new 25kV breaker | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 927L (102s Langdon - 356s Milo) | 2017-06-29 07:30 | 2017-06-29 17:30 | N | Y | emergency repairs | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 287S Hazelwood | 2017-06-29 10:00 | 2017-08-21 09:00 | N | N | close open points & connect 287s (RATD) | Station |  |  | For Information Only
ALTALINK | 420L (214s Innisfail - 287s Hazelwood) | 2017-06-29 11:00 | 2017-10-20 08:00 | N | N | connect new 420L | Line
ALTALINK | 214s T1 (214s Innisfail),80L (63s Red Deer - 214s Innisfail),214s Innisfail 138kV Bus 1 | 2017-06-29 11:00 | 2017-07-27 10:00 | N | N | connect new 419L bay & replace and install protections & cut free 80L | Bus, Line, Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 305s 739X (305s Acheson) | 2017-06-29 17:00 | 2017-10-03 08:00 | N | N | keep 305s739X breaker under GOI new 446L ready to be connected and breaker renamed | Circuit Breaker
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2017-06-30 15:00 | 2017-06-30 18:00 | N | N | to connect 746L tap | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36) | 2017-07-01 08:00 | 2017-07-01 18:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 15.1TR (ENMAX 15),15.60L (ENMAX 21 - ENMAX 15) | 2017-07-02 08:00 | 2017-07-02 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.2TR (ENMAX 15),15.62L (ENMAX 15 - ENMAX 16) | 2017-07-02 12:00 | 2017-07-02 16:00 | N | N | substation washing | Line, Transformer
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2017-07-02 18:48 | 2017-07-06 16:00 | N | N | forced outage | Line |  | water leak in valve hall. | 500 kV
EPCOR | 987s T1 (987s Clover Bar) | 2017-07-03 07:00 | 2017-07-12 17:00 | N | Y | doble | Transformer |  |  | 240 kV, Firm Load Loss
EPCOR | Meadowlark T1 (Meadowlark) | 2017-07-03 07:00 | 2017-07-07 17:00 | N | N | doble | Transformer
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27) | 2017-07-03 08:00 | 2017-07-03 12:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.2TR (ENMAX 16),16.60L (ENMAX 34 - ENMAX 16),16.63L (ENMAX 16 - ENMAX 36) | 2017-07-03 12:00 | 2017-07-03 16:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred T3 (Syncrude Mildred Lake),Mildred 13.8 kV Bus 3 (Syncrude Mildred lake) | 2017-07-04 07:00 | 2017-07-13 20:00 | N | N | 5 year PM | Transformer, Bus |  |  | For Information Only
ALTALINK | 394s T1 (394s Empress) | 2017-07-04 08:00 | 2017-07-13 10:00 | N | N | connect new buswork and VR1 | Transformer |  |  | For Information Only
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2017-07-04 08:00 | 2017-07-05 10:00 | N | N | damaged transmission pole | Line |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3) | 2017-07-04 08:00 | 2017-07-07 16:00 | N | N | LTC & transformer maintenance | Transformer
ATCO | 7L92 (7L92D3 - 7L92D4) | 2017-07-04 08:00 | 2017-07-06 17:00 | N | N | replace cross arms and insulators | Line |  | replace cross arms and insulators | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2017-07-04 08:00 | 2017-07-04 16:00 | N | N | maintenance on 14.2 cap and 14CS138-14.2CAP circuit switcher | Shunts |  | Capacitor Bank maintenance 14.2CAP. Circuit Switcher Maintenance 14CS138-14.2CAP | For Information Only
ALTALINK | 1041L (370s North Lethbridge - 554s Travers) | 2017-07-04 12:30 | 2017-07-04 17:30 | N | N | emergency structure repairs (str177) | Line |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 650s 752 (650s Hansman Lake) | 2017-07-04 12:30 | 2017-07-04 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 827s 701T (827s Cranberry Lake) | 2017-07-04 13:00 | 2017-07-06 15:00 | N | N | major testing on 701T and 501VR | Transformer |  | Major Testing on 701T and 501VR, Equipment is for emergency only - no load being carried | For Information Only
EPCOR | RossdaleT2 (Rossdale) | 2017-07-05 07:00 | 2017-07-11 07:59 | N | N | retrofit | Transformer |  |  | For Information Only
EPCOR | Poundmaker T3 (Poundmaker) | 2017-07-05 07:00 | 2017-07-07 17:00 | N | Y | tapchanger maintenance | Transformer |  |  | For Information Only
ALTALINK | 1036L (554s Travers - 356s Milo) | 2017-07-05 07:30 | 2017-07-06 17:30 | N | Y | emergency structure repairs | Line |  | Emergency structure repairs (str23, 45, 61, 123) | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 38.1C (ENMAX 38) | 2017-07-05 08:00 | 2017-07-06 16:00 | N | N | Cap bank maintenance | Shunts |  |  | For Information Only
ATCO | 2011s 901T (2011s Dawes) | 2017-07-05 14:00 | 2017-07-06 18:00 | N | N | forced outage | Transformer |  |  | 240 kV
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton),71s 761W (71s Lamoureux) | 2017-07-06 07:30 | 2017-07-11 17:30 | N | N | replacing structures to accommodate road intersection widening | Line, Switch |  |  | Overload, Contingency Requires Mitigation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),15B69-15.62 (ENMAX 15),16B69-15.62 (ENMAX 16) | 2017-07-06 08:00 | 2017-07-07 16:00 | N | N | HV breaker inspection, tower inspection on 15.62L | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 770S Threehills | 2017-07-06 08:00 | 2017-07-07 16:30 | N | N | RTU/HMI update and testing | Station |  | 770S Three Hills - RTU/HMI Update and Testing, Update RTU/HMI Configs, Test with STG. Loss of control and visibility while downloading (~1-2 mins) | Affects Visibility
ATCO | 802S Michichi Creek | 2017-07-06 08:00 | 2017-07-07 16:30 | N | N | RTU/HMI update and testing | Station |  | 802S Michichi RTU/HMI Update and Testing, Update RTU/HMI Configs, Test with STG. Loss of control and visibility while downloading (~1-2 mins) July 06 -07 2017 (08:00 to 16:30) | Affects Visibility
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2017-07-06 08:30 | 2017-07-06 17:00 | N | Y | breaker maintenance | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake),63s 648 (63s Red Deer) | 2017-07-06 08:30 | 2017-07-06 15:00 | N | N | breaker maintenance 138kV DTI Alstom | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 732s 703 (732s Mitsue),732s 707 (732s Mitsue),7L23 (732s Mitsue - 858s Narrows Creek),732s 144kV bus (732s Mitsue),7L23D4 (732s Mitsue) | 2017-07-06 09:00 | 2017-07-06 15:00 | N | N | 703PT testing and repairs | Line, Bus, Switch, Circuit Breaker |  | 703PT Emergency testing, repairs, and replacement if necessary, Phase C PT is measuring 20% below normal and may cause protection misoperation. | Contingency Requires Mitigation, Creates Radial Feeds
AESO-SC | DFS Network | 2017-07-06 17:00 | 2017-07-06 19:00 | N | N | this change is to make the underlying structure of DFS compatible with the new storage operating system | SCInternal |  |  | For Information Only
EPCOR | 330P 12TC1 (330p Genesee),330p 805 (330p Genesee) | 2017-07-07 07:00 | 2017-07-08 17:00 | N | Y | tapchanger maintenance | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2017-07-07 07:00 | 2017-07-19 17:00 | N | Y | steel pole refurbishment | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2017-07-07 07:30 | 2017-07-08 12:58 | N | N | emergency structure repairs | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2017-07-08 08:00 | 2017-07-08 12:00 | N | N | transmission line washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.81L (ENMAX 2 - ENMAX 9),ENMAX 9 B138-2.81 (ENMAX 9) | 2017-07-08 08:00 | 2017-07-08 16:00 | N | N | HV breaker inspection and SF6 gas sample | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2017-07-08 12:00 | 2017-07-08 17:00 | N | N | transmission line washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 330P 12TC2 (330p Genesee) | 2017-07-09 07:00 | 2017-07-09 17:00 | N | Y | tap changer maintenance | Transformer |  |  | Contingency Requires Mitigation, 500 kV
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2017-07-09 08:00 | 2017-07-09 17:00 | N | N | transmission line washing | Line |  |  | For Information Only
ATCO | 789s 701R (789s Keg River) | 2017-07-10 07:00 | 2017-07-17 18:00 | N | N | commission 705 protection and CT's and commission 705 breaker | Shunts |  | Commission 705 protection and CT's and commission 705 breaker. Go to 789S Keg River K Stage 5 SLD (701R is being renamed 705R) | For Information Only
EPCOR | 72JW19 (805s Jasper - Woodcroft),805s J724 (805s Jasper) | 2017-07-10 07:00 | 2017-07-11 17:00 | N | N | doble | Circuit Breaker, Line |  |  | Pre-Condition
EPCOR | 511s Victoria T1 (511s Victoria) | 2017-07-10 07:00 | 2017-07-12 17:00 | N | N | tapchanger maint | Transformer |  |  | For Information Only
EPCOR | 803s L2404 (803s Lambton) | 2017-07-10 07:00 | 2017-07-14 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 796L (282s Grassland (Alpac) - 796L28) | 2017-07-10 07:30 | 2017-07-14 16:30 | N | Y | maintenance | Line |  |  | Pre-Condition, Restricts Generation
ALTALINK | 916L (42s Sarcee - 5s East Calgary),42s 916E (42s Sarcee) | 2017-07-10 07:30 | 2017-07-13 16:30 | N | Y | 240kV breaker maintenance (42s916E) and 916L line structure maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 6L02 (765s Mannix Mine - 757s Battle River) | 2017-07-10 08:00 | 2017-07-13 17:00 | N | N | change a H frame structure in between the box and 6L02D2 | Line |  | Change a H Frame Structure in between the Box and 6L02D2 GOI to change out poles | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.1TR (ENMAX 36) | 2017-07-10 08:00 | 2017-07-14 16:00 | N | N | doble. DGA HV bushings | Transformer |  |  | For Information Only
ENMAX | 24.2TR (ENMAX 24) | 2017-07-10 08:00 | 2017-07-11 16:00 | N | N | LTC maintenance (Reinhausen Type RMV II) | Transformer |  |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2017-07-10 08:00 | 2017-07-10 12:00 | N | N | install dev 90 PT ground | Transformer |  |  | For Information Only
ATCO | 2075s SVC1 (2075s Newell) | 2017-07-10 08:00 | 2017-07-12 16:00 | N | Y | SVC1 GLYCOL PUMP REPAIR @ NEWELL 2075S remove failed pump and replace with new pump. There are no system constraints. SVC2 will be available and there is no affect to 13L50. | Shunts |  | SVC1 GLYCOL PUMP REPAIR @ NEWELL 2075S remove failed pump and replace with new pump. There are no system constraints. SVC2 will be available and there is no affect to 13L50. | 240 kV
ENMAX | 31.1TR (ENMAX 31) | 2017-07-10 08:00 | 2017-07-22 16:00 | N | N | TR Bushing/CT replacement TR diff relay replacement | Transformer |  |  | For Information Only
ALTALINK | 352S Onoway,123L (19s Wabamun - 352s Onoway) | 2017-07-10 08:00 | 2017-07-10 19:00 | N | N | removing 471s & MR1 | Line, Station |  |  | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34),21B69-21.61 (ENMAX 21),34B69-21.61 (ENMAX 34) | 2017-07-10 08:00 | 2017-07-13 16:00 | N | N | HV breaker inspection 34B69-21.61 & 21B69-21.61, SF6 gas sample 21B69-21.61, Doble 34B69-21.61 | Line, Circuit Breaker |  |  | For Information Only
ENMAX | ENMAX 35 B138-82 (ENMAX 35),ENMAX 35 B138-81 (ENMAX 35),ENMAX 35.1TR (ENMAX 35) | 2017-07-10 08:00 | 2017-07-10 16:00 | N | N | (SWCRR) initial energization of 35.1TR | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 786L (799s Coleman - Natal) | 2017-07-10 09:00 | 2017-07-21 18:00 | N | Y | AltaLink line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 184s T3 (184s Petro-Canada Edmonton) | 2017-07-10 09:30 | 2017-07-13 17:30 | N | N | bushing replacement - 138 kV & 13.8 kV | Transformer |  |  | For Information Only
ALTALINK | 275s T1 (275s Jenner),275s Jenner 240kV Bus 1 | 2017-07-10 09:30 | 2017-07-11 19:00 | N | Y | 240kV protection testing and final bus installation at 275s2152 and 275s39 | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 142s C1 (142s Magcan),727L (678s Okotoks - 142s Magcan - 65s High River) | 2017-07-10 10:00 | 2017-08-01 17:00 | N | N | line protections & settings changes as part of Okotoks project | Line, Shunts |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 678s T2 (678s Okotoks),678s Okotoks 138kV Bus 2 | 2017-07-10 10:00 | 2017-08-01 17:00 | N | N | remove motor from 678s33, install & commission 678s452 & 678s 1652 breakers, install 678s58 & 678s59 switches, salvage 678s44, replace 349LN, 2181L & AMI UG cables, replace SS2, install T2 slip-on CT's, install UG cables to 25kV bus 4 | Bus, Transformer |  |  | For Information Only
ENMAX | 10.2TR (ENMAX 10) | 2017-07-10 12:00 | 2017-07-10 16:00 | N | N | install dev 90 PT ground | Transformer |  |  | For Information Only
ALTALINK | 163s T2 (163s Amoco Empress) | 2017-07-10 12:15 | 2017-07-21 16:15 | N | Y | maintenance | Transformer |  | Fix Oil leaks on Tx18482 T2, change out SS2, change out bus CT's on X and Y center phases. | 240 kV, For Information Only
ALTALINK | 719L (256s Harmattan - 719L135X) | 2017-07-11 07:00 | 2017-07-14 18:00 | N | Y | structure move for road widening, structure replacement, install/commission new A/B | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 35 B138-80 (ENMAX 35),ENMAX 35 B138-83 (ENMAX 35) | 2017-07-11 08:00 | 2017-07-11 16:00 | N | N | (SWCRR) Initial energization of 35.2TR | Circuit Breaker |  |  | For Information Only
ALTALINK | 523s T2 (523s Bullshead) | 2017-07-11 08:00 | 2017-07-13 16:00 | N | N | closing open point 'A' and installing bird coverup on 25kV equipment | Transformer |  |  | For Information Only
ENMAX | ENMAX 35.1TR (ENMAX 35) | 2017-07-11 08:00 | 2017-07-12 12:00 | N | N | 35.1TR final commissioning checks | Transformer |  |  | For Information Only
EPCOR | RossdaleT2 (Rossdale) | 2017-07-11 08:00 | 2017-08-13 18:00 | N | N | retrofit | Transformer |  |  | Pre-Condition
ATCO | 725s 701T (725s Goose River) | 2017-07-11 08:00 | 2017-07-11 16:00 | N | N | change the taps and seal some leaks | Transformer |  | 725S GOOSE RIVER To change the taps and seal some leaks. | For Information Only
ALTALINK | 428s T1 (428s Namaka) | 2017-07-11 09:00 | 2017-07-13 17:00 | N | N | fix oil leaks on T1 Tx18578 | Transformer |  |  | For Information Only
ATCO | 720s 501R (720s Wabasca),720s 901T (720s Wabasca),720s 502R (720s Wabasca),720s 504R (720s Wabasca) | 2017-07-11 10:00 | 2017-07-12 13:00 | N | Y | GOI to sample bushings and set up oil processor | Shunts, Transformer |  | GOI to Sample bushings and set up Oil Processor 25 KV reactors out of service for duration of outage | For Information Only
ALTALINK | 760L (394s Empress - 163s Amoco Empress),394s 760N (394s Empress) | 2017-07-11 11:00 | 2017-07-11 14:00 | N | N | trip test to commission modified control circuits | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 668L (394s Empress - 562s Cypress),394s 668 (394s Empress) | 2017-07-11 14:30 | 2017-07-11 17:00 | N | N | trip test to commission modified control circuits | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 557s 2405 (557s Castle Downs) | 2017-07-12 07:00 | 2017-07-13 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 35.2TR (ENMAX 35) | 2017-07-12 08:00 | 2017-07-13 12:00 | N | N | 35.2TR final commissioning checks | Transformer |  |  | For Information Only
ATCO | 940s 701T (940s Beartrap) | 2017-07-12 08:00 | 2017-07-12 12:00 | N | N | inspect 701T NGR | Transformer |  | Inspect 701T NGR, 3L226 load transferred to 302 (3L231), Transfer AC Stn Service to Alternate supply, momentary customer outage reqd -------- Load Transfer -------- 940S 3L226 Peak Load = 4.91 MVA 940S 3L231 Peak Load = 5.37 MVA 940S 3L226 Relay Settings: No IPS data available, asses real time 940S 3L231 Relay Settings: No IPS data available, asses real time -------- Load Transfer -------- | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2017-07-12 08:00 | 2017-07-14 16:00 | N | N | LTC maintenance Fed Pioneer | Transformer |  |  | For Information Only
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2017-07-12 08:00 | 2017-07-13 16:00 | N | N | 7L68 outage for 7L10 mitigation | Line |  | 7L68 outage for 7L10 mitigation | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 940s 702T (940s Beartrap) | 2017-07-12 12:00 | 2017-07-12 16:00 | N | N | inspect 702T NGR | Transformer |  | Inspect 702T NGR, 3L231 load transferred to 301 (3L226), Transfer AC Stn Service back to Normal supply, momentary customer outage reqd -------- Load Transfer -------- 940S 3L231 Peak Load = 5.37 MVA 940S 3L226 Peak Load = 4.91 MVA 940S 3L231 Relay Settings: No IPS data available, asses real time 940S 3L226 Relay Settings: No IPS data available, asses real time -------- Load Transfer --------
EPCOR | 511s Victoria T1 (511s Victoria) | 2017-07-13 07:00 | 2017-07-14 17:00 | N | N | tapchanger maint | Transformer |  |  | Pre-Condition, Overload
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek) | 2017-07-13 09:00 | 2017-07-13 16:00 | N | N | upgrading 186s Dry creek and 199s MPLS node | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2017-07-13 10:00 | 2017-07-13 12:00 | N | Y | MW radio 9356R - 338s upgraded | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 805s J2404 (805s Jasper),805s J2403 (805s Jasper),E805sJDS25 (Jasper) | 2017-07-14 07:00 | 2017-07-14 17:00 | N | N | JDS25 disconnect repair | Switch, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
Medicine Hat | MH69s2 MH69_206 (MH69s2 North Industrial),MH69s2 MH69-T21(North Industrial substation) | 2017-07-14 07:00 | 2017-07-14 16:00 | N | N | final bus connection for the new 10L and for 16L | Transformer, Circuit Breaker |  | On July 14, 2017 the City of Medicine Hat Electric Distribution will be taking an outage on MH-2S - West 69 kV bus. The equipment included as part of the outage is: Transformer T-21 Disconnect Switch  MH69-205 & MH69-204 Circuit Breakers  MH69-206 Scheduled outage durations: Start time = 07:00 Friday July 14, 2017 End time = 16:00 Friday July 14, 2017 Scope of work: To complete the final bus connection for the new 10L and for 16L | For Information Only
SUNCOR | 29EDD-71 752_4622 (29EDD-71),29EDD-71 752_4621 (29EDD-71),29PT-234 (29EDD-71) | 2017-07-14 08:00 | 2017-08-11 20:00 | N | Y | inspection and maintenance | Circuit Breaker, Transformer |  |  | Pre-Condition, Restricts Generation
ATCO | 827s SVC (827s Cranberry Lake) | 2017-07-14 10:00 | 2017-07-14 13:00 | N | Y | replace thyristor air filters | Shunts |  |  | Pre-Condition, For Information Only
ATCO | 789S 706C | 2017-07-14 10:00 | 2017-07-14 13:00 | N | N | test the electrical interlock between breakers 705 and 706, which requires operation of 706 | Terminal Equipment |  | While 701R (to be renamed to 705R) is OOS (refer to GOI 2-41950), Commissioning needs to test the electrical interlock between breakers 705 and 706, which requires operation of 706. 706C will be unavailable for dispatch. | For Information Only
EPCOR | E511s VictoriaT3 (511s Victoria) | 2017-07-15 07:00 | 2017-07-17 17:00 | N | N | tapchanger maintenance | Transformer |  |  | For Information Only
MONTANA | 120s 1152 (120s Picture Butte),120s C1 (120s Picture Butte) | 2017-07-15 08:00 | 2017-08-04 16:00 | N | Y | forced outage | Circuit Breaker, Shunts |  |  | 240 kV, For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 138 kV North Bus | 2017-07-15 08:00 | 2017-07-18 16:00 | N | Y | new construction, remove bus piece, SW91 and 162RB138-RB85 will remain out-of-service on return | Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7) | 2017-07-15 08:00 | 2017-07-15 12:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7) | 2017-07-15 12:00 | 2017-07-15 16:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24),ENMAX 24 B138-24.81 (ENMAX 24) | 2017-07-16 08:00 | 2017-07-16 16:00 | N | N | doble | Line, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 139S Hillridge | 2017-07-17 06:00 | 2017-07-17 18:00 | N | Y | customer requested perform protection system maintenance and testing. | Station |  |  | Restricts Generation
ALTALINK | 719L (575s Sundre - 719L135W) | 2017-07-17 07:00 | 2017-07-22 18:00 | N | Y | install/remove temp bypass to facilitate install/commission new A/B | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale R72C2 (Rossdale) | 2017-07-17 07:00 | 2017-07-21 17:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2017-07-17 08:00 | 2017-07-19 16:00 | N | N | 138kV bus diff / auto switching upgrade | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2017-07-17 08:00 | 2017-07-19 16:00 | N | Y | move pole and extend guys on 138kv for contractor | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 47.1TR (ENMAX 47) | 2017-07-17 08:00 | 2017-07-21 17:30 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2017-07-17 08:00 | 2017-07-18 16:00 | N | N | HV breaker inspection (HLC). SF6 gas sample 21B69-15.60 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 826s 901T (826s Marguerite Lake) | 2017-07-17 08:00 | 2017-07-20 16:00 | N | Y | routine maintenance on 901T | Transformer |  | Routine Maintenance on 901T, 902T will remain in service, 502R 20 MVAR reactor unavailable for dispatch | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2017-07-17 08:00 | 2017-07-20 17:00 | N | N | replace cross arms and insulators | Line |  | replace cross arms and insulators | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 434s T3 (434s East Stony Plain),739L (305s Acheson - 434s Stony Plain) | 2017-07-17 09:00 | 2017-07-17 17:45 | N | N | replace 138kV insulators on 739L associated with breaker 434s739E | Transformer, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 500s T1 (500s Flatbush) | 2017-07-17 09:30 | 2017-07-20 19:00 | N | N | add 3rd PT for metering, PT junction box and move SS1 to new location | Transformer |  |  | For Information Only
ATCO, ALTALINK | 7L230 (7L230 tap - 743s Sarah Lake),7L230 (69s North Barrhead - 7L230 tap),888L (234s Fort Assiniboine - 7L230 tap) | 2017-07-17 10:30 | 2017-07-17 17:30 | N | Y | switch maintenance - 234s2 | Line |  |  | Pre-Condition
ATCO | 876s 902T (876s Brintnell) | 2017-07-17 13:00 | 2017-07-20 15:00 | N | Y | manufacturer upgrade | Transformer |  | 3 Phase Tap changer, Manufacturer upgrade, 902T. All Load to be carried on 901T and 501VR | 240 kV
BLACKSPRING | 485S Black Springs | 2017-07-18 06:00 | 2017-07-19 19:00 | N | Y | sub annual maintenance | Station |  |  | Restricts Generation
ALTALINK | 434s T1 (434s East Stony Plain),739L (434s Stony Plain - 739L216A),434s Stony Plain 138kV Bus 1 | 2017-07-18 07:15 | 2017-07-18 17:45 | N | N | replace 138kV insulators | Line, Bus, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 754L (118s Canmore - 437s Baymag) | 2017-07-18 07:30 | 2017-08-23 15:30 | N | Y | structure replacements | Line |  |  | Pre-Condition, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 186s C1 (186s Dry Creek),186s 17 (186s Dry Creek) | 2017-07-18 07:30 | 2017-07-27 17:30 | N | N | removing trips from 186s17 and transferring them to the new 186s652 | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 215L (38s East Edmonton - 286s Yasa),38s 215N (38s East Edmonton) | 2017-07-18 07:30 | 2017-07-18 17:30 | N | N | repair CT leak | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 234s T1 (234s Fort Assiniboine) | 2017-07-18 08:00 | 2017-07-18 17:30 | N | N | transformer maintenance | Transformer
ALTALINK | 186s T2 (186s Dry Creek),611L (391S Balzac - 186s Dry Creek) | 2017-07-18 08:00 | 2017-07-18 14:00 | N | N | installing new 186s VT6 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 745L (602s Cold Creek - 745L482) | 2017-07-18 08:00 | 2017-07-19 16:00 | N | N | replace C phase 602s4 CVT7 & secondary cable | Line |  |  | Firm Load Loss, Creates Radial Feeds
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2017-07-18 09:30 | 2017-07-18 09:45 | N | N | high load move | Line |  |  | For Information Only
ALTALINK | 275s T3 (275s Jenner),601L (275s Jenner - 230s Wardlow) | 2017-07-18 13:00 | 2017-07-18 17:00 | N | N | functional testing 275s83 | Transformer, Line
ALTALINK | 574s T2 (574s Nilrem) | 2017-07-18 15:00 | 2017-07-19 17:00 | N | Y | forced outage | Transformer |  |  | 240 kV, For Information Only
ENMAX | 162s 138-RB85 (162s Beddington) | 2017-07-18 16:00 | 2017-08-23 16:00 | N | N | new construction, breaker and bus outage to install new transformer bay | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 434s T1 (434s East Stony Plain) | 2017-07-19 07:15 | 2017-07-21 17:45 | N | N | replace 25kV insulators | Transformer |  | Replace 25kV insulators on both sides of 434s9, incomer to the 25kV structure, 481L insulators at the structure, & 210L insulators at the structure | For Information Only
ALTALINK | 234s T2 (234s Fort Assiniboine) | 2017-07-19 08:00 | 2017-07-19 17:30 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO | 813s SVC (813s Little Smoky) | 2017-07-19 09:00 | 2017-07-20 17:00 | N | Y | SVC maintenance | Shunts |  | SVC maintenance, SVC not available for dispatch | Pre-Condition
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2017-07-19 17:00 | 2017-07-20 12:00 | N | N | vegetation (emergency outage) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2017-07-20 08:00 | 2017-07-22 16:00 | N | N | 138kV bus diff / auto-switching upgrade and HV breaker inspection | Line, Transformer |  |  | Overload, Contingency Requires Mitigation
ATCO | 7L574 (822s Wolf Lake - 7L574 tap) | 2017-07-22 07:00 | 2017-07-23 17:30 | N | Y | 7L587/7L86 temp bypass construction @ 822s Wolf Lake | Line |  | 7L587/7L86 temp bypass construction @ 822s Wolf Lk, 859s Primrose will be radial fed from 970s Bourque, 1200s Cenovus will be radial tied to 7L587 via 144kV bus at 822s Wolf Lk | Creates Radial Feeds
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),47.2 TR (ENMAX 47) | 2017-07-22 07:00 | 2017-07-23 17:30 | N | N | install piles for bus supports at 162 Sub | Line, Transformer
ENMAX | ENMAX 47 | 2017-07-22 07:00 | 2017-07-23 17:30 | N | N | LTC maintenance | Station |  |  | For Information Only
ENMAX | 918L (281s Johnson - 162s Beddington) | 2017-07-22 08:00 | 2017-07-22 16:00 | N | Y | doble PT 918 & RB133 | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2017-07-22 08:00 | 2017-07-22 17:00 | N | N | repair 31MD138-31.1TR (cracked harp) | Line, Shunts, Transformer |  |  | Pre-Condition
AESO-SC | ENMAX back up activation | 2017-07-22 15:00 | 2017-07-23 11:00 | N | N | planned activation | Terminal Equipment |  |  | For Information Only
EPCOR | 987S Cloverbar | 2017-07-22 19:00 | 2017-07-23 07:00 | N | Y | customer support | Station |  |  | Restricts Generation, For Information Only
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2017-07-23 08:00 | 2017-07-23 16:00 | N | N | doble 12B138-832 | Line, Circuit Breaker |  |  | Creates Radial Feeds
EPCOR | 987S Cloverbar | 2017-07-23 18:00 | 2017-07-24 07:00 | N | Y | customer support | Station |  |  | Restricts Generation, For Information Only
EPCOR | 805s C1 (805s Jasper),805s J2408 (805s Jasper) | 2017-07-24 07:00 | 2017-07-28 17:00 | N | Y | maintenance | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker) | 2017-07-24 07:00 | 2017-07-27 17:00 | N | Y | doble | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L587 (826s Marguerite Lake - 822s Wolf Lake) | 2017-07-24 07:00 | 2017-07-25 17:30 | N | Y | attach 7L587/7L86 temp bypass to 7L587 | Line |  | Attach 7L587/7L86 Temp Bypass to 7L587, 1200s Cenovus, 822s Wolf Lk, and 859s Primrose will be radial fed via 7L574, With 7L587 OOS Cenovus Load RAS will be armed to operate if 7L86 import is > 20MW and 822s 144kV voltage <130kV for 5 cycles. | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L64 (779s Chinchaga River - 789s Keg River) | 2017-07-24 07:00 | 2017-07-27 17:00 | N | Y | reroute 7L64 from 789s old to 789s new substation, | Line |  | Reroute 7L64 from 789s old to 789s new substation, 747s, 748s, and 779s will be radial fed from 930s Arcenciel | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 186s T1 (186s Dry Creek),631L (199s East Airdrie - 186s Dry Creek) | 2017-07-24 07:00 | 2017-07-25 18:00 | N | N | testing of relay trips | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2017-07-24 07:30 | 2017-07-24 17:30 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s T1 (39s Bickerdike) | 2017-07-24 07:30 | 2017-07-30 17:30 | N | Y | replacing bushings | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 36.2TR (ENMAX 36) | 2017-07-24 08:00 | 2017-08-01 16:00 | N | N | bushing/CT and differential relay replacement | Transformer |  | TR Bushing/CT replacement. TR DIFF Relay Replacement | For Information Only
SUNCOR | 29EDD-34 952_132 (29EDD-34),29EDD-34 952_133 (29EDD-34),29EDD-34 652_10201 (29EDD-34),29EDD-34 652_10202 (29EDD-34),29EDD-34 29PS-372 (29EDD-34),29PT-340 (29EDD-34),29EDD-34 29PS-378 (29EDD-34),29EDD-34 29PS-376 (29EDD-34) | 2017-07-24 08:00 | 2017-08-22 17:00 | N | Y | project 1716 - switching | Transformer, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 826s 902T (826s Marguerite Lake) | 2017-07-24 08:00 | 2017-07-27 16:00 | N | Y | routine maintenance on 902T | Transformer |  | Routine Maintenance on 902T, 901T will remain in service, 503R, 504R 20 MVAR reactors unavailable for dispatch, Stn service will be on 5L263 alternate source | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ENMAX | 28.4TR (ENMAX 28) | 2017-07-24 08:00 | 2017-07-25 16:00 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2017-07-24 08:00 | 2017-07-26 16:00 | N | N | LTC maintenance | Transformer |  | LTC Maintenance. Transformer Maintenance. Check Reversing SW | For Information Only
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12),ENMAX 12 B138-833L (ENMAX 12) | 2017-07-24 08:00 | 2017-07-26 16:00 | N | Y | HV breaker inspect (Day 2-3) & doble (day 1) | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T2 (65s High River) | 2017-07-24 08:45 | 2017-07-24 14:15 | N | N | repair 65s15 | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome),89s 1052 (89s Ellerslie),89s 1152 (89s Ellerslie) | 2017-07-24 10:30 | 2017-07-24 16:30 | N | Y | replace insulator on bus.89s1052 will remain out of service for maintenance. | Line, Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 373s T1 (373s Madden) | 2017-07-24 11:00 | 2017-07-24 15:00 | N | N | replace temperature probe well on top of the tapchanger | Transformer |  | Urgent: The tap changer is leaking profusely and needs to be addressed as soon as possible. Replace temperature probe well on top of the tapchanger. | For Information Only
SUNCOR | 29EDD-34 652_10201 (29EDD-34),29EDD-34 652_10202 (29EDD-34),29EDD-34 29PS-372 (29EDD-34),29PT-340 (29EDD-34),29EDD-34 29PS-378 (29EDD-34),29EDD-34 29PS-376 (29EDD-34) | 2017-07-24 12:01 | 2017-08-22 18:00 | N | Y | project 1716 | Circuit Breaker, Transformer, Switch |  | "Work associated with AESO approved Project 1716 - Suncor Plant 300HV . This is to modify a portion of 72kV system in order to offload 29EDD-56 to 29EDD-34 and 29EDD-200. Installation of 2 circuit breaters at 29EDD-34 is required. July 11th, 2017 - equipment below associated with the transformer high side of MOD 29PS-372 for isolation only. One MOD PS-372 has been opened the equipment listed below will be immediately brought back into service. " CVT 29PT-342 " breaker 29-952-133 with Isolating switches 29PS-371 & 29PS-224 " breaker 29-952-132 with Isolating switches 29PS-223 & 29PS-370. " CT-29-952-132 " CT-29-952-133 The following equipment will be out of service for the duration of the work. 260kV " Transformer 29PT-340 " High side 260kV surge arresters " MOD 29PS-372 72kV " 29-652-10201 with Isolating motorized switch 29PS-378 " breaker 29-652-10202 with Isolating motorized switches 29PS-376 & 29PS-377 " CVT 29PT-344 " CVT 29PT-346 " NGR- 29PR-67 " XFMR LV side 72kV surge arresters " | 240 kV, For Information Only
ATCO | 809s 902T (809s Louise Creek),809s 702 (809s Louise Creek) | 2017-07-24 13:00 | 2017-07-27 15:00 | N | Y | maintenance | Transformer, Circuit Breaker |  | Maintain 902T/Tapchanger and 702 Bkr, Load Carried on 901T and breaker 701 | 240 kV, For Information Only
ALTALINK | 89s 1052 (89s Ellerslie) | 2017-07-24 16:30 | 2017-07-27 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 730L (285s East Camrose - 730L62) | 2017-07-24 20:00 | 2017-07-26 19:00 | N | N | forced outage | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 212S Lacombe,423L (212s N.E.Lacombe - 332s Ellis),80AL (958s West Lacombe - 212s N.E Lacombe) | 2017-07-25 07:15 | 2017-07-25 17:30 | N | N | remove 212s189 interlock (RATD) | Line, Station |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2017-07-25 07:30 | 2017-07-27 17:30 | N | N | contamination monitoring program | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake),157s 794X (157s Lac La Biche) | 2017-07-25 07:30 | 2017-08-14 13:30 | N | Y | connect new T2 and 157s652 and new construction on 25 kV bus | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2017-07-25 08:00 | 2017-07-26 16:00 | N | N | TR bushing/CT replacement and diff relay replacement | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 943L (13s Deerland - 108s Amelia) | 2017-07-25 09:00 | 2017-07-27 14:00 | N | Y | replace 13s49 CVT (like for like) | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 186s C1 (186s Dry Creek),186s T2 (186s Dry Creek),611L (391S Balzac - 186s Dry Creek),186s Dry Creek 138kV Bus 2 | 2017-07-25 18:00 | 2017-07-27 18:00 | N | N | testing of relay trips | Shunts, Bus, Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s 1 (62s Brazeau) | 2017-07-25 23:00 | 2017-07-27 07:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 62s 2 (62s Brazeau) | 2017-07-26 01:00 | 2017-07-26 05:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 80L (331s Ponoka - 958s West Lacombe) | 2017-07-26 08:00 | 2017-08-30 18:00 | N | N | salvage | Line |  |  | For Information Only
ALTALINK | 716L/80L (40s Wetaskiwin - 958s West Lacombe) | 2017-07-26 08:00 | 2017-08-30 16:00 | N | N | salvage | Line
SUNCOR, ATCO | 6L32 (29EDD-1 Millennium - 737s Horseshoe),29EDD-1 29EDD1S1352 (29EDD-1),29EDD-1 29EDD1S1252 (29EDD-1) | 2017-07-26 08:00 | 2017-07-29 17:00 | N | N | maintenance on lighting arrestor 29PLA185 B&C | Circuit Breaker, Line |  | Atco has requested to perform work on 6L32. To support this work Suncor is required to operate breaker 29EDD1S1352. Suncor will be taking opportunity during the Atco work to perform maintenance on lighting arrestor 29PLA185 A, B & C
ENMAX | 21.1C (ENMAX 21),ENMAX 21 B138-21.CAP (ENMAX 21) | 2017-07-26 08:00 | 2017-07-28 16:00 | N | N | cap bank maintenance and doble circuit switcher | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 1036L (554s Travers - 356s Milo),1041L (370s North Lethbridge - 554s Travers) | 2017-07-26 09:00 | 2017-07-26 13:00 | N | Y | firmware upgrade for the MW radio between 120S Picture Butte and 554S Travers | Line |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation
ATCO | 822s 702 (822s Wolf Lake),822s 703 (822s Wolf Lake),7L574 (822s Wolf Lake - 7L574 tap) | 2017-07-26 10:00 | 2017-08-03 14:00 | N | Y | install new 700PT2 bus PT @ 822s | Circuit Breaker, Line |  | Install new 700PT2 bus PT @ 822s, 7L86 will be radial tied to 7L587 and bypass 822s, Primrose will be radial fed from 970s via 7L574 | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ATCO | 822s 701T (822s Wolf Lake) | 2017-07-26 11:00 | 2017-09-05 17:00 | N | N | replace 701TCS @ 822s with 704A and 704 | Transformer |  | Replace 701TCS @ 822s with 704A and 704, 7L587 will be open ended @ 822s when GOI is expanded to include 700BS1 Aug 8-16. Jul 26 (2-36721A) - Isolate 701T between 501TD and 701TCS Aug 8 (2-36721B) - Expand/Isolate 701T and 700BS1 between 501TD, 700D1, 7L587D2, 700PT1 secondaries @ 822s to install 704A Aug 16-Sep 5 (2-36721C) - Shrink/Isolate 701T between 704A and 501TD @ 822s to remove 701TCS/install 704 | For Information Only
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),ENMAX 39 B138-39.82 (ENMAX 39) | 2017-07-27 | 2017-07-28 05:00 | N | N | low SF6 - emergency | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 150L (42s Sarcee - 150L47),3L (42s Sarcee - 272s Springbank) | 2017-07-27 07:15 | 2017-08-19 18:45 | N | N | SWCRR: relocate to new alignment on ROW, set structures and string | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2017-07-27 08:00 | 2017-08-01 16:00 | N | N | DGA & transformer maintenance | Transformer
ALTALINK | 511s 4852 (511s Crossings) | 2017-07-27 08:00 | 2017-07-27 09:00 | N | Y | security maintenance for CIP compliance | Circuit Breaker |  | Security maintenance for CIP compliance: Password change on 4852 96/25/4852 breaker failure relay.A breaker outage is required to complete the password change as there is a 5 second period where the protection may not be available for breaker failure.Relay: 4852 96/285/4852 6MD66. | 240 kV
ENMAX | ENMAX 65 B138-D81 (ENMAX 65) | 2017-07-27 08:00 | 2017-07-27 12:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 80L (214s Innisfail - 55s Olds),80L (63s Red Deer - 214s Innisfail) | 2017-07-27 10:01 | 2017-08-30 18:00 | N | N | salvage | Line |  |  | For Information Only
ENMAX | ENMAX 65 B138-D82 (ENMAX 65) | 2017-07-27 12:00 | 2017-07-27 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 631L (199s East Airdrie - 186s Dry Creek),186s 652 (186s Dry Creek),186s Dry Creek 138kV Bus 1 | 2017-07-27 20:30 | 2017-07-28 02:00 | N | N | repair a broken switch 186s4 - emergency,repair a broken switch 186s4 - emergency | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds
AESO-SC | Phone Outage | 2017-07-27 22:00 | 2017-07-27 23:00 | N | N | TransALta Hydro Control Center recorded phones short outage | SCInternal |  |  | For Information Only
ATCO | 797s 701T (797s Kemp River),7L62 (789s Keg River - 797s Kemp River) | 2017-07-28 07:00 | 2017-08-01 12:00 | N | Y | reroute line into new Keg River substation | Line, Transformer |  | Reroute line into new Keg River substation, modify 7L62D3 from DLO to LS/LD Work Sequence - transfer 5L457 to adjacent sub - Issue GOI 2-33607A (Isol. pts - 702A, 7L62D2, 7L62PTX @ 789s, 7L62D4, 701TD1 @ 797s) - line work, modify 7L62D3 - Plains Midstream outage reqd - Collapse GOI to 7L62D3 @ 797s - issue 2-33607B, then release 2-33607A - re-energize 797s - restore 5L457 external load transfer to normal - continue 7L62 line reroute into 789s | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | 1098L (805s Jasper - Poundmaker) | 2017-07-28 07:00 | 2017-07-28 17:00 | N | Y | doble | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2017-07-29 08:00 | 2017-07-30 16:00 | N | N | install new risers for 5.7TR, doble test & breaker inspection | Line, Transformer |  |  | Pre-Condition
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41) | 2017-07-29 08:00 | 2017-08-05 16:00 | N | N | (FATDSC) remove temporary jumpers, re-terminate into 41s, update line protection | Line |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 5L72 (Mica Creek - Nicola) | 2017-07-30 23:00 | 2017-08-13 22:00 | N | Y | doble - BC maintenance does not affect AB ATC | Line | Peak RC#: 1-00502103, 1-00502104 Peak RC outage ID: 1-00500645 |  | Limits ATC, 500 kV
EPCOR | Poundmaker T2 (Poundmaker) | 2017-07-31 07:00 | 2017-08-04 17:00 | N | Y | doble | Transformer |  |  | 240 kV
EPCOR | NamaoT2 (Namao) | 2017-07-31 07:00 | 2017-08-04 17:00 | N | N | maintenance | Transformer |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
EPCOR | 511s Victoria T1 (511s Victoria) | 2017-07-31 07:00 | 2017-08-22 17:00 | N | N | TX protection upgrade | Transformer |  |  | Pre-Condition, Creates Radial Feeds
EPCOR | 72RW3 (Rossdale - Woodcroft),Rossdale RW727 (Rossdale) | 2017-07-31 07:00 | 2017-08-04 17:00 | N | N | doble | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 39s T2 (39s Bickerdike) | 2017-07-31 07:30 | 2017-08-03 12:30 | N | Y | replacing bushings | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2017-07-31 07:30 | 2017-08-01 17:30 | N | N | contamination monitoring program | Line |  |  | Overload, Contingency Requires Mitigation
ENMAX | 16.1TR (ENMAX 16) | 2017-07-31 08:00 | 2017-08-02 16:00 | N | N | investigate arcing / buzzing sounds on secondary / 8kV bus | Transformer
ENMAX | 37.1TR (ENMAX 37) | 2017-07-31 08:00 | 2017-08-04 16:00 | N | N | doble | Transformer
ALTALINK | 186s T1 (186s Dry Creek) | 2017-07-31 09:30 | 2017-08-01 18:00 | N | N | testing of relay trips | Transformer
BCH | 2L293 (Selkirk - Nelway) | 2017-07-31 10:00 | 2017-08-01 13:00 | N | Y | replace cracked and broken cross arms - BC maintenance does not affect AB ATC | Line | Peak COS ID: 1-00502106 , 1-00502109 Peak Outage ID: 1-00492720 |  | Limits ATC, For Information Only
ALTALINK | 710L (159s Colinton - 56s Boyle) | 2017-07-31 10:00 | 2017-07-31 15:00 | N | N | emergency crossarm replacement | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 1152 (89s Ellerslie) | 2017-07-31 10:30 | 2017-08-03 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 68s T2 (68s Willesden Green) | 2017-07-31 13:00 | 2017-08-01 16:00 | N | Y | investigate oil leak | Transformer |  |  | 240 kV
ALTALINK | 678s 452 (678s Okotoks),678s 552 (678s Okotoks),678s 352 (678s Okotoks) | 2017-08-01 | 2017-08-02 | N | N | in-service date: August 1, 2017 | Circuit Breaker
ALTALINK | 186s 652 (186s Dry Creek) | 2017-08-01 | 2017-08-02 16:00 | N | N | in-service-date: August 1, 2017 | Circuit Breaker
Syncrude | Aurora 11 (Aurora),Aurora T3 (Aurora) | 2017-08-01 07:00 | 2017-08-15 20:00 | N | Y | replace 72kV isolating disconnects (11B and 12A) | Transformer, Circuit Breaker |  | Transformer # T3, G01 - SubStation at Aurora.will be disconnetced to replace 72kV isolating disconnects (11B and 12A). | Restricts Generation, For Information Only
ALTALINK | 678s 452 (678s Okotoks) | 2017-08-01 08:00 | 2017-08-01 16:00 | N | N | in-service-date: Aug 1, 2017 | Circuit Breaker |  |  | For Information Only
REDDEER, ALTALINK | 464L (87s Gaetz - 209s Timberlands),209s T1 (209s Timberlands),209s 768W (209s Timberlands),209s 464E (209s Timberlands),768L (217s North Red Deer - 209s Timberlands) | 2017-08-01 08:30 | 2017-08-01 15:30 | N | N | ABB protection relay binary input module RMA recall replacement | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 394s T1 (394s Empress) | 2017-08-01 08:30 | 2017-08-08 16:30 | N | N | install bird cover, swap AMI feed's between busses and close open point 'H' | Transformer | VR1 & 25kV Bus 1 GOI |  | For Information Only
ALTALINK | 523s T1 (523s Bullshead) | 2017-08-01 11:00 | 2017-08-01 17:00 | N | N | investigate chattering contact on 523s389 | Transformer |  |  | For Information Only
ALTALINK | 142s C1 (142s Magcan) | 2017-08-01 17:00 | 2017-08-11 16:00 | N | N | faulty air break switch | Shunts |  |  | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks),678s 850 (678s Okotoks) | 2017-08-02 07:30 | 2017-08-02 16:30 | N | N | tie in breaker fail initiates and trip testing to line breaker | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11) | 2017-08-02 08:00 | 2017-08-11 16:00 | N | N | TR bushing/CT replacement. TR diff relay replacement | Transformer |  |  | For Information Only
ENMAX | 162s 138_RB94 (162s Beddington) | 2017-08-02 08:00 | 2017-08-03 16:00 | N | N | transport new 162.3TR into 162sub yard | Circuit Breaker |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2017-08-02 08:00 | 2017-08-04 16:00 | N | N | LTC maintenance | Transformer
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek) | 2017-08-02 08:00 | 2017-08-02 17:00 | N | N | reframe dead-end and install inter-phase spacers | Line |  | reframe dead-end and install inter-phase spacers | Pre-Condition
ATCO | 6L54 (736s Valleyviewp.R.O.P.L. - 734s Sturgeon),734s 601 (734s Sturgeon) | 2017-08-02 10:00 | 2017-08-02 16:00 | N | N | PCB oil samples | Line, Circuit Breaker |  | PCB Oil samples, 6L54 currently not carrying load | For Information Only
ALTALINK | 646L (678s Okotoks - 237s Foothills),678s 646 (678s Okotoks) | 2017-08-02 10:30 | 2017-08-02 16:30 | N | N | tie in breaker fail initiates and trip testing to line breaker | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2017-08-03 08:00 | 2017-08-03 12:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 1081L (17s Benalto - 281s Johnson),17s 3 (17s Benalto),17s 2 (17s Benalto) | 2017-08-03 08:00 | 2017-08-03 15:30 | N | Y | adjust 240kV switch (17s32) | Line, Circuit Breaker |  | Adjust 240kV switch(17s32), East and West phase out of adjustment. | 240 kV, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2017-08-03 12:00 | 2017-08-03 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 166s T3 (166s Dow Chemical Fort Saskatchewan),787L (166s Dow Chemical Fort Saskatchewan - 787L33),166s 787W (166s Dow Chem Fort Saskatchewan) | 2017-08-03 14:30 | 2017-08-03 16:30 | N | Y | energize new PT2 | Circuit Breaker, Transformer, Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker T2 (Poundmaker),Poundmaker PMDS3 (Poundmaker),Poundmaker PMDS6 (Poundmaker) | 2017-08-04 07:00 | 2017-08-04 17:00 | N | Y | doble | Transformer, Switch |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2017-08-04 07:30 | 2017-08-04 17:30 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 16.2TR (ENMAX 16) | 2017-08-04 08:00 | 2017-08-04 16:00 | N | N | urgent repair SW24 | Transformer
ALTALINK | 35s9 (35s Rundle) | 2017-08-04 08:00 | 2017-08-13 17:00 | N | Y | 35s2 breaker replacement | Switch |  | RU2 Bus outage for 35s2 breaker replacement | Restricts Generation
ALTALINK | 35S Rundle | 2017-08-04 08:00 | 2017-08-18 08:00 | N | Y | breaker 35s1, 35s3 & 35s4 replacement | Station |  | TAU request for RU1 Bus outage for breaker 35s1, 35s3 & 35s4 replacement. | Restricts Generation
ENMAX | 41.1C (ENMAX 41) | 2017-08-05 08:00 | 2017-11-18 12:00 | N | N | FATDSC construction, install new breaker - due to arrive in Sept (original breaker used at 14s) | Shunts |  |  | Pre-Condition, For Information Only
ENMAX | 41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41),41.84L (ENMAX 54 - ENMAX 41) | 2017-08-06 06:00 | 2017-08-06 14:00 | N | N | facilitate wiring changes for autoswitching relay install to set a streetlight. | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred T4 (Syncrude Mildred Lake) | 2017-08-07 07:00 | 2017-08-13 20:00 | N | N | 5Yr PM of transformer # 4, plant 31 substation | Transformer |  | 5Yr PM of Transformer # 4, Plant 31 substation Note: Generator G4 will be disconnected from 72kV bus. | Restricts Generation, For Information Only
ENMAX | 5.8TR (ENMAX 5) | 2017-08-07 08:00 | 2017-08-11 16:00 | N | N | LTC maintenance | Transformer |  | LTC maintenance. Network crew required to switch alternates | For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9),ENMAX 9 B138-9.83 (ENMAX 9),ENMAX 43 B138-9.83 (ENMAX 43) | 2017-08-07 08:00 | 2017-08-10 16:00 | N | N | line and breaker testing, inspection and maintenance | Line, Circuit Breaker |  |  | Overload, Contingency Requires Mitigation
BCH | 2L294 (Nelway - A.A. Lambert) | 2017-08-07 09:00 | 2017-08-18 17:00 | N | Y | maintenance | Line |  |  | Pre-Condition
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2017-08-08 07:00 | 2017-09-01 17:00 | N | Y | disconnect cabling and remove existing panel A10 then modify, update and test breakers and protection | Line |  | 9L70 and 901T will have single feed (240kV bus open) Scope of work " Disconnect cabling and remove existing panel A10 " Cutover prepped cabling in panel B10 " Complete Bkr and MOD control wiring. " Update 902/903 BF and 21B relay settings. " Test Breaker and MOD control " Relay testing. " Remove SEL 2506 and rewire at Tinchebray. " Relay testing at Tinchebray. " Test end to end teleprotection tripping to Tinchebray. " Remove 50TG CTs from 9L59PT and 902CT. | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | NamaoT3 (Namao) | 2017-08-08 07:00 | 2017-08-11 17:00 | N | N | doble | Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds, For Information Only
EPCOR | 805s J2401 (805s Jasper) | 2017-08-08 07:00 | 2017-08-11 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 7.2TR (ENMAX 7) | 2017-08-08 08:00 | 2017-08-08 16:00 | N | N | investigate why the 43 switch closed the breaker when being turned from off to local | Transformer |  |  | For Information Only
ATCO | 6L03 (6L17 tap - 757s Battle River),775s 603 (775s Sullivan Lake) | 2017-08-08 08:00 | 2017-08-10 16:00 | N | N | 775S BKR 603 min oil hlc complete testing | Line, Circuit Breaker |  | 775S BKR 603 MIN OIL HLC COMPLETE TESTING Bkr 603 Complete Maintenance 6L03 will be open ended | Pre-Condition, For Information Only
ATCO | 822s 701T (822s Wolf Lake),822s 701 (822s Wolf Lake),7L587 (826s Marguerite Lake - 822s Wolf Lake) | 2017-08-08 08:00 | 2017-08-16 17:00 | N | Y | replace 701TCS @ 822s with 704A and 704 | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 678s T3 (678s Okotoks) | 2017-08-08 09:00 | 2017-08-08 17:30 | N | N | connect T3 AMI risers & close open point 'E', install bird cover | Transformer |  | Connect T3 AMI risers & close open point 'E', and install bird cover. Tighten loose bolt on T3 corona ring on high side on T3. | For Information Only
ATCO | 800s 703C (800s Friedenstal),800s 703 (800s Friedenstal) | 2017-08-08 09:00 | 2017-08-08 16:00 | N | N | 800S 703 breaker SF6 hpl partial testing | Circuit Breaker, Shunts |  | 800S 703 BREAKER SF6 HPL PARTIAL TESTING 703C Out of service for the duration of the work | For Information Only
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2017-08-08 09:30 | 2017-08-08 17:00 | N | N | fix some down lead deficiencies | Line |  | fix some down lead deficiencies | Pre-Condition
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2017-08-08 10:00 | 2017-08-10 20:00 | N | Y | move 7L59 from 789s Old to 789s New, Melito radial fed from 786s | Line |  | Move 7L59 from 789s Old to 789s New, Melito radial fed from 786s | Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (746s Sherwood Park - 700L TAP),746s 700N (746s Sherwood Park) | 2017-08-08 10:30 | 2017-08-10 17:30 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 939s 904 (939s Livock) | 2017-08-08 11:00 | 2017-08-11 14:00 | N | Y | repair breaker 904 @ 939S Livock | Circuit Breaker |  | Repair Breaker 904 @ 939S Livock Repair and Top up Breaker 904. This Breaker has a long history of a slow leak. The Breaker is currently low and will need a top up for safe operation. We will be attempting a permanent repair during this outage which is why it cannot be done in one day. 240 KV Bus Open for duration of repair | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 525s 850N (525s Carseland),850L (525s Carseland - 678s Okotoks) | 2017-08-08 11:00 | 2017-08-10 16:00 | N | N | maintain 138kV breaker | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s T2 (17s Benalto),17s 85 (17s Benalto) | 2017-08-08 12:00 | 2017-08-10 16:00 | N | Y | maintain 17s85 138kV breaker | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ATCO | 939s 911 (939s Livock),939s 903T (939s Livock) | 2017-08-08 13:00 | 2017-08-08 16:00 | N | Y | top up breaker with SF6/CF4 | Transformer, Circuit Breaker |  | BKR 911 @ Livock was noted to be low during inspection. Top up breaker with SF6/CF4, Phase Shifting 903T will need to be by-passed. | 240 kV, Pre-Condition, For Information Only
ALTALINK | 394s T1 (394s Empress) | 2017-08-08 16:31 | 2017-10-10 08:00 | N | N | VR1 to remain out of service until 138kV portion of 394s project resumes in Sept | Transformer |  | Due to potential protection mis-coordination, VR1 to remain out of service until 138kV portion of 394s project resumes in Sept. | For Information Only
ALTALINK | 21s T1 (21s Marion) | 2017-08-09 07:30 | 2017-08-09 17:30 | N | N | transformer maintenance | Transformer
ATCO | 791s 601T (791s Rainbow Lake),791s 703T (791s Rainbow Lake) | 2017-08-09 08:00 | 2017-08-09 17:00 | N | N | remove u/grd cable between 601T and 14.4kV swgr @ 791s | Transformer |  | Remove u/grd cable between 601T and 14.4kV swgr @ 791s, RB3 will already be offline
ATCO | 7L85 (804s Wintering Hills - 803s Bullpound) | 2017-08-09 08:00 | 2017-08-09 17:00 | N | N | fix conductor #503 to #508 WO# E08814-85300 | Line |  | fix conductor #503 to #508 WO# E08814-85300 | Creates Radial Feeds
ALTALINK | 648s Metiskow RTU/SCADA | 2017-08-09 08:00 | 2017-08-09 15:00 | N | N | radio maintenance | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 678s 850 (678s Okotoks) | 2017-08-09 09:00 | 2017-08-09 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | For Information Only
ATCO | 886s 701T (886s Updike) | 2017-08-09 12:00 | 2017-08-10 13:00 | N | N | 886s Updike mobile sub setup | Transformer |  | 886S Updike Set Up Mobile Sub Set up mobile sub and attach J2 to 500D2 Energize mobile sub Phase across 500D2 Leave 902S energized
AESO-SC | Phone Outage,DFS Network | 2017-08-09 17:00 | 2017-08-09 21:00 | N | N | make the underlining infrastructure of DFS compatible with the new storage operating system | SCInternal |  |  | For Information Only
ALTALINK | 701L (395s North Holden - 223s Strome) | 2017-08-10 07:30 | 2017-08-10 17:00 | N | N | emergency repair span of o/h conductor | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
CNRL | 838s 75-BC-1911 (838s Horizon Mining),838s 75-BC-1912 (838s Horizon Mining),838s 75-BC-1913 (838s Horizon Mining),838s 75-BC-1914 (838s Horizon Mining),838s 75-BC-1915 (838s Horizon Mining),838s 75-BC-1916 (838s Horizon Mining),838s 75-BC-1917 (838s Horizon Mining),838s 75-BC-1918 (838s Horizon Mining) | 2017-08-10 08:00 | 2017-08-30 15:00 | N | Y | testing of 260kV circuit breakers | Circuit Breaker |  |  | 240 kV, For Information Only
BCH | 1L274 (Elkford - EFT1D22) | 2017-08-10 09:00 | 2017-08-10 17:00 | Y | Y | disconnect to be operated momentarily to complete commissioning for new control wiring to MOD terminals | Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 33 B138-33.84 (ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2017-08-11 08:00 | 2017-08-13 16:00 | N | N | spring transmission line washing, 138KV cable test and HV breaker works | Line, Circuit Breaker |  | Doble 33B138-33.84, Sheath Test & DGA on LPOF 138KV cable. Spring Transmission Line Washing Potheads. HV Breaker inspection (HLR) 43B138-33.84 & (SF6) 33B138-33.84. SF6 Gas RE-Sample (monitor due to previous poor results) | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L58 (789s Keg River - 905s Meikle) | 2017-08-12 07:00 | 2017-08-13 16:00 | N | Y | reroute 7L58 from 789s old to new substation | Line |  | Reroute 7L58 from 789s old to new substation | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RS5 (Rossdale - Strathcona),Strathcona S721 (Strathcona) | 2017-08-12 07:00 | 2017-08-12 17:00 | N | N | maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s 788N (157s Lac La Biche),788L (157s Lac La Biche - 788L Tap) | 2017-08-12 08:45 | 2017-08-12 10:15 | N | N | trip test from new 157s652 breaker fail protection | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 728L (353s Plamondon - 157s Lac La Biche),157s 728W (157s Lac La Biche) | 2017-08-12 10:16 | 2017-08-12 11:45 | N | N | trip test from new 157s652 breaker fail protection | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s C1 (157s Lac La Biche),157s23 (157s Lac La Biche) | 2017-08-12 12:45 | 2017-08-12 14:15 | N | N | trip test from new 157s652 breaker fail protection | Shunts, Switch |  |  | For Information Only
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2017-08-13 08:00 | 2017-08-23 16:00 | N | N | line protection upgrade | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2017-08-13 08:00 | 2017-08-13 16:00 | N | N | spring substation washing | Line, Transformer
BCH | 5L71 (Mica Creek - Nicola),5L72 (Mica Creek - Nicola) | 2017-08-13 21:00 | 2017-08-13 22:00 | N | Y | MCA black out, when the plant is restored, LS1 will be returned and LS2 will be isolated - BC maintenance does not affect AB ATC | Line | BC Peak RC COS#: 1-00501566 AB Peak RC COS# : 1-00504521 (W-E), 1-00504522 (E-W) |  | Limits ATC, 500 kV
BCH | 5L71 (Mica Creek - Nicola) | 2017-08-13 22:00 | 2017-08-16 22:00 | N | Y | doble testing on MCA 5CVT24 - BC maintenance does not affect AB ATC | Line | BC Peak RC COS#: 1-00501563 AB Peak RC COS# : 1-00504519 (W-E), 1-00504520 (E-W) |  | Limits ATC, 500 kV
ALTALINK | 157s T2 (157s Lac La Biche) | 2017-08-14 | 2017-08-15 16:00 | N | N | ISD Aug 14, 2017 | Transformer
EPCOR | 72NW15 (Namao - Woodcroft),Woodcroft W723 (Woodcroft) | 2017-08-14 07:00 | 2017-08-14 17:00 | N | N | maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred T1 (Syncrude Mildred Lake) | 2017-08-14 07:00 | 2017-08-20 20:00 | N | Y | 5 year PM of transformer #1 | Transformer |  | 5Yr PM of Transformer #1, Plant 31 substation | Restricts Generation
EPCOR | RossdaleT3 (Rossdale) | 2017-08-14 07:00 | 2017-09-15 17:00 | N | N | cable reconfig | Transformer |  |  | For Information Only
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2017-08-14 07:30 | 2017-08-17 17:30 | N | N | protection upgrade | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 678s T1 (678s Okotoks) | 2017-08-14 08:00 | 2017-08-14 14:00 | N | N | change CT wiring for HMI metering of T1 | Transformer |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2017-08-14 08:00 | 2017-08-22 16:00 | N | N | TR bushing/CT replacement and differential relay replacement | Transformer |  | TR Bushing/CT replacement. TR DIFF Relay Replacement | For Information Only
ENMAX | 33.1TR (ENMAX 33) | 2017-08-14 08:00 | 2017-08-18 16:00 | N | N | doble | Transformer |  |  | For Information Only
ATCO | 886s 701T (886s Updike) | 2017-08-14 08:00 | 2017-08-16 16:00 | N | N | maintenance | Transformer |  | Maintenance on 701T Transfer load from 902S to 701T | For Information Only
ENMAX | ENMAX 25 B240-D132 (ENMAX 25) | 2017-08-14 08:00 | 2017-08-14 12:00 | N | Y | SF6 sample | Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 39.4TR (ENMAX 39) | 2017-08-14 08:00 | 2017-08-18 16:00 | N | N | LTC maintenance (Reinhausen) | Transformer |  | LTC maintenance (Reinhausen). Transformer Maintenance. outage on 22.81L required | For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2017-08-14 08:00 | 2017-08-14 12:00 | N | N | replace three U-bolts (Valard) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11) | 2017-08-14 08:00 | 2017-08-28 08:00 | N | N | TR CT replacement, differential relay replacement, 11s reliability upgrade | Transformer |  | TR CT replacement. TR DIFF Relay Replacement. 11s reliability upgrade | For Information Only
ATCO | 9L93 (972s Tinchebray - 615s Halkirk) | 2017-08-14 09:00 | 2017-08-16 15:00 | N | Y | maintenance | Line |  | Capital power Corporation performing maintenance on our 89-T11 DS and 89G-T11 GS inside the Halkirk substation | 240 kV, Restricts Generation, For Information Only
ALTALINK | 746S Sherwood Park | 2017-08-14 09:30 | 2017-08-17 17:30 | N | N | 222X breaker maintenance | Station |  |  | For Information Only
ALTALINK | 940L (370s North Lethbridge - 120s Picture Butte) | 2017-08-14 09:30 | 2017-08-18 08:00 | N | Y | emerency structure repairs | Line |  |  | 240 kV, Pre-Condition
ENMAX | ENMAX 25 B240-D131 (ENMAX 25) | 2017-08-14 12:00 | 2017-11-12 16:00 | N | Y | SF6 sample, repair SW132 switch | Circuit Breaker |  | SW.132 inoperable. Must wait for an outage on 1GSU. Nov. 7-12. SW.132 left open until repairs can be made. | 240 kV, Pre-Condition
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2017-08-14 13:00 | 2017-08-17 17:00 | N | Y | arm change/ insulators | Line |  | Arm change/ insulators | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Lethbridge | 593s6 (593s Lethbridge Lakeview) | 2017-08-14 15:30 | 2017-08-16 16:00 | N | N | real-time request | Switch |  |  | For Information Only
Saskpower | Sask Power R1S line | 2017-08-15 06:00 | 2017-08-15 12:00 | N | Y | erecting bus in close proximity | Line |  |  | Limits ATC
ALTALINK | 213s T2 (213s Hughenden) | 2017-08-15 07:00 | 2017-08-22 18:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
EPCOR | Woodcroft W722 (Woodcroft) | 2017-08-15 07:00 | 2017-08-15 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Creates Radial Feeds, For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton),133s T2 (133s Stelco Edmonton) | 2017-08-15 08:00 | 2017-08-17 14:30 | N | N | customer work - 133s station advice for AltaSteel | Transformer |  |  | For Information Only
ALTALINK | 142s C1 (142s Magcan),727L (678s Okotoks - 142s Magcan - 65s High River) | 2017-08-15 08:30 | 2017-08-15 17:00 | N | N | repair 142s727ALN switch | Line, Shunts |  | Trouble corrective: Repair 142s727ALN switch | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 795s 701T (795s Zama),795s 701TCS (795s Zama) | 2017-08-15 09:00 | 2017-08-16 16:00 | N | N | 701T & 701TCS maintenance | Transformer, Switch |  | Complete 701T & 701TCS Maintenance, 701T & 501VR Out of Service for the Duration of the Work, Load transferred to 702T; N.O. 500D1 closed. | For Information Only
ALTALINK | 671L (58s Edson - 39s Bickerdike) | 2017-08-15 09:15 | 2017-08-15 14:45 | N | N | high load move | Line |  |  | Pre-Condition
ENMAX | 32B138-32BT5 (ENMAX 32) | 2017-08-15 12:00 | 2017-08-15 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | Creates Radial Feeds
ATCO | 6L11 (854s Swan Dive - 742s Freeman Lake) | 2017-08-15 13:00 | 2017-08-21 16:00 | N | N | mitigate line due to frosting area | Line |  | mitigate line due to frosting area BKR 602 will be replaced at 739S Edith Lake, 854S Swan Dive and 742S Freeman Lake will be radially fed from 743S Sarah Lake. | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 41s T11 (41s Medicine Hat) | 2017-08-16 05:30 | 2017-08-16 12:00 | N | N | emergency outage to repair hot disconnect | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 913L (69s North Barrhead - 732s Mitsue) | 2017-08-16 06:15 | 2017-08-16 17:15 | N | Y | emergency crossarm repairs | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | Woodcroft W721 (Woodcroft) | 2017-08-16 07:00 | 2017-08-16 17:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
ALTALINK | 35s T3 (35s Rundle) | 2017-08-16 07:30 | 2017-08-18 14:30 | N | Y | adjust 35s41 switch | Transformer |  |  | Restricts Generation
ALTALINK | 221S Sunken Lake,472L (648s Metiskow - 472AL tap),472AL (221s Sunken Lake - 648s Metiskow) | 2017-08-16 07:30 | 2017-08-16 14:00 | N | N | 221s15 , 221s16 and T3 prd micro switch fix | Station, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | Mobile Substation #3 | 2017-08-16 08:00 | 2017-08-16 16:00 | N | N | take down jumper J2 | Terminal Equipment |  | Take down jumper J2 | For Information Only
ALTALINK | 35s8 (35s Rundle) | 2017-08-16 08:00 | 2017-08-18 17:00 | N | Y | bus outage for breaker 35s1 & 35s4 replacement | Switch |  | TAU request for RU1 Bus outage for breaker 35s1 & 35s4 replacement. | Restricts Generation
ALTALINK | 421s C1 (421s Hays),421s T2 (421s Hays),421s Hays 138 kV Bus | 2017-08-16 09:00 | 2017-08-17 14:00 | N | N | 421s29 switch adjustment and 138kV SF6 breaker maintain, cap bank breaker & investigate densimeter | Bus, Transformer, Shunts |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 221s T1 (221s Sunken Lake) | 2017-08-16 14:00 | 2017-08-17 17:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 35s41 (35s Rundle) | 2017-08-16 14:00 | 2017-08-18 17:00 | N | Y | outage for breaker 35s1 & 35s4 replacement | Switch |  |  | Restricts Generation
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2017-08-17 07:00 | 2017-08-17 17:00 | N | N | doble CVTs | Line |  |  | Pre-Condition
ALTALINK | 170L (632s Russell - 799s Coleman) | 2017-08-17 07:15 | 2017-09-01 18:15 | N | Y | BCH structure replacements | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 723L (69s North Barrhead - 723L133) | 2017-08-17 07:15 | 2017-08-17 17:15 | N | N | emergency crossarm repairs | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 423L (212s N.E.Lacombe - 332s Ellis),80AL (212s N.E.Lacombe - 958s West Lacombe) | 2017-08-17 08:00 | 2017-08-17 17:00 | N | N | remove 212s189 interlock | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1C (ENMAX 21),ENMAX 21 B138-21.CAP (ENMAX 21) | 2017-08-17 08:00 | 2017-08-17 16:00 | N | N | HV breaker inspection | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 795s 702T (795s Zama),795s 702TCS (795s Zama) | 2017-08-17 09:00 | 2017-08-18 16:00 | N | N | 702T & 702TCS maintenance | Transformer, Switch |  | Complete 702T & 702TCS Maintenance, 702T Out of service for the duration of the work, Load transferred to 701T; N.O. 500D1 Closed | For Information Only
ALTALINK | 33s3 (33s Spray) | 2017-08-17 12:00 | 2017-08-17 17:00 | N | Y | remove lock out tags | Switch |  |  | Restricts Generation
CMH | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2017-08-18 06:00 | 2017-08-18 12:00 | N | N | tie in new OPGW fiber into new incoming A frame | Line |  |  | For Information Only
ENMAX | 1.81L (ENMAX 20 - ENMAX 1),ENMAX 20 B138-1.81 (ENMAX 20) | 2017-08-18 08:00 | 2017-08-18 16:00 | N | N | HV breaker inspection 20B138-1.81 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker T3 (Poundmaker) | 2017-08-19 07:00 | 2017-08-21 17:00 | N | Y | SFRA | Transformer |  |  | 240 kV, For Information Only
EPCOR | 665s TX2 (665s Dome) | 2017-08-19 07:00 | 2017-08-19 17:00 | N | Y | repair blown fuse | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 739L (434s Stony Plain - 739L216A) | 2017-08-19 07:30 | 2017-08-19 18:30 | N | N | SWEATD: install/remove aerial number boards between 434s Stony Plain and 105s Bilby. | Line |  | Install/remove aerial number boards between Stony Plain 434s and Bilby 105s as part of SWEATD line re-numbering | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2017-08-19 08:00 | 2017-08-19 16:00 | N | N | emergency bushing replacing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (432s Carvel - 739L214B) | 2017-08-20 07:30 | 2017-08-20 18:30 | N | N | install/remove aerial number boards as part of SWEATD line re-numbering | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),Hardisty H725 (Hardisty Epcor) | 2017-08-21 07:00 | 2017-08-21 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 14s T3 (14s Devon),739L (14s Devon - 305s Acheson),838L (14s Devon - 325s Leduc) | 2017-08-21 07:30 | 2017-08-24 17:30 | N | N | 739L protection upgrade, 14s30/14s44 switch repair | Line, Transformer | GM: 739L/838L/14s 138kV 1/2 Bus/T3 outage affecting 138kV Bus PT that requires to disable line protection on 739L (14s  155s) at 14s to prevent any unwanted tripping. For faults on 14s Devon end, 739L (14s -155s) will be tripped by 155s protection and the fault clearing time is around 27 cycles. (Please check the General internal Comments section) |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28) | 2017-08-21 08:00 | 2017-08-24 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ALTALINK | 925L (63s Red Deer - 74s Janet),929L (63s Red Deer - 74s Janet) | 2017-08-21 08:00 | 2017-09-14 09:00 | N | Y | RATD build and cut in new QQ towers for Hazelwood | Line |  |  | 240 kV, Pre-Condition
SUNCOR | 29EDD-34 Edd34Sub | 2017-08-21 08:00 | 2017-10-06 20:00 | N | Y | 5 year PM breakers, bus CT, switches | Station |  | 29EDD-34 Partial Outage/s (w/o affecting power flow in and out of 29EDD-34) - 260kV Buses for 5YR PMs - 260kV Breakers for 5YR PMs - Bus PTs and CTs for 5YR PMs - Bus CVTs for 5YR PMs - SSVTs for 5YR PMs - 260kV Disconnect Switches(incl. motorized) for 5YR PMs - 260kV Arrestors for 5YR PMs - 265/145(144)/13.8 kV Transformer for 5YR PMs - 144kV assets for 5YR PMs | 240 kV, For Information Only
SUNCOR | 29PL9-12 (29EDD-34 - 29EDD-65) | 2017-08-21 08:00 | 2017-09-01 20:00 | N | Y | 5 year maintenance | Line |  | 5 YR maintenance - from 29PS220 to 29PS-63 SLD - SL30-P-141-106 & SL30-P141-109 | 240 kV
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2017-08-21 08:00 | 2017-08-24 17:00 | N | N | change arms and insulators | Line |  | change arms and insulators, 804S and 803s radial fed from 7L85, RAS # 123 !!! | Firm Load Loss, Creates Radial Feeds
ATCO | 2029s 1201 (2029s Heathfield) | 2017-08-21 08:00 | 2017-08-24 14:00 | N | Y | 1201 breaker inspection | Circuit Breaker |  | 1201 breaker inspection - repair breaker wiring on 2 poles and confirm breaker operation and rewire damaged wires as necessary. | 500 kV
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2017-08-21 08:00 | 2017-08-21 12:00 | N | N | SF6 gas sample | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 746s T1 (746s Sherwood Park) | 2017-08-21 09:00 | 2017-08-24 18:00 | N | N | 25kV Bus 1 GOI for switch maintenance | Transformer |  |  | For Information Only
BCH | 5L92 (Cranbrook - Selkirk) | 2017-08-21 09:00 | 2017-08-26 10:30 | Y | Y | CBK 5CVT4 replacement - BC maintenance | Line | Peak RC COS: E-W>1-00505777 Peak RC COS: W-E>1-00505778 BC 5L92 Outage>1-00505412 |  | Limits ATC, 500 kV
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2017-08-21 12:00 | 2017-08-21 16:00 | N | N | SF6 gas sample | Line |  |  | For Information Only
ALTALINK | 776L (410s Josephburg - 308s Albchem Beaverhill Creek) | 2017-08-21 12:15 | 2017-08-21 15:45 | N | N | urgent repair - replace structures 127-128 | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 650s SVC (650s Hansman Lake),650s T3 (650s Hansman Lake) | 2017-08-21 13:00 | 2017-08-23 15:00 | N | Y | SVC maintenance | Shunts, Transformer |  |  | 240 kV, Pre-Condition
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2017-08-21 16:01 | 2017-09-22 12:00 | N | N | 739s602 breaker replacement | Line |  | BKR 602 will be replaced at 739S Edith Lake, 854S Swan Dive and 742S Freeman Lake will be radially fed from 743S Sarah Lake. | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 226S Garden City,891L (226s Garden City - 891L1) | 2017-08-22 06:00 | 2017-08-22 19:00 | N | Y | protection system maintenance and testing | Station, Line |  |  | Restricts Generation
EPCOR | 72CH9 (Hardisty - 987s Clover Bar),Hardisty H723 (Hardisty Epcor) | 2017-08-22 07:00 | 2017-08-22 17:00 | N | N | maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.84L (ENMAX 36 - ENMAX 7),ENMAX 36 B138-7.84 (ENMAX 36) | 2017-08-22 08:00 | 2017-08-22 12:00 | N | N | SF6 gas sample 36B138-7.84 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 237s 152 (237s Foothills) | 2017-08-22 08:00 | 2017-08-22 12:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 789s 706C (789s Keg River),7L58 (789s Keg River - 905s Meikle),789s 705R (789s Keg River) | 2017-08-22 08:00 | 2017-08-22 12:00 | N | Y | create jumper J2 on 700BS3 | Shunts, Line |  | Create jumper J2 on 144kV bus @ 789s, then remove temp bus between 700BS3 @ 789s New and 700 Bus 1 @ 789Ks Old and install new bus deadend structure, then close J2. 789Ks Old will be separated from the BES on completion. 705R and 706C will be OOS Aug 22-29, 7L58 will be open ended and 7L64 will be tied to 7L62 via bypass 7L62D2 for 2 4hr periods while opening and closing J2. | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s C1 (157s Lac La Biche),157s T1 (157s Lac La Biche),728L (353s Plamondon - 157s Lac La Biche),788L (157s Lac La Biche - 788L Tap) | 2017-08-22 09:00 | 2017-08-29 15:00 | N | N | 138 kV bus diff protection changes, upgrade to 25 kV equipment | Transformer, Shunts, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 2033s 704C (2033s Mowat) | 2017-08-22 09:00 | 2017-08-22 13:00 | N | N | painting equipment | Shunts |  | Painting equipment | For Information Only
ATCO | 789s 706C (789s Keg River),789s 705R (789s Keg River) | 2017-08-22 12:00 | 2017-08-29 12:00 | N | N | remove temporary bus between 700BS3 and 800B1 and install new bus dead-end structure | Shunts |  | Create jumper J2 on 144kV bus @ 789s, then remove temp bus between 700BS3 @ 789s New and 700 Bus 1 @ 789Ks Old and install new bus deadend structure, then close J2. 789Ks Old will be separated from the BES on completion. 705R and 706C will be OOS Aug 22-29, 7L58 will be open ended and 7L64 will be tied to 7L62 via bypass 7L62D2 for 2 4hr periods while opening and closing J2. | Pre-Condition
ALTALINK | 237s 252 (237s Foothills) | 2017-08-22 13:00 | 2017-08-22 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 6L06 (705s Kitscoty - 751s Hill),751s 602 (751s Hill) | 2017-08-23 07:30 | 2017-08-23 15:00 | N | N | demonstrating 602 breaker testing with new innovative test set | Line, Circuit Breaker |  | demonstrating 602 breaker testing with new innovative test set, 6L06 will be open ended @ 751s, 6L06 is not presently carrying load (hot emerg spare), system impact minimal. | Pre-Condition, For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington),162s Beddington 138 kV North Bus | 2017-08-23 08:00 | 2017-08-25 16:00 | N | Y | New Construction. Bus outage required in order re-install bus section from SW92 jaw side to north bus. | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 5.5TR (ENMAX 5) | 2017-08-23 08:00 | 2017-08-24 16:00 | N | N | Tx Secondary Cable Tests | Transformer |  |  | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2017-08-23 08:00 | 2017-08-23 12:00 | N | N | Take measurements for new CT's in TR cell | Transformer |  |  | For Information Only
ENMAX | 21.2TR (ENMAX 21) | 2017-08-23 08:00 | 2017-09-05 16:00 | N | N | TR bushing/CT replacement, diff relay replacement | Transformer |  |  | For Information Only
ENMAX | 2.80L (ENMAX 2 - ENMAX 23),ENMAX 23 B138-2.80 (ENMAX 23) | 2017-08-23 08:00 | 2017-08-23 12:00 | N | N | emergency top up breaker with SF6 | Circuit Breaker, Line |  | Emergency top up breaker 23B138-2.80 with SF6 due to low SF6 density alarm. | Pre-Condition, Creates Radial Feeds
ALTALINK | 237s552 (237s Foothills) | 2017-08-23 08:00 | 2017-08-23 12:00 | N | N | warranty tank heater modification | Circuit Breaker |  | Warranty tank heater modification. | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 65s 16E (65s High River) | 2017-08-23 08:30 | 2017-08-23 14:30 | N | N | Revert temp settings back to permanent settings on L3 feeder protection | Circuit Breaker |  | Revert temp settings back to permanent settings on L3 feeder protection. | Pre-Condition, For Information Only
WINDYPWPL | 112S Windy Point | 2017-08-23 09:00 | 2017-08-24 16:00 | N | Y | substation maintenance | Station |  |  | Restricts Generation
ENMAX | 39.4TR (ENMAX 39) | 2017-08-23 12:00 | 2017-08-23 16:00 | N | N | take measurements for new CT's in TR cell | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 237s 652 (237s Foothills) | 2017-08-23 13:00 | 2017-08-23 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  | Warranty tank heater modification. | Pre-Condition, Contingency Requires Mitigation
MONTANA | MATL (120s Picture Butte - Montana) | 2017-08-24 01:01 | 2017-08-25 16:16 | N | Y | unable to control PST | Line | Peak RC COS outage ID: 1-00508828 Peak RC Path Derate ID: 1-00508831 (N>S), 1-00508833 (S>N) |  | 240 kV, Limits ATC
ALTALINK | 916L (42s Sarcee - 5s East Calgary) | 2017-08-24 07:15 | 2017-09-18 12:00 | N | Y | [SWCRR] - erect and terminate new 916L cables at 42s | Line | GM: Please find the study results attached for 916L,693L and 6.82L outage overlap. |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 234L (310p Sundance - 234L1),505L (505L1 - 234L tap),310P 234N (310p Sundance) | 2017-08-24 07:15 | 2017-08-24 17:45 | N | N | urgent repair crossarm structure 45 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | WATL (510s Sunnybrook - 511s Crossings) | 2017-08-24 07:30 | 2017-08-25 14:00 | N | N | 510s and 511s valve hall inspection | Line |  | 510s Valve Hall Advice Aug 24 07:30  19:00 Ref #: 256432 Job Scope: Urgent outage needed to 511s Crossings valve hall to investigate loss of check back signals and potential water cooling leak. Isolation Points: 511s1325, 511s178, 511s176, 511s75, 511s1489 Rest time: 6 hr 511s Valve Hall Advice Aug 24 07:30  19:00 Ref #: 256433 Job Scope: Valve hall inspection of corona shields and fibre optic support. Urgent outage needed to 511s Crossings valve hall to investigate loss of check back signals and potential water cooling leak. Isolation Points: 510s1325, 510s42, 510s98, 510s100, 510s104, 510s4289 Rest time: 6 hr | 500 kV
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2017-08-24 07:30 | 2017-08-24 17:30 | N | N | bushing replacement - 1 phase | Transformer |  |  | For Information Only
ENMAX | 39.1TR (ENMAX 39) | 2017-08-24 08:00 | 2017-08-24 12:00 | N | N | 39.1TR and 8kV bus - take measurements for new CT's in TR cell | Transformer |  |  | For Information Only
ALTALINK, ENMAX | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21),ENMAX 21 SW86 (ENMAX 21) | 2017-08-24 08:00 | 2017-08-25 16:00 | N | Y | TR bushing/CT replacement, differential relay replacement | Line, Transformer, Shunts, Switch |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 6.80L (ENMAX 30 - ENMAX 6),30.81L (ENMAX 35 - ENMAX 30) | 2017-08-24 08:00 | 2017-09-08 16:00 | N | N | (SWCRR) - connect last spans of the relocated 6.80L to the existing line | Line |  | (SWCRR)-Connect last spans of the relocated 6.80L to the existing line at 146 Ave and 35 sub locations. Portion of 6.80L and 30.81 will be decommissioned. 6.80 will feed 35s from 6s on return. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39) | 2017-08-24 12:00 | 2017-08-24 16:00 | N | N | 39.2TR and 8kV bus - take measurements for new CT's in TR cell | Transformer |  | Take measurements for new CT's in TR cell | For Information Only
EPCOR | E511s VictoriaT4 (511s Victoria) | 2017-08-24 20:00 | 2017-08-25 05:00 | N | N | penetration checks | Transformer |  |  | For Information Only
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2017-08-25 07:15 | 2017-08-25 17:45 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.3TR (ENMAX 39) | 2017-08-25 08:00 | 2017-08-27 16:00 | N | N | LTC and transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 162s 240-RB131 (162s Beddington),162s 240-RB134 (162s Beddington) | 2017-08-25 08:00 | 2017-08-25 16:00 | N | Y | Doble PT Z43 | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 149s C1 (149s Nisku),149s T1 (149s Nisku),858L (149s Nisku - 40s Wetaskiwin),149s 858X (149s Nisku) | 2017-08-25 08:30 | 2017-08-27 17:30 | N | N | replacing 149s1 and T1 maintenance | Line, Circuit Breaker, Shunts, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2017-08-26 07:00 | 2017-08-26 17:00 | N | Y | doble | Line |  |  | 240 kV
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2017-08-26 08:00 | 2017-08-27 16:00 | N | Y | LTC maintenance | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),34B69-16.60 (ENMAX 34) | 2017-08-27 08:00 | 2017-08-27 16:00 | N | N | doble 34B69-16.60 | Line, Circuit Breaker |  |  | Pre-Condition
BCH | 5L92 (Cranbrook - Selkirk) | 2017-08-28 08:00 | 2017-09-01 17:00 | Y | Y | CBK 5CVT4 replacement - BC maintenance | Line | Peak RC COS: E-W>1-00505777 Peak RC COS: W-E>1-00505778 BC 5L92 Outage>1-00505412 |  | Limits ATC, 500 kV
ENMAX | 1.81L (ENMAX 20 - ENMAX 1),ENMAX 20 B138-1.81 (ENMAX 20) | 2017-08-28 08:00 | 2017-08-31 16:00 | N | N | civil work | Line, Circuit Breaker |  | Civil work. Cross with a 12 x 4 + 3 x 5 duct bank from new man hole 2310 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L32 (862s South Bezanson - 813s Little Smoky) | 2017-08-28 08:00 | 2017-08-31 17:00 | N | Y | replace rotten cross-arms | Line |  | Replace rotten cross-arms from inspection | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 113L (20s Ghost - 33s Spray) | 2017-08-28 08:00 | 2017-08-31 14:00 | N | Y | emergency structure replacement (fire damage) | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11) | 2017-08-28 08:00 | 2017-09-08 16:00 | N | N | differential relay replacement | Transformer |  |  | For Information Only
ALTALINK | 99s 747X (99s North St Albert),747L (99s North St. Albert - 747L3A) | 2017-08-28 09:30 | 2017-08-31 17:30 | N | N | 99s 5 138kV switch replacement | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 266s 1037L FSC (266s SC1) | 2017-08-28 13:00 | 2017-08-29 16:00 | N | Y | yearly maintenance | Shunts |  |  | 240 kV
ATCO | 7L67 (851s Morse River - 824s Fieldgate),851s 703 (851s Morse River) | 2017-08-28 13:00 | 2017-09-17 17:00 | N | N | protection upgrade | Line, Circuit Breaker |  | Protection upgrade, 851s Morse River, 785s Judy Ck, and 824s Fieldgate on radial feed from 809s Louise Creek | Firm Load Loss, Creates Radial Feeds
ALTALINK | 704L (252s Jarrow - 704L106A) | 2017-08-28 17:00 | 2017-08-31 16:00 | N | N | 704L will be open at 252s during our mobile install | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 353s T1 (353s Plamondon) | 2017-08-29 07:00 | 2017-08-31 15:00 | N | N | Replace 25kV strain insulators, Salvage 353s2 & VT2 | Transformer |  | Replace 25kV strain insulators,install lightning arresters, new bird cover up and Salvage 353s2 & VT2(353s20 & 353s19). | For Information Only
BLACKSPRING | 485s Black Springs RTU/SCADA | 2017-08-29 07:00 | 2017-08-29 11:00 | N | N | software upgrade | Terminal Equipment |  |  | Affects Visibility
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2017-08-29 07:00 | 2017-08-29 17:00 | N | N | Doble | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L89 (826s Marguerite Lake - 721s La Corey) | 2017-08-29 08:00 | 2017-08-30 17:00 | N | Y | To change double circuit. Poles on 7L89/7L91, side. | Line |  | To change double circuit. Poles on 7L89/7L91, side. | Pre-Condition
ENMAX | 40.2TR (ENMAX 40) | 2017-08-29 08:00 | 2017-09-01 16:00 | N | N | maintenance | Transformer |  | LTC Maintenance. Transformer Maintenance. Check Reversing SW. Doble sec. cables (Sub 55 )**41s must be restored before outage can be given** | For Information Only
ALTALINK | 434L (65s High River - 237s Foothills),65s 434(65s Highriver) | 2017-08-29 08:30 | 2017-08-29 16:00 | N | N | warranty tank heater modification | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 428s T1 (428s Namaka) | 2017-08-29 09:00 | 2017-08-31 17:00 | N | N | Fix oil leaks on T1 Tx18578 | Transformer |  |  | For Information Only
ENMAX | 16.1TR (ENMAX 16) | 2017-08-29 10:00 | 2017-08-29 16:00 | N | N | Inspect transformer seconday cables for damage | Transformer |  | Inspect transformer seconday cables for damage. Return 16.1TR to service carrying load with secondary cabinet door removed. After 2hrs IR scan cables. Remove 16.1TR from service to re-install secondary cabinet door. | For Information Only
ATCO | 789s 706C (789s Keg River),7L58 (789s Keg River - 905s Meikle),789s 705R (789s Keg River) | 2017-08-29 12:00 | 2017-08-29 17:00 | N | Y | close jumper J2 on 700BS3 | Shunts, Line |  | Create jumper J2 on 144kV bus @ 789s, then remove temp bus between 700BS3 @ 789s New and 700 Bus 1 @ 789Ks Old and install new bus deadend structure, then close J2. 789Ks Old will be separated from the BES on completion. 705R and 706C will be OOS Aug 22-29, 7L58 will be open ended and 7L64 will be tied to 7L62 via bypass 7L62D2 for 2 4hr periods while opening and closing J2. | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn) | 2017-08-30 07:00 | 2017-08-31 07:00 | N | Y | maintneance | Switch |  |  | Restricts Generation
EPCOR | 805s T4 (805s Jasper) | 2017-08-30 07:00 | 2017-09-01 17:00 | N | Y | oil work | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2017-08-30 07:00 | 2017-08-31 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
Saskpower | SaskPower A1R | 2017-08-30 07:00 | 2017-08-30 09:00 | N | Y | high load move | Line |  |  | Limits ATC
ALTALINK | 202L (61s Lodgepole - 202AL) | 2017-08-30 07:15 | 2017-08-31 14:45 | N | N | emergency structure replacement. | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds,Affects Cranking Path
ENMAX | 6.4TR (ENMAX 6) | 2017-08-30 08:00 | 2017-08-31 16:00 | N | N | 6BA25-6.4TR. repair | Transformer |  | 6BA25-6.4TR. Shutters do not lift in time to clear breaker rosette's when racking in. | For Information Only
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2017-08-30 08:00 | 2017-08-31 17:00 | N | Y | arm change/ insulators. | Line |  | Arm change/ insulators | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 28s 60 (28s West Brooks) | 2017-08-30 08:00 | 2017-08-30 17:00 | N | N | maintain 138kV HPL ABB minimum oil breaker | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 180s 252 (180s Cope Creek) | 2017-08-30 08:30 | 2017-08-30 12:30 | N | N | warranty tank heater modification | Circuit Breaker |  |  | For Information Only
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2017-08-30 09:00 | 2017-08-30 17:00 | N | N | high load move | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
WINDYPWPL | 112s T1 (112s Windy Point),112s CAP1 (112s Windy Point) | 2017-08-30 09:00 | 2017-08-30 15:00 | N | Y | tap changer & cap bank repairs | Transformer, Shunts |  |  | Restricts Generation
ALTALINK | 180s 152 (180s Cope Creek) | 2017-08-30 13:00 | 2017-08-30 17:00 | N | N | warranty tank heater modification. | Circuit Breaker |  |  | For Information Only
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2017-08-31 07:30 | 2017-08-31 17:00 | N | N | emergency repair; badly leaning structure | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 853L (28s West Brooks - 853L75) | 2017-08-31 08:00 | 2017-08-31 14:00 | N | N | adjust 28s853W, not closing properly | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 975s T1 (975s Dalehurst) | 2017-08-31 10:00 | 2017-08-31 14:00 | N | N | doble re-test | Transformer
ALTALINK | 704L (252s Jarrow - 7L50 tap) | 2017-09-01 08:00 | 2017-09-18 08:00 | N | Y | breaker replacement and bus protection upgrade | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 2017-09-01 08:00 | 2017-09-01 17:00 | N | Y | replace rotten cross-arms from inspection | Line |  |  | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L574 (822s Wolf Lake - 7L574 tap) | 2017-09-01 08:00 | 2017-09-01 17:00 | N | N | remove temp bypass at Wolf Lake | Line |  | 7L587/7L86 temp bypass removal @ 822s Wolf Lk, 859s Primrose will be radial fed from 970s Bourque, 1200s Cenovus will be radial tied to 7L587 via 144kV bus at 822s Wolf Lk | Firm Load Loss, Creates Radial Feeds
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2017-09-02 07:15 | 2017-09-07 17:15 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2017-09-02 08:00 | 2017-09-02 18:00 | N | N | repair hot spot on transformer | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),47.2 TR (ENMAX 47) | 2017-09-02 08:00 | 2017-09-04 12:00 | N | N | erect high bus at 162s for 162.3TR addition, 771L 138 kV bay wash | Line, Transformer
ENMAX | ENMAX 5 5B138-5BT12 (ENMAX 5) | 2017-09-03 08:00 | 2017-09-03 16:00 | N | N | SF6 gas sample | Circuit Breaker
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake),717s 702 (717s Ethel Lake) | 2017-09-04 07:00 | 2017-09-04 17:00 | N | Y | remove shield wire | Circuit Breaker, Line |  | Remove shield wire, 7L66 OOS (Cold Lk Cutplane), Ethel Lk radial fed from 846s, | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.1TR (ENMAX 36) | 2017-09-04 08:00 | 2017-09-15 16:00 | N | N | diff relay replacement | Transformer |  |  | For Information Only
SUNCOR | 29EDD-3 29PT-6 | 2017-09-04 08:00 | 2017-09-22 20:00 | N | Y | oil leak repairs | Transformer |  |  | 240 kV
ENMAX | 31.3TR (ENMAX 31) | 2017-09-04 08:00 | 2017-09-12 16:00 | N | N | bushing/CT replacement and diff relay replacement | Transformer |  |  | For Information Only
EPCOR | Rossdale RR729 (Rossdale) | 2017-09-05 07:00 | 2017-09-08 17:00 | N | N | maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),874L (522s Cooking Lake - 45s Bretona),522s Station | 2017-09-05 07:00 | 2017-09-14 18:00 | N | N | SWEATD-remove 522s3, replace 522s2, install new 522s2 and add line PT to 174L @ 197s | Line, Terminal Equipment |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CCP7213 (987s Clover Bar) | 2017-09-05 07:00 | 2017-09-30 17:00 | N | N | breaker replacement | Circuit Breaker |  |  | For Information Only
EPCOR | 330P 12TC2 (330p Genesee) | 2017-09-05 07:00 | 2017-09-08 17:00 | N | Y | doble | Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
EPCOR | 665s TX1 (665s Dome) | 2017-09-05 07:00 | 2017-09-29 17:00 | N | Y | bushing replacement | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 38.1C (ENMAX 38),38Cs 138-38CAP (ENMAX 38) | 2017-09-05 08:00 | 2017-09-09 16:00 | N | N | cap bank maintenance | Shunts, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29PL9-13 (29EDD-34 - 29EDD-65) | 2017-09-05 08:00 | 2017-09-12 20:00 | N | Y | maintenance from 29PS-216 to 29PS-201 | Line |  | 5 YR maintenance - from 29PS-216 to 29PS-201 SLD - SL30-P-141-106 & SL30-P141-109 | 240 kV
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27),16B69-16.61 (ENMAX 16),ENMAX 27 SW65 (ENMAX 27) | 2017-09-05 08:00 | 2017-09-10 16:00 | N | N | replace pt and re-install shroud on circuit breaker | Line, Circuit Breaker, Transformer, Switch |  | replace 69kV PTs. HV breaker inspection 27B69-16.61 & 16B69-16.61. Re-install shroud on circuit breaker. New lamacoid (27B69-16.61L) | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 38s T3 (38s East Edmonton) | 2017-09-05 08:00 | 2017-09-14 17:30 | N | N | move new switchgear and feeders to new building, salvage 25kV Bus B2, add SS1 & SS2, and move 118L to new switchgear building | Transformer |  |  | For Information Only
ALTALINK | 746s T2 (746s Sherwood Park) | 2017-09-05 09:00 | 2017-09-07 18:00 | N | N | 746s35 switch and 25 kV breaker maintenance | Transformer |  |  | For Information Only
BCH | 5L96 (Selkirk - Vaseux Lake) | 2017-09-05 09:00 | 2017-09-08 17:00 | N | Y | arcing horn install and spacer replacement - BC maintenance does not affect AB ATC | Line | Peak RC outage ID: 1-00457928 Peak RC path ID: 1-00509621 (E>W, export), 1-00509622 (W>E, import) |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK | 56L (245s Seebe - 20s Ghost),754L (245s Seebe - 754L65A),87L (245s Seebe - 2s Kananaskis),245s Seebe 138 kV North Bus | 2017-09-05 09:00 | 2017-09-08 15:00 | N | Y | bus protection upgrade on north bus | Bus, Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 452s T1 (452s B.F. Goodrich Fort Saskatchewan) | 2017-09-05 09:00 | 2017-09-05 17:00 | N | N | transformer troubleshooting | Transformer |  |  | For Information Only
ALTALINK | 671L (58s Edson - 39s Bickerdike) | 2017-09-05 09:30 | 2017-09-05 12:30 | N | N | high load move | Line |  |  | Pre-Condition, For Information Only
SUNCOR | 635EDD-1001 635-752-642 (635EDD-1001),635EDD-1001 635-752-643 (635EDD-1001),635EDD-1001 635-752-631 (635EDD-1001),635EDD-1001 635-752-632 (635EDD-1001) | 2017-09-05 10:00 | 2017-09-05 11:00 | N | N | commissioning cap bank one at a time | Circuit Breaker |  |  | For Information Only
ALTALINK | 230S Wardlow,275s T3 (275s Jenner),601L (275s Jenner - 230s Wardlow),275s 64 (275s Jenner) | 2017-09-05 11:30 | 2017-09-07 15:00 | N | N | bird cover on 275s64 | Switch, Transformer, Line, Station |  |  | For Information Only
ALTALINK | 69s T2 (69s North Barrhead),69s T4 (69s North Barrhead),69s 713 (69s North Barrhead) | 2017-09-05 12:00 | 2017-09-18 14:00 | N | Y | replace T4 bushing and maintenance; repairs to 69s23, & 69s713 maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2017-09-05 12:15 | 2017-09-07 14:30 | N | N | emergency repair: line clearance mitigation over roadway | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 266s 1038L FSC (266s SC1) | 2017-09-05 13:00 | 2017-09-06 16:00 | N | Y | FSC2 yearly maintenance | Shunts |  |  | 240 kV, Pre-Condition
AESO | 876L (179s Gleichen - 253s Blackie) | 2017-09-05 14:00 | 2017-09-07 16:30 | N | N | install gantry structure | Line |  | Install Gantry Structure on Line side of 253s181, Set Control Building on new piles | Firm Load Loss, Creates Radial Feeds
ALTALINK | 289s T2 (289s Saunders Lake),289s T1 (289s Saunders Lake),289s Saunders Lake 138kV Bus 1,289s Saunders Lake 138kV Bus 2 | 2017-09-06 07:30 | 2017-09-15 07:30 | N | N | SWEATD - move 289s T1, T2 & 138kV busses from CI to GOI, continue 138kV bus construction | Transformer, Bus |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2017-09-06 08:00 | 2017-09-08 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
FHEC | FH1 Fort Hills Generator Test | 2017-09-06 08:00 | 2017-12-02 16:00 | N | N | cogen1 & 2 commissioning and WECC testing starting from Sep 6 - Nov 11, 2017. in-service-date: unit 2 Oct 18 & unit 1 Oct 22, 2017. | Unit
ALTALINK | 237s 2152 (237s Foothills) | 2017-09-06 09:00 | 2017-09-06 11:00 | N | Y | apply sunshields to CTs associated with 2152 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 237s 2452 (237s Foothills) | 2017-09-06 11:00 | 2017-09-06 13:00 | N | Y | apply sunshields to CTs associated with 2452 | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm),138s 2552 (138s Windy Flats) | 2017-09-07 08:30 | 2017-09-07 12:30 | N | Y | warrant work: replace defective heater | Circuit Breaker, Line |  |  | Restricts Generation
ALTALINK | 608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm),138s 2152 (138s Windy Flats) | 2017-09-07 13:00 | 2017-09-07 17:00 | N | Y | warrant work & replace defective heater | Circuit Breaker, Line |  |  | Restricts Generation
ALTALINK | 535s T5 (535s Joffre) | 2017-09-08 09:00 | 2017-09-27 17:30 | N | N | replace U/G cables between T5 & 535s49 & perform maintenance on T5 transformer | Transformer
ALTALINK | 87L (245s Seebe - 2s Kananaskis) | 2017-09-08 15:01 | 2017-09-20 14:00 | N | Y | bus protection upgrade | Line |  |  | Restricts Generation
EPCOR | 987S Cloverbar | 2017-09-09 02:00 | 2017-09-14 10:00 | N | N | maintenance | Station |  |  | Restricts Generation
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2017-09-09 07:00 | 2017-09-09 15:30 | N | N | correct deficiencies on 3L - SWCRR | Line |  |  | Pre-Condition, For Information Only
ALTALINK | 901AL (64s East Crossfield - 901L tap),901L (63s Red Deer - 901AL tap),901L (74s Janet - 901AL tap) | 2017-09-09 07:15 | 2017-09-12 17:45 | N | N | emergency repair; structure repair from vehicle contact | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38) | 2017-09-09 08:00 | 2017-09-09 12:00 | N | N | Fall substation washing | Line, Transformer, Shunts |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2017-09-09 12:01 | 2017-09-09 16:00 | N | N | Fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-09-09 15:31 | 2017-09-10 20:00 | N | N | correct deficiencies on 150L - SWCRR | Line |  |  | Pre-Condition, For Information Only
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2017-09-10 07:00 | 2017-09-10 17:00 | N | N | mine shut-down | Line |  |  | For Information Only
EPCOR | Hardisty T3 (Hardisty),72CH9 (Hardisty - 987s Clover Bar),Hardisty H724 (Hardisty Epcor),Hardisty H723 (Hardisty Epcor) | 2017-09-10 07:00 | 2017-09-10 17:00 | N | N | doble | Transformer, Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2017-09-10 08:00 | 2017-09-10 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 391s23 (391s Balzac) | 2017-09-10 10:00 | 2017-09-14 11:30 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2017-09-10 12:00 | 2017-09-10 16:00 | N | N | Fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred 13.8 kV Bus 2 (Syncrude Mildred lake) | 2017-09-11 | 2017-09-17 23:59 | N | N | replace zigzag transformer | Bus |  | replace zigzag transformer | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale),987s CDS17 (987s Clover Bar) | 2017-09-11 07:00 | 2017-09-15 17:00 | N | N | disconnect replacement | Switch, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 330P 12TC1 (330p Genesee) | 2017-09-11 07:00 | 2017-09-15 17:00 | N | Y | Doble | Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
CMH, Medicine Hat | MH69s5 MH69_514 (MH69s5 NE Crescent Height),MH69_60LMH_60L (MH69s5 North East Cresent Heights - Cancarb) | 2017-09-11 07:00 | 2017-09-15 16:00 | N | N | Finalizing 5S 60L panel upgrade | Line, Circuit Breaker |  | Finalizing 5S 60L panel upgrade to be re-energized to MHS-7 MH69-712 on sept 15 | For Information Only
EPCOR | E511s VictoriaT2 (511s Victoria) | 2017-09-11 07:00 | 2017-12-15 17:00 | N | N | containment pit | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK, EPCOR | 1045L (310p Sundance - 805s Jasper) | 2017-09-11 07:00 | 2017-09-11 17:00 | N | Y | Doble | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2017-09-11 08:00 | 2017-09-11 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D134 (ENMAX 25) | 2017-09-11 08:00 | 2017-09-11 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
CMH | CMH1 Medicine Hat #1 Generator Test | 2017-09-11 08:00 | 2017-11-03 16:00 | N | N | unit #16 commissioning. In-service-date: Oct 1st, 2017. | Unit
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek) | 2017-09-11 08:00 | 2017-09-18 17:00 | N | Y | replace rotten crossarms | Line |  | replace rotten crossarms, 741s radial fed via 7L199 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 482S Haynes | 2017-09-11 08:00 | 2017-10-05 17:00 | N | N | Altalink PT addition and customer switchgear replacement | Station |  |  | Pre-Condition, For Information Only
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2017-09-11 09:00 | 2017-09-15 17:00 | Y | Y | annual maintenance - BC maintenance does not affect AB ATC | Line | Peak RC:1-00457927 Peak RC E-W: 1-00512018 Peak RC W-E: 1-00512019 |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK | 924L (102s Langdon - 356s Milo) | 2017-09-11 09:15 | 2017-09-13 07:15 | N | Y | emergency damper repair | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 3L (245s Seebe - 3L145),58L (245s Seebe - 32s Barrier),777L (245s Seebe - 48s Pocaterra),245s Seebe 138 kV South Bus | 2017-09-11 10:00 | 2017-09-15 15:00 | N | Y | bus protection upgrade on south bus | Bus, Line | Peak RC: 1-00511962 |  | Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Creates Radial Feeds
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2017-09-11 11:00 | 2017-09-14 17:00 | N | Y | migrate controls, annunciation and analogs to new RTU | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 83s T3 (83s Taber) | 2017-09-11 11:00 | 2017-09-11 17:00 | N | N | replace tapchanger lower and raise contactor and fix winding temp gauge | Transformer
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2017-09-11 12:00 | 2017-09-11 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, For Information Only
ENMAX | ENMAX 25 B240-D135 (ENMAX 25) | 2017-09-11 12:00 | 2017-09-11 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 801L (358s Amoco Brazeau - 801L302) | 2017-09-11 13:00 | 2017-09-20 16:45 | N | Y | replace structures/insulators, repair guy wires, general maintenance | Line |  |  | Pre-Condition, Overload, Restricts Generation, Creates Radial Feeds
ALTALINK | 62s12 (62s Brazeau) | 2017-09-11 23:00 | 2017-10-27 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
CUPCAN | 850s 701T (850s Rainbow Cogen) | 2017-09-12 07:00 | 2017-09-18 17:00 | N | Y | protection upgrades | Transformer |  | Protection upgrades | Restricts Generation
ALTALINK | 649s T1 (649s Chappice Lake) | 2017-09-12 07:00 | 2017-09-12 19:00 | N | N | 649s VR1 & 25kV bus: metering upgrade, add new PT | Transformer |  |  | For Information Only
ATCO | 851s 701T (851s Morse River),7L19 (809s Louise Creek - 851s Morse River),7L67 (851s Morse River - 824s Fieldgate),7L78 (785s Judy Creek - 851s Morse River),851s 702 (851s Morse River) | 2017-09-12 07:00 | 2017-10-16 17:00 | N | N | replace 701TCS at 851s | Line, Circuit Breaker, Transformer |  | Replace 701TCS @ 851s, 7L78/7L19 Bypass will already be in place (see HOP 2-37020), 7L67 will be open ended at 851s, 851s 25kV load will be transferred to adjacent subs, stn service will be backfed from 25kV system. Once 701A is installed, 2-36722B will be issued to shrink the GOI down to 701A, 501TD2 @ 851s. The 144kV bus will then be put back in service | For Information Only
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2017-09-12 07:30 | 2017-09-14 18:30 | N | N | deficiencies - dampers, insulators change out | Line |  | Deficiencies - dampers, insulators change out . This outage will require an outage to a significant DG signalta resources at 368s | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 310p 452 (310p Sundance) | 2017-09-12 07:30 | 2017-09-20 10:00 | N | Y | replace leaking CT - center phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 676L (523s Bullshead - 244s Bowmanton) | 2017-09-12 07:30 | 2017-09-14 18:30 | N | Y | deficiencies,splices,dampers,insulators | Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2017-09-12 08:00 | 2017-09-12 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
CNRL | 838s 75-TR-2801 (838s Horizon Mining) | 2017-09-12 08:00 | 2017-10-20 18:00 | N | Y | removal of old transformer and install of a new transformer | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO, ALTALINK | 9L961 (13s Deerland - 825s Whitefish Lake) | 2017-09-12 08:00 | 2017-09-13 17:00 | N | N | emergency outage request to repair a deadend structure | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D136 (ENMAX 25) | 2017-09-12 08:00 | 2017-09-12 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2017-09-12 08:00 | 2017-09-13 17:00 | N | N | change poles | Line |  | Change poles from test and treat | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s T1 (83s Taber) | 2017-09-12 08:30 | 2017-09-12 16:30 | N | Y | remove birds nest in 25kV bus | Transformer |  | Remove birds nest in 25kV bus above 83s23 and 83s40 | Restricts Generation, For Information Only
ATCO | 969s 701T (969s Lindbergh) | 2017-09-12 10:00 | 2017-09-12 16:00 | N | N | require to inspect NGR as repeated fail alarms | Transformer |  | Require to inspect NGR as Repeated Fail Alarms, During outage IPF site will be out, as well will have to island Pengrowth on the 25KV Feed. | Restricts Generation, For Information Only
ENMAX | ENMAX 25 B240-D138 (ENMAX 25) | 2017-09-12 12:00 | 2017-09-12 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 927L (102s Langdon - 356s Milo) | 2017-09-13 07:16 | 2017-09-15 17:45 | N | Y | emergency damper repair | Line |  |  | 240 kV, Pre-Condition
ENMAX | ENMAX 25 B240-D139 (ENMAX 25) | 2017-09-13 08:00 | 2017-09-13 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 38.1TR (ENMAX 38) | 2017-09-13 08:00 | 2017-09-22 16:00 | N | N | TR bushing/CT replacement and TR diff relay replacement | Transformer |  |  | For Information Only
ENMAX | 31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2017-09-13 08:00 | 2017-09-13 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 103s T1 (103s Goose Lake) | 2017-09-13 09:00 | 2017-09-14 15:00 | N | Y | maintain, doble, and fix hydran sensor | Transformer |  |  | Pre-Condition, Overload
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2017-09-13 12:01 | 2017-09-13 16:00 | N | N | fall substation washing | Line, Shunts, Transformer |  |  | Pre-Condition
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2017-09-14 07:00 | 2017-09-14 17:00 | N | N | change poles from test and treat | Line |  | Change poles from test and treat | Pre-Condition, For Information Only
ALTALINK | 44s T1 (44s Bearspaw Plant) | 2017-09-14 08:00 | 2017-09-14 17:00 | N | N | Doble T1 and fix oil leaks | Transformer |  |  | For Information Only
SUNCOR | 635PL7-1000 (635EDD-1000 - 635EDD-1001) | 2017-09-14 08:00 | 2017-09-16 17:00 | N | Y | Fort Hills IMS and LoadShed system field equipment tie-in and testing, ABB relays card change | Line |  | 1. Fort Hills Islanding Managemen System (IMS) and LoadShed System Field Equipment Tie-in and Testing 2 . ABB Relays Card Change | Firm Load Loss, Creates Radial Feeds, For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2017-09-14 08:00 | 2017-09-14 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
CNRL | 842s 75-1901 (842s Horizon Upgrading),842s 75-1902 (842s Horizon Upgrading),842s 75-1903 (842s Horizon Upgrading),842s 75-1904 (842s Horizon Upgrading),842s 75-1905 (842s Horizon Upgrading),842s 75-1906 (842s Horizon Upgrading) | 2017-09-14 08:00 | 2017-09-26 15:00 | N | Y | testing of the 260kV circuit breakers and capacitive voltage transformers | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 287S Hazelwood,929L (63s Red Deer - 74s Janet),63s 2752 (63s Red Deer),63s 2652 (63s Red Deer),74s 352 (74s Janet),74s 252 (74s Janet) | 2017-09-14 09:01 | 2017-10-18 12:00 | N | Y | build and cut in 929L into Hazelwood and rename to 1082L | Station, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2017-09-14 10:00 | 2017-09-14 15:00 | N | Y | emergency replacement of shot-out dead end bells | Line |  |  | Pre-Condition, Restricts Generation
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2017-09-15 06:30 | 2017-09-19 17:30 | N | Y | line clearance mitigation | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 780L (38s East Edmonton - 149s Nisku) | 2017-09-15 07:30 | 2017-09-21 15:30 | N | N | cut 780L in/out of 289s, close open points O & L, rename line portion going to 149s to 454L, add VT4 at 149s (SWEATD) | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36) | 2017-09-15 16:00 | 2017-09-27 16:00 | N | N | diff relay replacement | Transformer |  |  | For Information Only
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2017-09-15 17:00 | 2017-09-15 17:30 | N | Y | energize new CT on 310p 452 (310p Sundance) | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 11.2TR (ENMAX 11),11.3TR (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2017-09-16 01:30 | 2017-09-30 16:00 | N | N | 11s reliability upgrade and fall substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | Kennedale T1 (Kennedale) | 2017-09-16 07:00 | 2017-09-17 17:00 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L (ENMAX 2 - 2.83L tap),5.9TR (ENMAX 5),5.10TR (ENMAX 5) | 2017-09-16 08:00 | 2017-09-16 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2017-09-16 12:00 | 2017-09-16 16:00 | N | N | fall substation washing and network switching required | Line, Transformer |  |  | Pre-Condition, Overload
EPCOR | 72CK13 (987s Clover Bar - Kennedale),Kennedale K722 (Kennedale),Kennedale K721 (Kennedale),Kennedale T1 (Kennedale) | 2017-09-17 07:00 | 2017-09-17 17:00 | N | N | doble | Transformer, Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 635PL7-1001 (635EDD-1000 - 635EDD-1001) | 2017-09-17 08:00 | 2017-09-19 17:00 | N | N | Fort Hills IMS and load shed system field equipment tie-in and testing ABB relays card change | Line |  | 1. Fort Hills Islanding Managemen System (IMS) and LoadShed System Field Equipment Tie-in and Testing 2 . ABB Relays Card Change | Firm Load Loss, Creates Radial Feeds
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2017-09-17 08:00 | 2017-09-17 12:00 | N | N | fall substation washing, network switching required | Line, Transformer |  |  | Overload
ALTALINK | 535s T4 (535s Joffre) | 2017-09-17 09:00 | 2017-09-27 16:15 | N | N | replace U/G cables between T4 & 535s44 & perform oil reclaim | Transformer
BCH | 5L71 (Mica Creek - Nicola),5L72 (Mica Creek - Nicola) | 2017-09-17 13:00 | 2017-09-17 17:00 | N | Y | MCA blackstart testing with G1 & G2, in association with CM 47919/8-298064 | Line | BC Peak RC COS#: 1-00511229 AB Peak RC COS# : 1-00513136 (W-E), 1-00513138 (E-W) | 5L71, 5L72 OOS, MCA RMR: 2 units Must be ONLINE for Black start testing , MCA 12F51, 12F52, GST 12F51, MCK 25F51, GSM, 60L223 OOS MCA Blackstart Testing with G1 & G2, in association with CM 47919/8-298064 | Limits ATC
CENOVUS | 539s 9201T (539s Sunday Creek) | 2017-09-18 07:00 | 2017-09-30 18:00 | N | Y | 5 year maintenance | Transformer |  | 5 year Maintenance on the transformer and its attached auxiliary devices | 240 kV, For Information Only
Syncrude | Aurora 14 (Aurora),Aurora 24 (Aurora),Aurora 34 (Aurora),Aurora T-11 | 2017-09-18 07:00 | 2017-10-02 20:00 | N | Y | 5 yr PM and replacing 14B, 24B and 34B isolating disconnects | Transformer, Circuit Breaker |  | 5Yr PM of Transformer # T11, G01 - SubStation at Aurora and Replacing 14B, 24B and 34B isolating disconnects. | 240 kV, Creates Radial Feeds, For Information Only
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2017-09-18 07:15 | 2017-09-19 12:00 | N | N | contamination monitoring program | Line |  |  | Creates Radial Feeds
ALTALINK | 62s 32 (62s Brazeau) | 2017-09-18 07:30 | 2017-09-18 16:30 | N | Y | RET will be opening/closing 62s33 to functional test new 189 (62s33) module prior to T3 GOI | Switch |  |  | 240 kV, For Information Only
ALTALINK | 310P T32 (310P Sundance) | 2017-09-18 07:30 | 2017-09-19 17:30 | N | Y | metering upgrade. | Transformer |  |  | 240 kV
CNRL | 75PHL-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2017-09-18 08:00 | 2017-09-20 18:00 | N | Y | transmission line insulator replacement and maintenance | Line |  |  | 240 kV, For Information Only
ALTALINK | 38s T2 (38s East Edmonton) | 2017-09-18 08:00 | 2017-09-18 17:00 | N | N | create open points to prep outdoor 25kV bus B1 for salvage | Transformer |  |  | For Information Only
ATCO, ALTALINK | 7L50 (757s Battle River - 526s Buffalo Creek) | 2017-09-18 08:00 | 2017-09-18 14:00 | N | N | AltaLink request for AltaLink work at 252s Jarrow | Line |  | AltaLink Request for AltaLink work at 252s Jarrow | For Information Only
ALBIAN | 920s 902T (920s Jackpine) | 2017-09-18 08:00 | 2017-09-22 17:00 | N | Y | CNRL requires a condition of guarantee to accommodate the 72 KV cable repair and the 72 KV sensing resistor in the 902T transformer | Transformer |  | Customer Request **CNRL Request - they require a Condition Of Guarantee to accommodate the 72 KV cable repair and the 72 KV sensing resistor in the 902T transformer. | 240 kV, For Information Only
ENMAX | 34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2017-09-18 08:00 | 2017-09-18 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.3TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2017-09-18 08:00 | 2017-09-18 16:00 | N | N | fall substation washing | Line, Shunts, Transformer |  |  | For Information Only
ATCO, ALTALINK | 7L50 (757s Battle River - 526s Buffalo Creek), 252S Jarrow | 2017-09-18 09:00 | 2017-09-18 12:00 | N | Y | complete 25kV metering PT upgrade, 252s2 breaker replacement, 138kV | Line, Station |  | complete 25kV metering PT upgrade, 252s2 breaker replacement, 138kV. and Risers Between 252s2 & 252s3 Bus Protection Upgrade | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 715s 702T (715s Leming Lake) | 2017-09-18 09:00 | 2017-09-21 16:00 | N | N | replace questionable bushings and repair leaks on transformer | Transformer |  | Replace questionable bushings and repair leaks on transformer. Site will be fed from 701T & 703T | For Information Only
ALTALINK | 827L (121s Brooks - 28s West Brooks) | 2017-09-18 10:00 | 2017-09-22 15:00 | N | N | replace 2 CTs associated with breaker 28s55 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss
ALTALINK | 704L (252s Jarrow - 704L tap) | 2017-09-18 11:00 | 2017-09-18 15:00 | N | N | remove 472s & MR1 138kV mobile high side cables to 704L - 478s | Line |  |  | For Information Only
ENMAX | 41.2TR (ENMAX 41) | 2017-09-18 12:00 | 2017-09-18 16:00 | N | N | remove control wiring from 41.2TR (94) relay | Transformer |  |  | For Information Only
ALTALINK | 892L (895s Suffield - 244s Bowmanton) | 2017-09-18 12:15 | 2017-09-20 17:45 | N | N | emergency repair, line clearance mitigation, public safety concern. | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 983L (251s Whitla - 244s Bowmanton) | 2017-09-18 12:30 | 2017-09-20 18:00 | N | Y | deficiencies,dampers on 983L str4. | Line |  |  | 240 kV, Over/Under Voltage
ALTALINK | 746S Sherwood Park | 2017-09-18 12:30 | 2017-09-21 17:30 | N | N | breaker maintenance | Station |  | 746s34N GOI for breaker maintenance. | For Information Only
ALTALINK | 678s T2 (678s Okotoks) | 2017-09-18 13:00 | 2017-09-20 16:00 | N | N | T2 doble and maintenance | Transformer |  |  | For Information Only
ATCO | 791s 703T (791s Rainbow Lake) | 2017-09-18 13:00 | 2017-09-18 16:00 | N | N | PCB sampling for 704, 703T and 601T@ 791S Rainbow Lake | Transformer |  | PCB sampling for 704, 703T and 601T@ 791S Rainbow Lake | For Information Only
ALTALINK | 69s T4 (69s North Barrhead),69s 713 (69s North Barrhead) | 2017-09-18 14:01 | 2017-11-28 06:59 | N | Y | emergency tap changer repair | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s T3 (62s Brazeau) | 2017-09-18 16:31 | 2017-09-29 08:00 | N | Y | replacing S protection, changes to T3 A protection | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 38s T2 (38s East Edmonton) | 2017-09-18 17:01 | 2017-09-28 17:00 | N | N | bring in new Fortis feeders, move protections over to new switchgear building, install risers structure, connect SS1 | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap),747L (37s North Calder - 99s North St Albert) | 2017-09-19 07:00 | 2017-09-22 17:00 | N | N | insulator washing - EPCOR | Line |  |  | For Information Only
ATCO | 7L696 (508s Lakesend - 892s Ribstone Creek) | 2017-09-19 07:00 | 2017-09-19 17:00 | N | Y | install inter phase spacers between A and C phase | Line |  | To mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost. This mitigation is to install inter phase spacers between A and C phase so that they cannot get close to each other as frost comes off of the wire. | For Information Only
ALTALINK | 723s T1 (723s Christina Lake) | 2017-09-19 07:00 | 2017-09-19 18:00 | N | Y | 723s christina Lke temp montr(T1) FOPS | Transformer |  |  | 240 kV, For Information Only
ATCO | 7L79 (771s Veteran - 892s Ribstone Creek),7L79 (771s Veteran - 932s Pemukan) | 2017-09-19 07:00 | 2017-09-19 17:00 | N | N | install inter phase spacers between A and C phase | Line |  | To mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost. This mitigation is to install inter phase spacers between A and C phase so that they cannot get close to each other as frost comes off of the wire. | Firm Load Loss, For Information Only
SUNCOR | 635EDD-1000 635-752-132 (635EDD-1000),635EDD-1000 635-752-142 (635EDD-1000),635EDD-1000 635-752-152 (635EDD-1000),635EDD-1000 635-752-162 (635EDD-1000),635EDD-1000 635-752-133 (635EDD-1000),635EDD-1000 635-752-143 (635EDD-1000),635EDD-1000 635-752-153 (635EDD-1000),635EDD-1000 635-752-163 (635EDD-1000) | 2017-09-19 08:00 | 2017-09-19 17:00 | N | N | breaker trip function test from IMS relays one at a time | Circuit Breaker |  |  | For Information Only
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2017-09-19 08:00 | 2017-09-19 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds
ENMAX | 14.2TR (ENMAX 14) | 2017-09-19 08:00 | 2017-09-29 16:00 | N | N | bushing/CT replacement | Transformer |  | bushing/CT replacement. TR DIFF Relay Replacement | For Information Only
ALTALINK | 437s T2 (437s Baymag) | 2017-09-19 08:00 | 2017-09-19 16:00 | N | N | customer annual maintenance | Transformer |  |  | For Information Only
ALTALINK | 437s T1 (437s Baymag) | 2017-09-19 08:00 | 2017-09-19 16:00 | N | N | customer annual maintenance | Transformer |  |  | For Information Only
ATCO | 791s 701T (791s Rainbow Lake) | 2017-09-19 08:00 | 2017-09-19 12:00 | N | N | PCB sampling on transformer and bushings | Transformer |  | PCB sampling on Transformer and bushings, All 25kV load will go through 702T | For Information Only
ALTALINK | 755L (535s Joffre - 247s Piper Creek),427L (63s Red Deer - 247s Piper Creek) | 2017-09-19 08:30 | 2017-10-23 17:00 | N | N | replacement of protection and control devices | Line |  |  | Overload, Contingency Requires Mitigation
ALTALINK | 1036L (554s Travers - 356s Milo),1041L (370s North Lethbridge - 554s Travers) | 2017-09-19 09:00 | 2017-09-19 11:00 | N | Y | firmware upgrade | Line |  | The MW radio between 120S Picture Butte and 554S Travers requires firmware upgrade to improve reliability. This outage requires 1041L and 1036L to be opened AT THE SAME TIME for 2 hours. Upgrade required in order to avoid any unplanned breakdown or malfunction of the system. | 240 kV, Restricts Generation, Contingency Requires Mitigation
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2017-09-19 12:00 | 2017-09-19 16:00 | N | Y | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2017-09-19 12:00 | 2017-09-19 18:45 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 791s 702T (791s Rainbow Lake) | 2017-09-19 13:00 | 2017-09-19 16:00 | N | N | PCB sampling on transformer and bushings | Transformer |  | PCB sampling on Transformer and bushings, All 25kV load will go through 701T | For Information Only
ATCO | 7L122 (791s Rainbow Lake - 930s Arcenciel) | 2017-09-20 07:00 | 2017-10-06 17:00 | N | N | replace 7L122D1 footings and structure at 791s | Line |  | Replace 7L122D1 footings and structure @ 791s. | Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2017-09-20 07:15 | 2017-09-21 17:45 | N | N | contamination monitoring program | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works),801L (294s Brazeau Outlet Works - 801L302 Tap) | 2017-09-20 07:15 | 2017-09-22 12:00 | N | Y | deadend insulator replacements | Line |  |  | Pre-Condition, Overload, Restricts Generation, Creates Radial Feeds
ALTALINK | 310P T33 (310P Sundance) | 2017-09-20 07:30 | 2017-09-21 17:30 | N | N | metering upgrade | Transformer |  |  | For Information Only
ENMAX | ENMAX 65 B240-D130 (ENMAX 65) | 2017-09-20 08:00 | 2017-09-20 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15),15B69-15.60 (ENMAX 15),21B69-15.60 (ENMAX 21) | 2017-09-20 08:00 | 2017-09-23 16:00 | N | N | SEL-321 relay replacement on 15B69-15.60 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L29 (946s Oakland - 963s Coyote Lake) | 2017-09-20 10:00 | 2017-09-20 12:00 | N | N | repair damaged and unraveled OPGW wire on 9L29 | Line |  | OPGW wire on 9L29 that is damaged and unraveled. We need to make a repair on this fairly soon so that it doesnt unravel more and cause an unplanned outage or possibly a fire. | 240 kV, For Information Only
ALTALINK | 233s T1 (233s Beamer) | 2017-09-20 10:00 | 2017-09-20 15:00 | N | N | customer work on switchgear | Transformer |  |  | For Information Only
ATCO | 828S Sulphur Point,828s 507C1 (828s Sulphur Point),828s 507C2 (828s Sulphur Point) | 2017-09-20 12:00 | 2017-09-20 16:00 | N | N | taking PCB samples off of station service cans | Shunts, Station |  | Taking PCB Samples off of station service cans. 507C will be unavailable during the work. 25kV feeder relays will lose the frequency protection all remaining protection will be in service. The station service will be off to the main control building and all of the Protection and Control will be reliant on the DC batteries for the duration of the work. Techs will be on site at all times and will monitor the batteries. | For Information Only
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2017-09-20 12:00 | 2017-09-20 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 780L (38s East Edmonton - 289s Saunders Lake) | 2017-09-21 | 2017-09-22 | N | N | ISD Sept 21, 2017 | Line
ALTALINK | 454L (149s Nisku - 289s Saunders Lake) | 2017-09-21 | 2017-09-22 | N | N | ISD Sept 21, 2017 | Line
ALTALINK | 289S Saunders Lake | 2017-09-21 | 2017-09-22 | N | N | ISD Sept 21, 2017 | Station
ALTALINK | 432s T1 (432s Carvel) | 2017-09-21 07:00 | 2017-09-21 18:00 | N | N | 432s Carvel temp monitor (T1) | Transformer |  |  | For Information Only
ATCO | 6L12 (6L12D5- 6L12D3) | 2017-09-21 08:00 | 2017-09-21 17:00 | N | N | Conductor fix and insulators change | Line |  | Conductor fix and insulators change | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D140 (ENMAX 25) | 2017-09-21 08:00 | 2017-09-21 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 25B240-D141 (ENMAX 25) | 2017-09-21 12:00 | 2017-09-21 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 454L (149s Nisku - 289s Saunders Lake) | 2017-09-21 15:30 | 2017-09-21 16:00 | N | N | [SWEATD] energize 454L (149s-289s), 780L now 38s-289s | Line |  |  | For Information Only
ALTALINK | 858L (149s Nisku - 40s Wetaskiwin),289s T2 (289s Saunders Lake),289s T1 (289s Saunders Lake),289s Saunders Lake 138kV Bus 1,289s Saunders Lake 138kV Bus 2 | 2017-09-21 15:31 | 2017-09-28 16:00 | N | N | [SWEATD] - bring new 858/454L line sections into 289s, cut 858L in/out of 289s, add VT5 at 149s | Line, Bus, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 25B240-D142 | 2017-09-22 08:00 | 2017-09-22 12:00 | N | Y | SF6 Gas Sample | Terminal Equipment |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2017-09-23 07:00 | 2017-09-23 16:00 | N | N | road excavation by civil dept | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2017-09-23 08:00 | 2017-09-23 12:00 | N | N | fall substation washing | Line, Transformer
AESO-SC | Security Patching | 2017-09-23 08:00 | 2017-09-23 16:00 | N | N | EMS 3.0 CIP and PI | SCInternal |  |  | For Information Only
ENMAX | 32.83L (ENMAX 32 - ENMAX 40),26.81L (ENMAX 32 - ENMAX 26) | 2017-09-23 12:00 | 2017-09-23 16:00 | N | N | fall substation washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2017-09-24 08:00 | 2017-09-24 12:00 | N | Y | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2017-09-24 12:00 | 2017-09-24 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2017-09-24 12:00 | 2017-09-24 16:00 | N | N | fall transmission line washing | Line
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2017-09-24 12:00 | 2017-09-24 14:00 | N | N | fall transmission line washing (pothead washing) | Line
EPCOR | 72CK13 (987s Clover Bar - Kennedale),987s CK726 (987s Clover Bar),Kennedale K721 (Kennedale) | 2017-09-25 07:00 | 2017-09-27 17:00 | N | N | line impedance testing | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Strathcona T3 (Strathcona) | 2017-09-25 07:00 | 2017-09-29 17:00 | N | N | doble | Transformer |  |  | For Information Only
ALTALINK | 666L (498s Tilley - 28s West Brooks),498s 666 (498s Tilley),28S 666 (28S West Brooks) | 2017-09-25 07:15 | 2017-09-27 17:45 | N | Y | emergency structure replacements, fire damage from grass fire | Line, Switch, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s T7 (62s Brazeau) | 2017-09-25 07:15 | 2017-09-29 17:45 | N | N | replacing A & B protections and metering | Transformer |  |  | For Information Only
ALTALINK | 934L (132s Ware Junction - 801s Anderson),132s 15 (132s Ware Junction),132s 18 (132s Ware Junction),132s 934N (132s Ware Junction) | 2017-09-25 07:30 | 2017-09-29 17:30 | N | Y | replacing 'A' & 'B' line protections | Line, Circuit Breaker, Switch |  |  | 240 kV, Overload, Contingency Requires Mitigation
ATCO | 2029s ACF21 (2029s Heathfield),2029s ACF23 (2029s Heathfield),2029s ACF22 (2029s Heathfield) | 2017-09-25 07:30 | 2017-09-28 16:30 | N | Y | ACF2 inspections and breaker 1223 wiring fix | Shunts |  | ACF2 inspections and Bkr 1223 wiring fix, 750MW power transfer limit | For Information Only, 500 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2017-09-25 08:00 | 2017-10-06 19:00 | N | Y | align with 1201L outage | Line | Peak RC COS outage ID: 1-00504530 Peak RC Path Derate ID: 1-00504532 (E>W), 1-00504534 (W>E) |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | ENMAX 65 B240-D132 (ENMAX 65) | 2017-09-25 08:00 | 2017-09-25 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2017-09-25 09:00 | 2017-10-06 17:30 | Y | Y | AML annual maintenance & BCH replace CBK 5CVT5 | Line | Peak RC COS outage ID: 1-00504530 Peak RC Path Derate ID: 1-00504532 (E>W), 1-00504534 (W>E) |  | Limits ATC, 500 kV
ENMAXEC | 383S Kettles Hill Windfarm | 2017-09-25 09:00 | 2017-09-25 15:00 | N | N | transfer/commission communications from wireless/radio to newly installed fiber line | Station |  |  | Affects Visibility
ATCO | 863S Paintearth,9L27 (863s Paintearth - 755s Cordel),9L948 (650s Hansman Lake - 863s Paintearth) | 2017-09-25 09:00 | 2017-11-06 15:00 | N | Y | 240 kV switch replacement | Station, Line |  | the 863S Paint Earth Substation 240KV replacement switches are to arrive early August. The plan is for replacement of the devices Off-loading the entire substation and back feeding the station service would be the preferred method Switch Replacement dates: 900D1 - September 25th - 29th . 9L27D2 - October 2 - 6th. 901A - October 10 -15th. 9L948D4 - October 16 - 20th. 902A - October 23 - 27th. | 240 kV, For Information Only
ALTALINK | 931L (132s Ware Junction - 28s West Brooks),28s 5 (28s West Brooks),28s 8 (28s West Brooks) | 2017-09-25 10:00 | 2017-09-28 16:00 | N | Y | replace 3 PTs at 28s17 | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 320p T1 (320p Keephills) | 2017-09-25 10:30 | 2017-09-27 14:10 | N | Y | bushing replacement | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 63s 452 (63s Red Deer) | 2017-09-25 11:00 | 2017-09-27 17:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 102s SVC (102s Langdon) | 2017-09-25 11:00 | 2017-09-28 15:00 | N | Y | SVC maintenance | Shunts |  |  | 240 kV
ENMAX | ENMAX 65 B240-D133 (ENMAX 65) | 2017-09-25 12:00 | 2017-09-25 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2075s SVC2 (2075s Newell) | 2017-09-26 07:00 | 2017-09-28 16:00 | N | Y | SVC2 programming changes | Shunts |  | SVC2 PROGRAMMING CHANGES, SVC1 will remain in service, There will be no operating constraints to 13L50 while the SVC is out of service how ever we will be down to a single contingency for the SVC's while it is out of service Programming updates must be made to SVC 2 TDC controllers to ensure that if there is a loss of communication to either TDC operating system a change over occurs first rather than an shut down of the SVC. | 240 kV
ALTALINK | 435S Bassano | 2017-09-26 08:00 | 2017-09-28 12:00 | N | N | reinstall underground terminations | Station |  | Reinstall underground terminations.12 terminations will need to be done. The 6 on the Cables connected to the 25 kV buss outside by the tx, the 3 associated with 435s2254, and the 3 associated with 435s2253. | For Information Only
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2017-09-26 08:00 | 2017-09-27 16:00 | N | N | water leak in the cabinet and the top plate needs to be resealed | Line |  | 20B138-20.82  Water leak in the cabinet and the top plate needs to be resealed. 21B138-20.82  Alarm on the spring charge system. | Creates Radial Feeds
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek) | 2017-09-26 08:00 | 2017-10-02 17:00 | N | Y | replace rotten crossarms | Line |  | replace rotten crossarms, 741s radial fed via 7L199 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.2TR (ENMAX 38) | 2017-09-26 08:00 | 2017-10-06 16:00 | N | N | TR bushing/CT replacement. TR DIFF relay replacement | Transformer |  |  | For Information Only
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2017-09-26 08:15 | 2017-09-26 12:45 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale C2 | 2017-09-26 15:00 | 2017-12-08 15:00 | N | N | forced outage | Shunts |  |  | For Information Only
ALTALINK | 1054L (13s Deerland - 12s Heartland) | 2017-09-27 07:30 | 2017-09-28 17:30 | N | Y | damper replacements | Line |  |  | 240 kV, Pre-Condition, Overload, Creates Radial Feeds
CNRL | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2017-09-27 08:00 | 2017-09-28 16:20 | N | Y | transmission line insulator replacement and maintenance | Line |  |  | 240 kV, Creates Radial Feeds
CNRL | 838S Horizon Mining | 2017-09-27 08:00 | 2017-10-16 15:00 | N | Y | testing of 260kV VTs and CTs | Station |  |  | 240 kV, Restricts Generation
ALTALINK | 58s Edson RTU/SCADA | 2017-09-27 10:00 | 2017-09-28 16:00 | N | N | change NIC card in RTU | Terminal Equipment |  |  | Affects Visibility
ATCO | 876s 901T (876s Brintnell) | 2017-09-27 10:00 | 2017-09-29 14:00 | N | Y | major test | Transformer |  | TRANSFORMER CLASS1 MAJOR TESTING 901T | 240 kV, For Information Only
ALTALINK | 62s C1 (62s Brazeau),62s 215 (62s Brazeau) | 2017-09-27 12:30 | 2017-09-27 18:30 | N | N | wiring cutovers and trip test from new T3 and T7 | Circuit Breaker, Shunts |  | Wiring cutovers and trip tests from new T3 & T7 protections; Re-test block closing scheme on this breaker. | Pre-Condition
ALTALINK | 455L (149s Nisku - 289s Saunders Lake) | 2017-09-28 | 2017-09-30 | N | N | ISD Sept 28, 2017 | Line
ALTALINK | 719L (378s Shell Caroline - 719214X) | 2017-09-28 07:15 | 2017-10-01 17:45 | N | N | component replacements, structure replacements, install/commission new airbrake at str 213 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L24 (700s Bonnyville - 7L24 D2) | 2017-09-28 08:00 | 2017-09-29 17:00 | N | N | road move | Line |  | Road move, 940s Beartrap radial fed from 846s Grande Centre | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 132s Ware Junction RTU/SCADA | 2017-09-28 09:30 | 2017-09-28 12:30 | N | N | emergency troubleshoot missing points within the RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 767L (320p Keephills - 767L167A),320p 767N (320p Keephills) | 2017-09-28 12:00 | 2017-09-28 16:00 | N | N | grading capacitor blown out in one phase - urgent repair | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 455L (149s Nisku - 289s Saunders Lake) | 2017-09-28 15:30 | 2017-09-28 16:00 | N | N | energize 455L (149s-289s). 858L now 40s-289s | Line
ALTALINK | 289s T1 (289s Saunders Lake) | 2017-09-28 15:31 | 2017-10-05 07:00 | N | N | [SWEATD] T1 under GOI until energization | Transformer
ALTALINK | 289s T2 (289s Saunders Lake) | 2017-09-28 15:31 | 2017-10-05 12:00 | N | N | [SWEATD] T2 under GOI until energization | Transformer
EPCOR | 330p 1203 (330p Genesee) | 2017-09-28 15:52 | 2017-10-01 17:00 | N | N | forced outage (return to service date unknown) | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
CNRL | 75-TR-2801 (838s Horizon Mining) | 2017-09-29 | 2017-10-01 16:00 | N | N | ISD Sept 30, 2017 (like for like transformer replacement) | Transformer |  |  | For Information Only
ALTALINK | 297s T1 (297s Rimbey) | 2017-09-29 07:00 | 2017-10-05 17:30 | N | N | replace 25 kV bushing & perform T1 maintenance & oil reclaim | Transformer
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works) | 2017-09-29 07:15 | 2017-10-06 16:45 | N | Y | replace structures/insulators, repair guy wires, general maintenance | Line |  |  | Overload, Restricts Generation
ALTALINK | 719L (575s Sundre - 378s Shell Caroline) | 2017-09-29 07:15 | 2017-09-29 17:45 | N | Y | component replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 2033s 701 (2033s Mowat),2033s 701T (2033s Mowat) | 2017-09-29 08:30 | 2017-09-29 16:00 | N | N | urgent repair/top-up SF6 breaker | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 75-PLH-901 (838s Horizon Mining - 849s Joslyn) | 2017-09-29 09:00 | 2017-10-02 09:00 | N | Y | transmission line insulator replacement and maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RG7 (Rossdale - Garneau),Rossdale RG725 (Rossdale) | 2017-09-30 07:00 | 2017-10-01 17:00 | N | N | doble | Circuit Breaker, Line |  |  | Pre-Condition, Creates Radial Feeds
EPCOR | 987s T1 (987s Clover Bar),987s T3 (987s Clover Bar),987s C2402 (987s Clover Bar),987s C2403 (987s Clover Bar),987s C2401 (987s Clover Bar) | 2017-09-30 07:00 | 2017-09-30 17:00 | N | Y | disconnect replacement | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 987s T1 (987s Clover Bar),987s C2403 (987s Clover Bar),987s C2401 (987s Clover Bar) | 2017-09-30 07:01 | 2017-10-06 17:00 | N | Y | disconnect replacement | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2017-09-30 08:00 | 2017-09-30 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2017-09-30 12:00 | 2017-09-30 14:00 | N | N | fall substation washing | Line, Transformer |  | fall substation washing (Wash SW83 and 138kV PTs) | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2017-09-30 14:00 | 2017-09-30 18:00 | N | N | fall substation washing | Line, Shunts, Transformer |  | Fall Substation Washing (Wash SW84) | Pre-Condition
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2017-09-30 16:00 | 2017-09-30 21:00 | N | N | 11s reliability upgrade | Line |  | 11s reliability upgrade. Short out 138kV BD CTs | Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2017-09-30 16:00 | 2017-09-30 23:59 | N | N | 11s reliability upgrade and short out 138kV BD CTs | Transformer |  |  | For Information Only
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2017-09-30 21:00 | 2017-09-30 23:59 | N | N | 11s reliability upgrade, short duration outage required to short out BD CTs in order to move remove panel | Line |  | 11s reliability upgrade, short duration outage required to short out BD CTs in order to move remove panel | Pre-Condition, For Information Only
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2017-10-01 08:00 | 2017-10-01 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354s DVAR1 (354s Summerview),354s DVAR2 (354s Summerview) | 2017-10-01 08:00 | 2017-10-31 16:00 | N | N | maintenance | Shunts |  |  | For Information Only
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2017-10-01 12:01 | 2017-10-01 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s T4 (535s Joffre) | 2017-10-01 17:00 | 2017-10-05 17:00 | N | N | Nova switchgear testing | Transformer |  |  | For Information Only
ALTALINK | 40s 729E (40s Wetaskiwin),729L (40s Wetaskiwin - 729AL Tap) | 2017-10-02 06:00 | 2017-10-02 07:00 | N | N | breaker fail trip test from 40s858N | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 805s J2405 (805s Jasper) | 2017-10-02 07:00 | 2017-10-06 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ATCO | 7L78 (785s Judy Creek - 851s Morse River) | 2017-10-02 07:00 | 2017-10-16 16:00 | N | N | protection cutovers and CT wiring changes | Line |  | Protection cutovers and CT wiring changes
EPCOR | 330p 803 (330p Genesee) | 2017-10-02 07:00 | 2017-10-06 17:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin),40s 804W (40s Wetaskiwin) | 2017-10-02 07:01 | 2017-10-02 08:00 | N | N | [SWEATD] breaker fail trip test from 40s858N | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2017-10-02 07:15 | 2017-10-02 14:45 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 801L (62s Brazeau - 294s Brazeau Outlet Works),62s 201 (62s Brazeau) | 2017-10-02 07:30 | 2017-10-05 17:30 | N | Y | replacing 801L "A" protection | Circuit Breaker, Line |  |  | Overload, Restricts Generation
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2017-10-02 08:00 | 2017-10-14 09:16 | N | N | line protection upgrade | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 162s 240-RB132 (162s Beddington),918L (281s Johnson - 162s Beddington),162s 240-RB133 (162s Beddington) | 2017-10-02 08:00 | 2017-10-02 16:00 | N | Y | fall substation washing | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
CNRL | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2017-10-02 08:00 | 2017-10-04 18:00 | N | Y | transmission line insulator replacement and maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
BCH | 5L72 (Mica Creek - Nicola) | 2017-10-02 08:00 | 2017-10-06 16:00 | N | Y | replace spacers and arcing horns | Line |  | 5L72 OOS, MCA RMR: MCA PLANT limited by ambient temperature Replace spacers and arcing horns | Limits ATC
ATCO | 7L70 (700s Bonnyville - 707s St.Paul),700s 701 (700s Bonnyville) | 2017-10-02 08:00 | 2017-10-05 16:00 | N | N | routine maintenance on 701BKR (7L70) | Line, Circuit Breaker |  | Routine Maintenance on 701BKR (7L70), 7L70 will be open ended, 707S & 936S will be radial fed from 7L139 (819S Whitby) | Firm Load Loss, Creates Radial Feeds
ATCO | 7L701 (223s Strome - 7L701D1) | 2017-10-02 08:00 | 2017-10-05 17:00 | N | Y | 7L701 arm change | Line |  | 7L701 Arm Change | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 253S Blackie,253s C1 (253s Blackie),753L (65s High River - 253s Blackie),851L (525s Carseland - 253s Blackie),876L (179s Gleichen - 253s Blackie) | 2017-10-02 09:00 | 2017-10-02 17:00 | N | N | install piles in proximity to 753L/851L and the 138kV Bus | Station, Line, Shunts |  | Install Piles in proximity to 753L/851L and the 138kV Bus. This is prep work for Analog to Digital Station conversion that take splace in 2018 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 180s T2 (180s Cope Creek) | 2017-10-02 09:00 | 2017-12-01 11:00 | N | N | borrow the CT for switchgear replacement at 482s | Transformer
ATCO | 969s 701T (969s Lindbergh) | 2017-10-02 09:00 | 2017-10-02 16:00 | N | Y | repair NGR | Transformer |  | Repair NGR, During outage IPF site will be out, as well will have to island Pengrowth on the 25KV Feed. | Restricts Generation
ALTALINK | 520s T1 (520s Bennett) | 2017-10-02 09:30 | 2017-10-06 17:30 | N | Y | 500kV surge arrestor replacements | Transformer |  |  | 240 kV, Limits ATC, 500 kV
ALTALINK | 32s 22 (32s Barrier) | 2017-10-02 10:00 | 2017-10-02 14:00 | N | Y | top up gas | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 320p T1 (320p Keephills) | 2017-10-02 10:00 | 2017-12-12 16:00 | N | Y | urgent repair - forced outage | Transformer |  |  | 240 kV
ALTALINK | 149s C1 (149s Nisku),149s 3 (149s Nisku) | 2017-10-02 10:01 | 2017-10-02 11:00 | N | N | [SWEATD] breaker fail trip testing from 149s455 and 149s454 protection | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 946s 902 (946s Oakland) | 2017-10-02 13:24 | 2017-11-05 16:00 | N | N | forced outage (end date unknown) | Circuit Breaker |  |  | 240 kV
ALTALINK | 40s 81 (40s Wetaskiwin) | 2017-10-02 14:00 | 2017-10-02 15:00 | N | N | [SWEATD] breaker fail trip test from 40s858N | Circuit Breaker |  |  | For Information Only
ALTALINK | 253s C1 (253s Blackie) | 2017-10-02 17:00 | 2017-10-05 16:00 | N | N | construction work in close proximity - required for safety | Shunts |  |  | For Information Only
ENMAX | 693L (42s Sarcee - ENMAX 10) | 2017-10-02 23:15 | 2017-10-03 02:45 | N | Y | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 268s 199N (268s Whitecourt),199L (268s Whitecourt - 199L187B) | 2017-10-03 07:30 | 2017-10-10 12:30 | N | Y | Replace 199 line protection | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 149S Nisku | 2017-10-03 08:00 | 2017-10-03 09:00 | N | N | [SWEATD] 149s 45 breaker fail trip testing from 149s455 and 149s454 protection | Station |  |  | Pre-Condition, For Information Only
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac),162s 138-RB81 (162s Beddington),162s 138-RB80 (162s Beddington) | 2017-10-03 08:00 | 2017-10-03 16:00 | N | N | Fall Substation Washing | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 739L (305s Acheson - 434s Stony Plain) | 2017-10-03 08:00 | 2017-11-03 08:00 | N | N | [SWEATD] install the new 446L/453L to Acheson | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PT-341 (29EDD-34) | 2017-10-03 08:00 | 2017-11-17 18:00 | N | Y | project 1716 - Suncor Plant 300HV | Transformer |  | Project 1716 - Suncor Plant 300HV. The following equipment will be out of service for the duration of the work. 260kV - 260kV Transformer 29PT-341 - 260kV High side 260kV surge arresters - 260kV MOD 29PS-375 72kV - 72kV breaker 29-652-10301 with Isolating motorized switch 29PS-383 - 72kV breaker 29-652-10302 with Isolating motorized switches 29PS-381 & 29PS-382 - 72kV N/O Breaker 29-652-10200T with Isolating motorized switch 29PS-380 - 72kV CVT 29PT-345B - 72kV CVT 29PT-347 - 72kV NGR- 29PR-69 - XFMR LV side 72kV surge arresters | 240 kV, Pre-Condition, For Information Only
ALTALINK | 367s Harry Smith 138 kV Bus 1,367s T1 (367s Harry Smith),367s T2 (367S Harry Smith) | 2017-10-03 08:00 | 2017-10-26 09:00 | N | N | [SWEATD] move 367s 138kV lines to GOI, install the new 446L/453L to Acheson | Bus, Transformer
ATCO | 2029S DCF11 (2029s Heathfield) | 2017-10-03 08:00 | 2017-10-05 16:00 | N | Y | DC filter inspection at 2029S Heathfield | Terminal Equipment |  | DC filter inspection at 2029S Heathfield. Access filter bay for inspection. Will not be able to open DC filter at Newell. | Pre-Condition, 500 kV
ALTALINK | 755L (535s Joffre - 247s Piper Creek),535s 5452 (535s Joffre),535s 5552 (535s Joffre) | 2017-10-03 08:30 | 2017-10-03 17:30 | N | N | inspect and possibly replace drops on 755L A frame at 535s | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 17s T1 (17s Benalto) | 2017-10-03 08:30 | 2017-10-03 16:30 | N | N | doble T1 and SFRA | Transformer |  |  | For Information Only
ALTALINK | 511s SVC Plus (511s Crossings) | 2017-10-03 09:00 | 2017-10-05 17:00 | N | Y | SVCP protection settings test | Shunts |  | SVCP Protection Settings Test Will not impact the link dispatch. | Pre-Condition, 500 kV
AESO-SC | EMS | 2017-10-03 09:00 | 2017-10-04 16:00 | N | N | Flexpod Patching - Prod SDC & PDC - VMWare | SCInternal |  |  | For Information Only
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2017-10-03 10:00 | 2017-10-12 14:30 | N | Y | 17s6 breaker replacement & C60 relay replacement | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2017-10-03 11:00 | 2017-10-06 17:00 | N | Y | migrate controls, annunciation and analogs to new RTU | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 149S Nisku | 2017-10-03 11:00 | 2017-10-03 12:00 | N | N | [SWEATD] 149s 22 breaker fail trip testing from 149s455 and 149s454 protections | Station |  |  | Pre-Condition, For Information Only
Saskpower | SaskPower A1R | 2017-10-04 07:00 | 2017-10-04 08:30 | N | Y | high load move | Line |  |  | Limits ATC
EPCOR | 330p 1208 (330p Genesee) | 2017-10-04 07:00 | 2017-10-06 17:00 | N | Y | doble | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2017-10-04 07:30 | 2017-10-04 17:30 | N | N | bushing replacement | Transformer
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2017-10-04 08:00 | 2017-10-05 16:00 | N | N | salvage switches, 191s4, 191s10, 191s14 | Transformer |  |  | For Information Only
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2017-10-04 08:00 | 2017-10-04 12:00 | N | N | RTU upgrade & change out control relays | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake),63s 648 (63s Red Deer) | 2017-10-04 08:30 | 2017-10-04 15:30 | N | N | breaker maintenance 138kV DTI Alstom | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320P Keephills RTU/SCADA | 2017-10-04 09:00 | 2017-10-04 16:00 | N | N | salvage of tripping cct | Terminal Equipment |  | salvage of tripping cct on GT3 stub bus to KH3.
AESO-SC | EMS | 2017-10-04 09:00 | 2017-10-04 13:00 | N | N | Scheduled ALSTOM EMS power system database update | SCInternal |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3),3.84L (ENMAX 13 - ENMAX 3) | 2017-10-04 12:00 | 2017-10-04 18:00 | N | N | RTU upgrade & change out control relays | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 604L (149s Nisku - 155s Blackmud),149s 604 (149s Nisku) | 2017-10-05 06:00 | 2017-10-05 07:00 | N | N | [SWEATD] breaker fail trip testing from 149s455 and 149s454 protection | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 289s T1 (289s Saunders Lake) | 2017-10-05 07:00 | 2017-10-05 12:00 | N | N | [SWEATD] test energize to allow it to soak, then de- energize and move to GOI | Transformer
ENMAX | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington) | 2017-10-05 07:00 | 2017-10-08 15:00 | N | Y | switch repair, doble, fall substation washing | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 454L (149s Nisku - 289s Saunders Lake),149s 454 (149s Nisku) | 2017-10-05 07:01 | 2017-10-05 08:00 | N | N | [SWEATD] breaker fail trip testing from 149s455 protection | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 959s 901T (959s Lanfine) | 2017-10-05 08:00 | 2017-10-05 15:00 | N | Y | leak repair | Transformer |  | 959S Lanfine - 901T OOS for Leak Repair | 240 kV
CNRL | 75-PLH-902 (838s Horizon Mining - 849s Joslyn) | 2017-10-05 09:00 | 2017-10-06 09:00 | N | Y | transmission line insulator replacement and maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 289s T1 (289s Saunders Lake) | 2017-10-05 12:00 | 2017-11-03 14:00 | N | N | [SWEATD] T1 outage until 240 kV bus energization | Transformer
ALTALINK | 289s T2 (289s Saunders Lake) | 2017-10-05 17:00 | 2017-11-03 14:00 | N | N | [SWEATD] T2 outage until 240kV bus energization | Transformer
ENMAX | 162.1TR (ENMAX 162 Beddington),162s 240-RB131 (162s Beddington),162s 240-RB132 (162s Beddington),162s Beddington 240 kV North Bus | 2017-10-05 17:00 | 2017-10-08 20:00 | N | Y | SF6 gas sample, doble, switch maintenance, fall substation washing | Circuit Breaker, Transformer, Bus |  |  | 240 kV, Restricts Generation
ALTALINK | 740L (39s-426s-414s-527s-101s) | 2017-10-06 07:00 | 2017-10-06 14:00 | N | N | repair a damaged conductor - urgent | Line
ALTALINK | 719L (719L259A - 719L214N) | 2017-10-06 07:15 | 2017-10-07 17:45 | N | N | component replacements, structure replacements, crossarm replacements | Line |  |  | Pre-Condition, For Information Only
ENMAX | 38.1C (ENMAX 38) | 2017-10-06 08:00 | 2017-10-06 16:00 | N | N | line protection upgrade, re-wire trip circuits | Shunts |  |  | For Information Only
ALTALINK, ENMAX | 21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21),138-21.CAP (ENMAX 21) | 2017-10-06 12:00 | 2017-10-06 18:00 | N | N | fall substation washing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | 987s CC24 (987s Clover Bar) | 2017-10-07 07:00 | 2017-10-07 17:00 | N | N | doble | Circuit Breaker |  |  | Overload, Contingency Requires Mitigation
ENMAX | 162.1TR (ENMAX 162s Beddington),162s Beddington 138 kV North Bus | 2017-10-07 08:00 | 2017-10-07 18:00 | N | N | fall substation washing | Transformer, Bus |  |  | Pre-Condition, Overload
ALTALINK | 719L (719L259A - 719L214N) | 2017-10-08 07:15 | 2017-10-11 17:45 | N | N | structure replacements, install/commission new airbrake at str1, salvage airbrake at str214 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power),526L (268s Whitecourt - 526DL185),268s 268 (268s Whitecourt) | 2017-10-08 07:30 | 2017-10-08 12:30 | N | Y | cut in trips from 199L | Circuit Breaker, Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | RossdaleT4 (Rossdale) | 2017-10-09 07:00 | 2017-10-20 17:00 | N | N | doble/ PRD | Transformer
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2017-10-09 07:00 | 2017-10-09 17:00 | N | N | mine shut-down line maintenance | Line
ALTALINK | 5s C3 (5s East Calgary),5s 7 (5s East Calgary),5s C4 (5s East Calgary) | 2017-10-09 08:00 | 2017-10-09 16:00 | N | N | fall substation washing | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 33.2TR (ENMAX 33) | 2017-10-09 08:00 | 2017-10-12 16:00 | N | N | Reinhausen tap changer inspection, doble | Transformer
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek),48s38 (48s Pocaterra) | 2017-10-09 09:30 | 2017-10-09 21:00 | N | N | BCH switch repairs BCK 1D21 & BCK 1D22 | Line, Switch |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 826s 502R (826s Marguerite Lake) | 2017-10-09 17:00 | 2018-07-12 16:00 | N | N | techs found scorch marks on the reactor (forced outage) | Shunts |  |  | For Information Only
ALTALINK | 394s T2 (394s Empress),394s T4 (394s Empress),668L (394s Empress - 562s Cypress),394s Empress 138kV Bus 2,394s 952 (394s Empress) | 2017-10-10 07:00 | 2017-10-18 17:00 | N | N | add 138kV bus tie breaker and disconnect switch, replace line PT4, bus PT3, and 668L lightning arrestors | Line, Bus, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 816s P2404 (816s Petrolia) | 2017-10-10 07:00 | 2017-10-12 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 330p 802 (330p Genesee) | 2017-10-10 07:00 | 2017-10-13 17:00 | N | N | doble | Circuit Breaker
ATCO, ALTALINK | 9L950 (132s Ware Junction - 801s Anderson),801s 911 (801s Anderson),801s 912 (801s Anderson),132s 950N (132s Ware Junction) | 2017-10-10 07:00 | 2017-11-02 17:00 | N | Y | protection upgrade | Line, Circuit Breaker, Switch |  | Protection upgrade, 1 leg of breaker and a third scheme open @ 801s FS Switching to isolate 9L950. Isolation points to be 911A, 912A, and 9L950D2 @ Ware Junction PSE crew Disconnect and remove panels A20, B20 "Complete cutover of 9L950 ""A and B"" protection" Complete control wiring for 911, 911B, 912B, 9L950D1 Disconnect, cut off and remove tank ground CT's from 911PT, 911CT, 912CT Begin salvage Tank Gound yard cables, etc Commissioning Commission CT's, 21A, 21B, 49A protections, update 50BF/911 and 50BF/912 relay settings Commission 911, 911B, 912B, 9L950D1controls End to end tests with TOC and Ware Junction ASE Telecontrol programming Telecom Test comm to Ware Junction and Sheerness PSE crew Salvage work | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 202L (61s Lodgepole - 62s Brazeau),62s 202 (62s Brazeau) | 2017-10-10 07:30 | 2017-10-13 17:30 | N | Y | replace L2 A protection and trip testing | Circuit Breaker, Line |  | Replace L2 A protection, trip testing from new T3 and T7 protections | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 370s T3 (370s North Lethbridge),370s North Lethbridge 240kV Bus 1 | 2017-10-10 08:00 | 2017-10-12 17:00 | N | Y | replace 370s28 PT | Bus, Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 7L701 (757s Battle River - 7L701D2) | 2017-10-10 08:00 | 2017-10-12 17:00 | N | Y | 7L701 arm change | Line |  | 7L701 Arm Change | Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2017-10-10 08:00 | 2017-10-10 12:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX, ALTALINK | 12.2TR (ENMAX 12),833L (ENMAX 2 - ENMAX 12) | 2017-10-10 08:00 | 2017-10-10 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 62s Brazeau),61s 202X (61s Lodgepole),61s T2 (61s Lodgepole) | 2017-10-10 09:00 | 2017-10-13 17:30 | N | N | replacing 61s PT2 | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 185L (396s Pincher Creek - 379s Shell Canada Waterton) | 2017-10-10 09:15 | 2017-10-12 17:45 | N | N | structure repairs (61,67,121) | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1075L (132s Ware Junction - 28s West Brooks) | 2017-10-10 09:30 | 2017-10-12 17:00 | N | Y | replace 2 PTs at 28s40 | Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 535s T3 (535s Joffre) | 2017-10-10 09:30 | 2017-10-13 15:30 | N | N | upgrade 535s23 PT from 2 phase to 3 phase metering, replace 2 meters | Transformer
ALTALINK | 320p 989 (320p Keephills) | 2017-10-10 11:00 | 2017-10-10 17:00 | N | Y | migrate controls, annunciation and analogs to new RTU | Switch |  | migrate controls, annunciation and analogs to new RTU. Redundant protections will be taken out of service | 240 kV, For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt) | 2017-10-10 12:00 | 2017-10-10 17:00 | N | N | cut in trips from 199L | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 12.1TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12) | 2017-10-10 12:00 | 2017-10-10 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 217s C1 (217s North Red Deer),217s 652 (217s North Red Deer) | 2017-10-10 12:30 | 2017-10-12 15:00 | N | N | replace 217s652 breaker CT's | Shunts, Switch |  |  | For Information Only
ALTALINK | 71s T1 (71s Lamoureux),71s 152 (71s Lamoureux),71s Lamoureux 138 kV West Bus,71s12 ( 71s Lamoureux),71s14 (71s Lamoureux) | 2017-10-10 13:00 | 2017-10-12 17:00 | N | Y | replace 71s25 A phase PT & T1 leak repairs | Bus, Transformer, Circuit Breaker, Switch |  |  | Contingency Requires Mitigation
ALTALINK | 320p T4 (320p Keephills) | 2017-10-11 07:00 | 2017-10-12 17:00 | N | N | migrate controls, annunciation and analogs to new RTU | Transformer
ALTALINK | 118s T2 (118s Canmore) | 2017-10-11 07:15 | 2017-10-12 16:00 | N | N | create open point 'A' bird protection installation | Transformer
ALTALINK | 325s 852 (325s Leduc) | 2017-10-11 07:30 | 2017-10-11 12:30 | N | N | tank heater repair | Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2017-10-11 08:00 | 2017-10-11 12:00 | N | N | fall substation washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2017-10-11 08:00 | 2017-10-13 13:00 | N | N | forced outage | Transformer |  |  | Pre-Condition, Overload
ALTALINK | 191S N.W.Cardiff | 2017-10-11 09:00 | 2017-10-11 15:30 | N | N | repair control wiring | Station
Lethbridge | Lethbridge loss of visibility | 2017-10-11 10:15 | 2017-10-11 10:35 | N | N | ICCP points outage to replace 2 communication switches | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 250p11 (250p Bighorn) | 2017-10-11 11:00 | 2017-10-11 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2017-10-11 12:00 | 2017-10-11 18:00 | N | N | fall substation washing | Line, Transformer |  | . unable to wash 34.3TR due to station capacity and PT outage issues | Firm Load Loss, Creates Radial Feeds
AESO-SC | Phone Outage,AESO Network | 2017-10-12 | 2017-10-12 06:00 | N | N | maintenance on WAN network | SCInternal |  |  | For Information Only
Saskpower | SaskPower A1R | 2017-10-12 07:00 | 2017-10-12 12:00 | N | Y | high load move | Line |  |  | Limits ATC
ALTALINK | 835AL (454s Bucklake - 835L tap) | 2017-10-12 08:00 | 2017-10-12 12:00 | N | Y | tank heater modification | Line |  |  | Restricts Generation
ENMAX | 14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2017-10-12 08:00 | 2017-10-12 16:00 | N | N | fall substation washing | Line, Transformer |  | Fall Substation Washing. (Cannot take 138kV PTs out of service due to 11s 138kV BD). | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2017-10-12 08:00 | 2017-10-12 16:00 | N | N | doble 12B138 | Line, Circuit Breaker |  | Doble 12B138-832L | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2017-10-12 08:00 | 2017-10-12 16:00 | N | N | fall substation washing | Shunts |  |  | For Information Only
BCH | 5L71 (Mica Creek - Nicola) | 2017-10-12 08:00 | 2017-10-13 16:00 | N | Y | Kamloops transmission to replace spacers and arcing horns - BC maintenance does not affect AB ATC | Line | BC Outage Peak RC COS: 1-00508245 AB Peak RC COS# : 1-00518593 (W-E), 1-00518594 (E-W) | 5L71 OOS, MCA RMR: MCA PLANT limited by ambient temperature Kamloops Transmission to replace spacers and arcing horns | Limits ATC
ALTALINK | 250p22 (250p Bighorn) | 2017-10-12 09:00 | 2017-10-12 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 1053L (132s Ware Junction - 324s Cassils),324s Cassils 240kV Bus 1,324s 1052 (324s Cassils) | 2017-10-12 09:00 | 2017-10-12 17:00 | N | N | top up SF6 gas | Circuit Breaker, Bus, Line |  |  | 240 kV, Pre-Condition
ATCO | 7L14 (705s Kitscoty - 751s Hill) | 2017-10-12 13:00 | 2017-10-12 16:00 | N | N | pole change | Line |  | Pole change | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau T2 (Garneau) | 2017-10-12 23:00 | 2017-10-13 07:00 | N | N | cutover of new DFR | Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2017-10-13 08:00 | 2017-10-13 17:00 | N | N | 7L68 outage to complete 7L10 mitigation | Line |  | 7L68 outage to complete 7L10 mitigation | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1TR (ENMAX 21) | 2017-10-13 08:00 | 2017-10-29 16:00 | N | N | bushing/CT replacement, diff relay replacement & bushing gasket replacement. | Transformer
ATCO | 2015s 901T (2015s Yeo) | 2017-10-13 08:00 | 2017-10-17 18:00 | N | Y | forced/emergency outage | Transformer |  |  | 240 kV
ATCO | 939s 911 (939s Livock) | 2017-10-13 11:00 | 2017-10-13 13:00 | N | N | top up leaking breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 6L05 (764s Heisler - 843s Bigknife Creek) | 2017-10-13 16:00 | 2017-10-13 20:37 | N | N | forced/emergency outage | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau T3 (Garneau) | 2017-10-14 06:30 | 2017-10-14 18:00 | N | N | cutover of new DFR | Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2017-10-14 07:15 | 2017-10-15 14:45 | N | N | structure replacement, line clearance mitigation | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2017-10-14 08:00 | 2017-10-14 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.1TR (ENMAX 21),21.4TR (ENMAX 21),21.80L (42s Sarcee - ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2017-10-14 08:00 | 2017-10-15 16:00 | N | Y | TR bushing/CT replacement and diff relay replacement | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.1TR (ENMAX 21),21.4TR (ENMAX 21),21.80L (42s Sarcee - ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2017-10-14 12:00 | 2017-10-14 16:00 | N | Y | fall substation washing | Line, Transformer
EPCOR | Garneau T1 (Garneau) | 2017-10-15 06:30 | 2017-10-15 18:00 | N | N | cutover of new DFR | Transformer
ALTALINK | 914L (86s Bigstone - 89s Ellerslie),910L (89s Ellerslie - 288s Wolf Creek) | 2017-10-15 07:00 | 2017-10-23 07:59 | N | Y | [SWEATD] remove span of 910L conductor, install 910/914L50 & 1112/1140L50 structures,remove span of 910L conductor, install 910/914L50 & 1112/1140L50 structures | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
CMH, Medicine Hat | MH69s3 MH69_302 (MH69s3 South Ridge),MH69s6 MH69_611 (MH69s6 Riverview),20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2017-10-15 07:00 | 2018-02-28 17:00 | N | N | pole replacement work | Line, Circuit Breaker
ALTALINK | 719L (256s Harmattan - 719L134) | 2017-10-15 07:15 | 2017-10-15 17:45 | N | Y | component replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
Syncrude | Aurora UT2 (Aurora) | 2017-10-16 07:00 | 2017-10-27 20:00 | N | N | replace switches | Transformer |  |  | For Information Only
ALBIAN | 920s 901T (920s Jackpine) | 2017-10-16 07:00 | 2017-10-19 18:00 | N | Y | 901T maintenance | Transformer |  | CNRL 901T maint, customer outage will result | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 840S McNeill Station | 2017-10-16 07:00 | 2017-11-03 10:00 | N | Y | McNeill 2017 fall turn around, site shut down for maintenance work. | Station |  | McNeill 2017 Fall turn around. Site shut down for maint. work. | Limits ATC
EPCOR | 805s J2406 (805s Jasper) | 2017-10-16 07:00 | 2017-10-20 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72CK12 (987s Clover Bar - Kennedale),Kennedale K722 (Kennedale),Kennedale T2 (Kennedale),Kennedale KDS6 (Kennedale) | 2017-10-16 07:00 | 2017-10-27 17:00 | N | N | temp monitor install | Transformer, Line, Circuit Breaker, Switch |  |  | Creates Radial Feeds
ALTALINK | 719L (263s Strachan - 719L259C) | 2017-10-16 07:15 | 2017-10-18 17:45 | N | N | component replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2017-10-16 07:30 | 2017-10-31 17:30 | N | Y | replacing 347s199W with a new SF6 breaker and adding LA's to 199L | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2017-10-16 08:00 | 2017-10-27 16:00 | N | Y | relay upgrades | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1TR (ENMAX 14) | 2017-10-16 08:00 | 2017-10-29 16:00 | N | N | replacing panels at 14s | Transformer |  |  | For Information Only
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2017-10-16 08:00 | 2017-10-20 16:00 | N | Y | 11s reliability upgrade, restring line over CP tracks, terminate 11.83L on new structure | Line |  |  | Pre-Condition
BCH | 5L72 (Mica Creek - Nicola) | 2017-10-16 09:00 | 2017-10-20 16:00 | N | Y | replace spacers and arcing horns - BC maintenance does not affect AB ATC | Line | BC Peak RC COS#: 1-00511215 and 1-00518441 AB Peak RC COS# : 1-00520389 (W-E), 1-00520393 (E-W) |  | Limits ATC
ALTALINK | 523s T1 (523s Bullshead) | 2017-10-16 09:00 | 2017-10-17 16:00 | N | N | investigating chattering contact on 523s389 and creating Open Point 'A' for future outage on 523s T2 | Transformer |  |  | For Information Only
ALTALINK | 95s T2 (95s Imperal Oil Edmonton) | 2017-10-16 09:30 | 2017-10-25 16:30 | N | N | bushing replacement and bushing monitor install | Transformer |  |  | For Information Only
ALTALINK | 118s T1 (118s Canmore) | 2017-10-16 10:45 | 2017-10-18 17:00 | N | N | bird protection installation: risers, bus supports, T1 LA's, T1 TC filter bus supports | Transformer |  |  | For Information Only
ALTALINK | 320p 1352 (320p Keephills) | 2017-10-16 11:00 | 2017-10-17 17:00 | N | Y | migrate controls, annunciation and analogs to new RTU | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 370s 56 (370s North Lethbridge),370s 23 (370s North Lethbridge),967L (370s North Lethbridge - 138s Windy Flats) | 2017-10-16 11:30 | 2017-10-19 17:00 | N | N | replace 370s17 CVTs | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs),71s 1652 (71s Lamoureux),71s 1552 (71s Lamoureux) | 2017-10-16 13:00 | 2017-10-19 17:00 | N | Y | replace 71s23 240kV VTs | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2029s ACF14 (2029s Heathfield),2029s ACF11 (2029s Heathfield),2029s ACF12 (2029s Heathfield),2029s ACF13 (2029s Heathfield) | 2017-10-17 07:00 | 2017-10-20 17:00 | N | Y | ACF1 filter bank inspection | Shunts |  | ACF1 filter Bank inspection, Inspections required for ACF11, ACF12, ACF13 and ACF14, HVDC Power limit of 750MW, When ACF1 is taken out of service we loose our shunt reactor which will put us in a low voltage mode until power transfer is set somewhere above 300MW. Once above 300MW the voltage will be back to 500KV DC and we will still have ramp capabilities to 750MW. | For Information Only, 500 kV
ATCO | 7L696 (508s Lakesend - 892s Ribstone Creek) | 2017-10-17 07:00 | 2017-10-19 17:00 | N | Y | mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost | Line |  | To mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost. This mitigation is to install inter phase spacers between A and C phase so that they cannot get close to each other as frost comes off of the wire. | For Information Only
EPCOR | 72CH9 (Hardisty - 987s Clover Bar),Hardisty H724 (Hardisty Epcor),Hardisty H723 (Hardisty Epcor) | 2017-10-17 07:00 | 2017-10-17 12:00 | N | N | close HAB3 and restore Tx3 @ Hardisty S/S | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 806 (330p Genesee) | 2017-10-17 07:00 | 2017-10-19 17:00 | N | N | urgent repair because of nitrogen leaking | Circuit Breaker |  | urgent work for 330p Genesee breaker 806 because of Nitrogen leaking | Pre-Condition
ATCO | 7L79 (771s Veteran - 892s Ribstone Creek),7L79 (771s Veteran - 932s Pemukan) | 2017-10-17 07:00 | 2017-10-19 17:00 | N | N | mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost | Line |  | To mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost. This mitigation is to install inter phase spacers between A and C phase so that they cannot get close to each other as frost comes off of the wire. | For Information Only
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2017-10-17 07:15 | 2017-10-21 17:45 | N | N | line clearance mitigation | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2017-10-17 08:00 | 2017-10-18 16:00 | N | N | capacitor bank maintenance 14.2CAP | Shunts |  |  | For Information Only
ATCO | 828s 507C1 (828s Sulphur Point),828s 507C2 (828s Sulphur Point) | 2017-10-17 09:00 | 2017-10-18 17:00 | N | N | repair and test capacitor wafers on 507C1 | Shunts |  | Repair and Test Capacitor Wafers on 507C1, 507 Capacitor out of service for the duration of the work | For Information Only
ALTALINK | 61L (252s Jarrow - 61DL386) | 2017-10-17 09:30 | 2017-10-17 17:00 | N | N | salvage 61L | Line |  | Salvage 61L - Currently has Open Point 'A' at the end of the line
ALTALINK | 349S Stavely | 2017-10-17 10:00 | 2017-10-17 16:00 | N | Y | standard relay maintenance on 14L_349S10 | Station |  | Techs to complete standard relay maintenance on 14L_349S10 67/67N/79/L1 SEL351S and also test some feeder protection alarms that were not tested late last year. | Restricts Generation
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2017-10-17 17:03 | 2017-10-31 15:00 | N | N | forced outage (structures down) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2017-10-17 17:33 | 2017-10-19 17:00 | N | N | forced outage | Line |  |  | 240 kV
ATCO | 2015s 902T (2015s Yeo) | 2017-10-17 18:01 | 2017-10-20 18:00 | N | Y | forced/emergency outage | Transformer |  |  | 240 kV
ALTALINK | 523s T2 (523s Bullshead) | 2017-10-18 06:30 | 2017-10-18 14:30 | N | N | installing bird coverup on 523s589 | Transformer |  |  | For Information Only
ALTALINK | 834L (384s Keystone - 320p Keephills),384s 834 (384s Keystone) | 2017-10-18 07:30 | 2017-10-18 12:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 6.80L (ENMAX 30 - ENMAX 6) | 2017-10-18 08:00 | 2017-10-18 17:00 | N | N | isolate line for testing purposes | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 618s 725N (618s Riverbend) | 2017-10-18 09:00 | 2017-10-18 16:00 | N | Y | techs to change CT ratio from 400:5 to 800:5 | Circuit Breaker |  | At the request of Op Eng. Techs to change CT ratio from 400:5 to 800:5. Relay setting will not be changed. In conjunction with City Of Leth. and AML outage. | For Information Only
ALTALINK | 394s T1 (394s Empress),394s T3 (394s Empress),760L (394s Empress - 163s Amoco Empress),394s Empress 138kV Bus 1 | 2017-10-18 09:01 | 2017-10-26 17:00 | N | N | install new 138kV bus PT & bird cover | Transformer, Line, Bus |  | Install new 138kV bus PT. Install bird cover on 25kV equipment. Replace line PT5 and 760L lightning arrestors. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 523s T1 (523s Bullshead) | 2017-10-18 14:30 | 2017-10-18 17:30 | N | N | closing open point 'A' | Transformer |  |  | For Information Only
EPCOR | 72MG16 (Meadowlark - Garneau) | 2017-10-19 07:00 | 2017-10-20 17:00 | N | N | cutover of new DFR | Line |  |  | Pre-Condition, Contingency Requires Mitigation
EPCOR | RossdaleT4 (Rossdale) | 2017-10-19 07:00 | 2017-10-19 17:00 | N | N | doble | Transformer |  |  | For Information Only
ALTALINK | 118s T2 (118s Canmore) | 2017-10-19 07:15 | 2017-10-19 14:00 | N | N | close open point 'A' | Transformer
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2017-10-19 08:00 | 2017-10-19 16:00 | N | N | fix hotspot on SW89 at ENMAX 9 | Line, Transformer |  |  | Pre-Condition, Overload
ALTALINK | 123S Banff | 2017-10-19 08:30 | 2017-10-19 13:30 | N | N | 123s1152 relay maintenance | Station
ALTALINK | 353S Plamondon | 2017-10-19 08:30 | 2017-10-19 13:30 | N | N | 353s2073 relay maintenance | Station
AESO-SC | EMS | 2017-10-19 09:00 | 2017-10-19 16:00 | N | N | upgrade switch and patching | SCInternal
ALTALINK | 784L (332s Ellis - 784AL tap),332s 784 (332s Ellis) | 2017-10-19 09:00 | 2017-10-19 13:00 | N | N | heater modification on 138kV SF6 breaker, warranty work | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 826s 702 (826s Marguerite Lake) | 2017-10-19 15:00 | 2017-11-03 17:00 | N | N | emergency outage for low SF6 gas | Circuit Breaker |  | Atco has requested to SC to take an emergency outage on breaker 702 @ 826s Marguerite. The breaker has low SF6 gas.
ALTALINK | 287S Hazelwood,287s T1 (287s Hazelwood) | 2017-10-20 | 2017-10-22 23:00 | N | N | ISD: Oct 18, 2017 | Station, Transformer
ALTALINK | 1082L (63s Red Deer - 287s Hazelwood),420L (214s Innisfail - 287s Hazelwood),419L (214s Innisfail - 287s Hazelwood),929L (63s Red Deer - 287s Hazelwood) | 2017-10-20 | 2017-10-21 23:00 | N | N | ISD: Oct 18, 2017 | Line
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2017-10-20 11:00 | 2017-10-20 15:30 | Y | Y | emergency insulator repairs | Line | Peak RC COS outage ID: 1-00521711 Peak RC Path Derate ID: 1-00521712 (E>W), 1-00521716 (W>E) |  | Limits ATC, 500 kV
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2017-10-21 07:00 | 2017-10-22 16:00 | N | N | install new duct between MHs 0045-0046 at 9 ave and 7st SW | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s T5 (62s Brazeau),62s 207 (62s Brazeau) | 2017-10-21 07:30 | 2017-10-21 14:00 | N | Y | wiring cutovers and trip tests from new T3 & T7 protections | Circuit Breaker, Transformer |  |  | Overload, Restricts Generation
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2017-10-21 09:00 | 2017-10-21 18:00 | N | N | Fall substation washing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 514L (513s Lundbreck - 514L198) | 2017-10-21 09:15 | 2017-10-22 17:45 | N | N | emergency repair; pole replacement due to wind storm | Line
ALTALINK | 102s SVC (102s Langdon) | 2017-10-21 18:09 | 2017-10-27 18:00 | N | Y | forced out | Shunts |  |  | 240 kV
EPCOR | Meadowlark M722 (Meadowlark) | 2017-10-22 07:00 | 2017-10-22 17:00 | N | N | maintneance | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2017-10-22 08:00 | 2017-10-22 16:00 | N | Y | SWCRR project, contractor requires outage to relocate 7.82L anchors at 42s | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2017-10-22 08:00 | 2017-10-22 16:00 | N | Y | fall substation washing | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2017-10-23 07:00 | 2017-10-27 12:00 | N | N | 9th ave bridge. GLTW | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 2075S Newell | 2017-10-23 07:00 | 2017-10-27 10:00 | N | N | 2075S VCS pump alignment | Station |  | 2075S LOP #711 VCS Pump Alignment- Warranty We will need to take each DIW and Glycol pump ( one at a time ) out of service to perform required maintenance. Redundancy in place, No work to be completed on operating pump | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2017-10-23 07:00 | 2017-10-27 17:00 | N | N | MDS1 disconnect replacement/switching demonstration | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 557s T1 (557s Castle Downs) | 2017-10-23 07:00 | 2017-10-27 17:00 | N | Y | DGA monitor | Transformer |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2017-10-23 08:00 | 2017-10-23 18:00 | N | Y | fall substation washing | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 914L (86s Bigstone - 89s Ellerslie),89s 1052 (89s Ellerslie),89s 952 (89s Ellerslie),910L (89s Ellerslie - 288s Wolf Creek),288s 452 (288s Wolf Creek),288s 552 (288s Wolf Creek) | 2017-10-23 08:00 | 2017-10-30 18:00 | N | Y | [SWEATD] remove span of 910L conductor, 910L P&C work at 89s | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33) | 2017-10-23 08:00 | 2017-10-27 16:00 | N | N | doble TR | Transformer |  |  | For Information Only
ATCO | 715s 703T (715s Leming Lake) | 2017-10-23 09:00 | 2017-10-24 16:00 | N | N | emergency repair of leaking transformer | Transformer |  |  | For Information Only
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2017-10-23 09:15 | 2017-10-27 17:45 | N | N | line clearance mitigation | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 945s T2 (945s Sunshine Village) | 2017-10-23 09:30 | 2017-10-27 16:00 | N | N | breaker replacement | Transformer |  | breaker replacement (945s7) | For Information Only
ALTALINK | 214S Innisfail | 2017-10-23 10:45 | 2017-10-23 12:15 | N | Y | breaker 2047W (feeder 2047) remove TPR module which disables 2047 L protection | Station |  | 214s2047W Open breaker advice, remove TPR module which disables 2047 L protection | Restricts Generation
ALTALINK | 370s 172E (370s North Lethbridge) | 2017-10-23 11:30 | 2017-10-25 17:30 | N | N | replace 370s172E breaker CT's | Circuit Breaker |  | Replace 370s172E Breaker CT's | Pre-Condition, For Information Only
ALTALINK | 650s 852 (650s Hansman Lake) | 2017-10-23 11:30 | 2017-10-23 19:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 61s T1 (61s Lodgepole),202L (61s Lodgepole - 202L335),836L (61s Lodgepole - 283s Violet Grove) | 2017-10-23 12:00 | 2017-10-25 13:00 | N | Y | T1 bushing replacement | Transformer, Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 151s T1 (151s Strathmore) | 2017-10-23 12:00 | 2017-10-26 16:30 | N | N | 138 kV and 25 kV bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 244s 3752 (244s Bowmanton) | 2017-10-23 13:00 | 2017-10-23 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 320p 989 (320p Keephills) | 2017-10-23 15:00 | 2017-11-20 19:00 | N | N | required for clearance on 320pT1 | Switch |  |  | 240 kV, For Information Only
ALTALINK | 58s T1 (58s Edson) | 2017-10-24 07:00 | 2017-10-25 18:00 | N | N | install bird cover-up | Transformer |  | 58s1, AMI (81B37613UDS), 58s38, 58s42, 58s41, 377LE (377L1), 334LW (334L1) | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2017-10-24 08:00 | 2017-10-24 16:00 | N | N | fall substation washing | Shunts |  |  | For Information Only
ALTALINK | 244s 2152 (244s Bowmanton) | 2017-10-24 08:00 | 2017-10-24 12:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 648s T3 (648s Metiskow) | 2017-10-24 08:00 | 2017-10-26 16:00 | N | Y | transformer maintenance | Transformer |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2017-10-24 08:00 | 2017-11-02 17:15 | N | Y | line maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2017-10-24 08:00 | 2017-10-24 16:00 | N | N | fall substation washing - 36sub | Line |  |  | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | Northwestern Energy BUCC test | 2017-10-24 08:00 | 2017-10-24 12:00 | N | N | BUCC test | Station |  |  | Affects Visibility
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2017-10-24 08:00 | 2017-10-24 16:00 | N | N | replace broken and burnt conductors | Line |  | urgent outage on 15.62L to replace broken and burnt conductors due to a third party accident with pole at 15 sub. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s 2252 (244s Bowmanton) | 2017-10-24 13:00 | 2017-10-24 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 244s 2552 (244s Bowmanton) | 2017-10-25 08:00 | 2017-10-25 12:00 | N | N | warranty tank heater modification. | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2017-10-25 08:00 | 2017-10-25 12:00 | N | N | fall substation washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds, For Information Only
ENMAX | 34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2017-10-25 12:00 | 2017-10-25 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 61s T1 (61s Lodgepole) | 2017-10-25 12:00 | 2017-10-26 18:00 | N | Y | T1 bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 244s 2652 (244s Bowmanton) | 2017-10-25 13:00 | 2017-10-25 17:00 | N | N | warranty tank heater modification. | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 205S Castle Rock Ridge | 2017-10-26 06:00 | 2017-10-26 20:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ALTALINK | 205s13 (205s Castle Rock Ridge) | 2017-10-26 06:00 | 2017-10-26 20:00 | N | Y | customer maintenance | Switch |  | Advice for customer | 240 kV, Restricts Generation
ALTALINK | 368s 879 (368s Burdett),879L (368s Burdett - 244s Bowmanton) | 2017-10-26 08:00 | 2017-10-26 14:00 | N | N | warranty tank heater modification. | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | Northwestern Energy BUCC test | 2017-10-26 08:00 | 2017-10-26 12:00 | N | N | BUCC test | Station |  |  | Affects Visibility
ALTALINK | 244S 2952 (244S BOWMANTON) | 2017-10-26 08:00 | 2017-10-26 12:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
Lethbridge | 674s 725W (674s Lethbridge Bowron) | 2017-10-26 15:00 | 2017-10-26 16:00 | N | N | breaker fail test - emergency | Circuit Breaker |  |  | Pre-Condition, For Information Only
ATCO | 2033s 701 (2033s Mowat) | 2017-10-27 10:00 | 2017-10-28 17:00 | N | N | investigate leak, top up, on 701 breaker | Circuit Breaker |  | investigate leak, top up, on 701 Bkr change settings on Bkr 511 and 513, sub will be off loaded to adjacent Substations | For Information Only
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2017-10-27 12:00 | 2017-10-29 22:00 | N | N | 9th ave bridge. GLTW | Line |  |  | Pre-Condition
EPCOR | 240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2017-10-28 07:00 | 2017-10-28 17:00 | N | Y | oil samples | Line |  |  | 240 kV
EPCOR | RossdaleT1 (Rossdale) | 2017-10-28 07:00 | 2017-10-29 17:00 | N | N | dutting over and commissioning new metering CT connection | Transformer
ALTALINK, ENMAX | 37.82L (74s Janet - ENMAX 37),74s 37.82W (74s Janet) | 2017-10-28 08:00 | 2017-10-29 17:00 | N | Y | maintain 138kV minimum oil breaker S&S HPF | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L77 (Revelstoke - Ashton Creek) | 2017-10-29 09:00 | 2017-10-29 17:00 | N | Y | black start testing - BC maintenance does not affect AB ATC | Line | Peak COS outage ID: 1-00518801 Peak Path COS ID: 1-00523206 (E>W), 1-00523207 (W>E) |  | Limits ATC, 500 kV
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2017-10-29 22:01 | 2017-10-30 04:00 | N | N | 9th ave bridge, GLTW, line outage to re-install 5s portion | Line |  |  | Pre-Condition
MONTANA | MATL (120s Picture Butte - Montana) | 2017-10-30 02:50 | 2017-11-03 20:00 | N | Y | 120s PST issue and testing | Line | PEAK COS outage ID:1-00524413 PEAK COS path de-rate ID1-00524416 (N-S), (S-N)1-00524418 |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1081L (17s Benalto - 281s Johnson),17s 3 (17s Benalto),17s 2 (17s Benalto),281s 1081 (281s Johnson) | 2017-10-30 06:30 | 2017-11-09 15:00 | N | N | 17s3 breaker & C60 relay replacement & PMU wiring & airbreak module replacement | Line, Circuit Breaker, Switch |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2017-10-30 07:00 | 2017-11-10 17:00 | N | N | cutover of new line protection | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark M724 (Meadowlark),Meadowlark M723 (Meadowlark),Meadowlark T3 (Meadowlark) | 2017-10-30 07:00 | 2017-11-03 17:00 | N | N | PRD replacement | Transformer, Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 745s 601T (745s Slave Lake),745s 601 (745s Slave Lake) | 2017-10-30 07:00 | 2017-12-04 17:00 | N | N | replace foundations in 25 kV bay | Transformer, Circuit Breaker |  | Replace foundations in 25 kv bay, 25kV load will be transferred to adjacent subs, no impact to 72kV. | For Information Only
ENMAX | 8.1TR (ENMAX 8) | 2017-10-30 08:00 | 2017-11-03 16:00 | N | N | bushing replacement (LV) | Transformer |  |  | For Information Only
ENMAX | 2.3TR (ENMAX 2) | 2017-10-30 08:00 | 2017-10-31 16:00 | N | N | doble 2.3TR secondary cables | Transformer |  |  | For Information Only
ENMAX | 21.4TR (ENMAX 21) | 2017-10-30 08:00 | 2017-11-06 16:00 | N | N | transformer differential relay replacement | Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (245s Seebe - 3L145) | 2017-10-30 09:30 | 2017-11-02 17:00 | N | N | replace 245s27 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 945s T1 (945s Sunshine Village) | 2017-10-30 09:30 | 2017-11-03 16:00 | N | N | breaker replacement (945s10) | Transformer |  |  | For Information Only
ALTALINK | 163s 1752 (163s Amoco Empress) | 2017-10-30 10:30 | 2017-11-16 15:00 | N | Y | replace 163s1752 breaker to new SF6 type | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 385s T2 (385s Spring Coulee) | 2017-10-30 12:00 | 2017-11-05 09:30 | N | N | replacing motor mechanics on 385s9 | Transformer |  |  | For Information Only
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2017-10-30 12:30 | 2017-10-30 17:30 | N | Y | create open point 'A' at Str44; 492s load to remain online | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
REDDEER | 217s T2 (217s North Red Deer) | 2017-10-30 12:30 | 2017-11-02 15:00 | N | N | replace Altalink revenue metering CT's on T2 | Transformer |  |  | For Information Only
ALTALINK | 244s 3052 (244S Bowmanton) | 2017-10-30 13:00 | 2017-10-30 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ENMAX | 39.4TR (ENMAX 39) | 2017-10-30 16:00 | 2017-11-13 16:00 | N | N | bushing/CT replacement | Transformer |  | TR Bushing/CT replacement. TR DIFF Relay Replacement. 39.4TR will be out of service due to 25kV bus diff function testing Oct 30th. (Outage required on 22.81L for crane) | For Information Only
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2017-10-30 17:30 | 2017-11-19 08:30 | N | Y | component replacements, re-string on multiple sections | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 910L (89s Ellerslie - 288s Wolf Creek),288s 452 (288s Wolf Creek),288s 552 (288s Wolf Creek) | 2017-10-30 18:01 | 2017-11-09 07:00 | N | Y | 910L P&C work at 288s,910L P&C work at 89s | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2017-10-31 08:00 | 2017-10-31 18:00 | N | N | TR bushing/CT replacement for 39.4TR | Line |  | TR Bushing/CT replacement for 39.4TR. (Outage required on 22.81L for crane) | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s 3152 (244s Bowmanton) | 2017-10-31 08:00 | 2017-10-31 12:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 65s T2 (65s High River) | 2017-10-31 08:00 | 2017-11-07 17:00 | N | N | reclaim T2 oil, doble and maintain | Transformer |  |  | For Information Only
ALTALINK | 325s C1 (325s Leduc) | 2017-10-31 08:00 | 2017-11-12 16:00 | N | N | in service date: Dec 12, 2017. | Shunts
ALTALINK | 262s T1 (262s Rocky Mountain House),870L (262s Rocky Mountain House - 263s Strachan),262s 870W (262s Rocky Mountain House) | 2017-10-31 09:00 | 2017-10-31 17:30 | N | Y | breaker maintenance | Circuit Breaker, Transformer, Line |  | Fix leaky head, change seal in breaker head on one phase. 262s65 will also need to be repaired. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s 3252 (244s Bowmanton) | 2017-10-31 13:00 | 2017-10-31 17:00 | N | N | warranty tank heater modification | Circuit Breaker |  |  | Pre-Condition
ALTALINK, ENMAX | 916L (42s Sarcee - 5s East Calgary),693L (42s Sarcee - ENMAX 10) | 2017-11-01 07:00 | 2017-12-16 10:00 | N | Y | [SWCRR] 916L and 693L to move U/G for a portion, connect new U/G cables at both ends | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 121s T5 (121s Brooks) | 2017-11-01 07:00 | 2017-11-01 11:00 | N | N | replacing SS1, 121s44 and 121s45 | Transformer
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2017-11-01 07:15 | 2017-11-03 17:45 | N | N | structure repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 364s 3052 (364s Whitecourt Industrial) | 2017-11-01 07:30 | 2017-11-01 12:30 | N | N | tank heater repair | Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10),ENMAX 10 B138-693 (ENMAX 10) | 2017-11-01 08:00 | 2017-11-02 16:00 | N | N | SF6 gas sample | Circuit Breaker, Line |  |  | For Information Only
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2017-11-01 08:00 | 2017-11-01 15:00 | N | N | change poles from test and treat | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37) | 2017-11-01 08:00 | 2017-11-12 16:00 | N | Y | line protection upgrade | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.4TR (ENMAX 2) | 2017-11-01 08:00 | 2017-11-02 16:00 | N | N | doble 2.4TR secondary cables | Transformer
ALTALINK | 80AL (212s N.E.Lacombe - 958s West Lacombe),212s 80 (212s N.E. Lacombe) | 2017-11-01 08:00 | 2017-11-01 12:00 | N | N | warranty tank heater modification | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 (38s East Edmonton) | 2017-11-01 09:00 | 2017-11-03 19:00 | N | N | fence replacement between capacitor banks | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2017-11-01 09:00 | 2017-11-02 19:00 | N | N | fence replacement between capacitor banks | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 385S Spring Coulee | 2017-11-01 12:00 | 2017-11-05 09:00 | N | N | replacement of 69kV VT1 and junction box | Station
ALTALINK | 798L (364s Whitecourt Industrial - 77s Sagitawah),364s 798 (364s Whitecourt Industrial) | 2017-11-01 12:30 | 2017-11-01 17:30 | N | N | tank heater repair | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 423L (212s N.E.Lacombe - 332s Ellis),212s 423 (212s Lacombe) | 2017-11-01 13:00 | 2017-11-01 17:00 | N | N | warranty tank heater modification | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2017-11-01 23:00 | 2017-11-02 02:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2017-11-02 02:00 | 2017-11-07 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 121s T2 (121s Brooks) | 2017-11-02 07:00 | 2017-11-02 11:00 | N | N | replacing SS2, 121s46 and 121s45 | Transformer
ALTALINK | 454L (149s Nisku - 289s Saunders Lake) | 2017-11-02 07:30 | 2017-11-02 17:00 | N | N | [SWEATD] setting changes to A&B line protection relays at 149s and 289s, CT ratio change at 149s | Line |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),364s 797 (364s Whitecourt Industrial) | 2017-11-02 07:30 | 2017-11-02 12:30 | N | N | tank heater repair | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 945s T2 (945s Sunshine Village) | 2017-11-02 08:00 | 2017-11-02 17:00 | N | N | 945s11 switch replacement | Transformer
SUNCOR | 635EDD-1000 635PK-1000 (635EDD-1000),635EDD-1000 635PK-1001 (635EDD-1000) | 2017-11-02 08:00 | 2017-11-03 17:00 | N | N | capacitor bank protection setting change and test activities | Shunts |  |  | For Information Only
ATCO | 801s 911A (801s Anderson) | 2017-11-02 08:00 | 2017-11-02 16:00 | N | N | test 911A new control logic while de-coupled | Switch |  | Test 911A new control logic while de-coupled | 240 kV
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2017-11-02 08:00 | 2017-11-02 15:00 | N | N | snow storm repairs | Line |  | Snow Storm Repairs | Pre-Condition
ALTALINK | 446L (305s Acheson - 367s Harry Smith) | 2017-11-03 | 2017-11-05 23:00 | N | N | ISD: Nov 3, 2017 | Line
ALTALINK | 453L (305s Acheson - 367s Harry Smith) | 2017-11-03 | 2017-11-05 23:00 | N | N | ISD: Nov 3, 2017 | Line
ALTALINK | 367S Harry Smith | 2017-11-03 | 2017-11-05 23:00 | N | N | 138 kV bus. ISD: Nov 3, 2017 | Station
ALTALINK | 452L (434s Stony Plain - 367s Harry Smith) | 2017-11-03 | 2017-11-05 23:00 | N | N | ISD: Nov 3, 2017 | Line
ATCO | 9L97 (946s Oakland - 801s Anderson) | 2017-11-03 07:00 | 2017-11-14 15:00 | N | Y | protection upgrade | Line |  | Protection upgrade, see following outage sequence; Nov 3 7:00-Nov 13 15:00 Permit - 9L97 OOS (2-36261A) Isolation points - - 905A, 906A @ 801S Anderson, 9L97D2 @ 946S Oakland Nov 13 15:01 - Nov 17 15:00 Expand GOI to include 9L99 Permit - 9L97 & 9L99 OOS (2-36261B) Isolation points - 9L97D2 @ 946S Oakland, 905A, 907B @ 801S Anderson, Nov 17 15:01 - Nov 20 15:00 Shrink GOI Permit - 9L99 OOS 2-36261C, then re-energize 9L97 Isolation points - 906B, 907B @ 801S Anderson, Nov 20 15:01 - Dec 4 17:00 Expand GOI to include 9L933 Permit - 9L933 & 9L99 OOS (2-36261D) Isolation points - 906B, 908A @ 801S Anderson, COG from Altalink on 9L933 at 132S Ware Junction | 240 kV, For Information Only
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2017-11-03 07:15 | 2017-11-24 18:15 | N | N | structure/conductor/OHSW repair and maintenance | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH, AESO-SC | 2L113 (B1s Natal - B2s Cranbrook),Natal T3 (BCH Natal),Natal T4 (BCH Natal) | 2017-11-03 08:00 | 2017-11-03 16:00 | N | Y | pin and glass replacements at BC Natal | Line, Transformer | Peak RC COS Path #: 1-00524977, 1-00524979 Peak RC COS Outage # (BCH outage): 1-00524869 |  | Limits ATC
ALTALINK | 446L (305s Acheson - 367s Harry Smith) | 2017-11-03 08:00 | 2017-11-05 09:00 | N | N | [SWEATD] finish P&C testing for 446L | Line |  |  | For Information Only
ALTALINK | 289s T1 (289s Saunders Lake),289s Saunders Lake 240kV Bus 1 | 2017-11-03 14:00 | 2017-11-11 11:00 | N | Y | [SWEATD] Finish bus work, close OP 'CC' | Bus, Transformer |  |  | 240 kV
ALTALINK | 289s T2 (289s Saunders Lake),289s Saunders Lake 240kV Bus 2 | 2017-11-03 14:00 | 2017-11-13 07:00 | N | Y | [SWEATD] keep 289s T2 & 240kV bus under GOI until 914L cut-in and energization Nov 13-22 | Transformer, Bus |  |  | 240 kV
ALTALINK | 1140L (289s Saunders Lake - 89s Ellerslie) | 2017-11-03 17:00 | 2017-11-10 17:30 | N | N | [SWEATD] energize 1140L | Line
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee),385s 225 (385s Spring Coulee) | 2017-11-03 17:46 | 2017-11-08 20:30 | N | N | line is required to be open ended at 385s while 385s VT1 is being replaced | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s C1 (987s Clover Bar),987s T2 (987s Clover Bar),72CH9 (Hardisty - 987s Clover Bar),72CN10 (987s Clover Bar - Namao),987s CDS2 (987s Clover Bar),987s GDS-1B1 (987s Clover Bar),987s GDS-1B2 (987s Clover Bar) | 2017-11-03 19:00 | 2017-11-05 19:00 | N | Y | disconnect replacement | Line, Transformer, Switch, Shunts |  |  | 240 kV, Pre-Condition, Restricts Generation
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2017-11-04 07:00 | 2017-11-05 16:00 | N | N | Installing new water main to Rosedale school (905 - 13 Ave. NW) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s T2 (58s Edson) | 2017-11-04 08:00 | 2017-11-05 18:00 | N | Y | replace 25kV risers between the new breakers and the 25kV bus & install bird cover-up | Transformer |  | Replace 25kV Risers Between the New breakers and the 25kV Bus & Install Bird Cover-up - Requires DG outage | Restricts Generation
ENMAX | ENMAX 21 B138-21.CAP (ENMAX 21) | 2017-11-04 08:00 | 2017-11-04 16:00 | N | N | install new panel for 21.4TR | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2017-11-04 09:00 | 2017-11-04 19:00 | N | N | fence replacement around capacitor bank | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 385S Spring Coulee | 2017-11-05 08:00 | 2017-11-05 09:00 | N | N | de-energizing the 69kV bus to commission the new VT1 | Station
ALTALINK | 446L (305s-367s) Energized [SWEATD] | 2017-11-05 09:00 | 2017-11-05 12:00 | N | N | [SWEATD] energize 446L (305s-367s) | Terminal Equipment |  |  | For Information Only
ALTALINK | 367s T2 (367S Harry Smith) | 2017-11-05 09:00 | 2017-11-14 08:00 | N | N | [SWEATD] T1 under GOI until 240kV bus energization | Transformer |  | [SWEATD] T2 under GOI until 240kV bus energization | For Information Only
ALTALINK | 367s T1 (367s Harry Smith) | 2017-11-05 09:00 | 2017-11-14 08:00 | N | N | [SWEATD] T1 under GOI until 240kV bus energization | Transformer |  | [SWEATD] T1 under GOI until 240kV bus energization | For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10) | 2017-11-05 21:15 | 2017-11-06 00:45 | N | Y | high load move | Line |  |  | Pre-Condition
Saskpower | Sask Power S1C line | 2017-11-06 07:00 | 2017-11-06 17:00 | N | Y | removal of S1C connection to SW808LM and connect to SW812LM | Line |  |  | Limits ATC
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11) | 2017-11-06 08:00 | 2017-11-10 16:00 | N | N | 11s reliability upgrade, relocate line structure and 11.1TR MD replacement | Line, Transformer |  |  | For Information Only
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2017-11-06 08:00 | 2017-11-09 15:00 | N | N | line repairs | Line |  | Line repairs, 846s and 940s will be radial fed | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.4TR (ENMAX 11) | 2017-11-06 08:00 | 2017-11-12 16:00 | N | N | doble TX | Transformer |  |  | For Information Only
TRANSALTA, STROBE | 240s T1 (240s McBride Lake),240s T2 (240s McBride Lake),240s T3 (240s McBride Lake) | 2017-11-06 09:00 | 2017-11-06 09:30 | N | Y | to test supervisory control of breakers | Transformer |  |  | Restricts Generation
ALTALINK | 67s T1 (67s Stirling) | 2017-11-06 11:00 | 2017-11-06 17:00 | N | N | 67s Pin cap insulator broke on the conductor from 67s30 to the 25kV bus. Change all 3 pin caps. | Transformer |  |  | For Information Only
ALTALINK | 320p 152 (320p Keephills) | 2017-11-06 11:00 | 2017-11-07 17:00 | N | Y | migrate controls and annunciation and analogs to new RTU | Circuit Breaker |  | Migrate controls, annunciation and analogs to new RTU. Redundant protections will be taken out of service one at a time. Will also be working on VT12 (240 kV A Bus) ground alarm module (analog and ground alarm). Crew will be operating 320p152. | 240 kV, Contingency Requires Mitigation
ALTALINK | 426L (194s South Red Deer - 63s Red Deer),194s 426 (194s South Red deer) | 2017-11-06 13:00 | 2017-11-08 16:00 | N | N | maintain 138kV HPF minimum oil breaker Sprecher | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354s T3 (354s Summerview) | 2017-11-06 14:00 | 2017-11-06 17:00 | N | Y | tap changer oil top up | Transformer |  |  | Restricts Generation
ATCO | 863S Paintearth,9L948 (650s Hansman Lake - 863s Paintearth) | 2017-11-06 15:01 | 2018-03-02 16:00 | N | Y | 240 kV switch replacement - changed to forced outage | Line, Station |  | the 863S Paint Earth Substation 240KV replacement switches are to arrive early August. The plan is for replacement of the devices Off-loading the entire substation and back feeding the station service would be the preferred method Switch Replacement dates: 900D1 - September 25th - 29th . 9L27D2 - October 2 - 6th. 901A - October 10 -15th. 9L948D4 - October 16 - 20th. 902A - October 23 - 27th. | 240 kV, For Information Only
ATCO | 7L696 (508s Lakesend - 892s Ribstone Creek) | 2017-11-07 08:00 | 2017-11-08 17:00 | N | Y | mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost | Line |  | To mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost. This mitigation is to install inter phase spacers between A and C phase so that they cannot get close to each other as frost comes off of the wire. | Firm Load Loss
ENMAX | 8.5TR (ENMAX 8),8.6TR (ENMAX 8),1.85L (ENMAX 1 - ENMAX 8),Enmax 8 B138-2A0 (ENMAX 8) | 2017-11-07 08:00 | 2017-11-25 16:00 | N | N | HV breaker inspection | Line, Transformer, Circuit Breaker
ATCO | 7L79 (771s Veteran - 892s Ribstone Creek) | 2017-11-07 08:00 | 2017-11-08 17:00 | N | N | mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost | Line |  | To mitigate some of the areas on 7L79 and 7L696 that really get affected by hoar frost. This mitigation is to install inter phase spacers between A and C phase so that they cannot get close to each other as frost comes off of the wire.
SUNCOR | 29EDD-94 952_9701 (29EDD-94) | 2017-11-07 08:30 | 2017-11-09 18:00 | N | Y | repair leaking gasket on SF-6 breaker | Circuit Breaker |  |  | 240 kV
ALTALINK | 297s 757 (297s Rimbey) | 2017-11-08 00:01 | 2017-11-08 02:00 | N | N | urgent: replace defective heater | Circuit Breaker |  |  | Pre-Condition, For Information Only
EPCOR | Kennedale K724 (Kennedale),Kennedale K723 (Kennedale),72KN23 (Namao - Kennedale) | 2017-11-08 06:30 | 2017-11-08 18:30 | N | N | replace faulty CVT | Line, Circuit Breaker
EPCOR | 803s T2 (803s Lambton),803s L2402 (803s Lambton),803s L2405 (803s Lambton) | 2017-11-08 07:00 | 2017-11-09 17:00 | N | Y | cutover of new relay protection on T2 | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss
ALTALINK | 320p 752 (320p Keephills) | 2017-11-08 07:00 | 2017-11-09 17:00 | N | Y | migrate controls, annunciation and analogs to new RTU | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D131 (ENMAX 25),ENMAX 25 B240-D132 (ENMAX 25) | 2017-11-08 07:00 | 2017-11-10 14:00 | N | Y | repair SW132, SF6 gas sample on D131 | Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2017-11-08 07:15 | 2017-11-08 17:45 | N | N | emergency repair; replace insulators | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAXGPI | 134S Taber Wind Farm | 2017-11-08 08:00 | 2017-11-08 18:00 | N | N | communication outage | Station |  |  | Affects Visibility
ALTALINK | 33s3 (33s Spray) | 2017-11-08 08:00 | 2017-11-08 17:00 | N | Y | routine maintenance | Switch |  |  | Restricts Generation
ALTALINK | 74s C4 (74s Janet),74s 103 (74s Janet) | 2017-11-08 08:00 | 2017-11-08 17:00 | N | Y | C phase mechanical local/remote switch does not work and will be rewired | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 671L (58s Edson - 39s Bickerdike),58s 671 (58s Edson) | 2017-11-08 08:15 | 2017-11-08 11:45 | N | N | high load move | Line, Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 225L (385s Spring Coulee - 225s Magrath) | 2017-11-08 20:31 | 2017-11-08 21:29 | N | N | open line to transfer load without 69kV being paralleled | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee),385s 225 (385s Spring Coulee) | 2017-11-08 21:30 | 2017-11-09 01:00 | N | N | line is required to be open ended at 385s while 385s VT1 is being replaced | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1140L (289s Saunders Lake - 89s Ellerslie),910L (289s Saunders Lake - 288s Wolf Creek) | 2017-11-09 07:00 | 2017-11-10 17:00 | N | Y | [SWEATD] close OP 'JJ', 'GG', 'EE', 'MM', energize 910L & 1140L and phase @ 289s | Line |  |  | 240 kV
ALTALINK | 288s 452 (288s Wolf Creek),288s 552 (288s Wolf Creek) | 2017-11-09 07:01 | 2017-11-10 14:00 | N | Y | 910L P&C work @ 288s | Circuit Breaker |  |  | 240 kV
ENMAX | 34.4TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2017-11-09 08:00 | 2017-11-09 12:00 | N | N | install OAC/CAC relays for RTU upgrade | Line, Transformer |  | Install OAC/CAC relays for RTU upgrade. Devices will need to be operated Locally, due to RTU change out. Close open close operation required for commissioning | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
SUNCOR | 635EDD-1000 635PK-1002 (635EDD-1000),635EDD-1000 635PK-1003 (635EDD-1000) | 2017-11-09 08:00 | 2017-11-10 17:00 | N | N | capacitor bank protection setting change and test activities | Shunts |  | capacitor bank protection setting change and test activities | For Information Only
REDDEER | 194s T2 (194s South Red Deer) | 2017-11-09 08:30 | 2017-11-15 16:30 | N | N | protection replacement | Transformer |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2017-11-09 12:00 | 2017-11-09 16:00 | N | N | install OAC/CAC relays for RTU upgrade | Line, Transformer |  | Install OAC/CAC relays for RTU upgrade. Devices will need to be operated Locally, due to RTU changeout. Close open close operation required for commissioning. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 289s Saunders Lake 138kV Bus 1 | 2017-11-10 08:00 | 2017-11-11 11:00 | N | N | [SWEATD] re-do bus CVT phase cable connections | Bus
ALTALINK | 289s T1 (289s Saunders Lake) | 2017-11-10 08:00 | 2017-11-12 07:00 | N | N | SWEATD ISD: Nov 11, 2017 | Transformer |  |  | For Information Only
ALTALINK | 1140L (289s Saunders Lake - 89s Ellerslie),910L (289s Saunders Lake - 288s Wolf Creek) | 2017-11-10 08:00 | 2017-11-11 07:00 | N | N | SWEATD ISD: Nov 10, 2017 | Line |  |  | For Information Only
EPCOR | 803s T1 (803s Lambton) | 2017-11-11 07:00 | 2017-11-11 17:00 | N | Y | cutover of new relay protection | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 25 MD240-3GSU (ENMAX 25) | 2017-11-11 15:30 | 2017-11-12 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 12.2TR (ENMAX 12) | 2017-11-12 08:00 | 2017-11-12 16:00 | N | N | top up LTC | Transformer |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),874L (522s Cooking Lake - 45s Bretona) | 2017-11-12 08:00 | 2017-11-12 10:30 | N | N | [SWEATD] offload 522s and to operate 138kV bus switches | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 25 MD240-2GSU (ENMAX 25) | 2017-11-12 08:00 | 2017-11-15 10:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 874L (522s Cooking Lake - 45s Bretona) | 2017-11-12 10:30 | 2017-11-18 07:59 | N | N | [SWEATD] install 522s874 as a 'dumb' breaker with no protection inputs | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2017-11-13 06:30 | 2017-11-16 17:00 | N | Y | 74s49 PT replacement | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK, EPCOR | 1043L (320p Keephills - 816s Petrolia) | 2017-11-13 07:00 | 2017-12-05 18:00 | N | Y | [SWEATD] cut in 1043L/1139L to Harry Smith Substation 367s and 320p SCADA work | Line |  | [SWEATD] Cut in 1043L/1139L to Harry Smith Substation 367s. 320p SCADA work (Migrate controls, annunciation and analogs to new RTU. Redundant protections will be taken out of service one at a time) | 240 kV
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2017-11-13 07:00 | 2017-11-25 17:00 | N | N | cutover of new line protection | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 89s Ellerslie),289s T2 (289s Saunders Lake),289s Saunders Lake 240kV Bus 2 | 2017-11-13 07:00 | 2017-11-24 17:00 | N | Y | [SWEATD] cut 914L in/out of 289s, add new 1112L | Line, Transformer, Bus |  |  | 240 kV, Pre-Condition
ENMAX | 11.2TR (ENMAX 11) | 2017-11-13 08:00 | 2017-11-13 16:00 | N | N | 11s reliability upgrade | Transformer |  | 11s reliability upgrade. Remove jumpers rom BD circuit in order to install Z32 138kV BD | Pre-Condition, For Information Only
ENMAX | 11.3TR (ENMAX 11) | 2017-11-13 08:00 | 2017-11-13 16:00 | N | N | 11s reliability upgrade | Transformer |  | 11s reliability upgrade. Remove jumpers rom BD circuit in order to install Z32 138kV BD | Pre-Condition, For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2017-11-13 09:00 | 2017-11-13 12:00 | N | N | 11s reliability upgrade | Line |  | 11s reliability upgrade. Remove jumpers rom BD circuit in order to install Z32 138kV BD | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 863L (225s Magrath - 618s Riverbend) | 2017-11-13 09:00 | 2017-11-13 16:00 | N | Y | airbreak 891L1 adjustment in conjunction with MPLS work. | Line |  |  | Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie),851L (525s Carseland - 253s Blackie),253S Blackie 138 kV bus,876L (179s Gleichen - 253s Blackie) | 2017-11-13 09:30 | 2017-11-14 17:00 | N | N | install piles in proximity to 753L/851L and the 138kV Bus | Line, Bus |  | Install Piles in proximity to 753L/851L and the 138kV Bus. This is prep work for Analog to Digital Station conversion that take place in 2018. | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T1 (987s Clover Bar),987s C2403 (987s Clover Bar),987s C2401 (987s Clover Bar),987s CCP7214 (987s Clover Bar),987s CCP7213 (987s Clover Bar),987s CDS25 (987s Cloverbar) | 2017-11-14 07:00 | 2017-11-17 17:00 | N | Y | CDS25 disconnect replacement | Transformer, Switch, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO, ALTALINK | 912L (63s Red Deer - 766s Nevis),9L912 (766s Nevis - 63s Red Deer) | 2017-11-14 07:00 | 2017-11-17 18:00 | N | Y | upgrade 9L912 protection | Line |  | Upgrade 9L912 protection. Altalink to upgrade their end at the same time. | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 705s 601T (705s Kitscoty),751s 701T (751s Hill),6L06 (705s Kitscoty - 751s Hill) | 2017-11-14 07:00 | 2017-11-27 17:00 | N | N | salvage 72kV equipment | Line, Transformer |  | Salvage 72kV equipment @ 751S up to 701T, 701T will be OOS Nov 23, 701T is a hot standby only Nov 14-22 Issue 2-41160A Isolation Points - 501TD @ 705S to 601TD, 600PT1 secondaries @ 751S Nov 23 AM Expand GOI, Issue 2-41160B Isolation Points - 501TD @ 705S to 701TD, 511B, 600PT1 secondaries @ 751S Release 2-41160A On RTN SLD to show 72kv equipment and 6L06 removed @ 751s 701T @ 751s placed back in service on RTN | For Information Only
ALTALINK | 150L (42s Sarcee - 150L47) | 2017-11-14 07:15 | 2017-11-19 15:45 | N | N | line move | Line |  |  | Pre-Condition, For Information Only
ALTALINK | 720L (347s Fox Creek - 397s Benbow),347s 720X (347s Fox Creek) | 2017-11-14 07:30 | 2017-11-21 17:30 | N | N | replace 347s720X with a new SF6 breaker and add LA's to 720L | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Creates Radial Feeds
ALTALINK | 428L (818s Winefred - 167s Ipiatik Lake) | 2017-11-14 08:00 | 2017-11-14 16:30 | N | N | tank heater repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L75 (A793s West Peace River - 800s Friedenstal) | 2017-11-14 12:00 | 2017-11-17 17:00 | N | Y | setting and CT ratio changes required to upgrade line limits. | Line |  | CT ratio and settings changes required to upgrade line limits. | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 818s C1 (818s Winefred),818s 14 (818s Winefred) | 2017-11-14 12:30 | 2017-11-14 17:30 | N | N | tank heater repair | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 9L97 (946s Oakland - 801s Anderson),9L99 (807s Sheerness - 801s Anderson) | 2017-11-14 15:01 | 2017-11-17 15:00 | N | Y | protection upgrade | Line |  | Protection upgrade, see following outage sequence; Nov 3 7:00-Nov 13 15:00 Permit - 9L97 OOS (2-36261A) Isolation points - - 905A, 906A @ 801S Anderson, 9L97D2 @ 946S Oakland Nov 13 15:01 - Nov 17 15:00 Expand GOI to include 9L99 Permit - 9L97 & 9L99 OOS (2-36261B) Isolation points - 9L97D2 @ 946S Oakland, 905A, 907B @ 801S Anderson, Nov 17 15:01 - Nov 20 15:00 Shrink GOI Permit - 9L99 OOS 2-36261C, then re-energize 9L97 Isolation points - 906B, 907B @ 801S Anderson, Nov 20 15:01 - Dec 4 17:00 Expand GOI to include 9L933 Permit - 9L933 & 9L99 OOS (2-36261D) Isolation points - 906B, 908A @ 801S Anderson, COG from Altalink on 9L933 at 132S Ware Junction | 240 kV, Restricts Generation
ALTALINK | 790L (434s Stony Plain - 432s Carvel),434s790 (434s Stony Plain) | 2017-11-15 07:00 | 2017-11-15 10:00 | N | N | SWEATD: cutover and test all new breaker fail trips and circuits to breaker | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 285s T1 (285s East Camrose) | 2017-11-15 07:30 | 2017-11-15 12:00 | N | N | install bird cover-up | Transformer |  |  | For Information Only
ALTALINK | 818s C2 (818s Winefred),818s 17 (818s Winefred) | 2017-11-15 07:30 | 2017-11-15 12:30 | N | N | tank heater repair | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 296s T2 (296s Rosyth) | 2017-11-15 08:00 | 2017-11-15 17:00 | N | N | investigate and possibly change 1 metering PT | Transformer |  |  | For Information Only
CONSTENERGY | 944s Lowe Lake RTU/SCADA | 2017-11-15 08:30 | 2017-11-15 13:30 | N | N | replace the Orion 5 RTU with an Orion LXm RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 268s 69 (268s Whitecourt) | 2017-11-15 12:00 | 2017-12-05 16:30 | N | N | redundant protections may be taken out of service one at a time for testing 268s 69 outage | Circuit Breaker |  |  | For Information Only
ALTALINK | 452L (434s Stony Plain - 367s Harry Smith) | 2017-11-15 12:00 | 2017-11-15 17:00 | N | N | SWEATD: trip-test breakers from breaker fail between 367s & 434s | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 526L (268s Whitecourt - 526DL185),268s 69 (268s Whitecourt) | 2017-11-15 12:00 | 2017-12-05 16:30 | N | N | replace 526 control module | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 818s C3 (818s Winefred),818s 41 (818s Winefred) | 2017-11-15 12:30 | 2017-11-15 17:30 | N | N | tank heater repair | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 712L (99s North St. Albert - 595s Spruce Grove),595s 712 (595s Spruce Grove) | 2017-11-16 07:30 | 2017-11-16 11:30 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2017-11-16 08:00 | 2017-11-16 16:00 | N | N | repair hotspot SW84 and fall substation washing | Line, Shunts, Transformer |  | SW84@14sub (WR#279867) | Firm Load Loss, Creates Radial Feeds
ALTALINK | 993s 437 (993s Abee) | 2017-11-16 09:00 | 2017-11-16 17:00 | N | N | tank heater repair | Circuit Breaker |  |  | For Information Only
ALTALINK | 595s677 (595s Spruce Grove),677L (305s Acheson  595s Spruce Grove) | 2017-11-16 12:30 | 2017-11-16 17:30 | N | N | breaker maintenance | Line, Circuit Recloser |  |  | Overload, Over/Under Voltage
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress),163s 1752 (163s Amoco Empress) | 2017-11-16 14:30 | 2017-11-16 15:00 | N | Y | required to commission new 163s1752 breaker | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
BCH | 2L293 (Selkirk - Nelway) | 2017-11-17 09:00 | 2017-11-17 17:00 | N | Y | BCH - annual maintenance - BC maintenance does not affect AB ATC | Line | Peak Outage ID BC Outage: 1-00518353 Peak COS ID: 1-00527546 , 1-00527547 |  | Limits ATC, For Information Only
ATCO | 9L99 (807s Sheerness - 801s Anderson) | 2017-11-17 15:01 | 2017-11-20 15:00 | N | Y | protection upgrade | Line |  | Protection upgrade, see following outage sequence; Nov 3 7:00-Nov 13 15:00 Permit - 9L97 OOS (2-36261A) Isolation points - - 905A, 906A @ 801S Anderson, 9L97D2 @ 946S Oakland Nov 13 15:01 - Nov 17 15:00 Expand GOI to include 9L99 Permit - 9L97 & 9L99 OOS (2-36261B) Isolation points - 9L97D2 @ 946S Oakland, 905A, 907B @ 801S Anderson, Nov 17 15:01 - Nov 20 15:00 Shrink GOI Permit - 9L99 OOS 2-36261C, then re-energize 9L97 Isolation points - 906B, 907B @ 801S Anderson, Nov 20 15:01 - Dec 4 17:00 Expand GOI to include 9L933 Permit - 9L933 & 9L99 OOS (2-36261D) Isolation points - 906B, 908A @ 801S Anderson, COG from Altalink on 9L933 at 132S Ware Junction | 240 kV, Restricts Generation
EPCOR | 987s T1 (987s Clover Bar),987s CH724 (987s Clover Bar),987s CK725 (987s Clover Bar),987s CK726 (987s Clover Bar),987s CCP7214 (987s Clover Bar),987s CC13 (987s Clover Bar),987s CC24 (987s Clover Bar),987s CDS12 (987s Clover Bar) | 2017-11-18 06:00 | 2017-11-19 17:00 | N | Y | CDS12 disconnect replacement | Transformer, Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 41.2TR (ENMAX 41),33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41) | 2017-11-18 08:00 | 2017-11-18 12:00 | N | N | test breaker fail trips | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),874L (522s Cooking Lake - 45s Bretona) | 2017-11-18 08:00 | 2017-11-18 10:30 | N | N | [SWEATD] Offload 522s and open 174L & 874L in order to operate 522s 138kV bus switches | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D133 (ENMAX 25) | 2017-11-18 08:00 | 2017-11-18 16:00 | N | Y | SF6 gas sample | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds
ALPAC | 282S Grassland (Alpac) | 2017-11-18 10:00 | 2017-11-18 18:00 | N | N | control room phone line unavailable | Station |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),522s T2 (522s Cooking Lake) | 2017-11-18 10:30 | 2017-11-27 17:00 | N | N | [SWEATD] install 522s780 breaker and connect 522s30 & 522s26 switch drive assembly | Line, Transformer |  | [SWEATD] Install 522s780 breaker, Connect 522s30 & 522s26 switch drive assembly Close Open Points "A", "E", "F", "G", "K", energize T2 & 25kV bus 2, connect 522s VT3 & VT4, connect 197s VT3 | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 262s T1 (262s Rocky Mountain House),870L (262s Rocky Mountain House - 263s Strachan),262s 870W (262s Rocky Mountain House) | 2017-11-19 08:00 | 2017-11-19 17:30 | N | Y | emergency fix breaker head | Circuit Breaker, Line, Transformer |  | Emergency. Fix leaky head, change seal in breaker head on one phase.262s65 will also need to be repaired. | Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2017-11-19 08:30 | 2017-11-19 12:30 | N | Y | close open point 'A' at Str44; 492s load to remain online | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 252s T1 (252s Jarrow) | 2017-11-19 08:30 | 2017-11-26 17:00 | N | N | salvaging equipment | Transformer |  | Salvaging Transformer T1 TX18147, Breaker CB61, Switches 252s13, 252s4, 252s5, 252s6, and all associated bus work, risers, and support structures. | For Information Only
ALTALINK | 367S Harry Smith | 2017-11-20 | 2017-11-22 23:00 | N | N | 240 kV bus. ISD Nov 20, 2017 | Station
ALTALINK | 834L (384s Keystone - 320p Keephills),320p 834X (320p Keephills) | 2017-11-20 07:00 | 2017-11-22 17:00 | N | N | migrate controls, annunciation and analogs to new RTU | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 35.81L (42s Sarcee - ENMAX 35),42s 35 (42s Sarcee) | 2017-11-20 07:30 | 2017-12-04 16:30 | N | Y | [SWCRR] relocate OSHW on 3L @ 42s near 35.81L | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge),111s 207L (111s Coalbanks) | 2017-11-20 08:00 | 2017-11-30 16:00 | N | Y | Altalink & Lethbridge 207L protection relay upgrade | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 3L (42s Sarcee - 272s Springbank),42s 3W (42s Sarcee) | 2017-11-20 08:00 | 2017-11-21 16:00 | N | N | new 35.81L shield wire crosses over 3 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 10.2TR (ENMAX 10) | 2017-11-20 08:00 | 2017-11-21 16:00 | N | N | inspect float and revise float arm length | Transformer
EPCOR | 72NW15 (Namao - Woodcroft) | 2017-11-20 09:00 | 2017-11-30 15:00 | N | N | line maintenance and upgrades | Line |  |  | Pre-Condition
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2017-11-20 12:00 | 2017-11-23 16:00 | N | N | line mitigation | Line |  | Line mitigation, 739s to D2, Swan Dive and Freeman Lk will be radial fed | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 9L99 (807s Sheerness - 801s Anderson),9L933 (132s Ware Junction - 801s Anderson) | 2017-11-20 15:01 | 2017-12-01 17:00 | N | Y | protection upgrade | Line |  | Protection upgrade, see following outage sequence; Nov 3 7:00-Nov 13 15:00 Permit - 9L97 OOS (2-36261A) Isolation points - - 905A, 906A @ 801S Anderson, 9L97D2 @ 946S Oakland Nov 13 15:01 - Nov 17 15:00 Expand GOI to include 9L99 Permit - 9L97 & 9L99 OOS (2-36261B) Isolation points - 9L97D2 @ 946S Oakland, 905A, 907B @ 801S Anderson, Nov 17 15:01 - Nov 20 15:00 Shrink GOI Permit - 9L99 OOS 2-36261C, then re-energize 9L97 Isolation points - 906B, 907B @ 801S Anderson, Nov 20 15:01 - Dec 4 17:00 Expand GOI to include 9L933 Permit - 9L933 & 9L99 OOS (2-36261D) Isolation points - 906B, 908A @ 801S Anderson, COG from Altalink on 9L933 at 132S Ware Junction | 240 kV, Restricts Generation
ALTALINK | 719L (263s Strachan - 719L259C) | 2017-11-21 07:30 | 2017-11-21 17:30 | N | N | create open point 'A'; 719L259C A/B repair; close open point 'A' | Line |  |  | Creates Radial Feeds
ATCO | 823S Wapiti | 2017-11-21 08:00 | 2017-11-27 13:00 | N | N | create 25kV open jumper J2 and connect 902S secondary taps to 25kV bus | Station |  | Create 25kV open jumper J2, connect 902S secondary taps to 25kV bus. -------- Load Transfer -------- 823S 5L371 Peak Load = 9.53 MVA 823S 5L370 Peak Load = 6.47 MVA 823S 5L371 Relay Settings: 13.8 MVA CO9 (Setting change reqd) 823S 5L370 Relay Settings: 13.8 MVA CO9 (Setting change reqd) -------- Load Transfer -------- | For Information Only
ALTALINK | 76L (115s Mt. Allan - 33s Spray) | 2017-11-21 12:15 | 2017-11-21 17:45 | N | N | bird nest removal | Line |  |  | Pre-Condition, Restricts Generation, Creates Radial Feeds
ALTALINK | 325s T2 (325s Leduc) | 2017-11-22 07:30 | 2017-11-24 17:00 | N | N | move T2 fiber conduit out of way for filter bank piles | Transformer |  |  | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2017-11-22 08:00 | 2017-12-05 16:00 | N | N | transformer bushing/CT replacement & relay replacement | Transformer |  |  | For Information Only
ENMAX | 5.9TR (ENMAX 5) | 2017-11-22 08:00 | 2017-11-23 16:00 | N | N | inspect float and revise float arm length | Transformer |  |  | For Information Only
ALTALINK | 113L (20s Ghost - 33s Spray) | 2017-11-22 08:00 | 2017-11-22 17:00 | N | N | emergency: replace operating mechanism on 20s154 and adjust the open for 20s155 | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 289s T2 (289s Saunders Lake) | 2017-11-22 11:00 | 2017-11-23 17:00 | N | N | [SWEATD] ISD: Nov 23, 2017 | Transformer
ALTALINK | 1112L (289s Saunders Lake - 89s Ellerslie) | 2017-11-22 17:00 | 2017-11-22 17:30 | N | N | [SWEATD] energize 1112L (289s-89s) | Line |  |  | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2017-11-22 23:08 | 2017-11-23 15:15 | N | Y | 120s PST issue and testing | Line | PEAK COS outage ID:1-00530148 PEAK COS path de-rate ID1-00530157 (N-S), 1-00530158 (S-N) |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 22.3TR (ENMAX 22) | 2017-11-23 08:00 | 2017-11-26 16:00 | N | N | doble transformer and maintenance | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 1112L (289s Saunders Lake - 89s Ellerslie),914L (289s Saunders Lake - 86s Bigstone) | 2017-11-24 | 2017-11-24 23:00 | N | N | SWEATD ISD: Nov 22, 2017 | Line |  |  | For Information Only
ALTALINK | 289S Saunders Lake | 2017-11-24 | 2017-11-27 23:00 | N | N | 240 kV bus. ISD Nov 24, 2017 | Station |  |  | For Information Only
ALTALINK | 780L (38s East Edmonton - 289s Saunders Lake) | 2017-11-25 07:30 | 2017-12-04 07:00 | N | N | [SWEATD] cut new sections of 780/174L into existing 780L, remove 780L from 289s and reinstall into 522s | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 892L (895s Suffield - 244s Bowmanton) | 2017-11-25 07:30 | 2017-11-25 16:30 | N | N | emergency structure replacement | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),ENMAX 3 B138-3.84 (ENMAX 3) | 2017-11-25 08:00 | 2017-11-25 16:00 | N | N | 138kV BD and AS installation & trip lockout and function testing | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8),ENMAX 3 B138-3.82 (ENMAX 3) | 2017-11-26 08:00 | 2017-11-26 16:00 | N | N | 138kV BD and AS installation & trip lockout and function testing | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Aurora 12 (Aurora),Aurora 13 (Aurora),Aurora UT1 (Aurora) | 2017-11-27 07:00 | 2017-12-05 20:00 | N | N | 5Yr PM of transformer and replacing 12B and 13A isolating disconnects | Transformer, Circuit Breaker |  | 5Yr PM of Transformer # UT1, G01 - SubStation at Aurora and Replacing 12B and 13A isolating disconnects. | For Information Only
EPCOR | 803s T2 (803s Lambton) | 2017-11-27 07:00 | 2017-11-27 17:00 | N | Y | cutover of new relay protection | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 214s T1 (214s Innisfail),214s Innisfail 138kV Bus 1,419L (214s Innisfail - 287s Hazelwood) | 2017-11-27 07:30 | 2017-11-28 14:30 | N | N | bus connector replacement and damper installation | Transformer, Bus, Line |  | Bus connector replacement and damper installation, changed from SAP#257331 | Pre-Condition
ALTALINK | 419L (214s Innisfail - 287s Hazelwood) | 2017-11-27 07:30 | 2017-11-30 17:00 | N | N | installing bird diverters | Line |  |  | Pre-Condition
ENMAX | 31.1TR (ENMAX 31) | 2017-11-27 08:00 | 2017-12-04 14:00 | N | N | transformer differential relay replacement | Transformer |  |  | For Information Only
ENMAX | 40.1TR (ENMAX 40) | 2017-11-27 08:00 | 2017-11-28 16:00 | N | N | transformer secondary cable tests | Transformer |  |  | For Information Only
ENMAX | 162.1TR (ENMAX 162 Beddington) | 2017-11-27 08:00 | 2017-12-01 16:00 | N | Y | commision new equipment for 162.3TR addition | Transformer |  |  | Pre-Condition, Overload, Firm Load Loss
ENMAX | 5.1TR (ENMAX 5) | 2017-11-27 08:00 | 2017-11-28 16:00 | N | N | inspect float and revise float arm length, test gas relays | Transformer |  | Inspect Float and Revise Float Arm Length. Test gas relays | For Information Only
ENMAX | 14.2TR (ENMAX 14) | 2017-11-27 08:00 | 2017-12-06 16:00 | N | N | transformer differential relay replacement | Transformer |  |  | For Information Only
ATCO | 823s 701T (823s Wapiti) | 2017-11-27 13:00 | 2017-12-11 18:00 | N | N | 701TCS and 701T will be replaced | Transformer |  | 701TCS and 701T will be replaced. 501VR will be salvaged (see attached wplan) Nov 27 13:00 - Issue GOI 2-40190A - 701TCS and 701T will be replaced. 501VR will be salvaged. Dec 9 8:00 - Expand/Issue GOI 2-40190B to include new 7L09D1 - Release GOI 2-40190A - GOTO HOP 2-43740A (connect 7L09D1 to 7L09) - Release HOP 2-43740A Dec 10 8:00 - Release GOI 2-40190B - 701T new energization switching - Soak 701T overnight Dec 11 8:00 - Check phasing on 701T 25kV side @ S11881 - Check phasing on 502/500D3 loop - Parallel 701T to 902S - Load Transfer  902S to New 701T @ 823s Dec 12 8:00 - GOTO GOI 2-xxxxxA | Pre-Condition
FORTIS | Brooks Solar Generator Test | 2017-11-28 | 2017-12-21 23:00 | N | N | commissioning and testing ISD Nov 28 - Load Only. Dec 6 - 1st inverter startup | Unit
ALTALINK | 69s T4 (69s North Barrhead) | 2017-11-28 07:00 | 2017-12-07 14:00 | N | Y | urgent tapchanger repair | Transformer |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 900L (63s Red Deer - 17s Benalto) | 2017-11-28 07:15 | 2017-11-30 16:45 | N | Y | maintenance and marker ball install | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2017-11-28 07:15 | 2017-12-03 17:45 | N | Y | emergency repair; replace complete structure 113L52 | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2017-11-28 07:30 | 2017-11-28 17:30 | N | N | repairing damaged structure 721 | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s T2 (157s Lac La Biche) | 2017-11-28 07:30 | 2017-11-29 18:00 | N | N | install wildlife protection | Transformer |  |  | For Information Only
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2017-11-28 08:00 | 2017-11-29 17:00 | N | Y | update CIP passwords on valve cooling software | Shunts, Transformer |  | Update CIP passwords on Valve Cooling Software. | 500 kV
ENMAX | 162.1TR (ENMAX 162 Beddington),162s 240-RB131 (162s Beddington),162s 240-RB134 (162s Beddington) | 2017-11-28 08:00 | 2017-11-28 16:00 | N | Y | commission new equipment for 162.3TR addition | Circuit Breaker, Transformer |  |  | 240 kV, Firm Load Loss
ENMAX | 1.85L (ENMAX 1 - ENMAX 8),Enmax 1 B138-9A0 (ENMAX 1),Enmax 1 B138-10A0 (ENMAX 1) | 2017-11-28 08:00 | 2017-12-14 11:16 | N | N | GIS HV breaker inspection on 10a0, 138kV GIS | Line, Circuit Breaker |  |  | For Information Only
ATCO | 9L29 (946s Oakland - 963s Coyote Lake) | 2017-11-28 08:00 | 2017-12-01 17:00 | N | Y | repair OPGW | Line |  | OPGW Repair | 240 kV, For Information Only
ALTALINK | 995L (62s Brazeau - 995AL tap),62s 995X (62s Brazeau) | 2017-11-28 12:00 | 2017-11-28 15:00 | N | Y | connect new antenna on new tower | Circuit Breaker, Line |  | Connect new antenna on new tower at Alder Flats for the 9495R Alder Flats - 9062R Brazeau radio path. All traffic will be interrupted. Working with TransAlta for SCADA to Brazeau plant. 62s995X will be open due to loss of TPR. List of RTU sent in seperate email. | 240 kV, Overload, Over/Under Voltage, Restricts Generation, Creates Radial Feeds
ALTALINK | 170s 1452 (170s Pike),170s T2 (170s Pike) | 2017-11-28 12:30 | 2017-11-28 17:30 | N | Y | tank heater repair | Circuit Breaker, Transformer |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 228S T.M.P.L.Niton,744L (235s Entwistle - 228s T.M.P.L.Niton),744L (228s T.M.P.L.Niton - 207s Pinedale) | 2017-11-29 07:00 | 2017-11-30 17:30 | N | N | replace grounding | Station, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p Keephills 240kV Bus B,320p T1 (Tx18429) & 240kV 'B' Bus Advice | 2017-11-29 07:00 | 2017-11-30 18:00 | N | Y | [SWEATD] Trip test 320p91, 320p1352, 320p752 & 320p2152 from new 320p352 breaker fail | Terminal Equipment, Bus |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 170s 1352 (170s Pike),170s T1 (170s Pike) | 2017-11-29 07:30 | 2017-11-29 12:30 | N | Y | tank heater repair | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ALTALINK | 287s 652 (287S Hazelwood) | 2017-11-29 07:30 | 2017-11-30 14:30 | N | Y | breaker mechanism repair | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 522s T1 (522s Cooking Lake),874L (522s Cooking Lake - 45s Bretona) | 2017-11-29 07:30 | 2017-12-03 15:00 | N | N | [SWEATD] Salvage 522s4, replace 522s1, connect 522s1252 to 522s1, and replace 874 breaker bus side riser | Line, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.3TR (ENMAX 3) | 2017-11-29 08:00 | 2017-11-29 16:00 | N | N | 138kV BD and AS installation with trip lockout and function testing | Transformer |  |  | For Information Only
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2017-11-29 08:00 | 2017-11-29 16:00 | N | N | commision equipment for 162.3TR addition | Line |  |  | Pre-Condition, Overload
ENMAX | 13.1TR (ENMAX 13) | 2017-11-29 09:00 | 2017-11-29 11:00 | N | N | add wiring to device 43 | Transformer |  |  | For Information Only
ENMAX | 13.2TR (ENMAX 13) | 2017-11-29 11:00 | 2017-11-29 13:00 | N | N | add wiring to device 43 | Transformer |  |  | For Information Only
ENMAX | 13.3TR (ENMAX 13) | 2017-11-29 13:00 | 2017-11-29 15:00 | N | N | add wiring to device 43 | Transformer |  |  | For Information Only
ALTALINK | 157s T1 (157s Lac La Biche) | 2017-11-30 07:30 | 2017-11-30 18:00 | N | N | install wildlife protection | Transformer |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3) | 2017-11-30 08:00 | 2017-11-30 16:00 | N | N | 138kV BD and AS installation and function testing | Transformer |  | 138kV BD and AS installation . Trip lockout and function testing. | For Information Only
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2017-11-30 09:15 | 2017-11-30 13:45 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 2033s 701 (2033s Mowat) | 2017-11-30 09:30 | 2017-12-01 17:00 | N | N | investigate leak and top up on 701 breaker | Circuit Breaker |  | investigate leak, top up, on 701 Bkr- Sub Off Loaded see Ld Tx 2-43979, 2-43980, 2-43981, 2-43982 | For Information Only
ALTALINK | 912L (63s Red Deer - 766s Nevis) | 2017-12-01 07:15 | 2017-12-11 16:45 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 268s 199N (268s Whitecourt),199L (268s Whitecourt - 199L187B) | 2017-12-01 08:00 | 2017-12-03 16:30 | N | N | move communication and trip testing | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L02 (873s Marion Lake - 769s Stettler) | 2017-12-01 08:00 | 2017-12-01 16:00 | N | N | de-energize 6L02 between D6 and 769s Stettler | Line |  | Request to de-energize 6L02 between D6 and 769s Stettler, no permit to be issued | For Information Only
BCH | 1L275 (799s Coleman - Natal) | 2017-12-01 09:00 | 2017-12-01 17:00 | N | Y | perform the condition assessment for 1CB2 | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ATCO | 9L933 (132s Ware Junction - 801s Anderson) | 2017-12-01 17:01 | 2017-12-04 17:00 | N | Y | protection upgrade | Line |  | Protection upgrade, see following outage sequence; Nov 3 7:00-Nov 14 15:00 Permit - 9L97 OOS (2-36261A) Isolation points - - 905A, 906A @ 801S Anderson, 9L97D2 @ 946S Oakland Nov 14 15:01 - Nov 17 15:00 Expand GOI to include 9L99 Permit - 9L97 & 9L99 OOS (2-36261B) Isolation points - 9L97D2 @ 946S Oakland, 905A, 907B @ 801S Anderson, COG from ATCO Power Sheerness from 9L99 @ 807s Nov 17 15:01 - Nov 20 15:00 Shrink GOI Permit - 9L99 OOS 2-36261C, then re-energize 9L97 Isolation points - 906B, 907B @ 801S Anderson, COG from ATCO Power Sheerness on 9L99 Nov 20 15:01 - Nov 27 17:00 Expand GOI to include 9L933 Permit - 9L933 & 9L99 OOS (2-36261D) Isolation points - COG from ATCO Power Sheerness on 9L99, 906B, 908A @ 801S Anderson, COG from Altalink on 9L933 at 132S Ware Junction Nov 27 17:01 - Dec 4 17:00 Shrink GOI Permit - 9L933 OOS 2-36261E, then re-energize 9L99 Isolation points - 907A, 908A @ 801S Anderson, COG from Altalink on 9L933 at 132S Ware Junction | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 58s T2 (58s Edson) | 2017-12-02 06:00 | 2017-12-03 19:00 | N | Y | replace 25kV risers between the new breakers and the 25kV bus & install bird cover-up | Transformer |  |  | Restricts Generation
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2017-12-02 08:00 | 2017-12-03 16:00 | N | Y | DGA sampling required | Transformer |  |  | 240 kV
ALTALINK | 268s 69 (268s Whitecourt) | 2017-12-02 08:30 | 2017-12-03 16:30 | N | N | IPP comms and trip testing | Circuit Breaker |  |  | For Information Only
BCH | 5L77 (Revelstoke - Ashton Creek) | 2017-12-03 11:00 | 2017-12-03 16:00 | N | Y | black start testing - BC maintenance does not affect AB ATC | Line | Peak COS outage ID: 1-00518817 Peak Path COS ID: 1-00530817 (E>W), 1-00530818 (W>E) |  | Limits ATC, 500 kV
ALTALINK | 522s T1 (522s Cooking Lake) | 2017-12-03 15:01 | 2017-12-12 17:00 | N | N | [SWEATD] shrink existing advice, salvage 51L, 522s51N, install new 522s689 MOD, replace 522s7 & 522s8, buswork, install new 138 kV breaker feeders, and replace station service | Transformer |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 522s Cooking Lake),38s 780X (38s East Edmonton),780L (38s East Edmonton - 289s Saunders Lake),522s 780 (Cooking Lake),289s 652 (Saunders Lake),289s 852 (Saunders Lake) | 2017-12-04 07:01 | 2017-12-08 15:00 | N | N | [SWEATD] continue 780L cut into 289s, move 174L from 522s to 197s, move 780L into old 174L bay @ 522s | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.3TR (ENMAX 36) | 2017-12-04 08:00 | 2017-12-05 16:00 | N | N | transformer secondary tests | Transformer |  |  | For Information Only
ATCO | 706s 702 (706s Irish Creek),706s 702T (706s Irish Creek),706s Irish Creek 144kV Bus 700BS2 | 2017-12-04 08:00 | 2017-12-14 12:00 | N | N | attach new capacitor bank, 705C breaker fail trip 701 test | Transformer, Bus, Circuit Breaker |  | Attach new Capacitor bank switch 705A, All load on 701T, Bypass installed between 7L53 and 7L117, on RTN all load moved onto 701T so 705C breaker fail trip 701 can be tested. | Pre-Condition
ENMAX | 162.3TR (ENMAX 162 Beddington) | 2017-12-04 08:00 | 2017-12-06 16:00 | N | N | In-service-date: Dec 5, 2017 | Transformer
ENMAX | 65.1 TR (ENMAX 65) | 2017-12-04 08:00 | 2017-12-05 16:00 | N | Y | DGA sample required | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2017-12-04 08:30 | 2017-12-05 11:30 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2017-12-04 12:00 | 2017-12-04 14:00 | N | N | high load move under 6L56 at SE-9-30-17-W4 | Line |  | Move a high load under 6L56 at SE-9-30-17-W4 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, EPCOR | 367s T1 (367s Harry Smith),367s T2 (367S Harry Smith),1043L (320p Keephills - 367s Harry Smith),1139L (367s Harry Smith - 816s Petrolia) | 2017-12-05 | 2017-12-07 23:00 | N | N | SWEATD ISD Dec 5, 2017 | Transformer, Line
ALTALINK | 305S Acheson | 2017-12-05 07:00 | 2017-12-05 17:30 | N | N | create open point 'A' to replace N.O 305s28 at 25kV | Station |  |  | For Information Only
ALTALINK | 305s C1 (305s Acheson),305s T1 (305s Acheson),446L (305s Acheson - 367s Harry Smith),739L (14s Devon - 305s Acheson),305s1152 (305s Acheson),305s Acheson 138 kV Bus 1 | 2017-12-05 07:00 | 2017-12-05 17:00 | N | N | [SWEATD] Replace risers between 305s446 and 305s4 | Bus, Line, Transformer, Shunts, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 463L (181s Chinook - 463L28) | 2017-12-05 07:30 | 2017-12-05 17:30 | N | Y | create open point 'A' at str43 & 463L28 switch repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 103s T1 (103s Goose Lake) | 2017-12-05 08:00 | 2017-12-06 20:00 | N | N | forced outage - tap changer oil leakage | Transformer |  |  | 240 kV
ENMAX | 162s 138-RB86 (162s Beddington) | 2017-12-05 08:00 | 2017-12-05 16:00 | N | N | Initial energization of equipment | Circuit Breaker
ALTALINK | 33s6 (33s Spray) | 2017-12-05 08:00 | 2017-12-05 17:00 | N | Y | routine maintenance | Switch |  |  | Restricts Generation
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2017-12-05 08:00 | 2017-12-05 16:00 | N | N | 14.2TR diff relay installation | Shunts |  |  | Pre-Condition
ALTALINK | 916L (42s Sarcee - 5s East Calgary),936L (102s Langdon - 5s East Calgary) | 2017-12-05 10:00 | 2017-12-05 12:00 | N | Y | netcom and field operations will be upgrading radio between 5S E. Calgary and 9074R Janet | Line |  |  | 240 kV
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2017-12-05 11:31 | 2017-12-05 18:45 | N | N | contamination monitoring program | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s T2 (305s Acheson),453L (305s Acheson - 367s Harry Smith),677L (305s Acheson  595s Spruce Grove),305s Acheson 138 kV Bus 2 | 2017-12-06 07:00 | 2017-12-06 17:00 | N | N | [SWEATD] replace risers between 305s453 and 305s1 | Line, Bus, Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746s Sherwood Park),746L (700L TAP - 746DL19 TAP) | 2017-12-06 07:15 | 2017-12-07 17:45 | N | N | contamination monitoring program | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 305S Acheson | 2017-12-06 07:30 | 2017-12-07 17:30 | N | N | 25kV west bus outage to replace 305s28 | Station |  |  | For Information Only
ENMAX | 36.2TR (ENMAX 36),36.5TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2017-12-06 08:00 | 2017-12-08 16:00 | N | N | maintenance and fall substation washing at ENMAX 36 | Line, Transformer |  | HV SW/MD Maintenance 36.5MD, 36.2MD, SW85. Fall Substation Washing. Replace Three Way Filling Valve on 36B69-16.63/36.5TR (WO278677). 14.2TR Diff relay installation. Commissioning trip circuits on 14B138-14.83 | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39) | 2017-12-06 08:00 | 2017-12-15 16:00 | N | N | replace Z1 8kV feeder panel doors | Transformer |  |  | For Information Only
ENMAX | 65.2 TR (ENMAX 65) | 2017-12-06 08:00 | 2017-12-07 16:00 | N | Y | DGA sample required | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 250p11 (250p Bighorn) | 2017-12-06 11:00 | 2017-12-06 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 162.3TR (ENMAX 162 Beddington) | 2017-12-06 12:00 | 2017-12-06 16:00 | N | N | commissioning | Transformer |  | Initial energization of transformer (backfeed) Dec 5, then taken out of service for commissioning. Carrying load Dec 6
EPCOR | 72RG1 (Rossdale - Garneau) | 2017-12-07 07:00 | 2017-12-07 17:00 | N | N | cutover of new DFR | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.1TR (ENMAX 33) | 2017-12-07 08:00 | 2017-12-07 16:00 | N | N | RTU upgrade | Transformer |  |  | For Information Only
ALTALINK | 250p22 (250p Bighorn) | 2017-12-07 09:00 | 2017-12-07 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
AESO-SC | EMS | 2017-12-07 09:00 | 2017-12-07 16:00 | N | N | BUCC Sstandalone de-activation (migrate EMS from SDC to PDC) | SCInternal
ALTALINK | 244s 552 (244s Bowmanton) | 2017-12-07 10:30 | 2017-12-07 15:00 | N | Y | top up gas on the center phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake) | 2017-12-08 | 2017-12-09 23:00 | N | N | SWEATD ISD Dec 8, 2017 | Line
ALTALINK | 675L (244s Bowmanton - 41s Medicine Hat) | 2017-12-08 06:30 | 2017-12-11 19:30 | N | Y | eye nut changeout | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s T1 (305s Acheson) | 2017-12-08 07:30 | 2017-12-08 17:00 | N | N | close open point 'A' | Transformer |  |  | For Information Only
ALTALINK | 892L (895s Suffield - 244s Bowmanton) | 2017-12-08 07:30 | 2017-12-11 18:00 | N | N | emergency work, replace 7 structures from storm damage, deficiency work, eye nut replacement and breaker maintenance | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 12.2TR (ENMAX 12) | 2017-12-08 08:00 | 2017-12-08 16:00 | N | N | RTU upgrade | Transformer |  | Replace OAC & CAC. Check polarities on 12BB8-12.2TR & 12BA8-12.2TR CTs | For Information Only
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2017-12-08 15:00 | 2017-12-11 14:30 | N | N | [SWEATD] continue 174L cut into 289s | Line
ENMAX | 36.2TR (ENMAX 36) | 2017-12-08 16:01 | 2017-12-15 16:00 | N | N | bushing doble testing | Transformer |  | 36.2TR bushing doble testing | For Information Only
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake) | 2017-12-08 17:00 | 2017-12-08 17:30 | N | N | [SWEATD] energize 780L (38s-522s) | Line
EPCOR | Woodcroft T1 (Woodcroft) | 2017-12-09 07:00 | 2017-12-09 17:00 | N | N | bus maintenance | Transformer |  |  | For Information Only
EPCOR | 72RG7 (Rossdale - Garneau),Garneau G722 (Garneau),Garneau G723 (Garneau) | 2017-12-09 07:00 | 2017-12-09 17:00 | N | N | cutover of new DFR | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss
ALTALINK | 42s T1 (42s Sarcee),42s 80 (42s Sarcee),42s 40 (42s Sarcee) | 2017-12-09 08:00 | 2017-12-09 13:00 | N | Y | [SWCRR] due to simultaneous 138kV bus 1 (north) protection outage, 42s40 & 42s80 opened to reduce fault clearing times with the bus protection OOS,[SWCRR] due to simultaneous 138kV bus 1 (north) protection outage, 42s40 & 42s80 opened to reduce potentially lengthy fault clearing times with the bus protection OOS | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 42s T2 (42s Sarcee),42s 80 (42s Sarcee),42s 60 (42s Sarcee) | 2017-12-09 13:01 | 2017-12-09 17:00 | N | Y | [SWCRR] due to simultaneous 138kV bus 2 (south) protection outage, 42s60 & 42s80 to reduce fault clearing times with bus protection OOS | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 823s 701T (823s Wapiti) | 2017-12-10 | 2017-12-12 23:00 | N | N | transformer capacity upgrade Dec 11 | Transformer
EPCOR | Woodcroft T2 (Woodcroft) | 2017-12-10 07:00 | 2017-12-10 17:00 | N | N | bus maintenance | Transformer |  |  | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2017-12-10 20:00 | 2017-12-10 21:00 | N | N | install CAC/OAC relays for RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 13.2TR (ENMAX 13) | 2017-12-10 21:00 | 2017-12-10 22:00 | N | N | install CAC/OAC relays for RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2017-12-10 22:00 | 2017-12-10 23:00 | N | N | install CAC/OAC relays for RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 2.83L (ENMAX 13 - 2.83L tap),ENMAX 13 B138-2.83 (ENMAX 13) | 2017-12-10 23:00 | 2017-12-11 00:01 | N | N | install CAC/OAC relays for RTU upgrade. | Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2017-12-11 | 2017-12-13 23:00 | N | N | SWEATD ISD Dec 11, 2017 | Line
ENMAX | 13.82L (ENMAX 22 - ENMAX 13) | 2017-12-11 00:01 | 2017-12-11 01:00 | N | N | install CAC/OAC relays for RTU upgrade | Line |  | Devices will need to be operated locally due to RTU change out. Close open close operation required for commissioning. | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2017-12-11 01:00 | 2017-12-11 02:00 | N | N | install CAC/OAC relays for RTU upgrade | Line |  | Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning. | Firm Load Loss, Creates Radial Feeds
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2017-12-11 02:00 | 2017-12-11 04:00 | N | N | install CAC/OAC relays for RTU upgrade | Line, Transformer |  | Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning. | For Information Only
ALTALINK | 289s 1152 (289s Saunders Lake) | 2017-12-11 07:00 | 2017-12-11 17:00 | N | N | replace faulted CTs in 138kv dead tank breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 287s 652 (287S Hazelwood) | 2017-12-11 07:30 | 2017-12-13 17:30 | N | Y | urgent breaker mechanism repair-wired incorrectly | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 420L (214s Innisfail - 287s Hazelwood),287s 1152 (287s Hazelwood) | 2017-12-11 07:30 | 2017-12-13 17:30 | N | N | trouble shoot & repair the VT8 ground alarm at 287s impacting the operation of 420L B protection | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 6.1TR (ENMAX 6) | 2017-12-11 08:00 | 2017-12-11 16:00 | N | N | oil sampling | Transformer |  |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2017-12-11 08:00 | 2017-12-11 18:00 | N | N | outage required to replace 36.2TR failed bushings | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1s 452 (29EDD-1 Millennium) | 2017-12-11 08:00 | 2017-12-14 20:00 | N | Y | emergency break-in work | Circuit Breaker |  |  | 240 kV
ENMAX | 15.62L (ENMAX 15 - ENMAX 16),21.61L (ENMAX 21 - ENMAX 34) | 2017-12-11 08:00 | 2017-12-11 16:00 | N | N | transmission line clearance violation | Line |  | Transmission Line Clearance Violation. GOI to be issued to OH-45 (Don Bennett, 403-689-9425) | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 667L (370s North Lethbridge - 146s Lethbridge MacDonald) | 2017-12-11 08:00 | 2017-12-15 16:00 | N | Y | removing overhead line | Line |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2017-12-11 09:30 | 2017-12-11 14:30 | N | Y | [SWEATD] line protection upgrade @ 197s | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 197S Bardo | 2017-12-11 10:00 | 2017-12-11 14:00 | N | N | [SWEATD] addition of fusing to bus PT distribution inside of control building | Station |  |  | For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt) | 2017-12-11 10:30 | 2017-12-14 16:30 | N | N | replace 797 line control cables and perform trip tests | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2017-12-11 12:15 | 2017-12-15 17:45 | N | N | component replacement, breaker tank heater repair | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2017-12-11 14:31 | 2017-12-14 14:00 | N | N | [SWEATD] line protection upgrade @ 197s | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2017-12-11 17:00 | 2017-12-11 17:30 | N | N | [SWEATD] energize 174L (289s-197s) | Line |  |  | For Information Only
ALTALINK | 574s T1 (574s Nilrem) | 2017-12-12 07:00 | 2017-12-12 19:00 | N | Y | urgent replace grounding | Terminal Equipment |  |  | 240 kV, For Information Only
ALTALINK | 767L (320p Keephills - 767L167A) | 2017-12-12 07:00 | 2017-12-14 17:30 | N | N | migrate controls, annunciation and analogs to new RTU | Line |  | Migrate controls, annunciation and analogs to new RTU. Redundant protections will be taken out of service one at a time. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 896L (19s Wabamun - 432s Carvel),432s 896 (432s Carvel) | 2017-12-12 07:00 | 2017-12-12 18:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 823S Wapiti | 2017-12-12 08:00 | 2017-12-12 17:00 | N | N | remove 25kV open jumper J2 and disconnect 902S secondary taps to 25kV bus | Station |  | Remove 25kV open jumper J2, disconnect 902S secondary taps to 25kV bus. -------- Load Transfer -------- 823S 5L371 Peak Load = 9.53 MVA 823S 5L370 Peak Load = 6.47 MVA 823S 5L371 Relay Settings: 13.8 MVA CO9 (Setting change reqd) 823S 5L370 Relay Settings: 13.8 MVA CO9 (Setting change reqd) -------- Load Transfer -------- | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 33 B138-33.83 (ENMAX 33),33.1TR (ENMAX 33) | 2017-12-12 08:00 | 2017-12-12 12:00 | N | N | upgrade RTU and CAC/OAC relays | Line, Circuit Breaker, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 945L (275s Jenner - 562s Cypress),275s 5 (275s Jenner),275s 8 (275s Jenner) | 2017-12-12 08:00 | 2017-12-12 12:00 | N | Y | repair 275s6 switch | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 33s6 (33s Spray) | 2017-12-12 08:00 | 2017-12-12 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 9L934 (132s Ware Junction - 801s Anderson),801s 909 (801s Anderson),801s 910 (801s Anderson) | 2017-12-12 08:00 | 2017-12-12 18:00 | N | Y | logic function test 909A and 910A | Circuit Breaker, Line |  | Logic function test 909A and 910A, 909 and 910 will be opened to perform tests, 9L934 will be open ended @ 801s, done in conjunction with CSP 2-43669 | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21),44s 50X (44s Bearspaw) | 2017-12-12 08:30 | 2017-12-12 16:00 | N | Y | emergency replace tank heater | Circuit Breaker, Line |  |  | Pre-Condition
TRANSALTA, STROBE | 240s T1 (240s McBride Lake),240s T3 (240s McBride Lake) | 2017-12-12 09:00 | 2017-12-12 15:00 | N | N | gas relay replacement,gas relay test | Transformer |  |  | Restricts Generation
ALTALINK | 212s T1 (212s N.E.Lacombe) | 2017-12-12 09:00 | 2017-12-12 17:00 | N | N | working on DC circuits inside the old control building | Transformer |  |  | For Information Only
ALTALINK | 28s T1 (28s West Brooks),28s 240kV Bus 1 (28s West Brooks) | 2017-12-12 09:30 | 2017-12-13 18:00 | N | Y | replace 1 PT at 28s19 (Like for Like) | Transformer, Bus |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 932s 905 (932s Pemukan) | 2017-12-12 10:30 | 2017-12-12 12:30 | N | Y | change CT ratio | Circuit Breaker |  | CT Ratio Change, breaker outage only, no impact to system. | 240 kV, For Information Only
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33),ENMAX 33 B138-33.84 (ENMAX 33) | 2017-12-12 12:00 | 2017-12-12 16:00 | N | N | upgrade RTU and CAC/OAC relays | Line, Circuit Breaker, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 932s 906 (932s Pemukan) | 2017-12-12 13:00 | 2017-12-12 15:00 | N | Y | change CT ratio | Circuit Breaker |  | CT Ratio Change, breaker outage only, no impact to system. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 874L (522s Cooking Lake - 45s Bretona),522S 138 KV BUS 1 (522s Cooking Lake) | 2017-12-12 15:00 | 2017-12-12 17:00 | N | N | [SWEATD] test energize new 522s1252 remotely | Line, Bus |  | [SWEATD] Open 874L & isolate 522s partial 138kV bus in order to test energize new 522s1252 remotely | Firm Load Loss, Creates Radial Feeds
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2017-12-13 06:30 | 2017-12-17 19:30 | N | Y | eye nut changeout | Line |  | Eye Nut changeout. This outage will require an outage to a significant DG signalta resources at 368s | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 676L (523s Bullshead - 244s Bowmanton) | 2017-12-13 06:30 | 2017-12-17 19:30 | N | Y | eye nut changeout | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 574s T2 (574s Nilrem) | 2017-12-13 07:00 | 2017-12-13 19:00 | N | Y | replace grounding - urgent | Transformer |  |  | 240 kV, For Information Only
ENMAX | 5.6TR (ENMAX 5) | 2017-12-13 08:00 | 2017-12-13 16:00 | N | N | test gas relay (63M/63TC) | Transformer |  |  | For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11),ENMAX 13 B138-11.81 (ENMAX 13) | 2017-12-13 08:00 | 2017-12-13 11:00 | N | N | install CAC/OAC relays for RTU upgrade | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 719AL (581s Amoco Ricinus - 719LAL1) | 2017-12-13 09:00 | 2017-12-13 15:00 | N | N | emergency repair; splice out damage conductor | Line |  |  | For Information Only
SUNCOR | 635EDD-1000 635-752-121 (635EDD-1000) | 2017-12-14 08:00 | 2017-12-16 17:00 | N | N | breaker tank heater troubleshooting | Circuit Breaker |  | breaker tank heater troubleshooting/replacement | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2017-12-14 08:00 | 2017-12-14 16:00 | N | N | test gas relay | Transformer |  |  | For Information Only
ENMAX | ENMAX 34 | 2017-12-14 08:00 | 2017-12-14 12:00 | N | N | station service transformer: transfer switch will not function properly | Station |  |  | For Information Only
ALTALINK | 898L (37s North Calder - 92s Viscount),92s 898 (92s Viscount) | 2017-12-14 08:30 | 2017-12-14 17:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (Line Creek Tap - Elkford Tap) | 2017-12-14 09:00 | 2017-12-14 17:00 | N | Y | complete commissioning for new control wiring to MOD terminals | Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ATCO | 706s 703 (706s Irish Creek) | 2017-12-14 12:00 | 2017-12-15 12:00 | N | N | breaker fail testing for cap bank addition | Circuit Breaker |  | Breaker fail testing for cap bank addition | Pre-Condition
ENMAX | 12.1TR (ENMAX 12) | 2017-12-15 08:00 | 2017-12-15 16:00 | N | N | RTU upgrade | Transformer |  |  | For Information Only
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton) | 2017-12-16 07:15 | 2017-12-18 16:45 | N | N | install new structures | Line |  |  | Pre-Condition
ALTALINK | 42S Sarcee | 2017-12-16 10:00 | 2018-01-10 08:00 | N | N | 42s552 under outage until salvage | Station |  |  | For Information Only
EPCOR | Woodcroft T3 (Woodcroft) | 2017-12-17 07:00 | 2017-12-17 17:00 | N | N | bus maintenance | Transformer |  |  | For Information Only
ALTALINK | 42s C1 (42s Sarcee),42s1652 (42s Sarcee) | 2017-12-18 08:00 | 2017-12-18 09:00 | N | N | test trips to 42s1652 | Circuit Breaker, Shunts |  |  | For Information Only
ATCO, ALTALINK | 7L77 (395s North Holden - 709s Vegreville) | 2017-12-18 08:00 | 2017-12-20 17:00 | N | Y | arm changes | Line |  | Arm changes | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2017-12-18 09:00 | 2017-12-18 11:00 | N | N | hot spot repair | Line |  | 775S - 601A Hot Spot Repair HOT SPOT ON 601A >30 DEG C, NEED TO OPERATE SWITCH 6L15 WILL BE OUT OF SERVICE | Pre-Condition, Over/Under Voltage
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7),42s 7 (42s Sarcee) | 2017-12-18 09:00 | 2017-12-18 10:00 | N | Y | function trips test on 42s7 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21),42s 21 (42s Sarcee) | 2017-12-18 10:01 | 2017-12-18 11:00 | N | Y | function trips test on 42s21 | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 42s 80 (42s Sarcee) | 2017-12-18 11:01 | 2017-12-18 12:00 | N | N | function trips test on 42s80 | Circuit Breaker |  | Function trips test on 42s80 | Pre-Condition
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde) | 2017-12-18 11:30 | 2017-12-18 16:30 | N | N | CT hot spot repair | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 42s T1 (42s Sarcee),42s 40 (42s Sarcee) | 2017-12-18 12:01 | 2017-12-18 13:00 | N | Y | function trips test on 42s40 | Transformer, Circuit Breaker |  | Function trips test on 42s40 Issue to: Mark MacHattie | 240 kV, Pre-Condition
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2017-12-18 12:15 | 2017-12-21 17:45 | N | N | component replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2017-12-20 06:00 | 2017-12-21 14:45 | N | Y | replace cross arm on structure | Line |  |  | 240 kV, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72MG16 (Meadowlark - Garneau) | 2017-12-20 07:00 | 2017-12-21 17:00 | N | N | urgent request - CVT replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
VISIONREQ, ALTALINK, TRANSALTA | 528s Blue Trail Wind Farm RTU/SCADA,322s Cowley Ridge RTU/SCADA,418s Ardenville RTU/SCADA,239s Castle River RTU/SCADA,240s McBride Lake RTU/SCADA,243s Soderglen Wind Farm RTU/SCADA,354s Summerview RTU/SCADA | 2017-12-20 08:30 | 2017-12-20 17:00 | N | N | firmware upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 339s T1 (339s Duchess),831L (339s Duchess - 831L tap),339s 20 (339s Duchess) | 2017-12-20 10:00 | 2017-12-20 10:15 | N | N | de-energize station to allow for the safe reset of 339s19 | Switch, Transformer, Line |  | Altalink is taking a 15 minute outage to 339s to fix the faulting switch. The faulting switch is currently not completely reset and may not operate correctly. We have worked out the load transfer with Fortis. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2017-12-20 22:00 | 2017-12-21 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2017-12-21 02:00 | 2017-12-21 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation, For Information Only
ATCO | 813s 902T (813s Little Smoky),813s Little Smoky 240kV Bus 2 | 2017-12-21 09:30 | 2017-12-21 17:00 | N | Y | emergency clean and check 813S 902TD | Transformer, Bus |  | 813S 902TD Clean and Check Operation EMERGENCY WORK DUE TO 902TD switch failure due to damage of melting rubber. Clean up switch and check operation THIS IS TIED TO CSP 2-44210 Coordinate with AESO to dispatch 75 MW GP TMR at Poplar Hill & Lowe Lake If the switch is not repairable and does not operate properly the switch will be manually opened so that the 240KV breakers can be closed back in. 902T will remain out of service | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 838L (14s Devon - 325s Leduc),325s T2 (325s Leduc),325s Leduc 138kV Bus 2 | 2017-12-22 08:00 | 2017-12-22 12:00 | N | N | [SWEATD] install new name plate tags for VT6 | Line, Bus, Transformer |  | [SWEATD] Install new name plate tags for VT6 (LOAs), energize 325s cap/filter bank | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 86s T1 (86s Bigstone) | 2017-12-27 10:12 | 2017-12-28 15:35 | N | Y | 86s station service transformer failure | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 42s C1 (42s Sarcee),42s 1652 (42s Sarcee) | 2017-12-28 08:00 | 2018-01-03 17:00 | N | N | 42s1652s forced outage | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 813s SVC (813s Little Smoky) | 2017-12-29 13:30 | 2018-01-08 17:00 | N | Y | SVC emergency repairs | Shunts |  | SVC emergency repairs to the de-ionized water system
ALTALINK | 320p T1 (320p Keephills) | 2017-12-29 14:46 | 2018-01-02 23:33 | N | Y | low gas pressure, forced out | Transformer |  |  | 240 kV
ATCO | 734s 701 (734s Sturgeon) | 2017-12-31 | 2018-01-02 23:00 | N | N | Replace 734s704 with 734s701. ISD: Dec 7, 2017 | Circuit Breaker
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2017-12-31 08:00 | 2017-12-31 16:00 | N | N | emergency outage top up low oil level in the LTC | Transformer |  |  | 240 kV
ATCO | 801s Anderson 240kV BUS #2 | 2018-01-02 07:00 | 2018-01-08 07:00 | N | Y | protection upgrade | Bus |  | 240kV bus # 2 OOS for Construction - Protection upgrade, Breaker and a third bus configuration at 801s will be open at one end. Jan 2-8, 2018 - 900BUS#2 OOS - Isolation points: 900PT2X, 904B, 908B, 912B @801S Anderson Jan 8-25, 2018 - Expand outage to include, 900BUS#2 & 9L70 - Isolation points: 900PT2X, 903A, 908B, 912B @801S Anderson & 9L70D2 @946S Oakland | 240 kV
ATCO | 734s 702T (734s Sturgeon) | 2018-01-02 08:00 | 2018-01-04 16:00 | N | N | test new wiring to 702T and 702 breaker | Transformer |  | To test new wiring to 702T and 702 Breaker, 701T must be in service to supply 25kv load prior to this work proceeding. | For Information Only
ALTALINK | 17s T2 (17s Benalto),17s 9 (17s Benalto) | 2018-01-02 12:30 | 2018-01-04 17:30 | N | Y | emergency outage,emergency outage, oil leaks | Transformer, Circuit Breaker |  |  | 240 kV
ALTALINK | 574s T2 (574s Nilrem),574s T1 (574s Nilrem) | 2018-01-02 13:00 | 2018-01-03 18:00 | N | Y | emergency outage, replace the transformer grounds | Transformer, Terminal Equipment |  |  | 240 kV, For Information Only
ATCO | 9L01 (888s Dover - 848s Ruth Lake),848s 9L01D1 (848s Ruth Lake),888s 9L01D2 (888s Dover) | 2018-01-03 06:30 | 2018-01-06 17:00 | N | Y | install piles for new structures for Thickwood tap | Line, Switch |  | Install piles for new structures for Thickwood tap. | 240 kV
ALTALINK | 633L (56s Boyle - 405s Waupisoo),405s 633 (405s Waupisoo) | 2018-01-03 09:30 | 2018-01-03 16:30 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 223 (159s Colinton) | 2018-01-04 07:30 | 2018-01-04 14:30 | N | N | replace tank heater | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss
ENMAX, ALTALINK | 12.2TR (ENMAX 12),833L (ENMAX 2 - ENMAX 12),ENMAX 12 B138-833L (ENMAX 12) | 2018-01-04 08:00 | 2018-01-04 12:00 | N | Y | install CAC/OAC relays and rewire device 43 for RTU upgrade | Line, Circuit Breaker, Transformer |  | Install CAC/OAC relays and rewire dev. 43 for RTU upgrade. Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s T2 (17s Benalto) | 2018-01-04 08:30 | 2018-01-04 09:00 | N | Y | fix oil leaks | Transformer |  | Trouble Corrective: Fix oil leaks on 17s T2 Tx18477 | 240 kV, For Information Only
ENMAX, ALTALINK | 12.1TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2018-01-04 12:00 | 2018-01-04 16:00 | N | Y | inInstall CAC/OAC relays and rewire device 43 for RTU upgrade | Line, Circuit Breaker, Transformer |  | Install CAC/OAC relays and rewire dev. 43 for RTU upgrade. Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 935L (324s Cassils - 356s Milo) | 2018-01-05 07:15 | 2018-01-24 18:45 | N | Y | line maintenance | Line |  |  | 240 kV
CENOVUS | 539S 9301T (539s Sunday Creek) | 2018-01-06 07:00 | 2018-01-06 18:00 | N | Y | replace faulty temperature gauge | Transformer |  |  | 240 kV, For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2018-01-06 08:00 | 2018-01-06 16:00 | N | N | repair distribution cable which runs directly over 9.83L cable at Heritage Dr. and Bonaventure Dr. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L70 (946s Oakland - 801s Anderson),801s Anderson 240kV BUS #2 | 2018-01-08 07:01 | 2018-01-25 17:00 | N | Y | protection upgrade | Bus, Line |  | 240kV bus # 2 OOS for Construction - Protection upgrade, Breaker and a third bus configuration at 801s will be open at one end. Jan 2-8, 2018 - 900BUS#2 OOS - Isolation points: 900PT2X, 904B, 908B, 912B @801S Anderson Jan 8-25, 2018 - Expand outage to include, 900BUS#2 & 9L70 - Isolation points: 900PT2X, 903A, 908B, 912B @801S Anderson & 9L70D2 @946S Oakland | 240 kV, Contingency Requires Mitigation
ATCO | 7L89 (826s Marguerite Lake - 721s La Corey) | 2018-01-08 08:00 | 2018-01-11 17:00 | N | Y | to change double circuit poles on 7L89/7L91 | Line |  | Pole change on 7L89/7L91 double cct line, 721s radial fed from 700s | Pre-Condition
ALTALINK | 186s C1 (186s Dry Creek),186s T2 (186s Dry Creek),611L (391S Balzac - 186s Dry Creek),186s 611 (186s Dry Creek),186s 652 (186s Dry Creek),186s Dry Creek 138kV Bus 2 | 2018-01-08 09:00 | 2018-01-09 15:30 | N | N | replace 138kV Bus 2 differential relay | Line, Bus, Circuit Breaker, Shunts, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 704L (478s Tucuman - 704L tap),478s 152 (478s Tucuman),51s Wainwright 138kV Bus 2 | 2018-01-08 10:30 | 2018-02-08 15:00 | N | N | create open points C and D for new 51s252 and install new 51s704 and switches | Line, Bus, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 3452 (320p Keephills),320p 2952 (320p Keephills),1203L (320p Keephills - 510s Sunnybrook) | 2018-01-08 11:00 | 2018-01-11 17:00 | N | Y | migrate controls, annunciation and analogs to new RTU | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 896L (19s Wabamun - 432s Carvel),19s 896 (19s Wabamun),432s 896 (432s Carvel) | 2018-01-08 12:15 | 2018-01-11 17:45 | N | N | component replacements on 896L | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2018-01-09 07:00 | 2018-02-01 14:00 | N | Y | replacing structures and conductors from structures 1 - 151 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 759L (87s Gaetz - 276s Prentiss),87s 759E (87s Gaetz) | 2018-01-09 07:15 | 2018-01-12 17:45 | N | N | components maintenance | Line, Switch |  |  | For Information Only
ALTALINK | 325s C1 (325s Leduc) | 2018-01-09 08:00 | 2018-04-27 12:00 | N | N | forced outage | Shunts |  | (SWEATD) Cap bank remains OOS until ~late April while new settings are created/installed. Will update as return to service date is finalized | For Information Only
ALTALINK, ENMAX | 42s T2 (42s Sarcee),150L (42s Sarcee - 150L47),28.80L (42s Sarcee - ENMAX 28),3L (42s Sarcee - 272s Springbank),42s Sarcee 138 kV South Bus,35.81L (42s Sarcee - ENMAX 35) | 2018-01-10 08:00 | 2018-01-11 18:00 | N | N | [SWCRR] salvage 42s552 from underneath south bus | Bus, Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s 5652 (102s Langdon) | 2018-01-10 08:00 | 2018-01-10 12:00 | N | Y | change out burned up heaters | Circuit Breaker |  |  | 240 kV
ENMAX | 39.1TR (ENMAX 39) | 2018-01-10 08:00 | 2018-01-19 16:00 | N | N | replace Z1 8kV feeder panel doors | Transformer |  |  | For Information Only
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2018-01-10 13:00 | 2018-01-10 15:00 | N | N | urgent replacement on broken insulators | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s 7452 (102s Langdon) | 2018-01-10 13:00 | 2018-01-10 16:00 | N | Y | change out burned up heaters | Circuit Breaker |  |  | 240 kV
ALTALINK | 675L (244s Bowmanton - 41s Medicine Hat) | 2018-01-11 07:00 | 2018-01-17 17:30 | N | Y | cut free 675L from 41s & cut in 675L at 321s Al Rothbauer | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2018-01-11 08:00 | 2018-01-11 17:00 | N | N | replace jumpers/risers on 6L12D4 found from heat scanning | Line |  | Replace Jumpers/risers on 6L12D4 found from heat scanning. Insulator and jumper at Monitor sub | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74S CAP14 (74s Janet),74s 54 (74s Janet) | 2018-01-11 08:30 | 2018-01-11 15:30 | N | N | replace faulty relay | Circuit Breaker, Shunts |  |  | Pre-Condition
ALTALINK | 102s 252 (102s Langdon) | 2018-01-11 11:00 | 2018-01-11 15:00 | N | Y | change out burned up heaters | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 202L (61s Lodgepole - 202L335) | 2018-01-12 07:30 | 2018-01-12 12:30 | N | N | required to create open point A | Line |  | Required to create Open Point 'A'; AML Crew will use sticks to pull blade past 90 degrees | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 202L335) | 2018-01-12 07:30 | 2018-01-19 14:30 | N | N | required to adjust 202L335 | Line |  | Required to adjust 202L335; Jan. 13, 2018 the isolation zone will be contracted down to 202L335 and Open Point 'A' will be closed | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2018-01-13 08:00 | 2018-01-14 16:00 | N | Y | DGA sampling required, Doble PT Z44, 162PT138-T2, repair SW146, maintenance on SW88 | Transformer, Bus |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 202L335 (202AL tap) | 2018-01-13 08:30 | 2018-01-13 17:30 | N | N | close open point 'A' | Switch |  |  | For Information Only
ATCO | 9L07 (888s Dover - 2011s Dawes) | 2018-01-14 07:00 | 2018-01-15 17:30 | N | Y | install pilings for new structures on 9L07 for new 951S Thickwood Hills substation | Line |  | Install pilings for new structures on 9L07 for new 951S Thickwood Hills substation. | 240 kV, Pre-Condition
ALTALINK | 38s T2 (38s East Edmonton) | 2018-01-15 07:00 | 2018-01-18 19:00 | N | N | install new CT's on T2 for new bus relay and bird cover-up | Transformer
VISIONREQ | 354s DVAR1 (354s Summerview) | 2018-01-15 08:00 | 2018-01-26 23:00 | N | N | repair | Shunts |  |  | For Information Only
Syncrude | Aurora 13 (Aurora),Aurora 14 (Aurora) | 2018-01-15 08:00 | 2018-01-15 18:00 | N | N | operate breakers to restore transmission line TL1 | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28) | 2018-01-15 08:00 | 2018-01-26 16:00 | N | Y | line protection upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2018-01-15 08:00 | 2018-01-15 16:00 | N | N | doble and gis check | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 162.3TR (162s Beddington) | 2018-01-15 08:00 | 2018-01-15 16:00 | N | N | repair LTC oil filter | Transformer |  |  | For Information Only
EPCOR | 805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2018-01-15 09:00 | 2018-01-17 08:00 | N | Y | manhole resurfacing | Transformer, Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 931L (132s Ware Junction - 28s West Brooks),28s 8 (28s West Brooks) | 2018-01-15 09:00 | 2018-01-25 15:30 | N | Y | breaker replacement | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2018-01-15 09:15 | 2018-01-18 17:45 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 775L (535s Joffre - 276s Prentiss) | 2018-01-15 09:15 | 2018-01-19 17:45 | N | N | components maintenance | Line |  |  | For Information Only
ALTALINK | 525s 850N (525s Carseland),850L (525s Carseland - 678s Okotoks) | 2018-01-15 09:30 | 2018-01-18 15:30 | N | N | replace breaker cts | Line, Circuit Breaker |  | Replace Breaker CT's 525s850N | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 6L11 (854s Swan Dive - 742s Freeman Lake) | 2018-01-15 12:00 | 2018-01-19 17:00 | N | N | line mitigation | Line |  | Line mitigation, 854s and 742s radial fed, 6L11D4 is DLO. 6L11 will have to be de-energized from 743s to open/close D4 (2 momentary outages to 742s Freeman Lk Dec 11 and Dec 15 in order to open 6L11D4) | Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2018-01-15 12:15 | 2018-01-18 17:45 | N | N | component replacements | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 930s Syn Condenser (930s Arcenciel) | 2018-01-16 00:15 | 2018-01-24 16:00 | N | Y | forced outage | Shunts |  |  | For Information Only
ALTALINK | 38s 780X (38s East Edmonton),780L (38s East Edmonton - 522s Cooking Lake) | 2018-01-16 07:00 | 2018-01-16 19:00 | N | N | trip testing and CT loops and sats for new bus relay | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2018-01-16 07:30 | 2018-01-16 16:00 | Y | Y | urgent trouble corrective:test and inspect breaker (flash over from lightning) | Line | Peak RC COS outage ID: 1-00532812 Peak RC Path Derate ID: 1-00532836 (E>W), 1-00532839 (W>E) |  | 500 kV
MONTANA | MATL (120s Picture Butte - Montana) | 2018-01-16 07:30 | 2018-01-16 16:00 | N | Y | align with 1201L outage | Line | PEAK COS outage ID:1-00532826 PEAK COS path de-rate ID1-00532834 (N-S), 1-00532835 (S-N) |  | 240 kV, Pre-Condition, Limits ATC
ENMAX | 1.83L (ENMAX 1 - ENMAX 8),ENMAX 1 B138-10A (ENMAX 1),ENMAX 1 B138-1A0 (ENMAX 1) | 2018-01-16 08:00 | 2018-01-17 16:00 | N | N | GIS SW check 1-10A101, 1-10A26, 1-10A8, 1-10A9, 1-1A101@1sub | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 63s T2 (63s Red Deer) | 2018-01-16 08:00 | 2018-01-17 17:00 | N | Y | fix oil leaks on T2 Tx18898 | Transformer |  |  | Overload, Contingency Requires Mitigation
ENMAX | 14.4TR (ENMAX 14) | 2018-01-17 08:00 | 2018-01-25 16:00 | N | N | 14.4TR panel replacement | Transformer |  |  | For Information Only
ALTALINK | 74S CAP14 (74s Janet),74s 54 (74s Janet) | 2018-01-17 08:00 | 2018-01-17 16:00 | N | N | maintain 138kV SF6 Mitsubishi breaker cap bank | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 63s T1 (63s Red Deer) | 2018-01-18 08:00 | 2018-01-18 16:00 | N | Y | fix oil leaks | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2018-01-18 08:00 | 2018-01-18 16:00 | N | N | GIS SW check 8-1A2, 8-2A1, 8-1A01@8sub | Line |  |  | For Information Only
ALTALINK | 738L (38s East Edmonton - 95s Imperial Oil Edmonton),38s 738W (38s East Edmonton) | 2018-01-18 08:30 | 2018-01-18 19:30 | N | N | trip testing and CT loops and sats for new bus relay | Circuit Breaker, Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 38s T4 (38s East Edmonton) | 2018-01-20 07:00 | 2018-01-20 19:00 | N | Y | trip testing for 38s18 and transformer inspection | Transformer |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L165 (718s Parsons Creek - 933s Tower Road) | 2018-01-20 08:00 | 2018-01-20 17:00 | N | N | change poles found by test and treat program | Line |  | Change poles found by test and treat program | Firm Load Loss, Creates Radial Feeds
ALTALINK | 897L (38s East Edmonton - 45s Bretona),38s 897 (38s East Edmonton) | 2018-01-21 07:30 | 2018-01-21 12:30 | N | N | trip testing and CT loops and sats for new bus relay | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s 75 (38s East Edmonton) | 2018-01-21 12:30 | 2018-01-21 18:30 | N | N | trip testing and CT loops and sats for new bus relay | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 557s T1 (557s Castle Downs) | 2018-01-22 07:00 | 2018-01-26 17:00 | N | Y | calisto install | Transformer |  |  | 240 kV, For Information Only
ENMAX | 8.3TR (ENMAX 8) | 2018-01-22 08:00 | 2018-01-28 12:00 | N | N | install neutral ground reactors | Transformer |  |  | For Information Only
ENMAX | 32.1TR (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),26.81L (ENMAX 32 - ENMAX 26) | 2018-01-22 08:00 | 2018-01-22 16:00 | N | N | maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 751s 701T (751s Hill) | 2018-01-22 08:00 | 2018-02-21 16:00 | N | N | transformer replacement | Transformer |  | Transformer Replacement, 701T load will be transferred to 702T | For Information Only
TRANSALTAW | 418s T2 (418s Ardenville) | 2018-01-22 09:00 | 2018-01-23 16:00 | N | Y | repair circuit breaker 35CB2 | Transformer |  |  | Restricts Generation
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2018-01-22 09:00 | 2018-01-29 16:00 | N | N | replace rotten cross arms | Line |  | Replace rotten cross arms | Pre-Condition
STROBE | 240S McBride Lake | 2018-01-22 09:00 | 2018-01-22 13:00 | N | N | upgrade and test SCADA controls | Station |  |  | Restricts Generation
ALTALINK | 851L (525s Carseland - 253s Blackie),525s 851X (525s Carseland) | 2018-01-22 09:30 | 2018-01-25 15:30 | N | N | replace breaker ct's | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 673L (283s Violet Grove - 131s Moon Lake) | 2018-01-22 10:30 | 2018-01-22 16:30 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s T3 (38s East Edmonton) | 2018-01-23 07:00 | 2018-01-24 19:00 | N | N | install new CTs on T3 for new bus relay, insulator replacements, install bird cover-up and trip testing | Transformer |  | Install new CT's on T3 for new bus relay, insulator replacements, installing bird cover-up and trip testing of 38s761N, 215N, 731E, 38s75 & 38s62
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2018-01-23 07:15 | 2018-01-26 17:45 | N | Y | component replacement | Line | 1. Transient Studies show that SOK(ac+dc) stability limit can be increase up to 2174 MW for 925L, 906L, 922L and 1140L outages if there are no concerns from RTCA. ( Note: limit for 925L,906L, 922L and 1112L = 2345 MW; limit for 925L,906L, 922L and 910L = 2348 MW; limit for 925L,906L, 922L and 914L = 2662 MW) - FQ. |  | 240 kV
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2018-01-23 07:15 | 2018-01-24 17:45 | N | Y | emergency repair; sleeve 906L structure 76/77 | Line | 1. Transient Studies show that SOK(ac+dc) stability limit can be increase up to 2174 MW for 906L, 922L, 925L and 1140L outages if there are no concerns from RTCA. ( Note: limit for 906L,922L, 925L and 1112L = 2345 MW; limit for 906L,922L, 925L and 910L = 2348 MW; limit for 906L,922L, 925L and 914L = 2662 MW) - FQ. |  | 240 kV, Pre-Condition
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2018-01-23 07:15 | 2018-01-26 17:45 | N | N | component replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2018-01-23 08:00 | 2018-01-23 16:00 | N | N | HV SW MD maintance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 384s T1 (384s Keystone),384s 15 (384s Keystone) | 2018-01-23 10:00 | 2018-01-23 11:00 | N | N | confirm supervisory operation of 384s15 | Transformer, Switch |  |  | For Information Only
ALTALINK | 305s T2 (305s Acheson) | 2018-01-24 07:30 | 2018-01-26 08:59 | N | N | 305s 25kV west bus - 305s28 installation and setting | Transformer |  |  | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16),34B69-16.60 (ENMAX 34) | 2018-01-24 08:00 | 2018-01-24 12:00 | N | N | 34.1TR replacement | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32),32B138-32BT5 (ENMAX 32),ENMAX 32 SW89 (ENMAX 32) | 2018-01-24 08:00 | 2018-01-24 16:00 | N | N | HV SW maintenance SW86@32sub | Transformer, Switch, Circuit Breaker |  |  | For Information Only
ALTALINK | 250p11 (250p Bighorn),250P 1 (250P Bighorn Plant) | 2018-01-24 08:00 | 2018-01-24 20:00 | N | Y | maintenance | Switch, Circuit Breaker |  |  | Restricts Generation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34),34B69-21.61 (ENMAX 34) | 2018-01-24 12:00 | 2018-01-24 16:00 | N | N | 34.1TR replacement | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s 822X (38s East Edmonton),822L (133s Stelco Edmonton - 38s East Edmonton) | 2018-01-25 07:00 | 2018-01-25 12:00 | N | N | trip testing, CT loops and sats for new bus relay | Circuit Breaker, Line |  |  | For Information Only
ATCO, ALTALINK | 923L (2075s Newell - 356s Milo) | 2018-01-25 07:15 | 2018-01-26 18:45 | N | Y | complete line maintenance / trouble corrective work | Line |  |  | 240 kV, Impacts RAS
ENMAX | 40.2 TR (ENMAX 40) | 2018-01-25 08:00 | 2018-01-26 16:00 | N | N | replace top oil temp gauge | Transformer |  |  | For Information Only
ALTALINK | 322S Cowley Ridge | 2018-01-25 09:00 | 2018-01-25 13:00 | N | N | SCADA control upgrades and testing | Station |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn) | 2018-01-25 09:00 | 2018-01-25 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton),38s 761N (38s East Edmonton) | 2018-01-25 12:30 | 2018-01-25 19:00 | N | N | trip testing and CT loops and sats for new bus relay | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),38s 731E (38s East Edmonton),38s48 (38s East Edmonton) | 2018-01-26 07:00 | 2018-01-26 12:00 | N | N | trip testing and CT loops and sats for new bus relay | Switch, Circuit Breaker, Line |  |  | Overload, Contingency Requires Mitigation
SUNCOR | 29EDD-34 652_10301 (29EDD-34),29EDD-34 652_10201 (29EDD-34),29EDD-34 652_10200T (29EDD-34),29EDD-34 29PS-372 (29EDD-34),29PT-340 (29EDD-34),29PT-341 (29EDD-34),29EDD-34 29PS-375 (29EDD-34) | 2018-01-26 09:00 | 2018-01-29 18:00 | N | Y | project 1716 | Circuit Breaker, Transformer, Switch |  | Work associated with AESO approved Project 1716 - Suncor Plant 300HV . There will be no impact to AIES power flow, only Suncor downstream assets will be affected. 240 kV, For Information Only ALTALINK 305s T1 (305s Acheson) 1/26/2018 9:00:00 AM 1/26/2018 5:00:00 PM N N 25kV East Bus: close Open Point 'A' Transformer For Information Only ALTALINK, ENMAX 42s C1 (42s Sarcee),42s T1 (42s Sarcee),21.80L (42s Sarcee - ENMAX 21),7.82L (42s Sarcee - ENMAX 7),42s 80 (42s Sarcee),693L (42s Sarcee - ENMAX 10),42s Sarcee 138 kV North Bus 1/27/2018 8:00:00 AM 1/27/2018 6:00:00 PM N Y [SWCRR] salvage 42s43 Bus, Shunts, Transformer, Circuit Breaker, Line Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds ENMAX 8.1TR (ENMAX 8) 1/28/2018 12:00:00 PM 2/4/2018 12:00:00 PM N N install neutral ground reactors Transformer For Information Only ALTALINK 925L (63s Red Deer - 74s Janet) 1/29/2018 7:00:00 AM 2/2/2018 5:45:00 PM N Y Install bird divertors & component replacement Line Install bird divertors & Component Replacement. reference original SAP # 257916 240 kV, Pre-Condition ALTALINK 551L (945s Sunshine Village - 953s Lake Louise) 1/29/2018 7:00:00 AM 2/19/2018 6:00:00 PM N N energize/de-energize bypass line between Str135 and Str153 to allow for rebuild of 551L (sections 6) Line Energize/de-energize bypass line between Str135 and Str153 to allow for rebuild of 551L (Sections 6). Bypass to be energized/de-energized using live line techniques; no interruption to 551L loads For Information Only ALTALINK 929L (74S Janet - 287s Hazelwood) 1/29/2018 7:00:00 AM 2/1/2018 5:45:00 PM N Y installing bird diverters Line Installing bird diverters, changed from sap#257915 240 kV, Pre-Condition ALTALINK 420L (214s Innisfail - 287s Hazelwood),419L (214s Innisfail - 287s Hazelwood) 1/29/2018 7:15:00 AM 2/1/2018 5:30:00 PM N Y install bird divertors Line Install Bird Divertors. reference original SAP#257918.
Installing bird diverters. Refernece original SAP#257917." | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 834L (384s Keystone - 320p Keephills),320p 834X (320p Keephills) | 2018-01-29 07:30 | 2018-02-06 08:00 | N | N | replace CT & protections | Circuit Breaker, Line | Replace CTs and A & B protections |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.2TR (ENMAX 14),14.4TR (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2018-01-29 08:00 | 2018-01-30 16:00 | N | N | maintenance | Line, Shunts, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.4TR (ENMAX 34) | 2018-01-29 09:00 | 2018-01-29 15:00 | N | N | move cables in cable tray for 34.1TR replacement | Transformer |  | move cables in cable tray for 34.1TR replacement. Unshort bus CTs in 34.22 cell, outage scheduled for customer 9am-3pm. | For Information Only
REDDEER | 209s T1 (209s Timberlands) | 2018-01-29 09:00 | 2018-02-02 15:30 | N | N | repair transformer bushing | Transformer |  | Transformer oil continues to weep from the secondary bushing (X3) and tracking down the secondary incomer cables. The manufacturer (Siemens) will be onsite to warranty replace (X3) transformer bushing. | For Information Only
ALTALINK | 793L (87s Gaetz - 535s Joffre) | 2018-01-29 09:15 | 2018-01-31 12:00 | N | N | components maintenance | Line |  |  | For Information Only
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake),730s 704 (730s Rycroft) | 2018-01-29 10:00 | 2018-01-29 15:00 | N | N | hot spots clean connections | Line, Circuit Breaker |  | 730S 704 CT Hot Spots Clean connections 7L68 open ended | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 85L (35s Rundle - 85L12),35s 85 (35s Rundle) | 2018-01-29 10:30 | 2018-02-01 17:30 | N | Y | replacing 85L B protection module at 35s Rundle substation | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 703L (377s Hardisty - 703BL tap) | 2018-01-29 10:30 | 2018-02-06 17:30 | N | N | replace protections | Line | Replace 703L A & B protections |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s T1 (5s East Calgary) | 2018-01-29 12:00 | 2018-01-31 14:00 | N | Y | urgent repair to fix leaky H1 turret | Transformer |  |  | 240 kV, For Information Only
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2018-01-30 07:00 | 2018-01-30 17:00 | N | N | disconnect measurements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 945S Sunshine Village | 2018-01-30 07:30 | 2018-01-30 17:30 | N | N | 551BL1 raise bypass line conductors up and above 551BL tap | Station |  | Raise Bypass line conductors up and above 551BL Tap. 551BL is currently on a generator, and secondaries are cut clear | For Information Only
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-01-31 07:00 | 2018-02-27 18:00 | N | N | energize/de-energize bypass line between Str80 and Str109 to allow for rebuild of 551L (section 40) | Line |  |  | For Information Only
ALTALINK | 59s 852 (59s Peigan) | 2018-01-31 07:30 | 2018-01-31 14:30 | N | Y | top up SF6 gas | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2033s 704C (2033s Mowat) | 2018-01-31 10:00 | 2018-01-31 15:00 | N | N | relay change and test cap bank | Shunts |  | 2033S 704C Relay Change Change failed relay on 704C and test. Energize bank After relay has been installed and tested, energize 704C to confirm relay operation. Bank will be out of service and not available | For Information Only
ALTALINK | 765L (74s Janet - 151s Strathmore) | 2018-01-31 10:15 | 2018-01-31 14:45 | N | N | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 801s 910 (801s Anderson) | 2018-01-31 12:00 | 2018-01-31 17:00 | N | Y | protection upgrade, 9L100D1 logic testing | Circuit Breaker |  | Protection upgrade, 9L100D1 logic testing | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 10.1TR (ENMAX 10),832L (ENMAX 10 - ENMAX 12) | 2018-02-01 08:00 | 2018-02-01 16:00 | N | Y | transformer maintenance and broken line insulator replacement | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
STROBE | 240S McBride Lake | 2018-02-01 09:00 | 2018-02-01 13:00 | N | N | upgrade and test SCADA controls | Station |  |  | Restricts Generation
ALTALINK | 42s C1 (42s Sarcee),42s C3 (42s Sarcee) | 2018-02-01 09:00 | 2018-02-07 17:00 | N | Y | forced outage | Shunts |  | AltaLink reports; (42s -Sarcee) 240Kv Cap unavailable for approximately 1 week. (Relay problems). also 42s 138Kv 1652 cap unavailable- time unknown. | 240 kV, For Information Only
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2018-02-01 14:30 | 2018-02-02 18:00 | N | Y | reroute line away from river to highway | Line |  | Reroute line away from river to highway due to poles river bank erosion, will be coordinated with AltaLink work on 526L. 526L/6L126 loop will have to be returned to normal prior to outage. | Firm Load Loss, Creates Radial Feeds
ATCO | 9L07 (888s Dover - 2011s Dawes) | 2018-02-02 07:00 | 2018-02-11 17:30 | N | Y | install new in and out tap and string new portion 9L01/9L30 over 9L07 for new 951S Thickwood Hills substation | Line |  | Install new in and out tap and string new portion 9L01/9L30 over 9L07 for new 951S Thickwood Hills substation. | 240 kV, Pre-Condition
ATCO | 2029s 1214 (2029s Heathfield),2029s 1202 (2029s Heathfield) | 2018-02-02 08:00 | 2018-02-02 14:00 | N | N | urgent test operate MOD switches one at a time | Circuit Breaker |  |  | 500 kV
ALTALINK | 945L (275s Jenner - 562s Cypress) | 2018-02-03 06:15 | 2018-02-23 12:00 | N | Y | interphase spacer installation | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 162.3TR (ENMAX 162 Beddington) | 2018-02-03 08:00 | 2018-02-04 16:00 | N | N | In-service-date: Feb 3, 2018. | Transformer
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2018-02-03 08:00 | 2018-02-03 18:00 | N | Y | HV SW MD maintenance MD-162.81, SW82, SW83 | Line |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 959S SVC (959s Lanfine) | 2018-02-03 17:50 | 2018-02-14 16:00 | N | N | forced outage | Shunts
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37) | 2018-02-04 08:00 | 2018-02-04 16:00 | N | N | HV SW MD maintenance MD-37.1TR | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 8.5TR (ENMAX 8) | 2018-02-04 12:00 | 2018-02-11 15:00 | N | N | install neutral ground reactors | Transformer |  |  | For Information Only
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2018-02-05 07:00 | 2018-02-06 17:00 | N | N | line impedance and CT testing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark T2 (Meadowlark) | 2018-02-05 07:00 | 2018-02-05 12:00 | N | N | disconnect measurements | Transformer |  |  | For Information Only
ALTALINK | 325s C1 (325s Leduc) | 2018-02-05 07:00 | 2018-02-08 17:00 | N | N | [SWEATD] test and inspect resisters/C1/C2 banks | Shunts |  | [SWEATD] Test and inspect resisters/C1/C2 banks. | Pre-Condition
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake),717S Ethel Lake 144kV Bus | 2018-02-05 07:00 | 2018-02-16 17:00 | N | Y | install new 704A | Line, Bus |  | Install new 704A, 144 KV bus PT's, 704, 704T, 504TD, 7L66 OOS (7L66 is part of cold lake cutplane), 717s radial fed via 7L28 | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2018-02-05 08:00 | 2018-02-05 16:00 | N | N | adjust MD whips | Line, Transformer |  | Adjust MD Whips and Operation as Required [AVANTIS]. I & R Switch Not Fully Closing [AVANTIS]. West Phase of MD Requires Adjustment [AVANTIS] | Firm Load Loss, Creates Radial Feeds
ENMAX | 34.4TR (ENMAX 34) | 2018-02-05 08:00 | 2018-02-05 16:00 | N | N | prepare site for 34.1TR replacement | Transformer |  | Permanently remove from service to prep site for replacement transformer | For Information Only
EPCOR | 816sT1 (816s Petrolia) | 2018-02-05 08:00 | 2018-02-09 17:00 | N | Y | performing cutover of new ION metering | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 916L (42s Sarcee - 5s East Calgary),42s 916E (42s Sarcee) | 2018-02-05 09:00 | 2018-02-16 15:00 | N | Y | replacement of 42s916E breaker | Line, Circuit Breaker |  | Replacement of 42s916E breaker and LAs | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 54L (118s Canmore - 54L172),118s 54W (118s Canmore) | 2018-02-05 09:00 | 2018-02-07 15:00 | N | N | replacing B protection module | Circuit Breaker, Line |  | Replacing 54AL B protection module at 118s Canmore substation. | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 763L (158s Vauxhall - 763L259),158s 763N (158s Vauxhall) | 2018-02-05 09:30 | 2018-02-08 14:30 | N | N | replace breaker CT's | Line, Circuit Breaker |  | Replace Breaker CT's 158s163N | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1081L (17s Benalto - 281s Johnson),17s 3 (17s Benalto),17s 2 (17s Benalto) | 2018-02-05 10:00 | 2018-02-09 17:00 | N | Y | C60 installation for 17s3 breaker | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2018-02-05 10:30 | 2018-02-07 17:00 | N | N | salvage switches | Transformer |  | salvage switches, 191s4, 191s10, 191s14 | For Information Only
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2018-02-05 12:00 | 2018-02-12 16:00 | N | N | replace rotten cross arms | Line |  | Replace rotten cross arms | For Information Only
ATCO | 741s 701T (741s Fox Creek),741s 703 (741s Fox Creek) | 2018-02-06 07:00 | 2018-02-06 17:00 | N | N | breaker fail testing | Transformer, Circuit Breaker |  | Breaker fail testing. | For Information Only
EPCOR | 72NW15 (Namao - Woodcroft) | 2018-02-06 07:00 | 2018-02-06 17:00 | N | N | disconnect measurements | Line |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3),3.84L (ENMAX 13 - ENMAX 3) | 2018-02-06 08:00 | 2018-02-06 16:00 | N | N | I&R whip seating misalignment [AVANTIS] SF6 gas sample 3B138-3.84 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2018-02-06 08:00 | 2018-02-06 12:44 | N | N | replace the dead ends on all three phases | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 813s SVC (813s Little Smoky) | 2018-02-06 08:00 | 2018-02-06 16:00 | N | Y | change Pump #1 | Shunts |  | 813S SVC Change Pump #1 Change cooling pump SVC will be off line | Pre-Condition
ATCO | EX1-01 (879s Scotford Upgrader - 402s Scotford Expansion) | 2018-02-06 08:00 | 2018-02-06 16:00 | N | N | change contaminated insulators | Line |  | To change contaminated insulators, on EX1-01L | Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (268s Whitecourt - 526DL185) | 2018-02-06 10:00 | 2018-03-30 15:30 | N | Y | work between structures 1 - 151 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (272s Springbank - 3L147) | 2018-02-06 12:46 | 2018-02-06 17:30 | N | N | replace the dead ends on all three phases | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 741s 702T (741s Fox Creek),741s 704 (741s Fox Creek) | 2018-02-07 07:00 | 2018-02-07 17:00 | N | N | Breaker fail testing. | Transformer, Circuit Breaker |  | Breaker fail testing. | Pre-Condition
ENMAX | 1.83L (ENMAX 1 - ENMAX 8),Enmax 1 B138-1A0 (ENMAX 1),Enmax 1 B138-10A0 (ENMAX 1) | 2018-02-07 08:00 | 2018-02-08 16:00 | N | N | GIS SW check | Line, Circuit Breaker |  | GIS SW check 1-10A101, 1-10A26, 1-10A8, 1-10A9, 1-1A101@1sub | For Information Only
AIRLIQUIDE | ALC03L (408s Air Liquide Scotford - 402s Scotford Expansion) | 2018-02-07 08:00 | 2018-02-07 16:00 | N | Y | change contaminated insulators | Line |  | To change contaminated insulators, on ALC03L | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 11.3TR (ENMAX 11) | 2018-02-07 08:00 | 2018-02-09 16:00 | N | N | transformer maintenance | Transformer |  | Replace Both Winding and Temperature Gauges [AVANTIS] As Identified in WO277111. Transformer maintenance | For Information Only
EPCOR | 72MG16 (Meadowlark - Garneau) | 2018-02-07 12:00 | 2018-02-07 17:00 | N | N | disconnect measurements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 42s C1 (42s Sarcee) | 2018-02-07 17:01 | 2018-02-08 17:00 | N | N | forced outage | Shunts |  | AltaLink reports; (42s -Sarcee) 240Kv Cap unavailable for approximately 1 week. (Relay problems). also 42s 138Kv 1652 cap unavailable- time unknown. | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2018-02-07 23:00 | 2018-02-08 04:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2018-02-08 04:01 | 2018-02-08 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2018-02-08 07:00 | 2018-02-09 17:00 | N | N | line impedance and CT testing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | CROW | 2018-02-08 08:00 | 2018-02-08 09:00 | N | N | migration | SCInternal |  |  | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2018-02-08 08:00 | 2018-02-08 16:00 | N | N | commission new 34MD69-34.1TR Panel. install new risers on 34MD69-34.1TR | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L05 (813s Little Smoky - 809s Louise Creek) | 2018-02-08 08:00 | 2018-02-08 16:00 | N | N | investigate 903PT top discoloration and corona noise | Line |  | Investigate 903PT top discoloration and corona noise, 9L05 open ended, 240KV ring open. | 240 kV, Pre-Condition
ALTALINK | 704L (51s Wainwright - 478s Tuccuman) | 2018-02-08 08:00 | 2018-02-09 16:00 | N | N | In-service-date: Feb 08, 2018. 704L changed to 51s in and out configuration. | Line
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2018-02-08 08:00 | 2018-02-12 16:30 | N | Y | forced outage | Shunts, Circuit Breaker |  |  | 240 kV
ALTALINK | 338s T1 (338s Cherhill) | 2018-02-08 12:30 | 2018-02-08 16:00 | N | N | urgent trouble corrective | Transformer |  |  | 240 kV
ALTALINK | 704L (252s Jarrow - 704L tap),51s Wainwright 138kV Bus 1 | 2018-02-08 15:01 | 2018-03-01 09:00 | N | N | install new PTs and line renumbering | Line, Bus |  |  | Pre-Condition
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2018-02-10 08:00 | 2018-02-11 16:00 | N | N | switch and transformer maintenance | Line, Transformer, Shunts |  | HD SW MD maint MD-31.1TR, MD-31.2TR, SW84, SW85, SW86, SW89@31sub, check reversing SW 31.1TR. Oil sampling TR, TC 31.1TR, 31.2TR. Transformer maintenance 31.1TR | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2018-02-12 06:30 | 2018-02-12 11:23 | N | Y | forced outage | Line | PEAK COS outage ID:1-00547818 PEAK COS path de-rate ID1-00547840 (N-S), (S-N)1-00547843 |  | 240 kV, Pre-Condition, Limits ATC
EPCOR | Hardisty T1 (Hardisty),72CH11 (Hardisty - 987s Clover Bar) | 2018-02-12 07:30 | 2018-02-13 17:00 | N | N | relay maintenance | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark T3 (Meadowlark) | 2018-02-12 07:30 | 2018-02-20 17:00 | N | N | relay maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 729s 701T (729s Otauwau),7L49 (732s Mitsue - 729s Otauwau) | 2018-02-12 08:00 | 2018-02-13 15:00 | N | N | terminate and commission lockout from 702T protection and breaker 705 | Line, Transformer |  | Terminate and Commission Lockout from 702T protection and breaker 705 | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11) | 2018-02-12 08:00 | 2018-02-13 16:00 | N | N | switch maintenance and oil sample | Line, Transformer |  |  | Pre-Condition
EPCOR | 816s T2 (816s Petrolia) | 2018-02-12 08:00 | 2018-02-16 17:00 | N | Y | performing cutover of new ION metering | Transformer |  |  | 240 kV
ALTALINK | 821L (158s Vauxhall - 421s Hays) | 2018-02-12 09:30 | 2018-02-15 14:30 | N | N | replace breaker CT's 158s821E | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2018-02-12 10:00 | 2018-02-15 15:00 | N | Y | protections upgrade - C60 installation for 17s4 breaker/ trip from 17s5 C60 to 17s4 breaker | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 646L (678s Okotoks - 237s Foothills) | 2018-02-12 12:30 | 2018-02-12 16:30 | N | N | salvage 911L conductor of off joint use pole with 646L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 869L (204s Sandy Point - 163s Amoco Empress) | 2018-02-13 08:00 | 2018-02-13 17:00 | N | N | replace Leaking PT and trouble corrective | Line |  | Trouble Corrective: Replace Leaking PT. | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2018-02-13 09:00 | 2018-02-13 16:00 | N | N | faulted bushing | Transformer
BCH | 2L112 (Nelway - Boundary) | 2018-02-13 09:00 | 2018-02-13 17:00 | N | Y | change the tap change oil filter for T2 | Line | Peak RC COS: E-W>1-00544292 Peak RC COS: W-E>1-00544293 BC 2L112 Outage>1-00537314 |  | Limits ATC
ENMAX | 31.2TR (ENMAX 31) | 2018-02-14 08:00 | 2018-02-22 16:00 | N | N | transformer differential relay replacement. | Transformer
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.3TR (ENMAX 14),14.1TR (ENMAX 14),ENMAX 14 138kV Bus 1,11.82L (ENMAX 14 - ENMAX 11) | 2018-02-14 08:00 | 2018-02-15 16:00 | N | N | equipment maintenance | Line, Shunts, Transformer, Bus |  | HV SW maint SW81, SW82, SW83 @14sub. Oil sampling 14.1TR MT, TC. 14.3TR MT, TC. Check reversing SW | Pre-Condition
EPCOR | Hardisty T2 (Hardisty) | 2018-02-15 07:30 | 2018-02-16 17:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek),741s 702 (741s Fox Creek) | 2018-02-16 07:00 | 2018-02-16 17:00 | N | Y | breaker fail testing, 7L199 will be open ended @ 741s | Line, Circuit Breaker |  | Breaker fail testing, 7L199 will be open ended @ 741s. | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | E511s VictoriaT2 (511s Victoria) | 2018-02-16 07:30 | 2018-02-16 17:00 | N | N | tapchanger repair | Transformer |  |  | For Information Only
ENMAX | 7.84L (ENMAX 36 - ENMAX 7),ENMAX 36 B138-7.84 (ENMAX 36) | 2018-02-16 08:00 | 2018-02-16 16:00 | N | N | SF6 Gas pressure top up on 36B138-7.84 | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 924L (102s Langdon - 356s Milo) | 2018-02-16 09:15 | 2018-02-16 12:45 | N | Y | repair broken interphase spacer | Line |  |  | 240 kV, Pre-Condition
ATCO | 751s 701C (751s Hill),751s 704C (751s Hill),751s 701T (751s Hill),751s 702T (751s Hill),7L42 (751s Hill - 716s Lloydminster) | 2018-02-17 07:00 | 2018-02-21 17:00 | N | N | install mobile and replace 770PT1 | Transformer, Shunts, Line |  | Install mobile and replace 700PT1. Issue GOI 2-43492D (701T/501VR/144kV Bus OOS) (CROW ref 2-41226) Isolation Pts  703A, 704A, 7L14D2, 7L42D1, 510B, 511B, Further isolate 500PTY1, 500PTX1 @ 751s SOW  Replace 700PT1, Connect new 701T to 701TD, new construction, commissioning, FS - repair 702T hotspots | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 741s 705C (741s Fox Creek) | 2018-02-17 08:00 | 2018-02-20 20:00 | N | N | New cap bank in-service -date: Feb 18, 2018 | Shunts |  | Construction - Install new cap bank
ALTALINK | 17s 13 (17s Benalto) | 2018-02-19 06:30 | 2018-02-19 12:30 | N | Y | protections upgrade | Circuit Breaker |  | Protections Upgrade - Breaker trip tests /PMU | 240 kV, Pre-Condition
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek) | 2018-02-19 07:00 | 2018-03-02 17:00 | N | Y | attach Muir t-tap switch | Line |  | Attach Muir POD T-Tap switch 7LA90, 144kV ring bus will be open @ 813s. Issue COG on new 7LA90 line switch at tap. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek),741s 701 (741s Fox Creek) | 2018-02-19 07:00 | 2018-02-19 17:00 | N | Y | breaker fail testing, 7L90 already out-of-service | Line, Circuit Breaker |  | Breaker fail testing, 7L90 will already be OOS under GOI 2-42130 | Pre-Condition
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2018-02-19 08:00 | 2018-02-19 16:00 | N | N | adjust SW88 south phase alignment | Line |  | SW88@ 32sub. Adjust South Phase Alignment at Next Maintenance [AVANTIS] | Firm Load Loss, Creates Radial Feeds
AESO | 551CL1 (945s Sunshine - 551CL1 Tap) | 2018-02-19 12:30 | 2018-02-19 17:30 | N | N | re-connect tap to 551L mainline after section 6 rebuild | Line |  |  | For Information Only
ALTALINK | 17s 4 (17s Benalto) | 2018-02-19 12:30 | 2018-02-19 18:00 | N | Y | protections upgrade | Circuit Breaker |  | Protections Upgrade - Breaker trip tests /PMU | 240 kV, Pre-Condition
ALTALINK | 17s 9 (17s Benalto) | 2018-02-20 06:30 | 2018-02-20 12:30 | N | Y | protections upgrade, breaker trip tests and PMU | Circuit Breaker |  | Protections Upgrade - Breaker trip tests /PMU | 240 kV
ALTALINK | 74s T1 (74s Janet),932L (74s Janet - 162s Beddington),74s Janet 240kV Bus 1,929L (74S Janet - 287s Hazelwood),287s 352 (287s Hazelwood) | 2018-02-20 07:00 | 2018-02-20 12:30 | N | Y | create open point A | Line, Bus, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2018-02-20 08:00 | 2018-02-28 11:00 | N | Y | line mitigation | Line |  | Line Mitigation | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s 7552 (38s East Edmonton) | 2018-02-20 08:00 | 2018-02-20 19:00 | N | Y | urgent repair: replace damaged breaker control cables | Circuit Breaker |  | Urgent repair to replace damaged breaker control cables | 240 kV
ENMAX | ENMAX 26 B138-26BT3 (ENMAX 26) | 2018-02-20 08:00 | 2018-02-20 16:00 | N | N | repair tank heaters | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.3TR (ENMAX 11) | 2018-02-20 08:00 | 2018-02-20 12:00 | N | N | transformer measurements for CT replacement program | Transformer |  |  | For Information Only
ALTALINK | 74s 2052 (74s Janet) | 2018-02-20 08:00 | 2018-03-08 16:00 | N | N | 74s20N switch damaged - forced outage | Circuit Breaker |  |  | 240 kV
ALTALINK | 158s 763X (158s Vauxhall),763L (158s Vauxhall - 257s Hull) | 2018-02-20 09:00 | 2018-02-23 14:30 | N | N | replace breaker CT's | Circuit Breaker, Line |  | replace Breaker CT's158s763X | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 2 (17s Benalto) | 2018-02-20 12:30 | 2018-02-20 18:00 | N | Y | protections upgrade, breaker trip tests and PMU | Circuit Breaker |  | Protections Upgrade - Breaker trip tests /PMU | 240 kV
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2018-02-20 12:30 | 2018-03-01 17:30 | N | N | component replacements | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s T1 (74s Janet),932L (74s Janet - 162s Beddington),929L (74S Janet - 287s Hazelwood) | 2018-02-20 12:31 | 2018-03-08 13:00 | N | Y | 74s352 CT, 74s552 CT, 74s92 PT, 74s94 PT replacements | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 17s 1652 (17s Benalto) | 2018-02-21 06:30 | 2018-02-21 12:30 | N | Y | protections upgrade and breaker trip tests/PMU | Circuit Breaker |  |  | 240 kV, For Information Only
ATCO | 717s 602T (717s Ethel Lake),717s 703T (717s Ethel Lake),7L28 (717s Ethel Lake - 846s Grand Centre) | 2018-02-21 07:00 | 2018-03-05 17:00 | N | Y | salvage 703T and remaining old substation equipment | Transformer, Line |  | Salvage 703T and remaining old substation equipment All load transferred to New 704T Transformer via Temp Breaker 510 Stage 2 SLD Description - Remove O/H shield wires over the 25kV Lines and 144kV bus including the 72kV Transfer load to 704T Rewire Bkr702, 702CT, and 700PT1 to new control building and commission all, cut free 703T from 703TD, rename 703TD to 703A | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22) | 2018-02-21 08:00 | 2018-02-21 12:00 | N | N | transformer measurements for CT replacement program | Transformer |  |  | For Information Only
ALTALINK | 535s 6052 (535s Joffre) | 2018-02-21 08:00 | 2018-02-21 13:00 | N | N | top up SF6 | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10) | 2018-02-21 09:00 | 2018-02-22 17:00 | N | Y | [SWCRR] replacement of surge arrestor sets for 42s693 breaker | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 790s 509C1 (790s Poplar Hill),790s 509C2 (790s Poplar Hill),790s 509C3 (790s Poplar Hill),790s 509C4 (790s Poplar Hill),790s 509C5 (790s Poplar Hill),790s 509 (790s Poplar Hill) | 2018-02-21 09:00 | 2018-02-21 13:00 | N | N | microprocessor based complete relay testing | Shunts, Circuit Breaker |  | Microprocessor based complete Relay Testing, on breaker 509, 509C will be out of service for the duration, no isolation required | For Information Only
ENMAX | 22.3TR (ENMAX 22) | 2018-02-21 12:00 | 2018-02-21 16:00 | N | N | transformer measurements for CT replacement program | Transformer |  |  | For Information Only
ALTALINK | 17s T2 (17s Benalto),17s 85 (17s Benalto) | 2018-02-21 12:30 | 2018-02-21 18:00 | N | Y | protections upgrade and breaker trip tests/PMU | Transformer, Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 535s 6452 (535s Joffre) | 2018-02-21 13:00 | 2018-02-21 17:00 | N | N | top up SF6 | Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2018-02-21 17:01 | 2018-02-22 17:00 | N | N | to changes 174 arm structures | Line |  | To changes 174 arm structures | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s C1 (17s Benalto),17s 16 (17s Benalto) | 2018-02-22 06:30 | 2018-02-22 12:30 | N | Y | protections upgrade - breaker trip tests /PMU | Circuit Breaker, Shunts |  |  | 240 kV
ENMAX | 41.2TR (ENMAX 41) | 2018-02-22 08:00 | 2018-02-22 12:00 | N | N | transformer measurements for CT replacement program | Transformer
CMH | Medicine Hat ICCP Outage | 2018-02-22 09:30 | 2018-02-22 11:30 | N | N | ICCP connection outage | Terminal Equipment |  |  | Affects Visibility
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2018-02-22 10:00 | 2018-02-22 12:00 | N | N | temporary repair to double circuit pole | Line |  | Temporary repair to double circuit pole, Pole will be replaced at a later date. | Pre-Condition, Over/Under Voltage
ENMAX | 12.1TR (ENMAX 12) | 2018-02-22 12:00 | 2018-02-22 16:00 | N | N | transformer measurements for CT replacement program | Transformer
ALTALINK | 815L (13s Deerland - 127s Bruderheim) | 2018-02-22 13:00 | 2018-02-22 17:00 | N | N | replace faulty VSR1000 with new relay and test | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.3TR | 2018-02-23 08:00 | 2018-03-05 16:00 | N | N | Transformer differential relay replacement | Terminal Equipment
ENMAX | 31.3TR (ENMAX 31) | 2018-02-23 08:00 | 2018-03-02 16:00 | N | N | transformer differential relay replacement | Transformer |  |  | For Information Only
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress) | 2018-02-23 12:30 | 2018-03-06 16:45 | N | Y | interphase spacer installation | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27) | 2018-02-24 08:00 | 2018-02-25 16:00 | N | N | maintenance: SW61, SW62, SW63, SW67, SW68, SW71, MD-16.1TR at ENMAX 16 | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1140L (289s Saunders Lake - 89s Ellerslie),289s 1452 (289s Saunders Lake),289s 1552 (289s Saunders Lake) | 2018-02-26 07:00 | 2018-02-26 11:30 | N | Y | [SWEATD] install grounding stirrups on 1140L stub bus | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
Saskpower | Sask Power CC904T | 2018-02-26 07:00 | 2018-02-26 16:00 | N | N | repair to CC815A | Transformer |  |  | For Information Only
AESO-SC | DT,ETS | 2018-02-26 07:00 | 2018-03-01 16:00 | N | N | improve database and application performance | SCInternal |  |  | For Information Only
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2018-02-26 08:00 | 2018-03-01 17:00 | N | N | changes 174 arm structures | Line |  | To changes 174 arm structures | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.3TR (ENMAX 14) | 2018-02-26 08:00 | 2018-03-09 16:00 | N | N | feeder panel replacement | Transformer |  |  | For Information Only
ENMAX | 16.2TR (ENMAX 16),16.60L (ENMAX 34 - ENMAX 16),16.63L (ENMAX 16 - ENMAX 36) | 2018-02-26 08:00 | 2018-02-27 16:00 | N | N | maintenance | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | Security Patching | 2018-02-26 09:00 | 2018-02-26 16:00 | N | N | Microsoft security updates and patches | SCInternal |  |  | For Information Only
EPCOR | 72NW15 (Namao - Woodcroft) | 2018-02-26 09:00 | 2018-03-28 15:00 | N | N | line maintenance & upgrades | Line |  |  | For Information Only
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2018-02-26 10:00 | 2018-02-26 17:00 | N | N | reboot Optimux 125 in Rainbow Lake substation | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1048L (138s Windy Flats - 59s Peigan) | 2018-02-26 11:00 | 2018-02-26 18:00 | N | Y | RAS scheme modifications | Line |  | RAS scheme 129, 604, 605 modifications as directed by AESO. affecting 1048L protections | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 1112L (289s Saunders Lake - 89s Ellerslie),289s 1752 (289s Saunders Lake),289s 1852 (289s Saunders Lake) | 2018-02-26 12:00 | 2018-02-26 17:30 | N | Y | [SWEATD] install grounding stirrups on 1112L stub bus | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 320p 2152 (320p Keephills) | 2018-02-26 13:00 | 2018-02-26 16:00 | N | Y | low in gas | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 910L (289s Saunders Lake - 288s Wolf Creek),289s 1352 (289s Saunders Lake),289s 1452 (289s Saunders Lake) | 2018-02-27 07:00 | 2018-02-27 11:30 | N | Y | Install Grounding stirrups on 910L stub bus | Line, Circuit Breaker |  | Install Grounding stirrups on 910L stub bus | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 421s T1 (421s Hays) | 2018-02-27 07:15 | 2018-02-27 17:30 | N | N | 138kV Bus Bus Protection Upgrade - Cut over Cts and trip tests on 25kV Breakers | Transformer |  |  | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays),421s 795N (421s Hays) | 2018-02-27 07:15 | 2018-02-27 17:30 | N | N | 138kV bus protection upgrade and CT cutover | Circuit Breaker, Line |  | 138kV Bus Protection Upgrade CT Cutover | Firm Load Loss, Creates Radial Feeds
NWE | Marias Shunt Capacitor | 2018-02-27 07:30 | 2018-07-13 20:00 | N | N | take down shunt bank 3, disassemble and order repplacement parts | Shunts |  |  | For Information Only
AESO-SC | MARGO | 2018-02-27 08:00 | 2018-02-27 14:00 | N | N | database cleanup on MARGO, to improve performance, and reduce unused data | SCInternal |  |  | For Information Only
ALTALINK | 421s C1 (421s Hays),421s 30 (421s Hays) | 2018-02-27 08:00 | 2018-02-27 14:30 | N | N | urgent trouble corrective | Circuit Breaker, Shunts |  | Urgent Trouble Corrective: Fix densimeter | For Information Only
ALTALINK | 1049L (59s Peigan - 138s Windy Flats) | 2018-02-27 08:00 | 2018-02-27 13:00 | N | Y | RAS scheme modifications | Line |  | RAS scheme 129, 604, 605 modifications as directed by AESO. affecting 1049L protections | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 38s 7152 (38s East Edmonton) | 2018-02-27 08:00 | 2018-02-27 17:30 | N | Y | urgent outage to replace the AC and DC cables | Circuit Breaker |  | Urgent outage to replace the AC and DC cables to 38s7152 due to damage on existing cables | 240 kV, Contingency Requires Mitigation
ALTALINK | 765L (74s Janet - 151s Strathmore),74s 765E (74s Janet) | 2018-02-27 08:30 | 2018-02-27 17:00 | N | N | CT ratio settings changes | Circuit Breaker, Line |  | Bundled work.Techs will be at site to perform CT ratio settings changeson:S952 96/952 SBFU14H(No Redundant protection - OUTR- 4 hrs).Techs willalso perform relay maintenance while on site for the following:- 901L A21/L8 7SA522.Redundant protection will be in placewhile work is being performed, unless otherwise stated. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (289s Saunders Lake - 86s Bigstone),289s 1652 (289s Saunders Lake),289s 1752 (289s Saunders Lake) | 2018-02-27 12:00 | 2018-02-27 17:30 | N | Y | install grounding stirrups on 914L stub bus | Line, Circuit Breaker |  | [SWEATD] Install Grounding stirrups on 914L stub bus | 240 kV, Pre-Condition
ALTALINK | 945S Sunshine Village | 2018-02-27 12:30 | 2018-02-27 17:30 | N | N | re-connect tap to 551L mainline after section 4 rebuild | Station
ALTALINK | 955L (59s Peigan - 103s Goose Lake) | 2018-02-27 13:00 | 2018-02-27 18:00 | N | Y | RAS scheme modifications | Line |  | RAS scheme 129, 604, 605 modifications as directed by AESO. affecting 955L protections | 240 kV, Contingency Requires Mitigation
BCH, ALTALINK | 887L (48s Pocaterra - BCH Britt Creek),1L274 (48s Pocaterra - Britt Creek) | 2018-02-27 13:00 | 2018-02-27 17:00 | Y | Y | end to end testing with AltaLink | Line | Peak RC COS outage ID: 1-00546977 |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds, Impacts RAS
ALTALINK | 956L (103s Goose Lake - 59s Peigan) | 2018-02-28 07:00 | 2018-02-28 13:00 | N | Y | RAS scheme 129, 604, 605 modifications | Line |  | RAS scheme 129, 604, 605 modifications as directed by AESO. affecting 956L protections | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 9L07 (888s Dover - 2011s Dawes) | 2018-02-28 07:00 | 2018-03-02 18:00 | N | Y | install pilings for new structures on 9L07 | Line |  | Install pilings for new structures on 9L07 for new 951S Thickwood Hills substation. | 240 kV, Pre-Condition
ALTALINK | 454L (149s Nisku - 289s Saunders Lake),289s 652 (Saunders Lake),289s 552 (Saunders Lake) | 2018-02-28 07:00 | 2018-02-28 11:30 | N | N | [SWEATD] install grounding stirrups on 454L stub bus | Line, Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 421s C1 (421s Hays),421s T2 (421s Hays) | 2018-02-28 07:15 | 2018-02-28 17:30 | N | N | 138 kV bus protection upgrade | Transformer, Shunts |  | 138 kV bus protection upgrade - cut over CTs, trip tests to related breakers | For Information Only
ALTALINK | 821L (158s Vauxhall - 421s Hays),421s 821W (421s Hays) | 2018-02-28 08:00 | 2018-02-28 18:00 | N | N | 138kV bus protection upgrade, cut over CTs, trip tests to 421s821W | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1053L (132s Ware Junction - 324s Cassils),324s 1152 (324s Cassils),324s28 (324s Cassils) | 2018-02-28 08:00 | 2018-02-28 16:00 | N | N | urgent: adjust switch 28 | Line, Circuit Breaker, Switch |  |  | 240 kV, Pre-Condition
ALTALINK | 932L (74s Janet - 162s Beddington) | 2018-02-28 08:00 | 2018-03-01 16:00 | N | Y | repair SW145 and SW144 at 162 sub | Line
ALTALINK | 233s T1 (233s Beamer) | 2018-02-28 09:00 | 2018-02-28 12:00 | N | N | customer inspection prior to upcoming shutdown | Transformer |  |  | For Information Only
ALTALINK | 455L (149s Nisku - 289s Saunders Lake),289s 1152 (289s Saunders Lake),289s 952 (Saunders Lake) | 2018-02-28 12:00 | 2018-02-28 17:30 | N | N | [SWEATD] install grounding stirrups on 455L stub bus | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 289s T2 (289s Saunders Lake),289s Saunders Lake 138kV Bus 2,858L (289s Saunders Lake - 40s Wetaskiwin) | 2018-03-01 07:00 | 2018-03-01 11:30 | N | Y | [SWEATD] install grounding stirrups on 858L stub bus and 138kv bus 2 | Bus, Line, Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 408L (252s Jarrow - 51s Wainwright) | 2018-03-01 08:00 | 2018-03-02 16:00 | N | N | In-service-date: Mar 01, 2018. Old 704L changed to 51s in and out configuration. | Line
ALTALINK | 51s Wainwright 138kV Bus 2,704L (51s Wainwright - 478s Tuccuman) | 2018-03-01 10:00 | 2018-03-01 17:00 | N | N | closing open points C and D and energizing new 51s252 breaker | Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 289s Saunders Lake),289s 652 (Saunders Lake),289s 852 (Saunders Lake) | 2018-03-01 12:00 | 2018-03-01 17:30 | N | N | [SWEATD] install grounding stirrups on 174L stub bus | Circuit Breaker, Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-03-02 07:00 | 2018-03-19 18:00 | N | N | energize/de-energize bypass line | Line |  | energize/de-energize bypass line, no interruption to load | For Information Only
NWE | NWMT Broadview Switchyard-Judith Gap South 230kV Line | 2018-03-02 09:00 | 2018-03-02 13:00 | N | Y | urgent: repair broken wire | Line | Peak RC Path Outage ID: 1-00553171 (N-S), 1-00553170 (S-N) Peak RC Outage ID: 1-00553049 |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 289s 1552 (289s Saunders Lake) | 2018-03-04 20:00 | 2018-04-09 08:59 | N | Y | CT emergency repair - forced outage | Circuit Breaker |  | Breaker remains OOS until new CT is procured and installed. Finish date is estimate, Will update as return to service date is finalized | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 1139L (367s Harry Smith - 816s Petrolia),367s 1352 (367s Harry Smith),367s 1552 (367s Harry Smith) | 2018-03-05 07:00 | 2018-03-05 12:00 | N | Y | [SWEATD] install 240kV ground stirrups | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | Hardisty T3 (Hardisty),72CH9 (Hardisty - 987s Clover Bar),Hardisty H724 (Hardisty Epcor),Hardisty H723 (Hardisty Epcor) | 2018-03-05 07:30 | 2018-03-06 17:00 | N | N | relay maintenance | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2018-03-05 07:30 | 2018-03-06 12:30 | N | N | insulator washing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 751s 702T (751s Hill) | 2018-03-05 08:00 | 2018-03-09 17:00 | N | N | transfer load from 702T to mobile Sub | Transformer |  | Transfer load from 702T to mobile Sub | For Information Only
ENMAX | 27.1TR (ENMAX 27) | 2018-03-05 08:00 | 2018-03-13 16:00 | N | N | PRD installation | Transformer |  |  | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2018-03-05 08:00 | 2018-03-12 16:00 | N | N | bushing and CT replacement and DIFF relay replacement | Transformer |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2018-03-05 08:00 | 2018-03-06 16:00 | N | N | shutters do not lift in time to clear breaker rosette's when racking | Transformer |  |  | For Information Only
ATCO | 7L701 (223s Strome - 7L701D1) | 2018-03-05 09:30 | 2018-03-09 17:00 | N | Y | 7L701 arm change | Line |  | 7L701 Arm Change | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 729s 702T (729s Otauwau),6L73 (729s Otauwau - 745s Slave Lake) | 2018-03-05 10:00 | 2018-03-06 17:00 | N | N | wire in lockout relay upgrade & 702T & breaker 601 | Transformer, Line |  | Wire in Lockout relay Upgrade, 702T @ 729S Otauwau 745S Slave lake load will be required to be transferred to 729S Otauwau This outage will be used to insert the Bus trip signal into the trip circuit of breaker 601. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2018-03-05 11:00 | 2018-03-09 12:00 | N | N | 7L40 Xarm/insulator replacement | Line |  | 7L40 Xarm/Insulator Replacement | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, EPCOR | 320p 252 (320p Keephills),320p 352 (320p Keephills),1043L (320p Keephills - 367s Harry Smith),367s 1652 (367s Harry Smith),367s 1852 (367s Harry Smith) | 2018-03-05 13:00 | 2018-03-06 17:30 | N | N | [SWEATD] install ground stirrups on 240KV stub bus @ 367s and recloser logic testing | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 880L (523s Bullshead - 321s Al Rothbauer) | 2018-03-06 | 2018-03-16 23:00 | N | N | ISD: March 14, 2018 | Line
ALTALINK | 446L (305s Acheson - 367s Harry Smith),367s T2 (367S Harry Smith),367s Harry Smith 138 kV Bus 2 | 2018-03-06 07:00 | 2018-03-06 17:30 | N | Y | [SWEATD] install ground stirrups on 138KV bus | Line, Bus, Transformer |  |  | 240 kV
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2018-03-06 07:30 | 2018-03-06 18:00 | N | N | urgent repair on structures 60 and 63 | Line |  | Urgent repair on structures 60 and 63 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 41S Medicine Hat,880L (523s Bullshead - 41s Medicine Hat) | 2018-03-06 08:00 | 2018-03-13 18:00 | N | Y | cut free 880L(523s-41s), energize new 880L(523s-321s) | Station, Line |  | Install 880L bypass, cut free 41s-create open points:AA, BB,CC, DD,R,S,T (salvage release). Close open points: A,B and D on new 880L. Test energize new 880L(523s-321s)and phase @ 321s. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2018-03-06 08:00 | 2018-03-06 16:00 | N | N | install new PT | Line |  | Install new 138kV PT on 705L. Pile for PT was previously installed. | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2018-03-06 08:00 | 2018-03-06 16:00 | N | N | 138kV BD and auto switching upgrade, wiring and functional checks | Line |  | 31s 138kV BD and auto switching upgrade. Wiring and functional checks. | For Information Only
ALTALINK | 33s6 (33s Spray) | 2018-03-06 08:00 | 2018-03-06 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 788L (157s Lac La Biche - 788L Tap) | 2018-03-06 08:30 | 2018-03-08 12:00 | N | Y | component replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Saskpower | SaskPower A1R | 2018-03-06 09:00 | 2018-03-06 11:00 | N | Y | high load move | Line |  |  | Limits ATC
ATCO | 7L162 (732s Mitsue - 729s Otauwau),729s 704 (729s Otauwau) | 2018-03-06 09:00 | 2018-03-06 15:00 | N | N | test and operate 704, lock-out wiring and commission | Line, Circuit Breaker |  | Test and Operate 704, Lock-out wiring and Commission @ 729S All Load being supplied by 7L49 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2018-03-06 12:30 | 2018-03-06 18:30 | N | N | insulator washing | Line |  | Insulator washing | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO | 893L (893BL tap - 893AL tap),893L (312s Fidler - 893AL tap) | 2018-03-07 07:00 | 2018-03-08 19:00 | N | Y | install bird diverter | Line |  | bird diverter install; 893L to be closed at 103s to maintain I_806s prior to switching for 893L/893AL GOI | Pre-Condition, Restricts Generation
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2018-03-07 07:00 | 2018-03-08 18:00 | N | N | insulator washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 452L (434s Stony Plain - 367s Harry Smith),453L (305s Acheson - 367s Harry Smith),367s Harry Smith 138 kV Bus 1,367s T1 (367s Harry Smith) | 2018-03-07 07:00 | 2018-03-07 17:30 | N | N | [SWEATD] install ground stirrups on 138KV bus | Line, Bus, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2018-03-07 08:00 | 2018-03-07 16:00 | N | N | wiring and functional checks | Line |  | 31s 138kV BD and auto switching upgrade. Wiring and functional checks. Inspect 32B138-31.84 for leaks. | For Information Only
ATCO | 840S McNeill Station | 2018-03-07 08:00 | 2018-03-09 17:00 | N | Y | repair of leaks in De-Ionizing system and main piping of valve cooling | Station |  | Require McNeill to Standby for Repair of leaks in De-Ionizing system and main piping of valve cooling.- no ability to transfer during work | Limits ATC
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2018-03-07 10:00 | 2018-03-07 16:00 | N | Y | required to cutover radios | Line |  |  | 240 kV, Pre-Condition
ATCO | 729s 703T (729s Otauwau) | 2018-03-07 10:00 | 2018-03-08 16:00 | N | N | terminate and commission lockout from 703T protection | Transformer |  | Terminate and Commission Lockout from 703T protection, Sub Carried by 701T RE: Permit 2-44687 702T will be returned to normal prior to taking 703T OOS | For Information Only
ATCO | 7L42 (751s Hill - 716s Lloydminster),751s 702 (751s Hill) | 2018-03-08 08:00 | 2018-03-11 14:00 | N | N | change 702CT ratio and test 7L42 21A & 21B protections with the new CT ratio | Circuit Breaker, Line |  | To change 702CT ratio and test 7L42 21A & 21B protections with the new CT ratio. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L24 (846s Grand Centre - 7L24D3) | 2018-03-08 08:00 | 2018-03-08 17:00 | N | N | change pole damaged from woodpecker | Line |  | We will need an Emergency GOI on 7L24 to change a pole damaged from woodpeckers 7L24-# 327 wood pecker holes | Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2018-03-08 08:00 | 2018-03-08 16:00 | N | N | 31s 138kV BD and auto switching upgrade, wiring and functional checks | Line |  | Wind generation = 220 MW - no impact on overload. | Pre-Condition
ALTALINK | 788L (898s Heart Lake - 788L107A - 602L1) | 2018-03-08 12:30 | 2018-03-12 15:30 | N | Y | component replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 932L (74s Janet - 162s Beddington),74s Janet 240kV Bus 1,929L (74S Janet - 287s Hazelwood),287s 352 (287s Hazelwood) | 2018-03-08 13:01 | 2018-03-08 18:00 | N | Y | close open point A | Bus, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 611L (391S Balzac - 186s Dry Creek) | 2018-03-09 07:00 | 2018-03-11 18:00 | N | N | replace structures 50~54, install new structure 53A | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | CROW | 2018-03-09 10:00 | 2018-03-09 11:00 | N | N | migration from SDC to PDC | SCInternal |  |  | For Information Only
EPCOR | 987s GDS2 (987s Cloverbar) | 2018-03-10 06:00 | 2018-03-10 20:00 | N | Y | customer outage | Switch |  | EPCOR G2 @ Cloverbar | Restricts Generation
ENMAX | 6.80L (ENMAX 30 - ENMAX 6) | 2018-03-10 06:00 | 2018-03-10 11:00 | N | N | KGL removing tree near line and knocking down dirt stock piles that are too close to line. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs),557s 2404 (557s Castle Downs),557s 2405 (557s Castle Downs) | 2018-03-12 07:00 | 2018-03-16 17:00 | N | Y | relay maintenance | Line, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 803s 701T (803s Bullpound) | 2018-03-12 07:00 | 2018-03-23 17:00 | N | N | protection upgrade and replace PLC | Transformer |  | Protection upgrade and replace PLC. | For Information Only
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2018-03-12 08:00 | 2018-04-13 16:00 | N | N | line protection upgrade | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
Syncrude | Aurora 52-222 (Aurora) | 2018-03-12 08:00 | 2018-03-12 20:00 | N | N | low gas | Circuit Breaker |  | Circuit Breaker (52-222) outage required due to low level of insulating gas | 240 kV
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2018-03-12 08:00 | 2018-03-15 17:00 | N | N | to changes 174 arm structures | Line |  | To changes 174 arm structures | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2018-03-12 08:00 | 2018-03-30 16:00 | N | N | (SWCRR)-relocated a section of 6.82L | Line |  | (SWCRR)-relocated a section of 6.82L around the new planned intersection at 162AVE SW and the SWCRR. | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1TR (ENMAX 31) | 2018-03-12 08:00 | 2018-03-12 16:00 | N | N | 138kV BD and auto switching upgrade | Transformer |  |  | For Information Only
ENMAX | 14.4TR (ENMAX 14) | 2018-03-12 08:00 | 2018-03-23 16:00 | N | N | feeder panel replacement | Transformer |  |  | For Information Only
ALTALINK | 922L (310p Sundance - 17s Benalto),17s 5 (17s Benalto),17s 6 (17s Benalto),310p 1952 (310p Sundance),310p 2052 (310p Sundance) | 2018-03-12 08:30 | 2018-03-16 15:30 | N | Y | protections upgrade - C60 installation | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 7L38 (875s Algar - 917s Horse River),875s 701 (875s Algar) | 2018-03-12 09:00 | 2018-03-12 12:00 | N | N | add wiring to 701 breaker trip circuit | Line, Circuit Breaker |  | Add wiring to 701 Bkr trip circuit for 875S 701TCS risk mitigation To be coordinated with Permit 2-44978 875S 702 BKR & 7L170 will remain in service while this breaker is out of service. | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2018-03-12 09:15 | 2018-03-15 14:45 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 408L (252s Jarrow - 51s Wainwright) | 2018-03-12 10:45 | 2018-03-13 12:00 | N | N | forced outage - bird crossarm | Line |  |  | Creates Radial Feeds
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2018-03-12 11:00 | 2018-03-19 16:00 | N | N | replace rotten cross arms | Line |  | Replace rotten cross arms | Pre-Condition
ALTALINK | 198s T2 (198s Blackfalds) | 2018-03-12 11:30 | 2018-03-15 17:00 | N | N | investigate bushing leak and replace center phase low side if required | Transformer |  |  | For Information Only
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2018-03-12 12:00 | 2018-03-15 18:00 | N | N | line maintenance to replace crossarms and glass change | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 741s 705C (741s Fox Creek) | 2018-03-12 12:00 | 2018-03-15 16:00 | N | N | re-test the capacitor bank | Shunts |  | Need to re-test C phase of the capacitor bank, due to higher unbalance currents than on the other two phases. | For Information Only
ATCO | 7L170 (875s Algar - 2011s Dawes),875s 702 (875s Algar) | 2018-03-12 12:01 | 2018-03-12 16:30 | N | N | add wiring to 702 breaker trip circuit | Line, Circuit Breaker |  | Add wiring to 702 Bkr trip circuit for 875S 701TCS risk mitigation, To be coordinated with Permit 2-44977 875S 701 BKR & 7L38 will remain in service while this breaker is out of service. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 283s T1 (283s Violet Grove) | 2018-03-12 12:15 | 2018-03-22 15:45 | N | N | doble, gas detector leaking, reclaim oil and maintenance | Transformer |  | 283sT1 Top LTC bolts are loose. ADD: 283s doble Tx18542 LTC TTI/ASEA 138/25KV, 283s T1 gas detector leaking, 283s T1 reclaim oil, 283s maint Tx18542 LTC TTI/ASEA 138/25KV | For Information Only
ALTALINK | 377s T1 (377s Hardisty) | 2018-03-13 07:00 | 2018-03-14 17:30 | N | N | investigate and test 377sT1 | Transformer
ALTALINK | 428s T1 (428s Namaka) | 2018-03-13 08:00 | 2018-03-13 17:00 | N | N | investigate T1 oil leak and maintain 138kV SF6 breaker | Transformer
ENMAX, ALTALINK | 162s 240-RB132 (162s Beddington),162s 240-133 (162s Beddington),918L (281s Johnson - 162s Beddington) | 2018-03-13 08:00 | 2018-03-13 17:00 | N | Y | replace operating mechanism of switch 135 | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 800s 501C (800s Friedenstal),800s 502C (800s Friedenstal) | 2018-03-13 09:30 | 2018-03-13 14:30 | N | N | obtain PCB sample from 501PT, 501C1 & 501C2 | Shunts |  | Obtain PCB Sample from 501PT, 501C1 & 501C2 out of service for the duration of the work | For Information Only
SUNCOR | 635EDD-1000 RTU/SCADA,635EDD-1002 RTU/SCADA,635EDD-1001 RTU/SCADA,635EDD-1003 RTU/SCADA | 2018-03-13 10:00 | 2018-03-13 14:00 | N | N | SCADA comms cutover to new Telus MPLS network and EMS | Terminal Equipment |  |  | Affects Visibility
ATCO | 9L01 (888s Dover - 848s Ruth Lake),848s 9L01D1 (848s Ruth Lake),888s 9L01D2 (888s Dover) | 2018-03-14 07:00 | 2018-03-25 17:30 | N | Y | install new structures for Thickwood tap | Line, Switch |  | 9L01 Cut in for in and out addition of 951S Thickwood Hills substation. Install new structures. | 240 kV
ALTALINK | 121s T5 (121s Brooks) | 2018-03-14 07:30 | 2018-03-14 18:30 | N | Y | reinforcing structure supporting T5 station service transformer | Transformer |  |  | Restricts Generation
ENMAX | 31.2TR (ENMAX 31) | 2018-03-14 08:00 | 2018-03-15 16:00 | N | N | 31s 138kV BD and auto switching upgrade, wiring and functional checks | Transformer |  | 31s 138kV BD and auto switching upgrade. Wiring and functional checks. | For Information Only
ALTALINK | 250p11 (250p Bighorn) | 2018-03-14 11:00 | 2018-03-14 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 924L (102s Langdon - 356s Milo),927L (102s Langdon - 356s Milo) | 2018-03-15 07:00 | 2018-03-18 18:00 | N | Y | re-conductor both OHSW's and install ariel markers on Str 53-54 | Line |  | Re-Conductor Both OHSW's & Install Ariel Markers on 924L (Str 53-54) and 927L (Str 53-54). | 240 kV, Pre-Condition
ENMAX | 34.1TR (ENMAX 34) | 2018-03-15 08:00 | 2018-03-16 16:00 | N | N | In-service-date: Mar 15, 2018. | Transformer
ENMAX | 1.5TR (ENMAX 1) | 2018-03-15 08:00 | 2018-03-15 16:00 | N | N | soak test after a forced outage | Transformer |  |  | For Information Only
ALTALINK | 610L (336s Fincastle - 83s Taber),83s 610 (83s Taber),336s 610 (336s Fincastle) | 2018-03-15 09:00 | 2018-03-15 16:00 | N | Y | investigate spring charge issue and limit switch issue. | Circuit Breaker, Line |  | Investigate spring charge issue and limit switch issue. | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn) | 2018-03-15 09:00 | 2018-03-15 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
Saskpower | SaskPower A1R | 2018-03-15 10:00 | 2018-03-15 12:00 | N | Y | high load move | Line |  |  | Limits ATC
ENMAX | 138_31_CAP (ENMAX 31) | 2018-03-16 08:00 | 2018-03-16 16:00 | N | N | upgrade 138 kV BD and auto switching | Circuit Breaker |  | 31s 138kV BD and auto switching upgrade. Wiring and functional checks. | For Information Only
EPCOR | 805s J2404 (805s Jasper) | 2018-03-16 13:30 | 2018-03-16 17:00 | N | Y | nait switching | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2018-03-18 08:00 | 2018-03-18 18:00 | N | N | repair hot spot on SW82 @ 20sub | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1S1852 (29EDD-1) | 2018-03-18 09:00 | 2018-03-22 11:00 | N | N | leak repair and SF6 top up | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 184s T3 (184s Petro-Canada Edmonton),606L (184s Petro-Canada Edmonton - 185s Bretville),184s Petro-Canada Edmonton 138 kV Bus 1 | 2018-03-19 07:00 | 2018-04-03 17:30 | N | N | move metering, P&C & telecom to new control building | Line, Bus, Transformer |  | Move metering, P&C & telecom to new control building, bird coverup, replace bus, line & Tx protections, replace breaker controls, replace & add supervisory control to 184s21 | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2018-03-19 07:00 | 2018-03-22 12:30 | N | N | cable salvage and de-commissioning | Line |  | Cable salvage and de-commissioning | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L65 (709s Vegreville - 710s Vermilion),710s 703 (710s Vermilion) | 2018-03-19 07:00 | 2018-03-29 17:00 | N | N | protection upgrade | Line, Circuit Breaker |  | Protection upgrade | Pre-Condition, Over/Under Voltage
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs),557s 2403 (557s Castle Downs),557s 2401 (557s Castle Downs) | 2018-03-19 07:00 | 2018-03-22 15:00 | N | Y | relay maintenance | Line, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s3 MH69_311 (MH69s3 South Ridge),MH69s3 MH69-T31 (MH69s6 Riverview) | 2018-03-19 07:00 | 2018-03-23 16:00 | N | N | transformer oil reclamation | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2018-03-19 07:30 | 2018-03-23 17:00 | N | N | relay maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark T1 (Meadowlark) | 2018-03-19 07:30 | 2018-03-23 17:00 | N | N | relay maintenance | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2018-03-19 08:00 | 2018-03-22 13:00 | N | Y | T30 inspection, cooling system maintenance, corrective P &C work and testing | Transformer, Shunts |  | T30 inspection, cooling system maintenance, corrective P &C work and testing. No impact to Link Dispatch for MW transfer | 240 kV
ATCO | 729s 701T (729s Otauwau),7L49 (732s Mitsue - 729s Otauwau) | 2018-03-19 08:00 | 2018-03-20 15:00 | N | N | terminate and commission lockout from 702T protection and breaker 705 | Transformer, Line |  | Terminate and Commission Lockout from 702T protection and breaker 705 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.3TR (ENMAX 39) | 2018-03-19 08:00 | 2018-03-30 16:00 | N | N | bushing/CT replacement and differential relay replacement | Transformer |  | TR bushing/CT replacement and TR DIFF relay replacement. (Outage required on 39.82L for crane) | For Information Only
ENMAX | 38.1TR (ENMAX 38) | 2018-03-19 08:00 | 2018-03-19 12:00 | N | N | inspect secondary power cable terminations and cabinet | Transformer |  |  | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2018-03-19 08:00 | 2018-03-20 16:00 | N | N | 31s 138kV BD and auto switching upgrade | Transformer |  | 31s 138kV BD and auto switching upgrade, wiring and functional checks | For Information Only
ALTALINK | 17s 11 (17s Benalto) | 2018-03-19 09:00 | 2018-03-19 12:30 | N | Y | protections upgrade and breaker trip tests | Circuit Breaker |  | Protections Upgrade - Breaker trip tests | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 430L (330P Genesee - 510S Sunnybrook) | 2018-03-19 09:00 | 2018-03-19 17:00 | N | Y | Relay Maintenance | Line
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2018-03-19 09:00 | 2018-03-21 15:00 | N | Y | structure repair (Str87~89) | Line | Peak COS outage ID: 1-00556095 |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2018-03-19 09:15 | 2018-03-23 17:45 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 746s T1 (746s Sherwood Park) | 2018-03-19 09:30 | 2018-03-22 18:30 | N | N | transformer maintenance | Transformer |  | Sherwd Pk 746s5 25kV Switch-Field Op. ADD: 746s Tx18347 T1 Leaks, 746s TX18347 X0 Leak, 746sT1 maint TX 18347 LTC FPE/FPE 138/25 | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2018-03-19 12:00 | 2018-03-19 16:00 | N | N | inspect secondary power cable terminations and cabinet | Transformer |  |  | For Information Only
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2018-03-19 12:00 | 2018-03-22 18:00 | N | N | line maintenance to replace crossarms and glass change | Line |  | Line mtce to replace crossarms and glass change | Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 7 (17s Benalto) | 2018-03-19 12:30 | 2018-03-19 18:00 | N | Y | protections upgrade & breaker trip tests | Circuit Breaker |  | Protections Upgrade - Breaker trip tests | 240 kV, Contingency Requires Mitigation
BCH | 5L75 (Revelstoke - Ashton Creek) | 2018-03-19 23:00 | 2018-03-21 23:00 | N | Y | 5L75 OOS for disconnect and ground disconnect PM's at REV | Line | Peak COS outage ID: 1-00550534 Peak Path COS ID: 1-00556098 (E>W), 1-00556099 (W>E) |  | Limits ATC, 500 kV
ALTALINK | 17s 1 (17s Benalto) | 2018-03-20 06:30 | 2018-03-20 12:30 | N | Y | protections upgrade - breaker trip tests | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 515s T1 (515s FedpipeJudy Creek) | 2018-03-20 07:00 | 2018-03-20 20:00 | N | N | DGA test & doble & tap changer handle leaking | Transformer
ALTALINK | 167s T2 (167s Ipiatik Lake) | 2018-03-20 07:30 | 2018-03-22 16:30 | N | Y | x3 turret leaking - emergency repair | Terminal Equipment |  |  | 240 kV, Pre-Condition
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-03-20 12:00 | 2018-04-06 18:00 | N | N | energize/de-energize bypass line between Str163 and Str188 to allow for rebuild of 551L (Sections 8) | Line |  |  | For Information Only
ALTALINK | 17s 5 (17s Benalto) | 2018-03-20 12:30 | 2018-03-20 18:00 | N | Y | Protections Upgrade - Breaker trip tests | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 10 (17s Benalto) | 2018-03-21 06:30 | 2018-03-21 12:30 | N | Y | protections upgrade & breaker trip tests | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2018-03-21 07:00 | 2018-03-21 17:00 | N | N | mine shut down, line maintenance | Line |  |  | For Information Only
ALTALINK | 87s 852 (87s Gaetz) | 2018-03-21 08:00 | 2018-03-21 15:00 | N | N | maintain 138 kV SF6 gas breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 118s T2 (118s Canmore) | 2018-03-21 08:00 | 2018-03-21 17:30 | N | N | techs to replace Weschler transformer monitor units while at site | Transformer |  |  | For Information Only
ALTALINK | 377s C1 (377s Hardisty),377s 34 (377s Hardisty) | 2018-03-21 08:00 | 2018-03-21 15:00 | N | N | maintain 138kV cap bank breaker | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2018-03-21 08:00 | 2018-03-21 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz),86s 1752 (86s Bigstone) | 2018-03-21 08:30 | 2018-03-21 18:30 | N | Y | tech to perform standard relay maintenance and recloser maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2018-03-21 12:00 | 2018-03-21 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 2852 (17s Benalto),17s T3 (17s Benalto) | 2018-03-21 12:30 | 2018-03-21 18:00 | N | Y | Protections Upgrade - Breaker trip tests | Circuit Breaker, Transformer |  |  | 240 kV
ALTALINK | 320p2089 (320p Keephills) | 2018-03-21 21:00 | 2018-03-28 18:00 | N | Y | customer requested outage | Switch |  |  | Restricts Generation, 500 kV
AESO-SC | Northwestern Energy BUCC test | 2018-03-22 08:00 | 2018-03-22 12:00 | N | N | BUCC test | Station |  |  | Affects Visibility
ALTALINK | 17s 5 (17s Benalto) | 2018-03-22 08:00 | 2018-03-22 12:00 | N | Y | repair sync check | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 87s 252 (87s Gaetz) | 2018-03-22 08:00 | 2018-03-22 15:00 | N | N | maintain 138 kV SF6 gas breaker | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 15.1TR (ENMAX 15) | 2018-03-22 08:00 | 2018-03-22 16:00 | N | N | transformer measurements for CT replacement program | Transformer |  |  | For Information Only
ALTALINK | 1112L (289s Saunders Lake - 89s Ellerslie) | 2018-03-22 09:00 | 2018-03-22 16:00 | N | Y | de-energized for stability issues with radio emergency outage | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 1140L (289s Saunders Lake - 89s Ellerslie) | 2018-03-22 09:00 | 2018-03-22 16:00 | N | Y | de-energized for stability issues with radio emergency outage | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 17s 6 (17s Benalto) | 2018-03-22 12:00 | 2018-03-22 18:00 | N | Y | repair sync check | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2018-03-23 10:00 | 2018-03-23 12:00 | N | N | spring transmission pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2018-03-23 12:00 | 2018-03-23 14:00 | N | N | spring transmission pothead washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2018-03-24 08:00 | 2018-03-25 16:00 | N | N | switch maintenance, SF6 gads sample, replace cracked operating arm and substation washing (weather dependent) | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 780s 707C (780s Lubicon),780s 707 (780s Lubicon) | 2018-03-24 10:00 | 2018-07-06 16:00 | N | N | failed relay repair | Circuit Breaker, Shunts |  | Forced outage - 707c Relay fail affecting the overcurrent/overvoltage protection on the CAP bank. The bank will be out of service until this can be fixed. The replacement relay has been ordered however no date as to the arrival, in addition good weather is required to fly into the site. | For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2018-03-25 08:00 | 2018-03-25 12:00 | N | N | spring transmission line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 69s T4 (69s North Barrhead),69s 713 (69s North Barrhead) | 2018-03-25 08:00 | 2018-03-28 14:30 | N | Y | replace 69s713 breaker fail protection | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.3TR (ENMAX 22) | 2018-03-25 08:00 | 2018-03-31 14:00 | N | N | install NGR | Transformer
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2018-03-25 12:00 | 2018-03-25 16:00 | N | N | spring transmission line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | Aurora 12 (Aurora),Aurora 13 (Aurora),Aurora UT1 (Aurora) | 2018-03-26 08:00 | 2018-03-29 18:00 | N | N | replace disconnect switch 12A and 13A | Transformer, Circuit Breaker |  |  | For Information Only
Syncrude | AL-1 (D05 Syncrude - Aurora) | 2018-03-26 08:00 | 2018-04-01 18:00 | N | Y | line maintenance | Line |  |  | 240 kV, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-03-26 08:00 | 2018-03-26 12:00 | N | N | spring transmission pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | EMS | 2018-03-26 08:00 | 2018-03-29 17:00 | N | N | Q1 release | SCInternal |  |  | For Information Only
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2018-03-26 08:00 | 2018-03-30 17:00 | N | Y | reactor inspection and leak repair | Shunts |  |  | For Information Only, 500 kV
SUNCOR | 29EDD1S452 (29EDD-1 Millennium) | 2018-03-26 09:00 | 2018-03-30 18:00 | N | Y | SF6 top up | Circuit Breaker |  |  | 240 kV
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2018-03-26 09:15 | 2018-03-28 17:45 | N | Y | component replacement | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 746s T2 (746s Sherwood Park) | 2018-03-26 09:30 | 2018-03-28 18:30 | N | N | transformer maintenance & 25kV work | Transformer |  | 746s Sherwd Pk 746s35 25kV Swtch-FieldOp. ADD: 746sT2 maint TX 18305 LTC WES/ASEA 138/2, 746sT2 doble TX 18305 LTC WES/ASEA 138/2, 746s222X (CB631) BO 25kV FKP | For Information Only
ALTALINK | 522s T1 (522s Cooking Lake) | 2018-03-26 09:30 | 2018-03-29 08:30 | N | N | Cantega bird cover install | Transformer |  | 522s T1, VR1 & 25kV Bus 1 for Cantega bird cover install | For Information Only
AESO-SC | DT | 2018-03-26 10:00 | 2018-03-26 11:30 | N | N | DT Q1 path release | SCInternal |  |  | For Information Only
ALTALINK | 765L (74s Janet - 151s Strathmore) | 2018-03-26 10:00 | 2018-03-29 18:00 | N | N | structure move/addition to accommodate intersection widening on TWP240 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 851s 701T (851s Morse River) | 2018-03-26 10:00 | 2018-03-27 16:00 | N | N | test and recommmision CT circuit | Transformer |  | Test and ReCommmision CT Circuit for 701T Protection@ 851S Investigate of CT Circuit failure alarm The 25KV CT circuit that supplies both the 87A and 87B/50-51 protection needs to be re-commissioned. The 87A and 87B relays have given us a CT Input fail alarm, indicating an intermittent open on the CT circuit. We need to take the Transformer off line in order to test the primary and Secondary of the bus CT and all wiring to find the source of the alarm, in order to prevent a Station Lockout. | For Information Only
ALTALINK | 151s 765W (151s Strathmore) | 2018-03-26 11:00 | 2018-03-26 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2018-03-26 12:00 | 2018-03-26 18:00 | N | Y | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2018-03-26 12:00 | 2018-03-28 18:00 | N | N | line maintenance to replace crossarms and glass change | Line |  | Line mtce to replace crossarms and glass change | Firm Load Loss, Creates Radial Feeds
ALTALINK | 291s T2 (291s Cochrane) | 2018-03-26 12:00 | 2018-03-27 16:00 | N | N | maintain T2 Tx18792 and doble | Transformer |  |  | For Information Only
ALTALINK | 100L (895s Suffield - 498s Tilley),895s 100 (895s Suffield) | 2018-03-26 12:00 | 2018-03-26 17:30 | N | N | replace burned heater. | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2018-03-26 12:00 | 2018-03-26 17:00 | N | N | spring transmission pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | DT | 2018-03-26 15:00 | 2018-03-26 16:00 | N | N | post Q1 release | SCInternal |  |  | For Information Only
ALTALINK | 157s T1 (157s Lac La Biche) | 2018-03-27 07:00 | 2018-03-27 18:00 | N | N | work on 157s289 | Transformer |  |  | For Information Only
ALTALINK | 51s T3 (51s Wainwright),408L (252s Jarrow - 51s Wainwright),51s Wainwright 138kV Bus 1 | 2018-03-27 07:30 | 2018-03-27 15:00 | N | N | replace nameplate on VT4 & replace fiber cable on T3 | Bus, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 254s T2 (254s Coaldale) | 2018-03-27 08:00 | 2018-03-27 17:30 | N | N | replace Weschler tansformer monitor units | Transformer |  | Techs to replace Weschler Transformer monitor units while at site. | For Information Only
ATCO | 6L96 (735s Swan River - 6L96 Tap) | 2018-03-27 08:00 | 2018-03-28 12:00 | N | N | 6L96 fuel tank move, changing/moving poles | Line |  | 6L96 fuel tank move Changing/Moving poles | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2018-03-27 08:00 | 2018-03-27 16:00 | N | N | spring transmission line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge) | 2018-03-27 09:00 | 2018-03-27 10:00 | N | N | de-energized as part of the MPLS nodes upgrade at 370s North Lethbridge | Line |  | 770L needs to be de-energized as part of the MPLS nodes upgrade @ 370s. Linked to order # 258863 | For Information Only
ALTALINK | 931L (132s Ware Junction - 28s West Brooks) | 2018-03-27 09:00 | 2018-03-27 18:00 | N | Y | salvaging old underpower RAS scheme and associated equipment at 132s Ware Junction | Line |  | Salvaging old Underpower RAS Scheme and associated equipment @ 132s; This RAS is no longer in use and is being removed permanently. Crews will not be hanging grounds and just require the equipment de- energized | 240 kV
ALTALINK | 891L (226s Garden City - 891L1) | 2018-03-27 09:00 | 2018-03-27 18:00 | N | Y | emergency repair; splice repair/damper repair | Line |  | Emergency repair; Splice repair/Damper repair (Str 56, 17, 59) | Restricts Generation
ALTALINK | 159s T1 (159s Colinton) | 2018-03-27 10:00 | 2018-03-28 17:45 | N | N | fix a leak on 159sVR1 | Transformer |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2018-03-27 23:00 | 2018-03-28 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2018-03-28 03:01 | 2018-03-28 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 157s T2 (157s Lac La Biche) | 2018-03-28 07:00 | 2018-03-28 18:00 | N | N | work on 157s489 | Transformer |  |  | For Information Only
ATCO | 939s 904 (939s Livock) | 2018-03-28 12:30 | 2018-03-29 15:00 | N | Y | repair breaker 904 @ 939S Livock | Circuit Breaker |  | Repair Breaker 904 @ 939S Livock Repair and Top up Breaker 904. this Breaker has a long history of a slow leak. The Breaker is currently low and will need a top up for safe operation. We will be attempting a permanent repair during this outage which is why it cannot be done in one day. 240 KV Bus Open for duration of repair | 240 kV, Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 913L (69s North Barrhead - 732s Mitsue),69s 913N (69s North Barrhead) | 2018-03-28 15:30 | 2018-03-28 17:30 | N | Y | trip test from new 69s713 breaker fail protection | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36B138-36BT3 (ENMAX 36),36.81L (44s Bearspaw - ENMAX 36) | 2018-03-31 08:00 | 2018-04-01 18:00 | N | Y | switch maintenance and spring substation washing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33) | 2018-03-31 08:00 | 2018-04-07 12:00 | N | N | install NGR | Transformer |  |  | For Information Only
TRANSALTA | SD3 Sundance #3 | 2018-03-31 15:00 | 2020-07-31 23:00 | N | N | Mothball outage | Unit
ALTALINK, ATCO | 69s T5 (69s North Barrhead),723L (69s North Barrhead - 723L133),7L230 (69s North Barrhead - 7L230 tap),69s 723E (69s North Barrhead),69s 230W (69s North Barrhead) | 2018-04-02 08:00 | 2018-04-06 13:00 | N | Y | replace 69s13 & 69s15, and 69s723W breaker fail protection | Line, Circuit Breaker, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D131 (ENMAX 25),ENMAX 25 B240-D132 (ENMAX 25),ENMAX 25 1GSU-XF-001 (ENMAX 25) | 2018-04-02 09:00 | 2018-04-11 09:00 | N | Y | switch maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Restricts Generation
ENMAX | ENMAX 25 B240-D141 (ENMAX 25),ENMAX 25 B240-D140 (ENMAX 25),ENMAX 25 MD240-3GSU (ENMAX 25) | 2018-04-02 10:00 | 2018-04-16 10:00 | N | Y | testing | Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2018-04-03 07:00 | 2018-04-03 18:00 | N | Y | installing bird diverters | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2018-04-03 07:00 | 2018-04-20 17:00 | N | Y | manhole resurfacing | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 7L117 (706s Irish Creek - 710s Vermilion),710s 701 (710s Vermilion) | 2018-04-03 07:00 | 2018-04-16 08:00 | N | N | protection upgrade | Line, Circuit Breaker |  | Protection upgrade | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 2018s Muir | 2018-04-03 08:00 | 2018-04-04 16:00 | N | N | Tap in 7L90 (941s - 813s). In-service-date: Apr 3, 2018 | Station
ALTALINK | 95s T2 (95s Imperial Oil Edmonton) | 2018-04-03 08:00 | 2018-04-24 16:00 | N | N | customer switchgear change | Transformer
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge) | 2018-04-03 09:00 | 2018-04-07 18:00 | N | N | emergency repairs; damper repair | Line |  |  | For Information Only
ALTALINK | 820AL (315s Chin Chute - 820L tap),820L (254s Coaldale - 820L tap),820L (67s Stirling - 820AL tap) | 2018-04-03 09:00 | 2018-04-07 18:00 | N | Y | emergency repairs; damper repair | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO, CNRL | 859s 701T (859s Primrose),859s 701 (859s Primrose),859s 704 (859s Primrose),859s701TD1 (859s Primrose),859s 52G (859s Primrose) | 2018-04-03 12:00 | 2018-04-09 07:00 | N | Y | maintenance | Circuit Breaker, Transformer, Switch |  |  | Restricts Generation
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2018-04-03 17:31 | 2018-04-04 16:00 | N | N | protection wiring to breakers | Transformer |  |  | For Information Only
ALTALINK | 730L (285s East Camrose - 730L62) | 2018-04-04 07:00 | 2018-04-04 18:00 | N | Y | install bird diverters | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.1TR (ENMAX 15) | 2018-04-04 08:00 | 2018-04-12 16:00 | N | N | install PRD | Transformer |  |  | For Information Only
ATCO | EX1-01 (879s Scotford Upgrader - 402s Scotford Expansion) | 2018-04-04 08:00 | 2018-04-04 16:00 | N | N | change contaminated insulators | Line |  | To change contaminated insulators, on EX1-01L | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s 552 (77s Sagitawah) | 2018-04-04 08:00 | 2018-04-04 18:00 | N | N | install CT secondary ground on breaker 77s552 | Circuit Breaker |  | Techs will be at site to install a CT secondary ground on Breaker 77s552. | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 936L (102s Langdon - 5s East Calgary),937L (102s Langdon - 5s East Calgary) | 2018-04-04 08:00 | 2018-04-11 16:00 | N | Y | green Line LRT project | Line |  |  | 240 kV
Saskpower | Sask Power SW903T | 2018-04-04 09:00 | 2018-04-12 17:00 | N | N | attach new 230 kV bus to 911C isolator, primary injections and breaker interlocks | Circuit Breaker |  |  | Limits ATC
ALTALINK | 184s T1 (184s Petro-Canada Edmonton),184s T2 (184s Petro-Canada Edmonton),705L (184s Petro-Canada Edmonton - 216s Knightsbridge),184s Petro-Canada Edmonton 138 kV Bus 2 | 2018-04-04 16:00 | 2018-04-24 06:00 | N | N | move metering, telecom to new control building and bus and line maintenance | Bus, Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PL6-4 (836s Steepbank - 29EDD-1),30EDD-1-623 (30EDD-1),30EDD-1-621 (30EDD-1),30EDD-1-622 (30EDD-1) | 2018-04-05 08:00 | 2018-04-15 01:00 | N | Y | line maintenance and protection | Line, Circuit Breaker |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 25B240-D132 (ENMAX 25),ENMAX 25 B240-D131 (ENMAX 25),ENMAX 25 1GSU-XF-001 (ENMAX 25) | 2018-04-05 09:00 | 2018-04-06 18:00 | N | Y | switch repair and testing | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Restricts Generation
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2018-04-06 07:00 | 2018-04-06 18:00 | N | N | urgent repair to damaged structures | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | D05 T1 (D05 Syncrude) | 2018-04-06 08:00 | 2018-04-17 18:00 | N | Y | 5 yr PM | Transformer |  | will be isolated from Primary and Secondary for 5 Yr PM. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 723L (69s North Barrhead - 723L133),69s 723E (69s North Barrhead) | 2018-04-06 13:00 | 2018-04-09 10:00 | N | Y | replace 69s13 & 69s15, and 69s723W breaker fail protection | Line, Circuit Breaker |  | There is some testing to be completed from 69s T2 protections to 69s723E breaker fail protection (new). As 69s T2 does not have redundant protections, an outage to this equipment is required. As that outage could not be scheduled until April 9 @ 08:00  10:00, we cannot restore the breaker 69s723E until that test has been completed. | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.1TR (ENMAX 33) | 2018-04-07 12:00 | 2018-04-14 16:00 | N | N | install NGR | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 38s T1 (38s East Edmonton),38s 7152 (38s East Edmonton),38s 7652 (38s East Edmonton),38s East Edmonton 240 kV Bus 1 | 2018-04-08 07:00 | 2018-04-19 14:00 | N | Y | replacement of T1, 38s50 | Bus, Transformer, Circuit Breaker |  | Replacement of T1, Replacement of 38s50 switch including new structure and foundations | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 1352 (320p Keephills) | 2018-04-09 06:30 | 2018-04-29 18:00 | N | Y | [KATR]-installing new line protection for 3-terminal scheme and functional testing; repairing 320p212 | Circuit Breaker |  |  | 240 kV
EPCOR | Namao T1 (Namao) | 2018-04-09 06:30 | 2018-04-09 17:00 | N | N | relay maintenance | Transformer
ENMAX | 47B138-BT3 (ENMAX 47) | 2018-04-09 07:00 | 2018-04-13 16:00 | N | N | repair breaker heater circuit | Circuit Breaker
ALTALINK | 69s T2 (69s North Barrhead) | 2018-04-09 08:00 | 2018-04-09 10:00 | N | N | breaker fail initiate to 69s723W | Transformer |  |  | For Information Only
ENMAX | 41.1TR (ENMAX 41) | 2018-04-09 08:00 | 2018-04-10 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer
ALTALINK | 54L (118s Canmore - 54L172) | 2018-04-09 08:15 | 2018-04-12 15:45 | N | N | replace two structures for clearance mitigation | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 289s 1552 (289s Saunders Lake) | 2018-04-09 09:00 | 2018-04-12 17:30 | N | N | replace failed CT with temporary one | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 233s T1 (233s Beamer),807L (233s Beamer - 807L tap),233s Beamer 138 kV Bus 1 | 2018-04-09 09:30 | 2018-04-19 18:30 | N | N | switch maintenance, TX maintenance, customer switchgear change | Transformer, Bus, Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK | 417L (55s Olds - 281s Johnson),55s 417 (55S Olds) | 2018-04-09 11:00 | 2018-04-13 17:30 | N | Y | breaker replacement | Circuit Breaker, Line |  | Breaker replacement. Redundant protections will be removed from service one at a time to facilitate CT connections. | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 254s T1 (254s Coaldale) | 2018-04-09 12:00 | 2018-04-12 16:00 | N | N | LA replacement and bird cover up | Transformer
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2018-04-10 08:00 | 2018-04-10 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2018-04-10 12:00 | 2018-04-10 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s T3 (83s Taber) | 2018-04-11 07:00 | 2018-04-23 12:00 | N | N | under ground cable replacements | Transformer |  | U/G cable replacements on 194LS & 263LE | For Information Only
ATCO | 786s 508C (786s High Level) | 2018-04-11 08:00 | 2018-04-11 16:00 | N | N | blown fuse found on capacitor | Shunts |  |  | For Information Only
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28),42s 28 (42s Sarcee) | 2018-04-11 08:00 | 2018-04-11 12:00 | N | Y | spring substation washing | Line, Transformer, Circuit Breaker |  | Spring Substation Washing. (Original outage Mar 22nd) | Firm Load Loss, Creates Radial Feeds
ENMAX | 41.2TR (ENMAX 41) | 2018-04-11 08:00 | 2018-04-12 16:00 | N | N | tapchanger inspection and check reversing switch | Transformer |  |  | For Information Only
ENMAX | ENMAX 25 B240-D134 (ENMAX 25),ENMAX 25 MD240-2GSU (ENMAX 25),ENMAX 25 B240-D135 (ENMAX 25) | 2018-04-11 11:00 | 2018-04-16 09:00 | N | Y | testing | Switch, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 1046L (310p Sundance - 338s Cherhill),902L (19s Wabamun - 310p Sundance) | 2018-04-11 11:15 | 2018-05-03 17:00 | N | Y | forced outage - leaning tower | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-04-11 12:00 | 2018-04-11 18:00 | N | N | spring substation washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 706s Irish Creek RTU/SCADA | 2018-04-12 10:00 | 2018-04-12 12:00 | N | N | download new build | Terminal Equipment |  |  | Affects Visibility
Syncrude | AL-2 (D05 Syncrude - Aurora) | 2018-04-13 08:00 | 2018-04-20 18:00 | N | Y | line maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap) | 2018-04-14 07:00 | 2018-04-15 17:00 | N | N | line maintenance & upgrades | Line
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2018-04-15 07:00 | 2018-04-22 15:00 | N | N | RET / Suncor work on 13.8kV bus 2 | Transformer |  |  | For Information Only
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),26.81L (ENMAX 32 - ENMAX 26) | 2018-04-15 09:00 | 2018-04-15 18:00 | N | N | spring substation washing, wash structure #1 & check reversing switch 32.1TR, 32.2TR | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2018-04-15 12:00 | 2018-04-15 18:00 | N | N | spring substation washing urgent | Line, Transformer |  |  | Pre-Condition
ATCO | 706s 705C (706s Irish Creek) | 2018-04-16 | 2018-04-22 16:00 | N | N | In-service-date; April 20, 2018, 25 MVAr cap | Shunts
EPCOR | 557s T2 (557s Castle Downs) | 2018-04-16 07:00 | 2018-04-20 17:00 | N | Y | Calisto install | Transformer |  |  | 240 kV
EPCOR | Rossdale T1 (Rossdale) | 2018-04-16 07:00 | 2018-04-17 17:00 | N | N | cutting over and commissioning new protection | Transformer |  |  | For Information Only
EPCOR | Garneau T1 (Garneau) | 2018-04-16 07:00 | 2018-04-20 17:00 | N | N | doble | Transformer |  |  | For Information Only
ALTALINK | 367s T1 (367s Harry Smith) | 2018-04-16 07:30 | 2018-04-18 17:30 | N | Y | tap changer gas piping modification | Transformer |  | [SWEATD] Tap changer gas piping modification | 240 kV
ENMAX | 5.9TR (ENMAX 5) | 2018-04-16 08:00 | 2018-04-30 16:00 | N | N | 5.8TR cable replacement | Transformer |  | Taken out of service for work associated with 5.8TR Cable Replacement. | For Information Only
Saskpower | Sask Power SW901T | 2018-04-16 08:00 | 2018-04-20 18:00 | N | N | attach new 230 kV bus to 901C isolator, primary injections and breaker interlocks | Circuit Breaker |  |  | Limits ATC
Syncrude | Aurora 22 (Aurora),Aurora 23 (Aurora),TL-2 (Aurora - Aurora) | 2018-04-16 08:00 | 2018-04-22 18:00 | N | N | replacements for 22B & 23A | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 5.8TR (ENMAX 5) | 2018-04-16 08:00 | 2018-05-25 08:00 | N | N | MV cable replacement | Transformer |  | MV Cable replacement. Network required to switch the alternate to 8 sub. | For Information Only
ATCO | 7L49 (732s Mitsue - 729s Otauwau),732s 702 (732s Mitsue),732s 703 (732s Mitsue),7L49D1 (732s Mitsue) | 2018-04-16 08:00 | 2018-04-24 17:00 | N | N | breaker, CT and PT replacement | Line, Circuit Breaker, Switch |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT April 16-24 GOI 2-43738A Outage on 702 & 703 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 701B, 500D1, 707B, 7L49D1, 7L23D4 May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 500D1, 7L31D1 706A, 707B, 7L49D1, 7L23D4 Outage expanded to include 7L31 due to limits of approach issues with replacing 702PT. This outage is planned to be reduced at the end of day to allow for restoration of 7L31 May 5 -Jun 7 GOI 2-43738D Reduce Isolation zone to include Breaker 702 & 703 Isolation points: 702A, 703A, 7L49D1 If May 5th scope is not able to be completed as planned, this reduction of outage will be delayed to May 6. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2018-04-16 08:00 | 2018-04-17 16:00 | N | N | HV breaker maintenance | Line |  | HV breaker maintenance 11B138-11.81, 13B138-11.81. SF6 gas sample 11B138-11.81, 13B138-11.81. | For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2018-04-16 08:00 | 2018-04-20 16:00 | N | N | PRD installation | Transformer |  |  | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2018-04-16 08:00 | 2018-05-16 16:00 | N | N | panel replacement on 25kV feeder | Transformer |  |  | For Information Only
ALTALINK | 523s T1 (523s Bullshead) | 2018-04-16 09:30 | 2018-04-17 16:00 | N | N | install bird cover up | Transformer |  | Install bird cover up on VR 1 (TX18411) and undergrounds on 25kv bus 1 | For Information Only
ATCO | 7L130 (710s Vermilion - 705s Kitscoty),710s 702 (710s Vermilion) | 2018-04-17 07:00 | 2018-04-30 17:00 | N | N | protection upgrade | Line, Circuit Breaker |  | Protection upgrade | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Lethbridge | 172L (370s North Lethbridge - 181s Chinook) | 2018-04-17 08:00 | 2018-04-18 16:00 | N | Y | add fs6 gas and function test | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 847s 902T (847s Muskeg River) | 2018-04-18 06:30 | 2018-05-02 16:00 | N | Y | isolation for customer | Transformer |  | Isolation for Customer Shutdown | 240 kV, Restricts Generation
ALTALINK | 137s T1 (137s Sedgewick) | 2018-04-18 07:30 | 2018-04-18 16:30 | N | N | transformer maintenance and change DC to 25 kV breakers | Transformer |  | Change DC to 25 kV breakers, add new PT, TX maintenance | For Information Only
ALTALINK | 185s T1 (185s Bretville) | 2018-04-18 07:30 | 2018-04-19 18:30 | N | N | 185s T1 H2 bushing leak | Transformer |  |  | For Information Only
ENMAX | 13.82L (ENMAX 22 - ENMAX 13),ENMAX 13 B138-13.82 (ENMAX 13) | 2018-04-18 08:00 | 2018-04-18 16:00 | N | N | 13B138-13.82 breaker maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 47.1TR (ENMAX 47),771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington),47.2 TR (ENMAX 47) | 2018-04-18 08:00 | 2018-04-19 18:00 | N | N | spring substation washing | Line, Circuit Breaker, Transformer |  | Spring Substation Washing. HV SW MD maintenance 162MD138-771L. Dashpot check RB82. Doble 162.81L Las @ 162s | Contingency Requires Mitigation
ALTALINK | 38s 73 (38s East Edmonton) | 2018-04-18 14:00 | 2018-04-19 14:00 | N | N | transformer soak with no load for 24 hours | Circuit Breaker |  | After 38s T1 replacement complete April 18 (ref# 258251), Tx to soak with no load for 24 hrs as per manufacturer | Pre-Condition
ALTALINK | 234L (310p Sundance - 234L1),505L (505L1 - 234L tap),521AL (867s Sundance Blow-Down - 521L tap),521L (521L2 - 505L tap) | 2018-04-19 06:30 | 2018-04-20 16:00 | N | N | urgent request to make repairs to 902L/1046L | Line |  | April 18th, 2018 (06:30  19:00) 234L/505L/521L (310p-867s) will be removed from service to string across 234L(between Structures 73 & 74) & 521L (between Structures 41 - 43). | For Information Only
EPCOR | Rossdale T3 (Rossdale) | 2018-04-19 07:00 | 2018-04-20 17:00 | N | N | cutting over and commissioning new protection | Transformer |  |  | For Information Only
ALTALINK | 324s 2152 (324s Cassils) | 2018-04-19 07:30 | 2018-04-19 14:30 | N | Y | investigate low gas | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, For Information Only
ALTALINK | 367s T2 (367S Harry Smith) | 2018-04-19 07:30 | 2018-04-20 16:00 | N | Y | [SWEATD] tap changer gas piping modification | Transformer |  |  | 240 kV, For Information Only
ENMAX | 6.80L (ENMAX 35 - ENMAX 6) | 2018-04-19 08:00 | 2018-04-19 16:00 | N | N | SF6 gas sample 6B138-6.80 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2018-04-19 08:00 | 2018-04-19 16:00 | N | N | oil sample transformer and check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap) | 2018-04-19 09:00 | 2018-04-19 13:00 | N | N | urgent repair/maintenance of 233s CVT3 (807L PT) | Line |  |  | For Information Only
ALTALINK | 63s T3 (63s Red Deer) | 2018-04-19 09:00 | 2018-04-19 16:00 | N | N | urgent top up SF6 138kV breaker low gas on 63s26 | Transformer |  |  | For Information Only
ALTALINK | 767CL (635s Rose Valley - 767L tap),767L (320p Keephills - 767L167A) | 2018-04-20 07:00 | 2018-04-20 15:00 | N | N | repairing 767L167A | Line
ENMAX | 9.2TR (ENMAX 9),9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9) | 2018-04-20 08:00 | 2018-04-20 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALPAC | 282S Grassland (Alpac) | 2018-04-20 08:00 | 2018-04-20 16:00 | N | N | 487E relay B replacement | Station
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2018-04-21 08:00 | 2018-09-14 06:44 | N | N | forced outage due to underbuild issues | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36),36.1 TR (ENMAX 36) | 2018-04-21 08:00 | 2018-04-22 18:00 | N | N | repair 36MD138-36.1TR, doble 36PT138-Z31-C, spring substation washing | Transformer, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2018-04-21 14:00 | 2018-04-22 16:00 | N | N | replace insulator strain and salvage VSR from 705L @ 184s | Line
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap) | 2018-04-22 07:00 | 2018-04-22 17:00 | N | N | line maintenance & upgrades | Line
ALTALINK | 747L (99s North St. Albert - 747DL4) | 2018-04-22 07:00 | 2018-04-22 17:30 | N | N | replace the strain insulators on 747L inside 37s substation at 37s42 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALPAC | 282S Grassland (Alpac) | 2018-04-22 08:00 | 2018-05-07 16:00 | N | N | 87 relay B replacement | Station
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2018-04-22 08:01 | 2018-04-27 10:00 | N | N | remain oos until Suncor ready | Transformer |  |  | For Information Only
ALTALINK | 184s T3 (184s Petro-Canada Edmonton),705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2018-04-22 08:01 | 2018-04-22 16:00 | N | N | station outage to trip AML & Suncor breakers from new auto-restoration scheme | Line, Transformer
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2018-04-22 16:00 | 2018-04-27 18:00 | N | N | replace T2 25kV bushings | Transformer
EPCOR | Namao T3 (Namao),72CN10 (987s Clover Bar - Namao) | 2018-04-23 06:30 | 2018-04-27 17:00 | N | N | relay maintenance | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2018-04-23 06:30 | 2018-05-03 20:00 | N | N | cutover of new line protection | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 289s T2 (289s Saunders Lake) | 2018-04-23 07:30 | 2018-04-24 14:00 | N | Y | [SWEATD] tap changer gas piping modification | Transformer |  |  | 240 kV
ENMAX | 36.1TR (ENMAX 36) | 2018-04-23 08:00 | 2018-05-13 16:00 | N | N | switchgear upgrade | Transformer |  |  | For Information Only
Saskpower | SaskPower C1S | 2018-04-23 08:00 | 2018-04-28 17:00 | N | N | maintenance | Line |  |  | Limits ATC
Syncrude | Aurora 24 (Aurora),Aurora 23 (Aurora),MH1 (Aurora - Aurora) | 2018-04-23 08:00 | 2018-04-29 18:00 | N | N | replacements for 22B & 23A | Circuit Breaker, Line
EPCOR | 987s C2406 (987s Clover Bar) | 2018-04-23 08:30 | 2018-04-27 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Garneau T3 (Garneau) | 2018-04-23 08:30 | 2018-04-27 17:00 | N | N | doble | Transformer
BCH | 5L51 (Ingledow - Custer) | 2018-04-23 09:00 | 2018-04-27 19:00 | N | Y | ING 5D23 cutting over controls and replace failed glass on 9 structures | Line |  | ING 5D23 cutting over controls to new station control equipment. (PLC upgrade project) Replace failed glass on 9 structures. Requires outage - unable to do hot. Issues last summer with this circuit - main feed to the states. Cannot wait until October - complete ASAP | Limits ATC, 500 kV
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan),862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons),899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen),166s 862N (166s Dow Chem Fort Saskatchewan),166s 899N (166s Dow Chem Fort Saskatchewan) | 2018-04-23 09:30 | 2018-05-03 18:00 | N | Y | replace CT4 and replace 166s8, maintenance on T1 | Circuit Breaker, Line, Transformer |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | 814s T1 (814s Bellamy) | 2018-04-23 09:30 | 2018-04-27 17:00 | N | Y | doble | Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 225AL (313s Raymond Reservoir - 225L tap),225L (67s Stirling - 225s Magrath) | 2018-04-24 07:00 | 2018-04-25 18:00 | N | Y | create open point 'A' for upcoming 225L structure moves | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 233s T2 (233s Beamer),708L (233s Beamer - 708L88N),735L (171s Redwater - 233s Beamer),233s Beamer 138 kV Bus 2 | 2018-04-24 07:30 | 2018-05-05 18:30 | N | Y | switch maintenance, TX maintenance and customer switchgear change | Bus, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 732s 501R (732s Mitsue),732s 901T (732s Mitsue),7L49 (732s Mitsue - 729s Otauwau),732s 702 (732s Mitsue),732s 703 (732s Mitsue),7L23 (732s Mitsue - 858s Narrows Creek),7L23D4 (732s Mitsue),7L49D1 (732s Mitsue) | 2018-04-24 08:00 | 2018-05-05 17:00 | N | Y | breaker, CT and PT replacement | Circuit Breaker, Line, Switch, Transformer, Shunts |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT STAGE A: April 16-24 GOI 2-43738A Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 Completed STAGE B: April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 Present STAGE C: May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2, 706A, 7L31D1 STAGE D: End of May 5  May 16 GOI 2-43738D Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 STAGE E: (Vendors Tentative delivery Date of CTs) May 16  May 18 GOI 2-43738E Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 2nd Expansion due to late install of 2 CTs on 703 STAGE F: May 18 - June 7 GOI 2-43738F Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank),30EDD-1-626 (30EDD-1),30EDD-1-627 (30EDD-1),30EDD-1-628 (30EDD-1),30EDD-1-629 (30EDD-1) | 2018-04-24 08:00 | 2018-05-08 18:00 | N | Y | line maintenance and protection | Line, Circuit Breaker |  | Planned maintenance 29PL6-3 Line Assets Inc. of Bus Breaker, Protection and Line appratus: - 5 Year mtce - 5 year mtce on breakers, bus CT and switches - Relay Retrofits for 626, 627, 628, 629 Breakers - 624T Transformer Mtce | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.3TR (ENMAX 36) | 2018-04-24 08:00 | 2018-04-24 16:00 | N | N | breaker remote closing issue on 36B25-36.3TR | Transformer |  |  | For Information Only
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2018-04-24 08:30 | 2018-04-24 10:30 | N | Y | upgrading 166s, 218s and 258s MPLS node | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 158s T2 (158s Vauxhall) | 2018-04-24 08:30 | 2018-04-25 16:00 | N | N | maintain and doble T2, fix leaky pipe and check out gas alarm | Transformer |  | Maintain and doble T2, fix leaky pipe and check out gas alarm | For Information Only
ALTALINK | 28s T2 (28s West Brooks) | 2018-04-24 10:30 | 2018-04-26 14:00 | N | Y | maintain, doble and SFRA T2 | Transformer |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s T3 (38s East Edmonton),215L (38s East Edmonton - 286s Yasa),731L (38s East Edmonton - 420s Broadmoor),761L (71s Lamoureux - 38s East Edmonton),38s East Edmonton 138 kV Bus 2 | 2018-04-24 12:00 | 2018-04-26 18:00 | N | N | protection trip tests, post insulator and strain insulator replacements begin 38s62 replacement & 38s4152 addition | Line, Bus, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 767L (320p Keephills - 767L167A),834L (384s Keystone - 320p Keephills),809L (320p Keephills - 510s Sunnybrook) | 2018-04-25 07:00 | 2018-04-27 18:00 | N | Y | [KATR]-moving a portion of 1043L in preparation for 1045L to terminate at 320P and stringing conductor overtop of 834L | Line |  | [KATR]-Moving a portion of 1043L in preparation for 1045L to terminate at 320P and Stringing conductor overtop of 834L | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 320p 1352 (320p Keephills),1043L (320p Keephills - 367s Harry Smith) | 2018-04-25 07:00 | 2018-04-29 19:00 | N | Y | [KATR]-re-configure part of 1043L into 320p1352 bay | Line, Circuit Breaker |  |  | 240 kV, Overload
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2018-04-25 08:00 | 2018-04-25 12:00 | N | N | spring substation washing and check reversing switches 22.1(X), 22.1(Y), 22.3 | Line, Transformer |  | Spring Substation Washing. Check reversing switch 22.1(X), 22.1(Y), 22.3 | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12),ENMAX 12 B138-832L (ENMAX 12) | 2018-04-25 08:00 | 2018-04-26 16:00 | N | N | breaker maintenance 12B138-832L | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s T1 (17s Benalto) | 2018-04-25 08:30 | 2018-04-28 17:00 | N | N | maintain, doble and SFRA T1 | Transformer |  |  | For Information Only
ATCO | 930s SVC (930s Arcenciel) | 2018-04-25 08:30 | 2018-04-25 15:30 | N | Y | complete SVC air cooling inspection and breaker 401 partial PM | Shunts |  | Complete SVC Air Cooling Inspection and Adjustment And Complete Breaker 401 Partial PM, SVC Offline for the Duration of the Work | Pre-Condition
ALTALINK | 580s T1 (580s Sylvan Lake) | 2018-04-25 08:30 | 2018-04-26 15:00 | N | N | doble transformer | Transformer |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2018-04-25 12:00 | 2018-04-25 18:00 | N | N | spring substation washing and check reversing switches 22.2(X), 22.2(Y) | Line, Transformer |  | Spring Substation Washing. Check reversing switch 22.2(X), 22.2(Y) | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225L (67s Stirling - Open Point A) | 2018-04-25 18:00 | 2018-05-24 08:00 | N | N | 225L structure moves | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.81L (ENMAX 22 - ENMAX 39),ENMAX 22 B138-22.81 (ENMAX 22) | 2018-04-25 18:01 | 2018-04-27 18:00 | N | N | fix 22B138-22.81 closing issues | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale T4 (Rossdale) | 2018-04-26 07:00 | 2018-04-27 17:00 | N | N | cutting over and commissioning new protection | Transformer
ALTALINK | 325s 1552 (325s Leduc) | 2018-04-26 07:00 | 2018-04-26 17:00 | N | N | install bird coverup, perform settings updates, re- test relays and return cap bank to service | Shunts |  |  | For Information Only
EPCOR | 803s T2 (803s Lambton) | 2018-04-26 07:00 | 2018-04-26 19:15 | N | Y | cutover of new relay protection | Transformer |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 289s T1 (289s Saunders Lake) | 2018-04-26 07:30 | 2018-04-28 17:30 | N | Y | tap changer gas piping modification | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | 14.1TR (ENMAX 14) | 2018-04-26 08:00 | 2018-04-26 16:00 | N | N | 14s autoswitching relay replacement | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 10.1TR (ENMAX 10),832L (ENMAX 10 - ENMAX 12) | 2018-04-26 08:00 | 2018-04-26 16:00 | N | N | adjust 10.1TR whips | Line, Transformer |  | Adjust 10.1TR whips. Outage on 832L required | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | Phone Outage | 2018-04-26 08:00 | 2018-04-26 20:00 | N | N | install Orderwire phone set at 5th desks at SCC and BUCC | SCInternal |  |  | Pre-Condition
AESO-SC | ETS | 2018-04-26 09:00 | 2018-04-26 10:00 | N | N | needed for the Weblogic 12c upgrade project | SCInternal |  |  | Pre-Condition
ALTALINK | 445s T1 (445s Elk River) | 2018-04-26 10:30 | 2018-04-26 17:00 | N | N | urgent inspect and repair tap changer | Transformer |  | Urgent trouble corrective: Inspect and repair tap changer as it is between taps. | For Information Only
ALTALINK | 38s 62 (38s East Edmonton) | 2018-04-26 16:00 | 2018-04-30 18:00 | N | N | replace 38s62 and install new tie breaker 38s4152 | Circuit Breaker |  |  | Pre-Condition, Overload, Creates Radial Feeds
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2018-04-26 22:00 | 2018-04-27 03:00 | N | N | wiring and commissioning on 94 relay | Transformer, Line
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2018-04-27 08:00 | 2018-04-27 16:00 | N | N | autoswitching relay replacement | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton),38s 761N (38s East Edmonton),38s89 (38s East Edmonton) | 2018-04-27 11:01 | 2018-04-27 13:00 | N | N | Trip test from 38s4152 breaker fail | Switch, Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor),38s 731E (38s East Edmonton),38s48 (38s East Edmonton) | 2018-04-27 13:01 | 2018-04-27 15:00 | N | N | trip test from 38s4152 breaker fail | Switch, Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-65 952_4813 (29EDD-65),29EDD-65 952_4823 (29EDD-65) | 2018-04-27 20:00 | 2018-05-06 23:00 | N | N | forced outage to repair oil leak | Circuit Breaker |  |  | 240 kV
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 ( 38s East Edmonton) | 2018-04-28 07:00 | 2018-04-28 09:00 | N | N | trip test from 38s62 breaker fail | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2018-04-28 08:00 | 2018-04-28 12:00 | N | N | spring substation washing | Line, Shunts, Transformer |  | Spring Substation Washing. Check reversing switch 31.1TR | Pre-Condition
ALTALINK | 38s T1 (38s East Edmonton) | 2018-04-28 08:00 | 2018-05-02 16:00 | N | N | transformer replacement, replace existing one with new 240/138 kV 500 MVA transformer. ISD April 30, 2018 | Transformer |  |  | For Information Only
Syncrude | UE_1 7204 (UE_1 Syncrude Plant 30-2),UE_1 7205 (UE_1 Syncrude Plant 30-2),UE_1 7209 (UE_1 Syncrude Plant 30-2) | 2018-04-28 08:00 | 2018-04-29 18:00 | N | Y | switch PM work | Switch, Circuit Breaker |  |  | Restricts Generation, For Information Only
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2018-04-28 09:01 | 2018-04-28 11:00 | N | N | Trip test from 38s62 breaker fail | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2018-04-28 12:00 | 2018-04-28 18:00 | N | N | Spring Substation Washing. 31.3TR check reversing switch | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 865L (216s Knightsbridge - 38s East Edmonton),38s 865N (38s East Edmonton) | 2018-04-28 13:01 | 2018-04-28 15:00 | N | N | trip test from 38s62 breaker fail | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2018-04-29 07:00 | 2018-05-02 19:00 | N | Y | [KATR] implementing new A & B protections and closing 320p Open Point 'C' | Line |  | Implementing new A & B protections; closing 320p Open Point 'C' (located between Structures #1043L13 & #1045L32A); jumpering across existing in-line insulators West of Structure #1045L32A | 240 kV, Pre-Condition
ENMAX, ALTALINK | 37.2TR (ENMAX 37),37.82L (74s Janet - ENMAX 37) | 2018-04-29 08:00 | 2018-04-29 18:00 | N | Y | breaker maintenance and SW84 corrective repair | Line, Transformer |  | HV SW MD maint on MD-37.2TR. SF6 gas sample 37B138-37.82. SW84 corrective repair. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 749AL (267s Killarney Lake - 749AL0A) | 2018-04-29 10:19 | 2018-05-03 17:00 | N | N | forced outage, flooding issue, tower base eroded | Line
EPCOR | Garneau T2 (Garneau) | 2018-04-30 07:00 | 2018-05-03 17:00 | N | N | doble | Transformer |  |  | For Information Only
EPCOR | Namao T1 (Namao),Namao N721 (Namao),Namao N722 (Namao) | 2018-04-30 07:00 | 2018-10-01 17:00 | N | N | TX replacement | Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 2075S Newell | 2018-04-30 07:00 | 2018-05-11 18:00 | N | Y | valve hall outage to conduct preventative Maintenance on all equipment within the zone of isolation | Station |  | Valve Hall outage is required to conduct Preventative Maintenance on all equipment within the zone of isolation. i.e. Valve Cooling DIW Strainers, Valve Module inspections, Switch operations, etc. Power transmission on the DC link (13L50) will not be possible during the outage. | Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2018-04-30 07:00 | 2018-05-11 18:00 | N | Y | Heathfield and Newell isolating their respective valve halls | Line |  | 13L50 will be out of service during this time as the connecting stations, Heathfield and Newell, are isolating their respective Valve Halls. | Over/Under Voltage, Contingency Requires Mitigation, 500 kV
ATCO | 2029s Heathfield | 2018-04-30 07:00 | 2018-05-11 18:00 | N | Y | valve hall outage to conduct preventative Maintenance on all equipment within the zone of isolation | Station |  | Valve Hall outage is required to conduct Preventative Maintenance on all equipment within the zone of isolation i.e. Valve Cooling DIW Strainers, Valve Module inspections, Switch operations, etc. Power transmission on the DC link (13L50) will not be possible during the outage. . | Pre-Condition
EPCOR | 814s T2 (814s Bellamy),814s B2402 (814s Bellamy),Rossdale BR722 (Rossdale),814s B2406 (814s Bellamy) | 2018-04-30 07:00 | 2018-05-04 17:00 | N | Y | doble | Transformer, Circuit Breaker |  |  | 240 kV
EPCOR | 72VN21 (Namao - 511s Victoria) | 2018-04-30 07:30 | 2018-05-03 17:00 | N | N | relay maintenance | Line |  |  | For Information Only
ALTALINK, Lethbridge | 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2018-04-30 08:00 | 2018-05-02 13:30 | N | Y | move transmission pole and install new one - City of Lethbridge | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.2TR (ENMAX 27) | 2018-04-30 08:00 | 2018-05-02 14:50 | N | N | PRD installation | Transformer |  |  | For Information Only
ENMAX | 40.1TR (ENMAX 40) | 2018-04-30 08:00 | 2018-05-11 16:00 | N | N | tapchanger inspection and check reversing switch | Transformer |  |  | For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2018-04-30 08:00 | 2018-04-30 16:00 | N | N | 14s autoswitching relay replacement | Line |  | 14s Autoswitching relay replacement. 11B138-11.82L HV breaker maintenance | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2018-04-30 08:00 | 2018-05-03 16:00 | N | N | KATR In-service-date: May 02, 2018. | Line |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2018-04-30 08:00 | 2018-04-30 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Syncrude | Aurora 34 (Aurora),Aurora 33 (Aurora),MH2 (Aurora - Aurora) | 2018-04-30 08:00 | 2018-05-06 18:00 | N | N | replacements for 33B & 34A | Circuit Breaker, Line |  |  | For Information Only
REDDEER | 209s T1 (209s Timberlands) | 2018-04-30 09:00 | 2018-05-04 15:30 | N | N | warranty repair work on transformer bushing | Transformer |  | Oil weeps from 209T1 secondary bushing (X3). The manufacturer (Siemens) will be onsite to complete warranty repair. | For Information Only
ALTALINK, TRANSALTA | 35s T1 (35s Rundle),35s T3 (35s Rundle),35s8 (35s Rundle),35s41 (35s Rundle),35s Rundle 13.8kV Bus | 2018-04-30 09:00 | 2018-05-10 18:00 | N | Y | breaker replacements | Transformer, Switch, Bus |  |  | Restricts Generation
TRANSALTAW | 418s Ardenville | 2018-04-30 09:30 | 2018-05-03 18:00 | N | N | maintenance | Station |  |  | Restricts Generation
ALTALINK | 54L (118s Canmore - 54L172) | 2018-04-30 09:45 | 2018-04-30 13:15 | N | N | install dampers (str 163) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s 452 (63s Red Deer) | 2018-04-30 11:30 | 2018-05-03 16:30 | N | Y | maintain minimum oil breaker 240kV ABB HLRE. | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 74s 2052 (74s Janet) | 2018-04-30 12:00 | 2018-05-03 16:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2018-04-30 12:00 | 2018-04-30 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s 62 (38s East Edmonton) | 2018-04-30 18:00 | 2018-05-01 18:00 | N | N | replace 38s62 and install new tie breaker 38s4152 | Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 987s CC13 (987s Clover Bar) | 2018-05-01 07:00 | 2018-05-01 17:00 | N | N | maintenance | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ATCO | 7L129 (918s Bauer - 710s Vermilion),710s 704 (710s Vermilion) | 2018-05-01 07:00 | 2018-05-13 17:30 | N | N | protection upgrades | Line, Circuit Breaker |  | Protection upgrades | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 404s T2 (404s Peace Butte) | 2018-05-01 08:00 | 2018-05-02 18:00 | N | N | doble and maintain 404sT2 Tx18713, maintain 404s12. | Transformer |  |  | For Information Only
ALTALINK | 661S Laura Lake | 2018-05-01 08:00 | 2018-05-01 18:00 | N | N | replace battery on OCR-FORM6 and standard relay maintenance | Station
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2018-05-01 08:00 | 2018-05-01 16:00 | N | N | breaker maintenance 38B138-38.83, SF6 gas sample 38B138-38.83 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2018-05-01 08:00 | 2018-05-01 18:00 | N | N | spring substation washing & check reversing switch 32.3TR | Line, Transformer
ENMAX | 14.2TR (ENMAX 14) | 2018-05-01 08:00 | 2018-05-01 16:00 | N | N | 14s autoswitching relay replacement | Transformer |  |  | For Information Only
CMH | MHS7 T71 (MHS1 CMH Brier Park),MHS7 MH138-707 (MHS7 CMH Brier Park),MHS7 MH69-706 (MHS7 CMH Brier Park) | 2018-05-02 06:30 | 2018-05-06 11:30 | N | N | investigate transformer bushing oil leak | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 908AL (52S East Industrial - 908L Tap),52sE2402 (52s East Industrial) | 2018-05-02 07:00 | 2018-05-02 17:00 | N | Y | maintenance | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power) | 2018-05-02 07:00 | 2018-05-02 18:00 | N | Y | 503L10 metering platform replacement | Line |  |  | Restricts Generation
ENMAX | 34.1TR (ENMAX 34),34.3TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2018-05-02 08:00 | 2018-05-04 16:00 | N | N | HV SW maintenance. SW61, SW62, SW63@34sub, check reversing switch 34.1TR, 34.3TR, gas relay testing 34.3TR | Line, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 41.84L (ENMAX 54 - ENMAX 41),54.81L (ENMAX 54 - ENMAX 65),54.1TR (ENMAX 54) | 2018-05-02 08:00 | 2018-05-02 18:00 | N | N | spring substation washing, check reversing switch, backfeed 25kV bus for SSTR | Line, Transformer |  |  | For Information Only
ALTALINK | 38s T1 (38s East Edmonton),38s 73 (38s East Edmonton) | 2018-05-02 08:00 | 2018-05-02 10:00 | N | Y | trip test from 38s62 breaker fail | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.3TR (ENMAX 14) | 2018-05-02 08:00 | 2018-05-02 16:00 | N | N | autoswitching relay replacement | Transformer |  |  | For Information Only
ALTALINK | 688L (199s East Airdrie - 688DL23),199s 688 (199s East Airdrie) | 2018-05-02 08:30 | 2018-05-02 16:00 | N | Y | maintain 138 kV SF6 breaker | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 522L (320p Keephills - 522L6),320p T5 (320p Keephills) | 2018-05-02 09:00 | 2018-05-03 17:00 | N | N | 320pT5 steam clean/assess leaks | Transformer, Line |  |  | For Information Only
Saskpower | SaskPower C1S | 2018-05-02 09:00 | 2018-05-02 16:00 | N | N | maintenance | Line |  |  | Limits ATC
ENMAX | 54.81L (ENMAX 54 - ENMAX 65) | 2018-05-02 18:01 | 2018-05-07 16:00 | N | N | spring substation washing, check reversing switch, backfeed 25kV bus for SSTR | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 14.4TR (ENMAX 14) | 2018-05-03 08:00 | 2018-05-03 16:00 | N | N | 14s autoswitching relay replacement | Transformer |  |  | For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2018-05-03 08:00 | 2018-05-03 16:00 | N | N | test high side CTs and check reversing switch | Transformer |  | Test high side CTs currently in service on 11.1TR being used by the T60 (WO 21151434?) Check Reversing switch | For Information Only
ALTALINK | 95s T1 (95s Imperal Oil Edmonton),738L (95s Imperial Oil Edmonton - 738AL1) | 2018-05-03 08:00 | 2018-05-18 16:00 | N | N | customer switchgear change | Line, Transformer |  |  | For Information Only
ALTALINK | 151s T2 (151s Strathmore) | 2018-05-03 08:30 | 2018-05-03 17:30 | N | N | CT saturation and ratio testing on 151sT2 CT's | Transformer |  | Techs to perform the following while at site:CT Saturation and Ratio testing on 151sT2 CT's. | For Information Only
ALTALINK | 681s 1152 (681s Bannerman) | 2018-05-03 10:00 | 2018-05-03 17:30 | N | Y | 681s1152 N phase densimeter req replacement | Circuit Breaker |  | 681s1152 N Ph Densimeter Req Replacement | 240 kV
ALTALINK | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen) | 2018-05-03 18:00 | 2018-05-21 18:00 | N | Y | maintenance | Line |  |  | Restricts Generation
ENMAX | 14.1C (ENMAX 14) | 2018-05-04 08:00 | 2018-05-04 16:00 | N | N | 14s autoswitching relay replacement | Shunts |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2018-05-04 09:00 | 2018-05-04 18:00 | N | N | spring substation washing | Line, Transformer |  | Spring Substation Washing. Check reversing switch | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2018-05-05 08:00 | 2018-05-05 16:00 | N | N | remove birds nest from structure | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 732s 501R (732s Mitsue),732s 901T (732s Mitsue),7L31 (732s Mitsue - 844s AEC MILL),7L49 (732s Mitsue - 729s Otauwau),732s 702 (732s Mitsue),732s 703 (732s Mitsue),7L23 (732s Mitsue - 858s Narrows Creek),7L23D4 (732s Mitsue),7L49D1 (732s Mitsue),7L31D1 (732s Mitsue) | 2018-05-05 08:00 | 2018-05-05 19:00 | N | Y | breaker, CT and PT replacement | Circuit Breaker, Line, Switch, Transformer, Shunts |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT April 16-24 GOI 2-43738A Outage on 702 & 703 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 701B, 500D1, 707B, 7L49D1, 7L23D4 May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 500D1, 7L31D1 706A, 707B, 7L49D1, 7L23D4 Outage expanded to include 7L31 due to limits of approach issues with replacing 702PT. This outage is planned to be reduced at the end of day to allow for restoration of 7L31 May 5 -Jun 7 GOI 2-43738D Reduce Isolation zone to include Breaker 702 & 703 Isolation points: 702A, 703A, 7L49D1 If May 5th scope is not able to be completed as planned, this reduction of outage will be delayed to May 6. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2018-05-05 08:00 | 2018-05-05 16:00 | N | N | digging test pits near 1.81L for future 1.81L cable replacement | Line |  | Contractor digging test pits near 1.81L for future 1.81L cable replacement | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2018-05-05 09:00 | 2018-05-05 10:30 | N | N | 38.1TR panel replacement | Line |  | 38.1TR Panel replacement. Short BD CTs | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2018-05-05 10:30 | 2018-05-05 12:00 | N | N | 38.1TR panel replacement | Line |  | 38.1TR Panel replacement. Short BD CTs | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 233s T2 (233s Beamer) | 2018-05-05 18:31 | 2018-06-12 18:30 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ATCO | 7L49 (732s Mitsue - 729s Otauwau),732s 702 (732s Mitsue),732s 703 (732s Mitsue),7L49D1 (732s Mitsue) | 2018-05-05 19:01 | 2018-05-16 08:00 | N | N | breaker, CT and PT replacement | Circuit Breaker, Switch, Line |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT STAGE A: April 16-24 GOI 2-43738A Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 Completed STAGE B: April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 Present STAGE C: May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2, 706A, 7L31D1 STAGE D: End of May 5  May 16 GOI 2-43738D Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 STAGE E: (Vendors Tentative delivery Date of CTs) May 16  May 18 GOI 2-43738E Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 2nd Expansion due to late install of 2 CTs on 703 STAGE F: May 18 - June 7 GOI 2-43738F Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 524s 6 (524s Fiberglass),524s T1 (524s Owen Corning) | 2018-05-06 07:00 | 2018-05-07 13:00 | N | N | transformer leak | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 37.1TR (ENMAX 37) | 2018-05-06 08:00 | 2018-05-12 12:00 | N | N | install NGR | Transformer |  |  | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark),Meadowlark T1 (Meadowlark) | 2018-05-07 07:00 | 2018-05-18 17:00 | N | N | PRD install | Transformer, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 528S Blue Trail Wind Farm | 2018-05-07 07:00 | 2018-05-10 17:00 | N | N | maintenance | Station |  |  | Restricts Generation
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2018-05-07 07:00 | 2018-06-14 17:00 | N | N | new protection cutover / degass | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 452 (39s Bickerdike) | 2018-05-07 07:00 | 2018-05-08 15:00 | N | N | isolate existing 740L S protections and connect new B protections | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 38.1C (ENMAX 38),ENMAX 38 138-38.CAP (ENMAX 38) | 2018-05-07 08:00 | 2018-05-07 16:00 | N | N | 38.1TR panel replacement, short BD CTs | Circuit Breaker, Shunts |  |  | Pre-Condition
ENMAX | 2.4TR (ENMAX 2) | 2018-05-07 08:00 | 2018-05-08 16:00 | N | N | tap changer inspection | Transformer |  | Tapchanger Inspection. Check reversing switch. Oil sample MT, bushings, TC | For Information Only
ENMAX | 14.2C (ENMAX 14) | 2018-05-07 08:00 | 2018-05-07 16:00 | N | N | 14s autoswitching relay replacement | Shunts |  |  | Pre-Condition
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2018-05-07 08:00 | 2018-05-09 16:00 | N | N | SF6 gas sample 5B138-1.84 and doble and repair switch operation SW99 | Line |  |  | Pre-Condition
ENMAX | 11.3TR (ENMAX 11) | 2018-05-07 08:00 | 2018-05-11 16:00 | N | N | Doble test transformer and associated maintenance | Transformer
ATCO | 9L29 (946s Oakland - 963s Coyote Lake) | 2018-05-07 08:30 | 2018-05-07 13:00 | N | N | re-install missing marker cone | Line |  |  | For Information Only
BCH | 2L112 (Nelway - Boundary) | 2018-05-07 09:00 | 2018-05-08 17:00 | N | Y | annual plan request F19 | Line |  |  | Limits ATC
ALTALINK | 35s T2 (35s Rundle),35s9 (35s Rundle) | 2018-05-07 09:00 | 2018-05-09 17:00 | N | Y | bushing repair | Switch, Transformer |  |  | Restricts Generation
ENMAX | 38.2TR (ENMAX 38) | 2018-05-07 09:00 | 2018-05-07 11:00 | N | N | panel replacement | Transformer |  | 38.1TR Panel replacement. Short BD CTs | For Information Only
ALTALINK | 708L (71s Lamoureux - 708L88X),71s 852 (71s Lamoureux),71s 752 (71s Lamoureux) | 2018-05-07 09:30 | 2018-05-10 16:30 | N | Y | replace PT's | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 20s T5 (20s Ghost) | 2018-05-07 13:00 | 2018-05-07 15:00 | N | N | determine tap position | Transformer |  |  | For Information Only
ATCO | 724s 6L37D2 (724s Hines Creek) | 2018-05-07 13:30 | 2018-05-10 15:30 | N | N | switch replacement of 6L37D2 | Switch |  | switch replacement of 6L37D2, cut switch clear, contractor to drive pilings | For Information Only
ENMAX | 38.1TR (ENMAX 38) | 2018-05-07 14:00 | 2018-05-19 16:00 | N | N | panel replacement | Transformer |  | Panel replacement. Drop oil in TR to take measurements (Sub 57 May 14-15. Mohamed Noor 403-390-7180) | For Information Only
BCH | 5L52 (Ingledow - Custer) | 2018-05-07 15:00 | 2018-05-07 17:00 | N | Y | ING 5D25 cutting over controls to new station control equipment | Line |  | ING 5D23 cutting over controls to new station control equipment. (PLC upgrade project) Replace failed glass on 9 structures. Requires outage - unable to do hot. Issues last summer with this circuit - main feed to the states. Cannot wait until October - complete ASAP | Limits ATC, 500 kV
ALTALINK | 756L (87s Gaetz - 535s Joffre) | 2018-05-08 07:15 | 2018-05-10 17:45 | N | N | maintenance components | Line | Studied with Joffre #1 (JOF1) net generation = 120 MW. Higher JOF1 generation may alleviate overload concerns for next contingencies.
ALTALINK | 199s T2 (199s East Airdrie) | 2018-05-08 08:30 | 2018-05-08 17:30 | N | N | replace Weschler transformer monitor units | Transformer |  | techs to replace Weschler transformer monitor units while at site
ATCO | 6L03 (6L17 tap - 757s Battle River) | 2018-05-08 09:00 | 2018-05-08 20:00 | N | N | replace damaged pole (emergency) | Line
ATCO | 749s 704 (749s Flyingshot Lake) | 2018-05-08 09:30 | 2018-05-08 16:00 | N | N | repair leaking CT (low oil could cause CT failure), breaker out of service, ring open | Circuit Breaker |  | repair leaking CT (low oil could cause CT failure), breaker out of service, ring open | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 39s 352 (39s Bickerdike) | 2018-05-08 15:00 | 2018-05-14 15:00 | N | N | isolate 740L S protection, install new B protection, function test | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 575s T1 (575s Sundre) | 2018-05-09 09:00 | 2018-05-09 17:00 | N | N | urgent trouble corrective | Transformer |  | Urgent Trouble Corrective: Assess leaks on 575sT1 Tx18533. | For Information Only
ALTALINK | 551GL1 | 2018-05-09 09:30 | 2018-05-09 14:30 | N | N | change fuse size for better protection coordination | Switch |  | Fortis request; change fuse size for better protection coordination | For Information Only
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2018-05-09 11:30 | 2018-11-26 09:00 | N | Y | emergency safety requirement | Line |  |  | 240 kV, Pre-Condition
MONTANA | MATL (120s Picture Butte - Montana) | 2018-05-09 11:45 | 2018-05-14 23:40 | N | Y | PST repair due to forced outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 33s3 (33s Spray) | 2018-05-10 08:00 | 2018-05-10 12:00 | N | Y | test | Switch |  |  | Restricts Generation
REDDEER | 217s T1 (217s North Red Deer) | 2018-05-10 09:00 | 2018-05-10 13:30 | N | N | maintain transmission facilities | Transformer |  |  | For Information Only
ALTALINK | 33s6 (33s Spray) | 2018-05-10 13:00 | 2018-05-10 17:00 | N | Y | test | Switch |  |  | Restricts Generation
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2018-05-12 08:00 | 2018-05-13 16:00 | N | N | HV cable sheath testing and DGA sample | Line |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | UE-1 30-2PTR72-3 (UE-1) | 2018-05-12 08:00 | 2018-05-12 18:00 | N | Y | switch 72-09 PM work | Transformer |  |  | Restricts Generation
ENMAX | 37.2TR (ENMAX 37) | 2018-05-12 12:00 | 2018-05-18 16:00 | N | N | install NGR | Transformer |  |  | For Information Only
ALTALINK | 238S Shell Harmattan | 2018-05-13 13:00 | 2018-05-16 18:00 | N | N | upgrade metering and install new 238s12 | Station |  | Metering Upgrade, T1 LA's, Install New 238s12 and U/G cables on T1 NGR to 238s9 PT | For Information Only
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan),862L (166s Dow Chemical Fort Saskatchewan - 258s Dow Hydro Carbons),899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen),166s 862N (166s Dow Chem Fort Saskatchewan),166s 899N (166s Dow Chem Fort Saskatchewan) | 2018-05-14 07:30 | 2018-05-17 17:00 | N | Y | replace 166s8 insulators | Circuit Breaker, Line, Transformer |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 41.1TR (ENMAX 41) | 2018-05-14 08:00 | 2018-05-15 16:00 | N | N | tapchanger inspection | Transformer |  | tapchanger inspection. Check reversing switch. Oil sampling MT, TC | For Information Only
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2018-05-14 08:00 | 2018-05-15 16:00 | N | N | HV breaker 20B138-20.82, SF6 gas sample 21B138-20.82 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11) | 2018-05-14 08:00 | 2018-05-25 16:00 | N | N | test high side CT, check reversing switch | Transformer
SUNCOR | 29EDD-34 752_121 (29EDD-34),29EDD-85 752_10040 (29EDD-85),29EDD-85 752_10020 (29EDD-85),29PL7-1 (29EDD-34 - 29EDD-85) | 2018-05-14 08:00 | 2018-05-25 15:45 | N | N | line raise for clearance | Line, Circuit Breaker |  | FIREBAG 29PL7-1 EAST ATHABASCA HIGHWAY HIGH VOLTAGE LINE LIFT: Line outage is required in order to raise the existing 29PL7-1 144kV transmission line to accommodate the required 18m road clearance over the new Imperial Oil access road off the East Athabasca Hwy. The new IOL access road will be crossing the 29PL7-1 (144kV) transmission line between structures 143-144, and 29PL9-12/13 (260kV) transmission lines between structures 46-47, as well as multiple pipeline Rights-of-Ways. | Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354S Summerview | 2018-05-14 09:00 | 2018-05-14 16:00 | N | N | SMV1 DVAR maintenance | Station |  |  | Pre-Condition
ALTALINK | 703L (213s Hughenden - 703L33) | 2018-05-14 12:15 | 2018-05-14 17:30 | N | N | create open point 'A' between Str 31-32 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 338s 252 (338s Cherhill) | 2018-05-14 12:30 | 2018-05-16 14:30 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 39s 452 (39s Bickerdike) | 2018-05-14 15:00 | 2018-05-14 16:00 | N | N | connect new B Protections in new rack | Circuit Breaker |  | 425 Breaker outage to isolate existing 740L S Protections and connect new B Protections in new rack. Function test with new B protection | Pre-Condition, Contingency Requires Mitigation
VISIONREQ | 354S Summerview | 2018-05-14 16:01 | 2018-05-15 06:59 | N | N | SMV2 DVAR maintenance | Station |  |  | Pre-Condition
ALTALINK | 703L (213s Hughenden - 703L33) | 2018-05-14 17:30 | 2018-05-31 08:00 | N | N | airbrake switch replacement (703L33) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, AESO | 736L (38s East Edmonton - 293s Bernese),38s 736E (38s East Edmonton) | 2018-05-15 07:00 | 2018-05-15 19:00 | N | N | 38s736E maintenance & low gas repair | Circuit Breaker, Line |  | 38s736E maintenance & low gas repair Issue to: Tyler Kee @ AML Contact #: 780-217-9319 | For Information Only
VISIONREQ | 354S Summerview | 2018-05-15 07:00 | 2018-05-15 19:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ATCO | 763s 507C (763s Hanna) | 2018-05-15 07:30 | 2018-05-15 16:00 | N | N | 763s Hanna - 507C PCB testing | Shunts |  | 763S Hanna - 507C PCB Testing CAPACITOR BANK 507C @ 763S 507C out of service PCB Testing of 3 wafers on 507C. We will be doing destructive PCB Testing on 3 cap wafers from second half of 507C. After testing is complete the second half of 507C will be have to be de-rated to 1.8MVAR. This is down from 2.25MVAR. | For Information Only
ALTALINK | WATL (510s Sunnybrook - 511s Crossings) | 2018-05-15 08:00 | 2018-05-16 18:00 | N | N | urgent repair to thyristors | Line |  |  | 500 kV
ALTALINK | 87s 2352 (87s Gaetz) | 2018-05-15 08:00 | 2018-05-17 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | Maintain 240kV minimum oil breaker. | 240 kV, Contingency Requires Mitigation
ALTALINK | 293s T1 (293s Bernese) | 2018-05-15 08:30 | 2018-05-15 12:30 | N | N | repair 293s T1 X0 to VT2 concentric | Transformer |  | Repair 293s T1 X0 to VT2 Concentric, currently Ungrounded | For Information Only
ATCO | 786s SVC (786s High Level) | 2018-05-15 08:30 | 2018-05-15 16:30 | N | Y | SVC maintenance | Shunts |  | Complete Inspection and Adjustment of SVC Air Cooling, SVC Off LIne for the Duration of the Work | Pre-Condition
ALTALINK | 953s T2 (953s Lake Louise) | 2018-05-15 09:00 | 2018-05-17 16:00 | N | N | tapchanger upgrade and adjust 953s18 | Transformer |  |  | For Information Only
ALTALINK | 293s T2 (293s Bernese) | 2018-05-15 09:30 | 2018-05-15 12:30 | N | N | repair 293s T2 X0 to VT3 concentric | Transformer |  | repair 293s T2 X0 to VT3 concentric, currently ungrounded | For Information Only
VISIONREQ | 354S Summerview | 2018-05-16 07:00 | 2018-05-17 17:00 | N | N | DVAR test | Station |  | TransAlta is requesting a 2 day outage on T6 at Summerview 354s for testing. The outage would be from 8:00 May 16 to 17:00 May 17, 2018. The outage will not affect production but will limit Summerview 2 DVAR to 50%. | Pre-Condition
ALTALINK | 367s 1352 (367s Harry Smith) | 2018-05-16 07:30 | 2018-05-16 12:00 | N | Y | [SWEATD] install head bolt in breaker CT | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 905L (19s Wabamun - 37s North Calder),37s 82 (37s North Calder),37s71 (37s North Calder) | 2018-05-16 07:30 | 2018-05-16 18:00 | N | Y | 37s71 60 deg hot spot | Switch, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 880L (523s Bullshead - 321s Al Rothbauer) | 2018-05-16 07:30 | 2018-05-17 16:00 | N | Y | install steel A-frame structure for MH15 line | Line |  | Install Steel A-frame structure for MH15 Line City of Medicine Hat that connects MHS-9 and MHS-7. | Firm Load Loss, Creates Radial Feeds
ENMAX | 41.2TR (ENMAX 41) | 2018-05-16 08:00 | 2018-05-17 16:00 | N | N | tapchanger inspection and maintenance | Transformer |  |  | For Information Only
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2018-05-16 08:00 | 2018-05-18 16:00 | N | N | doble CT 5B138-2.82 and maintenance | Line |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2018-05-16 08:00 | 2018-05-18 16:00 | N | N | switch maintenance: MD-34.2TR, MD 34.3TR SW64, SW65, SW66@34sub | Line, Transformer |  |  | For Information Only
ATCO | 732s 501R (732s Mitsue),732s 901T (732s Mitsue),7L49 (732s Mitsue - 729s Otauwau),732s 702 (732s Mitsue),732s 703 (732s Mitsue),7L23 (732s Mitsue - 858s Narrows Creek),7L23D4 (732s Mitsue),7L49D1 (732s Mitsue) | 2018-05-16 08:01 | 2018-05-18 17:00 | N | Y | breaker, CT and PT replacement | Circuit Breaker, Line, Switch, Transformer, Shunts |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT STAGE A: April 16-24 GOI 2-43738A Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 Completed STAGE B: April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 Present STAGE C: May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2, 706A, 7L31D1 STAGE D: End of May 5  May 16 GOI 2-43738D Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 STAGE E: (Vendors Tentative delivery Date of CTs) May 16  May 18 GOI 2-43738E Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 2nd Expansion due to late install of 2 CTs on 703 STAGE F: May 18 - June 7 GOI 2-43738F Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 253s C1 (253s Blackie),253s 182 (253s Blackie) | 2018-05-16 09:30 | 2018-05-16 16:30 | N | N | maintenance around cap bank enclosure | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2018-05-16 23:00 | 2018-05-17 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2018-05-17 03:00 | 2018-05-17 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 305S Acheson | 2018-05-17 07:30 | 2018-05-17 12:00 | N | N | close open point 'A' at 25kv | Station |  |  | For Information Only
ENMAX | 35.81L (42s Sarcee - ENMAX 35) | 2018-05-17 08:00 | 2018-06-01 16:00 | N | Y | (SWCRR)-request from road contractor to install girders on a bridge south of 42s | Line |  |  | Firm Load Loss, Creates Radial Feeds
TRANSALTA | 239S Castle River | 2018-05-17 08:00 | 2018-05-17 12:00 | N | N | VQ5 outage for work to underground conductors | Station |  |  | Restricts Generation
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2018-05-17 09:00 | 2018-05-17 16:00 | N | Y | 71s35 hotspot all phases (60deg) | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 391S Balzac | 2018-05-17 13:00 | 2018-05-17 15:00 | N | N | 25kV switchgear | Station |  |  | For Information Only
ATCO | 7L49 (732s Mitsue - 729s Otauwau),732s 702 (732s Mitsue),732s 703 (732s Mitsue),7L49D1 (732s Mitsue) | 2018-05-18 17:01 | 2018-06-07 12:00 | N | N | breaker, CT and PT replacement | Circuit Breaker, Switch, Line |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT STAGE A: April 16-24 GOI 2-43738A Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 Completed STAGE B: April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 Present STAGE C: May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2, 706A, 7L31D1 STAGE D: End of May 5  May 16 GOI 2-43738D Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 STAGE E: (Vendors Tentative delivery Date of CTs) May 16  May 18 GOI 2-43738E Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 2nd Expansion due to late install of 2 CTs on 703 STAGE F: May 18 - June 7 GOI 2-43738F Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2018-05-19 08:00 | 2018-05-19 18:00 | N | N | breaker maintenance | Line |  | HV Breaker maintenance 13B138-3.84, Doble 13LA138-3.84. SF6 gas sample 3B138-3.84. | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38) | 2018-05-20 08:00 | 2018-05-20 13:00 | N | N | line protection upgrade | Line, Transformer |  | Line Protection Upgrade. Test devices 95, 96, and 97 for autoswitching | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39) | 2018-05-20 13:00 | 2018-05-20 18:00 | N | N | line protection upgrade. | Transformer, Line |  | Line Protection Upgrade. Test devices 95, 96, and 97 for autoswitching | Firm Load Loss, Creates Radial Feeds
ENMAX | 38.3TR (ENMAX 38) | 2018-05-21 08:00 | 2018-05-31 08:00 | N | N | panel replacement | Transformer |  |  | For Information Only
Syncrude | Aurora 13 (Aurora),Aurora 14 (Aurora),TL-1 (Aurora - Aurora) | 2018-05-21 08:00 | 2018-06-04 18:00 | N | N | line trouble shooting | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2018-05-21 22:00 | 2018-05-22 04:00 | N | N | 9th ave bridge replacement | Line |  |  | Pre-Condition
ENMAX | 2.83L (ENMAX 5 - 2.83L tap),2.83L. 5s Portion | 2018-05-22 04:00 | 2018-05-28 22:00 | N | N | 9th ave bridge replacement | Terminal Equipment, Line |  | 9th ave bridge replacement. 5B138-2.83 spring replacement (21103814) | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 511s Victoria T5 (511s Victoria),CV5 (557s Castle Downs - 511s Victoria) | 2018-05-22 07:00 | 2018-05-25 17:00 | N | Y | doble/cable, manhole inspection | Line, Transformer |  |  | 240 kV, For Information Only
EPCOR | Meadowlark M722 (Meadowlark),Meadowlark M723 (Meadowlark),Meadowlark T2 (Meadowlark) | 2018-05-22 07:00 | 2018-06-01 17:00 | N | N | PRD install | Transformer, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Victoria V723 (Victoria) | 2018-05-22 07:00 | 2018-05-22 17:00 | N | N | doble | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 787L (71s Lamoureux - 787L29) | 2018-05-22 07:00 | 2018-05-24 16:30 | N | Y | replace PT's | Line |  |  | Pre-Condition, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO | 728s 701T (728s Mercer Hill),728s 701 (728s Mercer Hill) | 2018-05-22 07:00 | 2018-05-31 17:00 | N | N | replace breaker 701 | Circuit Breaker, Transformer |  | Replace breaker 701 | For Information Only
CMH | 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2018-05-22 08:00 | 2018-05-23 16:00 | N | N | ISD: May 22 -23, 2018 | Line
ENMAX | 40.2TR (ENMAX 40) | 2018-05-22 08:00 | 2018-05-23 16:00 | N | N | testing and oil sampling | Transformer |  | Tapchanger Inspection. Check reversing switch. Oil sampling MT/LTC | For Information Only
ALTALINK | 28s T1 (28s West Brooks),28s 22 (28s West Brooks),28s 31 (28s West Brooks),28S West Brooks 138kV Bus 1 | 2018-05-22 08:45 | 2018-05-26 17:45 | N | Y | CT wiring of T1, 28s22, 28s31 and trip tests for B protection addition | Bus, Transformer, Circuit Breaker |  | CT Wiring of T1, 28s22, 28s31 & Trip Tests for B Protection Addition | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | Phone Outage | 2018-05-22 10:00 | 2018-05-22 18:00 | N | N | install Orderwire phone set at 5th desks at SCC and BUCC | SCInternal |  |  | Pre-Condition
ALTALINK | 304S Shell Limestone,764L (581s Amoco Ricinus - 304s Shell Limestone) | 2018-05-22 11:00 | 2018-05-27 13:00 | N | N | tx maintenance, wildlife cover-up installation | Station, Line |  | Change 304s195, 304s295, 304s3, TX maintenance, wildlife cover-up installation | For Information Only
ALTALINK | 190L (17s Benalto - 320p Keephills),17s 2 (17s Benalto),17s 1 (17s Benalto),17s Benalto 240 kV North Bus 1,17s T3 (17s Benalto) | 2018-05-22 12:00 | 2018-05-25 15:00 | N | Y | 17s190N switch & post insulator replacements | Line, Bus, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2018-05-22 12:00 | 2018-05-25 16:00 | N | N | multiple leaks repair | Transformer |  | 54s T3 TX 18364 multiple leaks, 54sT3 maint TX 18364 LTC FPE/FPE 138/25K 90241710, 54sT3 doble TX 18364 LTC FPE/FPE 138/25K 90241709. Leaks are serious and need immediate attention. | For Information Only
ALTALINK | 763L (28s West Brooks - 763L257A) | 2018-05-23 07:00 | 2018-05-23 17:00 | N | N | forced outage | Line |  | Repair 28s30 airbreak | Pre-Condition, Creates Radial Feeds
EPCOR | Victoria V727 (Victoria) | 2018-05-23 07:00 | 2018-05-27 17:00 | N | N | doble | Circuit Breaker |  |  | For Information Only
ALTALINK | 250p11 (250p Bighorn Plant) | 2018-05-23 07:00 | 2018-05-24 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn Plant) | 2018-05-23 07:00 | 2018-05-24 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 973L (39s Bickerdike - 310p Sundance),310p 2252 (310p Sundance),310p 2352 (310p Sundance),39s973E (39s Bickerdike) | 2018-05-23 07:30 | 2018-05-24 17:30 | N | Y | replace 1 PT @ 310p | Switch, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 698s 452 (698s Jackfish) | 2018-05-23 07:30 | 2018-05-23 12:30 | N | Y | 698s452 gas leak | Circuit Breaker |  |  | 240 kV
ALTALINK | 250P 1 (250P Bighorn Plant) | 2018-05-23 09:00 | 2018-05-23 20:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
EPCOR | 987S Cloverbar | 2018-05-24 06:00 | 2018-05-27 20:00 | N | Y | customer outage | Station |  |  | Restricts Generation
ENMAX | 26.2TR (ENMAX 26) | 2018-05-24 08:00 | 2018-05-24 16:00 | N | N | replace retaining nuts on the HV bushing draw leads, parts in sub building, check reversing switch | Transformer
ALTALINK | 225L (67s Stirling - 225AL tap),67s226 (67s Stirling) | 2018-05-24 08:00 | 2018-05-24 13:00 | N | N | close open point 'A' | Line, Switch |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36) | 2018-05-24 08:00 | 2018-06-19 16:00 | N | N | sub medium voltage switchgear upgrade, transformer secondary to connect to new switchgear on return | Transformer
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2018-05-24 08:00 | 2018-05-25 18:00 | N | Y | HV SW MD maintenance, doble | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 37 (39s Bickerdike) | 2018-05-24 09:00 | 2018-05-24 12:30 | N | N | 39s37 W phase low in gas | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 85L (35s Rundle - 85L12) | 2018-05-24 10:00 | 2018-05-24 11:00 | N | Y | 85L needs to be de-energized as part of the MPLS upgrade at 35s | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 903L (17s Benalto - 320p Keephills),17s 8 (17s Benalto),17s 7 (17s Benalto),17s Benalto 240 kV North Bus 1,17s T3 (17s Benalto) | 2018-05-25 15:00 | 2018-05-29 16:00 | N | Y | 17s903N switch replacement | Line, Bus, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2018-05-26 06:00 | 2018-05-26 16:00 | N | N | disconnect switch repair | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2018-05-26 08:00 | 2018-05-26 16:00 | N | Y | HV breaker maintenance 7B138-7.82 | Line |  | HV breaker maintenance 7B138-7.82, SF6 gas sample 7B138-7.82 (originally scheduled Apr 22) | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 28s R1 (28s West Brooks),28s 44 (28s West Brooks) | 2018-05-26 11:00 | 2018-05-26 13:30 | N | Y | trip test required for bus protection addition | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 28s 41 (28s West Brooks) | 2018-05-26 13:30 | 2018-05-26 15:30 | N | Y | trip test required for bus protection addition | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 28s 8 (28s West Brooks) | 2018-05-26 15:30 | 2018-05-26 17:30 | N | Y | trip test required for bus protection addition | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36),36.5TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2018-05-27 05:00 | 2018-05-27 12:00 | N | N | spring substation washing and maintenance | Line, Transformer |  | Spring Substation Washing. Check reversing switch 36.2. Doble 36PT138-Z32. 36.2TR already out of service. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 484s T2 (484s Millar Western) | 2018-05-27 08:00 | 2018-05-30 17:00 | N | N | replace T2 metering | Transformer |  |  | For Information Only
ALTALINK | 304s T2 (304s Shell Limestone) | 2018-05-27 12:00 | 2018-05-29 17:30 | N | N | change 304s195, 304s295, 304s3, TX maintenance, wildlife cover-up installation | Transformer |  | Change 304s195, 304s295, 304s3, TX maintenance, wildlife cover-up installation | For Information Only
ALTALINK | 378s T1 (378s Shell Caroline),378s 152 (378s Shell Caroline),378s 452 (378s Shell Caroline),719L (378s Shell Caroline - 719L213) | 2018-05-27 15:00 | 2018-05-29 15:30 | N | N | tap changer filter install.PLC replacement and PLC trip testing of 378s752, 378s952 | Circuit Breaker, Line, Transformer |  | Complete the TX18598 Tap Changer filter install. PLC replacement and PLC Trip testing of 378s752, 378s952. Co-ordinated with Customer Shutdown. Commissioning of supervisory control to 378s15. AML to perform maintenance and adjust 378s7. | Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2018-05-27 22:00 | 2018-05-28 04:00 | N | N | 9th ave bridge replacement | Line |  |  | Pre-Condition
ATCO | 881s 702T (881s Sturgeon) | 2018-05-28 07:00 | 2018-05-29 17:00 | N | Y | maintenance. | Transformer |  | 881S Sturgeon 2 701T and 702T Maintenance: 702T Maintenance: Start 0700 on May 28 End 1700 on May 29 701T Maintenance: Start 1700 on May 29 End 1700 on May 31. | Restricts Generation
ALTALINK | 536s T1 (536s Brookfield) | 2018-05-28 07:00 | 2018-05-30 08:00 | N | N | fix oil leaks, doble, maintain 536s T1 | Transformer |  |  | For Information Only
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2018-05-28 07:00 | 2018-05-29 13:00 | N | N | insulator washing | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.2TR (ENMAX 27) | 2018-05-28 08:00 | 2018-06-01 16:00 | N | N | PRD installation and check reversing switch | Transformer |  | PRD installation. Check reversing switch | For Information Only
ENMAX | 47B138-BT3 (ENMAX 47) | 2018-05-28 08:00 | 2018-05-28 16:00 | N | N | repair breaker heater circuit | Circuit Breaker |  |  | For Information Only
Syncrude | UE_1 7204 (UE_1 Syncrude Plant 30-2),UE_1 7205 (UE_1 Syncrude Plant 30-2),UE_1 7209 (UE_1 Syncrude Plant 30-2) | 2018-05-28 08:00 | 2018-05-28 18:00 | N | Y | isolation switch 72-09 PM work | Circuit Breaker, Switch |  | Circuit Breaker 52-7204 and 52-7205 will be open and closed | Restricts Generation, For Information Only
ENMAX | 43.1TR (ENMAX 43) | 2018-05-28 08:00 | 2018-06-08 16:00 | N | N | doble test and various transformer testing and maintenance | Transformer |  | Doble test transformer. Secondary cable tests, check reversing switch (x2), gas relay testing, transformer maintenance | For Information Only
ALTALINK | 28s T2 (28s West Brooks),28s 55 (28s West Brooks),28s 81 (28s West Brooks),28S West Brooks 138kV Bus 2 | 2018-05-28 08:45 | 2018-05-31 17:45 | N | Y | CT wiring of T2, 28s55, 28s81 & trip tests for B protection addition | Bus, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2018-05-28 09:15 | 2018-06-08 17:45 | N | Y | component replacement | Line |  |  | 240 kV
ALTALINK | 412s T1 (412s Shell Eagle Creek) | 2018-05-28 10:00 | 2018-05-30 15:00 | N | N | doble and maintain T1 and VR1 | Transformer |  | Doble and maintain T1 and VR1. Co-ordinated with Customer Shutdown. | For Information Only
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2018-05-29 07:00 | 2018-05-31 18:30 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 510s 2852 (510s Sunnybrook) | 2018-05-29 07:00 | 2018-06-19 18:00 | N | Y | installing foundation for new 510s2952 and associated equipment | Circuit Breaker |  |  | For Information Only, 500 kV
EPCOR | 511s Victoria T5 (511s Victoria),CV5 (557s Castle Downs - 511s Victoria) | 2018-05-29 07:00 | 2018-06-08 17:00 | N | Y | doble/cable, manhole inspection | Line, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 747L (37s North Calder - 711L tap),37s 747W (37s North Calder) | 2018-05-29 07:30 | 2018-05-29 12:30 | N | N | create open point 'A' between Str 747L2 & 747L1C | Circuit Breaker, Line |  |  | Pre-Condition
ALC | ALS1 Air Liquide Scotford #1 | 2018-05-29 08:00 | 2018-06-03 16:00 | N | N | control system upgrade,ISD June 1, 2018 | Unit |  |  | For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2018-05-29 08:00 | 2018-05-29 16:00 | N | Y | SF6 gas sample 21B138-21.80 | Line |  |  | Over/Under Voltage, Contingency Requires Mitigation
BCH | 5L71 (Mica Creek - Nicola) | 2018-05-29 09:00 | 2018-06-15 17:00 | N | Y | annual plan request F19 - BC maintenance does not affect AB ATC | Line | BC Outage Peak RC COS: 1-00566458 AB Peak RC COS# : 1-00573903 (W-E), 1-00573904 (E-W) |  | Limits ATC, 500 kV
AESO, ALTALINK | 898L (37s North Calder - 92s Viscount),37s 898 (37s North Calder),37s 747W (37s North Calder),747L (37s North Calder - Open Point "A") | 2018-05-29 12:31 | 2018-06-01 08:00 | N | N | replacing burnt structure 1B | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2018-05-29 13:00 | 2018-05-29 19:00 | N | N | insulator washing on structures #2 & 4 and connect mobile substation at 172s | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 378s T1 (378s Shell Caroline),378s 152 (378s Shell Caroline),378s 452 (378s Shell Caroline) | 2018-05-29 15:30 | 2018-06-02 08:00 | N | N | tap changer filter install.PLC replacement and PLC trip testing of 378s752, 378s952 | Circuit Breaker, Transformer |  | Complete the TX18598 Tap Changer filter install. PLC replacement and PLC Trip testing of 378s752, 378s952. Co-ordinated with Customer Shutdown. Commissioning of supervisory control to 378s15. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ATCO | 881s 701T (881s Sturgeon) | 2018-05-29 17:00 | 2018-05-31 17:00 | N | Y | maintenance | Transformer |  | 881S Sturgeon 2 701T and 702T Maintenance: 702T Maintenance: Start 0700 on May 28 End 1700 on May 29 701T Maintenance: Start 1700 on May 29 End 1700 on May 31. | Restricts Generation
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2018-05-30 07:00 | 2018-05-31 18:00 | N | N | insulator washing on structures #28, 29, 60, 61, 62, 63, 64, 65 & 80 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 38s C1 (38s East Edmonton),38s 3052 ( 38s East Edmonton) | 2018-05-30 07:00 | 2018-05-30 11:00 | N | N | trip test from new 38s 138kV bus protection | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | Victoria V728 (Victoria) | 2018-05-30 07:00 | 2018-05-30 17:00 | N | N | doble | Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2018-05-30 08:00 | 2018-05-30 12:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ATCO | 843s 601T (843s Bigknife Creek),843s 301TD (843s Big Knife Creek) | 2018-05-30 08:00 | 2018-05-31 15:00 | N | N | repair broken insulator 301TD and sample station service | Switch, Transformer |  | Repair broken insulator 301TD and Sample Station Service | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2018-05-30 08:00 | 2018-05-30 12:00 | N | N | engineering measurements for NGR, check reversing switch | Transformer |  |  | For Information Only
ATCO | 732s 702 (732s Mitsue),732s 703 (732s Mitsue) | 2018-05-30 08:00 | 2018-06-04 16:00 | N | N | breaker replacement, new breaker fault clearing capability increased. ISD June 1, 2018 | Circuit Breaker |  |  | For Information Only
REDDEER | 209s T1 (209s Timberlands) | 2018-05-30 09:00 | 2018-05-31 15:30 | N | N | routing inspection | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2018-05-30 12:00 | 2018-05-31 12:00 | N | N | engineering measurements for NGR, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2018-05-30 12:01 | 2018-05-30 16:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 38s C2 (38s East Edmonton),38s 3152 (38s East Edmonton) | 2018-05-30 13:00 | 2018-05-30 17:00 | N | N | trip test from new 38s 138kV bus protection | Circuit Breaker, Shunts |  |  | For Information Only
SUNCOR | 635EDD-1000 635-752-111 (635EDD-1000) | 2018-05-31 08:00 | 2018-06-01 17:00 | N | N | change the GE brick merging unit MU-1 | Circuit Breaker
ENMAX | 2.4TR (ENMAX 2) | 2018-05-31 08:00 | 2018-06-01 16:00 | N | N | tapchanger inspection, check reversing switch, oil sample MT, bushings,TC | Transformer |  |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703BL tap) | 2018-05-31 08:00 | 2018-05-31 13:15 | N | N | close open Point 'A' between Str 31-32 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 865L (216s Knightsbridge - 38s East Edmonton),38s 865N (38s East Edmonton) | 2018-05-31 08:00 | 2018-05-31 12:00 | N | N | trip test from new 38s 138kV bus 1 protection | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (575s Sundre - 378s Shell Caroline) | 2018-05-31 08:30 | 2018-05-31 17:00 | N | N | 719L needs to be de-energized as part of the radio link repair upgrade @ 378s & 9433R. Linked to order # 259459 | Line
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2018-05-31 08:30 | 2018-05-31 17:00 | N | Y | repair hot spot on 17s50 and maintain 17s717W | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
SUNCOR | 29EDD-5 29Edd-5,29PL6-7 (836s Steepbank - 29EDD-5 29Edd-5) | 2018-05-31 09:00 | 2018-06-21 18:00 | N | Y | 5 year maintenance | Line, Station |  | Perform the 5 year mtce on 29PT7 & 29PL6-7 | Restricts Generation
Saskpower | Sask Power S1C line | 2018-05-31 09:00 | 2018-05-31 16:00 | N | Y | removal of S1C connection to SW808LM and connect to SW812LM | Line |  |  | Limits ATC
ENMAX | 38.2TR (ENMAX 38) | 2018-05-31 10:00 | 2018-06-15 13:00 | N | N | panel replacement | Transformer |  |  | For Information Only
ALTALINK | 531s T1 (531s Shell Schrader Creek) | 2018-05-31 10:00 | 2018-06-05 15:00 | N | N | doble and maintain T1 and VR1 | Transformer |  |  | For Information Only
ALTALINK | 256S Harmattan | 2018-05-31 10:00 | 2018-05-31 16:30 | N | Y | 228x breaker maintenance 25kV R1 vacuum breaker | Station |  |  | Restricts Generation
ALTALINK | 28s 52 (28s West Brooks) | 2018-05-31 12:30 | 2018-05-31 15:00 | N | Y | trip test required for bus protection addition | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAXGPI | 134s Taber Wind Farm RTU/SCADA | 2018-05-31 13:00 | 2018-05-31 15:00 | N | N | upgrade server hardware | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 28s 2 (28s West Brooks) | 2018-05-31 15:00 | 2018-05-31 17:00 | N | Y | trip test required for bus protection addition | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 172s T4 (172s Sherritt Gordon) | 2018-06-01 07:30 | 2018-06-01 17:30 | N | N | connect mobile substation to T4 bus & Isolate T4 low side | Transformer |  |  | For Information Only
ENMAX | ENMAX 5 | 2018-06-01 08:00 | 2018-06-01 16:00 | N | N | doble test 138 kV bus PTs | Station |  |  | For Information Only
ATCO | 7L81 RAS | 2018-06-01 08:00 | 2018-06-07 16:00 | N | N | ISD June 4, 2018 | RAS |  |  | For Information Only
ALTALINK, AESO | 37s 747W (37s North Calder),747L (37s North Calder - Open Point "A") | 2018-06-01 08:01 | 2018-06-01 13:00 | N | N | closing open point 'A' between Str 747L2 & 747L1C | Circuit Breaker, Line |  |  | Pre-Condition
Saskpower | Sask Power S1C line | 2018-06-01 09:00 | 2018-06-01 16:30 | N | Y | removal of S1C connection to SW808LM and connect to SW812LM | Line |  |  | Limits ATC
ATCO | 7L81 (FNG Fort Nelson - 791s Rainbow Lake),791s 702 (791s Rainbow Lake) | 2018-06-02 08:00 | 2018-06-04 17:00 | N | Y | install new 7L81 RASA & RASB | Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 133S Stelco Edmonton | 2018-06-02 09:00 | 2018-06-05 17:00 | N | N | AltaSteel request for isolation and grounding | Station |  |  | For Information Only
ALTALINK | 378s T2 (378s Shell Caroline) | 2018-06-02 17:00 | 2018-06-08 08:00 | N | Y | PLC replacement and PLC trip testing of 378s852 & 378s952. | Transformer |  |  | Restricts Generation
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft W721 (Woodcroft) | 2018-06-04 07:00 | 2018-06-29 17:00 | N | N | breaker replacement | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T3 (987s Clover Bar) | 2018-06-04 07:00 | 2018-06-08 17:00 | N | Y | doble | Transformer |  |  | 240 kV
ENMAX | 28.2TR (ENMAX 28) | 2018-06-04 08:00 | 2018-06-05 16:00 | N | N | inspection of tapchanger, reversing switch and transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 39.4TR (ENMAX 39) | 2018-06-04 08:00 | 2018-06-08 16:00 | N | N | panel replacement on 25kV feeders | Transformer |  |  | For Information Only
SUNCOR | 635PT-1036 (635EDD-1001) | 2018-06-04 08:00 | 2018-06-06 17:00 | N | N | transformer oil minor leak investigation | Transformer
Syncrude | Mildred_335 (Syncrude Mildred Lake),Mildred T3 (Syncrude Mildred Lake) | 2018-06-04 08:00 | 2018-06-10 18:00 | N | Y | transformer inspection/ oil leak repair | Transformer, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2018-06-04 08:00 | 2018-06-06 16:00 | N | N | HV breaker maintenance HLR 31B138-31.84. doble 31B138-31.84, 32B138-31.84-CT | Line |  |  | For Information Only
ATCO | 7L81 RAS | 2018-06-04 08:00 | 2018-07-24 16:00 | N | N | disable RAS A/B tripping | RAS |  |  | For Information Only
ATCO | 722s 702T (722s Crystal Lake) | 2018-06-04 08:00 | 2018-09-26 17:00 | N | N | real time forced outage | Transformer |  | REAL TIME GOI | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2018-06-04 08:00 | 2018-06-13 16:00 | N | N | replace transformer bushings H2, H3 | Transformer |  |  | For Information Only
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2018-06-04 08:00 | 2018-06-05 17:00 | N | N | changing cross-arms on 7L53 | Line |  | CHANGING CROSS-ARMS ON 7L53 | Pre-Condition, Overload, Contingency Requires Mitigation, Impacts RAS
Saskpower | Sask Power S1C line | 2018-06-04 09:00 | 2018-06-04 16:30 | N | Y | removal of S1C connection to SW808LM and connect to SW812LM | Line |  |  | Limits ATC
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt),172s 709X (172s Sherrit) | 2018-06-04 09:00 | 2018-06-04 11:00 | N | N | CT circuit work as part of bus differential protection replacement | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2018-06-04 09:15 | 2018-06-07 17:45 | N | Y | replace 'A' protection | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 77s T1 (77s Sagitawah),77s 51 (77s Sagitawah),77s 252 (77s Sagitawah),77s 26 (77s Sagitawah),77s 14 (77s Sagitawah),77s 352 (77s Sagitawah),77s Sagitawah 138 kV West Bus,77s Sagitawah 240 kV West Bus | 2018-06-04 09:30 | 2018-06-07 17:00 | N | Y | Protection upgrade | Transformer, Bus, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 726L (37s North Calder - 71s Lamoureux),71s 252 (71s Lamoureux),71s 352 (71s Lamoureux) | 2018-06-04 09:30 | 2018-06-07 16:30 | N | N | replace PT's | Line, Circuit Breaker |  |  | Overload
ALTALINK | 172s T1 (172s Sherritt Gordon) | 2018-06-04 09:30 | 2018-06-04 11:30 | N | N | CT circuit work | Transformer |  | CT circuit work as part of Bus Differential protection replacement. | For Information Only
ENMAX | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington),162s 2GSU-XF-0002 (162s Beddington) | 2018-06-04 10:00 | 2018-06-11 17:00 | N | Y | maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 163s 1352 (163s Amoco Empress) | 2018-06-04 10:00 | 2018-06-04 16:00 | N | Y | urgent trouble corrective: 240kV minimum oil breaker needs to be topped up with N2, having a low N2 level will affect its interrupting capability | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 902L (19s Wabamun - 310p Sundance),905L (19s Wabamun - 37s North Calder),19s T10 (19s Wabamun),19S Wabamun 240kV Bus B,19S Wabamun 240kV Bus A,19S Wabamun 240kV Transfer Bus | 2018-06-04 10:30 | 2018-06-14 19:00 | N | Y | replace 902L post insulators and 19s52 switch | Line, Transformer, Bus |  | replace 902L post insulators and 19s52 Switch. Entire 240kV Buses outage required due to proximately clearance etc... | 240 kV, Over/Under Voltage
AESO-SC | CROW | 2018-06-04 11:00 | 2018-06-04 12:00 | N | N | migration | SCInternal |  |  | For Information Only
ALTALINK | 489s T2 (489s Petro Canada Brazeau River) | 2018-06-04 12:30 | 2018-06-07 16:00 | N | N | transformer maintenance | Transformer |  | 489sT2 doble TX 18559 LTC FPE/ASEA 138/4, ADD: 489sT2 maint TX 18559 LTC FPE/ASEA 138/4, 489s T2 Moisture in temp gauge 2, 489sT2 LTC 1" Conservator Valve Leak 90241462, 489s T2 MT 2" Bleed Leaking, 489sT2 MT Conservator Moisture in Gauge, motor/man sw, 489s photo cell not working | For Information Only
ALTALINK | 1053L (132s Ware Junction - 324s Cassils),324s 1152 (324s Cassils),324s 1052 (324s Cassils) | 2018-06-04 13:00 | 2018-06-07 17:00 | N | Y | SCADA system upgrade | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 172s T2 (172s Sherritt Gordon),172s T3 (172s Sherritt Gordon),172s T4 (172s Sherritt Gordon) | 2018-06-04 16:00 | 2018-06-09 19:00 | N | N | replace insulators, replace 172s11, replace 172s24, T4 maintenance, replace T3 A protection | Transformer |  | Replace insulators, replace 172s11, replace 172s24, T4 maintenance, replace T3 A protection | Overload, Firm Load Loss, Creates Radial Feeds
AESO-SC | ASP | 2018-06-04 16:30 | 2018-06-04 17:30 | N | N | moving the ASP application from SDC to PDC | SCInternal |  |  | For Information Only
ALTALINK | 205s T1 (205s Castle Rock Ridge) | 2018-06-05 07:00 | 2018-06-06 12:00 | N | N | real time customer request | Transformer
ALTALINK | 13s T2 (13s Deerland),13s Deerland 138kV Bus 2,13s Deerland 240kV Bus 2 | 2018-06-05 07:15 | 2018-06-05 18:15 | N | Y | replace O/C protections for T2 | Bus, Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 151s T1 (151s Strathmore) | 2018-06-05 08:00 | 2018-06-07 18:00 | N | N | switch replacement | Transformer |  | Replace 151s6, 151s7, 151s8, 151s10 Switches Like for Like | For Information Only
ALTALINK | 912L (63s Red Deer - 766s Nevis) | 2018-06-05 08:00 | 2018-06-05 20:00 | N | Y | de-enrgized for double TPR for both A & B replacement-outage | Line |  | De-enrgized for double TPR for Both A & B replacement-outage. In conjunction with work @ 9766R to move MPLS and Quantar mobile from old building to new building at ATCO Nevis. Commission and put into service new Aviat radio to replace existing Constellation radio. Linked to order # 259678. | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 42s 80 (42s Sarcee) | 2018-06-05 13:30 | 2018-06-05 17:30 | N | N | install 138kV pollution monitor | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 284S Nose Creek | 2018-06-06 06:00 | 2018-06-07 17:00 | N | N | T1 doble maintenance and low side LA's | Station |  |  | For Information Only
CENOVUS | 539s PCB_9202 (539s Sunday Creek),539s PCB_9203 (539s Sunday Creek),539s 9201T (539s Sunday Creek) | 2018-06-06 07:00 | 2018-06-13 18:00 | N | Y | insulator testing | Circuit Breaker, Transformer |  | Removing 539s CT-9206 from service | 240 kV
ALTALINK | 13s 852 (13s Deerland) | 2018-06-06 07:30 | 2018-06-06 12:30 | N | N | required trip test related to O/C protections for T2 replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
CMH | 15L (MHS7 Brier Park - MHS9 Power Plant) | 2018-06-06 08:00 | 2018-06-24 16:00 | N | N | ISD: June 22, 2018 | Line
ENMAX | 6.4TR (ENMAX 6) | 2018-06-06 08:00 | 2018-06-07 16:00 | N | N | tap changer inspection | Transformer |  |  | For Information Only
CMH | MHS9 (Power Plant),MHS9 T11 (Power Plant) | 2018-06-06 08:00 | 2018-06-24 16:00 | N | N | ISD: June 22, 2018 | Transformer, Station
ALTALINK | 515S Fedpipe Judy Creek | 2018-06-06 10:00 | 2018-06-06 16:00 | N | N | customer work | Station |  |  | For Information Only
ALTALINK | 13s 452 (13s Deerland) | 2018-06-06 12:30 | 2018-06-06 18:00 | N | N | required trip test related to O/C protections for T2 replacement | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 13s 1452 (13s Deerland) | 2018-06-07 07:30 | 2018-06-07 12:30 | N | Y | required trip test related to O/C protections for T2 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2018-06-07 08:00 | 2018-06-07 16:00 | N | N | HV breaker maintenance 40B138-40.81, SF6 gas sample 40B138-40.81 | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 635PT-1039 (635EDD-1001) | 2018-06-07 08:00 | 2018-06-09 17:00 | N | N | transformer oil residue investigation | Transformer
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2018-06-07 08:00 | 2018-12-17 13:00 | N | N | 1.80L/1.81L cable replacement project | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 732s 703 (732s Mitsue) | 2018-06-07 12:01 | 2018-06-19 08:00 | N | N | breaker, CT and PT replacement | Circuit Breaker |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT STAGE A: April 16-24 GOI 2-43738A Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 Completed STAGE B: April 24-May 5 GOI 2-43738B Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 Present STAGE C: May 5 GOI 2-43738C Expand Outage to include 7L49, 7L23, 901T, 7L31 Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2, 706A, 7L31D1 STAGE D: End of May 5  May 16 GOI 2-43738D Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 STAGE E: (Vendors Tentative delivery Date of CTs) May 16  May 18 GOI 2-43738E Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 2nd Expansion due to late install of 2 CTs on 703 STAGE F: May 18 - June 7 GOI 2-43738F Outage on 702 &703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue New updated Work plan for 732S Mitsue Current - June 7 12:00 GOI 2-43738D Outage on 702 & 703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue Current June 7 12:01  June 19 08:00 GOI 2-43738E Shrink Down to 703 Breaker (Waiting for CT delivery from Vendor) Isolation points: 703A & 703B @ 732S (Ring Bus open) June 19 08:01  June 22 17:00 Final expansion of permit to install the CTs on Breaker 703 GOI 2-43738F Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 | Contingency Requires Mitigation
ALTALINK | 13s 1752 (13s Deerland) | 2018-06-07 12:30 | 2018-06-07 18:00 | N | Y | required trip test related to O/C protections for T2 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2018-06-08 07:00 | 2018-06-08 17:00 | N | Y | doble | Line |  |  | 240 kV
ALTALINK | 394s T2 (394s Empress),394s T4 (394s Empress),668L (394s Empress - 562s Cypress),394s Empress 138kV Bus 2,394s 952 (394s Empress) | 2018-06-08 08:00 | 2018-06-08 14:00 | N | N | investigate why the MOD-394s32 indicates open when closed | Bus, Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2018-06-08 09:30 | 2018-06-08 15:00 | N | N | install mobile sub at 804s and install risers | Line |  | 750S Mobile Sub installation at 804S Wintering Hills Establish a GOI on the 144kV bus between 701A and 700D1 to install risers for 750S. Also connect 750S 25kV leads using 599TD as a GOI point. Once 750S is connected, release GOI and energize 750S to soak over the weekend. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L72 (Mica Creek - Nicola) | 2018-06-08 16:00 | 2018-06-08 17:00 | N | Y | conductor spacer replacement | Line | BC Peak RC COS#: 1-00573583 AB Peak RC COS# : 1-00570234 (W>E), 1-00570236 (E>W) | Annual Plan Request F19 - PLACEHOLDER for Conductor Spacer Replacement | Limits ATC, 500 kV
ALTALINK | 396s T3 (396s Pincher Creek) | 2018-06-09 07:00 | 2018-06-10 17:00 | N | N | doble, repair leak, possibly replace H2 bushing, bird cover | Transformer |  | Doble, repair leak, possibly replace H2 bushing, bird cover on TX and U/G cables | For Information Only
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2018-06-09 08:00 | 2018-06-09 16:00 | N | N | HV breaker maintenance | Line |  | HV breaker maintenance 31B138-24.81L. SF6 gas sample 31B138-24.81. Doble 24B138-24.81 Repair or Replace Center Phase Mech Cover [AVANTIS] 24B13-24.81 | Pre-Condition
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia),89s 908W (89s Ellerslie),816s PDS13 (816s Petrolia) | 2018-06-09 09:00 | 2018-06-09 17:00 | N | Y | doble | Switch, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 719L (575s Sundre - 378s Shell Caroline),870L (262s Rocky Mountain House - 263s Strachan) | 2018-06-09 10:00 | 2018-06-09 11:00 | N | Y | 719L needs to be de-energized as part of the radio link repair upgrade at 378s & 9433R,870L needs to be de-energized as part of the radio link repair upgrade at 378s & 9433R | Line |  | 719L needs to be de-energized as part of the radio link repair upgrade @ 378s & 9433R. Linked to order # 260324. 870L needs to be de-energized as part of the radio link repair upgrade @ 378s & 9433R. Linked to order # 260324. | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2018-06-09 18:48 | 2018-06-17 18:00 | N | N | forced out | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2018-06-09 18:57 | 2018-06-15 17:00 | N | N | forced out | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s Cloverbar 72kV Bus 2 | 2018-06-10 07:00 | 2018-06-10 17:00 | N | N | doble | Bus |  |  | Overload, Contingency Requires Mitigation
Saskpower | SASK POWER P1C | 2018-06-11 07:00 | 2018-06-21 16:30 | N | N | replace insulators | Line |  |  | Limits ATC
ALTALINK | 38s 75 (38s East Edmonton) | 2018-06-11 07:00 | 2018-06-20 17:00 | N | N | add new 38s4252 breaker | Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 172s T4 (172s Sherritt Gordon) | 2018-06-11 07:30 | 2018-06-14 17:30 | N | N | disconnect mobile substation | Transformer |  |  | For Information Only
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2018-06-11 08:00 | 2018-06-13 12:00 | N | N | changing cross arm on 7L53 | Line |  | CHANGING CROSS-ARMS ON 7L53 | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 26.81L (ENMAX 32 - ENMAX 26) | 2018-06-11 08:00 | 2018-06-25 16:00 | N | N | LRT project | Line |  | Green Line LRT Project | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.2TR (ENMAX 43) | 2018-06-11 08:00 | 2018-06-22 16:00 | N | N | Doble test transformer and check reversing switch (x2), gas relay testing | Transformer |  |  | For Information Only
SUNCOR | 635PT-1037 (635EDD-1001) | 2018-06-11 08:00 | 2018-06-13 17:00 | N | N | transformer oil leak investigation | Transformer |  |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 33 B138-33.83 (ENMAX 33),ENMAX 41 B138-33.83 (ENMAX41) | 2018-06-11 08:00 | 2018-06-14 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | HV breaker maintenance. Sprecher 41B138-33.83. Investigate gas leak 33B138-33.83 | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.2TR (ENMAX 31) | 2018-06-11 08:00 | 2018-06-14 16:00 | N | N | tapchanger inspection and oil sample | Transformer |  |  | For Information Only
ALTALINK | 431s T1 (431s Hussar) | 2018-06-11 08:30 | 2018-06-15 09:30 | N | N | replace failed u/g cables | Transformer |  |  | For Information Only
ATCO | 804s 701T (804s Wintering Hills) | 2018-06-11 09:00 | 2018-07-06 16:00 | N | N | oil reclamation | Transformer |  | Oil reclamation on 701T and 501VR - all 25kv load to be fed from 750S mobile substation. | For Information Only
ALTALINK | 103s 893 (103s Goose Lake) | 2018-06-11 09:30 | 2018-06-11 12:30 | N | N | create open point "A" | Switch |  | create open point "A" (Str5-6) | For Information Only
ALTALINK | 77s T2 (77s Sagitawah),77s Sagitawah 138 kV East Bus,77s Sagitawah 240 kV East Bus | 2018-06-11 09:30 | 2018-06-13 14:00 | N | Y | protection upgrade | Transformer, Bus |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 151s 39 (151s Strathmore) | 2018-06-11 10:00 | 2018-06-11 17:00 | N | N | complete functionals from the breaker maintenance switches and the 2010L feeder protection | Circuit Breaker |  |  | For Information Only
ALTALINK | 522s T2 (522s Cooking Lake) | 2018-06-11 10:00 | 2018-06-13 15:00 | N | N | wildlife cover-up installation on T2 secondary outdoor energized parts | Transformer |  |  | For Information Only
ALTALINK | 396s T2 (396s Pincher Creek) | 2018-06-11 11:00 | 2018-06-12 16:30 | N | N | install bird cover-up, Doble test, repair leak | Transformer |  |  | For Information Only
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2018-06-11 11:00 | 2018-06-14 16:00 | N | N | 7L40 Xarm/insulator replacement | Line |  | 7L40 Xarm/Insulator Replacement | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 396s VR1 (396s Pincher Creek) | 2018-06-11 11:00 | 2018-06-11 17:30 | N | N | install bird cover-up | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 1139L (367s Harry Smith - 816s Petrolia) | 2018-06-11 11:08 | 2018-06-15 17:00 | N | Y | A & B protection forced outage | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 893L (103s Goose Lake - 893BL tap) | 2018-06-11 12:00 | 2018-06-28 08:30 | N | N | structure maintenance | Line |  |  | For Information Only
ALTALINK | 935L (324s Cassils - 356s Milo) | 2018-06-11 13:00 | 2018-06-14 17:00 | N | Y | SCADA system upgrade | Line |  |  | 240 kV, Pre-Condition
EPCOR | 72CK12 (987s Clover Bar - Kennedale),Kennedale K724 (Kennedale),Kennedale K723 (Kennedale) | 2018-06-12 07:00 | 2018-06-12 17:00 | N | N | doble | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2018-06-12 07:15 | 2018-06-15 17:45 | N | N | trouble corrective | Line |  | Trouble Corrective; Components 164L (Str's 5A,17A,18A,72) X-Arms and Sway Braces | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
CMH, Medicine Hat | 20L (MH69S-6 Riverview - MH69S-3 South Ridge),MH69s6 MH69-T63 (MH69s6 Riverview) | 2018-06-12 08:00 | 2018-06-12 16:00 | N | N | emergency repair potential oil leak | Line, Transformer
ATCO | 6L96 (744s Federated Pipelines - 743s Sarah Lake),6L96 (735s Swan River - 6L96 Tap) | 2018-06-12 08:00 | 2018-06-12 16:30 | N | N | 6L96 salvage 3 way gang switch, remove 3 way gang switch at Federated pipe | Line |  | 6L96 salvage 3 way gang switch remove 3 way gang switch at Federated pipe | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 5.5TR (ENMAX 5) | 2018-06-12 08:00 | 2018-06-13 16:00 | N | N | repair hotspot on H1 and H3 bushings, check reversing switch, oil sampling MT, TC | Transformer |  | repair hotspot on H1 and H3 bushings, check reversing switch, oil sampling MT, TC | For Information Only
ALTALINK | 216s T1 (216s Knightsbridge) | 2018-06-12 08:00 | 2018-06-12 20:00 | N | N | Enbridge request for T1 isolation | Transformer |  |  | For Information Only
Syncrude | Aurora 223 (Aurora),Aurora 213 (Aurora),Aurora T-11 | 2018-06-12 08:00 | 2018-06-12 18:00 | N | Y | replace metering PT | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 394s T3 (394s Empress) | 2018-06-12 08:30 | 2018-06-23 17:00 | N | N | maintain, doble, fix dc ground, oil sample, SFRA and oil reclaim on T3 | Transformer |  |  | For Information Only
ATCO | 715s 701T (715s Leming Lake) | 2018-06-12 09:00 | 2018-06-12 16:30 | N | N | repair leak on transformer | Transformer |  | Repair Leak on Transformer | For Information Only
ATCO | 903s 701T (903s Loyalist) | 2018-06-12 09:00 | 2018-06-13 17:00 | N | N | bird proof 4.16kV bus work | Transformer |  | 903S 701T OOS Bird Proof 4.16kV Bus Work at 903S Loyalist | For Information Only
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2018-06-12 09:00 | 2018-06-12 12:00 | N | N | high load move | Line |  | High Load Move | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 368s C1 (368s Burdett),368s 35 (368s Burdett) | 2018-06-12 09:30 | 2018-06-12 17:30 | N | N | gravel addition in fenced cap bank area required for safety | Circuit Breaker, Shunts |  |  | Pre-Condition
Saskpower | SaskPower A1R | 2018-06-12 10:00 | 2018-06-12 14:00 | N | Y | building move | Line |  |  | Limits ATC
EPCOR | Kennedale K722 (Kennedale) | 2018-06-13 07:00 | 2018-06-13 17:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
ATCO | 844s 701T (844s AEC Mill),844s 702T (844s AEC Mill) | 2018-06-13 07:00 | 2018-06-13 19:00 | N | Y | maintenance | Transformer |  | Slave Lake Pulp (SLP AKA AEC Mill) is planning to have a complete power outage to their plant, Must de-energize 701T and 702T to open 401TD and 402TD. Contact SLP Control room to issue permit (780-849-7748) | Restricts Generation
ATCO | 844s 701T (844s AEC Mill) | 2018-06-13 07:00 | 2018-06-14 17:00 | N | N | maintenance | Transformer |  | Maintenance | For Information Only
ALTALINK | 763L (28s West Brooks - 763L257A) | 2018-06-13 07:45 | 2018-06-13 14:45 | N | N | high load move | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s6 (33s Spray) | 2018-06-13 08:00 | 2018-06-13 16:00 | N | Y | maintneance | Switch |  |  | Restricts Generation
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2018-06-13 08:00 | 2018-06-13 17:00 | N | N | 9286 radio work and protection work | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 739s 701T (739s Edith Lake),6L11 (739s Edith Lake - 854s Swan Dive) | 2018-06-13 08:00 | 2018-06-13 20:48 | N | N | forced outage | Line, Transformer |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 715s 702T (715s Leming Lake) | 2018-06-13 09:00 | 2018-06-14 16:00 | N | N | bushing change, replace H3 bushing and test | Transformer |  | 715S LEMING 702T BUSHING CHANGE replace H3 Bushing and test
NOVACORP | 330s 330-PTR-01 (330s Nova Corp),330s 330-PTR-03 (330s Nova Corp) | 2018-06-13 10:00 | 2018-06-13 12:00 | N | N | deluge testing | Transformer |  |  | For Information Only
EPCOR | 72CK13 (987s Clover Bar - Kennedale),Kennedale K721 (Kennedale) | 2018-06-14 07:00 | 2018-06-14 17:00 | N | N | maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss
SUNCOR | 635PL9-1000 (2005s Secord - 635EDD-1000),635PT-1000 (635EDD-1000) | 2018-06-14 08:00 | 2018-06-15 17:00 | N | Y | troubleshoot the transformer alarms | Line, Transformer |  | Troubleshoot the temperature sensors and resolve the transformer winding/oil high temperature alarms | 240 kV, Firm Load Loss, Creates Radial Feeds
IMPERIALOIL | 9900S Kearl | 2018-06-14 09:00 | 2018-06-14 17:00 | N | N | program new distance settings | Station
ALTALINK | 368s C2 (368s Burdett),368s 44 (368s Burdett) | 2018-06-14 09:30 | 2018-06-14 17:30 | N | N | gravel addition in fenced cap bank area | Circuit Breaker, Shunts |  |  | Over/Under Voltage, Firm Load Loss, For Information Only
ENMAX | 1.5TR (ENMAX 1) | 2018-06-15 08:00 | 2018-06-15 16:00 | N | N | oil sample | Transformer |  | Oil Sample TR after 3 months in service. | For Information Only
ENMAX | ENMAX 11 B138-11.81 (ENMAX 11) | 2018-06-15 08:00 | 2018-06-15 16:00 | N | N | HV breaker maintenance | Circuit Breaker |  | HV breaker maintenance 11B138-11.81 | For Information Only
SUNCOR | 635PT-1038 (635EDD-1001) | 2018-06-15 08:00 | 2018-06-17 17:00 | N | N | transformer rad top valve investigation | Transformer |  |  | For Information Only
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2018-06-15 08:00 | 2018-06-15 14:00 | N | Y | urgent conductor work | Line | AB Peak RC COS# : 1-00576424 (W-E), 1-00576428 (E-W) Peak RC COS Outage # (BCH outage): 1-00574139 |  | Limits ATC
ALTALINK | 431s T2 (431s Hussar) | 2018-06-15 11:30 | 2018-06-25 12:00 | N | N | replace u/g cables | Transformer |  |  | For Information Only
EPCOR | 1055L (816s Petrolia - 629s Argyll Transfer Station) | 2018-06-16 05:30 | 2018-06-17 18:00 | N | Y | washing program | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2018-06-16 08:00 | 2018-06-17 16:00 | N | N | breaker maintenance | Line |  | HV breaker maintenance HLR 22B138-22.81. I&R FU1 Fuse Faling Out of Place [AVANTIS]. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 761L (38s East Edmonton - 189s Celanese),38s 731E (38s East Edmonton),38s 761N (38s East Edmonton),731L (420s Broadmoor - 731L tap) | 2018-06-16 10:00 | 2018-06-16 13:00 | N | N | trip fail test from new breaker | Circuit Breaker, Line |  | Trip test from 38s4252 breaker fail | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 215L (38s East Edmonton - 286s Yasa),38s 215N (38s East Edmonton),38s62 (38s East Edmonton) | 2018-06-16 13:01 | 2018-06-16 16:00 | N | N | trip fail test from new breaker | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
CMH | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2018-06-18 07:00 | 2018-06-18 19:00 | N | N | replace broken pole damaged by storm | Line |  |  | For Information Only
EPCOR | Strathcona T1 (Strathcona),72RS5 (Rossdale - Strathcona) | 2018-06-18 07:00 | 2018-08-27 07:29 | N | N | transformer replacement | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker 2401 (Poundmaker) | 2018-06-18 07:00 | 2018-06-18 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 199L (268s Whitecourt - 199L187B) | 2018-06-18 07:00 | 2018-06-19 17:30 | N | N | Fortis will be removing their U/B between structures 372 & 397/21 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2018-06-18 07:30 | 2018-06-18 17:30 | N | N | connect mobile substation to T2 bus, isolate low side | Transformer |  |  | For Information Only
ALTALINK | 671L (58s Edson - 39s Bickerdike) | 2018-06-18 08:00 | 2018-06-18 13:00 | N | N | high load move | Line |  |  | Pre-Condition
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2018-06-18 08:00 | 2018-06-21 16:00 | N | N | breaker maintenance, doble, sheath test and DGA sample | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2018-06-18 08:00 | 2018-06-21 17:00 | N | N | changing cross arms | Line |  | CHANGING CROSS-ARMS ON 7L53 BONNYVILLE TO LINDBERGH | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.4TR (ENMAX 14) | 2018-06-18 08:00 | 2018-06-19 16:00 | N | N | tapchanger inspection, check reversing switch, top up oil level | Transformer |  |  | For Information Only
Syncrude | Aurora T1 | 2018-06-18 08:00 | 2018-07-05 20:00 | N | Y | 5 year maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1C (ENMAX 38),ENMAX 38 138-38.CAP (ENMAX 38) | 2018-06-18 08:00 | 2018-06-18 16:00 | N | N | unshort BD CTs, for transformer panel replacement | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ATCO | 846s 702T (846s Grand Centre) | 2018-06-18 08:00 | 2018-06-22 15:00 | N | N | leak repair | Transformer |  | 846S 702T Leak Monitor Transformer Leak Repair 702T will be OOS for duration of the work. 701T will carry all load. | For Information Only
ALTALINK | 514BL (322s Cowley Ridge Wind Plant - 514L tap),514L (396s Pincher Creek - 514BL tap),514L (513s Lundbreck - 514L198) | 2018-06-18 08:30 | 2018-06-19 18:00 | N | Y | Place new 396s514N breaker and install LA's | Line |  |  | Restricts Generation, Firm Load Loss
ENMAX | 38PT138-Z5 (ENMAX 38) | 2018-06-18 09:00 | 2018-06-18 13:00 | N | N | 38.2TR panel construction. | Terminal Equipment |  |  | For Information Only
ALTALINK | 233s T1 (233s Beamer) | 2018-06-18 09:00 | 2018-06-21 17:00 | N | N | customer deficiency clean-up after project | Transformer |  |  | For Information Only
ALTALINK | 542s T1 (542s Ervick) | 2018-06-18 09:30 | 2018-06-22 14:00 | N | N | switch replacement 542s3 & 542s4; 25kV metering upgrade | Transformer |  |  | For Information Only
ATCO | 743s 702T (743s Sarah Lake),7L230 (7L230 tap - 743s Sarah Lake),7L67 (824s Fieldgate - 743s Sarah Lake) | 2018-06-18 10:00 | 2018-06-19 17:00 | N | Y | replace insulators, switch maintenance | Line, Transformer |  | Replace insulators, Switch maintenance | Firm Load Loss, Creates Radial Feeds
ATCO | 959S SVC (959s Lanfine) | 2018-06-18 10:00 | 2018-06-22 14:00 | N | Y | warranty repair work | Shunts |  | SVC warranty repair work- GE Repairs/Modifications, SVC will not be available for duration of outage | For Information Only
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2018-06-18 10:00 | 2018-06-21 14:00 | N | N | 7L40 Xarm/insulator replacement | Line |  | 7L40 Xarm/Insulator Replacement | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 163s T1 (163s Amoco Empress) | 2018-06-18 10:30 | 2018-06-28 08:30 | N | Y | replace T1 A/B protections | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 1002L (275s Jenner - 163s Amoco Empress) | 2018-06-18 10:30 | 2018-06-21 13:00 | N | N | replace 2 Phases of 163s23 PT | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 396s T1 (396s Pincher Creek) | 2018-06-18 11:00 | 2018-06-20 17:30 | N | N | doble, TC maintenance, repair IDD | Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 1052L (28s West Brooks - 324s Cassils),324s 1952 (324s Cassils),324s 2052 (324s Cassils) | 2018-06-18 13:00 | 2018-06-21 17:00 | N | Y | SCADA system upgrade | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 172s T1 (172s Sherritt Gordon),172s T2 (172s Sherritt Gordon),709L (54s Fort Saskatchewan - 172s Sherritt) | 2018-06-19 07:00 | 2018-06-21 17:00 | N | N | replace insulators, switch maintenance | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker 2402 (Poundmaker) | 2018-06-19 07:00 | 2018-06-19 17:00 | N | Y | Maint | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | ENMAX 37 | 2018-06-19 08:00 | 2018-06-19 16:00 | N | N | 37.1 TR measure protection/revenue metering CTs | Station
ALTALINK | 283s T1 (283s Violet Grove) | 2018-06-19 08:00 | 2018-06-19 18:00 | N | N | to repair 283s483 | Transformer |  |  | For Information Only
ATCO | 732s 501R (732s Mitsue),732s 901T (732s Mitsue),7L49 (732s Mitsue - 729s Otauwau),732s 703 (732s Mitsue),7L23 (732s Mitsue - 858s Narrows Creek) | 2018-06-19 08:01 | 2018-06-23 17:00 | N | Y | breaker, CT and PT replacement | Circuit Breaker, Line, Transformer, Shunts |  | Replace breaker 702 and CT's and Breaker 703 and CT's, and 701PT & 702PT Current - June 7 12:00 GOI 2-43738D Outage on 702 & 703, 7L49 Isolation points: 702A, 703A, 7L49D1 @732S Mitsue June 7 12:01 - June 19 08:00 GOI 2-43738E Shrink Down to 703 Breaker (Waiting for CT delivery from Vendor) Isolation points: 703A & 703B @ 732S (Ring Bus open) June 19 08:01  June 23 17:00 Final expansion of permit to install the CT's on Breaker 703 GOI 2-43738F Expand Outage to include 7L49, 7L23, 901T Isolation points: 901TD, 501SS, 500PT1X1, 701B, 707B, 7L49D1, 7L23D4, 703PTX2, 703PTY1, 703PTY2 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L72 (Mica Creek - Nicola) | 2018-06-19 09:00 | 2018-07-06 17:00 | N | Y | annual plan request F19 - BC maintenance does not affect AB ATC | Line | BC Outage Peak RC COS: 1-00573232 AB Peak RC COS# : 1-00573934 (W>E), 1-00573935 (E>W) |  | Limits ATC, 500 kV
BCH | 2L293 (Selkirk - Nelway) | 2018-06-19 09:00 | 2018-06-21 17:00 | N | Y | markerballs 8/2 - 8/3 installation - BC maintenance does not affect AB ATC | Line | Peak Outage ID BC Outage: 1-00568840 Peak COS ID: 1-00573798 (E>W), 1-00527547 (W>E) |  | Limits ATC
ALTALINK | 514L (396s Pincher Creek - 514BL tap),396s 514N (396s Pincher Creek) | 2018-06-19 17:00 | 2018-06-21 18:00 | N | Y | replace breaker, and add LAs | Circuit Breaker, Line |  |  | Restricts Generation
ATCO | 6L02 (873s Marion Lake - 769s Stettler) | 2018-06-20 07:00 | 2018-06-20 17:00 | N | N | 6L02 is being requested out of service | Line |  | 6L06 IS BEING REQUESTED out of service between 6L02D6 and 769s Stettler (601) in order to salvage understrung 7KV lineno permit or GOI is required - outage is to avoid induction on understrung system | Firm Load Loss, Creates Radial Feeds
ATCO | 6L11 (742s Freeman Lake - 743s Sarah Lake),6L126 (515L tap - 743s Sarah Lake),6L96 (744s Federated Pipelines - 743s Sarah Lake),743s Sarah Lake 72kV Bus | 2018-06-20 07:00 | 2018-06-21 17:00 | N | N | replace insulators and bus PT's, switch maintenance | Line, Bus |  | Replace insulators and bus PT's, Switch maintenance | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker 2403 (Poundmaker) | 2018-06-20 07:00 | 2018-06-20 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.2TR (ENMAX 14) | 2018-06-20 08:00 | 2018-06-22 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ENMAX | 39.4TR (ENMAX 39) | 2018-06-20 08:00 | 2018-06-20 16:00 | N | N | panel replacement on 25 kV feeders | Transformer |  |  | For Information Only
ALTALINK | 394s T4 (394s Empress) | 2018-06-20 09:00 | 2018-06-23 10:00 | N | N | equipment testing | Transformer |  |  | For Information Only
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek),741s 701 (741s Fox Creek) | 2018-06-20 11:00 | 2018-06-20 17:00 | N | N | top up low SF6 on one pole | Line, Circuit Breaker |  | Top up low SF6 on One Pole, if pole gets much lower it will alarm, If too low it will go to lockout and block operation. | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2018-06-20 14:03 | 2018-06-22 13:13 | N | Y | forced outage | Line | PEAK COS outage ID:1-00578324 PEAK COS path de-rate ID:1-00578325 (N-S), (S-N):1-00578326 |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2018-06-21 07:00 | 2018-06-22 18:00 | N | N | changing out structures #47 & 48 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Poundmaker 2404 (Poundmaker) | 2018-06-21 07:00 | 2018-06-21 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 737L (95s Imperial Oil Edmonton - 38s East Edmonton),38s 737N (38s East Edmonton),38s37 (38s East Edmonton) | 2018-06-21 08:00 | 2018-06-21 12:00 | N | N | trip test from new 38s 138kV bus 1 protection | Switch, Line, Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 396s T1 (396s Pincher Creek),185L (396s Pincher Creek - 379s Shell Canada Waterton),396s Pincher Creek 69kV Bus | 2018-06-21 16:00 | 2018-06-21 17:00 | N | Y | open 396s 69kV bus breakers to remotely test energize new 396s514N breaker | Bus, Transformer, Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power A1P | 2018-06-21 17:00 | 2018-07-05 16:30 | N | Y | isolator replacement | Line |  |  | Limits ATC
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2018-06-22 07:30 | 2018-06-22 17:30 | N | N | disconnect mobile substation | Transformer |  | disconnect mobile substation from T2 bus, and re-connect T2 low side | For Information Only
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2018-06-23 05:30 | 2018-06-24 18:00 | N | Y | washing program | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2018-06-23 08:00 | 2018-06-24 18:00 | N | N | doble | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 9L913 (69s North Barrhead - 732s Mitsue) | 2018-06-25 07:00 | 2018-06-28 18:00 | N | Y | rebuilding of current section of line due to new 500KV right-of-way requirements | Line |  | Cutting over to a temporary section of 9L913 line to allow rebuilding of current section of line due to 12L41 500KV right-of-way requirements. | 240 kV
EPCOR | 805s T3 (805s Jasper) | 2018-06-25 07:00 | 2018-06-29 17:00 | N | Y | doble | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 233s T1 (233s Beamer) | 2018-06-25 07:00 | 2018-06-26 17:00 | N | N | urgent repair | Transformer |  | Urgent repair - 233s T1 X & Y Bus hot spots, replace CT's on same busses - hot spots, replace 233s33 | For Information Only
ALTALINK | 763L (28s West Brooks - 763L257A) | 2018-06-25 07:00 | 2018-06-25 11:00 | N | N | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22) | 2018-06-25 08:00 | 2018-06-25 16:00 | N | N | measurements required on 8kV protection and revenue CTs | Transformer |  | Measurements required on 8kV protection and revenue CTs. Tech lead Annie Wang 403-514-2612 | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2018-06-25 08:00 | 2018-06-29 16:00 | N | N | doble test transformer | Transformer |  | Doble test transformer. Secondary cable tests. Check reversing switch. Transformer maintenance. Remediate Rust on Tapchanger Floor Next Outage [AVANTIS] | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34),34B69-21.61 (ENMAX 34) | 2018-06-25 08:00 | 2018-06-26 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2018-06-25 08:00 | 2018-06-28 17:00 | N | N | changing cross arms | Line |  | CHANGING CROSS-ARMS ON 7L53 BONNYVILLE TO LINDBERGH | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
REDDEER | 247s T1 (247s Piper Creek) | 2018-06-25 09:00 | 2018-06-29 15:30 | N | N | maintenance | Transformer |  |  | For Information Only
ATCO | 729s 701T (729s Otauwau) | 2018-06-25 09:30 | 2018-06-26 16:00 | N | N | leak repair | Transformer |  | Leak Repair with Colt Group, 701T @ 729S | For Information Only
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2018-06-25 09:30 | 2018-06-26 18:30 | N | N | disconnect mobile substation and replace insulators on 172s219, Replace 172s220 junction box | Line |  | Disconnect mobile substation at 172s, replace insulators on 172s219, Replace 172s220 junction box | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 932s 901T (932s Pemukan) | 2018-06-25 10:00 | 2018-06-28 15:00 | N | Y | leak repairs | Transformer |  | 932S - 901T Leak Repairs 240kV - 144kV tie transformer will be out of service | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 760L (394s Empress - 163s Amoco Empress),394s 760N (394s Empress) | 2018-06-25 10:30 | 2018-06-25 16:30 | N | N | Replace insulators on arrestor brackets | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 789s 705R (789s Keg River) | 2018-06-25 12:00 | 2018-06-28 15:00 | N | N | bushing replacement & testing | Shunts |  | 789S KEG RIVER 705R Bushing Replacement & Testing 705R Out of Service for the Duration of the Work | Pre-Condition
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2018-06-25 13:00 | 2018-06-28 17:00 | N | Y | SCADA system upgrade | Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 452L (434s Stony Plain - 367s Harry Smith) | 2018-06-26 07:00 | 2018-07-16 13:00 | N | N | moving portions of line to allow for road widening between Structures 33 - 59 | Line |  | Moving portions of line to allow for road widening between Structures 33 - 59. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 17s 4 (17s Benalto) | 2018-06-26 07:30 | 2018-06-26 10:00 | N | Y | apply voltage settings threshold for the 17s3 breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 2739s T1 (2739s Wabamun),2739s T2 (2739s Wabamun),124L (19s Wabamun - 2739s Wabamun) | 2018-06-26 07:30 | 2018-06-26 18:30 | N | N | 2739s T2 replace one LV (X2) bushing, 2739s T2 and T1 testing | Transformer, Line |  | 2739s TX5698 replace one LV (X2) bushing, 2739sT2 doble TX 5698 PIO/NONE 69/25KV6M, 2739sT1 doble TX 4015 FER/NONE 69/25KV5M | For Information Only
ALTALINK | 76L (115s Mt. Allan - 33s Spray) | 2018-06-26 08:00 | 2018-06-26 12:45 | N | Y | plates on all three dead ends to be replaced (76L dead ends at 115s) | Line |  |  | Pre-Condition, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 668L (394s Empress - 562s Cypress),394s 668 (394s Empress) | 2018-06-26 08:30 | 2018-06-26 13:30 | N | N | replace insulators on arrestor brackets | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 3 (17s Benalto) | 2018-06-26 10:00 | 2018-06-26 12:30 | N | Y | apply voltage settings threshold for the 17s3 breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | CROW | 2018-06-26 10:00 | 2018-06-26 11:00 | N | N | migration from SDC to PDC | SCInternal |  |  | For Information Only
ALTALINK | 17s 5 (17s Benalto) | 2018-06-26 12:30 | 2018-06-26 14:30 | N | Y | apply voltage settings threshold for the 17s5 breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2018-06-26 12:46 | 2018-06-26 17:30 | N | N | plates on all three dead ends to be replaced (90L dead ends at 115s) | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2018-06-26 12:55 | 2018-06-28 12:00 | N | Y | trees falling on line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 6 (17s Benalto) | 2018-06-26 14:30 | 2018-06-26 17:00 | N | Y | apply voltage settings threshold for the 17s5 breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 708L (233s Beamer - 708L88N) | 2018-06-27 07:00 | 2018-07-13 18:00 | N | Y | installing new switch 708L89 | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2018-06-27 08:00 | 2018-06-27 16:00 | Y | Y | emergency broken jumper repair | Line | Peak RC COS outage ID: 1-00578704 Peak RC Path Derate ID: 1-00578708 (E>W), 1-00578709 (W>E) |  | Pre-Condition, Limits ATC, 500 kV
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2018-06-27 08:00 | 2018-06-28 16:00 | N | N | breaker maintenance | Line |  | HV Breaker Maintenance 41B138-40.81. Sprecher HPF. HV Breaker Maintenance 40B138-40.81 | Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2018-06-27 08:00 | 2018-06-28 18:00 | N | Y | align with 1201L outage | Line | Peak RC COS outage ID: 1-00578704 PEAK COS path de-rate ID: 1-00578705 (N-S), 1-00578706 (S-N) |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 760L (394s Empress - 163s Amoco Empress),163s 760X (163s Amoco Empress) | 2018-06-27 08:00 | 2018-06-27 10:00 | N | N | trip test 163s760X | Line, Circuit Breaker |  | Trip Test 163s760X Required for T1 Protection Replacement | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2018-06-27 08:00 | 2018-06-28 16:00 | N | N | tapchanger inspection | Transformer |  | local lower pushbutton not working and oil sample | For Information Only
ALTALINK | 103s T1 (103s Goose Lake) | 2018-06-27 08:30 | 2018-06-28 12:00 | N | Y | urgent trouble corrective:change qualitrol | Transformer |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 17s 4 (17s Benalto) | 2018-06-27 09:30 | 2018-06-27 17:00 | N | Y | fix sync check function | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 63s 252 (63s Red Deer) | 2018-06-27 09:30 | 2018-06-27 12:30 | N | N | urgent trouble corrective: top up nitrogen 240kV ABB HLRE breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 760L (163s Amoco Empress - 760L41),163s 760N (163s Amoco Empress) | 2018-06-27 10:00 | 2018-06-27 12:00 | N | Y | trip test 163s760N | Line, Circuit Breaker |  | Trip Test 163s760N Required for T1 Protection Replacement | Creates Radial Feeds
ALTALINK | 669L (163s Amoco Empress - 562s Cypress) | 2018-06-27 12:00 | 2018-06-27 14:00 | N | N | trip test 163s669 required for T1 protection replacement | Line |  |  | For Information Only
ALTALINK | 63s 452 (63s Red Deer) | 2018-06-27 13:00 | 2018-06-27 16:30 | N | Y | urgent trouble corrective: top up nitrogen 240kV ABB HLRE breaker | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 871L (341s Sand Hills - 163s Amoco Empress) | 2018-06-27 14:00 | 2018-06-27 16:00 | N | N | Trip Test 163s871X Required for T1 Protection Replacement | Line
EPCOR | 805s C1 (805s Jasper),805s J2408 (805s Jasper) | 2018-06-28 07:00 | 2018-06-28 17:00 | N | Y | maintenance due to low density alarm | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 103s 893 (103s Goose Lake),893L (103s Goose Lake - 893BL tap) | 2018-06-28 07:30 | 2018-06-28 12:30 | N | N | close open point "A" (str5-6) | Switch, Line |  |  | For Information Only
ALTALINK | 163s T1 (163s Amoco Empress),163s T5 (163s Amoco Empress) | 2018-06-28 08:30 | 2018-06-28 14:00 | N | Y | perform trip tests for 163s1252, 163s1552, 163s189 required for T1 protection replacement | Transformer |  | perform trip tests for 163s1252, 163s1552, 163s189 required for T1 protection replacement | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 13L/158L (65s High River - 392s Black Diamond) | 2018-06-28 09:45 | 2018-06-28 15:15 | N | N | emergency outage; remove UAV | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 163s C1 (163s Amoco Empress) | 2018-06-28 13:30 | 2018-06-28 16:30 | N | N | trip test 163s63 required for T1 protection replacement | Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 163s C2 (163s Amoco Empress) | 2018-06-28 13:30 | 2018-06-28 16:30 | N | N | trip test 163s64 required for T1 protection replacement | Shunts |  |  | Pre-Condition, For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2018-06-29 08:00 | 2018-06-29 16:00 | N | N | repair or replace winding temperature relay [AVANTIS]. check reversing switch. oil sampling MT, TC | Transformer |  |  | For Information Only
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2018-06-30 08:00 | 2018-07-02 16:00 | N | N | breaker maintenance and testing | Line |  | HV breaker maintenance HLR 37B138-37.81, 38B138-37.81. SF6 gas sample 38B138-37.81. Perform HLR Measurements Tests and Confirm Overtravel has been Eliminated [AVANTIS] | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 786L (799s Coleman - Natal) | 2018-07-02 09:00 | 2018-07-06 17:00 | N | N | BC work at Natal | Line |  | Inspection of NTL 1VT22, 1D22, and 1CB2 | For Information Only
REDDEER | 217s T1 (217s North Red Deer) | 2018-07-02 09:00 | 2018-07-06 15:30 | N | N | OLTC maintenance | Transformer |  |  | For Information Only
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2018-07-03 07:00 | 2018-07-03 17:00 | N | Y | maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s-C-31 (MH69S-3) | 2018-07-03 07:00 | 2018-07-03 16:00 | N | N | cap bank reconfiguration | Shunts |  |  | Pre-Condition
EPCOR | Woodcroft W725 (Woodcroft) | 2018-07-03 07:00 | 2018-07-19 12:00 | N | N | breaker replacement | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 330P SST2 (330P Genesee) | 2018-07-03 07:00 | 2018-07-05 17:30 | N | N | customer outage | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24),ENMAX 24 B138-24.83 (ENMAX 24) | 2018-07-03 08:00 | 2018-07-03 16:00 | N | Y | SF6 gas sample & Doble | Line, Circuit Breaker |  |  | Pre-Condition
BCH | 1L275 (799s Coleman - Natal) | 2018-07-03 09:00 | 2018-07-06 17:00 | N | Y | inspection of NTL 1VT22, 1D22, and 1CB2 | Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 729L (542s Ervick - 729L13A) | 2018-07-03 09:30 | 2018-07-03 18:00 | N | Y | installing bird diverters on two spans of OHSW structures #138 - #140 | Line |  | installing bird diverters on two spans of OHSW between Structures #138 - #140 | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 379s T2 (379s Shell Canada Waterton),379s VR1 (379s Shell Canada Waterton) | 2018-07-03 12:30 | 2018-07-06 13:00 | N | N | maintenance | Transformer |  | Replace three (3) HV bushings on 379sT2. Maintenance items: 379s VR1 doble, TC maintenance, OBG leak | For Information Only
ALTALINK | 502s T1 (502s Shell Waterton (#2)),502s VR1 (502s Shell Waterton (#2)) | 2018-07-03 13:30 | 2018-07-05 17:00 | N | N | maintenance | Transformer |  | Replace one (1) HV bushing H2 on 502sT1, possibly H1 & H3 if available. Maintenance items: 502s T1 & VR1 doble, TC maintenance, TC alarm investigation, DGA sample on T1 H1 & H3 bushings if not replaced. | For Information Only
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2018-07-03 15:00 | 2018-07-19 07:59 | N | N | emergency outage | Line |  |  | Overload, Over/Under Voltage
EPCOR | 803s L2403 (803s Lambton) | 2018-07-04 07:00 | 2018-07-04 17:00 | N | Y | maintenance | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 502s T3 (502s Shell Waterton (#2)) | 2018-07-04 08:00 | 2018-07-04 12:00 | N | N | repair 25kV riser to the 25kV lightning arrestors | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2018-07-04 08:00 | 2018-07-08 18:00 | N | N | replace two structures for road clearance between Structures #335 & #484 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2018-07-04 08:00 | 2018-07-04 16:00 | N | N | doble 43B138-33.84, sheath test and DGA sample | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L224 (774s Monitor - 650s Hansman Lake) | 2018-07-04 08:00 | 2018-07-04 12:00 | N | Y | re-sag line | Line |  | Land owner crossing is sagging close to legal limit need to re-sag line. | Firm Load Loss, Creates Radial Feeds
Syncrude | UE-1 (D05 Syncrude - UE_1 Syncrude Plant 30-2) | 2018-07-04 09:00 | 2018-07-04 18:00 | N | N | urgent replace relays at D05 Syncrude substation | Line |  |  | For Information Only
ALTALINK | 277s T1 (277s Hayter),748L (267s Killarney Lake - 277s Hayter) | 2018-07-04 11:00 | 2018-07-05 15:00 | N | Y | breaker maintenance | Transformer, Line |  | 138kV HGF SF6 gas breaker maintenance @ both ends of 748L. | Restricts Generation
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2018-07-04 21:00 | 2018-07-05 05:00 | N | N | commission 138kV BD circuits on 38B138-38.83 | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2018-07-04 23:00 | 2018-07-05 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2018-07-05 03:00 | 2018-07-05 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 847L (39s Bickerdike - 406s Fickle Lake) | 2018-07-05 07:00 | 2018-07-06 18:00 | N | N | replace insulation on (str 223  228) damaged from fire retardant (forced) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 267s 748E (267s Killarney Lake) | 2018-07-05 08:00 | 2018-08-14 16:00 | N | N | forced outage due to a bird nest environmental risk | Circuit Breaker |  |  | Pre-Condition
ALC | ALS1 Air Liquide Scotford #1 | 2018-07-05 08:00 | 2018-08-23 17:00 | N | N | PSS unavailable | Unit |  |  | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2018-07-05 08:00 | 2018-07-05 16:00 | N | N | doble 41B138-6.82 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 277s T1 (277s Hayter) | 2018-07-05 13:55 | 2018-07-12 17:00 | N | N | 277sT1 bushing/LA replacement and install bird cover ups | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 803s L2401 (803s Lambton),803s L2404 (803s Lambton),1059L (38s East Edmonton - 803s Lambton) | 2018-07-06 07:00 | 2018-07-06 17:00 | N | Y | maintenance | Line, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2018-07-06 07:00 | 2018-07-09 17:00 | N | Y | steel pole refurbishment | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 848s 704T (848s Ruth Lake) | 2018-07-06 08:00 | 2018-07-09 17:00 | N | N | oil reclaiming | Transformer |  | 848S Ruth Lake - 704T Oil Reclaiming 704T @ 848S OOS | For Information Only
ENMAX | 9.80L (ENMAX 31 - ENMAX 9),Enmax 31 B138-9.80 (ENMAX 31) | 2018-07-06 08:00 | 2018-07-06 09:00 | N | N | install relays for RTU upgrade | Line, Circuit Breaker |  | Install CAC/OAC relays for RTU upgrade. Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning DPAC1 | Pre-Condition, For Information Only
ENMAX | 24.81L (ENMAX 31 - ENMAX 24),ENMAX 31 B138-24.81 (ENMAX 31) | 2018-07-06 09:00 | 2018-07-06 10:00 | N | N | install relays for RTU upgrade | Line, Circuit Breaker |  | Install CAC/OAC relays for RTU upgrade. Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning. DPAC1 | Pre-Condition, For Information Only
Syncrude | RL1 (848s Ruth Lake - D05 Syncrude) | 2018-07-06 09:00 | 2018-07-07 20:00 | N | Y | install marker balls at the highway-63 crossing | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
SUNCOR | 139S Hillridge | 2018-07-06 09:00 | 2018-07-07 17:00 | N | N | field testing | Station |  |  | Restricts Generation
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),ENMAX 31 B138-31.84 (ENMAX 31) | 2018-07-06 10:00 | 2018-07-06 11:00 | N | N | install relays for RTU upgrade | Line, Circuit Breaker |  | Install CAC/OAC relays for RTU upgrade. Devices will need to be operated Locally due to RTU change out. Close open close operation required for commissioning. DPAC1 | Pre-Condition, For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2018-07-06 11:00 | 2018-07-06 12:00 | N | N | install CAC/OAC relays for RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2018-07-06 12:00 | 2018-07-06 14:00 | N | N | install CAC/OAC relays for RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2018-07-06 14:00 | 2018-07-06 16:00 | N | N | install CAC/OAC relays for RTU upgrade | Transformer |  |  | For Information Only
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-07-06 18:01 | 2018-07-08 18:00 | N | N | replace insulation on (str 223  228) damaged from fire retardant (forced) | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2018-07-07 07:00 | 2018-07-18 18:00 | N | N | component replacement | Line | The outage is done earlier on Jul 18 as originally planned on Jul 22. |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 32.83L (ENMAX 32 - ENMAX 40),40.1 TR (ENMAX 40) | 2018-07-07 08:00 | 2018-07-07 14:00 | N | N | hot spot SW85 north phase bus connection and substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Syncrude | UE-1 (D05 Syncrude - UE_1 Syncrude Plant 30-2) | 2018-07-07 09:00 | 2018-07-08 22:00 | N | N | urgent - replace faulty relay | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 40.2TR (ENMAX 40),40.81L (ENMAX 40 - ENMAX 41) | 2018-07-07 14:00 | 2018-07-07 18:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station),89s 252 (89s Ellerslie),89s 352 (89s Ellerslie) | 2018-07-08 08:00 | 2018-07-08 17:45 | N | Y | 89s1056 36deg and 45deg hot spots | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
Syncrude | ML1 (Syncrude Mildred Lake - D05 Syncrude) | 2018-07-08 09:00 | 2018-07-09 22:00 | N | N | urgent - replace faulty relay | Line |  |  | Restricts Generation
Syncrude | RL2 (848s Ruth Lake - D05 Syncrude) | 2018-07-08 09:00 | 2018-07-09 20:00 | N | Y | install marker balls at the highway-63 crossing | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 330P SST1 (330P Genesee) | 2018-07-09 07:00 | 2018-07-12 17:30 | N | N | customer outage | Transformer |  |  | For Information Only
EPCOR | 987s T4 (987s Clover Bar) | 2018-07-09 07:00 | 2018-07-13 17:00 | N | Y | doble | Transformer |  |  | 240 kV
EPCOR | Rossdale T3 (Rossdale) | 2018-07-09 07:00 | 2018-08-03 17:00 | N | N | cable moves | Transformer |  |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2018-07-09 08:00 | 2018-07-12 16:00 | N | N | breaker maintenance and doble | Line |  | HV breaker maintenance 15B69-15.62, 16B69-15.62. Replace samaged braid on center phase SW61@16sub. Doble 15B69-15.62 | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39) | 2018-07-09 08:00 | 2018-07-20 16:00 | N | N | panel replacement | Transformer |  |  | For Information Only
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2018-07-09 08:00 | 2018-07-12 17:00 | N | Y | change arms and insulators on 7L702 | Line |  | Change Arms and Insulators on 7L702 | Firm Load Loss, Creates Radial Feeds
TRANSALTA | 239S Castle River | 2018-07-09 08:00 | 2018-07-09 19:00 | N | N | maintenance | Station |  |  | Restricts Generation
ENMAX | 15.2TR (ENMAX 15) | 2018-07-09 08:00 | 2018-07-13 16:00 | N | N | maintenance, testing and doble | Transformer |  | Doble test transformer. Secondary cable tests. Check reversing switch. Gas relay testing. Transformer maintenance. | For Information Only
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2018-07-09 08:00 | 2018-07-10 18:00 | N | N | repair and inspect switch | Line, Transformer |  | Repair hot spot on SW89@9sub. Check reversing switch 9.1TR. Replace insulator on SW86@9sub. Hot spot North East Phase of 31B138-9.80 | Pre-Condition, For Information Only
ATCO | 800s 701T (800s Friedenstal) | 2018-07-09 09:00 | 2018-07-10 12:00 | N | N | commission 701T circuits for 501VR non-electrical switch | Transformer |  | Commission 701T circuits for 501VR Non-Electrical switch, 701T OOS for duration; 702T to feed 25kV & 72kV. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P2C | 2018-07-09 09:00 | 2018-07-13 16:00 | N | Y | structure replacement | Line |  |  | Limits ATC
ALTALINK | 368s C1 (368s Burdett),368s T2 (368s Burdett) | 2018-07-09 10:00 | 2018-07-17 12:00 | N | N | maintain 368s42 | Transformer, Shunts |  | T2 doble, maintain 368s42 and fix leaks and replace a bushing. | Over/Under Voltage, Firm Load Loss
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2018-07-09 10:00 | 2018-07-09 16:00 | N | N | remove mobile sub from 804s Wintering Hills | Line |  | 750S Mobile Sub removal from 804S Wintering Hills | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 151S Strathmore | 2018-07-09 12:30 | 2018-07-09 16:30 | N | N | 25kV Bus 1 Outage for testing | Station |  | P&C will be testing the DG transfer trip scheme to enable Renew Energy(DG customer) to come on line. P&C techs will be checking the breaker maintenance switch inputs to the scheme, 2010L protections inputs and sending transfer trips to the DG. The bypass switch 151s11 does not operate so an extended outage is required in order to complete testing. The substation crew will be working on 151s11 and will attempt to repair it if possible. | For Information Only
ATCO | 1087L (324s Cassils - 2075s Newell) | 2018-07-09 13:00 | 2018-07-12 17:00 | N | Y | SCADA system upgrade | Line |  |  | 240 kV, Limits Ratings
Lethbridge | 172L (370s North Lethbridge - 181s Chinook) | 2018-07-09 14:41 | 2018-07-09 17:22 | N | Y | low SF6 gas (emergency) on 181s172 breaker | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 514L (396s Pincher Creek - 514BL tap) | 2018-07-10 07:00 | 2018-07-11 07:00 | N | Y | maintenance on 322s69CS1 | Line |  | customer maintenance on 322s69CS1 | Pre-Condition, Restricts Generation
ALTALINK | 322S Cowley Ridge | 2018-07-10 07:00 | 2018-07-11 17:00 | N | N | maintenance | Station |  |  | Restricts Generation
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2018-07-10 08:00 | 2018-07-10 12:00 | N | N | install screw piles for new 6L12D2 west of existing 6L12D2 | Line |  | to install screw piles new gang switches (Install new 6L12D2 west of existing 6L12D2) | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
NWE | NWMT Highwood-Judith Gap Auto 230kV Line | 2018-07-10 08:00 | 2018-07-11 16:30 | N | Y | urgent: repair broken wire | Line | Peak RC Path Outage ID: n/a Peak RC Outage ID: n/a |  | 240 kV, Pre-Condition
ALTALINK | 377s T1 (377s Hardisty) | 2018-07-10 11:00 | 2018-07-11 18:00 | N | N | pressure relay replacement on T1 with new 3 sensor Qualitrol | Transformer |  |  | Pre-Condition, For Information Only
ATCO | 800s 702T (800s Friedenstal) | 2018-07-10 13:00 | 2018-07-11 16:00 | N | N | commission 702T circuits for 501VR non-electrical switch | Transformer |  | Commission 702T Circuits for 501VR Non-Electrical Switch, 702T OOS for duration; 701T feeds 25 kv & 72 kV | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2018-07-10 13:00 | 2018-07-20 17:00 | N | N | install screw piles for new 6L12D3 just east of existing 6L12D3 | Line |  | to install screw piles for new gang switches (Install new 6L12D3 just east of existing 6L12D3) | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2018-07-10 18:00 | 2018-08-03 16:00 | N | N | line protection upgrade | Line |  | Line Protection Upgrade. Replace 31B138-9.80. GOI transferred from 9.80L.9.1TR outage | For Information Only
Lethbridge | 172L (370s North Lethbridge - 181s Chinook) | 2018-07-11 06:30 | 2018-07-11 19:00 | N | Y | low SF6 gas (emergency) on 181s172 breaker | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 745L (602s Cold Creek - 745L482) | 2018-07-11 07:00 | 2018-07-11 12:00 | N | N | replacing/moving structure #569 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 745AL (411s Obed - 745AL4) | 2018-07-11 07:00 | 2018-07-14 15:00 | N | N | replace insulation on structures #22, 23, 49, 51, 52 | Line |  |  | For Information Only
ALTALINK | 510S Sunnybrook | 2018-07-11 08:00 | 2018-07-11 16:00 | N | N | de-ionized water pumps urgent outage | Station
ALTALINK | 767L (310p Sundance - 767L50) | 2018-07-11 08:00 | 2018-07-12 14:00 | N | N | connect 471s to 767L at 310p | Line |  |  | Pre-Condition
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2018-07-11 09:00 | 2018-07-11 12:00 | N | N | high load move | Line |  | High Load Move | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn Plant) | 2018-07-11 11:00 | 2018-07-11 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2018-07-12 07:00 | 2018-07-12 11:00 | N | N | high load move | Line |  | High load move between 799L738 & 799L739 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn Plant) | 2018-07-12 09:00 | 2018-07-12 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 783s 701T (783s Cadotte River) | 2018-07-12 11:00 | 2018-07-12 16:00 | N | N | pole change | Transformer |  | Need to take an outage on 783S Cadotte River Sub to change a pole @ S17049 and at asset 846244 on 5L594 (Just outside the sub) | For Information Only
ALTALINK | 512L (310p Sundance - 821s Sundance) | 2018-07-12 14:00 | 2018-07-30 18:00 | N | N | replace all wooden cross arms | Line |  | Replace all wooden crossarms at 821s | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1045L (310p Sundance - 805s Jasper) | 2018-07-13 07:00 | 2018-07-16 17:00 | N | Y | steel pole refurbishment | Line |  |  | 240 kV, Pre-Condition, Overload
ATCO | 850s 702T (850s Rainbow Cogen) | 2018-07-13 08:00 | 2018-07-14 12:00 | N | Y | emergency replace faulty gas relay | Transformer |  |  | Restricts Generation
ENMAX | 13.82L (ENMAX 22 - ENMAX 13),ENMAX 22 B138-13.82 (ENMAX 22) | 2018-07-13 08:00 | 2018-07-13 16:00 | N | N | doble,inspect/replace gauge | Line, Circuit Breaker |  | Doble 22B138-13.82. Inspect/replace Gauge on center phase 22B138-13.82 [AVANTIS]. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (515s Fed Pipe Judy Creek - 526L420) | 2018-07-13 12:00 | 2018-07-13 16:00 | N | N | damaged structure X-arm | Line |  |  | For Information Only
ENMAX | 41.1C (ENMAX 41),41.2TR (ENMAX 41),33.83L (ENMAX 41 - ENMAX 33),6.82L (ENMAX 6 - ENMAX 41) | 2018-07-14 08:00 | 2018-07-14 16:00 | N | N | substation washing | Line, Transformer, Shunts |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RG1 (Rossdale - Garneau) | 2018-07-15 07:00 | 2018-07-15 17:00 | N | N | doble | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31) | 2018-07-15 08:00 | 2018-07-15 16:00 | N | N | breaker maintenance and weed control | Shunts |  | HD breaker maint 31B138-31.1CAP. Weed control in CAPSubstation - Cap bank, HV Maintenance. 31B138-31CAP breaker has a motor run time alarm on the closing. Weeds in capacitor bank are growing high, has caused outage in past, rusting capacitors as well t. | For Information Only
ATCO | 2075s ACF11 (2075s Newell) | 2018-07-16 07:00 | 2018-07-18 15:30 | N | Y | maintenance on the 901T 240KV transformer, and inspections of ACF11 | Shunts |  | Maintenance on the 901T 240KV transformer, and inspections of ACF11, SVC2 will be in service. | 240 kV, For Information Only
Medicine Hat | MH69s3 MH69_314 (MH69s3 South Ridge),MH69s3 MH69_316 (MH69s3 South Ridge),MH69s-C-31 (MH69S-3),MH69s3 T33 (MH69s3 South Ridge) | 2018-07-16 07:00 | 2018-07-16 19:00 | N | N | emergency rewire bus PT | Circuit Breaker, Shunts, Transformer |  | Rewire 69 kV Bus PTs to provide correct PT signal for MH-20L Line protection | For Information Only
ENMAX | 36.3TR (ENMAX 36) | 2018-07-16 08:00 | 2018-07-18 16:00 | N | N | tap changer inspection - investigate oil leak | Transformer |  | Tapchanger Inspection. Investigate Oil Leak [AVANTIS]. Check reversing switch. Oil sample MT, TC | For Information Only
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2018-07-16 08:00 | 2018-07-19 17:00 | N | Y | change arms and insulators on 7L702 | Line |  | Change Arms and Insulators on 7L702 | Firm Load Loss, Creates Radial Feeds
ENMAX | 12.1TR (ENMAX 12) | 2018-07-16 08:00 | 2018-07-20 16:00 | N | N | HV CT addition | Transformer |  |  | For Information Only
ENMAX | 28.2TR (ENMAX 28) | 2018-07-16 08:00 | 2018-07-20 16:00 | N | N | doble test transformer - maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 932L (74s Janet - 162s Beddington) | 2018-07-16 08:00 | 2018-07-16 16:00 | N | Y | repair SW144 | Line |  |  | 240 kV
ALTALINK | 575s T1 (575s Sundre) | 2018-07-16 09:30 | 2018-07-19 17:00 | N | N | fix leaks and change H1 & H3 bushings on 575sT1 | Transformer |  | fix leaks and change H1 & H3 bushings on 575sT1 Tx18533 | For Information Only
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2018-07-16 09:30 | 2018-07-20 17:00 | N | Y | inspect the filter bank | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 1112L (289s Saunders Lake - 89s Ellerslie),89s 1452 (89s Ellerslie),89s 1552 (89s Ellerslie) | 2018-07-16 11:00 | 2018-07-27 16:00 | N | Y | 89s1452 breaker replacement, 89s81 PT replacement | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 1088L (324s Cassils - 2075s Newell) | 2018-07-16 13:00 | 2018-07-19 17:00 | N | Y | SCADA system upgrade | Line |  |  | 240 kV, For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2018-07-16 22:00 | 2018-07-17 06:00 | N | N | outage required for 11sub | Line |  |  | For Information Only
BLACKSPRING | 485S Black Springs | 2018-07-17 06:00 | 2018-07-18 19:00 | N | Y | substation maintenance and inspections | Station |  |  | Restricts Generation
Medicine Hat | MH69s3 MH69_314 (MH69s3 South Ridge),MH69s3 MH69_316 (MH69s3 South Ridge),MH69s-C-31 (MH69S-3),MH69s3 T33 (MH69s3 South Ridge) | 2018-07-17 06:00 | 2018-07-17 10:00 | N | N | repair cap bank circuit breaker | Shunts, Circuit Breaker, Transformer |  | Rewire 69 kV Bus PTs to provide correct PT signal for MH-20L Line protection | For Information Only
EPCOR | 72RV2 (Rossdale - 511s Victoria),Rossdale RV728 (Rossdale) | 2018-07-17 07:00 | 2018-07-17 17:00 | N | N | maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 92s T1 (92s Viscount) | 2018-07-17 07:30 | 2018-07-18 17:00 | N | N | maintenance | Transformer |  | Visct Tx Temp Monitr Field Ops. ADD 92s T1 (18685)Disable hydran, 92sT1 Filter Pack turned off due to leak, 92s2251 (CB1766) maintain 36kV,1200A,3AH, 92s2277 (CB1823) maintain 36kV,1200A,3AH | For Information Only
SUNCOR | 139S Hillridge | 2018-07-17 07:30 | 2018-07-18 10:00 | N | N | to perform maintenance | Station |  | Customer driven request | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2018-07-17 08:00 | 2018-07-19 16:00 | N | N | breaker maintenance | Line |  | HV breaker maintenance 34B69-16.60. Doble 16B69-16.60 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 368s C1 (368s Burdett),368s T2 (368s Burdett),612L (336s Fincastle - 368s Burdett),722L (368s Burdett - 107s Westfield),368s 36 (368s Burdett) | 2018-07-17 08:00 | 2018-07-17 12:00 | N | Y | close the open point A | Transformer, Shunts, Circuit Breaker, Line |  | To close open point A as part of 368s T2(Tx 18500) GOI | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 834s 708 (834s Wesley Creek) | 2018-07-17 08:00 | 2018-07-17 16:00 | N | Y | low SF6 | Circuit Breaker |  |  | Overload, Contingency Requires Mitigation
BCH | 2L113 (B1s Natal - B2s Cranbrook),Natal T2 (BCH Natal),1L274 (B1s BCH Natal - 1D1L274),Natal T3 (BCH Natal),Natal T4 (BCH Natal) | 2018-07-17 08:00 | 2018-07-17 19:00 | N | Y | line work and work at Natal | Line, Transformer | AB Peak RC COS# : 1-00582973 (W-E), 1-00582974 (E-W) Peak RC COS Outage # (BCH outage): 1-00579738 |  | Overload, Over/Under Voltage, Limits ATC
ENMAXEC | 383S Kettles Hill Windfarm | 2018-07-17 08:00 | 2018-07-17 18:00 | N | Y | DVar annual maintenance | Station |  | Requested for annual maintenance on voltage control units PME#1 and #2. Voltage site support will be reduced to 50% (4MVA dynamic support). We will only take one unit down at a time to complete the maintenance. | Restricts Generation
ATCO, ALTALINK | 9L913 (69s North Barrhead - 732s Mitsue) | 2018-07-17 08:00 | 2018-07-22 17:00 | N | Y | replace rotten crossarms & poles | Line |  | replace rotten crossarms & poles | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 368s T2 (368s Burdett) | 2018-07-17 12:01 | 2018-07-23 17:00 | N | N | emergeny repair on 368s8 switch which broke when on earlier T2 maintenance | Transformer |  |  | For Information Only
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2018-07-18 01:05 | 2018-07-20 18:00 | N | N | forced outage | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 708L (71s Lamoureux - 708L88X) | 2018-07-18 07:00 | 2018-08-01 18:00 | N | Y | install new switch 708L87F | Line |  |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 443s T1 (443s South Mayerthorpe) | 2018-07-18 07:30 | 2018-07-19 18:00 | N | N | doble, maintenance and leak 25 kv repairs | Transformer |  |  | For Information Only
ALTALINK | 396s T3 (396s Pincher Creek) | 2018-07-18 08:00 | 2018-07-19 17:00 | N | N | urgent replacement of 2-138kV bushings | Transformer |  |  | For Information Only
ALTALINK | 305s C1 (305s Acheson),305s32 (305s Acheson) | 2018-07-18 08:30 | 2018-07-18 13:00 | N | N | standard relay maintenance on the following: C1 50/51/27/59/C1 SR760V4 | Switch, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 163s T1 (163s Amoco Empress) | 2018-07-18 08:30 | 2018-07-18 17:30 | N | Y | emergency work to correct A protection wiring to CTs | Transformer |  | Correct A Protection Wiring to CT's - A Protection is currently out of service. Emergency request related to 163s T1 recent trip event. | 240 kV, For Information Only
ALTALINK | 103s T1 (103s Goose Lake),103s 452 (103s Goose Lake),103s 1152 (103s Goose Lake),103s 252 (103s Goose Lake),103s Goose Lake 240kV Bus 1 | 2018-07-18 09:00 | 2018-07-18 15:00 | N | Y | install voltage test leads on 240kV bus for harmonic measurement | Bus, Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2018-07-18 10:00 | 2018-07-18 13:00 | N | N | urgent replacement on switch 6L15D1 | Line |  | Replace Centre Phase Switch on 6L15D1 to fix this as the ring burnt off of last week during that storm at Sullivan Lake | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (123s Banff - 953s Lake Louise) | 2018-07-18 23:30 | 2018-07-19 04:30 | N | N | structure 73A, 73A1 (outside 945s); change insulators, jumpers. 953s; install mobile, create open point on 551L (area loads offline) | Line |  |  | Firm Load Loss
ATCO | 2075s ACF12 (2075s Newell) | 2018-07-19 07:00 | 2018-07-20 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter Bank Maintenance and Inspection, ACF12 will be out of service during outage, One A type filter needs to be available at all times so we will lose redundancy when ACF12 is out of service. ACF 22 will still be available. Power Cap will be at 1000 MW @ 500 kV when only one A type filter is available. | 240 kV, Pre-Condition
ALTALINK | 953S Lake Louise | 2018-07-19 08:00 | 2018-08-31 16:00 | N | N | station upgrade - 69kV bus rebuild | Station |  |  | For Information Only
ALTALINK | 760L (163s Amoco Empress - 760L41),163s 760N (163s Amoco Empress) | 2018-07-19 09:00 | 2018-07-19 17:30 | N | N | urgent trouble corrective: remove the sync-check bypass switch and wiring in the breaker control circuit | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Creates Radial Feeds
ATCO | 7L85 (803s Bullpound - 801s Anderson) | 2018-07-19 09:00 | 2018-07-19 12:00 | N | N | high load move | Line |  | High load move | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 452L (434s Stony Plain - 367s Harry Smith) | 2018-07-19 13:00 | 2018-07-28 17:00 | N | N | moving portions of line to allow for road widening between Structures 33 - 59 | Line |  | Moving portions of line to allow for road widening between Structures 33 - 59. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 1098L (805s Jasper - Poundmaker) | 2018-07-20 07:00 | 2018-07-23 17:00 | N | Y | steel pole refurbishment | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2018-07-20 07:15 | 2018-07-20 17:45 | N | Y | emergency repair, broken spacer (str 218) | Line |  |  | 240 kV, Pre-Condition
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2018-07-20 17:46 | 2018-09-17 07:00 | N | N | emergency outage | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX | ENMAX 24 B138_24BT3 (ENMAX 24) | 2018-07-21 08:00 | 2018-07-21 16:00 | N | N | doble 24B138-24BT3 | Circuit Breaker
ENMAX | 11.1TR (ENMAX 11) | 2018-07-21 08:00 | 2018-07-22 16:00 | N | N | Install new card on T60 | Transformer
MONTANA | MATL (120s Picture Butte - Montana) | 2018-07-21 09:00 | 2018-07-22 18:00 | N | Y | align with 1201L outage | Line | Peak RC COS outage ID: 1-00582981 Peak RC Path Derate ID: 1-00582993 (N>S), 1-00582995 (S>N) |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2018-07-21 09:00 | 2018-07-22 18:00 | Y | Y | emergency replace jumper string, shackles & flashed insulators (str 441-444) | Line | Peak RC COS outage ID: 1-00582981 Peak RC Path Derate ID: 1-00582982 (E>W), 1-00582983 (W>E) |  | Pre-Condition, Limits ATC, 500 kV
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar),89s 1652 (89s Ellerslie) | 2018-07-21 10:00 | 2018-07-21 10:30 | N | Y | replacing DC fuse holder | Line, Circuit Breaker |  | Required for replacing DC fuse holder in junction box for existing outage 1112L GOI. Junction box shipped with wrong fuse size holder. 89s1652 breaker is required to be open to avoid protection issues with DC offline. No work is being performed around the breaker so just a breaker open advice is required | 240 kV
EPCOR | 814s T1 (814s Bellamy),72RS5 (Rossdale - Strathcona),72RV6 (Rossdale - 511s Victoria) | 2018-07-22 07:00 | 2018-07-22 17:00 | N | Y | doble | Transformer, Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2018-07-22 08:00 | 2018-07-22 16:00 | N | N | fall substation washing. check reversing switch | Line, Transformer
EPCOR | E511s VictoriaT3 (511s Victoria),Victoria V725 (Victoria),Victoria V724 (Victoria) | 2018-07-23 07:00 | 2018-08-10 17:00 | N | N | cutting over and commissioning new protection | Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ATCO | 2075s ACF13 (2075s Newell) | 2018-07-23 07:00 | 2018-07-24 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter bank inspection/maintenance, redundant filters will remain in service | 240 kV, For Information Only
ATCO | 7L702 (137s Sedgewick - 757s Battle River),757s 708 (757s Battle River) | 2018-07-23 07:00 | 2018-07-26 17:00 | N | N | Install and test transfer trip from Altalink | Line, Circuit Breaker |  | Install and test transfer trip from Altalink for a new DG at Sedgewick | Firm Load Loss, Creates Radial Feeds
FORTIS | GenAlta Bellshill DG | 2018-07-23 08:00 | 2018-09-07 16:00 | N | N | ISD: Sept 4, 2018 | Unit
ENMAX | 15.60L (ENMAX 21 - ENMAX 15),15B69-15.60 (ENMAX 15) | 2018-07-23 08:00 | 2018-07-24 16:00 | N | N | breaker maintenance & Doble | Line, Circuit Breaker |  | HV breaker maintenance 15B69-15.60. Doble 15B69-15.60 | Firm Load Loss, Creates Radial Feeds
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2018-07-23 08:00 | 2018-07-31 17:00 | N | N | install screw piles for new 6L12D3 just east of existing 6L12D3 | Line |  | to install new gang switches (Install new 6L12D3 just east of existing 6L12D3) to install new gang switches (Install new 6L12D2 west of existing 6L12D2) | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.1TR (ENMAX 36) | 2018-07-23 08:00 | 2018-07-24 16:00 | N | N | transformer inspection and maintenance | Transformer |  |  | Pre-Condition
ENMAX | 12.2TR (ENMAX 12) | 2018-07-23 08:00 | 2018-07-26 17:00 | N | N | HV CT addition | Transformer |  |  | For Information Only
SUNCOR | 29PL7-8 (29EDD-85 - 29EDD-160) | 2018-07-23 09:00 | 2018-07-24 18:00 | N | N | improve suspension insulator support to avoid flashover - insulator replacement | Line |  | Corrective work on line 29PL7-8 from 29EDD-85 substation - improve suspension insulator support to avoid flashover - Insulator replacement | For Information Only
ALTALINK | 754L (437s Baymag - 754L75) | 2018-07-23 09:15 | 2018-08-03 17:45 | N | Y | structure replacements | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 510s ACF11 (510s Sunnybrook) | 2018-07-23 09:30 | 2018-07-25 12:00 | N | Y | inspect the filter bank | Shunts |  | Outage and GOI required to inspect the Filter Bank. No impact to HVDC link capability | For Information Only, 500 kV
ALTALINK | 87s T1 (87s Gaetz),914L (87s Gaetz - 63s Red Deer),87s 552 (87s Gaetz),87s 152 (87s Gaetz),87s 952 (87s Gaetz),87s 1652 (87s Gaetz) | 2018-07-23 10:00 | 2018-07-26 16:00 | N | Y | replace bus protection and perform test trips | Circuit Breaker, Line, Transformer |  | Replace A87/240BW Protection and perform test trips to 87s2352, 87s1652, 87s952, 87s552, & 87s152 | 240 kV
ATCO | 801s 911 (801s Anderson) | 2018-07-23 10:00 | 2018-07-27 16:00 | N | Y | breaker testing and maintenance | Circuit Breaker |  | 801S Anderson - BREAKER MIN OIL HLR PARTIAL TESTING 911 Breaker Maintenance Complete Breaker 911 Not Available | 240 kV, Contingency Requires Mitigation
ALTALINK | 212s T1 (212s N.E.Lacombe) | 2018-07-23 11:00 | 2018-07-26 14:00 | N | N | 212s28 replacement, bird cover & Doble test | Transformer |  | 212s28 Replacement, Bird cover on T1 & VR1, & T1 Doble test | For Information Only
ALTALINK | 338s 252 (338s Cherhill) | 2018-07-23 12:30 | 2018-07-25 14:30 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 945s T2 (945s Sunshine Village) | 2018-07-23 12:30 | 2018-07-26 16:30 | N | N | change out the 25kV bushings ,doble and maintain | Transformer |  | Change out the 25kV bushings on T1, doble and maintain. | For Information Only
ALTALINK | 974L (39s Bickerdike - 310p Sundance),310p 152 (310p Sundance),310p 252 (310p Sundance) | 2018-07-23 13:00 | 2018-07-26 16:00 | N | Y | migrate and commission new protections | Line, Circuit Breaker |  | Migrate and commission all L1 - 974L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L1 alarms. | 240 kV, Over/Under Voltage
ALTALINK | 562s T2 (562s Cypress) | 2018-07-23 13:30 | 2018-07-25 16:30 | N | Y | Maintain, doble, SFRA and investigate alarm on T2. | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 791s 701T (791s Rainbow Lake) | 2018-07-23 13:30 | 2018-07-27 12:30 | N | N | MR TC upgrade and maintenance | Transformer |  | Complete MR TC Upgrade and Maintenance, MR Rep from Germany confirmed for the week of July 23, 2018, 702T to carry load | For Information Only
ALTALINK | 723L (69s North Barrhead - 723L133) | 2018-07-24 07:00 | 2018-07-26 18:00 | N | N | install new dead end structure east of Str. #205 and remove anchors on Str. #205 | Line |  | Install new dead end structure east of Str. #205 and remove anchors on Str. #205 that are in the river. | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.3TR (ENMAX 14) | 2018-07-24 08:00 | 2018-07-24 16:00 | N | N | winding temp gauge checking | Transformer |  | On 14.3 TR the winding temp gauge is not picking up the fans >55degC | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2018-07-24 08:00 | 2018-08-03 16:00 | N | N | panel replacement | Transformer |  |  | For Information Only
ALTALINK | 799s T1 (799s Coleman) | 2018-07-24 23:30 | 2018-07-30 04:59 | N | N | replace 25 kV wood pole (bus support) | Transformer
ALTALINK | 799s T1 (799s Coleman),799s T3 (799s Coleman) | 2018-07-24 23:30 | 2018-07-25 06:30 | N | N | replace 25 kV wood pole (bus support) | Transformer |  |  | For Information Only
Medicine Hat | MH69s2 C-21(MH69s2 North Industrial),MH-16L (MH69S-2 - MH69S-16),MH69s2 MH69_208 (MH69s2 North Industrial),MH69s2 MH69_224 (MH69s2 North Industrial),MH69s2 MH69_205 (MH69s2 North Industrial),MH69s2 T21 (MH69s2 North Industrial) | 2018-07-25 07:00 | 2018-07-25 19:00 | N | Y | emergency rewire 69 kV Bus PTs to provide correct PT signal for MH-10L, MH-16L and Bus 709 Line protection | Circuit Breaker, Line, Shunts, Transformer |  |  | Restricts Generation
ATCO | 2075s ACF14 (2075s Newell) | 2018-07-25 07:00 | 2018-07-25 15:00 | N | Y | filter bank inspection/maintenance, | Shunts |  | Filter bank inspection/maintenance, No redundancy for type C filter. ACF24 will still be available | 240 kV
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2018-07-25 07:15 | 2018-07-25 10:00 | N | Y | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 37.1TR (ENMAX 37) | 2018-07-25 08:00 | 2018-07-26 16:00 | N | N | tapchanger inspection. oil sampling MT | Transformer
ALTALINK | 671L (58s Edson - 39s Bickerdike),39s 37 (39s Bickerdike),39s 38 (39s Bickerdike) | 2018-07-25 08:00 | 2018-07-25 12:00 | N | N | high load move between structures #135 & 136 | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 305s T1 (305s Acheson) | 2018-07-25 08:30 | 2018-07-27 12:00 | N | N | replace 305sT1 bushing X2 and X3 & install bird cover up on the bushings | Transformer
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2018-07-25 10:30 | 2018-07-25 17:45 | N | Y | high load move | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2018-07-25 12:01 | 2018-07-26 15:30 | N | Y | outage and required to inspect the filter bank | Shunts |  |  | 500 kV
ALTALINK | 310p 152 (310p Sundance) | 2018-07-26 16:01 | 2018-07-30 18:00 | N | Y | unable to close in switch | Circuit Breaker |  |  | 240 kV
ENMAX | 12.1TR (ENMAX 12) | 2018-07-26 17:00 | 2018-07-28 12:37 | N | N | forced outage | Transformer
Saskpower | SaskPower C1S | 2018-07-27 07:00 | 2018-07-30 12:00 | N | N | maintenance | Line |  |  | Limits ATC
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),72CK12 (987s Clover Bar - Kennedale),72CK13 (987s Clover Bar - Kennedale),987s 69kV Bus 4 (987s Cloverbar) | 2018-07-28 07:00 | 2018-07-29 17:00 | N | N | CVT replacement | Bus, Line |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station),1055L (816s Petrolia - 629s Argyll Transfer Station) | 2018-07-28 07:00 | 2018-07-28 17:00 | N | Y | doble | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 5 | 2018-07-28 08:00 | 2018-07-28 18:00 | N | N | doble test PTs | Station |  | Doble test PTs. 2.82L, 1.84L, and 1.82L distance elements will not function while PTs are out of service but lines will remain protected through line differential protection. | For Information Only
ENMAX | ENMAX 5 5B138-5BT7 (ENMAX 5) | 2018-07-28 08:00 | 2018-07-28 18:00 | N | N | doble 5B138-5BT7 138kV east & west CTs | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 799s T3 (799s Coleman) | 2018-07-30 05:00 | 2018-08-02 14:00 | N | N | de-energize T3 with 799s bus outage | Transformer |  | in preparation for T3 GOI outage July 30- Aug 02 ref# 258738. | For Information Only
ALTALINK | 799s T3 (799s Coleman) | 2018-07-30 05:00 | 2018-08-02 14:00 | N | N | replace 799s T3 bushings, 138kV LA and 25kV LA, doble and fix oil leaks | Transformer |  |  | For Information Only
ATCO | 2075s ACF21 (2075s Newell),2075s 902T (2075s Newell) | 2018-07-30 07:00 | 2018-08-01 15:30 | N | Y | ACF21/902T inspections/maintenance | Shunts, Transformer |  | ACF21/902T inspections/maintenance, SVC1 will remain in service. | 240 kV, For Information Only
STROBE | 240S McBride Lake | 2018-07-30 07:00 | 2018-07-31 17:00 | N | N | maintenance | Station |  |  | Restricts Generation
ENMAX | 38.3TR (ENMAX 38) | 2018-07-30 08:00 | 2018-08-02 18:00 | N | N | CT replacement | Transformer |  |  | For Information Only
ENMAX | ENMAX 65 B240-D130 (ENMAX 65) | 2018-07-30 08:00 | 2018-08-01 16:00 | N | Y | HV breaker maintenance | Circuit Breaker |  | HV breaker maintenance. Remediate Bird Mess Inside Insulating Blankets [AVANTIS]. Heater Fail Alarm [AVANTIS] | 240 kV, Contingency Requires Mitigation
ENMAX | 41.2TR (ENMAX 41) | 2018-07-30 08:00 | 2018-08-03 16:00 | N | N | doble, secondary cable tests and maintenance | Transformer |  |  | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2018-07-30 08:00 | 2018-08-02 16:00 | N | N | tapchanger inspection and oil sample | Transformer |  |  | For Information Only
SUNCOR | 29EDD-34 Edd34Sub,29PL9-14 (29EDD-56 - 29EDD-34) | 2018-07-30 09:00 | 2018-08-19 18:00 | N | Y | 5 year maintenance on breakers, bus CT and switches | Line, Station |  | planned maintenance on 29EDD-34 and 29PL9-14: - 5 Year mtce - 5 year mtce on breakers, bus CT and switches - replace gauge 952-141 (B) | 240 kV, Contingency Requires Mitigation
ATCO | 801s 912 (801s Anderson) | 2018-07-30 10:00 | 2018-08-02 07:59 | N | Y | breaker maintenance | Circuit Breaker |  | 801S Anderson - BREAKER MIN OIL HLR PARTIAL TESTING Breaker 912 Partial Maint Breaker 912 Not Available | 240 kV, Contingency Requires Mitigation
ALTALINK | 87s T2 (87s Gaetz),914L (86s Bigstone - 87s Gaetz),87s 852 (87s Gaetz),87s 252 (87s Gaetz),87s 2352 (87s Gaetz),87s 1052 (87s Gaetz),87s 1252 (87s Gaetz),87s Gaetz 138kV East Bus,87s Gaetz 240kV East Bus | 2018-07-30 10:00 | 2018-08-02 16:00 | N | Y | replace A87/240BE protection and perform test trips to 87s2352, 87s1252, 87s1052, 87s852, & 87s252 | Bus, Circuit Breaker, Transformer, Line |  | Replace A87/240BE protection and perform test trips to 87s2352, 87s1252, 87s1052, 87s852, & 87s252 | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s T2 (17s Benalto) | 2018-07-30 12:00 | 2018-07-30 17:00 | N | Y | emergency outage, CT wiring changes/testing | Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 945s T1 (945s Sunshine Village) | 2018-07-30 12:30 | 2018-08-02 16:30 | N | N | change out the 25kV bushings on T1, doble and maintain | Transformer |  |  | For Information Only
ALTALINK | 310p 952 (310p Sundance),310p 852 (310p Sundance) | 2018-07-30 13:15 | 2018-08-02 16:45 | N | Y | migrate and commission protections, alarms, status, controls, metering and remote access to new RTU and LAN | Circuit Breaker |  | Migrate and commission all G3 stub bus protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission 310p3G & T3 alarms. | 240 kV
ATCO | 743s 701T (743s Sarah Lake),743s 701 (743s Sarah Lake),743s 704 (743s Sarah Lake),743s 605 (743s Sarah Lake),743s 501 (743s Sarah Lake) | 2018-07-31 07:00 | 2018-08-01 17:00 | N | N | replace insulators, switch maintenance | Circuit Breaker, Transformer |  | Replace insulators, Switch Maintenance | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 767L (310p Sundance - 767L50) | 2018-07-31 08:00 | 2018-08-01 14:00 | N | N | disconnect 471s from 767L at 310p | Line |  | Disconnect 471s from 767L at 310p. 21s & 635s to be fed via 320p. | Pre-Condition
ATCO | 796s 701T (796s Nipisi) | 2018-07-31 08:00 | 2018-08-27 14:00 | N | N | emergency repair | Transformer |  | EMERGENCY REPAIR | For Information Only
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap),6L12 (6L25 tap - 774s Monitor) | 2018-07-31 08:00 | 2018-09-11 12:30 | N | N | install new gang switches | Line |  | to install new gang switches 6L12D1(Sullivan) to 6L12D5(Monitor) including 773S Coronation(6L25) To Salvage the old Gang Switches | Pre-Condition, For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2018-07-31 08:00 | 2018-08-06 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ALTALINK | 723L (69s North Barrhead - 723L133),69s723E Open (Affecting 723L) | 2018-07-31 09:00 | 2018-07-31 12:00 | N | N | MPLS upgrade node | Terminal Equipment, Line |  | Netcom and Field Ops will be upgrading MPLS nodes A and B at 69S Barrhead. During this outage the RTU to 69S will be lost 15 minutes. 723L TPR A and B will be out of servcie for 15 minutes 913L TPR have redundant channels and will be down one at a time, while 1201L TPR (disabled) will be down for 15 minutes. | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2018-07-31 11:10 | 2018-08-09 14:32 | N | Y | forced outage | Line | PEAK COS outage ID:1-00586446 PEAK COS path de-rate ID:1-00586447 (N-S), (S-N):1-00586448 |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2018-08-01 07:00 | 2018-08-02 17:00 | N | Y | install new piles underneath 180L for new 15s NGR and 25 kV cable structure | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
Saskpower | SaskPower C1S | 2018-08-01 07:00 | 2018-08-03 19:00 | N | N | maintenance | Line |  |  | Limits ATC
GWPCORP | 243S Soderglen Wind Farm | 2018-08-01 07:00 | 2018-08-02 17:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ALTALINK | 104S Watson Creek,615L (602s Cold Creek - 104s Watson Creek) | 2018-08-01 07:30 | 2018-08-02 18:00 | N | N | new structure 143 installation | Line, Station |  | 615L Transmission Line Outage for new Structure 143 installation. 492L1 Bypass Structure Installation and tie-in with 615L. | For Information Only
ATCO | 716s 701C (716s Lloydminster) | 2018-08-01 08:00 | 2018-08-02 16:00 | N | N | forced outage- 51N protection issue | Shunts |  |  | For Information Only
ATCO | 2075s ACF22 (2075s Newell) | 2018-08-02 07:00 | 2018-08-03 15:30 | N | Y | filter bank maintenance & inspection | Shunts |  | Filter Bank Maintenance and Inspection, One A type filter needs to be available at all times so we will lose redundancy when ACF22 is out of service. ACF 12 will still be available. Power Cap will be at 1000 MW @ 500 kV when only one A type filter is available. | 240 kV
ALTALINK | 708L (233s Beamer - 708L88N) | 2018-08-02 07:30 | 2018-08-03 17:30 | N | Y | 708L bypass cutover/ create open points 'C' & 'D' | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 801s 911 (801s Anderson) | 2018-08-02 08:00 | 2018-08-02 17:00 | N | Y | emergency repairs to relieve leaking device on breaker | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 708L (233s Beamer - 708L88N) | 2018-08-03 17:30 | 2018-08-09 08:30 | N | Y | salvaging old switches 708L88X & 708L88N | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2018-08-04 04:00 | 2018-08-04 07:00 | N | N | panel replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2018-08-04 07:00 | 2018-08-04 10:00 | N | N | panel replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2018-08-04 08:00 | 2018-08-04 10:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2018-08-04 10:00 | 2018-08-04 13:00 | N | N | panel replacement | Line |  |  | Pre-Condition, Overload
ENMAX | 1.6TR (ENMAX 1) | 2018-08-04 10:00 | 2018-08-04 12:00 | N | N | Fall Substation Washing, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2018-08-04 12:00 | 2018-08-04 15:00 | N | N | Fall Substation Washing, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2018-08-04 15:00 | 2018-08-04 18:00 | N | N | fall substation washing, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 162.1TR (ENMAX 162s Beddington),162s Beddington 138 kV North Bus | 2018-08-06 08:00 | 2018-08-13 12:00 | N | Y | doble 162PT138-T1, dashpot checks RB80, Fall washing | Transformer, Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 162.1TR (ENMAX 162s Beddington),162s Beddington 240 kV North Bus | 2018-08-06 08:00 | 2018-08-17 16:00 | N | Y | oil sampling and doble test transformer | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 2029s ACF21 (2029s Heathfield) | 2018-08-07 07:00 | 2018-08-08 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter Bank Maintenance and Inspection, redundant filter banks in service, no system impact | Pre-Condition, For Information Only, 500 kV
ATCO | 2075s ACF23 (2075s Newell) | 2018-08-07 07:00 | 2018-08-08 15:30 | N | Y | filter bank inspection/maintenance | Shunts |  | Filter bank inspection/maintenance, redundant filter ACF13 (B filter) will remain available | 240 kV, Pre-Condition, For Information Only
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2018-08-07 07:00 | 2018-08-09 17:00 | N | N | change arms insulators/fix conductor/shield wire. | Line |  | change arms insulators/fix conductor/shield wire. | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 754L (245s Seebe - 754L65A) | 2018-08-07 07:15 | 2018-08-16 17:45 | N | Y | structure replacements (Str 34-64) | Line |  |  | Overload
ENMAX | 13.1TR (ENMAX 13) | 2018-08-07 08:00 | 2018-08-17 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ENMAX | 39.4TR (ENMAX 39) | 2018-08-07 08:00 | 2018-08-17 16:00 | N | N | panel replacement | Transformer |  |  | For Information Only
ALTALINK | 89s 1052 (89s Ellerslie) | 2018-08-07 08:30 | 2018-08-07 13:30 | N | Y | 89s1052 close dashpot empty | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
SUNCOR | 29EDD-65 240 KV BUS | 2018-08-07 08:30 | 2018-08-10 18:00 | N | Y | forced outage | Bus |  |  | 240 kV
ATCO | 727s 601 (727s Kinuso) | 2018-08-07 09:00 | 2018-08-09 15:00 | N | N | breaker oil testing | Circuit Breaker |  | BREAKER MIN OIL HLC PARTIAL TESTING @ KINUSO 727S 601 Breaker test and relay commission for Project The out of service and breaker for 6L91 will be utilized for the construction of the new 727S Kinuso. 6L57 will be transferred to breaker 601 for the construction phase. These are just function checks and relay setting transfers to ensure system reliability before the bypass is completed. Breaker and relays are currently out of service | For Information Only
ALTALINK | 310p 252 (310p Sundance),310p 352 (310p Sundance) | 2018-08-07 09:15 | 2018-08-09 15:45 | N | Y | migrate and commission to new RTU and LAN | Circuit Breaker |  | Migrate and commission all G2 stub bus protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission 310p2G & T2 alarms. | 240 kV, For Information Only
ATCO | 939s 904 (939s Livock) | 2018-08-07 10:00 | 2018-08-09 17:00 | N | Y | emergency repair leaking breaker 904 @ 939S | Circuit Breaker |  | Emergency Repair Breaker 904 @ 939S Livock This leak is causing a Huge Environmental Concern (Need to repair before reportable release limits are reached and then we do have a breaker failure) Repair and Top up Breaker 904. This Breaker has a long history of a slow leak. The Breaker is currently low and will need a top up for safe operation. We will be again attempting a permanent repair during this outage 240 KV Bus Open for duration of repair | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek) | 2018-08-07 12:00 | 2018-08-12 17:00 | N | N | replace rotten cross-arms | Line |  | Replace rotten crossarms, (June 8-12, 2018 start at 08:00, Work finished each day @17:00 Can be restored evenings if required in an emergency) | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 510S Sunnybrook,511s Crossing,1325L (510s Sunnybrook - 511s Crossings),510s T11 (510s Sunnybrook),511s T11 (511s Crossings) | 2018-08-07 12:00 | 2018-08-09 18:00 | N | Y | 510s and 511s valve hall inspection and maintenance | Line, Transformer, Station |  |  | 240 kV, 500 kV
ALTALINK | 358s T1 (358s Amoco Brazeau) | 2018-08-07 17:00 | 2018-08-29 10:00 | N | N | transformer maintenance, insulator replacement, arrestor replacement, adding and test controls during re-energization switching | Transformer |  |  | For Information Only
ALTALINK | 778L (217s North Red Deer - 87s Gaetz),768L (217s North Red Deer - 209s Timberlands) | 2018-08-08 07:00 | 2018-08-31 13:00 | N | Y | install OPGW and salvage existing o/h wire on structure tops (str12-217s) | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B240-D133 (ENMAX 65) | 2018-08-08 08:00 | 2018-08-10 16:00 | N | Y | HV breaker maintenance and remediate bird mess inside insulating blankets | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 650s 952 (650s Hansman Lake) | 2018-08-08 08:00 | 2018-08-08 14:30 | N | Y | change faulty gas gauge | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 103s T1 (103s Goose Lake),103s 452 (103s Goose Lake),103s 1152 (103s Goose Lake),103s 252 (103s Goose Lake),103s Goose Lake 240kV Bus 1 | 2018-08-08 09:00 | 2018-08-08 15:00 | N | Y | remove voltage test leads from 240kV bus | Circuit Breaker, Transformer, Bus |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
AESO-SC | DT | 2018-08-08 10:00 | 2018-08-08 12:00 | N | N | migrated from the SDC back to the PDC | SCInternal |  |  | For Information Only
AESO-SC | CROW | 2018-08-08 12:00 | 2018-08-08 13:00 | N | N | CROW Prod Migration from SDC to PDC | SCInternal |  |  | For Information Only
NWE | Marias Shunt Capacitor | 2018-08-08 18:00 | 2018-09-28 18:30 | N | N | bank #3, send in damaged relay for repair | Shunts |  |  | For Information Only
ATCO | 2029s ACF22 (2029s Heathfield) | 2018-08-09 07:00 | 2018-08-10 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter Bank Maintenance and Inspection, redundant filter banks in service, no system impact. | 240 kV
ATCO | 2075s ACF24 (2075s Newell) | 2018-08-09 07:00 | 2018-08-10 15:30 | N | Y | filter bank inspection/maintenance | Shunts |  | Filter bank inspection/maintenance, No redundancy of Type C filter during outage. ACF14 will still be available. | 240 kV
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2018-08-09 07:00 | 2018-08-09 17:00 | N | N | install temp bypass for construction of new Kinuso substation | Line |  | Install temp bypass for construction of new Kinuso substation | Firm Load Loss, Creates Radial Feeds
AESO-SC | EMS | 2018-08-09 08:00 | 2018-08-09 12:00 | N | N | configuration change on the proddigi devices (Digi`s) | SCInternal |  |  | For Information Only
ALTALINK | 708L (233s Beamer - 708L88N) | 2018-08-09 08:30 | 2018-08-10 17:30 | N | Y | closing open points 'C' & 'D' and cutting the temporary bypass free | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
AESO-SC | EMS | 2018-08-09 09:10 | 2018-08-09 12:10 | N | N | SDC EMS production Fortigate firewalls need to be updated to FortiOS 5.4.6 | SCInternal |  |  | For Information Only
BCH | 5L71 (Mica Creek - Nicola) | 2018-08-12 09:00 | 2018-10-21 16:00 | N | Y | switchgear roof replacement | Line | BC Outage Peak RC COS: 1-00587013 AB Peak RC COS# : 1-00589742 (W>E), 1-00589743 (E>W) |  | Limits ATC, 500 kV
ALTALINK | 149s C1 (149s Nisku) | 2018-08-13 07:30 | 2018-08-16 17:00 | N | N | replacement of C1 A protection relay with retrofit relay in existing module | Shunts |  |  | For Information Only
ENMAXGPI | 134S Taber Wind Farm | 2018-08-13 08:00 | 2018-08-17 15:00 | N | N | substation maintenance outage | Station |  | Purpose: The outage is requested to test and maintain substation equipment as per our 4yr maintenance schedule practice. | Affects Visibility
ENMAX | 15.1TR (ENMAX 15) | 2018-08-13 08:00 | 2018-08-25 16:00 | N | N | HV bushing replacement and HV CT addition | Transformer |  |  | For Information Only
ATCO | 7L20 (810s Dome Cutbank - 740s H.R.Milner) | 2018-08-13 08:00 | 2018-08-16 17:00 | N | Y | changing over rated XARMS | Line |  | Changing over rated XARMS | Pre-Condition, Restricts Generation, Firm Load Loss
ATCO | 7L85 (803s Bullpound - 801s Anderson) | 2018-08-13 08:00 | 2018-08-20 17:00 | N | N | change arms insulators | Line |  | change arms insulators | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2018-08-13 08:00 | 2018-08-13 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | For Information Only
ENMAX | 41.2TR (ENMAX 41) | 2018-08-13 08:00 | 2018-08-18 16:00 | N | N | HV CT addition | Transformer |  |  | For Information Only
Syncrude | D05 T2 (D05 Syncrude),D05 78 (D05 D05) | 2018-08-13 09:00 | 2018-08-22 22:00 | N | Y | urgent adjustment on protection settings | Transformer, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, For Information Only
REDDEER | 247s T2 (247s Piper Creek) | 2018-08-13 09:00 | 2018-08-24 15:30 | N | N | transformer repair | Transformer |  |  | For Information Only
ATCO | 840S McNeill Station | 2018-08-13 09:00 | 2018-08-23 15:30 | N | Y | arrestor install and bird proofing | Station |  | 2018 McNeill Fall T/A. Arrestor install and Bird Proofing | Limits ATC
ALTALINK | 510s ACF21 (510s Sunnybrook) | 2018-08-13 09:30 | 2018-08-17 17:30 | N | Y | inspection | Shunts |  |  | For Information Only, 500 kV
AESO-SC | DT | 2018-08-13 10:00 | 2018-08-13 12:00 | N | N | migrating DT to the Secondary Data Centre (SDC) | SCInternal |  |  | For Information Only
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside) | 2018-08-13 11:00 | 2018-08-23 16:00 | N | Y | 89s452 breaker replacement and 89s73 PT replacement | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 266s 1037L FSC (266s SC1) | 2018-08-13 11:30 | 2018-08-16 12:00 | N | Y | yearly maintenance | Shunts |  |  | 240 kV
ALTALINK | 678s T1 (678s Okotoks) | 2018-08-13 11:30 | 2018-08-16 17:30 | N | N | T1 bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 410s T2 (410s Josephburg) | 2018-08-13 12:30 | 2018-08-17 17:30 | N | Y | transformer bushing replacement & maintenance work | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2018-08-13 13:00 | 2018-08-16 16:00 | N | Y | migrate and commission line protections | Line |  | Migrate and commission all L7 - 922L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L7 alarms. | 240 kV, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2018-08-14 07:00 | 2018-09-13 18:00 | N | N | maintenance components (str 103-394) | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 9L93 (972s Tinchebray - 615s Halkirk) | 2018-08-14 07:00 | 2018-08-15 19:00 | N | Y | upgrade on Kirkkey interlock on 89-T11 DS | Line |  | CPC will be performing minor upgrade on Kirkkey Interlock on 89-T11 DS at 615s Halkirk | 240 kV, Restricts Generation
ALTALINK | 277s T1 (277s Hayter),277s T2 (277s Hayter) | 2018-08-14 07:30 | 2018-08-14 10:30 | N | Y | restore 267s748E | Transformer |  |  | Restricts Generation
ALTALINK | 615L (602s Cold Creek - 104s Watson Creek) | 2018-08-14 07:30 | 2018-08-15 18:00 | N | N | outage for structure 143 caisson foundation drilling near 104s | Line |  | 615L Transmission Line Outage for Structure 143 caisson foundation drilling near 104s. Clearance required to safely drill piers and install rebar cage. Connect new 492L1 to 615L near 602s | Firm Load Loss, Creates Radial Feeds
ALTALINK | 304s T1 (304s Shell Limestone) | 2018-08-14 07:45 | 2018-08-15 17:45 | N | N | replace bushings on T1 | Transformer |  |  | For Information Only
ALTALINK | 801L (358s Amoco Brazeau - 801L302),844L (358s Amoco Brazeau - 477s Amoco West Pembina),358s 138kV Bus (358s Amoco Brazeau) | 2018-08-14 08:00 | 2018-08-14 13:00 | N | N | Switch maintenance - 358s19. Coordinated with TransAlta. | Bus, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2018-08-14 08:00 | 2018-08-14 16:00 | N | N | HV breaker maintenance 14CS138-14.1CAP | Shunts |  |  | For Information Only
ALTALINK | 28s T2 (28s West Brooks) | 2018-08-14 12:00 | 2018-08-16 17:00 | N | Y | replace faulty Qualitrol 910 relay with 930 model and 3 sensor measurement device. | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2018-08-15 08:00 | 2018-08-15 16:00 | N | N | HV breaker maintenance 20B138-1.81L | Line |  |  | For Information Only
ALTALINK | 266s 1038L FSC (266s SC1) | 2018-08-15 09:00 | 2018-08-16 16:00 | N | Y | yearly maintenance | Shunts |  |  | 240 kV
AESO-SC | DT | 2018-08-15 10:00 | 2018-08-15 12:00 | N | N | DT will be migrated from the SDC back to the PDC | SCInternal |  |  | For Information Only
ATCO | 740s 704A (740s H.R. Milner),740s 704B (740s H.R. Milner),740s 704Y (740s H.R. Milner) | 2018-08-15 10:00 | 2018-08-15 12:00 | N | N | PCB sample | Switch |  | 740S 704PT PCB Sample 7L20 will be already out of service for Transmission line crew (2-46319) | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2018-08-15 23:00 | 2018-08-16 03:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2018-08-16 03:00 | 2018-08-16 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2018-08-16 08:00 | 2018-08-16 16:00 | N | N | HV breaker maintenance 16B69-15.62 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11) | 2018-08-18 08:00 | 2018-08-19 16:00 | N | N | install new card on T60, test HV slipover CTs, check reversing switch | Transformer |  |  | For Information Only
EPCOR | Victoria V729 (Victoria) | 2018-08-19 07:00 | 2018-08-19 17:00 | N | N | maint/disconnect repair | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24) | 2018-08-19 08:00 | 2018-08-19 16:00 | N | N | doble 24B138-24.81, repair or replace center phase mech cover | Line |  | doble 24B138-24.81, repair or replace center phase mech cover [AVANTIS] 24B13-24.81 | Pre-Condition
EPCOR | 330p 1201 (330p Genesee) | 2018-08-20 07:00 | 2018-08-21 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | For Information Only, 500 kV
ALTALINK | 305s C1 (305s Acheson) | 2018-08-20 07:30 | 2018-08-23 17:00 | N | N | replacement of C1 A protection relay with retrofit relay in existing module | Shunts |  |  | Pre-Condition
ALTALINK | 740L (39s-426s-414s-527s-101s) | 2018-08-20 07:30 | 2018-08-26 17:30 | N | N | installing new switch | Line |  | Installing new switch 740L235B and two new deadends keeping all customers online | For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2018-08-20 08:00 | 2018-08-20 16:00 | N | N | rewire circuitry for 15.1TR | Line |  | Rewire circuitry for 15.1TR Diff installation. 15.1TR already out of service. Distance protection removed from 15.62L (15sub end) while PTs are offline, line remains protected from 16s end. | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L20 (810s Dome Cutbank - 740s H.R.Milner) | 2018-08-20 08:00 | 2018-08-23 17:00 | N | Y | changing over rated XARMS | Line |  | Changing over rated XARMS | Pre-Condition, Restricts Generation, Firm Load Loss
ENMAX | 36.3TR (ENMAX 36) | 2018-08-20 08:00 | 2018-08-24 16:00 | N | N | transformer maintenance | Transformer |  | Doble test transformer. Secondary cable tests. Transformer maintenance | For Information Only
BCH | 1L274 (EFT - 1D2L274) | 2018-08-20 08:00 | 2018-08-31 16:00 | N | Y | annual plan request F19 | Line |  |  | Pre-Condition, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 765L (74s Janet - 151s Strathmore),151s 765W (151s Strathmore),74s 765E (74s Janet) | 2018-08-20 09:00 | 2018-08-30 16:00 | N | N | connect new 419s | Circuit Breaker, Line | Connect new 419s to 138KV system and commission. Rename 765L (419s to 74s) to 691L on Aug 22 |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-34 Edd34Sub,29PL9-15 (29EDD-56 - 29EDD-34) | 2018-08-20 09:00 | 2018-09-09 18:00 | N | Y | maintenance on breakers, bus CT and switches | Line, Station |  | planned maintenance on 29EDD-34 and 29PL9-15: - 5 Year mtce - 5 year mtce on breakers, bus CT and switches | 240 kV, For Information Only
ALTALINK | 325s T2 (325s Leduc) | 2018-08-20 09:30 | 2018-08-23 17:30 | N | N | terminate & commission new 1052L U/G cables | Transformer |  | terminate & commission new 1052L U/G cables to existing 325s1052 breaker in switchgear building 2 | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2018-08-20 09:30 | 2018-08-22 12:30 | N | Y | inspect the filter bank | Shunts |  |  | 500 kV
ALTALINK, ENMAX | 74s T1 (74s Janet),932L (74s Janet - 162s Beddington),74s Janet 240kV Bus 1,929L (74S Janet - 287s Hazelwood) | 2018-08-20 10:00 | 2018-08-20 15:45 | N | Y | cut open point 'A' on 240kV bus between 74s48 and 74s20N | Transformer, Line, Bus |  | Cut Open Point 'A' on 240kV Bus between 74s48 and 74s20N. Bus Required in order to replace 74s252 Ct due to proximity | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 42s T1 (42s Sarcee) | 2018-08-20 10:00 | 2018-08-24 15:00 | N | Y | repairs to control building | Transformer |  |  | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station),89s 252 (89s Ellerslie) | 2018-08-20 10:00 | 2018-08-20 11:00 | N | Y | required for replacing DC fuse holder in junction box for existing outage 1057L | Circuit Breaker, Line |  | required for replacing DC fuse holder in junction box for existing outage 1057L GOI. Junction box shipped with wrong fuse size holder. 89s252 breaker is required to be open to avoid protection issues with DC offline. No work is being performed around the breaker so just a breaker open advice is required | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar),71s 1352 (71s Lamoureux),71s 1252 (71s Lamoureux) | 2018-08-20 10:30 | 2018-08-23 16:30 | N | Y | replace PT's | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
ALTALINK | 729L (542s Ervick - 729L13A) | 2018-08-20 10:30 | 2018-08-20 18:00 | N | Y | installing bird diverters on two spans of OHSW structures #138 - #140 | Line |  | installing bird diverters on two spans of OHSW between Structures #138 - #140 | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s T2 (39s Bickerdike) | 2018-08-20 11:00 | 2018-08-23 18:00 | N | Y | replace tertiary bushing | Transformer |  | Replace T2 Tertiary Bushing | 240 kV, Pre-Condition
ALTALINK | 900L (63s Red Deer - 17s Benalto),17s 10 (17s Benalto),17s 1652 (17s Benalto) | 2018-08-20 11:00 | 2018-08-20 17:00 | N | Y | 17s900E unable to open and needs to be adjusted | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 331s T1 (331s Ponoka) | 2018-08-20 11:00 | 2018-08-22 18:00 | N | N | doble test on T1 and VR1 | Transformer |  |  | For Information Only
ALTALINK | 895s T3 (895s Suffield) | 2018-08-20 12:00 | 2018-08-22 16:00 | N | N | doble and maintain, fix counter and valve on tapchanger for oil sampling | Transformer |  |  | For Information Only
ALTALINK | 266s 1038L FSC (266s SC1) | 2018-08-20 12:00 | 2018-08-23 15:30 | N | Y | trouble shoot for leaky capacitors and perform relay maintenance | Shunts |  | Trouble shoot for leaky capacitors and perform relay maintenance | 240 kV
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2018-08-20 12:00 | 2018-08-23 17:00 | N | N | TC filter leak CAT 3 | Transformer |  | TX 18348 LTC FPE/FPE 138/25KV42MVA. ADD: TX 18348 LTC FPE/FPE 138/25KV42MVA, 54s T1 Tx18348 TC filter | For Information Only
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm),608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm),138s Windy Flats 138kV Bus 2 | 2018-08-20 12:00 | 2018-08-20 17:00 | N | Y | create open point on SST1 primary | Bus, Line |  | Create open point on SST1 primary | 240 kV, For Information Only
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-08-20 13:00 | 2018-08-23 08:00 | N | N | new 492L1 bypass structure tie-in with 615L | Line |  | 847L Transmission Line Outage for new 492L1 bypass structure tie-in with 615L. 492L1 will be locked open & unusable until later date | Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2152 (310p Sundance),310p 2052 (310p Sundance) | 2018-08-20 13:15 | 2018-08-23 15:45 | N | Y | migrate and commission protections, alarms, status, controls, metering and remote access to new RTU and LAN | Circuit Breaker |  | Migrate and commission all G5 stub bus protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission 310p5G & T5 alarms. | 240 kV, For Information Only
ALTALINK, ENMAX | 74s T1 (74s Janet),932L (74s Janet - 162s Beddington),929L (74S Janet - 287s Hazelwood) | 2018-08-20 15:45 | 2018-08-30 10:30 | N | Y | bus outage required in order to replace 74s252 CT due to proximity | Transformer, Line |  | Bus outage required in order to replace 74s252 CT due to proximity. | Pre-Condition, Overload, Contingency Requires Mitigation, For Information Only
ALTALINK | 138S Windy Flats | 2018-08-20 16:00 | 2018-08-23 10:00 | N | N | station service | Station |  | Arc Flash mitigation on Station Service secondary devices. | For Information Only
ALTALINK | 754L (245s Seebe - 985s Exshaw - 437s Baymag) | 2018-08-21 06:30 | 2018-08-22 07:30 | N | Y | customer requested outage | Line |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2018-08-21 07:00 | 2018-08-24 18:00 | N | N | replace two structures for road clearance between structures #335 & #484 | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station),1055L (816s Petrolia - 629s Argyll Transfer Station) | 2018-08-21 07:00 | 2018-08-21 17:00 | N | Y | emergency - low SF6 | Line |  | Emergency Work | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 535s 6452 (535s Joffre) | 2018-08-21 08:00 | 2018-08-21 17:00 | N | N | top up SF6 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 184s 34 (184s Petro Canada Edmonton) | 2018-08-21 08:30 | 2018-08-21 17:00 | N | N | 184s34 (CB1326) SF6 138kV HGF | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1238L (510s Sunnybrook - 330p Genesee) | 2018-08-22 07:00 | 2018-08-22 17:00 | N | Y | breaker maintenance | Line |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
NextEra | 114S Ghost Pine | 2018-08-22 07:00 | 2018-08-22 15:00 | N | N | fault relay and padmount transformer testing | Station |  |  | Restricts Generation, For Information Only
ALTALINK | 250p11 (250p Bighorn Plant),250p22 (250p Bighorn Plant) | 2018-08-22 07:00 | 2018-08-23 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 718L (250p Bighorn Plant - 263s Strachan) | 2018-08-22 08:00 | 2018-08-22 16:30 | N | Y | install new DDR wiring and testing inputs, status and analogs from protections | Line |  |  | Restricts Generation
ALTALINK | 250P T40 (250P Bighorn Plant) | 2018-08-22 08:30 | 2018-08-22 16:00 | N | N | remove protection trips from breaker, perform setting changes & verifying trip string | Transformer |  |  | For Information Only
ALTALINK | 510s ACF13 (510s Sunnybrook) | 2018-08-22 12:30 | 2018-08-23 17:30 | N | Y | inspect the filter bank | Shunts |  |  | 500 kV
ALTALINK | 221s T1 (221s Sunken Lake) | 2018-08-23 06:00 | 2018-08-23 18:00 | N | N | outage to add 4" bus connection to customers 4.16KV bus | Transformer |  |  | For Information Only
ALTALINK | 221s T3 (221s Sunken Lake) | 2018-08-23 06:00 | 2018-08-23 18:00 | N | N | customer work downstream of T3 | Transformer |  |  | For Information Only
EPCOR | 814s B2401 (814s Bellamy) | 2018-08-23 07:00 | 2018-08-23 17:00 | N | Y | emergency - low SF6 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 170L (632s Russell - 799s Coleman) | 2018-08-23 07:00 | 2018-08-23 18:00 | N | Y | emergency repair; cross arm/ insulators | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 330p 1203 (330p Genesee) | 2018-08-23 07:00 | 2018-08-24 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | For Information Only, 500 kV
ALTALINK | 615L (602s Cold Creek - 104s Watson Creek) | 2018-08-23 07:30 | 2018-08-24 18:00 | N | N | new structure 143 installation and demo of old structure 143 | Line |  |  | For Information Only
ALTALINK | 756L (87s Gaetz - 535s Joffre),87s 152 (87s Gaetz),87s 252 (87s Gaetz) | 2018-08-23 08:00 | 2018-08-23 14:00 | N | N | adjust 87s3 138kV switch | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2018-08-23 08:00 | 2018-08-24 16:00 | N | N | remove bird's nest from structure, doble 32B138-31.84-CT | Line, Transformer |  |  | Pre-Condition, For Information Only
ENMAX | 23.3TR (ENMAX 23) | 2018-08-23 08:00 | 2018-08-24 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-08-23 08:00 | 2018-08-23 12:00 | N | N | close open point 'B' using live-line techniques for 847L outage Aug 20-23 (ref# 260339) | Line | 847L Transmission Line Outage for new 492L1 bypass structure tie-in with 615L. 492L1 will be locked open & unusable until later date |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm),608L (138s Windy Flats - 418s Ardenville - 528s Blue Trail Wind Farm),138S T2 (138s Windy Flats) | 2018-08-23 09:00 | 2018-08-23 14:00 | N | Y | close open point on SST1 primary | Transformer, Line |  |  | 240 kV, Restricts Generation, For Information Only
ENMAX | 28.1TR (ENMAX 28),28.5TR (ENMAX 28) | 2018-08-26 08:00 | 2018-08-26 16:00 | N | N | hotspot repair SW8 and LV switch maintenance | Transformer |  | ENMAX 28.1TR. 8-28.15. 8-28.14. 8-28.13. 8-28.12. 28.5TR move and re-wire a PT on sec. side of TR. Hotspot repair SW8. LV SW maintenance. Check reversing switch | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2018-08-26 17:00 | 2018-09-30 16:00 | N | N | forced outage | Transformer |  | Transformer started smoking after being put back into service.Replace faulted PT. Retest transformer. | For Information Only
ATCO | 2029s ACF14 (2029s Heathfield) | 2018-08-27 07:00 | 2018-08-28 15:30 | N | Y | shunt reactor inspection & testing. | Shunts |  | ACF 14 Shunt reactor inspection & testing. | For Information Only
EPCOR | Strathcona T1 (Strathcona),72RS5 (Rossdale - Strathcona) | 2018-08-27 07:00 | 2018-09-23 17:00 | N | N | transformer commissioning | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | E511s VictoriaT4 (511s Victoria),72RV2 (Rossdale - 511s Victoria),72RV4 (Rossdale - 511s Victoria),72RV6 (Rossdale - 511s Victoria) | 2018-08-27 07:00 | 2018-09-12 22:00 | N | N | cutting over and commissioning new protection | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
BLACKSPRING | 485s C1 (485s Blackspring),485s C2 (485s Blackspring),485s DVAR1 (485s Blacksprings),485s DVAR2 (485s Blacksprings) | 2018-08-27 08:00 | 2018-08-31 17:00 | N | Y | dstatcom annual maintenance | Shunts |  |  | For Information Only
ENMAX | 162s Beddington 138 kV South Bus | 2018-08-27 08:00 | 2018-09-04 12:00 | N | Y | fall substation washing and upgrade T60 settings | Bus |  | HV SW maint SW88, Doble 162PT138-T2, fall substation washing and Upgrade T60 settings | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.2TR (ENMAX 162 Beddington) | 2018-08-27 08:00 | 2018-09-07 16:00 | N | Y | tap changer inspection and transformer maintenance | Transformer |  | Tapchanger Inspection. Doble Test Transformer. Transformer maintenance. Check reversing SW. HV SW maint SW88 . 162.2TR gas relay testing. Doble 162PT138-T2. Fall wash?? Upgrade T60 settings. Doble 162PT138-T2. | 240 kV, Pre-Condition, Overload
ATCO | 7L20 (810s Dome Cutbank - 740s H.R.Milner) | 2018-08-27 08:00 | 2018-08-30 17:00 | N | Y | changing over rated XARMS | Line |  | Changing over rated XARMS | Restricts Generation, Firm Load Loss
ENMAX | 24.1TR (ENMAX 24) | 2018-08-27 08:00 | 2018-08-31 16:00 | N | N | HV CT addition | Transformer |  |  | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2018-08-27 08:00 | 2018-08-29 16:00 | N | N | tapchanger inspection | Transformer |  | Tapchanger inspection. 38.2 TR level gauge cable is damaged. Cable is supplied from shop. Oilsampling TR, TC, H3. 38.2TR CT Junction box leaks into control cabinet | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2018-08-27 08:00 | 2018-09-07 14:00 | N | N | panel replacement | Transformer |  |  | For Information Only
ENMAX | 6.80L (ENMAX 35 - ENMAX 6) | 2018-08-27 08:00 | 2018-08-31 16:00 | N | N | repair leak | Line |  |  | Firm Load Loss, Creates Radial Feeds
REDDEER | 217s T2 (217s North Red Deer) | 2018-08-27 09:00 | 2018-08-31 15:30 | N | N | oltc maintenance | Transformer |  |  | For Information Only
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2018-08-27 09:00 | 2018-08-27 18:00 | N | N | emergency repair broken strands | Line |  | Emergency Repair; repair broken strands (Str502) | Overload, Contingency Requires Mitigation
ALTALINK | 77s 40 (77s Sagitawah) | 2018-08-27 09:00 | 2018-08-31 17:00 | N | Y | replacing CT's | Circuit Breaker |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 781L (172s Sherritt - 71s Lamoureux),71s 152 (71s Lamoureux),71s 252 (71s Lamoureux),71s 781E (71s Lamoureux) | 2018-08-27 09:30 | 2018-08-30 16:30 | N | N | replace PT's | Line, Circuit Breaker, Switch |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap) | 2018-08-27 10:00 | 2018-08-27 13:00 | N | N | pole replacement | Line |  | POLE REPLACEMENT ON 6L03 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 28s R1 (28s West Brooks),28s 44 (28s West Brooks) | 2018-08-27 12:00 | 2018-08-28 17:00 | N | Y | maintain 240kV SF6 breaker | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 989L (310p Sundance - 77s Sagitawah),310p 2652 (310p Sundance),310p 2752 (310p Sundance) | 2018-08-27 13:00 | 2018-08-30 16:00 | N | Y | migrate and commission all L1 - 974L at 310P Sundance | Line, Circuit Breaker |  | Migrate and commission all L1 - 974L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L1 alarms. | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2018-08-27 13:30 | 2018-08-30 17:00 | N | N | change out fiberglass cross arms | Line |  | Change out fiberglass cross arms | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 86s T1 (86s Bigstone),804L (86s Bigstone - 40s Wetaskiwin),805L (964s Pigeon Lake - 86s Bigstone),86s Bigstone 138kV bus | 2018-08-28 08:00 | 2018-08-29 16:00 | N | Y | replace one phase of PT32064 associated with SS2 and PT cables terminate in junction box 86s30 | Transformer, Bus, Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 839s 701T (839s Daishowa Plant) | 2018-08-28 08:30 | 2018-08-28 16:00 | N | Y | oil reclamation outage to set up and start oil processing | Transformer |  | 839S 701T Oil Reclamation Outage for Setup Set Up and start oil processing 701T Out of Service for the Duration of the Work | Pre-Condition, Restricts Generation
ATCO | 9L29 (946s Oakland - 963s Coyote Lake),963s 901 (963s Coyote Lake) | 2018-08-28 09:30 | 2018-08-29 16:00 | N | Y | CT ratio & relay settings changes on equipment associated with 901CT and 50BF/901 relay | Line, Circuit Breaker |  | 963S Coyote 901CT Ratio Change Project CT Ration & Relay Settings Changes on equipment Associated with 901CT and 50BF/901 Relay | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | Rossdale C2 (Rossdale) | 2018-08-28 17:00 | 2018-09-07 08:00 | N | N | forced outage | Shunts |  |  | For Information Only
ALTALINK, NRGREEN | 259S Chickadee Creek,199L (268s Whitecourt - 199L187B),199L (347s Fox Creek - 199L187B) | 2018-08-29 07:30 | 2018-08-29 12:30 | N | Y | create open point at str 199L187A | Line, Station |  | Outage to create open point at str 199L187A | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 720L (347s Fox Creek - 397s Benbow),7L199 (347s Fox Creek - 741s Fox Creek),347s Fox Creek 138 kV Bus,199L (347s Fox Creek - Open Point A) | 2018-08-29 07:30 | 2018-08-30 17:30 | N | Y | replace station service PT and secondary wiring | Bus, Line |  | replace station service PT and secondary wiring | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31) | 2018-08-29 08:00 | 2018-08-29 16:00 | N | N | blown fuse | Shunts |  | Neutral imbalance alarm, blown fuse
ALTALINK | 368s T1 (368s Burdett) | 2018-08-29 08:30 | 2018-08-30 16:30 | N | N | doble & maintenance | Transformer |  | Doble, maintain, upgrade temperature monitor equipment | For Information Only
ALTALINK | 601L (275s Jenner - 230s Wardlow) | 2018-08-29 11:00 | 2018-08-29 16:00 | N | N | inspect main breaker | Line |  |  | Creates Radial Feeds
ALTALINK | 199L (347s Fox Creek - Open Point A) | 2018-08-29 12:30 | 2018-09-05 07:30 | N | N | add new airbreak at str 199L187 | Line |  | Add new airbreak at str 199L187 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2018-08-29 13:00 | 2018-08-29 16:00 | N | N | wire fraying | Line |  | 6L57 has some wire fraying and in danger of contacting the 25kv. below | Firm Load Loss, Creates Radial Feeds
ENMAX | 2.4TR (ENMAX 2) | 2018-08-30 08:00 | 2018-08-30 16:00 | N | N | oil sample MT, bushings, TC | Transformer |  |  | For Information Only
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s T2 (42s Sarcee),906L (17s Benalto - 42s Sarcee),42s Sarcee 240kV South Bus | 2018-08-30 09:30 | 2018-08-30 12:30 | N | Y | install 240kV pollution monitor | Shunts, Bus, Line, Transformer |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK, ENMAX | 74s T1 (74s Janet),932L (74s Janet - 162s Beddington),74s Janet 240kV Bus 1,929L (74S Janet - 287s Hazelwood) | 2018-08-30 10:30 | 2018-08-30 14:15 | N | Y | close open point 'A' on 240kV bus between 74s48 and 74s20N bus | Transformer, Bus, Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 419s T1 (419s Chestermere),419s T2 (419s Chestermere) | 2018-08-30 12:00 | 2018-09-22 08:00 | N | N | complete commisioning of Tx's & 25kV equipment | Transformer |  |  | For Information Only
ALTALINK | 42s 80 (42s Sarcee) | 2018-08-30 13:30 | 2018-08-30 16:30 | N | N | replace pollution monitor sensor at location #6 located near breaker 42s80 | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ENMAX | 13.1TR (ENMAX 13) | 2018-08-31 08:00 | 2018-08-31 16:00 | N | N | relay testing and reversing switch checking | Transformer |  |  | For Information Only
Saskpower | SASK POWER P2C | 2018-08-31 11:30 | 2018-09-01 16:00 | N | Y | forced outage | Line |  |  | Limits ATC
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus,162s Beddington 138 kV South Bus | 2018-09-01 08:00 | 2018-09-01 18:00 | N | Y | fall substation washing | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-09-02 01:00 | 2018-09-02 06:00 | N | N | locate on 1.80L to facilitate 1.81L manhole construction | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36),36PT138-Z32 (ENMAX 36) | 2018-09-02 08:00 | 2018-09-03 18:00 | N | N | fall substation washing, breaker maintenance, doble | Line, Transformer, Terminal Equipment |  | Fall Substation Washing 36.2, 16.63, BT3. HV breaker maintenance 16B69-16.63. Doble PT 36PT138-Z32 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 9L913 (69s North Barrhead - 732s Mitsue),69s 913N (69s North Barrhead) | 2018-09-03 07:00 | 2018-09-09 18:00 | N | Y | connect the permanent line back up to the existing line | Line, Circuit Breaker |  | Outage to connect the permanent line back up to the existing line. Return to Normal after rebuilding of current section of line due to 12L41 500KV right-of-way requirements. | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 6.4TR (ENMAX 6) | 2018-09-03 08:00 | 2018-09-07 16:00 | N | N | doble test, transformer secondary cable tests, transformer maintenance | Transformer |  | Doble test transformer. Transformer secondary cable tests. Transformer maintenance. | For Information Only
SUNCOR | 29EDD-1 29EDD1s 552 (29EDD-1 Millennium) | 2018-09-03 09:00 | 2018-09-09 18:00 | N | Y | replacement of 29CT-5 | Circuit Breaker |  |  | 240 kV
EPCOR | 803s L2405 (803s Lambton) | 2018-09-04 07:00 | 2018-09-08 17:00 | N | Y | maintenance | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 657s SU2402 (657s Summerside) | 2018-09-04 07:00 | 2018-09-04 17:00 | N | Y | refill SF6 | Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 816s T1 (816s Petrolia) | 2018-09-04 07:00 | 2018-11-30 17:00 | N | Y | tap changer & bushing replacements | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 681s T2 (681s Bannerman) | 2018-09-04 07:00 | 2018-09-17 10:00 | N | Y | isolate and install grounds for the customer to repair cable terminations | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 367s T2 (367S Harry Smith),367s Harry Smith 138 kV Bus 2,367s 1552 (367s Harry Smith),367s 1852 (367s Harry Smith),367s Harry Smith 240 kV Bus 2,367s 852 (367s Harry Smith),367s 1252 (367s Harry Smith) | 2018-09-04 07:30 | 2018-09-04 17:00 | N | Y | retesting of T2 non-electrical trips to all bus breakers and replace 509ITM | Transformer, Circuit Breaker, Bus |  |  | 240 kV, Overload, Contingency Requires Mitigation
CNRL | 75-TR-1801 (838s Horizon Mining) | 2018-09-04 08:00 | 2018-09-20 15:00 | N | Y | transformer OLTC maintenance | Transformer |  |  | 240 kV
CNRL | 75-TR-2701 (838s Horizon Mining) | 2018-09-04 08:00 | 2018-09-24 07:59 | N | Y | transformer OLTC maintenance | Transformer |  |  | 240 kV
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2018-09-04 08:00 | 2018-09-05 17:00 | N | N | changes out cross arms | Line |  | To changes out cross arms No study request sent | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ATCO | 796s 701T (796s Nipisi) | 2018-09-04 08:00 | 2018-09-04 16:00 | N | N | emergency repair | Transformer |  | 701T and 25 KV Bus#1 at 796S. 500PT1 Primary fuse has a bad connection, The Fuse is a Rack Out type that and needs a bus outage to repair due to limited clearances. | For Information Only
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1),20PT138-Z31 (ENMAX 20) | 2018-09-04 08:00 | 2018-09-04 16:00 | N | N | 1.81L already out of service,20.1TR west whip will not reset. | Line, Transformer, Terminal Equipment
ENMAX | 1.8TR (ENMAX 1) | 2018-09-04 08:00 | 2018-09-14 16:00 | N | N | HV, MV bushing replacement | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2018-09-04 08:15 | 2018-09-21 16:45 | N | Y | component replacement | Line | component replacement, and installing interphase spacers on 918L circuit between str 763-839 |  | 240 kV, Pre-Condition
REDDEER | 247s T1 (247s Piper Creek) | 2018-09-04 09:00 | 2018-09-07 15:30 | N | N | inspection and power factor test | Transformer |  |  | For Information Only
ALTALINK | 289s 1552 (289s Saunders Lake) | 2018-09-04 10:00 | 2018-09-06 13:40 | N | Y | [SWEATD] replacement of CT | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 510S Sunnybrook,511s Crossing,1238L (510s Sunnybrook - 330p Genesee),1325L (510s Sunnybrook - 511s Crossings),510s T11 (510s Sunnybrook),511s T11 (511s Crossings) | 2018-09-04 11:00 | 2018-09-12 15:45 | N | Y | modify and test disconnects and earthing switches in the HVDC AC and DC yards | Line, Transformer, Station | 510s, 511s HVDC Link Outage to modify and test disconnects and earthing switches in the HVDC AC and DC yards. DC Link will be out of service. 1238L will be open. 1239L and 1203L remain in service. |  | 240 kV, 500 kV
EPCOR | Woodcroft W724 (Woodcroft) | 2018-09-05 07:00 | 2018-09-05 17:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 615L (602s Cold Creek - 104s Watson Creek) | 2018-09-05 07:30 | 2018-09-06 18:00 | N | N | foundation drilling near 104s | Line |  | 615L Transmission Line Outage for Structure 143 caisson foundation drilling near 104s. Clearance required to safely drill piers and install rebar cage. Connect new 492L1 to 615L near 602s | For Information Only
ALTALINK | 245s T2 (245s Seebe) | 2018-09-05 08:00 | 2018-09-06 17:00 | N | N | maintain, fix leaks and heaters on T2 and have MR techs onsite to perform tapchanger upgrades. | Transformer |  |  | For Information Only
ENMAX | 34.1TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2018-09-05 08:00 | 2018-09-05 16:00 | N | N | center whip not reset | Transformer, Line |  |  | For Information Only
ENMAX | 39.1TR (ENMAX 39) | 2018-09-05 08:00 | 2018-09-05 12:00 | N | N | functional checks | Transformer |  |  | For Information Only
ALTALINK | 535s 1152 (535s Joffre) | 2018-09-05 08:00 | 2018-09-05 17:00 | N | N | fix trip coil | Circuit Breaker |  |  | Pre-Condition
ALTALINK, NRGREEN | 259S Chickadee Creek,199L (268s Whitecourt - 199L187B),199L (347s Fox Creek - 199L187B) | 2018-09-05 09:30 | 2018-09-05 16:30 | N | Y | close open point at str 199L187A | Line, Station |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 9L953 (574s Nilrem - 755s Cordel),953L (574s Nilrem - 755s Cordel) | 2018-09-05 11:00 | 2018-09-05 15:00 | N | Y | required for 9465R (lougheed) tower replacement (dynamic study) | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 39.2TR (ENMAX 39) | 2018-09-05 12:00 | 2018-09-05 16:00 | N | N | functional checks | Transformer |  |  | For Information Only
ALTALINK | 914L (86s Bigstone - 87s Gaetz),86s 1752 (86s Bigstone) | 2018-09-06 07:30 | 2018-09-06 16:30 | N | Y | top up low oil on 240kV HLR-E breaker | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 13.3TR (ENMAX 13) | 2018-09-06 08:00 | 2018-09-06 16:00 | N | N | relay testing, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26) | 2018-09-06 08:00 | 2018-09-06 16:00 | N | N | doble test instrument transformer | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 35s9 (35s Rundle) | 2018-09-06 09:00 | 2018-09-10 12:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2018-09-06 09:00 | 2018-09-06 11:00 | N | N | inspect previous repairs | Line |  | Inspect Previous repairs | Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 33s6 (33s Spray) | 2018-09-06 10:00 | 2018-09-09 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 33s3 (33s Spray) | 2018-09-06 10:00 | 2018-09-09 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 35s 41 (35s Rundle),35s8 (35s Rundle) | 2018-09-06 17:00 | 2018-09-09 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 501CL (983s Cadomin - 501L tap),501L (426s Coalspur - 501CL tap) | 2018-09-07 07:00 | 2018-09-07 17:00 | N | N | re-locating a portion of 501L between existing structures #95 - 105 | Line |  |  | For Information Only
ATCO | 783S Cadotte River,783s 701T (783s Cadotte River) | 2018-09-07 07:00 | 2018-10-19 16:00 | N | N | replace 701TD and 701T | Transformer, Station |  | Replace 701TD and 701T. | For Information Only
ATCO | 845s 702 (845s Big Mountain) | 2018-09-07 08:00 | 2018-09-13 13:49 | N | Y | forced | Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH, ALTALINK | 48s 887X (48s Pocaterra),1L274 (48s Pocaterra - Britt Creek) | 2018-09-07 09:00 | 2018-09-07 17:00 | Y | Y | POC RAS transfer trip from NIC PLC is unavailable | Line, Circuit Breaker |  | Due to CBK MPLS equipment upgrade POC RAS transfer trip from NIC PLC unavailable refer to 8-340329 | Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.4TR (ENMAX 39) | 2018-09-07 14:00 | 2018-09-07 18:00 | N | N | functional checks | Transformer |  | Functional checks (After 39.3TR has been returned to service) | Pre-Condition, For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt) | 2018-09-07 16:00 | 2018-09-13 09:30 | N | N | connect 472s & MR1 to 797L at 268s. Install temporary dead end outside 268s. | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T2 (987s Clover Bar),987s T4 (987s Clover Bar),987S Clover Bar 240 kV Bus 2 | 2018-09-08 07:00 | 2018-09-08 17:00 | N | Y | doble | Bus, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 700s 702T (700s Bonnyville) | 2018-09-09 07:00 | 2018-09-21 17:00 | N | N | replace circuit switcher, 702TCS replacement project | Transformer |  | Replace circuit switcher 700S Bonnyville 702TCS Replacement Project | For Information Only
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2018-09-09 08:00 | 2018-09-09 12:00 | N | N | fall substation washing 31.2, 31.3 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (B1s BCH Natal - 1D1L274) | 2018-09-09 08:00 | 2018-09-16 16:00 | N | Y | overhead rating restoration | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Limits ATC, Firm Load Loss, Creates Radial Feeds
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2018-09-09 09:00 | 2018-09-09 16:00 | N | Y | proximity outage for work on 1L274 outside Natal | Line | Peak RC COS Outage (BCH outage) ID: 1-00591934 Peak RC COS Derate ID: 1-00596318 (W>E), 1-00596319 (E>W) |  | Pre-Condition, Overload, Over/Under Voltage, Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2018-09-09 12:01 | 2018-09-09 18:00 | N | N | fall substation washing | Line, Shunts, Transformer |  |  | Pre-Condition
EPCOR | Rossdale R723 (Rossdale) | 2018-09-10 07:00 | 2018-10-12 17:00 | N | N | breaker replacement | Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark M723 (Meadowlark) | 2018-09-10 07:00 | 2018-09-14 17:00 | N | N | maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 33.1TR (ENMAX 33) | 2018-09-10 08:00 | 2018-09-13 16:00 | N | N | tapchanger inspection | Transformer |  | Tapchanger inspection. Oil sampling TR, TC. Check reversing switch | For Information Only
ENMAX | 31.1C (ENMAX 31) | 2018-09-10 08:00 | 2018-09-13 16:00 | N | N | capacitor banks maintenance | Shunts |  |  | Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2018-09-10 08:00 | 2018-09-14 16:00 | N | N | HV CT replacement | Transformer |  |  | For Information Only
CNRL | 842s 75-TR-4701 (842s Horizon Upgrading),75-TR-8701 (842s Horizon Upgrading) | 2018-09-10 08:00 | 2018-09-20 15:00 | N | Y | transformer OLTC maintenance | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 62s T5 (62s Brazeau) | 2018-09-10 08:00 | 2018-09-19 18:00 | N | Y | protection upgrade | Transformer |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation
ALTALINK | 62s 11 (62s Brazeau) | 2018-09-10 08:00 | 2018-10-23 04:00 | N | Y | annual maintenance | Switch |  |  | Restricts Generation
ATCO | 7L20 (810s Dome Cutbank - 740s H.R.Milner) | 2018-09-10 08:00 | 2018-09-13 13:49 | N | Y | changing cross arms | Line |  | Changing over rated XARMS | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.1TR (ENMAX 27) | 2018-09-10 08:00 | 2018-09-10 16:00 | N | N | repair shutters in 27B8-27.1TR breaker cell | Transformer |  | Repair shutters in 27B8-27.1TR breaker cell. Check reversing SW. LV Breaker Maintenance (Time dependant) | For Information Only
ENMAX | ENMAX 35.1TR (ENMAX 35) | 2018-09-10 08:00 | 2018-09-10 12:00 | N | N | fall substation washing | Transformer |  | fall substation washing. Oil sampling TC | For Information Only
BCH | 1L275 (799s Coleman - Natal) | 2018-09-10 08:30 | 2018-09-14 17:30 | N | Y | 1CB1 insp/ 1VT1 insp/doble | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 260kV bus 29PP-45 (29EDD-34) | 2018-09-10 09:00 | 2018-09-23 18:00 | N | Y | 5 year maintenance on 29PP-45 bus | Bus |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 946s 901 (946s Oakland) | 2018-09-10 09:30 | 2018-09-11 20:00 | N | Y | CT ratio increase and protection settings changes | Circuit Breaker |  | 946S Oakland BKR 901 CT Ratio Increase CT Ratio Changes and Protection Settings | 240 kV, Contingency Requires Mitigation
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah),77s 252 (77s Sagitawah),77s 452 (77s Sagitawah) | 2018-09-10 10:00 | 2018-09-13 17:00 | N | N | replace PTs and junction box | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, NOVAC | 330L1 (I-330s Nova Corp Plant - 535s Joffre),535s96N (535s Joffre) | 2018-09-10 10:00 | 2018-09-11 16:00 | N | Y | yearly maintenance and testing | Switch, Line |  | Perform yearly maintenance and testing of the electrical devices located at the 330S Substation. Scheduled outage with AESO. | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 171s T1 (171s Redwater) | 2018-09-10 10:30 | 2018-09-13 17:30 | N | N | multiple oil leaks | Transformer |  | 171s T1 Multiple oil Leaks. ADD: 171sT1 doble TX 18394 LTC FPE/ASEA 138/2 90245300, 171sT1 maint TX 18394 LTC FPE/ASEA 138/2, 171s T1 TX 18394 TX leaks | For Information Only
ENMAX | ENMAX 35.2TR (ENMAX 35) | 2018-09-10 12:00 | 2018-09-10 16:00 | N | N | fall substation washing | Transformer |  | Fall Substation Washing. Oil sampling TC | Pre-Condition, For Information Only
SUNCOR | 29EDD-1 29EDD1s 452 (29EDD-1 Millennium) | 2018-09-10 14:30 | 2018-09-14 18:00 | N | Y | SF6 top up and leak repair | Circuit Breaker |  | SF6 top up & leak repair on 260kV breaker 29EDD1S452 | 240 kV
ALTALINK | 221s T1 (221s Sunken Lake) | 2018-09-11 07:00 | 2018-09-11 17:00 | N | N | enbridge work | Transformer |  |  | For Information Only
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2018-09-11 07:00 | 2018-09-11 18:00 | N | N | replace DC wiring to 54s24 | Transformer |  |  | For Information Only
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2018-09-11 08:00 | 2018-09-11 16:00 | N | N | line outage for 33.1TR tapchanger inspection | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, FORTIS | 140S Thompson,788L (157s Lac La Biche - 898s Heart Lake),789L (818s Winefred - 898s Heart Lake) | 2018-09-11 08:00 | 2018-09-11 16:00 | N | Y | adjusting 788L107A and 788L106B | Line, Station |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX, ALTALINK | 281s 918(281s Johnson),918L (281s Johnson - 162s Beddington) | 2018-09-11 08:00 | 2018-09-11 16:30 | N | N | fall substation washing | Line, Switch |  |  | 240 kV, For Information Only
ALTALINK | 703L (213s Hughenden - 703L33) | 2018-09-11 08:15 | 2018-09-11 12:45 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 162s 240-RB132 (162s Beddington),918L (281s Johnson - 162s Beddington),162s 240-RB133 (162s Beddington) | 2018-09-11 08:16 | 2018-09-11 16:00 | N | Y | fall substation washing | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 172s T2 (172s Sherritt Gordon),172s 72 (172s Sherrit) | 2018-09-11 08:30 | 2018-09-11 17:30 | N | N | replace gas density gauge | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 299s T1 (299s Kingman) | 2018-09-11 09:00 | 2018-09-11 17:00 | N | N | enbridge work | Transformer |  |  | For Information Only
TRANSALTA, ALTALINK | 528s Blue Trail Wind Farm RTU/SCADA,418s Ardenville RTU/SCADA,240s McBride Lake RTU/SCADA | 2018-09-11 11:00 | 2018-09-11 12:00 | N | N | firewall upgrade | Terminal Equipment |  |  | Affects Visibility
ENMAXEC | 383s Kettles Hill Windfarm RTU/SCADA | 2018-09-11 21:00 | 2018-09-11 23:00 | N | N | network upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-09-11 22:30 | 2018-09-12 06:00 | N | N | remove mobile & close open point | Line |  | 953s; remove mobile, close open point on 551L (area loads offline) | For Information Only
ALTALINK | 789L (818s Winefred - 898s Heart Lake),788L (898s Heart Lake - 788L107A - 602L1) | 2018-09-12 07:00 | 2018-09-12 18:00 | N | Y | adjusting 602LA1 and OHSW | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALBIAN, SHELL | 847s 901T (847s Muskeg River),919s 906 (919s Hartley) | 2018-09-12 07:00 | 2018-09-27 16:00 | N | Y | transformer protection upgrade | Circuit Breaker, Transformer |  | CNRL Albian Sands will be shutting down GT-1 for a hot gas path inspection and maintenance Transformer 901T protection upgrade during CNRL planned generator turnaround. | 240 kV, Restricts Generation
ENMAX | 6.4TR (ENMAX 6) | 2018-09-12 08:00 | 2018-09-13 16:00 | N | N | ABB to inspect 6BA25-6.4TR shutters | Transformer |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34),34.3TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2018-09-12 08:00 | 2018-09-12 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | SCR5 Poplar Creek | 2018-09-12 08:00 | 2018-09-17 16:00 | N | N | STG3 control system upgrade ISD: Sept 15 | Unit
ATCO | 783s 701T (783s Cadotte River) | 2018-09-12 08:00 | 2018-10-19 16:00 | N | N | transformer replacement. ISD Nov 22, 2018 | Transformer |  | there is faulty bushings for the x-mer and replacement parts are expected 8 weeks from now.
ATCO | 946s 902 (946s Oakland) | 2018-09-12 13:01 | 2018-09-14 16:00 | N | Y | CT ratio and protection settings changes | Circuit Breaker |  | 946S Oakland 902CT Ratio Increase, CT Ratio and Protection Settings Changes | 240 kV, Pre-Condition
ALTALINK | 268s T3 (268s Whitecourt),268s 797 (268s Whitecourt) | 2018-09-13 10:00 | 2018-09-17 08:00 | N | N | install bird cover-up on 25 kV bus and start replacement of 138 kV bus | Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2018-09-14 06:45 | 2018-09-14 11:15 | N | Y | perform IR scan of 892L | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.83L (ENMAX 14 - ENMAX 36) | 2018-09-14 08:00 | 2018-09-14 16:00 | N | N | fall substation washing | Line, Shunts |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2018-09-14 11:16 | 2018-10-04 13:24 | N | N | forced outage due to underbuild issues | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s GDS1 (987s Cloverbar) | 2018-09-15 07:00 | 2018-09-23 17:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2018-09-15 08:00 | 2018-09-15 12:00 | N | N | transmission line washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2018-09-15 12:00 | 2018-09-15 16:00 | N | N | transmission line washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 41.84L (ENMAX 54 - ENMAX 41),54.81L (ENMAX 54 - ENMAX 65),54.1TR (ENMAX 54) | 2018-09-16 08:00 | 2018-09-16 18:00 | N | N | fall substation washing | Transformer, Line |  | Fall Substation Washing, 54.1, 41.84, 54.81, Z31
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2018-09-16 08:00 | 2018-09-16 12:00 | N | N | fall transmission line washing | Line |  | Fall Transmission Line Washing. Shared structure with 16.60L | Firm Load Loss, Creates Radial Feeds
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2018-09-16 12:00 | 2018-09-16 16:00 | N | N | fall transmission line washing | Line |  | Fall Transmission Line Washing. Shared structure with 15.62L | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s GDS2 (987s Cloverbar) | 2018-09-17 06:00 | 2018-09-19 08:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 2029s ACF23 (2029s Heathfield) | 2018-09-17 07:00 | 2018-09-19 13:30 | N | Y | maintenance | Shunts |  | Filter Bank Maintenance and Inspection, redundant filter banks in service, no system impact | 500 kV
ALTALINK | 286s T1 (286s Yasa) | 2018-09-17 07:00 | 2018-09-30 17:00 | N | N | emergency repair | Transformer |  | Emergency repair and replacement of incoming cables on Bus A, clean and test Bus A and associated equipment. Suncor A station service cable replacement. (Customer Outage) | For Information Only
ALTALINK | 204S Sandy Point,760L (163s Amoco Empress - 760L41),869L (204s Sandy Point - 163s Amoco Empress),163s C1 (163s Amoco Empress),163s C2 (163s Amoco Empress) | 2018-09-17 07:00 | 2018-09-18 17:00 | N | Y | switches repairs | Line, Shunts, Station |  | Repairs to 163s50, 163s49, 163s3 Switches, Customer Needs to be de-energized for their shutdown and breaker maintenance, | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 42s C1 (42s Sarcee) | 2018-09-17 07:30 | 2018-09-20 17:00 | N | N | relay replacement | Shunts |  | Replacement of Cap Bank C1 A protection relay with retrofit relay in existing module. | For Information Only
ALTALINK | 323S Whitecourt Power,268S Whitecourt,268s T3 (268s Whitecourt),503L (268s Whitecourt - 323s Whitecourt Power),526L (268s Whitecourt - 526DL185),797L (364s Whitecourt industrial - 268s Whitecourt),199L (268s Whitecourt - 199L187B) | 2018-09-17 08:00 | 2018-09-21 16:30 | N | Y | 268s project | Line, Station, Transformer |  | 69 kV bus PT replacement, protection replacement - 503L, connect protections on 526L to 268s503 (temporary), work on 138 kV Bus rebuild. | Pre-Condition, Restricts Generation
ENMAX | 5.1TR (ENMAX 5) | 2018-09-17 08:00 | 2018-09-17 16:00 | N | N | maintenance | Transformer |  | Oil sample MT, bushings, TC. Check reversing SW. Substation  Tap Changer  Filmax LTC Oil Filtration Maintenance  5.1-TC | For Information Only
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2018-09-17 08:00 | 2018-09-18 18:00 | N | N | change cross-arm | Line |  | CHANGING CROSS-ARMS ON 7L53 | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1C (ENMAX 21) | 2018-09-17 08:00 | 2018-09-20 16:00 | N | N | maintenance | Shunts |  |  | Pre-Condition
ENMAX | ENMAX 65 B240-D132 (ENMAX 65) | 2018-09-17 08:00 | 2018-09-18 16:00 | N | Y | remediate bird mess | Circuit Breaker |  | Re Mediate Bird Mess Inside Insulating Blankets [AVANTIS]. | 240 kV, Contingency Requires Mitigation
ENMAX | 11.3TR (ENMAX 11) | 2018-09-17 08:00 | 2018-09-21 16:00 | N | N | replace CT | Transformer |  |  | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2018-09-17 09:00 | 2018-09-27 18:00 | Y | Y | maintenance components and BCH line maintenance | Line | Peak RC COS outage ID: 1-00532816 Peak RC Path Derate ID: 1-00538739 (E>W), 1-00538740 (W>E) |  | Pre-Condition, Limits ATC, 500 kV
ATCO | 959S SVC (959s Lanfine) | 2018-09-17 09:00 | 2018-09-21 16:00 | N | Y | firmware modifications | Shunts |  | This outage is to install the firmware modifications that GE didnt install in our June outage. Also attached is the update system testing / commissioning requirements after new firmware has been installed in the controllers. SVC will not be available for duration of outage | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2018-09-17 09:00 | 2018-10-04 18:00 | N | Y | align with 1201L outage | Line | Peak RC COS outage ID: 1-00597799 (1201L and MATL Outage record from Sep 17 to Sep 27) PEAK COS path de-rate ID: 1-00597828 (N-S), 1-00597830 (S-N) PEAK COS outage ID:1-00538722 (1201L and MATL Outage record from Oct 1 to Oct 4) PEAK COS path de-rate ID: 1-00538752 (N-S), 1-00538754 (S-N) PEAK COS outage ID: 1-00597787(MATL outage from Sep 27 to Oct 1) PEAK COS path de-rate ID: 1-00597834 (N-S), 1-00597835 (S-N) |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 275s T2 (275s Jenner) | 2018-09-17 09:30 | 2018-09-20 16:00 | N | Y | maintenance | Transformer |  | Maintain, fix leaks and heaters on T2 and have MR techs onsite to perform tapchanger upgrades. | 240 kV
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2018-09-17 09:30 | 2018-09-18 13:00 | N | N | washing insulators | Line |  | Washing insulators on Structures #33, 60, 63, 66 - 68 | For Information Only
ATCO | 856s 505R (856s Kinosis) | 2018-09-17 09:30 | 2018-09-19 12:00 | N | N | relay settings change | Shunts |  | 856S Kinosis - 50-51-59N/505R Relay Settings Change | For Information Only
ALTALINK | 995L (17s Benalto - 995AL tap) | 2018-09-17 10:00 | 2018-09-17 12:00 | N | Y | create open point 'A' | Line |  | Create Open Point 'A' between 17s995N and Str 491. Hot Line Work. | 240 kV, Pre-Condition, Restricts Generation
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 2018-09-17 10:00 | 2018-09-20 16:00 | N | Y | changes arms and insulators | Line |  | Changes Arms and Insulators | Pre-Condition
ATCO | 6L57 (735s Swan River - 727s Kinuso),735s 602 (735s Swan River) | 2018-09-17 10:00 | 2018-11-16 15:00 | N | N | breaker replacement and commission | Circuit Breaker, Line |  | 735S BKR 602 Replacement Replace Breaker 602 and commission. 6L57 will be out of service | Firm Load Loss, Creates Radial Feeds
ATCO | 946s 903 (946s Oakland) | 2018-09-17 10:00 | 2018-09-19 12:00 | N | Y | change CT ratio and protection settings | Circuit Breaker |  | 946S Oakland 903CT Ratio Increase, CT Ratio Changes and Protection Settings | 240 kV, Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2018-09-17 10:00 | 2018-09-17 11:00 | N | N | relay replacement | Line |  | 43s Autoswitching and 138kV BD relay relacement. Outage required to short out BD CTs. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s C1 (62s Brazeau),62s 215 (62s Brazeau) | 2018-09-17 10:00 | 2018-10-04 18:00 | N | N | protection upgrade | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 681s T1 (681s Bannerman) | 2018-09-17 10:05 | 2018-09-25 18:00 | N | Y | customer outage to repair cable terminations | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 310p 252 (310p Sundance) | 2018-09-17 10:30 | 2018-09-18 15:00 | N | Y | 310p252 (CB773) MO 240kV HPF | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 43.2TR (ENMAX 43) | 2018-09-17 11:00 | 2018-09-17 12:00 | N | N | relay replacement | Transformer |  | 43s Autoswitching and 138kV BD relay relacement. Outage required to short out BD CTs. | For Information Only
ALTALINK | 926L (310p Sundance - 17s Benalto),17s Benalto 240 kV North Bus 1,17s T3 (17s Benalto) | 2018-09-17 12:00 | 2018-09-17 18:00 | N | Y | replace strain insulators on 995L due to reasons of approach | Line, Bus, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s C1 (17s Benalto) | 2018-09-17 12:00 | 2018-09-24 13:00 | N | Y | replace strain insulators on 995L | Shunts |  | Outage required to replace strain insulators on 995L due to reasons of approach on the substation side of 995L | 240 kV, Pre-Condition
ALTALINK | 995L (17s Benalto - 995AL tap),17s 12 (17s Benalto),17s 13 (17s Benalto) | 2018-09-17 12:00 | 2018-09-24 13:00 | N | Y | replacement of strain insulators for 995L | Line, Circuit Breaker |  | Replacement of Strain insulators for 995L (on sub side of 17s995N switch),Post insulators for 17s76, 17s77, & CVT(17s78) replacement like for like. | 240 kV, Pre-Condition, Restricts Generation, Contingency Requires Mitigation
ENMAX | 43.1TR (ENMAX 43) | 2018-09-17 13:00 | 2018-09-17 14:00 | N | N | relay replacement | Transformer |  | 43s Autoswitching and 138kV BD relay relacement. Outage required to short out BD CTs. | For Information Only
ALTALINK | 926L (310p Sundance - 17s Benalto) | 2018-09-17 13:00 | 2018-09-21 16:00 | N | Y | Migrate and commission all L9 - 926L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L4 alarms. | Line |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1C (ENMAX 38),38.1TR (ENMAX 38),38.3TR (ENMAX 38),38.83L (ENMAX 39 - ENMAX 38) | 2018-09-17 21:00 | 2018-09-18 01:00 | N | N | fall substation washing | Line, Transformer, Shunts |  | Fall Substation Washing 38CAP, 38.1, 38.3. 39 sub functional checks | Firm Load Loss, Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2018-09-18 01:00 | 2018-09-18 06:00 | N | N | fall substation washing | Transformer, Shunts, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 221s T1 (221s Sunken Lake) | 2018-09-18 06:00 | 2018-09-18 18:00 | N | N | customer work | Transformer |  | Replace T1 NGR, Add trip and block close from customer SE330 relay | For Information Only
ALTALINK | 221s T3 (221s Sunken Lake) | 2018-09-18 06:00 | 2018-09-18 18:00 | N | N | customer work | Transformer |  |  | For Information Only
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2018-09-18 07:00 | 2018-09-18 13:29 | N | Y | damper replacement on structure 164-165 | Line |  | Emergency Repair, Damper Replacement on Str 164-165 | 240 kV, Contingency Requires Mitigation
ALTALINK | 910s 701T (910s Excel) | 2018-09-18 07:00 | 2018-09-18 19:00 | N | N | preventative maintenance | Transformer |  | A Station power outage is required so TransCanada crews can perform preventative maintenance electrical inspections. | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2018-09-18 08:00 | 2018-09-18 12:00 | N | N | fall substation washing | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 41.84L (ENMAX 54 - ENMAX 41) | 2018-09-18 08:00 | 2018-09-20 16:00 | N | N | breaker maintenance | Line |  | HV breaker maintenance 41B138-41.84. 54B138-41.84SF6 Equipment Top Up and Audit. | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.3TR (ENMAX 3) | 2018-09-18 08:00 | 2018-09-18 12:00 | N | N | maintenance | Transformer |  | Oil sample MT, TC. Check reversing sw | For Information Only
ALTALINK | 719L (263s Strachan - 719L259C),263s 719 (263s Strachan) | 2018-09-18 08:00 | 2018-09-18 16:00 | N | N | installing new DDR | Line, Circuit Breaker |  | Installing new DDR- wiring and testing inputs, status and analogs from 719L (L6) protections. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 45s T1 (45s Bretona) | 2018-09-18 08:30 | 2018-09-20 12:00 | N | N | transformer maintenance | Transformer |  | 45sT1 maint TX18684 LTC PAU/ABB 138/26.5 | For Information Only
ALTALINK | 752L (64s East Crossfield - 752L67) | 2018-09-18 09:00 | 2018-10-04 16:00 | N | Y | project rebuild of 752L of str66 to 64s | Line |  | Project Rebuild of 752L of str66 to 64s | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 527s T1 (527s Coal Valley),743L (527s Coal Valley - 743L1A) | 2018-09-18 09:00 | 2018-09-21 18:00 | N | N | T1 bushing replacements and VR1 TC filter installation | Line, Transformer |  | T1 Bushing Replacements and VR1 TC Filter Installation | For Information Only
ALTALINK | 737L (95s Imperial Oil Edmonton - 38s East Edmonton) | 2018-09-18 09:00 | 2018-09-18 11:00 | N | N | hybrid replacement at 95s | Line |  | Hybrid requires replacement at 95s which will interrupt channel 1 and 2 of 737L. | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.4TR (ENMAX 3) | 2018-09-18 12:00 | 2018-09-18 16:00 | N | N | maintenance | Transformer |  | Oil sample MT, TC. Check reversing sw. Install Shielding for Cabinet Heating [AVANTIS] | For Information Only
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2018-09-18 12:00 | 2018-09-18 18:00 | N | N | fall substation washing | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 1035L (2075s Newell - 244s Bowmanton) | 2018-09-18 13:31 | 2018-09-20 19:00 | N | Y | damper replacement on structure 23-311 | Line |  | Emergency Repair, Damper Replacement on Str 23-311 | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 760L (163s Amoco Empress - 760L41),869L (204s Sandy Point - 163s Amoco Empress),163s C1 (163s Amoco Empress),163s C2 (163s Amoco Empress),163s Partial 138kV Bus - Advice | 2018-09-18 16:00 | 2018-10-11 15:00 | N | Y | replace 163s4 PT, replace 163s64 breaker, & add new 163s65, switch & perform 163s869W breaker fail replacement | Terminal Equipment, Line, Shunts |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 204S Sandy Point,869L (204s Sandy Point - 163s Amoco Empress) | 2018-09-18 16:30 | 2018-10-11 16:00 | N | N | maintenance and repairs at 204s taking place during 204s customer shutdown | Line, Station |  |  | For Information Only
ALTALINK | 221s T3 (221s Sunken Lake) | 2018-09-18 18:00 | 2019-05-01 14:00 | N | N | transformer removal | Transformer |  | Put existing T3 under GOI to begin disconnecting it from station for removal. T3 to be replaced with 6.9kV unit in Q4 2018/Q1 2019 | For Information Only
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36) | 2018-09-18 21:00 | 2018-09-19 06:00 | N | Y | SF6 gas sample and fall substation washing | Line, Transformer |  | SF6 gas sample 36B138-36.81. Fall Substation Washing 36.1, 36.3, BT3 (Origional outage Sept 16) | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2018-09-18 22:00 | 2018-09-19 06:00 | N | N | functional checks | Line |  |  | Pre-Condition, Overload
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2018-09-19 07:00 | 2018-09-24 17:30 | N | Y | emergency outage to repair the leaks in both respective buildings | Line |  |  | Pre-Condition, 500 kV
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2018-09-19 07:00 | 2018-09-20 18:00 | N | N | washing insulators on structures #28, 29, 60 - 65, 80 | Line |  | Washing insulators on Structures #28, 29, 60 - 65, 80 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.1TR (ENMAX 6) | 2018-09-19 08:00 | 2018-09-19 16:00 | N | N | oil sample and maintenance | Transformer |  | Oil sample MT, bushings, TC. Check reversing SW | For Information Only
ALTALINK | 945S Sunshine Village | 2018-09-19 08:00 | 2018-09-19 17:00 | N | N | create open point 'C' and 'D' for 69kV rebuild project | Station |  |  | For Information Only
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2018-09-19 08:00 | 2018-09-21 18:00 | N | N | changing cross-arms | Line |  | Changing cross-arms | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2018-09-19 08:00 | 2018-09-20 16:00 | N | Y | remediate bird mess inside insulating blankets and exposed cables | Circuit Breaker |  | Remediate Bird Mess Inside Insulating Blankets [AVANTIS]. Reterminate Exposed Cables on Control Cable [AVANTIS] | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 765L (74s Janet - 151s Strathmore),151s 765W (151s Strathmore),74s 765E (74s Janet),419s Chestermere | 2018-09-19 09:00 | 2018-09-28 12:00 | N | N | connect new 419s, rename 765L (74s-419s) to 691L | Circuit Breaker, Line, Station |  | Connect new 419s to 138KV system and commission, rename 765L (74s-419s) to 691L | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s T2 (74s Janet) | 2018-09-19 09:00 | 2018-09-24 16:00 | N | Y | fix oil leaks, doble and maintaenance | Transformer |  | Fix oil leaks on T2 Tx18571, doble and maintain. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 418s Ardenville RTU/SCADA | 2018-09-19 11:00 | 2018-09-19 12:00 | N | N | firewall upgrade | Terminal Equipment |  |  | Affects Visibility
ATCO | 946s 904 (946s Oakland) | 2018-09-19 13:00 | 2018-09-20 13:40 | N | Y | CT ratio and protection settings changes | Circuit Breaker |  | 946S Oakland BKR 904 CT Ratio Increase CT Ratio Changes and Protection Settings | 240 kV, Pre-Condition
ATCO | 740s 702T (740s H.R.Milner) | 2018-09-19 13:12 | 2018-10-05 16:00 | N | N | gas pressure trip (forced outage) | Transformer
ALTALINK | 945S Sunshine Village | 2018-09-19 17:01 | 2018-11-07 17:00 | N | N | station upgrade - 69kV bus rebuild and addition of hybrid breakers | Station |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2018-09-19 21:00 | 2018-09-20 06:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 703L (213s Hughenden - 703L33) | 2018-09-20 07:00 | 2018-09-20 12:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 238S Shell Harmattan,238s166x (238s Shell Harmattan) | 2018-09-20 07:30 | 2018-09-23 17:00 | N | N | yearly maintenance | Switch, Station |  |  | For Information Only
SUNCOR | 635PT-1004 (635EDD-1000) | 2018-09-20 08:00 | 2018-09-21 17:00 | N | Y | transformer oil leak troubleshooting and repair | Transformer |  |  | 240 kV
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan) | 2018-09-20 08:00 | 2018-09-20 13:00 | N | Y | install new DDR- wiring from 870L (L5) protections | Line |  |  | Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 700s 710 (700s Bonnyville) | 2018-09-20 08:00 | 2018-09-24 16:00 | N | N | replacement of 702TCS circuit switcher. ISD Sept 21 | Circuit Breaker
ENMAX | 34.2TR (ENMAX 34) | 2018-09-20 08:00 | 2018-09-20 16:00 | N | N | transformer maintenance | Transformer |  | transformer maintenance. Substation  Tap Changer  Filmax LTC Oil Filtration Maintenance  34.2-TC. Oil sample MT, TC | For Information Only
ENMAX | 14.3TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2018-09-20 21:00 | 2018-09-21 06:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.5TR (ENMAX 1) | 2018-09-21 08:00 | 2018-09-21 16:00 | N | N | oil sample after 6 months in service | Transformer |  |  | For Information Only
ENMAX | 34.3TR (ENMAX 34) | 2018-09-21 08:00 | 2018-09-21 16:00 | N | N | transformer maintenance, oil sample | Transformer |  |  | For Information Only
ALTALINK | 268s T1 (268s Whitecourt),268s T3 (268s Whitecourt),797L (364s Whitecourt industrial - 268s Whitecourt),199L (268s Whitecourt - 199L187B) | 2018-09-21 16:30 | 2018-10-25 08:00 | N | Y | complete replacement of 138 kV equipment and protections | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 21.1C (ENMAX 21),21.2TR (ENMAX 21),50L (44s Bearspaw Plant - ENMAX 21) | 2018-09-21 21:00 | 2018-09-22 06:00 | N | Y | fall substation washing | Transformer, Shunts, Line |  | Fall Substation Washing. 50L, 21.2TR, 21CAP (Original outage Sept 10) | Pre-Condition
ENMAX | 13.4TR (ENMAX 13),27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2018-09-22 08:00 | 2018-09-22 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2018-09-22 12:00 | 2018-09-22 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s24.83X Enmax - Advice | 2018-09-22 20:30 | 2018-09-23 06:30 | N | N | doble, SF5 gas sample, sub washing | Terminal Equipment
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24) | 2018-09-22 21:00 | 2018-09-23 06:00 | N | Y | doble, SF5 gas sample, sub washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.1TR (ENMAX 11),11.4TR (ENMAX 11),11.81L (ENMAX 13 - ENMAX 11) | 2018-09-23 08:00 | 2018-09-23 16:00 | N | N | fall substation washing | Line, Transformer
ENMAX | 20.3TR (ENMAX 20) | 2018-09-23 08:00 | 2018-09-24 06:00 | N | N | sub roof replacement (west), station service TR already transferred | Transformer
ALTALINK | 166L (281s Johnson - 256s Harmattan),281s Johnson 138kV Bus2 | 2018-09-23 09:00 | 2018-09-23 13:00 | N | Y | energize new cables at 238s | Line, Bus |  |  | Pre-Condition, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2018-09-23 21:00 | 2018-09-24 06:00 | N | N | fall substation washing, SF6 gas sample, oil sampling, bushings | Line, Transformer
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2018-09-24 07:00 | 2018-09-24 09:59 | N | Y | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 2029s ACF12 (2029s Heathfield) | 2018-09-24 07:00 | 2018-09-25 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter Bank Maintenance and Inspection, redundant filter banks in service, no system impact | Pre-Condition, For Information Only, 500 kV
EPCOR | 987s SST2 (987s Clover Bar) | 2018-09-24 07:00 | 2018-09-28 17:00 | N | N | transformer maintenance & Doble | Transformer |  |  | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2018-09-24 07:00 | 2018-10-19 17:00 | N | N | pothead rebuild | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.7TR (ENMAX 5) | 2018-09-24 08:00 | 2018-09-24 16:00 | N | N | transfer trip upgrades | Transformer |  |  | For Information Only
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2018-09-24 08:00 | 2018-10-01 17:00 | N | Y | repair leaking bladder on TX30 and failed power module in the SVC Plus | Shunts, Transformer |  |  | 240 kV
ALTALINK | MATL 120s-941L Advice | 2018-09-24 08:00 | 2018-09-28 18:00 | N | N | test CVT 120S31 as part of MATLs preventative maintenance program | Terminal Equipment |  | test CVT 120S31 as part of MATLs preventative maintenance program | For Information Only
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2018-09-24 08:00 | 2018-09-24 16:00 | N | N | remove weeds from cap bank area | Shunts |  |  | Affects Visibility, For Information Only
ATCO | 710s 702T (710s Vermilion) | 2018-09-24 09:00 | 2018-09-27 16:00 | N | N | wiring and equipment upgrade | Transformer |  | 710S E64558 DG Perpetual 1MW Generation. Wiring and equipment upgrade to accommodate 1MW DG | For Information Only
ATCO | 946s 905 (946s Oakland) | 2018-09-24 10:00 | 2018-09-26 12:00 | N | Y | CT ratio changes and protection settings | Circuit Breaker |  | 946S Oakland 905CT Ratio Increase, CT Ratio Changes and Protection Settings | 240 kV, Pre-Condition, For Information Only
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2018-09-24 10:00 | 2018-09-24 17:00 | N | N | repair gas leak and top off breaker | Transformer
ATCO | 7L32 (862s South Bezanson - 813s Little Smoky) | 2018-09-24 10:00 | 2018-09-27 16:00 | N | Y | changes arms and insulators | Line |  | Changes Arms and Insulators | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 171s T2 (171s Redwater) | 2018-09-24 10:00 | 2018-09-27 13:30 | N | N | oil reclaim and bushings | Transformer |  |  | For Information Only
ALTALINK | 55s 443 (55S Olds),443L (214s Innisfail - 55s Olds) | 2018-09-24 10:00 | 2018-09-29 16:00 | N | N | replace breaker | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2018-09-24 10:01 | 2018-09-24 15:00 | N | Y | high load move and conductor repair (Str 101-102) | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 973L (39s Bickerdike - 310p Sundance),310p 2252 (310p Sundance),310p 2352 (310p Sundance) | 2018-09-24 13:00 | 2018-09-27 16:00 | N | Y | migrate and commission all L8 - 973L metering and protection to new RTU and LAN | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 995L (17s Benalto - 995AL tap),17s995N (17s Benalto) | 2018-09-24 13:01 | 2018-09-24 15:30 | N | Y | close Open Point 'A' at between 17s995N and Str 491 and hot line work | Switch, Line |  |  | 240 kV, Pre-Condition, Restricts Generation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2018-09-24 21:00 | 2018-09-24 22:00 | N | N | relay replacement | Line |  | 21sub 69kV BD Relay Replacement | Firm Load Loss, Creates Radial Feeds
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2018-09-24 21:00 | 2018-09-25 01:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2018-09-24 22:00 | 2018-09-24 23:00 | N | N | relay replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21) | 2018-09-24 23:00 | 2018-09-25 01:00 | N | N | relay replacement | Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2018-09-25 01:00 | 2018-09-25 06:00 | N | Y | fall substation washing | Transformer, Line |  | Fall Substation Washing (Origional outage date Sept 19th) Hotspot repair SW84 | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s CGB3 (987s Clover Bar) | 2018-09-25 06:00 | 2018-09-28 08:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
EPCOR | 805s C1 (805s Jasper) | 2018-09-25 07:00 | 2018-09-26 17:00 | N | Y | doble | Shunts |  |  | 240 kV
ALTALINK | 99s T1 (99s North St. Albert) | 2018-09-25 07:00 | 2018-09-27 18:00 | N | N | replace outdoor AC junction boxes and station service SS1 | Transformer |  |  | For Information Only
ATCO | 830S Carmon,830s 701T (830s Carmon) | 2018-09-25 07:00 | 2018-10-14 17:00 | N | Y | replace metal clad gear | Station, Transformer |  | Replace metal clad gear with AIS, 830S Carmon Breaker Replacement Project Regarding Genalta Generation: a temporary DTT relay will be installed for this outage | Restricts Generation, For Information Only
ALTALINK | 55s T1 (55s Olds) | 2018-09-25 07:30 | 2018-09-25 17:30 | N | N | move old breaker 55s443 out of yard: conductor too low | Transformer |  |  | For Information Only
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2018-09-25 08:00 | 2018-09-27 16:00 | N | N | complete the OPGW repair | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s T3 (62s Brazeau),202L (61s Lodgepole - 62s Brazeau),801L (62s Brazeau - 294s Brazeau Outlet Works),62s Brazeau 138 kV South Bus | 2018-09-25 08:00 | 2018-10-03 08:00 | N | Y | protection upgrade | Transformer, Line, Bus |  |  | 240 kV, Pre-Condition, Restricts Generation, Contingency Requires Mitigation
ENMAX | 5.8TR (ENMAX 5) | 2018-09-25 08:00 | 2018-09-25 16:00 | N | N | transfer trip upgrades | Transformer |  |  | For Information Only
CNRL | 838s 75-TR-1701 (838s Horizon Mining) | 2018-09-25 08:00 | 2018-09-26 15:00 | N | Y | emergency critical maintenance | Transformer |  | emergency critical maintenance: NGR testing and relay replacement | 240 kV
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2018-09-25 08:00 | 2018-09-25 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 635PT-1038 (635EDD-1001) | 2018-09-25 08:00 | 2018-09-26 17:00 | N | N | transformer oil leak troubleshooting and repair | Transformer
ALTALINK | 263s C1 (263s Strachan),263s 35 (263s Strachan) | 2018-09-25 08:00 | 2018-09-25 16:00 | N | N | installing new DDR- wiring and testing status and analogs from C1 protections | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 807AL (402s Shell Expansion I - 807L tap) | 2018-09-25 08:00 | 2018-09-25 17:00 | N | N | 30 minute outage window required for TPR work | Line |  | 30 minute outage window required to reseat/replace RAC 1/RFU 1. TPR 807L (233s - 402s - 410s). Differential protection to be blocked prior to the wrok. Based on Interconnection Agreement with ATCO for Shell Scotford, 807ALD2 needs to be open for loss of communication on 807L/807AL to prevent risk of mis-coordination. This needs to be communicated and confirmed with I-402s since the circuits are reroutable and loss of comm is only for 50 ms. | For Information Only
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2018-09-25 09:00 | 2018-10-04 17:00 | N | Y | line maintenance. coordinated with 62s 138 kV bus outages | Line
ALTALINK | 102s 552 (102s Langdon) | 2018-09-25 09:00 | 2018-09-25 15:00 | N | N | urgent trouble corrective:102s552 CT warning alarm | Circuit Breaker |  | 102s552 CT warning alarm came in August 13th. Tech responded to site to investigate. Alarm cleared by the time Tech arrived. Appears north phase CT is a little low on gas. When densitmeter is in direct sunlight it will cause the low gas alarm to come in. CT should be topped up. | 500 kV
ALTALINK | 61s 202X (61s Lodgepole) | 2018-09-25 09:00 | 2018-10-04 17:00 | N | Y | breaker fail protection replacement & coordinated with 202L & 62s bus outages | Circuit Breaker
REDDEER | 217s T1 (217s North Red Deer) | 2018-09-25 09:00 | 2018-09-28 15:30 | N | Y | replace switch 14-T1-2 | Transformer |  | Transformer incomer breaker 25kV bus isolation switch 14-T1-2 is no longer operable and needs to be replaced
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2018-09-25 21:00 | 2018-09-26 01:00 | N | N | fall substation washing | Line |  |  | Pre-Condition
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),162s 138-RB82 (162s Beddington),162s 138-RB83 (162s Beddington) | 2018-09-26 01:00 | 2018-09-26 06:00 | N | N | fall substation washing | Circuit Breaker, Line |  | Fall Substation Washing. 39.82L, RB82, RB83. Remove CT from 39.3TR (Origional outage Oct 14th) | Pre-Condition, Overload
ATCO | 2029s ACF13 (2029s Heathfield) | 2018-09-26 07:00 | 2018-09-27 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter Bank Maintenance and Inspection, redundant filter banks in service, no system impact | Pre-Condition, 500 kV
EPCOR | 803s T2 (803s Lambton),803s L2402 (803s Lambton),803s L2405 (803s Lambton) | 2018-09-26 07:00 | 2018-09-28 17:00 | N | Y | cutover of new relay protection | Circuit Breaker, Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 12.1TR (ENMAX 12) | 2018-09-26 08:00 | 2018-10-05 16:00 | N | N | relay protection upgrades | Transformer |  |  | For Information Only
SUNCOR | 635PT-1037 (635EDD-1001) | 2018-09-26 08:00 | 2018-09-27 17:00 | N | N | transformer oil leak troubleshooting and repair | Transformer |  |  | For Information Only
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2018-09-26 08:00 | 2018-09-26 17:00 | N | N | repair capacitor units | Circuit Breaker, Shunts |  |  | Pre-Condition
BLACKSPRING | 485s C1 (485s Blackspring),485s C2 (485s Blackspring),485s DVAR1 (485s Blacksprings),485s DVAR2 (485s Blacksprings) | 2018-09-26 09:00 | 2018-09-27 17:00 | N | Y | maintenance | Shunts |  |  | For Information Only
ENMAX, ALTALINK | 932L (74s Janet - 162s Beddington),162s 240-RB135 (162s Beddington),162s 240-136 (162s Beddington) | 2018-09-26 10:00 | 2018-09-26 18:00 | N | Y | fall substation washing | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition
VISIONREQ | 354s Summerview RTU/SCADA | 2018-09-26 11:00 | 2018-09-26 13:00 | N | N | firewall upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 404s T1 (404s Peace Butte) | 2018-09-26 12:00 | 2018-09-26 15:30 | N | N | annual maintenance | Transformer |  | perform some annual maintenance. (Customer Outage) | For Information Only
ATCO | 946s 908 (946s Oakland) | 2018-09-26 13:00 | 2018-09-28 16:00 | N | Y | 908CT ratio changes and protection settings | Circuit Breaker |  | 946S Oakland 908CT Ratio Increase, CT Ratio Changes and Protection Settings | 240 kV, Pre-Condition
ENMAX | 5.9TR (ENMAX 5),5.10TR (ENMAX 5),2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2018-09-26 23:00 | 2018-09-27 05:00 | N | N | fall substation washing, check reversing sw 5.10TR | Line, Transformer |  | fall substation washing, check reversing sw 5.10TR and oil sampling 5.10TR MT TC, 5.9TR MT, TC. time permitting | Pre-Condition
EPCOR | 816s P2404 (816s Petrolia) | 2018-09-27 07:00 | 2018-09-28 17:00 | N | Y | doble | Circuit Breaker |  |  | 240 kV
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2018-09-27 08:00 | 2018-09-27 10:59 | N | Y | high load move | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 263s T2 (263s Strachan) | 2018-09-27 08:00 | 2018-09-27 16:00 | N | N | install new DDR - wiring and testing inputs, status and analogs from Tx 18821 (T2) protections and 263s289 | Transformer |  |  | For Information Only
ENMAX | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24) | 2018-09-27 08:00 | 2018-09-27 18:00 | N | N | substation washing | Line, Transformer |  | Substation Washing. SF6 gas sample 24B138-24.82. Check reversing switch 24.2TR | For Information Only
SHELL | 847s 902 (847s Muskeg River),847s 903 (847s Muskeg River) | 2018-09-27 08:00 | 2018-09-27 16:00 | N | Y | breaker sync testing | Circuit Breaker |  |  | For Information Only
ATCO | 885s 902T (885s McMillan),885S 501R | 2018-09-27 10:30 | 2018-09-28 16:00 | N | Y | repair oil leak | Transformer, Terminal Equipment |  | Investigate and Repair Oil Leak, 240/144 tie transformer and 501 Reactor unavailable. | 240 kV
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2018-09-27 11:01 | 2018-09-27 14:00 | N | Y | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan) | 2018-09-27 12:45 | 2018-09-27 13:45 | N | N | add supervisory controls to 166s2 | Transformer |  | add supervisory controls to 166s2 | For Information Only
ALTALINK | 166s T2 (166s Dow Chemical Fort Saskatchewan) | 2018-09-27 13:46 | 2018-09-27 14:45 | N | N | add supervisory controls | Transformer |  | Add supervisory controls to 166s2 | For Information Only
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2018-09-27 21:00 | 2018-09-28 01:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2018-09-28 01:00 | 2018-09-28 06:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 501L (302s Cardinal River - 501L286) | 2018-09-28 07:00 | 2018-10-03 18:00 | N | N | working on structure #328 | Line
EPCOR | 330P Genesee | 2018-09-28 07:00 | 2018-10-22 17:00 | N | Y | maintenance | Station |  | 12GT30 advice. | Restricts Generation
ALTALINK, Lethbridge | 667L (146s MacDonald - 370s North Lethbridge), 813L (146s MacDonald - 241s Uplands), 146s T1 (146s Macdonald) | 2018-09-28 08:00 | 2018-10-04 14:00 | N | Y |  | Line, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2018-09-28 08:00 | 2018-09-28 16:00 | N | N | fall substation washing 32.3TR, 32BT5 | Line, Transformer |  |  | Pre-Condition
ALTALINK | 419s Chestermere,765L (151s Strathmore - 419s Chestermere),691L (74s Janet - 419s Chestermere) | 2018-09-28 08:00 | 2018-10-03 16:00 | N | N | ISD: Oct 01, 2018 | Station, Line
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2018-09-28 08:15 | 2018-09-28 13:45 | N | N | Fortis to install tap on U/B on 739L757 | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 171s T1 (171s Redwater) | 2018-09-28 09:00 | 2018-10-09 17:00 | N | N | urgent transformer dry out | Transformer |  |  | For Information Only
ALTALINK | 681s 1152 (681s Bannerman) | 2018-09-28 09:00 | 2018-09-28 15:30 | N | Y | N ph densimeter repalcement | Circuit Breaker |  |  | 240 kV
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34) | 2018-09-28 23:00 | 2018-09-29 05:00 | N | N | fall substation washing, oil sample & maintenance | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 987s GDS2 (987s Cloverbar) | 2018-09-29 | 2018-09-30 20:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | Woodcroft T3 (Woodcroft) | 2018-09-29 07:00 | 2018-09-30 17:00 | N | N | doble | Transformer |  |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703L33) | 2018-09-29 07:00 | 2018-09-29 12:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),26.81L (ENMAX 32 - ENMAX 26) | 2018-09-29 08:00 | 2018-09-29 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-09-30 01:00 | 2018-09-30 06:00 | N | N | locate on 1.80L to facilitate 1.81L manhole construction | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41),41.84L (ENMAX 54 - ENMAX 41) | 2018-09-30 08:00 | 2018-09-30 18:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 916L (42s Sarcee - 5s East Calgary) | 2018-10-01 07:00 | 2018-10-04 17:00 | N | Y | 916L POW breaker (1352) modifications | Line |  |  | 240 kV, Pre-Condition
EPCOR | 803s T1 (803s Lambton),803s L2401 (803s Lambton),803s L2402 (803s Lambton) | 2018-10-01 07:00 | 2018-10-03 17:00 | N | Y | cutover of new relay protection | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 34.2TR (ENMAX 34) | 2018-10-01 08:00 | 2018-10-03 16:00 | N | N | LTC maintenance | Transformer |  |  | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2018-10-01 08:00 | 2018-10-01 16:00 | N | N | T60 CPU upgrade | Transformer |  | T60 CPU upgrade | For Information Only
ENMAX | 11.1TR (ENMAX 11) | 2018-10-01 08:00 | 2018-10-01 16:00 | N | N | CT maintenance | Transformer |  | Seal up the cracked CTs with silicone | For Information Only
ENMAX, ALTALINK | ENMAX 47,771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington) | 2018-10-01 08:00 | 2018-10-03 18:00 | N | N | fall substation washing | Line, Circuit Breaker, Station |  | Fall Substation Washing. 771L, RB81, RB82, 47.1TR, 47.2TR, 47-BT3, 47-SW81. Doble 162PT138-771. Dashpot checks RB81, RB82 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
REDDEER | 209s T1 (209s Timberlands) | 2018-10-01 09:00 | 2018-10-04 15:30 | N | N | oil leak repairs | Transformer |  |  | For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2018-10-01 09:00 | 2018-10-01 10:00 | N | N | 43s auto-switching and 138kV BD relay replacement | Line |  | 43s Autoswitching and 138kV BD relay replacement. Outage required to short out BD CTs. | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s C1 (305s Acheson) | 2018-10-01 10:00 | 2018-10-01 15:30 | N | N | replacement of A protection relays | Shunts |  | Replacement of Cap Bank C1 A protection relay with retrofit relay in existing module. Continued from back in August | Pre-Condition
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2018-10-01 10:00 | 2018-10-04 16:00 | N | Y | migrate and commission all L4 - 1046L at 310p Sundance associated alarms, status, controls, metering and remote access to new RTU and LAN | Line |  | Migrate and commission all L4 - 1046L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L4 alarms. | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 946s 909 (946s Oakland) | 2018-10-01 10:00 | 2018-10-02 12:00 | N | Y | change CT ratio and protection settings | Circuit Breaker |  | 946S Oakland BKR 909 CT Ratio Increase CT Ratio Changes and Protection Settings | 240 kV, Pre-Condition
ENMAX | 43.1TR (ENMAX 43) | 2018-10-01 10:00 | 2018-10-01 11:00 | N | N | relay replacement | Transformer |  | 43s Autoswitching and 138kV BD relay replacement. Outage required to short out BD CTs. | For Information Only
ENMAX | 43.2TR (ENMAX 43) | 2018-10-01 11:00 | 2018-10-01 12:00 | N | N | relay replacement | Transformer |  | 43s Autoswitching and 138kV BD relay replacement. Outage required to short out BD CTs. | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2018-10-01 12:00 | 2018-10-04 18:00 | Y | Y | maintenance components | Line | Peak RC COS outage ID: 1-00538722 Peak RC Path Derate ID: 1-00538728 (E>W), 1-00538724 (W>E) |  | Limits ATC, 500 kV
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2018-10-01 12:00 | 2018-10-01 16:00 | N | N | settings change on relays | Line |  | Outage required to short out BD CTs. Settings change on relays. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 263s 652 (263s Strachan) | 2018-10-01 13:00 | 2018-10-01 16:00 | N | N | installing new DDR- wiring and testing status and analogs from 263s239X breaker | Circuit Breaker |  | Installing new DDR- wiring and testing status and analogs from 263s239X Breaker | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2018-10-01 21:00 | 2018-10-01 22:00 | N | N | 69kV BD relay replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2018-10-01 22:00 | 2018-10-01 23:00 | N | N | 69kV BD relay replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21) | 2018-10-01 23:00 | 2018-10-02 01:00 | N | N | relay replacement | Transformer |  | 21sub 69kV BD Relay Replacement | For Information Only
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan),166s T2 (166s Dow Chemical Fort Saskatchewan) | 2018-10-02 07:00 | 2018-10-03 12:00 | N | Y | customer switchgear maintenance | Transformer |  |  | For Information Only
ALTALINK | 703L (213s Hughenden - 703L33) | 2018-10-02 07:00 | 2018-10-02 12:00 | N | N | high load move | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36) | 2018-10-02 08:00 | 2018-10-02 16:00 | N | N | seal up the cracked CTs with silicone | Transformer |  |  | For Information Only
ALTALINK | 61s T1 (61s Lodgepole) | 2018-10-02 08:00 | 2018-10-02 12:00 | N | N | tie in trips to new 61s202X controls | Transformer |  |  | For Information Only
ALTALINK | 277s T1 (277s Hayter) | 2018-10-02 08:00 | 2018-10-02 17:00 | N | N | 25kV Bushing bird cover up replacement | Transformer |  |  | For Information Only
ALTALINK | 520s T1 (520s Bennett) | 2018-10-02 10:15 | 2018-10-04 17:45 | N | Y | installing a main tank oil filter on TX18415 | Transformer |  |  | For Information Only, 500 kV
ALTALINK | 887S Carson Creek,887s T1 (887s Mobil Oil Carson Creek),887s 520 (887s Carson Creek) | 2018-10-02 12:30 | 2018-10-04 16:00 | N | N | maintenance and doble | Transformer, Circuit Breaker, Station |  | 887s520 10 PSI low of gas. ADD: CB 2332 (887s520) CS SF6 CSV- 145 (TX), 887s Tx18145 T1 doble PIO/NONE 69/4.16K, 887s T1 SFRA test | For Information Only
ALTALINK | 510s 2852 (510s Sunnybrook) | 2018-10-03 07:00 | 2018-10-17 14:00 | N | Y | Installing new 510s2952, CT's, 510s46, 510s48 and protection; Closing Open Points 'A', 'B', 'D' & 'E' | Circuit Breaker |  | Installing new 510s2952, CT's, 510s46, 510s48 and protection; Closing Open Points 'A', 'B', 'D' & 'E' | 500 kV
ALTALINK | 263s T1 (263s Strachan) | 2018-10-03 08:00 | 2018-10-03 16:00 | N | N | installing new DDR | Transformer |  | Installing new DDR - wiring and testing inputs, status and analogs from Tx 18616 (T1) protections and 263s1. Add ACC supervisory to 263s1 | For Information Only
ALTALINK | 650s SVC (650s Hansman Lake) | 2018-10-03 08:00 | 2018-10-04 15:00 | N | Y | inspection on the SVC | Shunts |  |  | 240 kV
ALTALINK | 62s T3 (62s Brazeau),62s T5 (62s Brazeau),202L (61s Lodgepole - 62s Brazeau),801L (62s Brazeau - 294s Brazeau Outlet Works) | 2018-10-03 08:00 | 2018-10-04 18:00 | N | Y | protection upgrade | Transformer, Line |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 166s T3 (166s Dow Chemical Fort Saskatchewan) | 2018-10-03 12:00 | 2018-10-04 17:00 | N | Y | switchgear maintenance | Transformer |  |  | For Information Only
ALTALINK | 767L (310p Sundance - 767L50) | 2018-10-04 07:00 | 2018-10-08 16:00 | N | N | dragline crossing line at Sundance Mine between Structures #42 & 43 | Line |  |  | Pre-Condition
Syncrude | SCL1 Syncrude #1 | 2018-10-04 08:00 | 2018-10-22 16:00 | N | N | G3 & G5 upgrade. ISD Oct 19, 2018 | Unit
Syncrude | Mildred T3 (Syncrude Mildred Lake) | 2018-10-04 09:00 | 2020-02-24 07:59 | N | Y | damaged transformer repairs (P2039) | Transformer | Mildred T3 (Syncrude Mildred Lake) |  | For Information Only
ALTALINK | 294s 201 (294s Brazeau Outlet Works) | 2018-10-04 12:30 | 2018-10-04 14:00 | N | N | add supervisory controls to 294s201 | Switch |  |  | For Information Only
ALTALINK | 62s T4 (62s Brazeau) | 2018-10-04 18:00 | 2018-10-12 18:00 | N | N | protection upgrade | Transformer |  |  | For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2018-10-04 22:00 | 2018-10-05 06:00 | N | N | 11 sub building construction | Line |  |  | For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2018-10-05 02:00 | 2018-10-05 07:00 | N | N | maintenance | Switch |  |  | For Information Only
ALTALINK | 62s T1 (62s Brazeau),62s T2 (62s Brazeau),62s T3 (62s Brazeau),62s T5 (62s Brazeau),995L (62s Brazeau - 995AL tap),62s Brazeau 240kV Bus | 2018-10-05 03:00 | 2018-10-05 07:00 | N | Y | protection upgrade | Bus, Line, Transformer |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 974L (39s Bickerdike - 310p Sundance),310p 152 (310p Sundance),310p 252 (310p Sundance),310p 352 (310p Sundance),310P T2 (310p Sundance) | 2018-10-05 07:00 | 2018-10-06 18:00 | N | Y | dragline crossing line at Sundance Mine between Structures #84 & 85 | Line, Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2018-10-05 07:00 | 2018-10-06 18:00 | N | Y | dragline crossing line at Sundance Mine between Structures #84 & 85 | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 704L (51s Wainwright - 478s Tuccuman) | 2018-10-05 07:00 | 2018-10-05 14:00 | N | N | urgent: replace a section of overhead shield wire that has come loose | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 511s Victoria T5 (511s Victoria) | 2018-10-05 08:00 | 2018-10-11 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ALTALINK | 511s ACF22 (511s Crossings) | 2018-10-05 08:00 | 2018-10-12 16:00 | N | N | forced outage | Shunts
ENMAX | 20.1TR (ENMAX 20) | 2018-10-06 06:00 | 2018-10-06 18:00 | N | N | 20 sub roof replacement (EAST) | Transformer |  |  | For Information Only
ENMAX | 1.5TR (ENMAX 1) | 2018-10-06 08:00 | 2018-10-14 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2018-10-06 09:00 | 2018-10-06 18:00 | N | N | fall substation washing | Line, Transformer, Shunts |  | Fall Substation Washing 31.1. 31CAP, 31.2. HV SW84 adjustment. | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-10-07 01:00 | 2018-10-07 06:00 | N | N | locate on 1.80L to facilitate 1.81L manhole construction | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20) | 2018-10-07 06:00 | 2018-10-07 18:00 | N | N | 20 sub roof replacement (West) | Transformer |  | 20 sub roof replacement (West). Station service TR already transferred | For Information Only
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2018-10-07 07:00 | 2018-10-08 18:00 | N | N | dragline crossing line at Sundance Mine between Structures # 96 & 97 | Line |  | Dragline crossing line at Sundance Mine between Structures #96 & 97 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 162.81L (ENMAX 162 Beddington - 391S Balzac) | 2018-10-07 08:00 | 2018-10-07 18:00 | N | Y | fall substation washing | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 989L (310p Sundance - 77s Sagitawah) | 2018-10-07 08:00 | 2018-10-08 19:00 | N | N | dragline crossing line at Sundance Mine between Structures # 96 & 97 | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 515s T1 (515s FedpipeJudy Creek) | 2018-10-07 08:00 | 2018-10-13 16:00 | N | N | transformer replacement with a refurbished transformer TX 18332 (72/4.156 kV, 7.5/10 MVA, OLTC). ISD: October 10, 2018 | Transformer
ALTALINK | 752AL (316s West Crossfield - 752L),752L (64s East Crossfield - 752L67) | 2018-10-08 07:00 | 2018-10-14 16:00 | N | Y | project rebuild of 752L of str1-70 | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
ENMAX | 37.81L (ENMAX 38 - ENMAX 37) | 2018-10-08 08:00 | 2018-10-08 18:00 | N | N | HV breaker maintenance 38B138-37.81 | Line |  |  | Creates Radial Feeds
ALTALINK | 163s68 (163s Amoco Empress),163s 67 (163s Amoco Empress) | 2018-10-08 08:00 | 2018-10-13 16:00 | N | N | replace 163s68 and 163s67. ISD: Oct 11, 2018. | Circuit Breaker, Switch
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2018-10-08 08:30 | 2018-10-08 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred_T14 (Syncrude Mildred Lake) | 2018-10-08 09:00 | 2018-10-31 16:00 | N | N | maintenance | Transformer |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2018-10-08 12:00 | 2018-10-08 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 853s 701T (853s Ring Creek),7L82 (855s Hamburg - 853s Ring Creek),853S 501VR,853s Ring Creek 144kV Bus 700BS1 | 2018-10-09 07:00 | 2018-10-17 15:30 | N | Y | protection upgrade, replace 501VRX - 853S Ring Creek Protection Upgrade Project | Bus, Terminal Equipment, Line, Transformer |  | Protection upgrade, replace 501VRX 853S Ring Creek Protection Upgrade Project | Pre-Condition, Overload, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO | 2029s ACF11 (2029s Heathfield) | 2018-10-09 07:00 | 2018-10-10 15:30 | N | Y | filter bank maintenance and inspection | Shunts |  | Filter Bank Maintenance and Inspection, redundant filter banks in service, no system impact | Pre-Condition, 500 kV
EPCOR | Namao N724 (Namao) | 2018-10-09 07:00 | 2018-10-09 17:00 | N | N | maintenance | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss
ALTALINK | 562s T1 (562s Cypress) | 2018-10-09 07:30 | 2018-10-10 12:30 | N | Y | replace qualitrol relay | Transformer |  |  | 240 kV
ENMAX | 8.2TR (ENMAX 8) | 2018-10-09 08:00 | 2018-10-11 16:00 | N | N | testing and maintenance | Transformer |  | Clean and inspect North HV Bushing. Check reversing switch. Network required to transfer alternates. | For Information Only
ENMAX | 162s 138_RB94 (162s Beddington),162s 138_RB92 (162s Beddington),162.4TR. 162PT138-T4 | 2018-10-09 08:00 | 2018-10-11 16:00 | N | N | oil sample, repair SW107, replace tapchanger counter, check reversing switch, filmax LTC filtration maintenance, rewire 43 switch, fall substation washing 162.4TR, RB94 | Terminal Equipment, Circuit Breaker |  | oil sample TR, TC, H1, H2, H3. Repair SW107. Replace tapchanger counter. Check reversing switch. Filmax LTC Filtration Maint. Rewire 43 switch. Fall substation washing 162.4TR, RB94 | For Information Only
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2018-10-09 08:00 | 2018-10-11 16:00 | N | N | change arms insulators | Line |  | Change Arms Insulators fiberglass to wood NO STUDY SENT YET | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2018-10-09 08:00 | 2018-10-14 18:50 | N | N | replace 138KV airbreak | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 927L (102s Langdon - 356s Milo) | 2018-10-09 08:15 | 2018-10-10 08:00 | N | Y | emergency repair: repair spacers on Str175, 203 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2018-10-09 08:15 | 2018-10-09 17:45 | N | N | emergency repair 90L38 | Line |  | Emergency Repair 90L38; Broken strands from lighting strike and replace flashed insulation string | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 29S Cascade | 2018-10-09 09:00 | 2018-10-19 19:00 | N | N | 13.8KV bus outage | Station |  | 13.8KV bus outage for breaker retrofits on 29S40, 29S54, 29S1, 29S2 | For Information Only
ALTALINK | 850L (525s Carseland - 678s Okotoks),678s 850 (678s Okotoks) | 2018-10-09 11:00 | 2018-10-09 17:00 | N | N | replace heater | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1112L (289s Saunders Lake - 89s Ellerslie),89s 1452 (89s Ellerslie),89s 1552 (89s Ellerslie) | 2018-10-09 12:00 | 2018-10-12 18:00 | N | Y | component replacements between structures #1 - 49 | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO | 9L948 (650s Hansman Lake - 863s Paintearth) | 2018-10-10 08:00 | 2018-10-10 17:00 | N | Y | change pole #301 on 9L948 | Line |  | Change Pole #301 on 9L948 | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 244s 552 (244s Bowmanton) | 2018-10-10 08:00 | 2018-10-10 14:00 | N | Y | top up gas on the center phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 924L (102s Langdon - 356s Milo) | 2018-10-10 08:01 | 2018-10-10 17:45 | N | Y | emergency repair | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 744L (228s T.M.P.L.Niton - 207s Pinedale),890L (58s Edson - 207s Pinedale) | 2018-10-10 08:30 | 2018-10-11 17:30 | N | N | create open point G between 207s4 and 138kV bus and close open point B | Line |  | Create open point "G" between 207s4 and 138kV Bus to allow relocation of switches and breaker to new T2 bay. Close Open Point 'B', relocate existing AMI to 25kV bus 1 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 526s T2 (526s Buffalo Creek) | 2018-10-10 09:00 | 2018-10-10 15:00 | N | N | leaking tap changer oil filter | Transformer |  |  | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo),405s 633 (405s Waupisoo) | 2018-10-10 09:00 | 2018-10-10 17:30 | N | N | 405s633 tank heater failing | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s T2 (17s Benalto) | 2018-10-10 09:30 | 2018-10-10 16:30 | N | Y | urgent CT wiring changes, testing and investigation | Transformer |  | Urgent Trouble Corrective: Discovered more issues with the CTs. Techs to perform CT wiring changes and CT testing/ investigation.Urgent Repairs. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 370s T4 (370s North Lethbridge) | 2018-10-10 09:30 | 2018-10-18 13:00 | N | N | A and B protection move to new building | Transformer |  | T4 A and B protection move to new building. Completing trip testing to breakers on 138 kV Bus 1.
TRANSALTAW | 418s T1 (418s Ardenville) | 2018-10-10 10:00 | 2018-10-10 13:00 | N | N | replace disconnects on PT | Transformer |  |  | Restricts Generation
ALTALINK | 250p11 (250p Bighorn Plant) | 2018-10-10 11:00 | 2018-10-10 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 13.3TR (ENMAX 13) | 2018-10-10 11:00 | 2018-10-10 16:00 | N | N | testing and maintenance | Transformer |  | Gas relay testing. Check reversing switch. Oil sampling MT, TC | For Information Only
ALTALINK | 562s T2 (562s Cypress) | 2018-10-10 12:30 | 2018-10-11 16:30 | N | Y | replace qualitrol relay | Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-10-11 07:00 | 2018-10-26 18:00 | N | N | energize/de-energize bypass line between Str365 and Str379 to rebuild of 551L | Line |  | Energize/de-energize bypass line between Str365 and Str379 to allow for rebuild of 551L (Sections 16A). Bypass to be energized/de-energized using live line techniques; no interruption to 551L loads | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2018-10-11 08:00 | 2018-10-11 16:00 | N | N | investigate oil leak | Transformer |  | investigate oil leak in secondary cabinet | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde),159s 223 (159s Colinton) | 2018-10-11 08:30 | 2018-10-11 17:30 | N | N | 159s223 tank heater failing | Circuit Breaker, Line |  | 159s223 Tank Heater Failing, ADD: 159sT1 Monitor Fail | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 672L (235s Entwistle - 131s Moon Lake),131s 672 (131s Moon Lake) | 2018-10-11 08:30 | 2018-10-11 17:30 | N | N | 131s672 tank heaters failing | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 890L (58s Edson - 207s Pinedale),207S T2 (207S Pinedale),138 kV BUS 2 (207S Pinedale) | 2018-10-11 17:31 | 2018-10-29 14:30 | N | N | relocate 890L from 138kV bus 1 to 138kV bus 2 | Line, Transformer, Bus |  | Relocate 890L from 138kV bus 1 to 138kV bus 2, add new VT4. Complete construction of new bus, T2 and assoiciated equipment, close open points D, E & F | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 985S Exshaw | 2018-10-13 06:00 | 2018-10-13 08:00 | N | N | emergency disconnection | Station |  |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2018-10-13 08:00 | 2018-10-13 16:00 | N | N | SF6 gas sample 14B138-14.83 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.1TR (ENMAX 43),9.83L (ENMAX 43 - ENMAX 9) | 2018-10-13 08:30 | 2018-10-13 12:00 | N | N | 43s autoswitching and 138kV bus differential relay replacement, adjust MD status contact, remove kite from bus | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.2TR (ENMAX 43),33.84L (ENMAX 43 - ENMAX 33) | 2018-10-13 12:00 | 2018-10-13 16:00 | N | N | ENMAX 43 autoswitching and 138kV bus differential relay replacement, adjust motorized disconnect status contact | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20) | 2018-10-13 12:00 | 2018-10-15 06:00 | N | N | 20 sub roof replacement (West). | Transformer |  |  | For Information Only
ALTALINK | 985S Exshaw | 2018-10-13 22:00 | 2018-10-13 23:30 | N | N | emergency disconnection | Station |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-10-14 01:00 | 2018-10-14 06:00 | N | N | locate on 1.80L to facilitate 1.81L manhole construction | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),26.81L (ENMAX 32 - ENMAX 26) | 2018-10-14 08:00 | 2018-10-14 18:00 | N | N | fall substation washing 32.1, 32.2, 32BT5 | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s23 (391s Balzac) | 2018-10-14 16:00 | 2018-10-16 18:00 | N | Y | perform yearly maintenance | Switch, Line |  |  | Restricts Generation
EPCOR | 657s SU2404 (657s Summerside) | 2018-10-15 07:00 | 2018-10-15 17:00 | N | Y | refill SF6 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2018-10-15 07:00 | 2018-10-18 18:00 | N | N | line maintenance | Line |  | Line Maint. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2018-10-15 07:15 | 2018-11-05 17:45 | N | N | rebuild (Str 514-611) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L84 (722s Crystal Lake - 749s Flyingshot Lake) | 2018-10-15 08:00 | 2018-10-17 16:00 | N | Y | crossarm changes | Line |  | Crossarm Changes | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 2L294 (Nelway - A.A. Lambert) | 2018-10-15 08:00 | 2018-10-15 16:00 | N | Y | CB3-1 switch replacement, to create bus cut | Line | Fortis Annual Plan 2018 (Outage)AAL CB3-1 Switch Replacement, to CREATE BUS CUT to RESTORE 2L294 during the replacement of CB3-1 |  | Pre-Condition, Limits ATC
ENMAX | 38.1TR (ENMAX 38) | 2018-10-15 08:00 | 2018-10-25 16:00 | N | N | bushing replacement, fix leaking pipe | Transformer |  |  | For Information Only
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2018-10-15 08:00 | 2018-10-18 16:00 | N | N | change arm insulators fiberglass to wood | Line |  | Change Arms Insulators fiberglass to wood NO STUDY SENT YET | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 722s 701T (722s Crystal Lake) | 2018-10-15 10:00 | 2018-10-19 17:00 | N | N | tap changer maintenance | Transformer |  | Tap changer maintenance. Manufacturers rep will be on site | For Information Only
ATCO | 706s 701T (706s Irish Creek) | 2018-10-15 10:00 | 2018-10-26 16:00 | N | N | differential relay replacement | Transformer |  | 706S - 701T 87 Relay Replacement 701T and 501VR will be out of service for the duration of work. 702T will be in service | For Information Only
ENMAX | 6.80L (ENMAX 35 - ENMAX 6) | 2018-10-15 10:00 | 2018-10-15 13:00 | N | N | fall substation washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T1 (65s High River),13L/158L (65s High River - 392s Black Diamond) | 2018-10-15 10:00 | 2018-10-18 18:00 | N | N | replace bushings and install bird cover, 65s24 switch repairs | Line, Transformer |  | Replace the T1 72kV bushings, as well as Y1, Y2, Y3, Y4 and N bushings, bird cover will be installed on the Y bushings. 65s24 Switch repairs | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 64s T2 (64s East Crossfield),901AL (64s East Crossfield - 901L tap),901L (63s Red Deer - 74s Janet) | 2018-10-15 10:30 | 2018-10-25 15:00 | N | Y | replace 64s901 breaker to SF6 type | Line, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 171s T2 (171s Redwater) | 2018-10-15 11:30 | 2018-10-18 17:30 | N | N | bushing replacement | Transformer |  | 171s T2, 138kV and 25kV Bushing Replacement | For Information Only
ALTALINK | 914L (289s Saunders Lake - 86s Bigstone) | 2018-10-15 12:00 | 2018-10-18 18:00 | N | Y | component replacements | Line |  | Component replacements between Structures #52 - 143 | 240 kV, Pre-Condition
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2018-10-15 12:00 | 2018-10-19 10:00 | N | N | move mobile onto site (3L required due to proximity) and create open point 'E" | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 672L (235s Entwistle - 131s Moon Lake) | 2018-10-15 12:30 | 2018-10-16 17:30 | N | N | 235s672 tank heaters failing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 35.81L (42s Sarcee - ENMAX 35) | 2018-10-15 13:00 | 2018-10-15 16:00 | N | Y | fall substation washing | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 72s T1 (72s Leismer) | 2018-10-16 07:00 | 2018-10-18 18:00 | N | Y | transformer bushing replacement | Transformer |  | Extended from Oct 17th to 18th due to bushing failure. | 240 kV, Pre-Condition, For Information Only
ALTALINK | 511s ACF22 (511s Crossings) | 2018-10-16 07:30 | 2018-10-16 15:30 | N | N | investigate overcurrent trip on October 4th during switching of Bennett Tx | Shunts |  | 511s Filter Bank ACF22 outage to investigate overcurrent trip on October 4th during switching of Bennett Tx. Looking at this element now that personnel are available. | 240 kV
AESO-SC | Northwestern Energy BUCC test | 2018-10-16 08:00 | 2018-10-16 12:00 | N | N | BUCC test | Station |  |  | For Information Only
ENMAX, ALTALINK | 771L (162s Beddington - ENMAX 47),162s 138-RB81 (162s Beddington),162s 138-RB82 (162s Beddington) | 2018-10-16 08:00 | 2018-10-17 18:00 | N | N | fall substation washing | Circuit Breaker, Line |  | Fall Substation Washing. 771L, RB81, RB82, 47.1TR, 47.2TR, 47-BT3, 47-SW81. Doble 162PT138-771. Dashpot checks RB81, RB82. Backfeed SST through 25kV bus | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2018-10-16 08:30 | 2018-10-16 18:00 | N | N | hydrovacing near line | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L52 (Ingledow - Custer) | 2018-10-16 09:00 | 2018-10-19 17:00 | N | Y | ING 5CB12 inspection | Line |  | ING 5D23 cutting over controls to new station control equipment. (PLC upgrade project) Replace failed glass on 9 structures. Requires outage - unable to do hot. Issues last summer with this circuit - main feed to the states. Cannot wait until October - complete ASAP | Limits ATC, 500 kV
ALTALINK | 102s 6852 (102s Langdon) | 2018-10-16 09:30 | 2018-10-16 15:30 | N | N | repair leaking CT | Switch |  | Urgent trouble corrective: top up CT on 102s6852 SF6/N2. Leaking CT is not a good idea to leave, the warning alarm is in | 240 kV, For Information Only
TRANSALTA | 239s Castle River RTU/SCADA | 2018-10-16 10:00 | 2018-10-16 17:00 | N | N | firewall updates | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 370s T3 (370s North Lethbridge) | 2018-10-17 07:00 | 2018-10-17 10:30 | N | Y | trip test 370s2152 from new T4 protections | Transformer |  |  | 240 kV, Pre-Condition
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2018-10-17 08:00 | 2018-10-19 16:00 | N | Y | remediate bird mess inside insulating blankets | Circuit Breaker |  | Remediate Bird Mess Inside Insulating Blankets [AVANTIS]. Counter Repair Near and Center Phases [AVANTIS]. Replace Cabinet Door Handle [AVANTIS] | 240 kV, Contingency Requires Mitigation
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle),235s 799N (235s Entwistle) | 2018-10-17 08:30 | 2018-10-17 17:30 | N | N | repair 235s799N tank heaters | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 72s C2 (72s Leismer),72s 3052 (72s Leismer) | 2018-10-17 09:30 | 2018-10-18 13:30 | N | N | 72s3052 tank heater failing | Circuit Breaker, Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 322s Cowley Ridge RTU/SCADA | 2018-10-17 10:00 | 2018-10-18 11:00 | N | N | firewall updates | Terminal Equipment |  |  | Affects Visibility
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge),370s 207X (370s North Lethbridge) | 2018-10-17 10:31 | 2018-10-17 14:00 | N | Y | trip test from new T4 A & B protections | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage
ALTALINK, Lethbridge | 370s 175 (370s North Lethbridge),172L (370s North Lethbridge - 181s Chinook) | 2018-10-17 14:01 | 2018-10-17 17:30 | N | Y | trip test from new T4 A & B protections | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
STROBE | 240s T2 (240s McBride Lake) | 2018-10-18 07:00 | 2018-10-18 12:00 | N | N | troubleshooting and repair 138DS2 | Transformer |  |  | Restricts Generation
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2018-10-18 07:15 | 2018-10-18 10:45 | N | Y | create open point 'z' (str103) | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge),370s 770E (370s North Lethbridge) | 2018-10-18 07:30 | 2018-10-18 11:00 | N | N | trip test from new T4 A & B protections | Circuit Breaker, Line |  |  | Pre-Condition
SUNCOR | 635PT-1003 (635EDD-1000) | 2018-10-18 08:00 | 2018-10-19 17:00 | N | N | repair oil leaks | Transformer |  |  | For Information Only
AESO-SC | Northwestern Energy BUCC test | 2018-10-18 08:00 | 2018-10-18 12:00 | N | N | BUCC test | Station |  |  | For Information Only
ENMAX | 162s 138-RB85 (162s Beddington),162.3TR (ENMAX 162 Beddington),162s 138-RB86 (162s Beddington) | 2018-10-18 08:00 | 2018-10-18 18:00 | N | N | fall substation washing and oil sampling | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2018-10-18 08:30 | 2018-10-22 16:00 | N | N | NGR installation | Transformer |  |  | For Information Only
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2018-10-18 09:00 | 2018-10-18 12:00 | N | N | correct cycling alarm condition on radio link 45s-9038R which in turn is causing the HMI to build a buffer, also upgrade the MPLS nodes to newer firmware version | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 157s T1 (157s Lac La Biche) | 2018-10-18 10:00 | 2018-10-18 16:00 | N | N | install bird cover | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - Open Point 'Z') | 2018-10-18 10:46 | 2018-10-22 07:44 | N | Y | component replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 370s T4 (370s North Lethbridge),370s 2552 (370s North Lethbridge) | 2018-10-18 12:30 | 2018-10-25 17:30 | N | N | T4 A and B protection move to new building | Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 12.2TR (ENMAX 12) | 2018-10-19 08:00 | 2018-10-19 16:00 | N | N | gas relay testing, check reversing switch, oil sampling | Transformer |  |  | For Information Only
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2018-10-19 10:30 | 2018-10-19 12:30 | N | N | connect 470s mobile to 3L | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 272S Spring Bank,3L (272s Springbank - 3L147) | 2018-10-19 15:00 | 2018-10-26 09:00 | N | N | replacements / maintenance | Station, Line |  | 272s1 Visibility, 272s T1, Station Switches Replacements / Maintenance, & 25kV Metering 272s13 PT Replacement. Replace 272s236N to V/B | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 41.1TR (ENMAX 41),40.81L (ENMAX 40 - ENMAX 41),41.84L (ENMAX 54 - ENMAX 41) | 2018-10-20 08:00 | 2018-10-20 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2018-10-20 08:00 | 2018-10-20 16:00 | N | N | 14B138-11.82L HV breaker maintenance | Line |  | 14B138-11.82L HV breaker maintenance (Fall outage due to summer loading) | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 29S Cascade | 2018-10-20 09:00 | 2018-10-30 19:00 | N | N | 13.8 kV bus outage for breaker retrofits | Station |  | TAU 13.8KV bus outage for breaker retrofits on 29S40, 29S54, 29S1, 29S2 | For Information Only
EPCOR | 330p 1207 (330p Genesee),330p 1208 (330p Genesee) | 2018-10-21 07:00 | 2018-10-22 17:00 | N | Y | customer outage | Circuit Breaker |  |  | Pre-Condition, 500 kV
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2018-10-21 08:30 | 2018-10-21 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2018-10-21 12:00 | 2018-10-21 18:00 | N | N | fall substation washing and check reversing SW | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 5L72 (Mica Creek - Nicola) | 2018-10-21 15:00 | 2018-11-18 15:00 | N | Y | switchgear roof replacement | Line | BC Outage Peak RC COS: 1-00597148 AB Peak RC COS# : 1-00602641 (W>E), 1-00602643 (E>W) |  | Limits ATC, 500 kV
ATCO | 853s 702T (853s Ring Creek),7L113 (853s Ring Creek - 930s Arcenciel),853s Ring Creek 144kV Bus 700BS2 | 2018-10-22 07:00 | 2018-10-30 17:00 | N | Y | protection upgrade, replace 502VRX | Transformer, Line, Bus |  | Protection upgrade, replace 502VRX | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2018-10-22 07:00 | 2018-10-25 18:00 | N | N | line maintenance | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 886s 701T (886s Updike) | 2018-10-22 07:00 | 2018-10-26 17:00 | N | N | protection upgrade | Transformer |  | Protection upgrade | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark),Meadowlark T1 (Meadowlark) | 2018-10-22 07:00 | 2018-10-27 17:00 | N | N | disconnect replacement | Transformer, Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft T1 (Woodcroft) | 2018-10-22 07:00 | 2018-11-02 17:00 | N | N | cutover of new transformer protection | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 286s T1 (286s Yasa) | 2018-10-22 07:00 | 2018-10-26 14:00 | N | N | emergency customer outage | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 725BL (725BL54 - 240s McBride Lake),725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2018-10-22 07:45 | 2018-10-22 13:15 | N | N | close open point 'Z' and create open point 'Y' (Str102) | Line |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2018-10-22 08:00 | 2018-10-22 18:00 | N | N | fall substation washing | Line, Transformer |  |  | For Information Only
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2018-10-22 08:00 | 2018-10-23 17:30 | N | Y | replace valve cooling pump | Shunts, Transformer |  | Replace valve cooling pump to restore cooling capacity and eliminate reoccurring alarms. The failure initiating this work resulted in a SVC+ trip on October 15th. This work requires a 3rd party contractor who is only available Monday onward. No impact to Link Dispatch for MW transfer. | 240 kV
ENMAX | 32.3TR (ENMAX 32) | 2018-10-22 08:00 | 2018-10-25 16:00 | N | N | HICO transformer tap changer re-plumb and check reversing switch | Transformer |  |  | For Information Only
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2018-10-22 08:00 | 2018-10-25 16:00 | N | N | change arms insulators fiberglass to wood | Line |  | Change Arms Insulators fiberglass to wood NO STUDY SENT YET | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 15s Fort Macleod 138kV Bus2,15s T2 (15s Fort Macleod) | 2018-10-22 09:30 | 2018-10-26 12:45 | N | N | move 138kV Bus 2, T2 & 25 kV bus 2 from CI to GOI, close open points "A", "B" "C", relocate VT9 from existing 725L to new 725L bay, trip testing | Transformer, Bus |  |  | For Information Only
ATCO | 959s 904 (959s Lanfine) | 2018-10-22 10:00 | 2018-10-24 17:00 | N | Y | CT ratio change and associated relay changes | Circuit Breaker |  | CT Ratio Changes and Associated Relay Changes, Associated with 904CT and 50BF/904 Relay | 240 kV, Contingency Requires Mitigation
ALTALINK | 253S Blackie,253s C1 (253s Blackie),753L (65s High River - 253s Blackie),851L (525s Carseland - 253s Blackie),876L (179s Gleichen - 253s Blackie) | 2018-10-22 10:15 | 2018-11-02 17:45 | N | N | convert analog station to digital project | Line, Station, Shunts |  | convert analog station to digital project, Add new line PT's 253s12, 253s11 and rename the existing PT's to align with naming standard. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2018-10-22 12:00 | 2018-10-26 18:00 | N | Y | component replacements between structures #144 - 391 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 89s 252 (89s Ellerslie) | 2018-10-22 12:30 | 2018-10-22 17:30 | N | Y | 889s252 low gas south pole | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 285s T1 (285s East Camrose),730L (285s East Camrose - 730L62),285s East Camrose 138kV Partial Bus,285s 96 (285s East Camrose) | 2018-10-22 13:00 | 2018-10-23 08:30 | N | N | replace 138 kV bus protections | Line, Bus, Switch, Transformer |  | Replace 138kV bus protections. Outage on 730L and T1 required to isolate currents coming to old summation module | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO | 725L (15s Fort Macleod - Open Point 'Y') | 2018-10-22 13:16 | 2018-10-26 12:00 | N | N | disconnect 725L & VT3 from 138 KV bus and relocate to new bay, and AML lines, component replacements (Str 1- 102) | Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 21.1TR (ENMAX 21) | 2018-10-23 08:00 | 2018-10-23 16:00 | N | N | replace 21.1TR lightning arrestors | Transformer |  |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2018-10-23 08:00 | 2018-11-05 16:00 | N | N | lightning arrestor replacement, NGR installation | Transformer |  |  | For Information Only
ALTALINK | 419s T1 (419s Chestermere) | 2018-10-23 08:00 | 2018-10-25 10:00 | N | N | install bird cover-up, close open point J | Transformer |  |  | For Information Only
ALTALINK | 285s T2 (285s East Camrose),729L (285s East Camrose - 542s Ervick),285s East Camrose 138kV Partial Bus,285s 96 (285s East Camrose) | 2018-10-23 08:30 | 2018-10-25 08:30 | N | N | replace 138 kV bus protections,replace 138k V bus protections | Switch, Line, Transformer, Bus |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-10-23 23:00 | 2018-11-07 07:00 | N | N | expedite work within 1.80/1.81 pothead yard | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 959s 905 (959s Lanfine) | 2018-10-24 07:00 | 2018-10-25 17:00 | N | Y | CT radio changes and relay changes | Circuit Breaker |  | CT Ratio Changes and Associated Relay Changes, Associated with 905CT and 50BF/905 Relay | 240 kV, Contingency Requires Mitigation
ALTALINK | 835L (384s Keystone - 835L tap),384s 835X (384s Keystone) | 2018-10-24 08:00 | 2018-10-24 12:30 | N | N | perform standard relay maintenance | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale R72C1 (Rossdale) | 2018-10-24 08:00 | 2018-11-16 16:00 | N | N | forced out of service | Circuit Breaker |  |  | For Information Only
ENMAX | 2.2TR (ENMAX 2) | 2018-10-24 10:00 | 2018-10-24 16:00 | N | N | oil sampling, tap changer, maintenance | Transformer |  |  | For Information Only
ENMAX | 20.3TR (ENMAX 20) | 2018-10-25 08:00 | 2018-10-25 16:00 | N | N | gas relay testing | Transformer |  | Gas relay testing, check reversing sw. Oil sampling 20s | For Information Only
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2018-10-25 08:00 | 2018-10-25 17:00 | N | N | urgent repair due to several critical hot spots | Transformer
BLACKSPRING | 485s C2 (485s Blackspring),485s DVAR1 (485s Blacksprings) | 2018-10-25 08:00 | 2018-10-26 17:00 | N | Y | maintenance | Shunts |  |  | For Information Only
ALTALINK | 285s T1 (285s East Camrose),730L (285s East Camrose - 730L62),285s East Camrose 138kV Partial Bus,285s 96 (285s East Camrose) | 2018-10-25 08:30 | 2018-10-26 14:00 | N | N | replace 138 kV bus protections | Bus, Transformer, Line, Switch |  | Replace 138kV bus protections. Outage on 730L and T1 for cutovers to new module and trip testing | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 2L294 (Nelway - A.A. Lambert) | 2018-10-25 09:00 | 2018-10-25 17:00 | N | Y | switch replacement | Line |  | Fortis Annual Plan 2018 and AAL CB3-1 Switch Replacement | Pre-Condition, Limits ATC
ALTALINK | 419s T2 (419s Chestermere) | 2018-10-25 10:00 | 2018-10-29 10:00 | N | N | install bird cover-up, close open point K | Transformer |  |  | For Information Only
ATCO | 790s 704 (790s Poplar Hill) | 2018-10-25 10:00 | 2018-10-25 16:00 | N | Y | urgent breaker SF6 filling | Circuit Breaker |  | Low SF6 Alarm came in today and has been confirmed stage one. The danger is that once the SF6 pressure gets to the stage two, the breaker will be blocked from tripping. ATCO Power Has been notified through our normal Maintenance contacts. | Restricts Generation
ATCO | 767s 701T (767s Oyen),7L132 (767s Oyen - 959s Lanfine),7L760 (7L760D2 - 767s Oyen) | 2018-10-25 10:00 | 2018-10-25 14:00 | N | N | 700PT1 oil sample require,700PT1 oil sample required | Transformer, Line |  | 767S Oyen 700PT1 PCB oil sample required Oyen Area on 6L09 System for the duration of the work | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 268s 503 (268s Whitecourt) | 2018-10-25 11:00 | 2018-10-25 14:00 | N | Y | disconnect temporary trip | Circuit Breaker |  | Disconnect temporary trip. Will be restoring 268s T1 while 268s503 is out of service. | Restricts Generation
ATCO | 813s 719 (813s Little Smoky),813S SVC (813s Little Smoky) | 2018-10-25 12:00 | 2018-10-25 16:00 | N | N | urgent repair for PLC | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt),268s 797 (268s Whitecourt) | 2018-10-25 16:30 | 2018-11-01 16:30 | N | N | remove temporary dead end outside 268s | Line, Circuit Breaker |  | Disconnect 472s & MR1 to 797L at 268s. Remove temporary dead end outside 268s. | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2018-10-26 07:00 | 2018-10-30 13:00 | N | N | washing insulators on structures #33, 60, 63, 66 - 68 | Line |  |  | Pre-Condition
BCH | Natal T3 (BCH Natal) | 2018-10-26 09:00 | 2018-11-05 13:00 | N | Y | 12CX3 OOS leak repair and 12 kv pin and cap replacement | Transformer | BC Outage Peak RC COS: 1-00604473 |  | Pre-Condition
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2018-10-26 12:00 | 2018-10-26 17:00 | N | Y | close open point 'Y' (725L Str103) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2018-10-26 16:00 | 2018-10-28 16:00 | N | N | remove mobile & close open point 'E" | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2018-10-27 08:00 | 2018-10-27 18:00 | N | Y | HV breaker maintenance | Line |  |  | Pre-Condition, Overload
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2018-10-28 07:00 | 2018-10-28 15:00 | N | N | South LRT project | Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 34.1TR (ENMAX 34),34.2TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2018-10-28 09:00 | 2018-10-28 18:00 | N | N | Fall substation washing SW63 | Transformer, Line |  |  | Pre-Condition, Creates Radial Feeds
ALTALINK | 365s T1 (365s Canadian Oxyas Totin Creek),846L (127s Bruderheim - 365s Canadian Oxy Astotin Creek),365s 846N (365s Canadianoxy Astotin Creek) | 2018-10-29 06:00 | 2018-10-29 19:00 | N | N | customer work | Line, Transformer, Circuit Breaker |  | Customer work (Tan Delta Testing of 13.8 kV cable NGR) | Creates Radial Feeds, For Information Only
ALTALINK | 17s 13 (17s Benalto) | 2018-10-29 06:30 | 2018-11-02 15:00 | N | Y | C60 replacement and commissioning | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare),815s 702 (815s Goodfare) | 2018-10-29 07:00 | 2018-10-29 17:00 | N | Y | protection upgrade | Circuit Breaker, Line |  | Protection upgrade for DG Advantage Oil & Gas Project GOI ON 815S BKR 702 | Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L51 (927s Buchanan Creek - 788s Hotchkiss) | 2018-10-29 07:00 | 2018-11-01 18:00 | N | N | line maintenance | Line |  | Line Maint. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK13 (987s Clover Bar - Kennedale),Kennedale T1 (Kennedale) | 2018-10-29 07:00 | 2018-11-03 17:00 | N | N | CVT replacement | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
Saskpower | Sask Power A1P | 2018-10-29 07:00 | 2018-12-13 19:00 | N | Y | maintenance | Line | Dec-02-Informed by Greg that Sask Power informed and provided the updated import and export limits. |  | Limits ATC
EPCOR | Meadowlark T2 (Meadowlark) | 2018-10-29 07:00 | 2018-11-03 17:00 | N | N | disconnect replacement | Transformer |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 35.1TR (ENMAX 35) | 2018-10-29 08:00 | 2018-10-29 12:00 | N | N | oil sampling and oie filtration maintenance on LTC | Transformer |  |  | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2018-10-29 08:00 | 2018-11-02 17:00 | N | N | change fiber arms and insulators | Line |  | Change Fiber Arms and Insulators | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.1TR (ENMAX 7) | 2018-10-29 08:00 | 2018-12-28 18:00 | N | N | transformer upgrade phase1: remove old 7.1TR, build new pad & oil containment, install new 7.1TR | Transformer |  | 7.1TR will be backfeed December 21st. However, it will be put into service December 28th. On Nov 29, ENMAX requested for 7.1TR return date to be moved to December 28th as the crews are running into construction difficulties. | For Information Only
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2018-10-29 08:00 | 2018-10-29 16:00 | N | N | HVB heater retrofit - 47B138-771 | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 207s T2 (207S Pinedale),207s 552 (207s Pinedale) | 2018-10-29 08:00 | 2018-11-01 16:00 | N | N | ISD: Nov 01, 2018 & 138kV bus tie breaker energization Oct 29, 2018 | Circuit Breaker, Transformer
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2018-10-29 08:30 | 2018-10-30 19:00 | N | Y | BCH urgent structure repairs | Line |  |  | Pre-Condition, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s T3 (37s North Calder) | 2018-10-29 09:00 | 2018-10-30 17:30 | N | N | 25 kV insulator replacement | Transformer
ALTALINK | 418s Ardenville RTU/SCADA | 2018-10-29 09:00 | 2018-10-29 15:00 | N | N | software upgrade | Terminal Equipment |  |  | Affects Visibility
ATCO | 959s 906 (959s Lanfine) | 2018-10-29 10:00 | 2018-10-31 14:00 | N | Y | CT ratio changes and associated relay changes | Circuit Breaker |  | CT Ratio Changes and Associated Relay Changes, Associated with 906CT and 50BF/906 Relay | 240 kV, For Information Only
ALTALINK | 370s T4 (370s North Lethbridge),370s 2552 (370s North Lethbridge) | 2018-10-29 10:30 | 2018-11-02 18:00 | N | N | urgent repair of 370s44 | Circuit Breaker, Transformer |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | ENMAX 35.2TR (ENMAX 35) | 2018-10-29 12:01 | 2018-10-29 16:00 | N | N | oil sampling and oie filtration maintenance on LTC | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 890L (58s Edson - 207s Pinedale),207s T2 (207S Pinedale),207s Pinedale 138kV Bus 2 | 2018-10-29 14:30 | 2018-10-30 08:00 | N | N | energize 890L & new PT via 58s | Transformer, Bus, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 869s 701T (869s Seal Lake) | 2018-10-30 07:00 | 2018-11-28 17:00 | N | N | 25 kV breaker replacement | Transformer |  | 869S 701T OOS FOR BREAKER REPLACEMENT -------- Load Transfer -------- 869S 5L597 Peak Load = 2.841 MVA 869S 5L500 Peak Load = 4.535 MVA 869S 5L597 Relay Settings: SEL RELAY 2.841 MVA 869S 5L500 Relay Settings: SEL RELAY 17.3 MVA -------- Load Transfer -------- | For Information Only
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2018-10-30 07:00 | 2018-11-02 18:00 | N | Y | component replacements between structures #144 - 391 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 15s T1 (15s Fort Macleod) | 2018-10-30 07:00 | 2018-11-15 17:00 | N | N | 25 kV reconfigurations | Transformer |  | Salvage 15s25, install new MOD switch for VR1, Connect 25kV Tie between 25kV Bus 1 and Bus 2, Modifications to existing protections, connect existing AC station load to new Transfer Switch, Salvage existing 15s428E Breaker and existing U/G Cable, Connect new AMI Feeder cable, Reconfigure 14L Overhead Feeder to underground, Reconfigure 41L Overhead Feeder to underground, Close Open Point 'H', "J" and "K" | For Information Only
ATCO | 7L69 (815s Goodfare - 731s Elmworth),815s 704 (815s Goodfare) | 2018-10-30 07:00 | 2018-10-30 17:00 | N | Y | upgrade protections | Circuit Breaker, Line |  | Protection upgrade for DG Advantage Oil & Gas Project GOI ON 815S BKR 704 | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely),15s Fort Macleod 138kV Bus1,463L (15s Fort Macleod - 463L46) | 2018-10-30 07:00 | 2018-11-09 17:00 | N | Y | 138kV reconfiguration | Bus, Line | 138kV Bus 1 Modifications: Salvage 138kV Mobile Sub Connection , Install piles and relocate 138kV Bus PT, Construct concrete pad for 138kV Tie Breaker, Relocate and Commission Tie Breaker (15s452), Relocate 138KV Switches (15s28, 15s29 --> 15s10, 15s11), String Line in between 138kV Bus 1 and Bus , Modification to existing protections |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.4TR (ENMAX 39) | 2018-10-30 08:00 | 2018-10-30 18:00 | N | N | check abnormal temperature gauge function | Transformer |  | I&R Abnormal Temperature Gauge Function. Check reversing SW. Oil sampling MT, TC | For Information Only
Saskpower | Sask Power PR 230KV Bus | 2018-10-30 08:00 | 2018-10-30 15:00 | N | Y | maintenance | Line |  |  | Limits ATC
ALTALINK | 257s T1 (257s Hull) | 2018-10-30 08:30 | 2018-11-01 16:00 | N | N | replace X1 bushing and fix PRD. | Transformer |  |  | For Information Only
ALTALINK | 55s T1 (55s Olds) | 2018-10-30 08:30 | 2018-10-30 12:30 | N | N | change CT ratios and perform CT testing | Transformer |  | Techs to change CT ratios and perform CT testing on 55sT1 as per Fortis request. | For Information Only
ALTALINK | 528s Blue Trail Wind Farm RTU/SCADA | 2018-10-30 09:00 | 2018-10-30 15:00 | N | N | software upgrade | Terminal Equipment |  |  | Affects Visibility
BCH | 1L274 (Britt Creek - 1D4L274) | 2018-10-30 09:00 | 2018-11-08 17:00 | Y | Y | rating restoration project & replace end-of-life structures | Line |  |  | Pre-Condition, Limits ATC, Firm Load Loss, Creates Radial Feeds
ATCO | 815S 703 (815s Goodfare) | 2018-10-30 13:00 | 2018-10-30 16:00 | N | N | verify DTT sent to 886s Updike | Circuit Breaker |  | Operate Breaker 703 to verify DTT sent to Updike / AOG, Bypass switch 700D2 will be closed | Pre-Condition
ALTALINK | 55s T2 (55s Olds) | 2018-10-30 13:00 | 2018-10-30 16:30 | N | N | change CT ratios and perform CT testing | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 781L (172s Sherritt - 71s Lamoureux),71s 152 (71s Lamoureux),71s 252 (71s Lamoureux) | 2018-10-30 13:00 | 2018-10-30 19:00 | N | N | washing insulators on structures #2 & 4 | Circuit Breaker, Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 9L01 (888s Dover - 848s Ruth Lake) | 2018-10-31 07:00 | 2018-11-07 17:30 | N | Y | cut in for in and out addition of 951s Thickwood Hills substation. remove bypass at substation | Line |  | 9L01 Cut in for in and out addition of 951S Thickwood Hills substation. Remove bypass at substation. | 240 kV, For Information Only
ALTALINK | 700L (422s Westwood - 746L tap),700L (746s Sherwood Park - 700L TAP) | 2018-10-31 07:00 | 2018-11-01 18:00 | N | N | washing insulators on structures #28, 29, 60 - 65, 80 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 37s T5 (37s North Calder) | 2018-10-31 07:30 | 2018-11-01 15:00 | N | N | 25 kV insulator replacement | Transformer
ENMAX | 162.2TR (ENMAX 162 Beddington),162s Beddington 240 kV South Bus | 2018-10-31 08:00 | 2018-11-01 16:00 | N | Y | install replacement parts | Bus, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L130 (710s Vermilion - 705s Kitscoty) | 2018-10-31 08:00 | 2018-11-01 17:00 | N | N | clearance mitigation | Line |  | Clearance Mitigation | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.1TR (ENMAX 39) | 2018-10-31 08:00 | 2018-10-31 16:00 | N | N | oil sampling, maintenance, bushing & check reversing switch | Transformer
VISIONREQ | 354s Summerview RTU/SCADA | 2018-10-31 09:00 | 2018-10-31 15:00 | N | N | software upgrade | Terminal Equipment |  |  | Affects Visibility
EPCOR | 805s J2404 (805s Jasper) | 2018-11-01 07:00 | 2018-11-01 17:00 | N | Y | nait tour | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 320p 3152 (320p Keephills) | 2018-11-01 09:30 | 2018-11-01 17:30 | N | Y | gas top up (SF6) | Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 243s Soderglen Wind Farm RTU/SCADA | 2018-11-01 09:30 | 2018-11-01 16:00 | N | N | network upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 77s 51 (77s Sagitawah) | 2018-11-01 10:30 | 2018-11-01 15:30 | N | Y | leaking HPL (north phase) | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 528s Blue Trail Wind Farm RTU/SCADA | 2018-11-01 12:00 | 2018-11-01 13:00 | N | N | switch replacement | Terminal Equipment |  |  | Affects Visibility
ENMAX | 21.2TR (ENMAX 21) | 2018-11-02 08:00 | 2018-11-02 15:00 | N | N | oil sample MT, TC | Transformer |  |  | For Information Only
ATCO | 813S SVC (813s Little Smoky) | 2018-11-02 10:00 | 2018-11-02 16:00 | N | N | urgent repair for cooling pump #2 | Shunts |  |  | For Information Only
ALTALINK | 17s 12 (17s Benalto) | 2018-11-02 15:00 | 2018-11-02 16:00 | N | Y | trip test for C60 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2018-11-03 07:00 | 2019-03-29 17:00 | N | N | termination rebuild | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s C1 (17s Benalto),17s 16 (17s Benalto) | 2018-11-03 07:00 | 2018-11-03 09:00 | N | Y | trip test for C60 replacement | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 491L (252s Jarrow - 7L50 tap) | 2018-11-03 07:00 | 2018-11-04 18:00 | N | Y | component replacement work between structures #1 - 4 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 4 (17s Benalto) | 2018-11-03 09:00 | 2018-11-03 11:00 | N | Y | trip rest for C60 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 9 (17s Benalto) | 2018-11-03 11:00 | 2018-11-03 13:00 | N | Y | trip test for C60 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-11-03 13:00 | 2018-11-04 13:00 | N | N | create open point 'A' using live-line techniques for 847L outage Nov 4-17 (ref# 261603) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 3 (17s Benalto) | 2018-11-03 13:00 | 2018-11-03 15:00 | N | Y | trip test for C60 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 1652 (17s Benalto) | 2018-11-03 15:00 | 2018-11-03 16:30 | N | Y | trip test for C60 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s T2 (17s Benalto),17s 85 (17s Benalto) | 2018-11-03 16:30 | 2018-11-03 18:00 | N | Y | trip test for C60 replacement | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 24.82L (ENMAX 65 - ENMAX 24) | 2018-11-04 08:00 | 2018-11-04 18:00 | N | N | SF6 gas sample 24B138-24.82 | Line |  |  | For Information Only
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-11-04 13:00 | 2018-11-17 13:00 | N | N | install two new air breaks for new 847AL tap to 1029s Vista | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 190L (17s Benalto - 320p Keephills) | 2018-11-04 20:19 | 2018-11-08 12:00 | N | Y | forced outage (structure damage) | Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 17s 12 (17s Benalto) | 2018-11-05 06:30 | 2018-11-09 14:30 | N | Y | C60 replacement and commissioning | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 408L (252s Jarrow - 51s Wainwright) | 2018-11-05 07:00 | 2018-11-21 18:00 | N | N | structure replacement | Line | Structure replacement work between Structures #1 - 106 |  | Creates Radial Feeds
EPCOR | 72MG16 (Meadowlark - Garneau) | 2018-11-05 07:00 | 2018-11-11 17:00 | N | N | disconnect replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale R721 (Rossdale) | 2018-11-05 07:00 | 2018-11-30 17:00 | N | N | breaker replacement | Circuit Breaker |  |  | Pre-Condition
EPCOR | Meadowlark T3 (Meadowlark) | 2018-11-05 07:30 | 2018-11-09 17:00 | N | N | metering cutover | Transformer |  |  | For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2018-11-05 08:00 | 2018-11-09 17:00 | N | N | change fiber arms and insulators | Line |  | Change Fiber Arms and Insulators | Pre-Condition
ENMAX | 11.3TR (ENMAX 11) | 2018-11-05 08:00 | 2018-11-05 16:00 | N | N | relay maintenance | Transformer |  |  | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2018-11-05 08:00 | 2018-11-14 16:00 | N | N | MV bushing replacement | Transformer |  |  | For Information Only
ENMAX | 65.1 TR (ENMAX 65) | 2018-11-05 08:00 | 2018-11-06 12:00 | N | Y | Oil sampling MT, TC. Check reversing switch | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 10.1TR (ENMAX 10) | 2018-11-05 08:00 | 2018-11-16 16:00 | N | N | doble test transformer and maintenance | Transformer |  | doble test transformer. Transformer maintenance. Secondary cable tests. Investigate smell in 10 sub building during 10.1TR initial outage. Special switching instructions. Oil sampling MT, TC | For Information Only
ATCO | 7L130 (710s Vermilion - 705s Kitscoty) | 2018-11-05 08:00 | 2018-11-09 17:00 | N | N | clearance mitigation | Line |  | Clearance Mitigation | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310P T36 (310p Sundance),310p T30 (310p Sundance),310p Sundance 240kV Bus C | 2018-11-05 09:00 | 2018-11-15 16:00 | N | Y | migrate and commission protection and control to the new RTU and LAN | Transformer, Bus |  | Migrate and commission all T36, T30 & 310P69 protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. Replace 310P3089 & 310P3389 air break control modules, commission alarms control and status to new RTU. Replace T30 & T36 metering transducers with SEL-735 meters for SCADA metering of T30 & T36 | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2018-11-05 09:30 | 2018-11-09 14:30 | N | Y | repair oil leak on CT | Shunts |  | Outage and GOI required to repair oil leak on CT. Outage to 510s ACF22. Does not impact link dispatch. | 500 kV
ALTALINK | 747L (99s North St. Albert - 747DL4),99s 747X (99s North St Albert) | 2018-11-05 09:30 | 2018-11-09 17:30 | N | N | replace protections | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s T1 (83s Taber) | 2018-11-05 10:00 | 2018-11-08 18:00 | N | Y | upgrade metering and 83s43 bus PT | Transformer |  | Full Metering upgrade and 83s43 Bus PT Update to 3 Phase and add supervisory controls to 83s53 and 83s7 Switches | Restricts Generation
EPCOR | 557s 2403 (557s Castle Downs),557s 2401 (557s Castle Downs) | 2018-11-05 10:00 | 2018-11-08 17:00 | N | Y | update teleprotection | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2018-11-05 10:00 | 2018-11-08 16:00 | N | Y | upgrade TPR protection | Line |  |  | 240 kV
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2018-11-05 11:00 | 2018-11-05 17:00 | N | Y | fix heaters | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 914L (86s Bigstone - 87s Gaetz) | 2018-11-05 12:00 | 2018-11-06 18:00 | N | Y | component replacements between Structures #144 - 391 | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L54 (794s Valleyview - 813s Little Smoky) | 2018-11-05 12:00 | 2018-11-08 12:00 | N | N | pole repairs | Line |  | Pole Repairs from 2017 Inspection & Crossarm change | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 945s T2 (945s Sunshine Village) | 2018-11-05 13:00 | 2018-11-06 13:00 | N | N | fix leaks from conservator piping | Transformer |  |  | For Information Only
BCH | Natal T4 (BCH Natal) | 2018-11-05 13:01 | 2018-11-13 17:00 | N | Y | leak repair and 12 kV pin and cap replacement | Transformer | BC Outage Peak RC COS: 1-00605696 |  | Pre-Condition
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2018-11-06 07:00 | 2018-11-06 17:00 | N | N | mine shut-down | Line |  |  | For Information Only
EPCOR | 803s T2 (803s Lambton),803s L2402 (803s Lambton),803s L2405 (803s Lambton) | 2018-11-06 07:00 | 2018-11-07 17:00 | N | N | emergency repair/settings update | Transformer, Circuit Breaker |  | emergency repair/settings update to New Bus Diff and Tx Protection | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power PR 230KV Bus | 2018-11-06 07:00 | 2018-11-07 10:00 | N | Y | reconnect switchyard | Line |  |  | Limits ATC
ALTALINK | 994L (103s Goose Lake - 312s Fidler) | 2018-11-06 08:00 | 2018-11-06 17:00 | N | Y | breaker and switch maintenance | Line |  | 994L outage for 103s552 and 652 low gas top up and investigate leak. 103s994 adjust switch. | 240 kV, Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 74s C4 (74s Janet),74s 103 (74s Janet) | 2018-11-06 08:00 | 2018-11-07 17:00 | N | Y | fix heaters and make some wiring changes | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 267s C3 (267s Killarney Lake) | 2018-11-06 08:00 | 2019-01-30 16:00 | N | N | forced out of service | Shunts |  |  | For Information Only
ALTALINK | 368s T1 (368s Burdett) | 2018-11-06 08:30 | 2018-11-06 16:30 | N | N | upgrade temperature monitor equipment | Transformer |  |  | For Information Only
ALTALINK | 515s T1 (515s FedpipeJudy Creek),526L (515s Fed Pipe Judy Creek - 526L420) | 2018-11-06 09:00 | 2018-11-06 21:00 | N | N | installing 471s mobile substation for replacement of 515s T1 | Transformer, Line |  | Installing 471s mobile substation for replacement of 515s T1; Crews will also be creating Open Points 'C' & 'D' | For Information Only
ALTALINK | 254s T1 (254s Coaldale) | 2018-11-06 10:00 | 2018-11-28 17:00 | N | N | replace feeder cables - 407L, 411L, 443L | Transformer |  |  | For Information Only
ALTALINK | 435s T1 (435s Bassano),435s 853A (435s Bassano) | 2018-11-06 10:00 | 2018-11-06 17:00 | N | N | fix 2 tank heaters | Circuit Breaker, Transformer |  |  | For Information Only
ENMAX | 65.2 TR (ENMAX 65) | 2018-11-06 12:00 | 2018-11-07 16:00 | N | Y | oil sampling MT, TC, check reversing switch | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 515s T1 (515s FedpipeJudy Creek) | 2018-11-06 21:00 | 2018-11-13 17:30 | N | N | removing and replacing 515s T1 | Transformer |  |  | For Information Only
ALTALINK | 702L (377s Hardisty - 137s Sedgewick),377s 702W (377s Hardisty) | 2018-11-07 08:00 | 2018-11-07 17:30 | N | N | tank heater replacement | Circuit Breaker, Line |  | 377s702w Tank heater is starting to fail. One phase was reading 2.3A while the other two phases were reading 3.3A. Heater should be replaced. Outage is required. | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 535s 6352 (535s Joffre) | 2018-11-07 09:00 | 2018-11-07 16:00 | N | N | replace blown tank heater. | Circuit Breaker
ALTALINK | 324s 1652 (324s Cassils) | 2018-11-07 09:00 | 2018-11-07 15:00 | N | Y | Pole A1 heater burned out. | Circuit Breaker |  |  | 240 kV
ALTALINK | 356s 552 (356s Milo) | 2018-11-07 10:30 | 2018-11-07 16:00 | N | Y | fix heaters | Circuit Breaker |  |  | 240 kV
VISIONREQ | 354s Summerview RTU/SCADA | 2018-11-07 15:00 | 2018-11-07 15:30 | N | N | firewall upgrade | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 431s C1 (431s Hussar) | 2018-11-08 08:00 | 2018-11-29 16:00 | N | N | forced out of service | Shunts |  |  | For Information Only
ALTALINK | 678s T3 (678s Okotoks) | 2018-11-08 09:00 | 2018-11-08 14:00 | N | N | discharge springs and change out heater | Transformer |  | One of the 167 watt heaters is burnt out in the breaker mech. Outage required to discharge springs and change out heater. | For Information Only
ALTALINK | 551JL (551JL Tap - 551JL1) | 2018-11-08 12:00 | 2018-11-12 18:00 | N | N | 551L string bypass over tap point | Line |  |  | For Information Only
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2018-11-08 13:15 | 2018-11-08 17:45 | N | N | high load move | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L34 (886s Updike - 815s Goodfare),886S 701T | 2018-11-09 07:00 | 2018-11-16 17:00 | N | N | protection upgrade | Terminal Equipment, Line |  | Protection upgrade for Advantage Oil and Gas DG addition project, Mobile sub will carry 886S load NOVEMBER 8/2018 - ENERGIZE AND SOAK MOBILE SUB NOVEMBER 13/2018 - REMOVE 886S - 701T FROM SERVICE , MOBILE SUB TO CARRY LOAD | Creates Radial Feeds, For Information Only
ALTALINK | 461L (212s N.E. Lacombe - 198s Blackfalds) | 2018-11-09 08:00 | 2018-11-23 16:00 | N | N | ISD; Nov 16, 2018 | Line
ATCO | 9L30 (888s Dover - 951s Thickwood),9L01 (848s Dover - 951s Thickwood) | 2018-11-09 08:00 | 2018-11-16 16:00 | N | N | ISD: Nov 09, 2018 | Line
ALTALINK | 958S West Lacombe,80AL (212s N.E.Lacombe - 958s West Lacombe),80L (198s Blackfalds - 958s West Lacombe) | 2018-11-09 08:00 | 2018-11-23 16:00 | N | N | Decommissioned Nov 16, 2018 | Line, Station
ALTALINK | 755L (535s Joffre - 247s Piper Creek),247s 755 (247s Piper Creek),247s Piper Creek 138kV Bus,427L (63s Red Deer - 247s Piper Creek),247s 427 (247s Piper Creek) | 2018-11-09 09:00 | 2018-11-23 15:30 | N | Y | 17-89-1 & 17-89-2 138kV Motor Operated Disconnect replacement | Line, Bus, Circuit Breaker |  | 17-89-1 & 17-89-2 138kV Motor Operated Disconnect replacement | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 17s 13 (17s Benalto) | 2018-11-09 14:30 | 2018-11-09 16:30 | N | Y | C60 replacement and commissioning | Circuit Breaker |  |  | Pre-Condition, Overload, Restricts Generation
ALTALINK | 15s 452 (15s Fort Macleod) | 2018-11-09 17:00 | 2018-11-16 08:00 | N | N | new breaker work | Circuit Breaker |  | 15s 138kV bus 1 (180/463L) & bus 2 (725L) split as Open Point 'E' between busses cannot be closed until CoL 824L is energized. End date is not confirmed | For Information Only
ENMAX | 2.80L (ENMAX 2 - ENMAX 23) | 2018-11-10 08:00 | 2018-11-10 16:00 | N | N | top up SF6 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 370s T1 (370s North Lethbridge),207L (111s Coalbanks - 370s North Lethbridge),770L (254s Coaldale - 370s North Lethbridge),370s North Lethbridge 138kV Bus 1,172L (370s North Lethbridge - 181s Chinook) | 2018-11-10 08:00 | 2018-11-10 12:00 | N | Y | urgent repair / jumpering of 370s1 airbreak | Bus, Transformer, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-11-10 08:00 | 2018-11-25 18:00 | N | N | energize/de-energize bypass line between str377 and str407 to allow for rebuild of 551L | Line |  | Energize/de-energize bypass line between Str377 and Str407 to allow for rebuild of 551L (Sections 16B). Bypass to be energized/de-energized using live line techniques; no interruption to 551L loads | For Information Only
ENMAX | 34.1TR (ENMAX 34),34.3TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2018-11-10 09:00 | 2018-11-10 18:00 | N | N | fall substation washing | Line, Transformer |  | Fall Substation Washing. Wash SW63 | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.3TR (ENMAX 32) | 2018-11-11 08:00 | 2018-11-11 18:00 | N | N | top up LTC oil level | Transformer |  | Top up LTC oil level. Investigate LTC oil level guage. | For Information Only
ENMAX | 22.1TR (ENMAX 22) | 2018-11-11 08:00 | 2018-11-12 16:00 | N | N | repair winding temperature gauge, main tank valve, and oil leak, and check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 15s 452 (15s Fort Macleod) | 2018-11-11 08:00 | 2018-11-16 16:00 | N | N | ISD: Nov 15, 2018. | Circuit Breaker
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2018-11-12 07:00 | 2018-11-19 16:00 | N | N | maintenance on 202L structures | Line |  | Maintenance on 202L Structures #378, 450, 454, 510, 514, 568 608, 635, 762 & 767 | Pre-Condition
ALTALINK | 958S West Lacombe,80L (198s Blackfalds - 958s West Lacombe),80AL (958s West Lacombe - 212s N.E Lacombe) | 2018-11-12 07:30 | 2018-11-15 15:00 | N | N | 958s station salvage | Line, Station |  | 958s Station will be salvaged and line settings changed @ 212s & 198s; 80L & 80AL will be re-designated 461L | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37) | 2018-11-12 08:00 | 2018-11-12 18:00 | N | N | SW 83 maintenance | Line, Transformer |  | Corrective. SW 83 not opening past 90 degrees. | Firm Load Loss, Creates Radial Feeds
BCH | 5L96 (Selkirk - Vaseux Lake) | 2018-11-12 09:00 | 2018-11-16 17:00 | N | Y | to repair the failed operating mechanism on 5D42 | Line | Peak RC outage ID: 1-00605698 Peak RC path ID: 1-00610378 (E>W, export), 1-00610386 (W>E, import) |  | Limits ATC, 500 kV
ALTALINK | 17s 11 (17s Benalto) | 2018-11-12 09:00 | 2018-11-12 11:00 | N | Y | trip test for C60 replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, Lethbridge | 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2018-11-12 13:00 | 2018-12-10 14:00 | N | Y | install self-supporting structures | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s T3 (83s Taber) | 2018-11-13 07:00 | 2018-11-16 18:00 | N | N | metering upgrade, PT update and add supervisory controls | Transformer | Full Metering upgrade and 83s56 Bus PT Update to 3 Phase and add supervisory controls to 83s52 switch |  | For Information Only
ATCO, ALTALINK | 7L65 (709s Vegreville - 710s Vermilion),7L77 (395s North Holden - 709s Vegreville) | 2018-11-13 07:00 | 2018-11-17 17:30 | N | Y | transfer line to new part of 706S Vegreville substation | Line |  | Transfer line to new part of 706S Vegreville substation 7L65 and 77 Lines on a common H frame structure. Only 7L77 being moved at this time. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
Medicine Hat, CMH | MH69s6 MH69_614 (MH69s6 Riverview),MH69_8L_1 (MH69s1 Power Plant - MH69s6 Riverview) | 2018-11-13 07:00 | 2018-11-13 12:27 | N | N | repair substations fence and access gate | Circuit Breaker, Line |  |  | For Information Only
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2018-11-13 07:00 | 2018-11-15 17:00 | N | N | change out poles | Line |  | GOI to change out poles | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 876L (179s Gleichen - 253s Blackie) | 2018-11-13 07:15 | 2018-11-30 12:45 | N | N | component replacement | Line |  | Component replacement (Spacers/Dampers/OH Reties/Crossarms) str180-str355 | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington) | 2018-11-13 07:15 | 2018-11-28 15:45 | N | Y | component replacement and installing interphase spacers | Line | component replacement, and installing interphase spacers on 918L circuit between str 763-796 |  | 240 kV, Pre-Condition
ATCO | 7L03 (749s Flyingshot Lake - 7L03D2) | 2018-11-13 08:00 | 2018-11-15 16:00 | N | Y | line maintenance | Line |  | 7L03 Line Maint | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 536s T1 (536s Brookfield) | 2018-11-13 08:00 | 2018-11-13 16:00 | N | N | replace high voltage surge arresters | Transformer |  |  | For Information Only
ENMAX | 5.9TR (ENMAX 5) | 2018-11-13 08:00 | 2018-11-19 16:00 | N | N | HICO transformer tap changer re-plumb | Transformer |  | HICO transformer tap changer re-plumb. 5.9TR MD Whip not Reset on East Phase | For Information Only
ENMAX | 26.2TR (ENMAX 26) | 2018-11-13 08:00 | 2018-11-14 16:00 | N | N | replace retaining nuts | Transformer |  | Replace Retaining Nuts on the HV Bushing Draw Leads [AVANTIS]. Parts in sub building. Check reversing switch | For Information Only
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2018-11-13 09:15 | 2018-11-28 08:00 | N | Y | maintenance components | Line | Maintenance Components (Str 117-404) |  | 240 kV, Pre-Condition
ENMAX | 1.80L | 2018-11-13 23:00 | 2018-11-16 07:00 | N | N | Expedite work within 1.80/1.81 Pothead yard. | Terminal Equipment |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2018-11-14 07:00 | 2018-11-17 18:00 | N | Y | emergency repair, damper replacements (str 179~211) | Line |  | Emergency Repair; damper replacements (Str 179~211) | 240 kV, Pre-Condition, Overload
ATCO | 9L07 (888s Dover - 2011s Dawes) | 2018-11-14 07:00 | 2018-11-22 17:30 | N | Y | cut in 951S Thickwood Hills substation | Line |  | Cut in 951S Thickwood Hills substation. | 240 kV, Pre-Condition
ATCO | 959S SVC (959s Lanfine) | 2018-11-14 07:30 | 2018-11-14 16:00 | N | Y | new software installation | Shunts |  | Emergency Lanfine SVC Shut Down required to correct tripping issues that have been occurring. Nov 14 for install of new software Nov 15 will be for system testing as per GE Re-commission Test Plan | 240 kV, Pre-Condition
ALTALINK | 86s T1 (86s Bigstone) | 2018-11-14 07:30 | 2018-11-21 15:30 | N | Y | replace bushings | Transformer |  | replace X2 and x3 bushings | 240 kV, Over/Under Voltage
ENMAX | 1.8TR (ENMAX 1) | 2018-11-14 08:00 | 2018-11-21 16:00 | N | N | NGR Installation | Transformer |  |  | For Information Only
ALTALINK | 615L (602s Cold Creek - 104s Watson Creek) | 2018-11-14 08:00 | 2018-11-15 17:00 | N | N | clearance remediation on structure 142 and pile installation | Line |  | 615L Transmission Line Outage for clearance remediation on Structure 142. Helical screw pile installation under 615L on Watson Creek 104S expanded site. | For Information Only
ALTALINK, ATCO | 6L126 (515L tap - 743s Sarah Lake),526L (515s Fed Pipe Judy Creek - 526L418) | 2018-11-14 09:00 | 2018-11-14 19:00 | N | Y | installing temporary bypass and creating open points 'A' & 'B' | Line |  | Installing temporary bypass and creating Open Points 'A' & 'B' | Pre-Condition, Creates Radial Feeds
ALTALINK | 515s T1 (515s FedpipeJudy Creek) | 2018-11-14 09:00 | 2018-11-14 19:00 | N | N | removing 471s mobile substation from 515s and closing open points 'C' & 'D' | Transformer |  | Removing 471s mobile substation from 515s; Crews will also be closing Open Points 'C' & 'D' | For Information Only
ALTALINK | 132s 55 (132s Ware Junction) | 2018-11-14 10:30 | 2018-11-14 13:30 | N | Y | breaker heater replacement | Circuit Breaker |  | The 70 watt anticon heater on the west phase of 132s28 is burnt out. A new 70 watt HPL heater is required to replace the burnt out one. | 240 kV, Contingency Requires Mitigation
ALTALINK | 132s 28 (132s Ware Junction) | 2018-11-14 13:30 | 2018-11-14 16:30 | N | Y | breaker heater replacement | Circuit Breaker |  | The 70 watt anticon heater on the west phase of 132s28 is burnt out. A new 70 watt HPL heater is required to replace the burnt out one. | 240 kV, Pre-Condition
ATCO | 6L126 (515L tap - 743s Sarah Lake) | 2018-11-14 19:00 | 2018-12-04 18:00 | N | Y | replacing 8703S1 with a new switch | Line |  | Replacing 8703S1 with a new switch; this switch will be changing its designation to 126L1 and the small portion of line will be renamed to 126L | Pre-Condition, Creates Radial Feeds
ALTALINK | 510s 2852 (510s Sunnybrook) | 2018-11-15 06:00 | 2018-12-10 08:00 | N | Y | installing new 510s2952 and closing open points 'A', 'B', 'D' & 'E' | Circuit Breaker |  | installing new 510s2952, CT's, 510s46, 510s48 and protection: closing open points 'A', 'B', 'D' & 'E' | 500 kV
Saskpower | Sask Power 904,Sask Power 901 | 2018-11-15 08:00 | 2018-11-15 14:00 | N | Y | infrared scans | Circuit Breaker |  |  | Limits ATC
ENMAX | 20.3TR | 2018-11-15 08:00 | 2018-11-28 10:00 | N | N | NGR addition | Terminal Equipment |  | 20.3TR will be returned Friday Nov 23rd, the crew is now waiting on new device 90 settings before they can energize. Consequently, the outage time for 20.1TR will be delayed. | For Information Only
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely),725L (15s Fort MacLeod - 725BL54),15s T2 (15s Fort Macleod) | 2018-11-16 07:30 | 2018-11-16 16:00 | N | Y | close open point "E" & connect bus tie to 138kV high bay | Transformer, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 958S West Lacombe,80AL (212s N.E.Lacombe - 958s West Lacombe),80L (198s Blackfalds - 958s West Lacombe) | 2018-11-16 08:00 | 2018-12-12 16:00 | N | N | temporary modeling issue | Station, Line |  |  | For Information Only
ATCO | 9L07 (2011s Dawes - 951s Thickwood),9L112 (888s Dover - 951s Thickwood) | 2018-11-16 08:00 | 2018-11-30 16:00 | N | N | ISD: Nov 23, 2018 | Line
ENMAX | 22.1TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2018-11-16 22:00 | 2018-11-19 06:00 | N | N | construction for 138kV BT at 22sub | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 22 | 2018-11-17 08:00 | 2019-02-18 16:00 | N | N | partial 138 kV bus outage for construction of new 138kV PT at 22sub | Station |  |  | For Information Only
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27) | 2018-11-17 08:00 | 2018-11-17 18:00 | N | N | outside phases are not closing completely on 16-SW62 | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-11-17 13:01 | 2018-11-21 13:00 | N | N | 847L236B Advice for AML crew to close Open Point 'A' using live-line techniques for 847L outage Nov 4-17 (ref# 261603) | Line |  |  | Creates Radial Feeds
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2018-11-18 07:00 | 2018-11-18 15:00 | N | N | DACRO industries re-design | Line |  |  | Pre-Condition, Creates Radial Feeds
ENMAX | 24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32),31.3TR (ENMAX 31) | 2018-11-18 08:00 | 2018-11-18 18:00 | N | N | switch adjustment required 31- SW 87 - does not open past 90 deg | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 709s 701Ta (709s Vegreville) | 2018-11-18 08:00 | 2019-05-30 16:00 | N | N | construction GOI for new vegreville substation | Transformer |  | Outage 1 - Construction GOI for New Vegreville substation | For Information Only
ALTALINK | 29s T2 (29s Cascade),177s West Cascade | 2018-11-18 12:00 | 2018-11-30 19:00 | N | Y | 13.8KV bus outage for breaker retrofits on 29S40, 29S54, 29S1, 29S2 | Transformer, Station
EPCOR | 72NW15 (Namao - Woodcroft) | 2018-11-19 07:00 | 2018-12-07 17:00 | N | N | Line Maintenance & Upgrades | Line |  |  | For Information Only
EPCOR | 987s T1 (987s Clover Bar) | 2018-11-19 07:00 | 2018-11-23 17:00 | N | Y | oil filtration replacement and CDS25 commissioning | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | Woodcroft T2 (Woodcroft) | 2018-11-19 07:00 | 2018-11-30 17:00 | N | N | Cutover of New Transformer Protection | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2018-11-19 08:00 | 2018-11-30 16:00 | N | N | line protection upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2018-11-19 08:00 | 2018-11-23 17:00 | N | N | GOI to change out poles | Line |  | GOI to change out poles | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32) | 2018-11-19 08:00 | 2018-12-07 16:00 | N | N | seal replacement | Transformer |  | Tap Changer Window Gasket and seal to main tank. 32.1TR LTC seal replacement [AVANTIS]. On Nov 21, ENMAX notified that the outage for 32.1TR will be extended to Friday November 30th. The crew has found an additional leak that needs to be repaired. On Nov 29th, ENMAX notified that the outage for 32.1TR will be extended to Friday December 07th. | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2018-11-19 08:00 | 2018-11-22 14:00 | N | N | move 2 poles for green line LRT project | Line |  |  | For Information Only
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2018-11-19 08:00 | 2018-11-26 17:00 | N | N | line maintenance | Line |  | Line Maintenance | Pre-Condition
ATCO | 7L90 (813s Little Smoky - 741s Fox Creek) | 2018-11-19 08:00 | 2018-11-22 17:00 | N | N | replace rotten crossarms | Line |  | Replace rotten crossarms, (Working 08:00- 17:00 each day, line could be restored evenings if required in an emergency) | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.1TR (ENMAX 6) | 2018-11-19 08:00 | 2018-11-21 16:00 | N | N | T-60 relay CPU upgrade | Transformer |  |  | For Information Only
ENMAX | ENMAX 22 | 2018-11-19 08:00 | 2019-02-02 06:00 | N | N | construction of new 138kV BT at 22sub | Station |  |  | For Information Only
BCH | 1L274 (Britt Creek - 1D4L274) | 2018-11-19 09:00 | 2018-11-29 17:00 | Y | Y | annual plan request F19 | Line |  |  | Pre-Condition, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 310p 1352 (310p Sundance),310p 1452 (310p Sundance),909L (310p Sundance - 665s Dome) | 2018-11-19 10:00 | 2018-11-22 16:00 | N | Y | AltaLink - migrate and commission CVT-L5 alarms, EPCOR - line maintenance & upgrades | Line, Circuit Breaker |  | migrate and commission all L5 - 909L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L5 alarms. | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 719L (575s Sundre - 378s Shell Caroline) | 2018-11-19 11:00 | 2018-11-23 15:00 | N | Y | upgrade line protection | Line |  | upgrade line protection (A21/L4 & B21/L4) | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 313S Raymond Reservoir,225L (67s Stirling - 225s Magrath) | 2018-11-19 13:00 | 2018-11-22 14:30 | N | Y | repair station grounding damaged by a copper theft incident | Station, Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK, ENMAX | 391s T2 (391s Balzac),162.81L (ENMAX 162 Beddington - 391S Balzac) | 2018-11-19 13:30 | 2018-11-20 16:00 | N | Y | adjust 391s26 and 391s28 and fix T2 hydran | Transformer, Line |  | Adjust 391s26 and 391s28 and fix T2 hydran. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s T1 (77s Sagitawah) | 2018-11-20 07:30 | 2018-11-20 17:30 | N | N | maintenance | Transformer |  | 77s T1 leaks CAT3 now a CAT5 | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 202L (61s Lodgepole - 202L335),61s 202N (61s Lodgepole) | 2018-11-20 08:00 | 2018-11-20 10:30 | N | N | trip testing from new 61s202X breaker fail protection | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 102s SVC (102s Langdon) | 2018-11-20 10:00 | 2018-11-20 17:30 | N | Y | urgent trouble shooting | Shunts |  | Urgent Trouble Corrective: Trouble shoot SVC to find why the pumps do not switch to station service after a swap. | 240 kV
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove),61s 836N (61s Lodgepole) | 2018-11-20 10:30 | 2018-11-20 13:00 | N | Y | trip testing from new 61s202X breaker fail protection | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 391s T1 (391s Balzac),611L (391S Balzac - 186s Dry Creek),391s 17 (391s Balzac) | 2018-11-20 16:00 | 2018-11-22 16:00 | N | N | adjust 391s18,391s19, 391s16 and remove birds nest from T1 radiator | Transformer, Line, Switch |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
EPCOR | 803s L2403 (803s Lambton) | 2018-11-21 07:00 | 2018-11-22 17:00 | N | Y | transfer DC supply | Circuit Breaker |  |  | 240 kV
ENMAX | 37.1TR (ENMAX 37) | 2018-11-21 08:00 | 2018-11-21 16:00 | N | N | 37s RTU replacement, relay settings changes | Transformer
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2018-11-21 08:00 | 2019-02-05 18:00 | N | N | replace 36.5TR | Transformer, Line |  |  | Pre-Condition
ALTALINK | 217s C1 (217s North Red Deer),217s 652 (217s North Red Deer) | 2018-11-21 08:30 | 2018-11-21 15:00 | N | N | SF6 leak investigation and gas top up | Shunts, Switch |  |  | For Information Only
ALTALINK | 62s11 (62s Brazeau) | 2018-11-21 23:00 | 2018-11-22 02:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2018-11-22 02:01 | 2018-11-22 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s T5 (62s Brazeau) | 2018-11-22 04:00 | 2018-11-22 06:00 | N | Y | place T3 into service for load readings | Transformer |  | Place T3 into service for load readings. T5 will be out of service. | Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36) | 2018-11-22 08:00 | 2018-11-22 18:00 | N | N | replace 36.5TR | Line, Transformer |  | Replace 36.5TR. Bus outage required for transformer move. | Creates Radial Feeds
ALTALINK | 704L (51s Wainwright - 478s Tuccuman) | 2018-11-23 07:00 | 2018-12-15 18:00 | N | N | structure replacement work between structures #170 - 304 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L77 (Revelstoke - Ashton Creek) | 2018-11-23 23:00 | 2018-11-26 23:00 | N | Y | black start testing - BC maintenance does not affect AB ATC | Line | Peak COS outage ID: 1-00608392 Peak Path COS ID: 1-00608445 (E>W), 1-00608447 (W>E) |  | Limits ATC, 500 kV
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-11-24 00:01 | 2018-11-24 06:00 | N | N | expedite work within 1.80/1.81 pothead yard | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7) | 2018-11-24 06:00 | 2018-11-26 06:00 | N | N | 7 sub transformer upgrade phase1, install and energize SW87 | Line, Transformer |  | 7 sub transformer upgrade Phase1. Install and energize SW87 | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-11-24 08:00 | 2018-11-27 18:00 | N | N | place 551JL tap loads on temp genset to remove bypass over tap point | Line |  | place 551JL tap loads on temp genset to remove bypass over tap point. loads to remain on genset until bypass has been removed at which point 551JL loads to be connected to 551L | For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2018-11-25 08:00 | 2018-11-25 18:00 | N | N | investigate PT connection on NGR install | Transformer |  |  | For Information Only
EPCOR | 52s T1 (52s East Industrial) | 2018-11-26 07:00 | 2018-11-28 17:00 | N | Y | cutover of new relay protection | Transformer |  |  | 240 kV, For Information Only
ATCO | 2075s ACF21 (2075s Newell),2075s 902T (2075s Newell) | 2018-11-26 07:00 | 2018-11-29 10:00 | N | Y | switching for SVC2 outage | Shunts, Transformer |  | Switching for SVC2 Outage Save Device Configuration Backups (Digsi Project, transformer ITM), Password Changes (VCS PLCs, transformer ITM, WinCC HMI computers  SVC building & MCB, TFR computer), Firmware upgrades (VCS PLCs) SVC1 will remain in service while SVC2 is out of service. This will provide no restrictions to the DC or AC system while it is out of service. Loss of SVC redundancy while SVC2 is out of service. There is no change to 13L50 DC power transfer capabilities while one SVC is out of service, however the reactive power capabilities of the SVC's will be reduced from +/-150Mvar to +/-75Mvar with only SVC1 in service. | 240 kV, For Information Only
EPCOR | 987s T2 (987s Clover Bar),987s CC721 (987s Clover Bar),987s C2405 (987s Clover Bar),987s C2406 (987s Clover Bar) | 2018-11-26 07:00 | 2018-11-30 17:00 | N | Y | bushing monitor removal | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s T3 (805s Jasper),805s J2404 (805s Jasper),805s J2405 (805s Jasper) | 2018-11-26 07:30 | 2018-11-30 17:00 | N | Y | metering cutover | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1TR (ENMAX 38) | 2018-11-26 08:00 | 2018-11-29 16:00 | N | N | upgrade T-60 relay CPU | Transformer |  |  | For Information Only
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2018-11-26 08:00 | 2018-11-30 14:00 | N | Y | changes cross-arm | Line |  | Cross-Arm Changes | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L85 (804s Wintering Hills - 803s Bullpound) | 2018-11-26 08:00 | 2018-11-29 17:00 | N | N | change arms and insulators | Line |  | Changing Arms and Insulators STUDY NOT REQUESTED YET | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 8.6TR (ENMAX 8) | 2018-11-26 08:00 | 2018-11-29 09:00 | N | N | HICO transformer tap changer re-plumb | Transformer |  | HICO Transformer Tap Changer Re-plumb. Check reversing SW. Oil sampling MT, TC | For Information Only
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake),715s 702 (715s Leming Lake) | 2018-11-26 08:00 | 2018-11-29 16:00 | N | Y | emergency 715S 7L91D2 switch replacement | Circuit Breaker, Line |  | 715S 7L91D2 Switch Replacement, 7L91 OOS for duration of work | Pre-Condition, Restricts Generation
ENMAX | 41.1C (ENMAX 41) | 2018-11-26 09:00 | 2018-11-26 16:00 | N | N | protection upgrade | Shunts |  |  | Pre-Condition
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2018-11-26 09:01 | 2018-12-03 09:59 | N | Y | upgrading firmware and installing temporary settings @ 19s & 310p in preparation for the re-configuration of 902L/1046L | Line |  | CANA will be upgrading firmware and installing temporary settings @ 19s & 310p in preparation for the re-configuration of 902L/1046L in January 2019 - Upgrade firmware and install temporary settings and re-name A21/L2 902/1046L (old 902) @ 19s B21/L2 902/1046L (old 902) @ 19s - Line protections will be set for temp. 19s  338s connection and named 902L/1046L - Upgrade firmware and install permanent settings A21/L3 902L @ 310p B21/L3 902L @ 310p **Emergency restoration would require setting change at 19s to coordinate** | 240 kV, Pre-Condition
ALTALINK | 522s T1 (522s Cooking Lake) | 2018-11-26 10:00 | 2018-11-29 14:00 | N | N | replace 25kv metering PTs | Transformer |  | Replace 25kv Metering PTs, Salvage 522s5, Install wildlife cover on 25KV Bus 1 | For Information Only
ALTALINK | 310p Sundance 240kV Bus A,310P T32 (310P Sundance) | 2018-11-26 11:00 | 2018-11-29 16:00 | N | Y | migrate and commission all T32 & 310P412 protections, breaker, status, controls, alarms, metering and remote access to the new RTU | Bus, Transformer |  | Migrate and commission all T32 & 310P412 protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. Replace 310P3289 air break control module, commission alarms control and status to new RTU. | 240 kV, Contingency Requires Mitigation
Saskpower | SaskPower A1R | 2018-11-27 01:00 | 2018-11-27 16:00 | N | Y | forced outage | Line |  |  | Limits ATC
ALTALINK | 752L (64s East Crossfield - 752L67),64s 752X (64s East Crossfield) | 2018-11-27 07:15 | 2018-12-10 16:45 | N | Y | project: rebuild of 752L from str 36 to 64s | Line, Circuit Breaker |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T1 (65s High River),13L/158L (65s High River - 392s Black Diamond) | 2018-11-27 07:30 | 2018-11-29 15:00 | N | N | replace the T1 bushings | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 847L (602s Cold Creek - 406s Fickle Lake) | 2018-11-28 07:30 | 2018-11-28 17:00 | N | N | install conductor on 847AL and connect to 847L, energize 1029s Vista | Line |  | Outage to install conductor on 847AL and connect to 847L & customer-owned 1029s, energize 1029s | Pre-Condition, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20) | 2018-11-28 10:30 | 2018-12-04 16:00 | N | N | NGR addition | Transformer |  |  | For Information Only
ALTALINK, ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader),409s 110 (409s Shell Scotford) | 2018-11-28 10:30 | 2018-11-28 16:30 | N | Y | 409s110 breaker trouble breaker fail | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn Plant) | 2018-11-28 11:00 | 2018-11-28 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 869s 702T (869s Seal Lake) | 2018-11-29 07:00 | 2019-01-11 17:00 | N | N | transfer load to 701T | Transformer |  |  | For Information Only
EPCOR | 52s T2 (52s East Industrial) | 2018-11-29 07:00 | 2018-12-05 17:00 | N | Y | cutover of new relay protection | Transformer |  |  | 240 kV, Pre-Condition
ATCO | 951s 920C (951s Thickwood),951s SVC (951s Thickwood) | 2018-11-29 08:00 | 2018-11-30 16:00 | N | N | ISD: Nov 29, 2018 | Shunts
ALTALINK | 250p22 (250p Bighorn Plant) | 2018-11-29 09:00 | 2018-11-29 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 256s C1 (256s Harmattan),256s 53 (256s Harmattan) | 2018-11-29 09:00 | 2018-11-29 16:00 | N | N | perform standard relay maintenance | Circuit Breaker, Shunts |  | Techs to perform standard relay maintenance on the following:C1 50/51/51N/27/59/60/C1 SR760. | Pre-Condition, For Information Only
ALTALINK | 551GL1 | 2018-11-29 10:00 | 2018-11-29 12:00 | N | N | Fortis crew installing 20A OCR on distribution line | Switch |  |  | For Information Only
ATCO | 2075s ACF11 (2075s Newell) | 2018-11-29 10:00 | 2018-11-30 17:30 | N | Y | switching for SVC1 outage | Shunts |  | Switching for SVC1 Outage ACF11 Firmware upgrades (VCS PLCs, Siemens AC relays), Password Changes (VCS PLCs & HMI, transformer ITM, 6MD BCUs, SEL relay, WinCC HMI computers  SVC building & MCB, TFR computer), Save Device Configuration Backups (Digsi Project, AcSELerator Project, VCS PLCs & HMI, transformer ITM), Cisco switch replacement. Loss of SVC Redundancy. There is no change to 13L50 DC power transfer capabilities while one SVC is out of service, however the reactive power capabilities of the SVC's will be reduced from +/-150Mvar to +/-75Mvar with only SVC2 in service | 240 kV, Pre-Condition
ALTALINK | 331s T2 (331s Ponoka) | 2018-11-29 11:30 | 2018-11-29 13:00 | N | N | add supervisory controls to 331s21 | Transformer |  |  | For Information Only
ALTALINK | 331s T1 (331s Ponoka) | 2018-11-29 13:30 | 2018-11-29 15:00 | N | N | add supervisory controls to 331s18 | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 13L/158L (65s High River - 392s Black Diamond) | 2018-11-29 15:00 | 2018-12-20 17:45 | N | N | 13L rebuild phase I (str1-53) | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 926L (310p Sundance - 17s Benalto) | 2018-11-30 08:00 | 2018-12-19 14:00 | N | Y | component replacements on structures | Line |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2018-12-01 00:01 | 2018-12-03 06:00 | N | N | contractors working near line installing water, sewer and gas | Line |  |  | For Information Only
ENMAX | 138-31.CAP (ENMAX 31),ENMAX 31 B138-31CAP (ENMAX 31) | 2018-12-01 08:00 | 2018-12-02 18:00 | N | N | replace and test rusted capacitors | Circuit Breaker |  |  | Pre-Condition
ATCO | 7L53 (7L53 tap - 700s Bonnyville),700s 702 (700s Bonnyville) | 2018-12-02 07:45 | 2018-12-04 18:00 | N | N | forced outage | Line, Circuit Breaker |  | Changing cross-arms | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft W722 (Woodcroft),Woodcroft W724 (Woodcroft),Woodcroft T3 (Woodcroft) | 2018-12-03 07:00 | 2018-12-14 17:00 | N | N | cutover of new transformer protection | Transformer, Circuit Breaker |  |  | For Information Only
EPCOR | 805s T4 (805s Jasper) | 2018-12-03 07:30 | 2018-12-07 17:00 | N | Y | metering cutover | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 38 138-38.CAP (ENMAX 38) | 2018-12-03 08:00 | 2018-12-09 18:00 | N | N | replace and test rusted capacitors at Enmax 38 | Circuit Breaker |  |  | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2018-12-03 08:00 | 2018-12-05 16:00 | N | N | T-60 relay CPU upgrade | Transformer |  |  | For Information Only
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2018-12-03 08:00 | 2018-12-07 14:00 | N | Y | changes cross-arm | Line |  | Cross-Arm Changes | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2018-12-03 08:00 | 2018-12-06 16:00 | N | Y | change cross-arm | Line |  | Cross Arm Change | Pre-Condition
AESO | 6L96 (735s Swan River - 744s Federated Pipelines - 743s Sarah Lake) | 2018-12-03 08:00 | 2018-12-06 16:00 | N | N | salvage 3 way gang switch tTo remove 3 way gang switch at Federated pipe | Line |  | 6L96 salvage 3 way gang switch To remove 3 way gang switch at Federated pipe | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2018-12-03 08:00 | 2018-12-07 16:00 | N | N | HVB heater retrofit - 47B138-771/1 | Circuit Breaker |  |  | For Information Only
ENMAX | 5.10TR | 2018-12-03 08:00 | 2018-12-09 16:00 | N | N | HICO transformer tap changer re-plumb | Terminal Equipment |  |  | For Information Only
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake),717s 702 (717s Ethel Lake),715s 703 (715s Leming Lake) | 2018-12-03 08:00 | 2018-12-06 16:00 | N | Y | 715s 7L66D1 replacement ground grid modifications | Circuit Breaker, Line |  | 715S 7L66D1 REPLACEMENT GROUND GRID MODIFICATIONS Switch Replacement 7L66 OOS for duration of work, 846S and 940S will be radial fed from 700S , 717S radial from 846S for duration of the work | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 9L46 (932s Pemukan - 959s Lanfine) | 2018-12-03 08:00 | 2018-12-09 15:00 | N | N | OPGW (fibre optic) repair on 9L46 | Line |  | GOI to complete the OPGW (Fibre Optic) repair on 9L46 | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | 33.2TR (ENMAX 33) | 2018-12-03 08:00 | 2018-12-03 16:00 | N | N | oil sampling and investigate PT connection on NGR install | Transformer |  | oil sampling MT, TC. Investigate PT connection on NGR install - 33.2TR | For Information Only
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2018-12-03 09:15 | 2018-12-10 10:14 | N | Y | component replacement | Line |  | Component Replacement (multi str between 20-79) | 240 kV
ALTALINK | 207s T1 (207s Pinedale),744L (228s T.M.P.L.Niton - 207s Pinedale),207s 744 (207s Pinedale),138 kV BUS 1 (207S Pinedale),207s 552 (207s Pinedale) | 2018-12-03 09:30 | 2018-12-04 17:00 | N | N | replace switch and SS1, install bird coverup, close open point C verify bus damper | Transformer, Line, Bus, Circuit Breaker |  | Replace 207s16 & rename to 207s40, replace SS1 & connect to 207s41, install bird coverup, Close Open Point "C", Verify Bus Damper installation in existing 138 Bus 1. If not present, install new damper. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 902L (19s Wabamun - 310p Sundance),19s 902 (19s Wabamun) | 2018-12-03 10:00 | 2018-12-06 16:00 | N | Y | migrate and commission all L3 to new RTU and LAN | Line, Circuit Breaker |  | Migrate and commission all L3 - 902L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L3 alarms. | 240 kV, Pre-Condition
ATCO | 6L12 (6L25 tap - 774s Monitor),774s 601 (774s Monitor),774S 701T | 2018-12-03 10:00 | 2018-12-13 16:00 | N | N | 601 breaker replacement | Circuit Breaker, Line, Terminal Equipment |  | 774S - BKR 601 EMERGENCY REPLACEMENT Replace BKR 601, Repair hot spots on 6L12D5 and 601A 773S Coronation will be radial fed during outage | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 56s C1 (56s Boyle) | 2018-12-03 13:00 | 2018-12-03 16:30 | N | N | standard relay maintenance | Shunts |  | Techs to perform standard relay maintenance on: Cap bank protections: SILH 60N-A/C1 C1, SILH 60N-T/C1 C1. Note: Cap Bank will need to be out of service while techs are testing the Cap Bank Protections. | Pre-Condition
ENMAXEC | 383S Kettles Hill Windfarm | 2018-12-04 08:00 | 2018-12-05 18:00 | N | Y | DVar maintenance | Station |  | The outage is requested for equipment parts replacement on voltage control units PME#1 and #2. Voltage site support will be reduced to 50% (4MVA dynamic support). We will only take one unit down at a time to complete the repair per day. | Restricts Generation
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely),725L (15s Fort MacLeod - 725BL54),15s Fort Macleod 138kV Bus2,15s T2 (15s Fort Macleod) | 2018-12-04 08:00 | 2018-12-04 17:00 | N | N | cut existing 180L shield wire and connect to new 138kV high bay | Line, Transformer, Bus |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
TRANSALTA | 239S Castle River | 2018-12-04 09:00 | 2018-12-04 17:00 | N | N | installation of fiberoptic cable over the underground cables | Station |  |  | Restricts Generation
ALTALINK | 227S Cutting Lake | 2018-12-04 10:00 | 2018-12-06 12:00 | N | N | 227s2125 input and commission new SEL-351R line protection settings, transfer trip salvaged | Station |  | Input and commission new SEL-351R line protection settings. Transfer trip salvaged. | For Information Only
ATCO | 6L126 (515L tap - 743s Sarah Lake) | 2018-12-04 18:00 | 2018-12-06 12:30 | N | Y | closing open Points 'A' & 'B' and removing temporary bypass using hot line technique | Line |  |  | Pre-Condition, For Information Only
ATCO | 7L65 (709s Vegreville - 710s Vermilion) | 2018-12-05 07:00 | 2018-12-07 17:30 | N | N | transfer line to new substation | Line |  | Transfer line to new substation | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK, ATCO | 650s 252 (650s Hansman Lake),650s 352 (650s Hansman Lake),650S SVC (650s Hansman Lake) | 2018-12-05 08:00 | 2018-12-06 16:00 | N | Y | urgent replace flow sensor on cooling system | Circuit Breaker, Shunts |  |  | 240 kV
ALTALINK | 905L (19s Wabamun - 37s North Calder),19s 905 (19s Wabamun),19s T10 (19s Wabamun) | 2018-12-05 08:00 | 2018-12-06 18:00 | N | Y | urgent repair for breaker | Line, Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.1TR (ENMAX 2) | 2018-12-05 08:00 | 2018-12-05 16:00 | N | N | measure MV bushing for engineering. | Transformer |  |  | For Information Only
ALTALINK | 207s T2 (207S Pinedale) | 2018-12-05 08:00 | 2018-12-06 16:00 | N | N | install bird cover on T2 and 25KV bus/AMI cable frame | Transformer |  |  | For Information Only
ALTALINK | 250p11 (250p Bighorn Plant) | 2018-12-05 11:00 | 2018-12-05 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 52s T1 (52s East Industrial) | 2018-12-06 07:00 | 2018-12-07 17:00 | N | Y | cutover of new relay protection. | Transformer |  |  | 240 kV
ALTALINK | 445s T2 (445s Elk River) | 2018-12-06 10:00 | 2018-12-06 14:00 | N | N | clean and repair bushing connector for hot spot | Transformer
ALTALINK | 902L (19s Wabamun - 310p Sundance) | 2018-12-06 16:01 | 2019-01-07 08:00 | N | Y | upgrading firmware and installing temporary settings @ 19s & 310p in preparation for the re-configuration of 902L/1046L | Line |  | CANA will be upgrading firmware and installing temporary settings @ 19s & 310p in preparation for the re-configuration of 902L/1046L in January 2019 - Upgrade firmware and install temporary settings and re-name A21/L2 902/1046L (old 902) @ 19s B21/L2 902/1046L (old 902) @ 19s - Line protections will be set for temp. 19s  338s connection and named 902L/1046L - Upgrade firmware and install permanent settings A21/L3 902L @ 310p B21/L3 902L @ 310p **Emergency restoration would require setting change at 19s to coordinate** | 240 kV, Pre-Condition
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-12-08 07:00 | 2018-12-11 19:00 | N | N | expedite work within 1.80/1.81 pothead yard | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2018-12-08 08:00 | 2018-12-09 20:00 | N | N | Project 1787 - install 7.1TR risers and initial energization of new SW87 special energization step for SW87 required. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 7 SW87 (ENMAX 7) | 2018-12-09 20:00 | 2018-12-16 09:00 | N | N | 7 sub transformer upgrade Phase1. 7PT138-Z31(new) construction | Switch |  |  | For Information Only
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-12-10 07:00 | 2018-12-19 18:00 | N | N | line rebuild | Line |  | Energize/de-energize bypass line between Str275 and Str303 to allow for rebuild of 551L (Sections 12A/12B). Bypass to be energized/de-energized using live line techniques; no interruption to 551L loads | For Information Only
SUNCOR | 139s Hillridge RTU/SCADA | 2018-12-10 07:00 | 2018-12-10 18:00 | N | N | point to point testing | Terminal Equipment |  | Complete integration of Chin Chute substation and point to point testing. | Affects Visibility
ALTALINK | 874L (522s Cooking Lake - 45s Bretona) | 2018-12-10 07:15 | 2018-12-12 16:00 | N | N | structures repair | Line |  | repairing 874L Structures #132, 146 & 147, 165-167, 200 & 201 | Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1238L (510s Sunnybrook - 330p Genesee),510s 2852 (510s Sunnybrook),510s 3052 (510s Sunnybrook) | 2018-12-10 08:00 | 2018-12-17 08:00 | N | Y | installing new 510s2952, CT's, 510s46, 510s48 and protection; closing open points 'A', 'B', 'D' & 'E' | Line, Circuit Breaker |  | Installing new 510s2952, CT's, 510s46, 510s48 and protection; Closing Open Points 'A', 'B', 'D' & 'E' | Pre-Condition, Contingency Requires Mitigation, 500 kV
ENMAX | 23.3TR (ENMAX 23) | 2018-12-10 08:00 | 2018-12-13 16:00 | N | N | transformer maintenance | Transformer |  | ILJIN Transformer Tap Changer Re-plumb. Transformer maintenance | For Information Only
ENMAX | 37.1TR (ENMAX 37) | 2018-12-10 08:00 | 2018-12-21 16:00 | N | N | RTU replacement | Transformer |  | 37s RTU replacement. Panel Door replacement. | For Information Only
ALTALINK | 33s6 (33s Spray) | 2018-12-10 08:00 | 2018-12-13 18:00 | N | Y | maintenance | Switch |  | TAU Spray Two Generator Routine Maint. (Brushgear & other PMs) | Restricts Generation
SUNCOR | 29EDD-18 Firebag | 2018-12-10 08:00 | 2018-12-24 16:00 | N | N | G8, 9, 10, 11 reactive capacity increase. ISD Dec 17, 2018 | Station
ENMAX | 14.4TR (ENMAX 14) | 2018-12-10 08:00 | 2018-12-10 18:00 | N | N | RTU upgrade | Transformer |  | 14 sub RTU Upgrade. Pulling cables into cells. MD open and closed during return for commissioning Manual breaker control operation required. | For Information Only
EPCOR | 524s T1 (524s Owen Corning) | 2018-12-10 08:00 | 2018-12-10 12:00 | N | N | hot fuse | Transformer |  |  | For Information Only
ENMAX | 36.2TR (ENMAX 36) | 2018-12-10 08:00 | 2018-12-11 16:00 | N | N | rebuilt PRD | Transformer |  | Corrective. Rebuilt PRD Found Not Wired - Complete Wiring and Test [AVANTIS]. | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2018-12-10 08:00 | 2018-12-12 16:00 | N | N | relay upgrade | Transformer |  |  | For Information Only
ALTALINK | 805L (964s Pigeon Lake - 86s Bigstone) | 2018-12-10 08:15 | 2018-12-13 14:45 | N | N | rebuild underbuild | Line |  | Fortis Maintenance (rebuild underbuild (WW-376); requires outage on 805L to salvage conductor and re-move hardwear from AltaLink structures) | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20) | 2018-12-10 09:00 | 2018-12-10 12:00 | N | N | RTU Upgrade | Transformer |  | 20 sub RTU Upgrade. Manual breaker control operation required. MD required to open and close on return. Outage shared with NGR project. | For Information Only
ATCO | 724s 601 (724s Hines Creek) | 2018-12-10 09:00 | 2018-12-20 16:00 | N | N | maintenance | Circuit Breaker |  | 724S 601 cutover alarm points / CT Ratio / PT wire / Commission ratio change on 601, re-wire PT, replace 21A relay 800S Friedenstal protecting line during outage to 601 and 600PT1 | Pre-Condition, For Information Only
ALTALINK | 767L (310p Sundance - 767L50),310p 767X (310p Sundance) | 2018-12-10 10:00 | 2018-12-20 17:00 | N | N | upgrade breaker fail protection | Circuit Breaker, Line |  | Upgrade breaker fail protection. | Pre-Condition
ALTALINK | 844L (358s Amoco Brazeau - 477s Amoco West Pembina),477s 844X (477s Amoco West Pembina) | 2018-12-10 10:15 | 2018-12-13 15:30 | N | N | CT replacement | Line, Circuit Breaker |  | CT replacement. Redundant line and bus protections will have short outages (one at a time) to facilitate the CT replacement. | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 937L (102s Langdon - 5s East Calgary) | 2018-12-10 10:15 | 2018-12-12 17:45 | N | Y | component replacement | Line |  | Component Replacement (multi str between 21-87) | 240 kV, Pre-Condition
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2018-12-10 12:00 | 2018-12-20 18:00 | N | Y | relocate poles, line move | Line |  | 7L199 relocate poles 30 36 [ crew charge ] 7L199 Line Move | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.3TR (ENMAX 20) | 2018-12-10 12:00 | 2018-12-10 16:00 | N | N | RTU Upgrade | Transformer |  | 20 sub RTU Upgrade. Manual breaker control operation required. MD required to open and close on return. | For Information Only
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station),1057L (89s Ellerslie - 657s Summerside),89s 452 (89s Ellerslie),89s 352 (89s Ellerslie) | 2018-12-11 07:00 | 2018-12-11 17:00 | N | Y | replace 89s452 breaker wiring in the JB | Line, Circuit Breaker |  | Replace 89s452 Breaker Wiring in the JB | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2018-12-11 07:00 | 2018-12-11 17:00 | N | Y | urgent repair required | Line |  | High Priority - Urgent repair required - Hot connection | 240 kV, Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 226S Garden City,891L (226s Garden City - 891L1) | 2018-12-11 07:00 | 2018-12-13 18:00 | N | N | integrate RTAC | Station, Line |  | To complete integration of the Real-Time Automation Controller (RTAC). MWF will be in an outage and isolate itself from the 891L. | For Information Only
ATCO | 7L92 (7L92D5 - 709s Vegreville) | 2018-12-11 07:00 | 2018-12-14 17:30 | N | N | transfer line to new substation | Line |  | Transfer line to new substation | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 747L (99s North St. Albert - 747L3A) | 2018-12-11 07:00 | 2018-12-12 16:00 | N | N | maintenance on 747L between Structures #29  70 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 283s T2 (283s Violet Grove) | 2018-12-11 08:00 | 2018-12-18 17:00 | N | N | replace bus transfer switch | Transformer |  | Trouble Corrective: Replace bus transfer switch. Install 2 new MOD on the 25kV crossbus.283s16 will be moved outside and 283s18 is permanently disabled to adress the arc flash concerns in the medal clad. Return CI S/O_____________________ to Close open point 'A' | For Information Only
ENMAX | 14.3TR (ENMAX 14) | 2018-12-11 08:00 | 2018-12-11 18:00 | N | N | upgrade 14 sub RTU | Transformer |  | 14 sub RTU Upgrade. Pulling cables into cells. MD open and closed during return for commissioning Manual breaker control operation required. | For Information Only
ALTALINK | 163s T1 (163s Amoco Empress) | 2018-12-11 08:00 | 2018-12-11 14:30 | N | Y | customer replace their 163s48 PT | Transformer |  | Customer Replacing their 163s48 PT - Like for Like | 240 kV
ATCO | 930s Syn Condenser (930s Arcenciel) | 2018-12-11 08:00 | 2018-12-13 16:00 | N | Y | synchronous condenser turnaround | Shunts |  | Sync Condenser turnaround, unavailable for dispatch | Pre-Condition
ATCO | 828s 701T (828s Sulphur Point) | 2018-12-11 08:00 | 2018-12-20 16:00 | N | N | upgrade 701T protection | Transformer |  | Upgrade 701T protection, Ensure all 25kV Load can be offloaded to 791S, transfer all load from 828S to 791S. Close in BKR 506 to maintain station service | For Information Only
BCH | 1L274 (Britt Creek - 1D4L274) | 2018-12-11 09:00 | 2018-12-20 17:00 | Y | Y | annual plan request F19 | Line |  |  | Pre-Condition, Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1112L (289s Saunders Lake - 89s Ellerslie),947L (89s Ellerslie - 987s Clover Bar) | 2018-12-12 07:00 | 2018-12-12 17:00 | N | Y | Replace 89s1652 Breaker Wiring in the JB | Line |  |  | 240 kV
ENMAX | 14.1TR (ENMAX 14) | 2018-12-12 08:00 | 2018-12-12 18:00 | N | N | RTU upgrade | Transformer |  | 14 sub RTU Upgrade. MD open and closed during return for commissioning Manual breaker control operation required. | For Information Only
ALTALINK | 199L (347s Fox Creek - 741s Fox Creek),347s 199W (347s Fox Creek) | 2018-12-12 08:00 | 2018-12-20 18:00 | N | Y | replace broken mechanism in the breaker | Circuit Breaker, Line | Trouble Corrective: Replace broken mechanism in the breaker. |  | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 691L (74s Janet - 419s Chestermere) | 2018-12-12 08:00 | 2018-12-12 12:00 | N | N | installation of corona rings on 691L line polymers at substation dead end | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ATCO | 9L950 (132s Ware Junction - 801s Anderson),801s 911 (801s Anderson) | 2018-12-12 09:00 | 2018-12-12 16:00 | N | Y | breaker testing and maintenance | Circuit Breaker, Line |  | breaker testing and maintenance | 240 kV, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 17s T2 (17s Benalto),17s Benalto 240 kV South Bus 2 | 2018-12-12 09:00 | 2018-12-12 17:00 | N | Y | changing out insulators on the 240kV south bus 2 | Transformer, Bus |  |  | Pre-Condition, Overload, Over/Under Voltage, Restricts Generation
ALTALINK | 254s36 (254s Coaldale),254s 25kV bus2 (254s Coaldale) | 2018-12-12 13:00 | 2018-12-12 17:00 | N | N | create open point on 25 kV Bus 2 to facilitate the replacement of 254s15. | Bus, Switch |  | Create Open Point on 25 kV Bus 2 to facilitate the replacement of 254s15. | For Information Only
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2018-12-12 14:00 | 2018-12-12 17:00 | N | N | Installation of corona rings on 765L line | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2018-12-13 06:00 | 2018-12-14 16:00 | N | Y | repair a broken structure | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 2075s SVC2 (2075s Newell) | 2018-12-13 07:00 | 2018-12-14 17:00 | N | Y | replace a failed module | Shunts |  |  | 240 kV
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2018-12-13 07:00 | 2018-12-13 09:00 | N | N | RTU upgrade, manual breaker control operation required | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 702L (377s Hardisty - 137s Sedgewick),377s 702W (377s Hardisty) | 2018-12-13 07:30 | 2018-12-13 14:30 | N | Y | change center phase heater | Circuit Breaker, Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2018-12-13 08:00 | 2018-12-13 16:00 | N | N | RTU upgrade, commissioning manual breaker control operation required | Shunts |  |  | For Information Only
ALTALINK | 510s 2952 (510s Sunnybrook),510s48 (510s Sunnybrook),510s46 (510s Sunnybrook) | 2018-12-13 08:00 | 2018-12-27 16:00 | N | N | ISD Dec 20, 2018 | Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 254s T1 (254s Coaldale) | 2018-12-13 08:00 | 2018-12-14 09:00 | N | N | replace 254s15 | Transformer
ENMAX | 5.8TR (ENMAX 5) | 2018-12-13 08:00 | 2018-12-13 13:00 | N | N | oil sampling | Transformer
ALTALINK | 76L (115s Mt. Allan - 33s Spray) | 2018-12-13 08:15 | 2018-12-13 17:45 | N | Y | repair/replace blown lightning arrestor | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s T3 (63s Red Deer) | 2018-12-13 09:00 | 2018-12-13 15:00 | N | N | trouble corrective:top up SF6 138kV breaker-63s26 low gas | Transformer
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2018-12-13 09:00 | 2018-12-13 16:00 | N | N | spare TX move across yard | Line, Transformer |  |  | Pre-Condition
ALTALINK | 728L (405s Waupisoo - 353s Plamondon),405s 728 (405s Waupisoo) | 2018-12-13 09:30 | 2018-12-13 14:00 | N | N | breaker trouble | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2018-12-13 12:00 | 2018-12-13 16:00 | N | N | RTU upgrade, manual breaker control operation required | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 58s T2 (58s Edson) | 2018-12-13 13:00 | 2018-12-13 13:45 | N | N | add supervisory control to 58s3. 58s39 will be closed to allow the operation of 58s3 | Transformer
ALTALINK | 58s T1 (58s Edson) | 2018-12-13 14:00 | 2018-12-13 14:45 | N | N | add supervisory control to 58s37 and 58s39. 58s39 will be closed to allow the operation of 58s37 | Transformer
ALTALINK | 202L (58s Edson - 178s Cynthia),58s 202X (58s Edson) | 2018-12-13 15:00 | 2018-12-13 16:00 | N | N | add supervisory control to 58s202X re-closer | Circuit Breaker, Line |  | Add supervisory control to 58s202X recloser. Need to test breaker. | Pre-Condition
ATCO | 744S Federated Pipelines | 2018-12-14 08:00 | 2018-12-28 16:00 | N | N | 744s DTS termination and substation salvaged after Dec 21st | Station
ALTALINK | 1029s Vista | 2018-12-14 08:00 | 2018-12-28 16:00 | N | N | ISD: Dec 21, 2018. Tap in 847L (406s - 39s) | Station
ENMAX | 7.1TR (ENMAX 7) | 2018-12-14 08:00 | 2018-12-28 18:00 | N | N | transformer upgrade. ISD Dec 21, 2018 | Transformer
ALTALINK | 254s T2 (254s Coaldale) | 2018-12-14 09:00 | 2018-12-14 13:00 | N | Y | close open point on 25 kV bus 2 after the replacement of 254s15 | Transformer |  |  | For Information Only
ATCO | 828s 507C1 (828s Sulphur Point),828s 507C2 (828s Sulphur Point),828s 507 (828s Sulphur Point) | 2018-12-14 09:30 | 2018-12-15 17:30 | N | N | breaker 507 CT ratio change | Circuit Breaker, Shunts |  | BKR 507 CT ratio change 507C1 and 507C2 remain out of service for duration of work. | For Information Only
ALTALINK | 526BL (659s Pegasus Lake - 526L tap),526L(526L190 - 526L208) | 2018-12-16 08:00 | 2018-12-16 17:00 | N | Y | installing temporary bypass from structure #200 - 203 and creating open points 'C' & 'D' | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2018-12-16 09:00 | 2018-12-16 13:00 | N | N | 7 sub transformer upgrade Phase1. Initial energization of 7PT138-Z31(New) open secondary fuses. old 7PT138-Z31 will remian in service | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L14 (705s Kitscoty - 751s Hill) | 2018-12-17 08:00 | 2018-12-20 17:00 | N | N | clearance mitigation on 7L14 | Line |  | Clearance Mitigation on 7L14 STUDY NOT SENT | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.3TR (ENMAX 39) | 2018-12-17 08:00 | 2018-12-17 18:00 | N | N | upgrade RTU | Transformer |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2018-12-17 08:00 | 2018-12-19 16:00 | N | N | upgrade T-60 relay CPU | Transformer |  |  | For Information Only
ENMAX | 12.2TR (ENMAX 12) | 2018-12-17 08:00 | 2018-12-17 16:00 | N | N | LTC low oil alarm | Transformer |  |  | For Information Only
ALTALINK | 841L (477s Amoco West Pembina - 489s Amoco Canada Brazeau River),477s 841X (477s Amoco West Pembina) | 2018-12-17 08:00 | 2018-12-19 18:00 | N | N | CT replacement, redundant line and bus protections will have short outages (one at a time) to facilitate the CT replacement | Circuit Breaker, Line |  | CT replacement. Redundant line and bus protections will have short outages (one at a time) to facilitate the CT replacement. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s 2852 (510s Sunnybrook) | 2018-12-17 08:00 | 2018-12-19 15:30 | N | Y | install new 510s2952, CT's, 510s46, 510s48 and protection | Circuit Breaker |  | Installing new 510s2952, CT's, 510s46, 510s48 and protection; Closing Open Points 'A', 'B', 'D' & 'E' | 500 kV
ALTALINK | 252s 2 (252s Jarrow),491L (252s Jarrow - 7L50 tap) | 2018-12-17 11:30 | 2018-12-17 17:00 | N | N | urgent change relay settings | Line, Circuit Breaker |  | Techs will be onsite to repair issues with the following relay and perform settings changes to 252s 491L 167N relay | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29PL7-10 (29EDD-18 - 29EDD-85) | 2018-12-17 17:00 | 2018-12-19 18:44 | N | N | forced outage due to loss of protection | Line |  |  | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2018-12-18 00:01 | 2018-12-28 12:00 | N | N | 1.80L/1.81L cable replacement project | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),Enmax 1 B138-5A0 (ENMAX 1),Enmax 1 B138-4A0 (ENMAX 1) | 2018-12-18 00:01 | 2018-12-21 16:00 | N | N | expand GOI at 1sub for GIS work | Line, Circuit Breaker |  | 1.80L/1.81L cable replacement project. Expand GOI at 1sub for GIS work. GOI SW84@28Sub, 4a9@1sub, Ground 4a8 on return. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2018-12-18 03:30 | 2018-12-18 12:30 | N | N | emergency repair | Line |  | Emergency Repair: change broken insulator at Str428 | For Information Only
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2018-12-18 07:00 | 2018-12-20 18:00 | N | Y | 17s903N switch replacement - bus needed due to proximity / approach | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 526L(526L190 - 526L208) | 2018-12-18 07:00 | 2019-01-26 08:00 | N | Y | creating temporary Open Point 'E' between structures #215 & 216 | Line |  | creating temporary Open Point 'E' between structures #215 & 216 | Creates Radial Feeds
ENMAX | 39.4TR (ENMAX 39) | 2018-12-18 08:00 | 2018-12-18 18:00 | N | N | RTU upgrade | Transformer |  | RTU upgrade. Manual breaker control operation required. 39.118 Fortis switching required | For Information Only
ALTALINK | 519L (519AL tap - 996s Imperial Oil Carson Lake) | 2018-12-18 08:00 | 2018-12-18 13:00 | N | N | 996s519 low in gas | Line |  |  | For Information Only
ATCO | 826s 901T (826s Marguerite Lake),826s 701TD (826s Marguerite Lake) | 2018-12-18 09:00 | 2018-12-20 16:00 | N | Y | emergency hot spot repair | Transformer, Switch |  | 826S 701TD EMERGENCY Hot spot repair (over 30 degrees) Assess and repair hotspot on 701TD Plan to coordinate with 710CT Replacement at same time 826S 710CT North Phase Oil Leak 901T will be de energized for duration of GOI 7L587 will only have a single breaker feeding line 710 PT is de energized for the duration of GOI (901T Voltage transducer and controller, no problem) | 240 kV
ALTALINK | 945s T2 (945s Sunshine Village) | 2018-12-18 10:30 | 2018-12-18 15:30 | N | N | techs need to familiarize themselves with these new breakers | Transformer |  |  | For Information Only
ALTALINK | 501L (302s Cardinal River - 501L286) | 2018-12-19 07:00 | 2018-12-20 13:00 | N | N | component replacements between structures #312 - 328 | Line |  |  | For Information Only
ENMAX | 39.1TR (ENMAX 39) | 2018-12-19 08:00 | 2018-12-19 13:00 | N | N | RTU upgrade | Transformer |  |  | For Information Only
ALTALINK | 283s T1 (283s Violet Grove) | 2018-12-19 08:00 | 2018-12-20 16:00 | N | N | install new steel standoffs & install new hook switches | Transformer |  | Trouble Corrective:Install new steel standoffs & install new Hook Switches. Close open point 'B' | For Information Only
ALTALINK | 320p 2152 (320p Keephills) | 2018-12-19 08:30 | 2018-12-19 13:30 | N | Y | 320p3152 gas top up | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 347s Fox Creek RTU/SCADA | 2018-12-19 09:00 | 2018-12-19 15:00 | N | N | fix UHF radio link issue between 9928R | Terminal Equipment |  |  | Affects Visibility
ENMAX | 39.2TR (ENMAX 39) | 2018-12-19 13:00 | 2018-12-19 18:00 | N | N | RTU upgrade | Transformer |  |  | For Information Only
ALTALINK | 310P T36 (310p Sundance),310p T30 (310p Sundance),310p Sundance 240kV Bus C | 2018-12-20 09:00 | 2018-12-20 13:00 | N | Y | trip testing from 310p767X breaker fail | Transformer, Bus |  | trip testing from 310p767X breaker fail to 310p2852, 310p69 and 310p414. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 7.2TR (ENMAX 7) | 2019-01-03 08:00 | 2019-02-26 18:00 | N | N | remove old 7.2TR and install new 7.2TR | Transformer |  | P#1787. 7 sub transformer upgrade Phase2. Remove old 7.2TR, Install new 7.2TR. 24hr backfeed required prior to energization | For Information Only
ATCO | 7L130 (710s Vermilion - 705s Kitscoty) | 2019-01-03 08:00 | 2019-01-03 15:00 | N | N | clearance mitigation | Line |  | Clearance Mitigation | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.2TR (ENMAX 37) | 2019-01-03 08:00 | 2019-01-11 16:00 | N | N | replace RTU and panel door | Transformer |  | 37s RTU replacement. Panel Door replacement. | For Information Only
Syncrude | Aurora T4 (Aurora) | 2019-01-04 08:00 | 2019-01-13 09:00 | N | Y | urgent oil inspection | Transformer |  |  | 240 kV, Restricts Generation
EPCOR | 72LS24 (Strathcona - 803s Lambton) | 2019-01-06 20:00 | 2019-01-07 04:00 | N | N | Dacro Industries re - design | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39),ENMAX 39 B138-39.82 (ENMAX 39) | 2019-01-07 05:00 | 2019-01-07 06:00 | N | N | upgrade 39 sub RTU | Line, Circuit Breaker |  | 39 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition
ENMAX | 38.83L (ENMAX 39 - ENMAX 38),ENMAX 39 B138-38.83 (ENMAX 39) | 2019-01-07 06:00 | 2019-01-07 07:00 | N | N | upgrade 39 sub RTU | Line, Circuit Breaker |  | 39 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1046L (310p Sundance - 338s Cherhill),902L (19s Wabamun - 310p Sundance),310p 1052 (310p Sundance),310p 1152 (310p Sundance),310p 752 (310p Sundance),310p 852 (310p Sundance) | 2019-01-07 07:00 | 2019-01-14 13:00 | N | Y | re-route 1046L temporarily onto 902L by creating Open Point 'B' & 'C' and jumper 1046L to 902L to accommodate structure repairs | Line, Circuit Breaker |  | Re-routing 1046L temporarily onto 902L by creating Open Point 'B' & 'C' and jumpering 1046L to 902L to accommodate structure repairs CANA will be upgrading firmware and installing temporary settings @ 19s & 310p - Upgrade firmware and install temporary settings and re-name A21/L2 902/1046L (old 902) @ 19s B21/L2 902/1046L (old 902) @ 19s - Line protections will be set for temp. 19s  338s connection and named 902L/1046L - Upgrade firmware and install permanent settings A21/L3 902L @ 310p B21/L3 902L @ 310p | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 805s C1 (805s Jasper),805s T1 (805s Jasper),72JM18 (805s Jasper - Meadowlark),72JW19 (805s Jasper - Woodcroft) | 2019-01-07 07:30 | 2019-01-12 17:00 | N | Y | metering cutover | Transformer, Shunts, Line |  |  | 240 kV, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1046L (338s Cherhill - 19s Wabamun) | 2019-01-07 08:00 | 2019-01-21 16:00 | N | N | terminate line from 310p to 19s. ISD Jan 14, 2018 | Line
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2019-01-07 08:00 | 2019-01-08 16:00 | N | N | maintenance on SW83, SW84, SW85 | Line, Transformer |  | HV SW Maintenance SW83, SW84, SW85. Adjust 1.80L GOI | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11B138-BT5 (ENMAX 11) | 2019-01-07 19:00 | 2019-01-07 20:00 | N | N | upgrade 11 sub RTU | Circuit Breaker |  | 11 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 11 B138-11.82 (ENMAX 11),11.82L (ENMAX 14 - ENMAX 11) | 2019-01-07 20:00 | 2019-01-07 21:00 | N | N | upgrade 11 sub RTU | Line, Circuit Breaker |  | 11 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.81L (ENMAX 13 - ENMAX 11),ENMAX 11 B138-11.81 (ENMAX 11) | 2019-01-07 21:00 | 2019-01-09 18:00 | N | N | upgrade 11 sub RTU | Line, Circuit Breaker |  | 11 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition
ENMAX | 11.83L (162s Beddington - ENMAX 11),ENMAX 11 B138-11.83 (ENMAX 11) | 2019-01-07 22:00 | 2019-01-07 23:00 | N | N | upgrade 11 sub RTU | Line, Circuit Breaker |  | 11 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition, Overload
Saskpower | SaskPower P2A | 2019-01-08 06:00 | 2019-01-08 15:00 | N | Y | maintenance | Line |  |  | Limits ATC
ALTALINK | 1088L (324s Cassils - 2075s Newell) | 2019-01-08 07:00 | 2019-01-09 18:00 | N | Y | component replacements between structures #11 - 14 | Line |  |  | 240 kV
ATCO | 7L73 (829s Boucher Creek - 800s Friedenstal),800s 702 (800s Friedenstal) | 2019-01-08 07:00 | 2019-01-15 17:00 | N | Y | upgrade 7L73 protection and install TPR and new RAS | Circuit Breaker, Line |  | Upgrade 7L73 protection and install TPR and new RAS. study not sent for | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 2029s Heathfield RTU/SCADA | 2019-01-08 08:00 | 2019-01-08 16:00 | N | N | troubleshoot RAS RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 950L (132s Ware Junction - 801s Anderson),132s 3 (132s Ware Junction),132s 6 (132s Ware Junction) | 2019-01-08 09:00 | 2019-01-08 17:00 | N | Y | fix 132s4 hot switch | Line, Circuit Breaker
ALTALINK | 64s T2 (64s East Crossfield),901AL (64s East Crossfield - 901L tap),901L (63s Red Deer - 74s Janet) | 2019-01-08 17:00 | 2019-01-09 17:00 | N | Y | emergency repair on shield wires | Line, Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 835L (384s Keystone - 835L tap),384s 835X (384s Keystone) | 2019-01-09 08:00 | 2019-01-09 12:30 | N | N | standard relay maintenance | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
BLACKSPRING | 485s Black Springs RTU/SCADA | 2019-01-09 08:00 | 2019-01-09 17:00 | N | N | update the software within RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2019-01-09 08:30 | 2019-01-09 12:30 | N | N | high load move between structures 46 and 47 | Line |  | High Load Move Between Structures 46 and 47 Requested By: Wally Popik / 780.918.5194 | Pre-Condition
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2019-01-09 10:00 | 2019-01-09 12:00 | N | Y | remove a nest from 255s34 | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 1035L (2075s Newell - 244s Bowmanton) | 2019-01-10 07:00 | 2019-01-22 18:00 | N | Y | component replacements | Line |  | Component replacements between Structures #17 - 388 | 240 kV, Pre-Condition
ENMAX | 38.83L (ENMAX 39 - ENMAX 38) | 2019-01-10 08:00 | 2019-01-14 16:00 | N | N | insulator and conductor replacement | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Saskpower | SaskPower P2A | 2019-01-11 06:00 | 2019-01-11 15:00 | N | Y | maintenance | Line |  |  | Limits ATC
ALTALINK | 5s C4 (5s East Calgary), 5s C3 (5s East Calgary), 5s 7 (5s East Calgary) | 2019-01-11 08:00 | 2019-01-15 16:00 | N | N | forced outage | Shunts, Circuit Breaker |  |  | Pre-Condition
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39) | 2019-01-12 08:00 | 2019-01-13 16:00 | N | N | 38.83L insulator & conductor replacement | Transformer |  |  | For Information Only
ALTALINK, FORTIS | 1020s Exshaw Extension,985s 811QC04 (985s Exshaw) | 2019-01-14 06:00 | 2019-01-14 18:00 | N | N | maintenance | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 812AL (512s Hartell - 812L tap),812L (392s Black Diamond - 65s High RIver) | 2019-01-14 07:00 | 2019-01-14 18:00 | N | N | repair broken conductor | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 11.4TR (ENMAX 11) | 2019-01-14 08:00 | 2019-01-14 18:00 | N | N | RTU upgrade | Transformer |  | 11 sub RTU Upgrade. Manual breaker control operation required. Pull new cable in switchgear. | For Information Only
ENMAX | 3.3TR (ENMAX 3) | 2019-01-14 08:00 | 2019-01-16 16:00 | N | N | T-60 relay CPU upgrade and test HV CTs | Transformer |  | T-60 Relay CPU upgrade. Test HV CTs | For Information Only
ATCO, GREENGATEP | 9L59 (972s Tinchebray - 801s Anderson),9L59D1 (801s Anderson),9L59D2 (972s Tinchebray) | 2019-01-14 08:00 | 2019-01-18 18:00 | N | Y | clearance mitigation | Line, Switch |  | 9L59- GOI permit for Clearance Mitigation | 240 kV, Creates Radial Feeds
ENMAX | 37.2TR (ENMAX 37) | 2019-01-14 08:00 | 2019-01-28 16:00 | N | N | 37s RTU replacement | Transformer |  | 37s RTU replacement. Panel Door replacement. | For Information Only
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2019-01-14 08:00 | 2019-02-08 14:00 | N | N | place 551JL tap loads on temp gen-set to string bypass | Line |  | place 551JL tap loads on temp genset to string bypass over tap point. loads to remain on genset until bypass has been completed and energized at which point 551IL loads to be connected to bypass | For Information Only
ENMAX | 6.4TR (ENMAX 6),6.80L (ENMAX 35 - ENMAX 6) | 2019-01-14 08:00 | 2019-01-15 18:00 | N | N | switch maintenance and check reversing switch | Line, Transformer |  | HV SW MD maint SW81, SW82, SW84, SW89, SW90, MD-6.4TR. Check reversing switch | Firm Load Loss, Creates Radial Feeds
ALTALINK | 254s 2162X (254s Coaldale) | 2019-01-14 09:30 | 2019-01-17 17:00 | N | Y | disconnect old cables and connect new cables | Circuit Breaker |  | Disconnect old cables and connect new cables | Restricts Generation, For Information Only
ATCO | 7L61 (780s Lubicon - 796s Nipisi) | 2019-01-14 12:00 | 2019-01-18 10:30 | N | N | replace/repair transmission poles | Line |  | Replace/repair transmission poles | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1046L (310p Sundance - 338s Cherhill),902L (19s Wabamun - 310p Sundance) | 2019-01-14 13:00 | 2019-03-30 08:00 | N | Y | replacing structures #11 & 12,this portion of 902L remain under a separate GOI zone to prevent mis-coordination | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 13L/158L (65s High River - 392s Black Diamond) | 2019-01-15 07:00 | 2019-04-12 14:30 | N | N | phase 2 & 3 rebuilding 13L line from Structures #1 - 16 and rebuilding 158L line from Structures #4 - 53 | Line |  | Phase 2 & 3 rebuilding 13L line from Structures #1 - 16; Rebuilding 158L line from Structures #4 - 53 | Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2019-01-15 08:00 | 2019-01-15 16:00 | N | N | RTU upgrade | Shunts |  |  | For Information Only
ATCO | 827s SVC (827s Cranberry Lake) | 2019-01-15 08:00 | 2019-01-17 16:00 | N | Y | UPS replacement: replace 5KVA DC/AC inverter | Shunts |  | UPS replacement @ 827S Cranberry SVC Outage to Replace 5KVA DC/AC Inverter Limited VAR control on system. The only other means of control is the Capacitor Bank @ 780S | Pre-Condition, For Information Only
ENMAX | 22.1TR (ENMAX 22) | 2019-01-15 08:00 | 2019-01-15 12:00 | N | N | construction for 138kV BT at 22sub | Transformer |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22) | 2019-01-15 12:00 | 2019-01-15 16:00 | N | N | construction for 138kV BT at 22sub | Transformer |  |  | For Information Only
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2019-01-15 12:00 | 2019-01-30 14:00 | N | N | rebuild of 551L (Sections 14B/C) | Line |  | Energize/de-energize bypass line between Str327 and Str346 to allow for rebuild of 551L (Sections 14B/C). Bypass to be energized/de- energized using live line techniques; no interruption to 551L loads | For Information Only
CMH, Medicine Hat | 20L (MH69S-6 Riverview - MH69S-3 South Ridge),MH69s6 MH69-T63 (MH69s6 Riverview),MH69s3 T34 (MH69s3 South Ridge) | 2019-01-16 07:00 | 2019-01-18 12:00 | N | N | line work on underbuild distribution circuits | Line, Transformer |  | The equipment included as part of the outage is: MH-20L 138kV transmission line MH138-317 138kV breaker MH138-318 138kV disconnect switch MH138-620 138kV breaker MH138-621 138kV disconnect switch | For Information Only
ALTALINK | 13s 1352 (13s Deerland) | 2019-01-16 08:00 | 2019-01-16 17:00 | N | Y | correct a wiring error on the 13s1352 breaker control interface | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 14.3TR (ENMAX 14) | 2019-01-16 08:00 | 2019-01-16 10:00 | N | N | 14 sub RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36),ENMAX 36.2TR (ENMAX 36) | 2019-01-16 08:00 | 2019-01-16 18:00 | N | N | crane in new 36.5TR to pad | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.2TR (ENMAX 11) | 2019-01-16 08:00 | 2019-01-16 12:00 | N | N | 11 sub RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 2.80L (ENMAX 2 - ENMAX 23) | 2019-01-16 08:00 | 2019-01-25 16:00 | N | N | Green Line LRT Project | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 6.1TR (ENMAX 6),6.82L (ENMAX 6 - ENMAX 41) | 2019-01-16 08:00 | 2019-01-17 18:00 | N | N | switch maintenance and check reversing switch 6.1TR | Transformer, Line |  | HV SW MD maint SW85, SW86, SW87, SW88, MD-6.1TR. Check reversing switch 6.1TR. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.4TR (ENMAX 14) | 2019-01-16 10:00 | 2019-01-16 12:00 | N | N | RTU upgrade | Transformer |  |  | For Information Only
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2019-01-16 10:00 | 2019-01-16 15:00 | N | N | high load move between Structures #198 & 199 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-01-16 11:00 | 2019-01-16 15:00 | N | N | maintenance | Switch |  |  | Restricts Generation
ENMAX | 11.1TR (ENMAX 11) | 2019-01-16 12:00 | 2019-01-16 16:00 | N | N | RTU upgrade | Transformer |  |  | For Information Only
ENMAX | 22.3TR (ENMAX 22) | 2019-01-16 14:00 | 2019-01-18 16:00 | N | N | emergency outage due to a bad lightening arrestor | Transformer
ENMAX | 32.1TR (ENMAX 32) | 2019-01-17 08:00 | 2019-01-17 16:00 | N | N | take measurements for HV and MV bushings | Transformer |  |  | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2019-01-17 09:00 | 2019-01-17 16:00 | N | N | reverse PT secondary wiring in control cabinet | Transformer |  |  | For Information Only
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2019-01-17 09:00 | 2019-02-01 16:00 | N | N | line re-build | Line |  | Re-building line between Structures #551 & 611 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-01-17 09:00 | 2019-01-17 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 1.5TR (ENMAX 1) | 2019-01-18 08:00 | 2019-01-18 12:00 | N | N | add heat shrink to NGR riser | Transformer |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2019-01-18 12:00 | 2019-01-18 18:00 | N | N | add heat shrink to NGR riser | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2019-01-19 05:00 | 2019-01-21 06:00 | N | Y | transformer upgrade | Line |  | P#1787. 7 sub transformer upgrade Phase2. Remove old Z31 138kV PTs, Drill pilings for BT1. 7.84L and 7.82L protection potential source to be rewired to new 138kV PTs. | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2019-01-20 08:00 | 2019-01-25 17:00 | N | N | forced outage | Line
ENMAX | 16.2TR (ENMAX 16),16.60L (ENMAX 34 - ENMAX 16),16.63L (ENMAX 16 - ENMAX 36) | 2019-01-20 08:00 | 2019-01-20 18:00 | N | N | hot spot | Line, Transformer |  | 16SW69 Hot Spot middle phase harp | Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s 2852 (510s Sunnybrook),510s 2952 (510s Sunnybrook) | 2019-01-21 07:00 | 2019-01-25 18:00 | N | Y | 510s Sunnybrook to 939s Livock end to end protection testing via microwave path | Circuit Breaker |  |  | 500 kV
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft WDS1 (Woodcroft) | 2019-01-21 07:00 | 2019-01-26 17:00 | N | N | disconnect replacement | Switch, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2019-01-21 07:00 | 2019-01-25 17:00 | N | Y | DC power move and relay maintenance | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station),1055L (816s Petrolia - 629s Argyll Transfer Station) | 2019-01-21 07:00 | 2019-01-25 17:00 | N | Y | relay maintenance | Line |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Creates Radial Feeds
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2019-01-21 08:00 | 2019-01-25 18:00 | N | Y | clearance mitigation | Line |  | 9L59- GOI permit for Clearance Mitigation | 240 kV, Firm Load Loss, Creates Radial Feeds
ENMAX | 21.1TR (ENMAX 21) | 2019-01-21 08:00 | 2019-01-24 16:00 | N | N | T-60 relay CPU upgrade, test CT | Transformer
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2019-01-21 08:00 | 2019-01-22 18:00 | N | N | switch maintenance, check reversing switch | Line, Transformer |  |  | Pre-Condition
ATCO | 826s 704 (826s Marguerite Lake) | 2019-01-21 10:30 | 2019-01-21 16:00 | N | N | repair oil leak, ring bus will be open for the duration | Circuit Breaker |  | Repair oil Leak, Ring Bus will be open for the duration | Contingency Requires Mitigation
ATCO | 7L06 (784s Donnelly - 787s High Prairie) | 2019-01-21 12:00 | 2019-01-24 14:00 | N | N | pole fire, replace structures | Line |  | 7L06 pole fire / replace after emergency replace structures | Firm Load Loss, Creates Radial Feeds
ALTALINK | 234L (310p Sundance - 234L1),505L (505L1 - 234L tap) | 2019-01-22 06:00 | 2019-01-31 19:00 | N | N | re-locating structures #234L73 - 234L76 | Line
ALTALINK | 521AL (867s Sundance Blow-Down - 521L tap),521L (521L2 - 505L tap) | 2019-01-22 07:00 | 2019-01-31 20:00 | N | N | re-locating structures #521L39 - 521L42 | Line
ATCO | 7L75 (ATC 793s West Peace River - 800s Friedenstal) | 2019-01-22 07:00 | 2019-01-29 17:00 | N | Y | upgrade 7L75 protection and install new TPR and RAS | Line |  | Upgrade 7L75 protection and install new TPR and RAS study not sent for | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 3.4TR (ENMAX 3) | 2019-01-22 08:00 | 2019-01-24 16:00 | N | N | T-60 relay CPU upgrade | Transformer |  |  | For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2019-01-22 08:00 | 2019-01-23 18:00 | N | N | building construction | Line
ATCO | 826s 702 (826s Marguerite Lake) | 2019-01-22 09:00 | 2019-01-22 16:00 | N | N | open ring bus to repair leaking 702CT's | Circuit Breaker |  | Open ring bus to Repair Leaking 702CT's | Contingency Requires Mitigation
ATCO | 832s 701T (832s Blumenort) | 2019-01-22 09:00 | 2019-01-22 17:00 | N | N | alarm on low oil in conservator | Transformer
ALTALINK | 28s 41 (28s West Brooks) | 2019-01-22 10:00 | 2019-01-22 16:00 | N | N | add oil to middle phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2019-01-23 07:00 | 2019-01-31 18:00 | N | Y | component replacements between structures #2 - 386 | Line |  |  | 240 kV, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 14.3TR (ENMAX 14) | 2019-01-23 08:00 | 2019-01-25 16:00 | N | N | investigate oil leak, change the gas relay cable and check reversing switch | Transformer |  |  | For Information Only
ATCO | 826s 710 (826s Marguerite Lake) | 2019-01-23 09:00 | 2019-01-23 16:00 | N | N | repair oil leak | Circuit Breaker |  | Repair oil Leak, Ring Bus will be open for the duration | Pre-Condition, Contingency Requires Mitigation
BLACKSPRING | 485S Black Springs | 2019-01-23 09:00 | 2019-01-23 17:30 | N | N | servers replacement | Station |  |  | For Information Only
SUNCOR | 29EDD-34 RTU/SCADA | 2019-01-23 10:00 | 2019-01-23 13:00 | N | N | update RTU | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 157s T1 (157s Lac La Biche) | 2019-01-24 07:30 | 2019-01-24 13:00 | N | N | install bird cover | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1),1.82L (ENMAX 1 - ENMAX 5) | 2019-01-24 08:00 | 2019-02-04 16:00 | N | N | breaker maintenance on 1B138-2a0, 138kV GIS | Line, Transformer |  |  | For Information Only
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton) | 2019-01-25 07:30 | 2019-01-31 17:30 | N | N | replace structure 21 | Line |  | Replace Structure 21 Requested By: Ignacio Saralegui | For Information Only
ENMAX | 36.5TR (ENMAX 36) | 2019-01-25 08:00 | 2019-02-08 16:00 | N | N | replace existing transformer. ISD Feb 1, 2019 | Transformer
ATCO | 890s 701T (890s Melito) | 2019-01-25 21:06 | 2019-02-18 16:00 | N | N | forced outage | Transformer |  | 890s Melito sustained load transformer fault on 890sL701T which also tripped 7LA59_1 (Melito 890s - T7LA59). 4MW load lost @890s. Mobile substation is being used to feed the load.
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-01-26 07:00 | 2019-01-31 19:00 | N | N | high POT testing and fence installation and remaining outdoor work in pothead yard | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 7.82L (42s Sarcee - ENMAX 7) | 2019-01-26 08:00 | 2019-01-27 18:00 | N | Y | transformer upgrade phase 2 | Line |  | P#1787. 7 sub transformer upgrade Phase2. Place new 138kV breaker on footings. Energize new SW88, Special energization instructions required. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 520L (887s Mobil Oil Carson Creek - 520L1),526L (268s Whitecourt - 526DL185),526BL (659s Pegasus Lake - 526L tap),526L(526L190 - 526L208) | 2019-01-26 08:00 | 2019-01-26 17:00 | N | Y | removing temporary bypass; replacing wire | Line |  | Removing temporary bypass between Structures #200 - 203; Also replacing some wire near the A-frame @ 659s | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 519AL (519L tap - 661s Laura Lake),519L (519AL tap - 519L2),519L (519AL tap - 996s Imperial Oil Carson Lake),526L (526L220 - 526L365) | 2019-01-27 07:00 | 2019-01-27 17:00 | N | Y | closing temporary open point 'E' and creating new temporary open point 'F | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (526L220 - 526L365) | 2019-01-27 17:00 | 2019-01-31 08:00 | N | N | line rebuild | Line |  | Re-building 526L between Structures #526L217 - 526L220 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside),89s 452 (89s Ellerslie),89s 352 (89s Ellerslie) | 2019-01-28 07:00 | 2019-01-31 15:00 | N | Y | relay maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station),240BA2 (814s Bellamy - 629s Argyll Transfer Station),814s B2401 (814s Bellamy),814s B2402 (814s Bellamy) | 2019-01-28 07:00 | 2019-02-01 17:00 | N | Y | relay maintenance | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 803s T3 (803s Lambton),72LH8 (Hardisty - 803s Lambton),72LS24 (Strathcona - 803s Lambton),803s L721 (803s Lambton) | 2019-01-28 07:30 | 2019-01-28 15:30 | N | Y | disconnect repair on LDS11 and LDS12 | Transformer, Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 162.3TR (ENMAX 162 Beddington) | 2019-01-28 08:00 | 2019-02-01 16:00 | N | N | relay CPU upgrade | Transformer |  | T-60 Relay CPU upgrade. Remove GSSE messaging from affected relays. | Pre-Condition, For Information Only
ENMAX | 5.1TR (ENMAX 5),5.6TR (ENMAX 5),5.8TR (ENMAX 5),1.82L (ENMAX 1 - ENMAX 5) | 2019-01-28 08:00 | 2019-01-31 13:00 | N | N | maintenance | Line, Transformer |  | HV SW maint SW101, SW82G, SW89, SW90, SW94, SW95. 5MD138-5.1TR whips not seated. 5B138-1.82 Breaker Mod. Stiff Switch Operation SW95. 5B138-1.82L Hotspot Repair. SF6 sample 5B138-1.82(weather)SW 89 East phase not closing all the way | For Information Only
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2019-01-28 08:00 | 2019-01-31 17:00 | N | N | cross arm change | Line |  | Crossarm Change | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L90 (813s Little Smoky - 7L90D2) | 2019-01-28 12:00 | 2019-01-31 14:00 | N | N | replace cross arm and structures | Line |  | Replace XARMS and structures | Pre-Condition, Over/Under Voltage
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2019-01-29 07:00 | 2019-02-04 17:00 | N | Y | spacer and damper replacement on structures # 4 - 191 | Line |  |  | For Information Only, 500 kV
ALTALINK | 113L (20s Ghost - 33s Spray) | 2019-01-29 07:00 | 2019-01-30 18:00 | N | Y | replacing 113L structures #46, 47 & 48 | Line |  | Urgent work declared by Altalink | Overload
ENMAX | 28.2TR (ENMAX 28) | 2019-01-29 08:00 | 2019-01-30 16:00 | N | N | replace and test T60 relay | Transformer |  |  | For Information Only
ATCO | 959S SVC (959s Lanfine) | 2019-01-29 08:00 | 2019-01-30 16:00 | N | Y | GE to install latest software for SVC | Shunts |  | GE to Install latest software for SVC, SVC will not be available for duration of outage | 240 kV, Pre-Condition
ALTALINK | 267s C3 (267s Killarney Lake) | 2019-01-29 10:30 | 2019-01-30 10:30 | N | N | repair leaking caps | Shunts |  |  | For Information Only
ALTALINK | 83s C2 (83s Taber),83s 67 (83s Taber) | 2019-01-29 11:30 | 2019-01-31 12:30 | N | N | Upgrade protection relay | Circuit Breaker, Shunts |  | Upgrade C2 protection relay from GE SR750 to GE SR850 | Pre-Condition, For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa),38s 215N (38s East Edmonton) | 2019-01-30 07:30 | 2019-01-30 12:30 | N | N | replace CT cover | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie) | 2019-01-30 08:00 | 2019-01-30 13:00 | N | N | high load move between structures #109 & 110 | Line |  |  | Overload, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 225L (225s Magrath - 225AL tap) | 2019-01-30 18:03 | 2019-02-14 14:10 | N | N | Urgent: clearance issues | Line |  | Line touching under built 25 kV | For Information Only
ALTALINK | 76L (115s Mt. Allan - 33s Spray) | 2019-01-31 07:00 | 2019-01-31 18:00 | N | Y | replacing structure #76L46 arrestor | Line |  | Urgent work declared by Altalink | Firm Load Loss, Creates Radial Feeds
ALTALINK | 526L (526DL365 - 526DL208) | 2019-01-31 08:00 | 2019-01-31 17:00 | N | N | closing temporary open point 'F' | Line |  | Closing temporary Open Point 'F' between Structures #216 & 217 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2019-01-31 09:00 | 2019-02-01 16:00 | N | Y | shunt reactor leak repair | Shunts |  |  | For Information Only, 500 kV
ATCO, ALTALINK | 789L (818s Winefred - 898s Heart Lake) | 2019-02-01 07:00 | 2019-03-01 18:00 | N | Y | install new line airbreaks | Line |  | install New Line Airbreaks - Pre work for Future New 1034s CNRL Margie substation. 789L is N.O. at 818s | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2019-02-01 08:00 | 2019-02-08 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2019-02-01 20:00 | 2019-03-05 07:59 | N | N | Urgent: clearance issues | Line |  |  | Contingency Requires Mitigation, For Information Only
ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap) | 2019-02-01 20:00 | 2019-02-15 12:00 | N | N | Urgent: clearance issues | Line |  |  | Contingency Requires Mitigation, For Information Only
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2019-02-01 20:00 | 2019-02-07 19:00 | N | N | Urgent: clearance issues | Line |  |  | Contingency Requires Mitigation, For Information Only
ALTALINK | 807L (233s Beamer - 807L tap) | 2019-02-01 20:00 | 2019-02-22 18:00 | N | N | Urgent: clearance issues | Line |  |  | Contingency Requires Mitigation, For Information Only
ENMAX | 22.1TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13) | 2019-02-02 07:00 | 2019-02-04 12:00 | N | N | construction for 138kV BT at 22sub | Line, Transformer |  | Construction for 138kV BT at 22sub. Energize new 22PT138-Z31. Re-position SW89. Special energization instructions required. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2019-02-04 07:00 | 2019-02-11 16:00 | N | Y | Sunnybrook interconnection project requires modification to the 510s-511s C&P systems | Line |  | Sunnybrook interconnection project requires modification to the 510s-511s C&P systems. Modifications are required in programming, software and hard wiring. After modifications are implemented, testing of new logic and new equipment status of 510s2952, 510s4789 and trip /open command A21/12L41 to initiate ESOF1-P1, trip/open command B21/12L41 to initiate ESOF1-P2 trips are required. | 500 kV
ALTALINK | 510s 2852 (510s Sunnybrook),510s 2952 (510s Sunnybrook) | 2019-02-04 07:00 | 2019-02-11 18:00 | N | Y | functional testing HVDC logic | Circuit Breaker |  |  | 500 kV
ALTALINK | 510S (510s Sunnybrook - 510s Sunnybrook),510s T11 (510s Sunnybrook) | 2019-02-04 07:00 | 2019-02-07 13:00 | N | Y | 510s station maintenance and modifications for Fort McMurray interconnection | Line, Transformer |  |  | 500 kV
ALTALINK | 511s T11 (511s Crossings) | 2019-02-04 07:00 | 2019-02-11 17:00 | N | Y | 511s valve hall maintenance, thyristor replacement and T11-B cooler leak repair | Transformer |  | 511s Valve Hall maintenance, Thyristor Replacement and T11-B Cooler Leak repair. 511s will require a Open Convertor Test when GOI is released. Link is already scheduled to be out of service during this time for the | 240 kV
EPCOR | Rossdale T3 (Rossdale) | 2019-02-04 08:00 | 2019-02-09 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ALTALINK | 190L (17s Benalto - 320p Keephills),320p 652 (320p Keephills),320p 552 (320p Keephills) | 2019-02-04 09:30 | 2019-02-18 17:00 | N | Y | firmware upgrades and testing | Line, Circuit Breaker |  | 17s1, 17s2 C60s, 190L A&B Line protections and 190L Air Brk Control Modules. Firmware Upgrades and Testing | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 310P 512N (310p Sundance) | 2019-02-04 10:30 | 2019-02-07 16:30 | N | N | migrate and commission all 310P512N protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN | Circuit Breaker |  | Migrate and commission all 310P512N protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. | Pre-Condition
ATCO | 977s 910R (977s Salt Creek),977s 910 (977s Salt Creek) | 2019-02-04 12:00 | 2019-02-06 16:00 | N | N | forced outage | Circuit Breaker, Shunts |  |  | Pre-Condition
ENMAX | 21.1C (ENMAX 21) | 2019-02-04 12:00 | 2019-02-05 10:00 | N | N | forced | Shunts |  |  | Pre-Condition
ENMAX | 22.81L (ENMAX 22 - ENMAX 39),22B138-22.81 (ENMAX 22) | 2019-02-04 22:00 | 2019-02-04 23:59 | N | N | construction for 138kV BT at 22sub | Line, Circuit Breaker |  | construction for 138kV BT at 22sub. Short out BD CT Circuit | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 747L (99s North St. Albert - 747L3A) | 2019-02-05 07:00 | 2019-02-13 17:00 | N | N | maintenance on 747L between str 29  70 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2019-02-05 07:00 | 2019-02-11 19:00 | N | N | high POT testing and fence installation and remaining outdoor work in pothead yard | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2019-02-05 08:00 | 2019-02-08 17:00 | N | Y | investigate failures of cooling system with manufacturer present | Shunts, Transformer |  | Investigate failures of cooling system (Runtime Faults) with manufacturer present. Will require SVC+ to be energized for part of this outage to perform heatrun test on cooling system. No VARs will be exchanged with | 240 kV, Pre-Condition
ENMAX | Enmax 1 B138-4A0 (ENMAX 1) | 2019-02-05 08:30 | 2019-02-06 16:00 | N | N | breaker would not close - follow up work order. | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (Britt Creek - 1D4L274) | 2019-02-05 09:00 | 2019-02-14 17:00 | Y | Y | replace end-of-life structures and related defects. | Line | Peak RC COS outage ID: 1-00625438 |  | Pre-Condition, Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds, Impacts RAS
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek),730s 703 (730s Rycroft) | 2019-02-06 07:00 | 2019-02-12 17:00 | N | Y | upgrade protection,install teleprotection and new RAS | Circuit Breaker, Line |  | Upgrade 7L73 protection and install teleprotection and new RAS @ 730s, 829s radial fed from 800s. study not sent for | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 796s 701T (796s Nipisi) | 2019-02-06 07:00 | 2019-03-01 17:00 | N | N | switching to isolate 701T and 25kV switchgear bus | Transformer |  | Switching to isolate 701T and 25kV switchgear bus | For Information Only
ENMAX | 54.1TR (ENMAX 54) | 2019-02-06 08:00 | 2019-02-12 16:00 | N | N | HICO transformer tap changer re-plumb | Transformer |  |  | For Information Only
ENMAX | ENMAX 54,41.84L (ENMAX 54 - ENMAX 41),54.81L (ENMAX 54 - ENMAX 65) | 2019-02-06 08:00 | 2019-02-15 16:00 | N | N | move double circuit pole for interchange | Line, Station |  |  | For Information Only
ENMAX | 22.3TR (ENMAX 22) | 2019-02-06 08:00 | 2019-02-06 16:00 | N | N | construction for 138kV BT at 22sub | Transformer |  | construction for 138kV BT at 22sub CT testing, changing bus diff tap | For Information Only
ALTALINK | 723s T2 (723s Christina Lake),723s 252 (723s Christina Lake) | 2019-02-06 08:00 | 2019-02-08 16:00 | N | Y | forced outage | Transformer, Circuit Breaker |  | Emergency Work; low gas west phase | 240 kV, For Information Only
AESO-SC | EMS | 2019-02-06 09:00 | 2019-02-06 16:00 | N | N | database update | SCInternal |  |  | For Information Only
ALTALINK | 723s 252 (723s Christina Lake) | 2019-02-07 00:45 | 2019-02-12 16:00 | N | N | forced outage | Circuit Breaker
EPCOR | 814s B2402 (814s Bellamy),814s B2406 (814s Bellamy),814s T2 (814s Bellamy) | 2019-02-07 07:00 | 2019-02-08 17:00 | N | Y | relay maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Over/Under Voltage
ENMAX | 22.2TR (ENMAX 22) | 2019-02-07 08:00 | 2019-02-07 16:00 | N | N | construction for 138kV BT at 22sub | Transformer |  | construction for 138kV BT at 22sub. CT testing, changing bus diff tap | Pre-Condition, For Information Only
ALTALINK | 508L (344s Warner - 67s Stirling) | 2019-02-07 09:00 | 2019-02-13 18:00 | N | N | connecting temporary bypass and changing out structures #17 & 18 (open point 'C' and open point D) | Line |  |  | For Information Only
ENMAX | 36.3TR (ENMAX 36) | 2019-02-07 19:30 | 2019-03-15 16:00 | N | N | forced outage - investigate and repair transformer trip. 36.3TR LTC trip - the PRD on the LTC was activated | Transformer |  | investigate and repair transformer trip. 36.3TR LTC trip - the PRD on the LTC was activated | For Information Only
EPCOR, ALTALINK | 665s TX1 (665s Dome),909L (89s Ellerslie - 665s Dome),665s D2401 (665s Dome),665s D2402 (665s Dome) | 2019-02-08 07:00 | 2019-02-12 17:00 | N | Y | relay maintenance | Circuit Breaker, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 658L (649s Chappice Lake - 562s Cypress) | 2019-02-08 07:00 | 2019-03-18 18:00 | N | N | line rebuild between Structures #1 - 56 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 318s T5 (318s Scoria) | 2019-02-08 08:00 | 2019-02-22 16:00 | N | N | ISD Feb 15, 2019 | Transformer
AESO-SC | CROW | 2019-02-08 11:00 | 2019-02-08 13:00 | N | N | CROW production migration: SDC to PDC | SCInternal |  |  | For Information Only
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2019-02-09 09:00 | 2019-02-09 11:00 | N | N | 20 sub RTU upgrade | Line |  | 20 sub RTU Upgrade. Manual breaker control operation required. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 37.2TR (ENMAX 37),37.82L (74s Janet - ENMAX 37) | 2019-02-10 08:00 | 2019-02-10 12:00 | N | Y | 37s CAC OAC RTU commissioning | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.1TR (ENMAX 37),37.81L (ENMAX 38 - ENMAX 37) | 2019-02-10 12:00 | 2019-02-10 16:00 | N | N | 37s CAC OAC RTU commissioning | Line, Transformer |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 814s T1 (814s Bellamy),814s B2401 (814s Bellamy),814s B2407 (814s Bellamy) | 2019-02-11 07:00 | 2019-02-11 17:00 | N | Y | relay maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, Over/Under Voltage
EPCOR | 657s Summerside T2 (657s Summerside),657s SU2403 (657s Summerside),657s SU2402 (657s Summerside) | 2019-02-11 07:00 | 2019-02-15 17:00 | N | Y | relay maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition, For Information Only
EPCOR | 557s 2405 (557s Castle Downs) | 2019-02-11 07:00 | 2019-02-11 17:00 | N | Y | relay maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 8.3TR (ENMAX 8) | 2019-02-11 08:00 | 2019-02-14 18:00 | N | N | dew point too low needs be dried out | Transformer |  | dew point too low needs be dried out. 4aO comp.#4. | For Information Only
ENMAX | 8.4TR (ENMAX 8) | 2019-02-11 08:00 | 2019-02-14 18:00 | N | N | dew point too low on 4aO | Transformer |  | Corrective. Dew point too low on 4aO comp.#5. | For Information Only
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2019-02-11 08:00 | 2019-02-14 17:00 | N | N | crossarm change | Line |  | Crossarm Change | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet) | 2019-02-11 08:00 | 2019-02-12 17:00 | N | N | forced outage | Shunts |  |  | For Information Only
ATCO | 890s 701T (890s Melito) | 2019-02-11 08:00 | 2019-02-25 16:00 | N | N | ISD Feb 18, 2019. Replacement of failed transformer. | Transformer
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2019-02-11 10:00 | 2019-02-15 15:00 | N | Y | crossarm/insulator replacement | Line |  | 7L40 Xarm/Insulator Replacement | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 552 (310p Sundance),310p 652 (310p Sundance) | 2019-02-11 10:30 | 2019-02-19 12:00 | N | Y | migrate and commission protections to new RTU and LAN | Circuit Breaker |  | Migrate and commission all G1 Stub bus protections (including G1 Rev Power tripping auxiliary module), breakers, breaker fail protections status, controls, alarms, metering and remote access to new RTU and LAN. Migrate and commission T1 B protection alarms, 310P1G alarms and status to new RTU. | 240 kV, For Information Only
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2019-02-11 12:00 | 2019-02-18 12:00 | N | Y | pole repairs from 2017 report | Line |  | 7L64 pole repairs from 2017 report | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 720L (347s Fox Creek - 397s Benbow) | 2019-02-12 07:00 | 2019-02-19 18:00 | N | N | component & structure replacement | Line |  |  | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-02-12 07:00 | 2019-02-14 19:00 | N | N | high POT testing, fence installation and remaining outdoor work in pothead yard | Line |  | High POT testing and Fence installation and remaining outdoor work in pothead yard | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2019-02-12 07:00 | 2019-03-09 20:00 | N | Y | spacer and damper replacement | Line |  |  | 500 kV
ENMAX | 22PT138-Z7 (ENMAX 22) | 2019-02-12 08:00 | 2019-02-12 16:00 | N | N | troubleshoot PT sec. voltages | Terminal Equipment |  | Troubleshoot PT sec. voltages | For Information Only
ATCO | 12L44 (951s Thickwood Hills - 939s Livock) | 2019-02-12 08:00 | 2019-02-26 16:00 | N | N | ISD Feb 19, 2019 | Line
ATCO | 951s 1201T (951s Thickwood Hills),951s 1205 (951s Thickwood Hills),951s 1206 (951s Thickwood Hills),951s 1213 (951s Thickwood Hills),951s 1213R (951s Thickwood HIlls) | 2019-02-12 08:00 | 2019-02-26 16:00 | N | N | ISD Feb 19, 2019 | Transformer, Circuit Breaker, Shunts
ATCO | 939s 1207 (939s Livock),939s 1206 (939s Livock),939s 1214 (939s Livock),939s 1216 (939s Livock),939s 1214R (939s Livock),939s 1216R (939s Livock) | 2019-02-12 08:00 | 2019-02-26 16:00 | N | N | ISD Feb 19, 2019 | Circuit Breaker, Shunts
TRANSCANADA | Scoria Cogen | 2019-02-12 08:00 | 2019-02-26 16:00 | N | N | 45.8 MW cogen. ISD Feb 19, 2019 | Unit
ALTALINK | 723s T2 (723s Christina Lake),723s 252 (723s Christina Lake) | 2019-02-12 08:30 | 2019-02-12 13:00 | N | Y | emergency work, low gas west phase | Transformer, Circuit Breaker |  | Emergency Work; low gas west phase | 240 kV, For Information Only
CapitalPower | 615S Halkirk | 2019-02-12 09:00 | 2019-02-12 18:00 | N | N | emergency VOB server replacement | Station
ATCO | 2029s ACF11 (2029s Heathfield) | 2019-02-12 16:19 | 2019-02-21 12:00 | N | Y | forced outage | Shunts |  |  | 500 kV
ATCO | 757s 912T (757s Battle River),9L80 (757s Battle River - 755s Cordel) | 2019-02-12 23:40 | 2019-03-06 18:00 | N | N | forced outage | Transformer, Line |  |  | 240 kV
ENMAX | 2.2TR (ENMAX 2) | 2019-02-13 08:00 | 2019-02-13 16:00 | N | N | low oil level LTC | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2019-02-13 08:00 | 2019-02-13 18:00 | N | Y | maintenance on SW135, SW134, MD-985@25sub | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 331s T2 (331s Ponoka),422L (331s Ponoka - 288s Wolf Creek),331s Ponoka 138kV East Bus | 2019-02-13 08:00 | 2019-02-13 18:45 | N | N | replacement of 1 phase of VT2 331s33 | Bus, Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 761L (71s Lamoureux - 38s East Edmonton) | 2019-02-13 08:00 | 2019-02-16 17:00 | N | N | replace 5 poles between structures #178-190 | Line |  |  | Pre-Condition, For Information Only
BLACKSPRING | 485S Black Springs | 2019-02-13 09:30 | 2019-02-13 17:30 | N | N | servers replacement | Station |  |  | For Information Only
ATCO | 757s 701 (757s Battle River) | 2019-02-13 23:40 | 2019-02-15 18:00 | N | N | forced outage | Circuit Breaker
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2019-02-14 07:00 | 2019-02-14 13:00 | N | N | high load move between structures #198 & 199 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2019-02-14 08:00 | 2019-02-14 18:00 | N | Y | maintenance SW140, SW141, MD-1003@25sub | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2019-02-15 07:00 | 2019-02-17 19:00 | N | N | high POT testing and fence installation | Line |  | High POT testing and Fence installation and remaining outdoor work in pothead yard | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),1.81L (ENMAX 20 - ENMAX 1) | 2019-02-15 23:00 | 2019-02-16 06:00 | N | N | install bridge girders for Crowchild Trail road widening | Line |  | Install bridge girders for Crowchild Trail road widening by Graham Construction | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7) | 2019-02-17 08:00 | 2019-02-17 18:00 | N | Y | P1787 - 7 sub transformer upgrade | Line, Transformer |  | P1787 - 7 sub transformer upgrade Phase2. Energize 7PT138-Z32. Special energization instructions required. | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.2TR (ENMAX 7) | 2019-02-17 08:00 | 2019-03-03 16:00 | N | N | ISD Feb 24, 2019 | Transformer
ALTALINK | 753L (65s High River - 253s Blackie) | 2019-02-18 07:00 | 2019-02-20 18:00 | N | N | structure modification on #1A and #2 | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 330P 12TC1 (330p Genesee),330p 1201 (330p Genesee),330p 1204 (330p Genesee),330p 1207 (330p Genesee),330p 805 (330p Genesee),330P Genesee 500 kV Bus 1 | 2019-02-18 07:00 | 2019-02-22 17:00 | N | Y | relay maintenance | Transformer, Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2019-02-18 07:00 | 2019-02-21 14:00 | N | N | urgent:repair structures #401, 441, 442 & 522 | Line |  |  | Pre-Condition, Over/Under Voltage
EPCOR | 557s T1 (557s Castle Downs),557s 2401 (557s Castle Downs),557s 2406 (557s Castle Downs) | 2019-02-18 07:00 | 2019-02-22 17:00 | N | Y | relay maintenance | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 23.3TR (ENMAX 23) | 2019-02-18 08:00 | 2019-03-01 16:00 | N | N | arc flash relocation: re-route secondary cables | Transformer |  |  | Pre-Condition
ENMAX | 9.3TR (ENMAX 9) | 2019-02-18 08:00 | 2019-03-29 16:00 | N | N | arc flash relocation; re-route secondary cables | Transformer |  |  | For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2019-02-18 08:00 | 2019-03-01 16:00 | N | N | line protection upgrade | Line |  | Line Protection Upgrade | Creates Radial Feeds
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2019-02-18 08:00 | 2019-03-11 13:00 | N | N | construction for 138kV BT at 22sub | Line, Transformer |  | Construction for 138kV BT at 22sub. | Creates Radial Feeds
ENMAX | 1.8TR (ENMAX 1),1.83L (ENMAX 1 - ENMAX 8) | 2019-02-18 08:00 | 2019-03-01 16:00 | N | N | breaker maintenance | Line, Transformer |  | HV Breaker maintenance on 1B138-1a0, 138kV GIS | For Information Only
ALTALINK | 161L (255s Vulcan - 504s Queenstown),504s 5 (504s Queenstown) | 2019-02-18 10:00 | 2019-02-21 17:30 | N | N | replace CTs (CT1) at breaker 504s161 | Line, Switch |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 665s D2402 (665s Dome),665s D2403 (665s Dome),909L (310p Sundance - 665s Dome) | 2019-02-19 07:00 | 2019-02-21 15:10 | N | Y | relay maintenance | Line, Circuit Breaker |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 657s Summerside T1 (657s Summerside) | 2019-02-19 07:00 | 2019-02-22 15:47 | N | Y | relay maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s 11 (17s Benalto) | 2019-02-19 07:30 | 2019-02-19 11:30 | N | Y | trip test | Circuit Breaker |  | Trip Test for 190L Protection Replacement | 240 kV
ALTALINK | 1109L (ENMAX 65 - ENMAX 25) | 2019-02-19 08:00 | 2019-02-19 18:00 | N | Y | switch maintenance SW153, SW152 | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 77s 252 (77s Sagitawah) | 2019-02-19 08:00 | 2019-02-21 19:00 | N | N | Complete Replacement of CT16 (77s252). | Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
BCH | 1L274 (Britt Creek - 1D4L274) | 2019-02-19 09:00 | 2019-03-01 17:00 | Y | Y | replace end-of-life structures and related defects | Line |  |  | Pre-Condition, Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 164L (103s Goose Lake - 415s Drywood) | 2019-02-19 09:00 | 2019-02-28 18:00 | N | N | component replacements | Line |  | Component replacements between Structures #7A - 21A | Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 124L (19s Wabamun - 2739s Wabamun),19s 124 (19s Wabamun) | 2019-02-19 10:30 | 2019-02-19 17:30 | N | N | breaker maintenance | Line, Circuit Breaker |  | 69kV breaker maintenance | For Information Only
ALTALINK | 17s 6 (17s Benalto) | 2019-02-19 11:30 | 2019-02-19 14:00 | N | Y | trip test | Circuit Breaker |  | Trip Test for 190L Protection Replacement | 240 kV
ALTALINK | 926L (310p Sundance - 17s Benalto) | 2019-02-19 12:00 | 2019-03-01 16:00 | N | Y | component replacements and maintenance | Line |  | Working on structures between Benalto and Sundance performing component replacements and maintenance items on 926L | 240 kV
ALTALINK | 275s T1 (275s Jenner),275s Jenner 240kV Bus 1 | 2019-02-19 12:00 | 2019-02-20 14:00 | N | Y | urgent outage to replace the failed 275s2 SBFU breaker relay | Transformer, Bus |  | Urgent outage to replace the failed 275s2 SBFU Breaker relay with a SEL-2BFR relay. Trip test 275s38, 275s152, 275s1752 | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 767L (310p Sundance - 767L50),310p 767X (310p Sundance) | 2019-02-19 12:00 | 2019-02-21 16:30 | N | N | commission 310P767X to the new RTU and LAN | Circuit Breaker, Line |  | Migrate and commission all 310P767X protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 17s 7 (17s Benalto) | 2019-02-19 14:00 | 2019-02-19 16:00 | N | Y | trip test | Circuit Breaker |  | Trip Test for 190L Protection Replacement | 240 kV
ALTALINK | 17s 10 (17s Benalto) | 2019-02-20 07:30 | 2019-02-20 11:30 | N | Y | trip test for 190L protection replacement | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 422L (331s Ponoka - 288s Wolf Creek),331s 422 (331s Ponoka) | 2019-02-20 09:00 | 2019-02-20 18:00 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 149s T3 (149s Nisku) | 2019-02-20 09:00 | 2019-02-20 18:00 | N | N | replace strain insulators on 28LS and on 362LW | Transformer |  | 149s T3 and partial 25kV bus GOI - Replace strain insulators on 28LS and on 362LW. Replace a set of 25kV post insulators on the South bus | For Information Only
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2019-02-20 10:30 | 2019-02-24 15:00 | N | Y | relocate poles 30 36 | Line |  | 7L199 relocate poles 30 36 [ crew charge ] | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 17s 2852 (17s Benalto),17s T3 (17s Benalto) | 2019-02-20 11:30 | 2019-02-20 14:00 | N | Y | trip test for 190L protection replacement | Circuit Breaker, Transformer |  |  | 240 kV, Pre-Condition
ALTALINK | 17s 3 (17s Benalto) | 2019-02-20 14:00 | 2019-02-20 16:00 | N | Y | trip test for 190L protection replacement | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 275s 5 (275s Jenner) | 2019-02-20 15:00 | 2019-02-20 17:00 | N | Y | trip test 275s5 from new 275s2 SBFU breaker relay | Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 149s T1 (149s Nisku) | 2019-02-21 08:00 | 2019-02-21 19:00 | N | N | replace strain insulators on 28LN and on 363LW, and standard relay maintenance 149s2194 | Transformer |  | replace strain insulators on 28LN and on 363LW, and standard relay maintenance 149s2194 | For Information Only
ENMAX | ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D133 (ENMAX 25),ENMAX 25 B240-D139 (ENMAX 25),ENMAX 25 B240-D142 (ENMAX 25),ENMAX 25 240kV North Bus | 2019-02-21 12:01 | 2019-02-22 18:00 | N | Y | HV SW MD maintenance SW136, SW142, SW148, SW154 | Circuit Breaker, Bus |  |  | 240 kV, Pre-Condition
ATCO | MUL1 Mowat | 2019-02-22 08:00 | 2019-03-08 16:00 | N | N | ISD March 1, 2019 | Unit
EPCOR | 72JW19 (805s Jasper - Woodcroft),72NW15 (Namao - Woodcroft) | 2019-02-22 17:00 | 2019-02-24 20:00 | N | N | disconnect replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 753L (65s High River - 253s Blackie),65s 753E (65s High River) | 2019-02-23 07:00 | 2019-02-26 18:00 | N | N | stringing new line overtop of Structure #1A and #2 | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2019-02-23 12:00 | 2019-03-18 14:00 | N | N | energize/de-energize bypass between Str435 and Str469 for rebuild of 551L | Line |  |  | For Information Only
Saskpower | SASK POWER P1C | 2019-02-25 06:00 | 2019-03-12 17:00 | N | Y | salvage three spans of wire and relocate | Line |  |  | Limits ATC
ATCO | 824s 701T (824s Fieldgate),7L67 (824s Fieldgate - 743s Sarah Lake) | 2019-02-25 07:00 | 2019-03-11 17:00 | N | Y | replace 701TCS with BKR 701 and GSW 701A | Transformer, Line |  | Replace 701TCS with BKR 701 and GSW 701A and protection upgrade Mobile sub in service, 824S Radial fed from 851S Morse River and WCSB Power (Genalta) DG separated from the grid for this work until March 5th. Mar 5 - 12, 2019 GOI isolation points shrunk down to 701A (NEW) and 501TD. | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L97 (933s Tower Road - 7LA97) | 2019-02-25 07:00 | 2019-03-01 17:00 | N | N | Crossarm /Insulator /Pole Changes | Line |  | Crossarm /Insulator /Pole Changes | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
EPCOR | 557s T2 (557s Castle Downs),557s 2404 (557s Castle Downs),557s 2403 (557s Castle Downs) | 2019-02-25 07:00 | 2019-03-01 17:00 | N | Y | Relay Maintenance | Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 330P 12TC2 (330p Genesee),330p 1203 (330p Genesee),330p 1206 (330p Genesee),330p 1209 (330p Genesee),330p 809 (330p Genesee),330p Genesee 500 kV Bus 2 | 2019-02-25 07:00 | 2019-03-01 17:00 | N | Y | relay maintenance | Transformer, Bus, Circuit Breaker |  |  | Contingency Requires Mitigation, 500 kV
ATCO | 757s 912T (757s Battle River) | 2019-02-25 08:00 | 2019-03-06 16:00 | N | N | replacement of failed transformer. ISD March 6, 2019 | Transformer
ALTALINK | 77s 352 (77s Sagitawah) | 2019-02-25 08:00 | 2019-02-27 19:30 | N | N | complete replacement | Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1081L (17s Benalto - 281s Johnson) | 2019-02-25 09:30 | 2019-03-01 15:30 | N | Y | A&B line protections replacement | Line |  |  | 240 kV
ALTALINK | 853L (504s Queenstown - 853L76A) | 2019-02-25 10:00 | 2019-02-28 17:00 | N | N | replace CTs (CT3) at breaker 504s853E | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 2852 (310p Sundance),310P T36 (310p Sundance),310p T30 (310p Sundance),310p Sundance 240kV Bus C | 2019-02-25 10:30 | 2019-03-07 16:30 | N | Y | migrate and commission | Bus, Transformer, Circuit Breaker |  | Migrate and commission all T30 & 310p2852 protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2019-02-25 12:00 | 2019-03-05 07:59 | N | Y | pole repairs from 2017 report | Line |  | 7L64 pole repairs from 2017 report | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 745L (602s Cold Creek - 745L482) | 2019-02-26 06:00 | 2019-02-26 18:00 | N | Y | install a coal conveyor under 745L | Line |  | Bighorn Mining, Coalspur Vista needs an outage on 745L so that they can install a coal conveyor under our line. This conveyor would cross between 745L structures 566-567 (closer to 567). 602s DG cannot not be generating onto the system during this outage. | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ATCO | 800s 701T (800s Friedenstal),800s 711 (800s Friedenstal) | 2019-02-26 07:00 | 2019-02-26 17:00 | N | N | breaker fail testing | Circuit Breaker, Transformer |  | Breaker fail testing | For Information Only
ALTALINK | 69s T4 (69s North Barrhead) | 2019-02-26 08:00 | 2019-02-26 17:30 | N | Y | diverter gear box leak | Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 800s 702T (800s Friedenstal),800s 712 (800s Friedenstal) | 2019-02-27 07:00 | 2019-02-27 17:00 | N | N | Breaker fail testing | Transformer, Circuit Breaker |  | Breaker fail testing | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 37.1TR (ENMAX 37) | 2019-02-27 08:00 | 2019-02-28 16:00 | N | N | investigate possible water contamination in tap changer | Transformer |  | investigate possible water contamination in tapchanger. Check reversing switch | For Information Only
ENMAX | 27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13) | 2019-02-27 08:00 | 2019-02-27 18:00 | N | N | HV SW MD maint SW65, SW66, SW67, MD-27.2TR | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B),54s 706N (54s Fort Saskatchewan) | 2019-02-27 08:15 | 2019-02-27 12:45 | N | N | high load move | Line, Circuit Breaker |  | 12.5 meter high load - Mammoet - from Cessco Edmonton to IPL Fort Saskatchewan - travel under 706 Line between structures 46 & 47 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin) | 2019-02-27 08:15 | 2019-02-28 17:45 | N | N | 138kV breaker maintenance (40s804W), 15deg hot spot repair (40s86) | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 127s C1 (127s Bruderheim),127s 33 (127s Bruderheim) | 2019-02-27 08:30 | 2019-02-27 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 253s C1 (253s Blackie),253s 182 (253s Blackie) | 2019-02-27 08:30 | 2019-02-27 13:00 | N | N | digital substation deficiencies resolution | Circuit Breaker, Shunts |  | Digital Substation deficiencies resolution | For Information Only
AESO-SC | EMS | 2019-02-27 09:00 | 2019-02-27 16:00 | N | N | database update | SCInternal |  |  | For Information Only
ALTALINK | 121s 23N (121s Brooks) | 2019-02-27 09:00 | 2019-02-27 16:00 | N | N | maintain 25kV vacuum breaker | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 368s 879 (368s Burdett),244s 3152 (244s Bowmanton),244s 3252 (244s Bowmanton),879L (368s Burdett - 244s Bowmanton) | 2019-02-27 09:00 | 2019-02-27 16:30 | N | Y | techs to troubleshoot and repair supervisory control on 244s879 air break switch | Line, Circuit Breaker |  |  | Pre-Condition, Restricts Generation, Prevents Normal Events, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2019-02-27 23:00 | 2019-02-28 04:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2019-02-28 04:00 | 2019-02-28 07:00 | N | Y | maintenance | Switch |  |  | 240 kV, Restricts Generation
ATCO | 800s 703C (800s Friedenstal) | 2019-02-28 07:00 | 2019-02-28 17:00 | N | N | breaker fail testing | Shunts |  | Breaker fail testing | For Information Only
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2019-02-28 08:00 | 2019-02-28 18:00 | N | N | switch maintenance | Line, Transformer |  | HV SW MD maint SW61, SW62, SW64, SW63, MD-27.1TR | Firm Load Loss, Creates Radial Feeds
ATCO | 796s 702T (796s Nipisi) | 2019-03-01 07:00 | 2019-08-07 16:00 | N | N | switching to isolate 702T and 25kV switch gear bus 2 | Transformer |  | Switching to isolate 702T and 25kV switch gear bus 2 | For Information Only
ATCO | 7L165 (718s Parsons Creek - 933s Tower Road) | 2019-03-02 07:00 | 2019-03-02 17:00 | N | N | arm/insulator/pole changes | Line |  | Arm /Insulator /Pole Changes | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 11 B138-11.82 (ENMAX 11),ENMAX 14 14B138-11.82 (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11) | 2019-03-02 08:00 | 2019-03-03 16:00 | N | N | change damaged pole STR#72 | Line, Circuit Breaker |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 14.3TR (ENMAX 14),14.1TR (ENMAX 14) | 2019-03-02 08:00 | 2019-03-02 18:00 | N | N | maintenance MD-14.3TR, MD-14.1TR. check reversing Sw 14.3TR | Transformer |  |  | Pre-Condition, For Information Only
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib) | 2019-03-03 07:00 | 2019-03-03 17:00 | N | N | arm /insulator /pole changes | Line |  | To do Arm /Insulator /Pole Changes | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 7.1TR (ENMAX 7) | 2019-03-04 08:00 | 2019-03-20 18:00 | N | N | transformer upgrade | Transformer |  | P#1787. 7 sub transformer upgrade. Install oil containment on 7.1TR | For Information Only
SUNCOR | 635EDD-1001 635-752-611 (635EDD-1001) | 2019-03-04 08:00 | 2019-03-04 17:00 | N | N | replace the brick (MU1-1) | Circuit Breaker |  | Replace the Brick (MU1-1) for 635-752-611 Breaker at Central substation 635EDD-1001 | For Information Only
ALTALINK | 580s T2 (580s Sylvan Lake) | 2019-03-04 08:00 | 2019-03-05 16:00 | N | N | forced outage | Transformer
ENMAX | 20.82L (ENMAX 21 - ENMAX 20) | 2019-03-04 08:00 | 2019-03-05 16:00 | N | N | HVB heater retrofit - 21B138-20.82 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2019-03-04 08:00 | 2019-03-18 13:00 | N | N | line protection upgrade | Line |  | Line Protection Upgrade | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2019-03-04 08:00 | 2019-03-04 16:00 | N | Y | repair hotspot on SW84@23sub. 23MD138-23.4TR west phase not closing | Line, Transformer |  | Repair Hotspot on SW84@23sub. 23MD138-23.4TR West phase not closing | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred_1225 (Syncrude Mildred Lake),ML1 (Syncrude Mildred Lake - D05 Syncrude),Mildred Lake 72kV Bus B (Sycrude Mildred Lake) | 2019-03-04 09:00 | 2019-03-17 22:00 | N | Y | preventive maintenance | Bus, Circuit Breaker, Line | "Bus ""B"" Outage for PM Note: Generator G1, G2 and G3 will be Islanded from 72kV (""B""-bus). Transformer T14, T16 and T19 will be isolated." |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
BCH | 5L71 (Mica Creek - Nicola),5L82 (American Creek - Nicola) | 2019-03-04 09:00 | 2019-03-04 13:00 | N | Y | NIC 5CB18 POW testing | Line | BC Outage Peak RC COS: No restriction AB Peak RC COS# : No Restriction | NIC 5CB18 POW testing requires trip and closes to pick up the line for waveform analysis. 5L71/5L82 PY/SY PN OOS OAT to test trip outputs to these breakers. | For Information Only, 500 kV
ALTALINK | 508L (344s Warner - 67s Stirling) | 2019-03-04 09:30 | 2019-03-14 17:30 | N | N | connecting temporary bypass and changing out structures #17 & 18 | Line |  | Connecting temporary bypass and changing out Structures #17 & 18 | For Information Only
ALTALINK | 54L (118s Canmore - 54L172),118s 54W (118s Canmore) | 2019-03-04 10:00 | 2019-03-04 17:45 | N | Y | replace strain insulators on 54L at 118s | Line, Circuit Breaker |  | Replace strain insulators on 54L at 118s | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s 452 (63s Red Deer) | 2019-03-04 10:30 | 2019-03-04 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 492S Monarch | 2019-03-04 11:30 | 2019-03-04 14:00 | N | N | rewiring in the 492s14 JB | Station |  | Techs will be rewiring in the 492s14 JB (only on secondary side (dead side)). Techs will require fuses to be pulled to complete this work. | For Information Only
EPCOR | 805s J2404 (805s Jasper) | 2019-03-04 12:00 | 2019-03-04 16:00 | N | Y | nait tour | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 835L (283s Violet Grove - 835L tap) | 2019-03-04 12:15 | 2019-03-07 17:45 | N | N | component replacements str's range 1-60 and 283s north side east bay | Line |  | Component Replacements Str's Range 1-60 and 283s North Side East Bay | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2019-03-05 07:00 | 2019-03-05 17:00 | N | N | line maintenance | Line |  | Mine Shut-Down( Line Maintenance ) | For Information Only
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2019-03-05 07:00 | 2019-03-05 17:00 | N | N | high load move | Line |  | High load move | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.1TR (ENMAX 36) | 2019-03-05 08:00 | 2019-03-06 16:00 | N | N | tap changer maintenance | Transformer |  | Investigate tapchanger for possible water contamination | For Information Only
ALTALINK | 754L (118s Canmore - 437s Baymag),118s 754E (118s Canmore) | 2019-03-05 08:00 | 2019-03-05 15:45 | N | Y | replace strain insulators | Line, Circuit Breaker |  | Replace strain insulators on 754L at 118s | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2019-03-05 08:00 | 2019-03-05 16:00 | N | N | switch maintenance | Transformer, Line |  | Maintain SW85. GOI for 33.84 will be moved to SW86@33sub while switch is being repaired. | For Information Only
ENMAX | 8.5TR (ENMAX 8) | 2019-03-05 08:00 | 2019-03-05 16:00 | N | N | ground buggy alignment issues | Transformer |  | Corrective. 8GND-8-4 I & R Ground Buggy Alignment Issues | For Information Only
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2019-03-05 08:00 | 2019-03-07 18:00 | N | N | clearance mitigation work | Line |  | Clearance Mitigation work AML to work on 897L/780L Str's 79- 80 - Line is already out of service | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.2TR (ENMAX 21) | 2019-03-05 08:00 | 2019-03-07 16:00 | N | N | relay CPU upgrade | Transformer |  | T-60 Relay CPU upgrade | For Information Only
ALTALINK | 77s 552 (77s Sagitawah) | 2019-03-05 08:00 | 2019-03-07 19:00 | N | N | complete replacement of CT6 | Circuit Breaker |  | Complete Replacement of CT6 (77s552). | Firm Load Loss, Creates Radial Feeds, For Information Only
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2019-03-05 08:00 | 2019-03-07 17:00 | N | Y | pole repairs from 2017 report | Line |  | 7L64 pole repairs from 2017 report | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | Enmax 8 B138-4A0 (ENMAX 8) | 2019-03-06 08:00 | 2019-03-07 18:00 | N | N | corrective - 8B138-4A0 I&R switching issues caused by semaphore contacts not engaging | Circuit Breaker |  | Corrective. 8B138-4A0 I&R Switching Issues Caused by Semaphore Contacts Not Engaging. 8B138-4A0 I&R High Operations on Hydraulic Pump. | Contingency Requires Mitigation, For Information Only
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark M724 (Meadowlark) | 2019-03-06 08:00 | 2019-03-06 17:00 | N | N | disconnect repair | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B),54s 706N (54s Fort Saskatchewan) | 2019-03-06 08:15 | 2019-03-06 12:45 | N | N | high load - travel under 706 Line between structures 46 & 47 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L85 (803s Bullpound - 801s Anderson) | 2019-03-06 09:00 | 2019-03-06 12:00 | N | N | high load move | Line |  | High load move | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Creates Radial Feeds, For Information Only
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-03-06 11:00 | 2019-03-06 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark T3 (Meadowlark) | 2019-03-07 08:00 | 2019-03-07 17:00 | N | N | disconnect repair | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2019-03-07 08:00 | 2019-03-07 16:00 | N | N | hotspot SW32 | Transformer
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-03-07 09:00 | 2019-03-07 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
AESO-SC | SCC | 2019-03-07 10:00 | 2019-03-07 16:00 | N | N | patch deployment for computers in SCC | SCInternal
NRGREEN | NRG3 NRGreen Cogen | 2019-03-07 11:00 | 2019-03-07 17:00 | N | N | AltaLink work on 259s Chickadee RAS | Unit
ALTALINK, EPCOR | 809L (320p Keephills - 510s Sunnybrook) | 2019-03-08 07:00 | 2019-03-18 18:00 | N | Y | stringing new 12L41 overtop | Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK12 (987s Clover Bar - Kennedale) | 2019-03-08 08:00 | 2019-03-08 17:00 | N | N | disconnect repair | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 797L (364s Whitecourt industrial - 268s Whitecourt) | 2019-03-09 08:00 | 2019-03-17 16:00 | N | N | maintenance on 797L between A frame 364S  str 74 | Line |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
BCH | 5L71 (Mica Creek - Nicola),5L72 (Mica Creek - Nicola) | 2019-03-10 11:00 | 2019-03-10 16:00 | N | Y | MCA testing | Line | BC Outage Peak RC COS: 1-00633606 AB Peak RC COS# : 1-00634334 (W>E), 1-00634335 (E>W) | MCA Blackstart Testing with G1 & G2, in association with CM 52944/8-366561 | Limits ATC, For Information Only, 500 kV
ENBRIDGE | Hay Lake North Series Capacitor,Marias South Series Capacitor | 2019-03-10 12:43 | 2019-03-22 14:35 | N | Y | series capacitor banks were removed from service | Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 408L (252s Jarrow - 51s Wainwright),252s 408 (252s Jarrow) | 2019-03-11 07:00 | 2019-03-14 18:00 | N | N | replacement of 138kV CTs at 252s408 | Line, Circuit Breaker |  | Replacement of 138kV CTs at 252s408 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 510S Sunnybrook | 2019-03-11 07:00 | 2019-03-15 18:00 | N | N | station service ss2 outage for connecting cables into switchgear | Station |  | Connecting cables into switchgear | For Information Only
ENMAX | 37.1TR (ENMAX 37) | 2019-03-11 08:00 | 2019-03-12 16:00 | N | N | investigate possible water contamination in tapchanger and check reversing switch | Transformer |  | Investigate possible water contamination in tapchanger. Check reversing switch | For Information Only
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2019-03-11 08:00 | 2019-03-14 16:00 | N | N | HVB heater retrofit - 13B69-13.4TR/13.60 | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK, TRANSALTA | 35s T1 (35s Rundle),35s T3 (35s Rundle),35s8 (35s Rundle),35s41 (35s Rundle),35s Rundle 13.8kV Bus | 2019-03-11 08:00 | 2019-03-18 18:00 | N | Y | 13.8 kV bus outage for breakers 35s1,35s3,35s4 replacement | Switch, Transformer, Bus |  | 13.8 kV bus outage for breakers 35s1,35s3,35s4 replacement. Bus outage for breakers 35s1,35s3,35s4 control wiring upgrades and CT and PT testing. | Restricts Generation
ENMAX | ENMAX 65 B240-D135 (ENMAX 65) | 2019-03-11 08:00 | 2019-03-12 16:00 | N | Y | remediate bird mess inside insulating blankets | Circuit Breaker |  | Remediate Bird Mess Inside Insulating Blankets [AVANTIS]. | 240 kV, Contingency Requires Mitigation
ENMAX | 32.1TR (ENMAX 32) | 2019-03-11 08:00 | 2019-03-11 16:00 | N | N | hotspot | Transformer |  | hotspot SW23 | For Information Only
ENMAX | 41.1TR (ENMAX 41) | 2019-03-11 08:00 | 2019-03-15 16:00 | N | N | CT Addition | Transformer |  | HV CT Addition | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2019-03-11 08:00 | 2019-03-30 16:00 | N | N | overcurrent relay replacement | Transformer |  |  | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale),72NK23 (Kennedale - Namao),Kennedale K724 (Kennedale),Kennedale K723 (Kennedale) | 2019-03-11 08:00 | 2019-03-11 17:00 | N | N | disconnect Repair | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 15s T1 (15s Fort Macleod) | 2019-03-11 09:30 | 2019-03-14 12:00 | N | N | install bird coverup on 25kV bus modified equipment, replace SS1 transformer, install 15s12 12A drop out fuse for SS1, close open point "D" | Transformer |  | Install Bird Coverup on 25kV Bus modified equipment, Replace SS1 transformer, Install 15s12 12A Drop out Fuse for SS1, Close Open Point "D" | For Information Only
AESO-SC | CROW | 2019-03-11 10:00 | 2019-03-11 11:00 | N | N | CROW production migration: PDC to SDC | SCInternal |  |  | For Information Only
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2019-03-11 10:00 | 2019-03-20 17:00 | N | Y | crossarm replacements | Line |  | 7L63 crossarm replacements | Pre-Condition
ALTALINK | 310p 1252 (310p Sundance) | 2019-03-11 10:00 | 2019-03-14 15:00 | N | Y | migrate and commission all 310P1252 associated breaker and breaker fail alarms, status, controls, metering and remote access to new RTU and LAN | Circuit Breaker |  | Migrate and commission all 310P1252 associated breaker and breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | 240 kV
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2019-03-11 11:00 | 2019-03-19 16:00 | N | N | T1 & T2 138kV bushings and LAs | Transformer |  |  | For Information Only
ALTALINK | 310p 452 (310p Sundance) | 2019-03-11 11:00 | 2019-03-21 12:00 | N | Y | breaker fail protection replacement | Circuit Breaker |  |  | 240 kV
ALTALINK | 225L (67s Stirling - 225AL tap),67s 225 (67s Stirling) | 2019-03-11 11:30 | 2019-03-12 16:30 | N | N | replace 225L SCADA meter | Circuit Breaker, Line |  | Techs require breaker 67s225 out of service to replace 225L SCADA meter. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L794 (157s Lac La Biche - 819s Whitby Lake) | 2019-03-11 12:00 | 2019-03-16 17:00 | N | Y | 7L794 pole changes | Line |  | 7L794 Pole Changes | Pre-Condition, Overload
ALTALINK | 835L (384s Keystone - 835L tap) | 2019-03-11 12:15 | 2019-03-14 17:45 | N | N | component replacements | Line |  | Component Replacements Str's Range 107-271 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 575s T1 (575s Sundre),719L (575s Sundre - 378s Shell Caroline) | 2019-03-11 13:00 | 2019-03-14 17:00 | N | Y | replace 138kV VTs (575s20), maintain 575s719N | Transformer, Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.82L (ENMAX 22 - ENMAX 13) | 2019-03-11 13:00 | 2019-03-11 15:00 | N | N | construction for 138kV BT at 22sub | Line |  | Construction for 138kV BT at 22sub. Outage required to unshort BD CTs | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 22 | 2019-03-11 13:00 | 2019-03-23 18:00 | N | N | SW88 outage for construction of 138kV BT | Station |  | Construction for 138kV BT at 22sub. Isolate 22PT138-Z32 for commissioning tests | For Information Only
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2019-03-12 07:00 | 2019-04-15 18:00 | N | Y | spacer and damper replacement on structures # 4 - 191 | Line |  |  | For Information Only, 500 kV
ALTALINK | 77s 652 (77s Sagitawah) | 2019-03-12 08:00 | 2019-03-14 19:00 | N | N |  | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2019-03-12 08:00 | 2019-03-14 16:00 | N | N | replace water valve near the line | Line |  | contractor hydrovaccing near line in order to replace water valve | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | EX1-01 (879s Scotford Upgrader - 402s Scotford Expansion) | 2019-03-12 08:00 | 2019-03-15 16:00 | N | N | relay testing | Line |  | 402S - EX1-01L 87 RELAY MICROPROCESSOR BASED COMPLETE We will be testing multiple relays at both ends of the lines (402S and 879S) At 402S: -EX1-01L 21A -EX1-01L 21B -552 50BF -652 50BF At 879S: -EX1-01L 21A -EX1-01L 21B -152 50BF | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
MONTANA | MATL (120s Picture Butte - Montana) | 2019-03-12 08:00 | 2019-03-14 16:00 | N | Y | align with 1201L outage | Line | PEAK COS outage ID:1-00627126 PEAK COS path de-rate ID:1-00627127 (N-S) :1-00627128 (S-N) | Install Oil filter on Tx18413 (520sT1) | 240 kV, Pre-Condition, Limits ATC
EPCOR | 805s C1 (805s Jasper),805s J2408 (805s Jasper) | 2019-03-12 08:00 | 2019-03-12 17:00 | N | Y | breaker repair | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ENMAX | 33.1TR (ENMAX 33) | 2019-03-12 08:00 | 2019-03-12 12:00 | N | N | line protection upgrade | Transformer |  | Line Protection Upgrade. Settings and wiring changes required. | For Information Only
ALTALINK | 1201L (520s Bennett - BCH Cranbrook),520s T1 (520s Bennett) | 2019-03-12 08:00 | 2019-03-14 16:00 | Y | Y | install oil filter on 520sT1 | Line, Transformer | Peak RC COS outage ID: 1-00627123 Peak RC Path Derate ID: 1-00627124 (E>W), 1-00627125 (W>E) | install oil filter on Tx18413 | Limits ATC, 500 kV
ALTALINK | 283S Violet Grove | 2019-03-12 08:30 | 2019-03-12 16:30 | N | N | Fortis request to replace flashed over switch cubicle 130LLOU | Station |  | Fortis request.To replace flashed over switch cubicle 130LLOU (breaker 283s130E). | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel),930s 702T (930s Arcenciel) | 2019-03-12 08:30 | 2019-03-12 12:00 | N | Y | remove bird nests on the structures | Shunts, Transformer |  | To remove bird nests on the structures in the 13.8 KV bus work around 406R and 402TD1. | Pre-Condition
ATCO | 828s 507C1 (828s Sulphur Point),828s 507C2 (828s Sulphur Point),828s 507 (828s Sulphur Point) | 2019-03-12 09:30 | 2019-03-15 17:30 | N | N | CT ratio change for breaker 507 | Shunts, Circuit Breaker |  | BKR 507 CT ratio change 507C1 and 507C2 remain out of service for duration of work. | Pre-Condition
AESO-SC | Computer | 2019-03-12 10:00 | 2019-03-12 16:00 | N | N | Patch Deployment for Computers in BUCC Control Room | SCInternal
ENMAX | 33.2TR (ENMAX 33) | 2019-03-12 12:00 | 2019-03-12 16:00 | N | N | line protection upgrade | Transformer |  | Line Protection Upgrade. Settings and wiring changes required. | For Information Only
ENMAX, ALTALINK | 1080L (ENMAX 65 - ENMAX 25) | 2019-03-12 14:53 | 2019-06-24 10:00 | N | Y | forced outage due to field cable | Line |  |  | 240 kV
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2019-03-13 07:00 | 2019-03-14 17:00 | N | Y | DFR Upgrade | Line |  |  | 240 kV, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 22.3TR (ENMAX 22) | 2019-03-13 08:00 | 2019-03-13 12:00 | N | N | construction for 138kV BT | Transformer |  | Construction for 138kV BT at 22sub. Outage required to unshort bus diff CTs | For Information Only
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2019-03-13 08:00 | 2019-03-13 16:00 | N | Y | Counter Repair Near and Center Phases | Circuit Breaker |  |  | 240 kV
ALTALINK | 463L (15s Fort Macleod - 463L46) | 2019-03-13 08:00 | 2019-03-13 17:00 | N | Y | replace 15s185 VT JB | Line |  |  | Over/Under Voltage, Restricts Generation, Creates Radial Feeds
ATCO | 757s 701T (757s Battle River),757s 701 (757s Battle River) | 2019-03-13 08:00 | 2019-03-14 16:00 | N | N | change this CT wiring and test the circuit | Transformer, Circuit Breaker |  | ATCO engineering would like to extend the zone on the 701T differential relay to cover 701 breaker after we get 912T back in service. Crew has been asked to change this CT wiring and test the circuit. | Pre-Condition, Over/Under Voltage
ENMAX | 22.1TR (ENMAX 22) | 2019-03-13 12:00 | 2019-03-20 16:00 | N | N | construction for 138kV BT and NGR installation | Transformer |  | Construction for 138kV BT at 22sub. Outage required to unshort bus diff CTs. NGR Installation. | For Information Only
ALTALINK | 85L (35s Rundle - 85L12),35s 85 (35s Rundle) | 2019-03-13 13:00 | 2019-03-13 13:30 | N | Y | MPLS node upgrade | Circuit Breaker, Line |  | Visibility of the 35s85 breaker open as part of the 35s MPLS node upgrade. Breaker needs to be opened as both TPR circuits will be out of service | Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 162s 138-RB83 (162s Beddington) | 2019-03-14 08:30 | 2019-03-14 12:00 | N | N | top up oil level in dashpot | Circuit Breaker |  | Corrective. Top up oil level in dashpot on 162B138-RB83 | Contingency Requires Mitigation, For Information Only
VISIONREQ | 354s Summerview RTU/SCADA | 2019-03-14 10:00 | 2019-03-14 10:45 | N | N | server updates | Terminal Equipment |  | TransAlta is requesting a 45 minute communication outage to the AESO for server updates on March 14, 2019 from 10:00 to 10:45 at Summerview 1 The Control Center will still have control and visibility of the site. WFMS to Summerview 2 will not be affected. | Affects Visibility
ENMAX | 162s 138-RB82 (162s Beddington) | 2019-03-14 12:00 | 2019-03-14 16:00 | N | N | top up oil level in dashpot | Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 15s T2 (15s Fort Macleod) | 2019-03-14 12:01 | 2019-03-15 17:00 | N | N | install bird coverup on T2 low side and 25kV cable frame and replace 15s5 fuses | Transformer |  | Install Bird Coverup on T2 low side and 25kV Cable Frame, Replace 15s5 Fuses | For Information Only
ALTALINK | 835L (283s Violet Grove - 835L tap) | 2019-03-15 07:00 | 2019-03-17 18:00 | N | N | component replacements Str's range 1-60 and 283s North side east bay | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2019-03-15 07:15 | 2019-03-19 17:00 | N | N | high loads | Line |  | Two 19.5 meter high loads from Engie Com east of Fort Saskatchewan to IPL Fort Saskatchewan to travel under 706 Line between structures 46 & 47 on the temporary bypass road west of RR 220. | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.3TR (ENMAX 38) | 2019-03-15 08:00 | 2019-03-15 16:00 | N | N | correct LTC filter unit oil leak | Transformer |  | Corrective. 38.3TR LTC Filter unit - Oil leak. | For Information Only
DAISHOWA | 147S Daishowa Plant | 2019-03-16 09:00 | 2019-03-16 12:30 | N | N | possible ADAMS dispatch interruption | Station |  |  | For Information Only
EPCOR | 816s P2402 (816s Petrolia),816s P2403 (816s Petrolia),1055L (816s Petrolia - 629s Argyll Transfer Station),814s B2406 (814s Bellamy),814s B2407 (814s Bellamy) | 2019-03-18 07:00 | 2019-03-19 17:00 | N | Y | DFR upgrade | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark T2 (Meadowlark) | 2019-03-18 07:00 | 2019-03-29 17:00 | N | N | DGA | Transformer |  |  | For Information Only
SUNCOR | 29PL9-13 (29EDD-34 - 29EDD-65) | 2019-03-18 08:00 | 2019-03-19 11:00 | N | Y | broken strand repair | Line | The outage is back early informed by SC on Mar 19 at 10:42am. | Broken strand repair on 29PL9-12 Will update elements not available at a later date | 240 kV
ENMAX | 3.84L (ENMAX 13 - ENMAX 3) | 2019-03-18 08:00 | 2019-03-21 16:00 | N | N | HVB heater retrofit | Line |  | HVB heater retrofit - 13B138-3.84 | Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28) | 2019-03-18 08:00 | 2019-03-22 16:00 | N | N | replace X3 bushing | Transformer |  |  | For Information Only
EPCOR | Hardisty T3 (Hardisty) | 2019-03-18 08:00 | 2019-08-01 10:00 | N | N | transformer replacement | Transformer |  |  | For Information Only
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2019-03-18 08:00 | 2019-03-19 16:30 | N | Y | clearance mitigation | Line |  | 9L59- GOI permit for Clearance Mitigation 6 more structures left to change for clearance Mitigation. | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | Hardisty T3 (Hardisty),72CH9 (Hardisty - 987s Clover Bar) | 2019-03-18 08:00 | 2019-03-19 17:00 | N | N | remove transformer protection | Transformer, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2019-03-18 08:00 | 2019-03-22 18:00 | N | N | HVB heater retrofit | Transformer, Line |  | HVB heater retrofit - 36B69-16.63/36.5TR. | Pre-Condition
BCH | 5L76 (Ashton Creek - Nicola) | 2019-03-18 09:00 | 2019-03-18 17:00 | N | Y | NIC 5CB4 and 5CB14 POW testing | Line | BC Outage Peak RC COS: Not required. AB Peak RC COS# : Not required. | NIC 5CB4 and 5CB14 POW testing requires trip and closes to pick up the line for waveform analysis. Each CB will be Operated one at a time. 5L76 PY/SY PN OOS OAT to test trip outputs to these breakers. NIC 5CB13 POW testing requires trip and closes to pick up the line for waveform analysis. 5L72 PY/SY PN OOS OAT to test trip outputs to these breakers.
ALTALINK | 283s T2 (283s Violet Grove) | 2019-03-18 09:30 | 2019-03-20 12:00 | N | N | install bird cover up. | Transformer |  | T2 Outage to install bird cover up on new 283s489 and 283s589 MODs, 25kV Cross Bus, and temporary bus-bypass cables. | For Information Only
SHELL | 402s 252 (402s Scotford Expansion) | 2019-03-18 10:00 | 2019-03-20 12:00 | N | N | 50BF relay microprocessor based testing | Circuit Breaker |  | 402S - 252 50BF RELAY MICROPROCESSOR BASED COMPLETE Testing 252 50BF protective relay We will be taking a T&O on breaker 252. The breaker will be switched out of service in the morning and returned back to normal at the end of each day. While the breaker is out of service we will be testing the breaker fail relay 252 | Contingency Requires Mitigation
ALTALINK | 310P 234N (310p Sundance) | 2019-03-18 10:30 | 2019-03-21 16:30 | N | N | migrate and commission all 310P234N protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. | Circuit Breaker |  | Migrate and commission all 310P234N protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. | Pre-Condition
ALTALINK | 305s T1 (305s Acheson) | 2019-03-18 11:45 | 2019-04-01 16:45 | N | N | replace 305s394N & 305s268E with new vacuum dead tank breakers and install bird cover up. replace arresters on feeders. | Transformer |  | Replace 305s394N & 305s268E with new vacuum dead tank breakers and install bird cover up. Replace the arresters on feeder 394L and 268L | For Information Only
ALTALINK | 854L (39s Bickerdike - 854L228A) | 2019-03-18 12:15 | 2019-03-21 17:45 | N | N | component replacements Str 220. | Line |  | Component replacements Str 220. | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2019-03-18 13:00 | 2019-03-18 15:00 | N | N | line protection upgrade and functional check | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 859s 701T (859s Primrose),859s701TD1 (859s Primrose) | 2019-03-19 04:00 | 2019-03-25 13:00 | N | N | safety clearance | Transformer, Switch |  |  | Restricts Generation, For Information Only
SHELL, AIRLIQUIDE | ALC03L (408s Air Liquide Scotford - 402s Scotford Expansion),402s 352 (402s Scotford Expansion),402s 452 (402s Scotford Expansion) | 2019-03-19 08:00 | 2019-03-20 16:00 | N | N | 50BF relay microprocessor based complete testing | Circuit Breaker, Line |  | 402S - 352 50BF RELAY MICROPROCESSOR BASED COMPLETE Testing 352 50BF protective relay We will be taking a T&O on breaker 352. The breaker will be switched out of service in the morning and returned back to normal at the end of each day. While the breaker is out of service we will be testing the breaker fail relay 352 402S - 452 50BF RELAY MICROPROCESSOR BASED COMPLETE Testing 452 50BF protective relay We will be taking a T&O on breaker 452. The breaker will be switched out of service in the morning and returned back to normal at the end of each day. While the breaker is out of service we will be testing the breaker fail relay 452 This work will not overlap with other planned work, one will be completed before the next one is started | Contingency Requires Mitigation
ENMAX | 3.4TR (ENMAX 3),3.84L (ENMAX 13 - ENMAX 3) | 2019-03-19 08:00 | 2019-03-19 16:00 | N | N | whip adjustment for 3MD138-3.4TR | Line, Transformer |  | 3.84L - 3MD138-3.4TR - east whip not reset - need to adjust | For Information Only
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2019-03-19 08:00 | 2019-03-20 17:00 | N | Y | to install DLR systems/wind and weather monitors | Line |  | To install DLR Systems/Wind and weather monitors | Pre-Condition
ALTALINK | 77s 752 (77s Sagitawah) | 2019-03-19 08:00 | 2019-03-21 19:00 | N | N | complete replacement of CT9 | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2019-03-19 08:00 | 2019-03-21 16:00 | N | Y | 50L vault inspection | Line |  |  | Pre-Condition
ALTALINK | 788L (157s Lac La Biche - 788L Tap) | 2019-03-19 08:15 | 2019-03-19 12:45 | N | N | high load move | Line |  | High Load Move for Neufeld Building Movers - 8.72 meters high - moving from Lloydminster to Elinor Lake Resort - NW-20-65-11-4; travel under 788 Line between structures 7 & 8 over hwy 55/36 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 42s T2 (42s Sarcee),42s 60 (42s Sarcee) | 2019-03-19 08:30 | 2019-03-19 16:00 | N | Y | maintain 138 kV SF6 breaker | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 310P 234N (310p Sundance) | 2019-03-19 08:30 | 2019-03-19 17:30 | N | N | 69 kV breaker maintenance | Circuit Breaker |  |  | Pre-Condition, For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2019-03-19 09:00 | 2019-03-19 11:00 | N | N | line protection upgrade and functional check | Line |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | DDST | 2019-03-19 09:00 | 2019-03-22 17:00 | N | N | Q1 integration | SCInternal |  |  | For Information Only
AESO-SC | OATI | 2019-03-19 18:00 | 2019-03-19 19:00 | N | N | inter-site transfer business continuity drill | SCInternal
ALTALINK, EPCOR | 816s P2403 (816s Petrolia),816s P2404 (816s Petrolia),1139L (367s Harry Smith - 816s Petrolia) | 2019-03-20 07:00 | 2019-03-21 17:00 | N | Y | DFR upgrade | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p Sundance 240kV Bus B | 2019-03-20 08:00 | 2019-03-20 18:30 | N | Y | breaker fail trip testing | Bus |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 455L (149s Nisku - 289s Saunders Lake),149s 455 (149s Nisku) | 2019-03-20 08:30 | 2019-03-21 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker, Line |  |  | Pre-Condition
ALTALINK | 42s C1 (42s Sarcee),42s 1652 (42s Sarcee) | 2019-03-20 08:30 | 2019-03-20 16:00 | N | N | maintain breaker | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 790L (434s Stony Plain - 790L62) | 2019-03-20 08:45 | 2019-03-21 17:45 | N | N | 138kV breaker, switch maintenance, replace cracked fitting on blade | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | EMS | 2019-03-20 09:00 | 2019-03-20 16:00 | N | N | database update | SCInternal |  |  | For Information Only
ALTALINK | 118s C1 (118s Canmore) | 2019-03-20 09:00 | 2019-03-20 16:30 | N | N | perform changes comms settings | Shunts |  | Techs will be onsite to perform changes to SR760V4 50/51/27/59/C1 C1 Comms settings. | For Information Only
BCH | 5L72 (Mica Creek - Nicola) | 2019-03-20 09:00 | 2019-03-20 13:00 | N | Y | NIC 5CB13 POW testing | Line | BC Outage Peak RC COS: not required AB Peak RC COS# : not required | NIC 5CB13 POW testing requires trip and closes to pick up the line for waveform analysis. 5L72 PY/SY PN OOS OAT to test trip outputs to these breakers. | Limits ATC, 500 kV
ALTALINK | 283s T1 (283s Violet Grove) | 2019-03-20 13:00 | 2019-03-21 14:00 | N | N | install bird cover up | Transformer |  | T1 Outage to install bird coverup on new 283s40 hook switch and bypass cables. | Pre-Condition, For Information Only
Medicine Hat | MH69s2 MH69_212 (MH69s2 North Industrial),MH69s5 MH69_510 (MH69s5 NE Crescent Height),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2019-03-21 07:00 | 2019-03-21 15:00 | N | N | emergency replace burnt dead-end insulators | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 54L (118s Canmore - 54L172) | 2019-03-21 07:00 | 2019-03-22 18:00 | N | N | urgent repair to replace structure #169 | Line |  |  | Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
AESO-SC | Excitation and Governor Control Systems | 2019-03-21 08:00 | 2019-04-04 16:00 | N | N | NX01 gas turbine control systems replacement. ISD March 28, 2019 | SCInternal
ALTALINK, Lethbridge | 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2019-03-21 08:00 | 2019-03-21 16:00 | N | Y | replace substation transformer | Line |  |  | Pre-Condition
ENMAX | 34.1TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2019-03-21 08:00 | 2019-03-21 16:00 | N | N | rectify secondary cable grounded on both ends - 34.1TR | Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 7 B138-7BT3 (ENMAX 7) | 2019-03-21 08:00 | 2019-04-04 16:00 | N | N | ISD March 28, 2019 | Circuit Breaker
AESO-SC | Control System | 2019-03-21 08:00 | 2019-04-04 16:00 | N | N | Primrose #1 (PR1) AVR controller upgrade. ISD March 28, 2019 | SCInternal
Lethbridge | 813L (241s Lethbridge Uplands - 146s Lethbridge MacDonald) | 2019-03-21 08:00 | 2019-03-21 16:00 | N | N | replace substation transformer | Line |  |  | Pre-Condition
AESO-SC | MARGO | 2019-03-21 09:00 | 2019-03-21 15:00 | N | N | Q1 release | SCInternal |  |  | For Information Only
ALTALINK | 310p 552 (310p Sundance) | 2019-03-21 13:00 | 2019-03-21 16:00 | N | Y | breaker fail trip testing from 310p452 | Circuit Breaker |  |  | 240 kV, Pre-Condition
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock),939s 1213R (939s Livock),510s R3 (510s Sunnybrook) | 2019-03-22 08:00 | 2019-04-05 16:00 | N | N | ISD Mar 29, 2019 | Line, Shunts
AESO-SC | DDST,DT,ETS,MARGO | 2019-03-22 10:00 | 2019-03-22 12:00 | N | N | critical aApplication migration: primary data centre to secondary data centre | SCInternal |  |  | For Information Only
ENMAX | 22.2TR (ENMAX 22),22.81L (ENMAX 22 - ENMAX 39) | 2019-03-23 08:00 | 2019-03-23 18:00 | N | N | construction for 138kV BT, spring substation washing and maintenance | Line, Transformer |  | Construction for 138kV BT at 22sub. Remove bus from between SW84, SW85. Energize 22B138-22BT8. Energize 22PT138-Z32. Special energization instructions required. Spring substation washing. MD 22.2TR center whip not reset -adjust next outage | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7) | 2019-03-23 08:00 | 2019-03-31 18:00 | N | Y | P1787 - 7 sub transformer upgrade | Line, Transformer | P#1787. 7 sub transformer upgrade Phase 3. Line Protection Upgrade. Eneergize new 7B138-7BT3. Special energization instructions required. |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27) | 2019-03-24 08:00 | 2019-03-24 18:00 | N | N | hot spot jaw side SW67 | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 754s 702C (754s Ksituan River) | 2019-03-25 07:00 | 2019-04-01 17:00 | N | N | attach new 703T bay and rebuild 25 kV bus | Shunts |  | Attach new 703T bay and rebuild 25 kv bus. Transfer 5L368 & 5L440 to 5L438 - Settings changes required. 702C Cap Bank OOS -------- Load Transfer -------- 754S 5L368 Peak Load = 13.45 MVA 754S 5L440 Peak Load = 4.27 MVA 754S 5L438 Peak Load = 6.718 MVA 754S 5L368 Relay Settings: 17.3 MVA C09 relay 754S 5L440 Relay Settings: 12.1 MVA C09 relay 754S 5L438 Relay Settings: 13.9 MVA C09 relay -------- Load Transfer -------- | Pre-Condition, Over/Under Voltage
EPCOR | 816s T1 (816s Petrolia), 816s P2402 (816s Petrolia), 816s P2401 (816s Petrolia) | 2019-03-25 07:00 | 2019-03-26 17:00 | N | Y | DFR upgrade | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
Medicine Hat | MH69s5 MH69_510 (MH69s5 NE Crescent Height),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2019-03-25 07:00 | 2019-03-26 12:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 22.1TR (ENMAX 22),22.3TR (ENMAX 22),13.82L (ENMAX 22 - ENMAX 13),ENMAX 13 B138-13.82 (ENMAX 13) | 2019-03-25 08:00 | 2019-03-25 18:00 | N | N | construction for 138kV BT at 22sub and spring substation washing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO | 789L (818s Winefred - 1034s Margie - 898s Heart Lake) | 2019-03-25 08:00 | 2019-04-07 16:00 | N | N | 1034s Margie energization ISD: Apr 1, 2019 | Line |  |  | For Information Only
ENMAX | 12.2TR (ENMAX 12) | 2019-03-25 08:00 | 2019-04-05 16:00 | N | N | transformer differential relay replacement | Transformer |  | Transformer Differential Relay Replacement, dev. 90 replacement and Auto switching | For Information Only
ENMAX | Enmax 8 B138-1A0 (ENMAX 8) | 2019-03-25 08:00 | 2019-03-28 00:01 | N | N | suspected loose internal ground 8SW1A51 | Circuit Breaker |  | Corrective. Suspected loose internal ground 8SW1A51 [AVANTIS]. 1.85L outage required on return to service | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 754s 703T (754s Ksituan River) | 2019-03-25 08:00 | 2019-04-08 16:00 | N | N | 754s Ksituan River capacity increase ISD: Apr 01, 2019 | Transformer
ATCO | 824s 701 (824s Fieldgate),824s701A (824s Fieldgate) | 2019-03-25 08:00 | 2019-04-08 16:00 | N | N | ISD April 1, 2019. Replacement of 824s701TCS with new switch & breaker. | Circuit Breaker, Switch
AESO-SC | EMS | 2019-03-25 09:00 | 2019-03-25 16:00 | N | N | CIP-007 Annual Password change AE1 Console Admin on Domain Account - BUCC | SCInternal |  |  | For Information Only
ALTALINK | 310p 1852 (310p Sundance) | 2019-03-25 10:00 | 2019-03-28 16:00 | N | Y | migrate and commission breaker and breaker fail alarms, status, controls, metering and remote access to new RTU and LAN | Circuit Breaker |  | Migrate and commission all 310P1852 associated breaker and breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. | 240 kV, Contingency Requires Mitigation
EPCOR | Namao T3 (Namao) | 2019-03-25 10:00 | 2019-04-30 17:00 | N | N | emergency repair. | Transformer |  | Emergency repair. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 575s T1 (575s Sundre) | 2019-03-25 13:00 | 2019-03-28 17:00 | N | N | replace 25kV CB 575s2048X, replace 25kV LAs (575s2048X, 575s283N & 575s147N) | Transformer |  |  | For Information Only
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2019-03-25 18:00 | 2019-04-06 10:00 | N | Y | clearance issue | Line |  |  | Pre-Condition, Restricts Generation, Prevents Normal Events, Creates Radial Feeds
ALTALINK | 854L (1012s Deer Hill - 854L228) | 2019-03-26 07:15 | 2019-03-28 12:15 | N | N | component replacements str 220 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 113L (20s Ghost - 33s Spray),20s 113 (20s Ghost),33s 113 (33s Spray) | 2019-03-26 07:45 | 2019-03-26 16:45 | N | N | breakers maintenance | Line, Circuit Breaker |  | Maintain 33s113 & 20s113 breakers | For Information Only
ALTALINK | 836L (61s Lodgepole - 283s Violet Grove),61s 836N (61s Lodgepole) | 2019-03-26 08:00 | 2019-03-28 19:00 | N | Y | replace CTs | Line, Circuit Breaker |  |  | Pre-Condition
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2019-03-26 08:00 | 2019-03-26 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2019-03-26 08:00 | 2019-03-27 17:00 | N | N | changing cross-arms | Line |  | CHANGING CROSS-ARMS ON 7L53 | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 834s 708 (834s Wesley Creek) | 2019-03-26 09:00 | 2019-03-26 15:30 | N | N | leak detection and repair | Circuit Breaker |  | Leak Detection and Repair with ABB Manufacturer representative on Site, 708 OOS for the Duration of the work | Overload, Contingency Requires Mitigation
AESO-SC | EMS | 2019-03-26 10:00 | 2019-03-26 11:00 | N | N | oracle patching - tibrepp database | SCInternal |  |  | For Information Only
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2019-03-26 12:00 | 2019-03-26 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Medicine Hat, CMH | MH69s3 MH69_308 (MH69s3 South Ridge),MH69s5 MH69_502 (MH69s5 NE Crescent Height),MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2019-03-26 12:00 | 2019-03-28 14:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
AESO-SC | DDST,DT,ETS,MARGO | 2019-03-26 14:00 | 2019-03-26 16:00 | N | N | critical application migration: SDC to PDC | SCInternal
ALTALINK | 76L (115s Mt. Allan - 33s Spray),33s 76 (33s Spray) | 2019-03-27 08:00 | 2019-03-27 16:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | Maintain 138kV SF6 gas breaker | Pre-Condition, For Information Only
ENMAX | 20.3TR (ENMAX 20),ENMAX 20 B138-20.82 (ENMAX 20),20.82L (ENMAX 21 - ENMAX 20) | 2019-03-27 08:00 | 2019-03-27 18:00 | N | N | spring substation washing | Line, Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | CROW | 2019-03-27 09:00 | 2019-03-27 15:00 | N | N | Q1 2019 release | SCInternal |  | OMCS CROW ¦ INTEG ¦ OST SE Q1 2019 Release
ALTALINK | 528S Blue Trail Wind Farm | 2019-03-27 10:00 | 2019-03-27 12:00 | N | N | DVAR outage | Station |  |  | For Information Only
TRANSALTAW | 418s Ardenville DVAr | 2019-03-27 12:00 | 2019-03-27 14:00 | N | N | DVAR outage | Shunts |  |  | For Information Only
ENMAX | 8.1TR (ENMAX 8),8.2TR (ENMAX 8),1.85L (ENMAX 1 - ENMAX 8) | 2019-03-27 23:00 | 2019-03-27 23:59 | N | N | suspected loose internal ground | Line, Transformer |  | Corrective. Suspected loose internal ground 8SW1A51 [AVANTIS]. Outage required to return 8B138-1a0 to service | For Information Only
EPCOR | 816s T2 (816s Petrolia),816s P2404 (816s Petrolia),816s P2405 (816s Petrolia) | 2019-03-28 07:00 | 2019-03-29 17:00 | N | Y | upgrade DFR | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 14.3TR (ENMAX 14) | 2019-03-28 08:00 | 2019-03-29 16:00 | N | N | correctives | Transformer |  | Corrective. 14.3TR Investigate oil leak in secondary cable compartment. | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2019-03-28 08:00 | 2019-03-28 12:00 | N | N | spring substation washing | Line, Transformer |  |  | For Information Only
ALTALINK | 84L (35s Rundle - 33s Spray),33s 84 (33s Spray) | 2019-03-28 08:00 | 2019-03-28 16:00 | N | N | maintain 138kV SF6 gas breaker | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
AESO-SC | Northwestern Energy BUCC test | 2019-03-28 08:00 | 2019-03-28 12:00 | N | N | BUCC test | Station |  |  | For Information Only
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2019-03-28 08:30 | 2019-03-28 12:00 | N | N | emergency remove the object wrapped up around the conductor | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
VISIONREQ | 354S Summerview | 2019-03-28 10:00 | 2019-03-28 12:00 | N | N | DVAR outage | Station |  |  | For Information Only
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),26.81L (ENMAX 54 - ENMAX 26),32.83L (ENMAX 32 - ENMAX 40) | 2019-03-28 12:00 | 2019-03-28 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 4G (310p Sundance) | 2019-03-29 07:00 | 2019-04-17 17:00 | N | Y | turnaround | Switch |  |  | Restricts Generation
ATCO, ALTALINK | 789L (818s Winefred - 898s Heart Lake) | 2019-03-29 08:00 | 2019-04-01 11:00 | N | Y | connect new 789BL to 789L (Close Open Point 'A') | Line |  |  | For Information Only
ATCO, ALTALINK | 1117L (898s Heart Lake - 167s Ipiatik Lake) | 2019-03-29 08:00 | 2019-04-01 11:00 | N | Y | required due to proximity for connecting new 789BL to 789L | Line |  |  | 240 kV, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.1TR (ENMAX 34),21.61L (ENMAX 21 - ENMAX 34) | 2019-03-29 08:00 | 2019-03-29 16:00 | N | N | spring substation washing | Line, Transformer |  | Spring Substation Washing. Check reversing switch | Firm Load Loss, Creates Radial Feeds
ENMAX | 2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9),9.2 TR (ENMAX 9),9.3 TR (ENMAX 9) | 2019-03-30 08:00 | 2019-03-30 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 902L (19s Wabamun - 310p Sundance),310p 1052 (310p Sundance),310p 1152 (310p Sundance),310p 752 (310p Sundance),310p 852 (310p Sundance),338s 452 (338s Cherhill),1046L (338s Cherhill - 19s Wabamun),338s 552 (338s Cherhill) | 2019-03-30 08:00 | 2019-04-06 10:50 | N | Y | closing temporary open point 'A', 'B' & 'C' and removing temporary bypass between 902L & 1046L | Line, Circuit Breaker |  | Valard will be closing temporary Open Point 'A', 'B' & 'C' and removing temporary bypass between 902L & 1046L | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2019-03-31 08:00 | 2019-03-31 13:00 | N | N | Spring substation washing | Line, Transformer
EPCOR | 72LH8 (Hardisty - 803s Lambton) | 2019-03-31 08:00 | 2019-04-05 15:00 | N | N | transformer replacement | Line
ENMAX | 31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9),138-31.CAP (ENMAX 31) | 2019-03-31 13:00 | 2019-03-31 18:00 | N | N | Spring substation washing & heck reversing switch | Transformer, Line, Circuit Breaker |  |  | Pre-Condition
Medicine Hat | MH69s3 MH69_311 (MH69s3 South Ridge),MH69s3 T31 (MH69s3 South Ridge),MH69s3 MH69_3S3-M (MH69s3 South Ridge) | 2019-04-01 07:00 | 2019-04-02 12:00 | N | N | breaker maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 233s T2 (233s Beamer) | 2019-04-01 07:45 | 2019-04-10 17:45 | N | N | replace transformer with original | Transformer |  |  | For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2019-04-01 08:00 | 2019-04-18 16:00 | N | N | HV CT addition, maintenance and repair | Transformer |  | HV CT addition. 15.2TR H3 bushing oil on top skirt and bushing cap (Close WO out if no longer valid). 15.2TR Secondary bushing leak repair follow | For Information Only
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2019-04-01 08:00 | 2019-04-12 09:30 | N | N | replace ZE2-E1 bus differential relay | Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 Millennium,29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island),29EDD-1 29EDD1S1452 (29EDD-1 Millennium),29EDD-1 29EDD1S1352 (29EDD-1) | 2019-04-01 08:00 | 2019-04-12 14:00 | N | Y | 5 years maintenance | Line, Circuit Breaker, Station |  | Perform maintenance and testing (5 year) breakers, CVT and surge arrestors: Varies from 4 to 16 hours depending on the stage of work. | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2019-04-01 08:00 | 2019-04-01 18:00 | N | Y | spring substation washing | Line, Transformer |  | Spring Substation Washing 28.80, 28.2, Z31. HV SW maint SW80, SW81, SW82, SW86, MD-28.2TR. Original outage May 29th moved due to loading issues. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.1TR (ENMAX 43) | 2019-04-01 08:00 | 2019-04-12 16:00 | N | N | transformer differential relay panel replacement | Transformer |  | Transformer Differential Relay Panel Replacement | For Information Only
ALTALINK | 61s T1 (61s Lodgepole) | 2019-04-01 09:00 | 2019-04-04 17:00 | N | N | replace and install metering PTs 61s36 and switches | Transformer |  | Replace metering PTs 61s36 and switches and install new metering elements on all 3 phases. | For Information Only
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725BL54) | 2019-04-01 10:00 | 2019-04-18 08:00 | N | Y | replace 674S725W switch | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 432s 790 (432s Carvel),790L (432s Carvel - 790L57) | 2019-04-01 10:00 | 2019-04-02 17:30 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 310p 1452 (310p Sundance),310p 1552 (310p Sundance) | 2019-04-01 10:00 | 2019-04-04 16:00 | N | Y | migrate and commission protections to new RTU and LAN | Circuit Breaker |  | Migrate and commission all G4 Stub bus protections (including G4 Rev Power tripping auxiliary module), breakers, breaker fail protections status, controls, alarms, metering and remote access to new RTU and LAN. Migrate and commission T4 B protection alarms, 310P4G alarms and status to new RTU. | 240 kV, Pre-Condition, For Information Only
ALTALINK | 914L (86s Bigstone - 87s Gaetz),87s 1252 (87s Gaetz) | 2019-04-01 10:00 | 2019-04-05 17:00 | N | Y | replace 914L A & B line protections | Line, Circuit Breaker |  |  | 240 kV
ALTALINK | 251s SR1 (251s Whitla),251s 252 (251s Whitla),251s 552 (251s Whitla),251s Whitla 240kV Bus 1 | 2019-04-01 10:00 | 2019-07-15 17:00 | N | Y | construct new equipment | Circuit Breaker, Bus, Shunts |  | Construct new equipment for connection to 1018s Shamrock | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 151s T1 (151s Strathmore) | 2019-04-01 10:15 | 2019-04-03 17:00 | N | N | maintenance and repair, remove bird nest | Transformer |  | Replace parts on 151s11, remove birds nest 151s38, repair/adjust switches 151s3,6,7 and install switch signs | For Information Only
ALTALINK | 310p 252 (310p Sundance) | 2019-04-01 10:30 | 2019-04-04 17:30 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 461L (212s N.E. Lacombe - 198s Blackfalds) | 2019-04-01 11:00 | 2019-04-06 17:00 | N | N | replace CB 198s461 and install LA's | Line |  | replace CB 198s461 and install LA's | Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 725BL (725BL54 - 240s McBride Lake),725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2019-04-01 12:00 | 2019-04-01 17:30 | N | Y | creating open point 'A' | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 725BL54) | 2019-04-01 17:30 | 2019-04-18 07:30 | N | Y | component replacements | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 754s 701T (754s Ksituan River),754s 701TCS (754s Ksituan River) | 2019-04-02 07:00 | 2019-05-06 17:00 | N | N | new protection for 701T AND 701TCS | Transformer, Circuit Breaker |  | New protection for 701T AND 701TCS. 703T will carry 754S Ksituan Load | Pre-Condition, Firm Load Loss
ALTALINK | 305s T1 (305s Acheson),446L (305s Acheson - 367s Harry Smith),739L (14s Devon - 305s Acheson),305s1152 (305s Acheson),305s Acheson 138 kV Bus 1 | 2019-04-02 08:00 | 2019-04-04 17:00 | N | N | urgent work to replace a faulty switch 305s5 and a leaking PT 305s52 | Bus, Transformer, Line, Circuit Breaker |  | This is to replace a faulty switch 305s5 and a leaking PT 305s52 | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 36.1TR (ENMAX 36),36.3TR (ENMAX 36),7.84L (ENMAX 36 - ENMAX 7),36.81L (44s Bearspaw - ENMAX 36),7.84L. 36.81L. 36.1TR. 36.3TR. 36PT138-Z31. 7PT138-7.84 | 2019-04-02 08:00 | 2019-04-02 18:00 | N | Y | Spring Substation Washing | Terminal Equipment, Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.7TR (ENMAX 1) | 2019-04-02 09:00 | 2019-04-02 16:00 | N | N | oil sampling and maintenance | Transformer |  | Oil sampling MT, TC | For Information Only
Medicine Hat | MH69s3 MH69_306 (MH69s3 South Ridge),MH69s3 T32 (MH69s3 South Ridge) | 2019-04-02 12:00 | 2019-04-04 12:00 | N | N | breaker maintenance. | Circuit Breaker, Transformer |  | Breaker maintenance. | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale),72KN23 (Namao - Kennedale) | 2019-04-03 07:00 | 2019-04-05 17:00 | N | N | open ring to build scaffold | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 72KN23 (Namao - Kennedale) | 2019-04-03 07:30 | 2019-05-03 17:00 | N | N | pothead repair | Line |  |  | For Information Only
ALTALINK | 102s 6552 (102s Langdon) | 2019-04-03 07:45 | 2019-04-03 17:15 | N | Y | Urgent outage to install trip latch assembly and time breaker | Circuit Breaker |  | Urgent outage to install trip latch assembly and time breaker. This is in response to the 937L T&R event on Mar 24 | 240 kV
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2019-04-03 08:00 | 2019-04-03 11:00 | N | N | spring substation washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P2C | 2019-04-03 08:00 | 2019-04-03 19:00 | N | Y | forced outage | Line |  |  | Limits ATC
ATCO | 727s 601T (727s Kinuso) | 2019-04-03 08:00 | 2019-04-17 16:00 | N | N | 727s substation rebuild (capital maintenance). Replaced existing 601T with new 601T. ISD April 10, 2019 | Transformer
ENMAX | 14.4TR (ENMAX 14) | 2019-04-03 08:00 | 2019-04-03 11:00 | N | N | spring substation washing | Transformer |  |  | For Information Only
ALTALINK | 515s T1 (515s FedpipeJudy Creek) | 2019-04-03 08:00 | 2019-04-03 12:00 | N | N | trouble repair T1(TX18332) | Transformer |  | AML; TC trouble repair T1(TX18332), Customer; lock out relay wiring changes | For Information Only
ALTALINK | 100L (895s Suffield - 498s Tilley),498s 100X (498s Tilley) | 2019-04-03 08:30 | 2019-04-03 16:00 | N | N | maintain 498s100X | Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | Natal T1 (BCH Natal) | 2019-04-03 09:00 | 2019-04-05 17:00 | N | Y | annual plan request F20 - inspection/doble | Transformer |  |  | Pre-Condition
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14),14.3TR (ENMAX 14),14.1TR (ENMAX 14),11.82L (ENMAX 14 - ENMAX 11),11.82L. 14.1TR. 14.3TR. 14PT138-Z31. 14.1 CAP. 14.2 CAP | 2019-04-03 11:00 | 2019-04-03 18:00 | N | N | spring substation washing feeder ties required | Terminal Equipment, Line, Transformer, Shunts |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENBRIDGE | Hay Lake North Series Capacitor,Marias South Series Capacitor | 2019-04-03 17:53 | 2019-04-04 23:59 | N | Y | series capacitor banks were removed from service | Shunts |  |  | 240 kV, Limits ATC
Saskpower | Sask Power A1P | 2019-04-04 07:00 | 2019-04-10 16:00 | N | Y | maintenance | Line | Dec-02-Informed by Greg that Sask Power informed and provided the updated import and export limits. |  | Limits ATC
ENMAX | 39.1TR (ENMAX 39),39.3TR (ENMAX 39),38.83L (ENMAX 39 - ENMAX 38),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2019-04-04 08:00 | 2019-04-04 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 83s T1 (83s Taber) | 2019-04-04 09:15 | 2019-04-04 15:45 | N | Y | urgent outage for bird nest removal and mitigation prior to bird season | Transformer |  | Urgent outage for bird nest removal & mitigation prior to bird season | Restricts Generation
ENMAX | 39.2TR (ENMAX 39),39.4TR (ENMAX 39),22.81L (ENMAX 22 - ENMAX 39),39.82L (ENMAX 162 Beddington - ENMAX 39) | 2019-04-04 12:00 | 2019-04-04 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36),14.83L (ENMAX 14 - ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2019-04-05 08:00 | 2019-04-05 18:00 | N | N | spring substation washing | Line, Transformer |  | Spring Substation Washing. 36MD138-36.5TR Blade Adjustment | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Syncrude Mildred Lake | 2019-04-05 08:00 | 2019-04-11 20:00 | N | N | N16B substation (72kV / 4.16kV) PM | Station |  | N16B Substation (72kV / 4.16kV) PM, ML Extraction train 2 Equipment | For Information Only
ALTALINK, EPCOR | 711L (Inland Cement - 747L tap) | 2019-04-06 07:00 | 2019-04-07 17:00 | N | Y | line maintenance and upgrade | Line |  |  | For Information Only
ALTALINK | 799L (443s South Mayerthorpe - 77s Sagitawah) | 2019-04-06 07:15 | 2019-04-10 17:45 | N | N | clearance mitigation on Strs 591, 592, 655 & 656 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 13 B138-2.83 (ENMAX 13),5.9TR (ENMAX 5),5.10TR (ENMAX 5),ENMAX 5 5B138-5BT12 (ENMAX 5),2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13),ENMAX 2 MD138-2.83 (ENMAX 2) | 2019-04-06 08:00 | 2019-04-07 18:00 | N | N | repair whips and hot spot and switch maintenance | Line, Transformer, Circuit Breaker, Switch |  |  | For Information Only
ALTALINK | 902L (19s Wabamun - 310p Sundance),310p 752 (310p Sundance),310p 852 (310p Sundance) | 2019-04-06 10:51 | 2019-04-08 13:00 | N | Y | closing temporary open point 'A', 'B' & 'C' | Line, Circuit Breaker |  | Valard will be closing temporary Open Point 'A', 'B' & 'C' | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 951s SVC (951s Thickwood),951s 919 (951s Thickwood Hills) | 2019-04-07 08:00 | 2019-04-10 17:00 | N | Y | vendor to correct deficiencies | Circuit Breaker, Shunts |  | SVC outage at 951S Thickwood | 240 kV
ENMAX | 16.61L (ENMAX 16 - ENMAX 27),ENMAX 16 B69-16.61 (ENMAX 16),ENMAX 27 B69-16.61 (ENMAX 27) | 2019-04-07 12:00 | 2019-04-07 17:00 | N | N | spring transmission line washing | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs),557s 2404 (557s Castle Downs),557s 2405 (557s Castle Downs),71s 920W (71s Lamoureux) | 2019-04-08 07:00 | 2019-04-08 17:00 | N | Y | disconnect repair | Line, Switch, Circuit Breaker |  |  | 240 kV, For Information Only
Medicine Hat | MH69s2 MH69_215 (MH69s2 North Industrial),MH69s2 MH69-T22 (North Industrial Substation) | 2019-04-08 07:00 | 2019-04-09 12:00 | N | N | breaker maintenance | Circuit Breaker, Transformer |  |  | For Information Only
EPCOR | 987s C2401 (987s Clover Bar) | 2019-04-08 08:00 | 2019-04-12 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.1TR (ENMAX 43),9.83L (ENMAX 43 - ENMAX 9),ENMAX 43 B138-9.83 (ENMAX 43) | 2019-04-08 08:00 | 2019-04-08 16:00 | N | N | transformer differential relay panel replacement. | Line, Transformer, Circuit Breaker |  | Transformer Differential Relay Panel Replacement. Commission 43.1TR MD circuits, 9.83 breaker trip circuits. Expand current GOI for 43.1TR | Firm Load Loss, Creates Radial Feeds
ENMAX | 21.4TR (ENMAX 21),15.60L (ENMAX 21 - ENMAX 15),21.61L (ENMAX 21 - ENMAX 34),ENMAX 15 B69-15.60 (ENMAX 15),ENMAX 21 B69-21.61 (ENMAX 21),ENMAX 21 B69-15.60 (ENMAX 21),ENMAX 21 B69-21.4TR (ENMAX 21),ENMAX 34 B69-21.61 (ENMAX 34) | 2019-04-08 08:00 | 2019-04-08 18:00 | N | N | spring substation washing. | Line, Transformer, Circuit Breaker |  | Spring Substation Washing. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | AURORA Aurora | 2019-04-08 08:00 | 2019-07-15 20:00 | N | N | G40 Substation (72kV / 4.16kV) PM AN Tailings Distributor Equipment | Station |  | G40 Substation (72kV / 4.16kV) PM AN Tailings Distributor Equipment | For Information Only
ENMAX | 36.2TR (ENMAX 36) | 2019-04-08 08:00 | 2019-04-09 16:00 | N | N | replace damaged shutters | Transformer |  | replace damaged shutters - 36BA8-36.2TR | For Information Only
BCH | 5L52 (Ingledow - Custer) | 2019-04-08 09:00 | 2019-04-12 17:00 | N | Y | ING 5CB6 inspection and doble | Line |  | ING 5CB6 Inspection / Doble. Coordinate with BPA Outage 8-358903 | Limits ATC, 500 kV
ALTALINK | 538S Buford,538s T1 (538s Buford) | 2019-04-08 09:30 | 2019-04-08 18:00 | N | N | VR1 bypass switch repair (538s17) | Transformer, Station |  |  | For Information Only
ALTALINK | 454L (149s Nisku - 289s Saunders Lake),604L (149s Nisku - 155s Blackmud),149s 604 (149s Nisku),149s 454 (149s Nisku) | 2019-04-08 10:00 | 2019-04-11 18:45 | N | N | replace the 138kV VT (149s39). T3(TX18349) maintenance, leaks, SFRA, Doble | Line, Circuit Breaker |  | Replace the 138kV VT (149s39). T3(TX18349) maintenance, leaks, SFRA, Doble | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 914L (87s Gaetz - 63s Red Deer),87s 1652 (87s Gaetz) | 2019-04-08 10:00 | 2019-04-12 17:00 | N | Y | replace 87s Gaetz - 914L/L12 A & B line protections. | Circuit Breaker, Line |  | Replace 87s Gaetz - 914L/L12 A & B line protections. Affects 914L. | 240 kV
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2019-04-08 10:00 | 2019-04-11 16:00 | N | Y | migrate and commission all L6 alarms | Line |  | Migrate and commission all L6  1045L at 310P Sundance associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission CVT-L6 alarms. | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 107s T1 (107s Westfield),722L (368s Burdett - 107s Westfield) | 2019-04-08 10:30 | 2019-04-12 16:00 | N | N | doble, oil leak, broken site glass on bush | Transformer, Line |  |  | For Information Only
ALTALINK | 666L (498s Tilley - 28s West Brooks),498s 666 (498s Tilley) | 2019-04-08 11:30 | 2019-04-12 17:30 | N | Y | replace CTs, 666L A protection upgrade, and 666L B protection upgrade. | Line, Circuit Breaker |  | 498s666 outage to replace 3 138kV CTs, 666L A Protection Upgrade, and 666L B Protection Upgrade. Outage April 8-12 1200-1700 continuous. | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 267s C1 (267s Killarney Lake),267s C3 (267s Killarney Lake),267s 748E (267s Killarney Lake),267s C2 (267s Killarney Lake) | 2019-04-08 11:45 | 2019-04-11 11:45 | N | N | 138kV C/S maintenance | Shunts, Circuit Breaker |  | 138kV C/S maintenance | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 745s 601T (745s Slave Lake),745s Slave Lake RTU/SCADA | 2019-04-08 13:00 | 2019-05-03 17:00 | N | N | transformer swap, construction & commissioning | Transformer, Terminal Equipment |  | Replace 601T, Transformer Swap, Construction & Commissioning, SCADA RTU will have intermittent interruptions during downloads of 5-10 minutes | Affects Visibility
ATCO | 6L57 (735s Swan River - 727s Kinuso) | 2019-04-08 13:00 | 2019-04-09 17:00 | N | N | remove temporary bypass and install new overhead connections to new Kinuso substation | Line |  | Remove temp bypass and install new overhead connections to new Kinuso substation | Firm Load Loss, Creates Radial Feeds
ALTALINK | 123s T1 (123s Banff),123s T2 (123s Banff),551L (123s Banff - 953s Lake Louise) | 2019-04-09 01:00 | 2019-04-09 05:00 | N | N | urgent outage to replace failed 69kV bus PT | Transformer, Line |  |  | Firm Load Loss
ALTALINK | 296S Rosyth,769L (296s Rosyth - 769AL tap) | 2019-04-09 07:00 | 2019-04-09 18:00 | N | N | replace arrestors on T1 & T2 and switch maintenance | Station, Line |  |  | For Information Only
EPCOR | 72VN21 (Namao - 511s Victoria),Namao N725 (Namao) | 2019-04-09 08:00 | 2019-04-09 17:00 | N | N | disconnect repair | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 769AL (656s Clipper - 769L tap),769L (377s Hardisty - 296s Rosyth) | 2019-04-09 08:00 | 2019-04-09 18:00 | N | N | connect new 594s Battlesands and 769BL | Line |  | Connect new 594s Battlesands and 769BL, Switch maintenance at 656s by Enbridge. | For Information Only
ENMAX | 16.2TR (ENMAX 16) | 2019-04-09 08:00 | 2019-04-09 16:00 | N | N | oil level low - head space re-adjustment needed | Transformer |  |  | For Information Only
SUNCOR | 635EDD-1000 PT-1001 (635EDD-1000) | 2019-04-09 08:00 | 2019-04-10 17:00 | N | Y | investigate and clean the oil leak | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 756s 601T (756s Bigfoot) | 2019-04-09 12:00 | 2019-04-09 16:00 | N | N | remove the wire on the load side of the bus work | Transformer |  | To remove the wire on the load side of the bus work as per Westmoreland (the coalmine) request. Require 601T de-energized due to clearance issues | For Information Only
Medicine Hat | MH69s2 MH69_206 (MH69s2 North Industrial),MH69s2 T21 (MH69s2 North Industrial) | 2019-04-09 12:00 | 2019-04-10 16:00 | N | N | breaker maintenance | Circuit Breaker, Transformer |  |  | For Information Only
AESO-SC | OATI | 2019-04-09 13:00 | 2019-04-09 14:00 | N | N | firewall maintenance | SCInternal |  |  | For Information Only
ALTALINK, MONTANA | MATL (120s Picture Butte - Montana),1201L (520s Bennett - BCH Cranbrook) | 2019-04-09 16:00 | 2019-04-12 17:00 | Y | Y | forced outage- structure repair for 1201L | Line | 1201L: Peak RC COS outage ID: 1-00642386 Peak RC Path Derate ID: 1-00642387 (E>W), 1-00642388 (W>E) MATL: PEAK COS outage ID: 1-00642386 PEAK COS path de-rate ID:1-00642393 (N-S) :1-00642394 (S-N) |  | 240 kV, Limits ATC, 500 kV
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2019-04-10 07:00 | 2019-04-16 11:00 | N | N | line move from structure 54A to 59 & ICMP on structures # 33,60,63,66,67,68 | Line |  | Line Move from Structure 54A to 59 & ICMP on structures # 33,60,63,66,67,68 | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale T2 (Rossdale) | 2019-04-10 07:00 | 2019-04-10 17:00 | N | N | remove bird nest & clean up environmental conditions | Transformer |  |  | For Information Only
Medicine Hat | MH69s5 MH69_505 (MH69s5 NE Crescent Height),MH69s5 MH69-T51 (MH69s5 NE Crescent Height) | 2019-04-10 07:00 | 2019-04-10 16:00 | N | N | breaker maintenance | Transformer, Circuit Breaker |  |  | For Information Only
Syncrude | Syncrude Mildred Lake | 2019-04-10 08:00 | 2019-04-11 20:00 | N | N | N10 substation (72kV / 4.16kV) preventative maintenance | Station |  | N10 Substation (72kV / 4.16kV) PM, ML Extraction Crusher 10 Equipment | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2019-04-10 08:00 | 2019-04-11 16:00 | N | N | conservator oil leak from manhole | Transformer |  |  | For Information Only
CMH | MH_65L (MH69s7 - Cancarb) | 2019-04-10 08:00 | 2019-04-12 16:00 | N | N | relay work A protection | Line |  |  | For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11), 11.83L (162s Beddington - ENMAX 11), 11.3TR (ENMAX 11), 11.2TR (ENMAX 11) | 2019-04-10 08:00 | 2019-04-10 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 722L (368s Burdett - 107s Westfield),368s 722X (368s Burdett) | 2019-04-10 08:15 | 2019-04-11 14:45 | N | N | breaker maintenance | Circuit Breaker, Line |  | Maintain 368s722X (cb1729) SF6 138kV SFMT | For Information Only
ALTALINK | 394s T1 (394s Empress) | 2019-04-10 08:45 | 2019-04-10 11:45 | N | N | settings changes/standard relay maintenance | Transformer |  | Techs to perform settings changes/standard relay maintenance on the following: T1 S50/51/51NN/T1 SR760. T1 will be de-energized as unit has only single protection | For Information Only
AESO-SC | DDST | 2019-04-10 09:00 | 2019-04-10 17:00 | N | N | Q1 PROD | SCInternal
Saskpower | SASK POWER P1C | 2019-04-10 16:00 | 2019-04-16 17:00 | N | Y | bus replacement | Line |  |  | Limits ATC
Medicine Hat | MH69s2 C-21(MH69s2 North Industrial),MH69s2 MH69_208 (MH69s2 North Industrial) | 2019-04-11 07:00 | 2019-04-11 16:00 | N | N | breaker maintenance | Shunts, Circuit Breaker |  |  | For Information Only
EPCOR | Rossdale T3 (Rossdale) | 2019-04-11 07:00 | 2019-04-11 17:00 | N | N | clean up birds nest & environmental conditions | Transformer |  |  | For Information Only
ALTALINK | 799L (443s South Mayerthorpe - 235s Entwistle) | 2019-04-11 07:15 | 2019-04-15 17:45 | N | N | clearance mitigation | Line |  | 799L Clearance mitigation on Strs 858, 973 and 974 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 635EDD-1000 PT-1000 (635EDD-1000) | 2019-04-11 08:00 | 2019-04-12 17:00 | N | Y | Investigate transformer high temperature alarm | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ATCO | 933s 701T (933s Tower Road),933s 701 (933s Tower Road) | 2019-04-11 08:00 | 2019-04-11 17:00 | N | N | emergency SF6 top up | Transformer, Circuit Breaker |  | Very Low SF6 Gas on Breaker 701, Tower Road 25kv load has been transferred to 718S Parsons Creek. | For Information Only
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24) | 2019-04-11 08:00 | 2019-04-11 18:00 | N | Y | spring substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s5 MH69-T52 (MH69s5 NE Crescent Height),MH69s5 MH69_507 (MH69s5 NE Crescent Height) | 2019-04-12 07:00 | 2019-04-12 16:00 | N | N | breaker maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ENMAX | 9.1TR (ENMAX 9),9.80L (ENMAX 31 - ENMAX 9) | 2019-04-12 08:00 | 2019-04-12 18:00 | N | N | spring substation washing | Line, Transformer |  | Spring Substation Washing. Hotspot SW86@9sub. Hotspot 85 | For Information Only
ALTALINK | 197L (349s Stavely - 928s East Stavely) | 2019-04-13 06:00 | 2019-04-14 18:00 | N | Y | cutting in the new portion of 197L | Line |  | Cutting in the new portion of 197L replacing all Structures between 197L3 & 197L101 | Restricts Generation
Medicine Hat | MH69s1 MH69_13 (MH69s1 Power P Switchyard),MH69s1 MH69_17 (MH69s1 Power P Switchyard) | 2019-04-13 07:00 | 2019-05-07 16:00 | N | N | replacement of breakers | Circuit Breaker |  | Partial Rung outage  Commence removal/ replacement of Breakers/bus MH69-13 and MH69-17. | For Information Only
ENMAX | 16.1TR (ENMAX 16),15.62L (ENMAX 15 - ENMAX 16),16.61L (ENMAX 16 - ENMAX 27) | 2019-04-13 08:00 | 2019-04-13 18:00 | N | N | corrective | Transformer, Line |  | Corrective. Hot Spot jaw side SW67. Check reversing switch 16.1TR | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2019-04-13 12:00 | 2019-04-13 14:00 | N | N | spring pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2019-04-13 14:00 | 2019-04-13 16:00 | N | N | spring pothead washing | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2019-04-14 08:00 | 2019-04-14 18:00 | N | N | HV SW maintenance | Line, Transformer |  | HV SW maint SW84G, SW91, SW96, SW97, SW98, SW99. Network switching required. | Pre-Condition
EPCOR | 557s T1 (557s Castle Downs) | 2019-04-15 07:00 | 2019-04-18 17:00 | N | Y | doble / SFRA | Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 72JM18 (805s Jasper - Meadowlark),Meadowlark M722 (Meadowlark),Meadowlark T1 (Meadowlark) | 2019-04-15 07:00 | 2019-04-17 15:10 | N | N | interlock wiring | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-04-15 07:00 | 2019-04-19 19:00 | N | N | 1.80L/1.81L cable replacement project | Line |  | 1.80L/1.81L Cable replacement project. Complete the installation of our ground wells at the tower site. | Firm Load Loss, Creates Radial Feeds
Medicine Hat, CMH | MH69s5 MH69_514 (MH69s5 NE Crescent Height),MH69_60LMH_60L (MH69s5 North East Cresent Heights - Cancarb) | 2019-04-15 07:00 | 2019-04-15 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 104s T1 (104s Watson Creek),615L (602s Cold Creek - 104s Watson Creek),104s Watson Creek 138kV Bus | 2019-04-15 07:00 | 2019-04-18 17:00 | N | N | 104s substation expansion project, install & connect SS2, install 138kV rigid bus, add motor mech to 104s2 | Transformer, Line, Bus |  | 104s substation expansion project. Install & connect SS2, Install 138kV rigid bus, add motor mech to 104s2 | For Information Only
ALTALINK | 104s T2 (104s Watson Creek),104s T3 (104s Watson Creek),104s Watson Creek 69kV Bus,530L (2085s Sheridan - 104s Watson Creek) | 2019-04-15 07:30 | 2019-04-23 07:45 | N | N | complete scope on 530L, close Open Point 'A' on 530L at fenceline of 104s | Line, Transformer, Bus |  | Complete scope on 530L, close Open Point 'A' on 530L at fenceline of 104s | For Information Only
ENMAX | 7PT138-Z32 (ENMAX 7) | 2019-04-15 08:00 | 2019-04-15 12:00 | N | N | remedy PT wiring | Terminal Equipment |  | Remedy PT Wiring. Distance protection on 7.82L disabled while PTs are offline | For Information Only
ENMAX | 5.5TR (ENMAX 5) | 2019-04-15 08:00 | 2019-04-16 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-04-15 08:00 | 2019-04-15 16:00 | N | N | HV breaker maintenance | Line |  | HV breaker maintenance 20B138-1.81L | Firm Load Loss, Creates Radial Feeds
ENMAX | 16.1TR (ENMAX 16) | 2019-04-15 08:00 | 2019-04-24 16:00 | N | N | corrective maintenance | Transformer |  | Corrective. 16.1TR oil leak from temp/winding probe housing. 16.1TR oil leak secondary cabinet. LV bus outage required to open cabinet doors. Check reversing switch | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2019-04-15 08:00 | 2019-05-24 16:00 | N | N | test transformer | Transformer |  | doble test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing | For Information Only
EPCOR | 987s C2403 (987s Clover Bar) | 2019-04-15 08:00 | 2019-04-18 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds
SUNCOR | 29EDD-1 Millennium,29EDD-1 29EDD1s952 (29EDD-1 Millennium),29EDD-1 29EDD1s1052 (29EDD-1 Millennium),29EDD-1 Millennium 260kV West Bus 1 | 2019-04-15 08:00 | 2019-04-28 18:00 | N | Y | 5 years maintenance | Station, Circuit Breaker, Bus |  | Perform maintenance and testing (5 year) breakers, CVT and surge arrestors: Varies from 4 to 16 hours depending on the stage of work. | 240 kV, For Information Only
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2019-04-15 08:00 | 2019-04-15 16:00 | N | N | transformer differential relay panel replacement | Circuit Breaker, Line |  | Transformer Differential Relay Panel Replacement. Commission trip circuits | Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s T30 (511s Crossings),511s SVC Plus (511s Crossings) | 2019-04-15 08:15 | 2019-04-16 16:00 | N | Y | annual maintenance | Shunts, Transformer |  | 511s Annual Maintenance, MSR Inspections, Power Module Change and Communication Checks. | 240 kV
BCH | 5L72 (Mica Creek - Nicola) | 2019-04-15 09:00 | 2019-04-30 17:00 | N | Y | urgent repair work | Line |  | BC Outage Peak RC COS: 1-00642461 AB Peak RC COS# : 1-00643314 (W>E), 1-00643315 (E>W) | 500 kV
ALTALINK | 895s2219 (895s Suffield) | 2019-04-15 11:15 | 2019-04-15 16:45 | N | Y | maintain 25 kV vacuum breaker | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 437s T1 (437s Baymag) | 2019-04-15 12:15 | 2019-04-17 16:15 | N | N | maintenance, doble, fix leaks and temp gauge | Transformer |  |  | For Information Only
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2019-04-16 07:00 | 2019-05-05 18:00 | N | Y | spacer and damper replacement on structures #4 - 191 | Line |  |  | Pre-Condition, 500 kV
Medicine Hat | MH69s3 MH69_316 (MH69s3 South Ridge),MH69s-C-31 (MH69S-3) | 2019-04-16 07:00 | 2019-04-16 16:00 | N | N | breaker maintenance | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 739L (14s Devon - 305s Acheson) | 2019-04-16 07:15 | 2019-04-23 17:45 | N | N | replace Str # 523 On 739L | Line |  |  | Pre-Condition, Overload, Over/Under Voltage
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2019-04-16 08:00 | 2019-04-18 16:00 | N | N | HV breaker maintenance 15B69-15.60 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20),1.81L (ENMAX 20 - ENMAX 1) | 2019-04-16 08:00 | 2019-04-16 16:00 | N | N | maintenance | Line, Transformer |  | SW 82 @ 20 Sub stiff to operate, requires maintenance | Firm Load Loss, Creates Radial Feeds
ALTALINK | 87s T2 (87s Gaetz) | 2019-04-16 08:15 | 2019-04-17 17:45 | N | Y | transformer maintenance | Transformer |  | transformer maintenance: doble LTC FPE/MR 240/138kV, oil leak, maintain LTC FPE/MR 240/1, piping oil Leak | 240 kV, Contingency Requires Mitigation
ALTALINK | 338s 252 (338s Cherhill) | 2019-04-16 08:30 | 2019-04-17 15:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 197s 174W (197s Bardo),174L (197s Bardo - 289s Saunders Lake) | 2019-04-16 08:30 | 2019-04-16 18:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 580s T2 (580s Sylvan Lake) | 2019-04-16 08:45 | 2019-04-17 16:15 | N | N | transformer maintenance | Transformer |  | transformer maintenance; doble LTC PAU/ABB 138/26, maint LTC PAU/ABB 138/26 | For Information Only
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2019-04-16 09:00 | 2019-04-18 17:00 | N | Y | BCH urgent work | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 919L (310p Sundance - 77s Sagitawah) | 2019-04-16 10:00 | 2019-04-17 15:10 | N | Y | migrate and commission 919L signals | Line |  | migrate and commission all 919L protections, breakers, breaker fail protections status, controls, alarms, metering and remote access to new RTU and LAN | 240 kV, Pre-Condition, Overload
AESO-SC | OATI | 2019-04-16 18:00 | 2019-04-16 19:00 | N | N | inter-site transfer business continuity drill | SCInternal
ATCO | 6L99 (727s Kinuso - 745s Slave Lake),727s 603 (727s Kinuso) | 2019-04-17 07:00 | 2019-04-17 17:00 | N | N | install temp bypass for construction of new Kinuso substation 727s | Line, Circuit Breaker |  | Install temp bypass for construction of new Kinuso substation 727S NEW OVERALL WORK PLAN: APRIL 9 - 6L57 GOI TO STRING 6L57 INTO NEW 727S, ENERGIZE NEW SUB & SOAK 601T (CROW 2-43273)(OLD & NEW STILL ENERGIZED) APRIL 10 - 25KV CUTOVER TO 727S NEW (CROW 2-48358) APRIL 17 - 6L99 GOI TO STRING 6L99 INTO NEW 727S (CROW 2-43274) | Firm Load Loss, Creates Radial Feeds
ALTALINK | 700L (422s Westwood - 746s Sherwood Park) | 2019-04-17 07:00 | 2019-04-18 18:00 | N | N | ICMP on structures #28,29,60,61,62,63,64,65,80 | Line |  |  | Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s3 MH69_314 (MH69s3 South Ridge) | 2019-04-17 07:00 | 2019-04-17 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 41.84L (ENMAX 54 - ENMAX 41),54.81L (ENMAX 54 - ENMAX 65),54.1TR (ENMAX 54) | 2019-04-17 08:00 | 2019-04-17 18:00 | N | N | spring substation washing | Line, Transformer |  |  | For Information Only
ENMAX | 41.1C (ENMAX 41) | 2019-04-17 08:00 | 2019-04-17 16:00 | N | N | repair the screen for BMR 85 (ABB REC670) | Shunts |  |  | For Information Only
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2019-04-17 08:00 | 2019-04-22 17:00 | N | N | line move from structure 54A to 59 & ICMP on structures # 33,60,63,66,67,68 | Line |  | Line Move from Structure 54A to 59 & ICMP on structures # 33,60,63,66,67,68 | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.1TR (ENMAX 5) | 2019-04-17 08:00 | 2019-04-18 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
Syncrude | Aurora T3 (Aurora) | 2019-04-17 08:00 | 2019-04-28 20:00 | N | Y | maintenance | Transformer |  | Aurora T3Substation (13.8kV / 72kV) Tag # 201-1-PTR72-003. CB 52-11 and 52-12 will be opened. Generator G20 witll be Offline due to HRHWG Inspection Outage | Restricts Generation
ALTALINK | 174L (197s Bardo - 395s North Holden),197s 174E (197s Bardo) | 2019-04-17 08:30 | 2019-04-17 17:00 | N | N | 138kV breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
AESO-SC | EMS,PI | 2019-04-17 09:00 | 2019-04-17 16:00 | N | N | database and SCADAcalc update | SCInternal
ALTALINK | 244s 552 (244s Bowmanton) | 2019-04-17 09:15 | 2019-04-17 14:45 | N | Y | emergency work to top up gas on center phase | Circuit Breaker |  | Urgent outage to top up gas on center phase, breaker keeps alarming | 240 kV, Contingency Requires Mitigation
ALTALINK | 62s11 (62s Brazeau) | 2019-04-17 23:00 | 2019-04-18 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2019-04-18 03:00 | 2019-04-18 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
Medicine Hat, CMH | MH69s3 MH69_302 (MH69s3 South Ridge),20L (MH69S-6 Riverview - MH69S-3 South Ridge),MH69s3 MH138_317 (MH69s3 South Ridge) | 2019-04-18 07:00 | 2019-04-18 18:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK, Lethbridge | 725BL (725BL54 - 240s McBride Lake),725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2019-04-18 07:30 | 2019-04-18 15:30 | N | Y | closing Open Point 'A' @ structure #103 and perform maintenance on 725BL54 | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, Lethbridge | 725L (674s Lethbridge Bowron - 15s Fort MacLeod) | 2019-04-18 08:00 | 2019-04-18 14:00 | N | Y | replace 674S725W switch | Line |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32),32PT138-Z32 (ENMAX 32) | 2019-04-18 08:00 | 2019-04-18 18:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  |  | For Information Only
ATCO | 767s 701T (767s Oyen),7L132 (767s Oyen - 959s Lanfine),7L760 (7L760D2 - 767s Oyen) | 2019-04-18 09:00 | 2019-04-18 17:00 | N | N | 767s Oyen 700PT1 PCB oil sample required, 701 breaker & hot spot repairs | Line, Transformer |  | 767S Oyen 700PT1 PCB oil sample required, Also PM work on 701 Breaker & Hot Spot Repairs on 701A. Oyen Area on 6L09 System for the duration of the work Coordinated with Spectre Energy (Excel Pipeline 6L21) planned outage | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Syncrude Mildred Lake | 2019-04-18 09:00 | 2019-04-18 12:00 | N | N | substation transformer (1-PTR72-179) 72kV/72kV outage to fix issues of protection relay | Station |  | C05 Substation Transformer (1-PTR72-179) 72kV/72kV outage to fix issues of protection relay. It is fed from the SWMF powerline which is fed from Plant 31, CB # 1315 (This CB will not be operated). | For Information Only
ENMAX | 7.1TR (ENMAX 7),7.84L (ENMAX 36 - ENMAX 7),ENMAX 36 B138-7.84 (ENMAX 36),ENMAX 7 B138-7BT3 (ENMAX 7) | 2019-04-19 08:00 | 2019-04-19 18:00 | N | N | substation washing | Line, Transformer, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69s1 MH69_21 (MH69s1 Power P Switchyard) | 2019-04-20 07:00 | 2019-05-10 16:00 | N | N | replacement of breakers | Circuit Breaker |  | Remaining rung outage- Commence removal/replacement of breaker/bus MH69-21. | Restricts Generation, For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2019-04-20 07:00 | 2019-04-24 19:00 | N | N | 1.80L/1.81L Cable replacement project - complete the installation of our ground wells at the tower site | Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2019-04-20 09:00 | 2019-04-20 18:00 | N | N | spring substation washing | Transformer, Line |  |  | Pre-Condition
ENMAXEC | 383s Kettles Hill Windfarm RTU/SCADA | 2019-04-20 20:00 | 2019-04-20 23:00 | N | N | network upgrade | Terminal Equipment |  |  | Affects Visibility
ENMAXGPI | 134s Taber Wind Farm RTU/SCADA | 2019-04-20 21:30 | 2019-04-21 02:00 | N | N | repair internet router | Terminal Equipment |  |  | Affects Visibility
SHELL | 402s T1 (402s Shell Expansion 1) | 2019-04-22 07:30 | 2019-04-26 16:00 | N | N | transformer testing | Transformer |  | 402S - 701T TRANSFORMER CLASS1 MAJOR TESTING Testing 701T Customer will be looking at their U/G cables from 701T to their building 701T will be out of service for the duration of the work. The load will be fed from 702T | For Information Only
Medicine Hat | MH69s2 MH69_212 (MH69s2 North Industrial),MH69s5 MH69_510 (MH69s5 NE Crescent Height),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2019-04-22 08:00 | 2019-04-22 16:00 | N | N | emergency outage - repair leaking drain valve on MH69-212 69kV breaker in MHS-2 North Industrial substation | Line, Circuit Breaker |  |  | For Information Only
ATCO, ALTALINK | 530L (2085s Sheridan - 104s Watson Creek) | 2019-04-23 07:00 | 2019-05-08 07:00 | N | N | continue work on 530L P1603 | Line |  |  | For Information Only
EPCOR | Woodcroft T2 (Woodcroft),TX2 @ Woodcroft | 2019-04-23 07:00 | 2019-04-23 17:00 | N | N | ITM measurement | Terminal Equipment, Transformer |  | ITM Measurement | Firm Load Loss, Creates Radial Feeds
ALTALINK | 615L (602s Cold Creek - 104s Watson Creek) | 2019-04-23 07:00 | 2019-04-25 17:00 | N | N | 104s substation expansion project | Line | P1603 Sheridan sub (V.Chan April 10, 2019) | 104s substation expansion project. Connect 104s289 & 104s389 to 138kV bus, add motor mech to 104s2, P&C commissioning | For Information Only
EPCOR | 524s T1 (524s Owen Corning) | 2019-04-23 07:00 | 2019-05-07 07:00 | N | N | regasketing transformer | Transformer |  |  | For Information Only
EPCOR | Namao T3 (Namao),72CN10 (987s Clover Bar - Namao) | 2019-04-23 07:00 | 2019-04-27 17:00 | N | N | extended zone to decom protection (72CN10 NIS) | Transformer, Line |  |  | For Information Only
Medicine Hat, CMH | MH69s6 MH69_614 (MH69s6 Riverview),8L (MH69S-6 Riverview - MH69S-1 Power Plant) | 2019-04-23 07:00 | 2019-04-23 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | Breaker Maintenance | Pre-Condition
ALTALINK | 508S Lakesend | 2019-04-23 07:00 | 2019-04-23 17:00 | N | N | customer work on their equipment | Station |  | customer work on their equipment | For Information Only
EPCOR | 987s C2404 (987s Clover Bar) | 2019-04-23 08:00 | 2019-04-26 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 745s 601T (745s Slave Lake) | 2019-04-23 08:00 | 2019-05-07 16:00 | N | N | replacement of 20 MVA with new 25 MVA transformer (capital maintenance). ISD April 30, 2019 | Transformer
ALTALINK | 221s T3 (221s Sunken Lake) | 2019-04-23 08:00 | 2019-05-07 16:00 | N | N | Transformer Replacement. ISD April 30, 2019 | Transformer
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar),987s C2402 (987s Clover Bar),987s C2404 (987s Clover Bar) | 2019-04-23 08:00 | 2019-04-23 17:00 | N | Y | Repair on CDS28 | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin) | 2019-04-23 08:00 | 2019-04-30 18:00 | N | N | replacing structures | Line |  | 803L/804L ULCM project, replacing structures 4, 5 and 29A | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 104s Watson Creek RTU/SCADA | 2019-04-23 08:00 | 2019-04-25 17:00 | N | N | correction of transformer monitoring equipment for P1603 | Terminal Equipment |  | Supervisory outage of RTU update configuration for the correction of transformer monitoring equipment in support of the Jasper project. Short loss of visibility (2 -15 minutes) during downloading of new configuration. Loss of controls during testing due to supervisory I/O switches being off most of the day (Restoration time 10 minutes). Several false status and alarms may be generated during cutovers and testing / commissioning. HMI will be out of service briefly during updates. Will be in-service for the duration of testing | Affects Visibility
ALTALINK | 89s 752 (89s Ellerslie) | 2019-04-23 09:00 | 2019-04-25 18:00 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO, ALTALINK | 807AL (402s Shell Expansion I - 807L tap), 807L (410s Josephburg - 402s Scotford Expansion), 807L (233s Beamer - 807AL tap) | 2019-04-23 09:00 | 2019-04-26 18:00 | N | Y | clearance mitigation structure #75 | Line |  | Clearance Mitigation Structure #75 | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 100L (895s Suffield - 498s Tilley) | 2019-04-23 09:00 | 2019-04-24 18:00 | N | N | moving 100L356B & 666L3 | Line |  | moving 100L356B & 666L3 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2019-04-23 09:00 | 2019-04-26 17:00 | N | Y | BCH urgent work | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
AESO-SC | DDST,DT,ETS,MARGO | 2019-04-23 10:00 | 2019-04-23 12:00 | N | N | critical application migration (Primary Data Centre to Secondary Data Centre) | SCInternal
ALTALINK, Lethbridge | 725AL (618s Riverbend - 725L tap),725L (111s Coalbanks - 674s Lethbridge Bowron) | 2019-04-23 10:00 | 2019-05-09 18:00 | N | Y | replace 674S725E switch and component replacement | Line |  | Replace 674S725E switch and Component Replacements: (725AL Str's Range 1-13) and (725L Str's Range 310-367) | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 726L (37s North Calder - 71s Lamoureux),71s 252 (71s Lamoureux),71s 352 (71s Lamoureux) | 2019-04-23 10:00 | 2019-04-23 18:00 | N | N | hotspot repair | Circuit Breaker, Line |  | 65deg Hotspot repair | Pre-Condition
ALTALINK | 310P 3352 (310p Sundance),310P 69 (310p Sundance),310P 234N (310p Sundance),310P 512N (310p Sundance),310p T30 (310p Sundance),310P Sundance 69kV Bus,310P T33 (310P Sundance) | 2019-04-23 11:00 | 2019-05-02 16:00 | N | Y | migrate and commission controls and protection to new RTU and LAN | Bus, Transformer, Circuit Breaker |  | Migrate and commission all T31(TX18152), T33(T18300), 69KV Bus & 310P3352 protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. Replace 310P696 air break control module, commission alarms control and status to new RTU. | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 87s T1 (87s Gaetz) | 2019-04-23 11:15 | 2019-04-25 15:45 | N | Y |  | Transformer |  | transformer maintenance; doble LTC CGE/MR 240/138kV, maintain LTC CGE/MR 240/13, oil leaks | 240 kV, Contingency Requires Mitigation
ALTALINK | 5s 7 (5s East Calgary), 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2019-04-23 11:15 | 2019-04-24 16:45 | N | N | maintain circuit switcher 5s71 and 5s7 breaker | Circuit Breaker, Shunts |  | Maintain circuit switcher 5s71 and 5s7 138kV SF6 gas breaker | Pre-Condition
ALTALINK | 54L (118s Canmore - 54L172) | 2019-04-24 07:00 | 2019-04-24 18:00 | N | N | urgent outage to modify underbuild | Line |  | urgent outage required for Fortis to modify underbuild on 54L Str 152 and 144 to accommodate the re-framing of 138kV structures from X-arm suspension insulation to post-insulators | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft T3 (Woodcroft) | 2019-04-24 07:00 | 2019-04-24 17:00 | N | N | ITM measurement | Transformer |  |  | For Information Only
Medicine Hat | MH69s6 MH69_607 (MH69s6 Riverview) | 2019-04-24 07:00 | 2019-04-24 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 447s T1 (447s Enchant) | 2019-04-24 07:45 | 2019-04-25 16:30 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2019-04-24 08:00 | 2019-04-25 16:00 | N | N | tap changer heater replacement | Transformer |  |  | For Information Only
ATCO | 840s 503 (840s McNeill) | 2019-04-24 08:30 | 2019-04-25 15:00 | N | Y | install cables In filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Station will be limited to 90 Mw Export and 90 Mw Import for the duration | Limits ATC
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-04-24 11:00 | 2019-04-24 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
Medicine Hat | MH69s6 MH69_604 (MH69s6 Riverview) | 2019-04-25 07:00 | 2019-04-25 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 20s T1 (20s Ghost),113L (20s Ghost - 33s Spray),150L (20s Ghost - 150L46),859L (20s Ghost - T793s Horse Creek) | 2019-04-25 07:00 | 2019-04-28 18:30 | N | Y | Replace 20s149, 20s153, T1 CTs Replace bus conductor and strain Insulators | Line, Transformer |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 408L (252s Jarrow - 51s Wainwright) | 2019-04-25 07:15 | 2019-04-26 17:45 | N | N | replace Str. 4 on 408L | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2019-04-25 08:00 | 2019-04-28 16:00 | N | N | hydrovaccing near line to replace water valve | Line |  | Contractor hydrovaccing near line in order to replace water valve. | Firm Load Loss, Creates Radial Feeds
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2019-04-25 08:00 | 2019-04-27 16:00 | N | N | breaker maintenance and SF6 gas sample | Line, Transformer |  | HV breaker maintenance 27B69-13.60, 13B69-13.4TR/13.60. SF6 Gas sample | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-04-25 09:00 | 2019-04-25 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK, ATCO | 104s Watson Creek 69kV Bus,530L (2085s Sheridan - 104s Watson Creek) | 2019-04-25 17:00 | 2019-05-01 12:00 | N | N | 69kV bus outage for any remaining Iconic scope | Bus, Line |  |  | For Information Only
Medicine Hat | MH69s6 MH69_608 (MH69s6 Riverview),MH69s6 MH69_616 (MH69s6 Riverview) | 2019-04-26 07:00 | 2019-04-26 18:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ENMAX | 54.81L (ENMAX 54 - ENMAX 65) | 2019-04-26 08:00 | 2019-04-26 12:00 | N | N | repair required on line | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 320p 152 (320p Keephills),320p 452 (320p Keephills),320p 252 (320p Keephills) | 2019-04-27 08:00 | 2019-05-24 10:00 | N | Y | replace 320p489 and maintain 320p452 | Circuit Breaker |  | Turnaround, replace 320p489, maintain 320p452, AltaLink to replace 320p452 CTs | 240 kV, Restricts Generation, Contingency Requires Mitigation
MONTANA | MATL (120s Picture Butte - Montana) | 2019-04-28 01:04 | 2019-04-30 23:59 | N | Y | forced outage | Line | PEAK COS outage ID:1-00645528 PEAK COS path de-rate ID:1-00645615(N-S), (S-N):1-00645617 |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 113L (20s Ghost - 33s Spray) | 2019-04-28 17:00 | 2019-04-30 18:30 | N | N | finish work on 20s155s | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2019-04-28 17:00 | 2019-05-01 18:00 | N | N | remove and replace 20s51, 20s413, 20s103 and replace insulators conductor | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Medicine Hat, CMH | MH69s6 MH69_602 (MH69s6 Riverview),MH69_10L (MH69s2 North Industrial - MH69s6 Riverview) | 2019-04-29 07:00 | 2019-04-29 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 814s T2 (814s Bellamy),Rossdale T1 (Rossdale) | 2019-04-29 07:00 | 2019-05-10 17:00 | N | Y | 15 kV bus 5 addition | Transformer |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 Millennium,29PL6-5 (29EDD-1 Millennium - 29EDD-2 Tar Island),29EDD-1 29EDD1S1652 (29EDD-1),29EDD-1 29EDD1S1752 (29EDD-1) | 2019-04-29 08:00 | 2019-05-08 12:00 | N | N | 5 years maintenance | Line, Circuit Breaker, Station |  | Perform maintenance and testing (5 year) breakers, CVT and surge arrestors: Varies from 4 to 16 hours depending on the stage of work. | For Information Only
EPCOR | Namao T3 (Namao) | 2019-04-29 08:00 | 2019-12-11 17:00 | N | N | transformer replacement | Transformer | Namao T3 (Namao) |  | For Information Only
Syncrude | Syncrude Mildred Lake | 2019-04-29 08:00 | 2019-05-05 20:00 | N | N | substation transformer (23-PTR5-177) PM | Station |  | C03 Substation Transformer PM is (23-PTR5-177), 72 kV / 4.16kV. It is fed from the WMF powerline which is fed from Plant 31, CB # 815 (This CB will not be operated). | For Information Only
EPCOR | 803s L2401 (803s Lambton) | 2019-04-29 08:00 | 2019-05-03 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D133 (ENMAX 25),ENMAX 25 B240-D139 (ENMAX 25),ENMAX 25 B240-D142 (ENMAX 25),ENMAX 25 240kV North Bus | 2019-04-29 08:00 | 2019-04-29 18:00 | N | Y | assist with the repairs to the faulted cable on 1080L | Circuit Breaker, Bus |  | Altalink will require a 240kV Bus outage @ 25s to assist with the repairs to the faulted cable on 1080L. Crews will be removing 1080L pot head from structure. Switching crew required. Grounds required | 240 kV, Contingency Requires Mitigation
ALTALINK | 252s 2 (252s Jarrow),491L (252s Jarrow - 7L50 tap) | 2019-04-29 08:30 | 2019-05-02 17:30 | N | Y | replacing protections and testing locally with 252 breaker | Circuit Breaker, Line |  | Replacing L1 A and B Protections and testing locally with 252 breaker | Firm Load Loss, Creates Radial Feeds
ATCO | 7L95 (889s Mahkeses - 715s Leming Lake),715s 704 (715s Leming Lake) | 2019-04-29 09:00 | 2019-05-18 16:00 | N | Y | breaker maintenance and tie in bus lockout logic | Circuit Breaker, Line |  | Breaker Maintenance & tie in bus lockout logic | Restricts Generation
ATCO | 715s 701T (715s Leming Lake) | 2019-04-29 09:30 | 2019-05-01 16:30 | N | N | changing test switch on 701T Protection, and completing wiring for non-elects | Transformer |  | 715S 701T Non-Elec Tripping Logic (June 12 incident action) Require changing Test switch on 701T Protection, and completing wiring for Non-Elects. | For Information Only
ALTALINK | 95s T1 (95s Imperal Oil Edmonton) | 2019-04-29 10:15 | 2019-05-08 12:38 | N | N | transformer maintenance | Transformer |  | Transformer Maintenance; Bushing and Monitor replacement, Winding temp Gauge repair, oil replacement, doble, Multiple Leaks, Re-Gasket OBG and valve, T/C shaft seal oil leak | For Information Only
ALTALINK | 163s T2 (163s Amoco Empress) | 2019-04-29 11:30 | 2019-05-01 17:00 | N | Y | transformer maintenance | Transformer |  |  | 240 kV, For Information Only
ATCO | 840s 504 (840s McNeill) | 2019-04-29 11:30 | 2019-04-30 17:00 | N | Y | install cables in filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Station will be limited to 90 Mw Export and 90 Mw Import for the duration | Pre-Condition
ALTALINK | 68s T2 (68s Willesden Green) | 2019-04-29 12:30 | 2019-05-02 16:00 | N | Y | replace existing bulk oil 25kV breaker and switch maintenance | Transformer |  | Replace the existing bulk oil 25kV Breaker at 68s290E & switch maintenance on 68s25. | 240 kV, For Information Only
Medicine Hat, CMH | MH69s6 MH69_611 (MH69s6 Riverview),20L (MH69S-6 Riverview - MH69S-3 South Ridge),MH69s6 MH138_620 (MH69s6 Riverview) | 2019-04-30 07:00 | 2019-04-30 18:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 437s T1 (437s Baymag) | 2019-04-30 08:00 | 2019-04-30 16:45 | N | N | customer request for isolation and grounds installed | Transformer |  |  | For Information Only
ALTALINK | 437s T2 (437s Baymag) | 2019-04-30 08:00 | 2019-05-01 16:45 | N | N | maintenance, doble, rad leak, customer request for isolation and grounds installed | Transformer |  |  | For Information Only
Syncrude | Syncrude Mildred Lake | 2019-04-30 09:00 | 2019-04-30 16:00 | N | N | substation transformer (1-PTR72-180) outage to fix issues of protection relay | Station |  | C05 Substation Transformer (1-PTR72-180) 72kV/72kV Outage to fix issues of protection relay. It is fed from the WMF powerline which is fed from Plant 31, CB # 815 (This CB will not be operated). | For Information Only
ALTALINK | 285s3202 (285s East Camrose) | 2019-04-30 09:30 | 2019-04-30 11:30 | N | Y | update DNP address on 3202L 67/67N/79/L8 SEL351S | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 763L (28s West Brooks - 763L257A) | 2019-05-01 07:00 | 2019-05-01 13:00 | N | N | high load move | Line |  | High load move crossing underneath line between structures # 49 & 50 | Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CK12 (987s Clover Bar - Kennedale),72KN23 (Namao - Kennedale) | 2019-05-01 07:00 | 2019-05-03 17:00 | N | N | open ring to build scaffold | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | A.T. Plastics 5R ATP1382 (A.T. Plastics 5R) | 2019-05-01 07:00 | 2019-05-06 17:00 | N | N | doble/ maintenance for T3 | Circuit Breaker |  |  | For Information Only
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power),268s 503 (268s Whitecourt) | 2019-05-01 07:30 | 2019-05-01 18:00 | N | Y | customer high voltage equipment maintenance | Line, Circuit Breaker |  |  | Restricts Generation, For Information Only
ENMAX | 162s 240-RB134 (162s Beddington),162s 240-RB135 (162s Beddington),162s PTZ42 (162s Beddington),162s 2GSU-XF-0002 (162s Beddington) | 2019-05-01 08:00 | 2019-05-13 16:00 | N | Y | fall substation washing and protection upgrade | Circuit Breaker, Transformer, Terminal Equipment |  | Fall Substation Washing. Upgrade Protection on 2-GSU-XF-0002 | 240 kV, Restricts Generation, Contingency Requires Mitigation
TRANSALTAGP | EAGL Whitecourt Power | 2019-05-01 08:00 | 2019-05-16 16:00 | N | N | Whitecourt Power PSS Tuning and Model Validation. ISD: May 10, 2019 | Unit
ENMAX | ENMAX 36.2TR (ENMAX 36) | 2019-05-01 08:00 | 2019-05-02 16:00 | N | N | replace damaged shutters | Transformer |  |  | For Information Only
ALTALINK | 922L (310p Sundance - 17s Benalto) | 2019-05-01 08:00 | 2019-05-16 17:30 | N | Y | urgent clearance issue | Line |  |  | 240 kV, Pre-Condition
ATCO | 840s 505 (840s McNeill) | 2019-05-01 08:30 | 2019-05-02 16:00 | N | Y | install cables In filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Station will be limited to 90 Mw Export and 90 Mw Import for the duration | Limits ATC
ATCO | 715s 702T (715s Leming Lake) | 2019-05-01 09:30 | 2019-05-03 16:30 | N | N | update logic in 87TA | Transformer |  | Update logic in 87TA ( 702T Non-Electrical Tripping Logic ) to prevent tripping during Non Electrical testing Load will be transferred to 701T. | For Information Only
CMH, Medicine Hat | MH69s1 MH69_6 (MH69s1 Power P Switchyard),MH69s1 MH69_10 (MH69s1 Power P Switchyard),MHS9 T11 (Power Plant),MHS9 MH138-902 (MHS9 Poer Plant) | 2019-05-02 07:00 | 2019-05-03 12:00 | N | N | replace radiator | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 118s C1 (118s Canmore),118s T1 (118s Canmore),54L (118s Canmore - 54L172),118s 54W (118s Canmore) | 2019-05-02 07:15 | 2019-05-02 15:45 | N | N | maintain 138kV circuit switcher 118s18 | Line, Circuit Breaker, Transformer, Shunts |  |  | For Information Only
ALTALINK | 478s T1 (478s Tucuman) | 2019-05-02 07:15 | 2019-05-02 15:15 | N | N | calibrate a transducer and check SCADA | Transformer |  | calibrate a transducer and check proper SCADA indication is received for all tap position on LTC | For Information Only
ALTALINK | 760L (394s Empress - 163s Amoco Empress),163s 760X (163s Amoco Empress) | 2019-05-02 07:45 | 2019-05-02 14:45 | N | N | breaker maintenance on 138kV SF6 gas | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 530L (2085s Sheridan - 104s Watson Creek) | 2019-05-02 08:00 | 2019-05-16 16:00 | N | N | 2085s Sheridan energization. ISD: May 09, 2019 | Line
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2019-05-02 08:15 | 2019-05-02 13:45 | N | Y | urgent outage to replace termination on underground cable | Line |  |  | Pre-Condition
ENMAX | 1.7TR (ENMAX 1) | 2019-05-02 09:00 | 2019-05-03 16:00 | N | N | oil sampling | Transformer |  | oil sampling MT, TC | For Information Only
ALTALINK | 733L (179s Gleichen - 428s Namaka) | 2019-05-02 18:00 | 2019-05-04 18:00 | N | Y | forced repair for clearance mitigation | Line |  | forced repair for clearance mitigation | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 757s 905T (757s Battle River) | 2019-05-03 03:00 | 2019-05-06 14:00 | N | N | forced outage | Transformer |  | Site: BR5 Event: Outage  Forced (Delayed) Start: May 3, 2019 HE03 End: May 5, 2019 HE18 AC: 0 MW AOR: Replace failed 905T tap changer with new parts
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 7L50D2), 491L (252s Jarrow - 7L50), 252s 2 (252s Jarrow), 526s 252 (526s Buffalo Creek) | 2019-05-03 08:00 | 2019-05-06 08:00 | N | Y | setting changes at 526s and end to end testing with 252s | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.84L (ENMAX 1 - ENMAX 5) | 2019-05-04 08:00 | 2019-05-09 16:00 | N | N | install SW99, replace motor on 6a51 | Line |  | Install SW99. Replace motor on 6a51. Inv and Repair 1-6A9 Broken Motor Ground Switch [AVANTIS]. HV breaker modification 5B138-1.84 | For Information Only
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5) | 2019-05-04 08:00 | 2019-05-05 18:00 | N | N | install PT structure and switch maintenance | Transformer, Line |  | Install PT structure and New 5PT138-Z31. Install SW99. HV SW SW97 maint | Pre-Condition
Medicine Hat | MH69s1 MH69_2 (MH69s1 Power P Switchyard),MH69s1 MH69_13 (MH69s1 Power P Switchyard),MH69s1 MH69_24 (MH69s1 Power P Switchyard),MH69s1 MH69_34 (MH69s1 Power P Switchyard),MH69s1 69kV North Bus (MH69s1 Power P Switchyard) | 2019-05-05 06:00 | 2019-05-07 19:00 | N | N | switch gear upgrade | Bus, Circuit Breaker |  |  | For Information Only
Medicine Hat | MH69s6 MH69_607 (MH69s6 Riverview) | 2019-05-05 07:00 | 2019-05-07 17:00 | N | N | maintenance | Circuit Breaker |  | Issue Transmission GOI to City of Medicine Hat Generation for their North Bus scheduled outage. | For Information Only
ENMAX | 16.2TR (ENMAX 16),16.60L (ENMAX 34 - ENMAX 16),16.63L (ENMAX 16 - ENMAX 36) | 2019-05-05 08:00 | 2019-05-05 18:00 | N | N | hot spot and breaker maintenance | Line, Transformer |  | 16SW64 Hot spot north phase jaw hinges side. HV Breaker Maintenance 36B69-16.63/36.5TR, 16B69-16.63. SF6 Gas sample. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72LH8 (Hardisty - 803s Lambton) | 2019-05-05 08:00 | 2019-05-11 08:00 | N | N | transformer replacement | Line |  |  | Overload
EPCOR | 987s GB1B (987s Clover Bar) | 2019-05-06 07:00 | 2019-05-10 17:00 | N | N | 72kV BF protection upgrade project | Circuit Breaker |  |  | For Information Only
ATCO | 729s 701T (729s Otauwau) | 2019-05-06 07:00 | 2019-05-19 17:00 | N | N | replace 701TCS and 144 kV low bus structures | Transformer |  | Replace 701TCS and 144kv low bus structures, 7L49 open ended*** LEAVE FOR TRAVIS TO PROCESS*** | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 408L (252s Jarrow - 51s Wainwright),252s 408 (252s Jarrow) | 2019-05-06 07:30 | 2019-05-06 11:30 | N | N | tie in L1 A and B trips to 352 and test | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 2.1TR (ENMAX 2) | 2019-05-06 08:00 | 2019-05-17 16:00 | N | N | MV bushing replacement | Transformer |  |  | For Information Only
ALTALINK | 133L (19s Wabamun - 133L697A) | 2019-05-06 08:00 | 2019-05-10 16:00 | N | N | replace 19s133 breaker | Line |  | Replace 19s133 Breaker to SF6 Type | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.1TR (ENMAX 24) | 2019-05-06 08:00 | 2019-05-10 16:00 | N | N | doble transformer and maintenance, and cable tests | Transformer |  |  | For Information Only
ENMAX | 36.1TR (ENMAX 36) | 2019-05-06 08:00 | 2019-05-09 16:00 | N | N | install NGR | Transformer |  |  | For Information Only
ENMAX | 162s 1GSU-XF-0001 (162s Beddington) | 2019-05-06 08:00 | 2019-05-07 16:00 | N | Y | transformer testing | Transformer |  | CEC testing requires 1-GSU-XF-0001 Current Transformer Isolation Monday, May 7th 8:00 to 16:00 for the purposes of Current Transformer testing | 240 kV, Pre-Condition, Restricts Generation, Contingency Requires Mitigation
ALTALINK | 89s T1 (89s Ellerslie) | 2019-05-06 08:30 | 2019-05-08 18:30 | N | Y | transformer maintenance | Transformer |  | 89s T1-B South Rad Leak, 89s T1-A Rad Valve Leak, 89s T1-C Oil Leak from Model 11 GDR, 89s T1-B wash | Overload, 500 kV
ALTALINK | 1203L (320p Keephills - 510s Sunnybrook) | 2019-05-06 09:30 | 2019-05-09 17:00 | N | Y | line maintenance | Line |  |  | Pre-Condition, Overload, 500 kV
ALTALINK | 310P T36 (310p Sundance),310P T37 (310p Sundance) | 2019-05-06 10:00 | 2019-05-09 16:30 | N | Y | migrate and commission all T37 & 310p414 protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN | Transformer |  | Migrate and commission all T37 & 310P414 protections, breaker, status, controls, alarms, metering and remote access to the new RTU and LAN. Replace 310P3489 air break control module, commission alarms control and status to new RTU. | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 840s 508 (840s McNeill) | 2019-05-06 11:30 | 2019-05-07 17:00 | N | Y | install cables in filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Station will be limited to 90 Mw Export and 90 Mw Import for the duration | Pre-Condition, Limits ATC
ALTALINK | 953s T2 (953s Lake Louise) | 2019-05-06 12:00 | 2019-05-09 17:00 | N | N | bushing replacement along with maintenance work on the tab changer | Transformer |  | - 25 & 69kV Bushing replacement along with maintenance work on the tab changer | For Information Only
ALTALINK | 296s T1 (296s Rosyth),296s T2 (296s Rosyth) | 2019-05-07 07:00 | 2019-05-07 18:00 | N | N | switch maintenance - 296s5, 296s11 | Transformer |  |  | For Information Only
ALTALINK | 223s T2 (223s Strome),223s 44 (223s Strome) | 2019-05-07 07:00 | 2019-05-07 18:00 | N | N | transformer maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 221s T1 (221s Sunken Lake) | 2019-05-07 07:00 | 2019-05-07 15:00 | N | N | customer work | Transformer |  |  | For Information Only
ALTALINK | 223s T1 (223s Strome),223s 43 (223s Strome) | 2019-05-07 07:30 | 2019-05-07 18:00 | N | N | customer work and transformer maintenance | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 299s T1 (299s Kingman),299s 732N (299s Kingman) | 2019-05-07 07:30 | 2019-05-07 17:30 | N | N | customer equipment maintenance | Transformer, Circuit Breaker |  |  | For Information Only
SUNCOR | 29EDD-18 Firebag | 2019-05-07 08:00 | 2019-05-24 15:00 | N | N | perform maintenance | Station |  | PERFORM Maint ON 29-752-102, 29-752-103, 29PS-55, 29PS-56, 29PS-59, 29PT-110, 29PLA-11A/B/C, 29PLA-137A/B/C, 29PT-100, 29-352-1601, 29VT-1601, 29PL3-73 THRU 76 1.29-752-102 a. Multilin C60 (29-752-102) b. Multilin T60 (29PT-100 A Prot.) 2. 29-752-103 a. Multilin C60 (29-752-102) b. Multilin T60 (29PT-100 A Prot.) 3. 29PT-100 a. Multilin T60 A Prot. b. SEL-387A B Prot. 4. 29-352-1601 a. SEL-351A There is no impact to powerflow, and the system will be fully isolated. Suncor has full redundancy for this system.
ALTALINK | 445s T1 (445s Elk River) | 2019-05-07 09:00 | 2019-05-07 10:30 | N | N | check 445s3, 445s11 switch operations | Transformer |  | Transfer T1 Loads To T2 in order to check 445s3, 445s11 Switch Operations | For Information Only
AESO-SC | OATI | 2019-05-07 13:00 | 2019-05-07 14:00 | N | N | firewall maintenance | SCInternal |  |  | For Information Only
Syncrude | TL-1 (Aurora - Aurora) | 2019-05-07 14:00 | 2019-05-07 20:00 | N | N | urgent outage to remove flagging tape wrapped around all the phases | Line |  | Urgent - TL-1 (72kV) Transmission Line Outage at Aurora G01 Substation is required to remove flagging tape wrapped around all the pahses. CB # 52-13, 52-14 and SW-17 will be operated. | For Information Only
Medicine Hat | MH69s1 MH69_10 (MH69s1 Power P Switchyard),MH69s1 MH69_21 (MH69s1 Power P Switchyard),MH69s1 MH69_31 (MH69s1 Power P Switchyard),MH69s1 MH69_42 (MH69s1 Power P Switchyard),MH69s1 69kV South Bus (MH69s1 Power P Switchyard) | 2019-05-08 06:00 | 2019-05-10 19:00 | N | N | switch gear upgrade | Bus, Circuit Breaker |  |  | For Information Only
ALTALINK | 352S Onoway,123L (19s Wabamun - 352s Onoway),19s 123 (19s Wabamun) | 2019-05-08 07:00 | 2019-05-09 18:00 | N | N | line move from structures 338 to 347, 69 kV breaker maintenance (19s123), & 19s125 switch maintenance | Line, Circuit Breaker, Station |  |  | Pre-Condition, For Information Only
ALTALINK | 123L (19s Wabamun - 352s Onoway),124L (19s Wabamun - 2739s Wabamun),133L (19s Wabamun - 133L697A),19s 72 (19s Wabamun),19s 49 (19s Wabamun),19s T10 (19s Wabamun),19S Wabamun 69kV Bus,19S Wabamun 138kV Bus | 2019-05-08 07:00 | 2019-05-09 18:00 | N | Y | replace 19s15 PT, 69kv bus LAs, 138kV strain insulators, remove 19s75 and it's related structure | Bus, Circuit Breaker, Transformer, Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
Medicine Hat | MH69s6 MH69_614 (MH69s6 Riverview) | 2019-05-08 07:00 | 2019-05-10 17:00 | N | N | maintenance | Circuit Breaker |  | Issue Transmission GOI to City of Medicine Hat Generation for their South Bus scheduled outage. | For Information Only
ATCO, ALTALINK | 530L (2085s Sheridan - 104s Watson Creek) | 2019-05-08 07:01 | 2019-05-08 10:00 | N | N | close open point 'F' between 530L & 6L530 (str. 530L71) | Line |  |  | Pre-Condition, For Information Only
ALTALINK | 56L (245s Seebe - 20s Ghost),20s 56 (20s Ghost),20s T5 (20s Ghost),20s Ghost 138 kV north bus,418L (20s Ghost - 418L193A),20s 452 (20s Ghost) | 2019-05-08 07:30 | 2019-05-15 18:30 | N | N | replace north bus insulators and conductor | Bus, Line, Circuit Breaker, Transformer |  | Replace North bus insulators and conductor Replace 20s102, replace 56L, 418L insulators, Replace 20s57 and 20s81 | Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D133 (ENMAX 25),ENMAX 25 B240-D138 (ENMAX 25),ENMAX 25 B240-D139 (ENMAX 25),ENMAX 25 B240-D142 (ENMAX 25),ENMAX 25 240kV North Bus | 2019-05-08 08:00 | 2019-06-24 10:00 | N | Y | urgent request to assist with the repairs to the faulted cable on 1080L | Bus, Circuit Breaker |  | Altalink will require a 240kV Bus outage @ 25s to assist with the repairs to the faulted cable on 1080L. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK, EPCOR | 430L (330P Genesee - 510S Sunnybrook) | 2019-05-08 08:00 | 2019-05-08 17:00 | N | Y | doble | Line |  |  | For Information Only
Syncrude | TL-2 (Aurora - Aurora) | 2019-05-08 08:00 | 2019-05-08 20:00 | N | N | assess leaking bushing on transformer (201-1-PTR72-363) | Line |  | G27 Substation Outage (assess Leaking bushing), Transformer (201-1-PTR72-363) - 72kV/ 4.16kV, Fed from TL-2 Feeder, Aurora. | For Information Only
ENMAX | 16.60L (ENMAX 34 - ENMAX 16) | 2019-05-08 08:00 | 2019-05-09 16:00 | N | N | HV breaker maintenance 34B69-16.60. | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 840s 509 (840s McNeill) | 2019-05-08 08:30 | 2019-05-09 17:00 | N | Y | install cables In filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Station will be limited to 90 Mw Export and 90 Mw Import for the duration | Pre-Condition, Limits ATC
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin),40s 804W (40s Wetaskiwin) | 2019-05-08 09:00 | 2019-05-09 15:30 | N | N | 18 kV breaker maintenance valves sweating | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 781L (172s Sherritt - 71s Lamoureux) | 2019-05-10 07:00 | 2019-05-10 13:00 | N | N | ICMP on structures # 2 & 4 | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
ATCO | 790s 703T (790s Poplar Hill) | 2019-05-10 08:00 | 2019-05-13 08:00 | N | Y | maintenance | Transformer |  | Planned Outage at the Poplar Hill Generating Station | Pre-Condition, Restricts Generation
ENMAX | 34.2TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2019-05-10 08:00 | 2019-05-10 16:00 | N | N | hotspot repair SW65, SW66 | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2019-05-11 07:00 | 2019-05-11 17:00 | N | Y | repair flashed insulators - urgent | Line |  | Component Replacement (multi str between 20-79) | 240 kV, Pre-Condition
ALTALINK | 122s T2 (122s Alberta Newsprint) | 2019-05-12 05:30 | 2019-05-16 18:15 | N | N | to replace the existing A87/T2 and B87/T2 protection modules | Transformer |  |  | 240 kV, For Information Only
CALPINE, PANC | CAVALIER Cavalier RTU/SCADA,CEC Calpine Energy Center RTU/SCADA | 2019-05-12 06:00 | 2019-05-12 07:00 | N | N | firewall and network switch upgrade | Terminal Equipment |  |  | Affects Visibility
ENMAX, ALTALINK | 21.1TR (ENMAX 21),21.4TR (ENMAX 21),21.80L (42s Sarcee - ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2019-05-12 08:00 | 2019-05-12 18:00 | N | Y | Spring substation washing | Line, Transformer |  | Altalink crew required to pull CAP VOLT PT fuses. Original outage date April 9th, outage cancelled due to switching error. | Firm Load Loss, Creates Radial Feeds
BCH | 5L71 (Mica Creek - Nicola),5L72 (Mica Creek - Nicola) | 2019-05-12 12:00 | 2019-05-12 13:00 | N | Y | MCA blackstart test | Line | BC Outage Peak RC COS: 1-00641238 AB Peak RC COS# : 1-00647633 (W>E), 1-00647635 (E>W) |  | For Information Only, 500 kV
ATCO | 9L01 (848s Dover - 951s Thickwood) | 2019-05-12 15:36 | 2019-05-22 17:00 | N | Y | forced out of service | Line |  |  | 240 kV, For Information Only
ENMAX | 16.63L (ENMAX 16 - ENMAX 36) | 2019-05-12 16:41 | 2019-05-25 17:00 | N | N | forced outage | Line |  |  | Pre-Condition
ENMAX | 36.5TR (ENMAX 36) | 2019-05-12 16:41 | 2019-05-25 16:00 | N | N | transformer forced outage | Transformer |  |  | For Information Only
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2019-05-13 01:23 | 2019-05-16 10:00 | N | Y | forced outage to repair structure | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 791s 701T (791s Rainbow Lake),791s 706 (791s Rainbow Lake) | 2019-05-13 07:00 | 2019-07-05 17:00 | N | N | refurbish transformer | Transformer, Circuit Breaker |  | Refurbish transformer | For Information Only
EPCOR | 330P SST1 (330P Genesee) | 2019-05-13 07:00 | 2019-05-13 17:00 | N | N | switching to support customer outage | Transformer |  |  | For Information Only
EPCOR | 987s C1 (987s Clover Bar) | 2019-05-13 07:00 | 2019-05-17 17:00 | N | N | 72 kV BF protection upgrade project | Shunts |  |  | For Information Only
AIRLIQUIDE | 408S 408S - Air Liquide Owned Substation | 2019-05-13 08:00 | 2019-05-13 17:00 | N | N | islanding scheme outage to make a change on the under-frequency relay (for compliance reasons) | Station |  |  | For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2019-05-13 08:00 | 2019-05-13 08:30 | N | N | transformer differential relay replacement, run new DC supply | Transformer |  | Transformer differential relay replacement. Run new DC supply. | For Information Only
Syncrude | ML-3 (D05 Syncrude - N11 Syncrude) | 2019-05-13 08:00 | 2019-05-14 20:00 | N | N | transformer maintenance | Line |  | N11 substation outage for transformer maintenance (1-0PTR72-211) | For Information Only
EPCOR | 72VN21 (Namao - 511s Victoria),Namao N725 (Namao) | 2019-05-13 08:00 | 2019-05-13 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2019-05-13 08:00 | 2019-05-14 16:00 | N | Y | HV switch maintenance | Line, Transformer |  | HV SW Maintenance SW80, SW81, SW82, SW86, MD-28.2TR. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.2TR (ENMAX 24) | 2019-05-13 08:00 | 2019-05-17 16:00 | N | N | doble test, maintenance, secondary cable tests, gas relay testing | Transformer |  | Doble test transformer. Transformer maintenance. Transformer Secondary Cable Tests. Gas Relay Testing | For Information Only
SUNCOR | 29EDD-1 Millennium,29EDD-1 952_102 (29EDD-1 Millennium),29EDD-1 952_101 (29EDD-1 Millennium),29PL9-16 (29EDD-1 Millennium - 29EDD-94 Voyageur) | 2019-05-13 08:00 | 2019-05-23 10:32 | N | Y | 5 years maintenance | Station, Circuit Breaker, Line |  | Perform maintenance and testing (5 year) breakers, CVT and surge arrestors: Varies from 4 to 16 hours depending on the stage of work. | 240 kV
ENMAX | 37.1TR (ENMAX 37) | 2019-05-13 08:30 | 2019-05-24 16:00 | N | N | transformer differential relay replacement | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2019-05-13 08:30 | 2019-06-11 18:00 | N | N | airbreak replacements 928s197W, 928s180N & 928s180X | Line |  | Airbreak Replacements 928s197W, 928s180N & 928s180X | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 14s T3 (14s Devon) | 2019-05-13 09:00 | 2019-05-13 15:45 | N | N | create open point A to allow for replacement of switches in outage 2 | Transformer |  | Create open point A to allow for replacement of switches in outage 2 | For Information Only
ALTALINK | 89s T2 (89s Ellerslie) | 2019-05-13 09:30 | 2019-06-06 13:24 | N | Y |  | Transformer |  | transformer maintenance: Re-gasket (T2-B), (T2-C) 240KV bushing leak, (T2-A) 240kV Bushing Leak, (T2-B) Conservator Valve Leaking | Pre-Condition, 500 kV
ALTALINK | 185L (415s Drywood - 379s Shell Canada Waterton) | 2019-05-13 10:00 | 2019-05-13 15:00 | N | N | high load move | Line |  | High load move crossing underneath line between structures # 209 & 210 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 953s T1 (953s Lake Louise) | 2019-05-13 12:00 | 2019-05-16 17:00 | N | N | bushing replacement along with deficiency work on 953s47 | Transformer |  | - 25 & 69kV Bushing replacement along with deficiency work on 953s47 | For Information Only
ALTALINK | 14s T1 (14s Devon) | 2019-05-13 16:00 | 2019-05-16 14:00 | N | N | switch and insulator replacement | Transformer |  | Use open point A created on the 13th to allow for replacement of switches: 14s5, 14s7, 14s8, 14s13, 14s18, 14s37 and insulators: pin type at 14s5, 14s6 sets strain insulators on the bypass bus, two sets on 14s37, one set above 14s5 | For Information Only
ALTALINK | 804L (86s Bigstone - 40s Wetaskiwin) | 2019-05-14 07:00 | 2019-05-15 18:00 | N | N | project reframing | Line |  | 803L/804L ULCM project reframing structure 29A | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 72RV6 (Rossdale - 511s Victoria),Rossdale RV722 (Rossdale) | 2019-05-14 08:00 | 2019-05-14 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2019-05-14 08:00 | 2019-05-14 16:00 | N | N | HV breaker maintenance 9B138-2.81. | Line |  |  | For Information Only
EPCOR | 803s L2405 (803s Lambton) | 2019-05-14 08:00 | 2019-05-14 17:00 | N | Y | doble | Circuit Breaker |  |  | Contingency Requires Mitigation
BCH | 5L71 (Mica Creek - Nicola) | 2019-05-14 09:00 | 2019-07-24 17:00 | N | Y | switchgear roof replacement project. BC Maintenance does not affect the Alberta ATC | Line | BC Outage Peak RC COS: 1-00649243 AB Peak RC COS# : 1-00650774 (W>E), 1-00650775 (E>W) | The other 5L71 outages (May 15 - Jun 28) and (May 29 - Jun 14) are combined with this record. | For Information Only, 500 kV
ATCO | 840s 510 (840s McNeill) | 2019-05-14 11:30 | 2019-05-14 15:30 | N | Y | install cables In filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Station will be limited to 90 Mw Export and 90 Mw Import for the duration | Pre-Condition, Limits ATC
ALTALINK | 719L (263s Strachan - 719L259C) | 2019-05-14 12:30 | 2019-05-14 14:30 | N | Y | open end 719L due to loss of both TPR circuits | Line |  | Open end 719L due to loss of both TPR circuits. Stability study completed. Outage will be for 15 - 30 minutes in the timeframe indicated. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1081L (17s Benalto - 281s Johnson) | 2019-05-14 19:50 | 2019-05-23 18:00 | N | Y | forced outage for structure repair | Line |  |  | 240 kV
VISIONREQ | 354s T3 (354s Summerview) | 2019-05-15 07:00 | 2019-05-16 18:00 | N | N | maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-05-15 07:00 | 2019-05-16 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 330P SST1 (330P Genesee) | 2019-05-15 07:00 | 2019-05-15 17:00 | N | N | repairs | Transformer |  |  | For Information Only
VISIONREQ | 354s T1 (354s Summerview) | 2019-05-15 07:00 | 2019-05-16 18:00 | N | N | maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-05-15 07:00 | 2019-05-16 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 100L (895s Suffield - 498s Tilley),895s 100 (895s Suffield) | 2019-05-15 07:00 | 2019-05-15 18:00 | N | N | urgent outage to repair clearance violation on 100L356B - 666L3 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 394s T1 (394s Empress) | 2019-05-15 07:45 | 2019-05-15 15:25 | N | N | investigate VR1 low oil alarm | Transformer |  |  | For Information Only
EPCOR | Victoria V722 (Victoria) | 2019-05-15 08:00 | 2019-05-15 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Contingency Requires Mitigation
Saskpower | SASK POWER P1C | 2019-05-15 17:00 | 2019-05-15 18:30 | N | Y | 13126 - CL - TC Keystone Caron maintenance (TOG# 2019-22) | Line |  |  | Limits ATC
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft W722 (Woodcroft),Woodcroft T1 (Woodcroft) | 2019-05-16 07:00 | 2019-05-16 17:00 | N | N | repair disconnect and refill breaker | Transformer, Circuit Breaker, Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | 240BA3 (814s Bellamy - 629s Argyll Transfer Station),1055L (816s Petrolia - 629s Argyll Transfer Station) | 2019-05-16 08:00 | 2019-05-16 17:00 | N | Y | doble | Line |  | Doble. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2019-05-16 08:00 | 2019-05-16 18:00 | N | N | HV breaker maintenance | Line |  | HV Breaker Maintenance. Retest breaker to get proper baseline results. | Pre-Condition, Overload
ALTALINK | 281s T1 (281s Johnson) | 2019-05-16 08:15 | 2019-05-16 16:45 | N | Y | investigate T1 leaks | Transformer |  | Investigate T1 leaks | 240 kV, Over/Under Voltage
ATCO | 840s 512 (840s McNeill) | 2019-05-16 08:30 | 2019-05-16 17:00 | N | N | install cables In filter bay, cap bank unavailable - CS2 & CSA functioning | Circuit Breaker |  | Install Cables In Filter Bay, Cap Bank Unavailable - CS2 & CSA Functioning | Pre-Condition, For Information Only
ALTALINK | 14s T3 (14s Devon) | 2019-05-16 14:05 | 2019-05-16 18:30 | N | N | close open point A | Transformer |  | Close open point A | For Information Only
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia),816s P2405 (816s Petrolia),816s P2406 (816s Petrolia) | 2019-05-17 08:00 | 2019-05-17 17:00 | N | Y | doble | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 739L (14s Devon - 305s Acheson),14s 739N (14s Devon) | 2019-05-17 08:15 | 2019-05-17 14:45 | N | N | complete replacement of 138kV insulators | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage
ATCO | 840s 511 (840s McNeill) | 2019-05-17 08:30 | 2019-05-17 17:00 | N | N | install cables in filter bay | Circuit Breaker |  | Install Cables In Filter Bay, Cap Bank Unavailable - CS1 & CSA Functioning | Pre-Condition, For Information Only
ALTALINK | 418s Ardenville RTU/SCADA | 2019-05-17 09:00 | 2019-05-17 10:00 | N | N | firewall software updates | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 243s Soderglen Wind Farm RTU/SCADA | 2019-05-17 13:00 | 2019-05-17 14:00 | N | N | firewall software update | Terminal Equipment |  |  | Affects Visibility
ENMAX | 5.5TR (ENMAX 5),5.7TR (ENMAX 5),1.84L (ENMAX 1 - ENMAX 5),2.82L (ENMAX 2 - ENMAX 5),ENMAX 5 5B138-5BT7 (ENMAX 5) | 2019-05-18 08:00 | 2019-05-19 18:00 | N | N | install PT structure and new 5PT138-Z31, SW97 maintenance | Line, Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2019-05-18 20:59 | 2019-05-23 18:00 | N | Y | forced outage due to fire | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L59 (789s Keg River - 7L59 tap),7L82 (788s Hotchkiss - 855s Hamburg),7L82 (855s Hamburg - 853s Ring Creek) | 2019-05-18 20:59 | 2019-05-23 18:00 | N | Y | forced outage due to fire | Line |  |  | For Information Only
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37) | 2019-05-19 08:00 | 2019-05-19 16:00 | N | Y | HV Breaker Maintenance 37B138-37.82 | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 987s SST2 (987s Clover Bar) | 2019-05-20 07:00 | 2019-05-24 17:00 | N | N | 72kV breaker fail protection upgrade project | Transformer |  |  | For Information Only
Syncrude | D05 D05 | 2019-05-20 08:00 | 2019-05-26 20:00 | N | N | N08 substation maintenance | Station |  | N08 Substation PM Outage for transformer maintenance, Transformer (1-PTR72-183) 72kV/ 13.8kV, Fed From ML-3 Feeder | For Information Only
ATCO | 786s SVC (786s High Level),7L133 (786s High Level - 828s Sulphur Point),7L59 (786s High Level - 7L59 tap),7L76 (786s High Level - 832s Blumenort) | 2019-05-20 08:47 | 2019-05-21 22:18 | N | Y | forced outage due to fire | Line, Shunts |  |  | Firm Load Loss, For Information Only
EPCOR | Rossdale T2 (Rossdale) | 2019-05-21 07:00 | 2019-05-31 17:00 | N | N | 15 kV Bus 5 Addition | Transformer |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR, ALTALINK | 1056L (89s Ellerslie - 629s Argyll Transfer Station),240BA2 (814s Bellamy - 629s Argyll Transfer Station) | 2019-05-21 07:00 | 2019-06-21 17:00 | N | Y | degassify 240BA2 cable | Line |  |  | 240 kV, Overload, Over/Under Voltage
ATCO | 729s 703T (729s Otauwau),729S 502VR,729s 144 kV BUS (729s Otauwau) | 2019-05-21 07:00 | 2019-07-10 17:30 | N | N | replacement work | Bus, Terminal Equipment, Transformer |  | Work being done: replace 703TCS with BKR 703, add 703A GSW & move 502VR 729S 144kv bus & 700PT1 OOS May 21 - May 28 729S 703T & 502VR OOS May 21 - July 4 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.2TR (ENMAX 39) | 2019-05-21 08:00 | 2019-05-22 16:00 | N | N | tapchanger inspection, check reversing switch, Filmax LTC filtration | Transformer |  |  | For Information Only
ALTALINK | 83s T1 (83s Taber) | 2019-05-21 08:00 | 2019-05-22 12:00 | N | Y | urgent outage to replace motor mech on 83s7, maintenance/cleaning on 83s7 switch | Transformer |  |  | Restricts Generation
EPCOR | 72CK12 (987s Clover Bar - Kennedale),72KN23 (Namao - Kennedale) | 2019-05-21 08:00 | 2019-05-24 17:00 | N | N | CVT replacement | Line |  | CVT Replacement | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | ENMAX 20 B138-20.82 (ENMAX 20),ENMAX 21 B138-20.82 (ENMAX 21),20.82L (ENMAX 21 - ENMAX 20) | 2019-05-21 08:00 | 2019-05-22 16:00 | N | N | HV breaker maintenance 21B138-20.82, 20B138-20.82 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32) | 2019-05-21 08:00 | 2019-06-04 16:00 | N | N | HV bushing replacement | Transformer |  |  | For Information Only
REDDEER | 194s T2 (194s South Red Deer) | 2019-05-21 09:00 | 2019-05-24 15:30 | N | N | maintenance | Transformer |  | power transformer 15T2 maintenance insulation power factor and capacitance testing | For Information Only
ALTALINK | 42s T1 (42s Sarcee) | 2019-05-21 11:15 | 2019-05-30 16:45 | N | Y | replace 42s40 with new SF6 breaker | Transformer |  | Replace 42s40 with new SF6 breaker. | 240 kV, Contingency Requires Mitigation
AESO-SC | OATI | 2019-05-21 18:00 | 2019-05-21 19:00 | N | N | Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ATCO | 786s SVC (786s High Level) | 2019-05-21 22:19 | 2019-06-11 16:00 | N | Y | forced out-of-service: forest fires | Shunts |  |  | Pre-Condition, For Information Only
ALTALINK | 72s C2 (72s Leismer),72s 3052 (72s Leismer) | 2019-05-22 08:00 | 2019-05-22 17:30 | N | N | C2 unbalanced alarm cycling | Shunts, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2019-05-22 08:30 | 2019-05-22 16:30 | N | Y | emergency perform settings changes on the pole discrepancy timer | Circuit Breaker |  | Emergency Work; Techs will be performing settings changes on the pole discrepancy timer on breaker 320p3152 as well as complete functionals, test - trip/reclose, live line, and follow end logic. AESO Operations Engineering has requested this work be done before lightningseason. This work will be completed with the protection outage submitted for 1202L B21/79/L21 SEL421 | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2019-05-22 09:00 | 2019-06-19 18:00 | N | N | component replacements between Structures #103 - 403 | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 103s T1 (103s Goose Lake),103s 1352 (103s Goose Lake),103s 1752 (103s Goose Lake),103s 138 kV BUS 1 (103s Goose Lake) | 2019-05-22 09:30 | 2019-05-22 16:30 | N | Y | emergency:top up low oil in bus PT (103s72) | Transformer, Circuit Breaker, Bus |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2019-05-23 08:00 | 2019-05-23 16:00 | N | N | maintenance | Transformer, Line |  | HV Breaker Maintenance 36B69-16.63/36.5TR. SF6 Gas sample. | For Information Only
ENMAX | 2.1TR (ENMAX 2) | 2019-05-23 08:00 | 2019-05-24 16:00 | N | N | maintenance | Transformer |  | tap changer inspection & check reversing switch & maintenance | For Information Only
BCH | 5L76 (Ashton Creek - Nicola) | 2019-05-23 09:00 | 2019-05-24 17:00 | N | Y | Annual Plan Request F20 | Line | BC Outage Peak RC COS: Not required. AB Peak RC COS# : Not required. | Annual Plan Request F20 - Daryl Cory, Mike Claxton PM INSPECTION: ACK 5D22, ACK 5D2CB5, ACK 5D1CB6
ALTALINK | 433L (291s Cochrane - T793s Horse Creek),793s 433 (793s Horse Creek) | 2019-05-23 09:30 | 2019-05-23 17:00 | N | N | investigate sync check relay | Circuit Breaker, Line |  | Techs to investigate sync check, perform functionals and may need to replace 25 - sync check relay | Firm Load Loss, Creates Radial Feeds
ATCO | 840s 502 (840s McNeill) | 2019-05-23 12:30 | 2019-05-23 14:30 | N | N | pre work for Mcneil T/A | Circuit Breaker |  | Pre work for Mcneil T/A, Connect AC & DC Supply to Breaker, Commission protection after installation of new DC Feed, will require the breaker to be isolated to operate the protection. No other reactive devices or filters will be out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages are such that this Device is required to maintain Transfer limits, this work will not proceed. | For Information Only
ATCO | 9L07 (2011s Dawes - 951s Thickwood) | 2019-05-23 14:00 | 2019-05-23 16:00 | N | Y | emergency: repair insulator string | Line |  |  | 240 kV
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s23 (391s Balzac) | 2019-05-23 21:00 | 2019-05-25 17:00 | N | Y | maintenance | Switch, Line |  |  | Restricts Generation
EPCOR | 72CK12 (987s Clover Bar - Kennedale),72NK23 (Kennedale - Namao),Kennedale K724 (Kennedale),Kennedale K723 (Kennedale),NamaoKN23 (Namao) | 2019-05-24 07:00 | 2019-05-24 17:00 | N | N | expanded zone for cable testing | Switch, Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
IMPERIALOIL | 9900s ST9903 (9900s Kearl) | 2019-05-24 08:00 | 2019-06-07 16:00 | N | N | P2215 Transformer replacement. ISD May 31, 2019. | Transformer
ATCO | 7L133 (786s High Level - 828s Sulphur Point) | 2019-05-24 08:00 | 2019-05-26 15:03 | N | Y | forced out-of-services: forest fires | Line |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2019-05-24 08:00 | 2019-05-24 16:00 | N | N | PCL Hydrovacing near line | Line |  | PCL Hydrovacing near line ducts to install tie backs for building at 9A St NW. | Firm Load Loss, Creates Radial Feeds
Syncrude | AURORA Aurora | 2019-05-24 08:00 | 2019-05-30 20:00 | N | N | G17 substation maintenance | Station |  | G17 Substation PM Outage, Transformer (201-2-PTR72-024) 72kV/ 4.16kV, Fed From MH2 Feeder at Aurora | For Information Only
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2019-05-24 10:00 | 2019-05-24 11:00 | N | Y | 240kV ring will briefly be open | Line |  | SEC maintenance outage. 25s 240kV ring will briefly be open between SW135 and 25B240-D132 while 25MD240-1GSU is being returned. | 240 kV, Pre-Condition, Overload
ENMAX | ENMAX 25 1GSU-XF-001 (ENMAX 25) | 2019-05-24 10:00 | 2019-05-28 16:00 | N | Y | switch maintenance & sub washing | Transformer |  | HV SW MD maint SW133, MD-1GSU. Doble 240kV 25MCT1, 25PT240-Z43. SW133 Corrective Substation Washing Z43. Crew lock on to Shephard LOTO | Restricts Generation
ATCO | 832s 701T (832s Blumenort) | 2019-05-25 08:00 | 2019-06-08 16:00 | N | N | transformer replacement (capital maintenance). ISD: June 1, 2019 | Transformer
ALTALINK, PANC | PCES02L (391s Balzac - PCES02S Balzac Power Station),391s 25 (391s Balzac) | 2019-05-25 08:00 | 2019-05-25 17:00 | N | Y | install grading capacitors | Circuit Breaker, Line |  |  | Pre-Condition
ENMAX, ALTALINK | 7.2TR (ENMAX 7),7.82L (42s Sarcee - ENMAX 7),ENMAX 7 B138-7BT3 (ENMAX 7) | 2019-05-25 08:00 | 2019-05-25 18:00 | N | Y | substation washing | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 26.81L (ENMAX 32 - ENMAX 26) | 2019-05-26 06:00 | 2019-05-27 16:00 | N | N | high line removing streetlights from corner of Deerfoot Tr. & Douglasdale Blvd. | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 1L274 (1D2L274 - 1D3L274) | 2019-05-26 07:30 | 2019-05-26 19:30 | N | Y | replace structure | Line |  |  | Pre-Condition, Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9),ENMAX 31 B138-31CAP (ENMAX 31) | 2019-05-26 08:00 | 2019-05-26 18:00 | N | N | corrective doble, repair switches | Line, Transformer, Circuit Breaker |  |  | Pre-Condition
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft W722 (Woodcroft) | 2019-05-27 07:00 | 2019-05-27 17:00 | N | N | Repair disconnect and refill breaker | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
EPCOR | 987s T1 (987s Clover Bar) | 2019-05-27 07:00 | 2019-05-29 17:00 | N | Y | commissioning of Anti- Islanding upgrade project | Transformer |  | Commissioning of Anti- Islanding Upgrade Project | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
SUNCOR | 29EDD-1 Millennium,29EDD-1 952_104 (29EDD-1 Millennium) | 2019-05-27 08:00 | 2019-06-02 18:00 | N | Y | 5 years maintenance | Station, Circuit Breaker |  | Perform maintenance and testing (5 year) breakers, CVT and surge arrestors: Varies from 4 to 16 hours depending on the stage of work | 240 kV
ENMAX | 39.1TR (ENMAX 39) | 2019-05-27 08:00 | 2019-05-31 16:00 | N | N | transformer maintenance. | Transformer |  | Doble test transformer. Transformer Maintenance. Transformer Secondary Cable Tests.Gas Relay Testing. Check reversing switch. | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2019-05-27 08:00 | 2019-05-28 16:00 | N | N | tap-changer inspection & check reversing switch. | Transformer | Tapchanger inspection. Check reversing switch. |  | For Information Only
EPCOR | Rossdale T2 (Rossdale) | 2019-05-27 08:00 | 2019-05-31 17:00 | N | N | doble | Transformer |  |  | For Information Only
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2019-05-27 08:00 | 2019-05-27 16:00 | N | N | bushing replacement | Line |  | HV Bushing Replacement. Bus outage required to install high voltage busshings. 26.81L oos | Firm Load Loss, Creates Radial Feeds
ENMAX | 15.1TR (ENMAX 15) | 2019-05-27 08:00 | 2019-05-29 16:00 | N | N | repair station service | Transformer |  | Corrective. Repair station service NC drawer. Back-up generator required for station load. | For Information Only
ATCO | 840s 516 (840s McNeill) | 2019-05-27 08:30 | 2019-05-27 13:00 | N | N | install AC & DC cable pre work | Circuit Breaker |  | 840S McNeill RS1 BKR 516 Install AC & DC Cable Pre work for Mcneil T/A, Connect AC & DC Supply to Breaker, Commission protection after installation of new DC Feed, will require the breaker to be isolated to operate the protection. No other reactive devices or filters will out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages are such that this Device is required to maintain Transfer limits, this work will not proceed. | For Information Only
REDDEER | 209s T1 (209s Timberlands) | 2019-05-27 09:00 | 2019-05-29 15:30 | N | N | warranty routine maintenance | Transformer |  |  | For Information Only
ATCO | 881s 701T (881s Sturgeon) | 2019-05-27 09:00 | 2019-05-31 17:00 | N | Y | replace CTs | Transformer |  |  | Restricts Generation
ALTALINK | 747L (99s North St. Albert - 747L3A) | 2019-05-27 09:30 | 2019-05-30 17:00 | N | N | work on structures | Line |  | Complete work on structures 34, 50, 51. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 233s T1 (233s Beamer) | 2019-05-27 10:00 | 2019-05-31 10:00 | N | N | CT replacement on T1, 233s35 replacement | Transformer |  | CT replacement on T1, 233s35 replacement, change 233s35 to X winding from Y winding. | For Information Only
ALTALINK | 13s T2 (13s Deerland) | 2019-05-27 10:15 | 2019-05-30 17:45 | N | Y | transformer maintenance | Transformer |  | transformer maintenance: Blown H1 LA, LTC FER/MR (maint) 245/145kV, LTC FER/MR (doble)245/145kV3, 1" sample valve sweating, Rad Valves Sweating | 240 kV, Overload, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 535s T1 (535s Joffre) | 2019-05-27 11:15 | 2019-05-30 17:45 | N | N | bushing replacement | Transformer |  |  | For Information Only
ATCO | 840s 515 (840s McNeill) | 2019-05-27 14:00 | 2019-05-27 17:00 | N | N | install AC & DC cable pre work | Circuit Breaker |  | 840S McNeill RS2 BKR 515 Install AC & DC Cable Pre work for McNeill T/A, Connect AC & DC Supply to Breaker, Commission protection after installation of new DC Feed, will require the breaker to be isolated to operate the protection. No other reactive devices or filters will out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages are such that this Device is required to maintain Transfer limits, this work will not proceed. | For Information Only
ALTALINK | 795L (121s Brooks - 421s Hays) | 2019-05-28 07:00 | 2019-05-28 16:00 | N | N | high load move crossing underneath line between Structures # 169 & 170 | Line |  | High load move crossing underneath line between Structures # 169 & 170 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 330p 807 (330p Genesee),430L (330P Genesee - 510S Sunnybrook) | 2019-05-28 08:00 | 2019-05-31 17:00 | N | N | breaker maintenance | Line, Circuit Breaker |  |  | For Information Only
ENMAX | 9.83L (ENMAX 43 - ENMAX 9) | 2019-05-28 08:00 | 2019-05-29 16:00 | N | N | sheath testing and oil sampling | Line |  |  | Pre-Condition
ENMAX | 9.3TR (ENMAX 9),2.81L (ENMAX 2 - ENMAX 9),9.83L (ENMAX 43 - ENMAX 9),9.2 TR (ENMAX 9) | 2019-05-28 08:00 | 2019-05-31 18:00 | N | N | maintenance on HV SW MD | Transformer, Line |  | HV SW MD maint SW80, SW81, SW82, SW83, SW84, SW87, SW88, SW90, MD-9.2TR, MD-9.3TR. Substation - Circuit Breaker, Inspection - 9B8-9.2TR. Hotspot SW82, 9B138-9.83 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 840s 514 (840s McNeill) | 2019-05-28 08:30 | 2019-05-28 12:00 | N | N | pre work for McNeil T/A | Circuit Breaker |  | Pre work for Mcneil T/A, Connect AC & DC Supply to Breaker, Commission protection after installation of new DC Feed, will require the breaker to be isolated to operate the protection. No other reactive devices or filters will out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages are such that this Device is required to maintain Transfer limits, this work will not proceed. | Pre-Condition
ATCO | 840s 513 (840s McNeill) | 2019-05-28 12:30 | 2019-05-28 16:30 | N | N | pre work for McNeil T/A | Circuit Breaker |  | Pre work for Mcneil T/A, Connect AC & DC Supply to Breaker, Commission protection after installation of new DC Feed, will require the breaker to be isolated to operate the protection. No other reactive devices or filters will out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages are such that this Device is required to maintain Transfer limits, this work will not proceed. | Pre-Condition
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2019-05-28 15:00 | 2019-05-28 16:00 | N | Y | maintenance | Line |  | SEC maintenance outage. 25s 240kV ring will briefly be open between SW135 and 25B240-D132 while 25MD240-1GSU is being isolated. | 240 kV, Pre-Condition
ALTALINK | 223s T2 (223s Strome) | 2019-05-29 07:30 | 2019-07-05 18:00 | N | N | Urgent 223s T2 H3 Bushing Replacement | Transformer |  |  | For Information Only
ALTALINK | 223s T2 (223s Strome) | 2019-05-29 07:30 | 2019-05-29 17:30 | N | N | urgent 223s T2 H3 bushing replacement | Transformer
ALTALINK | 353s T1 (353s Plamondon) | 2019-05-29 07:45 | 2019-05-30 12:45 | N | N | VR1 maintenance & doble & filter pack leaking | Transformer
ALPAC | 282s Grassland (Alpac) RTU/SCADA | 2019-05-29 08:00 | 2019-05-29 11:00 | N | N | firmware update | Terminal Equipment |  |  | Affects Visibility
ENMAX | 13.3TR (ENMAX 13) | 2019-05-29 08:00 | 2019-05-30 16:00 | N | N | tap changer inspection & check reversing switch & oil sampling | Transformer
ACCIONA | 226S Magrath DVAr | 2019-05-29 08:00 | 2019-12-06 19:00 | N | N | Suncor Magrath (SCR2) MVAr capability | Terminal Equipment |  |  | For Information Only
ATCO | 840s 506 (840s McNeill) | 2019-05-29 08:30 | 2019-05-30 17:00 | N | N | install cables in filter bay | Circuit Breaker |  | Filter FA4 out of service to Install Cables In Filter Bay No other reactive devices or filters will out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages & conditions are such that this Device is required to maintain Transfer limits, this work will not proceed and will be cancelled. | Pre-Condition
ATCO | 840s 507 (840s McNeill) | 2019-05-29 08:30 | 2019-05-30 16:00 | N | N | CSA install PT and new cable for protection upgrade | Circuit Breaker |  | 840S McNeill BKR 507 CSA Install PT Shared Cap Bank unavailable Install new cable for protection upgrade No other reactive devices or filters will out of service at the same time. This does not affect Transfer capability of Converter If Bulk Electric System voltages are such that this Device is required to maintain Transfer limits, this work will not proceed. | Pre-Condition
ATCO | 7L59 (786s High Level - 789s Keg River) | 2019-05-29 18:27 | 2019-06-10 18:00 | N | Y | forced outage due to fires in the area. | Line |  | 7L59 (786s-890s-789s) forced out due to fires in the area.
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock) | 2019-05-29 21:44 | 2019-06-05 18:28 | N | Y | forced outage due to fires in the area. | Line |  | 12L41 (510s-939s) forced outage due to fires in the area. | 500 kV
ATCO | 9L15 (834s Wesley Creek - 876s Brintnell) | 2019-05-29 23:57 | 2019-06-11 15:44 | N | Y |  | Line |  | 9L15 (876s-834s) forced outage due to fires in the area. | 240 kV
ATCO | 9L56 (720s Wabasca - 732s Mitsue) | 2019-05-30 02:13 | 2019-06-11 14:45 | N | Y | forced outage due to fires in the area. | Line |  | 9L56 (720s-876s) forced outage due to fires in the area. | 240 kV, Creates Radial Feeds
EPCOR | 987s C2402 (987s Clover Bar) | 2019-05-30 07:00 | 2019-05-31 17:00 | N | Y | commissioning of anti-islanding upgrade project | Circuit Breaker |  | Commissioning of Anti- Islanding Upgrade Project | 240 kV, Contingency Requires Mitigation
REDDEER | 247s T1 (247s Piper Creek),247s T2 (247s Piper Creek) | 2019-05-30 09:00 | 2019-06-10 09:30 | N | N | maintenance and power factor testing | Transformer |  | power transformer 17T1 oil testing and weeping oil repairs.17T2 power factor testing. Includes all 25kV feeder circuit breaker testing preventative maintenance. | For Information Only
ATCO | 754s 702C (754s Ksituan River),754s 702 (754s Ksituan River) | 2019-05-31 07:00 | 2019-06-03 17:00 | N | N | breaker fail testing | Shunts, Circuit Breaker |  | Breaker fail testing | Pre-Condition, Over/Under Voltage
ATCO, ALTALINK | 807AL (402s Shell Expansion I - 807L tap),807L (233s Beamer - 807L tap),807L (410s Josephburg - 807L tap),233s 6 (233s Beamer),233s Beamer 138 kV Bus 1 | 2019-05-31 10:00 | 2019-06-12 13:00 | N | Y | replace equipment | Line, Bus, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 741s 701 (741s Fox Creek),7L90 (813s Little Smoky - 7L90D2) | 2019-05-31 10:00 | 2019-05-31 16:00 | N | N | emergency: breaker has low gas alarm | Line, Circuit Breaker |  | We have 2 poles on BKR 701 in Low SF6 Gas alarm. Not repairing may lead to BKR 701 not being able to clear a fault on the line. I have sent notice to Altalink also. | Pre-Condition, Overload
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2019-06-02 08:00 | 2019-06-02 18:00 | N | N | breaker maintenance | Line |  | HV Breaker Maintenance. Retest breaker to get proper baseline results. Original outage May 16th, cancelled due to inclement weather | Pre-Condition, Overload
EPCOR | 72MG16 (Meadowlark - Garneau) | 2019-06-03 07:00 | 2019-06-08 17:00 | N | N | protection upgrade | Line |  | 72kV BF Protection Upgrade Project | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale R724 (Rossdale) | 2019-06-03 07:00 | 2019-07-05 17:00 | N | N | breaker replacement | Circuit Breaker |  | Breaker Replacement | Firm Load Loss, Creates Radial Feeds
BCH | 5L52 (Ingledow - Custer) | 2019-06-03 07:00 | 2019-06-07 17:00 | N | Y | BC work | Line |  |  | Limits ATC, 500 kV
ALTALINK | 535s 152 (535s Joffre) | 2019-06-03 07:30 | 2019-06-04 16:30 | N | N | CT cable replacements | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 2.82L (ENMAX 2 - ENMAX 5),ENMAX 5 B138-2.82 (ENMAX 5) | 2019-06-03 08:00 | 2019-06-04 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | HV Breaker Maintenance 5B138-2.82 (HLR) | Pre-Condition
ENMAX | 41.2TR (ENMAX 41) | 2019-06-03 08:00 | 2019-06-19 16:00 | N | N | transformer differential relay panel replacement | Transformer |  |  | For Information Only
ENMAX | 33.84L (ENMAX 43 - ENMAX 33) | 2019-06-03 08:00 | 2019-06-06 16:00 | N | N | northstar installing water line | Line |  | Northstar Installing Water line | Firm Load Loss, Creates Radial Feeds
BLACKSPRING | 485s DVAR1 (485s Blacksprings),485s DVAR2 (485s Blacksprings) | 2019-06-03 08:00 | 2019-06-07 17:00 | N | N | inverter replacement | Shunts |  |  | For Information Only
EPCOR | 330p 808 (330p Genesee),8L10 (330P Genesee - Fording Coal Mine) | 2019-06-03 08:00 | 2019-06-05 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 805s T3 (805s Jasper) | 2019-06-03 08:00 | 2019-07-06 06:59 | N | Y | bushing replacement | Transformer |  |  | 240 kV
ENMAX | 3.3TR (ENMAX 3) | 2019-06-03 08:00 | 2019-06-07 16:00 | N | N | tapchanger inspection. | Transformer |  | Tapchanger inspection. Reinhausen. Check reversing switch. Oil sampling MT, TC | For Information Only
ENMAX | 9.3TR (ENMAX 9) | 2019-06-03 08:00 | 2019-06-07 16:00 | N | N | transformer testing. | Transformer |  | Doble test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch | For Information Only
Syncrude | MH2 (Aurora - Aurora) | 2019-06-03 08:00 | 2019-06-09 20:00 | N | N | maintenance | Line |  | G19 Substation PM Outage (Maintenance Work), Transformer (201-2-PTR72-023) 72kV/13.8 kV, Fed From MH-2 Feeder at Aurora | For Information Only
ALTALINK | 74s T2 (74s Janet) | 2019-06-03 08:45 | 2019-06-03 17:15 | N | Y | urgent outage to repair oil leak | Transformer |  | Urgent outage to repair 74s T2 Oil Leak | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 422S Westwood | 2019-06-03 10:00 | 2019-06-06 18:00 | N | N | replace 25kv bus and maintenance | Station |  | 422s replace 25kv bus, T1(TX18799) sweating manhole's, doble, maintenance SIE/MR,VRC,138/26 | For Information Only
AESO-SC | DT | 2019-06-03 10:00 | 2019-06-03 12:00 | N | N | DT outage | SCInternal |  |  | For Information Only
ALTALINK | 942L (71s Lamoureux - 681s Bannerman) | 2019-06-03 10:30 | 2019-06-06 17:00 | N | Y | replace 71s51 VTs | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s T1 (63s Red Deer) | 2019-06-03 10:30 | 2019-06-06 18:00 | N | Y | transformer maintenance | Transformer |  | tansformer maintenance, doble, hydran sensor replacement | 240 kV, Pre-Condition, Overload
ALTALINK | 834L (384s Keystone - 320p Keephills) | 2019-06-03 12:00 | 2019-06-13 18:00 | N | N | component replacements | Line |  | Component replacements 834L (Range- 834L320P East 2nd Bay /Line Str's 211- 23) | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH69S -16 631- BRK-10 (MH69S-16) | 2019-06-03 14:00 | 2019-06-03 16:00 | N | N | testing | Circuit Breaker |  | testing | For Information Only
ALTALINK | 74s C3 (74s Janet),74s 102 (74s Janet) | 2019-06-03 17:15 | 2019-06-19 16:30 | N | Y | forced out-of-service | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 205S Castle Rock Ridge | 2019-06-04 07:00 | 2019-06-05 17:00 | N | N | annual substation maintenance | Station |  |  | Restricts Generation
CRRLP, ALTALINK | Castle Rock Ridge | 2019-06-04 07:00 | 2019-06-05 17:00 | N | N | substation outage | Unit
ALTALINK | 42s C2 (42s Sarcee),42s C3 (42s Sarcee),42s 76 (42s Sarcee) | 2019-06-04 07:45 | 2019-06-05 16:45 | N | Y | Maintain 240kV SF6 cap bank breaker | Circuit Breaker, Shunts |  |  | 240 kV
Syncrude | MH1 (Aurora - Aurora) | 2019-06-04 08:00 | 2019-06-10 20:00 | N | N | maintenance | Line |  | G19 Substation PM Outage (Maintenance Work), Transformer (201-1-PTR72-015) 72kV/4.16 kV, Fed From MH-1 Feeder at Aurora | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2019-06-04 08:00 | 2019-06-07 12:00 | N | N | forced outage | Transformer
ENMAXEC | 383S Kettles Hill Windfarm | 2019-06-04 08:00 | 2019-06-05 18:00 | N | Y | DVAr maintenance | Station |  |  | For Information Only
Syncrude | AL-1 (D05 Syncrude - Aurora) | 2019-06-04 09:00 | 2019-06-04 22:00 | N | Y | install marker ball and clean the conductors | Line |  | "AL-1 Transmission Line (260kV) Outage PM (Install Marker Ball and clean the conductors) CB # 517 and 519 at D05 Substation will be operated to isolated AL-1 Line. CB # 211 and 213 at G01 Substation will be operated to isolated AL-1 Line. " | 240 kV, Creates Radial Feeds
ATCO | 844s 702T (844s AEC Mill) | 2019-06-04 12:00 | 2019-06-04 21:00 | N | N | bird mitigation on 702T | Transformer |  | Bird Mitigation on 702T, coordinated with Customer outage Permit # 2-48830
ATCO | 844s 701T (844s AEC Mill) | 2019-06-04 12:00 | 2019-06-04 21:00 | N | N | check leaks on 701T | Transformer |  | Check Leaks on 701T, coordinated with Customer outage Permit # 2-48830
CNRL | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-06-05 07:00 | 2019-06-05 18:00 | N | Y | de-energized to allow for construction work in proximity of powerline | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 12.2TR (ENMAX 12),833L (ENMAX 2 - ENMAX 12) | 2019-06-05 08:00 | 2019-06-06 16:00 | N | Y | HV breaker maintenance and Doble | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 40.1TR (ENMAX 40) | 2019-06-05 08:00 | 2019-06-13 16:00 | N | N | MV bushing replacement | Transformer |  |  | For Information Only
Saskpower, ATCO, ALTALINK | 840S McNeill Station,830L (562s Cypress - 840s McNeill Station),9LS1M (840s McNeil - Swift Current) | 2019-06-05 08:00 | 2019-08-15 12:59 | Y | Y | protection upgrade | Line, Station |  | 2019 McNeill Shutdown for Protection Upgrade Install, 25KV Protection Upgrade Project. Once started will not be able to return to service until project is completed. | Limits ATC
Syncrude | AL-1 (D05 Syncrude - Aurora),Aurora 211 (Aurora),Aurora 213 (Aurora),D05 517 (D05 Syncrude),D05 519 (D05 Syncrude) | 2019-06-05 10:30 | 2019-06-10 22:00 | N | Y | urgent repairing dead end insulator | Line, Circuit Breaker |  | Urgent - Significnat Outage - AL-1 Transmission Line (260kV) Repairing dead end insulator | 240 kV, Creates Radial Feeds
BCH | Natal T4 (BCH Natal) | 2019-06-05 11:00 | 2019-06-06 11:00 | N | Y | BC last minute planned outage | Transformer | BC Outage Peak RC COS: 1-00653498 |  | Pre-Condition
ALTALINK | 995L (17s Benalto - 995AL tap) | 2019-06-05 23:00 | 2019-06-06 07:00 | N | Y | commission new airbreak control module and supervisory control of switch 17s995N | Line |  | commission new airbreak control module and supervisory control of switch 17s995N | 240 kV, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2019-06-05 23:00 | 2019-06-06 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2019-06-06 03:00 | 2019-06-06 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
CNRL | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-06-06 07:00 | 2019-06-08 18:00 | N | Y | de-energized to allow for construction work in proximity of powerline | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2019-06-06 07:00 | 2019-06-10 15:39 | N | N | urgent repairs | Line |  | Urgent Repairs - Landowner made contact with steel structure 127. Structure Damage | 240 kV, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 843s 601T (843s Bigknife Creek) | 2019-06-06 08:00 | 2019-06-06 17:00 | N | N | leak repair and oil filling of metering tank | Transformer |  | Metering Tank was found to be leaking. Need to repair and refill as the hotter the weather the more load will be put on the cooling tower and the more likely there will be a failure. It is unknown what the oil level is currently in the metering tank. Suspect bushing o-ring needs replaced and tank can then be topped up with oil. | For Information Only
ALTALINK | 1075L (132s Ware Junction - 28s West Brooks),28s 12 (28s West Brooks),28s 41 (28s West Brooks) | 2019-06-06 10:00 | 2019-06-13 08:00 | N | Y | replace 28s41, linked to 28s 240kV Bus 1(1075L) | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 135s T1 (135s Conrad),135s T2 (135s Conrad) | 2019-06-06 12:30 | 2019-06-17 10:30 | N | N | connection of new T2 and 25kV Bus 2 switchgear to system | Transformer |  | connection of new T2 and 25kV Bus 2 switchgear to system, 135s607 to be renamed to 135s689 | For Information Only
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2019-06-07 07:00 | 2019-06-10 17:00 | N | Y | washing program | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 135s T2 (135s Conrad) | 2019-06-07 08:00 | 2019-06-21 16:00 | N | N | P1766. New transformer. ISD: June 14, 2019 | Transformer
ENMAX | 6.82L (ENMAX 6 - ENMAX 41),ENMAX 41 B138-6.82 (ENMAX 41) | 2019-06-08 08:00 | 2019-06-08 13:00 | N | N | transformer differential relay panel replacement | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 41 B138-33.83 (ENMAX 41) | 2019-06-08 13:00 | 2019-06-08 18:00 | N | N | transformer differential relay panel replacement | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
CNRL | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-06-09 07:00 | 2019-06-10 18:00 | N | Y | de-energized to allow for construction work in proximity of powerline | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.5TR (ENMAX 36),16.63L (ENMAX 16 - ENMAX 36) | 2019-06-09 08:00 | 2019-06-14 13:00 | N | N | breaker maintenance | Line, Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 535s T2 (535s Joffre) | 2019-06-09 09:00 | 2019-06-09 11:00 | N | N | switching low side breaker | Transformer |  |  | For Information Only
EPCOR | Rossdale RR723 (Rossdale) | 2019-06-10 06:00 | 2019-06-10 10:00 | N | N | emergency repair on control wiring | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
EPCOR | Meadowlark M723 (Meadowlark) | 2019-06-10 07:00 | 2019-06-15 17:00 | N | N | protection upgrade project | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss
EPCOR | 987s T2 (987s Clover Bar) | 2019-06-10 07:00 | 2019-06-17 07:00 | N | Y | line maintenance & upgrades | Transformer |  | Line Maintenance & Upgrades | 240 kV, Firm Load Loss, Creates Radial Feeds
EPCOR | 72NW15 (Namao - Woodcroft) | 2019-06-10 07:00 | 2019-07-08 17:00 | N | N | line maintenance & upgrades | Line |  | Line Maintenance & Upgrades | Firm Load Loss, Creates Radial Feeds
ATCO | 2075s ACF11 (2075s Newell) | 2019-06-10 07:00 | 2019-06-14 17:30 | N | Y | maintenance, inspection, PLC firmware upgrades | Shunts |  | Maintenance on 901T, ACF11 Inspection, PLC Firmware Upgrades, Relay Firmware Upgrades, & Glycol Bypass Calibration SVC Redundancy Lost | 240 kV, For Information Only
SUNCOR | 29EDD-1 29EDD1s652 (29EDD-1 Millennium),29EDD-1 29EDD1s552 (29EDD-1 Millennium),29PL9-3 (29EDD-1 Millennium - 29EDD-3) | 2019-06-10 08:00 | 2019-06-20 15:00 | N | N | forced outage: troubleshooting | Circuit Breaker, Line |  | GTG-6 forced outage. Troubleshooting. | For Information Only
ENMAX | 13.82L (ENMAX 22 - ENMAX 13),ENMAX 22 B138-13.82 (ENMAX 22) | 2019-06-10 08:00 | 2019-06-11 16:00 | N | N | HV breaker maintenance | Line, Circuit Breaker |  | HV Breaker Maintenance 22B138-13.82. HLR. 22B138-13.82 Control wiring modification | Firm Load Loss, Creates Radial Feeds
Syncrude | AURORA Aurora | 2019-06-10 08:00 | 2019-06-15 20:00 | N | N | G41 substation outage and transformer maintenance | Station |  | G41 Substation Outage (Replace Leaky Bushing), Transformer (201-1-PTR72-372) 72kV/ 4.16 kV, Fed From TL1 Transmission line out of G01 Substaion, Aurora | For Information Only
ENMAX | 9.3TR (ENMAX 9) | 2019-06-10 08:00 | 2019-06-11 16:00 | N | N | tapchanger inspection and transformer maintenance | Transformer |  |  | For Information Only
EPCOR | E511s VictoriaT4 (511s Victoria) | 2019-06-10 08:00 | 2019-06-14 07:59 | N | N | doble | Transformer |  |  | For Information Only
EPCOR | Rossdale T3 (Rossdale) | 2019-06-10 08:00 | 2019-06-14 07:59 | N | N | doble | Transformer |  |  | For Information Only
EPCOR | 330P 12TC2 (330p Genesee),330p 809 (330p Genesee) | 2019-06-10 08:00 | 2019-06-18 17:00 | N | Y | DGA upgrade | Transformer, Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss, 500 kV
ATCO | 7L53 (7L53 tap - 700s Bonnyville),700s 702 (700s Bonnyville) | 2019-06-10 09:00 | 2019-06-13 16:00 | N | N | complete breaker maintenance | Circuit Breaker, Line |  | Complete Breaker Maintenance | Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee),330p 1208 (330p Genesee),330p 1209 (330p Genesee) | 2019-06-10 09:00 | 2019-06-14 17:00 | N | Y | enable single pole tripping | Line, Circuit Breaker |  | Relay Settings changes to 1209L protection to enable single pole tripping | Pre-Condition, Overload, 500 kV
ALTALINK | 215L (38s East Edmonton - 286s Yasa),38s 215N (38s East Edmonton) | 2019-06-10 10:15 | 2019-06-10 15:45 | N | N | replace CT cover (38s215N) | Circuit Breaker, Line |  | replace CT cover (38s215N) | Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale BR722 (Rossdale) | 2019-06-11 06:00 | 2019-06-11 10:00 | N | N | emergency repair on control wiring | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 394s T2 (394s Empress) | 2019-06-11 07:00 | 2019-10-03 18:00 | N | N | replace bus work with new switchgear building | Transformer | 394s T2 (394s Empress) |  | For Information Only
ALTALINK | 905L (19s Wabamun - 37s North Calder) | 2019-06-11 07:00 | 2019-06-14 18:00 | N | Y | Urgent Repairs - Replace Structure #132 | Line |  | Foundation of structure corroded away. | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
Medicine Hat | MH-16L (MH69S-2 - MH69S-16),MH69s2 MH69_224 (MH69s2 North Industrial) | 2019-06-11 07:00 | 2019-06-13 08:00 | N | Y | replace pole and line maintenance | Circuit Breaker, Line |  |  | Restricts Generation
ENMAX | 41.1C (ENMAX 41) | 2019-06-11 08:00 | 2019-06-11 13:00 | N | N | transformer differential relay panel replacement | Shunts |  |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2019-06-11 08:00 | 2019-06-13 16:00 | N | N | T-60 relay CPU upgrade, check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 511s 4852 (511s Crossings) | 2019-06-11 08:00 | 2019-06-11 16:30 | N | Y | replacement of relay contactor and operate 511s74 airbreak | Circuit Breaker | Wire in a replacement K03 relay contactor in the control cabinet for 511s74 airbreak and operate the airbreak with no current flowing through it, will see 511s74 airbreak open and close during testing |  | 240 kV
ATCO | 828s 701T (828s Sulphur Point) | 2019-06-11 09:00 | 2019-06-16 16:00 | N | N | bypass switch replacement | Transformer |  | 828S Bypass Switch Replacement. Install Lamicoids for new 501VR by-pass switches. Perform electrical tests on 501VRA, 501VRB & 501VRX. Record nameplate data. | For Information Only
ATCO | 828s 507C1 (828s Sulphur Point),828s 507C2 (828s Sulphur Point),828s 507 (828s Sulphur Point) | 2019-06-11 10:00 | 2019-06-16 17:30 | N | N | BKR 507 CT ratio change | Circuit Breaker, Shunts |  | BKR 507 CT ratio change. 507C1 and 507C2 remain out of service for duration of work. | For Information Only
ENMAX | ENMAX 41 B138-41BT3 (ENMAX 41) | 2019-06-11 13:00 | 2019-06-11 18:00 | N | N | transformer differential relay panel replacement | Circuit Breaker |  |  | For Information Only
ENMAX | 23.3TR (ENMAX 23) | 2019-06-12 08:00 | 2019-06-13 16:00 | N | N | transformer inspection and maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 937L (102s Langdon - 5s East Calgary) | 2019-06-12 09:00 | 2019-06-14 18:00 | N | Y | replacing insulators | Line |  | replacing insulators between Structures #50 - 64 | 240 kV, Pre-Condition, Overload
ALTALINK | 233s T2 (233s Beamer),708L (233s Beamer - 708L88N),735L (171s Redwater - 233s Beamer),171s 735X (171s Redwater),233s 708X (233s Beamer),233s 735N (233s Beamer),233s Beamer 138 kV Bus 2 | 2019-06-12 13:00 | 2019-06-28 13:00 | N | N | component replacement | Circuit Breaker, Bus, Transformer, Line |  | Insulator replacement, CT replacement on T2, 138kV PT replacement, 233s36 replacement, change 233s36 to X winding from Y winding. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 951s SVC (951s Thickwood) | 2019-06-12 20:05 | 2019-06-15 11:03 | N | Y | forced outage: glycol pump failures | Shunts |  |  | 240 kV
ALTALINK | 28s R1 (28s West Brooks),28s T1 (28s West Brooks),1075L (132s Ware Junction - 28s West Brooks),28s 240kV Bus 1 (28s West Brooks) | 2019-06-13 08:01 | 2019-06-13 15:00 | N | Y | replace 28s41 & expand GOI to mitigate clearance issues | Bus, Line, Transformer, Shunts |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ALTALINK | 28s 41 (28s West Brooks) | 2019-06-14 06:40 | 2019-06-18 17:00 | N | Y | breaker failed to close | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | Rossdale T3 (Rossdale),Rossdale R723 (Rossdale) | 2019-06-14 08:00 | 2019-06-14 17:00 | N | N | doble | Transformer, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss
EPCOR | E511s VictoriaT4 (511s Victoria),Victoria V725 (Victoria),Victoria V726 (Victoria) | 2019-06-14 08:00 | 2019-06-14 17:00 | N | N | doble | Transformer, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 65.1TR (ENMAX 65),ENMAX 65 240kV South Bus,ENMAX 65 138 kV South Bus | 2019-06-15 08:00 | 2019-06-20 18:00 | N | Y | doble test, maintenance and inspection | Bus, Transformer |  | Doble test transformer. Transformer maintenance. Doble 65PT240-Z41. 65PT138-Z31. 65CAP138-C3. 65CAP240-C1. Check reversing Switch. Tapchanger inspection. Oil Sampling MT TC. Substation washing MD138, MD240bus | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 13.1TR (ENMAX 13),13.3TR (ENMAX 13),3.84L (ENMAX 13 - ENMAX 3),2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2019-06-16 08:00 | 2019-06-16 13:00 | N | N | substation washing ENMAX 13 | Line, Transformer |  | Substation Washing. 13 sub. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 13.2TR (ENMAX 13),13.4TR (ENMAX 13),11.81L (ENMAX 13 - ENMAX 11),13.60L (ENMAX 27 - ENMAX 13),13.82L (ENMAX 22 - ENMAX 13) | 2019-06-16 13:00 | 2019-06-16 18:00 | N | N | substation washing ENMAX 13, check reversing switch 13.2TR | Line, Transformer |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 330P GT1 (330p Genesee) | 2019-06-17 07:00 | 2019-06-21 17:00 | N | Y | relay maintenance | Transformer |  |  | Contingency Requires Mitigation, 500 kV
EPCOR | 987s CC13 (987s Clover Bar) | 2019-06-17 07:00 | 2019-06-21 17:00 | N | N | 72kV BF protection upgrade project | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 953s T2 (953s Lake Louise) | 2019-06-17 07:00 | 2019-10-10 14:00 | N | N | creating temporary open point 'A' | Transformer | 953s T2 (953s Lake Louise) | Installing temporary 953s852, 953s VT3 and 25kV U/G cable to Finning/Caterpillar generators; Also creating temporary 953s Open Point 'A' between 953s18 & 953s T2 | For Information Only
ATCO | 2075s ACF21 (2075s Newell) | 2019-06-17 07:00 | 2019-06-20 16:00 | N | Y | maintenance, inspection | Shunts |  | Maintenance on 902T, ACF21 Inspection, Move Network Switches, & Glycol Bypass Calibration SVC Redundancy Lost | 240 kV
ENMAX | 32.2TR (ENMAX 32) | 2019-06-17 08:00 | 2019-06-28 16:00 | N | N | bushing replacement, oil sampling bushings, check reversing switch | Transformer |  | MV Bushing Replacement. Oil sampling bushings, MT, TC. Check reversing switch. | For Information Only
ENMAX | 38.1TR (ENMAX 38) | 2019-06-17 08:00 | 2019-06-17 12:00 | N | N | view cable terminations in 8kV cell | Transformer |  | View cable terminations in 8kV cell. Engineering contact Andrew Nikulin (403-514-2646) | For Information Only
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2019-06-17 08:00 | 2019-06-17 16:00 | N | N | breaker maintenance | Line |  | HV Breaker Maintenance 14B138-14.83. 36B138-14.83. SF6 gas sample 36B138-14.83. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2019-06-17 08:00 | 2019-06-21 17:30 | N | N | changing cross-arms on 7L53 | Line |  | CHANGING CROSS-ARMS ON 7L53. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft T2 (Woodcroft) | 2019-06-17 08:00 | 2019-06-21 17:00 | N | N | doble | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 431s T1 (431s Hussar) | 2019-06-17 08:30 | 2019-06-18 17:00 | N | N | customer maintenance | Transformer |  | Customer maintenance | For Information Only
BCH | 5L96 (Selkirk - Vaseux Lake) | 2019-06-17 09:00 | 2019-06-17 17:00 | N | Y | re-install broken guy wire at structure 239-1 | Line | Peak RC outage ID: 1-00655044 Peak RC path ID: 1-00655152 (E>W, export), 1-00655153 (W>E, import) | clearance required to re-install broken guy wire at structure 239-1 | Limits ATC, 500 kV
ATCO | 826s 701 (826s Marguerite Lake) | 2019-06-17 09:00 | 2019-06-19 16:00 | N | N | 826s breaker 701 closing issue monitor/repair | Circuit Breaker |  | 826S BREAKER 701 CLOSING ISSUE MONITOR/ REPAIR 144kV ring bus will be opened for the duration of the work | Pre-Condition, Contingency Requires Mitigation
REDDEER | 194s T1 (194s South Red Deer) | 2019-06-17 09:00 | 2019-10-14 15:30 | N | N | maintenance | Transformer | 194s T1 (194s South Red Deer) | 138/25kV Power Transformer 15T1 replacement | For Information Only
ALTALINK | 866S Sundance Make-Up | 2019-06-17 09:30 | 2019-06-27 16:30 | N | N | upgrade metering | Station |  | Upgrade Metering | For Information Only
ALTALINK | 510s ACF14 (510s Sunnybrook) | 2019-06-17 09:30 | 2019-06-19 18:30 | N | Y | leak repair and inspection | Shunts |  |  | 500 kV
ATCO | 813s SVC (813s Little Smoky) | 2019-06-17 11:00 | 2019-06-20 11:35 | N | Y | SVC glycol system maintenance, 703T maintenance | Shunts |  | SVC glycol system maintenance, 703T maintenance, Fix 703T oil leaks | For Information Only
ALTALINK | 975s T1 (975s Dalehurst) | 2019-06-17 12:00 | 2019-06-20 18:00 | N | N | transformer maintenance | Transformer |  | T1(TX18073) high/low bushing replacement. VR1(TX18182) maintenance, doble, leaks. 975s745 mixed gas percent test, maintenance | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2019-06-17 12:15 | 2019-06-20 17:45 | N | N | component replacements 223L structure range 0A-440 | Line |  | Component replacements 223L Structure range 0A-440 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 63s 952 (63s Red Deer) | 2019-06-17 13:30 | 2019-06-20 17:30 | N | Y | 240kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 135s T1 (135s Conrad) | 2019-06-17 16:00 | 2019-07-30 10:00 | N | N | complete alterations T1, 25 kV bus 1 and replace 25 kV U/G cables for new cubicles on Fortis 342L/466L | Transformer |  |  | For Information Only
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2019-06-18 07:00 | 2019-06-20 18:00 | N | Y | replacing insulators between structures #50 - 64 | Line |  |  | 240 kV, Pre-Condition
ENMAX | ENMAX 11 | 2019-06-18 08:00 | 2019-06-18 16:00 | N | N | permanently remove station service transformer from service | Station |  |  | For Information Only
ENMAX | 13.4TR (ENMAX 13),27.2TR (ENMAX 27),13.60L (ENMAX 27 - ENMAX 13),ENMAX 27 B69-13.60 (ENMAX 27) | 2019-06-18 08:00 | 2019-06-18 16:00 | N | N | remove bird nest on structure between SW66 & SW67 | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 3L (245s Seebe - 3L145) | 2019-06-18 08:00 | 2019-06-18 17:00 | N | N | urgent line clearance mitigation | Line |  | URGENT Line Clearance Mitigation, Replace broken insulators on Structure 81. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 502s T3 (502s Shell Waterton (#2)) | 2019-06-18 08:00 | 2019-07-23 17:00 | N | N | capital upgrade: remove VR3, T3 and replace with new T3 transformer | Transformer |  |  | For Information Only
ENMAX | ENMAX 36 B138-36BT3 (ENMAX 36) | 2019-06-18 08:00 | 2019-06-18 16:00 | N | N | SF6 sample and maintenance | Circuit Breaker |  |  | For Information Only
ALTALINK | 74s C3 (74s Janet),74s C4 (74s Janet),74s 104 (74s Janet),74s 102 (74s Janet) | 2019-06-18 09:00 | 2019-06-20 16:30 | N | Y | replace failed capacitors on A phase | Circuit Breaker, Shunts |  |  | For Information Only
ATCO | 9L23 (848s Ruth Lake - 977s Salt Creek),977s 902 (977s Salt Creek) | 2019-06-18 15:50 | 2019-07-08 18:00 | N | Y | forced outage | Line, Circuit Breaker |  | 9L23 was hit by helicopter. After trip, 977s 902 won't close.
AESO-SC | OATI | 2019-06-18 18:00 | 2019-06-18 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
ATCO | 7L40 (813s Little Smoky - 733s Simonette) | 2019-06-18 19:23 | 2019-06-20 06:15 | N | N | forced outage to repair broken conductor | Line
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2019-06-19 08:00 | 2019-06-20 18:00 | N | Y | urgent repair | Line |  | Urgent Repair Glass and DMR Insulator has failed 1325L492 1325L Str's 491-492 OHSW repairs added on. | 500 kV
ALTALINK | 754L (245s Seebe - 754L65A) | 2019-06-19 08:00 | 2019-06-19 17:00 | N | Y | urgent line clearance mitigation | Line |  | URGENT Line Clearance Mitigation, Repairing downlead to overhead shield wire | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 27.1TR (ENMAX 27),16.61L (ENMAX 16 - ENMAX 27) | 2019-06-19 08:00 | 2019-06-19 16:00 | N | N | remove bird nest | Line, Transformer |  | Remove Bird nest on structure btw SW61 & SW62 @ 27 Sub | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.5TR (ENMAX 5) | 2019-06-19 08:00 | 2019-06-20 16:00 | N | N | relay CPU upgrade | Transformer |  | T-60 Relay CPU upgrade. No CT testing required. Check reversing switch. | For Information Only
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2019-06-19 08:30 | 2019-06-19 16:30 | N | Y | switch maintenance | Line |  | Switch maintenance by customer. Customer requested. | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 431s T2 (431s Hussar) | 2019-06-19 08:30 | 2019-06-20 17:00 | N | N | maintenance | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant) | 2019-06-20 08:00 | 2019-06-20 17:00 | N | N | urgent line clearance mitigation | Line |  | URGENT Line Clearance Mitigation, Replace broken insulators on Structure 49 and Structure 57 | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.84L (ENMAX 13 - ENMAX 3),ENMAX 13 B138-3.84 (ENMAX 13) | 2019-06-20 08:00 | 2019-06-20 16:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | HV Breaker Maintenance - 13B138-3.84. SF6 Gas Sample. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.2TR (ENMAX 15) | 2019-06-20 08:00 | 2019-06-21 16:00 | N | N | transformer inspection | Transformer |  | Tapchanger inspection. Check reversing switch. Oil sampling MT, TC | For Information Only
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2019-06-20 09:30 | 2019-06-21 14:30 | N | Y | inspection and weed control | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 275s 2 (275s Jenner) | 2019-06-20 09:45 | 2019-06-20 15:15 | N | Y | urgent gas top up | Circuit Breaker |  | Urgent outage to top up N2 on 2 phases. The north and south phase nitrogen pressure gauges are indicating low pressures. | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 65.1TR (ENMAX 65),ENMAX 65 138 kV South Bus | 2019-06-20 18:01 | 2019-06-23 18:00 | N | Y | doble test, maintenance and inspection | Transformer, Bus |  | Doble test transformer. Transformer maintenance. Doble 65PT240-Z41. 65PT138-Z31. 65CAP138-C3. 65CAP240-C1. Check reversing Switch. Tapchanger inspection. Oil Sampling MT TC. Substation washing MD138, MD240bus | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 2085s 602T Sheridan | 2019-06-21 07:30 | 2019-06-21 12:30 | N | N | damaged motor | Line |  | Damaged motor limit switch from factory needs to be swapped out. T&O required on BKR 602 Transfer 602T load to 601T | For Information Only
EPCOR | Woodcroft W725 (Woodcroft),Woodcroft T2 (Woodcroft) | 2019-06-21 08:00 | 2019-06-21 17:00 | N | N | doble | Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds, For Information Only
ALTALINK | 669L (163s Amoco Empress - 562s Cypress) | 2019-06-21 13:00 | 2019-07-29 16:00 | N | N | de-rated to 0MVA, Clearance issue | Line |  |  | For Information Only
ALTALINK | 320p T4 (320p Keephills) | 2019-06-22 07:00 | 2019-06-23 18:00 | N | Y | replace 138 kV & 25kV Bus PT, replace 25 kV Bus PT & T4 maintenance | Transformer | replace 25 kV Bus PT, replace metering |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK, EPCOR | 1055L (629s Argyll Transfer - 816s Petrolia) | 2019-06-22 07:00 | 2019-06-27 17:00 | N | Y | washing program | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage
ENMAX | ENMAX 11 B138-11.82 (ENMAX 11) | 2019-06-22 08:00 | 2019-06-22 16:00 | N | N | breaker maintenance | Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ATCO | 766s 701T (766s Nevis) | 2019-06-23 06:00 | 2019-06-23 10:00 | N | N | reclaiming the oil in 701T | Transformer |  | Reclaiming the oil in 701T | For Information Only
ENMAX | ENMAX 35.2TR (ENMAX 35) | 2019-06-23 08:00 | 2019-06-28 16:00 | N | N | repair and maintenance | Transformer |  | Corrective. Oil Leak Repair - 35.2TC. Parts required. Oil sampling TC. Filmax LTC Maintenance. | For Information Only
ALTALINK, TRANSALTA | 229s T2 (229s Glenwood),225L (229s Glenwood - 385s Spring Coulee) | 2019-06-24 | 2019-06-24 07:00 | N | N | restring a new span of wire from 225L611 to the "A" frame in 229s Glenwood | Line, Transformer |  |  | Pre-Condition, Overload, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 752L (653s Summit - 752L76) | 2019-06-24 07:00 | 2019-06-26 19:00 | N | Y | urgent: line clearance issue | Line |  | Salvage Fortis u/b below 752L in clearance violation Str 85-103. 688L reclose block required for span at str 103. | Pre-Condition, Overload, Restricts Generation
EPCOR | Garneau G722 (Garneau) | 2019-06-24 07:00 | 2019-06-24 12:00 | N | N | relay maintenance checks | Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 987s CC24 (987s Clover Bar) | 2019-06-24 07:00 | 2019-06-28 17:00 | N | N | 72kV breaker fail protection upgrade project | Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
CNRL | 641s 701T (641s Primrose East),641s 704 (641s Primrose East) | 2019-06-24 07:30 | 2019-06-24 17:00 | N | N | maintenance | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 718s 701T (718s Parsons Creek) | 2019-06-24 08:00 | 2019-06-28 16:00 | N | N | transformer maintenance and leak repair | Transformer |  | TRANSFORMER CLASS2 MAJOR TESTING @ PARSONS CREEK 718S 701T Transformer maintenance and leak repair 701T OOS for duration of work, all load carried by 702T | For Information Only
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2019-06-24 08:00 | 2019-06-28 17:00 | N | Y | clearance mitigation | Line |  | 9L59- GOI permit for Clearance Mitigation . 6 more structures left to change for clearance Mitigation. | 240 kV, Firm Load Loss, Creates Radial Feeds
Syncrude | Syncrude Mildred Lake | 2019-06-24 08:00 | 2019-06-30 20:00 | N | N | N18A substation maintenance | Station |  | N18A Substation PM Outage (Maintenance Work), Transformer (1-OPTR72-218A) 72kV/ 4.16kV, Fed From WMF Feeder | For Information Only
ENMAX | 65.2TR (ENMAX 65),ENMAX 65 240kV North Bus | 2019-06-24 08:00 | 2019-07-04 18:00 | N | Y | doble test transformer, check reversing switch, tap changer inspection, gas relay, oil sample MT, TC.replace manual operation knob, substation washing | Transformer, Bus |  | Doble test transformer. Transformer maint. Doble 65PT240-Z42. 65PT138-Z32. 65PT138-C4, 65PT240-C2. Check reversing Switch. Tapchanger inspection. Gas Relay. Oil sample MT, TC.Replace Manual Operation Knob. Substation washing | 240 kV, Contingency Requires Mitigation
ENMAX | 3.82L (ENMAX 3 - ENMAX 8),ENMAX 3 B138-3.82 (ENMAX 3),ENMAX 8 B138-5A01 (ENMAX 8) | 2019-06-24 08:00 | 2019-06-25 16:00 | N | N | DCRPR set up scaffolding near 3.82L @ 8sub | Line, Switch, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
Syncrude | D05 D05 | 2019-06-24 08:00 | 2019-06-30 20:00 | N | N | N10 substation maintenance | Station | N10 SS Outage  Downstream of ML-4 (ML-4 Feeder), Isolation switch will be operated at NMF2 (North Mine Feeder 2)  Not part of the AESO visibility. N10 Substation PM Outage (Maintenance Work), Transformer (1-OPTR72-210) 72kV/ 4.16kV, Fed From ML-4 Feeder |  | For Information Only
Syncrude | Syncrude Mildred Lake | 2019-06-24 08:00 | 2019-06-30 20:00 | N | N | N19A substation maintenance | Station |  | N19A Substation PM Outage (Maintenance Work), Transformer (1-OPTR72-219A) 72kV/ 4.16kV, Fed From SWMF Feeder | For Information Only
ENMAX | 24.81L (ENMAX 31 - ENMAX 24),ENMAX 24 B138-24.81 (ENMAX 24) | 2019-06-24 08:00 | 2019-06-25 15:00 | N | N | HV breaker maintenance 24B138-24.81. SF6 gas sample | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan),262s 870W (262s Rocky Mountain House) | 2019-06-24 10:00 | 2019-07-11 18:00 | N | Y | component replacements (structure range 9-153) | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2019-06-24 10:00 | 2019-06-25 13:00 | N | N | repairing deficiencies on 945s26 | Line |  |  | For Information Only
EPCOR | Garneau G723 (Garneau) | 2019-06-24 12:30 | 2019-06-24 17:00 | N | N | relay maintenance checks | Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 87s T2 (87s Gaetz) | 2019-06-24 13:45 | 2019-07-05 16:45 | N | Y | emergency work; oil condition is in question and requires inspection, CS mitigation, oil leak | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 760L (163s Amoco Empress - 760L41) | 2019-06-24 17:00 | 2019-07-12 17:00 | N | Y | Urgent clearance mitigation at structure 29 of 760L | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Garneau G724 (Garneau) | 2019-06-25 07:00 | 2019-06-25 12:00 | N | N | relay maintenance op-checks | Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2019-06-25 07:15 | 2019-06-27 17:45 | N | N | component replacements, structure range 0A-440 | Line |  | Component replacements 223L Structure range 0A-440 Requested By: Geri Green | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 317s T1 (317s Baseline) | 2019-06-25 07:30 | 2019-06-25 09:30 | N | N | operate a switch downstream de-energized | Transformer |  | Enbridge request to open 317s1 to allow them to operate a switch downstream de-energized. | For Information Only
BCH | Natal T4 (BCH Natal) | 2019-06-25 09:00 | 2019-06-28 17:00 | N | Y | protection trip testing | Transformer | BC Outage Peak RC COS: 1-00655620 |  | For Information Only
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2019-06-25 09:00 | 2019-06-27 12:00 | N | Y | repair to cross arms | Line |  | 7L63 crossarm replacements | Pre-Condition
EPCOR | Garneau G725 (Garneau) | 2019-06-25 12:30 | 2019-06-25 17:00 | N | N | relay maintenance op-checks | Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 945s T1 (945s Sunshine Village) | 2019-06-25 13:00 | 2019-06-27 18:00 | N | N | repairing deficiencies on 945s32 | Transformer |  |  | For Information Only
ENMAX | 41.84L (ENMAX 54 - ENMAX 41) | 2019-06-26 08:00 | 2019-06-28 16:00 | N | N | HV breaker maintenance 54B138-41.84. | Line |  | HV Breaker Maintenance 54B138-41.84. Doble 54PT138-Z31. Doble Las. Distance protection on 54.81L will be disabled on A and B protection while PTs offline but line remains protected through differential protection. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-06-26 11:00 | 2019-06-26 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
AESO-SC | OATI | 2019-06-26 13:00 | 2019-06-26 15:00 | N | N | firewall maintenance | SCInternal |  |  | For Information Only
AESO-SC | Video Wall Hardware | 2019-06-27 08:00 | 2019-06-28 17:00 | N | N | Change Lens in Barco controllers | SCInternal
ATCO, ALTALINK | 1035L (2075s Newell - 244s Bowmanton) | 2019-06-27 08:00 | 2019-06-28 17:00 | N | Y | P1800 trip testing of new Shamrock (1018s) RAS | Line |  | Trip testing of new Shamrock (1018s) RAS | 240 kV
FORTIS | Blackfalds BFD1 DER | 2019-06-27 08:00 | 2019-07-11 16:00 | N | N | P2079. ISD: Jul 04, 2019 | Unit
ALTALINK | 64S East Crossfield | 2019-06-27 08:30 | 2019-06-27 10:30 | N | N | close open point | Station |  | Close Open Point on low side of 472s and Connect 25kV U/G cables to low side of 472s. Outage of 25KV breaker 64S94N | For Information Only
ALTALINK | 752L (64s East Crossfield - 752L67), 64s 752X (64s East Crossfield) | 2019-06-27 09:00 | 2019-06-27 11:00 | N | N | connect high side of mobile | Line, Circuit Breaker |  | Outage on 752L to connect high side of mobile(472s) | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-06-27 09:00 | 2019-06-27 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
AESO-SC | Control System | 2019-06-27 11:00 | 2019-06-27 16:00 | N | N | patch deployment for computers SCC control room | SCInternal |  |  | For Information Only
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2019-06-27 12:28 | 2019-06-29 18:00 | N | Y | forced outage | Line
ENMAX | 11.81L (ENMAX 13 - ENMAX 11) | 2019-06-27 20:42 | 2019-08-06 02:00 | N | N | forced outage | Line
ENMAX | 13.4TR (ENMAX 13),13.60L (ENMAX 27 - ENMAX 13) | 2019-06-27 20:42 | 2019-07-08 14:00 | N | N | forced outage | Line, Transformer
ALTALINK | 953s T2 (953s Lake Louise) | 2019-06-28 07:30 | 2019-06-28 17:00 | N | N | testing and creating temporary open point A | Transformer |  | run up Lake Louise generators for voltage checks on VT2 (25kV bus2 PTs); Also creating temporary 953s Open Point 'A' between 953s18 & 953s T2 | For Information Only
ATCO | 7L794 (157s Lac La Biche - 819s Whitby Lake) | 2019-06-28 08:30 | 2019-06-28 17:00 | N | Y | replace a damaged pole | Line |  | Replace a damaged pole | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 72JM18 (805s Jasper - Meadowlark),Meadowlark T1 (Meadowlark) | 2019-06-28 22:00 | 2019-06-30 22:00 | N | N | 72kV BF protection upgrade project | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1034L (244s Bowmanton - 324s Cassils) | 2019-06-29 08:00 | 2019-06-30 17:00 | N | Y | trip testing of new Shamrock (1018s) RAS(P1800) | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 244s 352 (244s Bowmanton) | 2019-07-01 07:30 | 2019-07-01 12:00 | N | Y | trip testing of new Shamrock (1018s) RAS (P1800) | Circuit Breaker |  | Trip testing of new Shamrock (1018s) RAS (P1800) | Pre-Condition, Over/Under Voltage
SUNCOR | 29EDD-1 29EDD1s252 (29EDD-1 Millennium),29EDD-1 29EDD1s352 (29EDD-1 Millennium) | 2019-07-01 08:00 | 2019-08-12 22:00 | N | Y | 5 year maintenance | Circuit Breaker |  | Perform 5 year mtce on 29CVT-2. during the scheduled "C" inspection on generator GTG #5 Will update elements not available at a later date Due to GTG5 being out of service, this RTS will hinge on GTG5. May take up to 72 hours for GTG to be brought online | 240 kV, For Information Only
SUNCOR | 29EDD-3 29PT-5 (29EDD-3) | 2019-07-01 08:00 | 2019-07-21 18:00 | N | Y | maintenance | Transformer |  | Perform maintenance work during GTG5 "C" inspection - 29PT-5 oil leak repair - 29PT-5 Core ground post - 29PT-5 Core ground leak Repair. Will update elements not available at a later date | 240 kV, For Information Only
ALTALINK | 244s 652 (244s Bowmanton) | 2019-07-01 12:30 | 2019-07-01 17:30 | N | Y | trip testing of new Shamrock (1018s) RAS (P1800) | Circuit Breaker |  | Trip testing of new Shamrock (1018s) RAS (P1800) | Pre-Condition, Over/Under Voltage
ALTALINK | 225S Magrath | 2019-07-01 18:10 | 2019-07-01 23:59 | N | N | Suncor Magrath (SCR2) MVAr capability | Station |  |  | For Information Only
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2019-07-02 07:00 | 2019-07-05 17:00 | N | Y | structure refurbishment and upgrades | Line |  |  | 240 kV
ENMAX | 34.2TR (ENMAX 34) | 2019-07-02 08:00 | 2019-07-16 08:00 | N | N | 34.2TR replacement. remove old TR | Transformer |  |  | For Information Only
ALTALINK | 511s 1252 (511s Crossings) | 2019-07-02 08:30 | 2019-07-03 12:30 | N | Y | maintenance and vegetation control | Circuit Breaker |  |  | 240 kV, For Information Only
ALTALINK | 64s T1 (64s East Crossfield),64s T2 (64s East Crossfield) | 2019-07-02 08:30 | 2019-07-15 12:30 | N | Y | relocate PT | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 510s ACF13 (510s Sunnybrook) | 2019-07-02 08:30 | 2019-07-03 16:30 | N | Y | annual inspection | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 285s T1 (285s East Camrose) | 2019-07-02 09:00 | 2019-07-05 18:00 | N | N | change T1/87B protection module wiring | Transformer |  | Change T1/87B protection module wiring to move mechanical trips out of the relay and to come directly from 94 tripping relays | For Information Only
ALTALINK | 198s T2 (198s Blackfalds) | 2019-07-02 09:15 | 2019-07-04 16:45 | N | N | P2079 protection setting changes | Transformer |  | Install VTs on the 198s2235 Feeder and connect to protection, Change settings on 198s2235 feeder protection and test, | For Information Only
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2019-07-02 09:30 | 2019-07-04 17:00 | N | Y | Change Arms and Insulators on 7L702 | Line |  | Change Arms and Insulators on 7L702 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2019-07-02 12:15 | 2019-07-11 17:45 | N | N | component replacements 223L | Line |  | Component replacements 223L Structure range 0A-440 Requested By: Geri Green | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1212L (89s Ellerslie - 12s Heartland) | 2019-07-03 06:00 | 2019-07-15 19:00 | N | Y | spacer and damper replacement on structures # 4 - 191 | Line |  | spacer and damper replacement on structures # 4 - 191 | For Information Only, 500 kV
ALTALINK | 704L (51s Wainwright - 478s Tuccuman) | 2019-07-03 07:00 | 2019-07-05 19:00 | N | N | structure replacement work on 704L from structures 260 to 267 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 305s T2 (305s Acheson) | 2019-07-03 08:00 | 2019-07-03 17:30 | N | N | temperature monitor replacement | Transformer |  |  | For Information Only
ALTALINK | 580s T1 (580s Sylvan Lake) | 2019-07-03 08:00 | 2019-07-03 17:30 | N | N | temperature monitor replacement | Transformer |  |  | For Information Only
AESO-SC | DT | 2019-07-03 10:00 | 2019-07-03 16:00 | N | N | DT Q4 release will be deployed in PROD. | SCInternal |  | DT Q4 release will be deployed in PROD. | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2019-07-03 12:00 | 2019-07-05 15:30 | N | Y | annual Inspection | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 511s ACF12 (511s Crossings),511s 1352 (511s Crossings) | 2019-07-03 12:30 | 2019-07-04 16:30 | N | Y | filter bank maintenance and vegetation control | Shunts, Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | Rossdale T4 (Rossdale) | 2019-07-04 07:00 | 2019-07-05 17:00 | N | N | operation check | Transformer |  |  | Pre-Condition, Overload, Firm Load Loss
ALTALINK | 580s T2 (580s Sylvan Lake) | 2019-07-04 08:00 | 2019-07-04 17:30 | N | N | temperature monitor replacement | Transformer |  |  | For Information Only
ALTALINK | 420s T1 (420s Broadmoor) | 2019-07-04 08:00 | 2019-07-04 17:30 | N | N | temperature monitor replacement | Transformer |  |  | For Information Only
ALTALINK | 511s 1452 (511s Crossings) | 2019-07-04 08:30 | 2019-07-04 16:30 | N | Y | ACF Bank Maintenance and Vegetation Control | Circuit Breaker |  | ACF Bank Maintenance and Vegetation Control | 240 kV, For Information Only
ATCO | 791s 702T (791s Rainbow Lake),791s 707 (791s Rainbow Lake) | 2019-07-05 07:00 | 2019-09-02 17:00 | N | N | add jumper J1 between 144 kV bus and 702TD for salvage/addition of equipment | Circuit Breaker, Transformer |  | Create jumper J1 between 144 kv bus and 702TD. Remove 702TD, 702T, 707, 502TD1. Attach new 701TD, 501TD1, Bkr 706. Need to expand outage to include 501B, 502B, 503B, 504B, J1, J2, | For Information Only
ALTALINK | 285s3202 (285s East Camrose) | 2019-07-05 10:00 | 2019-07-05 11:00 | N | Y | change T1/87B protection module wiring | Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 730L (285s East Camrose - 730L62),285s 730N (285s East Camrose) | 2019-07-05 16:00 | 2019-07-05 17:00 | N | N | change T1/87B protection module wiring | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 729L (285s East Camrose - 542s Ervick),285s 729W (285s East Camrose) | 2019-07-05 17:01 | 2019-07-05 18:00 | N | N | change T1/87B protection module wiring | Circuit Breaker, Line |  |  | Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72JM18 (805s Jasper - Meadowlark),Meadowlark M721 (Meadowlark),Meadowlark M722 (Meadowlark),Meadowlark T1 (Meadowlark) | 2019-07-05 22:00 | 2019-07-07 17:00 | N | N | 72kV breaker fail protection upgrade | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 805s T3 (805s Jasper),805s J2404 (805s Jasper),805s J2405 (805s Jasper) | 2019-07-06 07:00 | 2019-07-06 17:00 | N | Y | bushing replacement | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss
Syncrude | AURORA Aurora | 2019-07-06 08:00 | 2019-07-12 20:00 | N | N | G18 Substation 5 year PM | Station |  | G18 Substation 5 yr PM Outage, Transformer (201-2-PTR72-022) 72/13.8KV, Fed From MH-2 72kV Feeder , Aurora G01 Susbsation | For Information Only
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar),987s C2404 (987s Clover Bar),987s C2406 (987s Clover Bar) | 2019-07-08 07:00 | 2019-07-10 17:00 | N | Y | commissioning of anti-islanding upgrade project | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2019-07-08 07:15 | 2019-07-08 12:45 | N | N | high load move | Line |  | We have a high load on highway 24 on the Morning of July 8 PO 4031/4032 2018. The load is 8.68 m. The crossing is between structures 198 and 199.This job is being done for Totran. Requested By: Darryl Rempel | Pre-Condition, Overload, Over/Under Voltage
ALTALINK | 511s 1652 (511s Crossings) | 2019-07-08 07:30 | 2019-07-08 12:30 | N | Y | MSR maintenance and vegetation control | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 993s T1 (993s Abee) | 2019-07-08 07:45 | 2019-07-08 17:00 | N | N | customer requested station outage | Transformer |  | Customer requested station outage | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2019-07-08 08:00 | 2019-07-09 16:00 | N | N | inspection and maintenance | Transformer |  | Tapchanger inspection. Corrective. 15.1TR Remediate Rust on Tapchanger Floor. Check reversing switch. Oil sampling MT, TC | For Information Only
ENMAX | 43.2TR (ENMAX 43) | 2019-07-08 08:00 | 2019-07-25 16:00 | N | N | protection upgrade | Transformer |  |  | For Information Only
CapitalPower, ALTALINK | 1018s Shamrock,1148L (1018s Shamrock - 251s Whitla),1018s T1 (1018s Shamrock) | 2019-07-08 08:00 | 2019-07-22 16:00 | N | N | P1800. ISD July 15, 2019 | Station, Line, Transformer
ENMAX | 31.3TR (ENMAX 31) | 2019-07-08 08:00 | 2019-07-10 16:00 | N | N | T-60 relay CPU upgrade, CT testing | Transformer |  | T-60 Relay CPU upgrade. CT Testing. Prints - # 2 WO Field Revisions to WO21147169 (31.3TR Dev 90x). | For Information Only
EPCOR | Woodcroft W725 (Woodcroft),Woodcroft T2 (Woodcroft) | 2019-07-08 08:00 | 2019-07-19 17:00 | N | N | LTC upgrade | Transformer, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 918s701T (918s Bauer) | 2019-07-08 09:00 | 2019-07-12 16:00 | N | N | leak repair | Transformer |  | Isolate transformer and repair leak | For Information Only
BCH | 2L293 (Selkirk - Nelway) | 2019-07-08 09:00 | 2019-07-18 17:00 | N | Y | replace over-loaded and end-of-life structures and timbers | Line | BC Outage Peak RC COS: 1-00658512 AB Peak RC COS# : 1-00660070 (E>W), 1-00660071 (W>E) | replace over-loaded and end-of-life structures and timbers. | Limits ATC
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2019-07-08 09:30 | 2019-07-11 17:00 | N | Y | change arms and insulators | Line |  | Change Arms and Insulators on 7L702 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 744L (235s Entwistle - 744L88C) | 2019-07-08 09:30 | 2019-07-10 18:00 | N | N | component replacement work on structures | Line |  | Component Replacement Work on Structures #59A, 67A, 86A, 104A, 111A, 118A, 126A, 11, 14, 24, 26, 27, 28, 63, 70 and 78. U/B line on Strs #86A, 11 and 78 Requested By: Ignacio Saralegui | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 1109L | 2019-07-08 09:45 | 2019-07-08 17:45 | N | Y | washing and maintenance | Terminal Equipment |  | Wash 25PT240-1109 zone. HV SW maintenance SW153, SW152, 25MD240-1109. | 240 kV, Pre-Condition
ALTALINK | 735L (171s Redwater - 233s Beamer),171s 735X (171s Redwater) | 2019-07-08 09:45 | 2019-07-08 11:15 | N | N | install temp DC supply | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 285s T2 (285s East Camrose) | 2019-07-08 10:00 | 2019-07-11 16:00 | N | N | change T2/87B protection module wiring | Transformer |  | Change T2/87B protection module wiring to move mechanical trips out of the relay and to come directly from 94 tripping relays | For Information Only
ALTALINK | 925L (63s Red Deer - 74s Janet),74s 2052 (74s Janet),74s 2152 (74s Janet) | 2019-07-08 10:15 | 2019-07-11 15:45 | N | Y | upgrade SCADA equipment | Line, Circuit Breaker |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | 240 kV, Pre-Condition
ALTALINK | 171s T2 (171s Redwater),808L (171s Redwater - 808L75C) | 2019-07-08 11:20 | 2019-07-11 17:30 | N | N | breaker replacement on 25 kV side | Transformer, Line |  | 171s partial 138kV bus, T2 and 25kV North bus 171s249N breaker replacement, 171s249N LAs, 171s291W LAs, 171s70N LAs, CVT1-JB, DC JB1 | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s 1752 (511s Crossings) | 2019-07-08 12:30 | 2019-07-08 18:30 | N | Y | MSR maintenance and vegetation control | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 385s T1 (385s Spring Coulee) | 2019-07-08 12:30 | 2019-07-11 17:00 | N | N | replace 3 HV, HO, LO bushings on T1 | Transformer |  | Replace 3 HV, HO, LO bushings on T1 | For Information Only
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2019-07-09 07:00 | 2019-07-09 17:00 | N | N | breaker fail protection upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 760AL (164s Empress Liquids - 760L41),760L (163s Amoco Empress - 760L41) | 2019-07-09 07:00 | 2019-07-11 18:00 | N | N | urgent structure replacement on 760L structure #29 | Line |  |  | Pre-Condition, For Information Only
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D135 (ENMAX 25) | 2019-07-09 07:45 | 2019-07-09 17:15 | N | Y | replaced cracked sheath voltage limiters | Circuit Breaker, Line |  |  | 240 kV, Pre-Condition, Overload
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2019-07-10 04:00 | 2019-07-24 | N | N | rebuilding 551L sections 17B (structures #419 - 436) & 19 structures #469 - 476) | Line |  | - Rebuilding 551L Sections 17B (Structures #419 - 436) & 19 Structures #469 - 476) 551L (Open Point 'B' - 953s) - GOI | For Information Only
EPCOR | 72CH9 (Hardisty - 987s Clover Bar) | 2019-07-10 07:00 | 2019-07-10 17:00 | N | N | BF upgrade project | Line |  |  | Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s SVC Plus (511s Crossings),511s 1552 (511s Crossings) | 2019-07-10 07:30 | 2019-07-10 16:30 | N | Y | maintenance and vegetation control | Shunts, Circuit Breaker |  | 511s1552, Voltage Source Converter Reactor Maintenance and Vegetation Control. | 240 kV, Pre-Condition
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2019-07-10 07:45 | 2019-07-10 16:15 | N | Y | replaced voltage limiters | Line |  | replaced cracked sheath voltage limiters | 240 kV, Pre-Condition
ENMAX | ENMAX 25 B240-D140 (ENMAX 25),ENMAX 25 B240-D138 (ENMAX 25),ENMAX 25 B240-D134 (ENMAX 25),ENMAX 25 B240-D131 (ENMAX 25),ENMAX 25 240kV South Bus,25PT240-Z41 (ENMAX 25) | 2019-07-10 08:00 | 2019-07-12 18:00 | N | Y | substation washing | Circuit Breaker, Terminal Equipment, Bus |  | Substation washing, Doble Test 25PT240-Z41, HV SW Maint SW131, SW137, SW145, SW149. Repair erroneous CT wiring on 25B240-D131. | 240 kV, Contingency Requires Mitigation
ENMAX | 9.1TR (ENMAX 9) | 2019-07-10 08:00 | 2019-07-11 16:00 | N | N | inspection and maintenance | Transformer |  | Tapchanger inspection. Check reversing switch. Oil sampling MT, Bonybrook transfer required. | For Information Only
Syncrude | Aurora 13 (Aurora),Aurora 14 (Aurora),TL-1 (Aurora - Aurora) | 2019-07-10 08:00 | 2019-07-14 20:00 | N | N | TL-1 Transmission Line Outage (72kV), Fed From Aurora G01 Susbsation. CB 52-13 and 52-14 will be operated | Line, Circuit Breaker |  | TL-1 Transmission Line Outage (72kV), Fed From Aurora G01 Susbsation. CB 52-13 and 52-14 will be operated | For Information Only
ENMAX, ALTALINK | 937L (102s Langdon - 5s East Calgary) | 2019-07-10 16:15 | 2019-07-11 15:45 | N | Y | replaced voltage limiters | Line |  | replaced cracked sheath voltage limiters on UG cables | 240 kV, Pre-Condition
ALTALINK | 511s 2152 (511s Crossings),511s ACF21 (511s Crossings) | 2019-07-11 07:30 | 2019-07-11 16:30 | N | Y | ACF21 maintenance and vegetation control | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
EPCOR | 72CH11 (Hardisty - 987s Clover Bar),987s CH724 (987s Clover Bar) | 2019-07-11 08:00 | 2019-07-11 16:00 | N | N | breaker fail upgrade | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 837L (964s Pigeon Lake - 538s Burford) | 2019-07-11 08:00 | 2019-07-12 16:00 | N | N | forced outage due to lightning | Line
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2019-07-11 08:15 | 2019-07-11 17:45 | N | N | 25 kV u/g cable term, 23 deg hot spot | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia) | 2019-07-11 09:30 | 2019-07-15 18:00 | N | Y | structure refurbishment and upgrades | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 285s3202 (285s East Camrose) | 2019-07-11 10:00 | 2019-07-11 11:00 | N | Y | protection module wiring change | Circuit Breaker |  | Change T2/87B protection module wiring to move mechanical trips out of the relay and to come directly from 94 tripping relays. Breaker advice to function test trip to breaker from protection. | Restricts Generation
ATCO | 7L22 (811s Clairmont Lake - 7L22D2),811s 708 (811s Clairmont Lake) | 2019-07-11 10:00 | 2019-07-11 15:00 | N | Y | emergency investigate and repair | Line, Circuit Breaker |  | BKR 708 @ 811S is showing no oil (or very low). Require outage to investigate, repair and fill. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 730L (285s East Camrose - 730L62),285s 730N (285s East Camrose) | 2019-07-11 16:00 | 2019-07-11 17:00 | N | N | change T1/87B protection module wiring | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 729L (285s East Camrose - 542s Ervick),285s 729W (285s East Camrose) | 2019-07-11 17:01 | 2019-07-11 18:00 | N | N | change T1/87B protection module wiring and breaker test | Circuit Breaker, Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2019-07-12 07:00 | 2019-07-12 17:00 | N | N | BF upgrade | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s 2252 (511s Crossings),511s ACF22 (511s Crossings) | 2019-07-12 07:30 | 2019-07-16 16:30 | N | Y | ACF22 maintenance and vegetation control | Shunts, Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2019-07-12 14:30 | 2019-08-04 10:00 | N | Y | urgent outage to address clearance issues | Line |  |  | Pre-Condition, For Information Only
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia),816s P2405 (816s Petrolia),816s P2406 (816s Petrolia),805s J2404 (805s Jasper),805s J2401 (805s Jasper),805s J2408 (805s Jasper) | 2019-07-13 01:00 | 2019-07-13 02:00 | N | Y | switching for emergency repair of 805s J2403 | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 805s J2403 (805s Jasper) | 2019-07-13 02:00 | 2019-07-15 16:00 | N | Y | emergency repair | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
Medicine Hat | MH69s2 MH69_212 (MH69s2 North Industrial),MH69s5 MH69_510 (MH69s5 NE Crescent Height),MH-50L (MHS-2 North Industrial - MH69S-5 North East Crescent Heights) | 2019-07-15 07:00 | 2019-07-18 16:00 | N | N | insulator replacement | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 848s 703T (848s Ruth Lake),7L47 (848s Ruth Lake - 718s Parsons Creek) | 2019-07-15 08:00 | 2019-07-22 16:00 | N | N | PCB phase-out - replace PT and maintenance at 848S Ruth Lake | Transformer, Line |  | PCB Phase-Out - Replace PT 600PT3 (phase A&C) and maintenance at 848S Ruth Lake Sub 600PT3 Replacement, 703T PM, 702 PM, 603 PM, 607 PM, 505 CM Assets will be OOS for duration of the work, restore time may be affected by status of the work on a given day | Pre-Condition
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2019-07-15 08:00 | 2019-07-18 18:30 | N | N | change arms insulators, fix conductor, shield wire | Line |  | Transmission Maintenance Project. change arms insulators/fix conductor/shield wire. Project E63415 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 15.2TR (ENMAX 15),15.62L (ENMAX 15 - ENMAX 16) | 2019-07-15 08:00 | 2019-07-15 16:00 | N | N | corrective | Line, Transformer |  | Corrective I&R Switch Alignment Issues on 65@15sub [AVANTIS]. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33) | 2019-07-15 08:00 | 2019-07-19 16:00 | N | N | maintenance | Transformer |  | Tapchanger inspection. Reinhausen. Check reversing switch. Oil sampling MT, TC | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2019-07-15 08:00 | 2019-07-19 16:00 | N | N | maintenance | Transformer |  | Doble test transformer. Transformer secondary cable tests. Transformer maintenance. Gas relay testing. Check reversing switch. | For Information Only
ALTALINK | 545s T1 (545s Provost) | 2019-07-15 08:30 | 2019-07-15 18:00 | N | N | install new pile foundations | Transformer |  | T1 Outage to install new pile foundations for SWGB feeder and SSTX/AMI Structure foundations | For Information Only
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2019-07-15 09:00 | 2019-07-19 17:00 | N | Y | BCH urgent live line work | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 233s T1 (233s Beamer) | 2019-07-15 09:30 | 2019-07-18 16:45 | N | N | maintenance | Transformer |  | Customer request to isolate T1 for maintenance on Nutrien 13.8kV Junction point enclosure. | For Information Only
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar) | 2019-07-15 09:30 | 2019-07-18 17:00 | N | Y | structure refurbishment & upgrades | Line |  |  | 240 kV, For Information Only
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2019-07-15 11:15 | 2019-07-26 17:45 | N | N | regasket TC | Transformer |  |  | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2019-07-15 12:15 | 2019-07-18 17:45 | N | N | component replacements | Line |  | Component replacements 223L Structure range 0A-440 - This outage to be broken up into shorter duration outages later on. Most likely 2 weeks at a time Requested By: Geri Green | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 526s T2 (526s Buffalo Creek) | 2019-07-15 12:30 | 2019-07-16 18:00 | N | N | transformer maintenance | Transformer |  | transformer maintenance: TC filter oil leak, temperature monitor replacement | For Information Only
ALTALINK | 1206L (89s Ellerslie - 12s Heartland) | 2019-07-16 06:00 | 2019-08-12 19:00 | N | Y | spacer and damper replacement on structures # 4 - 191 | Line |  |  | Pre-Condition, 500 kV
BLACKSPRING | 485S Black Springs | 2019-07-16 07:00 | 2019-07-16 19:00 | N | Y | sub annual maintenance | Station |  |  | Restricts Generation
ATCO | 914s 701T (914s Bindloss) | 2019-07-16 07:00 | 2019-07-16 19:00 | N | N | 3-year electrical maintenance at the Bindloss pump station | Transformer |  | TransCanada Electrical Outage Request for Guarantee of Isolation Complete the TransCanada 3-year electrical maintenance at the Bindloss pump station. | For Information Only
CNRL | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-07-16 07:00 | 2019-07-16 18:00 | N | Y | urgent tower replacement | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 99s T1 (99s North St. Albert) | 2019-07-16 08:00 | 2019-07-19 17:30 | N | N | 138kV bushing replacement | Transformer |  |  | For Information Only
ENMAX | 34.2TR (ENMAX 34),16.60L (ENMAX 34 - ENMAX 16) | 2019-07-16 08:00 | 2019-07-26 12:00 | N | N | 34.2TR replacement | Transformer, Line |  | 34.2TR replacement. Remove old TR and MD. Install new MD for 34.2TR. 34.2TR oos on return. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2019-07-16 08:00 | 2019-07-16 20:00 | N | Y | preventive maintenance | Transformer |  |  | Restricts Generation
SUNCOR | SCR1 Base Plant Generator Test | 2019-07-16 08:00 | 2019-07-30 16:00 | N | N | P2021 Suncor TG1 & TG2 ISD: Jul 23, 2019. | Unit
ALTALINK | 899s T3 (899s Edgerton) | 2019-07-16 08:30 | 2019-07-17 17:30 | N | N | transformer maintenance | Transformer |  | transformer maintenance: temperature monitor replacement, doble, filterpack leaking | For Information Only
ALTALINK | 510s ACF21 (510s Sunnybrook) | 2019-07-16 08:30 | 2019-07-19 12:00 | N | Y | annual inspection | Shunts |  |  | 500 kV
ATCO | 741s 705C (741s Fox Creek) | 2019-07-16 14:00 | 2019-08-09 16:00 | N | N | emergency fix leaking CT | Shunts |  |  | For Information Only
AESO-SC | OATI | 2019-07-16 18:00 | 2019-07-16 19:00 | N | N | inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
CNRL | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-07-17 07:00 | 2019-07-17 18:00 | N | Y | urgent tower replacement | Line |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 706L (54s Fort Saskatchewan - 706L72B) | 2019-07-17 07:00 | 2019-07-17 18:00 | N | N | high load move | Line |  | High load move between Structures #46 & 47 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 1042L (485s Blacksprings - 554s Travers) | 2019-07-17 07:00 | 2019-07-18 19:00 | N | Y | customer switch maintenance | Line |  | customer switch maintenance | 240 kV, Restricts Generation
ENMAX | 28.1TR (ENMAX 28),1.80L (ENMAX 28 - ENMAX 1) | 2019-07-17 08:00 | 2019-07-17 16:00 | N | N | 28s 138kV BD and AS relay replacement and testing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 43.2TR (ENMAX 43),33.84L (ENMAX 43 - ENMAX 33),ENMAX 43 B138-33.84 (ENMAX 43) | 2019-07-17 08:00 | 2019-07-17 16:00 | N | N | protection upgrade and commission | Line, Transformer, Circuit Breaker |  | 43.2TR Protection Upgrade. Commission 43.2TR MD circuits, commission 33.84L breaker trip circuits, PT circuit wiring | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
BLACKSPRING | 485S Black Springs | 2019-07-17 08:00 | 2019-07-18 19:00 | N | Y | sub annual maintenance | Station |  |  | Restricts Generation
ENMAX, ALTALINK | ENMAX 25 B240-D133 (ENMAX 25),985L (ENMAX 25 - 74s Janet),ENMAX 25 B240-D132 (ENMAX 25) | 2019-07-17 08:15 | 2019-07-17 16:45 | N | Y | replaced cracked sheath voltage limiters | Line, Circuit Breaker |  | replaced cracked sheath voltage limiters | 240 kV, Overload, Contingency Requires Mitigation
ALTALINK | 995L (62s Brazeau - 995AL tap) | 2019-07-17 08:30 | 2019-07-18 18:30 | N | Y | double TPR outage and 9062R radio tower repair | Line |  |  | 240 kV, Pre-Condition, Overload, Restricts Generation, Contingency Requires Mitigation
AESO-SC | OATI | 2019-07-17 13:00 | 2019-07-17 15:00 | N | N | firewall maintenance | SCInternal |  |  | For Information Only
CNRL | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-07-18 07:00 | 2019-07-19 18:00 | N | Y | urgent tower replacement | Line |  |  | 240 kV, Firm Load Loss, Creates Radial Feeds
ALTALINK | 87s T2 (87s Gaetz) | 2019-07-18 07:15 | 2019-07-18 17:45 | N | Y | oil condition is in question and requires followup inspection | Transformer |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 41.1C (ENMAX 41) | 2019-07-18 08:00 | 2019-07-18 16:00 | N | N | doble 41PT138-Z32 | Shunts |  | Doble 41PT138-Z32. Distance Protection elements on 6.82L and 33.83L disabled while PT offline. Lines remain protected through A and B line differential schemes. | For Information Only
ALTALINK, TRANSALTA | 528s Blue Trail Wind Farm RTU/SCADA,418s Ardenville RTU/SCADA,240s McBride Lake RTU/SCADA | 2019-07-18 09:00 | 2019-07-18 13:30 | N | N | testing of the circuit for AESO communications | Terminal Equipment |  |  | Affects Visibility
AESO-SC | OrderWire | 2019-07-18 10:00 | 2019-07-18 12:00 | N | N | DA2DNS server decommission | SCInternal
Syncrude | SCL1 Syncrude #1 | 2019-07-19 08:00 | 2019-08-02 16:00 | N | N | P2225. G1 AVR & PSS Upgrade ISD July 26, 2019 | Unit
SUNCOR | SCR5 Poplar Creek Generator Test | 2019-07-19 08:00 | 2019-08-02 16:00 | N | N | P2221 ISD: Jul 26, 2019 | Unit
ENMAX | 1.6TR (ENMAX 1) | 2019-07-19 11:00 | 2019-07-20 18:00 | N | N | repair SW28@1sub & switch out 1.6TR ahead one day before 8kV bus outage & check reversing switch | Transformer |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar),987s T4 (987s Clover Bar),987s CC721 (987s Clover Bar),987s C2405 (987s Clover Bar),987s C2406 (987s Clover Bar) | 2019-07-22 07:00 | 2019-07-26 17:00 | N | Y | structure refurbishment & upgrades | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 860L (291s Cochrane - 44s Bearspaw Plant) | 2019-07-22 07:00 | 2019-07-27 17:00 | N | N | structure addition on spans 52 & 53, 56 & 57 and 85 & 86, insulator modifications on spans 65 & 66, 77 & 78 and 94 & 95 | Line |  | Adding mid-span structures on Spans 52 & 53, 56 & 57 and 85 & 86. Insulator modifications on spans 65 & 66, 77 & 78 and 94 & 95. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Hardisty T3 (Hardisty),72CH9 (Hardisty - 987s Clover Bar) | 2019-07-22 07:00 | 2019-08-01 10:00 | N | N | commissioning/energization of new Tx3 | Transformer, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 133s T1 (133s Stelco Edmonton),133s T2 (133s Stelco Edmonton),822L (133s Stelco Edmonton - 38s East Edmonton) | 2019-07-22 07:00 | 2019-07-25 15:00 | N | N | Customer outage | Line, Transformer |  |  | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2019-07-22 08:00 | 2019-07-23 16:00 | N | N | maintenance | Transformer |  | Tapchanger inspection. Check reversing switch. Filmax maintenance. Oil sampling MT, TC | For Information Only
ENMAX | 20.1TR (ENMAX 20) | 2019-07-22 08:00 | 2019-07-24 16:00 | N | N | T-60 relay CPU upgrade | Transformer |  |  | For Information Only
ENMAX | 47.2TR (ENMAX 47) | 2019-07-22 08:00 | 2019-07-26 16:00 | N | N | maintenance | Transformer |  | Doble test transformer. Check reversing switch. Transformer maintenance, Transformer Secondary Cable Test. Gas Relay Testing - 47.2TR. Check reversing switch. | For Information Only
ENMAX | 26.1TR (ENMAX 26),26.81L (ENMAX 32 - ENMAX 26) | 2019-07-22 08:00 | 2019-07-22 16:00 | N | N | breaker maintenance and doble test | Line, Transformer |  | HV Breaker Maintenance 26B138-26.81. Doble test 26PT138-26.81, 26PT138-Z31 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Syncrude | Mildred_135 (Syncrude Mildred Lake),Mildred T1 (Syncrude Mildred Lake),Mildred_1335 (Syncrude Mildred Lake) | 2019-07-22 08:00 | 2019-08-01 16:30 | N | Y | DECS upgrade | Circuit Breaker, Transformer |  |  | Restricts Generation
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2019-07-22 08:00 | 2019-07-25 18:30 | N | N | change arms insulators/fix conductor/shield wire | Line |  | Transmission Maintenance Project. change arms insulators/fix conductor/shield wire. Project E63415 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 739s 701T (739s Edith Lake) | 2019-07-22 08:00 | 2019-08-16 17:00 | N | N | protection upgrade | Transformer |  | The scope of work is A GOI will be needed to isolate 701T and to remove ION/505-507 and install ION7550/701T. Also replacing the differential relay 87T/701T with a Siemens 87TA/701T. 701T will be offloaded to 702T. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Woodcroft T3 (Woodcroft) | 2019-07-22 08:00 | 2019-08-01 15:25 | N | N | LTC upgrade | Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 510s ACF11 (510s Sunnybrook) | 2019-07-22 08:30 | 2019-07-25 16:30 | N | Y | annual Inspection | Shunts |  |  | For Information Only, 500 kV
ALTALINK | 945s T2 (945s Sunshine Village) | 2019-07-22 09:00 | 2019-07-24 04:00 | N | N | protection setting changes | Transformer |  | Changing transformer 'A' & 'S' and 945s7 50/51 settings in preparation for when the Finning Generators will be feeding both 953s & 945s | For Information Only
ATCO | 832s 701T (832s Blumenort) | 2019-07-22 09:00 | 2019-09-06 16:00 | N | N | replace 701T | Transformer |  | Replace 701T | For Information Only
ALTALINK | 276s 652 (276s Un Carb Prentiss),276s C1 (276s Prentiss) | 2019-07-22 09:30 | 2019-07-25 14:30 | N | N | cap bank protection replacement | Shunts, Circuit Breaker |  |  | Pre-Condition, For Information Only
ATCO | 7L20 (810s Dome Cutbank - 740s H.R.Milner) | 2019-07-22 10:00 | 2019-08-20 14:00 | N | Y | CrossArm and Insulators Replacement | Line |  | 7L20 X-Arm/Insulators Replacement | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 74s C1 (74s Janet),74s 56 (74s Janet) | 2019-07-22 10:15 | 2019-07-25 16:45 | N | N | repair capacitors | Circuit Breaker, Shunts |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | Pre-Condition
ALTALINK | 632PS (632s Russell) | 2019-07-22 10:15 | 2019-07-22 17:45 | N | Y | change filters on 3 presses | Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 835L (283s Violet Grove - 835L tap),283s 835E (283s Violet Grove) | 2019-07-22 12:30 | 2019-07-26 17:00 | N | N | replacing CTs for 835E and A/B line protections for 835L | Circuit Breaker, Line |  | Replacing 138kV CTs associated with 283s835E and replacing both A and B line protections on 835L during same outage. | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 760L (394s Empress - 163s Amoco Empress) | 2019-07-23 07:00 | 2019-07-24 18:00 | N | N | urgent line mitigation on structures #2 & 3 | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | ATCO Radio Tower | 2019-07-23 08:00 | 2019-07-23 17:00 | N | N | Smoky Lake telecom, Vegreville telecom, Valleyview telecom, Crow telecom, Coronation telecom, Big Valley telecom, and Astoria telecom | Terminal Equipment |  | 5 minute disruption to the following SCADA Sites: 873S Marion Lakes, 724S Hines Creek, 771S Veteran, & APL 500KV visibility @ sites; 951S Thickwood, 939S Livock & 510S Sunnybrook. Firewall replacements for core Vegreville firewalls including Operational, Mobile and Telecom firewalls. Total disruption time should be less than 5 minutes per firewall, services include: -Mobile and P25 -Crow web and client access -WiPro and External Access through Firewall for remote desktops -All services to substations accessed through the Telus SIPA network, including SCADA Listed above. -Access/Visibility to APL site including Thickwood/Livock and the Fibre repeater sites -Telecom Access to RACS and ORION SCADA and Protection to general substations are NOT affected by these firewall changes, unless specified above. | Affects Visibility
AESO-SC | OATI | 2019-07-23 08:00 | 2019-07-23 16:00 | N | N | performing maintenance on the Minneapolis data center load balancers | SCInternal |  |  | For Information Only
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2019-07-23 08:00 | 2019-07-23 16:00 | N | N | HV doble test 15B69-15.60, re-test | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 511s ACF21 (511s Crossings) | 2019-07-23 11:30 | 2019-07-24 18:00 | N | Y | forced outage | Shunts |  |  | 240 kV
ALTALINK | 945S Sunshine Village,551L (123s Banff - 953s Lake Louise) | 2019-07-24 | 2019-07-24 06:00 | N | N | closing 551L Open Point 'B' & creating 551L Open Point 'C' | Line, Station |  |  | For Information Only
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2019-07-24 02:31 | 2019-07-26 16:00 | N | N | forced outage | Line
ALTALINK | 123s T1 (123s Banff),123s T2 (123s Banff),551L (945s Sunshine Village - 123s Banff) | 2019-07-24 06:00 | 2019-09-05 | N | N | structures re-building | Line, Transformer |  | - Re-building 551L Sections 2A & 2B (Structures #52 - 73) | For Information Only
ENMAX | 54.81L (ENMAX 54 - ENMAX 65) | 2019-07-24 08:00 | 2019-07-24 16:00 | N | N | doble test 54PT138-54.81. Doble Las | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 36.2TR (ENMAX 36) | 2019-07-24 08:00 | 2019-07-26 16:00 | N | N | maintenace | Transformer |  | Tapchanger inspection. Check reversing switch, Oil sampling MT, TC | For Information Only
ALTALINK | 575s 719N (575s Sundre) | 2019-07-24 08:15 | 2019-07-24 17:45 | N | Y | oil samples | Circuit Breaker |  | CT 45131, 45132, 45133 oil samples | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood) | 2019-07-24 09:00 | 2019-07-24 15:00 | N | N | upgrade MPLS node at 422s & reduce chance of mis-coordination or dynamic system issues | Line |  | Upgrade MPLS node at 422s. De-energize 694L to reduce chance of mis-coordination or dynamic system issues. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 62s11 (62s Brazeau) | 2019-07-24 23:00 | 2019-07-25 03:00 | N | Y | maintenance | Switch |  | BR1 generator brushgear maint outage | Restricts Generation, For Information Only
ALTALINK | 62s12 (62s Brazeau) | 2019-07-25 03:05 | 2019-07-25 07:00 | N | Y | maintenance | Switch |  | BR2 generator brushgear maint outage | Restricts Generation
ALTALINK | 760L (7L760D3 - 760L41) | 2019-07-25 07:00 | 2019-07-26 18:00 | N | Y | urgent line mitigation on structures #43, 44 & 53 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 322S Cowley Ridge | 2019-07-25 09:00 | 2019-07-25 12:00 | N | Y | maintenance | Station |  |  | Restricts Generation
NWE | NWMT Broadview Switchyard-Judith Gap South 230kV Line | 2019-07-26 07:00 | 2019-07-26 17:00 | N | Y | urgent: repair broken wire | Line | ###Peak RC Path Outage ID: 1-00664949 (N-S), 1-00664948 (1-00553170) (S-N) Peak RC Outage ID: 1-00664650 |  | 240 kV, Pre-Condition, Limits ATC
Syncrude | SCL1 Syncrude #1 | 2019-07-26 08:00 | 2019-08-08 16:00 | N | N | P2226. G2 AVR & PSS Upgrade ISD Aug 1, 2019 | Unit
ENMAX | 41.84L (ENMAX 54 - ENMAX 41) | 2019-07-26 08:00 | 2019-07-26 16:00 | N | N | maintenance | Line |  | Doble 41B138-41.84 | Firm Load Loss, Creates Radial Feeds
ENMAX | 34.2TR (ENMAX 34) | 2019-07-26 12:00 | 2019-11-07 16:00 | N | N | 34.2TR replacement & yard construction | Transformer | 34.2TR (ENMAX 34) |  | For Information Only
ALTALINK | 164S Empress Liquids,760AL (164s Empress Liquids - 760L41),760L (163s Amoco Empress - 760L41),163s 760N (163s Amoco Empress) | 2019-07-27 07:00 | 2019-07-28 18:00 | N | N | urgent line mitigation on structures #16 & 17 | Line, Circuit Breaker, Station |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.6TR (ENMAX 1) | 2019-07-27 08:00 | 2019-07-27 16:00 | N | N | replace SW47 PT fuse | Transformer |  |  | For Information Only
ATCO | 9L59 (972s Tinchebray - 801s Anderson) | 2019-07-27 15:32 | 2019-07-31 16:10 | N | Y | forced outage | Line |  |  | 240 kV, Creates Radial Feeds
ATCO | 826s 502R (826s Marguerite Lake) | 2019-07-27 19:18 | 2019-09-19 19:15 | N | N | forced outage | Shunts |  |  | Pre-Condition
ATCO | 7L183 (856s Kinosis - 2060s Engstrom) | 2019-07-28 07:00 | 2019-07-28 16:00 | N | N | shut down 7L183 to move two 9 meter highloads | Line |  | Field crews need to shut down 7L183 to get two 9 meter Highloads into the Conoco site. 2081S Meadow Creek will be OOS (Load transferred to Kinosis) for the duration. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
SUNCOR | 30EDD-2 | 2019-07-28 08:00 | 2019-08-11 18:00 | N | Y | maintenance and testing on breaker | Station |  | Mtce & testing on breaker, cable and other electrical apparatus inclusive of protective relays. | For Information Only
ALTALINK | 162L (415s Drywood - 229s Glenwood),415s 146E (415s Drywood) | 2019-07-28 09:00 | 2019-08-01 09:00 | N | N | install new breaker control/breaker fail on breaker 252 (415s146E) | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 930s Syn Condenser (930s Arcenciel) | 2019-07-28 11:18 | 2019-07-31 12:19 | N | Y | forced out-of-service | Shunts |  |  | For Information Only
EPCOR | 987s CGB1 (987s Clover Bar) | 2019-07-29 | 2019-07-29 06:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2019-07-29 07:00 | 2019-07-29 18:00 | N | N | high load move between structures #341 & 342 | Line |  | High load move between Structures #341 & 342 | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 413L (239s Castle River - 632s Russell) | 2019-07-29 07:30 | 2019-07-29 15:30 | N | Y | switch maintenance | Line |  |  | Restricts Generation
ENMAX | 28.2TR (ENMAX 28) | 2019-07-29 08:00 | 2019-08-02 16:00 | N | N | 28s 138kV BD and AS relay replacement | Transformer |  |  | For Information Only
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2019-07-29 08:00 | 2019-08-01 18:30 | N | N | change arms insulators/fix conductor/shield wire. Project E63415 | Line |  | Transmission Maintenance Project. change arms insulators/fix conductor/shield wire. Project E63415 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
TRANSALTA | 239s T2 (239s Castle River) | 2019-07-29 08:00 | 2019-07-30 17:00 | N | N | maintenance | Transformer |  |  | Restricts Generation
ENMAX | 47.2TR (ENMAX 47) | 2019-07-29 08:00 | 2019-07-30 16:00 | N | N | inspection and maintenance | Transformer |  | Tapchanger inspection. Oil sampling TC, MT, Check reversing switch. (TR maint. Gas relay) | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33) | 2019-07-29 08:00 | 2019-07-29 16:00 | N | N | Doble 41B138-33.83 | Line |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 29EDD-1 29EDD1S1252 (29EDD-1),29EDD-1 29EDD1S1152 (29EDD-1),29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island | 2019-07-29 08:00 | 2019-08-06 18:00 | N | N | perform maintenance and testing | Line, Circuit Breaker |  | Perform maintenance and testing (5/10yr) breakers & CVT: 29PS-195, 29EDD1S27, 29EDD1S26, 29EDD1S1152, 29EDD1S1252, 29CTV-5A/B/C, 29PLA-184A/B/C, 29PL6 R23 A relay | Contingency Requires Mitigation, For Information Only
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2019-07-29 09:30 | 2019-08-01 18:00 | N | Y | structure upgrades | Line |  | Structure Refurbishment & Upgrades | 240 kV
ATCO | 815s 701T (815s Goodfare) | 2019-07-29 10:00 | 2019-08-01 14:00 | N | N | maintenance | Transformer |  | 815S 701T Maintenance & 501VRX Change out load will be transferred to Mobile Sub. 144KV Bus Differential Relay will be block for the Mobile install | For Information Only
ALTALINK, EPCOR | 908L (89s Ellerslie - 816s Petrolia),89s 652 (89s Ellerslie),89s 752 (89s Ellerslie) | 2019-07-29 10:45 | 2019-08-01 17:45 | N | Y | breaker maintenance | Circuit Breaker, Line |  | 240kV breaker maintenance, leaking capacitors; 89s13 doesn't fully open adjustment needed | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 185AL (415s Drywood - 995s Yarrow) | 2019-07-29 12:30 | 2019-07-31 14:00 | N | N | replace 3 HV bushings | Line |  | replace 3 HV bushings, and 69kV LAs on T1 | For Information Only
CNRL | 1034s T1 (1034s Margie) | 2019-07-29 14:00 | 2019-08-05 09:00 | N | N | maintenance | Transformer |  |  | For Information Only
EPCOR | 987s CGB2 (987s Clover Bar) | 2019-07-30 | 2019-07-30 06:00 | N | Y | maintenance | Circuit Breaker |  |  | Restricts Generation
NWE | Marias Shunt Capacitor | 2019-07-30 01:42 | 2019-08-02 01:42 | N | Y | bank #3 forced outage | Shunts |  |  | For Information Only
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2019-07-30 07:00 | 2019-08-06 18:00 | N | N | changing crossarms and insulators | Line |  | Urgent Fire Mitigation - changing crossarms and insulators from structure 496 to 805
Medicine Hat, CMH | MH69s3 MH69_308 (MH69s3 South Ridge),MH69s5 MH69_502 (MH69s5 NE Crescent Height),MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2019-07-30 07:00 | 2019-07-31 16:00 | N | N | repair damage from April equipment failure | Circuit Breaker, Line |  |  | Firm Load Loss, Creates Radial Feeds, For Information Only
ATCO | 791s 701T (791s Rainbow Lake), 791s 702T (791s Rainbow Lake) | 2019-07-30 07:00 | 2019-10-30 17:00 | N | N | substation rebuild project | Transformer | 791s 701T (791s Rainbow Lake), 791s 702T (791s Rainbow Lake) | 791S Substation Rebuild Project - Re-Configure 25KV Bus /Replace POD transformers & Breakers All 25kv load transferred to 828S Sulphur Point. Isolation: 25KV Jumpers J3, J4, J5 & J6 & 144KV Jumpers J1 & J2, station service fed by on site generator | For Information Only
ENMAX, ALTALINK | 12.1TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12) | 2019-07-30 08:00 | 2019-07-30 18:00 | N | Y | adjust MD Alignment | Line, Transformer |  | Adjust MD Alignment on the next Outage. [AVANTIS] 12 Sub 12MD138-12.1TR Phases not flat. Doble 10PT138-832 | Firm Load Loss, Creates Radial Feeds
AESO-SC | OATI | 2019-07-30 08:00 | 2019-07-30 16:00 | N | N | performing maintenance on the Minneapolis data center load balancers | SCInternal |  |  | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2019-07-30 09:00 | 2019-08-02 17:00 | Y | Y | tree removals | Line |  |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2019-07-30 09:15 | 2019-07-31 17:00 | N | N | urgent repair | Line |  | urgent repair 174L452 change both arms and insulation on STR 452 | Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 987s CGB3 (987s Clover Bar) | 2019-07-31 | 2019-07-31 06:00 | N | Y | maintenance | Circuit Breaker |  | CPC Outage Request | Restricts Generation
ENMAX | 32.3TR (ENMAX 32) | 2019-07-31 08:00 | 2019-08-02 16:00 | N | N | tapchanger inspection, check reversing switch, oil sampling MT, TC | Transformer |  |  | For Information Only
ALTALINK | 574s T2 (574s Nilrem) | 2019-07-31 08:00 | 2019-08-01 16:45 | N | Y | maintenance, doble, replace neutral conductor, oil leaks, qualitrol modifications | Transformer |  | TX maintenance, doble, replace neutral conductor, oil leaks, qualitrol modifications | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 9.83L (ENMAX 43 - ENMAX 9),ENMAX 43 B138-9.83 (ENMAX 43) | 2019-07-31 08:00 | 2019-07-31 12:00 | N | N | 43.2TR protection upgrade, commission trip circuits | Circuit Breaker, Line |  | 43.2TR Protection Upgrade. Commission trip circuits. | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 24.82L (ENMAX 65 - ENMAX 24),ENMAX 65 B138-D82 (ENMAX 65),ENMAX 65 B138-D81 (ENMAX 65),ENMAX 65 PT138-24.82 (ENMAX 65) | 2019-07-31 08:00 | 2019-07-31 16:00 | N | N | doble 65PT138-24.82 | Line, Terminal Equipment, Circuit Breaker |  |  | Pre-Condition, For Information Only
AESO-SC | OATI | 2019-07-31 08:00 | 2019-07-31 16:00 | N | N | performing maintenance on the Bloomington data center load balancers | SCInternal |  |  | For Information Only
ENMAX, ALTALINK | 28.2TR (ENMAX 28),28.80L (42s Sarcee - ENMAX 28) | 2019-07-31 08:30 | 2019-07-31 16:00 | N | Y | relay replacement and testing | Line, Transformer |  | 28s 138kV BD and AS relay replacement. Test MD open circuit and short bus diff CTs. Original outage July 29th | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-07-31 11:00 | 2019-07-31 15:00 | N | Y | maintenance | Switch |  | BH2 generator brushgear maint outage | Restricts Generation
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2019-07-31 12:00 | 2019-08-01 18:00 | N | N | high load move between structures #198 & 199 | Line |  | High load move between Structures #198 & 199 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 6.4TR (ENMAX 6),6.80L (ENMAX 35 - ENMAX 6) | 2019-08-01 08:00 | 2019-08-01 16:00 | N | N | doble 6PT138-6.80. 6PT138-Z31. distance elements disabled on 6.82L while PTs are offline | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK, ATCO | 7L437 (993s Abee - 947s Weasel Creek),993s T1 (993s Abee) | 2019-08-01 08:00 | 2019-08-01 17:15 | N | N | station outage | Transformer, Line |  | Customer requested station outage | For Information Only
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-08-01 09:00 | 2019-08-01 13:00 | N | Y | maintenance | Switch |  | BH2 generator brushgear maint outage | Restricts Generation
ALTALINK | 164L (103s Goose Lake - 415s Drywood),415s 21 (415s Drywood) | 2019-08-01 09:00 | 2019-08-01 15:00 | N | N | test new 415s146E and 415s352 breaker fail trips to 415s21 | Line, Circuit Breaker |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
TRANSALTAW | 418s Ardenville | 2019-08-02 08:00 | 2019-08-02 12:00 | N | Y | maintenance | Station |  |  | Restricts Generation
ALTALINK, EPCOR | 330p 1205 (330p Genesee),330p 1206 (330p Genesee),1239L (510s Sunnybrook - 330p Genesee) | 2019-08-02 08:00 | 2019-08-02 17:00 | N | Y | doble cts | Line, Circuit Breaker |  |  | Pre-Condition, 500 kV
GWPCORP | 243S Soderglen Wind Farm | 2019-08-06 07:00 | 2019-08-07 18:00 | N | N | maintenance | Station |  |  | Restricts Generation
ALTALINK | 784L (332s Ellis - 784AL tap),332s 784 (332s Ellis) | 2019-08-06 07:30 | 2019-08-08 17:30 | N | N | connecting temporary bypass | Circuit Breaker, Line |  | Connecting temporary bypass and creating Open points 'C' & 'D' | Pre-Condition
BLACKSPRING | 485S Black Springs | 2019-08-06 08:00 | 2019-08-09 17:00 | N | N | annual maintenance on DSTATCOM | Station |  |  | For Information Only
EPCOR | 816s P2401 (816s Petrolia) | 2019-08-06 08:00 | 2019-08-07 17:00 | N | Y | splitting of DC | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 11.1TR (ENMAX 11) | 2019-08-06 08:00 | 2019-08-20 02:00 | N | N | install new transformer secondary cables, energize new switch gear | Transformer | Install new transformer secondary cables. Secondary cable test. Energize new 8kV switch gear on return to service. |  | For Information Only
EPCOR | Hardisty H725 (Hardisty Epcor) | 2019-08-06 08:00 | 2019-08-06 16:00 | N | N | investigate and repair low SF6 | Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 352 (39s Bickerdike) | 2019-08-06 08:00 | 2019-08-10 12:00 | N | N | replace breaker fail and control module | Circuit Breaker |  | Replace s352 breaker fail module and control module with new C60 breaker fail and control module. | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 5.6TR (ENMAX 5) | 2019-08-06 08:00 | 2019-08-09 16:00 | N | N | tapchanger inspection, check reversing switch | Transformer |  | HICO Transformer Tapchanger Re-plumb. Tapchanger inspection. Check reversing switch | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2019-08-06 08:00 | 2019-08-06 16:00 | N | N | doble testing | Line | Doble 6PT138-6.82 |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 14.1C (ENMAX 14),14.2C (ENMAX 14) | 2019-08-06 08:00 | 2019-08-06 16:00 | N | N | HV breaker maintenance | Shunts | HV Breaker maintenance 14CS138-14.2CAP |  | For Information Only
ENMAX | 32.3TR (ENMAX 32) | 2019-08-06 08:00 | 2019-08-09 16:00 | N | N | doble test and maintenance | Transformer |  | Doble test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch | For Information Only
ENMAX | 1.80L (ENMAX 28 - ENMAX 1) | 2019-08-06 08:00 | 2019-08-06 16:00 | N | N | new development doing pilings | Line | New development doing pilings. |  | Firm Load Loss, Creates Radial Feeds
Syncrude | SCL1 Syncrude #1 | 2019-08-06 08:00 | 2019-08-20 16:00 | N | N | P2095. G4 AVR & PSS Upgrade ISD August 13, 2019 | Unit
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm) | 2019-08-06 08:00 | 2019-08-07 16:00 | N | Y | urgent outage repairs to structures | Line |  | repairs to Structures #37 & 38 for clearance mitigation. | Affects Visibility, For Information Only
AESO-SC | Video Wall Hardware | 2019-08-06 08:00 | 2019-08-07 17:00 | N | N | Change Lens in Barco controllers | SCInternal
ALTALINK | 89s 1352 (89s Ellerslie) | 2019-08-06 09:00 | 2019-08-14 09:00 | N | Y | replace protection relay | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. | 240 kV
ALTALINK | 786L (799s Coleman - Natal) | 2019-08-06 09:00 | 2019-08-16 17:00 | N | Y | re-building | Line | Peak RC COS outage ID: 1-00665887 | Re-building from Structures #77 - 81 | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1064L (102s Langdon - 74s Janet),74s 2752 (74s Janet),74s 2852 (74s Janet) | 2019-08-06 10:15 | 2019-08-09 15:45 | N | Y | SCADA equipment upgrade | Line, Circuit Breaker |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | 240 kV
ALTALINK | 172EL (139s Hillridge - 172EL1),172L (83s Taber - 172L944A),172L (254s Coaldale - 172L944C) | 2019-08-06 19:21 | 2019-08-09 16:00 | N | Y | damaged structures due to storm | Line |  |  | Restricts Generation
ALTALINK | 671L (58s Edson - 39s Bickerdike) | 2019-08-07 07:00 | 2019-08-07 18:00 | N | N | urgent fire mitigation, make repairs on structures 25, 57, 102, 109, 115 and 121 | Line |  | Urgent Fire Mitigation - Make repairs on structures 25, 57, 102, 109, 115 and 121. | Pre-Condition
ALTALINK | 906L (17s Benalto - 42s Sarcee) | 2019-08-07 07:45 | 2019-08-07 17:45 | N | Y | repair 17s906X | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 38.1TR (ENMAX 38) | 2019-08-07 08:00 | 2019-08-07 12:00 | N | N | scan the concrete where the secondary cables enter the 8kV cells | Transformer |  |  | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32),32PT138-Z32 (ENMAX 32) | 2019-08-07 08:00 | 2019-08-07 16:00 | N | N | breaker maintenance | Line, Transformer, Terminal Equipment |  | HV Breaker Maintenance 32B138-31.84. Doble 32PT138-Z32PT. Wiring modifications 31B138-31.84, 32B138-31.84 | Pre-Condition, For Information Only
ALTALINK | 89s 452 (89s Ellerslie) | 2019-08-07 08:30 | 2019-08-08 17:30 | N | Y | warranty repair | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 205s 452 (205s Castle Rock), 205s 240 kV Bus 2 (205s Castle Rock Ridge) | 2019-08-07 09:00 | 2019-11-12 17:00 | N | Y | construction for new wind farm | Circuit Breaker, Bus | 205s 452 (205s Castle Rock),205s 240 kV Bus 2 (205s Castle Rock Ridge) |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
AESO-SC | MSAT Iridium | 2019-08-07 11:00 | 2019-08-07 12:00 | N | N | scheduled system maintenance | SCInternal |  |  | Pre-Condition
ENMAX | 38.2TR (ENMAX 38) | 2019-08-07 12:00 | 2019-08-07 16:00 | N | N | scan the concrete where the secondary cables enter the 8kV cells | Transformer |  |  | For Information Only
BCH | 5L96 (Selkirk - Vaseux Lake) | 2019-08-07 13:19 | 2019-08-09 20:30 | N | Y | forced due to fight the fire near VAS | Line | Peak RC outage ID: 1-00666953 Peak RC path ID: 1-00667062 (E>W, export), 1-00667063 (W>E, import) | BC Forest service has requested that 5L96 be deenergized while they fight the fire near VAS. | Limits ATC, 500 kV
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2019-08-07 16:00 | 2019-09-26 17:00 | N | Y | urgent outage to address clearance issues | Line | 50L (44s Bearspaw Plant - ENMAX 21) |  | For Information Only, Pre-Condition
ATCO | 796s 701T (796s Nipisi) | 2019-08-08 07:00 | 2019-09-20 17:00 | N | N | switching to isolate 701T for 25kV GIS replacement project | Transformer |  | Switching to isolate 701T for 25kv GIS replacement Project
ENMAX | 38.1C (ENMAX 38),ENMAX 38 B138-38.1CAP (ENMAX 38) | 2019-08-08 08:00 | 2019-08-08 16:00 | N | N | breaker maintenance 38B138-38.1CAP | Circuit Breaker, Shunts |  | HV Breaker Maintenance 38B138-38.1CAP | Pre-Condition
ENMAX | 37.81L (ENMAX 38 - ENMAX 37),ENMAX 37 B138-37.81 (ENMAX 37) | 2019-08-08 08:00 | 2019-08-08 18:00 | N | N | doble 37B138-37.81 | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power S1C line | 2019-08-08 08:00 | 2019-08-16 18:00 | N | Y | maintenace | Line |  |  | Limits ATC
EPCOR | 816s P2402 (816s Petrolia) | 2019-08-08 08:00 | 2019-08-09 17:00 | N | Y | splitting the DC | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 5s C3 (5s East Calgary) | 2019-08-08 08:30 | 2019-08-08 11:30 | N | N | emergency de-energize for weed removal in cap bank area | Shunts |  |  | Pre-Condition
TRANSALTA, ALTALINK | 528s Blue Trail Wind Farm RTU/SCADA,418s Ardenville RTU/SCADA,240s McBride Lake RTU/SCADA | 2019-08-08 09:00 | 2019-08-08 13:30 | N | N | Telus circuit testing | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 784L (332s Ellis - 784AL tap),332s 784 (332s Ellis) | 2019-08-08 17:30 | 2019-09-03 13:00 | N | N | install new air breaks 784L74A & 784AL1A | Line, Circuit Breaker |  |  | Pre-Condition
ALTALINK | 38s East Edmonton | 2019-08-09 08:00 | 2019-08-23 16:00 | N | N | connect new 25 kV feeder 38s1822 ISD: Aug 16, 2019 | Not In Model
ALTALINK | 83s C2 (83s Taber),83s T3 (83s Taber),610L (336s Fincastle - 83s Taber),83s Taber 138kV West Bus | 2019-08-09 08:00 | 2019-08-09 16:00 | N | Y | urgent repair 83s36 | Line, Shunts, Transformer, Bus |  |  | Pre-Condition, Over/Under Voltage, Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.84L (ENMAX 43 - ENMAX 33),ENMAX 33 B138-33.84 (ENMAX 33) | 2019-08-09 08:00 | 2019-08-09 16:00 | N | N | SF6 gas sample 33B138-33.84 | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 172L (83s Taber - 172L944A) | 2019-08-09 16:01 | 2019-08-11 14:00 | N | Y | damaged structures due to storm | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ENMAX | 38.1C (ENMAX 38),38.2TR (ENMAX 38),38.3TR (ENMAX 38),37.81L (ENMAX 38 - ENMAX 37) | 2019-08-10 08:00 | 2019-08-10 18:00 | N | N | doble 38PT138-Z31 | Line, Transformer, Shunts |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 252 (39s Bickerdike) | 2019-08-10 12:30 | 2019-08-10 14:30 | N | N | trip testing s252 from new s352 C60 breaker fail module. | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 39s 452 (39s Bickerdike) | 2019-08-10 14:30 | 2019-08-10 16:30 | N | N | trip testing s452 from new s352 C60 breaker fail module. | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2019-08-11 09:00 | 2019-08-11 13:00 | N | N | vibration sensors installed for Bonnybrook tunnel relocation | Line |  |  | Pre-Condition
ENMAXGPI | 134S Taber Wind Farm | 2019-08-12 00:01 | 2019-08-19 19:35 | N | Y | MET tower replacement | Station |  |  | For Information Only
VISIONREQ | 354s T2 (354s Summerview) | 2019-08-12 07:00 | 2019-08-13 17:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
EPCOR | Rossdale T3 (Rossdale) | 2019-08-12 07:00 | 2019-08-16 17:00 | N | N | doble | Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation
EPCOR | 72JW19 (805s Jasper - Woodcroft),Woodcroft T1 (Woodcroft) | 2019-08-12 07:00 | 2019-08-16 17:00 | N | N | WDS2 LCR, doble | Transformer, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 418L (20s Ghost - 418L193A) | 2019-08-12 07:00 | 2019-08-15 18:00 | N | N | urgent fire mitigation, structure changes at structures #5, 13, 109 & 110 | Line |  | Urgent fire mitigation; Scope of work includes complete structure changes at Structures #5, 13, 109 & 110 | Pre-Condition
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2019-08-12 07:00 | 2019-08-17 18:00 | N | N | grounding repairs, insulator replacements and structure replacements | Line |  | Scope of work includes grounding repairs, insulator replacements, And 5 complete structure replacements Structures 11, 15, 111, 126, 131, 134, 141, 142, 153 and 163. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2019-08-12 07:00 | 2019-08-13 18:00 | N | N | urgent repair to conductor between structures #292 & 293 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s 1752 (275s Jenner) | 2019-08-12 07:30 | 2019-08-12 16:45 | N | Y | settings changes of sync check and functional testing on 275s1752 | Circuit Breaker |  | Settings Changes of Sync Check and Functional Testing on 275s1752 | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 39s 452 (39s Bickerdike) | 2019-08-12 08:00 | 2019-08-16 11:00 | N | N | replace breaker fail and control module with new C60 module | Circuit Breaker |  | Replace s452 breaker fail module and control module with new C60 breaker fail and control module | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 1107L (ENMAX 65 - 237s Foothills) | 2019-08-12 08:00 | 2019-08-12 18:00 | N | Y | substation washing | Line |  |  | 240 kV
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2019-08-12 08:00 | 2019-08-15 16:00 | N | Y | urgent - 23B138-23.80 SF6 leak repair | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 20.1TR (ENMAX 20) | 2019-08-12 08:00 | 2019-08-12 16:00 | N | N | winding temp alarm | Transformer |  |  | For Information Only
EPCOR | 816s P2403 (816s Petrolia) | 2019-08-12 08:00 | 2019-08-13 17:00 | N | Y | splitting the DC | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ENMAX | 16.2TR (ENMAX 16) | 2019-08-12 08:00 | 2019-08-16 16:00 | N | N | doble test, maintenance and testing, check reversing switch | Transformer |  | Doble test transformer. Transformer secondary cable tests. Transformer maintenance. Gas relay testing. Check reversing switch. | For Information Only
ATCO | 7L159 (7L159 tap - 770s Three Hills) | 2019-08-12 10:00 | 2019-08-16 23:59 | N | N | crossarm/insulator replacement | Line |  | Crossarm/insulator replacement - line returned each evening | Firm Load Loss, Creates Radial Feeds
ALTALINK | 1065L (102s Langdon - 74s Janet) | 2019-08-12 10:15 | 2019-08-15 15:45 | N | Y | SCADA equipment upgrade | Line |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | 240 kV
ALTALINK | 171s T1 (171s Redwater),735L (171s Redwater - 233s Beamer) | 2019-08-12 10:30 | 2019-08-15 18:00 | N | N | 171s284X breaker replacement | Transformer, Line |  | - 171s284X breaker replacement, 171s284X LAs, 171s92X LAs, 735L insulators, AC1-JB | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 722s 701T (722s Crystal Lake),7L39 (7L39 tap - 722s Crystal Lake) | 2019-08-12 11:00 | 2019-08-14 18:00 | N | Y | change foundation anchors on bus structure | Transformer, Line |  | 722S 700BS1 Foundation Change Change foundation anchors on bus structure Sub radially fed from 7L84 From Flyingshot. | Firm Load Loss, Creates Radial Feeds
ALTALINK | 65s T3 (65s High River) | 2019-08-12 11:15 | 2019-08-15 15:15 | N | N | transformer maintenance, doble, fix leaks and CT connection | Transformer | T3 maintain, doble, fix leaks, 65s812W CT connection hotspot fix, 65s46 s/w exercise clean/adjust, Tx storage bin |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 835L (384s Keystone - 835L tap) | 2019-08-12 11:30 | 2019-08-16 18:30 | N | N | replacing CTs and line protections | Line | Replacing 138kV CTs associated with 384s835X and replacing both A and B line protections on 835L during same outage |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 11.4TR (ENMAX 11) | 2019-08-13 02:00 | 2019-08-14 02:00 | N | N | arc flash switchgear construction | Transformer |  |  | For Information Only
VISIONREQ | 354s T4 (354s Summerview) | 2019-08-13 07:00 | 2019-08-14 17:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 324s 1252 (324s Cassils) | 2019-08-13 07:30 | 2019-08-13 16:45 | N | Y | settings changes of sync check and functional testing on 324s1252 | Circuit Breaker |  | Settings Changes of Sync Check and Functional Testing on 324s1252 | 240 kV, Contingency Requires Mitigation
AESO-SC | OATI | 2019-08-13 08:00 | 2019-08-13 16:00 | N | N | performing maintenance on the Minneapolis data center load balancers | SCInternal |  |  | For Information Only
ENMAX | 24.2TR (ENMAX 24) | 2019-08-13 08:00 | 2019-08-13 16:00 | N | N | repair 24BB25-24.2TR racking mechanism | Transformer |  | Outage required to repair 24BB25-24.2TR racking mechanism. | For Information Only
ENMAX | 22.3TR (ENMAX 22) | 2019-08-13 08:00 | 2019-08-14 16:00 | N | N | tapchanger maintenance, HV bushing hot spot repair, check reversing switch, oil sample CT | Transformer |  | Corrective. 22.3TR Tapchanger 22.3TR HV Bushing Hot Spot Repair. Check reversing switch. Oil sample TC. | For Information Only
ALTALINK | 1106L (ENMAX 65 - 237s Foothills) | 2019-08-13 08:00 | 2019-08-13 18:00 | N | Y | substation washing | Line |  | Substation Washing. 65MD240-1106 Investigate and repair whip operation | 240 kV, Pre-Condition
BLACKSPRING | 485S Black Springs | 2019-08-13 08:00 | 2019-08-14 13:00 | N | Y | point-to-point communication checkout | Station |  |  | Restricts Generation
ALTALINK | 89s 252 (89s Ellerslie) | 2019-08-13 08:45 | 2019-08-13 10:15 | N | Y | replace breaker fail protection relay module and breaker control module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s252 breaker from new breaker failure module. | 240 kV, Contingency Requires Mitigation
BCH | 5L96 (Selkirk - Vaseux Lake) | 2019-08-13 09:30 | 2019-08-13 13:30 | N | Y | urgent repair on guy wire | Line | Peak RC outage ID: 1-00667162 Peak RC path ID: 1-00667374 (E>W, export), 1-00667375 (W>E, import) | Urgent repair on guy wire. | Limits ATC, 500 kV
ALTALINK | 89s 652 (89s Ellerslie) | 2019-08-13 10:16 | 2019-08-13 11:45 | N | Y | replace breaker fail protection relay module and breaker control module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s652 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 89s 952 (89s Ellerslie) | 2019-08-13 11:46 | 2019-08-13 13:15 | N | Y | replace breaker fail protection relay module and breaker control module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s952 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 89s 1752 (89s Ellerslie) | 2019-08-13 13:16 | 2019-08-13 14:45 | N | Y | replace breaker fail protection relay module and breaker control module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s952 breaker from new breaker failure module. | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 2052 (89s Ellerslie) | 2019-08-13 14:46 | 2019-08-13 16:15 | N | Y | replace breaker fail protection relay module and breaker control module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s952 breaker from new breaker failure module. | Pre-Condition, Contingency Requires Mitigation, 500 kV
ENMAX | 1.80L (ENMAX 28 - ENMAX 1),ENMAX 28 B138-1.80 (ENMAX 28) | 2019-08-14 08:00 | 2019-08-15 12:00 | N | N | 28s 138kV BD and AS relay replacement. Re-terminate CT, loop check, ASW re-close and trip/lockout testing | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 32.2TR (ENMAX 32) | 2019-08-14 08:00 | 2019-08-14 16:00 | N | N | replace gas accumulation gas relay, LV breaker maintenance | Transformer |  | Replace Gas Accumulation Gas Relay on 32.2TR. LV Breaker Maintenance 32B8-32.2TR. | For Information Only
ENMAX | 28.1TR (ENMAX 28) | 2019-08-14 08:00 | 2019-08-14 12:00 | N | N | 138 kV BD and AS relay replacement | Transformer |  | 28s 138kV BD and AS relay replacement. Re-terminate CT, loop check, ASW re-close and trip/lockout testing | For Information Only
ALTALINK, ENMAX | 1109L (ENMAX 65 - ENMAX 25),ENMAX 65 B240-D135 (ENMAX 65),ENMAX 65 B240-D134 (ENMAX 65),ENMAX 25 MD240_1109 (ENMAX 25) | 2019-08-14 08:00 | 2019-08-16 18:00 | N | N | substation washing. doble 65PT240-1109. 1109 Las. investigate birds nest on B phase D135 @ 65 sub (see LD) | Line, Circuit Breaker, Switch |  | Substation Washing. Doble 65PT240-1109. 1109 Las. Investigate birds nest on B Phase D135 @ 65 Sub (See LD) | 240 kV, Pre-Condition
ALTALINK | 89s 1452 (89s Ellerslie) | 2019-08-14 09:30 | 2019-08-14 11:30 | N | Y | function trip test to89s1452 breaker from new breaker failure module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s1452 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 28.2TR (ENMAX 28) | 2019-08-14 12:00 | 2019-08-14 16:00 | N | N | 138kV BD and AS relay replacement | Transformer |  | 28s 138kV BD and AS relay replacement, re-terminate CT, loop check, ASW re-close and trip/lockout testing | Pre-Condition, For Information Only
EPCOR | 816s P2404 (816s Petrolia) | 2019-08-15 08:00 | 2019-08-16 17:00 | N | Y | splitting the DC | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 15.60L (ENMAX 21 - ENMAX 15),ENMAX 15 B69-15.60 (ENMAX 15) | 2019-08-15 08:00 | 2019-08-15 18:00 | N | N | 15B69-15.60, change oil and re-test PF | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
SUNCOR | 836s 624T (836s Steep Bank) | 2019-08-15 08:00 | 2019-09-09 14:49 | N | N | 5 year 624T transformer maintenance and repair | Transformer |  | Repair 624T leaking Brushing & 5 year transformer maintenance Will update elements not available at a later date | For Information Only
ATCO | 722s 702T (722s Crystal Lake),7L84 (722s Crystal Lake - 749s Flyingshot Lake),722s Crystal Lake 144 kV bus | 2019-08-15 08:00 | 2019-08-18 18:00 | N | Y | 722S 700BS2 foundation change | Bus, Transformer, Line |  | 722S 700BS2 Foundation Change Change foundation anchors on bus structure Sub radIally fed from 7L39 Clairmont . 700PT1 will be out of service. 7L39 distance protection will be blocked | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28),ENMAX 28 B138-28.80 (ENMAX 28) | 2019-08-15 12:00 | 2019-08-15 16:00 | N | Y | 138kV BD and AS relay replacement, re-terminate CT and ASW re-close and trip/lockout testing | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale T3 (Rossdale),Rossdale R724 (Rossdale),Rossdale R723 (Rossdale) | 2019-08-16 07:00 | 2019-08-16 17:00 | N | N | doble | Transformer, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
SUNCOR | 29EDD-56 29PT-190 (29EDD-56) | 2019-08-16 08:00 | 2019-08-22 18:00 | N | Y | replace and commission TAP | Transformer |  | 29EDD-56; 29PT-190 - OLTC CARD FAIL replace and comission TAP | 240 kV
ALTALINK | 39s 352 (39s Bickerdike) | 2019-08-16 11:30 | 2019-08-16 13:30 | N | N | advice for trip testing s352 from new s452 C60 breaker fail module | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 39s 852 (39s Bickerdike) | 2019-08-16 13:30 | 2019-08-16 15:30 | N | N | advice for trip testing s852 from new s452 C60 breaker fail module | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation
ALTALINK | 795L (121s Brooks - 421s Hays) | 2019-08-16 13:50 | 2019-09-16 14:30 | N | N | urgent clearance mitigation | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 39s 1052 (39s Bickerdike) | 2019-08-16 15:30 | 2019-08-16 17:30 | N | Y | advice for trip testing s1052 from new s452 C60 breaker fail module | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 39s 29 (39s Bickerdike) | 2019-08-16 17:30 | 2019-08-16 19:30 | N | Y | advice for trip testing s29 from new s452 C60 breaker fail module | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 7L159 (948s Heatburg - 7L159 tap) | 2019-08-17 | 2019-08-19 16:00 | N | N | crossarm/insulator replacement | Line |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 77s T2 (77s Sagitawah),826L (701s Blue Ridge Lumber - 77s Sagitawah),77s 652 (77s Sagitawah),77s 452 (77s Sagitawah),77s Sagitawah 138 kV East Bus | 2019-08-17 08:00 | 2019-08-17 19:00 | N | Y | 701sT1 maintenance | Bus, Circuit Breaker, Transformer, Line |  | 701sT1 maint 701sT1 doble, 90255282, 701s T1 Thermal Plate oil leak, 701S826 CS SF6 138KV S+C (TX) 701s19 U/G terminators need repair. 826L Line Structure Dead End Replacements inside 77s and 701s. | 240 kV, Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 34.3TR (ENMAX 34) | 2019-08-17 08:00 | 2019-08-20 16:00 | N | N | 34.2TR replacement., yard construction | Transformer |  | 34.2TR replacement. Yard construction. Construct temporary power cables to remove the 34.3TR ducts. Phasing required across 34MD69-34.3TR | For Information Only
ENMAX | 3.3TR (ENMAX 3),3.82L (ENMAX 3 - ENMAX 8) | 2019-08-17 08:00 | 2019-08-17 13:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 3.4TR (ENMAX 3),3.84L (ENMAX 13 - ENMAX 3) | 2019-08-17 13:00 | 2019-08-17 18:00 | N | N | substation washing, check reversing switch | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 1.82L (ENMAX 1 - ENMAX 5) | 2019-08-18 08:00 | 2019-08-18 18:00 | N | N | 5B138-1.82 doble CTs, SF6 gas sample | Line |  |  | Pre-Condition, For Information Only
EPCOR | Rossdale T4 (Rossdale) | 2019-08-19 07:00 | 2019-08-23 17:00 | N | N | doble | Transformer |  |  | For Information Only
EPCOR | 987s CCP7214 (987s Clover Bar) | 2019-08-19 07:00 | 2019-09-06 17:00 | N | N | breaker replacement | Circuit Breaker |  |  | Pre-Condition, For Information Only
ALTALINK | 745L (602s Cold Creek - 745L482) | 2019-08-19 07:00 | 2019-08-19 17:00 | N | Y | urgent fire mitigation work on structure # 644 | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RW3 (Rossdale - Woodcroft),Woodcroft W724 (Woodcroft),Woodcroft W725 (Woodcroft) | 2019-08-19 07:00 | 2019-08-26 17:00 | N | N | disconnect replacement | Circuit Breaker, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 7L33 (7L33D2 - 845s Big Mountain),845s 708 (845s Big Mountain),845s 707 (845s Big Mountain) | 2019-08-19 08:00 | 2019-08-21 12:30 | N | Y | change foundation on 707PT | Line, Circuit Breaker |  | Change foundation on 707PT | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ATCO | 2075s T11 (2075s Newell) | 2019-08-19 08:00 | 2019-08-29 15:00 | N | Y | 2019 turnaround maintenance | Transformer |  | 2019 TURNAROUND MAINTENANCE at NEWELL 2075S (GOI #2) 13L50 will be out of Service | Pre-Condition, 500 kV
ENMAX | 22.1TR (ENMAX 22) | 2019-08-19 08:00 | 2019-08-29 14:00 | N | N | doble and maintenance | Transformer |  | Doble test transformer, Transformer Secondary Cable Tests (X)(Y), Transformer Maintenance, Gas Relay Testing. Check reversing switch X,Y | For Information Only
ATCO | 2029s T11 (2029s Heathfield) | 2019-08-19 08:00 | 2019-08-29 15:00 | N | Y | 2019 turnaround maintenance | Transformer |  | 2019 TURNAROUND MAINTENANCE at HEATHFIELD 2029S (GOI #1) 13L50 will be out of Service | Pre-Condition, 500 kV
SUNCOR | 29EDD-56 | 2019-08-19 08:00 | 2019-09-09 15:01 | N | Y | 5 year maintenance | Station |  | Perform 5 year mtce on: 29PP-41A, 29PP-41B, 29PP-41C, 29PP-41H | 240 kV, For Information Only
ENMAX, ALTALINK | ENMAX 65 B240-D132 (ENMAX 65),ENMAX 65 B240-D131 (ENMAX 65),1080L (ENMAX 65 - ENMAX 25) | 2019-08-19 08:00 | 2019-08-19 18:00 | N | N | doble 65PT240-1080 | Line, Circuit Breaker |  | Doble 65PT240-1080. SF6 Sample 65-D131, 25-D132. Substation washing PT1080. | 240 kV, Pre-Condition, Contingency Requires Mitigation
EPCOR | 816s P2405 (816s Petrolia) | 2019-08-19 08:00 | 2019-08-20 17:00 | N | Y | splitting the DC | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALBIAN | 920s 901T (920s Jackpine) | 2019-08-19 08:00 | 2019-08-26 17:00 | N | Y | transformer preventive maintenance | Transformer |  | OLTC & Transformer Preventive Maintenance | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive),6L97 (735s Swan River - 739s Edith Lake),739s 601 (739s Edith Lake),739s 603 (739s Edith Lake),739s 602 (739s Edith Lake) | 2019-08-19 08:00 | 2019-09-06 17:00 | N | N | install new line protection relays | Circuit Breaker, Line |  | The scope of work is A GOI will be needed to install these new line protection relays. Remove 67N/6L11 and 67N/6L97 Install 21A/6L11 and 21A/6L97 SEL-421 21A/6L11 and 21A/6L97 will be renamed to 21B/6L11 and 21B/6L97 600PT1X renamed to 600PT1X2 | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2019-08-19 08:00 | 2019-08-29 15:00 | N | Y | 2019 turnaround maintenance | Line |  | 2019 TURNAROUND MAINTENANCE on 13L50 (GOI #3) 2029S and 2075S will be out of Service | Pre-Condition, 500 kV
ENMAX | 54.1TR (ENMAX 54) | 2019-08-19 08:00 | 2019-08-22 16:00 | N | N | tapchanger inspection | Transformer |  | Tapchanger inspection. Check reversing switch. Filmax maintenance. Oil sampling MT, TC. Repair LTC Counter. HICO Transformer Tapchanger Re-plumb | For Information Only
ATCO | 832s 701TCS (832s Blumenort) | 2019-08-19 09:00 | 2019-08-21 16:00 | N | N | testing 701TCS operation | Circuit Recloser |  | Testing 701TCS operation | For Information Only
ALTALINK | 415s 352 (415s Drywood) | 2019-08-19 09:00 | 2019-08-22 14:00 | N | N | install new breaker control and breaker fail on breaker 352 | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 868s T1 (868s Keephills Make-Up) | 2019-08-19 09:30 | 2019-08-29 16:30 | N | N | upgrade metering and replace transformer bushing | Transformer |  |  | For Information Only
ALTALINK | 522AL (868s Keephills Make-Up - 522L tap),522L (866s Sundance Make-Up - 522AL tap) | 2019-08-19 09:30 | 2019-08-19 15:00 | N | N | create open point on 522AL for the work at 868s | Line |  |  | For Information Only
ENMAX, ALTALINK | 932L (74s Janet - SS-162), 74s 252 (74s Janet), 74s 552 (74s Janet), 162B240-RB135 (SS-162), 162s 240-136 (162s Beddington) | 2019-08-19 10:00 | 2019-09-15 16:30 | N | Y | line protection upgrade | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation,Affects Cranking Path
ALTALINK | 634s T1 (634s Shell Raven River),719BL (634s Shell Raven River - 719BL0) | 2019-08-19 10:00 | 2019-08-22 18:00 | N | N | transformer and 138 kV breaker maintenance | Transformer, Line |  | 634s T1(TX18601): maintenance, doble, DGA/Oil Quality sample/check, repair oil leaks 634s VR1(TX18604): maintenance, doble, LTC temperature differential investigation/repair 634s1: 138kV airbreak; replace connector bolts 634s4: 138kV switch; hotspot repair (12deg) 634s719: 138kV breaker maintenance | For Information Only
ALTALINK | 135s T1 (135s Conrad) | 2019-08-19 10:15 | 2019-08-22 14:45 | N | N | Fix T1, VR1 oil leaks, maintain and doble, replace t/c oil | Transformer |  | T1 leak maintenance and T1 bird cover-up installation.135sVR1 bushing replacement. | For Information Only
ALTALINK | 691L (74s Janet - 419s Chestermere) | 2019-08-19 10:15 | 2019-08-22 15:45 | N | N | SCADA equipment upgrade | Line | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 186s T2 (186s Dry Creek) | 2019-08-19 10:45 | 2019-08-21 17:15 | N | N | maintain, doble & SFRA T2, and repair LTC | Transformer |  |  | For Information Only
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2019-08-19 11:00 | 2019-08-21 16:00 | N | Y | replace 1 phase of CVT8 at 39s | Line |  |  | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan) | 2019-08-19 12:00 | 2019-08-22 17:30 | N | N | replacement of 138kV and 25kV bushings on T1 | Transformer |  | Replacement of 138kV and 25kV Bushings on T1, plugged rad, OBG3 Leaking, maintenance | Pre-Condition, For Information Only
BCH | 2L294 (Nelway - A.A. Lambert) | 2019-08-19 13:00 | 2019-08-30 17:00 | N | Y | annual plan request F20 - structure replacements | Line |  |  | Pre-Condition, Limits ATC
ALTALINK | 745L (39s Bickerdike - 745L480) | 2019-08-20 07:00 | 2019-08-20 17:00 | N | N | urgent fire mitigation work on structures # 391 & 402 | Line |  |  | Pre-Condition, Restricts Generation, Firm Load Loss, Creates Radial Feeds
Saskpower | SASK POWER P1C | 2019-08-20 07:00 | 2019-08-20 21:00 | N | Y | maintenance | Line |  |  | Limits ATC
DMIL | DAI1 52MW Turbo Generator | 2019-08-20 07:00 | 2019-08-20 19:00 | N | N | 839s701T outage | Unit
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2019-08-20 07:00 | 2019-08-23 18:00 | N | Y | urgent fire mitigation: structure changes and woodpecker damage repairs on structures | Line |  | urgent fire mitigation: scope of work consists of structure changes and woodpecker damage repairs on structures | Restricts Generation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 293s T1 (293s Bernese),293s T2 (293s Bernese) | 2019-08-20 07:00 | 2019-08-20 19:00 | N | N | NGR & electrical equipment maintenace - Enbridge | Transformer |  | 293s2, 293s3, 293s6, 293s7, 293s9, 293s10. | For Information Only
ATCO | 839s 701T (839s Daishowa Plant) | 2019-08-20 07:00 | 2019-08-20 19:00 | N | Y | 13.8 kV bird proofing and testing U/G cable | Transformer |  | 13.8 kV bird proofing and testing U/G cable PRP will not be able to generate power to the grid for duration of outage | Restricts Generation
ENMAX | 26.83L (ENMAX 65 - ENMAX 26) | 2019-08-20 08:00 | 2019-08-21 16:00 | N | N | breaker maintenance, substation washing, doble | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 89s 1652 (89s Ellerslie) | 2019-08-20 09:00 | 2019-08-28 09:30 | N | Y | replace existing breaker fail protection relay module and breaker control module with C60 module | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
BCH | 5L72 (Mica Creek - Nicola) | 2019-08-20 09:00 | 2019-08-30 17:00 | N | Y | arcing horn and spacer damper | Line | BC Outage Peak RC COS: AB Peak RC COS# : (W>E), (E>W) | arcing horn and spacer damper. BC Maintenance does not affect the Alberta ATC | For Information Only, 500 kV
ALTALINK | 418s Ardenville RTU/SCADA | 2019-08-20 10:00 | 2019-08-20 10:45 | N | N | firewall update | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 37s T3 (37s North Calder),726L (37s North Calder - 71s Lamoureux),747L (37s North Calder - 711L tap),898L (37s North Calder - 92s Viscount),37s North Calder 138kV Bus | 2019-08-20 10:45 | 2019-08-20 16:30 | N | N | emergency repair; jumper out 37s39 (failing switch) | Line, Transformer, Bus |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 243s Soderglen Wind Farm RTU/SCADA | 2019-08-20 10:50 | 2019-08-20 11:35 | N | N | firewall update | Terminal Equipment |  |  | Affects Visibility
VISIONREQ | 354s Summerview RTU/SCADA | 2019-08-20 12:40 | 2019-08-20 13:25 | N | N | firewall update | Terminal Equipment |  |  | Affects Visibility
TRANSALTA | 240s McBride Lake RTU/SCADA | 2019-08-20 13:30 | 2019-08-20 14:15 | N | N | firewall update | Terminal Equipment |  |  | Affects Visibility
SUNCOR | 139S Hillridge | 2019-08-20 14:00 | 2019-08-30 13:30 | N | N | equipment repair | Station |  |  | For Information Only
TRANSALTA, ALTALINK, VISIONREQ | 528s Blue Trail Wind Farm RTU/SCADA,322s Cowley Ridge RTU/SCADA,418s Ardenville RTU/SCADA,239s Castle River RTU/SCADA,240s McBride Lake RTU/SCADA,243s Soderglen Wind Farm RTU/SCADA,354s Summerview RTU/SCADA | 2019-08-20 14:20 | 2019-08-20 14:45 | N | N | wind control center firewall update | Terminal Equipment |  |  | Affects Visibility
AESO-SC | OATI | 2019-08-20 18:00 | 2019-08-20 19:00 | N | N | perform an inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
AESO-SC | OATI | 2019-08-21 08:00 | 2019-08-21 16:00 | N | N | performing maintenance on the Bloomington data center load balancers | SCInternal |  |  | For Information Only
ALTALINK | 356s 652 (356s Milo) | 2019-08-21 08:15 | 2019-08-21 17:45 | N | Y | modifying sync check settings on SEL-352-2 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | EMS,PI | 2019-08-21 09:00 | 2019-08-21 16:00 | N | N | apply power system related changes to the EMS model and displays | SCInternal |  |  | For Information Only
ATCO | 7L44 (749s Flyingshot Lake - 845s Big Mountain) | 2019-08-21 13:00 | 2019-08-23 17:00 | N | Y | change 709PT foundation | Line |  | Change 709PT foundation | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 995L (62s Brazeau - 995AL tap) | 2019-08-22 07:00 | 2019-08-22 17:00 | N | Y | open due to double TPR outage. 9062R - 9495R radio replacement | Line |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | ENMAX 47 B138-771 (ENMAX 47) | 2019-08-22 08:00 | 2019-08-22 16:00 | N | N | HV breaker maintenance 47B138-771. SF6 gas sample | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 924L (102s Langdon - 356s Milo) | 2019-08-22 08:00 | 2019-08-22 16:00 | N | Y | emergency repair of the insulator stack at str 23 | Line |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 24.82L (ENMAX 65 - ENMAX 24),ENMAX 65 PT138-24.82 (ENMAX 65) | 2019-08-22 08:00 | 2019-08-22 18:00 | N | N | substation washing | Line, Terminal Equipment |  |  | Pre-Condition, Contingency Requires Mitigation
EPCOR | 816s P2406 (816s Petrolia) | 2019-08-22 08:00 | 2019-08-23 17:00 | N | Y | splitting the DC | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 356s 952 (356s Milo) | 2019-08-22 08:15 | 2019-08-22 17:45 | N | Y | modifying sync check settings on SEL-352-2 | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 732s 501R (732s Mitsue) | 2019-08-22 17:35 | 2019-09-24 16:00 | N | N | forced outage | Shunts | 732s 501R (732s Mitsue) | Mitsue 501 reactor has blown up. Unavailable until further notice reactor damaged beyond repair, will need to be replaced - ETR unknown at this time | Pre-Condition
EPCOR | Rossdale T4 (Rossdale),Rossdale R724 (Rossdale),Rossdale RR729 (Rossdale) | 2019-08-23 07:00 | 2019-08-23 17:00 | N | N | doble | Circuit Breaker, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
Medicine Hat | MH-16L (MH69S-2 - MH69S-16),MH69s2 MH69_224 (MH69s2 North Industrial) | 2019-08-23 08:00 | 2019-08-23 12:00 | N | N | ISOCH testing | Circuit Breaker, Line |  |  | Restricts Generation
EPCOR | 816s T1 (816s Petrolia) | 2019-08-24 07:00 | 2019-08-25 17:00 | N | Y | bushing replacement repair 1 phase | Transformer |  |  | 240 kV
ATCO | 7L228 (845s Big Mountain - 2091s Thornton) | 2019-08-24 08:00 | 2019-08-25 17:00 | N | Y | change 703PT foundation | Line |  | Change 703PT foundation | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 24.1TR (ENMAX 24),24.81L (ENMAX 31 - ENMAX 24),24.83L (74s Janet - ENMAX 24),ENMAX 24 B138_24BT3 (ENMAX 24) | 2019-08-24 08:00 | 2019-08-24 18:00 | N | Y | breaker maintenance, doble, CT repair | Line, Circuit Breaker, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 930s Syn Condenser (930s Arcenciel) | 2019-08-24 22:25 | 2019-11-28 18:00 | N | Y | forced out-of-service | Shunts | 930s Syn Condenser (930s Arcenciel) |  | Pre-Condition, For Information Only
CapitalPower | Shamrock Whitla Wind Farm | 2019-08-25 08:00 | 2019-11-30 16:00 | N | N | ISD: Sep 01, 2019 & commissioning | Unit
ATCO | 951s SVC (951s Thickwood) | 2019-08-26 07:00 | 2019-08-31 07:00 | N | Y | troubleshooting for low differential pressure alarm | Shunts |  | Siemens requested outage to perform troubleshooting for the recurring low differential pressure alarm at Thickwood. | 240 kV
EPCOR | Rossdale T2 (Rossdale) | 2019-08-26 07:00 | 2019-08-26 17:00 | N | N | bird cover install | Transformer |  |  | Over/Under Voltage, Contingency Requires Mitigation
EPCOR | 72MG16 (Meadowlark - Garneau),Meadowlark T3 (Meadowlark) | 2019-08-26 07:00 | 2019-08-30 17:00 | N | N | doble | Transformer, Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2019-08-26 08:00 | 2019-09-09 17:16 | N | N | line protection upgrade | Line |  |  | Firm Load Loss, Creates Radial Feeds
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2019-08-26 08:00 | 2019-09-03 17:30 | N | N | changing cross-arms on 7L53 | Line |  | CHANGING CROSS-ARMS ON 7L53 | Overload, Contingency Requires Mitigation
ATCO | 7L45 (845s Big Mountain - 798s Bridge Creek) | 2019-08-26 08:00 | 2019-08-27 16:00 | N | Y | Change foundation on 701PT | Line |  | Change foundation on 701PT | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ENMAX | 20.3TR (ENMAX 20) | 2019-08-26 08:00 | 2019-08-28 16:00 | N | N | relay CPU upgrade | Transformer |  |  | For Information Only
Saskpower | Sask Power S1C line | 2019-08-26 08:00 | 2019-08-30 17:00 | N | Y | removal of S1C | Line |  |  | Limits ATC
ALTALINK | 1109L (ENMAX 65 - ENMAX 25) | 2019-08-26 08:00 | 2019-08-26 18:00 | N | Y | Substation Washing. HV SW maint, doble | Line | Substation Washing. HV SW maint SW152. Doble 25PT240-1109 |  | 240 kV, Pre-Condition
ATCO | 793s 702T (A793s West Peace) | 2019-08-26 08:30 | 2019-08-30 14:00 | N | N | OLTC refurbishment | Transformer |  | 793S 702T OLTC refurbishment 701T will be carrying the Load at 793S. No impact to transmission system. | For Information Only
ALTALINK | 513S Range. Pipe Lundbreck | 2019-08-26 09:00 | 2019-08-27 15:00 | N | N | replace station service transformer | Station |  |  | For Information Only
ALTALINK | 65s T1 (65s High River),65s T2 (65s High River),434L (65s High River - 237s Foothills),753L (65s High River - 253s Blackie),65s High River 138kV Bus 1,13L/158L (65s High River - 392s Black Diamond) | 2019-08-26 09:00 | 2019-08-30 15:00 | N | Y | replace 138 kV PTs, strain insulators and 69 kV strain insulators | Transformer, Line, Bus |  | Replace 138kv PTs (65s41), 138kv strain insulators (753L and 138kv bus) and 69kv strain insulators (T1). | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 135s T2 (135s Conrad) | 2019-08-26 10:00 | 2019-08-27 14:00 | N | N | installation of cantega cover on T2 18966 and associated 25 KV bus | Transformer |  |  | For Information Only
ALTALINK | 929L (74S Janet - 287s Hazelwood) | 2019-08-26 10:15 | 2019-08-29 15:45 | N | Y | SCADA equipment upgrade | Line | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. |  | 240 kV, Pre-Condition
ALTALINK | 17s 2852 (17s Benalto),17s T3 (17s Benalto) | 2019-08-26 11:00 | 2019-08-29 17:45 | N | Y | qualitrol modification, oil leaks, maintenance, doble | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 151s C1 (151s Strathmore),151s 44 (151s Strathmore) | 2019-08-26 11:30 | 2019-08-26 16:30 | N | N | top up low gas on breaker | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 166s T2 (166s Dow Chemical Fort Saskatchewan) | 2019-08-26 12:00 | 2019-08-29 17:30 | N | N | replacement of bushings, maintenance, winding temp gauge replacement | Transformer | Replacement of 138kV and 25kV Bushings on T1. Maintenance, Winding Temp Guage replacement |  | Pre-Condition, For Information Only
ALTALINK | 275s T1 (275s Jenner) | 2019-08-26 13:45 | 2019-09-04 15:15 | N | Y | tap changer upgrades, maintain, fix leaks, doble, IDD, hydran and bird cover install | Transformer | Techs onsite to perform tap changer upgrades, maintain, fix leaks, doble, IDD, hydran and bird cover install |  | 240 kV
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2019-08-26 15:30 | 2019-08-28 10:00 | N | N | forced outage | Line |  | water main break caused the forced outage | Firm Load Loss, Creates Radial Feeds
EPCOR | Namao T3 (Namao),72CN10 (987s Clover Bar - Namao),Namao N723 (Namao),Namao N724 (Namao) | 2019-08-27 07:00 | 2019-09-05 17:00 | N | N | commissioning/energization of new TX3 | Line, Transformer, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
NextEra | 114S Ghost Pine | 2019-08-27 08:00 | 2019-09-03 18:00 | N | Y | sensor adjustments to the MET tower | Station |  |  | For Information Only
ENMAX, ALTALINK | ENMAX 25 B240-D133 (ENMAX 25),25B240-D132 (ENMAX 25),985L (ENMAX 25 - 74s Janet) | 2019-08-27 08:00 | 2019-08-27 18:00 | N | Y | substation washing | Line, Circuit Breaker |  | Substation Washing. Doble 25PT240-985. Switch maint SW134 | 240 kV, Overload, Contingency Requires Mitigation
ENMAX | 5.7TR (ENMAX 5) | 2019-08-27 08:00 | 2019-08-30 16:00 | N | N | tapchanger inspection | Transformer |  | Tapchanger inspection. Check reversing switch. Oil sampling TC, Reinhausen Network required for alternates switching | For Information Only
ALTALINK | 89s 452 (89s Ellerslie) | 2019-08-27 08:45 | 2019-08-27 10:15 | N | Y | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to 89s452 breaker from new breaker failure module. | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO | 740s 702T (740s H.R.Milner), 740s H.R.Milner 144 kV Floating Bus | 2019-08-27 09:30 | 2019-10-24 10:00 | N | N | transformer replacement and bus reconfiguration | Transformer, Bus | 740s 702T (740s H.R.Milner), 740s H.R.Milner 144 kV Floating Bus | Replace 702T, BKR 702 & BKR 501, reconfiguring 144kv Floating Bus. 740S Rebuild workplan & sequence (up to Oct 21) -Aug 20 GCC to swap 14.4 feeders from T2 to T1 -Aug 26 702/702T/501 GOI to Replace 702,702T & 501 -Aug 26 25kv bus HOP to create J1 -Aug 26 500PT1D (J1) GOI to replace 500PT1 -Oct 21 Transfer load to 702T (GCC to swap feeders) -Oct 21 703T/503 GOI to Replace 703T & 503 | Pre-Condition, For Information Only
ALTALINK | 89s 852 (89s Ellerslie) | 2019-08-27 10:16 | 2019-08-27 11:45 | N | Y | replace existing breaker fail protection relay module and breaker control module with C60 module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to 89s852 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 324s 2152 (324s Cassils) | 2019-08-27 10:30 | 2019-08-27 16:30 | N | Y | urgent top up SF6 on west phase of 324s2152 | Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 89s 1252 (89s Ellerslie) | 2019-08-27 11:46 | 2019-08-27 13:15 | N | Y | replace existing breaker fail protection relay module and breaker control module with C60 module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to 89s1252 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 89s 1952 (89s Ellerslie) | 2019-08-27 13:16 | 2019-08-27 14:45 | N | Y | replace existing breaker fail protection relay module and breaker control module with C60 module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to 89s1952 breaker from new breaker failure module. | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 2252 (89s Ellerslie) | 2019-08-27 14:46 | 2019-08-27 16:15 | N | Y | replace existing breaker fail protection relay module and breaker control module with C60 module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to 89s2252 breaker from new breaker failure module. | Pre-Condition, Contingency Requires Mitigation, 500 kV
Saskpower | Sask Power S1C line,SaskPower C1S | 2019-08-27 17:00 | 2019-08-28 18:00 | N | Y | removal of S1C | Line |  |  | Limits ATC
ALTALINK | 68s T1 (68s Willesden Green),68s 152 (68s Amoco Willesden Green) | 2019-08-28 07:45 | 2019-08-28 17:15 | N | Y | techs to remove 25kV bus RAS scheme (as per Sys Ops/AESO request) | Circuit Breaker, Transformer |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25),ENMAX 25 B240-D136 (ENMAX 25),ENMAX 25 B240-D135 (ENMAX 25) | 2019-08-28 08:00 | 2019-08-28 18:00 | N | N | substation washing and Doble 25PT240-1003 | Line, Circuit Breaker |  |  | 240 kV, Pre-Condition, For Information Only
ALTALINK | 420s T1 (420s Broadmoor) | 2019-08-28 08:00 | 2019-08-28 17:30 | N | N | temperature monitor replacement | Transformer |  |  | For Information Only
ALTALINK | 113L (20s Ghost - 33s Spray),33s 113 (33s Spray) | 2019-08-28 08:00 | 2019-08-28 13:00 | N | N | connect and commission new cables to grounding detector | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ALTALINK | 151s T1 (151s Strathmore) | 2019-08-28 08:30 | 2019-08-29 16:45 | N | N | maintain and doble VR1 | Transformer |  |  | For Information Only
ALTALINK | 89s 1552 (89s Ellerslie) | 2019-08-28 09:30 | 2019-08-28 11:30 | N | Y | replace breaker fail protection relay module and breaker control module; function trip test to 89s1552 breaker from new breaker failure module | Circuit Breaker |  |  | 240 kV, Pre-Condition
ALTALINK | 76L (115s Mt. Allan - 33s Spray),33s 76 (33s Spray) | 2019-08-28 13:00 | 2019-08-28 18:00 | N | N | urgent change of crossarm on structure #19; connect and commission new cables to grounding detector | Circuit Breaker, Line |  |  | Pre-Condition, For Information Only
ALTALINK, CapitalPower | 1148L (1018s Shamrock - 251s Whitla),251s T1 (251s Whitla) | 2019-08-29 07:30 | 2019-08-31 17:00 | N | Y | customer requested crane walk between Turbines T62 and T65 approx 2.0m below 1148L strain bus | Line, Transformer |  |  | 240 kV
ENMAX | ENMAX 26 PT138-26.83 (ENMAX 26),26.81L (ENMAX 32 - ENMAX 26),26.1 TR (ENMAX 26) | 2019-08-29 08:00 | 2019-08-29 16:00 | N | N | substation washing. check reversing switch 26.1TR | Line, Terminal Equipment, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 522AL (868s Keephills Make-Up - 522L tap),522L (522L8 - 522L tap),522L (866s Sundance Make-Up - 522AL tap) | 2019-08-29 12:00 | 2019-08-29 18:00 | N | N | Close open point on 522AL after work at 868s complete | Line |  |  | For Information Only
ENMAX | 26.2TR (ENMAX 26),26.83L (ENMAX 65 - ENMAX 26) | 2019-08-30 08:00 | 2019-08-30 16:00 | N | N | substation washing | Line, Transformer |  | Substation Washing. Check reversing switch 26.2TR. Repair hotspot on SW81 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 170L (632s Russell - 799s Coleman) | 2019-08-31 07:00 | 2019-09-01 18:00 | N | Y | urgent fire mitigation; insulator changes, damaged wire repair on structures #19, 20, 21, 22 & 30 | Line |  | Peak RC: #1-00671749 | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 740s 701T (740s H.R.Milner) | 2019-08-31 08:00 | 2019-08-31 12:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
ENMAX | ENMAX 5 | 2019-08-31 08:00 | 2019-08-31 16:00 | N | N | doble test 5PT138-Z33 | Station |  | Doble test PTs. 2.83L Distance Protection elements(21) and nuetral directional overcurrent elements (67N) disable while PT offline. Lines remain protected through differential schemes. | For Information Only
ENMAX | ENMAX 39 | 2019-09-01 08:00 | 2019-09-01 16:00 | N | N | doble 39PT138-1 | Station |  | 39s 138KV PT Doble 39PT138-1. Distance Protection elements(21) and nuetral directional overcurrent elements (67N) disable while PT offline. Lines remain protected through differential schemes. | For Information Only
ENMAX | ENMAX 65 | 2019-09-02 08:00 | 2019-09-02 18:00 | N | N | Doble test transformer station service transformer | Station |  |  | For Information Only
ALTALINK | 58L (245s Seebe - 32s Barrier) | 2019-09-03 05:00 | 2019-09-06 15:00 | N | N | urgent fire mitigation | Line |  | Urgent fire mitigation; Scope of work includes new ground rods Str #14, 15 & 16. Replace Structures #24, 25 & 32. | Pre-Condition, Overload
EPCOR | 816s T2 (816s Petrolia) | 2019-09-03 07:00 | 2019-12-12 14:26 | N | Y | tap changer & oil reclamation | Transformer | 816s T2 (816s Petrolia) | Tap changer & Oil reclamation | 240 kV, For Information Only
ATCO | 729s 701T (729s Otauwau) | 2019-09-03 07:00 | 2019-09-24 17:00 | N | N | move protection and underground cable | Transformer | 729s 701T (729s Otauwau) | Move 25kv protection from 500BS2 to 500BS1 (new) Move 25kv underground cable from 701T to 500BS1 (new) | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2019-09-03 07:00 | 2019-10-11 17:00 | N | N | termination rebuild | Line | 72CH11 (Hardisty - 987s Clover Bar) |  | Pre-Condition
ALTALINK | 880L (523s Bullshead - 321s Al Rothbauer) | 2019-09-03 07:00 | 2019-09-04 18:00 | N | N | urgent line clearance mitigation | Line | Urgent line clearance mitigation on Structures #5 & 6 |  | Firm Load Loss, Creates Radial Feeds
EPCOR | Meadowlark T2 (Meadowlark) | 2019-09-03 07:00 | 2019-09-06 17:00 | N | N | doble | Transformer |  | MDS5 LCR, Doble | Pre-Condition
EPCOR | Kennedale T2 (Kennedale) | 2019-09-03 07:00 | 2019-09-04 17:00 | N | N | doble | Transformer |  |  | For Information Only
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2019-09-03 07:00 | 2019-09-05 18:00 | N | Y | urgent line clearance mitigation | Line | Urgent line clearance mitigation on Structures #4 & 5 |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 9.80L (ENMAX 31 - ENMAX 9),9.1 TR (ENMAX 9) | 2019-09-03 08:00 | 2019-09-03 18:00 | N | N | substation washing | Line, Transformer |  | Fall Substation Washing. Check reversing switch 9.1TR. Corrective SW 89 @ 9 Sub - east phase does not open past 90 Degrees | Pre-Condition, Overload, Contingency Requires Mitigation
ENMAX | 22.2TR (ENMAX 22) | 2019-09-03 08:00 | 2019-09-13 16:00 | N | N | transformer maintenance and Doble test transformer and cables | Transformer |  |  | For Information Only
ALBIAN | 920s 902T (920s Jackpine) | 2019-09-03 08:00 | 2019-09-09 16:00 | N | Y | maintenance | Transformer |  | OLTC & Transformer Preventive Maintenance | 240 kV, For Information Only
ENMAX | 24.1TR (ENMAX 24) | 2019-09-03 08:00 | 2019-09-04 16:00 | N | N | tapchanger inspection, check reversing switch, oil sampling MT | Transformer |  | Tapchanger inspection. Check reversing switch. Oil sampling MT, TC. Outage Required - 24.1TR XO ground cable corrective | For Information Only
ALTALINK | 89s 852 (89s Ellerslie) | 2019-09-03 08:30 | 2019-09-10 17:30 | N | Y | replace breaker fail protection relay module and breaker control module | Circuit Breaker | Replace existing breaker fail protection relay module and breaker control module with C60 module. |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 65s T2 (65s High River) | 2019-09-03 09:00 | 2019-09-04 12:00 | N | N | replace insulators | Transformer |  | Replace 25kv strain insulators on North bus, 37L and 14L. | For Information Only
ALTALINK | 115s T2 (115s Mt.Allan) | 2019-09-03 09:00 | 2019-09-05 09:00 | N | N | preparation for Project P2023:install piles for new 138kv breaker (252). | Transformer | P2023 |  | For Information Only
AESO | 551BL (551BL1 - 551BCL Tap) | 2019-09-03 09:30 | 2019-10-01 10:30 | N | N | install temporary gen | Line | 551BL (551BL1 - 551BCL Tap) | Installing temporary gen. set to supply Fortis load in preparation for outage on 551L under SAP #264390 | For Information Only
ALTALINK | 866S Sundance Make-Up | 2019-09-03 09:30 | 2019-09-11 07:00 | N | N | upgrade metering | Station |  | Upgrade Metering. Short outage to 522L & 868s to allow opening/closing of 866s1 (heavy and awkward) during swithcing to isolate/switching to restore. | Pre-Condition, For Information Only
ATCO | 947s 701T (947s Weasel Creek) | 2019-09-03 09:30 | 2019-09-05 16:00 | N | N | install bird guards | Transformer |  | Isolate 701T and 5kV bus and install bird guards | For Information Only
ALTALINK | 74s C2 (74s Janet) | 2019-09-03 10:30 | 2019-09-06 15:30 | N | N | SCADA equipment upgrade | Shunts |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | Pre-Condition
ALTALINK | 68s T2 (68s Willesden Green) | 2019-09-03 12:15 | 2019-09-12 13:00 | N | Y | CS mitigation | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 784L (332s Ellis - 784AL tap) | 2019-09-03 13:00 | 2019-09-05 12:00 | N | N | removing temporary bypass and closing Open points 'C' & 'D' | Line |  | Removing temporary bypass and closing Open points 'C' & 'D' | Pre-Condition
ALTALINK | 551CL1 (945s Sunshine - 551CL1 Tap) | 2019-09-03 13:30 | 2019-10-01 14:30 | N | N | install temporary gen | Line | 551CL1 (945s Sunshine - 551CL1 Tap) | - Installing temporary gen. set to supply Fortis load in preparation for outage on 551L under SAP #264390 | For Information Only
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-09-04 | 2019-09-05 06:00 | N | N | maintenance and testing | Switch |  | BH1 generator brushgear & leakage test outage | Restricts Generation
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-09-04 06:00 | 2019-09-05 06:00 | N | N | maintenance and testing | Switch |  | BH1 generator brushgear & leakage test outage | Restricts Generation
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2019-09-04 07:00 | 2019-09-05 18:00 | N | Y | urgent fire mitigation, insulator changes, bird perch diverters and damaged wire repair | Line | Peak RC : #1-00671864 | Urgent fire mitigation; Insulator changes, bird perch diverters and damaged wire repair on Structures #19, 20, 21, 22 & 30 | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 12.2TR (ENMAX 12),833L (ENMAX 2 - ENMAX 12) | 2019-09-04 08:00 | 2019-09-04 13:00 | N | N | substation washing, check reversing switch 12.2TR | Line, Transformer |  | Substation Washing. Check reversing switch 12.2TR | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
Saskpower | Sask Power A1P | 2019-09-04 08:00 | 2019-09-04 23:00 | N | Y | removal of A1P | Line |  |  | Limits ATC
ALTALINK | 310p 1852 (310p Sundance) | 2019-09-04 08:30 | 2019-09-04 16:30 | N | Y | close dashpots leaking | Circuit Breaker |  |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation
BCH | Selkirk 5CB4 | 2019-09-04 09:00 | 2019-09-04 17:00 | N | Y | BC protection work | Circuit Breaker | Peak RC COS outage ID: 1-00669910 Peak RC Path Derate ID: 1-00671588 (E>W), 1-00671591 (W>E) |  | Limits ATC, 500 kV
ATCO | 771s 701T (771s Veteran) | 2019-09-04 09:00 | 2019-09-13 16:00 | N | N | replace PLC with cooper station controller | Transformer |  | Replace PLC with Cooper Station Controller, Offload Substation and back feed station service. | For Information Only
ALTALINK, CapitalPower | 1148L (1018s Shamrock - 251s Whitla),1018s T1 (1018s Shamrock) | 2019-09-04 12:00 | 2019-09-06 16:30 | N | Y | CT circuit cut over to Vestas VOB and PPC panels | Line, Transformer |  |  | 240 kV
ENMAX, ALTALINK | 12.1TR (ENMAX 12),832L (ENMAX 10 - ENMAX 12) | 2019-09-04 13:00 | 2019-09-04 18:00 | N | Y | substation washing | Line, Transformer |  |  | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 275s T1 (275s Jenner) | 2019-09-04 13:45 | 2019-09-04 17:15 | N | Y | clean hot 25 kV switch 275s62 | Transformer |  |  | 240 kV, For Information Only
EPCOR | Kennedale T1 (Kennedale) | 2019-09-04 17:00 | 2019-09-07 18:00 | N | N | forced outage | Transformer |  |  | For Information Only
ATCO, ALTALINK | 395s T1 (395s North Holden),174L (197s Bardo - 395s North Holden),7L77 (395s North Holden - 709s Vegreville),701L (395s North Holden - 223s Strome),395s North Holden 138 kV Bus | 2019-09-04 22:00 | 2019-09-05 06:00 | N | Y | bus insulators to be replaced & T1 doble/maintenance | Line, Transformer, Bus |  | 138kV bus insulators to be replaced, T1(TX18243) doble/maintenance | Pre-Condition, Overload, Contingency Requires Mitigation
ALTALINK | 551L (945s Sunshine - 551L238) | 2019-09-05 04:00 | 2019-10-01 | N | N | rebuild | Line | 551L (945s Sunshine - 551L238) |  | Pre-Condition, For Information Only
ALTALINK | 704L (51s Wainwright - 478s Tuccuman) | 2019-09-05 07:00 | 2019-09-10 14:15 | N | N | structure replacement work on 704L from structures #260 - 267 | Line |  |  | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ALTALINK | 102s SVC (102s Langdon) | 2019-09-05 07:30 | 2019-09-05 17:30 | N | Y | pull weeds in the SVC fenced area | Shunts |  |  | 240 kV
ENMAX | 6.4TR (ENMAX 6),6.80L (ENMAX 35 - ENMAX 6) | 2019-09-05 08:00 | 2019-09-05 13:00 | N | N | substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 26.1TR (ENMAX 26),26.81L (ENMAX 32 - ENMAX 26) | 2019-09-05 08:00 | 2019-09-05 16:00 | N | N | breaker maintenance | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 33s 1 (33s Spray) | 2019-09-05 08:00 | 2019-09-05 17:30 | N | Y | urgent repair; 138kV breaker maintenance | Circuit Breaker |  |  | Restricts Generation
ALTALINK | 727L (65s High River - 727L52S) | 2019-09-05 09:00 | 2019-09-05 14:00 | N | N | replace 138 kV strain insulators | Line |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ALTALINK | 163s C2 (163s Amoco Empress),163s 67 (163s Amoco Empress) | 2019-09-05 10:30 | 2019-09-05 17:00 | N | N | urgent investigating/ troubleshootin | Circuit Breaker, Shunts |  |  | For Information Only
ENMAX | 6.1TR (ENMAX 6),6.82L (ENMAX 6 - ENMAX 41) | 2019-09-05 13:00 | 2019-09-05 18:00 | N | N | substation washing, check reversing switch, oil sampling | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 115s T1 (115s Mt.Allan) | 2019-09-05 15:00 | 2019-10-29 08:00 | N | N | T1 replacement, install piles for new 138 kV breaker | Transformer | P2023, 115s T1 (115s Mt.Allan) | In preparation for the FortisAlberta Kananaskis Area Reliability Project:T1 Replacement,Install piles for new 138kv breaker (152),Salvage existing T1 (TX 2701),Salvage grounding switch 115s2,Install new T1 and Install new 138kv breaker (152). | Pre-Condition
CMH, Medicine Hat | MH69s3 MH69_308 (MH69s3 South Ridge),MH69s5 MH69_502 (MH69s5 NE Crescent Height),MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights) | 2019-09-06 07:00 | 2019-09-14 19:00 | N | N | replace poles and framing in difficult access area of line | Line, Circuit Breaker |  |  | Firm Load Loss, Creates Radial Feeds
ALTALINK | 581S Amocoricinus | 2019-09-06 08:00 | 2019-09-11 15:00 | N | N | replace 138kV and 25kV lightning arrestors on T1 & 25kV, replace 25kV bus PTs and CTs | Station |  |  | For Information Only
ENMAX | ENMAX 65 B138-D83 (ENMAX 65) | 2019-09-06 08:00 | 2019-09-06 16:00 | N | N | SF6 gas sample | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 868s T1 (868s Keephills Make-Up) | 2019-09-06 08:30 | 2019-09-06 16:30 | N | N | urgent repair of phasing for TransAlta | Transformer
EPCOR | 987s T1 (987s Clover Bar),987s C2403 (987s Clover Bar),987s C2401 (987s Clover Bar),987s CCP7214 (987s Clover Bar),987s CCP7213 (987s Clover Bar) | 2019-09-06 09:00 | 2019-09-06 10:00 | N | Y | restore CCP7214 new breaker | Transformer, Circuit Breaker |  |  | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAX | 22.81L (ENMAX 22 - ENMAX 39) | 2019-09-07 08:00 | 2019-09-07 16:00 | N | N | SF6 gas sample 39B138-22.81 | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
BCH | 5L71 (Mica Creek - Nicola) | 2019-09-07 09:00 | 2019-10-06 08:38 | N | Y | MCA switchgear roof replacement project. BC Maintenance does not affect the Alberta ATC | Line | Peak COS ID: 1-00667852 AB Peak RC COS# : 1-00677163 (W>E), 1-00677165 (E>W) , 5L71 (Mica Creek - Nicola) | MCA Switchgear Roof Replacement project& | For Information Only, 500 kV
ENMAX | 31.2TR (ENMAX 31),31.3TR (ENMAX 31),24.81L (ENMAX 31 - ENMAX 24),31.84L (ENMAX 31 - ENMAX 32) | 2019-09-08 08:00 | 2019-09-08 13:00 | N | N | fall substation washing, check reversing switch | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 31.1C (ENMAX 31),31.1TR (ENMAX 31),31.2TR (ENMAX 31),9.80L (ENMAX 31 - ENMAX 9) | 2019-09-08 13:00 | 2019-09-08 18:00 | N | N | fall substation washing | Line, Transformer, Shunts |  |  | Pre-Condition
SUNCOR | 30EDD-1 | 2019-09-09 04:00 | 2019-09-22 18:00 | N | N | 5 yr PM on downstream assets. | Station | 30EDD-1 |  | For Information Only
EPCOR | Woodcroft T2 (Woodcroft), Woodcroft W725 (Woodcroft), Woodcroft W723 (Woodcroft), 72NW15 (Namao - Woodcroft) | 2019-09-09 07:00 | 2019-09-11 16:00 | N | N | disconnect replacement | Transformer, Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
EPCOR | Rossdale T1 (Rossdale) | 2019-09-09 07:00 | 2019-09-13 17:00 | N | N | doble | Transformer |  |  | Pre-Condition, For Information Only
EPCOR | 72VN21 (Namao - 511s Victoria) | 2019-09-09 07:00 | 2019-10-18 17:00 | N | N | maintenance | Line | 72VN21 (Namao - 511s Victoria) | Norwood cable reroute | Firm Load Loss, Creates Radial Feeds
ALTALINK | 205s T1 (205s Castle Rock Ridge),205s13 (205s Castle Rock Ridge) | 2019-09-09 07:00 | 2019-09-19 16:30 | N | Y | maintenance | Switch, Transformer |  | Maintenance and construction by customer | Restricts Generation
ALTALINK | 444L (198s Blackfalds - 217s North Red Deer) | 2019-09-09 07:00 | 2019-09-15 18:00 | N | N | clearance mitigation work | Line |  |  | Restricts Generation, Firm Load Loss, Creates Radial Feeds
MONTANA | 120s 1352 (120s Picture Butte),120s 1052 (120s Picture Butte),120s 1152 (120s Picture Butte),120s 1252 (120s Picture Butte) | 2019-09-09 08:00 | 2019-09-19 18:00 | N | Y | annual shutdown for routine maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2019-09-09 08:00 | 2019-09-13 12:00 | N | Y | repair pinhole SF6 leak | Line |  | 23B138-23.80 Repair pinhole SF6 Leak. (Sub washing Sept 13th am) | Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO | 834s 901T (834s Wesley Creek) | 2019-09-09 08:30 | 2019-09-13 14:00 | N | Y | refurbishment | Transformer |  | 834S 901T OLTC Refurbishment 902T will be carrying the full substation load | Pre-Condition, Restricts Generation, Contingency Requires Mitigation
ATCO | 6L05 (764s Heisler - 6L05 tap) | 2019-09-09 09:00 | 2019-09-11 12:00 | N | N | pole changes | Line |  | Pole changes | Firm Load Loss, Creates Radial Feeds
ALTALINK, MONTANA | 1201L (520s Bennett - BCH Cranbrook), MATL (120s Picture Butte - Montana) | 2019-09-09 09:00 | 2019-09-19 18:00 | Y | Y | component replacements | Line |  | 1201L: Peak RC COS outage ID: 1-00646151 Peak RC Path Derate ID: 1-00646152 (E>W), 1-00646153 (W>E) MATL: PEAK COS outage ID: 1-00646151 PEAK COS path de-rate ID:1-00646154 (N-S) :1-00646155 (S-N) | 240 kV, Limits ATC, 500 kV
ALTALINK | 901AL (64s East Crossfield - 901L tap), 64s T2 (64s East Crossfield), 64s 901 (64s East Crossfield) | 2019-09-09 10:15 | 2019-09-19 18:30 | N | Y | replace bushings, fix leaks, doble, maintenance | Line, Transformer, Circuit Breaker | Replace 240/138kV Bushings, fix leaks, doble, maintain. |  | 240 kV, Pre-Condition, Overload, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 359s T1 (359s Esso West Pembina) | 2019-09-09 11:30 | 2019-09-12 07:00 | N | N | transformer maintenance | Transformer |  |  | For Information Only
ALTALINK | 520s T1 (520s Bennett) | 2019-09-09 12:00 | 2019-09-12 16:00 | N | Y | change 240/500kV bus work | Transformer | Change 240/500kv bus work(close Open Points) in order to energize Tx18414. Tx18415 to become the spare.In conjunction with 1201L/5L94 outage Ref# 26411. |  | For Information Only, 500 kV
ALTALINK | 283s C1 (283s Violet Grove),283s 31 (283s Violet Grove) | 2019-09-09 12:30 | 2019-09-12 18:00 | N | N | replace CTs | Circuit Breaker, Shunts | Replace 138kV CTs at 283s31 |  | For Information Only
EPCOR | 987s CC13 (987s Clover Bar), 987s CK725 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale), 987s CCP7213 (987s Clover Bar), 987s CGB2 (987s Clover Bar), 987S Clover Bar 72 kV Bus 3 | 2019-09-10 02:00 | 2019-09-13 16:00 | N | Y | disconnect aux contacts and doble | Circuit Breaker, Line, Bus |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2019-09-10 07:00 | 2019-09-10 13:00 | N | Y | urgent fire mitigation - replace OHSW assembly on structure 250 | Line |  | Urgent Fire Mitigation - Scope of work includes replace OHSW assembly on Structure 250 | 240 kV, Pre-Condition, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 216s T1 (216s Knightsbridge),216s T2 (216s Knightsbridge) | 2019-09-10 07:00 | 2019-09-10 18:00 | N | N | NGR and electrical equipment maintenance | Transformer |  | NGR and electrical equipment maintenance - Enbridge | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale), 987s CK725 (987s Clover Bar), Kennedale K724 (Kennedale) | 2019-09-10 07:00 | 2019-09-11 16:00 | N | N | disconnect aux contacts and doble | Line, Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ATCO, ALTALINK | 7L129 (526s Buffalo Creek - 710s Vermilion),526s 152 (526s Buffalo Creek) | 2019-09-10 07:30 | 2019-09-10 12:00 | N | Y | tank heater repair | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 89s 452 (89s Ellerslie) | 2019-09-10 08:45 | 2019-09-10 10:15 | N | Y | replace existing breaker fail protection relay and breaker control modules with C60 module and functional testing | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s452 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ENMAXEC | 383s Kettles Hill Windfarm RTU/SCADA | 2019-09-10 10:15 | 2019-09-10 12:45 | N | N | updates to a network router | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 89s 1252 (89s Ellerslie) | 2019-09-10 10:16 | 2019-09-10 11:45 | N | Y | replace existing breaker fail protection relay and breaker control modules with C60 module and functional testing | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s1252 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 89s 1652 (89s Ellerslie) | 2019-09-10 11:46 | 2019-09-10 13:15 | N | Y | replace existing breaker fail protection relay and breaker control modules with C60 module and functional testing | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s1652 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ATCO, ALTALINK | 526s 252 (526s Buffalo Creek),7L50 (757s Battle River - 526s Buffalo Creek) | 2019-09-10 12:01 | 2019-09-10 17:30 | N | Y | tank heater repair | Line, Circuit Breaker |  |  | Pre-Condition, Overload, Over/Under Voltage, Contingency Requires Mitigation
ALTALINK | 89s 1952 (89s Ellerslie) | 2019-09-10 13:16 | 2019-09-10 14:45 | N | Y | replace existing breaker fail protection relay and breaker control modules with C60 module and functional testing | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to 89s1952 breaker from new breaker failure module. | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 2252 (89s Ellerslie) | 2019-09-10 14:46 | 2019-09-10 16:15 | N | Y | replace existing breaker fail protection relay and breaker control modules with C60 module and functional testing | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s2252 breaker from new breaker failure module. | Pre-Condition, Contingency Requires Mitigation, 500 kV
ALTALINK | 89s 752 (89s Ellerslie) | 2019-09-10 17:30 | 2019-09-11 08:00 | N | Y | replace existing breaker fail protection relay module and breaker control module with C60 module | Circuit Breaker |  | Replace existing breaker fail protection relay module and breaker control module with C60 module. Function trip test to89s752 breaker from new breaker failure module. | 240 kV, Pre-Condition, Contingency Requires Mitigation
ALTALINK | 740L (58s Edson - 39s Bickerdike) | 2019-09-11 07:00 | 2019-09-12 17:00 | N | N | urgent fire mitigation on structures 1A, 3, 8, 9, 10, 15, 17, 19, 25 and 34 | Line |  | Urgent Fire Mitigation Work on Structures 1A, 3, 8, 9, 10, 15, 17, 19, 25 and 34. Scope includes, grounding repairs, insulator replacements and structure straightening. | For Information Only
ALTALINK | 13L/158L (65s High River - 392s Black Diamond) | 2019-09-11 07:00 | 2019-09-11 12:00 | N | N | high load move between structures 24 and 25 | Line |  | High load move between Structures #24 & 25 | Firm Load Loss, Creates Radial Feeds
CNRL | 1034s T1 (1034s Margie),1034s CB1 (1034s Margie) | 2019-09-11 08:00 | 2019-09-12 17:00 | N | N | replacing ss transformer and installing isolation disconnect | Transformer, Circuit Breaker | Replacement of station service transformer (112-SUB-SST1) and installation of isolation disconnect for the station service transformer |  | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2019-09-11 08:00 | 2019-09-11 16:00 | N | N | corrective | Transformer |  | Corrective. 15.1TR Las Ground Cable Upgrade | For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32),32.3TR (ENMAX 32) | 2019-09-11 08:00 | 2019-09-11 12:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition, For Information Only
ALTALINK | 445s T1 (445s Elk River) | 2019-09-11 09:00 | 2019-10-16 09:00 | N | N | replace 445s T1 to new TX18964, & replace LA's. | Transformer | 445s T1 (445s Elk River) |  | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel) | 2019-09-11 10:00 | 2019-09-11 14:00 | N | Y | emergency sync condenser troubleshoot | Shunts |  |  | Pre-Condition
ATCO | 851s 701T (851s Morse River) | 2019-09-11 10:00 | 2019-09-12 12:00 | N | N | repair leaks | Transformer |  | Repair Leaks - Oil is to be drained and bushing gaskets to be replaced. All Substation load to be transferred to other locations through the distribution system. Substation station service to stay on by back feeding through a feeder breaker. | For Information Only
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2019-09-11 11:00 | 2019-09-11 18:00 | N | N | high load move between structures #198 & 199 | Line |  |  | Pre-Condition, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ENMAX | 32.1TR (ENMAX 32),32.2TR (ENMAX 32),32.83L (ENMAX 32 - ENMAX 40),26.81L (ENMAX 32 - ENMAX 26) | 2019-09-11 12:00 | 2019-09-11 18:00 | N | N | fall substation washing | Transformer, Line |  | Fall Substation Washing. Wash structure #1 26.81L. Check reversing switch 32.1TR | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7LA24 (940s Beartrap - 7LA24D1) | 2019-09-11 13:00 | 2019-09-11 15:00 | N | N | emergency insulator replacement | Line |  | Insulator replacement  missing insulators found during patrols | For Information Only
ATCO | 6L03 (6L17 tap - 757s Battle River) | 2019-09-11 13:00 | 2019-09-11 16:00 | N | N | emergency repair insulator tipped over due to cross arm failure | Line |  |  | For Information Only
Medicine Hat | MH69s1 MH69_38 (MH69s1 Power P Switchyard) | 2019-09-11 16:00 | 2020-05-28 17:00 | N | N | replace breaker | Circuit Breaker | MH69s1 MH69_38 (MH69s1 Power P Switchyard) | Step 1 - MH69-35 and MH69-36 opened to connect MH69-38 to MH69-37 Step 2  commission and test Step 3  MH69-40 and MH69-41 opened to connect MH69-38 to MH69-39 Step 4 - commission and test Step 5  return to service | For Information Only
ALTALINK | 359S Esso West Pembina | 2019-09-12 07:00 | 2019-09-12 19:00 | N | N | maintenance | Station |  | Switchgear maintenance, requires entire station due to arc flash concerns. | For Information Only
ALTALINK | 396s T1 (396s Pincher Creek) | 2019-09-12 07:45 | 2019-09-12 17:15 | N | N | techs will be on site for TX temp monitor replacement. | Transformer |  |  | Pre-Condition, Over/Under Voltage, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),33.1TR (ENMAX 33) | 2019-09-12 08:00 | 2019-09-12 12:00 | N | N | substation washing | Line, Transformer |  | Fall Substation Washing. Check reversing switch 33.1TR | Firm Load Loss, Creates Radial Feeds
ALTALINK | 283s C1 (283s Violet Grove),283s T1 (283s Violet Grove),673L (283s Violet Grove - 131s Moon Lake),836L (61s Lodgepole - 283s Violet Grove),283s 836W (283s Violet Grove),283s 673 (283s Violet Grove),283s 5 (283s Violet Grove) | 2019-09-12 11:00 | 2019-09-12 14:00 | N | Y | energize the cap bank | Circuit Breaker, Transformer, Shunts, Switch, Line |  | To energize the cap bank new CT15 | Pre-Condition, Overload, Firm Load Loss, Creates Radial Feeds
ENMAX | 33.2TR (ENMAX 33),33.84L (ENMAX 43 - ENMAX 33) | 2019-09-12 12:00 | 2019-09-12 18:00 | N | N | substation washing | Line, Transformer |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 501L (426s Coalspur - 501CL tap),740L (426s Coalspur - 740L tap),743L (527s Coal Valley - 743L1A),762L (101s Cheviot - 762L2) | 2019-09-13 07:00 | 2019-09-13 18:00 | N | N | urgent fire mitigation | Line
ALTALINK | 359S Esso West Pembina,202AL (359s Esso West Pembina - 202L tap),202L (178s Cynthia - 202AL tap) | 2019-09-13 07:00 | 2019-09-13 19:00 | N | N | 138 kV switch maintenance at 359s | Line, Station |  |  | Pre-Condition
ALTALINK, ATCO | 409s Shell Scotford 138 kV Bus 2, 409s T1 (409s Shell Scotford), 409s T3 (409s Shell Scotford), 857L (409s Shell Scotford - 410s Josephburg), ALC02L (409s Shell Scotford - 879s Scotford Upgrader) | 2019-09-13 07:00 | 2019-09-20 18:00 | N | Y | bushing & insulator replacement, breaker maintenance,wildlife cover, protection upgrade, NGR maintenance | Bus, Transformer, Line |  |  | Firm Load Loss, Creates Radial Feeds
ENMAX | 33.83L (ENMAX 41 - ENMAX 33),ENMAX 33 B138-33.83 (ENMAX 33) | 2019-09-13 08:00 | 2019-09-13 16:00 | N | N | HV breaker maintenance 33B138-33.83 | Line, Circuit Breaker |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX, ALTALINK | 23.4TR (ENMAX 23),23.80L (74s Janet - ENMAX 23) | 2019-09-13 08:00 | 2019-09-13 12:00 | N | N | fall substation washing, check reversing switch | Line, Transformer
ENMAX | 23.3TR (ENMAX 23),2.80L (ENMAX 2 - ENMAX 23) | 2019-09-13 12:00 | 2019-09-13 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Pre-Condition
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2019-09-14 00:01 | 2019-09-14 05:00 | N | N | relocate an anchor off of a distribution pole | Line |  |  | Pre-Condition
ALTALINK | 359S Esso West Pembina, 202AL (359s Esso West Pembina - 202L tap) | 2019-09-14 07:00 | 2019-09-14 19:00 | N | N | switchgear maintenance | Station, Line |  | Switchgear maintenance, requires entire station due to arc flash concerns. | For Information Only
ALTALINK | 847L (602s Cold Creek - 847AL Tap) | 2019-09-14 07:00 | 2019-09-14 15:00 | N | N | urgent fire mitigation - STR 286, STR 305 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 359s T2 (359s Esso West Pembina) | 2019-09-14 18:30 | 2019-09-17 17:30 | N | N | transformer maintenance | Transformer |  |  | For Information Only
CMH, Medicine Hat | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview), MH69s2 MH69_202 (MH69s2 North Industrial), MH69s6 MH69_602 (MH69s6 Riverview) | 2019-09-15 07:00 | 2019-11-04 19:00 | N | N | completion of MH-10L 138 kV upgrade project | Line, Circuit Breaker | MH69_10L (MH69s2 North Industrial - MH69s6 Riverview), MH69s2 MH69_202 (MH69s2 North Industrial), MH69s6 MH69_602 (MH69s6 Riverview) | Completion of MH-10L 138 kV Upgrade Project | For Information Only
ENMAX | 5.6TR (ENMAX 5), 1.82L (ENMAX 1 - ENMAX 5), 5.1TR (ENMAX 5), 5.8TR (ENMAX 5) | 2019-09-15 08:00 | 2019-09-15 13:00 | N | N | fall substation washing | Transformer, Line |  | Fall Substation Washing. Check reversing switch 5.1TR, 5.8TR. Oilsampling 5.8TC | Pre-Condition
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13), 5.9TR (ENMAX 5), 5.10TR (ENMAX 5) | 2019-09-15 13:00 | 2019-09-15 18:00 | N | N | fall substation washing | Line, Transformer |  | Fall Substation Washing. Check reversing switch 5.9TR, 5.10TR | Pre-Condition
NOVACORP | 330s 330-PTR-01 (330s Nova Corp), 330s 330-PTR-03 (330s Nova Corp), 330s Nova Corp 138kV Bus 1B | 2019-09-15 14:00 | 2019-09-20 14:00 | N | Y | maintenance | Transformer, Bus |  |  | Restricts Generation
ALTALINK | 38s 737N (38s East Edmonton) | 2019-09-16 07:00 | 2019-09-19 18:00 | N | N | breaker replacement | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s452 (29EDD-1 Millennium) | 2019-09-16 08:00 | 2019-09-20 18:00 | N | Y | replace Phase C pole on breaker 29EDD1S452 | Circuit Breaker |  | replace Phase C pole on breaker 29EDD1S452 | 240 kV
ENMAX | 54.1TR (ENMAX 54) | 2019-09-16 08:00 | 2019-09-19 16:00 | N | N | doble test, secondary cable tests, maintenance and gas relay testing | Transformer |  | Doble test transformer. Transformer Secondary Cable Tests. Transformer maintenance. Gas relay testing | For Information Only
ATCO | 850s 702T (850s Rainbow Cogen), 4L228 (850s Rainbow Cogen - 791s Rainbow Lake) | 2019-09-16 08:00 | 2019-09-19 16:00 | N | Y | maintenance | Transformer, Line |  | 791S RB5 outage for 702T and 13.8kv bus Maintenance @ 850S - to be coordinated with ATCO Power | Restricts Generation
ALTALINK, Lethbridge | 824L (593s Lethbridge Lakeview - 618s Riverbend) | 2019-09-16 08:00 | 2019-09-20 17:00 | N | Y | replace 593S4 motorized A/B | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 16.63L (ENMAX 16 - ENMAX 36), 36.2TR (ENMAX 36) | 2019-09-16 08:00 | 2019-09-16 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2019-09-16 08:00 | 2019-09-19 16:00 | N | N | crossarm change | Line |  | Crossarm Change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 739s 702 (739s Edith Lake) | 2019-09-16 08:00 | 2019-09-18 09:00 | N | N | wire in a couple new statuses | Circuit Breaker |  | The scope of work is A GOI to wire in a couple new statuses from BKR 702 into ION7550/701T and ION7550/702T. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 826s 701 (826s Marguerite Lake) | 2019-09-16 09:00 | 2019-09-18 14:30 | N | N | reclaim and leak repair | Circuit Breaker |  | 826S 701 BREAKER SF6 HPL Reclaim and leak repair Replace O-ring on top of Center Phase unit 144KV loop will be broken at Marguerite. As well 7L89 will be fed by only 702 breaker for duration. | Contingency Requires Mitigation
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2019-09-16 10:00 | 2019-09-19 16:00 | N | N | cross arms maintenance | Line |  | Change out fiberglass cross arms | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s T1 (74s Janet), 74s Janet 240kV Bus 1 | 2019-09-16 10:00 | 2019-09-22 12:00 | N | Y | upgrade SCADA equipment | Transformer, Bus | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. Replace 74s25N switch., 74s Janet 240kV Bus 1, 74s T1 (74s Janet) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 895s T2 (895s Suffield) | 2019-09-16 11:00 | 2019-09-23 09:00 | N | N | VR1 replacement | Transformer | 895s T2 (895s Suffield) | Complete replacement of VR1 with three new single phase regulators. | For Information Only
ALTALINK | 545s T1 (545s Provost) | 2019-09-16 11:00 | 2019-09-24 17:00 | N | N | connect new SWGB | Transformer | 545s T1 (545s Provost) | Outage to Connect new SWGB and close Open Point 'E' | For Information Only
ALTALINK | 737L (95s Imperial Oil Edmonton - 38s East Edmonton), 865L (216s Knightsbridge - 38s East Edmonton), 736L (38s East Edmonton - 293s Bernese), 38s East Edmonton 138 kV Bus 1, 38s 62 (38s East Edmonton), 38s T1 (38s East Edmonton), 38s C1 (38s East Edmonton), 38s C2 (38s East Edmonton) | 2019-09-16 12:00 | 2019-09-16 18:00 | N | Y | various switch & hot spot repairs | Line, Bus, Circuit Breaker, Transformer, Shunts |  | Various Switch & Hot Spot Repairs | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 447s T1 (447s Enchant) | 2019-09-16 12:00 | 2019-09-17 16:30 | N | N | doble | Transformer |  |  | For Information Only
NOVAC, NOVACORP | 330L2 (535s Joffre - I-330s Nova Corp Plant), 330s BR_50 (330s Nova Corp) | 2019-09-16 12:00 | 2019-09-20 10:00 | N | Y | maintenance | Line, Circuit Breaker |  |  | Restricts Generation
ALTALINK | 244s 152 (244s Bowmanton) | 2019-09-16 12:30 | 2019-09-17 17:00 | N | Y | Repair gas leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage
ATCO | 813s 501R (813s Little Smoky), 813s 901T (813s Little Smoky) | 2019-09-16 13:00 | 2019-09-22 10:00 | N | Y | tap changer refurbishment | Shunts, Transformer | 20190905-May require NPP1 TMR for overload and voltage n-1 on 813s902T., 813s 501R (813s Little Smoky), 813s 901T (813s Little Smoky) | Tap Changer refurbishment, transformer out of service | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 359S Esso West Pembina | 2019-09-17 07:00 | 2019-09-19 19:00 | N | N | switchgear maintenance | Station |  | Switchgear maintenance, requires entire station due to arc flash concerns. | For Information Only
STROBE | 240S McBride Lake | 2019-09-17 07:00 | 2019-09-18 18:00 | N | N | maintenance | Station |  |  | Restricts Generation
ALTALINK | 317s T2 (317s Baseline) | 2019-09-17 07:30 | 2019-09-17 16:30 | N | N | upgrade metering on T2 | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 28.2TR (ENMAX 28), 28.80L (42s Sarcee - ENMAX 28), 42s 28 (42s Sarcee) | 2019-09-17 08:00 | 2019-09-17 12:00 | N | Y | fall substation washing | Transformer, Line, Circuit Breaker |  | fall substation washing, check reversing switch 28.2TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 718s 701T (718s Parsons Creek) | 2019-09-17 08:00 | 2019-09-24 16:00 | N | N | leak repairs | Transformer | 718s 701T (718s Parsons Creek) |  | For Information Only
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 89s 352 (89s Ellerslie), 89s 452 (89s Ellerslie) | 2019-09-17 08:00 | 2019-09-17 18:00 | N | Y | replace 1057L strain insulators at 89s Ellerslie | Line, Circuit Breaker |  | Replace 1057L Strain Insulators at 89s Ellerslie | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 54s Fort Saskatchewan 138 kV West Bus, 694L (54s Fort Saskatchewan - 422s Westwood), 706L (54s Fort Saskatchewan - 706L72B), 54s C1 (54s Fort Saskatchewan), 54s T1 (54s Fort Saskatchewan) | 2019-09-17 10:00 | 2019-09-20 18:00 | N | N | install and commission additional protection on 138 kV west bus, install slip on bushing CTs on T1 | Bus, Line, Shunts, Transformer |  | Install and commission additional 138kV bus protection on West Bus, install slip on bushing CTs on T1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 77s Sagitawah 138 kV East Bus, 825L (484s Millar Western - 77s Sagitawah), 77s T2 (77s Sagitawah), 77s 552 (77s Sagitawah), 77s 652 (77s Sagitawah), 77s 752 (77s Sagitawah) | 2019-09-17 12:00 | 2019-09-17 18:00 | N | Y | replace dead end structures for 825L inside at both 77s and 484s | Bus, Line, Transformer, Circuit Breaker |  | Line work - 825L Replace Dead end structures inside the stations at both 77s and 484s | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 1.80L (ENMAX 28 - ENMAX 1), 28.1TR (ENMAX 28) | 2019-09-17 12:00 | 2019-09-17 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Firm Load Loss, Creates Radial Feeds
AESO-SC | OATI | 2019-09-17 18:00 | 2019-09-17 19:00 | N | N | performing maintenance on the Minneapolis data center load balancers | SCInternal |  |  | For Information Only
CENOVUS | 539s PCB_9201 (539s Sunday Creek) | 2019-09-18 07:00 | 2019-09-24 18:00 | N | Y | 5 year maintenance | Circuit Breaker | 539s PCB_9201 (539s Sunday Creek) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 95s T2 (95s Imperial Oil Edmonton) | 2019-09-18 07:30 | 2019-09-19 18:00 | N | N | transformer maintenance | Transformer |  | T2 Transformer Maintenance and Oil Leak Repairs | For Information Only
Syncrude | SCL1 Syncrude #1 | 2019-09-18 08:00 | 2019-10-02 16:00 | N | N | P2095 G4 PSS AVR upgrade. ISD Sept 25, 2019 | Unit
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station), 89s 252 (89s Ellerslie), 89s 352 (89s Ellerslie) | 2019-09-18 08:00 | 2019-09-18 18:00 | N | Y | replace 1056L strain insulators | Line, Circuit Breaker |  | Replace 1056L Strain Insulators at 89s Ellerslie | 240 kV, Contingency Requires Mitigation, Over/Under Voltage
ALTALINK | 244s 552 (244s Bowmanton) | 2019-09-18 08:00 | 2019-09-19 15:30 | N | Y | repair gas leak | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 1.81L (ENMAX 20 - ENMAX 1), 20.1TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2019-09-18 08:00 | 2019-09-18 12:00 | N | N | substation washing | Line, Transformer, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 737L (95s Imperial Oil Edmonton - 38s East Edmonton) | 2019-09-18 08:30 | 2019-09-19 17:30 | N | N | maintenance | Line |  | Brushing Borehole work on 737L. | Creates Radial Feeds, Firm Load Loss
ENMAX | 20.82L (ENMAX 21 - ENMAX 20), 20.3TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2019-09-18 12:00 | 2019-09-18 18:00 | N | N | fall substation washing | Line, Transformer, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 62s11 (62s Brazeau) | 2019-09-18 23:00 | 2019-09-19 02:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2019-09-19 02:05 | 2019-09-19 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 796s 701T (796s Nipisi), 796s 701TCS (796s Nipisi) | 2019-09-19 07:00 | 2019-09-19 17:00 | N | N | function test 50BF | Transformer, Circuit Breaker |  | Function test 50BF | For Information Only, Pre-Condition
ENMAX | 54.81L (ENMAX 54 - ENMAX 65), ENMAX 65 B138-D83 (ENMAX 65), ENMAX 65 B138-D84 (ENMAX 65) | 2019-09-19 08:00 | 2019-09-19 18:00 | N | N | substation washing | Line, Circuit Breaker |  | Substation Washing, 65PT138-54.81 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 826s 504R (826s Marguerite Lake) | 2019-09-19 08:00 | 2021-08-11 13:00 | N | N | emergency: move reactor from 826s to 732s | Shunts | 826s 504R (826s Marguerite Lake) |  | Pre-Condition
BLACKSPRING | 485s C1 (485s Blackspring), 485s DVAR1 (485s Blacksprings) | 2019-09-19 09:00 | 2019-09-19 15:00 | N | Y | maintenance | Shunts |  |  | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2019-09-19 18:00 | 2019-09-20 11:00 | N | Y | component replacements | Line |  | PEAK COS outage ID: 1-00646151 PEAK COS path de-rate ID:1-00646154 (N-S) :1-00646155 (S-N) | 240 kV, Limits ATC
EPCOR | 987s T2 (987s Clover Bar) | 2019-09-20 07:00 | 2019-09-27 16:00 | N | Y | line rebuild and upgrade | Transformer | 987s T2 (987s Clover Bar) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
CNRL | 75-TR-1701 (838s Horizon Mining) | 2019-09-20 07:30 | 2019-09-28 15:45 | N | Y | transformer OLTC and 5 year maintenance. | Transformer | 75-TR-1701 (838s Horizon Mining) |  | 240 kV
BCH | 5L92 (Cranbrook - Selkirk) | 2019-09-20 09:30 | 2019-09-20 20:30 | Y | Y | annual plan request F19 | Line |  | Peak RC COS outage ID: 1-00675483 Peak RC Path Derate ID: 1-00675733 (E>W), 1-00675734 (W>E) | Limits ATC, 500 kV
CNRL | 75-TR-7701 (842s Horizon Upgrading), 75-TR-5701 (842s Horizon Upgrading) | 2019-09-21 07:30 | 2019-10-11 18:00 | N | Y | transformer OLTC and 5 yr maintenance | Transformer | 75-TR-7701 (842s Horizon Upgrading), 75-TR-5701 (842s Horizon Upgrading) |  | 240 kV
ENMAX | 38.83L (ENMAX 39 - ENMAX 38), 39.82L (ENMAX 162 Beddington - ENMAX 39), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) | 2019-09-21 08:00 | 2019-09-21 13:00 | N | N | fall substation washing, check reversing switch 39.3TR | Line, Transformer | 38.83L (ENMAX 39 - ENMAX 38), 39.82L (ENMAX 162 Beddington - ENMAX 39), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39), 22.81L (ENMAX 22 - ENMAX 39), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) | 2019-09-21 13:00 | 2019-09-21 18:00 | N | N | fall substation washing, check reversing switch 39.4TR | Line, Transformer | 39.82L (ENMAX 162 Beddington - ENMAX 39), 22.81L (ENMAX 22 - ENMAX 39), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 84L (35s Rundle - 33s Spray) | 2019-09-22 07:00 | 2019-09-26 18:00 | N | N | Structure Replacements | Line | Structure Replacements (Str's Range #2-13), 84L (35s Rundle - 33s Spray) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 38.83L (ENMAX 39 - ENMAX 38), 38.1C (ENMAX 38), 38.1TR (ENMAX 38), 38.3TR (ENMAX 38) | 2019-09-22 08:00 | 2019-09-22 13:00 | N | N | fall substation washing, check reversing switch 38.1 | Line, Shunts, Transformer | 38.83L (ENMAX 39 - ENMAX 38), 38.1C (ENMAX 38), 38.1TR (ENMAX 38), 38.3TR (ENMAX 38) |  | Creates Radial Feeds, Firm Load Loss
BCH | 5L52 (Ingledow - Custer) | 2019-09-22 09:00 | 2019-09-22 15:00 | N | Y | BPA insulator replacement | Line | 5L52 (Ingledow - Custer)
ENMAX | 37.81L (ENMAX 38 - ENMAX 37), 38.1C (ENMAX 38), 38.2TR (ENMAX 38), 38.3TR (ENMAX 38) | 2019-09-22 13:00 | 2019-09-22 18:00 | N | N | fall substation washing, check reversing switch 38.2 | Line, Shunts, Transformer | 37.81L (ENMAX 38 - ENMAX 37), 38.1C (ENMAX 38), 38.2TR (ENMAX 38), 38.3TR (ENMAX 38) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.3TR (ENMAX 11) | 2019-09-23 02:00 | 2019-10-04 02:00 | N | N | relay replacement | Transformer | 11.3TR (ENMAX 11) |  | For Information Only
EPCOR | 805s T4 (805s Jasper) | 2019-09-23 07:00 | 2019-09-27 17:00 | N | Y | doble Testing | Transformer | 805s T4 (805s Jasper) |  | 240 kV
ALTALINK, ATCO | 409s Shell Scotford 138 kV bus B1, 856L (409s Shell Scotford - 410s Josephburg), ALC01L (409s Shell Scotford - 408s Air Liquide Scotford), 409s T2 (409s Shell Scotford) | 2019-09-23 07:00 | 2019-09-29 18:00 | N | Y | bushing replacement, insulator replacement, breaker maintenance, protection upgrade, NGR maintenance | Bus, Line, Transformer | Includes 856L and ALC01L in isolation. T2 Bushing replacement Insulator replacement (ALC01L strain), 409s20 breaker maintenance, 856L B protection upgrade, ALC01L protection upgrade, NGR maintenance  Shell, 409s Shell Scotford 138 kV bus B1, 856L (409s Shell Scotford - 410s Josephburg), ALC01L (409s Shell Scotford - 408s Air Liquide Scotford), 409s T2 (409s Shell Scotford) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 803s L2401 (803s Lambton) | 2019-09-23 07:00 | 2019-09-28 17:00 | N | Y | maintenance | Circuit Breaker | 803s L2401 (803s Lambton) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | Poundmaker T3 (Poundmaker) | 2019-09-23 07:00 | 2019-09-27 17:00 | N | Y | repair the air integrity bag | Transformer | Poundmaker T3 (Poundmaker) |  | 240 kV
ENMAX | 39.2TR (ENMAX 39) | 2019-09-23 08:00 | 2019-11-28 16:00 | N | N | testing and maintenance | Transformer | 39.2TR (ENMAX 39) | Doble test transformer. Transformer secondary cable tests. Transformer maintenance. Gas relay testing. ECI Bushings, 39.2TR (ENMAX 39) | For Information Only
ENMAX | ENMAX 15 B69-15.62 (ENMAX 15), ENMAX 16 B69-15.62 (ENMAX 16), 15.62L (ENMAX 15 - ENMAX 16) | 2019-09-23 08:00 | 2019-09-26 16:00 | N | N | breaker maintenance | Circuit Breaker, Line | HV Breaker Maintenance 15B8-15.62. 16B69-15.62. 15s 69kV bus Differential and Autoswitching protection replacement. Wiring and commissioning checks. Adjust the sag on the line, 15.62L (ENMAX 15 - ENMAX 16), ENMAX 15 B69-15.62 (ENMAX 15), ENMAX 16 B69-15.62 (ENMAX 16) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L117 (706s Irish Creek - 710s Vermilion) | 2019-09-23 08:00 | 2019-09-27 17:00 | N | N | Crossarm Change | Line | 7L117 (706s Irish Creek - 710s Vermilion) | Crossarm Change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (ENMAX 43 - ENMAX 9), 43.1TR (ENMAX 43) | 2019-09-23 08:00 | 2019-09-23 12:00 | N | N | Substation Washing | Line, Transformer | 9.83L (ENMAX 43 - ENMAX 9), 43.1TR (ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 820s 701T (820s Hangingstone), 820s 505C1 (820s Hangingstone), 820s 505C2 (820s Hangingstone) | 2019-09-23 08:00 | 2019-09-27 17:00 | N | N | install bird proofing | Transformer, Shunts | 820s 701T (820s Hangingstone), 820s 505C1 (820s Hangingstone), 820s 505C2 (820s Hangingstone) | 820S Bird Proofing - 701T Outage (Sept. 23 to 27) Install Bird Proofing at 820S Hanginigstone 701T & affected 25KV bus OOS | For Information Only
BCH | 5L51 (Ingledow - Custer) | 2019-09-23 08:00 | 2019-09-25 18:30 | N | Y | BPA celllular work & BC maintenance does not affect the Alberta ATC | Line | 5L51 (Ingledow - Custer) | Requested by BPA for PCS CELLULAR WORK. Tag on INGLEDOW 5D23 TERMINAL TO PROTECT BPA PERSONNEL | Limits ATC, 500 kV
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2019-09-23 08:00 | 2019-10-11 17:00 | N | Y | fire mitigation work on structures | Line | 777L (245s Seebe - 48s Pocaterra) | Fire mitigation work on Structures #18 - 231 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, ATCO | 347s Fox Creek 138 kV Bus, 199L (347s Fox Creek - 199L187A), 720L (347s Fox Creek - 397s Benbow), 7L199 (347s Fox Creek - 741s Fox Creek) | 2019-09-23 08:15 | 2019-09-23 14:45 | N | Y | PT work | Bus, Line | 347s Fox Creek 138 kV Bus, 199L (347s Fox Creek - 199L187A), 720L (347s Fox Creek - 397s Benbow), 7L199 (347s Fox Creek - 741s Fox Creek) | Work on PT secondary circuits affecting all line protections. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
BCH | 5L96 (Selkirk - Vaseux Lake) | 2019-09-23 09:00 | 2019-09-27 17:00 | N | Y | annual plan request & BC maintenance does not affect the Alberta ATC | Line | Peak RC outage ID: 1-00662555 Peak RC path ID: 1-00676774 (E>W, export), 1-00676776 (W>E, import) , 5L96 (Selkirk - Vaseux Lake) |  | Limits ATC, 500 kV
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2019-09-23 09:00 | 2019-10-02 18:00 | N | Y | inspection, maintenance and testing | Line | Annual inspection, maintenance and testing of DC line side grounding switches (510s457, 511s357), 1325L (510s Sunnybrook - 511s Crossings) |  | 500 kV
ALTALINK | 895s T2 (895s Suffield) | 2019-09-23 09:00 | 2019-09-25 10:00 | N | N | riser replacement | Transformer | 895s T2 (895s Suffield) | Complete riser replacement between 895s43 and VR1. | For Information Only
ALTALINK | 901L (63s Red Deer - 74s Janet), 901AL (64s East Crossfield - 901L tap) | 2019-09-23 10:00 | 2019-09-26 16:00 | N | Y | SCADA equipment upgrade | Line | SCADA equipment upgrade 74s & 63s, migrate new alarms, controls, analogs and remote access to new SCADA system. Replace 74s25X., 901L (63s Red Deer - 74s Janet), 901AL (64s East Crossfield - 901L tap) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 54s Fort Saskatchewan 138 kV East Bus, 54s T3 (54s Fort Saskatchewan), 709L (54s Fort Saskatchewan - 172s Sherritt), 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2019-09-23 10:00 | 2019-09-26 18:00 | N | Y | install and commission bus protection, install slip on bushing CTs | Bus, Transformer, Line | Install and commission additional 138kV bus protection on East Bus, install slip on bushing CTs on T3, 54s Fort Saskatchewan 138 kV East Bus, 54s T3 (54s Fort Saskatchewan), 709L (54s Fort Saskatchewan - 172s Sherritt), 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T5 (370s North Lethbridge) | 2019-09-23 10:45 | 2019-09-26 16:45 | N | Y | maintain and doble | Transformer | 370s T5 (370s North Lethbridge) |  | 240 kV
ENMAX | 33.84L (ENMAX 43 - ENMAX 33), 43.2TR (ENMAX 43) | 2019-09-23 12:00 | 2019-09-23 18:00 | N | N | Substation Washing | Line, Transformer | Substation Washing. Adjust North Whip on 43MD138-43.2TR next outage. Check reversing switch., 33.84L (ENMAX 43 - ENMAX 33), 43.2TR (ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 739L (14s Devon - 305s Acheson), 305s 739 (305s Acheson), 14s 739N (14s Devon) | 2019-09-24 07:15 | 2019-10-01 17:45 | N | N | component replacements | Line, Circuit Breaker | 20190906- 604L n-1 looks to cause very low voltages (108 kV at 14s in basecase). Load transfer likely required., 739L (14s Devon - 305s Acheson), 305s 739 (305s Acheson), 14s 739N (14s Devon) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ENMAX | 1.1 CAP BANK | 2019-09-24 08:00 | 2019-09-24 16:00 | N | N | fall substation washing | Terminal Equipment | 1.1 CAP BANK |  | For Information Only
ENMAX | 1.5TR (ENMAX 1) | 2019-09-24 08:00 | 2019-09-24 10:00 | N | N | fall substation washing | Transformer | 1.5TR (ENMAX 1) | Fall Substation Washing. Check reversing switch | For Information Only
ALTALINK | 1140L (289s Saunders Lake - 89s Ellerslie) | 2019-09-24 08:00 | 2019-09-26 17:00 | N | Y | replace line PTs | Line | 1140L (289s Saunders Lake - 89s Ellerslie) |  | 240 kV, Contingency Requires Mitigation
ATCO | 956s 702T (956s Watt Lake) | 2019-09-24 08:00 | 2019-09-24 16:00 | N | N | install bird proofing | Transformer | 956s 702T (956s Watt Lake) | 956S - Install bird proofing on 502TD 702T will be out of service for the duration of work 701T will be in service | For Information Only
ALTALINK | 898L (37s North Calder - 92s Viscount), 92s 898 (92s Viscount) | 2019-09-24 08:30 | 2019-09-25 17:30 | N | N | breaker maintenance | Line, Circuit Breaker | 898L (37s North Calder - 92s Viscount), 92s 898 (92s Viscount) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 893L (312s Fidler - 893AL tap), 893L (806s Oldman River - 312s Fidler), 893AL (112s Windy Point - 893AL tap) | 2019-09-24 09:00 | 2019-09-24 15:00 | N | Y | upgrade MPLS node | Line | 893L (312s Fidler - 893AL tap), 893L (806s Oldman River - 312s Fidler), 893AL (112s Windy Point - 893AL tap) | Upgrade MPLS node. Need to de-energize 893L as comms will be lost to 112s and 806s. | For Information Only
ALTALINK | 445S Elk River | 2019-09-24 09:30 | 2019-09-24 13:30 | N | N | de-energize station | Station | Elk River | De-energize station in order to perform trip tests required for T1 Transformer Replacement, & Replace 445s3, 445s11, & 445s4 | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2019-09-24 10:00 | 2019-09-24 12:00 | N | N | fall substation washing | Transformer | 1.6TR (ENMAX 1) |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2019-09-24 12:00 | 2019-09-24 14:00 | N | N | fall substation washing | Transformer | 1.7TR (ENMAX 1) | Fall Substation Washing. Check reversing switch | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2019-09-24 14:00 | 2019-09-24 16:00 | N | N | fall substation washing | Transformer | 1.8TR (ENMAX 1) | Fall Substation Washing. Check reversing switch | For Information Only
NOVACORP | 330s BR_52 (330s Nova Corp), 330s Nova Corp 138kV Bus 1A | 2019-09-24 16:00 | 2019-09-26 12:00 | N | Y | maintenance | Circuit Breaker, Bus | 330s BR_52 (330s Nova Corp), 330s Nova Corp 138kV Bus 1A |  | Restricts Generation
ALTALINK | 715L (545s Provost - 650s Hansman Lake) | 2019-09-24 16:30 | 2019-09-24 17:00 | N | N | to energize 545s new 25kV switchgear | Line | 715L (545s Provost - 650s Hansman Lake) | to energize 545s new 25kV Switchgear | For Information Only
ENMAX | 11.2TR (ENMAX 11) | 2019-09-25 02:30 | 2019-10-10 02:00 | N | N | install new transformer secondary cables & energize new 8kV switch gear on return to service | Transformer | 11.2TR (ENMAX 11)
CENOVUS | 539s PCB_9202 (539s Sunday Creek) | 2019-09-25 07:00 | 2019-10-01 18:00 | N | Y | 5 year maintenance | Circuit Breaker | 539s PCB_9202 (539s Sunday Creek) |  | 240 kV, For Information Only
ALTALINK | 215L (38s East Edmonton - 286s Yasa), 38s 215N (38s East Edmonton) | 2019-09-25 07:15 | 2019-09-27 16:45 | N | N | replace 38s215N | Line, Circuit Breaker | 215L (38s East Edmonton - 286s Yasa), 38s 215N (38s East Edmonton) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.81L. 9.83L. 9.3TR. 9.2TR. 9PT138-Z31, 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 43 - ENMAX 9), 9.3TR (ENMAX 9), 9.2TR (ENMAX 9) | 2019-09-25 08:00 | 2019-09-25 18:00 | N | N | Fall Substation Washing. | Terminal Equipment, Line, Transformer | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 43 - ENMAX 9), 9.3TR (ENMAX 9), 9.2TR (ENMAX 9)
AESO-SC | OATI | 2019-09-25 08:00 | 2019-09-25 16:00 | N | N | performing maintenance on the Bloomington data center load balancers | SCInternal |  |  | For Information Only
ALTALINK | 827L (121s Brooks - 28s West Brooks) | 2019-09-25 08:30 | 2019-09-26 15:00 | N | N | install new air break control module for 28s827E (689) | Line | 827L (121s Brooks - 28s West Brooks) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 853s 701T (853s Ring Creek) | 2019-09-25 10:00 | 2019-09-29 10:00 | N | N | 2019 leak repair | Transformer | 853s 701T (853s Ring Creek) | 2019 Leak Repair / 853S Ring Creek 701T Load transfer to 702T
ALTALINK | 895s T2 (895s Suffield) | 2019-09-25 12:00 | 2020-01-24 16:00 | N | N | forced outage | Transformer | 895s T2 (895s Suffield) | Gas leak | For Information Only
EPCOR | 72CH11 (Hardisty - 987s Clover Bar) | 2019-09-26 02:00 | 2019-09-29 14:00 | N | N | disconnect Aux contacts and doble | Line | 72CH11 (Hardisty - 987s Clover Bar) |  | Pre-Condition
EPCOR | 72CK13 (987s Clover Bar - Kennedale) | 2019-09-26 02:00 | 2019-09-29 14:00 | N | N | disconnect Aux contacts and doble | Line | 72CK13 (987s Clover Bar - Kennedale) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s 69kV Bus 4 (987s Cloverbar) | 2019-09-26 02:00 | 2019-09-29 14:00 | N | Y | disconnect Aux contacts and doble | Bus | 987s 69kV Bus 4 (987s Cloverbar) |  | Pre-Condition, Restricts Generation
BLACKSPRING | 485S Black Springs | 2019-09-26 07:00 | 2019-09-26 11:00 | N | N | software replacement | Station
CNRL | 75-PLH-901 (838s Horizon Mining - 849s Joslyn) | 2019-09-26 07:30 | 2019-09-27 18:00 | N | Y | line maintenance | Line | 75-PLH-901 (838s Horizon Mining - 849s Joslyn) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s 80X (63s Red Deer) | 2019-09-26 08:00 | 2019-09-26 17:30 | N | N | salvage SF6 breaker | Circuit Breaker | 63s 80X (63s Red Deer) | 63s80X request to salvage SF6 breaker | For Information Only
ENMAX | 14.4TR (ENMAX 14) | 2019-09-26 08:00 | 2019-09-26 18:00 | N | N | fall substation washing | Transformer | 14.4TR (ENMAX 14) |  | For Information Only
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2019-09-26 08:00 | 2019-09-26 18:00 | N | N | fall substation washing | Shunts | 14.1C (ENMAX 14), 14.2C (ENMAX 14) |  | Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2019-09-26 08:00 | 2019-09-26 16:00 | N | N | 69kV bus differential and auto switching protection replacement at ENMAX 15 | Line | 15.62L (ENMAX 15 - ENMAX 16) |  | Pre-Condition
ATCO | 853s 702T (853s Ring Creek) | 2019-09-26 12:00 | 2019-09-30 10:00 | N | N | 2019 leak repair | Transformer | 853s 702T (853s Ring Creek) | 2019 Leak Repair / 853S Ring Creek 702T Load transfer to 701T | For Information Only, Pre-Condition
EPCOR | 805s T4 (805s Jasper), 805s J2405 (805s Jasper), 805s J2406 (805s Jasper) | 2019-09-27 07:00 | 2019-09-27 17:00 | N | Y | doble testing | Transformer, Circuit Breaker | 805s T4 (805s Jasper), 805s J2405 (805s Jasper), 805s J2406 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.60L (ENMAX 21 - ENMAX 15) | 2019-09-27 08:00 | 2019-09-27 16:00 | N | N | bus differential and autoswitching protection replacement and testing | Line | 15.60L (ENMAX 21 - ENMAX 15) | 15s 69kV bus Differential and Autoswitching protection replacement. Wiring and commissioning checks. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 21.2TR (ENMAX 21), ENMAX 21 B138-21.CAP (ENMAX 21), 50L (44s Bearspaw Plant - ENMAX 21), 44s 50X (44s Bearspaw) | 2019-09-27 08:00 | 2019-09-27 18:00 | N | Y | fall substation washing | Transformer, Circuit Breaker, Line | 21.2TR (ENMAX 21), ENMAX 21 B138-21.CAP (ENMAX 21), 50L (44s Bearspaw Plant - ENMAX 21), 44s 50X (44s Bearspaw) | Fall Substation Washing. Corrective 21MD138-21.2TR center phase whip not set correctly. Oil sampling 21.2TC. Check reversing switch 21.2TR. | For Information Only, Pre-Condition
ATCO | 740s H.R.Milner RTU/SCADA | 2019-09-27 09:00 | 2019-10-11 17:00 | N | N | forced outage | Terminal Equipment |  |  | For Information Only
CNRL | 75-PLH-902 (838s Horizon Mining - 849s Joslyn) | 2019-09-28 07:30 | 2019-09-29 18:00 | N | Y | line maintenance | Line | 75-PLH-902 (838s Horizon Mining - 849s Joslyn) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Syncrude Mildred Lake | 2019-09-29 08:00 | 2019-10-09 20:00 | N | N | 5 year maintenance | Station |  | Bus 18 will be isolated for a 5 year PM CB 1835 will be operated to isolate Bus 18 10 MVAr Capacitor bank (already shown on visibility) tag 31-0PC15-1 will be tested. Once Bus 18 PM and capacitor bank testing is concluded, CB 18215 will be operated to commission capacitor bank and CB 1835 will be operarted to energize Bus 18. | For Information Only
ATCO | ALC01L (409s Shell Scotford - 408s Air Liquide Scotford) | 2019-09-29 17:00 | 2019-10-11 17:00 | N | Y | complete protection upgrade | Line | ALC01L (409s Shell Scotford - 408s Air Liquide Scotford) | Complete ALC01L protection upgrade. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72MG16 (Meadowlark - Garneau), Meadowlark M724 (Meadowlark) | 2019-09-30 07:00 | 2019-10-04 17:00 | N | N | breaker maintenance & doble CT's | Line, Circuit Breaker | Meadowlark M724 (Meadowlark), 72MG16 (Meadowlark - Garneau) |  | Firm Load Loss, Pre-Condition
ATCO | 7L23 (858s Narrows Creek - 796s Nipisi), 796s 702 (796s Nipisi) | 2019-09-30 07:00 | 2019-10-10 15:35 | N | N | protection upgrade and breaker replacement | Line, Circuit Breaker | 7L23 (858s Narrows Creek - 796s Nipisi), 796s 702 (796s Nipisi) | Protection Upgrade and 25kv breaker replacement project | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 803s L2402 (803s Lambton) | 2019-09-30 07:00 | 2019-10-04 17:00 | N | Y | breaker maintenance | Circuit Breaker | 803s L2402 (803s Lambton) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | Woodcroft T3 (Woodcroft), Woodcroft WAB3 (Woodcroft) | 2019-09-30 07:00 | 2019-10-06 17:00 | N | N | disconnect replacement | Transformer, Switch | Woodcroft WAB3 (Woodcroft) |  | For Information Only, Pre-Condition
CNRL | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-09-30 07:30 | 2019-09-30 18:00 | N | Y | line maintenance | Line | 75-PLH-903 (838s Horizon Mining - 842s Horizon Upgrading) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 820s 702T (820s Hangingstone), 820s 507C1 (820s Hangingstone), 820s 507C2 (820s Hangingstone) | 2019-09-30 08:00 | 2019-10-04 17:00 | N | N | install bird proofing | Transformer, Shunts | 820s 702T (820s Hangingstone), 820s 507C1 (820s Hangingstone), 820s 507C2 (820s Hangingstone) | 820S Bird Proofing - 702T Outage (Sept. 30 to Oct. 4) Install Bird Proofing at 820S Hangingstone 702T & affected 25KV bus OOS | For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2019-09-30 08:00 | 2019-09-30 16:00 | N | N | differential and auto-switching protection replacement | Transformer | 15.2TR (ENMAX 15) | 15s 69kV bus Differential and Autoswitching protection replacement. Wiring and commissioning checks. | For Information Only
ALTALINK | 752L (64s East Crossfield - 752L67), 64s 752X (64s East Crossfield) | 2019-09-30 08:00 | 2019-10-19 17:30 | N | N | relocate 752L to new 138kV bus 2, relocate 752L to new 138kV bus 2 (P1904) | Line, Circuit Breaker | Relocate 752L to new 138kV bus 2 Relocate VT4,Connect bus from new 64s652 tie breaker to 64s46 Install new 94L and 1704L Fortis cables to new Switch gear. Test Energize New T3, Bus 2, and Switch Gear building.Close Open PointE, F, G,J and K. |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 320p 834X (320p Keephills), 834L (384s Keystone - 320p Keephills) | 2019-09-30 08:00 | 2019-10-01 17:00 | N | N | modifying sync-check settings on relay | Circuit Breaker, Line | 320p 834X (320p Keephills), 834L (384s Keystone - 320p Keephills) | Modifying sync-check settings on relay | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 14.1TR (ENMAX 14) | 2019-09-30 08:00 | 2019-10-05 18:00 | N | N | doble test and maintenance | Transformer | Doble test transformer. Transformer secondary cable tests. Transformer maintenance. Gas relay testing. Check reversing switch. |  | For Information Only
BLACKSPRING | 485S Black Springs | 2019-09-30 08:00 | 2019-09-30 12:00 | N | N | software replacement | Station
ENMAX | 38.3TR (ENMAX 38) | 2019-09-30 08:00 | 2019-10-11 16:00 | N | N | doble test and maintenance | Transformer | Doble test transformer. Transformer secondary cable tests. Transformer maintenance. Gas relay testing. Check reversing switch. Possible ECI bushings |  | For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2019-09-30 08:00 | 2019-10-10 12:00 | N | N | transformer differential relay panel replacement | Transformer | 37.2TR (ENMAX 37) |  | For Information Only
ALTALINK | 1075L (132s Ware Junction - 28s West Brooks) | 2019-09-30 09:00 | 2019-10-02 08:00 | N | Y | install new air break control module | Line | 1075L (132s Ware Junction - 28s West Brooks) | Install new air break control module for 28s1075 (389). | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 2L294 (Nelway - A.A. Lambert) | 2019-09-30 09:00 | 2019-10-11 17:00 | N | Y | to install new 2SA3 & 2SSVT1 on NLY 2B3 | Line | 2L294 (Nelway - A.A. Lambert) |  | Limits ATC, Pre-Condition
ALTALINK | 347s 720X (347s Fox Creek), 720L (347s Fox Creek - 397s Benbow) | 2019-09-30 09:30 | 2019-10-04 17:00 | N | N | change breaker control module and line protections to the new control building | Circuit Breaker, Line | 347s 720X (347s Fox Creek), 720L (347s Fox Creek - 397s Benbow) | Change 720X breaker control module and 720L line protections to the new control building. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2019-09-30 09:30 | 2019-10-01 17:00 | N | Y | change arms and insulators | Line | 7L702 (137s Sedgewick - 757s Battle River) | Change Arms and Insulators on 7L702 | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 746s T2 (746s Sherwood Park) | 2019-09-30 09:30 | 2019-10-03 16:00 | N | N | filter installation, maintenance, doble | Transformer | Tap Changer Filter Installation (746sT2), TX maintenance, doble, oil leaks |  | For Information Only
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 787L (166s Dow Chemical Fort Saskatchewan - 787L33), 166s T2 (166s Dow Chemical Fort Saskatchewan), 166s T3 (166s Dow Chemical Fort Saskatchewan), 166s Dow Chemical Fort Saskatchewan 138kV Bus 1 | 2019-09-30 10:00 | 2019-09-30 18:00 | N | Y | switch & breaker maintenance | Line, Transformer, Bus | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan), 787L (166s Dow Chemical Fort Saskatchewan - 787L33), 166s T2 (166s Dow Chemical Fort Saskatchewan), 166s T3 (166s Dow Chemical Fort Saskatchewan), 166s Dow Chemical Fort Saskatchewan 138kV Bus 1 | Switch maintenance 166s11 and others, breaker maintenance 166s787W. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation
ATCO | 6L05 (764s Heisler - 6L05 tap) | 2019-09-30 10:00 | 2019-09-30 13:00 | N | N | structure replacement | Line | 6L05 (764s Heisler - 6L05 tap) | Emergency outage to replace damaged structure | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s Red Deer 240kV North Bus, 63s T1 (63s Red Deer) | 2019-09-30 10:00 | 2019-10-03 15:00 | N | Y | RTU upgrades | Bus, Transformer | 63s Red Deer 240kV North Bus, 63s T1 (63s Red Deer) | Migrate and commission all T1 (TX18310) & 63s24 (1552) protections, breaker fail protections, breaker, status, controls, alarms, metering, to the new RTU and LAN. Replace 63s11 (189) air break control module, commission alarms control and status to new RTU. Replace and commission T1 SCADA meter.T1 TX18310 and 240KV North Bus, breaker control and associated T1 transformer protections will be out of service. Loss of visibility or possible false status and alarms for associated equipment during cut over and commissioning tests. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2019-09-30 11:00 | 2019-10-03 17:00 | N | Y | SCADA equipment upgrade | Line | 23.80L (74s Janet - ENMAX 23) | SCADA equipment upgrade | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 161L (255s Vulcan - 504s Queenstown) | 2019-09-30 12:00 | 2019-09-30 14:30 | N | N | close open point and connect high side of mobile | Line |  | Vulcan Area Capacity and reliability Project: Close open point and connect high side of 470s mobile. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 454s T1 (454s Buck Lake) | 2019-09-30 12:30 | 2019-10-03 17:30 | N | N | bushing replacement | Transformer | - 138kV (HV) Bushing Replacement at Tx18433 (T1), - 25kV (LV) Bushing Replacement at Tx18433 (T1) and 25kV (Neutral) Bushing Replacement at Tx18433 (T1) |  | For Information Only
ALTALINK | 255s T1 (255s Vulcan) | 2019-09-30 12:30 | 2019-09-30 14:30 | N | N | close open point and connect low side of mobile. | Transformer |  | Vulcan Area Capacity and reliability Project: Close open point and connect low side of 470s mobile. | For Information Only
ATCO | 773s 601T (773s Coronation) | 2019-09-30 13:00 | 2019-10-06 16:00 | N | N | replace PLC with cooper station controller | Transformer | 773s 601T (773s Coronation) | 601T OOS in order to Replace PLC with Cooper Station Controller Backfeed station service | For Information Only
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2019-09-30 13:00 | 2019-10-04 13:00 | N | Y | fire damage repairs | Line | 20190906- likely require control of RCP flow, 7L59 (789s Keg River - 7L59 tap) | FIRE DAMAGE REPAIRS | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2019-09-30 14:30 | 2019-10-11 08:00 | N | Y | in conjunction with 255s outage | Line |  | Vulcan Area Capacity and reliability Project: In conjunction with 255s Station outage. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 255S Vulcan | 2019-09-30 15:00 | 2019-10-11 17:00 | N | N | adding new transformer | Station |  | Vulcan Area Capacity and reliability Project: 470s mobile supporting 255s Fortis load. Add new transformer and 25 kV metal clad.Test energize new trnasformer and soak Oct. 7. test enrgize new 25kv metal clad and put load on new Xmer Oct. 7. Close Open Points A, B, E, J, K, I. | For Information Only
ALTALINK | 551L (945s Sunshine - 551L238) | 2019-10-01 | 2019-10-01 04:00 | N | N | close 551L open point 'D' and change protections back to normal on 953s2167, 953s2397 & 953s47 | Line | 551L (945s Sunshine - 551L238) | - Valard will be closing 551L Open Point 'D'; RET will be changing protections back to normal on 953s2167, 953s2397 & 953s47 | For Information Only, Pre-Condition
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2019-10-01 07:00 | 2019-10-01 18:30 | N | N | modifications to allow construction to continue at 150s Clyde | Line | 223L (159s Colinton - 150s Clyde) | T-Line outage on 223L to allow for modifications to allow construction to continue at 150s Clyde substation. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 879L (368s Burdett - 244s Bowmanton) | 2019-10-01 07:00 | 2019-10-21 17:00 | N | Y | component replacements between structures #298 - 731 | Line | 879L (368s Burdett - 244s Bowmanton) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 72VN21 (Namao - 511s Victoria) | 2019-10-01 07:00 | 2019-10-11 17:00 | N | N | line maintenance and upgrades | Line | 72VN21 (Namao - 511s Victoria) |  | Pre-Condition
CNRL | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) | 2019-10-01 07:30 | 2019-10-02 18:00 | N | Y | line maintenance | Line | 75-PLH-904 (838s Horizon Mining - 842s Horizon Upgrading) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2019-10-01 08:00 | 2019-10-01 16:00 | N | N | performing maintenance on the Minneapolis data center load balancers | SCInternal |  |  | For Information Only
ALTALINK, EPCOR | 89s 1052 (89s Ellerslie), 89s 1152 (89s Ellerslie), 909L (89s Ellerslie - 665s Dome) | 2019-10-01 08:00 | 2019-10-02 17:00 | N | Y | replace 89s78 Line PTs | Circuit Breaker, Line | 89s 1152 (89s Ellerslie), 909L (89s Ellerslie - 665s Dome) | Replace 89s78 Line PTs | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 71s 1552 (71s Lamoureux) | 2019-10-01 08:00 | 2019-10-01 12:59 | N | Y | low gas | Circuit Breaker | 71s 1552 (71s Lamoureux) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 618sVR1 (618s Riverbend) | 2019-10-01 08:00 | 2019-10-02 17:00 | N | N | maintain and doble | Transformer |  | maintain, doble, winding resistance testing VR1 | For Information Only
Medicine Hat | MH69s2 MH69_215 (MH69s2 North Industrial), MH69s2 MH69-T22 (North Industrial Substation), MH69s2 MH69_206 (MH69s2 North Industrial), MH69s2 T21 (MH69s2 North Industrial) | 2019-10-01 08:00 | 2019-10-01 12:00 | N | N | control verification | Circuit Breaker, Transformer | MH69s2 MH69_215 (MH69s2 North Industrial), MH69s2 MH69-T22 (North Industrial Substation), MH69s2 MH69_206 (MH69s2 North Industrial), MH69s2 T21 (MH69s2 North Industrial) |  | For Information Only
ENMAX | 15.1TR (ENMAX 15) | 2019-10-01 08:00 | 2019-10-01 16:00 | N | N | 69kV bus differential and autoswitching protection replacement at ENMAX 15 | Transformer | 15.1TR (ENMAX 15) | 15s 69kV bus Differential and Autoswitching protection replacement. Wiring and commissioning checks. | For Information Only
ENMAX | ENMAX 21 B138-20.82 (ENMAX 21), 20.82L (ENMAX 21 - ENMAX 20) | 2019-10-01 08:00 | 2019-10-01 16:00 | N | N | breaker maintenance | Circuit Breaker, Line | ENMAX 21 B138-20.82 (ENMAX 21), 20.82L (ENMAX 21 - ENMAX 20) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 418L (20s Ghost - 418L193A) | 2019-10-01 08:00 | 2019-10-03 10:00 | N | N | line clearance mitigation on structure #154 | Line | 418L (20s Ghost - 418L193A) |  | Pre-Condition
ATCO | 827s SVC (827s Cranberry Lake), 827s 703T (827s Cranberry Lake) | 2019-10-01 09:00 | 2019-10-06 17:00 | N | Y | urgent trouble shoot and repair failed control system #1 | Shunts, Transformer | 827s SVC (827s Cranberry Lake) | Trouble shoot and Repair Failed Control System #1 The SVC is currently running on its backup system. Need to repair Control System 1 to restore the stations reliability. | Pre-Condition
ALTALINK | 83s T3 (83s Taber) | 2019-10-01 09:15 | 2019-10-02 16:45 | N | N | replace SS2 | Transformer | 83s T3 (83s Taber) |  | For Information Only
ALTALINK | 284s 688A (284s Nose Creek) | 2019-10-02 07:00 | 2019-10-03 16:00 | N | N | customer requested outage | Switch | 284s 688A (284s Nose Creek), 688AL (284s Nosecreek - 688L tap) |  | For Information Only
ALTALINK | 723L (438s Westlock - 150s Clyde) | 2019-10-02 07:00 | 2019-10-02 18:30 | N | N | maintenance | Line | 723L (438s Westlock - 150s Clyde) | T-Line outage on 723L to allow for modifications to allow construction to continue at 150s Clyde substation. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
CENOVUS | 539s PCB_9203 (539s Sunday Creek) | 2019-10-02 07:00 | 2019-10-08 18:00 | N | Y | 5 year maintenance | Circuit Breaker | 539s PCB_9203 (539s Sunday Creek) |  | 240 kV, For Information Only
CNRL | 75-TR-2701 (838s Horizon Mining) | 2019-10-02 07:30 | 2019-10-14 18:00 | N | Y | transformer maintenance. | Transformer | 75-TR-2701 (838s Horizon Mining) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 266s SC1 | 2019-10-02 08:00 | 2019-10-02 17:30 | N | N | techs to investigate issue | Station | 266s 1038L FSC (266s SC1) | Techs to investigate issue with laser power unit. FSC2 Urgent GOI. Priority 5 work. This issue needs to be investigated before the yearly outage in Nov/19 | For Information Only
ALTALINK | 320p552 GOI | 2019-10-02 08:00 | 2019-10-03 17:00 | N | Y | Modifying sync-check settings on relay | Terminal Equipment | 320p 552 (320p Keephills) |  | 240 kV, For Information Only
ENMAX | ENMAX 26 B138-26BT3 (ENMAX 26) | 2019-10-02 08:00 | 2019-10-02 16:00 | N | N | HV breaker maintenance | Circuit Breaker | ENMAX 26 B138-26BT3 (ENMAX 26) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2019-10-02 08:00 | 2019-10-06 18:00 | N | N | change crossarms & insulators | Line | 7L16 (766s Nevis - 948s Heatburg) | change crossarms & insulators | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 1051L (28s West Brooks - 324s Cassils) | 2019-10-02 08:30 | 2019-10-03 15:00 | N | Y | Install new air break | Line | 1051L (28s West Brooks - 324s Cassils) | Install new air break control module for 28s1051 (489). | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 84L (35s Rundle - 33s Spray) | 2019-10-02 09:00 | 2019-10-04 18:00 | N | N | structure replacements | Line | 84L (35s Rundle - 33s Spray) | Structure Replacements (Str's Range #2-13) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff) | 2019-10-03 07:00 | 2019-10-03 18:30 | N | N | construction at 150s | Line | 792L (150s Clyde - 191s N.W. Cardiff) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s T2 (121s Brooks) | 2019-10-03 07:30 | 2019-10-04 14:30 | N | N | replace arrestors | Transformer | 121s T2 (121s Brooks) | Replace 138kV Arrestors for T2 | For Information Only
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee), 89s 2052 (89s Ellerslie), 89s 2152 (89s Ellerslie) | 2019-10-03 07:45 | 2019-10-03 17:45 | N | Y | re-enable SPTR | Line, Circuit Breaker |  | Techs to modify logic and complete required rewiring on 89s2052, 89s2152 (as per AESO request to re-enable SPTR) | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX, ALTALINK | 7.84L (ENMAX 36 - ENMAX 7), 36.81L (44s Bearspaw - ENMAX 36), 36.1TR (ENMAX 36) | 2019-10-03 08:00 | 2019-10-03 18:00 | N | Y | fall substation washing | Line, Transformer |  | Fall Substation Washing. 36MD138-36.1TR Whip not set - adjust/repair next outage. Check reversing switch 36.1TR, 36.3TR | Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ENMAX | 162s 138-RB85 (162s Beddington) | 2019-10-03 08:00 | 2019-10-03 16:00 | N | N | breaker maintenance | Circuit Breaker | 162s 138-RB85 (162s Beddington) |  | Contingency Requires Mitigation, Creates Radial Feeds
SUNCOR | 29PL9-6 (29EDD-1 Millennium - 29EDD-34) | 2019-10-03 08:00 | 2019-10-14 18:00 | N | Y | planned 5 year maintenance | Line | 29PL9-6 (29EDD-1 Millennium - 29EDD-34) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 34.2TR (ENMAX 34), 16.60L (ENMAX 34 - ENMAX 16) | 2019-10-03 08:00 | 2019-10-07 16:00 | N | N | Tx replacement | Transformer, Line |  | 34.2TR replacement. Install bus to 34.2MD, remove bus from 34.3MD, rewire 69kv PTs, install flex bus structure | Creates Radial Feeds, Pre-Condition
ALTALINK | 409s T1 (409s Shell Scotford) | 2019-10-03 08:30 | 2019-10-03 17:30 | N | N | maintenance | Transformer |  | TX maintenance, hotspot (10deg) 406s5, hotspot (20deg) 406s3, 138kV breaker maintenance, replace damage insulators 406s6 | For Information Only
ALTALINK | 418L (281s Johnson - 418L194A) | 2019-10-03 12:00 | 2019-10-10 17:00 | N | N | line clearance mitigation on structures #232, 236, 237, 253 & 267 | Line | 418L (281s Johnson - 418L194A) | Line clearance mitigation on Structures #232, 236, 237, 253 & 267 | Pre-Condition
BLACKSPRING | 485S Black Springs | 2019-10-04 09:00 | 2019-10-04 15:00 | N | N | frequency testing | Station |  |  | For Information Only
ALTALINK | 349S Stavely | 2019-10-05 08:00 | 2019-10-06 16:30 | N | N | upgrade 25KV bus ampacity | Station | P1907 Vulcan Stavely area capacity and reliability |  | For Information Only
ALTALINK | 444L (198s Blackfalds - 217s North Red Deer) | 2019-10-05 08:00 | 2019-10-06 17:30 | N | N | repair train contact damage | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.82L (ENMAX 14 - ENMAX 11), 14.1C (ENMAX 14), 14.1TR (ENMAX 14), 14.3TR (ENMAX 14), 14.2C (ENMAX 14) | 2019-10-05 08:00 | 2019-10-05 16:00 | N | N | fall substation washing and check reversing switch 14.1 | Line, Shunts, Transformer | 14.1C (ENMAX 14), 14.2C (ENMAX 14), 14.1TR (ENMAX 14), 14.2TR (ENMAX 14), 11.82L (ENMAX 14 - ENMAX 11) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L06 (A793s West Peace River - 784s Donnelly) | 2019-10-05 10:00 | 2019-10-09 14:00 | N | N | 784s 706D2 emergency repair | Line |  |  | Firm Load Loss, Pre-Condition
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2019-10-05 16:00 | 2019-10-05 18:00 | N | N | fall substation washing | Line | 14.83L (ENMAX 14 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 | 2019-10-06 07:00 | 2019-10-09 17:00 | N | N | CT associated to the breaker to be tie-in to DFR for monitoring & trending of 144kV system current values | Station | CT associated to the breaker to be Tie-in to DFR for monitoring & trending of 144kV system current values. It will be approximately 2 hour outage on breaker. Only one breaker taken out of service at a time and restored prior to working on next breaker. The following breakers affected: 635-752-611, 635-752-612, 635-752-613, 635-752-621, 635-752-622, 635-752-623, 635-752-631, 635-752-632, 635-752-642, 635-752-643, 635-752-651, 635-752-652, 635-752-653, 635-752-661, 635-752-662, 635-752-663 |  | For Information Only
BCH | 5L72 (Mica Creek - Nicola) | 2019-10-06 08:39 | 2019-10-15 08:00 | N | Y | Urgent outage. BC Maintenance does not affect the Alberta ATC | Line | Peak COS ID: 1-00680933 AB Peak RC COS# : 1-00683959 (W>E), 1-00683960 (E>W) , 5L72 (Mica Creek - Nicola) | MCA Switchgear Roof Replacement project& | For Information Only, 500 kV
ENMAX | 16.61L (ENMAX 16 - ENMAX 27), ENMAX 16 B69-16.61 (ENMAX 16), ENMAX 27 B69-16.61 (ENMAX 27) | 2019-10-06 10:00 | 2019-10-06 12:00 | N | N | fall transmission line washing | Line, Circuit Breaker | 16.61L (ENMAX 16 - ENMAX 27) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.83L (ENMAX 43 - ENMAX 9), ENMAX 43 B138-9.83 (ENMAX 43), ENMAX 9 B138-9.83 (ENMAX 9) | 2019-10-06 12:00 | 2019-10-06 14:00 | N | N | fall pothead washing | Line, Circuit Breaker | 9.83L (ENMAX 43 - ENMAX 9) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37), 37.2TR (ENMAX 37), 74s 37.82W (74s Janet) | 2019-10-06 13:00 | 2019-10-06 18:00 | N | Y | substation washing and check reversing switch | Line, Transformer, Circuit Breaker | 37.82L (74s Janet - ENMAX 37), 37.2TR (ENMAX 37) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 33.84L (ENMAX 43 - ENMAX 33), ENMAX 33 B138-33.84 (ENMAX 33), ENMAX 43 B138-33.84 (ENMAX 43) | 2019-10-06 14:00 | 2019-10-06 16:00 | N | N | fall pothead washing | Line, Circuit Breaker | 33.84L (ENMAX 43 - ENMAX 33) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2019-10-07 02:00 | 2019-10-18 02:00 | N | N | differential relay replacement | Transformer | 11.4TR (ENMAX 11) |  | For Information Only
EPCOR | 330p 808 (330p Genesee), 8L10 (330P Genesee - Fording Coal Mine) | 2019-10-07 07:00 | 2019-10-11 17:00 | N | N | breaker maintenance | Circuit Breaker, Line | 330p 808 (330p Genesee) |  | For Information Only
EPCOR | Rossdale RV726 (Rossdale), 72RV4 (Rossdale - 511s Victoria) | 2019-10-07 07:00 | 2019-10-07 17:00 | N | N | breaker maintenance | Circuit Breaker, Line | Rossdale RV726 (Rossdale) |  | For Information Only
ENMAX | 14.3TR (ENMAX 14) | 2019-10-07 08:00 | 2019-10-17 16:00 | N | N | bushing replacement | Transformer | 14.3TR (ENMAX 14) |  | For Information Only
ENMAX | 22.3TR (ENMAX 22) | 2019-10-07 08:00 | 2019-10-18 16:00 | N | N | transformer differential panel replacement | Transformer | 22.3TR (ENMAX 22) | transformer differential panel replacement. Install slip over HV CTs | For Information Only
ENMAX | 31.3TR (ENMAX 31) | 2019-10-07 08:00 | 2019-10-25 16:00 | N | N | transformer maintenance | Transformer | 31.3TR (ENMAX 31) | Doble test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. ECI Bushings. Oil sampling MT. TC | For Information Only
ENMAX | 32.3TR (ENMAX 32) | 2019-10-07 08:00 | 2019-10-09 16:00 | N | N | upgrade T-60 relay CPU and test CTs | Transformer | 32.3TR (ENMAX 32) |  | For Information Only
ALTALINK | 320p 2052 (320p Keephills) | 2019-10-07 08:00 | 2019-10-07 16:00 | N | Y | modifying sync-check settings | Circuit Breaker | 320p 2052 (320p Keephills) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), ENMAX 23 B138-2.80 (ENMAX 23) | 2019-10-07 08:00 | 2019-10-11 16:00 | N | N | SF6 leak repair, sheath test | Line, Circuit Breaker | 23B138-2.80 - SF6 leak repair. Transmission - Cables - Sheath Test - 138-2.80 Line XLPE |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 95s T2 (95s Imperial Oil Edmonton) | 2019-10-07 08:15 | 2019-10-10 16:45 | N | N | customer requested to replace NGR | Transformer | 95s T2 (95s Imperial Oil Edmonton) |  | For Information Only
ALTALINK | 931L (132s Ware Junction - 28s West Brooks) | 2019-10-07 09:00 | 2019-10-08 15:00 | N | Y | install new air break control module for 28s931N (189) | Line | 931L (132s Ware Junction - 28s West Brooks) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 347s 199W (347s Fox Creek), 199L (347s Fox Creek - 741s Fox Creek) | 2019-10-07 09:00 | 2019-10-11 17:00 | N | Y | change breaker control module and line protections | Circuit Breaker, Line | 347s 199W (347s Fox Creek), 199L (347s Fox Creek - 741s Fox Creek) | Change 199W breaker control module and 199LW line protections to the new control building, Change out 347s10 PT JB. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 84L (35s Rundle - 33s Spray) | 2019-10-07 09:00 | 2019-10-10 18:00 | N | N | structure replacements | Line | 84L (35s Rundle - 33s Spray) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 63s T2 (63s Red Deer), 63s Red Deer 240kV South Bus | 2019-10-07 10:00 | 2019-10-10 15:00 | N | Y | RTU upgrades | Transformer, Bus | 63s T2 (63s Red Deer) | Migrate and commission all T2 (TX18898) & 63s25 (1652) protections, breaker fail protections, breaker, status, controls, alarms, metering, to the new RTU and LAN. Replace 63s10 (289) air break control module, commission alarms control and status to new RTU. Replace and commission T2 SCADA meter. T1 TX18898 and 240KV South Bus, breaker control and associated T2 transformer protections will be out of service. Loss of visibility or possible false status and alarms for associated equipment during cut over and commissioning tests. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 71s T2 (71s Lamoureux) | 2019-10-07 10:30 | 2019-10-10 18:00 | N | Y | transformer maintenance | Transformer | Perform maintenance on T2. |  | 240 kV, Pre-Condition
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24), ENMAX 24 B138-24.83 (ENMAX 24), 74s 24.83X (74s Janet) | 2019-10-07 11:00 | 2019-10-10 17:00 | N | Y | SCADA equipment upgrade | Line, Circuit Breaker | 24.83L (74s Janet - ENMAX 24) | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | For Information Only
ALTALINK | 730L (285s East Camrose - 730L62), 285s 730N (285s East Camrose) | 2019-10-07 12:00 | 2019-10-10 18:00 | N | N | replace damaged switch and dead end strain insulators | Line, Circuit Breaker | Replace damaged switch 285s90 and replacement of the 730L dead end strain insulators |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 739L (14s Devon - 305s Acheson) | 2019-10-07 12:15 | 2019-10-10 17:45 | N | N | component replacements | Line | Component Replacements Str's Range 438-645 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2019-10-07 13:00 | 2019-10-11 13:00 | N | Y | FIRE DAMAGE REPAIRS | Line | 20190906- likely require control of RCP flow | FIRE DAMAGE REPAIRS | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s 2252 (244s Bowmanton) | 2019-10-08 07:30 | 2019-10-08 12:30 | N | N | replace tank heaters | Circuit Breaker | 244s 2252 (244s Bowmanton) |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s11 (62s Brazeau) | 2019-10-08 07:30 | 2019-10-08 20:30 | N | Y | maintenance | Switch | 62s11 (62s Brazeau) | BR1 generator brushgear & GSU monitoring system outage | Restricts Generation
ALTALINK | 522AL (868s Keephills Make-Up - 522L tap), 522L (866s Sundance Make-Up - 522AL tap), 866S Sundance Make-Up, 868S Keephills Make-Up | 2019-10-08 08:00 | 2019-10-11 17:00 | N | N | metering upgrade | Line, Station | 522AL (868s Keephills Make-Up - 522L tap), 522L (866s Sundance Make-Up - 522AL tap) | Metering upgrade - move meter location | For Information Only
ALTALINK | 244s 2652 (244s Bowmanton) | 2019-10-08 12:31 | 2019-10-08 17:30 | N | N | replace tank heaters | Circuit Breaker | 244s 2652 (244s Bowmanton) |  | Contingency Requires Mitigation, Overload, Pre-Condition
CENOVUS | 539s Sunday Creek 240 kV East Bus | 2019-10-09 07:00 | 2019-10-15 18:00 | N | Y | 5 year maintenance | Bus | 539s Sunday Creek 240 kV East Bus |  | 240 kV
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2019-10-09 07:00 | 2019-10-13 17:00 | N | Y | construction activity around line (driving piles) | Line | 909L (89s Ellerslie - 665s Dome) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s C1 (17s Benalto) | 2019-10-09 07:30 | 2019-10-09 17:30 | N | Y | commission new 43M switch in control building | Shunts | 17s C1 (17s Benalto) |  | 240 kV, Pre-Condition
ALTALINK | 445S Elk River | 2019-10-09 08:00 | 2019-10-09 18:00 | N | N | de-energize station in order to perform trip tests required for T1 transformer replacement & Replace 445s3, 445s11, & 445s4 | Station | Elk River |  | For Information Only
AESO-SC | OATI | 2019-10-09 08:00 | 2019-10-09 16:00 | N | N | performing maintenance on the Bloomington data center load balancers | SCInternal |  |  | For Information Only
ALTALINK | 525S Carseland | 2019-10-09 08:00 | 2019-10-09 17:00 | N | N | 25 kV breaker maintenance, oil leak repair and tank heater replacement | Station |  |  | For Information Only
ALTALINK | 255S Vulcan | 2019-10-09 08:30 | 2019-10-09 12:30 | N | N | Vulcan area capacity and reliability project, disconnect low side of 470s mobile (P1907) | Station | P1907 Vulcan Stavely area capacity and reliability |  | For Information Only
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 665s TX1 (665s Dome) | 2019-10-09 09:00 | 2019-10-09 15:00 | N | Y | pile installation | Line, Transformer |  |  | 240 kV
ATCO | 729s 703T (729s Otauwau) | 2019-10-09 09:00 | 2019-10-11 16:00 | N | N | drain oil remove bushings and replace failing gaskets | Transformer | 729s 703T (729s Otauwau) | Drain Oil Remove Bushings and replace failing gaskets, all Load Being Carried by 701T
SUNCOR | 635EDD-1000 PT-1000 (635EDD-1000), 635EDD-1000 PT-1001 (635EDD-1000) | 2019-10-10 07:00 | 2019-10-12 17:00 | N | Y | tie-in for digital fault recorder relay project | Transformer | 635EDD-1000 PT-1000 (635EDD-1000), 635EDD-1000 PT-1001 (635EDD-1000) | Tie-in for Digital Fault Recorder Relay project. Only one transformer taken out of service at a time and restored prior to working on next transformer. | 240 kV
SUNCOR | 29PL6-7 (836s Steepbank - 29EDD-5 29Edd-5) | 2019-10-10 08:00 | 2019-10-25 18:00 | N | N | 72kV Line 29PL6-7 switch alignment, work on 625TD | Line | 29PL6-7 (836s Steepbank - 29EDD-5 29Edd-5)
SUNCOR | 29EDD-1 Millennium RTU/SCADA, SUNCOR DNP Outage, SUNCOR ICCP Outage | 2019-10-11 07:00 | 2019-10-11 13:00 | N | N | fiber optic upgrade | Terminal Equipment |  | Suncor is performing a fiber move on Friday Oct 11th, 2019, work will start between 7am and 1pm and will take up to 4 hours. Suncor has identified a minimal risk that visibility of the Suncor System to AESO may be lost. Suncor will contact both the AESO System Controller and the AESO Real Time desk one hour prior to the start of work. | Affects Visibility
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2019-10-11 08:00 | 2019-10-11 18:00 | N | Y | urgent outage to address clearance issues | Line | 50L (44s Bearspaw Plant - ENMAX 21) |  | For Information Only
ALTALINK | 170L (632s Russell - 799s Coleman) | 2019-10-12 07:00 | 2019-10-13 18:00 | N | Y | urgent trouble corrective on structures #5, 22, 23 & 38 | Line | 170L (632s Russell - 799s Coleman) RC West webOMS Outage ID: 60012815 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635PT-1038 (635EDD-1001) | 2019-10-12 07:00 | 2019-10-13 17:00 | N | N | replace RTD and Thermowell for repairing minor leak | Transformer | 635PT-1038 (635EDD-1001) |  | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41), 6.1TR (ENMAX 6) | 2019-10-12 08:00 | 2019-10-12 18:00 | N | N | substation washing | Line, Transformer | 6.82L (ENMAX 6 - ENMAX 41), 6.1TR (ENMAX 6) | Substation Washing. Oil sampling 6.1TR bushing. | Creates Radial Feeds, Firm Load Loss
EPCOR, ALTALINK | 330p 807 (330p Genesee), 430L (330P Genesee - 510S Sunnybrook) | 2019-10-13 07:00 | 2019-10-13 17:00 | N | Y | doble | Circuit Breaker, Line | 330p 807 (330p Genesee) |  | For Information Only
ENMAX | 47.2TR (ENMAX 47) | 2019-10-13 08:00 | 2019-10-13 18:00 | N | N | substation washing | Transformer | 47.2TR (ENMAX 47) | Spring Substation Washing. 47s. Corrective 47.2TR MD left phase blade not set correctly. 10/13/2019 | For Information Only
ENMAX | 47.1TR (ENMAX 47) | 2019-10-14 08:00 | 2019-10-14 18:00 | N | N | substation washing | Transformer | 47.1TR (ENMAX 47) | Spring Substation Washing | For Information Only, Pre-Condition
Syncrude | ML1 (Syncrude Mildred Lake - D05 Syncrude), D05 72kV Bus B | 2019-10-14 08:00 | 2019-10-25 16:00 | N | N | maintenance | Line, Bus |  | ML-1 (72kV) Transmission Line will be isolated to replace power poles between D05 substation and Plant-31 Substation CB 52-76 (At D05) and CB 52-915 (At Plant 31) will be isolated. | Creates Radial Feeds, Firm Load Loss
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2019-10-14 09:00 | 2019-10-14 17:00 | Y | Y | Required to apply phasing sticks and connect 3 spans of conductor on the bypass around EFT | Line | Peak RC outage ID: 1-00681541 |  | Limits ATC, Firm Load Loss, Creates Radial Feeds
ALTALINK | 953s T1 (953s Lake Louise) | 2019-10-14 09:00 | 2019-10-16 17:00 | N | N | installing bird coverup and reverting relay to become T1 'S' protection | Transformer | 953s T1 (953s Lake Louise) |  | For Information Only
ALTALINK | 928L (17s Benalto - 42s Sarcee), 17s 8 (17s Benalto), 17s 9 (17s Benalto) | 2019-10-14 09:30 | 2019-10-25 16:30 | N | Y | replace 17s9 breake | Line, Circuit Breaker | 928L (17s Benalto - 42s Sarcee) | Replace 17s9 breaker, and breaker control and fail module. Replace control module for 17s928X, trip test to 17s8 from new 17s9 breaker control fail module. Operate s928X. | 240 kV, Contingency Requires Mitigation
BCH | 1L274 (1D2L274 - 1D3L274) | 2019-10-15 | 2019-10-15 04:00 | N | Y | install temporary station by-pass for replacement of EFT 1D21 | Line |  |  | Pre-Condition, Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
EPCOR | 72RS5 (Rossdale - Strathcona), Strathcona T1 (Strathcona) | 2019-10-15 06:00 | 2019-10-17 18:00 | N | N | doble and installation of gantry foundations | Line, Transformer | 72RS5 (Rossdale - Strathcona) | Doble @ Strathcona and Rossdale Install new gantry foundations at Strathcona S/S | Creates Radial Feeds, Firm Load Loss
ATCO | 6L73 (729s Otauwau - 745s Slave Lake), 729s 702T (729s Otauwau), 7L162 (732s Mitsue - 729s Otauwau) | 2019-10-15 07:00 | 2019-10-24 17:00 | N | N | replace 702T and 144 kV bus structures | Line, Transformer | 729s 702T (729s Otauwau), 6L73 (729s Otauwau - 745s Slave Lake), 7L162 (732s Mitsue - 729s Otauwau) | Replace 702T and 144 kv bus structures. 702T & PORTION OF 729S 144KV BUS OOS FOR DURATION 729S LOAD RADIAL FED FROM 7L49 OCT 15 Drop section of 144kv bus HOP 2-48165 to create J1 GOI 2-45225 on 702T & 144kv bus OCT 22 GOI 2-45225 & HOP 2-48166 close J1 & shrink zone to only 702T - points 702A (new) & 745S 6L73D1 & 600D1 + PT's NOV 4 Return system to normal | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330P 12TC2 (330p Genesee), 330p 809 (330p Genesee) | 2019-10-15 07:00 | 2019-10-18 17:00 | N | Y | breaker maintenance | Transformer, Circuit Breaker | 330p 809 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
EPCOR | 987s CDS25 (987s Cloverbar), 987s T1 (987s Clover Bar) | 2019-10-15 07:00 | 2019-10-18 17:00 | N | Y | disconnect aux contacts and doble | Switch, Transformer | 987s T1 (987s Clover Bar) | Disconnect Aux Contacts and Doble | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
ATCO | 7L61 (780s Lubicon - 796s Nipisi), 796s 701 (796s Nipisi) | 2019-10-15 07:00 | 2019-10-25 17:00 | N | N | protection upgrade | Line, Circuit Breaker | 7L61 (780s Lubicon - 796s Nipisi), 796s 701 (796s Nipisi) | Protection upgrade | Creates Radial Feeds, Firm Load Loss
Syncrude | Aurora 22 (Aurora), Aurora 23 (Aurora), TL-2 (Aurora - Aurora) | 2019-10-15 08:00 | 2019-10-19 20:00 | N | N | customer work | Circuit Breaker, Line | TL-2 (Aurora - Aurora) TL-2 Transmission Line Outage (72kV), Fed From Aurora G01 Susbsation. CB 52-22 and 52-23 will be operated |  | For Information Only
ENMAX | 20.1TR (ENMAX 20) | 2019-10-15 08:00 | 2019-10-18 16:00 | N | N | doble test transformer and transformer maintenance | Transformer | 20.1TR (ENMAX 20) |  | For Information Only
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2019-10-15 08:00 | 2019-10-18 16:00 | N | Y | breaker heater retrofit | Line | 23.80L (74s Janet - ENMAX 23) | breaker heater retrofit - 23B138-23.80. Repair 23B138-23.80 Pin hole leak. | Creates Radial Feeds, Firm Load Loss
Syncrude | 72 kV Bus-2 (Aurora), Aurora T-11 | 2019-10-15 08:00 | 2019-10-18 20:00 | N | Y | customer work | Bus, Transformer | Aurora T-11, 72 kV Bus-2 (Aurora) Significant - Bus-2 (72kV) Outage, to suppot TL-2 Outage, At Aurora G01 Susbsation. CB # 52-34, 24, 14 and Isolation switch 52, 34B, 24B and 14B will be operated. Transformer T11 will be de-energized for swtiching purpose only. |  | 240 kV, Contingency Requires Mitigation
SUNCOR | 29PL9-5 (29EDD-1 Millennium - 29EDD-34) | 2019-10-15 08:00 | 2019-10-24 16:25 | N | Y | planned 5 year maintenance | Line | 29PL9-5 (29EDD-1 Millennium - 29EDD-34) | Planned 5 year mtce on lines 29PL9-5 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
Lethbridge | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) | 2019-10-15 08:00 | 2019-10-18 17:00 | N | N | replace 138 kV airbreak 593s9 | Line | 823L (146s Lethbridge MacDonald - 593s Lethbridge Lakeview) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
SUNCOR | 635PT-1036 (635EDD-1001) | 2019-10-15 08:00 | 2019-10-19 18:00 | N | N | Replace secondary bushing gaskets | Transformer | 635PT-1036 (635EDD-1001) |  | For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11), 14.1TR (ENMAX 14), 14.3TR (ENMAX 14) | 2019-10-15 08:00 | 2019-10-15 16:00 | N | N | HV bushing replacement | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 95s T1 (95s Imperal Oil Edmonton) | 2019-10-15 08:15 | 2019-10-18 16:45 | N | N | NGR replacement | Transformer | 95s T1 (95s Imperal Oil Edmonton) | customer requested; NGR replacement | For Information Only
BCH | 5L98 (BCH Nicola - Vaseux Lake) | 2019-10-15 09:00 | 2019-10-18 17:00 | Y | Y | clearance required to replace end of life insulators | Line | 5L98 (BCH Nicola - Vaseux Lake) Peak RC outage ID: 1-00667854 Peak RC path ID: 1-00683257 (E>W, export), 1-00683258 (W>E, import) | Clearance required to replace end of life insulators, install arcing horns and replace marker balls. BC Maintenance does not affect the Alberta ATC | Limits ATC, 500 kV
ALTALINK | 1052L (28s West Brooks - 324s Cassils) | 2019-10-15 09:00 | 2019-10-17 15:00 | N | Y | install new air break control module for 28s289 (289) | Line | 1052L (28s West Brooks - 324s Cassils) | Install new air break control module for 28s289 (289) | 240 kV, Contingency Requires Mitigation
ALTALINK | 84L (35s Rundle - 33s Spray) | 2019-10-15 09:00 | 2019-10-17 18:00 | N | N | structure replacements | Line | 84L (35s Rundle - 33s Spray) | Structure Replacements (Str's Range #2-13) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 199L (268s Whitecourt - 347s Fox Creek) | 2019-10-15 09:00 | 2019-10-21 09:00 | N | Y | maintenance | Line | 199L (347s Fox Creek - Open Point A) | Change 199E breaker control module and 199E line protections to the new control building, Change out 347s7 PT. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2019-10-15 10:00 | 2019-10-18 15:00 | N | N | change out poles | Line | 6L02 (873s Marion Lake - 765s Mannix Mine) | GOI to change out poles | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 426L (194s South Red Deer - 63s Red Deer) | 2019-10-15 10:00 | 2019-10-17 15:00 | N | N | maintenance | Line | 426L (194s South Red Deer - 63s Red Deer) | Migrate and commission all L12  426L at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Remove L12-426L SCADA metering module and install DNP mapping in A87L/L12 protection for SCADA metering.Will require disabling of 426L A and B protections at 194S Red Deer. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 74s T2 (74s Janet) | 2019-10-15 10:15 | 2019-10-30 17:45 | N | Y | maintenance | Transformer | 74s T2 (74s Janet) | 74s T2 reclaim oil, download IDD data, new hydrean sensor, corrosive sulfur mitigation, fix leaks | 240 kV, Contingency Requires Mitigation
ALTALINK | 255s T1 (255s Vulcan) | 2019-10-15 11:00 | 2019-10-25 09:00 | N | N | 25 KV bus 1 alterations, close open point 'C', open point 'D' and open point 'M' | Transformer | 255s T1 (255s Vulcan) | 25KV bus 1 alterations, salvage old 16LS feeder cables, replace old 16LN feeder cables, 389 addition, AMI TX 1B6410U connection. Close Open Point 'C' , Open Point 'D' and Open Point 'M' | For Information Only
ALTALINK | 74s C4 (74s Janet) | 2019-10-15 11:30 | 2019-10-18 16:30 | N | Y | upgrade SCADA equipmen | Shunts | 74s C4 (74s Janet) | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | Pre-Condition
ALTALINK | 739L (14s Devon - 305s Acheson) | 2019-10-15 12:15 | 2019-10-17 17:45 | N | N | component replacements | Line | 739L (14s Devon - 305s Acheson) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ATCO | 7L133 (786s High Level - 828s Sulphur Point) | 2019-10-15 13:00 | 2019-10-18 13:00 | N | Y | 7L133 Pole and Cross-Arm replacement | Line | 7L133 (786s High Level - 828s Sulphur Point) | 7L133 Pole and Cross-Arm replacement | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
AESO-SC | OATI | 2019-10-15 18:00 | 2019-10-15 19:00 | N | N | perform an inter-site transfer business continuity drill | SCInternal |  |  | For Information Only
SUNCOR | 139S Hillridge | 2019-10-16 02:14 | 2019-10-25 06:00 | N | N | equipment repair | Station |  |  | For Information Only
EPCOR | 72KN23 (Namao - Kennedale) | 2019-10-16 06:00 | 2019-10-16 18:00 | N | N | doble testing Namao zone | Line | 72KN23 (Namao - Kennedale) |  | For Information Only
BCH | 1L274 (Britt Creek - 1D4L274) | 2019-10-16 07:00 | 2019-10-17 19:00 | Y | Y | 60CB1 SF6 leak investigation | Line |  |  | Pre-Condition, Overload, Limits ATC, Firm Load Loss, Creates Radial Feeds
CENOVUS | 539s PCB-9203 (539s Sunday Creek), 539s Sunday Creek 240 kV West Bus, 539s PCB-9103 (539s Sunday Creek), 539s PCB-9303 (539s Sunday Creek), 539s PCB-9403 (539s Sunday Creek) | 2019-10-16 07:00 | 2019-10-20 12:00 | N | Y | West bus 5 year maintenance | Circuit Breaker, Bus | 539s Sunday Creek 240 kV West Bus |  | 240 kV
AESO-SC | OATI | 2019-10-16 08:00 | 2019-10-16 16:00 | N | N | performing maintenance on the Bloomington data center load balancers | SCInternal |  |  | For Information Only
ENMAX | 1.84L (ENMAX 1 - ENMAX 5), ENMAX 5 B138-1.84 (ENMAX 5) | 2019-10-16 08:00 | 2019-10-16 16:00 | N | N | 5B138-1.84 circuit modification | Line, Circuit Breaker |  |  | For Information Only
ALTALINK | 161L (255s Vulcan - 504s Queenstown) | 2019-10-16 10:00 | 2019-10-16 13:30 | N | N | Vulcan Area Capacity and reliability: disconnect high side of 470s mobile (P1907) | Line | 161L (255s Vulcan - 504s Queenstown) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 235S Entwistle, 156L (19s Wabamun - 235s Entwistle), 672L (235s Entwistle - 131s Moon Lake), 744L (235s Entwistle - 228s T.M.P.L.Niton), 799L (443s South Mayerthorpe - 235s Entwistle) | 2019-10-16 23:00 | 2019-10-17 06:30 | N | N | 25 kV maintenance, hot spots, transformer maintenance, doble, leaks | Station, Line | 156L (235s Entwistle - 156L 86A), 672L (235s Entwistle - 131s Moon Lake), 744L (235s Entwistle - 744L88C), 799L (443s South Mayerthorpe - 235s Entwistle) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1001 635-752-652 (635EDD-1001), 635EDD-1001 635-752-653 (635EDD-1001) | 2019-10-17 07:00 | 2019-10-17 17:00 | N | N | install upper vent cap on 635PLA-1042C bushings | Circuit Breaker |  |  | For Information Only
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2019-10-17 08:00 | 2019-10-17 18:00 | N | N | urgent line clearance mitigation | Line | 859L (20s Ghost - T793s Horse Creek) | Urgent line clearance mitigation on Structure #17 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635PT-1037 (635EDD-1001) | 2019-10-18 08:00 | 2019-10-20 18:00 | N | N | repair pipe flange leak | Transformer | 635PT-1037 (635EDD-1001) |  | For Information Only
ALTALINK | 874L (522s Cooking Lake - 45s Bretona) | 2019-10-18 15:28 | 2019-11-08 18:00 | N | N | urgent line clearance mitigation on structures #203 & 204 | Line | 874L (522s Cooking Lake - 45s Bretona) | Urgent line clearance mitigation on Structures #203 & 204 November 04 - 08, 2019 (07:00 - 18:00); line was removed from service real time on October 18, 2019 @ 15:28 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 666L (498s Tilley - 28s West Brooks) | 2019-10-19 06:30 | 2019-10-19 13:30 | N | Y | perform IR scan of 892L; requires 892L to be loaded to (min) 30% to line rating | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTAGAS | ALP1 ALP | 2019-10-19 06:30 | 2019-10-19 13:30 | N | N | AltaLink 666L outage | Unit
EPCOR | 330p 803 (330p Genesee) | 2019-10-19 07:00 | 2019-10-19 17:00 | N | N | repair | Circuit Breaker | 330p 803 (330p Genesee)
EPCOR | CV5 (557s Castle Downs - 511s Victoria), 511s Victoria T5 (511s Victoria) | 2019-10-19 07:00 | 2019-11-01 17:00 | N | Y | CV5 240 kV splice/ termination | Line, Transformer | CV5 (557s Castle Downs - 511s Victoria) |  | 240 kV
ALTALINK, EPCOR | 320p Keephills 138kV Bus, 320p T1 (320p Keephills), 320p T4 (320p Keephills), 767L (320p Keephills - 767L167A), 809L (320p Keephills - 510s Sunnybrook), 834L (384s Keystone - 320p Keephills), 400L (320p Keephills - 320p Keephills), 401L (320p Keephills - 320p Keephills) | 2019-10-19 07:00 | 2019-10-20 21:00 | N | Y | replace 138 kV bus PT, replace metering on SS 1/2, 138 kV switch maintenance, AltaLink will put T5 into service to feed 25 kV loads | Bus, Transformer, Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 803s T3 (803s Lambton), 72LH8 (Hardisty - 803s Lambton), 72LS24 (Strathcona - 803s Lambton) | 2019-10-19 07:00 | 2019-10-19 15:00 | N | Y | doble testing at Strathcona, Lambton | Transformer, Line | 72LH8 (Hardisty - 803s Lambton), 72LS24 (Strathcona - 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 2.82L (ENMAX 2 - ENMAX 5), 1.84L (ENMAX 1 - ENMAX 5), 5.7TR (ENMAX 5), 5.5TR (ENMAX 5) | 2019-10-19 08:00 | 2019-10-19 18:00 | N | N | fall substation washing, oil sampling 5.7TR | Line, Transformer | 2.82L (ENMAX 2 - ENMAX 5), 1.84L (ENMAX 1 - ENMAX 5) |  | Pre-Condition
ALTALINK | 349S Stavely | 2019-10-19 08:00 | 2019-10-20 16:30 | N | N | connect 349s4044 breaker and Fortis power cables to the system | Station
EPCOR | 330p Genesee 138kV Bus 1 | 2019-10-20 07:00 | 2019-10-20 17:00 | N | N | doble | Bus | 330p Genesee 138kV Bus 1
Syncrude | MH1 (Aurora - Aurora), Aurora T-11 | 2019-10-20 08:00 | 2019-10-24 14:00 | N | N | line outage | Line, Transformer | MH1 (Aurora - Aurora)
CMH | MH_10L (MH69s2 North Industrial - MHS8 Burnside), MH69_12L (MHS8 Burnside - MH69s6 Riverview) | 2019-10-20 08:00 | 2019-11-04 16:00 | N | N | ISD: Oct 28, 2019. 69kV & 138kV line upgrade | Line |  |  | Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 15.60L (ENMAX 21 - ENMAX 15), 21.4TR (ENMAX 21) | 2019-10-20 08:00 | 2019-10-20 12:00 | N | N | fall substation washing | Line, Transformer | 15.60L (ENMAX 21 - ENMAX 15), 21.61L (ENMAX 21 - ENMAX 34) |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 21 - ENMAX 20), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21) | 2019-10-20 12:00 | 2019-10-20 18:00 | N | Y | fall substation washing | Line, Transformer | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 21 - ENMAX 20), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21) | Fall Substation Washing. Altalink required. Original outage Sept 28th | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.81L (ENMAX 13 - ENMAX 11), 11.1TR (ENMAX 11), 11.4TR (ENMAX 11), ENMAX 13 B138-11.81 (ENMAX 13), ENMAX 11 B138-11.81 (ENMAX 11) | 2019-10-21 02:00 | 2019-10-31 02:00 | N | N | 11.1TR MD replacement and transformer maintenance | Line, Transformer, Circuit Breaker | 11.81L (ENMAX 13 - ENMAX 11), 11.1TR (ENMAX 11), 11.4TR (ENMAX 11) |  | For Information Only
EPCOR | 1098L (Jasper - Poundmaker) | 2019-10-21 07:00 | 2019-10-25 17:00 | N | Y | line maintenance & upgrades | Terminal Equipment | 1098L (805s Jasper - Poundmaker) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72MG16 (Meadowlark - Garneau), Meadowlark MAB3 (Meadowlark), Meadowlark T3 (Meadowlark), Meadowlark M723 (Meadowlark), Meadowlark M724 (Meadowlark) | 2019-10-21 07:00 | 2019-10-25 17:00 | N | N | airbreak replacement | Line, Switch, Transformer, Circuit Breaker | Meadowlark MAB3 (Meadowlark) |  | Firm Load Loss, Pre-Condition
ALTALINK | 418L (20s Ghost - 418L193A) | 2019-10-21 07:00 | 2019-10-22 18:00 | N | N | complete structure change at Structure #109 and repair OHSW at structure #13 | Line | 418L (20s Ghost - 418L193A) |  | Firm Load Loss, Pre-Condition
ALTALINK | 310P T32 (310P Sundance) | 2019-10-21 07:00 | 2019-10-25 16:30 | N | N | maintenance | Transformer | 310P T32 (310P Sundance) |  | 240 kV
EPCOR | 330p Genesee 138kV Bus 2 | 2019-10-21 07:00 | 2019-10-21 17:00 | N | N | doble | Bus | 330p Genesee 138kV Bus 2 |  | Pre-Condition
EPCOR | 987s C1 (987s Clover Bar) | 2019-10-21 07:00 | 2019-10-25 17:00 | N | N | disconnect auxiliary contacts and Doble | Shunts | 987s C1 (987s Clover Bar) |  | For Information Only
ALTALINK | 268s Whitecourt 69 kV bus, 526L (268s Whitecourt - 526DL185), 503L (268s Whitecourt - 323s Whitecourt Power), 268s 503 (268s Whitecourt) | 2019-10-21 07:30 | 2019-10-22 17:00 | N | Y | replace 268s503 and PT2 | Bus, Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 9.80L (ENMAX 31 - ENMAX 9), ENMAX 9 B138-9.80 (ENMAX 9), ENMAX 31 B138-9.80 (ENMAX 31) | 2019-10-21 08:00 | 2019-11-15 16:00 | N | N | flood mitigation by City of Calgary and insulator replacement | Line, Circuit Breaker | 9.80L (ENMAX 31 - ENMAX 9) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 22.1TR (ENMAX 22) | 2019-10-21 08:00 | 2019-11-01 16:00 | N | N | transformer differential panel replacement, install slip over HV CTs, gas relay testing | Transformer | 22.1TR (ENMAX 22) | Transformer differential panel replacement. Install slip over HV CTs. Gas Relay testing. | For Information Only
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2019-10-21 08:00 | 2019-10-23 17:30 | N | N | changing cross-arms | Line | 7L53 (7L53 tap - 706s Irish Creek) | CHANGING CROSS-ARMS | Contingency Requires Mitigation, Over/Under Voltage, Overload
ENMAX | 14.4TR (ENMAX 14) | 2019-10-21 08:00 | 2019-10-30 16:00 | N | N | HV bushing replacement, check reversing switch | Transformer | 14.4TR (ENMAX 14) |  | For Information Only
BCH | 1L275 (799s Coleman - Natal) | 2019-10-21 09:00 | 2019-10-31 17:00 | N | Y | end-of-life structure replacements | Line | 1L275 (799s Coleman - Natal) |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 347s 199E (347s Fox Creek), 199L (268s Whitecourt - 347s Fox Creek) | 2019-10-21 09:00 | 2019-10-24 17:00 | N | N | change breaker control module and line protections | Circuit Breaker, Line |  | Change 199E breaker control module and 199E line protections to the new control building, Change out 347s7 PT. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 723L (69s North Barrhead - 723L133), 69s 723E (69s North Barrhead) | 2019-10-21 09:00 | 2019-10-24 17:00 | N | N | replace B protection | Line, Circuit Breaker |  | Replace the 723L B protection at 69s Barrhead. Crew will be on site from October 15th to October 24th. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
BCH | 2L112 (Nelway - Boundary) | 2019-10-21 09:00 | 2019-10-30 17:00 | N | Y | annual plan request F19, BC maintenance does not affect the Alberta ATC | Line | 2L112 (Nelway - Boundary) Peak RC COS: E-W>1-00684959 Peak RC COS: W-E>1-00684960 BC 2L112 Outage>1-00667853 |  | Limits ATC
ALTALINK | 121s T5 (121s Brooks) | 2019-10-21 09:30 | 2019-10-24 16:00 | N | N | 25 kV: replace 83L U/G cables & Fortis to replace 83L0A with new 83L1 | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 1059L (38s East Edmonton - 803s Lambton) | 2019-10-21 09:30 | 2019-10-25 17:00 | N | Y | line maintenance & upgrades | Line | 1059L (38s East Edmonton - 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2019-10-21 10:00 | 2019-10-21 14:00 | N | Y | FortisAlberta Kananaskis Area Reliability Project: connect high side of 471s mobile (P2023) | Line | P2023 | FortisAlberta Kananaskis Area Reliability Project: Connect high side of 471s mobile. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 6L15 (775s Sullivan Lake - 763s Hanna) | 2019-10-21 10:00 | 2019-10-25 16:00 | N | N | road work and pole resets. | Line | 6L15 (775s Sullivan Lake - 763s Hanna) | East side road work and Pole resets. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 305s T1 (305s Acheson) | 2019-10-21 10:00 | 2019-10-23 17:30 | N | N | 25 kv (305s7) replace 25kV post insulators with 69kV class insulators - 305s8, s9, s10 removal (salvage) | Transformer |  |  | For Information Only
ALTALINK | 914L (87s Gaetz - 63s Red Deer) | 2019-10-21 10:00 | 2019-10-24 10:15 | N | N | RTU and SCADA work | Line |  | Migrate and commission all L5  914L at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission VT-5 alarms. Replace and commission new 63S914N (789) airbreak control module. Salvage L5-914L SCADA metering module. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 632PS (632s Russell) | 2019-10-21 10:15 | 2019-10-25 17:15 | N | N | maintenance, doble, update qualitrol | Transformer |  | Maintain phase shifter transformer, doble test & update qualitrol | Pre-Condition
REDDEER | 194s T2 (194s South Red Deer) | 2019-10-21 11:00 | 2019-11-08 08:00 | N | N | replace control cable | Transformer | 194s T2 (194s South Red Deer) |  | For Information Only
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2019-10-21 12:15 | 2019-10-31 17:45 | N | N | component replacements | Line | 739L (14s Devon - 155s Blackmud) | Component Replacements Str's Range 646-753 including 739L14S Devon West Side South Bay OUT | Creates Radial Feeds, Firm Load Loss
ALTALINK | 115S Mt.Allan | 2019-10-21 13:30 | 2019-11-04 11:30 | N | N | FortisAlberta Kananaskis Area Reliability Project (P2023) | Station |  |  | For Information Only
EPCOR | 330p 1202 (330p Genesee) | 2019-10-22 07:00 | 2019-10-22 17:00 | N | Y | doble | Circuit Breaker | 330p 1202 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
EPCOR | 72CH9 (Hardisty - 987s Clover Bar), Hardisty H724 (Hardisty Epcor), Hardisty H722 (Hardisty Epcor) | 2019-10-22 07:00 | 2019-10-25 17:00 | N | N | disconnect aux contacts and Doble | Line, Circuit Breaker | 72CH9 (Hardisty - 987s Clover Bar) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 64s T1 (64s East Crossfield) | 2019-10-22 08:00 | 2019-11-18 13:00 | N | N | salvage and installations for new station service (P1904) | Transformer | 64s T1 (64s East Crossfield) | Salvage Regulator Bypass switch, Breaker 64s94N and 94L power cables. Installation of 589, connect bus tie cables. Complete New SS installation. | For Information Only
ATCO | 808s 702T (808s Procter & Gamble) | 2019-10-22 08:00 | 2019-10-30 13:26 | N | N | distribution connection project | Transformer | 808s 702T (808s Procter & Gamble) | Distribution Connection Project | Firm Load Loss, Restricts Generation
ATCO | 959S SVC (959s Lanfine) | 2019-10-22 08:00 | 2019-10-23 16:00 | N | Y | repair cooling pump motor #2 | Shunts | 959S SVC (959s Lanfine) | 959S Lanfine SVC Repair Cooling Pump Motor #2 Repair of SVC Cooling Pump Contactors and Cables Station will be offline to allow for work | 240 kV, Pre-Condition
ENMAX | 3.4TR (ENMAX 3) | 2019-10-22 08:00 | 2019-10-23 16:00 | N | N | oil sampling MT, TC | Transformer |  |  | For Information Only
ALTALINK | 1041L (370s North Lethbridge - 554s Travers), 370s 47 (370s North Lethbridge), 370s 51 (370s North Lethbridge) | 2019-10-22 08:30 | 2019-10-30 15:30 | N | Y | replace 370s48 and 370s50 | Line, Circuit Breaker | 1041L (370s North Lethbridge - 554s Travers) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 64s East Crossfield 138kV Bus, 64s East Crossfield 240kV Bus, 64s T1 (64s East Crossfield), 64s T2 (64s East Crossfield) | 2019-10-22 10:00 | 2019-10-22 16:00 | N | Y | test new trips from 64s652 and to test block close from 64s33 | Bus, Transformer |  | Breaker and breaker protection outage for 64s901 and 64s652 (new 138kV bus tie) to test new trips from 64s652 Breaker Protection and to test block closes from MODs 64s33, | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2019-10-22 10:00 | 2019-10-24 17:00 | N | Y | troubleshoot | Shunts | 930s Syn Condenser (930s Arcenciel) | Troubleshoot intermittent high impedance fault to ground on the 13.8Kv bus causing tripping of the Synchronous Condenser. SC is currently unavailable due to this issue | For Information Only, Pre-Condition
ATCO | 939s 901T (939s Livock), 939s 901 (939s Livock), 939s 904 (939s Livock), 7L125 (950s Germain - 939s Livock) | 2019-10-22 13:00 | 2019-10-22 15:00 | N | Y | 240 kV bus -900BS1 work | Transformer, Circuit Breaker, Line | 939s 901T (939s Livock) | Remove a section of the bus pipe between 904 bkr and 901T due to H-Pile heaving and replace it with flexible bus before there is a failure to the bus clamp. Station service for 939S Livock 240KV and 500KV substations will be fed from the Backup generation Germain Substation will be out of service for the duration. | 240 kV, For Information Only, Pre-Condition
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power), 268s 503 (268s Whitecourt) | 2019-10-22 17:00 | 2019-10-25 12:00 | N | Y | replace 268s503 and PT2 | Line, Circuit Breaker |  |  | For Information Only, Pre-Condition, Restricts Generation
ATCO | 7L749 (716s Lloydminister - 7L749D2) | 2019-10-23 04:41 | 2019-10-24 18:00 | N | N | forced outage | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 310P T36 (310p Sundance), 310P T37 (310p Sundance), 767L (310p Sundance - 767L50) | 2019-10-23 06:30 | 2019-10-23 19:30 | N | N | footings for new station service PTs | Transformer, Line |  |  | 240 kV, Pre-Condition
EPCOR | 330p 1204 (330p Genesee) | 2019-10-23 07:00 | 2019-10-23 17:00 | N | Y | doble | Circuit Breaker | 330p 1204 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 791s 702T (791s Rainbow Lake), 791s 701T (791s Rainbow Lake) | 2019-10-23 08:00 | 2019-11-06 16:00 | N | N | 791s702T decommission Oct 30, 2019, 791s701T relocate to 702T position. | Transformer
ALTALINK | 28s R1 (28s West Brooks), 28s T1 (28s West Brooks), 28s 240kV Bus 1 (28s West Brooks) | 2019-10-23 08:30 | 2019-10-25 15:00 | N | Y | install new air break control module for 28s15 (89) | Shunts, Transformer, Bus |  | Install new air break control module for 28s15 (89) | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 939s 903T (939s Livock) | 2019-10-23 10:00 | 2019-10-24 15:00 | N | Y | top up oil and leak repair on tap-changer piping | Transformer | 939s 903T (939s Livock) | Top up oil and leak repair on Tap-changer piping | 240 kV, Pre-Condition
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-10-23 11:00 | 2019-10-23 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 6L09 (763s Hanna - 776s Richdale) | 2019-10-23 13:00 | 2019-10-29 13:00 | N | N | cross arm replacement | Line | 6L09 (763s Hanna - 776s Richdale) | 6L09 Crossarm Replacement Construction HANNA 763S TO OYEN 767S | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
AESO-SC | OATI | 2019-10-23 17:00 | 2019-10-23 19:00 | N | N | performing maintenance on the Bloomington data center load balancers | SCInternal |  |  | For Information Only
EPCOR | 330p 1209 (330p Genesee) | 2019-10-24 07:00 | 2019-10-24 17:00 | N | Y | doble | Circuit Breaker | 330p 1209 (330p Genesee) |  | 500 kV
ATCO | 740s 702T (740s H.R.Milner) | 2019-10-24 08:00 | 2019-11-07 16:00 | N | N | transformer replacement ISD Oct 31, 2019 (capital maintenance) | Transformer
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-10-24 09:00 | 2019-10-24 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 6L73 (729s Otauwau - 745s Slave Lake), 729s 702T (729s Otauwau) | 2019-10-24 17:01 | 2019-11-16 17:00 | N | N | replace 702T and 144 kV bus structures | Line, Transformer | 729s 702T (729s Otauwau), 6L73 (729s Otauwau - 745s Slave Lake), 7L162 (732s Mitsue - 729s Otauwau) | Replace 702T and 144 kv bus structures. 702T & PORTION OF 729S 144KV BUS OOS FOR DURATION 729S LOAD RADIAL FED FROM 7L49 OCT 15 Drop section of 144kv bus HOP 2-48165 to create J1 GOI 2-45225 on 702T & 144kv bus OCT 22 GOI 2-45225 & HOP 2-48166 close J1 & shrink zone to only 702T - points 702A (new) & 745S 6L73D1 & 600D1 + PT's NOV 4 Return system to normal | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 526L (526L220 - 526L365) | 2019-10-25 07:15 | 2019-10-25 17:45 | N | N | urgent repair on 526L structure # 352  repair damaged conductor | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 64s T3 (64s East Crossfield) | 2019-10-25 08:00 | 2019-11-08 16:00 | N | N | P1904 ISD Nov 1, 2019 | Transformer
FORTIS | Signalta Coaldale | 2019-10-25 08:00 | 2019-11-08 16:00 | N | N | G1 & G2 engergization. ISD: Nov 01, 2019. | Unit
ALTALINK | 255sT2 (255s Vulcan), 349S Stavely | 2019-10-25 08:00 | 2019-11-08 16:00 | N | N | P1907 ISD: Nov 01, 2019. capacity increase (new 255sT2 and 349s 25 kV 4044L feeder), P1907 ISD: Nov 01, 2019. capacity increase (new 255sT2 and 349s 25 kV 4044L feeder) | Transformer, Station
ALTALINK | 17s C1 (17s Benalto) | 2019-10-25 08:00 | 2019-10-25 10:00 | N | N | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | Shunts |  |  | 240 kV, Pre-Condition
PCLP | CRR2 Castle Rock Ridge 2 | 2019-10-25 08:00 | 2020-03-29 16:00 | N | N | P462. 29 MW wind. ISD Mar 22, 2020 | Unit
ALTALINK | 17s 13 (17s Benalto) | 2019-10-25 11:00 | 2019-10-25 13:30 | N | N | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ALTALINK | 17s 4 (17s Benalto) | 2019-10-25 14:30 | 2019-10-25 16:30 | N | N | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap), 6L12 (6L25 tap - 774s Monitor) | 2019-10-25 17:00 | 2019-10-26 16:00 | N | N | forced outage due to broken pole | Line |  | Change Arms Insulators fiberglass to wood NO STUDY SENT YET | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
SUNCOR | 139S Hillridge | 2019-10-26 | 2019-10-28 14:45 | N | N | equipment repair | Station |  |  | For Information Only
ALTALINK | 226S Garden City | 2019-10-26 00:01 | 2019-10-30 13:26 | N | N | network connection repair | Station |  |  | For Information Only
ATCO | 740s 705 (740s H.R. Milner) | 2019-10-26 08:00 | 2019-10-26 10:00 | N | N | perform commissioning tests of new 700 bus 2 differential protection | Circuit Breaker |  | 740S 705 required OOS for approx 2hrs to perform commissioning tests of new 700 BUS 2 differential protection Will be required to operate the breaker 7L80 to remain in service - 700 breaker to supply back up line protection | For Information Only
ALTALINK | 17s23 (17s Benalto), 17s 3 (17s Benalto) | 2019-10-26 08:00 | 2019-10-26 10:00 | N | Y | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | Switch, Circuit Breaker | 17s23 (17s Benalto) | Cutover Breaker Fail Trip from old 17s9 Protection to new Protection and complete Functional Trip Test | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 740s 704 (740s H.R. Milner) | 2019-10-26 10:00 | 2019-10-26 12:00 | N | N | perform commissioning tests of new 700 bus 2 differential protection | Circuit Breaker |  | 740S 704 required OOS for approx 2hrs to perform commissioning tests of new 700 BUS 2 differential protection Will be required to operate the breaker 7L20 to remain in service - 700 breaker to supply back up line protection | For Information Only
ALTALINK | 17s43 (17s Benalto), 17s 1652 (17s Benalto) | 2019-10-26 11:00 | 2019-10-26 13:30 | N | Y | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | Switch, Circuit Breaker | 17s43 (17s Benalto) | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 17s 85 (17s Benalto), 17s84 (17s Benalto), 17s T2 (17s Benalto) | 2019-10-26 14:30 | 2019-10-26 16:30 | N | Y | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | Circuit Breaker, Switch, Transformer |  | cutover breaker fail trip from old 17s9 protection to new protection and complete functional trip test | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 13.82L (ENMAX 22 - ENMAX 13), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | 2019-10-27 08:00 | 2019-10-27 18:00 | N | N | fall substation washing | Line, Transformer |  | Fall Substation Washing. SW 84 @ 22 Sub - stiff operation while opening | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 281s T1 (281s Johnson) | 2019-10-27 09:45 | 2019-10-31 13:15 | N | Y | repair leak and testing | Transformer |  |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 740s H.R.Milner 144 kV Main Bus, 740s 703T (740s H.R.Milner) | 2019-10-27 12:00 | 2019-12-20 16:00 | N | Y | rebuild (capital maintenance) | Bus, Transformer | 7L80 (740s H.R.Milner - 857s Kakwaridge) | 740S REBUILD: Replacing 703T & 144KV bus structures Replacing 705PTs & CTs 703T & 700 BUS 2 (MAIN BUS) OOS OCT 21-DEC 20 705 OOS & 7L80 OPEN ENDED NOV 4-11 | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s CC721 (987s Clover Bar), 987s T2 (987s Clover Bar) | 2019-10-28 07:00 | 2019-11-22 06:59 | N | Y | breaker replacement | Circuit Breaker, Transformer | 987s CC721 (987s Clover Bar), 987s T1 (987s Clover Bar) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | 805s J2403 (805s Jasper) | 2019-10-28 07:00 | 2019-10-28 17:00 | N | Y | switch and breaker operation for Nait student demo | Circuit Breaker | 805s J2403 (805s Jasper) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 205s T1 (205s Castle Rock Ridge) | 2019-10-28 08:00 | 2019-11-01 17:00 | N | Y | integration testing | Transformer |  | Customer request. Phase 1 and Phase 2 integration testing | Restricts Generation
SUNCOR | 29PL6-2 (836s Steepbank - 29EDD-55) | 2019-10-28 08:00 | 2019-10-30 13:26 | N | N | line A/B protection upgrades | Line | 29PL6-2 (836s Steepbank - 29EDD-55) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 31.1TR (ENMAX 31) | 2019-10-28 08:00 | 2019-11-12 16:00 | N | N | breaker addition | Transformer | 31.1TR (ENMAX 31) |  | For Information Only
ENMAX | 9.80L (ENMAX 31 - ENMAX 9) | 2019-10-28 08:00 | 2019-11-15 16:00 | N | N | corrective, replace center phase jaw and hotspot repair | Line | 9.80L (ENMAX 31 - ENMAX 9) |  | For Information Only
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2019-10-28 08:00 | 2019-10-30 16:00 | N | N | cap bank maintenance | Shunts | 14.1C (ENMAX 14), 14.2C (ENMAX 14) |  | For Information Only
ENMAX | 41.1TR (ENMAX 41) | 2019-10-28 08:00 | 2019-11-07 16:00 | N | N | transformer differential panel replacement | Transformer | 41.1TR (ENMAX 41) |  | For Information Only
ALTALINK | 635S Rose Valley | 2019-10-28 08:15 | 2019-10-29 17:45 | N | N | breaker replacement deficiencies/testing | Station |  |  | For Information Only
ATCO | 7L25 (768s Rowley - 802s Michichi Creek), 802s 707 (802s Michichi Creek) | 2019-10-28 08:30 | 2019-10-29 17:00 | N | N | CT ratio changes | Line, Circuit Breaker | 7L25 (768s Rowley - 802s Michichi Creek), 802s 707 (802s Michichi Creek) | 802S Michichi Creek 7L25 CT Ratio Changes CT Ratio change for Breaker 707 - 7L25. Breaker 707 out of service for duration of work. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 8 (17s Benalto) | 2019-10-28 08:30 | 2019-11-01 16:30 | N | Y | replace breaker control and fail module and remove recloser | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 793s 701T (A793s West Peace) | 2019-10-28 09:00 | 2019-11-01 15:30 | N | N | leak repair, replace VR | Transformer | 793s 701T (A793s West Peace) | Replace 501VRX, Leak Repair on 501VR & 701T, 25kV Load fed from 702T for the duration of the work No Impact to BES | For Information Only
ALTALINK | 28s T1 (28s West Brooks), 28S West Brooks 138kV Bus 1 | 2019-10-28 09:00 | 2019-10-30 08:00 | N | Y | Install new air break control module | Transformer, Bus |  | Install new air break control module for 28s20 (1389) | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 121s T2 (121s Brooks) | 2019-10-28 09:30 | 2019-10-31 16:00 | N | N | replace feeder underground cable | Transformer | 121s T2 (121s Brooks) | replace underground 527L | For Information Only
ALTALINK | 427L (63s Red Deer - 247s Piper Creek), 63s 427 (63s Red Deer) | 2019-10-28 10:00 | 2019-10-31 15:00 | N | N | migrate and commission all line protections | Line, Circuit Breaker |  | Migrate and commission all L18  427L at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Replace and commission L18-427L SCADA metering module. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 37s T3 (37s North Calder) | 2019-10-28 11:00 | 2019-10-28 16:30 | N | N | creating open point to replace switch | Transformer | 37s T3 (37s North Calder) | Creating Open Point 'A' (to replace 37s47) | For Information Only
ALTALINK | 74s C3 (74s Janet), 74s C4 (74s Janet) | 2019-10-28 11:30 | 2019-10-29 17:00 | N | Y | SCADA equipment upgrade | Shunts |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. Work affects 74s104, 74s102 and C3. Need both cap banks for 1.5 day then just C3. | 240 kV, Pre-Condition
ALTALINK | 37s T5 (37s North Calder) | 2019-10-28 16:31 | 2019-11-01 10:00 | N | N | replace switch | Transformer | 37s T5 (37s North Calder) | Replace 37s47 | For Information Only, Pre-Condition
ATCO | 796s 702T (796s Nipisi), 796s 702TCS (796s Nipisi) | 2019-10-29 07:00 | 2019-10-29 17:00 | N | N | tie 700BS1 BF protection into 702TCS logic | Transformer, Circuit Breaker | 796s 702T (796s Nipisi), 796s 702TCS (796s Nipisi) | Tie 700BS1 BF protection into 702TCS logic | For Information Only
ALTALINK | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | 2019-10-29 07:00 | 2019-11-03 17:30 | N | Y | move CT circuit from 205s452 to 205s252 | Line | 1072L (103s Goose Lake - 205s Castle Rock Ridge) | Move CT circuit from 205s452 to 205s252, Trip testing of breakers, Line protection setting changes. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 790L (432s Carvel - 790L57) | 2019-10-29 07:00 | 2019-10-29 17:00 | N | N | urgent P5 trouble corrective change out spar arms and insulation on Str 45 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2019-10-29 08:00 | 2019-11-04 17:00 | N | N | line maintenance | Line | 6L56 (763s Hanna - 802s Michichi Creek) | Line Maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | ENMAX 25 B240-D134 (ENMAX 25), ENMAX 25 B240-D135 (ENMAX 25), ENMAX 25 2GSU-XF-001 (ENMAX 25) | 2019-10-29 08:00 | 2019-11-07 17:00 | N | Y | maintenance on transformer and switches | Circuit Breaker, Transformer | ENMAX 25 2GSU-XF-001 (ENMAX 25) | HV SW maint SW138, SW139, MD maint MD-2GSU. Doble 240kV 25MCT2, 25PT240-Z44. Corrective 25 Sub SW 139 Hot Spot Repair. Substation washing (weather dependant). Replace switch mech SW138, SW139. SEC to assume GOI. | 240 kV, Restricts Generation
Syncrude | 72 kV Bus-2 (Aurora), Aurora T-11 | 2019-10-29 08:00 | 2019-10-31 20:00 | N | Y | support MH-2 transmission line outage | Bus, Transformer | 72 kV Bus-2 (Aurora) | Significant - Bus-2 (72kV) Outage, to suppot MH-2 Transmission Line Outage (72kV), Fed From Aurora G01 Susbsation. CB 52-14, 24 and 34 will be operated. MOD- 52, CB 52-213, 223 at T11 will be operated. | 240 kV, For Information Only
ENMAX | 16.1TR (ENMAX 16) | 2019-10-29 08:00 | 2019-10-29 16:00 | N | N | measurements required in secondary cabinet. | Transformer | 16.1TR (ENMAX 16) |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft) | 2019-10-29 08:00 | 2019-10-30 08:00 | N | N | loading VN21 | Line |  |  | Creates Radial Feeds, Firm Load Loss
Syncrude | MH2 (Aurora - Aurora) | 2019-10-29 08:00 | 2019-11-02 20:00 | N | N | maintenance | Line | MH-2 (Aurora - Aurora) | MH-2 Transmission Line Outage (72kV), Fed From Aurora G01 Susbsation. CB 52-33, 34 and MOD 37 will be operated. | For Information Only
BLACKSPRING | 485s DVAR1 (485s Blacksprings), 485s DVAR2 (485s Blacksprings) | 2019-10-29 09:00 | 2019-10-31 15:00 | N | N | replacement of failed inverter trays on dstatcom | Shunts |  |  | For Information Only
ALTALINK | 183s 445 (183s Underwood), 445L (183s Underwood - 170s Pike) | 2019-10-29 09:00 | 2019-10-29 17:30 | N | N | tank heater repair | Circuit Breaker, Line | 445L (183s Underwood - 170s Pike) |  | For Information Only
ALTALINK | 74s C3 (74s Janet), 74s 102 (74s Janet) | 2019-10-29 16:00 | 2019-10-31 16:30 | N | Y | upgrade SCADA equipment | Shunts, Circuit Breaker |  | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. Work affects 74s102 and C3. Continuation after restoring 74s104 and C4. | 240 kV, Pre-Condition
ENMAX | 39.3TR (ENMAX 39) | 2019-10-30 08:00 | 2019-10-30 16:00 | N | N | oil sampling TC | Transformer |  |  | For Information Only
ALTALINK | 428L (818s Winefred - 167s Ipiatik Lake) | 2019-10-30 08:30 | 2019-10-30 15:30 | N | N | breaker heater repair/replace | Line | 428L (818s Winefred - 167s Ipiatik Lake) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 28s T2 (28s West Brooks), 28s West Brooks 240kV Bus 2 | 2019-10-30 08:30 | 2019-10-31 15:00 | N | Y | install new air break control module for 28s50 | Transformer, Bus |  | install new air break control module for 28s50 (1489) | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 28s 22 (28s West Brooks) | 2019-10-30 14:00 | 2019-10-31 17:00 | N | N | forced outage | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s11 (62s Brazeau) | 2019-10-30 23:00 | 2019-10-31 03:00 | N | Y | maintenance | Switch | 62s11 (62s Brazeau) |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2019-10-31 03:00 | 2019-10-31 07:00 | N | Y | maintenance | Switch | 62s12 (62s Brazeau) |  | Restricts Generation
ALTALINK | 818s 41 (818s Winefred), 818s C3 (818s Winefred) | 2019-10-31 07:30 | 2019-10-31 13:30 | N | N | tank heater repair/replace | Circuit Breaker, Shunts | 818s C3 (818s Winefred) |  | Pre-Condition
ALTALINK | 353s 552 (353s Plamondon), 728L (353s Plamondon - 157s Lac La Biche) | 2019-10-31 07:30 | 2019-10-31 15:00 | N | N | repair/replace tank heater | Circuit Breaker, Line | 728L (353s Plamondon - 157s Lac La Biche) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.7TR (ENMAX 1) | 2019-10-31 08:00 | 2019-10-31 16:00 | N | N | oil sampling HV bushings | Transformer | 1.7TR (ENMAX 1) |  | For Information Only
ENMAX | 34.2TR (ENMAX 34) | 2019-10-31 08:00 | 2019-11-14 16:00 | N | N | transformer replacement. ISD Nov 7, 2019 (capital maintenance) | Transformer
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2019-10-31 10:00 | 2019-10-31 14:00 | N | Y | emergency- replacement of light emitter boards | Line | 13L50 (2029s Heathfield - 2075s Newell) | 2075s LOP 848 Light emitter fault Emergency replacement of Light emitter boards. During Power Direction Change on 13L50, requesting moving from de-blocked to blocked for about 2 hours to replace light emitter boards in VBE Cabinet to clear alarms. 13L50 will be unavailable for transfer during outage | 500 kV, Pre-Condition
ALTALINK | 17s 9 (17s Benalto), 928L (17s Benalto - 42s Sarcee) | 2019-10-31 13:00 | 2019-10-31 16:00 | N | Y | trip test to 17s9 from new 17s8 breaker fail | Circuit Breaker, Line |  |  | 240 kV, Contingency Requires Mitigation
AESO-SC | OATI | 2019-10-31 15:30 | 2019-11-01 06:00 | N | N | adjusting routing for traffic coming in over OATINET in preparation for scheduled provider maintenance | SCInternal |  |  | For Information Only
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2019-11-01 08:00 | 2019-11-01 18:00 | N | N | T1 138 kV bushing and 34 kV arrestor replacement | Transformer | 133s T1 (133s Stelco Edmonton),133s T2 (133s Stelco Edmonton) |  | For Information Only
ALTALINK | 936L (102s Langdon - 5s East Calgary) | 2019-11-01 08:00 | 2019-11-04 16:00 | N | Y | replace insulators on Enmax's portion of line | Line | 936L (102s Langdon - 5s East Calgary) |  | 240 kV, Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), ENMAX 15 B69-15.62 (ENMAX 15), ENMAX 16 B69-15.62 (ENMAX 16) | 2019-11-01 08:00 | 2019-12-06 16:00 | N | N | transmission line clearance restoration | Line, Circuit Breaker | 15.62L (ENMAX 15 - ENMAX 16) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), ENMAX 21 B69-21.61 (ENMAX 21), ENMAX 34 B69-21.61 (ENMAX 34) | 2019-11-01 08:00 | 2019-12-06 16:00 | N | N | transmission line clearance restoration | Line, Circuit Breaker | 21.61L (ENMAX 21 - ENMAX 34) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 58s T1 (58s Edson) | 2019-11-01 08:00 | 2019-11-04 17:00 | N | N | change 58s37 MOD controls to new building | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2019-11-01 08:00 | 2019-11-01 16:00 | N | N | oil sampling TC | Transformer | 1.8TR (ENMAX 1) |  | For Information Only
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2019-11-01 08:00 | 2019-11-01 16:00 | N | Y | replace control module for 17s903N, trip test to 17s7 from new 17s8 breaker fail | Line |  | Replace control module for 17s903N, trip test to 17s7 from new 17s8 breaker fail. Operate s903N. | 240 kV, Contingency Requires Mitigation
FORTIS | COD1 Coaldale | 2019-11-01 08:00 | 2019-11-12 16:00 | N | N | ISD: Nov 05, 2019. 254s DER commissioning. P2010 | Unit
ALTALINK | 37s T3 (37s North Calder) | 2019-11-01 10:01 | 2019-11-01 18:00 | N | N | close open point 'A' (after replacing 37s47) | Transformer | 37s T3 (37s North Calder) |  | For Information Only, Pre-Condition
ENMAX | 31.1C (ENMAX 31) | 2019-11-02 08:00 | 2019-11-02 16:00 | N | N | install ground grid in cap bank yard | Shunts |  |  | For Information Only, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux), 747L (37s North Calder - 711L tap), 898L (37s North Calder - 92s Viscount), 37s North Calder 138kV Bus, 37s T3 (37s North Calder) | 2019-11-02 09:00 | 2019-11-08 15:00 | N | N | replace 138kV switches & T3 tap changer repair, PT maintenance | Line, Bus, Transformer | 726L (37s North Calder - 71s Lamoureux),747L (37s North Calder - 711L tap),898L (37s North Calder - 92s Viscount) |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 9.3TR (ENMAX 9) | 2019-11-04 08:00 | 2019-11-05 16:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2019-11-04 08:00 | 2019-11-15 16:00 | N | N | replace secondary bushings | Transformer | 38.3TR (ENMAX 38) |  | For Information Only
ENMAX | 22.2TR (ENMAX 22) | 2019-11-04 08:00 | 2019-11-15 16:00 | N | N | differential panel replacement, install slip over HV CTs, replace failing ABB (ASEA) selector switches | Transformer | 22.2TR (ENMAX 22) | Transformer differential panel replacemant. Install slip over HV CTs. Replace Failing ABB (ASEA) Selector Switches | For Information Only
ALTALINK | 17s 7 (17s Benalto) | 2019-11-04 08:30 | 2019-11-08 16:30 | N | Y | replace breaker control module | Circuit Breaker | 17s 7 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 28s T2 (28s West Brooks), 28S West Brooks 138kV Bus 2 | 2019-11-04 09:00 | 2019-11-05 16:00 | N | Y | install new air break control module for 28s49 | Transformer, Bus | 28s T2 (28s West Brooks), 28S West Brooks 138kV Bus 2 |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 63s 152 (63s Red Deer), 63s 252 (63s Red Deer), 900L (63s Red Deer - 17s Benalto) | 2019-11-04 10:00 | 2019-11-08 15:00 | N | Y | migrate and commission all L1  900L at 63s to new RTU and LAN | Circuit Breaker, Line | 900L (63s Red Deer - 17s Benalto) | Migrate and commission all L1  900L at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission VT-1 alarms. Replace and commission new 63S900W (389) airbreak control module. | 240 kV, Contingency Requires Mitigation
ALTALINK | 77s 57 (77s Sagitawah) | 2019-11-04 11:00 | 2019-11-05 15:30 | N | Y | 240kV breaker maintenance | Circuit Breaker | 77s 57 (77s Sagitawah) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2019-11-04 11:00 | 2019-11-13 17:00 | N | Y | fire mitigation on structures | Line | 777L (245s Seebe - 48s Pocaterra) | Fire Mitigation Work on Structures #18, 19, 20, 21, 22 ,26, 31, 32, 33, 36, 42, 91, 92, 95, 96, 97, 103, 105, 106, 106A, 111, 112, 113, 116, 117, 119, 121A, 122, 123, 124, 126, 127, 129, 130, 132, 133, 229 and 231. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ALTALINK | 74s 76 (74s Janet) | 2019-11-04 11:30 | 2019-11-07 16:30 | N | N | upgrade SCADA equipments | Circuit Breaker | 74s 76 (74s Janet) | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 87s T2 (87s Gaetz) | 2019-11-04 12:00 | 2019-11-25 18:00 | N | Y | sulphur mitigation | Transformer | 87s T2 (87s Gaetz) | 87s T2 corrosive sulphur mitigation | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale) | 2019-11-04 13:00 | 2019-11-06 18:00 | N | N | crossarm replacement construction | Line | 6L09 (763s Hanna - 776s Richdale) | 6L09 Crossarm Replacement Construction | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 255sT2 (255s Vulcan) | 2019-11-05 08:00 | 2019-11-06 14:00 | N | N | install bird cover-up | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 937L (102s Langdon - 5s East Calgary) | 2019-11-05 08:00 | 2019-11-08 16:00 | N | Y | replace insulators on Enmax's portion of line | Line | 937L (102s Langdon - 74s Janet) |  | 240 kV, Pre-Condition
RVLP | RIV1 Riverview | 2019-11-05 08:00 | 2020-05-08 16:00 | N | N | P524. 105 MW wind. ISD Apr 18, 2020 | Unit
ATCO | 808s 701T (808s Procter & Gamble) | 2019-11-05 08:00 | 2019-11-11 16:00 | N | N | distribution connection project | Transformer | 808s 701T (808s Procter & Gamble) | Distribution Connection Project | Firm Load Loss, Pre-Condition, Restricts Generation
AESO-SC | Northwestern Energy BUCC test | 2019-11-05 08:00 | 2019-11-05 12:00 | N | N | Backup Control Center (BUCC) test | Station |  |  | Affects Visibility
ENMAX | 25PT240-Z41 (ENMAX 25), ENMAX 25 B240-D131 (ENMAX 25), ENMAX 25 B240-D134 (ENMAX 25), ENMAX 25 B240-D138 (ENMAX 25), ENMAX 25 B240-D140 (ENMAX 25), ENMAX 25 240kV South Bus | 2019-11-05 08:00 | 2019-11-07 18:00 | N | Y | switch maintenance | Terminal Equipment, Circuit Breaker, Bus |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 115s T2 (115s Mt.Allan) | 2019-11-05 09:00 | 2019-12-06 14:00 | N | N | FortisAlberta Kananaskis Area Reliability Project (P2023) | Transformer | 115s T2 (115s Mt.Allan), P2023 | FortisAlberta Kananaskis Area Reliability Project:Salvage 115s11 Disconnect and 115s14 Grounding Switch.Install new 138KV 252 Breaker, Install new High Bay, Install new 25KV 652, 752 Breakers, Install new High Bay ,Install new VT2 and CTs, Install relocated VR,Install SS2, Connect AMI 25kV Injection and Connect Bus Tie Conductor. | For Information Only
ATCO | 840s 504 (840s McNeill) | 2019-11-05 09:00 | 2019-11-05 17:00 | N | Y | FA2 filter bay emergency inspections | Circuit Breaker |  | 840S McNeill FA2 Filter Bay Emergency Inspections We have been getting Filter capacitor unbalance alarms and 49 O/L alarms and BKR trips occurring in filter bay. Remove bay from service and inspect and test capacitor wafers. Replace as needed. With Filter O/S Station Transfer Limited to 90MW | Limits ATC, Pre-Condition
ATCO | 851s 701T (851s Morse River) | 2019-11-05 10:00 | 2019-11-07 14:00 | N | N | repair oil leaks | Transformer |  | Repair Leaks - Oil is to be drained and bushing gaskets to be replaced. All Substation load to be transferred to other locations through the distribution system. Substation station service to stay on by back feeding through a feeder breaker. previous repair did not work. need to redo the gaskets with a thicker material. Oil is to be drained and bushing gaskets to be replaced. Leak is substantial needs repairs quickly | For Information Only
ALTALINK | 77s 54 (77s Sagitawah) | 2019-11-05 15:30 | 2019-11-06 15:00 | N | Y | breaker maintenance | Circuit Breaker | 77s 54 (77s Sagitawah) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 28s 81 (28s West Brooks) | 2019-11-05 16:00 | 2019-11-06 12:00 | N | N | forced outage | Circuit Breaker |  |  | Pre-Condition
ENMAX | 9.2TR (ENMAX 9) | 2019-11-06 08:00 | 2019-11-07 16:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
ALTALINK | 899L (166s Dow Chemical Fort Saskatchewan - 218s Fort Saskatchewan Co-Gen), 166s8 (166s Dow Chemical Fort Saskatchewan) | 2019-11-06 08:00 | 2019-11-07 17:00 | N | Y | P&C work on 166s899N, confirm 166s24 closed properly | Line, Switch |  | P&C work on 166s899N, confirm 166s24 closed properly | Pre-Condition, Restricts Generation
ALTALINK | 678s T1 (678s Okotoks) | 2019-11-06 08:30 | 2019-11-06 16:30 | N | N | relay maintenance | Transformer
ATCO | 840s 505 (840s McNeill) | 2019-11-06 09:00 | 2019-11-06 17:00 | N | Y | FA3 filter bay emergency inspections | Circuit Breaker |  | 840S McNeill FA3 Filter Bay Emergency Inspections We have been getting Filter capacitor unbalance alarms and 49 O/L alarms and BKR trips occurring in filter bay. Remove bay from service and inspect and test capacitor wafers. Replace as needed. With Filter O/S Station Transfer Limited to 90MW | Limits ATC
ALTALINK | 763L (28s West Brooks - 763L257A) | 2019-11-06 12:01 | 2019-11-07 15:00 | N | N | install new air break control module for 28s763X (889) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 77s 51 (77s Sagitawah) | 2019-11-06 15:00 | 2019-11-07 16:30 | N | Y | 240 kV breaker maintenance | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAXGPI, ENMAXEC | 134S Taber Wind Farm, 383S Kettles Hill Windfarm | 2019-11-07 07:00 | 2019-11-07 14:00 | N | Y | upgrading PI system | Station |  |  | For Information Only
ALTALINK | 135s T1 (135s Conrad) | 2019-11-07 08:00 | 2019-11-07 15:00 | N | N | bird cover up installation on 25 kV bus 1 | Transformer | 135s T1 (135s Conrad) | Bird Cover Up Installation On 25kV Bus 1 | For Information Only
ATCO | 6L09 (772s Youngstown - 776s Richdale) | 2019-11-07 08:00 | 2019-11-10 13:00 | N | N | crossarm replacement construction | Line | 6L09 (772s Youngstown - 776s Richdale) | 6L09 Crossarm Replacement Construction | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALC | ALS1 Air Liquide Scotford #1 | 2019-11-07 08:00 | 2019-11-21 16:00 | N | N | P2202. 9.9 MW ISD Nov 14, 2019 | Unit
ALTALINK | 17s57 (17s Benalto) | 2019-11-07 08:00 | 2019-11-07 09:30 | N | Y | trip test | Switch | 17s57 (17s Benalto) | trip test 17s11 from new 17s7 breaker control and fail module | 240 kV, Contingency Requires Mitigation
ALTALINK | 650s 752 (650s Hansman Lake) | 2019-11-07 08:30 | 2019-11-07 14:30 | N | Y | breaker maintenance, gas leak | Circuit Breaker |  | 240 kV breaker maintenance, gas leak | 240 kV, Contingency Requires Mitigation
ALTALINK | 67s 2 (67s Stirling), 67s T2 (67s Stirling), 820L (67s Stirling - 820AL tap) | 2019-11-07 09:00 | 2019-11-07 13:00 | N | Y | mobile connection | Circuit Breaker, Transformer, Line | 820L (67s Stirling - 820AL tap) | to connect Mobile. (Close Open Point A), line crew to perp for 67s Open Point D, test energize 475s and phase across 67s18. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 17s26 (17s Benalto) | 2019-11-07 09:30 | 2019-11-07 11:30 | N | Y | trip test | Switch | 17s26 (17s Benalto) | Trip test 17s6 from new 17s7 breaker control and fail module | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 17s31 (17s Benalto) | 2019-11-07 12:00 | 2019-11-07 13:30 | N | Y | trip test | Switch | 17s31 (17s Benalto) | Trip test 17s1 from new 17s7 breaker control and fail module | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | AL-1 (D05 Syncrude - Aurora), D05 T1 (D05 Syncrude), D05 517 (D05 Syncrude), D05 519 (D05 Syncrude), D05 511 (D05 Syncrude), D05 71 (D05 D05) | 2019-11-08 08:00 | 2019-11-20 13:00 | N | Y | substation outage | Line, Transformer, Circuit Breaker | D05 511 (D05 Syncrude), D05 510 (D05 Syncrude), D05 520 (D05 Syncrude), D05 517 (D05 Syncrude), D05 519 (D05 Syncrude), D05 T1 (D05 Syncrude), AL-1 (D05 Syncrude - Aurora) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 7.1TR (ENMAX 7) | 2019-11-08 08:00 | 2019-11-08 12:00 | N | N | 7.1TR LTC low oil level - need to adjust oil level | Transformer |  |  | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 34.1TR (ENMAX 34) | 2019-11-08 08:00 | 2019-11-08 16:00 | N | N | 34.2TR replacement, test autoswitching scheme | Line, Transformer | Capital maintenance (confirmed with OPTRA Sept 20, 2019 V.Chan). | 34.2TR replacement. Test Autoswitching scheme. 21.61L oos | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 2L294 (Cranbrook - A.A. Lambert) | 2019-11-08 08:30 | 2019-11-08 17:00 | N | Y | replace vandalism damaged insulators | Line |  |  | Limits ATC, Pre-Condition
ALTALINK | 17s42 (17s Benalto) | 2019-11-08 14:00 | 2019-11-08 15:30 | N | Y | trip test 17s10 from new 17s7 breaker control and fail module | Switch | 17s42 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 17s46 (17s Benalto), 17s T3 (17s Benalto) | 2019-11-08 15:30 | 2019-11-08 17:00 | N | Y | trip test 17s2852 from new 17s7 breaker control and fail module | Switch, Transformer | 17s T3 (17s Benalto) |  | 240 kV
ALTALINK | 17s 8 (17s Benalto), 903L (17s Benalto - 320p Keephills) | 2019-11-08 17:30 | 2019-11-08 19:00 | N | Y | trip test 17s8 from new 17s7 breaker control and fail module | Circuit Breaker, Line | 17s 8 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 37.81L (ENMAX 38 - ENMAX 37), ENMAX 38 B138-37.81 (ENMAX 38) | 2019-11-10 08:00 | 2019-11-10 18:00 | N | N | substation washing. repair hotspot | Line, Circuit Breaker | 37.81L (ENMAX 38 - ENMAX 37) | substation washing. repair hotspot 38B138-37.81 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 6.80L (ENMAX 35 - ENMAX 6), 6.4TR (ENMAX 6) | 2019-11-11 08:00 | 2019-11-11 12:00 | N | N | RTU upgrade | Line, Transformer | 6.80L (ENMAX 35 - ENMAX 6) | RTU upgrade. Commissioning OAC/CAC Control center will have no control on equipment. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-11-11 08:30 | 2019-11-11 12:00 | N | N | SF6 top-up | Line | 1.81L (ENMAX 20 - ENMAX 1) | SF6 Top-up 20B138-1.81L. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 6.82L (ENMAX 6 - ENMAX 41), 6.1TR (ENMAX 6) | 2019-11-11 12:00 | 2019-11-11 16:00 | N | N | RTU upgrade | Line, Transformer | 6.82L (ENMAX 6 - ENMAX 41) | RTU upgrade. Commissioning OAC/CAC Control center will have no control on equipment. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | Rossdale RW727 (Rossdale), 72RW3 (Rossdale - Woodcroft) | 2019-11-12 07:00 | 2019-12-06 17:00 | N | N | breaker replacement | Circuit Breaker, Line | Rossdale RW727 (Rossdale) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 6L05 (764s Heisler - 6L05 tap) | 2019-11-12 08:00 | 2019-11-14 17:00 | N | N | pole changes | Line | 6L05 (764s Heisler - 6L05 tap) | Pole Changes | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 3.3TR (ENMAX 3) | 2019-11-12 08:00 | 2019-11-13 18:00 | N | N | neutral reactor installation | Transformer |  |  | For Information Only
ENMAX | 9.1TR (ENMAX 9) | 2019-11-12 08:00 | 2019-11-13 16:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
ATCO | 6L09 (772s Youngstown - 776s Richdale) | 2019-11-12 08:00 | 2019-11-15 17:00 | N | N | line maintenance | Line |  | Line Maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 853L (28s West Brooks - 853L75) | 2019-11-12 09:00 | 2019-11-14 15:00 | N | N | install new air break control module for 28s853W (689) | Line | 853L (28s West Brooks - 853L75) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER | 209s T1 (209s Timberlands) | 2019-11-12 09:00 | 2019-11-26 15:30 | N | N | oil leak welding repairs | Transformer | 209s T1 (209s Timberlands) | power transformer 209S oil leak welding repairs | For Information Only
ALTALINK | 347s 720X (347s Fox Creek), 720L (347s Fox Creek - 397s Benbow) | 2019-11-12 09:30 | 2019-11-12 17:30 | N | N | work on new 138 kV bus protection, connect CT circuit and trip test, work on new 138 kV bus protection, connect CT circuit and trip test | Circuit Breaker, Line | 720L (347s Fox Creek - 397s Benbow) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 63s 252 (63s Red Deer), 63s 352 (63s Red Deer), 925L (63s Red Deer - 74s Janet) | 2019-11-12 10:00 | 2019-11-14 15:00 | N | Y | migrate and commission all L6  925L at 63s to new RTU and LAN | Circuit Breaker, Line | 925L (63s Red Deer - 74s Janet) | Migrate and commission all L6  925L at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission VT-6 alarms. Replace and commission new 63S925X (489) airbreak control module. | 240 kV, Contingency Requires Mitigation
ALTALINK | 898L (37s North Calder - 92s Viscount) | 2019-11-12 10:30 | 2019-11-13 18:00 | N | N | change to post insulators and replace U/B arms STR 19, 22 & 29 (ULCM work on 898L) | Line | 898L (37s North Calder - 92s Viscount) | ULCM Work on 898L (PRIORITY 5)  change to post insulators and replace U/B arms STR 19, 22 & 29 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX, ALTALINK | 37.82L (74s Janet - ENMAX 37) | 2019-11-12 11:00 | 2019-11-15 17:00 | N | Y | SCADA equipment upgrade | Line | 37.82L (74s Janet - ENMAX 37) | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 67s Stirling 69 kV Bus 1, 225L (67s Stirling - 225s Magrath), 67s T1 (67s Stirling) | 2019-11-12 11:00 | 2019-12-17 14:00 | N | Y | create open points C and D, connect mobile and replace 69 kV equipment | Bus, Line, Transformer | 225L (67s Stirling - 225AL tap) | Mobile connected and carrying load. DG will be off-line. replace 67a508x breaker, Install new L1 and L2 21kV line arrestors, Remove existing 69kV disconnect on top of 69kv Bay, Remove SS1 transformer, Remove 69kV Bus Arrestors next to VT1, Replace existing hookswitches 67s11, 67s95, 67s224, Replace existing crossings arms for 67s11, 67s12, 67s95, 67s224, 69s226, Replace PTs 1247 and 1248 at 67s14, Replace various 69KV insulators, Replace circuit switcher 67s31 with new breaker and Relocate all existing P&C equipment from Building 1 to Buildings 2 and 3. | Creates Radial Feeds, Restricts Generation
ALTALINK | 58s Edson 138kV East Bus, 202L (58s Edson - 178s Cynthia), 740L (58s Edson - 39s Bickerdike), 58s T1 (58s Edson) | 2019-11-12 11:00 | 2019-11-20 09:00 | N | N | move devices to new building, replace devices and install new devices | Bus, Line, Transformer | 740L (58s Edson - 39s Bickerdike) | Move 58s1 to the new building, install new strain insulators on 58s9, replace switches 58s33, and 58s201, move protection and control for 58s202X, move the 58s17 PT distribution to the new building, Replace 58s17 PTs. | Over/Under Voltage, Pre-Condition
ALTALINK | 671L (58s Edson - 39s Bickerdike) | 2019-11-12 11:25 | 2019-11-12 11:45 | N | N | upload temporary settings to 58s 671L/B87/21/79 & 58s 671L/B87/21/79 relays due to 138kV Bus PT removed from service | Line
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2019-11-13 07:00 | 2019-11-13 17:00 | N | N | mine shutdown | Line | 8L10 (330P Genesee - Fording Coal Mine) |  | For Information Only
ALTALINK | 432s 790 (432s Carvel), 790L (432s Carvel - 790L57) | 2019-11-13 07:30 | 2019-11-13 17:30 | N | N | densimeter requires replacement | Circuit Breaker, Line | 790L (432s Carvel - 790L57) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 54 (74s Janet), 74s C1 (74s Janet) | 2019-11-13 08:00 | 2019-11-13 17:00 | N | N | maintain 138 kV SF6 cap bank breaker | Circuit Breaker, Shunts | 74s 54 (74s Janet), 74s C2 (74s Janet) |  | Pre-Condition
ALTALINK | 84L (35s Rundle - 33s Spray) | 2019-11-13 08:00 | 2019-11-13 15:00 | N | N | Changing insulator on Structure #13 | Line | 84L (35s Rundle - 33s Spray) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 347s 199E (347s Fox Creek), 199L (347s Fox Creek - 199L187A) | 2019-11-13 08:30 | 2019-11-13 17:30 | N | Y | work on new 138 kV bus protection & connect CT circuit and trip test | Circuit Breaker, Line | 347s 199E (347s Fox Creek), 199L (347s Fox Creek - 199L187B) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 734s 701T (734s Sturgeon) | 2019-11-13 09:00 | 2019-12-15 16:00 | N | N | investigate gas relay trip | Transformer | 734s 701T (734s Sturgeon) | Investigate 701T gas relay trip from Oct 26, Transformer currently OOS Oil samples showed no gassing, suspect problem with relay 701T is hot standby unit and normally does not carry any load Also will be checking 701 heaters | For Information Only
ALTALINK | 512s T1 (512s Hartell) | 2019-11-13 09:30 | 2019-11-14 12:30 | N | N | fix leaks in transformer | Transformer | 512s T1 (512s Hartell) |  | For Information Only
ALTALINK | 38s 3152 (38s East Edmonton), 38s C2 (38s East Edmonton) | 2019-11-13 10:30 | 2019-11-13 13:30 | N | N | low gas - centre phase | Circuit Breaker, Shunts | 38s C2 (38s East Edmonton) |  | Pre-Condition
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2019-11-13 16:30 | 2019-11-14 01:42 | N | N | forced outage | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 310p T30 (310p Sundance), 310P T33 (310P Sundance), 310P 3352 (310p Sundance), 310P 512N (310p Sundance), 310P 234N (310p Sundance) | 2019-11-14 07:00 | 2019-11-20 19:00 | N | Y | replace bus protection | Transformer, Circuit Breaker | 310p T30 (310p Sundance) | Replace 69 kV Bus Diff prot., Place donut CTs on T30 for new 240 protection. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 92s 792 (92s Viscount), 792L (191s N.W. Cardiff - 92s Viscount) | 2019-11-14 07:30 | 2019-11-14 17:30 | N | N | o-ring replacement | Circuit Breaker, Line | 792L (191s N.W. Cardiff - 92s Viscount) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 3.4TR (ENMAX 3) | 2019-11-14 08:00 | 2019-11-15 18:00 | N | N | neutral reactor Installation | Transformer |  |  | For Information Only
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-11-14 08:30 | 2019-11-14 12:00 | N | N | SF6 top-up | Line | 1.81L (ENMAX 20 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 347s 199W (347s Fox Creek), 199L (347s Fox Creek - 741s Fox Creek) | 2019-11-14 08:30 | 2019-11-14 17:30 | N | Y | bus protection work | Circuit Breaker, Line | 347s 199W (347s Fox Creek), 199L (347s Fox Creek - 741s Fox Creek) | work on new 138 kV Bus protection. Connect CT circuit and trip test | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 256s C1 (256s Harmattan) | 2019-11-14 09:30 | 2019-11-14 12:30 | N | N | get rid of weeds | Shunts | 256s C1 (256s Harmattan) |  | For Information Only
EPCOR | 987s Cloverbar 72kV Bus 1, 72CN10 (987s Clover Bar - Namao), 987s T2 (987s Clover Bar) | 2019-11-15 23:00 | 2019-11-17 23:00 | N | Y | auxiliary contacts and doble | Bus, Line, Transformer | 72CN10 (987s Clover Bar - Namao) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2019-11-16 08:00 | 2019-11-18 17:00 | N | N | line maintenance | Line | 6L09 (767s Oyen - 6L21 tap) | Line Maintenance | Creates Radial Feeds, Firm Load Loss
ENMAX | 32.83L (ENMAX 32 - ENMAX 40), 40.1TR (ENMAX 40) | 2019-11-16 08:00 | 2019-11-16 13:00 | N | N | hotspot on SW85 at 40 sub, check reversing switch | Line, Transformer | 32.83L (ENMAX 32 - ENMAX 40) |  | Firm Load Loss
ENMAX | 7.84L (ENMAX 36 - ENMAX 7) | 2019-11-16 08:00 | 2019-11-17 16:00 | N | N | doble test , breaker inspection | Line | 7.84L (ENMAX 36 - ENMAX 7) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 40.2TR (ENMAX 40) | 2019-11-16 13:00 | 2019-11-16 18:00 | N | N | switch adjustment/maintenance, check reversing switch | Line, Transformer | 40.81L (ENMAX 40 - ENMAX 41) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 793s 701T (A793s West Peace) | 2019-11-17 07:00 | 2019-11-22 17:00 | N | N | forced outage from gassing trip | Transformer
ENMAX | 24.82L (ENMAX 65 - ENMAX 24), 24.2TR (ENMAX 24) | 2019-11-17 08:00 | 2019-11-17 18:00 | N | N | switch maintenance, check reversing switch | Line, Transformer | 24.2TR (ENMAX 24),24.82L (ENMAX 65 - ENMAX 24)
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-11-17 08:30 | 2019-11-17 12:00 | N | N | SF6 top-up | Line | 1.81L (ENMAX 20 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.1TR (ENMAX 11) | 2019-11-18 02:00 | 2019-11-22 02:00 | N | N | replace HV CTs | Transformer | 11.1TR (ENMAX 11) |  | For Information Only
EPCOR | 52s T1 (52s East Industrial), 1059AL (52s East Industrial - 1059L tap) | 2019-11-18 07:00 | 2019-11-21 17:00 | N | Y | CVT replacement | Transformer, Line | 52s T1 (52s East Industrial) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | Kennedale K721 (Kennedale), 72CK13 (987s Clover Bar - Kennedale) | 2019-11-18 07:00 | 2019-11-20 17:00 | N | N | cutover of new BF protection | Circuit Breaker, Line | Kennedale K721 (Kennedale) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | Rossdale T2 (Rossdale) | 2019-11-18 07:00 | 2019-11-22 17:00 | N | N | wildlife covering installation | Transformer | Rossdale T2 (Rossdale) |  | For Information Only
ALTALINK | 54L (118s Canmore - 54L172) | 2019-11-18 07:00 | 2019-11-22 18:00 | N | N | urgent fire mitigation | Line | 54L (118s Canmore - 54L172) | Urgent fire mitigation between Structures #139 - 168 | Creates Radial Feeds, Firm Load Loss
ATCO | 729s 705 (729s Otauwau), 7L49 (732s Mitsue - 729s Otauwau) | 2019-11-18 08:00 | 2019-11-20 16:00 | N | N | Breaker 705 Maintenance, 7L49 open ended @ 729S Otauwau | Circuit Breaker, Line | 7L49 (732s Mitsue - 729s Otauwau) | Breaker 705 Maintenance, 7L49 open ended @ 729S Otauwau | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 31.2TR (ENMAX 31) | 2019-11-18 08:00 | 2019-11-19 18:00 | N | N | neutral reactor installation | Transformer | 31.2TR (ENMAX 31) |  | For Information Only
ALTALINK | 814L (121s Brooks - 28s West Brooks) | 2019-11-18 08:00 | 2019-11-21 16:00 | N | N | replace 28s814E | Line | 814L (121s Brooks - 28s West Brooks) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington), 281s 252(281s Johnson), 281s 552(281s Johnson), 162s 240-RB132 (162s Beddington), 162s 240-RB133 (162s Beddington) | 2019-11-18 08:00 | 2019-12-19 16:00 | N | Y | line protection upgrade | Line, Circuit Breaker | 918L (281s Johnson - 162s Beddington) |  | 240 kV, Contingency Requires Mitigation
BCH | 1L274 (Britt Creek - 1D4L274) | 2019-11-18 09:00 | 2019-11-22 17:00 | Y | Y | annual maintenance | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Overload, Pre-Condition
ALPAC | 282S Grassland (Alpac) | 2019-11-18 09:00 | 2019-11-18 12:00 | N | N | APF Athabasca (AFG1) phone outage for Telus firmware upgrade | Station |  |  | For Information Only
ENMAX | 11.82L (ENMAX 14 - ENMAX 11) | 2019-11-18 09:00 | 2019-11-29 16:00 | N | N | line protection upgrade | Line | 11.82L (ENMAX 14 - ENMAX 11) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2019-11-18 10:00 | 2019-11-21 15:00 | N | Y | migrate and commission RTU/SCADA | Line | 1083L (63s Red Deer - 288s Wolf Creek) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 266s 1037L FSC (266s SC1) | 2019-11-18 10:15 | 2019-11-19 17:45 | N | Y | Yearly maintenance | Shunts | 266s 1037L FSC (266s SC1) | Yearly maintenance P&C Techs to participate in yearly 266s FSC1 Capbank maintenance with the Substation group | 240 kV
ALTALINK | 415s 16 (415s Drywood) | 2019-11-18 10:30 | 2019-11-18 17:30 | N | N | Urgent outage to reconnect power cables | Switch |  | Customer requested outage to reconnect power cables to 415s16 to get them back online | Restricts Generation
ENMAX, ALTALINK | 985L (ENMAX 25 - 74s Janet) | 2019-11-18 11:00 | 2019-11-21 17:00 | N | Y | SCADA equipment upgrade | Line | 985L (ENMAX 25 - 74s Janet) | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | 240 kV, Overload, Pre-Condition
ALTALINK | 301s T1 (301s Queensland) | 2019-11-18 12:15 | 2019-11-18 17:45 | N | N | tap changer repair | Transformer | 301s T1 (301s Queensland) |  | For Information Only
ALTALINK | 64s T3 (64s East Crossfield) | 2019-11-19 07:00 | 2019-11-20 17:00 | N | N | bird cover up | Transformer | 64s T3 (64s East Crossfield) |  | For Information Only
ALTALINK | 394s T1 (394s Empress) | 2019-11-19 07:30 | 2019-11-19 18:00 | N | N | replace 394s54 with new 400A JBSS2 and replace existing 50KVA SS1 with new 75KVA SS1 | Transformer | 394s T1 (394s Empress) |  | For Information Only
ALTALINK | 221s T3 (221s Sunken Lake) | 2019-11-19 07:30 | 2019-11-20 15:30 | N | N | warranty repairs | Transformer | 221s T3 (221s Sunken Lake) |  | For Information Only
Syncrude | UE-1 30-2PTR72-A1 (UE-1) | 2019-11-19 08:00 | 2019-11-25 20:00 | N | Y | maintenance | Transformer | UE-1 30-2PTR72-A1 (UE-1) |  | Restricts Generation
ALTALINK | 244s T1 (244s Bowmanton) | 2019-11-19 08:00 | 2019-11-19 17:00 | N | Y | techs to investigate tap changer controller issues | Transformer | 244s T1 (244s Bowmanton) |  | 240 kV
ATCO | 741s 702T (741s Fox Creek), 741s 704 (741s Fox Creek) | 2019-11-19 10:00 | 2019-11-19 13:00 | N | N | top up on breaker 704, low oil pole 3 & check for leaks | Transformer, Circuit Breaker |  | Top up on Breaker 704, Low Oil Pole 3 & check for leaks, Transformer 702T out of service, load tied to 701T | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2019-11-19 10:00 | 2019-12-11 16:00 | N | N | forced outage | Transformer | 38.2TR (ENMAX 38) | gas, fault LTC contact | For Information Only
AESO-SC | OATI | 2019-11-19 18:00 | 2019-11-19 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 157s T1 (157s Lac La Biche) | 2019-11-20 07:00 | 2019-11-21 17:30 | N | N | install doble bushing monitors on T1 HV bushings | Transformer | 157s T1 (157s Lac La Biche) |  | For Information Only
ALTALINK | 489s T1 (489s Petro Canada Brazeau River) | 2019-11-20 07:30 | 2019-11-20 16:30 | N | N | modification to transformer CT secondary circuit | Transformer | 489s T1 (489s Petro Canada Brazeau River) | Modification to transformer CT secondary circuit. CT secondary is to be spared and requires short circuit installed at secondary terminals located in transformer junction box. | For Information Only
ALTALINK | 266s 1038L FSC (266s SC1) | 2019-11-20 08:15 | 2019-11-21 17:45 | N | Y | yearly maintenance | Shunts | 266s 1038L FSC (266s SC1) | yearly maintenance Techs to investigate issue with laser power unit P&C Techs to participate in yearly 266s FSC2 Capbank maintenance with the Substation group | 240 kV, For Information Only
ALTALINK | 149s T1 (149s Nisku) | 2019-11-20 08:15 | 2019-11-20 16:15 | N | N | replace 25kV switch (149s67) and standard relay maintenance (149s2194) | Transformer | 149s T1 (149s Nisku) |  | For Information Only
ALTALINK | 58s 202X (58s Edson) | 2019-11-20 08:30 | 2019-11-21 10:30 | N | N | perform 352BF trip tests after restoring 138kV east bus to service | Circuit Breaker | 58s 202X (58s Edson)
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-11-20 08:30 | 2019-11-20 12:00 | N | N | SF6 Top-up 20B138-1.81L. | Line | 1.81L (ENMAX 20 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2019-11-20 09:00 | 2019-11-25 18:00 | N | N | urgent fire mitigation - changing crossarms and insulators from structure 496 to 805 | Line | 202L (58s Edson - 178s Cynthia) |  | For Information Only, Pre-Condition
ALTALINK | 58s 890 (58s Edson), 890L (58s Edson - 207s Pinedale) | 2019-11-20 11:00 | 2019-11-20 12:00 | N | N | perform a trip test from 352 BF protection to 138kV breaker 452 (58s890). | Circuit Breaker, Line | 890L (58s Edson - 207s Pinedale) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | RL1 (848s Ruth Lake - D05 Syncrude), D05 T2 (D05 Syncrude), D05 517 (D05 Syncrude), D05 516 (D05 Syncrude), D05 513 (D05 Syncrude), D05 78 (D05 D05) | 2019-11-20 12:00 | 2019-11-29 11:59 | N | Y | substation outage | Line, Transformer, Circuit Breaker |  | Significant outage - D05 Substation 260/72 kV Outage - Zone 2. Following Cicuit Breakers will operated: 910 (Ruth Lake  by ATCO), 911 (Ruth Lake  by ATCO), 517, 516, 513, 78 at D05 . Following MOD will be Operated: RL-1D1 (Ruth Lake  by ATCO), 518, 517A, 517B, 516B, 516A, 513A, 513B, 509, 78A at D05 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 58s 671 (58s Edson), 671L (58s Edson - 39s Bickerdike) | 2019-11-20 12:15 | 2019-11-20 13:15 | N | N | perform a trip test from 352 BF protection to 138kV breaker 1052 (58s671) | Circuit Breaker, Line | 671L (58s Edson - 39s Bickerdike) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 58s 35 (58s Edson), 58s C1 (58s Edson) | 2019-11-20 13:20 | 2019-11-20 14:45 | N | N | perform a trip test from 352 BF protection to 138kV breaker 1352 (58s35). | Circuit Breaker, Shunts | 58s 35 (58s Edson), 58s C1 (58s Edson) |  | Pre-Condition
ALTALINK, MONTANA | 1201L (520s Bennett - BCH Cranbrook), MATL (120s Picture Butte - Montana) | 2019-11-20 22:00 | 2019-11-21 05:00 | Y | Y | forced outage | Line |  | 1201L: Peak RC COS outage ID: 1-00693798 Peak RC Path Derate ID: 1-00693799 (E>W), 1-00693800 (W>E) MATL: PEAK COS outage ID: 1-00646151 PEAK COS path de-rate ID:1-00646154 (N-S) :1-00646155 (S-N) | 240 kV, Limits ATC, 500 kV
EPCOR | 987s T2 (987s Clover Bar), 987s C2406 (987s Clover Bar), 987s C2405 (987s Clover Bar), 987s C2408 (987s Clover Bar), 987s T4 (987s Clover Bar) | 2019-11-21 07:00 | 2019-11-22 17:00 | N | Y | complete BF upgrade cutover to C2406, C2405 and C2408 breakers | Transformer, Circuit Breaker | 987s T2 (987s Clover Bar) | Extended Isolation points of CC721 breaker replacement outage in order to complete BF upgrade cutover to C2406, C2405 and C2408 breakers. | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | Kennedale K722 (Kennedale) | 2019-11-21 07:00 | 2019-11-23 17:00 | N | N | cutover of new BF protection | Circuit Breaker | Kennedale K722 (Kennedale) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 489s T2 (489s Petro Canada Brazeau River) | 2019-11-21 07:30 | 2019-11-21 16:30 | N | N | modification to transformer CT secondary circuit | Transformer | modification to transformer CT secondary circuit | modification to transformer CT secondary circuit. CT secondary is to be spared and requires short circuit installed at secondary terminals located in transformer junction box. | For Information Only
ALTALINK | 33s3 (33s Spray) | 2019-11-21 08:00 | 2019-11-21 17:00 | N | Y | disconnect maintenance | Switch | 33s3 (33s Spray) |  | Restricts Generation
ALTALINK | 131s T1 (131s Moon Lake) | 2019-11-21 08:30 | 2019-11-21 17:30 | N | N | tap changer repair | Transformer | 131s T1 (131s Moon Lake) |  | For Information Only
ALTALINK | 895s T3 (895s Suffield) | 2019-11-21 14:00 | 2019-11-21 16:00 | N | N | test new trip to 895s47 | Transformer | 895s T3 (895s Suffield) |  | Pre-Condition
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-11-23 08:30 | 2019-11-23 12:00 | N | N | SF6 top-up 20B138-1.81L. | Line | 1.81L (ENMAX 20 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.82L (ENMAX 14 - ENMAX 11), 11.83L (162s Beddington - ENMAX 11), 11.2TR (ENMAX 11), 11.3TR (ENMAX 11) | 2019-11-23 08:30 | 2019-11-24 02:00 | N | N | Fall substation washing (original outage Oct 5th) | Line, Transformer | 11.82L (ENMAX 14 - ENMAX 11), 11.83L (162s Beddington - ENMAX 11) |  | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 24.81L (ENMAX 31 - ENMAX 24), 24.83L (74s Janet - ENMAX 24), 24.1TR (ENMAX 24) | 2019-11-24 08:00 | 2019-11-24 12:00 | N | Y | RTU upgrade & AC OAC commissioning | Line, Transformer | 24.81L (ENMAX 31 - ENMAX 24) | Control Center will have no control on equipment. | Creates Radial Feeds, Firm Load Loss
ENMAX | 54.81L (ENMAX 54 - ENMAX 65) | 2019-11-24 08:00 | 2019-11-24 18:00 | N | N | HV Breaker Maintenance | Line | 54.81L (ENMAX 54 - ENMAX 65) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 24.82L (ENMAX 65 - ENMAX 24), 24.2TR (ENMAX 24) | 2019-11-24 12:00 | 2019-11-24 16:00 | N | N | RTU upgrade & CAC OAC commissioning | Line, Transformer | 24.82L (ENMAX 65 - ENMAX 24) | Control Center will have no control on equipment | For Information Only
EPCOR | 72CK12 (987s Clover Bar - Kennedale), Kennedale K723 (Kennedale) | 2019-11-25 07:00 | 2019-11-27 17:00 | N | N | cutover of new BF protection | Line, Circuit Breaker | 72CK12 (987s Clover Bar - Kennedale) |  | Pre-Condition
EPCOR | Rossdale T1 (Rossdale) | 2019-11-25 07:00 | 2019-11-29 17:00 | N | N | wildlife covering | Transformer | Rossdale T1 (Rossdale) |  | For Information Only
ENMAX | 39.2TR (ENMAX 39) | 2019-11-25 08:00 | 2019-11-28 16:00 | N | N | replace HV CTs. oil sampling MT, TC | Transformer | 39.2TR (ENMAX 39) |  | For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2019-11-25 08:00 | 2019-11-26 18:00 | N | N | neutral reactor installation | Transformer | 21.1TR (ENMAX 21) |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2019-11-25 08:00 | 2019-11-26 16:00 | N | N | relay maintenance zones 87-T5 and 51/51N. | Transformer | 1.8TR (ENMAX 1) |  | For Information Only
ENMAX | 162.2TR (ENMAX 162 Beddington), 162s Beddington 138 kV South Bus | 2019-11-25 08:00 | 2019-11-26 18:00 | N | Y | Oil sampling, switch maintenance | Transformer, Bus | 162.2TR (ENMAX 162 Beddington) | Oil sampling bushing, TC. Check reversing switch. HV SW maint SW88. 162.2TR LTC low oil | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 5L52 (Ingledow - Custer) | 2019-11-25 08:00 | 2019-11-27 19:00 | N | Y | BPA work | Line | 5L52 (Ingledow - Custer) |  | 500 kV, Pre-Condition
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2019-11-25 08:00 | 2019-12-02 17:00 | N | N | line maintenance | Line | 6L12 (6L25 tap - 774s Monitor) | Line maintenance | Pre-Condition
ALTALINK | 95s T1 (95s Imperal Oil Edmonton) | 2019-11-25 08:15 | 2019-11-28 16:45 | N | N | upgrade teleprotection / transfer trip scheme on 738L and add supervisory control to high side T1 MOD (95s738X) | Transformer | 95s T1 (95s Imperal Oil Edmonton) | Upgrade teleprotection / transfer trip scheme on 738L between 95s and 38s in preparation for IOL Cogen. (2) Add supervisory control to high side T1 MOD (95s738X) | For Information Only
ALTALINK | 38s 738W (38s East Edmonton) | 2019-11-25 08:30 | 2019-11-28 16:30 | N | N | upgrade teleprotection/transfer trip scheme on 738L between 95s and 38s | Circuit Breaker | 738L (38s East Edmonton - 738AL1) | preparation for IOL Cogen | Pre-Condition
ALTALINK, TRANSALTA | 616L (59s Peigan - 616AL tap), 59s T1 (59s Peigan), 59s Peigan 138kV Bus | 2019-11-25 09:00 | 2019-12-03 18:00 | N | Y | replace switches and post insulators | Line, Transformer, Bus | 59s T1 (59s Peigan), 59s Peigan 138kV Bus, 616L (59s Peigan - 103s Goose Lake) | Replace 138kv switches like for like, (59s5, 6 and 10) and post insulators. | 240 kV, Pre-Condition
ALTALINK | 912L (63s Red Deer - 766s Nevis) | 2019-11-25 10:00 | 2019-11-28 15:00 | N | Y | migrate and commission protections, alarms, status, controls, metering and remote access to new RTU and LAN | Line | 912L (63s Red Deer - 766s Nevis) | Migrate and commission all L4  912L at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission VT-4 alarms. Replace and commission new 63s912E (889) airbreak control module. | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25) | 2019-11-25 11:00 | 2019-11-28 17:00 | N | Y | SCADA equipment upgrade | Line | 1003L (74s Janet - ENMAX 25) | SCADA equipment upgrade, migrate new alarms, controls, analogs and remote access to new SCADA system. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 535s 6252 (535s Joffre) | 2019-11-25 11:30 | 2019-11-25 17:00 | N | N | implement sync check changes on relay | Circuit Breaker | 535s 6252 (535s Joffre) | implement/function sync check changes on M388/389 relay | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 113L (20s Ghost - 33s Spray) | 2019-11-25 12:00 | 2019-11-29 18:00 | N | N | inspect cables | Line | 113L (20s Ghost - 33s Spray) | inspect cables in 6 underground vaults | Contingency Requires Mitigation
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2019-11-25 12:00 | 2019-11-28 12:00 | N | N | line maintenance | Line | 7L23 (732s Mitsue - 796s Nipisi) | Line Maintenance | Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 973L (39s Bickerdike - 310p Sundance) | 2019-11-26 07:00 | 2019-11-26 18:00 | N | N | urgent fire mitigation | Line | 973L (39s Bickerdike - 310p Sundance) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
TALISMAN | TLM2 Talisman Edson | 2019-11-26 08:00 | 2019-11-27 11:00 | N | N | due to 58sT2 outage | Unit
ALTALINK | 58s T2 (58s Edson) | 2019-11-26 08:00 | 2019-11-27 11:00 | N | Y | connect CT contributions to protection relay & commission | Transformer | 58s T2 (58s Edson) |  | Restricts Generation
ENMAX | 5.8TR (ENMAX 5) | 2019-11-26 08:00 | 2019-11-26 16:00 | N | N | oil sampling | Transformer | 5.8TR (ENMAX 5)
EPCOR | 8L10 (330P Genesee - Fording Coal Mine) | 2019-11-26 08:00 | 2019-11-26 13:00 | N | N | repairing a sensor | Line | 8L10 (330P Genesee - Fording Coal Mine)
ENMAX | 1.81L (ENMAX 20 - ENMAX 1) | 2019-11-26 09:00 | 2019-12-19 16:00 | N | N | repair 20B138-1.81L leak by manufacturer | Line | 1.81L (ENMAX 20 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 795s 701T (795s Zama) | 2019-11-26 09:30 | 2019-11-27 11:59 | N | N | replace sequential bypass switch | Transformer | 795s 701T (795s Zama) | 795S Replace 501VRX with 1200A Sequential Bypass Switch, Replace 501VRX and Commission, 25kV Load fed from 702T for the duration of the work
ALTALINK | 523s T1 (523s Bullshead) | 2019-11-27 07:00 | 2019-11-28 17:30 | N | N | install Doble Bushing monitors | Transformer | 523s T1 (523s Bullshead) | Install Doble Bushing monitors on T1 HV Bushings | For Information Only
ALTALINK | 763L (158s Vauxhall - 257s Hull) | 2019-11-27 07:00 | 2019-11-28 17:00 | N | N | urgent repair to install sleeve clamps near structures #415, 494 & 500 | Line | 763L (158s Vauxhall - 257s Hull) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 21.2TR (ENMAX 21) | 2019-11-27 08:00 | 2019-11-28 18:00 | N | N | neutral reactor installation | Transformer | 21.2TR (ENMAX 21) |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2019-11-27 08:00 | 2019-11-28 16:00 | N | N | relay maintenance | Transformer | 1.7TR (ENMAX 1) | Relay maintenance zones 87-T5 and 51/51N. | For Information Only
ALTALINK | 158s T2 (158s Vauxhall) | 2019-11-27 09:00 | 2019-11-28 17:00 | N | Y | install and commission operator for MOD 158s21 | Transformer | 158s T2 (158s Vauxhall) | Install and commission operator for MOD 158s21.Linked to Ref# 266765. | For Information Only
ATCO | 795s 702T (795s Zama) | 2019-11-27 12:00 | 2019-11-28 15:30 | N | N | regulator replacement | Transformer | 795s 702T (795s Zama) | 795S Replace 502VRX with 1200A Sequential Bypass Switch, Replace 502VRX and Commission, 25kV Load fed from 701T for the duration of the work | For Information Only
ATCO | 7L73 (829s Boucher Creek - 800s Friedenstal) | 2019-11-27 12:00 | 2019-11-28 17:00 | N | Y | line maintenance | Line | 7L73 (829s Boucher Creek - 800s Friedenstal) | Line Maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALPAC | 282S Grassland (Alpac) | 2019-11-27 23:00 | 2019-11-28 06:00 | N | N | APF Athabasca (AFG1) phone outage for Telus firmware upgrade | Station |  |  | For Information Only
EPCOR | Kennedale K724 (Kennedale), 72CK12 (987s Clover Bar - Kennedale) | 2019-11-28 07:00 | 2019-11-29 17:00 | N | N | cutover of new BF protection | Circuit Breaker, Line | 72CK12 (987s Clover Bar - Kennedale) |  | Pre-Condition
ALTALINK | 421s T2 (421s Hays) | 2019-11-28 08:00 | 2019-11-28 18:00 | N | N | test new trip to 25kV breaker | Transformer | 421s T2 (421s Hays) | T2 transformer will need to be out of service to test new trip to 421s27. 25kV Bus 1 and Bus 2 will have to be tied together using 421s14 and T1 will supply both busses for the duration of trip test. Transformers T1 and T2 will have to be paralleled for a short period of time. | For Information Only
ENMAX | 20.1TR (ENMAX 20), ENMAX 20 B138-1.81 (ENMAX 20) | 2019-11-28 09:00 | 2019-11-28 18:00 | N | N | breaker repair | Transformer, Circuit Breaker | 20.1TR (ENMAX 20) | Repair 20B138-1.81L leak by manufacturer. Bus outage required to remove breaker. 1.81L OOS. | For Information Only
TALISMAN | TLM2 Talisman Edson | 2019-11-28 12:05 | 2019-12-02 12:30 | N | N | due to 153L (25 kV) feeder outage | Unit
ALTALINK | 58S Edson | 2019-11-28 12:05 | 2019-12-02 12:30 | N | N | replace strain insulators on 153L structure | Station | 58s153W GOI | Trip wiring and commissioning to breaker 53s153W from 38B/B87 protection relay, replace strain insulators on 153L structure | Restricts Generation
ALTALINK | 507L (257s Hull - 83s Taber) | 2019-11-29 07:00 | 2019-11-29 15:00 | N | N | urgent repair to install sleeve clamps near structure #9 | Line | 507L (257s Hull - 83s Taber) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | RL2 (848s Ruth Lake - D05 Syncrude), D05 512 (D05 Syncrude), D05 513 (D05 Syncrude) | 2019-11-29 12:00 | 2019-12-06 12:00 | N | Y | substation outage | Line, Circuit Breaker | RL2 (848s Ruth Lake - D05 Syncrude) | Significant outage - D05 Substation 260/72 kV Outage - Zone 3. Following Cicuit Breakers will operated: 902 (Ruth Lake  by ATCO only after RL-1 power has been restored) 907 (Ruth Lake  by ATCO only after RL-1 power has been restored). CB 512, 513 at D05. Following MOD will be Operated: RL-2D1 (Ruth Lake  by ATCO only after RL-1 power has been restored) 515, 512A, 512B, 513A, 513B at D05. | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 310p Sundance 240kV Bus C, 310P Sundance 138kV Bus, 310p 2852 (310p Sundance), 310p 767X (310p Sundance), 310P T36 (310p Sundance), 310p T30 (310p Sundance), 310P 69 (310p Sundance) | 2019-11-30 07:30 | 2019-12-03 18:00 | N | Y | footings for new station service PTs & add second bus protection to 240kV C Bus | Bus, Circuit Breaker, Transformer | 310p Sundance 240kV Bus C |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 551L (945s Sunshine Village - 953s Lake Louise) | 2019-11-30 08:00 | 2019-12-13 17:00 | N | N | energize/de-energize bypass line between Str345 and Str365A to allow for rebuild of 551L (Sections 15) | Line | 551L (945s Sunshine Village - 953s Lake Louise) |  | For Information Only
ATCO | 7L702 (137s Sedgewick - 757s Battle River) | 2019-11-30 08:00 | 2019-11-30 17:00 | N | Y | change arms and insulators | Line | 7L702 (137s Sedgewick - 757s Battle River) | Change Arms and Insulators on 7L702 | Pre-Condition, Restricts Generation
ALTALINK | 349S Stavely | 2019-11-30 08:00 | 2019-12-01 12:00 | N | Y | installation of bird cover. | Station | STAVELY |  | Restricts Generation
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2019-11-30 08:00 | 2019-12-01 07:59 | N | N | transmission - cables sheath test - 138-2.81 Line XLPE | Line | 2.81L (ENMAX 2 - ENMAX 9) |  | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2019-12-01 07:00 | 2019-12-04 19:00 | N | N | urgent: ULCM work-replace STR 13, 30, 40 & 42 for clearance mitigation | Line | 633L (56s Boyle - 405s Waupisoo) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 43 - ENMAX 9), 9.2TR (ENMAX 9), 9.3TR (ENMAX 9), ENMAX 9 B138-2.81 (ENMAX 9), ENMAX 9 B138-9.83 (ENMAX 9) | 2019-12-01 08:00 | 2019-12-01 18:00 | N | N | hotspot SW82, SW83 | Line, Transformer, Circuit Breaker | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 43 - ENMAX 9) |  | For Information Only
ALTALINK | 172L (370s North Lethbridge - 254s Coaldale) | 2019-12-02 07:00 | 2019-12-03 18:00 | N | N | replacing structures | Line | 172L (370s North Lethbridge - 254s Coaldale) | Replacing Structures #1067 & 1068 for line clearance mitigation | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2019-12-02 08:00 | 2019-12-04 16:00 | N | N | wiring modifications | Line | 31.84L (ENMAX 31 - ENMAX 32) | Wiring modifications required 32B138-31.84, 31B138-31.84 | For Information Only
ATCO | 791s 701T (791s Rainbow Lake) | 2019-12-02 08:00 | 2019-12-03 16:00 | N | N | tap changer will be wired and tested (tap changing) for commissioning purposes | Transformer | 791s 701T (791s Rainbow Lake) | 701T tap changer will be wired and tested (tap changing) for commissioning purposes. 701T will need to be isolated, via 701TD, while tap changing is occurring. Currently 701T does not have load, it is soaking. | For Information Only
SUNCOR, ATCO | 29PL6-2 (836s Steepbank - 29EDD-55), 836s 624 (836s Steepbank), 836s 625 (836s Steepbank) | 2019-12-02 08:00 | 2019-12-17 18:00 | N | N | line protection upgrades | Line, Circuit Breaker | 29PL6-2 (836s Steepbank - 29EDD-55) | 72kV Line 29PL6-2 outage for Line A/B Protection Upgrades | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 16.1TR (ENMAX 16) | 2019-12-02 08:00 | 2019-12-02 16:00 | N | N | replace gas relay | Transformer | 16.1TR (ENMAX 16) |  | For Information Only
ENMAX | 13.3TR (ENMAX 13) | 2019-12-02 08:00 | 2019-12-02 12:00 | N | N | transformer measurements | Transformer | 13.3TR (ENMAX 13) |  | For Information Only
ATCO | 7L51 (927s Buchanan Creek - A793s West Peace River) | 2019-12-02 08:00 | 2019-12-11 17:00 | N | Y | replace crossarms | Line | 7L51 (927s Buchanan Creek - A793s West Peace River) | replace crossarms | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.5TR (ENMAX 1) | 2019-12-02 08:00 | 2019-12-03 16:00 | N | N | relay testing and transformer maintenance | Transformer | 1.5TR (ENMAX 1) |  | For Information Only
ENMAX | 40.1TR (ENMAX 40) | 2019-12-02 08:00 | 2019-12-03 16:00 | N | N | protection testing: GE T60 87 relay | Transformer | 40.1TR (ENMAX 40) |  | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2019-12-02 09:00 | 2019-12-06 17:00 | Y | Y | annual maintenance | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 603L (138s Windy Flats - 243s Soderglen Wind Farm), 138s 2552 (138s Windy Flats) | 2019-12-02 09:30 | 2019-12-03 17:00 | N | Y | install and test new tele-protection module | Line, Circuit Breaker | 603L (138s Windy Flats - 243s Soderglen Wind Farm) | Install and test new tele-protection module that provides transfer tripping between 138s Windy Flats and 243s Soderglen. Working on 603L protections and 138s2552 breaker fail protection. | Pre-Condition, Restricts Generation
ALTALINK | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) | 2019-12-02 10:00 | 2019-12-04 17:00 | N | N | T2 electrical testing & T1 leakage reactance test | Transformer | 133s T1 (133s Stelco Edmonton), 133s T2 (133s Stelco Edmonton) |  | For Information Only
ALTALINK | 28s T3 (28s West Brooks) | 2019-12-02 10:00 | 2019-12-04 15:00 | N | N | install new air break control module | Transformer | 28s T3 (28s West Brooks) | Install new air break control module for 28s61 (1689). | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1082L (63s Red Deer - 287s Hazelwood) | 2019-12-02 10:00 | 2019-12-05 15:00 | N | Y | migrate and commission new RTU and LAN | Line | 1082L (63s Red Deer - 287s Hazelwood) | Migrate and commission all L7 1082 at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection alarms, status, controls, metering and remote access to new RTU and LAN. Migrate and commission VT-7 alarms. Replace and commission new 63S1082 (1189) airbreak control module. | 240 kV, Pre-Condition
ATCO | 7L73 (730s Rycroft - 829s Boucher Creek) | 2019-12-02 12:00 | 2019-12-06 12:00 | N | Y | line maintenance | Line | 7L73 (730s Rycroft - 829s Boucher Creek) | Line Maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L23 (732s Mitsue - 796s Nipisi) | 2019-12-02 12:00 | 2019-12-03 16:30 | N | N | line maintenance | Line | 7L23 (732s Mitsue - 796s Nipisi) | Line Maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 847L (602s Cold Creek - 492L1 - 847L236D) | 2019-12-03 07:00 | 2019-12-05 18:00 | N | Y | fire mitigation work includes repairs on structures strs 292, 293, 294, 298 and 303 | Line | 847L (602s Cold Creek - 847AL Tap) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 63s T3 (63s Red Deer) | 2019-12-03 07:30 | 2019-12-03 17:30 | N | N | tap change & testing | Transformer | 63s T3 (63s Red Deer) |  | For Information Only
ENMAX | 16.2TR (ENMAX 16) | 2019-12-03 08:00 | 2019-12-03 16:00 | N | N | corrective: replace gas relay | Transformer | 16.2TR (ENMAX 16) |  | For Information Only
ENMAX | 31.2TR (ENMAX 31) | 2019-12-03 08:00 | 2019-12-03 16:00 | N | N | oil sampling MT and TC | Transformer | 31.2TR (ENMAX 31) |  | For Information Only
ALTALINK | 995L (62s Brazeau - 995AL tap) | 2019-12-03 08:45 | 2019-12-03 13:15 | N | Y | radio work at 9062R | Line | 995L (62s Brazeau - 995AL tap) |  | 240 kV, Pre-Condition
ALTALINK | 744L (228s T.M.P.L.Niton - 207s Pinedale) | 2019-12-03 17:01 | 2019-12-09 18:00 | N | N | component replacements | Line | 744L (228s T.M.P.L.Niton - 207s Pinedale) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 391s T2 (391s Balzac) | 2019-12-04 08:00 | 2019-12-04 17:00 | N | N | investigate issues on tap position indication | Transformer | 391s T2 (391s Balzac) |  | For Information Only
ALTALINK | 156L (19s Wabamun - 156L84A), 896L (19s Wabamun - 432s Carvel), 19s T10 (19s Wabamun), 19S Wabamun 138kV Bus1, 19s T8 (19s Wabamun), 19S Wabamun 138kV Bus2 | 2019-12-04 08:00 | 2019-12-13 17:30 | N | Y | salvage 138kv structure and switches 19s75 and 19s74 & replace 138kv insulators, relocate 19s7 and 19s240 | Line, Transformer, Bus | 19s T10 (19s Wabamun) | Salvage 138kv structure and switches 19s75 and 19s74. Replace 138kv insulators, relocate 19s7 and 19s240(will be in the same location) | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 13.2TR (ENMAX 13) | 2019-12-04 08:00 | 2019-12-04 16:00 | N | N | fix hotspot | Transformer | 13.2TR (ENMAX 13) |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2019-12-04 08:00 | 2019-12-05 16:00 | N | N | relay maintenance zones 87-T5 and 51/51N. | Transformer | 1.6TR (ENMAX 1) |  | For Information Only
ENMAX | 35.1TR (ENMAX 35) | 2019-12-04 08:00 | 2019-12-04 14:00 | N | N | relay testing and transformer maintenance | Transformer | ENMAX 35.1TR (ENMAX 35) |  | For Information Only
ALTALINK | 426s VR1 (426s Coalspur) | 2019-12-04 08:00 | 2019-12-04 16:00 | N | N | urgent maintenance | Transformer |  |  | For Information Only
ALTALINK | 739L (14s Devon - 305s Acheson), 14s 739N (14s Devon) | 2019-12-04 12:00 | 2019-12-04 15:00 | N | N | low gas | Line, Circuit Breaker | 739L (14s Devon - 305s Acheson) |  | Creates Radial Feeds, Overload, Pre-Condition
ALTALINK | 171s T2 (171s Redwater), 808L (171s Redwater - 808L75C) | 2019-12-05 07:00 | 2019-12-06 14:00 | N | N | replace 171s48 junction box | Transformer, Line | 808L (171s Redwater - 808L75C) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 2075s SVC2 (2075s Newell) | 2019-12-05 07:00 | 2019-12-06 17:30 | N | Y | emergency outage for SVC2 to repair station major alarms | Shunts | 2075s SVC2 (2075s Newell) | DIW Strainer replacement on SVC1 & SVC 2 Cooling System. Replace CPU551 boards on TDC System 1 in SVC2. Will not need GOI, but will disable and tag 930A in case of inadvertent operation from damaged TDC. | 240 kV
ALTALINK | 719L (263s Strachan - 719L259C) | 2019-12-05 07:00 | 2019-12-07 18:00 | N | N | urgent fire mitigation; scope of work includes maintenance work on Strs #280, 288 & 289 | Line | urgent fire mitigation; scope of work includes maintenance work on Strs #280, 288 & 289 |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2019-12-05 07:00 | 2019-12-08 17:00 | N | Y | insulation & aerial marker upgrades | Line | 909L (89s Ellerslie - 665s Dome) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 39.1TR (ENMAX 39) | 2019-12-05 08:00 | 2019-12-05 12:00 | N | N | oil sampling bushing | Transformer | 39.1TR (ENMAX 39) |  | For Information Only
ENMAX | 24.1TR (ENMAX 24) | 2019-12-05 08:00 | 2019-12-05 16:00 | N | N | 24.1TR XO ground cable corrective | Transformer | 24.1TR (ENMAX 24) |  | For Information Only
ALTALINK | 33s6 (33s Spray) | 2019-12-05 08:00 | 2019-12-05 17:00 | N | Y | maintenance | Switch | 33s6 (33s Spray) |  | Restricts Generation
ALTALINK | 115S Mt.Allan | 2019-12-05 08:00 | 2019-12-25 16:00 | N | N | P2023 Fortis- Kananaskis Area Reliability ISD: Dec 18, 2019 | Station
ENMAX | 40.2TR (ENMAX 40) | 2019-12-05 08:00 | 2019-12-06 16:00 | N | N | relay protection testing | Transformer | 40.2TR (ENMAX 40) |  | For Information Only
ATCO | 7L760 (7L760D2 - 767s Oyen) | 2019-12-05 10:00 | 2019-12-06 17:00 | N | Y | emergency outage for climbing patrol to locate the fault | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ENMAX | 39.4TR (ENMAX 39) | 2019-12-05 12:00 | 2019-12-05 16:00 | N | N | oil sampling tap changer | Transformer | 39.4TR (ENMAX 39) |  | For Information Only
ENMAX | 41.84L (ENMAX 54 - ENMAX 41) | 2019-12-06 08:00 | 2019-12-06 16:00 | N | N | install bird deterrents at river crossings | Line | 41.84L (ENMAX 54 - ENMAX 41) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 906L (17s Benalto - 42s Sarcee), 17s Benalto 240 kV South Bus 2, 17s T2 (17s Benalto) | 2019-12-06 09:00 | 2019-12-06 12:59 | N | Y | replace 17s906X | Line, Bus, Transformer | 906L (17s Benalto - 42s Sarcee) | Replace 17s906X. Bus outage needed to disconnect 17s906X switch base from 906L. (Like for Like) | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
Syncrude | AL-2 (D05 Syncrude - Aurora), Aurora 222 (Aurora), Aurora 223 (Aurora), D05 511 (D05 Syncrude), D05 512 (D05 Syncrude) | 2019-12-06 12:00 | 2019-12-14 20:00 | N | Y | substation outage | Line, Circuit Breaker | AL-2 (D05 Syncrude - Aurora) | Significant outage - D05 Substation 260/72 kV Outage - Zone 4. Following Cicuit Breakers will operated: 222 (Aurora G01 Substation), 223 (Aurora G01 Substation), and 511, 512 at D05 Following MOD will be Operated: 225 (Aurora G01 Substation), and 514, 511A, 511B, 512A, 512B at D05. | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 906L (17s Benalto - 42s Sarcee), 17s 4 (17s Benalto), 17s 5 (17s Benalto) | 2019-12-06 13:00 | 2019-12-10 12:30 | N | Y | continue replacing 17s906X switch | Line, Circuit Breaker | 906L (17s Benalto - 42s Sarcee) |  | 240 kV, Contingency Requires Mitigation, For Information Only
ALTALINK | 171s T2 (171s Redwater), 171s 808E (171s Redwater), 808L (171s Redwater - 808L75C) | 2019-12-06 14:00 | 2019-12-13 18:00 | N | N | urgent switch repair | Transformer, Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 786L (799s Coleman - Natal) | 2019-12-07 07:00 | 2019-12-07 18:00 | N | Y | urgent fire mitigation; installing clampstar assemblies over hot sleeves in spans adjacent to Str. #87 | Line | 786L (799s Coleman - Natal) RC West WebOMS ID: 8052408 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ATCO | 757s 911 (757s Battle River) | 2019-12-07 08:00 | 2019-12-21 16:00 | N | N | emergency breaker replacement. ISD Dec 14, 2019 (capital maintenance) | Circuit Breaker
ALTALINK | 170L (632s Russell - 799s Coleman) | 2019-12-08 07:00 | 2019-12-09 18:00 | N | Y | urgent fire mitigation; installing clampstar assemblies over hot sleeves in spans | Line | RC West webOMS Outage ID: 8052431 |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | Kennedale KAB2 (Kennedale), Kennedale K723 (Kennedale), Kennedale K722 (Kennedale), Kennedale T2 (Kennedale) | 2019-12-09 07:00 | 2019-12-13 17:00 | N | N | repair to motor drive | Switch, Circuit Breaker, Transformer | Kennedale KAB2 (Kennedale) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | Namao N724 (Namao), Namao N723 (Namao), Namao T3 (Namao), 72CN10 (987s Clover Bar - Namao) | 2019-12-09 07:00 | 2019-12-11 17:00 | N | N | repair | Circuit Breaker, Transformer, Line | Namao T3 (Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 13s Deerland 138kV Bus 1 | 2019-12-09 07:30 | 2019-12-19 18:00 | N | N | replace PT | Bus | 13s Deerland 138kV Bus 1 | Demo and replace PT1, replace 138kV Station Service transformer, Complete connections to secondary disconnects, Energize new transfer switch and AC Distribution panel. Demolish existing feed to old transfer switch. | Contingency Requires Mitigation
ENMAX | 2.2TR (ENMAX 2) | 2019-12-09 08:00 | 2019-12-09 16:00 | N | N | maintenance | Transformer | 2.2TR (ENMAX 2) | Oil sampling MT, TC. Check reversing switch. ABB LTC Oil Filtration Maintenance | For Information Only
ATCO | 6L12 (775s Sullivan Lake - 6L25 tap) | 2019-12-09 08:00 | 2019-12-10 17:00 | N | N | line maintenance | Line | 6L12 (775s Sullivan Lake - 6L25 tap) | Line maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 38s East Edmonton RTU/SCADA | 2019-12-09 08:30 | 2019-12-09 16:00 | N | N | techs to investigate nuisance failovers on RTU at site. | Terminal Equipment |  |  | Affects Visibility
ATCO | 7L129 (918s Bauer - 710s Vermilion) | 2019-12-09 08:30 | 2019-12-10 17:00 | N | N | line inspection | Line | 7L129 (918s Bauer - 710s Vermilion) | Line inspection of 7L129 | Over/Under Voltage, Overload, Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs), 37s 88 (37s North Calder), 37s 82 (37s North Calder) | 2019-12-09 09:15 | 2019-12-13 13:15 | N | Y | switch replacement | Line, Circuit Breaker | 920L (37s North Calder - 557s Castle Downs) | Replace 240kV Switch (37s87), 240kV PTs (37s85) | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 63s T4 (63s Red Deer) | 2019-12-09 10:00 | 2019-12-12 15:00 | N | N | migrate and commission protections to new RTU and LAN | Transformer | 63s T4 (63s Red Deer) | Migrate and commission all T4 (TX18822), 63s1952 & 63s2052 protections, breaker fail protections, breaker, status, controls, alarms, metering, to the new RTU and LAN. Cut over and commission VT17 ground alarms (to be done hot, tested by jumpering out contacts).T4 TX18822, 63s1952, 63s2052 breaker control and associated T4 transformer protections will be out of service. Loss of visibility or possible false status and alarms for associated equipment during cut over and commissioning tests. | For Information Only
ALTALINK | 737L (95s Imperial Oil Edmonton - 38s East Edmonton) | 2019-12-09 12:15 | 2019-12-12 11:25 | N | N | components replacements | Line | 737L (95s Imperial Oil Edmonton - 38s East Edmonton) | 737L Components Replacements (Str's: 26A, 27A, 27) | Creates Radial Feeds, Firm Load Loss
ALTALINK | 19s245 (19s Wabamun) | 2019-12-10 08:00 | 2019-12-10 17:30 | N | N | salvage PT 2018 | Switch | 19s245 (19s Wabamun) |  | For Information Only
ENMAX | 162.3TR (ENMAX 162 Beddington) | 2019-12-10 08:00 | 2019-12-10 16:00 | N | N | oil sampling, maintenance | Transformer | 162.3TR (ENMAX 162 Beddington) | Oil sampling TC, Filmax LTC Oil Filtration Maintenance. Check reversing switch. | For Information Only
ALTALINK | 58s 890 (58s Edson), 890L (58s Edson - 207s Pinedale) | 2019-12-10 08:00 | 2019-12-10 11:29 | N | N | trip test | Circuit Breaker, Line | 58s 890 (58s Edson), 890L (58s Edson - 207s Pinedale) | Trip Test 58s890 from new 138B/B87 Relay, Connect CT Contributions. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2019-12-10 09:00 | 2019-12-20 17:00 | Y | Y | annual maintenance | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 58s 671 (58s Edson), 671L (58s Edson - 39s Bickerdike) | 2019-12-10 11:30 | 2019-12-10 16:29 | N | N | trip test | Circuit Breaker, Line | 671L (58s Edson - 39s Bickerdike) | Trip Test 58s671 from new 138B/B87 Relay, Connect CT Contributions. Update settings and test fault location settings. Update sync check settings and test relay. | Over/Under Voltage, Pre-Condition
ALTALINK | 906L (17s Benalto - 42s Sarcee), 17s Benalto 240 kV South Bus 2, 17s T2 (17s Benalto) | 2019-12-10 13:00 | 2019-12-10 17:00 | N | Y | replace switch | Line, Bus, Transformer | 906L (17s Benalto - 42s Sarcee) | Replace 17s906X. Bus outage needed to Re-connect 17s906X switch base to 906L. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
ALTALINK | 58s C1 (58s Edson), 58s 35 (58s Edson) | 2019-12-10 14:30 | 2019-12-10 17:30 | N | N | trip test | Shunts, Circuit Breaker | 58s 35 (58s Edson), 58s C1 (58s Edson) | Trip Test 58s35 from new 138B/B87 Relay, Connect CT Contributions. | Pre-Condition
EPCOR | 987s C72C1 (987s Clover Bar) | 2019-12-11 07:00 | 2019-12-11 17:00 | N | N | cutover of new breaker fail protection to C72C1 breaker | Circuit Breaker | 987s C72C1 (987s Clover Bar) |  | Pre-Condition
ALTALINK | 13L/158L (65s High River - 392s Black Diamond) | 2019-12-11 07:00 | 2019-12-13 18:00 | N | N | install marker cones and OPGW suspensions | Line | 13L/158L (65s High River - 392s Black Diamond) | install marker cones and OPGW suspensions, splice fiber boxes  Various locations between STR #1 & 142 | Creates Radial Feeds, Firm Load Loss
ALTALINK | 199s East Airdrie RTU/SCADA | 2019-12-11 08:00 | 2019-12-11 16:00 | N | N | urgent repair issue with RS232 connection from RTU and splitter | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 744L (228s T.M.P.L.Niton - 744L89B) | 2019-12-11 08:00 | 2019-12-16 18:00 | N | N | component replacements on STRs 95, 106, 112, 152, 159, 222, 224, 240, 266 | Line | 744L (228s T.M.P.L.Niton - 744L89B) | Component Replacements on 744L, STRs 95, 106, 112, 152, 159, 222, 224, 240, 266 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 39.1TR (ENMAX 39) | 2019-12-11 08:00 | 2019-12-12 16:00 | N | N | upgrade T-60 | Transformer | 39.1TR (ENMAX 39) |  | For Information Only
ALTALINK | 19s244 (19s Wabamun) | 2019-12-11 08:00 | 2019-12-11 17:30 | N | N | salvage PT 1257 at 19s244. | Switch | 19s244 (19s Wabamun) |  | For Information Only
ENMAX | 162.4TR (ENMAX 162 Beddington) | 2019-12-11 08:00 | 2019-12-11 16:00 | N | N | oil sampling | Transformer | 162.4TR (ENMAX 162 Beddington) | Oil sampling TC, check reversing switch. Filmax Maint. | For Information Only, Pre-Condition
ATCO | 6L02 (873s Marion Lake - 765s Mannix Mine) | 2019-12-11 08:00 | 2019-12-11 17:00 | N | N | line road move | Line | 6L02 (873s Marion Lake - 765s Mannix Mine) | Line road move, for a turning lane into the mine site. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L129 (526s Buffalo Creek - 918s Bauer) | 2019-12-11 08:30 | 2019-12-12 17:00 | N | Y | line inspection | Line | 7L129 (526s Buffalo Creek - 918s Bauer) | Line inspection of 7L129 | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 895S Suffield | 2019-12-11 09:00 | 2019-12-12 17:00 | N | N | isolating cables that come out of 895s2272 in order to install new cubicle outside the substation | Station |  | 895s2272 - Advice. Isolating cables that come out of 895s2272 in order to install new cubicle outside the substation. 2272L3 will be removed after project is complete and 2272L1U 1xyz will be in its place. Fortis will require Altalink staff to install grounds on the line side of 895s2272. | For Information Only
ALTALINK | 115s T1 (115s Mt.Allan) | 2019-12-11 09:00 | 2019-12-18 14:00 | N | N | install bird cover-up | Transformer | 115s T1 (115s Mt.Allan) | Connect 25KV Bus Tie to 25kV Bus 1(Close Open point 'A' and SS1 open point).Install Bird Coverup on new 25kV Bus 1 equipment. Test energize new 115s15. Phase across 115s16 between the two buses. Test capability of 115s889. SS1 checks. | For Information Only
ALTALINK | 250p11 (250p Bighorn Plant) | 2019-12-11 11:00 | 2019-12-11 15:00 | N | Y | maintenance | Switch | 250p11 (250p Bighorn Plant) |  | Restricts Generation
EPCOR | 72CH9 (Hardisty - 987s Clover Bar), 987s CH722 (987s Clover Bar) | 2019-12-12 07:00 | 2019-12-12 17:00 | N | N | cutover of new breakerfail protection to CH722 breaker | Line, Circuit Breaker | 72CH9 (Hardisty - 987s Clover Bar) |  | Firm Load Loss, Pre-Condition
ALTALINK | 671L (58s Edson - 39s Bickerdike) | 2019-12-12 07:00 | 2019-12-12 18:00 | N | N | fire mitigation work includes repairs on structures 57, 111 and 112 | Line | 671L (58s Edson - 39s Bickerdike) |  | Pre-Condition
ALTALINK | 64s East Crossfield 138kV Bus2, 752L (64s East Crossfield - 752L67), 64s 452 (64s East Crossfield), 64s 652 (64s East Crossfield) | 2019-12-12 08:00 | 2019-12-12 13:00 | N | N | urgent repair on GE CT cabling issues on 64s452 and 64s652 | Bus, Line, Circuit Breaker | 752L (64s East Crossfield - 752L67) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L73 (829s Boucher Creek - 800s Friedenstal) | 2019-12-12 08:00 | 2019-12-12 16:07 | N | Y | line maintenance | Line | 7L73 (829s Boucher Creek - 800s Friedenstal) | Line Maintenance | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 250p22 (250p Bighorn Plant) | 2019-12-12 09:00 | 2019-12-12 13:00 | N | Y | maintenance | Switch | 250p22 (250p Bighorn Plant) |  | Restricts Generation
ALTALINK | 115s Mt.Allan RTU/SCADA | 2019-12-12 09:00 | 2019-12-12 17:00 | N | N | correct T1 tap changer points | Terminal Equipment |  | Correct T1 Tap Changer points. SCADA visibility to ACC will be isolated. RTU will only be down 10 min at a time during the configuration updates. Linked to Ref# 267186 | Affects Visibility
ATCO | 779s 701T (779s Chinchaga River) | 2019-12-12 10:00 | 2019-12-12 14:00 | N | N | bushing PCB samples | Transformer | 779s 701T (779s Chinchaga River) | 779S 701T Bushing PCB Samples, Station out of Service for the Duration of the work | For Information Only
ATCO | 951s SVC (951s Thickwood) | 2019-12-13 00:45 | 2019-12-20 18:00 | N | Y | forced out | Shunts |  |  | 240 kV
ALTALINK | 266s 1038L FSC (266s SC1) | 2019-12-13 08:00 | 2019-12-18 17:30 | N | Y | forced outage | Shunts |  |  | 240 kV, For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2019-12-13 08:00 | 2019-12-13 18:00 | N | N | install neutral reactor and remove cables from duct | Transformer | 21.1TR (ENMAX 21) |  | For Information Only
ATCO | 740s 703T (740s H.R.Milner) | 2019-12-13 08:00 | 2019-12-27 16:00 | N | N | transformer replacement ISD Dec 20, 2019 (capital maintenance) | Transformer
EPCOR | 987s T2 (987s Clover Bar), 72CN10 (987s Clover Bar - Namao), 987s CC13 (987s Clover Bar), 987s CN723 (987s Clover Bar), 987s GDS3 (987s Cloverbar), 987s CC721 (987s Clover Bar) | 2019-12-14 | 2019-12-14 06:00 | N | Y | emergency repair of overheating disconnect | Transformer, Line, Circuit Breaker, Switch | 987s T2 (987s Clover Bar) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2019-12-14 07:00 | 2019-12-18 17:00 | N | N | fire mitigation work includes repairs on structures STR's 494A, 506, 777, 779 and 781. | Line | 202L (58s Edson - 178s Cynthia) |  | Pre-Condition,Affects Cranking Path
ATCO | 7L54 (794s Valleyview - 813s Little Smoky) | 2019-12-14 08:00 | 2019-12-20 15:00 | N | N | change x-arm | Line | 7L54 (794s Valleyview - 813s Little Smoky) | Contractor work to change xarm | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ENMAX | 1.81L (ENMAX 20 - ENMAX 1), 20.1TR (ENMAX 20) | 2019-12-15 08:00 | 2019-12-15 18:00 | N | N | repair 20B138-1.81L leak by manufacturer | Line, Transformer | 1.81L (ENMAX 20 - ENMAX 1) |  | For Information Only, Pre-Condition
ENMAX | 31.3TR (ENMAX 31) | 2019-12-15 08:00 | 2019-12-15 10:00 | N | N | oil sampling LTC | Transformer | 31.3TR (ENMAX 31) |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2019-12-15 10:00 | 2019-12-15 13:00 | N | N | oil sampling LTC | Transformer | 31.1TR (ENMAX 31) |  | For Information Only
ALTALINK | 54L (118s Canmore - 54L172) | 2019-12-16 07:00 | 2019-12-18 18:00 | N | N | urgent fire mitigation - structure replacement and maintenance | Line | 54L (118s Canmore - 54L172) | Urgent fire mitigation; Scope of work includes replacing Str #171A and maintenance on Strs #141, 142, 143, 144, 148, 150, 152, 154 & 160 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L12 (6L25 tap - 774s Monitor) | 2019-12-16 08:00 | 2019-12-19 16:00 | N | N | Change Arms Insulators fiberglass to wood | Line | 6L12 (6L12D5- 6L12D3) | Change Arms Insulators fiberglass to wood | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 2019-12-16 08:00 | 2019-12-17 17:00 | N | Y | replace crossarms | Line | 7L32 (811s Clairmont Lake - 862s South Bezanson), 7L32 (862s South Bezanson - 813s Little Smoky) | replace crossarms | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2019-12-16 08:00 | 2019-12-16 16:00 | N | N | remove scaffolding at 8 sub | Line | 3.82L (ENMAX 3 - ENMAX 8) | DCTRP. Remove scaffolding at 8sub. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 39.1TR (ENMAX 39) | 2019-12-16 08:00 | 2019-12-16 12:00 | N | N | oil sampling bushing | Transformer | 39.1TR (ENMAX 39) |  | For Information Only
ATCO | 7L90 (813s Little Smoky - 7L90D2) | 2019-12-16 09:00 | 2019-12-20 13:00 | N | N | replace crossarms | Line | 7L90 (813s Little Smoky - 7L90D2) | replace crossarms | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 310p Sundance 240kV Bus C, 310P Sundance 138kV Bus, 310P T37 (310p Sundance), 310P T36 (310p Sundance), 310p T30 (310p Sundance), 310p 2852 (310p Sundance), 310P 69 (310p Sundance) | 2019-12-16 10:00 | 2019-12-19 17:30 | N | Y | install new station service PTs | Bus, Transformer, Circuit Breaker | 310p Sundance 240kV Bus C | Install new Station Service PTs, complete second bus protection to 240kV C Bus | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 648L (63s Red Deer - 580s Sylvan Lake) | 2019-12-16 10:00 | 2019-12-19 15:00 | N | N | migrate and commission line protections, breakers, breaker fail and tele-protection communications alarms, status, controls, metering and remote access to new RTU and LAN | Line | 648L (63s Red Deer - 580s Sylvan Lake) | Migrate and commission all L14  648L, 63s648 at 63S Red Deer associated line protections, breakers, breaker fail and Tele-protection communications alarms, status, controls, metering and remote access to new RTU and LAN. Remove L14-648L SCADA metering module and install DNP mapping in A87L/L14 protection for SCADA metering. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 217s C1 (217s North Red Deer) | 2019-12-16 11:00 | 2019-12-16 17:30 | N | N | standard relay maintenance | Shunts | 217s C1 (217s North Red Deer) | Techs to perform standard relay maintenance on: C1 50/51/60/27/59/C1 SR760 | For Information Only
ALTALINK | 255s T1 (255s Vulcan) | 2019-12-16 12:00 | 2019-12-18 12:00 | N | N | installation of cantega cover | Transformer | 255s T1 (255s Vulcan) |  | For Information Only
ALTALINK | 223L (159s Colinton - 150s Clyde) | 2019-12-16 13:00 | 2019-12-19 17:45 | N | N | component replacements 223L structures 65, 237, 255, 426, 427 & 428 | Line | 223L (159s Colinton - 150s Clyde) | Component replacements 223L structures 65, 237, 255, 426, 427, & 428 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 71s 452 (71s Lamoureux) | 2019-12-17 07:00 | 2019-12-19 17:00 | N | N | CT replacement | Circuit Breaker | 71s 452 (71s Lamoureux) | Replace 71s CTs associated with breaker 71s452 | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 67s 508X (67s Stirling), 67s 2 (67s Stirling) | 2019-12-17 08:00 | 2019-12-17 11:30 | N | N | line crew to close open point C, line crew to close open point D | Circuit Breaker | 67s 508X (67s Stirling) |  | Pre-Condition
ALTALINK | 744L (235s Entwistle - 744L88C) | 2019-12-17 08:00 | 2019-12-20 18:00 | N | N | component replacements | Line | 744L (235s Entwistle - 744L88C) | Component Replacements on 744L, STRs 11, 14, 78, 86A, 104A, 111A, 118A, 126A | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s 2152 (74s Janet) | 2019-12-17 08:30 | 2019-12-17 17:00 | N | Y | breaker maintenance | Circuit Breaker | 74s 2152 (74s Janet) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 6L126 (515L tap - 743s Sarah Lake) | 2019-12-17 09:00 | 2019-12-17 15:00 | N | Y | taking wire samples for testing | Line | 6L126 (515L tap - 743s Sarah Lake) | Taking Wire samples for testing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 67s 820 (67s Stirling), 67s T2 (67s Stirling), 67s 2 (67s Stirling) | 2019-12-17 12:00 | 2019-12-17 15:00 | N | N | disconnect mobile | Circuit Breaker, Transformer | 67s 820 (67s Stirling) | to disconnect Mobile. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
AESO-SC | OATI | 2019-12-17 18:00 | 2019-12-17 19:00 | N | N | switching from one Data Centre to another | SCInternal |  |  | For Information Only
ATCO | 6L11 (742s Freeman Lake - 743s Sarah Lake) | 2019-12-18 08:00 | 2019-12-18 12:00 | N | N | taking wire samples for testing | Line | 6L11 (742s Freeman Lake - 743s Sarah Lake) | Taking wire samples for testing | Pre-Condition
ATCO | 6L11 (739s Edith Lake - 854s Swan Dive) | 2019-12-18 13:00 | 2019-12-18 16:00 | N | N | take wire samples for testing | Line | 6L11 (739s Edith Lake - 854s Swan Dive) | Taking wire samples for testing | Pre-Condition
ALTALINK | 62s11 (62s Brazeau) | 2019-12-18 23:00 | 2019-12-19 03:00 | N | Y | maintenance | Switch | 62s 11 (62s Brazeau) |  | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2019-12-19 03:00 | 2019-12-19 07:00 | N | Y | maintenance | Switch | 62s12 (62s Brazeau) |  | 240 kV, Restricts Generation
ALTALINK | 76L (115s Mt. Allan - 33s Spray) | 2019-12-19 07:00 | 2019-12-20 18:00 | N | N | urgent fire mitigation & maintenance on strs 45, 46 & 52 | Line | 76L (115s Mt. Allan - 33s Spray) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L32 (862s South Bezanson - 813s Little Smoky) | 2019-12-19 08:00 | 2019-12-19 17:00 | N | Y | replace crossarms | Line | 7L32 (862s South Bezanson - 813s Little Smoky) | replace crossarms | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 6L96 (735s Swan River - 743s Sarah Lake) | 2019-12-19 08:00 | 2019-12-19 14:00 | N | N | taking wire samples for testing | Line | 6L96 (735s Swan River - 744s Federated Pipelines - 743s Sarah Lake) | Taking wire samples for testing | Pre-Condition
ALTALINK | 133L (19s Wabamun - 133L697A) | 2019-12-19 17:31 | 2020-01-31 17:00 | N | N | urgent line clearance mitigation | Line | 133L (19s Wabamun - 133L697A) |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 2019-12-20 13:00 | 2019-12-21 17:00 | N | Y | replace crossarms | Line | 7L32 (811s Clairmont Lake - 862s South Bezanson), 7L32 (862s South Bezanson - 813s Little Smoky) | replace crossarms | Contingency Requires Mitigation, Overload, Pre-Condition,Affects Cranking Path
ATCO | 7L32 (862s South Bezanson - 813s Little Smoky) | 2019-12-22 08:00 | 2019-12-23 17:00 | N | Y | replace crossarms | Line | 7L32 (862s South Bezanson - 813s Little Smoky) | replace crossarms | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition,Affects Cranking Path
ENMAX | 162.1TR (ENMAX 162s Beddington) | 2019-12-23 08:00 | 2019-12-23 18:00 | N | Y | top up LTC oil then do samples and checks | Transformer | 162.1TR (ENMAX 162s Beddington) | top up LTC oil in order to clear intermittent LTC oil level alarm. Oil sampling LTC, Check reversing switch. Urgent outage required | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 861S 602T (861S Eurekariver) | 2019-12-24 12:00 | 2020-04-16 17:00 | N | N | forced outage, low gas pressure | Transformer | 861S 602T (861S Eurekariver) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-01-01 08:00 | 2020-12-31 18:00 | N | N | 29L3-167, 29L3-141 , 29PL3-63, 29PL3-183, 29PT-241 & 29PL7-4, 29PP-47 & 29PT-576, 29PP-46 & 29PT-575, 144KV NODE,29PT-246, 144KV NODE,29PT-238, 29PT-257 & 29PL7-4,29PT-260 & 29PL7-4, 29PT-250&29PL7-3,29PT-236 & 29PL7-3,29PL3-153/152/196, 29PT-128 & 29PL7-10 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
Medicine Hat, CMH | MH69s3 MH138_317 (MH69s3 South Ridge), MH69s3 MH69_304 (MH69s3 South Ridge), 20L (MH69S-6 Riverview - MH69S-3 South Ridge) | 2020-01-06 07:00 | 2020-01-10 16:00 | N | N | switches maintenance | Circuit Breaker, Line |  |  | For Information Only
EPCOR | 987s CC24 (987s Clover Bar) | 2020-01-06 07:00 | 2020-01-06 17:00 | N | N | cutover of new BF protection and relay maintenance op-checks | Circuit Breaker | 987s CC24 (987s Clover Bar) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ATCO | 740S H.R.Milner | 2020-01-06 08:00 | 2020-01-13 16:00 | N | N | replace 700PT1 | Station |  | Replace 700PT1 | Pre-Condition
ALTALINK, EPCOR | 1139L (367s Harry Smith - 816s Petrolia) | 2020-01-06 08:00 | 2020-02-11 17:00 | N | Y | cutting in EPCOR new sub (Riverview) to Altalink 1139L | Line | P1695 Riverview project | cutting in EPCOR new sub (Riverview) to Altalink 1139L, and the line gets renumbered to 1164L going to Epcor E816s and Stays 1139L going to Altalink 367s | Overload, Pre-Condition,Affects Cranking Path
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2020-01-06 08:00 | 2020-01-09 17:00 | N | Y | replacing structures and crossarms | Line | 7L64 (930s Arcenciel - 7L64D5) | Contractor replacing structures and crossarms | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ENMAX | 47.1TR (ENMAX 47) | 2020-01-06 08:00 | 2020-01-08 16:00 | N | N | T-60 upgrade phase 2. 47.1TR T60, internal battery replacement and check reversing switch | Transformer | 47.1TR (ENMAX 47) | T-60 Upgrade Phase 2. 47.1TR T60 Internal Battery Replacement, Check reversing switch | For Information Only
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2020-01-06 09:00 | 2020-01-14 13:00 | N | Y | 7L63 crossarm replacements | Line | 7L63 (788s Hotchkiss - 783s Cadotte River) | 7L63 crossarm replacements | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2033s 703C (2033s Mowat) | 2020-01-06 10:00 | 2020-01-06 15:00 | N | N | maintenance & testing | Shunts |  |  | For Information Only
EPCOR | 987s CH724 (987s Clover Bar) | 2020-01-07 07:00 | 2020-01-07 17:00 | N | N | cutover of new BF protection and relay maintenance op-checks | Circuit Breaker | 987s CH724 (987s Clover Bar) | Cutover of new BF protection and relay maintenance op-checks | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C3 (74s Janet) | 2020-01-07 07:30 | 2020-01-08 17:00 | N | Y | install new C3 meter | Shunts | 74s C3 (74s Janet) |  | 240 kV, Pre-Condition
CapitalPower | 7294-CAP-001 (1018s Shamrock), 7294-CAP-002 (1018s Shamrock) | 2020-01-07 08:00 | 2020-01-07 16:00 | N | N | update protection settings | Shunts |  |  | For Information Only
ATCO | 2033s 704C (2033s Mowat) | 2020-01-07 09:00 | 2020-01-07 15:00 | N | N | maintenance & testing | Shunts |  |  | For Information Only
EPCOR | 72RS5 (Rossdale - Strathcona), Strathcona T1 (Strathcona) | 2020-01-08 07:00 | 2020-01-12 17:00 | N | N | relay maintenance op-checks | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s CK725 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale) | 2020-01-08 07:00 | 2020-01-08 17:00 | N | N | cutover of new breaker fail protection and relay maintenance | Circuit Breaker, Line | 72CK12 (987s Clover Bar - Kennedale) | cutover of new breaker fail protection and relay maintenance op-checks | Creates Radial Feeds, Firm Load Loss
ALTALINK | 957L (72s Leismer - 723s Christina Lake) | 2020-01-08 07:00 | 2020-01-08 18:00 | N | Y | urgent fire mitigation on str 115 | Line | 957L (72s Leismer - 723s Christina Lake) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 1.82L (ENMAX 1 - ENMAX 5), 5.1TR (ENMAX 5), 5.6TR (ENMAX 5), 5.8TR (ENMAX 5) | 2020-01-08 08:00 | 2020-01-09 16:00 | N | N | maintenance on HV SW | Line, Transformer | 1.82L (ENMAX 1 - ENMAX 5) | HV SW maint. MD-5.1TR. MD-5.8TR. MD-5.6TR. Check reversing switch 5.6TR, 5.8TR, 5.1TR. Oil sampling 5.8TR | Pre-Condition
ATCO | 722s 703C (722s Crystal Lake) | 2020-01-08 09:00 | 2020-01-08 16:00 | N | N | maintenance & testing | Shunts |  | 722S 703C unavailable for the duration of work | For Information Only
ATCO | 7L128 (802s Michichi Creek - 963s Coyote Lake) | 2020-01-08 10:00 | 2020-01-08 14:00 | N | N | urgent permanent repair of temporary shield wire fix | Line |  | Permanent Repair of temporary shield wire fix | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House), 262s 717E (262s Rocky Mountain House), 262s T2 (262s Rocky Mountain House) | 2020-01-09 07:00 | 2020-01-09 18:00 | N | N | urgent replacement of DC distribution box JB4 | Line, Circuit Breaker, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 754L (118s Canmore - 437s Baymag) | 2020-01-09 07:00 | 2020-01-09 18:00 | N | N | urgent fire mitigation and maintenance on strs #118 & 122 | Line | 754L (118s Canmore - 437s Baymag) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s CK726 (987s Clover Bar), 72CK13 (987s Clover Bar - Kennedale) | 2020-01-09 07:00 | 2020-01-09 17:00 | N | N | cutover of new BF protection and relay maintenance op-checks | Circuit Breaker, Line | 72CK13 (987s Clover Bar - Kennedale) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 47.2TR (ENMAX 47) | 2020-01-09 08:00 | 2020-01-10 16:00 | N | N | upgrade T-60 phase 2 | Transformer | 47.2TR (ENMAX 47) | T-60 Upgrade Phase 2. Check reversing switch | For Information Only, Pre-Condition
ALTALINK | 777L (245s Seebe - 48s Pocaterra) | 2020-01-09 08:15 | 2020-01-09 17:45 | N | Y | test PLC on 777L | Line | webOMS ID 8075629 |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 754s 702C (754s Ksituan River) | 2020-01-09 10:00 | 2020-01-09 16:00 | N | N | maintenance & testing | Shunts |  | 754S 702C unavailable for the duration of work | For Information Only
ALTALINK | 789L (818s Winefred - 1034s Margie) | 2020-01-10 07:00 | 2020-01-11 18:00 | N | Y | urgent fire mitigation change insulators on Str 185, 188, 194, 230 and 237 scheduled | Line | 789L (818s Winefred - 1034s Margie) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 754L (245s Seebe - 754L65A) | 2020-01-10 07:00 | 2020-01-11 18:00 | N | N | urgent fire mitigation; scope of work consists maintenance on Strs #10, 17, 20, 24, 39, 42 & 56 | Line | 754L (245s Seebe - 754L65A) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 789L (898s Heart Lake - 1034s Margie) | 2020-01-12 07:30 | 2020-01-12 17:30 | N | Y | urgent fire mitigationlive line work on str 185, 188 | Line | 789L (818s Winefred - 1034s Margie) |  | For Information Only, Pre-Condition
ALTALINK | 511s SVC Plus (511s Crossings), 511s 1552 (511s Crossings) | 2020-01-13 08:30 | 2020-01-16 17:30 | N | Y | install snubber for SVC+ expansion tank sensors and yearly maintenance | Shunts, Circuit Breaker | 511s SVC Plus (511s Crossings) |  | 240 kV, Pre-Condition
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2020-01-13 09:30 | 2020-01-26 18:30 | N | N | 174L rebuild from structure #442 to 471 | Line | 174L (197s Bardo - 289s Saunders Lake) |  | Over/Under Voltage, Pre-Condition
ALTALINK | 63s 51 (63s Red Deer) | 2020-01-13 10:00 | 2020-01-20 16:30 | N | N | breaker maintenance | Circuit Breaker | 63s 51 (63s Red Deer) | Migrate and commission all 63s51 breaker & breaker fail alarms, status, controls, metering and remote access to new RTU and LAN. 63s51 (138KV bus tie breaker) out of service. Loss of visibility or possible false status and alarms for associated equipment during cut over and commissioning tests. Scheduled By: Ray Gauthier Requested By: John Denton Contact #: 403-604-7931 Issue to: Same Contact #: Same | For Information Only, Pre-Condition
VISIONREQ | 354s DVAR2 (354s Summerview) | 2020-01-14 10:00 | 2020-01-14 13:00 | N | N | maintenance | Shunts |  |  | For Information Only
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2020-01-15 08:00 | 2020-01-15 17:10 | N | N | forced outage due to oil leak | Line | Namao T3 (Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 5s 1152 (5s East Calgary) | 2020-01-15 08:00 | 2020-01-21 17:00 | N | Y | forced outage low SF6 | Circuit Breaker |  |  | 240 kV
ENMAX | 31.1TR (ENMAX 31) | 2020-01-15 08:00 | 2020-01-15 16:00 | N | N | maintenance | Transformer |  | Repair Cut Lightning Arrestor Ground. Check reversing switch. | For Information Only
ENMAX | 31.1C (ENMAX 31) | 2020-01-15 09:00 | 2020-01-20 16:00 | N | N | urgent SF6 pressure low alarm | Shunts |  |  | Pre-Condition
ALTALINK | 320p 3152 (320p Keephills) | 2020-01-15 11:00 | 2020-01-16 16:00 | N | Y | urgent SF6 top up on 320p3152 to address the low gas alarm | Circuit Breaker |  |  | Pre-Condition, Contingency Requires Mitigation, 500 kV
ATCO | 755s 903 (755s Cordel) | 2020-01-15 11:30 | 2020-01-20 16:00 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV
EPCOR | Strathcona T3 (Strathcona) | 2020-01-19 07:00 | 2020-01-19 15:00 | N | N | outage to T3 required for relay maintenance op-checks | Transformer | Strathcona T3 (Strathcona) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 739s 702T (739s Edith Lake) | 2020-01-19 14:30 | 2020-01-31 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
EPCOR | 987s T1 (987s Clover Bar) | 2020-01-20 07:00 | 2020-01-24 17:00 | N | Y | maintenance | Transformer | 987s T1 (987s Clover Bar) | Cutover of new BF protection and relay maintenance op-checks | 240 kV, Contingency Requires Mitigation
EPCOR | Rossdale RR723 (Rossdale) | 2020-01-20 07:00 | 2020-01-20 17:00 | N | N | relay maintenance | Circuit Breaker | Rossdale R723 (Rossdale) | Outage to RR723 breaker for relay maintenance op-checks | For Information Only
ALTALINK | 90L (115s Mt. Allan - 32s Barrier) | 2020-01-20 07:00 | 2020-01-22 18:00 | N | N | urgent fire mitigation | Line | 90L (115s Mt. Allan - 32s Barrier) | Urgent fire mitigation; Scope of work consists of replacing Str #2 & 39 along with maintenance work on Str #48 | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | ENMAX 8 138kV Bus, 8.1TR (ENMAX 8), 8.2TR (ENMAX 8) | 2020-01-20 08:00 | 2020-04-15 16:00 | N | N | installation of new switchgear and protection | Bus, Transformer | ENMAX 8 138kV Bus | DCTRP. Outage#1 Installation of new switchgear and protection on 138kV ring. 2.84L not connected 8MD138-2.84 to remain open on return to service. Network crew required for alternates. Grounds applied to 6a81, 6a82 after GOI issued. | For Information Only
ENMAX | 11.81L (ENMAX 13 - ENMAX 11), 13.82L (ENMAX 22 - ENMAX 13), 13.60L (ENMAX 27 - ENMAX 13), 13.4TR (ENMAX 13), 13.2TR (ENMAX 13) | 2020-01-20 08:00 | 2020-01-22 18:00 | N | N | switch maintenance | Line, Transformer | 11.81L (ENMAX 13 - ENMAX 11), 13.82L (ENMAX 22 - ENMAX 13) | HV SW maint SW63, SW66, SW68, SW84, SW85, SW86, SW87, SW88, MD-13.2TR, MD-13.4TR. Check reversing sw. 13.2TR. 13MD138-13.2TR North Phase Whip Requires Replacement | Creates Radial Feeds, Firm Load Loss
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2020-01-20 08:00 | 2020-02-03 12:00 | N | Y | Contractor replacing structures and crossarms | Line | 7L64 (747s Bassett - 930s Arcenciel), 7L64 (748s Haig River - 747s Bassett), 7L64 (748s Haig River - 779s Chinchaga River) | Contractor replacing structures and crossarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
Syncrude | Aurora 222 (Aurora) | 2020-01-20 08:00 | 2020-01-27 22:00 | N | Y | maintenance | Circuit Breaker |  | Urgent Significant Outage: Circuit Breaker#52-222 (260KV) in G01 Substation at Aurora outage is required due to SF6 gas leak, breaker is currently inoperable Following MOD's will be operated: 222A, 222B (in G01 Substation) | 240 kV
ENMAX | 14.2TR (ENMAX 14) | 2020-01-20 08:00 | 2020-01-23 16:00 | N | N | Investigate and repair | Transformer |  |  | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-01-20 08:30 | 2020-02-07 17:00 | Y | Y | refurbishment project | Line | 1L274 (48s Pocaterra - Britt Creek) | Refurbishment project - replace structures and related components. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2020-01-20 09:00 | 2020-01-28 17:00 | N | Y | 7L63 crossarm replacements | Line | 7L63 (788s Hotchkiss - 783s Cadotte River) | 7L63 crossarm replacements | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 115s T2 (115s Mt.Allan) | 2020-01-20 09:00 | 2020-01-22 15:00 | N | N | install bird coverup on new equipment | Transformer | 115s T2 (115s Mt.Allan) P2023 | FortisAlberta Kananaskis Area Reliability Project:Install Bird Coverup on new 25kV Bus 2 equipment. | For Information Only
ATCO | 7L159 (948s Heatburg - 7L159 tap) | 2020-01-20 10:00 | 2020-01-24 16:00 | N | N | change arms and insulators | Line |  | To change Arms and Insulators WO# 1021065 Task C.07.001 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
EPCOR | Strathcona S722 (Strathcona), Strathcona S723 (Strathcona), Strathcona T2 (Strathcona) | 2020-01-21 07:00 | 2020-01-23 16:00 | N | N | relay maintenance | Circuit Breaker, Transformer | Strathcona T2 (Strathcona) | Outage to Tx2 required for relay maintenance op-checks | For Information Only
EPCOR | Rossdale RW727 (Rossdale), 72RW3 (Rossdale - Woodcroft) | 2020-01-21 07:00 | 2020-01-21 17:00 | N | N | relay maintenance | Circuit Breaker, Line | Rossdale RW727 (Rossdale) | Outage to RW727 breaker for relay maintenance op-checks | Creates Radial Feeds, Firm Load Loss
ENMAX | 31.84L (ENMAX 31 - ENMAX 32) | 2020-01-21 07:00 | 2020-01-21 09:00 | N | N | upgrade 32s RTU | Line |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | For Information Only
ALTALINK | 895s T2 (895s Suffield) | 2020-01-21 08:00 | 2020-01-23 16:00 | N | N | re-install the single-phase repaired VR for VR1 | Transformer | 895s T2 (895s Suffield) | Re-install the single-phase repaired VR for VR1. New conductor will be installed from Tx 18608 to the VR. Close open points and remove jumper. | For Information Only, Pre-Condition
BLACKSPRING | 485s DVAR1 (485s Blacksprings), 485s DVAR2 (485s Blacksprings) | 2020-01-21 08:00 | 2020-01-23 15:00 | N | N | repair and replacement of failed inverter trays on dstatcom | Shunts |  |  | For Information Only
ALTALINK | 5s 1152 (5s East Calgary) | 2020-01-21 08:00 | 2020-01-21 17:00 | N | Y | urgent investigate possible leaking CT(s) and top up | Circuit Breaker |  | investigate possible leaking CT(s) and top up. This is in response to real time issue 01/15/2020 11:00 when 5s1152 was taken OOS | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | D05 T1 (D05 Syncrude), D05 519 (D05 Syncrude), D05 511 (D05 Syncrude), D05 71 (D05 D05) | 2020-01-21 08:00 | 2020-01-21 19:00 | N | Y | urgent troubleshooting of T1 gas alarm | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 347s 720X (347s Fox Creek), 720L (347s Fox Creek - 397s Benbow) | 2020-01-21 08:15 | 2020-01-21 17:45 | N | N | switch repairs - 347s13 | Circuit Breaker, Line | 720L (347s Fox Creek - 397s Benbow) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 26.81L (ENMAX 32 - ENMAX 26) | 2020-01-21 09:00 | 2020-01-21 11:00 | N | N | upgrade 32s RTU | Line |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 77s 452 (77s Sagitawah) | 2020-01-21 10:00 | 2020-01-22 17:00 | N | N | relay setting changes and functional testing | Circuit Breaker | 77s 452 (77s Sagitawah) | Settings Changes of Sync Check and Functional Testing on 77s452 CUH90 relay.Single breaker outage in breaker-and-a-half scheme. | Contingency Requires Mitigation
ALTALINK | 158s 821E (158s Vauxhall), 421s 821W (421s Hays), 821L (158s Vauxhall - 421s Hays) | 2020-01-21 10:30 | 2020-01-21 15:30 | N | N | re-attach PLC voltage sensing cable | Circuit Breaker, Line | 821L (158s Vauxhall - 421s Hays) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (ENMAX 32 - ENMAX 40) | 2020-01-21 11:00 | 2020-01-21 13:00 | N | N | upgrade 32s RTU | Line |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32B138-32BT5 (ENMAX 32) | 2020-01-21 13:00 | 2020-01-21 15:00 | N | N | upgrade 32s RTU | Circuit Breaker |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALPAC | 282S Grassland (Alpac) | 2020-01-21 17:30 | 2020-01-21 22:30 | N | N | TELUS maintenance | Station |  | Telus will be performing maintenance on our plants fibre line which will impact our phone system. Between 5:30pm and 10:30pm on January 21. Please use our backup phone line 780-525-2578 for communication with our control room. | Affects Reserves, Prevents Normal Events
AESO-SC | OATI | 2020-01-21 18:00 | 2020-01-21 19:00 | N | N | switching from one Data Centre to another | SCInternal |  |  | For Information Only
EPCOR | 987s CGB1 (987s Clover Bar) | 2020-01-22 07:00 | 2020-01-23 16:00 | N | Y | breaker work | Circuit Breaker |  |  | For Information Only
ATCO | ALC01L (409s Shell Scotford - 408s Air Liquide Scotford) | 2020-01-22 07:00 | 2020-01-22 11:45 | N | Y | work on dead end insulators and corona rings | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 32.1TR (ENMAX 32) | 2020-01-22 07:00 | 2020-01-22 09:00 | N | N | 32s RTU upgrade, commission CAC/OAC circuits | Transformer |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | For Information Only
EPCOR | 72RV2 (Rossdale - 511s Victoria), Rossdale RV728 (Rossdale) | 2020-01-22 07:00 | 2020-01-22 17:00 | N | N | relay maintenance op-checks | Line, Circuit Breaker | 72RV2 (Rossdale - 511s Victoria) | Outage to RV728 outage for relay maintenance op-checks | For Information Only, Pre-Condition
ENMAX | 32.2TR (ENMAX 32) | 2020-01-22 09:00 | 2020-01-22 11:00 | N | N | 32s RTU upgrade, commission CAC/OAC circuits | Transformer |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | For Information Only
ALTALINK | 575s 719N (575s Sundre), 719L (575s Sundre - 378s Shell Caroline) | 2020-01-22 10:00 | 2020-01-23 17:00 | N | Y | settings changes of sync check and functional testing on CUH90 relay for 575s719N | Circuit Breaker, Line | 719L (575s Sundre - 378s Shell Caroline) | Settings Changes of Sync Check and Functional Testing on CUH90 relay for 575s719N. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.3TR (ENMAX 32) | 2020-01-22 11:00 | 2020-01-22 13:00 | N | N | 32s RTU upgrade, commission CAC/OAC circuits | Transformer |  | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | For Information Only
ATCO | ALC02L (409s Shell Scotford - 879s Scotford Upgrader) | 2020-01-22 12:15 | 2020-01-22 17:15 | N | Y | work on dead end insulators and corona rings | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ATCO | 2029s ACF11 (2029s Heathfield) | 2020-01-22 15:15 | 2020-01-24 19:42 | N | Y | forced outage | Shunts |  |  | 500 kV, Prevents Normal Events
ALTALINK | 115s T1 (115s Mt.Allan) | 2020-01-22 16:00 | 2020-01-23 16:00 | N | N | install bird cover-up | Transformer | 115s T1 (115s Mt.Allan) P2023 | FortisAlberta Kananaskis Area Reliability Project:Install Bird Coverup on new 25kV Bus 1 equipment. | For Information Only
ALTALINK | 172L (83s Taber - 172L944A) | 2020-01-23 07:00 | 2020-01-29 17:00 | N | Y | urgent fire mitigation; scope of work includes replacing structures #874 & 875 | Line | 172L (83s Taber - 172L944A) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2020-01-23 07:00 | 2020-01-25 18:00 | N | N | urgent line clearance mitigation work str 37 & 44 | Line | 726L (37s North Calder - 71s Lamoureux) |  | Overload, Pre-Condition
EPCOR | 72RV4 (Rossdale - 511s Victoria) | 2020-01-23 07:00 | 2020-01-24 17:00 | N | N | relay maintenance op-checks | Line | 72RV4 (Rossdale - 511s Victoria) |  | Overload, Pre-Condition
ENMAX | 15.60L (ENMAX 21 - ENMAX 15), 15.1TR (ENMAX 15) | 2020-01-23 08:00 | 2020-01-24 18:00 | N | N | switch maintenance, check reversing switch, oil sampling | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.8TR (ENMAX 1) | 2020-01-23 08:00 | 2020-01-23 16:00 | N | N | breaker maintenance. oil sampling, check reversing switch | Transformer |  |  | For Information Only
ATCO | 2029s ACF13 (2029s Heathfield) | 2020-01-24 08:00 | 2021-04-24 16:00 | N | Y | forced outage repairs | Shunts | 2029s ACF13 (2029s Heathfield). Outage extended due to COVID-19. CT is on order from Spain, no estimated delivery date due to COVID-19 | Forced outage repairs | 240 kV, For Information Only
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank) | 2020-01-25 05:00 | 2020-01-26 20:00 | N | N | installation of new transmission structures near existing 72 kV line | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 72RG7 (Rossdale - Garneau), Rossdale RG725 (Rossdale) | 2020-01-26 07:00 | 2020-01-26 12:00 | N | N | relay maintenance op-checks | Line, Circuit Breaker | 72RG7 (Rossdale - Garneau) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
BCH | 5L77 (Revelstoke - Ashton Creek) | 2020-01-26 11:00 | 2020-01-26 16:00 | N | Y | BC generator test - does not affect AB ATC | Line | Peak COS outage ID: 1-00608392 (old) Peak Path COS ID: 1-00608445 (E>W) (old), 1-00608447 (W>E) (old) |  | Limits ATC, 500 kV
EPCOR | Rossdale RG7210 (Rossdale), 72RG1 (Rossdale - Garneau) | 2020-01-26 12:00 | 2020-01-26 17:00 | N | N | relay maintenance op-checks | Circuit Breaker, Line | 72RG1 (Rossdale - Garneau) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.3TR (ENMAX 32) | 2020-01-27 07:00 | 2020-01-27 11:00 | N | N | upgrade 32s RTU | Transformer | 32.3TR (ENMAX 32) | 32s RTU upgrade. Commission CAC/OAC circuits. Control center will have no control on equipment. | For Information Only
EPCOR | 814s T1 (814s Bellamy), 814s B2401 (814s Bellamy), 814s B2407 (814s Bellamy) | 2020-01-27 07:00 | 2020-01-31 17:00 | N | Y | outage to TX1 required for relay maintenance op-checks | Transformer, Circuit Breaker | 814s T1 (814s Bellamy) |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 7L84 (722s Crystal Lake - 749s Flyingshot Lake) | 2020-01-27 08:00 | 2020-01-31 16:00 | N | Y | crossarm changes | Line | 7L84 (722s Crystal Lake - 749s Flyingshot Lake) | Crossarm Changes | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 37.81L (ENMAX 38 - ENMAX 37), 38.1C (ENMAX 38), 38.2TR (ENMAX 38), 38.3TR (ENMAX 38) | 2020-01-27 08:00 | 2020-01-28 18:00 | N | N | switch maintenance | Line, Shunts, Transformer |  | HV SW maint SW81, SW82, MD-38.2TR. Check reversing Switch 38.2TR, 38.3TR **38.3TR and 38.1CAP Outage Jan 28th only. (SW83, SW87, MD-38.3TR done Jan 28th)** | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 13S Deerland | 2020-01-27 09:30 | 2020-01-30 16:30 | N | N | station service transformer outage to complete connections between station service transformer and secondary disconnects | Station |  | Complete connections between station service transformer and secondary disconnects. Cut over AC feeds to new AC distribution. Complete Demo of old TS1. | For Information Only
ALTALINK | 197s 174E (197s Bardo), 174L (197s Bardo - 395s North Holden) | 2020-01-27 10:00 | 2020-01-28 17:00 | N | N | settings changes on relay | Circuit Breaker, Line | 174L (197s Bardo - 395s North Holden) | Settings Changes of Sync Check and Functional Testing on 197s174E CUH90 relay. | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 7L159 (948s Heatburg - 7L159 tap) | 2020-01-27 10:00 | 2020-02-03 16:00 | N | N | change arms and insulators | Line | 7L159 (948s Heatburg - 7L159 tap) | To change Arms and Insulators WO# 1021065 Task C.07.001 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 13s 1452 (13s Deerland) | 2020-01-27 10:00 | 2020-01-28 17:00 | N | Y | settings changes on relay | Circuit Breaker | 13s 1452 (13s Deerland) | Settings Changes of Sync Check and Functional Testing on 13s1452 CUH90 relay.Single breaker outage in breaker-and-a-half scheme. | 240 kV, Contingency Requires Mitigation
ATCO | 2029s ACF21 (2029s Heathfield) | 2020-01-27 13:00 | 2020-02-28 16:00 | N | Y | forced outage - inspection and repair after trip | Shunts | 2029s ACF21 (2029s Heathfield) | Forced outage - Inspection and repair after trip | 240 kV, For Information Only
BCH | 5L52 (Ingledow - Custer) | 2020-01-28 07:00 | 2020-01-30 19:00 | N | Y | BPA work | Line | 5L52 (Ingledow - Custer) |  | 500 kV, Pre-Condition
ALTALINK | 788L (898s Heart Lake - 788L107A - 602L1) | 2020-01-28 07:15 | 2020-01-29 17:45 | N | Y | 788L components (str's 151-282) | Line | 788L (898s Heart Lake - 788L107A - 602L1) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ENMAX | 36.3TR (ENMAX 36) | 2020-01-28 08:00 | 2020-01-28 16:00 | N | N | relay testing. | Transformer | 36.3TR (ENMAX 36) |  | For Information Only
ALTALINK | 113L (20s Ghost - 33s Spray) | 2020-01-28 08:00 | 2020-01-28 18:00 | N | N | Replace transmission line span between Substation deadend and 1st T-line structure. | Line | 113L (20s Ghost - 33s Spray) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss,Affects Cranking Path
ALTALINK | 421s T2 (421s Hays) | 2020-01-28 09:00 | 2020-01-29 10:00 | N | N | maintenance | Transformer | 421s T2 (421s Hays) | CT Cable demolition between protection B87/T2 and 7330/T2, Terminate two new CT cables to insert the new A27/L6 DER between B87/T2 and 7330/T2, do CT Loop Check and Saturation. Trip/Functional Testing of 421s27 Airbreak via 652 Breaker Fail Relay 67/67N/79/81/96/L6 (467L) also needs to be out of service during this time. | For Information Only
ATCO | 800s 501C (800s Friedenstal), 800s 501 (800s Friedenstal), 800s 501C2 (800s Friedenstal) | 2020-01-28 15:30 | 2020-02-21 16:00 | N | N | forced outage | Shunts, Circuit Breaker | 800s 501C2 (800s Friedenstal), 800s 501 (800s Friedenstal), 800s 501C (800s Friedenstal) |  | For Information Only
ALTALINK | 892L (895s Suffield - 244s Bowmanton) | 2020-01-29 07:00 | 2020-01-30 18:00 | N | N | components/structure replacements (structures #40 - 248) | Line | 892L (895s Suffield - 244s Bowmanton) | Components/Structure Replacements (Structures #40 - 248) | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ENMAX, ALTALINK | 918L (281s Johnson - 162s Beddington), 162s 240-RB132 (162s Beddington), 162s 240-RB133 (162s Beddington) | 2020-01-29 07:15 | 2020-02-08 16:45 | N | Y | component replacement and installing interphase spacers on 918L circuit between structures 791-828 | Line, Circuit Breaker | 918L (281s Johnson - 162s Beddington) | Performing component replacement and installing interphase spacers on 918L circuit between structures 791-828. Portion of circuit parallels 771L on same towers and requires a reclosure block when work is taking place. | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 150L (20s Ghost - 150L46) | 2020-01-29 08:00 | 2020-01-29 19:00 | N | N | replace transmission line | Line | 150L (20s Ghost - 150L46) | Replace transmission line span between Substation deadend and 1st T-line structure. | Creates Radial Feeds, Pre-Condition
ALTALINK | 61s 836N (61s Lodgepole), 836L (61s Lodgepole - 283s Violet Grove) | 2020-01-29 10:00 | 2020-01-30 17:00 | N | Y | settings changes of sync check relay and functional testing | Circuit Breaker, Line | 61s 836N (61s Lodgepole), 836L (61s Lodgepole - 283s Violet Grove) | Settings Changes of Sync Check and Functional Testing on 61s836N CUH90 relay. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 13s 1652 (13s Deerland) | 2020-01-29 10:00 | 2020-01-30 17:00 | N | Y | settings changes of sync check and functional testing | Circuit Breaker | 13s 1652 (13s Deerland) | Settings Changes of Sync Check and Functional Testing on 13s1652 CUH90 relay.Single breaker outage in breaker-and-a-half scheme. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 250p11 (250p Bighorn Plant) | 2020-01-29 11:00 | 2020-01-29 15:00 | N | Y | maintenance | Switch | 250p11 (250p Bighorn Plant) |  | Restricts Generation
ALTALINK | 67s T1 (67s Stirling), 67s 31 (67s Stirling) | 2020-01-30 07:00 | 2020-01-30 19:00 | N | Y | install bird coverup, salvage bus arrestors | Transformer, Circuit Breaker |  |  | Pre-Condition, Restricts Generation
ALTALINK | 859L (20s Ghost - T793s Horse Creek) | 2020-01-30 08:00 | 2020-01-30 19:00 | N | N | replace transmission line span between substation deadend and 1st t-line structure | Line | 859L (20s Ghost - T793s Horse Creek) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p22 (250p Bighorn Plant) | 2020-01-30 09:00 | 2020-01-30 13:00 | N | Y | maintenance | Switch | 250p22 (250p Bighorn Plant) | Brushgear | Restricts Generation
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39) | 2020-02-01 08:00 | 2020-02-02 18:00 | N | N | HV SW maint SW86, SW87, MD-39.82 | Line | 39.82L (ENMAX 162 Beddington - ENMAX 39) |  | Overload
ENMAX | 2.1TR (ENMAX 2) | 2020-02-01 08:00 | 2020-02-01 18:00 | N | N | substation upgrades | Transformer | 2.1TR (ENMAX 2) | Substation Building Upgrades. Install Roxtec plugs in ducts. (Weekend only) | For Information Only
ENMAX | 162.4TR (ENMAX 162 Beddington), 162s 138-RB92 (162s Beddington), 162s 138_RB94 (162s Beddington) | 2020-02-03 01:30 | 2020-02-05 01:30 | N | N | switch maintenance, LTC counter replacement | Transformer, Circuit Breaker | 162.4TR (ENMAX 162 Beddington) | HV SW maint SW MD, SW106, SW107, SW109, MD-162.4TR. Check reversing sw. Replace RTD probe. LTC Counter replacement. | For Information Only, Pre-Condition
EPCOR | 814s B2402 (814s Bellamy), 814sB2406 (814s Bellamy), 814s T2 (814s Bellamy) | 2020-02-03 07:00 | 2020-02-07 17:00 | N | Y | relay maintenance op-checks | Circuit Breaker, Transformer | 814s T2 (814s Bellamy) | Outage to TX2 required for relay maintenance op-checks | 240 kV, Over/Under Voltage, Pre-Condition
EPCOR | 987s CS2 (987s Clover Bar), 987s SST2 (987s Clover Bar) | 2020-02-03 07:00 | 2020-02-17 17:00 | N | N | protection upgrade and relay maintenance | Circuit Breaker, Transformer | 987s CS2 (987s Clover Bar) | CS2 outage required for relay protection upgrade and relay maintenance op-checks | For Information Only
ENMAX | 22.1TR (ENMAX 22) | 2020-02-03 08:00 | 2020-02-05 16:00 | N | N | substation building upgrades | Transformer | 22.1TR (ENMAX 22) | Substation Building Upgrades. Install Roxtec plugs in ducts | For Information Only
ENMAX | 23.3TR (ENMAX 23) | 2020-02-03 08:00 | 2020-02-04 16:00 | N | N | T-60 upgrade phase 2, check reversing switch | Transformer | 23.3TR (ENMAX 23) |  | For Information Only
EPCOR | 1139L (367s Harry Smith - EPCOR Riverview), 1164L (EPCOR Riverview - 816s Petrolia), EPCOR Riverview | 2020-02-03 08:00 | 2020-02-16 16:00 | N | N | EPCOR Riverview Energization. ISD: Feb 10, 2020. | Line, Station
ATCO | 13L50 (2029s Heathfield - 2075s Newell), 2029s 1205 (2029s Heathfield), 2029s 1206 (2029s Heathfield), 2075s 916 (2075s Newell), 2075s 917 (2075s Newell) | 2020-02-03 08:00 | 2020-02-07 17:00 | N | Y | emergency repair broken OPGW | Line, Circuit Breaker | 13L50 (2029s Heathfield - 2075s Newell) | Repair broken OPGW. Remove and restring five spans of fibre optics and then splice. Currently P1 is isolated and no south fibre available, microwave communications only resulting in loss of redundancy. EATL will be unavailable for transfer for the duration of the outage. | 500 kV, Pre-Condition
ENMAX | 14.2TR (ENMAX 14) | 2020-02-03 08:00 | 2020-02-07 16:00 | N | N | adjust breaker alignment | Transformer |  | Adjust breaker alignment. 14 Sub - 14SW16 - Operating handle stopper bolts bent. Finish commissioning 14 sub RTU Upgrade. OH crew required to remove risers. | For Information Only
ATCO | 9L43 (888s Dover - 874s McKay River) | 2020-02-03 08:00 | 2020-02-11 16:00 | N | Y | customer requested to complete repairs at 874s and fix insulators on structure #3 and structure #10 | Line | 9L43 (888s Dover - 874s McKay River) | TC Energy has requested 9L43 OOS for repairs to be completed at 874S MacKay IPP Date & time have been selected by customer in coordination with their shutdown, generation OOS for duration. ATCO is planning to complete some line work during this planned outage and fix Structure #3 and Structure #10 insulators, | 240 kV, Restricts Generation
ATCO | 7L63 (788s Hotchkiss - 783s Cadotte River) | 2020-02-03 09:00 | 2020-02-10 17:00 | N | Y | 7L63 crossarm replacements | Line | 7L63 (788s Hotchkiss - 783s Cadotte River) | 7L63 crossarm replacements | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 71s 1552 (71s Lamoureux) | 2020-02-03 10:00 | 2020-02-04 17:00 | N | Y | settings changes of sync check and functional testing | Circuit Breaker | 71s 1552 (71s Lamoureux) | Settings Changes of Sync Check and Functional Testing on 71s1552 CUH90 relay.Single breaker outage in breaker-and-a-half scheme. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 63s T3 (63s Red Deer) | 2020-02-03 10:00 | 2020-02-06 15:00 | N | N | migrate and commission protections to the new RTU and LAN | Transformer | 63s T3 (63s Red Deer) | Migrate and commission all T3 (TX18620), VR1 (TX18746,TX18747,TX18748), 63s26 (1152) & VT11 protections, breaker fail protections, breaker, status, controls, alarms, metering, to the new RTU and LAN. Replace 63s29 (1089) air break control module, commission alarms control and status to new RTU. Replace and commission T3 SCADA meter.T3 TX18620 and 25KV Bus 1, breaker control and associated T3 transformer protections will be out of service. Loss of visibility or possible false status and alarms for associated equipment during cut over and commissioning tests. | For Information Only
ALTALINK | 310P T36 (310p Sundance) | 2020-02-03 11:30 | 2020-02-26 17:00 | N | Y | urgent repair of oil leaks | Transformer | 310P T36 (310p Sundance) |  | 240 kV, Pre-Condition
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2020-02-03 12:15 | 2020-02-06 17:45 | N | Y | replace components str's range 9-258 | Line | 794L (157s Lac La Biche - 819s Whitby Lake) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
AESO-SC | OATI | 2020-02-03 17:45 | 2020-02-03 19:30 | N | N | schedule provider maintenance | SCInternal |  | OATI staff will be adjusting routing for traffic coming in over OATINET in preparation for scheduled provider maintenance. There may be brief disruptions for OATINET connections to OATI services on Monday February 03, 2020 at 5:45  7:30PM (MS) when the re-routing takes place near the beginning and end of the maintenance. Ensure that NSI in WIT is aligned with NSI in EMS and if a mismatch does occur enable back-scheduler prior to start of the ramp and proceed with SCP 302 1.10.3 | For Information Only
ALTALINK | 461L (212s N.E. Lacombe - 198s Blackfalds) | 2020-02-04 07:00 | 2020-02-06 17:00 | N | Y | replace 461L Structures 33 & 34 for line clearance mitigation | Line | 461L (212s N.E. Lacombe - 198s Blackfalds) |  | Creates Radial Feeds, Firm Load Loss, Restricts Generation
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank), 29PL6-4 (836s Steepbank - 29EDD-1) | 2020-02-04 08:00 | 2020-02-18 16:00 | N | N | line relocation (P2127) ISD Feb 11, 2020 | Line
ENMAX | 162.3TR (ENMAX 162 Beddington), 162s 138-RB85 (162s Beddington), 162s 138-RB86 (162s Beddington) | 2020-02-05 01:30 | 2020-02-07 01:30 | N | N | HV switch maintenance SW92, SW93, MD-162.3TR and check reversing switch | Transformer, Circuit Breaker | 162.3TR (ENMAX 162 Beddington) | HV SW maint SW92, SW93, MD-162.3TR. Check reversing sw. | Contingency Requires Mitigation
ATCO | 752s 701T (752s Albright&Wilson) | 2020-02-05 06:00 | 2020-02-05 08:00 | N | N | hot spot repair | Transformer | 752s 701T (752s Albright&Wilson) | 752S 701T Hot Spot Repair 25KV Lightning Arrester Customer was notified. they are planning an outage this day and have agreed to a complete outage from 6am to 8am. | For Information Only
ALTALINK | 310p 152 (310p Sundance), 974L (39s Bickerdike - 310p Sundance) | 2020-02-05 07:30 | 2020-02-05 17:30 | N | Y | CT replacement | Circuit Breaker, Line | 974L (39s Bickerdike - 310p Sundance) | Replace 1 CT. Will need a 15 minute outage to 974L for energization of the CT due to safe switching requirements | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 165s T1 (165s T.M.P.L.Gainford) | 2020-02-05 07:30 | 2020-02-05 17:30 | N | N | installing U/G cables | Transformer | 165s T1 (165s T.M.P.L.Gainford) | Installing another set of U/G Cables between TMPL & Altalink | For Information Only
ENMAX | 34.1TR (ENMAX 34) | 2020-02-05 08:00 | 2020-02-06 16:00 | N | N | T-60 upgrade phase 2 and check reversing switch | Transformer | 34.1TR (ENMAX 34) | T-60 Upgrade Phase 2. Check reversing switch | For Information Only
ALTALINK | 71s 1452 (71s Lamoureux) | 2020-02-05 10:00 | 2020-02-05 17:00 | N | Y | settings changes of Sync Check | Circuit Breaker | 71s 1452 (71s Lamoureux) | Settings Changes of Sync Check and Functional Testing on 71s1452 CUH90 relay.Single breaker outage in breaker-and-a-half scheme. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2020-02-05 23:00 | 2020-02-06 04:00 | N | Y | maintenance | Switch | 62s 11 (62s Brazeau) | Brushgear and blackstart test | Restricts Generation
ALTALINK | 62s12 (62s Brazeau) | 2020-02-06 04:00 | 2020-02-06 07:00 | N | Y | maintenance | Switch | 62s12 (62s Brazeau) | Brushgear | 240 kV, Restricts Generation
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2020-02-06 09:30 | 2020-02-19 19:00 | N | N | rebuild structures | Line | 174L (197s Bardo - 289s Saunders Lake) | 174L Rebuild From Str #379 to Str#485 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, ATCO | 948L (650s Hansman Lake - 863s Paintearth), 9L948 (650s Hansman Lake - 863s Paintearth) | 2020-02-07 07:00 | 2020-02-13 18:00 | N | Y | 948L component replacements Str 4 - 186 | Line | 948L (650s Hansman Lake - 863s Paintearth) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | Victoria V728 (Victoria) | 2020-02-07 08:00 | 2020-02-07 17:00 | N | N | substation training | Circuit Breaker
ENMAX | 162s Beddington 138 kV South Bus, 162.2TR (ENMAX 162 Beddington), 162s 138-RB83 (162s Beddington), 162s 138-RB84 (162s Beddington), 162s 138-RB92 (162s Beddington) | 2020-02-08 08:00 | 2020-02-08 18:00 | N | Y | investigate and repair SW105 | Bus, Transformer, Circuit Breaker |  | Urgent outage is required on 162.2TR to repair SW105@162sub. The switch mechanism broke when they went to operate the switch. The switch is currently locked in the closed position, load flow is not restricted through the switch. | 240 kV, Pre-Condition
ENMAX | 2.3TR (ENMAX 2) | 2020-02-08 08:00 | 2020-02-08 18:00 | N | N | substation building upgrades | Transformer | 2.3TR (ENMAX 2) | substation building upgrades. Install Roxtec plugs in ducts. (Weekend only) | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel) | 2020-02-08 08:00 | 2020-02-11 13:25 | N | Y | forced outage | Shunts |  |  | Pre-Condition
ALTALINK | 895s T2 (895s Suffield) | 2020-02-08 11:03 | 2020-05-29 18:00 | N | N | forced outage | Transformer | 895s T2 (895s Suffield) |  | Pre-Condition
EPCOR | Poundmaker 2401 (Poundmaker), Poundmaker 2404 (Poundmaker), Poundmaker T3 (Poundmaker) | 2020-02-10 07:00 | 2020-02-14 17:00 | N | Y | relay maintenance and op-checks | Circuit Breaker, Transformer | Poundmaker T3 (Poundmaker) | outage to Tx3 required for relay maintenance and op-checks | 240 kV, For Information Only
EPCOR | Rossdale VHBB1 (Rossdale) | 2020-02-10 07:00 | 2020-02-10 12:00 | N | N | relay maintenance | Circuit Breaker | Rossdale VHBB1 (Rossdale) | Outage to VHBB1 breaker for relay maintenance op-checks | Pre-Condition
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2020-02-10 08:00 | 2020-02-23 17:00 | N | Y | replacing structures and crossarms | Line | 7L64 (747s Bassett - 930s Arcenciel), 7L64 (748s Haig River - 747s Bassett), 7L64 (748s Haig River - 779s Chinchaga River) | Contractor replacing structures and crossarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation, Affects Cranking Path
ENMAX | 5.1TR (ENMAX 5) | 2020-02-10 08:00 | 2020-02-11 16:00 | N | N | T-60 upgrade phase 2 | Transformer | 5.1TR (ENMAX 5) | T-60 Upgrade Phase 2 | For Information Only
ENMAX | 22.3TR (ENMAX 22) | 2020-02-10 08:00 | 2020-02-12 16:00 | N | N | substation building upgrades | Transformer | 22.3TR (ENMAX 22) | substation building upgrades. Install Roxtec plugs in ducts | For Information Only
ENMAX, ALTALINK | 932L (74s Janet - 162s Beddington), 162s 240-RB135 (162s Beddington), 162s 240-RB136 (162s Beddington) | 2020-02-10 08:00 | 2020-02-11 16:00 | N | Y | switch maintenance | Line, Circuit Breaker | 932L (74s Janet - 162s Beddington) | HV SW maint SW144, SW145, MD-932L | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
Syncrude | AL-2 (D05 Syncrude - Aurora), D05 511 (D05 Syncrude), D05 512 (D05 Syncrude), Aurora 222 (Aurora), Aurora 223 (Aurora) | 2020-02-10 08:00 | 2020-02-18 13:00 | N | Y | line repairs | Line, Circuit Breaker | AL-2 (D05 Syncrude - Aurora) | Significant Outage - AL2 powerline (260 kV) will be taken offline to perform line repairs. In G01 Substation, following will be operated to isolate AL2 line: CB # 222 and 223 MOD # 222B, 223A and 223 In D05 Substation, following will be operated to isolate AL2 line: CB # 511 and 512 MOD # 511B, 512A and 514 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 308S Albchem Beaverhill Creek, 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2020-02-10 09:00 | 2020-02-13 17:00 | N | N | CT replacement | Station, Line | 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), ALBCHEMBEAVERHILLCREEK, 776L (410s Josephburg - 308s Albchem Beaverhill Creek) | Like for like replacement of 308s773E CTs, 308s776W CTs and 308s VT1 | Creates Radial Feeds, Firm Load Loss, Overload
ATCO, ALTALINK | 7L230 (69s North Barrhead - 7L230 tap), 7L230 (7L230 tap - 743s Sarah Lake), 888AL (234s Fort Assiniboine - 7L230 tap) | 2020-02-10 10:30 | 2020-02-10 13:30 | N | Y | cut in opener J1 | Line |  | Cut in opener J1 close to 7L230 tap on 7L230 (7L230 tap - 743s Sarah Lake) to restore 234s Fort Assiniboine from 7L230 (69s North Barrhead - 7L230 tap). | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2020-02-10 12:15 | 2020-02-13 17:45 | N | Y | replace components str's range 9-258 | Line | 794L (157s Lac La Biche - 819s Whitby Lake) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | Rossdale VHBB2 (Rossdale) | 2020-02-10 13:00 | 2020-02-10 17:00 | N | N | relay maintenance | Circuit Breaker | Rossdale VHBB2 (Rossdale) | Outage to VHBB2 breaker for relay maintenance op-checks | Pre-Condition
ATCO | 7L230 (7L230 tap - 743s Sarah Lake) | 2020-02-10 13:30 | 2020-02-21 14:00 | N | Y | replace Xarms and insulators | Line | 7L230 (7L230 tap - 743s Sarah Lake) | 7L230 Xarms & Insulators | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
AESO-SC | OATI | 2020-02-10 17:15 | 2020-02-10 19:30 | N | N | conducting maintenance on the power rails | SCInternal |  |  | For Information Only
EPCOR | Rossdale T4 (Rossdale), Rossdale R724 (Rossdale), Rossdale RR729 (Rossdale) | 2020-02-11 07:00 | 2020-02-11 17:00 | N | N | relay maintenance | Transformer, Circuit Breaker | Rossdale T4 (Rossdale) | Outage to Tx4 for relay maintenance op-checks | Creates Radial Feeds, Firm Load Loss, Overload
CapitalPower | 615S Halkirk | 2020-02-11 08:00 | 2020-02-11 10:00 | N | N | RTAC software upgrade | Station |  |  | Affects Visibility
FORTIS | VXH1 Vauxhall Solar | 2020-02-11 08:00 | 2020-05-08 16:00 | N | N | P1922. 22 MW DER. ISD Feb 29, 2020 | Unit
ALTALINK | 417L (55s Olds - 281s Johnson) | 2020-02-11 08:30 | 2020-02-13 18:00 | N | Y | clearance mitigation | Line | 417L (55s Olds - 281s Johnson) |  | Restricts Generation
BCH | Natal T2 (BCH Natal) | 2020-02-11 09:00 | 2020-02-12 17:00 | N | Y | non-electrical maintenance | Transformer | Natal T2 (BCH Natal) | Transformer will then need to be isolated to perform Non-EL PN testing. | For Information Only
ALTALINK | 723s Christina Lake RTU/SCADA | 2020-02-11 10:00 | 2020-02-11 14:00 | N | N | ADAMS system and ETS system will be unavailable | Terminal Equipment |  | On January 28th 2020 from approximately 10am until 2pm, the ADAMS system and ETS system will be unavailable to the Generator Operator at CL01 Christina Lake due to network reconfiguration work. There may also be a short interruption of telephone service. AESO System Controller should first try to contact the Generator Operator on the normal telephone at 780-559-6460. If the normal phone service is interrupted, the System Controller can contact the Generator Operator on the satellite phone at 403-987-0134. | For Information Only
TRANSALTA, ALTALINK, VISIONREQ | 240s McBride Lake RTU/SCADA, 418s Ardenville RTU/SCADA, 528s Blue Trail Wind Farm RTU/SCADA, 239s Castle River RTU/SCADA, 322s Cowley Ridge RTU/SCADA, 243s Soderglen Wind Farm RTU/SCADA, 354s Summerview RTU/SCADA | 2020-02-12 | 2020-02-12 02:00 | N | N | internet service maintenance | Terminal Equipment |  |  | Affects Visibility
EPCOR | Rossdale T3 (Rossdale), Rossdale R723 (Rossdale), Rossdale R724 (Rossdale) | 2020-02-12 07:00 | 2020-02-12 17:00 | N | N | relay maintenance op-checks | Transformer, Circuit Breaker | Rossdale T3 (Rossdale) |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 39.4TR (ENMAX 39) | 2020-02-12 08:00 | 2020-02-12 16:00 | N | N | oil sampling TC and heck reversing switch | Transformer | 39.4TR (ENMAX 39) |  | For Information Only
ALTALINK | 103s 138 kV BUS 1 (103s Goose Lake), 103s 1352 (103s Goose Lake), 103s 1752 (103s Goose Lake), 103s T1 (103s Goose Lake) | 2020-02-12 08:00 | 2020-02-13 16:00 | N | Y | replace A phase PT of VT7/SS2 | Bus, Circuit Breaker, Transformer | 103s T1 (103s Goose Lake) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 5.6TR (ENMAX 5) | 2020-02-12 08:00 | 2020-02-13 16:00 | N | N | T-60 upgrade phase 2 | Transformer | 5.6TR (ENMAX 5) |  | For Information Only
VISIONREQ | 354s Summerview RTU/SCADA | 2020-02-12 09:00 | 2020-02-12 17:00 | N | N | firewall update | Terminal Equipment |  | During this time the site would not be able to respond to WPM curtailments. The Wind Control Center would still have control over substation breakers and DVAR controls. | Affects Visibility
ALTALINK | 1116L (170s Pike - 167s Ipiatik Lake) | 2020-02-12 09:00 | 2020-02-12 16:00 | N | Y | marker ball installation Str's 69-70 | Line | 1116L (170s Pike - 167s Ipiatik Lake) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Pre-Condition
AESO-SC | OATI | 2020-02-12 12:00 | 2020-02-12 14:00 | N | N | conducting maintenance on the power rails | SCInternal |  | OATI staff will be conducting maintenance on the power rails for the DMZ network rows at the Minneapolis Datacenter on Wednesday February 12th, at 12:00  14:00 (MS) . During this time, there will be some device and power source failovers. | For Information Only
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2020-02-12 22:00 | 2020-02-13 12:00 | N | N | blowout violation  line de-energized due to public safety concern | Line | 726L (37s North Calder - 71s Lamoureux) |  | Overload, Pre-Condition
EPCOR, ALTALINK | 665s TX2 (665s Dome), 909L (310p Sundance - 665s Dome) | 2020-02-13 07:00 | 2020-02-14 17:00 | N | Y | outage to TX2 required for relay maintenance op-checks | Transformer, Line | 909L (310p Sundance - 665s Dome), 665s TX2 (665s Dome) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
EPCOR | Rossdale T2 (Rossdale), Rossdale R721 (Rossdale), Rossdale R723 (Rossdale) | 2020-02-13 07:00 | 2020-02-13 17:00 | N | N | relay maintenance op-checks | Transformer, Circuit Breaker | Rossdale T2 (Rossdale) | outage to Tx2 for relay maintenance op-checks | Contingency Requires Mitigation, Firm Load Loss, Overload, Pre-Condition
SUNCOR | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank) | 2020-02-13 08:00 | 2020-02-21 20:00 | N | N | maintenance | Line | 29PL6-3 (29EDD-1 Millennium - 836s Steepbank) | 72 kV line 29PL6-3 is being relocated to create space for cogeneration project. Only line 29PL6-3 will not be available while 29PL6-4 will be supplying Steepbank Sub. 5 year PM on 29CVT- 10 and replace surge arrestors on 29PLA-189A/B/C, 10 Year 29EDD1s 1752/1852 29PL9-1 & 29PL9-2 - "B" Protection (partial elements) communication loss, "A" Protection will be available. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
BLACKSPRING | 485s DVAR2 (485s Blacksprings) | 2020-02-13 08:00 | 2020-02-14 16:00 | N | N | repair and replacement of failed inverter trays on dstatcom | Shunts |  |  | For Information Only
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2020-02-13 08:00 | 2020-02-13 20:00 | N | Y | address tap changer issue | Transformer | Mildred T6 (Syncrude Mildred Lake) | Transformer T6 (72kV/13.8kV) Outage at Plant-31 Substation is required to address tap changer issue. CB # 52-6335 and 52-635 will be operated. | Restricts Generation
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2020-02-13 08:00 | 2020-02-13 16:00 | N | N | substation building upgrades | Line | 2.81L (ENMAX 2 - ENMAX 9) | Substation Building Upgrades. Install Roxtec plugs in ducts | For Information Only
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2020-02-13 09:00 | 2020-02-13 13:00 | N | Y | trip coil testing | Line | 7L91 (715s Leming Lake - 826s Marguerite Lake), 715s 702 (715s Leming Lake) | PRC 005 Trip Coil Testing, 7L91 will require to be open ended for duration of work | Pre-Condition, Restricts Generation
ALTALINK | 68s T2 (68s Willesden Green) | 2020-02-13 09:00 | 2020-02-13 15:00 | N | Y | urgent fuse holder repair | Transformer |  | 68s AMI fuse holder broken and required to be repaired | 240 kV, For Information Only
CapitalPower | 615S Halkirk | 2020-02-13 09:00 | 2020-02-13 10:00 | N | N | reprogramming door alarms | Station |  |  | Affects Visibility
Saskpower | SaskPower A1R | 2020-02-13 22:00 | 2020-02-14 11:00 | N | Y | forced outage | Line |  |  | Limits ATC, Pre-Condition
EPCOR | 987s 69kV Bus 4 (987s Cloverbar), 72CK13 (987s Clover Bar - Kennedale), 72CH11 (Hardisty - 987s Clover Bar) | 2020-02-14 | 2020-02-14 01:00 | N | Y | emergency energization of Clover Bar SST2 | Bus, Line |  |  | Restricts Generation, Contingency Requires Mitigation, Firm Load Loss, Creates Radial Feeds
ALTALINK | 214s T1 (214s Innisfail) | 2020-02-14 07:30 | 2020-02-14 13:30 | N | N | complete trip check to 389 (214s22) MOD, complete wiring, settings changes and testing on protection | Transformer | 214s T1 (214s Innisfail)
ATCO | 7L19 (809s Louise Creek - 851s Morse River) | 2020-02-15 10:00 | 2020-02-17 14:00 | N | N | FAC line violation mitigation | Line | 7L19 (809s Louise Creek - 851s Morse River) | FAC Line Violation Mitigation | Creates Radial Feeds, Firm Load Loss
EPCOR | Poundmaker 2402 (Poundmaker), Poundmaker 2403 (Poundmaker), Poundmaker T2 (Poundmaker) | 2020-02-17 07:00 | 2020-02-21 17:00 | N | Y | relay maintenance | Circuit Breaker, Transformer | Poundmaker T2 (Poundmaker) | Outage to Tx2 required for relay maintenance and op-checks | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 765L (151s Strathmore - 419s Chestermere) | 2020-02-17 07:15 | 2020-02-18 17:45 | N | N | remove OHSW between str 197 and 200 | Line | 765L (151s Strathmore - 419s Chestermere) | Remove OHSW between STR 197 and 200, replace STR 198 and 199 cross arms with horizontal post insulators | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 2.2TR (ENMAX 2) | 2020-02-17 08:00 | 2020-02-17 16:00 | N | N | substation building upgrades | Transformer | 2.2TR (ENMAX 2) | Substation Building Upgrades. Install Roxtec plugs in ducts | For Information Only
ALTALINK, EPCOR | 38s 738W (38s East Edmonton), 738L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2020-02-17 08:30 | 2020-02-22 16:30 | N | N | upgrade protections and transfer trip scheme on 738L between 95s and 38s | Circuit Breaker, Line | 738L (38s East Edmonton - 738AL1) | Upgrade teleprotection/transfer trip scheme on 738L between 95s and 38s in preparation for future project. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.9TR (ENMAX 5) | 2020-02-18 08:00 | 2020-02-19 16:00 | N | N | upgrade T-60 phase 2 | Transformer | 5.9TR (ENMAX 5) |  | For Information Only
ENMAX | 33.83L (ENMAX 41 - ENMAX 33), 33.1TR (ENMAX 33) | 2020-02-18 08:00 | 2020-02-20 16:00 | N | N | HV SW maintenance | Line, Transformer | 33.83L (ENMAX 41 - ENMAX 33), 33.1TR (ENMAX 33) | HV SW maint SW81, SW82, SW83, MD-33.1TR. SW82 @ 33 Sub hard to open. Check reversing switch 33.1. Oil sampling MT, TC. Investigate PT connection on NGR install - 33.1TR. Replace 33.1TR LTC Lower control. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH, Medicine Hat | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights), MH69s3 MH69_308 (MH69s3 South Ridge), MH69s5 MH69_502 (MH69s5 NE Crescent Height) | 2020-02-18 08:00 | 2020-03-02 13:00 | N | N | replace insulators | Line, Circuit Breaker | MH-30L (MH69s3 South Ridge - MH69s5 NE Crescent Heights), MH69s3 MH69_308 (MH69s3 South Ridge), MH69s5 MH69_502 (MH69s5 NE Crescent Height) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 95s T1 (95s Imperal Oil Edmonton) | 2020-02-18 08:15 | 2020-02-22 16:45 | N | N | upgrade protections and transfer trip scheme on 738L between 95s and 38s | Transformer | 95s T1 (95s Imperal Oil Edmonton) | (1) Upgrade teleprotection / transfer trip scheme on 738L between 95s and 38s in preparation for future project. (2) Add supervisory control to high side T1 MOD (95s738X) | For Information Only
ATCO | 9L100 (801s Anderson - 807s Sheerness), 807s 902 (807s Sheerness), 807s 902T (807s Sheerness) | 2020-02-18 09:00 | 2020-03-27 16:00 | N | Y | maintenance & 9L100 protection upgrade | Line, Circuit Breaker, Transformer | 9L100 (801s Anderson - 807s Sheerness), 807s 902T (807s Sheerness) | 807S BKR 902 maintenance & 9L100 protection upgrade Work has been coordinated with ATCO Power and it was stated that 807S unit #2 Shutdown will occur from Feb14 to March 27, 2020, outages are dependant on 807S unit 2 shutdown Outage zone needs to expand from 9100D1 to 910B & 911B to include 910 & 911 for testing ( 2 days required) | 240 kV, Restricts Generation,Affects Cranking Path
ATCO | 7L63 (783s Cadotte River - 812s Norcen) | 2020-02-18 09:00 | 2020-02-27 12:00 | N | Y | 7l63 crossarm replacement | Line | 7L63 (783s Cadotte River - 812s Norcen) | 7L63 crossarm replacements | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 419s T1 (419s Chestermere) | 2020-02-18 09:00 | 2020-02-18 15:00 | N | N | address oil leak | Transformer | 419s T1 (419s Chestermere) | Address oil leak on T1 TX 18935 | For Information Only
ATCO | 7L66 (715s Leming Lake - 717s Ethel Lake), 715s 703 (715s Leming Lake) | 2020-02-18 11:00 | 2020-02-18 16:00 | N | Y | trip coil testing | Line, Circuit Breaker | 7L66 (715s Leming Lake - 717s Ethel Lake), 715s 703 (715s Leming Lake) | PRC 005 Trip Coil Testing, 7L66 will be open ended for duration of work | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 632PS (632s Russell) | 2020-02-18 11:30 | 2020-02-18 17:00 | N | Y | replace cabinet heater in 632s452 | Transformer | 632PS (632s Russell) | Replace cabinet heater in 632s452 | Pre-Condition
ALTALINK | 310p T30 (310p Sundance) | 2020-02-18 12:00 | 2020-03-06 08:30 | N | Y | corrosive sulphur mitigation | Transformer | 310p T30 (310p Sundance) | Corrosive Sulphur Mitigation | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2020-02-18 12:15 | 2020-02-20 17:45 | N | Y | replace components str's range 9-258 | Line | 794L (157s Lac La Biche - 819s Whitby Lake) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
AESO-SC | OATI | 2020-02-18 18:00 | 2020-02-18 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 786L (799s Coleman - Natal) | 2020-02-19 07:00 | 2020-02-23 17:00 | N | Y | Emergency Repair: install clampstar assemblies over hot sleeves and replace hot conductor on multiple spans between Str 73 - 121 | Line | 786L (799s Coleman - Natal) | Emergency Repair: Install clampstar assemblies over hot sleeves and replace hot conductor on multiple spans between Str 73 - 121 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 870L (262s Rocky Mountain House - 263s Strachan), 719L (575s Sundre - 378s Shell Caroline) | 2020-02-19 07:15 | 2020-02-21 17:45 | N | Y | emergency repair: structure/post insulators replacement (Strs 33, 133, 243) | Line | 870L (262s Rocky Mountain House - 263s Strachan), 719L (575s Sundre - 378s Shell Caroline) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK, CRRLP, PCLP | CRR1 Enel Alberta Castle Rock Wind Farm Generator Test, CRR2 Castle Rock Ridge 2 Generator Test | 2020-02-19 08:00 | 2020-02-19 12:00 | N | N | master PPC timing tests | Unit
ENMAX | 20.1TR (ENMAX 20) | 2020-02-19 08:00 | 2020-02-19 16:00 | N | N | remove, replace bearings | Transformer |  | 20.1 TR fan #8-noisy - remove, replace bearings | For Information Only
ENMAX | 2.4TR (ENMAX 2) | 2020-02-19 08:00 | 2020-02-20 16:00 | N | N | substation building upgrades | Transformer | 2.4TR (ENMAX 2) | substation building upgrades Substation Building Upgrades. Install Roxtec plugs in ducts | For Information Only
ATCO | 9L27 (863s Paintearth - 755s Cordel) | 2020-02-19 08:30 | 2020-02-19 17:00 | N | Y | clearance mitigation | Line | 9L27 (863s Paintearth - 755s Cordel) | Clearance Mitigation | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2020-02-19 08:30 | 2020-02-19 17:00 | N | Y | clearance mitigation | Line | 7L28 (717s Ethel Lake - 846s Grand Centre) | Clearance Mitigation | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L85 (803s Bullpound - 801s Anderson) | 2020-02-19 09:00 | 2020-02-19 17:00 | N | N | clearance mitigation | Line | 7L85 (803s Bullpound - 801s Anderson) | Clearance Mitigation | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 951s SVC (951s Thickwood) | 2020-02-20 08:00 | 2020-02-28 16:00 | N | Y | maintenance | Shunts | 951s SVC (951s Thickwood) | To correct deficiencies that were identified during the initial energization period of Thickwood SVC, | 240 kV
ATCO | 7L583 (970s Bourque - 715s Leming Lake) | 2020-02-20 09:00 | 2020-02-20 13:00 | N | Y | maintenance | Line | 7L583 (970s Bourque - 715s Leming Lake), 715s 701 (715s Leming Lake) | PRC 005 Trip Coil Testing, 7L583 will be open ended for duration of work | For Information Only
ATCO | 7L224 (774s Monitor - 650s Hansman Lake) | 2020-02-20 09:00 | 2020-02-20 17:00 | N | Y | Clearance Mitigation on one structure | Line | 7L224 (774s Monitor - 650s Hansman Lake) | Clearance Mitigation on one structure | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ATCO | 783s 701T (783s Cadotte River) | 2020-02-20 11:00 | 2020-02-20 16:00 | N | N | installing VFI on 5C1L | Transformer |  | Installing VFI on 5C1L, outside of 783S Cadotte River Substation replacing S17049 with new VFI, Station Outage, no station service.
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2020-02-20 22:00 | 2020-02-21 04:00 | N | N | rail tower relocate | Line | 2.83L (ENMAX 13 - 2.83L tap), 2.83L (ENMAX 2 - 2.83L tap), 2.83L (ENMAX 5 - 2.83L tap) | CP Rail Tower Relocate. Disconnect 5sub leg at t-tap. | Pre-Condition
ENMAX | 2.83L (ENMAX 5 - 2.83L tap) | 2020-02-21 04:00 | 2020-02-24 22:00 | N | N | CP Rail tower relocate, phasing required on return to service | Line | 2.83L (ENMAX 5 - 2.83L tap) |  | Pre-Condition
EPCOR | 805s J724 (805s Jasper), 72JW19 (805s Jasper - Woodcroft) | 2020-02-21 07:00 | 2020-02-21 17:00 | N | N | relay maintenance op-checks | Circuit Breaker, Line | 72JW19 (805s Jasper - Woodcroft), 805s J724 (805s Jasper) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 795L (121s Brooks - 421s Hays) | 2020-02-21 07:00 | 2020-02-27 15:30 | N | N | structure replacements and modifications for line clearance mitigation between structure 170 to 176 | Line | 795L (121s Brooks - 421s Hays) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.84L (ENMAX 43 - ENMAX 33), ENMAX 33 B138-33.84 (ENMAX 33), ENMAX 43 B138-33.84 (ENMAX 43), 33.2TR (ENMAX 33) | 2020-02-21 08:00 | 2020-02-22 16:00 | N | N | maintenance | Line, Circuit Breaker, Transformer | 33.84L (ENMAX 43 - ENMAX 33), 33.2TR (ENMAX 33) | HV SW maint SW84, SW85, SW86, MD-33.2TR. Check reversing switch 33.2. Oil sampling MT, TC | Creates Radial Feeds, Firm Load Loss
EPCOR | Rossdale RR729 (Rossdale) | 2020-02-21 08:00 | 2020-02-21 17:00 | N | N | Substation training | Circuit Breaker | Rossdale RR729 (Rossdale) |  | Firm Load Loss, Pre-Condition
ATCO, ALTALINK | 7L230 (69s North Barrhead - 7L230 tap), 7L230 (7L230 tap - 743s Sarah Lake), 888AL (234s Fort Assiniboine - 7L230 tap) | 2020-02-21 13:30 | 2020-02-21 16:30 | N | Y | ATCO replace X-arms and line mitigation | Line | 7L230 (7L230 tap - 743s Sarah Lake), 888AL (234s Fort Assiniboine - 7L230 tap) | ATCO remove 7L230 J1 | Pre-Condition
ALTALINK | 409s T1 (409s Shell Scotford) | 2020-02-22 09:09 | 2020-02-28 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark), 805s J722 (805s Jasper) | 2020-02-23 07:00 | 2020-02-23 17:00 | N | N | relay maintenance op-checks | Line, Circuit Breaker | 72JM18 (805s Jasper - Meadowlark), 805s J722 (805s Jasper) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.83L (ENMAX 13 - 2.83L tap), 5.10TR (ENMAX 5), 5.9TR (ENMAX 5) | 2020-02-23 08:00 | 2020-02-23 18:00 | N | N | switch maintenance, check reversing switch | Line, Transformer |  | HV SW maint. MD-5.9TR. MD-5.10TR. Check reversing sw 5.9, 5.10. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 930s SVC (930s Arcenciel) | 2020-02-23 11:30 | 2020-02-25 15:09 | N | Y | forced outage | Shunts |  | SVC has a cooling system issue. | Pre-Condition
ATCO | 930s Syn Condenser (930s Arcenciel) | 2020-02-23 11:30 | 2020-02-28 18:00 | N | Y | forced outage | Shunts |  | The SC had a mechanical failure (Broken Fins). | Pre-Condition
EPCOR | 1098L (805s Jasper - Poundmaker), 805s J2407 (805s Jasper), 805s J2401 (805s Jasper), Poundmaker 2401 (Poundmaker), Poundmaker 2402 (Poundmaker) | 2020-02-24 07:00 | 2020-02-26 17:00 | N | Y | relay maintenance | Line, Circuit Breaker | 1098L (805s Jasper - Poundmaker), Poundmaker 2401 (Poundmaker), Poundmaker 2402 (Poundmaker) | Outage to 1098L required for relay maintenance and op-checks | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 170L (632s Russell - 799s Coleman) | 2020-02-24 07:00 | 2020-02-28 17:00 | N | Y | emergency repair | Line | 170L (632s Russell - 799s Coleman) | Emergency Repair: Install clampstar assemblies over hot Sleeves and sleeve out hot conductor in multiple spans between Str 1K - 31 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2020-02-24 08:00 | 2020-03-01 17:00 | N | Y | FAC-008 line to ground mitigation | Line | 7L59 (789s Keg River - 7L59 tap) | FAC-008 line to ground mitigation | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 95s T2 (95s Imperial Oil Edmonton), 737L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2020-02-24 08:00 | 2020-02-28 17:00 | N | N | upgrade teleprotection / transfer trip scheme and add supervisory control to high side T2 MOD | Transformer, Line | 95s T2 (95s Imperial Oil Edmonton), 737L (95s Imperial Oil Edmonton - 38s East Edmonton) | (1) Upgrade teleprotection / transfer trip scheme on 737L between 95s and 38s in preparation for IOL Cogen. (2) Add supervisory control to high side T2 MOD (95s737N) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.1TR (ENMAX 14) | 2020-02-24 08:00 | 2020-02-28 15:00 | N | N | adjust breaker alignment and check reversing switch | Transformer | 14.1TR (ENMAX 14) | Adjust breaker alignment. Check reversing sw 14.1TR. 14.1TR. OH crew required for risers and distribution switching. | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), 15.2TR (ENMAX 15) | 2020-02-24 08:00 | 2020-02-25 18:00 | N | N | switch maintenance | Line, Transformer | 15.62L (ENMAX 15 - ENMAX 16), 15.2TR (ENMAX 15) | HV SW maint SW64, SW65, SW66, MD-15.2TR. Check reversing switch. Oil sampling 15.2TR MT, TC. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | MD138-2-1CAP (ENMAX 2), 5s C4 (5s East Calgary), 5s C3 (5s East Calgary) | 2020-02-24 08:00 | 2020-02-25 16:00 | N | Y | substation building upgrades | Switch, Shunts | 5s C4 (5s East Calgary), 5s C3 (5s East Calgary) | substation building upgrades. Install Roxtec plugs in ducts | Pre-Condition
ATCO, ALTALINK | 9L912 (766s Nevis - 63s Red Deer), 912L (63s Red Deer - 766s Nevis) | 2020-02-24 09:00 | 2020-03-04 18:00 | N | Y | urgent line clearance | Line | 912L (63s Red Deer - 766s Nevis) | urgent line clearance on 912L due to public safety hazard in high wind conditions. | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L53 (7L53 tap - 700s Bonnyville) | 2020-02-24 09:00 | 2020-02-27 17:00 | N | N | insulator and arm changes | Line | 7L53 (7L53 tap - 700s Bonnyville) | Insulator and Arm Changes | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L90 (813s Little Smoky - 7L90D2) | 2020-02-24 10:00 | 2020-03-02 16:00 | N | N | line mitigation | Line | 7L90 (813s Little Smoky - 7L90D2) | Complete line mitigation project | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2020-02-24 22:00 | 2020-02-25 04:00 | N | N | rail tower relocate | Line | 2.83L (ENMAX 13 - 2.83L tap), 2.83L (ENMAX 2 - 2.83L tap), 2.83L (ENMAX 5 - 2.83L tap) | CP Rail Tower Relocate. Install 5 sub leg at t-tap | Pre-Condition
SUNCOR | 635EDD-1001 635-752-642 (635EDD-1001) | 2020-02-25 07:00 | 2020-02-25 17:00 | N | N | breaker outage for brick unit replacement | Circuit Breaker |  | 635-752-642 breaker will be taken out -of service in 635EDD-1001 to replace GE Brick Unit on 635-752-642. There are 3 relays associated with this Brick unit which will be also taken out of service: GC70A35PK1002_Z 636PK-1002 Cap Bank A Protection. The redundant B proection will remain in service. GC60A35PP1007_4 635-752-642 and 635-752-643 breaker failure A protection. The redundant B protection will remain in service. GB95A35PP1006_Z 635PP-1006 bus A protection. The redundant B protection will remain in service. | For Information Only
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2020-02-25 08:00 | 2020-02-27 17:45 | N | Y | replace components str's range 9-258 | Line | 794L (157s Lac La Biche - 819s Whitby Lake) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
Syncrude | Mildred T6 (Syncrude Mildred Lake) | 2020-02-25 08:00 | 2020-02-25 22:00 | N | Y | urgent tap changer repair | Transformer | Mildred T6 (Syncrude Mildred Lake) | Urgent - Transformer T6 (72 kV/13.8 kV) at Plant-31 Substation - address tap changer issue to support Generator G6 revalidation testing | For Information Only
BLACKSPRING | 485s DVAR2 (485s Blacksprings) | 2020-02-25 08:00 | 2020-02-27 16:00 | N | N | repair and replacement of failed inverter trays on dstatcom | Shunts |  |  | For Information Only
ALTALINK | 521AL (867s Sundance Blow-Down - 521L tap), 867s T1 (867s Sundance Blow-Down) | 2020-02-25 08:30 | 2020-02-25 18:00 | N | N | urgent repair on 521AL structure 1 broken anchor. | Line, Transformer |  | URGENT Repair on 521AL Structure 1(Inside 867s) Broken Anchor. | For Information Only
ALTALINK | 102s 252 (102s Langdon) | 2020-02-25 09:00 | 2020-02-25 17:00 | N | Y | urgent work to prevent breaker lockout due to low SF6 gas | Circuit Breaker | 102s 252 (102s Langdon) |  | 240 kV
ENMAX | 5.10TR (ENMAX 5) | 2020-02-26 08:00 | 2020-02-27 16:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2020-02-26 08:00 | 2020-02-28 16:00 | N | Y | raise power poles for mitigation | Line | 7L45 (798s Bridge Creek - 813s Little Smoky) | Raise power poles for mitigation, use phaseraiser system to raise line, Associated with 7L46 HOP # 2-51016 | Pre-Condition
ALTALINK | 33s6 (33s Spray) | 2020-02-26 08:00 | 2020-02-26 17:00 | N | Y | maintenance | Switch | 33s6 (33s Spray) |  | Restricts Generation
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12), 12.1TR (ENMAX 12) | 2020-02-26 08:00 | 2020-02-27 16:00 | N | Y | HV SW maintenance SW84, SW85, SW86, MD-12.1TR, check reversing switch | Line, Transformer | 832L (ENMAX 10 - ENMAX 12), 12.1TR (ENMAX 12) | HV SW maint SW84, SW85, SW86, MD-12.1TR. Check reversing sw. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 443L (55s Olds - 214s Innisfail) | 2020-02-26 08:30 | 2020-03-04 16:45 | N | Y | complete structure changes | Line | 443L (214s Innisfail - 55s Olds) | complete structure changes at STRs 6,11,40,42,55,57 and 92 on 443L | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 68s T2 (68s Willesden Green) | 2020-02-26 09:00 | 2020-02-26 18:00 | N | Y | urgent 68s32 swictch repair | Transformer |  | Urgent repair of 68s32 broken switch, possible damage to equipment and personnel | 240 kV, For Information Only
EPCOR | RW 2401 (EPCOR Riverview) | 2020-02-26 12:45 | 2020-03-11 18:00 | N | N | forced outage | Circuit Breaker |  |  | 240 kV, For Information Only
Syncrude | Mildred T3 (Syncrude Mildred Lake) | 2020-02-27 08:00 | 2020-03-17 20:00 | N | Y | de-energize temporary transformer to install new transformer T3 (P2039) | Transformer | Mildred T3 (Syncrude Mildred Lake) | de-energize temporary transformer (G15) to install new transformer T3 | Restricts Generation
EPCOR | 805s J2403 (805s Jasper) | 2020-02-27 09:00 | 2020-02-27 15:00 | N | Y | switch and breaker operation for NAIT student demo | Circuit Breaker | 805s J2403 (805s Jasper) | Switch and breaker operation for NAIT Student Demo | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
BLACKSPRING | 485s Black Springs RTU/SCADA | 2020-02-27 10:00 | 2020-02-28 11:00 | N | N | software patch update | Terminal Equipment |  |  | For Information Only
ALTALINK | 7L53 (A706s - A700s - A969s) ATCO Info | 2020-02-28 08:00 | 2020-02-28 17:00 | N | N | ATCO :insulator and arm changes | Terminal Equipment |  |  | For Information Only
ATCO | 7L53 (7L53 tap - 706s Irish Creek) | 2020-02-28 08:00 | 2020-02-28 17:00 | N | N | insulator and arm changes | Line | 7L53 (7L53 tap - 706s Irish Creek) | Insulator and Arm Changes | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 661s T1 (661s Laura Lake) | 2020-02-28 08:00 | 2020-02-29 18:00 | N | N | replace oil and fix leaks | Transformer |  | To facilitate this outage we will need to temporarily de-energize 519L/519AL & 996s Station for approx. 1 hour on both days. This is required due to a safety issue with opening/closing our isolation pt. 661s1. | For Information Only
ENMAX, ALTALINK | 833L (ENMAX 2 - ENMAX 12) | 2020-02-28 08:00 | 2020-02-28 18:00 | N | N | HV SW maintenance SW81@12 sub, contractor applying roxtec duct seal at 2 sub | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L56 (813s Little Smoky - 725s Goose River) | 2020-02-29 10:00 | 2020-03-01 14:00 | N | N | line violation mitigation | Line | 7L56 (813s Little Smoky - 725s Goose River) | FAC Line Violation Mitigation | Overload, Pre-Condition
EPCOR | Rossdale T2 (Rossdale) | 2020-03-02 07:00 | 2020-03-02 13:00 | N | N | repair to R6T2 | Transformer | Rossdale T2 (Rossdale) | Vendor repair to R6T2 | For Information Only
ALTALINK, EPCOR | 930L (37s North Calder - Poundmaker) | 2020-03-02 07:00 | 2020-03-06 17:00 | N | Y | maintenance | Line | 930L (37s North Calder - Poundmaker) |  | 240 kV, Pre-Condition, Affects Cranking Path
ENMAX | 21.1TR (ENMAX 21) | 2020-03-02 08:00 | 2020-03-03 16:00 | N | N | substation building upgrades, install Roxtec plugs in ducts | Transformer | 21.1TR (ENMAX 21) | Substation Building Upgrades. Install Roxtec plugs in ducts | For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2020-03-02 08:00 | 2020-03-02 16:00 | N | N | hotspot 37.2TR H1, oil sampling MT, TC. check reversing switch, gas relay testing | Transformer | 37.2TR (ENMAX 37) | Hotspot 37.2TR H1. Oil sampling MT, TC. Check reversing switch. Gas relay testing. | For Information Only
ENMAX | 20.82L (ENMAX 20 - ENMAX 21) | 2020-03-02 08:00 | 2020-03-03 16:00 | N | N | detect breaker SF6 leak and sampling | Line | 20.82L (ENMAX 21 - ENMAX 20) | Detect leak 20B138-20.82. SF6 Sample 20B138-20.82 | Creates Radial Feeds, Firm Load Loss
ATCO | 7L64 (930s Arcenciel - 7L64D5) | 2020-03-02 08:00 | 2020-03-22 17:00 | N | Y | replacing structures and crossarms | Line | 7L64 (747s Bassett - 930s Arcenciel), 7L64 (748s Haig River - 747s Bassett), 7L64 (748s Haig River - 779s Chinchaga River) | Contractor replacing structures and crossarms | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar) | 2020-03-02 08:00 | 2020-03-02 17:00 | N | Y | relay maintenance | Line | 921L (71s Lamoureux - 987s Clover Bar) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 32.2TR (ENMAX 32) | 2020-03-02 08:00 | 2020-03-05 16:00 | N | N | replace broken bushing insulator 32.17. 32 Sub 8kv 32.15 insulator broken, check reversing switch, oil sampling 32.2TR bushing | Transformer | 32.2TR (ENMAX 32) | Corrective. Replace Broken Bushing Insulator 32.17. 32 Sub 8kv 32.15 Insulator broken. Check reversing switch. Oil sampling 32.2TR bushing | For Information Only
ATCO | 2029s ACF11 (2029s Heathfield) | 2020-03-02 08:00 | 2020-05-07 17:00 | N | Y | Forced outage repairs | Shunts | 2029s ACF11 (2029s Heathfield) | Forced outage repairs | 240 kV, For Information Only
ALTALINK | 538s T1 (538s Buford) | 2020-03-02 08:30 | 2020-03-03 17:00 | N | N | replace VT1, and T1 maintenance | Transformer | 538s Station - GOI | Replace VT1. T1 maintenance. | For Information Only
ATCO | 7L63 (783s Cadotte River - 812s Norcen) | 2020-03-02 09:00 | 2020-03-27 17:00 | N | Y | crossarm replacements | Line | 7L63 (783s Cadotte River - 812s Norcen) | 7L63 crossarm replacements | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2020-03-02 12:15 | 2020-03-05 17:45 | N | Y | replace components str's range 9-258 | Line | 794L (157s Lac La Biche - 819s Whitby Lake) | 794L Components Replacements Str's 9-258 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
NOVACORP | 330s BR_50 (330s Nova Corp), 330s Nova Corp 138kV Bus 1B | 2020-03-03 07:00 | 2020-03-04 17:00 | N | Y | maintenance | Circuit Breaker, Bus | 330s BR_50 (330s Nova Corp), 330s Nova Corp 138kV Bus 1A | 330-Bus-1B Outage for maintenance of PTR-01, PTR-03 Deluge Testing and 330-BR-50 Maintenance | For Information Only, Restricts Generation
ATCO | 740s 507C (740s H.R.Milner) | 2020-03-03 08:00 | 2020-03-15 06:30 | N | N | replace breaker | Shunts | 740S 507 | replace breaker 507 & 507C as part of 740S rebuild 500BS1, 508, 506, 507 all required OOS during 507/507C replacement for crane & clearance access | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 41.84L (ENMAX 41 - ENMAX 54) | 2020-03-03 08:00 | 2020-03-03 16:00 | N | N | check hotspot | Line | 41.84L (ENMAX 54 - ENMAX 41) | Hotspot. 41 Sub hot spot, 41B138-41.84 CT H2 | Creates Radial Feeds, Firm Load Loss
ALTALINK | 704L (51s Wainwright - 478s Tuccuman), 478s 152 (478s Tucuman) | 2020-03-03 08:00 | 2020-03-03 17:30 | N | N | breaker maintenance | Line, Circuit Breaker | 704L (51s Wainwright - 478s Tuccuman), 478s 152 (478s Tucuman) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2020-03-03 08:30 | 2020-03-05 17:00 | N | N | clearance Mitigation | Line | 7L171 (802s Michichi Creek - 804s Wintering Hills) | Clearance Mitigation | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2020-03-03 09:00 | 2020-03-07 15:00 | N | Y | line mitigation | Line | 7L32 (862s South Bezanson - 813s Little Smoky) | Line Mitigation | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2020-03-03 09:30 | 2020-03-03 10:30 | N | Y | teleprotection work | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 103s 1452 (103s Goose Lake) | 2020-03-03 10:00 | 2020-03-03 17:00 | N | N | modifications to breaker control | Circuit Breaker | 103s 1452 (103s Goose Lake) | Modifications to 103s1452 breaker control to remove Dead Line/Dead Bus bypass as part of the Sync Check Program. | Contingency Requires Mitigation
ALTALINK | 538S Buford, 632L (325s Leduc - 538s Buford), 837L (538s Buford - 964s Pigeon Lake) | 2020-03-03 16:00 | 2020-03-03 17:00 | N | N | de-energize 138kV bus to perform initial energization of VT1 | Station, Line | 538s 138kV Bus - De-energization |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 172EL (139s Hillridge - 172EL1) | 2020-03-04 07:00 | 2020-03-05 18:00 | N | Y | urgent structure 15- 121 conductor and damper repair | Line |  | Structure 15- 121 Conductor-Repairs & Damper repair | For Information Only, Restricts Generation
SUNCOR | 139S Hillridge, 139s 138B1 (139s Hillridge) | 2020-03-04 07:00 | 2020-03-05 18:00 | N | Y | equipment repair | Station, Circuit Breaker |  | Replacement of damaged conductors on AltaLink 172EL feeder to CCWF. | For Information Only, Restricts Generation
ALTALINK | 370s T5 (370s North Lethbridge) | 2020-03-04 07:30 | 2020-03-04 17:30 | N | Y | component replacements | Transformer | 370s T5 (370s North Lethbridge) | replace diverter lid/gear box and replace oil in diverters | 240 kV, Pre-Condition
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 14.2TR (ENMAX 14), 14.4TR (ENMAX 14), 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2020-03-04 08:00 | 2020-03-05 18:00 | N | N | switch maintenance | Line, Transformer, Shunts |  | HV Switch maint. MD-14.2TR, MD-14.4TR. Check reversing sw 14.2TR, 14.4TR. Gas relay testing 14.2TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 756s 601T (756s Bigfoot) | 2020-03-04 08:00 | 2020-03-18 16:00 | N | N | Salvage March 11, 2020 (capital maintenance) | Transformer
ENMAX | 31.1C (ENMAX 31) | 2020-03-04 08:00 | 2020-03-04 16:00 | N | N | recheck and top up gas pressure | Shunts | 31.1C (ENMAX 31) |  | Pre-Condition
ALTALINK | 681L (377s Hardisty - 478s Tucuman), 478s 252 (478s Tucuman) | 2020-03-04 08:00 | 2020-03-04 16:00 | N | N | breaker maintenance | Line, Circuit Breaker | 681L (377s Hardisty - 478s Tucuman), 478s 252 (478s Tucuman) |  | Over/Under Voltage, Pre-Condition
EPCOR | 987s T2 (987s Clover Bar), 987s T4 (987s Clover Bar) | 2020-03-04 08:00 | 2020-03-04 17:00 | N | Y | relay maintenance | Transformer | 987s T2 (987s Clover Bar) | Relay maintenance and op-checks to Tx2 protection . Outage will affect Tx4 on Cloverbar POD S/S. | 240 kV, Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2020-03-04 09:30 | 2020-03-17 17:45 | N | N | rebuild structures | Line | 174L (197s Bardo - 289s Saunders Lake) | 174L Rebuild From Str #379 to Str#485 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 77s 352 (77s Sagitawah) | 2020-03-04 09:30 | 2020-03-04 17:30 | N | N | breaker maintenance | Circuit Breaker | 77s 352 (77s Sagitawah) | Maintenance on 77s352 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 364s 3052 (364s Whitecourt Industrial) | 2020-03-05 07:30 | 2020-03-05 16:00 | N | N | maintenance | Circuit Breaker | 364s3052 - GOI |  | Creates Radial Feeds, Over/Under Voltage, Pre-Condition
ALTALINK | 409s T2 (409s Shell Scotford) | 2020-03-05 09:00 | 2020-03-05 13:00 | N | N | remove CTs from system | Transformer |  | Remove CTs from system. Temporarily wire meters into spare CTs in T2. | For Information Only
ALTALINK | 948L (650s Hansman Lake - 863s Paintearth) | 2020-03-06 07:00 | 2020-03-15 17:30 | N | Y | component replacements | Line | 948L (650s Hansman Lake - 863s Paintearth) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 37.1TR (ENMAX 37) | 2020-03-06 08:00 | 2020-03-06 16:00 | N | N | hotspot 37.1TR south phase | Transformer | 37.1TR (ENMAX 37) | hotspot 37.1TR south phase, oil sampling MT, TC, check reversing switch | For Information Only
EPCOR | Rossdale RR729 (Rossdale) | 2020-03-06 08:00 | 2020-03-06 17:00 | N | N | substation training | Circuit Breaker | Rossdale RR729 (Rossdale) |  | Pre-Condition
ALTALINK | 331s T1 (331s Ponoka) | 2020-03-06 14:00 | 2020-03-10 17:00 | N | N | maintenance | Transformer | 331s T1 (331s Ponoka) | Replace VT1. Replace 496LS Meter. | For Information Only
ATCO | 859s 701T (859s Primrose) | 2020-03-09 03:00 | 2020-03-22 14:00 | N | Y | maintenance | Transformer | 859s 701T (859s Primrose) |  | Restricts Generation
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2020-03-09 06:30 | 2020-03-14 11:30 | N | N | replace str # 521 | Line | 202L (58s Edson - 178s Cynthia) |  | Over/Under Voltage, Pre-Condition, Affects Cranking Path
EPCOR | 72JW19 (805s Jasper - Woodcroft), 805s J724 (805s Jasper), Woodcroft W721 (Woodcroft) | 2020-03-09 07:00 | 2020-04-10 17:00 | N | N | termination rebuild | Line, Circuit Breaker | 72JW19 (805s Jasper - Woodcroft) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 805s C1 (805s Jasper), 805s J2408 (805s Jasper) | 2020-03-09 07:00 | 2020-03-10 17:00 | N | Y | relay maintenance op-checks | Shunts, Circuit Breaker | 805s C1 (805s Jasper) |  | 240 kV, Pre-Condition
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2020-03-09 07:00 | 2020-03-31 15:00 | N | N | rebuilding a portion of 890L between Strs 2 and 27 | Line | 890L (58s Edson - 207s Pinedale) | Scope of work includes rebuilding a portion of 890L between Strs 2 and 27 Scheduled: Shannon Bouchard Issue To: Carson Webber Contact #: 778.214.6493 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RV6 (Rossdale - 511s Victoria), Rossdale RV722 (Rossdale) | 2020-03-09 07:00 | 2020-03-09 17:00 | N | N | relay maintenance op-checks | Line, Circuit Breaker | 72RV6 (Rossdale - 511s Victoria), Rossdale RV722 (Rossdale) |  | For Information Only
EPCOR | Genesee S/S 12TC1 outage, 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee) | 2020-03-09 07:00 | 2020-03-14 17:00 | N | Y | relay repair/maintenance op-checks | Terminal Equipment, Circuit Breaker | 330P 12TC1 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
ENMAX | 27.1TR (ENMAX 27) | 2020-03-09 08:00 | 2020-03-10 16:00 | N | N | T-60 upgrade phase 2, check reversing switch | Transformer | 27.1TR (ENMAX 27) |  | For Information Only
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2020-03-09 08:00 | 2020-03-10 18:00 | N | N | HV switch maintenance | Line |  | HV SW maint SW90, SW91, MD-11.83 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.2TR (ENMAX 32) | 2020-03-09 08:00 | 2020-03-11 16:00 | N | N | T-60 upgrade phase 2, check reversing switch, oil sampling 32.2TR MT, TC, bushing | Transformer | 32.2TR (ENMAX 32) | T-60 Upgrade Phase 2. Check reversing switch. Oil sampling 32.2TR MT, TC, Bushing | For Information Only
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2020-03-09 08:00 | 2020-03-09 16:00 | N | N | remove scaffolding at 8 sub | Line |  | DCTRP. Remove scaffolding at 8sub | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
SUNCOR | 29PL6-4 (836s Steepbank - 29EDD-1) | 2020-03-09 08:00 | 2020-03-19 20:00 | N | N | maintenance | Line | 29PL6-4 (836s Steepbank - 29EDD-1) | 72 kV line 29PL6-4 is being relocated to create space for cogeneration project. Only line 29PL6-4 will not be available while 29PL6-3 will be supplying Steepbank Sub. 5 year PM on 29CVT-8 and low SF6 on 29EDD1s1552 and replace arresters 29PLA-187ABC, 10YR 29EDD1s-1552/1652 29PL9-1 & 29PL9-2 - "B" Protection (partial elements) communication loss, "A" Protection will be available. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 7L139 (707s St.Paul - 7L139D3) | 2020-03-09 08:00 | 2020-03-12 17:00 | N | N | crossarm and insulator change | Line | 7L139 (819s Whitby Lake - 707s St.Paul) | Crossarm & Insulator Change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2020-03-09 08:15 | 2020-03-12 11:00 | N | Y | de-energized due to PT replacement at ENMAX 21 | Line |  | Enmax wants AltaLink to de-energized due to having 60s100 out of service (Ref # 268141). | For Information Only
ENMAX | ENMAX 21 SW83 (ENMAX 21) | 2020-03-09 08:30 | 2020-03-12 15:30 | N | Y | PT replacement | Switch |  |  | For Information Only
ALTALINK | 205s Castle Rock Ridge RTU/SCADA | 2020-03-09 08:30 | 2020-03-09 11:00 | N | N | implement and test the RTAC changes | Terminal Equipment |  |  | For Information Only
EPCOR | Kennedale KAB1 (Kennedale), 72CK13 (987s Clover Bar - Kennedale) | 2020-03-09 09:00 | 2020-03-09 14:30 | N | N | repairs to disconnect switch | Switch, Line | Kennedale KAB1 (Kennedale), 72CK13 (987s Clover Bar - Kennedale) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 665s TX1 (665s Dome) | 2020-03-09 09:30 | 2020-03-11 17:00 | N | Y | relay maintenance | Line, Transformer | 909L (89s Ellerslie - 665s Dome), 665s TX1 (665s Dome) | Outage to TX#1 required for relay mtce op-checks and installation of new 240 KV breaker | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ALTALINK | 728L (353s Plamondon - 405s Waupisoo) | 2020-03-09 12:15 | 2020-03-12 17:45 | N | N | components replacement | Line | 728L (405s Waupisoo - 353s Plamondon) | 728L Components Str 189 Replace Pole | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 535s T3 (535s Joffre) | 2020-03-10 07:00 | 2020-03-11 19:30 | N | N | replace 25kV feeder cables & switching cubicle on 297L1 | Transformer | 535s T3 (535s Joffre) | Replace 25kV feeder cables & switching cubicle on 297L1 | For Information Only
CMH | MH-10L (MH69s2 North Industrial - MHS8 Burnside) | 2020-03-10 08:00 | 2020-03-11 16:00 | N | N | install a transformer that will be in proximity to the 10L line | Line | MH-10L (MH69s2 North Industrial - MHS8 Burnside) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L46 (813s Little Smoky - 845s Big Mountain) | 2020-03-10 08:00 | 2020-03-12 16:00 | N | Y | raise structures for line mitigation | Line | 7L46 (845s Big Mountain - 813s Little Smoky) | Raise Structures for Line mitigation, Associated with 7L45 HOP # 2-51167 | Over/Under Voltage, Overload, Pre-Condition
CapitalPower | 615s Halkirk RTU/SCADA | 2020-03-10 10:00 | 2020-03-10 12:00 | N | N | update logic in the RTU | Terminal Equipment |  |  | Affects Visibility
REDDEER | 194s T2 (194s South Red Deer) | 2020-03-11 04:00 | 2020-03-21 18:00 | N | N | forced outage | Transformer | 194s T2 (194s South Red Deer) |  | For Information Only
EPCOR | 805s J2403 (805s Jasper) | 2020-03-11 07:00 | 2020-03-11 11:00 | N | Y | relay maintenance op-checks | Circuit Breaker | 805s J2403 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ATCO | 756s 601T (756s Bigfoot), 6L08 (756s Bigfoot - 757s Battle River), 756S Bigfoot | 2020-03-11 07:30 | 2020-03-11 19:00 | N | N | 756S 601T salvage, 500SST1 install and relocate station service transformer | Transformer, Line, Station | 756s 601T (756s Bigfoot) | 756S 601T Salvage / 500SST1 Install 756S 601T Salvage/ Relocate station service transformer | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2020-03-11 08:00 | 2020-03-12 15:00 | N | N | hotspot, 23 sub Sw3 (South phase), EPSC installing SSTR23-1, which will be energized on return | Transformer | 23.4TR (ENMAX 23) | Hotspot. 23 sub Sw3 (South phase). EPSC Installing SSTR23-1, which will be energized on return. | For Information Only
ENMAX | 32.1TR (ENMAX 32) | 2020-03-11 08:00 | 2020-03-12 16:00 | N | N | T-60 upgrade phase 2 | Transformer | 32.1TR (ENMAX 32) |  | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2020-03-11 08:00 | 2020-03-12 16:00 | N | N | T-60 upgrade phase 2, check reversing switch | Transformer | 27.2TR (ENMAX 27) |  | For Information Only
ENMAX | 23.4TR (ENMAX 23) | 2020-03-11 08:00 | 2020-03-12 16:00 | N | N | tapchanger inspection check reversing switch oil sampling MT, TC. gas relay testing | Transformer | 23.4TR (ENMAX 23) | tapchanger inspection check reversing switch oil sampling MT, TC. gas relay testing | For Information Only
EPCOR | 805s J2404 (805s Jasper) | 2020-03-11 12:00 | 2020-03-11 17:00 | N | Y | relay maintenance op-checks | Circuit Breaker | 805s J2404 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 320p T6 (320p Keephills), 320p PS2 (320p Keephills), 320p 2652 (320p Keephills), 320p 2752 (320p Keephills) | 2020-03-11 15:46 | 2020-03-18 15:44 | N | N | urgent outage - burnt auxiliary CT | Transformer, Circuit Breaker |  |  | 240 kV
EPCOR | 805s J2405 (805s Jasper) | 2020-03-12 07:00 | 2020-03-12 11:00 | N | Y | relay maintenance op-checks | Circuit Breaker | 805s J2405 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 205s Castle Rock Ridge RTU/SCADA | 2020-03-12 08:00 | 2020-03-12 10:00 | N | N | implement and test the RTAC changes | Terminal Equipment |  |  | For Information Only
ALTALINK | 719L (256s Harmattan - 719L134), 256s 719N (256s Harmattan) | 2020-03-12 09:00 | 2020-03-12 16:30 | N | Y | fix burned up thermostat in the cabinet | Line, Circuit Breaker |  |  | Creates Radial Feeds, Pre-Condition
ENMAX, ALTALINK | 20.82L (ENMAX 20 - ENMAX 21), 21.80L (42s Sarcee - ENMAX 21) | 2020-03-12 11:00 | 2020-03-12 12:00 | N | N | breakers open only in order to energize Altalinks New 60s100PTs | Line |  |  | Creates Radial Feeds, Pre-Condition
EPCOR | 805s J2406 (805s Jasper) | 2020-03-13 07:00 | 2020-03-13 11:00 | N | Y | relay maintenance | Circuit Breaker | 805s J2406 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 7L101 (790s Poplar Hill - 944s Lowe Lake) | 2020-03-13 10:00 | 2020-03-14 16:00 | N | Y | test relays | Line |  | Grande Prairie Generation (Lowe Lake) request - they are testing relays SEL-311L and SEL-421 which will result in tripping breaker 705 @ 790S Poplar Hill. 7L101 will be de-energized and disconnect 705A will be open for the duration of the testing. | Restricts Generation,Affects Cranking Path
ATCO | 7L45 (798s Bridge Creek - 813s Little Smoky) | 2020-03-15 08:00 | 2020-03-17 16:00 | N | Y | maintnance | Line | 7L45 (845s Big Mountain - 798s Bridge Creek) | Raise Structures for mitigation, Associated with 7L46 HOP # 2-51164 | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
MONTANA | MATL (120s Picture Butte - Montana) | 2020-03-15 11:50 | 2020-03-22 13:50 | N | Y | forced outage | Line |  |  | 240 kV, Limits ATC
AESO-SC | OC On-Call Contact | 2020-03-16 07:00 | 2022-04-01 23:00 | N | N | OC team work from home | SCInternal |  |  | For Information Only
EPCOR | 330p 1203 (330p Genesee), 330p 1206 (330p Genesee), 330p 1209 (330p Genesee), 330P 12TC2 (330p Genesee) | 2020-03-16 07:00 | 2020-03-19 17:00 | N | Y | relay maintenance op-checks | Circuit Breaker, Transformer | 330P 12TC2 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L139 (707s St.Paul - 7L139D3) | 2020-03-16 08:00 | 2020-03-19 17:00 | N | N | crossarm and insulator change | Line | 7L139 (819s Whitby Lake - 707s St.Paul) | Crossarm & Insulator Change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | 2020-03-16 08:00 | 2020-03-16 16:00 | N | N | spring substation washing and maintenance | Line, Transformer |  | Spring Substation Washing. Check reversing Switch 22.1TR(X), 22.1TR(Y), 22.3TR. 22 Sub, SW 83 Hotspot | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L28 (717s Ethel Lake - 846s Grand Centre) | 2020-03-16 08:00 | 2020-03-20 16:00 | N | Y | breaker and CT maintenance | Line | 7L28 (717s Ethel Lake - 846s Grand Centre) | 701 BKR and Ct maintenance 7L28 will be open at 846S Relay protection upgrade panel 7l28 (panel 1c) 86-50BF/700BS1 partial install/testing (panel 1c) Install new relay (21A-Siemens) Change CT cores going to relays (701CT work) Demo metering from ION 7300, metering will be done through SEL relay after. Commission wiring/relays/CT-ratios | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1552 (29EDD-1 Millennium), 29EDD-1 29EDD1s1652 (29EDD-1 Millennium) | 2020-03-16 08:00 | 2020-03-19 20:00 | N | N | install bird interaction deterants | Circuit Breaker | 29EDD-1 29EDD1s1152 (29EDD-1 Millennium) | To install bird interaction deterants. Work is to isolate one breaker at a time. 29EDD1S1152 29EDD1S1252 29EDD1S1352 29EDD1S1452 29EDD1S1552 29EDD1S1652 29EDD1S1752 29EDD1S1852 | For Information Only, Pre-Condition
ENMAX | 33.1TR (ENMAX 33) | 2020-03-16 08:00 | 2020-03-17 16:00 | N | N | T-60 upgrade phase 2 | Transformer | 33.1TR (ENMAX 33) | T-60 Upgrade Phase 2 | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-03-16 09:00 | 2020-03-17 12:38 | N | Y | components/structure replacements (Structures #59, 60, 61, 79, 80, 81, 151) | Line | 909L (310p Sundance - 665s Dome) | Components/Structure Replacements (Structures #59, 60, 61, 79, 80, 81, 151) | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 523s T1 (523s Bullshead) | 2020-03-16 09:00 | 2020-03-16 14:00 | N | N | create open point A to allow for replacement of 523s589 | Transformer | 523s T1 (523s Bullshead) |  | For Information Only
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-03-16 12:00 | 2020-03-17 13:54 | N | N | components/structure replacements (structures #1 - 61) | Line | 798L (364s Whitecourt Industrial - 77s Sagitawah) |  | Over/Under Voltage, Pre-Condition
ALTALINK | 523s T2 (523s Bullshead) | 2020-03-16 14:05 | 2020-03-19 14:00 | N | N | replacement of 523s598 | Transformer |  |  | For Information Only
Syncrude | Mildred T3 (Syncrude Mildred Lake) | 2020-03-17 08:00 | 2020-03-23 16:00 | N | N | commissioning and testing. ISD: Mar 23, 2020. | Transformer
ENMAX | 26.81L (ENMAX 32 - ENMAX 26), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32), 32PT138-Z31 (ENMAX 32) | 2020-03-17 08:00 | 2020-03-17 16:00 | N | N | substation washing. | Line, Transformer, Terminal Equipment |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 498s 33 (498s Tilley), 498s C1 (498s Tilley) | 2020-03-17 08:00 | 2020-03-17 16:30 | N | N | breaker maintenance | Circuit Breaker, Shunts | 498s C1 (498s Tilley) |  | For Information Only
ATCO | 892s 701T (892s Ribstone Creek) | 2020-03-17 08:00 | 2020-03-17 15:24 | N | N | bird proofing | Transformer | 892s 701T (892s Ribstone Creek) | 892S - 701T Bird Proofing | For Information Only
ALTALINK | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer) | 2020-03-17 09:00 | 2020-03-18 17:30 | N | Y | breaker maintenance | Transformer, Circuit Breaker | 63s T1 (63s Red Deer), 63s 24 (63s Red Deer) | CB 1480 (63S24) SF6 138KV DT1 Breaker Maintenance | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 20s 8 (20s Ghost), 20s T5 (20s Ghost) | 2020-03-17 09:00 | 2020-03-17 17:00 | N | N | breaker maintenance | Circuit Breaker, Transformer | 20s 8 (20s Ghost), 20s T5 (20s Ghost) |  | For Information Only
AESO-SC | OATI | 2020-03-17 18:00 | 2020-03-17 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ENMAX | 33.2TR (ENMAX 33) | 2020-03-18 08:00 | 2020-03-19 16:00 | N | N | T-60 upgrade phase 2 | Transformer | 33.2TR (ENMAX 33) |  | For Information Only
ATCO, ALTALINK | 7L50 (526s Buffalo Creek - 757s Battle River) | 2020-03-18 09:00 | 2020-03-21 16:00 | N | Y | conductor sampling | Line | 7L50 (526s Buffalo Creek - 757s Battle River) | crew do some conductor sampling on 7L50 , which means that I have to splice out some fairly large pieces of conductor. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
BLACKSPRING | 485S Black Springs | 2020-03-18 10:00 | 2020-03-18 11:00 | N | N | change 34.5 kV voltage regulation set point | Station |  |  | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2020-03-18 11:00 | 2020-03-18 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | Strathcona T2 (Strathcona) | 2020-03-19 08:00 | 2020-03-19 15:00 | N | N | maintenance | Transformer | Strathcona T2 (Strathcona) | Inspection of Liquid level Gauge and Float | For Information Only
ALTALINK | 250p 22 (250p Bighorn Plant) | 2020-03-19 09:00 | 2020-03-19 13:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 63s T2 (63s Red Deer), 63s 25 (63s Red Deer) | 2020-03-19 09:00 | 2020-03-19 17:30 | N | Y | 63S25 SF6 138KV DT1 breaker maintenance | Transformer, Circuit Breaker | 63s T2 (63s Red Deer), 63s 25 (63s Red Deer) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 523s T1 (523s Bullshead) | 2020-03-19 14:05 | 2020-03-19 18:15 | N | N | close open point A | Transformer | 523s T1 (523s Bullshead) |  | For Information Only
ENMAX | 11.82L (ENMAX 11 - ENMAX 14) | 2020-03-20 08:00 | 2020-03-20 16:00 | N | N | replace rotten pole. SF6 sample 11B138-11.82 | Line | 11.82L (ENMAX 14 - ENMAX 11) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 948L (650s Hansman Lake - 863s Paintearth) | 2020-03-21 07:00 | 2020-03-27 18:00 | N | Y | component replacements | Line | 948L (650s Hansman Lake - 863s Paintearth) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 2.1TR (ENMAX 2) | 2020-03-21 08:00 | 2020-03-22 16:00 | N | N | T-60 upgrade phase 2, maintenance, testing and oil sampling | Transformer | 2.1TR (ENMAX 2) | T-60 Upgrade Phase 2. Transformer secondary cable tests. Transformer maintenance. Gas relay testing. Check reversing switch. Oil sampling MT, TC | For Information Only
ENMAX | ENMAX 2 B138-D82 (ENMAX 2), ENMAX 2 B138-D81 (ENMAX 2) | 2020-03-21 10:00 | 2020-03-21 16:00 | N | N | verify 2MD138-2.84 (DS) open | Circuit Breaker
ALTALINK | 324s 2152 (324s Cassils) | 2020-03-21 16:45 | 2020-03-23 16:00 | N | Y | forced outage; low gas | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 936L (5s East Calgary - 102s Langdon) | 2020-03-22 08:00 | 2020-03-24 18:00 | N | Y | line clearance mitigation insulators, double circuit 937L | Line | 936L (5s East Calgary - 102s Langdon) |  | 240 kV, Pre-Condition, Affects Cranking Path
EPCOR | 330p 1202 (330p Genesee) | 2020-03-23 07:00 | 2020-03-23 17:00 | N | Y | relay maintenance op-checks | Circuit Breaker | 330p 1202 (330p Genesee) | Relay maintenance op-checks | 500 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 26.1TR (ENMAX 26) | 2020-03-23 08:00 | 2020-03-24 16:00 | N | N | T-60 upgrade phase 2, check reversing switch | Transformer | 26.1TR (ENMAX 26) |  | For Information Only
ATCO | 729s 601 (729s Otauwau), 6L73 (729s Otauwau - 745s Slave Lake) | 2020-03-23 08:00 | 2020-03-24 18:00 | N | N | emergency outage low gas on breaker | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 162.3TR (ENMAX 162 Beddington) | 2020-03-23 08:00 | 2020-03-26 14:30 | N | N | maintenance | Transformer |  | GIS Minor Maintenance. 25kV GIS switches on 25kV bus 1-1, 1-2. Special switching instructions required to capture Kelman trace162B25-162.112, 162B25-162.3TR, 162BT1, 162BT2, 162BT3, 162BT4. Line crew required for switching. | For Information Only
ALTALINK | 212s 461 (212s N.E. Lacombe), 461L (198s Blackfalds - 212s N.E. Lacombe) | 2020-03-23 09:30 | 2020-03-23 17:30 | N | Y | breaker maintenance | Circuit Breaker, Line | 461L (212s N.E. Lacombe - 198s Blackfalds), 212s 461 (212s N.E. Lacombe) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L139 (819s Whitby Lake - 7L139D2) | 2020-03-23 10:00 | 2020-04-02 17:00 | N | N | arm and insulator change | Line |  | 2020 arm and insulator change | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s 51 (370s North Lethbridge) | 2020-03-23 11:00 | 2020-03-24 17:00 | N | Y | relay settings changes | Circuit Breaker |  | Settings Changes of Sync Check and Functional Testing on 370s51 CUH90 relay. | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 330p 1205 (330p Genesee) | 2020-03-24 07:00 | 2020-03-24 17:00 | N | Y | relay maintenance op-checks | Circuit Breaker | 330p 1205 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-03-24 07:00 | 2020-03-26 18:00 | N | N | structure replacements | Line | 798L (364s Whitecourt Industrial - 77s Sagitawah) | Components/Structure Replacements (Structures #1 - 61) | Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 13s Deerland 138kV Bus 1 | 2020-03-24 07:15 | 2020-03-24 17:45 | N | N | correct grounding deficiencies with the new SST PT installation | Bus | 808L (13s Deerland - 171s Redwater) |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 212s 423 (212s N.E. Lacombe), 423L (212s N.E.Lacombe - 332s Ellis) | 2020-03-24 07:30 | 2020-03-24 17:30 | N | Y | 138 kV breaker maintenance | Circuit Breaker, Line | 423L (212s N.E.Lacombe - 332s Ellis), 212s 423 (212s N.E. Lacombe) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK, ENMAX | 44s 36_81E (44s Bearspaw), 36.81L (44s Bearspaw - ENMAX 36) | 2020-03-24 08:15 | 2020-03-24 17:15 | N | Y | 138 kV breaker maintenance | Circuit Breaker, Line | 36.81L (44s Bearspaw - ENMAX 36) |  | Pre-Condition
ALTALINK | 305s 453 (305s Acheson), 453L (305s Acheson - 367s Harry Smith) | 2020-03-24 08:30 | 2020-03-26 13:30 | N | N | breaker maintenance | Circuit Breaker, Line | 453L (305s Acheson - 367s Harry Smith) |  | Pre-Condition
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2020-03-24 08:30 | 2020-03-25 12:30 | N | N | install mechanical protection and retest loops after cables are reconnected | Transformer | 54s T1 (54s Fort Saskatchewan) | Install Mechanical protection for the bushing CT secondary cables on the outside of the transformer. Retest loops after cables are reconnected to the CTs. | For Information Only
ENMAX, ALTALINK | 937L (5s East Calgary - 102s Langdon) | 2020-03-25 07:00 | 2020-03-26 18:00 | N | Y | line clearance mitigation insulators 936L50 double circuit 936L | Line | 937L (102s Langdon - 5s East Calgary) |  | 240 kV, Pre-Condition, Affects Cranking Path
EPCOR | 330p 1208 (330p Genesee) | 2020-03-25 07:00 | 2020-03-25 17:00 | N | Y | relay maintenance op-checks | Circuit Breaker | 330p 1208 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 223s 39 (223s Strome), 701L (223s Strome - 395s North Holden) | 2020-03-25 07:30 | 2020-03-26 18:00 | N | N | breaker maintenance & line clearance mitigation on structures #204, 235 & 319 | Circuit Breaker, Line | 701L (395s North Holden - 223s Strome), 223s 39 (223s Strome) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 26.2TR (ENMAX 26) | 2020-03-25 08:00 | 2020-03-26 16:00 | N | N | T-60 upgrade phase 2 and check reversing switch | Transformer | 26.2TR (ENMAX 26) |  | For Information Only
ALTALINK | 44s 50X (44s Bearspaw), 50L (44s Bearspaw Plant - ENMAX 21) | 2020-03-25 08:15 | 2020-03-25 17:15 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line | 50L (44s Bearspaw Plant - ENMAX 21) |  | For Information Only
ALTALINK | 275s 2 (275s Jenner) | 2020-03-25 11:00 | 2020-03-26 17:00 | N | Y | settings changes of sync check and functional testing on 275s2 CUH90 relay | Circuit Breaker | 275s 2 (275s Jenner) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 54s T3 (54s Fort Saskatchewan) | 2020-03-25 12:05 | 2020-03-26 16:30 | N | N | install protection and retest loops | Transformer | 54s T3 (54s Fort Saskatchewan) | install Mechanical protection for the bushing CT secondary cables on the outside of the transformer. Retest loops after cables are reconnected to the CTs. | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2020-03-25 22:00 | 2020-03-26 02:00 | N | Y | maintenance | Switch | 62s 11 (62s Brazeau) |  | For Information Only, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2020-03-26 02:00 | 2020-03-26 07:00 | N | Y | maintenance and testing | Switch | 62s 12 (62s Brazeau) | Brushgear and blackstart test | For Information Only, Restricts Generation
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28) | 2020-03-26 08:00 | 2020-03-26 16:00 | N | Y | spring substation washing and check reversing switch | Line, Transformer | 28.80L (42s Sarcee - ENMAX 28) | Spring Substation Washing. Check reversing switch. Original outage March 19th. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 348s T2 (348s Marlboro) | 2020-03-26 08:00 | 2020-03-26 16:00 | N | N | repair corroded terminals JB CT2 | Transformer | 348s T2 (348s Marlboro) | Repair corroded terminals JB CT2 | For Information Only
ALTALINK | 253s 182 (253s Blackie), 253s C1 (253s Blackie) | 2020-03-26 09:00 | 2020-03-26 17:00 | N | N | maintenance, signage replacement | Circuit Breaker, Shunts | 283s C1 (283s Violet Grove) |  | Pre-Condition
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-03-26 09:30 | 2020-03-26 14:30 | N | N | asbestos concrete test sample | Shunts | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) |  | Pre-Condition
ALTALINK | 283s 31 (283s Violet Grove), 283s C1 (283s Violet Grove) | 2020-03-26 14:30 | 2020-04-01 18:00 | N | N | forced outage | Circuit Breaker, Shunts |  |  | For Information Only
EPCOR | 987s C72C1 (987s Clover Bar) | 2020-03-26 16:00 | 2020-04-01 07:59 | N | N | forced outage | Circuit Breaker | 987s C72C1 (987s Clover Bar) | forced outage due to phasing issues | For Information Only
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 2020-03-27 08:00 | 2020-04-07 18:00 | N | N | clearance mitigation | Line | 9s Shell Canada Waterton - 396s Pincher Creek) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Restricts Generation
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 14.1C (ENMAX 14), 14.2C (ENMAX 14), 14.2TR (ENMAX 14), 14.4TR (ENMAX 14), 14PT138-Z31 (ENMAX 14) | 2020-03-27 08:00 | 2020-03-27 16:00 | N | N | substation washing | Line, Shunts, Transformer, Not In Model | 14.83L (ENMAX 14 - ENMAX 36), 14.2TR (ENMAX 14), 14.4TR (ENMAX 14) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 38.1C (ENMAX 38), 38.1TR (ENMAX 38), 38.3TR (ENMAX 38) | 2020-03-28 08:00 | 2020-03-29 16:00 | N | N | switch maintenance, check reversing switch and SF6 leak | Line, Shunts, Transformer | 38.3TR (ENMAX 38), 38.1C (ENMAX 38), 38.83L (ENMAX 39 - ENMAX 38), 38.1TR (ENMAX 38) | HV SW maint SW84, SW85, SW86, MD-38.1TR, 38MD138-38.1TR B PH Whip Not Reset. Check reversing switch 38.1TR. One day only for transformer combo. Investigate SF6 leak on 39B138-38.83. SF6 sample 39B138-38.83 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 740S 704, 740s 702T (740s H.R.Milner) | 2020-03-30 08:00 | 2020-04-13 08:00 | N | N | replace breaker 704 and re conductor switches | Terminal Equipment, Transformer | 740s 702T (740s H.R.Milner), 740s 704 (740s H.R. Milner) | replace breaker 704 and re conductor switches 704X to be closed & floating BKR 700 to serve as 7L20 line protection (702T needs to be switched OOS) | Pre-Condition
EPCOR | 814s T1 (814s Bellamy), Rossdale BR721 (Rossdale) | 2020-03-30 08:00 | 2020-03-31 16:00 | N | Y | doble and breaker maintenance | Transformer, Circuit Breaker | Rossdale BR721 (Rossdale), 814s T1 (814s Bellamy) | Doble Testing and Breaker Mtce | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX | 40.1TR (ENMAX 40) | 2020-03-30 08:00 | 2020-03-31 16:00 | N | N | T-60 upgrade phase 2 check reversing switch | Transformer |  |  | For Information Only
ENMAX | 162.4TR (ENMAX 162 Beddington) | 2020-03-30 08:00 | 2020-04-03 15:00 | N | N | GIS minor maintenance | Transformer |  | GIS Minor Maintenance. SW903, SW907, SW909, SW615, SW815, SW912, SW616, SW816, SW914G, SW618, SW818, SW905, SW911. 162B25-162.4TR, 162B25-162.115, 162B25-162.116, 162B25-162.118, 162B25-162.117, SW617, SW717, SW817 | For Information Only
ENMAX | 10.2TR (ENMAX 10) | 2020-03-30 08:00 | 2020-04-02 16:00 | N | N | urgent outage to investigate odor from switchgear | Transformer |  |  | For Information Only
ATCO | 770s 703T (770s Three Hills) | 2020-03-30 08:00 | 2020-04-17 17:00 | N | N | adding a new 51-LV/500BS2 protection | Transformer | 770s 703T (770s Three Hills) | 770S Protection Upgrade - 703T Outage Adding a new 51-LV/500BS2 protection which requires modifying CT circuits on the secondary of 703T. | For Information Only
ALTALINK | 415s T2 (415s Drywood) | 2020-03-30 08:30 | 2020-04-02 16:30 | N | Y | isolate customer power cables to facilitate installation of new replacement cables | Transformer | 415s T2 (415s Drywood) | Isolate customer power cables to facilitate installation of new replacement cables. Customer requested outage. | Restricts Generation
EPCOR | 987s T1 (987s Clover Bar), 987s CCP7213 (987s Clover Bar), 987s CCP7214 (987s Clover Bar) | 2020-03-30 09:00 | 2020-03-30 14:30 | N | Y | repair of disconnect switch | Transformer, Circuit Breaker | 987s T1 (987s Clover Bar), 987s CCP7214 (987s Clover Bar), 987s CCP7215 (987s Clover Bar), 987s CDS20 (987s Cloverbar) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L22 (811s Clairmont Lake - 7L22D2) | 2020-03-30 09:00 | 2020-04-07 14:00 | N | Y | customer road move for county of Grande Prairie | Line | 7L22 (811s Clairmont Lake - 7L22D2) | Customer road move for county of Grande Prairie | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 115s T1 (115s Mt.Allan) | 2020-03-30 09:00 | 2020-03-30 17:00 | N | N | replace terminators on AMI power cables at 115s26 | Transformer | 115s T1 (115s Mt.Allan) |  | For Information Only
ATCO | 846s 701T (846s Grand Centre) | 2020-03-30 09:00 | 2020-03-30 16:00 | N | N | 86-50BF/700BS1 wiring install/testing (panel 1k) commission wiring/50BF | Transformer | 846s 701T (846s Grand Centre) | 701T OUT OF SERVICE, 702T SUPPLYING 25KV FEED Isolate 701T for the following work to commence: 86-50BF/700BS1 wiring install/testing (panel 1k) Commission wiring/50BF | For Information Only
ALTALINK | 514L (513s Lundbreck - 514L198) | 2020-03-30 09:00 | 2020-04-02 18:00 | N | N | urgent repair insulators structures range 207-437 | Line | 514L (513s Lundbreck - 514L198) |  | For Information Only
ALTALINK | 172L (254s Coaldale - 172L944C) | 2020-03-30 09:00 | 2020-03-30 16:00 | N | N | modify guy wires | Line | 172L (254s Coaldale - 172L944C) | Modify guy wires on 172L1021C, working in close proximity to 172L conductor. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENEL | 205s T2 (205s Castle Rock Ridge) | 2020-03-30 10:00 | 2020-04-01 12:00 | N | Y | substation outage | Transformer |  |  | 240 kV, Restricts Generation
ALTALINK | 163s 1252 (163s Amoco Empress) | 2020-03-30 11:00 | 2020-03-31 17:00 | N | Y | relay testing and settings changes | Circuit Breaker | 163s 1252 (163s Amoco Empress) | Settings Changes of Sync Check and Functional Testing on 163s1252 CUH90 relay. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-03-30 12:00 | 2020-04-02 18:00 | N | N | components/structure replacements (structures #1 - 61) | Line | 798L (364s Whitecourt Industrial - 77s Sagitawah) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 28s 52 (28s West Brooks) | 2020-03-30 13:30 | 2020-04-03 16:00 | N | Y | CT replacement | Circuit Breaker | 28s 52 (28s West Brooks) | 240 kV CT replacement (28s52) | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 987s C2405 (987s Clover Bar) | 2020-03-31 07:00 | 2020-03-31 17:00 | N | Y | urgent - replace leaking capacitors | Circuit Breaker |  | Urgent | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2020-03-31 07:00 | 2020-03-31 17:00 | N | Y | replace structure | Line |  | Replace structure 20 | Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 115s T2 (115s Mt.Allan) | 2020-03-31 09:00 | 2020-04-06 17:00 | N | N | terminators replacement | Transformer |  | Replace terminators on AMI power cables at 115s27. | For Information Only
ATCO | 846s 702T (846s Grand Centre) | 2020-03-31 09:00 | 2020-03-31 16:00 | N | N | 86-50BF/700BS1 wiring install/testing (panel 2k) commission wiring/50BF | Transformer | 846s 702T (846s Grand Centre) | 702T OUT OF SERVICE, 701T SUPPLYING 25KV FEED Isolate 702T for the following work to commence: 86-50BF/700BS1 wiring install/testing (panel 2k) Commission wiring/50BF | For Information Only
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2020-03-31 09:00 | 2020-03-31 17:00 | N | Y | replacement of surge arrestor | Line |  | Replacement of surge arrestor counter | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.2TR (ENMAX 40) | 2020-04-01 08:00 | 2020-04-02 16:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
EPCOR | 814s T2 (814s Bellamy), Rossdale BR722 (Rossdale) | 2020-04-01 08:00 | 2020-04-02 15:00 | N | N | doble testing and breaker maintenance | Transformer, Circuit Breaker | 814s T2 (814s Bellamy), Rossdale BR722 (Rossdale) |  | Over/Under Voltage, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8), ENMAX 3 B138-3.82 (ENMAX 3), ENMAX 8 B138-5A0 (ENMAX 8), ENMAX 8 B138-6A0 (ENMAX 8) | 2020-04-01 08:00 | 2020-04-10 18:00 | N | N | protection upgrade | Line, Circuit Breaker | 3.82L (ENMAX 3 - ENMAX 8) | install new protection 87BA-Z65, 87BB-Z65 on138kV ring | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 987s C72C1 (987s Clover Bar) | 2020-04-01 08:00 | 2020-07-26 17:00 | N | N | cutover of new breaker fail protection to C72C1 breaker | Circuit Breaker | 987s C72C1 (987s Clover Bar) |  | Pre-Condition
ALTALINK | 149s 3 (149s Nisku), 149s C1 (149s Nisku) | 2020-04-01 08:00 | 2020-04-01 12:30 | N | N | operate breaker to test POW controller | Circuit Breaker, Shunts |  |  | Pre-Condition
ATCO | 856s 505 (856s Kinosis), 856s 505R (856s Kinosis) | 2020-04-01 08:00 | 2020-04-01 11:00 | N | N | PRC-005 - test 505 trip coil(s), only one breaker tested at a time | Circuit Breaker, Shunts | 856s 505R (856s Kinosis) | PRC-005 Test 505 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
Syncrude | Aurora 23 (Aurora), Aurora 24 (Aurora), MH1 (Aurora - Aurora) | 2020-04-01 08:00 | 2020-04-08 20:00 | N | N | 72KV zone 5 outage - Aurora | Circuit Breaker, Line | MH1 (Aurora - Aurora) |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2020-04-01 09:00 | 2020-04-01 13:00 | N | Y | maintenance | Switch | 62s 11 (62s Brazeau) |  | For Information Only, Restricts Generation
ALTALINK | 498s 100X (498s Tilley), 100L (498s Tilley - 895s Suffield) | 2020-04-01 09:00 | 2020-04-01 18:00 | N | N | test CT's (saturation and ratio) as well as fix CT wiring issue | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 856s 707 (856s Kinosis), 856s 707C (856s Kinosis) | 2020-04-01 11:00 | 2020-04-01 14:00 | N | N | PRC-005 - test 707 trip coil(s), only one breaker tested at a time | Circuit Breaker, Shunts | 856s 707C (856s Kinosis) | PRC-005 Test 707 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
ALTALINK | 163s 1352 (163s Amoco Empress) | 2020-04-01 11:00 | 2020-04-02 17:00 | N | Y | setting changes on sync check and functional testing CUH90 relay | Circuit Breaker | 163s 1352 (163s Amoco Empress) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 856s 708 (856s Kinosis), 856S 708C | 2020-04-01 14:00 | 2020-04-01 17:00 | N | N | PRC-005 test 708 trip coil(s), only one breaker tested at a time | Circuit Breaker, Terminal Equipment | 856s 708C (856s Kinosis) | PRC-005 Test 708 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
ATCO | 856s 701 (856s Kinosis) | 2020-04-02 08:00 | 2020-04-02 11:00 | N | N | PRC-005 test 701 trip coil(s), only one breaker tested at a time | Circuit Breaker | 856s 701 (856s Kinosis) | PRC-005 Test 701 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
ALTALINK | 186s 17 (186s Dry Creek), 186s C1 (186s Dry Creek) | 2020-04-02 08:30 | 2020-04-02 17:00 | N | N | breaker maintenance | Circuit Breaker, Shunts | 186s C1 (186s Dry Creek) | 138kV breaker maintenance | Pre-Condition
EPCOR | 805s C1 (805s Jasper), 805s J2408 (805s Jasper) | 2020-04-02 09:00 | 2020-04-02 14:30 | N | Y | repair spring charging indicator | Shunts, Circuit Breaker | 805s J2408 (805s Jasper) |  | 240 kV, Pre-Condition
ATCO | 856s 703 (856s Kinosis) | 2020-04-02 11:00 | 2020-04-02 14:00 | N | N | PRC-005 test 703 trip coil(s), only one breaker tested at a time | Circuit Breaker | 856s 703 (856s Kinosis) | PRC-005 Test 703 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
BLACKSPRING | 485S Black Springs | 2020-04-02 13:00 | 2020-04-02 15:00 | N | N | change power transformer taps | Station |  |  | For Information Only
ATCO | 856s 704 (856s Kinosis) | 2020-04-02 14:00 | 2020-04-02 17:00 | N | N | PRC-005 test 704 trip coil(s), only one breaker tested at a time | Circuit Breaker | 856s 704 (856s Kinosis) | PRC-005 Test 704 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
EPCOR | 987sC2407 (987s Clover Bar), 987s T3 (987s Clover Bar) | 2020-04-03 08:00 | 2020-04-03 16:00 | N | Y | doble testing | Circuit Breaker, Transformer | 987sC2407 (987s Clover Bar) |  | 240 kV, Pre-Condition
ATCO | 856s 705 (856s Kinosis) | 2020-04-03 08:00 | 2020-04-03 11:00 | N | N | PRC-005 test 705 Trip Coil(s), only one breaker tested at a time | Circuit Breaker | 856s 705 (856s Kinosis) | PRC-005 Test 705 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
EPCOR | 803s L2402 (803s Lambton), 803s L2405 (803s Lambton), 803s T2 (803s Lambton) | 2020-04-03 09:00 | 2020-04-03 14:30 | N | Y | repair difficult to close condition | Circuit Breaker, Transformer | 803s L2402 (803s Lambton), 803s L2405 (803s Lambton), 803s T2 (803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 856s 706 (856s Kinosis) | 2020-04-03 11:00 | 2020-04-03 14:00 | N | N | PRC-005 test 706 Trip Coil(s), only one breaker tested at a time | Circuit Breaker | 856s 706 (856s Kinosis) | PRC-005 Test 706 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Pre-Condition
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22), 22PT138-31 (ENMAX 22), ENMAX 13 B138-13.82 (ENMAX 13) | 2020-04-03 13:00 | 2020-04-03 18:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment, Circuit Breaker | 13.82L (ENMAX 13 - ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CapitalPower | WHT1 Whitla | 2020-04-03 14:00 | 2020-04-03 15:00 | N | N | power park control (PPC) outage | Unit |  |  | For Information Only
EPCOR | Victoria VDS21 (Victoria) | 2020-04-06 07:00 | 2020-04-06 17:00 | N | N | repair disconnect | Switch | CV5 (557s Castle Downs - 511s Victoria) |  | Contingency Requires Mitigation
ENMAX | 14.2TR (ENMAX 14) | 2020-04-06 08:00 | 2020-04-30 16:00 | N | N | power factor test transformer | Transformer | 14.2TR (ENMAX 14) | Power factor test transformer. Transformer secondary cable tests. Transformer maintenance. Oil sampling MT, TC | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2020-04-06 08:00 | 2020-04-06 15:00 | N | N | doble testing and breaker maintenance | Circuit Breaker | Hardisty H722 (Hardisty Epcor) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 740s 701 (740s H.R. Milner) | 2020-04-06 08:00 | 2020-04-13 16:00 | N | Y | RAS testing & coordination on BKR 701 | Circuit Breaker | 740s 701 (740s H.R. Milner) | RAS testing & coordination on BKR 701 This work has been coordinated with Milner Power Generation scheduled down time | Restricts Generation
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2020-04-06 08:00 | 2020-04-06 09:00 | N | N | spring pothead washing | Line | 1.80L (ENMAX 28 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 28.1TR (ENMAX 28) | 2020-04-06 08:00 | 2020-04-27 16:00 | N | N | arc flash mitigation project | Transformer | 28.1TR (ENMAX 28) | arc flash mitigation project. Protection outage and MV cable swap. | For Information Only
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2020-04-06 09:00 | 2020-04-06 10:00 | N | N | spring pothead washing | Line | 1.81L (ENMAX 20 - ENMAX 1) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 917s 703 (917s Horse River) | 2020-04-06 10:00 | 2020-04-06 15:00 | N | N | test breaker trip coils | Circuit Breaker | 917s 703C (917s Horse River) | PRC-005 - TRIP COIL TESTING - BREAKER 703 @ 917S PRC-005 Test 703 Breaker trip coil(s) 703 Breaker at 917S HORSE RIVER OOS | Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2020-04-06 10:00 | 2020-04-06 11:00 | N | N | spring pothead washing | Line | 9.83L (ENMAX 9 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2020-04-06 11:00 | 2020-04-06 12:00 | N | N | spring pothead washing | Line | 33.84L (ENMAX 43 - ENMAX 33) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 163s 1552 (163s Amoco Empress) | 2020-04-06 11:00 | 2020-04-07 17:00 | N | Y | settings changes of sync check and functional testing on 163s1552 CUH90 relay | Circuit Breaker | 163s 1552 (163s Amoco Empress) | Settings Changes of Sync Check and Functional Testing on 163s1552 CUH90 relay. | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 428s T2 (428s Namaka) | 2020-04-06 11:30 | 2020-04-08 16:30 | N | N | maintain, doble and fix leaks on T2, maintain 138kV breaker 428s652 | Transformer | 428s T2 (428s Namaka) |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), 15.2TR (ENMAX 15) | 2020-04-06 12:00 | 2020-04-06 18:00 | N | N | substation washing | Line, Transformer | 15.62L (ENMAX 15 - ENMAX 16) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-04-06 12:00 | 2020-04-08 18:00 | N | N | components/structure replacements (structures #1 - 61) | Line | 798L (364s Whitecourt Industrial - 77s Sagitawah) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 917s 706 (917s Horse River) | 2020-04-06 12:00 | 2020-04-06 15:00 | N | N | test breaker trip coils | Circuit Breaker | 917s 706C (917s Horse River) | PRC-005 - TRIP COIL TESTING - BREAKER 706 @ 917S PRC-005 Test 706 Breaker trip coil(s) 706 Breaker at 917S Horse River OOS. | Pre-Condition
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2020-04-07 08:00 | 2020-04-07 08:30 | N | Y | emergency outage to remove balloons | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 132s 6 (132s Ware Junction) | 2020-04-07 08:00 | 2020-04-07 17:30 | N | Y | breaker maintenance | Circuit Breaker | 132s 6 (132s Ware Junction) | Maintain 240kV SF6 breaker. | 240 kV
ATCO | 7L38 (875s Algar - 917s Horse River), 917s 704 (917s Horse River) | 2020-04-07 10:00 | 2020-04-07 12:00 | N | N | trip coil testing | Line, Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 704 @ 917S 704 Breaker at 917S Horse River OOS 7L38 OPEN-ENDED AT 917S HORSE RIVER ONLY ONE LINE OOS AT A TIME. NO OVERLAP IS PLANNED | Creates Radial Feeds, Firm Load Loss
EPCOR | Kennedale T1 (Kennedale), Kennedale K721 (Kennedale), Kennedale K722 (Kennedale) | 2020-04-07 10:00 | 2020-04-09 17:00 | N | N | emergency outage, oil leak | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L121 (917s Horse River - 7L121D2), 917s 705 (917s Horse River) | 2020-04-07 12:00 | 2020-04-08 12:00 | N | N | trip coil testing | Line, Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 705 @ 917S 705 Breaker at 917S Horse River OOS 7L121 OPEN-ENDED AT 917S HORSE RIVER ONLY ONE LINE OOS AT A TIME. NO OVERLAP IS PLANNED | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | Hardisty H726 (Hardisty Epcor), 72LH8 (Hardisty - 803s Lambton) | 2020-04-08 07:00 | 2020-04-08 13:12 | N | N | maintenance & doble | Circuit Breaker, Line | Hardisty H726 (Hardisty Epcor), 72LH8 (Hardisty - 803s Lambton) |  | Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 2.80L (ENMAX 2 - ENMAX 23) | 2020-04-08 08:00 | 2020-04-08 16:00 | N | N | substation building upgrades, install Roxtec plugs in ducts | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2020-04-08 08:00 | 2020-04-09 17:00 | N | N | line move between structures 58 & 69 | Line | 761L (38s East Edmonton - 71s Lamoureux) |  | For Information Only
ENMAX | EGC1 Shepard | 2020-04-08 08:00 | 2020-04-22 16:00 | N | N | Blade Upgrade. MC increase to 483MW. ISD: Apr 15, 2020. | Unit
ATCO | 7L38 (875s Algar - 917s Horse River), 875s 701 (875s Algar) | 2020-04-08 12:30 | 2020-04-08 15:00 | N | N | PRC-005 test 701 trip coils | Line, Circuit Breaker |  | PRC-005 Test 701 Trip Coil(s), only one breaker tested at a time, 7L38 open ended, there will be no overlap with 7L170, approximate testing time per breaker = 2 hours | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 875s 702 (875s Algar), 7L170 (875s Algar - 2011s Dawes) | 2020-04-08 15:01 | 2020-04-08 17:00 | N | N | PRC-005 test 702 trip coils | Circuit Breaker, Line |  | PRC-005 Test 702 Trip Coil(s), only one breaker tested at a time, 7L170 open ended, there will be no overlap with 7L38, approximate testing time per breaker = 2 hours | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2020-04-09 08:00 | 2020-04-09 12:00 | N | N | substation washing | Line, Transformer, Terminal Equipment |  | Spring Substation Washing. Check reversing switch. | Creates Radial Feeds, Firm Load Loss
Syncrude | Aurora 31 (Aurora), Aurora 32 (Aurora), Aurora 33 (Aurora), Aurora 34 (Aurora), Aurora C1 (Aurora), MH2 (Aurora - Aurora) | 2020-04-09 08:00 | 2020-04-17 20:00 | N | N | 72kV zone 3 outage - Aurora | Circuit Breaker, Shunts, Line |  |  | For Information Only
ENMAX | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2020-04-09 12:00 | 2020-04-09 18:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  | spring substation washing. Check reversing switch. | Creates Radial Feeds, Firm Load Loss
ATCO | 2018s T1 (2018s Muir) | 2020-04-09 16:30 | 2020-04-10 16:00 | N | N | forced outage | Transformer
ALTALINK | 283s C1 (283s Violet Grove) | 2020-04-10 08:00 | 2020-04-14 16:00 | N | N | Breaker Fail Alarm | Shunts |  | Settings changes on C1 relays. Redundant protection always in service. | For Information Only
ALTALINK | 227S Cutting Lake | 2020-04-11 08:00 | 2020-04-12 17:30 | N | N | doble, maintain, fix leaks T1, fix hot switch 227s8 | Station
ATCO | 7L80 (740s H.R.Milner - 857s Kakwa Ridge), 740s 705 (740s H.R. Milner) | 2020-04-13 08:00 | 2020-04-27 16:00 | N | Y | maintenance (P2158) | Line, Circuit Breaker | 7L80 (740s H.R.Milner - 733s Simonette), 740s 705 (740s H.R. Milner) | replace 705 PT and 705 CT 7L80 required open ended for the duration | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
EPCOR | 1098L (805s Jasper - Poundmaker) | 2020-04-14 07:00 | 2020-04-15 17:00 | N | Y | repair PMDS9 | Line | 1098L (805s Jasper - Poundmaker) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L54 (794s Valleyview - 813s Little Smoky) | 2020-04-14 08:00 | 2020-04-17 17:00 | N | N | cross arm changes | Line | 7L54 (794s Valleyview - 813s Little Smoky) | Cross arm changes | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | Kennedale T1 (Kennedale), Kennedale K721 (Kennedale), Kennedale K722 (Kennedale) | 2020-04-14 08:00 | 2020-04-17 15:00 | N | N | continue the oil leak repair work left from Apr 9 | Transformer, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 5s C3 (5s East Calgary) | 2020-04-14 08:00 | 2020-07-10 16:00 | N | N | reconfigure / replace caps | Shunts | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | Reconfigure Cap bank breaker and switches. Remove interlock, Replace C3/C10 with Like for Like Capacitors 54MVAR, Replace Cap Bank LA's to new Gap Style | For Information Only
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-04-14 09:00 | 2020-06-24 17:00 | N | N | reconfigure / replace caps | Shunts | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | Reconfigure Cap bank breaker and switches. Remove interlock, Replace C3/C10 with Like for Like Capacitors 54MVAR, Replace Cap Bank LA's to new Gap Style | For Information Only
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2020-04-14 09:00 | 2020-04-16 17:00 | N | N | maintenance | Transformer | 191s T1 (191s N.W.Cardiff) | Replace control cables in T1 cabinet. Install new Junction Box and cabling. | For Information Only
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2020-04-14 09:00 | 2020-04-14 18:00 | N | N | urgent repair 225L490 loose damper | Line | 225L (229s Glenwood - 385s Spring Coulee) | P5 Urgent repair 225L490 Loose damper on structure 490 of 225L on the scheduled detailed ground patrol. It has worn through several strands at this point and will not get any better, located on rebuilt section of line between Spring Coulee and Glenwood substations on the left phase | Contingency Requires Mitigation, Over/Under Voltage, Overload
ALTALINK | 308s 776W (308s Albchem Beaverhill Creek), 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2020-04-14 09:30 | 2020-04-14 17:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | Maintenance on 308s776W breaker. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake) | 2020-04-14 10:00 | 2020-04-16 17:00 | N | N | line clearance mitigation | Line |  | Line Clearance Mitigation 858L Strs Range 2, 3-197-198, also Re-tensioning the Line ( Spans 154-157). Double circuit with 804L (R/B Required) | Over/Under Voltage, Overload, Pre-Condition
ENMAX | 1.85L (ENMAX 1 - ENMAX 8) | 2020-04-14 10:00 | 2020-04-14 12:00 | N | N | DCTRP. outage required for 138kV bus energization | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 396s C1 (396s Pincher Creek) | 2020-04-15 08:00 | 2020-04-15 17:00 | N | N | replace 3 leaking capacitors | Shunts | 396s C1 (396s Pincher Creek) |  | For Information Only, Pre-Condition
ENMAX | 36.3TR (ENMAX 36) | 2020-04-15 08:00 | 2020-04-16 16:00 | N | N | secondary cable test | Transformer |  |  | For Information Only
ALTALINK | 71s 1752 (71s Lamoureux) | 2020-04-15 08:30 | 2020-04-15 17:30 | N | Y | breaker maintenance | Circuit Breaker | 71s 1752 (71s Lamoureux) | Breaker maintenance | 240 kV, Contingency Requires Mitigation
ALTALINK | 15s 452 (15s Fort Macleod) | 2020-04-15 08:30 | 2020-04-15 17:00 | N | N | breaker work | Circuit Breaker | 15s 452 (15s Fort Macleod) | 15s452 (cb1662) SF6 138kV SFMT | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L85 (801s Anderson - 803s Bullpound) | 2020-04-15 09:00 | 2020-04-15 15:00 | N | N | replace interrupter bottle on 7L85D4 | Line | 7L85 (801s Anderson - 803s Bullpound) | Replace Interrupter bottle on 7L85D4, Bullpound Load will be off-loaded to other subs | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 420s 636 (420s Broadmoor), 636L (420s Broadmoor - 746s Sherwood Park) | 2020-04-15 09:00 | 2020-04-15 17:00 | N | N | breaker maintenance | Circuit Breaker, Line | 636L (420s Broadmoor - 746s Sherwood Park) 420s 636 (420s Broadmoor) | Breaker maintenance | Creates Radial Feeds, Firm Load Loss
ALTALINK | 432s 896 (432s Carvel), 896L (19s Wabamun - 432s Carvel) | 2020-04-15 09:30 | 2020-04-15 17:00 | N | N | maintenance on 432s896 breaker | Circuit Breaker, Line | 896L (19s Wabamun - 432s Carvel) 432s 896 (432s Carvel) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 150s 723W (150s Clyde) | 2020-04-15 10:00 | 2020-04-15 10:30 | N | N | upgrade MPLS node at 9150R | Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 225L (67s Stirling - 225s Magrath) | 2020-04-15 10:00 | 2020-04-15 16:00 | N | N | urgent repair | Line |  | P5 Urgent repair 225L238 Structure 225L238 left phase eye bolt appears to be backing out of cross arm or arm is starting to decay. Require urgent repair | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 856s 903T (856s Kinosis) | 2020-04-15 10:00 | 2020-05-08 17:00 | N | Y | 903T tertiary 59N protection installation | Transformer | 856s 903T (856s Kinosis) | 903T Tertiary 59N Protection Installation at 856S Kinosis, 901T and 902T will be Inservice @ 856S | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 163s 1752 (163s Amoco Empress) | 2020-04-15 11:00 | 2020-04-16 17:00 | N | Y | settings changes of sync check and functional testing on CUH90 relay. | Circuit Breaker | 163s 1752 (163s Amoco Empress) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 913L (69s North Barrhead - 732s Mitsue) | 2020-04-16 07:00 | 2020-04-24 18:00 | N | Y | urgent repair line clearance mitigation | Line | 913L (69s North Barrhead - 732s Mitsue) | Urgent repair line clearance mitigation to adjust sag between Structures #187 - 196 and between Structures #199 - 202 | 240 kV, Overload, Pre-Condition,Affects Cranking Path
ALTALINK | 71s 1052 (71s Lamoureux), 71s C2 (71s Lamoureux) | 2020-04-16 08:30 | 2020-04-16 16:30 | N | N | breaker maintenance | Circuit Breaker, Shunts | 71s C2 (71s Lamoureux) |  | Pre-Condition
ALTALINK | 432s 790 (432s Carvel), 790L (432s Carvel - 790L57) | 2020-04-16 09:30 | 2020-04-16 17:00 | N | N | maintenance on 432s790 breaker | Circuit Breaker, Line | 432s 790 (432s Carvel) 790L (432s Carvel - 790L57) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 731L (38s East Edmonton - 420s Broadmoor), 38s 731E (38s East Edmonton) | 2020-04-16 09:30 | 2020-04-16 17:00 | N | N | maintenance on 38s731E breaker | Line, Circuit Breaker | 38s 731E (38s East Edmonton) | Maintenance on 38s731E breaker including 1st trip test. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 741s 701 (741s Fox Creek), 7L90 (741s Fox Creek - 7L90D3) | 2020-04-16 10:00 | 2020-04-16 16:00 | N | N | emergency breaker repair due to low SF6 | Circuit Breaker, Line | 7L90 (741s Fox Creek - 7L90D3) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 799s T1 (799s Coleman) | 2020-04-17 | 2020-04-17 04:45 | N | N | install new switch for 799s22 and new station service transformer | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 747L (37s North Calder - 99s North St Albert), 711L (Inland Cement - 747L tap) | 2020-04-17 07:00 | 2020-04-19 17:00 | N | Y | 711L4 air break - replacement | Line | 711L (Inland Cement - 747L tap), 747L (37s North Calder - 99s North St Albert) | - 711L4 (Replacement) Out of Service from Apr 17 - Apr 26 - 711L / 747L can be re-energized during the week as 711L4 will be temporarily bypassed. - 711L / 747L Two complete line outages required. Apr 17 (07:00) - Apr 19 (18:00) Continuous Apr 25 (07:00) - Apr 26 (16:00) Continuous Inland Cement has approved these outages in principle & along with EPCOR Operations would like to get confirmation regarding availability ASAP. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | HUL1 Hull Solar | 2020-04-17 08:00 | 2020-04-24 16:00 | N | N | P1878. 25 MW DER. ISD Apr 24, 2020 | Unit
ENMAX | 23.3TR (ENMAX 23), 2.80L (ENMAX 2 - ENMAX 23) | 2020-04-17 08:00 | 2020-04-17 12:00 | N | N | spring substation washing | Transformer, Line | 2.80L (ENMAX 2 - ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss
VISIONREQ | 354s DVAR2 (354s Summerview), 354s T4 (354s Summerview) | 2020-04-17 09:00 | 2020-04-17 15:00 | N | Y | install pilings | Shunts, Transformer |  |  | Restricts Generation
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23), 23.4TR (ENMAX 23) | 2020-04-17 12:00 | 2020-04-17 18:00 | N | Y | spring substation washing and verify 23MD138-23.4TR west phase closing | Line, Transformer | 23.80L (74s Janet - ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 780s 706 (780s Lubicon), 780s 706C (780s Lubicon) | 2020-04-17 21:32 | 2020-05-22 16:00 | N | N | forced outage breaker relay fail | Circuit Breaker, Shunts |  |  | Pre-Condition
MILNERP | HRM H.R. Milner | 2020-04-18 08:00 | 2020-05-30 16:00 | N | N | P1581. MC 208 MW ISD May 09, 2020 | Unit
ENMAX | 1.80L (ENMAX 1 - ENMAX 28), 28.1TR (ENMAX 28) | 2020-04-18 08:00 | 2020-04-18 18:00 | N | N | spring substation washing & check reversing switch | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 987s CK725 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale) | 2020-04-19 07:00 | 2020-04-19 17:00 | N | N | breaker maintenance | Circuit Breaker, Line | 987s CK725 (987s Clover Bar), 72CK12 (987s Clover Bar - Kennedale) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 24.81L (ENMAX 24 - ENMAX 31), 31.2TR (ENMAX 31), 31.3TR (ENMAX 31) | 2020-04-19 08:00 | 2020-04-19 13:00 | N | N | spring substation washing &check reversing switch 31.2TR, 31.3TR | Line, Transformer | 24.81L (ENMAX 24 - ENMAX 31) 31.84L (ENMAX 31 - ENMAX 32) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31.1C (ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31) | 2020-04-19 13:00 | 2020-04-19 18:00 | N | N | spring substation washing | Line, Shunts, Transformer | 9.80L (ENMAX 9 - ENMAX 31) 138-31.CAP (ENMAX 31) |  | For Information Only, Pre-Condition
EPCOR | 805s J2403 (805s Jasper) | 2020-04-20 07:00 | 2020-04-24 17:00 | N | Y | Maintenance / Doble | Circuit Breaker | 805s J2403 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | Namao N722 (Namao) | 2020-04-20 07:00 | 2020-04-21 17:00 | N | N | maintenance / Doble | Circuit Breaker | Namao N722 (Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 32.83L (ENMAX 32 - ENMAX 40), 40.1TR (ENMAX 40) | 2020-04-20 08:00 | 2020-04-20 12:00 | N | N | substation washing | Line, Transformer | 32.83L (ENMAX 32 - ENMAX 40) | Substation Washing. Check reversing switch. | Creates Radial Feeds, Firm Load Loss
ENMAX | ENMAX 21 B69-15.60 (ENMAX 21), 15.60L (ENMAX 15 - ENMAX 21) | 2020-04-20 08:00 | 2020-04-20 16:00 | N | N | breaker maintenance 21B69-15.60 | Circuit Breaker, Line |  | HV breaker maintenance 21B69-15.60. SF6 sample 21B69-15.60. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.3TR (ENMAX 13) | 2020-04-20 08:00 | 2020-04-30 16:00 | N | N | replace HV bushing and CT | Transformer | 13.3TR (ENMAX 13) | HV Bushing and CT replacement. Oil sampling MT, TC | For Information Only
ATCO | 856s 901 (856s Kinosis) | 2020-04-20 08:00 | 2020-04-20 12:00 | N | Y | test trip coils | Circuit Breaker | 856s 901 (856s Kinosis) | PRC-005 Test 901 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 846s 702 (846s Grand Centre), 7L24 (846s Grand Centre - 7L24D3) | 2020-04-20 08:00 | 2020-04-24 16:00 | N | Y | relay protection upgrade | Circuit Breaker, Line | 7L24 (846s Grand Centre - 7L24D3) | ISOLATE 702 FOR THE FOLLOWING WORK TO COMMENCE: RELAY PROTECTION UPGRADE PANEL 7L24 (PANEL 2C) 86-50BF/700BS1 PARTIAL INSTALL/TESTING (PANEL 2C) INSTALL NEW RELAY (21A-SIEMENS) CHANGE CT CORES GOING TO RELAYS (702CT WORK) DEMO METERING FROM ION 7300, METERING WILL BE DONE THROUGH SEL RELAY AFTER. COMMISSION WIRING/RELAYS/CT-RATIOS | Creates Radial Feeds, Firm Load Loss
ENMAX | 27.2TR (ENMAX 27) | 2020-04-20 08:00 | 2020-05-05 16:00 | N | N | maintenance | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch. | For Information Only
ALTALINK | 283s C1 (283s Violet Grove) | 2020-04-20 08:00 | 2020-06-08 16:00 | N | N | forced ouatge due to breaker gas issue | Shunts | 283s C1 (283s Violet Grove) |  | For Information Only
Syncrude | Aurora 211 (Aurora), Aurora 213 (Aurora), Aurora 223 (Aurora), Aurora T11 (Aurora), AL-1 (Aurora - D05 Syncrude), 72 kV Bus-2 (Aurora) | 2020-04-20 08:00 | 2020-05-03 20:00 | N | Y | maintenance | Circuit Breaker, Transformer, Line, Bus | Aurora T11 (Aurora) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L54 (794s Valleyview - 813s Little Smoky) | 2020-04-20 08:00 | 2020-04-23 17:00 | N | N | cross arm changes | Line | 7L54 (794s Valleyview - 813s Little Smoky) | Cross arm changes | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | ENMAX 65 B240-D130 (ENMAX 65), ENMAX 65 B240-D133 (ENMAX 65), 65.1TR (ENMAX 65) | 2020-04-20 08:00 | 2020-04-22 12:00 | N | Y | upgrade T-60 phase 2 | Circuit Breaker, Transformer | 65.1TR (ENMAX 65) | T-60 Upgrade Phase 2. Oil sampling MT, TC, Check reversing switch. Replace Switch Mech SW130, SW136. Install shrouds SW130, SW136. | 240 kV, Contingency Requires Mitigation
ALTALINK | 858L (40s Wetaskiwin - 289s Saunders Lake) | 2020-04-20 09:30 | 2020-04-22 17:45 | N | N | line clearance mitigation | Line |  | Continuation of Line Clearance Mitigation 858L Strs Range 2, 3-197-198, also Re-tensioning the Line ( Spans 154-157). | Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 305s C1 (305s Acheson), 305s 32 (305s Acheson) | 2020-04-20 10:00 | 2020-04-20 17:00 | N | N | maintenance | Shunts, Switch | 305s C1 (305s Acheson) | Maintenance on 305s32 breaker | For Information Only, Pre-Condition
ATCO | 856s 902 (856s Kinosis) | 2020-04-20 12:00 | 2020-04-20 17:00 | N | Y | test trip coils | Circuit Breaker | 856s 902 (856s Kinosis) | PRC-005 Test 902 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 368s C1 (368s Burdett), 368s C2 (368s Burdett) | 2020-04-20 12:00 | 2020-04-20 17:30 | N | N | fix bird cover up on C1 | Shunts | 368s C1 (368s Burdett) 368s C2 (368s Burdett) |  | For Information Only, Pre-Condition
ENMAX | 40.81L (ENMAX 40 - ENMAX 41), 40.2TR (ENMAX 40) | 2020-04-20 12:00 | 2020-04-20 18:00 | N | N | substation washing | Line, Transformer |  | Substation Washing. Check reversing switch. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 217s 652 (217s North Red Deer), 217s C1 (217s North Red Deer) | 2020-04-20 12:30 | 2020-04-30 17:30 | N | N | breaker replacement | Switch, Shunts | 217s C1 (217s North Red Deer) 217s 652 (217s North Red Deer) |  | For Information Only, Pre-Condition
ATCO | 7L33 (749s Flyingshot Lake - 7L33D3), 749s 703 (749s Flyingshot Lake), 749s 704 (749s Flyingshot Lake) | 2020-04-20 13:00 | 2020-04-22 12:00 | N | Y | PT replacement | Line, Circuit Breaker | 7L33 (749s Flyingshot Lake - 7L33D3) | 749S 703PT PCB PT replacement - Cat 1 2020 7L33 open ended; Ring bus will be open | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2020-04-21 07:00 | 2020-04-23 18:00 | N | Y | structure replacements to eliminate line clearance violation in 717L | Line | 717L (17s Benalto - 262s Rocky Mountain House) | Structure replacements to eliminate line clearance violation in 717L. Urgent P5 Work to be completed prior to May 1. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 33.1TR (ENMAX 33) | 2020-04-21 08:00 | 2020-04-21 12:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | ENMAX 47 B138-BT3 (ENMAX 47) | 2020-04-21 08:00 | 2020-04-21 16:00 | N | N | breaker maintenance SF6 sample | Circuit Breaker |  |  | For Information Only
ATCO | 856s 903 (856s Kinosis) | 2020-04-21 08:00 | 2020-04-21 12:00 | N | Y | PRC-005 test trip coil(s) | Circuit Breaker | 856s 903 (856s Kinosis) | PRC-005 Test 903 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2020-04-21 08:00 | 2020-04-21 10:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 71s 152 (71s Lamoureux) | 2020-04-21 08:00 | 2020-04-23 13:30 | N | N | maintenance on 71s152 breaker | Circuit Breaker | 71s 152 (71s Lamoureux) |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 38s 865N (38s East Edmonton), 865L (38s East Edmonton - 216s Knightsbridge) | 2020-04-21 08:30 | 2020-04-23 13:00 | N | N | maintenance on breaker | Circuit Breaker, Line | 865L (38s East Edmonton - 216s Knightsbridge) 38s 865N (38s East Edmonton) | maintenance on 38s865N breaker, replace grading caps for breaker no special requirements here | Creates Radial Feeds, Firm Load Loss
ALTALINK | 149s 3 (149s Nisku), 149s C1 (149s Nisku) | 2020-04-21 08:30 | 2020-04-21 17:00 | N | N | maintenance on 149s3 breaker | Circuit Breaker, Shunts | 149s 3 (149s Nisku) |  | For Information Only
EPCOR | Rossdale T2 (Rossdale) | 2020-04-21 08:30 | 2020-04-21 14:30 | N | N | emergency removal of bird nest | Transformer | Rossdale T2 (Rossdale) |  | For Information Only
ATCO | 802s 703T (802s Michichi Creek) | 2020-04-21 09:00 | 2020-04-21 16:00 | N | N | installing green jacket bird proofing | Transformer |  | Installing Green Jacket bird Proofing, 703T 25kv transferred to 702T | For Information Only
ALTALINK | 263s T1 (263s Strachan) | 2020-04-21 10:00 | 2020-04-28 15:30 | N | N | upgrade, replace and install equipment | Transformer | 263s T1 (263s Strachan) | 25kv bus 1 outage required to upgrade 25kv switches 263s10, 263s11, 263s17, 263s50. Replace 9qty 25kv post insulators, replace 1 25kv breaker 263s242X. Install 3qty 17kv MCOV arrestors. Install bird mitigation throughout 25kv bus 1 equipment. | For Information Only
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2020-04-21 10:00 | 2020-04-21 12:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 33.2TR (ENMAX 33) | 2020-04-21 12:00 | 2020-04-21 18:00 | N | N | spring substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2020-04-21 12:00 | 2020-04-21 16:00 | N | N | spring transmission line washing | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 856s 904 (856s Kinosis) | 2020-04-21 12:00 | 2020-04-21 17:00 | N | Y | PRC-005 test 904 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | Circuit Breaker | 856s 904 (856s Kinosis) | PRC-005 Test 904 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
AESO-SC | OATI | 2020-04-21 18:00 | 2020-04-21 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 102s 552 (102s Langdon) | 2020-04-22 07:30 | 2020-04-22 16:30 | N | Y | top up low gas and investigate leak | Circuit Breaker | 102s 552 (102s Langdon) | top up low gas and investigate leak | 240 kV
EPCOR | Namao N723 (Namao) | 2020-04-22 08:00 | 2020-04-22 15:30 | N | N | doble and breaker maintenance | Circuit Breaker | Namao N723 (Namao) | Doble and Breaker Mtce | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | ENMAX 32 B138-32BT5 (ENMAX 32) | 2020-04-22 08:00 | 2020-04-22 16:00 | N | N | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 32B138-32BT5. SF6 sample | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.60L (ENMAX 15 - ENMAX 21), 15.1TR (ENMAX 15) | 2020-04-22 08:00 | 2020-04-22 12:00 | N | N | substation washing | Line, Transformer |  | Substation Washing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 856s 906 (856s Kinosis) | 2020-04-22 08:00 | 2020-04-22 12:00 | N | Y | PRC-005 test trip coil(s) | Circuit Breaker | 856s 906 (856s Kinosis) | PRC-005 Test 906 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
PCLP | CRR2 Castle Rock Ridge 2 | 2020-04-22 08:30 | 2020-04-22 19:00 | N | Y | MET02 at Castle Rock Ridge II wind farm offline | Unit |  |  | For Information Only
ALTALINK | 115s T1 (115s Mt.Allan) | 2020-04-22 09:00 | 2020-04-22 13:00 | N | N | replace terminators on AMI power cables | Transformer |  |  | For Information Only
ATCO | 802s 702T (802s Michichi Creek) | 2020-04-22 09:00 | 2020-04-22 16:00 | N | N | installing bird proofing | Transformer |  | Installing Green Jacket bird Proofing, 702T 25kv transferred to 703T | For Information Only, Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), 15.2TR (ENMAX 15) | 2020-04-22 12:00 | 2020-04-22 18:00 | N | N | substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 65.2TR (ENMAX 65) | 2020-04-22 12:00 | 2020-04-24 16:00 | N | Y | upgrade phase 2, oil sampling maintenance, check reversing switch, replace switch | Transformer | 65.2TR (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation
ALPAC | 282S Grassland (Alpac) | 2020-04-22 17:00 | 2020-04-22 21:00 | N | N | phone maintenance | Station |  |  | For Information Only
EPCOR | 330P Genesee 500 kV Bus 1 | 2020-04-23 07:00 | 2020-04-23 17:00 | N | Y | Doble | Bus | 330P Genesee 500 kV Bus 1 |  | 500 kV, Contingency Requires Mitigation
ENMAX | ENMAX 5 B138-5BT7 (ENMAX 5) | 2020-04-23 08:00 | 2020-04-23 16:00 | N | N | SF6 sample | Circuit Breaker | ENMAX 5 5B138-5BT7 (ENMAX 5) |  | For Information Only, Pre-Condition
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32), 32PT138-Z32 (ENMAX 32) | 2020-04-23 08:00 | 2020-04-23 13:00 | N | N | spring substation washing | Line, Transformer, Terminal Equipment |  | Spring Substation Washing. Check reversing switch. | For Information Only, Pre-Condition
ALTALINK | 115s T2 (115s Mt.Allan) | 2020-04-23 09:00 | 2020-04-23 13:00 | N | N | replace terminators | Transformer |  | Replace terminators on AMI power cables at 115s27. | For Information Only, Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft) | 2020-04-24 07:00 | 2020-04-24 17:00 | N | N | replace hit 60' pole | Line |  | Line Maintenance & Upgrades | Firm Load Loss, Creates Radial Feeds
EPCOR | 330p Genesee 500 kV Bus 2 | 2020-04-24 07:00 | 2020-04-24 17:00 | N | Y | doble | Bus | 330p Genesee 500 kV Bus 2 |  | 500 kV, Contingency Requires Mitigation
ATCO | 800s 501C (800s Friedenstal) | 2020-04-24 09:30 | 2020-04-24 15:00 | N | N | urgent repair damaged insulator and test 501C | Shunts |  |  | Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2020-04-24 16:20 | 2020-04-29 17:00 | N | Y | emergency: leaky CVT | Line |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition,Affects Cranking Path
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13), 3.84L (ENMAX 3 - ENMAX 13), 13.3TR (ENMAX 13), 13.1TR (ENMAX 13) | 2020-04-25 07:00 | 2020-04-26 18:00 | N | N | HV bushing and CT replacement, HV SW maintenance SW81 and paint 138kV bus structure at 13sub | Line, Transformer | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) 3.84L (ENMAX 3 - ENMAX 13) | HV bushing and CT replacement. HV SW maint SW81. Paint 138kV bus structure at 13sub. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | Victoria VDS22 (Victoria), 72VN21 (511s Victoria - Namao) | 2020-04-25 07:00 | 2020-04-25 17:00 | N | N | repair disconnect | Switch, Line | Victoria VDS22 (Victoria) |  | For Information Only
ALTALINK, EPCOR | 747L (37s North Calder - 99s North St Albert), 711L (Inland Cement - 747L tap) | 2020-04-25 07:00 | 2020-04-26 17:00 | N | Y | 711L4 air break replacement | Line | 747L (37s North Calder - 99s North St Albert), 711L (Inland Cement - 747L tap) | Inland Cement has approved these outages in principle & along with EPCOR Operations would like to get confirmation regarding availability ASAP. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.3TR (ENMAX 9) | 2020-04-25 08:00 | 2020-04-26 16:00 | N | N | arc flash mitigation project | Transformer |  |  | For Information Only
EPCOR | 987s C72C1 (987s Clover Bar), 987s C1 (987s Clover Bar) | 2020-04-25 08:00 | 2020-04-26 17:00 | N | N | investigate and repair failed capacitors in bank | Circuit Breaker, Shunts | 987s C1 (987s Clover Bar) 987s C72C1 (987s Clover Bar) |  | For Information Only
ALTALINK | 58s T2 (58s Edson) | 2020-04-25 20:00 | 2020-04-28 15:51 | N | N | forced outage | Transformer |  |  | For Information Only
ATCO | 2075s ACF14 (2075s Newell) | 2020-04-27 07:00 | 2020-05-01 17:30 | N | Y | trip coil testing | Shunts | 2075s ACF14 (2075s Newell) | PRC-005 Trip Coil Testing, No constraints,other type C is available | For Information Only
EPCOR | 816s P2401 (816s Petrolia) | 2020-04-27 07:00 | 2020-05-01 17:00 | N | Y | doble and breaker maintenance | Circuit Breaker | 816s P2401 (816s Petrolia) | Doble and Breaker Mtce | 240 kV, Contingency Requires Mitigation
EPCOR | 330p 803 (330p Genesee) | 2020-04-27 07:00 | 2020-04-30 17:00 | N | N | doble and maintenance | Circuit Breaker | 330p 803 (330p Genesee) |  | For Information Only
EPCOR | Victoria V721 (Victoria) | 2020-04-27 07:00 | 2020-04-27 17:00 | N | N | doble and breaker maintenance | Circuit Breaker | Victoria V721 (Victoria) | Maintenance / Doble | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 339S Duchess | 2020-04-27 07:15 | 2020-05-02 15:45 | N | N | Installing and replacing equipment for future 138kV circuit breaker | Station | DUCHESS | Installing new 138kV CVTs, replacing 25kV equipment (strain insulators, post insulators, LAs), new screw piles for future 138kV circuit breaker | For Information Only
ENMAX | 13.60L (ENMAX 13 - ENMAX 27), 13.4TR (ENMAX 13) | 2020-04-27 08:00 | 2020-05-01 16:00 | N | N | lightning arrestor installation and transformer maintenance | Line, Transformer | 13.60L (ENMAX 13 - ENMAX 27) | 27s 13.60L Lightning Arrestor Installation. 13.4TR Power factor test transformer, Transformer Maintenance, Gas Relay Testing. Oil samplingli | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 24.2TR (ENMAX 24) | 2020-04-27 08:00 | 2020-04-28 16:00 | N | N | check reversing switch | Transformer |  | T-60 Upgrade Phase 2. Check reversing switch. | For Information Only
ALTALINK, Lethbridge | 667L (146s Lethbridge MacDonald - 370s North Lethbridge) | 2020-04-27 08:00 | 2020-04-29 15:00 | N | Y | removing 13.8 kv line in close proximity of 667L line | Line | 667L (146s Lethbridge MacDonald - 370s North Lethbridge) | removing 13.8 kv line in close proximity of 667L138kv line | For Information Only, Pre-Condition
ENMAX | 35.1TR (ENMAX 35) | 2020-04-27 08:00 | 2020-04-28 16:00 | N | N | check reversing switch | Transformer | 35.1TR (ENMAX 35) | T-60 Upgrade Phase 2. Check reversing switch. Oil sampling 35.1TR | For Information Only
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) | 2020-04-27 08:00 | 2020-04-27 13:00 | N | N | substation washing | Line, Transformer | 22.81L (ENMAX 22 - ENMAX 39) 22.2TR (ENMAX 22) | Spring Substation Washing. Check reversing switch 22.2(X), 22.2(Y) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 755s 901 (755s Cordel) | 2020-04-27 09:00 | 2020-04-27 12:00 | N | Y | trip and close coil testing | Circuit Breaker | 755s 901 (755s Cordel) | PRC-005 - TRIP & CLOSE COIL TESTING - BREAKER 901-WEST @ 755S RING BUS WILL BE OPENED | 240 kV, Contingency Requires Mitigation
ALTALINK | 37s T5 (37s North Calder) | 2020-04-27 09:30 | 2020-04-30 17:30 | N | N | breaker replacement | Transformer | 37s T5 (37s North Calder) | Replacing 37s49 with a new V/B | For Information Only
ALTALINK | 781L (71s Lamoureux - 172s Sherritt) | 2020-04-27 09:30 | 2020-04-27 17:30 | N | N | line clearance mitigation | Line |  | Structure modification to eliminate line clearance violation in 781L Span 16  17 - This is P5 work as dictated by Asset Management. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 822L (38s East Edmonton - 133s Stelco Edmonton), 133S Stelco Edmonton | 2020-04-27 10:00 | 2020-05-11 15:00 | N | N | replace SCADA system | Line, Station | 822L (38s East Edmonton - 133s Stelco Edmonton) |  | For Information Only
CapitalPower | 615S Halkirk | 2020-04-27 10:30 | 2020-04-27 13:30 | N | N | upgrading door alarm logic | Station |  |  | Affects Visibility, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-04-27 12:00 | 2020-05-01 14:00 | N | Y | structure replacements | Line | 909L (310p Sundance - 665s Dome) | Components/Structure Replacements (Structures #1B - 214). Line clearance mitigation will also be bundled into this outage on Structures #199 & 200 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ATCO | 755s 902 (755s Cordel) | 2020-04-27 12:30 | 2020-04-27 16:00 | N | Y | trip and close coil testing | Circuit Breaker | 755s 902 (755s Cordel) | PRC-005 - TRIP & CLOSE COIL TESTING - BREAKER 902-WEST @ 755S RING BUS WILL BE OPENED | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 38s 761N (38s East Edmonton), 761L (38s East Edmonton - 71s Lamoureux) | 2020-04-27 13:00 | 2020-04-30 13:00 | N | N | breaker maintenance | Circuit Breaker, Line | 761L (38s East Edmonton - 71s Lamoureux) 38s 761N (38s East Edmonton) | Maintenance on 38s761N breaker. replace grading caps for breaker no special requirements here. | Pre-Condition
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22) | 2020-04-27 13:00 | 2020-04-27 18:00 | N | N | substation washing | Line, Transformer | 13.82L (ENMAX 13 - ENMAX 22) 22.1TR (ENMAX 22) | Spring Substation Washing | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2020-04-27 16:34 | 2020-04-30 15:45 | N | Y | forced outage | Line | 13L50 (2029s Heathfield - 2075s Newell) |  | 500 kV
ATCO | 7L760 (767s Oyen - 7L760D2) | 2020-04-27 17:02 | 2020-04-28 11:53 | N | Y | forced outage | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
EPCOR | Victoria V724 (Victoria) | 2020-04-28 07:00 | 2020-04-28 17:00 | N | N | maintenance / doble | Circuit Breaker | Victoria V724 (Victoria) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 33s 5 (33s Spray) | 2020-04-28 07:00 | 2020-04-29 17:30 | N | Y | pole replacement | Switch | 33s 5 (33s Spray) | Pole replacement, changing insulators and reconductor. 138kV breaker maintenance (33s1) | Restricts Generation
ALTALINK | 113L (20s Ghost - 33s Spray), 76L (33s Spray - 115s Mt. Allan), 84L (33s Spray - 35s Rundle) | 2020-04-28 07:00 | 2020-04-28 17:30 | N | Y | 33sSS1/33s5 arcing | Line | 84L (33s Spray - 35s Rundle), 113L (20s Ghost - 33s Spray), 76L (33s Spray - 115s Mt. Allan) |  | Restricts Generation, Affects Cranking Path
ATCO | 7L54 (794s Valleyview - 813s Little Smoky) | 2020-04-28 08:00 | 2020-04-30 17:00 | N | N | cross arm changes | Line | 7L54 (794s Valleyview - 813s Little Smoky) | Cross arm changes | Affects Cranking Path
ATCO | 7L69 (731s Elmworth - 815s Goodfare) | 2020-04-28 08:00 | 2020-04-28 17:00 | N | Y | emergency repair due to 7L03 fire | Line |  | To complete repairs due to 7L03 Fire (Shared structure) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 6.80L (ENMAX 6 - ENMAX 35), 6.4TR (ENMAX 6) | 2020-04-28 08:00 | 2020-04-28 13:00 | N | N | corrective & substation washing & check reversing switch | Line, Transformer | 6.80L (ENMAX 6 - ENMAX 35) 6.4TR (ENMAX 6) |  | Creates Radial Feeds
ALTALINK | 71s 652 (71s Lamoureux) | 2020-04-28 08:00 | 2020-04-29 13:30 | N | N | maintenance on 71s652 breaker | Circuit Breaker | 71s 652 (71s Lamoureux) |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 939s 1214 (939s Livock) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 Testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 939s 1216 (939s Livock) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 939s 1207 (939s Livock) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 939s 1206 (939s Livock) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 951s 1213 (951s Thickwood Hills) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 951s 1206 (951s Thickwood Hills) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 Testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 951s 1205 (951s Thickwood Hills) | 2020-04-28 09:00 | 2020-04-28 17:00 | N | Y | PRC 005 testing requirement | Circuit Breaker |  | PRC 005 Testing requirement | 500 kV, Pre-Condition
ATCO | 755s 904 (755s Cordel) | 2020-04-28 09:00 | 2020-04-28 12:00 | N | Y | trip and close coil testing (PRC-005) | Circuit Breaker | 755s 904 (755s Cordel) | PRC-005 - TRIP & CLOSE COIL TESTING - BREAKER 904-WEST @ 755S RING BUS WILL BE OPENED | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 237s 2152 (237s Foothills) | 2020-04-28 09:30 | 2020-04-28 14:45 | N | Y | emergency repair | Circuit Breaker | 237s 2152 (237s Foothills) | emergency repair: SF6 top up for all 3 phases (need to top up before breaker goes into a lock out due to low gas and fails to operate) | 240 kV, Contingency Requires Mitigation
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock) | 2020-04-28 10:00 | 2020-05-01 15:10 | N | N | address warranty defects along 12L41 | Line |  | Valard is planning to address warranty defects along 12L41 during the upcoming outage scheduled by AltaLink's request to clean up deficiencies at 510S | For Information Only
ATCO | 12L44 (939s Livock - 951s Thickwood Hills) | 2020-04-28 10:00 | 2020-04-28 17:00 | N | Y | remove vibration monitors | Line |  | Remove Vibration monitors, no impact 12L41 will be out of service at this time GOI 2-51278 | 500 kV, Pre-Condition
ALTALINK, ATCO | 510s 2852 (510s Sunnybrook), 510s 2952 (510s Sunnybrook), 12L41 (510s Sunnybrook - 939s Livock) | 2020-04-28 10:00 | 2020-05-01 15:10 | N | Y | cleaning up deficiencies from the project | Circuit Breaker, Line | 12L41 (510s Sunnybrook - 939s Livock) |  | 500 kV, Pre-Condition
ATCO | 755s 905 (755s Cordel) | 2020-04-28 12:30 | 2020-04-28 16:00 | N | Y | trip and close coil testing (PRC-005) | Circuit Breaker | 755s 905 (755s Cordel) | PRC-005 - TRIP & CLOSE COIL TESTING - BREAKER 905-WEST @ 755S RING BUS WILL BE OPENED | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 6.82L (ENMAX 6 - ENMAX 41), 6.1TR (ENMAX 6) | 2020-04-28 13:00 | 2020-04-28 18:00 | N | N | corrective. substation washing & check reversing switch | Line, Transformer | 6.82L (ENMAX 6 - ENMAX 41) 6.1TR (ENMAX 6) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 237s 2252 (237s Foothills) | 2020-04-28 14:46 | 2020-04-28 19:00 | N | Y | emergency repair | Circuit Breaker | 237s 2252 (237s Foothills) | emergency repair: SF6 top up for all 3 phases (need to top up before breaker goes into a lock out due to low gas and fails to operate) | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | Victoria V725 (Victoria) | 2020-04-29 07:00 | 2020-04-29 17:00 | N | N | Maintenance / Doble | Circuit Breaker | Victoria V725 (Victoria) |  | Creates Radial Feeds
ALTALINK | 54s T1 (54s Fort Saskatchewan) | 2020-04-29 08:00 | 2020-05-01 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ENMAX | 2.4TR (ENMAX 2) | 2020-04-29 08:00 | 2020-04-30 16:00 | N | N | maintenance | Transformer |  | T-60 Upgrade Phase 2. Check reversing switch. | For Information Only
ENMAX | ENMAX 35.2TR (ENMAX 35) | 2020-04-29 08:00 | 2020-04-30 16:00 | N | N | T-60 Upgrade Phase 2. Check reversing switch. | Transformer |  | T-60 Upgrade Phase 2. Check reversing switch. | For Information Only
ENMAX | 16.1TR (ENMAX 16) | 2020-04-29 08:00 | 2020-04-30 16:00 | N | N | Tapchanger inspection. Check reversing switch. Oil sampling MT, TC | Transformer | 16.1TR (ENMAX 16) |  | For Information Only
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2020-04-29 08:30 | 2020-04-29 17:30 | N | Y | maintenance | Line | 50L (44s Bearspaw Plant - ENMAX 21) | AltaLink Ref# 269241, maintain 138kV SF6 breaker IR scan and site check | For Information Only
ALTALINK | 528S Blue Trail Wind Farm | 2020-04-29 09:00 | 2020-04-29 13:00 | N | N | DVAR outage | Station |  |  | For Information Only
ATCO | 755s 906 (755s Cordel) | 2020-04-29 09:00 | 2020-04-29 12:00 | N | Y | trip and close coil testing | Circuit Breaker | 755s 906 (755s Cordel) | PRC-005 - TRIP & CLOSE COIL TESTING - BREAKER 906-WEST @ 755S RING BUS WILL BE OPENED | 240 kV, Contingency Requires Mitigation
EPCOR | Victoria V726 (Victoria) | 2020-04-30 07:00 | 2020-04-30 17:00 | N | N | maintenance / doble | Circuit Breaker | Victoria V726 (Victoria) |  | Firm Load Loss, Pre-Condition
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2020-04-30 08:00 | 2020-04-30 18:00 | N | N | urgent line clearance mitigation on str 98, public hazard | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L760 (767s Oyen - 7L760D2) | 2020-04-30 16:06 | 2020-05-07 18:00 | N | Y | forced outage | Line |  |  | Pre-Condition, Firm Load Loss, Creates Radial Feeds
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2020-05-01 | 2020-05-04 11:59 | N | N | blowout violation  line de-energized due to public safety concern | Line | 726L (37s North Calder - 71s Lamoureux) |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 72RV2 (511s Victoria - Rossdale), Victoria V721 (Victoria), Victoria V729 (Victoria) | 2020-05-01 07:00 | 2020-05-01 17:00 | N | N | Doble | Line, Circuit Breaker | 72RV2 (Rossdale - 511s Victoria) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 9 - ENMAX 43), 9.2TR (ENMAX 9), 9.3TR (ENMAX 9) | 2020-05-01 08:00 | 2020-05-01 16:00 | N | N | spring substation washing & check reversing switch 9.2, 9.3 | Line, Transformer | 2.81L (ENMAX 2 - ENMAX 9) 9.83L (ENMAX 9 - ENMAX 43) 9.3TR (ENMAX 9) 9.2TR (ENMAX 9) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR, ALTALINK | 240BA2 (629s Argyll Transfer Station - 814s Bellamy), 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2020-05-02 07:00 | 2020-05-02 17:00 | N | Y | doble | Line | 1056L (89s Ellerslie - 629s Argyll Transfer Station), 240BA2 (629s Argyll Transfer Station - 814s Bellamy) |  | 240 kV, For Information Only
ENMAX | 11.82L (ENMAX 11 - ENMAX 14) | 2020-05-02 08:00 | 2020-05-03 16:00 | N | N | replace rotten pole and SF6 sample 14B138-11.82 | Line | 11.82L (ENMAX 11 - ENMAX 14) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27), 15.62L (ENMAX 15 - ENMAX 16), 16.60L (ENMAX 16 - ENMAX 34), 16.1TR (ENMAX 16) | 2020-05-03 08:00 | 2020-05-03 16:00 | N | N | power factor test HV PT 16sub 69kV PT | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 919L (77s Sagitawah - 310p Sundance) | 2020-05-03 13:00 | 2020-05-04 16:00 | N | N | forced outage | Line |  |  | Affects Cranking Path
EPCOR | 657s SU2403 (657s Summerside) | 2020-05-04 03:44 | 2020-05-26 15:19 | N | Y | forced outage | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | 511s Victoria T1 (511s Victoria) | 2020-05-04 07:00 | 2020-05-08 17:00 | N | N | doble | Transformer | 511s Victoria T1 (511s Victoria) |  | Pre-Condition
EPCOR | 816s P2405 (816s Petrolia) | 2020-05-04 07:00 | 2020-05-08 17:00 | N | Y | maintenance / doble | Circuit Breaker | 816s P2405 (816s Petrolia) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2020-05-04 07:00 | 2020-05-05 17:00 | N | Y | doble | Line | 920L (37s North Calder - 557s Castle Downs) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
EPCOR | 330p 806 (330p Genesee) | 2020-05-04 07:00 | 2020-05-07 16:00 | N | N | maintenance /doble | Circuit Breaker | 330p 806 (330p Genesee) |  | For Information Only
EPCOR | 1164L (816s Petrolia - EPCOR Riverview) | 2020-05-04 07:00 | 2020-05-15 17:00 | N | Y | breaker repairs | Line | 1164L (816s Petrolia - EPCOR Riverview) | 1164L bay outage required for vendor breaker repairs at Riverview S/S | 240 kV, Creates Radial Feeds, Firm Load Loss
ATCO | 2075s ACF12 (2075s Newell) | 2020-05-04 07:00 | 2020-05-08 17:30 | N | Y | PRC-005 trip coil testing | Shunts | 2075s ACF12 (2075s Newell) | PRC-005 Trip Coil Testing, No constraints,Redundant filter bank ACF22 will be in service. | 240 kV, Pre-Condition
EPCOR | 816s T2 (816s Petrolia) | 2020-05-04 08:00 | 2020-05-15 17:00 | N | Y | replace secondary cables | Transformer | 816s T2 (816s Petrolia) |  | 240 kV
ATCO | 749s 702T (749s Flyingshot Lake) | 2020-05-04 08:00 | 2020-05-04 13:00 | N | N | open jumper J1 on 25 kV | Transformer |  | GOI on 749S 702T to open jumper J1 J1 will be in between 702T X and the 702T LAs so that when the T & O on 502TD we will not be paralleling and breaking parallel with 701T | For Information Only
ENMAX | 43.1TR (ENMAX 43) | 2020-05-04 08:00 | 2020-05-07 16:00 | N | N | tapchanger inspection X-TC, Y-TC. check reversing switch(X), (Y). Oil sampling MT, X-TC, Y-TC. | Transformer | 43.1TR (ENMAX 43) |  | For Information Only
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2020-05-04 08:00 | 2020-05-07 16:00 | N | N | breaker maintenance | Line | 15.62L (ENMAX 15 - ENMAX 16) | HV Breaker Maintenance 15B69-15.62. 16B69-15.62. | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2020-05-04 08:00 | 2020-05-10 16:00 | N | N | water main installation on 9A st by PCL | Line | 3.82L (ENMAX 3 - ENMAX 8) | Water main installation on 9A st by PCL. DGA & sheath testing. | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.2TR (ENMAX 9) | 2020-05-04 08:00 | 2020-05-07 16:00 | N | N | power factor test transformer, secondary cable tests, maintenance, | Transformer | 9.2TR (ENMAX 9) |  | For Information Only
Syncrude | Aurora 13 (Aurora), Aurora 14 (Aurora), Aurora T1 (Aurora) | 2020-05-04 08:00 | 2020-05-08 15:00 | N | N | G01 substation 72KV zone 7 outage | Circuit Breaker, Transformer | Aurora 13 (Aurora) Aurora 14 (Aurora) | G01 Substation 72KV Zone 7 Outage - Aurora Following Circuit Breakers will be operated: 13 & 14 Following MOD will be operated: 17 Following switches will be operated: 13A, 13B, 14A & 14B | For Information Only
ENMAX | 54.1TR (ENMAX 54) | 2020-05-04 08:00 | 2020-05-05 16:00 | N | N | maintenance | Transformer | 54.1TR (ENMAX 54) | T-60 Upgrade Phase 2. Oil sampling MT, TC. Check reversing switch. Filmax maint. | For Information Only
ENMAX | 22.2TR (ENMAX 22) | 2020-05-04 08:00 | 2020-05-14 16:00 | N | N | MV bushing replacement and checks | Transformer | 22.2TR (ENMAX 22) |  | For Information Only
ATCO | 7L54 (794s Valleyview - 813s Little Smoky) | 2020-05-04 09:00 | 2020-05-07 17:00 | N | N | cross arm changes | Line | 7L54 (794s Valleyview - 813s Little Smoky) | Cross arm changes | Pre-Condition,Affects Cranking Path
ALTALINK | 189L (373s Madden - 418L), 373S Madden | 2020-05-04 09:15 | 2020-05-08 17:45 | N | N | line clearance mitigation | Line, Station | 189L (373s Madden - 418L) | Urgent Line Clearance Mitigation 189L Structures Range 74-79 | For Information Only
ALTALINK | 245s 56E (245s Seebe), 56L (20s Ghost - 245s Seebe) | 2020-05-04 09:15 | 2020-05-07 16:00 | N | N | 138kV CT replacement | Circuit Breaker, Line | 56L (20s Ghost - 245s Seebe) | 138kV CT Replacement | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 754L (245s Seebe - 742L), 245s 754W (245s Seebe) | 2020-05-04 09:15 | 2020-05-07 16:00 | N | N | 138kV CT replacement | Line, Circuit Breaker | 754L (245s Seebe - 754L65A) | 138kV CT Replacement | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2020-05-04 09:30 | 2020-05-15 17:30 | N | N | line clearance mitigation work | Line | 737L (38s East Edmonton - 95s Imperial Oil Edmonton) | Ground line for customer. Line Clearance Mitigation work. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 325s 1552 (325s Leduc), 325s C1 (325s Leduc) | 2020-05-04 09:30 | 2020-05-04 17:30 | N | N | breaker maintenance | Circuit Breaker, Shunts | 325s 1552 (325s Leduc) | Breaker maintenance | For Information Only, Pre-Condition
ATCO | 7L12 (834s Wesley Creek - 7L12D2) | 2020-05-04 10:00 | 2020-05-13 16:00 | N | N | walk up inspection, climbing patrol and change arms and insulators | Line | 7L12 (834s Wesley Creek - 869s Seal Lake) | for Walk up Inspection, Climbing patrol and Change arms and insulators | Creates Radial Feeds, Firm Load Loss
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2020-05-04 12:00 | 2020-06-18 18:00 | N | N | component replacement and line clearance mitigation | Line | 726L (37s North Calder - 71s Lamoureux) | Component replacement and line clearance mitigation between Structures #1 - 227 | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 65s T1 (65s High River), 13L/158L (65s High River - 392s Black Diamond), 392s T2 (392s Black Diamond) | 2020-05-04 13:15 | 2020-05-14 13:45 | N | N | 138 kV component replacement | Transformer, Line | 13L (65s High River - 392s Black Diamond) 65s T1 (65s High River) 392s T2 (392s Black Diamond) | 138 kV component replacement at 65s and 392s. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 83s C1 (83s Taber) | 2020-05-04 14:00 | 2020-05-08 18:00 | N | N | cap bank protection upgrade | Shunts | 83s C1 (83s Taber) | 83s34 advice for cap bank protection upgrade. | For Information Only
ALTALINK | 54s 45 (54s Fort Saskatchewan), 54s C1 (54s Fort Saskatchewan) | 2020-05-05 08:30 | 2020-05-05 17:00 | N | N | breaker maintenance | Circuit Breaker, Shunts | 54s 45 (54s Fort Saskatchewan) |  | Pre-Condition
ATCO | 700s 703T (700s Bonnyville) | 2020-05-05 09:00 | 2020-05-07 16:30 | N | N | leak severity inspection / repair | Transformer | 700s 703T (700s Bonnyville) | 700S 703T Leak Severity Leak Severity inspection / repair on 703T @ 700s Bonnyville | For Information Only
ALTALINK | 38s 3152 (38s East Edmonton), 38s C2 (38s East Edmonton) | 2020-05-05 09:00 | 2020-05-06 16:30 | N | N | breaker maintenance | Circuit Breaker, Shunts | 38s 3152 (38s East Edmonton) 38s C2 (38s East Edmonton) | Maintenance on 38s3152 breaker & Low Gas on center phase | Pre-Condition
EPCOR, ALTALINK | 557s 2404 (557s Castle Downs), 557s 2405 (557s Castle Downs), 920L (71s Lamoureux - 557s Castle Downs) | 2020-05-06 07:00 | 2020-05-07 17:00 | N | Y | doble | Circuit Breaker, Line | 920L (71s Lamoureux - 557s Castle Downs) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO | 749s 702T (749s Flyingshot Lake) | 2020-05-06 08:00 | 2020-05-06 12:00 | N | N | close jumper J1 on 25 kV | Transformer |  | GOI on 749S 702T to Close jumper J1 between 702T X and the 702T LAs | For Information Only
ALTALINK | 235s 744W (235s Entwistle), 744L (235s Entwistle - 744L88C) | 2020-05-06 08:30 | 2020-05-06 17:30 | N | N | 235s744W breaker maintenance | Circuit Breaker, Line | 744L (235s Entwistle - 744L88C) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 20.1TR (ENMAX 20) | 2020-05-07 08:00 | 2020-05-07 16:00 | N | N | replace fan | Transformer |  |  | For Information Only
ALTALINK | 38s 3052 ( 38s East Edmonton), 38s C1 (38s East Edmonton) | 2020-05-07 08:30 | 2020-05-07 17:00 | N | N | maintenance | Circuit Breaker, Shunts | 38s 3052 ( 38s East Edmonton) 38s C1 (38s East Edmonton) |  | For Information Only, Pre-Condition
ALTALINK | 21s T1 (21s Marion) | 2020-05-07 10:00 | 2020-05-10 10:30 | N | N | oil replacement | Transformer | 21s T1 (21s Marion)
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), 15.2TR (ENMAX 15) | 2020-05-08 08:00 | 2020-05-08 16:00 | N | N | power factor test HV PT 15sub 69kV PT | Line, Transformer | 15.62L (ENMAX 15 - ENMAX 16), 15.2TR (ENMAX 15)
ALTALINK | 719L (378s Shell Caroline - 575s Sundre) | 2020-05-08 17:00 | 2020-05-12 18:00 | N | Y | urgent - replace 719L structure 163 and install mid-span structure between Str 169 & 170 to mitigate line clearance violations - this is P5 work as dictated by Asset Management. | Line | 719L (575s Sundre - 378s Shell Caroline) |  | Creates Radial Feeds, Pre-Condition, Restricts Generation
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 9.1TR (ENMAX 9) | 2020-05-09 08:00 | 2020-05-09 16:00 | N | N | spring substation washing | Line, Transformer | 9.80L (ENMAX 9 - ENMAX 31) 9.1TR (ENMAX 9) | Spring Substation Washing. Check reversing switch. | For Information Only, Pre-Condition
ENMAX | 26.81L (ENMAX 32 - ENMAX 26), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2020-05-10 08:00 | 2020-05-10 18:00 | N | N | spring substation washing | Line, Transformer | 26.81L (ENMAX 32 - ENMAX 26) 32.83L (ENMAX 32 - ENMAX 40) 32.1TR (ENMAX 32) 32.2TR (ENMAX 32) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 814s T1 (814s Bellamy), Rossdale BR721 (Rossdale) | 2020-05-11 07:00 | 2020-05-11 17:00 | N | Y | doble | Transformer, Circuit Breaker | 814s T1 (814s Bellamy) |  | 240 kV, Over/Under Voltage, Pre-Condition
EPCOR | 511s Victoria T3 (511s Victoria) | 2020-05-11 07:00 | 2020-05-15 17:00 | N | N | doble | Transformer | 511s Victoria T3 (511s Victoria)
EPCOR | 816s P2406 (816s Petrolia) | 2020-05-11 07:00 | 2020-05-15 17:00 | N | Y | maintenance / doble | Circuit Breaker | 816s P2406 (816s Petrolia) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 162.1TR (ENMAX 162s Beddington) | 2020-05-11 08:00 | 2020-05-22 16:00 | N | Y | protection upgrade | Transformer | 162.1TR (ENMAX 162s Beddington) | B protection upgrade. Commission new circuits. HV SW maint SW131, SW141, SW81, SW96, MD138-162.1TR, MD240-162.1TR. Oil sampling 162.1 MT, TC, Bushing. Replace sw mech SW131, SW141. Check reversing sw. | 240 kV, Contingency Requires Mitigation, Pre-Condition
Syncrude | Aurora UT1 (Aurora) | 2020-05-11 08:00 | 2020-05-11 20:00 | N | N | relay co-ordination | Transformer |  |  | For Information Only
ENMAX | 27.1TR (ENMAX 27) | 2020-05-11 08:00 | 2020-05-12 16:00 | N | N | tapchanger inspection, gas relay testing and transformer maintenance | Transformer | 27.1TR (ENMAX 27) |  | For Information Only
ALTALINK | 214s T1 (214s Innisfail) | 2020-05-11 08:00 | 2020-05-14 13:00 | N | N | replace exiting NGR | Transformer | 214s T1 (214s Innisfail) |  | For Information Only
ENMAX | 24.82L (ENMAX 24 - ENMAX 65) | 2020-05-11 08:00 | 2020-05-20 16:00 | N | N | transmission line pole relocation (3 structures) | Line | 24.82L (ENMAX 24 - ENMAX 65) | Power factor test HV LA 65MD138-24.82. 24B138-24.82 HV CT Transmission Line Pole Relocation (3 structures). Power factor test 24B138-24.82 CT. Phasing required on return. | For Information Only
ENMAX | 24.82L (ENMAX 24 - ENMAX 65), ENMAX 65 B138-D82 (ENMAX 65), ENMAX 65 B138-D81 (ENMAX 65) | 2020-05-11 08:00 | 2020-05-11 16:00 | N | N | power factor test and SF6 sample | Line, Circuit Breaker |  | power factor test HV LA 65MD138-24.82. SF6 Sample 65B138-D82, 65B138-D81 | For Information Only
SUNCOR | 29EDD-56, 29PL9-14 (29EDD-34 - 29EDD-56) | 2020-05-11 08:00 | 2020-05-19 18:00 | N | Y | perform 5/10yr PM | Station, Line | 29EDD-56 | Line outage to perform 5/10yr PM 29PL9-14 buss 29PP-41C and transformer 29PT-191 : 29EDD56;29PT-191 SYSTEM;PM 5Y/10Y, Repair OHSW bonds to towers PL9-14/15, 29PL9-14, Reconnect Suspension Clamp, 29PL9-14, Repair OH Shield Bonds, 29EDD56;652-4170 MAINT & TEST;PM 10y, 29EDD-56 29PT-191 Oil Leak Repairs | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2020-05-11 09:00 | 2020-05-15 16:00 | N | Y | cross-arm change out | Line | 7L32 (813s Little Smoky - 862s South Bezanson) | X-arm change out | Over/Under Voltage, Overload, Pre-Condition,Affects Cranking Path
ALTALINK | 245s 58X (245s Seebe), 58L (32s Barrier - 245s Seebe) | 2020-05-11 09:15 | 2020-05-15 10:45 | N | N | CT replacement | Circuit Breaker, Line | 58L (32s Barrier - 245s Seebe) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 245s 777X (245s Seebe), 777L (48s Pocaterra - 245s Seebe) | 2020-05-11 09:15 | 2020-05-15 10:45 | N | Y | clearance mitigation and CT replacement | Circuit Breaker, Line | 777L (48s Pocaterra - 245s Seebe) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 535s 6052 (535s Joffre) | 2020-05-11 10:30 | 2020-05-15 17:30 | N | N | 138kV breaker replacement | Circuit Breaker | 535s 6052 (535s Joffre) |  | For Information Only
ALTALINK | 429s T1 (429s Nelson Lake) | 2020-05-11 11:00 | 2020-05-14 17:30 | N | N | replace bushings and lightning arresters on T1 | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2020-05-11 12:00 | 2020-05-15 14:00 | N | Y | components/structure replacements | Line | 909L (89s Ellerslie - 665s Dome) | Components/Structure Replacements (Structures #218 - 228) | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ATCO | 7L121 (833s Mariana - 860s Crow) | 2020-05-11 12:00 | 2020-05-11 16:00 | N | N | 7L121 required out of service for a high load move Brief outages required at 860S Crow & 833S Mariana to isolate required section of line | Line | 7L121 (833s Mariana - 860s Crow) | 7L121 required out of service for a high load move Brief outages required at 860S Crow & 833S Mariana to isolate required section of line | Creates Radial Feeds, Firm Load Loss
ALTALINK | 58L (32s Barrier - 245s Seebe) | 2020-05-12 07:15 | 2020-05-13 17:45 | N | N | urgent clearance | Line | 58L (32s Barrier - 245s Seebe) | P5 Urgent Clearance on 58L | For Information Only, Affects Cranking Path
EPCOR | Rossdale BR722 (Rossdale), 814s T2 (814s Bellamy) | 2020-05-12 08:00 | 2020-05-12 17:00 | N | Y | breaker doble testing | Circuit Breaker, Transformer | 814s T2 (814s Bellamy) | BR722 Doble | 240 kV, Over/Under Voltage, Pre-Condition
Syncrude | Aurora 21 (Aurora), Aurora 22 (Aurora), Aurora 23 (Aurora), Aurora UT2 (Aurora), TL-2 (Aurora - Aurora) | 2020-05-12 08:00 | 2020-05-20 20:00 | N | N | G01 substation 72KV zone 4 outage - Aurora | Circuit Breaker, Transformer, Line | Aurora 21 (Aurora) Aurora 22 (Aurora) Aurora 23 (Aurora) | G01 Substation 72KV Zone 4 Outage - Aurora; Following Circuit Breakers will be operated: 21, 22 & 23; Following MOD will be operated: 25 & 26; Following switches will be operated: 21A, 21B, 22A, 22B, 23A, & 23B; Transformer T6 (Aurora Go1 Substation) will be offline for the duration of this outage | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2020-05-12 08:00 | 2020-05-12 12:00 | N | Y | maintenance | Switch |  | Brushgear | For Information Only, Restricts Generation
ENMAX | ENMAX 65 B138-D85 (ENMAX 65) | 2020-05-12 08:00 | 2020-05-12 12:00 | N | N | SF6 sample | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 308s T1 (308s Albchem Beaverhill Creek) | 2020-05-12 08:30 | 2020-05-14 17:30 | N | N | transformer LV bushing replacement | Transformer | 308s T1 (308s Albchem Beaverhill Creek) |  | For Information Only
ATCO | 7L129 (526s Buffalo Creek - 918s Bauer) | 2020-05-12 09:00 | 2020-05-12 15:00 | N | Y | correct leaning pole | Line | 7L129 (526s Buffalo Creek - 918s Bauer) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek) | 2020-05-12 09:30 | 2020-05-12 11:00 | N | N | PRC testing of breaker trip and close coils | Line | 7L43 (739s Edith Lake - 809s Louise Creek) | PRC Testing of 701 BKR trip and close Coils 7L43 required open ended for 2 hours | For Information Only
ALTALINK | 32s 22 (32s Barrier), 32s T1 (32s Barrier) | 2020-05-12 11:45 | 2020-05-12 17:30 | N | Y | trip test PRC 5 maintain 138kV SF6 breaker | Circuit Breaker, Transformer | 32s 22 (32s Barrier) 32s T1 (32s Barrier) |  | Restricts Generation
ENMAX | ENMAX 65 B138-D84 (ENMAX 65) | 2020-05-12 12:01 | 2020-05-12 16:00 | N | N | SF6 sample | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
CapitalPower | 615S Halkirk | 2020-05-12 13:00 | 2020-05-12 14:00 | N | N | RTAC software upgrade | Station |  |  | Affects Visibility
ALTALINK | 62s 12 (62s Brazeau) | 2020-05-12 13:00 | 2020-05-12 17:00 | N | Y | maintenance | Switch |  | Brushgear | Restricts Generation
EPCOR | 987s T4 (987s Clover Bar) | 2020-05-13 07:00 | 2020-05-13 17:00 | N | Y | tap changer maitenance | Transformer | 987s T4 (987s Clover Bar) |  | 240 kV, Firm Load Loss, Pre-Condition
ALTALINK | 719L (256s Harmattan - 719CL) | 2020-05-13 07:00 | 2020-05-14 18:00 | N | Y | P5 work to replace structure 74 to mitigate line clearance violations | Line | 719L (256s Harmattan - 719L134) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2020-05-13 08:00 | 2020-05-13 16:00 | N | N | SF6 sample 20B138-1.81 | Line | 1.81L (ENMAX 1 - ENMAX 20) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome) | 2020-05-13 08:00 | 2020-05-13 17:00 | N | Y | 72DS26 and T3 - new equipment installation | Line | Extension in the isolation zone for the on going 909L outage to install new equipment for D2404 and transformer T3. | DDS2 DDS13 DVT13 | 240 kV, For Information Only,Affects Cranking Path
ENMAX | 33.1TR (ENMAX 33) | 2020-05-13 08:00 | 2020-05-14 16:00 | N | N | investigate cracked CT | Transformer |  |  | For Information Only
ENMAX | 14.1TR (ENMAX 14) | 2020-05-13 08:00 | 2020-05-14 16:00 | N | N | tapchanger inspection, oil sampling MT, TC | Transformer | 14.1TR (ENMAX 14) | Tapchanger inspection. Oil sampling MT, TC | For Information Only
VISIONREQ | 354s DVAR1 (354s Summerview), 354s DVAR2 (354s Summerview) | 2020-05-13 09:00 | 2020-05-13 11:00 | N | N | partial outage | Shunts |  |  | For Information Only
ATCO | 7L172 (739s Edith Lake - 743s Sarah Lake) | 2020-05-13 11:00 | 2020-05-13 13:00 | N | N | PRC testing of 702 breaker trip and close coils | Line | 7L172 (739s Edith Lake - 743s Sarah Lake) | PRC Testing of 702 BKR trip and close Coils Open ended 7L172 for the duration | For Information Only, Pre-Condition
ALTALINK | 418s DVAR (418s Ardenville) | 2020-05-13 13:00 | 2020-05-13 14:00 | N | N | partial outage | Shunts |  |  | For Information Only
ALTALINK, EPCOR | 921L (71s Lamoureux - 987s Clover Bar) | 2020-05-14 07:00 | 2020-06-30 17:00 | N | Y | Doble | Line | 921L (71s Lamoureux - 987s Clover Bar) |  | 240 kV, Affects Cranking Path
ENMAX | 3.4TR (ENMAX 3) | 2020-05-14 08:00 | 2020-05-14 16:00 | N | N | investigate cracked CT | Transformer |  |  | For Information Only
ENMAX | ENMAX 26 B138-26BT3 (ENMAX 26) | 2020-05-14 08:00 | 2020-05-14 12:00 | N | N | SF6 sample | Circuit Breaker | ENMAX 26 B138-26BT3 (ENMAX 26) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 857S Kakwaridge | 2020-05-14 10:00 | 2020-05-14 16:00 | N | N | testing PT | Station |  | Testing the PT @857S Kakwa Ridge and replacing the Fuse | For Information Only
ATCO | 7L80 (733s Simonette - 740s H.R.Milner) | 2020-05-14 10:00 | 2020-05-14 16:00 | N | Y | maintenance | Line |  | Test PT and change blown fuse at 857S Kakwa, 7L80D2 switch at 857S is faulty and cannot be used for isolation | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 26.81L (ENMAX 32 - ENMAX 26) | 2020-05-14 12:00 | 2020-05-14 16:00 | N | N | maintenance | Line | 26.81L (ENMAX 32 - ENMAX 26) | SF6 sample 26B138-26.81 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | Strathcona T3 (Strathcona) | 2020-05-15 07:00 | 2020-05-19 17:00 | N | N | decom of the transformer protection | Transformer | Strathcona T3 (Strathcona) |  | Pre-Condition
EPCOR | T2 (Namao) | 2020-05-15 07:00 | 2020-09-21 17:00 | N | N | transformer replacement | Transformer | T2 (Namao) |  | For Information Only
EPCOR | Namao N723 (Namao), Namao T2 (Namao) | 2020-05-15 07:00 | 2020-05-19 17:00 | N | N | expanded zone outage for protection decom | Circuit Breaker, Transformer | Namao T2 (Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Strathcona) | 2020-05-15 07:00 | 2020-10-21 17:00 | N | N | transformer replacement | Transformer | T3 (Strathcona) |  | For Information Only
EPCOR | 803s T3 (803s Lambton), 72LS24 (803s Lambton - Strathcona), 72LH8 (803s Lambton - Hardisty) | 2020-05-15 07:00 | 2020-05-18 17:00 | N | N | metering cutover | Transformer, Line | 803s T3 (803s Lambton) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.80L (ENMAX 2 - ENMAX 23) | 2020-05-15 08:00 | 2020-05-15 16:00 | N | N | SF6 sample 23B138-2.80 | Line | 2.80L (ENMAX 2 - ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 151s T1 (151s Strathmore) | 2020-05-15 08:00 | 2020-05-29 18:00 | N | N | emergency transformer replacement | Transformer
SUNCOR | 29EDD-71 752-4651 (29EDD-71), 29EDD-71 752-4652 (29EDD-71) | 2020-05-16 08:00 | 2020-05-22 18:00 | N | Y | repair of 29PS-430 control circuit failure | Circuit Breaker |  | repair of 29PS-430 control circuit failure. | For Information Only, Restricts Generation
ENMAX | 37.81L (ENMAX 37 - ENMAX 38), 37.1TR (ENMAX 37) | 2020-05-16 08:00 | 2020-05-16 18:00 | N | N | substation washing | Line, Transformer | 37.81L (ENMAX 37 - ENMAX 38) 37.1TR (ENMAX 37) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | ENMAX 5 5B138-5BT12 (ENMAX 5) | 2020-05-17 08:00 | 2020-05-17 16:00 | N | N | breaker maintenance | Circuit Breaker | ENMAX 5 5B138-5BT12 (ENMAX 5) | HV Breaker Maintenance 5B138-5BT12. SF6 sample. | For Information Only, Pre-Condition
ENMAX | 28.2TR (ENMAX 28) | 2020-05-18 08:00 | 2020-06-04 16:00 | N | N | arc flash mitigation project: protection outage and MV cable swap, phasing required on return | Transformer |  | Arc Flash Mitigation Project: protection outage and MV cable swap. phasing required on return. | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2020-05-18 09:00 | 2020-05-22 16:00 | N | Y | cross-arm change out | Line | 7L32 (813s Little Smoky - 862s South Bezanson) | X-arm change out | Over/Under Voltage, Overload, Pre-Condition,Affects Cranking Path
ALTALINK | 165s T1 (165s T.M.P.L.Gainford) | 2020-05-19 06:00 | 2020-05-19 18:00 | N | N | removing old 4160V U/G feeder cables, 165s13 & 165s12 permanently | Transformer | 165s T1 (165s T.M.P.L.Gainford) |  | For Information Only
EPCOR | RW 2405 (EPCOR Riverview) | 2020-05-19 07:00 | 2020-05-29 17:00 | N | Y | breaker repair for vendor deficiency | Circuit Breaker | RW 2405 (EPCOR Riverview) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s ACF13 (2075s Newell) | 2020-05-19 07:00 | 2020-05-22 17:30 | N | Y | PRC-005 trip coil testing | Shunts | 2075s ACF13 (2075s Newell) | PRC-005 Trip Coil Testing, No constraints, Redundant filter bay ACF23 will be in service. | 240 kV, For Information Only
EPCOR | 803s T3 (803s Lambton), 72LH8 (803s Lambton - Hardisty), 72LS24 (803s Lambton - Strathcona) | 2020-05-19 07:00 | 2020-05-24 17:00 | N | N | doble testing, disconnect repair and T.C./breaker maintenance | Transformer, Line | 72LH8 (Hardisty - 803s Lambton), 72LS24 (803s Lambton - Strathcona), 803s T3 (803s Lambton) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 835L (384s Keystone - 835AL) | 2020-05-19 07:30 | 2020-05-19 18:00 | N | N | switch repair, install mid-span structure | Line | 835L (384s Keystone - 835AL) | Repair 384s13. Install mid-span structure between STR 156 & 157 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21), ENMAX 21 60s50 (ENMAX 21) | 2020-05-19 08:00 | 2020-05-23 18:00 | N | Y | Calgary Ring Road 50L line clearance for pile foundations for new Str 133 and 134 steel poles | Line, Circuit Breaker | 50L (44s Bearspaw Plant - ENMAX 21) |  | For Information Only, Pre-Condition
ENMAX | 23.4TR (ENMAX 23) | 2020-05-19 08:00 | 2020-05-21 16:00 | N | N | power factor test transformer transformer maintenance | Transformer |  |  | For Information Only
ENMAX | 40.2TR (ENMAX 40) | 2020-05-19 08:00 | 2020-05-20 16:00 | N | N | tapchanger inspection oil sampling MT, TC. filmax maintenance | Transformer |  |  | For Information Only
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2020-05-19 08:00 | 2020-05-19 16:00 | N | Y | HV breaker maintenance 23B138-23.80 | Line | 23.80L (74s Janet - ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CMH | MH-65L (MH69s7 - Cancarb) | 2020-05-19 08:00 | 2020-05-21 21:00 | N | Y | PRC-005 compliance testing | Line |  | facilitate the PRC-005 compliance testing of the cancarb facility by the operator of said facility | For Information Only, Restricts Generation
Syncrude | RL2 (848s Ruth Lake - D05 Syncrude), D05 512 (D05 Syncrude), D05 513 (D05 Syncrude) | 2020-05-19 08:00 | 2020-05-21 20:00 | N | Y | maintenance | Line, Circuit Breaker | RL2 (848s Ruth Lake - D05 Syncrude) | Significant Outage - RL-2 Transmission Line 260KV. | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
SUNCOR | 29PT-233 (29EDD-71) | 2020-05-19 08:00 | 2020-05-20 18:00 | N | N | 29PT-233 oil leak repairs | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 38s 738W (38s East Edmonton), 738L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2020-05-19 08:15 | 2020-05-25 16:45 | N | N | breaker replacement | Circuit Breaker, Line | 738L (38s East Edmonton - 95s Imperial Oil Edmonton) 38s 738W (38s East Edmonton) | 138kV breaker replacement (IOL Co-Gen project) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 95s T1 (95s Imperal Oil Edmonton) | 2020-05-19 08:15 | 2020-05-25 16:45 | N | N | facilitate IOL wiring in their switchgear | Transformer | 95s T1 (95s Imperal Oil Edmonton) |  | For Information Only
ALTALINK | 341s T1 (341s Sand Hills Sub) | 2020-05-19 08:30 | 2020-05-19 19:00 | N | N | fix oil leak | Transformer
ALTALINK | 610L (83s Taber - 336s Fincastle) | 2020-05-19 09:00 | 2020-05-22 08:00 | N | Y | P1902, install temp bypass | Line | P1902 | Fincastle Fortis Capacity Increase Project: Installation of Temp bypass and anti-Islanding scheme. Closing of open point K. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 38.1TR (ENMAX 38) | 2020-05-19 09:00 | 2020-05-27 16:00 | N | N | secondary cable replacement phasing required across MD on return | Transformer | 38.1TR (ENMAX 38) |  | For Information Only
ALTALINK | 838L (14s Devon - 325s Leduc), 739L (14s Devon - 305s Acheson), 14s T3 (14s Devon) | 2020-05-19 09:15 | 2020-05-21 17:45 | N | N | replace PT | Line, Transformer | 14s Devon 138kV South Bus 14s T3 (14s Devon) | Replace 14s33 PTs. T3 Maintenance. Replace pole on 14s739N. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 245s 10 (245s Seebe) | 2020-05-19 09:15 | 2020-05-22 14:45 | N | N | 138kV CT Replacement | Circuit Breaker | 245s 10 (245s Seebe) |  | For Information Only, Pre-Condition
ALTALINK | 359s T1 (359s Esso West Pembina) | 2020-05-19 09:30 | 2020-05-21 16:30 | N | N | install new CTs load side of T1, commission tripping and status to new protection relays from 359s13 | Transformer | 359s T1 (359s Esso West Pembina) |  | For Information Only
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-05-19 12:00 | 2020-05-22 14:00 | N | Y | components/structure replacements (structures #1B - 214) | Line | 909L (310p Sundance - 665s Dome) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Affects Cranking Path
ALTALINK | 297s T2 (297s Rimbey) | 2020-05-19 12:00 | 2020-05-20 17:30 | N | N | doble, maintenance | Transformer |  |  | For Information Only
ALTALINK | 320p 252 (320p Keephills) | 2020-05-19 13:00 | 2020-05-20 18:00 | N | Y | breaker maintenance | Circuit Breaker | 320p 252 (320p Keephills) | 240kV Breaker Maintenance on 320p252, 1st trip, 1st close, 2nd trip | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
AESO-SC | OATI | 2020-05-19 18:00 | 2020-05-19 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ALTALINK | 753L (65s High River - 253s Blackie) | 2020-05-20 07:15 | 2020-05-26 17:45 | N | N | line clearance mitigation (str 157-252) | Line | 753L (65s High River - 253s Blackie) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
TRANSALTA, ALTALINK | 239s Castle River RTU/SCADA, 240s McBride Lake RTU/SCADA, 322s Cowley Ridge RTU/SCADA | 2020-05-20 08:00 | 2020-05-20 12:00 | N | N | substation SCADA alarming upgrades and testing | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 511s SVC Plus (511s Crossings) | 2020-05-20 09:00 | 2020-05-20 13:00 | N | Y | urgent repair to address level sensor analog circuit wiring changes | Shunts | 511s SVC Plus (511s Crossings) |  | 240 kV, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2020-05-20 09:30 | 2020-05-20 17:00 | N | Y | structure modifications | Line | 202L (61s Lodgepole - 62s Brazeau) | : Includes adding Structure 8A, and removing OHSW between existing Str 8 and new str 8A on 202L and the stringing of 995L between new structures 995L4E and 995L4F. Scheduled: Shannon Bouchard Issue To: Carson Webber Contact #: 778.214.6493 | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 207s 890 (207s Pinedale), 890L (58s Edson - 207s Pinedale) | 2020-05-20 10:30 | 2020-05-21 15:00 | N | N | PRC5 breaker maintenance and replace tank heaters | Circuit Breaker, Line | 890L (58s Edson - 207s Pinedale) 207s 890 (207s Pinedale) | 207s890 PRC5 Breaker maintenance, and Replace tank heaters 1st Trip, 1st Close, 2nd Trip, | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 185L (379s Shell Canada Waterton - 396s Pincher Creek) | 2020-05-21 07:30 | 2020-05-21 17:30 | N | N | line clearance mitigation project, install conductor dampers at structure 30 & 31 | Line | 185L (379s Shell Canada Waterton - 396s Pincher Creek) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAXGPI | 134s T1 (134s Taber Wind Farm), 134s T2 (134s Taber Wind Farm) | 2020-05-21 08:00 | 2020-05-22 18:00 | N | Y | temporary bypass arrangement AltaLink proposes during the Fincastle upgrade project construction (P1902) | Transformer |  |  | Restricts Generation
ALTAGAS | HMT1 AltaGas Harmattan | 2020-05-21 10:15 | 2020-05-21 17:45 | N | N | 717L outage | Unit
ALTALINK | 17s50 (17s Benalto), 717L (17s Benalto - 262s Rocky Mountain House) | 2020-05-21 10:15 | 2020-05-21 17:45 | N | Y | repair broken conductor | Switch, Line | 717L (17s Benalto - 262s Rocky Mountain House) |  | Contingency Requires Mitigation, Pre-Condition, Restricts Generation
ALTALINK | 267s Killarney Lake 138kV bus, 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2020-05-21 15:23 | 2020-06-17 15:30 | N | N | forced outage | Bus, Shunts |  |  | Pre-Condition
ALTALINK | 612L (336s Fincastle - 368s Burdett) | 2020-05-22 08:00 | 2020-05-22 12:00 | N | Y | capacity increase project | Line | P1902, 612L (336s Fincastle - 368s Burdett) | Fincastle Fortis Capacity Increase Project: Connect mobile high side to 612L. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-05-22 08:00 | 2020-05-28 18:00 | N | N | 29PL6-36 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ALTALINK | 336s 607 (336s Fincastle), 336s 610 (336s Fincastle) | 2020-05-22 16:00 | 2020-06-01 13:00 | N | Y | 610L/607L bypassed at 336s | Circuit Breaker | 607L (336s Fincastle Sub - 607L108) 336s 607 (336s Fincastle) | DG at 368s Burdett need to be offline during the outage (AltaLink procedure). | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 15.62L (ENMAX 15 - ENMAX 16), 16.61L (ENMAX 16 - ENMAX 27), 16.1TR (ENMAX 16) | 2020-05-23 08:00 | 2020-05-23 12:00 | N | N | Substation washing & check reversing switch | Line, Transformer | 15.62L (ENMAX 15 - ENMAX 16) 16.61L (ENMAX 16 - ENMAX 27) 16.1TR (ENMAX 16) |  | Creates Radial Feeds
ALTALINK | 359s T2 (359s Esso West Pembina) | 2020-05-23 09:30 | 2020-05-25 16:30 | N | N | commission tripping and status to new protection relays from 359s14 | Transformer | 359s T2 (359s Esso West Pembina)
ENMAX | 16.60L (ENMAX 16 - ENMAX 34), 16.63L (ENMAX 16 - ENMAX 36), 16.2TR (ENMAX 16), 36.5TR (ENMAX 36) | 2020-05-23 12:01 | 2020-05-23 18:00 | N | N | Substation washing & check reversing switch | Line, Transformer | 16.60L (ENMAX 16 - ENMAX 34) 16.63L (ENMAX 16 - ENMAX 36) 16.2TR (ENMAX 16) |  | Creates Radial Feeds, Pre-Condition
ENMAX | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2020-05-24 08:00 | 2020-05-24 18:00 | N | N | repair 32.1TR MD & Spring substation washing on 32.83L structure & repair hotspot SW84 | Line, Transformer |  |  | Creates Radial Feeds
SUNCOR | 29EDD-56 | 2020-05-24 08:00 | 2020-05-30 18:00 | N | N | 72kV line 29PL6-14 and 29PP-41G bus breakers & damage stress cone & cable sup | Station | 29EDD-56
EPCOR | 72RV4 (511s Victoria - Rossdale), Victoria V726 (Victoria), Victoria V727 (Victoria) | 2020-05-25 07:00 | 2020-05-25 17:00 | N | N | doble | Line, Circuit Breaker | 72RV4 (Rossdale - 511s Victoria) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s 918 (2075s Newell) | 2020-05-25 07:00 | 2020-05-28 10:58 | N | Y | PRC-005 trip coil testing | Circuit Breaker | 2075s 918 (2075s Newell) | PRC-005 Trip Coil Testing, No constraints,Breaker 917 and Filter Bank 1 will remain in service | 240 kV, For Information Only
ATCO | 2029s ACF12 (2029s Heathfield) | 2020-05-25 07:00 | 2020-06-05 15:00 | N | Y | perform PRC-005 tests on all devices associated with ACF12 and breaker 1219 | Shunts | 2029s ACF12 (2029s Heathfield) | Perform PRC-005 tests on all devices associated with ACF12 and breaker 1219, Filter will be unavailable, One device worked on at a time 10BF12+SW1- 86, 94 relays 10R10+R22 - F602, F604, & F502 trench relay, 87, 86, 94 Diff Relay 10R01+R1- 86, 94 relays Trip Coils | 500 kV, For Information Only
ATCO | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 2020-05-25 08:00 | 2020-06-07 16:00 | N | Y | 240/144kV breaker fail protection and 826S Marguerite protection upgrade | Line | 7L91 (715s Leming Lake - 826s Marguerite Lake) | 240/144kV Breaker Fail Protection (OOS for duration of outages) 826S Marguerite P&C Upgrade | Pre-Condition
ENMAX | ENMAX 65 B240-D131 (ENMAX 65) | 2020-05-25 08:00 | 2020-05-25 12:00 | N | Y | SF6 sample | Circuit Breaker | ENMAX 65 B240-D131 (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 987s T3 (987s Clover Bar) | 2020-05-25 08:00 | 2020-05-25 17:00 | N | Y | tap changer maintenance | Transformer |  |  | 240 kV, For Information Only
ENMAX | 24.1TR (ENMAX 24) | 2020-05-25 08:00 | 2020-05-26 16:00 | N | N | 24.1TR XO ground cable corrective, check reversing switch | Transformer |  |  | For Information Only
ENMAX | 5.1TR (ENMAX 5) | 2020-05-25 08:00 | 2020-05-29 16:00 | N | N | power factor test, secondary cable tests, maintenance, gas relay testing | Transformer |  | power factor test transformer, transformer secondary cable tests, transformer maintenance, gas relay testing. 5.1TR outage has been extended to Friday May 29th due to test equipment issues. | For Information Only
ENMAX | 23.3TR (ENMAX 23) | 2020-05-25 08:00 | 2020-05-28 16:00 | N | N | power factor test, secondary cable tests, maintenance, gas relay testing, oil sampling MT, TC | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil sampling MT, TC | For Information Only
ALTALINK | 245s 3E (245s Seebe), 3L (245s Seebe - 3AL) | 2020-05-25 09:15 | 2020-05-29 16:45 | N | N | 138kV CT replacement | Circuit Breaker, Line | 3L (245s Seebe - 3L145) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L59 (789s Keg River - 7L59 tap) | 2020-05-25 10:00 | 2020-05-31 02:00 | N | Y | cross- arm change out | Line | 7L59 (789s Keg River - 7L59 tap) | Cross- Arm change out | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L02 (765s Mannix Mine - 873s Marion Lake) | 2020-05-25 10:00 | 2020-05-25 16:00 | N | N | emergency outage, replace crossarm | Line |  | A crossarm has been identified as twisted and the Bolts are partially sheared, a storm will most likely cause the crossarm to fail Risk assessment is attached | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 77s T2 (77s Sagitawah) | 2020-05-25 10:15 | 2020-05-28 17:45 | N | Y | transformer maintenance | Transformer | 77s T2 (77s Sagitawah) |  | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK | 370s T3 (370s North Lethbridge) | 2020-05-25 10:30 | 2020-05-28 17:30 | N | Y | maintenance, doble, conservator tank leak repair | Transformer | 370s T3 (370s North Lethbridge) |  | 240 kV, Pre-Condition
ENMAX | ENMAX 65 B240-D130 (ENMAX 65) | 2020-05-25 12:00 | 2020-05-25 16:00 | N | Y | SF6 sample | Circuit Breaker | ENMAX 65 B240-D130 (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-05-25 12:00 | 2020-05-29 14:00 | N | Y | structure replacements | Line | 909L (89s Ellerslie - 665s Dome) | Components/Structure Replacements (Structures #1B - 214) | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Affects Cranking Path
ALTALINK | 336S Fincastle | 2020-05-25 13:00 | 2020-06-03 13:30 | N | N | mobile install for fincastle fortis capacity increase project | Station |  | mobile install for fincastle fortis capacity increase project:138kV Bus outage for the installation 336s31, 336s28, piles, steel and bus work.336s1 Motor mech will be removed and replaced with manual ganged switch Closingopen points C, D, G & H in this outage.Mobile will be disconnected on May 3,13:30 and 336s Load will be on new T2. | Pre-Condition
ATCO | 6L11 (742s Freeman Lake - 743s Sarah Lake) | 2020-05-25 13:00 | 2020-05-25 16:00 | N | N | line inspection | Line | 6L11 (742s Freeman Lake - 743s Sarah Lake) | Line Inspection | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 638S Esso Judy Creek | 2020-05-25 13:00 | 2020-05-29 17:00 | N | N | replace 25kV and 69kV T1 bushings, repair | Station | ESSOJUDYCREEK | Replace 25kV and 69kV T1 Bushings, Repair T1 Breather Piping, Replace T1 Oil. Scheduled: Shannon Bouchard Issue To: Brent Reichenbaugh Contact #: 780.948.4136 | For Information Only
EPCOR | 72RV6 (511s Victoria - Rossdale), Victoria V723 (Victoria), Victoria V724 (Victoria) | 2020-05-26 07:00 | 2020-05-26 17:00 | N | N | Doble | Line, Circuit Breaker | 72RV6 (Rossdale - 511s Victoria) |  | Contingency Requires Mitigation, Firm Load Loss
ENMAX, ALTALINK | 36.81L (44s Bearspaw - ENMAX 36), ENMAX 36 B138-36.81 (ENMAX 36) | 2020-05-26 08:00 | 2020-05-26 10:00 | N | Y | RTU upgrade to commission CAC/OAC circuits | Line, Circuit Breaker | 36.81L (44s Bearspaw - ENMAX 36) |  | For Information Only, Pre-Condition
ALTALINK | 760L (163s Amoco Empress - 394s Empress) | 2020-05-26 08:15 | 2020-05-29 14:45 | N | N | urgent repair: upgrade failed "B" protection and "A" protection sync check | Line | 760L (163s Amoco Empress - 394s Empress) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 336s 607 (336s Fincastle) | 2020-05-26 09:30 | 2020-05-26 16:30 | N | N | PRC 5 maintain 138kV SF6 gas breaker-linked to Ref# 269066 | Circuit Breaker |  |  | For Information Only
ALTALINK | 202L (61s Lodgepole - 202AL), 61s 202N (61s Lodgepole) | 2020-05-26 09:30 | 2020-05-26 17:30 | N | N | maintenance on breaker including 1st trip testing | Line, Circuit Breaker | 202L (61s Lodgepole - 202L335) |  | Firm Load Loss, Affects Cranking Path
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), ENMAX 36 B138-14.83 (ENMAX 36) | 2020-05-26 10:00 | 2020-05-26 12:00 | N | N | 36 Sub RTU upgrade, commission CAC/OAC circuits | Line, Circuit Breaker | 14.83L (ENMAX 14 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 551EL1 | 2020-05-26 10:30 | 2020-05-26 15:30 | N | N | repair / replace broken fuse hook and change out fuse size | Switch | 551lL (953s Lake Louise) |  | For Information Only
ENMAX | 7.84L (ENMAX 7 - ENMAX 36) | 2020-05-26 12:00 | 2020-05-26 14:00 | N | N | 36 Sub RTU upgrade, commission CAC/OAC circuits | Line | 7.84L (ENMAX 7 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | ENMAX 36 B138-36BT3 (ENMAX 36) | 2020-05-26 14:00 | 2020-05-26 16:00 | N | N | 36 Sub RTU upgrade, commission CAC/OAC circuits | Circuit Breaker | 36B138-36.BT3 (ENMAX 36) |  | For Information Only, Pre-Condition
ENMAX | 16.63L (ENMAX 16 - ENMAX 36), 36.5TR (ENMAX 36) | 2020-05-26 16:00 | 2020-05-26 18:00 | N | N | 36 Sub RTU upgrade, commission CAC/OAC circuits | Line, Transformer | 36.5TR (ENMAX 36) |  | For Information Only, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2020-05-27 | 2020-05-28 06:00 | N | Y | maintenance | Switch |  | Leakage test and maintenance | Restricts Generation
ALTALINK | 250p 11 (250p Bighorn Plant) | 2020-05-27 | 2020-05-28 06:00 | N | Y | maintenance | Switch |  | leakage test and maintenance | Restricts Generation
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2020-05-27 07:00 | 2020-05-27 17:00 | N | N | doble | Line | 72CN10 (987s Clover Bar - Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 36.1TR (ENMAX 36) | 2020-05-27 08:00 | 2020-05-27 12:00 | N | N | 36 sub RTU upgrade, commission CAC/OAC circuits, open close open required on MD on return | Transformer | 36.1TR (ENMAX 36) |  | For Information Only
ENMAX | ENMAX 65 B240-D134 (ENMAX 65) | 2020-05-27 08:00 | 2020-05-27 16:00 | N | Y | SF6 sample, counter repair near and center phases | Circuit Breaker | ENMAX 65 B240-D134 (ENMAX 65) | SF6 sample. Counter Repair Near and Center Phases | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 6L57 (727s Kinuso - 735s Swan River) | 2020-05-27 08:00 | 2020-06-01 17:00 | N | N | line inspection | Line | 6L57 (727s Kinuso - 735s Swan River) | Line Inspection | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2020-05-27 08:00 | 2020-05-28 16:00 | N | N | change HV riser lugs and bushing caps, check reversing switch | Transformer |  | 11.4TR change HV riser lugs and bushing caps, check reversing switch | For Information Only
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood) | 2020-05-27 08:00 | 2020-05-28 17:45 | N | N | install mid-span structure (19A) between STR 19 & 20 to mitigate line clearance violations | Line | 694L (54s Fort Saskatchewan - 422s Westwood) | -Install mid-span structure (19A) between STR 19 & 20 to mitigate line clearance violations. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 336s 612 (336s Fincastle) | 2020-05-27 09:00 | 2020-05-27 16:30 | N | N | PRC 5 maintain 138kV SF6 gas breaker | Circuit Breaker |  | PRC 5 maintain 138kV SF6 gas breaker.336s Station OOS. Linked to Ref# 269066 | For Information Only
ALTALINK | 420s T1 (420s Broadmoor) | 2020-05-27 09:00 | 2020-05-28 17:00 | N | N | maintenance and doble | Transformer | 420s T1 (420s Broadmoor) | Maintenance on T1 & Doble | For Information Only
ENMAX | 36.2TR (ENMAX 36) | 2020-05-27 12:00 | 2020-05-27 14:00 | N | N | 36 sub RTU uugrade, commission CAC/OAC circuits, open close open required on MD on return | Transformer | 36.2TR (ENMAX 36) | 36 Sub RTU Upgrade. Commission CAC/OAC circuits. Open close open required on MD on return | For Information Only
EPCOR | 72VN21 (511s Victoria - Namao) | 2020-05-28 07:00 | 2020-05-28 17:00 | N | N | doble | Line | 72VN21 (511s Victoria - Namao) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 233s T2 (233s Beamer) | 2020-05-28 07:30 | 2020-05-28 17:00 | N | N | Replace oil pump | Transformer |  |  | For Information Only
ATCO | 7L61 (780s Lubicon - 796s Nipisi) | 2020-05-28 08:00 | 2020-05-28 17:00 | N | N | cross arm and insulator change out | Line | 7L61 (780s Lubicon - 796s Nipisi) | 7L61 Cross arm and insulator change out | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 995L (62s Brazeau - 995AL) | 2020-05-28 08:00 | 2020-05-28 20:00 | N | N | Required for creating Open Point 'A' | Line |  | Required for creating Open Point 'A' south of structure 5 on 995L outside of 62s. Open Point 'A" needed for 995L Structure replacements. Scheduled: Shannon Bouchard Issue To: Ted Graham Contact #: 778.214.6493 | Over/Under Voltage, Restricts Generation, Affects Cranking Path
ENMAX | 54.81L (ENMAX 54 - ENMAX 65) | 2020-05-28 08:00 | 2020-05-28 12:00 | N | N | SF6 sample 54B138-54.81 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 38.2TR (ENMAX 38) | 2020-05-28 09:00 | 2020-06-05 16:00 | N | N | secondary cable replacement, phasing required across MD on return | Transformer | 38.2TR (ENMAX 38) |  | For Information Only
ATCO | 6L03 (757s Battle River - 6L17 tap) | 2020-05-28 09:00 | 2020-05-28 11:00 | N | N | GOI to install some bird perch deterrents in a trouble area where we have had a few bird contacts. | Line |  | GOI to install some bird perch deterrents in a trouble area where we have had a few bird contacts. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 498s C1 (498s Tilley) | 2020-05-28 09:30 | 2020-05-28 16:30 | N | N | 138kV breaker maintenance | Shunts | 498s C1 (498s Tilley) |  | For Information Only
ENMAX | 40.81L (ENMAX 40 - ENMAX 41) | 2020-05-28 12:00 | 2020-05-28 16:00 | N | N | SF6 sample 41B138-40.81 | Line | 40.81L (ENMAX 40 - ENMAX 41) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 995L (62s Brazeau - 995AL) | 2020-05-29 07:00 | 2020-05-31 18:00 | N | Y | relocate structures 1 - 5 | Line | 995L (62s Brazeau - 995AL) | Relocate Structures 1 - 5 | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation,Affects Cranking Path
EPCOR | 1055L (629s Argyll Transfer Station - 816s Petrolia) | 2020-05-29 07:00 | 2020-06-03 17:00 | N | Y | line maintenance | Line | 1055L (629s Argyll Transfer - 816s Petrolia) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2020-05-29 08:00 | 2020-05-29 16:00 | N | N | power factor test HV breaker | Line | 21.61L (ENMAX 21 - ENMAX 34) | Power factor test HV breaker. 34B69-21.61. SF6 sample 21B69-21.61 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-05-29 08:00 | 2020-06-05 18:00 | N | N | 29PS-266 maintenance | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2020-05-29 12:00 | 2020-05-29 17:00 | N | Y | remove conductor from 995L1 and 995L2 over top of span 202L1 and 202L2 | Line | 202L (61s Lodgepole - 62s Brazeau) | Required for removing conductor from 995L1 and 995L2 over top of span 202L1 and 202L2. | Creates Radial Feeds, Firm Load Loss, Restricts Generation,Affects Cranking Path
ENMAX | 11.82L (ENMAX 11 - ENMAX 14), 11.83L (162s Beddington - ENMAX 11), 11.2TR (ENMAX 11), 11.3TR (ENMAX 11) | 2020-05-31 08:00 | 2020-05-31 16:00 | N | N | power factor test HV PT 11PT138-Z32. check reversing switch 11.3TR | Line, Transformer | 11.82L (ENMAX 11 - ENMAX 14) 11.83L (162s Beddington - ENMAX 11) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-56 | 2020-05-31 08:00 | 2020-06-09 18:00 | N | N | 72 kV work at 29EDD-56 & 29EDD-7 | Station |  |  | For Information Only
EPCOR | 52s T2 (52s East Industrial), 908AL (52S East Industrial - 908L) | 2020-06-01 07:00 | 2020-06-01 17:00 | N | Y | tap changer maintenance | Transformer, Line | 52s T2 (52s East Industrial) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 657s Summerside T2 (657s Summerside), 657s SU2402 (657s Summerside), 657s SU2403 (657s Summerside) | 2020-06-01 07:00 | 2020-06-05 17:00 | N | Y | doble and SFRA | Transformer, Circuit Breaker | 657s Summerside T2 (657s Summerside) |  | 240 kV, Pre-Condition
EPCOR | RW 2403 (EPCOR Riverview) | 2020-06-01 07:00 | 2020-06-12 17:00 | N | Y | breaker repair | Circuit Breaker | RW 2403 (EPCOR Riverview) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 987s CC13 (987s Clover Bar) | 2020-06-01 07:00 | 2020-06-26 17:00 | N | N | breaker replacement | Circuit Breaker | 987s CC13 (987s Clover Bar) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 330p 1209 (330p Genesee) | 2020-06-01 07:00 | 2020-06-02 17:00 | N | Y | maintenance and doble | Circuit Breaker | 330p 1209 (330p Genesee) |  | 500 kV
ATCO | 7L43 (739s Edith Lake - 809s Louise Creek) | 2020-06-01 08:00 | 2020-06-07 17:00 | N | N | pole repairs | Line |  | Pole Repairs | For Information Only
ALTALINK | 995L (62s Brazeau - 995AL) | 2020-06-01 08:00 | 2020-06-02 17:00 | N | Y | close Open Point 'A' | Line | 995L (62s Brazeau - 995AL) | Required to close Open Point 'A' south of structure 5 on 995L outside of 62s. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation,Affects Cranking Path
ENMAX | 5.10TR (ENMAX 5) | 2020-06-01 08:00 | 2020-06-05 16:00 | N | N | transformer checks and maintenance | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check PRD junction box | For Information Only
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10), ENMAX 10 B138-693 (ENMAX 10) | 2020-06-01 08:00 | 2020-06-01 16:00 | N | Y | breaker maintenance, SF6 sample | Line, Circuit Breaker | 693L (42s Sarcee - ENMAX 10) | HV Breaker Maintenance 10B138-693. SF6 sample. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 50L (44s Bearspaw Plant - ENMAX 21) | 2020-06-01 08:00 | 2020-06-30 17:00 | N | Y | Calgary ring road 50L line clearance; modify & replace structures and restring | Line | 50L (44s Bearspaw Plant - ENMAX 21) | Calgary Ring Road 50L line clearance: Modify STR 131-132. Replace STR 133-135 and re-string 133-134. Replace STR 141, 143, remove STR 142 and re-string 141-143 span | For Information Only, Pre-Condition
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2020-06-01 08:00 | 2020-06-04 17:00 | N | N | chang cross-arms and insulators | Line | 7L16 (766s Nevis - 948s Heatburg) | Changing Cross-arms & insulators | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 778s 601T (778s Big Valley) | 2020-06-01 08:00 | 2020-06-18 17:00 | N | N | replace 601TD and 601T | Transformer |  | Replacing 601TD & 601T - Sub will need to be offloaded to adjacent substations | For Information Only
ATCO | 770s 506C (770s Three Hills) | 2020-06-01 08:00 | 2020-06-12 17:00 | N | N | protection upgrade | Shunts |  | 770S Protection Upgrade - 506 Outage Outage to 506 to upgrade 506C protection. 506C will be unavailable for the duration of the outage. | Pre-Condition
ENMAX | 11.2TR (ENMAX 11) | 2020-06-01 08:00 | 2020-06-04 16:00 | N | N | testing and maintenance | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil sampling MT, TC. | For Information Only
ENMAX | 41.1TR (ENMAX 41) | 2020-06-01 08:00 | 2020-06-02 16:00 | N | N | transformer and tapchanger checks and maintenance | Transformer |  |  | For Information Only
ENMAXGPI | 134s T1 (134s Taber Wind Farm), 134s T2 (134s Taber Wind Farm) | 2020-06-01 08:00 | 2020-06-01 18:00 | N | Y | Fincastle upgrade project construction (P1902): temporary bypass arrangement | Transformer |  |  | Restricts Generation
ALTALINK | 777L (48s Pocaterra - 245s Seebe) | 2020-06-01 08:15 | 2020-06-09 18:00 | N | Y | urgent line clearance (Str 49 - 207) | Line | 777L (48s Pocaterra - 245s Seebe) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 263s 35 (263s Strachan), 263s C1 (263s Strachan) | 2020-06-01 08:30 | 2020-06-05 14:30 | N | N | capacitor bank protection upgrade | Circuit Breaker, Shunts | 263s C1 (263s Strachan) 263s 35 (263s Strachan) |  | Pre-Condition
SHELL | 402s T1 (402s Shell Expansion 1) | 2020-06-01 09:00 | 2020-06-10 14:00 | N | N | cable termination inspection/repair of 484-SG-3501 switchgear & 52-1A breaker cell | Transformer |  | Customer Requested Outage - cable termination inspection/repair of 484-SG-3501 switchgear & 52-1A breaker cell - GOI to Garnet Sims on 701T at the same time See GOI# | For Information Only
ALTALINK | 178s 202X (178s Cynthia), 61s 202N (61s Lodgepole), 202L (178s Cynthia - 202AL), 202L (61s Lodgepole - 202AL), 202AL (359s Esso West Pembina - 202L), 359s T1 (359s Esso West Pembina), 359s T2 (359s Esso West Pembina) | 2020-06-01 09:00 | 2020-06-05 17:00 | N | N | commissioning for the new additions (P2012) | Circuit Breaker, Line, Transformer | 202AL (359s Esso West Pembina - 202L) 202L (178s Cynthia - 202AL) 202L (61s Lodgepole - 202AL) |  | Pre-Condition,Affects Cranking Path
ALTALINK | 410s 852 (410s Josephburg), 410s 952 (410s Josephburg), 776L (308s Albchem Beaverhill Creek - 410s Josephburg) | 2020-06-01 09:00 | 2020-06-02 16:00 | N | N | removing recloser capabilities for 410s952 | Circuit Breaker, Line | 706L (410s Josephburg - 706AL) | Removing recloser capabilities for 410s952. Recommissioning remaining circuits for proper functionality. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 510s ACF11 (510s Sunnybrook) | 2020-06-01 09:30 | 2020-06-04 16:30 | N | Y | annual inspection & maintenance | Shunts | 510s ACF11 (510s Sunnybrook) |  | 500 kV, For Information Only
ALTALINK | 391s 611 (391s Balzac), 611L (186s Dry Creek - 391S Balzac) | 2020-06-01 10:30 | 2020-06-04 17:00 | N | N | 138 kV breaker maintenance, riser replacements | Circuit Breaker, Line | 611L (186s Dry Creek - 391S Balzac) 391s 611 (391s Balzac) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge) | 2020-06-01 10:30 | 2020-06-02 17:30 | N | N | maintenance, doble | Transformer | 370s T4 (370s North Lethbridge) | N.O. TX; maintenance, doble | For Information Only
ATCO | 813s SVC (813s Little Smoky) | 2020-06-01 11:00 | 2020-06-30 14:45 | N | Y | yearly maintenance | Shunts | 813s SVC (813s Little Smoky) | Yearly maintenance - Glycol is being changed - drain, flush, refill, Fittings and tubing will be changed as fittings have been leaking. | For Information Only
ALTALINK | 610L (83s Taber - 336s Fincastle) | 2020-06-01 11:00 | 2020-06-01 16:00 | N | Y | P1902, removal of temporary bypass and restore anti-Islanding scheme to normal | Line | P1902 | Fincastle Fortis Capacity Increase Project: Removal of Temp bypass conductors connected to 610L and restor anti-Islanding scheme to normal | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 320p 2052 (320p Keephills), 320p 2152 (320p Keephills), 903L (17s Benalto - 320p Keephills) | 2020-06-01 12:00 | 2020-06-01 17:00 | N | Y | replace damaged 903L relay FT switch | Circuit Breaker, Line | 903L (17s Benalto - 320p Keephills) |  | 240 kV,Affects Cranking Path
ALTALINK | 434s 790 (434s Stony Plain), 790L (434s Stony Plain - 790AL) | 2020-06-01 12:30 | 2020-06-04 15:30 | N | N | replace the 434s4 switch | Circuit Breaker, Line | 790L (434s Stony Plain - 790L62) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 324s 1252 (324s Cassils) | 2020-06-01 12:30 | 2020-06-01 17:30 | N | Y | replace burned out heater on west phase | Circuit Breaker | 324s 1252 (324s Cassils) |  | 240 kV, Contingency Requires Mitigation
ATCO | 722s 703C (722s Crystal Lake), 722s 703 (722s Crystal Lake) | 2020-06-01 13:00 | 2020-06-04 16:00 | N | N | re-route control cables | Shunts, Circuit Breaker |  | Re-route control cables for 702T change, Cap bank unavailable during outage | For Information Only
EPCOR | Garneau T2 (Garneau) | 2020-06-02 07:00 | 2020-06-02 17:00 | N | N | maintenance (tap changer) | Transformer | Garneau T2 (Garneau) |  | For Information Only
ALTALINK | 205s13 (205s Castle Rock Ridge) | 2020-06-02 07:30 | 2020-06-03 16:30 | N | Y | customer maintenance outage | Switch |  |  | 240 kV, For Information Only, Restricts Generation
ATCO | 751s 701 (751s Hill) | 2020-06-02 08:00 | 2020-06-04 16:00 | N | N | breaker testing | Circuit Breaker |  | Breaker testing | Pre-Condition
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12) | 2020-06-02 08:00 | 2020-06-02 16:00 | N | Y | HV breaker maintenance 10B138-832L. SF6 sample | Line | 832L (ENMAX 10 - ENMAX 12) |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 6L44 (769s Stettler - 778s Big Valley) | 2020-06-02 08:00 | 2020-06-02 17:00 | N | N | change 2 poles, from test and treat program | Line |  | Change 2 poles, from test and treat.Program Risk Assessment: 6L44 OOS has no impact to bulk electrical system - line is radially fed to 778S 778S 25kv load will be transferred to adjacent substations | For Information Only
ALTALINK | 574s T1 (574s Nilrem) | 2020-06-02 08:30 | 2020-06-04 17:00 | N | Y | PRC-5 maintenance & doble, neutral conductor replacement, oil leak, and testing | Terminal Equipment |  | PRC-5 574sT1 Maintenance & Doble. Neutral conductor replacement, Oil Leak, AC supply and SFRA Testing. | 240 kV, For Information Only
ALTALINK | 324s 1152 (324s Cassils) | 2020-06-02 08:30 | 2020-06-02 17:30 | N | Y | top up west phase and investigate leak | Circuit Breaker | 324s 1152 (324s Cassils) |  | 240 kV, For Information Only, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-06-02 09:00 | 2020-06-11 16:00 | N | Y | components/structure replacements (structures #1B - 214) | Line | 909L (310p Sundance - 665s Dome) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Affects Cranking Path
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-06-02 09:30 | 2020-06-02 13:00 | N | N | maintenance on 364s798 breaker and 1st trip testing | Line | 798L (77s Sagitawah - 364s Whitecourt Industrial) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial) | 2020-06-02 13:00 | 2020-06-02 16:30 | N | N | maintenance on breaker | Line | 797L (268s Whitecourt - 364s Whitecourt industrial) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | Garneau T3 (Garneau) | 2020-06-03 07:00 | 2020-06-03 17:00 | N | N | tap changer maintenance | Transformer | Garneau T3 (Garneau) | Maintenance (Tap Changer) | For Information Only, Pre-Condition
EPCOR | 330p 1204 (330p Genesee) | 2020-06-03 07:00 | 2020-06-04 17:00 | N | Y | doble and breaker maintenance | Circuit Breaker | 330p 1204 (330p Genesee) | Doble and Breaker Mtce | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 411S Obed | 2020-06-03 07:00 | 2020-06-03 21:00 | N | N | transformer maintenance, doble test, barrier leak, winding temp gauge reset repair, TC oil leak. | Station | MOUNTAINCOALOBED | Transformer Maintenance, doble test, barrier leak, Winding temp gauge reset repair, TC oil leak. Scheduled: Shannon Bouchard Issue To: Marek Gwozdz / Daniel Maier Contact #: 780.221.7397 / 780.686.0546 | For Information Only
ALTALINK | 745AL (745A1L - 745L), 745L (602s Cold Creek - 745AL), 745L (39s Bickerdike - 745AL), 745AL (411s Obed - 745A1L), 745A1L (975s Dalehurst - 745AL) | 2020-06-03 07:00 | 2020-06-03 21:00 | N | Y | maintenance | Line | 745L (39s Bickerdike - 602s Cold Creek) | Scope of work includes maintenance on Structures 745ALJCT- 745AL3 & 745A1L1 on 745AL1 and Strs 4, 7, 8 and 9 on 745AL and Strs 358, 561, 572 and 575 on 745L. Scheduled: Shannon Bouchard Issue To: Ken Teasdale Contact #: 403.360.4960 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 90L (32s Barrier - 115s Mt. Allan) | 2020-06-03 08:00 | 2020-06-04 18:00 | N | Y | structure replacement and maintenance | Line | 90L (32s Barrier - 115s Mt. Allan) | Scope of work consists of replacing Str 4 and maintenance on Str 36 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 370s T1 (370s North Lethbridge) | 2020-06-03 08:00 | 2020-06-04 17:30 | N | N | maintenance and doble | Transformer | 370s T1 (370s North Lethbridge) | maintenance and doble | For Information Only
ALTALINK | 33s 5 (33s Spray) | 2020-06-03 08:00 | 2020-06-03 12:00 | N | Y | maintenance | Switch |  |  | For Information Only, Restricts Generation
ENMAX | 41.2TR (ENMAX 41) | 2020-06-03 08:00 | 2020-06-04 16:00 | N | N | tapchanger inspection and transformer maintenance | Transformer |  | Tapchanger inspection. Check reversing switch. Oil sampling MT, TC. Filmax maint. | For Information Only
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2020-06-03 08:00 | 2020-06-04 16:00 | N | N | HV breaker maintenance, HLR, DGA, and sheath testing | Line | 9.83L (ENMAX 9 - ENMAX 43) | HV Breaker maintenance 9B138-9.83. HLR. DGA & sheath testing. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 324s 1552 (324s Cassils) | 2020-06-03 08:30 | 2020-06-03 17:30 | N | Y | investigate leak | Circuit Breaker | 324s 1552 (324s Cassils) | top up C phase - low gas and investigate leak | 240 kV, Pre-Condition
ALTALINK | 410s 1152 (410s Josephburg), 410s 552 (410s Josephburg), 706L (410s Josephburg - 706AL) | 2020-06-03 09:00 | 2020-06-04 16:00 | N | N | removing recloser capabilities for 410s1152, recommissioning remaining circuits for proper functionality | Circuit Breaker, Line | 706L (410s Josephburg - 706AL) |  | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
VISIONREQ | 354s Summerview RTU/SCADA | 2020-06-03 10:00 | 2020-06-03 12:00 | N | N | computer updates | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 33s 4 (33s Spray) | 2020-06-03 13:00 | 2020-06-03 17:00 | N | Y | maintenance | Switch |  |  | For Information Only, Restricts Generation
ALTALINK | 895s T2 (895s Suffield) | 2020-06-04 08:00 | 2020-07-23 14:00 | N | N | forced outage since Feb | Transformer |  | Re-install the single-phase repaired VR for VR1. New conductor will be installed from Tx 18608 to the VR. | For Information Only
ALTALINK | 33s 6 (33s Spray) | 2020-06-04 08:00 | 2020-06-10 17:00 | N | Y | maintenance | Switch |  |  | For Information Only, Restricts Generation
SUNCOR | 29EDD-71 752-4633 (29EDD-71), 29EDD-71 752-4634 (29EDD-71), 29EDD-71 752-4652 (29EDD-71), 29PL7-3 (29EDD-65 - 29EDD-71), 29PL7-5 (29EDD-18 - 29EDD-71) | 2020-06-04 14:00 | 2020-06-06 18:00 | N | N | breaker fail protection being out of service on the breakers 752_4633, 752_4634 and 752_4652 | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK, EPCOR | 1056L (89s Ellerslie - 629s Argyll Transfer Station) | 2020-06-05 07:00 | 2020-06-08 17:00 | N | Y | line maintenance | Line | 1056L (89s Ellerslie - 629s Argyll Transfer Station) |  | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
SUNCOR | 635PT-1003 (635EDD-1000) | 2020-06-05 07:00 | 2020-06-08 17:00 | N | N | replace tap changer selector switch & breaker tank heater | Transformer |  |  | For Information Only
ALTALINK | 113L (20s Ghost - 33s Spray) | 2020-06-06 08:00 | 2020-06-09 18:00 | N | N | P5 urgent clearance on 113L at 113L64 and 113L105 | Line |  |  | Pre-Condition, Affects Cranking Path
ENMAX | 162.4TR (ENMAX 162 Beddington) | 2020-06-06 08:00 | 2020-06-06 16:00 | N | N | urgent outage required to investigate and repair oil leak | Transformer |  |  | For Information Only
ALTALINK | 77s T1 (77s Sagitawah), 77s Sagitawah 138 kV West Bus, 77s Sagitawah 240 kV West Bus | 2020-06-08 07:00 | 2020-06-17 13:30 | N | Y | replace protections and maintenance | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
EPCOR | 511s Victoria T1 (511s Victoria) | 2020-06-08 07:00 | 2020-06-19 17:00 | N | N | LTC install | Transformer | 511s Victoria T1 (511s Victoria) |  | For Information Only
ALTALINK | 511s 1252 (511s Crossings), 511s ACF11 (511s Crossings) | 2020-06-08 07:30 | 2020-06-11 16:30 | N | N | annual inspection & maintenance | Circuit Breaker, Shunts |  |  | 240 kV, Pre-Condition
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2020-06-08 08:00 | 2020-06-09 16:00 | N | N | HV breaker maintenance, replace poles | Line | 6.82L (ENMAX 6 - ENMAX 41) | HV Breaker maintenance. 41B138-6.82. HLR. Replace Poles on Underbuild. | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.1TR (ENMAX 2) | 2020-06-08 08:00 | 2020-06-12 16:00 | N | N | reversing switch replacement, substation washing | Transformer |  | 2.1TR LTC reversing switch pitting - replacement needed. Substation Washing | For Information Only
ATCO | 848s 605T (848s Ruth Lake) | 2020-06-08 08:00 | 2020-06-11 17:00 | N | N | install bird proofing | Transformer |  | Install bird proofing on 500BS2, 605T, 504 Bkr @ 848S -------- Load Transfer -------- 848S 5L381 Peak Load = 0 MVA 848S 5L309 Peak Load = 0 MVA 848S 5L381 Relay Settings: 848S 5L309 Relay Settings: -------- Load Transfer -------- | For Information Only
ENMAX | 5.10TR (ENMAX 5) | 2020-06-08 08:00 | 2020-06-11 18:00 | N | N | plastibeton tray replacement at 5 Sub | Transformer |  |  | For Information Only
ENMAX | 37.2TR (ENMAX 37) | 2020-06-08 08:00 | 2020-06-11 16:00 | N | N | power factor test, secondary cable tests, maintenance, oil sampling MT | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance. Oil sampling MT. | For Information Only
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2020-06-08 08:00 | 2020-06-11 17:00 | N | N | change cross-arms and insulators | Line | 7L16 (766s Nevis - 948s Heatburg) | Changing Cross-arms & insulators | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Innisfail Solar Corporation | INF1 Innisfail | 2020-06-08 08:00 | 2020-06-24 16:00 | N | N | P2097 Innisfail DER Solar 22 MW. ISD June 17, 2020 | Unit
ENMAX | 162.2TR (ENMAX 162 Beddington), 162s Beddington 240 kV South Bus, 162s Beddington 138 kV South Bus | 2020-06-08 08:00 | 2020-06-18 16:00 | N | Y | transformer differential relay replacement, switch maintenance | Transformer, Bus | 162.2TR (ENMAX 162 Beddington) | Transformer differential relay replacement. Commission circuits. HV SW maint SW105, SW89, SW88, SW136, SW146, MD138-162.2TR, MD240-162.2TR. Oil sampling MT, TC, Bushings. Check reversing switch. Replace switch mech SW136. Oil top up PT Z44 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | ENMAX 2 B138-D81 (ENMAX 2), ENMAX 2 B138-D82 (ENMAX 2) | 2020-06-08 08:00 | 2020-06-18 16:00 | N | N | DCTRP. upgrade 2.84L settings | Circuit Breaker |  | DCTRP. Upgrade 2.84L settings. | For Information Only, Pre-Condition
BCH | 2L294 (A.A. Lambert - Cranbrook) | 2020-06-08 09:00 | 2020-06-26 17:00 | N | Y | structure replacement & disconnect maintenance | Line | 2L294 (Cranbrook - A.A. Lambert), NLY 2D23 to AAL 2D22 | structure replacement & disconnect maintenance | 240 kV, Limits ATC, Pre-Condition
ATCO | 716s 701T (716s Lloydminster) | 2020-06-08 09:00 | 2020-06-11 16:00 | N | N | testing | Transformer | 716s 701T (716s Lloydminster) | Isolate 701T and Bkr 703 and test, 716S Load to be transferred to 751S/880S | For Information Only
ALTALINK | 38s 7552 (38s East Edmonton) | 2020-06-08 09:30 | 2020-06-11 17:30 | N | Y | breaker maintenance and grading cap replacement and testing | Circuit Breaker |  | Maintenance on 38s7552 breaker & grading cap replacement. 1st Trip, 1st Close, 2nd Trip testing | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 789s 701 (789s Keg River), 7L64 (779s Chinchaga River - 789s Keg River) | 2020-06-08 09:30 | 2020-06-08 13:00 | N | Y | trip coil testing | Circuit Breaker, Line |  | PRC-005 - TRIP COIL TESTING - BREAKER 701 @ 789S 7L64 will be Open Ended for duration of work. | Pre-Condition, Affects Cranking Path
ATCO | 6L11 (742s Freeman Lake - 854s Swan Dive) | 2020-06-08 10:00 | 2020-06-11 17:00 | N | N | line inspection | Line | 6L11 (742s Freeman Lake - 854s Swan Dive) | Line Inspection | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 826s 710 (826s Marguerite Lake) | 2020-06-08 10:00 | 2020-06-08 12:00 | N | N | breaker testing | Circuit Breaker |  | Test new Breaker Fail trip coming from new 50BF/704 protection relay. Test and Operate will happen after 7L91 work completed (GOI 2-49583) and Prior to 7L89 outage proceeding (GOI 2-49582) | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 421s T1 (421s Hays) | 2020-06-08 11:00 | 2020-06-08 15:00 | N | N | test contact and fix wiring | Transformer |  |  | For Information Only
ALTALINK | 385s68 (385s Spring Coulee), 225L (225s Magrath - 385s Spring Coulee) | 2020-06-08 11:15 | 2020-06-08 17:15 | N | N | frayed conductor repair | Switch, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 55s T1 (55s Olds) | 2020-06-08 11:30 | 2020-06-13 17:00 | N | N | bushings replacement, doble, maintenance | Transformer |  |  | For Information Only
ALTALINK | 305s 446 (305s Acheson), 446L (305s Acheson - 367s Harry Smith) | 2020-06-08 12:30 | 2020-06-10 17:30 | N | N | breaker and switch maintenance and testing | Circuit Breaker, Line |  | 305s446 Breaker Maintenance. 305s23 Maintenance. 1st Trip testing. | Pre-Condition
ATCO | 7L89 (721s La Corey - 826s Marguerite Lake) | 2020-06-08 13:00 | 2020-06-21 16:00 | N | Y | P&C upgrade | Line |  | 240/144kV Breaker Fail Protection (OOS for duration of outages) 826S Marguerite P&C Upgrade, Cutover 7L89 21A and 21B PT, CT, and P&C ccts | Pre-Condition
ALTALINK | 744L (235s Entwistle - 744AL) | 2020-06-08 13:00 | 2020-06-09 17:00 | N | N | clearance mitigation | Line |  | Urgent Repair to 744L str's 75 and 120A replacing glass | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 789s 702 (789s Keg River), 7L62 (789s Keg River - 797s Kemp River) | 2020-06-08 13:00 | 2020-06-08 16:30 | N | Y | trip coil testing | Circuit Breaker, Line | 7L62 (789s Keg River - 797s Kemp River) 789s 702 (789s Keg River) | PRC-005 - Trip coil testing breaker 702 @ 789S, 7L62 will be Open Ended for duration of work. | Pre-Condition
ENMAX | 65.1TR (ENMAX 65), 65.2TR (ENMAX 65) | 2020-06-09 06:10 | 2020-06-10 17:00 | N | Y | forced outage | Transformer |  |  | 240 kV, Overload, Pre-Condition
ATCO | 724s 601T (724s Hines Creek), 724s 601 (724s Hines Creek) | 2020-06-09 08:00 | 2020-07-16 16:00 | N | N | work includes 72kV breaker replacement, fix bypass switch, new PT, and some other misc. items | Transformer, Circuit Breaker |  | 724S Hines Creek, 601 & 601T required out of service for the duration 72kv bypass will be in place (6L16 & 6L37) and 25kv load offloaded via distribution system The scope of work includes 72KV breaker replacement, fix bypass switch, new PT, and some other misc. items. | For Information Only, Pre-Condition
ATCO | 789s 703 (789s Keg River), 7L59 (789s Keg River - 7L59 tap) | 2020-06-09 08:30 | 2020-06-09 12:30 | N | Y | PRC-005 trip coil testing | Circuit Breaker, Line | 7L59 (789s Keg River - 7L59 tap) 789s 703 (789s Keg River) | PRC-005 - Trip coil testing breaker 703 @ 789S, 7L59 will be Open Ended for duration of work. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 508L (67s Stirling - 344s Warner), 344s T1 (344s Warner), 344s T2 (344s Warner) | 2020-06-09 09:00 | 2020-06-09 18:00 | N | N | urgent replace shot out insulators | Line, Transformer |  |  | For Information Only
STROBE | 240S McBride Lake | 2020-06-09 09:00 | 2020-06-09 15:00 | N | Y | repair leaking transformer | Station |  |  | Restricts Generation
ALTALINK | 275s 2 (275s Jenner) | 2020-06-09 09:00 | 2020-06-11 14:30 | N | N | urgent repair leaking on one phase | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-06-09 09:30 | 2020-06-09 14:30 | N | N | replace dead end polymers on the A-frame 77s and 798L str 1 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 415s164 (415s Drywood), 164L (103s Goose Lake - 415s Drywood), 415s T1 (415s Drywood), 415s 21 (415s Drywood) | 2020-06-09 09:30 | 2020-06-11 17:00 | N | N | breaker maintenance, transformer maintenance, doble, leak repair | Switch, Line, Transformer, Circuit Breaker |  | 69kV breaker maintenance (s21), 138kV breaker maintenance (s164), TX maintenance, doble, leak repair | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 789s 704 (789s Keg River), 7L58 (789s Keg River - 905s Meikle) | 2020-06-09 12:30 | 2020-06-09 16:30 | N | Y | PRC-005 trip coil testing | Circuit Breaker, Line | 7L58 (789s Keg River - 905s Meikle) 789s 704 (789s Keg River) | PRC-005 - Trip coil testing breaker 704 @ 789S, 7L58 will be Open Ended for duration of work. | Pre-Condition, Affects Cranking Path
ATCO | 827s SVC (827s Cranberry Lake) | 2020-06-09 22:00 | 2020-06-10 16:00 | N | Y | forced outage | Shunts |  |  | For Information Only
ALTALINK | 754L (245s Seebe - 742L) | 2020-06-10 07:00 | 2020-06-10 09:00 | N | N | maintenance | Line |  | 754L65A has been repaired, arranged for TLS to be on site to confirm operation of repair, switch was deemed unsafe as per Fortis on previous outage. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 853L (28s West Brooks - 853AL) | 2020-06-10 08:00 | 2020-06-10 18:00 | N | Y | maintenance | Line |  | *P5 Urgent Repair on 853L34 Loose Conductor Damper | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 7L67 (824s Fieldgate - 851s Morse River) | 2020-06-10 08:00 | 2020-06-12 16:00 | N | N | Line Inspection | Line | 7L67 (824s Fieldgate - 851s Morse River) | Line Inspection | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.83L (ENMAX 33 - ENMAX 41) | 2020-06-10 08:00 | 2020-06-12 16:00 | N | N | HV breaker maintenance | Line | 33.83L (ENMAX 41 - ENMAX 33) | HV breaker maintenance. 41B138-33.83. SF6 sample 33B138-33.83. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 744L (207s Pinedale - 228s T.M.P.L.Niton) | 2020-06-10 08:00 | 2020-06-11 17:30 | N | N | component replacements | Line | 744L (228s T.M.P.L.Niton - 207s Pinedale) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 789s 705 (789s Keg River), 789s 705R (789s Keg River) | 2020-06-10 08:30 | 2020-06-10 12:30 | N | N | maintenance | Circuit Breaker, Shunts | 789s 705R (789s Keg River) | PRC-005 - TRIP COIL TESTING - BREAKER 705 @ 789S PRC-005 Trip Coil Testing & Sudden Pressure Relay Testing 705R will be OOS for duration of work. PRC-005 Testing Auxiliary relays at same time, Relays will be OOS one at a time | For Information Only
ALTALINK | 595sT1 (595s Spruce Grove) | 2020-06-10 08:30 | 2020-06-11 17:30 | N | N | relay settings changes | Transformer |  | Techs to perform settings changes on: T1 B8750/51/51NN/T1 URT60 Redundant protection will be in place while work is being performed, unless otherwise stated. | For Information Only
ATCO | 741s 705C (741s Fox Creek) | 2020-06-10 10:00 | 2020-06-10 16:00 | N | N | trip coil testing | Shunts |  | PRC-005 - TRIP COIL TESTING - BREAKER 705 @ 741S, 705C OOS | For Information Only
ALTALINK | 336s T1 (336s Fincastle) | 2020-06-10 11:00 | 2020-06-30 09:00 | N | N | installation and reconductoring of 2151L | Transformer |  | Installation of 752, 289, reconductoring of 2151L, 2152L, and 2153L inside the station.Closing Open Point'E' and Open point 'F" | For Information Only
ALTALINK | 267s Killarney Lake 138kV bus, 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2020-06-10 12:30 | 2020-06-11 15:30 | N | N | 138kV bus repair | Bus, Shunts |  |  | For Information Only
ATCO | 789s 706 (789s Keg River), 789s 706C (789s Keg River) | 2020-06-10 12:30 | 2020-06-10 16:30 | N | N | maintenance | Circuit Breaker, Shunts | 789s 706C (789s Keg River) 789s 706 (789s Keg River) | PRC-005 - Trip coil testing breaker 706 @ 789S, Also testing the following auxiliary relays: 86C-1/706C, 94C-1/706C, 94-1/706C - Capacitor 706C will be OOS for duration of work. | For Information Only
ALTALINK | 763L (158s Vauxhall - 763AL) | 2020-06-11 07:45 | 2020-06-18 17:45 | N | N | urgent line clearance mitigation (str 324-406), repair loose conductor damper (str 272) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 524s T1 (524s Owen Corning) | 2020-06-11 08:00 | 2020-06-11 12:00 | N | N | shutdown | Transformer |  |  | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2020-06-11 08:00 | 2020-06-11 17:00 | N | N | H722 Doble | Circuit Breaker | Hardisty H722 (Hardisty Epcor) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 257s T1 (257s Hull) | 2020-06-11 14:57 | 2020-06-11 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2020-06-11 22:05 | 2020-06-12 15:06 | N | N | forced outage | Transformer |  |  | For Information Only
EPCOR | Hardisty H726 (Hardisty Epcor) | 2020-06-12 08:00 | 2020-06-12 17:00 | N | N | doble | Circuit Breaker | Hardisty H726 (Hardisty Epcor) |  | Contingency Requires Mitigation, Overload, Pre-Condition
PANC, ALTALINK | PCES02L (391s Balzac - PCES02S Balzac Power Station), 611L (186s Dry Creek - 391S Balzac), 391s T1 (391s Balzac) | 2020-06-13 06:00 | 2020-06-14 18:00 | N | Y | protection upgrade and replacements | Line, Transformer | PCES02L (391s Balzac - PCES02S Balzac Power Station) | protection upgrade (PCES02L), grading cap replacement (392s25), hotspot repair (391s17, 391s18, 391s24), glass replacement (391s19) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 320p 652 (320p Keephills), 320p 752 (320p Keephills) | 2020-06-13 07:00 | 2020-06-22 17:00 | N | N | TransAlta switch work | Circuit Breaker |  |  | Pre-Condition
ATCO | 7L67 (743s Sarah Lake - 824s Fieldgate) | 2020-06-13 08:00 | 2020-06-15 16:00 | N | N | line inspection | Line | 7L67 (743s Sarah Lake - 824s Fieldgate) | Line Inspection | Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | 511s Victoria T1 (511s Victoria), Victoria V721 (Victoria), Victoria V722 (Victoria) | 2020-06-13 08:00 | 2020-06-13 17:00 | N | N | doble | Transformer, Circuit Breaker |  |  | Pre-Condition
SUNCOR | 29EDD-55 29Edd-55, 29PL6-2 (836s Steepbank - 29EDD-55) | 2020-06-13 08:00 | 2020-06-21 02:35 | N | N | maintenance | Station, Line | 29EDD-55 |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 83s T1 (83s Taber) | 2020-06-13 08:00 | 2020-06-13 18:00 | N | Y | remove nest | Transformer |  | remove nest from 25kV bus 1 before it falls and takes out a breaker like last time. ISO significant DG on 83s15E | Restricts Generation
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee) | 2020-06-13 08:00 | 2020-06-14 17:00 | N | Y | doble and aerial marker upgrades | Line | 1209L (89s Ellerslie - 330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO, ALTALINK | 12L41 (510s Sunnybrook - 939s Livock), 12L44 (939s Livock - 951s Thickwood Hills) | 2020-06-13 08:00 | 2020-06-14 17:00 | N | Y | EPCOR outage on 1209L for Doble testing, requires de- energizing of 12L41 outage due to risk of forming Genesee Island with the HVDC facilities at 510s Sunnybrook | Line | 12L41 (510s Sunnybrook - 939s Livock) |  | 500 kV
ALTALINK | 431s T1 (431s Hussar) | 2020-06-13 08:15 | 2020-06-15 17:15 | N | N | maintenance, doble, replace CT phases | Transformer | 431s T1 (431s Hussar) |  | For Information Only
ALTALINK | 55s T2 (55s Olds) | 2020-06-13 17:01 | 2020-06-19 17:30 | N | N | bushings replacement, doble, maintenance | Transformer | 55s T2 (55s Olds) |  | For Information Only, Pre-Condition
ALTALINK | 227S Cutting Lake | 2020-06-14 10:00 | 2020-06-14 16:30 | N | N | replace leaking gas detector on T1 | Station |  |  | For Information Only
ALTALINK | 285s East Camrose 138kV Partial Bus, 285s T2 (285s East Camrose), 729L (285s East Camrose - 542s Ervick) | 2020-06-15 06:00 | 2020-06-21 02:35 | N | N | install new 138kV switch, move PT7 | Bus, Transformer, Line | 285s East Camrose 138kV Bus | Install new 138kV switch, move PT7 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | Meadowlark MDS7 (Meadowlark), Meadowlark M723 (Meadowlark), Meadowlark M724 (Meadowlark), 72MG16 (Garneau - Meadowlark) | 2020-06-15 07:00 | 2020-06-19 17:00 | N | N | disconnect replacement | Switch, Circuit Breaker, Line | 72MG16 (Garneau - Meadowlark) Meadowlark T3 (Meadowlark) Meadowlark M723 (Meadowlark) Meadowlark M724 (Meadowlark) |  | Firm Load Loss, Pre-Condition
ATCO | 2075s 900BS2 240kV bus ( 2075s Newell), 2075s 901T (2075s Newell) | 2020-06-15 07:00 | 2020-06-22 17:30 | N | Y | transformer maintenance | Bus, Transformer |  | SVC TRANSFORMER MAINTENANCE @ NEWELL 2075S 901T Testing, SVC1 OUT OF SERVICE. SVC2 WILL STILL BE AVAILABLE Note: Breakers 917, 918, 906, 912, 921 & 923 (isolate 900 BS2) will be required opened for testing. This will only be for a few hours on one day of the outage. | 240 kV, Pre-Condition
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2020-06-15 07:00 | 2020-06-19 18:00 | N | Y | work includes Alberta Transportation to drive piles for new overpass, working in proximity of structures 909L188/1044L8 and 909L189/1044L9. | Line |  |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 263s T1 (263s Strachan) | 2020-06-15 07:00 | 2020-06-18 15:00 | N | N | salvage of breaker 239x, associated switches 263s15,263s16 and install bird cover on 263s50, 242L arrestors, 243L arrestors | Transformer |  |  | For Information Only
EPCOR | 665s TX2 (665s Dome), 665s D2402 (665s Dome), 665s D2403 (665s Dome) | 2020-06-15 07:00 | 2020-06-19 17:00 | N | Y | maintenance / Doble | Transformer, Circuit Breaker | 665s TX2 (665s Dome) |  | 240 kV, For Information Only, Pre-Condition
ALTALINK, EPCOR | 1057L (89s Ellerslie - 657s Summerside), 657s SU2401 (657s Summerside), 657s SU2402 (657s Summerside) | 2020-06-15 07:00 | 2020-06-15 17:00 | N | Y | Doble | Line, Circuit Breaker | 1057L (89s Ellerslie - 657s Summerside) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 909L (310p Sundance - 665s Dome) | 2020-06-15 07:00 | 2020-06-19 18:00 | N | Y | work includes Alberta Transportation to drive piles for new overpass, in proximity of structures 909L188/1044L8 and 909L189/1044L9 | Line |  |  | 240 kV, For Information Only, Pre-Condition, Affects Cranking Path
ENMAX | 5.1TR (ENMAX 5) | 2020-06-15 08:00 | 2020-06-25 18:30 | N | N | plastibeton tray replacement | Transformer |  | Plastibeton Tray Replacement at 5 Sub | For Information Only
ATCO | 848s 606T (848s Ruth Lake) | 2020-06-15 08:00 | 2020-06-19 17:00 | N | N | install bird proofing | Transformer |  | Install bird proofing on 500BS1, 606T, 25KV line disconnects | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2020-06-15 08:00 | 2020-06-18 16:00 | N | N | power factor test, maintenance, gas relay testing, check reversing switch, oil sampling MT, TC, bushing | Transformer |  | Power factor test transformer, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil sampling MT, TC, Bushing | For Information Only
ENMAX | 13.1TR (ENMAX 13) | 2020-06-15 08:00 | 2020-07-03 16:00 | N | N | Arc Flash Mitigation Project: protection outage and MV cable swap | Transformer | 13.1TR (ENMAX 13) |  | For Information Only
ENMAX | 21.1TR (ENMAX 21) | 2020-06-15 08:00 | 2020-06-19 16:00 | N | N | reinhausen tapchanger maintenance, oil sample MT | Transformer | 21.1TR (ENMAX 21) | Reinhausen Tapchanger Maintenance. Oil sample MT. TC | For Information Only
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2020-06-15 08:00 | 2020-06-18 17:00 | N | N | changing cross-arms and insulators | Line | 7L16 (766s Nevis - 948s Heatburg) | Changing Cross-arms & insulators | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 2.3TR (ENMAX 2) | 2020-06-15 08:00 | 2020-06-18 16:00 | N | N | power factor test, maintenance, gas relay testing, check reversing switch, oil sampling MT, TC, bushing | Transformer |  | Power factor test transformer. Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Check reversing switch. Oil sampling MT, TC | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-06-15 08:00 | 2020-06-15 17:00 | Y | Y | hazard tree removals - 10-01 to 17-01 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 510s ACF21 (510s Sunnybrook) | 2020-06-15 09:30 | 2020-06-18 16:30 | N | Y | annual inspection & maintenance | Shunts | 510s ACF21 (510s Sunnybrook) | Annual inspection & maintenance | 500 kV
ATCO | 7L73 (730s Rycroft - 800s Friedenstal), 829S Boucher Creek | 2020-06-15 09:30 | 2020-06-15 16:30 | N | Y | remove PTs and replace conductor on bypass switch | Line, Station | 7L73 (730s Rycroft - 800s Friedenstal) | Will be taking an entire line and station outage to 7L73, 829S and 750S mobile sub #1. 829S is supplying power to the CNRL plant before the outage, but Mobile sub 750S will be supplying power to the plant after the outage so we can complete upgrade construction. The following work will take place during this outage: Remove 144kV Line PT's 7L73PT2 and 7L73PT3. These will no longer be needed because auto Sectionalizing scheme is being demoed. Replace conductor on 13.8kV bypass switch 401X. It is in rough shape and we will use this opportunity to make it right. Cut open jumpers J3 and J4 for substation outage. Mobile substation will be supplying power to the CNRL plant after this outage. Attach mobile substation 750S 13.8kV hot taps to outgoing distribution line. The following work will take place during this outage: Remove 144kV Line PT's 7L73PT2 and 7L73PT3. These will no longer be needed because auto Sectionalizing scheme is being demoed. Replace conductor on 13.8kV bypass switch 401X. It is in rough shape and we will use this opportunity to make it right. Cut open jumpers J3 and J4 for substation outage. Mobile substation will be supplying power to the CNRL plant after this outage. Attach mobile substation 750S 13.8kV hot taps to outgoing distribution line. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 384s 834 (384s Keystone), 834L (320p Keephills - 384s Keystone) | 2020-06-15 10:00 | 2020-06-15 16:30 | N | N | breaker maintenance and testing | Circuit Breaker, Line | 834L (320p Keephills - 384s Keystone) | Breaker Maintenance, and 1st trip, 1st Close, 2nd Trip | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-06-15 10:00 | 2020-06-18 15:00 | N | Y | crossarm change out | Line | 7L40 (733s Simonette - 813s Little Smoky) | XARM change out | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 890L (58s Edson - 207s Pinedale) | 2020-06-15 10:00 | 2020-06-19 16:00 | N | N | connect and commission new protections to existing equipment | Line | 890L (58s Edson - 207s Pinedale) | Connect and commission new C60, L8/A21 & L8/B21 protections to existing equipment. Move CTV4 distribution to new building distribution. Commission breaker fail trips to adjacent breakers, card replacement and settings changes on the 890L protection at 207s. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2020-06-15 10:30 | 2020-06-17 17:30 | N | Y | breaker maintenance | Line | 23.80L (74s Janet - ENMAX 23) | 138kV break maintenance | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 694L (54s Fort Saskatchewan - 422s Westwood) | 2020-06-15 12:00 | 2020-06-15 16:00 | N | N | maintenance on 694L str 2 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 157s T1 (157s Lac La Biche) | 2020-06-15 12:00 | 2020-06-18 18:30 | N | N | replace LAs on T1 HV, LV and 305LN, and replace 157s8 | Transformer |  | Replace LAs on T1 HV, LV and 305LN, and replace 157s8 | For Information Only
ATCO | 829s 701T (829s Boucher Creek) | 2020-06-15 16:30 | 2020-07-15 16:30 | N | N | substation outage | Transformer |  | 829S Boucher Creek Substation Outage - Load fed from 750S Mobile for duration of the work. May have intermittent interruptions to SCADA Visibility & Control < 5 min as new configurations are downloaded to the RTU | For Information Only, Pre-Condition
EPCOR | 657s SU2403 (657s Summerside), 657s SU2404 (657s Summerside), 803s L2403 (803s Lambton), 803s L2404 (803s Lambton), 1058L (657s Summerside - 803s Lambton) | 2020-06-16 07:00 | 2020-06-16 17:00 | N | Y | doble | Circuit Breaker, Line | 1058L (657s Summerside - 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 28.1TR (ENMAX 28) | 2020-06-16 08:00 | 2020-06-16 12:00 | N | N | repair an arc vent | Transformer |  | Arc Flash Mitigation Project. ABB to repair an arc vent | For Information Only
Syncrude | Mildred T17 (Syncrude Mildred Lake) | 2020-06-16 08:00 | 2020-07-02 20:00 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 809L (320p Keephills - 510s Sunnybrook) | 2020-06-16 08:00 | 2020-06-18 18:00 | N | Y | urgent replace 809L68 with new structure to mitigate line clearance violation | Line |  | Urgent outage to replace 809L68 with new structure to mitigate line clearance violation. -Relocate 809L181 anchor and guy wire that has clearance violation to 834L. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 409s T1 (409s Shell Scotford) | 2020-06-16 08:00 | 2020-06-16 17:30 | N | N | urgent - replace CT | Transformer |  | replace CT's associated with T1 | For Information Only
ALTALINK | 378s 152 (378s Shell Caroline), 378s 252 (378s Shell Caroline), 848L (378s Shell Caroline - 848L490W) | 2020-06-16 08:00 | 2020-06-17 17:00 | N | Y | implement/function sync check changes on M388/389 relays for 378s152 and 378s252. | Circuit Breaker, Line | 848L (378s Shell Caroline - 848L490W) | Outage on 848L to implement/function sync check changes on M388/389 relays for 378s152 and 378s252. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 431s T1 (431s Hussar) | 2020-06-16 08:15 | 2020-06-18 17:15 | N | N | transformer maintenance | Transformer | 431s T1 (431s Hussar) | TX maintenance, doble. C/S maintenance (s295). Replace cracked CT on CT3 | For Information Only
ATCO | 7L22 (790s Poplar Hill - 7L22D3), 790s 702 (790s Poplar Hill) | 2020-06-16 09:00 | 2020-06-16 17:00 | N | Y | 790S 702 breaker SF6 HPL complete testing | Line, Circuit Breaker | 7L22 (790s Poplar Hill - 7L22D3) | 790S 702 BREAKER SF6 HPL COMPLETE TESTING 7L22 OPEN-ENDED | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 190L (17s Benalto - 320p Keephills), 320p 552 (320p Keephills), 320p 652 (320p Keephills) | 2020-06-16 09:00 | 2020-06-17 17:00 | N | Y | 320p552 & 320p652 Low Gas maintenance | Line, Circuit Breaker | 190L (17s Benalto - 320p Keephills) | 320p552 & 320p652 Low Gas maintenance. Adjust 320p5A. | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 102s SVC (102s Langdon) | 2020-06-16 09:00 | 2020-06-16 16:00 | N | Y | cooling system maintenance | Shunts | 102s SVC (102s Langdon) | Replace 1 phase, 600V/230V TX for SVC cooling system. No isolation required, but SVC Cooling system will need to come offline, requiring a STOP command | 240 kV
ALTALINK | 267s Killarney Lake 138kV bus, 267s C1 (267s Killarney Lake), 267s C2 (267s Killarney Lake), 267s C3 (267s Killarney Lake) | 2020-06-16 12:30 | 2020-06-17 15:30 | N | N | urgent 138kV bus repair | Bus, Shunts |  |  | Pre-Condition
ALTALINK | 767L (320p Keephills - 767AL) | 2020-06-17 08:00 | 2020-06-17 18:00 | N | N | urgent outage to relocate 767L184 anchor and guy wire that has clearance violation to 809L | Line |  |  | Affects Cranking Path
Medicine Hat | MH69S-1 Power Plant Switchyard RTU/SCADA | 2020-06-17 08:00 | 2020-06-17 10:00 | N | N | reboot control system communication switch number 11 | Terminal Equipment |  |  | Affects Visibility
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2020-06-17 08:00 | 2020-06-17 17:00 | N | N | doble at Woodcroft | Line | 72JW19 (805s Jasper - Woodcroft) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 850s 702T (850s Rainbow Cogen) | 2020-06-17 09:00 | 2020-06-18 16:00 | N | Y | maintenance | Transformer |  | Heartland Generation is planning to complete maintenance on the 13.8kV Bus at Rainbow Lake Unit 5. | Restricts Generation
ALTALINK | 521AL (867s Sundance Blow-Down - 521L) | 2020-06-17 10:00 | 2020-06-18 18:00 | N | N | maintenance on structures 56 and 58 | Line
ATCO | 741s 701T (741s Fox Creek) | 2020-06-17 10:00 | 2020-06-18 16:00 | N | N | close valves and drain leak | Transformer |  | 741S 701T Rad Leak Close valves and drain leaking rad Transformer out of service. Load transferred to 702T
ALTALINK | 77s 54 (77s Sagitawah) | 2020-06-17 13:30 | 2020-06-17 18:30 | N | Y | test trips from 96/1752 (77s51) protection | Circuit Breaker | 77s 54 (77s Sagitawah) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 854L (39s Bickerdike - 854AL) | 2020-06-18 07:30 | 2020-06-23 17:30 | N | N | structures replacement | Line |  | Replacing structures 231 & 232, adding a new structure between structures 237 & 238, adjusting sag at structure 238. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 409s T2 (409s Shell Scotford) | 2020-06-18 08:00 | 2020-06-18 17:30 | N | N | replace CT's | Transformer |  | Replace CT's associated with T2 | For Information Only
ALTALINK | 151s 765W (151s Strathmore), 765L (151s Strathmore - 419s Chestermere) | 2020-06-18 08:00 | 2020-06-19 17:00 | N | N | relay changes | Circuit Breaker, Line | 765L (151s Strathmore - 419s Chestermere) | Outage on 151s765W to implement/function sync check changes on M388/389 relay. | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 63s 427 (63s Red Deer), 427L (63s Red Deer - 247s Piper Creek) | 2020-06-18 08:30 | 2020-06-18 12:30 | N | N | breaker maintenance | Circuit Breaker, Line | 63s 427 (63s Red Deer) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 7L50 (757s Battle River - 7L50D1) | 2020-06-18 09:00 | 2020-06-18 17:00 | N | Y | conductor check | Line | 7L50 (757s Battle River - 7L50D1) | For a Conductor Check | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 491L (252s Jarrow - 7L50) | 2020-06-18 09:30 | 2020-06-18 16:00 | N | N | add ground point to VT3 junction box | Line | 491L (252s Jarrow - 7L50)
ALTALINK | 253s C1 (253s Blackie) | 2020-06-18 10:30 | 2020-06-18 17:30 | N | N | breaker maintenance | Shunts |  | 138kV C/S Maintenance | Pre-Condition
ALTALINK | 428s 886N (428s Namaka), 886L (428s Namaka - 431s Hussar) | 2020-06-19 06:00 | 2020-06-19 17:00 | N | N | protection upgrades | Circuit Breaker, Line |  |  | For Information Only, Pre-Condition
KP | PMB1 Keyera West Pembina Gas Turbine | 2020-06-19 08:00 | 2020-08-28 16:00 | N | N | P2012. 12 MW. ISD August 21, 2020. | Unit
ALTALINK | 58s 35 (58s Edson), 58s C1 (58s Edson) | 2020-06-19 08:30 | 2020-06-19 09:15 | N | N | perform a trip test from 452 BF protection to 138kV breaker 1352 (58s35) | Circuit Breaker, Shunts |  | perform a trip test from 452 BF protection to 138kV breaker 1352 (58s35). | For Information Only, Pre-Condition
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2020-06-19 09:45 | 2020-06-19 10:30 | N | N | Perform a trip test from 452 BF protection to 138kV breaker 352 (58s202X). | Line |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2020-06-19 11:00 | 2020-06-19 11:45 | N | N | perform a trip test from 452 BF protection to 138kV breaker 552 (58s740X) | Line | 740L (39s Bickerdike - 58s Edson) |  | For Information Only
ALTALINK | 671L (39s Bickerdike - 58s Edson) | 2020-06-19 12:15 | 2020-06-19 13:00 | N | N | perform a trip test from 452 BF protection to 138kV breaker 1052 (58s671) | Line | 671L (39s Bickerdike - 58s Edson) |  | For Information Only
ALTALINK | 58s T1 (58s Edson) | 2020-06-20 07:30 | 2020-06-20 16:00 | N | N | perform trip test from 452 BF protection | Transformer |  | Perform a trip test from 452 BF protection to 25kV breakers 1152 (58s334X), and 1252 (58s377E), Install new PT1 Junction box. | For Information Only
ENMAX, ALTALINK | 162s 138-RB81 (162s Beddington), 162s 138-RB82 (162s Beddington), 771L (162s Beddington - ENMAX 47), 47.1TR (ENMAX 47), 47.2TR (ENMAX 47) | 2020-06-20 08:00 | 2020-06-21 18:00 | N | Y | spring substation washing | Circuit Breaker, Line, Transformer |  | Spring Substation Washing. 47s SW86, SW81. Oil sample 47.2TC. HV SW maint SW84, SW85, MD-771L@162sub. Backfeed sstr from 25kV bus. | Contingency Requires Mitigation
ATCO | 826s 904 (826s Marguerite Lake) | 2020-06-20 08:00 | 2020-06-20 12:00 | N | Y | test new breaker fail trips and block closes from new 50BF/701 to breaker 904 | Circuit Breaker |  | To test new Breaker fail trips and block closes from new 50BF/701 to breaker 904 | 240 kV, Contingency Requires Mitigation
ATCO | 826s 908 (826s Marguerite Lake) | 2020-06-20 12:30 | 2020-06-20 16:00 | N | Y | test new breaker fail trips and block closes from new 50BF/701 to breaker 908 | Circuit Breaker |  | To test new Breaker fail trips and block closes from new 50BF/701 to breaker 908 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALPAC | 282s Grassland (Alpac) RTU/SCADA | 2020-06-20 13:00 | 2020-06-20 14:00 | N | N | internet firewall upgrade | Terminal Equipment |  |  | For Information Only
ATCO | 826s 903 (826s Marguerite Lake) | 2020-06-21 08:00 | 2020-06-21 12:00 | N | Y | test the new breaker fail trips from new 50BF/704 protection relay on BKR 903 | Circuit Breaker |  | Test the new Breaker Fail trips from new 50BF/704 protection relay on BKR 903 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 826s 907 (826s Marguerite Lake) | 2020-06-21 12:30 | 2020-06-21 16:00 | N | Y | test the new breaker fail trips from new 50BF/704 protection relay on BKR 907 | Circuit Breaker |  | Test the new Breaker Fail trips from new 50BF/704 protection relay on BKR 907 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 10.2TR (ENMAX 10) | 2020-06-22 07:00 | 2020-06-23 18:30 | N | N | neutral reactor installation | Transformer | 10.2TR (ENMAX 10) |  | For Information Only
ATCO | 2075s 902T (2075s Newell) | 2020-06-22 07:00 | 2020-06-26 17:30 | N | Y | SVC transformer maintenance | Transformer | 2075s 902T (2075s Newell) | SVC TRANSFORMER MAINTENANCE @ NEWELL 2075S 902T Testing SVC2 OUT OF SERVICE. SVC1 WILL STILL BE AVAILABLE | 240 kV, Pre-Condition
EPCOR | At-Plastics-4Rs | 2020-06-22 07:00 | 2020-06-26 17:00 | N | N | doble | Station | AT-PLASTICS-4RS |  | For Information Only
EPCOR | Riverview T1 (EPCOR Riverview) | 2020-06-22 07:00 | 2020-06-23 17:00 | N | Y | repair oil leak | Transformer |  |  | 240 kV, For Information Only
EPCOR | Woodcroft T3 (Woodcroft) | 2020-06-22 07:00 | 2020-06-26 17:00 | N | N | transformer secondary retrofit and disconnect | Transformer | Woodcroft T3 (Woodcroft) |  | For Information Only
EPCOR | Hardisty H722 (Hardisty Epcor) | 2020-06-22 07:00 | 2020-06-26 17:00 | N | N | breaker fail cutover | Circuit Breaker | Hardisty H722 (Hardisty Epcor) |  | Creates Radial Feeds, Firm Load Loss
Syncrude | Mildred T5 (Syncrude Mildred Lake) | 2020-06-22 08:00 | 2020-07-22 19:00 | N | Y | maintenance | Transformer |  | T5 Transformer (72/13.8kV) - Plant 31 Powerhouse | Restricts Generation
ATCO | 7L587 (822s Wolf Lake - 826s Marguerite Lake) | 2020-06-22 08:00 | 2020-07-05 16:00 | N | Y | P&C upgrade | Line | 7L587 (826s Marguerite Lake - 822s Wolf Lake) | 240/144kV Breaker Fail Protection (OOS for duration of outages) 826S Marguerite P&C Upgrade | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 16.2TR (ENMAX 16) | 2020-06-22 08:00 | 2020-07-08 16:00 | N | N | arc flash mitigation project | Transformer |  | Arc Flash Mitigation Project. Protection outage and MV cable swap. | For Information Only
ENMAX | 21.2TR (ENMAX 21) | 2020-06-22 08:00 | 2020-06-26 16:00 | N | N | reinhausen tapchanger maintenance | Transformer | 21.2TR (ENMAX 21) | reinhausen tapchanger maintenance. Oil sampling MT, TC | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2020-06-22 08:00 | 2020-06-25 16:00 | N | N | transformer test and maintenance | Transformer |  | power factor test transformer, transformer maintenance, Gas Relay Testing. Check reversing switch. Oil sampling TC, Bushing | For Information Only
ENMAX | 2.4TR (ENMAX 2) | 2020-06-22 08:00 | 2020-06-25 16:00 | N | N | transformer test and maintenance | Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil sampling Bushing | For Information Only
ATCOP | RL1 Rainbow Lake #1 | 2020-06-22 08:00 | 2020-06-25 16:00 | N | N | ATCO work | Unit
SUNCOR | 29EDD-71 752-4641 (29EDD-71) | 2020-06-22 08:00 | 2020-06-30 07:56 | N | N | emergency outage | Circuit Breaker
ATCO | 2009s 703 (2009s Willow Lake) | 2020-06-22 08:00 | 2020-06-23 12:00 | N | N | PRC-005 - trip coil testing | Circuit Breaker |  | PRC-005 - TRIP COIL TESTING on 703 BKR | Creates Radial Feeds, Firm Load Loss
ATCO | 850S Rainbow Cogen | 2020-06-22 08:00 | 2020-06-25 16:00 | N | Y | maintenance | Station |  | transfer load to RB5, for RB4 isolation June 25 expand GOI to include 705A @ 791S and 702TD, 701PT @ 850S Units 4 & 5 will be disconnected from the BES Grid on June 22 | Restricts Generation
ENMAX | 41.1C (ENMAX 41) | 2020-06-22 08:00 | 2020-06-25 16:00 | N | N | maintenance | Shunts |  |  | Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1252 (29EDD-1 Millennium) | 2020-06-22 08:00 | 2020-06-22 20:00 | N | N | install bird interaction deterrants | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L16 (766s Nevis - 948s Heatburg) | 2020-06-22 08:00 | 2020-06-25 17:00 | N | N | Changing Cross-arms & insulators | Line | 7L16 (766s Nevis - 948s Heatburg) | Changing Cross-arms & insulators | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 796s 701T (796s Nipisi) | 2020-06-22 08:30 | 2020-06-25 17:00 | N | N | test transformer and repair leaks, adjust 501TD | Transformer |  | Test Transformer and Repair Leaks, adjust 501TD, Load carried on 702T | For Information Only
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2020-06-22 09:00 | 2020-07-24 18:00 | N | Y | OPGW install | Line | 180L (255s Vulcan - 928s East Stavely) | OPGW install for the Claresholm project. 180L ( Str range 1- 204)#####################adding steps for cutting the new customer###### sub##################################################################### | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 905L (19s Wabamun - 37s North Calder), 37s 76 (37s North Calder), 37s 82 (37s North Calder) | 2020-06-22 09:00 | 2020-06-25 18:00 | N | Y | replacing PT | Line, Circuit Breaker | 905L (19s Wabamun - 37s North Calder) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 58s T2 (58s Edson) | 2020-06-22 09:30 | 2020-06-26 16:00 | N | N | protection upgrades, 289 and 489 MOD control upgrades and relocations | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK, REDDEER | 425L (194s South Red Deer - 217s North Red Deer), 194s T1 (194s South Red Deer) | 2020-06-22 10:00 | 2020-06-24 18:30 | N | N | 138 kV CT removal on transformer T1 high side | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-06-22 10:00 | 2020-06-25 15:00 | N | Y | XARM change out | Line | 7L40 (733s Simonette - 813s Little Smoky) | XARM change out | Contingency Requires Mitigation, Creates Radial Feeds, Over/Under Voltage, Overload, Affects Cranking Path
ALTALINK | 511s 2152 (511s Crossings), 511s ACF21 (511s Crossings) | 2020-06-22 11:00 | 2020-06-25 16:30 | N | Y | annual inspection & maintenance | Circuit Breaker, Shunts | 511s 2152 (511s Crossings) |  | 240 kV, For Information Only
ALTALINK | 405s 796 (405s Waupisoo), 796L (405s Waupisoo - 796AL), 796L (282s Grassland (Alpac) - 796AL), 796AL (242s Flat Lake - 796L) | 2020-06-22 11:30 | 2020-06-22 17:00 | N | Y | heater repair | Circuit Breaker, Line | 796L (405s Waupisoo - 796AL),796AL (242s Flat Lake - 796L),796L (282s Grassland (Alpac) - 796AL) |  | Restricts Generation
ALTALINK | 39s 152 (39s Bickerdike) | 2020-06-22 11:30 | 2020-06-22 17:00 | N | N | breaker maintenance | Circuit Breaker |  | 39s152 Breaker maintenance and 1st trip, 1st Close, 2nd Trip. | Contingency Requires Mitigation
ALTALINK | 68s 152 (68s Amoco Willesden Green), 68s T1 (68s Willesden Green) | 2020-06-22 12:30 | 2020-06-24 17:30 | N | Y | maintenance and doble | Circuit Breaker, Transformer |  | Maintenance and Doble and 68s152 1st trip, 1st Close , 2nd Trip. also Maintenance on 68s152 and and gauge cover replacement. | 240 kV
ALTALINK | 394s T1 (394s Empress) | 2020-06-22 13:30 | 2020-06-26 14:30 | N | N | bushing replacement, maintenance, doble | Transformer |  |  | For Information Only
SUNCOR | 29EDD-1 29EDD1s1352 (29EDD-1 Millennium) | 2020-06-23 08:00 | 2020-06-23 20:00 | N | N | install bird interaction deterrants | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 757s 912T (757s Battle River), 9L80 (755s Cordel - 757s Battle River) | 2020-06-23 08:00 | 2020-07-01 15:20 | N | Y | add 59N protection to 912T tertiary winding | Transformer, Line |  | Add 59N Protection to 912T Tertiary Winding, 9L80 will be out of service | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 848s 901T (848s Ruth Lake) | 2020-06-23 08:00 | 2020-06-29 08:59 | N | Y | oil reclaiming | Transformer | 848s 901T (848s Ruth Lake) | 901T Oil Reclaiming at 848S Ruth Lake | 240 kV, Pre-Condition
ENMAX | 16.60L (ENMAX 16 - ENMAX 34), 34.2TR (ENMAX 34) | 2020-06-23 08:00 | 2020-06-23 12:00 | N | N | substation washing, check reversing switch | Line, Transformer |  | Substation Washing. Check reversing switch. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Aurora T4 (Aurora) | 2020-06-23 08:00 | 2020-06-25 20:00 | N | Y | relay work | Transformer |  |  | 240 kV
TRANSALTA | 239s 138CB1 (239s Castle River) | 2020-06-23 08:00 | 2020-06-23 18:00 | N | Y | maintenance | Circuit Breaker | 239s 138CB1 (239s Castle River) |  | Restricts Generation
ALTALINK | 730L (285s East Camrose - 732L), 285s 730N (285s East Camrose) | 2020-06-23 08:00 | 2020-06-26 18:00 | N | N | component replacements structures range 64-196 | Line, Circuit Breaker |  | Component Replacements Structures Range 64-196 South Section of 730L | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 5.5TR (ENMAX 5) | 2020-06-23 08:00 | 2020-06-26 18:00 | N | N | plastibeton tray replacement | Transformer |  | plastibeton tray replacement at 5 Sub | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2020-06-23 08:30 | 2020-06-23 12:30 | N | N | breaker maintenance and testing | Line | 633L (56s Boyle - 405s Waupisoo) | Maintenance on 405s633 breaker. 1st trip testing. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 39s 452 (39s Bickerdike) | 2020-06-23 08:30 | 2020-06-24 17:30 | N | N | breaker maintenance testing | Circuit Breaker |  | 39s452 Breaker maintenance and 1st trip, 1st Close, 2nd Trip. | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 320p 1352 (320p Keephills), 1045L (310p Sundance - 320p Keephills - 805s Jasper), 805s J2406 (805s Jasper), 805s J2407 (805s Jasper) | 2020-06-23 09:00 | 2020-06-24 14:00 | N | Y | sync check modifications, recommissioning circuits for proper functionality | Circuit Breaker, Line | 1045AL (320p Keephills - 1045L) | 320p1352 sync check modifications. Recommissioning circuits for proper functionality. | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
BCH, ALTALINK | 1L274 (48s Pocaterra - Britt Creek), 48s 887X (48s Pocaterra) | 2020-06-23 09:00 | 2020-06-23 17:00 | Y | Y | urgent - BCH hazard tree removals | Line, Circuit Breaker |  | WebOMS ID: 8763691 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 103s 352 (103s Goose Lake) | 2020-06-23 09:30 | 2020-06-23 17:30 | N | Y | top up gas | Circuit Breaker | 103s 352 (103s Goose Lake) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 21.61L (ENMAX 21 - ENMAX 34), 34.1TR (ENMAX 34) | 2020-06-23 12:00 | 2020-06-23 18:00 | N | N | substation washing | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 728L (353s Plamondon - 405s Waupisoo) | 2020-06-23 12:30 | 2020-06-23 16:30 | N | N | breaker maintenance and testing | Line | 728L (353s Plamondon - 405s Waupisoo) | Maintenance on 405s728 breaker. 1st trip testing. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ATCO | 2009s 704 (2009s Willow Lake) | 2020-06-23 12:30 | 2020-06-23 15:00 | N | N | PRC-005 - trip coil testing on 704 breaker | Circuit Breaker |  | PRC-005 - TRIP COIL TESTING on 704 BKR | Pre-Condition
TRANSALTA | 239sT1 (239s Castle River) | 2020-06-23 18:00 | 2020-06-24 18:00 | N | Y | maintenance | Transformer | 239sT1 (239s Castle River) |  | Restricts Generation
EPCOR | Riverview T2 (EPCOR Riverview) | 2020-06-24 07:00 | 2020-06-25 17:00 | N | Y | repair oil leak | Transformer |  |  | 240 kV, For Information Only, Pre-Condition
ENMAX | 41.84L (ENMAX 41 - ENMAX 54), 54.81L (ENMAX 54 - ENMAX 65), 54.1TR (ENMAX 54) | 2020-06-24 08:00 | 2020-06-24 18:00 | N | N | substation washing | Line, Transformer | 41.84L (ENMAX 41 - ENMAX 54) 54.81L (ENMAX 54 - ENMAX 65) 54.1TR (ENMAX 54) |  | For Information Only, Pre-Condition
ALTALINK | 1053L (132s Ware Junction - 324s Cassils), 132s 12 (132s Ware Junction), 132s 15 (132s Ware Junction) | 2020-06-24 08:00 | 2020-06-25 17:00 | N | Y | implement/function sync check changes on M388/389 relays for 132s12 breaker | Line, Circuit Breaker | 1053L (132s Ware Junction - 324s Cassils) |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 103s 252 (103s Goose Lake) | 2020-06-24 08:00 | 2020-06-24 17:30 | N | Y | top up gas | Circuit Breaker | 103s 252 (103s Goose Lake) |  | 240 kV, For Information Only, Pre-Condition
SUNCOR | 29EDD-1 29EDD1S1452 (29EDD-1 Millennium) | 2020-06-24 08:00 | 2020-06-24 20:00 | N | N | install bird interaction deterrants | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 913L (69s North Barrhead - 338s Cherhill) | 2020-06-24 08:00 | 2020-06-27 17:00 | N | Y | line clearance mitigation: work includes adjusting sag between structures 58B and 63 | Line | 913L (69s North Barrhead - 338s Cherhill) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 157s23 (157s Lac La Biche), 157s C1 (157s Lac La Biche) | 2020-06-24 08:30 | 2020-06-24 16:00 | N | N | PRC5 maintenance: 1st trip | Switch, Shunts |  |  | Pre-Condition
ALTALINK | 632PS (632s Russell) | 2020-06-24 08:30 | 2020-06-24 15:30 | N | Y | test transformer controller | Transformer | 632PS (632s Russell) |  | Pre-Condition
ALTALINK | 77s 51 (77s Sagitawah) | 2020-06-24 08:30 | 2020-06-24 17:30 | N | Y | urgent outage to replace cable for bus differential protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 7L78 (785s Judy Creek - 851s Morse River) | 2020-06-24 09:00 | 2020-06-24 15:00 | N | N | pole replacement | Line | 7L78 (785s Judy Creek - 851s Morse River) | POLE REPLACEMENT | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2020-06-24 11:00 | 2020-06-24 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | Rossdale RR729 (Rossdale) | 2020-06-25 07:00 | 2020-06-25 17:00 | N | N | isolation for EPCOR switching school | Circuit Breaker |  | Outage required to provide isolation for EPCOR switching school | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 14s T1 (14s Devon) | 2020-06-25 07:00 | 2020-06-25 18:00 | N | N | separating out alarms in transformer | Transformer |  |  | For Information Only
EPCOR | 987s T2 (987s Clover Bar) | 2020-06-25 07:00 | 2020-06-25 17:00 | N | Y | line maintenance | Transformer |  | Line Maintenance | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, ATCOP | RB5 Rainbow #5 | 2020-06-25 08:00 | 2020-06-25 16:00 | N | N | ATCO work | Unit
SUNCOR | 29EDD-1 29EDD1s1152 (29EDD-1 Millennium) | 2020-06-25 08:00 | 2020-06-25 20:00 | N | N | install bird interaction deterrants | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 194s 426 (194s South Red deer), 426L (63s Red Deer - 194s South Red Deer) | 2020-06-25 08:00 | 2020-06-25 12:00 | N | N | maintenance | Circuit Breaker, Line | 426L (63s Red Deer - 194s South Red Deer) | Breaker outage to replace DC JB6 which feeds breaker 152 (194s426). | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 103s 652 (103s Goose Lake) | 2020-06-25 08:00 | 2020-06-25 17:30 | N | Y | top up gas | Circuit Breaker |  | top up gas | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX, ALTALINK | 693L (42s Sarcee - ENMAX 10), 10.2TR (ENMAX 10) | 2020-06-25 08:00 | 2020-06-25 12:00 | N | Y | substation washing and check transformer reversing switch | Line, Transformer | 693L (42s Sarcee - ENMAX 10) 10.2TR (ENMAX 10) | Substation Washing. Check reversing switch 10.2TR | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 405s C1 - GOI | 2020-06-25 08:30 | 2020-06-25 15:30 | N | N | breaker maintenance | Terminal Equipment |  | Maintenance on 405s17 breaker | Impacts RAS, Pre-Condition
ALTALINK | 39s 1052 (39s Bickerdike) | 2020-06-25 08:30 | 2020-06-25 17:00 | N | Y | breaker maintenance | Circuit Breaker |  | 39s1052 Breaker maintenance and 1st trip, 1st Close, 2nd Trip. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 250p 22 (250p Bighorn Plant) | 2020-06-25 09:00 | 2020-06-25 13:00 | N | Y | maintenance | Switch |  | Brushgear | Restricts Generation
ENMAX, ALTALINK | 832L (ENMAX 10 - ENMAX 12), 10.1TR (ENMAX 10) | 2020-06-25 12:00 | 2020-06-25 18:00 | N | Y | Substation washing & check reversing switch 10.1TR | Line, Transformer | 832L (ENMAX 10 - ENMAX 12) 10.1TR (ENMAX 10) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
CAPPOWERLP | ENC3 Cloverbar #3 | 2020-06-25 13:00 | 2020-06-25 15:00 | N | N | 72CN10 outage | Unit
EPCOR | 72CN10 (987s Clover Bar - Namao) | 2020-06-25 13:00 | 2020-06-25 15:00 | N | Y | urgent closing breaker CC13 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 194s 425 (194s South Red deer), 425L (194s South Red Deer - 217s North Red Deer) | 2020-06-25 13:00 | 2020-06-25 17:00 | N | N | breaker outage to replace DC JB6 which feeds breaker 252 (194s425) | Circuit Breaker, Line | 425L (194s South Red Deer - 217s North Red Deer) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 58s C1 (58s Edson) | 2020-06-25 13:30 | 2020-06-25 14:30 | N | N | perform a trip test from T2 | Shunts |  | Protection to 138kV breaker 1352 (58s35). Demo existing A86/T2, B86/T2 and 289 blocking circuits. Tie in A86/T2, B86/T2 and 289 blocking contacts to 1352 (58s35) close circuit. Preform functional blocking test of breaker close. | Pre-Condition
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2020-06-25 15:00 | 2020-06-25 15:45 | N | N | perform a trip test from T2 protections to 138kV breaker 352 (58s202X) | Line |  |  | Pre-Condition, Affects Cranking Path
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2020-06-25 16:15 | 2020-06-25 17:00 | N | N | perform a trip test from T2 protections to 138kV breaker 552 (58s740X) | Line | 740L (39s Bickerdike - 58s Edson). Demo existing A86/T2, B86/T2 and 289 blocking circuits. Tie in A86/T2, B86/T2 and 289 blocking contacts to 552 (58s740X) close circuit. Preform functional blocking test of breaker close.Scheduled By: Shannon Bouchard Issue to: Matthew Cowan Contact #: 780.224.2728 |  | Pre-Condition
ALTALINK | 671L (39s Bickerdike - 58s Edson) | 2020-06-25 17:30 | 2020-06-25 18:15 | N | N | perform a trip test from T2 protections to 138kV breaker 1052 (58s671) | Line | 671L (39s Bickerdike - 58s Edson). Demo existing A86/T2, B86/T2 and 289 blocking circuits. Tie in A86/T2, B86/T2 and 289 blocking contacts to 1052 (58s671) close circuit. Perform functional blocking test of breaker close. |  | Pre-Condition
ALTALINK, EPCOR | 1059L (38s East Edmonton - 1059AL), 1059L (803s Lambton - 1059AL) | 2020-06-26 07:00 | 2020-07-06 17:00 | N | Y | line maintenance | Line | 1059L (803s Lambton - 1059AL tap), 1059L (38s East Edmonton - 1059AL tap) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 739L (14s Devon - 155s Blackmud) | 2020-06-26 07:00 | 2020-06-26 18:00 | N | N | add remote recloser blocking functionality | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
MONTANA | Great Falls Switchyard (NorthWestern Energy) - Marias (MATL) | 2020-06-26 07:00 | 2020-06-26 18:00 | N | Y | urgent restore damaged fiber | Line | OC to follow up with RTM Kevin S on what to put for manual override in MARGO next time. |  | 240 kV, Limits ATC
ALTALINK, EPCOR | 71s 1252 (71s Lamoureux), 71s 1352 (71s Lamoureux), 921L (71s Lamoureux - 987s Clover Bar) | 2020-06-26 08:00 | 2020-06-30 17:30 | N | Y | replace 71s921X | Circuit Breaker, Line |  | 921L was forced out of service on May 14, 2020. 71s921X needs to be replaced | 240 kV, Contingency Requires Mitigation, Pre-Condition,Affects Cranking Path
ENMAX | 7.84L (ENMAX 7 - ENMAX 36) | 2020-06-26 08:00 | 2020-07-04 16:00 | N | N | west Calgary ring road project -relocate a portion of 7.84L | Line | 7.84L (ENMAX 7 - ENMAX 36) | West Calgary Ring Road Project. ENMAX to relocate a portion of 7.84L line. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1852 (29EDD-1 Millennium) | 2020-06-26 08:00 | 2020-06-27 20:00 | N | N | install bird interaction deterrants | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T3 (370s North Lethbridge) | 2020-06-26 08:30 | 2020-06-26 17:30 | N | Y | urgent trouble shoot DC ground | Transformer | 370s T3 (370s North Lethbridge) | trouble shoot DC ground on T3 to prevent false tripping condition | 240 kV, Pre-Condition
EPCOR | 72RG1 (Garneau - Rossdale) | 2020-06-27 07:00 | 2020-06-28 17:00 | N | N | surge arrestor replacement | Line |  | The arrestors will be replaced: 72RG1 72SA271, 72SA272, 72SA273 at Rossdale Substation | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2020-06-27 08:00 | 2020-06-27 10:00 | N | N | arc flash mitigation | Line |  | Arc Flash Mitigation Project. Panel wiring changes. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2020-06-27 10:00 | 2020-06-27 12:00 | N | N | arc flash mitigation | Line |  | Arc Flash Mitigation Project. Panel wiring changes. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.63L (ENMAX 16 - ENMAX 36), 36.5TR (ENMAX 36) | 2020-06-27 12:00 | 2020-06-27 14:00 | N | N | arc flash mitigation | Line, Transformer |  | Arc Flash Mitigation Project. Panel wiring changes. | Pre-Condition
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2020-06-27 14:00 | 2020-06-27 16:00 | N | N | arc flash mitigation | Line |  | Arc Flash Mitigation Project. Panel wiring changes. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-1 29EDD1s1752 (29EDD-1 Millennium) | 2020-06-28 08:00 | 2020-06-29 20:00 | N | N | install bird interaction deterrants | Circuit Breaker |  |  | Pre-Condition
ALTALINK | 14s T3 (14s Devon) | 2020-06-29 07:00 | 2020-06-29 18:00 | N | N | separating out alarms in transformer | Transformer |  |  | For Information Only
EPCOR | 72RW3 (Rossdale - Woodcroft), Woodcroft W724 (Woodcroft), Woodcroft W725 (Woodcroft) | 2020-06-29 07:00 | 2020-07-10 17:00 | N | N | disconnect replacement | Line, Circuit Breaker | 72RW3 (Rossdale - Woodcroft) |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ENMAX | 28.1TR (ENMAX 28) | 2020-06-29 08:00 | 2020-07-03 16:00 | N | N | Reinhausen tapchanger maintenance, oil sampling | Transformer | 28.1TR (ENMAX 28) |  | For Information Only
ENMAX, ALTALINK | 1080L (ENMAX 25 - ENMAX 65) | 2020-06-29 08:00 | 2020-06-30 18:00 | N | Y | power factor test, replace switches and SF6 sample | Line | 1080L (ENMAX 65 - ENMAX 25) | Power factor test HV LA 25MD240-1080. LA 65MD240-1080. Replace switch mech 25SW146, 25SW147, 65SW133, 65SW134. SF6 Sample 25-D139, 25-D138 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L137 (768s Rowley - 770s Three Hills), 770s 702 (770s Three Hills) | 2020-06-29 08:00 | 2020-06-29 17:00 | N | N | PRC-005 - test and operate breaker 702 to move alarm circuits to new SCADA system from old PLC system | Line, Circuit Breaker |  | Test and operate on breaker 702 to move alarm circuits to new SCADA system from old PLC system. Permit will be required to test trip coil for PRC-005. Line protection settings will be updated on A and B protection to change soft alarm descriptors. Each line protection relay (A and B) will only be isolated while the other is in service due to tele-protection being in place. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 768s 703 (768s Rowley) | 2020-06-29 08:00 | 2020-06-29 14:00 | N | N | PRC-005 trip coil testing | Circuit Breaker |  | PRC-005 Trip Coil Testing on Breaker 703, coordinated with Bkr 702 @770S 2-52227 - 7L137 will be out of Service | For Information Only, Pre-Condition
ATCO | 848s 703T (848s Ruth Lake), 7L47 (718s Parsons Creek - 848s Ruth Lake) | 2020-06-29 09:00 | 2020-06-29 17:00 | N | N | install bird proofing on 703T @ 848S Ruth Lake | Transformer, Line |  | Install Bird Proofing on 703T @ 848S Ruth Lake | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 928L (17s Benalto - 42s Sarcee), 906L (17s Benalto - 42s Sarcee) | 2020-06-29 09:00 | 2020-07-04 18:00 | N | Y | maintenance on structures | Line |  | 928L-maintenance on structures 336, 337, 341, 342, 344, 346, 348, 349, 350, 365, 366, 368, 369, 370, 371, 372, 377, 379, 381, 384, 385, 386, 387, 388, 389, 390, 406 906L-maintenance on structures 336, 340, 343, 344, 349, 350, 352, 353, 354, 355, 358, 362, 363, 364, 365, 366, 368, 369, 370, 371, 372, 381, 384, 385, 386, 387, 388, 389, 390 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L230 (743s Sarah Lake - 7L230 tap) | 2020-06-29 09:30 | 2020-07-02 00:15 | N | Y | test PRC trip coils on breaker 703 - re-wire heaters | Line |  | Test PRC trip coils On bkr 703 - re-wire heaters 7L230 open ended for the duration | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 256S Harmattan | 2020-06-29 09:30 | 2020-06-30 17:30 | N | Y | 228L - replace the failed relays: 67/67N/79/L3 SEL351S | Station |  |  | For Information Only, Pre-Condition, Restricts Generation
ALTALINK | 730L (285s East Camrose - 732L) | 2020-06-29 12:00 | 2020-06-30 18:00 | N | N | component replacements structures (64-196) on south section of 730L | Line | 730L (285s East Camrose - 730L62) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 20s T5 (20s Ghost), 20s 8 (20s Ghost) | 2020-06-29 12:00 | 2020-06-30 17:30 | N | N | doble test 20sT5 Tx5773 and repair explosion tube | Transformer, Circuit Breaker |  |  | For Information Only
ALTALINK | 186s T1 (186s Dry Creek) | 2020-06-29 12:00 | 2020-07-02 17:30 | N | N | fix oil leak and doble test | Transformer |  |  | For Information Only
ALTALINK | 14s 739N (14s Devon), 739L (14s Devon - 305s Acheson) | 2020-06-30 07:00 | 2020-06-30 18:00 | N | N | add remote recloser blocking functionality | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L159 (770s Three Hills - 7L159 tap), 770s 704 (770s Three Hills) | 2020-06-30 08:00 | 2020-06-30 17:00 | N | N | protection upgrade | Line, Circuit Breaker |  | 770S Protection Upgrade - 704 Test and Operate Test and operate on breaker 704 to move alarm circuits to new SCADA system from old PLC system. Permit will be required to test trip coil for PRC-005. Line protection settings will be updated on A and B protection to change soft alarm descriptors. Each line protection relay (A and B) will only be isolated while the other is in service due to tele-protection being in place. 7L159 will be open at 770S Three Hills end. Line protection will be isolated, one relay at a time. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 498s 666 (498s Tilley), 666L (28s West Brooks - 498s Tilley) | 2020-06-30 08:00 | 2020-06-30 17:00 | N | Y | implement/function sync check changes | Circuit Breaker, Line | 666L (28s West Brooks - 498s Tilley) | Outage on 498s666 to implement/function sync check changes on M388/389 relay. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 848s 704T (848s Ruth Lake), 7L71 (848s Ruth Lake - 2082s Dog Rib) | 2020-06-30 08:00 | 2020-07-03 17:00 | N | N | maintenance, major testing and bird proofing | Transformer, Line |  | 848S 704T MAJOR TESTING 704T Maint. and bird proofing @ 848S Ruth Lake 704T @ 848S OOS | Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L15 (763s Hanna - 775s Sullivan Lake) | 2020-06-30 08:30 | 2020-06-30 17:00 | N | N | install spacers | Line | 6L15 (763s Hanna - 775s Sullivan Lake) | to install Inter Phase Spacers on 6L15 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 263s 870E (263s Strachan), 870L (262s Rocky Mountain House - 263s Strachan) | 2020-06-30 09:00 | 2020-06-30 17:00 | N | Y | 138kV breaker maintenance | Circuit Breaker, Line | 870L (262s Rocky Mountain House - 263s Strachan) 263s 870E (263s Strachan) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L25 (768s Rowley - 802s Michichi Creek), 768s 704 (768s Rowley) | 2020-07-02 07:00 | 2020-07-02 16:00 | N | N | PRC-005 breaker trip coil testing | Line, Circuit Breaker |  | PRC-005 Breaker Trip Coil Testing, 7L25 open at 768S | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX, ALTALINK | 985L (74s Janet - ENMAX 25) | 2020-07-02 08:00 | 2020-07-02 18:00 | N | Y | power factor test, replace switch mech. SW135, SW134, SF6 sample D133, D132 | Line | 985L (74s Janet - ENMAX 25) | power factor test HV LA 25MD240-985. replace switch mech. SW135, SW134. SF6 Sample D133, D132 | 240 kV, Affects Cranking Path
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-07-02 09:00 | 2020-07-02 12:00 | Y | Y | hazard tree removals | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L32 (811s Clairmont Lake - 862s South Bezanson), 811s 710 (811s Clairmont Lake) | 2020-07-02 09:30 | 2020-07-02 17:00 | N | Y | breaker testing | Line, Circuit Breaker | 7L32 (811s Clairmont Lake - 862s South Bezanson) | 811S 710 BREAKER SF6 HPL PARTIAL TESTING | Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 268s 797 (268s Whitecourt), 797L (268s Whitecourt - 364s Whitecourt industrial) | 2020-07-02 10:00 | 2020-07-02 13:00 | N | N | upgrade MPLS node | Circuit Breaker, Line |  | upgrade MPLS node at 268s and 364s & breaker open due to loss of TPR | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 5.9TR (ENMAX 5) | 2020-07-02 20:00 | 2020-07-06 18:00 | N | N | emergency trip - testing | Transformer | 5.9TR (ENMAX 5) | 5.9TR Tripped out the night of July 2, 2020. The estimated date of return is Monday July 6, 2020. The crew is waiting on test results. | For Information Only
SUNCOR | 635EDD-1001 635-752-621 (635EDD-1001), 635EDD-1001 635-752-622 (635EDD-1001), 635PL7-1000 (635EDD-1000 - 635EDD-1001), 635EDD-1000 635-752-111 (635EDD-1000), 635EDD-1000 635-752-112 (635EDD-1000) | 2020-07-04 07:00 | 2020-07-13 09:00 | N | N | maintenance of 144kV breakers, disconnects and CVTs | Circuit Breaker, Line |  |  | Creates Radial Feeds
ATCO | 7L15 (841s Long Lake - 856s Kinosis) | 2020-07-04 07:30 | 2020-07-04 18:30 | N | Y | CNOOC will be completing a PM on the main disconnect switch (7L15D2) to our site, this job will require an isolation from Atco and a guarantee of isolation to be in place | Line |  | CNOOC will be completing a PM on the main disconnect switch (7L15D2) to our site, this job will require an isolation from Atco and a guarantee of isolation to be in place. As well well like to complete a quick Islanding trip test. | Restricts Generation
ATCO | 826s 903 (826s Marguerite Lake) | 2020-07-05 08:00 | 2020-07-05 12:00 | N | Y | add new breaker trip and block close coming from new 50BF/710 to trip breaker 903 | Circuit Breaker |  | To add new Breaker Trip and Block Close coming from new 50BF/710 to trip breaker 903 | 240 kV, Contingency Requires Mitigation
ENMAX | 14.83L (ENMAX 14 - ENMAX 36) | 2020-07-05 08:00 | 2020-07-05 12:00 | N | N | stand a street light pole | Line |  |  | Creates Radial Feeds
ATCO | 826s 907 (826s Marguerite Lake) | 2020-07-05 12:30 | 2020-07-05 17:00 | N | Y | add new breaker trip and block close coming from new 50BF/710 to trip breaker 907 | Circuit Breaker |  | To add new Breaker Trip and Block Close coming from new 50BF/710 to trip breaker 907 | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 830L (562s Cypress - 840s McNeill Station) | 2020-07-06 04:00 | 2020-07-06 22:00 | Y | N | forced outage | Line
EPCOR | 987s CC24 (987s Clover Bar) | 2020-07-06 07:00 | 2020-07-23 17:00 | N | N | breaker replacement | Circuit Breaker | 987s CC24 (987s Clover Bar) |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | H723 (Hardisty Epcor) | 2020-07-06 07:00 | 2020-07-09 16:00 | N | N | breaker fail cutover | Circuit Breaker | Hardisty H723 (Hardisty Epcor) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2020-07-06 07:00 | 2020-07-17 17:30 | N | Y | T11 testing | Line | 13L50 (2029s Heathfield - 2075s Newell) | 2075S - NEWELL EATL OUTAGE 2020 EATL Outage: T11 Testing | 500 kV, Pre-Condition
ALTALINK | 511s 1352 (511s Crossings), 511s ACF12 (511s Crossings) | 2020-07-06 07:30 | 2020-07-09 10:10 | N | Y | filter bank outage, maintenance, inspection | Circuit Breaker, Shunts |  | Annual Filter Bank outage, maintenance, inspection. All Other AC Filters to remain in-service and available for Link power transfer requirements | 240 kV, For Information Only
ENMAX, ALTALINK | 36.81L (44s Bearspaw - ENMAX 36) | 2020-07-06 08:00 | 2020-07-16 18:00 | N | Y | Haskayne line raise project | Line | 36.81L (44s Bearspaw - ENMAX 36) | Haskayne line raise project. Raising the line and replacing 4 structures to accommodate a new road construction. | For Information Only
ENMAX | 43.2TR (ENMAX 43) | 2020-07-06 08:00 | 2020-07-10 16:00 | N | N | tapchanger inspection X-TC, Y-TC. check reversing switch(X), (Y). Oil sampling MT, X-TC, Y-TC. | Transformer |  |  | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2020-07-06 08:00 | 2020-07-06 16:00 | N | N | investigate, replace rotten flex cables running to the LTC gas relays and LTC low temp lockout sensors | Transformer |  |  | For Information Only
ENMAX | 13.2TR (ENMAX 13) | 2020-07-06 08:00 | 2020-07-31 16:00 | N | N | Arc Flash Mitigation Project: protection outage and MV cable swap | Transformer | 13.2TR (ENMAX 13) |  | For Information Only
SUNCOR | 29PT-341 (29EDD-34), 29EDD-34 952-142 (29EDD-34), 29EDD-34 952-143 (29EDD-34) | 2020-07-06 08:00 | 2020-07-19 18:00 | N | N | line outage to perform 5/10yr PM | Transformer, Circuit Breaker | 29EDD-34 | line outage to perform 5/10yr PM 29PL6-39 buss and transformer: 29EDD34;29PP-103 SYSTEM;PM 5y,10y 29EDD34;29PT-341 SYSTEM;PM 10y 29EDD34;29PL6-39 SYSTEM;PM 5y,10y | 240 kV, For Information Only
ENMAX | 162.3TR (162s Beddington), 162s 138-RB86 (162s Beddington), 162s 138-RB85 (162s Beddington) | 2020-07-06 08:00 | 2020-07-10 16:00 | N | N | transformer tests and maintenance | Transformer, Circuit Breaker |  | Power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Power factor test HV PT 162PT138-T3 | Contingency Requires Mitigation
ATCO | 826s 902T (826s Marguerite Lake), 826s 503R (826s Marguerite Lake) | 2020-07-06 08:00 | 2020-08-30 16:00 | N | Y | breaker fail protection upgrade | Transformer, Shunts | 826s 902T (826s Marguerite Lake) | 826S Marguerite P&C 240/144kV Breaker Fail Protection Upgrade | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-07-06 09:00 | 2020-07-10 17:00 | Y | Y | LLP for hazard tree removals | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
REDDEER | 209s T1 (209s Timberlands) | 2020-07-06 09:00 | 2020-07-09 14:20 | N | Y | routine maintenance | Transformer |  |  | For Information Only
ALTALINK | 178s T1 (178s Cynthia) | 2020-07-06 09:00 | 2020-07-09 18:00 | N | N | leak repairs, SFRA test and doble test | Transformer |  | 138 kV bushings monitor & Lightning Arrestors on Transformer T1, 25 kV strain insulators between T1 and 178s4, 25 kV PT bird cover replacement (178s8); 178sT1 Leak repairs, SFRA test, Doble test, Conservator leak repair | For Information Only
BCH | 5L52 (Custer - Ingledow) | 2020-07-06 09:00 | 2020-07-06 17:00 | N | Y | disconnect maintenance | Line | 5L52 (Ingledow - Custer) | disconnect maintenance | 500 kV, Limits ATC
ATCO | 6L56 (763s Hanna - 802s Michichi Creek), 802s 606 (802s Michichi Creek) | 2020-07-06 10:00 | 2020-07-06 16:00 | N | N | breaker maintenance, testing | Line, Circuit Breaker |  | 802S Michichi 606 BREAKER BULK OIL KSO PARTIAL TESTING Partial Breaker Maintenance 6L56 Open Ended | Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-07-06 10:00 | 2020-07-13 15:00 | N | Y | XARM change out | Line |  | XARM change out | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ATCO, ALTALINK | 898s 501R (898s Heart Lake), 898s 902T (898s Heart Lake), 788L (898s Heart Lake - 788AL), 789L (898s Heart Lake - 1034s Margie) | 2020-07-06 11:00 | 2020-07-11 16:00 | N | Y | transformer test | Shunts, Transformer, Line |  | Isolate 902T, 704, 708, 501 and test | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 285s T1 (285s East Camrose) | 2020-07-06 11:15 | 2020-07-07 17:45 | N | N | maintenance | Transformer |  |  | For Information Only
ALTALINK | 163s T5 (163s Amoco Empress) | 2020-07-06 12:15 | 2020-07-10 15:23 | N | Y | bushing replacement, maintenance, doble testing | Transformer |  | bushing replacement, TX maintenance, T/C maintenance, doble, testing. maintain, doble, run tap changer through neutral, fix T/C indicator | 240 kV, For Information Only
ALTALINK | 205S Castle Rock Ridge | 2020-07-07 07:00 | 2020-07-07 12:00 | N | N | maintenance | Station |  |  | For Information Only
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2020-07-07 07:00 | 2020-07-16 17:00 | N | Y | line maintenance | Line | 1058L (657s Summerside - 803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T2 (Rossdale) | 2020-07-07 07:00 | 2020-07-07 17:00 | N | N | isolation of reactors for UGD | Transformer |  |  | For Information Only
ALTALINK | 747L (99s North St. Albert - 711L) | 2020-07-07 07:00 | 2020-07-07 18:00 | N | N | fire mitigation to repair structure #63 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 12.2TR (ENMAX 12) | 2020-07-07 08:00 | 2020-07-07 16:00 | N | N | replace liquid temperature gauge | Transformer |  |  | For Information Only
ATCO | 951s SVC (951s Thickwood) | 2020-07-07 08:00 | 2020-07-10 16:00 | N | Y | emergency outage to repair failed equipuipment to prevent trip | Shunts |  | 951S SVC outage(Repair failed equip to prevent trip) ATCO has been receiving some alarms (UMD Overtemp Alarm and a more recent Failed Thyristor that requires replacement) There is great concern that the SVC will trip off on the Overheat alarm. Siemens would like to take an Emergency outage to repair these items Through all the COVID -19 Restrictions, Siemens has finally been able to get permission to send a crew to get these repairs done. | 240 kV
ATCO | 7L59 (786s High Level - 7L59 tap) | 2020-07-07 08:00 | 2020-07-09 17:00 | N | Y | FAC-008 intolerable span violation mitigation, STR 5A require GOI to be changed | Line |  | FAC-008 intolerable span violation mitigation STR 5A require GOI to be changed | Firm Load Loss, Pre-Condition
ALTALINK | 156L (19s Wabamun - 156BL) | 2020-07-07 08:00 | 2020-07-07 18:00 | N | N | remove 156L Str 1  2 OHSW and remove downhaul guy on 156L Str 1 to mitigate clearance violation to 896L | Line |  |  | Firm Load Loss
ENMAX | 31.1C (ENMAX 31), 31B138-31CAP (ENMAX 31) | 2020-07-07 08:00 | 2020-07-09 16:00 | N | N | HV cap bank maintenance | Shunts, Circuit Breaker |  |  | For Information Only
ALTALINK | 535s 5452 (535s Joffre) | 2020-07-07 08:00 | 2020-07-07 17:00 | N | N | implement/function sync check changes on M388/389 relay | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 162s 162B240-RB132 (162s Beddington) | 2020-07-07 08:00 | 2020-07-07 16:00 | N | Y | breaker maintenance, dashpot checks and SF6 sample | Circuit Breaker | 162s 240-RB132 (162s Beddington) |  | 240 kV, Contingency Requires Mitigation
ATCO | 898s 901 (898s Heart Lake), 898s 902 (898s Heart Lake), 9L22 (825s Whitefish Lake - 898s Heart Lake) | 2020-07-07 08:00 | 2020-07-07 17:00 | N | Y | test breakers | Circuit Breaker, Line | 9L22 (825s Whitefish Lake - 898s Heart Lake) | Isolate and test breaker, 9L22 Open ended as Breaker 901 will also be open under 2-51472 | 240 kV, Pre-Condition
ATCO | 7L55 (743s Sarah Lake - 809s Louise Creek), 743s 701 (743s Sarah Lake) | 2020-07-07 08:30 | 2020-07-08 15:00 | N | N | breaker maintenance and PRC testing | Line, Circuit Breaker |  | Major breaker Maint and PRC testing, 7L55 open ended for the duration | For Information Only
BCH | 5L51 (Custer - Ingledow) | 2020-07-07 09:00 | 2020-07-08 17:00 | N | Y | disconnect maintenance | Line | 5L51 (Ingledow - Custer), ING 5B3 OOS | disconnect maintenance | 500 kV, Limits ATC
ALTALINK | 735L (171s Redwater - 233s Beamer) | 2020-07-07 09:00 | 2020-07-08 18:00 | N | N | urgent repair/replace 735L Str 30 and Str 33 to mitigate line clearance violations | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72CH11 (987s Clover Bar - Hardisty) | 2020-07-08 07:00 | 2020-07-08 17:00 | N | N | emergency outage, clean the potheads after fault | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162s 240-RB135 (162s Beddington) | 2020-07-08 08:00 | 2020-07-08 16:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV
BLACKSPRING | 485S Black Springs | 2020-07-08 08:00 | 2020-07-09 17:00 | N | N | feeder 3 outage to replace dead break junction | Station |  | Feeder 3 outage to replace dead break junction, install bird cover up at riser 1 & 2, replace surge arrestors at multiple turbines. | Restricts Generation
ALTALINK | 535s 5752 (535s Joffre) | 2020-07-08 08:00 | 2020-07-08 17:00 | N | N | implement/function sync check changes on M388/389 relay | Circuit Breaker |  |  | Contingency Requires Mitigation
ALTALINK | 896L (19s Wabamun - 432s Carvel) | 2020-07-08 08:00 | 2020-07-08 18:00 | N | N | raise cross arm on str 15 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 452s T1 (452s B.F. Goodrich Fort Saskatchewan) | 2020-07-08 08:00 | 2020-07-08 18:00 | N | N | investigate low gas indication on 452s10 & replace 1 head, 452s10 1st trip testing, 452s10 T1 testing | Transformer | 452s T1 (452s B.F. Goodrich Fort Saskatchewan) |  | For Information Only
ATCO | 7L71 (718s Parsons Creek - 2082s Dog Rib) | 2020-07-08 08:00 | 2020-07-09 18:00 | N | N | ground resistivity and line impendence testing at 718s Parsons Creek | Line |  | Ground resistivity and line impendence testing at 718s Parsons Creek | Pre-Condition
TRANSALTA | 239S Castle River | 2020-07-08 08:00 | 2020-07-08 15:00 | N | Y | substation maintenance | Station |  |  | Restricts Generation
TRANSALTA | CR1 Castle River | 2020-07-08 08:00 | 2020-07-08 15:00 | N | N | substation maintenance | Unit
ALTALINK | 58s T2 (58s Edson) | 2020-07-08 09:00 | 2020-07-08 17:00 | N | N | strain insulators for the flex bus between 58s3 and 25kV bus require replacement | Transformer
ALTALINK | 172L (83s Taber - 172EL) | 2020-07-08 13:15 | 2020-07-08 17:45 | N | N | maintenance on str 839 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2020-07-08 23:00 | 2020-07-09 03:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2020-07-09 03:00 | 2020-07-09 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 16.1TR (ENMAX 16) | 2020-07-09 08:00 | 2020-07-26 16:00 | N | N | Arc Flash Mitigation Project. protection outage and MV cable swap | Transformer |  |  | For Information Only
ALTALINK | 535s 6052 (535s Joffre) | 2020-07-09 08:00 | 2020-07-09 17:00 | N | N | implement/function sync check changes on M388/389 relay | Circuit Breaker |  | Outage on 535s6052 to implement/function sync check changes on M388/389 relay. | Pre-Condition
ATCO, ALTALINK | 1086L/9L47 (852s Round Hill - 898s Heart Lake), 898s 902 (898s Heart Lake), 898s 903 (898s Heart Lake) | 2020-07-09 08:00 | 2020-07-09 17:00 | N | Y | breaker testing | Line, Circuit Breaker | 1086L/9L47 (852s Round Hill - 898s Heart Lake) | Isolate and test breaker, 9L47 Open ended as Breaker 903 will also be open under 2-51478 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | UE-1 7203 (UE-1 Syncrude Plant 30-2), UE-1 30-2PTR72-A1 (UE-1) | 2020-07-10 08:00 | 2020-07-10 20:00 | N | N | substation work | Circuit Breaker, Transformer |  | 30-2PTR72-A2 - Transformer 72/13.8KV - UE-1 Substation - PM Following Circuit Breaker will be operated: Breaker 52-7203 (UE-1 Substation) Following switch will be operated: 72-03 (UE-1 Substation) | For Information Only
ATCO | 898s 904 (898s Heart Lake) | 2020-07-12 08:00 | 2020-07-12 10:00 | N | Y | PRC-005 - trip coil testing | Circuit Breaker | 898s 904 (898s Heart Lake) | PRC-005 - TRIP COIL TESTING - BREAKER 904-A @ 898S Isolate Breaker test trip coils Breaker 904 will be out of service for the duration of work | 240 kV, Contingency Requires Mitigation
ATCO | 898s 905 (898s Heart Lake) | 2020-07-12 10:00 | 2020-07-12 12:00 | N | Y | PRC-005 - trip coil testing | Circuit Breaker | 898s 905 (898s Heart Lake) | PRC-005 - TRIP COIL TESTING - BREAKER 905-A @ 898S Isolate Breaker test trip coils Breaker 905 will be out of service for the duration of work | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 898s 906 (898s Heart Lake) | 2020-07-12 12:00 | 2020-07-12 14:00 | N | Y | PRC-005 test trip coil | Circuit Breaker | 898s 906 (898s Heart Lake) | PRC-005 Test 906 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 898s 908 (898s Heart Lake) | 2020-07-12 14:00 | 2020-07-12 16:00 | N | Y | PRC-005 test trip coil | Circuit Breaker | 898s 908 (898s Heart Lake) | PRC-005 Test 908 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 898s 909 (898s Heart Lake) | 2020-07-12 16:00 | 2020-07-12 18:00 | N | Y | PRC-005 test trip coil | Circuit Breaker | 898s 909 (898s Heart Lake) | PRC-005 Test 909 Trip Coil(s), only one breaker tested at a time, approximate testing time per breaker = 2 hours | 240 kV, Pre-Condition
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake) | 2020-07-13 07:00 | 2020-07-13 12:00 | N | N | structure replacements | Line |  | 174L and 780L (Double Circuit) Structures 160,171,172 | Creates Radial Feeds, Firm Load Loss
EPCOR | H726 (Hardisty Epcor), 72LH8 (803s Lambton - Hardisty) | 2020-07-13 07:00 | 2020-07-17 17:00 | N | N | breaker fail cutover | Circuit Breaker, Line | Hardisty H726 (Hardisty Epcor) |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | T2 (Woodcroft), 72NW15 (Namao - Woodcroft) | 2020-07-13 07:00 | 2020-07-17 17:00 | N | N | secondary transformer retrofit and disconnects | Transformer, Line | 72NW15 (Namao - Woodcroft) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2020-07-13 07:00 | 2020-07-13 12:00 | N | N | insulator wash | Line |  | insulator wash program: structures 79, 80, 81 174L and 780L structures 160,171,172 | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 956L (59s Peigan - 103s Goose Lake) | 2020-07-13 07:00 | 2020-07-13 17:00 | N | Y | structure replacements | Line |  | 956L Str 39 Replace Saddle top phase, check and take photos of broken strands, 956L Str 56 bottom phase replace damper, 955L Str 63 Top phase damper replace, 955L Str 83 Replace OHSW assembly 956L side. | 240 kV, For Information Only
ALTALINK | 511s ACF13 (511s Crossings), 511s 1452 (511s Crossings) | 2020-07-13 07:30 | 2020-07-16 16:30 | N | Y | maintenance and inspection | Shunts, Circuit Breaker |  | Annual Filter Bank outage, maintenance, inspection. All Other AC Filters to remain in-service and available for Link power transfer requirements | 240 kV, Pre-Condition
ATCO | 724s 601 (724s Hines Creek) | 2020-07-13 08:00 | 2020-07-27 16:00 | N | N | New breaker. ISD July 20, 2020 (capital maintenance) | Circuit Breaker
ALTALINK | 202L (58s Edson - 178s Cynthia) | 2020-07-13 08:00 | 2020-07-17 18:00 | N | N | replace 202L str 458, 647 and 785 to mitigate line clearance violations | Line |  | Replace 202L Str 458, 647 and 785 to mitigate line clearance violations. - Install guy links on Str 797, 808, 811, 812 and 813 for fire risk mitigation | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ATCO | 856s 901T (856s Kinosis) | 2020-07-13 08:00 | 2020-07-16 17:00 | N | Y | transformer class 1 major testing | Transformer |  | TRANSFORMER CLASS1 MAJOR TESTING @ KINOSIS 856S 901T Dist. Load Fed from other subs 901T may be restored on evening of July 14 &15 as required by customer | 240 kV, Pre-Condition
ENMAX | 31B138-31.84 (ENMAX 31), 32B138-31.84 (ENMAX 32), 31.84L (ENMAX 31 - ENMAX 32) | 2020-07-13 08:00 | 2020-07-15 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | HV Breaker Maintenance 31B138-31.84. SF6 sample 32B138-31.84. | For Information Only
ALTALINK | 535s 6252 (535s Joffre) | 2020-07-13 08:00 | 2020-07-13 17:00 | N | N | sync check changes on relay. | Circuit Breaker |  |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 162s 138-RB92 (162s Beddington), 162s 138_RB94 (162s Beddington), 162.4TR (162s Beddington) | 2020-07-13 08:00 | 2020-07-17 16:00 | N | N | power factor test transformer | Circuit Breaker, Transformer |  | Power factor test transformer, Transformer Secondary Cable Tests, Power factor test HV PT 162PT138-T4. HV SW maint. SW106 | For Information Only
ALTALINK | 359s T2 (359s Esso West Pembina) | 2020-07-13 08:30 | 2020-07-15 16:30 | N | N | install new CTs load side of T2 | Transformer |  | install new CTs load side of T2. Test CTs and CT loops | For Information Only
ATCO | 732s 701 (732s Mitsue), 732s 702 (732s Mitsue), 732s 901T (732s Mitsue) | 2020-07-13 08:30 | 2020-07-16 16:30 | N | Y | major testing 901T | Circuit Breaker, Transformer |  | Major Testing 901T, 144KV ring bus open during outage, all load carried by 902T | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 6L56 (763s Hanna - 802s Michichi Creek), 763s 601 (763s Hanna) | 2020-07-13 09:00 | 2020-07-14 17:00 | N | N | 763S Hanna 601 breaker min oil HLC complete testing | Line, Circuit Breaker |  | 763S Hanna 601 BREAKER MIN OIL HLC COMPLETE TESTING | Over/Under Voltage, Pre-Condition
ALTALINK, EPCOR | 71s 1752 (71s Lamoureux), 71s 1652 (71s Lamoureux), 71s 1552 (71s Lamoureux), 920L (71s Lamoureux - 557s Castle Downs), 942L (71s Lamoureux - 681s Bannerman) | 2020-07-13 09:00 | 2020-07-15 18:00 | N | Y | replacing M/O breaker with a new SF6 breaker | Circuit Breaker, Line |  | Replacing M/O Breaker with a new SF6 Breaker & re-wiring JB27 | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 63s 2652 (63s Red Deer) | 2020-07-13 09:15 | 2020-07-16 17:45 | N | Y | 63s2652L PRC5 maintenance | Circuit Breaker |  | 63s2652L PRC5 Maintenance and 1st trip, also will be replacing the grading caps on 63s2652 | 240 kV, Contingency Requires Mitigation
ALTALINK | 510s 1452 (510s Sunnybrook), 510s ACF14 (510s Sunnybrook) | 2020-07-13 09:30 | 2020-07-16 16:30 | N | Y | annual inspection & maintenance | Circuit Breaker, Shunts | 510s ACF14 (510s Sunnybrook) |  | 500 kV, Pre-Condition
ATCO | 741s 701 (741s Fox Creek), 7L90 (741s Fox Creek - 7L90D3) | 2020-07-13 10:00 | 2020-07-14 16:00 | N | N | top up gas, check leaks | Circuit Breaker, Line |  | 741S 701 Top up Gas / Check Leaks Top up breaker SF6, check for leaks 7L90 Open-ended for duration of work | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 635EDD-1000 635-752-112 (635EDD-1000), 635EDD-1000 635-752-113 (635EDD-1000), 635PT-1004 (635EDD-1000) | 2020-07-13 11:00 | 2020-07-19 17:00 | N | N | transformer protection and breaker failure protection maintenance | Circuit Breaker, Transformer |  |  | For Information Only
ALTALINK | 83s34 (83s Taber), 83s C1 (83s Taber) | 2020-07-13 11:00 | 2020-07-14 18:00 | N | N | cap bank protection upgrade | Switch, Shunts |  |  | Pre-Condition
ALTALINK | 708L (71s Lamoureux - 708AL) | 2020-07-13 12:00 | 2020-07-16 18:00 | N | N | components/structure replacements (structures #21 - 57) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 930s 701 (930s Arcenciel) | 2020-07-13 12:00 | 2020-07-13 17:00 | N | N | PRC-005 - trip coil testing | Circuit Breaker | 930s 701 (930s Arcenciel) | PRC-005 - trip Coil Testing - Breaker 701 @ 930S | Contingency Requires Mitigation
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2020-07-13 12:00 | 2020-07-14 12:00 | N | N | insulator wash program: structures 634 to 650, 653, 654, 657 | Line | Studied with Wind = 990 MW, Battle River (net-to-grid) = 155 MW - increasing or decreasing has no impacts to 7L701 contingency. |  | Over/Under Voltage, Pre-Condition
ALTALINK | 163s 1352 (163s Amoco Empress) | 2020-07-13 12:30 | 2020-07-16 18:00 | N | Y | PRC 5 and perform 1st and 2nd trip , then maintain 240kV HLR- E minimum oil breaker | Circuit Breaker |  |  | Contingency Requires Mitigation, Firm Load Loss
CapitalPower | Clover Bar Energy Centre | 2020-07-14 01:00 | 2020-07-14 03:00 | N | N | network outage | SCInternal |  |  | For Information Only, Pre-Condition
ALTALINK | 226S Garden City, 891L (226s Garden City - 863L) | 2020-07-14 06:00 | 2020-07-15 18:00 | N | N | maintenance and testing | Station, Line |  | maintenance and testing at Garden City Substation 226S. | Restricts Generation
ALTALINK | 968L (138s Windy Flats - 370s North Lethbridge) | 2020-07-14 07:00 | 2020-07-17 17:00 | N | N | P5 replacing dampers and marker cones | Line |  | P5 replacing dampers and marker cones from STRs 26-159. Marker cones on STRs 111 & 140 will be replaced with a helicopter. | 240 kV, Pre-Condition
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon) | 2020-07-14 07:00 | 2020-07-14 18:00 | N | N | clearance mitigation | Line |  | Reframe tangent structures 335 and 347 for clearance mitigation | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 955L (59s Peigan - 103s Goose Lake) | 2020-07-14 07:15 | 2020-07-14 17:45 | N | N | Emergency Repair; repair OHSW str83 | Line |  | Emergency Repair; repair OHSW str83 | 240 kV, Pre-Condition
ATCO | 930s 702 (930s Arcenciel) | 2020-07-14 08:00 | 2020-07-14 12:30 | N | N | PRC-005 - trip coil testing | Circuit Breaker | 930s 702 (930s Arcenciel) | PRC-005 - trip Coil Testing - Breaker 702 @ 930S | For Information Only, Pre-Condition
ALTALINK | 535s 6452 (535s Joffre) | 2020-07-14 08:00 | 2020-07-14 17:00 | N | N | implement/function sync check changes | Circuit Breaker |  | Outage on 535s6452 to implement/function sync check changes on M388/389 relay. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 186s 611 (186s Dry Creek), 611L (186s Dry Creek - 391S Balzac) | 2020-07-14 08:30 | 2020-07-14 12:30 | N | N | PRC 5 and 1st trip | Circuit Breaker, Line |  | PRC 5 and 1st trip, crew will do first trip analysis so they need to get set up before switching starts. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 28s R1 (28s West Brooks), 28s 44 (28s West Brooks) | 2020-07-14 09:15 | 2020-07-15 17:45 | N | Y | PRC5 and 1st trip | Shunts, Circuit Breaker |  | PRC5 and 1st trip on 28s44 then doble test 28sR1 | 240 kV, Pre-Condition
ALTALINK | 704L (51s Wainwright - 478s Tucuman) | 2020-07-14 12:00 | 2020-07-14 18:00 | N | N | insulator wash program | Line |  | Insulator Wash Program: Structures 301, 302, 303,304,305,306 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 186s 631 (186s Dry Creek), 631L (186s Dry Creek - 199s East Airdrie) | 2020-07-14 12:30 | 2020-07-14 17:00 | N | N | PRC 5 and 1st trip | Circuit Breaker, Line |  | PRC 5 and 1st trip, crew will do first trip analysis so they need to get set up before switching starts. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 930s 703 (930s Arcenciel) | 2020-07-14 12:30 | 2020-07-14 17:00 | N | N | PRC-005 - trip coil testing | Circuit Breaker | 930s 703 (930s Arcenciel) | PRC-005 - trip Coil Testing - Breaker 703 @ 930S | Contingency Requires Mitigation, Pre-Condition
ATCO | 840s 502 (840s McNeill) | 2020-07-14 15:45 | 2020-08-05 16:00 | N | N | locked out | Circuit Breaker |  |  | For Information Only
ALTALINK, EPCOR | 1045L (310p Sundance - 320p Keephills - 805s Jasper) | 2020-07-15 07:00 | 2020-07-21 17:00 | N | Y | line maintenance | Line | 1045L (310p Sundance - 320p Keephills - 805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 744L (235s Entwistle - 744AL) | 2020-07-15 07:00 | 2020-07-15 15:00 | N | N | insulator washing program 744L: structures 5 to 12 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 930s 704 (930s Arcenciel) | 2020-07-15 08:00 | 2020-07-15 12:30 | N | N | PRC-005 - maintenance | Circuit Breaker | 930s 704 (930s Arcenciel) | PRC-005 - trip Coil Testing - Breaker 704 @ 930S | For Information Only
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2020-07-15 08:00 | 2020-07-15 16:30 | N | N | replacing 38s897 breaker grading capacitor | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale), 763s 603 (763s Hanna) | 2020-07-15 08:00 | 2020-07-15 16:00 | N | N | 763S Hanna 603 BREAKER MIN OIL HLC PARTIAL TESTING | Line, Circuit Breaker |  | 763S Hanna 603 BREAKER MIN OIL HLC PARTIAL TESTING | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 162.81L (162s Beddington - 391S Balzac), 391s T2 (391s Balzac) | 2020-07-15 08:30 | 2020-07-16 17:30 | N | N | replace existing 138kV PT3 | Line, Transformer |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
BCH | Natal T1 (BCH Natal) | 2020-07-15 09:00 | 2020-07-16 17:00 | N | Y | station maintenance | Transformer | Natal T1 (BCH Natal) 60B1, 60CB11, 60CB15, 60CB1, SS1 OOS |  | Pre-Condition
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek), 741s 702 (741s Fox Creek) | 2020-07-15 09:30 | 2020-07-15 17:00 | N | Y | PRC-005 - trip coil testing | Line, Circuit Breaker | 7L199 (347s Fox Creek - 741s Fox Creek) | 741S Breaker 702 PRC-005 - Trip Coil Testing - 7L199 Open Ended | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 741s 705 (741s Fox Creek), 741s 705C (741s Fox Creek) | 2020-07-15 10:00 | 2020-07-15 16:00 | N | N | PRC-005 - trip coil testing | Circuit Breaker, Shunts |  | PRC-005 - TRIP COIL TESTING - BREAKER 705-A @ 741S PRC-005 Trip coil, aux relay testing Cap bank out of service while testing | For Information Only, Pre-Condition
ATCO | 930s 706 (930s Arcenciel) | 2020-07-15 12:30 | 2020-07-15 17:00 | N | N | PRC-005 - trip coil testing | Circuit Breaker | 930s 706 (930s Arcenciel) | PRC-005 - trip Coil Testing - Breaker 706 @ 930S | For Information Only, Pre-Condition
ALTALINK | 71s 1552 (71s Lamoureux) | 2020-07-15 18:00 | 2020-07-26 18:00 | N | Y | replacing M/O breaker with a new SF6 breaker | Circuit Breaker |  | Was extended to Jul 31 from originally scheduled end date of Jul 23. | 240 kV, Contingency Requires Mitigation
ALTALINK | 199L (268s Whitecourt - 199AL) | 2020-07-16 07:00 | 2020-07-16 18:00 | N | N | insulator wash program: structures 367 to 379, 382, 383, 409, 410, 411, 412 | Line |  |  | Creates Radial Feeds, Over/Under Voltage, Pre-Condition
ATCO | 930s 707 (930s Arcenciel) | 2020-07-16 08:00 | 2020-07-16 12:30 | N | N | PRC-005 - trip coil testing | Circuit Breaker | 930s 707 (930s Arcenciel) | PRC-005 - trip Coil Testing - Breaker 707 @ 930S | For Information Only, Pre-Condition
ATCO | 778s 601T (778s Big Valley) | 2020-07-16 08:00 | 2020-07-30 16:00 | N | N | Transformer replacement (capital maintenance). ISD July 23, 2020 | Transformer
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2020-07-16 08:00 | 2020-07-17 16:00 | N | N | move double structures on Sarcee Trail & drill and set bases for new poles & breaker maintenance | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 874L (45s Bretona - 522s Cooking Lake) | 2020-07-16 08:30 | 2020-07-16 17:30 | N | N | 45s874 tank heater replacement | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 28s T2 (28s West Brooks) | 2020-07-16 08:30 | 2020-07-16 17:00 | N | Y | fix the timing on the tapchanger | Transformer |  | fix the timing on the tapchanger | 240 kV, Over/Under Voltage
ATCO | 763s 507C (763s Hanna) | 2020-07-16 08:30 | 2020-07-16 16:00 | N | N | add blocking switches on 51-27-59/507C | Shunts |  | 763S Hanna - Add Blocking Switches on 51-27-59/507C 507C Out of Service Need to complete wiring on 51-27-59/507C Relay to add in blocking switches for the trip outputs of the relay. Taking 507C out of service in order to commission the new blocking switches to breaker 507 | For Information Only, Pre-Condition
ATCO | 9L80 (755s Cordel - 757s Battle River) | 2020-07-16 13:00 | 2020-07-16 14:00 | N | Y | ATCO radio upgrades | Line |  |  | 240 kV, Restricts Generation, Affects Cranking Path
ALTALINK | 507L (83s Taber - 257s Hull) | 2020-07-17 07:15 | 2020-07-18 13:00 | N | N | maintenance on strs 151 and 153 | Line |  | Extended due to Jul 18 1300H from Jul 17 extended damage on line. | Creates Radial Feeds, Pre-Condition
ENMAX | 162.81L (162s Beddington - 391S Balzac) | 2020-07-18 08:00 | 2020-07-18 16:00 | N | Y | replace rotten pole and HV SW maintenance | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2020-07-19 07:15 | 2020-07-19 15:10 | N | Y | installing street light south of structure 446 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 729L (285s East Camrose - 542s Ervick) | 2020-07-20 07:00 | 2020-07-21 12:00 | N | Y | insulator wash program | Line |  | Insulator Wash Program: Strs 204B to 209, 241 to 256, 259, 260, 268 to 270, 286 to 289 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2020-07-20 07:00 | 2020-07-20 17:00 | N | N | doble | Line | 72JM18 (805s Jasper - Meadowlark) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | H724 (Hardisty Epcor), 72CH9 (987s Clover Bar - Hardisty) | 2020-07-20 07:00 | 2020-07-24 17:00 | N | N | breaker fail cutover | Circuit Breaker, Line | Hardisty H724 (Hardisty Epcor) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 801s 905 (801s Anderson) | 2020-07-20 07:00 | 2020-07-23 16:00 | N | Y | maintenance | Circuit Breaker |  | 801S Anderson 905 BREAKER MIN OIL HLR COMPLETE TESTING BKR 905 Complete Maint 9L97 to Oakland fed off of 906 only | 240 kV
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2020-07-20 08:00 | 2020-07-21 16:00 | N | N | move double structures on Sarcee Trail & set top of pole and transfer wire and assemble top | Line | 1.80L (ENMAX 28 - ENMAX 1) |  | Creates Radial Feeds
ALTALINK | 895s T2 (895s Suffield) | 2020-07-20 08:00 | 2020-07-23 14:00 | N | N | re-install new VR1 C phase regulator | Transformer |  | Re-install new VR1 C phase regulator. | For Information Only
SUNCOR | 635EDD-1001 635-752-622 (635EDD-1001), 635EDD-1001 635-752-623 (635EDD-1001), 635PT-1039 (635EDD-1001) | 2020-07-20 08:00 | 2020-07-26 17:00 | N | N | transformer protection and breaker failure protection maintenance | Circuit Breaker, Transformer |  |  | For Information Only
ATCO | 879s 701T (879s Scottford Upgrader) | 2020-07-20 08:00 | 2020-07-24 17:00 | N | Y | Maintenance | Transformer | 879s 701T (879s Scottford Upgrader) | 35 kV A Bus Maintenance " Scheduled for July 23, 2020 " 701T will be isolated July 20th,2020 as originally planned and restored July 24th, 2020 " Basler relay testing will be coordinated with the transformer restoration on July 24th 702T and ALC02L will be the only source of power for the duration of the outage GOI was extended to include BKR 152 as per customer request | For Information Only
ENMAX | 5.6TR (ENMAX 5) | 2020-07-20 08:00 | 2020-07-25 16:00 | N | N | plastibeton tray replacement at 5 Sub | Transformer
ENMAX | 10.1TR (ENMAX 10) | 2020-07-20 08:00 | 2020-07-24 16:00 | N | N | power factor test transformer & transformer secondary cable tests & transformer maintenance & check reversing switch | Transformer |  |  | For Information Only
ENMAX | 31.1TR (ENMAX 31) | 2020-07-20 08:00 | 2020-07-24 16:00 | N | N | HV bushing replacement. oil sampling MT, TC | Transformer
ENMAX | 2.2TR (ENMAX 2) | 2020-07-20 08:00 | 2020-07-21 16:00 | N | N | T-60 upgrade phase 2. check reversing switch. | Transformer
BCH | 2L112 (Boundary - Nelway) | 2020-07-20 08:30 | 2020-07-23 17:00 | N | Y | bpa outage/BCH disconnect maintenance, BC maintenance does not affect the Alberta ATC | Line | 2L112 (Nelway - Boundary), NLY 2D24, 2D2CB7 OOS | bpa outage/disconnect maintenance | 240 kV, Limits ATC
ALTALINK | 511s Crossing | 2020-07-20 09:00 | 2020-07-20 13:00 | N | Y | replace failed K3 relay in 511s6257 motor mechanic | Station |  |  | For Information Only
ALTALINK | 848L (17s Benalto - 848AL) | 2020-07-20 09:00 | 2020-07-20 19:00 | N | Y | scope of work includes installing a bridge along 848L between structures 204 and 207 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 7L53 (700s Bonnyville - 7L53 tap) | 2020-07-20 09:00 | 2020-07-22 17:00 | N | N | Insulator and Arm Changes | Line |  | Insulator and Arm Changes | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L84 (722s Crystal Lake - 749s Flyingshot Lake), 722s 702 (722s Crystal Lake) | 2020-07-20 09:00 | 2020-07-21 17:00 | N | Y | PRC- 005 relays & breaker min oil HLR complete testing | Line, Circuit Breaker |  | BREAKER MIN OIL HLR COMPLETE TESTING PRC- 005 relays, trip coils aux coils, complete main. | Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition,Affects Cranking Path
ALTALINK | 368s T1 (368s Burdett) | 2020-07-20 09:15 | 2020-07-23 17:45 | N | N | fix oil leak, install bracket for breather pipe and do some containment pit maintenance and look at the hydran | Transformer
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-07-20 10:00 | 2020-07-27 15:00 | N | Y | XARM change out | Line |  | XARM change out | Overload, Restricts Generation, Affects Cranking Path
ALTALINK | 522s T1 (522s Cooking Lake) | 2020-07-20 11:00 | 2020-07-23 17:45 | N | N | oil leaks, doble, 138KV LAs & 522sVR1 maintenance, doble | Transformer |  | Oil Leaks, Oil Gage condensation, & 522s259X maintenance, leaking sight glass.
ALTALINK | 283s T1 (283s Violet Grove) | 2020-07-20 11:15 | 2020-07-23 16:45 | N | N | replace T1 bushings and TC filter | Transformer
ALTALINK, TRANSALTA | 616L (59s Peigan - 103s Goose Lake), 59s T1 (59s Peigan), 159s 138kV Bus 1 (159s Colinton) | 2020-07-20 12:00 | 2020-07-24 16:30 | N | Y | miscellaneous maintenance | Line, Transformer, Bus |  | Replace 59s7, install Whips on 59s5, and complete misc. grounding deficiencies on other 138kv Switches. | 240 kV, Pre-Condition
ALTALINK | 708L (71s Lamoureux - 708AL) | 2020-07-20 12:00 | 2020-07-23 18:00 | N | N | components/structure replacements | Line |  | Components/Structure Replacements (Structures #21 - 57) | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 76L (33s Spray - 115s Mt. Allan) | 2020-07-20 12:15 | 2020-07-24 17:45 | N | N | inspect cables in six underground vaults | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 277s T1 (277s Hayter) | 2020-07-20 15:00 | 2020-07-23 14:45 | N | N | oil leak repair, filter pack replacement and bird cover install | Transformer
EPCOR | 987s C72C1 (987s Clover Bar) | 2020-07-21 07:00 | 2020-07-22 17:00 | N | N | repair cap banks | Circuit Breaker | 987s C72C1 (987s Clover Bar) |  | Pre-Condition
ALTALINK, ATCO | 912L (63s Red Deer - 766s Nevis), 9L912 (63s Red Deer - 766s Nevis) | 2020-07-21 07:00 | 2020-07-24 17:00 | N | Y | install phase raiser assemblies on all 3 phases at 912L Str 59 & 60 to mitigate ground clearance violation. | Line |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 8B138-7A0 (ENMAX 8), 8B138-1A0 (ENMAX 8) | 2020-07-21 08:00 | 2020-07-30 16:00 | N | N | installation of 2.84L to 138kV GIS gear - DCTRP | Circuit Breaker |  | DCTRP. Outage#3 Installation of 2.84L to 138kV GIS gear. Reduce SF6 gas in switchgear. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 743s 702 (743s Sarah Lake), 7L67 (743s Sarah Lake - 824s Fieldgate) | 2020-07-21 09:30 | 2020-07-21 15:30 | N | Y | test PRC trip coils | Circuit Breaker, Line |  | Test PRC trip coils On bkr 702 - 7L67 open ended, | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 729L (40s Wetaskiwin - 729AL), 729L (542s Ervick - 729AL), 729AL (6500s Dravo Trueweld Grating - 729L) | 2020-07-21 12:00 | 2020-07-21 18:15 | N | N | insulator wash program structure 12, 120 - 124, 198-199 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
AESO-SC | OATI | 2020-07-21 18:00 | 2020-07-21 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
EPCOR | 1098L (805s Jasper - Poundmaker), 805s J2401 (805s Jasper) | 2020-07-22 07:00 | 2020-07-27 12:00 | N | Y | line maintenance | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 903L (17s Benalto - 320p Keephills) | 2020-07-22 07:00 | 2020-07-25 17:00 | N | Y | replace damaged lattice tower (903L66) with new steel pole H-frame structure | Line |  |  | 240 kV, Contingency Requires Mitigation,Affects Cranking Path
ALTALINK | 838L (14s Devon - 325s Leduc) | 2020-07-22 07:00 | 2020-07-26 18:00 | N | N | changing Strs 23 and 24 and rebuild between Strs 39 and 43 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
BLACKSPRING | 485S Black Springs | 2020-07-22 08:00 | 2020-07-23 17:00 | N | N | feeder 7 outage to replace circuit breaker bushing | Station |  | Feeder 7 outage to replace circuit breaker bushing. | Restricts Generation
ENMAX | 2.3TR (ENMAX 2) | 2020-07-22 08:00 | 2020-07-23 16:00 | N | N | T-60 Upgrade Phase 2 | Transformer |  |  | For Information Only
ALTALINK | 801AL (445s Elk River - 801L), 445S Elk River | 2020-07-22 08:00 | 2020-07-22 20:00 | N | N | replace 445s3, 445s11, & 445s4 and install LA's on T2 low side | Line, Station |  |  | Firm Load Loss, For Information Only
ALTALINK | 753L (65s High River - 253s Blackie) | 2020-07-22 09:00 | 2020-07-23 18:00 | N | Y | insulator wash program: 753L Structures 1,2, 13B, 14 to 27, 153 to 156, 167, 168 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 722s 701 (722s Crystal Lake), 7L39 (811s Clairmont Lake - 7L39 tap) | 2020-07-22 10:00 | 2020-07-23 17:00 | N | Y | PRC-005 complete testing: auxiliary relays, trip coils relay testing | Circuit Breaker, Line | 7L39 (811s Clairmont Lake - 7L39 tap) | 722S 701 BREAKER MIN OIL HLD COMPLETE TESTING Breaker complete testing, PRC005 aux relays, trip coils relay testing | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 848L (17s Benalto - 848AL) | 2020-07-23 07:00 | 2020-07-23 17:00 | N | Y | scope of work includes installing a bridge along 848L between structures 204 and 207 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
EPCOR | 987s C72C1 (987s Clover Bar), 72CH9 (987s Clover Bar - Hardisty) | 2020-07-23 07:00 | 2020-07-23 17:00 | N | N | place CC24 into service | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 150L (42s Sarcee - 150AL) | 2020-07-23 07:15 | 2020-07-25 17:45 | N | N | maintenance on structures (112, 143, 144, 145, 146, 146A, 146B, 189, 189A) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2020-07-23 08:00 | 2020-07-26 16:00 | N | Y | move double structures on Sarcee Trail and HV breaker maintenance | Line |  |  | Pre-Condition
ATCO | 7L53 (706s Irish Creek - 7L53 tap) | 2020-07-23 08:00 | 2020-07-23 17:00 | N | N | insulator and arm changes | Line |  | Insulator and Arm Changes | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 65B240-D132 (ENMAX 65) | 2020-07-23 08:00 | 2020-07-23 11:00 | N | Y | SF6 sample, remove birds nest and add deterant | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 65B240-D130 (ENMAX 65) | 2020-07-23 11:00 | 2020-07-23 13:00 | N | Y | SF6 sample, remove birds nest and add deterant | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 65B240-D133 (ENMAX 65) | 2020-07-23 13:00 | 2020-07-23 16:00 | N | Y | SF6 sample, remove birds nest and add deterant | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 180L (255s Vulcan - 928s East Stavely) | 2020-07-24 09:00 | 2020-07-24 12:00 | N | Y | insulator wash program: structures 162s | Line |  |  | For Information Only
ATCO | 930s Syn Condenser (930s Arcenciel) | 2020-07-24 17:00 | 2020-07-27 16:00 | N | N | forced outage | Shunts |  |  | For Information Only
EPCOR | 72CH9 (987s Clover Bar - Hardisty) | 2020-07-25 07:00 | 2020-07-25 17:00 | N | N | Doble testing 72CH9 zone | Line | 72CH9 (987s Clover Bar - Hardisty) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
MONTANA | MATL (120s Picture Butte - Montana) | 2020-07-25 07:30 | 2020-07-26 16:00 | N | Y | align with 1201L outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2020-07-25 07:30 | 2020-07-26 16:00 | Y | Y | urgent repair; conductor repairs str435 | Line |  | 1201L (520s Bennett - BCH Cranbrook) MATL (120s Picture Butte - Montana) | 500 kV, Limits ATC, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 909L (89s Ellerslie - 665s Dome), 665s D2401 (665s Dome) | 2020-07-26 07:00 | 2020-08-04 17:00 | N | Y | doble, cutover, commissioning and energization then maintenance | Line, Circuit Breaker |  | doble, cutover, commissioning and energization of new S/S expansion for 72 kV upgrade | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
EPCOR | 557s 2403 (557s Castle Downs), 557s 2404 (557s Castle Downs), 557s T2 (557s Castle Downs) | 2020-07-27 07:00 | 2020-07-31 17:00 | N | Y | protection upgrade project | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
EPCOR | H725 (Hardisty Epcor) | 2020-07-27 07:00 | 2020-07-31 17:00 | N | N | breaker fail cutover | Circuit Breaker | Hardisty H725 (Hardisty Epcor) |  | For Information Only
EPCOR | 72CH11 (987s Clover Bar - Hardisty) | 2020-07-27 07:00 | 2020-07-28 17:00 | N | N | doble | Line | 72CH11 (987s Clover Bar - Hardisty) |  | For Information Only
EPCOR | 805s T1 (805s Jasper), 72JM18 (805s Jasper - Meadowlark), 72JW19 (805s Jasper - Woodcroft) | 2020-07-27 07:00 | 2020-07-31 17:00 | N | Y | doble | Transformer, Line | 805s T1 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
EPCOR | 987s CH724 (987s Clover Bar), H725 (Hardisty Epcor), 72CH11 (987s Clover Bar - Hardisty) | 2020-07-27 07:00 | 2020-08-27 17:00 | N | N | degassing | Circuit Breaker, Line | 72CH11 (Hardisty - 987s Clover Bar) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 879L (244s Bowmanton - 368s Burdett) | 2020-07-27 07:00 | 2020-07-30 18:00 | N | Y | insulator wash program structures 588 to 731 and 192 to 201 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 428s T2 (428s Namaka) | 2020-07-27 07:30 | 2020-07-28 18:30 | N | N | upgrade work for new 138kV bus protections | Transformer |  |  | For Information Only
ENMAXEC | 383s DVAR (383s Kettle Hill Windfarm) | 2020-07-27 08:00 | 2020-07-31 16:00 | N | N | forced outage (not modelled) | Shunts |  |  | For Information Only
ENMAX | 6.4TR (ENMAX 6) | 2020-07-27 08:00 | 2020-07-28 16:00 | N | N | ABB to inspect 6BA25-6.4TR shutters | Transformer |  |  | For Information Only
ENMAX | 41B138-41.84 (ENMAX 41), 54B138-41.84 (ENMAX 54), 41.84L (ENMAX 41 - ENMAX 54) | 2020-07-27 08:00 | 2020-07-29 16:00 | N | N | breaker maintenance | Circuit Breaker, Line | 41.84L (ENMAX 41 - ENMAX 54) | HV breaker maintenance 41B138-41.84. SF6 Sample 54B138-41.84 | Creates Radial Feeds, Firm Load Loss
ATCO | 7L24 (700s Bonnyville - 7L24D2) | 2020-07-27 08:00 | 2020-07-30 17:00 | N | Y | replace cross-arms, poles and ground rods | Line | 7L24 (700s Bonnyville - 7L24D2) | Replacing Cross-Arms, Poles and Ground Rod's | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 5.9TR (ENMAX 5) | 2020-07-27 08:00 | 2020-07-28 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
ENMAX | 2.1TR (ENMAX 2) | 2020-07-27 08:00 | 2020-07-29 16:00 | N | N | power factor test transformer | Transformer |  |  | For Information Only
ENMAX | 12.1TR (ENMAX 12) | 2020-07-27 08:00 | 2020-07-30 16:00 | N | N | tests and maintenance | Transformer |  | power factor test transformer, Transformer Secondary Cable Tests, Transformer Maintenance, Gas Relay Testing. Oil sampling MT, TC | For Information Only
ALTALINK | 708L (233s Beamer - 708AL) | 2020-07-27 09:00 | 2020-07-27 18:00 | N | N | components/structure replacements (structures #97 - 99) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition,Affects Cranking Path
REDDEER | 217s T1 (217s North Red Deer) | 2020-07-27 09:00 | 2020-07-29 15:30 | N | N | power factor dissipation testing including bushings | Transformer |  |  | For Information Only
ALTALINK | 170L (632s Russell - 799s Coleman) | 2020-07-27 09:00 | 2020-07-28 18:00 | N | Y | P5 170L24 urgent repair | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 835L (384s Keystone - 835AL) | 2020-07-27 09:30 | 2020-07-31 19:30 | N | N | moving structures | Line |  | Moving Strs 128, 129, 137, 138 and 139 | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ATCO | 7L113 (853s Ring Creek - 930s Arcenciel) | 2020-07-27 10:00 | 2020-08-02 16:00 | N | Y | line inspection and insulator change | Line |  | Line inspection and insulator change | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ATCO | 790s 701T (790s Poplar Hill) | 2020-07-27 10:00 | 2020-08-01 16:00 | N | N | leak severity repairs | Transformer |  | Leak severity repairs 790S 701T OOS | For Information Only
ALTALINK | 115S Mt.Allan, 76L (33s Spray - 115s Mt. Allan), 90L (32s Barrier - 115s Mt. Allan) | 2020-07-27 10:15 | 2020-07-28 17:45 | N | N | replace vacuum bottles and repair mech | Station, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK | 42s C2 (42s Sarcee), 42s C3 (42s Sarcee) | 2020-07-27 10:45 | 2020-07-29 17:15 | N | Y | repair trip latch and replace capacitors | Shunts |  | repair trip latch on center phase and replace 2 capacitors on C3 | 240 kV, Pre-Condition
ATCO | 828s 701T (828s Sulphur Point) | 2020-07-27 12:00 | 2020-07-30 12:00 | N | N | maintenance | Transformer |  | 828S SULPHUR POINT MAINTENANCE OUTAGE 7L72 & 7L93 Tied together for the duration of the work By 7L93D3 25kV Load tied to 791S via 5L461 & 5L462 for the duration of the work | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | D05 T2 (D05 Syncrude) | 2020-07-27 13:00 | 2020-07-27 20:00 | N | Y | urgent replace failed protections | Transformer |  |  | 240 kV, Creates Radial Feeds
ALTALINK | 163s T1 (163s Amoco Empress) | 2020-07-27 13:00 | 2020-07-30 15:30 | N | Y | maintain, doble, and install IDD | Transformer |  |  | 240 kV, For Information Only
ALTALINK | 283s T2 (283s Violet Grove) | 2020-07-27 13:00 | 2020-08-05 17:00 | N | N | maintenance & doble | Transformer | 283s T2 Maintenance & doble. Install Adapter for future Filter pack install, Replace T2. TC Filters. 283s T2 LA replacements both sides - High side due to Age and Low side to Metal Oxide Type |  | For Information Only
EPCOR | 557s 2406 (557s Castle Downs) | 2020-07-27 15:00 | 2020-07-28 18:00 | N | Y | emergency repair low SF6 | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354s DVAR1 (354s Summerview), 354s DVAR2 (354s Summerview) | 2020-07-28 07:00 | 2020-07-31 17:00 | N | Y | integration work for WindCharger | Shunts |  |  | For Information Only, Restricts Generation
ENMAX | 13.3TR (ENMAX 13) | 2020-07-28 08:00 | 2020-08-21 16:00 | N | N | arc flash mitigation project | Transformer |  | Arc Flash Mitigation Project. Protection outage and MV cable swap. Secondary cables attached to new switchgear on return. | For Information Only
ENMAX | 14.3TR (ENMAX 14) | 2020-07-28 08:00 | 2020-07-29 16:00 | N | N | check reversing switch | Transformer |  | T-60 Upgrade Phase 2. check reversing switch | For Information Only
CAPPOWERLP | ENC1 Cloverbar #1, ENC2 Cloverbar #2, ENC3 Cloverbar #3 | 2020-07-28 19:00 | 2020-07-28 23:00 | N | N | A business network switch will be replaced | Unit
ENMAX | 11.3TR (ENMAX 11) | 2020-07-29 08:00 | 2020-07-29 16:00 | N | N | CT ground wire to be rerun | Transformer |  |  | For Information Only
ENMAX | 5.10TR (ENMAX 5) | 2020-07-29 08:00 | 2020-07-30 16:00 | N | N | tapchanger inspection | Transformer |  |  | For Information Only
BLACKSPRING | 485s DVAR1 (485s Blacksprings), 485s DVAR2 (485s Blacksprings) | 2020-07-29 08:00 | 2020-07-29 17:00 | N | N | collect oil samples from DSATCOM transformers | Shunts |  | Feeder 7 outage to replace circuit breaker bushing. | Restricts Generation
ALTALINK | 179s T1 (179s Gleichen) | 2020-07-29 08:15 | 2020-07-30 16:45 | N | N | maintenance | Transformer |  | fix leaks, maintain, doble VR1 | For Information Only
ATCO | 790s 702T (790s Poplar Hill) | 2020-07-29 09:00 | 2020-07-30 17:00 | N | N | repair leaks | Transformer |  | Repair leaks at 790S Poplar Hill - Transformer 702T - CAT 1 - 20 Leak severity (switch out after 701T is switched back in) | For Information Only
ALTALINK, ATCO | 69s 230W (69s North Barrhead), 7L230 (69s North Barrhead - 7L230 tap) | 2020-07-29 09:00 | 2020-07-29 17:00 | N | Y | Maintenance | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
REDDEER | 217s T2 (217s North Red Deer) | 2020-07-29 15:31 | 2020-07-31 15:30 | N | N | power factor dissipation testing including bushings | Transformer |  |  | For Information Only
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2020-07-30 07:00 | 2020-07-31 17:00 | N | Y | urgent line clearance mitigation on structures #4 & 5 | Line |  |  | 240 kV, Contingency Requires Mitigation,Affects Cranking Path
ALTALINK | 676L (244s Bowmanton - 523s Bullshead) | 2020-07-30 07:00 | 2020-07-30 18:00 | N | Y | insulator wash program: structures 192 to 201 double circuit with 879L | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.4TR (ENMAX 11) | 2020-07-30 08:00 | 2020-07-30 16:00 | N | N | CT ground wire to be rerun | Transformer |  |  | For Information Only
ENMAX | 1.6TR (ENMAX 1) | 2020-07-30 08:00 | 2020-07-30 16:00 | N | N | remove hot collar strap from X0 bushing | Transformer |  |  | For Information Only
ALTALINK | 5s T1 (5s East Calgary) | 2020-07-30 08:15 | 2020-07-30 17:15 | N | Y | IDD investigate low voltage sensor issue | Transformer |  |  | 240 kV
ALTALINK | 55s T2 (55s Olds) | 2020-07-30 08:30 | 2020-07-30 16:00 | N | N | emergency oil leak repair | Transformer
ATCO | 7L130 (705s Kitscoty - 710s Vermilion) | 2020-07-30 08:30 | 2020-07-30 17:00 | N | N | required to relocate pole for new service road | Line |  | Required to relocate pole for new service road | Creates Radial Feeds
ALTALINK | 69s 723E (69s North Barrhead), 723L (69s North Barrhead - 724L) | 2020-07-30 09:00 | 2020-07-30 17:00 | N | N | maintenance & 1st trip testing | Circuit Breaker, Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L183 (856s Kinosis - 2060s Engstrom) | 2020-07-31 08:00 | 2020-07-31 16:00 | N | N | high-loads move into Conoco site | Line |  | We will require a GOI on 7L183 between Kinosis Sub and Engstrom Sub on July 31st. The outage is to accommodate high-loads moving into Conoco site. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 39.4TR (ENMAX 39) | 2020-07-31 08:00 | 2020-08-03 16:00 | N | N | reinhausen tapchanger maintenance, oil sampling | Transformer | 39.4TR (ENMAX 39)
SUNCOR | 635PL7-1003 (635EDD-1000 - 635EDD-1004), 635EDD-1000 635-752-162 (635EDD-1000), 635EDD-1000 635-752-163 (635EDD-1000) | 2020-07-31 08:00 | 2020-08-07 17:00 | N | N | maintenance of powerline, transformer protection and breaker failure protection | Line, Circuit Breaker
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon) | 2020-07-31 08:00 | 2020-08-02 17:00 | N | N | urgent work on structures | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 10.2TR (ENMAX 10) | 2020-07-31 08:00 | 2020-08-06 16:00 | N | N | investigate noise | Transformer
ATCO, SHELL | 847s 902T (847s Muskeg River), 847s 903 (847s Muskeg River), 847s 904 (847s Muskeg River) | 2020-07-31 12:00 | 2020-07-31 16:00 | N | Y | testing | Transformer, Circuit Breaker |  | CNRL is requesting assistance with 260kV line switching at the 847S Muskeg River substation for the purpose of testing. July 31st 12:00pm  ATCO to Open breaker 903 at the Muskeg River 847S substation July 31st  After 903 breaker is confirmed open, CNRL will request ATCO open 904 breaker at 847S substation to put GT-2 in an island state July 31st 14:00  Muskeg River CRO will re-synchronize breaker 904 at the Muskeg River 847S substation July 31st  After 904 is closed CNRL will request ATCO close 903 breaker at the Muskeg River 847S substation | 240 kV, Restricts Generation
ALTALINK | 726L (37s North Calder - 71s Lamoureux) | 2020-08-01 07:00 | 2020-08-02 18:00 | N | N | modifying structures #8, 55 - 58, 82 & 82A to make line clearance repairs to 920L | Line |  | Modifying Structures #8, 55 - 58, 82 & 82A to make line clearance repairs to 920L | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 22B138-22.81 (ENMAX 22), 39B138-22.81 (ENMAX 39), 22.81L (ENMAX 22 - ENMAX 39) | 2020-08-01 08:00 | 2020-08-02 18:00 | N | N | reinhausen tapchanger maintenance | Circuit Breaker, Line | 22.81L (ENMAX 22 - ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2020-08-01 08:15 | 2020-08-01 12:45 | N | Y | insulator wash program structures 544, 545 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ATCO | 847s 902T (847s Muskeg River) | 2020-08-02 18:00 | 2020-08-10 18:00 | N | Y | customer maintenance | Transformer |  | CNRL Albian Sands - Request for a Condition guarantee from ATCO to isolate 902T | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
EPCOR | 557s 2401 (557s Castle Downs), 557s 2406 (557s Castle Downs), 557s T1 (557s Castle Downs) | 2020-08-03 07:00 | 2020-08-07 17:00 | N | Y | protection upgrade project | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 31.2TR (ENMAX 31) | 2020-08-03 08:00 | 2020-08-06 16:00 | N | N | tapchanger maintenance | Transformer |  | Reinhausen Tapchanger Maintenance. Oil sampling MT, TC | For Information Only
Syncrude | Aurora T3 (Aurora) | 2020-08-03 08:00 | 2020-08-23 20:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
ATCO | 9L19 (937s AMR02 - 960s Birchwood Creek) | 2020-08-03 08:00 | 2020-08-07 05:00 | N | Y | disconnect switch maintenance | Line |  | Customer request - Disconnect Switch Maintenance | 240 kV, Creates Radial Feeds, Firm Load Loss
ENMAX | 11B138-11.81 (ENMAX 11), 13B138-11.81 (ENMAX 13), 11.81L (ENMAX 11 - ENMAX 13) | 2020-08-03 08:00 | 2020-08-21 16:00 | N | N | arc flash mitigation project line protection upgrade | Circuit Breaker, Line | 11.81L (ENMAX 13 - ENMAX 11) | Line Protection Upgrade. Control cable swap out. Arc Flash Mitigation Project. | For Information Only
ALTALINK | 150s 223N (150s Clyde), 159s 223 (159s Colinton), 223L (150s Clyde - 159s Colinton) | 2020-08-03 09:30 | 2020-08-21 18:30 | N | N | install new structures | Circuit Breaker, Line | 223L (150s Clyde - 159s Colinton) | New 223L Span from 223L0A to New Steel A-Frame/Deadend in 150s. New 150s24 Switch, New 138kV CT's for breaker 150s223N, Move 150s223N Breaker to new structure, Recommission breaker after moving. Replace 223L A/B Protections and 150s223N Breaker Fail Relays | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 658L (562s Cypress - 649s Chappice Lake) | 2020-08-03 20:47 | 2020-08-05 17:00 | N | N | forced outage due to lightening | Line |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 801s 907 (801s Anderson) | 2020-08-04 07:00 | 2020-08-06 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | 801S Anderson 907 BREAKER MIN OIL HLR PARTIAL TESTING BKR 907 Partial Maint. SHEERNESS UNIT 1 TIED TO SYSTEM BY BKR 906 ONLY | 240 kV, Contingency Requires Mitigation
ALTALINK | 744L (235s Entwistle - 744AL) | 2020-08-04 07:00 | 2020-08-06 18:00 | N | N | replace structures | Line |  | Replace 744L Str 42 and modify Str 43, 70, 71 | Creates Radial Feeds, Firm Load Loss
VISIONREQ | 354S Summerview | 2020-08-04 07:00 | 2020-08-07 17:00 | N | Y | integration work for windcharger | Station |  |  | Restricts Generation
ALTALINK, ENMAX | 916L (5s East Calgary - 42s Sarcee), 693L (42s Sarcee - ENMAX 10) | 2020-08-04 07:15 | 2020-08-06 17:45 | N | Y | maintenance on str 15 | Line | Wind and Shepard (EGC1) has no impact on overloads for next contingencies. | scope of includes maintenance on str 15, crews are milling overtop of UG cables | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Affects Cranking Path
ALTALINK | 733L (151s Strathmore - 428S Namaka) | 2020-08-04 07:15 | 2020-08-07 18:45 | N | N | protection upgrades, breaker & switch maintenance & modify reclose logic | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 138s 603 (138s Windy Flats), 603L (138s Windy Flats - 243s Soderglen Wind Farm) | 2020-08-04 07:30 | 2020-08-04 17:30 | N | Y | 138 kV switch maintenance by customer | Switch, Line | 603L (138s Windy Flats - 243s Soderglen Wind Farm) |  | Restricts Generation
TRANSALTA | Summerview Battery Storage Generator Test | 2020-08-04 08:00 | 2020-08-14 16:00 | N | N | commissioning | Unit
ENMAX, ALTALINK | 24.83L (74s Janet - ENMAX 24) | 2020-08-04 08:00 | 2020-09-13 16:00 | N | Y | transmission line relocate | Line | Wind and Shepard (EGC1) has no impact on overloads for next contingencies. |  | Over/Under Voltage, Pre-Condition
GWPCORP | 243s T1 (243s Soderglen Wind Farm) | 2020-08-04 08:00 | 2020-08-04 18:00 | N | Y | substation maintenance | Transformer | 243s T1 (243s Soderglen Wind Farm) |  | Restricts Generation
BLACKSPRING | 485s DVAR1 (485s Blacksprings), 485s DVAR2 (485s Blacksprings) | 2020-08-04 08:00 | 2020-08-06 17:00 | N | N | maintenance | Shunts |  | Feeder 7 outage to replace circuit breaker bushing. | Pre-Condition
EPCOR | RR723 (Rossdale) | 2020-08-04 09:00 | 2020-08-28 17:00 | N | N | breaker replacement | Circuit Breaker | Rossdale RR723 (Rossdale) |  | For Information Only
ALTALINK | 786L (799s Coleman - BCH Natal) | 2020-08-04 09:00 | 2020-08-14 18:00 | N | Y | P5 786L urgent repair str's range 76-117 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 798L (77s Sagitawah - 364s Whitecourt Industrial) | 2020-08-04 09:30 | 2020-08-07 17:30 | N | N | line clearance mitigation | Line |  | Line clearance mitigation Str's Range Str's 54-58 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-08-04 10:00 | 2020-08-10 15:00 | N | Y | x-arm change out | Line |  | XARM change out | Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation, Affects Cranking Path
ATCO | 794s 701T (794s Valleyview) | 2020-08-04 11:00 | 2020-08-06 17:00 | N | N | repair leak | Transformer |  | Repair leak on 701T, all load transferred to 702T | For Information Only
ALTALINK | 421s 795N (421s Hays), 795L (121s Brooks - 421s Hays) | 2020-08-04 12:00 | 2020-08-04 18:00 | N | N | change CT ratio on CT1 as per SysOps request | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L701 (223s Strome - 7L701D1), 7L701 (757s Battle River - 7L701D1) | 2020-08-04 18:00 | 2020-08-06 17:00 | N | N | forced outage due to lightning | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 747L (99s North St. Albert - 711L) | 2020-08-05 06:00 | 2020-08-06 18:30 | N | N | installation of foundations for new control building | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 39.1TR (ENMAX 39) | 2020-08-05 07:00 | 2020-08-05 18:00 | N | N | roxtec installation | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK, EPCOR | 310p 1352 (310p Sundance), 310p 1452 (310p Sundance), 909L (310p Sundance - 665s Dome) | 2020-08-05 07:00 | 2020-08-10 17:00 | N | Y | line maintenance | Circuit Breaker, Line | 909L (310p Sundance - 665s Dome) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
GWPCORP | 243s T1 (243s Soderglen Wind Farm) | 2020-08-05 07:00 | 2020-08-05 17:00 | N | Y | substation maintenance | Transformer | 243s T1 (243s Soderglen Wind Farm) |  | Restricts Generation
ENMAX | 33.1TR (ENMAX 33) | 2020-08-05 08:00 | 2020-08-08 16:00 | N | N | reinhausen tapchanger maintenance | Transformer |  |  | For Information Only
ALTALINK | 63s 2652 (63s Red Deer), 63s 2752 (63s Red Deer), 1082L (63s Red Deer - 287s Hazelwood) | 2020-08-05 08:00 | 2020-08-06 16:00 | N | Y | modify synch check logic and test | Circuit Breaker, Line |  | Modify synch check logic on breaker 63S2752 and remove PLC reclosing on 63S2652. Test L7  1082L reclosing and synch logic after completing modifications. | 240 kV
ENMAX | 39.2TR (ENMAX 39) | 2020-08-06 07:00 | 2020-08-06 18:00 | N | N | roxtec installation. | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 1041L (370s North Lethbridge - 554s Travers) | 2020-08-06 07:15 | 2020-08-06 17:45 | N | Y | maintenance on Str 1041L254 | Line |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 418s T1 (418s Ardenville) | 2020-08-06 08:00 | 2020-08-07 12:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
ENMAX | 33B138-33.84 (ENMAX 33), 43B138-33.84 (ENMAX 43), 33.84L (ENMAX 33 - ENMAX 43) | 2020-08-06 08:00 | 2020-08-07 16:00 | N | N | reinhausen tapchanger maintenance | Circuit Breaker, Line |  | Reinhausen Tapchanger Maintenance. 33.84L outage required. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L24 (700s Bonnyville - 7L24D2) | 2020-08-06 08:00 | 2020-08-07 17:00 | N | Y | replacing cross-arms, poles and ground rods | Line | 7L24 (700s Bonnyville - 7L24D2) | Replacing Cross-Arms, Poles and Ground Rod's | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 763L (158s Vauxhall - 763AL) | 2020-08-06 13:00 | 2020-08-14 18:00 | N | N | urgent line clearance | Line |  | Urgent Line Clearance Structure Changes 763L ( Structures range 322-406) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 848L (17s Benalto - 848AL) | 2020-08-07 07:00 | 2020-08-07 17:00 | N | Y | install a bridge along 848L between structures 204 and 207 | Line |  | Scope of work includes installing a bridge along 848L between structures 204 and 207 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 604L (149s Nisku - 155s Blackmud) | 2020-08-07 08:00 | 2020-08-07 12:00 | N | N | maintenance | Line |  | Scope of work includes maintenance Str 3 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 418s T2 (418s Ardenville) | 2020-08-07 12:00 | 2020-08-08 18:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
SUNCOR | 635EDD-1000 635PK-1001 (635EDD-1000), 635EDD-1000 635-752-161 (635EDD-1000), 635EDD-1000 635-752-162 (635EDD-1000) | 2020-08-07 17:00 | 2020-08-13 17:00 | N | N | maintenance | Shunts, Circuit Breaker |  | maintenance of 635PK-1001 capacitor bank protection and breaker failure protection of 635-752-161/162; Maintenance of 635PK-1001 capacitor bank, 144kV breakers, disconnects and CVTs | For Information Only
ALTALINK | 744L (228s T.M.P.L.Niton - 744AL) | 2020-08-08 07:00 | 2020-08-11 18:00 | N | N | modify 744L str 108, 109, 117, 118, 130 and 131 | Line |  | Modify 744L Str 108, 109, 117, 118, 130 and 131 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2020-08-08 08:00 | 2020-08-08 17:00 | N | Y | maintenance on strs 2, 7 and 17 | Line |  | Scope of work includes maintenance on strs 2, 7 and 17 | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 514L (513s Lundbreck - 514BL) | 2020-08-09 07:00 | 2020-08-14 18:00 | N | N | maintenance work on strs 201 - 447 | Line |  | Description/Scope: Scope of work includes maintenance Scope of work includes maintenance work on Strs 201 - 447 | For Information Only
ALTALINK | 528s T1 (528s Blue Trail Wind Farm) | 2020-08-09 07:00 | 2020-08-10 12:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
EPCOR | 803s T1 (803s Lambton) | 2020-08-10 07:00 | 2020-08-14 17:00 | N | Y | doble / SFRA | Transformer | 803s T1 (803s Lambton) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
EPCOR | 557s T2 (557s Castle Downs) | 2020-08-10 07:00 | 2020-08-12 17:00 | N | Y | protection upgrade project | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
EPCOR | 805s T3 (805s Jasper) | 2020-08-10 07:00 | 2020-08-21 17:00 | N | Y | DGA monitor | Transformer | 805s T3 (805s Jasper) |  | 240 kV, For Information Only
ALTALINK | 428s 733X (428s Namaka), 733L (179s Gleichen - 428s Namaka) | 2020-08-10 07:30 | 2020-08-13 18:30 | N | N | protection upgrades | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2020-08-10 08:00 | 2020-08-10 16:00 | N | N | breaker maintenance | Shunts |  |  | For Information Only
ALTALINK | 37s 88 (37s North Calder) | 2020-08-10 08:00 | 2020-08-10 17:00 | N | Y | complete wiring, commissioning and function testing for reclosing circuit | Circuit Breaker |  | complete wiring, commissioning and function testing for reclosing circuit for breaker 37s88 (2152). Changes are to accommodate new sync check logic. | 240 kV, Contingency Requires Mitigation
ENMAX | 5.9TR (ENMAX 5) | 2020-08-10 08:00 | 2020-08-14 18:30 | N | N | plastibeton tray replacement | Transformer |  |  | For Information Only
ATCO | 7L24 (846s Grand Centre - 7L24D3) | 2020-08-10 08:00 | 2020-08-13 17:00 | N | Y | replacing cross-arms, poles and ground rod's | Line | 7L24 (846s Grand Centre - 7L24D3) | Replacing Cross-Arms, Poles and Ground Rod's | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Aurora 11 (Aurora), Aurora 12 (Aurora), Aurora 13 (Aurora) | 2020-08-10 08:00 | 2020-08-23 20:00 | N | Y | operate breaker and switch | Circuit Breaker |  |  | Restricts Generation
ENMAX | 37.2TR (ENMAX 37) | 2020-08-10 08:00 | 2020-08-13 16:00 | N | N | reinhausen tapchanger maintenance | Transformer |  |  | For Information Only
ATCO | 801s 906 (801s Anderson) | 2020-08-10 08:30 | 2020-08-13 16:00 | N | Y | breaker min oil, HLR complete testing | Circuit Breaker |  | 801S Anderson 906 BREAKER MIN OIL HLR COMPLETE TESTING SHEERNESS UNIT 1 TIED TO SYSTEM BY BKR 907 ONLY | 240 kV, Contingency Requires Mitigation
ALTALINK | 71s 1652 (71s Lamoureux) | 2020-08-10 09:00 | 2020-08-21 18:00 | N | Y | replacing M/O breaker with a new SF6 Breaker | Circuit Breaker |  |  | Contingency Requires Mitigation, For Information Only
REDDEER | 194s T2 (194s South Red Deer) | 2020-08-10 09:00 | 2020-08-14 15:30 | N | N | on load tap changer testing and overhaul | Transformer | 194s T2 (194s South Red Deer) |  | For Information Only
ALTALINK | 174L (197s Bardo - 395s North Holden) | 2020-08-10 09:30 | 2020-08-24 18:15 | N | N | re-build from structure 486 to 539 | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 879s 702T (879s Scotford Upgrader) | 2020-08-10 10:00 | 2020-08-13 16:00 | N | Y | 35 kV B bus maintenance and Basler relay testing | Transformer |  | 35 kV B Bus Maintenance " Scheduled for August 12, 2020 " 702T will be isolated August 10th, 2020 as originally planned and restored August 13th, 2020 " Basler relay testing will be coordinated with the transformer restoration on August 13th done on Bkr 252, Bkr 352, & 702TD Bkrs 252 & 352 must be opened prior to opening 702TD | Pre-Condition
ALTALINK | 262s T1 (262s Rocky Mountain House) | 2020-08-10 11:00 | 2020-08-14 18:00 | N | N | 138 kV & 25 kV bushings and 138 kV & 25 kV LAs (T1) & bird cover | Transformer | 262s T1 (262s Rocky Mountain House) |  | For Information Only
ALTALINK | 776L (308s Albchem Beaverhill Creek - 410s Josephburg), 773L (127s Bruderheim - 308s Albchem Beaverhill Creek), 308S Albchem Beaverhill Creek | 2020-08-10 12:00 | 2020-08-16 18:00 | N | N | replace the RTU | Line, Station |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 391s T1 (391s Balzac) | 2020-08-10 12:00 | 2020-08-13 17:30 | N | N | perform 1st trip on 391s9 and PRC 5 tests on 391s30, replace T1 high side bushing, doble, SFRA & tapchanger maintenance | Transformer |  | perform 1st trip on 391s9 and PRC 5 tests on 391s30, replace T1 high side bushing, doble, SFRA & tapchanger maintenance | For Information Only
ALTALINK | 528s T2 (528s Blue Trail Wind Farm) | 2020-08-10 12:00 | 2020-08-11 18:00 | N | Y | maintenance | Transformer |  |  | Restricts Generation
ALTALINK | 157s T1 (157s Lac La Biche) | 2020-08-10 12:15 | 2020-08-16 17:45 | N | N | maintenance, oil reclaim (T1), leak repairs, & VR1 pad repair | Transformer |  |  | For Information Only
ALTALINK | 797L (268s Whitecourt - 364s Whitecourt industrial) | 2020-08-10 12:30 | 2020-08-16 17:30 | N | N | line clearance mitigation str's range 6-64 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 786s SVC (786s High Level) | 2020-08-11 06:30 | 2020-08-11 17:00 | N | Y | complete spring maintenance and software upgrade | Shunts |  | 786S SPRING SVC AIR COOLED MAINTENANCE Complete Spring Maintenance and Software Upgrade SVC Out of Service for the Duration of the Work | Pre-Condition
ENMAX | 28.1TR (ENMAX 28) | 2020-08-11 08:00 | 2020-08-11 16:00 | N | N | Arc Flash Mitigation Project | Transformer |  |  | For Information Only
REDDEER | 217s T1 (217s North Red Deer) | 2020-08-11 08:00 | 2020-08-14 17:00 | N | N | forced outage | Transformer |  |  | For Information Only
ALTALINK | 336s T1 (336s Fincastle) | 2020-08-11 08:00 | 2020-08-12 15:00 | N | N | install bird cover on T1, VR1 and associated 25kV Bus 1 equipment. | Transformer |  |  | For Information Only
ATCO | 7L32 (813s Little Smoky - 862s South Bezanson) | 2020-08-11 08:00 | 2020-08-11 17:00 | N | Y | complete FAC-008 violation mitigation | Line |  | To complete FAC-008 violation mitigation | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 37s 82 (37s North Calder) | 2020-08-11 08:00 | 2020-08-11 17:00 | N | Y | complete wiring, commissioning and function testing for reclosing circuit | Circuit Breaker |  | Complete wiring, commissioning and function testing for reclosing circuit for breaker 37s82 (2252). Changes are to accommodate new sync check logic. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 575s 719N (575s Sundre) | 2020-08-11 09:00 | 2020-08-11 14:00 | N | Y | upgrade MPLS node @ 575s | Circuit Breaker |  | upgrade MPLS node @ 575s. Breaker open required for system stability due to loss of 719L (378s-575s) A & B TPR. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 521AL (867s Sundance Blow-Down - 521L), 521L (505L - 512L) | 2020-08-12 07:00 | 2020-08-13 17:00 | N | N | maintenance on structures 51, 53, 54, 55, 56, 57, 58, 60A, 61A, 62, 63, 65, and 66 | Line |  | Scope of work includes maintenance on Structures 51, 53, 54, 55, 56, 57, 58, 60A, 61A, 62, 63, 65, and 66 | For Information Only
ENMAX | 40.1TR (ENMAX 40) | 2020-08-12 07:00 | 2020-08-12 18:00 | N | N | roxtec installation | Transformer |  |  | For Information Only
ENMAX | 9.3TR (ENMAX 9) | 2020-08-12 08:00 | 2020-08-28 16:00 | N | N | arc flash mitigation project protection outage and MV cable swap | Transformer |  | arc flash mitigation project. Protection outage and MV cable swap. | For Information Only
BLACKSPRING | 485S Black Springs | 2020-08-12 08:00 | 2020-08-13 17:00 | N | N | feeder 7 outage to replace circuit breaker bushing | Station |  |  | Restricts Generation
ENMAX | 3.3TR (ENMAX 3) | 2020-08-12 08:00 | 2020-08-15 16:00 | N | N | Reinhausen tapchanger maintenance, oil sampling MT, TC, check reversing switch | Transformer |  | Reinhausen Tapchanger Maintenance. Oil sampling MT, TC. Check reversing switch. | For Information Only
ENMAX | ENMAX 8 | 2020-08-12 08:00 | 2020-08-17 11:00 | N | N | DCTRP. highpot test 2.84L | Station |  | DCTRP. Highpot test 2.84L. 8B138-7a0. 8B138-1a0. PT-E7 | For Information Only
ALTALINK | 37s 76 (37s North Calder) | 2020-08-12 08:00 | 2020-08-12 17:00 | N | Y | complete wiring, commissioning and function testing for reclosing circuit | Circuit Breaker |  | Complete wiring, commissioning and function testing for reclosing circuit for breaker 37s76 (2352). Changes are to accommodate new sync check logic. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 102s SVC (102s Langdon) | 2020-08-12 08:15 | 2020-08-13 17:15 | N | Y | spray and pull weeds in the SVC fenced area, glycol leak repairs | Shunts |  | spray and pull weeds in the SVC fenced area, Glycol leak repairs | 240 kV
ATCO | 930s SVC (930s Arcenciel) | 2020-08-12 09:00 | 2020-08-12 17:00 | N | Y | maintenance and software upgrade | Shunts |  | 930S SPRING 2020 SVC AIR COOLED MAINTENANCE Complete Spring Maintenance and Software Upgrade SVC Out of Service for the Duration of the Work | Pre-Condition
ENMAX | 40.2TR (ENMAX 40) | 2020-08-13 07:00 | 2020-08-13 18:00 | N | N | roxtec installation | Transformer |  |  | For Information Only
SUNCOR | 635EDD-1000 PT-1000 (635EDD-1000), 635EDD-1000 635-752-111 (635EDD-1000), 635EDD-1000 635-752-121 (635EDD-1000), 635EDD-1000 635-752-131 (635EDD-1000), 635EDD-1000 635-752-142 (635EDD-1000), 635EDD-1000 635-752-152 (635EDD-1000), 635EDD-1000 635-752-161 (635EDD-1000), 635EDD-1000 635-752-162 (635EDD-1000) | 2020-08-13 07:00 | 2020-08-13 18:00 | N | N | maintenance | Transformer, Circuit Breaker |  | maintenance of 635PK-1001 capacitor bank protection and breaker failure protection of 635-752-161/162; Maintenance of 635PK-1001 capacitor bank, 144kV breakers, disconnects and CVTs | For Information Only
ALTALINK | 737L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2020-08-13 07:00 | 2020-08-13 18:00 | N | N | line clearance mitigation | Line |  | Urgent line clearance mitigation on Structure #13 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 37s 81 (37s North Calder) | 2020-08-13 08:00 | 2020-08-13 17:00 | N | Y | complete wiring, commissioning and function testing for reclosing circuit | Circuit Breaker |  | Complete wiring, commissioning and function testing for reclosing circuit for breaker 37s81 (2552). Changes are to accommodate new sync check logic. | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 162s 138-RB80 (162s Beddington) | 2020-08-13 08:00 | 2020-08-13 16:00 | N | N | breaker maintenance | Circuit Breaker |  | HV Breaker maintenance 162B138-RB80. Dashpot checks. SF6 sample | Contingency Requires Mitigation, For Information Only
SHELL | 847s 901T (847s Muskeg River) | 2020-08-13 08:00 | 2020-08-16 08:00 | N | Y | customer maintenance | Transformer |  | CNRL Albian Sands - Request for a Condition guarantee from ATCO to isolate 901T | 240 kV, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 922L (17s Benalto - 310p Sundance) | 2020-08-14 07:15 | 2020-08-14 17:45 | N | Y | maintenance on str 461 | Line |  | Scope of includes maintenance on Str 461 | 240 kV,Affects Cranking Path
Syncrude | SCL1 Syncrude #1 | 2020-08-14 08:00 | 2020-09-14 16:00 | N | N | Aurora G20 modification (upgrade controller). P2332. ISD August 21, 2020 | Unit
ALTALINK | 172s T1 (172s Sherritt Gordon) | 2020-08-15 07:00 | 2020-08-15 13:00 | N | N | customer repairs to their 172s23 Breaker | Transformer
ALTALINK | 166L (256s Harmattan - 166AL) | 2020-08-15 07:15 | 2020-08-17 17:45 | N | Y | scope of work including moving and replacing structures 109 and 110 and adding new str 109A | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 523s T1 (523s Bullshead) | 2020-08-15 07:30 | 2020-08-16 17:30 | N | N | repair AMI structure and replace 523s T1 LAs | Transformer
SUNCOR | 29EDD-55 29Edd-55 | 2020-08-16 08:00 | 2020-08-25 18:00 | N | N | bus outage 29PP-37D, 29PT-165 | Station | Suncor 29EDD-55
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2020-08-16 08:00 | 2020-08-16 16:00 | N | N | power factor test HV breaker 5B138-2.82 | Line |  |  | For Information Only
ALTALINK | 523S Bullshead | 2020-08-16 15:30 | 2020-08-20 16:00 | N | N | 523s406W 25kV breaker replacement | Station
ATCO | 2029s ACF14 (2029s Heathfield) | 2020-08-17 07:00 | 2020-08-24 20:45 | N | Y | trip coil testing | Shunts | 2029s ACF14 (2029s Heathfield) | PRC-005 - Trip Coil Testing - Breaker 1221-A @ 2029S Breaker 1221 (10BF14) @ 2029S Filter will be unavailable, One device worked on at a time Depending on power transfer level, reduce voltage mode will be activated. | 500 kV
Saskpower | Sask Power PR901 | 2020-08-17 07:00 | 2020-08-21 17:00 | N | Y | transformer & switch maintenance | Circuit Breaker |  |  | Limits ATC
EPCOR | T2 (Rossdale) | 2020-08-17 07:00 | 2020-08-23 17:00 | N | N | outage for UGD | Transformer |  |  | For Information Only
EPCOR | 803s T2 (803s Lambton), 803s L2402 (803s Lambton), 803s L2405 (803s Lambton) | 2020-08-17 07:00 | 2020-08-21 17:00 | N | Y | doble/ SFRA T2 | Transformer, Circuit Breaker | 803s T2 (803s Lambton) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
EPCOR | 805s T3 (805s Jasper), 805s J2404 (805s Jasper), 805s J2405 (805s Jasper) | 2020-08-17 07:00 | 2020-08-21 17:00 | N | Y | Doble T3 | Transformer, Circuit Breaker | 805s T3 (805s Jasper) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 914L (86s Bigstone - 87s Gaetz), 87s 1252 (87s Gaetz) | 2020-08-17 07:15 | 2020-08-20 17:45 | N | Y | SCADA upgrade | Line, Circuit Breaker | 914L (86s Bigstone - 87s Gaetz) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Affects Cranking Path
ALTALINK | 276s T2 (276s Union Carbide Prentiss) | 2020-08-17 07:15 | 2020-08-28 11:00 | N | N | CT upgrade | Transformer |  | T2(TX18471) upgrade CT12 to high ration CTs. | For Information Only
ALTALINK | 19s T8 (19s Wabamun), 19S Wabamun 69kV Bus, 133L (19s Wabamun - 234L), 124L (19s Wabamun - 2739s Wabamun), 123L (19s Wabamun - 352s Onoway), 2739S Wabamun, 352S Onoway | 2020-08-17 07:30 | 2020-08-24 14:30 | N | N | replace 19s125 and install SAs for 19s123 & 19s124 | Transformer, Bus, Line, Station |  |  | Firm Load Loss, Pre-Condition
ALTALINK | 428s T1 (428s Namaka) | 2020-08-17 07:30 | 2020-08-21 18:30 | N | N | Upgrade existing protections, LA replacement, bird cover install | Transformer |  | Upgrade existing T1 protections, LA replacement, bird cover install | For Information Only
ATCO | 848s 903 (848s Ruth Lake) | 2020-08-17 08:00 | 2020-08-21 17:00 | N | Y | replace CT | Circuit Breaker |  | 2020 848S 903CT REPLACEMENT/ COMMISSIONING Replace 903CT at 848S Ruth Lake 903 Breaker/903CT OOS at 848S Ruth Lake | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 1080L (ENMAX 25 - ENMAX 65), 25B240-D138 (ENMAX 25), 25B240-D139 (ENMAX 25) | 2020-08-17 08:00 | 2020-08-17 18:00 | N | Y | power factor test HV LA 25MD240-1080. | Line, Circuit Breaker |  |  | 240 kV, For Information Only
ENMAX | 2.84L (ENMAX 2 - ENMAX 8) | 2020-08-17 08:00 | 2020-08-27 16:00 | N | N | P1456 DCTRP. ISD August 18, 2020 | Line
ATCO | 7L24 (846s Grand Centre - 7L24D3) | 2020-08-17 08:00 | 2020-08-20 17:00 | N | Y | replacing cross arms, poles and ground rods | Line | 7L24 (846s Grand Centre - 7L24D3) | Replacing Cross-Arms, Poles and Ground Rod's | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 23.4TR (ENMAX 23) | 2020-08-17 08:00 | 2020-09-04 16:00 | N | N | protection outage and MV cable swap | Transformer |  | Arc Flash Mitigation Project. Protection outage and MV cable swap. Cables attached to new switchgear on return. Phasing required | For Information Only
ATCO | 743s 701T (743s Sarah Lake) | 2020-08-17 08:00 | 2020-08-18 08:00 | N | N | replace breaker | Transformer |  |  | Pre-Condition
ATCO | 770s 704 (770s Three Hills), 7L159 (770s Three Hills - 7L159 tap) | 2020-08-17 08:00 | 2020-08-17 17:00 | N | N | protection upgrade | Circuit Breaker, Line |  | 770S Protection Upgrade - 704 Test and Operate Test and operate on breaker 704 to move alarm circuits to new SCADA system from old PLC system. Permit will be required to test trip coil for PRC-005. Line protection settings will be updated on A and B protection to change soft alarm descriptors. Each line protection relay (A and B) will only be isolated while the other is in service due to tele-protection being in place. 7L159 will be open at 770S Three Hills end. Line protection will be isolated, one relay at a time. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 34B69-16.60 (ENMAX 34), 16.60L (ENMAX 16 - ENMAX 34) | 2020-08-17 08:00 | 2020-08-17 16:00 | N | N | power factor test HV breaker. 34B69-16.60 | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
Syncrude | Mildred T19 (Syncrude Mildred Lake) | 2020-08-17 08:00 | 2020-08-31 20:00 | N | N | 72/13.8KV transformer & capacitor bank outage (31-0-PC15-2) - Plant 31 Powerhouse | Transformer |  |  | For Information Only
ATCO | 849s 901 (849s Joslyn Creek) | 2020-08-17 08:15 | 2020-08-17 10:30 | N | Y | trip coil testing | Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 901 @ 849S BREAKER 901 OOS | 240 kV, Contingency Requires Mitigation
ATCO | 801s 909 (801s Anderson) | 2020-08-17 08:30 | 2020-08-20 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | Complete Breaker Maintenance, Ring Bus 910 Breaker in service | 240 kV, Contingency Requires Mitigation
ALTALINK | 763L (158s Vauxhall - 763AL) | 2020-08-17 09:00 | 2020-08-20 15:05 | N | N | urgent line clearance: change structures range 322-406 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L172 (739s Edith Lake - 743s Sarah Lake), 743s 704 (743s Sarah Lake) | 2020-08-17 10:00 | 2020-08-17 12:00 | N | N | breaker trip coil maintenance | Line, Circuit Breaker |  | PRC-005 - Breaker Trip Coil Maintenance, 704 at 743S Test PRC Trip Coils Open end 7L172 | For Information Only
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-08-17 10:00 | 2020-08-24 15:00 | N | Y | x-arm change out | Line |  | XARM change out | Creates Radial Feeds, Firm Load Loss, Overload, Restricts Generation, Affects Cranking Path
ATCO | 849s 902 (849s Joslyn Creek) | 2020-08-17 10:45 | 2020-08-17 13:30 | N | Y | trip coil testing | Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 902 @ 849S BREAKER 902 OOS | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 262s T2 (262s Rocky Mountain House) | 2020-08-17 11:00 | 2020-08-20 18:00 | N | N | bushings, LAs and bird cover | Transformer | 262s T2 (262s Rocky Mountain House) | 138 kV & 25 kV bushings and 138 kV & 25 kV LAs (T2) & Bird Cover | For Information Only
ATCO | 743s 605 (743s Sarah Lake) | 2020-08-17 12:00 | 2020-09-04 11:00 | N | N | replacing breaker | Circuit Breaker |  | Replacing breaker 605, 605A & 605B @ 743S Sarah Lake | Over/Under Voltage, Pre-Condition
ALTALINK | 226S Garden City | 2020-08-17 12:15 | 2020-08-19 19:00 | N | N | network connection repair | Station |  |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2020-08-17 12:30 | 2020-08-20 17:30 | N | N | component replacements including poles on Str's 1-195 | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 514L (396s Pincher Creek - 514BL) | 2020-08-18 07:00 | 2020-08-20 18:00 | N | Y | maintenance between Strs 2 & 195 | Line |  |  | Pre-Condition, Restricts Generation
ALTALINK | 336s T2 (336s Fincastle) | 2020-08-18 08:00 | 2020-08-19 13:00 | N | N | replace temp SS2 Tx to permanent one, complete bird cover on SS2 TX and 25kV UG bus structure, repair 336s1452 | Transformer |  |  | For Information Only
ATCO | 743s 702T (743s Sarah Lake) | 2020-08-18 08:00 | 2020-08-31 12:00 | N | N | replacing breaker 605, 605A & 605B | Transformer |  | Replacing breaker 605, 605A & 605B @ 743S Sarah Lake GOI on 702T to de energize over head lines in order to safely move new breaker 605 in & out. | Pre-Condition
ALTALINK | 221s T3 (221s Sunken Lake) | 2020-08-18 08:00 | 2020-08-18 16:00 | N | N | customer installing wildlife cover-up | Transformer |  |  | For Information Only
ALTALINK | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-08-18 08:00 | 2020-08-18 16:00 | N | N | installing replacement surge arrestor on the cap bank CT neutral | Shunts |  |  | Pre-Condition
ENMAX | 25B240-D139 (ENMAX 25), 25 B240-D142 (ENMAX 25), ENMAX 25 240kV North Bus, 25B240-D133 (ENMAX 25), 25B240-D136 (ENMAX 25) | 2020-08-18 08:00 | 2020-08-20 16:00 | N | Y | power factor test and replace switch mechs | Circuit Breaker, Bus |  | power factor test HV PT 25PT240-Z42. Replace switch mechs SW136, SW142, SW148, SW154 | 240 kV, Contingency Requires Mitigation
ATCO | 7L69 (731s Elmworth - 815s Goodfare) | 2020-08-18 08:00 | 2020-08-18 16:00 | N | Y | pole relocate for customer | Line |  | Pole relocate for Customer | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 2.84L (ENMAX 2 - ENMAX 8) | 2020-08-18 08:00 | 2020-08-27 16:00 | N | N | outage isolation required for AESO SCADA cutover and 2.84L minor deficiency clean-up by ENMAX crews (DCTRP) | Line |  | DCTRP. Outage#4 Isolation required for AESO SCADA cutover and 2.84L minor deficiency clean-up by ENMAX crews | For Information Only
ALTALINK | 418s T2 (418s Ardenville) | 2020-08-18 08:00 | 2020-08-19 16:00 | N | Y | bushing replacement | Transformer |  |  | Restricts Generation
ENMAX | 47B138-771 (ENMAX 47) | 2020-08-18 08:00 | 2020-08-18 16:00 | N | N | power factor test HV PT | Circuit Breaker |  |  | For Information Only
ENMAX | 16.61L (ENMAX 16 - ENMAX 27), 27.1TR (ENMAX 27) | 2020-08-18 08:00 | 2020-08-19 16:00 | N | N | tapchanger inspection | Line, Transformer |  |  | Pre-Condition
ALTALINK | 859L (20s Ghost - T793s Horse Creek), 793s 859W (793s Horse Creek) | 2020-08-18 08:00 | 2020-08-18 17:00 | N | N | implement/function sync check changes on M388/389 relay | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
ATCO | 898s 901 (898s Heart Lake) | 2020-08-18 08:00 | 2020-08-19 12:00 | N | Y | replace trip latch due to issue found during maintenance | Circuit Breaker |  | Replace Trip latch due to issue found during maintenance | 240 kV, Contingency Requires Mitigation
ATCO | 849s 904 (849s Joslyn Creek) | 2020-08-18 08:15 | 2020-08-18 10:00 | N | Y | PRC-005 trip coil testing | Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 904-CENTER @ 849S BREAKER 904 OOS | 240 kV, Contingency Requires Mitigation, Pre-Condition
BCH | 1L275 (799s Coleman - Natal) | 2020-08-18 09:00 | 2020-08-18 17:00 | N | Y | protection work | Line |  |  | Pre-Condition
REDDEER | 247s T1 (247s Piper Creek) | 2020-08-18 09:00 | 2020-08-20 15:30 | N | N | power factor dissipation testing including bushings | Transformer |  |  | For Information Only
ALTALINK | 638S Esso Judy Creek | 2020-08-18 09:00 | 2020-08-19 17:00 | N | N | customer replacing failed cables | Station |  |  | For Information Only
ALTALINK | 253s C1 (253s Blackie) | 2020-08-18 09:15 | 2020-08-18 15:45 | N | N | PRC5 maintenance and perform 1st trip | Shunts |  |  | Pre-Condition
ATCO | 849s 905 (849s Joslyn Creek) | 2020-08-18 10:30 | 2020-08-18 13:00 | N | Y | PRC-005 trip coil testing | Circuit Breaker |  | PRC-005 - TRIP COIL TESTING - BREAKER 905 @ 849S BREAKER 905 OOS | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 747L (99s North St. Albert - 711L) | 2020-08-19 06:00 | 2020-08-19 18:30 | N | N | offload new control building onto new foundations | Line |  | Offload new control building onto new foundations | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 10.2TR (ENMAX 10) | 2020-08-19 07:00 | 2020-08-19 18:00 | N | N | roxtec installation | Transformer |  |  | For Information Only
ATCO | 770S Threehills | 2020-08-19 08:00 | 2020-08-19 17:00 | N | N | adding new station service transformers 500SST2 to be fed from 500BUS1 | Station |  | Adding new station service transformers 500SST2 to be fed from 500BUS1 so there is a station service on each side of the split bus. 51-51N/701T Protection will need to be blocked as opening 500PT1D will cause the relay to lose its voltage input signal. Backup protection will remain in service. | For Information Only
ENMAX | 47.1TR (ENMAX 47) | 2020-08-19 08:00 | 2020-08-19 16:00 | N | N | power factor test HV PT 47PT138-Z31 | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 433L (291s Cochrane - T793s Horse Creek), 793s 433 (793s Horse Creek) | 2020-08-19 08:00 | 2020-08-19 17:00 | N | N | implement/function sync check changes on M388/389 relay | Line, Circuit Breaker |  | Outage on 793s433 to implement/function sync check changes on M388/389 relay | Creates Radial Feeds, Firm Load Loss, Pre-Condition
IMPERIALOIL | IOR4 Strathcona | 2020-08-19 08:00 | 2020-11-21 16:00 | N | N | P2057. 47 MW cogen. ISD Sep. 08, 2020 | Unit
BCH | 5L71 (Mica Creek - Nicola) | 2020-08-19 08:00 | 2020-10-11 15:00 | N | Y | forced outage - MCA 5RX4, 5B10 repair. BC Maintenance does not affect the Alberta ATC | Line | 5L71 (Mica Creek - Nicola) |  | For Information Only, 500 kV
ATCO | 790s 702T (790s Poplar Hill), 790s 509C (790s Poplar Hill) | 2020-08-19 09:00 | 2020-08-21 17:00 | N | N | repair leaks | Transformer, Shunts |  | Repair leaks at 790S Poplar Hill - Transformer 702T - CAT 1 - 20 Leak severity (switch out after 701T is switched back in) | For Information Only, Pre-Condition
ALTALINK | 895s T3 (895s Suffield) | 2020-08-19 10:00 | 2020-08-19 12:00 | N | N | tie in riser from new NGR to T3 | Transformer |  |  | For Information Only
ALTALINK | 62s 11 (62s Brazeau) | 2020-08-19 23:00 | 2020-08-20 03:00 | N | N | maintenance | Switch |  |  | For Information Only, Restricts Generation
ALTALINK | 62s 12 (62s Brazeau) | 2020-08-20 03:00 | 2020-08-20 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 707L (54s Fort Saskatchewan - 166s Dow Chemical Fort Saskatchewan) | 2020-08-20 07:00 | 2020-08-22 18:00 | N | Y | repair structures | Line |  | Fire mitigation to repair Structures #5 - 8, 16 - 19, 24, 35 & 36 | Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 7L22 (811s Clairmont Lake - 7L22D2) | 2020-08-20 08:00 | 2020-08-24 16:00 | N | Y | protection upgrade | Line |  | 811S Clairmont Lake Protection Upgrade Project Wiring modification to 21A/7L22 & 21B/7L22 708CT modification, 708 Logic/Alarms, SCADA updates, SCADA End-End Checks and 1Z wiring | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 47.2TR (ENMAX 47) | 2020-08-20 08:00 | 2020-08-20 16:00 | N | N | power factor test | Transformer |  |  | For Information Only
ALTALINK | 56s C1 (56s Boyle) | 2020-08-20 09:00 | 2020-08-20 17:30 | N | N | Urgent repair to circuit switcher | Shunts |  |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-08-21 08:00 | 2020-08-27 18:00 | N | N | 29PP-70C & 29PP-70F | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ENMAX | 39.3TR (ENMAX 39) | 2020-08-21 08:00 | 2020-08-24 16:00 | N | N | Reinhausen tapchanger maintenance | Transformer | 39.3TR (ENMAX 39)
ALTALINK | 396s Pincher Creek 69kV Bus, 185L (379s Shell Canada Waterton - 396s Pincher Creek), 514L (396s Pincher Creek - 514BL), 396s T1 (396s Pincher Creek) | 2020-08-21 08:00 | 2020-08-21 14:00 | N | Y | 396s31 replace 69kV switch and fill bushing on 396s30 | Bus, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK, Lethbridge | 725L (15s Fort MacLeod - 725BL), 725AL (618s Riverbend - 725L), 725L (674s Lethbridge Bowron - 725BL) | 2020-08-22 07:00 | 2020-08-22 18:00 | N | Y | maintenance work and work on str 27 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 39.82L (ENMAX 162 Beddington - ENMAX 39), 39B138-39.82 (ENMAX 39) | 2020-08-22 08:00 | 2020-08-23 18:00 | N | N | tapchanger maintenance. 39.82L outage required | Line, Circuit Breaker | 39.82L (ENMAX 162 Beddington - ENMAX 39) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 834s 502R (834s Wesley Creek) | 2020-08-22 11:00 | 2020-10-16 16:00 | N | N | Iispect arc flash damage after forced lockout. | Shunts | 834s 502R (834s Wesley Creek) | Inspect arc flash damage after lockout. | Pre-Condition
ALTALINK | 781L (71s Lamoureux - 172s Sherritt) | 2020-08-23 07:00 | 2020-08-23 18:00 | N | N | fire mitigation to repair structures #8 & 13A | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, EPCOR | 920L (37s North Calder - 557s Castle Downs) | 2020-08-24 07:00 | 2020-08-28 15:11 | N | Y | urgent repair to replace damaged lattice tower (920L3) with new steel pole H-frame structure. | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage, Affects Cranking Path
ATCO | 2075s ACF13 (2075s Newell) | 2020-08-24 07:00 | 2020-08-24 12:00 | N | Y | hole tapping on cap towers | Shunts |  | HOLE TAPPING ON ACF13 CAP TOWERS @2075S, Tap holes on ACF13 cap towers to prevent future damage No constraints, redundant filter bank ACF 23 is still in service | 240 kV, For Information Only, Pre-Condition
EPCOR | 987s C72C1 (987s Clover Bar), 987s C1 (987s Clover Bar) | 2020-08-24 07:00 | 2020-08-24 17:00 | N | N | breaker repair | Circuit Breaker, Shunts |  |  | Pre-Condition
EPCOR, ALTALINK | Dome TX1, 665s D2401 (665s Dome), 665s D2402 (665s Dome), 909L (89s Ellerslie - 665s Dome) | 2020-08-24 07:00 | 2020-08-28 17:00 | N | Y | maintenance / doble | Terminal Equipment, Circuit Breaker, Line | 665s TX1 (665s Dome) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 901L (63s Red Deer - 74s Janet) | 2020-08-24 07:15 | 2020-08-28 17:45 | N | Y | emergency repair: repairing damaged tower legs on structures 142, 143, 154 | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 756L (87s Gaetz - 535s Joffre), 87s 152 (87s Gaetz), 87s 252 (87s Gaetz) | 2020-08-24 07:15 | 2020-08-27 17:45 | N | N | SCADA upgrade | Line, Circuit Breaker | 756L (87s Gaetz - 535s Joffre) |  | For Information Only
ALTALINK | 511s T30 (511s Crossings) | 2020-08-24 07:30 | 2020-09-03 18:30 | N | Y | pallet switch change on 511s180 SVC plus fire system inspection general maintenance on lighting | Transformer |  |  | 240 kV, For Information Only
ENMAX | ENMAX 27 | 2020-08-24 08:00 | 2020-08-27 16:00 | N | N | PTs isolated for PF testing on 27.1TR | Station |  | PTs isolated for PF testing on 27.1TR. 16.61L remains protected by remote end distance protection. | For Information Only
ALTALINK | 1325L (510s Sunnybrook - 511s Crossings) | 2020-08-24 08:00 | 2020-09-03 18:00 | N | Y | annual inspection & maintenance | Line | 1325L (510s Sunnybrook - 511s Crossings) |  | 500 kV, Pre-Condition
ALTALINK | 33s 3 (33s Spray) | 2020-08-24 08:00 | 2020-08-28 11:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ENMAX | 27.1TR (ENMAX 27) | 2020-08-24 08:00 | 2020-08-27 16:00 | N | N | power factor test transformer, transformer secondary cable tests | Transformer |  |  | For Information Only
ENMAX | 13.60L (ENMAX 13 - ENMAX 27), 13.4TR (ENMAX 13) | 2020-08-24 08:00 | 2020-09-04 16:00 | N | N | line protection upgrade, control cable swap out, arc flash mitigation project | Line, Transformer | 13.60L (ENMAX 27 - ENMAX 13) | Line Protection Upgrade. Control cable swap out. Arc Flash Mitigation Project. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29EDD-2 29PT-3 (29EDD-2 Tar Island), 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | 2020-08-24 08:00 | 2020-09-13 18:00 | N | N | pre-work for breaker replacement | Transformer, Line | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | Pre-work for Oct outage for 29PT-5205 replacement in 29PL6-22, 29PT3 at 29EDD-2 | For Information Only
ENMAX | 26.83L (ENMAX 26 - ENMAX 65), 65B138-D84 (ENMAX 65), 65B138-D85 (ENMAX 65) | 2020-08-24 08:00 | 2020-08-24 16:00 | N | N | power factor test, SF6 gas sample | Line, Circuit Breaker |  | Power factor test HV LA 65MD138-26.83. SF6 Gas Sample - 26B138-26.83 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 885s 902T (885s McMillan), 885s 501R (885s McMillan) | 2020-08-24 08:00 | 2020-08-27 17:00 | N | Y | major PM | Transformer, Shunts |  | 885S 902T Major PM 902T @ 885S OOS | 240 kV, Creates Radial Feeds, Firm Load Loss
REDDEER | 247s T2 (247s Piper Creek) | 2020-08-24 09:00 | 2020-08-28 15:30 | N | N | on load tap changer testing and overhaul | Transformer |  |  | For Information Only
ATCO | 9L27 (755s Cordel - 863s Paintearth), 755s 903 (755s Cordel), 755s 902 (755s Cordel) | 2020-08-24 09:00 | 2020-08-28 16:00 | N | Y | repair switches and leaks on breaker | Line, Circuit Breaker |  | Repair leaks on Breaker, require manufacturer representative on site. Repair leaks on BKR 903 repair 903A, 9L29D1 Ring bus open as well as 9L27 OOS | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 887L (48s Pocaterra - BCH Britt Creek) | 2020-08-24 09:15 | 2020-08-28 17:45 | N | Y | maintenance on structures | Line |  | excavating soil to reduce grade between strs 8, 9, maintenance on Strs 12, 44 and replacing Structures 27, 53, 56, 57, 58 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 28s R1 (28s West Brooks) | 2020-08-24 09:30 | 2020-08-30 17:30 | N | Y | emergency repair, bushing replacement | Shunts |  |  | 240 kV, Pre-Condition
ALTALINK | 522AL (868s Keephills Make-Up - 522L), 522L (866s Sundance Make-Up - 522AL tap), 522L (133L - 522AL) | 2020-08-24 10:30 | 2020-08-28 15:30 | N | N | bushing replacement. replace LAs, replace oil, doble, SFRA, repair leaks. | Line |  | 866s T1 69kV bushing replacement. Replace T1 High side LAs, Replace Oil, Doble, SFRA, repair leaks. | For Information Only
ATCO | 2075s ACF14 (2075s Newell) | 2020-08-24 12:00 | 2020-08-24 18:00 | N | Y | hole tapping on cap towers | Shunts |  | HOLE TAPPING ON ACF14 CAP TOWERS @2075S Tap holes on ACF14 cap towers to prevent future damage No constraints, redundant filter bank ACF 24 is still in service | 240 kV, For Information Only, Pre-Condition
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2020-08-24 12:30 | 2020-08-28 17:30 | N | N | component replacements including poles on Str's 1-195 | Line |  |  | For Information Only, Pre-Condition
ATCO | 930s 708 (930s Arcenciel) | 2020-08-24 13:00 | 2020-08-24 14:00 | N | N | trip coil testing | Circuit Breaker |  | PRC-005 - trip Coil Testing - Breaker 708 @ 930S | For Information Only
ATCO | 930s 710 (930s Arcenciel) | 2020-08-24 14:00 | 2020-08-24 15:00 | N | N | trip coil testing | Circuit Breaker |  | PRC-005 - trip Coil Testing - Breaker 710 @ 930S | For Information Only, Pre-Condition
ATCO | 930s 712 (930s Arcenciel) | 2020-08-24 16:00 | 2020-08-24 17:00 | N | N | trip coil testing | Circuit Breaker |  | PRC-005 - trip Coil Testing - Breaker 712 @ 930S | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 636L (420s Broadmoor - 746s Sherwood Park) | 2020-08-25 07:00 | 2020-08-25 18:00 | N | N | fire mitigation on structures #29 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2075s ACF24 (2075s Newell) | 2020-08-25 07:00 | 2020-08-25 12:00 | N | Y | tap holes on ACF24 cap towers to prevent future damage | Shunts |  | HOLE TAPPING ON ACF24 CAP TOWERS @2075S Tap holes on ACF24 cap towers to prevent future damage No constraints, redundant filter bank ACF 14 is still in service | 240 kV, Pre-Condition
ALTALINK | 710L (56s Boyle - 159s Colinton) | 2020-08-25 07:00 | 2020-08-25 18:00 | N | N | maintenance on structure 230 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 33s 6 (33s Spray) | 2020-08-25 08:00 | 2020-08-27 17:00 | N | Y | maintenance | Switch | 33s6 (33s Spray) |  | Restricts Generation
ENMAX | 47B138-771 (ENMAX 47) | 2020-08-25 08:00 | 2020-08-25 16:00 | N | N | power factor test HV PT 47PT138-771L | Circuit Breaker |  | power factor test HV PT 47PT138-771L | For Information Only, Pre-Condition
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 39B138-38.83 (ENMAX 39) | 2020-08-25 08:00 | 2020-08-25 16:00 | N | N | replace SF6 gauge | Line, Circuit Breaker |  | 39B138-38.83 - SF6 gauge cracked center pole -replace gauge | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
CMH | MH69s6 MH138-620 (MH69s6 Riverview), MH69s3 MH138_317 (MH69s3 South Ridge), MH-20L (MH69S-3 South Ridge - MH69S-6 Riverview) | 2020-08-25 08:00 | 2020-08-27 15:00 | N | N | tree trimming within proximity to MH-20L | Circuit Breaker, Line |  |  | For Information Only
ALTALINK | 574s T1 (574s Nilrem) | 2020-08-25 08:30 | 2020-08-27 17:00 | N | Y | PRC-5 - maintenance, doble and testing | Terminal Equipment |  | PRC-5 574sT1 Maintenance & Doble. Neutral conductor replacement, Oil Leak, AC supply and SFRA Testing. | 240 kV, Contingency Requires Mitigation
ATCO | 2075s ACF23 (2075s Newell) | 2020-08-25 12:00 | 2020-08-25 16:00 | N | Y | tap holes on ACF23 cap towers to prevent future damage | Shunts |  | HOLE TAPPING ON ACF23 CAP TOWERS @2075S Tap holes on ACF23 cap towers to prevent future damage No constraints, redundant filter bank ACF 13 is still in service | 240 kV, For Information Only, Pre-Condition
ATCO | 2075s ACF12 (2075s Newell) | 2020-08-26 07:00 | 2020-08-27 18:00 | N | Y | structure tower repair | Shunts |  | REPAIRS TO ACF12 CAPACITOR BANK STRUCTURAL TOWERS @2075S REPAIR STRUCTURAL TOWERS SUPPORTING ACF12 CAPACITOR BANKS No constraints, redundant filter bank ACF 22 is still in service | 240 kV, For Information Only, Pre-Condition
ENMAX | 10.1TR (ENMAX 10) | 2020-08-26 07:00 | 2020-08-26 16:00 | N | N | roxtec installation | Transformer |  |  | For Information Only
ALTALINK | 633L (56s Boyle - 405s Waupisoo) | 2020-08-26 07:30 | 2020-08-26 17:30 | N | N | maintenance on Str 10 | Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 377s T1 (377s Hardisty) | 2020-08-26 07:30 | 2020-08-27 17:30 | N | N | maintenance & H2X CT failure repair | Transformer |  |  | For Information Only
ALTALINK | 511s ACF21 (511s Crossings), 511s ACF22 (511s Crossings) | 2020-08-26 07:30 | 2020-08-28 18:30 | N | Y | switch inspection and cleaning; filter bank inspection | Shunts |  |  | 240 kV, For Information Only
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32), 31B138-31.84 (ENMAX 31), 32B138-32BT5 (ENMAX 32), 32B138-31.84 (ENMAX 32) | 2020-08-26 08:00 | 2020-08-26 16:00 | N | N | replace broken lightning sprire 32sub, check reversing switch 32.3TR, power factor test HV breaker 31B138-31.84. | Line, Transformer, Circuit Breaker
ATCO | 770s 705C (770s Three Hills), 770s 705 (770s Three Hills) | 2020-08-26 08:00 | 2020-08-26 16:00 | N | N | test trip coils on breaker 705 | Shunts, Circuit Breaker |  | Test trip coils on Bkr 705, 705C-Cap bank will be out of service | For Information Only
ATCO | 7L14 (705s Kitscoty - 751s Hill) | 2020-08-26 08:00 | 2020-08-26 17:00 | N | N | line impedance test & ground resistivity study @ 705s using transmission line and new test equipment | Line |  | Line Impedance test on 7L14, Ground Resistivity study @ 705s using transmission line and new test equipment | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.1TR (ENMAX 11) | 2020-08-26 08:00 | 2020-08-27 16:00 | N | N | 11.1TR Inv & Rep / TC temp sensor fail & check reversing switch | Transformer |  |  | For Information Only
SUNCOR | 29EDD-55 29Edd-55 | 2020-08-26 08:00 | 2020-09-03 18:00 | N | N | bus outage 29PP-37B, 29PT-163: | Station |  |  | For Information Only
ALTALINK | 42s Sarcee 240kV North Bus, 916L (5s East Calgary - 42s Sarcee), 928L (17s Benalto - 42s Sarcee), 42s C2 (42s Sarcee), 42s T1 (42s Sarcee) | 2020-08-26 09:00 | 2020-08-26 15:00 | N | Y | urgent remove bird nest from north bus, urgent work - remove bird nest from north bus | Bus, Line, Shunts, Transformer |  | Bird Nest between N&S 240kv buses. Bird nest is in potential to cause power issue. "The Ravens nest at 42s seems to be getting a little messy. Long stringy strands hanging and blowing from the nest. May pose a flash over risk if it gets any bigger, or falls apart etc. | 240 kV, Pre-Condition
ALTALINK | 32S Barrier | 2020-08-26 09:00 | 2020-08-26 11:00 | N | Y | ugprade MPLS | Station |  | 32s genearation offline. Upgrade 33s and 245s MPLS which causes loss of transfer trip to 32s. Coordinated with TransAlta. Coordinated with TransAlta. | Restricts Generation
ENMAX, ALTALINK | 1003L (74s Janet - ENMAX 25), 25B240-D136 (ENMAX 25), 25B240-D135 (ENMAX 25) | 2020-08-27 08:00 | 2020-08-28 18:00 | N | Y | power factor test HV LA 25MD240-1003 and replace switch | Line, Circuit Breaker |  |  | 240 kV, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 35s 85 (35s Rundle), 85L (35s Rundle - 54L) | 2020-08-27 09:00 | 2020-08-27 11:00 | N | N | open breaker 35s85 for upgrade MPLS node at 35s and 118s which affects 54L/85L TPR | Circuit Breaker, Line |  | Open breaker 35s85 for Upgrade MPLS node at 35s and 118s which affects 54L/85L TPR. Coordinated with TransAlta. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 775s 601 (775s Sullivan Lake), 6L15 (763s Hanna - 775s Sullivan Lake) | 2020-08-27 09:00 | 2020-08-27 12:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | 601 Breaker Maintenance, 6L15 open ended | Creates Radial Feeds, Firm Load Loss, Pre-Condition
VISIONREQ | 354s T3 (354s Summerview) | 2020-08-27 10:00 | 2020-08-27 12:00 | N | Y | install pilings | Transformer |  |  | Restricts Generation
VISIONREQ | 354s T4 (354s Summerview) | 2020-08-27 12:00 | 2020-08-27 14:00 | N | Y | install pilings | Transformer |  |  | Restricts Generation
ATCO | 6L03 (775s Sullivan Lake - 6L17 tap), 775s 603 (775s Sullivan Lake) | 2020-08-27 12:15 | 2020-08-27 16:00 | N | N | breaker maintenance | Line, Circuit Breaker |  | 603 Breaker Maintenance, 6L03 open ended | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 32S Barrier | 2020-08-27 13:00 | 2020-08-27 14:00 | N | N | upgrade 33s and 245s MPLS | Station |  | 32s generation offline. Upgrade 33s and 245s MPLS which causes loss of transfer trip to 32s. Coordinated with TransAlta. Back-up date/time. | Restricts Generation
ALTALINK | 794L (157s Lac La Biche - 819s Whitby Lake) | 2020-08-27 13:00 | 2020-08-27 17:00 | N | Y | scope of includes maintenance on sttr 170 | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | 814s T2 (814s Bellamy), R721 (Rossdale), BR722 (Rossdale), T1 (Rossdale) | 2020-08-28 | 2020-08-28 04:00 | N | Y | place RR723 into service | Transformer, Circuit Breaker |  |  | 240 kV, Firm Load Loss
ALTALINK | 519L (996s Imperial Oil Carson Lake - 519AL), 519AL (661s Laura Lake - 519L) | 2020-08-28 07:00 | 2020-08-28 18:30 | N | N | creating Open Point 'A' inside 661s in preparation for the replacement of 661s T1 | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 661s T1 (661s Laura Lake) | 2020-08-28 18:30 | 2020-10-21 10:00 | N | N | replacing transformer | Transformer | 661s T1 (661s Laura Lake) |  | For Information Only, Pre-Condition
ALTALINK | 743L (527s Coal Valley - 740L), 527S Coal Valley | 2020-08-30 07:00 | 2020-09-01 21:00 | N | N | doble, leak repairs and maintenance work | Line, Station | 743L (527s Coal Valley - 743L1A) COALVALLEY | T1 Bushings & 527s1 Insulators, T1 Maintenance Scheduled: Shannon Bouchard Issue To: XXXXX Contact #: XXXXX T1 Bushings & 527s1 Insulators, T1 Doble, SFRA, & OBG2 leak Repairs Maintenance Work, 743L Scope includes maintenance on structures 28, 34, 37 and 39 Scheduled: Shannon Bouchard Issue To: Jared Harrison Contact #: 780.289.5989 | For Information Only
ATCO | 2075s ACF22 (2075s Newell) | 2020-08-31 07:00 | 2020-09-01 18:00 | N | Y | repair capacitor band structural towers | Shunts |  | REPAIRS TO ACF22 CAPACITOR BANK STRUCTURAL TOWERS @2075S REPAIR STRUCTURAL TOWERS SUPPORTING ACF22 CAPACITOR BANKS No constraints, redundant filter bank ACF 12 is still in service | 240 kV, For Information Only, Pre-Condition
EPCOR | 805s C1 (805s Jasper) | 2020-08-31 07:00 | 2021-03-26 06:00 | N | Y | forced | Shunts | 805s J2408 (805s Jasper) |  | 240 kV, Pre-Condition
ATCO | 2029s ACF11 (2029s Heathfield) | 2020-08-31 07:00 | 2020-09-18 17:00 | N | Y | perform PRC005 tests on all devices associated with ACF11 | Shunts | 2029s ACF11 (2029s Heathfield) | Perform PRC005 tests on all devices associated with ACF11, Filter will be unavailable, One device worked on at a time. 10BF11+SW1 Breaker fail relay 94 relay 10BF11+SW1K302 86 relay 10BF11+SW1K861 94 relay 10BF11+SW1K301 10R10+R21 10R10+R21F602 trench relay 10R10+R21F604 trench relay 10R10+R21F502 trench relay 10R10+R21F504 trench relay 87 diff relay 10R10+R21F872 86 relay 10R10+R21K862 94 relay 10R10+R21K942 10R01+R1 94 relay 10R01+R1K11 86 relay 10R01+R1K10 1218 Trip Coil 1218A1 Trip Coil 1218A2 Trip Coil 1218B1 Trip Coil 1218B2 Trip Coil 1218C1 Trip Coil 1218C2 | 500 kV, For Information Only
EPCOR | 1164L (816s Petrolia - EPCOR Riverview) | 2020-08-31 07:00 | 2020-08-31 17:00 | N | Y | doble | Line | 1164L (816s Petrolia - EPCOR Riverview) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 657s T1 (657s Summerside), 657s SU2401 (657s Summerside), 657s SU2404 (657s Summerside) | 2020-08-31 07:00 | 2020-09-04 17:00 | N | Y | Doble testing | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 805s T4 (805s Jasper) | 2020-08-31 07:00 | 2020-10-23 17:00 | N | Y | bushing replacement & oil work | Transformer | 661s T1 (661s Laura Lake) |  | 240 kV, For Information Only
ALTALINK | 778L (87s Gaetz - 217s North Red Deer), 87s 652 (87s Gaetz), 87s 752 (87s Gaetz) | 2020-08-31 07:15 | 2020-09-03 17:45 | N | N | SCADA upgrade | Line, Circuit Breaker | 778L (87s Gaetz - 217s North Red Deer) |  | For Information Only, Pre-Condition
ALTALINK | 85L (35s Rundle - 54L tap) | 2020-08-31 07:15 | 2020-09-04 17:45 | N | N | replacing structures 3 and 4 and maintenance on Structures 1 and 6 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 511s ACF12 (511s Crossings), 511s 1352 (511s Crossings) | 2020-08-31 07:30 | 2020-09-02 18:30 | N | Y | filter bank inspection & paint reactor L2 in C phase | Shunts, Circuit Breaker |  |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 414S Gulfrobb | 2020-08-31 08:00 | 2020-09-04 18:00 | N | N | T1 & VR1 leak repairs & maintenance | Station | GULFROBB | T1 Oil Claim / Maintenance, T1 Bushings, and 414s SS1 50kVA Replacement Scheduled: Shannon Bouchard Issue To: XXXXX Contact #: XXXXX
ATCO | 826s 901T (826s Marguerite Lake), 826s 502R (826s Marguerite Lake) | 2020-08-31 08:00 | 2020-10-25 16:00 | N | Y | upgrade P&C, beaker fail protection, complete wiring for new 87TA, 87TB, and 51TV relays | Transformer, Shunts | 826s 901T (826s Marguerite Lake) | 826S Marguerite P&C Upgrade 240/144kV Breaker Fail Protection Complete wiring for new 87TA, 87TB, and 51TV relays, Complete wiring for 87B/700BS1 and 87B/900BS1 Add 901TD and 701TD status to 87TB and commission | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 7L03 (731s Elmworth - 7L03D3), 731s 701T (731s Elmworth) | 2020-08-31 08:00 | 2020-09-14 12:00 | N | Y | breaker replacement and protection upgrade, remove old panel, enter terminate outdoor apparatus, install new panels, test protection relays & logic/alarms, CT work, & SCADA end-to-end testing | Line, Transformer | 7L03 (731s Elmworth - 7L03D3) | 731S Elmworth Bkr Replacement and Protection Upgrade, 902S Mobile Sub to carry 701T load Remove old panel, Enter terminate outdoor apparatus, Install new panels, Test 7L03 Protection Relays & Logic/Alarms, CT Work, & SCADA End-to-End testing | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ENMAX | 8.3TR (ENMAX 8) | 2020-08-31 08:00 | 2020-09-04 16:00 | N | N | power factor test transformer, secondary cable tests, maintenance, gas relay testing. check reversing switch. oil sampling | Transformer |  |  | For Information Only
ALTALINK | 19S Wabamun 138kV Bus1, 19S Wabamun 138kV Bus2, 896L (19s Wabamun - 432s Carvel), 19s T10 (19s Wabamun), 156L (19s Wabamun - 156BL) | 2020-08-31 08:00 | 2020-09-04 11:00 | N | Y | replace 19s156, 138kV string insulators and salvage 19s138 | Bus, Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 36.2TR (ENMAX 36) | 2020-08-31 08:00 | 2020-09-04 16:00 | N | N | CT replacement | Transformer |  |  | For Information Only
ENMAX | 38.1CAP, 38B138-38.1CAP (ENMAX 38) | 2020-08-31 08:00 | 2020-09-01 16:00 | N | N | HV cap bank maintenance | Terminal Equipment, Circuit Breaker |  |  | For Information Only, Pre-Condition
ATCO | 757s 603 (757s Battle River), 6L03 (757s Battle River - 6L17 tap) | 2020-08-31 08:30 | 2020-08-31 11:30 | N | N | breaker maintenance | Circuit Breaker, Line |  | 603 Breaker Maintenance, 6L03 open ended | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C1 (74s Janet), 74s C2 (74s Janet) | 2020-08-31 08:30 | 2021-06-08 14:30 | N | N | replace 138kV C1 cap bank | Shunts | 74s C1 (74s Janet), 74s C2 (74s Janet) |  | For Information Only, Pre-Condition
ATCO | 767s 701 (767s Oyen), 7L132 (767s Oyen - 959s Lanfine) | 2020-08-31 09:00 | 2020-08-31 16:00 | N | N | partial breaker maintenance | Circuit Breaker, Line | Battle River and Central Wind does not help with voltage collapse. | Partial Breaker Maintenance, 7L132 Open Ended | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 763L (158s Vauxhall - 763AL) | 2020-08-31 09:00 | 2020-09-03 18:00 | N | N | urgent line clearance structure changes 763L (structures range 322-406) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 792L (150s Clyde - 191s N.W. Cardiff), 150s 792X (150s Clyde) | 2020-08-31 09:30 | 2020-09-18 18:30 | N | N | replace dead end structure, switch 150s22, & relocation of 150s792X breaker and CTs & new 150s33 VT4 Installation on 792L | Line, Circuit Breaker | 792L (150s Clyde - 191s N.W. Cardiff) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 827s SVC (827s Cranberry Lake) | 2020-08-31 09:30 | 2020-09-03 16:00 | N | Y | perform testing on 703T, and other equipment.SVC will be offline | Shunts |  | perform testing on 703T, and other equipment.SVC will be offline | For Information Only, Pre-Condition
ALTALINK | 184s T3 (184s Petro-Canada Edmonton) | 2020-08-31 10:00 | 2020-08-31 12:00 | N | N | advice to switch out station service | Transformer |  |  | For Information Only
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-08-31 10:00 | 2020-09-06 15:00 | N | Y | x-arm change out | Line |  | XARM change out | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 498s 666 (498s Tilley), 666L (28s West Brooks - 498s Tilley) | 2020-08-31 10:00 | 2020-08-31 17:00 | N | Y | maintenance | Circuit Breaker, Line |  | Outage on 498s666 to implement/function sync check changes on M388/389 relay | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ATCO | 757s 602 (757s Battle River), 6L05 (757s Battle River - 843s Bigknife Creek) | 2020-08-31 12:00 | 2020-08-31 15:00 | N | N | breaker maintenance | Circuit Breaker, Line |  | 602 Breaker Maintenance, 6L05 open ended | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L159 (770s Three Hills - 7L159 tap) | 2020-08-31 12:00 | 2020-09-03 15:00 | N | N | crossarm/insulator replacement | Line |  | Crossarm/insulator replacement | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2020-08-31 12:30 | 2020-09-03 17:30 | N | N | component peplacements including poles on Str's 1-195 | Line |  |  | For Information Only, Pre-Condition
ALTALINK | 275s 5 (275s Jenner) | 2020-08-31 12:30 | 2020-09-03 17:00 | N | Y | 1st trip to be done and then PRC5 maintenance and replace grading capacitors | Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2020-08-31 13:00 | 2020-08-31 15:00 | N | N | advice to switch out station service | Transformer |  |  | For Information Only
BLACKSPRING | 485S Black Springs | 2020-08-31 13:00 | 2020-08-31 14:30 | N | N | voltage slope verification test | Station |  |  | For Information Only
ALTALINK | 164s T2 (164s Empress Liquids) | 2020-08-31 13:30 | 2020-09-03 15:30 | N | N | fix leaks, doble, maintain T2 | Transformer |  |  | For Information Only
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2020-08-31 15:00 | 2020-09-11 10:00 | N | N | 184sT1 leak repairs and maintenance | Transformer |  |  | For Information Only
ALTALINK | 740L (39s-426s-414s-527s-101s) | 2020-09-01 07:00 | 2020-09-01 21:00 | N | N | maintenance on structures | Line |  | Scope of work includes maintenance on Structures 52B, 54, 217, 228, 236, 240 and 247 on 740L and structures 740ALJCT  740L233A & 740AL0, 740AL1, 9, 10, 16, 17 and 87 on 740AL, Replace 740L Str 192 for urgent line clearance mitigation. Scheduled: Shannon Bouchard Issue To: Carson Webber Contact #: 778.214.6493 | For Information Only
ALTALINK, EPCOR | 920L (71s Lamoureux - 557s Castle Downs) | 2020-09-01 07:00 | 2020-09-02 17:00 | N | Y | line clearance mitigation | Line |  | Line clearance mitigation on Structures #4 & 5 | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Affects Cranking Path
ALTALINK, EPCOR | 915L (38s East Edmonton - 987s Clover Bar), 987s C2403 (987s Clover Bar), 987s C2405 (987s Clover Bar) | 2020-09-01 07:00 | 2020-09-01 17:00 | N | Y | doble testing | Line, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 762L (101s Cheviot - 740L) | 2020-09-01 07:00 | 2020-09-03 18:00 | N | N | maintenance on structures | Line | 762L (101s Cheviot - 762L2) | Scope of work includes changing Str 35 and maintenance on Strs 11, 12, 13, 42, 47, 109 and 137. Scheduled: Shannon Bouchard Issue To: Steve Predinchuck Contact #: 403.836.4471 | For Information Only
Saskpower | Sask Power A1P | 2020-09-01 08:00 | 2020-09-04 16:00 | N | Y | stability concerns | Line |  |  | Limits ATC
BCH | 2L113 (B1s Natal - B2s Cranbrook) | 2020-09-01 08:00 | 2020-09-03 17:00 | N | Y | disconnect maintenance | Line | 2L113 (B1s Natal - B2s Cranbrook), CBK 2B5 OOS | disconnect maintenance/structure replacement 2L113, CBK 2B5, 2D1CB9, 2D2CB5, 2D1CB6 OOS CBK 2D23, 2L113 OOS | Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Pre-Condition
ENMAX | 5.10TR (ENMAX 5) | 2020-09-01 08:00 | 2020-09-04 18:30 | N | N | tray replacement | Transformer |  | Plastibeton Tray Replacement at 5 Sub | For Information Only
TRANSALTA | IEW2 Summerview Phase 2 | 2020-09-01 08:00 | 2020-10-04 16:00 | N | N | P2198 Summerview Battery Storage Commissioning ISD: Sep 04, 2020 | Unit
ALTALINK | 893L (312s Fidler - 806s Oldman River) | 2020-09-01 08:00 | 2020-09-01 12:00 | N | N | customer equipment maintenance | Line |  |  | For Information Only
Lethbridge | 241s T1 (241s Lethbridge Uplands) | 2020-09-01 08:00 | 2020-11-02 16:00 | N | N | replacing transformer | Transformer | 241s T1 (241s Lethbridge Uplands) | replacing 241S T1 Transformer from 30 MVA to 50 MVA | For Information Only
ATCO | 757s 710 (757s Battle River) | 2020-09-01 08:30 | 2020-09-02 15:00 | N | N | breaker maintenance | Circuit Breaker |  | Breaker Maintenance, No Impact - 706 floating breaker will be utilized to tie 912T to the 144kv system | Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge), 370s 2552 (370s North Lethbridge) | 2020-09-01 09:00 | 2020-09-01 15:30 | N | N | cut open point "A" for future outage | Transformer, Circuit Breaker |  | To fixed 370s44. Wire spare T4 CT core for the new B87/138B1 protection and wire 2552 CT. Cut Open point "A" for future outage ref 271757 | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 953L (574s Nilrem - 755s Cordel) | 2020-09-01 10:00 | 2020-09-01 12:00 | N | Y | Upgrade MPLS node, loss of TPR requires 953L open for system stability | Line |  |  | 240 kV, Overload, Pre-Condition
ATCO | 743s 701T (743s Sarah Lake) | 2020-09-01 10:00 | 2020-09-04 10:00 | N | N | breaker replacement and removing jumpers | Transformer |  | Replacing breaker 605, 605A & 605B @ 743S Sarah Lake GOI on 701T (Install 72KV Risers removing jumper J1 | For Information Only, Pre-Condition
ATCO | 743s Sarah Lake 72kV Bus | 2020-09-01 11:00 | 2020-09-04 11:00 | N | N | replacing breaker 605, 605A & 605B | Bus |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge) | 2020-09-01 13:30 | 2020-09-04 14:00 | N | N | fix switch, wire CT core | Transformer |  | To fixed 370s44. Wire spare T4 CT core for the new B87/138B1 protection and wire 2552 CT. | For Information Only
ALTALINK | 250p 22 (250p Bighorn Plant) | 2020-09-02 00:01 | 2020-09-03 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
EPCOR | 987s T2 (987s Clover Bar) | 2020-09-02 07:00 | 2020-09-02 17:00 | N | Y | tapchanger maintenance | Transformer |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK, EPCOR | 947L (89s Ellerslie - 987s Clover Bar) | 2020-09-02 07:00 | 2020-09-02 17:00 | N | Y | doble testing | Line |  |  | 240 kV, Affects Cranking Path
ALTALINK | 740L (39s Bickerdike - 58s Edson) | 2020-09-02 07:00 | 2020-09-03 18:00 | N | N | maintenance | Line |  | Scope of work includes maintenance on structure 44 and Str 25 Scheduled: Shannon Bouchard Issue To: Carson Webber Contact #: 778.214.6493 | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2020-09-02 07:00 | 2020-09-03 07:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 463L (15s Fort Macleod - 463AL) | 2020-09-02 07:15 | 2020-09-03 17:45 | N | Y | urgent repair due to damaged cross arm | Line |  |  | Over/Under Voltage, Restricts Generation, Creates Radial Feeds
ALTALINK | 216s T1 (216s Knightsbridge) | 2020-09-02 07:30 | 2020-09-02 17:30 | N | N | add CT input from T1 to new metering module | Transformer
VISIONREQ | 354S Summerview | 2020-09-02 08:00 | 2020-09-06 18:00 | N | N | replacement of transformer T6 | Station |  |  | For Information Only
ENMAX | 21.1C (ENMAX 21) | 2020-09-02 08:00 | 2020-09-02 16:00 | N | N | HV breaker maintenance | Shunts
ENMAX | 162s 138-RB81 (162s Beddington) | 2020-09-03 08:00 | 2020-09-03 16:00 | N | N | HV breaker maintenance 162B138-RB81, dashpot checks, SF6 sample | Circuit Breaker |  | HV Breaker maintenance 162B138-RB81. Dashpot checks. SF6 sample | Contingency Requires Mitigation, For Information Only
ATCO | 7L171 (802s Michichi Creek - 804s Wintering Hills) | 2020-09-03 09:00 | 2020-09-03 15:00 | N | N | clearance mitigation, bird diverter installation | Line |  | 7L171 Clearance Mitigation, bird diverter installation. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 72JW19 (805s Jasper - Woodcroft) | 2020-09-04 07:00 | 2020-09-04 17:00 | N | N | doble | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s T4 (370s North Lethbridge), 370s 2552 (370s North Lethbridge) | 2020-09-04 07:00 | 2020-09-08 07:30 | N | N | close open point "A" | Transformer, Circuit Breaker |  | To fixed 370s44. Wire spare T4 CT core for the new B87/138B1 protection and wire 2552 CT. | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 838L (14s Devon - 325s Leduc) | 2020-09-04 07:00 | 2020-09-08 18:00 | N | N | rebuilding a portion of 838L between Strs 40 and 42 | Line |  |  | Creates Radial Feeds, Firm Load Loss
SSLP | SUF1 Suffield Solar | 2020-09-04 08:00 | 2020-11-30 16:00 | N | N | P1838. Suffield 23MW Solar DG. | Unit
ATCO | 7L68 (730s Rycroft - 811s Clairmont Lake) | 2020-09-04 08:00 | 2020-09-07 16:00 | N | Y | wiring modification SCADA updates, SCADA End-End Checks and 1Z wiring | Line |  | Wiring modification to 21A/7L68 & 21B/7L68 707CT modification, 707 Logic/Alarms, SCADA updates, SCADA End-End Checks and 1Z wiring | Creates Radial Feeds, Firm Load Loss
ALTALINK | 19s 156 (19s Wabamun), 156L (19s Wabamun - 156BL) | 2020-09-04 11:00 | 2020-09-07 18:00 | N | N | finish installing and commissioning of new 19s156 | Circuit Breaker, Line |  |  | For Information Only
ENMAX | 34B69-16.60 (ENMAX 34), 16.60L (ENMAX 16 - ENMAX 34) | 2020-09-05 08:00 | 2020-09-06 16:00 | N | N | breaker maintenance | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 805s T4 (805s Jasper) | 2020-09-06 08:00 | 2020-09-17 17:00 | N | Y | forced outage - due to harmonics reactor on fire | Transformer | 805s T4 (805s Jasper) |  | 240 kV, For Information Only
ALTALINK | 464L (87s Gaetz - 209s Timberlands) | 2020-09-07 07:15 | 2020-09-10 17:45 | N | Y | SCADA upgrade | Line | 464L (87s Gaetz - 209s Timberlands)
Syncrude | Mildred T17 (Syncrude Mildred Lake) | 2020-09-07 08:00 | 2020-09-12 20:00 | N | N | transformer outage | Transformer
ENMAX | 13.82L (ENMAX 13 - ENMAX 22) | 2020-09-07 08:00 | 2020-09-25 16:00 | N | N | line protection upgrade, control cable swap out, arc flash mitigation project | Line | 13.82L (ENMAX 22 - ENMAX 13) |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-09-07 08:00 | 2020-09-13 18:00 | N | N | 29PL6-16 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
SUNCOR | 29PL6-38 (29EDD-34) | 2020-09-07 08:00 | 2020-09-21 15:45 | N | N | line outage to perform 5/10yr maintenance | Line | 29EDD-34
ATCO | 6L11 (742s Freeman Lake - 743s Sarah Lake), 6L126 (743s Sarah Lake - 515L tap), 6L96 (743s Sarah Lake - 744s Federated Pipelines), 743s Sarah Lake 72kV Bus | 2020-09-07 08:00 | 2020-09-09 12:00 | N | N | replace 605A | Line, Bus |  | 72kv Bus GOI to replace 605A @ 743S Sarah Lake | Creates Radial Feeds, Firm Load Loss, Pre-Condition
REDDEER, ALTALINK | 209S Timberlands, 209s 768W (209s Timberlands), 464L (87s Gaetz - 209s Timberlands), 768L (209s Timberlands - 217s North Red Deer), 209s T1 (209s Timberlands) | 2020-09-07 09:00 | 2020-09-10 15:30 | N | Y | seal leaks around cables | Station, Circuit Breaker, Line, Transformer |  | seal leaks around 138kV cables in the basement | Pre-Condition
EPCOR | RR729 (Rossdale) | 2020-09-08 07:00 | 2020-10-01 17:00 | N | N | breaker replacement | Circuit Breaker | RR729 (Rossdale) |  | Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 801s 907 (801s Anderson) | 2020-09-08 07:00 | 2020-09-10 16:00 | N | Y | breaker maintenance | Circuit Breaker |  | 801S Anderson 907 BREAKER MIN OIL HLR PARTIAL TESTING BKR 907 Partial Maint. SHEERNESS UNIT 1 TIED TO SYSTEM BY BKR 906 ONLY | 240 kV, Contingency Requires Mitigation
ALTALINK | 123s T3 (123s Banff), 54L (123s Banff - 177s West Cascade) | 2020-09-08 07:15 | 2020-09-11 18:00 | N | N | upgrade T3 A protection and 54L maintenance on str (267, 274, 275, 276, 281, 284, 285, 293, 294, 300, 301, 302, 303, 305, 306, 313, 314) | Transformer, Line | 54L (123s Banff - 177s West Cascade) | Upgrade T3 A protection and relocate 43s/bypass switch. Replace 25/138kV LA's, doble, maintenance. 138kV breaker maintenance (123s54E). 54L maintenance on Str (267, 274, 275, 276, 281, 284, 285, 293, 294, 300, 301, 302, 303, 305, 306, 313, 314) Loads will be supplied via the distribution (Fortis/TAU) systems | For Information Only, Pre-Condition
Lethbridge | 172L (181s Chinook - 370s North Lethbridge) | 2020-09-08 07:30 | 2020-09-16 08:00 | N | Y | move 552 breaker protection to new control building, replace 370s176 insulators | Line | 172L (181s Chinook - 370s North Lethbridge) | Move 552 breaker protection to new control building. Replace 370s176 insulators. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
CMH | MHS9 T11 (MHS9 Power Plant), 15L (MHS7 Brier Park - MHS9 Power Plant), MH69s1 MH69-6 (MH69s1 Power P Switchyard), MH69s1 MH69-10 (MH69s1 Power P Switchyard) | 2020-09-08 08:00 | 2020-09-17 10:00 | N | N | upgrades | Transformer, Line, Circuit Breaker | MHS9 T11 (MHS9 Power Plant), 15L (MHS7 Brier Park - MHS9 Power Plant) | Capital work, equipment upgrade | For Information Only
ENMAX | 162s 240-RB134 (162s Beddington) | 2020-09-08 08:00 | 2020-09-08 16:00 | N | Y | HV breaker maintenance | Circuit Breaker | 162s 240-RB134 (162s Beddington) |  | 240 kV, Contingency Requires Mitigation
ATCO | 839s 701T (839s Daishowa Plant) | 2020-09-08 08:00 | 2020-09-12 17:00 | N | Y | upgrade breaker 19 and 15 protections and upgrade transformer and line protections | Transformer | 839s 701T (839s Daishowa Plant) | Mercer Pulp Work: Protection Upgrades Bkr 19 and 15 ATCO Work: Transformer Protection Upgrade Line Protection Upgrade SCADA Upgrade Tap Changer Refurbishment Leak Repairs 701T, 400PT1 PCB Samples | Restricts Generation
ENMAX | 10.1TR (ENMAX 10) | 2020-09-08 08:00 | 2020-09-11 16:00 | N | N | inspection maintenance, relay upgrades and oil sampling | Transformer |  |  | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2020-09-08 09:00 | 2020-09-11 18:00 | N | Y | align with 1201L outage | Line |  |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2020-09-08 09:00 | 2020-09-11 18:00 | Y | Y | structure range 187-508 components and fire mitigation( 95050674) | Line | 1201L (520s Bennett - BCH Cranbrook) |  | 500 kV, Limits ATC, Pre-Condition, Affects Cranking Path
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2020-09-08 09:30 | 2020-09-11 17:30 | N | N | component replacements including poles on str's 1-195 | Line |  |  | Pre-Condition
ATCO | 722s 702T (722s Crystal Lake) | 2020-09-08 10:00 | 2020-10-26 10:00 | N | N | construction replace 702T | Transformer | 722s 702T (722s Crystal Lake) | 722S 702T Construction Replace 702T | For Information Only
ALTALINK | 44s T1 (44s Bearspaw Plant) | 2020-09-08 11:00 | 2020-09-08 17:00 | N | N | relay maintenance | Transformer |  | techs to perform relay maintenance on the following: T1 A50/51/T1 SEL351A. | For Information Only
ATCO | 6L05 (764s Heisler - 843s Bigknife Creek) | 2020-09-08 11:00 | 2020-09-10 15:00 | N | N | pole changes | Line |  | Pole Changes | Creates Radial Feeds, Firm Load Loss
ALTALINK | 127s T1 (127s Bruderheim) | 2020-09-08 12:15 | 2020-09-10 17:45 | N | N | maintenance, leak repairs, and oil interceptor cleanup | Transformer |  |  | For Information Only
ALTALINK | 370s T1 (370s North Lethbridge) | 2020-09-08 13:00 | 2020-09-16 12:30 | N | N | install new T1 protections in control building 3 | Transformer | 370s T1 (370s North Lethbridge) |  | For Information Only
EPCOR | T2 (Namao) | 2020-09-09 07:00 | 2020-09-21 17:00 | N | N | ring outage for commissioning | Transformer | T2 (Namao) |  | Contingency Requires Mitigation, Creates Radial Feeds
ENMAX | 36.5TR (ENMAX 36), 16.63L (ENMAX 16 - ENMAX 36) | 2020-09-09 08:00 | 2020-09-10 16:00 | N | N | HV breaker maintenance | Transformer, Line | 16.63L (ENMAX 16 - ENMAX 36) |  | Overload
ALTALINK | 166s T1 (166s Dow Chemical Fort Saskatchewan) | 2020-09-09 08:15 | 2020-09-10 15:45 | N | N | replace T1 bushings | Transformer |  |  | For Information Only
ALTALINK | 719L (378s Shell Caroline - 719BL) | 2020-09-09 08:30 | 2020-09-09 12:30 | N | N | adding grounding alarms | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 283s C1 (283s Violet Grove) | 2020-09-09 08:30 | 2020-09-09 17:30 | N | N | maintenance | Shunts |  | Techs require a GOI on breaker 283s31 as ACC was unable to open the breaker remotely | For Information Only
ALTALINK | 299s Kingman RTU/SCADA | 2020-09-09 09:00 | 2020-09-09 17:00 | N | N | repair/replace D20ME RTU at site. | Terminal Equipment |  | Techs to repair/replace D20ME RTU at site. A few 10 minute supervisory outages during reboots, Currently we have no remote site visibility | Affects Visibility
ALTALINK | 15s T1 (15s Fort Macleod) | 2020-09-09 09:00 | 2020-09-10 17:00 | N | N | tap change and test | Transformer |  |  | For Information Only
ATCO | A793s 704 (A793s West Peace), 7L04 (A793s West Peace River - 839s Daishowa) | 2020-09-09 10:00 | 2020-09-11 16:00 | N | Y | protection upgrade, protection upgrade | Circuit Breaker, Line |  | 793S 704 GOI for 7L04 Protection Upgrade 7L04 Protection upgrade, construction and commission 7L04 will be out of service until protection is good this work is coordinated with the 701T Outage at 839S 2-51989 Sept 8-12, 2020 While the GOI at 839S Diashowa is occuring, we need a GOI on breaker 704 to finish the Protection Upgrade construction and commission. wiring commissioning AC Injection | For Information Only
ALTALINK | 719L (378s Shell Caroline - 575s Sundre) | 2020-09-09 12:31 | 2020-09-09 17:30 | N | Y | adding grounding alarms | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTAGAS | HMT1 AltaGas Harmattan | 2020-09-09 12:31 | 2020-09-09 17:30 | N | N | 719L (378s Shell Caroline - 575s Sundre) outage | Unit
ENMAX | 1.5TR (ENMAX 1) | 2020-09-10 08:00 | 2020-09-10 10:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2020-09-10 08:00 | 2020-10-05 06:59 | N | N | forced outage | Line | 72JM18 (805s Jasper - Meadowlark) |  | Creates Radial Feeds
ENMAX | 1.6TR (ENMAX 1) | 2020-09-10 10:00 | 2020-09-10 12:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 1.7TR (ENMAX 1) | 2020-09-10 12:00 | 2020-09-10 14:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2020-09-10 14:00 | 2020-09-10 16:00 | N | N | fall substation washing | Transformer |  |  | For Information Only
ALTALINK | 745AL (411s Obed - 745A1L) | 2020-09-11 07:00 | 2020-09-11 17:00 | N | N | maintenance on structures 7, 8 and 9 | Line
ALTALINK | 638S Esso Judy Creek | 2020-09-11 07:30 | 2020-09-11 17:00 | N | N | customer replacing cables | Station |  |  | For Information Only
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2020-09-11 08:00 | 2020-09-18 18:00 | N | N | security upgrades & install pole for cameras at NW corner at 27 SUB | Line | 16.61L (ENMAX 16 - ENMAX 27) |  | Creates Radial Feeds, Pre-Condition
SUNCOR | 635EDD-1000 635-752-152 (635EDD-1000), 635PL7-1002 (635EDD-1000 - 635EDD-1004) | 2020-09-11 08:00 | 2020-09-18 17:00 | N | N | maintenance of powerline 635PL7-1002 protection, 635PT-1028 transformer protection and breaker | Circuit Breaker, Line | 635EDD-1000 635-752-152 (635EDD-1000), 635PL7-1002 (635EDD-1000 - 635EDD-1004)
ENMAX | 47B138-771 (ENMAX 47) | 2020-09-11 08:00 | 2020-09-11 16:00 | N | N | HV breaker maintenance | Circuit Breaker |  |  | Pre-Condition
ENBRIDGE | Hay Lake North Series Capacitor | 2020-09-11 19:00 | 2020-09-14 07:00 | N | Y | series capacitors issues at Marias | Shunts |  |  | 240 kV, Limits ATC
ALTALINK | 276s 775X (276s Un Carb Prentiss), 775L (276s Prentiss - 535s Joffre) | 2020-09-12 07:30 | 2020-09-13 17:30 | N | N | moving modules up in rack 8 | Circuit Breaker, Line |  | Moving modules up in Rack 8. 775X control and 775L B differential protection required out of service. Require S775X breaker open. | For Information Only, Pre-Condition
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2020-09-12 09:00 | 2020-09-21 10:00 | N | N | Suncor maintenance. | Transformer | 184s T2 (184s Petro-Canada Edmonton) |  | For Information Only
ALTALINK | 370s 770E (370s North Lethbridge), 770L (254s Coaldale - 370s North Lethbridge) | 2020-09-14 07:00 | 2020-09-14 11:00 | N | N | trip test 370s770E (breaker 752) initiated by 370s175 (552) breaker fail protection | Circuit Breaker, Line | 370s 770E (370s North Lethbridge), 770L (254s Coaldale - 370s North Lethbridge) |  | For Information Only
EPCOR | CV5 (511s Victoria - 557s Castle Downs) | 2020-09-14 07:00 | 2020-09-27 17:00 | N | Y | maintenance and splice repair | Line | CV5 (511s Victoria - 557s Castle Downs) |  | 240 kV, For Information Only
MONTANA | 120s 27 (120s Picture Butte), MATL (120s Picture Butte - Montana) | 2020-09-14 07:00 | 2020-09-18 19:00 | N | Y | maintenance | Switch, Line | 120s 27 (120s Picture Butte) |  | 240 kV, Limits ATC
EPCOR | 330p 1202 (330p Genesee) | 2020-09-14 07:00 | 2020-09-16 17:00 | N | Y | doble | Circuit Breaker | 330p 1202 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
ALTALINK | 793L (87s Gaetz - 535s Joffre) | 2020-09-14 07:15 | 2020-09-17 17:45 | N | N | SCADA upgrade | Line | 793L (87s Gaetz - 535s Joffre) |  | Contingency Requires Mitigation, Affects Cranking Path
ATCO | 848s 902T (848s Ruth Lake) | 2020-09-14 08:00 | 2020-09-18 17:00 | N | Y | major testing | Transformer | 848s 902T (848s Ruth Lake) | 902T MAJOR TESTING | Over/Under Voltage, Pre-Condition
ENMAX | 10.2TR (ENMAX 10) | 2020-09-14 08:00 | 2020-09-23 16:00 | N | N | power factor test transformer and maintenance | Transformer |  | power factor test transformer. Transformer Secondary Cable Tests. Transformer maintenance. Oil sampling MT, TC. Investigate noise coming from 10B8-10.16 Cell. OH Crew required | For Information Only
ENMAX | 11.82L (ENMAX 11 - ENMAX 14), 14.1TR (ENMAX 14), 14.3TR (ENMAX 14), 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2020-09-14 08:00 | 2020-09-14 13:00 | N | N | fall substation washing | Line, Transformer, Shunts | 11.82L (ENMAX 11 - ENMAX 14), 14.1C (ENMAX 14), 14.2C (ENMAX 14) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 811s 701C (811s Clairmont Lake) | 2020-09-14 08:00 | 2020-09-28 16:00 | N | N | wiring modification SCADA end-end checks | Shunts | 811s 701C (811s Clairmont Lake) | Wiring modification to 700PT2, 701C CT Work, 701CCS Logic/Alarms, SCADA End-End Checks | Pre-Condition
ENMAX | 1.7TR (ENMAX 1) | 2020-09-14 08:00 | 2020-09-17 16:00 | N | N | tapchanger inspection, LTC drive shaft boot replacement | Transformer | 1.7TR (ENMAX 1) | tapchanger inspection, 1.7TR LTC drive shaft boot replacement | For Information Only
ATCO, ALTALINK | 840S McNeill Station, 830L (562s Cypress - 840s McNeill Station) | 2020-09-14 08:00 | 2020-09-24 17:00 | Y | Y | 840S McNeill fall 2020 outage PRC-005 maintenance | Station, Line | 830L (562s Cypress - 840s McNeill Station), MCNEILLSTATION | 840S McNeill Fall 2020 Outage PRC-005 Maintenance | Limits ATC
ENMAX | 25B240-D134 (ENMAX 25) | 2020-09-14 08:00 | 2020-09-14 11:00 | N | Y | SF6 sample | Circuit Breaker | 25B240-D134 (ENMAX 25) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 510s ACF12 (510s Sunnybrook) | 2020-09-14 08:30 | 2020-09-17 16:30 | N | Y | annual inspection & maintenance | Shunts | 510s ACF12 (510s Sunnybrook) |  | 500 kV, For Information Only
BCH, ALTALINK | 1L274 (48s Pocaterra - Britt Creek), 48s 887X (48s Pocaterra) | 2020-09-14 09:00 | 2020-09-15 17:00 | Y | Y | maintenance | Line, Circuit Breaker | 1L274 (48s Pocaterra - Britt Creek) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 13L/158L (65s High River - 392s Black Diamond) | 2020-09-14 09:15 | 2020-10-09 17:15 | N | N | replace 69kV wood deadend with new steel structure with new MOD and faulting switch | Line | 13L (65s High River - 392s Black Diamond) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 25B240-D135 (ENMAX 25) | 2020-09-14 11:00 | 2020-09-14 13:00 | N | Y | SF6 sample | Circuit Breaker | 25B240-D135 (ENMAX 25) |  | 240 kV, For Information Only, Pre-Condition
ATCO | 6L05 (764s Heisler - 6L05 tap) | 2020-09-14 11:00 | 2020-09-17 15:00 | N | N | pole replacement | Line | 6L05 (764s Heisler - 6L05 tap) | 6L05 Pole replacement | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 271s T1 (271s Shell Jumping Pound) | 2020-09-14 11:30 | 2020-09-24 14:20 | N | N | oil reclaim | Transformer | 271s T1 (271s Shell Jumping Pound) |  | For Information Only
ALTALINK | 761L (38s East Edmonton - 71s Lamoureux) | 2020-09-14 12:30 | 2020-09-17 17:00 | N | N | component replacements including poles on Str's 1-195 | Line | 761L (38s East Edmonton - 71s Lamoureux) |  | Pre-Condition
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 14.2TR (ENMAX 14), 14.4TR (ENMAX 14), 14.1C (ENMAX 14), 14.2C (ENMAX 14) | 2020-09-14 13:00 | 2020-09-14 18:00 | N | N | fall substation washing | Line, Transformer, Shunts | 14.83L (ENMAX 14 - ENMAX 36), 14.1C (ENMAX 14), 14.2C (ENMAX 14) |  | Creates Radial Feeds, Pre-Condition
ALTALINK | 445s T2 (445s Elk River) | 2020-09-14 13:00 | 2020-09-17 17:00 | N | N | maintenance/ doble repairs andreplacements | Transformer | 445s T2 (445s Elk River) | maintenance/ doble, T2 TC maintenance, breather replacement, T2 temp gauge replacement, leak repairs, and new TC counter. T2 Bushing replacements, T2 138kV LA Replacements, T2 25KV LA Addition | For Information Only
ENMAX | 25B240-D136 (ENMAX 25) | 2020-09-14 13:00 | 2020-09-14 16:00 | N | Y | SF6 sample | Circuit Breaker | 25B240-D136 (ENMAX 25) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 370s 2152 (370s North Lethbridge), 370s T3 (370s North Lethbridge) | 2020-09-15 07:00 | 2020-09-15 10:30 | N | N | trip test 370s2152 | Circuit Breaker, Transformer | 370s 2152 (370s North Lethbridge) | Trip test 370s2152 (Breaker 2152) initiated by 370s175 (552) Breaker Fail Protection | 240 kV, Contingency Requires Mitigation
ALTALINK | 378s 452 (378s Shell Caroline) | 2020-09-15 07:30 | 2020-09-15 12:30 | N | N | 138kV breaker maintenance | Circuit Breaker | 378s 452 (378s Shell Caroline) |  | Contingency Requires Mitigation
ALTALINK | 237s 252 (237s Foothills) | 2020-09-15 07:30 | 2020-09-15 13:00 | N | N | fix burned out tank heater | Circuit Breaker | 237s 252 (237s Foothills) |  | Contingency Requires Mitigation
ALTALINK | 736L (38s East Edmonton - 293s Bernese), 38s 736E (38s East Edmonton) | 2020-09-15 07:30 | 2020-09-15 17:30 | N | N | installation of grading capacitors to breaker 38s736E | Line, Circuit Breaker | 38s 736E (38s East Edmonton), 736L (38s East Edmonton - 293s Bernese) |  | For Information Only, Pre-Condition
ALTALINK | 19s T10 (19s Wabamun), 19s T8 (19s Wabamun), 19S Wabamun 138kV Bus2 | 2020-09-15 08:00 | 2020-09-21 18:30 | N | Y | maintenance | Transformer, Bus | 19s 72 (19s Wabamun), 19s T10 (19s Wabamun), 19s T8 (19s Wabamun) |  | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX | 25B240-D141 (ENMAX 25) | 2020-09-15 08:00 | 2020-09-15 11:00 | N | Y | SF6 sample | Circuit Breaker | 25B240-D141 (ENMAX 25) |  | 240 kV, For Information Only, Pre-Condition
ENMAX | 1.81L (ENMAX 1 - ENMAX 20), 20.1TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2020-09-15 08:00 | 2020-09-15 12:00 | N | N | fall substation washing | Line, Transformer, Terminal Equipment | 25B240-D136 (ENMAX 25) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 225L (225s Magrath - 385s Spring Coulee) | 2020-09-15 08:00 | 2020-10-27 18:00 | N | N | maintenance | Line | 225L (225s Magrath - 385s Spring Coulee) |  | Contingency Requires Mitigation, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 191s T1 (191s N.W.Cardiff) | 2020-09-15 08:00 | 2020-09-15 16:00 | N | N | replace damaged T1 138kV LA's like for like | Transformer | 191s T1 (191s N.W.Cardiff) |  | For Information Only
ALTALINK | 709L (54s Fort Saskatchewan - 172s Sherritt), 172s T1 (172s Sherritt Gordon) | 2020-09-15 08:30 | 2020-09-16 17:00 | N | N | maintenance | Line, Transformer | 172s T1 (172s Sherritt Gordon), 709L (54s Fort Saskatchewan - 172s Sherritt) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 349s 10 (349s Stavely) | 2020-09-15 09:00 | 2020-09-15 17:00 | N | Y | 25kV breaker maintenance | Circuit Breaker | 349s 10 |  | Restricts Generation
ENMAX | 25 B240-D142 (ENMAX 25) | 2020-09-15 11:00 | 2020-09-15 13:00 | N | Y | SF6 sample | Circuit Breaker | 25B240-D142 (ENMAX 25) |  | 240 kV, Pre-Condition
ENMAX | 20.82L (ENMAX 20 - ENMAX 21), 20.3TR (ENMAX 20), 20PT138-Z31 (ENMAX 20) | 2020-09-15 12:00 | 2020-09-15 18:00 | N | N | fall substation washing | Line, Transformer, Terminal Equipment | 20.82L (ENMAX 20 - ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L69 (731s Elmworth - 815s Goodfare) | 2020-09-15 12:01 | 2020-09-27 16:00 | N | Y | protection upgrade | Line | 7L69 (731s Elmworth - 815s Goodfare) | 731S Elmworth Bkr Replacement and Protection Upgrade Northstone generation will not be required off line as there will be a temporary Rate of Change of Frequency protection in Place. Northstone DTT will be returned to normal at the end of outage | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 378s 552 (378s Shell Caroline) | 2020-09-15 12:31 | 2020-09-15 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker | 378s 552 (378s Shell Caroline) |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 25B240-D131 (ENMAX 25) | 2020-09-15 13:00 | 2020-09-15 16:00 | N | Y | SF6 sample | Circuit Breaker | 25B240-D131 (ENMAX 25) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 237s 652 (237s Foothills) | 2020-09-15 13:05 | 2020-09-15 17:00 | N | N | top-up low gas level. | Circuit Breaker | 237s 652 (237s Foothills) |  | Pre-Condition
AESO-SC | OATI | 2020-09-15 18:00 | 2020-09-15 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
ENMAX | 38.1TR (ENMAX 38) | 2020-09-16 07:00 | 2020-09-16 18:00 | N | N | roxtec installation | Transformer | 38.1TR (ENMAX 38) |  | For Information Only
ALTALINK | 43S Shell Canada Jumpingpound Jct | 2020-09-16 07:15 | 2020-09-20 17:45 | N | N | replace PT and replace with new, reposition 43s7 accordingly. T1 maintenance, doble, leak repair, customer maintenance | Station | 43s T1 (43s Shell Canada Jumping Pound Jct) |  | For Information Only
ALTALINK | 378s 152 (378s Shell Caroline) | 2020-09-16 07:30 | 2020-09-16 12:30 | N | N | breaker maintenance | Circuit Breaker | 378s 152 (378s Shell Caroline) |  | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 3AL (43s Shell Canada Jumping Pound jct - 3L tap), 3L (3L145 - 3L147) | 2020-09-16 07:45 | 2020-09-18 07:00 | N | N | changing strs 1,2,3 (aligns with customer outage) | Line | 3AL (43s Shell Canada Jumping Pound jct - 3L) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 25B240-D140 (ENMAX 25) | 2020-09-16 08:00 | 2020-09-16 12:00 | N | Y | SF6 Sample | Circuit Breaker | 25B240-D140 (ENMAX 25) |  | 240 kV, Contingency Requires Mitigation
ALTALINK, Lethbridge | 370s 207X (370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge) | 2020-09-16 08:00 | 2020-09-16 12:30 | N | Y | trip test 370s207X (breaker 252) initiated by 370s175 (552) breaker fail protection | Circuit Breaker, Line | 370s 207X (370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ENMAX | 31.84L (ENMAX 31 - ENMAX 32), 32.3TR (ENMAX 32) | 2020-09-16 08:00 | 2020-09-16 13:00 | N | N | fall substation washing | Line, Transformer | 31.84L (ENMAX 31 - ENMAX 32) |  | For Information Only
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2020-09-16 12:00 | 2020-09-16 16:00 | N | N | SF6 sample. 9B138-9.80 | Line | 9.80L (ENMAX 9 - ENMAX 31) |  | Creates Radial Feeds, Pre-Condition
ALTALINK | 370s 2552 (370s North Lethbridge), 370s T4 (370s North Lethbridge) | 2020-09-16 12:30 | 2020-09-17 10:00 | N | N | trip test 370s2552 initiated by 370s175 (552) breaker fail protection | Circuit Breaker, Transformer | 370s T4 (370s North Lethbridge), 370s 2552 (370s North Lethbridge) |  | For Information Only
ALTALINK | 378s 252 (378s Shell Caroline) | 2020-09-16 12:31 | 2020-09-16 17:30 | N | N | 138kV breaker maintenance | Circuit Breaker | 378s 252 (378s Shell Caroline) |  | Contingency Requires Mitigation
ENMAX | 32.83L (ENMAX 32 - ENMAX 40), 26.81L (ENMAX 26 - ENMAX 32), 32.1TR (ENMAX 32), 32.2TR (ENMAX 32) | 2020-09-16 13:00 | 2020-09-16 18:00 | N | N | Fall substation washing | Line, Transformer | 26.81L (ENMAX 26 - ENMAX 32), 32.83L (ENMAX 32 - ENMAX 40) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 370s T1 (370s North Lethbridge) | 2020-09-16 16:00 | 2020-09-22 07:30 | N | N | install new T1 protections in control building 3 | Transformer | 370s T1 (370s North Lethbridge) |  | For Information Only
ENMAX | 38.2TR (ENMAX 38) | 2020-09-17 07:00 | 2020-09-17 18:00 | N | N | roxtec installation. | Transformer | 38.2TR (ENMAX 38) |  | For Information Only
ALTALINK | 172s T2 (172s Sherritt Gordon) | 2020-09-17 07:30 | 2020-09-18 17:00 | N | N | doble, replace oil gauge and 138 kV insulators | Transformer | 172s T2 (172s Sherritt Gordon) | 172s T2 doble & 172s T2 Top Oil Gauge Req Replacement ,Replace 172s2 138kV Insulators. | Creates Radial Feeds, Firm Load Loss
ALTALINK | 378s 652 (378s Shell Caroline) | 2020-09-17 07:30 | 2020-09-17 12:30 | N | N | 138kV breaker maintenance | Circuit Breaker | 378s 652 (378s Shell Caroline) |  | Contingency Requires Mitigation, Pre-Condition
ENMAX | 33.83L (ENMAX 33 - ENMAX 41), 33B138-33.83 (ENMAX 33), 33.1TR (ENMAX 33) | 2020-09-17 08:00 | 2020-09-17 12:00 | N | N | fall substation washing | Line, Circuit Breaker, Transformer | 33.83L (ENMAX 33 - ENMAX 41) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 732L (299s Kingman - 732AL) | 2020-09-17 08:00 | 2020-09-17 17:30 | N | N | customer requested work at their station | Line |  | customer requested advice for work at their station | For Information Only
ALTALINK | 830L (562s Cypress - 840s McNeill Station) | 2020-09-17 08:00 | 2020-09-17 18:00 | Y | Y | reframe and mitigate line clearance violation | Line | 830L (562s Cypress - 840s McNeill Station) | Reframe 830L82 with horizontal line post insulators and lower Fortis cross arm to mitigate line clearance violation. | Limits ATC
ENMAX | 31.3TR (ENMAX 31) | 2020-09-17 08:00 | 2020-09-17 16:00 | N | N | main tank pressure relay corrective, oil sampling MT, TC | Transformer | 31.3TR (ENMAX 31) | 31.3TR Main Tank Pressure Relay Corrective. Oil Sampling MT, TC | For Information Only
ENMAX | 31.1C (ENMAX 31), 31B138-31CAP (ENMAX 31) | 2020-09-17 08:00 | 2020-09-17 16:00 | N | N | HV breaker maintenance | Shunts, Circuit Breaker | 31.1C (ENMAX 31) |  | For Information Only
ALTALINK | 370s 51 (370s North Lethbridge) | 2020-09-17 08:30 | 2020-09-17 16:30 | N | Y | urgent - relay module replacement | Circuit Breaker |  | Techs require breaker 370s51 to investigate and replace a failed relay module(RXMA1 relay). Urgent issue as ACC does not have closing control of breaker. | 240 kV, Contingency Requires Mitigation
ATCO | 7L40 (733s Simonette - 813s Little Smoky) | 2020-09-17 10:00 | 2020-09-22 17:00 | N | Y | XARM change out | Line | 7L40 (733s Simonette - 813s Little Smoky) | XARM change out | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 33.84L (ENMAX 33 - ENMAX 43), 33B138-33.84 (ENMAX 33), 33.2TR (ENMAX 33) | 2020-09-17 12:00 | 2020-09-17 18:00 | N | N | fall substation washing | Line, Circuit Breaker, Transformer | 33.84L (ENMAX 33 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 310p 2352 (310p Sundance) | 2020-09-17 12:20 | 2020-09-24 16:00 | N | Y | forced outage | Circuit Breaker | 310p 2352 (310p Sundance) |  | 240 kV, For Information Only
ENMAX | 38.3TR (ENMAX 38) | 2020-09-18 07:00 | 2020-09-18 18:00 | N | N | roxtec iInstallation. | Transformer | 38.3TR (ENMAX 38) |  | For Information Only
EPCOR | 5R ATP1382 (A.T. Plastics 5R), 738AL (A. T. Plastics 4R - A. T. Plastics 5R - 738L) | 2020-09-18 07:00 | 2020-09-20 17:00 | N | N | surge arrester replacement on T1, T3 and the gantry | Circuit Breaker, Line | 738L (95s Imperial Oil Edmonton - 738AL) | Surge arrester replacement on T1, T3 and the gantry. | For Information Only
ALTALINK, EPCOR | 738L (38s East Edmonton - 95s Imperial Oil Edmonton), 38s 738W (38s East Edmonton) | 2020-09-18 07:00 | 2020-09-18 09:00 | N | N | de-energize 738L to allow Epcor to open their 738AL1 switch for their work at AT Plastics | Line, Circuit Breaker | 738L (38s East Edmonton - 95s Imperial Oil Edmonton) 38s 738W (38s East Edmonton) | de-energize 738L to allow Epcor to open their 738AL1 switch for their work at AT Plastics | For Information Only
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2020-09-18 07:15 | 2020-09-18 17:45 | N | Y | emergency repair, damper repair (str 163, 203, 207) | Line |  | P5 urgent repair dampers 1005L Str's 163, 203, 207 Double circuits 1041L. Repairing damaged conductor | 240 kV, Pre-Condition, Overload
BCH | 1L274 (B1s BCH Natal - 1D1L274), 1L275 (799s Coleman - Natal) | 2020-09-18 08:00 | 2020-09-21 20:00 | N | Y | disconnect maintenance | Line | 1L274 (B1s BCH Natal - 1D1L274), 1L275 (799s Coleman - Natal) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK, ENMAX | 50L (44s Bearspaw Plant - ENMAX 21), 44s 50X (44s Bearspaw), 21.2TR (ENMAX 21), 21B138-21.CAP (ENMAX 21) | 2020-09-18 08:00 | 2020-09-18 18:00 | N | Y | fall substation washing | Line, Circuit Breaker, Transformer | 50L (44s Bearspaw Plant - ENMAX 21) |  | For Information Only, Pre-Condition
ENMAX | 162s 138-RB82 (162s Beddington) | 2020-09-18 08:00 | 2020-09-18 16:00 | N | N | HV breaker maintenance, dashpot checks | Circuit Breaker | 162s 138-RB82 (162s Beddington) | HV Breaker maintenance 162B138-RB82. Dashpot checks. | Contingency Requires Mitigation
ALTALINK | 199L (268s Whitecourt - 199L tap) | 2020-09-18 09:00 | 2020-09-18 17:00 | N | N | urgent repair to the structure | Line |  |  | Creates Radial Feeds, Over/Under Voltage, Overload, Pre-Condition
EPCOR | T2 (Kennedale) | 2020-09-19 07:30 | 2020-09-19 20:00 | N | N | check secondary cables and the terminations | Transformer |  |  | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2020-09-19 08:00 | 2020-10-05 13:00 | N | N | breaker overhaul 6B138-6.82 | Line | 6.82L (ENMAX 6 - ENMAX 41) | Hitachi HV Breaker Overhaul 6B138-6.82. | Creates Radial Feeds, Firm Load Loss
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 21.1TR (ENMAX 21), 21.4TR (ENMAX 21) | 2020-09-19 08:00 | 2020-09-19 18:00 | N | Y | fall substation washing | Line, Transformer | 21.80L (42s Sarcee - ENMAX 21), 20.82L (ENMAX 20 - ENMAX 21), 21.4TR (ENMAX 21) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 759L (87s Gaetz - 276s Prentiss), 276s Union Carbide Prentiss 138 kV Center Bus | 2020-09-20 07:00 | 2020-09-27 07:00 | N | N | upgrade bus SCADA and P&C | Line, Bus | 276s T1 (276s Union Carbide Prentiss) | T1 & BUS SCADA and P&C upgrades, installation of CT's on T1. Will reduce to 276sT1(Tx18470) GOI Sept 27th, 0700 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 276s T1 (276s Union Carbide Prentiss) | 2020-09-20 07:00 | 2020-09-29 18:00 | N | N | upgrade SCADA and P&C, installation of CT's on T1 | Transformer | 276s T1 (276s Union Carbide Prentiss) | T1 & BUS SCADA and P&C upgrades, installation of CT's on T1. Will reduce to 276sT1(Tx18470) GOI Sept 27th, 0700 | For Information Only
ATCO, IMPERIALOIL | 7L157 (837s Mahihkan - 970s Bourque), 7L105 (837s Mahihkan - 909s Mahno) | 2020-09-20 08:00 | 2020-09-20 17:00 | N | Y | install temporary bypass between 7L105 and 7L157 | Line | 7L157 (837s Mahihkan - 970s Bourque) | install Bypass installed to feed 7L105 from 7L157 for 702@ 837S maintenance 7L157D2 will remain open after the Bypass is installed see 2-52891 837S 702 breaker ct change. | Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ENMAX | 15.60L (ENMAX 15 - ENMAX 21), 21.61L (ENMAX 21 - ENMAX 34), 21.4TR (ENMAX 21) | 2020-09-20 08:00 | 2020-09-20 18:00 | N | N | fall substation washing | Line, Transformer | 15.60L (ENMAX 15 - ENMAX 21), 21.61L (ENMAX 21 - ENMAX 34) | Fall Substation Washing. Oil sampling MT, Bushing 21.4TR. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L157 (837s Mahihkan - 970s Bourque), 837s 702 (837s Mahihkan) | 2020-09-20 08:00 | 2020-09-27 17:00 | N | N | change CT on breaker 702 | Circuit Breaker, Line | 7L157 (837s Mahihkan - 970s Bourque), 837s 702 (837s Mahihkan) | CT Change on breaker 702 There will be a Bypass installed tying 7L105 to 7L157. 7L157 will be open ended at 970S Bourque 7L157D2 will be open, 970S ring bus closed. 7L105 will back feed through Breaker 701@ 837S Mahihkan. This is being done to maintain the metering for 7L105 | Affects Visibility, Contingency Requires Mitigation
ALTALINK, EPCOR | 38s 738W (38s East Edmonton), 738L (38s East Edmonton - 95s Imperial Oil Edmonton) | 2020-09-20 17:00 | 2020-09-20 19:00 | N | N | de-energize 738L to close 738AL1 switch for work at AT Plastics | Circuit Breaker, Line |  | de-energize 738L to allow Epcor to close their 738AL1 switch for their work at AT Plastics | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 8L10 Luscar | 2020-09-21 07:00 | 2020-09-25 17:00 | N | N | maintenance, doble | Terminal Equipment | 8L10 (330P Genesee - Fording Coal Mine) |  | For Information Only
EPCOR | CV5 (511s Victoria - 557s Castle Downs), E511s Victoria T5 (511s Victoria) | 2020-09-21 07:00 | 2020-09-22 17:00 | N | Y | doble and repair | Line, Transformer | CV5 (511s Victoria - 557s Castle Downs), E511s Victoria T5 (511s Victoria) | Doble 250CV5 CVVT/CT's zone at Castledowns, and Low side CVT's of TX5 at Victoria. VDS21 Repair. | 240 kV, Contingency Requires Mitigation
ALTALINK, EPCOR | 1044L (805s Jasper - 816s Petrolia) | 2020-09-21 07:00 | 2020-09-25 17:00 | N | Y | VT replacement | Line | 1044L (805s Jasper - 816s Petrolia) |  | 240 kV, Pre-Condition
ALTALINK | 759L (87s Gaetz - 276s Prentiss) | 2020-09-21 07:15 | 2020-09-24 17:45 | N | N | SCADA upgrade | Line | 759L (87s Gaetz - 276s Prentiss) |  | For Information Only
ALTALINK | 172s T3 (172s Sherritt Gordon), 172s 73 (172s Sherrit) | 2020-09-21 07:30 | 2020-09-22 18:00 | N | N | bushings, doble,172s73 breaker maintenance | Transformer, Circuit Breaker | 172s T3 (172s Sherritt Gordon) |  | For Information Only
ENMAX | 13.82L (ENMAX 13 - ENMAX 22), 22.1TR (ENMAX 22), 22.3TR (ENMAX 22), 22PT138-31 (ENMAX 22) | 2020-09-21 08:00 | 2020-09-21 16:00 | N | N | fall substation washing | Line, Transformer, Terminal Equipment | 13.82L (ENMAX 13 - ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 770s 705 (770s Three Hills), 770s 705C (770s Three Hills) | 2020-09-21 08:00 | 2020-09-21 16:00 | N | N | test trip coils on breaker 705 | Circuit Breaker, Shunts | 770s 705C (770s Three Hills) | Test trip coils on Bkr 705, 705C-Cap bank will be out of service | Pre-Condition
ENMAX | 36.3TR (ENMAX 36) | 2020-09-21 08:00 | 2020-09-25 18:30 | N | N | plastibeton tray replacement | Transformer | 36.3TR (ENMAX 36) | Plastibeton Tray Replacement at 36 Sub | For Information Only
ATCO | 2029s ACF21 (2029s Heathfield) | 2020-09-21 08:00 | 2020-09-23 17:00 | N | Y | ACF21 CA-300 CT Upgrades, redundant filter banks in service, no system impact | Shunts | 2029s ACF21 (2029s Heathfield) | ACF21 CA-300 CT Upgrades, redundant filter banks in service, no system impact | 500 kV, For Information Only
ENMAX | 8.4TR (ENMAX 8) | 2020-09-21 08:00 | 2020-09-23 16:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
ALTALINK | 510s ACF22 (510s Sunnybrook) | 2020-09-21 08:30 | 2020-09-23 16:30 | N | Y | annual inspection & maintenance | Shunts | 510s ACF22 (510s Sunnybrook) |  | 500 kV, For Information Only
REDDEER | 217s T1 (217s North Red Deer), 217s T2 (217s North Red Deer) | 2020-09-21 09:00 | 2020-09-29 18:00 | N | N | 25kV breaker replacements to 14-B-13, 13-B-31 and 14-B-38 | Transformer | 217s T1 (217s North Red Deer), 217s T2 (217s North Red Deer) |  | For Information Only
ALTALINK | 787L (166s Dow Chemical Fort Saskatchewan - 787AL) | 2020-09-21 09:00 | 2020-09-22 18:00 | N | Y | maintenance on structures 38, 40, 41, 42 | Line | 787L (166s Dow Chemical Fort Saskatchewan - 787AL) | Maintenance on structures 38, 40, 41, 42 | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ATCO | 7L49 (729s Otauwau - 732s Mitsue), 729s 705 (729s Otauwau) | 2020-09-21 09:00 | 2020-09-21 12:00 | N | N | PRC-005 - breaker trip coil testing , 705 at 729S | Line, Circuit Breaker | 7L49 (729s Otauwau - 732s Mitsue), 729s 705 (729s Otauwau) | PRC-005 - BREAKER TRIP COIL TESTING, 705 at 729S | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 310p 2452 (310p Sundance), 310p 2352 (310p Sundance) | 2020-09-21 09:30 | 2020-09-24 17:15 | N | Y | convert last of SCADA items to new RTU | Circuit Breaker | 310p 2352 (310p Sundance), 310p 2452 (310p Sundance) | Convert last of SCADA items to new RTU. | 240 kV, For Information Only
ALTALINK | 385s T1 (385s Spring Coulee) | 2020-09-21 11:15 | 2020-09-24 17:45 | N | N | replace 3 HV, HO, LO bushings | Transformer | 385s T1 (385s Spring Coulee) |  | For Information Only
ATCO | 7L159 (948s Heatburg - 7L159 tap) | 2020-09-21 12:00 | 2020-09-25 16:00 | N | N | crossarm/insulator replacement | Line | 7L159 (948s Heatburg - 7L159 tap) | Crossarm/insulator replacement | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 733s 702 (733s Simonette) | 2020-09-21 13:00 | 2020-09-22 17:00 | N | Y | breaker SF6 HPL partial testing | Circuit Breaker | 7L40 (733s Simonette - 813s Little Smoky), 733s 702 (733s Simonette) | BREAKER SF6 HPL PARTIAL TESTING @ SIMONETTE 733S 702 Top up low pole, investigate leaks, partial main. Line is open ended. (Transmission line crew has line out until Sept 21) continued outage with 2-52675 | For Information Only
ALTALINK | 283s C1 (283s Violet Grove), 283s 31 (283s Violet Grove) | 2020-09-21 14:30 | 2020-10-08 14:30 | N | N | urgent repair | Shunts, Circuit Breaker | 283s C1 (283s Violet Grove), 283s 31 (283s Violet Grove) | 283s31 Failed to Trip and requires investigation and repairs open the breaker remotely. | For Information Only
ALTALINK | 600L (404s Peace Butte - 523s Bullshead) | 2020-09-22 06:00 | 2020-09-22 19:00 | N | N | maintenance | Line |  | Replace 600L Str 2A and modify Str 3 for line clearance mitigation. Coordinated with customer planned shut down. | For Information Only
Lethbridge, ALTALINK | 172L (181s Chinook - 370s North Lethbridge), 370s T1 (370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge), 770L (254s Coaldale - 370s North Lethbridge), 370s T3 (370s North Lethbridge), 370s North Lethbridge 138kV Bus 1 | 2020-09-22 06:30 | 2020-10-05 17:30 | N | Y | bus & T1 protection cut over & reconductoring of substation bus & trip testing new protections. replacement of switches s1, s3, s27, s171 & s174 | Line, Transformer, Bus | 370s T1 (370s North Lethbridge), 172L (181s Chinook - 370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge) |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 9.2TR (ENMAX 9) | 2020-09-22 07:00 | 2020-09-22 18:00 | N | N | Roxtec Installation. | Transformer |  |  | For Information Only
ATCO | 844s 701T (844s AEC Mill) | 2020-09-22 07:00 | 2020-09-22 20:00 | N | N | maintenance | Transformer |  | Isolate Transformer 702T to coincide with customer planned outage Install remaining Green Jacket on 701T at 844S AEC Mill....Master Work on Transformer Leaks/install bird guard 401TD | For Information Only
ATCO | 844s 702T (844s AEC Mill) | 2020-09-22 07:00 | 2020-09-23 07:00 | N | N | maintenance | Transformer |  | Isolate Transformer 702T to coincide with customer planned outage | For Information Only
ALTALINK | 944L (132s Ware Junction - 275s Jenner) | 2020-09-22 07:15 | 2020-09-29 17:45 | N | Y | maintenance | Line | 944L (132s Ware Junction - 275s Jenner) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 6L99 (727s Kinuso - 745s Slave Lake) | 2020-09-22 08:00 | 2020-09-22 16:00 | N | N | maintenance | Line | 6L99 (727s Kinuso - 745s Slave Lake) | Remove temp bypass and install new overhead connections to new Kinuso substation | Creates Radial Feeds, Firm Load Loss
ALTALINK | 835L (283s Violet Grove - 835AL), 835L (384s Keystone - 835AL) | 2020-09-22 08:00 | 2020-09-22 15:00 | N | N | P5 urgent repair & HRFA on 835AL (Str 28, 32, 35) | Line |  |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 13.2TR (ENMAX 13) | 2020-09-22 08:00 | 2020-09-25 16:00 | N | N | repair, maintenance & testing | Transformer | 13.2TR (ENMAX 13) | Corrective Oil Leak Repair. Transformer maintenance. Oil sampling MT, TC. Gas relay testing. | For Information Only
ENMAX | 24.81L (ENMAX 24 - ENMAX 31) | 2020-09-22 08:00 | 2020-09-24 16:00 | N | N | interphase spacers installation | Line | 24.81L (ENMAX 24 - ENMAX 31) |  | For Information Only
ATCO | 856s 902T (856s Kinosis) | 2020-09-22 08:00 | 2020-09-25 17:00 | N | Y | preventive maintenance | Transformer | 856s 902T (856s Kinosis) | 902T preventive maintenance and bird proofing, 901T and 903T will be in service | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 723L (438s Westlock - 724L tap) | 2020-09-22 08:00 | 2020-09-22 17:00 | N | N | maintenance | Line | 723L (438s Westlock - 724L) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
CMH | MH69s1 69kV South Bus (MH69s1 Power P Switchyard), MH69s1 MH69-10 (MH69s1 Power P Switchyard), MH69s1 MH69-31 (MH69s1 Power P Switchyard), 8L (MH69S-1 Power Plant - MH69S-6 Riverview) | 2020-09-22 08:00 | 2020-09-26 16:00 | N | N | upgrades | Bus, Circuit Breaker, Line | 8L (MH69S-1 Power Plant - MH69S-6 Riverview) |  | For Information Only
ALTALINK | 77s 14 (77s Sagitawah) | 2020-09-22 09:00 | 2020-09-22 18:30 | N | Y | 77s14 maintenance including 1st trip test | Circuit Breaker | 77s 14 (77s Sagitawah) |  | 240 kV, Contingency Requires Mitigation
ENMAX, ALTALINK | 2MD138-2.1CAP (ENMAX 2), 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-09-22 09:00 | 2020-09-22 10:00 | N | N | Substation washing 5S7E | Switch, Shunts | 5s C3 (5s East Calgary), 5s C4 (5s East Calgary) |  | Contingency Requires Mitigation, Pre-Condition
ATCO | 729s 704 (729s Otauwau), 7L162 (729s Otauwau - 732s Mitsue) | 2020-09-22 09:00 | 2020-09-22 12:00 | N | N |  | Line, Circuit Breaker | 7L162 (729s Otauwau - 732s Mitsue), 729s 704 (729s Otauwau) | PRC-005 - BREAKER TRIP COIL TESTING, 704 at 729S | Creates Radial Feeds, Firm Load Loss
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2020-09-22 09:00 | 2020-09-24 18:00 | N | N | components and structure replacement's on 207L. Str's Range 1-23 | Line | 207L (111s Coalbanks - 370s North Lethbridge) |  | For Information Only
ENMAX | 2.3TR (ENMAX 2) | 2020-09-22 10:00 | 2020-09-22 11:00 | N | N | substation washing | Transformer | 2.3TR (ENMAX 2) |  | For Information Only
ENMAX | 2.1TR (ENMAX 2) | 2020-09-22 11:00 | 2020-09-22 13:00 | N | N | substation washing | Transformer | 2.1TR (ENMAX 2) |  | For Information Only, Pre-Condition
ALTALINK | 575s 719X (575s Sundre), 719L (575s Sundre - 719CL) | 2020-09-22 11:00 | 2020-09-24 17:00 | N | Y | settings changes of sync check and functional testing on CUH90 relay for 575s719X | Circuit Breaker, Line | 575s 719X (575s Sundre), 719L (575s Sundre - 719CL) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 184s T3 (184s Petro-Canada Edmonton) | 2020-09-22 13:00 | 2020-09-30 10:00 | N | N | leak repairs and mitigate NGR limits of approach, customer maintenance | Transformer | 184s T3 (184s Petro-Canada Edmonton) | 184sT3 leak repairs and mitigate NGR limits of approach. Suncor maintencance | For Information Only
ENMAX | 2.2TR (ENMAX 2) | 2020-09-22 13:00 | 2020-09-22 14:00 | N | N | substation washing | Transformer | 2.2TR (ENMAX 2) |  | For Information Only, Pre-Condition
ENMAX | 2.4TR (ENMAX 2) | 2020-09-22 14:00 | 2020-09-22 15:00 | N | N | substation washing | Transformer | 2.4TR (ENMAX 2) |  | For Information Only, Pre-Condition
ALTALINK | 787L (71s Lamoureux - 787AL) | 2020-09-23 07:00 | 2020-09-25 18:00 | N | Y | maintenance on structures 2, 3, 8, 12, 13, 15, 16, 21, 22, 23,24, 25, 26, and 28, maintenance on 71s452 | Line | 787L (71s Lamoureux - 787AL) |  | Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
CNRL | 842s 75-TR-7701 (842s Horizon Upgrading) | 2020-09-23 07:30 | 2020-09-26 18:00 | N | Y | transformer maintenance | Transformer | 842s 75-TR-7701 (842s Horizon Upgrading) |  | 240 kV
ALTALINK | 178s T1 (178s Cynthia) | 2020-09-23 07:30 | 2020-09-23 16:30 | N | N | installation of doble IDD bushing monitors | Transformer | 178s T1 (178s Cynthia) |  | For Information Only
ALTALINK | 723L (150s Clyde - 438s Westlock) | 2020-09-23 08:00 | 2020-09-27 17:00 | N | N | maintenance on structures | Line | 723L (150s Clyde - 438s Westlock) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 742s 601T (742s Freeman Lake) | 2020-09-23 08:00 | 2020-10-07 16:00 | N | N | Decommission Sept 30, 2020 | Transformer
ALTALINK | 388s 708A (388s Riverside), 708AL (388s Riverside - 708L tap) | 2020-09-23 08:00 | 2020-09-23 16:00 | N | Y | maintenance and 1st trip testing and repair breaker fail | Circuit Breaker, Line | 388s 708A (388s Riverside), 708L (233s Beamer - 708AL) |  | Restricts Generation, Affects Cranking Path
ENMAX | 2.81L (ENMAX 2 - ENMAX 9), 9.83L (ENMAX 9 - ENMAX 43), 9.3TR (ENMAX 9), 9.2TR (ENMAX 9) | 2020-09-23 08:00 | 2020-09-23 16:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 51s 408N (51s Wainwright), 408L (51s Wainwright - 252s Jarrow) | 2020-09-23 08:30 | 2020-09-23 17:00 | N | N | maintenance and 1st trip 1st close, 2nd trip | Circuit Breaker, Line | 51s 408N (51s Wainwright), 408L (51s Wainwright - 252s Jarrow) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 77s 26 (77s Sagitawah) | 2020-09-23 09:00 | 2020-09-23 17:00 | N | Y | maintenance including 1st trip test | Circuit Breaker | 77s 26 (77s Sagitawah) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 77s 29 (77s Sagitawah) | 2020-09-23 17:00 | 2020-09-24 16:00 | N | Y | maintenance including 1st trip test | Circuit Breaker | 77s 29 (77s Sagitawah) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 927L (102s Langdon - 356s Milo) | 2020-09-24 07:15 | 2020-09-24 17:45 | N | N | urgent interphase spacers str's (221-222) | Line | 927L (102s Langdon - 356s Milo) | P5 Urgent Interphase Spacers Str's (221-222) Double circuits 924L | 240 kV,Affects Cranking Path
SUNCOR | 29EDD-71 752-4642 (29EDD-71), 29EDD-71 752-4644 (29EDD-71) | 2020-09-24 08:00 | 2020-09-26 18:00 | N | N | 29PT-247 install and test MVT | Circuit Breaker | 29EDD-71 752-4642 (29EDD-71), 29EDD-71 752-4644 (29EDD-71) |  | For Information Only, Pre-Condition
ENMAX, ALTALINK | 28.80L (42s Sarcee - ENMAX 28), 28.2TR (ENMAX 28) | 2020-09-24 08:00 | 2020-09-24 12:00 | N | Y | fall substation washing | Line, Transformer | 28.80L (42s Sarcee - ENMAX 28) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 606L (184s Petro-Canada Edmonton - 185s Bretville) | 2020-09-24 08:30 | 2020-09-24 14:30 | N | N | remove modify structure 606L10 for line clearance mitigation | Line | 606L (184s Petro-Canada Edmonton - 185s Bretville) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 1.80L (ENMAX 1 - ENMAX 28), 28.1TR (ENMAX 28) | 2020-09-24 12:00 | 2020-09-24 18:00 | N | N | fall substation washing | Line, Transformer | 1.80L (ENMAX 1 - ENMAX 28) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | N721 (Namao), N722 (Namao), T1 (Namao) | 2020-09-25 07:00 | 2020-10-02 16:00 | N | N | motorized disconnect replacement | Circuit Breaker, Transformer | T1 (Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
CNRL | 842s 75-TR-5701 (842s Horizon Upgrading) | 2020-09-25 07:30 | 2020-09-29 18:00 | N | Y | transformer maintenance | Transformer | 842s 75-TR-5701 (842s Horizon Upgrading) |  | 240 kV, For Information Only
ENMAX | 22.1TR (ENMAX 22) | 2020-09-25 08:00 | 2020-09-25 16:00 | N | N | slip over CT ground shield ground wire corrective, low LTC oil Y winding | Transformer | 22.1TR (ENMAX 22) | 22.1TR Slip over CT ground shield ground wire corrective. 22.1TR Low LTC oil Y winding | For Information Only
ENMAX | 41.2TR (ENMAX 41) | 2020-09-25 08:00 | 2020-09-25 16:00 | N | N | replacement of external control wiring | Transformer | 41.2TR (ENMAX 41) |  | For Information Only
EPCOR | 330p 801 (330p Genesee), 330P SST3 (330P Genesee) | 2020-09-26 05:30 | 2020-09-27 17:30 | N | N |  | Circuit Breaker, Transformer | 330p 801 (330p Genesee)
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 38.1TR (ENMAX 38), 38.3TR (ENMAX 38), 38.1C (ENMAX 38) | 2020-09-26 08:00 | 2020-09-26 13:00 | N | N | Fall substation washing | Line, Transformer, Shunts | 38.83L (ENMAX 38 - ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 849s 903 (849s Joslyn Creek) | 2020-09-26 08:30 | 2020-09-26 12:30 | N | Y | PRC-005 trip coil testing | Circuit Breaker | 849s 903 (849s Joslyn Creek) | PRC-005 - TRIP COIL TESTING - BREAKER 903 @ 849S BREAKER 903 OOS | 240 kV, Contingency Requires Mitigation
ATCO | 849s 906 (849s Joslyn Creek) | 2020-09-26 13:00 | 2020-09-26 15:00 | N | Y | PRC-005 trip coil testing | Circuit Breaker | 849s 906 (849s Joslyn Creek) | PRC-005 - TRIP COIL TESTING - BREAKER 906 @ 849S BREAKER 906 OOS | 240 kV, Contingency Requires Mitigation
ENMAX | 38.1C (ENMAX 38), 37.81L (ENMAX 37 - ENMAX 38), 38.2TR (ENMAX 38), 38.3TR (ENMAX 38) | 2020-09-26 13:00 | 2020-09-26 18:00 | N | N | Fall substation washing | Shunts, Line, Transformer | 37.81L (ENMAX 37 - ENMAX 38), 38.1C (ENMAX 38) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO, CNRL | 849s 907 (849s Joslyn Creek), 75-PLH-901 (838s Horizon Mining - 849s Joslyn) | 2020-09-26 15:00 | 2020-09-26 17:00 | N | Y | PRC-005 - trip coil testing | Circuit Breaker, Line | 75-PLH-901 (838s Horizon Mining - 849s Joslyn), 849s 907 (849s Joslyn Creek) | PRC-005 - TRIP COIL TESTING - BREAKER 907 @ 849, To be coordinated with CNRL Horizon Shutdown 75-PLH-901 open ended at 849S Joslyn | 240 kV, Creates Radial Feeds
CNRL | 842s 75-TR-8701 (842s Horizon Upgrading) | 2020-09-27 07:30 | 2020-10-02 18:00 | N | Y | transformer maintenance | Transformer | 842s 75-TR-8701 (842s Horizon Upgrading) |  | 240 kV, Pre-Condition
ATCO, IMPERIALOIL | 7L157 (837s Mahihkan - 970s Bourque), 7L105 (837s Mahihkan - 909s Mahno) | 2020-09-27 08:00 | 2020-09-27 17:00 | N | Y | remove 7L105 /7L157 bypass | Line | 7L157 (837s Mahihkan - 970s Bourque) | Remove 7L105 /7L157 Bypass | Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 5s T1 (5s East Calgary), 5s East Calgary 240kV Bus 1, 5s 1152 (5s East Calgary), 5s 1652 (5s East Calgary) | 2020-09-27 08:00 | 2020-09-27 10:00 | N | Y | substation washing | Transformer, Bus, Circuit Breaker | 5s T1 (5s East Calgary) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 115s T2 (115s Mt.Allan) | 2020-09-27 08:30 | 2020-10-02 18:00 | N | N | fix leaks, doble, SFRA | Transformer |  |  | For Information Only
ALTALINK | 5s T2 (5s East Calgary), 5s East Calgary 240kV Bus 2, 5s 1552 (5s East Calgary), 5s 1252 (5s East Calgary) | 2020-09-27 10:00 | 2020-09-27 11:00 | N | Y | Substation washing | Transformer, Bus, Circuit Breaker | 5s T2 (5s East Calgary) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13), 5.9TR (ENMAX 5), 5.10TR (ENMAX 5) | 2020-09-27 11:00 | 2020-09-27 18:00 | N | N | fall substation washing | Line, Transformer | 2.83L (ENMAX 5 - 2.83L tap) |  | Pre-Condition
ALTALINK | 777L (48s Pocaterra - 245s Seebe) | 2020-09-28 06:15 | 2020-10-23 17:45 | N | Y | maintenance and structure replacements (Str 1 - 226) and PLC replacement after line work complete | Line | 777L (48s Pocaterra - 245s Seebe) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 72JM18 (805s Jasper - Meadowlark), T1 (Meadowlark) | 2020-09-28 07:00 | 2020-10-02 17:00 | N | N | oil leak repair and spill remediation | Line, Transformer
ALTALINK | 268s T1 (268s Whitecourt) | 2020-09-28 07:00 | 2020-10-08 19:00 | N | Y | high and low side bushings replacement along with oil leak mitigation on T1 & VR1 | Transformer | 268s T1 (268s Whitecourt) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ENMAX | 10.2TR (ENMAX 10) | 2020-09-28 07:00 | 2020-09-28 18:00 | N | N | roxtec installation. | Transformer | 10.2TR (ENMAX 10) |  | For Information Only
ALTALINK | 87s T1 (87s Gaetz) | 2020-09-28 07:30 | 2020-10-01 17:30 | N | Y | SCADA upgrade | Transformer | 87s T1 (87s Gaetz) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2020-09-28 08:00 | 2020-09-30 16:00 | N | N | interphase spacers installation | Line | 9.80L (ENMAX 9 - ENMAX 31)
ENMAX | 3.84L (ENMAX 3 - ENMAX 13) | 2020-09-28 08:00 | 2020-10-09 16:00 | N | N | line protection upgrade, control cable swap out, arc flash mitigation project | Line | 3.84L (ENMAX 13 - ENMAX 3) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 14.83L (ENMAX 14 - ENMAX 36), 16.63L (ENMAX 16 - ENMAX 36), 36.2TR (ENMAX 36), 36.5TR (ENMAX 36) | 2020-09-28 08:00 | 2020-09-28 13:00 | N | N | fall substation washing, check reversing switch | Line, Transformer | 14.83L (ENMAX 14 - ENMAX 36), 16.63L (ENMAX 16 - ENMAX 36), 36.5TR (ENMAX 36), 36.2TR (ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss
SUNCOR | 29PL9-15 (29EDD-34 - 29EDD-56) | 2020-09-28 08:00 | 2020-10-07 18:00 | N | Y | maintenance, repair leak | Line | 29PL9-15 (29EDD-34 - 29EDD-56), |  | 240 kV, Creates Radial Feeds, Firm Load Loss
CMH | MH69s1 MH69-28 (MH69s1 Power P Switchyard), MH69s1 MH69-31 (MH69s1 Power P Switchyard), MH69s1 MH69-T3B (MH69s1 Power P Switchyard) | 2020-09-28 08:00 | 2020-10-08 09:00 | N | N | upgrades | Circuit Breaker, Transformer | MH69s1 MH69-28 (MH69s1 Power P Switchyard), MH69s1 MH69-31 (MH69s1 Power P Switchyard), MH69s1 MH69-T3B (MH69s1 Power P Switchyard)
ALTALINK | 902L (19s Wabamun - 310p Sundance), 905L (19s Wabamun - 37s North Calder), 19s T10 (19s Wabamun), 19s T8 (19s Wabamun) | 2020-09-28 08:00 | 2020-10-05 18:30 | N | Y | replacing 240kV string insulators | Line, Transformer | 902L (19s Wabamun - 310p Sundance), 905L (19s Wabamun - 37s North Calder), 19s T10 (19s Wabamun), 19s T8 (19s Wabamun) |  | 240 kV, Over/Under Voltage, Pre-Condition
ENMAX | 16.1TR (ENMAX 16) | 2020-09-28 08:00 | 2020-10-01 16:00 | N | N | replace faulty metering CT | Transformer | 16.1TR (ENMAX 16) |  | For Information Only
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2020-09-28 09:00 | 2020-10-08 18:00 | N | Y | components and structure replacement's on 207L. Str's Range 1-23. | Line | 207L (111s Coalbanks - 370s North Lethbridge) |  | Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition
ATCO | 9L20 (755s Cordel - 766s Nevis), 766s 901 (766s Nevis) | 2020-09-28 09:00 | 2020-10-01 16:00 | N | Y | 901 breaker maintenance@ 766S Nevis | Line, Circuit Breaker | 9L20 (755s Cordel - 766s Nevis), 766s 901 (766s Nevis) | 901 Breaker maintenance@ 766S Nevis - 9L20 Open ended | 240 kV, Contingency Requires Mitigation, Overload, Affects Cranking Path
ALTALINK | 223L (150s Clyde - 159s Colinton), 723L (150s Clyde - 438s Westlock), 792L (150s Clyde - 191s N.W. Cardiff), 150S Clyde | 2020-09-28 09:30 | 2020-09-28 14:30 | N | N | station outage to install 138kV & 25kV cables to 472s mobile | Line, Station | 723L (150s Clyde - 438s Westlock), 792L (150s Clyde - 191s N.W. Cardiff) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 6L02 (765s Mannix Mine - 873s Marion Lake) | 2020-09-28 10:00 | 2020-10-01 15:00 | N | N | 6L02 crossarm replacement and Inter phase spacers | Line |  | 6L02 Crossarm replacement and Inter phase spacers | Creates Radial Feeds, Pre-Condition
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2020-09-28 10:00 | 2020-10-05 15:00 | N | Y | replacement of under rated and rotten crossarms | Line | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | Replacement of under rated and rotten crossarms | Creates Radial Feeds, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 86s 1752 (86s Bigstone), 914L (86s Bigstone - 87s Gaetz) | 2020-09-28 10:30 | 2020-10-08 18:00 | N | Y | breaker replacement and CT replacement. 87s1252 will be de-energized to energize the new breaker. | Circuit Breaker, Line | 914L (86s Bigstone - 87s Gaetz), 86s 1752 (86s Bigstone) |  | 240 kV, For Information Only, Affects Cranking Path
ATCO | 813s SVC (813s Little Smoky) | 2020-09-28 11:00 | 2020-09-30 17:00 | N | Y | 813S SVC adjust glycol percentage | Shunts | 813s SVC (813s Little Smoky) | 813S SVC Adjust Glycol Percentage Adjust Glycol percentage by draining and adding 100% glycol | Over/Under Voltage, Pre-Condition
ALTALINK | 344S Warner | 2020-09-28 11:15 | 2020-10-02 17:45 | N | N | fix leaks, doble, SFRA T2 | Station |  |  | For Information Only
ENMAX, ALTALINK | 7.84L (ENMAX 7 - ENMAX 36), 36.81L (44s Bearspaw - ENMAX 36), 36.1TR (ENMAX 36), 36.3TR (ENMAX 36) | 2020-09-28 13:00 | 2020-09-28 18:00 | N | Y | fall substation washing, check reversing switch | Line, Transformer | 7.84L (ENMAX 7 - ENMAX 36), 36.81L (44s Bearspaw - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 723L (150s Clyde - 438s Westlock), 792L (150s Clyde - 191s N.W. Cardiff), 150S Clyde | 2020-09-28 16:00 | 2020-10-20 16:00 | N | N | 138kV bus rebuild & protections upgrade, transformer maintenance on T1, and installation of 25kV bird cover-up | Line, Station | 723L (150s Clyde - 438s Westlock), 792L (150s Clyde - 191s N.W. Cardiff) | Full Station Outage to complete 138kV Bus Rebuild, & Protections Upgrade. Transformer maintenance on T1, and installation of 25kV Bird Cover-up. T1 138kV and 25kV LA replacements. Also Cut over station controls to new building (already built) | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 36.1TR (ENMAX 36) | 2020-09-29 08:00 | 2020-09-30 18:30 | N | N | plastibeton tray replacement | Transformer | 36.1TR (ENMAX 36) | plastibeton tray replacement at 36 Sub | For Information Only
ENMAX | 38.83L (ENMAX 38 - ENMAX 39), 39.82L (ENMAX 162 Beddington - ENMAX 39), 39.1TR (ENMAX 39), 39.3TR (ENMAX 39) | 2020-09-29 08:00 | 2020-09-29 13:00 | N | N | Fall Substation Washing | Line, Transformer | 38.83L (ENMAX 38 - ENMAX 39), 39.82L (ENMAX 162 Beddington - ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 39.82L (ENMAX 162 Beddington - ENMAX 39), 39.2TR (ENMAX 39), 39.4TR (ENMAX 39) | 2020-09-29 13:00 | 2020-09-29 18:00 | N | N | Fall Substation Washing. | Line, Transformer | 39.82L (ENMAX 162 Beddington - ENMAX 39), 22.81L (ENMAX 22 - ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 669L (163s Amoco Empress - 562s Cypress), 760L (163s Amoco Empress - 394s Empress), 871L (163s Amoco Empress - 341s Sand Hills), 163s C1 (163s Amoco Empress) | 2020-09-30 06:00 | 2020-10-01 20:00 | N | Y | urgent install new switch and protection, replace insulator and maintenance | Line, Shunts |  | Install new switch before circuit switcher to allow replacement of circuit switcher with breaker (ref 271522). Replace insulators on 138kV lines, 871L, 669L, 760L. Install new "A" line protection for 871L. 138kV switch maintenance, 163s55, 163s56, 163s57, 163s59, 163s60, 163s61. | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 37s 747W (37s North Calder), 747L (37s North Calder - 711L) | 2020-09-30 06:30 | 2020-10-02 17:00 | N | N | 747L line reclose control and status addition | Circuit Breaker, Line | 37s 747W (37s North Calder), 747L (37s North Calder - 711L) | 747L line reclose control and status addition | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 2029s ACF22 (2029s Heathfield) | 2020-09-30 07:00 | 2020-10-02 17:00 | N | Y | upgrades on ACF22 CA-300 CT | Shunts | 2029s ACF22 (2029s Heathfield) | ACF22 CA-300 CT Upgrades,Filter will be unavailable for duration of work, reduced redundancy | 500 kV, Pre-Condition
ALTALINK | 876L (179s Gleichen - 253s Blackie) | 2020-09-30 07:15 | 2020-09-30 17:45 | N | N | emergency repair; structures 104, 155 | Line | 876L (179s Gleichen - 253s Blackie) | Emergency Repair; Structures 104, 155 | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2020-09-30 08:00 | 2020-09-30 16:00 | N | N | fall substation washing | Line |  |  | For Information Only
ALTALINK | 275S Jenner | 2020-09-30 08:00 | 2020-09-30 12:30 | N | N | relay settings changes on: 167L 51/79/96/L8 SR760V4 | Station | 275s167W GOI | Techs to perform Fortis Requested settings changes on: 167L 51/79/96/L8 SR760V4 | For Information Only
EPCOR | RR729 (Rossdale) | 2020-10-01 | 2020-10-01 04:00 | N | N | return breaker to service | Circuit Breaker | RR729 (Rossdale) |  | For Information Only
SUNCOR | 29EDD-56 | 2020-10-01 08:00 | 2020-10-08 16:20 | N | N | PL6-23 outage to replace jumpers that have indicated PD | Station |  |  | For Information Only
NPC | NPC1 Denis St. Pierre | 2020-10-01 09:00 | 2020-10-01 12:00 | N | N | ATCO's work at 731s | Unit
ALTALINK | 184s T2 (184s Petro-Canada Edmonton) | 2020-10-01 09:00 | 2020-10-01 11:00 | N | N | advice to switch in Suncor station service | Transformer | 184s T2 (184s Petro-Canada Edmonton) |  | For Information Only
ALTALINK | 5s 852 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-10-01 11:00 | 2020-10-21 16:00 | N | N | forced outage | Circuit Breaker, Shunts |  |  | For Information Only
ALTALINK | 184s T1 (184s Petro-Canada Edmonton) | 2020-10-01 11:00 | 2020-10-01 13:00 | N | N | advice to switch in Suncor station service | Transformer | 184s T1 (184s Petro-Canada Edmonton) |  | For Information Only
ALTALINK | 163s 66 (163s Amoco Empress), 163s C1 (163s Amoco Empress) | 2020-10-01 17:30 | 2020-10-23 10:30 | N | N | replace C/S with new breaker and switch | Switch, Shunts | 163s C1 (163s Amoco Empress) |  | For Information Only, Pre-Condition
Syncrude | D05 517 (D05 Syncrude), D05 519 (D05 Syncrude), Aurora 211 (Aurora), Aurora 213 (Aurora), AL-1 (Aurora - D05 Syncrude) | 2020-10-02 07:00 | 2020-10-05 20:00 | N | Y | tie-ins for various infrastructure system | Circuit Breaker, Line | AL-1 (Aurora - D05 Syncrude) | Tie-Ins for various infrastructure system. Following Circuit Breakers will be operated: 517, 519 (D05 Sub.) 211, 213 (G01 Sub.) Following MOD's will be operated: 517A, 519B, 520 (D05 Sub.) 212B, 213A, 215 (G01 Sub.) | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 13.60L (ENMAX 13 - ENMAX 27), 27.2TR (ENMAX 27) | 2020-10-02 08:00 | 2020-10-02 13:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2020-10-02 09:15 | 2020-10-09 17:45 | N | Y | completion of 90 maintenance tasks between str 12 and 218. | Line | 951L (132s Ware Junction - 275s Jenner) | -For completion of 90 maintenance tasks on 944L between Str 12 and 218. | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27), 27.1TR (ENMAX 27) | 2020-10-02 13:00 | 2020-10-02 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, PANC | 428s 23 (428s Namaka), PCES01L (428s Namaka - PCES01S Cavalier) | 2020-10-03 06:00 | 2020-10-09 19:00 | N | Y | protection upgrades, breaker maintenance | Circuit Breaker, Line |  |  | Restricts Generation
ENMAX | 11.82L (ENMAX 11 - ENMAX 14), 11.83L (162s Beddington - ENMAX 11), 11.2TR (ENMAX 11), 11.3TR (ENMAX 11) | 2020-10-03 08:00 | 2020-10-03 12:00 | N | N | fall substation washing | Line, Transformer | 11.82L (ENMAX 11 - ENMAX 14), 11.83L (162s Beddington - ENMAX 11), 11.2TR (ENMAX 11), 11.3TR (ENMAX 11) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 744L (207s Pinedale - 228s T.M.P.L.Niton) | 2020-10-03 09:00 | 2020-10-03 18:00 | N | N | replace cross arms on 744L346 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.81L (ENMAX 11 - ENMAX 13), 11.1TR (ENMAX 11), 11.4TR (ENMAX 11) | 2020-10-03 12:00 | 2020-10-03 18:00 | N | N | fall substation washing | Line, Transformer | 11.81L (ENMAX 11 - ENMAX 13), 11.1TR (ENMAX 11), 11.4TR (ENMAX 11) |  | For Information Only, Pre-Condition
ALTALINK | 370s T4 (370s North Lethbridge), 370s 2552 (370s North Lethbridge) | 2020-10-04 07:15 | 2020-10-04 16:45 | N | N | trip test 370s2552 (breaker 2552) breaker fail testing | Transformer, Circuit Breaker | 370s T4 (370s North Lethbridge), 370s 2552 (370s North Lethbridge) |  | For Information Only, Pre-Condition
ENMAX | 24.81L (ENMAX 24 - ENMAX 31), 31.84L (ENMAX 31 - ENMAX 32), 31.2TR (ENMAX 31), 31.3TR (ENMAX 31) | 2020-10-04 08:00 | 2020-10-04 13:00 | N | N | fall substation washing | Line, Transformer | 24.81L (ENMAX 24 - ENMAX 31), 31.84L (ENMAX 31 - ENMAX 32) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 15.62L (ENMAX 15 - ENMAX 16) | 2020-10-04 08:00 | 2020-10-04 10:00 | N | N | fall transmission line washing | Line | 15.62L (ENMAX 15 - ENMAX 16) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.61L (ENMAX 16 - ENMAX 27) | 2020-10-04 10:00 | 2020-10-04 12:00 | N | N | fall transmission line washing | Line | 16.61L (ENMAX 16 - ENMAX 27) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2020-10-04 12:00 | 2020-10-04 16:00 | N | N | fall transmission line washing: shared structure with 15.62L | Line | 16.60L (ENMAX 16 - ENMAX 34) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 9.80L (ENMAX 9 - ENMAX 31), 31.1C (ENMAX 31), 31.1TR (ENMAX 31), 31.2TR (ENMAX 31) | 2020-10-04 13:00 | 2020-10-04 18:00 | N | N | fall substation washing | Line, Shunts, Transformer | 9.80L (ENMAX 9 - ENMAX 31), 31.1C (ENMAX 31) |  | For Information Only, Pre-Condition
ALTALINK | 62s 12 (62s Brazeau) | 2020-10-05 00:01 | 2020-11-22 22:00 | N | Y | turnaround | Switch | 62s 12 (62s Brazeau) |  | 240 kV, Restricts Generation
EPCOR | 72JM18 (805s Jasper - Meadowlark) | 2020-10-05 07:00 | 2020-11-04 17:00 | N | N | replace the termination at Meadowlark | Line | 72JM18 (805s Jasper - Meadowlark) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72NK23 (Kennedale - Namao) | 2020-10-05 07:00 | 2020-10-05 17:00 | N | N | doble CVTs | Line | 72NK23 (Kennedale - Namao) |  | For Information Only
ATCO | 2029s ACF23 (2029s Heathfield) | 2020-10-05 07:00 | 2020-10-05 17:00 | N | Y | upgrade ACF23 CA-300 CT | Shunts | 2029s ACF23 (2029s Heathfield) | ACF23 CA-300 CT Upgrades, Filter will be unavailable for duration of work, reduced redundancy | 500 kV, Pre-Condition
EPCOR | T2 (Rossdale) | 2020-10-05 07:00 | 2020-10-09 17:00 | N | N | duct bank work | Transformer | T2 (Rossdale) |  | For Information Only
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2020-10-05 07:00 | 2020-10-05 09:00 | N | N | pothead washing | Line | 1.80L (ENMAX 1 - ENMAX 28) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | H723 (Hardisty Epcor) | 2020-10-05 07:00 | 2020-10-05 17:00 | N | N | doble | Circuit Breaker | H723 (Hardisty Epcor) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 526L (268s Whitecourt - 526DL185), 503L (268s Whitecourt - 323s Whitecourt Power) | 2020-10-05 07:00 | 2020-10-05 20:00 | N | Y | replacing 268s PT3 | Line | 503L (268s Whitecourt - 323s Whitecourt Power), 526L (268s Whitecourt - 526DL185) |  | Pre-Condition, Restricts Generation
ALTALINK | 87s T2 (87s Gaetz) | 2020-10-05 07:30 | 2020-10-08 17:30 | N | Y | upgrade SCADA | Transformer | 87s T2 (87s Gaetz) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 993s T1 (993s Abee) | 2020-10-05 07:30 | 2020-10-05 17:30 | N | N | customer maintenance | Transformer | 993s T1 (993s Abee) | Enbridge is closing up an open point on their tie bus downstream and require us to ground inside 993s | For Information Only
ENMAX | 36.2TR (ENMAX 36) | 2020-10-05 08:00 | 2020-10-07 18:30 | N | N | plastibeton tray replacement | Transformer | 36.2TR (ENMAX 36) |  | For Information Only
USPCE | 841s Long Lake RTU/SCADA | 2020-10-05 08:00 | 2020-10-09 17:00 | N | N | install newer version of RTU | Terminal Equipment |  |  | Affects Visibility
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) | 2020-10-05 08:00 | 2020-10-05 16:00 | N | N | fall substation washing | Line, Transformer | 22.81L (ENMAX 22 - ENMAX 39), 22.2TR (ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 65B240-D133 (ENMAX 65) | 2020-10-05 08:00 | 2020-10-05 12:00 | N | Y | remove birds nest and SF6 sample | Circuit Breaker | 65B240-D133 (ENMAX 65) | SF6 sample. 65B240-D133 Remove birds nest and add deterant | 240 kV, Contingency Requires Mitigation
ENMAX | 16.1TR (ENMAX 16) | 2020-10-05 08:00 | 2020-10-07 16:00 | N | N | NGR Installation | Transformer |  |  | For Information Only
ENMAX | 1.81L (ENMAX 1 - ENMAX 20) | 2020-10-05 09:00 | 2020-10-05 11:00 | N | N | pothead washing | Line | 1.81L (ENMAX 1 - ENMAX 20) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L02 (769s Stettler - 873s Marion Lake) | 2020-10-05 10:00 | 2020-10-08 15:00 | N | N | cross arm replacement and inter-phase spacers | Line |  | 6L02 Crossarm replacement and Inter phase spacers | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 13s 1552 (13s Deerland), 13s 1652 (13s Deerland), 1054L (12s Heartland - 13s Deerland) | 2020-10-05 10:00 | 2020-10-08 18:00 | N | Y | replacing CT | Circuit Breaker, Line | 1054L (12s Heartland - 13s Deerland), 13s 1652 (13s Deerland), 13s 1552 (13s Deerland) | Replacing CT on 13s1552 | 240 kV, Contingency Requires Mitigation
ALTALINK | 266s 1037L FSC (266s SC1) | 2020-10-05 10:45 | 2020-10-08 17:45 | N | Y | yearly maintenance FAC501 | Shunts | 266s 1037L FSC (266s SC1) |  | 240 kV, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43) | 2020-10-05 11:00 | 2020-10-05 13:00 | N | N | pothead washing | Line | 9.83L (ENMAX 9 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 65B240-D130 (ENMAX 65) | 2020-10-05 12:00 | 2020-10-05 16:00 | N | Y | remove birds nest and SF6 sample | Circuit Breaker | 65B240-D130 (ENMAX 65) | SF6 Sample. 65B240-D130 Remove birds nest and add deterant | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2020-10-05 13:00 | 2020-10-05 15:00 | N | N | pothead washing. | Line | 33.84L (ENMAX 33 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 370s T1 (370s North Lethbridge) | 2020-10-05 16:30 | 2020-11-03 14:00 | N | N | install new T1 protections in control building 3 | Transformer | 370s T1 (370s North Lethbridge) |  | For Information Only
ALTALINK | 503L (268s Whitecourt - 323s Whitecourt Power) | 2020-10-05 20:00 | 2020-10-06 17:00 | N | Y | customer maintenance | Line | 503L (268s Whitecourt - 323s Whitecourt Power) | EA Nunn will be installing grounds for Whitecourt Power on 503L so that they can perform maintenance on 323-S1 and their metering tank | Restricts Generation
ALTALINK | 89s T1 (89s Ellerslie) | 2020-10-06 07:00 | 2020-10-07 18:00 | N | Y | urgent work to check core grounds | Transformer | 89s T1 (89s Ellerslie) | Urgent outage to check core grounds on all three | 500 kV, Overload, Pre-Condition
ALTALINK | 774L (276s Prentiss - 332s Ellis), 276s C1 (276s Prentiss), 276s T2 (276s Union Carbide Prentiss), 276s Union Carbide Prentiss 138 kV North Bus | 2020-10-06 07:00 | 2020-10-13 18:00 | N | N | install high side CT's, upgrade SCADA & P&C | Line, Shunts, Transformer, Bus | 276s T2 (276s Union Carbide Prentiss), 276s C1 (276s Prentiss), 774L (276s Prentiss - 332s Ellis), 276s 16 (276s Un Carb Prentiss), 276s 774N (276s Un Carb Prentiss) | Install high side CT's, upgrade SCADA & P&C | For Information Only, Pre-Condition
EPCOR | S722 (Strathcona) | 2020-10-06 07:00 | 2020-10-06 17:00 | N | N | maintenance / doble | Circuit Breaker | S722 (Strathcona) |  | For Information Only
ALTALINK | 5s T2 (5s East Calgary) | 2020-10-06 07:45 | 2020-10-08 17:45 | N | Y | doble, maintenance | Transformer | 5s T2 (5s East Calgary) |  | 240 kV, Pre-Condition
ENMAX | 1.82L (ENMAX 1 - ENMAX 5), ENMAX 5 B138-5BT7 ( ENMAX 5), 5.1TR (ENMAX 5), 5.6TR (ENMAX 5), 5.8TR (ENMAX 5), 5B138-5BT12 (ENMAX 5) | 2020-10-06 08:00 | 2020-10-06 16:00 | N | N | fall substation washing. oil sampling 5.8TC | Line, Circuit Breaker, Transformer | 1.82L (ENMAX 1 - ENMAX 5), 5.1TR (ENMAX 5), 5.6TR (ENMAX 5), 5.8TR (ENMAX 5) |  | For Information Only, Pre-Condition
ENMAX | 162s 240-RB135 (162s Beddington) | 2020-10-06 08:00 | 2020-10-06 12:00 | N | Y | SF6 gas resample | Circuit Breaker | 162s 240-RB135 (162s Beddington) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2020-10-06 08:00 | 2020-10-06 11:00 | N | N | upgrade RTU, commission CA/OAC controls | Line | 9.80L (ENMAX 9 - ENMAX 31) |  | For Information Only
ALTALINK | 310p Sundance 240kV Bus C, 310P Sundance 138kV Bus, 310p 767X (310p Sundance), 767L (310p Sundance - 767AL), 310p T36 (310p Sundance), 310p T30 (310p Sundance) | 2020-10-06 08:00 | 2020-10-16 14:30 | N | Y | T30 A & B protection upgrade | Bus, Circuit Breaker, Line, Transformer | 310p Sundance 240kV Bus C, 310p 2852 (310p Sundance), 310p 767X (310p Sundance), 767L (310p Sundance - 767AL), 310p 310p T36 (310p Sundance), T30 (310p Sundance) , ????? |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
SUNCOR | SCR5 Poplar Creek | 2020-10-06 08:00 | 2020-10-20 16:00 | N | N | STG4 modification. ISD Oct 13, 2020. P2327 | Unit
ALTALINK | 185AL (415s Drywood - 995s Yarrow) | 2020-10-06 08:15 | 2020-10-16 14:45 | N | N | 995s station upgrade | Line | 185AL (415s Drywood - 995s Yarrow) | replace 69kV strain insulators, 69kV switch (995s185AN), 4.16kV insulators, install of new PT/CT and revenue meter | Firm Load Loss, For Information Only
ALTALINK | 37s 82 (37s North Calder) | 2020-10-06 08:30 | 2020-10-06 17:30 | N | Y | urgent advice to investigate sync check issue | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ENMAX | 2.81L (ENMAX 2 - ENMAX 9) | 2020-10-06 11:00 | 2020-10-06 14:00 | N | N | upgrade RTU, commission CA/OAC controls | Line | 2.81L (ENMAX 2 - ENMAX 9) |  | For Information Only, Pre-Condition
ENMAX | 162s 138-RB92 (162s Beddington) | 2020-10-06 12:00 | 2020-10-06 16:00 | N | N | SF6 sample 162B138-RB92 retest | Circuit Breaker | 162s 138-RB92 (162s Beddington) |  | Contingency Requires Mitigation, Firm Load Loss, For Information Only, Pre-Condition
ENMAX | 9.83L (ENMAX 9 - ENMAX 43), 9B138-9.83 (ENMAX 9) | 2020-10-06 14:00 | 2020-10-06 17:00 | N | N | upgrade RTU, commission CA/OAC controls | Line, Circuit Breaker | 9.83L (ENMAX 9 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Strathcona), 72LS24 (803s Lambton - Strathcona), S723 (Strathcona), S724 (Strathcona) | 2020-10-07 07:00 | 2020-10-21 17:00 | N | N | commissioning of TX3 new transformer | Transformer, Line, Circuit Breaker | T3 (Strathcona), S723 (Strathcona), S724 (Strathcona),72LS24 (803s Lambton - Strathcona) |  | Pre-Condition
EPCOR | T3 (Poundmaker) | 2020-10-07 07:00 | 2020-10-08 17:00 | N | Y | conservator bladder replacement | Transformer | T3 (Poundmaker) |  | 240 kV, For Information Only, Pre-Condition
EPCOR | 72LH8 (803s Lambton - Hardisty), 72LS24 (803s Lambton - Strathcona) | 2020-10-07 07:00 | 2020-10-09 17:00 | N | N | outages required to provide clearances for primary impedance testing | Line |  |  | For Information Only, Pre-Condition
ENMAX | 22.3TR (ENMAX 22) | 2020-10-07 08:00 | 2020-10-07 12:00 | N | N | 22.3TR slip over CT ground shield ground wire corrective | Transformer | 22.3TR (ENMAX 22) |  | For Information Only
ENMAX | 11B138-BT5 (ENMAX 11) | 2020-10-07 08:00 | 2020-10-07 16:00 | N | N | HV breaker maintenance | Circuit Breaker | 11B138-BT5 (ENMAX 11) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 33.84L (ENMAX 33 - ENMAX 43) | 2020-10-07 08:00 | 2020-10-08 16:00 | N | N | DGA & sheath testing | Line | 33.84L (ENMAX 33 - ENMAX 43) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.82L (ENMAX 2 - ENMAX 5), 1.84L (ENMAX 1 - ENMAX 5), 5.7TR (ENMAX 5), 5.5TR (ENMAX 5) | 2020-10-07 08:00 | 2020-10-08 16:00 | N | N | fall substation washing and check reversing switch | Line, Transformer | 1.84L (ENMAX 1 - ENMAX 5), 2.82L (ENMAX 2 - ENMAX 5), 5.5TR (ENMAX 5), 5.7TR (ENMAX 5) | Fall Substation Washing. Check reversing Switch. 5.7TR, 5.5TR. Oil sampling 5.7TC. HV SW maint. MD-5.5TR, MD-5.7TR | For Information Only, Pre-Condition
ALTALINK | 37s 88 (37s North Calder) | 2020-10-07 08:30 | 2020-10-07 17:30 | N | N | urgent advice to investigate sync check issue. | Circuit Breaker |  |  | Contingency Requires Mitigation
ENMAX | 9.2TR (ENMAX 9) | 2020-10-07 10:00 | 2020-10-07 12:00 | N | N | upgrade RTU, commission CA/OAC controls | Transformer | 9.2TR (ENMAX 9) |  | For Information Only, Pre-Condition
ENMAX | 22.2TR (ENMAX 22) | 2020-10-07 12:00 | 2020-10-07 16:00 | N | N | 22.2TR slip over CT ground shield ground wire corrective. 22BA8-22.2TR Replace Counter | Transformer | 22.2TR (ENMAX 22) |  | For Information Only, Pre-Condition
ALTALINK | 268s T1 (268s Whitecourt), 199L (268s Whitecourt - 199AL) | 2020-10-07 17:00 | 2020-10-07 18:30 | N | N | abnormal system condition during restoration and return to service switching | Transformer, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2020-10-07 23:00 | 2020-10-08 03:00 | N | Y | maintenance | Switch | 62s 11 (62s Brazeau) | Brushgear | 240 kV, Restricts Generation
ALTALINK | 754L (245s Seebe - 742L tap) | 2020-10-08 06:30 | 2020-10-11 12:00 | N | N | replacing structure 56 and maintenance1 | Line | 754L (245s Seebe - 742L tap) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 162s 2-EHA-DS-0002 (162s Beddington), 162s 2GSU-XF-0002 (162s Beddington) | 2020-10-08 07:00 | 2020-10-08 18:00 | N | Y | transformer and switch maintenance | Switch, Transformer |  |  | 240 kV, Restricts Generation
ENMAX | 16.2TR (ENMAX 16) | 2020-10-08 08:00 | 2020-10-13 16:00 | N | N | NGR Installation | Transformer |  |  | For Information Only
ENMAX | 41B138-41BT3 (ENMAX 41) | 2020-10-08 08:00 | 2020-10-08 16:00 | N | N | SF6 gas sample 41B138-BT3 | Circuit Breaker | 41B138-41BT3 (ENMAX 41) | SF6 Gas Sample 41B138-BT3 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | K722 (Kennedale) | 2020-10-08 08:30 | 2020-10-08 16:00 | N | N | substation switching school isolation of K722 at Kennedale | Circuit Breaker | K722 (Kennedale) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 197s 174E (197s Bardo), 174L (197s Bardo - 395s North Holden) | 2020-10-08 08:30 | 2020-10-08 11:00 | N | N | minor wiring deficiency fix on breaker 197s174E control | Circuit Breaker, Line | 197s 174E (197s Bardo), 174L (197s Bardo - 395s North Holden) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 860s 701T (860s Crow) | 2020-10-08 10:00 | 2020-10-08 16:00 | N | N | CT settings change affecting 3L214 | Transformer |  | Perform CT settings change affecting 3L214 | For Information Only
ALTALINK | 901L (63s Red Deer - 74s Janet) | 2020-10-09 07:00 | 2020-10-12 18:00 | N | Y | replacing structure 210 & urgent work due to farm equipment hitting tower | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 235s T4 (235s Entwistle), 156L (235s Entwistle - 156BL), 672L (131s Moon Lake - 235s Entwistle), 744L (235s Entwistle - 744AL), 799L (235s Entwistle - 443s South Mayerthorpe), 235s Entwistle 138 kV bus | 2020-10-09 07:00 | 2020-10-09 16:00 | N | N | replacing strain insulators on the 138kV Bus | Transformer, Line, Bus | 156L (235s Entwistle - 156BL), 672L (131s Moon Lake - 235s Entwistle), 744L (235s Entwistle - 744AL), 799L (235s Entwistle - 443s South Mayerthorpe), 235s 156E (235s Entwistle), 235s 672 (235s Entwistle),235s 744W (235s Entwistle), 235s 799N (235s Entwistle), 235s T4 (235s Entwistle) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 744L (235s Entwistle - 744AL) | 2020-10-09 07:00 | 2020-10-22 17:00 | N | N | replace 744L Str 7A, 8A, 9A & 10A for urgent line clearance mitigation | Line | 744L (235s Entwistle - 744AL) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 162s 1GSU-XF-0001 (162s Beddington), 162s 1-EHA-DS-0001 (162s Beddington) | 2020-10-09 08:00 | 2020-10-12 16:00 | N | Y | replace 87-XF1 B differential protection & commission checks and trip testing. HV SW maint SW133, SW132 & replace switch mech. SW132, SW133 | Transformer, Switch | 162s 1GSU-XF-0001 (162s Beddington) |  | 240 kV, Restricts Generation
ALTALINK | 310p 24B (310p Sundance) | 2020-10-09 08:00 | 2020-10-15 16:00 | N | Y | replace seized switch like for like | Switch |  |  | 240 kV, For Information Only
SUNCOR | 635EDD-1000 635-752-133 (635EDD-1000), 635PT-1002 (635EDD-1000), 635EDD-1000 635-752-132 (635EDD-1000) | 2020-10-09 08:00 | 2020-10-15 08:00 | N | N | maintenance of 635PT-1002 transformer protection | Circuit Breaker, Transformer |  |  | For Information Only
GENL | WCD1 West Cadotte | 2020-10-09 09:00 | 2020-10-09 10:00 | N | N | Simon Lake_T-Telecom work affecting DTT | Unit
SUNCOR | 29EDD-2 Tar Island, 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island), 29EDD-1 Millennium | 2020-10-10 08:00 | 2020-10-21 18:00 | N | N | 5 year system pm | Station, Line | 29PL6-22 (29EDD-1 Millennium - 29EDD-2 Tar Island) | PL6-22 OUTAGE 5YR SYSTEM PM, 29PT-3 AND BREAKER 29EDD1S1452: 29EDD-1;29EDD1S1452 MAINT&TEST;PM 10y, 29EDD-2;29PT-3 SYSTEM;PM 5y,10y | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 6.80L (ENMAX 6 - ENMAX 35) | 2020-10-10 08:00 | 2020-10-23 16:00 | N | N | Hitachi HV breaker overhaul 6B138-6.80 | Line | 6.80L (ENMAX 6 - ENMAX 35) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 11.81L (ENMAX 11 - ENMAX 13), 13.82L (ENMAX 13 - ENMAX 22), 13.60L (ENMAX 13 - ENMAX 27), 13.4TR (ENMAX 13), 13.2TR (ENMAX 13) | 2020-10-10 08:00 | 2020-10-12 16:00 | N | N | install lightning arrestors on 11.81L | Line, Transformer | 11.81L (ENMAX 11 - ENMAX 13), 13.82L (ENMAX 13 - ENMAX 22), 13.60L (ENMAX 13 - ENMAX 27) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
SUNCOR | 29EDD-56 | 2020-10-11 08:00 | 2020-10-20 18:00 | N | N | maintenance | Station |  | PL6-29 OUTAGE 5YR SYSTEM PM, BUSS 29PP-41E BREAKERS 652-4140: 29EDD-56;29PP-41D & 41E SYSTEM;PM 5y, 29EDD-56;652-4140 MAINT & TEST;PM 10y | For Information Only
ALTALINK | 87s 2352 (87s Gaetz) | 2020-10-12 07:30 | 2020-10-15 17:30 | N | Y | SCADA upgrade | Circuit Breaker | 87s 2352 (87s Gaetz) |  | 240 kV, For Information Only
CMH | MH69s1 MH69-24 (MH69s1 Power P Switchyard), MH69s1 MH69-T3A (MH69s1 Power P Switchyard), MH69s1 MH69-28 (MH69s1 Power P Switchyard) | 2020-10-12 08:00 | 2020-10-21 13:00 | N | N | upgrades | Circuit Breaker, Transformer | MH69s1 MH69-24 (MH69s1 Power P Switchyard), MH69s1 MH69-T3A (MH69s1 Power P Switchyard), MH69s1 MH69-28 (MH69s1 Power P Switchyard) |  | Creates Radial Feeds, Firm Load Loss, For Information Only
ALTALINK | 392s T3 (392s Black Diamond) | 2020-10-12 09:15 | 2020-10-15 17:15 | N | N | replace B phase PT1, and demolish 25kV L/As, complete bird cover installation and structure modifications | Transformer | 392s T3 (392s Black Diamond) | Replace B Phase PT1, and demolish 25kV L/As. Complete Bird cover installation and structure modifications. | For Information Only
ALTALINK | 715L (545s Provost - 650s Hansman Lake), 545S Provost | 2020-10-13 07:00 | 2020-10-16 10:00 | N | N | installing 475s mobile substation | Line, Station |  |  | For Information Only, Pre-Condition
EPCOR | 987s C2404 (987s Clover Bar) | 2020-10-13 07:00 | 2020-10-14 17:00 | N | Y | doble | Circuit Breaker | 987s C2404 (987s Clover Bar) |  | 240 kV, Contingency Requires Mitigation
EPCOR | 816s T1 (816s Petrolia) | 2020-10-13 07:00 | 2020-10-23 17:00 | N | Y | DGA install | Transformer | 816s T1 (816s Petrolia) |  | 240 kV, Pre-Condition
ALTALINK | 71s T1 (71s Lamoureux) | 2020-10-13 07:30 | 2020-10-23 18:00 | N | Y | replacing HV & LV bushings, maintenance and doble | Transformer | 71s T1 (71s Lamoureux) | crews will be replacing the HV & LV bushings; some minor maintenance work & doble will also be completed if time exists | 240 kV, Contingency Requires Mitigation
Syncrude | Mildred T15 (Syncrude Mildred Lake) | 2020-10-13 08:00 | 2020-10-19 20:00 | N | N | breaker and switch maintenance | Transformer |  | T15 Transformer 72/13.8KV - Plant 31 Powerhouse Following Circuit Breaker will be operated: Breaker 1535 (Plant 31 Powerhouse) Following switch will be operated: 1534 (Plant 31 Powerhouse) | For Information Only
MONTANA | MATL (120s Picture Butte - Montana) | 2020-10-13 08:00 | 2020-10-29 17:00 | N | Y | maintenance | Line | MATL (120s Picture Butte - Montana) |  | 240 kV, Pre-Condition, Limits ATC
ALTALINK | 1201L (520s Bennett - BCH Cranbrook) | 2020-10-13 08:00 | 2020-10-25 17:00 | Y | Y | replace the damaged sub-conductor and damaged spacers between str 186 and 204 | Line | 1201L (520s Bennett - BCH Cranbrook) | -There is a broken steel core on the right phase, sub- conductor as the spacers are all pulled from tower 187-203.Crews will identify the sub-conductor that has the broken steel core, remove all spacers, replacing the damaged sub-conductor between Str 186 and 204, re-install spacers and replace any damaged spacers. | 500 kV, Limits ATC, Pre-Condition, Affects Cranking Path
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2020-10-13 08:00 | 2020-11-06 16:00 | N | N | line protection upgrade | Line | 2.83L (ENMAX 13 - 2.83L tap), 2.83L (ENMAX 2 - 2.83L tap), 2.83L (ENMAX 5 - 2.83L tap) | Line Protection Upgrade. Control cable swap out. Arc Flash Mitigation Project. Cable sheath test Expand GOI Oct 29th for 2sub GIS Maint. | Pre-Condition
ALTALINK | Path 1 (AIES Islanding) | 2020-10-13 08:00 | 2020-10-23 17:45 | Y | Y | 1201L & 777L both OOS | Line | Path 1 (AIES Islanding) |  | Pre-Condition
ENMAX, ALTALINK | 23.80L (74s Janet - ENMAX 23) | 2020-10-13 09:00 | 2020-10-14 17:30 | N | Y | 138 kV breaker maintenance | Line | 74s 23.80W (74s Janet), 23.80L (74s Janet - ENMAX 23) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2020-10-13 09:00 | 2020-10-15 17:00 | N | Y | components and structure replacements structure range 1-23 | Line | 207L (111s Coalbanks - 370s North Lethbridge) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2020-10-13 10:00 | 2020-10-19 15:00 | N | Y | replacement of under rated and rotten crossarms | Line | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | Replacement of under rated and rotten crossarms | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 102s 7452 (102s Langdon), 102s 7552 (102s Langdon), 1114L (102s Langdon - 520s Bennett), 520s T1 (520s Bennett) | 2020-10-13 10:15 | 2020-10-15 16:45 | Y | Y | fix main tank filter on T1-4 and fix leaky valve on R7 | Circuit Breaker, Line, Transformer | 1114L (102s Langdon - 520s Bennett), 1102s 7452 (102s Langdon), 102s 7552 (102s Langdon), 520s T1 (520s Bennett), 1201L (520s Bennett - BCH Cranbrook), MATL (120s Picture Butte - Montana) | fix main tank filter on T1-4 and fix leaky valve on R7 and 520s 500kV corona ring is bent and needs adjustment/replacing at 520s13 upper bus. 2nd Scope: FAC 501 switches 102s2689, 102s130, 102s132 need to be operated | 500 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 512s T1 (512s Hartell) | 2020-10-13 10:45 | 2020-10-15 17:45 | N | N | fix leak on DETC handle, install bird cover | Transformer | 512s T1 (512s Hartell) |  | For Information Only
ALTALINK | 421s 30 (421s Hays), 421s C1 (421s Hays) | 2020-10-13 12:30 | 2020-10-20 16:30 | N | N | 421s C1 protection upgrade | Circuit Breaker, Shunts | 421s 30 (421s Hays) |  | Pre-Condition
ALTALINK | 12s T1 (12s Heartland) | 2020-10-13 13:00 | 2020-10-15 17:00 | N | Y | doble and qualitrol cycling power | Transformer | 12s T1 (12s Heartland) |  | 500 kV, Pre-Condition
ENMAX | 36.5TR (ENMAX 36), 16.63L (ENMAX 16 - ENMAX 36) | 2020-10-14 08:00 | 2020-10-14 16:00 | N | N | 36.5TR, gas alarm, in and out | Transformer, Line |  |  | For Information Only, Pre-Condition
ALTALINK | 310P T33 (310P Sundance) | 2020-10-14 08:00 | 2020-10-14 17:00 | N | N | T33 meter replacement | Transformer | 310P T33 (310P Sundance) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-10-14 08:00 | 2020-10-20 18:00 | N | N | 29PP-37D | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
Saskpower | SASK POWER P2C | 2020-10-14 08:00 | 2020-10-14 18:00 | N | N | maintenance | Line |  |  | For Information Only
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2020-10-14 08:30 | 2020-10-14 15:00 | N | Y | urgent conductor repair between 951L41 and 951L42 | Line | 951L (132s Ware Junction - 275s Jenner) | repair between 951L41 and 951L42 | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 727L (65s High River - 142s Magcan - 678s Okotoks), 142s C1 (142s Magcan) | 2020-10-14 08:30 | 2020-10-15 18:00 | N | N | remove lower bus jumpers to upper bus jumpers due to clearance issues at 142s11 from structure frost heaving | Line, Shunts | 727AL (142s Magcan - 727L tap), 142s C1 (142s Magcan) |  | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK | 498s T1 (498s Tilley) | 2020-10-14 09:15 | 2020-10-14 14:45 | N | N | move the MOD control module for 498s4 down one space | Transformer | 100L (498s Tilley - 895s Suffield), 498s 100X (498s Tilley), 498s T2 (498s Tilley) | Move the MOD control module for 498s4 down one space. The existing wiring should be long enough, re-commissioning is not expected. | For Information Only
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2020-10-14 13:00 | 2020-10-14 14:00 | N | Y | open end 7L93 @ 930s for Arcenciel Telecom outage 2-53081 due to stability concerns | Line | 7L93 (828s Sulphur Point - 930s Arcenciel) | Open end 7L93 @ 930S for Arcenciel Telecom outage 2-53081 due to stability concerns | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 913L (69s North Barrhead - 338s Cherhill), 913L (69s North Barrhead - 732s Mitsue) | 2020-10-14 13:09 | 2020-10-17 18:00 | N | Y | force - structure damaged | Line |  |  | 240 kV,Affects Cranking Path
ALTALINK | 760AL (164s Empress Liquids - 760L), 760L (163s Amoco Empress - 760AL) | 2020-10-14 15:05 | 2020-10-15 18:00 | N | Y | replace PT1 and insulators at 760LN 163s | Line | 760L (163s Amoco Empress - 760AL) | Replace PT1 and insulators at 760LN 163s A-Frame structure Trip test breaker 163s760N from new 163s63 C60 Protection. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 202L (61s Lodgepole - 62s Brazeau) | 2020-10-15 07:00 | 2020-10-21 18:00 | N | Y | line clearance mitigation on structures #23, 24, 126, 151, 152, 154 | Line | 202L (61s Lodgepole - 62s Brazeau) |  | Pre-Condition, Restricts Generation, Affects Cranking Path
CNRL | 838s 75-TR-1801 (838s Horizon Mining) | 2020-10-15 07:30 | 2020-10-22 18:00 | N | Y | transformer maintenance | Transformer | 838s 75-TR-1801 (838s Horizon Mining) |  | 240 kV
SUNCOR | 635EDD-1000 635-752-131 (635EDD-1000), 635EDD-1000 635PK-1000 (635EDD-1000), 635EDD-1000 635-752-132 (635EDD-1000) | 2020-10-15 08:00 | 2020-10-21 17:00 | N | N | maintenance of cap bank | Circuit Breaker, Shunts |  |  | For Information Only, Pre-Condition
ATCO | MUL1 Mowat | 2020-10-15 13:00 | 2020-10-15 14:00 | N | N | ATCO firmware upgrade work on 754s RAS | Unit
ALTALINK | 74s 691 (74s Janet), 691L (74s Janet - 419s Chestermere) | 2020-10-16 08:00 | 2020-10-18 18:00 | N | Y | 1st trip and maintenance | Circuit Breaker, Line | 691L (74s Janet - 419s Chestermere), 74s 691 (74s Janet) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 545s Provost 138 kV Bus, 545s T1 (545s Provost) | 2020-10-16 10:00 | 2020-11-30 08:00 | N | N | re-configuring 138kV Bus and installing new equipment | Bus, Transformer | 545s Provost 138 kV bus, 545s T1 (545s Provost) |  | For Information Only, Pre-Condition
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2020-10-16 13:00 | 2020-10-16 14:00 | N | Y | open end 7L93 @ 930S for RainbowTelecom outage 2-53085 due to stability concerns | Line | 7L93 (828s Sulphur Point - 930s Arcenciel) | Open end 7L93 @ 930S for RainbowTelecom outage 2-53085 due to stability concerns | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation
ALTALINK | 38s T3 (38s East Edmonton) | 2020-10-16 14:31 | 2020-10-16 18:00 | N | N | force outage | Transformer |  |  | For Information Only
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2020-10-17 05:00 | 2020-10-19 16:00 | N | Y | forced outage | Line |  |  | Contingency Requires Mitigation, Over/Under Voltage
ALTALINK | 163s 56 (163s Amoco Empress), 163s 57 (163s Amoco Empress), 163s 669 (163s Amoco Empress), 669L (163s Amoco Empress - 562s Cypress) | 2020-10-17 07:30 | 2020-10-17 11:00 | N | N | trip testing breaker for new protection | Switch, Circuit Breaker, Line | 669L (163s Amoco Empress - 562s Cypress), 163s 669 (163s Amoco Empress) |  | Pre-Condition
ALTALINK | 163s 59 (163s Amoco Empress), 163s 60 (163s Amoco Empress), 163s 760X (163s Amoco Empress), 760L (163s Amoco Empress - 394s Empress) | 2020-10-17 11:05 | 2020-10-17 14:00 | N | N | trip testing 163s760X breaker for new protection testing | Switch, Circuit Breaker, Line | 163s 760X (163s Amoco Empress), 760L (163s Amoco Empress - 394s Empress) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 163s 68 (163s Amoco Empress), 163s 67 (163s Amoco Empress), 163s C1 (163s Amoco Empress) | 2020-10-17 14:05 | 2020-10-17 17:00 | N | N | trip testing 163s67 breaker for new protection testing | Switch, Circuit Breaker, Shunts | 163s 67 (163s Amoco Empress), 163s C1 (163s Amoco Empress) |  | Pre-Condition
ALTALINK | 163s 15A (163s Amoco Empress), 163s 15B (163s Amoco Empress), 163s 1552 (163s Amoco Empress) | 2020-10-18 07:30 | 2020-10-18 11:00 | N | Y | trip testing breaker for new protection testing | Switch, Circuit Breaker | 163s 1552 (163s Amoco Empress) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 275s 2 (275s Jenner) | 2020-10-18 08:30 | 2020-10-18 17:30 | N | Y | urgent repair, replacement of 944L prorection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss
ALTALINK | 65s T1 (65s High River), 13L/158L (65s High River - 392s Black Diamond), 392s T2 (392s Black Diamond), 65s 13N (65s High River) | 2020-10-18 09:15 | 2020-10-18 14:45 | N | N | urgent - breaker maintenance for low SF6 | Transformer, Line, Circuit Breaker | 13L (65s High River - 392s Black Diamond) 65s T1 (65s High River) 392s T2 (392s Black Diamond) | Urgent 69kV Hitachi breaker came into low gas and needs to be topped up | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 163s 12A (163s Amoco Empress), 163s 12B (163s Amoco Empress), 163s 1252 (163s Amoco Empress) | 2020-10-18 11:05 | 2020-10-18 14:00 | N | Y | trip testing breaker for new protection testing | Switch, Circuit Breaker | 163s 1252 (163s Amoco Empress) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 557s T1 (557s Castle Downs) | 2020-10-19 07:00 | 2020-10-20 17:00 | N | Y | outage required for protection upgrade project | Transformer | 557s T1 (557s Castle Downs), 557s 2401 (557s Castle Downs), 557s 2406 (557s Castle Downs) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 822L (38s East Edmonton - 133s Stelco Edmonton), 133S Stelco Edmonton | 2020-10-19 07:00 | 2020-10-25 13:00 | N | N | maintenance and repair | Line, Station | 822L (38s East Edmonton - 133s Stelco Edmonton) | 133sT2 replacement and 133s2 DS move and replacement. Replace bushing and repair oil leaks on 133sT1. | For Information Only
EPCOR | 814s T1 (814s Bellamy), 814s B2401 (814s Bellamy), 814s B2407 (814s Bellamy) | 2020-10-19 07:00 | 2020-12-11 17:00 | N | Y | regasketing work | Transformer, Circuit Breaker | 814s T1 (814s Bellamy) | Bellamy TX1 Regasketing Work and Breakers Maintenance | 240 kV
ALTALINK | 163s T1 (163s Amoco Empress) | 2020-10-19 07:15 | 2020-10-19 15:45 | N | Y | replace 13.8kV LAs | Transformer | 163s T1 (163s Amoco Empress) |  | 240 kV, For Information Only
ALTALINK | 76L (33s Spray - 115s Mt. Allan) | 2020-10-19 07:15 | 2020-10-23 17:45 | N | N | replacing structures | Line | 76L (33s Spray - 115s Mt. Allan) | replacing strs 47, 83, 87, 96, 98, 111A, 112, 113, 114. Maintenance on strs 2, 5, 7, 9, 12, 14, 15, 17, 19, 22, 50, 52, 53, 63, 69. Re-sag OHSW between strs 87, 93 | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAXGPI | CRS3 Summit- Crossfield | 2020-10-19 08:00 | 2020-11-02 16:00 | N | N | P2222 Battery Storage ISD Oct 26, 2020 | Unit
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-10-19 08:00 | 2020-10-20 18:00 | N | N | 29EDD-160, 29PT-580 inspection | Not In Model |  |  | For Information Only
ENMAX | 37.1TR (ENMAX 37) | 2020-10-19 08:00 | 2020-10-22 16:00 | N | N | leak repair | Transformer |  |  | For Information Only
ENMAX | 8.3TR (ENMAX 8) | 2020-10-19 08:00 | 2020-10-21 12:00 | N | N | T-60 upgrade phase 2 | Transformer |  |  | For Information Only
ATCO | 951s SVC (951s Thickwood) | 2020-10-19 08:00 | 2020-10-26 18:00 | N | Y | maintenance/Warranty items | Shunts | 951s SVC (951s Thickwood) | 951S Thickwood SVC maintenance/Warranty items | 240 kV, Over/Under Voltage, Pre-Condition
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2020-10-19 08:00 | 2020-10-29 18:00 | N | Y | components and structure replacements structure range 1-23 | Line | 207L (111s Coalbanks - 370s North Lethbridge) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation
ALTALINK | 275s 5 (275s Jenner) | 2020-10-19 08:30 | 2020-10-20 17:30 | N | Y | urgent repair, replacement of 944L protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ATCO | 757s 701T (757s Battle River) | 2020-10-19 08:30 | 2020-10-20 16:00 | N | N | breaker maintenance on 606 & 701, 72kV-144kV tie open | Transformer | 757s 701T (757s Battle River) | Breaker Maintenance on 606 & 701, 72Kv-144kv tie open | Pre-Condition
ALTALINK | 156L (235s Entwistle - 156BL), 235s 156E (235s Entwistle) | 2020-10-19 09:00 | 2020-10-19 17:30 | N | N | replacing strain insulators on 156L | Line, Circuit Breaker | 156L (235s Entwistle - 156BL) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 1081L (17s Benalto - 281s Johnson) | 2020-10-19 09:00 | 2020-10-29 17:00 | N | Y | replace 17s1081 underhung switch and MOD, 17s23 switch, 17s32 switch | Line | 1081L (17s Benalto - 281s Johnson) | Replace 17s1081 Underhung Switch and MOD, 17s23 switch, 17s32 switch | 240 kV, Contingency Requires Mitigation, Pre-Condition
ATCO | 801s 912 (801s Anderson) | 2020-10-19 09:00 | 2020-10-22 16:00 | N | Y | breaker maintenance | Circuit Breaker | 801s 912 (801s Anderson) | Complete Breaker Maintenance, Ring Bus 911 Breaker in service | 240 kV, Contingency Requires Mitigation
ALTALINK | 722L (107s Westfield - 368s Burdett), 107S Westfield | 2020-10-19 09:00 | 2020-10-23 17:30 | N | N | replace 107s2 25kV s/w, repair 107s3, replace conductor on 138kV high side of T1 and install equipment | Line, Station | 722L (107s Westfield - 368s Burdett) | replace 107s2 25kV s/w, repair 107s3, replace conductor on 138kV high side of T1. 2nd Scope: Installing screw piles for 138kV PTs. Installing steel structure, 138kV PTs, junction box, grounding and connections to the bus. | For Information Only
ALTALINK | 812AL (512s Hartell - 812L), 812L (65s High RIver - 392s Black Diamond) | 2020-10-19 09:15 | 2020-10-19 17:15 | N | N | replace strain insulators on 812L dead end | Line | 812L (65s High RIver - 392s Black Diamond) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, For Information Only, Pre-Condition
ATCO | 7L70 (700s Bonnyville - 707s St.Paul) | 2020-10-19 10:00 | 2020-10-21 15:00 | N | Y | 7L70 crossarm replacements | Line | 7L70 (700s Bonnyville - 707s St.Paul) | 7L70 Crossarm replacements | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 17s Benalto 240 kV South Bus 2, 17s T2 (17s Benalto), 17s C1 (17s Benalto) | 2020-10-19 10:00 | 2020-10-19 17:00 | N | Y | remove 1081L dead end from switch and lattice structure | Bus, Transformer, Shunts | 17s 13 (17s Benalto), 17s 9 (17s Benalto), 17s 1652 (17s Benalto), 17s C1 (17s Benalto), 17s 85 (17s Benalto), 17s T2 (17s Benalto) | Bus outage to remove 1081L Dead End from Switch and Lattice Structure. Line Crew will tie this back to the lattice for switch replacement | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 86s 1252 (86s Bigstone), 914L (86s Bigstone - 289s Saunders Lake) | 2020-10-19 10:30 | 2020-10-29 18:00 | N | Y | 86s1252 breaker replacement | Circuit Breaker, Line | 86s 1252 (86s Bigstone), 914L (86s Bigstone - 289s Saunders Lake) | 86s1252 breaker replacement. 914L will be de-energized to energize new breaker from 289s. | Affects Cranking Path
ALTALINK | 320p PS2 (320p Keephills), 320p 2652 (320p Keephills), 320p 2752 (320p Keephills) | 2020-10-19 11:00 | 2020-10-29 16:30 | N | Y | doble test 320P PS2 | Transformer, Circuit Breaker | 914L (86s Bigstone - 289s Saunders Lake) |  | 240 kV, Pre-Condition
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2020-10-19 12:00 | 2020-10-23 18:00 | N | Y | components structure range 1-121 | Line | 1046L (310p Sundance - 338s Cherhill) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 392s T3 (392s Black Diamond), 812L (392s Black Diamond - 812AL) | 2020-10-19 12:15 | 2020-10-23 16:45 | N | N | complete bushings and LAs on T3 | Transformer, Line | 392s T3 (392s Black Diamond) | Outage to complete bushings and LAs on T3. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, For Information Only, Pre-Condition
ALTALINK | 745AL (411s Obed - 745A1L), 411S Obed | 2020-10-20 07:00 | 2020-10-22 19:00 | N | N | 411s T1 oil replacement and doble, 411s2 switch repairs | Line, Station | 745AL (411s Obed - 745A1L) | 411s T1 Oil Replacement and Doble, 411s2 Switch Repairs Scheduled: Shannon Bouchard Issue To: Tyler Kee Contact #: 778.214.6493 | For Information Only
Syncrude | ML3 (D05 Syncrude - N11 Syncrude) | 2020-10-20 08:00 | 2020-10-30 20:00 | N | N | support E02 Substation PM | Line | ML3 (D05 Syncrude - N11 Syncrude) |  | For Information Only
ENMAX | ENMAX 5 | 2020-10-20 08:00 | 2020-10-22 16:00 | N | N | replacement on 5PT138-Z32 | Station |  |  | For Information Only
Syncrude | RL1 (848s Ruth Lake - D05 Syncrude) | 2020-10-20 08:00 | 2020-10-21 20:00 | N | Y | 260KV 5 Yr PM for RL-1 | Line |  |  | 240 kV, Creates Radial Feeds, Affects Cranking Path
ALTALINK | 310p T30 (310p Sundance), 310p Sundance 240kV Bus C, 310p T36 (310p Sundance) | 2020-10-20 08:00 | 2020-10-28 17:30 | N | Y | protection upgrade and equipment replacements | Transformer, Bus | 310p Sundance 240kV Bus C, 310p 767X (310p Sundance), 310p 2852 (310p Sundance), 310p T36 (310p Sundance), 310p T30 (310p Sundance), ???? | T36 A & B protection upgrade, 310p140 PT 138kV & 310p139 PT 69 kV replacements | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 28.2TR (ENMAX 28) | 2020-10-20 08:00 | 2020-10-20 12:00 | N | N | arc flash mitigation project. change the grounding on the concentrics of the 8 kV cables | Transformer |  | Arc Flash Mitigation Project. Change the grounding on the concentrics of the 8kV cables | For Information Only
ENMAX | 2.1TR (ENMAX 2) | 2020-10-20 08:00 | 2020-10-22 16:00 | N | N | GIS minor maintenance | Transformer |  | GIS Minor Maintenance 2B138-D83. 2B138-D82. GIS Switch Maintenance 2MD84_84G, 2MD83_83G, 2SW2.1TRG, 2MD138-2.1TR_2.1TRG. Special switching instructions required. | For Information Only
ALTALINK | 649s T1 (649s Chappice Lake) | 2020-10-20 08:30 | 2020-10-20 13:30 | N | N | station outage to perform relay maintenance | Transformer |  | techs require station outage to perform relay maintenance on: 649s 2059X Breaker protection 2058L 79/L8 MVTR51 (recloser OOS while testing 1 hr - No redundancy for 2058L recloser) | For Information Only
ALTALINK | 283s T2 (283s Violet Grove) | 2020-10-20 08:30 | 2020-10-22 17:30 | N | N | investigation of tap board & TC filter installation | Transformer | 283s T2 (283s Violet Grove) | 283s T2 investigation of Tap Board & TC filter installation, | For Information Only
ALTALINK | 612L (336s Fincastle - 368s Burdett), 722L (107s Westfield - 368s Burdett), 368s C1 (368s Burdett), 368s T2 (368s Burdett) | 2020-10-20 09:00 | 2020-10-23 18:00 | N | N | equipment repair on bus | Line, Shunts, Transformer | 368s T2 (368s Burdett), 368s 722X (368s Burdett), 368s 612 (368s Burdett), 368s 35 (368s Burdett), 722L (107s Westfield - 368s Burdett), 612L (336s Fincastle - 368s Burdett), 368s C1 (368s Burdett) | Equipment repair on bus. Fortis DG not required to call down, no impact to generation | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 723L (150s Clyde - 438s Westlock) | 2020-10-20 09:00 | 2020-11-02 17:00 | N | N | breaker HV connection, complete dead end installation and line connection, install and connect s17 | Line | 723L (150s Clyde - 438s Westlock) | Complete Breaker HV Connection, Complete dead end installation and line connection, Install and connect s17 | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 519L (519AL - 526L), 661S Laura Lake, 996S Imperial Oil Carson Lake | 2020-10-20 10:00 | 2020-10-20 18:30 | N | N | closing open point 'A' inside 661s | Line, Station | 519AL (661s Laura Lake - 519L), 519L (996s Imperial Oil Carson Lake - 519AL) |  | For Information Only
EPCOR | 814s B2401 (814s Bellamy) | 2020-10-21 07:00 | 2020-10-23 17:00 | N | Y | breaker maintenance | Circuit Breaker |  |  | 240 kV, For Information Only
EPCOR | 557s T2 (557s Castle Downs) | 2020-10-21 07:00 | 2020-10-23 17:00 | N | Y | protection upgrade project | Transformer | 557s T2 (557s Castle Downs), 557s 2403 (557s Castle Downs), 557s 2404 (557s Castle Downs) | Outage required for protection upgrade project | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 310p 2452 (310p Sundance), 310p 2352 (310p Sundance) | 2020-10-21 08:00 | 2020-10-27 16:30 | N | Y | trip testing from new protections on 4160V in plant (Unit service) | Circuit Breaker | 310p 2352 (310p Sundance), 310p 2452 (310p Sundance) |  | 240 kV, For Information Only
ATCO | 7L760 (767s Oyen - 7L760D2), 7LA760 (914s Bindloss - 7LA760) | 2020-10-21 08:00 | 2020-10-22 19:00 | N | Y | cut in Cavendish tie in new line, maintenance (P865) | Line | 7LA760 (914s Bindloss - 7LA760) | GOI on 7LA760 to cut in Cavendish Tie In new line,7LB760 also have some work to do on 7L760 to take 4 wind monitors down, and fix the 3 way switches, 7L760- D2---7LA760-D1---7L760-D3 When we have 7LB760 Line cut in to 7LA760--- we will need a GOI from new open Gang switch 7LB760D1 to 893S Cavendish sub (7LB760D2) to finish line construction. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 275s 2 (275s Jenner) | 2020-10-21 08:30 | 2020-10-22 17:30 | N | Y | urgent repair, replacement of 944L protection | Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ATCO | 9L27 (755s Cordel - 863s Paintearth), 863s 901 (863s Paintearth) | 2020-10-21 08:30 | 2020-10-22 16:00 | N | Y | breaker maintenance | Line, Circuit Breaker | 9L27 (755s Cordel - 863s Paintearth), 863s 901 (863s Paintearth) | Breaker Maintenance on 901, 9L27 open ended | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 223L (150s Clyde - 159s Colinton) | 2020-10-21 09:00 | 2020-10-21 14:30 | N | N | mobile disconnection | Line | 223L (150s Clyde - 159s Colinton) | Outage to Remove 138kV & 25kV Cables from 472s Mobile Disconnect Mobile. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 799L (235s Entwistle - 443s South Mayerthorpe) | 2020-10-21 09:00 | 2020-10-21 17:30 | N | N | replacing strain insulators | Line | 799L (235s Entwistle - 443s South Mayerthorpe) | Replacing strain insulators on 799L | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 8.6TR (ENMAX 8) | 2020-10-21 12:00 | 2020-10-23 16:00 | N | N | T-60 upgrade phase 2 | Transformer | 8.6TR (ENMAX 8) |  | For Information Only
ATCO | 2029s ACF14 (2029s Heathfield), 2029s ACF11 (2029s Heathfield), 2029s ACF12 (2029s Heathfield), 2029s ACF13 (2029s Heathfield) | 2020-10-22 07:30 | 2020-10-23 15:00 | N | Y | PRC testing AC filter bank 1 | Shunts | 2029s ACF11 (2029s Heathfield), 2029s ACF12 (2029s Heathfield), 2029s ACF13 (2029s Heathfield), 2029s ACF14 (2029s Heathfield) | PRC testing AC Filter Bank 1 No Filter redundancy during work and Reduced Voltage Mode Depending on system dispatch levels the voltage will be reduced below 500KV DC and PCAP will adjust accordingly. (1050MW to 950MW range) | 240 kV, Limits Ratings, Pre-Condition
Syncrude | RL2 (848s Ruth Lake - D05 Syncrude) | 2020-10-22 08:00 | 2020-10-23 20:00 | N | Y | 5 year PM | Line | RL2 (848s Ruth Lake - D05 Syncrude) | Significant Outage: 260KV, 5 Yr PM RL-2 Following Circuit Breakers will be operated: 512, 513 (D05 Sub.) 902, 907 (Ruth Lake Sub.) Following MOD's will be operated: 512B, 513B, 515 (D05 Sub.) 902A, 907A, RL-2D1 (Ruth Lake Sub.) | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
Syncrude | Aurora T4 (Aurora), Aurora 221 (Aurora), Aurora 222 (Aurora) | 2020-10-22 08:00 | 2020-10-30 20:00 | N | Y | urgent hot spot repair | Transformer, Circuit Breaker |  |  | 240 kV, Restricts Generation
ALTALINK | 5s 70 (5s East Calgary), 5s C3 (5s East Calgary) | 2020-10-23 08:00 | 2020-10-23 17:00 | N | N | emergency repair: replace SCC controller device on breaker | Switch, Shunts | 5s C3 (5s East Calgary) |  | Pre-Condition
ENMAX | 39.3TR (ENMAX 39) | 2020-10-23 08:00 | 2020-10-23 16:00 | N | N | replacement of external control wiring | Transformer | 39.3TR (ENMAX 39) |  | For Information Only
ALTALINK | 5s 852 (5s East Calgary), 5s C4 (5s East Calgary) | 2020-10-23 08:00 | 2020-10-23 17:00 | N | N | emergency repair: replace failed SCC controller device | Circuit Breaker, Shunts | 5s 852 (5s East Calgary), 5s C4 (5s East Calgary) |  | Pre-Condition
ALTALINK | 5s T2 (5s East Calgary) | 2020-10-23 15:00 | 2020-10-30 16:00 | N | Y | forced outage | Transformer | 5s T2 (5s East Calgary) |  | 240 kV
Saskpower | SaskPower C1S | 2020-10-23 22:00 | 2020-10-25 19:00 | N | Y | structure replacements | Line | SaskPower C1S |  | Limits ATC
ALTALINK | 391s T1 (391s Balzac) | 2020-10-24 08:00 | 2020-10-29 16:00 | N | N | forced outage | Transformer |  |  | For Information Only
ALTALINK | 337s 746BW (337s Canada Liquid Air), 337s T1 (337s Canada Liquidair), 337s T2 (337s Canada Liquidair) | 2020-10-25 08:00 | 2020-10-27 17:00 | N | N | maintenance and doble | Circuit Breaker, Transformer | CANADALIQUIDAIR | 337s746BW Gas level/gauge covers, Maintenance and Doble on T1 TX18588 | For Information Only
EPCOR | 665s T3 (665s Dome) | 2020-10-26 07:00 | 2020-11-25 17:00 | N | Y | cut in and energization of new 72DS26 line (P1659) | Transformer | 665s T3 (665s Dome) |  | 240 kV, For Information Only
EPCOR | 814s B2407 (814s Bellamy) | 2020-10-26 07:00 | 2020-10-28 17:00 | N | N | breaker maintenance | Circuit Breaker |  |  | For Information Only
ATCO | 13L50 (2029s Heathfield - 2075s Newell) | 2020-10-26 07:00 | 2020-11-06 17:30 | N | Y | EATL outage | Line |  | EATL OUTAGE 2020 EATL Outage: Inspections IR Camera Installs nLFL Testing Expansion Tank Sensor Replacement | 500 kV, Pre-Condition
EPCOR | T3 (Namao), 72CN10 (987s Clover Bar - Namao) | 2020-10-26 07:00 | 2020-11-05 17:00 | N | N | motorized disconnect replacement | Transformer, Line | T3 (Namao) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72RS5 (Rossdale - Strathcona) | 2020-10-26 07:00 | 2020-11-18 17:00 | N | N | de-energize RS5, remove pot heads, connect 72DS26 to Strathcona and energization (P1659) | Line | 72RS5 (Rossdale - Strathcona) | de-energize RS5, remove pot heads, connect 72DS26 to Strathcona and energization (P1659) | Creates Radial Feeds, Firm Load Loss
ENMAX | 9.1TR (ENMAX 9) | 2020-10-26 07:00 | 2020-10-27 12:00 | N | N | roxtec installation, upgrade RTU, commission CA/OAC controls and NGR installation | Transformer |  | roxtec installation. Upgrade RTU. Commission CA/OAC controls. NGR installation. | For Information Only
ALTALINK | 58L (32s Barrier - 245s Seebe) | 2020-10-26 07:15 | 2020-10-30 17:45 | N | N | replacing structures and maintenance | Line | 58L (32s Barrier - 245s Seebe) | replacing Strs 36, 37, 42, 43 and maintenance on Strs 33, 39 | Creates Radial Feeds, Overload, Pre-Condition, Affects Cranking Path
ATCO | 9L36 (825s Whitefish Lake - 826s Marguerite Lake) | 2020-10-26 08:00 | 2020-11-08 16:00 | N | Y | upgrade P&C | Line | 9L36 (826s Marguerite Lake - 825s Whitefish Lake) | 240/144kV Breaker Fail Protection (OOS for duration of outages) 826S Marguerite P&C Upgrade | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 16.63L (ENMAX 16 - ENMAX 36), 36.5TR (ENMAX 36), 16B69-16.63 (ENMAX 16) | 2020-10-26 08:00 | 2020-11-06 16:00 | N | N | Hitachi HV breaker overhaul | Line, Transformer, Circuit Breaker | 16.63L (ENMAX 16 - ENMAX 36), 36.5TR (ENMAX 36) |  | Contingency Requires Mitigation, Overload, Pre-Condition
SUNCOR | 29PL6-1 (836s Steepbank - 29EDD-55) | 2020-10-26 08:00 | 2020-11-01 20:00 | N | N | 29PL6-1 from 30EDD-1/29EDD-55 - 5 year maintenance | Line |  | 29PL6-1 from 30EDD-1/29EDD-55 - 5 YR PM652-3701,3702, 29PS-119,111,112, 29PP37A 5yr PM 72kV Line | Creates Radial Feeds, Firm Load Loss
ENMAX | 65B240-D135 (ENMAX 65) | 2020-10-26 08:00 | 2020-10-26 12:00 | N | Y | remove birds nest and SF6 sample | Circuit Breaker | 65B240-D135 (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 831L (339s Duchess - 831AL), 339s T1 (339s Duchess) | 2020-10-26 08:00 | 2020-10-31 09:00 | N | N | installing new 138kV LA's on 831L, install new MOD disconnect (339s20), connect and commission new 138kV breaker (339s24), commission new transformer protection, connect CT circuit for LOP, replacing 25kV strain insulators | Line, Transformer | DUCHESS | Installing new 138kV LA's on 831L, install new MOD disconnect (339s20), connect and commission new 138kV breaker (339s24), Commission new transformer protection, connect CT circuit for LOP, replacing 25kV strain insulators | For Information Only
ALTALINK | 723L (150s Clyde - 438s Westlock) | 2020-10-26 08:00 | 2020-10-26 17:00 | N | N | for completion of maintenance tasks on 723L Str. 5A, | Line |  |  | For Information Only
ENMAX | 10.2TR (ENMAX 10) | 2020-10-26 08:00 | 2020-10-27 16:00 | N | N | phase 2 T-60 upgrade | Transformer |  |  | For Information Only
CMH | MH69s1 69kV North Bus (MH69s1 Power P Switchyard), 4L (MH69S-1 Power Plant - MH69S-6 Riverview), MH69s1 MH69-24 (MH69s1 Power P Switchyard), MH69s6 MH69-607 (MH69s6 Riverview) | 2020-10-26 08:00 | 2020-10-28 16:00 | N | N | upgrades | Bus, Line, Circuit Breaker | MH69s1 69kV North Bus (MH69s1 Power P Switchyard), 4L (MH69S-1 Power Plant - MH69S-6 Riverview), MH69s1 MH69-24 (MH69s1 Power P Switchyard) | Capital work, equipment upgrade | For Information Only, Pre-Condition
ALTALINK | 39s T2 (39s Bickerdike) | 2020-10-26 08:03 | 2020-11-05 17:00 | N | Y | fix leak repairs and counter repairs, replace oil | Transformer | 39s T2 (39s Bickerdike) |  | 240 kV, Over/Under Voltage, Pre-Condition
ATCO | 770s 703 (770s Three Hills), 770s 703T (770s Three Hills) | 2020-10-26 08:30 | 2020-10-27 16:00 | N | N | breaker maintenance | Circuit Breaker, Transformer | 770s 703 (770s Three Hills), 770s 703T (770s Three Hills) | Breaker Maintenance, 701T will be carrying all the load | For Information Only
BCH | B2S Cranbrook | 2020-10-26 08:30 | 2020-10-29 17:00 | N | Y | maintenance on 5RXN5 | Station | B2S Cranbrook | -There is a broken steel core on the right phase, sub- conductor as the spacers are all pulled from tower 187-203.Crews will identify the sub-conductor that has the broken steel core, remove all spacers, replacing the damaged sub-conductor between Str 186 and 204, re-install spacers and replace any damaged spacers. | 500 kV, Limits ATC, Pre-Condition
ATCO | 766s 701 (766s Nevis), 766s 901T (766s Nevis), 9L20 (755s Cordel - 766s Nevis), 9L912 (63s Red Deer - 766s Nevis) | 2020-10-26 08:30 | 2020-10-26 17:00 | N | Y | breaker maintenance | Circuit Breaker, Transformer, Line | 766s 901T (766s Nevis), 766s 701 (766s Nevis) | HLD PARTIAL TESTING @ NEVIS 766S 701 Breaker Maintenance 9L912 & 9L20 Open ended During Switching Breaker 901 & 902 are required open before operating 901TD@766S | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ATCO | 801s 910 (801s Anderson) | 2020-10-26 09:00 | 2020-10-29 16:00 | N | Y | breaker maintenance | Circuit Breaker | 801s 910 (801s Anderson) | Complete Breaker Maintenance, Ring Bus 911 Breaker in service | 240 kV, Contingency Requires Mitigation
ATCO | 7L70 (700s Bonnyville - 707s St.Paul) | 2020-10-26 10:00 | 2020-10-29 15:00 | N | Y | 7L70 crossarm replacements | Line | 7L70 (700s Bonnyville - 707s St.Paul) | 7L70 Crossarm replacements | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2020-10-26 10:00 | 2020-11-02 15:00 | N | Y | replacement of under rated and rotten crossarms | Line | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | Replacement of under rated and rotten crossarms | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 498s T2 (498s Tilley), 100L (498s Tilley - 895s Suffield) | 2020-10-26 11:00 | 2020-11-04 18:00 | N | N | install new 138kV "A" bus protection | Transformer, Line | 100L (498s Tilley - 895s Suffield), 498s T2 (498s Tilley) | Install new 138kV "A" Bus protection, Connect CT circuits from 498s100X and T2, Connect breaker status and trips for 498s100X, 498s2273, 498s5031, and 498s6260. Redundant protection will remain in place | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 65B240-D134 (ENMAX 65) | 2020-10-26 12:00 | 2020-10-26 16:00 | N | Y | SF6 sample, 65B240-D134 remove birds nest | Circuit Breaker | 65B240-D134 (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2020-10-26 12:00 | 2020-10-30 18:00 | N | Y | components structures range 1-121 | Line | 1046L (310p Sundance - 338s Cherhill) |  | 240 kV, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 275s 8 (275s Jenner) | 2020-10-26 12:30 | 2020-10-30 13:30 | N | Y | replacement of 1652 (275s8) breaker control | Circuit Breaker | 275s 8 (275s Jenner) |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 255s T1 (255s Vulcan) | 2020-10-26 13:00 | 2020-10-26 15:32 | N | N | bushing replacement, leak repairs, SFRA, doble, maintenance | Transformer | 255s T1 (255s Vulcan) | Bushing replacement, leak repairs, SFRA, Doble, maintenance Note: The transformer was removed from service today at 13:12 and returned to service at 15:32 when resources were re-allocated. Plan is to remove the transformer at 255s from service on Monday November 2, 2020. | For Information Only
ALTALINK | 954L (648s Metiskow - 650s Hansman Lake), 648s T3 (648s Metiskow) | 2020-10-27 07:00 | 2020-10-30 16:00 | N | Y | replacement of 648s33, PTs 2466, 2467 and 2468 | Line, Transformer | 954L (648s Metiskow - 650s Hansman Lake), 648s T3 (648s Metiskow), 648s 29 (648s Metiskow) | Replacement of 648s33, PTs 2466, 2467 and 2468 | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ENMAX | 27.1TR (ENMAX 27) | 2020-10-27 08:00 | 2020-10-27 12:00 | N | N | adjust LTC low oil level | Transformer |  | 27.1TR LTC low oil level - need to adjust | For Information Only
ALTALINK | 174L (197s Bardo - 289s Saunders Lake) | 2020-10-27 08:00 | 2020-10-29 17:00 | N | N | re string 2 spans of OPGW dead end on structures 379 and 381 | Line | 174L (197s Bardo - 289s Saunders Lake) | STR 379 to 381. re string 2 spans of OPGW dead end on 379 and 381(currently a tangent) and train OPGW down both structure. | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ENMAX | 2.3TR (ENMAX 2) | 2020-10-27 08:00 | 2020-10-28 16:00 | N | N | GIS minor switch maintenance | Transformer | 2.3TR (ENMAX 2) | GIS Minor Maintenance 2B138-D91, 2B138-D90. GIS Switch Maintenance - 2MD101_101G, 2MD99_99G, 2MD100_100G, 2MD138-2.3TR_2.3TRG, 2SW2.3TRG. Special switching instructions required. | For Information Only
ALTALINK | 77s T1 (77s Sagitawah) | 2020-10-27 08:30 | 2020-10-29 18:00 | N | Y | replace bushings and maintenance | Transformer | 77s T1 (77s Sagitawah) | Replace 77sT1 X1&X3 bushings, maintenance | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-10-27 09:00 | 2020-10-27 17:00 | Y | Y | drilling and blasting activities within close proximity of 1L274 | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 926L (17s Benalto - 310p Sundance) | 2020-10-27 09:00 | 2020-10-28 15:00 | N | Y | replace 17s926N control module and repairs to 17s926N switch | Line | 17s 11 (17s Benalto), 17s 12 (17s Benalto), 926L (17s Benalto - 310p Sundance), | Replace 17s926N Control Module, and Make to repairs to 17s926N Switch | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 293s T2 (293s Bernese) | 2020-10-27 13:00 | 2021-01-27 08:00 | N | N | install grounds to facilitate high bus installation | Transformer |  | Install grounds to facilitate high bus installation overtop of AltaLink owned bus pipe. No connection to the system at this time. | For Information Only
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-10-28 07:30 | 2020-10-28 19:00 | Y | Y | urgent repair of D/E structure cross-arms | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ENMAX | 12.1TR (ENMAX 12) | 2020-10-28 08:00 | 2020-10-28 12:00 | N | N | 12.1TR LTC low oil need to adjust oil level | Transformer |  |  | For Information Only
CMH | MH69s1 MH69-24 (MH69s1 Power P Switchyard) | 2020-10-28 08:00 | 2020-11-03 16:00 | N | N | upgrades | Circuit Breaker | MH69s1 MH69-24 (MH69s1 Power P Switchyard) |  | For Information Only
Syncrude | UE-1 30-2PTR72-B2 (UE-1) | 2020-10-28 08:00 | 2020-10-28 19:00 | N | N | maintenance | Transformer | 30-2PTR72-B2 |  | For Information Only
ATCO | 7L07 (790s Poplar Hill - 815s Goodfare), 790s 703 (790s Poplar Hill) | 2020-10-28 09:00 | 2020-10-30 10:00 | N | Y | top up and investigate low SF6 on one pole | Line, Circuit Breaker | 7L07 (790s Poplar Hill - 815s Goodfare), 790s 703 (790s Poplar Hill) | 790S 703 Center Pole Low 0.66Mpa Top up and investigate low SF6 on one pole | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload
ALTALINK | 205s Castle Rock Ridge RTU/SCADA | 2020-10-28 09:00 | 2020-10-28 13:00 | N | N | SCADA ICCP Comms cutover for ENEL sites from Telus MPLS network to new MASERGY network | Terminal Equipment |  |  | Affects Visibility
ATCO | 757s 604 (757s Battle River), 6L02 (757s Battle River - 765s Mannix Mine) | 2020-10-28 09:00 | 2020-10-30 16:00 | N | N | breaker 604 leak test / maintenance | Circuit Breaker, Line | 6L02 (757s Battle River - 765s Mannix Mine) | Breaker 604 Leak test / maintenance | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 216s 865X (216s Knightsbridge), 865L (38s East Edmonton - 216s Knightsbridge) | 2020-10-28 09:30 | 2020-10-28 16:30 | N | N | add CT input from 216s865X to new metering module | Circuit Breaker, Line | 216s 865X (216s Knightsbridge), 865L (38s East Edmonton - 216s Knightsbridge) |  | Creates Radial Feeds, Firm Load Loss
ATCO | 940s 701T (940s Beartrap) | 2020-10-28 11:00 | 2020-11-11 16:00 | N | N | forced outage - broken bushing | Transformer |  | BROKEN BUSHING ON 701T | For Information Only
ALTALINK | 250p 11 (250p Bighorn Plant) | 2020-10-28 11:00 | 2020-10-28 15:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ATCO | 7L93 (828s Sulphur Point - 930s Arcenciel) | 2020-10-28 14:00 | 2020-10-28 15:00 | N | Y | open end 7L93 @ 930S Arcenciel for Sulphur Point Telecom outage 2-53099 due to stability concerns | Line | 7L93 (828s Sulphur Point - 930s Arcenciel) | Open end 7L93 @ 930S Arcenciel for Sulphur Point Telecom outage 2-53099 due to stability concerns | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 28.2TR (ENMAX 28) | 2020-10-29 07:00 | 2020-10-29 12:00 | N | N | repair shutters on 28BB8-28.2TR cell | Transformer | 28.2TR (ENMAX 28) |  | For Information Only
EPCOR | K722 (Kennedale) | 2020-10-29 08:30 | 2020-10-29 16:00 | N | N | substation switching school isolation of K722 at Kennedale | Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-10-29 09:00 | 2020-10-30 17:00 | Y | Y | drilling and blasting activities within close proximity of 1L274 | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Limits ATC, Pre-Condition
ALTALINK | 17s Benalto 240 kV South Bus 2, 17s T2 (17s Benalto), 17s C1 (17s Benalto) | 2020-10-29 09:00 | 2020-10-29 17:00 | N | Y | transfer 1081L slack span from lattice structure to new 1081 switch | Bus, Transformer, Shunts | 17s 13 (17s Benalto), 17s 4 (17s Benalto), 17s 1652 (17s Benalto), 17s 9 (17s Benalto), 17s 85 (17s Benalto), 17s T2 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 216s 32 (216s Knightsbridge), 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) | 2020-10-29 09:00 | 2020-10-29 16:30 | N | N | add CT input from 216s32 to new metering module | Circuit Breaker, Line | 216s 32 (216s Knightsbridge), 705L (184s Petro-Canada Edmonton - 216s Knightsbridge) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T3 (Rossdale) | 2020-10-30 07:00 | 2020-10-30 17:00 | N | N | tap changer maintenance | Transformer | T3 (Rossdale) |  | For Information Only
ALTALINK | 268s 797 (268s Whitecourt), 797L (268s Whitecourt - 364s Whitecourt industrial) | 2020-10-30 08:00 | 2020-10-30 17:00 | N | N | 9269R radio work requires line OOS | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR, ALTALINK | 113S Inland-Cement, 711L (Inland Cement - 747L tap) | 2020-10-31 07:00 | 2020-11-01 17:00 | N | N | emergency repair on hot connections | Station, Line |  | Emergency Repair on hot connections | For Information Only
Syncrude | D05 512 (D05 Syncrude), D05 D05 | 2020-10-31 08:00 | 2020-11-03 20:00 | N | Y | breaker operation | Circuit Breaker, Station |  | Significant Outage - D05 Substation 260KV Outage - Tie Breaker (512PM). Following Circuit Breakers will be operated: - 512 Following MOD's will be operated: - 512A, 512B | For Information Only
ALTALINK, EPCOR | 1238L (330p Genesee - 510s Sunnybrook), 330p 1201 (330p Genesee), 330p 1202 (330p Genesee) | 2020-11-02 07:00 | 2020-11-03 17:00 | N | Y | cutover of new DFR | Line, Circuit Breaker | 1238L (330p Genesee - 510s Sunnybrook), 330p 1201 (330p Genesee), 330p 1202 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 285s T2 (285s East Camrose) | 2020-11-02 07:00 | 2020-11-06 08:00 | N | N | cut T2 free from 285s91 and create open point T, replace T2 with T2X | Transformer |  | Replace T2 with T2X. Cut T2 free from 285s91. Create Open Point T | For Information Only
EPCOR | RW2401 (EPCOR Riverview), RW2405 (EPCOR Riverview), T1 (EPCOR Riverview) | 2020-11-02 07:00 | 2020-11-06 17:00 | N | Y | riser repair and commissioning | Circuit Breaker, Transformer | T1 (EPCOR Riverview) | Riser Repair and Commissioning | 240 kV, Contingency Requires Mitigation
ALTALINK | 76L (33s Spray - 115s Mt. Allan) | 2020-11-02 07:15 | 2020-11-20 17:45 | N | N | replacing strs 47, 83, 87, 96, 98, 111A, 112, 113, 114 | Line | 76L (33s Spray - 115s Mt. Allan) | replacing strs 47, 83, 87, 96, 98, 111A, 112, 113, 114. Maintenance on strs 2, 5, 7, 9, 12, 14, 15, 17, 19, 22, 50, 52, 53, 63, 69. Re-sag OHSW between strs 87, 93 | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ENMAX | 15.2TR (ENMAX 15) | 2020-11-02 08:00 | 2020-11-04 16:00 | N | N | replace CT in 15B8-15.17 cell | Transformer |  | Replace CT in 15B8-15.17 cell. Customer outage required on 25W-121. OH Crew scheduled. | For Information Only
ENMAX | 6.1TR (ENMAX 6) | 2020-11-02 08:00 | 2020-11-04 16:00 | N | N | NGR installation | Transformer | 6.1TR (ENMAX 6) |  | For Information Only
ENMAX | 10.1TR (ENMAX 10) | 2020-11-02 08:00 | 2020-11-02 16:00 | N | N | investigate 10.1TR low oil alarm | Transformer |  |  | For Information Only
ALTALINK | 3L (245s Seebe - 3AL) | 2020-11-02 08:30 | 2020-11-02 11:00 | N | N | create open Point 'A' (between Str 3L145 and JCT 3L46/3AL0) | Line | 3L (245s Seebe - 3AL) | Create Open Point 'A' (between Str 3L145 and JCT 3L46/3AL0). Required for Emergency Repair: 3L145 (43s loads to remain online) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 914L (63s Red Deer - 87s Gaetz) | 2020-11-02 08:45 | 2020-11-05 15:45 | N | Y | upgrade SCADA | Line |  |  | 240 kV, Pre-Condition, Affects Cranking Path
ATCO | 794s 701T (794s Valleyview) | 2020-11-02 09:00 | 2020-11-03 17:00 | N | N | emergency repair leak on 701T | Transformer |  | Emergency repair leak on 701T, all 25Kv Load will be carried on 702T. | For Information Only
Lethbridge | 241s 813L (241s Lethbridge Uplands), 813L (146s Lethbridge MacDonald - 241s Lethbridge Uplands) | 2020-11-02 09:00 | 2020-11-02 10:00 | N | N | test trip breaker | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 13 (17s Benalto) | 2020-11-02 09:30 | 2020-11-13 14:00 | N | Y | replace 17s13 breaker to new SF6 type | Circuit Breaker | 17s 13 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 162s 138-RB80 (162s Beddington), 162s 138-RB81 (162s Beddington), 162.81L (162s Beddington - 391S Balzac) | 2020-11-02 09:30 | 2020-12-05 16:00 | N | Y | line protection upgrade | Circuit Breaker, Line |  | Line Protection Upgrade. Adjust GOI for 771L Outage Nov-24-25th | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
EPCOR | 1058L (657s Summerside - 803s Lambton) | 2020-11-02 09:30 | 2020-11-06 14:00 | N | Y | line maintenance and upgrades | Line | 1058L (657s Summerside - 803s Lambton) | Line Maintenance/Upgrades | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ATCO | 6L02 (765s Mannix Mine - 873s Marion Lake) | 2020-11-02 10:00 | 2020-11-06 02:30 | N | N | crossarm replacement and inter phase spacers | Line |  | 6L02 Crossarm replacement and Inter phase spacers Isolation Expanded Nov 6, 2020 2020-11-02 10:00 to 2020-11-06 13:00 - 6L02D4 & 6L02D5 2020-11-06 13:00-16:00 - 6L02D5, 6L02D2, 6L02D3, 6L05D2 765S Mannix Mine Customers have agreed to an outage. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 7L70 (700s Bonnyville - 707s St.Paul) | 2020-11-02 10:00 | 2020-11-05 15:00 | N | Y | crossarm replacements | Line | 7L70 (700s Bonnyville - 707s St.Paul) | 7L70 Crossarm replacements | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
Lethbridge, ALTALINK | 241s 734L (241s Lethbridge Uplands), 734L (241s Lethbridge Uplands - 370s North Lethbridge) | 2020-11-02 10:30 | 2020-11-02 16:00 | N | Y | test trip breaker, commission control points | Circuit Breaker, Line |  | Test Trip Breaker, Commission control points and Energize New 241s T1 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 74s C2 (74s Janet), 74s C1 (74s Janet) | 2020-11-02 10:30 | 2020-11-02 17:30 | N | N | emergency repair: investigate internal CT's on this cap | Shunts | 74s C1 (74s Janet), 74s C2 (74s Janet) | Emergency Repair: investigate internal CT's on this cap | Pre-Condition
ACCIONA | 139s89SAB-1 (139s Hillridge) | 2020-11-02 10:45 | 2020-11-02 15:00 | N | Y | complete control operational functionality commissioning for the new joint venture operator | Switch |  |  | Restricts Generation
ALTALINK | 3L (245s Seebe - 3AL) | 2020-11-02 11:00 | 2020-11-02 15:00 | N | N | emergency repair: 3L145 airbrake requires adjustment | Line | 3L (245s Seebe - 3AL) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 255s T1 (255s Vulcan) | 2020-11-02 12:30 | 2020-11-06 02:30 | N | N | bushing replacement, leak repairs, SFRA, doble, maintenance | Transformer |  |  | For Information Only
ALTALINK | 3L (245s Seebe - 3AL) | 2020-11-02 15:00 | 2020-11-02 17:30 | N | N | close open point 'A' (between Str 3L145 and JCT 3L46/3AL0) | Line | 3L (245s Seebe - 3AL) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
Syncrude | AL-1 (Aurora - D05 Syncrude), Aurora 211 (Aurora), Aurora 213 (Aurora), D05 517 (D05 Syncrude), D05 519 (D05 Syncrude) | 2020-11-03 07:00 | 2020-11-09 20:00 | N | Y | tie-ins for various infrastructure system | Line, Circuit Breaker |  | Tie-Ins for various infrastructure system. Following Circuit Breakers will be operated: 517, 519 (D05 Sub.) 211, 213 (G01 Sub.) Following MOD's will be operated: 517A, 517B, 519A, 519B, 520, (D05 Sub.) 211A, 212B, 213A, 213B, 215 (G01 Sub.) | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 99s T1 (99s North St. Albert) | 2020-11-03 07:00 | 2020-11-05 16:00 | N | N | upgrade station service SS1 | Transformer | 99s T1 (99s North St. Albert) |  | For Information Only
ALTALINK | 728L (157s Lac La Biche - 353s Plamondon) | 2020-11-03 08:00 | 2020-11-03 16:00 | N | Y | urgent repairing 157s19 | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 205s Castle Rock Ridge RTU/SCADA | 2020-11-03 08:00 | 2020-11-03 17:00 | N | N | RTAC reboot | Terminal Equipment |  |  | Affects Visibility
ALTALINK | 412L (396s Pincher Creek - 632s Russell), 396s 412 (396s Pincher Creek) | 2020-11-03 10:00 | 2020-11-03 11:00 | N | Y | upgrade 396s MPLS node | Line, Circuit Breaker |  |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-11-03 11:30 | 2020-11-03 17:00 | Y | Y | drilling and blasting activities within close proximity of 1L274 | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Limits ATC, Pre-Condition
BCH | 1L274 (Elkford Tap - Elkford), 1L274 (EFT - 1D2L274) | 2020-11-03 17:30 | 2020-11-03 22:00 | N | Y | bypass removal | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Pre-Condition
ALTALINK | 1046L (310p Sundance - 338s Cherhill) | 2020-11-04 07:00 | 2020-11-06 18:00 | N | Y | components structure range 1-121 | Line | 1046L (310p Sundance - 338s Cherhill) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ALTALINK, EPCOR | 1239L (330p Genesee - 510s Sunnybrook), 330p 1205 (330p Genesee), 330p 1206 (330p Genesee) | 2020-11-04 07:00 | 2020-11-05 17:00 | N | Y | cutover of new DFR at Genesee | Line, Circuit Breaker | 1239L (330p Genesee - 510s Sunnybrook), 330p 1205 (330p Genesee), 330p 1206 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 106S Paddle River | 2020-11-04 08:00 | 2020-11-04 15:00 | N | N | customer maintenance | Station |  |  | For Information Only
ENMAX | ENMAX 25 240kV South Bus, 25B240-D131 (ENMAX 25), 25B240-D134 (ENMAX 25), 25B240-D138 (ENMAX 25), 25B240-D140 (ENMAX 25) | 2020-11-04 08:00 | 2020-11-05 18:00 | N | Y | HV switch maintenance | Bus, Circuit Breaker | 25B240-D131 (ENMAX 25), 25B240-D134 (ENMAX 25), 25B240-D140 (ENMAX 25) | HV SW maint SW145, SW149. Replace switch mech SW131, SW137. SW 145 at 25 sub - stiff to operate. Original outage Oct 21-22 | 240 kV, Contingency Requires Mitigation
ALTALINK | 723L (69s North Barrhead - 724L tap) | 2020-11-04 08:00 | 2020-11-14 17:00 | N | N | maintenance on structures | Line | 723L (69s North Barrhead - 724L) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 284S Nose Creek | 2020-11-04 08:00 | 2020-11-05 17:00 | N | N | customer switchgear maintenance | Station |  |  | For Information Only
ATCO | MUL1 Mowat | 2020-11-04 10:00 | 2020-11-04 11:00 | N | N | due to 7L68, 7L73 and 7L75 TPR outage | Unit
ALTALINK, ACCIONA | 226s SAB-1 (226s Garden City) | 2020-11-04 10:45 | 2020-11-04 15:00 | N | Y | complete control operational functionality commissioning for the new joint venture operator | Switch |  |  | Restricts Generation
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2020-11-05 07:00 | 2020-11-06 18:00 | N | Y | urgent replacement of one 240 kV CVT (275s24) due to oil leak and conductor repair | Line |  | Urgent replacement of one 240 kV CVT (275s24) due to oil leak. 2nd Scope: P5 Urgent Conductor Repair between 951L41 & 951L42 D/C 944L | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 723s T2 (723s Christina Lake), 723s 252 (723s Christina Lake) | 2020-11-05 07:00 | 2020-11-05 18:00 | N | Y | emergency work, 723s 252 gas leak | Transformer, Circuit Breaker |  | Emergency Work; l723s252 SF6 Gas leaking out  Almost empty | 240 kV, For Information Only
ENMAX, ALTALINK | 918L (162s Beddington - 281s Johnson) | 2020-11-05 07:15 | 2020-11-12 17:45 | N | Y | maintenance on structures 764 - 842, RB on 771L for shared towers | Line |  | Scope of work includes maintenance on structures 764 - 842. RB on 771L for shared towers | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
ALTALINK | 418L (20s Ghost - 189L tap) | 2020-11-05 07:15 | 2020-11-06 17:45 | N | N | replacing structures 131 and 135 | Line | 418L (20s Ghost - 189L) | Scope of work includes replacing structures 131 and 135 | Affects Cranking Path
ENMAX | 5.10TR (ENMAX 5) | 2020-11-05 08:00 | 2020-11-07 16:00 | N | N | NGR installation | Transformer | 5.10TR (ENMAX 5) |  | For Information Only
ENMAX | 918L | 2020-11-05 08:00 | 2020-11-06 17:00 | N | Y | RTU & line protection upgrade- settings changes | Terminal Equipment | 918L (162s Beddington - 281s Johnson) | RTU & Line Protection Upgrade. Settings changes. Altalink sharing outage until Nov 12th | 240 kV, For Information Only
CMH | MH-10L (MH69s2 North Industrial - MHS8 Burnside) | 2020-11-05 08:00 | 2020-12-16 08:00 | N | N | cut the 10L into the new MHS-10 substation (P2151 CMH Central Area Upgrade) | Line | MH-10L (MH69s2 North Industrial - MHS8 Burnside) | cut the 10L into the new MHS-10 substation (P2151 CMH Central Area Upgrade) | Contingency Requires Mitigation, Creates Radial Feeds
ALTALINK | 42s C1 (42s Sarcee) | 2020-11-05 08:15 | 2020-11-05 17:45 | N | N | top up SF6 | Shunts | 42s C1 (42s Sarcee), 42s 1652 (42s Sarcee) | SF6 % might be low, have to retest the % of SF6 | For Information Only
EPCOR | K722 (Kennedale) | 2020-11-05 08:30 | 2020-11-05 16:00 | N | N | substation switching school isolation of K722 | Circuit Breaker | K722 (Kennedale) | substation switching school isolation of K722 at Kennedale Substation Switching School isolation of K722 | Creates Radial Feeds, Firm Load Loss
ALTALINK | 729L (285s East Camrose - 542s Ervick), 285s 729W (285s East Camrose), 285s T2 (285s East Camrose), 285s East Camrose 138kV Partial Bus | 2020-11-05 17:00 | 2020-11-05 19:00 | N | N | energization of new 285sT2X and new switchgear from 285s729W breaker | Line, Circuit Breaker, Transformer, Bus | 285s East Camrose 138kV Partial Bus | Outage to facilitate the energization of new 285sT2X and new switchgear from 285s729W breaker. Voltage sensitive relays to be disabled (UF & 730L) as part of switching. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | 330P 12TC1 (330p Genesee), 330P Genesee 500 kV Bus 1, 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 1207 (330p Genesee), 330p 805 (330p Genesee) | 2020-11-06 07:00 | 2020-11-06 17:00 | N | Y | cutover of new DFR | Transformer, Bus, Circuit Breaker | 330P 12TC1 (330p Genesee), 330p 1201 (330p Genesee), 330p 1204 (330p Genesee), 330p 805 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
EPCOR | 72CH11 (987s Clover Bar - Hardisty) | 2020-11-06 07:00 | 2020-11-06 17:00 | N | N | emergency surge arrestor repair | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 3L (42s Sarcee - 272s Springbank) | 2020-11-06 07:15 | 2020-11-09 17:45 | N | Y | structure replacement (Str 392) due to lightning damage | Line | 3L (42s Sarcee - 272s Springbank) | Structure Replacement (Str 392) due to lightning damage | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 285s3202 (285s East Camrose) | 2020-11-06 08:00 | 2020-11-07 18:30 | N | N | cutover protections from 285s3202 to new switchgear building breaker 285s3202X | Circuit Breaker |  | Cutover protections from 285s3202 to new switchgear building breaker 285s3202X. Swap power cables on 3202L1U and close Open Point 'M'. Cut free 285s3202 from the system. DG does not come offline as load will be transferred with updated settings to 285s2157W so deemed non- significant. | For Information Only
ATCO | 765s 601T (765s Mannix Mine) | 2020-11-06 13:00 | 2020-11-06 16:00 | N | N | 6L02 crossarm replacement and inter phase spacers | Transformer |  | 6L02 Crossarm replacement and Inter phase spacers Isolation Expanded Nov 6, 2020 2020-11-02 10:00 to 2020-11-06 13:00 - 6L02D4 & 6L02D5 2020-11-06 13:00-16:00 - 6L02D5, 6L02D2, 6L02D3, 6L05D2 765S Mannix Mine Customers have agreed to an outage. | For Information Only
ALTALINK | 83s 172W (83s Taber), 172L (83s Taber - 172EL) | 2020-11-07 07:30 | 2020-11-08 17:30 | N | N | complete RAS scheme upgrade and functional testing at 83s | Circuit Breaker, Line | 83s 172W (83s Taber), 172L (83s Taber - 172EL) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 2.82L (ENMAX 2 - ENMAX 5), 2B138-D85 (ENMAX 2), 2B138-D86 (ENMAX 2) | 2020-11-07 08:00 | 2020-11-08 18:00 | N | N | maintenance 2B138-D85, D86, 2MD90_90G, 2MD89_89G, 2SW2.82G, 2MD138-2.82_2.82G and cable sheath test | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK, EPCOR | 1209L (89s Ellerslie - 330p Genesee) | 2020-11-09 07:00 | 2020-11-10 17:00 | N | Y | cutover of new DFR @ Genesee S/S | Line | 1209L (89s Ellerslie - 330p Genesee), 330p 1208 (330p Genesee), 330p 1209 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation, Over/Under Voltage, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
EPCOR | T1 (Garneau) | 2020-11-09 07:00 | 2020-11-20 17:00 | N | N | protection upgrade cutover | Transformer |  |  | Contingency Requires Mitigation, Overload, Pre-Condition
EPCOR | T2 (Kennedale) | 2020-11-09 07:00 | 2020-11-10 17:00 | N | N | emergency secondary term replacement | Transformer | T2 (Kennedale) | 1007395 - Emergency secondary term replacement | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2020-11-09 08:00 | 2020-11-09 16:00 | N | N | measure XO bushing connector, NGR installation | Transformer |  |  | For Information Only
ATCO | 757s 912T (757s Battle River), 9L80 (755s Cordel - 757s Battle River), 757s 912 (757s Battle River) | 2020-11-09 08:00 | 2020-11-11 08:00 | N | Y | breaker maintenance | Transformer, Line, Circuit Breaker | 757s 912 (757s Battle River), 757s 912T (757s Battle River), 9L80 (755s Cordel - 757s Battle River), 757s 701 (757s Battle River),757s 707 (757s Battle River), 7L701 (757s Battle River - 7LA701), 757s 701T (757s Battle River) | 757S - BKR 912 MIN OIL HPF COMPLETE TESTING, 912T OOS | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation, Affects Cranking Path
ENMAX | 13.1TR (ENMAX 13) | 2020-11-09 08:00 | 2020-11-09 16:00 | N | N | make grounding changes to concentric cables in the switchgear cubicle | Transformer |  | Make grounding changes to concentric cables in the switchgear cubicle | For Information Only
ENMAX | 5.1TR (ENMAX 5) | 2020-11-09 08:00 | 2020-11-11 16:00 | N | N | NGR installation | Transformer | 5.1TR (ENMAX 5) |  | For Information Only
ENMAX | 14B138-11.82 (ENMAX 14), 11.82L (ENMAX 11 - ENMAX 14), 11B138-11.82 (ENMAX 11) | 2020-11-09 08:00 | 2020-11-19 16:00 | N | N | breaker overhaul | Circuit Breaker, Line | 11.82L (ENMAX 11 - ENMAX 14) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 9L37 (825s Whitefish Lake - 826s Marguerite Lake) | 2020-11-09 08:00 | 2020-11-22 16:00 | N | Y | breaker fail protection | Line | 9L37 (826s Marguerite Lake - 825s Whitefish Lake) | 240/144kV Breaker Fail Protection (OOS for duration of outages) 826S Marguerite P&C Upgrade - Wiring and Commissioning | 240 kV, Contingency Requires Mitigation, Pre-Condition
ENMAX | 15.60L (ENMAX 15 - ENMAX 21) | 2020-11-09 08:00 | 2020-11-11 16:00 | N | N | 15.1 TR & 15.2 TR neutral reactor install | Line |  | 15 Sub Neutral Reactor Install (15.1 TR & 15.2 TR). Mobilize drilling rig and drill 2 piles for 15.1TR and 15.2TR NGRs | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.84L (ENMAX 2 - ENMAX 8) | 2020-11-09 08:00 | 2020-11-10 18:00 | N | N | GIS maintenance | Line |  |  | For Information Only
Syncrude | ML4 (D05 Syncrude) | 2020-11-09 08:00 | 2020-11-18 20:00 | N | N | ML4 feeder to support E02 substation maintenance | Line | Outage: ML4 Feeder to Support E02 Substation PM The following circuit breakers will be operated: 80 (D05 Substation) The following switches will be operated: 80A, 80B |  | For Information Only
ALTALINK | 661s T1 (661s Laura Lake) | 2020-11-09 08:30 | 2020-11-09 17:30 | N | N | closing 661s Open Point 'B' and returning equipment back to normal | Transformer |  | Closing 661s Open Point 'B' and returning equipment back to normal | For Information Only
BCH | 5L96 (Selkirk - Vaseux Lake) | 2020-11-09 09:00 | 2020-11-10 19:00 | N | Y | insulator replacement, BC maintenance does not affect the Alberta ATC | Line | 5L96 (Selkirk - Vaseux Lake) |  | Limits ATC, 500 kV
ALTALINK, EPCOR | 1059L (38s East Edmonton - 803s Lambton) | 2020-11-09 09:30 | 2020-11-13 14:00 | N | Y | line maintenance & upgrades | Line | 1059L (803s Lambton - 1059AL) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 701L (223s Strome - 7LA701) | 2020-11-09 10:00 | 2020-11-09 17:00 | N | N | ATCO requires 223s38 to be opened to prevent any transient stability issues during their outage on 757s 912T | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2020-11-09 10:00 | 2020-11-15 15:00 | N | Y | replacement of under rated and rotten crossarms | Line | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | Replacement of under rated and rotten crossarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Restricts Generation,Affects Cranking Path
ATCO | 6L05 (764s Heisler - 6L05 tap) | 2020-11-09 10:00 | 2020-11-09 17:00 | N | N | 6L05 pole replacement and changing cross-arms | Line | 6L05 (764s Heisler - 6L05 tap) | 6L05 Pole replacement and changing Cross-arms | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 276s T2 (276s Union Carbide Prentiss) | 2020-11-09 10:15 | 2020-11-20 17:45 | N | N | oil reclaim, SFRA test | Transformer | 276s T2 (276s Union Carbide Prentiss) | 276s T2 oil reclaim, SFRA test | For Information Only
Syncrude | AL-2 (Aurora - D05 Syncrude), D05 511 (D05 Syncrude), D05 512 (D05 Syncrude), D05 519 (D05 Syncrude), Aurora 222 (Aurora), Aurora 223 (Aurora) | 2020-11-10 07:00 | 2020-11-16 20:00 | N | Y | tie-ins for various infrastructure system, tie-ins for various infrastucture system | Line, Circuit Breaker |  | Tie-Ins for various infrastructure system Following Circuit Breakers will be operated: 511, 512, 519 (D05 Sub.) 222, 223 (G01 Sub.) Following MOD's will be operated: 511A, 511B, 512A, 512B, 514, 519A, 519B (D05 Sub.) 222A, 222B, 223A, 223B, 225 (G01 Sub.) | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 285s T1 (285s East Camrose) | 2020-11-10 07:00 | 2020-11-12 18:00 | N | N | cut over bus tie cables to new switchgear building, add new SS1,close open point 'C' & open point 'S, remove open point T | Transformer |  | Cut over bus tie cables to new switchgear building. Add new SS1. Close Open Point 'C' & Open Point 'S. Remove Open Point T. Return settings on 285s2157W L1 protection and T1 'A' protection back to normal as 285s3202 has been cut over to the new switchgear breaker 285s3202X. | For Information Only, Pre-Condition
ALTALINK | 770L (254s Coaldale - 370s North Lethbridge), 370s 770E (370s North Lethbridge), 254s 770 (254s Coaldale) | 2020-11-10 07:00 | 2020-11-19 17:00 | N | N | replace existing line protections | Line, Circuit Breaker | 770L (254s Coaldale - 370s North Lethbridge) | 370s: To replace existing line protections, breaker control and protection and CVT10 distribution module. 254s: To replace existing line protections | For Information Only, Pre-Condition
ALTALINK | 452L (367s Harry Smith - 434s Stony Plain) | 2020-11-10 07:00 | 2020-11-10 18:00 | N | N | counter weight install on 452L39 | Line | 452L (367s Harry Smith - 434s Stony Plain) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 786L (799s Coleman - BCH Natal) | 2020-11-10 07:15 | 2020-11-10 17:45 | N | Y | urgent repair structure 95 | Line |  | *P5 786L Urgent Repair structure 95 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
SUNCOR | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island, 29EDD-1 29EDD1s1152 (29EDD-1 Millennium), 29EDD-1 29EDD1s1252 (29EDD-1 Millennium) | 2020-11-10 08:00 | 2020-11-20 18:00 | N | N | maintenance | Line, Circuit Breaker | 29PL6-6 (29EDD-1 Millennium - 29EDD-2 Tar Island, 29EDD-1 29EDD1s1152 (29EDD-1 Millennium) |  | Contingency Requires Mitigation, For Information Only
ALTALINK | 535s T3 (535s Joffre) | 2020-11-10 08:15 | 2020-11-10 17:45 | N | N | qualitrol replacement | Transformer | 535s T3 (535s Joffre) |  | For Information Only
ALTALINK | 463L (15s Fort Macleod - 463AL), 15s 463 (15s Fort Macleod) | 2020-11-10 09:30 | 2020-11-10 15:30 | N | Y | tie in CT circuits to new 166RAS relays | Line, Circuit Breaker | 15s 463 (15s Fort Macleod), 463L (15s Fort Macleod - 463AL) | Outage on 15s463 (Breaker 1052) to tie in CT circuits to new 166RAS relays.. | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ATCO | 6L15 (763s Hanna - 775s Sullivan Lake) | 2020-11-10 10:00 | 2020-11-10 16:00 | N | N | inter phase spacers work | Line | 6L15 (763s Hanna - 775s Sullivan Lake) | 6L15 Inter phase spacers | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 666L (28s West Brooks - 498s Tilley), 498s 138 kV bus 1 (498s Tilley), 498s C1 (498s Tilley), 498s T1 (498s Tilley) | 2020-11-10 11:00 | 2020-11-13 18:00 | N | N | install 138 kV bus 'B' protection and commission 'A' protection | Line, Bus, Shunts, Transformer |  | Install 138kV BUS 'B' protectiong and commission 'A' Protection.Fortis DG generation call down required. Redundant protection in place. UV Ras scheme will be OOS for duration of outage. | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ATCO | 6L56 (763s Hanna - 802s Michichi Creek) | 2020-11-11 08:00 | 2020-11-11 16:00 | N | N | installing inter-phase spacers | Line | 6L56 (763s Hanna - 802s Michichi Creek) | Installing inter-phase spacers | Over/Under Voltage, Pre-Condition
ENMAX | 162.4TR (162s Beddington) | 2020-11-11 08:00 | 2020-11-13 16:00 | N | N | RTU & line protection upgrade - settings changes | Transformer | 162.4TR (162s Beddington) | RTU & Line Protection Upgrade. Settings changes. | For Information Only
ALTALINK | 20s 452 (20s Ghost), 418L (20s Ghost - 189L tap) | 2020-11-12 06:30 | 2020-11-12 17:30 | N | N | sync check changes | Circuit Breaker, Line |  |  | For Information Only, Pre-Condition, Affects Cranking Path
EPCOR, ALTALINK | 330p 807 (330p Genesee), 430L (330P Genesee - 510S Sunnybrook) | 2020-11-12 07:00 | 2020-11-12 17:00 | N | Y | cutover of new DFR @ Genesee S/S | Circuit Breaker, Line | 430L (330P Genesee - 510S Sunnybrook), 330p 807 (330p Genesee) | cutover of new DFR @ Genesee S/S | For Information Only
ENMAX | 5.5TR (ENMAX 5) | 2020-11-12 08:00 | 2020-11-14 18:00 | N | N | install NGR | Transformer | 5.5TR (ENMAX 5) |  | For Information Only
ENMAX | 2B138-D83 (ENMAX 2), 2B138-D84 (ENMAX 2), 2.81L (ENMAX 2 - ENMAX 9) | 2020-11-12 08:00 | 2020-11-13 16:00 | N | N | minor maintenance GIS 2B138-D84 | Circuit Breaker, Line | 2.81L (ENMAX 2 - ENMAX 9) | GIS Minor Maintenance 2B138-D84. GIS Switch Maintenance 2MD85_85G, 2MD86_86G, 2MD138-2.81_2.81G, 2SW2.81G | Contingency Requires Mitigation, Pre-Condition
ALTALINK | 20s 150 (20s Ghost), 150L (20s Ghost - 150AL) | 2020-11-13 06:30 | 2020-11-13 17:30 | N | N | sync check changes | Circuit Breaker, Line |  |  | For Information Only, Pre-Condition
EPCOR | 330p 809 (330p Genesee), 330p 1203 (330p Genesee), 330p 1206 (330p Genesee), 330p 1209 (330p Genesee), 330P 12TC2 (330p Genesee) | 2020-11-13 07:00 | 2020-11-13 17:00 | N | Y | cutover of new DFR @ Genesee S/S | Circuit Breaker, Transformer | 330p 809 (330p Genesee), 330p 1203 (330p Genesee), 330p 1206 (330p Genesee), 330p 1209 (330p Genesee), 330P 12TC2 (330p Genesee) |  | 500 kV, Contingency Requires Mitigation
EPCOR | 987s GDS3 (987s Cloverbar) | 2020-11-13 07:00 | 2020-11-17 10:00 | N | Y | maintenance | Switch |  |  | Restricts Generation
ALTALINK | 17s 995N (17s Benalto), 995L (17s Benalto - 995AL) | 2020-11-13 14:30 | 2020-11-13 16:30 | N | Y | commission new 17s13 breaker | Switch, Line | 17s 995N (17s Benalto), 995L (17s Benalto - 995AL) | 1.5 Hour outage to 995L (Open at 17s) is required in order to test energize new 17s13 Breaker via 17s12. ACC Issue 17s995N Advice then open 17s12 to Commission New 17s13 Breaker | 240 kV, Contingency Requires Mitigation, Affects Cranking Path
EPCOR | 665s T1 (665s Dome) | 2020-11-16 07:00 | 2020-11-19 17:00 | N | Y | transformer Calisto repair | Transformer | 665s T1 (665s Dome) |  | 240 kV, For Information Only
ALTALINK | 729L (285s East Camrose - 542s Ervick), 285s East Camrose 138kV Partial Bus, 285s T2 (285s East Camrose) | 2020-11-16 07:00 | 2020-11-16 18:00 | N | N | remove 285s91 | Line, Bus, Transformer | 285s East Camrose 138kV Partial Bus |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
EPCOR | T3 (Meadowlark), 72MG16 (Garneau - Meadowlark), M723 (Meadowlark), M724 (Meadowlark) | 2020-11-16 07:00 | 2020-11-27 17:00 | N | N | disconnect and VT replacement | Transformer, Line, Circuit Breaker | T3 (Meadowlark) |  | Firm Load Loss, Pre-Condition
EPCOR | T2 (EPCOR Riverview), RW2403 (EPCOR Riverview), RW2402 (EPCOR Riverview) | 2020-11-16 07:00 | 2020-11-20 17:00 | N | Y | switch and riser repair/commissioning | Transformer, Circuit Breaker | T2 (EPCOR Riverview) |  | 240 kV, Contingency Requires Mitigation
ATCO | 790s 703T (790s Poplar Hill), 790s 704 (790s Poplar Hill) | 2020-11-16 08:00 | 2020-11-25 17:00 | N | Y | protection upgrades | Transformer, Circuit Breaker | 790s 703T (790s Poplar Hill) | Protection upgrades | Pre-Condition, Restricts Generation
ENMAX | 65.1TR (ENMAX 65) | 2020-11-16 08:00 | 2020-11-24 09:00 | N | Y | online monitoring installation | Transformer | 65.1TR (ENMAX 65) |  | 240 kV, Contingency Requires Mitigation
ATCO | ERV1 Rycroft Battery | 2020-11-16 08:00 | 2020-12-07 16:00 | N | N | P2214 - 730s Rycroft battery 20 MW DER, ISD Nov 30, 2020 | Unit
EPCOR | 665s T3 (665s Dome), 72DS26 (Dome - Strathcona) | 2020-11-16 08:00 | 2020-11-30 16:00 | N | N | P1659 ISD Nov 23, 2020 | Transformer, Line
EPCOR | 72RS5 (Rossdale - Strathcona) | 2020-11-16 08:00 | 2020-11-18 16:00 | N | N | Decommission Sept 30, 2020 | Line
ENMAX | 1.85L (ENMAX 1 - ENMAX 8), 8B138-1A0 (ENMAX 8), 8B138-2A0 (ENMAX 8) | 2020-11-16 08:00 | 2020-11-20 16:00 | N | N | GIS switch maintenance | Line, Circuit Breaker | 1.85L (ENMAX 1 - ENMAX 8) | GIS Switch maintenance 8SW1A52, 8SW2A52, 8SW2A51, 8SW1A01, 8SW1A8, 8SW1A2, 8SW2A1, 8SW1A10, Don not operate or ground 8SW1A51 | Contingency Requires Mitigation, Firm Load Loss
ENMAX | 24.1TR (ENMAX 24) | 2020-11-16 08:00 | 2020-11-30 16:00 | N | N | protection upgrade | Transformer |  | 24.1TR Protection upgrade. | For Information Only
ENMAX | 2.2TR (ENMAX 2) | 2020-11-16 08:00 | 2020-11-17 16:00 | N | N | GIS switch maintenance | Transformer |  | GIS Minor Maintenance 2B138-D87. 2B138-D86. GIS Switch Maintenance 2MD91_91G, 2MD92_92G, 2SW2.2TRG, 2MD138-2.2TR_2.2TRG. 2SW516_516G | For Information Only
ENMAX | 162.3TR (162s Beddington), 162s 138-RB85 (162s Beddington), 162s 138-RB86 (162s Beddington) | 2020-11-16 08:00 | 2020-11-17 16:00 | N | N | RTU & line protection upgrade -settings changes, oil sampling MT, TC, filmax maintenance | Transformer, Circuit Breaker | 162.3TR (162s Beddington) | RTU & Line Protection Upgrade. Settings changes. Oil sampling MT, TC. Filmax maint. | Contingency Requires Mitigation
ATCO | 790s 701C (790s Poplar Hill) | 2020-11-16 08:00 | 2020-11-25 16:00 | N | N | protection & SCADA upgrade outage on 701C | Shunts | 790s 701C (790s Poplar Hill) | 790S Poplar Hill Protection & SCADA Upgrade Outage on 701C | Contingency Requires Mitigation, Over/Under Voltage, Pre-Condition
ALTALINK | 821L (158s Vauxhall - 421s Hays) | 2020-11-16 08:15 | 2020-11-22 17:45 | N | N | bird flight marker installation (str 52-192) | Line | 821L (158s Vauxhall - 421s Hays) | Bird Flight Marker installation (str 52-192) | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 2L112 (Boundary - Nelway) | 2020-11-16 09:00 | 2020-11-18 17:00 | N | Y | BCH disconnect inspections, BC maintenance does not affect the Alberta ATC | Line | 2L112 (Nelway - Boundary), NLY 2D24, 2D2CB7 OOS | bpa outage/disconnect maintenance BCH disconnect inspections, BC maintenance does not affect the Alberta ATC | 240 kV, Limits ATC
ALTALINK | 17s Benalto 240 kV South Bus 2, 17s T2 (17s Benalto), 17s C1 (17s Benalto) | 2020-11-16 09:30 | 2020-11-20 17:00 | N | Y | replace 240B2 (south bus) strain insulators, replace 1ph bus CVT 17s191 | Bus, Transformer, Shunts | 17s 13 (17s Benalto), 17s 4 (17s Benalto), 17s 1652 (17s Benalto), 17s 9 (17s Benalto), 17s 85 (17s Benalto), 17s T2 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 396s T3 (396s Pincher Creek) | 2020-11-16 10:39 | 2020-11-16 23:00 | N | N | forced outage due to bird contact | Transformer
ALTALINK | 266s 1038L FSC (266s SC1) | 2020-11-16 10:45 | 2020-11-19 17:45 | N | Y | FAC501 yearly maintenance | Shunts | 266s 1038L FSC (266s SC1) | FAC501 yearly maintenance | 240 kV, For Information Only, Pre-Condition
ALTALINK | 65s T2 (65s High River) | 2020-11-16 11:00 | 2020-11-19 17:30 | N | N | bushing monitors and LV LA replacement | Transformer | 65s T2 (65s High River) | 65sT2 bushing monitors and LV LA replacement | For Information Only
ALTALINK | 421s 821W (421s Hays), 821L (158s Vauxhall - 421s Hays) | 2020-11-16 12:30 | 2020-11-20 16:30 | N | N | 421s 821L A/B protection upgrade | Circuit Breaker, Line | 421s 821W (421s Hays), 821L (158s Vauxhall - 421s Hays) |  | For Information Only
ALTALINK | 728L (353s Plamondon - 405s Waupisoo) | 2020-11-17 07:00 | 2020-11-20 18:00 | N | N | replacing structure #189 and maintenance on structures #197 & 198 | Line | 728L (353s Plamondon - 405s Waupisoo) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 225L (229s Glenwood - 385s Spring Coulee) | 2020-11-17 07:15 | 2020-11-19 19:45 | N | N | replacing structure 467, salvaging structure 468 and modifying structure 469 | Line | 225L (229s Glenwood - 385s Spring Coulee) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 122s T1 (122s Alberta Newsprint) | 2020-11-17 07:45 | 2020-11-18 16:30 | N | Y | investigate metering value issue | Transformer | 122s T1 (122s Alberta Newsprint) |  | 240 kV
ENMAX | 31.1TR (ENMAX 31) | 2020-11-17 08:00 | 2020-11-19 16:00 | N | N | NGR installation | Transformer | 31.1TR (ENMAX 31) |  | For Information Only
Syncrude, ATCO | RL1 (848s Ruth Lake - D05 Syncrude), 848s 910 (848s Ruth Lake), 848s 911 (848s Ruth Lake), D05 516 (D05 Syncrude), D05 517 (D05 Syncrude) | 2020-11-17 08:00 | 2020-11-19 20:00 | N | Y | 5 Yr PM for RL-1 | Line, Circuit Breaker |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK, ATCO | 347s 3 (347s Fox Creek), 199L (347s Fox Creek - 741s Fox Creek), 7L199 (347s Fox Creek - 741s Fox Creek) | 2020-11-17 08:00 | 2020-11-25 01:44 | N | N | cross arm changes for ATCO | Switch, Line | 7L199 (347s Fox Creek - 741s Fox Creek) |  | For Information Only
ATCO | 7L199 (347s Fox Creek - 741s Fox Creek) | 2020-11-17 08:00 | 2020-11-25 01:44 | N | Y | X-arms changes | Line | 7L199 (347s Fox Creek - 741s Fox Creek) | 7L199 OOS for X-ARMS changes | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 744L (207s Pinedale - 228s T.M.P.L.Niton) | 2020-11-17 08:00 | 2020-11-18 18:00 | N | N | P5 replace damaged arm - str 744L346 | Line | 744L (207s Pinedale - 228s T.M.P.L.Niton) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 13.82L (ENMAX 13 - ENMAX 22) | 2020-11-17 08:00 | 2020-11-20 16:00 | N | N | centre phase CT is leaking oil | Line | 13.82L (ENMAX 13 - ENMAX 22) |  | Creates Radial Feeds, Firm Load Loss
ATCO | PEC1 Lindbergh | 2020-11-17 10:00 | 2020-11-17 11:00 | N | N | due to ATCO's Moose Hill telecom work | Unit
ALTALINK | 418s Ardenville RTU/SCADA | 2020-11-17 12:00 | 2020-11-17 16:00 | N | N | reboot DVAr relay | Terminal Equipment |  |  | Affects Visibility
AESO-SC | OATI | 2020-11-17 18:00 | 2020-11-17 19:00 | N | N | perform an Inter-Site Transfer business continuity drill | SCInternal |  |  | For Information Only
EPCOR | 987s GDS2 (987s Cloverbar) | 2020-11-18 07:00 | 2020-11-23 10:00 | N | Y | CPC Requested Isolation | Switch | 987s GDS2 (987s Cloverbar) |  | Restricts Generation
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-11-18 07:30 | 2020-11-19 17:30 | Y | Y | BCH conducting blasting work in the vicinity of 1L274 | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Limits ATC, Pre-Condition
ATCO | 749s 701T (749s Flyingshot Lake) | 2020-11-18 08:00 | 2020-11-18 17:00 | N | N | hot spot repair on 701T | Transformer |  | Hot spot repair on 701T. | For Information Only
ENMAX, ALTALINK | 932L (74s Janet - 162s Beddington) | 2020-11-18 08:00 | 2020-11-20 16:00 | N | Y | RTU & line protection upgrade settings changes | Line | 932L (74s Janet - 162s Beddington) |  | 240 kV,Affects Cranking Path
ENMAX | 15.1TR (ENMAX 15) | 2020-11-18 08:00 | 2020-11-19 16:00 | N | N | neutral reactor install, perform connections to the NGR and energize | Transformer | 15.1TR (ENMAX 15) | 15 Sub Neutral Reactor Install (15.1 TR & 15.2 TR). Perform connections to the NGR and energize. | For Information Only
ENMAX | 15.60L (ENMAX 15 - ENMAX 21) | 2020-11-18 08:00 | 2020-11-18 16:00 | N | N | 15 Sub neutral reactor install | Line | 15.60L (ENMAX 15 - ENMAX 21) | 15 Sub Neutral Reactor Install (15.1 TR & 15.2 TR). Erecting steel | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.4TR (ENMAX 2) | 2020-11-18 08:00 | 2020-11-19 16:00 | N | N | GIS switch maintenance | Transformer |  | GIS Minor Maintenance 2B138-D95, 2B138-D94. GIS Switch Maintenance - 2SW2.4TRG, 2MD138-2.4TR_2.4TRG, 2MD108_108G, 2MD107_107G, 2SW503_503G | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-11-18 08:00 | 2020-11-24 18:00 | N | N | 29PL6-34 & 29PP-70E | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ATCO | 7L760 (767s Oyen - 7L760D2), 767s 702 (767s Oyen) | 2020-11-18 08:00 | 2020-11-18 19:00 | N | Y | Test & Operate to commissioning Cavendish substation (P865), Test & Operate to commissioning Cavendish substation (P865) | Line, Circuit Breaker | P0865 V.Chan 11/4/2020. | Test & Operate to commissioning Cavendish substation trip relays to 767S Oyen, On return to normal will take an outage to 7L760 & 7LA760 to do close new switch 7LB760D1 to tie in new Cavendish tap off. This will take a maximum of two hours. Return to normal Sequence: Release T&O permit at 767S Oyen Open 914S Bindloss Breaker 701 Open Line switch 7L760D3 Confirm 7LB760D2 @ 893S Cavendish Open and COG issued for construction Close 7LB760D1 @ Cavendish tap Close 7L760D1 @ 767S Oyen substation Close Bkr 702 @ 767S Oyen substation Commissioning to verify Voltage and rotations on line PTs at Cavendish tap Close 914S Bindloss Breaker 701 Close Line switch 7L760D3 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 62s T3 (62s Brazeau) | 2020-11-18 09:00 | 2020-11-19 09:00 | N | Y | maintenance | Transformer | 62s T3 (62s Brazeau) |  | For Information Only
Lethbridge, ALTALINK | 172L (181s Chinook - 370s North Lethbridge), 370s 175 (370s North Lethbridge) | 2020-11-18 12:00 | 2020-11-18 16:00 | N | N | Trip test 370s175 (Breaker 552) | Line, Circuit Breaker |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Restricts Generation
ALTALINK, Lethbridge | 207L (111s Coalbanks - 370s North Lethbridge) | 2020-11-19 07:30 | 2020-11-19 11:30 | N | Y | 370s207X breaker testing | Line | 370s 207X (370s North Lethbridge), 207L (111s Coalbanks - 370s North Lethbridge) | Trip test 370s207X (Breaker 652) initiated by 370s770E (752) Breaker Fail Protection. | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 744L (228s T.M.P.L.Niton - 744AL) | 2020-11-19 09:00 | 2020-11-19 16:00 | N | N | P5 replace damaged arm - Str 744L206 | Line | 744L (228s T.M.P.L.Niton - 744AL) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 62s T5 (62s Brazeau) | 2020-11-19 09:00 | 2020-11-19 11:00 | N | Y | load reading test on 62s T3 | Transformer | 62s T5 (62s Brazeau) | 62s T3 needs to be put into service to take load readings | 240 kV, Contingency Requires Mitigation, Overload, Pre-Condition, Restricts Generation
ENMAX | 28.2TR (ENMAX 28) | 2020-11-20 07:00 | 2020-11-20 16:00 | N | N | repair shutters on 28BB8-28.2TR cell | Transformer |  | Repair shutters on 28BB8-28.2TR cell. | For Information Only
ENMAX | 15.2TR (ENMAX 15) | 2020-11-20 08:00 | 2020-11-20 16:00 | N | N | neutral reactor install, perform connections to the NGR and energize | Transformer | 15.2TR (ENMAX 15) | 15 Sub Neutral Reactor Install (15.1 TR & 15.2 TR). Perform connections to the NGR and energize. | For Information Only
ENMAX | 2.2TR (ENMAX 2) | 2020-11-20 08:00 | 2020-11-22 16:00 | N | N | NGR installation | Transformer | 2.2TR (ENMAX 2) |  | For Information Only
Syncrude | MH1 (Aurora - Aurora), 23 (Aurora), 24 (Aurora) | 2020-11-20 08:00 | 2020-11-23 20:00 | N | N | Poweline Outage - G01 Substation, Poweline Outage - G01 Substation | Line, Circuit Breaker | MH1 (Aurora - Aurora) | MH1 72kV Poweline Outage - G01 Substation Following Circuit Breakers will be operated: 23, 24 Following MOD will be operated: 27 | For Information Only
Syncrude | RL2 (848s Ruth Lake - D05 Syncrude) | 2020-11-20 08:00 | 2020-11-22 20:00 | N | Y | 5 year PM | Line | RL2 (848s Ruth Lake - D05 Syncrude) | Significant Outage: 260KV, 5 Yr PM RL-2 Following Circuit Breakers will be operated: 512, 513 (D05 Sub.) 902, 907 (Ruth Lake Sub.) Following MOD's will be operated: 512B, 513B, 515 (D05 Sub.) 902A, 907A, RL-2D1 (Ruth Lake Sub.) | 240 kV, Contingency Requires Mitigation, Pre-Condition, Affects Cranking Path
ALTALINK | 3L (245s Seebe - 3AL) | 2020-11-20 08:30 | 2020-11-20 11:00 | N | N | create open point 'A' (between Str 3L145 and JCT 3L46/3AL0) | Line |  | Create Open Point 'A' (between Str 3L145 and JCT 3L46/3AL0). Required for Emergency Repair: 3L145 (43s loads to remain online) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 3L (245s Seebe - 3AL) | 2020-11-20 11:05 | 2020-11-20 15:00 | N | N | emergency repair: 3L145 airbrake requires adjustment | Line |  | Emergency Repair: 3L145 airbrake requires adjustment. (43s loads to remain online) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 3L (245s Seebe - 3AL) | 2020-11-20 15:00 | 2020-11-20 17:30 | N | N | close open point 'A' (between Str 3L145 and JCT 3L46/3AL0) | Line |  | Close Open Point 'A' (between Str 3L145 and JCT 3L46/3AL0). Required for Emergency Repair: 3L145. (43s loads to remain online) | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition, Affects Cranking Path
ENMAX | 7.84L (ENMAX 7 - ENMAX 36) | 2020-11-21 07:00 | 2020-12-03 16:00 | N | N | Broadcast Hill project, relocating structures 11 to 16, phasing required | Line | 7.84L (ENMAX 7 - ENMAX 36) |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 3.84L (ENMAX 3 - ENMAX 13) | 2020-11-21 08:00 | 2020-12-02 16:00 | N | N | Hitachi HV breaker overhaul 13B138-3.84 | Line | 3.84L (ENMAX 3 - ENMAX 13) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 37s 726E (37s North Calder), 726L (37s North Calder - 71s Lamoureux) | 2020-11-22 07:00 | 2020-11-24 17:30 | N | N | adding supervisory control of the reclosing | Circuit Breaker, Line | 37s 726E (37s North Calder), 726L (37s North Calder - 71s Lamoureux) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 951L (132s Ware Junction - 275s Jenner) | 2020-11-23 07:15 | 2020-11-29 17:45 | N | Y | completion of urgent repair, splicing conductor over coulee crossing between structures 41-42. | Line | 951L (132s Ware Junction - 275s Jenner) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ENMAX | 8B138-2A0 (ENMAX 8), 8B138-3A0 (ENMAX 8), 8.5TR (ENMAX 8), 8.6TR (ENMAX 8) | 2020-11-23 08:00 | 2020-11-27 16:00 | N | N | maintenance on GIS switches | Circuit Breaker, Transformer | 8.5TR (ENMAX 8), 8.6TR (ENMAX 8) | GIS Switch maintenance 8SW2A02, 8SW2A52, 8SW2A10, 8SW2A82, 8SW3A51, 8SW2A01, 8SW3A1. Check Reversing Switch 8.6TR, 8.5TR. Do not maintain or ground 8SW2A51 or 8SW3A52. | Contingency Requires Mitigation, Pre-Condition
ENMAX | 11.1TR (ENMAX 11) | 2020-11-23 08:00 | 2020-11-25 16:00 | N | N | install NGR | Transformer | 11.1TR (ENMAX 11) |  | For Information Only
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2020-11-23 08:00 | 2020-11-27 16:00 | N | N | drilling wells directly under line | Line |  | 34.2TR & 34.3TR Replacement-Grounding Study. Drilling wells directly under line. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 72VN21 (511s Victoria - Namao) | 2020-11-23 09:30 | 2020-11-27 14:00 | N | N | Line Maintenance & Upgrades | Line | 72VN21 (511s Victoria - Namao) |  | Creates Radial Feeds, Firm Load Loss
EPCOR | 1139L (367s Harry Smith - EPCOR Riverview) | 2020-11-23 09:30 | 2020-11-27 17:00 | N | Y | switch repair | Line | 1139L (367s Harry Smith - EPCOR Riverview) |  | 240 kV
ALTALINK | 180L (255s Vulcan - 928s East Stavely), 255s 34 (255s Vulcan) | 2020-11-23 09:30 | 2020-11-27 16:30 | N | N | implement and test new RAS scheme | Line, Circuit Breaker | 255s 34 (255s Vulcan), 180L (255s Vulcan - 928s East Stavely) | Outage on 255s34 to implement and test new RAS scheme. Line protection relays will be taken out of service at the same time. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 244s 3252 (244s Bowmanton), 244s 3152 (244s Bowmanton), 879L (244s Bowmanton - 368s Burdett) | 2020-11-23 09:45 | 2020-11-23 15:45 | N | Y | investigate why motor mech isn't working on 244s879 | Circuit Breaker, Line | 879L (244s Bowmanton - 368s Burdett) |  | Restricts Generation
ALTALINK | 17s 11 (17s Benalto) | 2020-11-23 10:00 | 2020-11-28 11:30 | N | Y | replace 17s11 breaker fail and control module | Circuit Breaker | 17s 11 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2020-11-23 10:00 | 2020-11-30 16:00 | N | Y | replacement of under rated and rotten crossarms | Line | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | Replacement of under rated and rotten crossarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation,Affects Cranking Path
ALTALINK | 55s T2 (55s Olds) | 2020-11-23 11:15 | 2020-12-03 17:45 | N | N | oil reclamation | Transformer | 55s T2 (55s Olds) |  | For Information Only
ALTALINK | 266s 1037L FSC (266s SC1) | 2020-11-23 11:30 | 2020-11-26 18:00 | N | Y | perform PRC005 maintenance on the relays | Shunts | 266s 1037L FSC (266s SC1) | Techs are required to perform PRC005 Maintenance on the following relays: FSC1 A7/50/51/60/64/81/86/96/FSC1 MVME41 FSC1 B7/50/51/60/64/81/86/96/FSC1 MVME41 | 240 kV, Pre-Condition
ALTALINK | 427L (63s Red Deer - 247s Piper Creek) | 2020-11-23 12:30 | 2020-12-04 17:30 | N | N | replace A and B line protections at 247s | Line | 427L (63s Red Deer - 247s Piper Creek) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
ALTALINK | 701L (223s Strome - 7LA701 tap) | 2020-11-24 07:00 | 2020-11-26 18:00 | N | Y | P5 repair broken strands structures 340, 370, 371 | Line | 701L (223s Strome - 7LA701) | Urgent request | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage
ALTALINK | 835L (283s Violet Grove - 835AL) | 2020-11-24 07:00 | 2020-11-25 16:00 | N | N | P5 replace both dead-end spars and all insulation on 835L34 | Line | 835L (283s Violet Grove - 835AL) |  | Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ALTALINK | 2s T1 (2s Kananaskis), 87L (2s Kananaskis - 245s Seebe) | 2020-11-24 07:00 | 2020-11-26 14:45 | N | Y | 138kV VT replacement and 87L maintenance (str 6, 16) | Transformer, Line | 2s T1 (2s Kananaskis), 87L (2s Kananaskis - 245s Seebe) | 138kV VT Replacement, coordinated with planned TAU generation outage. 2nd Scope: 87L maintenance (str 6, 16) | Restricts Generation
EPCOR | T1 (Woodcroft) | 2020-11-24 07:00 | 2020-11-24 17:00 | N | N | transducer removal | Transformer | T1 (Woodcroft) |  | For Information Only
ALTALINK | 675L (244s Bowmanton - 321s Al Rothbauer) | 2020-11-24 07:15 | 2020-11-25 17:45 | N | Y | scope of work includes maintenance on str 150 and 153 shared towers with 880L | Line | 675L (244s Bowmanton - 321s Al Rothbauer) |  | Creates Radial Feeds, Affects Cranking Path
ALTALINK | 102s SVC (102s Langdon) | 2020-11-24 07:30 | 2020-11-26 18:00 | N | Y | cooling system issue - investigative 102s SVC stop sequence and 7189 - investigate and correct logic issues | Shunts | 102s SVC (102s Langdon) | 102s SVC Cooling system issue - investigative 102s SVC Stop sequence and 7189 - investigate and correct logic issues with breakers 555, 252 and airbrake 7189 102sT4 transfix service alarm Stnd Mnt 00102s A87/T4 URT60 Tr(Tx Relay Maintenance) Stnd Mnt 00102s B87/T4 SEL387-5 Tr (Tx Relay Maintenance) Replace ABB HMI SVC Computers at site. | 240 kV, Pre-Condition
ENMAX, ALTALINK | 771L (162s Beddington - ENMAX 47), ENMAX 47 | 2020-11-24 08:00 | 2020-11-26 18:00 | N | N | RTU & line protection upgrade | Line, Station | 771L (162s Beddington - ENMAX 47), 47.1TR (ENMAX 47), 47.2TR (ENMAX 47) | RTU & line protection upgrade. Settings changes. Transfer Protection on 771L at #47 Sub from JMUX to JPAX system. HV SW maint SW84, SW85 at 162sub. Backfeed 47s sstr from 25kV bus. Original Outage Nov 9-10 | Pre-Condition
CMH | MH-10L (MHS10 - MHS8 Burnside), MH-9L (MH69s2 North Industrial - MHS10), MHS-10 | 2020-11-24 08:00 | 2020-12-23 16:00 | N | N | P2151 ISD Dec 16, 2020 | Line, Station
Syncrude | MH2 (Aurora - Aurora), 33 (Aurora), 34 (Aurora) | 2020-11-24 08:00 | 2020-11-27 20:00 | N | N | maintenance | Line, Circuit Breaker | MH2 (Aurora - Aurora) | MH2 72kV Poweline Outage - G01 Substation Following Circuit Breakers will be operated: 33, 34 Following MOD will be operated: 37 | For Information Only
ALTALINK | 65s 434(65s Highriver), 434L (65s High River - 237s Foothills) | 2020-11-24 08:30 | 2020-11-24 17:30 | N | N | replace tank heater | Circuit Breaker, Line | 65s 434(65s Highriver), 434L (65s High River - 237s Foothills) |  | Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ATCO | 715s 701T (715s Leming Lake) | 2020-11-24 08:30 | 2020-11-24 15:30 | N | N | repair leaking union on conservator piping, and inspect/repair hotspot on 501TD | Transformer |  | Repair Leaking union on Conservator Piping, and inspect/repair hotspot on 501TD | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-11-25 08:00 | 2020-12-01 18:00 | N | N | 29PP-12 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ALTALINK, ATCO | 69s North Barrhead 240kV Bus, 913L (69s North Barrhead - 338s Cherhill), 9L913 (69s North Barrhead - 732s Mitsue) | 2020-11-25 08:00 | 2020-11-27 17:00 | N | Y | replace structure 142F | Bus, Line | 913L (69s North Barrhead - 732s Mitsue), 913L (69s North Barrhead - 338s Cherhill) |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition, Affects Cranking Path
ALTALINK | 267s T1 (267s Killarney Lake) | 2020-11-25 08:00 | 2020-11-25 18:00 | N | N | replace switch 267s13, also hotspot repairs on 267s11, 267s12, & 267s9, & T1 TX18650 leak on XO bushing | Transformer |  |  | For Information Only
ALTALINK | 156L (235s Entwistle - 156BL), 235s 156E (235s Entwistle) | 2020-11-25 09:00 | 2020-11-25 17:30 | N | N | replace strain insulators on 156L | Line, Circuit Breaker | 156L (235s Entwistle - 156BL) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 741s 701 (741s Fox Creek), 7L90 (741s Fox Creek - 7L90D3) | 2020-11-25 10:00 | 2020-11-25 14:00 | N | N | emergency breaker repair due to low SF6 | Circuit Breaker, Line | 7L90 (741s Fox Creek - 7L90D3) |  | Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition
ALTALINK | 62s 11 (62s Brazeau) | 2020-11-25 23:00 | 2020-11-26 03:00 | N | Y | maintenance | Switch | 62s 11 (62s Brazeau) |  | 240 kV, Restricts Generation
EPCOR | T3 (Woodcroft) | 2020-11-26 07:00 | 2020-11-26 17:00 | N | N | transducer removal | Transformer | T3 (Woodcroft) |  | For Information Only
ENMAX | 11.2TR (ENMAX 11) | 2020-11-26 08:00 | 2020-11-28 16:00 | N | N | NGR installation | Transformer | 11.2TR (ENMAX 11) |  | For Information Only, Pre-Condition
Syncrude | 11 (Aurora), T1 (Aurora), 21 (Aurora), 31 (Aurora), 211 (Aurora), 221 (Aurora) | 2020-11-26 08:00 | 2020-12-07 20:00 | N | Y | transformer maintenance | Circuit Breaker, Transformer |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK | 1075L (28s West Brooks - 132s Ware Junction) | 2020-11-27 07:00 | 2020-11-27 18:00 | N | Y |  | Line | 1075L (28s West Brooks - 132s Ware Junction) |  | 240 kV, For Information Only, Affects Cranking Path
ALTALINK | 17s 26 (17s Benalto) | 2020-11-27 08:00 | 2020-11-27 10:00 | N | Y | trip test 17s6 from new s11 breaker fail | Switch | 17s 26 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation
Syncrude | Mildred T15 (Syncrude Mildred Lake), Mildred Lake 1535 (Syncrude Mildred Lake) | 2020-11-27 08:00 | 2020-12-10 20:00 | N | N | maintenance | Transformer, Circuit Breaker | Mildred T15 (Syncrude Mildred Lake), Mildred Lake 1535 (Syncrude Mildred Lake) | T15 Transformer 72/13.8KV - Plant 31 Powerhouse T15 Transformer 72/13.8KV - Plant 31 Powerhouse Following Circuit Breaker will be operated: Breaker 1535 (Plant 31 Powerhouse) Following switch will be operated: 1534 (Plant 31 Powerhouse)- Following Circuit Breaker will be operated: Breaker 1535 (Plant 31 Powerhouse) Following switch will be operated: 1534 (Plant 31 Powerhouse)
ALTALINK | 17s 29 (17s Benalto) | 2020-11-27 10:00 | 2020-11-27 12:00 | N | Y | trip test 17s7 from new s11 breaker fail | Switch | 17s29 - Advice |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 17s 31 (17s Benalto) | 2020-11-27 12:00 | 2020-11-27 15:00 | N | Y | trip test 17s1 from new s11 breaker fail | Switch | 17s 31 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
ALTALINK | 17s 42 (17s Benalto) | 2020-11-27 15:00 | 2020-11-27 18:00 | N | Y | trip test 17s10 from new s11 breaker fail | Switch | 17s 42 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | T2 (Strathcona) | 2020-11-27 17:00 | 2020-11-29 17:00 | N | N | bus work on line side of S8 feeder breaker | Transformer | S8 Feeder Repair | Bus 2 outage request to develop repair scope for buswork on LINE side of S8 breaker. | For Information Only
ALTALINK | 931L (28s West Brooks - 132s Ware Junction) | 2020-11-28 07:00 | 2020-11-28 18:00 | N | Y | maintenance on structure 7 | Line | 931L (28s West Brooks - 132s Ware Junction) | Scope of work includes maintenance on structure 7, also require a reclose block on 1075L. | 240 kV,Affects Cranking Path
ALTALINK | 89s 252 (89s Ellerslie), 89s T1 (89s Ellerslie), 89s Ellerslie 240kV Bus 1 | 2020-11-28 08:00 | 2020-11-29 18:00 | N | Y | 89s1 switch repair | Circuit Breaker, Transformer, Bus | 89s T1 (89s Ellerslie), 89s Ellerslie 240kV Bus 1 |  | 500 kV, Contingency Requires Mitigation, Overload, Pre-Condition
ALTALINK | 17s 2852 (17s Benalto), 17s T3 (17s Benalto) | 2020-11-28 08:00 | 2020-11-28 11:00 | N | Y | trip test 17s2852 from new s11 breaker fail | Circuit Breaker, Transformer | 17s 46 (17s Benalto), 17s T3 (17s Benalto) |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-11-28 08:00 | 2020-12-08 18:00 | N | N | 29PP-37C, 29PP-37B, 29PP-37A, 652-3701, 652-3702, 652-3703, 652-3704 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-11-28 08:00 | 2020-12-07 18:00 | N | N | 29-652-7010, 29-652-7020, 29-652-7030, 29-652-7040, 29-652-7050, 29-652-7060 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
SUNCOR | Unmodeled Transmission Facility (Suncor) | 2020-11-28 08:00 | 2020-12-04 18:00 | N | N | 452-9001, 652-9102, 652-9003T, 30PP-91, 29PP-70B, 30PP-90, 29PT280, 29PT281 | Not In Model | Unmodeled Transmission Facility (Suncor) |  | For Information Only
ALTALINK | 17s 12 (17s Benalto) | 2020-11-28 12:00 | 2020-11-28 15:00 | N | Y | trip test 17s12 from new s11 breaker fail | Circuit Breaker | 17s58 |  | 240 kV, Contingency Requires Mitigation, Pre-Condition
EPCOR | 1164L (816s Petrolia - EPCOR Riverview) | 2020-11-30 07:00 | 2020-12-04 17:00 | N | Y | switch repair/P&C wiring | Line | 1164L (816s Petrolia - EPCOR Riverview) |  | 240 kV, Creates Radial Feeds, Firm Load Loss
ALTALINK | 545s T1 (545s Provost), 715L (545s Provost - 650s Hansman Lake), 715L (648s Metiskow - 650s Hansman Lake) | 2020-11-30 07:00 | 2020-12-04 18:00 | N | N | removing mobile substation and energizing new 138kV bus and associated equipment | Transformer, Line | 715L (545s Provost - 650s Hansman Lake), 715L (648s Metiskow - 650s Hansman Lake) | Removing mobile substation and energizing new 138kV Bus and associated equipment | For Information Only
EPCOR | 657s T1 (657s Summerside) | 2020-11-30 07:00 | 2020-11-30 17:00 | N | Y | breaker and tap changer maintenance | Transformer | 657s T1 (657s Summerside) | SU1T1 Breaker Maintenance and TX1 Tap Changer Maintenance | 240 kV, For Information Only
EPCOR | 72LH8 (803s Lambton - Hardisty), 72LS24 (803s Lambton - Strathcona) | 2020-11-30 07:00 | 2020-12-10 16:00 | N | N | Line protection cutover | Line | 72LS24 (Strathcona - 803s Lambton), 72LH8 (Hardisty - 803s Lambton) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 704L (51s Wainwright - 478s Tucuman) | 2020-11-30 07:00 | 2020-11-30 18:00 | N | N | scope of work includes maintenance on structure 286 | Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 89s 252 (89s Ellerslie) | 2020-11-30 07:30 | 2020-12-04 17:30 | N | Y | replace CT252 | Circuit Breaker | 89s 252 (89s Ellerslie) |  | 240 kV, Contingency Requires Mitigation
ENMAX | 27.1TR (ENMAX 27) | 2020-11-30 08:00 | 2020-12-02 16:00 | N | N | NGR installation | Transformer | 27.1TR (ENMAX 27) |  | For Information Only
ENMAX | 8B138-3A0 (ENMAX 8), 8B138-4A0 (ENMAX 8), 1.83L (ENMAX 1 - ENMAX 8) | 2020-11-30 08:00 | 2020-12-03 16:00 | N | N | maintenance GIS switches | Circuit Breaker, Line | 1.83L (ENMAX 1 - ENMAX 8) | GIS Switch maintenance. 8SW3A52, 8SW3A2, 8SW4A1, 8SW3A10, 8SW4A51, 8SW3A8, 8SW3A01 | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L09 (763s Hanna - 776s Richdale) | 2020-11-30 08:00 | 2020-12-02 17:00 | N | N | crossarm and insulator replacements | Line | 6L09 (763s Hanna - 776s Richdale) | crossarm and insulator replacements | Creates Radial Feeds, Firm Load Loss
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-11-30 09:00 | 2020-12-04 17:00 | Y | Y | structure refurbishment | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Overload, Pre-Condition
EPCOR | 72NW15 (Namao - Woodcroft) | 2020-11-30 09:30 | 2020-12-16 14:00 | N | N | line maintenance and upgrades | Line | 72NW15 (Namao - Woodcroft) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 730L (285s East Camrose - 732L) | 2020-11-30 12:15 | 2020-12-03 17:45 | N | N | component replacements complete remaining work structures range 64-196 - south section of 730L | Line | 730L (285s East Camrose - 732L) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 61s T1 (61s Lodgepole) | 2020-12-01 07:00 | 2020-12-01 18:00 | N | N | separating out alarms in transformer for ACC visibility enhancement project | Transformer | 61s T1 (61s Lodgepole) |  | For Information Only
EPCOR | 657s T2 (657s Summerside) | 2020-12-01 07:00 | 2020-12-01 17:00 | N | Y | SU2T2 breaker maintenance | Transformer | 657s T2 (657s Summerside) |  | 240 kV, For Information Only, Pre-Condition
ALTALINK | 5s 1152 (5s East Calgary), 5s 1252 (5s East Calgary), 936L (5s East Calgary - 102s Langdon) | 2020-12-01 07:15 | 2020-12-03 17:45 | N | Y | urgent replace C-phase (CT43572) on 5s1152 due to leaking SF6 | Circuit Breaker, Line | 936L (5s East Calgary - 102s Langdon) |  | 240 kV, Pre-Condition, Affects Cranking Path
ALTALINK | 245s T1 (245s Horseshoe) | 2020-12-01 07:15 | 2020-12-03 16:45 | N | Y | 138kV CT replacement (245s T1) | Transformer | 245s T1a (245s Horseshoe) |  | Restricts Generation
ALTALINK | 226s Garden City RTU/SCADA | 2020-12-01 08:00 | 2020-12-01 15:34 | N | N | telemetry outages for network configuration changes | Terminal Equipment |  |  | Affects Visibility
ENMAX | 162.1TR (162s Beddington), 162s 138-RB86 (162s Beddington), 162s 138_RB94 (162s Beddington), 162s 240-RB131 (162s Beddington), 162s 240-RB134 (162s Beddington) | 2020-12-01 08:00 | 2020-12-04 16:00 | N | Y | RTU & line protection upgrade & settings changes | Transformer, Circuit Breaker | 162.1TR (162s Beddington) |  | 240 kV, Contingency Requires Mitigation, Firm Load Loss, Pre-Condition
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2020-12-01 08:00 | 2020-12-14 16:00 | N | Y | install new tap for new substation 604s Granum & OPGW repairs between structures 515-520 (P1879) | Line | P1879 Claresholm Solar. V.Chan 11/4/2020 |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition, Restricts Generation
ALTALINK | 1005L (120s Picture Butte - 356s Milo) | 2020-12-01 08:00 | 2020-12-01 18:00 | N | Y | urgent *P5 1005L206 conductor damage | Line |  |  | 240 kV, Pre-Condition
ALTALINK | 15s 180N (15s Fort Macleod) | 2020-12-01 09:30 | 2020-12-11 16:30 | N | N | implement and test new RAS scheme | Circuit Breaker | 15s 180N (15s Fort Macleod), 180L (15s Fort Macleod - 928s East Stavely) |  | For Information Only
ALTALINK | 519L (996s Imperial Oil Carson Lake - 519AL), 519AL (661s Laura Lake - 519L tap), 519L (519AL - 526L) | 2020-12-02 07:00 | 2020-12-03 18:00 | N | N | fire mitigation | Line | 519AL (661s Laura Lake - 519L tap), 519L (996s Imperial Oil Carson Lake - 519AL), 519L (519AL - 526L) |  | For Information Only
ALTALINK | 162L (229s Glenwood - 415s Drywood) | 2020-12-02 07:00 | 2020-12-02 18:00 | N | N | *P5 162L Str's 32, 170, 210 Loose Dampers | Line |  |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Restricts Generation
ALTALINK | 925L (63s Red Deer - 74s Janet) | 2020-12-02 07:15 | 2020-12-03 17:45 | N | Y | maintenance on strs 27, 29, 37, 38 | Line | 925L (63s Red Deer - 74s Janet) |  | 240 kV, Pre-Condition
ALTALINK | 1082L (63s Red Deer - 287s Hazelwood) | 2020-12-02 07:15 | 2020-12-03 17:45 | N | Y | maintenance on strs 27, 29, 37 38 | Line | 1082L (63s Red Deer - 287s Hazelwood) |  | 240 kV, Pre-Condition
ALTALINK | 85L (35s Rundle - 54L tap) | 2020-12-02 07:15 | 2020-12-03 17:45 | N | N | maintenance on structure 1 | Line | 85L (35s Rundle - 54L tap) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ENMAX | 65B138-D81 (ENMAX 65), 65B138-D82 (ENMAX 65), 24.82L (ENMAX 24 - ENMAX 65) | 2020-12-02 08:00 | 2020-12-02 16:00 | N | N | replace structure 138-24.82-27 | Circuit Breaker, Line | 24.82L (ENMAX 24 - ENMAX 65) | Replace structure 138-24.82-27. Heater Circuit Contactor Upgrades 65B138-D82, 65B138-D81 | Pre-Condition
ALTALINK | 33s 6 (33s Spray) | 2020-12-02 08:00 | 2020-12-02 17:00 | N | Y | maintenance | Switch | 33s 6 (33s Spray) |  | Restricts Generation
SUNCOR | 139s Hillridge RTU/SCADA | 2020-12-02 08:00 | 2020-12-02 16:00 | N | N | telemetry outages for network configuration changes | Terminal Equipment |  |  | Affects Visibility
ATCO | 6L09 (772s Youngstown - 776s Richdale) | 2020-12-02 08:00 | 2020-12-03 17:00 | N | N | crossarm and insulator replacements | Line | 6L09 (772s Youngstown - 776s Richdale) | crossarm and insulator replacements | Creates Radial Feeds, Firm Load Loss, For Information Only, Pre-Condition
ATCO | 7L95 (715s Leming Lake - 889s Mahkeses) | 2020-12-02 09:00 | 2020-12-03 09:00 | N | Y | urgent breaker maintenance and tie in bus lockout logic | Line |  | Urgent | Restricts Generation
ENMAX | 41.2TR (ENMAX 41) | 2020-12-03 08:00 | 2020-12-03 16:00 | N | N | replacement of external control wiring | Transformer |  |  | For Information Only
ENMAX | 27.2TR (ENMAX 27) | 2020-12-03 08:00 | 2020-12-05 16:00 | N | N | NGR installation | Transformer | 27.2TR (ENMAX 27) |  | For Information Only, Pre-Condition
MONTANA | MATL (120s Picture Butte - Montana) | 2020-12-03 12:00 | 2020-12-03 18:00 | N | Y | emergency PST outage to investigate & repair oil leak | Line |  |  | 240 kV, Pre-Condition, Limits ATC
CapitalPower | 615s Halkirk RTU/SCADA | 2020-12-03 23:00 | 2020-12-04 06:00 | N | N | Telus network maintenance | Terminal Equipment |  |  | Affects Visibility
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2020-12-04 08:00 | 2020-12-04 16:00 | N | N | crew setting streetlight near line and routine maintenance on line | Line | 3.82L (ENMAX 3 - ENMAX 8) | Crew setting streetlight near line. Routine maintenance on line. Switching must be done before and after 2.84L outage at 8sub. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 417L (55s Olds - 281s Johnson) | 2020-12-04 08:00 | 2020-12-04 18:00 | N | Y | urgent fix broken conductor strands 55s79 | Line |  | Urgent fix broken conductor strands 55s79 | Creates Radial Feeds, Firm Load Loss, Restricts Generation
ENMAX | 9.80L (ENMAX 9 - ENMAX 31) | 2020-12-05 08:00 | 2020-12-05 16:00 | N | N | SF6 gas sample retest | Line | 9.80L (ENMAX 9 - ENMAX 31) | 9B138-9.80 SF6 gas sample retest | For Information Only, Pre-Condition
ENMAX | 2.82L (ENMAX 2 - ENMAX 5) | 2020-12-05 08:00 | 2020-12-05 18:00 | N | N | cable sheath test | Line | 2.82L (ENMAX 2 - ENMAX 5) |  | For Information Only, Pre-Condition
Syncrude | Syncrude Mildred Lake | 2020-12-05 08:00 | 2020-12-09 20:00 | N | N | operation of circuit breaker 18215 | Station |  | Non-Significant Outage: 31-0-PC15-1 Substation Cap Bank in Plant 31 Substation The following circuit breaker will be operated: 18215 | For Information Only
ENMAXEC | 383S Kettles Hill Windfarm | 2020-12-05 21:15 | 2020-12-05 23:55 | N | N | replace network firewalls | Station |  |  | For Information Only
ALTALINK | 452L (367s Harry Smith - 434s Stony Plain) | 2020-12-06 07:00 | 2020-12-06 18:00 | N | N | maintenance on structure 7 | Line | 452L (367s Harry Smith - 434s Stony Plain) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 1083L (63s Red Deer - 288s Wolf Creek) | 2020-12-06 07:15 | 2020-12-07 17:45 | N | Y | maintenance on strs 133, 135, 154 | Line | 1083L (63s Red Deer - 288s Wolf Creek) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Affects Cranking Path
ENMAX | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | 2020-12-06 08:00 | 2020-12-06 18:00 | N | N | GIS switch maintenance | Line | 2.83L (ENMAX 2 - ENMAX 5 - ENMAX 13) | GIS Switch Maintenance 2MD138-2.83_2.83G, 2SW2.83G | For Information Only, Pre-Condition
ALTALINK | 780L (38s East Edmonton - 522s Cooking Lake) | 2020-12-07 07:00 | 2020-12-07 18:00 | N | N | maintenance on structures 83, 86 and 87 | Line | 780L (38s East Edmonton - 522s Cooking Lake) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ATCO | 6L09 (772s Youngstown - 776s Richdale) | 2020-12-07 08:00 | 2020-12-10 17:00 | N | N | crossarm and insulator replacements | Line | 6L09 (772s Youngstown - 776s Richdale) | crossarm and insulator replacements | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 11.83L (162s Beddington - ENMAX 11) | 2020-12-07 08:00 | 2020-12-10 16:00 | N | N | RTU & line protection upgrade | Line | 11.83L (162s Beddington - ENMAX 11) | RTU & Line Protection Upgrade. Settings changes. | Creates Radial Feeds, Firm Load Loss
ENMAX | 2.80L (ENMAX 2 - ENMAX 23) | 2020-12-07 08:00 | 2020-12-18 16:00 | N | N | breaker overhaul | Line | 2.80L (ENMAX 2 - ENMAX 23) | Hitachi HV Breaker Overhaul 23B138-2.80. GIS Minor Maintenance 2B138-D94, 2B138-D93. GIS Switch Maintenance 2MD105_105G, 2MD106_106G, 2MD138-2.80_2.80G, 2SW2.80G | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 14.1TR (ENMAX 14) | 2020-12-07 08:00 | 2020-12-08 16:00 | N | N | 14B8-14.1TR breaker racking adjustment | Transformer |  |  | For Information Only
ENMAX | 12.1TR (ENMAX 12) | 2020-12-07 08:00 | 2020-12-09 16:00 | N | N | installation NGR | Transformer | 12.1TR (ENMAX 12) |  | For Information Only
ENMAX | 6.82L (ENMAX 6 - ENMAX 41) | 2020-12-07 08:00 | 2020-12-18 16:00 | N | N | maintenance | Line |  | Transmission Line Pole Relocation. Phasing required. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 3.82L (ENMAX 3 - ENMAX 8) | 2020-12-07 08:00 | 2020-12-10 16:00 | N | N | GIS switch maintenance | Line | 3.82L (ENMAX 3 - ENMAX 8) | GIS Switch maintenance. 8SW5A8, 8SW5A01, 8SW5A10, 8SW6A51, 8SW5A52, 8SW6A1. 8SW5A2 | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 17s 637 (17s Benalto), 637L (17s Benalto - 580s Sylvan Lake) | 2020-12-07 09:00 | 2020-12-11 12:30 | N | N | replace 17s637 breaker fail and control module | Circuit Breaker, Line | 17s 637 (17s Benalto), 637L (17s Benalto - 580s Sylvan Lake) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 611L (186s Dry Creek - 391S Balzac) | 2020-12-07 09:00 | 2020-12-07 18:00 | N | N | work includes maintenance on structures 8 and 79. | Line | 611L (186s Dry Creek - 391S Balzac) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition,Affects Cranking Path
EPCOR | T3 (Strathcona) | 2020-12-07 09:00 | 2020-12-10 16:00 | N | N | emergency outage for Strathcona SVT02 replacement | Transformer |  |  | For Information Only, Pre-Condition
ALTALINK | 205S Castle Rock Ridge | 2020-12-07 09:00 | 2020-12-07 18:00 | N | Y | feeder1 and feeder4 outage to replace two T bodies | Station |  |  | Restricts Generation
ALTALINK | 777L (48s Pocaterra - 245s Seebe) | 2020-12-07 09:00 | 2020-12-07 18:00 | N | Y | urgent 777L136 uplift concerns-install hold down arm | Line |  | urgent 777L136 uplift concerns-Will install Hold Down Arm | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 310p T30 (310p Sundance) | 2020-12-07 09:15 | 2020-12-08 16:30 | N | Y | move T30 tapchanger indication from old RTU to new RTU | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 378s 552 (378s Shell Caroline) | 2020-12-07 09:30 | 2020-12-10 16:00 | N | N | emergency replace breaker fail relay and breaker control module | Circuit Breaker | 378s 552 (378s Shell Caroline) |  | Contingency Requires Mitigation
ATCO | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | 2020-12-07 10:00 | 2020-12-14 15:00 | N | Y | Replacement of under rated and rotten crossarms | Line | 7L20 (740s H.R.Milner - 810s Dome Cutbank) | Replacement of under rated and rotten crossarms | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation, Affects Cranking Path
ALTALINK | 730L (285s East Camrose - 732L) | 2020-12-07 12:00 | 2020-12-09 18:00 | N | N | component replacements complete remaining work Structures Range 64-196 | Line | 730L (285s East Camrose - 732L) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Pre-Condition
ALTALINK | 993s T1 (993s Abee) | 2020-12-08 07:00 | 2020-12-08 16:00 | N | N | connecting new 993s T2 | Transformer | 993s T1 (993s Abee), 7L437 (947s Weasel Creek - 993s Abee) |  | For Information Only
ALTALINK | 56s Boyle 138 kV Bus 2, 710L (56s Boyle - 159s Colinton), 56s 652 (56s Boyle), 56s C1 (56s Boyle), 56s T2 (56s Boyle) | 2020-12-08 07:00 | 2020-12-09 18:00 | N | N | replace 56s27 circuit switcher - with new 56s1252 SF6 breaker & 56s28 switch | Bus, Line, Circuit Breaker, Shunts, Transformer | 56s T2 (56s Boyle), 56s Boyle 138 kV Bus 2, 56s C1 (56s Boyle), 710L (56s Boyle - 159s Colinton) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Over/Under Voltage, Overload, Pre-Condition
ALTALINK | 901L (63s Red Deer - 901AL), 901L (74s Janet - 901AL), 901AL (64s East Crossfield - 901L) | 2020-12-08 07:00 | 2020-12-09 18:00 | N | Y | maintenance on strs 26, 28, 36 and 37 | Line | 901AL (64s East Crossfield - 901L), 901L (74s Janet - 901AL), 901L (63s Red Deer - 901AL) |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition, Affects Cranking Path
ENMAX | 2.80L (ENMAX 2 - ENMAX 23), 23.3TR (ENMAX 23) | 2020-12-08 08:00 | 2020-12-09 18:00 | N | N | fall substation washing | Line, Transformer |  |  | Creates Radial Feeds, Firm Load Loss
ENMAX | 21.61L (ENMAX 21 - ENMAX 34) | 2020-12-08 08:00 | 2020-12-13 16:00 | N | N | 34.2TR & 34.3TR replacement-grounding study | Line |  |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
BCH | 1L274 (48s Pocaterra - Britt Creek) | 2020-12-08 09:00 | 2020-12-18 17:00 | Y | Y | structure refurbishment | Line | 1L274 (48s Pocaterra - Britt Creek) |  | Creates Radial Feeds, Firm Load Loss, Limits ATC, Over/Under Voltage, Pre-Condition
ALTALINK | 58s 35 (58s Edson), 58s C1 (58s Edson) | 2020-12-08 09:30 | 2020-12-08 16:30 | N | N | SPRC5 test breaker | Circuit Breaker, Shunts | 58s C1 (58s Edson) |  | Pre-Condition
ALTALINK | 308s 773E (308s Albchem Beaverhill Creek), 773L (127s Bruderheim - 308s Albchem Beaverhill Creek) | 2020-12-08 13:00 | 2020-12-10 16:00 | N | N | forced outage | Circuit Breaker, Line |  |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 789L (898s Heart Lake - 1034s Margie) | 2020-12-09 07:00 | 2020-12-09 18:00 | N | Y | maintenance work on Str 185 | Line | 789L (898s Heart Lake - 1034s Margie) | Urgent request | For Information Only
ALTALINK, WINDYPWPL, VISIONREQ, ATCO | 312s T1 (312s Fidler), 312s 138 kV BUS 1 (312s Fidler), 624L (312s Fidler - 354s Summerview), 893L (312s Fidler - 893AL), 112S Windy Point, 354S Summerview, 806S Oldman River | 2020-12-09 07:15 | 2020-12-09 17:15 | N | Y | urgent repair attempt repair / oil top up of VT22 one phase has a slow leak | Transformer, Bus, Line, Station | 624L (312s Fidler - 354s Summerview), 893L (312s Fidler - 893AL), 312s T1 (312s Fidler) |  | Firm Load Loss, Restricts Generation
ALTALINK | 69s T2 (69s North Barrhead) | 2020-12-09 08:00 | 2020-12-09 16:00 | N | N | T2 tap change and testing | Transformer | 69s T2 (69s North Barrhead) |  | For Information Only
ENMAX | 14.2TR (ENMAX 14) | 2020-12-09 08:00 | 2020-12-10 16:00 | N | N | 14B8-14.2TR breaker racking adjustment and oil sampling TC | Transformer |  |  | For Information Only
ALTALINK | 310p T36 (310p Sundance) | 2020-12-09 09:15 | 2020-12-10 16:30 | N | Y | move T36 tapchanger indication from old RTU to new RTU | Transformer |  |  | 240 kV, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 250p 11 (250p Bighorn Plant) | 2020-12-09 11:00 | 2020-12-09 15:00 | N | Y | maintenance | Switch | 250p 11 (250p Bighorn Plant) | Brushgear | Restricts Generation
ENMAX | 1.80L (ENMAX 1 - ENMAX 28) | 2020-12-10 07:00 | 2020-12-10 16:00 | N | N | conductor scanning on circuit | Line | 1.80L (ENMAX 1 - ENMAX 28) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 897L (38s East Edmonton - 45s Bretona) | 2020-12-10 07:00 | 2020-12-10 18:00 | N | N | fire mitigation on structures #57, 83 & 96 | Line | 897L (38s East Edmonton - 45s Bretona) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 180L (15s Fort Macleod - 928s East Stavely) | 2020-12-10 07:15 | 2020-12-10 17:45 | N | Y | maintenance on Str 540 | Line | 180L (15s Fort Macleod - 928s East Stavely) |  | Restricts Generation
EPCOR | K722 (Kennedale) | 2020-12-10 08:30 | 2020-12-10 16:00 | N | N | substation switching school isolation | Circuit Breaker | K722 (Kennedale), |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss
ALTALINK | 250p 22 (250p Bighorn Plant) | 2020-12-10 09:00 | 2020-12-10 13:00 | N | Y | maintenance | Switch | 250p 22 (250p Bighorn Plant) |  | Restricts Generation
ALTALINK | 17s 91 (17s Benalto) | 2020-12-10 10:00 | 2020-12-10 12:00 | N | N | trip test 17s92 from new s637 breaker fail | Switch | 17s 92 (17s Benalto) |  | Contingency Requires Mitigation, For Information Only
ENMAX, ALTALINK | 21.80L (42s Sarcee - ENMAX 21) | 2020-12-11 07:00 | 2020-12-11 16:00 | N | Y | conductor scanning on circuit | Line | 21.80L (42s Sarcee - ENMAX 21) |  | For Information Only, Pre-Condition
ENMAX | 34.2TR (ENMAX 34) | 2020-12-11 08:00 | 2020-12-11 16:00 | N | N | rack in new ground buggy | Transformer |  | 34.2TR Outage to rack in new ground buggy | For Information Only
ALTALINK | 1212L (12s Heartland - 89s Ellerslie) | 2020-12-11 08:00 | 2020-12-13 18:00 | N | Y | urgent repair - reposition dampers | Line | 1212L (12s Heartland - 89s Ellerslie) | *P5 Urgent repair 1212L Reposition Dampers 1212L Str's 29,130,145,148 See also 1206L Recloser block SAP 273058 that goes with this due to proximity | 500 kV, Pre-Condition
AESO-SC | CLR1 Claresholm Solar | 2020-12-11 08:00 | 2021-03-10 17:00 | N | N | P1879 Solar Connection ISD Jan 25, 2021, 130 MW | Unit
ATCO | 893S Caven Dish | 2020-12-11 08:00 | 2020-12-25 18:00 | N | N | P865 TransCanada Keystone KXL Pumpstation #5-Cavendish, ISD Dec 18, 2020 | Station |  | P0865 TransCanada Keystone KXL Pumpstation #5-Cavendish | For Information Only
ENMAX | 22.81L (ENMAX 22 - ENMAX 39), 39B138-22.81 (ENMAX 39), 22B138-22.81 (ENMAX 22) | 2020-12-12 08:00 | 2020-12-12 16:00 | N | N | replace structure 138-22.81-9 | Line, Circuit Breaker | 22.81L (ENMAX 22 - ENMAX 39) |  | Creates Radial Feeds, Firm Load Loss
ALTALINK | 17s T3 (17s Benalto), 17s 2852 (17s Benalto) | 2020-12-13 09:30 | 2020-12-21 17:30 | N | Y | emergency work: T3 repair and oil work and inspections | Transformer, Circuit Breaker |  |  | 240 kV, Contingency Requires Mitigation
ALTALINK, ENMAX | 5s T2 (5s East Calgary), ENMAX 2 138kV Z32 Bus | 2020-12-13 10:30 | 2020-12-22 17:30 | N | Y | T2: drain the tank, internal inspection/possible repair, vac fill, test | Transformer, Bus |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | T1 (Meadowlark) | 2020-12-14 07:00 | 2020-12-14 17:00 | N | N | oil leak repair | Transformer | T1 (Meadowlark) |  | For Information Only
ALTALINK | 812L (65s High RIver - 392s Black Diamond), 812AL (512s Hartell - 812L) | 2020-12-14 07:15 | 2020-12-14 17:15 | N | N | maintenance | Line | 812L (65s High RIver - 392s Black Diamond) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 928L (17s Benalto - 42s Sarcee) | 2020-12-14 07:15 | 2020-12-16 17:45 | N | Y | maintenance on structures | Line | Scope of work includes maintenance on structures 340, 355, 365 and 381 |  | 240 kV, For Information Only
ATCO | 6L09 (767s Oyen - 6L21 tap) | 2020-12-14 08:00 | 2020-12-17 17:00 | N | N | crossarm and insulator replacements | Line | 6L09 (767s Oyen - 6L21 tap) | crossarm and insulator replacements | Pre-Condition
ENMAX | 16.60L (ENMAX 16 - ENMAX 34) | 2020-12-14 08:00 | 2020-12-18 16:00 | N | N | drilling wells directly under line | Line |  | 34.2TR & 34.3TR Replacement-Grounding Study. Drilling wells directly under line. | Creates Radial Feeds, Firm Load Loss, Pre-Condition
ENMAX | 40.1TR (ENMAX 40) | 2020-12-14 08:00 | 2020-12-14 12:00 | N | N | oil sampling TR, TC | Transformer |  |  | For Information Only
ENMAX | 1.8TR (ENMAX 1) | 2020-12-14 08:00 | 2020-12-14 12:00 | N | N | oil Sampling TC and check reversing switch | Transformer |  |  | For Information Only
VISIONREQ | 354S Summerview | 2020-12-14 08:00 | 2020-12-16 17:00 | N | N | windcharger work | Station |  |  | For Information Only, Restricts Generation
ALTALINK | 17s T3 (17s Benalto), 17s 46 (17s Benalto), 17s 2852 (17s Benalto) | 2020-12-14 10:30 | 2020-12-14 13:30 | N | Y | maintenance | Transformer, Switch, Circuit Breaker | 17s T3 (17s Benalto), 17s 46 (17s Benalto) |  | 240 kV, For Information Only, Pre-Condition
ENMAX | 1.5TR (ENMAX 1) | 2020-12-14 12:00 | 2020-12-14 16:00 | N | N | oil sampling TC check reversing switch | Transformer |  |  | For Information Only
ALTALINK | 1206L (12s Heartland - 89s Ellerslie) | 2020-12-14 12:00 | 2020-12-18 18:00 | N | Y | maintenance | Line | 1206L (12s Heartland - 89s Ellerslie) |  | 500 kV, Pre-Condition
ALTALINK | 717L (17s Benalto - 262s Rocky Mountain House) | 2020-12-14 13:30 | 2020-12-14 17:00 | N | Y | trip test 17s717W from new s637 breaker fail | Line | 717L (17s Benalto - 262s Rocky Mountain House) |  | Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Overload, Pre-Condition, Restricts Generation
ALTALINK | 54L (118s Canmore - 85L) | 2020-12-15 07:00 | 2020-12-18 18:00 | N | N | structure maintenance | Line | 54L (118s Canmore - 85L) |  | Creates Radial Feeds, Firm Load Loss, Pre-Condition
EPCOR | 240BA2 (629s Argyll Transfer Station - 814s Bellamy) | 2020-12-15 07:00 | 2020-12-15 16:00 | N | Y | emergency outage top up low SF6 on Phase 1 on BDS13 compartment | Line |  |  | 240 kV, Contingency Requires Mitigation, Creates Radial Feeds, Firm Load Loss, Pre-Condition
ALTALINK | 919L (77s Sagitawah - 310p Sundance) | 2020-12-15 07:00 | 2020-12-15 18:00 | N | Y | urgent repair on span 125 | Line |  |  | Contingency Requires Mitigation, Overload, Pre-Condition, Affects Cranking Path
ALTALINK | 392s T3 (392s Black Diamond), 812L (392s Black Diamond - 812AL) | 2020-12-15 07:15 | 2020-12-16 17:15 | N | N | demolish 392s20 and install rigid bus bypass, demolish 392s3 and install standoff glass with flex bus and bird cover on both modifications | Transformer, Line | 392s T3 (392s Black Diamond), 812L (392s Black Diamond - 812AL) | Demolish 392s20 and install rigid bus bypass. Demolish 392s3 and install standoff glass with flex bus. Bird cover on both modifications. | Creates Radial Feeds, Firm Load Loss
ENMAX | 12.1TR (ENMAX 12) | 2020-12-15 08:00 | 2020-12-17 12:00 | N | N | 12BA8-12.1TR breaker replacement | Transformer |  |  | For Information Only
ENMAX | 3.4TR (ENMAX 3) | 2020-12-15 08:00 | 2020-12-15 16:00 | N | N | oil sampling TC and check reversing switch | Transformer |  |  | For Information Only